## JDE Supply Plan
Westrac West - May 2026 Thiess Supplier Plan
Westrac West - May 2026 Thiess Supplier Plan
State | Site | Unit Number | Unit Description | Service Type | Service Type Description | JDE Forecast Date | Frequency | Last Completed Date | Last Completed SMU | Approved Start Date | PO Promised Delivery Date | Start Date Change From Last Month | WO Number | Ship To Destination | PO Number | Qty # | Part Number | PN # Description
State | Site | Unit Number | Unit Description | Service Type | Service Type Description | JDE Forecast Date | Frequency | Last Completed Date | Last Completed SMU | Approved Start Date | PO Promised Delivery Date | Start Date Change From Last Month | WO Number | Ship To Destination | PO Number | Qty # | Part Number | PN # Description | LTP - Commens | Comments | Status | Estimated Ship Date | Will this make Thiess Required by Date?
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486572 | FleetCo (WA) LTP | 8345804 | 1 | 10R-2075 | TURBO, D10T, REMAN
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486572 | FleetCo (WA) LTP | 8345804 | 1 | 10R-2075 CORE CHARGE | CORE DEPOSIT 10R-2075
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 2 | 175-2582 | RING SEAL
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 9N-9545 | ELBOW
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 175-2583 | RING SEAL
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 7E-8630 | HOSE
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 251-6775 | HOSE
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 9N-1941 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 127-0929 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 7C-3910 | HOSE
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 2 | 114-9223 | SPACER
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 8C-3089 | SEAL
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 8 | 9X-2201 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 2 | 106-1793 | STUD
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 2 | 2N-2765 | BOLT
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 210-9246 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 239-5609 | CLAMP TBOLT
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 2 | 5L-8854 | RING SEAL
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 1S-4295 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 457-9164 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 4 | 2N-2766 | LOCKNUT
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 136-7227 | SEAL
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 2 | 284-3502 | CLAMP-BAND
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 8L-2746 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 4 | 341-9211 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 7N-7559 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 3 | 180-8424 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-14 |  | 8486572 | FleetCo (WA) LTP | 8345805 | 1 | 4P-4460 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345806 | 1 | 10R-2075 | TURBO, D10T, REMAN
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345806 | 1 | CORE CHARGE | CORE DEPOSIT 10R-2075
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 2 | 175-2582 | RING SEAL
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 9N-9545 | ELBOW
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 175-2583 | RING SEAL
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 7E-8630 | HOSE
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 251-6775 | HOSE
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 9N-1941 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 127-0929 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 7C-3910 | HOSE
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 8C-3089 | SEAL
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 8 | 9X-2201 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 4 | 2N-2765 | BOLT
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 239-5609 | CLAMP TBOLT
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 2 | 5L-8854 | RING SEAL
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 1S-4295 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 457-9164 | CLAMP
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 6V-5050 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 4 | 2N-2766 | LOCKNUT
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 136-7227 | SEAL
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 2 | 284-3502 | CLAMP-BAND
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 8L-2746 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 4 | 341-9211 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 7N-7559 | GASKET
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 3 | 180-8424 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486574 | FleetCo (WA) LTP | 8345807 | 1 | 4P-4460 | GASKET
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 1 | 222-2187 | HOSE AS (SUPPLY)
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 1 | 8C-3089 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 1 | 238-5081 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 1 | 238-5080 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 1 | 2M-9780 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 1 | 7J-9108 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 2 | 3B-1915 | BOLT
WA |  | DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486575 | FleetCo (WA) LTP | 8345809 | 2 | 5M-2894 | WASHER
WA |  | DZ3430 | Cat D10T | N9020 | Alternator | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-11 |  | 8486577 | FleetCo (WA) LTP | 8345810 | 1 | 350-1223 | V-BELT BAND
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 593-7750 | REGULATOR-TEMPERATURE (92-DEG
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 391-4605 | HOSE
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 398-7199 | HOSE AS
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 9Y-9236 | GAUGE-SIGHT
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 398-7197 | HOSE AS
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 398-7198 | HOSE AS
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 7S-8780 | HOSE
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 6V-8775 | TEE-FACE SEAL
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 4 | 209-4588 | CLAMP
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 3S-9643 | SEAL-LIP TYPE (WATER TEMPERATU
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 236-5423 | HOSE
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 7X-7958 | CLAMPS
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 215-4013 | CLAMPS
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 3 | 109-0076 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 4 | 209-4590 | CLAMP AS BAND
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 259-8303 | GASKET
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 107-5769 | SEAL-O-RING (TEMPERATURE REGUL
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 200-6410 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 9 | 106-4572 | HOSE
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 3B-0622 | PLUG-CUP
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 111-4374 | VALVE AS-VENT LINE
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 3 | 8T-1703 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 3 | 219-4474 | GASKET
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 5 | 231-4708 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 9M-3116 | GASKET
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 7M-8485 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 7M-8485 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 3D-2824 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 35 | 1P-4278 | CLAMP-HOSE
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 6V-5063 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 7C-0307 | GASKET
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 13 | 371-8952 | HOSE 13CM
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 6V-9746 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 3 | 3K-0360 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 2 | 3K-0360 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 6V-6609 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 6 | 6V-8398 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 21 | 371-8950 | HOSE (21-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 12 | 371-8950 | HOSE (12-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 3J-1907 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 4 | 3J-7354 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 1 | 6V-9027 | SEAL-O-RING
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 45 | 371-8094 | HOSE (44.5-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 52 | 371-8094 | HOSE (52-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 180 | 8C-3681 | HOSE (180-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 26 | 5P-1465 | HOSE (25.5-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 35 | 5P-1465 | HOSE (34.5-CM)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 24 | 5P-1465 | HOSE (24-CM EACH)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 10 | 5P-1465 | HOSE (8-CM EACH)
WA |  | DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 2025-10-29 | 6000 | 2023-04-03 | 24801 | 2026-06-01 | 2026-05-18 |  | 8486576 | FleetCo (WA) LTP | 8351375 | 129 | 5P-1465 | HOSE (128.8-CM)
WA | Iron Bridge | RD4921 | Cat 793F | N1310 | Radiator | 2026-01-19 | 24000 | 2021-06-11 | 45510 | 2026-06-04 | 2026-05-15 |  | 8340925 |  | 8249045 | -1 | 2900574FIH | 793F RADIATOR GRP
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 349-7119 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 274-1707 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 224-8171 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 7E-8630 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 9N-1941 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 127-0929 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 241-9265 | CLAMP-MUFFLE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 8T-4988 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 8C-3089 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 5P-3860 | CLAMP-BAND | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 2 | 216-2211 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 2 | 208-7448 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 5P-0599 | CLAMP-BAND | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 1 | 237-0226 | CLAMP-TBOLT | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 24 | 541-7154 | SLEEVE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1100 | Turbo Primary | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486464 | FleetCo (WA) LTP | 8344656 | 30 | 541-7154 | SLEEVE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 314-9284 | HOSE AS | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 136-9141 | LINE-FUEL | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 5P-4889 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 7V-6571 | GROMMET | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 107-5769 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 2 | 238-5080 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 228-7090 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 214-7568 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 228-7089 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 2M-9780 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486466 | FleetCo (WA) LTP | 8344658 | 1 | 6V-8398 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 291-6388 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 151-8190 | CLAMP-CYL | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 248-5513 | REGULATOR | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 163-2919 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 239-8135 | VALVE AS | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 3S-9643 | SEAL, O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 227-5075 | SEAL | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 224-6361 | SEAL | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 4 | 208-6054 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 2 | 209-4577 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 2 | 209-4575 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 2 | 8T-1117 | CLAMP-HO | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 5P-4961 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 2 | 7L-6580 | SEAL,O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 2 | 5D-1026 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 5D-1026 | CLAMP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 9X-7380 | SEAL | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 1 | 3D-2824 | SEAL, O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 16 | 371-8946 | HOSE (CM) | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 16 | 371-8946 | HOSE (CM) | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 161 | 371-8094 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 71 | 5P-0767 | HOSE, CM STK | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 133 | 9X-2133 | HOSE, STK, CM | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1300 | Cooling Sys Service | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486467 | FleetCo (WA) LTP | 8345813 | 234 | 6V-8523 | HOSE | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1400 | Belt Tensioner Assembly | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486469 | FleetCo (WA) LTP | 8345820 | 1 | 211-7895 | TENSIONER - | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1400 | Belt Tensioner Assembly | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486469 | FleetCo (WA) LTP | 8345820 | 1 | 197-9642 | PULLEY AS.-IDLER | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1400 | Belt Tensioner Assembly | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486469 | FleetCo (WA) LTP | 8345820 | 1 | 348-7889 | BELT | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1400 | Belt Tensioner Assembly | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486469 | FleetCo (WA) LTP | 8345820 | 1 | 8T-4178 | BOLT | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1400 | Belt Tensioner Assembly | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486469 | FleetCo (WA) LTP | 8345820 | 1 | 8T-4121 | WASHER-HARD | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 2025-12-17 | 7000 | 2021-04-04 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486470 | FleetCo (WA) LTP | 8345821 | 2 | 2T-3013 | SPIDER & BEARING GP | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 2025-12-17 | 7000 | 2021-04-04 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486470 | FleetCo (WA) LTP | 8345821 | 2 | 5B-0925 | GREASE FITTINGS | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 2025-12-17 | 7000 | 2021-04-04 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486470 | FleetCo (WA) LTP | 8345821 | 8 | 290-7514 | BOLT (M12X1.75X60-MM) | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 2025-12-17 | 7000 | 2021-04-04 | 14535 | 2026-06-06 | 2026-05-11 |  | 8486470 | FleetCo (WA) LTP | 8345821 | 8 | 6V-3823 | BOLT (M12X1.75X60-MM) | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 6V-7350 | SEAL,O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 224-2675 | SEAL-PRESS I | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 225-7003 | SEAL-O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 229/8810 | SEAL-PRESS I | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 4F-7389 | SEAL, O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 6V-5063 | SEAL,O-RING | THIESS MANAGED
WA |  | GR1549 | Cat 16M | N1301 | Water Pump | 2025-12-17 | 7000 | 2023-03-16 | 14535 | 2026-06-06 | 2026-05-14 |  | 8486468 | FleetCo (WA) LTP | 8353043 | 1 | 7L-6580 | SEAL,O-RING | THIESS MANAGED
WA | Iron Bridge | RD2030 | Cat 793D | N1000 | Engine | 2026-05-04 | 20000 | 2022-10-01 | 62061 | 2026-06-11 | 2026-05-18 |  | 8091268 |  | 8307046 | 1 | 793D-EN-MOUNTS | IK,ENG-MOUNTS
WA | Iron Bridge | RD2030 | Cat 793D | N1000 | Engine | 2026-05-04 | 20000 | 2022-10-01 | 62061 | 2026-06-11 | 2026-05-18 |  | 8091268 |  | 8307046 | 1 | 793D-EN-INDUCTION | IK,ENG-INDUCTION
WA | Iron Bridge | RD2030 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 2026-05-04 | 20000 | 2022-10-01 | 62061 | 2026-06-11 | 2026-05-18 |  | 8430968 |  | 8310824 | 1 | CAT793D_N7613 | 793D-HYD-CLR-STEER
WA | Iron Bridge | RD2030 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 2026-05-04 | 20000 | 2022-10-01 | 62061 | 2026-06-11 | 2026-05-18 |  | 8430974 |  | 8312358 | 1 | 793D-AC-SERVICEMA | IK,AC-SERVICEMA
WA | Iron Bridge | DR2114 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 2026-01-18 | 15000 |  | 4460 | 2026-06-11 | 2026-04-26 | 47 | 8236523 |  | 8332946 | 1 | 6310-CYL-MSTRAI-RH | UNBUDGETED MAJOR REPAIRS
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 6060-PUMP-IMP-7-8 | IK,PUMP-IMP-7-8
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 522-4877 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 520-6586 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 577-0223 | HOSE AS
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 577-0222 | HOSE AS
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 502-3347 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 601-0549 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 583-4843 | HOSE AS
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 502-3350 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 3 | 610-6229 | HOSE AS
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 502-3345 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 634-3100 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 634-3051 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 8 | 501-0624 | FLAT WASHER
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 633-8357 | 2 WIRE HOSE
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 6V-1195 | SEAL- O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 4 | 235-2480 | RECTANGULAR SEAL
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 2 | 235-2476 | RECTANGULAR SEAL
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 1 | 109-5705 | SEAL-O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 2 | 451-2767 | SEAL-O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 8 | 8T-4141 | HEX HEAD BOLT
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 4 | 228-7093 | SEAL-O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 4 | 228-7090 | SEAL-O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 2 | 6V-0852 | CAP
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 2 | 214-7568 | SEAL-O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 16 | 228-7089 | SEAL-O-RING
WA | Iron Bridge | EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 2026-06-04 | 15000 | 2023-12-11 | 8877 | 2026-06-11 | 2026-05-18 |  | 8421108 |  | 8353898 | 6 | 451-2766 | SEAL-O-RING
WA |  | LO2121 | Cat 992K | N7232 | Hyd Motor Engine Fan | 2025-09-22 | 12000 | 2022-04-15 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488032 | FleetCo (WA) LTP | 8345844 | 1 | 0R-9340 | MOTOR FAN GP | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-L | Hyd Accum Brake Reseal LEFT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488035 | FleetCo (WA) LTP | 8345846 | 1 | 222-2367 | VALVE-GAS | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-L | Hyd Accum Brake Reseal LEFT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488035 | FleetCo (WA) LTP | 8345846 | 1 | 3D-2824 | SEAL-O-RING | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-L | Hyd Accum Brake Reseal LEFT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488035 | FleetCo (WA) LTP | 8345846 | 2 | 6V-9746 | SEAL-O-RING | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-L | Hyd Accum Brake Reseal LEFT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488035 | FleetCo (WA) LTP | 8345846 | 1 | 1J-9671 | SEAL-O-RING | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-R | Hyd Accum Brake Reseal RIGHT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488036 | FleetCo (WA) LTP | 8345847 | 1 | 222-2367 | VALVE-GAS | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-R | Hyd Accum Brake Reseal RIGHT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488036 | FleetCo (WA) LTP | 8345847 | 1 | 3D-2824 | SEAL-O-RING | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-R | Hyd Accum Brake Reseal RIGHT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488036 | FleetCo (WA) LTP | 8345847 | 2 | 6V-9746 | SEAL-O-RING | THIESS MANAGED
WA |  | LO2121 | Cat 992K | N7647-R | Hyd Accum Brake Reseal RIGHT | 2025-09-22 | 12000 | 2025-08-30 | 18565 | 2026-06-13 | 2026-05-18 |  | 8488036 | FleetCo (WA) LTP | 8345847 | 1 | 1J-9671 | SEAL-O-RING | THIESS MANAGED
WA | Sanjiv Ridge | RD6194 | Cat 785D | N1000 | Engine | 2026-05-15 | 20000 | 2024-09-21 | 16713.94 | 2026-06-16 | 2026-05-15 |  | 8379255 |  | 8288035 | 1 | 785D-EN-FUEL-LINE | IK,ENG-FUEL-LINE
WA | Sanjiv Ridge | RD6194 | Cat 785D | N1310 | Radiator | 2026-02-11 | 20000 | 2022-06-01 |  | 2026-06-16 | 2026-05-15 |  | 8379258 |  | 8288037 | 1 | 785D-RADIATOR | IK,RADIATOR
WA | Sanjiv Ridge | RD6194 | Cat 785D | N1000 | Engine | 2026-05-15 | 20000 | 2024-09-21 | 16713.94 | 2026-06-16 | 2026-05-15 |  | 8379255 |  | REQ_9445515 | 1 | CORE CHAGRE | Cap Components - M
WA | Iron Bridge | DZ8029 | Cat D10T2 | N8995 | Operator Seat | 2025-12-26 | 6000 | 2023-12-09 | 23165 | 2026-06-20 | 2026-06-10 | 91 | 8171702 |  | 8357256 | 1 | D10T2-OPERATORSEAT | IK,OPERATOR-SEAT
WA | Iron Bridge | RD4916 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 2026-04-07 | 16000 | 2023-02-20 | 52539 | 2026-06-26 | 2026-06-01 |  | 8441038 |  | 8313127 | 1 | 793F-SLKADJ-BRK-RE | IK,SLKADJ-BRAKE-RE
WA | Iron Bridge | RD4916 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 2025-12-22 | 16000 | 2022-09-29 | 50567 | 2026-06-26 | 2026-06-01 |  | 8441036 |  | 8313129 | 1 | 793F-SLKADJ-BRK-FR | IK,SLKADJ-BRAKE-FR
WA | Iron Bridge | RD4916 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 2026-04-07 | 16000 | 2023-02-20 | 52539 | 2026-06-26 | 2026-06-01 |  | 8441034 |  | 8313132 | 1 | 793F-DSHFT-TCTRANS | IK,DSHFT-TC-TRANS
WA | Iron Bridge | RD4916 | Cat 793F | N7021 | Pump Brake Cooling | 2025-11-20 | 22000 | 2021-05-24 | 43980 | 2026-06-26 | 2026-06-01 |  | 8441039 |  | 8313142 | 1 | 793F-PMP-BRAKE-CLG | IK,PMP-BRAKE-CLG
WA | Iron Bridge | RD4916 | Cat 793F | N9500 | Air Cond'r-Serv | 2026-05-01 | 4000 | 2025-09-21 | 64973 | 2026-06-26 | 2026-06-01 |  | 8441040 |  | 8313144 | 1 | 793F-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | DR2118 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 2026-02-24 | 15000 |  |  | 2026-06-28 | 2026-04-20 | 59 | 8243298 |  | 8332960 | 1 | 555-8816 | CYLINDER GP
WA | Iron Bridge | DR2118 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 2026-06-12 | 7500 | 2025-03-10 | 9022 | 2026-06-29 | 2026-05-18 |  | 8411679 |  | 8293365 | 1 | 6310-MTR-ROT-RIGHT | IK,MTR-ROT-RIGHT
WA | Iron Bridge | RD4911 | Cat 793F | N1000 | Engine | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458740 |  | 8323219 | 1 | 793F-EN-INDUCTION | IK,ENG-INDUCTION
WA | Iron Bridge | RD4911 | Cat 793F | N1000 | Engine | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458740 |  | 8323219 | 1 | 793F-EN-EXHAUST | IK,ENG-EXHAUST
WA | Iron Bridge | RD4911 | Cat 793F | N1000 | Engine | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458740 |  | 8323219 | 1 | 793F-EN-HARNESS-EL | IK,ENG-HARNESS-EL
WA | Iron Bridge | RD4911 | Cat 793F | N1000 | Engine | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458740 |  | 8323219 | 1 | 793F-EN-FUEL-LINE | IK,ENG-FUEL-LINE
WA | Iron Bridge | RD4911 | Cat 793F | N1000 | Engine | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458740 |  | 8323219 | 1 | 793F-ENG-AUX-FITMT | IK,ENG AUXILARY
WA | Iron Bridge | RD4911 | Cat 793F | N1310 | Radiator | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458742 |  | 8323220 | 1 | 2900574FIH | 793F RADIATOR GRP
WA | Iron Bridge | RD4911 | Cat 793F | N1310 | Radiator | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458742 |  | 8323237 | 1 | 793F-RADIATOR | IK,RADIATOR
WA | Iron Bridge | RD4911 | Cat 793F | N2000 | Transmission | 2026-03-26 | 18000 | 2022-07-13 | 50472 | 2026-07-02 | 2026-06-08 |  | 8458743 |  | 8323238 | 1 | 793F-TRANSMISSION | INSKT,793F,TRANSMISSION
WA | Iron Bridge | RD4911 | Cat 793F | N8200-02 | Ride Strut POS 2 | 2025-12-10 | 22000 | 2021-05-03 | 44498 | 2026-07-02 | 2026-06-08 |  | 8458757 |  | 8323249 | 1 | 793F-RIDE-STRUT-P2 | IK,RIDE-STRUT-P2
WA | Iron Bridge | RD4911 | Cat 793F | N8122-02 | Wheel Group POS 2 | 2025-12-10 | 22000 | 2021-05-03 | 44498 | 2026-07-02 | 2026-06-08 |  | 8458756 |  | 8323251 | 1 | 793F-WHEEL-GRP-P2 | IK,WHEEL-GRP-P2
WA | Iron Bridge | RD4911 | Cat 793F | N8122-01 | Wheel Group POS 1 | 2025-12-10 | 22000 | 2021-05-03 | 44498 | 2026-07-02 | 2026-06-08 |  | 8458755 |  | 8323252 | 1 | 793F-WHEEL-GRP-P1 | IK,WHEEL-GRP-P1
WA | Iron Bridge | RD4911 | Cat 793F | N6061 | Oil Cooler Front Brakes | 2026-07-14 | 26000 | 2021-05-03 | 44498 | 2026-07-02 | 2026-06-08 |  | 8458753 |  | 8323253 | 1 | 793F-OILCLR-BRK-FR | IK,OILCLR-BRK-FR
WA | Iron Bridge | RD4911 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 2026-01-31 | 16000 | 2022-09-21 | 51466 | 2026-07-02 | 2026-06-08 |  | 8458752 |  | 8323255 | 1 | 793F-SLKADJ-BRK-RE | IK,SLKADJ-BRAKE-RE
WA | Iron Bridge | RD4911 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 2026-01-31 | 16000 | 2022-09-21 | 51466 | 2026-07-02 | 2026-06-08 |  | 8458751 |  | 8323256 | 1 | 793F-SLKADJ-BRK-FR | IK,SLKADJ-BRAKE-FR
WA | Iron Bridge | RD4911 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 2026-05-21 | 25000 | 2021-05-03 | 44498 | 2026-07-02 | 2026-06-08 |  | 8458750 |  | 8323257 | 1 | 793F-FINAL-DRVELP4 | IK,FINAL-DRVELP4
WA | Iron Bridge | RD4911 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 2026-01-04 | 25000 | 2020-10-22 | 41969 | 2026-07-02 | 2026-06-08 |  | 8458749 |  | 8323259 | 1 | 793F-FINAL-DRVELP3 | IK,FINAL-DRVELP3
WA | Iron Bridge | RD4911 | Cat 793F | N4000 | Bevel Gear | 2026-03-26 | 18000 | 2022-07-13 | 50472 | 2026-07-02 | 2026-06-08 |  | 8458748 |  | 8323260 | 1 | 793F-BEVEL-GEAR | IK,BEVEL-GEAR
WA | Iron Bridge | RD4911 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458747 |  | 8323262 | 1 | 793F-DSHFT-PMP-DRV | IK,DSHFT-PUMP-DRV
WA | Iron Bridge | RD4911 | Cat 793F | N2050 | Torque Convertor | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458746 |  | 8323263 | 1 | 793F-TORQUE-CONV | IK,TORQUE-CONV
WA | Iron Bridge | RD4911 | Cat 793F | N2002 | Oil Cooler - Transmission | 2026-07-12 | 20000 | 2022-07-13 | 50472 | 2026-07-02 | 2026-06-08 |  | 8458744 |  | 8323264 | 1 | 793F-TRANS-OIL-CLR | IK,TRANS-OILCOOL
WA | Iron Bridge | RD4911 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458759 |  | 8324524 | 1 | 793F-AC-SERVICEMA | IK,AC-SERVICEMA
WA | Iron Bridge | RD4911 | Cat 793F | N1000 | Engine | 2026-03-22 | 24000 | 2021-04-18 | 44390 | 2026-07-02 | 2026-06-08 |  | 8458740 |  | 8326342 | 1 | 793F-EN-MOUNTS | IK,ENG-MOUNTS
WA | Iron Bridge | RD4822 | Cat 785C | N9500 | Air Cond'r-Serv | 2026-04-15 | 5000 |  |  | 2026-07-03 | 2026-06-08 |  | 8469375 |  | 8331415 | 1 | 785C-AC-SERVICE-R1 | IK,AC-SERVICE-REV1
WA |  | DZ3431 | Cat D10T | N1100-L | Turbo Primary LEFT | 2026-03-31 | 6000 | 2023-09-29 | 25721 | 2026-07-03 | 2026-06-08 |  | 8491910 | FleetCo (WA) LTP | 8345873 | 1 | D10T-TURBO-LEFT | IK,TURBO-LEFT | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N1100-R | Turbo Primary RIGHT | 2026-03-31 | 6000 | 2023-09-29 | 25721 | 2026-07-03 | 2026-06-08 |  | 8491911 | FleetCo (WA) LTP | 8345875 | 1 | D10T-TURBO-RIGHT | IK,TURBO-RIGHT | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N1202 | Fuel Transfer Pump | 2026-03-31 | 6000 | 2023-09-29 | 25721 | 2026-07-03 | 2026-06-08 |  | 8491912 | FleetCo (WA) LTP | 8345877 | 1 | D10T-PMP-FUEL-XFER | IK,PMP-FUEL-XFER | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N1300 | Cooling Sys Service | 2026-03-31 | 6000 | 2023-09-29 | 25721 | 2026-07-03 | 2026-06-08 |  | 8491913 | FleetCo (WA) LTP | 8345878 | 1 | D10T-CLG-SYSTEMSVC | IK,CLG-SYSTEMSVC | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 1 | 221-1843 | HOSE ASSY | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 1 | 221-1840 | HOSE AS | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 1 | 4J-0520 | SEAL-O-RING | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 1 | 4J-5267 | SEAL-O-RING | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 1 | 3D-2824 | SEAL-O-RING | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 1 | 6V-9746 | SEAL-O-RING | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 6 | 8T-4185 | BOLT | THIESS MANAGED
WA |  | DZ3431 | Cat D10T | N2020 | Powertrain Pump | 2026-07-16 | 12000 | 2022-03-21 | 20897 | 2026-07-03 | 2026-06-08 |  | 8491914 | FleetCo (WA) LTP | 8349854 | 6 | 8T-4182 | BOLT | THIESS MANAGED
WA | Iron Bridge | DZ8083 | Cat D10T2 | N2020 | Powertrain Pump | 2026-05-27 | 7000 | 2024-10-12 | 27664 | 2026-07-04 | 2026-06-08 |  | 8457580 |  | 8323215 | 1 | D10T2-PMP-PWRTRAIN | IK,PUMP-PWRTRAIN
WA | Iron Bridge | RD4913 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 2026-05-09 | 16000 | 2021-09-26 | 42772 | 2026-07-13 | 2026-06-22 |  | 8460340 |  | 8324525 | 1 | 793F-SLKADJ-BRK-FR | IK,SLKADJ-BRAKE-FR
WA | Iron Bridge | RD4913 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 2026-06-25 | 16000 | 2021-11-24 | 43649 | 2026-07-13 | 2026-06-22 |  | 8460341 |  | 8324526 | 1 | 793F-SLKADJ-BRK-RE | IK,SLKADJ-BRAKE-RE
WA | Iron Bridge | RD4913 | Cat 793F | N9500 | Air Cond'r-Serv | 2026-05-04 | 4000 | 2025-10-06 | 54678 | 2026-07-13 | 2026-06-22 |  | 8460342 |  | 8324527 | 1 | 793F-AC-SERVICE | IK,AC-SERVICE
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498046 |  | 8349739 | 1 | 293-1016 | KIT
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498046 |  | 8349739 | 1 | 5T-6065 | SHIM PACK
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498046 |  | 8349739 | 14 | 1D-4585 | BOLT
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498046 |  | 8349739 | 14 | 5P-8247 | WASHER
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498048 |  | 8349740 | 1 | 293-1016 | KIT
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498048 |  | 8349740 | 1 | 5T-6065 | SHIM PACK
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498048 |  | 8349740 | 14 | 1D-4585 | BOLT
WA | Sanjiv Ridge | RD6502 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 2026-05-13 | 15000 | 2021-02-07 | 51920 | 2026-07-15 | 2026-06-22 |  | 8498048 |  | 8349740 | 14 | 5P-8247 | WASHER
WA | Sanjiv Ridge | RD6196 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 2026-05-14 | 10000 | 2023-12-08 | 13656.89 | 2026-07-15 | 2026-06-22 |  | 8498078 |  | 8349743 | 1 | 785D-UNIS-PUMP-DRV | IK,UNIS-ENG-PMPDRV
WA | Sanjiv Ridge | RD6196 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 2026-07-31 | 15000 | 2023-01-30 | 9711.01 | 2026-07-15 | 2026-06-22 |  | 8498080 |  | 8349744 | 1 | 785D-PRESSCONV-LRE | IK,PRESSCONV-LRE
WA | Sanjiv Ridge | RD6196 | Cat 785D | N7605 | Steering Hmu | 2026-06-16 | 12000 | 2023-07-31 | 12105.11 | 2026-07-15 | 2026-06-22 |  | 8498081 |  | 8349745 | 1 | 785D-STGHMU | IK,STGHMU
WA | Iron Bridge | DR2115 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 2026-10-24 | 4000 | 2025-10-02 | 15347 | 2026-07-16 | 2026-06-22 |  | 8451064 |  | 8319790 | 1 | 6310-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | LO1965 | Cat 994H | N7021 | Pump Brake Cooling | 2026-04-30 | 12000 | 2023-07-14 | 21855 | 2026-07-16 | 2026-06-22 |  | 8467581 |  | 8330163 | 1 | 20R-8528 | PUMP GP-Gr A
WA | Iron Bridge | LO1965 | Cat 994H | N7021 | Pump Brake Cooling | 2026-04-30 | 12000 | 2023-07-14 | 21855 | 2026-07-16 | 2026-06-22 |  | 8467581 |  | 8330165 | 1 | 994H-PMP-BRAKE-CLG | IK,PMP-BRAKE-CLG
WA | Iron Bridge | LO1965 | Cat 994H | N7562-R | Hyd Cyl Tilt RIGHT | 2025-10-02 | 12000 | 2022-05-20 | 19340 | 2026-07-16 | 2026-06-22 |  | 8467582 |  | 8330177 | 1 | 994H-CYL-TILT-RH | IK,CYL-TILT-RIGHT
WA | Iron Bridge | LO1965 | Cat 994H | N7600-L | Control Valve LEFT | 2026-04-15 | 24000 |  |  | 2026-07-16 | 2026-06-22 |  | 8468872 |  | 8330188 | 1 | 994H-VALVE-CTRL-LH | IK,VALVE-CTRL-LH
WA | Iron Bridge | LO1965 | Cat 994H | N8995 | Operator Seat | 2026-06-07 | 6000 | 2025-04-02 | 28311 | 2026-07-16 | 2026-06-22 |  | 8467591 |  | 8330190 | 1 | 994H-OPERATOR-SEAT | IK,OPERATOR-SEAT
WA | Iron Bridge | RD4920 | Cat 793F | N9500 | Air Cond'r-Serv | 2026-07-12 | 4000 | 2025-12-08 | 58764 | 2026-07-20 | 2026-06-29 |  | 8460488 |  | 8324528 | 1 | 793F-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | EX2619 | Cat 6060 | N0555-E1 | Cooler Fan Brgs EN1 | 2026-07-08 | 15000 | 2023-11-03 | 9161 | 2026-07-20 | 2026-06-29 |  | 8467121 |  | 8328310 | 1 | 6060-BRGS-ENCOOL-1 | IK,BRGS-ENG-COOL-1
WA | Iron Bridge | EX8388 | Cat 6060 | N7234-FU | Hyd Motor Cooler Fan FRONT UPP | 2026-07-21 | 15000 | 2024-02-11 | 9763 | 2026-07-24 | 2026-06-29 |  | 8467543 |  | 8328324 | 1 | 6060-MTR-CLRFAN-FU | IK,MTR-CLRFAN-FRUP
WA | Iron Bridge | RD4378 | Cat 785C | N0200 | A Frame Bearing | 2025-11-04 | 20000 | 2019-02-02 | 32110 | 2026-08-01 | 2026-07-06 |  | 8501894 |  | 8353952 | 1 | 785C-A-FRAME-BRG | IK,A-FRAME-BEARING
WA | Iron Bridge | RD4378 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 2025-10-07 | 20000 | 2022-12-11 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501908 |  | 8353954 | 1 | 785C-CYL-STEER-LH | IK,CYL-STEERING-LH
WA | Iron Bridge | RD4378 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 2025-10-07 | 20000 | 2022-12-14 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501909 |  | 8353956 | 1 | 785C-CYL-STEER-RH | IK,CYL-STEERING-RH
WA | Iron Bridge | RD4378 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 2026-04-25 | 5000 | 2025-08-24 | 49521 | 2026-08-01 | 2026-07-06 |  | 8501907 |  | 8353959 | 1 | 785C-PMP-HOIST-BRK | IK,PMP-HOIST-BRK
WA | Iron Bridge | RD4378 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 2026-04-25 | 5000 | 2025-08-24 | 49521 | 2026-08-01 | 2026-07-06 |  | 8501907 |  | 8353963 | 1 | 10R-7971 | PUMP GP GEAR
WA | Iron Bridge | RD4378 | Cat 785C | N5000-04 | Final Drive POS 4 | 2026-09-19 | 20000 | 2023-02-26 | 36580 | 2026-08-01 | 2026-07-06 |  | 8501903 |  | 8353966 | 1 | 785C-FINAL-DRV-P4 | IK,FINAL-DRV-P4
WA | Iron Bridge | RD4378 | Cat 785C | N5000-03 | Final Drive POS 3 | 2025-10-07 | 20000 | 2022-11-25 | 31721 | 2026-08-01 | 2026-07-06 |  | 8501902 |  | 8353969 | 1 | 785C-FINAL-DRV-P3 | IK,FINAL-DRV-P3
WA | Iron Bridge | RD4378 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 2026-09-19 | 20000 | 2023-01-17 | 36580 | 2026-08-01 | 2026-07-06 |  | 8501900 |  | 8353971 | 1 | 6G-6408 | SHAFT-AXLE (LH)
WA | Iron Bridge | RD4378 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 2026-09-19 | 20000 | 2023-01-17 | 36580 | 2026-08-01 | 2026-07-06 |  | 8501900 |  | 8353971 | 1 | 6D-1355 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 2026-09-19 | 20000 | 2023-01-17 | 36580 | 2026-08-01 | 2026-07-06 |  | 8501900 |  | 8353971 | 1 | 7D-7705 | RING-RETAINING
WA | Iron Bridge | RD4378 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 2025-10-07 | 20000 | 2022-11-01 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501901 |  | 8353974 | 1 | 6G-6407 | SHAFT-AXLE (RH)
WA | Iron Bridge | RD4378 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 2025-10-07 | 20000 | 2022-11-01 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501901 |  | 8353974 | 1 | 6D-1355 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 2025-10-07 | 20000 | 2022-11-01 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501901 |  | 8353974 | 1 | 7D-7705 | RING-RETAINING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 2G-3005 | HOSE AS
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 5P-4892 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 2 | 5F-3999 | SEAL,O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 2 | 6H-3977 | O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 8T-2885 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 3 | 4J-0527 | O-RING,56.74MM ID,3.53MM THK
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 4 | 6C-3240 | BOLT (5/8-11X1.75-IN)
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 6 | 4J-0524 | O-RING,47.22MM ID,3.53MM THK
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 4J-0522 | O-RING,37.69MM ID,3.53MM THK
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 4 | 4J-0522 | O-RING,37.69MM ID,3.53MM THK
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 3 | 4J-0520 | O-RING,32.92MM ID,3.53MM THK
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 4 | 8T-4122 | WASHER-HARD (17X32X3.5-MM THK)
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 3K-0360 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 3K-0360 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 6V-8398 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 1 | 3J-1907 | SEAL-O-RING
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 8 | 0L-0478 | BOLT (5/8-11X1.75-IN)
WA | Iron Bridge | RD4378 | Cat 785C | N3320 | Pump Drive Box | 2025-10-07 | 20000 | 2022-12-18 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501898 |  | 8353977 | 8 | 3V-2431 | WASHER
WA | Iron Bridge | RD4378 | Cat 785C | N4000 | Bevel Gear | 2026-06-22 | 20000 | 2017-08-01 | 35327 | 2026-08-01 | 2026-07-06 |  | 8501899 |  | 8353979 | 1 | 785C-BEVEL-GEAR | IK,BEVEL-GEAR
WA | Iron Bridge | RD4378 | Cat 785C | N2004 | Transmission Pump | 2026-01-08 | 20000 | 2019-08-29 | 33026 | 2026-08-01 | 2026-07-06 |  | 8501897 |  | 8353982 | 1 | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
WA | Iron Bridge | RD4378 | Cat 785C | N2004 | Transmission Pump | 2026-01-08 | 20000 | 2019-08-29 | 33026 | 2026-08-01 | 2026-07-06 |  | 8501897 |  | 8353984 | 1 | 785C-PMP-TRANSM | IK,PMP-TRANSM
WA | Iron Bridge | RD4378 | Cat 785C | N2004 | Transmission Pump | 2026-01-08 | 20000 | 2019-08-29 | 33026 | 2026-08-01 | 2026-07-06 |  | 8501897 |  | 8353984 | 1 | 321-3778 | HOSE AS
WA | Iron Bridge | RD4378 | Cat 785C | N2002 | Oil Cooler - Transmission | 2025-11-07 | 20000 | 2019-04-04 | 32151 | 2026-08-01 | 2026-07-06 |  | 8501896 |  | 8353986 | 1 | 0R-3344 | CORE GP-O CLR
WA | Iron Bridge | RD4378 | Cat 785C | N2002 | Oil Cooler - Transmission | 2025-11-07 | 20000 | 2019-04-04 | 32151 | 2026-08-01 | 2026-07-06 |  | 8501896 |  | 8353988 | 1 | 785C-TRANS-OIL-CLR | IK,TRANS-OILCOOL
WA | Iron Bridge | RD4378 | Cat 785C | N2002 | Oil Cooler - Transmission | 2025-11-07 | 20000 | 2019-04-04 | 32151 | 2026-08-01 | 2026-07-06 |  | 8501896 |  | 8353988 | 60 | 541-7110 | HOSE
WA | Iron Bridge | RD4378 | Cat 785C | N2000 | Transmission | 2026-01-08 | 20000 | 2019-08-29 | 33026 | 2026-08-01 | 2026-07-06 |  | 8501895 |  | 8353990 | 1 | 785C-TRANSMISSION | IK,TRANSMISSION
WA | Iron Bridge | RD4378 | Cat 785C | N2000 | Transmission | 2026-01-08 | 20000 | 2019-08-29 | 33026 | 2026-08-01 | 2026-07-22 |  | 8501895 |  | 8353990 | 1 | 2N-2486 | BOLT
WA | Iron Bridge | RD4378 | Cat 785C | N9500 | Air Cond'r-Serv | 2026-07-30 | 5000 | 2025-10-26 | 50856 | 2026-08-01 | 2026-07-06 |  | 8501914 |  | 8357244 | 1 | 785C-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | RD4378 | Cat 785C | N8200-02 | Ride Strut POS 2 | 2025-10-07 | 20000 | 2022-11-24 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501913 |  | 8357245 | 1 | 785C-RIDE-STRUT-P2 | IK,RIDE-STRUT-P2
WA | Iron Bridge | RD4378 | Cat 785C | N8122-02 | Wheel Group POS 2 | 2025-10-07 | 20000 | 2022-11-08 | 31720 | 2026-08-01 | 2026-07-06 |  | 8501915 |  | 8357246 | 1 | 785C-WHEEL-GRP-P2 | IK,WHEEL-GRP-P2
WA | Iron Bridge | RD4378 | Cat 785C | N7605 | Steering Hmu | 2026-05-17 | 20000 | 2020-09-15 | 34829 | 2026-08-01 | 2026-07-06 |  | 8501911 |  | 8357248 | 1 | 785C-STGHMU | IK,STGHMU
WA | Iron Bridge | RD4378 | Cat 785C | N7605 | Steering Hmu | 2026-05-17 | 20000 | 2020-09-15 | 34829 | 2026-08-01 | 2026-07-06 |  | 8501911 |  | 8357248 | 4 | 9D-7924 | ASSEMBLY; MOUNT
WA | Iron Bridge | GR1271 | Cat 16M | N9500 | Air Cond'r-Serv | 2026-07-12 | 4000 | 2025-10-23 | 23100 | 2026-08-05 | 2026-07-13 |  | 8507364 |  | 8357239 | 1 | 16M-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N1000 | Engine | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495402 |  | 8347925 | 1 | 6310-ENGINE | IK,ENGINE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N1000 | Engine | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495402 |  | 8347926 | 1 | 5875935X | EXCHANGE ENGINE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495403 |  | 8347929 | 1 | 6310-AFTRCLRCORE-L | IK,AFTERCLRCORE-LH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495404 |  | 8347930 | 1 | 6310-AFTRCLRCORE-R | IK,AFTERCLRCORE-RH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495405 |  | 8347932 | 1 | 6310-COOLER-FAN-EN | IK,COOLER-FAN-ENG
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347934 | 1 | 6310-PUMPDRIVE-BOX | IK,PUMPDRIVE-BOX
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3340 | Rotary Head | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495407 |  | 8347937 | 1 | 6310-ROTARY-HEAD | IK,ROTARY-HEAD
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495408 |  | 8347940 | 1 | 6310-FINAL-DRV-LH | IK,FINAL-DRV-LH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495409 |  | 8347942 | 1 | 6310-FINAL-DRV-RH | IK,FINAL-DRV-RH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495411 |  | 8347944 | 1 | 20R-9460 | PUMP GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 031-4392 | SEAL-O-RING
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 3 | 6J-2680 | SEAL-O-RING
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 2 | 1P-3704 | SEAL-RECTANGULAR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 3D-2824 | SEAL-O-RING-STOR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 6V-9746 | SEAL-O-RING-ORFS
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 6V-8397 | SEAL-O-RING-ORFS
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 3J-1907 | SEAL-O-RING-STOR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 4J-5477 | SEAL-O-RING-ORFS
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495406 |  | 8347946 | 1 | 3J-7354 | SEAL-O-RING-STOR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495411 |  | 8347948 | 1 | 6310-PMP-HYD-POS2 | IK,PMP-HYD-POS2
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495410 |  | 8347950 | 1 | 6310-PMP-HYD-POS1 | IK,PMP-HYD-POS1
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495410 |  | 8347954 | 1 | 20R-9460 | PUMP GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495413 |  | 8347955 | 1 | 6310-PMP-CLGFANENG | IK,PMP-CLGFANENG
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495413 |  | 8347957 | 1 | 11R-1030 | PUMP GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495412 |  | 8347958 | 1 | 6310-PMP-CLGFANHYD | IK,PMP-CLG-FAN-HYD
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495412 |  | 8347960 | 1 | 11R-1030 | PUMP GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495415 |  | 8347964 | 1 | 6310-PUMP-AUXILARY | IK,PUMP-AUXILIARY
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495415 |  | 8347965 | 1 | 20R-9457 | PUMP GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495414 |  | 8347967 | 1 | 392-4160 | SPIDER-AS-FAN
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495414 |  | 8347967 | 6 | 198-4777 | WASHER
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495414 |  | 8347967 | 6 | 8T-4195 | BOLT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495417 |  | 8347969 | 1 | 6310-HYD-MOTOR-A/C | IK,HYDR-MOTOR-A/C
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495419 |  | 8347971 | 1 | 6310-COOLFANMTR-RH | IK,COLR-FAN-MTR-RH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495418 |  | 8347975 | 1 | 6310-COOLFANMTR-LH | IK,COLR-FAN-MTR-LH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 2026-05-26 | 7500 | 2025-03-03 | 6904 | 2026-08-06 | 2026-07-13 |  | 8495420 |  | 8347978 | 1 | 11R-0141 | MOTOR GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 2026-05-26 | 7500 | 2025-03-03 | 6904 | 2026-08-06 | 2026-07-13 |  | 8495420 |  | 8347980 | 1 | 6310-MTR-ROT-LEFT | IK,MTR-ROT-LEFT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495423 |  | 8347983 | 1 | 6310-TRVL-MOTOR-RH | IK,TRAVEL-MOTOR-RH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495423 |  | 8347985 | 1 | 20R-9462 | MOTOR GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495422 |  | 8347987 | 1 | 6310-TRVL-MOTOR-LH | IK,TRAVEL-MOTOR-LH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495422 |  | 8347990 | 1 | 20R-9462 | MOTOR GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 2026-05-18 | 7500 | 2025-01-23 | 6785 | 2026-08-06 | 2026-07-13 |  | 8495421 |  | 8347992 | 1 | 6310-MTR-ROT-RIGHT | IK,MTR-ROT-RIGHT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 2026-05-18 | 7500 | 2025-01-23 | 6785 | 2026-08-06 | 2026-07-13 |  | 8495421 |  | 8347994 | 1 | 11R-0142 | MOTOR GP-PISTON
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N0550 | Air End | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495400 |  | 8348878 | 1 | 5418635X | COMPRESSOR 1500CFM 500PSI
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496241 |  | 8349267 | 1 | 515-6798 | CYLINDER GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496241 |  | 8349267 | 1 | 6310-CYL-POS-SWING | IK,CYL-POS-SWING
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496242 |  | 8349270 | 1 | 524-8999 | CYLINDER GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496242 |  | 8349270 | 1 | 6310-CYL-POS-CLAMP | IK,CYL-POS-CLAMP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496243 |  | 8349271 | 1 | 555-8816 | CYLINDER GP CAROUSEL INDEX
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496243 |  | 8349271 | 1 | 6310-CYL-LOCK-CAR | IK,CYL-LOCK-CAR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496244 |  | 8349272 | 1 | 581-1110 | CYLINDER GP CAROUSEL LOCK
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496244 |  | 8349272 | 1 | 6310-CYL-LCKCAR-FR | IK,CYL-LOCK-CAR-FR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496245 |  | 8349274 | 1 | 6310-CYL-LCKCAR-RE | IK,CYL-LOCK-CAR-RE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496246 |  | 8349276 | 1 | 6310-CYL-DUSTCRTFR | IK,CYL-DUSTCURT-FR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496247 |  | 8349277 | 1 | 6310-CYL-DUSTCRTRE | IK,CYL-DUSTCURT-RE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496248 |  | 8349278 | 1 | 515-6805 | CYL GP-127 1
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496248 |  | 8349278 | 1 | 6310-CYL-BITBASKLH | IK,CYL-BITBASKT-LH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496249 |  | 8349279 | 1 | 515-6805 | CYL GP-127 1
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496249 |  | 8349279 | 1 | 6310-CYL-BITBASKRE | IK,CYL-BITBASKT-RH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496250 |  | 8349280 | 1 | 515-6798 | CYL GP-076 3
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496250 |  | 8349280 | 1 | 6310-CYL-ACCESSLAD | IK,CYL-ACCESS-LADR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496267 |  | 8349281 | 1 | 6310-CYL-JACK-LHRE | IK,CYL-JACK-LH-RE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496268 |  | 8349282 | 1 | 6310-CYL-JACK-RHRE | IK,CYL-JACK-RH-RE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496269 |  | 8349283 | 1 | 524-0147 | CYLINDER GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496269 |  | 8349283 | 1 | 6310-CYL-BRKOUTROT | IK,CYL-BRKOUT-ROT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N0550 | Air End | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495400 |  | 8349285 | 1 | 6310-AIR-END-HP | IK,AIR-END,HP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495401 |  | 8349286 | 1 | 6310-AIR-COOLER | IK,COMP-AIR-COOLER
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496270 |  | 8349287 | 1 | 524-0146 | CYLINDER GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496270 |  | 8349287 | 1 | 6310-CYL-BRKOUTSWG | IK,CYL-BRKOUT-SWG
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496271 |  | 8349290 | 1 | 524-0148 | CYLINDER GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496271 |  | 8349290 | 1 | 6310-CYL-BRKOUTCLA | IK,CYL-BRKOUTCLAMP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496273 |  | 8349291 | 1 | 6310-CYL-DECKHATCH | IK,CYL-DECK-HATCH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496274 |  | 8349293 | 2 | 296-1374 | PIN AS
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496274 |  | 8349293 | 1 | 6310-CYL-MSTRAI-LH | IK,CYL-MASTRAISELH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496274 |  | 8349293 | 2 | 565-6936 | SPACER (76.2X88.9X9-MM THK)
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496275 |  | 8349294 | 1 | 6310-CYL-MSTLOCKLH | IK,CYL-MSTLOCK-LFT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496276 |  | 8349295 | 1 | 6310-CYL-MSTLOCKRH | IK,CYL-MSTLOCK-RHT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496277 |  | 8349296 | 1 | 539-1901 | CYL GP-127 1
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496277 |  | 8349296 | 1 | 6310-CYL-CRSWG-LWR | IK,CYL-CAR-SWG-LWR
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496278 |  | 8349297 | 1 | 539-1901 | CYL GP-127 1
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496278 |  | 8349297 | 1 | 6310-CYL-CRSWG-UPP | IK,CYL-CAR-SWG-UPP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496240 |  | 8351570 | 1 | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496240 |  | 8351570 | 1 | 6310-CYL-FEEDTENRU | IK,CYL-FEED-TEN-RU
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496239 |  | 8351572 | 1 | 6310-CYL-FEEDTENRL | IK,CYL-FEED-TEN-RL
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496238 |  | 8351573 | 1 | 6310-CYL-FEEDTENLU | IK,CYL-FEED-TEN-LU
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496237 |  | 8351575 | 1 | 6310-CYL-FEEDTENLL | IK,CYL-FEED-TEN-LL
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495424 |  | 8351578 | 1 | 6310-CYL-FEED | IK,CYL-FEED
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 2026-08-03 | 4000 | 2025-11-09 | 11360 | 2026-08-06 | 2026-07-13 |  | 8499739 |  | 8351580 | 1 | 6310-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N9501 | A/C Compressor | 2026-05-26 | 7500 | 2025-03-03 | 6904 | 2026-08-06 | 2026-07-13 |  | 8496400 |  | 8351583 | 1 | 6310-AC-COMPRESS | IK,AC-COMPRESS
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 1 | 489-6525 | SEAT GP
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 1 | 436-8490 | SUSPENSION ASSEMBLY-SEAT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 1 | 595-6766 | HARNESS AS
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 1 | 528-7198 | HIGH VISIBILITY ORANGE RETRACT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 1 | 173-7035 | BLOCK KIT-SLIDER
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 4 | 8T-4182 | BOLT
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496285 |  | 8351587 | 4 | 8T-4121 | FLAT WASHER
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496284 |  | 8351589 | 1 | 515-6798 | CYLINDER GP HYD
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8496284 |  | 8351589 | 1 | 6310-CYL-ROD-CATCH | IK,CYL-ROD-CATCH
WA | Iron Bridge | DR2117 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 2026-07-08 | 15000 |  |  | 2026-08-06 | 2026-07-13 |  | 8495401 |  | 8351593 | 2000 | 308-9131 | RUBBER BULK SEAL
WA | Iron Bridge | RD2030 | Cat 793D | N6200-03 | Press Convertor POS 3 | 2026-07-01 | 10000 | 2024-10-30 | 73121 | 2026-08-06 | 2026-08-06 |  | 8507392 |  | 8356606 | 1 | 793D-PRESSCONV-P3 | INSKT,793D,PRESS-CONV-POS-3
WA | Iron Bridge | RD2030 | Cat 793D | N6200-03 | Press Convertor POS 3 | 2026-07-01 | 10000 | 2024-10-30 | 73121 | 2026-08-06 | 2026-08-06 |  | 8507392 |  | 8356606 | 1 | 8W-3405 | CHAMBER, BRAKE
WA | Iron Bridge | RD2030 | Cat 793D | N6200-03 | Press Convertor POS 3 | 2026-07-01 | 10000 | 2024-10-30 | 73121 | 2026-08-06 | 2026-08-06 |  | 8507392 |  | 8356606 | 1 | 8J-6173 | VALVE
WA | Iron Bridge | RD2030 | Cat 793D | N6200-03 | Press Convertor POS 3 | 2026-07-01 | 10000 | 2024-10-30 | 73121 | 2026-08-06 | 2026-08-06 |  | 8507392 |  | 8356606 | 1 | 8X-6262 | HOSE A
WA | Iron Bridge | RD2030 | Cat 793D | N6200-04 | Press Convertor POS 4 | 2026-07-01 | 10000 | 2024-10-30 | 73121 | 2026-08-06 | 2026-08-06 |  | 8507393 |  | 8357238 | 1 | 793D-PRESSCONV-P4 | INSKT,793D,PRESS-CONV-POS-4
WA | Iron Bridge | EX2619 | Cat 6060 | N9500-R | Air Cond'r-Serv RIGHT | 2026-08-07 | 4500 | 2025-10-09 | 20210 | 2026-08-10 | 2026-07-20 |  | 8507242 |  | 8357240 | 1 | 6060-AC-SERVICE-RH | IK,AC-SERVIC-RIGHT
WA | Iron Bridge | EX2619 | Cat 6060 | N9500-L | Air Cond'r-Serv LEFT | 2026-08-07 | 4500 | 2025-10-09 | 20210 | 2026-08-10 | 2026-07-20 |  | 8507241 |  | 8357241 | 1 | 6060-AC-SERVICE-LH | IK,AC-SERVICE-LEFT
WA | Iron Bridge | EX2619 | Cat 6060 | N7232-E1 | Hyd Motor Engine Fan EN1 | 2026-07-08 | 15000 | 2023-11-03 | 9161 | 2026-08-10 | 2026-07-20 |  | 8507238 |  | 8357242 | 1 | 6060-MTR-ENGFAN-E1 | IK,MTR-ENGFAN-E1
WA | Iron Bridge | EX2619 | Cat 6060 | N7232-E1 | Hyd Motor Engine Fan EN1 | 2026-07-08 | 15000 | 2023-11-03 | 9161 | 2026-08-10 | 2026-07-20 |  | 8507238 |  | 8357243 | 1 | 20R-2014 | MOTOR GROUP-PISTON
WA | Iron Bridge | RD4915 | Cat 793F | N9500 | Air Cond'r-Serv | 2026-06-11 | 4000 | 2025-10-07 | 61567 | 2026-08-12 | 2026-07-20 |  | 8509170 |  | 8357740 | 1 | 793F-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | RD4915 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 2026-07-23 | 16000 | 2022-01-23 | 50338 | 2026-08-12 | 2026-07-20 |  | 8509169 |  | 8357742 | 1 | 793F-SLKADJ-BRK-FR | IK,SLKADJ-BRAKE-FR
WA | Iron Bridge | RD4910 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 2026-06-08 | 24000 | 2020-10-26 | 38283 | 2026-08-13 | 2026-07-20 |  | 8508613 |  | 8357226 | 1 | 793F-PMP-AXLE-LUBE | IK,PMP-AXLE-LUBE
WA | Iron Bridge | RD4910 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 2026-06-08 | 24000 | 2020-10-26 | 38283 | 2026-08-13 | 2026-07-20 |  | 8508613 |  | 8357228 | 1 | 20R-8004 | PUMP GP-GR A
WA | Iron Bridge | RD4910 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 2026-01-29 | 16000 | 2021-11-14 | 43882 | 2026-08-13 | 2026-07-20 |  | 8508612 |  | 8357229 | 1 | 793F-SLKADJ-BRK-RE | IK,SLKADJ-BRAKE-RE
WA | Iron Bridge | RD4910 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 2026-01-29 | 16000 | 2021-11-14 | 43882 | 2026-08-13 | 2026-07-20 |  | 8508611 |  | 8357231 | 1 | 793F-SLKADJ-BRK-FR | IK,SLKADJ-BRAKE-FR
WA | Iron Bridge | RD4910 | Cat 793F | N8200-04 | Ride Strut POS 4 | 2025-06-01 | 25000 | 2019-03-03 | 30403 | 2026-08-13 | 2026-07-20 |  | 8508617 |  | 8357747 | 1 | 793F-RIDE-STRUT-P4 | IK,RIDE-STRUT-P4
WA | Iron Bridge | RD4910 | Cat 793F | N8200-03 | Ride Strut POS 3 | 2025-06-01 | 25000 | 2019-03-03 | 30403 | 2026-08-13 | 2026-07-20 |  | 8508616 |  | 8357748 | 1 | 793F-RIDE-STRUT-P3 | IK,RIDE-STRUT-P3
WA | Iron Bridge | RD4910 | Cat 793F | N7605 | Steering Hmu | 2026-06-08 | 24000 | 2020-10-26 | 38283 | 2026-08-13 | 2026-07-20 |  | 8508615 |  | 8357749 | 1 | 793F-STGHMU | IK,STGHMU
WA | Iron Bridge | RD4910 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 2026-06-08 | 24000 | 2020-10-26 | 38283 | 2026-08-13 | 2026-07-20 |  | 8508614 |  | 8357750 | 1 | 793F-MTR-AXLE-LUBE | IK,MTR-AXLE-LUBE
WA | Iron Bridge | RD4910 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 2026-06-08 | 24000 | 2020-10-26 | 38283 | 2026-08-13 | 2026-07-20 |  | 8508614 |  | 8357751 | 1 | 10R-5465 | MOTOR
WA | Iron Bridge | RD4910 | Cat 793F | N9500 | Air Cond'r-Serv | 2026-04-05 | 4000 | 2025-09-14 | 57104 | 2026-08-13 | 2026-07-20 |  | 8508618 |  | REQ_9442766 | 1 | 793F-AC-SERVICE | IK,AC-SERVICE
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 1 | 6310-DRV-COUPLING | IK,DRV-COUPLING
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 1 | 102-3819 | ELBOW
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 2 | 274-1707 | HOSE
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 4 | 217-7088 | HOSE
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 1 | 2W-9646 | ELBOW
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 1 | 9X-7287 | SEAL-O-RING
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 4 | 447-7206 | SEAL-O-RING
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 4 | 6V-4590 | SEAL-O-RING
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 2 | 233-8484 | CLAMP
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 2 | 254-0816 | CLAMP
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 12 | 208-7448 | CLAMP
WA | Iron Bridge | DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 2026-07-04 | 5000 | 2025-06-22 | 8474 | 2026-08-15 | 2026-07-20 |  | 8500367 |  | 8351567 | 4 | 4J-5477 | SEAL-O-RING
WA | Sanjiv Ridge | RD6314 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 2025-05-30 | 10000 | 2019-09-01 | 40293 | 2026-08-17 | 2026-07-17 |  | 8498649 |  | 8350699 | 1 | 785C-UNIS-PUMP-DRV | IK,UNIS-ENG-PMPDRV
WA | Iron Bridge | RD4912 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 2026-06-29 | 16000 | 2021-11-28 | 44102 | 2026-08-18 | 2026-07-27 |  | 8509098 |  | 8357744 | 1 | 793F-SLKADJ-BRK-RE | IK,SLKADJ-BRAKE-RE
WA | Iron Bridge | RD4912 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 2026-07-27 | 16000 | 2021-12-29 | 44625 | 2026-08-18 | 2026-07-27 |  | 8509097 |  | 8357746 | 1 | 793F-SLKADJ-BRK-FR | IK,SLKADJ-BRAKE-FR
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2450 | Drv Cpling Fan Pump-Trans Pump | 2026-04-10 | 7000 | 2023-12-14 | 23635 | 2026-08-27 | 2026-08-03 |  | 8500425 |  | 8357233 | 1 | D10T2-DCPLG-FANPMP | IK,DRV-CPLGFANTRAN
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | D10T2-PMP-PWRTRAIN | IK,PUMP-PWRTRAIN
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 374-9977 | HOSE AS.
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 374-9976 | HOSE AS.
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 374-9983 | HOSE ASSEMBLY
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 2 | 061-9455 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 061-7540 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 1P-3706 | RECTANGULAR SEAL
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 4J-0522 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 7M-8485 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 3D-2824 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 6V-8400 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 3K-0360 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 2 | 6V-8398 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 6V-8397 | SEAL-O-RING
WA | Iron Bridge | DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 2026-07-02 | 7000 | 2025-02-11 | 24807 | 2026-08-27 | 2026-08-03 |  | 8500423 |  | 8357235 | 1 | 3J-1907 | SEAL-O-RING

## JDE 12M Forecast
Westrac West - May 2026 Thiess Month Forecast
Westrac West - May 2026 Thiess Month Forecast
ServiceType | State | OEM | Ownership | Location | Unit Number | Unit Description | Component Description | Interal Supply | Engine Hours | Frequency | Forecasted Start Date | Daily Hour Estimate | Approved Start Date | Last Changed Hours | Last Changed Date | LTP - Comments | Forecasted Part Number | Part Number Description
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Uni's T/C - Trans |  | 32588.7 | 9000 | 1986-04-17 | 1.61 |  | 0 | 2022-06-01
N1301 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Water Pump |  | 32588.7 | 9000 | 1986-04-17 | 1.61 |  | 0 | 2022-06-01
N0180 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Deck Plates |  | 47029 | 6000 | 1999-02-21 | 4.12 |  | 0 | 1999-09-01
N8152 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Kingpin |  | 47029 | 6000 | 1999-02-21 | 4.12 |  | 0 | 1999-09-01
N7490-L | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Hyd Cyl Lift LEFT |  | 47029 | 6000 | 1999-02-21 | 4.12 |  | 0 | 1999-09-01
N7490-R | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Hyd Cyl Lift RIGHT |  | 47029 | 6000 | 1999-02-21 | 4.12 |  | 0 | 1999-09-01
N7120 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Pump Steering |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2013-05-19
N2002 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Oil Cooler - Transmission |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2013-05-19
N7064 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Pump Hoist |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N6060-RE | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Oil Cooler - Brakes REAR |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N6030-RR | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Brake Slack Adj RHT REAR |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N6060-F | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Oil Cooler - Brakes FRONT |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N6030-RF | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Brake Slack Adj RHT FRONT |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N2025 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Pump Trans / T/C / Brk Cooling |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N1100-R | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Turbo Primary RIGHT |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2019-12-17
N7122 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Pump Emerg/Sup Steering |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Drive Shaft T/C - Trans |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N1100-L | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Turbo Primary LEFT |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2019-06-22
N6030-LR | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Brake Slack Adj LFT REAR |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N5000-03 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Final Drive POS 3 |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N5000-04 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Final Drive POS 4 |  | 32588.7 | 18000 | 2001-08-06 | 1.61 |  | 0 | 2022-06-01
N9050 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Starter Motor |  | 41729 | 10000 | 2003-01-06 | 1.2 |  | 21477 | 2015-03-20
N9500-MA | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Air Cond'r-Serv - MAJOR |  | 41729 | 20000 | 2004-02-13 | 1.2 |  | 11961 | 2013-08-30
N9020 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Alternator |  | 41729 | 20000 | 2004-02-13 | 1.2 |  | 11961 | 2013-08-30
N1002 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Engine Valve Adj |  | 65021 | 4000 | 2006-10-02 | 8.5 |  | 12 | 2025-10-03
N2002 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Oil Cooler - Transmission |  | 47029 | 18000 | 2007-02-11 | 4.12 |  | 0 | 1999-09-01
N1301 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Water Pump |  | 47332.5 | 9000 | 2011-09-08 | 7.13 |  | 0 | 2022-06-01
N3029 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Uni's T/C - Trans |  | 43005.2 | 16000 | 2014-10-05 | 6.35 |  | 0 | 2022-06-01
N1312-L | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Aftercooler Core - LEFT |  | 43005.2 | 16000 | 2014-10-05 | 6.35 |  | 0 | 2022-06-01
N7610 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Hyd Cooler Core |  | 43005.2 | 16000 | 2014-10-05 | 6.35 |  | 0 | 2022-06-01
N7541 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Hyd Cyl Access Ladder |  | 79490 | 20000 | 2014-10-09 | 14 |  | 0 | 2011-09-03 |  | 339-3275 | CYLINDER GP
N7541 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Hyd Cyl Access Ladder |  | 79044 | 20000 | 2014-11-10 | 14 |  | 0 | 2011-09-05 |  | 339-3275 | CYLINDER GP
N7541 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Cyl Access Ladder |  | 73929 | 20000 | 2014-12-14 | 14 |  | 0 | 2011-09-23 |  | 339-3275 | CYLINDER GP
N8130-L | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Steering Tie Rods LEFT |  | 47029 | 30000 | 2015-02-02 | 4.12 |  | 0 | 1999-09-01
N8130-R | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Steering Tie Rods RIGHT |  | 47029 | 30000 | 2015-02-02 | 4.12 |  | 0 | 1999-09-01
N6030-RR | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Brake Slack Adj RHT REAR |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N6060-RE | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Oil Cooler - Brakes REAR |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N6060-F | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Oil Cooler - Brakes FRONT |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N2002 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Oil Cooler - Transmission |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N3028 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Drive Shaft T/C - Trans |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N6030-LR | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Brake Slack Adj LFT REAR |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N6030-RF | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Brake Slack Adj RHT FRONT |  | 47332.5 | 18000 | 2015-02-21 | 7.13 |  | 0 | 2022-06-01
N6200-LR | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Press Converter LEFT REAR |  | 71548 | 10000 | 2015-03-04 | 15 |  | 2 | 2023-07-27 |  | 8W-3405 | CHAMBER, BRAKE
N7541 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Hyd Cyl Access Ladder |  | 77195 | 20000 | 2015-03-22 | 14 |  | 0 | 2011-10-11 |  | 339-3275 | CYLINDER GP
N0030 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Truck Body |  | 47332.5 | 20000 | 2015-11-29 | 7.13 |  | 0 | 2022-06-01
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Oil Cooler - Brakes |  | 67683.26 | 20000 | 2015-12-17 | 12.5 |  | 0 | 2022-06-01
N0550 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Air End |  | 67683.26 | 20000 | 2015-12-17 | 12.5 |  | 0 | 2022-06-01
N4100-R | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Rear Axle RIGHT |  | 67683.26 | 20000 | 2015-12-17 | 12.5 | 18/09/2026 | 0 | 2022-06-01
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Drive Shaft T/C - Trans |  | 67683.26 | 20000 | 2015-12-17 | 12.5 |  | 0 | 2022-06-01
N0030 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Truck Body |  | 67683.26 | 20000 | 2015-12-17 | 12.5 |  | 0
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 67683.26 | 20000 | 2015-12-17 | 12.5 |  | 0
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Rear Axle LEFT |  | 67683.26 | 20000 | 2015-12-17 | 12.5 | 18/09/2026 | 0 | 2022-06-01
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Hyd Cooler Core |  | 67106.81 | 20000 | 2016-02-01 | 12.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 67106.81 | 20000 | 2016-02-01 | 12.5 |  | 0
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Drive Shaft T/C - Trans |  | 67106.81 | 20000 | 2016-02-01 | 12.5 |  | 0 | 2022-06-01
N6030-RE | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Brake Slack Adj REAR |  | 67106.81 | 20000 | 2016-02-01 | 12.5 |  | 0 | 2022-06-01
N0550 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Air End |  | 67106.81 | 20000 | 2016-02-01 | 12.5 |  | 0 | 2022-06-01
N0030 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Truck Body |  | 67106.81 | 20000 | 2016-02-01 | 12.5 |  | 0 | 2022-06-01
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Hyd Cooler Core |  | 66446.13 | 20000 | 2016-03-25 | 12.5 |  | 0 | 2021-02-01
N0550 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Air End |  | 66446.13 | 20000 | 2016-03-25 | 12.5 |  | 0 | 2021-02-01
N4100-R | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Rear Axle RIGHT |  | 66446.13 | 20000 | 2016-03-25 | 12.5 |  | 0 | 2021-02-01
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Rear Axle LEFT |  | 66446.13 | 20000 | 2016-03-25 | 12.5 |  | 0 | 2021-02-01
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Oil Cooler AXLE |  | 66446.13 | 20000 | 2016-03-25 | 12.5 |  | 0 | 2021-02-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 66446.13 | 20000 | 2016-03-25 | 12.5 |  | 0
N0030 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Truck Body |  | 66379.67 | 20000 | 2016-03-31 | 12.5 |  | 0
N0550 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Air End |  | 66379.67 | 20000 | 2016-03-31 | 12.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 66379.67 | 20000 | 2016-03-31 | 12.5 |  | 0
N6030-RE | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Brake Slack Adj REAR |  | 66379.67 | 20000 | 2016-03-31 | 12.5 |  | 0 | 2022-06-01
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Rear Axle LEFT |  | 66379.67 | 20000 | 2016-03-31 | 12.5 |  | 0 | 2022-06-01
N4100-R | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Rear Axle RIGHT |  | 66379.67 | 20000 | 2016-03-31 | 12.5 |  | 0 | 2022-06-01
N8301 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Artic Hitch Inspect/Adjust |  | 41729 | 10000 | 2016-04-07 | 1.2 |  | 27285 | 2016-02-24
N6360 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Brake Control Valve |  | 49963 | 30000 | 2016-06-19 | 5.5 |  | 0
N0050 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Blade Assembly |  | 43005.2 | 20000 | 2016-06-26 | 6.35 |  | 0 | 2022-06-01
N0201-01 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | A Frame Bearing Reshim Initial |  | 79025 | 2000 | 2016-07-09 | 14 |  | 26484.1 | 2015-11-06 |  | 8X-2934 | SHIM PACK
N7654 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Hyd Accum Service Brake |  | 63459.48 | 15000 | 2016-07-29 | 13.5 |  | 0 | 2022-06-01
N3210-R | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Tandem Drive Chain RIGHT |  | 33341.1 | 12000 | 2016-08-01 | 5.95 | 15/07/2026 | 0 | 2016-02-08 | Danny M to Investigate possible replacement already
N3210-L | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Tandem Drive Chain LEFT |  | 33341.1 | 12000 | 2016-08-01 | 5.95 | 15/07/2026 | 0 | 2016-02-08 | Danny M to Investigate possible replacement already
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 64732.59 | 20000 | 2016-08-09 | 12.5 |  | 0
N6030-RE | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Brake Slack Adj REAR |  | 64732.59 | 20000 | 2016-08-09 | 12.5 |  | 0 | 2022-06-01
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Rear Axle LEFT |  | 64732.59 | 20000 | 2016-08-09 | 12.5 |  | 0 | 2022-06-01
N0030 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Truck Body |  | 64732.59 | 20000 | 2016-08-09 | 12.5 |  | 0
N4100-R | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Rear Axle RIGHT |  | 64732.59 | 20000 | 2016-08-09 | 12.5 |  | 0 | 2022-06-01
N7541 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cyl Access Ladder |  | 82501 | 20000 | 2017-02-26 | 18.5 |  | 0 | 2013-12-17 |  | 339-3275 | CYLINDER GP
N7541 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cyl Access Ladder |  | 82501 | 20000 | 2017-02-26 | 18.5 |  | 0 | 2013-12-17 |  | 339-3275 | CYLINDER GP
N9500 | WA | CAT | 19 | Iron Bridge | RD6260 | Cat 785C | Air Cond'r-Serv |  | 57924 | 5000 | 2017-05-07 | 16 |  | 0
N8995 | WA | CAT | 19 | Iron Bridge | RD6260 | Cat 785C | Operator Seat |  | 57924 | 6000 | 2017-07-09 | 16 |  | 0 |  |  | 384-6168 | OPERATOR SEAT_CAT 785C
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Rear Axle LEFT |  | 60509.94 | 20000 | 2017-07-13 | 12.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 60509.94 | 20000 | 2017-07-13 | 12.5 |  | 0
N4100-R | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Rear Axle RIGHT |  | 60509.94 | 20000 | 2017-07-13 | 12.5 |  | 0 | 2022-06-01
N6030-RE | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Brake Slack Adj REAR |  | 60509.94 | 20000 | 2017-07-13 | 12.5 |  | 0 | 2022-06-01
N1310 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Radiator |  | 75270 | 25000 | 2017-07-30 | 6.5 |  | 69709 | 2024-01-15
N6030-RE | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Brake Slack Adj REAR |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0
N0550 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Air End |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2022-06-01
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Oil Cooler - Brakes |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2011-09-17
N6063 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Oil Cooler - Steering |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2011-09-17
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Hyd Cooler Core |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2011-09-17
N0030 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Truck Body |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2022-06-01
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Oil Cooler AXLE |  | 63459.48 | 20000 | 2017-08-04 | 13.5 |  | 0 | 2011-09-17
N7514-R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Hyd Cyl Ripper Pitch RIGHT |  | 34410.8 | 14000 | 2017-08-09 | 6.35 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 62901.67 | 20000 | 2017-09-14 | 13.5 |  | 0
N3020 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 58227.56 | 20000 | 2018-01-12 | 12.5 |  | 0
N6030-RE | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Brake Slack Adj REAR |  | 58227.56 | 20000 | 2018-01-12 | 12.5 |  | 0 | 2022-06-01
N4100-R | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Rear Axle RIGHT |  | 58227.56 | 20000 | 2018-01-12 | 12.5 |  | 0 | 2022-06-01
N0030 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Truck Body |  | 58227.56 | 20000 | 2018-01-12 | 12.5 |  | 0
N4100-L | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Rear Axle LEFT |  | 58227.56 | 20000 | 2018-01-12 | 12.5 |  | 0 | 2022-06-01
N6030-RE | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Brake Slack Adj REAR |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Hyd Cooler Core |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0 | 2011-09-17
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Oil Cooler - Brakes |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0 | 2011-09-17
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Oil Cooler AXLE |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0 | 2011-09-17
N6063 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Oil Cooler - Steering |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0 | 2011-09-17
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Drive Shaft T/C - Trans |  | 60870.4 | 20000 | 2018-02-12 | 13.5 |  | 0 | 2022-06-01
N7474-L | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Hyd Cyl Hoist LEFT |  | 67683.26 | 30000 | 2018-02-24 | 12.5 |  | 0
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Brake Slack Adj FRONT |  | 67106.81 | 30000 | 2018-04-11 | 12.5 |  | 0 | 2022-06-01
N8061-01 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Slew Ring Bolts Check -Initial |  | 55435 | 1000 | 2018-05-08 | 18.5 |  | 0 | 2024-04-05
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Brake Slack Adj FRONT |  | 66379.67 | 30000 | 2018-06-09 | 12.5 |  | 0 | 2022-06-01
N7610 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Hyd Cooler Core |  | 34410.8 | 16000 | 2018-06-20 | 6.35 |  | 0 | 2022-06-01
N7654 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Hyd Accum Service Brake |  | 53598.82 | 15000 | 2018-07-30 | 13.5 |  | 0 | 2022-06-01
N2090 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Drv Coupling |  | 20577.1 | 9000 | 2018-09-10 | 4.11 |  | 0 | 2022-06-01
N0020 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Bucket |  | 14715.2 | 6000 | 2018-10-04 | 3.12 |  | 0 | 2022-06-01
N6060 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Oil Cooler - Brakes |  | 54833.54 | 20000 | 2018-10-10 | 12.5 | 17/08/2026 | 0 | 2022-06-01
N4100-R | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Rear Axle RIGHT |  | 54833.54 | 20000 | 2018-10-10 | 12.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 54833.54 | 20000 | 2018-10-10 | 12.5 |  | 0
N7610 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Hyd Cooler Core |  | 54833.54 | 20000 | 2018-10-10 | 12.5 | 17/08/2026 | 0 | 2022-06-01
N0030 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Truck Body |  | 54833.54 | 20000 | 2018-10-10 | 12.5 |  | 0 | 2022-06-01
N4100-L | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Rear Axle LEFT |  | 54833.54 | 20000 | 2018-10-10 | 12.5 |  | 0 | 2022-06-01
N5015 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Oil Cooler AXLE |  | 54833.54 | 20000 | 2018-10-10 | 12.5 | 17/08/2026 | 0 | 2022-06-01
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Brake Slack Adj FRONT |  | 64732.59 | 30000 | 2018-10-18 | 12.5 |  | 0 | 2022-06-01
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Rear Axle LEFT |  | 56902.96 | 20000 | 2018-12-02 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 56902.96 | 20000 | 2018-12-02 | 13.5 |  | 0
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Oil Cooler AXLE |  | 56902.96 | 20000 | 2018-12-02 | 13.5 |  | 0 | 2022-06-01
N4100-R | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Rear Axle RIGHT |  | 56902.96 | 20000 | 2018-12-02 | 13.5 |  | 0 | 2022-06-01
N0030 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Truck Body |  | 56902.96 | 20000 | 2018-12-02 | 13.5 |  | 0
N7420-R | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Hyd Cyl Blade Lift RIGHT |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7087 | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Pump Pilot |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7542-L | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Hyd Cyl Steer LEFT |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7421-L | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Hyd Cyl Blade Tilt LEFT |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7542-R | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Hyd Cyl Steer RIGHT |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7120 | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Pump Steering |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7421-R | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Hyd Cyl Blade Tilt RIGHT |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N7420-L | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Hyd Cyl Blade Lift LEFT |  | 11209.7 | 8000 | 2018-12-16 | 1.18 |  | 0 | 2013-07-03
N6360 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Brake Control Valve |  | 62609 | 30000 | 2018-12-19 | 12 |  | 0
N7541 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Hyd Cyl Access Ladder |  | 70515 | 20000 | 2019-02-15 | 19 |  | 0 |  |  | 339-3275 | CYLINDER GP
N1100 | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Turbo Primary |  | 33341.1 | 18000 | 2019-05-07 | 5.95 |  | 0 | 2022-06-01
N1301 | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Water Pump |  | 33341.1 | 18000 | 2019-05-07 | 5.95 |  | 0 | 2022-06-01
N0020 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Bucket |  | 20577.1 | 10000 | 2019-05-11 | 4.11 |  | 0 | 2022-06-01
N8995 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Operator Seat |  | 20577.1 | 10000 | 2019-05-11 | 4.11 | 01/06/2026 | 0 | 2022-06-01 | Nearest service
N8441 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Rear Axle Dog Bone |  | 76590 | 15000 | 2019-06-23 | 14 |  | 26150 | 2015-09-25 |  | 211-4924 | LATERAL LINK, 793
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Oil Cooler - Brakes |  | 64732.59 | 20000 | 2019-07-14 | 12.5 |  | 13357 | 2013-06-15
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Oil Cooler AXLE |  | 64732.59 | 20000 | 2019-07-14 | 12.5 |  | 13357 | 2013-06-15
N8450-FR | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Diff Stabiliser Brgs FRONT |  | 45967 | 16000 | 2019-07-27 | 12 |  | 0
N4100-L | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Rear Axle LEFT |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0 | 2022-06-01
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Oil Cooler AXLE |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0 | 2012-02-10
N0550 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Air End |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0
N6063 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Oil Cooler - Steering |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0 | 2012-02-10
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Hyd Cooler Core |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0 | 2012-02-10
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Oil Cooler - Brakes |  | 53598.82 | 20000 | 2019-08-04 | 13.5 |  | 0 | 2012-02-10
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Brake Slack Adj FRONT |  | 63459.48 | 30000 | 2019-08-15 | 13.5 |  | 0 | 2022-06-01
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Brake Slack Adj FRONT |  | 60509.94 | 30000 | 2019-09-21 | 12.5 |  | 0 | 2022-06-01
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Brake Slack Adj FRONT |  | 62901.67 | 30000 | 2019-09-25 | 13.5 |  | 0 | 2022-06-01
N8200-01 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Ride Strut POS 1 |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N7474-R | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Hyd Cyl Hoist RIGHT |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N0200 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | A Frame Bearing |  | 47332.5 | 30000 | 2019-10-01 | 7.13 | 08/08/2026 | 0 | 2022-06-01 | Nearest service
N8130-L | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Tie Rods LEFT |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N7474-L | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Hyd Cyl Hoist LEFT |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N8155-R | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Control Arm RIGHT |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N8140 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Y Piece |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N8130-R | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Tie Rods RIGHT |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N8155-L | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Control Arm LEFT |  | 47332.5 | 30000 | 2019-10-01 | 7.13 |  | 0 | 2022-06-01
N9500 | WA | CAT | 85 |  | LO2129 | Cat 992K | Air Cond'r-Serv |  | 30364 | 4000 | 2019-11-04 | 11 |  | 0 | 2025-10-15
N0200 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | A Frame Bearing |  | 79025 | 20000 | 2020-01-16 | 14 |  | 26484 | 2015-11-06 |  | 106-9343 | BEARING
N7474-R | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Hyd Cyl Hoist RIGHT |  | 60870.4 | 30000 | 2020-02-22 | 13.5 |  | 0 | 2011-09-17
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Brake Slack Adj FRONT |  | 60870.4 | 30000 | 2020-02-22 | 13.5 |  | 0 | 2022-06-01
N7654 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Hyd Accum Service Brake |  | 60870.4 | 30000 | 2020-02-22 | 13.5 |  | 0 | 2022-06-01
N7500 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Pin Pull |  | 33117 | 8000 | 2020-02-26 | 11 |  | 0
N0050 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Blade Assembly |  | 34410.8 | 20000 | 2020-03-11 | 6.35 |  | 0 | 2022-06-01
N6030-F | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Brake Slack Adj FRONT |  | 58227.56 | 30000 | 2020-03-22 | 12.5 |  | 0 | 2022-06-01
N4000-F | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Bevel Gear FRONT |  | 75270 | 30000 | 2020-04-18 | 6.5 |  | 30770 | 2008-06-27
N8995 | WA | CAT | 85 |  | LO2129 | Cat 992K | Operator Seat |  | 30364 | 6000 | 2020-05-04 | 11 |  | 0 | 2025-10-15
N7657-C | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Accum Steering CENTER |  | 82501 | 20000 | 2020-05-19 | 18.5 | 11/06/2026 | 21806 | 2026-04-22 |  | 20R-8270 | ACCUMULATOR, STEERING, 793D 793F
N7657-C | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Accum Steering CENTER |  | 82501 | 20000 | 2020-05-19 | 18.5 |  | 21806 | 2026-04-22 |  | 20R-8270 | ACCUMULATOR, STEERING, 793D 793F
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Drive Shaft T/C - Trans |  | 66379.67 | 20000 | 2020-05-29 | 12.5 |  | 19000 | 2014-06-15
N1100 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Turbo Primary |  | 34291 | 5000 | 2020-08-03 | 13.79 |  | 0 | 2022-09-19
N1210 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Fuel Injectors |  | 34291 | 5000 | 2020-08-03 | 13.79 |  | 0 | 2022-09-19
IN0005 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Pre-Service Inspection |  | 52003.6 | 250 | 2020-08-13 | 12 |  | 26379.86 | 2018-08-21
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Drive Shaft T/C - Trans |  | 64732.59 | 20000 | 2020-08-14 | 12.5 |  | 18322 | 2014-03-15
N1210 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Fuel Injectors |  | 32622 | 5000 | 2020-12-02 | 13.79 |  | 0 | 2022-10-15
N1100 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Turbo Primary |  | 32622 | 5000 | 2020-12-02 | 13.79 |  | 0 | 2022-10-15
N7474-L | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Hyd Cyl Hoist LEFT |  | 56902.96 | 30000 | 2020-12-12 | 13.5 |  | 0
N7474-R | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Hyd Cyl Hoist RIGHT |  | 56902.96 | 30000 | 2020-12-12 | 13.5 |  | 0
N6360 | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Brake Control Valve |  | 53910 | 30000 | 2020-12-13 | 12 |  | 0
N6360 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Brake Control Valve |  | 55934 | 30000 | 2021-02-22 | 13.5 |  | 0
N0050 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Blade Assembly |  | 33117 | 12000 | 2021-02-23 | 11 |  | 0
N7514-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Hyd Cyl Ripper Pitch LEFT |  | 47986 | 25000 | 2021-02-27 | 12 |  | 0 | 2013-12-17 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N0121-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Carrier Roller No 1 LEFT |  | 62609 | 8000 | 2021-06-15 | 12 |  | 32914 | 2012-12-19 |  | 309-7679 | ROLLER GP-SF
N0121-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Carrier Roller No 1 RIGHT |  | 62609 | 8000 | 2021-06-15 | 12 |  | 32914 | 2012-12-19 |  | 309-7679 | ROLLER GP-SF
N7510-L | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Hyd Cyl Ripper Lift LEFT |  | 43005.2 | 14000 | 2021-06-18 | 6.35 |  | 17542 | 2018-04-07
N7510-R | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Hyd Cyl Ripper Lift RIGHT |  | 43005.2 | 14000 | 2021-06-18 | 6.35 |  | 17542 | 2018-04-07
N7474-R | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Hyd Cyl Hoist RIGHT |  | 53598.82 | 30000 | 2021-08-14 | 13.5 |  | 0 | 2012-02-10
N6030-F | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Brake Slack Adj FRONT |  | 53598.82 | 30000 | 2021-08-14 | 13.5 |  | 0 | 2022-06-01
N7474-L | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Hyd Cyl Hoist LEFT |  | 53598.82 | 30000 | 2021-08-14 | 13.5 |  | 0 | 2012-02-10
N6360 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Brake Control Valve |  | 43005.2 | 32000 | 2021-08-29 | 6.35 |  | 0 | 2022-06-01
N0144 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Pivot Shaft |  | 43005.2 | 32000 | 2021-08-29 | 6.35 |  | 0 | 2022-06-01
N9500 | NT | CAT | 19 | FleetCo | LO2083 | Cat 993K | Air Cond'r-Serv |  | 36409 | 5000 | 2021-10-03 | 18.5 |  | 0
N9500 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Air Cond'r-Serv |  | 28724 | 4000 | 2021-11-22 | 15 |  | 0 | 2022-12-14
N8995 | NT | CAT | 19 | FleetCo | LO2083 | Cat 993K | Operator Seat |  | 36409 | 6000 | 2021-11-26 | 18.5 |  | 0
N1490 | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Cam Shaft Inspection |  | 24820 | 2000 | 2021-12-10 | 14 |  | 0 | 2026-02-12 |  | 449-9059 | SEAL
N8200-01 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Ride Strut POS 1 |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2013-05-19
N7600-L | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Control Valve LEFT |  | 70621 | 24000 | 2022-01-01 | 15 |  | 22494 | 2016-09-08
N7474-R | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Hyd Cyl Hoist RIGHT |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2013-05-19
N7474-L | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Hyd Cyl Hoist LEFT |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2013-05-19
N8130-R | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Steering Tie Rods RIGHT |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N8122-01 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Wheel Group POS 1 |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N7600-R | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Control Valve RIGHT |  | 70621 | 24000 | 2022-01-01 | 15 |  | 22494 | 2016-09-08
N8122-02 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Wheel Group POS 2 |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N0200 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | A Frame Bearing |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N8155-L | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Steering Control Arm LEFT |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N8140 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Steering Y Piece |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N8155-R | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Steering Control Arm RIGHT |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N8130-L | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Steering Tie Rods LEFT |  | 32588.7 | 30000 | 2022-01-01 | 1.61 |  | 0 | 2022-06-01
N4000 | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Bevel Gear |  | 33341.1 | 24000 | 2022-02-08 | 5.95 |  | 0 | 2021-07-01
N4000 | SA | CAT | 01 | Prominent Hill | GR0996 | Cat 16H | Bevel Gear |  | 41788 | 12000 | 2022-02-27 | 0.75 |  | 28625 | 2012-04-18
N0140 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Equalizer Bar |  | 17737.5 | 8000 | 2022-03-17 | 6.35 |  | 0 | 2022-06-01
N0105-L | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Idler LEFT |  | 14715.2 | 10000 | 2022-04-08 | 3.12 |  | 0 | 2022-06-01
N0050 | WA | CAT | 85 |  | GR1550 | Cat 16M | Blade Assembly |  | 27110.6 | 12000 | 2022-04-08 | 10 |  | 0 | 2018-03-28
N7546 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Cyl Stick |  | 14715.2 | 10000 | 2022-04-08 | 3.12 |  | 0 | 2022-06-01
N7426-R | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Cyl Boom Lift RIGHT |  | 14715.2 | 10000 | 2022-04-08 | 3.12 |  | 0 | 2022-06-01
N7432 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Cyl Bucket |  | 14715.2 | 10000 | 2022-04-08 | 3.12 |  | 0 | 2022-06-01
N6360 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Brake Control Valve |  | 47986 | 30000 | 2022-04-20 | 12 |  | 0
N7460-05 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Feed Swing |  | 32622 | 12000 | 2022-04-24 | 13.79 |  | 0 | 2022-10-15
N7426 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Boom Lift |  | 32622 | 12000 | 2022-04-24 | 13.79 |  | 0 | 2022-10-15
N7595-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Mast Lock RIGHT |  | 32622 | 12000 | 2022-04-24 | 13.79 |  | 0 | 2022-10-15
N7480-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Track Oscillation LEFT |  | 32622 | 12000 | 2022-04-24 | 13.79 |  | 0 | 2022-10-15
N7597 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Boom Swing |  | 32622 | 12000 | 2022-04-24 | 13.79 |  | 0 | 2022-10-15
N7595-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Mast Lock LEFT |  | 32622 | 12000 | 2022-04-24 | 13.79 |  | 0 | 2022-10-15
N6060 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Oil Cooler - Brakes |  | 58227.56 | 20000 | 2022-04-27 | 12.5 |  | 19576 | 2015-01-15
N5015 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Oil Cooler AXLE |  | 58227.56 | 20000 | 2022-04-27 | 12.5 |  | 19576 | 2015-01-15
N1310 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Radiator |  | 43005.2 | 16000 | 2022-04-29 | 6.35 |  | 17542 | 2018-04-07
N0102-L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 24820 | 4000 | 2022-05-02 | 14 |  | 0 | 2026-03-02
N0102-R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 24820 | 4000 | 2022-05-02 | 14 |  | 0 | 2026-03-02
N0104-L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Sprockets LEFT |  | 24820 | 4000 | 2022-05-02 | 14 |  | 0 | 2026-03-02 |  | 433-6739 | 7796590
N0104-R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Sprockets RIGHT |  | 24820 | 4000 | 2022-05-02 | 14 |  | 0 | 2026-03-02 |  | 433-6739 | 7796592
N9500 | WA | CAT | 85 |  | LO2130 | Cat 992K | Air Cond'r-Serv |  | 20261 | 4000 | 2022-05-11 | 11 |  | 0 | 2025-10-21
N6360 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Brake Control Valve |  | 50673 | 30000 | 2022-05-12 | 14 |  | 0
N0134-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Adjuster LEFT |  | 34291 | 14000 | 2022-05-18 | 13.79 |  | 0 | 2022-09-19
N0134-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Adjuster RIGHT |  | 34291 | 14000 | 2022-05-18 | 13.79 |  | 0 | 2022-09-19
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Oil Cooler AXLE |  | 66379.67 | 20000 | 2022-06-06 | 12.5 |  | 28229 | 2016-01-15
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Oil Cooler - Brakes |  | 66379.67 | 20000 | 2022-06-06 | 12.5 |  | 28229 | 2016-01-15
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Hyd Cooler Core |  | 66379.67 | 20000 | 2022-06-06 | 12.5 |  | 28229 | 2016-01-15
N2002 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Oil Cooler - Transmission |  | 41713 | 20000 | 2022-06-10 | 15 |  | 0 |  |  | 0R-3344 | COOLER, OIL, CORE, REMAN
N2440 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Drv Coupling PTO |  | 75270 | 10000 | 2022-06-23 | 6.5 |  | 55941 | 2018-09-29
N7510-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cyl Ripper Lift LEFT |  | 31190.5 | 14000 | 2022-06-25 | 12 |  | 0 | 2018-09-12
N7310-R | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation RIGHT |  | 16244 | 2500 | 2022-06-25 | 9.59 |  | 0 | 2022-06-01
N7421-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cyl Blade Tilt LEFT |  | 31190.5 | 14000 | 2022-06-25 | 12 |  | 0 | 2018-09-12
N7421-R | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cyl Blade Tilt RIGHT |  | 31190.5 | 14000 | 2022-06-25 | 12 |  | 0 | 2018-09-12
N7510-R | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cyl Ripper Lift RIGHT |  | 31190.5 | 14000 | 2022-06-25 | 12 |  | 0 | 2018-09-12
N7310-L | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation LEFT |  | 16244 | 2500 | 2022-06-25 | 9.59 |  | 0 | 2022-06-01
N0139-R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Frame Mid Life RIGHT |  | 49963 | 15000 | 2022-07-09 | 5.5 |  | 27161 | 2015-08-07
N0139-L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Frame Mid Life LEFT |  | 49963 | 15000 | 2022-07-09 | 5.5 |  | 27161 | 2015-08-07
N7330-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Motor Travel LEFT |  | 34291 | 15000 | 2022-07-29 | 13.79 |  | 0 | 2022-09-19
N7330-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Motor Travel RIGHT |  | 34291 | 15000 | 2022-07-29 | 13.79 |  | 0 | 2022-09-19
N3025 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Uni's Tfr - Hitch |  | 28724 | 8000 | 2022-08-15 | 15 |  | 0 | 2022-12-14
N3032 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Uni's Ctr Bearing - Bevel Gear |  | 28724 | 8000 | 2022-08-15 | 15 |  | 0 | 2022-12-14
N1300 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Cooling Sys Service |  | 28724 | 8000 | 2022-08-15 | 15 |  | 0 | 2022-12-14
N3031 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Uni's Trans-Tfr |  | 28724 | 8000 | 2022-08-15 | 15 |  | 0 | 2022-12-14
N1301 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Water Pump |  | 28724 | 8000 | 2022-08-15 | 15 |  | 0 | 2022-12-14
N8400 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Loader Frame Inspect |  | 44396 | 24000 | 2022-09-06 | 15 |  | 0
N0134-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Adjuster RIGHT |  | 32622 | 14000 | 2022-09-16 | 13.79 |  | 0 | 2022-10-15
N0134-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Adjuster LEFT |  | 32622 | 14000 | 2022-09-16 | 13.79 |  | 0 | 2022-10-15
N1301 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Water Pump |  | 34410.8 | 16000 | 2022-10-25 | 6.35 |  | 10084 | 2018-09-15
N8995 | WA | CAT | 85 |  | LO2130 | Cat 992K | Operator Seat |  | 20261 | 6000 | 2022-11-09 | 11 |  | 0 | 2025-10-21
N0103-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Plates LEFT |  | 55934 | 1500 | 2022-11-27 | 13.5 |  | 37177 | 2026-01-10
N7330-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Motor Travel RIGHT |  | 32622 | 15000 | 2022-11-27 | 13.79 |  | 0 | 2022-10-15
N7330-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Motor Travel LEFT |  | 32622 | 15000 | 2022-11-27 | 13.79 |  | 0 | 2022-10-15
N1490 | WA | CAT | 85 |  | LO2122 | Cat 992K | Cam Shaft Inspection |  | 35037 | 1500 | 2022-11-27 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N7658 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Hyd Accum Interaxle |  | 28724 | 10000 | 2022-12-27 | 15 |  | 0 | 2022-12-14
N7310-R | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation RIGHT |  | 18651 | 2500 | 2023-01-02 | 13 |  | 0 | 2022-06-01
N7310-L | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation LEFT |  | 18651 | 2500 | 2023-01-02 | 13 |  | 0 | 2022-06-01
N9500 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Air Cond'r-Serv |  | 58227.56 | 0 | 2023-01-05 | 12.5 |  | 0 | 2022-01-05
N8061-01 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Slew Ring Bolts Check -Initial |  | 23402 | 500 | 2023-01-06 | 18.5 |  | 0
N0145 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Pivot Shaft Brgs |  | 62609 | 15000 | 2023-01-19 | 12 |  | 32914 | 2012-12-19 |  | 7T-4135 | BEARING
N9501 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | A/C Compressor |  | 65021 | 10000 | 2023-01-21 | 8.5 |  | 44622 | 2017-08-01
N8061-01 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Slew Ring Bolts Check -Initial |  | 23756 | 500 | 2023-01-23 | 18.5 |  | 659 | 2022-09-06
N0111-7L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 7 LEFT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-7R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 7 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-1L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 1 LEFT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-2R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 2 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-4L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 4 LEFT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-5L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 5 LEFT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-4R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 4 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-5R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 5 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-3R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 3 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-6R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 6 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-1R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 1 RIGHT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-6L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 6 LEFT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0111-2L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Roller 2 LEFT |  | 17737.5 | 10000 | 2023-01-25 | 6.35 |  | 0 | 2022-06-01
N0500 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Bulk Water Pump |  | 42291 | 5000 | 2023-02-03 | 10 |  | 25191 | 2019-09-04
N0201-01 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | A Frame Bearing Reshim Initial |  | 76600 | 2000 | 2023-02-09 | 14 |  | 57750.1 | 2022-08-19 |  | 8X-2934 | SHIM PACK
N1490 | WA | CAT | 85 |  | LO2121 | Cat 992K | Cam Shaft Inspection |  | 33290 | 1500 | 2023-02-11 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N0101-L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Chain LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 569-2544 | TRACK GP
N0111-1L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 1 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-5L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 5 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-3R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 3 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0103-L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Plates LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02
N0121-L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Carrier Roller No 1 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7679 | ROLLER GP-SF
N0111-6L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 6 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-3L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 3 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 4 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-2R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 2 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0105-LF | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Idler LFT FRONT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 125-3537 | IDLER GP-TRACK
N0111-1R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 1 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0105-RF | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Idler RHT FRONT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 125-3537 | IDLER GP-TRACK
N0105-LR | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Idler LFT REAR |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 125-3537 | IDLER GP-TRACK
N0111-7L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 7 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0121-R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Carrier Roller No 1 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7679 | ROLLER GP-SF
N0105-RR | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Idler RHT REAR |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 125-3537 | IDLER GP-TRACK
N0111-6R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 6 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-4R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 4 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-8L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 8 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0101-R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Chain RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 569-2544 | TRACK GP
N0111-8R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 8 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0103-R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Plates RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02
N0111-7R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 7 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-5R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 5 RIGHT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N0111-2L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Roller 2 LEFT |  | 24820 | 8000 | 2023-02-12 | 14 |  | 0 | 2026-03-02 |  | 309-7678 | ROLLER GP-DF
N7310-L | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation LEFT |  | 18065 | 2500 | 2023-02-16 | 13 |  | 0 | 2022-06-01
N7310-R | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation RIGHT |  | 18065 | 2500 | 2023-02-16 | 13 |  | 0 | 2022-06-01
N2004 | WA | CAT | 85 |  | GR1550 | Cat 16M | Transmission Pump |  | 27110.6 | 14000 | 2023-03-02 | 10 |  | 1285 | 2020-07-14
N7310-R | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation RIGHT |  | 17835 | 2500 | 2023-03-05 | 13 |  | 0 | 2022-06-01
N7310-L | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation LEFT |  | 17835 | 2500 | 2023-03-05 | 13 |  | 0 | 2022-06-01
N0102-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 55934 | 3000 | 2023-03-18 | 13.5 |  | 37177 | 2026-01-10
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | A Frame Bearing Reshim Initial |  | 39200 | 2000 | 2023-04-08 | 14 |  | 21159.1 | 2018-06-14
N3047 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Drv Shft S/Bearing Pump Drives |  | 75270 | 12000 | 2023-04-10 | 6.5 |  | 55834 | 2018-06-17
N6360 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Brake Control Valve |  | 45807 | 30000 | 2023-04-25 | 14 |  | 0
N1302 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Aftercooler Pump |  | 75270 | 12000 | 2023-04-26 | 6.5 |  | 55941 | 2018-09-29
N1210 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Fuel Injectors |  | 75270 | 12000 | 2023-04-26 | 6.5 |  | 55941 | 2018-09-29
N1301 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Water Pump |  | 75270 | 12000 | 2023-04-26 | 6.5 |  | 55941 | 2018-09-29
N8200-01 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Ride Strut POS 1 |  | 28724 | 12000 | 2023-05-09 | 15 |  | 0 | 2022-12-14
N8200-02 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Ride Strut POS 2 |  | 28724 | 12000 | 2023-05-09 | 15 |  | 0 | 2022-12-14
N0201-01 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | A Frame Bearing Reshim Initial |  | 54428 | 2000 | 2023-05-31 | 17 |  | 33839.1 | 2020-01-31 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N8200-04 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Ride Strut POS 4 |  | 67106.81 | 30000 | 2023-06-05 | 12.5 |  | 23503 | 2012-04-15
N8995 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Operator Seat |  | 54781 | 6000 | 2023-06-07 | 15 |  | 32497 | 2019-06-02 |  | 384-6168 | SEAT GP
N0201-01 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | A Frame Bearing Reshim Initial |  | 60498 | 2000 | 2023-06-23 | 15 |  | 42445.1 | 2019-07-06
N1002 | WA | CAT | 85 |  | LO2121 | Cat 992K | Engine Valve Adj |  | 33290 | 3000 | 2023-06-27 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N0140 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Equalizer Bar |  | 62609 | 15000 | 2023-07-07 | 12 |  | 34933 | 2013-05-16 |  | 10R-9161 | BAR GP-EQUALIZER
N8995 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Operator Seat |  | 47986 | 6000 | 2023-07-09 | 12 |  | 29344 | 2020-05-08 |  | 443-8104 | CAT OPERATOR SEAT
N6360 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Brake Control Valve |  | 46731 | 30000 | 2023-07-17 | 16 |  | 0
N7420-R | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Hyd Cyl Blade Lift RIGHT |  | 49898.9 | 16000 | 2023-07-25 | 10 |  | 23519 | 2016-12-05 |  | 389-9512 | BLADE LIFT CYLINDER
N0405 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Mast |  | 34291 | 20000 | 2023-07-27 | 13.79 |  | 0 | 2022-09-19
N0008 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Boom |  | 34291 | 20000 | 2023-07-27 | 13.79 |  | 0
N0020 | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Bucket |  | 11209.7 | 10000 | 2023-08-07 | 1.18 |  | 0 | 2013-07-03
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Engine Valve Adj |  | 56457 | 4000 | 2023-08-11 | 14 |  | 38163 | 2018-11-25 |  | 272-0760 | SEAL-PIP
N9501 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | A/C Compressor |  | 47986 | 7500 | 2023-08-20 | 12 |  | 28346 | 2020-01-24 |  | 106-5122 | COMPRESSOR
N9050 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Starter Motor |  | 47986 | 7500 | 2023-08-20 | 12 |  | 28346 | 2020-01-24 |  | 10R-9816 | MOTOR GP-ELEC
N7500 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Pin Pull |  | 32356 | 8000 | 2023-09-02 | 11 |  | 13367 | 2020-06-09 | THIESS MANAGED
N1002 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Engine Valve Adj |  | 53351 | 4000 | 2023-09-06 | 12 | 04/11/2025 | 37406 | 2020-04-03
N0104-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Sprockets LEFT |  | 21277 | 7500 | 2023-09-17 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0503 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Water Cannon |  | 21277 | 7500 | 2023-09-17 | 14 |  | 0
N0104-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Sprockets RIGHT |  | 21277 | 7500 | 2023-09-17 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0104-R | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Sprockets RIGHT |  | 53910 | 4000 | 2023-10-15 | 12 |  | 38442 | 2018-12-19 |  | 433-6739 | 7796592
N0104-L | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Sprockets LEFT |  | 53910 | 4000 | 2023-10-15 | 12 |  | 38442 | 2018-12-19 |  | 433-6739 | 7796590
N0101-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Chain LEFT |  | 55934 | 6000 | 2023-10-26 | 13.5 |  | 37177 | 2026-01-10 |  | 569-2544 | TRACK GP
N0050 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Blade Assembly |  | 31190.5 | 20000 | 2023-11-07 | 12 |  | 0 | 2022-06-01
N0405 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Mast |  | 32622 | 20000 | 2023-11-25 | 13.79 |  | 0 | 2022-10-15
N8442-07 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Steering Ball Studs POS 7 |  | 47029 | 12000 | 2023-12-06 | 4.12 | 01/06/2026 | 31304 | 2007-03-28 | CC - AMT LEGACY WORK - CANCELLED
N0201-01 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | A Frame Bearing Reshim Initial |  | 71548 | 2000 | 2023-12-31 | 15 |  | 56358.1 | 2020-10-13
N0102-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 47986 | 4000 | 2024-01-03 | 12 |  | 33474 | 2021-08-19
N0104-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Sprockets RIGHT |  | 47986 | 4000 | 2024-01-03 | 12 |  | 33474 | 2021-08-19 |  | 433-6739 | 7796592
N0102-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 47986 | 4000 | 2024-01-03 | 12 |  | 33474 | 2021-08-19
N0104-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Sprockets LEFT |  | 47986 | 4000 | 2024-01-03 | 12 |  | 33474 | 2021-08-19 |  | 433-6739 | 7796590
N0026 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Bucket H-Link |  | 14715.2 | 12000 | 2024-01-09 | 3.12 |  | 0 | 2022-06-01
N7001 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hydraulic Tune |  | 14715.2 | 12000 | 2024-01-09 | 3.12 |  | 0 | 2022-06-01
N8410 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Bucket Pin Assembly |  | 14715.2 | 12000 | 2024-01-09 | 3.12 |  | 0 | 2022-06-01
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Engine Valve Adj |  | 58852 | 4000 | 2024-01-14 | 15 |  | 41876 | 2019-07-16 |  | 272-0760 | SEAL-PIP
N3021 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Uni's Eng - Pump Drive |  | 53598.82 | 10000 | 2024-01-30 | 13.5 |  | 32132 | 2021-07-08
N8450-CE | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Diff Stabiliser Brgs CENTRE |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N4000-RE | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Bevel Gear REAR |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N1000 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Engine |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N2000 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Transmission |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N5000-01 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Final Drive POS 1 |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8270-RR | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Suspension Block RIGHT REAR |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8270-LF | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Suspension Block LEFT FRONT |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N5000-02 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Final Drive POS 2 |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N0200-CE | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | A Frame Bearing - CENTRE |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7232 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Hyd Motor Engine Fan |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N3040-C | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Drive Shaft CENTRE |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8450-FR | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Diff Stabiliser Brgs FRONT |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N2050 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Torque Convertor |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N5000-03 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Final Drive POS 3 |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7653 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Hyd Accum Park Brake |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8450-RE | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Diff Stabiliser Brgs REAR |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N9020 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Alternator |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N4000-F | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Bevel Gear FRONT |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7120 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Pump Steering |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N2004 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Transmission Pump |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N5000-05 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Final Drive POS 5 |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8270-LR | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Suspension Block LEFT REAR |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N2002 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Oil Cooler - Transmission |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N9500-MA | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Air Cond'r-Serv - MAJOR |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N0200-FR | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | A Frame Ball FR |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N3042 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Driveline Ctr Bearing |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7064 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Pump Hoist |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7474-L | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Hyd Cyl Hoist LEFT |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8300 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Artic Hitch |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N3040-02 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Drive Shaft POS 02 |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N3030 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Drive Shaft Trans-Tfr |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N5000-04 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Final Drive POS 4 |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7099 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Pump Steering Hmu |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7020 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Pump Brake |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N1202 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Fuel Transfer Pump |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N8270-RF | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Suspension Block RIGHT FRONT |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7041 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Pump Cooling Fan Engine |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N1310 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Radiator |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7474-R | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Hyd Cyl Hoist RIGHT |  | 28724 | 16000 | 2024-01-31 | 15 |  | 0 | 2022-12-14
N7600-S | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Control Valve - STEERING |  | 49898.9 | 16000 | 2024-02-15 | 10 |  | 25573 | 2018-06-11
N7600-RE | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Control Valve REAR |  | 49898.9 | 16000 | 2024-02-15 | 10 |  | 25573 | 2018-06-11
N7422 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Hyd Cyl Blade Tip |  | 49898.9 | 16000 | 2024-02-15 | 10 |  | 25573 | 2018-06-11
N7600-FR | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Control Valve FRONT |  | 49898.9 | 16000 | 2024-02-15 | 10 |  | 25573 | 2018-06-11
N7657-R | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Hyd Accum Steering RIGHT |  | 26206.72 | 15000 | 2024-02-18 | 13.5 |  | 0 | 2022-06-01
N7657-L | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Hyd Accum Steering LEFT |  | 26206.72 | 15000 | 2024-02-18 | 13.5 |  | 0 | 2022-06-01
N7562-R | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Cyl Tilt RIGHT |  | 44396 | 12000 | 2024-02-21 | 15 |  | 19996 | 2021-08-18
N7490-R | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Cyl Lift RIGHT |  | 44396 | 12000 | 2024-02-21 | 15 |  | 19996 | 2021-08-22
N7490-L | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Cyl Lift LEFT |  | 44396 | 12000 | 2024-02-21 | 15 |  | 19996 | 2021-08-22
N0580 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Air Compressor - Auxiliary |  | 35745 | 6000 | 2024-03-07 | 15 |  | 17568
N9500 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Air Cond'r-Serv |  | 47986 | 5000 | 2024-03-26 | 12 |  | 33474 | 2021-08-19
N7541 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Hyd Cyl Access Ladder |  | 35745 | 24000 | 2024-04-05 | 15 |  | 0
N1002 | NT | CAT | 19 | FleetCo | LO2083 | Cat 993K | Engine Valve Adj |  | 36409 | 3000 | 2024-04-15 | 18.5 |  | 19100 | 2025-11-05
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | A Frame Bearing Reshim Initial |  | 55805 | 2000 | 2024-04-16 | 14 |  | 42993.1 | 2020-07-14
N9020 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Alternator |  | 45967 | 16000 | 2024-04-18 | 12 |  | 20726 | 2015-08-31
N1100-R | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Turbo Primary RIGHT |  | 14154.15 | 9000 | 2024-05-08 | 6.87 |  | 0 | 2022-10-17
N1100-L | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Turbo Primary LEFT |  | 14154.15 | 9000 | 2024-05-08 | 6.87 |  | 0 | 2022-10-17
N1312 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Aftercooler Core |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7600-S | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Control Valve - STEERING |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7422 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Cyl Blade Tip |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N0200 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | A Frame Bearing |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7610 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Cooler Core |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7600-FR | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Control Valve FRONT |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7600-RE | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Control Valve REAR |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7440 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Cyl Centreshift |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N8040 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Circle & Drawbar |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0
N7420-R | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Cyl Blade Lift RIGHT |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0 |  |  | 389-9512 | BLADE LIFT CYLINDER
N7420-L | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Cyl Blade Lift LEFT |  | 25353 | 16000 | 2024-05-10 | 12.5 |  | 0 |  |  | 389-9512 | BLADE LIFT CYLINDER
N1002 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Engine Valve Adj |  | 41729 | 2000 | 2024-05-17 | 1.2 |  | 38840 | 2021-06-27
N7490-R | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Cyl Lift RIGHT |  | 70621 | 12000 | 2024-05-17 | 15 |  | 47505 | 2021-09-08
N7490-L | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Cyl Lift LEFT |  | 70621 | 12000 | 2024-05-17 | 15 |  | 47505 | 2021-09-08
N7004-21 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Hose Clam Cylinder |  | 23756 | 5000 | 2024-05-28 | 18.5 |  | 5254 | 2023-05-26
N9500-MA | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv - MAJOR |  | 18651 | 0 | 2024-05-31 | 13 |  | 0 | 2022-06-01
N9500-MA | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv - MAJOR |  | 17835 | 0 | 2024-05-31 | 13 |  | 0 | 2022-06-01
N9020 | WA | CAT | 85 |  | GR1550 | Cat 16M | Alternator |  | 27110.6 | 7000 | 2024-05-31 | 10 |  | 12845 | 2020-07-14
N9500-MA | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv - MAJOR |  | 16244 | 0 | 2024-05-31 | 9.59 |  | 0 | 2022-06-01
N1002 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Engine Valve Adj |  | 67572 | 4000 | 2024-05-31 | 15 |  | 52669 | 2019-05-24
N9500-MA | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv - MAJOR |  | 18065 | 0 | 2024-05-31 | 13 |  | 0 | 2022-06-01
N9050 | WA | CAT | 85 |  | GR1550 | Cat 16M | Starter Motor |  | 27110.6 | 7000 | 2024-05-31 | 10 |  | 12845 | 2020-07-14
N7610 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Hyd Cooler Core |  | 58227.56 | 20000 | 2024-06-05 | 12.5 |  | 29202 | 2017-04-08
N7361 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Hyd Motor Water Pump |  | 42291 | 10000 | 2024-06-12 | 10 |  | 25144 | 2019-08-18
N0020 | WA | CAT | 85 |  | LO2122 | Cat 992K | Bucket |  | 35037 | 12000 | 2024-06-23 | 11 |  | 15288 | 2022-02-06 | THIESS MANAGED
N0134-R | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Adjuster RIGHT |  | 24820 | 15000 | 2024-06-26 | 14 |  | 0 | 2026-03-02
N0134-L | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Track Adjuster LEFT |  | 24820 | 15000 | 2024-06-26 | 14 |  | 0 | 2026-03-02
N0503 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Water Cannon |  | 17257 | 7500 | 2024-06-30 | 14 |  | 0
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | A Frame Bearing Reshim Initial |  | 67187 | 2000 | 2024-06-30 | 14 |  | 55435.1 | 2022-04-24
N0104-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Sprockets LEFT |  | 17257 | 7500 | 2024-06-30 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0104-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Sprockets RIGHT |  | 17257 | 7500 | 2024-06-30 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N7600 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Control Valve |  | 34410.8 | 30000 | 2024-07-02 | 6.35 |  | 0 | 2022-06-01
N7657-R | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Hyd Accum Steering RIGHT |  | 24344.16 | 15000 | 2024-07-05 | 13.5 |  | 0 | 2022-06-01
N7657-L | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Hyd Accum Steering LEFT |  | 24344.16 | 15000 | 2024-07-05 | 13.5 |  | 0 | 2022-06-01
N7654 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Hyd Accum Service Brake |  | 24344.16 | 15000 | 2024-07-05 | 13.5 |  | 0 | 2022-06-01
N7514-L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Cyl Ripper Pitch LEFT |  | 34671 | 25000 | 2024-07-06 | 14 |  | 0
N7510-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Cyl Ripper Lift RIGHT |  | 34679 | 25000 | 2024-07-06 | 14 |  | 0
N7514-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Cyl Ripper Pitch RIGHT |  | 34671 | 25000 | 2024-07-06 | 14 |  | 0
N9501 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | A/C Compressor |  | 60138 | 10000 | 2024-07-14 | 15 |  | 39892 | 2018-11-02 |  | 0R-6756 | COMPRESSOR GP -H
N1100-L | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Turbo Primary LEFT |  | 53598.82 | 20000 | 2024-07-21 | 13.5 |  | 24467 | 2016-11-09
N1100-R | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Turbo Primary RIGHT |  | 53598.82 | 20000 | 2024-07-21 | 13.5 |  | 24467 | 2016-11-09
N0104-L | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Sprockets LEFT |  | 52003.6 | 4000 | 2024-07-28 | 12 |  | 39972 | 2022-07-05
N0104-R | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Sprockets RIGHT |  | 52003.6 | 4000 | 2024-07-28 | 12 |  | 39972 | 2022-07-05
N7664-UP | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper UPPER |  | 18651 | 10000 | 2024-08-01 | 13 |  | 0 | 2022-06-01
N0695 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Centraliser Assembly |  | 18651 | 10000 | 2024-08-01 | 13 |  | 0 | 2022-06-01
N7664-LW | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper LOWER |  | 18651 | 10000 | 2024-08-01 | 13 |  | 0 | 2022-06-01
N0105-RF | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Idler RHT FRONT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 125-3537 | IDLER GP-TRACK
N0111-7R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 7 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7678 | ROLLER GP-DF
N0111-8R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 8 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7678 | ROLLER GP-DF
N0121-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Carrier Roller No 1 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7679 | ROLLER GP-SF
N0111-2L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 2 LEFT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 309-7678 | ROLLER GP-DF
N0121-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Carrier Roller No 1 LEFT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 309-7679 | ROLLER GP-SF
N0111-6R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 6 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7678 | ROLLER GP-DF
N0111-1R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 1 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7678 | ROLLER GP-DF
N0111-4R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 4 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 4 LEFT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 309-7678 | ROLLER GP-DF
N0111-7L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 7 LEFT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 309-7678 | ROLLER GP-DF
N0111-5L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 5 LEFT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 309-7678 | ROLLER GP-DF
N0105-LR | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Idler LFT REAR |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 125-3537 | IDLER GP-TRACK
N0111-2R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 2 RIGHT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-22 |  | 309-7678 | ROLLER GP-DF
N0105-LF | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Idler LFT FRONT |  | 46731 | 8000 | 2024-08-06 | 16 |  | 28169 | 2020-03-23 |  | 125-3537 | IDLER GP-TRACK
N7657-R | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Hyd Accum Steering RIGHT |  | 23844.2 | 15000 | 2024-08-11 | 13.5 |  | 0 | 2022-06-01
N7654 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Hyd Accum Service Brake |  | 23844.2 | 15000 | 2024-08-11 | 13.5 |  | 0 | 2022-06-01
N7657-L | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Hyd Accum Steering LEFT |  | 23844.2 | 15000 | 2024-08-11 | 13.5 |  | 0 | 2022-06-01
N7664-LW | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper LOWER |  | 16244 | 10000 | 2024-08-15 | 9.59 |  | 0 | 2022-06-01
N7664-UP | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper UPPER |  | 16244 | 10000 | 2024-08-15 | 9.59 |  | 0 | 2022-06-01
N0695 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Centraliser Assembly |  | 16244 | 10000 | 2024-08-15 | 9.59 |  | 0 | 2022-06-01
N4102-01 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Axle Shaft - POS 1 |  | 70621 | 30000 | 2024-08-23 | 15 |  | 30969 | 2018-06-11
N4102-04 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Axle Shaft - POS 4 |  | 70621 | 30000 | 2024-08-23 | 15 |  | 30969 | 2018-06-11
N4102-03 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Axle Shaft - POS 3 |  | 70621 | 30000 | 2024-08-23 | 15 |  | 30969 | 2018-06-11
N0105-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Idler LEFT |  | 23756 | 12000 | 2024-08-31 | 18.5 |  | 0
N0111-1L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 1 LEFT |  | 23756 | 12000 | 2024-08-31 | 18.5 |  | 0
N0105-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Idler RIGHT |  | 23756 | 12000 | 2024-08-31 | 18.5 |  | 0
N0111-1R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 1 RIGHT |  | 23756 | 12000 | 2024-08-31 | 18.5 |  | 0
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | A/C Compressor |  | 41713 | 10000 | 2024-09-04 | 15 |  | 22248 | 2014-04-23
N7420-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Cyl Blade Lift RIGHT |  | 62609 | 12000 | 2024-09-06 | 12 | 21/05/2026 | 43059 | 2017-11-20 | ASAP PLEASE | 20R-9809 | BLADE LIFT CYLINDER
N0104-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Sprockets RIGHT |  | 16307 | 7500 | 2024-09-06 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N7151 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Pump Water Injection (Bean) |  | 16307 | 7500 | 2024-09-06 | 14 |  | 0 |  |  | 521-3019 | PUMP GP-WATER
N0503 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Water Cannon |  | 16307 | 7500 | 2024-09-06 | 14 |  | 0
N0104-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Sprockets LEFT |  | 16307 | 7500 | 2024-09-06 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N6020 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Park Brake |  | 20577.1 | 18000 | 2024-09-08 | 4.11 |  | 0 | 2022-06-01
N1301 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Water Pump |  | 20577.1 | 18000 | 2024-09-08 | 4.11 |  | 0 | 2022-06-01
N4000-F | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Bevel Gear FRONT |  | 20577.1 | 18000 | 2024-09-08 | 4.11 |  | 0 | 2022-06-01
N2002 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Oil Cooler - Transmission |  | 20577.1 | 18000 | 2024-09-08 | 4.11 |  | 0 | 2022-06-01
N2004 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Transmission Pump |  | 20577.1 | 18000 | 2024-09-08 | 4.11 |  | 0 | 2022-06-01
N2000 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Transmission |  | 20577.1 | 18000 | 2024-09-08 | 4.11 |  | 0 | 2022-06-01
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | A Frame Bearing Reshim Initial |  | 64653 | 2000 | 2024-09-10 | 14 |  | 53905.1 | 2021-10-11
N0105-RF | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Idler RHT FRONT |  | 53910 | 8000 | 2024-09-13 | 12 | 01/02/2026 | 38442 | 2018-12-19 |  | 125-3537 | IDLER GP-TRACK
N0105-LF | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Idler LFT FRONT |  | 53910 | 8000 | 2024-09-13 | 12 | 01/02/2026 | 38442 | 2018-12-19 |  | 125-3537 | IDLER GP-TRACK
N0101-L | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Track Chain LEFT |  | 53910 | 8000 | 2024-09-13 | 12 |  | 38442 | 2018-12-19 |  | 569-2544 | TRACK GP
N0101-R | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Track Chain RIGHT |  | 53910 | 8000 | 2024-09-13 | 12 |  | 38442 | 2018-12-19 |  | 569-2544 | TRACK GP
N0695 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Centraliser Assembly |  | 18065 | 10000 | 2024-09-15 | 13 |  | 0 | 2022-06-01
N0302 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Feed Sprocket |  | 18065 | 10000 | 2024-09-15 | 13 |  | 0 | 2022-06-01
N0105-LR | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Idler LFT REAR |  | 34410.8 | 6000 | 2024-09-18 | 6.35 |  | 24492.81 | 2022-07-09
N0105-RF | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Idler RHT FRONT |  | 34410.8 | 6000 | 2024-09-18 | 6.35 |  | 24492.81 | 2022-07-09
N0105-LF | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Idler LFT FRONT |  | 34410.8 | 6000 | 2024-09-18 | 6.35 |  | 24492.81 | 2022-07-09
N7602 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Relief Valve |  | 34291 | 0 | 2024-09-18 | 13.79 | 01/09/2026 | 0 | 2022-09-19
N0105-RR | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Idler RHT REAR |  | 34410.8 | 6000 | 2024-09-18 | 6.35 |  | 24492.81 | 2022-07-09
N0121-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Carrier Roller No 1 RIGHT |  | 23402 | 12000 | 2024-09-19 | 18.5 |  | 0
N0111-1L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 1 LEFT |  | 23402 | 12000 | 2024-09-19 | 18.5 |  | 0
N0121-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Carrier Roller No 1 LEFT |  | 23402 | 12000 | 2024-09-19 | 18.5 |  | 0
N0111-1R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 1 RIGHT |  | 23402 | 12000 | 2024-09-19 | 18.5 |  | 0
N0111-7R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 7 RIGHT |  | 23402 | 12000 | 2024-09-19 | 18.5 |  | 0
N0111-7L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 7 LEFT |  | 23402 | 12000 | 2024-09-19 | 18.5 |  | 0
N1002 | WA | CAT | 85 |  | GR1549 | Cat 16M | Engine Valve Adj |  | 23153 | 2500 | 2024-09-23 | 10 |  | 14535 | 2023-03-16 | THIESS MANAGED | 229-5711 | SEAL-VALVE COVER
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Ride Strut POS 3 |  | 68788 | 25000 | 2024-09-24 | 18.5 | 13/06/2026 | 32485 | 2018-12-11
N8200-04 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Ride Strut POS 4 |  | 68788 | 25000 | 2024-09-24 | 18.5 | 13/06/2026 | 32485 | 2018-12-11
N8432 | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Trunnion Axle Bearings REAR |  | 14154.15 | 10000 | 2024-09-30 | 6.87 |  | 0 | 2022-10-17 | CC - CHECK WEAR - ADVISE IF C/O REQUIRED?
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Air Cond'r-Serv |  | 49506 | 5000 | 2024-09-30 | 14.5 |  | 35730 | 2022-06-09
N7664-LW | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper LOWER |  | 17835 | 10000 | 2024-10-02 | 13 |  | 0 | 2022-06-01
N7664-UP | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper UPPER |  | 17835 | 10000 | 2024-10-02 | 13 |  | 0 | 2022-06-01
N1430 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Air Starter |  | 54979 | 10000 | 2024-10-05 | 14 |  | 36585 | 2023-01-23
N9020 | WA | CAT | 85 |  | LO2122 | Cat 992K | Alternator |  | 35037 | 9000 | 2024-10-09 | 11 | 20/06/2026 | 19479 | 2023-02-24 | THIESS MANAGED
N9050-L | WA | CAT | 85 |  | LO2122 | Cat 992K | Starter Motor LEFT |  | 35037 | 9000 | 2024-10-09 | 11 | 20/06/2026 | 19479 | 2023-02-24 | THIESS MANAGED
N9050-R | WA | CAT | 85 |  | LO2122 | Cat 992K | Starter Motor RIGHT |  | 35037 | 9000 | 2024-10-09 | 11 | 20/06/2026 | 19479 | 2023-02-24 | THIESS MANAGED
N0201-01 | NT | CAT | 01 | Idle Plant / Off Hired | RD1902 | Cat 785C XQ | A Frame Bearing Reshim Initial |  | 46670 | 2000 | 2024-10-11 | 11.43 |  | 37881.1 | 2018-11-30 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N7421-R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Hyd Cyl Blade Tilt RIGHT |  | 17737.5 | 14000 | 2024-10-16 | 6.35 |  | 0 | 2022-06-01
N7514-R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Hyd Cyl Ripper Pitch RIGHT |  | 17737.5 | 14000 | 2024-10-16 | 6.35 |  | 0 | 2022-06-01
N0201-01 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | A Frame Bearing Reshim Initial |  | 77195 | 2000 | 2024-10-17 | 14 |  | 66969 | 2024-04-02 |  | 8X-2934 | SHIM PACK
N7421-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Blade Tilt RIGHT |  | 33117 | 8000 | 2024-10-21 | 11 |  | 18695 | 2021-08-21 |  | 20R-9634 | Tilt Cylinder
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Hyd Cyl Hoist LEFT |  | 50845.5 | 24000 | 2024-10-25 | 13.75 |  | 18873 | 2017-12-05
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 50845.5 | 24000 | 2024-10-25 | 13.75 |  | 18873 | 2017-12-05
N2000 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Transmission |  | 75270 | 10000 | 2024-10-27 | 6.5 |  | 61510 | 2020-09-21
N1490 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Cam Shaft Inspection |  | 33117 | 2000 | 2024-10-31 | 11 |  | 24801 | 2023-04-03 |  | 449-9059 | SEAL
N0100-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Group RIGHT |  | 34291 | 7000 | 2024-11-06 | 13.79 |  | 19459 | 2022-07-01
N0100-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Group LEFT |  | 34291 | 7000 | 2024-11-06 | 13.79 |  | 19459 | 2022-07-01
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Ride Strut POS 3 |  | 67791 | 25000 | 2024-11-08 | 18.5 |  | 32316 | 2019-03-12
N8995 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Operator Seat |  | 54428 | 6000 | 2024-11-12 | 17 |  | 38877 | 2022-01-28 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | A Frame Bearing Reshim Initial |  | 41713 | 2000 | 2024-11-15 | 15 |  | 31328.1 | 2020-03-30 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N7602 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Relief Valve |  | 32622 | 0 | 2024-11-21 | 13.79 |  | 0 | 2022-11-22
N0201-01 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | A Frame Bearing Reshim Initial |  | 39272 | 2000 | 2024-11-22 | 15 |  | 28997.1 | 2020-03-04 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N7474-L | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Hyd Cyl Hoist LEFT |  | 71898 | 27000 | 2024-11-22 | 18.5 |  | 34693 | 2019-03-31
N0102-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 62609 | 4000 | 2024-11-24 | 12 |  | 52010 | 2021-01-22
N0102-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 62609 | 4000 | 2024-11-24 | 12 |  | 52010 | 2021-01-22
N0104-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Sprockets RIGHT |  | 62609 | 4000 | 2024-11-24 | 12 |  | 52010 | 2021-01-22 |  | 433-6739 | 7796592
N0104-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Sprockets LEFT |  | 62609 | 4000 | 2024-11-24 | 12 |  | 52010 | 2021-01-22 |  | 433-6739 | 7796590
N7310-L | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation LEFT |  | 7751 | 2500 | 2024-11-26 | 9.59 |  | 0 | 2024-03-28
N7310-R | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Hyd Motor Rotation RIGHT |  | 7751 | 2500 | 2024-11-26 | 9.59 |  | 0 | 2024-03-28
N0103-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Plates RIGHT |  | 47986 | 8000 | 2024-12-01 | 12 |  | 33474 | 2021-08-19
N0101-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Chain LEFT |  | 47986 | 8000 | 2024-12-01 | 12 |  | 33474 | 2021-08-19 |  | 569-2544 | TRACK GP
N0103-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Plates LEFT |  | 47986 | 8000 | 2024-12-01 | 12 |  | 33474 | 2021-08-19
N0101-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Chain RIGHT |  | 47986 | 8000 | 2024-12-01 | 12 |  | 33474 | 2021-08-19 |  | 569-2544 | TRACK GP
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Operator Seat |  | 49506 | 6000 | 2024-12-08 | 14.5 |  | 35727 | 2022-01-27 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8995 | WA | CAT | 19 | Sanjiv Ridge | RD6222 | Cat 740GC | Operator Seat |  | 15335.9 | 10000 | 2024-12-10 | 10 |  | 0 | 2025-04-05
N1312-R | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Aftercooler Core - RIGHT |  | 42291 | 20000 | 2024-12-14 | 10 |  | 16989 | 2012-05-10 |  | 569-6955 | CORE AS-AFTERCOOLER
N1312-L | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Aftercooler Core - LEFT |  | 42291 | 20000 | 2024-12-14 | 10 |  | 16989 | 2012-05-10 |  | 569-6955 | CORE AS-AFTERCOOLER
N1310 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Radiator |  | 42291 | 20000 | 2024-12-14 | 10 |  | 16989 | 2012-05-10
N0104-R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Sprockets RIGHT |  | 49963 | 4000 | 2024-12-17 | 5.5 |  | 43066 | 2021-07-21 |  | 433-6739 | 7796592
N0104-L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Sprockets LEFT |  | 49963 | 4000 | 2024-12-17 | 5.5 |  | 43066 | 2021-07-21 |  | 433-6739 | 7796590
N0121-R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Carrier Roller No 1 RIGHT |  | 55435 | 18000 | 2024-12-18 | 18.5 |  | 27710 | 2019-08-29
N7514-L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Hyd Cyl Ripper Pitch LEFT |  | 17737.5 | 14000 | 2024-12-19 | 6.35 |  | 401 | 2021-03-11
N7474-L | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Hyd Cyl Hoist LEFT |  | 59122 | 27000 | 2024-12-22 | 18.5 | 18/05/2026 | 22474 | 2017-06-11 | ZX
N0104-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Sprockets LEFT |  | 46731 | 6000 | 2024-12-22 | 16 |  | 32376 | 2021-04-11 |  | 433-6739 | 7796590
N0104-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Sprockets RIGHT |  | 46731 | 6000 | 2024-12-22 | 16 |  | 32379 | 2021-04-11 |  | 433-6739 | 7796592
N1400 | WA | CAT | 85 |  | LO2121 | Cat 992K | Belt Tensioner Assembly |  | 33290 | 9000 | 2024-12-24 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N9050-R | WA | CAT | 85 |  | LO2121 | Cat 992K | Starter Motor RIGHT |  | 33290 | 9000 | 2024-12-24 | 11 | 13/06/2026 | 18565 | 2022-04-14 | THIESS MANAGED
N9501 | WA | CAT | 85 |  | LO2121 | Cat 992K | A/C Compressor |  | 33290 | 9000 | 2024-12-24 | 11 | 13/06/2026 | 18565 | 2022-04-14 | THIESS MANAGED
N9050-L | WA | CAT | 85 |  | LO2121 | Cat 992K | Starter Motor LEFT |  | 33290 | 9000 | 2024-12-24 | 11 | 13/06/2026 | 18565 | 2022-04-14 | THIESS MANAGED
N4110-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Steering Clutch/Brk LEFT |  | 31190.5 | 25000 | 2024-12-28 | 12 |  | 0 | 2018-09-12
N4110-R | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Steering Clutch/Brk RIGHT |  | 31190.5 | 25000 | 2024-12-28 | 12 |  | 0 | 2018-09-12
N6200-LR | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Press Converter LEFT REAR |  | 67400 | 10000 | 2024-12-29 | 17 |  | 48651 | 2019-07-11 |  | 8X-7220 | CHAMBER, BRAKE
N7300 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Motor Rod Loader |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7664 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7426 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Lift |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7668-UP | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Support UPPER |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7460-03 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump RIGHT |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7460-02 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump LEFT |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7460-04 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Ext |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7597 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Swing |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N7460-05 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Swing |  | 18651 | 12000 | 2025-01-01 | 13 |  | 0 | 2022-06-01
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | A/C Compressor |  | 39658.4 | 10000 | 2025-01-03 | 15 |  | 22005 | 2019-02-11
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | A/C Compressor |  | 39658.4 | 10000 | 2025-01-03 | 15 |  | 22005 | 2019-02-11
N8995 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Operator Seat |  | 62609 | 6000 | 2025-01-03 | 12 |  | 50489 | 2020-09-25 |  | 443-8104 | CAT OPERATOR SEAT
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | A/C Compressor |  | 58852 | 10000 | 2025-01-06 | 15 |  | 41254 | 2019-05-09 |  | 0R-6756 | COMPRESSOR GP -H
N1420 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Air Compressor |  | 44396 | 12000 | 2025-01-08 | 15 |  | 24824 | 2022-09-19
N7474-L | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Hyd Cyl Hoist LEFT |  | 65569 | 27000 | 2025-01-12 | 18.5 | 03/05/2026 | 29304 | 2018-01-19
N0104-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Sprockets LEFT |  | 14426 | 7500 | 2025-01-18 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0104-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Sprockets RIGHT |  | 14426 | 7500 | 2025-01-18 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0503 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Water Cannon |  | 14426 | 7500 | 2025-01-18 | 14 |  | 0
N7151 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Water Injection (Bean) |  | 14426 | 7500 | 2025-01-18 | 14 |  | 0 |  |  | 521-3019 | PUMP GP-WATER
N9501 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | A/C Compressor |  | 53351 | 10000 | 2025-01-18 | 12 |  | 37406 | 2020-04-03
N6200-LR | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Press Converter LEFT REAR |  | 69305 | 10000 | 2025-01-21 | 17 |  | 50933 | 2020-11-01 |  | 8X-7220 | CHAMBER, BRAKE
N7474-L | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Hyd Cyl Hoist LEFT |  | 65303 | 27000 | 2025-01-26 | 18.5 |  | 29298 | 2018-03-12
N0300-C | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Feed Chain CENTRE |  | 9782 | 2000 | 2025-01-27 | 16 |  | 0 | 2025-06-20
N0300 | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Feed Chain |  | 9782 | 2000 | 2025-01-27 | 16 |  | 0 | 2025-06-20
N1100 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Turbo Primary |  | 43005.2 | 16000 | 2025-01-27 | 6.35 |  | 23922 | 2019-11-04
N1301 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Water Pump |  | 43005.2 | 16000 | 2025-01-27 | 6.35 |  | 23922 | 2019-11-04
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Air Cond'r-Serv |  | 45745.5 | 5000 | 2025-02-01 | 13 |  | 34493 | 2020-01-01
N7426-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Boom Lift RIGHT |  | 23756 | 15000 | 2025-02-09 | 18.5 |  | 0
N7426-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Boom Lift LEFT |  | 23756 | 15000 | 2025-02-09 | 18.5 |  | 0
N7460-05 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Swing |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N7668-UP | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Support UPPER |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N7300 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Motor Rod Loader |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N7664 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N7460-04 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Ext |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N7597 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Swing |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N0008 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Boom |  | 18065 | 12000 | 2025-02-15 | 13 |  | 0 | 2022-06-01
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Alternator |  | 58852 | 10000 | 2025-02-17 | 15 |  | 41876 | 2019-07-16 |  | 10R-8755 | ALTERNATOR GP -B
N1310 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Radiator |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0
N1100-R | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Turbo Primary RIGHT |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N5015 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Oil Cooler AXLE |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N3028 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Drive Shaft T/C - Trans |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N6030-RE | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Brake Slack Adj REAR |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N1100-L | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Turbo Primary LEFT |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N6063 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Oil Cooler - Steering |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N6060 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Oil Cooler - Brakes |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N0550 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Air End |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N7610 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Hyd Cooler Core |  | 26206.72 | 20000 | 2025-02-22 | 13.5 |  | 0 | 2022-06-01
N7426-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Boom Lift LEFT |  | 23402 | 15000 | 2025-02-28 | 18.5 |  | 0
N7474-L | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Hyd Cyl Hoist LEFT |  | 59517 | 27000 | 2025-02-28 | 18.5 | 26/05/2026 | 24125 | 2017-09-14 | ZX
N7546-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Stick RIGHT |  | 23402 | 15000 | 2025-02-28 | 18.5 |  | 0
N7426-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Boom Lift RIGHT |  | 23402 | 15000 | 2025-02-28 | 18.5 |  | 0
N7510-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Hyd Cyl Ripper Lift RIGHT |  | 31311 | 25000 | 2025-03-03 | 14 |  | 0
N0201-01 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | A Frame Bearing Reshim Initial |  | 67400 | 2000 | 2025-03-04 | 17 |  | 57743 | 2023-10-01 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N7597 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Swing |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7480 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Track Oscillation |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7460-02 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump LEFT |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7460-05 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Swing |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7460-04 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Ext |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7460-03 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump RIGHT |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7668-UP | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Support UPPER |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7300 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Motor Rod Loader |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7426 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Lift |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N7664 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper |  | 17835 | 12000 | 2025-03-05 | 13 |  | 0 | 2022-06-01
N0121-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Carrier Roller No 1 RIGHT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0105-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Idler LEFT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0134-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Track Adjuster LEFT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0140 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Equalizer Bar |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 526-3821 | BAR AS-EQUAL
N0121-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Carrier Roller No 1 LEFT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0033-PR | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Water Tank - PRIMARY |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0
N0033-SC | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Water Tank - SECONDARY |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0
N0105-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Idler RIGHT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0123-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Carrier Roller No 3 RIGHT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Carrier Roller No 2 LEFT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Carrier Roller No 2 RIGHT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0123-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Carrier Roller No 3 LEFT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0101-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Track Chain RIGHT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N0134-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Track Adjuster RIGHT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0101-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Track Chain LEFT |  | 21277 | 15000 | 2025-03-06 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N7300 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Motor Rod Loader |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N0008 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Boom |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7426 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Lift |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7668-UP | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Support UPPER |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7597 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Boom Swing |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7460-03 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump RIGHT |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7460-05 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Swing |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7460-04 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Ext |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7664 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7460-02 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump LEFT |  | 16244 | 12000 | 2025-03-11 | 9.59 |  | 0 | 2022-06-01
N7562-R | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Cyl Tilt RIGHT |  | 70621 | 12000 | 2025-03-13 | 15 |  | 52004 | 2022-07-12
N8200-04 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Ride Strut POS 4 |  | 61931 | 25000 | 2025-03-16 | 18.5 | 24/05/2026 | 28826 | 2018-07-06
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Ride Strut POS 3 |  | 61931 | 25000 | 2025-03-16 | 18.5 | 24/05/2026 | 28826 | 2018-07-06
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Ride Strut POS 3 |  | 50845.5 | 20000 | 2025-03-18 | 13.75 |  | 24854 | 2018-03-20 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Ride Strut POS 4 |  | 50845.5 | 20000 | 2025-03-18 | 13.75 |  | 24854 | 2018-03-20 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Steering Linkage Group RIGHT |  | 49506 | 20000 | 2025-03-21 | 14.5 |  | 23231 | 2016-09-10 |  | 2A-7217 | LINK,STEERING,785
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Steering Linkage Group LEFT |  | 49506 | 20000 | 2025-03-21 | 14.5 |  | 23231 | 2016-09-10 |  | 2A-7217 | LINK,STEERING,785
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 49506 | 20000 | 2025-03-21 | 14.5 |  | 23231 | 2016-09-10
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Steering Y Piece |  | 49506 | 20000 | 2025-03-21 | 14.5 |  | 23231 | 2016-09-08
N0050 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Blade Assembly |  | 49898.9 | 20000 | 2025-03-21 | 10 |  | 25573 | 2018-06-11
N9500-MA | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Air Cond'r-Serv - MAJOR |  | 78345 | 18000 | 2025-03-23 | 14 | 07/05/2026 | 54312 | 2021-08-16 |  | 137-2134 | AIR CONDITIONER GP
N9020 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Alternator |  | 67600 | 10000 | 2025-03-24 | 17 |  | 50292 | 2019-08-30 |  | 10R-8755 | ALTERNATOR GP_B
N0050 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Blade Assembly |  | 25353 | 20000 | 2025-03-26 | 12.5 |  | 0
N0201-01 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | A Frame Bearing Reshim Initial |  | 79490 | 2000 | 2025-03-30 | 14 |  | 71560 | 2024-11-11 |  | 8X-2934 | SHIM PACK
N1490 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Cam Shaft Inspection |  | 32356 | 2000 | 2025-04-02 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 449-9059 | SEAL
N0111-2R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 2 RIGHT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N0111-6R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 6 RIGHT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N0111-5R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 5 RIGHT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N0111-4R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 4 RIGHT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N0111-3R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 3 RIGHT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N0111-2L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 2 LEFT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N0111-3L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 3 LEFT |  | 55435 | 22000 | 2025-04-05 | 18.5 |  | 25708 | 2019-04-16
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Press Converter RIGHT REAR |  | 49506 | 10000 | 2025-04-09 | 14.5 |  | 33497 | 2020-01-01 |  | 8X-7220 | CHAMBER, BRAKE
N1004 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Engine Midlife |  | 52003.6 | 9000 | 2025-04-18 | 12 |  | 38143 | 2022-01-15
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | A/C Compressor |  | 67187 | 10000 | 2025-04-25 | 14 |  | 51608 | 2021-01-17 |  | 0R-6756 | COMPRESSOR GP -H
N1002 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Engine Valve Adj |  | 33117 | 4000 | 2025-05-01 | 11 |  | 24801 | 2023-04-03 |  | 449-9059 | SEAL
N7514-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Cyl Ripper Pitch LEFT |  | 62609 | 25000 | 2025-05-02 | 12 |  | 32914 | 2012-12-19 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N7514-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Cyl Ripper Pitch RIGHT |  | 62609 | 25000 | 2025-05-02 | 12 |  | 32914 | 2012-12-19 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N7151 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Water Injection (Bean) |  | 12951 | 7500 | 2025-05-04 | 14 |  | 0 |  |  | 521-3019 | PUMP GP-WATER
N0503 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Water Cannon |  | 12951 | 7500 | 2025-05-04 | 14 |  | 0
N0104-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Sprockets RIGHT |  | 12951 | 7500 | 2025-05-04 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0104-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Sprockets LEFT |  | 12951 | 7500 | 2025-05-04 | 14 |  | 0 |  |  | 211-9843 | SPROCKET
N0520 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Pre Lube Pump |  | 47986 | 15000 | 2025-05-06 | 12 |  | 28346 | 2020-01-24 |  | 389-8169 | MOTOR GP-ELECTRIC
N1430 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Air Starter |  | 53351 | 10000 | 2025-05-06 | 12 |  | 38702 | 2021-05-01
N1312-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Aftercooler Core - RIGHT |  | 47986 | 15000 | 2025-05-06 | 12 | 06/07/2026 | 28346 | 2020-01-24 |  | 528-0686 | CORE AS-AFTERCOOLER
N7610 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Hyd Cooler Core |  | 47986 | 15000 | 2025-05-06 | 12 |  | 28346 | 2020-01-24 |  | 0R-5515 | CORE AS OIL
N9502 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | A/C Condenser |  | 47986 | 15000 | 2025-05-06 | 12 |  | 28346 | 2020-01-24 |  | 103-9527 | CONDENSER GP
N1312-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Aftercooler Core - LEFT |  | 47986 | 15000 | 2025-05-06 | 12 |  | 28346 | 2020-01-24 |  | 539-8656 | CORE AS-AFTERCOOLER
N9500-MA | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Air Cond'r-Serv - MAJOR |  | 47986 | 15000 | 2025-05-06 | 12 |  | 28346 | 2020-01-24 |  | 418-6835 | HEATER & AC GP
N7232 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Hyd Motor Engine Fan |  | 47986 | 15000 | 2025-05-06 | 12 | 06/07/2026 | 28346 | 2020-01-24 |  | 10R-5601 | MOTOR GP
N8995 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Operator Seat |  | 67400 | 6000 | 2025-05-06 | 17 |  | 54820 | 2021-12-08 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9501 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | A/C Compressor |  | 67572 | 10000 | 2025-05-07 | 15 |  | 51787 | 2019-03-31
N0100-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Group RIGHT |  | 32622 | 7000 | 2025-05-09 | 13.79 |  | 20330 | 2022-07-01
N0100-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Group LEFT |  | 32622 | 7000 | 2025-05-09 | 13.79 |  | 20330 | 2022-07-01
N0144 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Pivot Shaft |  | 34410.8 | 32000 | 2025-05-13 | 6.35 |  | 0 | 2022-06-01
N0111-1L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 1 LEFT |  | 46731 | 8000 | 2025-05-13 | 16 |  | 32643 | 2021-05-04 |  | 309-7678 | ROLLER GP-DF
N6360 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Brake Control Valve |  | 34410.8 | 32000 | 2025-05-13 | 6.35 |  | 0 | 2022-06-01
N0139-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Frame Mid Life LEFT |  | 62609 | 15000 | 2025-05-14 | 12 |  | 43059 | 2017-11-20
N0134-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Adjuster LEFT |  | 62609 | 15000 | 2025-05-14 | 12 |  | 43059 | 2017-11-20
N0139-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Frame Mid Life RIGHT |  | 62609 | 15000 | 2025-05-14 | 12 |  | 43059 | 2017-11-20
N0104-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Sprockets LEFT |  | 32356 | 6000 | 2025-05-17 | 11 |  | 22223 | 2022-07-04 | THIESS MANAGED | 433-6739 | 7796590
N7514-L | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Hyd Cyl Ripper Pitch LEFT |  | 52003.6 | 26000 | 2025-05-17 | 12 |  | 21491.68 | 2016-12-09
N2050 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Torque Convertor |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N4000-RE | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Bevel Gear REAR |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7070 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Pump Implement |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7605 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Steering Hmu |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Hyd Cyl Steer RIGHT |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N2000 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Transmission |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N5000-02 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Final Drive POS 2 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N5000-01 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Final Drive POS 1 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N6000-04 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Brake POS 4 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N9020 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Alternator |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N1000 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Engine |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7233 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Motor Cool Fan Eng |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N4000-F | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Bevel Gear FRONT |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7542-L | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Hyd Cyl Steer LEFT |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N2004 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Transmission Pump |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N8430-RE | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Trunnion Axle REAR |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Air Cond'r-Serv |  | 44852.3 | 5000 | 2025-05-19 | 15 |  | 34249 | 2020-09-05
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Air Cond'r-Serv |  | 44852.3 | 5000 | 2025-05-19 | 15 |  | 34249 | 2020-09-05
N5000-04 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Final Drive POS 4 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N8300 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Artic Hitch |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Brake POS 2 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Brake POS 1 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Final Drive POS 3 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7041 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Pump Cooling Fan Engine |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N1310 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Radiator |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7652 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Hyd Accum Ride Ctrl Reseal |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7120 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Pump Steering |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7023 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Pump Brake & Pilot |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N8432 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Trunnion Axle Bearings REAR |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N6000-03 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Brake POS 3 |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N7490-R | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Hyd Cyl Lift RIGHT |  | 21494.7 | 20000 | 2025-05-19 | 4 |  | 0 | 2012-09-12
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | A Frame Bearing Reshim Initial |  | 70515 | 2000 | 2025-05-20 | 19 |  | 61431 | 2024-07-23 |  | 8X-2934 | SHIM PACK
N9500 | WA | CAT | 85 | McPhee Creek | RD6651 | Cat 777 | Air Cond'r-Serv |  | 2803.3 | 0 | 2025-05-21 | 8.55 |  | 0 | 2024-05-21
N8820 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Boom Pivot |  | 22440 | 18000 | 2025-05-23 | 12 |  | 0
N1100-R | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Turbo Primary RIGHT |  | 60509.94 | 20000 | 2025-05-23 | 12.5 |  | 35882 | 2018-11-14
N1100-L | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Turbo Primary LEFT |  | 60509.94 | 20000 | 2025-05-23 | 12.5 |  | 35882 | 2018-11-14
N1310 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Radiator |  | 62609 | 15000 | 2025-05-23 | 12 |  | 43168 | 2017-12-11 |  | 371-6833 | RADIATOR AR
N8995 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Operator Seat |  | 69305 | 6000 | 2025-05-25 | 17 |  | 57051 | 2022-05-24 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N7474-R | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 67683.26 | 30000 | 2025-05-27 | 12.5 |  | 33105 | 2014-04-23
N7541 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Hyd Cyl Access Ladder |  | 75619 | 20000 | 2025-05-29 | 19 |  | 48694 | 2019-09-28 |  | 339-3275 | CYLINDER GP
N3021 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Uni's Eng - Pump Drive |  | 54833.54 | 10000 | 2025-05-30 | 12.5 | 17/08/2026 | 40293 | 2019-09-01
N7657-R | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Hyd Accum Steering RIGHT |  | 53351 | 20000 | 2025-05-31 | 12 | 04/11/2025 | 29007 | 2017-11-20 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N8122-02 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Wheel Group POS 2 |  | 53351 | 20000 | 2025-05-31 | 12 | 04/11/2025 | 29006 | 2017-11-18 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N6060-F | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Oil Cooler - Brakes FRONT |  | 53351 | 20000 | 2025-05-31 | 12 | 04/11/2025 | 29007 | 2017-11-23 |  | 10R-0817 | CORE GP-O CLR
N8200-02 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Ride Strut POS 2 |  | 53351 | 20000 | 2025-05-31 | 12 | 04/11/2025 | 29006 | 2017-11-18
N0145-R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Pivot Shaft Brgs RIGHT |  | 9782 | 4000 | 2025-06-01 | 16 |  | 0 | 2025-06-20
N8200-04 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Ride Strut POS 4 |  | 62083 | 25000 | 2025-06-01 | 18.5 | 13/08/2026 | 30403 | 2019-03-03
N0145-L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Pivot Shaft Brgs LEFT |  | 9782 | 4000 | 2025-06-01 | 16 |  | 0 | 2025-06-20
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Ride Strut POS 3 |  | 62083 | 25000 | 2025-06-01 | 18.5 | 13/08/2026 | 30403 | 2019-03-03
N7657-L | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Hyd Accum Steering LEFT |  | 53351 | 20000 | 2025-06-03 | 12 | 04/11/2025 | 29039 | 2018-01-09 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N4102-03 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Axle Shaft - POS 3 |  | 53351 | 20000 | 2025-06-03 | 12 | 04/11/2025 | 29039 | 2018-01-12 |  | 6G-6408 | SHAFT-AXLE (LH)
N0200 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | A Frame Bearing |  | 53351 | 20000 | 2025-06-03 | 12 | 04/11/2025 | 29039 | 2018-01-12 |  | 6V-0444 | BEARING, PLAIN, SPHERICAL
N4102-04 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Axle Shaft - POS 4 |  | 53351 | 20000 | 2025-06-03 | 12 | 04/11/2025 | 29039 | 2018-01-12 |  | 6G-6407 | SHAFT-AXLE (RH)
N0145 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Pivot Shaft Brgs |  | 46895 | 18000 | 2025-06-08 | 13.5 |  | 24113 | 2019-03-12 |  | 7T-4135 | BEARING
N0556 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Air Safety Valve |  | 786 | 0 | 2025-06-14 | 14 |  | 0 | 2024-06-14 |  | 549-2163 | VALVE-RELIEF 160psi
N0201-01 | WA | CAT | 01 |  | RD4247 | Cat 789C | A Frame Bearing Reshim Initial |  | 59268 | 2000 | 2025-06-14 | 20 |  | 50304 | 2021-10-21
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Ride Strut POS 4 |  | 60646.3 | 20000 | 2025-06-15 | 13.75 |  | 35881 | 2020-06-04
N0104-R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Sprockets RIGHT |  | 45807 | 4000 | 2025-06-16 | 14 |  | 36961 | 2022-07-22 |  | 433-6739 | 7796592
N0104-L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Sprockets LEFT |  | 45807 | 4000 | 2025-06-16 | 14 |  | 36961 | 2022-07-22 |  | 433-6739 | 7796590
N9500 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Air Cond'r-Serv |  | 62609 | 5000 | 2025-06-19 | 12 |  | 53489 | 2022-01-20
N0111-8L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 8 LEFT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 52712 | 24000 | 2025-06-20 | 13.75 |  | 24006 | 2019-05-03
N0111-7L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 7 LEFT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-3R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 3 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-1L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 1 LEFT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-8R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 8 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-2L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 2 LEFT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-5R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 5 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-6R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 6 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-5L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 5 LEFT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-6L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 6 LEFT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-7R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 7 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-2R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 2 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0111-4R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 4 RIGHT |  | 45807 | 8000 | 2025-06-20 | 14 |  | 33026 | 2020-11-29 |  | 309-7678 | ROLLER GP-DF
N0201-01 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | A Frame Bearing Reshim Initial |  | 54979 | 2000 | 2025-06-22 | 14 |  | 48214 | 2025-02-18 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1310 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Radiator |  | 46731 | 15000 | 2025-06-22 | 16 |  | 26290 | 2019-09-22 |  | 371-6833 | RADIATOR AR
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Operator Seat |  | 64230 | 6000 | 2025-06-22 | 14 |  | 53474 | 2022-07-15 |  | 384-6168 | SEAT GP
N1100-R | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Turbo Primary RIGHT |  | 66446.13 | 20000 | 2025-06-22 | 12.5 |  | 42191.07 | 2015-03-05
N0105-RR | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Idler RHT REAR |  | 46731 | 8000 | 2025-06-25 | 16 |  | 33335 | 2021-06-29 |  | 125-3537 | IDLER GP-TRACK
N7542-R | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Hyd Cyl Steer RIGHT |  | 53351 | 20000 | 2025-06-27 | 12 | 04/11/2025 | 29334 | 2018-04-25 |  | 1U-3182 | CYL, STEERING, 785
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Ride Strut POS 3 |  | 58874 | 20000 | 2025-06-29 | 13.75 |  | 34296 | 2020-08-04
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Press Converter LEFT REAR |  | 49506 | 10000 | 2025-07-04 | 14.5 |  | 34744 | 2020-08-07 |  | 8X-7220 | CHAMBER, BRAKE
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Air Starter |  | 49506 | 10000 | 2025-07-04 | 14.5 |  | 34745 | 2020-03-30
N8432 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Trunnion Axle Bearings REAR |  | 70621 | 12000 | 2025-07-05 | 15 |  | 53713 | 2022-11-09
N1430 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Air Starter |  | 67572 | 10000 | 2025-07-05 | 15 |  | 52669 | 2019-05-24
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Uni's Eng - Pump Drive |  | 49506 | 10000 | 2025-07-06 | 14.5 |  | 34783 | 2020-11-06
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Operator Seat |  | 67187 | 6000 | 2025-07-06 | 14 |  | 56622 | 2022-12-20 |  | 384-6168 | SEAT GP
N1002 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Engine Valve Adj |  | 59122 | 4000 | 2025-07-08 | 18.5 |  | 49127 | 2024-12-06
N8300 | WA | CAT | 85 |  | LO2122 | Cat 992K | Artic Hitch |  | 35037 | 12000 | 2025-07-09 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N4102-04 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Axle Shaft - POS 4 |  | 57859 | 20000 | 2025-07-09 | 16 |  | 35860 | 2018-10-30
N4102-03 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Axle Shaft - POS 3 |  | 57859 | 20000 | 2025-07-09 | 16 |  | 35860 | 2018-10-30
N8430-RE | WA | CAT | 85 |  | LO2122 | Cat 992K | Trunnion Axle REAR |  | 35037 | 18000 | 2025-07-09 | 11 |  | 13479 | 2022-09-24 | THIESS MANAGED
N7603 | WA | CAT | 85 |  | LO2122 | Cat 992K | Control Valve Main Hydraulic |  | 35037 | 12000 | 2025-07-09 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N3028 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Drive Shaft T/C - Trans |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N4100-R | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Rear Axle RIGHT |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0
N5015 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Oil Cooler AXLE |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N4100-L | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Rear Axle LEFT |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N6063 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Oil Cooler - Steering |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N1100-L | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Turbo Primary LEFT |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N0550 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Air End |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N6060 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Oil Cooler - Brakes |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N7610 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Hyd Cooler Core |  | 24344.16 | 20000 | 2025-07-10 | 13.5 |  | 0 | 2022-06-01
N9050 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Starter Motor |  | 32356 | 6000 | 2025-07-11 | 11 | 25/05/2026 | 22829 | 2026-05-16 | THIESS MANAGED | 10R-9816 | MOTOR GP-ELEC
N1100-R | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Turbo Primary RIGHT |  | 67106.81 | 20000 | 2025-07-12 | 12.5 |  | 43103 | 2018-01-25
N1100-L | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Turbo Primary LEFT |  | 67106.81 | 20000 | 2025-07-12 | 12.5 |  | 43103 | 2018-01-25
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Engine Valve Adj |  | 39200 | 4000 | 2025-07-15 | 14 |  | 30756 | 2020-10-03
N7570-LF | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT FRO |  | 14426 | 10000 | 2025-07-16 | 14 | 09/11/2025 | 0 |  |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N7420-L | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Hyd Cyl Blade Lift LEFT |  | 14154.15 | 12000 | 2025-07-18 | 6.87 |  | 0 | 2022-10-17
N7421-L | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Hyd Cyl Blade Tilt LEFT |  | 14154.15 | 12000 | 2025-07-18 | 6.87 |  | 0 | 2022-10-17
N7420-R | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Hyd Cyl Blade Lift RIGHT |  | 14154.15 | 12000 | 2025-07-18 | 6.87 |  | 0 | 2022-10-17
N7421-R | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Hyd Cyl Blade Tilt RIGHT |  | 14154.15 | 12000 | 2025-07-18 | 6.87 |  | 0 | 2022-10-17
N5002-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Final Drive Midlife RIGHT |  | 23756 | 18000 | 2025-07-21 | 18.5 |  | 0
N5002-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Final Drive Midlife LEFT |  | 23756 | 18000 | 2025-07-21 | 18.5 |  | 0
N8200-01 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Ride Strut POS 1 |  | 64732.59 | 30000 | 2025-07-21 | 12.5 |  | 30841 | 2017-01-15
N0091-02 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Grease Pump POS 02 |  | 23756 | 18000 | 2025-07-21 | 18.5 |  | 0
N7420-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Cyl Blade Lift LEFT |  | 46731 | 12000 | 2025-07-23 | 16 |  | 29781.6 | 2020-08-17 |  | 20R-9809 | BLADE LIFT CYLINDER
N7474-R | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Hyd Cyl Hoist RIGHT |  | 61931 | 27000 | 2025-07-25 | 18.5 |  | 29252 | 2018-08-11
N9501 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | A/C Compressor |  | 46731 | 7500 | 2025-07-29 | 16 |  | 34389 | 2021-09-11 |  | 106-5122 | COMPRESSOR
N9500 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Air Cond'r-Serv |  | 21494.7 | 5000 | 2025-07-30 | 4 |  | 15285 | 2020-05-12 |  | 268-8792 | FAN
N7474-L | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Hyd Cyl Hoist LEFT |  | 66379.67 | 30000 | 2025-08-01 | 12.5 |  | 32631 | 2017-05-06
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Oil Cooler AXLE |  | 60509.94 | 20000 | 2025-08-04 | 12.5 |  | 36799 | 2019-01-20
N7474-R | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Hyd Cyl Hoist RIGHT |  | 67791 | 27000 | 2025-08-06 | 18.5 |  | 35329 | 2019-09-21
N5002-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Final Drive Midlife RIGHT |  | 23402 | 18000 | 2025-08-09 | 18.5 |  | 0
N0091-02 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Grease Pump POS 02 |  | 23402 | 18000 | 2025-08-09 | 18.5 |  | 0
N7004-30 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Rotary Joint to Valve |  | 23402 | 18000 | 2025-08-09 | 18.5 | 25/07/2026 | 0
N5002-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Final Drive Midlife LEFT |  | 23402 | 18000 | 2025-08-09 | 18.5 |  | 0
N9500 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Air Cond'r-Serv |  | 69305 | 5000 | 2025-08-10 | 17 |  | 59355 | 2023-10-01 |  | 385-0244 | MOTOR,BLOWER
N8300 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Artic Hitch |  | 45967 | 16000 | 2025-08-14 | 12 | 20/07/2026 | 26525 | 2018-03-09
N7542-01 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Hyd Cyl Steer POS 1 |  | 45967 | 16000 | 2025-08-14 | 12 | 20/07/2026 | 26525 | 2018-03-09
N6023 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Park Brake Disc/Drum |  | 45967 | 16000 | 2025-08-14 | 12 | 20/07/2026 | 26525 | 2018-03-09
N7542-02 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Hyd Cyl Steer POS 2 |  | 45967 | 16000 | 2025-08-14 | 12 | 20/07/2026 | 26525 | 2018-03-09
N7310-F | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Hyd Motor Rotation FRONT |  | 5943 | 2000 | 2025-08-15 | 13.79 |  | 0 | 2025-04-19 | Parts Ordered in AMT?
N7310-RE | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Hyd Motor Rotation REAR |  | 5943 | 2000 | 2025-08-15 | 13.79 |  | 0 | 2025-04-19 | Parts Ordered in AMT?
N6060 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Oil Cooler - Brakes |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N7610 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Hyd Cooler Core |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N3028 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Drive Shaft T/C - Trans |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N5015 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Oil Cooler AXLE |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N0030 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Truck Body |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N3020 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0
N6063 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Oil Cooler - Steering |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N0550 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Air End |  | 23844.2 | 20000 | 2025-08-16 | 13.5 |  | 0 | 2022-06-01
N0104-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Sprockets RIGHT |  | 34679 | 4000 | 2025-08-17 | 14 |  | 26706 | 2024-08-13
N0104-L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Sprockets LEFT |  | 34679 | 4000 | 2025-08-17 | 14 |  | 26697 | 2024-08-13
N8810 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Pin & Bush BOOM |  | 18651 | 15000 | 2025-08-20 | 13 |  | 0 | 2022-06-01
N0104-R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Sprockets RIGHT |  | 23174 | 4000 | 2025-08-25 | 14 |  | 15305 | 2025-05-28 |  | 433-6739 | 7796592
N7650-RE | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Hyd Accum Blade Cushion REAR |  | 37630 | 16000 | 2025-08-25 | 12 |  | 18321 | 2018-04-19
N7650-F | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Hyd Accum Blade Cushion FRONT |  | 37630 | 16000 | 2025-08-25 | 12 |  | 18321 | 2018-04-19
N0104-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Sprockets LEFT |  | 46895 | 6000 | 2025-08-25 | 13.5 |  | 37165 | 2023-09-23 |  | 433-6739 | 7796590
N0104-L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Sprockets LEFT |  | 23174 | 4000 | 2025-08-25 | 14 |  | 15305 | 2025-05-28 |  | 433-6739 | 7796590
N7474-R | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Hyd Cyl Hoist RIGHT |  | 69479 | 27000 | 2025-08-27 | 18.5 |  | 37404 | 2020-02-27
N7421-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Cyl Blade Tilt RIGHT |  | 46731 | 15000 | 2025-08-30 | 16 |  | 27391 | 2019-12-27 |  | 20R-9634 | Tilt Cylinder
N8200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Ride Strut POS 2 |  | 75619 | 24000 | 2025-09-01 | 19 |  | 46507 | 2019-04-30 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Air Cond'r-Serv |  | 60741 | 5000 | 2025-09-02 | 14 |  | 51989 | 2023-05-03
N1002 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Engine Valve Adj |  | 67600 | 4000 | 2025-09-03 | 17 |  | 59057 | 2024-01-01
N4000 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Bevel Gear |  | 61931 | 18000 | 2025-09-04 | 18.5 | 24/05/2026 | 39014 | 2020-05-27
N0104-R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Sprockets RIGHT |  | 50673 | 4000 | 2025-09-04 | 14 |  | 42942 | 2023-12-01 |  | 433-6739 | 7796592
N0104-L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Sprockets LEFT |  | 50673 | 4000 | 2025-09-04 | 14 |  | 42942 | 2023-12-01 |  | 433-6739 | 7796590
N7310-F | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Hyd Motor Rotation FRONT |  | 5650 | 2000 | 2025-09-05 | 13.79 |  | 0 | 2025-04-01 | Parts Ordered in AMT
N7310-RE | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Hyd Motor Rotation REAR |  | 5650 | 2000 | 2025-09-05 | 13.79 |  | 0 | 2025-04-01 | Parts Ordered in AMT
N1301 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Water Pump |  | 31190.5 | 16000 | 2025-09-06 | 12 |  | 12022 | 2021-05-14
N0104-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Sprockets RIGHT |  | 31311 | 4000 | 2025-09-07 | 14 |  | 23635 | 2024-01-01
N0104-L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Sprockets LEFT |  | 31311 | 4000 | 2025-09-07 | 14 |  | 23635 | 2024-01-01
N3029 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Uni's T/C - Trans |  | 46731 | 7500 | 2025-09-08 | 16 |  | 35037 | 2022-01-31 |  | 173-0888 | UNIVERSAL JOINT GP
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | A/C Compressor |  | 49506 | 10000 | 2025-09-09 | 14.5 |  | 35727 | 2022-06-11
N1490 | WA | CAT | 19 | McPhee Creek | DZ3429 | Cat D10 | Cam Shaft Inspection |  | 4963.4 | 1000 | 2025-09-09 | 7.24 |  | 2074.33 | 2025-09-16
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Alternator |  | 49506 | 10000 | 2025-09-09 | 14.5 |  | 35727 | 2022-06-11 |  | 10R-8755 | ALTERNATOR GP_B
N0503 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Water Cannon |  | 11349 | 7500 | 2025-09-13 | 15 |  | 0
N0104-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Sprockets LEFT |  | 11349 | 7500 | 2025-09-13 | 15 |  | 0 |  |  | 211-9843 | SPROCKET
N0104-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Sprockets RIGHT |  | 11349 | 7500 | 2025-09-13 | 15 |  | 0 |  |  | 211-9843 | SPROCKET
N7474-L | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Hyd Cyl Hoist LEFT |  | 64591.2 | 24000 | 2025-09-16 | 13.75 |  | 37099 | 2019-04-17
N7474-L | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Hyd Cyl Hoist LEFT |  | 64591.2 | 24000 | 2025-09-16 | 13.75 |  | 37099 | 2019-04-17
N7474-R | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 64591.2 | 24000 | 2025-09-16 | 13.75 |  | 37099 | 2019-04-17
N7474-R | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 64591.2 | 24000 | 2025-09-16 | 13.75 |  | 37099 | 2019-04-17
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Air Starter |  | 64653 | 20000 | 2025-09-18 | 14 |  | 41128 | 2019-11-30
N2435 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 14426 | 5000 | 2025-09-18 | 14 | 18/06/2026 | 5896 | 2024-09-30 |  | 553-9494 | ELEMENT
N7542-L | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Cyl Steer LEFT |  | 33290 | 12000 | 2025-09-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N7542-R | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Cyl Steer RIGHT |  | 33290 | 12000 | 2025-09-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N8300 | WA | CAT | 85 |  | LO2121 | Cat 992K | Artic Hitch |  | 33290 | 12000 | 2025-09-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N7232 | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Motor Engine Fan |  | 33290 | 12000 | 2025-09-22 | 11 | 13/06/2026 | 18565 | 2022-04-15 | THIESS MANAGED
N7647-L | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Accum Brake Reseal LEFT |  | 33290 | 12000 | 2025-09-22 | 11 | 13/06/2026 | 18565 | 2025-08-30 | THIESS MANAGED
N7647-R | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Accum Brake Reseal RIGHT |  | 33290 | 12000 | 2025-09-22 | 11 | 13/06/2026 | 18565 | 2025-08-30 | THIESS MANAGED
N3044 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Drv Shaft C/Bearing-Bevel Gr |  | 75270 | 24000 | 2025-09-24 | 6.5 |  | 49669 | 2013-10-02
N7420-L | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Blade Lift LEFT |  | 27110.6 | 8000 | 2025-09-25 | 10 |  | 16660 | 2023-01-11 |  | 389-9512 | BLADE LIFT CYLINDER
N0111-8R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 8 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0121-L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Carrier Roller No 1 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7679 | ROLLER GP-SF
N7421-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Hyd Cyl Blade Tilt LEFT |  | 46895 | 15000 | 2025-09-27 | 13.5 |  | 28609 | 2020-07-03 |  | 20R-9634 | Tilt Cylinder
N0111-3L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 3 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-1R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 1 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0121-R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Carrier Roller No 1 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7679 | ROLLER GP-SF
N0111-2L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 2 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-5L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 5 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0105-RF | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Idler RHT FRONT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 125-3537 | IDLER GP-TRACK
N0101-L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Chain LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 569-2544 | TRACK GP
N0111-7L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 7 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-1L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 1 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0101-R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Chain RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 569-2544 | TRACK GP
N0111-5R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 5 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-2R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 2 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0105-RR | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Idler RHT REAR |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 125-3537 | IDLER GP-TRACK
N0105-LR | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Idler LFT REAR |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 125-3537 | IDLER GP-TRACK
N0111-6R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 6 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0105-LF | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Idler LFT FRONT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 125-3537 | IDLER GP-TRACK
N0111-7R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 7 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-3R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 3 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-6L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 6 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-4L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 4 LEFT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N0111-4R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Track Roller 4 RIGHT |  | 49963 | 8000 | 2025-09-27 | 5.5 |  | 44275 | 2022-06-07 |  | 309-7678 | ROLLER GP-DF
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Ride Strut POS 3 |  | 71898 | 25000 | 2025-09-28 | 18.5 |  | 42418 | 2020-10-22
N9500 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Air Cond'r-Serv |  | 67400 | 5000 | 2025-09-28 | 17 |  | 58283 | 2023-10-01 |  | 385-0244 | MOTOR,BLOWER
N3032 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Uni's Ctr Bearing - Bevel Gear |  | 75270 | 12000 | 2025-09-30 | 6.5 |  | 61707 | 2020-10-19
N1002 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Engine Valve Adj |  | 32356 | 4000 | 2025-09-30 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 449-9059 | SEAL
N9500 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Air Cond'r-Serv |  | 54428 | 5000 | 2025-09-30 | 17 |  | 45352 | 2024-02-20
N1100-R | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Turbo Primary RIGHT |  | 63459.48 | 20000 | 2025-10-01 | 13.5 |  | 40230 | 2021-02-01
N1100-L | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Turbo Primary LEFT |  | 63459.48 | 20000 | 2025-10-01 | 13.5 |  | 40230 | 2021-02-01
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Drive Shaft T/C - Trans |  | 63459.48 | 20000 | 2025-10-01 | 13.5 |  | 40230 | 2021-02-01
N7562-R | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Hyd Cyl Tilt RIGHT |  | 34192 | 12000 | 2025-10-02 | 12 | 16/07/2026 | 19340 | 2022-05-20
N0302 | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Feed Sprocket |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-5L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 5 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-4L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 4 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-8R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 8 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-1L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 1 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-8L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 8 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-3R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 3 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-9R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 9 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-3L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 3 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-1R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 1 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-2R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 2 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-6R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 6 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-7L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 7 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-7R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 7 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-4R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 4 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-9L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 9 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-2L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 2 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N0111-5R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 5 RIGHT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N8810 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Pin & Bush BOOM |  | 18065 | 15000 | 2025-10-04 | 13 |  | 0 | 2022-06-01
N0111-6L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Roller 6 LEFT |  | 9782 | 6000 | 2025-10-04 | 16 |  | 0 | 2025-06-20
N7605 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Steering Hmu |  | 52281 | 20000 | 2025-10-05 | 17 |  | 28294 | 2014-03-22
N8122-02 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Wheel Group POS 2 |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31720 | 2022-11-08 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N8200-04 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Ride Strut POS 4 |  | 54979 | 20000 | 2025-10-07 | 14 |  | 31720 | 2022-11-01 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N8200-01 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Ride Strut POS 1 |  | 54979 | 20000 | 2025-10-07 | 14 |  | 31720 | 2022-11-23
N3320 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Pump Drive Box |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31720 | 2022-12-18 |  | 6V-8260 | SEAL,O-RING
N7542-L | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Hyd Cyl Steer LEFT |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31720 | 2022-12-11 |  | 1U-3182 | CYL, STEERING, 785
N5000-03 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Final Drive POS 3 |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31721 | 2022-11-25
N8200-02 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Ride Strut POS 2 |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31720 | 2022-11-24
N2090 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Drv Coupling |  | 14426 | 5000 | 2025-10-07 | 14 | 18/06/2026 | 6169 | 2024-10-14 |  | 520-7010 | COUPLING GP-
N7542-R | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Hyd Cyl Steer RIGHT |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31720 | 2022-12-14 |  | 1U-3182 | CYL, STEERING, 785
N4102-04 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Axle Shaft - POS 4 |  | 54979 | 20000 | 2025-10-07 | 14 | 01/08/2026 | 31720 | 2022-11-01 |  | 6G-6407 | SHAFT-AXLE (RH)
N1490 | WA | CAT | 85 | McPhee Creek | DZ6660 | Cat D10T2 | Cam Shaft Inspection |  | 5222.3 | 1000 | 2025-10-10 | 7.2 |  | 2569.53 | 2025-08-04
N7155 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Pump Main |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N0123-R | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Carrier Roller No 3 RIGHT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7330-R | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Motor Travel RIGHT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N1000 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Engine |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7432-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Bucket LEFT |  | 23402 | 10000 | 2025-10-11 | 18.5 |  | 9161 | 2023-11-23
N7004-09 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Bucket Cylinder |  | 23402 | 10000 | 2025-10-11 | 18.5 | 25/07/2026 | 9161 | 2023-11-24
N0121-R | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Carrier Roller No 1 RIGHT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7004-19 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Bucket Supply |  | 23402 | 10000 | 2025-10-11 | 18.5 | 25/07/2026 | 9161 | 2023-07-15
N3321 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Pump Drive |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N0122-L | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Carrier Roller No 2 LEFT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N0123-L | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Carrier Roller No 3 LEFT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N0111-9L | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Track Roller 9 LEFT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N0122-R | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Carrier Roller No 2 RIGHT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7091 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Pump Servo/Brg Lube |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7610 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Cooler Core |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7432-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Bucket RIGHT |  | 23402 | 10000 | 2025-10-11 | 18.5 |  | 9161 | 2023-11-23
N0134-L | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Track Adjuster LEFT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N0121-L | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Carrier Roller No 1 LEFT |  | 14715.2 | 14000 | 2025-10-11 | 3.12 |  | 0 | 2022-06-01
N7460-05 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Cyl Feed Swing |  | 21508 | 9000 | 2025-10-12 | 12 | 28/05/2026 | 9774 | 2023-05-21
N7541 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Hyd Cyl Access Ladder |  | 86119 | 20000 | 2025-10-16 | 18.5 |  | 61972 | 2022-07-17 |  | 339-3275 | CYLINDER GP
N9500 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Air Cond'r-Serv |  | 52281 | 5000 | 2025-10-16 | 17 |  | 43474 | 2023-10-01 |  | 385-0244 | MOTOR,BLOWER
N0139-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Frame Mid Life LEFT |  | 46731 | 15000 | 2025-10-17 | 16 |  | 28169 | 2020-03-23
N0134-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Adjuster RIGHT |  | 46731 | 15000 | 2025-10-17 | 16 |  | 28169 | 2020-03-22
N0134-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Adjuster LEFT |  | 46731 | 15000 | 2025-10-17 | 16 |  | 28169 | 2020-03-23
N0139-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Frame Mid Life RIGHT |  | 46731 | 15000 | 2025-10-17 | 16 |  | 28169 | 2020-03-22
N0145 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Pivot Shaft Brgs |  | 46731 | 15000 | 2025-10-17 | 16 |  | 28168 | 2020-03-20 |  | 7T-4135 | BEARING
N0020 | WA | CAT | 01 | Miralga Creek | LO6111 | Cat 930H | Bucket |  | 11460 | 10000 | 2025-10-18 | 6.57 |  | 0 | 2023-01-03
N2002 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Oil Cooler - Transmission |  | 34671 | 14000 | 2025-10-22 | 14 | 25/05/2026 | 17615 | 2022-08-21
N8810 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Pin & Bush BOOM |  | 17835 | 15000 | 2025-10-22 | 13 |  | 0 | 2022-06-01
N0111-3R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 3 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-5L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 5 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-5R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 5 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0105-RR | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Idler RHT REAR |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-21 |  | 125-3537 | IDLER GP-TRACK
N0111-2L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 2 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0101-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Chain LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 569-2544 | TRACK GP
N0103-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Plates RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22
N0111-3L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 3 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-4R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 4 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0101-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Chain RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 569-2544 | TRACK GP
N9500 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Air Cond'r-Serv |  | 41729 | 5000 | 2025-10-23 | 1.2 |  | 36468 | 2018-02-01
N0111-4L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 4 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-1L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 1 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-1R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 1 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0105-RF | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Idler RHT FRONT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 125-3537 | IDLER GP-TRACK
N0105-LR | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Idler LFT REAR |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 125-3537 | IDLER GP-TRACK
N0111-8R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 8 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-7L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 7 LEFT |  | 23756 | 12000 | 2025-10-23 | 18.5 |  | 7750 | 2023-10-17
N0105-LF | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Idler LFT FRONT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 125-3537 | IDLER GP-TRACK
N0111-2R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 2 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-6L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 6 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0103-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Plates LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22
N0111-7R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 7 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-6R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 6 RIGHT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-8L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 8 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N0111-7L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Track Roller 7 LEFT |  | 62609 | 8000 | 2025-10-23 | 12 |  | 52010 | 2021-01-22 |  | 309-7678 | ROLLER GP-DF
N7541 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Hyd Cyl Access Ladder |  | 81805 | 20000 | 2025-10-27 | 18.5 |  | 57863 | 2022-07-17 |  | 339-3275 | CYLINDER GP
N5003-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Final Drive Ext Life POS 3 |  | 81805 | 20000 | 2025-10-27 | 18.5 |  | 57863 | 2022-07-17 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N9500 | WA | CAT | 85 | Iron Bridge | LO2089 | Cat 966M Wheel Loader | Air Cond'r-Serv |  | 6543 | 4000 | 2025-10-28 | 12 |  | 0
N0111-8L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 8 LEFT |  | 46731 | 8000 | 2025-10-28 | 16 |  | 35340 | 2022-08-20 |  | 309-7678 | ROLLER GP-DF
N0111-3R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 3 RIGHT |  | 46731 | 8000 | 2025-10-28 | 16 |  | 35340 | 2022-08-20 |  | 309-7678 | ROLLER GP-DF
N9020 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Alternator |  | 33117 | 6000 | 2025-10-29 | 11 | 01/06/2026 | 24801 | 2023-04-03 |  | 10R-9789 | ALTERNATOR
N0105-RR | WA | CAT | 85 |  | DZ3430 | Cat D10T | Idler RHT REAR |  | 33117 | 6000 | 2025-10-29 | 11 |  | 24801 | 2018-03-28 |  | 125-3537 | IDLER GP-TRACK
N1100-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Turbo Primary LEFT |  | 33117 | 6000 | 2025-10-29 | 11 | 01/06/2026 | 24801 | 2023-04-03 |  | 10R-2075 | TURBO, D10T, REMAN
N1202 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Fuel Transfer Pump |  | 33117 | 6000 | 2025-10-29 | 11 | 01/06/2026 | 24801 | 2023-04-03 |  | 20R-0967 | PUMP GP
N9050 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Starter Motor |  | 33117 | 6000 | 2025-10-29 | 11 | 01/06/2026 | 24801 | 2023-04-03 |  | 10R-9816 | MOTOR GP-ELEC
N0105-LF | WA | CAT | 85 |  | DZ3430 | Cat D10T | Idler LFT FRONT |  | 33117 | 6000 | 2025-10-29 | 11 |  | 24801 | 2018-03-28 |  | 125-3537 | IDLER GP-TRACK
N1300 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Cooling Sys Service |  | 33117 | 6000 | 2025-10-29 | 11 | 01/06/2026 | 24801 | 2023-04-03 |  | 248-5513 | REGULATOR-TEMPERATURE
N1100-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Turbo Primary RIGHT |  | 33117 | 6000 | 2025-10-29 | 11 | 01/06/2026 | 24801 | 2023-04-03 |  | 10R-2075 | TURBO, D10T, REMAN
N0105-LR | WA | CAT | 85 |  | DZ3430 | Cat D10T | Idler LFT REAR |  | 33117 | 6000 | 2025-10-29 | 11 |  | 24801 | 2018-03-28 |  | 125-3537 | IDLER GP-TRACK
N0105-RF | WA | CAT | 85 |  | DZ3430 | Cat D10T | Idler RHT FRONT |  | 33117 | 6000 | 2025-10-29 | 11 |  | 24801 | 2018-03-28 |  | 125-3537 | IDLER GP-TRACK
N4000-RE | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Bevel Gear REAR |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N2000 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Transmission |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7490-R | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Hyd Cyl Lift RIGHT |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N5000-01 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Final Drive POS 1 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7023 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Pump Brake & Pilot |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7070 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Pump Implement |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7041 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Pump Cooling Fan Engine |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7122 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Pump Emerg/Sup Steering |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7490-L | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Hyd Cyl Lift LEFT |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7542-L | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Hyd Cyl Steer LEFT |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N6000-02 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Brake POS 2 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N5000-02 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Final Drive POS 2 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N1312 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Aftercooler Core |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N8300 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Artic Hitch |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N2050 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Torque Convertor |  | 65569 | 24000 | 2025-10-30 | 18.5 | 03/05/2026 | 37677 | 2019-08-25
N5000-04 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Final Drive POS 4 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N4000-F | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Bevel Gear FRONT |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N6000-03 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Brake POS 3 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N5000-03 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Final Drive POS 3 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N2050 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Torque Convertor |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N6000-01 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Brake POS 1 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N2004 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Transmission Pump |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N8432 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Trunnion Axle Bearings REAR |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N6000-04 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Brake POS 4 |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N5015 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Oil Cooler AXLE |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N8430-RE | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Trunnion Axle REAR |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7562 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Hyd Cyl Tilt |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7542-R | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Hyd Cyl Steer RIGHT |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N7120 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Pump Steering |  | 41729 | 20000 | 2025-10-30 | 1.2 |  | 21477 | 2015-03-20
N0121-L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Carrier Roller No 1 LEFT |  | 55435 | 18000 | 2025-10-31 | 18.5 |  | 33568 | 2020-10-14
N9020 | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Alternator |  | 53910 | 7500 | 2025-10-31 | 12 | 01/02/2026 | 43906 | 2020-11-27 |  | 10R-9789 | ALTERNATOR
N9500 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Air Cond'r-Serv |  | 67600 | 5000 | 2025-11-01 | 17 |  | 59057 | 2024-01-01 |  | 385-0244 | MOTOR,BLOWER
N7546-L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cyl Stick LEFT |  | 55435 | 8000 | 2025-11-03 | 18.5 |  | 43626 | 2023-11-10
N1490 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Cam Shaft Inspection |  | 42291 | 1500 | 2025-11-03 | 10 |  | 38734 | 2025-06-02 |  | 224-7506 | SEAL-VALVE COVER
N7546-R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cyl Stick RIGHT |  | 55435 | 8000 | 2025-11-03 | 18.5 |  | 43626 | 2023-11-10
N7595-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Mast Lock LEFT |  | 34291 | 12000 | 2025-11-04 | 13.79 |  | 19459 | 2022-07-01
N7597 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Boom Swing |  | 34291 | 12000 | 2025-11-04 | 13.79 |  | 19459 | 2022-07-01
N3345 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Rotary Table |  | 34291 | 12000 | 2025-11-04 | 13.79 | 01/09/2026 | 19459 | 2022-07-01
N9501 | WA | CAT | 01 |  | RD4246 | Cat 789C | A/C Compressor |  | 54387 | 10000 | 2025-11-04 | 20 |  | 40291 | 2021-02-24 |  | 0R-6756 | COMPRESSOR GP -H
N7460-02 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Feed Dump LEFT |  | 34291 | 12000 | 2025-11-04 | 13.79 |  | 19459 | 2022-07-01
N7460-05 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Feed Swing |  | 34291 | 12000 | 2025-11-04 | 13.79 |  | 19459 | 2022-07-01
N7460-03 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Feed Dump RIGHT |  | 34291 | 12000 | 2025-11-04 | 13.79 |  | 19459 | 2022-07-01
N0200 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | A Frame Bearing |  | 54979 | 20000 | 2025-11-04 | 14 | 01/08/2026 | 32110 | 2019-02-02 |  | 6V-0444 | BEARING, PLAIN, SPHERICAL
N7595-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Mast Lock RIGHT |  | 34291 | 12000 | 2025-11-04 | 13.79 |  | 19459 | 2022-07-01
N8442-08 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Steering Ball Studs POS 8 |  | 47029 | 12000 | 2025-11-05 | 4.12 | 01/06/2026 | 34187 | 2008-12-11 | CC - AMT LEGACY WORK - CANCELLED
N7004-20 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Hose Clam Supply |  | 23756 | 10000 | 2025-11-06 | 18.5 |  | 10000 | 2024-02-04
N7510 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Hyd Cyl Ripper Lift |  | 26541 | 24000 | 2025-11-06 | 12.5 |  | 0 |  |  | 113-5264 | CYL, RIPPER, 16H, 16M
N0104-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Sprockets LEFT |  | 33024 | 6000 | 2025-11-07 | 11 |  | 24801 | 2023-04-03 |  | 433-6739 | 7796590
N7021 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Pump Brake Cooling |  | 69200 | 22000 | 2025-11-07 | 18.5 | 28/05/2026 | 43464 | 2021-03-23
N0104-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Sprockets RIGHT |  | 33024 | 6000 | 2025-11-07 | 11 |  | 24801 | 2023-04-03 |  | 433-6739 | 7796592
N8200-01 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Ride Strut POS 1 |  | 79490 | 30000 | 2025-11-07 | 14 |  | 46661 | 2019-11-10 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N2002 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Oil Cooler - Transmission |  | 54979 | 20000 | 2025-11-07 | 14 | 01/08/2026 | 32151 | 2019-04-04 |  | 0R-3344 | COOLER, OIL, CORE, REMAN
N3026-M | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Uni's Hitch - Bevel Gear MID |  | 28724 | 8000 | 2025-11-08 | 15 |  | 17710 | 2024-03-30
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | Alternator |  | 55805 | 10000 | 2025-11-08 | 14 |  | 42993 | 2020-07-14 |  | 10R-8755 | ALTERNATOR GP -B
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 8398 | 6000 | 2025-11-09 | 12 |  | 0
N7600 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Control Valve |  | 46895 | 30000 | 2025-11-09 | 13.5 |  | 14200.4 | 2017-02-22 |  | 20R-9134 | VALVE GROUP-CONTROL
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4235 | Cat 789C | A Frame Bearing Reshim Initial |  | 63637 | 2000 | 2025-11-10 | 14 |  | 58846.1 | 2022-09-15
N1430 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Air Starter |  | 34192 | 12000 | 2025-11-10 | 12 |  | 19803 | 2022-11-09
N9701 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | LiDAR Detection System |  | 14426 | 5000 | 2025-11-10 | 14 | 15/07/2026 | 6640 | 2025-01-06
N1002 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Engine Valve Adj |  | 54979 | 4000 | 2025-11-11 | 14 |  | 48214 | 2025-06-15
N1310 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Radiator |  | 25353 | 16000 | 2025-11-11 | 12.5 |  | 6877 | 2020-07-27 |  | 494-4833 | 16M RADIATOR
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Operator Seat |  | 60741 | 6000 | 2025-11-12 | 14 |  | 51989 | 2023-05-03 |  | 384-6168 | SEAT GP
N9501 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | A/C Compressor |  | 60487 | 10000 | 2025-11-12 | 7 | 12/05/2026 | 49109 | 2013-12-24
N0556 | WA | CAT | 73 | Iron Bridge | DR2122 | Cat MD6310 - ADS | Air Safety Valve |  | 153 | 0 | 2025-11-12 | 0.1 |  | 0 | 2024-11-12 |  | 549-2163 | VALVE-RELIEF 160psi
N8995 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Operator Seat |  | 35730 | 6000 | 2025-11-12 | 15 | 03/05/2026 | 26781 | 2025-03-28 |  | 358-3854 | SEAT ASSEMBLY - SUSPENSION
N0300-R | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Feed Chain RIGHT |  | 7751 | 2000 | 2025-11-14 | 9.59 | 01/08/2026 | 3885 | 2025-06-11
N9500 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Air Cond'r-Serv |  | 20577.1 | 0 | 2025-11-15 | 4.11 |  | 0 | 2024-11-15
N0111-1L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 1 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-4L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 4 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-3R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 3 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-3L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 3 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Uni's T/C - Trans |  | 53598.82 | 10000 | 2025-11-16 | 13.5 |  | 40994.94 | 2023-07-04
N8200-04 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Ride Strut POS 4 |  | 59517 | 25000 | 2025-11-16 | 18.5 |  | 30940 | 2019-06-08
N0111-2L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 2 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0105-LF | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Idler LFT FRONT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0105-LR | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Idler LFT REAR |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0105-RF | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Idler RHT FRONT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0105-RR | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Idler RHT REAR |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-1R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 1 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-4R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 4 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-2R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 2 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-5R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 5 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-6L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 6 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-6R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 6 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-7L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 7 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-7R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 7 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-8L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 8 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-8R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 8 RIGHT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N0111-5L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Track Roller 5 LEFT |  | 31311 | 8000 | 2025-11-16 | 14 |  | 20607 | 2023-05-06
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Ride Strut POS 3 |  | 59517 | 25000 | 2025-11-16 | 18.5 |  | 30940 | 2019-06-08
N0104-R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Sprockets RIGHT |  | 7287 | 5000 | 2025-11-18 | 12 |  | 0 | 2024-08-27
N0104-L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Sprockets LEFT |  | 7287 | 5000 | 2025-11-18 | 12 |  | 0 | 2024-08-27
N4110-R | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Steering Clutch/Brk RIGHT |  | 52003.6 | 25000 | 2025-11-20 | 12 |  | 24738 | 2018-02-14
N7021 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Pump Brake Cooling |  | 69479 | 22000 | 2025-11-20 | 18.5 | 26/06/2026 | 43980 | 2021-05-24
N7004-07 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Hose Boom Cylinder |  | 55435 | 12000 | 2025-11-20 | 18.5 |  | 39933 | 2022-10-15
N5000-R | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Final Drive RIGHT |  | 52003.6 | 25000 | 2025-11-20 | 12 |  | 24738 | 2018-02-14
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | A Frame Bearing Reshim Initial |  | 52712 | 2000 | 2025-11-23 | 13.75 |  | 48159 | 2025-05-07 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N2090 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Drv Coupling |  | 7751 | 6000 | 2025-11-26 | 9.59 | 01/08/2026 | 0 | 2024-03-28
N3065 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Bearing Unit & Adaptor Shaft |  | 7751 | 6000 | 2025-11-26 | 9.59 | 01/08/2026 | 0 | 2024-03-28
N1430 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Air Starter |  | 79044 | 9000 | 2025-11-27 | 14 |  | 67498 | 2024-02-20 |  | 10R-9657 | MOTOR GP-AIR STG
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Engine Valve Adj |  | 60741 | 4000 | 2025-11-28 | 14 |  | 54204 | 2023-08-22 |  | 272-0760 | SEAL-PIP
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Engine Valve Adj |  | 67187 | 4000 | 2025-11-30 | 14 |  | 60679 | 2023-08-23 |  | 272-0760 | SEAL-PIP
N7474-L | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Hyd Cyl Hoist LEFT |  | 62083 | 27000 | 2025-11-30 | 18.5 |  | 31770 | 2019-06-25
N5020-01 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | Wheel Bearing POS 1 |  | 60498 | 20000 | 2025-12-02 | 15 |  | 46380 | 2020-02-19 |  | 289-2131 | CONE-SPECIAL TAPERED
N0100-R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Group RIGHT |  | 9782 | 7000 | 2025-12-05 | 16 |  | 0 | 2025-06-20
N0100-L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Track Group LEFT |  | 9782 | 7000 | 2025-12-05 | 16 |  | 0 | 2025-06-20
N0121-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Carrier Roller No 1 LEFT |  | 23756 | 12000 | 2025-12-05 | 18.5 |  | 8534 | 2023-11-21
N7600-R | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Control Valve RIGHT |  | 44396 | 24000 | 2025-12-06 | 15 |  | 17798 | 2021-02-28
N7542-L | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Hyd Cyl Steer LEFT |  | 62083 | 12000 | 2025-12-06 | 18.5 | 22/05/2026 | 46875 | 2023-10-27
N0201-01 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | A Frame Bearing Reshim Initial |  | 54781 | 2000 | 2025-12-07 | 15 |  | 50202.1 | 2023-05-22
N7542-R | WA | CAT | 85 |  | GR1549 | Cat 16M | Hyd Cyl Steer RIGHT |  | 23153 | 8000 | 2025-12-10 | 10 |  | 13459 | 2022-09-02 | THIESS MANAGED
N8200-01 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Ride Strut POS 1 |  | 60509.94 | 30000 | 2025-12-10 | 12.5 |  | 28403 | 2016-12-04
N7542-L | WA | CAT | 85 |  | GR1549 | Cat 16M | Hyd Cyl Steer LEFT |  | 23153 | 8000 | 2025-12-10 | 10 |  | 13459 | 2022-09-02 | THIESS MANAGED
N7580 | WA | CAT | 85 |  | GR1549 | Cat 16M | Hyd Cyl Wheel Lean |  | 23153 | 8000 | 2025-12-10 | 10 |  | 13459 | 2022-09-02 | THIESS MANAGED
N8200-02 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Ride Strut POS 2 |  | 69633 | 22000 | 2025-12-10 | 18.5 | 02/07/2026 | 44498 | 2021-05-03
N8122-02 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Wheel Group POS 2 |  | 69633 | 22000 | 2025-12-10 | 18.5 | 02/07/2026 | 44498 | 2021-05-03
N8122-01 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Wheel Group POS 1 |  | 69633 | 22000 | 2025-12-10 | 18.5 | 02/07/2026 | 44498 | 2021-05-03
N4102-03 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Axle Shaft - POS 3 |  | 61931 | 30000 | 2025-12-11 | 18.5 | 24/05/2026 | 28826 | 2018-07-06
N4102-04 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Axle Shaft - POS 4 |  | 61931 | 30000 | 2025-12-11 | 18.5 | 24/05/2026 | 28826 | 2018-07-06
N0099 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 4002 | 2000 | 2025-12-12 | 12 |  | 0 | 2025-05-14
N8995 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Operator Seat |  | 52281 | 6000 | 2025-12-14 | 17 |  | 43474 | 2023-10-01 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4222 | Cat 785C | Uni's Eng - Pump Drive |  | 41444 | 10000 | 2025-12-16 | 14.5 |  | 29075 | 2022-08-17
N1300 | WA | CAT | 85 |  | GR1549 | Cat 16M | Cooling Sys Service |  | 23153 | 7000 | 2025-12-17 | 10 | 06/06/2026 | 14535 | 2023-03-16 | THIESS MANAGED | 248-5513
N1002 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Engine Valve Adj |  | 26519 | 2500 | 2025-12-17 | 12.5 |  | 22000 | 2025-07-28 |  | 229-5711 | SEAL-VALVE COVER
N1100 | WA | CAT | 85 |  | GR1549 | Cat 16M | Turbo Primary |  | 23153 | 7000 | 2025-12-17 | 10 | 06/06/2026 | 14535 | 2023-03-16 | THIESS MANAGED | 20R-3693 | TURBO GP-BASIC
N1400 | WA | CAT | 85 |  | GR1549 | Cat 16M | Belt Tensioner Assembly |  | 23153 | 7000 | 2025-12-17 | 10 | 06/06/2026 | 14535 | 2023-03-16 | THIESS MANAGED | 336-4953
N0201-01 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | A Frame Bearing Reshim Initial |  | 69305 | 2000 | 2025-12-17 | 17 |  | 64555 | 2025-05-27 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1202 | WA | CAT | 85 |  | GR1549 | Cat 16M | Fuel Transfer Pump |  | 23153 | 7000 | 2025-12-17 | 10 | 06/06/2026 | 14535 | 2023-03-16 | THIESS MANAGED | 20R-1524 | FUEL TRANSFER PUMP
N9050 | WA | CAT | 85 |  | GR1549 | Cat 16M | Starter Motor |  | 23153 | 7000 | 2025-12-17 | 10 |  | 14535 | 2023-03-16 | THIESS MANAGED
N1301 | WA | CAT | 85 |  | GR1549 | Cat 16M | Water Pump |  | 23153 | 7000 | 2025-12-17 | 10 | 06/06/2026 | 14535 | 2023-03-16 | THIESS MANAGED | 352-0205
N3038 | WA | CAT | 85 |  | GR1549 | Cat 16M | Uni's Trans - Bevel Gear |  | 23153 | 7000 | 2025-12-17 | 10 | 06/06/2026 | 14535 | 2021-04-04 | THIESS MANAGED
N7004-21 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Clam Cylinder |  | 23402 | 5000 | 2025-12-18 | 18.5 |  | 15426 | 2025-03-18
N0121-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Carrier Roller No 1 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0101-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Chain RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N0033-PR | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Water Tank - PRIMARY |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0
N0111-9R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 9 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 10 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7524 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock |  | 17257 | 15000 | 2025-12-18 | 14 | 22/05/2026 | 0
N0122-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Carrier Roller No 2 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0134-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Adjuster RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0101-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Chain LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N0112-1L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 11 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 11 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0140 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Equalizer Bar |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 526-3821 | BAR AS-EQUAL
N0112-2L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 12 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-2R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 12 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-3R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 13 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7600-LW | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Control Valve LOWER |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 517-7952 | VALVE GP-CONTROL
N0121-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Carrier Roller No 1 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 10 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0033-SC | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Water Tank - SECONDARY |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0
N7600-LU | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Control Valve LEFT UPPER |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 517-7953 | VALVE GP-CONTROL
N0111-3L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 3 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-2R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 2 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7524-FR | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - FRONT |  | 17257 | 15000 | 2025-12-18 | 14 | 22/05/2026 | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N0111-3R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 3 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-4L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 4 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0123-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Carrier Roller No 3 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7524-RE | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - REAR |  | 17257 | 15000 | 2025-12-18 | 14 | 22/05/2026 | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N0111-4R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 4 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-5L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 5 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7527-F | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain FRONT |  | 17257 | 15000 | 2025-12-18 | 14 | 05/06/2026 | 0 |  |  | 515-6795 | CYL GP-127 1
N0111-5R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 5 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Carrier Roller No 2 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-6L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 6 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0105-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Idler LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0111-7L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 7 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-6R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 6 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-1R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 1 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7600-LL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Control Valve LEFT LOWER |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 517-7954 | VALVE GP-CONTROL
N0105-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Idler RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N7598-LO | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing LOWER |  | 17257 | 15000 | 2025-12-18 | 14 | 05/06/2026 | 0 |  |  | 539-1901 | CYL GP-127 1
N0134-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Adjuster LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0111-2L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 2 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-9L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 9 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0123-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Carrier Roller No 3 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 8 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 8 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7570-RR | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT REA |  | 17257 | 15000 | 2025-12-18 | 14 | 05/06/2026 | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N7570-LR | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT REA |  | 17257 | 15000 | 2025-12-18 | 14 | 07/05/2026 | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N0111-7R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 7 RIGHT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-1L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 1 LEFT |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7608 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Control Valve Jack/Mast Raise |  | 17257 | 15000 | 2025-12-18 | 14 |  | 0 |  |  | 514-2137 | VALVE GP-CONTROL
N1400-L | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Belt Tensioner Assy - LEFT |  | 62083 | 12000 | 2025-12-19 | 18.5 | 18/06/2026 | 47115 | 2023-10-27
N1202 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Fuel Transfer Pump |  | 62083 | 12000 | 2025-12-19 | 18.5 | 18/06/2026 | 47115 | 2023-10-27
N8137-L | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Steering Linkage Group LEFT |  | 65569 | 24000 | 2025-12-20 | 18.5 | 03/05/2026 | 38629
N8137-R | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Steering Linkage Group RIGHT |  | 65569 | 24000 | 2025-12-20 | 18.5 | 03/05/2026 | 38629
N7542-R | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Hyd Cyl Steer RIGHT |  | 65569 | 12000 | 2025-12-20 | 18.5 | 03/05/2026 | 50629 | 2023-10-27
N3021 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Uni's Eng - Pump Drive |  | 65569 | 12000 | 2025-12-20 | 18.5 | 03/05/2026 | 50629 | 2023-10-27
N8200-02 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Ride Strut POS 2 |  | 45967 | 16000 | 2025-12-20 | 12 | 20/07/2026 | 28064 | 2018-05-26
N8140 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Steering Y Piece |  | 65569 | 24000 | 2025-12-20 | 18.5 | 03/05/2026 | 38629
N1490 | WA | CAT | 85 | McPhee Creek | LO6670 | Cat 854K | Cam Shaft Inspection |  | 2912.8 | 1500 | 2025-12-21 | 8.97 |  | 0 | 2025-01-08
N4000 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Bevel Gear |  | 70598 | 18000 | 2025-12-21 | 18.5 | 14/05/2026 | 49669 | 2021-12-01
N6030-F | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Brake Slack Adj FRONT |  | 69479 | 16000 | 2025-12-22 | 18.5 | 26/06/2026 | 50567 | 2022-09-29
N3021 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Uni's Eng - Pump Drive |  | 67600 | 10000 | 2025-12-22 | 17 |  | 54929 | 2021-09-14 |  | 230-4110 | JOINT GP, UNI
N6063 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Oil Cooler - Steering |  | 56902.96 | 20000 | 2025-12-23 | 13.5 |  | 34800 | 2020-12-14
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Hyd Cooler Core |  | 56902.96 | 20000 | 2025-12-23 | 13.5 |  | 34800 | 2020-12-14
N9501 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | A/C Compressor |  | 67600 | 10000 | 2025-12-23 | 17 |  | 54953 | 2021-10-28
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | A Frame Bearing Reshim Initial |  | 50845.5 | 2000 | 2025-12-24 | 13.75 |  | 46718 | 2025-05-16 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N8995 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Operator Seat |  | 31311 | 6000 | 2025-12-26 | 14 | 20/06/2026 | 23165 | 2023-12-09 |  | 443-8104 | CAT OPERATOR SEAT
N7600-L | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Control Valve LEFT |  | 44396 | 24000 | 2025-12-26 | 15 |  | 18095 | 2021-03-20
N6200-RR | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Press Converter RIGHT REAR |  | 52281 | 10000 | 2025-12-27 | 17 |  | 39691 | 2019-04-01 |  | 8X-7220 | CHAMBER, BRAKE
N0104-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Sprockets LEFT |  | 31190.5 | 5000 | 2025-12-27 | 12 |  | 24363.85 | 2024-09-16
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Steering Ball Studs POS 8 |  | 67791 | 12000 | 2025-12-27 | 18.5 |  | 52985 | 2023-10-31
N0104-R | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Sprockets RIGHT |  | 31190.5 | 5000 | 2025-12-27 | 12 |  | 24363.85 | 2024-09-16
N3021 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Uni's Eng - Pump Drive |  | 52281 | 10000 | 2025-12-27 | 17 |  | 39691 | 2019-04-01 |  | 230-4110 | JOINT GP, UNI
N6200-F | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Press Converter FRONT |  | 52281 | 10000 | 2025-12-27 | 17 |  | 39691 | 2019-04-01 |  | 8X-7220 | CHAMBER, BRAKE
N1490 | WA | CAT | 85 | McPhee Creek | RD6651 | Cat 777 | Cam Shaft Inspection |  | 2803.3 | 1500 | 2025-12-27 | 8.55 |  | 0 | 2024-05-21
N3021 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Uni's Eng - Pump Drive |  | 67400 | 10000 | 2025-12-27 | 17 |  | 54820 | 2021-12-07 |  | 230-4110 | JOINT GP, UNI
N6200-LR | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Press Converter LEFT REAR |  | 52281 | 10000 | 2025-12-27 | 17 |  | 39691 | 2019-04-01 |  | 8X-7220 | CHAMBER, BRAKE
N1002 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Engine Valve Adj |  | 61931 | 4000 | 2025-12-27 | 18.5 |  | 55118 | 2025-05-27
N9020 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Alternator |  | 52281 | 10000 | 2025-12-27 | 17 |  | 39691 | 2019-04-01 |  | 10R-8755 | ALTERNATOR GP_B
N0111-6L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Track Roller 6 LEFT |  | 55435 | 22000 | 2025-12-28 | 18.5 |  | 30643 | 2020-03-16
N8995 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Operator Seat |  | 67600 | 6000 | 2025-12-29 | 17 |  | 59057 | 2024-01-01 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Wheel Group POS 1 |  | 75619 | 24000 | 2025-12-30 | 19 |  | 48790 | 2019-11-21 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N9500 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Air Cond'r-Serv |  | 45967 | 4000 | 2025-12-30 | 12 | 20/07/2026 | 40174 | 2021-03-29
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Brake POS 1 |  | 75619 | 24000 | 2025-12-30 | 19 |  | 48790 | 2019-11-21 |  | 10R-5394 | BRAKE, FRT, 793
N6030-F | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Brake Slack Adj FRONT |  | 69200 | 16000 | 2025-12-30 | 18.5 | 28/05/2026 | 50446 | 2022-08-28
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Wheel Bearing POS 1 |  | 75619 | 24000 | 2025-12-30 | 19 |  | 48790 | 2019-11-21 |  | 446-0367 | KIT
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | A Frame Bearing Reshim Initial |  | 75619 | 2000 | 2026-01-02 | 19 |  | 70837 | 2025-03-29 |  | 8X-2934 | SHIM PACK
N8443-UL | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Rear Axle Control Arm U/LEFT |  | 69633 | 20000 | 2026-01-03 | 18.5 | 02/07/2026 | 46958 | 2021-10-22
N8995 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Operator Seat |  | 26519 | 6000 | 2026-01-03 | 12.5 | 21/05/2026 | 18701 | 2024-10-31
N5003-03 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Final Drive Ext Life POS 3 |  | 69633 | 25000 | 2026-01-04 | 18.5 | 02/07/2026 | 41969 | 2020-10-22
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 41713 | 24000 | 2026-01-04 | 15 |  | 15550
N9500 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Air Cond'r-Serv |  | 53351 | 5000 | 2026-01-05 | 12 |  | 46633 | 2023-12-20
N3016 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Drv Shaft Fan Pump-Trans Pump |  | 49954 | 15000 | 2026-01-06 | 5.5 | 09/04/2026 | 34171 | 2017-04-01 |  | 211-9087 | COUPLING AS
N1202 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Fuel Transfer Pump |  | 26541 | 8000 | 2026-01-07 | 12.5 | 21/05/2026 | 16779 | 2023-03-10 |  | 20R-1524 | FUEL TRANSFER PUMP
N1300 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Cooling Sys Service |  | 26541 | 8000 | 2026-01-07 | 12.5 | 21/05/2026 | 16779 | 2023-03-10 |  | 248-5513
N1400 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Belt Tensioner Assembly |  | 26541 | 8000 | 2026-01-07 | 12.5 | 21/05/2026 | 16779 | 2023-03-10 |  | 336-4953
N1301 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Water Pump |  | 26541 | 8000 | 2026-01-07 | 12.5 | 21/05/2026 | 16779 | 2023-03-10 |  | 352-0205
N9050 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Starter Motor |  | 26541 | 8000 | 2026-01-07 | 12.5 | 21/05/2026 | 16779 | 2023-03-10
N1100 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Turbo Primary |  | 26541 | 8000 | 2026-01-07 | 12.5 | 21/05/2026 | 16779 | 2023-03-10 |  | 20R-3693 | TURBO GP-BASIC
N9500 | WA | CAT | 85 | McPhee Creek | LO6670 | Cat 854K | Air Cond'r-Serv |  | 2912.8 | 0 | 2026-01-08 | 8.97 |  | 0 | 2025-01-08
N8432 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Trunnion Axle Bearings REAR |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N7542-R | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Hyd Cyl Steer RIGHT |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N8127-R | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Axle Assembly REAR |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N8127-F | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Axle Assembly FRONT |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N9500 | WA | CAT | 85 | McPhee Creek | RD6650 | Cat 777 | Air Cond'r-Serv |  | 2531.3 | 0 | 2026-01-08 | 8.55 |  | 0 | 2025-01-08
N9500 | WA | CAT | 85 | McPhee Creek | RD6623 | Cat 777 | Air Cond'r-Serv |  | 1958.65 | 0 | 2026-01-08 | 8 |  | 0 | 2025-01-08
N9500 | WA | CAT | 85 | McPhee Creek | RD6624 | Cat 777 | Air Cond'r-Serv |  | 1889.7 | 0 | 2026-01-08 | 8 |  | 0 | 2025-01-08
N7122 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Pump Emerg/Sup Steering |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N9500 | WA | CAT | 85 | McPhee Creek | EX6675 | Cat 330RB | Air Cond'r-Serv |  | 2293 | 0 | 2026-01-08 | 3.29 |  | 0 | 2025-01-08
N9500 | WA | CAT | 85 | McPhee Creek | RD6621 | Cat 777 | Air Cond'r-Serv |  | 1431.1 | 0 | 2026-01-08 | 3.95 |  | 0 | 2025-01-08
N9500 | WA | CAT | 85 | McPhee Creek | GR6655 | Cat 18M | Air Cond'r-Serv |  | 4648.5 | 0 | 2026-01-08 | 7.02 |  | 0 | 2025-01-08
N9500 | WA | CAT | 85 | McPhee Creek | RD6622 | Cat 777 | Air Cond'r-Serv |  | 1608.3 | 0 | 2026-01-08 | 8 |  | 0 | 2025-01-08
N0111-6L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 6 LEFT |  | 50673 | 8000 | 2026-01-08 | 14 |  | 40715 | 2021-08-13 |  | 309-7678 | ROLLER GP-DF
N0111-8R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 8 RIGHT |  | 50673 | 8000 | 2026-01-08 | 14 |  | 40715 | 2021-08-13 |  | 309-7678 | ROLLER GP-DF
N7421 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Hyd Cyl Blade Tilt |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N2004 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Transmission Pump |  | 54979 | 20000 | 2026-01-08 | 14 | 01/08/2026 | 33026 | 2019-08-29 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N0111-5L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 5 LEFT |  | 50673 | 8000 | 2026-01-08 | 14 |  | 40715 | 2021-08-13 |  | 309-7678 | ROLLER GP-DF
N7120 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Pump Steering |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N7420-R | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Hyd Cyl Blade Lift RIGHT |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N2000 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Transmission |  | 54979 | 20000 | 2026-01-08 | 14 | 01/08/2026 | 33026 | 2019-08-29 |  | 0R-4007 | TRANSMISSION, 789B 785C
N8300 | WA | CAT | 01 | Miralga Creek | LO6536 | Cat IT38G | Artic Hitch |  | 20577.1 | 20000 | 2026-01-08 | 4.11 |  | 0 | 2022-06-01
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Brake POS 2 |  | 75619 | 24000 | 2026-01-09 | 19 |  | 48970 | 2019-11-21 |  | 10R-5394 | BRAKE, FRT, 793
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Wheel Group POS 2 |  | 75619 | 24000 | 2026-01-09 | 19 |  | 48970 | 2019-11-21 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4376 | Cat 785C | Air Starter |  | 66519 | 10000 | 2026-01-09 | 13 |  | 54708 | 2019-11-12
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Wheel Bearing POS 2 |  | 75619 | 24000 | 2026-01-09 | 19 |  | 48970 | 2019-11-21 |  | 446-0367 | KIT
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 7661 | 6000 | 2026-01-10 | 12 |  | 0
N7234 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 7661 | 6000 | 2026-01-10 | 12 |  | 0
N7151 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 7661 | 6000 | 2026-01-10 | 12 |  | 0
N8200-02 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Ride Strut POS 2 |  | 47332.5 | 30000 | 2026-01-11 | 7.13 |  | 16355 | 2015-08-22
N2450 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Drv Cpling Fan Pump-Trans Pump |  | 62609 | 7500 | 2026-01-12 | 12 |  | 53483 | 2022-01-07 |  | 211-9087 | COUPLING AS
N3029 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Uni's T/C - Trans |  | 65569 | 8000 | 2026-01-13 | 18.5 | 03/05/2026 | 55077 | 2024-11-10
N0201-01 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | A Frame Bearing Reshim Initial |  | 60138 | 2000 | 2026-01-16 | 15 |  | 56154.1 | 2022-08-18
N1430 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Air Starter |  | 54428 | 10000 | 2026-01-16 | 17 |  | 42188 | 2023-05-30
N0201-01 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | A Frame Bearing Reshim Initial |  | 52281 | 2000 | 2026-01-16 | 17 |  | 48043 | 2025-05-31 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1490 | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Cam Shaft Inspection |  | 5903.7 | 1000 | 2026-01-17 | 7.2 | 12/08/2026 | 3957 | 2025-12-19
N8810 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Pin & Bush BOOM |  | 16244 | 15000 | 2026-01-18 | 9.59 |  | 0 | 2022-06-01
N7592-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Hyd Cyl Mast Raise RIGHT |  | 21277 | 15000 | 2026-01-18 | 14 | 11/06/2026 | 4460 |  |  | 450-7146X | MD6310 MAST RAISE CYL
N8441 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Rear Axle Dog Bone |  | 79044 | 15000 | 2026-01-19 | 14 |  | 62237 | 2023-01-16 |  | 211-4924 | LATERAL LINK, 793
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Steering Y Piece |  | 75619 | 20000 | 2026-01-19 | 19 |  | 53161 | 2020-10-10 |  | 207-7321 | CENTRE ARM, STEERING, 793
N9500 | WA | CAT | 85 | McPhee Creek | RD6610 | Cat 789D | Air Cond'r-Serv |  | 3606.6 | 0 | 2026-01-19 | 11.19 |  | 0 | 2025-01-19
N1202 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Fuel Transfer Pump |  | 59517 | 12000 | 2026-01-19 | 18.5 | 23/06/2026 | 45129 | 2023-10-27
N9500-MA | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Air Cond'r-Serv - MAJOR |  | 71898 | 24000 | 2026-01-19 | 18.5 | 04/06/2026 | 45510 | 2021-06-17
N1310 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Radiator |  | 71898 | 24000 | 2026-01-19 | 18.5 | 04/06/2026 | 45510 | 2021-06-11
N9500 | WA | CAT | 85 | McPhee Creek | RD6601 | Cat 789D | Air Cond'r-Serv |  | 3453.85 | 0 | 2026-01-19 | 11.19 |  | 0 | 2025-01-19
N5020-RF | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Wheel Bearing RIGHT FRONT |  | 56902.96 | 15000 | 2026-01-19 | 13.5 | 01/06/2026 | 40156 | 2022-08-24
N7542-L | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Hyd Cyl Steer LEFT |  | 75619 | 20000 | 2026-01-19 | 19 |  | 53161 | 2020-10-10 |  | 20R-5304 | STEER CYL
N1000 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Engine |  | 71898 | 24000 | 2026-01-19 | 18.5 | 15/07/2026 | 45510 | 2021-06-17
N9500 | WA | CAT | 85 | McPhee Creek | RD6602 | Cat 789D | Air Cond'r-Serv |  | 4287.2 | 0 | 2026-01-19 | 11.19 |  | 0 | 2025-01-19
N0520 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Pre Lube Pump |  | 71898 | 24000 | 2026-01-19 | 18.5 | 04/06/2026 | 45510 | 2021-06-17
N9500 | WA | CAT | 85 | McPhee Creek | LO6631 | Cat 972 | Air Cond'r-Serv |  | 2188.6 | 0 | 2026-01-19 | 8.21 |  | 0 | 2025-01-19
N3020 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Drive Shaft Eng - Pump Drive |  | 71898 | 24000 | 2026-01-19 | 18.5 | 04/06/2026 | 45510 | 2021-06-17
N9500 | WA | CAT | 85 | McPhee Creek | RD6612 | Cat 789D | Air Cond'r-Serv |  | 3903.15 | 0 | 2026-01-20 | 11.19 |  | 0 | 2025-01-20
N9500 | WA | CAT | 85 | McPhee Creek | RD6611 | Cat 789D | Air Cond'r-Serv |  | 3329.2 | 0 | 2026-01-20 | 11.19 |  | 0 | 2025-01-20
N0300-R | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Feed Chain RIGHT |  | 16244 | 2000 | 2026-01-20 | 9.59 | 01/07/2026 | 13017.63 | 2025-07-27
N1490 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Cam Shaft Inspection |  | 47986 | 2000 | 2026-01-21 | 12 |  | 44465 | 2025-08-09 |  | 449-9059 | SEAL
N9500 | WA | CAT | 85 | McPhee Creek | RD6608 | Cat 789D | Air Cond'r-Serv |  | 3150.15 | 0 | 2026-01-21 | 11.19 |  | 0 | 2025-01-21
N9500 | WA | CAT | 85 | McPhee Creek | RD6609 | Cat 789D | Air Cond'r-Serv |  | 3871 | 0 | 2026-01-21 | 11.19 |  | 0 | 2025-01-21
N8122-01 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Wheel Group POS 1 |  | 69200 | 22000 | 2026-01-21 | 18.5 | 28/05/2026 | 44844 | 2021-07-04
N0104-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Sprockets RIGHT |  | 5903.7 | 5000 | 2026-01-22 | 7.2 |  | 0 | 2025-01-08
N1100 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Turbo Primary |  | 28724 | 8000 | 2026-01-22 | 15 |  | 18828 | 2024-06-09
N0104-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Sprockets LEFT |  | 5903.7 | 5000 | 2026-01-22 | 7.2 |  | 0 | 2025-01-08
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Press Converter LEFT REAR |  | 58874 | 10000 | 2026-01-22 | 13.75 | 16/03/2026 | 47147 | 2023-12-02
N7602 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Relief Valve |  | 16244 | 0 | 2026-01-22 | 9.59 |  | 0 | 2024-01-23
N0100-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Group LEFT |  | 5903.7 | 2000 | 2026-01-24 | 7.2 |  | 3008 | 2025-10-05
N0100-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Group RIGHT |  | 5903.7 | 2000 | 2026-01-24 | 7.2 |  | 3008 | 2025-10-05
N7562-L | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Cyl Tilt LEFT |  | 44396 | 12000 | 2026-01-24 | 15 |  | 30536 | 2023-11-19
N9500 | WA | CAT | 01 | Miralga Creek | LO6111 | Cat 930H | Air Cond'r-Serv |  | 11460 | 0 | 2026-01-25 | 6.57 |  | 0 | 2025-01-25
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | A/C Compressor |  | 60741 | 10000 | 2026-01-26 | 14 |  | 49037 | 2021-11-26 |  | 0R-6756 | COMPRESSOR GP -H
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Brake Slack Adj REAR |  | 69200 | 16000 | 2026-01-26 | 18.5 | 28/05/2026 | 50947 | 2022-10-02
N0145-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Pivot Shaft Brgs RIGHT |  | 34291 | 4000 | 2026-01-27 | 13.79 | 20/05/2026 | 28620 | 2025-03-03
N0201-01 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | A Frame Bearing Reshim Initial |  | 64591.2 | 2000 | 2026-01-27 | 13.75 |  | 60924 | 2025-05-24 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0201-01 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | A Frame Bearing Reshim Initial |  | 64591.2 | 2000 | 2026-01-27 | 13.75 |  | 60924 | 2025-05-24 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1490 | WA | CAT | 85 | McPhee Creek | RD6650 | Cat 777 | Cam Shaft Inspection |  | 2531.3 | 1500 | 2026-01-27 | 8.55 |  | 0 | 2025-01-08
N0145-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Pivot Shaft Brgs LEFT |  | 34291 | 4000 | 2026-01-27 | 13.79 | 20/05/2026 | 28620 | 2025-03-03
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Brake Slack Adj FRONT |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 590-2531 | SLACK ADJUSTER
N7657-F | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Hyd Accum Steering FRONT |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Steering Linkage Group RIGHT |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 2A-6945 | LINK, STEERING, 789
N1310 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Radiator |  | 60138 | 20000 | 2026-01-28 | 15 |  | 38342 | 2018-07-05 |  | 145-1226 | PEX SX 789C RADIATOR
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Brake Slack Adj REAR |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 590-2533 | SLACK ADJUSTER
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Steering Linkage Group LEFT |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 2A-6945 | LINK, STEERING, 789
N6061 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Oil Cooler Front Brakes |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 10R-0816 | REMAN OIL COOLER
N0201-01 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | A Frame Bearing Reshim Initial |  | 78363 | 2000 | 2026-01-28 | 14 |  | 74682 | 2025-08-26 |  | 8X-2934 | SHIM PACK
N7542-L | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Hyd Cyl Steer LEFT |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 30R-1082 | STEER CYL 789C
N7657-RE | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Hyd Accum Steering REAR |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Hyd Cyl Steer RIGHT |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 30R-1082 | STEER CYL 789C
N0520 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Pre Lube Pump |  | 60741 | 20000 | 2026-01-28 | 14 |  | 39067 | 2020-02-20 |  | 20R-3396 | PRE-LUBE PUMP
N7542-L | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Hyd Cyl Steer LEFT |  | 67791 | 12000 | 2026-01-29 | 18.5 | 04/06/2026 | 53598 | 2024-02-12
N7420-R | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Hyd Cyl Blade Lift RIGHT |  | 53910 | 12000 | 2026-01-29 | 12 | 01/02/2026 | 40478 | 2019-08-09 |  | 20R-9809 | BLADE LIFT CYLINDER
N6030-F | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Brake Slack Adj FRONT |  | 62083 | 16000 | 2026-01-29 | 18.5 | 13/08/2026 | 43882 | 2021-11-14
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Steering Hmu |  | 60741 | 20000 | 2026-01-29 | 14 |  | 39072 | 2020-02-20 |  | 9T-1318 | PUMP
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Ride Strut POS 1 |  | 60741 | 20000 | 2026-01-29 | 14 |  | 39072 | 2020-02-20 |  | 347-7423 | SUSP CYL
N0102-R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 49963 | 4000 | 2026-01-29 | 5.5 |  | 45309 | 2023-02-18
N8200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Ride Strut POS 2 |  | 60741 | 20000 | 2026-01-29 | 14 |  | 39072 | 2020-02-20 |  | 347-7423 | SUSP CYL
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Pump Drive Box |  | 60741 | 20000 | 2026-01-29 | 14 |  | 39072 | 2020-02-20 |  | 11R-1517 | DRIVE GP-PUMP
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Radiator |  | 60741 | 20000 | 2026-01-29 | 14 |  | 39072 | 2020-02-20 |  | 145-1226 | PEX SX 789C RADIATOR
N0102-L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 49963 | 4000 | 2026-01-29 | 5.5 |  | 45309 | 2023-02-18
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Brake Slack Adj REAR |  | 62083 | 16000 | 2026-01-29 | 18.5 | 13/08/2026 | 43882 | 2021-11-14
N8995 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Operator Seat |  | 62083 | 6000 | 2026-01-30 | 18.5 | 22/05/2026 | 53901 | 2025-03-28
N7001 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hydraulic Tune |  | 23746 | 6000 | 2026-01-31 | 18.5 |  | 15589 | 2025-01-31
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Press Converter LEFT REAR |  | 60741 | 10000 | 2026-01-31 | 14 |  | 49108 | 2022-07-15 |  | 8W-3405 | CHAMBER, BRAKE
N6030-F | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Brake Slack Adj FRONT |  | 69633 | 16000 | 2026-01-31 | 18.5 | 02/07/2026 | 51466 | 2022-09-21
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Press Converter RIGHT REAR |  | 60741 | 10000 | 2026-01-31 | 14 |  | 49108 | 2022-07-15 |  | 8W-3405 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Press Converter FRONT |  | 60741 | 10000 | 2026-01-31 | 14 |  | 49108 | 2022-07-15 |  | 8W-3405 | CHAMBER, BRAKE
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Alternator |  | 60741 | 10000 | 2026-01-31 | 14 |  | 49108 | 2022-07-15 |  | 10R-8755 | ALTERNATOR GP -B
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Brake Slack Adj REAR |  | 69633 | 16000 | 2026-01-31 | 18.5 | 02/07/2026 | 51466 | 2022-09-21
N1310 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Radiator |  | 78345 | 18000 | 2026-02-01 | 14 | 07/05/2026 | 58728 | 2022-07-27 |  | 334-6025 | RADIATOR COOLING GP
N1000 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Engine |  | 78345 | 18000 | 2026-02-01 | 14 | 07/05/2026 | 58728 | 2022-07-27 |  | 488-8196 | 793D PEX ENGINE
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 41713 | 20000 | 2026-02-01 | 15 |  | 37262 | 2022-05-12
N7232 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Motor Engine Fan |  | 78345 | 18000 | 2026-02-01 | 14 | 07/05/2026 | 58728 | 2022-07-27 |  | 10R-5466 | MOTOR GP - HYD FAN
N1002 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Engine Valve Adj |  | 37630 | 2500 | 2026-02-02 | 12 |  | 33750 | 2021-07-22 |  | 229-5711 | SEAL-VALVE COVER
N0302 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Feed Sprocket |  | 18651 | 10000 | 2026-02-02 | 13 |  | 7154.04 | 2023-05-26
N9500 | WA | CAT | 85 |  | GR1549 | Cat 16M | Air Cond'r-Serv |  | 23153 | 3500 | 2026-02-03 | 10 |  | 18517 | 2025-01-01 | THIESS MANAGED
N7088 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Pump Park Brk Rel |  | 41713 | 40000 | 2026-02-03 | 15 |  | 0 |  |  | 5T-1060 | PUMP ASSY
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Brake Slack Adj REAR |  | 67791 | 16000 | 2026-02-04 | 18.5 | 04/06/2026 | 49698 | 2022-07-25
N4000 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Bevel Gear |  | 49898.9 | 14000 | 2026-02-04 | 10 | 17/11/2025 | 34766 | 2021-10-22 |  | 379-9145SX | AXLE ASSEMBLY, REAR, 16M
N3037 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Drive Shaft Trans - Bevel Gear |  | 49898.9 | 14000 | 2026-02-04 | 10 | 17/11/2025 | 34766 | 2021-10-22 |  | 419-1963
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Oil Cooler AXLE |  | 62901.67 | 20000 | 2026-02-06 | 13.5 |  | 41405 | 2021-05-30
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Drive Shaft T/C - Trans |  | 62901.67 | 20000 | 2026-02-06 | 13.5 |  | 41405 | 2021-05-30
N6063 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Oil Cooler - Steering |  | 62901.67 | 20000 | 2026-02-06 | 13.5 |  | 41405 | 2021-05-30
N7610 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Hyd Cooler Core |  | 62901.67 | 20000 | 2026-02-06 | 13.5 |  | 41405 | 2021-05-30
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Oil Cooler - Brakes |  | 62901.67 | 20000 | 2026-02-06 | 13.5 |  | 41405 | 2021-05-30
N7613 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Hyd Cooler Steering/Eng Fan |  | 79044 | 20000 | 2026-02-06 | 14 |  | 57492 | 2022-03-03 |  | 30R-0034 | CORE AS OIL
N2000 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Transmission |  | 79044 | 20000 | 2026-02-06 | 14 |  | 57492 | 2022-03-03 |  | 10R-4469 | TRANSMISSION, 793D
N1002 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Engine Valve Adj |  | 82501 | 4000 | 2026-02-06 | 18.5 |  | 76449 | 2025-05-09 |  | 272-0760 | SEAL-VALVE COVER
N0201-01 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | A Frame Bearing Reshim Initial |  | 79726 | 2000 | 2026-02-07 | 18.5 |  | 75688 | 2025-09-01 |  | 8X-2934 | SHIM PACK
G00050H | WA | CAT | 85 | McPhee Creek | RD6607 | Cat 789D | Generic Service 50 Hours |  | 1339.95 | 50 | 2026-02-07 | 11.19 |  | 62 | 2026-04-15
N3321 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Pump Drive |  | 53598.82 | 20000 | 2026-02-08 | 13.5 |  | 32132 | 2021-07-08
N1002 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Engine Valve Adj |  | 10578.3 | 2500 | 2026-02-08 | 7.02 |  | 7313.6 | 2025-03-01
N7510 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Cyl Ripper Lift |  | 25353 | 24000 | 2026-02-09 | 12.5 |  | 0 |  |  | 113-5264 | CYL, RIPPER, 16H, 16M
N7151 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 22440 | 6000 | 2026-02-09 | 12 |  | 15144 | 2024-06-07
N0105-RF | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Idler RHT FRONT |  | 7287 | 6000 | 2026-02-10 | 12 |  | 0 | 2024-08-27
N0105-RR | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Idler RHT REAR |  | 7287 | 6000 | 2026-02-10 | 12 |  | 0 | 2024-08-27
N0105-LF | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Idler LFT FRONT |  | 7287 | 6000 | 2026-02-10 | 12 |  | 0 | 2024-08-27
N7120 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Pump Steering |  | 53351 | 20000 | 2026-02-10 | 12 | 04/11/2025 | 32071 | 2018-12-03
N0105-LR | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Idler LFT REAR |  | 7287 | 6000 | 2026-02-10 | 12 |  | 0 | 2024-08-27
N9500 | WA | CAT | 85 | McPhee Creek | RD6607 | Cat 789D | Air Cond'r-Serv |  | 1690.45 | 0 | 2026-02-10 | 11.19 |  | 0 | 2025-02-10
N1310 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Radiator |  | 24344.16 | 20000 | 2026-02-11 | 13.5 | 16/06/2026 | 0 | 2022-06-01
N3029 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Uni's T/C - Trans |  | 70598 | 8000 | 2026-02-12 | 18.5 | 14/05/2026 | 60664 | 2024-10-22
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | A Frame Bearing Reshim Initial |  | 58874 | 2000 | 2026-02-13 | 13.75 |  | 55443 | 2025-07-16
N7613 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Hyd Cooler Steering/Eng Fan |  | 79471 | 20000 | 2026-02-13 | 14 | 14/05/2026 | 58016 | 2022-02-28 |  | 30R-0034 | CORE AS OIL
N8200-04 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Ride Strut POS 4 |  | 69479 | 25000 | 2026-02-15 | 18.5 |  | 42588 | 2021-01-29
N0102-R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 45807 | 4000 | 2026-02-15 | 14 |  | 40373 | 2023-12-17
N0102-L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 45807 | 4000 | 2026-02-15 | 14 |  | 40373 | 2023-12-17
N9701 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | LiDAR Detection System |  | 11349 | 5000 | 2026-02-15 | 15 | 02/06/2026 | 4823 | 2025-02-26
N1310 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Radiator |  | 70598 | 24000 | 2026-02-16 | 18.5 | 14/05/2026 | 44735 | 2021-01-12
N1000 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Engine |  | 70598 | 24000 | 2026-02-16 | 18.5 | 14/05/2026 | 44735 | 2021-01-12
N0520 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Pre Lube Pump |  | 70598 | 24000 | 2026-02-16 | 18.5 | 14/05/2026 | 44735 | 2021-01-12
N9500 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Air Cond'r-Serv |  | 65569 | 4000 | 2026-02-16 | 18.5 | 03/05/2026 | 59706 | 2025-07-26
N3020 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Drive Shaft Eng - Pump Drive |  | 70598 | 24000 | 2026-02-16 | 18.5 | 14/05/2026 | 44735 | 2021-01-12
N9500-MA | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Air Cond'r-Serv - MAJOR |  | 70598 | 24000 | 2026-02-16 | 18.5 | 14/05/2026 | 44735 | 2021-01-12
N2050 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Torque Convertor |  | 70598 | 24000 | 2026-02-16 | 18.5 | 14/05/2026 | 44735 | 2021-01-12
N7600 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Control Valve |  | 31190.5 | 30000 | 2026-02-18 | 12 |  | 0 | 2018-09-12
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Air Cond'r-Serv |  | 58874 | 5000 | 2026-02-19 | 13.75 | 16/03/2026 | 52533 | 2024-12-17 |  | 385-0244 | MOTOR,BLOWER
N7562-R | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Hyd Cyl Tilt RIGHT |  | 21494.7 | 20000 | 2026-02-21 | 4 |  | 1111 | 2015-08-07
N7562-L | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Hyd Cyl Tilt LEFT |  | 21494.7 | 20000 | 2026-02-21 | 4 |  | 1111 | 2015-08-07
N1490 | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Cam Shaft Inspection |  | 14154.15 | 1500 | 2026-02-22 | 6.87 |  | 12003.69 | 2025-09-05
N0201-01 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | A Frame Bearing Reshim Initial |  | 67600 | 2000 | 2026-02-22 | 17 |  | 63977 | 2025-08-10 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | A Frame Bearing Reshim Initial |  | 52309.6 | 2000 | 2026-02-22 | 13 |  | 49079 | 2024-08-27 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1310 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Radiator |  | 69200 | 24000 | 2026-02-23 | 18.5 | 28/05/2026 | 43464 | 2021-03-23
N2050 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Torque Convertor |  | 69200 | 24000 | 2026-02-23 | 18.5 | 28/05/2026 | 43464 | 2021-03-23
N1002-1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Engine Valve Adj EN1 |  | 23756 | 4000 | 2026-02-23 | 18.5 |  | 18022 | 2025-06-29
N7600 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Control Valve |  | 31311 | 30000 | 2026-02-23 | 14 |  | 0
N1000 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Engine |  | 69200 | 24000 | 2026-02-23 | 18.5 | 28/05/2026 | 43464 | 2021-03-23
N9500-MA | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Air Cond'r-Serv - MAJOR |  | 69200 | 24000 | 2026-02-23 | 18.5 | 28/05/2026 | 43464 | 2021-03-23
N0520 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Pre Lube Pump |  | 69200 | 24000 | 2026-02-23 | 18.5 | 28/05/2026 | 43464 | 2021-03-23
N8442-01 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 1 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N0123-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Carrier Roller No 3 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0123-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Carrier Roller No 3 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N1002 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Engine Valve Adj |  | 25353 | 2500 | 2026-02-24 | 12.5 |  | 21687 | 2025-08-26 |  | 229-5711 | SEAL-VALVE COVER
N0134-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Adjuster LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0111-8L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 8 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0134-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Adjuster RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0140 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Equalizer Bar |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 526-3821 | BAR AS-EQUAL
N0111-7R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 7 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-1L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 1 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-1R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 1 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-6R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 6 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-2L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 2 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-6L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 6 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-2R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 2 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-3L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 3 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-3R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 3 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-5R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 5 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-4L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 4 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-7L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 7 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 10 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Carrier Roller No 2 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N8442-04 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 4 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N0101-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Chain RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N0101-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Chain LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N8442-05 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 5 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N8442-06 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 6 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N0111-9R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 9 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N8442-08 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 8 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N0111-9L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 9 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 10 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Carrier Roller No 2 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 11 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 11 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0105-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Idler RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0112-2R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 12 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-3L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 13 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N8442-07 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 7 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N0121-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Carrier Roller No 1 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0121-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Carrier Roller No 1 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 8 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0105-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Idler LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0111-5L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 5 LEFT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-4R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 4 RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7600-LU | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Control Valve LEFT UPPER |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 517-7953 | VALVE GP-CONTROL
N0033-PR | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Water Tank - PRIMARY |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0
N7600-LL | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Control Valve LEFT LOWER |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 517-7954 | VALVE GP-CONTROL
N7570-RR | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT REA |  | 16307 | 15000 | 2026-02-24 | 14 | 31/05/2026 | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N7524 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock |  | 16307 | 15000 | 2026-02-24 | 14 | 28/06/2026 | 0
N7330-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Hyd Motor Travel RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 | 31/05/2026 | 0 |  |  | 20R-9462 | MOTOR GP
N8442-02 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Ball Studs POS 2 |  | 56902.96 | 20000 | 2026-02-24 | 13.5 | 01/06/2026 | 35643 | 2021-08-22
N7608 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Control Valve Jack/Mast Raise |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 514-2137 | VALVE GP-CONTROL
N5000-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Final Drive RIGHT |  | 16307 | 15000 | 2026-02-24 | 14 | 31/05/2026 | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N5000-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Final Drive LEFT |  | 16307 | 15000 | 2026-02-24 | 14 | 31/05/2026 | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N0033-SC | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Water Tank - SECONDARY |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0
N7330-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Hyd Motor Travel LEFT |  | 16307 | 15000 | 2026-02-24 | 14 | 31/05/2026 | 0 |  |  | 20R-9462 | MOTOR GP
N7600-LW | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Control Valve LOWER |  | 16307 | 15000 | 2026-02-24 | 14 |  | 0 |  |  | 517-7952 | VALVE GP-CONTROL
N9020 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Alternator |  | 67400 | 10000 | 2026-02-26 | 17 |  | 55854 | 2022-05-17 |  | 10R-8755 | ALTERNATOR GP_B
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD4376 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 66519 | 24000 | 2026-02-26 | 13 |  | 41337.7 | 2012-03-14
N3021 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Uni's Eng - Pump Drive |  | 56902.96 | 10000 | 2026-02-26 | 13.5 | 01/06/2026 | 34800 | 2020-12-14
IF22021 | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Harness Anchor Point Insp |  | 2718 | 0 | 2026-02-26 | 15.2 |  | 1445 | 2025-11-28
N9703 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Inertial Measurement Unit |  | 11349 | 10000 | 2026-02-27 | 15 | 02/06/2026 | 0
N7432-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Bucket LEFT |  | 23746 | 10000 | 2026-02-27 | 18.5 |  | 12089 | 2024-07-23
N7421-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Hyd Cyl Blade Tilt RIGHT |  | 31311 | 12000 | 2026-02-28 | 14 |  | 18071 | 2022-09-06 |  | 521-8392
N9735-JC | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | AS Hardware - JUMPER CONNECTOR |  | 21238 | 20000 | 2026-03-01 | 14 | 28/05/2026 | 0
N7542-L | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Hyd Cyl Steer LEFT |  | 59122 | 12000 | 2026-03-03 | 18.5 | 08/08/2026 | 45524 | 2023-10-27
N9500 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Air Cond'r-Serv |  | 34291 | 0 | 2026-03-03 | 13.79 |  | 0 | 2025-03-03
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 4002 | 3000 | 2026-03-05 | 12 | 01/08/2026 | 0 | 2025-05-14
N9500 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 4002 | 3000 | 2026-03-05 | 12 | 01/08/2026 | 0 | 2025-05-14
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Steering Ball Studs POS 8 |  | 70598 | 12000 | 2026-03-06 | 18.5 |  | 57060 | 2024-04-27
N7542-L | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Hyd Cyl Steer LEFT |  | 70598 | 12000 | 2026-03-06 | 18.5 | 14/05/2026 | 57060 | 2024-04-27
N7542-R | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Hyd Cyl Steer RIGHT |  | 70598 | 12000 | 2026-03-06 | 18.5 | 14/05/2026 | 57060 | 2024-04-27
N8442-07 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Steering Ball Studs POS 7 |  | 70598 | 12000 | 2026-03-06 | 18.5 |  | 57060 | 2024-04-27
N1400-R | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Belt Tensioner Assy - RIGHT |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N7542-L | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Hyd Cyl Steer LEFT |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N1301 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Water Pump |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N1205 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Fuel Pump - High Pressure |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N3021 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Uni's Eng - Pump Drive |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N7542-R | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Hyd Cyl Steer RIGHT |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N1202 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Fuel Transfer Pump |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N1400-L | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Belt Tensioner Assy - LEFT |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N1300 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Cooling Sys Service |  | 61931 | 12000 | 2026-03-07 | 18.5 | 24/05/2026 | 48409 | 2023-10-31
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4222 | Cat 785C | Operator Seat |  | 41444 | 6000 | 2026-03-08 | 14.5 |  | 34275 | 2024-01-05 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9500-MA | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Air Cond'r-Serv - MAJOR |  | 69479 | 24000 | 2026-03-08 | 18.5 |  | 43980 | 2021-05-24
N7613 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Cooler Steering/Eng Fan |  | 78363 | 20000 | 2026-03-08 | 14 |  | 57233 | 2022-04-02 |  | 30R-0034 | CORE AS OIL
N1002-2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Engine Valve Adj EN2 |  | 23756 | 4000 | 2026-03-09 | 18.5 |  | 18270 | 2025-07-24
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Air Cond'r-Serv |  | 67187 | 5000 | 2026-03-11 | 14 |  | 61097 | 2023-09-23
N6063 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Oil Cooler - Steering |  | 58874 | 20000 | 2026-03-12 | 13.75 | 16/03/2026 | 37813 | 2021-05-05 |  | 0R-5517 | CORE GP OIL
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Brake Slack Adj FRONT |  | 58874 | 20000 | 2026-03-12 | 13.75 | 16/03/2026 | 37813 | 2021-05-05
N7120 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Pump Steering |  | 58874 | 20000 | 2026-03-12 | 13.75 | 16/03/2026 | 37813 | 2021-05-05
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Brake Slack Adj REAR |  | 58874 | 20000 | 2026-03-12 | 13.75 | 16/03/2026 | 37813 | 2021-05-05
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Oil Cooler - Brakes FRONT |  | 58874 | 20000 | 2026-03-12 | 13.75 | 16/03/2026 | 37813 | 2021-05-05
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Torque Convertor |  | 67187 | 20000 | 2026-03-14 | 14 |  | 46133 | 2020-02-04 |  | 20R-0924 | TORQUE CONVERTOR
N2000 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Transmission |  | 67187 | 20000 | 2026-03-14 | 14 |  | 46133 | 2020-02-04
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Transmission Pump |  | 67187 | 20000 | 2026-03-14 | 14 |  | 46133 | 2020-02-04
N8995 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Operator Seat |  | 67791 | 6000 | 2026-03-14 | 18.5 | 04/06/2026 | 60396 | 2025-04-17
N8995 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Operator Seat |  | 82501 | 6000 | 2026-03-15 | 18.5 | 11/06/2026 | 75138 | 2025-02-23 |  | 384-6168 | SEAT GP-SUSPENSION
N8995 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Operator Seat |  | 82501 | 6000 | 2026-03-15 | 18.5 |  | 75138 | 2025-02-23 |  | 384-6168 | SEAT GP-SUSPENSION
N4110-R | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Steering Clutch/Brk RIGHT |  | 43005.2 | 25000 | 2026-03-16 | 6.35 |  | 17542 | 2018-04-07
N4110-L | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Steering Clutch/Brk LEFT |  | 43005.2 | 25000 | 2026-03-16 | 6.35 |  | 17542 | 2018-04-07
N2050 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Torque Convertor |  | 52281 | 20000 | 2026-03-16 | 17 | 07/06/2026 | 31044 | 2015-06-24 | DELIVER TO MACKAY - REQUIRED BY 19/05/26
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | Air Cond'r-Serv |  | 59952 | 5000 | 2026-03-17 | 14 |  | 53942 | 2023-09-23
N4102-03 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Axle Shaft - POS 3 |  | 52281 | 20000 | 2026-03-17 | 17 | 07/06/2026 | 31049 | 2015-08-11 |  | 6G-6408 | SHAFT-AXLE (LH)
N4102-04 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Axle Shaft - POS 4 |  | 52281 | 20000 | 2026-03-17 | 17 | 07/06/2026 | 31049 | 2015-08-11 |  | 6G-6407 | SHAFT-AXLE (RH)
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Rear Axle Dog Bone |  | 50845.5 | 25000 | 2026-03-17 | 13.75 |  | 24854 | 2018-03-20
N0621-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 14426 | 2500 | 2026-03-18 | 14 | 07/06/2026 | 10931 | 2025-10-14 |  | 565-3200 | PULL DOWN ROPE
N0620-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 14426 | 2500 | 2026-03-18 | 14 | 07/06/2026 | 10931 | 2025-10-13 |  | 565-3199 | PULL DOWN ROPE
N6200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Press Convertor POS 4 |  | 86119 | 10000 | 2026-03-18 | 18.5 |  | 71290 | 2024-01-13 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N0621-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 14426 | 2500 | 2026-03-18 | 14 | 07/06/2026 | 10931 | 2025-10-13 |  | 565-3200 | PULL DOWN ROPE
N9501 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | A/C Compressor |  | 56829 | 12000 | 2026-03-18 | 18.5 |  | 48409 | 2023-10-31
N0620-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 14426 | 2500 | 2026-03-18 | 14 | 07/06/2026 | 10931 | 2025-10-13 |  | 565-3199 | PULL DOWN ROPE
N1490 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Cam Shaft Inspection |  | 50673 | 2000 | 2026-03-19 | 14 |  | 47698 | 2025-10-20 |  | 449-9059 | SEAL
N7237 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Hyd Motor Rear Axle Cooler Fan |  | 79490 | 24000 | 2026-03-19 | 14 |  | 54514 | 2021-05-27 |  | 307-1504 | MOTOR
N6200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Press Convertor POS 3 |  | 81805 | 10000 | 2026-03-19 | 18.5 |  | 70513 | 2024-07-14 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N3021 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Uni's Eng - Pump Drive |  | 63459.48 | 10000 | 2026-03-19 | 13.5 |  | 52513 | 2024-01-21
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Alternator |  | 70515 | 10000 | 2026-03-20 | 19 |  | 59198 | 2023-06-15 |  | 10R-9789 | ALTERNATOR GP -B
N0099 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 22440 | 2000 | 2026-03-20 | 12 |  | 19610 | 2025-09-20
N7570-RE | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Hyd Cyl Levelling Jack REAR |  | 22440 | 12000 | 2026-03-20 | 12 | 18/06/2026 | 9610 | 2025-09-20
N8995 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Operator Seat |  | 70598 | 6000 | 2026-03-20 | 18.5 | 14/05/2026 | 63319 | 2025-04-07
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Fuel Transfer Pump |  | 70515 | 10000 | 2026-03-20 | 19 |  | 59198 | 2023-06-15 |  | 10R-8721 | PUMP GP FUEL
N4102-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4222 | Cat 785C | Axle Shaft - POS 4 |  | 41444 | 20000 | 2026-03-20 | 14.5 |  | 20445 | 2019-07-15 |  | 6G-6407 | SHAFT-AXLE (RH)
N1400 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Belt Tensioner Assembly |  | 70515 | 10000 | 2026-03-20 | 19 |  | 59198 | 2023-06-15 |  | 336-4953 | TENSIONER,BELT
N6023 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Park Brake Disc/Drum |  | 28724 | 16000 | 2026-03-21 | 15 |  | 11710 | 2024-03-30
N7234-RU | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Motor Cooler Fan REAR UPP |  | 55435 | 16000 | 2026-03-21 | 18.5 | 02/06/2026 | 38185 | 2021-10-11
N3340 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Rotary Head |  | 5943 | 5000 | 2026-03-21 | 13.79 |  | 0 | 2025-04-19 | Parts Ordered in AMT?
N9500-MA | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Air Cond'r-Serv - MAJOR |  | 69633 | 24000 | 2026-03-22 | 18.5 | 02/07/2026 | 44390 | 2021-04-18
N1310 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Radiator |  | 69633 | 24000 | 2026-03-22 | 18.5 | 02/07/2026 | 44390 | 2021-04-18
N1002 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Engine Valve Adj |  | 28724 | 2000 | 2026-03-22 | 15 |  | 25716 | 2025-07-04
N2050 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Torque Convertor |  | 69633 | 24000 | 2026-03-22 | 18.5 | 02/07/2026 | 44390 | 2021-04-18
N3020 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Drive Shaft Eng - Pump Drive |  | 69633 | 24000 | 2026-03-22 | 18.5 | 02/07/2026 | 44390 | 2021-04-18
N1000 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Engine |  | 69633 | 24000 | 2026-03-22 | 18.5 | 02/07/2026 | 44390 | 2021-04-18
N0201-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | A Frame Bearing Reshim Initial |  | 82501 | 2000 | 2026-03-23 | 18.5 |  | 79278 | 2025-10-02 |  | 8X-2934 | SHIM PACK
N3200-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Splitter Box EN2 |  | 23756 | 18000 | 2026-03-23 | 18.5 | 11/06/2026 | 4538 | 2023-04-24
N8200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Ride Strut POS 2 |  | 39200 | 20000 | 2026-03-23 | 14 |  | 18270 | 2017-12-17
N0140 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Equalizer Bar |  | 52003.6 | 14000 | 2026-03-24 | 12 |  | 37227 | 2021-07-29
N7657-L | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Hyd Accum Steering LEFT |  | 49506 | 20000 | 2026-03-25 | 14.5 |  | 28580 | 2017-09-24 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N0520 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Pre Lube Pump |  | 67791 | 24000 | 2026-03-25 | 18.5 | 04/06/2026 | 42612 | 2021-02-09
N7657-R | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Hyd Accum Steering RIGHT |  | 49506 | 20000 | 2026-03-25 | 14.5 |  | 28580 | 2017-09-24 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N9500-MA | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Air Cond'r-Serv - MAJOR |  | 67791 | 24000 | 2026-03-25 | 18.5 | 04/06/2026 | 42612 | 2021-02-09
N4000 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Bevel Gear |  | 69633 | 18000 | 2026-03-26 | 18.5 | 02/07/2026 | 50472 | 2022-07-13
N5003-04 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Final Drive Ext Life POS 4 |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N8137-L | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Steering Linkage Group LEFT |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 2A-6946 | LINK GP - STEERING
N6062-RE | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 10R-5675 | CORE AS OIL
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Radiator |  | 58852 | 20000 | 2026-03-26 | 15 |  | 37906 | 2018-08-24 |  | 145-1226 | PEX SX 789C RADIATOR
N6062-F | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 10R-5675 | CORE AS OIL
N7647 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Hyd Accum Brake Reseal |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 243-5339 | ACCUMULATOR GP-BRAKE
N8140 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Steering Y Piece |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 207-7321 | CENTRE ARM, STEERING, 793
N8137-R | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Steering Linkage Group RIGHT |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 2A-6946 | LINK GP - STEERING
N4102-04 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Axle Shaft - POS 4 |  | 79716 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 223-1079 | SHAFT (RH)
N4102-03 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Axle Shaft - POS 3 |  | 79716 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 223-1078 | SHAFT (LH)
N5003-03 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Final Drive Ext Life POS 3 |  | 79726 | 20000 | 2026-03-26 | 18.5 | 07/05/2026 | 58553 | 2022-07-17 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N7541 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Hyd Cyl Access Ladder |  | 79726 | 20000 | 2026-03-26 | 18.5 |  | 58553 | 2022-07-17 |  | 339-3275 | CYLINDER GP
N2000 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Transmission |  | 69633 | 18000 | 2026-03-26 | 18.5 | 02/07/2026 | 50472 | 2022-07-13
N7602 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Relief Valve |  | 18065 | 0 | 2026-03-27 | 13 |  | 0 | 2024-03-27
N7414-R | WA | CAT | 85 |  | GR1549 | Cat 16M | Hyd Cyl Artic RIGHT |  | 23153 | 8000 | 2026-03-27 | 10 |  | 14535 | 2023-03-16 | THIESS MANAGED
N7414-L | WA | CAT | 85 |  | GR1549 | Cat 16M | Hyd Cyl Artic LEFT |  | 23153 | 8000 | 2026-03-27 | 10 |  | 14535 | 2023-03-16 | THIESS MANAGED
N7602 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Relief Valve |  | 7751 | 0 | 2026-03-28 | 9.59 |  | 0 | 2024-03-28
N9500-MA | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv - MAJOR |  | 7751 | 0 | 2026-03-28 | 9.59 |  | 0 | 2024-03-28
N8995 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Operator Seat |  | 53351 | 6000 | 2026-03-28 | 12 |  | 46615 | 2023-11-02 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9701 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | LiDAR Detection System |  | 5839 | 5000 | 2026-03-29 | 14 | 07/07/2026 | 0 | 2024-11-09
N0105-LR | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Idler LFT REAR |  | 45807 | 8000 | 2026-03-29 | 14 |  | 36961 | 2022-07-22 |  | 125-3537 | IDLER GP-TRACK
N7039 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Pump Cooler Fan Hyd/Eng |  | 34291 | 14000 | 2026-03-29 | 13.79 | 20/05/2026 | 19459 | 2022-07-01
N0111-3L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 3 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0121-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Carrier Roller No 1 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-2R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 2 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-5L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 5 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0121-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Carrier Roller No 1 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-7L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 7 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-4R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 4 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-6L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 6 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0105-RR | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Idler RHT REAR |  | 45807 | 8000 | 2026-03-29 | 14 |  | 36961 | 2022-07-22 |  | 125-3537 | IDLER GP-TRACK
N0105-LF | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Idler LFT FRONT |  | 45807 | 8000 | 2026-03-29 | 14 |  | 36961 | 2022-07-22 |  | 125-3537 | IDLER GP-TRACK
N0111-5R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 5 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N1490 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 21277 | 2000 | 2026-03-29 | 14 |  | 18436 | 2025-10-16 |  | 449-9059 | SEAL
N0104-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Sprockets RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0105-R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Idler RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-2L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 2 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0105-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Idler LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0104-L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Sprockets LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0105-RF | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Idler RHT FRONT |  | 45807 | 8000 | 2026-03-29 | 14 |  | 36961 | 2022-07-22 |  | 125-3537 | IDLER GP-TRACK
N0111-6R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 6 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-4L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 4 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-1L | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 1 LEFT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-7R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 7 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N0111-3R | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Track Roller 3 RIGHT |  | 34291 | 14000 | 2026-03-29 | 13.79 |  | 19459 | 2022-07-01
N3020 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Drive Shaft Eng - Pump Drive |  | 82501 | 20000 | 2026-03-30 | 18.5 |  | 61407 | 2021-04-26 |  | 339-6380 | JOINT GP-UNI
N3020 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Drive Shaft Eng - Pump Drive |  | 82501 | 20000 | 2026-03-30 | 18.5 | 11/06/2026 | 61407 | 2021-04-26 |  | 339-6380 | JOINT GP-UNI
N7514-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cyl Ripper Pitch LEFT |  | 31190.5 | 14000 | 2026-03-30 | 12 |  | 16484.02 | 2022-06-30
N1300 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Cooling Sys Service |  | 32356 | 6000 | 2026-03-31 | 11 | 03/07/2026 | 25721 | 2023-09-29 | THIESS MANAGED | 248-5513 | REGULATOR-TEMPERATURE
N8442-07 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Steering Ball Studs POS 7 |  | 53598.82 | 20000 | 2026-03-31 | 13.5 |  | 32810 | 2021-09-11
N1100-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Turbo Primary LEFT |  | 32356 | 6000 | 2026-03-31 | 11 | 03/07/2026 | 25721 | 2023-09-29 | THIESS MANAGED | 10R-2075 | TURBO, D10T, REMAN
N8442-05 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Steering Ball Studs POS 5 |  | 53598.82 | 20000 | 2026-03-31 | 13.5 |  | 32810 | 2021-09-11
N0104-R | WA | CAT | 85 |  | DZ3431 | Cat D10T | Sprockets RIGHT |  | 32356 | 6000 | 2026-03-31 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 433-6739 | 7796592
N0105-RR | WA | CAT | 85 |  | DZ3431 | Cat D10T | Idler RHT REAR |  | 32356 | 6000 | 2026-03-31 | 11 |  | 25721 | 2025-01-01 | THIESS MANAGED | 125-3537 | IDLER GP-TRACK
N1202 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Fuel Transfer Pump |  | 32356 | 6000 | 2026-03-31 | 11 | 03/07/2026 | 25721 | 2023-09-29 | THIESS MANAGED | 20R-0967 | PUMP GP
N8442-06 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Steering Ball Studs POS 6 |  | 53598.82 | 20000 | 2026-03-31 | 13.5 |  | 32810 | 2021-09-11
N8442-04 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Steering Ball Studs POS 4 |  | 53598.82 | 20000 | 2026-03-31 | 13.5 |  | 32810 | 2021-09-11
N8442-08 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Steering Ball Studs POS 8 |  | 53598.82 | 20000 | 2026-03-31 | 13.5 |  | 32810 | 2021-09-11
N7602 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Relief Valve |  | 17835 | 0 | 2026-03-31 | 13 |  | 0 | 2024-03-31
N1100-R | WA | CAT | 85 |  | DZ3431 | Cat D10T | Turbo Primary RIGHT |  | 32356 | 6000 | 2026-03-31 | 11 | 03/07/2026 | 25721 | 2023-09-29 | THIESS MANAGED | 10R-2075 | TURBO, D10T, REMAN
N7602 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Relief Valve |  | 18651 | 0 | 2026-03-31 | 13 |  | 0 | 2024-03-31
N0105-RF | WA | CAT | 85 |  | DZ3431 | Cat D10T | Idler RHT FRONT |  | 32356 | 6000 | 2026-03-31 | 11 |  | 25721 | 2025-01-01 | THIESS MANAGED | 125-3537 | IDLER GP-TRACK
N0105-LF | WA | CAT | 85 |  | DZ3431 | Cat D10T | Idler LFT FRONT |  | 32356 | 6000 | 2026-03-31 | 11 |  | 25721 | 2025-01-01 | THIESS MANAGED | 125-3537 | IDLER GP-TRACK
N0105-LR | WA | CAT | 85 |  | DZ3431 | Cat D10T | Idler LFT REAR |  | 32356 | 6000 | 2026-03-31 | 11 |  | 25721 | 2025-01-01 | THIESS MANAGED | 125-3537 | IDLER GP-TRACK
N8442-03 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Steering Ball Studs POS 3 |  | 53598.82 | 20000 | 2026-03-31 | 13.5 |  | 32810 | 2021-09-11
N1490 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 11349 | 2000 | 2026-04-01 | 15 |  | 8495 | 2025-10-21 |  | 449-9059 | SEAL
N9500 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Air Cond'r-Serv |  | 5650 | 0 | 2026-04-01 | 13.79 |  | 0 | 2025-04-01
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Ride Strut POS 3 |  | 70598 | 25000 | 2026-04-01 | 18.5 |  | 44552 | 2020-12-21
N1490 | WA | CAT | 85 | McPhee Creek | RD6623 | Cat 777 | Cam Shaft Inspection |  | 1958.65 | 1500 | 2026-04-01 | 8 |  | 0 | 2025-01-08
N1002 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Engine Valve Adj |  | 42291 | 3000 | 2026-04-02 | 10 |  | 38734 | 2025-06-02 |  | 224-7506 | SEAL-VALVE COVER
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4235 | Cat 789C | Engine Valve Adj |  | 63637 | 4000 | 2026-04-02 | 14 |  | 58846 | 2022-09-29 |  | 272-0760 | SEAL-PIP
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Uni's T/C - Trans |  | 64230 | 10000 | 2026-04-04 | 14 |  | 53474 | 2022-07-15 |  | 363-1923 | MAIN DRIVESHAFT UNI
N0103-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Track Plates LEFT |  | 46895 | 1500 | 2026-04-04 | 13.5 |  | 44668 | 2025-07-03
N0099 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 21534 | 2000 | 2026-04-04 | 12 |  | 18883 | 2025-09-26
N0620-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 21277 | 2500 | 2026-04-04 | 14 | 31/12/2026 | 18019 | 2025-09-19 |  | 565-3199 | PULL DOWN ROPE
N0621-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 21277 | 2500 | 2026-04-04 | 14 | 31/12/2026 | 18019 | 2025-09-18 |  | 565-3200 | PULL DOWN ROPE
N0103-R | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Track Plates RIGHT |  | 46895 | 1500 | 2026-04-04 | 13.5 |  | 44668 | 2025-07-03
N0620-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 21277 | 2500 | 2026-04-04 | 14 | 31/12/2026 | 18019 | 2025-09-19 |  | 565-3199 | PULL DOWN ROPE
N9500 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Air Cond'r-Serv |  | 46731 | 5000 | 2026-04-04 | 16 |  | 40873 | 2023-10-04
N7474-L | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Hyd Cyl Hoist LEFT |  | 69305 | 24000 | 2026-04-04 | 17 | 06/07/2026 | 44395 | 2019-07-29 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N7474-R | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Hyd Cyl Hoist RIGHT |  | 69305 | 24000 | 2026-04-04 | 17 | 06/07/2026 | 44395 | 2019-07-29 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N0621-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 21277 | 2500 | 2026-04-04 | 14 | 31/12/2026 | 18019 | 2025-09-18 |  | 565-3200 | PULL DOWN ROPE
N9500 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Air Cond'r-Serv |  | 62083 | 4000 | 2026-04-05 | 18.5 | 13/08/2026 | 57104 | 2025-09-14
N8443-UL | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Rear Axle Control Arm U/LEFT |  | 70598 | 20000 | 2026-04-05 | 18.5 | 14/05/2026 | 49611 | 2021-11-22
N9500-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Air Cond'r-Serv RIGHT |  | 23756 | 4500 | 2026-04-05 | 18.5 | 11/06/2026 | 18270 | 2025-07-24
N8443-LL | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Rear Axle Control Arm L/LEFT |  | 70598 | 20000 | 2026-04-05 | 18.5 | 14/05/2026 | 49611 | 2021-11-22
N9500 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Air Cond'r-Serv |  | 44378 | 6000 | 2026-04-05 | 15 | 21/05/2026 | 37584 | 2025-03-22
N9500-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Air Cond'r-Serv LEFT |  | 23756 | 4500 | 2026-04-05 | 18.5 | 11/06/2026 | 18270 | 2025-07-24
N8200-03 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Ride Strut POS 3 |  | 54979 | 20000 | 2026-04-05 | 14 |  | 34235 | 2020-06-22 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N1490 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Cam Shaft Inspection |  | 52003.6 | 1500 | 2026-04-06 | 12 |  | 49885 | 2025-08-17
N3028 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Drive Shaft T/C - Trans |  | 69479 | 16000 | 2026-04-07 | 18.5 | 26/06/2026 | 52539 | 2023-02-20
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Brake Slack Adj REAR |  | 69479 | 16000 | 2026-04-07 | 18.5 | 26/06/2026 | 52539 | 2023-02-20
N1000 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Engine |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N1100 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Turbo Primary |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N7155-02 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L3,4 |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N7032 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Pump Cooler Fan Hyd |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N0551 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Cooler Aircompressor |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N0325 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Carousel Assembly |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N7155-01 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L1,2 |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N1312 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Aftercooler Core |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N2002 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Oil Cooler - Transmission |  | 70598 | 20000 | 2026-04-08 | 18.5 | 14/05/2026 | 49669 | 2021-12-01
N7610 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Cooler Core |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N7155-03 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L5,6 |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N1310 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Radiator |  | 18651 | 18000 | 2026-04-08 | 13 |  | 0 | 2022-06-01
N7514-R | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cyl Ripper Pitch RIGHT |  | 31190.5 | 14000 | 2026-04-09 | 12 |  | 16597 | 2022-06-30
N1490 | WA | CAT | 85 | McPhee Creek | RD6624 | Cat 777 | Cam Shaft Inspection |  | 1889.7 | 1500 | 2026-04-09 | 8 |  | 0 | 2025-01-08
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | Engine Valve Adj |  | 55805 | 4000 | 2026-04-09 | 14 |  | 51122 | 2022-05-07 |  | 272-0760 | SEAL-PIP
N0100-L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Group LEFT |  | 17737.5 | 1700 | 2026-04-10 | 6.35 |  | 15731.23 | 2025-08-04
N9500 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Air Cond'r-Serv |  | 47029 | 0 | 2026-04-10 | 4.12 |  | 0 | 2025-04-10
N1002 | WA | CAT | 85 | McPhee Creek | RD6606 | Cat 789D | Engine Valve Adj |  | 4532.2 | 4000 | 2026-04-10 | 11.19 |  | 0 | 2024-05-21
N0100-R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Group RIGHT |  | 17737.5 | 1700 | 2026-04-10 | 6.35 |  | 15731.06 | 2025-08-04
N2450 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Drv Cpling Fan Pump-Trans Pump |  | 31311 | 7000 | 2026-04-10 | 14 | 27/08/2026 | 23635 | 2023-12-14
N3340 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Rotary Head |  | 5650 | 5000 | 2026-04-11 | 13.79 |  | 0 | 2025-04-01 | Parts Ordered in AMT
N6060-F | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Oil Cooler - Brakes FRONT |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 10R-0817 | CORE GP-O CLR
N8140 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Steering Y Piece |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01
N0520 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Pre Lube Pump |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 116-7153 | PUMP & MOTOR, PRELUBE, ASSY
N3020 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01
N3028 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Drive Shaft T/C - Trans |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 10R-5186 | JOINT GP-SLIP
N8137-L | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Steering Linkage Group LEFT |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 |  |  | 2A-7217 | LINK,STEERING,785
N7657-L | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Hyd Accum Steering LEFT |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N8200-03 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Ride Strut POS 3 |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N7657-R | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Hyd Accum Steering RIGHT |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N4102-03 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Axle Shaft - POS 3 |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 | 2017-08-01 |  | 6G-6408 | SHAFT-AXLE (LH)
N8137-R | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Steering Linkage Group RIGHT |  | 65021 | 20000 | 2026-04-11 | 8.5 |  | 44622 |  |  | 2A-7217 | LINK,STEERING,785
N7020 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Brake |  | 44378 | 12000 | 2026-04-13 | 15 | 21/05/2026 | 31703 | 2024-02-04
N0300-H | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 21515 | 2500 | 2026-04-13 | 12 | 05/06/2026 | 18480 | 2025-09-01
N8995 | WA | CAT | 85 | Iron Bridge | LO2089 | Cat 966M Wheel Loader | Operator Seat |  | 6543 | 6000 | 2026-04-13 | 12 |  | 0
N6030-F | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Brake Slack Adj FRONT |  | 65569 | 16000 | 2026-04-14 | 18.5 | 03/05/2026 | 48746 | 2021-11-12
N7600-L | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Control Valve LEFT |  | 34192 | 24000 | 2026-04-15 | 12 | 16/07/2026 | 0
N1002 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Engine Valve Adj |  | 79490 | 4000 | 2026-04-15 | 14 |  | 74884 | 2025-07-17 |  | 272-0760 | SEAL-VALVE COVER
N9500 | WA | CAT | 19 | Iron Bridge | RD4822 | Cat 785C | Air Cond'r-Serv |  | 32755 | 5000 | 2026-04-15 | 12.9 | 03/07/2026 | 0
N0145 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Pivot Shaft Brgs |  | 17835 | 4000 | 2026-04-16 | 13 | 19/06/2026 | 13283.14 | 2025-04-25 | CHECK WEAR - ORDER PER ML 24/03 - PUSH TO JUNE
N9500 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Air Cond'r-Serv |  | 59517 | 4000 | 2026-04-16 | 18.5 | 21/07/2026 | 54741 | 2025-09-11
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | A Frame Bearing Reshim Initial |  | 60741 | 2000 | 2026-04-16 | 14 |  | 58150 | 2024-07-10
N9500 | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 22613 | 3000 | 2026-04-17 | 12 |  | 19120 | 2026-03-15
N6200-F | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Press Converter FRONT |  | 47029 | 12000 | 2026-04-18 | 4.12 | 01/09/2026 | 34865 | 2009-02-10
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Air Cond'r-Serv |  | 64230 | 5000 | 2026-04-19 | 14 |  | 58688 | 2023-09-14
N1002 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Engine Valve Adj |  | 54781 | 4000 | 2026-04-19 | 15 |  | 50191 | 2022-04-21 |  | 272-0760 | SEAL-PIP
N9500 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Air Cond'r-Serv |  | 5943 | 0 | 2026-04-19 | 13.79 |  | 0 | 2025-04-19
N8995 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Operator Seat |  | 21508 | 6000 | 2026-04-19 | 12 | 28/05/2026 | 15035 | 2024-07-27
N2090 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Drv Coupling |  | 21508 | 6000 | 2026-04-19 | 12 | 28/05/2026 | 15035 | 2024-07-26
N0558 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Air End Coupling |  | 21508 | 6000 | 2026-04-19 | 12 | 28/05/2026 | 15035 | 2024-07-27
N3016 | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Drv Shaft Fan Pump-Trans Pump |  | 53910 | 15000 | 2026-04-19 | 12 | 01/02/2026 | 38442 | 2018-12-19 |  | 211-9087 | COUPLING AS
N7605 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Steering Hmu |  | 24344.16 | 12000 | 2026-04-20 | 13.5 | 16/06/2026 | 11825.21 | 2023-07-16
N7432-R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cyl Bucket RIGHT |  | 55435 | 8000 | 2026-04-20 | 18.5 |  | 46727 | 2024-12-10
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | A Frame Bearing Reshim Initial |  | 49506 | 2000 | 2026-04-20 | 14.5 |  | 46952 | 2025-02-14 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N8443-UR | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Rear Axle Control Arm U/RIGHT |  | 70598 | 20000 | 2026-04-20 | 18.5 | 14/05/2026 | 49891 | 2021-12-18
N9500-F | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Air Cond'r-Serv FRONT |  | 55435 | 4000 | 2026-04-22 | 18.5 | 11/05/2026 | 50766 | 2025-08-19
N9500-RE | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Air Cond'r-Serv REAR |  | 55435 | 4000 | 2026-04-22 | 18.5 | 11/05/2026 | 50766 | 2025-08-19
N4102-03 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Axle Shaft - POS 3 |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 6G-6408 | SHAFT-AXLE (LH)
N0200 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | A Frame Bearing |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 6V-0444 | BEARING, PLAIN, SPHERICAL
N6030-F | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Brake Slack Adj FRONT |  | 54428 | 20000 | 2026-04-23 | 17 |  | 33839 | 2020-01-31 |  | 566-9762 | SLACK ADJUSTER
N7064 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Pump Hoist |  | 45967 | 16000 | 2026-04-23 | 12 | 20/07/2026 | 29545 | 2018-09-04
N6060-F | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Oil Cooler - Brakes FRONT |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 10R-0817 | CORE GP-O CLR
N7065 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Pump Hoist/ Brk Cooling |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 10R-7971 | PUMP, HOIST, REMAN
N8200-02 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Ride Strut POS 2 |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 | DELIVER TO MACKAY - REQUIRED BY 19/05/26
N7657-R | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Hyd Accum Steering RIGHT |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N7657-L | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Hyd Accum Steering LEFT |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N6030-RE | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Brake Slack Adj REAR |  | 54428 | 20000 | 2026-04-23 | 17 |  | 33839 | 2020-01-31 |  | 566-9766 | ADJUSTER GP
N1310 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Radiator |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31
N6000-04 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Brake POS 4 |  | 45967 | 16000 | 2026-04-23 | 12 | 20/07/2026 | 29545 | 2018-10-16
N4102-04 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Axle Shaft - POS 4 |  | 54428 | 20000 | 2026-04-23 | 17 | 01/06/2026 | 33839 | 2020-01-31 |  | 6G-6407 | SHAFT-AXLE (RH)
N0100-L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Group LEFT |  | 7287 | 2000 | 2026-04-24 | 12 |  | 4875 | 2025-10-28
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Steering Linkage Group LEFT |  | 41713 | 20000 | 2026-04-24 | 15 |  | 21206 |  |  | 2A-7217 | LINK,STEERING,785
N1490 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Cam Shaft Inspection |  | 31311 | 2000 | 2026-04-24 | 14 |  | 28840 | 2025-11-05 |  | 449-9059 | SEAL
N0100-R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Group RIGHT |  | 7287 | 2000 | 2026-04-24 | 12 |  | 4875 | 2025-10-28
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Steering Y Piece |  | 41713 | 20000 | 2026-04-24 | 15 |  | 21206 | 2014-04-23
N2000 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Transmission |  | 46731 | 15000 | 2026-04-24 | 16 |  | 31184 | 2020-12-07 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Steering Linkage Group RIGHT |  | 41713 | 20000 | 2026-04-24 | 15 |  | 21206 |  |  | 2A-7217 | LINK,STEERING,785
N2020 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Powertrain Pump |  | 46731 | 15000 | 2026-04-24 | 16 |  | 31186 | 2020-12-07 |  | 20R-7445 | PUMP GP
N7065 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Pump Hoist/ Brk Cooling |  | 54979 | 5000 | 2026-04-25 | 14 | 01/08/2026 | 49521 | 2025-08-24 |  | 10R-7971 | PUMP, HOIST, REMAN
N0091 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Grease Pump |  | 8398 | 8000 | 2026-04-25 | 12 |  | 0
N0623-RL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Sheave LOWER RIGHT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-8053 | SHEAVE AS
N0623-RU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Sheave UPPER RIGHT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-8053 | SHEAVE AS
N0623-TL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Sheave TRAVEL LEFT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-6156 | SHEAVE
N5000-R | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Final Drive RIGHT |  | 62609 | 15000 | 2026-04-26 | 12 | 10/07/2026 | 47224 | 2019-02-25 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-6295 | FINAL DRIVE, D10
N8300 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Artic Hitch |  | 37630 | 16000 | 2026-04-26 | 12 |  | 21251 | 2018-10-15
N0300-H | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 20661 | 2500 | 2026-04-26 | 12 | 21/08/2026 | 17771 | 2025-07-25
N7151 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 21534 | 6000 | 2026-04-26 | 12 |  | 15146 | 2024-11-18
N0623-TR | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Sheave TRAVEL RIGHT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-6156 | SHEAVE
N0623-LU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Sheave UPPER LEFT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-8053 | SHEAVE AS
N7610 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Cooler Core |  | 62609 | 15000 | 2026-04-26 | 12 |  | 47224 | 2019-03-04 |  | 0R-5515 | CORE AS OIL
N0622-TR | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL RIGHT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-6156 | SHEAVE
N0622-LL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Sheave LOWER LEFT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-30 |  | 450-8053 | SHEAVE AS
N9500-MA | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Air Cond'r-Serv - MAJOR |  | 62609 | 15000 | 2026-04-26 | 12 |  | 47224 | 2019-03-06 |  | 418-6835 | HEATER & AC GP
N0622-LU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Sheave UPPER LEFT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-8053 | SHEAVE AS
N3016 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Drv Shaft Fan Pump-Trans Pump |  | 62609 | 15000 | 2026-04-26 | 12 |  | 47224 | 2019-03-04 |  | 211-9087 | COUPLING AS
N0622-RL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Sheave LOWER RIGHT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-8053 | SHEAVE AS
N2050 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Torque Convertor |  | 62609 | 15000 | 2026-04-26 | 12 | 10/07/2026 | 47224 | 2019-02-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 10R-5295 | TORQUE CONVERTER, D10
N3028 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Drive Shaft T/C - Trans |  | 62609 | 15000 | 2026-04-26 | 12 |  | 47224 | 2019-03-12 |  | 173-0247 | YOKE COUPLING
N0622-RU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Sheave UPPER RIGHT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-30 |  | 450-8053 | SHEAVE AS
N2020 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Powertrain Pump |  | 62609 | 15000 | 2026-04-26 | 12 | 10/07/2026 | 47224 | 2019-03-04 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-7445 | PUMP GP
N0623-LL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pullback Sheave LOWER LEFT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-8053 | SHEAVE AS
N0622-TL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL LEFT |  | 14426 | 7500 | 2026-04-26 | 14 | 07/06/2026 | 6478 | 2024-11-29 |  | 450-6156 | SHEAVE
N7041 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Pump Cooling Fan Engine |  | 62609 | 15000 | 2026-04-26 | 12 | 10/07/2026 | 47224 | 2019-02-27 |  | 10R-5603 | PUMP GP
N7647-RE | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Accum Brake Reseal REAR |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N8442-05 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Steering Ball Studs POS 5 |  | 70598 | 12000 | 2026-04-28 | 18.5 |  | 58043 | 2024-06-18
N0620-L | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 5839 | 2500 | 2026-04-28 | 14 | 07/07/2026 | 2923 | 2025-10-29 |  | 565-3199 | PULL DOWN ROPE
N0620-R | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 5839 | 2500 | 2026-04-28 | 14 | 07/07/2026 | 2923 | 2025-10-29 |  | 565-3199 | PULL DOWN ROPE
N2440 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Drv Coupling PTO |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N0621-R | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 5839 | 2500 | 2026-04-28 | 14 | 07/07/2026 | 2923 | 2025-10-29 |  | 565-3200 | PULL DOWN ROPE
N1490 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Cam Shaft Inspection |  | 57859 | 1500 | 2026-04-28 | 16 |  | 55878 | 2025-01-13 |  | 224-7506 | SEAL-VALVE COVER
N3047 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Drv Shft S/Bearing Pump Drives |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02 | PLEASE ADD TO SHUT DOWN - RH
N7562-L | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Cyl Tilt LEFT |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | A Frame Bearing Reshim Initial |  | 54402.5 | 2000 | 2026-04-28 | 13.75 |  | 51994 | 2025-01-10
N0621-L | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 5839 | 2500 | 2026-04-28 | 14 | 07/07/2026 | 2923 | 2025-10-29 |  | 565-3200 | PULL DOWN ROPE
N3320-01 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Drive Box POS 1/FR |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N3320-02 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Drive Box POS 2/RE |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N7121 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Steering/Braking |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N3038-RE | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Uni's Trans - Bevel Gear REAR |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N7120-L | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Steering LEFT |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N7120-R | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Steering RIGHT |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N7122 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Emerg/Sup Steering |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N7087 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Pilot |  | 70621 | 12000 | 2026-04-28 | 15 |  | 58177 | 2023-10-02
N8442-06 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Steering Ball Studs POS 6 |  | 70598 | 12000 | 2026-04-28 | 18.5 |  | 58043 | 2024-06-18
N7510-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Ripper Lift LEFT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9632 | CYL, RIPPER, LIFT, LH, D10
N7514-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Ripper Pitch LEFT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N7421-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Blade Tilt LEFT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9634 | Tilt Cylinder
N7420-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Blade Lift LEFT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9809 | BLADE LIFT CYLINDER
N7514-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Ripper Pitch RIGHT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N7510-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Ripper Lift RIGHT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9631 | CYL, RIPPER, LIFT, RH, D10
N7420-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Hyd Cyl Blade Lift RIGHT |  | 33117 | 8000 | 2026-04-29 | 11 |  | 24801 | 2023-04-03 |  | 20R-9809 | BLADE LIFT CYLINDER
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Rear Axle Dog Bone |  | 60646.3 | 25000 | 2026-04-29 | 13.75 |  | 35253 | 2020-04-27
N8200-01 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Ride Strut POS 1 |  | 62901.67 | 30000 | 2026-04-30 | 13.5 |  | 32521 | 2018-10-22
N7021 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Brake Cooling |  | 34192 | 12000 | 2026-04-30 | 12 | 16/07/2026 | 21855 | 2023-07-14
N6200-LR | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Press Converter LEFT REAR |  | 24344.16 | 15000 | 2026-04-30 | 13.5 |  | 8965.34 | 2022-12-26
N2090 | WA | CAT | 85 |  | GR1550 | Cat 16M | Drv Coupling |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N8300 | WA | CAT | 85 |  | GR1550 | Cat 16M | Artic Hitch |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N6200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Press Convertor POS 1 |  | 86119 | 12000 | 2026-05-01 | 18.5 |  | 73613 | 2024-06-20 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N7070 | WA | CAT | 85 |  | GR1550 | Cat 16M | Pump Implement |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 20R-0010 | PUMP G PIST
N6000-03 | WA | CAT | 85 |  | GR1550 | Cat 16M | Brake POS 3 |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 20R-9994 | BRAKE GP FRONT
N9500 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Air Cond'r-Serv |  | 69479 | 4000 | 2026-05-01 | 18.5 | 26/06/2026 | 64973 | 2025-09-21
N7600-FR | WA | CAT | 85 |  | GR1550 | Cat 16M | Control Valve FRONT |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N7620 | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Rotary Joint |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N1312 | WA | CAT | 85 |  | GR1550 | Cat 16M | Aftercooler Core |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N7600-RE | WA | CAT | 85 |  | GR1550 | Cat 16M | Control Valve REAR |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N2000 | WA | CAT | 85 |  | GR1550 | Cat 16M | Transmission |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N6000-05 | WA | CAT | 85 |  | GR1550 | Cat 16M | Brake POS 5 |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 20R-9994 | BRAKE GP FRONT
N7510 | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Ripper Lift |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 113-5264 | CYL, RIPPER, 16H, 16M
N3021 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Uni's Eng - Pump Drive |  | 24344.16 | 10000 | 2026-05-01 | 13.5 | 16/06/2026 | 10049.33 | 2023-03-04 | Job Added since last LTP Approval
N4000 | WA | CAT | 85 |  | GR1550 | Cat 16M | Bevel Gear |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 379-9145SX | AXLE ASSEMBLY, REAR, 16M
N1000 | WA | CAT | 85 |  | GR1550 | Cat 16M | Engine |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Engine Valve Adj |  | 41713 | 4000 | 2026-05-01 | 15 |  | 37314 | 2022-05-20
N0200 | WA | CAT | 85 |  | GR1550 | Cat 16M | A Frame Bearing |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N9501 | WA | CAT | 85 |  | GR1550 | Cat 16M | A/C Compressor |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N1002 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Engine Valve Adj |  | 69479 | 4000 | 2026-05-01 | 18.5 |  | 64973 | 2025-09-21
N7610 | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cooler Core |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N7600-S | WA | CAT | 85 |  | GR1550 | Cat 16M | Control Valve - STEERING |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14
N6000-04 | WA | CAT | 85 |  | GR1550 | Cat 16M | Brake POS 4 |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 20R-9994 | BRAKE GP FRONT
N6200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Press Convertor POS 2 |  | 86119 | 12000 | 2026-05-01 | 18.5 |  | 73613 | 2024-06-20 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6000-06 | WA | CAT | 85 |  | GR1550 | Cat 16M | Brake POS 6 |  | 27110.6 | 14000 | 2026-05-01 | 10 |  | 12845 | 2020-07-14 |  | 20R-9994 | BRAKE GP FRONT
N1000 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Engine |  | 79044 | 18000 | 2026-05-02 | 14 |  | 60683 | 2022-10-11 |  | 488-8196 | 793D PEX ENGINE
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Turbo Primary RIGHT |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-18 |  | 20R-3423 | TURBO GRP
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Press Converter LEFT REAR |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-23 |  | 8X-7220 | CHAMBER, BRAKE
N1420 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Air Compressor |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-16 |  | 0R-9626 | COMPRESSOR GP -B
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Uni's T/C - Trans |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2020-03-30 |  | 8R-7036 | SPIDER
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Turbo Primary LEFT |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-24 |  | 20R-3423 | TURBO GRP
N1004 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Engine Midlife |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-24
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Press Converter RIGHT REAR |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-23 |  | 8X-7220 | CHAMBER, BRAKE
N0520 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Pre Lube Pump |  | 79044 | 18000 | 2026-05-02 | 14 |  | 60683 | 2022-10-11 |  | 20R-8989 | MOTOR GP ELE
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Fuel Transfer Pump |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-18 |  | 10R-9838 | PUMP GP-F XFR
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Press Converter FRONT |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-22 |  | 8X-7220 | CHAMBER, BRAKE
N9500-MA | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Air Cond'r-Serv - MAJOR |  | 79044 | 18000 | 2026-05-02 | 14 |  | 60683 | 2022-10-11 |  | 137-2134 | AIR CONDITIONER GP
N4110-L | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Steering Clutch/Brk LEFT |  | 52003.6 | 25000 | 2026-05-02 | 12 |  | 26690.02 | 2018-09-19
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Alternator |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-21 |  | 10R-8755 | ALTERNATOR GP_B
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Fan Pulley Brgs |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-22 |  | 6Y-7651 | CONE BEARING
N5000-L | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Final Drive LEFT |  | 52003.6 | 25000 | 2026-05-02 | 12 |  | 26690.02 | 2018-09-19
N1310 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Radiator |  | 79044 | 18000 | 2026-05-02 | 14 |  | 60683 | 2022-10-11 |  | 334-6025 | RADIATOR COOLING GP
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Jockey Pulley Brgs |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2019-10-22 |  | 4S-5367 | BUSHING
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Cooling Sys Service |  | 41713 | 10000 | 2026-05-02 | 15 |  | 31328 | 2020-03-30 |  | 418-4162 | REGULATOR
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Operator Seat |  | 39200 | 6000 | 2026-05-03 | 14 |  | 32849 | 2021-03-07
N7613 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cooler Steering/Eng Fan |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 30R-0034 | CORE AS OIL
N2000 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Transmission |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-4469 | TRANSMISSION, 793D
N8137-R | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Steering Linkage Group RIGHT |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 2A-6946 | LINK GP - STEERING
N7613 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cooler Steering/Eng Fan |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 30R-0034 | CORE AS OIL
N5003-04 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Final Drive Ext Life POS 4 |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N5003-04 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Final Drive Ext Life POS 4 |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N7041 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Cooling Fan Engine |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5464 | PUMP GP HYD
N5003-03 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Final Drive Ext Life POS 3 |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N5003-03 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Final Drive Ext Life POS 3 |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N3320 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Drive Box |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 11R-1519 | PUMP DRIVE, 793D, 793F
N7647 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Accum Brake Reseal |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 243-5339 | ACCUMULATOR GP-BRAKE
N3320 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Drive Box |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 11R-1519 | PUMP DRIVE, 793D, 793F
N2000 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Transmission |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-4469 | TRANSMISSION, 793D
N6062-RE | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5675 | CORE AS OIL
N6062-RE | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5675 | CORE AS OIL
N9500-MA | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Air Cond'r-Serv - MAJOR |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 137-2134 | AIR CONDITIONER GP
N9500 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Air Cond'r-Serv |  | 59122 | 4000 | 2026-05-04 | 18.5 | 13/07/2026 | 54678 | 2025-10-06
N9500-MA | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Air Cond'r-Serv - MAJOR |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 137-2134 | AIR CONDITIONER GP
N7120 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Steering |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5462 | PUMP GP STEER
N2050 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Torque Convertor |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5398 | TORQUE CONVERTER, 793D
N2050 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Torque Convertor |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5398 | TORQUE CONVERTER, 793D
N7647 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Accum Brake Reseal |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 243-5339 | ACCUMULATOR GP-BRAKE
N7041 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Cooling Fan Engine |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5464 | PUMP GP HYD
N7120 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Steering |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5462 | PUMP GP STEER
N3028 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Drive Shaft T/C - Trans |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 11R-1790 | SLIP JOINT GP
N4000 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Bevel Gear |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 11R-1753 | DIFFERENTIAL, 793D
N2052 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Convertor/Trans Pump |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 0R-1035 | PUMP GP GEAR
N7027 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Hoist/Brake Rel/Oil Cool |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 20R-6501 | PUMP GP - GEAR
N7027 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Hoist/Brake Rel/Oil Cool |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 20R-6501 | PUMP GP - GEAR
N3028 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Drive Shaft T/C - Trans |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 11R-1790 | SLIP JOINT GP
N7160 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Axle Lube/Cooler |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 20R-8004 | PUMP GP-GR A
N7160 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Pump Axle Lube/Cooler |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 20R-8004 | PUMP GP-GR A
N8137-R | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Steering Linkage Group RIGHT |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 2A-6946 | LINK GP - STEERING
N4000 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Bevel Gear |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 11R-1753 | DIFFERENTIAL, 793D
N8140 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Steering Y Piece |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 207-7321 | CENTRE ARM, STEERING, 793
N1000 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Engine |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 488-8196 | 793D PEX ENGINE
N8140 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Steering Y Piece |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 207-7321 | CENTRE ARM, STEERING, 793
N7169 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Mtr Axle Lube/Cooler |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5465 | MOTOR GP HYD
N8137-L | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Steering Linkage Group LEFT |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 2A-6946 | LINK GP - STEERING
N6062-F | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5675 | CORE AS OIL
N7169 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Mtr Axle Lube/Cooler |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5465 | MOTOR GP HYD
N6062-F | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5675 | CORE AS OIL
N7232 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Motor Engine Fan |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5466 | MOTOR GP - HYD FAN
N1000 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Engine |  | 82501 | 20000 | 2026-05-04 | 18.5 |  | 62061 | 2022-10-01 |  | 488-8196 | 793D PEX ENGINE
N8137-L | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Steering Linkage Group LEFT |  | 82501 | 20000 | 2026-05-04 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 2A-6946 | LINK GP - STEERING
N7474-R | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Hyd Cyl Hoist RIGHT |  | 59517 | 27000 | 2026-05-05 | 18.5 |  | 32096 | 2019-10-02
N1002 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Engine Valve Adj |  | 67400 | 4000 | 2026-05-05 | 17 | 25/06/2026 | 63011 | 2025-05-26
N7542-L | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Hyd Cyl Steer LEFT |  | 86119 | 20000 | 2026-05-07 | 18.5 |  | 65722 | 2023-02-28 |  | 20R-5304 | STEER CYL
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Uni's Eng - Pump Drive |  | 81805 | 5000 | 2026-05-07 | 18.5 |  | 76420 | 2025-07-07 |  | 390-8908 | SPIDER & BEARING AS
N2002 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Oil Cooler - Transmission |  | 68788 | 20000 | 2026-05-08 | 18.5 | 05/09/2026 | 48413 | 2021-10-13
N8200-04 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Ride Strut POS 4 |  | 52281 | 20000 | 2026-05-09 | 17 |  | 31957 | 2015-10-08 | AWAITING CONFIRMATION | 11R-1040 | CYL, SUSPENSION, REAR, 785
N6030-F | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Brake Slack Adj FRONT |  | 59122 | 16000 | 2026-05-09 | 18.5 | 13/07/2026 | 42772 | 2021-09-26
N0145 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Pivot Shaft Brgs |  | 18065 | 4000 | 2026-05-10 | 13 | 14/08/2026 | 13833.28 | 2025-04-05 | Nearest service
N0111-5R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 5 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-3R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 3 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-8R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 8 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N1002 | WA | CAT | 85 | McPhee Creek | RD6602 | Cat 789D | Engine Valve Adj |  | 4287.2 | 4000 | 2026-05-11 | 11.19 |  | 99 | 2025-06-09
N0111-1L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 1 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0105-RR | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Idler RHT REAR |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 125-3537 | IDLER GP-TRACK
N0105-LR | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Idler LFT REAR |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 125-3537 | IDLER GP-TRACK
N0111-7L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 7 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-6R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 6 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-2R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 2 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-4L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 4 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-7R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 7 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-6L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 6 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N3028 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Drive Shaft T/C - Trans |  | 66446.13 | 20000 | 2026-05-11 | 12.5 |  | 46230.94 | 2018-01-27
N0111-2L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 2 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-3L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 3 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0105-LF | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Idler LFT FRONT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 125-3537 | IDLER GP-TRACK
N0121-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Carrier Roller No 1 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7679 | ROLLER GP-SF
N0111-1R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 1 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-4R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 4 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0121-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Carrier Roller No 1 RIGHT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7679 | ROLLER GP-SF
N0105-RF | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Idler RHT FRONT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 125-3537 | IDLER GP-TRACK
N0111-8L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 8 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0111-5L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Track Roller 5 LEFT |  | 47986 | 8000 | 2026-05-11 | 12 |  | 39778 | 2023-10-28 |  | 309-7678 | ROLLER GP-DF
N0520 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Pre Lube Pump |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 389-8169 | MOTOR GP-ELECTRIC
N0100-R | WA | CAT | 19 | McPhee Creek | DZ3429 | Cat D10 | Track Group RIGHT |  | 4963.4 | 2000 | 2026-05-12 | 7.24 |  | 2849 | 2025-11-23
N7610 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Cooler Core |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 0R-5515 | CORE AS OIL
N5000-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Final Drive LEFT |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 20R-6295 | FINAL DRIVE, D10
N4110-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Steering Clutch/Brk RIGHT |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 10R-9976 | Steering Brake And Clutch
N4110-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Steering Clutch/Brk LEFT |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 10R-9976 | Steering Brake And Clutch
N1312-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Aftercooler Core - RIGHT |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 528-0686 | CORE AS-AFTERCOOLER
N5000-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Final Drive RIGHT |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 20R-6295 | FINAL DRIVE, D10
N7232 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Motor Engine Fan |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 10R-5601 | MOTOR GP
N0100-L | WA | CAT | 19 | McPhee Creek | DZ3429 | Cat D10 | Track Group LEFT |  | 4963.4 | 2000 | 2026-05-12 | 7.24 |  | 2849 | 2025-11-23
N2050 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Torque Convertor |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 10R-5295 | TORQUE CONVERTER, D10
N1000 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Engine |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 10R-7244 | ENGINE AR-BASIC
N3016 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Drv Shaft Fan Pump-Trans Pump |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 211-9087 | COUPLING AS
N9502 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | A/C Condenser |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 103-9527 | CONDENSER GP
N7041 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Pump Cooling Fan Engine |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31467 | 2021-01-30 |  | 10R-5603 | PUMP GP
N1312-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Aftercooler Core - LEFT |  | 46731 | 15000 | 2026-05-12 | 16 |  | 31472 | 2021-01-30 |  | 539-8656 | CORE AS-AFTERCOOLER
N5020-RF | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Wheel Bearing RIGHT FRONT |  | 67106.81 | 15000 | 2026-05-13 | 12.5 | 15/07/2026 | 51920 | 2021-02-07
N5020-LF | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Wheel Bearing LEFT FRONT |  | 67106.81 | 15000 | 2026-05-13 | 12.5 | 15/07/2026 | 51920 | 2021-02-07
N0556 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Air Safety Valve |  | 1713 | 0 | 2026-05-14 | 12 |  | 0
N0556 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Air Safety Valve |  | 4002 | 0 | 2026-05-14 | 12 | 31/05/2026 | 0 | 2025-05-14
N0556 | WA | EPI | 85 | Iron Bridge | DR3153 | Epiroc D65 XLF MKII | Air Safety Valve |  | 1450 | 0 | 2026-05-14 | 12 |  | 0 | 2025-05-14
N1002 | WA | CAT | 85 | Iron Bridge | EX4001 | Cat 374 | Engine Valve Adj |  | 2581 | 2500 | 2026-05-14 | 6 |  | 0 | 2024-02-20
N3021 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Uni's Eng - Pump Drive |  | 23844.2 | 10000 | 2026-05-14 | 13.5 | 15/07/2026 | 13656.89 | 2023-12-08
N1490 | WA | CAT | 85 | McPhee Creek | RD6622 | Cat 777 | Cam Shaft Inspection |  | 1608.3 | 1500 | 2026-05-14 | 8 |  | 0 | 2025-01-08
N1002 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Engine Valve Adj |  | 52281 | 4000 | 2026-05-14 | 17 | 07/06/2026 | 48043 | 2025-05-31
N1000 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Engine |  | 24344.16 | 20000 | 2026-05-15 | 13.5 | 16/06/2026 | 16713.94 | 2024-09-21
N9500 | WA | CAT | 85 |  | GR1550 | Cat 16M | Air Cond'r-Serv |  | 27110.6 | 3500 | 2026-05-15 | 10 |  | 23479 | 2025-01-01
N0201-01 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | A Frame Bearing Reshim Initial |  | 59732.1 | 2000 | 2026-05-16 | 13.75 |  | 57570 | 2025-04-08 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0201-01 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | A Frame Bearing Reshim Initial |  | 59732.1 | 2000 | 2026-05-16 | 13.75 |  | 57570 | 2025-04-08 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1000 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Engine |  | 21508 | 12000 | 2026-05-16 | 12 | 28/05/2026 | 9359 | 2023-04-04
N1490 | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Cam Shaft Inspection |  | 2161 | 2000 | 2026-05-16 | 14 |  | 0 | 2026-02-12 |  | 449-9059 | SEAL
N7340 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 21508 | 6000 | 2026-05-17 | 12 | 28/05/2026 | 15380 | 2024-08-14
N8200-02 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Ride Strut POS 2 |  | 79490 | 30000 | 2026-05-17 | 14 |  | 49336 | 2020-06-03 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N7151 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pump Water Injection (Bean) |  | 21277 | 7500 | 2026-05-17 | 14 |  | 13619 | 2024-02-29 |  | 521-3019 | PUMP GP-WATER
N5020-02 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Wheel Bearing POS 2 |  | 79490 | 30000 | 2026-05-17 | 14 |  | 49336 | 2020-06-03 |  | 446-0367 | KIT
N6000-02 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Brake POS 2 |  | 79490 | 30000 | 2026-05-17 | 14 |  | 49336 | 2020-06-03 |  | 10R-5394 | BRAKE, FRT, 793
N0099 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 20661 | 2000 | 2026-05-17 | 12 | 10/07/2026 | 18526 | 2025-11-06
N7605 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Steering Hmu |  | 54979 | 20000 | 2026-05-17 | 14 | 01/08/2026 | 34829 | 2020-09-15
N8122-02 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Wheel Group POS 2 |  | 79490 | 30000 | 2026-05-17 | 14 |  | 49336 | 2020-06-03 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Brake POS 2 |  | 49506 | 20000 | 2026-05-18 | 14.5 |  | 29360 | 2017-11-14 |  | 311-0517 | BRAKE, FRT, 785C
N8200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Ride Strut POS 2 |  | 49506 | 20000 | 2026-05-18 | 14.5 |  | 29360 | 2017-11-14
N7310-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Rotation RIGHT |  | 14426 | 7500 | 2026-05-18 | 14 | 06/08/2026 | 6785 | 2025-01-23 |  | 11R-0142 | MOTOR GP-PISTON
N0100-L | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Track Group LEFT |  | 52003.6 | 2000 | 2026-05-18 | 12 |  | 49885 | 2025-08-17
N0300-H | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 21508 | 2500 | 2026-05-18 | 12 | 28/05/2026 | 18884 | 2025-10-05
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Wheel Bearing POS 1 |  | 49506 | 20000 | 2026-05-18 | 14.5 |  | 29360 | 2017-11-14 |  | 293-1016 | KIT
N0100-R | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Track Group RIGHT |  | 52003.6 | 2000 | 2026-05-18 | 12 |  | 49885 | 2025-08-17
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Wheel Bearing POS 2 |  | 49506 | 20000 | 2026-05-18 | 14.5 |  | 29360 | 2017-11-14 |  | 293-1016 | KIT
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Wheel Group POS 2 |  | 49506 | 20000 | 2026-05-18 | 14.5 |  | 29360 | 2017-11-14 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N1490 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Cam Shaft Inspection |  | 35745 | 1500 | 2026-05-19 | 15 |  | 34103 | 2026-02-11
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Wheel Bearing POS 1 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 446-0367 | KIT
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Brake POS 2 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 10R-5394 | BRAKE, FRT, 793
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Ride Strut POS 1 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Wheel Group POS 1 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Brake POS 1 |  | 49506 | 20000 | 2026-05-20 | 14.5 |  | 29393 | 2017-11-22 |  | 311-0517 | BRAKE, FRT, 785C
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Wheel Bearing POS 2 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 446-0367 | KIT
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Wheel Group POS 1 |  | 49506 | 20000 | 2026-05-20 | 14.5 |  | 29393 | 2017-11-22 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Brake POS 1 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 10R-5394 | BRAKE, FRT, 793
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Wheel Group POS 2 |  | 86119 | 24000 | 2026-05-20 | 18.5 |  | 61972 | 2022-07-17 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N5020-LF | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Wheel Bearing LEFT FRONT |  | 56902.96 | 15000 | 2026-05-21 | 13.5 | 01/06/2026 | 41814 | 2023-01-17
N5003-04 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Final Drive Ext Life POS 4 |  | 69633 | 25000 | 2026-05-21 | 18.5 | 02/07/2026 | 44498 | 2021-05-03
N5003-04 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Final Drive Ext Life POS 4 |  | 75619 | 20000 | 2026-05-21 | 19 |  | 55489 | 2021-09-29 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Hyd Cyl Steer RIGHT |  | 75619 | 20000 | 2026-05-21 | 19 |  | 55489 | 2021-07-23 |  | 20R-5304 | STEER CYL
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Engine Valve Adj |  | 70515 | 4000 | 2026-05-22 | 19 |  | 66409 | 2025-05-05 |  | 272-0760 | SEAL-VALVE COVER
N7155-01 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L1,2 |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N1312 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Aftercooler Core |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N0325 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Carousel Assembly |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N7155-02 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L3,4 |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N1310 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Radiator |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N7610 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cooler Core |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N0551 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Cooler Aircompressor |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N1301 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Water Pump |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N1000 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Engine |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N7155-03 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L5,6 |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N1100 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Turbo Primary |  | 18065 | 18000 | 2026-05-23 | 13 |  | 0 | 2022-06-01
N1000 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Engine |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20
N2002-F | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Oil Cooler -Transmission FRONT |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20
N7655 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Accumulator Pilot |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20 | PLEASE ADD TO SHUT DOWN - RH
N0556 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Air Safety Valve |  | 21534 | 0 | 2026-05-24 | 12 | 03/07/2026 | 17046 | 2025-05-24
N0520 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pre Lube Pump |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20 | PLEASE ADD TO SHUT DOWN - RH
N3037-RE | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Drive Shft Trans - Bev Gear RE |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20 | PLEASE ADD TO SHUT DOWN - RH
N9500-MA | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Air Cond'r-Serv - MAJOR |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20
N2090 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Drv Coupling |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20
N2100 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Transfer Case |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20 | PLEASE ADD TO SHUT DOWN - RH
N2002-RE | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Oil Cooler -Transmission REAR |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20
N3045-RE | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Drv Shft S/Bearing-Pump Drv RE |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20 | PLEASE ADD TO SHUT DOWN - RH
N3028 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Drive Shaft T/C - Trans |  | 70621 | 24000 | 2026-05-24 | 15 |  | 46560 | 2021-06-20
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Final Drive POS 3 |  | 49506 | 20000 | 2026-05-25 | 14.5 |  | 29465 | 2019-02-24
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Ride Strut POS 3 |  | 49506 | 20000 | 2026-05-25 | 14.5 |  | 29461 | 2017-12-24 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N1490 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Cam Shaft Inspection |  | 45807 | 2000 | 2026-05-25 | 14 |  | 43768 | 2024-11-13 |  | 449-9059 | SEAL
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Oil Cooler - Brakes FRONT |  | 49506 | 20000 | 2026-05-25 | 14.5 |  | 29461 | 2017-12-24 |  | 10R-0817 | CORE GP-O CLR
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Brake Slack Adj REAR |  | 49506 | 20000 | 2026-05-25 | 14.5 |  | 29461 | 2017-12-24 |  | 566-9766 | ADJUSTER GP
N7595 | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Hyd Cyl Mast Lock |  | 2718 | 2000 | 2026-05-25 | 15.2 |  | 677 | 2025-08-14
N1100-RR | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Turbo Primary RHT REAR |  | 82501 | 10000 | 2026-05-26 | 18.5 |  | 72462 | 2024-09-28 |  | 20R-9727 | TURBO GP
N7310-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Rotation LEFT |  | 14426 | 7500 | 2026-05-26 | 14 | 06/08/2026 | 6904 | 2025-03-03 |  | 11R-0141 | MOTOR GP-PISTON
N9501 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | A/C Compressor |  | 14426 | 7500 | 2026-05-26 | 14 | 06/08/2026 | 6904 | 2025-03-03 |  | 629-8454 | COMPRESSOR GP-REFRIGERANT
N1300 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Cooling Sys Service |  | 47986 | 7500 | 2026-05-27 | 12 |  | 40479 | 2024-10-01 |  | 248-5513 | REGULATOR-TEMPERATURE
N1202 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Fuel Transfer Pump |  | 47986 | 7500 | 2026-05-27 | 12 |  | 40479 | 2024-10-01 |  | 20R-0967 | PUMP GP
N9020 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Alternator |  | 47986 | 7500 | 2026-05-27 | 12 |  | 40479 | 2024-10-01 |  | 10R-9789 | ALTERNATOR
N2020 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Powertrain Pump |  | 34679 | 7000 | 2026-05-27 | 14 | 04/07/2026 | 27664 | 2024-10-12 |  | 30R-0153 | PUMP GP-GEAR(POWER TRAIN OIL)
N1100-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Turbo Primary LEFT |  | 47986 | 7500 | 2026-05-27 | 12 | 06/07/2026 | 40479 | 2024-10-01 |  | 10R-2075 | TURBO, D10T, REMAN
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | Operator Seat |  | 59952 | 6000 | 2026-05-27 | 14 |  | 53942 | 2023-09-23 |  | 384-6168 | SEAT GP
N1004 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Engine Midlife |  | 47986 | 7500 | 2026-05-27 | 12 |  | 40479 | 2024-10-01
N1100-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Turbo Primary RIGHT |  | 47986 | 7500 | 2026-05-27 | 12 | 06/07/2026 | 40479 | 2024-10-01 |  | 10R-2075 | TURBO, D10T, REMAN
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Wheel Group POS 2 |  | 67187 | 20000 | 2026-05-29 | 14 |  | 47198 | 2020-05-01 |  | 328-8492 | WHEEL HUB BRK GRP, FRT, 789
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Wheel Bearing POS 2 |  | 67187 | 20000 | 2026-05-29 | 14 |  | 47198 | 2020-05-01 |  | 289-2131 | CONE-SPECIAL TAPERED
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Brake POS 2 |  | 67187 | 20000 | 2026-05-29 | 14 |  | 47198 | 2020-05-01 |  | 257-6301 | BRAKE GROUP
N1002 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Engine Valve Adj |  | 60138 | 4000 | 2026-05-29 | 15 |  | 56154 | 2022-08-18 |  | 272-0760 | SEAL-PIP
N7120 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Pump Steering |  | 67187 | 20000 | 2026-05-29 | 14 |  | 47198 | 2020-04-19 |  | 0R-7656 | REMAN PUMP GP
N1100-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Turbo Primary RHT REAR |  | 58852 | 10000 | 2026-05-30 | 15 |  | 48889 | 2020-10-07 |  | 20R-6651 | RE-MAN TURBO GP
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Uni's Eng - Pump Drive |  | 86119 | 5000 | 2026-05-31 | 18.5 |  | 81169 | 2025-07-19 |  | 390-8908 | SPIDER & BEARING AS
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Ride Strut POS 1 |  | 81805 | 24000 | 2026-05-31 | 18.5 |  | 57863 | 2022-07-17 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Wheel Bearing POS 1 |  | 81805 | 24000 | 2026-05-31 | 18.5 |  | 57863 | 2022-07-17 |  | 446-0367 | KIT
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Brake POS 1 |  | 81805 | 24000 | 2026-05-31 | 18.5 |  | 57863 | 2022-07-17 |  | 10R-5394 | BRAKE, FRT, 793
N3021 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Uni's Eng - Pump Drive |  | 69305 | 10000 | 2026-05-31 | 17 |  | 59355 | 2023-10-01 |  | 230-4110 | JOINT GP, UNI
IN0125HR | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | 125 Hour Inspection |  | 5903.7 | 125 | 2026-05-31 | 7.2 |  | 5803 | 2026-05-21
N1002 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Engine Valve Adj |  | 62083 | 4000 | 2026-05-31 | 18.5 | 20/06/2026 | 58142 | 2025-11-09 | ZX
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Wheel Group POS 1 |  | 81805 | 24000 | 2026-05-31 | 18.5 |  | 57863 | 2022-07-17 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N3029 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Uni's T/C - Trans |  | 69305 | 10000 | 2026-05-31 | 17 |  | 59355 | 2023-10-01 |  | 8R-7036 | SPIDER
N0200 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | A Frame Bearing |  | 58227.56 | 30000 | 2026-05-31 | 12.5 | 01/09/2026 | 28263 | 2017-02-05 | Nearest service
N0111-2R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 2 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-8L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 8 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-1R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 1 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N9500 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Air Cond'r-Serv |  | 10578.3 | 0 | 2026-06-01 | 7.02 |  | 0 | 2025-06-01
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Engine Valve Adj |  | 81805 | 4000 | 2026-06-01 | 18.5 |  | 77883 | 2025-10-02 |  | 272-0760 | SEAL-VALVE COVER
N0111-9R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 9 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N7036 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Pump Drive Gear |  | 5943 | 6000 | 2026-06-01 | 13.79 | 29/09/2026 | 0 | 2025-04-19
N1000 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Engine |  | 22440 | 12000 | 2026-06-01 | 12 | 18/06/2026 | 10491 | 2023-08-14
N0111-6R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 6 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N7627 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Valve Track Oscillation |  | 22440 | 12000 | 2026-06-01 | 12 | 18/06/2026 | 10491 | 2023-08-14
N7597 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Hyd Cyl Boom Swing |  | 22440 | 12000 | 2026-06-01 | 12 | 18/06/2026 | 10491 | 2023-08-11
N7008-02 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Pump Hydraulic POS 2 |  | 22440 | 12000 | 2026-06-01 | 12 | 18/06/2026 | 10491 | 2023-08-14
N0111-4L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 4 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-7L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 7 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-8R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 8 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N7008-01 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Pump Hydraulic POS 1 |  | 22440 | 12000 | 2026-06-01 | 12 | 18/06/2026 | 10491 | 2023-08-14
N0201-01 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | A Frame Bearing Reshim Initial |  | 65021 | 2000 | 2026-06-01 | 8.5 |  | 63059 | 2025-06-28 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N7583 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Hyd Cyl Breakout Wrench Break |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-6L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 6 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-5R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 5 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-9L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 9 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-7R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 7 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-2L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 2 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-5L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 5 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-3R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 3 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-3L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 3 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | A Frame Bearing Reshim Initial |  | 57576 | 2000 | 2026-06-01 | 14 |  | 55626 | 2024-05-15
N0111-1L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 1 LEFT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N0111-4R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Roller 4 RIGHT |  | 5943 | 6000 | 2026-06-01 | 13.79 |  | 0 | 2025-04-19
N1310 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Radiator |  | 22440 | 12000 | 2026-06-01 | 12 | 18/06/2026 | 10491 | 2023-08-15
N0104-L | WA | CAT | 19 | McPhee Creek | DZ3429 | Cat D10 | Sprockets LEFT |  | 4963.4 | 5000 | 2026-06-02 | 7.24 |  | 0 | 2025-04-01
N0104-R | WA | CAT | 19 | McPhee Creek | DZ3429 | Cat D10 | Sprockets RIGHT |  | 4963.4 | 5000 | 2026-06-02 | 7.24 |  | 0 | 2025-04-01
N0104-R | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Sprockets RIGHT |  | 46895 | 6000 | 2026-06-03 | 13.5 |  | 40981 | 2024-09-23 |  | 433-6739 | 7796592
N8432 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Trunnion Axle Bearings REAR |  | 57859 | 10000 | 2026-06-04 | 16 |  | 47965 | 2022-10-10
N6200-LR | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Press Converter LEFT REAR |  | 56902.96 | 15000 | 2026-06-04 | 13.5 | 01/06/2026 | 41997 | 2023-02-02
N8995 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Operator Seat |  | 23756 | 6000 | 2026-06-04 | 18.5 | 11/06/2026 | 17891 | 2025-06-20
N6200-RR | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Press Converter RIGHT REAR |  | 56902.96 | 15000 | 2026-06-04 | 13.5 | 01/06/2026 | 41997 | 2023-02-02
N7077-05 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Pump Imp 7&8 |  | 23756 | 15000 | 2026-06-04 | 18.5 | 11/06/2026 | 8877 | 2023-12-11
N1490 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 14426 | 2000 | 2026-06-05 | 14 |  | 12531 | 2026-01-19 |  | 449-9059 | SEAL
N2445 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Drv Coupling Compressor |  | 34291 | 7500 | 2026-06-05 | 13.79 | 20/05/2026 | 26903 | 2023-11-17
N1402 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Fan Pulley Brgs |  | 42291 | 10000 | 2026-06-05 | 10 | 04/06/2026 | 32369 | 2021-11-08
N1403 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Jockey Pulley Brgs |  | 42291 | 10000 | 2026-06-05 | 10 | 04/06/2026 | 32369 | 2021-11-08
N9500 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Air Cond'r-Serv |  | 49898.9 | 4000 | 2026-06-05 | 10 | 16/04/2026 | 45978 | 2025-03-23
N0111-3R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 3 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N1002 | WA | CAT | 85 | McPhee Creek | RD6612 | Cat 789D | Engine Valve Adj |  | 3903.15 | 4000 | 2026-06-06 | 11.19 |  | 0 | 2024-05-21
N0111-5L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 5 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-1L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 1 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-3L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 3 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-2R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 2 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0105-LF | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Idler LFT FRONT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 125-3537 | IDLER GP-TRACK
N0111-1R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 1 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N7420-R | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Hyd Cyl Blade Lift RIGHT |  | 26541 | 16000 | 2026-06-06 | 12.5 |  | 10657 | 2021-08-06 |  | 389-9512 | BLADE LIFT CYLINDER
N0121-L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Carrier Roller No 1 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7679 | ROLLER GP-SF
N8137-R | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Steering Linkage Group RIGHT |  | 77195 | 20000 | 2026-06-06 | 14 |  | 57323 | 2022-04-17 |  | 2A-6946 | LINK GP - STEERING
N0105-LR | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Idler LFT REAR |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 125-3537 | IDLER GP-TRACK
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | A Frame Bearing Reshim Initial |  | 44852.3 | 2000 | 2026-06-06 | 15 |  | 42983.1 | 2023-05-16 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | A Frame Bearing Reshim Initial |  | 44852.3 | 2000 | 2026-06-06 | 15 |  | 42983.1 | 2023-05-16 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0111-8R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 8 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N8140 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Steering Y Piece |  | 77195 | 20000 | 2026-06-06 | 14 |  | 57323 | 2022-04-17 |  | 207-7321 | CENTRE ARM, STEERING, 793
N0111-7L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 7 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-5R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 5 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0105-RF | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Idler RHT FRONT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 125-3537 | IDLER GP-TRACK
N0111-4R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 4 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-8L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 8 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 4 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0111-7R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 7 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0105-RR | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Idler RHT REAR |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 125-3537 | IDLER GP-TRACK
N0111-2L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 2 LEFT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N8137-L | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Steering Linkage Group LEFT |  | 77195 | 20000 | 2026-06-06 | 14 |  | 57323 | 2022-04-17 |  | 2A-6946 | LINK GP - STEERING
N0111-6R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Track Roller 6 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7678 | ROLLER GP-DF
N0121-R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Carrier Roller No 1 RIGHT |  | 23174 | 8000 | 2026-06-06 | 14 |  | 15305 |  |  | 309-7679 | ROLLER GP-SF
N9500 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 8398 | 3000 | 2026-06-06 | 12 | 26/05/2026 | 5511 | 2025-09-03
N8995 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Operator Seat |  | 34192 | 6000 | 2026-06-07 | 12 | 16/07/2026 | 28311 | 2025-04-02
N1002 | WA | CAT | 85 | McPhee Creek | LO6670 | Cat 854K | Engine Valve Adj |  | 2912.8 | 3000 | 2026-06-07 | 8.97 |  | 0
N7330-RF | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Motor Travel RHT FRONT |  | 55435 | 12000 | 2026-06-07 | 18.5 | 24/08/2026 | 43626 | 2023-11-10
N9500 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Air Cond'r-Serv |  | 37630 | 4000 | 2026-06-07 | 12 |  | 33750 | 2021-07-30
N7169 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Hyd Mtr Axle Lube/Cooler |  | 62083 | 24000 | 2026-06-08 | 18.5 | 13/08/2026 | 38283 | 2020-10-26
N7600-FR | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Control Valve FRONT |  | 37630 | 16000 | 2026-06-08 | 12 |  | 21761 | 2018-11-27
N7160 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Pump Axle Lube/Cooler |  | 62083 | 24000 | 2026-06-08 | 18.5 | 13/08/2026 | 38283 | 2020-10-26
N7600-S | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Control Valve - STEERING |  | 37630 | 16000 | 2026-06-08 | 12 |  | 21761 | 2018-11-27
N7605 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Steering Hmu |  | 62083 | 24000 | 2026-06-08 | 18.5 | 13/08/2026 | 38283 | 2020-10-26
N1490 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Cam Shaft Inspection |  | 55934 | 2000 | 2026-06-08 | 13.5 |  | 54081 | 2025-10-21 |  | 449-9059 | SEAL
N7600-RE | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Control Valve REAR |  | 37630 | 16000 | 2026-06-08 | 12 |  | 21761 | 2018-11-27
N9050-UP | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Starter Motor UPPER |  | 52281 | 10000 | 2026-06-08 | 17 |  | 42474 | 2023-10-01 |  | 10R-9816 | REMAN STARTER MOTOR
N1310 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Radiator |  | 34291 | 15000 | 2026-06-09 | 13.79 |  | 19459 | 2022-07-01
N1312 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Aftercooler Core |  | 34291 | 15000 | 2026-06-09 | 13.79 |  | 19459 | 2022-07-01
N7610 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cooler Core |  | 34291 | 15000 | 2026-06-09 | 13.79 |  | 19459 | 2022-07-01
N1002 | WA | CAT | 85 | McPhee Creek | RD6609 | Cat 789D | Engine Valve Adj |  | 3871 | 4000 | 2026-06-09 | 11.19 |  | 0 | 2024-05-21
N0111-1L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 1 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Turbo Primary LEFT |  | 52309.6 | 10000 | 2026-06-10 | 13 | 02/04/2026 | 42482 | 2021-01-01 |  | 20R-3423 | TURBO GRP
N0111-4R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 4 RIGHT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0111-8R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 8 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-2R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 2 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0102-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 46731 | 3000 | 2026-06-10 | 16 |  | 43942 | 2024-05-19
N0111-6L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 6 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-8L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 8 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0162-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Accumulator RIGHT |  | 23756 | 24000 | 2026-06-10 | 18.5 | 04/09/2026 | 0
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Turbo Primary RIGHT |  | 52309.6 | 10000 | 2026-06-10 | 13 | 02/04/2026 | 42482 | 2021-01-01 |  | 20R-3423 | TURBO GRP
N0121-R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Carrier Roller No 1 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0121-L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Carrier Roller No 1 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-3L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 3 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-5L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 5 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N1100 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Turbo Primary |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0551 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Cooler Aircompressor |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0111-6R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 6 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N1000 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Engine |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N7151 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Pump Water Injection (Bean) |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N7032 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Pump Cooler Fan Hyd |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N7155-02 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L3,4 |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0111-3R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 3 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0325 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Carousel Assembly |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N7155-01 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L1,2 |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0162-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Accumulator LEFT |  | 23756 | 24000 | 2026-06-10 | 18.5 | 04/09/2026 | 0
N0111-3R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 3 RIGHT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N1310 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Radiator |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0111-2L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 2 LEFT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N1301 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Water Pump |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0111-1R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 1 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-4L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 4 LEFT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0111-5R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 5 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-2L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 2 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-3L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 3 LEFT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0111-6L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 6 LEFT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0111-4L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 4 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N7155-03 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Pump Main L5,6 |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N1312 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Aftercooler Core |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0102-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 46731 | 3000 | 2026-06-10 | 16 |  | 43942 | 2024-05-19
N1004 | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Engine Midlife |  | 5903.7 | 6000 | 2026-06-10 | 7.2 | 12/08/2026 | 0 | 2025-01-08 | 46261
N0111-5L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 5 LEFT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N7610 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Hyd Cooler Core |  | 17835 | 18000 | 2026-06-10 | 13 |  | 0 | 2022-06-01
N0111-5R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 5 RIGHT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0111-4R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 4 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-7L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 7 LEFT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-6R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 6 RIGHT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0111-7R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Roller 7 RIGHT |  | 34410.8 | 10000 | 2026-06-10 | 6.35 |  | 24492.81 | 2022-07-09
N0111-2R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 2 RIGHT |  | 23756 | 24000 | 2026-06-10 | 18.5 |  | 0
N0145 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Pivot Shaft Brgs |  | 7751 | 4000 | 2026-06-11 | 9.59 | 01/08/2026 | 3885 | 2025-06-11 | Nearest service to
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Final Drive POS 3 |  | 64653 | 20000 | 2026-06-11 | 14 |  | 49595 | 2021-03-17 |  | 0R-9043 | FINAL DRIVE 789C
N8995 | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Operator Seat |  | 9782 | 10000 | 2026-06-11 | 16 |  | 0 | 2025-06-20
N9500 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Air Cond'r-Serv |  | 65303 | 4000 | 2026-06-11 | 18.5 | 12/08/2026 | 61567 | 2025-10-07
N9500 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 22440 | 3000 | 2026-06-11 | 12 | 18/06/2026 | 19610 | 2025-09-20
N9500 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv |  | 7751 | 0 | 2026-06-11 | 9.59 |  | 0 | 2025-06-11
N0100-L | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Track Group LEFT |  | 43005.2 | 1700 | 2026-06-12 | 6.35 |  | 41400 | 2025-10-08
N7310-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Hyd Motor Rotation RIGHT |  | 16307 | 7500 | 2026-06-12 | 14 | 29/06/2026 | 9022 | 2025-03-10 |  | 11R-0142 | MOTOR GP-PISTON
N7310-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Hyd Motor Rotation LEFT |  | 16307 | 7500 | 2026-06-12 | 14 | 29/06/2026 | 9022 | 2025-03-10 |  | 11R-0141 | MOTOR GP-PISTON
N0100-R | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Track Group RIGHT |  | 43005.2 | 1700 | 2026-06-12 | 6.35 |  | 41400 | 2025-10-08
N1490 | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Cam Shaft Inspection |  | 2718 | 1500 | 2026-06-12 | 15.2 |  | 1451 | 2025-11-15
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Steering Ball Studs POS 8 |  | 62083 | 12000 | 2026-06-13 | 18.5 |  | 50386 | 2024-09-18
N8442-05 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Steering Ball Studs POS 5 |  | 62083 | 12000 | 2026-06-13 | 18.5 |  | 50386 | 2024-09-18
N3029 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Uni's T/C - Trans |  | 47029 | 10000 | 2026-06-13 | 4.12 |  | 37093.96 | 2011-12-16
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4235 | Cat 789C | Air Cond'r-Serv |  | 63637 | 5000 | 2026-06-13 | 14 |  | 58860 | 2023-05-10
N8442-07 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Steering Ball Studs POS 7 |  | 62083 | 12000 | 2026-06-13 | 18.5 |  | 50386 | 2024-09-18
N8442-06 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Steering Ball Studs POS 6 |  | 62083 | 12000 | 2026-06-13 | 18.5 |  | 50386 | 2024-09-18
N1490 | WA | CAT | 85 | McPhee Creek | RD6621 | Cat 777 | Cam Shaft Inspection |  | 1431.1 | 1500 | 2026-06-14 | 3.95 |  | 0 | 2025-01-08
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | A Frame Bearing Reshim Initial |  | 86119 | 2000 | 2026-06-14 | 18.5 |  | 84439 | 2026-02-04 |  | 8X-2934 | SHIM PACK
N1004 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Engine Midlife |  | 46731 | 7500 | 2026-06-15 | 16 |  | 39522 | 2023-06-23
N0122-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Carrier Roller No 2 LEFT |  | 23756 | 12000 | 2026-06-15 | 18.5 |  | 12088 | 2024-07-23
IN0125HR | WA | CAT | 85 | McPhee Creek | DZ6660 | Cat D10T2 | 125 Hour Inspection |  | 5222.3 | 125 | 2026-06-15 | 7.2 |  | 5225 | 2026-03-31
N1100-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Turbo Primary LEFT |  | 46731 | 7500 | 2026-06-15 | 16 |  | 39522 | 2023-06-23 |  | 10R-2075 | TURBO, D10T, REMAN
N9050 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Starter Motor |  | 46731 | 7500 | 2026-06-15 | 16 |  | 39522 | 2023-06-23 |  | 10R-9816 | MOTOR GP-ELEC
N8061 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Slew Ring Bolts Check |  | 55435 | 5000 | 2026-06-15 | 18.5 |  | 50766 | 2025-08-19
N1100-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Turbo Primary RIGHT |  | 46731 | 7500 | 2026-06-15 | 16 |  | 39522 | 2023-06-23 |  | 10R-2075 | TURBO, D10T, REMAN
N1300 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Cooling Sys Service |  | 46731 | 7500 | 2026-06-15 | 16 |  | 39522 | 2023-06-23 |  | 248-5513 | REGULATOR-TEMPERATURE
N7035 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Pump Hoist, Brk Charge/Cooling |  | 71898 | 18000 | 2026-06-15 | 18.5 | 04/06/2026 | 54228 | 2023-02-10
N2450 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Drv Cpling Fan Pump-Trans Pump |  | 46731 | 7500 | 2026-06-15 | 16 |  | 39522 | 2023-06-23 |  | 211-9087 | COUPLING AS
N0111-5R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 5 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-4R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 4 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 4 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-7L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 7 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0105-RF | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Idler RHT FRONT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 125-3537 | IDLER GP-TRACK
N0111-2R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 2 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-7R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 7 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-2L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 2 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-3L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 3 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-6R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 6 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0111-3R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 3 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0105-RR | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Idler RHT REAR |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 125-3537 | IDLER GP-TRACK
N0111-1L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 1 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0121-R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Carrier Roller No 1 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7679 | ROLLER GP-SF
N0111-8L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 8 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N0105-LR | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Idler LFT REAR |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 125-3537 | IDLER GP-TRACK
N0121-L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Carrier Roller No 1 LEFT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7679 | ROLLER GP-SF
N7605 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Steering Hmu |  | 23844.2 | 12000 | 2026-06-16 | 13.5 | 15/07/2026 | 12105.11 | 2023-07-31
N0111-1R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Track Roller 1 RIGHT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 309-7678 | ROLLER GP-DF
N3340 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Rotary Head |  | 34291 | 4000 | 2026-06-16 | 13.79 | 20/05/2026 | 30556.35 | 2025-09-04
N0105-LF | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Idler LFT FRONT |  | 50673 | 8000 | 2026-06-16 | 14 |  | 42942 | 2023-12-01 |  | 125-3537 | IDLER GP-TRACK
N1202 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Fuel Transfer Pump |  | 46731 | 7500 | 2026-06-16 | 16 |  | 39528 | 2023-06-22 |  | 20R-0967 | PUMP GP
N1490 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Cam Shaft Inspection |  | 49963 | 2000 | 2026-06-17 | 5.5 |  | 48071 | 2025-03-01 |  | 449-9059 | SEAL
N6200-F | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Press Converter FRONT |  | 53598.82 | 15000 | 2026-06-18 | 13.5 |  | 38886.1 | 2023-01-20
N6200-LR | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Press Converter LEFT REAR |  | 53598.82 | 15000 | 2026-06-18 | 13.5 |  | 38886.1 | 2023-01-20
N0550 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Air End |  | 21508 | 12000 | 2026-06-18 | 12 | 28/05/2026 | 9757 | 2023-05-15
N0300-H | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 22613 | 2500 | 2026-06-19 | 12 | 18/06/2026 | 20379 | 2025-06-15
N9500 | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Air Cond'r-Serv |  | 9782 | 0 | 2026-06-20 | 16 |  | 0 | 2025-06-20
N9500 | WA | CAT | 19 | McPhee Creek | DZ3429 | Cat D10 | Air Cond'r-Serv |  | 4963.4 | 0 | 2026-06-20 | 7.24 |  | 993.89 | 2025-06-20
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | Air Cond'r-Serv |  | 55805 | 5000 | 2026-06-20 | 14 |  | 51122 | 2022-08-18
N1002 | WA | CAT | 85 | McPhee Creek | RD6651 | Cat 777 | Engine Valve Adj |  | 2803.3 | 3000 | 2026-06-20 | 8.55 |  | 0 | 2024-05-21
N7021 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Pump Brake Cooling |  | 68788 | 22000 | 2026-06-21 | 18.5 | 05/09/2026 | 47223 | 2021-07-18
N1002 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Engine Valve Adj |  | 64591.2 | 4000 | 2026-06-21 | 13.75 |  | 60924 | 2025-05-24
N1002 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Engine Valve Adj |  | 64591.2 | 4000 | 2026-06-21 | 13.75 |  | 60924 | 2025-05-24
N1490 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 1658 | 2000 | 2026-06-21 | 14 |  | 0 | 2024-11-12 |  | 449-9059 | SEAL
N0099 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 1713 | 2000 | 2026-06-21 | 12 |  | 0
N0111-2R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 2 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N4000 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Bevel Gear |  | 54979 | 20000 | 2026-06-22 | 14 | 01/08/2026 | 35327 | 2017-08-01
N0111-1R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 1 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-4R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 4 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-8L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 8 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-9R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 9 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-7L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 7 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-5R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 5 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-1L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 1 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-3L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 3 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-2L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 2 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N7583 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Hyd Cyl Breakout Wrench Break |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-9L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 9 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-4L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 4 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N7036 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Pump Drive Gear |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-6R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 6 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-5L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 5 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-8R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 8 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-6L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 6 LEFT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N7657-L | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Hyd Accum Steering LEFT |  | 54979 | 20000 | 2026-06-22 | 14 |  | 35327 | 2017-08-01 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N0111-7R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 7 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N0111-3R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Roller 3 RIGHT |  | 5650 | 6000 | 2026-06-22 | 13.79 |  | 0 | 2025-04-01
N7655 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Accumulator Pilot |  | 44396 | 24000 | 2026-06-22 | 15 |  | 20768 | 2021-10-24
N7657-R | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Hyd Accum Steering RIGHT |  | 54979 | 20000 | 2026-06-22 | 14 |  | 35327 | 2017-08-01 |  | 627-1041 | HYDRAULIC ACCUMULATOR
N8995 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Operator Seat |  | 21534 | 6000 | 2026-06-23 | 12 | 03/07/2026 | 15846 | 2024-12-15
N3341 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 21534 | 6000 | 2026-06-23 | 12 | 03/07/2026 | 15846 | 2025-01-16
N0350 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 21534 | 6000 | 2026-06-23 | 12 | 03/07/2026 | 15846 | 2024-12-05
N2090 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Drv Coupling |  | 21534 | 6000 | 2026-06-23 | 12 | 10/09/2026 | 15846 | 2024-11-21
N8137-L | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Steering Linkage Group LEFT |  | 78363 | 20000 | 2026-06-23 | 14 |  | 58728 | 2022-07-27 |  | 2A-6946 | LINK GP - STEERING
N7232 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Motor Engine Fan |  | 21534 | 6000 | 2026-06-23 | 12 | 10/09/2026 | 15846 | 2024-12-05
N0302 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Feed Sprocket |  | 21534 | 6000 | 2026-06-23 | 12 | 19/06/2026 | 15846 | 2024-12-05
N8137-R | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Steering Linkage Group RIGHT |  | 78363 | 20000 | 2026-06-23 | 14 |  | 58728 | 2022-07-27 |  | 2A-6946 | LINK GP - STEERING
N0346 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 21534 | 6000 | 2026-06-23 | 12 | 14/08/2026 | 15846 | 2024-12-05
N0558 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Air End Coupling |  | 21534 | 6000 | 2026-06-23 | 12 | 19/06/2026 | 15846 | 2024-12-11
N0596 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 21534 | 6000 | 2026-06-23 | 12 | 19/06/2026 | 15846 | 2024-12-19
N0597 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 21534 | 6000 | 2026-06-23 | 12 | 19/06/2026 | 15846 | 2024-12-05
N7340 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 21534 | 6000 | 2026-06-23 | 12 | 03/07/2026 | 15846 | 2024-12-20
N1310-E1 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Radiator EN1 |  | 55435 | 16000 | 2026-06-24 | 18.5 |  | 39933 | 2022-10-15
N2050 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Torque Convertor |  | 78345 | 20000 | 2026-06-24 | 14 | 07/05/2026 | 58728 | 2022-07-27 |  | 10R-5398 | TORQUE CONVERTER, 793D
N3220-LF | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Swing Box LFT FRONT |  | 55435 | 16000 | 2026-06-24 | 18.5 | 24/08/2026 | 39933 | 2022-10-15
N9500 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 16307 | 4000 | 2026-06-24 | 14 | 29/06/2026 | 12684 | 2025-09-22
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Brake Slack Adj REAR |  | 59122 | 16000 | 2026-06-25 | 18.5 | 13/07/2026 | 43649 | 2021-11-24
N8432 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Trunnion Axle Bearings REAR |  | 44396 | 12000 | 2026-06-25 | 15 |  | 32821 | 2024-04-25
N1490 | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Cam Shaft Inspection |  | 53910 | 2000 | 2026-06-26 | 12 |  | 52257 | 2025-08-08 |  | 449-9059 | SEAL
N9501 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | A/C Compressor |  | 7661 | 6000 | 2026-06-27 | 12 | 13/12/2025 | 2024 | 2025-01-14
N4000 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Bevel Gear |  | 67600 | 20000 | 2026-06-28 | 17 | 15/08/2026 | 48119 | 2019-03-09 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 21508 | 3000 | 2026-06-28 | 12 | 28/05/2026 | 18884 | 2025-10-05
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Air Cond'r-Serv |  | 64732.59 | 0 | 2026-06-28 | 12.5 |  | 0 | 2025-06-28
N8122-01 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Wheel Group POS 1 |  | 67600 | 20000 | 2026-06-28 | 17 | 15/08/2026 | 48119 | 2019-03-09 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N7041 | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Cooling Fan Engine |  | 35037 | 12000 | 2026-06-28 | 11 | 19/10/2026 | 23376 | 2023-10-24 | THIESS MANAGED
N6350 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Brake Relay Valves |  | 79044 | 12000 | 2026-06-28 | 14 |  | 67482 | 2024-02-12 |  | 159-5149 | BRAKE RELAY VALVE
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | A Frame Bearing Reshim Initial |  | 81805 | 2000 | 2026-06-28 | 18.5 |  | 80385 | 2026-02-19 |  | 8X-2934 | SHIM PACK
N0162-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Accumulator LEFT |  | 23402 | 24000 | 2026-06-29 | 18.5 | 12/10/2026 | 0
N0111-5L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 5 LEFT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-2R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 2 RIGHT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-2L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 2 LEFT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-3L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 3 LEFT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-6L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 6 LEFT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-4L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 4 LEFT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-3R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 3 RIGHT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N9500 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Air Cond'r-Serv |  | 54781 | 5000 | 2026-06-29 | 15 |  | 50263 | 2023-06-10
N0111-4R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 4 RIGHT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0111-5R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 5 RIGHT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Brake Slack Adj REAR |  | 59517 | 16000 | 2026-06-29 | 18.5 | 18/08/2026 | 44102 | 2021-11-28
N0111-6R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Roller 6 RIGHT |  | 23402 | 24000 | 2026-06-29 | 18.5 |  | 0
N0162-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Track Accumulator RIGHT |  | 23402 | 24000 | 2026-06-29 | 18.5 | 12/10/2026 | 0
N1300 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Cooling Sys Service |  | 82501 | 10000 | 2026-06-30 | 18.5 |  | 73111 | 2024-11-02 |  | 418-4162 | REGULATOR-TEMPERATURE
N7041-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Pump Cooling Fan Eng EN2 |  | 23756 | 15000 | 2026-06-30 | 18.5 | 11/06/2026 | 9367 | 2024-01-14
N1400 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Belt Tensioner Assembly |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-30 |  | 336-4953 | TENSIONER,BELT
N3023 | SA | CAT | 01 | Prominent Hill | LO1543 | Cat 994D | Uni's Pump Drive - Pump Drive |  | 75270 | 10000 | 2026-07-01 | 6.5 |  | 65490 | 2022-02-21
N9020 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Alternator |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-29 |  | 10R-9789 | ALTERNATOR GP -B
N0112-3L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Track Roller 13 LEFT |  | 17257 | 15000 | 2026-07-01 | 14 |  | 2726 | 2022-12-25 |  | 528-2933 | ROLLER
N9500 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Air Cond'r-Serv |  | 24344.16 | 0 | 2026-07-01 | 13.5 |  | 0 | 2025-07-01
N0300 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Feed Chain |  | 5943 | 2000 | 2026-07-01 | 13.79 | 29/09/2026 | 4416 | 2026-02-13
N1100-RF | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Turbo Primary RHT FRONT |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-30 |  | 20R-9727 | TURBO GP
N0300-C | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Feed Chain CENTRE |  | 5943 | 2000 | 2026-07-01 | 13.79 | 29/09/2026 | 4416 | 2026-02-13
N6200-03 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 3 |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-30 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-04 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 4 |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-30 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-03 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 3 |  | 82501 | 10000 | 2026-07-01 | 18.5 | 06/08/2026 | 73121 | 2024-10-30 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N1202 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Fuel Transfer Pump |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-31 |  | 10R-8721 | PUMP GP FUEL
N6200-04 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 4 |  | 82501 | 10000 | 2026-07-01 | 18.5 | 06/08/2026 | 73121 | 2024-10-30 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N1100-LF | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Turbo Primary LFT FRONT |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-30 |  | 20R-9727 | TURBO GP
N1100-LR | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Turbo Primary LFT REAR |  | 82501 | 10000 | 2026-07-01 | 18.5 |  | 73121 | 2024-10-30 |  | 20R-9727 | TURBO GP
N1002 | WA | CAT | 85 | McPhee Creek | RD6610 | Cat 789D | Engine Valve Adj |  | 3606.6 | 4000 | 2026-07-02 | 11.19 |  | 0 | 2024-05-21
N2020 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Powertrain Pump |  | 31311 | 7000 | 2026-07-02 | 14 | 27/08/2026 | 24807 | 2025-02-11 |  | 30R-0153 | PUMP GP-GEAR(POWER TRAIN OIL)
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 41713 | 20000 | 2026-07-03 | 15 |  | 22248 | 2014-04-23 |  | 322-7212 | BLOWER,ASSY
N6200-RR | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Press Converter RIGHT REAR |  | 63459.48 | 15000 | 2026-07-03 | 13.5 | 08/09/2026 | 48948.96 | 2023-03-31
N8200-02 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Ride Strut POS 2 |  | 69200 | 22000 | 2026-07-03 | 18.5 | 28/05/2026 | 47868 | 2022-01-07
N4000 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Bevel Gear |  | 41713 | 20000 | 2026-07-03 | 15 |  | 22248
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Engine |  | 41713 | 20000 | 2026-07-03 | 15 |  | 22248
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Torque Convertor |  | 41713 | 20000 | 2026-07-03 | 15 |  | 22248
N2000 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Transmission |  | 41713 | 20000 | 2026-07-03 | 15 |  | 22248 |  |  | 0R-4007 | TRANSMISSION, 789B 785C
N8122-02 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Wheel Group POS 2 |  | 69200 | 22000 | 2026-07-03 | 18.5 | 28/05/2026 | 47868 | 2022-01-07
N1002 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Engine Valve Adj |  | 46895 | 4000 | 2026-07-04 | 13.5 |  | 43401 | 2025-04-02 |  | 449-9059 | SEAL
N2090 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Drv Coupling |  | 12951 | 5000 | 2026-07-04 | 14 | 15/08/2026 | 8474 | 2025-06-22 |  | 520-7010 | COUPLING GP-
N6200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Press Convertor POS 1 |  | 81805 | 12000 | 2026-07-05 | 18.5 |  | 70513 | 2024-07-14 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Press Convertor POS 2 |  | 81805 | 12000 | 2026-07-05 | 18.5 |  | 70513 | 2024-07-14 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N1002 | WA | CAT | 85 | McPhee Creek | LO6631 | Cat 972 | Engine Valve Adj |  | 2188.6 | 2500 | 2026-07-05 | 8.21 |  | 0 | 2025-01-19
N0103-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Plates RIGHT |  | 46731 | 1000 | 2026-07-05 | 16 |  | 46344 | 2024-11-01
N0103-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Plates LEFT |  | 46731 | 1000 | 2026-07-05 | 16 |  | 46344 | 2024-11-01
N8127-F | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Axle Assembly FRONT |  | 26541 | 12000 | 2026-07-06 | 12.5 | 10/09/2026 | 15034 | 2022-10-02
N9500 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Air Cond'r-Serv |  | 17737.5 | 0 | 2026-07-07 | 6.35 | 01/09/2026 | 0 | 2025-07-07
N1002 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Engine Valve Adj |  | 47986 | 4000 | 2026-07-07 | 12 |  | 44465 | 2025-08-09 |  | 449-9059 | SEAL
N0555-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooler Fan Brgs EN1 |  | 23402 | 15000 | 2026-07-08 | 18.5 | 20/07/2026 | 9161 | 2023-11-03
N1000 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Engine |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 5875935X | EXCHANGE ENGINE
N2002 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Oil Cooler - Transmission |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N1312-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Aftercooler Core - LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 523-8685 | CORE AS-AFTC
N1312-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Aftercooler Core - RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 523-8685 | CORE AS-AFTC
N1320 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Cooling Fan Engine |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 392-4160 | SPIDER-AS-FAN
N5000-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Final Drive LEFT |  | 47986 | 15000 | 2026-07-08 | 12 | 06/07/2026 | 33474 | 2021-08-19 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-6295 | FINAL DRIVE, D10
N2050 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Torque Convertor |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N0550 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Air End |  | 20661 | 12000 | 2026-07-08 | 12 | 10/09/2026 | 9151 | 2023-05-30
N3320 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Drive Box |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 503-7615 | PUMP DRIVE,MD6310
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Air Cond'r-Serv |  | 66446.13 | 0 | 2026-07-08 | 12.5 |  | 0 | 2025-07-08
N0134-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Adjuster LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N3340 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Rotary Head |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 527-5344 | ROTARY HEAD, MD6310
N0130-R | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Frame RIGHT |  | 17737.5 | 18000 | 2026-07-08 | 6.35 |  | 0 | 2022-06-01
N7232-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Motor Engine Fan EN1 |  | 23402 | 15000 | 2026-07-08 | 18.5 | 10/08/2026 | 9161 | 2023-11-03
N0033-SC | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Water Tank - SECONDARY |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0
N0134-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Adjuster RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0033-PR | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Water Tank - PRIMARY |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0
N0140 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Equalizer Bar |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 526-3821 | BAR AS-EQUAL
N7600-LW | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Control Valve LOWER |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 517-7952 | VALVE GP-CONTROL
N7600-LL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Control Valve LEFT LOWER |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 517-7954 | VALVE GP-CONTROL
N0123-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Carrier Roller No 3 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0551 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Cooler Aircompressor |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-1356+527-8222 | CORE AS-OIL COOLER
N0130-L | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Track Frame LEFT |  | 17737.5 | 18000 | 2026-07-08 | 6.35 |  | 0 | 2022-06-01
N7608 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Control Valve Jack/Mast Raise |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 514-2137 | VALVE GP-CONTROL
N7669 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Rod Catcher |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6798 | CYLINDER GP HYD
N9500 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Air Cond'r-Serv |  | 82501 | 5000 | 2026-07-08 | 18.5 |  | 78251 | 2025-08-09 |  | 385-0244 | MOTOR AS-BLOWER
N8995 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Operator Seat |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 489-6525+436-8490 | SEAT GP
N0123-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Carrier Roller No 3 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7600-LU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Control Valve LEFT UPPER |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 517-7953 | VALVE GP-CONTROL
N0122-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Carrier Roller No 2 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N5000-04 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Final Drive POS 4 |  | 45967 | 16000 | 2026-07-08 | 12 | 20/07/2026 | 30462 | 2018-10-16 |  | 217-6290 | FINAL DRIVE, POS 1,2,3&4
N4110-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Steering Clutch/Brk LEFT |  | 47986 | 15000 | 2026-07-08 | 12 | 06/07/2026 | 33474 | 2021-08-19 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 10R-9976 | Steering Brake And Clutch
N0550 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Air End |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 541-8633 | COMPRESSOR G
N7598-UP | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing UPPER |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 539-1901 | CYL GP-127 1
N0122-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Carrier Roller No 2 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N5000-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Final Drive LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N0111-6L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 6 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N1310 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Radiator |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N0111-6R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 6 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-7L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 7 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-7R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 7 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7467-RU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension RU |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N7041 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Cooling Fan Engine |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 11R-1030 | PUMP GP-PISTON
N2020 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Powertrain Pump |  | 47986 | 15000 | 2026-07-08 | 12 | 06/07/2026 | 33474 | 2021-08-19 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-7445 | PUMP GP
N0111-8L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 8 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7521 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Pipe Positioner Swing |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6798 | CYLINDER GP
N0111-8R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 8 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7522 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Pipe Positioner Clamp |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-8999 | CYLINDER GP
N0111-9L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 9 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7524-FR | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - FRONT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N7032 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Cooler Fan Hyd |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 11R-1030 | PUMP GP-PISTON
N7524-RE | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - REAR |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N7527-F | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain FRONT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6795 | CYL GP-127 1
N0111-9R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 9 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7008-02 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Hydraulic POS 2 |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 20R-9460 | PUMP GP-PISTON
N0112-0L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 10 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 10 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7008-01 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Hydraulic POS 1 |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 20R-9460 | PUMP GP-PISTON
N0112-1L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 11 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 11 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7070 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Pump Implement |  | 47986 | 15000 | 2026-07-08 | 12 | 06/07/2026 | 33474 | 2021-08-19 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 11R-1962 | PUMP GP-GR C
N7044 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Cooler Fan Hyd |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 392-4160 | SPIDER-AS-FAN
N0111-5R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 5 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-5L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 5 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7467-RL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension RL |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0105-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Idler LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0105-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Idler RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0111-1L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 1 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0101-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Chain RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N0111-1R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 1 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N3021 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Uni's Eng - Pump Drive |  | 82501 | 5000 | 2026-07-08 | 18.5 |  | 78251 | 2025-08-09 |  | 390-8908 | SPIDER & BEARING AS
N0111-2L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 2 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N2004 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Transmission Pump |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N0101-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Chain LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N7234-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Cooler Fan RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 526-3938 | MOTOR GP-PISTON
N7234-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Cooler Fan LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 526-3938 | MOTOR GP-PISTON
N0111-2R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 2 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7527-RE | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain REAR |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6795 | CYL GP-127 1
N7201 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Air Con |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 419-0777 | MOTOR GP-PSF
N2000 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Transmission |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N0111-3R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 3 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7100 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Charge |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 594-6741 | PUMP GP-GEAR
N0111-4L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 4 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7330-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Travel LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 20R-9462 | MOTOR GP
N7068 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Pump Auxiliary |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 20R-9457 | PUMP GP-PISTON
N1000 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Engine |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N7330-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Motor Travel RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 20R-9462 | MOTOR GP
N7460 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Feed |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-9005X | MD6310 P/DOWN CYL
N7467-LL | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension LL |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0111-4R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 4 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7467-LU | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension LU |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0111-3L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 3 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N3029 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Uni's T/C - Trans |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N7524 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0
N7528-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Hyd Op Bit Basket RIGH |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6805 | CYL GP-127 1
N7570-RR | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT REA |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N7575 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Rotate |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-0147 | CYLINDER GP
N7581 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Swing |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-0146 | CYLINDER GP
N0112-2R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 12 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7582 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Clamp |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 524-0148 | CYLINDER GP
N7587 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Deck Inspection Hatch |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 548-0995 | CYL GP-051 0
N7610 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Hyd Cooler Core |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N0112-3L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 13 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N5000-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Final Drive RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N7592-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Mast Raise LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 450-7146X | MD6310 MAST RAISE CYL
N7528-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Hyd Op Bit Basket LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6805 | CYL GP-127 1
N7041 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Pump Cooling Fan Engine |  | 17737.5 | 18000 | 2026-07-08 | 6.35 | 18/08/2026 | 0 | 2022-06-01
N0112-4R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 14 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0121-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Carrier Roller No 1 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7595-L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Mast Lock LEFT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6795 | CYLINDER GP-HYDRAULIC -MAST LOCK
N7595-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Mast Lock RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6795 | CYLINDER GP-HYDRAULIC -MAST LOCK
N0121-R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Carrier Roller No 1 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7598-LO | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing LOWER |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 539-1901 | CYL GP-127 1
N0112-3R | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 13 RIGHT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-2L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 12 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-4L | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Track Roller 14 LEFT |  | 14426 | 15000 | 2026-07-08 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7541 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Access Ladder |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 515-6798 | CYL GP-076 3
N7570-LR | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT REA |  | 14426 | 15000 | 2026-07-08 | 14 | 06/08/2026 | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N0300 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Feed Chain |  | 5650 | 2000 | 2026-07-09 | 13.79 |  | 4232 | 2026-02-14
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Brake Slack Adj FRONT |  | 60646.3 | 20000 | 2026-07-09 | 13.75 |  | 41218 | 2021-05-15
N0300-C | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Feed Chain CENTRE |  | 5650 | 2000 | 2026-07-09 | 13.79 |  | 4232 | 2026-02-14
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Brake Slack Adj REAR |  | 60646.3 | 20000 | 2026-07-09 | 13.75 |  | 41218 | 2021-05-15
N1002 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Engine Valve Adj |  | 5943 | 3000 | 2026-07-10 | 13.79 |  | 3535 | 2025-12-17
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Air Cond'r-Serv |  | 41713 | 5000 | 2026-07-10 | 15 |  | 37356 | 2022-05-27
N0556 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Air Safety Valve |  | 5373 | 0 | 2026-07-10 | 13 |  | 3896 | 2025-07-10
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | A Frame Bearing Reshim Initial |  | 60646.3 | 2000 | 2026-07-10 | 13.75 |  | 59232 | 2025-11-21
N0300-H | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 4002 | 2500 | 2026-07-11 | 12 | 01/08/2026 | 2036 | 2026-01-18
N8122-01 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Wheel Group POS 1 |  | 67400 | 20000 | 2026-07-11 | 17 | 25/06/2026 | 48145 | 2019-05-25 | DELIVER TO MACKAY - REQUIRED BY 19/05/26 | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N2002 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Oil Cooler - Transmission |  | 69633 | 20000 | 2026-07-12 | 18.5 | 02/07/2026 | 50472 | 2022-07-13
N1310 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Radiator |  | 47986 | 15000 | 2026-07-12 | 12 | 06/07/2026 | 33531 | 2022-02-03 |  | 371-6833 | RADIATOR AR
N9500 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Air Cond'r-Serv |  | 61931 | 4000 | 2026-07-12 | 18.5 | 20/07/2026 | 58764 | 2025-12-08
N9500 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Air Cond'r-Serv |  | 26541 | 4000 | 2026-07-12 | 12.5 | 05/08/2026 | 23100 | 2025-10-23
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Drive Shaft Eng - Pump Drive |  | 60646.3 | 20000 | 2026-07-13 | 13.75 |  | 41277 | 2021-07-06
N0099 | WA | EPI | 85 | Iron Bridge | DR3153 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 1450 | 2000 | 2026-07-13 | 12 | 10/07/2026 | 0 | 2025-05-14
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Air Cond'r-Serv |  | 60646.3 | 5000 | 2026-07-13 | 13.75 |  | 56274 | 2025-04-28 |  | 385-0244 | MOTOR,BLOWER
N7434-R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cyl Bucket Clam RIGHT |  | 55435 | 5000 | 2026-07-13 | 18.5 |  | 51284 | 2025-09-17
N1320-E2 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Cooling Fan Engine EN2 |  | 55435 | 16000 | 2026-07-14 | 18.5 |  | 40304 | 2022-12-13 |  | 486-9962-T | CYL, BOOM LIFT, 6060
N6061 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Oil Cooler Front Brakes |  | 69633 | 26000 | 2026-07-14 | 18.5 | 02/07/2026 | 44498 | 2021-05-03
N9501 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | A/C Compressor |  | 52281 | 10000 | 2026-07-14 | 17 |  | 43086 | 2021-01-27
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Hyd Cyl Hoist LEFT |  | 75619 | 30000 | 2026-07-14 | 19 |  | 46507 | 2019-04-30 |  | 295-5708 | CYLINDER GP
N7232 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Hyd Motor Engine Fan |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0350 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N7340 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N2090 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Drv Coupling |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N9501 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | A/C Compressor |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N1301 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Water Pump |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0346 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0302 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Feed Sprocket |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0091-RT | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0597 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N9050 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Starter Motor |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N8995 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Operator Seat |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N9020 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Alternator |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N7151 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0145 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Pivot Shaft Brgs |  | 18651 | 4000 | 2026-07-15 | 13 | 17/07/2026 | 15279.66 | 2025-05-01 | CHECK WEAR - ORDER PER ML 24/03 - PUSH TO JULY
N1200 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Fuel Pump |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N1300 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Cooling Sys Service |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N1210 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Fuel Injectors |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N7421-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Cyl Blade Tilt LEFT |  | 62609 | 15000 | 2026-07-15 | 12 |  | 48187 | 2020-04-16 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-9634 | Tilt Cylinder
N0596 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N0558 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Air End Coupling |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N1004 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Engine Midlife |  | 5373 | 6000 | 2026-07-15 | 13 |  | 0
N9500 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Air Cond'r-Serv |  | 47332.5 | 0 | 2026-07-15 | 7.13 |  | 0 | 2025-07-15
N7474-R | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 59732.1 | 24000 | 2026-07-16 | 13.75 |  | 36405 | 2019-10-10
N7474-R | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 59732.1 | 24000 | 2026-07-16 | 13.75 |  | 36405 | 2019-10-10
N2020 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Powertrain Pump |  | 32356 | 12000 | 2026-07-16 | 11 | 03/07/2026 | 20897 | 2022-03-21 | THIESS MANAGED | 20R-7445 | PUMP GP
N5000-L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Final Drive LEFT |  | 8398 | 9000 | 2026-07-17 | 12 | 02/08/2026 | 0
N0111-8R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 8 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N5000-R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Final Drive RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 | 02/08/2026 | 0
N0101-L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Chain LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0345 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hose Drum Assembly |  | 8398 | 9000 | 2026-07-17 | 12 | 02/08/2026 | 0
N7460-05 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Feed Swing |  | 8398 | 9000 | 2026-07-17 | 12 | 02/08/2026 | 0
N0111-3R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 3 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-8L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 8 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-1L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 1 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-2L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 2 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-2R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 2 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-3L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 3 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-4L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 4 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-4R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 4 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0112-0L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 10 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-9R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 9 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-6R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 6 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-5R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 5 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0121-R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Carrier Roller No 1 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0101-R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Chain RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Engine Valve Adj |  | 52309.6 | 4000 | 2026-07-17 | 13 | 02/04/2026 | 48954 | 2023-10-22
N0104-R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Sprockets RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-7R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 7 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0104-L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Sprockets LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-6L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 6 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0112-0R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 10 RIGHT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-5L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 5 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-7L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 7 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0111-9L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Track Roller 9 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N0121-L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Carrier Roller No 1 LEFT |  | 8398 | 9000 | 2026-07-17 | 12 |  | 0
N6000-04 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Brake POS 4 |  | 37630 | 16000 | 2026-07-18 | 12 | 03/08/2026 | 22240 | 2018-12-30 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-9994 | BRAKE GP FRONT
N6000-06 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Brake POS 6 |  | 37630 | 16000 | 2026-07-18 | 12 | 03/08/2026 | 22240 | 2018-12-30 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 20R-9994 | BRAKE GP FRONT
N9500 | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Air Cond'r-Serv |  | 33341.1 | 0 | 2026-07-18 | 5.95 |  | 0 | 2025-07-18
N7021 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Pump Brake Cooling |  | 67791 | 22000 | 2026-07-18 | 18.5 | 25/09/2026 | 46743 | 2021-11-06
N1202 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Fuel Transfer Pump |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01 |  | 10R-9838 | PUMP GP-F XFR
N3029 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Uni's T/C - Trans |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01 |  | 8R-7036 | SPIDER
N1420 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Air Compressor |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01 |  | 0R-9626 | COMPRESSOR GP -B
N1100-R | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Turbo Primary RIGHT |  | 67400 | 10000 | 2026-07-19 | 17 | 25/06/2026 | 58283 | 2023-10-01 |  | 20R-3423 | TURBO GRP
N9050-UP | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Starter Motor UPPER |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01 |  | 10R-9816 | REMAN STARTER MOTOR
N5020-02 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Wheel Bearing POS 2 |  | 78363 | 30000 | 2026-07-19 | 14 |  | 49089 | 2020-08-26 |  | 446-0367 | KIT
N1300 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Cooling Sys Service |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01 |  | 418-4162 | REGULATOR
N9501 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | A/C Compressor |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01
N1002 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Engine Valve Adj |  | 5650 | 3000 | 2026-07-19 | 13.79 |  | 3373 | 2025-12-17
N6000-02 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Brake POS 2 |  | 78363 | 30000 | 2026-07-19 | 14 |  | 49089 | 2020-08-26 |  | 10R-5394 | BRAKE, FRT, 793
N1402 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Fan Pulley Brgs |  | 67400 | 10000 | 2026-07-19 | 17 | 25/06/2026 | 58283 | 2023-10-01 |  | 6Y-7651 | CONE BEARING
N1100-L | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Turbo Primary LEFT |  | 67400 | 10000 | 2026-07-19 | 17 | 25/06/2026 | 58283 | 2023-10-01 |  | 20R-3423 | TURBO GRP
N8122-02 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Wheel Group POS 2 |  | 78363 | 30000 | 2026-07-19 | 14 |  | 49089 | 2020-08-26 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N1403 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Jockey Pulley Brgs |  | 67400 | 10000 | 2026-07-19 | 17 | 25/06/2026 | 58283 | 2023-10-01 |  | 4S-5367 | BUSHING
N9050-LW | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Starter Motor LOWER |  | 67400 | 10000 | 2026-07-19 | 17 |  | 58283 | 2023-10-01 |  | 10R-9816 | REMAN STARTER MOTOR
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Engine Valve Adj |  | 47835.6 | 4000 | 2026-07-20 | 13 |  | 44527 | 2024-07-05
N3029 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Uni's T/C - Trans |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 8R-7036 | SPIDER
N9500 | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Air Cond'r-Serv |  | 23844.2 | 0 | 2026-07-21 | 13.5 |  | 0 | 2025-07-21
N1202 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Fuel Transfer Pump |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 10R-9838 | PUMP GP-F XFR
N1002 | WA | CAT | 85 | McPhee Creek | RD6601 | Cat 789D | Engine Valve Adj |  | 3453.85 | 4000 | 2026-07-21 | 11.19 |  | 60.27 | 2025-06-04
N1402 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Fan Pulley Brgs |  | 54428 | 10000 | 2026-07-21 | 17 | 01/06/2026 | 45352 | 2024-02-20 |  | 6Y-7651 | CONE BEARING
N0555-FU | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooler Fan Hyd Brgs FRNT UPPER |  | 23756 | 15000 | 2026-07-21 | 18.5 | 24/07/2026 | 9763 | 2024-02-11
N1100-L | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Turbo Primary LEFT |  | 54428 | 10000 | 2026-07-21 | 17 | 01/06/2026 | 45352 | 2024-02-20 |  | 20R-3423 | TURBO GRP
N0140 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Equalizer Bar |  | 34410.8 | 8000 | 2026-07-21 | 6.35 |  | 26751.28 | 2023-02-26
N3021 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Uni's Eng - Pump Drive |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20
N1403 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Jockey Pulley Brgs |  | 54428 | 10000 | 2026-07-21 | 17 | 01/06/2026 | 45352 | 2024-02-20 |  | 4S-5367 | BUSHING
N1100-R | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Turbo Primary RIGHT |  | 54428 | 10000 | 2026-07-21 | 17 | 01/06/2026 | 45352 | 2024-02-20 |  | 20R-3423 | TURBO GRP
N1300 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Cooling Sys Service |  | 54428 | 10000 | 2026-07-21 | 17 | 01/06/2026 | 45352 | 2024-02-20 |  | 418-4162 | REGULATOR
N9501 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | A/C Compressor |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20
N3052 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Uni's Trans- C/Bearing |  | 70621 | 12000 | 2026-07-21 | 15 |  | 59432 | 2023-12-23
N1420 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Air Compressor |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 0R-9626 | COMPRESSOR GP -B
N9020 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Alternator |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 10R-8755 | ALTERNATOR GP_B
N7542-R | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cyl Steer RIGHT |  | 82501 | 20000 | 2026-07-21 | 18.5 | 11/06/2026 | 63499 | 2023-02-20 |  | 20R-5304 | STEER CYL
N6200-LR | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Press Converter LEFT REAR |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 8X-7220 | CHAMBER, BRAKE
N7542-R | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cyl Steer RIGHT |  | 82501 | 20000 | 2026-07-21 | 18.5 |  | 63499 | 2023-02-20 |  | 20R-5304 | STEER CYL
N6200-F | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Press Converter FRONT |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 8X-7220 | CHAMBER, BRAKE
N6200-RR | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Press Converter RIGHT REAR |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20 |  | 8X-7220 | CHAMBER, BRAKE
N1004 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Engine Midlife |  | 54428 | 10000 | 2026-07-21 | 17 |  | 45352 | 2024-02-20
N7234-FU | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Motor Cooler Fan FRONT UPP |  | 23756 | 15000 | 2026-07-21 | 18.5 | 24/07/2026 | 9763 | 2024-02-11
N9500 | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Air Cond'r-Serv |  | 7287 | 0 | 2026-07-22 | 12 |  | 0 | 2025-07-22
N1002 | WA | CAT | 85 | McPhee Creek | RD6650 | Cat 777 | Engine Valve Adj |  | 2531.3 | 3000 | 2026-07-22 | 8.55 |  | 0
N6030-F | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Brake Slack Adj FRONT |  | 65303 | 16000 | 2026-07-23 | 18.5 | 12/08/2026 | 50338 | 2022-01-23
N7654 | WA | CAT | 01 |  | RD2644 | Cat 773F | Hyd Accum Service Brake |  | 22056 | 10000 | 2026-07-23 | 8 |  | 12500 | 2021-01-29
N9050-L | WA | CAT | 01 |  | RD2644 | Cat 773F | Starter Motor LEFT |  | 22056 | 10000 | 2026-07-23 | 8 |  | 12500 | 2021-01-13
N7653 | WA | CAT | 01 |  | RD2644 | Cat 773F | Hyd Accum Park Brake |  | 22056 | 10000 | 2026-07-23 | 8 |  | 12500 | 2021-01-22
N3029 | WA | CAT | 01 |  | RD2644 | Cat 773F | Uni's T/C - Trans |  | 22056 | 10000 | 2026-07-23 | 8 |  | 12500 | 2021-02-09
N9050-R | WA | CAT | 01 |  | RD2644 | Cat 773F | Starter Motor RIGHT |  | 22056 | 10000 | 2026-07-23 | 8 |  | 12500 | 2021-01-13
N7426 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Cyl Boom Lift |  | 34291 | 12000 | 2026-07-23 | 13.79 |  | 23063.43 | 2023-04-05
N0300 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Feed Chain |  | 32622 | 2000 | 2026-07-24 | 13.79 |  | 31408 | 2026-02-16
N8441 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Rear Axle Dog Bone |  | 53351 | 25000 | 2026-07-24 | 12 |  | 29039 | 2018-01-13
N7474-R | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Hyd Cyl Hoist RIGHT |  | 60138 | 24000 | 2026-07-24 | 15 |  | 36994 | 2018-05-02 |  | 438-6225 | CYLINDER GP-HOIST
N7088 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Pump Park Brk Rel |  | 39200 | 40000 | 2026-07-24 | 14 |  | 0
N0102-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 46895 | 3000 | 2026-07-24 | 13.5 |  | 44668 | 2025-07-03
N0300-C | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Feed Chain CENTRE |  | 32622 | 2000 | 2026-07-24 | 13.79 |  | 31408 | 2026-02-17
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Air Cond'r-Serv |  | 66379.67 | 0 | 2026-07-24 | 12.5 |  | 0 | 2025-07-24
N0102-R | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 46895 | 3000 | 2026-07-24 | 13.5 |  | 44668 | 2025-07-03
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Air Cond'r-Serv |  | 60509.94 | 0 | 2026-07-24 | 12.5 |  | 0 | 2025-07-24
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 21515 | 3000 | 2026-07-25 | 12 | 05/06/2026 | 19209 | 2025-07-19
N9500 | WA | CAT | 01 | Sanjiv Ridge | GR6524 | Cat 16M | Air Cond'r-Serv |  | 17448.6 | 0 | 2026-07-25 | 7 |  | 0 | 2025-07-25
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Hyd Cyl Hoist LEFT |  | 70515 | 30000 | 2026-07-25 | 19 |  | 41612 | 2019-02-06 |  | 295-5708 | CYLINDER GP
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Air Cond'r-Serv |  | 81805 | 5000 | 2026-07-25 | 18.5 |  | 77883 | 2025-10-10 |  | 385-0244 | MOTOR AS-BLOWER
N0140 | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Equalizer Bar |  | 7287 | 8000 | 2026-07-26 | 12 |  | 0 | 2024-08-27
N0621-L | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 1658 | 2500 | 2026-07-27 | 14 | 15/06/2026 | 0 | 2024-11-12 |  | 565-3200 | PULL DOWN ROPE
N0621-R | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 1658 | 2500 | 2026-07-27 | 14 | 15/06/2026 | 0 | 2024-11-12 |  | 565-3200 | PULL DOWN ROPE
N6030-F | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Brake Slack Adj FRONT |  | 59517 | 16000 | 2026-07-27 | 18.5 | 18/08/2026 | 44625 | 2021-12-29
N0620-L | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 1658 | 2500 | 2026-07-27 | 14 | 15/06/2026 | 0 | 2024-11-12 |  | 565-3199 | PULL DOWN ROPE
N0103-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Plates RIGHT |  | 55934 | 1500 | 2026-07-27 | 13.5 |  | 55250 | 2026-01-09
N0620-R | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 1658 | 2500 | 2026-07-27 | 14 | 15/06/2026 | 0 | 2024-11-12 |  | 565-3199 | PULL DOWN ROPE
N1002 | WA | CAT | 85 | McPhee Creek | RD6611 | Cat 789D | Engine Valve Adj |  | 3329.2 | 4000 | 2026-07-27 | 11.19 |  | 0 | 2024-05-21
N0144 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Pivot Shaft |  | 52003.6 | 28000 | 2026-07-28 | 12 |  | 24738 | 2018-02-14
N0500 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Bulk Water Pump |  | 54979 | 5000 | 2026-07-30 | 14 |  | 50856 | 2025-10-26
N9500 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Air Cond'r-Serv |  | 54979 | 5000 | 2026-07-30 | 14 | 01/08/2026 | 50856 | 2025-10-26
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | A/C Compressor |  | 39200 | 10000 | 2026-07-30 | 14 |  | 30081 | 2020-08-22
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Operator Seat |  | 75619 | 6000 | 2026-07-31 | 19 |  | 70837 | 2025-03-23 |  | 384-6168 | SEAT GP-SUSPENSION
N9500 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 5373 | 3000 | 2026-07-31 | 13 |  | 3209 | 2025-05-25
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 22613 | 3000 | 2026-07-31 | 12 | 13/07/2026 | 20383 | 2025-05-16
N1002 | NT | CAT | 01 | Idle Plant / Off Hired | RD1902 | Cat 785C XQ | Engine Valve Adj |  | 46670 | 4000 | 2026-07-31 | 11.43 |  | 43397 | 2020-01-28
N6200-LR | WA | CAT | 660 | Sanjiv Ridge | RD6196 | Cat 785D | Press Converter LEFT REAR |  | 23844.2 | 15000 | 2026-07-31 | 13.5 | 15/07/2026 | 9711.01 | 2023-01-30
N3320 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Pump Drive Box |  | 70598 | 18000 | 2026-07-31 | 18.5 | 25/09/2026 | 53790 | 2023-01-13
N3320 | WA | CAT | 01 |  | RD4246 | Cat 789C | Pump Drive Box |  | 54387 | 20000 | 2026-07-31 | 20 |  | 35658 | 2020-05-19 |  | 11R-1517 | DRIVE GP-PUMP
N7605 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Steering Hmu |  | 67572 | 20000 | 2026-08-01 | 15 |  | 48547 | 2018-07-06
N8040 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Circle & Drawbar |  | 37630 | 16000 | 2026-08-01 | 12 |  | 22408 | 2019-01-18 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Air Cond'r-Serv |  | 63459.48 | 0 | 2026-08-01 | 13.5 |  | 0 | 2025-08-01
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4235 | Cat 789C | Operator Seat |  | 63637 | 6000 | 2026-08-01 | 14 |  | 58546 | 2022-10-04 |  | 384-6168 | SEAT GP
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Pump Hoist/ Brk Cooling |  | 57576 | 16000 | 2026-08-01 | 14 |  | 42484 | 2021-02-27 |  | 10R-7967 | PUMP GP
N1002 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Engine Valve Adj |  | 21277 | 3750 | 2026-08-01 | 14 |  | 18436 | 2025-10-16 |  | 449-9059 | SEAL
N0200 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | A Frame Bearing |  | 37630 | 16000 | 2026-08-01 | 12 |  | 22408 | 2019-01-18
N7440 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Hyd Cyl Centreshift |  | 37630 | 16000 | 2026-08-01 | 12 | 03/08/2026 | 22408 | 2019-01-18 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N7620 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Hyd Rotary Joint |  | 37630 | 16000 | 2026-08-01 | 12 |  | 22408 | 2019-01-18
N7123 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Pump Steering & Fan |  | 69479 | 18000 | 2026-08-02 | 18.5 | 16/10/2026 | 52701 | 2023-03-06
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Air Cond'r-Serv |  | 56902.96 | 0 | 2026-08-02 | 13.5 |  | 0 | 2025-08-02
N3029 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Uni's T/C - Trans |  | 52281 | 10000 | 2026-08-02 | 17 |  | 43409 | 2021-03-10 |  | 8R-7036 | SPIDER
N0300-H | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 1713 | 2500 | 2026-08-02 | 12 |  | 0
N6030-L | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Brake Slack Adjuster LEFT |  | 14603 | 8000 | 2026-08-02 | 16 | 07/10/2026 | 7651 | 2024-10-17
N7610 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Cooler Core |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-12
N6360 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Brake Control Valve |  | 31190.5 | 32000 | 2026-08-03 | 12 |  | 0 | 2022-06-01
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Air Cond'r-Serv |  | 60870.4 | 0 | 2026-08-03 | 13.5 |  | 0 | 2025-08-03
N5000-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Final Drive RIGHT |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N3028 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Drive Shaft T/C - Trans |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N1000 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Engine |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-17
N9502 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | A/C Condenser |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-10
N9500-MA | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Air Cond'r-Serv - MAJOR |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17617.9 | 2022-08-17
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Operator Seat |  | 41713 | 6000 | 2026-08-03 | 15 |  | 36712 | 2022-02-13 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8140 | SA | CAT | 01 | Prominent Hill | RD1210 | Cat 777D | Steering Y Piece |  | 66041 | 20000 | 2026-08-03 | 6 |  | 46442 | 2015-09-16
N6030-R | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Brake Slack Adjuster RIGHT |  | 14603 | 8000 | 2026-08-03 | 16 | 07/10/2026 | 7681 | 2024-10-17
N0520 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Pre Lube Pump |  | 34679 | 18000 | 2026-08-03 | 14 |  | 17615 | 2022-08-21 |  | 389-8169 | MOTOR GP-ELECTRIC
N2050 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Torque Convertor |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N0144 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Pivot Shaft |  | 31190.5 | 32000 | 2026-08-03 | 12 |  | 0 | 2022-06-01
N1312-UP | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Aftercooler Core - UPPER |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N7070-L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Pump Implement LEFT |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N0621-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 12996 | 2500 | 2026-08-03 | 14 | 12/09/2026 | 11438 | 2026-02-15 |  | 565-3200 | PULL DOWN ROPE
N8137-R | SA | CAT | 01 | Prominent Hill | RD1210 | Cat 777D | Steering Linkage Group RIGHT |  | 66041 | 20000 | 2026-08-03 | 6 |  | 46442 | 2015-09-16
N0621-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 12996 | 2500 | 2026-08-03 | 14 | 12/09/2026 | 11438 | 2026-02-15 |  | 565-3200 | PULL DOWN ROPE
N0620-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 12996 | 2500 | 2026-08-03 | 14 | 12/09/2026 | 11438 | 2026-02-16 |  | 565-3199 | PULL DOWN ROPE
N1312-LW | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Aftercooler Core - LOWER |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N9500 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 14426 | 4000 | 2026-08-03 | 14 | 06/08/2026 | 11360 | 2025-11-09
N1310 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Radiator |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N0620-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 12996 | 2500 | 2026-08-03 | 14 | 12/09/2026 | 11438 | 2026-02-17 |  | 565-3199 | PULL DOWN ROPE
N7070-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Pump Implement RIGHT |  | 34679 | 18000 | 2026-08-03 | 14 | 03/09/2026 | 17615 | 2022-08-21
N7021 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Pump Brake Cooling |  | 79044 | 40000 | 2026-08-04 | 14 |  | 39992 | 2018-03-14 |  | 20R-7440 | PUMP GP-GEAR
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Drive Shaft T/C - Trans |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-02 |  | 10R-5186 | JOINT GP-SLIP
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Drive Shaft T/C - Trans |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-02 |  | 10R-5186 | JOINT GP-SLIP
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Oil Cooler - Brakes FRONT |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-31 |  | 10R-0817 | CORE GP-O CLR
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Brake POS 2 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 311-0517 | BRAKE, FRT, 785C
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Bearing POS 1 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-05 |  | 293-1016 | KIT
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Linkage Group RIGHT |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 2A-7217 | LINK,STEERING,785
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Bearing POS 2 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 293-1016 | KIT
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Brake POS 1 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-05 |  | 311-0517 | BRAKE, FRT, 785C
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Hmu |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-31
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Hmu |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-31
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Brake POS 1 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-05 |  | 311-0517 | BRAKE, FRT, 785C
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Brake POS 2 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 311-0517 | BRAKE, FRT, 785C
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Linkage Group LEFT |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 2A-7217 | LINK,STEERING,785
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Linkage Group LEFT |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 2A-7217 | LINK,STEERING,785
N0330 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Drifter |  | 18651 | 0 | 2026-08-04 | 13 | 01/07/2026 | 17967 | 2025-12-27
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Bearing POS 2 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 293-1016 | KIT
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Y Piece |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-02
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Pump Drive Box |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-12-31 |  | 6V-8260 | SEAL,O-RING
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Final Drive POS 3 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-30
N9500 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Air Cond'r-Serv |  | 60138 | 5000 | 2026-08-04 | 15 |  | 56154 | 2022-08-18
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Pump Drive Box |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-12-31 |  | 6V-8260 | SEAL,O-RING
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Final Drive POS 3 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-30
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Y Piece |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-02
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Steering Linkage Group RIGHT |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 2A-7217 | LINK,STEERING,785
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Bearing POS 1 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-05 |  | 293-1016 | KIT
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Group POS 2 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N7474-L | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Hyd Cyl Hoist LEFT |  | 79044 | 40000 | 2026-08-04 | 14 |  | 39992 | 2018-03-14 |  | 295-5708 | CYLINDER GP
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Oil Cooler - Brakes FRONT |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-31 |  | 10R-0817 | CORE GP-O CLR
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Group POS 2 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-04 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Group POS 1 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-05 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Wheel Group POS 1 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2018-01-05 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Axle Shaft - POS 3 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-30 |  | 6G-6408 | SHAFT-AXLE (LH)
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Axle Shaft - POS 3 |  | 44852.3 | 20000 | 2026-08-04 | 15 |  | 25870 | 2017-12-30 |  | 6G-6408 | SHAFT-AXLE (LH)
N9050-UP | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Starter Motor UPPER |  | 60646.3 | 10000 | 2026-08-05 | 13.75 |  | 51601 | 2024-05-04
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Press Converter RIGHT REAR |  | 60646.3 | 10000 | 2026-08-05 | 13.75 |  | 51601 | 2024-05-03
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Press Converter LEFT REAR |  | 60646.3 | 10000 | 2026-08-05 | 13.75 |  | 51601 | 2024-05-03
N1300 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Cooling Sys Service |  | 52281 | 10000 | 2026-08-06 | 17 |  | 43474 | 2023-10-01 |  | 418-4162 | REGULATOR
N1402 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Fan Pulley Brgs |  | 52281 | 10000 | 2026-08-06 | 17 | 07/06/2026 | 43474 | 2023-10-01 |  | 6Y-7651 | CONE BEARING
N1100-R | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Turbo Primary RIGHT |  | 52281 | 10000 | 2026-08-06 | 17 | 07/06/2026 | 43474 | 2023-10-01 |  | 20R-3423 | TURBO GRP
N1420 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Air Compressor |  | 52281 | 10000 | 2026-08-06 | 17 |  | 43474 | 2023-10-01 |  | 0R-9626 | COMPRESSOR GP -B
N1202 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Fuel Transfer Pump |  | 52281 | 10000 | 2026-08-06 | 17 |  | 43474 | 2023-10-01 |  | 10R-9838 | PUMP GP-F XFR
N1100-L | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Turbo Primary LEFT |  | 52281 | 10000 | 2026-08-06 | 17 | 07/06/2026 | 43474 | 2023-10-01 |  | 20R-3423 | TURBO GRP
N0597 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-28
N9500 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 7661 | 3000 | 2026-08-06 | 12 | 11/08/2026 | 5506 | 2025-12-30
N1004 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Engine Midlife |  | 52281 | 10000 | 2026-08-06 | 17 |  | 43474 | 2023-10-01
N8995 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Operator Seat |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-29
N7234 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-28
N2090 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Drv Coupling |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-27
N0596 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-28
N0558 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Air End Coupling |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-28
N0350 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-28
N0346 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 22440 | 6000 | 2026-08-06 | 12 | 18/06/2026 | 17275 | 2024-10-29
N1403 | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Jockey Pulley Brgs |  | 52281 | 10000 | 2026-08-06 | 17 | 07/06/2026 | 43474 | 2023-10-01 |  | 4S-5367 | BUSHING
N9050-LW | NT | CAT | 01 | FleetCo | RD1901 | Cat 785C XQ | Starter Motor LOWER |  | 52281 | 10000 | 2026-08-06 | 17 |  | 43474 | 2023-10-01 |  | 10R-9816 | REMAN STARTER MOTOR
N7420-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Cyl Blade Lift RIGHT |  | 34679 | 8000 | 2026-08-06 | 14 |  | 27664 | 2024-10-14 |  | 626-7409 | CYL,BLADE LIFT,D10T2
N8995 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Operator Seat |  | 21494.7 | 6000 | 2026-08-06 | 4 |  | 15776 | 2021-01-26
N9500-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Air Cond'r-Serv LEFT |  | 23402 | 4500 | 2026-08-07 | 18.5 | 10/08/2026 | 20210 | 2025-10-09
N8127-F | WA | CAT | 85 |  | GR1550 | Cat 16M | Axle Assembly FRONT |  | 27110.6 | 16000 | 2026-08-07 | 10 |  | 11817 | 2019-11-27
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Uni's Eng - Pump Drive |  | 60646.3 | 10000 | 2026-08-07 | 13.75 |  | 51622 | 2024-05-05
N7592-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Hyd Cyl Mast Raise LEFT |  | 21238 | 15000 | 2026-08-07 | 14 |  | 7230 | 2022-11-17 |  | 450-7146X | MD6310 MAST RAISE CYL
N9500-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Air Cond'r-Serv RIGHT |  | 23402 | 4500 | 2026-08-07 | 18.5 | 10/08/2026 | 20210 | 2025-10-09
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 20661 | 3000 | 2026-08-08 | 12 | 21/08/2026 | 18526 | 2025-11-06
N9500 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 20661 | 3000 | 2026-08-08 | 12 |  | 18526 | 2025-11-25
N7130-01 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Swing POS 1 |  | 55435 | 6000 | 2026-08-08 | 18.5 | 24/08/2026 | 50766 | 2025-08-19
N8441 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Rear Axle Dog Bone |  | 77195 | 15000 | 2026-08-08 | 14 |  | 63202 | 2023-05-31 |  | 211-4924 | LATERAL LINK, 793
N1002 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Engine Valve Adj |  | 50673 | 4000 | 2026-08-09 | 14 |  | 47698 | 2025-10-20 |  | 449-9059 | SEAL
N0300-H | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 8398 | 2500 | 2026-08-09 | 12 | 02/08/2026 | 6776 | 2025-12-17
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Air Cond'r-Serv |  | 62901.67 | 0 | 2026-08-09 | 13.5 |  | 0 | 2025-08-09
N0622-RU | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Sheave UPPER RIGHT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-8053 | SHEAVE AS
N0623-LL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Sheave LOWER LEFT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-8053 | SHEAVE AS
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6506 | Cat 777G | Air Cond'r-Serv |  | 32588.7 | 0 | 2026-08-10 | 1.61 |  | 0 | 2025-08-10
N0622-TR | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL RIGHT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-6156 | SHEAVE
N0622-TL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL LEFT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-6156 | SHEAVE
N6030-F | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Brake Slack Adj FRONT |  | 67400 | 20000 | 2026-08-10 | 17 |  | 48651 | 2019-07-11 |  | 566-9762 | SLACK ADJUSTER
N0622-LL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Sheave LOWER LEFT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-8053 | SHEAVE AS
N3300 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Circle Drive Box |  | 49898.9 | 8000 | 2026-08-10 | 10 |  | 42637 | 2024-02-28 |  | 454-4691 | CIRCLE DRIVE
N0622-LU | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Sheave UPPER LEFT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-8053 | SHEAVE AS
N0622-RL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Sheave LOWER RIGHT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-25 |  | 450-8053 | SHEAVE AS
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Engine Valve Adj |  | 86119 | 4000 | 2026-08-10 | 18.5 |  | 83491 | 2025-11-24 |  | 272-0760 | SEAL-VALVE COVER
N6060-F | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Oil Cooler - Brakes FRONT |  | 67400 | 20000 | 2026-08-10 | 17 |  | 48651 | 2019-07-11 |  | 10R-0817 | CORE GP-O CLR
N0623-RL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Sheave LOWER RIGHT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-24 |  | 450-8053 | SHEAVE AS
N0623-RU | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Sheave UPPER RIGHT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-24 |  | 450-8053 | SHEAVE AS
N0623-TR | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Sheave TRAVEL RIGHT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-24 |  | 450-6156 | SHEAVE
N7230 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Hyd Motor Circle Drive |  | 49898.9 | 8000 | 2026-08-10 | 10 |  | 42637 | 2024-02-28
N6200-LR | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Press Converter LEFT REAR |  | 63459.48 | 15000 | 2026-08-10 | 13.5 | 08/09/2026 | 49460 | 2023-05-13
N5003-04 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Final Drive Ext Life POS 4 |  | 69479 | 25000 | 2026-08-10 | 18.5 | 16/10/2026 | 45851 | 2021-10-09
N0623-TL | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Sheave TRAVEL LEFT |  | 17257 | 7500 | 2026-08-10 | 14 | 28/05/2026 | 10796 | 2024-10-24 |  | 450-6156 | SHEAVE
N6200-RR | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Press Converter RIGHT REAR |  | 54979 | 10000 | 2026-08-10 | 14 | 01/08/2026 | 46018 | 2025-02-08 |  | 8X-7220 | CHAMBER, BRAKE
N6030-RE | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Brake Slack Adj REAR |  | 67400 | 20000 | 2026-08-10 | 17 |  | 48651 | 2019-07-11 |  | 566-9766 | ADJUSTER GP
N0111-4L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 4 LEFT |  | 45807 | 8000 | 2026-08-11 | 14 |  | 38857 | 2023-06-04 |  | 309-7678 | ROLLER GP-DF
N9500 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 11357 | 4000 | 2026-08-12 | 15 | 09/09/2026 | 8496 | 2025-10-21
N1002 | WA | CAT | 85 | McPhee Creek | RD6608 | Cat 789D | Engine Valve Adj |  | 3150.15 | 4000 | 2026-08-12 | 11.19 |  | 0 | 2024-05-21
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Uni's T/C - Trans |  | 44852.3 | 10000 | 2026-08-13 | 15 |  | 36000 | 2021-01-07 |  | 8R-7036 | SPIDER
N0100-R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Group RIGHT |  | 5943 | 7000 | 2026-08-13 | 13.79 |  | 0 | 2025-04-19
N0100-L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Track Group LEFT |  | 5943 | 7000 | 2026-08-13 | 13.79 |  | 0 | 2025-04-19
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | A Frame Bearing Reshim Initial |  | 54615 | 2000 | 2026-08-13 | 15 |  | 53773 | 2023-07-05
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Uni's T/C - Trans |  | 44852.3 | 10000 | 2026-08-13 | 15 |  | 36000 | 2021-01-07 |  | 8R-7036 | SPIDER
N1310-E2 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Radiator EN2 |  | 55435 | 16000 | 2026-08-14 | 18.5 |  | 40871 | 2023-01-15
N8995 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Operator Seat |  | 70621 | 6000 | 2026-08-14 | 15 |  | 65798 | 2025-04-03
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Rear Axle Dog Bone |  | 70515 | 15000 | 2026-08-15 | 19 |  | 57008 | 2022-09-12 |  | 211-4924 | LATERAL LINK, 793
N2004 | WA | CAT | 01 | Sanjiv Ridge | GR6524 | Cat 16M | Transmission Pump |  | 17448.6 | 18000 | 2026-08-15 | 7 |  | 0 | 2022-06-01
N2052 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Convertor/Trans Pump |  | 67791 | 18000 | 2026-08-15 | 18.5 | 25/09/2026 | 51248 | 2022-11-06
N7044 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Cooler Fan Hyd |  | 20661 | 12000 | 2026-08-15 | 12 |  | 9604 | 2023-06-30
N2000 | WA | CAT | 01 | Sanjiv Ridge | GR6524 | Cat 16M | Transmission |  | 17448.6 | 18000 | 2026-08-15 | 7 |  | 0 | 2022-06-01
N1310 | WA | CAT | 01 | Sanjiv Ridge | GR6524 | Cat 16M | Radiator |  | 17448.6 | 18000 | 2026-08-15 | 7 |  | 0 | 2022-06-01
N1000 | WA | CAT | 01 | Sanjiv Ridge | GR6524 | Cat 16M | Engine |  | 17448.6 | 18000 | 2026-08-15 | 7 |  | 0 | 2022-06-01
N3038 | WA | CAT | 85 |  | GR1550 | Cat 16M | Uni's Trans - Bevel Gear |  | 27110.6 | 7000 | 2026-08-15 | 10 |  | 20896 | 2023-10-21
N3037 | WA | CAT | 85 |  | GR1550 | Cat 16M | Drive Shaft Trans - Bevel Gear |  | 27110.6 | 14000 | 2026-08-15 | 10 |  | 13896 | 2020-07-14 |  | 419-1963
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Uni's T/C - Trans |  | 52309.6 | 10000 | 2026-08-16 | 13 |  | 43346 | 2021-03-06 |  | 8R-7036 | SPIDER
N9500 | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Air Cond'r-Serv |  | 2718 | 0 | 2026-08-16 | 15.2 |  | 0 | 2025-08-16
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Press Converter RIGHT REAR |  | 52309.6 | 10000 | 2026-08-16 | 13 |  | 43346 | 2021-03-05 |  | 8X-7220 | CHAMBER, BRAKE
N8995 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Operator Seat |  | 69479 | 6000 | 2026-08-17 | 18.5 | 16/10/2026 | 64973 | 2025-09-20
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 22440 | 3000 | 2026-08-17 | 12 |  | 20411 | 2025-11-24
N6200-RR | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Press Converter RIGHT REAR |  | 65021 | 10000 | 2026-08-17 | 8.5 |  | 55706 | 2020-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Uni's Eng - Pump Drive |  | 60741 | 10000 | 2026-08-17 | 14 |  | 51870 | 2023-03-22 |  | 108-6587 | BEARING,SPIDER
N6200-LR | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Press Converter LEFT REAR |  | 65021 | 10000 | 2026-08-17 | 8.5 |  | 55706 | 2020-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Press Converter FRONT |  | 65021 | 10000 | 2026-08-17 | 8.5 |  | 55706 | 2020-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N7232 | WA | CAT | 85 |  | LO2122 | Cat 992K | Hyd Motor Engine Fan |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N3021 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Uni's Eng - Pump Drive |  | 78345 | 6000 | 2026-08-18 | 14 | 07/05/2026 | 73486 | 2025-06-02 |  | 390-8908 | SPIDER & BEARING AS
N7120 | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Steering |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N1400-L | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Belt Tensioner Assy - LEFT |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N3210-06 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Tandem Drive Chain POS 6 |  | 26541 | 16000 | 2026-08-18 | 12.5 | 10/09/2026 | 11564 | 2021-11-25
N1202 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Fuel Transfer Pump |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N0200 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | A Frame Bearing |  | 76600 | 20000 | 2026-08-18 | 14 |  | 57750 | 2022-08-19 |  | 106-9343 | BEARING
N1205 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Fuel Pump - High Pressure |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N7600-S | WA | CAT | 85 |  | LO2122 | Cat 992K | Control Valve - STEERING |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N7070-C | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Implement CENTRE |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N9501 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | A/C Compressor |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N0099 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 8398 | 2000 | 2026-08-18 | 12 | 22/09/2026 | 7380 | 2026-02-19
N7122 | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Emerg/Sup Steering |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N3210-04 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Tandem Drive Chain POS 4 |  | 26541 | 16000 | 2026-08-18 | 12.5 | 10/09/2026 | 11564 | 2021-11-25
N7070-R | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Implement RIGHT |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Ride Strut POS 4 |  | 58874 | 20000 | 2026-08-18 | 13.75 |  | 40006 | 2021-10-25
N1300 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Cooling Sys Service |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N7164 | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump & Motor Axle Cooler |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2023-11-23 | THIESS MANAGED
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Hyd Cyl Steer RIGHT |  | 58874 | 20000 | 2026-08-18 | 13.75 |  | 40006 | 2021-10-24
N7542-R | WA | CAT | 85 |  | LO2122 | Cat 992K | Hyd Cyl Steer RIGHT |  | 35037 | 12000 | 2026-08-18 | 11 | 19/10/2026 | 23935 | 2024-01-04 | THIESS MANAGED
N1301 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Water Pump |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N1400-R | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Belt Tensioner Assy - RIGHT |  | 65569 | 12000 | 2026-08-18 | 18.5 | 20/09/2026 | 55077 | 2024-11-12
N2055 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Convertor Charge Scav Pump |  | 54833.54 | 20000 | 2026-08-19 | 12.5 | 17/08/2026 | 35866 | 2014-07-17
N1002 | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Engine Valve Adj |  | 2718 | 4000 | 2026-08-20 | 15.2 |  | 0
N0201-01 | WA | CAT | 95 |  | RD4977 | Cat 789C | A Frame Bearing Reshim Initial |  | 818 | 2000 | 2026-08-20 | 14 |  | 0
N3341 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 21508 | 6000 | 2026-08-21 | 12 | 28/05/2026 | 16525 | 2025-04-30
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 21508 | 6000 | 2026-08-21 | 12 |  | 16525 | 2025-04-01
N7664-LW | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper LOWER |  | 18065 | 10000 | 2026-08-21 | 13 |  | 9170 | 2024-01-08
N3029 | WA | CAT | 660 | Sanjiv Ridge | RD6194 | Cat 785D | Uni's T/C - Trans |  | 24344.16 | 10000 | 2026-08-21 | 13.5 | 16/06/2026 | 15495.69 | 2024-06-16
N7234 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 21508 | 6000 | 2026-08-21 | 12 | 28/05/2026 | 16525 | 2025-04-01
N0350 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 21508 | 6000 | 2026-08-21 | 12 | 28/05/2026 | 16525 | 2025-04-30
N0346 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 21508 | 6000 | 2026-08-21 | 12 | 28/05/2026 | 16525 | 2025-04-30
N0302 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Feed Sprocket |  | 21508 | 6000 | 2026-08-21 | 12 | 28/05/2026 | 16525 | 2025-04-30
N8200-04 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Ride Strut POS 4 |  | 58227.56 | 30000 | 2026-08-21 | 12.5 |  | 29288 | 2017-04-15
N0099 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 7661 | 2000 | 2026-08-21 | 12 | 22/09/2026 | 6678 | 2026-03-09
N7664-UP | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper UPPER |  | 18065 | 10000 | 2026-08-21 | 13 |  | 9170 | 2024-01-08
N1403 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Jockey Pulley Brgs |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 4S-5367 | BUSHING
N1402 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Fan Pulley Brgs |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 6Y-7651 | CONE BEARING
N1420 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Air Compressor |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 0R-9626 | COMPRESSOR GP -B
N1300 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Cooling Sys Service |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 418-4162 | REGULATOR
N0621-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 11357 | 2500 | 2026-08-22 | 15 | 09/09/2026 | 10140 | 2026-02-21 |  | 565-3200 | PULL DOWN ROPE
N0621-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 11357 | 2500 | 2026-08-22 | 15 | 09/09/2026 | 10140 | 2026-02-22 |  | 565-3200 | PULL DOWN ROPE
N0620-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 11357 | 2500 | 2026-08-22 | 15 | 09/09/2026 | 10140 | 2026-02-21 |  | 565-3199 | PULL DOWN ROPE
N1202 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Fuel Transfer Pump |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 10R-9838 | PUMP GP-F XFR
N3029 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Uni's T/C - Trans |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 8R-7036 | SPIDER
N1100-R | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Turbo Primary RIGHT |  | 67600 | 10000 | 2026-08-22 | 17 | 15/08/2026 | 59057 | 2024-01-01 |  | 20R-3423 | TURBO GRP
N0620-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 11357 | 2500 | 2026-08-22 | 15 | 09/09/2026 | 10140 | 2026-02-22 |  | 565-3199 | PULL DOWN ROPE
N6200-F | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Press Converter FRONT |  | 39272 | 10000 | 2026-08-22 | 15 |  | 36099 | 2022-06-11 |  | 8X-7220 | CHAMBER, BRAKE
N1100-L | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Turbo Primary LEFT |  | 67600 | 10000 | 2026-08-22 | 17 | 15/08/2026 | 59057 | 2024-01-01 |  | 20R-3423 | TURBO GRP
N9050-LW | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Starter Motor LOWER |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 10R-9816 | REMAN STARTER MOTOR
N1490 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 16307 | 2000 | 2026-08-22 | 14 |  | 15514 | 2026-03-26 |  | 449-9059 | SEAL
N9050-UP | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Starter Motor UPPER |  | 67600 | 10000 | 2026-08-22 | 17 |  | 59057 | 2024-01-01 |  | 10R-9816 | REMAN STARTER MOTOR
N3210-04 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Tandem Drive Chain POS 4 |  | 49898.9 | 16000 | 2026-08-23 | 10 |  | 34766 | 2021-10-22
N3210-06 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Tandem Drive Chain POS 6 |  | 49898.9 | 16000 | 2026-08-23 | 10 |  | 34766 | 2021-10-22
N3210-05 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Tandem Drive Chain POS 5 |  | 49898.9 | 16000 | 2026-08-23 | 10 |  | 34766 | 2021-10-22
N7422-L | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Cyl Blade Tip LEFT |  | 14603 | 16000 | 2026-08-23 | 16 |  | 0 | 2022-09-04
N3210-03 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Tandem Drive Chain POS 3 |  | 49898.9 | 16000 | 2026-08-23 | 10 |  | 34766 | 2021-10-22
N1490 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 786 | 2000 | 2026-08-23 | 14 |  | 0 | 2024-11-12 |  | 449-9059 | SEAL
N7120 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Pump Steering |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7232 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Motor Engine Fan |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7650-F | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Accum Blade Cushion FRONT |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7650-RE | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Accum Blade Cushion REAR |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7647-R | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Accum Brake Reseal RIGHT |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N8300 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Artic Hitch |  | 14603 | 16000 | 2026-08-23 | 16 |  | 0 | 2022-09-04
N8995 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Operator Seat |  | 69633 | 6000 | 2026-08-23 | 18.5 | 29/09/2026 | 65249 | 2025-09-22
N7647-L | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Accum Brake Reseal LEFT |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7610 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Cooler Core |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7122 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Pump Emerg/Sup Steering |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7420-L | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Cyl Blade Lift LEFT |  | 14603 | 16000 | 2026-08-23 | 16 |  | 0 | 2022-09-04
N7422-R | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Cyl Blade Tip RIGHT |  | 14603 | 16000 | 2026-08-23 | 16 |  | 0 | 2022-09-04
N7029 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Pump Brake & Cooling Fan Eng |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7070 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Pump Implement |  | 14603 | 16000 | 2026-08-23 | 16 | 07/10/2026 | 0 | 2022-09-04
N7440 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Cyl Centreshift |  | 14603 | 16000 | 2026-08-23 | 16 |  | 0 | 2022-09-04
N7420-R | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Cyl Blade Lift RIGHT |  | 14603 | 16000 | 2026-08-23 | 16 |  | 0 | 2022-09-04
N0300-H | WA | EPI | 85 | Iron Bridge | DR3153 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 1450 | 2500 | 2026-08-24 | 12 | 04/09/2026 | 0 | 2025-05-14
N1310 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Radiator |  | 60509.94 | 20000 | 2026-08-24 | 12.5 | 30/09/2026 | 41614 | 2020-04-19 | Nearest service
N6061 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Oil Cooler Front Brakes |  | 69200 | 26000 | 2026-08-25 | 18.5 | 28/05/2026 | 44844 | 2021-07-04
N7605 | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Steering Hmu |  | 67400 | 20000 | 2026-08-25 | 17 | 25/06/2026 | 48920 | 2019-08-09
N7160 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Pump Axle Lube/Cooler |  | 70515 | 20000 | 2026-08-25 | 19 |  | 52212 | 2021-09-08 |  | 20R-8004 | PUMP GP-GR A
N0201-01 | WA | CAT | 01 |  | RD4246 | Cat 789C | A Frame Bearing Reshim Initial |  | 54387 | 2000 | 2026-08-25 | 20 |  | 54175 | 2024-01-08
N5003-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Final Drive Ext Life POS 3 |  | 70515 | 20000 | 2026-08-25 | 19 |  | 52212 | 2021-09-15 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N7542-L | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cyl Steer LEFT |  | 82501 | 20000 | 2026-08-26 | 18.5 |  | 64160 | 2023-06-30 |  | 20R-5304 | STEER CYL
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Air Cond'r-Serv |  | 67106.81 | 0 | 2026-08-26 | 12.5 |  | 0 | 2025-08-26
N7542-L | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Hyd Cyl Steer LEFT |  | 82501 | 20000 | 2026-08-26 | 18.5 | 11/06/2026 | 64160 | 2023-06-30 |  | 20R-5304 | STEER CYL
N7432-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Bucket RIGHT |  | 23746 | 10000 | 2026-08-26 | 18.5 |  | 15411 | 2025-01-17
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Brake Slack Adj REAR |  | 71898 | 16000 | 2026-08-26 | 18.5 | 20/10/2026 | 57560 | 2024-04-14
N0111-7R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 7 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-4R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 4 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0139-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Frame Mid Life RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25
N0139-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Frame Mid Life LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25
N0111-3L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 3 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0201-01 | WA | CAT | 95 |  | RD4978 | Cat 789C | A Frame Bearing Reshim Initial |  | 728 | 2000 | 2026-08-27 | 14 |  | 0
N0111-2L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 2 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-8R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 8 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-7L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 7 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N1002 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Engine Valve Adj |  | 35745 | 3000 | 2026-08-27 | 15 |  | 34103 | 2026-02-11
N3220 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Swing Box |  | 14715.2 | 15000 | 2026-08-27 | 3.12 |  | 0 | 2022-06-01
N0111-1R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 1 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0121-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Carrier Roller No 1 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7679 | ROLLER GP-SF
N8443-LR | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Rear Axle Control Arm L/RIGHT |  | 68788 | 20000 | 2026-08-27 | 18.5 | 05/09/2026 | 50470 | 2022-05-07
N0111-3R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 3 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-1L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 1 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-6L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 6 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 4 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-6R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 6 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N7320 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Hyd Motor Swing |  | 14715.2 | 15000 | 2026-08-27 | 3.12 |  | 0 | 2022-06-01
N0111-5L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 5 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-2R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 2 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-5R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 5 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0111-8L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Track Roller 8 LEFT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7678 | ROLLER GP-DF
N0121-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Carrier Roller No 1 RIGHT |  | 55934 | 9000 | 2026-08-27 | 13.5 |  | 48168 | 2024-06-25 |  | 309-7679 | ROLLER GP-SF
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | A Frame Bearing Reshim Initial |  | 39658.4 | 2000 | 2026-08-28 | 15 |  | 39044 | 2023-12-20 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N7065 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Pump Hoist/ Brk Cooling |  | 59732.1 | 20000 | 2026-08-28 | 13.75 |  | 40998 | 2020-07-17 |  | 10R-7971 | PUMP, HOIST, REMAN
N7065 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Pump Hoist/ Brk Cooling |  | 59732.1 | 20000 | 2026-08-28 | 13.75 |  | 40998 | 2020-07-17 |  | 10R-7971 | PUMP, HOIST, REMAN
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | A Frame Bearing Reshim Initial |  | 39658.4 | 2000 | 2026-08-28 | 15 |  | 39044 | 2023-12-20 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Brake Slack Adj FRONT |  | 64230 | 20000 | 2026-08-29 | 14 |  | 45537 | 2020-07-19 |  | 590-2531 | SLACK ADJUSTER
N4102-03 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Axle Shaft - POS 3 |  | 59517 | 30000 | 2026-08-29 | 18.5 |  | 31246 | 2019-07-02
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Brake Slack Adj REAR |  | 64230 | 20000 | 2026-08-29 | 14 |  | 45537 | 2020-07-19 |  | 590-2533 | SLACK ADJUSTER
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Uni's Eng - Pump Drive |  | 41713 | 10000 | 2026-08-30 | 15 |  | 37262 | 2022-05-12
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | Operator Seat |  | 55805 | 6000 | 2026-08-30 | 14 |  | 51122 | 2022-08-18 |  | 384-6168 | SEAT GP
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4222 | Cat 785C | A Frame Bearing Reshim Initial |  | 41444 | 2000 | 2026-08-30 | 14.5 |  | 40801 | 2025-04-24 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0111-3L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 3 LEFT |  | 45807 | 8000 | 2026-08-31 | 14 |  | 39140 | 2023-07-14 |  | 309-7678 | ROLLER GP-DF
N8995 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Operator Seat |  | 33117 | 6000 | 2026-08-31 | 11 |  | 28161 | 2023-12-16 |  | 443-8104 | CAT OPERATOR SEAT
N6200-02 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Press Convertor POS 2 |  | 79490 | 24000 | 2026-08-31 | 14 |  | 56826 | 2021-11-18 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6030-F | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Brake Slack Adj FRONT |  | 69305 | 20000 | 2026-09-01 | 17 |  | 50933 | 2020-11-01 |  | 566-9762 | SLACK ADJUSTER
N6030-RE | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Brake Slack Adj REAR |  | 69305 | 20000 | 2026-09-01 | 17 |  | 50933 | 2020-11-01 |  | 566-9766 | ADJUSTER GP
N7230 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Hyd Motor Circle Drive |  | 25353 | 8000 | 2026-09-01 | 12.5 |  | 18556 | 2024-10-21
N3300 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Circle Drive Box |  | 25353 | 8000 | 2026-09-01 | 12.5 |  | 18556 | 2024-10-21 |  | 454-4691 | CIRCLE DRIVE
N4110-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Steering Clutch/Brk RIGHT |  | 31311 | 18000 | 2026-09-01 | 14 |  | 14650 | 2021-11-13 |  | 10R-9976 | STEERING CLUTCH BRK GRP, D10
N4110-L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Steering Clutch/Brk LEFT |  | 31311 | 18000 | 2026-09-01 | 14 |  | 14650 | 2021-11-13 |  | 10R-9976 | STEERING CLUTCH BRK GRP, D10
N2050 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Torque Convertor |  | 31311 | 18000 | 2026-09-01 | 14 |  | 14650 | 2021-11-14
N0201-01 | WA | CAT | 95 |  | RD4974 | Cat 789C | A Frame Bearing Reshim Initial |  | 655 | 2000 | 2026-09-01 | 14 |  | 0
N8443-UR | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Rear Axle Control Arm U/RIGHT |  | 62083 | 20000 | 2026-09-02 | 18.5 |  | 43882 | 2021-11-14
N3220-LR | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Swing Box LFT REAR |  | 55435 | 16000 | 2026-09-02 | 18.5 | 24/08/2026 | 41237 | 2023-02-08
N7610-FU | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cooler Core FRONT UPPER |  | 55435 | 16000 | 2026-09-02 | 18.5 |  | 41237 | 2023-02-08
N0100-R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Group RIGHT |  | 5650 | 7000 | 2026-09-03 | 13.79 |  | 0 | 2025-04-01
N0100-L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Track Group LEFT |  | 5650 | 7000 | 2026-09-03 | 13.79 |  | 0 | 2025-04-01
N0100-R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Group RIGHT |  | 34410.8 | 1700 | 2026-09-03 | 6.35 |  | 33334 | 2025-12-17
N0556 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Air Safety Valve |  | 8398 | 0 | 2026-09-03 | 12 | 02/08/2026 | 5499 | 2025-09-03
N0100-L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Track Group LEFT |  | 34410.8 | 1700 | 2026-09-03 | 6.35 |  | 33334 | 2025-12-17
N1490 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Cam Shaft Inspection |  | 46731 | 2000 | 2026-09-03 | 16 |  | 46304 | 2024-10-28 |  | 449-9059 | SEAL
N0099 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 5373 | 2000 | 2026-09-04 | 13 |  | 4655 | 2025-08-31
N7004-09 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Hose Bucket Cylinder |  | 23756 | 10000 | 2026-09-04 | 18.5 | 04/09/2026 | 15589 | 2025-01-27
N0330 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Drifter |  | 18065 | 0 | 2026-09-05 | 13 |  | 17406 | 2026-03-01
N3021 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Uni's Eng - Pump Drive |  | 79490 | 6000 | 2026-09-05 | 14 |  | 74884 | 2025-07-17 |  | 390-8908 | SPIDER & BEARING AS
N0201-01 | WA | CAT | 95 |  | RD4979 | Cat 789C | A Frame Bearing Reshim Initial |  | 601 | 2000 | 2026-09-05 | 14 |  | 0
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Engine Valve Adj |  | 49506 | 4000 | 2026-09-05 | 14.5 |  | 46953 | 2025-02-19
N8995 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Operator Seat |  | 79490 | 6000 | 2026-09-05 | 14 |  | 74884 | 2025-07-17 |  | 384-6168 | SEAT GP-SUSPENSION
N0300-R | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Feed Chain RIGHT |  | 18651 | 2000 | 2026-09-06 | 13 |  | 17969 | 2026-02-14
N9703 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Inertial Measurement Unit |  | 17257 | 10000 | 2026-09-06 | 14 | 16/07/2026 | 8674 | 2024-06-16
N9760 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Fisheye Camera |  | 17257 | 10000 | 2026-09-06 | 14 | 16/07/2026 | 8674 | 2024-06-15
N7570-RF | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT FRO |  | 11349 | 10000 | 2026-09-06 | 15 |  | 2871 | 2024-09-07 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N8200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | Ride Strut POS 2 |  | 55805 | 20000 | 2026-09-07 | 14 |  | 37234 | 2019-06-29 |  | 347-7423 | SUSP CYL
N7120 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Pump Steering |  | 53598.82 | 20000 | 2026-09-07 | 13.5 |  | 34974 | 2022-02-27
N2000 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Transmission |  | 53598.82 | 20000 | 2026-09-07 | 13.5 |  | 34974 | 2022-02-27
N9501 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | A/C Compressor |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-06 |  | 629-8454 | COMPRESSOR GP-REFRIGERANT
N2050 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Torque Convertor |  | 53598.82 | 20000 | 2026-09-07 | 13.5 |  | 34974 | 2022-02-27
N0622-LL | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Sheave LOWER LEFT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N2055 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Convertor Charge Scav Pump |  | 53598.82 | 20000 | 2026-09-07 | 13.5 |  | 34974 | 2022-02-27
N0622-LU | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Sheave UPPER LEFT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N0623-TR | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Sheave TRAVEL RIGHT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-6156 | SHEAVE
N7064 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Pump Hoist |  | 53598.82 | 20000 | 2026-09-07 | 13.5 |  | 34974 | 2022-02-27
N0623-TL | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Sheave TRAVEL LEFT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-6156 | SHEAVE
N2004 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Transmission Pump |  | 53598.82 | 20000 | 2026-09-07 | 13.5 |  | 34974 | 2022-02-27
N0300-H | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 7661 | 2500 | 2026-09-07 | 12 | 22/09/2026 | 6384 | 2026-01-13
N0623-RU | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Sheave UPPER RIGHT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N0623-RL | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Sheave LOWER RIGHT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N0622-TR | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL RIGHT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-6156 | SHEAVE
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | A Frame Bearing Reshim Initial |  | 57617 | 2000 | 2026-09-07 | 20 |  | 57650 | 2024-05-26
N0623-LL | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Sheave LOWER LEFT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | A Frame Bearing Reshim Initial |  | 56457 | 2000 | 2026-09-07 | 14 |  | 55883 | 2024-03-04
N0622-RL | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Sheave LOWER RIGHT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N0201-01 | WA | CAT | 95 |  | RD4972 | Cat 789C | A Frame Bearing Reshim Initial |  | 566 | 2000 | 2026-09-07 | 14 |  | 0
N0622-TL | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL LEFT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-6156 | SHEAVE
N0622-RU | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pulldown Sheave UPPER RIGHT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N0623-LU | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pullback Sheave UPPER LEFT |  | 21277 | 7500 | 2026-09-07 | 14 |  | 15209 | 2024-10-02 |  | 450-8053 | SHEAVE AS
N7474-L | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Hyd Cyl Hoist LEFT |  | 79490 | 40000 | 2026-09-08 | 14 |  | 40935 | 2018-04-05 |  | 295-5708 | CYLINDER GP
N9500 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Air Cond'r-Serv |  | 65021 | 5000 | 2026-09-08 | 8.5 |  | 60896 | 2022-04-10
N0099 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 21508 | 2000 | 2026-09-08 | 12 |  | 20746 | 2026-03-26
N1420 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Air Compressor |  | 18651 | 20000 | 2026-09-09 | 13 |  | 0 | 2022-06-01
N0201-01 | WA | CAT | 95 |  | RD4981 | Cat 789C | A Frame Bearing Reshim Initial |  | 539 | 2000 | 2026-09-09 | 14 |  | 0
N8995 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Operator Seat |  | 37630 | 6000 | 2026-09-09 | 12 | 03/08/2026 | 32876 | 2020-12-15
N1002 | WA | CAT | 01 | Plant Idle - Mining West | LW4073 | Cat 980H | Engine Valve Adj |  | 21494.7 | 2000 | 2026-09-10 | 4 |  | 19915 | 2025-05-03
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Engine Valve Adj |  | 58874 | 4000 | 2026-09-10 | 13.75 |  | 56311 | 2025-09-10
N3029 | NT | CAT | 01 | Idle Plant / Off Hired | RD1902 | Cat 785C XQ | Uni's T/C - Trans |  | 46670 | 10000 | 2026-09-11 | 11.43 |  | 37881 | 2018-11-30 |  | 8R-7036 | SPIDER
N3300 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Circle Drive Box |  | 37630 | 8000 | 2026-09-11 | 12 | 03/08/2026 | 30896 | 2020-07-13 |  | 454-4691 | CIRCLE DRIVE
N6200-RR | NT | CAT | 01 | Idle Plant / Off Hired | RD1902 | Cat 785C XQ | Press Converter RIGHT REAR |  | 46670 | 10000 | 2026-09-11 | 11.43 |  | 37881 | 2018-11-30 |  | 8X-7220 | CHAMBER, BRAKE
N6200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Press Convertor POS 3 |  | 86119 | 10000 | 2026-09-11 | 18.5 |  | 78086 | 2025-02-08 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Press Converter FRONT |  | 49506 | 10000 | 2026-09-11 | 14.5 |  | 41044 | 2023-10-10 |  | 8X-7220 | CHAMBER, BRAKE
N6200-F | NT | CAT | 01 | Idle Plant / Off Hired | RD1902 | Cat 785C XQ | Press Converter FRONT |  | 46670 | 10000 | 2026-09-11 | 11.43 |  | 37881 | 2018-11-30 |  | 8X-7220 | CHAMBER, BRAKE
N7237 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Hyd Motor Rear Axle Cooler Fan |  | 76600 | 24000 | 2026-09-12 | 14 |  | 54097 | 2021-11-16 |  | 307-1504 | MOTOR
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Fuel Transfer Pump |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 10R-9838 | PUMP GP-F XFR
N1002 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Engine Valve Adj |  | 1713 | 3000 | 2026-09-12 | 12 |  | 0
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Turbo Primary LEFT |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 20R-3423 | TURBO GRP
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Cooling Sys Service |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 418-4162 | REGULATOR
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 1713 | 3000 | 2026-09-12 | 12 |  | 0
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | Engine Valve Adj |  | 59952 | 4000 | 2026-09-12 | 14 |  | 57450 | 2024-06-26 |  | 272-0760 | SEAL-PIP
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Air Starter |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Jockey Pulley Brgs |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 4S-5367 | BUSHING
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Turbo Primary RIGHT |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 20R-3423 | TURBO GRP
N1420 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Air Compressor |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 0R-9626 | COMPRESSOR GP -B
N7041 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Pump Cooling Fan Engine |  | 76600 | 24000 | 2026-09-12 | 14 |  | 54097 | 2021-11-16 |  | 10R-5464 | PUMP GP HYD
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Fan Pulley Brgs |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 6Y-7651 | CONE BEARING
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | A/C Compressor |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Alternator |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29 |  | 10R-8755 | ALTERNATOR GP_B
N9500 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 1713 | 3000 | 2026-09-12 | 12 | 15/09/2026 | 0
N1004 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Engine Midlife |  | 45745.5 | 10000 | 2026-09-12 | 13 |  | 37138 | 2021-01-29
N9501 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | A/C Compressor |  | 59122 | 12000 | 2026-09-13 | 18.5 |  | 49127 | 2024-12-04
N5000-04 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Final Drive POS 4 |  | 67683.26 | 20000 | 2026-09-13 | 12.5 | 18/09/2026 | 49037 | 2018-08-21
N4000 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Bevel Gear |  | 67683.26 | 20000 | 2026-09-13 | 12.5 | 18/09/2026 | 49037 | 2018-08-21
N1004 | WA | CAT | 85 | McPhee Creek | DZ6660 | Cat D10T2 | Engine Midlife |  | 5222.3 | 6000 | 2026-09-13 | 7.2 |  | 0 | 2025-01-08
N8995 | WA | CAT | 85 |  | LO2121 | Cat 992K | Operator Seat |  | 33290 | 6000 | 2026-09-13 | 11 |  | 28478 | 2025-03-02 | THIESS MANAGED
N5000-03 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Final Drive POS 3 |  | 67683.26 | 20000 | 2026-09-13 | 12.5 | 18/09/2026 | 49037 | 2018-08-21 | Ung, Heng - Work Order still at 'M' Status - Plan for Replacement?
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Steering Hmu |  | 52712 | 20000 | 2026-09-14 | 13.75 |  | 34212 | 2022-03-04
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Ride Strut POS 1 |  | 52712 | 20000 | 2026-09-14 | 13.75 |  | 34212 | 2022-03-04
N1002 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Engine Valve Adj |  | 31311 | 4000 | 2026-09-14 | 14 |  | 28840 | 2025-11-05 |  | 449-9059 | SEAL
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Ride Strut POS 3 |  | 52712 | 20000 | 2026-09-14 | 13.75 |  | 34212 | 2022-03-04 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N0201-01 | WA | CAT | 95 |  | RD4980 | Cat 789C | A Frame Bearing Reshim Initial |  | 461 | 2000 | 2026-09-15 | 14 |  | 0
N9501 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | A/C Compressor |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 106-5122 | COMPRESSOR
N9020 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Alternator |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 10R-9789 | ALTERNATOR
N1202 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Fuel Transfer Pump |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 20R-0967 | PUMP GP
N3029 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Uni's T/C - Trans |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 173-0888 | UNIVERSAL JOINT GP
N1000 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Engine |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-28
N1100-L | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Turbo Primary LEFT |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 10R-2075 | TURBO, D10T, REMAN
N1300 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Cooling Sys Service |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 248-5513 | REGULATOR-TEMPERATURE
N1310 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Radiator |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-27
N7460-02 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Cyl Feed Dump LEFT |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-25
N7627 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Valve Track Oscillation |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-30
N7480-R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation RIGH |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-26
N3320 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Pump Drive Box |  | 59122 | 18000 | 2026-09-15 | 18.5 |  | 43165 | 2021-10-27
N7008-03 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Pump Hydraulic POS 3 |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-27
N7460-03 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Cyl Feed Dump RIGHT |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-24
N7597 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Cyl Boom Swing |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-24
N7008-02 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Pump Hydraulic POS 2 |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-27
N7480-L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation LEFT |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-27
N7044 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Cooler Fan Hyd |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-26
N7008-01 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Pump Hydraulic POS 1 |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-26
N1004 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Engine Midlife |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21
N1100-R | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Turbo Primary RIGHT |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 10R-2075 | TURBO, D10T, REMAN
N7610 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hyd Cooler Core |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-10-26
N9500-MA | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Air Cond'r-Serv - MAJOR |  | 21534 | 12000 | 2026-09-15 | 12 | 10/09/2026 | 10851 | 2023-11-02
N9050 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Starter Motor |  | 49963 | 7500 | 2026-09-15 | 5.5 |  | 43066 | 2021-07-21 |  | 10R-9816 | MOTOR GP-ELEC
N4102-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Axle Shaft - POS 4 |  | 49506 | 20000 | 2026-09-16 | 14.5 |  | 31120 | 2019-07-10 |  | 6G-6407 | SHAFT-AXLE (RH)
N1100-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Turbo Primary LFT REAR |  | 39200 | 10000 | 2026-09-16 | 14 |  | 30756 | 2020-10-06
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Axle Shaft - POS 3 |  | 49506 | 20000 | 2026-09-16 | 14.5 |  | 31120 | 2019-07-10 |  | 6G-6408 | SHAFT-AXLE (LH)
N7460-05 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Feed Swing |  | 7661 | 9000 | 2026-09-17 | 12 | 22/09/2026 | 0
N0111-4R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 4 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-5L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 5 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-5R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 5 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-4L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 4 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0121-R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Carrier Roller No 1 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-7R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 7 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-6L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 6 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-6R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 6 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-7L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 7 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0112-0R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 10 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0112-0L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 10 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-8L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 8 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-9R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 9 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-9L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 9 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-8R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 8 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0121-L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Carrier Roller No 1 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-3R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 3 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N1000 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Engine |  | 79490 | 18000 | 2026-09-17 | 14 |  | 63053 | 2023-02-04 |  | 488-8196 | 793D PEX ENGINE
N5000-R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Final Drive RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 | 22/09/2026 | 0
N5000-L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Final Drive LEFT |  | 7661 | 9000 | 2026-09-17 | 12 | 22/09/2026 | 0
N9500-MA | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Air Cond'r-Serv - MAJOR |  | 79490 | 18000 | 2026-09-17 | 14 |  | 63053 | 2023-02-04 |  | 137-2134 | AIR CONDITIONER GP
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Operator Seat |  | 81805 | 6000 | 2026-09-17 | 18.5 |  | 77883 | 2025-10-08 |  | 384-6168 | SEAT GP-SUSPENSION
N0201-01 | WA | CAT | 95 |  | RD4976 | Cat 789C | A Frame Bearing Reshim Initial |  | 427 | 2000 | 2026-09-17 | 14 |  | 0
N0101-L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Chain LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-3L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 3 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0345 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hose Drum Assembly |  | 7661 | 9000 | 2026-09-17 | 12 | 22/09/2026 | 0
N0104-L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Sprockets LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0104-R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Sprockets RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0101-R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Chain RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | A Frame Bearing Reshim Initial |  | 58852 | 2000 | 2026-09-17 | 15 |  | 58529 | 2024-03-04
N0111-2R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 2 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-1L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 1 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N0111-2L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 2 LEFT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Engine Valve Adj |  | 60646.3 | 4000 | 2026-09-17 | 13.75 |  | 58192 | 2025-09-01
N1310 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Radiator |  | 79490 | 18000 | 2026-09-17 | 14 |  | 63053 | 2023-02-04 |  | 334-6025 | RADIATOR COOLING GP
N3021 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Uni's Eng - Pump Drive |  | 70598 | 12000 | 2026-09-17 | 18.5 |  | 60664 | 2024-10-21
N0111-1R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Track Roller 1 RIGHT |  | 7661 | 9000 | 2026-09-17 | 12 |  | 0
N6000-01 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Brake POS 1 |  | 79490 | 30000 | 2026-09-19 | 14 |  | 51080 | 2020-12-01 |  | 10R-5394 | BRAKE, FRT, 793
N4102-03 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Axle Shaft - POS 3 |  | 54979 | 20000 | 2026-09-19 | 14 | 01/08/2026 | 36580 | 2023-01-17 |  | 6G-6408 | SHAFT-AXLE (LH)
N5000-04 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Final Drive POS 4 |  | 54979 | 20000 | 2026-09-19 | 14 | 01/08/2026 | 36580 | 2023-02-26
N5020-01 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Wheel Bearing POS 1 |  | 79490 | 30000 | 2026-09-19 | 14 |  | 51080 | 2020-12-01 |  | 446-0367 | KIT
N8122-01 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Wheel Group POS 1 |  | 79490 | 30000 | 2026-09-19 | 14 |  | 51080 | 2020-12-01 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N3028 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Drive Shaft T/C - Trans |  | 33117 | 12000 | 2026-09-19 | 11 |  | 22374 | 2022-05-21 |  | 173-0247 | YOKE COUPLING
N1301 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Water Pump |  | 54979 | 20000 | 2026-09-20 | 14 |  | 36585 | 2023-01-12
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Turbo Primary LEFT |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 10R-2075 | TURBO, D10T, REMAN
N7542-R | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Hyd Cyl Steer RIGHT |  | 79490 | 20000 | 2026-09-20 | 14 |  | 61100 | 2022-09-22 |  | 20R-5304 | STEER CYL
N6062-F | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 79490 | 20000 | 2026-09-20 | 14 |  | 61100 | 2022-09-22 |  | 10R-5675 | CORE AS OIL
N9050 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Starter Motor |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 10R-9816 | MOTOR GP-ELEC
N6062-RE | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 79490 | 20000 | 2026-09-20 | 14 |  | 61100 | 2022-09-22 |  | 10R-5675 | CORE AS OIL
N1302 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Aftercooler Pump |  | 54979 | 20000 | 2026-09-20 | 14 |  | 36585 | 2023-01-12
N9501 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | A/C Compressor |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 106-5122 | COMPRESSOR
N7542-R | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Cyl Steer RIGHT |  | 44396 | 15000 | 2026-09-20 | 15 |  | 31119 | 2023-12-31
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Turbo Primary RIGHT |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 10R-2075 | TURBO, D10T, REMAN
N8995 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Operator Seat |  | 59732.1 | 6000 | 2026-09-20 | 13.75 |  | 55308 | 2024-07-26 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8995 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Operator Seat |  | 59732.1 | 6000 | 2026-09-20 | 13.75 |  | 55308 | 2024-07-26 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9500-MA | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 54979 | 20000 | 2026-09-20 | 14 |  | 36585 | 2023-03-28 |  | 322-7212 | BLOWER,ASSY
N1004 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Engine Midlife |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11
N7542-L | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Hyd Cyl Steer LEFT |  | 79490 | 20000 | 2026-09-20 | 14 |  | 61100 | 2022-09-22 |  | 20R-5304 | STEER CYL
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 8398 | 3000 | 2026-09-20 | 12 | 02/08/2026 | 6776 | 2025-12-17
N1202 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Fuel Transfer Pump |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 20R-0967 | PUMP GP
N6061 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Oil Cooler Front Brakes |  | 79490 | 20000 | 2026-09-20 | 14 |  | 61100 | 2022-09-22 |  | 10R-5673 | CORE AS OIL
N2450 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Drv Cpling Fan Pump-Trans Pump |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 211-9087 | COUPLING AS
N9020 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Alternator |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2025-01-14 |  | 10R-9789 | ALTERNATOR
N1300 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Cooling Sys Service |  | 55934 | 7500 | 2026-09-20 | 13.5 |  | 49989 | 2024-12-11 |  | 248-5513 | REGULATOR-TEMPERATURE
N1000 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Engine |  | 54979 | 20000 | 2026-09-20 | 14 |  | 36585 | 2023-01-12
N1002 | WA | CAT | 85 | McPhee Creek | GR6655 | Cat 18M | Engine Valve Adj |  | 4648.5 | 2500 | 2026-09-21 | 7.02 |  | 2959.8 | 2025-12-14
N6200-F | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Press Converter FRONT |  | 63459.48 | 15000 | 2026-09-22 | 13.5 | 08/09/2026 | 50034 | 2023-06-21
N1002 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Engine Valve Adj |  | 5373 | 3000 | 2026-09-22 | 13 |  | 3900 | 2025-07-12
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Drive Shaft T/C - Trans |  | 58852 | 20000 | 2026-09-22 | 15 |  | 40608 | 2019-03-29 |  | 10R-5185 | DRIVESHAFT TC-TRANS
N2050 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Torque Convertor |  | 79044 | 20000 | 2026-09-22 | 14 |  | 60683 | 2022-10-11 |  | 10R-5398 | TORQUE CONVERTER, 793D
N3042 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Driveline Ctr Bearing |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-29
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Engine Valve Adj |  | 52712 | 4000 | 2026-09-23 | 13.75 |  | 50341 | 2025-09-12
N7071-00 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Imp 1 |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-02-02
N7120-L | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Steering LEFT |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-28
N7120-R | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Steering RIGHT |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-28
N2050 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Torque Convertor |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-26
N1100-RR | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Turbo Primary RHT REAR |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N2000 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Transmission |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-29
N3320-02 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Drive Box POS 2/RE |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-26
N8432 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Trunnion Axle Bearings REAR |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-28
N7121 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Steering/Braking |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-29
N1301 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Water Pump |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N3046-F | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Uni's S/Bearing-Pmp Drv Box FR |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-02-06
N1400 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Belt Tensioner Assembly |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N7087 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Pilot |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-02-03
N1202 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Fuel Transfer Pump |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N3047 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Drv Shft S/Bearing Pump Drives |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-29
N6200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Press Convertor POS 3 |  | 70515 | 10000 | 2026-09-23 | 19 |  | 62763 | 2024-09-28 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N9020-R | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Alternator RIGHT |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N1302 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Aftercooler Pump |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N2020 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Powertrain Pump |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-27
N3032 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Uni's Ctr Bearing - Bevel Gear |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-02-06
N1100-RF | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Turbo Primary RHT FRONT |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N1100-LR | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Turbo Primary LFT REAR |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N1420 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Air Compressor |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N1004 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Engine Midlife |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N1300 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Cooling Sys Service |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N6200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Press Convertor POS 4 |  | 70515 | 10000 | 2026-09-23 | 19 |  | 62763 | 2024-09-28 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N7122 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Emerg/Sup Steering |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-28
N3320-01 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Pump Drive Box POS 1/FR |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-02-02
N1210 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Fuel Injectors |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N9020-L | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Alternator LEFT |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N2440 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Drv Coupling PTO |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23612 | 2024-01-26
N1100-LF | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Turbo Primary LFT FRONT |  | 34192 | 12000 | 2026-09-23 | 12 |  | 23607 | 2024-01-31
N0622-LU | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Sheave UPPER LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N9050-L | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Starter Motor LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 349-6554 | STARTER MOTOR
N0622-RU | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Sheave UPPER RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N0622-RL | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Sheave LOWER RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N9500 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Air Cond'r-Serv |  | 39272 | 5000 | 2026-09-24 | 15 |  | 36054 | 2022-06-03
N9050-R | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Starter Motor RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 349-6554 | STARTER MOTOR
N0622-LL | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Sheave LOWER LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N7151 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pump Water Injection (Bean) |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 521-3019 | PUMP GP-WATER
N1300 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Cooling Sys Service |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 248-5513 | REGULATOR-WATER TEMPERATURE
N0622-TR | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-6156 | SHEAVE
N1100-R | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Turbo Primary RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 20R-3695 | TURBO CHARGER GP (RH)
N1301 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Water Pump |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 10R-6400 | CAT REMAN WATER PUMP
N9020 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Alternator |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 11R-1235 | ALTERNATOR GP
N1210 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Fuel Injectors |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 11R-0276 | INJECTOR GP-FUEL
N0104-L | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Sprockets LEFT |  | 5839 | 7500 | 2026-09-24 | 14 |  | 0 | 2024-11-09 |  | 211-9843 | SPROCKET
N0623-TR | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Sheave TRAVEL RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-6156 | SHEAVE
N0622-TL | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-6156 | SHEAVE
N0104-R | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Sprockets RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 |  | 0 | 2024-11-09 |  | 211-9843 | SPROCKET
N0623-RU | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Sheave UPPER RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N7610-RL | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cooler Core REAR LOWER |  | 55435 | 16000 | 2026-09-24 | 18.5 |  | 41645 | 2023-03-09
N0503 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Water Cannon |  | 5839 | 7500 | 2026-09-24 | 14 |  | 0
N0623-RL | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Sheave LOWER RIGHT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N0623-LU | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Sheave UPPER LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N0623-LL | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Sheave LOWER LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-8053 | SHEAVE AS
N0623-TL | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Pullback Sheave TRAVEL LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 450-6156 | SHEAVE
N1202 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Fuel Transfer Pump |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 20R-0967 | PUMP GP FUEL
N1100-L | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Turbo Primary LEFT |  | 5839 | 7500 | 2026-09-24 | 14 | 24/09/2026 | 0 | 2024-11-09 |  | 20R-3688 | TURBO CHARGER GP (LH)
N2004 | WA | CAT | 85 |  | LO2121 | Cat 992K | Transmission Pump |  | 33290 | 18000 | 2026-09-24 | 11 |  | 16594 | 2021-08-31 | THIESS MANAGED
N6020 | WA | CAT | 85 |  | LO2121 | Cat 992K | Park Brake |  | 33290 | 18000 | 2026-09-24 | 11 |  | 16594 | 2021-08-31 | THIESS MANAGED
N7065 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | Pump Hoist/ Brk Cooling |  | 60498 | 16000 | 2026-09-24 | 15 |  | 46278 | 2020-02-04 |  | 10R-7967 | PUMP GP
N0300-H | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 5373 | 2500 | 2026-09-25 | 13 |  | 4430 | 2025-08-15
N1490 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Cam Shaft Inspection |  | 12951 | 2000 | 2026-09-25 | 14 |  | 12634 | 2026-04-28 | 45821 | 449-9059 | SEAL
N9050-LW | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Starter Motor LOWER |  | 58874 | 10000 | 2026-09-26 | 13.75 |  | 50543 | 2024-07-12
N0111-5R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 5 RIGHT |  | 46731 | 8000 | 2026-09-26 | 16 |  | 40669 | 2023-09-13 |  | 309-7678 | ROLLER GP-DF
N0100-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Track Group LEFT |  | 31190.5 | 2000 | 2026-09-26 | 12 |  | 30646 | 2026-04-11
N9050-UP | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Starter Motor UPPER |  | 58874 | 10000 | 2026-09-26 | 13.75 |  | 50543 | 2024-07-12
N0100-R | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Track Group RIGHT |  | 31190.5 | 2000 | 2026-09-26 | 12 |  | 30646 | 2026-04-11
N0621-L | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 786 | 2500 | 2026-09-27 | 14 |  | 0 | 2024-11-12 |  | 565-3200 | PULL DOWN ROPE
N7474-L | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Hyd Cyl Hoist LEFT |  | 67600 | 24000 | 2026-09-27 | 17 | 15/08/2026 | 45679 | 2018-09-23 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N0620-R | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 786 | 2500 | 2026-09-27 | 14 |  | 0 | 2024-11-12 |  | 565-3199 | PULL DOWN ROPE
N0620-L | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 786 | 2500 | 2026-09-27 | 14 |  | 0 | 2024-11-12 |  | 565-3199 | PULL DOWN ROPE
N0621-R | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 786 | 2500 | 2026-09-27 | 14 |  | 0 | 2024-11-12 |  | 565-3200 | PULL DOWN ROPE
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Air Cond'r-Serv |  | 39200 | 5000 | 2026-09-28 | 14 |  | 35926 | 2022-08-17 |  | 385-0244 | MOTOR,BLOWER
N0201-01 | WA | CAT | 95 |  | RD4973 | Cat 789C | A Frame Bearing Reshim Initial |  | 262 | 2000 | 2026-09-29 | 14 |  | 0
N0105-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Idler RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-5L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 5 LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0105-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Idler LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-1L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 1 LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-2L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 2 LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0104-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Sprockets RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-4L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 4 LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-8R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 8 RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-9R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 9 RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0111-2R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 2 RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N7514-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Ripper Pitch LEFT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9641 | CYL, RIPPER, TILT, D10
N0111-1R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 1 RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0104-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Sprockets LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N0300-R | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Feed Chain RIGHT |  | 18065 | 2000 | 2026-09-29 | 13 |  | 17676 | 2026-03-25
N7510-R | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Ripper Lift RIGHT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9631 | CYL, RIPPER, LIFT, RH, D10
N0121-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Carrier Roller No 1 LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N7510-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Ripper Lift LEFT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9632 | CYL, RIPPER, LIFT, LH, D10
N0111-3L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 3 LEFT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N7514-R | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Ripper Pitch RIGHT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9641 | CYL, RIPPER, TILT, D10
N7420-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Blade Lift LEFT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9809 | BLADE LIFT CYLINDER
N7421-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Blade Tilt LEFT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9634 | Tilt Cylinder
N0111-4R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 4 RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N7420-R | WA | CAT | 85 |  | DZ3431 | Cat D10T | Hyd Cyl Blade Lift RIGHT |  | 32356 | 8000 | 2026-09-29 | 11 |  | 25721 | 2023-09-29 | THIESS MANAGED | 20R-9809 | BLADE LIFT CYLINDER
N0111-3R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Track Roller 3 RIGHT |  | 32622 | 14000 | 2026-09-29 | 13.79 |  | 20330 | 2022-07-01
N1490 | WA | CAT | 01 |  | RD2642 | Cat 773F | Cam Shaft Inspection |  | 27652 | 1500 | 2026-09-30 | 12 |  | 27656 | 2025-11-11
N6061 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Oil Cooler Front Brakes |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 10R-5673 | CORE AS OIL
N7542-L | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Cyl Steer LEFT |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 20R-5304 | STEER CYL
N3028 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Drive Shaft T/C - Trans |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 11R-1790 | SLIP JOINT GP
N7542-R | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Cyl Steer RIGHT |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 20R-5304 | STEER CYL
N6062-RE | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 10R-5675 | CORE AS OIL
N6062-F | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 10R-5675 | CORE AS OIL
N1002 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Engine Valve Adj |  | 8398 | 3000 | 2026-09-30 | 12 |  | 6893 | 2026-01-11
N2000 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Transmission |  | 78363 | 20000 | 2026-09-30 | 14 |  | 60119 | 2022-10-19 |  | 10R-4469 | TRANSMISSION, 793D
N0020 | WA | CAT | 85 |  | LO2121 | Cat 992K | Bucket |  | 33290 | 12000 | 2026-10-01 | 11 |  | 22677 | 2025-03-29 | THIESS MANAGED
N8995 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Operator Seat |  | 59517 | 6000 | 2026-10-01 | 18.5 | 29/09/2026 | 55851 | 2025-11-10
N7113 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Motor Emergency Steering |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N2002 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Oil Cooler - Transmission |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N2000 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Transmission |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16717.9 | 2022-09-17
N7232 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Motor Engine Fan |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N7155 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Pump Main |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N8200-02 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Ride Strut POS 2 |  | 64591.2 | 20000 | 2026-10-02 | 13.75 |  | 46331 | 2020-12-18
N2050 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Torque Convertor |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N7121 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Pump Steering/Braking |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N7610 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Hyd Cooler Core |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N1000 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Engine |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N1310 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Radiator |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N7041 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Pump Cooling Fan Engine |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N1312-L | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Aftercooler Core - LEFT |  | 31190.5 | 16000 | 2026-10-02 | 12 |  | 16710.94 | 2022-09-17
N8200-02 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Ride Strut POS 2 |  | 64591.2 | 20000 | 2026-10-02 | 13.75 |  | 46331 | 2020-12-18
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Jockey Pulley Brgs |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 4S-5367 | BUSHING
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Fan Pulley Brgs |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 6Y-7651 | CONE BEARING
N1420 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Air Compressor |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 0R-9626 | COMPRESSOR GP -B
N1004 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Engine Midlife |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28
N1402 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Fan Pulley Brgs |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-10 |  | 105-2273 | FAN HUB PULLEY,789
N1004 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Engine Midlife |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28
N1403 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Jockey Pulley Brgs |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-10 |  | 4S-5367 | BUSHING AS
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Cooling Sys Service |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 418-4162 | REGULATOR
N1100-RF | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Turbo Primary RHT FRONT |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-07 |  | 20R-6651 | RE-MAN TURBO GP
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | A/C Compressor |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Alternator |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 10R-8755 | ALTERNATOR GP_B
N1100-LF | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Turbo Primary LFT FRONT |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-07 |  | 20R-6651 | RE-MAN TURBO GP
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | A/C Compressor |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Jockey Pulley Brgs |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 4S-5367 | BUSHING
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Alternator |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 10R-8755 | ALTERNATOR GP_B
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Fuel Transfer Pump |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 10R-9838 | PUMP GP-F XFR
N9500 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Air Cond'r-Serv |  | 52003.6 | 0 | 2026-10-03 | 12 |  | 50098 | 2025-10-03
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Turbo Primary RIGHT |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 20R-3423 | TURBO GRP
N1100-LR | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Turbo Primary LFT REAR |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-07 |  | 20R-6651 | RE-MAN TURBO GP
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Turbo Primary RIGHT |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 20R-3423 | TURBO GRP
N1202 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Fuel Transfer Pump |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-09 |  | 10R-9838 | PUMP GP-F XFR
N1002 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Engine Valve Adj |  | 65303 | 4000 | 2026-10-03 | 18.5 |  | 63679 | 2026-03-04
N6200-LR | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Press Converter LEFT REAR |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-12 |  | 8W-3405 | CHAMBER, BRAKE
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Air Cond'r-Serv |  | 86119 | 5000 | 2026-10-03 | 18.5 |  | 83491 | 2025-12-04 |  | 385-0244 | MOTOR AS-BLOWER
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Fuel Transfer Pump |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 10R-9838 | PUMP GP-F XFR
N9501 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | A/C Compressor |  | 46895 | 7500 | 2026-10-03 | 13.5 |  | 41129 | 2024-10-05 |  | 106-5122 | COMPRESSOR
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Cooling Sys Service |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 418-4162 | REGULATOR
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Turbo Primary LEFT |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 20R-3423 | TURBO GRP
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Turbo Primary LEFT |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 20R-3423 | TURBO GRP
N3029 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Uni's T/C - Trans |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-15 |  | 363-1923 | MAIN DRIVESHAFT UNI
N6200-RR | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Press Converter RIGHT REAR |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-12 |  | 8W-3405 | CHAMBER, BRAKE
N1420 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Air Compressor |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 0R-9626 | COMPRESSOR GP -B
N9500 | WA | CAT | 85 | Iron Bridge | GR1528 | Cat 14M | Air Cond'r-Serv |  | 3973 | 5000 | 2026-10-03 | 8 |  | 0
N6200-F | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Press Converter FRONT |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-12 |  | 8W-3405 | CHAMBER, BRAKE
N1100-RR | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Turbo Primary RHT REAR |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-08 |  | 20R-6651 | RE-MAN TURBO GP
N1300 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Cooling Sys Service |  | 60138 | 10000 | 2026-10-03 | 15 |  | 52062 | 2021-03-10 |  | 418-4162 | REGULATOR TE
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Fan Pulley Brgs |  | 44852.3 | 10000 | 2026-10-03 | 15 |  | 36775 | 2021-09-28 |  | 6Y-7651 | CONE BEARING
N9500-MA | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Air Cond'r-Serv - MAJOR |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 137-2134 | AIR CON GP
N4102-04 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Axle Shaft - POS 4 |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 8W-8739 | AXLE (RH)
N7657-F | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Hyd Accum Steering FRONT |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N4102-03 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Axle Shaft - POS 3 |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 8W-8741 | AXLE (LH)
N0520 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Pre Lube Pump |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 20R-3396 | PRE-LUBE PUMP
N9500 | WA | EPI | 85 | Iron Bridge | DR3153 | Epiroc D65 XLF MKII | Air Cond'r-Serv |  | 1450 | 3000 | 2026-10-04 | 12 | 04/09/2026 | 0 | 2025-05-14
N1000 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Engine |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 175-5289 | FLEXI ENGINE
N1430 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Air Starter |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06
N1002 | WA | EPI | 85 | Iron Bridge | DR3153 | Epiroc D65 XLF MKII | Engine Valve Adj |  | 1450 | 3000 | 2026-10-04 | 12 |  | 0 | 2025-05-14
N8200-01 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Ride Strut POS 1 |  | 60138 | 20000 | 2026-10-04 | 15 |  | 42079 | 2019-05-06 |  | 347-7423 | SUSP CYL
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3153 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 1450 | 3000 | 2026-10-04 | 12 | 04/09/2026 | 0 | 2025-05-14
N1002 | WA | CAT | 85 | McPhee Creek | RD6623 | Cat 777 | Engine Valve Adj |  | 1958.65 | 3000 | 2026-10-05 | 8 |  | 0 | 2024-05-21
N0200 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | A Frame Bearing |  | 60498 | 20000 | 2026-10-05 | 15 |  | 42445 | 2019-07-06 |  | 6V-0444 | BEARING
N7035 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Pump Hoist, Brk Charge/Cooling |  | 61931 | 18000 | 2026-10-05 | 18.5 |  | 46327 | 2021-09-27
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Engine Valve Adj |  | 64653 | 4000 | 2026-10-05 | 14 |  | 62475 | 2023-12-01 |  | 272-0760 | SEAL-PIP
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Uni's T/C - Trans |  | 39658.4 | 10000 | 2026-10-05 | 15 |  | 31605 | 2021-09-24 |  | 8R-7036 | SPIDER
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Uni's T/C - Trans |  | 39658.4 | 10000 | 2026-10-05 | 15 |  | 31605 | 2021-09-24 |  | 8R-7036 | SPIDER
N1002 | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Engine Valve Adj |  | 2161 | 4000 | 2026-10-06 | 14 |  | 0 | 2026-02-12 |  | 449-9059 | SEAL
N1002 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Engine Valve Adj |  | 17257 | 3750 | 2026-10-06 | 14 | 16/07/2026 | 15347 | 2025-09-29 |  | 449-9059 | SEAL
N0104-L | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Sprockets LEFT |  | 2161 | 4000 | 2026-10-06 | 14 |  | 0 | 2026-02-12
N0102-R | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Trk Chn Pin & Bush Trn RIGHT |  | 2161 | 4000 | 2026-10-06 | 14 |  | 0 | 2026-02-12 |  | 569-2544 | TRACK GP
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Engine Valve Adj |  | 50845.5 | 4000 | 2026-10-06 | 13.75 |  | 48641 | 2025-09-26
N0102-L | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Trk Chn Pin & Bush Trn LEFT |  | 2161 | 4000 | 2026-10-06 | 14 |  | 0 | 2026-02-12 |  | 569-2544 | TRACK GP
N0104-R | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Sprockets RIGHT |  | 2161 | 4000 | 2026-10-06 | 14 |  | 0 | 2026-02-12
N8995 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Operator Seat |  | 76600 | 6000 | 2026-10-07 | 14 |  | 72455 | 2025-07-10 |  | 384-6168 | SEAT GP-SUSPENSION
N3210-06 | WA | CAT | 85 |  | GR1550 | Cat 16M | Tandem Drive Chain POS 6 |  | 27110.6 | 14000 | 2026-10-08 | 10 |  | 14442 | 2022-03-14
N6030-F | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Brake Slack Adj FRONT |  | 70598 | 16000 | 2026-10-08 | 18.5 | 25/09/2026 | 57060 | 2024-04-27
N1002 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Engine Valve Adj |  | 62609 | 4000 | 2026-10-08 | 12 | 04/11/2025 | 60206 | 2025-11-10 |  | 449-9059 | SEAL
N3210-05 | WA | CAT | 85 |  | GR1550 | Cat 16M | Tandem Drive Chain POS 5 |  | 27110.6 | 14000 | 2026-10-08 | 10 |  | 14442 | 2022-03-14
N3300-RE | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Circle Drive Box REAR |  | 14603 | 12000 | 2026-10-08 | 16 |  | 4727 | 2023-10-16
N7514-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Cyl Ripper Pitch RIGHT |  | 46731 | 25000 | 2026-10-09 | 16 |  | 23867 | 2019-01-17 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N7514-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Cyl Ripper Pitch LEFT |  | 46731 | 25000 | 2026-10-09 | 16 |  | 23867 | 2019-01-17 |  | 20R-9641 | CYL, RIPPER, TILT, D10
N0620-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 16307 | 2500 | 2026-10-09 | 14 |  | 15677 | 2026-04-18 |  | 565-3199 | PULL DOWN ROPE
N2000 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Transmission |  | 34410.8 | 16000 | 2026-10-09 | 6.35 |  | 19264 | 2020-08-19
N8995 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Operator Seat |  | 60138 | 6000 | 2026-10-09 | 15 |  | 56154 | 2022-08-18 |  | 384-6168 | SEAT GP
N6030-RE | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Brake Slack Adj REAR |  | 61931 | 16000 | 2026-10-09 | 18.5 |  | 48409 | 2023-10-31
N0300-R | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Feed Chain RIGHT |  | 17835 | 2000 | 2026-10-09 | 13 |  | 17573 | 2026-04-26 | SCHEDULED FOR 30/03
N0621-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 16307 | 2500 | 2026-10-09 | 14 |  | 15677 | 2026-04-18 |  | 565-3200 | PULL DOWN ROPE
N0621-R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 16307 | 2500 | 2026-10-09 | 14 |  | 15677 | 2026-04-17 |  | 565-3200 | PULL DOWN ROPE
N0620-L | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 16307 | 2500 | 2026-10-09 | 14 |  | 15677 | 2026-04-17 |  | 565-3199 | PULL DOWN ROPE
N3029 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Uni's T/C - Trans |  | 71898 | 8000 | 2026-10-10 | 18.5 | 20/10/2026 | 66390 | 2025-07-29
N1000 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Engine |  | 20661 | 12000 | 2026-10-10 | 12 |  | 10282 | 2023-11-20
N7594 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Cyl Dust Hood |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-20
N7426 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Cyl Boom Lift |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-19
N1320 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Cooling Fan Engine |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-22
N7627 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Valve Track Oscillation |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-21
N8995 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Operator Seat |  | 79726 | 6000 | 2026-10-11 | 18.5 | 25/10/2026 | 76243 | 2025-09-29 |  | 384-6168 | SEAT GP-SUSPENSION
N1310 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Radiator |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-22
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Air Cond'r-Serv |  | 52309.6 | 5000 | 2026-10-11 | 13 |  | 49079 | 2024-08-27
N1312 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Aftercooler Core |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-22
N7008-02 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Pump Hydraulic POS 2 |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-24
N7008-03 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Pump Hydraulic POS 3 |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-24
N7039 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Pump Cooler Fan Hyd/Eng |  | 20661 | 12000 | 2026-10-11 | 12 |  | 10287 | 2023-11-21
N3021 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Uni's Eng - Pump Drive |  | 53351 | 10000 | 2026-10-12 | 12 |  | 44991 | 2023-02-15
N0201-01 | WA | CAT | 95 |  | RD4975 | Cat 789C | A Frame Bearing Reshim Initial |  | 84 | 2000 | 2026-10-12 | 14 |  | 0
N3029 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Uni's T/C - Trans |  | 53351 | 10000 | 2026-10-12 | 12 |  | 44991 | 2023-02-15 |  | 8R-7036 | SPIDER
N9020 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Alternator |  | 26541 | 8000 | 2026-10-12 | 12.5 |  | 20254 | 2025-03-14
N8995 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Operator Seat |  | 45967 | 6000 | 2026-10-13 | 12 |  | 41626 | 2025-02-14
N9500 | WA | CAT | 85 |  | DZ3431 | Cat D10T | Air Cond'r-Serv |  | 32356 | 4000 | 2026-10-13 | 11 |  | 29878 | 2025-01-01 | THIESS MANAGED
N9500 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Air Cond'r-Serv |  | 26206.72 | 0 | 2026-10-13 | 13.5 |  | 23161.21 | 2025-10-13
N7474-R | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Cyl Hoist RIGHT |  | 78363 | 40000 | 2026-10-14 | 14 |  | 40303 | 2018-05-28 |  | 295-5708 | CYLINDER GP
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Hyd Cyl Hoist LEFT |  | 52712 | 24000 | 2026-10-14 | 13.75 |  | 30620 | 2020-06-09
N0099 | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | Grease Safety Valve |  | 22613 | 2000 | 2026-10-14 | 12 |  | 22285 | 2026-03-17
N7021 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Pump Brake Cooling |  | 78363 | 40000 | 2026-10-14 | 14 |  | 40303 | 2018-05-28 |  | 20R-7440 | PUMP GP-GEAR
N7474-L | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Hyd Cyl Hoist LEFT |  | 78363 | 40000 | 2026-10-14 | 14 |  | 40303 | 2018-05-28 |  | 295-5708 | CYLINDER GP
N6020 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Park Brake |  | 34192 | 12000 | 2026-10-14 | 12 |  | 23863 | 2024-05-01
N1002 | WA | CAT | 85 | McPhee Creek | RD6624 | Cat 777 | Engine Valve Adj |  | 1889.7 | 3000 | 2026-10-14 | 8 |  | 0 | 2024-05-21
N9500 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv |  | 18065 | 0 | 2026-10-14 | 13 |  | 15939 | 2025-10-14
N7620 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Rotary Joint |  | 34291 | 2000 | 2026-10-15 | 13.79 |  | 34227 | 2026-05-10
N0300 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Feed Chain |  | 34291 | 2000 | 2026-10-15 | 13.79 |  | 34227 | 2026-05-10
N0300-C | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Feed Chain CENTRE |  | 34291 | 2000 | 2026-10-15 | 13.79 |  | 34227 | 2026-05-10
N0200 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | A Frame Bearing |  | 39200 | 20000 | 2026-10-15 | 14 |  | 21159 | 2018-06-14
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Press Converter RIGHT REAR |  | 64230 | 10000 | 2026-10-16 | 14 |  | 56210 | 2024-03-21 |  | 8W-3405 | CHAMBER, BRAKE
N7620 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Rotary Joint |  | 32622 | 2000 | 2026-10-16 | 13.79 | 25/05/2026 | 32567 | 2026-05-25
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Press Converter LEFT REAR |  | 64230 | 10000 | 2026-10-16 | 14 |  | 56210 | 2024-03-21 |  | 8W-3405 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Press Converter FRONT |  | 64230 | 10000 | 2026-10-16 | 14 |  | 56210 | 2023-03-21 |  | 8W-3405 | CHAMBER, BRAKE
N7100 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Pump Charge |  | 34679 | 9000 | 2026-10-17 | 14 | 03/09/2026 | 27664 | 2024-10-14 |  | 20R-0943 | PUMP GP-PS-BSC-V
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Ride Strut POS 1 |  | 75619 | 24000 | 2026-10-17 | 19 |  | 54311 | 2020-12-28 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N7570-LF | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT FRO |  | 17257 | 10000 | 2026-10-17 | 14 |  | 9238 | 2025-08-13 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N1002 | WA | CAT | 19 | McPhee Creek | DR1080 | Cat MD6250 | Engine Valve Adj |  | 444 | 3000 | 2026-10-17 | 18 |  | 0
N1002 | WA | CAT | 85 | McPhee Creek | RD6603 | Cat 789D | Engine Valve Adj |  | 7161 | 4000 | 2026-10-17 | 11.19 |  | 4744.8 | 2024-06-13
N1002 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Engine Valve Adj |  | 49898.9 | 2500 | 2026-10-18 | 10 |  | 48832 | 2025-11-27 |  | 229-5711 | SEAL-VALVE COVER
N7032-02 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Cooler Fan Hyd POS 2 |  | 55435 | 16000 | 2026-10-18 | 18.5 |  | 42080 | 2023-04-06
N7032-04 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Cooler Fan Hyd POS 4 |  | 55435 | 16000 | 2026-10-18 | 18.5 |  | 42080 | 2023-04-06
N0300-PD | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 7661 | 3000 | 2026-10-19 | 12 | 22/09/2026 | 6384 | 2026-01-14
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | A Frame Bearing Reshim Initial |  | 59952 | 2000 | 2026-10-19 | 14 |  | 59961 | 2026-04-07
N1310 | NT | CAT | 01 | FleetCo | DZ1746 | Cat D10T | Radiator |  | 53910 | 15000 | 2026-10-19 | 12 |  | 40633.2 | 2019-08-29 |  | 371-6833 | RADIATOR AR
N9500 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Air Cond'r-Serv |  | 50673 | 5000 | 2026-10-19 | 14 |  | 47690 | 2025-10-19
N1002 | SA | CAT | 01 | Prominent Hill | GR0996 | Cat 16H | Engine Valve Adj |  | 41788 | 2000 | 2026-10-19 | 0.75 |  | 39896 | 2023-11-13
N1002 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Engine Valve Adj |  | 7661 | 3000 | 2026-10-19 | 12 |  | 6384 | 2026-01-13
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | A Frame Bearing Reshim Initial |  | 64230 | 2000 | 2026-10-19 | 14 |  | 64242 | 2026-03-26
N1002 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Engine Valve Adj |  | 54428 | 4000 | 2026-10-20 | 17 |  | 52899 | 2025-11-26
N0111-1R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Roller 1 RIGHT |  | 45807 | 8000 | 2026-10-20 | 14 |  | 39843 | 2023-11-08 |  | 309-7678 | ROLLER GP-DF
N7570-LR | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT REA |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N0111-5R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 5 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-5L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 5 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-4R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 4 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7467-LU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension LU |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N7541 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Access Ladder |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6798 | CYL GP-076 3
N7330-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Travel LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 20R-9462 | MOTOR GP
N0112-2L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 12 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-2R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 12 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-3R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 13 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7528-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Hyd Op Bit Basket RIGH |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6805 | CYL GP-127 1
N0112-0R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 10 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N1320 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Cooling Fan Engine |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 392-4160 | SPIDER-AS-FAN
N1312-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Aftercooler Core - RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 523-8685 | CORE AS-AFTC
N7527-F | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain FRONT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6795 | CYL GP-127 1
N7521 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Pipe Positioner Swing |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6798 | CYLINDER GP
N0112-4R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 14 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 8 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 8 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7524-RE | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - REAR |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N0111-9L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 9 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 10 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7524-FR | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - FRONT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N7522 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Pipe Positioner Clamp |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-8999 | CYLINDER GP
N1312-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Aftercooler Core - LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 523-8685 | CORE AS-AFTC
N0112-4L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 14 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 11 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0121-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Carrier Roller No 1 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-7R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 7 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7467-LL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension LL |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0111-6L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 6 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Carrier Roller No 2 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-6R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 6 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7528-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Hyd Op Bit Basket LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6805 | CYL GP-127 1
N7330-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Travel RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 20R-9462 | MOTOR GP
N0330 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Drifter |  | 16244 | 0 | 2026-10-21 | 9.59 | 01/07/2026 | 0 | 2025-07-27
N0121-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Carrier Roller No 1 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7527-RE | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain REAR |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6795 | CYL GP-127 1
N0111-9R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 9 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7467-RL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension RL |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0112-1L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 11 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7460 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Feed |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-9005X | MD6310 P/DOWN CYL
N7467-RU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension RU |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0111-7L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 7 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0122-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Carrier Roller No 2 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7587 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Deck Inspection Hatch |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 548-0995 | CYL GP-051 0
N7600-LL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Control Valve LEFT LOWER |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 517-7954 | VALVE GP-CONTROL
N0551 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Cooler Aircompressor |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-1356+527-8222 | CORE AS-OIL COOLER
N7598-LO | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing LOWER |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 539-1901 | CYL GP-127 1
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Engine Valve Adj |  | 57576 | 4000 | 2026-10-21 | 14 |  | 55626 | 2024-04-18 |  | 272-0760 | SEAL-PIP
N7598-UP | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing UPPER |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 539-1901 | CYL GP-127 1
N0111-4L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 4 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7600-LU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Control Valve LEFT UPPER |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 517-7953 | VALVE GP-CONTROL
N7600-LW | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Control Valve LOWER |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 517-7952 | VALVE GP-CONTROL
N7608 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Control Valve Jack/Mast Raise |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 514-2137 | VALVE GP-CONTROL
N7234-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Cooler Fan RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 526-3938 | MOTOR GP-PISTON
N7234-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Cooler Fan LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 526-3938 | MOTOR GP-PISTON
N7669 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Rod Catcher |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6798 | CYLINDER GP HYD
N8995 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Operator Seat |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 489-6525+436-8490 | SEAT GP
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Wheel Group POS 2 |  | 57576 | 20000 | 2026-10-21 | 14 |  | 39625 | 2020-10-30 |  | 328-8492 | WHEEL HUB BRK GRP, FRT, 789
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Wheel Bearing POS 2 |  | 57576 | 20000 | 2026-10-21 | 14 |  | 39625 | 2020-10-30 |  | 289-2131 | CONE-SPECIAL TAPERED
N0550 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Air End |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 541-8633 | COMPRESSOR G
N7201 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Air Con |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 419-0777 | MOTOR GP-PSF
N7100 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Charge |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 594-6741 | PUMP GP-GEAR
N7068 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Auxiliary |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 20R-9457 | PUMP GP-PISTON
N7542-L | WA | CAT | 85 |  | LO2122 | Cat 992K | Hyd Cyl Steer LEFT |  | 35037 | 12000 | 2026-10-21 | 11 |  | 24638 | 2024-01-03 | THIESS MANAGED
N8122-01 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Wheel Group POS 1 |  | 54428 | 20000 | 2026-10-21 | 17 |  | 36904 | 2020-11-17 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N7044 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Cooler Fan Hyd |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 392-4160 | SPIDER-AS-FAN
N7041 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Cooling Fan Engine |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 11R-1030 | PUMP GP-PISTON
N3320 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Drive Box |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 503-7615 | PUMP DRIVE,MD6310
N7524 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0
N7032 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Cooler Fan Hyd |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 11R-1030 | PUMP GP-PISTON
N7008-02 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Hydraulic POS 2 |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 20R-9460 | PUMP GP-PISTON
N7008-01 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pump Hydraulic POS 1 |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 20R-9460 | PUMP GP-PISTON
N5000-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Final Drive RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N5000-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Final Drive LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N3340 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Rotary Head |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 527-5344 | ROTARY HEAD, MD6310
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Brake POS 2 |  | 57576 | 20000 | 2026-10-21 | 14 |  | 39625 | 2020-10-30 |  | 257-6301 | BRAKE GROUP
N0101-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Chain LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N0112-3L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 13 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0105-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Idler RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0111-2L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 2 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7570-RR | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT REA |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N0111-1L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 1 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0140 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Equalizer Bar |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 526-3821 | BAR AS-EQUAL
N0134-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Adjuster LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0111-2R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 2 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0123-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Carrier Roller No 3 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0033-SC | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Water Tank - SECONDARY |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0
N0105-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Idler LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 248-7151 | IDLER GP
N0123-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Carrier Roller No 3 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N7581 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Swing |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-0146 | CYLINDER GP
N0134-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Adjuster RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 200-0409 | ADUSTER GP
N7582 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Clamp |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-0148 | CYLINDER GP
N7575 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Rotate |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 524-0147 | CYLINDER GP
N7595-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Mast Lock LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6795 | CYLINDER GP-HYDRAULIC -MAST LOCK
N7595-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Mast Lock RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 515-6795 | CYLINDER GP-HYDRAULIC -MAST LOCK
N0101-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Chain RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N1000 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Engine |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 5875935X | EXCHANGE ENGINE
N7592-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Mast Raise RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 450-7146X | MD6310 MAST RAISE CYL
N0111-1R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 1 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0111-3R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 3 RIGHT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N0033-PR | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Water Tank - PRIMARY |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0
N0111-3L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Track Roller 3 LEFT |  | 12951 | 15000 | 2026-10-21 | 14 |  | 0 |  |  | 528-2933 | ROLLER
N8200-04 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Ride Strut POS 4 |  | 60509.94 | 30000 | 2026-10-22 | 12.5 |  | 32352 | 2017-09-16
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Uni's Eng - Pump Drive |  | 58874 | 10000 | 2026-10-22 | 13.75 |  | 50896 | 2024-08-15
N8442-03 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 3 |  | 47332.5 | 10000 | 2026-10-23 | 7.13 |  | 38389 | 2021-11-10
N7542-R | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Steer RIGHT |  | 27110.6 | 8000 | 2026-10-23 | 10 |  | 20586 | 2023-09-16
N8442-01 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 1 |  | 47332.5 | 10000 | 2026-10-23 | 7.13 |  | 38389 | 2021-11-10
N8061 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Slew Ring Bolts Check |  | 23756 | 5000 | 2026-10-23 | 18.5 |  | 21502 | 2026-01-16
N7542-L | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Steer LEFT |  | 27110.6 | 8000 | 2026-10-23 | 10 |  | 20586 | 2023-09-16
N8442-02 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 2 |  | 47332.5 | 10000 | 2026-10-23 | 7.13 |  | 38389 | 2021-11-10
N8995 | NT | CAT | 01 | Idle Plant / Off Hired | RD1902 | Cat 785C XQ | Operator Seat |  | 46670 | 6000 | 2026-10-23 | 11.43 |  | 42358 | 2019-11-06 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8442-04 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 4 |  | 47332.5 | 10000 | 2026-10-23 | 7.13 |  | 38389 | 2021-11-10
N1310 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Radiator |  | 76600 | 18000 | 2026-10-24 | 14 |  | 60684 | 2023-03-08 |  | 334-6025 | RADIATOR COOLING GP
N7072-00 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Pump Imp 2 |  | 5943 | 8000 | 2026-10-24 | 13.79 | 29/09/2026 | 0 | 2025-04-19
N7581 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Hyd Cyl Breakout Wrench Swing |  | 5943 | 8000 | 2026-10-24 | 13.79 | 29/09/2026 | 0 | 2025-04-19
N7232 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Hyd Motor Engine Fan |  | 76600 | 18000 | 2026-10-24 | 14 |  | 60684 | 2023-03-08 |  | 10R-5466 | MOTOR GP - HYD FAN
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | A Frame Bearing Reshim Initial |  | 45745.5 | 2000 | 2026-10-24 | 13 |  | 45677 | 2026-02-21 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N1420 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Air Compressor |  | 18065 | 20000 | 2026-10-24 | 13 |  | 0 | 2022-06-01
N7073-00 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Pump Imp 3 |  | 5943 | 8000 | 2026-10-24 | 13.79 | 29/09/2026 | 0 | 2025-04-19
N9500 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 17257 | 4000 | 2026-10-24 | 14 | 16/07/2026 | 15347 | 2025-10-02
N3029 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Uni's T/C - Trans |  | 78363 | 10000 | 2026-10-24 | 14 |  | 70452 | 2024-11-19 |  | 598-2864 | SPIDER & BEARING AS
N1002 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Engine Valve Adj |  | 1658 | 3750 | 2026-10-24 | 14 |  | 0 | 2024-11-12 |  | 449-9059 | SEAL
N7071-00 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Pump Imp 1 |  | 5943 | 8000 | 2026-10-24 | 13.79 | 29/09/2026 | 0 | 2025-04-19
N9500-MA | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Air Cond'r-Serv - MAJOR |  | 76600 | 18000 | 2026-10-24 | 14 |  | 60684 | 2023-03-08 |  | 137-2134 | AIR CONDITIONER GP
N7340 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Hyd Motor Feed |  | 5943 | 8000 | 2026-10-24 | 13.79 | 29/09/2026 | 0 | 2025-04-19
N8995 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Operator Seat |  | 65303 | 6000 | 2026-10-25 | 18.5 |  | 62077 | 2025-11-04
N0621-L | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Pullback Rope LEFT |  | 2718 | 5000 | 2026-10-25 | 15.2 | 09/09/2026 | 0 | 2025-02-01
N0621-R | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Pullback Rope RIGHT |  | 2718 | 5000 | 2026-10-25 | 15.2 | 09/09/2026 | 0 | 2025-02-01
N8122-02 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Wheel Group POS 2 |  | 62083 | 22000 | 2026-10-27 | 18.5 |  | 42900 | 2021-09-14
N9500 | WA | CAT | 01 |  | RD2642 | Cat 773F | Air Cond'r-Serv |  | 27652 | 5000 | 2026-10-27 | 12 |  | 24471 | 2024-06-21
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4235 | Cat 789C | Pump Hoist/ Brk Cooling |  | 63637 | 16000 | 2026-10-27 | 14 |  | 49772 | 2020-10-10 |  | 10R-7967 | PUMP GP
N8122-01 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Wheel Group POS 1 |  | 62083 | 22000 | 2026-10-27 | 18.5 |  | 42900 | 2021-09-14
N8200-02 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Ride Strut POS 2 |  | 62083 | 22000 | 2026-10-27 | 18.5 |  | 42900 | 2021-09-14
N6000-02 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Brake POS 2 |  | 62083 | 22000 | 2026-10-27 | 18.5 |  | 42900 | 2021-09-14
N8441 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Rear Axle Dog Bone |  | 54979 | 25000 | 2026-10-27 | 14 |  | 32110 | 2019-02-02
N6000-01 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Brake POS 1 |  | 62083 | 22000 | 2026-10-27 | 18.5 |  | 42900 | 2021-09-14
N8995 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Operator Seat |  | 67572 | 6000 | 2026-10-27 | 15 |  | 63851 | 2021-09-04 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8200-02 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Ride Strut POS 2 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N6000-02 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Brake POS 2 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 10R-5394 | BRAKE, FRT, 793
N6000-01 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Brake POS 1 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 10R-5394 | BRAKE, FRT, 793
N6030-F | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Brake Slack Adj FRONT |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 590-2533 | SLACK ADJUSTER GP
N5020-01 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Wheel Bearing POS 1 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 446-0367 | KIT
N8122-01 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Wheel Group POS 1 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N8122-02 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Wheel Group POS 2 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N6061 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Oil Cooler Front Brakes |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 10R-5673 | CORE AS OIL
N5020-02 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Wheel Bearing POS 2 |  | 79726 | 24000 | 2026-10-28 | 18.5 |  | 58553 | 2022-07-17 |  | 446-0367 | KIT
N2090 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Drv Coupling |  | 21277 | 5000 | 2026-10-29 | 14 |  | 18436 | 2025-10-18 |  | 520-7010 | COUPLING GP-
N3029 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Uni's T/C - Trans |  | 61931 | 8000 | 2026-10-29 | 18.5 |  | 56780 | 2025-08-20
N2435 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 21277 | 5000 | 2026-10-29 | 14 |  | 18436 | 2025-10-18 |  | 553-9494 | ELEMENT
N2050 | WA | CAT | 85 |  | LO2121 | Cat 992K | Torque Convertor |  | 33290 | 18000 | 2026-10-29 | 11 |  | 16983 | 2021-10-11 | THIESS MANAGED
N3321 | WA | CAT | 85 |  | LO2121 | Cat 992K | Pump Drive |  | 33290 | 18000 | 2026-10-29 | 11 |  | 16983 | 2021-10-11 | THIESS MANAGED
N7434-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Bucket Clam LEFT |  | 23402 | 5000 | 2026-10-30 | 18.5 |  | 21272 | 2026-02-03
N2002 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Oil Cooler - Transmission |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 0R-3344 | COOLER, OIL, CORE, REMAN
N0520 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pre Lube Pump |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 116-7153 | PUMP & MOTOR, PRELUBE, ASSY
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Oil Cooler - Brakes FRONT |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 10R-0817 | CORE GP-O CLR
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Transmission Pump |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-06 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N0201-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4376 | Cat 785C | A Frame Bearing Reshim Initial |  | 66519 | 2000 | 2026-10-31 | 13 |  | 66550 | 2026-04-22 |  | 8X-0570 | SHIM PACK (INCLUDES 33-SHIMS)
N0520 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pre Lube Pump |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 116-7153 | PUMP & MOTOR, PRELUBE, ASSY
N2002 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Oil Cooler - Transmission |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 0R-3344 | COOLER, OIL, CORE, REMAN
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pump Drive Box |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 6V-8260 | SEAL,O-RING
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Oil Cooler - Brakes FRONT |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 10R-0817 | CORE GP-O CLR
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Transmission Pump |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-06 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pump Drive Box |  | 39658.4 | 20000 | 2026-10-31 | 15 |  | 22005 | 2019-02-11 |  | 6V-8260 | SEAL,O-RING
N4102-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Axle Shaft - POS 4 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17 |  | 6G-6407 | SHAFT-AXLE (RH)
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Drive Shaft T/C - Trans |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-28 |  | 10R-5186 | JOINT GP-SLIP
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Steering Y Piece |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Steering Linkage Group LEFT |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 2A-7217 | LINK,STEERING,785
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-16 |  | 322-7212 | BLOWER,ASSY
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Steering Linkage Group LEFT |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 2A-7217 | LINK,STEERING,785
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Steering Linkage Group RIGHT |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 2A-7217 | LINK,STEERING,785
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Steering Linkage Group RIGHT |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 2A-7217 | LINK,STEERING,785
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Brake POS 2 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-19 |  | 311-0517 | BRAKE, FRT, 785C
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-16 |  | 322-7212 | BLOWER,ASSY
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Axle Shaft - POS 3 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17 |  | 6G-6408 | SHAFT-AXLE (LH)
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Hyd Cyl Steer RIGHT |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 1U-3182 | CYL, STEERING, 785
N2000 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Transmission |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17 |  | 0R-4007 | TRANSMISSION, 789B 785C
N2000 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Transmission |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17 |  | 0R-4007 | TRANSMISSION, 789B 785C
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Hyd Cyl Steer RIGHT |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 1U-3182 | CYL, STEERING, 785
N4000 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Bevel Gear |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17
N4102-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Axle Shaft - POS 4 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17 |  | 6G-6407 | SHAFT-AXLE (RH)
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Drive Shaft T/C - Trans |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-28 |  | 10R-5186 | JOINT GP-SLIP
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pump Hoist/ Brk Cooling |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 10R-7971 | PUMP, HOIST, REMAN
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Final Drive POS 3 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-16
N5000-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Final Drive POS 4 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17
N0112-3R | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Track Roller 13 RIGHT |  | 16307 | 15000 | 2026-11-01 | 14 |  | 3509 | 2024-03-12 |  | 528-2933 | ROLLER
N5000-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Final Drive POS 4 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Wheel Bearing POS 2 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-19 |  | 293-1016 | KIT
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Wheel Bearing POS 2 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-19 |  | 293-1016 | KIT
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pump Hoist/ Brk Cooling |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20 |  | 10R-7971 | PUMP, HOIST, REMAN
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Wheel Group POS 2 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-19 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N4000 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Bevel Gear |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Final Drive POS 3 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-16
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Wheel Group POS 2 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-19 |  | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Axle Shaft - POS 3 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-17 |  | 6G-6408 | SHAFT-AXLE (LH)
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Brake POS 2 |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-19 |  | 311-0517 | BRAKE, FRT, 785C
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Steering Y Piece |  | 39658.4 | 20000 | 2026-11-01 | 15 |  | 22011 | 2019-02-20
N0145 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Pivot Shaft Brgs |  | 45807 | 15000 | 2026-11-02 | 14 |  | 33026 | 2020-11-29 |  | 7T-4135 | BEARING
N0300-PD | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Feed Chain PULLDOWN |  | 5373 | 3000 | 2026-11-02 | 13 |  | 4430 | 2025-08-15
N6030-RE | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Brake Slack Adj REAR |  | 67600 | 20000 | 2026-11-02 | 17 |  | 50292 | 2019-08-30 |  | 566-9766 | ADJUSTER GP
N7130-02 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Swing POS 2 |  | 55435 | 6000 | 2026-11-02 | 18.5 |  | 52364 | 2025-11-14
N6030-F | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Brake Slack Adj FRONT |  | 67600 | 20000 | 2026-11-02 | 17 |  | 50292 | 2019-08-30 |  | 566-9762 | SLACK ADJUSTER
N0134-R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Adjuster RIGHT |  | 45807 | 15000 | 2026-11-02 | 14 |  | 33026 | 2020-11-29
N7037 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Pump Conv P/Brake Release |  | 67600 | 20000 | 2026-11-02 | 17 |  | 50292 | 2019-08-30
N0134-L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Adjuster LEFT |  | 45807 | 15000 | 2026-11-02 | 14 |  | 33026 | 2020-11-29
N6060-F | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Oil Cooler - Brakes FRONT |  | 67600 | 20000 | 2026-11-02 | 17 |  | 50292 | 2019-08-30 |  | 10R-0817 | CORE GP-O CLR
N7570-RF | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT FRO |  | 14426 | 10000 | 2026-11-02 | 14 |  | 6640 | 2025-01-06 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N7605 | NT | CAT | 01 | FleetCo | RD1903 | Cat 785C XQ | Steering Hmu |  | 67600 | 20000 | 2026-11-02 | 17 |  | 50292 | 2019-08-25
N9500 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Air Cond'r-Serv |  | 25353 | 4000 | 2026-11-02 | 12.5 |  | 23334 | 2025-12-10
N7237 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Hyd Motor Rear Axle Cooler Fan |  | 77195 | 24000 | 2026-11-03 | 14 |  | 55425 | 2021-11-21 |  | 307-1504 | MOTOR
N6030-F | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Brake Slack Adj FRONT |  | 71548 | 20000 | 2026-11-03 | 15 |  | 53933 | 2020-09-30 |  | 590-2531 | SLACK ADJUSTER
N1002 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Engine Valve Adj |  | 55934 | 4000 | 2026-11-03 | 13.5 |  | 54081 | 2025-10-21 |  | 449-9059 | SEAL
N7542-L | WA | CAT | 01 |  | RD4247 | Cat 789C | Hyd Cyl Steer LEFT |  | 59268 | 20000 | 2026-11-03 | 20 |  | 42440 | 2020-09-13 |  | 30R-1082 | STEER CYL 789C
N1202 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Fuel Transfer Pump |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 10R-9838 | PUMP GP-F XFR
N3021 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Uni's Eng - Pump Drive |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-09
N1300 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Cooling Sys Service |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 418-4162 | REGULATOR
N1300 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Cooling Sys Service |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 418-4162 | REGULATOR
N6200-RR | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Press Converter RIGHT REAR |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-02 |  | 8X-7220 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Press Converter FRONT |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-02 |  | 8X-7220 | CHAMBER, BRAKE
N7542-R | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Hyd Cyl Steer RIGHT |  | 53598.82 | 20000 | 2026-11-05 | 13.5 |  | 35778 | 2022-05-06
N1202 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Fuel Transfer Pump |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 10R-9838 | PUMP GP-F XFR
N3021 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Uni's Eng - Pump Drive |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-09
N3029 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Uni's T/C - Trans |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-09 |  | 8R-7036 | SPIDER
N1100-L | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Turbo Primary LEFT |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 20R-3423 | TURBO GRP
N5003-03 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Final Drive Ext Life POS 3 |  | 69479 | 25000 | 2026-11-05 | 18.5 |  | 47451 | 2022-01-29
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Pump Hoist/ Brk Cooling |  | 64230 | 16000 | 2026-11-05 | 14 |  | 50490 | 2021-05-20 |  | 10R-7967 | PUMP GP
N1100-R | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Turbo Primary RIGHT |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 20R-3423 | TURBO GRP
N1420 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Air Compressor |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 0R-9626 | COMPRESSOR GP -B
N1004 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Engine Midlife |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11
N1420 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Air Compressor |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 0R-9626 | COMPRESSOR GP -B
N9020 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Alternator |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 10R-8755 | ALTERNATOR GP_B
N9020 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Alternator |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 10R-8755 | ALTERNATOR GP_B
N1004 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Engine Midlife |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11
N6200-LR | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Press Converter LEFT REAR |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-02 |  | 8X-7220 | CHAMBER, BRAKE
N1100-R | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Turbo Primary RIGHT |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 20R-3423 | TURBO GRP
N6200-RR | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Press Converter RIGHT REAR |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-02 |  | 8X-7220 | CHAMBER, BRAKE
N9501 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | A/C Compressor |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11
N3029 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Uni's T/C - Trans |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-09 |  | 8R-7036 | SPIDER
N1402 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Fan Pulley Brgs |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 6Y-7651 | CONE BEARING
N1402 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Fan Pulley Brgs |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 6Y-7651 | CONE BEARING
N1100-L | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Turbo Primary LEFT |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 20R-3423 | TURBO GRP
N1403 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Jockey Pulley Brgs |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 4S-5367 | BUSHING
N9501 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | A/C Compressor |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11
N1403 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Jockey Pulley Brgs |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-11 |  | 4S-5367 | BUSHING
N6200-LR | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Press Converter LEFT REAR |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-02 |  | 8X-7220 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Press Converter FRONT |  | 64591.2 | 10000 | 2026-11-05 | 13.75 |  | 56799 | 2023-08-02 |  | 8X-7220 | CHAMBER, BRAKE
N1002 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Engine Valve Adj |  | 59517 | 4000 | 2026-11-06 | 18.5 |  | 58508 | 2026-04-01
N7070 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Pump Implement |  | 62609 | 15000 | 2026-11-06 | 12 |  | 49556 | 2020-07-30 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 11R-1962 | PUMP GP-GR C
N6200-F | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Press Converter FRONT |  | 71548 | 10000 | 2026-11-07 | 15 |  | 63992 | 2021-06-17 |  | 8W-3405 | CHAMBER, BRAKE
N9502 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | A/C Condenser |  | 46895 | 15000 | 2026-11-07 | 13.5 |  | 34089 | 2023-01-06 |  | 103-9527 | CONDENSER GP
N8995 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Operator Seat |  | 71898 | 6000 | 2026-11-07 | 18.5 | 20/10/2026 | 68914 | 2025-12-16
N3021 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Uni's Eng - Pump Drive |  | 71548 | 10000 | 2026-11-07 | 15 |  | 63992 | 2021-06-20 |  | 108-6587 | BEARING,SPIDER
N3029 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Uni's T/C - Trans |  | 71548 | 10000 | 2026-11-07 | 15 |  | 63992 | 2021-06-20 |  | 363-1923 | MAIN DRIVESHAFT UNI
N8995 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Operator Seat |  | 55435 | 6000 | 2026-11-08 | 18.5 |  | 52476 | 2025-11-24
N1002 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Engine Valve Adj |  | 67791 | 4000 | 2026-11-08 | 18.5 |  | 66823 | 2026-04-08
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | Hyd Cyl Hoist LEFT |  | 59952 | 24000 | 2026-11-08 | 14 |  | 38247 | 2020-02-18 |  | 438-6225 | CYLINDER GP-HOIST
N1004 | WA | CAT | 85 | McPhee Creek | RD6603 | Cat 789D | Engine Midlife |  | 7161 | 9000 | 2026-11-08 | 11.19 |  | 0 | 2026-02-01
N1320 | WA | CAT | 85 | McPhee Creek | RD6603 | Cat 789D | Cooling Fan Engine |  | 7161 | 9000 | 2026-11-08 | 11.19 |  | 0 | 2026-02-01
N7090-03 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Pilot/Servo POS 3 |  | 55435 | 6000 | 2026-11-08 | 18.5 |  | 52476 | 2025-11-27
N7035 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Pump Hoist, Brk Charge/Cooling |  | 62083 | 18000 | 2026-11-08 | 18.5 |  | 47115 | 2023-10-27
N7090-04 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Pilot/Servo POS 4 |  | 55435 | 6000 | 2026-11-08 | 18.5 |  | 52476 | 2025-11-26
N2052 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Convertor/Trans Pump |  | 65569 | 18000 | 2026-11-09 | 18.5 |  | 50629 | 2023-10-27
N3320 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Pump Drive Box |  | 65569 | 18000 | 2026-11-09 | 18.5 |  | 50629 | 2023-10-27
N7035 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Pump Hoist, Brk Charge/Cooling |  | 65569 | 18000 | 2026-11-09 | 18.5 |  | 50629 | 2023-10-27
N8995 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Operator Seat |  | 18065 | 10000 | 2026-11-09 | 13 |  | 10209.22 | 2024-04-20
N2090 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Drv Coupling |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N3341 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N1210 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Fuel Injectors |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N0597 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N8200-04 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Ride Strut POS 4 |  | 54833.54 | 30000 | 2026-11-10 | 12.5 |  | 26906 | 2012-07-11
N7310-R | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Hyd Motor Rotation RIGHT |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N0302 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Feed Sprocket |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N7310-L | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Hyd Motor Rotation LEFT |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N0346 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N0596 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N7234 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N0350 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N8200-03 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Ride Strut POS 3 |  | 54833.54 | 30000 | 2026-11-10 | 12.5 |  | 26906 | 2012-07-11
N0558 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Air End Coupling |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N7232 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Hyd Motor Engine Fan |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N7151 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N7340 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N9501 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | A/C Compressor |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Pump Drive Box |  | 75619 | 20000 | 2026-11-10 | 19 |  | 69320 | 2024-12-09 |  | 11R-1519 | PUMP DRIVE, 793D, 793F
N1100 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Turbo Primary |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N1004 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Engine Midlife |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N1200 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Fuel Pump |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N9050 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Starter Motor |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N1300 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Cooling Sys Service |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N8995 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Operator Seat |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N9020 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Alternator |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N1301 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Water Pump |  | 4002 | 6000 | 2026-11-10 | 12 |  | 0 | 2025-05-14
N7001 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hydraulic Tune |  | 55435 | 4000 | 2026-11-10 | 18.5 |  | 54501 | 2026-04-07
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Radiator |  | 57617 | 20000 | 2026-11-11 | 20 |  | 40962 | 2020-09-10 |  | 145-1226 | PEX SX 789C RADIATOR
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 57617 | 20000 | 2026-11-11 | 20 |  | 40962 | 2020-09-10 |  | 230-4112 | UNIVERSAL JOINT GP
N1420 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Air Compressor |  | 17835 | 20000 | 2026-11-11 | 13 |  | 0 | 2022-06-01
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Hyd Cyl Hoist LEFT |  | 56457 | 24000 | 2026-11-11 | 14 |  | 34793 | 2018-05-02 |  | 438-6225 | CYLINDER GP-HOIST
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Air Starter |  | 57617 | 20000 | 2026-11-11 | 20 |  | 40962 | 2020-09-10
N0300-H | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Feed Chain HOIST |  | 22440 | 2500 | 2026-11-11 | 12 |  | 21946 | 2026-04-03
N9500 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Air Cond'r-Serv |  | 31190.5 | 0 | 2026-11-11 | 12 |  | 28781 | 2025-11-11
N9500 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 1658 | 4000 | 2026-11-11 | 14 |  | 0 | 2024-11-12
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Engine |  | 57617 | 20000 | 2026-11-11 | 20 |  | 40962 | 2020-09-10 |  | 175-5289 | FLEXI ENGINE
N1002 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Engine Valve Adj |  | 59732.1 | 4000 | 2026-11-12 | 13.75 |  | 58047 | 2025-11-07
N1002 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Engine Valve Adj |  | 59732.1 | 4000 | 2026-11-12 | 13.75 |  | 58047 | 2025-11-07
N1002 | WA | CAT | 85 |  | LO2122 | Cat 992K | Engine Valve Adj |  | 35037 | 3000 | 2026-11-13 | 11 |  | 33891 | 2026-02-27 | THIESS MANAGED
N7073-00 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Pump Imp 3 |  | 5650 | 8000 | 2026-11-14 | 13.79 |  | 0 | 2025-04-01
N1000 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Engine |  | 76600 | 18000 | 2026-11-14 | 14 |  | 60983 | 2023-04-09 |  | 488-8196 | 793D PEX ENGINE
N7340 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Hyd Motor Feed |  | 5650 | 8000 | 2026-11-14 | 13.79 |  | 0 | 2025-04-01
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Uni's T/C - Trans |  | 52712 | 10000 | 2026-11-14 | 13.75 |  | 45047 | 2024-05-11 |  | 8R-7036 | SPIDER
N7071-00 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Pump Imp 1 |  | 5650 | 8000 | 2026-11-14 | 13.79 |  | 0 | 2025-04-01
N7581 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Hyd Cyl Breakout Wrench Swing |  | 5650 | 8000 | 2026-11-14 | 13.79 |  | 0 | 2025-04-01
N7072-00 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Pump Imp 2 |  | 5650 | 8000 | 2026-11-14 | 13.79 |  | 0 | 2025-04-01
N6200-RR | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Press Converter RIGHT REAR |  | 53598.82 | 15000 | 2026-11-15 | 13.5 |  | 40905.94 | 2023-06-26
N1002 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | Engine Valve Adj |  | 60498 | 4000 | 2026-11-15 | 15 |  | 59059 | 2022-03-18 |  | 272-0760 | SEAL-PIP
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Hyd Cyl Steer RIGHT |  | 67187 | 20000 | 2026-11-15 | 14 |  | 49576 | 2020-04-19 |  | 30R-1082 | STEER CYL 789C
N6015-RF | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Brake Travel RHT FRONT |  | 55435 | 15000 | 2026-11-16 | 18.5 |  | 43626 | 2023-11-10 |  | 535-2916 / 535-0350 | TRAVEL BRAKE, 6060
N0102-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 55934 | 3000 | 2026-11-16 | 13.5 |  | 55250 | 2026-01-09
N7330-RR | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Motor Travel RHT REAR |  | 55435 | 15000 | 2026-11-16 | 18.5 |  | 43626 | 2023-11-10
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 58852 | 20000 | 2026-11-16 | 15 |  | 41425 | 2019-05-09 |  | 230-4112 | UNIVERSAL JOINT GP
N8995 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Operator Seat |  | 60870.4 | 10000 | 2026-11-17 | 13.5 |  | 53208.81 | 2024-08-16
N1100 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Turbo Primary |  | 14603 | 6000 | 2026-11-17 | 16 |  | 11367 | 2025-08-05 |  | 10R-8964 | TURBO 24M
N8200-03 | WA | CAT | 01 |  | RD4247 | Cat 789C | Ride Strut POS 3 |  | 59268 | 30000 | 2026-11-18 | 20 |  | 32750 | 2019-04-11 |  | 11R-1042 | CYL, SUSPENSION, REAR, 789 793
N7077-05 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Imp 7&8 |  | 23402 | 15000 | 2026-11-18 | 18.5 |  | 11620 | 2024-08-05
N9701 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | LiDAR Detection System |  | 17257 | 5000 | 2026-11-18 | 14 | 16/07/2026 | 14699 | 2025-08-19
N1002 | WA | CAT | 85 | McPhee Creek | RD6622 | Cat 777 | Engine Valve Adj |  | 1608.3 | 3000 | 2026-11-18 | 8 |  | 0 | 2024-05-21
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6198 | Cat 785D | Air Cond'r-Serv |  | 53598.82 | 0 | 2026-11-19 | 13.5 |  | 51753.76 | 2025-11-19
N0302 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Feed Sprocket |  | 16244 | 10000 | 2026-11-20 | 9.59 | 01/07/2026 | 7935.55 | 2022-07-29 | Nearest service to
N0621-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Rope RIGHT |  | 17257 | 2500 | 2026-11-20 | 14 | 28/05/2026 | 17223 | 2026-01-31 |  | 565-3200 | PULL DOWN ROPE
N0620-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Rope LEFT |  | 17257 | 2500 | 2026-11-20 | 14 | 28/05/2026 | 17223 | 2026-01-31 |  | 565-3199 | PULL DOWN ROPE
N1205 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Fuel Pump - High Pressure |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N1004 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Engine Midlife |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N1202 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Fuel Transfer Pump |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N1400-L | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Belt Tensioner Assy - LEFT |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N1400-R | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Belt Tensioner Assy - RIGHT |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N0620-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pulldown Rope RIGHT |  | 17257 | 2500 | 2026-11-20 | 14 | 28/05/2026 | 17223 | 2026-01-31 |  | 565-3199 | PULL DOWN ROPE
N0621-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Rope LEFT |  | 17257 | 2500 | 2026-11-20 | 14 | 28/05/2026 | 17223 | 2026-01-31 |  | 565-3200 | PULL DOWN ROPE
N1301 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Water Pump |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N1300 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Cooling Sys Service |  | 59122 | 12000 | 2026-11-20 | 18.5 |  | 50385 | 2025-03-04
N1210-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Fuel Injectors EN1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N1202-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Fuel Transfer Pump EN 1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N9020-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Alternator EN1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N9152-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Starter Motor Lower EN1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N1002 | WA | CAT | 85 | McPhee Creek | RD6604 | Cat 789D | Engine Valve Adj |  | 6718.6 | 4000 | 2026-11-21 | 11.19 |  | 4695.4 | 2024-06-16
N1300-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooling Sys Service EN1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N7310-R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Motor Rotation RIGHT |  | 8398 | 6000 | 2026-11-21 | 12 |  | 4524 | 2025-06-28
N3341 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 8398 | 6000 | 2026-11-21 | 12 |  | 4524 | 2025-06-28
N1403-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Jockey Pulley Brgs EN1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N3341 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 22440 | 6000 | 2026-11-21 | 12 |  | 18564 | 2025-01-28
N9151-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Starter Motor Upper EN1 |  | 23756 | 9000 | 2026-11-21 | 18.5 |  | 18022 | 2025-06-29
N7169 | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Hyd Mtr Axle Lube/Cooler |  | 54402.5 | 20000 | 2026-11-21 | 13.75 |  | 36836 | 2021-03-10
N7065 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Pump Hoist/ Brk Cooling |  | 60138 | 16000 | 2026-11-21 | 15 |  | 46797 | 2020-04-14 |  | 10R-7967 | PUMP GP
N7320-LR | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Motor Swing LFT REAR |  | 55435 | 12000 | 2026-11-22 | 18.5 |  | 46727 | 2024-12-11
N8442-08 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 8 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N8442-03 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 3 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N8442-05 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 5 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N7073-05 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Imp 3&4 |  | 55435 | 12000 | 2026-11-22 | 18.5 |  | 46727 | 2024-12-12
N8442-02 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 2 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N8442-01 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 1 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N8442-06 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 6 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N8442-04 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 4 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N8442-07 | WA | CAT | 01 | Sanjiv Ridge | RD6562 | Cat 785D | Steering Ball Studs POS 7 |  | 62901.67 | 20000 | 2026-11-22 | 13.5 |  | 45308.36 | 2022-07-09
N7657-RE | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Hyd Accum Steering REAR |  | 71548 | 20000 | 2026-11-23 | 15 |  | 54232 | 2020-01-07 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N7422 | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Blade Tip |  | 27110.6 | 8000 | 2026-11-23 | 10 |  | 20896 | 2023-10-21
N7414-L | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Artic LEFT |  | 27110.6 | 8000 | 2026-11-23 | 10 |  | 20896 | 2023-10-20
N7420-R | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Blade Lift RIGHT |  | 27110.6 | 8000 | 2026-11-23 | 10 |  | 20896 | 2023-10-21 |  | 389-9512 | BLADE LIFT CYLINDER
N0145-L | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Pivot Shaft Brgs LEFT |  | 5943 | 4000 | 2026-11-23 | 13.79 | 29/09/2026 | 4416 | 2026-02-11
N7580 | WA | CAT | 85 |  | GR1550 | Cat 16M | Hyd Cyl Wheel Lean |  | 27110.6 | 8000 | 2026-11-23 | 10 |  | 20896 | 2023-10-21
N0145-R | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Pivot Shaft Brgs RIGHT |  | 5943 | 4000 | 2026-11-23 | 13.79 | 29/09/2026 | 4416 | 2026-02-11
N7657-F | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Hyd Accum Steering FRONT |  | 71548 | 20000 | 2026-11-23 | 15 |  | 54232 | 2020-01-07 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N7029 | WA | CAT | 85 |  | GR1550 | Cat 16M | Pump Brake & Cooling Fan Eng |  | 27110.6 | 8000 | 2026-11-23 | 10 |  | 20896 | 2023-10-21
N7071-05 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Pump Imp 1&2 |  | 23756 | 15000 | 2026-11-24 | 18.5 |  | 12088 | 2024-07-22
N9500 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 5839 | 4000 | 2026-11-24 | 14 | 24/09/2026 | 4353 | 2026-02-26
N6200-04 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Press Convertor POS 4 |  | 79726 | 10000 | 2026-11-24 | 18.5 |  | 73063 | 2025-04-14 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N2004 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Transmission Pump |  | 31190.5 | 16000 | 2026-11-24 | 12 |  | 17355 | 2022-11-19
N7546-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Stick LEFT |  | 23756 | 15000 | 2026-11-24 | 18.5 |  | 12088 | 2024-07-23
N6200-03 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Press Convertor POS 3 |  | 79726 | 10000 | 2026-11-24 | 18.5 |  | 73063 | 2025-04-14 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N7077-05 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Imp 7&8 |  | 55435 | 12000 | 2026-11-24 | 18.5 |  | 46767 | 2024-12-14
N8995 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Operator Seat |  | 18651 | 10000 | 2026-11-25 | 13 |  | 11008.17 | 2024-03-22 | Nearest service
N6200-LR | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Press Converter LEFT REAR |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N6200-RR | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Press Converter RIGHT REAR |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N6200-RR | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Press Converter RIGHT REAR |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Press Converter FRONT |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-07 |  | 8X-7220 | CHAMBER, BRAKE
N6200-LR | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Press Converter LEFT REAR |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-06 |  | 8X-7220 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Press Converter FRONT |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-07 |  | 8X-7220 | CHAMBER, BRAKE
N3029 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Uni's T/C - Trans |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-07 |  | 8R-7036 | SPIDER
N3029 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Uni's T/C - Trans |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-07 |  | 8R-7036 | SPIDER
N3021 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Uni's Eng - Pump Drive |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-07
N3021 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Uni's Eng - Pump Drive |  | 59732.1 | 10000 | 2026-11-25 | 13.75 |  | 52216 | 2023-02-07
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Steering Linkage Group LEFT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-10-04
N7037 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Pump Conv P/Brake Release |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N1002 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Engine Valve Adj |  | 46731 | 4000 | 2026-11-26 | 16 |  | 45640 | 2024-09-13 |  | 449-9059 | SEAL
N7160 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Pump Axle Lube/Cooler |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Steering Hmu |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-26
N7657-R | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Hyd Accum Steering RIGHT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-26
N4102-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Axle Shaft - POS 4 |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N6063 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Oil Cooler - Steering |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-10-06 |  | 0R-5517 | CORE GP OIL
N7657-L | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Hyd Accum Steering LEFT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-27
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Hyd Cyl Hoist RIGHT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-20
N8140 | WA | CAT | 01 |  | RD4246 | Cat 789C | Steering Y Piece |  | 54387 | 20000 | 2026-11-26 | 20 |  | 38026 | 2019-03-21 |  | 135-5269 | CENTRE ARM, STEERING, 789
N2000 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Transmission |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Operator Seat |  | 86119 | 6000 | 2026-11-26 | 18.5 |  | 83491 | 2025-11-27 |  | 384-6168 | SEAT GP-SUSPENSION
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Air Cond'r-Serv - MAJOR |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21743 | 2018-09-11
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Transmission Pump |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N2002 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Oil Cooler - Transmission |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-10-06
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Hyd Cyl Hoist LEFT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-21
N6030-F | WA | CAT | 01 |  | RD4246 | Cat 789C | Brake Slack Adj FRONT |  | 54387 | 20000 | 2026-11-26 | 20 |  | 38026 | 2020-09-15 |  | 590-2531 | SLACK ADJUSTER
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Axle Shaft - POS 3 |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N7120 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Pump Steering |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N4000 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Bevel Gear |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-24
N6030-RE | WA | CAT | 01 |  | RD4246 | Cat 789C | Brake Slack Adj REAR |  | 54387 | 20000 | 2026-11-26 | 20 |  | 38026 | 2020-09-15 |  | 590-2533 | SLACK ADJUSTER
N5000-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Final Drive POS 4 |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N7169 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Hyd Mtr Axle Lube/Cooler |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Drive Shaft T/C - Trans |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-25
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Steering Linkage Group RIGHT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-10-05
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Oil Cooler - Brakes FRONT |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-10-06
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Pump Hoist/ Brk Cooling |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-25
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Torque Convertor |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-23
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Pump Drive Box |  | 39200 | 20000 | 2026-11-26 | 14 |  | 21747 | 2018-09-24
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Air Starter |  | 52309.6 | 10000 | 2026-11-27 | 13 |  | 44693 | 2022-11-19
N0551 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Cooler Aircompressor |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N7151 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Pump Water Injection (Bean) |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N2050 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Torque Convertor |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N7610 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Hyd Cooler Core |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N0325 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Carousel Assembly |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N1000 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Engine |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N2004 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Transmission Pump |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N0103-L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Plates LEFT |  | 45807 | 8000 | 2026-11-27 | 14 |  | 40373 | 2023-12-17
N3321 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Pump Drive |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N1000 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Engine |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N0103-R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Plates RIGHT |  | 45807 | 8000 | 2026-11-27 | 14 |  | 40373 | 2023-12-17
N9500 | WA | CAT | 01 | Sanjiv Ridge | EX6541 | Cat 336DL | Air Cond'r-Serv |  | 14715.2 | 0 | 2026-11-27 | 3.12 |  | 14368 | 2025-11-27
N1310 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Radiator |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N1310 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Radiator |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N1301 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Water Pump |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N2000 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Transmission |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N0101-L | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Chain LEFT |  | 45807 | 8000 | 2026-11-27 | 14 |  | 40373 | 2023-12-17 |  | 569-2544 | TRACK GP
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Hyd Cyl Hoist LEFT |  | 64653 | 24000 | 2026-11-27 | 14 |  | 43213 | 2020-03-18 |  | 438-6225 | CYLINDER GP-HOIST
N2055 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Convertor Charge Scav Pump |  | 58227.56 | 20000 | 2026-11-27 | 12.5 |  | 40520 | 2020-01-12
N1312 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Aftercooler Core |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N7032 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Pump Cooler Fan Hyd |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N0101-R | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Track Chain RIGHT |  | 45807 | 8000 | 2026-11-27 | 14 |  | 40373 | 2023-12-17 |  | 569-2544 | TRACK GP
N1100 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Turbo Primary |  | 16244 | 18000 | 2026-11-27 | 9.59 |  | 0 | 2022-06-01
N1301 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Water Pump |  | 45967 | 8000 | 2026-11-28 | 12 |  | 40174 | 2021-02-17
N9501 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | A/C Compressor |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-08
N7310-L | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Motor Rotation LEFT |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-06
N3341 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-06
N3021 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Uni's Eng - Pump Drive |  | 67106.81 | 10000 | 2026-11-28 | 12.5 |  | 59402.31 | 2023-04-09
N7340 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-06
N2090 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Drv Coupling |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-09
N0302 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Feed Sprocket |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-06
N0346 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-06
N8995 | SA | CAT | 01 | Prominent Hill | LO1645 | Cat 966G | Operator Seat |  | 41729 | 6000 | 2026-11-28 | 1.2 |  | 35950 | 2017-12-17
N1100 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Turbo Primary |  | 45967 | 8000 | 2026-11-28 | 12 |  | 40174 | 2021-02-17
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Uni's T/C - Trans |  | 67106.81 | 10000 | 2026-11-28 | 12.5 |  | 59402.31 | 2023-04-09
N1300 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Cooling Sys Service |  | 45967 | 8000 | 2026-11-28 | 12 |  | 40174 | 2021-02-17
N2050 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Torque Convertor |  | 61931 | 24000 | 2026-11-28 | 18.5 |  | 41343 | 2020-10-18
N8995 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Operator Seat |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-07
N7232 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Motor Engine Fan |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-07
N7234 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 20661 | 6000 | 2026-11-28 | 12 |  | 16869 | 2025-03-07
N3210-04 | WA | CAT | 85 |  | GR1550 | Cat 16M | Tandem Drive Chain POS 4 |  | 27110.6 | 14000 | 2026-11-29 | 10 |  | 14962 | 2022-09-14
N0102-L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 50673 | 4000 | 2026-11-29 | 14 |  | 49269 | 2026-02-25
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Engine Valve Adj |  | 54402.5 | 4000 | 2026-11-29 | 13.75 |  | 52950 | 2025-03-27
N0102-R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 50673 | 4000 | 2026-11-29 | 14 |  | 49269 | 2026-02-24
N3210-03 | WA | CAT | 85 |  | GR1550 | Cat 16M | Tandem Drive Chain POS 3 |  | 27110.6 | 14000 | 2026-11-29 | 10 |  | 14962 | 2022-09-14
N7310-R | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Hyd Motor Rotation RIGHT |  | 20642 | 6000 | 2026-11-30 | 12 |  | 16869 | 2025-03-06
N0145-R | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Pivot Shaft Brgs RIGHT |  | 5650 | 4000 | 2026-12-01 | 13.79 |  | 4232 | 2026-02-14
N1310 | WA | CAT | 01 |  | RD4246 | Cat 789C | Radiator |  | 54387 | 20000 | 2026-12-01 | 20 |  | 38122 | 2020-09-24 |  | 145-1226 | PEX SX 789C RADIATOR
N8200-01 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Ride Strut POS 1 |  | 59732.1 | 20000 | 2026-12-01 | 13.75 |  | 42298 | 2020-12-10
N8200-01 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Ride Strut POS 1 |  | 59732.1 | 20000 | 2026-12-01 | 13.75 |  | 42298 | 2020-12-10
N0145-L | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Pivot Shaft Brgs LEFT |  | 5650 | 4000 | 2026-12-01 | 13.79 |  | 4232 | 2026-02-14
N5000-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Final Drive LEFT |  | 46895 | 15000 | 2026-12-02 | 13.5 |  | 34438 | 2023-02-06 |  | 20R-6295 | FINAL DRIVE, D10
N1002 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Engine Valve Adj |  | 57859 | 3000 | 2026-12-02 | 16 |  | 57859 | 2025-10-17 |  | 224-7506 | SEAL-VALVE COVER
N1002 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Engine Valve Adj |  | 60487 | 3000 | 2026-12-02 | 7 |  | 58801 | 2024-08-05
N9500 | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Air Cond'r-Serv |  | 43005.2 | 0 | 2026-12-02 | 6.35 |  | 41771.1 | 2025-12-02
N9500 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv |  | 18651 | 0 | 2026-12-02 | 13 |  | 17753 | 2025-12-02
N8441 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Rear Axle Dog Bone |  | 79490 | 15000 | 2026-12-02 | 14 |  | 67126 | 2023-11-29 |  | 211-4924 | LATERAL LINK, 793
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Steering Y Piece |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01
N1002 | WA | CAT | 01 |  | RD4246 | Cat 789C | Engine Valve Adj |  | 54387 | 4000 | 2026-12-03 | 20 |  | 54175 | 2024-01-04 |  | 272-0760 | SEAL-PIP
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Drive Shaft T/C - Trans |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 10R-5186 | JOINT GP-SLIP
N9500 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Air Cond'r-Serv |  | 35745 | 6000 | 2026-12-03 | 15 |  | 32584 | 2026-01-17
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Transmission Pump |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01
N7065 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Pump Hoist/ Brk Cooling |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 10R-7971 | PUMP, HOIST, REMAN
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Steering Linkage Group RIGHT |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 2A-7217 | LINK,STEERING,785
N1490 | WA | CAT | 01 |  | RD2644 | Cat 773F | Cam Shaft Inspection |  | 22056 | 1500 | 2026-12-03 | 8 |  | 22067 | 2025-11-05
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Ride Strut POS 4 |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Brake Slack Adj FRONT |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 566-9762 | SLACK ADJUSTER
N7602 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Relief Valve |  | 67683.26 | 0 | 2026-12-03 | 12.5 |  | 0 | 2022-12-04
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Brake Slack Adj REAR |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 566-9766 | ADJUSTER GP
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Steering Linkage Group LEFT |  | 45745.5 | 20000 | 2026-12-03 | 13 |  | 28205 | 2017-08-01 |  | 2A-7217 | LINK,STEERING,785
N1300-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooling Sys Service EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N9501-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | A/C Compressor LEFT |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-18
N1202-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Fuel Transfer Pump EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N1210-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Fuel Injectors EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N9020-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Alternator EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N1403-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Jockey Pulley Brgs EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N9501-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | A/C Compressor RIGHT |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-18
N7201-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Motor Air Con RIGHT |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-19
N9151-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Starter Motor Upper EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N7201-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Motor Air Con LEFT |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-19
N9152-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Starter Motor Lower EN2 |  | 23756 | 9000 | 2026-12-04 | 18.5 |  | 18270 | 2025-07-24
N7605 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Steering Hmu |  | 67106.81 | 12000 | 2026-12-05 | 12.5 |  | 57495.43 | 2022-10-26
N6061 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Oil Cooler Front Brakes |  | 82501 | 24000 | 2026-12-06 | 18.5 | 11/06/2026 | 62061 | 2022-10-01 |  | 10R-5673 | CORE AS OIL
N6030-F | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Brake Slack Adj FRONT |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 590-2533 | SLACK ADJUSTER GP
N6000-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Brake POS 2 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5394 | BRAKE, FRT, 793
N5020-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Bearing POS 2 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 446-0367 | KIT
N5020-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Bearing POS 2 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 446-0367 | KIT
N5020-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Bearing POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 446-0367 | KIT
N8122-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Group POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N8122-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Group POS 2 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N8122-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Group POS 2 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N6061 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Oil Cooler Front Brakes |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5673 | CORE AS OIL
N7038 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Pump Conv,P/Brk Rel, Brk Cool |  | 60138 | 20000 | 2026-12-06 | 15 |  | 43021 | 2019-07-01 |  | 30R-0359 | PUMP GP-GEAR
N8122-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Group POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N5020-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Wheel Bearing POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 446-0367 | KIT
N6030-F | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Brake Slack Adj FRONT |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 590-2533 | SLACK ADJUSTER GP
N7605 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Steering Hmu |  | 60138 | 20000 | 2026-12-06 | 15 |  | 43021 | 2019-07-01 |  | 9T-1318 | PUMP
N6000-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Brake POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5394 | BRAKE, FRT, 793
N6000-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Brake POS 2 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5394 | BRAKE, FRT, 793
N0556 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Air Safety Valve |  | 17257 | 0 | 2026-12-06 | 14 |  | 16417 | 2025-12-06 |  | 549-2163 | VALVE-RELIEF 160psi
N6000-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Brake POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 10R-5394 | BRAKE, FRT, 793
N8200-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Ride Strut POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N8200-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Ride Strut POS 1 |  | 82501 | 24000 | 2026-12-06 | 18.5 |  | 62061 | 2022-10-01 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N7120 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Pump Steering |  | 64732.59 | 20000 | 2026-12-07 | 12.5 |  | 47146 | 2020-10-24
N0091 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Grease Pump |  | 21534 | 8000 | 2026-12-07 | 12 |  | 15846 | 2024-12-05
N1004 | WA | CAT | 85 | McPhee Creek | GR6655 | Cat 18M | Engine Midlife |  | 4648.5 | 6000 | 2026-12-07 | 7.02 |  | 0 | 2025-01-08
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Hyd Cyl Steer RIGHT |  | 81805 | 20000 | 2026-12-08 | 18.5 |  | 65397 | 2023-09-14 |  | 20R-5304 | STEER CYL
N9501 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | A/C Compressor |  | 69200 | 12000 | 2026-12-08 | 18.5 |  | 60782 | 2025-02-25
N2435 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 11349 | 5000 | 2026-12-08 | 15 |  | 9252 | 2026-01-10 |  | 553-9494 | ELEMENT
N7434-L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cyl Bucket Clam LEFT |  | 55435 | 5000 | 2026-12-09 | 18.5 |  | 54048 | 2026-02-27
N0556 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Air Safety Valve |  | 22440 | 0 | 2026-12-09 | 12 |  | 20601 | 2025-12-09
N2052 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Convertor/Trans Pump |  | 59517 | 18000 | 2026-12-09 | 18.5 |  | 45129 | 2023-10-27
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Steering Hmu |  | 50845.5 | 20000 | 2026-12-09 | 13.75 |  | 33521 | 2020-06-15
N1002 | WA | CAT | 01 |  | RD4247 | Cat 789C | Engine Valve Adj |  | 59268 | 4000 | 2026-12-09 | 20 |  | 59163 | 2024-05-23 |  | 272-0760 | SEAL-PIP
N9720 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Autonomy Cabinet |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N7657-RE | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Hyd Accum Steering REAR |  | 77195 | 20000 | 2026-12-10 | 14 |  | 59946 | 2022-10-05 |  | 20R-8270 | ACCUMULATOR, STEERING, 793D 793F
N9735-FD | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Hardware - FIELD |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N9735-DE | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Hardware - DECK |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N7021 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Pump Brake Cooling |  | 65569 | 22000 | 2026-12-10 | 18.5 |  | 47203 | 2021-07-29
N9735-IO | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Hardware - I/O |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N7610 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cooler Core |  | 32622 | 15000 | 2026-12-10 | 13.79 |  | 20330 | 2022-07-01
N9735-MA | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Hardware - MAST |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N1312 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Aftercooler Core |  | 32622 | 15000 | 2026-12-10 | 13.79 |  | 20330 | 2022-07-01
N9735-JC | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Hardware - JUMPER CONNECTOR |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N1310 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Radiator |  | 32622 | 15000 | 2026-12-10 | 13.79 |  | 20330 | 2022-07-01
N9735-CA | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Hardware - CABIN |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N9731 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | AS Electrical Harness |  | 17257 | 20000 | 2026-12-10 | 14 |  | 0
N1100-RF | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Turbo Primary RHT FRONT |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 20R-6651 | RE-MAN TURBO GP
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Fuel Transfer Pump |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 10R-9838 | PUMP GP-F XFR
N1320 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Cooling Fan Engine |  | 69305 | 20000 | 2026-12-11 | 17 |  | 52661 | 2021-04-07
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Fan Pulley Brgs |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 105-2273 | FAN HUB PULLEY,789
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Uni's T/C - Trans |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 363-1923 | MAIN DRIVESHAFT UNI
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Uni's Eng - Pump Drive |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 108-6587 | BEARING,SPIDER
N8140 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Steering Y Piece |  | 69305 | 20000 | 2026-12-11 | 17 |  | 52661 | 2021-03-25
N1100-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Turbo Primary LFT REAR |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 20R-6651 | RE-MAN TURBO GP
N8995 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Operator Seat |  | 49963 | 6000 | 2026-12-11 | 5.5 |  | 45048 | 2022-12-10 |  | 443-8104 | CAT OPERATOR SEAT
N1100-LF | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Turbo Primary LFT FRONT |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 20R-6651 | RE-MAN TURBO GP
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Jockey Pulley Brgs |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 4S-5367 | BUSHING AS
N1000 | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Engine |  | 69305 | 20000 | 2026-12-11 | 17 |  | 52661 | 2021-04-07 |  | 0R-9844 | ENG ARR
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Cooling Sys Service |  | 58852 | 10000 | 2026-12-11 | 15 |  | 51805 | 2021-04-27 |  | 418-4162 | REGULATOR TE
N4100-R | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Rear Axle RIGHT |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02
N4100-L | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Rear Axle LEFT |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02
N3037 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Drive Shaft Trans - Bevel Gear |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02 |  | 419-1963
N8200-02 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Ride Strut POS 2 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N8995 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Operator Seat |  | 46895 | 6000 | 2026-12-13 | 13.5 |  | 43583 | 2025-04-16 |  | 443-8104 | CAT OPERATOR SEAT
N8122-02 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Wheel Group POS 2 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N9500 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Air Cond'r-Serv |  | 64591.2 | 5000 | 2026-12-13 | 13.75 |  | 62331 | 2025-09-29
N9500 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Air Cond'r-Serv |  | 64591.2 | 5000 | 2026-12-13 | 13.75 |  | 62331 | 2025-09-29
N5000-R | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Final Drive RIGHT |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02
N5020-02 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Wheel Bearing POS 2 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N6000-02 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Brake POS 2 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N8200-01 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Ride Strut POS 1 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N6000-01 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Brake POS 1 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N5000-L | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Final Drive LEFT |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02
N5020-01 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Wheel Bearing POS 1 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N2000 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Transmission |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02
N4000 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Bevel Gear |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02 |  | 379-9145SX | AXLE ASSEMBLY, REAR, 16M
N2004 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Transmission Pump |  | 26541 | 14000 | 2026-12-13 | 12.5 |  | 15034 | 2022-10-02
N8122-01 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Wheel Group POS 1 |  | 65569 | 22000 | 2026-12-13 | 18.5 |  | 47257 | 2021-08-10
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Uni's Eng - Pump Drive |  | 70515 | 5000 | 2026-12-14 | 19 |  | 69319 | 2025-12-22 |  | 390-8908 | SPIDER & BEARING AS
N0101-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Chain LEFT |  | 46731 | 6000 | 2026-12-15 | 16 |  | 43942 | 2024-05-19 |  | 569-2544 | TRACK GP
N8995 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Operator Seat |  | 67683.26 | 10000 | 2026-12-15 | 12.5 |  | 60194 | 2022-10-07
N0101-R | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Chain RIGHT |  | 46731 | 6000 | 2026-12-15 | 16 |  | 43942 | 2024-05-19 |  | 569-2544 | TRACK GP
N1100-R | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Turbo Primary RIGHT |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N7657-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Hyd Accum Steering REAR |  | 58852 | 20000 | 2026-12-16 | 15 |  | 41876 | 2019-07-16 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N0091 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Grease Pump |  | 5373 | 8000 | 2026-12-16 | 13 |  | 0
N3029 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Uni's T/C - Trans |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N1202 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Fuel Transfer Pump |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Engine |  | 58852 | 20000 | 2026-12-16 | 15 |  | 41876 | 2019-07-16 |  | 175-5289 | FLEXI ENGINE
N6073-02 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Brake Caliper Reseal POS 02 |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Air Cond'r-Serv |  | 64653 | 5000 | 2026-12-16 | 14 |  | 62475 | 2023-12-01
N6061 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Oil Cooler Front Brakes |  | 56457 | 20000 | 2026-12-16 | 14 |  | 39292 | 2019-02-12 |  | 10R-0816 | REMAN OIL COOLER
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Engine Valve Adj |  | 57617 | 4000 | 2026-12-16 | 20 |  | 57650 | 2024-05-23 |  | 272-0760 | SEAL-PIP
N6006-10 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Brake Pads POS 01 |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N1300 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Cooling Sys Service |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28 |  | 248-5513 | REGULATOR-WATER TEMPERATURE
N7657-F | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Hyd Accum Steering FRONT |  | 58852 | 20000 | 2026-12-16 | 15 |  | 41876 | 2019-07-16 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N1402 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Fan Pulley Brgs |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N1100-L | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Turbo Primary LEFT |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N1301 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Water Pump |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28 |  | 0R-4680 | REMAN WATER PUMP
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Air Starter |  | 58852 | 20000 | 2026-12-16 | 15 |  | 41876 | 2019-07-16
N6073-01 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Brake Caliper Reseal POS 01 |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N6006-20 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Brake Pads POS 02 |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N1403 | WA | CAT | 01 | Iron Bridge | RD4830 | Cat 775F | Jockey Pulley Brgs |  | 35745 | 12000 | 2026-12-16 | 15 |  | 26781 | 2025-03-28
N7230 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Hyd Motor Circle Drive |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
IN8125-5 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle NDT Inspection POS 5 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N6000-LR | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Brake LEFT REAR |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N6000-RF | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Brake RIGHT FRONT |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N7029 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Pump Brake & Cooling Fan Eng |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N1310 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Radiator |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N3210-R | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Tandem Drive Chain RIGHT |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
IN8125-3 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle NDT Inspection POS 3 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N8128-03 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle POS 3 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N8300 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Artic Hitch |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N3300 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Circle Drive Box |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N6000-RR | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Brake RIGHT REAR |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N4000 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Bevel Gear |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N8128-06 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle POS 6 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N8128-04 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle POS 4 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
IN8125-6 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle NDT Inspection POS 6 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N7004-31 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Valve to Trvl Mtr LH |  | 23402 | 18000 | 2026-12-17 | 18.5 |  | 9161 | 2023-10-13
N7004-32 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Valve to Trvl Mtr RH |  | 23402 | 18000 | 2026-12-17 | 18.5 |  | 9161 | 2023-10-13
N6000-LF | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Brake LEFT FRONT |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N1000 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Engine |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N8128-05 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle POS 5 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N7086 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Pump Implement & Steering |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N5000-L | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Final Drive LEFT |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N3210-L | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Tandem Drive Chain LEFT |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N5000-R | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Final Drive RIGHT |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
IN8125-4 | WA | CAT | 85 | McPhee Creek | GR6656 | Cat 18M | Spindle NDT Inspection POS 4 |  | 10578.3 | 12000 | 2026-12-17 | 7.02 |  | 0 | 2024-05-21
N1002 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Engine Valve Adj |  | 79726 | 4000 | 2026-12-17 | 18.5 |  | 79475 | 2026-05-12 |  | 272-0760 | SEAL-VALVE COVER
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Ride Strut POS 3 |  | 44852.3 | 20000 | 2026-12-18 | 15 |  | 27912 | 2019-03-18 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Ride Strut POS 3 |  | 44852.3 | 20000 | 2026-12-18 | 15 |  | 27912 | 2019-03-18 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N1004 | WA | CAT | 85 | McPhee Creek | RD6604 | Cat 789D | Engine Midlife |  | 6718.6 | 9000 | 2026-12-18 | 11.19 |  | 0 | 2026-02-01
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Steering Ball Studs POS 8 |  | 65303 | 12000 | 2026-12-18 | 18.5 |  | 57079 | 2025-01-03
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Ride Strut POS 4 |  | 44852.3 | 20000 | 2026-12-18 | 15 |  | 27912 | 2019-03-20 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N7542-R | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Hyd Cyl Steer RIGHT |  | 65303 | 12000 | 2026-12-18 | 18.5 |  | 57079 | 2025-01-03
N8442-06 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Steering Ball Studs POS 6 |  | 65303 | 12000 | 2026-12-18 | 18.5 |  | 57079 | 2025-01-03
N8442-05 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Steering Ball Studs POS 5 |  | 65303 | 12000 | 2026-12-18 | 18.5 |  | 57079 | 2025-01-03
N8442-07 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Steering Ball Studs POS 7 |  | 65303 | 12000 | 2026-12-18 | 18.5 |  | 57079 | 2025-01-03
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Ride Strut POS 4 |  | 44852.3 | 20000 | 2026-12-18 | 15 |  | 27912 | 2019-03-20 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N3021 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Uni's Eng - Pump Drive |  | 67683.26 | 10000 | 2026-12-18 | 12.5 |  | 60238 | 2023-08-03
N1320 | WA | CAT | 85 | McPhee Creek | RD6604 | Cat 789D | Cooling Fan Engine |  | 6718.6 | 9000 | 2026-12-18 | 11.19 |  | 0 | 2026-02-01
N7542-L | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Hyd Cyl Steer LEFT |  | 65303 | 12000 | 2026-12-18 | 18.5 |  | 57079 | 2025-01-03
N3029 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Uni's T/C - Trans |  | 14603 | 6000 | 2026-12-19 | 16 |  | 11883 | 2025-11-20
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Ride Strut POS 4 |  | 67187 | 30000 | 2026-12-19 | 14 |  | 40057 | 2019-01-08 |  | 11R-1042 | CYL, SUSPENSION, REAR, 789 793
N3038 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Uni's Trans - Bevel Gear |  | 14603 | 6000 | 2026-12-19 | 16 |  | 11883 | 2025-11-21
N9500 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Air Cond'r-Serv |  | 46895 | 5000 | 2026-12-19 | 13.5 |  | 44668 | 2025-07-02
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Ride Strut POS 3 |  | 67187 | 30000 | 2026-12-19 | 14 |  | 40057 | 2019-01-08 |  | 11R-1042 | CYL, SUSPENSION, REAR, 789 793
N9500 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Air Cond'r-Serv |  | 14603 | 6000 | 2026-12-19 | 16 |  | 11884 | 2025-11-29
N1300 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Cooling Sys Service |  | 14603 | 6000 | 2026-12-19 | 16 |  | 11884 | 2025-11-29
N1002 | WA | CAT | 85 | McPhee Creek | RD6607 | Cat 789D | Engine Valve Adj |  | 1690.45 | 4000 | 2026-12-20 | 11.19 |  | 0 | 2024-05-21
N7160 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Pump Axle Lube/Cooler |  | 65569 | 24000 | 2026-12-20 | 18.5 |  | 45383 | 2021-03-13
N7169 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Hyd Mtr Axle Lube/Cooler |  | 65569 | 24000 | 2026-12-20 | 18.5 |  | 45383 | 2021-03-13
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Air Cond'r-Serv |  | 47835.6 | 5000 | 2026-12-21 | 13 |  | 45525 | 2024-08-08
N7234-FU | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Motor Cooler Fan FRONT UPP |  | 55435 | 16000 | 2026-12-21 | 18.5 |  | 43269 | 2023-06-28
N7421-L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Hyd Cyl Blade Tilt LEFT |  | 46731 | 15000 | 2026-12-21 | 16 |  | 35037 | 2022-01-31 |  | 20R-9634 | Tilt Cylinder
N3028 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Drive Shaft T/C - Trans |  | 46731 | 15000 | 2026-12-21 | 16 |  | 35037 | 2022-01-31 |  | 173-0247 | YOKE COUPLING
N9500-MA | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Air Cond'r-Serv - MAJOR |  | 46731 | 15000 | 2026-12-21 | 16 |  | 35037 | 2022-01-31 |  | 418-6835 | HEATER & AC GP
N7230-RE | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Hyd Motor Circle Drive REAR |  | 14603 | 12000 | 2026-12-21 | 16 |  | 5908 | 2024-05-01
N3028 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Drive Shaft T/C - Trans |  | 67791 | 16000 | 2026-12-22 | 18.5 |  | 55630 | 2024-08-01
N2000 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Transmission |  | 79490 | 20000 | 2026-12-22 | 14 |  | 62405 | 2022-12-18 |  | 10R-4469 | TRANSMISSION, 793D
N8995 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Operator Seat |  | 14603 | 6000 | 2026-12-23 | 16 |  | 11952 | 2025-12-07
N9501 | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | A/C Compressor |  | 22613 | 6000 | 2026-12-23 | 12 |  | 19120 | 2026-03-15
N8995 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Operator Seat |  | 54979 | 6000 | 2026-12-23 | 14 |  | 51899 | 2025-12-14 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N8995 | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | Operator Seat |  | 22613 | 6000 | 2026-12-23 | 12 |  | 19120 | 2026-03-17
N1002 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Engine Valve Adj |  | 71548 | 4000 | 2026-12-23 | 15 |  | 70677 | 2023-06-23 |  | 272-0760 | SEAL-PIP
N9500 | WA | CAT | 85 | Iron Bridge | GR1527 | Cat 140M | Air Cond'r-Serv |  | 3320 | 5000 | 2026-12-24 | 8 |  | 0
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Rear Axle Dog Bone |  | 57617 | 15000 | 2026-12-24 | 20 |  | 46820 | 2021-06-12 |  | 211-4923 | LATERAL LINK, 789
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Engine Valve Adj |  | 75619 | 4000 | 2026-12-25 | 19 |  | 75621 | 2026-03-08 |  | 272-0760 | SEAL-VALVE COVER
N7490-R | WA | CAT | 85 |  | LO2122 | Cat 992K | Hyd Cyl Lift RIGHT |  | 35037 | 10000 | 2026-12-25 | 11 |  | 27363 | 2024-06-10 | THIESS MANAGED
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Engine Valve Adj |  | 54615 | 4000 | 2026-12-25 | 15 |  | 53775 | 2023-09-19 |  | 272-0760 | SEAL-PIP
N7613 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Hyd Cooler Steering/Eng Fan |  | 59122 | 24000 | 2026-12-25 | 18.5 |  | 39026 | 2021-01-29
N7169 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Hyd Mtr Axle Lube/Cooler |  | 59122 | 24000 | 2026-12-25 | 18.5 |  | 39026 | 2021-01-29
N7160 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Pump Axle Lube/Cooler |  | 59122 | 24000 | 2026-12-25 | 18.5 |  | 39026 | 2021-01-29
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Press Converter RIGHT REAR |  | 47835.6 | 10000 | 2026-12-26 | 13 |  | 40591 | 2019-12-15 |  | 8X-7220 | CHAMBER, BRAKE
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Press Converter LEFT REAR |  | 47835.6 | 10000 | 2026-12-26 | 13 |  | 40591 | 2019-12-11 |  | 8X-7220 | CHAMBER, BRAKE
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Alternator |  | 47835.6 | 10000 | 2026-12-26 | 13 |  | 40590 | 2019-12-08 |  | 10R-8755 | ALTERNATOR GP_B
N1002 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Engine Valve Adj |  | 39272 | 4000 | 2026-12-26 | 15 |  | 38445 | 2023-10-11
N1002 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Engine Valve Adj |  | 786 | 3750 | 2026-12-26 | 14 |  | 0 | 2024-11-12 |  | 449-9059 | SEAL
N7434-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Bucket Clam RIGHT |  | 23756 | 5000 | 2026-12-26 | 18.5 |  | 22685 | 2026-03-28
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Uni's T/C - Trans |  | 47835.6 | 10000 | 2026-12-26 | 13 |  | 40591 | 2019-12-12 |  | 8R-7036 | SPIDER
N4102-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Axle Shaft - POS 4 |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 6G-6407 | SHAFT-AXLE (RH)
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD5009 | Cat 785C | Operator Seat |  | 52309.6 | 6000 | 2026-12-27 | 13 |  | 49079 | 2024-08-27 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N0302 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Feed Sprocket |  | 17835 | 10000 | 2026-12-27 | 13 |  | 10600.19 | 2024-07-19
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Steering Linkage Group RIGHT |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 2A-7217 | LINK,STEERING,785
N8995 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Operator Seat |  | 17835 | 10000 | 2026-12-27 | 13 |  | 10600.19 | 2024-07-19
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Axle Shaft - POS 3 |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 6G-6408 | SHAFT-AXLE (LH)
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01
N6060-F | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Oil Cooler - Brakes FRONT |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 10R-0817 | CORE GP-O CLR
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Operator Seat |  | 54402.5 | 6000 | 2026-12-27 | 13.75 |  | 51332 | 2024-11-10
N0520 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Pre Lube Pump |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 116-7153 | PUMP & MOTOR, PRELUBE, ASSY
N9500 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 21277 | 4000 | 2026-12-27 | 14 |  | 20261 | 2026-03-13
N8137-L | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Steering Linkage Group LEFT |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 2A-7217 | LINK,STEERING,785
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Drive Shaft T/C - Trans |  | 47835.6 | 20000 | 2026-12-27 | 13 |  | 30599 | 2017-01-01 |  | 10R-5186 | JOINT GP-SLIP
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Fuel Transfer Pump |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-16 |  | 10R-9838 | PUMP GP-F XFR
N1100-RF | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Turbo Primary RHT FRONT |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-17 |  | 20R-6651 | RE-MAN TURBO GP
N9020 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Alternator |  | 45807 | 7500 | 2026-12-28 | 14 |  | 41305 | 2024-03-30 |  | 10R-9789 | ALTERNATOR
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Cooling Sys Service |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-16 |  | 418-4162 | REGULATOR TE
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4217 | Cat 785C | Engine Valve Adj |  | 45745.5 | 4000 | 2026-12-28 | 13 |  | 44528 | 2025-11-23
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Press Converter LEFT REAR |  | 54615 | 10000 | 2026-12-28 | 15 |  | 47826 | 2021-05-16 |  | 8W-3405 | CHAMBER, BRAKE
N1100-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Turbo Primary RHT REAR |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-16 |  | 20R-6651 | RE-MAN TURBO GP
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Fan Pulley Brgs |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-20 |  | 105-2273 | FAN HUB PULLEY,789
N1100-LF | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Turbo Primary LFT FRONT |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-14 |  | 20R-6651 | RE-MAN TURBO GP
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Jockey Pulley Brgs |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-20 |  | 4S-5367 | BUSHING AS
N1100-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Turbo Primary LFT REAR |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-15 |  | 20R-6651 | RE-MAN TURBO GP
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Uni's Eng - Pump Drive |  | 57617 | 10000 | 2026-12-28 | 20 |  | 51906 | 2022-03-21 |  | 108-6587 | BEARING,SPIDER
N3052 | WA | CAT | 85 |  | LO2122 | Cat 992K | Uni's Trans- C/Bearing |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N1100-L | WA | CAT | 85 |  | LO2122 | Cat 992K | Turbo Primary LEFT |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N8442-06 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Steering Ball Studs POS 6 |  | 60870.4 | 20000 | 2026-12-29 | 13.5 |  | 43778 | 2022-03-06
N7120 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Pump Steering |  | 60870.4 | 20000 | 2026-12-29 | 13.5 |  | 43778 | 2022-03-07
N8442-05 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Steering Ball Studs POS 5 |  | 60870.4 | 20000 | 2026-12-29 | 13.5 |  | 43778 | 2022-03-06
N3038-RE | WA | CAT | 85 |  | LO2122 | Cat 992K | Uni's Trans - Bevel Gear REAR |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N8442-08 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Steering Ball Studs POS 8 |  | 60870.4 | 20000 | 2026-12-29 | 13.5 |  | 43778 | 2022-03-06
N1400 | WA | CAT | 85 |  | LO2122 | Cat 992K | Belt Tensioner Assembly |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N8442-07 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Steering Ball Studs POS 7 |  | 60870.4 | 20000 | 2026-12-29 | 13.5 |  | 43778 | 2022-03-06
N3032 | WA | CAT | 85 |  | LO2122 | Cat 992K | Uni's Ctr Bearing - Bevel Gear |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N3029 | WA | CAT | 85 |  | LO2122 | Cat 992K | Uni's T/C - Trans |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N1100-R | WA | CAT | 85 |  | LO2122 | Cat 992K | Turbo Primary RIGHT |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N1202 | WA | CAT | 85 |  | LO2122 | Cat 992K | Fuel Transfer Pump |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N1300 | WA | CAT | 85 |  | LO2122 | Cat 992K | Cooling Sys Service |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N7064 | WA | CAT | 01 | Sanjiv Ridge | RD6565 | Cat 785D | Pump Hoist |  | 60870.4 | 20000 | 2026-12-29 | 13.5 |  | 43778 | 2022-03-07
N3042 | WA | CAT | 85 |  | LO2122 | Cat 992K | Driveline Ctr Bearing |  | 35037 | 9000 | 2026-12-29 | 11 |  | 28400 | 2024-08-14 | THIESS MANAGED
N0520 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Pre Lube Pump |  | 54428 | 20000 | 2026-12-29 | 17 |  | 38082 | 2021-01-31 |  | 116-7153 | PUMP & MOTOR, PRELUBE, ASSY
N7310-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Rotation LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-21 |  | 11R-0141 | MOTOR GP-PISTON
N0623-TR | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Sheave TRAVEL RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-6156 | SHEAVE
N7310-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Motor Rotation RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-21 |  | 11R-0142 | MOTOR GP-PISTON
N0623-TL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Sheave TRAVEL LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-6156 | SHEAVE
N0623-RU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Sheave UPPER RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N0622-LL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Sheave LOWER LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N0623-LU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Sheave UPPER LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N0622-LU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Sheave UPPER LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N0623-RL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Sheave LOWER RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N9050-R | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Starter Motor RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-23 |  | 349-6554 | STARTER MOTOR
N0623-LL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pullback Sheave LOWER LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N0622-RL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Sheave LOWER RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N0622-TR | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-6156 | SHEAVE
N0622-RU | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Sheave UPPER RIGHT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-8053 | SHEAVE AS
N9501 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | A/C Compressor |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-23 |  | 629-8454 | COMPRESSOR GP-REFRIGERANT
N0622-TL | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-22 |  | 450-6156 | SHEAVE
N9050-L | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Starter Motor LEFT |  | 12951 | 7500 | 2026-12-30 | 14 |  | 8474 | 2025-06-21 |  | 349-6554 | STARTER MOTOR
N7605 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Steering Hmu |  | 54428 | 20000 | 2026-12-30 | 17 |  | 38093 | 2021-02-06
N7021 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Pump Brake Cooling |  | 77195 | 40000 | 2026-12-31 | 14 |  | 40239 | 2018-08-12 |  | 20R-7440 | PUMP GP-GEAR
N7474-L | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Hyd Cyl Hoist LEFT |  | 77195 | 40000 | 2026-12-31 | 14 |  | 40237 | 2018-04-02 |  | 295-5708 | CYLINDER GP
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Fuel Transfer Pump |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 10R-9838 | PUMP GP-F XFR
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Cooling Sys Service |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 418-4162 | REGULATOR
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Jockey Pulley Brgs |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 4S-5367 | BUSHING
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Air Cond'r-Serv |  | 57576 | 5000 | 2027-01-01 | 14 |  | 55626 | 2024-05-30
N1004 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Engine Midlife |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Press Converter LEFT REAR |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-04 |  | 8X-7220 | CHAMBER, BRAKE
N7047 | NT | CAT | 01 | FleetCo | RD4103 | Cat 740 ADT | Pump Transfer Case |  | 45967 | 16000 | 2027-01-01 | 12 |  | 32578 | 2019-04-12
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Turbo Primary RIGHT |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 20R-3423 | TURBO GRP
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Pump Drive Box |  | 56457 | 20000 | 2027-01-01 | 14 |  | 39506 | 2019-03-12 |  | 11R-1517 | DRIVE GP-PUMP
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Uni's Eng - Pump Drive |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-08
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | A/C Compressor |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Fan Pulley Brgs |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 6Y-7651 | CONE BEARING
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Press Converter FRONT |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-05 |  | 8X-7220 | CHAMBER, BRAKE
N7122 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Pump Emerg/Sup Steering |  | 28724 | 32000 | 2027-01-01 | 15 |  | 0 | 2022-12-14
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Press Converter RIGHT REAR |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-04 |  | 8X-7220 | CHAMBER, BRAKE
N1420 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Air Compressor |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 0R-9626 | COMPRESSOR GP -B
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Alternator |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 10R-8755 | ALTERNATOR GP_B
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Turbo Primary LEFT |  | 52712 | 10000 | 2027-01-01 | 13.75 |  | 45706 | 2024-09-10 |  | 20R-3423 | TURBO GRP
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Radiator |  | 56457 | 20000 | 2027-01-02 | 14 |  | 39521 | 2019-03-12 |  | 145-1226 | PEX SX 789C RADIATOR
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Engine |  | 56457 | 20000 | 2027-01-02 | 14 |  | 39521 | 2019-03-12 |  | 175-5289 | FLEXI ENGINE
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 56457 | 20000 | 2027-01-02 | 14 |  | 39521 | 2019-03-15 |  | 230-4112 | UNIVERSAL JOINT GP
N1002 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Engine Valve Adj |  | 44396 | 4000 | 2027-01-03 | 15 |  | 43696 | 2026-04-14
N8200-04 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Ride Strut POS 4 |  | 39272 | 20000 | 2027-01-03 | 15 |  | 22570 | 2017-10-30 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Uni's T/C - Trans |  | 39200 | 10000 | 2027-01-03 | 14 |  | 32284 | 2021-01-22
N8200-03 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Ride Strut POS 3 |  | 39272 | 20000 | 2027-01-03 | 15 |  | 22570 | 2017-10-30 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N2435 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 17257 | 5000 | 2027-01-04 | 14 |  | 15347 | 2025-10-01 |  | 553-9494 | ELEMENT
N8995 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Operator Seat |  | 65021 | 6000 | 2027-01-04 | 8.5 |  | 60896 | 2022-04-10 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9020 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Alternator |  | 76600 | 9000 | 2027-01-04 | 14 |  | 70695 | 2025-03-07 |  | 10R-9789 | ALTERNATOR GP -B
N0100-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Group RIGHT |  | 33117 | 4000 | 2027-01-04 | 11 |  | 31545 | 2024-11-08
N2090 | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Drv Coupling |  | 17257 | 5000 | 2027-01-04 | 14 |  | 15347 | 2025-10-02 |  | 520-7010 | COUPLING GP-
N0100-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Group LEFT |  | 33117 | 4000 | 2027-01-04 | 11 |  | 31545 | 2024-11-09
N5015 | WA | CAT | 85 |  | LO2122 | Cat 992K | Oil Cooler AXLE |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N1310 | WA | CAT | 85 |  | LO2122 | Cat 992K | Radiator |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N4102-01 | WA | CAT | 85 |  | LO2122 | Cat 992K | Axle Shaft - POS 1 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N4102-02 | WA | CAT | 85 |  | LO2122 | Cat 992K | Axle Shaft - POS 2 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N9500 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Air Cond'r-Serv |  | 67683.26 | 0 | 2027-01-05 | 12.5 |  | 65727 | 2026-01-05
N2004 | WA | CAT | 85 |  | LO2122 | Cat 992K | Transmission Pump |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N1000 | WA | CAT | 85 |  | LO2122 | Cat 992K | Engine |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N6063 | WA | CAT | 85 |  | LO2122 | Cat 992K | Oil Cooler - Steering |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N2000 | WA | CAT | 85 |  | LO2122 | Cat 992K | Transmission |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Air Cond'r-Serv |  | 70515 | 5000 | 2027-01-05 | 19 |  | 69726 | 2026-01-14 |  | 385-0244 | MOTOR AS-BLOWER
N4000-RE | WA | CAT | 85 |  | LO2122 | Cat 992K | Bevel Gear REAR |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N6020 | WA | CAT | 85 |  | LO2122 | Cat 992K | Park Brake |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N3037-RE | WA | CAT | 85 |  | LO2122 | Cat 992K | Drive Shft Trans - Bev Gear RE |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N5000-01 | WA | CAT | 85 |  | LO2122 | Cat 992K | Final Drive POS 1 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N7610 | WA | CAT | 85 |  | LO2122 | Cat 992K | Hyd Cooler Core |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N7020 | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Brake |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N4102-03 | WA | CAT | 85 |  | LO2122 | Cat 992K | Axle Shaft - POS 3 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N3028 | WA | CAT | 85 |  | LO2122 | Cat 992K | Drive Shaft T/C - Trans |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N5000-02 | WA | CAT | 85 |  | LO2122 | Cat 992K | Final Drive POS 2 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N5000-04 | WA | CAT | 85 |  | LO2122 | Cat 992K | Final Drive POS 4 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N4102-04 | WA | CAT | 85 |  | LO2122 | Cat 992K | Axle Shaft - POS 4 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N3044 | WA | CAT | 85 |  | LO2122 | Cat 992K | Drv Shaft C/Bearing-Bevel Gr |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N3321 | WA | CAT | 85 |  | LO2122 | Cat 992K | Pump Drive |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N3043 | WA | CAT | 85 |  | LO2122 | Cat 992K | Drv Shaft Trans-Ctr Bearing |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N5000-03 | WA | CAT | 85 |  | LO2122 | Cat 992K | Final Drive POS 3 |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N1312-L | WA | CAT | 85 |  | LO2122 | Cat 992K | Aftercooler Core - LEFT |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N0140 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Equalizer Bar |  | 46731 | 15000 | 2027-01-05 | 16 |  | 35289 | 2022-07-28 |  | 10R-9161 | BAR GP-EQUALIZER
N1250 | WA | CAT | 85 |  | LO2122 | Cat 992K | Fuel Cooler |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N1312-R | WA | CAT | 85 |  | LO2122 | Cat 992K | Aftercooler Core - RIGHT |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N4000-F | WA | CAT | 85 |  | LO2122 | Cat 992K | Bevel Gear FRONT |  | 35037 | 18000 | 2027-01-05 | 11 |  | 19479 | 2023-02-24 | THIESS MANAGED
N1100 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Turbo Primary |  | 5373 | 6000 | 2027-01-06 | 13 |  | 2273 | 2025-03-19
N9500 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Air Cond'r-Serv |  | 70621 | 6000 | 2027-01-06 | 15 |  | 67964 | 2025-11-13
N9701 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | LiDAR Detection System |  | 16307 | 5000 | 2027-01-06 | 14 |  | 14428 | 2026-01-12
N7310-R | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Hyd Motor Rotation RIGHT |  | 5839 | 7500 | 2027-01-06 | 14 |  | 1458 | 2025-08-09 |  | 11R-0142 | MOTOR GP-PISTON
N1002 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Engine Valve Adj |  | 4002 | 3000 | 2027-01-06 | 12 |  | 3677 | 2026-05-06
N1002 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Engine Valve Adj |  | 16307 | 3750 | 2027-01-06 | 14 |  | 15677 | 2026-04-23 |  | 449-9059 | SEAL
N8122-01 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Wheel Group POS 1 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N6200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Press Convertor POS 2 |  | 70515 | 12000 | 2027-01-07 | 19 |  | 62763 | 2024-09-29 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6000-01 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Brake POS 1 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 10R-5394 | BRAKE, FRT, 793
N8200-02 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Ride Strut POS 2 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N6000-02 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Brake POS 2 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 10R-5394 | BRAKE, FRT, 793
N8061 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Slew Ring Bolts Check |  | 23402 | 5000 | 2027-01-07 | 18.5 |  | 22553 | 2026-04-14
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Brake Slack Adj REAR |  | 54402.5 | 20000 | 2027-01-07 | 13.75 |  | 37483 | 2021-05-08
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Brake Slack Adj FRONT |  | 54402.5 | 20000 | 2027-01-07 | 13.75 |  | 37483 | 2021-05-08
N8122-02 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Wheel Group POS 2 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N6200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Press Convertor POS 1 |  | 70515 | 12000 | 2027-01-07 | 19 |  | 62763 | 2024-09-29 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N7434-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cyl Bucket Clam RIGHT |  | 23402 | 5000 | 2027-01-07 | 18.5 |  | 22553 | 2026-04-16
N5020-02 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Wheel Bearing POS 2 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 446-0367 | KIT
N5020-01 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Wheel Bearing POS 1 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 446-0367 | KIT
N1430 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Air Starter |  | 78345 | 9000 | 2027-01-07 | 14 | 07/05/2026 | 72480 | 2025-04-01 |  | 10R-9657 | MOTOR GP-AIR STG
N8200-01 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Ride Strut POS 1 |  | 79044 | 30000 | 2027-01-07 | 14 |  | 52183 | 2021-02-14 |  | 295-5707 | CYL, SUSPENSION, FRT, 793
N9500 | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Air Cond'r-Serv |  | 5903.7 | 0 | 2027-01-08 | 7.2 |  | 4234 | 2026-01-08
N0102-L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Trk Chn Pin & Bush Trn LEFT |  | 31226 | 4000 | 2027-01-08 | 14 |  | 30378 | 2026-03-22 |  | 569-2544 | TRACK GP
N0111-4L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 4 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0121-L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Carrier Roller No 1 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-5L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 5 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-8L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 8 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-7L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 7 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-4R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 4 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N5000-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Final Drive RIGHT |  | 55934 | 15000 | 2027-01-09 | 13.5 |  | 43989 | 2023-05-29 |  | 20R-6295 | FINAL DRIVE, D10
N0121-R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Carrier Roller No 1 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-3L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 3 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Engine Valve Adj |  | 39658.4 | 4000 | 2027-01-09 | 15 |  | 39044 | 2023-12-20
N0111-2L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 2 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-7R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 7 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Engine Valve Adj |  | 64230 | 4000 | 2027-01-09 | 14 |  | 63400 | 2024-10-17 |  | 272-0760 | SEAL-PIP
N0111-5R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 5 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Engine Valve Adj |  | 39658.4 | 4000 | 2027-01-09 | 15 |  | 39044 | 2023-12-20
N9500 | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Air Cond'r-Serv |  | 14154.15 | 0 | 2027-01-09 | 6.87 |  | 12981 | 2026-01-09
N4110-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Steering Clutch/Brk RIGHT |  | 55934 | 15000 | 2027-01-09 | 13.5 |  | 43989 | 2023-05-28 |  | 10R-9976 | Steering Brake And Clutch
N0111-1R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 1 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N8995 | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Operator Seat |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-8R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 8 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-1L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 1 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-6R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 6 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N9500 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv |  | 16244 | 0 | 2027-01-09 | 9.59 |  | 14510 | 2026-01-09
N7035 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Pump Hoist, Brk Charge/Cooling |  | 69633 | 18000 | 2027-01-09 | 18.5 |  | 55806 | 2023-10-27
N0111-6L | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 6 LEFT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N9500 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Air Cond'r-Serv |  | 32622 | 0 | 2027-01-09 | 13.79 |  | 30832 | 2026-01-09
N0111-3R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 3 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N0111-2R | WA | CAT | 660 | Sanjiv Ridge | DZ6551 | Cat D9T | Track Roller 2 RIGHT |  | 7287 | 10000 | 2027-01-09 | 12 |  | 0 | 2024-08-27
N1002 | WA | CAT | 95 |  | RD4977 | Cat 789C | Engine Valve Adj |  | 818 | 4000 | 2027-01-10 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Press Converter FRONT |  | 50845.5 | 10000 | 2027-01-10 | 13.75 |  | 43968 | 2024-07-03 |  | 8X-7220 | CHAMBER, BRAKE
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Press Converter RIGHT REAR |  | 50845.5 | 10000 | 2027-01-10 | 13.75 |  | 43968 | 2024-07-03 |  | 8X-7220 | CHAMBER, BRAKE
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Press Converter LEFT REAR |  | 50845.5 | 10000 | 2027-01-10 | 13.75 |  | 43968 | 2024-07-03 |  | 8X-7220 | CHAMBER, BRAKE
N0111-6L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 6 LEFT |  | 46731 | 8000 | 2027-01-11 | 16 |  | 42372 | 2024-01-10 |  | 309-7678 | ROLLER GP-DF
N9500 | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Air Cond'r-Serv |  | 34410.8 | 0 | 2027-01-11 | 6.35 |  | 33497.7 | 2026-01-11
N9500 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Air Cond'r-Serv |  | 33117 | 4000 | 2027-01-11 | 11 |  | 31629 | 2025-01-01
N3065 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Bearing Unit & Adaptor Shaft |  | 18065 | 6000 | 2027-01-11 | 13 |  | 15032.77 | 2025-07-22
N0111-3L | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Track Roller 3 LEFT |  | 46731 | 8000 | 2027-01-11 | 16 |  | 42372 | 2024-01-10 |  | 309-7678 | ROLLER GP-DF
N9703 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Inertial Measurement Unit |  | 21277 | 10000 | 2027-01-11 | 14 |  | 14471 | 2024-07-14
N7232 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Motor Engine Fan |  | 34679 | 18000 | 2027-01-12 | 14 |  | 19881 | 2023-02-21
N9501 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | A/C Compressor |  | 79490 | 9000 | 2027-01-12 | 14 |  | 73693 | 2025-04-27 |  | 217-4448 | COMPRESSOR GP-REFRIGERANT
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Air Starter |  | 39658.4 | 10000 | 2027-01-13 | 15 |  | 33107 | 2022-02-02
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Air Starter |  | 39658.4 | 10000 | 2027-01-13 | 15 |  | 33107 | 2022-02-02
N0104-L | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Sprockets LEFT |  | 34410.8 | 5000 | 2027-01-13 | 6.35 |  | 30869 | 2025-09-01
N1002 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Engine Valve Adj |  | 45807 | 4000 | 2027-01-13 | 14 |  | 45031 | 2025-09-10 |  | 449-9059 | SEAL
N0104-R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Sprockets RIGHT |  | 34410.8 | 5000 | 2027-01-13 | 6.35 |  | 30869 | 2025-09-01
N9500 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 786 | 4000 | 2027-01-13 | 14 |  | 0 | 2024-11-12
N1004 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Engine Midlife |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-16
N1002 | WA | CAT | 85 | McPhee Creek | RD6605 | Cat 789D | Engine Valve Adj |  | 4708.7 | 4000 | 2027-01-14 | 11.19 |  | 3289.9 | 2025-09-20
N1402 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Fan Pulley Brgs |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-14 |  | 6Y-7651 | CONE BEARING
N9501 | WA | CAT | 01 |  | RD2642 | Cat 773F | A/C Compressor |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N2000 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Transmission |  | 45807 | 15000 | 2027-01-14 | 14 |  | 34043 | 2021-03-14 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N1300 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Cooling Sys Service |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-16 |  | 418-4162 | REGULATOR
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Press Converter RIGHT REAR |  | 58874 | 10000 | 2027-01-14 | 13.75 |  | 52057 | 2024-11-03
N9050-R | WA | CAT | 01 |  | RD2642 | Cat 773F | Starter Motor RIGHT |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N9501 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | A/C Compressor |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-14
N1403 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Jockey Pulley Brgs |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-14 |  | 4S-5367 | BUSHING
N1202 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Fuel Transfer Pump |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-15 |  | 10R-9838 | PUMP GP-F XFR
N1420 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Air Compressor |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-15 |  | 0R-9626 | COMPRESSOR GP -B
N2020 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Powertrain Pump |  | 45807 | 15000 | 2027-01-14 | 14 |  | 34042 | 2021-03-09 |  | 20R-7445 | PUMP GP
N1100-R | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Turbo Primary RIGHT |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-15 |  | 20R-3423 | TURBO GRP
N1403 | WA | CAT | 01 |  | RD2642 | Cat 773F | Jockey Pulley Brgs |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N1402 | WA | CAT | 01 |  | RD2642 | Cat 773F | Fan Pulley Brgs |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N1300 | WA | CAT | 01 |  | RD2642 | Cat 773F | Cooling Sys Service |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N1202 | WA | CAT | 01 |  | RD2642 | Cat 773F | Fuel Transfer Pump |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N1100-L | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Turbo Primary LEFT |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-16 |  | 20R-3423 | TURBO GRP
N3038 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Uni's Trans - Bevel Gear |  | 37630 | 8000 | 2027-01-14 | 12 |  | 32406 | 2020-11-15
N1100-R | WA | CAT | 01 |  | RD2642 | Cat 773F | Turbo Primary RIGHT |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N9020 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Alternator |  | 54979 | 10000 | 2027-01-14 | 14 |  | 48214 | 2025-06-15 |  | 10R-8755 | ALTERNATOR GP_B
N4000 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Bevel Gear |  | 45807 | 15000 | 2027-01-14 | 14 |  | 34043 | 2021-03-14 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N9020 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Alternator |  | 12951 | 7500 | 2027-01-14 | 14 |  | 8686 | 2025-07-19 |  | 11R-1235 | ALTERNATOR GP
N1100-L | WA | CAT | 01 |  | RD2642 | Cat 773F | Turbo Primary LEFT |  | 27652 | 10000 | 2027-01-14 | 12 |  | 20425 | 2023-06-08
N9050 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Starter Motor |  | 45807 | 7500 | 2027-01-15 | 14 |  | 41559 | 2024-04-24 |  | 10R-9816 | MOTOR GP-ELEC
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4222 | Cat 785C | Engine Valve Adj |  | 41444 | 4000 | 2027-01-15 | 14.5 |  | 40801 | 2025-04-28
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Rear Axle Dog Bone |  | 67187 | 15000 | 2027-01-15 | 14 |  | 55435 | 2022-04-24 |  | 211-4923 | LATERAL LINK, 789
N7305 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Motor Thrust/Pullback |  | 34291 | 10000 | 2027-01-16 | 13.79 |  | 27504.74 | 2024-02-15
N4000 | WA | CAT | 01 | Disposals | DZ1594 | Cat D10T | Bevel Gear |  | 46731 | 15000 | 2027-01-16 | 16 |  | 35464 | 2022-09-08 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Steering Hmu |  | 82579 | 20000 | 2027-01-17 | 18.5 |  | 71520 | 2024-01-27 |  | 9T-1318 | PUMP GP
N1002 | WA | CAT | 95 |  | RD4978 | Cat 789C | Engine Valve Adj |  | 728 | 4000 | 2027-01-17 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Torque Convertor |  | 39658.4 | 20000 | 2027-01-17 | 15 |  | 23161 | 2019-05-21
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Torque Convertor |  | 39658.4 | 20000 | 2027-01-17 | 15 |  | 23161 | 2019-05-21
N7037 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pump Conv P/Brake Release |  | 39658.4 | 20000 | 2027-01-17 | 15 |  | 23161 | 2019-05-21
N7037 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Pump Conv P/Brake Release |  | 39658.4 | 20000 | 2027-01-17 | 15 |  | 23161 | 2019-05-21
N0556 | WA | CAT | 85 | Iron Bridge | DR2117 | Cat MD6310 - ADS | Air Safety Valve |  | 14426 | 0 | 2027-01-18 | 14 |  | 12498 | 2026-01-18 |  | 549-2163 | VALVE-RELIEF 160psi
N0302 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Feed Sprocket |  | 7751 | 10000 | 2027-01-18 | 9.59 |  | 0 | 2024-03-28
N0695 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Centraliser Assembly |  | 7751 | 10000 | 2027-01-18 | 9.59 |  | 0 | 2024-03-28
N8995 | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Operator Seat |  | 7751 | 10000 | 2027-01-18 | 9.59 |  | 0 | 2024-03-28
N7664-LW | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper LOWER |  | 7751 | 10000 | 2027-01-18 | 9.59 |  | 0 | 2024-03-28
N7474-L | WA | CAT | 01 |  | RD4246 | Cat 789C | Hyd Cyl Hoist LEFT |  | 54387 | 24000 | 2027-01-18 | 20 |  | 35081 | 2020-04-14 |  | 438-6225 | CYLINDER GP-HOIST
N7664-UP | WA | EPI | 01 | Miralga Creek | DR6586 | Epiroc SmartRoc T45 10LF | Hyd Cyl Rod Gripper UPPER |  | 7751 | 10000 | 2027-01-18 | 9.59 |  | 0 | 2024-03-28
N8995 | WA | CAT | 01 |  | RD2642 | Cat 773F | Operator Seat |  | 27652 | 6000 | 2027-01-18 | 12 |  | 24471 | 2024-06-21
N3028 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Drive Shaft T/C - Trans |  | 71898 | 16000 | 2027-01-18 | 18.5 |  | 60249 | 2024-09-07
N6061 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Oil Cooler Front Brakes |  | 77195 | 20000 | 2027-01-19 | 14 |  | 60500 | 2022-11-15 |  | 10R-5673 | CORE AS OIL
N7605 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Hmu |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08
N6062-RE | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 77195 | 20000 | 2027-01-19 | 14 |  | 60500 | 2022-11-15 |  | 10R-5675 | CORE AS OIL
N7605 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Hmu |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08
N8137-L | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Linkage Group LEFT |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08 |  | 2A-7217 | LINK,STEERING,785
N3020 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-04
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Torque Convertor |  | 70515 | 20000 | 2027-01-19 | 19 |  | 55002 | 2021-02-23 |  | 10R-5398 | TORQUE CONVERTER, 793D
N6030-RE | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Brake Slack Adj REAR |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-05 |  | 566-9766 | ADJUSTER GP
N8137-R | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Linkage Group RIGHT |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08 |  | 2A-7217 | LINK,STEERING,785
N6030-F | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Brake Slack Adj FRONT |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-04 |  | 566-9762 | SLACK ADJUSTER
N6030-F | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Brake Slack Adj FRONT |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-04 |  | 566-9762 | SLACK ADJUSTER
N8140 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Y Piece |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08
N8140 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Y Piece |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08
N6062-F | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 77195 | 20000 | 2027-01-19 | 14 |  | 60500 | 2022-11-15 |  | 10R-5675 | CORE AS OIL
N3028 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Drive Shaft T/C - Trans |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-05 |  | 10R-5186 | JOINT GP-SLIP
N7542-R | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Hyd Cyl Steer RIGHT |  | 77195 | 20000 | 2027-01-19 | 14 |  | 60500 | 2022-11-15 |  | 20R-5304 | STEER CYL
N3028 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Drive Shaft T/C - Trans |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-05 |  | 10R-5186 | JOINT GP-SLIP
N8137-L | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Linkage Group LEFT |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08 |  | 2A-7217 | LINK,STEERING,785
N2004 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Transmission Pump |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-04 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N7542-L | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Hyd Cyl Steer LEFT |  | 77195 | 20000 | 2027-01-19 | 14 |  | 60500 | 2022-11-15 |  | 20R-5304 | STEER CYL
N8995 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Operator Seat |  | 23402 | 6000 | 2027-01-19 | 18.5 |  | 21759 | 2026-03-02
N2004 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Transmission Pump |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-04 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N2000 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Transmission |  | 77195 | 20000 | 2027-01-19 | 14 |  | 60500 | 2022-11-15 |  | 10R-4469 | TRANSMISSION, 793D
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Drive Shaft T/C - Trans |  | 70515 | 20000 | 2027-01-19 | 19 |  | 55002 | 2021-02-23 |  | 11R-1790 | SLIP JOINT GP
N8137-R | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Steering Linkage Group RIGHT |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-08 |  | 2A-7217 | LINK,STEERING,785
N6030-RE | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Brake Slack Adj REAR |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-05 |  | 566-9766 | ADJUSTER GP
N3020 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Drive Shaft Eng - Pump Drive |  | 64591.2 | 20000 | 2027-01-19 | 13.75 |  | 47836 | 2021-04-04
N4102-02 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Axle Shaft - POS 2 |  | 57859 | 20000 | 2027-01-20 | 16 |  | 41650 | 2020-02-22
N0556 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Air Safety Valve |  | 5839 | 0 | 2027-01-20 | 14 |  | 4020 | 2026-01-20 |  | 549-2163 | VALVE-RELIEF 160psi
N4102-01 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Axle Shaft - POS 1 |  | 57859 | 20000 | 2027-01-20 | 16 |  | 41650 | 2020-02-22
N9500 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | Air Cond'r-Serv |  | 60498 | 5000 | 2027-01-20 | 15 |  | 59059 | 2022-03-14
N6350 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Brake Relay Valves |  | 76600 | 12000 | 2027-01-21 | 14 |  | 67931 | 2024-09-04 |  | 159-5149 | BRAKE RELAY VALVE
N4000 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Bevel Gear |  | 59122 | 18000 | 2027-01-21 | 18.5 |  | 45524 | 2023-10-27
N8137-R | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Steering Linkage Group RIGHT |  | 75619 | 20000 | 2027-01-21 | 19 |  | 60134 | 2022-09-21 |  | 2A-6946 | LINK GP - STEERING
N5003-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Final Drive Ext Life POS 3 |  | 75619 | 20000 | 2027-01-21 | 19 |  | 60134 | 2022-09-26 |  | 20R-3787 | WHEEL HUB BRK GRP, REAR, 793
N2000 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Transmission |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N6060 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Oil Cooler - Brakes |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N8140 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Steering Y Piece |  | 58874 | 20000 | 2027-01-22 | 13.75 |  | 42166 | 2022-10-23 |  | 135-5267 | ARM,CENTRE,STEERING
N3321 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Pump Drive |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N7169 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Hyd Mtr Axle Lube/Cooler |  | 58874 | 20000 | 2027-01-22 | 13.75 |  | 42166 | 2022-10-22
N1002 | WA | CAT | 95 |  | RD4974 | Cat 789C | Engine Valve Adj |  | 655 | 4000 | 2027-01-22 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N2050 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Torque Convertor |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Hyd Cyl Hoist RIGHT |  | 67187 | 24000 | 2027-01-22 | 14 |  | 46532 | 2020-03-09 |  | 438-6225 | CYLINDER GP-HOIST
N4000 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Bevel Gear |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N2435 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 1658 | 5000 | 2027-01-22 | 14 |  | 0 | 2024-11-12 |  | 553-9494 | ELEMENT
N0556 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Air Safety Valve |  | 21277 | 0 | 2027-01-22 | 14 |  | 19311 | 2026-01-22 |  | 549-2163 | VALVE-RELIEF 160psi
N2090 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Drv Coupling |  | 18651 | 6000 | 2027-01-22 | 13 |  | 15754.31 | 2025-06-03
N7605 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Steering Hmu |  | 58874 | 20000 | 2027-01-22 | 13.75 |  | 42166 | 2022-10-23
N2445 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Drv Coupling Compressor |  | 18065 | 12000 | 2027-01-22 | 13 |  | 9170 | 2024-01-08
N5015 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Oil Cooler AXLE |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N9701 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | LiDAR Detection System |  | 1658 | 5000 | 2027-01-22 | 14 |  | 0 | 2024-11-12
N2004 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Transmission Pump |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N7160 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Pump Axle Lube/Cooler |  | 58874 | 20000 | 2027-01-22 | 13.75 |  | 42166 | 2022-10-23
N7480 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Track Oscillation |  | 18065 | 12000 | 2027-01-22 | 13 |  | 9170 | 2024-01-08
N7542-L | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Hyd Cyl Steer LEFT |  | 58874 | 20000 | 2027-01-22 | 13.75 |  | 42166 | 2022-10-23
N7460-02 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Hyd Cyl Feed Dump LEFT |  | 18065 | 12000 | 2027-01-22 | 13 |  | 9170 | 2024-01-08
N2090 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Drv Coupling |  | 1658 | 5000 | 2027-01-22 | 14 |  | 0 | 2024-11-12 |  | 520-7010 | COUPLING GP-
N2055 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Convertor Charge Scav Pump |  | 67106.81 | 20000 | 2027-01-22 | 12.5 |  | 50093 | 2020-02-27
N9500 | WA | CAT | 01 |  | RD4246 | Cat 789C | Air Cond'r-Serv |  | 54387 | 5000 | 2027-01-22 | 20 |  | 54175 | 2024-01-08
N9500 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Air Cond'r-Serv |  | 59732.1 | 5000 | 2027-01-23 | 13.75 |  | 58036 | 2025-11-10
N7420-L | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Cyl Blade Lift LEFT |  | 62609 | 12000 | 2027-01-23 | 12 |  | 53483 | 2022-01-07 |  | 20R-9809 | BLADE LIFT CYLINDER
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Transmission Pump |  | 54402.5 | 20000 | 2027-01-23 | 13.75 |  | 37702 | 2021-07-10
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD3830 | Cat 789C | Rear Axle Dog Bone |  | 60741 | 15000 | 2027-01-23 | 14 |  | 49108 | 2022-07-15 |  | 211-4923 | LATERAL LINK, 789
N9500 | WA | CAT | 01 | Prominent Hill | RD4211 | Cat 785C | Air Cond'r-Serv |  | 59732.1 | 5000 | 2027-01-23 | 13.75 |  | 58036 | 2025-11-10
N1002 | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Engine Valve Adj |  | 24820 | 4000 | 2027-01-24 | 14 |  | 24188 | 2026-02-12 |  | 449-9059 | SEAL
N0350 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 20661 | 6000 | 2027-01-24 | 12 |  | 17549 | 2025-04-30
N9050-UP | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Starter Motor UPPER |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N9050-LW | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Starter Motor LOWER |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N1100-L | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Turbo Primary LEFT |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N1300 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Cooling Sys Service |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N2000 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Transmission |  | 61931 | 18000 | 2027-01-25 | 18.5 |  | 48409 | 2023-10-31
N1403 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Jockey Pulley Brgs |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N1301 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Water Pump |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N6000-01 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Brake POS 1 |  | 78363 | 30000 | 2027-01-25 | 14 |  | 51755 | 2021-03-12 |  | 10R-5394 | BRAKE, FRT, 793
N1402 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Fan Pulley Brgs |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N5020-01 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Wheel Bearing POS 1 |  | 78363 | 30000 | 2027-01-25 | 14 |  | 51755 | 2021-03-12 |  | 446-0367 | KIT
N1420 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Air Compressor |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N1302 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Aftercooler Pump |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N8122-01 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Wheel Group POS 1 |  | 78363 | 30000 | 2027-01-25 | 14 |  | 51755 | 2021-03-12 |  | 280-2057 | WHEEL HUB BRK GRP, FRT, 793
N1100-R | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Turbo Primary RIGHT |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N3029 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Uni's T/C - Trans |  | 26206.72 | 10000 | 2027-01-25 | 13.5 |  | 19477.18 | 2025-01-10
N1202 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Fuel Transfer Pump |  | 60487 | 10000 | 2027-01-25 | 7 | 12/05/2026 | 52178 | 2020-05-05
N7467-LU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension LU |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N7467-LL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension LL |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N0102-L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Trk Chn Pin & Bush Trn LEFT |  | 34679 | 4000 | 2027-01-26 | 14 |  | 34081 | 2026-04-14 |  | 569-2544 | TRACK GP
N7467-RL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension RL |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N7460 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Feed |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-9005X | MD6310 P/DOWN CYL
N0111-3L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 3 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0111-3R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 3 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7330-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Travel RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 20R-9462 | MOTOR GP
N7032 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Cooler Fan Hyd |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 11R-1030 | PUMP GP-PISTON
N0551 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Cooler Aircompressor |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-1356+527-8222 | CORE AS-OIL COOLER
N7570-LR | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT REA |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 443-6895X | PEX MD6310 JACK LEG CYL
N0121-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Carrier Roller No 1 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7527-RE | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain REAR |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6795 | CYL GP-127 1
N0112-3R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 13 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 8 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0112-3L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 13 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0111-8R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 8 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0112-2R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 12 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0121-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Carrier Roller No 1 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0112-2L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 12 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7528-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Hyd Op Bit Basket RIGH |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6805 | CYL GP-127 1
N0111-9L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 9 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 11 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0111-9R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 9 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0112-1L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 11 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7541 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Access Ladder |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6798 | CYL GP-076 3
N0112-0R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 10 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0112-0L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 10 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7528-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Hyd Op Bit Basket LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6805 | CYL GP-127 1
N0111-7R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 7 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7527-F | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Dust Curtain FRONT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6795 | CYL GP-127 1
N7524-RE | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - REAR |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N7467-RU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Feed Rope Tension RU |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-9002 | CYLINDER GP-HYDRAULIC -TENSION
N7521 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Pipe Positioner Swing |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6798 | CYLINDER GP
N0140 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Equalizer Bar |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 526-3821 | BAR AS-EQUAL
N0111-4R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 4 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0033-PR | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Water Tank - PRIMARY |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0
N0111-5L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 5 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0111-5R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 5 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0134-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Adjuster RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0111-6L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 6 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7522 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Pipe Positioner Clamp |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-8999 | CYLINDER GP
N0134-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Adjuster LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 200-0409 | ADUSTER GP
N0033-SC | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Water Tank - SECONDARY |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0
N0111-6R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 6 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7524-FR | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock - FRONT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 533-4256 | CYLINDER GP CAROUSEL LOCK
N0111-7L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 7 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0123-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Carrier Roller No 3 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0123-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Carrier Roller No 3 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0122-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Carrier Roller No 2 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0122-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Carrier Roller No 2 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N0111-4L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 4 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Torque Convertor |  | 54615 | 20000 | 2027-01-26 | 15 |  | 38267 | 2019-09-14 |  | 20R-0924 | TORQUE CONVERTOR
N0111-2R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 2 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N1002 | WA | CAT | 95 |  | RD4979 | Cat 789C | Engine Valve Adj |  | 601 | 4000 | 2027-01-26 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N7600-LL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Control Valve LEFT LOWER |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 517-7954 | VALVE GP-CONTROL
N7581 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Swing |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-0146 | CYLINDER GP
N0101-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Chain RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N1312-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Aftercooler Core - LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 523-8685 | CORE AS-AFTC
N7600-LW | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Control Valve LOWER |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 517-7952 | VALVE GP-CONTROL
N7587 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Deck Inspection Hatch |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 548-0995 | CYL GP-051 0
N0105-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Idler RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 248-7151 | IDLER GP
N7608 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Control Valve Jack/Mast Raise |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 514-2137 | VALVE GP-CONTROL
N0105-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Idler LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 248-7151 | IDLER GP
N7234-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Cooler Fan RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 526-3938 | MOTOR GP-PISTON
N0101-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Chain LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 610-2801 | LINK AS-TRACK
N7582 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Clamp |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-0148 | CYLINDER GP
N1320 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Cooling Fan Engine |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 392-4160 | SPIDER-AS-FAN
N1312-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Aftercooler Core - RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 523-8685 | CORE AS-AFTC
N7524 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Carousel Lock |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0
N7669 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Rod Catcher |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6798 | CYLINDER GP HYD
N7575 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Breakout Wrench Rotate |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 524-0147 | CYLINDER GP
N7330-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Travel LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 20R-9462 | MOTOR GP
N7598-UP | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing UPPER |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 539-1901 | CYL GP-127 1
N7100 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Charge |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 594-6741 | PUMP GP-GEAR
N8995 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Operator Seat |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 489-6525+436-8490 | SEAT GP
N7595-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Mast Lock LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6795 | CYLINDER GP-HYDRAULIC -MAST LOCK
N7008-02 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Hydraulic POS 2 |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 20R-9460 | PUMP GP-PISTON
N7038 | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Pump Conv,P/Brk Rel, Brk Cool |  | 54615 | 20000 | 2027-01-26 | 15 |  | 38267 | 2019-09-14 |  | 30R-0359 | PUMP GP-GEAR
N0111-2L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 2 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7600-LU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Control Valve LEFT UPPER |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 517-7953 | VALVE GP-CONTROL
N7008-01 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Hydraulic POS 1 |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 20R-9460 | PUMP GP-PISTON
N7234-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Cooler Fan LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 526-3938 | MOTOR GP-PISTON
N7041 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Cooling Fan Engine |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 11R-1030 | PUMP GP-PISTON
N0111-1R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 1 RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N5000-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Final Drive RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N7598-LO | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Carousel Swing LOWER |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 539-1901 | CYL GP-127 1
N1000 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Engine |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 5875935X | EXCHANGE ENGINE
N3340 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Rotary Head |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 527-5344 | ROTARY HEAD, MD6310
N0102-R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Trk Chn Pin & Bush Trn RIGHT |  | 34679 | 4000 | 2027-01-26 | 14 |  | 34081 | 2026-04-13 |  | 569-2544 | TRACK GP
N3320 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Drive Box |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 503-7615 | PUMP DRIVE,MD6310
N7201 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Air Con |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 419-0777 | MOTOR GP-PSF
N0111-1L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Track Roller 1 LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 528-2933 | ROLLER
N7068 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pump Auxiliary |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 20R-9457 | PUMP GP-PISTON
N7595-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Cyl Mast Lock RIGHT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 515-6795 | CYLINDER GP-HYDRAULIC -MAST LOCK
N5000-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Final Drive LEFT |  | 11349 | 15000 | 2027-01-26 | 15 |  | 0 |  |  | 5283254X | FINAL DRIVE EXCHANGE
N7542-R | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Hyd Cyl Steer RIGHT |  | 68788 | 12000 | 2027-01-27 | 18.5 |  | 61299 | 2025-05-02
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Steering Ball Studs POS 8 |  | 68788 | 12000 | 2027-01-27 | 18.5 |  | 61299 | 2025-05-02
N8442-07 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Steering Ball Studs POS 7 |  | 68788 | 12000 | 2027-01-27 | 18.5 |  | 61299 | 2025-05-02
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Uni's Eng - Pump Drive |  | 47835.6 | 10000 | 2027-01-27 | 13 |  | 41006 | 2020-10-08
N8442-06 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Steering Ball Studs POS 6 |  | 68788 | 12000 | 2027-01-27 | 18.5 |  | 61299 | 2025-05-02
N8442-05 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Steering Ball Studs POS 5 |  | 68788 | 12000 | 2027-01-27 | 18.5 |  | 61299 | 2025-05-02
N7542-L | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Hyd Cyl Steer LEFT |  | 68788 | 12000 | 2027-01-27 | 18.5 |  | 61299 | 2025-05-02
N8995 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Operator Seat |  | 42291 | 6000 | 2027-01-27 | 10 |  | 38734 | 2025-06-03
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | Rear Axle Dog Bone |  | 59952 | 15000 | 2027-01-27 | 14 |  | 48370 | 2022-04-28 |  | 211-4923 | LATERAL LINK, 789
N9500 | WA | CAT | 01 |  | RD4247 | Cat 789C | Air Cond'r-Serv |  | 59268 | 5000 | 2027-01-28 | 20 |  | 59163 | 2024-05-23
N3020 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Drive Shaft Eng - Pump Drive |  | 76600 | 18000 | 2027-01-28 | 14 |  | 62028 | 2023-06-24 |  | 339-6380 | JOINT GP-UNI
N9500 | WA | CAT | 85 |  | LO2121 | Cat 992K | Air Cond'r-Serv |  | 33290 | 6000 | 2027-01-28 | 11 |  | 29988 | 2025-01-01 | THIESS MANAGED
N1002 | WA | CAT | 95 |  | RD4972 | Cat 789C | Engine Valve Adj |  | 566 | 4000 | 2027-01-28 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N3065 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Bearing Unit & Adaptor Shaft |  | 17835 | 6000 | 2027-01-29 | 13 |  | 15035.68 | 2025-09-26
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Air Cond'r-Serv |  | 57617 | 5000 | 2027-01-30 | 20 |  | 57560 | 2024-07-15
N7434-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Bucket Clam LEFT |  | 23756 | 5000 | 2027-01-30 | 18.5 |  | 23334 | 2026-04-30
N0111-7R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Roller 7 RIGHT |  | 23756 | 12000 | 2027-01-30 | 18.5 |  | 16318 | 2025-03-21
N8442-05 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 5 |  | 47332.5 | 10000 | 2027-01-30 | 7.13 |  | 39096 | 2022-01-10
N1002 | WA | CAT | 95 |  | RD4981 | Cat 789C | Engine Valve Adj |  | 539 | 4000 | 2027-01-30 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N8442-07 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 7 |  | 47332.5 | 10000 | 2027-01-30 | 7.13 |  | 39096 | 2022-01-10
N8442-08 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 8 |  | 47332.5 | 10000 | 2027-01-30 | 7.13 |  | 39096 | 2022-01-10
N8442-06 | WA | CAT | 01 | Miralga Creek | RD6527 | Cat 777G | Steering Ball Studs POS 6 |  | 47332.5 | 10000 | 2027-01-30 | 7.13 |  | 39096 | 2022-01-10
N7542-R | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Hyd Cyl Steer RIGHT |  | 39272 | 20000 | 2027-01-31 | 15 |  | 22997 | 2020-03-04 |  | 1U-3182 | CYL, STEERING, 785
N0520 | WA | CAT | 01 |  | RD4247 | Cat 789C | Pre Lube Pump |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 20R-3396 | PRE-LUBE PUMP
N3029 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Uni's T/C - Trans |  | 67791 | 8000 | 2027-01-31 | 18.5 |  | 64377 | 2025-11-22
N7542-R | WA | CAT | 01 |  | RD4247 | Cat 789C | Hyd Cyl Steer RIGHT |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 30R-1082 | STEER CYL 789C
N1430 | WA | CAT | 01 |  | RD4247 | Cat 789C | Air Starter |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16
N9500-MA | WA | CAT | 01 |  | RD4247 | Cat 789C | Air Cond'r-Serv - MAJOR |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 137-2134 | AIR CON GP
N7474-L | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Hyd Cyl Hoist LEFT |  | 53351 | 24000 | 2027-01-31 | 12 |  | 32328 | 2018-12-26
N3320 | WA | CAT | 01 |  | RD4247 | Cat 789C | Pump Drive Box |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 11R-1517 | DRIVE GP-PUMP
N1000 | WA | CAT | 01 |  | RD4247 | Cat 789C | Engine |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 175-5289 | FLEXI ENGINE
N1310 | WA | CAT | 01 |  | RD4247 | Cat 789C | Radiator |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 145-1226 | PEX SX 789C RADIATOR
N7120 | WA | CAT | 01 |  | RD4247 | Cat 789C | Pump Steering |  | 59268 | 20000 | 2027-01-31 | 20 |  | 44234 | 2020-12-16 |  | 0R-7656 | REMAN PUMP GP
N0105-LR | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Idler LFT REAR |  | 17737.5 | 6000 | 2027-01-31 | 6.35 |  | 13314.53 | 2024-08-10
N1100-RF | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Turbo Primary RHT FRONT |  | 54615 | 10000 | 2027-02-01 | 15 |  | 48352 | 2021-06-18 |  | 20R-6651 | RE-MAN TURBO GP
N9500 | WA | CAT | 85 | McPhee Creek | RD6606 | Cat 789D | Air Cond'r-Serv |  | 4532.2 | 0 | 2027-02-01 | 11.19 |  | 0 | 2026-02-01
N9500 | WA | CAT | 85 | McPhee Creek | RD6604 | Cat 789D | Air Cond'r-Serv |  | 6718.6 | 0 | 2027-02-01 | 11.19 |  | 0 | 2026-02-01
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Ride Strut POS 1 |  | 58852 | 20000 | 2027-02-01 | 15 |  | 42584 | 2019-10-07 |  | 347-7423 | SUSP CYL
N9500 | WA | CAT | 85 | McPhee Creek | RD6605 | Cat 789D | Air Cond'r-Serv |  | 4708.7 | 0 | 2027-02-01 | 11.19 |  | 0 | 2026-02-01
N9500 | WA | CAT | 85 | McPhee Creek | RD6603 | Cat 789D | Air Cond'r-Serv |  | 7161 | 0 | 2027-02-01 | 11.19 |  | 0 | 2026-02-01
N1100-RR | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Turbo Primary RHT REAR |  | 54615 | 10000 | 2027-02-01 | 15 |  | 48352 | 2021-06-18 |  | 20R-6651 | RE-MAN TURBO GP
N1002 | WA | CAT | 01 |  | RD2642 | Cat 773F | Engine Valve Adj |  | 27652 | 3000 | 2027-02-02 | 12 |  | 27656 | 2025-11-11
N9501 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | A/C Compressor |  | 82501 | 10000 | 2027-02-03 | 18.5 |  | 77141 | 2025-06-10 |  | 217-4448 | COMPRESSOR GP-REFRIGERANT
N6200-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 2 |  | 82501 | 12000 | 2027-02-03 | 18.5 |  | 75138 | 2025-02-23 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 1 |  | 82501 | 12000 | 2027-02-03 | 18.5 |  | 75138 | 2025-02-23 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-01 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 1 |  | 82501 | 12000 | 2027-02-03 | 18.5 |  | 75138 | 2025-02-23 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N6200-02 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Press Convertor POS 2 |  | 82501 | 12000 | 2027-02-03 | 18.5 |  | 75138 | 2025-02-23 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N7020 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Pump Brake |  | 70621 | 12000 | 2027-02-03 | 15 |  | 62383 | 2024-07-19
N9501 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | A/C Compressor |  | 82501 | 10000 | 2027-02-03 | 18.5 |  | 77141 | 2025-06-10 |  | 217-4448 | COMPRESSOR GP-REFRIGERANT
N9501 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | A/C Compressor |  | 45807 | 7500 | 2027-02-04 | 14 |  | 41833 | 2024-05-17 |  | 106-5122 | COMPRESSOR
N1202-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Fuel Transfer Pump EN 1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N1002 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Engine Valve Adj |  | 34192 | 4000 | 2027-02-04 | 12 |  | 33215 | 2026-03-15
N8995 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Operator Seat |  | 79044 | 6000 | 2027-02-04 | 14 |  | 76570 | 2025-11-30 |  | 384-6168 | SEAT GP-SUSPENSION
N1210-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Fuel Injectors EN2 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N9152-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Starter Motor Lower EN1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N1300-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooling Sys Service EN1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N9501-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | A/C Compressor LEFT |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-04
N1403-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Jockey Pulley Brgs EN2 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N7605 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Steering Hmu |  | 59517 | 24000 | 2027-02-04 | 18.5 |  | 40173 | 2021-03-28
N9501-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | A/C Compressor RIGHT |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-05
N9020-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Alternator EN1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N9151-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Starter Motor Upper EN1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N9500 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Air Cond'r-Serv |  | 31311 | 6000 | 2027-02-04 | 14 |  | 28840 | 2025-11-05
N6062 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Oil Cooler Rear Brakes |  | 69200 | 26000 | 2027-02-04 | 18.5 |  | 47868 | 2022-01-07
N7160 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Pump Axle Lube/Cooler |  | 59517 | 24000 | 2027-02-04 | 18.5 |  | 40173 | 2021-03-28
N7201-R | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Motor Air Con RIGHT |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-06
N9020-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Alternator EN2 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-06
N1403-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Jockey Pulley Brgs EN1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N1300-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooling Sys Service EN2 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N7169 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Hyd Mtr Axle Lube/Cooler |  | 59517 | 24000 | 2027-02-04 | 18.5 |  | 40173 | 2021-03-28
N1210-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Fuel Injectors EN1 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N7201-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Motor Air Con LEFT |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-05
N1202-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Fuel Transfer Pump EN2 |  | 23402 | 9000 | 2027-02-04 | 18.5 |  | 19070 | 2025-10-09
N7613 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Hyd Cooler Steering/Eng Fan |  | 59517 | 24000 | 2027-02-04 | 18.5 |  | 40173 | 2021-03-28
N1100-RR | WA | CAT | 01 |  | RD4247 | Cat 789C | Turbo Primary RHT REAR |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-11 |  | 20R-6651 | RE-MAN TURBO GP
N2090 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Drv Coupling |  | 11349 | 5000 | 2027-02-05 | 15 |  | 10140 | 2026-02-24 |  | 520-7010 | COUPLING GP-
N1403 | WA | CAT | 01 |  | RD4247 | Cat 789C | Jockey Pulley Brgs |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-05 |  | 4S-5367 | BUSHING AS
N1002 | WA | CAT | 95 |  | RD4980 | Cat 789C | Engine Valve Adj |  | 461 | 4000 | 2027-02-05 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N1300 | WA | CAT | 01 |  | RD4247 | Cat 789C | Cooling Sys Service |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-08 |  | 418-4162 | REGULATOR TE
N7570-RF | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT FRO |  | 17257 | 10000 | 2027-02-05 | 14 |  | 10796 | 2024-10-26 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N1100-LF | WA | CAT | 01 |  | RD4247 | Cat 789C | Turbo Primary LFT FRONT |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-11 |  | 20R-6651 | RE-MAN TURBO GP
N1100-RF | WA | CAT | 01 |  | RD4247 | Cat 789C | Turbo Primary RHT FRONT |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-10 |  | 20R-6651 | RE-MAN TURBO GP
N9500 | WA | CAT | 19 | McPhee Creek | DR1080 | Cat MD6250 | Air Cond'r-Serv |  | 444 | 5000 | 2027-02-05 | 18 |  | 0
N3024-F | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Uni's Tfr - Bevel Gear FRONT |  | 28724 | 8000 | 2027-02-05 | 15 |  | 24518 | 2025-04-24
N8995 | WA | CAT | 85 | Iron Bridge | GR1528 | Cat 14M | Operator Seat |  | 3973 | 6000 | 2027-02-05 | 8 |  | 0
N1402 | WA | CAT | 01 |  | RD4247 | Cat 789C | Fan Pulley Brgs |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-05 |  | 105-2273 | FAN HUB PULLEY,789
N1100-LR | WA | CAT | 01 |  | RD4247 | Cat 789C | Turbo Primary LFT REAR |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-11 |  | 20R-6651 | RE-MAN TURBO GP
N7600 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Control Valve |  | 55934 | 30000 | 2027-02-05 | 13.5 |  | 29354 | 2019-01-11 |  | 20R-9134 | VALVE GROUP-CONTROL
N1202 | WA | CAT | 01 |  | RD4247 | Cat 789C | Fuel Transfer Pump |  | 59268 | 10000 | 2027-02-05 | 20 |  | 54329 | 2022-05-08 |  | 10R-9838 | PUMP GP-F XFR
N7605 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Steering Hmu |  | 56902.96 | 12000 | 2027-02-05 | 13.5 |  | 48323.96 | 2024-09-03
N1402 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Fan Pulley Brgs |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 6Y-7651 | CONE BEARING
N1300 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Cooling Sys Service |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 418-4162 | REGULATOR
N1100-R | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Turbo Primary RIGHT |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 20R-3423 | TURBO GRP
N1004 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Engine Midlife |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Uni's T/C - Trans |  | 49506 | 10000 | 2027-02-06 | 14.5 |  | 43183 | 2024-05-25 |  | 8R-7036 | SPIDER
N1100-L | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Turbo Primary LEFT |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 20R-3423 | TURBO GRP
N3029 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Uni's T/C - Trans |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 8R-7036 | SPIDER
N1430 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Air Starter |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14
N1202 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Fuel Transfer Pump |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 10R-9838 | PUMP GP-F XFR
N1403 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Jockey Pulley Brgs |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14 |  | 4S-5367 | BUSHING
N3021 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Uni's Eng - Pump Drive |  | 65021 | 10000 | 2027-02-06 | 8.5 |  | 57177 | 2020-05-14
N3320 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Pump Drive Box |  | 39272 | 20000 | 2027-02-07 | 15 |  | 23096 | 2017-12-02 |  | 6V-8260 | SEAL,O-RING
N1002 | WA | CAT | 95 |  | RD4976 | Cat 789C | Engine Valve Adj |  | 427 | 4000 | 2027-02-07 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N1002 | SA | CAT | 01 | Prominent Hill | DZ1932 | Cat D10T | Engine Valve Adj |  | 49963 | 4000 | 2027-02-07 | 5.5 |  | 47366 | 2024-07-26 |  | 449-9059 | SEAL
N2004 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Transmission Pump |  | 39272 | 20000 | 2027-02-07 | 15 |  | 23099 | 2017-12-03 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N1430 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Air Starter |  | 76600 | 9000 | 2027-02-07 | 14 |  | 71175 | 2025-04-23 |  | 10R-9657 | MOTOR GP-AIR STG
N7065 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Pump Hoist/ Brk Cooling |  | 39272 | 20000 | 2027-02-07 | 15 |  | 23099 | 2017-12-03 |  | 10R-7971 | PUMP, HOIST, REMAN
N1310 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Radiator |  | 82501 | 20000 | 2027-02-08 | 18.5 | 11/06/2026 | 67229 | 2023-12-08 |  | 334-6025 | RADIATOR COOLING GP
N1310 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Radiator |  | 82501 | 20000 | 2027-02-08 | 18.5 |  | 67229 | 2023-12-08 |  | 334-6025 | RADIATOR COOLING GP
N7305 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Motor Thrust/Pullback |  | 32622 | 10000 | 2027-02-09 | 13.79 |  | 26167 | 2024-01-31
N5000-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Final Drive POS 4 |  | 64653 | 20000 | 2027-02-09 | 14 |  | 48250 | 2020-12-25 |  | 0R-9043 | FINAL DRIVE 789C
N8200-02 | WA | CAT | 01 | Disposals | RD4234 | Cat 789C | Ride Strut POS 2 |  | 60498 | 20000 | 2027-02-10 | 15 |  | 44367 | 2019-09-18 |  | 347-7423 | SUSP CYL
N0556 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Air Safety Valve |  | 11349 | 0 | 2027-02-10 | 15 |  | 9907 | 2026-02-10 |  | 549-2163 | VALVE-RELIEF 160psi
N3028 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Drive Shaft T/C - Trans |  | 69200 | 16000 | 2027-02-10 | 18.5 |  | 57974 | 2024-09-24
N8443-LL | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Rear Axle Control Arm L/LEFT |  | 62083 | 20000 | 2027-02-11 | 18.5 |  | 46875 | 2023-10-27
N8441 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Rear Axle Dog Bone |  | 54428 | 25000 | 2027-02-11 | 17 |  | 33839 | 2020-01-31
N8443-LR | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Rear Axle Control Arm L/RIGHT |  | 62083 | 20000 | 2027-02-11 | 18.5 |  | 46875 | 2023-10-27
N7021 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Pump Brake Cooling |  | 76600 | 40000 | 2027-02-12 | 14 |  | 40240 | 2018-03-06 |  | 20R-7440 | PUMP GP-GEAR
N2002 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Oil Cooler - Transmission |  | 58874 | 20000 | 2027-02-12 | 13.75 |  | 42452 | 2022-11-29
N7164 | WA | CAT | 85 |  | LO2121 | Cat 992K | Pump & Motor Axle Cooler |  | 33290 | 12000 | 2027-02-12 | 11 |  | 24150 | 2024-03-12 | THIESS MANAGED
N7106 | WA | CAT | 85 |  | LO2121 | Cat 992K | Pump Steering Pilot/Cooling |  | 33290 | 12000 | 2027-02-12 | 11 |  | 24150 | 2024-03-12 | THIESS MANAGED
N3029 | WA | CAT | 19 | Iron Bridge | RD4916 | Cat 793F | Uni's T/C - Trans |  | 69479 | 8000 | 2027-02-12 | 18.5 |  | 66298 | 2025-12-13
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Radiator |  | 58874 | 20000 | 2027-02-13 | 13.75 |  | 42466 | 2022-12-20
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Transmission Pump |  | 58874 | 20000 | 2027-02-13 | 13.75 |  | 42466 | 2022-12-21
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Pump Drive Box |  | 58874 | 20000 | 2027-02-13 | 13.75 |  | 42466 | 2022-12-20
N5000-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Final Drive RIGHT |  | 47986 | 15000 | 2027-02-13 | 12 |  | 36115 | 2022-08-28 |  | 20R-6295 | FINAL DRIVE, D10
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Transmission Pump |  | 41713 | 20000 | 2027-02-13 | 15 |  | 37262 | 2022-05-12 |  | 0R-7822 | PUMP GP-GEAR (TRANSMISSION)
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Engine |  | 58874 | 20000 | 2027-02-13 | 13.75 |  | 42466 | 2022-12-20
N8995 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Operator Seat |  | 68788 | 6000 | 2027-02-13 | 18.5 |  | 67625 | 2026-03-22
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Air Cond'r-Serv - MAJOR |  | 58874 | 20000 | 2027-02-13 | 13.75 |  | 42466 | 2022-12-21
N9500 | WA | CAT | 01 | Sanjiv Ridge | LO6590 | Cat 980H | Air Cond'r-Serv |  | 11209.7 | 0 | 2027-02-14 | 1.18 |  | 11018 | 2026-02-14
N7542-R | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Hyd Cyl Steer RIGHT |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 1U-3182 | CYL, STEERING, 785
N7037 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Pump Conv P/Brake Release |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877.6 | 2022-01-28
N2050 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Torque Convertor |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N7120 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Pump Steering |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28
N8140 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Steering Y Piece |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28
N4000 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Bevel Gear |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N7542-L | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Hyd Cyl Steer LEFT |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 1U-3182 | CYL, STEERING, 785
N3320 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Pump Drive Box |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 6V-8260 | SEAL,O-RING
N8137-L | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Steering Linkage Group LEFT |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 |  | 2A-7217 | LINK,STEERING,785
N8122-02 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Wheel Group POS 2 |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE | 309-9597 | WHEEL HUB BRK GRP, FRT, 785C
N8137-R | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Steering Linkage Group RIGHT |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 |  | 2A-7217 | LINK,STEERING,785
N2450 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Drv Cpling Fan Pump-Trans Pump |  | 34679 | 7000 | 2027-02-14 | 14 |  | 31352 | 2025-10-27
N8200-01 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Ride Strut POS 1 |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N3028 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Drive Shaft T/C - Trans |  | 69633 | 16000 | 2027-02-14 | 18.5 |  | 58478 | 2024-10-06
N5000-03 | NT | CAT | 01 | FleetCo | RD6033 | Cat 785C | Final Drive POS 3 |  | 54428 | 20000 | 2027-02-14 | 17 |  | 38877 | 2022-01-28 | REQUIRED IN MACKAY 3 MONTHS BEFORE START DATE
N9500 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Air Cond'r-Serv |  | 17835 | 0 | 2027-02-14 | 13 |  | 16709 | 2026-02-14
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Uni's Eng - Pump Drive |  | 75619 | 5000 | 2027-02-15 | 19 |  | 75621 | 2026-03-08 |  | 390-8908 | SPIDER & BEARING AS
N8995 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Operator Seat |  | 69200 | 6000 | 2027-02-15 | 18.5 |  | 68065 | 2026-03-31
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD2131 | Cat 793D | Air Cond'r-Serv |  | 75619 | 5000 | 2027-02-15 | 19 |  | 75621 | 2026-03-12 |  | 385-0244 | MOTOR AS-BLOWER
N0121-L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Carrier Roller No 1 LEFT |  | 9782 | 14000 | 2027-02-16 | 16 |  | 0 | 2025-06-20
N9720 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Autonomy Cabinet |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N0105-L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Idler LEFT |  | 9782 | 14000 | 2027-02-16 | 16 |  | 0 | 2025-06-20
N9731 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Electrical Harness |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N0105-R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Idler RIGHT |  | 9782 | 14000 | 2027-02-16 | 16 |  | 0 | 2025-06-20
N9735-CA | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Hardware - CABIN |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N0121-R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Carrier Roller No 1 RIGHT |  | 9782 | 14000 | 2027-02-16 | 16 |  | 0 | 2025-06-20
N9735-DE | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Hardware - DECK |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N8200-04 | WA | CAT | 01 | FleetCo | RD4377 | Cat 785C | Ride Strut POS 4 |  | 65021 | 20000 | 2027-02-16 | 8.5 |  | 47265 | 2018-10-12 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N9735-FD | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Hardware - FIELD |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N7340 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 22440 | 6000 | 2027-02-16 | 12 |  | 19610 | 2025-09-20
N9735-IO | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Hardware - I/O |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N9735-JC | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Hardware - JUMPER CONNECTOR |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N0302 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Feed Sprocket |  | 22440 | 6000 | 2027-02-16 | 12 |  | 19610 | 2025-09-20
N0104-L | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Sprockets LEFT |  | 9782 | 14000 | 2027-02-16 | 16 |  | 0 | 2025-06-20
N0104-R | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Sprockets RIGHT |  | 9782 | 14000 | 2027-02-16 | 16 |  | 0 | 2025-06-20
N9735-MA | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | AS Hardware - MAST |  | 16307 | 20000 | 2027-02-16 | 14 |  | 0
N7474-R | WA | CAT | 01 |  | RD4246 | Cat 789C | Hyd Cyl Hoist RIGHT |  | 54387 | 24000 | 2027-02-16 | 20 |  | 35658 | 2020-05-18 |  | 438-6225 | CYLINDER GP-HOIST
N9020 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Alternator |  | 16307 | 7500 | 2027-02-16 | 14 |  | 12505 | 2025-09-14 |  | 11R-1235 | ALTERNATOR GP
N9050-UP | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Starter Motor UPPER |  | 79726 | 10000 | 2027-02-17 | 18.5 |  | 74636 | 2025-07-10 |  | 10R-9816 | STARTING MOTOR GP-ELECTRIC
N0102-R | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Trk Chn Pin & Bush Trn RIGHT |  | 23174 | 4000 | 2027-02-17 | 14 |  | 22880 | 2026-05-07
N9050-LW | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Starter Motor LOWER |  | 79726 | 10000 | 2027-02-17 | 18.5 |  | 74636 | 2025-07-10 |  | 10R-9816 | STARTING MOTOR GP-ELECTRIC
N0102-L | WA | CAT | 19 | Iron Bridge | DZ3420 | Cat D10T | Trk Chn Pin & Bush Trn LEFT |  | 23174 | 4000 | 2027-02-17 | 14 |  | 22880 | 2026-05-07
N8995 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Operator Seat |  | 77195 | 6000 | 2027-02-18 | 14 |  | 74915 | 2025-11-18 |  | 384-6168 | SEAT GP-SUSPENSION
N3029 | WA | CAT | 01 |  | RD2642 | Cat 773F | Uni's T/C - Trans |  | 27652 | 10000 | 2027-02-18 | 12 |  | 20840 | 2023-07-20
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | Press Converter FRONT |  | 58874 | 10000 | 2027-02-18 | 13.75 |  | 52533 | 2024-12-11
N9500 | WA | CAT | 95 | Iron Bridge | LO1965 | Cat 994H | Air Cond'r-Serv |  | 34192 | 6000 | 2027-02-18 | 12 |  | 31381 | 2025-11-07
N0105-L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Idler LEFT |  | 55435 | 18000 | 2027-02-18 | 18.5 |  | 42347 | 2023-05-04
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4245 | Cat 789C | Drive Shaft T/C - Trans |  | 55805 | 20000 | 2027-02-18 | 14 |  | 39522 | 2019-12-06 |  | 10R-5185 | DRIVESHAFT TC-TRANS
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD4223 | Cat 785D | A/C Compressor |  | 58874 | 10000 | 2027-02-19 | 13.75 |  | 52548 | 2024-12-22
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Engine Valve Adj |  | 44852.3 | 4000 | 2027-02-19 | 15 |  | 44852 | 2026-02-12
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Engine Valve Adj |  | 44852.3 | 4000 | 2027-02-19 | 15 |  | 44852 | 2026-02-12
N9500 | SA | CAT | 01 | Prominent Hill | RD2618 | Cat 793D | Air Cond'r-Serv |  | 79490 | 6000 | 2027-02-19 | 14 |  | 77233 | 2026-01-04 |  | 385-0244 | MOTOR AS-BLOWER
N1002 | WA | CAT | 95 |  | RD4973 | Cat 789C | Engine Valve Adj |  | 262 | 4000 | 2027-02-19 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N6062-F | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 79044 | 20000 | 2027-02-20 | 14 |  | 62792 | 2023-02-27 |  | 10R-5675 | CORE AS OIL
N7542-R | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Hyd Cyl Steer RIGHT |  | 79044 | 20000 | 2027-02-20 | 14 |  | 62792 | 2023-02-27 |  | 20R-5304 | STEER CYL
N6061 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Oil Cooler Front Brakes |  | 79044 | 20000 | 2027-02-20 | 14 |  | 62792 | 2023-02-27 |  | 10R-5673 | CORE AS OIL
N7024 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Hyd Motor Brake Cooling |  | 71898 | 22000 | 2027-02-20 | 18.5 |  | 54858 | 2023-08-16
N8995 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Operator Seat |  | 59122 | 6000 | 2027-02-20 | 18.5 |  | 58084 | 2026-03-29
N8995 | WA | CAT | 85 |  | LO2122 | Cat 992K | Operator Seat |  | 35037 | 6000 | 2027-02-20 | 11 |  | 31982 | 2025-03-28 | THIESS MANAGED
N6062-RE | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 79044 | 20000 | 2027-02-20 | 14 |  | 62792 | 2023-02-27 |  | 10R-5675 | CORE AS OIL
N9500 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Air Cond'r-Serv |  | 12951 | 4000 | 2027-02-20 | 14 |  | 12703 | 2026-05-09
N9500 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Air Cond'r-Serv |  | 54833.54 | 0 | 2027-02-20 | 12.5 |  | 53773.57 | 2026-02-20
N1310 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Radiator |  | 52003.6 | 18000 | 2027-02-21 | 12 |  | 37227 | 2021-07-29
N7542-R | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Hyd Cyl Steer RIGHT |  | 14154.15 | 16000 | 2027-02-21 | 6.87 |  | 0 | 2022-10-17
N9501 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | A/C Compressor |  | 79726 | 10000 | 2027-02-21 | 18.5 |  | 74703 | 2025-07-14 |  | 217-4448 | COMPRESSOR GP-REFRIGERANT
N8995 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Operator Seat |  | 25353 | 6000 | 2027-02-21 | 12.5 |  | 22714 | 2025-10-31
N6000-02 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Brake POS 2 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N7542-L | WA | CAT | 660 | Sanjiv Ridge | LO6110 | Cat 993K | Hyd Cyl Steer LEFT |  | 14154.15 | 16000 | 2027-02-21 | 6.87 |  | 0 | 2022-10-17
N6000-01 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Brake POS 1 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N8200-01 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Ride Strut POS 1 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N7232 | NT | CAT | 01 | FleetCo | DZ1255 | Cat D10T | Hyd Motor Engine Fan |  | 62609 | 15000 | 2027-02-21 | 12 |  | 50836 | 2020-10-15 |  | 10R-5601 | MOTOR GP
N9500 | SA | CAT | 19 | Prominent Hill | EX2750 | Cat 340 | Air Cond'r-Serv |  | 1043 | 4000 | 2027-02-21 | 11 |  | 0
N8200-02 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Ride Strut POS 2 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N8122-02 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Wheel Group POS 2 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N5020-01 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Wheel Bearing POS 1 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N6020 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Park Brake |  | 70621 | 12000 | 2027-02-21 | 15 |  | 62649 | 2024-08-08
N9020 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Alternator |  | 31311 | 9000 | 2027-02-21 | 14 |  | 26075 | 2025-04-27
N5000-04 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Final Drive POS 4 |  | 66379.67 | 20000 | 2027-02-21 | 12.5 |  | 49737 | 2021-01-18
N8122-01 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Wheel Group POS 1 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N5020-02 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Wheel Bearing POS 2 |  | 68788 | 22000 | 2027-02-21 | 18.5 |  | 51766 | 2022-08-18
N8443-LR | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Rear Axle Control Arm L/RIGHT |  | 59122 | 20000 | 2027-02-22 | 18.5 |  | 44110 | 2021-12-22
N8995 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Operator Seat |  | 55934 | 6000 | 2027-02-22 | 13.5 |  | 53582 | 2025-09-15 |  | 443-8104 | CAT OPERATOR SEAT
N1400 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Belt Tensioner Assembly |  | 44396 | 12000 | 2027-02-23 | 15 |  | 36455 | 2024-12-23
N6200-F | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Press Converter FRONT |  | 53351 | 10000 | 2027-02-24 | 12 |  | 46615 | 2023-09-22 |  | 8X-7220 | CHAMBER, BRAKE
N6200-RR | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Press Converter RIGHT REAR |  | 53351 | 10000 | 2027-02-24 | 12 |  | 46615 | 2023-09-22 |  | 8X-7220 | CHAMBER, BRAKE
N0556 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Air Safety Valve |  | 16307 | 0 | 2027-02-24 | 14 |  | 15257 | 2026-02-24 |  | 549-2163 | VALVE-RELIEF 160psi
N7232 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Motor Engine Fan |  | 18651 | 12000 | 2027-02-24 | 13 |  | 10185 | 2024-01-05
N6200-LR | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Press Converter LEFT REAR |  | 53351 | 10000 | 2027-02-24 | 12 |  | 46615 | 2023-09-22 |  | 8X-7220 | CHAMBER, BRAKE
N0556 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Air Safety Valve |  | 21508 | 0 | 2027-02-25 | 12 | 28/05/2026 | 20495 | 2026-02-25
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Operator Seat |  | 64653 | 6000 | 2027-02-25 | 14 |  | 62475 | 2023-12-01 |  | 384-6168 | SEAT GP
N7570-RF | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT FRO |  | 12951 | 10000 | 2027-02-25 | 14 |  | 6773 | 2025-03-23 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Hyd Cyl Hoist LEFT |  | 49506 | 24000 | 2027-02-25 | 14.5 |  | 29464 | 2019-01-31
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Hyd Cyl Hoist RIGHT |  | 49506 | 24000 | 2027-02-25 | 14.5 |  | 29464 | 2019-01-31
N2002 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Oil Cooler - Transmission |  | 65569 | 20000 | 2027-02-26 | 18.5 |  | 50629 | 2023-10-27
N7330-RF | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Motor Travel RHT FRONT |  | 23756 | 18000 | 2027-02-26 | 18.5 |  | 10831 | 2024-05-18
N7330-RR | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Motor Travel RHT REAR |  | 23756 | 18000 | 2027-02-26 | 18.5 |  | 10831 | 2024-05-18
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Operator Seat |  | 70515 | 6000 | 2027-02-26 | 19 |  | 69728 | 2026-01-14 |  | 384-6168 | SEAT GP-SUSPENSION
N8443-LL | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Rear Axle Control Arm L/LEFT |  | 65569 | 20000 | 2027-02-26 | 18.5 |  | 50629 | 2023-10-27
N7420-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Hyd Cyl Blade Lift LEFT |  | 55934 | 12000 | 2027-02-26 | 13.5 |  | 47639 | 2024-04-28 |  | 20R-9809 | BLADE LIFT CYLINDER
N9500 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Air Cond'r-Serv |  | 71548 | 5000 | 2027-02-27 | 15 |  | 70677 | 2024-03-14
N7627 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Valve Track Oscillation |  | 21508 | 12000 | 2027-02-27 | 12 |  | 12812 | 2023-12-07
N0102-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Trk Chn Pin & Bush Trn RIGHT |  | 31311 | 4000 | 2027-02-27 | 14 |  | 31167 | 2026-05-15 |  | 569-2544 | TRACK GP
N7597 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Cyl Boom Swing |  | 21508 | 12000 | 2027-02-27 | 12 |  | 12812 | 2023-12-11
N7594 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Cyl Dust Hood |  | 21508 | 12000 | 2027-02-27 | 12 |  | 12812 | 2023-12-05
N7480-R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation RIGH |  | 21508 | 12000 | 2027-02-27 | 12 |  | 12812 | 2023-12-14
N7480-L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation LEFT |  | 21508 | 12000 | 2027-02-27 | 12 |  | 12812 | 2023-12-14
N9500-MA | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Air Cond'r-Serv - MAJOR |  | 21508 | 12000 | 2027-02-27 | 12 | 28/05/2026 | 12812 | 2023-12-15
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Brake Slack Adj FRONT |  | 49506 | 20000 | 2027-02-27 | 14.5 |  | 33497 | 2019-12-31 |  | 566-9762 | SLACK ADJUSTER
N7044 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Cooler Fan Hyd |  | 21508 | 12000 | 2027-02-27 | 12 |  | 12812 | 2023-12-10
N0111-1L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 1 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0112-0R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 10 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0101-L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Chain LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-15
N0111-3L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 3 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0101-R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Chain RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0121-L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Carrier Roller No 1 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N5000-R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Final Drive RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-2R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 2 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-2L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 2 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0345 | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Hose Drum Assembly |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0104-L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Sprockets LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N5000-L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Final Drive LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0104-R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Sprockets RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-3R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 3 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-1R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 1 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0112-0L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 10 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0121-R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Carrier Roller No 1 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-6R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 6 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-4L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 4 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-8R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 8 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-5L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 5 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-7R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 7 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-4R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 4 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-8L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 8 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-7L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 7 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-5R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 5 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-9L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 9 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-6L | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 6 LEFT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N0111-9R | WA | EPI | 85 | Iron Bridge | DR3119 | Epiroc D65 XLF MKII | Track Roller 9 RIGHT |  | 21534 | 9000 | 2027-02-28 | 12 |  | 15846 | 2024-12-05
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Air Cond'r-Serv |  | 54615 | 5000 | 2027-03-01 | 15 |  | 53773 | 2023-06-29
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Uni's T/C - Trans |  | 66379.67 | 10000 | 2027-03-01 | 12.5 |  | 59841.74 | 2024-10-10
N3021 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Uni's Eng - Pump Drive |  | 66379.67 | 10000 | 2027-03-01 | 12.5 |  | 59841.74 | 2024-10-10
N2090 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Drv Coupling |  | 5839 | 5000 | 2027-03-02 | 14 |  | 4724.9 | 2026-03-18 |  | 520-7010 | COUPLING GP-
N2435 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 5839 | 5000 | 2027-03-02 | 14 |  | 4724.9 | 2026-03-17 |  | 553-9494 | ELEMENT
N0100-L | WA | CAT | 85 | McPhee Creek | DZ6660 | Cat D10T2 | Track Group LEFT |  | 5222.3 | 2000 | 2027-03-02 | 7.2 |  | 5225 | 2026-04-01
N0100-R | WA | CAT | 85 | McPhee Creek | DZ6660 | Cat D10T2 | Track Group RIGHT |  | 5222.3 | 2000 | 2027-03-02 | 7.2 |  | 5225 | 2026-04-01
N7120 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Pump Steering |  | 60509.94 | 20000 | 2027-03-03 | 12.5 |  | 44000 | 2020-11-18
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Press Converter FRONT |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 8W-3405 | CHAMBER, BRAKE
N0101-R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Chain RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-5R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 5 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N1100-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Turbo Primary LFT REAR |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 20R-6651 | RE-MAN TURBO GP
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Press Converter LEFT REAR |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 8W-3405 | CHAMBER, BRAKE
N0111-6L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 6 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-7L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 7 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0101-L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Chain LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0101-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Track Chain LEFT |  | 46895 | 6000 | 2027-03-03 | 13.5 |  | 44668 | 2025-07-03 |  | 569-2544 | TRACK GP
N0111-6R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 6 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N5000-L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Final Drive LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N1100-RF | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Turbo Primary RHT FRONT |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 20R-6651 | RE-MAN TURBO GP
N0111-7R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 7 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-5L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 5 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-3L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 3 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-4L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 4 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0112-0R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 10 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-9R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 9 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0121-L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Carrier Roller No 1 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-2R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 2 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0121-R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Carrier Roller No 1 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-9L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 9 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-4R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 4 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0104-L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Sprockets LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0345 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Hose Drum Assembly |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-8R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 8 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-2L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 2 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-8L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 8 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-1R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 1 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0111-1L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 1 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N9500 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Air Cond'r-Serv |  | 68788 | 4000 | 2027-03-03 | 18.5 |  | 69950 | 2025-11-02
N0112-0L | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 10 LEFT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0104-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Sprockets LEFT |  | 55934 | 6000 | 2027-03-03 | 13.5 |  | 53699 | 2025-09-24 |  | 433-6739 | 7796590
N0104-R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Sprockets RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Fuel Transfer Pump |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 10R-9838 | PUMP GP-F XFR
N0111-3R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Track Roller 3 RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N5000-R | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Final Drive RIGHT |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N0101-R | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Track Chain RIGHT |  | 46895 | 6000 | 2027-03-03 | 13.5 |  | 44668 | 2025-07-03 |  | 569-2544 | TRACK GP
N7460-05 | WA | EPI | 85 | Plant Idle - Mining West | DR3148 | Epiroc D65 XLF MKII | Hyd Cyl Feed Swing |  | 5373 | 9000 | 2027-03-03 | 13 |  | 0
N2100 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Transfer Case |  | 44396 | 24000 | 2027-03-03 | 15 |  | 24587 | 2022-08-24
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Jockey Pulley Brgs |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 4S-5367 | BUSHING AS
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Alternator |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 10R-8755 | ALTERNATOR GP -B
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Uni's Eng - Pump Drive |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 108-6587 | BEARING,SPIDER
N1100-LF | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Turbo Primary LFT FRONT |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 20R-6651 | RE-MAN TURBO GP
N0104-R | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Sprockets RIGHT |  | 55934 | 6000 | 2027-03-03 | 13.5 |  | 53699 | 2025-09-24 |  | 433-6739 | 7796592
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Press Converter RIGHT REAR |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 8W-3405 | CHAMBER, BRAKE
N1100-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Turbo Primary RHT REAR |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 20R-6651 | RE-MAN TURBO GP
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Uni's T/C - Trans |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 363-1923 | MAIN DRIVESHAFT UNI
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Cooling Sys Service |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 418-4162 | REGULATOR TE
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Fan Pulley Brgs |  | 67187 | 10000 | 2027-03-03 | 14 |  | 61097 | 2023-09-23 |  | 105-2273 | FAN HUB PULLEY,789
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Hyd Cyl Hoist LEFT |  | 67187 | 24000 | 2027-03-04 | 14 |  | 47111 | 2020-09-02 |  | 438-6225 | CYLINDER GP-HOIST
N7474-L | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Hyd Cyl Hoist LEFT |  | 60509.94 | 30000 | 2027-03-04 | 12.5 |  | 34005 | 2018-04-29
N1002 | WA | CAT | 95 |  | RD4975 | Cat 789C | Engine Valve Adj |  | 84 | 4000 | 2027-03-04 | 14 |  | 0 |  |  | 272-0760 | SEAL-PIP
N8122-02 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Wheel Group POS 2 |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N8200-03 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Ride Strut POS 3 |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N4000 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Bevel Gear |  | 46895 | 15000 | 2027-03-05 | 13.5 |  | 35684 | 2023-05-20 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N8200-01 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Ride Strut POS 1 |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N8443-LL | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Rear Axle Control Arm L/LEFT |  | 67791 | 20000 | 2027-03-05 | 18.5 |  | 52985 | 2023-10-31
N8122-01 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Wheel Group POS 1 |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N8200-04 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Ride Strut POS 4 |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N8443-LR | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Rear Axle Control Arm L/RIGHT |  | 67791 | 20000 | 2027-03-05 | 18.5 |  | 52985 | 2023-10-31
N7474-R | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Hyd Cyl Hoist RIGHT |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N7474-L | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Hyd Cyl Hoist LEFT |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N8443-UL | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Rear Axle Control Arm U/LEFT |  | 67791 | 20000 | 2027-03-05 | 18.5 |  | 52985 | 2023-10-31
N8200-02 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Ride Strut POS 2 |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N6030-F | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Brake Slack Adj FRONT |  | 26206.72 | 30000 | 2027-03-05 | 13.5 |  | 0 | 2022-06-01
N8443-UR | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Rear Axle Control Arm U/RIGHT |  | 67791 | 20000 | 2027-03-05 | 18.5 |  | 52985 | 2023-10-31
N2000 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Transmission |  | 46895 | 15000 | 2027-03-05 | 13.5 |  | 35684 | 2023-05-20 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N4102-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Axle Shaft - POS 3 |  | 52712 | 20000 | 2027-03-06 | 13.75 |  | 36585 | 2022-11-15 |  | 6G-6408 | SHAFT-AXLE (LH)
N3037 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Drive Shaft Trans - Bevel Gear |  | 25353 | 14000 | 2027-03-06 | 12.5 |  | 14878 | 2023-04-06 |  | 419-1963
N2000 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Transmission |  | 25353 | 14000 | 2027-03-06 | 12.5 |  | 14878 | 2023-04-06
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Uni's T/C - Trans |  | 60509.94 | 10000 | 2027-03-06 | 12.5 |  | 54035.5 | 2024-10-01
N8995 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Operator Seat |  | 60509.94 | 10000 | 2027-03-06 | 12.5 |  | 54035.5 | 2024-10-01
N5000-03 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Final Drive POS 3 |  | 52712 | 20000 | 2027-03-06 | 13.75 |  | 36586 | 2022-11-21
N2004 | WA | CAT | 01 | Iron Bridge | GR0008 | Cat 16M | Transmission Pump |  | 25353 | 14000 | 2027-03-06 | 12.5 |  | 14878 | 2023-04-06
N9050-LW | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Starter Motor LOWER |  | 82501 | 10000 | 2027-03-07 | 18.5 |  | 77739 | 2025-07-13 |  | 10R-9816 | STARTING MOTOR GP-ELECTRIC
N1420 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Air Compressor |  | 82501 | 10000 | 2027-03-07 | 18.5 |  | 77738 | 2025-07-12 |  | 0R-9626 | AIR COMPRESSOR
N1420 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Air Compressor |  | 82501 | 10000 | 2027-03-07 | 18.5 |  | 77738 | 2025-07-12 |  | 0R-9626 | AIR COMPRESSOR
N9050-UP | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Starter Motor UPPER |  | 82501 | 10000 | 2027-03-07 | 18.5 |  | 77739 | 2025-07-13 |  | 10R-9816 | STARTING MOTOR GP-ELECTRIC
N9701 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | LiDAR Detection System |  | 21277 | 5000 | 2027-03-07 | 14 |  | 20244 | 2026-03-17
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Operator Seat |  | 47835.6 | 6000 | 2027-03-08 | 13 |  | 45525 | 2024-08-07 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9501 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | A/C Compressor |  | 14603 | 6000 | 2027-03-08 | 16 |  | 13139 | 2026-02-22 |  | 218-0324 | A/C COMPRESSOR
N9050 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Starter Motor |  | 34679 | 9000 | 2027-03-08 | 14 |  | 29657 | 2025-07-15
N1430 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Air Starter |  | 70621 | 12000 | 2027-03-08 | 15 |  | 62875 | 2024-09-05
N7230 | WA | CAT | 01 | Sanjiv Ridge | GR6524 | Cat 16M | Hyd Motor Circle Drive |  | 17448.6 | 12000 | 2027-03-08 | 7 |  | 7434.31 | 2022-11-25
N4000 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Bevel Gear |  | 64591.2 | 20000 | 2027-03-09 | 13.75 |  | 48504 | 2021-05-25
N4000 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Bevel Gear |  | 64591.2 | 20000 | 2027-03-09 | 13.75 |  | 48504 | 2021-05-25
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD3831 | Cat 789C | Uni's T/C - Trans |  | 59952 | 10000 | 2027-03-09 | 14 |  | 53942 | 2023-09-23 |  | 363-1923 | MAIN DRIVESHAFT UNI
N1002 | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Engine Valve Adj |  | 5903.7 | 4000 | 2027-03-09 | 7.2 | 12/08/2026 | 3957 | 2025-12-19
N0145-L | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Pivot Shaft Brgs LEFT |  | 32622 | 4000 | 2027-03-10 | 13.79 | 25/05/2026 | 32567 | 2026-05-25
N3038 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Uni's Trans - Bevel Gear |  | 26541 | 7000 | 2027-03-10 | 12.5 |  | 23110 | 2025-10-20
N0145-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Pivot Shaft Brgs RIGHT |  | 32622 | 4000 | 2027-03-10 | 13.79 | 25/05/2026 | 32567 | 2026-05-25
N3340 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Rotary Head |  | 32622 | 4000 | 2027-03-10 | 13.79 | 25/05/2026 | 32567 | 2026-05-25
N7041 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Pump Cooling Fan Engine |  | 55934 | 15000 | 2027-03-11 | 13.5 |  | 44804 | 2023-07-28 |  | 10R-5603 | PUMP GP
N6200-01 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Press Convertor POS 1 |  | 79726 | 12000 | 2027-03-12 | 18.5 |  | 73063 | 2025-04-13 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N2002 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Oil Cooler - Transmission |  | 53351 | 20000 | 2027-03-12 | 12 |  | 36811 | 2019-12-06 |  | 0R-3344 | COOLER, OIL, CORE, REMAN
N6200-02 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Press Convertor POS 2 |  | 79726 | 12000 | 2027-03-12 | 18.5 |  | 73063 | 2025-04-13 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N7004-09 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Hose Bucket Cylinder |  | 55435 | 10000 | 2027-03-12 | 18.5 |  | 50766 | 2025-08-19
N7004-08 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Hose Stick Cylinder |  | 55435 | 10000 | 2027-03-12 | 18.5 |  | 50766 | 2025-08-19
N8200-04 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Ride Strut POS 4 |  | 65569 | 25000 | 2027-03-12 | 18.5 |  | 45902 | 2021-04-22
N8200-03 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Ride Strut POS 3 |  | 65569 | 25000 | 2027-03-12 | 18.5 |  | 45902 | 2021-04-22
N7004-21 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Hose Clam Cylinder |  | 55435 | 10000 | 2027-03-12 | 18.5 |  | 50766 | 2025-08-19
N6030-F | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Brake Slack Adj FRONT |  | 53351 | 20000 | 2027-03-12 | 12 |  | 36811 | 2019-12-05 |  | 566-9762 | SLACK ADJUSTER
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Operator Seat |  | 57576 | 6000 | 2027-03-13 | 14 |  | 55626 | 2024-04-26 |  | 384-6168 | SEAT GP
N8995 | WA | CAT | 01 |  | RD4246 | Cat 789C | Operator Seat |  | 54387 | 6000 | 2027-03-13 | 20 |  | 54175 | 2024-01-08 |  | 384-6168 | SEAT GP
N0556 | WA | CAT | 73 | Iron Bridge | DR2121 | Cat MD6310 - ADS | Air Safety Valve |  | 1658 | 0 | 2027-03-13 | 14 |  | 138 | 2026-03-13 |  | 549-2163 | VALVE-RELIEF 160psi
N7514-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Ripper Pitch RIGHT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N7514-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Ripper Pitch LEFT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N7421-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Blade Tilt RIGHT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N7421-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Blade Tilt LEFT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N7510-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Ripper Lift LEFT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N7510-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Ripper Lift RIGHT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N3029 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Uni's T/C - Trans |  | 82501 | 10000 | 2027-03-15 | 18.5 |  | 77876 | 2025-07-22 |  | 598-2864 | SPIDER & BEARING AS
N7420-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Blade Lift LEFT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N7420-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Hyd Cyl Blade Lift RIGHT |  | 5903.7 | 8000 | 2027-03-15 | 7.2 |  | 0 | 2025-01-08
N3029 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Uni's T/C - Trans |  | 82501 | 10000 | 2027-03-15 | 18.5 |  | 77876 | 2025-07-22 |  | 598-2864 | SPIDER & BEARING AS
N7542-L | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Hyd Cyl Steer LEFT |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 20R-5304 | STEER CYL
N2052 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Convertor/Trans Pump |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 0R-1035 | PUMP GP GEAR
N9701 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | LiDAR Detection System |  | 12951 | 5000 | 2027-03-16 | 14 |  | 12046 | 2026-03-29
N3028 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Drive Shaft T/C - Trans |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 11R-1790 | SLIP JOINT GP
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Air Cond'r-Serv |  | 39658.4 | 5000 | 2027-03-16 | 15 |  | 39044 | 2023-12-20
N2435 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 12951 | 5000 | 2027-03-16 | 14 |  | 12046 | 2026-03-28 |  | 553-9494 | ELEMENT
N6062-F | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Oil Cooler Rear Brakes FRONT |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 10R-5675 | CORE AS OIL
N3016 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Drv Shaft Fan Pump-Trans Pump |  | 34679 | 14000 | 2027-03-16 | 14 |  | 24761 | 2024-03-18
N6062-RE | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Oil Cooler Rear Brakes REAR |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 10R-5675 | CORE AS OIL
N7613 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Hyd Cooler Steering/Eng Fan |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 30R-0034 | CORE AS OIL
N7542-R | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Hyd Cyl Steer RIGHT |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 20R-5304 | STEER CYL
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Air Cond'r-Serv |  | 39658.4 | 5000 | 2027-03-16 | 15 |  | 39044 | 2023-12-20
N6061 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Oil Cooler Front Brakes |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 10R-5673 | CORE AS OIL
N2050 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Torque Convertor |  | 76600 | 20000 | 2027-03-16 | 14 |  | 60684 | 2023-03-08 |  | 10R-5398 | TORQUE CONVERTER, 793D
N8995 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Operator Seat |  | 5943 | 10000 | 2027-03-18 | 13.79 |  | 0 | 2025-04-19
N5000-04 | WA | CAT | 01 | Miralga Creek | RD6507 | Cat 777C | Final Drive POS 4 |  | 47029 | 15000 | 2027-03-18 | 4.12 |  | 33241 | 2008-09-09
N7605 | NT | CAT | 01 | FleetCo | RD1211 | Cat 777D | Steering Hmu |  | 60487 | 20000 | 2027-03-18 | 7 | 12/05/2026 | 42545 | 2011-07-26
N6022 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Park Brake Pads |  | 28724 | 16000 | 2027-03-18 | 15 |  | 17139 | 2024-02-20
N6060-BC | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Oil Cooler - Brake Cooling |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N3044 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drv Shaft C/Bearing-Bevel Gr |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N2050 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Torque Convertor |  | 59122 | 24000 | 2027-03-19 | 18.5 |  | 40588 | 2021-05-13
N2090 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drv Coupling |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N3037-RE | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drive Shft Trans - Bev Gear RE |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N2002 | WA | CAT | 01 |  | RD4246 | Cat 789C | Oil Cooler - Transmission |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24 |  | 0R-3344 | COOLER TRANSMISSION
N2050 | WA | CAT | 01 |  | RD4246 | Cat 789C | Torque Convertor |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24 |  | 20R-0924 | TORQUE CONVERTOR
N2002-RE | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Oil Cooler -Transmission REAR |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N1430 | WA | CAT | 01 |  | RD4246 | Cat 789C | Air Starter |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24
N2004 | WA | CAT | 01 |  | RD4246 | Cat 789C | Transmission Pump |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24
N7610 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Cooler Core |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N1000 | WA | CAT | 01 |  | RD4246 | Cat 789C | Engine |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24 |  | 175-5289 | FLEXI ENGINE
N1000 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Engine |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N3028 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drive Shaft T/C - Trans |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N3045-RE | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drv Shft S/Bearing-Pump Drv RE |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N7234 | WA | EPI | 660 | Sanjiv Ridge | DR6566 | Epiroc SmartRoc T45 10LF | Hyd Motor Cooler Fan |  | 18651 | 12000 | 2027-03-19 | 13 |  | 10481.8 | 2024-01-29
N6060-BS | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Oil Cooler - Brakes & Steering |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N2000 | WA | CAT | 01 |  | RD4246 | Cat 789C | Transmission |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24
N9500-MA | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Air Cond'r-Serv - MAJOR |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N9500-MA | WA | CAT | 01 |  | RD4246 | Cat 789C | Air Cond'r-Serv - MAJOR |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24 |  | 137-2134 | AIR CON GP
N2002-F | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Oil Cooler -Transmission FRONT |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N8995 | WA | CAT | 01 |  | RD4247 | Cat 789C | Operator Seat |  | 59268 | 6000 | 2027-03-19 | 20 |  | 59163 | 2024-05-23 |  | 384-6168 | SEAT GP
N0520 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pre Lube Pump |  | 44396 | 24000 | 2027-03-19 | 15 |  | 24824 | 2022-09-19
N3028 | WA | CAT | 01 |  | RD4246 | Cat 789C | Drive Shaft T/C - Trans |  | 54387 | 20000 | 2027-03-19 | 20 |  | 40291 | 2021-02-24 |  | 10R-5185 | DRIVESHAFT TC-TRANS
N0145 | WA | EPI | 01 | Miralga Creek | DR6545 | Epiroc SmartRoc T45 10LF | Pivot Shaft Brgs |  | 16244 | 4000 | 2027-03-20 | 9.59 |  | 15080 | 2026-02-21
N4102-03 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Axle Shaft - POS 3 |  | 82501 | 20000 | 2027-03-21 | 18.5 |  | 67998 | 2024-01-21 |  | 223-1078 | SHAFT (LH)
N7570-RF | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT FRO |  | 5839 | 10000 | 2027-03-21 | 14 |  | 0 | 2024-11-09 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N7570-LF | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT FRO |  | 5839 | 10000 | 2027-03-21 | 14 |  | 0 | 2024-11-09 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N3029 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Uni's T/C - Trans |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-01 |  | 173-0888 | UNIVERSAL JOINT GP
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4248 | Cat 789C | Operator Seat |  | 57617 | 6000 | 2027-03-21 | 20 |  | 57560 | 2024-06-01 |  | 384-6168 | SEAT GP
N9020 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Alternator |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02 |  | 10R-9789 | ALTERNATOR
N9050 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Starter Motor |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02 |  | 10R-9816 | MOTOR GP-ELEC
N9703 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Inertial Measurement Unit |  | 5839 | 10000 | 2027-03-21 | 14 |  | 0 | 2024-11-09
N1300 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Cooling Sys Service |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02 |  | 248-5513 | REGULATOR-TEMPERATURE
N1004 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Engine Midlife |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02
N0091 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Grease Pump |  | 21508 | 8000 | 2027-03-21 | 12 |  | 17070 | 2025-06-14
N9760 | WA | CAT | 73 | Iron Bridge | DR2120 | Cat MD6310 - ADS | Fisheye Camera |  | 5839 | 10000 | 2027-03-21 | 14 |  | 0 | 2024-11-09
N2450 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Drv Cpling Fan Pump-Trans Pump |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-03-31 |  | 211-9087 | COUPLING AS
N1100-L | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Turbo Primary LEFT |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02 |  | 10R-2075 | TURBO, D10T, REMAN
N1100-R | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Turbo Primary RIGHT |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02 |  | 10R-2075 | TURBO, D10T, REMAN
N1202 | WA | CAT | 01 | Plant Idle - Mining West | TC8137 | Cat D10T | Fuel Transfer Pump |  | 46895 | 7500 | 2027-03-21 | 13.5 |  | 43401 | 2025-04-02 |  | 20R-0967 | PUMP GP
N4102-04 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Axle Shaft - POS 4 |  | 82501 | 20000 | 2027-03-21 | 18.5 |  | 67998 | 2024-01-21 |  | 223-1079 | SHAFT (RH)
N4102-04 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Axle Shaft - POS 4 |  | 82501 | 20000 | 2027-03-21 | 18.5 |  | 67998 | 2024-01-21 |  | 223-1079 | SHAFT (RH)
N4102-03 | WA | CAT | 01 | Iron Bridge | RD2030 | Cat 793D | Axle Shaft - POS 3 |  | 82501 | 20000 | 2027-03-21 | 18.5 |  | 67998 | 2024-01-21 |  | 223-1078 | SHAFT (LH)
N3028 | WA | CAT | 19 | Iron Bridge | RD4910 | Cat 793F | Drive Shaft T/C - Trans |  | 62083 | 16000 | 2027-03-22 | 18.5 |  | 51600 | 2024-11-18
N4102-03 | WA | CAT | 85 |  | LO2121 | Cat 992K | Axle Shaft - POS 3 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N8442-05 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Steering Ball Studs POS 5 |  | 69633 | 12000 | 2027-03-22 | 18.5 |  | 63150 | 2025-07-09
N3028 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Drive Shaft T/C - Trans |  | 65569 | 16000 | 2027-03-22 | 18.5 |  | 55077 | 2024-11-11
N1250 | WA | CAT | 85 |  | LO2121 | Cat 992K | Fuel Cooler |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N1000 | WA | CAT | 85 |  | LO2121 | Cat 992K | Engine |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N4000-F | WA | CAT | 85 |  | LO2121 | Cat 992K | Bevel Gear FRONT |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N1312-R | WA | CAT | 85 |  | LO2121 | Cat 992K | Aftercooler Core - RIGHT |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N7542-R | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Hyd Cyl Steer RIGHT |  | 69633 | 12000 | 2027-03-22 | 18.5 |  | 63150 | 2025-07-09
N6063 | WA | CAT | 85 |  | LO2121 | Cat 992K | Oil Cooler - Steering |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N4102-01 | WA | CAT | 85 |  | LO2121 | Cat 992K | Axle Shaft - POS 1 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N3044 | WA | CAT | 85 |  | LO2121 | Cat 992K | Drv Shaft C/Bearing-Bevel Gr |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N5000-03 | WA | CAT | 85 |  | LO2121 | Cat 992K | Final Drive POS 3 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N4102-02 | WA | CAT | 85 |  | LO2121 | Cat 992K | Axle Shaft - POS 2 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N3043 | WA | CAT | 85 |  | LO2121 | Cat 992K | Drv Shaft Trans-Ctr Bearing |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N4102-04 | WA | CAT | 85 |  | LO2121 | Cat 992K | Axle Shaft - POS 4 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N8430-RE | WA | CAT | 85 |  | LO2121 | Cat 992K | Trunnion Axle REAR |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N5000-02 | WA | CAT | 85 |  | LO2121 | Cat 992K | Final Drive POS 2 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N7655 | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Accumulator Pilot |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N3028 | WA | CAT | 85 |  | LO2121 | Cat 992K | Drive Shaft T/C - Trans |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N5000-04 | WA | CAT | 85 |  | LO2121 | Cat 992K | Final Drive POS 4 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N1312-L | WA | CAT | 85 |  | LO2121 | Cat 992K | Aftercooler Core - LEFT |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N5000-01 | WA | CAT | 85 |  | LO2121 | Cat 992K | Final Drive POS 1 |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N7020 | WA | CAT | 85 |  | LO2121 | Cat 992K | Pump Brake |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N4000-RE | WA | CAT | 85 |  | LO2121 | Cat 992K | Bevel Gear REAR |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N3037-RE | WA | CAT | 85 |  | LO2121 | Cat 992K | Drive Shft Trans - Bev Gear RE |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N2000 | WA | CAT | 85 |  | LO2121 | Cat 992K | Transmission |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-15 | THIESS MANAGED
N7651-L | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Accum Ride Control LEFT |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N1310 | WA | CAT | 85 |  | LO2121 | Cat 992K | Radiator |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N2090 | WA | EPI | 01 | Sanjiv Ridge | DR6549 | Epiroc SmartRoc T45 10LF | Drv Coupling |  | 18065 | 6000 | 2027-03-22 | 13 |  | 15939 | 2025-10-14
N7610 | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Cooler Core |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N8442-06 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Steering Ball Studs POS 6 |  | 69633 | 12000 | 2027-03-22 | 18.5 |  | 63150 | 2025-07-09
N7651-R | WA | CAT | 85 |  | LO2121 | Cat 992K | Hyd Accum Ride Control RIGHT |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N5015 | WA | CAT | 85 |  | LO2121 | Cat 992K | Oil Cooler AXLE |  | 33290 | 18000 | 2027-03-22 | 11 |  | 18565 | 2022-04-14 | THIESS MANAGED
N7361 | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Hyd Motor Water Pump |  | 54979 | 10000 | 2027-03-23 | 14 |  | 49159 | 2025-08-03
N9020 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Alternator |  | 79044 | 9000 | 2027-03-23 | 14 |  | 74234 | 2025-06-15 |  | 10R-9789 | ALTERNATOR GP -B
N9500 | WA | CAT | 95 |  | RD4977 | Cat 789C | Air Cond'r-Serv |  | 818 | 5000 | 2027-03-23 | 14 |  | 0
N0556 | WA | EPI | 85 | Iron Bridge | DR3120 | Epiroc D65 XLF MKII | Air Safety Valve |  | 22613 | 0 | 2027-03-23 | 12 |  | 22613 | 2026-03-23
N0122-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Carrier Roller No 2 LEFT |  | 23402 | 12000 | 2027-03-23 | 18.5 |  | 16932 | 2025-06-15
N7594 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Dust Hood |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N3029 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Uni's T/C - Trans |  | 69633 | 8000 | 2027-03-24 | 18.5 |  | 67185 | 2026-01-21
N7460-02 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Feed Dump LEFT |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7460-03 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Feed Dump RIGHT |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7480-L | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation LEFT |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7480-R | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation RIGH |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7570-RE | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Levelling Jack REAR |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7597 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Boom Swing |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7600 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Control Valve |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7610 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cooler Core |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7627 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Valve Track Oscillation |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4222 | Cat 785C | Air Cond'r-Serv |  | 41444 | 5000 | 2027-03-24 | 14.5 |  | 40801 | 2025-04-28
N9500-MA | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Air Cond'r-Serv - MAJOR |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N2090 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Drv Coupling |  | 16307 | 5000 | 2027-03-24 | 14 |  | 15514 | 2026-03-24 |  | 520-7010 | COUPLING GP-
N2435 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 16307 | 5000 | 2027-03-24 | 14 |  | 15514 | 2026-03-27 |  | 553-9494 | ELEMENT
N7426 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Cyl Boom Lift |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N1312 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Aftercooler Core |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7044 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Cooler Fan Hyd |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7039 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Pump Cooler Fan Hyd/Eng |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7008-03 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Pump Hydraulic POS 3 |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N0551 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Cooler Aircompressor |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7008-02 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Pump Hydraulic POS 2 |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7008-01 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Pump Hydraulic POS 1 |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N3320 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Pump Drive Box |  | 79726 | 20000 | 2027-03-24 | 18.5 |  | 65281 | 2023-09-15 |  | 11R-1519 | PUMP DRIVE, 793D, 793F
N1320 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Cooling Fan Engine |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N1310 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Radiator |  | 8398 | 12000 | 2027-03-24 | 12 |  | 0
N7021 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Pump Brake Cooling |  | 59122 | 22000 | 2027-03-25 | 18.5 |  | 42686 | 2021-09-13
N5020-RF | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Wheel Bearing RIGHT FRONT |  | 26206.72 | 15000 | 2027-03-25 | 13.5 |  | 15272.32 | 2024-02-23
N8995 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Operator Seat |  | 61931 | 6000 | 2027-03-25 | 18.5 |  | 61503 | 2026-04-30
N2435 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Drv Coupling Engine/Pump Drive |  | 786 | 5000 | 2027-03-25 | 14 |  | 0 | 2024-11-12 |  | 553-9494 | ELEMENT
N5020-LF | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Wheel Bearing LEFT FRONT |  | 26206.72 | 15000 | 2027-03-25 | 13.5 |  | 15272.32 | 2024-02-23
N9501 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | A/C Compressor |  | 49898.9 | 8000 | 2027-03-25 | 10 |  | 44909 | 2024-12-15
N9701 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | LiDAR Detection System |  | 786 | 5000 | 2027-03-25 | 14 |  | 0 | 2024-11-12
N2090 | WA | CAT | 73 | Iron Bridge | DR2123 | Cat MD6310 - ADS | Drv Coupling |  | 786 | 5000 | 2027-03-25 | 14 |  | 0 | 2024-11-12 |  | 520-7010 | COUPLING GP-
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Press Converter LEFT REAR |  | 64653 | 10000 | 2027-03-26 | 14 |  | 58880 | 2022-07-04 |  | 8W-3405 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Press Converter FRONT |  | 64653 | 10000 | 2027-03-26 | 14 |  | 58880 | 2022-07-04 |  | 8W-3405 | CHAMBER, BRAKE
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Press Converter RIGHT REAR |  | 64653 | 10000 | 2027-03-26 | 14 |  | 58880 | 2022-07-04 |  | 8W-3405 | CHAMBER, BRAKE
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Uni's T/C - Trans |  | 64653 | 10000 | 2027-03-26 | 14 |  | 58880 | 2022-07-04 |  | 363-1923 | MAIN DRIVESHAFT UNI
N9500 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Air Cond'r-Serv |  | 45807 | 5000 | 2027-03-26 | 14 |  | 45031 | 2025-09-01
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Uni's Eng - Pump Drive |  | 64653 | 10000 | 2027-03-26 | 14 |  | 58880 | 2022-07-03 |  | 108-6587 | BEARING,SPIDER
N8443-LR | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Rear Axle Control Arm L/RIGHT |  | 59517 | 20000 | 2027-03-27 | 18.5 |  | 45129 | 2023-10-27
N8443-UL | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Rear Axle Control Arm U/LEFT |  | 59517 | 20000 | 2027-03-27 | 18.5 |  | 45129 | 2023-10-27
N8443-LL | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Rear Axle Control Arm L/LEFT |  | 59517 | 20000 | 2027-03-27 | 18.5 |  | 45129 | 2023-10-27
N7546-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cyl Stick RIGHT |  | 23756 | 15000 | 2027-03-27 | 18.5 |  | 14366 | 2024-11-24
N8443-UR | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | Rear Axle Control Arm U/RIGHT |  | 59517 | 20000 | 2027-03-27 | 18.5 |  | 45129 | 2023-10-27
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD4243 | Cat 789C | Rear Axle Dog Bone |  | 64230 | 15000 | 2027-03-27 | 14 |  | 53474 | 2022-07-15 |  | 211-4923 | LATERAL LINK, 789
N0556 | WA | CAT | 85 | Iron Bridge | DR2116 | Cat MD6310 - ADS | Air Safety Valve |  | 12951 | 0 | 2027-03-28 | 14 |  | 12015 | 2026-03-28 |  | 549-2163 | VALVE-RELIEF 160psi
N9500 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Air Cond'r-Serv |  | 76600 | 6000 | 2027-03-28 | 14 |  | 74854 | 2026-01-27 |  | 385-0244 | MOTOR AS-BLOWER
N9500 | WA | CAT | 95 |  | RD4978 | Cat 789C | Air Cond'r-Serv |  | 728 | 5000 | 2027-03-29 | 14 |  | 0
N1300 | WA | CAT | 01 |  | RD4246 | Cat 789C | Cooling Sys Service |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 418-4162 | REGULATOR TE
N1100-RR | WA | CAT | 01 |  | RD4246 | Cat 789C | Turbo Primary RHT REAR |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-13 |  | 20R-6651 | RE-MAN TURBO GP
N1403 | WA | CAT | 01 |  | RD4246 | Cat 789C | Jockey Pulley Brgs |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 4S-5367 | BUSHING AS
N1402 | WA | CAT | 01 |  | RD4246 | Cat 789C | Fan Pulley Brgs |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 105-2273 | FAN HUB PULLEY,789
N6200-RR | WA | CAT | 01 |  | RD4246 | Cat 789C | Press Converter RIGHT REAR |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 8W-3405 | CHAMBER, BRAKE
N1100-LR | WA | CAT | 01 |  | RD4246 | Cat 789C | Turbo Primary LFT REAR |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 20R-6651 | RE-MAN TURBO GP
N1202 | WA | CAT | 01 |  | RD4246 | Cat 789C | Fuel Transfer Pump |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-11 |  | 10R-9838 | PUMP GP-F XFR
N1100-LF | WA | CAT | 01 |  | RD4246 | Cat 789C | Turbo Primary LFT FRONT |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 20R-6651 | RE-MAN TURBO GP
N1100-RF | WA | CAT | 01 |  | RD4246 | Cat 789C | Turbo Primary RHT FRONT |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-13 |  | 20R-6651 | RE-MAN TURBO GP
N6200-LR | WA | CAT | 01 |  | RD4246 | Cat 789C | Press Converter LEFT REAR |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 8W-3405 | CHAMBER, BRAKE
N6200-F | WA | CAT | 01 |  | RD4246 | Cat 789C | Press Converter FRONT |  | 54387 | 10000 | 2027-03-29 | 20 |  | 50493 | 2022-07-10 |  | 8W-3405 | CHAMBER, BRAKE
N7004-12 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Swing Pump Swing Mtr |  | 23402 | 10000 | 2027-03-30 | 18.5 |  | 19070 | 2025-10-05
N7130-01 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Swing POS 1 |  | 23402 | 10000 | 2027-03-30 | 18.5 |  | 19070 | 2025-10-06
N7130-03 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Swing POS 3 |  | 23402 | 10000 | 2027-03-30 | 18.5 |  | 19070 | 2025-10-06
N7130-04 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Swing POS 4 |  | 23402 | 10000 | 2027-03-30 | 18.5 |  | 19070 | 2025-10-06
N7130-02 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Swing POS 2 |  | 23402 | 10000 | 2027-03-30 | 18.5 |  | 19070 | 2025-10-06
N7605 | WA | CAT | 01 | Sanjiv Ridge | RD6564 | Cat 785D | Steering Hmu |  | 63459.48 | 12000 | 2027-03-31 | 13.5 |  | 55606.16 | 2024-09-23
N3020 | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Drive Shaft Eng - Pump Drive |  | 79044 | 18000 | 2027-03-31 | 14 |  | 65337 | 2023-09-04 |  | 339-6380 | JOINT GP-UNI
N5000-03 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Final Drive POS 3 |  | 66379.67 | 20000 | 2027-03-31 | 12.5 |  | 50214 | 2021-05-08
N7421-R | WA | CAT | 01 | Miralga Creek | DZ6526 | Cat D9T | Hyd Cyl Blade Tilt RIGHT |  | 34410.8 | 14000 | 2027-04-01 | 6.35 |  | 22366 | 2021-11-02
N6030-F | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Brake Slack Adj FRONT |  | 67791 | 16000 | 2027-04-01 | 18.5 |  | 57496 | 2024-11-07
N8200-02 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Ride Strut POS 2 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N0140 | NT | CAT | 01 | FleetCo | DZ1936 | Cat D10T | Equalizer Bar |  | 45807 | 15000 | 2027-04-01 | 14 |  | 35126 | 2021-06-15 |  | 10R-9161 | BAR GP-EQUALIZER
N1002 | WA | CAT | 01 | Plant Idle - Mining West | RD4376 | Cat 785C | Engine Valve Adj |  | 66519 | 4000 | 2027-04-01 | 13 |  | 66528 | 2023-10-21
N8122-01 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Wheel Group POS 1 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N6000-02 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Brake POS 2 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N8200-01 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Ride Strut POS 1 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N5020-01 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Wheel Bearing POS 1 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N8122-02 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Wheel Group POS 2 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N9500 | WA | CAT | 85 | McPhee Creek | DZ6660 | Cat D10T2 | Air Cond'r-Serv |  | 5222.3 | 0 | 2027-04-01 | 7.2 |  | 5222.3 | 2026-04-01
N5020-02 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Wheel Bearing POS 2 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N8995 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Operator Seat |  | 65569 | 6000 | 2027-04-01 | 18.5 |  | 65275 | 2026-05-12
N6000-01 | WA | CAT | 19 | Iron Bridge | RD4913 | Cat 793F | Brake POS 1 |  | 59122 | 22000 | 2027-04-01 | 18.5 |  | 42819 | 2021-10-02
N0520 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Pre Lube Pump |  | 60646.3 | 20000 | 2027-04-01 | 13.75 |  | 44883 | 2022-12-12
N7602 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Relief Valve |  | 5650 | 0 | 2027-04-01 | 13.79 |  | 0 | 2025-04-01
N8995 | WA | CAT | 19 | McPhee Creek | DR1080 | Cat MD6250 | Operator Seat |  | 444 | 6000 | 2027-04-02 | 18 |  | 0
N6200-RR | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Press Converter RIGHT REAR |  | 69305 | 10000 | 2027-04-02 | 17 |  | 64555 | 2025-05-28 |  | 8X-7220 | CHAMBER, BRAKE
N8200-02 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | Ride Strut POS 2 |  | 64732.59 | 30000 | 2027-04-02 | 12.5 |  | 38594 | 2018-11-14
N6200-F | NT | CAT | 01 | FleetCo | RD1900 | Cat 785C XQ | Press Converter FRONT |  | 69305 | 10000 | 2027-04-02 | 17 |  | 64555 | 2025-05-28 |  | 8X-7220 | CHAMBER, BRAKE
N8995 | WA | CAT | 85 |  | GR1549 | Cat 16M | Operator Seat |  | 23153 | 6000 | 2027-04-02 | 10 |  | 20239 | 2024-09-05 | THIESS MANAGED
N1300 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Cooling Sys Service |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-21 |  | 248-5513 | REGULATOR-WATER TEMPERATURE
N1301 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Water Pump |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 10R-6400 | CAT REMAN WATER PUMP
N1400 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Belt Tensioner Assembly |  | 76600 | 9000 | 2027-04-03 | 14 |  | 71935 | 2025-06-06 |  | 336-4953 | TENSIONER,BELT
N9500 | WA | CAT | 95 |  | RD4974 | Cat 789C | Air Cond'r-Serv |  | 655 | 5000 | 2027-04-03 | 14 |  | 0
N1202 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Fuel Transfer Pump |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 20R-0967 | PUMP GP FUEL
N0622-LU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Sheave UPPER LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-23 |  | 450-8053 | SHEAVE AS
N0622-RL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Sheave LOWER RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-23 |  | 450-8053 | SHEAVE AS
N9501 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | A/C Compressor |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-21 |  | 629-8454 | COMPRESSOR GP-REFRIGERANT
N9050-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Starter Motor RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-20 |  | 349-6554 | STARTER MOTOR
N9050-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Starter Motor LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-27 |  | 349-6554 | STARTER MOTOR
N9501 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | A/C Compressor |  | 76600 | 9000 | 2027-04-03 | 14 |  | 71935 | 2025-06-06 |  | 217-4448 | COMPRESSOR GP-REFRIGERANT
N7310-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Rotation RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-23 |  | 11R-0142 | MOTOR GP-PISTON
N7310-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Hyd Motor Rotation LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-22 |  | 11R-0141 | MOTOR GP-PISTON
N1210 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Fuel Injectors |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 11R-0276 | INJECTOR GP-FUEL
N1100-R | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Turbo Primary RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-20 |  | 20R-3695 | TURBO CHARGER GP (RH)
N1100-L | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Turbo Primary LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-20 |  | 20R-3688 | TURBO CHARGER GP (LH)
N0622-LL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Sheave LOWER LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-23 |  | 450-8053 | SHEAVE AS
N0623-TR | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Sheave TRAVEL RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 450-6156 | SHEAVE
N0622-TR | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 450-6156 | SHEAVE
N0622-RU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Sheave UPPER RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-23 |  | 450-8053 | SHEAVE AS
N0622-TL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pulldown Sheave TRAVEL LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 450-6156 | SHEAVE
N0623-TL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Sheave TRAVEL LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 450-6156 | SHEAVE
N0623-LL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Sheave LOWER LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 450-8053 | SHEAVE AS
N9020 | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Alternator |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-25 |  | 11R-1235 | ALTERNATOR GP
N0623-RL | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Sheave LOWER RIGHT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8496 | 2025-10-24 |  | 450-8053 | SHEAVE AS
N0623-LU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Sheave UPPER LEFT |  | 11349 | 7500 | 2027-04-03 | 15 |  | 8495 | 2025-10-22 |  | 450-8053 | SHEAVE AS
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4241 | Cat 789C | Air Cond'r-Serv |  | 58852 | 5000 | 2027-04-05 | 15 |  | 58529 | 2024-03-04
N7230 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Hyd Motor Circle Drive |  | 26541 | 8000 | 2027-04-06 | 12.5 |  | 22454 | 2025-09-09
N3300 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Circle Drive Box |  | 26541 | 8000 | 2027-04-06 | 12.5 |  | 22454 | 2025-09-09 |  | 454-4691 | CIRCLE DRIVE
N8995 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Operator Seat |  | 34291 | 10000 | 2027-04-07 | 13.79 |  | 28620 | 2025-03-03
N9500 | WA | CAT | 01 |  | DZ1658 | Cat 854K | Air Cond'r-Serv |  | 57859 | 5000 | 2027-04-07 | 16 |  | 57875 | 2025-10-17 |  | 466-7341 | FAN
N0695 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Centraliser Assembly |  | 17835 | 10000 | 2027-04-07 | 13 |  | 11922.26 | 2024-11-30
N7008-02 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Pump Hydraulic POS 2 |  | 34291 | 10000 | 2027-04-07 | 13.79 |  | 28620 | 2025-03-03
N9500 | WA | CAT | 95 |  | RD4979 | Cat 789C | Air Cond'r-Serv |  | 601 | 5000 | 2027-04-07 | 14 |  | 0
N7234 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Motor Cooler Fan |  | 34291 | 10000 | 2027-04-07 | 13.79 |  | 28620 | 2025-03-03
N1100-L | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Turbo Primary LEFT |  | 54833.54 | 20000 | 2027-04-07 | 12.5 |  | 38762 | 2017-09-13
N7008-01 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Pump Hydraulic POS 1 |  | 34291 | 10000 | 2027-04-07 | 13.79 |  | 28620 | 2025-03-03
N3321 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Pump Drive |  | 54833.54 | 20000 | 2027-04-07 | 12.5 |  | 38762 | 2017-09-13
N1310 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Radiator |  | 54833.54 | 20000 | 2027-04-07 | 12.5 |  | 38762 | 2017-09-13
N1100-R | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Turbo Primary RIGHT |  | 54833.54 | 20000 | 2027-04-07 | 12.5 |  | 38762 | 2017-09-13
N7232 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Hyd Motor Engine Fan |  | 34291 | 10000 | 2027-04-07 | 13.79 |  | 28620 | 2025-03-03
N2090 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Drv Coupling |  | 34291 | 10000 | 2027-04-07 | 13.79 |  | 28620 | 2025-03-03
N1000 | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Engine |  | 54833.54 | 20000 | 2027-04-07 | 12.5 |  | 38762 | 2017-09-13
N3028 | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Drive Shaft T/C - Trans |  | 2718 | 7500 | 2027-04-08 | 15.2 |  | 0 | 2025-02-01
N7310-R | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Hyd Motor Rotation RIGHT |  | 2718 | 7500 | 2027-04-08 | 15.2 |  | 0 | 2025-02-01
N3320 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Pump Drive Box |  | 21277 | 15000 | 2027-04-08 | 14 |  | 10681 | 2023-07-03 |  | 503-7615 | PUMP DRIVE,MD6310
N8995 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Operator Seat |  | 5650 | 10000 | 2027-04-08 | 13.79 |  | 0 | 2025-04-01
N7310-L | WA | EPI | 85 | McPhee Creek | DR6618 | Epiroc PV231 | Hyd Motor Rotation LEFT |  | 2718 | 7500 | 2027-04-08 | 15.2 |  | 0 | 2025-02-01
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Brake Slack Adj REAR |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 590-2533 | SLACK ADJUSTER
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Ride Strut POS 1 |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-19 |  | 347-7423 | SUSP CYL
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Hyd Cyl Hoist LEFT |  | 86119 | 30000 | 2027-04-09 | 18.5 |  | 61972 | 2022-07-17 |  | 295-5708 | CYLINDER GP
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Air Starter |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-17
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Pump Drive Box |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 11R-1517 | DRIVE GP-PUMP
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Brake Slack Adj FRONT |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 590-2531 | SLACK ADJUSTER
N7420-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Hyd Cyl Blade Lift RIGHT |  | 47986 | 12000 | 2027-04-09 | 12 |  | 39778 | 2023-10-28 |  | 20R-9809 | BLADE LIFT CYLINDER
N3320 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Pump Drive Box |  | 67791 | 18000 | 2027-04-09 | 18.5 |  | 55630 | 2025-04-23
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Ride Strut POS 4 |  | 86119 | 30000 | 2027-04-09 | 18.5 |  | 61972 | 2022-07-17 |  | 11R-1042 | REAR SUSP CYL 793D
N7064 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Pump Hoist |  | 66379.67 | 20000 | 2027-04-09 | 12.5 |  | 50325 | 2021-05-20
N0100-L | WA | CAT | 85 |  | DZ3431 | Cat D10T | Track Group LEFT |  | 32356 | 4000 | 2027-04-09 | 11 |  | 31828 | 2026-04-20 | THIESS MANAGED
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Engine |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-17 |  | 175-5289 | FLEXI ENGINE
N0100-R | WA | CAT | 85 |  | DZ3431 | Cat D10T | Track Group RIGHT |  | 32356 | 4000 | 2027-04-09 | 11 |  | 31828 | 2026-04-19 | THIESS MANAGED
N7035 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Pump Hoist, Brk Charge/Cooling |  | 67791 | 18000 | 2027-04-09 | 18.5 |  | 55630 | 2024-08-04
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 230-4112 | UNIVERSAL JOINT GP
N7420-L | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Hyd Cyl Blade Lift LEFT |  | 47986 | 12000 | 2027-04-09 | 12 |  | 39778 | 2023-10-28 |  | 20R-9809 | BLADE LIFT CYLINDER
N7123 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Pump Steering & Fan |  | 67791 | 18000 | 2027-04-09 | 18.5 |  | 55630 | 2024-08-04
N2000 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Transmission |  | 67791 | 18000 | 2027-04-09 | 18.5 |  | 55630 | 2024-08-02
N6061 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Oil Cooler Front Brakes |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 10R-0816 | REMAN OIL COOLER
N7038 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Pump Conv,P/Brk Rel, Brk Cool |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 30R-0359 | PUMP GP-GEAR
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Ride Strut POS 3 |  | 86119 | 30000 | 2027-04-09 | 18.5 |  | 61972 | 2022-07-17 |  | 11R-1042 | REAR SUSP CYL 793D
N4000 | WA | CAT | 19 | Iron Bridge | RD4919 | Cat 793F | Bevel Gear |  | 67791 | 18000 | 2027-04-09 | 18.5 |  | 55630 | 2024-08-03
N0520 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Pre Lube Pump |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 20R-3396 | PRE-LUBE PUMP
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4244 | Cat 789C | Radiator |  | 67187 | 20000 | 2027-04-09 | 14 |  | 51608 | 2021-01-20 |  | 145-1226 | PEX SX 789C RADIATOR
N8995 | WA | CAT | 19 | Iron Bridge | RD4822 | Cat 785C | Operator Seat |  | 32755 | 6000 | 2027-04-09 | 12.9 |  | 30826 | 2026-01-04 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4242 | Cat 789C | Air Cond'r-Serv |  | 56457 | 5000 | 2027-04-09 | 14 |  | 55883 | 2024-03-04
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6197 | Cat 785D | Uni's T/C - Trans |  | 56902.96 | 10000 | 2027-04-10 | 13.5 |  | 51181 | 2025-03-29
N0623-RU | WA | CAT | 85 | Iron Bridge | DR2119 | Cat MD6310 - ADS | Pullback Sheave UPPER RIGHT |  | 11349 | 7500 | 2027-04-10 | 15 |  | 8608 | 2025-11-15 |  | 450-8053 | SHEAVE AS
N9500 | WA | CAT | 95 |  | RD4972 | Cat 789C | Air Cond'r-Serv |  | 566 | 5000 | 2027-04-10 | 14 |  | 0
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Steering Ball Studs POS 8 |  | 69633 | 12000 | 2027-04-11 | 18.5 |  | 63510 | 2025-07-09
N7542-L | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Hyd Cyl Steer LEFT |  | 69633 | 12000 | 2027-04-11 | 18.5 |  | 63510 | 2025-07-09
N2090 | WA | EPI | 660 | Sanjiv Ridge | DR6567 | Epiroc SmartRoc T45 10LF | Drv Coupling |  | 17835 | 6000 | 2027-04-11 | 13 |  | 15974 | 2025-12-10
N8442-07 | WA | CAT | 19 | Iron Bridge | RD4911 | Cat 793F | Steering Ball Studs POS 7 |  | 69633 | 12000 | 2027-04-11 | 18.5 |  | 63510 | 2025-07-09
N0200 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | A Frame Bearing |  | 70515 | 20000 | 2027-04-11 | 19 |  | 56552 | 2022-11-16 |  | 106-9343 | BEARING
N9500 | WA | CAT | 95 |  | RD4981 | Cat 789C | Air Cond'r-Serv |  | 539 | 5000 | 2027-04-12 | 14 |  | 0
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 22440 | 6000 | 2027-04-12 | 12 |  | 20267 | 2025-11-16
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Air Cond'r-Serv |  | 54402.5 | 5000 | 2027-04-12 | 13.75 |  | 53784 | 2025-06-05 |  | 385-0244 | MOTOR,BLOWER
N8995 | WA | CAT | 01 | Miralga Creek | GR6528 | Cat 16M | Operator Seat |  | 33341.1 | 10000 | 2027-04-13 | 5.95 |  | 25244 | 2021-09-01
N0200 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | A Frame Bearing |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-10-13 |  | 6V-0444 | BEARING
N4102-03 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Axle Shaft - POS 3 |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-10-13 |  | 8W-8741 | AXLE (LH)
N8995 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Operator Seat |  | 44396 | 6000 | 2027-04-14 | 15 |  | 43208 | 2026-03-12
N5000-04 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Final Drive POS 4 |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-10-09 |  | 0R-9043 | FINAL DRIVE 789C
N7542-R | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Hyd Cyl Steer RIGHT |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-08-18 |  | 30R-1082 | STEER CYL 789C
N3029 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Uni's T/C - Trans |  | 69200 | 8000 | 2027-04-14 | 18.5 |  | 67144 | 2026-02-02
N5000-03 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Final Drive POS 3 |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-10-09 |  | 0R-9043 | FINAL DRIVE 789C
N4000 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Bevel Gear |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-10-23 |  | 11R-1751 | BEVEL GEAR 789C
N4102-04 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Axle Shaft - POS 4 |  | 71548 | 20000 | 2027-04-14 | 15 |  | 56358 | 2020-10-13 |  | 8W-8739 | AXLE (RH)
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 20661 | 6000 | 2027-04-15 | 12 |  | 18526 | 2025-11-07
N6350 | SA | CAT | 01 | Prominent Hill | RD2620 | Cat 793D | Brake Relay Valves |  | 78363 | 12000 | 2027-04-15 | 14 |  | 70874 | 2024-12-16 |  | 159-5149 | BRAKE RELAY VALVE
N0596 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 20661 | 6000 | 2027-04-15 | 12 |  | 18526 | 2025-11-16
N0558 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Air End Coupling |  | 20661 | 6000 | 2027-04-15 | 12 |  | 18526 | 2025-11-08
N7151 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 20661 | 6000 | 2027-04-15 | 12 |  | 18526 | 2025-11-22
N3021 | WA | CAT | 01 | Disposals | RD4236 | Cat 789C | Uni's Eng - Pump Drive |  | 60138 | 10000 | 2027-04-15 | 15 |  | 54962 | 2021-08-15 |  | 108-6587 | BEARING,SPIDER
N0597 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 20661 | 6000 | 2027-04-15 | 12 |  | 18526 | 2025-11-09
N3029 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Uni's T/C - Trans |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47690 | 2025-10-17 |  | 173-0888 | UNIVERSAL JOINT GP
N9500 | WA | CAT | 19 | Iron Bridge | DZ3453 | Cat D10T | Air Cond'r-Serv |  | 24820 | 5000 | 2027-04-16 | 14 |  | 24338 | 2026-02-12
N2000 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Transmission |  | 44396 | 12000 | 2027-04-16 | 15 |  | 37240 | 2025-02-12
N0105-RR | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Idler RHT REAR |  | 52003.6 | 6000 | 2027-04-16 | 12 |  | 49885 | 2025-08-17
N1004 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Engine Midlife |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20
N0105-LR | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Idler LFT REAR |  | 52003.6 | 6000 | 2027-04-16 | 12 |  | 49885 | 2025-08-17
N7073-05 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Imp 3&4 |  | 23402 | 15000 | 2027-04-16 | 18.5 |  | 14377 | 2025-01-06
N9501 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | A/C Compressor |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 106-5122 | COMPRESSOR
N1100-L | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Turbo Primary LEFT |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 10R-2075 | TURBO, D10T, REMAN
N3032 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Uni's Ctr Bearing - Bevel Gear |  | 44396 | 12000 | 2027-04-16 | 15 |  | 37240 | 2025-02-12
N3320-01 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Drive Box POS 1/FR |  | 44396 | 12000 | 2027-04-16 | 15 |  | 37240 | 2025-02-12
N2450 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Drv Cpling Fan Pump-Trans Pump |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47690 | 2025-10-17 |  | 211-9087 | COUPLING AS
N9050 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Starter Motor |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 10R-9816 | MOTOR GP-ELEC
N1300 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Cooling Sys Service |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 248-5513 | REGULATOR-TEMPERATURE
N9020 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Alternator |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 10R-9789 | ALTERNATOR
N8995 | NT | CAT | 01 | Idle Plant / Off Hired | RD6037 | Cat 785C | Operator Seat |  | 39272 | 6000 | 2027-04-16 | 15 |  | 38113 | 2022-10-31 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N3042 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Driveline Ctr Bearing |  | 44396 | 12000 | 2027-04-16 | 15 |  | 37240 | 2025-02-12
N1202 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Fuel Transfer Pump |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 20R-0967 | PUMP GP
N1100-R | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Turbo Primary RIGHT |  | 50673 | 7500 | 2027-04-16 | 14 |  | 47698 | 2025-10-20 |  | 10R-2075 | TURBO, D10T, REMAN
N8200-02 | WA | CAT | 01 | Sanjiv Ridge | RD6532 | Cat 785C | Ride Strut POS 2 |  | 60509.94 | 30000 | 2027-04-16 | 12.5 |  | 34553 | 2018-06-21
N6200-LR | WA | CAT | 01 | Iron Bridge | RD4378 | Cat 785C | Press Converter LEFT REAR |  | 54979 | 10000 | 2027-04-17 | 14 |  | 49521 | 2025-08-24 |  | 8X-7220 | CHAMBER, BRAKE
N0105-LF | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Idler LFT FRONT |  | 52003.6 | 6000 | 2027-04-17 | 12 |  | 49886.13 | 2025-08-26
N9500 | WA | CAT | 95 |  | RD4980 | Cat 789C | Air Cond'r-Serv |  | 461 | 5000 | 2027-04-17 | 14 |  | 0
N8995 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Operator Seat |  | 66446.13 | 10000 | 2027-04-17 | 12.5 |  | 60496.5 | 2024-04-29
N0302 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Feed Sprocket |  | 5943 | 6000 | 2027-04-17 | 13.79 |  | 4416 | 2026-02-12
N4110-R | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Steering Clutch/Brk RIGHT |  | 47986 | 15000 | 2027-04-17 | 12 |  | 39148 | 2023-03-06 |  | 10R-9976 | Steering Brake And Clutch
N1300 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Cooling Sys Service |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-17
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD4220 | Cat 785C | Air Cond'r-Serv |  | 52712 | 5000 | 2027-04-18 | 13.75 |  | 52186 | 2026-01-02
N3029 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Uni's T/C - Trans |  | 66446.13 | 10000 | 2027-04-18 | 12.5 |  | 60512 | 2024-10-18
N9050-L | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Starter Motor LEFT |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-16
N1100-L | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Turbo Primary LEFT |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-14
N1100-R | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Turbo Primary RIGHT |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-18
N1004 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Engine Midlife |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-14
N0556 | WA | EPI | 85 | Iron Bridge | DR3122 | Epiroc D65 XLF MKII | Air Safety Valve |  | 20661 | 0 | 2027-04-18 | 12 | 10/07/2026 | 20079 | 2026-04-18
N1202 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Fuel Transfer Pump |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-16
N1312 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Aftercooler Core |  | 21508 | 12000 | 2027-04-18 | 12 |  | 13404 | 2024-02-27
N7090-04 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Pilot/Servo POS 4 |  | 23402 | 15000 | 2027-04-18 | 18.5 |  | 14412 | 2025-01-10
N9020 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Alternator |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-13
N1310 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Radiator |  | 21508 | 12000 | 2027-04-18 | 12 |  | 13404 | 2024-02-27
N1301 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Water Pump |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-17
N3029 | WA | CAT | 01 | Iron Bridge | RD4201 | Cat 777F | Uni's T/C - Trans |  | 42291 | 10000 | 2027-04-18 | 10 |  | 35540 | 2024-03-17 |  | 172-5235 | SPIDER
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Operator Seat |  | 60646.3 | 6000 | 2027-04-18 | 13.75 |  | 59117 | 2025-11-07
N9703 | WA | CAT | 85 | Iron Bridge | DR2118 | Cat MD6310 - ADS | Inertial Measurement Unit |  | 16307 | 10000 | 2027-04-19 | 14 |  | 10874 | 2025-06-15
N2445 | WA | EPI | 19 |  | DR1079 | Epiroc D65 | Drv Coupling Compressor |  | 9782 | 15000 | 2027-04-19 | 16 |  | 0 | 2025-06-20
N7602 | WA | EPI | 85 | McPhee Creek | DR6686 | Epiroc D65 MKII | Relief Valve |  | 5943 | 0 | 2027-04-19 | 13.79 |  | 0 | 2025-04-19
N0140 | WA | CAT | 01 | Sanjiv Ridge | DZ6528 | Cat D9T | Equalizer Bar |  | 31190.5 | 8000 | 2027-04-19 | 12 |  | 27098.08 | 2025-06-22
N0104-R | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Sprockets RIGHT |  | 43005.2 | 5000 | 2027-04-19 | 6.35 |  | 40075.21 | 2025-04-03
N0104-L | WA | CAT | 01 | Miralga Creek | DZ6517 | Cat D9T | Sprockets LEFT |  | 43005.2 | 5000 | 2027-04-19 | 6.35 |  | 40075.21 | 2025-04-03
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Ride Strut POS 4 |  | 81805 | 30000 | 2027-04-20 | 18.5 |  | 57863 | 2022-07-17 |  | 11R-1042 | REAR SUSP CYL 793D
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Ride Strut POS 3 |  | 81805 | 30000 | 2027-04-20 | 18.5 |  | 57863 | 2022-07-17 |  | 11R-1042 | REAR SUSP CYL 793D
N9500 | WA | CAT | 95 |  | RD4976 | Cat 789C | Air Cond'r-Serv |  | 427 | 5000 | 2027-04-20 | 14 |  | 0
N8995 | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Operator Seat |  | 34679 | 6000 | 2027-04-20 | 14 |  | 34081 | 2026-02-07 |  | 443-8104 | CAT OPERATOR SEAT
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Hyd Cyl Hoist RIGHT |  | 81805 | 30000 | 2027-04-20 | 18.5 |  | 57863 | 2022-07-17 |  | 295-5708 | CYLINDER GP
N7474-L | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Hyd Cyl Hoist LEFT |  | 81805 | 30000 | 2027-04-20 | 18.5 |  | 57863 | 2022-07-17 |  | 295-5708 | CYLINDER GP
N3029 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Uni's T/C - Trans |  | 76600 | 10000 | 2027-04-20 | 14 |  | 71175 | 2025-04-24 |  | 598-2864 | SPIDER & BEARING AS
N9050-UP | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Starter Motor UPPER |  | 81805 | 10000 | 2027-04-21 | 18.5 |  | 77882 | 2025-10-08 |  | 10R-9816 | STARTING MOTOR GP-ELECTRIC
N6200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Press Convertor POS 4 |  | 81805 | 10000 | 2027-04-21 | 18.5 |  | 77882 | 2025-10-11 |  | 254-1143 | CYLINDER GP-AIR/HYDRAULIC
N9050-LW | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Starter Motor LOWER |  | 81805 | 10000 | 2027-04-21 | 18.5 |  | 77882 | 2025-10-08 |  | 10R-9816 | STARTING MOTOR GP-ELECTRIC
N6060-BC | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Oil Cooler - Brake Cooling |  | 70621 | 24000 | 2027-04-21 | 15 |  | 51548 | 2022-05-29
N3028 | WA | CAT | 19 | Iron Bridge | RD4922 | Cat 793F | Drive Shaft T/C - Trans |  | 70598 | 16000 | 2027-04-21 | 18.5 |  | 60664 | 2024-10-21
N9501 | WA | CAT | 19 | Iron Bridge | RD4912 | Cat 793F | A/C Compressor |  | 59517 | 12000 | 2027-04-21 | 18.5 |  | 53585 | 2025-07-15
N9501 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | A/C Compressor |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 217-4448 | COMPRESSOR GP-REFRIGERANT
N7542-R | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Hyd Cyl Steer RIGHT |  | 66379.67 | 20000 | 2027-04-22 | 12.5 |  | 50498 | 2021-06-04
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4225 | Cat 785D | Radiator |  | 60646.3 | 20000 | 2027-04-22 | 13.75 |  | 45169 | 2023-01-22
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Cooling Sys Service |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 418-4162 | REGULATOR-TEMPERATURE
N1420 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Air Compressor |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 0R-9626 | AIR COMPRESSOR
N1100-LR | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Turbo Primary LFT REAR |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 20R-9727 | TURBO GP
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Uni's T/C - Trans |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-06 |  | 598-2864 | SPIDER & BEARING AS
N1100-RF | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Turbo Primary RHT FRONT |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 20R-9727 | TURBO GP
N7542-L | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Hyd Cyl Steer LEFT |  | 66379.67 | 20000 | 2027-04-22 | 12.5 |  | 50498 | 2021-06-04
N9020 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Alternator |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 10R-9789 | ALTERNATOR GP -B
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Fuel Transfer Pump |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 10R-8721 | PUMP GP FUEL
N1400 | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Belt Tensioner Assembly |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 336-4953 | TENSIONER,BELT
N1100-LF | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Turbo Primary LFT FRONT |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 20R-9727 | TURBO GP
N1100-RR | WA | CAT | 01 | Plant Idle - Mining West | RD2029 | Cat 793D | Turbo Primary RHT REAR |  | 81805 | 10000 | 2027-04-22 | 18.5 |  | 77883 | 2025-10-02 |  | 20R-9727 | TURBO GP
N6200-F | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Press Converter FRONT |  | 67400 | 10000 | 2027-04-23 | 17 |  | 63011 | 2025-05-27 |  | 8X-7220 | CHAMBER, BRAKE
N3028 | WA | CAT | 19 | Iron Bridge | RD4918 | Cat 793F | Drive Shaft T/C - Trans |  | 68788 | 16000 | 2027-04-23 | 18.5 |  | 58892 | 2024-11-28
N6200-RR | NT | CAT | 01 | FleetCo | RD1870 | Cat 785C XQ | Press Converter RIGHT REAR |  | 67400 | 10000 | 2027-04-23 | 17 |  | 63011 | 2025-05-27 |  | 8X-7220 | CHAMBER, BRAKE
N7474-R | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Hyd Cyl Hoist RIGHT |  | 54615 | 24000 | 2027-04-23 | 15 |  | 35569 | 2018-08-24 |  | 438-6225 | CYLINDER GP-HOIST
N0200 | WA | CAT | 01 | Sanjiv Ridge | RD6533 | Cat 785C | A Frame Bearing |  | 64732.59 | 30000 | 2027-04-23 | 12.5 |  | 38860 | 2018-12-14
N8442-03 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 3 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N8442-07 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 7 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N8442-02 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 2 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N8442-04 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 4 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N1002 | WA | CAT | 19 | Iron Bridge | RD4914 | Cat 793F | Engine Valve Adj |  | 65569 | 4000 | 2027-04-24 | 18.5 |  | 67698 | 2025-09-22
N8442-08 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 8 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N8442-05 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 5 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N8442-06 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 6 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N8442-01 | WA | CAT | 01 | Sanjiv Ridge | RD6530 | Cat 785C | Steering Ball Studs POS 1 |  | 66379.67 | 20000 | 2027-04-24 | 12.5 |  | 50519 | 2021-06-07
N6080 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Brake Calipers Park |  | 28724 | 16000 | 2027-04-25 | 15 |  | 17710 | 2024-03-30
N4000-C | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Bevel Gear CENTRE |  | 28724 | 16000 | 2027-04-25 | 15 |  | 17710 | 2024-03-30
N3040-03 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Drive Shaft POS 03 |  | 28724 | 16000 | 2027-04-25 | 15 |  | 17710 | 2024-03-30
N2000 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Transmission |  | 79726 | 20000 | 2027-04-25 | 18.5 |  | 65873 | 2024-03-14 |  | 10R-4469 | TRANSMISSION, 793D
N1000 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Engine |  | 21277 | 15000 | 2027-04-25 | 14 |  | 10927 | 2023-07-21 |  | 5875935X | EXCHANGE ENGINE
N9500 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Air Cond'r-Serv |  | 50845.5 | 5000 | 2027-04-25 | 13.75 | 11/12/2025 | 50412 | 2026-01-29
N9020 | WA | CAT | 01 | Iron Bridge | RD2031 | Cat 793D | Alternator |  | 79726 | 10000 | 2027-04-25 | 18.5 |  | 75860 | 2025-09-10 |  | 10R-9789 | ALTERNATOR GP -B
N0302 | WA | EPI | 85 | McPhee Creek | DR6685 | Epiroc D65 MKII | Feed Sprocket |  | 5650 | 6000 | 2027-04-25 | 13.79 |  | 4232 | 2026-02-14
N1100-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Turbo Primary RIGHT |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-16 |  | 20R-3695 | TURBO CHARGER GP (RH)
N0091 | WA | EPI | 85 | Iron Bridge | DR3155 | Epiroc D65 XLF MKII | Grease Pump |  | 4002 | 8000 | 2027-04-26 | 12 |  | 0 | 2025-05-14
N9050-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Starter Motor LEFT |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-17 |  | 349-6554 | STARTER MOTOR
N9050-R | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Starter Motor RIGHT |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-18 |  | 349-6554 | STARTER MOTOR
N1301 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Water Pump |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-19 |  | 10R-6400 | CAT REMAN WATER PUMP
N1202 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Fuel Transfer Pump |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-18 |  | 20R-0967 | PUMP GP FUEL
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Press Converter RIGHT REAR |  | 39200 | 10000 | 2027-04-26 | 14 |  | 33868 | 2021-05-22
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Press Converter LEFT REAR |  | 39200 | 10000 | 2027-04-26 | 14 |  | 33868 | 2021-05-21
N1300 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Cooling Sys Service |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18438 | 2025-10-17 |  | 248-5513 | REGULATOR-WATER TEMPERATURE
N7310-L | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Motor Rotation LEFT |  | 17257 | 7500 | 2027-04-26 | 14 |  | 14424 | 2025-07-14 |  | 11R-0141 | MOTOR GP-PISTON
N1100-L | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Turbo Primary LEFT |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-16 |  | 20R-3688 | TURBO CHARGER GP (LH)
N1210 | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Fuel Injectors |  | 21277 | 7500 | 2027-04-26 | 14 |  | 18436 | 2025-10-17 |  | 11R-0276 | INJECTOR GP-FUEL
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4231 | Cat 785D | Press Converter FRONT |  | 39200 | 10000 | 2027-04-27 | 14 |  | 33870 | 2021-05-22
N3029 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Uni's T/C - Trans |  | 55934 | 7500 | 2027-04-27 | 13.5 |  | 52941 | 2025-07-30 |  | 173-0888 | UNIVERSAL JOINT GP
N7310-R | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Hyd Motor Rotation RIGHT |  | 17257 | 7500 | 2027-04-27 | 14 |  | 14436 | 2025-08-04 |  | 11R-0142 | MOTOR GP-PISTON
N5000-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Final Drive RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 20R-6295 | FINAL DRIVE, D10
N1000 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Engine |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 10R-7244 | ENGINE AR-BASIC
N0111-4R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 4 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-5L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 5 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-5R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 5 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-3R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 3 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N1100-LF | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Turbo Primary LFT FRONT |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 20R-6651 | RE-MAN TURBO GP
N0111-3L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 3 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-5R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 5 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-2R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 2 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N7070 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Pump Implement |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 11R-1962 | PUMP GP-GR C
N0111-2L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 2 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-1R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 1 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-1L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 1 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N4110-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Steering Clutch/Brk RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 10R-9976 | Steering Brake And Clutch
N0111-4R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 4 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 4 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-7L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 7 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-8L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 8 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-6R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 6 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0345 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Hose Drum Assembly |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N7542-L | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Cyl Steer LEFT |  | 70621 | 15000 | 2027-04-28 | 15 |  | 60645 | 2024-03-27
N5000-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Final Drive LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2020-06-29 |  | 20R-6295 | FINAL DRIVE, D10
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Press Converter LEFT REAR |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 8W-3405 | CHAMBER, BRAKE
N1100-RF | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Turbo Primary RHT FRONT |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 20R-6651 | RE-MAN TURBO GP
N0121-R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Carrier Roller No 1 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0144 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Pivot Shaft |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03
N0121-L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Carrier Roller No 1 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-1L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 1 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0112-0R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 10 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Uni's T/C - Trans |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 363-1923 | MAIN DRIVESHAFT UNI
N0111-6L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 6 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N1312-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Aftercooler Core - LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 |  |  | 539-8656 | CORE AS-AFTERCOOLER
N0112-0L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 10 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N8995 | WA | CAT | 85 | Iron Bridge | GR1527 | Cat 140M | Operator Seat |  | 3320 | 6000 | 2027-04-28 | 8 |  | 0
N0111-7R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 7 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-3R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 3 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N2020 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Powertrain Pump |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 20R-7445 | PUMP GP
N0111-9R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 9 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-9L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 9 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-8R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 8 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N2050 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Torque Convertor |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 10R-5295 | TORQUE CONVERTER, D10
N0111-7R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 7 RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0111-7L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Roller 7 LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0130-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Frame RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03
N1100-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Turbo Primary RHT REAR |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 20R-6651 | RE-MAN TURBO GP
N0111-8L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 8 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N4000 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Bevel Gear |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N5000-R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Final Drive RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 44852.3 | 20000 | 2027-04-28 | 15 |  | 29879 | 2019-09-19 |  | 322-7212 | BLOWER,ASSY
N1100-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Turbo Primary LFT REAR |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 20R-6651 | RE-MAN TURBO GP
N0104-R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Sprockets RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0130-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Frame LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03
N3021 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Uni's Eng - Pump Drive |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 108-6587 | BEARING,SPIDER
N4110-L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Steering Clutch/Brk LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 10R-9976 | Steering Brake And Clutch
N0111-8R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 8 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Press Converter RIGHT REAR |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-18 |  | 8W-3405 | CHAMBER, BRAKE
N1403 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Jockey Pulley Brgs |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 4S-5367 | BUSHING AS
N0111-6L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 6 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N7542-R | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Hyd Cyl Steer RIGHT |  | 70621 | 15000 | 2027-04-28 | 15 |  | 60645 | 2024-03-27
N0111-6R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 6 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-4L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 4 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N1402 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Fan Pulley Brgs |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 105-2273 | FAN HUB PULLEY,789
N0111-2R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 2 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-2L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 2 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N5000-L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Final Drive LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Press Converter FRONT |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 8W-3405 | CHAMBER, BRAKE
N0101-L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Chain LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0134-R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Adjuster RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03
N2000 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Transmission |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N3016 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Drv Shaft Fan Pump-Trans Pump |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 211-9087 | COUPLING AS
N0101-R | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Track Chain RIGHT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0104-L | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Sprockets LEFT |  | 21508 | 9000 | 2027-04-28 | 12 |  | 16525 | 2025-04-30
N0105-R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Idler RIGHT |  | 55435 | 18000 | 2027-04-28 | 18.5 |  | 43626 | 2023-11-10
N1310 | WA | CAT | 85 |  | DZ3430 | Cat D10T | Radiator |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 371-6833 | RADIATOR AR
N0111-5L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 5 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N1202 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Fuel Transfer Pump |  | 57576 | 10000 | 2027-04-28 | 14 |  | 52271 | 2022-07-10 |  | 10R-9838 | PUMP GP-F XFR
N0122-R | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Carrier Roller No 2 RIGHT |  | 55435 | 18000 | 2027-04-28 | 18.5 |  | 43626 | 2023-11-10
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4218 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 44852.3 | 20000 | 2027-04-28 | 15 |  | 29879 | 2019-09-19 |  | 322-7212 | BLOWER,ASSY
N0111-3L | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 3 LEFT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N0111-1R | WA | CAT | 85 |  | DZ3430 | Cat D10T | Track Roller 1 RIGHT |  | 33117 | 12000 | 2027-04-28 | 11 |  | 24801 | 2023-04-03 |  | 309-7678 | ROLLER GP-DF
N9500-MA | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Air Cond'r-Serv - MAJOR |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18012 | 2022-09-07
N7070-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Pump Implement RIGHT |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N7070-L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Pump Implement LEFT |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N5000-L | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Final Drive LEFT |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N1301 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Water Pump |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N0520 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Pre Lube Pump |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18010 | 2022-09-06 |  | 389-8169 | MOTOR GP-ELECTRIC
N7232 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Hyd Motor Engine Fan |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N1000 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Engine |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N9502 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | A/C Condenser |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N5000-R | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Final Drive RIGHT |  | 31311 | 18000 | 2027-04-29 | 14 |  | 18011 | 2022-09-06
N8995 | WA | CAT | 01 | Iron Bridge | DZ1937 | Cat D10T | Operator Seat |  | 50673 | 6000 | 2027-04-29 | 14 |  | 49381 | 2026-03-08 |  | 443-8104 | CAT OPERATOR SEAT
N7570-RF | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack RHT FRO |  | 21277 | 10000 | 2027-04-30 | 14 |  | 16001 | 2025-04-19 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N7570-LF | WA | CAT | 85 | Iron Bridge | DR2114 | Cat MD6310 - ADS | Hyd Cyl Levelling Jack LFT FRO |  | 21277 | 10000 | 2027-04-30 | 14 |  | 15999 | 2025-04-18 |  | 447-2670X | PEX MD6250/6310 JACK LEG CYL
N0050 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | Blade Assembly |  | 14603 | 20000 | 2027-04-30 | 16 |  | 0 | 2022-09-04
N0200 | WA | CAT | 01 | Iron Bridge | GR1475 | Cat 24M | A Frame Bearing |  | 14603 | 20000 | 2027-04-30 | 16 |  | 0 | 2022-09-04
N3205-F | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooler Spltr Box FRONT |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N0050 | WA | CAT | 85 |  | GR1549 | Cat 16M | Blade Assembly |  | 23153 | 12000 | 2027-05-01 | 10 |  | 14535 | 2023-03-16 | THIESS MANAGED
N7600-ST | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve Stick |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N3205-RE | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooler Spltr Box REAR |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7610-RE | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cooler Core REAR |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7004-25 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Hose Oil Suction |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N3029 | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Uni's T/C - Trans |  | 70515 | 10000 | 2027-05-01 | 19 |  | 66939 | 2025-06-03 |  | 598-2864 | SPIDER & BEARING AS
N7600-LL | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve LEFT LOWER |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N1320-E1 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooling Fan Engine EN1 |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N1320-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Cooling Fan Engine EN2 |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7600-LU | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve LEFT UPPER |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7024 | WA | CAT | 19 | Iron Bridge | RD4917 | Cat 793F | Hyd Motor Brake Cooling |  | 69200 | 22000 | 2027-05-01 | 18.5 |  | 53461 | 2023-08-16
N9500 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Air Cond'r-Serv |  | 55934 | 5000 | 2027-05-01 | 13.5 | 22/01/2026 | 55500 | 2026-01-26
N7600-RU | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve RIGHT UPPER |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7600-BO | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve Boom |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7600-RL | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve RIGHT LOWER |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N9500 | WA | CAT | 95 |  | RD4973 | Cat 789C | Air Cond'r-Serv |  | 262 | 5000 | 2027-05-01 | 14 |  | 0
N7600-CL | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Control Valve Clam |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N7610-F | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Hyd Cooler Core FRONT |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N1000 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Engine |  | 53351 | 20000 | 2027-05-01 | 12 |  | 37406 | 2020-04-03
N1310-E2 | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Radiator EN2 |  | 23756 | 30000 | 2027-05-01 | 18.5 |  | 0
N0556 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Air Safety Valve |  | 7661 | 0 | 2027-05-02 | 12 |  | 7459 | 2026-05-02
N0105-L | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Idler LEFT |  | 23402 | 12000 | 2027-05-02 | 18.5 |  | 17666 | 2025-07-26
N9500 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Air Cond'r-Serv |  | 67572 | 5000 | 2027-05-02 | 15 |  | 67650 | 2024-01-02
N6030-RE | SA | CAT | 01 | Prominent Hill | RD2619 | Cat 793D | Brake Slack Adj REAR |  | 79044 | 24000 | 2027-05-02 | 14 |  | 59791 | 2022-08-09 |  | 590-2533 | SLACK ADJUSTER GP
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Ride Strut POS 1 |  | 67572 | 20000 | 2027-05-03 | 15 |  | 52669 | 2019-05-28
N1310 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Radiator |  | 67572 | 20000 | 2027-05-03 | 15 |  | 52669 | 2019-05-28
N1301 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Water Pump |  | 67572 | 20000 | 2027-05-03 | 15 |  | 52669 | 2019-05-24
N1302 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Aftercooler Pump |  | 67572 | 20000 | 2027-05-03 | 15 |  | 52669 | 2019-05-24
N1310 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Radiator |  | 31311 | 18000 | 2027-05-03 | 14 |  | 18071 | 2022-09-06
N1000 | WA | CAT | 01 | Plant Idle - Mining West | DU1047 | Cat 785C | Engine |  | 67572 | 20000 | 2027-05-03 | 15 |  | 52669 | 2019-05-24
N1312-LW | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Aftercooler Core - LOWER |  | 31311 | 18000 | 2027-05-03 | 14 |  | 18071 | 2022-09-06
N7610 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Hyd Cooler Core |  | 31311 | 18000 | 2027-05-03 | 14 |  | 18071 | 2022-09-06
N1312-UP | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Aftercooler Core - UPPER |  | 31311 | 18000 | 2027-05-03 | 14 |  | 18071 | 2022-09-06
N7041-E1 | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Pump Cooling Fan Eng EN1 |  | 55435 | 15000 | 2027-05-03 | 18.5 |  | 46727 | 2024-12-11
N3028 | WA | CAT | 01 | Iron Bridge | DZ8029 | Cat D10T2 | Drive Shaft T/C - Trans |  | 31311 | 18000 | 2027-05-03 | 14 |  | 18071 | 2022-09-07
N8995 | WA | CAT | 01 | Disposals | RD2943 | Cat 789C | Operator Seat |  | 71548 | 6000 | 2027-05-05 | 15 |  | 70677 | 2023-11-15 |  | 384-6168 | SEAT GP
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Ride Strut POS 4 |  | 49506 | 20000 | 2027-05-05 | 14.5 |  | 34467 | 2020-03-12 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N6015-LF | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Brake Travel LFT FRONT |  | 55435 | 15000 | 2027-05-05 | 18.5 |  | 46767 | 2024-12-15 |  | 535-2916 / 535-0350 | TRAVEL BRAKE, 6060
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | RD2035 | Cat 793D | Hyd Cyl Steer RIGHT |  | 70515 | 20000 | 2027-05-05 | 19 |  | 57008 | 2022-09-17 |  | 20R-5304 | STEER CYL
N8441 | WA | CAT | 01 | Plant Idle - Mining West | RD4210 | Cat 785C | Rear Axle Dog Bone |  | 49506 | 25000 | 2027-05-05 | 14.5 |  | 29461 | 2017-12-28
N2052 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Convertor/Trans Pump |  | 65303 | 18000 | 2027-05-06 | 18.5 |  | 53653 | 2024-02-23
N3320 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Pump Drive Box |  | 71898 | 18000 | 2027-05-06 | 18.5 |  | 60249 | 2024-09-10
N1202 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Fuel Transfer Pump |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22 |  | 20R-1524 | FUEL TRANSFER PUMP
N1301 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Water Pump |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22 |  | 352-0205
N9501 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | A/C Compressor |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22
N2000 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Transmission |  | 71898 | 18000 | 2027-05-06 | 18.5 |  | 60249 | 2024-09-11
N1300 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Cooling Sys Service |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22 |  | 248-5513
N7123 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Pump Steering & Fan |  | 71898 | 18000 | 2027-05-06 | 18.5 |  | 60249 | 2024-09-10
N1400 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Belt Tensioner Assembly |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22 |  | 336-4953
N1004 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Engine Midlife |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22
N9050 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Starter Motor |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22
N9020 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Alternator |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22
N1100 | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Turbo Primary |  | 37630 | 8000 | 2027-05-06 | 12 |  | 33750 | 2021-07-22 |  | 20R-3693 | TURBO GP-BASIC
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD1740 | Cat 789C | Operator Seat |  | 54615 | 6000 | 2027-05-07 | 15 |  | 53773 | 2023-10-17 |  | 384-6168 | SEAT GP
N8442-02 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Steering Ball Studs POS 2 |  | 58227.56 | 20000 | 2027-05-08 | 12.5 |  | 42545 | 2020-12-04
N6015-RR | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Brake Travel RHT REAR |  | 55435 | 15000 | 2027-05-08 | 18.5 |  | 46817 | 2024-12-25 |  | 535-2916 / 535-0350 | TRAVEL BRAKE, 6060
N6200-RR | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Press Converter RIGHT REAR |  | 66446.13 | 15000 | 2027-05-08 | 12.5 |  | 55752.8 | 2023-04-26
N6200-LR | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Press Converter LEFT REAR |  | 66446.13 | 15000 | 2027-05-08 | 12.5 |  | 55752.8 | 2023-04-26
N1000 | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Engine |  | 52003.6 | 18000 | 2027-05-08 | 12 |  | 38143 | 2022-01-15
N8442-08 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Steering Ball Studs POS 8 |  | 58227.56 | 20000 | 2027-05-08 | 12.5 |  | 42545 | 2020-12-04
N8442-07 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Steering Ball Studs POS 7 |  | 58227.56 | 20000 | 2027-05-08 | 12.5 |  | 42545 | 2020-12-04
N3029 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Uni's T/C - Trans |  | 65303 | 8000 | 2027-05-08 | 18.5 |  | 63678 | 2026-03-02
N8442-01 | WA | CAT | 660 | Sanjiv Ridge | RD6531 | Cat 785C | Steering Ball Studs POS 1 |  | 58227.56 | 20000 | 2027-05-08 | 12.5 |  | 42545 | 2020-12-04
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Wheel Bearing POS 1 |  | 49898.9 | 12000 | 2027-05-09 | 10 |  | 41363 | 2023-10-20
N1004 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Engine Midlife |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Wheel Bearing POS 2 |  | 49898.9 | 12000 | 2027-05-09 | 10 |  | 41363 | 2023-10-20
N8127-F | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Axle Assembly FRONT |  | 49898.9 | 12000 | 2027-05-09 | 10 |  | 41363 | 2023-10-20
N7021 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Brake Cooling |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1100-RR | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Turbo Primary RHT REAR |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7087 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Pilot |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7120-R | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Steering RIGHT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7120-L | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Steering LEFT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7121 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Steering/Braking |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1301 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Water Pump |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N3038-RE | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Uni's Trans - Bevel Gear REAR |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N3047 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drv Shft S/Bearing Pump Drives |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1100-RF | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Turbo Primary RHT FRONT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N3029 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Uni's T/C - Trans |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1302 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Aftercooler Pump |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7037 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Pump Conv P/Brake Release |  | 64591.2 | 20000 | 2027-05-09 | 13.75 |  | 49353 | 2021-07-14
N2050 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Torque Convertor |  | 64591.2 | 20000 | 2027-05-09 | 13.75 |  | 49353 | 2021-07-14
N7474-L | WA | CAT | 660 | Sanjiv Ridge | RD6314 | Cat 785C | Hyd Cyl Hoist LEFT |  | 54833.54 | 30000 | 2027-05-09 | 12.5 |  | 29155 | 2012-12-10
N7580 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Hyd Cyl Wheel Lean |  | 49898.9 | 12000 | 2027-05-09 | 10 |  | 41363 | 2023-10-20
N9020-R | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Alternator RIGHT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7647-RE | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Accum Brake Reseal REAR |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N2050 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Torque Convertor |  | 64591.2 | 20000 | 2027-05-09 | 13.75 |  | 49353 | 2021-07-14
N1202 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Fuel Transfer Pump |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1210 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Fuel Injectors |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N2050 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Torque Convertor |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7037 | WA | CAT | 01 | Prominent Hill | RD4213 | Cat 785C | Pump Conv P/Brake Release |  | 64591.2 | 20000 | 2027-05-09 | 13.75 |  | 49353 | 2021-07-14
N9020-L | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Alternator LEFT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7542-R | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Hyd Cyl Steer RIGHT |  | 49898.9 | 12000 | 2027-05-09 | 10 |  | 41363 | 2023-10-20
N3320-02 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Drive Box POS 2/RE |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1100-LF | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Turbo Primary LFT FRONT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N2020 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Powertrain Pump |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7647-F | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Hyd Accum Brake Reseal FRONT |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N2440 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Drv Coupling PTO |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1100-LR | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Turbo Primary LFT REAR |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N1300 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Cooling Sys Service |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7122 | SA | CAT | 01 | Prominent Hill | LO1931 | Cat 994H | Pump Emerg/Sup Steering |  | 44396 | 12000 | 2027-05-09 | 15 |  | 37584 | 2025-03-22
N7654-F | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Hyd Accum Service Brake - FR |  | 37630 | 16000 | 2027-05-10 | 12 |  | 25793 | 2019-08-29
N0302 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Feed Sprocket |  | 32622 | 6000 | 2027-05-10 | 13.79 |  | 31408 | 2026-02-17
N7654-RE | NT | CAT | 01 | FleetCo | GR1360 | Cat 16M | Hyd Accum Service Brake - REAR |  | 37630 | 16000 | 2027-05-10 | 12 |  | 25793 | 2019-08-29
N8995 | WA | CAT | 01 | Sanjiv Ridge | RD6502 | Cat 785C | Operator Seat |  | 67106.81 | 10000 | 2027-05-10 | 12.5 |  | 61439.51 | 2023-11-23
N8400 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Loader Frame Inspect |  | 70621 | 24000 | 2027-05-10 | 15 |  | 51827 | 2022-06-30
N3040-04 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Drive Shaft POS 04 |  | 28724 | 16000 | 2027-05-12 | 15 |  | 17959 | 2024-04-13
N3040-01 | WA | CAT | 85 | Idle Plant / Off Hired | RD4873 | Cat 740 BL4F | Drive Shaft POS 01 |  | 28724 | 16000 | 2027-05-12 | 15 |  | 17959 | 2024-03-30
N3042 | SA | CAT | 01 | Prominent Hill | LO1637 | Cat 994H | Driveline Ctr Bearing |  | 70621 | 12000 | 2027-05-12 | 15 |  | 63858 | 2024-11-21
N1430 | WA | CAT | 01 | Plant Idle - Mining West | RD4208 | Cat 785C | Air Starter |  | 47835.6 | 10000 | 2027-05-12 | 13 |  | 42370 | 2022-11-15
N0597 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 21508 | 6000 | 2027-05-13 | 12 |  | 19709 | 2025-12-17
N0596 | WA | EPI | 85 | Iron Bridge | DR3118 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 21508 | 6000 | 2027-05-13 | 12 |  | 19709 | 2025-12-17
N6200-LR | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Press Converter LEFT REAR |  | 54402.5 | 10000 | 2027-05-13 | 13.75 |  | 49217 | 2024-05-27
N6200-F | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Press Converter FRONT |  | 54402.5 | 10000 | 2027-05-13 | 13.75 |  | 49212 | 2024-05-27
N7071-05 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Pump Imp 1&2 |  | 23402 | 15000 | 2027-05-13 | 18.5 |  | 14875 | 2025-02-08
N2002 | WA | CAT | 19 | Iron Bridge | RD4920 | Cat 793F | Oil Cooler - Transmission |  | 61931 | 20000 | 2027-05-13 | 18.5 |  | 48409 | 2023-10-31
N6200-RR | WA | CAT | 01 | Plant Idle - Mining West | RD4224 | Cat 785D | Press Converter RIGHT REAR |  | 54402.5 | 10000 | 2027-05-13 | 13.75 |  | 49217 | 2024-05-27
N7120 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Pump Steering |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-01 |  | 0R-7656 | REMAN PUMP GP
N8442-08 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Steering Ball Studs POS 8 |  | 71898 | 12000 | 2027-05-14 | 18.5 |  | 66390 | 2025-08-02
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Transmission Pump |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-03
N9500 | SA | CAT | 19 | Prominent Hill | LO2139 | Cat 988 XE | Air Cond'r-Serv |  | 141.8 | 4000 | 2027-05-14 | 11 |  | 0
N8442-05 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Steering Ball Studs POS 5 |  | 71898 | 12000 | 2027-05-14 | 18.5 |  | 66390 | 2025-08-02
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Drive Shaft T/C - Trans |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-01 |  | 10R-5185 | DRIVESHAFT TC-TRANS
N1310 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Radiator |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-02 |  | 145-1226 | PEX SX 789C RADIATOR
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-01 |  | 230-4112 | UNIVERSAL JOINT GP
N8442-07 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Steering Ball Studs POS 7 |  | 71898 | 12000 | 2027-05-14 | 18.5 |  | 66390 | 2025-08-02
N9500-MA | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Air Cond'r-Serv - MAJOR |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-03 |  | 137-2134 | AIR CON GP
N8442-06 | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Steering Ball Studs POS 6 |  | 71898 | 12000 | 2027-05-14 | 18.5 |  | 66390 | 2025-08-02
N9500 | WA | CAT | 95 |  | RD4975 | Cat 789C | Air Cond'r-Serv |  | 84 | 5000 | 2027-05-14 | 14 |  | 0
N6061 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Oil Cooler Front Brakes |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-02-26 |  | 10R-0816 | REMAN OIL COOLER
N7542-L | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Hyd Cyl Steer LEFT |  | 71898 | 12000 | 2027-05-14 | 18.5 |  | 66390 | 2025-08-02
N1000 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Engine |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-03-02 |  | 175-5289 | FLEXI ENGINE
N7038 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Pump Conv,P/Brk Rel, Brk Cool |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-02-26 |  | 30R-0359 | PUMP GP-GEAR
N7542-R | WA | CAT | 19 | Iron Bridge | RD4921 | Cat 793F | Hyd Cyl Steer RIGHT |  | 71898 | 12000 | 2027-05-14 | 18.5 |  | 66390 | 2025-08-02
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Torque Convertor |  | 57576 | 20000 | 2027-05-14 | 14 |  | 42484 | 2021-02-26 |  | 20R-0924 | TORQUE CONVERTOR
N0155-R | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Tension Cyl RIGHT |  | 23756 | 12000 | 2027-05-15 | 18.5 |  | 18270 | 2025-07-12
N7420-R | WA | CAT | 01 | Sanjiv Ridge | DZ6542 | Cat D10T | Hyd Cyl Blade Lift RIGHT |  | 52003.6 | 12000 | 2027-05-15 | 12 |  | 44229 | 2023-08-29
N0155-L | WA | CAT | 88 | Iron Bridge | EX8388 | Cat 6060 | Track Tension Cyl LEFT |  | 23756 | 12000 | 2027-05-15 | 18.5 |  | 18270 | 2025-07-23
N1300 | WA | CAT | 01 | Plant Idle - Mining West | RD4249 | Cat 789C | Cooling Sys Service |  | 57576 | 10000 | 2027-05-16 | 14 |  | 52516 | 2022-07-12 |  | 418-4162 | REGULATOR TE
N7420-L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Hyd Cyl Blade Lift LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-16 |  | 626-7409 | CYL,BLADE LIFT,D10T2
N2004 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Transmission Pump |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17
N5020-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Wheel Bearing POS 1 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 289-2131 | CONE-SPECIAL TAPERED
N0111-5L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 5 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-4R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 4 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-4L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 4 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-3R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 3 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N4000 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Bevel Gear |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 11R-1751 | BEVEL GEAR 789C
N0111-2R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 2 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-2L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 2 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-1R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 1 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-1L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 1 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0105-RR | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Idler RHT REAR |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-5R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 5 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0105-RF | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Idler RHT FRONT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-19
N5020-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Wheel Bearing POS 2 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 289-2131 | CONE-SPECIAL TAPERED
N0105-LF | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Idler LFT FRONT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N6030-F | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Brake Slack Adj FRONT |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 590-2531 | SLACK ADJUSTER
N3320 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Pump Drive Box |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 11R-1517 | DRIVE GP-PUMP
N2050 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Torque Convertor |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 20R-0924 | TORQUE CONVERTOR
N6000-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Brake POS 2 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 257-6301 | BRAKE GROUP
N3028 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Drive Shaft T/C - Trans |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 10R-5185 | DRIVESHAFT TC-TRANS
N7120 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Pump Steering |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 0R-7656 | REMAN PUMP GP
N6030-RE | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Brake Slack Adj REAR |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 590-2533 | SLACK ADJUSTER
N7038 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Pump Conv,P/Brk Rel, Brk Cool |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 30R-0359 | PUMP GP-GEAR
N0105-LR | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Idler LFT REAR |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N8200-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Ride Strut POS 1 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 347-7423 | SUSP CYL
N0111-3L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 3 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N8200-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Ride Strut POS 2 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 347-7423 | SUSP CYL
N0111-8L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 8 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-6R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 6 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N8122-02 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Wheel Group POS 2 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 328-8492 | WHEEL HUB BRK GRP, FRT, 789
N0111-7L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 7 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N8122-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Wheel Group POS 1 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 328-8492 | WHEEL HUB BRK GRP, FRT, 789
N2000 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Transmission |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17
N6000-01 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Brake POS 1 |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 257-6301 | BRAKE GROUP
N2002 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Oil Cooler - Transmission |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 0R-3344 | COOLER TRANSMISSION
N0111-7R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 7 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0111-6L | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 6 LEFT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N3020 | WA | CAT | 01 | Plant Idle - Mining West | RD4240 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 64653 | 20000 | 2027-05-16 | 14 |  | 49595 | 2021-03-17 |  | 230-4112 | UNIVERSAL JOINT GP
N0111-8R | WA | CAT | 01 | Iron Bridge | DZ8083 | Cat D10T2 | Track Roller 8 RIGHT |  | 34679 | 8000 | 2027-05-16 | 14 |  | 31621 | 2025-11-18
N0520 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Pre Lube Pump |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09 |  | 116-7153 | PUMP & MOTOR, PRELUBE, ASSY
N9500-MA | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Air Cond'r-Serv - MAJOR |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09 |  | 322-7212 | BLOWER,ASSY
N2000 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Transmission |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09 |  | 0R-4007 | TRANSMISSION, 789B 785C
N7037 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Pump Conv P/Brake Release |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09
N1310 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Radiator |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37602 | 2020-04-09
N4000 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Bevel Gear |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09
N3320 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Pump Drive Box |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09 |  | 6V-8260 | SEAL,O-RING
N6030-RE | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Brake Slack Adj REAR |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-01 |  | 566-9766 | ADJUSTER GP
N3021 | SA | CAT | 01 | Prominent Hill | RD2622 | Cat 793D | Uni's Eng - Pump Drive |  | 77195 | 6000 | 2027-05-17 | 14 |  | 76158 | 2026-03-25 |  | 390-8908 | SPIDER & BEARING AS
N7065 | NT | CAT | 01 | FleetCo | RD4215 | Cat 785C | Pump Hoist/ Brk Cooling |  | 53351 | 20000 | 2027-05-17 | 12 |  | 37605 | 2020-04-09 |  | 10R-7971 | PUMP, HOIST, REMAN
N8995 | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Operator Seat |  | 2161 | 6000 | 2027-05-18 | 14 |  | 1134 | 2026-02-12 |  | 443-8104 | CAT OPERATOR SEAT
N3029 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Uni's T/C - Trans |  | 47986 | 7500 | 2027-05-18 | 12 |  | 44746 | 2025-09-03 |  | 173-0888 | UNIVERSAL JOINT GP
N3028 | WA | CAT | 19 | Iron Bridge | RD4915 | Cat 793F | Drive Shaft T/C - Trans |  | 65303 | 16000 | 2027-05-18 | 18.5 |  | 55877 | 2024-10-10
N2450 | NT | CAT | 01 | FleetCo | DZ1912 | Cat D10T | Drv Cpling Fan Pump-Trans Pump |  | 47986 | 7500 | 2027-05-18 | 12 |  | 44746 | 2025-09-03 |  | 211-9087 | COUPLING AS
N8995 | WA | CAT | 660 | Sanjiv Ridge | RD6195 | Cat 785D | Operator Seat |  | 26206.72 | 10000 | 2027-05-18 | 13.5 |  | 21005.29 | 2025-05-01
N9500 | WA | CAT | 19 | Iron Bridge | DZ3454 | Cat D10T2 | Air Cond'r-Serv |  | 2161 | 6000 | 2027-05-18 | 14 |  | 1134 | 2026-02-12
N0050 | WA | CAT | 660 | Miralga Creek | DZ6536 | Cat D10T2 | Blade Assembly |  | 17737.5 | 20000 | 2027-05-19 | 6.35 |  | 0 | 2022-06-01
N3028 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Drive Shaft T/C - Trans |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40123 | 2020-08-21 |  | 10R-5185 | DRIVESHAFT TC-TRANS
N2050 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Torque Convertor |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 20R-0924 | TORQUE CONVERTOR
N6030-RE | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Brake Slack Adj REAR |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 590-2533 | SLACK ADJUSTER
N7542-R | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Hyd Cyl Steer RIGHT |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 30R-1082 | STEER CYL 789C
N4000 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Bevel Gear |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40123 | 2020-08-21 |  | 11R-1751 | BEVEL GEAR 789C
N8137-R | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Steering Linkage Group RIGHT |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 2A-6945 | LINK, STEERING, 789
N8140 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Steering Y Piece |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 135-5269 | CENTRE ARM, STEERING, 789
N8137-L | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Steering Linkage Group LEFT |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 2A-6945 | LINK, STEERING, 789
N7120 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Pump Steering |  | 66446.13 | 20000 | 2027-05-19 | 12.5 |  | 50894.78 | 2021-10-12
N6030-F | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Brake Slack Adj FRONT |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 590-2531 | SLACK ADJUSTER
N3020 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Drive Shaft Eng - Pump Drive |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40123 | 2019-11-25 |  | 230-4112 | UNIVERSAL JOINT GP
N7657-RE | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Hyd Accum Steering REAR |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40123 | 2020-08-21 |  | 524-7242 | ACCUMULATOR GP-HYDRAULIC
N3320 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Pump Drive Box |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40123 | 2020-08-21 |  | 11R-1517 | DRIVE GP-PUMP
N7542-L | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Hyd Cyl Steer LEFT |  | 54781 | 20000 | 2027-05-19 | 15 |  | 40124 | 2020-08-21 |  | 30R-1082 | STEER CYL 789C
N1320-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooling Fan Engine EN2 |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7600-RU | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve RIGHT UPPER |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N1320-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooling Fan Engine EN1 |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7610-F | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cooler Core FRONT |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7600-LL | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve LEFT LOWER |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N3205-RE | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooler Spltr Box REAR |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7004-25 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Hose Oil Suction |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7600-LU | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve LEFT UPPER |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7600-CL | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve Clam |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7600-ST | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve Stick |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N0346 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7151 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Pump Water Injection (Bean) |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7310-R | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Hyd Motor Rotation RIGHT |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7310-L | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Hyd Motor Rotation LEFT |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N3205-F | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Cooler Spltr Box FRONT |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7234 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7232 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Hyd Motor Engine Fan |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7610-RE | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Hyd Cooler Core REAR |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N3341 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Rotary Head Planetary |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N2090 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Drv Coupling |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N0091-RT | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Grease Pump ROD THREAD |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1310-E2 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Radiator EN2 |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N1301 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Water Pump |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1300 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Cooling Sys Service |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1210 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Fuel Injectors |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1200 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Fuel Pump |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1100 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Turbo Primary |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1004 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Engine Midlife |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N0596 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N0558 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Air End Coupling |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7600-BO | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve Boom |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N0350 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N0302 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Feed Sprocket |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N7340 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N8995 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Operator Seat |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N0597 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N9050 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Starter Motor |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N9020 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | Alternator |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N9501 | WA | EPI | 85 | Iron Bridge | DR3154 | Epiroc D65 XLF MKII | A/C Compressor |  | 1713 | 6000 | 2027-05-20 | 12 |  | 0
N1310-E1 | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Radiator EN1 |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N7432-L | WA | BE | 19 | Iron Bridge | EX2649 | O&K RH340B | Hyd Cyl Bucket LEFT |  | 55435 | 8000 | 2027-05-20 | 18.5 |  | 54043 | 2026-02-26
N7600-RL | WA | CAT | 88 | Iron Bridge | EX2619 | Cat 6060 | Control Valve RIGHT LOWER |  | 23402 | 30000 | 2027-05-20 | 18.5 |  | 0
N6000-05 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Brake POS 5 |  | 49898.9 | 16000 | 2027-05-21 | 10 |  | 37480 | 2022-08-28 |  | 20R-9994 | BRAKE GP FRONT
N6000-03 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Brake POS 3 |  | 49898.9 | 16000 | 2027-05-21 | 10 |  | 37477 | 2022-06-16 |  | 20R-9994 | BRAKE GP FRONT
N0554 | WA | EPI | 01 | McPhee Creek | DR6578 | Epiroc D65 | Air Inlet Valve |  | 34291 | 5000 | 2027-05-21 | 13.79 |  | 34227 | 2026-05-10
N6000-06 | WA | CAT | 01 | Plant Idle - Mining West | GR1373 | Cat 16M | Brake POS 6 |  | 49898.9 | 16000 | 2027-05-21 | 10 |  | 37477 | 2022-07-06 |  | 20R-9994 | BRAKE GP FRONT
N0554 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Air Inlet Valve |  | 32622 | 5000 | 2027-05-22 | 13.79 | 25/05/2026 | 32567 | 2026-05-25
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Operator Seat |  | 39658.4 | 6000 | 2027-05-22 | 15 |  | 39044 | 2023-12-20 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N4000 | WA | CAT | 01 | Sanjiv Ridge | RD6313 | Cat 785C | Bevel Gear |  | 66446.13 | 20000 | 2027-05-22 | 12.5 |  | 50928.86 | 2021-10-16
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD4219 | Cat 785C | Operator Seat |  | 39658.4 | 6000 | 2027-05-22 | 15 |  | 39044 | 2023-12-20 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N7414-L | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | Hyd Cyl Artic LEFT |  | 26541 | 16000 | 2027-05-22 | 12.5 |  | 15034 | 2022-10-13
N1002 | WA | CAT | 85 | Iron Bridge | LO2055 | Cat 962M | Engine Valve Adj |  | 2074 | 1000 | 2027-05-23 | 6 |  | 3237 | 2023-11-02
N8995 | WA | CAT | 01 | Plant Idle - Mining West | RD3977 | Cat 785C | Operator Seat |  | 50845.5 | 6000 | 2027-05-23 | 13.75 |  | 49801 | 2025-12-15 |  | 384-6168 | OPERATOR SEAT_CAT 785C
N0111-5L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 5 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-3L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 3 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-1L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 1 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-6L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 6 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N1402 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Fan Pulley Brgs |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 105-2273 | FAN HUB PULLEY,789
N9501 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | A/C Compressor |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 0R-6756 | COMPRESSOR GP -H
N0111-8R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 8 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0121-L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Carrier Roller No 1 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N1202 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Fuel Transfer Pump |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 10R-9838 | PUMP GP-F XFR
N3029 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Uni's T/C - Trans |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50202 | 2023-05-22 |  | 363-1923 | MAIN DRIVESHAFT UNI
N0111-8L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 8 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N6200-F | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Press Converter FRONT |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50202 | 2023-05-22 |  | 8W-3405 | CHAMBER, BRAKE
N1100-RR | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Turbo Primary RHT REAR |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 20R-6651 | RE-MAN TURBO GP
N0111-4L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 4 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N1300 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Cooling Sys Service |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 418-4162 | REGULATOR TE
N1100-LR | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Turbo Primary LFT REAR |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 20R-6651 | RE-MAN TURBO GP
N0111-6R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 6 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-2R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 2 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N3021 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Uni's Eng - Pump Drive |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50202 | 2023-05-22 |  | 108-6587 | BEARING,SPIDER
N9020 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Alternator |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 10R-8755 | ALTERNATOR GP -B
N0111-7L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 7 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-1R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 1 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-4R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 4 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-5R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 5 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N6200-LR | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Press Converter LEFT REAR |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50202 | 2023-05-22 |  | 8W-3405 | CHAMBER, BRAKE
N1100-LF | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Turbo Primary LFT FRONT |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 20R-6651 | RE-MAN TURBO GP
N0111-3R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 3 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N1403 | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Jockey Pulley Brgs |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 4S-5367 | BUSHING AS
N6200-RR | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Press Converter RIGHT REAR |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50202 | 2023-05-22 |  | 8W-3405 | CHAMBER, BRAKE
N0121-R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Carrier Roller No 1 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N1100-RF | WA | CAT | 01 | Disposals | RD2040 | Cat 789C | Turbo Primary RHT FRONT |  | 54781 | 10000 | 2027-05-24 | 15 |  | 50191 | 2022-04-21 |  | 20R-6651 | RE-MAN TURBO GP
N0111-2L | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 2 LEFT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N0111-7R | WA | CAT | 85 | McPhee Creek | DZ6661 | Cat D10T2 | Track Roller 7 RIGHT |  | 5903.7 | 8500 | 2027-05-24 | 7.2 |  | 0 | 2025-01-08
N1310 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Radiator |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N1320 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Cooling Fan Engine |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N1000 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Engine |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N1312 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Aftercooler Core |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N0551 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Cooler Aircompressor |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N8995 | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Operator Seat |  | 32622 | 10000 | 2027-05-25 | 13.79 |  | 27609.33 | 2025-06-02
N7460-03 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Feed Dump RIGHT |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7594 | WA | EPI | 85 | Iron Bridge | DR3121 | Epiroc D65 XLF MKII | Hyd Cyl Dust Hood |  | 22440 | 12000 | 2027-05-25 | 12 |  | 14782 | 2023-08-11
N7480-R | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation RIGH |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7597 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Boom Swing |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7480-L | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Track Oscillation LEFT |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7008-01 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Pump Hydraulic POS 1 |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7657-F | WA | CAT | 01 | Plant Idle - Mining West | RD2028 | Cat 793D | Hyd Accum Steering FRONT |  | 86119 | 20000 | 2027-05-25 | 18.5 |  | 72807 | 2024-05-09 |  | 20R-8270 | ACCUMULATOR, STEERING, 793D 793F
N7460-02 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Feed Dump LEFT |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7426 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Boom Lift |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7600 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Control Valve |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7570-RE | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Levelling Jack REAR |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7610 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cooler Core |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7594 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Hyd Cyl Dust Hood |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7008-02 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Pump Hydraulic POS 2 |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7627 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Valve Track Oscillation |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7008-03 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Pump Hydraulic POS 3 |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7039 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Pump Cooler Fan Hyd/Eng |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N7044 | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Cooler Fan Hyd |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N9500-MA | WA | EPI | 85 | Iron Bridge | DR3146 | Epiroc D65 XLF MKII | Air Cond'r-Serv - MAJOR |  | 7661 | 12000 | 2027-05-25 | 12 |  | 0
N3021 | SA | CAT | 01 | Prominent Hill | RD2621 | Cat 793D | Uni's Eng - Pump Drive |  | 76600 | 6000 | 2027-05-27 | 14 |  | 75699 | 2026-03-20 |  | 390-8908 | SPIDER & BEARING AS
N9500 | WA | CAT | 85 | Iron Bridge | EX4115 | Cat 374 | Air Cond'r-Serv |  | 2813 | 5000 | 2027-05-27 | 6 |  | 0
N8200-03 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Ride Strut POS 3 |  | 41713 | 20000 | 2027-05-27 | 15 |  | 27171 | 2018-04-25 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N7480-R | WA | EPI | 01 | McPhee Creek | DR6579 | Epiroc D65 | Hyd Cyl Track Oscillation RIGH |  | 32622 | 12000 | 2027-05-27 | 13.79 |  | 25639 | 2023-11-08
N8200-04 | WA | CAT | 01 | Plant Idle - Mining West | RD6032 | Cat 785C | Ride Strut POS 4 |  | 41713 | 20000 | 2027-05-27 | 15 |  | 27173 | 2018-05-16 |  | 11R-1040 | CYL, SUSPENSION, REAR, 785
N7605 | WA | CAT | 01 | Sanjiv Ridge | RD6503 | Cat 785C | Steering Hmu |  | 67683.26 | 12000 | 2027-05-27 | 12.5 |  | 60238 | 2023-08-03
N5000-L | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Final Drive LEFT |  | 55934 | 15000 | 2027-05-28 | 13.5 |  | 45863 | 2023-11-12 |  | 20R-6295 | FINAL DRIVE, D10
N0302 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Feed Sprocket |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N8995 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Operator Seat |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N0558 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Air End Coupling |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N0350 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Pump Hammer Lubrication |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N2090 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Drv Coupling |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N0623-LU | WA | CAT | 85 | Iron Bridge | DR2115 | Cat MD6310 - ADS | Pullback Sheave UPPER LEFT |  | 17257 | 7500 | 2027-05-28 | 14 |  | 14872 | 2025-08-28 |  | 450-8053 | SHEAVE AS
N0597 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Air Load Solenoid Valve |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N2000 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Transmission |  | 55934 | 15000 | 2027-05-28 | 13.5 |  | 45863 | 2023-11-12 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N1300 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Cooling Sys Service |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N9050 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Starter Motor |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N4000 | WA | CAT | 01 | Plant Idle - Mining West | DZ1757 | Cat D10T | Bevel Gear |  | 55934 | 15000 | 2027-05-28 | 13.5 |  | 45863 | 2023-11-12 |  | 10R-5292 | TRANSMISSION BEVEL GRP, D10
N7340 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Motor Feed |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N9501 | WA | CAT | 01 | Iron Bridge | GR1271 | Cat 16M | A/C Compressor |  | 26541 | 8000 | 2027-05-28 | 12.5 |  | 23109 | 2025-10-22
N9501 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | A/C Compressor |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N7234 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Motor Cooler Fan |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N0346 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hose Drum Sprocket |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N7232 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Hyd Motor Engine Fan |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N0596 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Air Flushing Valve |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17
N9020 | WA | EPI | 85 | Iron Bridge | DR3147 | Epiroc D65 XLF MKII | Alternator |  | 8398 | 6000 | 2027-05-28 | 12 |  | 6776 | 2025-12-17

## JDE Component Forecast
Unit Number | Equipment Description | Service Type | Service Type Description | Frequency SMU | Last Completed Hours | Last Completed Date | Hours Run | JDE Forecast Date | Meter to Run SMU | ST | Actual Location
DR1080 | Cat MD6250 | N0066 | Fire Suppression Sys Cylinder |  |  |  | 444 |  |  | WA | McPhee Creek
DR1080 | Cat MD6250 | N0556 | Air Safety Valve |  |  |  | 444 |  |  | WA | McPhee Creek
DR1080 | Cat MD6250 | N1002 | Engine Valve Adj | 3000 |  |  | 444 | 2026-10-17 | 2556 | WA | McPhee Creek
DR1080 | Cat MD6250 | N8995 | Operator Seat | 6000 |  |  | 444 | 2027-04-02 | 5556 | WA | McPhee Creek
DR1080 | Cat MD6250 | N9500 | Air Cond'r-Serv | 5000 |  |  | 444 | 2027-02-05 | 4556 | WA | McPhee Creek
DR2114 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  | 17223 | 2025-06-26 | 21277 | 2030-06-25 |  | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  |  | 21277 | 2023-09-17 | -13777 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  |  | 21277 | 2023-09-17 | -13777 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 | 15209 | 2024-10-04 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 | 15209 | 2024-10-06 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 | 15209 | 2024-10-06 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 | 15209 | 2024-10-06 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 | 15209 | 2024-10-06 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 | 15209 | 2024-10-06 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  |  | 21277 | 2025-03-06 | -6277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  |  | 21277 | 2028-02-10 | 8723 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 21277 | 2023-09-17 | -13777 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0550 | Air End | 15000 | 14471 | 2024-07-12 | 21277 | 2028-01-03 | 8194 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 | 14471 | 2024-07-13 | 21277 | 2028-01-03 | 8194 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 19311 | 2026-01-22 | 21277 | 2027-01-22 |  | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 18019 | 2025-09-19 | 21277 | 2026-04-04 | -758 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 18019 | 2025-09-19 | 21277 | 2026-04-04 | -758 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 18019 | 2025-09-18 | 21277 | 2026-04-04 | -758 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 18019 | 2025-09-18 | 21277 | 2026-04-04 | -758 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 | 15209 | 2024-10-02 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 21277 | 2030-01-24 | 18723 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1000 | Engine | 15000 | 10927 | 2023-07-21 | 21277 | 2027-04-25 | 4650 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 18436 | 2025-10-16 | 21277 | 2026-08-01 | 909 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 10927 | 2023-07-21 | 21277 | 2024-06-06 | -10100 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 | 18436 | 2025-10-16 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 | 18436 | 2025-10-16 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 | 18436 | 2025-10-18 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 | 18436 | 2025-10-17 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 | 18438 | 2025-10-17 | 21277 | 2027-04-26 | 4661 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 | 18436 | 2025-10-19 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  |  | 21277 | 2028-02-10 | 8723 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 | 15209 | 2024-10-01 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 | 15209 | 2024-10-01 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 | 14471 | 2024-07-14 | 21277 | 2028-01-03 | 8194 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 18436 | 2025-10-16 | 21277 | 2026-03-29 | -841 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 18436 | 2025-10-18 | 21277 | 2026-10-29 | 2159 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 18436 | 2025-10-18 | 21277 | 2026-10-29 | 2159 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 | 10681 | 2023-07-03 | 21277 | 2027-04-08 | 4404 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 | 17902 | 2025-08-22 | 21277 | 2028-09-04 | 11625 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 | 14471 | 2024-07-14 | 21277 | 2028-01-03 | 8194 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 | 18019 | 2025-09-22 | 21277 | 2028-09-13 | 11742 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 | 12677 | 2023-11-18 | 21277 | 2027-08-28 | 6400 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 | 12677 | 2023-11-19 | 21277 | 2027-08-28 | 6400 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 | 11683 | 2023-09-11 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 | 11683 | 2023-09-11 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 | 20257 | 2026-03-09 | 21277 | 2029-02-20 | 13980 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 | 12677 | 2023-11-20 | 21277 | 2027-08-28 | 6400 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 | 11683 | 2023-09-11 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 | 13619 | 2024-02-29 | 21277 | 2026-05-17 | -158 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 | 15209 | 2024-10-05 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 20261 | 2026-03-14 | 21277 | 2027-09-03 | 6484 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 18939 | 2025-11-14 | 21277 | 2027-06-01 | 5162 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 | 15202 | 2024-10-04 | 21277 | 2028-02-25 | 8925 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 | 15202 | 2024-10-04 | 21277 | 2028-02-25 | 8925 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 | 13565 | 2024-04-01 | 21277 | 2027-10-31 | 7288 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 | 15209 | 2024-10-02 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 | 15209 | 2024-10-02 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 | 15209 | 2024-10-01 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 | 15209 | 2024-10-02 | 21277 | 2028-02-25 | 8932 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 | 11683 | 2023-09-11 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 | 11683 | 2023-09-11 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 | 11683 | 2023-09-09 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 | 15999 | 2025-04-18 | 21277 | 2027-04-30 | 4722 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 | 16507 | 2025-05-16 | 21277 | 2028-05-28 | 10230 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 | 16001 | 2025-04-19 | 21277 | 2027-04-30 | 4724 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 | 17902 | 2025-08-22 | 21277 | 2028-09-04 | 11625 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 | 11683 | 2023-09-11 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 | 7230 | 2022-11-17 | 21277 | 2026-08-06 | 953 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 | 4460 |  | 21277 | 2026-01-18 | -1817 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 | 20261 | 2026-03-11 | 21277 | 2029-02-20 | 13984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 | 20925 | 2026-04-30 | 21277 | 2029-04-08 | 14648 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 | 11683 | 2023-09-10 | 21277 | 2027-06-18 | 5406 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 | 15160 | 2024-08-23 | 21277 | 2028-02-22 | 8883 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 | 12693 | 2023-11-20 | 21277 | 2027-08-29 | 6416 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 | 12693 | 2023-11-19 | 21277 | 2027-08-29 | 6416 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 | 12693 | 2023-11-20 | 21277 | 2027-08-29 | 6416 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 | 12693 | 2023-11-18 | 21277 | 2027-08-29 | 6416 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  |  | 21277 | 2028-02-10 | 8723 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 | 15160 | 2024-08-23 | 21277 | 2028-02-22 | 8883 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 | 13622 | 2024-01-12 | 21277 | 2027-11-04 | 7345 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9020 | Alternator | 7500 | 20261 | 2026-03-10 | 21277 | 2027-09-03 | 6484 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 | 18436 | 2025-10-17 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 | 18436 | 2025-10-18 | 21277 | 2027-04-26 | 4659 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 20261 | 2026-03-13 | 21277 | 2026-12-27 | 2984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 15209 | 2024-10-06 | 21277 | 2026-09-07 | 1432 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 | 20244 | 2026-03-17 | 21277 | 2027-03-07 | 3967 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 | 14471 | 2024-07-14 | 21277 | 2027-01-11 | 3194 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  |  | 21277 | 2028-02-10 | 8723 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 | 20261 | 2026-03-13 | 21277 | 2030-02-12 | 18984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 | 20261 | 2026-03-12 | 21277 | 2030-02-12 | 18984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 | 20244 | 2026-03-17 | 21277 | 2030-02-11 | 18967 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 | 20261 | 2026-03-17 | 21277 | 2030-02-12 | 18984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 | 20261 | 2026-03-13 | 21277 | 2030-02-12 | 18984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 | 20244 | 2026-03-17 | 21277 | 2030-02-11 | 18967 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  |  | 21277 | 2026-02-28 | -1277 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 | 20261 | 2026-03-13 | 21277 | 2030-02-12 | 18984 | WA | Iron Bridge
DR2114 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 | 19301 | 2026-01-11 | 21277 | 2027-12-22 | 8024 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  | 16417 | 2025-12-06 | 17257 | 2030-12-05 |  | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  |  | 17257 | 2024-06-30 | -9757 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  |  | 17257 | 2024-06-30 | -9757 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 | 2726 | 2022-12-25 | 17257 | 2026-07-01 | 469 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  |  | 17257 | 2028-11-23 | 12743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 17257 | 2024-06-30 | -9757 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0550 | Air End | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 16417 | 2025-12-06 | 17257 | 2026-12-06 |  | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 17223 | 2026-01-31 | 17257 | 2026-07-18 | 2466 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 17223 | 2026-01-31 | 17257 | 2026-07-18 | 2466 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 17223 | 2026-01-31 | 17257 | 2026-07-18 | 2466 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 17223 | 2026-01-31 | 17257 | 2026-07-18 | 2466 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 | 10796 | 2024-10-25 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 | 14872 | 2025-08-28 | 17257 | 2027-05-28 | 5115 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 | 10796 | 2024-10-24 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 | 10796 | 2024-10-24 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 | 10796 | 2024-10-24 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 | 10796 | 2024-10-24 | 17257 | 2026-04-14 | 1039 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 17257 | 2030-11-08 | 22743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1000 | Engine | 15000 | 15347 | 2025-09-29 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 15347 | 2025-09-29 | 17257 | 2026-08-03 | 1840 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 15589 | 2025-10-15 | 17257 | 2026-02-16 | -1418 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  |  | 17257 | 2028-11-23 | 12743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 12371 | 2025-02-19 | 17257 | 2025-09-22 | -2886 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 15347 | 2025-10-02 | 17257 | 2027-01-04 | 3090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 15347 | 2025-10-01 | 17257 | 2027-01-04 | 3090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 | 14436 | 2025-07-29 | 17257 | 2028-10-14 | 12179 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 | 15327 | 2025-09-23 | 17257 | 2028-12-17 | 13070 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 | 15327 | 2025-09-23 | 17257 | 2028-12-17 | 13070 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 | 15327 | 2025-10-03 | 17257 | 2028-12-17 | 13070 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 | 15819 | 2025-11-02 | 17257 | 2029-01-21 | 13562 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 | 16560 | 2025-12-19 | 17257 | 2027-09-26 | 6803 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 14424 | 2025-07-14 | 17257 | 2027-04-26 | 4667 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 14436 | 2025-08-04 | 17257 | 2027-04-27 | 4679 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 | 15347 | 2025-10-03 | 17257 | 2028-12-18 | 13090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 | 14436 | 2025-07-30 | 17257 | 2028-10-14 | 12179 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 | 15736 | 2025-10-25 | 17257 | 2029-01-15 | 13479 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 | 15736 | 2025-10-24 | 17257 | 2029-01-15 | 13479 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 | 15736 | 2025-10-25 | 17257 | 2029-01-15 | 13479 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 | 15736 | 2025-10-24 | 17257 | 2029-01-15 | 13479 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 | 16419 | 2025-12-06 | 17257 | 2029-03-05 | 14162 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 | 16237 | 2025-11-25 | 17257 | 2029-02-20 | 13980 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 17257 | 2025-12-15 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  |  | 17257 | 2025-12-15 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  |  | 17257 | 2025-12-15 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  |  | 17257 | 2025-11-05 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 | 16799 | 2026-01-02 | 17257 | 2029-04-01 | 14542 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 | 16799 | 2026-01-02 | 17257 | 2029-04-01 | 14542 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 | 16799 | 2026-01-02 | 17257 | 2029-04-01 | 14542 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 | 17213 | 2026-02-13 | 17257 | 2029-04-30 | 14956 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 | 9238 | 2025-08-13 | 17257 | 2026-08-14 | 1981 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  |  | 17257 | 2025-09-28 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 | 10796 | 2024-10-26 | 17257 | 2027-02-05 | 3539 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  |  | 17257 | 2025-11-05 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 | 16237 | 2025-11-25 | 17257 | 2029-02-20 | 13980 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 | 16237 | 2025-11-25 | 17257 | 2029-02-20 | 13980 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 | 16237 | 2025-11-26 | 17257 | 2029-02-20 | 13980 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 | 17302 | 2026-05-18 | 17257 | 2029-05-07 | 15045 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 | 17213 | 2026-02-13 | 17257 | 2029-04-30 | 14956 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 | 8611 | 2024-02-08 | 17257 | 2027-08-25 | 6354 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 | 12371 | 2024-03-02 | 17257 | 2028-05-19 | 10114 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 | 17213 | 2026-02-13 | 17257 | 2029-04-30 | 14956 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 | 17213 | 2026-02-13 | 17257 | 2029-04-30 | 14956 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  |  | 17257 | 2025-11-05 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 | 16424 | 2025-12-05 | 17257 | 2029-03-05 | 14167 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  |  | 17257 | 2025-12-18 | -2257 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  |  | 17257 | 2028-11-23 | 12743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 | 16301 | 2025-11-30 | 17257 | 2029-02-24 | 14044 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 | 17213 | 2026-02-15 | 17257 | 2029-04-30 | 14956 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9020 | Alternator | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 | 15347 | 2025-09-29 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 15347 | 2025-10-02 | 17257 | 2026-08-19 | 2090 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 15347 | 2025-10-02 | 17257 | 2027-07-01 | 5590 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 | 14699 | 2025-08-19 | 17257 | 2026-09-12 | 2442 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 | 8674 | 2024-06-16 | 17257 | 2026-07-05 | 1417 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  |  | 17257 | 2028-11-23 | 12743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  |  | 17257 | 2026-12-10 | 2743 | WA | Iron Bridge
DR2115 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 | 8674 | 2024-06-15 | 17257 | 2026-07-05 | 1417 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-06-23 | 12996 | 2028-06-21 |  | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  |  | 12996 | 2025-04-30 | -5496 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  |  | 12996 | 2025-04-30 | -5496 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  |  | 12996 | 2029-09-24 | 17004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 12996 | 2025-04-30 | -5496 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0550 | Air End | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 12015 | 2026-03-28 | 12996 | 2027-03-28 |  | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 11438 | 2026-02-17 | 12996 | 2026-08-03 | 942 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 11438 | 2026-02-16 | 12996 | 2026-08-03 | 942 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 11438 | 2026-02-15 | 12996 | 2026-08-03 | 942 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 11438 | 2026-02-15 | 12996 | 2026-08-03 | 942 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 12996 | 2031-09-08 | 27004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 12634 | 2026-04-28 | 12996 | 2027-01-25 | 3388 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 310 | 2023-07-08 | 12996 | 2023-12-22 | -12436 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 | 8474 | 2025-06-20 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 | 8474 | 2025-06-20 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 | 8474 | 2025-06-21 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 | 8474 | 2025-06-22 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 | 8474 | 2025-06-21 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 | 8474 | 2025-06-21 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  |  | 12996 | 2029-09-24 | 17004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 12634 | 2026-04-28 | 12996 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 8474 | 2025-06-22 | 12996 | 2026-07-01 | 478 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 12046 | 2026-03-28 | 12996 | 2027-03-13 | 4050 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  |  | 12996 | 2025-04-30 | -5496 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 8474 | 2025-06-21 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 8474 | 2025-06-21 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 | 9216 | 2025-08-13 | 12996 | 2027-08-15 | 6220 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 | 6773 | 2025-03-23 | 12996 | 2027-02-22 | 3777 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 | 11042 | 2026-01-27 | 12996 | 2028-12-15 | 13046 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 | 11438 | 2026-02-17 | 12996 | 2029-01-12 | 13442 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 |  |  | 12996 | 2026-10-11 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  |  | 12996 | 2029-09-24 | 17004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  |  | 12996 | 2026-10-18 | 2004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9020 | Alternator | 7500 | 8686 | 2025-07-19 | 12996 | 2027-01-11 | 3190 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 | 8474 | 2025-06-21 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 | 8474 | 2025-06-23 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 12703 | 2026-05-09 | 12996 | 2027-02-17 | 3707 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 8474 | 2025-06-23 | 12996 | 2026-12-27 | 2978 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 | 12046 | 2026-03-29 | 12996 | 2027-03-13 | 4050 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 | 10264 | 2025-12-07 | 12996 | 2027-10-29 | 7268 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  |  | 12996 | 2029-09-24 | 17004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  |  | 12996 | 2027-10-10 | 7004 | WA | Iron Bridge
DR2116 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 | 10894 | 2026-01-17 | 12996 | 2027-12-13 | 7898 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-06-01 | 14426 | 2028-05-30 |  | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  |  | 14426 | 2025-01-18 | -6926 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  |  | 14426 | 2025-01-18 | -6926 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  |  | 14426 | 2029-06-13 | 15574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 14426 | 2025-01-18 | -6926 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0550 | Air End | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 12498 | 2026-01-18 | 14426 | 2027-01-18 |  | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 10931 | 2025-10-13 | 14426 | 2026-04-01 | -995 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 10931 | 2025-10-13 | 14426 | 2026-04-01 | -995 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 10931 | 2025-10-14 | 14426 | 2026-04-01 | -995 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 10931 | 2025-10-13 | 14426 | 2026-04-01 | -995 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 | 6478 | 2024-11-30 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 | 6478 | 2024-11-30 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 | 6478 | 2024-11-29 | 14426 | 2026-05-08 | -448 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 14426 | 2031-05-29 | 25574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 12531 | 2026-01-19 | 14426 | 2026-10-03 | 1855 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 410 | 2023-10-14 | 14426 | 2023-09-13 | -13766 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 | 14306 | 2026-05-11 | 14409 | 2027-11-03 | 7397 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 | 6904 | 2025-03-04 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 | 6904 | 2025-03-02 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 | 6904 | 2025-03-03 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 | 6904 | 2025-03-03 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 | 6904 | 2025-03-03 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  |  | 14426 | 2029-06-13 | 15574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 12531 | 2026-01-19 | 14426 | 2026-06-05 | 105 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 6169 | 2024-10-14 | 14426 | 2025-10-01 | -3257 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 5896 | 2024-09-30 | 14426 | 2025-09-12 | -3530 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  |  | 14426 | 2025-01-18 | -6926 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 6904 | 2025-03-03 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 6785 | 2025-01-23 | 14426 | 2026-05-13 | -141 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 |  |  | 14426 | 2025-08-08 | -4426 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 | 6640 | 2025-01-06 | 14426 | 2026-11-02 | 2214 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 | 11684 | 2025-12-02 | 14426 | 2028-10-20 | 12258 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 | 10012 | 2025-08-30 | 14426 | 2028-06-22 | 10586 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  |  | 14426 | 2026-07-08 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  |  | 14426 | 2029-06-13 | 15574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  |  | 14426 | 2026-07-04 | 574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9020 | Alternator | 7500 | 10125 | 2025-09-05 | 14426 | 2027-01-07 | 3199 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 | 8980 | 2025-07-13 | 14426 | 2026-10-17 | 2054 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 | 8980 | 2025-07-13 | 14426 | 2026-10-17 | 2054 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 11360 | 2025-11-09 | 14426 | 2026-07-30 | 934 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 6904 | 2025-03-03 | 14426 | 2026-05-22 | -22 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 | 6640 | 2025-01-06 | 14426 | 2025-12-02 | -2786 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 | 11360 | 2025-11-09 | 14426 | 2027-10-05 | 6934 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  |  | 14426 | 2029-06-13 | 15574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  |  | 14426 | 2027-06-30 | 5574 | WA | Iron Bridge
DR2117 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 | 12696 | 2026-02-02 | 14426 | 2028-01-09 | 8270 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-07-01 | 16356 | 2027-06-30 |  | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  |  | 16356 | 2024-09-02 | -8856 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  |  | 16356 | 2024-09-02 | -8856 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 | 9508 | 2025-04-06 | 16356 | 2027-12-31 | 8152 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 | 3509 | 2024-03-12 | 16356 | 2026-10-29 | 2153 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  |  | 16356 | 2029-01-27 | 13644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 16356 | 2024-09-02 | -8856 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0550 | Air End | 15000 | 15514 | 2026-03-28 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 | 15514 | 2026-03-21 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 15257 | 2026-02-24 | 16356 | 2027-02-24 |  | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 15677 | 2026-04-17 | 16356 | 2026-10-05 | 1821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 15677 | 2026-04-18 | 16356 | 2026-10-05 | 1821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 15677 | 2026-04-18 | 16356 | 2026-10-05 | 1821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 15677 | 2026-04-17 | 16356 | 2026-10-05 | 1821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 | 15677 | 2026-04-17 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 16356 | 2031-01-11 | 23644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1000 | Engine | 15000 | 15677 | 2026-04-23 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 15677 | 2026-04-23 | 16356 | 2027-01-02 | 3071 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 7847 | 2024-12-17 | 16356 | 2026-04-30 | -8259 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 | 15677 | 2026-04-23 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 | 15677 | 2026-04-23 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 | 15677 | 2026-04-23 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 | 15677 | 2026-04-23 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 | 15677 | 2026-04-23 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 | 15677 | 2026-04-23 | 16356 | 2027-09-27 | 6821 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  |  | 16356 | 2029-01-27 | 13644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 | 15514 | 2026-03-20 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 | 15514 | 2026-03-20 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 | 15514 | 2026-03-19 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 15514 | 2026-03-26 | 16356 | 2026-08-19 | 1158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 15514 | 2026-03-24 | 16356 | 2027-03-21 | 4158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 15514 | 2026-03-27 | 16356 | 2027-03-21 | 4158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 | 15514 | 2026-03-24 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  |  | 16356 | 2026-02-17 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  |  | 16356 | 2026-02-17 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 | 15514 | 2026-03-22 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 | 15514 | 2026-03-22 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 | 15514 | 2026-03-24 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 | 15514 | 2026-03-24 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 | 12346 | 2025-09-06 | 16356 | 2028-07-21 | 10990 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 | 15514 | 2026-03-24 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 | 15514 | 2026-03-24 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  |  | 16356 | 2024-09-02 | -8856 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 | 15514 | 2026-03-25 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 | 15514 | 2026-03-19 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 | 15514 | 2026-03-24 | 16356 | 2029-03-04 | 14158 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 9022 | 2025-03-10 | 16356 | 2026-06-17 | 166 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 9022 | 2025-03-10 | 16356 | 2026-06-17 | 166 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  |  | 16356 | 2026-02-17 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  |  | 16356 | 2026-02-17 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 | 15677 | 2026-04-17 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 | 15677 | 2026-04-16 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 | 15677 | 2026-04-16 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 | 15677 | 2026-04-16 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 | 15677 | 2026-04-16 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 | 15677 | 2026-04-18 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 | 15677 | 2026-04-18 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 | 15677 | 2026-04-18 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 | 15677 | 2026-04-18 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 | 15677 | 2026-04-18 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 | 11489 | 2025-07-19 | 16356 | 2027-05-30 | 5133 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 | 15677 | 2026-04-24 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 | 13379 | 2025-10-29 | 16356 | 2027-10-12 | 7023 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  |  | 16356 | 2026-02-22 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 | 14982 | 2026-02-10 | 16356 | 2028-11-27 | 12793 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 | 15677 | 2026-04-20 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 | 15677 | 2026-04-17 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 | 15677 | 2026-04-18 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  |  | 16356 | 2026-02-20 | -1356 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  |  | 16356 | 2029-01-27 | 13644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 | 15677 | 2026-04-19 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 | 15677 | 2026-04-21 | 16356 | 2029-03-16 | 14321 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9020 | Alternator | 7500 | 12505 | 2025-09-14 | 16356 | 2027-02-13 | 3649 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 | 15514 | 2026-03-19 | 16356 | 2027-09-16 | 6658 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 | 15514 | 2026-03-19 | 16356 | 2027-09-16 | 6658 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 12684 | 2025-09-22 | 16356 | 2026-06-29 | 328 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 14374 | 2026-01-07 | 16356 | 2027-06-26 | 5518 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 | 14428 | 2026-01-12 | 16356 | 2027-01-02 | 3072 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 | 10874 | 2025-06-15 | 16356 | 2027-04-16 | 4518 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  |  | 16356 | 2029-01-27 | 13644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  |  | 16356 | 2027-02-12 | 3644 | WA | Iron Bridge
DR2118 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 | 14677 | 2026-01-24 | 16356 | 2028-01-12 | 8321 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  | 5866 | 2025-05-21 | 11357 | 2030-05-20 |  | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  |  | 11357 | 2025-09-13 | -3857 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  |  | 11357 | 2025-09-13 | -3857 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 | 8495 | 2025-10-23 | 11357 | 2028-08-14 | 12138 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 | 10987 | 2026-05-06 | 11357 | 2029-01-27 | 14630 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  |  | 11357 | 2029-10-22 | 18643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 11357 | 2025-09-13 | -3857 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0550 | Air End | 15000 | 10738 | 2026-04-20 | 11357 | 2029-01-11 | 14381 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 9907 | 2026-02-10 | 11357 | 2027-02-10 |  | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 10140 | 2026-02-22 | 11357 | 2026-08-22 | 1283 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 10140 | 2026-02-21 | 11357 | 2026-08-22 | 1283 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 10140 | 2026-02-22 | 11357 | 2026-08-22 | 1283 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 10140 | 2026-02-21 | 11357 | 2026-08-22 | 1283 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 | 8496 | 2025-10-23 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 | 8496 | 2025-10-23 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 | 8496 | 2025-10-23 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 | 8496 | 2025-10-23 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 | 8495 | 2025-10-22 | 11357 | 2027-04-02 | 4638 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 | 8608 | 2025-11-15 | 11357 | 2027-04-10 | 4751 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 11357 | 2031-08-20 | 28643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 8495 | 2025-10-21 | 11357 | 2026-07-26 | 888 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 718 | 2024-02-15 | 11357 | 2024-07-04 | -10389 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 | 8496 | 2025-10-20 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 | 8496 | 2025-10-20 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 | 8496 | 2025-10-21 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 | 8496 | 2025-10-24 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  |  | 11357 | 2029-10-22 | 18643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 8495 | 2025-10-21 | 11357 | 2026-04-01 | -862 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 10140 | 2026-02-24 | 11357 | 2027-02-04 | 3783 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 9252 | 2026-01-10 | 11357 | 2026-12-07 | 2895 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 | 17281 | 2026-02-08 | 11357 | 2030-03-23 | 20924 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 | 9676 | 2026-01-28 | 11357 | 2027-06-20 | 5819 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 8496 | 2025-10-22 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 8496 | 2025-10-23 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 | 10140 | 2026-02-23 | 11357 | 2028-01-04 | 8783 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 | 2871 | 2024-09-07 | 11357 | 2026-09-06 | 1514 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 | 10140 | 2026-02-23 | 11357 | 2028-12-02 | 13783 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 | 10738 | 2026-04-14 | 11357 | 2029-01-11 | 14381 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 | 10987 | 2026-05-06 | 11357 | 2029-01-27 | 14630 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 | 3166 | 2024-09-25 | 11357 | 2027-08-25 | 6809 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  |  | 11357 | 2029-10-22 | 18643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  |  | 11357 | 2027-01-26 | 3643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9020 | Alternator | 7500 | 8496 | 2025-10-25 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 | 8496 | 2025-10-27 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 | 8496 | 2025-10-20 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 8496 | 2025-10-21 | 11357 | 2026-08-12 | 1139 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 8496 | 2025-10-21 | 11357 | 2027-04-02 | 4639 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 | 4823 | 2025-02-26 | 11357 | 2026-02-06 | -1534 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 |  |  | 11357 | 2026-02-18 | -1357 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  |  | 11357 | 2029-10-22 | 18643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  |  | 11357 | 2027-12-25 | 8643 | WA | Iron Bridge
DR2119 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 | 10020 | 2026-02-17 | 11357 | 2027-12-27 | 8663 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-01-01 | 5862 | 2028-12-30 |  | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 | 4961 | 2026-04-16 | 5862 | 2029-02-28 | 14099 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  | 2024-11-09 | 5862 | 2031-02-15 | 24138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0550 | Air End | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 4020 | 2026-01-20 | 5862 | 2027-01-20 |  | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 | 2923 | 2025-10-29 | 5862 | 2026-04-27 | -439 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 | 2923 | 2025-10-29 | 5862 | 2026-04-27 | -439 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 | 2923 | 2025-10-29 | 5862 | 2026-04-27 | -439 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 | 2923 | 2025-10-29 | 5862 | 2026-04-27 | -439 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-23 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 5862 | 2033-01-29 | 34138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 | 4050 | 2026-02-04 | 5862 | 2026-10-13 | 1938 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 440 | 2024-12-16 | 5862 | 2025-05-24 | -5172 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  | 2024-11-09 | 5862 | 2031-02-15 | 24138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 | 4050 | 2026-02-04 | 5862 | 2026-06-10 | 188 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 | 4724.9 | 2026-03-18 | 5862 | 2027-02-28 | 3862.9 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 | 4724.9 | 2026-03-17 | 5862 | 2027-02-28 | 3862.9 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 | 2923 | 2025-11-02 | 5862 | 2028-10-06 | 12061 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 | 3184 | 2025-11-17 | 5862 | 2028-10-24 | 12322 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 | 5674 | 2026-05-12 | 5862 | 2027-11-01 | 7312 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 | 1458 | 2025-08-09 | 5862 | 2027-01-04 | 3096 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 |  | 2024-11-09 | 5862 | 2027-03-20 | 4138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 |  | 2024-11-09 | 5862 | 2027-03-20 | 4138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  | 2024-11-09 | 5862 | 2031-02-15 | 24138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  | 2024-11-09 | 5862 | 2028-03-11 | 9138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9020 | Alternator | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 |  | 2024-11-09 | 5862 | 2026-09-22 | 1638 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 | 4353 | 2026-02-26 | 5862 | 2026-11-22 | 2491 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 | 4020 | 2026-01-26 | 5862 | 2027-07-06 | 5658 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 |  | 2024-11-09 | 5862 | 2026-03-27 | -862 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 |  | 2024-11-09 | 5862 | 2027-03-20 | 4138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  | 2024-11-09 | 5862 | 2031-02-15 | 24138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  | 2024-11-09 | 5862 | 2029-03-03 | 14138 | WA | Iron Bridge
DR2120 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 |  | 2024-11-09 | 5862 | 2027-03-20 | 4138 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  | 138 | 2026-03-07 | 1675 | 2031-03-06 |  | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  | 2024-11-12 | 1675 | 2031-12-11 | 28325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0550 | Air End | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  | 138 | 2026-03-13 | 1675 | 2027-03-13 |  | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 |  | 2024-11-12 | 1675 | 2026-07-26 | 825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 |  | 2024-11-12 | 1675 | 2026-07-26 | 825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 |  | 2024-11-12 | 1675 | 2026-07-26 | 825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 |  | 2024-11-12 | 1675 | 2026-07-26 | 825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 1675 | 2033-11-25 | 38325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 |  | 2024-11-12 | 1675 | 2026-10-23 | 2075 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 | 140 | 2026-03-12 | 1675 | 2026-02-25 | -1285 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  | 2024-11-12 | 1675 | 2031-12-11 | 28325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 |  | 2024-11-12 | 1675 | 2026-06-20 | 325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 |  | 2024-11-12 | 1675 | 2027-01-21 | 3325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 |  | 2024-11-12 | 1675 | 2027-01-21 | 3325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 |  | 2024-11-12 | 1675 | 2028-01-13 | 8325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 |  | 2024-11-12 | 1675 | 2028-01-13 | 8325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-13 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  | 2024-11-12 | 1675 | 2031-12-11 | 28325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  | 2024-11-12 | 1675 | 2029-01-04 | 13325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9020 | Alternator | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 |  | 2024-11-12 | 1675 | 2026-11-10 | 2325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 |  | 2024-11-12 | 1675 | 2027-07-18 | 5825 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 |  | 2024-11-12 | 1675 | 2027-01-21 | 3325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 |  | 2024-11-12 | 1675 | 2028-01-13 | 8325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  | 2024-11-12 | 1675 | 2031-12-11 | 28325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  | 2024-11-12 | 1675 | 2029-12-27 | 18325 | WA | Iron Bridge
DR2121 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 |  | 2024-11-12 | 1675 | 2028-01-13 | 8325 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-01-01 | 153 | 2028-12-30 |  | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  | 2024-11-12 | 153 | 344640 | 29847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0550 | Air End | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  |  | 2024-11-12 | 153 | 2025-11-12 |  | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 |  | 2024-11-12 | 153 | 2090-08-30 | 2347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 |  | 2024-11-12 | 153 | 2090-08-30 | 2347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 |  | 2024-11-12 | 153 | 2090-08-30 | 2347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 |  | 2024-11-12 | 153 | 2090-08-30 | 2347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 153 | 2033-01-07 | 39847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 |  | 2024-11-12 | 153 | 2124-11-20 | 3597 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 |  | 2024-11-12 | 153 | 2029-01-22 | 97 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  | 2024-11-12 | 153 | 344640 | 29847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 |  | 2024-11-12 | 153 | 2076-12-21 | 1847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 |  | 2024-11-12 | 153 | 2159-02-10 | 4847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 |  | 2024-11-12 | 153 | 2159-02-10 | 4847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 |  | 2024-11-12 | 153 | 2296-01-03 | 9847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 |  | 2024-11-12 | 153 | 2296-01-03 | 9847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  | 2024-11-12 | 153 | 344640 | 29847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  | 2024-11-12 | 153 | 2432-11-25 | 14847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9020 | Alternator | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 |  | 2024-11-12 | 153 | 2131-09-25 | 3847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 |  | 2024-11-12 | 153 | 2227-07-24 | 7347 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 |  | 2024-11-12 | 153 | 2159-02-10 | 4847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 |  | 2024-11-12 | 153 | 2296-01-03 | 9847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  | 2024-11-12 | 153 | 344640 | 29847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  | 2024-11-12 | 153 | 244640 | 19847 | WA | Iron Bridge
DR2122 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 |  | 2024-11-12 | 153 | 2296-01-03 | 9847 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0033-PR | Water Tank - PRIMARY | 15000 |  |  | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0033-SC | Water Tank - SECONDARY | 15000 |  |  | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-08-15 | 808 | 2029-08-14 |  | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0101-L | Track Chain LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0101-R | Track Chain RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0104-L | Sprockets LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0104-R | Sprockets RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0105-L | Idler LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0105-R | Idler RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-1L | Track Roller 1 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-1R | Track Roller 1 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-2L | Track Roller 2 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-2R | Track Roller 2 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-3L | Track Roller 3 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-3R | Track Roller 3 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-4L | Track Roller 4 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-4R | Track Roller 4 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-5L | Track Roller 5 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-5R | Track Roller 5 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-6L | Track Roller 6 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-6R | Track Roller 6 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-7L | Track Roller 7 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-7R | Track Roller 7 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-8L | Track Roller 8 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-8R | Track Roller 8 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-9L | Track Roller 9 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0111-9R | Track Roller 9 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-0L | Track Roller 10 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-0R | Track Roller 10 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-1L | Track Roller 11 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-1R | Track Roller 11 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-2L | Track Roller 12 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-2R | Track Roller 12 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-3L | Track Roller 13 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-3R | Track Roller 13 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-4L | Track Roller 14 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0112-4R | Track Roller 14 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0121-L | Carrier Roller No 1 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0121-R | Carrier Roller No 1 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0122-L | Carrier Roller No 2 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0122-R | Carrier Roller No 2 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0123-L | Carrier Roller No 3 LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0123-R | Carrier Roller No 3 RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0134-L | Track Adjuster LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0134-R | Track Adjuster RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0140 | Equalizer Bar | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0405 | Mast | 30000 |  | 2024-11-12 | 808 | 2032-02-11 | 29192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0503 | Water Cannon | 7500 |  |  | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0550 | Air End | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0551 | Cooler Aircompressor | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0556 | Air Safety Valve |  |  | 2024-06-14 | 808 | 2025-06-14 |  | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0620-L | Pulldown Rope LEFT | 2500 |  | 2024-11-12 | 808 | 2026-09-26 | 1692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0620-R | Pulldown Rope RIGHT | 2500 |  | 2024-11-12 | 808 | 2026-09-26 | 1692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0621-L | Pullback Rope LEFT | 2500 |  | 2024-11-12 | 808 | 2026-09-26 | 1692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0621-R | Pullback Rope RIGHT | 2500 |  | 2024-11-12 | 808 | 2026-09-26 | 1692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0622-LL | Pulldown Sheave LOWER LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0622-LU | Pulldown Sheave UPPER LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0622-RL | Pulldown Sheave LOWER RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0622-RU | Pulldown Sheave UPPER RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0622-TL | Pulldown Sheave TRAVEL LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0622-TR | Pulldown Sheave TRAVEL RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0623-LL | Pullback Sheave LOWER LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0623-LU | Pullback Sheave UPPER LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0623-RL | Pullback Sheave LOWER RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0623-RU | Pullback Sheave UPPER RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0623-TL | Pullback Sheave TRAVEL LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0623-TR | Pullback Sheave TRAVEL RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N0674 | Vehicle Loading Crane | 40000 |  |  | 808 | 2034-01-25 | 39192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1000 | Engine | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1002 | Engine Valve Adj | 3750 |  | 2024-11-12 | 808 | 2026-12-24 | 2942 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1002-01 | Engine Valve Adj - Initial | 250 |  | 2024-11-12 | 808 | 2026-04-18 | -558 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1100-L | Turbo Primary LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1100-R | Turbo Primary RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1202 | Fuel Transfer Pump | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1210 | Fuel Injectors | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1300 | Cooling Sys Service | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1301 | Water Pump | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1310 | Radiator | 30000 |  | 2024-11-12 | 808 | 2032-02-11 | 29192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1312-L | Aftercooler Core - LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1312-R | Aftercooler Core - RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1320 | Cooling Fan Engine | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N1490 | Cam Shaft Inspection | 2000 |  | 2024-11-12 | 808 | 2026-08-21 | 1192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N2090 | Drv Coupling | 5000 |  | 2024-11-12 | 808 | 2027-03-23 | 4192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N2435 | Drv Coupling Engine/Pump Drive | 5000 |  | 2024-11-12 | 808 | 2027-03-23 | 4192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N3320 | Pump Drive Box | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N3340 | Rotary Head | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N5000-L | Final Drive LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N5000-R | Final Drive RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7008-01 | Pump Hydraulic POS 1 | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7008-02 | Pump Hydraulic POS 2 | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7032 | Pump Cooler Fan Hyd | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7041 | Pump Cooling Fan Engine | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7044 | Cooler Fan Hyd | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7068 | Pump Auxiliary | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7100 | Pump Charge | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7151 | Pump Water Injection (Bean) | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7201 | Hyd Motor Air Con | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7234-L | Hyd Motor Cooler Fan LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7234-R | Hyd Motor Cooler Fan RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7310-L | Hyd Motor Rotation LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7310-R | Hyd Motor Rotation RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7330-L | Hyd Motor Travel LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7330-R | Hyd Motor Travel RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7460 | Hyd Cyl Feed | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7467-LL | Hyd Cyl Feed Rope Tension LL | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7467-LU | Hyd Cyl Feed Rope Tension LU | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7467-RL | Hyd Cyl Feed Rope Tension RL | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7467-RU | Hyd Cyl Feed Rope Tension RU | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7521 | Hyd Cyl Pipe Positioner Swing | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7522 | Hyd Cyl Pipe Positioner Clamp | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7524 | Hyd Cyl Carousel Lock | 15000 |  |  | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7524-FR | Hyd Cyl Carousel Lock - FRONT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7524-RE | Hyd Cyl Carousel Lock - REAR | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7527-F | Hyd Cyl Dust Curtain FRONT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7527-RE | Hyd Cyl Dust Curtain REAR | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7528-L | Hyd Cyl Hyd Op Bit Basket LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7528-R | Hyd Cyl Hyd Op Bit Basket RIGH | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7541 | Hyd Cyl Access Ladder | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7570-LF | Hyd Cyl Levelling Jack LFT FRO | 10000 |  | 2024-11-12 | 808 | 2028-03-15 | 9192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7570-LR | Hyd Cyl Levelling Jack LFT REA | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7570-RF | Hyd Cyl Levelling Jack RHT FRO | 10000 |  | 2024-11-12 | 808 | 2028-03-15 | 9192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7570-RR | Hyd Cyl Levelling Jack RHT REA | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7575 | Hyd Cyl Breakout Wrench Rotate | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7581 | Hyd Cyl Breakout Wrench Swing | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7582 | Hyd Cyl Breakout Wrench Clamp | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7584 | Hyd Cyl Deckwrench | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7587 | Hyd Cyl Deck Inspection Hatch | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7592-L | Hyd Cyl Mast Raise LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7592-R | Hyd Cyl Mast Raise RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7595-L | Hyd Cyl Mast Lock LEFT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7595-R | Hyd Cyl Mast Lock RIGHT | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7598-LO | Hyd Cyl Carousel Swing LOWER | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7598-UP | Hyd Cyl Carousel Swing UPPER | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7600-LL | Control Valve LEFT LOWER | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7600-LU | Control Valve LEFT UPPER | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7600-LW | Control Valve LOWER | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7608 | Control Valve Jack/Mast Raise | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7610 | Hyd Cooler Core | 30000 |  | 2024-11-12 | 808 | 2032-02-11 | 29192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N7669 | Hyd Cyl Rod Catcher | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N8995 | Operator Seat | 15000 |  | 2024-11-12 | 808 | 2029-03-07 | 14192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9020 | Alternator | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9050-L | Starter Motor LEFT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9050-R | Starter Motor RIGHT | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9500 | Air Cond'r-Serv | 4000 |  | 2024-11-12 | 808 | 2027-01-11 | 3192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9501 | A/C Compressor | 7500 |  | 2024-11-12 | 808 | 2027-09-18 | 6692 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9701 | LiDAR Detection System | 5000 |  | 2024-11-12 | 808 | 2027-03-23 | 4192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9703 | Inertial Measurement Unit | 10000 |  | 2024-11-12 | 808 | 2028-03-15 | 9192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9711 | GNSS Receivers | 30000 |  | 2024-11-12 | 808 | 2032-02-11 | 29192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9720 | Autonomy Cabinet | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9731 | AS Electrical Harness | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9735-CA | AS Hardware - CABIN | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9735-DE | AS Hardware - DECK | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9735-FD | AS Hardware - FIELD | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9735-IO | AS Hardware - I/O | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9735-JC | AS Hardware - JUMPER CONNECTOR | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9735-MA | AS Hardware - MAST | 20000 |  | 2024-11-12 | 808 | 2030-02-27 | 19192 | WA | Iron Bridge
DR2123 | Cat MD6310 - ADS | N9760 | Fisheye Camera | 10000 |  | 2024-11-12 | 808 | 2028-03-15 | 9192 | WA | Iron Bridge
DU1047 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 48692 | 2018-07-27 | 67572 | 2023-07-26 |  | WA | Hazelmere
DU1047 | Cat 785C | N0200 | A Frame Bearing | 20000 | 63851 | 2021-09-01 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 63851 | 2021-09-03 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N1000 | Engine | 20000 | 52669 | 2019-05-24 | 67572 | 2027-05-03 | 5097 | WA | Hazelmere
DU1047 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 52669 | 2019-05-24 | 67572 | 2024-05-31 | -10903 | WA | Hazelmere
DU1047 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 52910 | 2019-06-20 | 67572 | 2023-09-27 | -14612 | WA | Hazelmere
DU1047 | Cat 785C | N1004 | Engine Midlife | 10000 | 63851 | 2021-08-28 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 63851 | 2021-08-28 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 63851 | 2021-08-28 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 63851 | 2021-08-31 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1301 | Water Pump | 20000 | 52669 | 2019-05-24 | 67572 | 2027-05-03 | 5097 | WA | Hazelmere
DU1047 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 52669 | 2019-05-24 | 67572 | 2027-05-03 | 5097 | WA | Hazelmere
DU1047 | Cat 785C | N1310 | Radiator | 20000 | 52669 | 2019-05-28 | 67572 | 2027-05-03 | 5097 | WA | Hazelmere
DU1047 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 63851 | 2021-08-31 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 63851 | 2021-05-31 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1420 | Air Compressor | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N1430 | Air Starter | 10000 | 52669 | 2019-05-24 | 67572 | 2025-07-05 | -4903 | WA | Hazelmere
DU1047 | Cat 785C | N2000 | Transmission | 20000 | 54617 | 2019-11-14 | 67572 | 2027-09-10 | 7045 | WA | Hazelmere
DU1047 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 54617 | 2019-11-14 | 67572 | 2027-09-10 | 7045 | WA | Hazelmere
DU1047 | Cat 785C | N2004 | Transmission Pump | 20000 | 54617 | 2019-11-14 | 67572 | 2027-09-10 | 7045 | WA | Hazelmere
DU1047 | Cat 785C | N2050 | Torque Convertor | 20000 | 67650 | 2024-01-09 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 67650 | 2024-04-02 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 67650 | 2024-04-02 | 67572 | 2028-03-30 | 10078 | WA | Hazelmere
DU1047 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 63851 | 2021-09-01 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N3320 | Pump Drive Box | 20000 | 63851 | 2021-09-01 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N4000 | Bevel Gear | 20000 | 54617 | 2019-11-14 | 67572 | 2027-09-10 | 7045 | WA | Hazelmere
DU1047 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 67650 | 2023-12-28 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 67650 | 2023-12-29 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 59789 | 2020-11-01 | 67572 | 2028-08-19 | 12217 | WA | Hazelmere
DU1047 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 63631 | 2021-08-10 | 67572 | 2029-05-03 | 16059 | WA | Hazelmere
DU1047 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 67650 | 2023-12-14 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 63851 | 2021-08-30 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 67650 | 2023-12-14 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 63851 | 2021-08-30 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 67650 | 2024-01-03 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 63851 | 2021-09-01 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 63851 | 2021-09-02 | 67572 | 2027-07-21 | 6279 | WA | Hazelmere
DU1047 | Cat 785C | N7037 | Pump Conv P/Brake Release | 10000 | 67650 | 2024-01-09 | 67572 | 2028-03-30 | 10078 | WA | Hazelmere
DU1047 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 54224 | 2019-10-16 | 67572 | 2027-08-14 | 6652 | WA | Hazelmere
DU1047 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 63851 | 2021-09-01 | 67572 | 2033-01-10 | 36279 | WA | Hazelmere
DU1047 | Cat 785C | N7120 | Pump Steering | 20000 | 63851 | 2021-09-01 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 67650 | 2023-12-11 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 67650 | 2023-12-13 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N7605 | Steering Hmu | 20000 | 48547 | 2018-07-06 | 67572 | 2026-08-01 | 975 | WA | Hazelmere
DU1047 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 67650 | 2024-04-09 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 67650 | 2024-04-09 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  | 2011-07-21 | 67572 | 2018-08-20 | -42572 | WA | Hazelmere
DU1047 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 67650 | 2023-12-14 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 63851 | 2021-08-30 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 67650 | 2023-12-07 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 67650 | 2023-12-07 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 67650 | 2023-12-12 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 67650 | 2023-12-12 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 67650 | 2023-12-07 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 67650 | 2023-12-12 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8140 | Steering Y Piece | 20000 | 67650 | 2023-12-12 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 52669 | 2019-05-28 | 67572 | 2027-05-03 | 5097 | WA | Hazelmere
DU1047 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 63851 | 2021-08-30 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 67650 | 2023-12-12 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 67650 | 2023-12-27 | 67572 | 2030-01-26 | 20078 | WA | Hazelmere
DU1047 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 67650 | 2023-12-27 | 67572 | 2030-12-25 | 25078 | WA | Hazelmere
DU1047 | Cat 785C | N8501 | Ball Stud Crack Test |  | 51474 | 2019-03-10 | 67572 | 2019-09-08 |  | WA | Hazelmere
DU1047 | Cat 785C | N8995 | Operator Seat | 6000 | 63851 | 2021-09-04 | 67572 | 2026-10-27 | 2279 | WA | Hazelmere
DU1047 | Cat 785C | N8999 | Cab Upgrade | 25000 |  | 2011-07-21 | 67572 | 2018-08-20 | -42572 | WA | Hazelmere
DU1047 | Cat 785C | N9020 | Alternator | 10000 | 67650 | 2024-01-02 | 67572 | 2028-03-30 | 10078 | WA | Hazelmere
DU1047 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 67650 | 2024-01-02 | 67572 | 2027-05-02 | 5078 | WA | Hazelmere
DU1047 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 63851 | 2021-09-01 | 67572 | 2029-05-17 | 16279 | WA | Hazelmere
DU1047 | Cat 785C | N9501 | A/C Compressor | 10000 | 51787 | 2019-03-31 | 67572 | 2025-05-07 | -5785 | WA | Hazelmere
DU1047 | Cat 785C | N9998 | Extended Life Rebuild | 45000 | 45000 | 2011-07-21 | 67572 | 2030-07-01 | 22428 | WA | Hazelmere
DU1047 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-07-21 | 67572 | 2025-12-08 | -2572 | WA | Hazelmere
DU1047 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-07-21 | 67572 | 2029-08-02 | 17428 | WA | Hazelmere
DZ1757 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  | 45570.2 | 2023-10-11 | 55934 | 2028-10-09 |  | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0101-L | Track Chain LEFT | 6000 | 37177 | 2026-01-10 | 55934 | 2023-10-26 | -12757 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0101-R | Track Chain RIGHT | 6000 | 55250 | 2026-01-09 | 55934 | 2027-06-26 | 5316 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0102-L | Trk Chn Pin & Bush Trn LEFT | 3000 | 37177 | 2026-01-10 | 55934 | 2023-03-18 | -15757 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 3000 | 55250 | 2026-01-09 | 55934 | 2026-11-16 | 2316 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0103-L | Track Plates LEFT | 1500 | 37177 | 2026-01-10 | 55934 | 2022-11-27 | -17257 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0103-R | Track Plates RIGHT | 1500 | 55250 | 2026-01-09 | 55934 | 2026-07-27 | 816 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0104-L | Sprockets LEFT | 6000 | 53699 | 2025-09-24 | 55934 | 2027-03-03 | 3765 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0104-R | Sprockets RIGHT | 6000 | 53699 | 2025-09-24 | 55934 | 2027-03-03 | 3765 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0105-LF | Idler LFT FRONT | 9000 | 55500 | 2026-01-27 | 55934 | 2028-02-22 | 8566 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0105-LR | Idler LFT REAR | 9000 | 55500 | 2026-01-27 | 55934 | 2028-02-22 | 8566 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0105-RF | Idler RHT FRONT | 9000 | 55500 | 2026-01-27 | 55934 | 2028-02-22 | 8566 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0105-RR | Idler RHT REAR | 9000 | 55500 | 2026-01-27 | 55934 | 2028-02-22 | 8566 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0121-L | Carrier Roller No 1 LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0121-R | Carrier Roller No 1 RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0130-L | Track Frame LEFT | 18000 | 48168 | 2024-06-25 | 55934 | 2028-06-24 | 10234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0130-R | Track Frame RIGHT | 18000 | 48168 | 2024-06-25 | 55934 | 2028-06-24 | 10234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0134-L | Track Adjuster LEFT | 18000 | 48168 | 2024-06-25 | 55934 | 2028-06-24 | 10234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0134-R | Track Adjuster RIGHT | 18000 | 48168 | 2024-06-25 | 55934 | 2028-06-24 | 10234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0139-L | Track Frame Mid Life LEFT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0139-R | Track Frame Mid Life RIGHT | 9000 | 48168 | 2024-06-25 | 55934 | 2026-08-27 | 1234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0140 | Equalizer Bar | 9000 | 52219 | 2025-06-07 | 55934 | 2027-06-23 | 5285 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0145 | Pivot Shaft Brgs | 18000 | 48168 | 2024-06-24 | 55934 | 2028-06-24 | 10234 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N0520 | Pre Lube Pump | 15000 | 49989 | 2024-12-11 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1000 | Engine | 15000 | 49989 | 2024-12-11 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1002 | Engine Valve Adj | 4000 | 54081 | 2025-10-21 | 55934 | 2026-11-03 | 2147 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1002-01 | Engine Valve Adj - Initial | 500 | 49989 | 2025-01-25 | 55934 | 2025-04-20 | -5445 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1004 | Engine Midlife | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1100-L | Turbo Primary LEFT | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1100-R | Turbo Primary RIGHT | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1202 | Fuel Transfer Pump | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1300 | Cooling Sys Service | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1310 | Radiator | 15000 | 49989 | 2024-12-10 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1312-L | Aftercooler Core - LEFT | 15000 | 49989 | 2024-12-10 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1312-R | Aftercooler Core - RIGHT | 15000 | 49989 | 2024-12-10 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N1490 | Cam Shaft Inspection | 2000 | 54081 | 2025-10-21 | 55934 | 2026-06-08 | 147 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N2000 | Transmission | 15000 | 45863 | 2023-11-12 | 55934 | 2027-05-28 | 4929 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N2020 | Powertrain Pump | 15000 | 52941 | 2025-07-30 | 55934 | 2028-11-02 | 12007 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N2050 | Torque Convertor | 15000 | 49989 | 2024-12-11 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N2450 | Drv Cpling Fan Pump-Trans Pump | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N3016 | Drv Shaft Fan Pump-Trans Pump | 15000 | 49989 | 2024-12-11 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N3028 | Drive Shaft T/C - Trans | 15000 | 52941 | 2025-07-30 | 55934 | 2028-11-02 | 12007 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N3029 | Uni's T/C - Trans | 7500 | 52941 | 2025-07-30 | 55934 | 2027-04-27 | 4507 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N4000 | Bevel Gear | 15000 | 45863 | 2023-11-12 | 55934 | 2027-05-28 | 4929 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N4110-L | Steering Clutch/Brk LEFT | 15000 | 53012 | 2025-08-10 | 55934 | 2028-11-08 | 12078 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N4110-R | Steering Clutch/Brk RIGHT | 15000 | 43989 | 2023-05-28 | 55934 | 2027-01-09 | 3055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N5000-L | Final Drive LEFT | 15000 | 45863 | 2023-11-12 | 55934 | 2027-05-28 | 4929 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N5000-R | Final Drive RIGHT | 15000 | 43989 | 2023-05-29 | 55934 | 2027-01-09 | 3055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N6360 | Brake Control Valve | 30000 |  |  | 55934 | 2021-02-22 | -25934 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7041 | Pump Cooling Fan Engine | 15000 | 44804 | 2023-07-28 | 55934 | 2027-03-11 | 3870 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7070 | Pump Implement | 15000 | 52941 | 2025-07-30 | 55934 | 2028-11-02 | 12007 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7232 | Hyd Motor Engine Fan | 15000 | 49989 | 2024-12-10 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7420-L | Hyd Cyl Blade Lift LEFT | 12000 | 47639 | 2024-04-28 | 55934 | 2027-02-26 | 3705 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7420-R | Hyd Cyl Blade Lift RIGHT | 12000 | 50303 | 2025-01-05 | 55934 | 2027-09-12 | 6369 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7421-L | Hyd Cyl Blade Tilt LEFT | 15000 | 47439 | 2024-04-14 | 55934 | 2027-09-22 | 6505 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 15000 | 48866 | 2024-09-04 | 55934 | 2028-01-06 | 7932 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7510-L | Hyd Cyl Ripper Lift LEFT | 25000 | 48001 | 2024-06-07 | 55934 | 2029-11-12 | 17067 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 25000 | 44804 | 2023-08-02 | 55934 | 2029-03-20 | 13870 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 25000 | 40765 | 2022-08-25 | 55934 | 2028-05-25 | 9831 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 25000 | 40768 | 2022-08-26 | 55934 | 2028-05-25 | 9834 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7600 | Control Valve | 30000 | 29354 | 2019-01-11 | 55934 | 2027-02-05 | 3420 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N7610 | Hyd Cooler Core | 15000 | 49989 | 2024-12-10 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N8000 | Main Frame/Chassis | 30000 |  |  | 55934 | 2021-02-22 | -25934 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N8995 | Operator Seat | 6000 | 53582 | 2025-09-15 | 55934 | 2027-02-22 | 3648 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9020 | Alternator | 7500 | 49989 | 2025-01-14 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9050 | Starter Motor | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9500 | Air Cond'r-Serv | 5000 | 55500 | 2026-01-26 | 55934 | 2027-05-01 | 4566 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9500-MA | Air Cond'r-Serv - MAJOR | 15000 | 49989 | 2024-12-11 | 55934 | 2028-03-29 | 9055 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9501 | A/C Compressor | 7500 | 49989 | 2024-12-11 | 55934 | 2026-09-20 | 1555 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9502 | A/C Condenser | 15000 | 55500 | 2026-01-26 | 55934 | 2029-05-11 | 14566 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9998 | Extended Life Rebuild | 30000 |  | 2011-02-10 | 55934 | 2021-02-22 | -25934 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9998-01 | Extended Life Rebuild ONE | 45000 |  | 2011-02-10 | 55934 | 2024-03-09 | -10934 | WA | Norrish Earthmoving
DZ1757 | Cat D10T | N9998-02 | Extended Life Rebuild TWO | 60000 |  | 2011-02-10 | 55934 | 2027-03-25 | 4066 | WA | Norrish Earthmoving
DZ1937 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  | 42942 | 2023-12-01 | 50673 | 2028-11-29 |  | WA | Iron Bridge
DZ1937 | Cat D10T | N0101-L | Track Chain LEFT | 8000 | 49269 | 2026-02-25 | 50673 | 2027-09-11 | 6596 | WA | Iron Bridge
DZ1937 | Cat D10T | N0101-R | Track Chain RIGHT | 8000 | 49269 | 2026-02-24 | 50673 | 2027-09-11 | 6596 | WA | Iron Bridge
DZ1937 | Cat D10T | N0102-L | Trk Chn Pin & Bush Trn LEFT | 4000 | 49269 | 2026-02-25 | 50673 | 2026-11-29 | 2596 | WA | Iron Bridge
DZ1937 | Cat D10T | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 4000 | 49269 | 2026-02-24 | 50673 | 2026-11-29 | 2596 | WA | Iron Bridge
DZ1937 | Cat D10T | N0103-L | Track Plates LEFT | 8000 | 49269 | 2026-04-06 | 50673 | 2027-09-11 | 6596 | WA | Iron Bridge
DZ1937 | Cat D10T | N0103-R | Track Plates RIGHT | 8000 | 49784 | 2026-04-06 | 50673 | 2027-10-18 | 7111 | WA | Iron Bridge
DZ1937 | Cat D10T | N0104-L | Sprockets LEFT | 4000 | 42942 | 2023-12-01 | 50673 | 2025-09-03 | -3731 | WA | Iron Bridge
DZ1937 | Cat D10T | N0104-R | Sprockets RIGHT | 4000 | 42942 | 2023-12-01 | 50673 | 2025-09-03 | -3731 | WA | Iron Bridge
DZ1937 | Cat D10T | N0105-LF | Idler LFT FRONT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0105-LR | Idler LFT REAR | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0105-RF | Idler RHT FRONT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0105-RR | Idler RHT REAR | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 8000 | 40715 | 2021-08-13 | 50673 | 2026-01-08 | -1958 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 8000 | 40715 | 2021-08-13 | 50673 | 2026-01-08 | -1958 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 8000 | 40715 | 2021-08-13 | 50673 | 2026-01-08 | -1958 | WA | Iron Bridge
DZ1937 | Cat D10T | N0121-L | Carrier Roller No 1 LEFT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0121-R | Carrier Roller No 1 RIGHT | 8000 | 42942 | 2023-12-01 | 50673 | 2026-06-16 | 269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0130-L | Track Frame LEFT | 30000 | 42942 | 2023-12-01 | 50673 | 2030-10-05 | 22269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0130-R | Track Frame RIGHT | 30000 | 42942 | 2023-12-01 | 50673 | 2030-10-05 | 22269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0134-L | Track Adjuster LEFT | 15000 | 42133 | 2023-02-24 | 50673 | 2027-09-01 | 6460 | WA | Iron Bridge
DZ1937 | Cat D10T | N0134-R | Track Adjuster RIGHT | 15000 | 42133 | 2023-02-24 | 50673 | 2027-09-01 | 6460 | WA | Iron Bridge
DZ1937 | Cat D10T | N0139-L | Track Frame Mid Life LEFT | 15000 | 42942 | 2023-12-01 | 50673 | 2027-10-29 | 7269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0139-R | Track Frame Mid Life RIGHT | 15000 | 42942 | 2023-12-01 | 50673 | 2027-10-29 | 7269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0140 | Equalizer Bar | 15000 | 49221 | 2026-03-02 | 50673 | 2029-01-20 | 13548 | WA | Iron Bridge
DZ1937 | Cat D10T | N0145 | Pivot Shaft Brgs | 15000 | 42942 | 2023-12-01 | 50673 | 2027-10-29 | 7269 | WA | Iron Bridge
DZ1937 | Cat D10T | N0520 | Pre Lube Pump | 15000 | 47690 | 2025-10-16 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N1000 | Engine | 15000 | 47698 | 2025-10-20 | 50673 | 2028-10-03 | 12025 | WA | Iron Bridge
DZ1937 | Cat D10T | N1002 | Engine Valve Adj | 4000 | 47698 | 2025-10-20 | 50673 | 2026-08-09 | 1025 | WA | Iron Bridge
DZ1937 | Cat D10T | N1002-01 | Engine Valve Adj - Initial | 500 | 48149 | 2025-11-22 | 50673 | 2026-01-03 | -2024 | WA | Iron Bridge
DZ1937 | Cat D10T | N1004 | Engine Midlife | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N1100-L | Turbo Primary LEFT | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N1100-R | Turbo Primary RIGHT | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N1202 | Fuel Transfer Pump | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N1300 | Cooling Sys Service | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N1310 | Radiator | 15000 | 47690 | 2025-10-14 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N1312-L | Aftercooler Core - LEFT | 15000 | 47690 | 2025-10-14 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N1312-R | Aftercooler Core - RIGHT | 15000 | 47690 | 2025-10-14 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N1490 | Cam Shaft Inspection | 2000 | 47698 | 2025-10-20 | 50673 | 2026-03-19 | -975 | WA | Iron Bridge
DZ1937 | Cat D10T | N2000 | Transmission | 15000 | 43599 | 2024-11-19 | 50673 | 2027-12-15 | 7926 | WA | Iron Bridge
DZ1937 | Cat D10T | N2020 | Powertrain Pump | 15000 | 42942 | 2023-12-01 | 50673 | 2027-10-29 | 7269 | WA | Iron Bridge
DZ1937 | Cat D10T | N2050 | Torque Convertor | 15000 | 47690 | 2025-10-15 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N2450 | Drv Cpling Fan Pump-Trans Pump | 7500 | 47690 | 2025-10-17 | 50673 | 2027-04-16 | 4517 | WA | Iron Bridge
DZ1937 | Cat D10T | N3016 | Drv Shaft Fan Pump-Trans Pump | 15000 | 47690 | 2025-10-17 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N3028 | Drive Shaft T/C - Trans | 15000 | 47690 | 2025-10-17 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N3029 | Uni's T/C - Trans | 7500 | 47690 | 2025-10-17 | 50673 | 2027-04-16 | 4517 | WA | Iron Bridge
DZ1937 | Cat D10T | N4000 | Bevel Gear | 15000 | 43599 | 2024-11-19 | 50673 | 2027-12-15 | 7926 | WA | Iron Bridge
DZ1937 | Cat D10T | N4110-L | Steering Clutch/Brk LEFT | 15000 | 43040 | 2024-10-06 | 50673 | 2027-11-05 | 7367 | WA | Iron Bridge
DZ1937 | Cat D10T | N4110-R | Steering Clutch/Brk RIGHT | 15000 | 41682 | 2022-10-29 | 50673 | 2027-07-31 | 6009 | WA | Iron Bridge
DZ1937 | Cat D10T | N5000-L | Final Drive LEFT | 15000 | 43040 | 2024-10-06 | 50673 | 2027-11-05 | 7367 | WA | Iron Bridge
DZ1937 | Cat D10T | N5000-R | Final Drive RIGHT | 15000 | 41682 | 2022-10-29 | 50673 | 2027-07-31 | 6009 | WA | Iron Bridge
DZ1937 | Cat D10T | N6360 | Brake Control Valve | 30000 |  |  | 50673 | 2022-05-12 | -20673 | WA | Iron Bridge
DZ1937 | Cat D10T | N7041 | Pump Cooling Fan Engine | 15000 | 47690 | 2025-10-14 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N7070 | Pump Implement | 15000 | 48149 | 2025-11-30 | 50673 | 2028-11-04 | 12476 | WA | Iron Bridge
DZ1937 | Cat D10T | N7232 | Hyd Motor Engine Fan | 15000 | 47690 | 2025-10-14 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N7420-L | Hyd Cyl Blade Lift LEFT | 12000 | 46908 | 2025-10-03 | 50673 | 2028-01-06 | 8235 | WA | Iron Bridge
DZ1937 | Cat D10T | N7420-R | Hyd Cyl Blade Lift RIGHT | 12000 | 49819 | 2026-04-10 | 50673 | 2028-08-01 | 11146 | WA | Iron Bridge
DZ1937 | Cat D10T | N7421-L | Hyd Cyl Blade Tilt LEFT | 15000 | 45063 | 2025-04-25 | 50673 | 2028-03-29 | 9390 | WA | Iron Bridge
DZ1937 | Cat D10T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 15000 | 45063 | 2025-04-25 | 50673 | 2028-03-29 | 9390 | WA | Iron Bridge
DZ1937 | Cat D10T | N7510-L | Hyd Cyl Ripper Lift LEFT | 25000 | 45063 | 2025-04-25 | 50673 | 2030-03-13 | 19390 | WA | Iron Bridge
DZ1937 | Cat D10T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 25000 | 45063 | 2025-04-25 | 50673 | 2030-03-13 | 19390 | WA | Iron Bridge
DZ1937 | Cat D10T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 25000 | 45063 | 2025-04-25 | 50673 | 2030-03-13 | 19390 | WA | Iron Bridge
DZ1937 | Cat D10T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 25000 | 45063 | 2025-04-25 | 50673 | 2030-03-13 | 19390 | WA | Iron Bridge
DZ1937 | Cat D10T | N7600 | Control Valve | 30000 | 42942 | 2023-12-01 | 50673 | 2030-10-05 | 22269 | WA | Iron Bridge
DZ1937 | Cat D10T | N7610 | Hyd Cooler Core | 15000 | 47690 | 2025-10-14 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N8000 | Main Frame/Chassis | 30000 | 31158 | 2018-09-26 | 50673 | 2028-06-15 | 10485 | WA | Iron Bridge
DZ1937 | Cat D10T | N8995 | Operator Seat | 6000 | 49381 | 2026-03-08 | 50673 | 2027-04-29 | 4708 | WA | Iron Bridge
DZ1937 | Cat D10T | N9020 | Alternator | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N9050 | Starter Motor | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N9500 | Air Cond'r-Serv | 5000 | 47690 | 2025-10-19 | 50673 | 2026-10-19 | 2017 | WA | Iron Bridge
DZ1937 | Cat D10T | N9500-MA | Air Cond'r-Serv - MAJOR | 15000 | 47690 | 2025-10-19 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N9501 | A/C Compressor | 7500 | 47698 | 2025-10-20 | 50673 | 2027-04-16 | 4525 | WA | Iron Bridge
DZ1937 | Cat D10T | N9502 | A/C Condenser | 15000 | 47690 | 2025-10-17 | 50673 | 2028-10-02 | 12017 | WA | Iron Bridge
DZ1937 | Cat D10T | N9998 | Extended Life Rebuild | 30000 | 36631 | 2020-06-30 | 50673 | 2029-07-11 | 15958 | WA | Iron Bridge
DZ1937 | Cat D10T | N9998-01 | Extended Life Rebuild ONE | 45000 |  | 2013-12-17 | 50673 | 2025-04-18 | -5673 | WA | Iron Bridge
DZ1937 | Cat D10T | N9998-02 | Extended Life Rebuild TWO | 60000 |  | 2013-12-17 | 50673 | 2028-03-24 | 9327 | WA | Iron Bridge
DZ3420 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-05-25 | 23174 | 2028-05-23 |  | WA | Iron Bridge
DZ3420 | Cat D10T | N0101-L | Track Chain LEFT | 8000 | 22880 | 2026-05-07 | 23174 | 2027-11-29 | 7706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0101-R | Track Chain RIGHT | 8000 | 22880 | 2026-05-07 | 23174 | 2027-11-29 | 7706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0102-L | Trk Chn Pin & Bush Trn LEFT | 4000 | 22880 | 2026-05-07 | 23174 | 2027-02-17 | 3706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 4000 | 22880 | 2026-05-07 | 23174 | 2027-02-17 | 3706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0103-L | Track Plates LEFT | 8000 | 22880 | 2026-05-07 | 23174 | 2027-11-29 | 7706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0103-R | Track Plates RIGHT | 8000 | 22880 | 2026-05-07 | 23174 | 2027-11-29 | 7706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0104-L | Sprockets LEFT | 4000 | 15305 | 2025-05-28 | 23174 | 2025-08-25 | -3869 | WA | Iron Bridge
DZ3420 | Cat D10T | N0104-R | Sprockets RIGHT | 4000 | 15305 | 2025-05-28 | 23174 | 2025-08-25 | -3869 | WA | Iron Bridge
DZ3420 | Cat D10T | N0105-LF | Idler LFT FRONT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0105-LR | Idler LFT REAR | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0105-RF | Idler RHT FRONT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0105-RR | Idler RHT REAR | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 8000 | 22880 | 2026-05-08 | 23174 | 2027-11-29 | 7706 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0121-L | Carrier Roller No 1 LEFT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0121-R | Carrier Roller No 1 RIGHT | 8000 | 15305 |  | 23174 | 2026-06-06 | 131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0130-L | Track Frame LEFT | 30000 | 15305 |  | 23174 | 2030-09-25 | 22131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0130-R | Track Frame RIGHT | 30000 | 15305 |  | 23174 | 2030-09-25 | 22131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0134-L | Track Adjuster LEFT | 15000 | 15305 |  | 23174 | 2027-10-19 | 7131 | WA | Iron Bridge
DZ3420 | Cat D10T | N0134-R | Track Adjuster RIGHT | 15000 | 15305 |  | 23174 | 2027-10-19 | 7131 | WA | Iron Bridge
DZ3429 | Cat D10 | N0050 | Blade Assembly | 20000 |  | 2025-04-01 | 4963.4 | 2032-02-03 | 15036.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-04-01 | 4963.4 | 2030-03-31 |  | WA | McPhee Creek
DZ3429 | Cat D10 | N0100-L | Track Group LEFT | 2000 | 2849 | 2025-11-23 | 4963.4 | 2026-05-12 | -114.4 | WA | McPhee Creek
DZ3429 | Cat D10 | N0100-R | Track Group RIGHT | 2000 | 2849 | 2025-11-23 | 4963.4 | 2026-05-12 | -114.4 | WA | McPhee Creek
DZ3429 | Cat D10 | N0104-L | Sprockets LEFT | 5000 |  | 2025-04-01 | 4963.4 | 2026-06-02 | 36.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0104-R | Sprockets RIGHT | 5000 |  | 2025-04-01 | 4963.4 | 2026-06-02 | 36.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0105-LF | Idler LFT FRONT | 12000 |  | 2025-04-01 | 4963.4 | 2029-01-24 | 7036.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0105-LR | Idler LFT REAR | 12000 |  | 2025-04-01 | 4963.4 | 2029-01-24 | 7036.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0105-RF | Idler RHT FRONT | 12000 |  | 2025-04-01 | 4963.4 | 2029-01-24 | 7036.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0105-RR | Idler RHT REAR | 12000 |  | 2025-04-01 | 4963.4 | 2029-01-24 | 7036.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-1L | Track Roller 1 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-1R | Track Roller 1 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-2L | Track Roller 2 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-2R | Track Roller 2 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-3L | Track Roller 3 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-3R | Track Roller 3 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-4L | Track Roller 4 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-4R | Track Roller 4 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-5L | Track Roller 5 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-5R | Track Roller 5 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-6L | Track Roller 6 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-6R | Track Roller 6 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-7L | Track Roller 7 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-7R | Track Roller 7 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-8L | Track Roller 8 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0111-8R | Track Roller 8 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0121-L | Carrier Roller No 1 LEFT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N0121-R | Carrier Roller No 1 RIGHT | 8500 |  | 2025-04-01 | 4963.4 | 2027-09-28 | 3536.6 | WA | McPhee Creek
DZ3429 | Cat D10 | N1490 | Cam Shaft Inspection | 1000 | 2074.33 | 2025-09-16 | 4963.4 | 2025-09-09 | -1889.07 | WA | McPhee Creek
DZ3429 | Cat D10 | N9500 | Air Cond'r-Serv |  | 993.89 | 2025-06-20 | 4963.4 | 2026-06-20 |  | WA | McPhee Creek
DZ3430 | Cat D10T | N0050 | Blade Assembly | 12000 |  |  | 33120.5 | 2021-02-23 | -21120.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  |  | 2021-12-15 | 33120.5 | 2026-12-14 |  | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0100-L | Track Group LEFT | 4000 | 31545 | 2024-11-09 | 33120.5 | 2027-01-03 | 2424.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0100-R | Track Group RIGHT | 4000 | 31545 | 2024-11-08 | 33120.5 | 2027-01-03 | 2424.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0104-L | Sprockets LEFT | 6000 | 24801 | 2023-04-03 | 33024 | 2025-10-29 | -2223 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0104-R | Sprockets RIGHT | 6000 | 24801 | 2023-04-03 | 33024 | 2025-10-29 | -2223 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0105-LF | Idler LFT FRONT | 6000 | 24801 | 2018-03-28 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0105-LR | Idler LFT REAR | 6000 | 24801 | 2018-03-28 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0105-RF | Idler RHT FRONT | 6000 | 24801 | 2018-03-28 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0105-RR | Idler RHT REAR | 6000 | 24801 | 2018-03-28 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0130-L | Track Frame LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0130-R | Track Frame RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0134-L | Track Adjuster LEFT | 12000 | 32913 | 2026-04-21 | 33120.5 | 2029-05-04 | 11792.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0134-R | Track Adjuster RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0140 | Equalizer Bar | 12000 | 30788 | 2024-08-20 | 33120.5 | 2028-10-23 | 9667.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N0144 | Pivot Shaft | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1000 | Engine | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1002 | Engine Valve Adj | 4000 | 24801 | 2023-04-03 | 33120.5 | 2025-04-30 | -4319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1002-01 | Engine Valve Adj - Initial | 500 | 24801 | 2023-04-03 | 33120.5 | 2024-06-16 | -7819.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1100-L | Turbo Primary LEFT | 6000 | 24801 | 2023-04-03 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1100-R | Turbo Primary RIGHT | 6000 | 24801 | 2023-04-03 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1202 | Fuel Transfer Pump | 6000 | 24801 | 2023-04-03 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1300 | Cooling Sys Service | 6000 | 24801 | 2023-04-03 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1310 | Radiator | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1312-L | Aftercooler Core - LEFT | 12000 | 24801 |  | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1312-R | Aftercooler Core - RIGHT | 12000 | 31629 | 2024-12-17 | 33120.5 | 2029-01-07 | 10508.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N1490 | Cam Shaft Inspection | 2000 | 24801 | 2023-04-03 | 33120.5 | 2024-10-30 | -6319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N2000 | Transmission | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N2020 | Powertrain Pump | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N2050 | Torque Convertor | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N3016 | Drv Shaft Fan Pump-Trans Pump | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N3028 | Drive Shaft T/C - Trans | 12000 | 22374 | 2022-05-21 | 33120.5 | 2026-09-19 | 1253.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N4000 | Bevel Gear | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N4110-L | Steering Clutch/Brk LEFT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N4110-R | Steering Clutch/Brk RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N5000-L | Final Drive LEFT | 12000 | 24801 | 2020-06-29 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N5000-R | Final Drive RIGHT | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7041 | Pump Cooling Fan Engine | 12000 | 31625 | 2024-12-16 | 33120.5 | 2029-01-07 | 10504.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7070 | Pump Implement | 12000 | 24801 | 2023-04-03 | 33120.5 | 2027-04-28 | 3680.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7232 | Hyd Motor Engine Fan | 12000 | 31625 | 2024-12-16 | 33120.5 | 2029-01-07 | 10504.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7421-L | Hyd Cyl Blade Tilt LEFT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 8000 | 18695 | 2021-08-21 | 33120.5 | 2024-10-21 | -6425.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7500 | Hyd Cyl Pin Pull | 8000 |  |  | 33120.5 | 2020-02-25 | -25120.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7510-L | Hyd Cyl Ripper Lift LEFT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 8000 | 24801 | 2023-04-03 | 33120.5 | 2026-04-29 | -319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N7600 | Control Valve | 12000 | 30789 | 2024-08-23 | 33120.5 | 2028-10-23 | 9668.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N8995 | Operator Seat | 6000 | 28161 | 2023-12-16 | 33120.5 | 2026-08-31 | 1040.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N9020 | Alternator | 6000 | 24801 | 2023-04-03 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N9050 | Starter Motor | 6000 | 24801 | 2023-04-03 | 33120.5 | 2025-10-29 | -2319.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N9500 | Air Cond'r-Serv | 4000 | 31629 | 2025-01-01 | 33120.5 | 2027-01-11 | 2508.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N9500-MA | Air Cond'r-Serv - MAJOR | 12000 | 31629 | 2025-01-01 | 33120.5 | 2029-01-07 | 10508.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N9501 | A/C Compressor | 12000 | 31629 | 2025-01-01 | 33120.5 | 2029-01-07 | 10508.5 | WA | Yilgarn Hub
DZ3430 | Cat D10T | N9502 | A/C Condenser | 12000 | 31629 | 2025-01-01 | 33120.5 | 2029-01-07 | 10508.5 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0050 | Blade Assembly | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-02-15 | 32365.9 | 2028-02-14 |  | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0100-L | Track Group LEFT | 4000 | 31828 | 2026-04-20 | 32365.9 | 2027-04-08 | 3462.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0100-R | Track Group RIGHT | 4000 | 31828 | 2026-04-19 | 32365.9 | 2027-04-08 | 3462.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0104-L | Sprockets LEFT | 6000 | 22223 | 2022-07-04 | 32365.9 | 2025-05-16 | -4142.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0104-R | Sprockets RIGHT | 6000 | 25721 | 2023-09-29 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0105-LF | Idler LFT FRONT | 6000 | 25721 | 2025-01-01 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0105-LR | Idler LFT REAR | 6000 | 25721 | 2025-01-01 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0105-RF | Idler RHT FRONT | 6000 | 25721 | 2025-01-01 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0105-RR | Idler RHT REAR | 6000 | 25721 | 2025-01-01 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0130-L | Track Frame LEFT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0130-R | Track Frame RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0134-L | Track Adjuster LEFT | 12000 | 31828 | 2026-04-20 | 32365.9 | 2029-04-04 | 11462.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0134-R | Track Adjuster RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0140 | Equalizer Bar | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N0144 | Pivot Shaft | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1000 | Engine | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1002 | Engine Valve Adj | 4000 | 25721 | 2023-09-29 | 32365.9 | 2025-09-30 | -2644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1002-01 | Engine Valve Adj - Initial | 500 | 25721 | 2023-09-29 | 32365.9 | 2024-11-15 | -6144.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1100-L | Turbo Primary LEFT | 6000 | 25721 | 2023-09-29 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1100-R | Turbo Primary RIGHT | 6000 | 25721 | 2023-09-29 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1202 | Fuel Transfer Pump | 6000 | 25721 | 2023-09-29 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1300 | Cooling Sys Service | 6000 | 25721 | 2023-09-29 | 32365.9 | 2026-03-30 | -644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1310 | Radiator | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1312-L | Aftercooler Core - LEFT | 12000 | 25721 | 2025-01-01 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1312-R | Aftercooler Core - RIGHT | 12000 | 25721 | 2025-01-01 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N1490 | Cam Shaft Inspection | 2000 | 25721 | 2023-09-29 | 32365.9 | 2025-04-03 | -4644.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N2000 | Transmission | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N2020 | Powertrain Pump | 12000 | 20897 | 2022-03-21 | 32365.9 | 2026-07-15 | 531.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N2050 | Torque Convertor | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N3016 | Drv Shaft Fan Pump-Trans Pump | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N3028 | Drive Shaft T/C - Trans | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N4000 | Bevel Gear | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N4110-L | Steering Clutch/Brk LEFT | 12000 | 30341 | 2025-12-25 | 32365.9 | 2028-11-20 | 9975.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N4110-R | Steering Clutch/Brk RIGHT | 12000 | 30341 | 2025-12-25 | 32365.9 | 2028-11-20 | 9975.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N5000-L | Final Drive LEFT | 12000 | 30341 | 2025-12-25 | 32365.9 | 2028-11-20 | 9975.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N5000-R | Final Drive RIGHT | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7041 | Pump Cooling Fan Engine | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7070 | Pump Implement | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7232 | Hyd Motor Engine Fan | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7421-L | Hyd Cyl Blade Tilt LEFT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 8000 | 28828 | 2024-07-24 | 32365.9 | 2027-07-08 | 4462.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7500 | Hyd Cyl Pin Pull | 8000 | 13367 | 2020-06-09 | 32365.9 | 2023-09-01 | -10998.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7510-L | Hyd Cyl Ripper Lift LEFT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 8000 | 25721 | 2023-09-29 | 32365.9 | 2026-09-28 | 1355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N7600 | Control Valve | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N8995 | Operator Seat | 6000 | 32190 | 2026-05-15 | 32365.9 | 2027-11-08 | 5824.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N9020 | Alternator | 6000 | 32913 | 2026-04-21 | 32365.9 | 2028-01-13 | 6547.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N9050 | Starter Motor | 6000 | 22829 | 2026-05-16 | 32365.9 | 2025-07-10 | -3536.9 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N9500 | Air Cond'r-Serv | 4000 | 29878 | 2025-01-01 | 32365.9 | 2026-10-12 | 1512.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N9500-MA | Air Cond'r-Serv - MAJOR | 12000 | 29878 | 2025-01-01 | 32365.9 | 2028-10-09 | 9512.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N9501 | A/C Compressor | 12000 | 25721 | 2023-09-29 | 32365.9 | 2027-09-27 | 5355.1 | WA | Yilgarn Hub
DZ3431 | Cat D10T | N9502 | A/C Condenser | 12000 | 30856 | 2026-02-08 | 32365.9 | 2029-01-06 | 10490.1 | WA | Yilgarn Hub
DZ3433 | Cat D10 | N0066 | Fire Suppression Sys Cylinder |  |  |  | 3177.4 |  |  | WA | McPhee Creek
DZ3433 | Cat D10 | N1490 | Cam Shaft Inspection | 1000 |  |  | 3177.4 | 2025-07-31 | -2177.4 | WA | McPhee Creek
DZ3433 | Cat D10 | N9500 | Air Cond'r-Serv |  |  | 2025-10-02 | 3177.4 | 2026-10-02 |  | WA | McPhee Creek
DZ3453 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-12-01 | 24820 | 2030-11-30 |  | WA | Iron Bridge
DZ3453 | Cat D10T | N0101-L | Track Chain LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0101-R | Track Chain RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0102-L | Trk Chn Pin & Bush Trn LEFT | 4000 |  | 2026-03-02 | 24820 | 2022-05-02 | -20820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 4000 |  | 2026-03-02 | 24820 | 2022-05-02 | -20820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0103-L | Track Plates LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-08 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0103-R | Track Plates RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-08 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0104-L | Sprockets LEFT | 4000 |  | 2026-03-02 | 24820 | 2022-05-02 | -20820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0104-R | Sprockets RIGHT | 4000 |  | 2026-03-02 | 24820 | 2022-05-02 | -20820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0105-LF | Idler LFT FRONT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0105-LR | Idler LFT REAR | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0105-RF | Idler RHT FRONT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0105-RR | Idler RHT REAR | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0121-L | Carrier Roller No 1 LEFT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0121-R | Carrier Roller No 1 RIGHT | 8000 |  | 2026-03-02 | 24820 | 2023-02-12 | -16820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0130-L | Track Frame LEFT | 30000 |  | 2026-03-02 | 24820 | 2027-06-02 | 5180 | WA | Iron Bridge
DZ3453 | Cat D10T | N0130-R | Track Frame RIGHT | 30000 |  | 2026-03-02 | 24820 | 2027-06-02 | 5180 | WA | Iron Bridge
DZ3453 | Cat D10T | N0134-L | Track Adjuster LEFT | 15000 |  | 2026-03-02 | 24820 | 2024-06-26 | -9820 | WA | Iron Bridge
DZ3453 | Cat D10T | N0134-R | Track Adjuster RIGHT | 15000 |  | 2026-03-02 | 24820 | 2024-06-26 | -9820 | WA | Iron Bridge
DZ3453 | Cat D10T | N1002 | Engine Valve Adj | 4000 | 24188 | 2026-02-12 | 24820 | 2027-01-24 | 3368 | WA | Iron Bridge
DZ3453 | Cat D10T | N1490 | Cam Shaft Inspection | 2000 |  | 2026-02-12 | 24820 | 2021-12-10 | -22820 | WA | Iron Bridge
DZ3453 | Cat D10T | N8995 | Operator Seat | 6000 | 24338 | 2026-02-12 | 24820 | 2027-06-26 | 5518 | WA | Iron Bridge
DZ3453 | Cat D10T | N9500 | Air Cond'r-Serv | 5000 | 24338 | 2026-02-12 | 24820 | 2027-04-16 | 4518 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0066 | Fire Suppression Sys Cylinder |  | 19823 | 2025-03-01 | 2161 | 2026-05-28 |  | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0101-L | Track Chain LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0101-R | Track Chain RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0102-L | Trk Chn Pin & Bush Trn LEFT | 4000 |  | 2026-02-12 | 2161 | 2026-10-06 | 1839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 4000 |  | 2026-02-12 | 2161 | 2026-10-06 | 1839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0103-L | Track Plates LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0103-R | Track Plates RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0104-L | Sprockets LEFT | 4000 |  | 2026-02-12 | 2161 | 2026-10-06 | 1839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0104-R | Sprockets RIGHT | 4000 |  | 2026-02-12 | 2161 | 2026-10-06 | 1839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0105-LF | Idler LFT FRONT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0105-LR | Idler LFT REAR | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0105-RF | Idler RHT FRONT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0105-RR | Idler RHT REAR | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-1L | Track Roller 1 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-1R | Track Roller 1 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-2L | Track Roller 2 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-2R | Track Roller 2 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-3L | Track Roller 3 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-3R | Track Roller 3 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-4L | Track Roller 4 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-4R | Track Roller 4 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-5L | Track Roller 5 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-5R | Track Roller 5 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-6L | Track Roller 6 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-6R | Track Roller 6 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-7L | Track Roller 7 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-7R | Track Roller 7 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-8L | Track Roller 8 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0111-8R | Track Roller 8 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0121-L | Carrier Roller No 1 LEFT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0121-R | Carrier Roller No 1 RIGHT | 8000 |  | 2026-02-12 | 2161 | 2027-07-19 | 5839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0130-L | Track Frame LEFT | 36000 |  | 2026-02-12 | 2161 | 2033-01-08 | 33839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0130-R | Track Frame RIGHT | 36000 |  | 2026-02-12 | 2161 | 2033-01-08 | 33839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0134-L | Track Adjuster LEFT | 18000 |  | 2026-02-12 | 2161 | 2029-07-02 | 15839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0134-R | Track Adjuster RIGHT | 18000 |  | 2026-02-12 | 2161 | 2029-07-02 | 15839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0139-L | Track Frame Mid Life LEFT | 18000 |  | 2026-02-12 | 2161 | 2029-07-02 | 15839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N0139-R | Track Frame Mid Life RIGHT | 18000 |  | 2026-02-12 | 2161 | 2029-07-02 | 15839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N1002 | Engine Valve Adj | 4000 |  | 2026-02-12 | 2161 | 2026-10-06 | 1839 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N1490 | Cam Shaft Inspection | 2000 |  | 2026-02-12 | 2161 | 2026-05-16 | -161 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N8995 | Operator Seat | 6000 | 1134 | 2026-02-12 | 2161 | 2027-05-18 | 4973 | WA | Iron Bridge
DZ3454 | Cat D10T2 | N9500 | Air Cond'r-Serv | 6000 | 1134 | 2026-02-12 | 2161 | 2027-05-18 | 4973 | WA | Iron Bridge
DZ6517 | Cat D9T | N0050 | Blade Assembly | 20000 |  | 2022-06-01 | 43005.2 | 2016-06-26 | -23005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-20 | 43005.2 | 2030-01-19 |  | WA | Miralga Creek
DZ6517 | Cat D9T | N0100-L | Track Group LEFT | 1700 | 41400 | 2025-10-08 | 43005.2 | 2026-06-12 | 94.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N0100-R | Track Group RIGHT | 1700 | 41400 | 2025-10-08 | 43005.2 | 2026-06-12 | 94.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N0104-L | Sprockets LEFT | 5000 | 40075.21 | 2025-04-03 | 43005.2 | 2027-04-19 | 2070.01 | WA | Miralga Creek
DZ6517 | Cat D9T | N0104-R | Sprockets RIGHT | 5000 | 40075.21 | 2025-04-03 | 43005.2 | 2027-04-19 | 2070.01 | WA | Miralga Creek
DZ6517 | Cat D9T | N0105-LF | Idler LFT FRONT | 6000 | 41064.76 | 2025-07-29 | 43005.2 | 2028-02-26 | 4059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0105-LR | Idler LFT REAR | 6000 | 41064.76 | 2025-07-29 | 43005.2 | 2028-02-26 | 4059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0105-RF | Idler RHT FRONT | 6000 | 41064.76 | 2025-07-29 | 43005.2 | 2028-02-26 | 4059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0105-RR | Idler RHT REAR | 6000 | 41064.76 | 2025-07-29 | 43005.2 | 2028-02-26 | 4059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-1L | Track Roller 1 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-1R | Track Roller 1 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-2L | Track Roller 2 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-2R | Track Roller 2 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-3L | Track Roller 3 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-3R | Track Roller 3 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-4L | Track Roller 4 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-4R | Track Roller 4 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-5L | Track Roller 5 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-5R | Track Roller 5 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-6L | Track Roller 6 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-6R | Track Roller 6 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-7L | Track Roller 7 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-7R | Track Roller 7 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-8L | Track Roller 8 LEFT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0111-8R | Track Roller 8 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0121-L | Carrier Roller No 1 LEFT | 10000 | 41579.3 | 2025-07-29 | 43005.2 | 2030-02-06 | 8574.1 | WA | Miralga Creek
DZ6517 | Cat D9T | N0121-R | Carrier Roller No 1 RIGHT | 10000 | 41064.76 | 2025-07-29 | 43005.2 | 2029-11-17 | 8059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0130-L | Track Frame LEFT | 16000 | 41064.76 | 2025-07-29 | 43005.2 | 2032-06-19 | 14059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0130-R | Track Frame RIGHT | 16000 | 41064.76 | 2025-07-29 | 43005.2 | 2032-06-19 | 14059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N0140 | Equalizer Bar | 8000 | 41276.42 | 2025-08-31 | 43005.2 | 2029-02-09 | 6271.22 | WA | Miralga Creek
DZ6517 | Cat D9T | N0144 | Pivot Shaft | 32000 |  | 2022-06-01 | 43005.2 | 2021-08-29 | -11005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N1000 | Engine | 16000 | 37384.21 | 2023-04-17 | 43005.2 | 2030-11-17 | 10379.01 | WA | Miralga Creek
DZ6517 | Cat D9T | N1002-01 | Engine Valve Adj - Initial | 500 | 37384.21 | 2023-04-17 | 43005.2 | 2024-03-13 | -5120.99 | WA | Miralga Creek
DZ6517 | Cat D9T | N1100 | Turbo Primary | 16000 | 23922 | 2019-11-04 | 43005.2 | 2025-01-27 | -3083.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N1301 | Water Pump | 16000 | 23922 | 2019-11-04 | 43005.2 | 2025-01-27 | -3083.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N1310 | Radiator | 16000 | 17542 | 2018-04-07 | 43005.2 | 2022-04-29 | -9463.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N1312-L | Aftercooler Core - LEFT | 16000 |  | 2022-06-01 | 43005.2 | 2014-10-05 | -27005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N2000 | Transmission | 16000 | 32525 | 2021-12-29 | 43005.2 | 2028-10-13 | 5519.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N2002 | Oil Cooler - Transmission | 16000 | 42804.3 | 2026-05-06 | 43005.2 | 2033-03-20 | 15799.1 | WA | Miralga Creek
DZ6517 | Cat D9T | N2004 | Transmission Pump | 16000 | 32525 | 2021-01-01 | 43005.2 | 2028-10-13 | 5519.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N2050 | Torque Convertor | 16000 | 32642 | 2022-01-16 | 43005.2 | 2028-11-01 | 5636.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N3029 | Uni's T/C - Trans | 16000 |  | 2022-06-01 | 43005.2 | 2014-10-05 | -27005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N4110-L | Steering Clutch/Brk LEFT | 25000 | 17542 | 2018-04-07 | 43005.2 | 2026-03-16 | -463.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N4110-R | Steering Clutch/Brk RIGHT | 25000 | 17542 | 2018-04-07 | 43005.2 | 2026-03-16 | -463.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N5000-L | Final Drive LEFT | 25000 | 31799 | 2021-10-09 | 43005.2 | 2032-05-08 | 13793.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N5000-R | Final Drive RIGHT | 25000 | 35843.06 | 2022-10-31 | 43005.2 | 2034-02-04 | 17837.86 | WA | Miralga Creek
DZ6517 | Cat D9T | N6360 | Brake Control Valve | 32000 |  | 2022-06-01 | 43005.2 | 2021-08-29 | -11005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N7041 | Pump Cooling Fan Engine | 16000 | 32525 | 2022-01-01 | 43005.2 | 2028-10-13 | 5519.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7113 | Motor Emergency Steering | 16000 | 32525 | 2022-01-01 | 43005.2 | 2028-10-13 | 5519.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7121 | Pump Steering/Braking | 16000 | 37074 | 2023-02-25 | 43005.2 | 2030-09-30 | 10068.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7155 | Hyd Pump Main | 16000 | 32525 | 2022-01-01 | 43005.2 | 2028-10-13 | 5519.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7232 | Hyd Motor Engine Fan | 16000 | 32525 | 2022-01-01 | 43005.2 | 2028-10-13 | 5519.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7420-L | Hyd Cyl Blade Lift LEFT | 14000 | 39187.61 | 2024-11-11 | 43005.2 | 2030-10-18 | 10182.41 | WA | Miralga Creek
DZ6517 | Cat D9T | N7420-R | Hyd Cyl Blade Lift RIGHT | 14000 | 41968 | 2025-12-31 | 43005.2 | 2031-12-29 | 12962.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7421-L | Hyd Cyl Blade Tilt LEFT | 14000 | 33007 | 2022-02-25 | 43005.2 | 2028-02-17 | 4001.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 14000 | 33007 | 2022-02-25 | 43005.2 | 2028-02-17 | 4001.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7510-L | Hyd Cyl Ripper Lift LEFT | 14000 | 17542 | 2018-04-07 | 43005.2 | 2021-06-18 | -11463.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 14000 | 17542 | 2018-04-07 | 43005.2 | 2021-06-18 | -11463.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 14000 | 39062.11 | 2024-10-15 | 43005.2 | 2030-09-28 | 10056.91 | WA | Miralga Creek
DZ6517 | Cat D9T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 14000 | 41064.76 | 2025-07-29 | 43005.2 | 2031-08-09 | 12059.56 | WA | Miralga Creek
DZ6517 | Cat D9T | N7600 | Control Valve | 30000 | 17542 | 2018-04-07 | 43005.2 | 2028-05-11 | 4536.8 | WA | Miralga Creek
DZ6517 | Cat D9T | N7610 | Hyd Cooler Core | 16000 |  | 2022-06-01 | 43005.2 | 2014-10-05 | -27005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N8000 | Main Frame/Chassis | 10000 |  | 2022-06-01 | 43005.2 | 2012-03-04 | -33005.2 | WA | Miralga Creek
DZ6517 | Cat D9T | N8995 | Operator Seat | 10000 | 37856.94 | 2024-04-23 | 43005.2 | 2028-06-30 | 4851.74 | WA | Miralga Creek
DZ6517 | Cat D9T | N9500 | Air Cond'r-Serv |  | 41771.1 | 2025-12-02 | 43005.2 | 2026-12-02 |  | WA | Miralga Creek
DZ6526 | Cat D9T | N0050 | Blade Assembly | 20000 |  | 2022-06-01 | 34410.8 | 2020-03-11 | -14410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-07-08 | 34410.8 | 2029-07-07 |  | WA | Miralga Creek
DZ6526 | Cat D9T | N0100-L | Track Group LEFT | 1700 | 33334 | 2025-12-17 | 34410.8 | 2026-09-03 | 623.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N0100-R | Track Group RIGHT | 1700 | 33334 | 2025-12-17 | 34410.8 | 2026-09-03 | 623.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N0104-L | Sprockets LEFT | 5000 | 30869 | 2025-09-01 | 34410.8 | 2027-01-13 | 1458.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N0104-R | Sprockets RIGHT | 5000 | 30869 | 2025-09-01 | 34410.8 | 2027-01-13 | 1458.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N0105-LF | Idler LFT FRONT | 6000 | 24492.81 | 2022-07-09 | 34410.8 | 2024-09-18 | -3917.99 | WA | Miralga Creek
DZ6526 | Cat D9T | N0105-LR | Idler LFT REAR | 6000 | 24492.81 | 2022-07-09 | 34410.8 | 2024-09-18 | -3917.99 | WA | Miralga Creek
DZ6526 | Cat D9T | N0105-RF | Idler RHT FRONT | 6000 | 24492.81 | 2022-07-09 | 34410.8 | 2024-09-18 | -3917.99 | WA | Miralga Creek
DZ6526 | Cat D9T | N0105-RR | Idler RHT REAR | 6000 | 24492.81 | 2022-07-09 | 34410.8 | 2024-09-18 | -3917.99 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-1L | Track Roller 1 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-1R | Track Roller 1 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-2L | Track Roller 2 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-2R | Track Roller 2 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-3L | Track Roller 3 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-3R | Track Roller 3 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-4L | Track Roller 4 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-4R | Track Roller 4 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-5L | Track Roller 5 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-5R | Track Roller 5 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-6L | Track Roller 6 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-6R | Track Roller 6 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-7L | Track Roller 7 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-7R | Track Roller 7 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-8L | Track Roller 8 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0111-8R | Track Roller 8 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0121-L | Carrier Roller No 1 LEFT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0121-R | Carrier Roller No 1 RIGHT | 10000 | 24492.81 | 2022-07-09 | 34410.8 | 2026-06-10 | 82.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0130-L | Track Frame LEFT | 16000 | 30119 | 2024-07-13 | 34410.8 | 2031-06-15 | 11708.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N0130-R | Track Frame RIGHT | 16000 | 24492.81 | 2022-07-09 | 34410.8 | 2029-01-10 | 6082.01 | WA | Miralga Creek
DZ6526 | Cat D9T | N0140 | Equalizer Bar | 8000 | 26751.28 | 2023-02-26 | 34410.8 | 2026-07-21 | 340.48 | WA | Miralga Creek
DZ6526 | Cat D9T | N0144 | Pivot Shaft | 32000 |  | 2022-06-01 | 34410.8 | 2025-05-13 | -2410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N1000 | Engine | 16000 | 26636.5 | 2023-02-13 | 34410.8 | 2029-12-13 | 8225.7 | WA | Miralga Creek
DZ6526 | Cat D9T | N1002-01 | Engine Valve Adj - Initial | 500 | 26722 | 2023-02-24 | 34410.8 | 2023-04-22 | -7188.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N1100 | Turbo Primary | 16000 | 24889.28 | 2022-09-03 | 34410.8 | 2029-03-13 | 6478.48 | WA | Miralga Creek
DZ6526 | Cat D9T | N1301 | Water Pump | 16000 | 10084 | 2018-09-15 | 34410.8 | 2022-10-25 | -8326.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N1310 | Radiator | 16000 | 33915 | 2026-03-20 | 34410.8 | 2033-02-02 | 15504.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N1312-L | Aftercooler Core - LEFT | 16000 | 26636.5 | 2023-02-13 | 34410.8 | 2029-12-13 | 8225.7 | WA | Miralga Creek
DZ6526 | Cat D9T | N2000 | Transmission | 16000 | 19264 | 2020-08-19 | 34410.8 | 2026-10-09 | 853.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N2002 | Oil Cooler - Transmission | 16000 | 23092 | 2022-01-22 | 34410.8 | 2028-06-03 | 4681.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N2004 | Transmission Pump | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N2050 | Torque Convertor | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N3029 | Uni's T/C - Trans | 16000 | 32635.68 | 2025-08-25 | 34410.8 | 2032-07-15 | 14224.88 | WA | Miralga Creek
DZ6526 | Cat D9T | N4110-L | Steering Clutch/Brk LEFT | 25000 | 20795 | 2021-06-01 | 34410.8 | 2031-04-25 | 11384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N4110-R | Steering Clutch/Brk RIGHT | 25000 | 20795 | 2021-06-01 | 34410.8 | 2031-04-25 | 11384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N5000-L | Final Drive LEFT | 25000 | 18784 | 2020-07-10 | 34410.8 | 2030-06-12 | 9373.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N5000-R | Final Drive RIGHT | 25000 | 20795 | 2021-06-01 | 34410.8 | 2031-04-25 | 11384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N6360 | Brake Control Valve | 32000 |  | 2022-06-01 | 34410.8 | 2025-05-13 | -2410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N7041 | Pump Cooling Fan Engine | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7113 | Motor Emergency Steering | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7121 | Pump Steering/Braking | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7155 | Hyd Pump Main | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7232 | Hyd Motor Engine Fan | 16000 | 20795 | 2021-06-01 | 34410.8 | 2027-06-07 | 2384.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7420-L | Hyd Cyl Blade Lift LEFT | 14000 | 22856 | 2021-12-19 | 34410.8 | 2027-06-17 | 2445.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7420-R | Hyd Cyl Blade Lift RIGHT | 14000 | 33334 | 2025-12-17 | 34410.8 | 2031-12-23 | 12923.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7421-L | Hyd Cyl Blade Tilt LEFT | 14000 | 27435 | 2023-05-16 | 34410.8 | 2029-06-07 | 7024.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 14000 | 22366 | 2021-11-02 | 34410.8 | 2027-04-01 | 1955.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7510-L | Hyd Cyl Ripper Lift LEFT | 14000 | 24191 | 2022-05-24 | 34410.8 | 2028-01-13 | 3780.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 14000 | 32269.4 | 2025-06-21 | 34410.8 | 2031-07-08 | 11858.6 | WA | Miralga Creek
DZ6526 | Cat D9T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 14000 | 29582.95 | 2024-04-20 | 34410.8 | 2030-05-11 | 9172.15 | WA | Miralga Creek
DZ6526 | Cat D9T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 14000 |  | 2022-06-01 | 34410.8 | 2017-08-09 | -20410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N7600 | Control Valve | 30000 |  | 2022-06-01 | 34410.8 | 2024-07-02 | -4410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N7610 | Hyd Cooler Core | 16000 |  | 2022-06-01 | 34410.8 | 2018-06-20 | -18410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N8000 | Main Frame/Chassis | 10000 |  | 2022-06-01 | 34410.8 | 2015-11-18 | -24410.8 | WA | Miralga Creek
DZ6526 | Cat D9T | N8995 | Operator Seat | 10000 | 33498 | 2026-01-12 | 34410.8 | 2030-04-28 | 9087.2 | WA | Miralga Creek
DZ6526 | Cat D9T | N9500 | Air Cond'r-Serv |  | 33497.7 | 2026-01-11 | 34410.8 | 2027-01-11 |  | WA | Miralga Creek
DZ6528 | Cat D9T | N0050 | Blade Assembly | 20000 |  | 2022-06-01 | 31190.5 | 2023-11-07 | -11190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-02-10 | 31190.5 | 2028-02-09 |  | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0100-L | Track Group LEFT | 2000 | 30646 | 2026-04-11 | 31190.5 | 2026-09-26 | 1455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0100-R | Track Group RIGHT | 2000 | 30646 | 2026-04-11 | 31190.5 | 2026-09-26 | 1455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0104-L | Sprockets LEFT | 5000 | 24363.85 | 2024-09-16 | 31190.5 | 2025-12-27 | -1826.65 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0104-R | Sprockets RIGHT | 5000 | 24363.85 | 2024-09-16 | 31190.5 | 2025-12-27 | -1826.65 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0105-LF | Idler LFT FRONT | 6000 | 30646 | 2026-04-11 | 31190.5 | 2027-08-26 | 5455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0105-LR | Idler LFT REAR | 6000 | 30646 | 2026-04-11 | 31190.5 | 2027-08-26 | 5455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0105-RF | Idler RHT FRONT | 6000 | 30646 | 2026-04-11 | 31190.5 | 2027-08-26 | 5455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0105-RR | Idler RHT REAR | 6000 | 30646 | 2026-04-11 | 31190.5 | 2027-08-26 | 5455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-1L | Track Roller 1 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-1R | Track Roller 1 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-2L | Track Roller 2 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-2R | Track Roller 2 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-3L | Track Roller 3 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-3R | Track Roller 3 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-4L | Track Roller 4 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-4R | Track Roller 4 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-5L | Track Roller 5 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-5R | Track Roller 5 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-6L | Track Roller 6 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-6R | Track Roller 6 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-7L | Track Roller 7 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-7R | Track Roller 7 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-8L | Track Roller 8 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0111-8R | Track Roller 8 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0121-L | Carrier Roller No 1 LEFT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0121-R | Carrier Roller No 1 RIGHT | 10000 | 30646 | 2026-04-11 | 31190.5 | 2028-07-24 | 9455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0130-L | Track Frame LEFT | 16000 | 30646 | 2026-04-11 | 31190.5 | 2029-12-06 | 15455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0130-R | Track Frame RIGHT | 16000 | 30646 | 2026-04-11 | 31190.5 | 2029-12-06 | 15455.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0140 | Equalizer Bar | 8000 | 27098.08 | 2025-06-22 | 31190.5 | 2027-04-19 | 3907.58 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N0144 | Pivot Shaft | 32000 |  | 2022-06-01 | 31190.5 | 2026-08-03 | 809.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N1000 | Engine | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N1002-01 | Engine Valve Adj - Initial | 500 | 17617 | 2022-12-19 | 31190.5 | 2023-06-04 | -13073.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N1100 | Turbo Primary | 16000 | 23210.43 | 2024-05-03 | 31190.5 | 2028-03-26 | 8019.93 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N1301 | Water Pump | 16000 | 12022 | 2021-05-14 | 31190.5 | 2025-09-06 | -3168.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N1310 | Radiator | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N1312-L | Aftercooler Core - LEFT | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N2000 | Transmission | 16000 | 16717.9 | 2022-09-17 | 31190.5 | 2026-10-02 | 1527.4 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N2002 | Oil Cooler - Transmission | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N2004 | Transmission Pump | 16000 | 17355 | 2022-11-19 | 31190.5 | 2026-11-24 | 2164.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N2050 | Torque Convertor | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N3029 | Uni's T/C - Trans | 16000 | 30940 | 2026-05-07 | 31190.5 | 2029-12-30 | 15749.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N4110-L | Steering Clutch/Brk LEFT | 25000 |  | 2018-09-12 | 31190.5 | 2024-12-28 | -6190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N4110-R | Steering Clutch/Brk RIGHT | 25000 |  | 2018-09-12 | 31190.5 | 2024-12-28 | -6190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N5000-L | Final Drive LEFT | 25000 | 27072.44 | 2025-06-15 | 31190.5 | 2031-03-03 | 20881.94 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N5000-R | Final Drive RIGHT | 25000 | 27072.44 | 2025-06-15 | 31190.5 | 2031-03-03 | 20881.94 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N6360 | Brake Control Valve | 32000 |  | 2022-06-01 | 31190.5 | 2026-08-03 | 809.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7041 | Pump Cooling Fan Engine | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7113 | Motor Emergency Steering | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7121 | Pump Steering/Braking | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7155 | Hyd Pump Main | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7232 | Hyd Motor Engine Fan | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7420-L | Hyd Cyl Blade Lift LEFT | 14000 | 24363.85 | 2024-09-16 | 31190.5 | 2028-01-16 | 7173.35 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7420-R | Hyd Cyl Blade Lift RIGHT | 14000 | 24606.7 | 2024-11-17 | 31190.5 | 2028-02-05 | 7416.2 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7421-L | Hyd Cyl Blade Tilt LEFT | 14000 |  | 2018-09-12 | 31190.5 | 2022-06-25 | -17190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 14000 |  | 2018-09-12 | 31190.5 | 2022-06-25 | -17190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7510-L | Hyd Cyl Ripper Lift LEFT | 14000 |  | 2018-09-12 | 31190.5 | 2022-06-25 | -17190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 14000 |  | 2018-09-12 | 31190.5 | 2022-06-25 | -17190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 14000 | 16484.02 | 2022-06-30 | 31190.5 | 2026-03-30 | -706.48 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 14000 | 16597 | 2022-06-30 | 31190.5 | 2026-04-09 | -593.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7600 | Control Valve | 30000 |  | 2018-09-12 | 31190.5 | 2026-02-18 | -1190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N7610 | Hyd Cooler Core | 16000 | 16710.94 | 2022-09-17 | 31190.5 | 2026-10-02 | 1520.44 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N8000 | Main Frame/Chassis | 10000 |  | 2022-06-01 | 31190.5 | 2021-07-27 | -21190.5 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N8995 | Operator Seat | 10000 | 26573.38 | 2025-05-08 | 31190.5 | 2027-08-20 | 5382.88 | WA | Sanjiv Ridge
DZ6528 | Cat D9T | N9500 | Air Cond'r-Serv |  | 28781 | 2025-11-11 | 31190.5 | 2026-11-11 |  | WA | Sanjiv Ridge
DZ6536 | Cat D10T2 | N0050 | Blade Assembly | 20000 |  | 2022-06-01 | 17737.5 | 2027-05-19 | 2262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-06-01 | 17737.5 | 2027-05-31 |  | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0100-L | Track Group LEFT | 1700 | 15731.23 | 2025-08-04 | 17737.5 | 2026-04-10 | -306.27 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0100-R | Track Group RIGHT | 1700 | 15731.06 | 2025-08-04 | 17737.5 | 2026-04-10 | -306.44 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0104-L | Sprockets LEFT | 5000 | 16060.73 | 2025-09-18 | 17737.5 | 2027-11-02 | 3323.23 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0104-R | Sprockets RIGHT | 5000 | 16060.73 | 2025-09-18 | 17737.5 | 2027-11-02 | 3323.23 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0105-LF | Idler LFT FRONT | 6000 | 16060.73 | 2025-09-18 | 17737.5 | 2028-04-08 | 4323.23 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0105-LR | Idler LFT REAR | 6000 | 13314.53 | 2024-08-10 | 17737.5 | 2027-01-31 | 1577.03 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0105-RF | Idler RHT FRONT | 6000 | 16060.73 | 2025-09-18 | 17737.5 | 2028-04-08 | 4323.23 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0105-RR | Idler RHT REAR | 6000 | 14844.69 | 2025-01-28 | 17737.5 | 2027-09-29 | 3107.19 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-1L | Track Roller 1 LEFT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-1R | Track Roller 1 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-2L | Track Roller 2 LEFT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-2R | Track Roller 2 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-3L | Track Roller 3 LEFT | 10000 | 16555 | 2025-12-12 | 17737.5 | 2030-03-17 | 8817.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-3R | Track Roller 3 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-4L | Track Roller 4 LEFT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-4R | Track Roller 4 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-5L | Track Roller 5 LEFT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-5R | Track Roller 5 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-6L | Track Roller 6 LEFT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-6R | Track Roller 6 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-7L | Track Roller 7 LEFT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-7R | Track Roller 7 RIGHT | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-8L | Track Roller 8 LEFT | 10000 | 13110.25 | 2024-07-25 | 17737.5 | 2028-09-20 | 5372.75 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0111-8R | Track Roller 8 RIGHT | 10000 | 13110.25 | 2024-07-25 | 17737.5 | 2028-09-20 | 5372.75 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0121-L | Carrier Roller No 1 LEFT | 10000 | 13110.25 | 2024-07-25 | 17737.5 | 2028-09-20 | 5372.75 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0121-R | Carrier Roller No 1 RIGHT | 10000 | 13314.53 | 2024-08-10 | 17737.5 | 2028-10-22 | 5577.03 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0130-L | Track Frame LEFT | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0130-R | Track Frame RIGHT | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0140 | Equalizer Bar | 8000 |  | 2022-06-01 | 17737.5 | 2022-03-17 | -9737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N0144 | Pivot Shaft | 36000 |  | 2022-06-01 | 17737.5 | 2034-04-12 | 18262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1000 | Engine | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1002-01 | Engine Valve Adj - Initial | 250 |  | 2022-06-01 | 17737.5 | 2018-11-12 | -17487.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1100-L | Turbo Primary LEFT | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1100-R | Turbo Primary RIGHT | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1301 | Water Pump | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1310 | Radiator | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1312-LW | Aftercooler Core - LOWER | 18000 | 2760 | 2021-11-26 | 17737.5 | 2027-09-16 | 3022.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1312-UP | Aftercooler Core - UPPER | 18000 | 2760 | 2021-11-26 | 17737.5 | 2027-09-16 | 3022.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N1490 | Cam Shaft Inspection | 1500 | 15554 | 2025-07-13 | 17737.5 | 2026-02-09 | -683.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N2000 | Transmission | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N2002 | Oil Cooler - Transmission | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N2004 | Transmission Pump | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N2050 | Torque Convertor | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N3029 | Uni's T/C - Trans | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N4110-L | Steering Clutch/Brk LEFT | 25000 |  | 2022-06-01 | 17737.5 | 2029-07-15 | 7262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N4110-R | Steering Clutch/Brk RIGHT | 25000 |  | 2022-06-01 | 17737.5 | 2029-07-15 | 7262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N5000-L | Final Drive LEFT | 25000 |  | 2022-06-01 | 17737.5 | 2029-07-15 | 7262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N5000-R | Final Drive RIGHT | 30000 |  | 2022-06-01 | 17737.5 | 2031-09-10 | 12262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N6360 | Brake Control Valve | 36000 |  | 2022-06-01 | 17737.5 | 2034-04-12 | 18262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7041 | Pump Cooling Fan Engine | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7070-L | Pump Implement LEFT | 18000 | 16060.73 | 2025-09-18 | 17737.5 | 2033-06-11 | 16323.23 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7070-R | Pump Implement RIGHT | 18000 | 9208.25 | 2023-01-30 | 17737.5 | 2030-06-27 | 9470.75 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7100 | Pump Charge | 18000 | 16060.73 | 2025-09-18 | 17737.5 | 2033-06-11 | 16323.23 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7232 | Hyd Motor Engine Fan | 18000 | 16029.6 | 2025-09-11 | 17737.5 | 2033-06-06 | 16292.1 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7420-L | Hyd Cyl Blade Lift LEFT | 14000 | 10556.45 | 2023-11-15 | 17737.5 | 2029-05-06 | 6818.95 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7420-R | Hyd Cyl Blade Lift RIGHT | 14000 | 17623 | 2026-05-18 | 17737.5 | 2032-05-23 | 13885.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7421-L | Hyd Cyl Blade Tilt LEFT | 14000 | 8616.21 | 2022-12-21 | 17737.5 | 2028-07-04 | 4878.71 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7421-R | Hyd Cyl Blade Tilt RIGHT | 14000 |  | 2022-06-01 | 17737.5 | 2024-10-16 | -3737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7510-L | Hyd Cyl Ripper Lift LEFT | 14000 | 14567.94 | 2024-12-16 | 17737.5 | 2031-01-28 | 10830.44 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7510-R | Hyd Cyl Ripper Lift RIGHT | 14000 | 13110.25 | 2024-07-25 | 17737.5 | 2030-06-12 | 9372.75 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7514-L | Hyd Cyl Ripper Pitch LEFT | 14000 | 401 | 2021-03-11 | 17737.5 | 2024-12-19 | -3336.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 14000 |  | 2022-06-01 | 17737.5 | 2024-10-16 | -3737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7600 | Control Valve | 30000 |  | 2022-06-01 | 17737.5 | 2031-09-10 | 12262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N7610 | Hyd Cooler Core | 18000 |  | 2022-06-01 | 17737.5 | 2026-07-08 | 262.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N8000 | Main Frame/Chassis | 10000 |  | 2022-06-01 | 17737.5 | 2023-01-25 | -7737.5 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N8995 | Operator Seat | 10000 | 15815.72 | 2025-08-16 | 17737.5 | 2029-11-20 | 8078.22 | WA | Miralga Creek
DZ6536 | Cat D10T2 | N9500 | Air Cond'r-Serv |  |  | 2025-07-07 | 17737.5 | 2026-07-07 |  | WA | Miralga Creek
DZ6542 | Cat D10T | N0050 | Blade Assembly | 20000 | 37227 | 2021-07-29 | 52003.6 | 2027-08-06 | 5223.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-01-15 | 52003.6 | 2027-01-14 |  | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0100-L | Track Group LEFT | 2000 | 49885 | 2025-08-17 | 52003.6 | 2026-05-18 | -118.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0100-R | Track Group RIGHT | 2000 | 49885 | 2025-08-17 | 52003.6 | 2026-05-18 | -118.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0104-L | Sprockets LEFT | 4000 | 39972 | 2022-07-05 | 52003.6 | 2024-07-28 | -8031.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0104-R | Sprockets RIGHT | 4000 | 39972 | 2022-07-05 | 52003.6 | 2024-07-28 | -8031.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0105-LF | Idler LFT FRONT | 6000 | 49886.13 | 2025-08-26 | 52003.6 | 2027-04-17 | 3882.53 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0105-LR | Idler LFT REAR | 6000 | 49885 | 2025-08-17 | 52003.6 | 2027-04-16 | 3881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0105-RF | Idler RHT FRONT | 6000 | 51650 | 2026-04-14 | 52003.6 | 2027-09-11 | 5646.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0105-RR | Idler RHT REAR | 6000 | 49885 | 2025-08-17 | 52003.6 | 2027-04-16 | 3881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0121-L | Carrier Roller No 1 LEFT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0121-R | Carrier Roller No 1 RIGHT | 10000 | 49885 | 2025-08-17 | 52003.6 | 2028-03-15 | 7881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0130-L | Track Frame LEFT | 18000 | 49885 | 2025-08-17 | 52003.6 | 2030-01-10 | 15881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0130-R | Track Frame RIGHT | 18000 | 49885 | 2025-08-17 | 52003.6 | 2030-01-10 | 15881.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0140 | Equalizer Bar | 14000 | 37227 | 2021-07-29 | 52003.6 | 2026-03-24 | -776.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N0144 | Pivot Shaft | 28000 | 24738 | 2018-02-14 | 52003.6 | 2026-07-28 | 734.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N1000 | Engine | 18000 | 38143 | 2022-01-15 | 52003.6 | 2027-05-08 | 4139.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N1002-01 | Engine Valve Adj - Initial | 500 | 38144 | 2022-02-05 | 52003.6 | 2023-05-11 | -13359.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N1004 | Engine Midlife | 9000 | 38143 | 2022-01-15 | 52003.6 | 2025-04-18 | -4860.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N1310 | Radiator | 18000 | 37227 | 2021-07-29 | 52003.6 | 2027-02-21 | 3223.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N1490 | Cam Shaft Inspection | 1500 | 49885 | 2025-08-17 | 52003.6 | 2026-04-06 | -618.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N2000 | Transmission | 18000 | 44119.17 | 2023-07-04 | 52003.6 | 2028-09-17 | 10115.57 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N2004 | Transmission Pump | 18000 | 44119.17 | 2023-07-04 | 52003.6 | 2028-09-17 | 10115.57 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N2050 | Torque Convertor | 18000 | 44119.17 | 2023-07-04 | 52003.6 | 2028-09-17 | 10115.57 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N3029 | Uni's T/C - Trans | 18000 | 44119.17 | 2023-07-04 | 52003.6 | 2028-09-17 | 10115.57 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N4110-L | Steering Clutch/Brk LEFT | 25000 | 26690.02 | 2018-09-19 | 52003.6 | 2026-05-02 | -313.58 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N4110-R | Steering Clutch/Brk RIGHT | 25000 | 24738 | 2018-02-14 | 52003.6 | 2025-11-20 | -2265.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N5000-L | Final Drive LEFT | 25000 | 26690.02 | 2018-09-19 | 52003.6 | 2026-05-02 | -313.58 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N5000-R | Final Drive RIGHT | 25000 | 24738 | 2018-02-14 | 52003.6 | 2025-11-20 | -2265.6 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7041 | Pump Cooling Fan Engine | 16000 | 51591 | 2026-04-07 | 52003.6 | 2029-12-17 | 15587.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7155 | Hyd Pump Main | 16000 | 42255.57 | 2022-12-07 | 52003.6 | 2027-10-31 | 6251.97 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7232 | Hyd Motor Engine Fan | 16000 | 47724.56 | 2024-12-08 | 52003.6 | 2029-01-29 | 11720.96 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7420-L | Hyd Cyl Blade Lift LEFT | 12000 | 50617 | 2025-12-20 | 52003.6 | 2028-10-28 | 10613.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7420-R | Hyd Cyl Blade Lift RIGHT | 12000 | 44229 | 2023-08-29 | 52003.6 | 2027-05-15 | 4225.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7421-L | Hyd Cyl Blade Tilt LEFT | 14000 | 47916 | 2025-01-14 | 52003.6 | 2028-08-31 | 9912.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 14000 | 47916 | 2025-01-14 | 52003.6 | 2028-08-31 | 9912.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7510-L | Hyd Cyl Ripper Lift LEFT | 23000 | 38143 | 2022-01-15 | 52003.6 | 2028-06-28 | 9139.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 23000 | 40731 | 2022-08-26 | 52003.6 | 2029-01-29 | 11727.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 26000 | 21491.68 | 2016-12-09 | 52003.6 | 2025-05-17 | -4511.92 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 26000 | 38143 | 2022-01-15 | 52003.6 | 2029-03-05 | 12139.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N8995 | Operator Seat | 10000 | 51303 | 2026-03-15 | 52003.6 | 2028-07-11 | 9299.4 | WA | Sanjiv Ridge
DZ6542 | Cat D10T | N9500 | Air Cond'r-Serv |  | 50098 | 2025-10-03 | 52003.6 | 2026-10-03 |  | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0050 | Blade Assembly | 20000 |  | 2024-08-27 | 7287 | 2029-04-21 | 12713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-08-27 | 7287 | 2029-08-26 |  | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0100-L | Track Group LEFT | 2000 | 4875 | 2025-10-28 | 7287 | 2026-04-24 | -412 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0100-R | Track Group RIGHT | 2000 | 4875 | 2025-10-28 | 7287 | 2026-04-24 | -412 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0104-L | Sprockets LEFT | 5000 |  | 2024-08-27 | 7287 | 2025-11-18 | -2287 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0104-R | Sprockets RIGHT | 5000 |  | 2024-08-27 | 7287 | 2025-11-18 | -2287 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0105-LF | Idler LFT FRONT | 6000 |  | 2024-08-27 | 7287 | 2026-02-10 | -1287 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0105-LR | Idler LFT REAR | 6000 |  | 2024-08-27 | 7287 | 2026-02-10 | -1287 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0105-RF | Idler RHT FRONT | 6000 |  | 2024-08-27 | 7287 | 2026-02-10 | -1287 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0105-RR | Idler RHT REAR | 6000 |  | 2024-08-27 | 7287 | 2026-02-10 | -1287 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-1L | Track Roller 1 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-1R | Track Roller 1 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-2L | Track Roller 2 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-2R | Track Roller 2 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-3L | Track Roller 3 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-3R | Track Roller 3 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-4L | Track Roller 4 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-4R | Track Roller 4 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-5L | Track Roller 5 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-5R | Track Roller 5 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-6L | Track Roller 6 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-6R | Track Roller 6 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-7L | Track Roller 7 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-7R | Track Roller 7 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-8L | Track Roller 8 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0111-8R | Track Roller 8 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0121-L | Carrier Roller No 1 LEFT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0121-R | Carrier Roller No 1 RIGHT | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0130-L | Track Frame LEFT | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0130-R | Track Frame RIGHT | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0140 | Equalizer Bar | 8000 |  | 2024-08-27 | 7287 | 2026-07-26 | 713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N0144 | Pivot Shaft | 32000 |  | 2024-08-27 | 7287 | 2032-01-16 | 24713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N1000 | Engine | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N1100 | Turbo Primary | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N1301 | Water Pump | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N1310 | Radiator | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N1312-L | Aftercooler Core - LEFT | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N2000 | Transmission | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N2002 | Oil Cooler - Transmission | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N2004 | Transmission Pump | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N2050 | Torque Convertor | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N3029 | Uni's T/C - Trans | 18000 |  | 2024-08-27 | 7287 | 2028-11-06 | 10713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N4110-L | Steering Clutch/Brk LEFT | 25000 |  | 2024-08-27 | 7287 | 2030-06-12 | 17713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N4110-R | Steering Clutch/Brk RIGHT | 25000 |  | 2024-08-27 | 7287 | 2030-06-12 | 17713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N5000-L | Final Drive LEFT | 25000 |  | 2024-08-27 | 7287 | 2030-06-12 | 17713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N5000-R | Final Drive RIGHT | 25000 |  | 2024-08-27 | 7287 | 2030-06-12 | 17713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N6360 | Brake Control Valve | 32000 |  | 2024-08-27 | 7287 | 2032-01-16 | 24713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7041 | Pump Cooling Fan Engine | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7113 | Motor Emergency Steering | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7121 | Pump Steering/Braking | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7155 | Hyd Pump Main | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7232 | Hyd Motor Engine Fan | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7420-L | Hyd Cyl Blade Lift LEFT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7420-R | Hyd Cyl Blade Lift RIGHT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7421-L | Hyd Cyl Blade Tilt LEFT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7510-L | Hyd Cyl Ripper Lift LEFT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 14000 |  | 2024-08-27 | 7287 | 2027-12-08 | 6713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7600 | Control Valve | 30000 |  | 2024-08-27 | 7287 | 2031-08-03 | 22713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N7610 | Hyd Cooler Core | 16000 |  | 2024-08-27 | 7287 | 2028-05-23 | 8713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N8995 | Operator Seat | 10000 |  | 2024-08-27 | 7287 | 2027-01-09 | 2713 | WA | Sanjiv Ridge
DZ6551 | Cat D9T | N9500 | Air Cond'r-Serv |  |  | 2025-07-22 | 7287 | 2026-07-22 |  | WA | Sanjiv Ridge
DZ6661 | Cat D10T2 | N0050 | Blade Assembly | 20000 |  | 2025-01-08 | 5903.7 | 2031-10-07 | 14096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 5903.7 | 2030-01-07 |  | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0100-L | Track Group LEFT | 2000 | 3008 | 2025-10-05 | 5903.7 | 2026-01-24 | -895.7 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0100-R | Track Group RIGHT | 2000 | 3008 | 2025-10-05 | 5903.7 | 2026-01-24 | -895.7 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0104-L | Sprockets LEFT | 5000 |  | 2025-01-08 | 5903.7 | 2026-01-26 | -903.7 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0104-R | Sprockets RIGHT | 5000 |  | 2025-01-08 | 5903.7 | 2026-01-26 | -903.7 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0105-LF | Idler LFT FRONT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0105-LR | Idler LFT REAR | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0105-RF | Idler RHT FRONT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0105-RR | Idler RHT REAR | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-1L | Track Roller 1 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-1R | Track Roller 1 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-2L | Track Roller 2 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-2R | Track Roller 2 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-3L | Track Roller 3 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-3R | Track Roller 3 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-4L | Track Roller 4 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-4R | Track Roller 4 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-5L | Track Roller 5 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-5R | Track Roller 5 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-6L | Track Roller 6 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-6R | Track Roller 6 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-7L | Track Roller 7 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-7R | Track Roller 7 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-8L | Track Roller 8 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0111-8R | Track Roller 8 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0121-L | Carrier Roller No 1 LEFT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0121-R | Carrier Roller No 1 RIGHT | 8500 |  | 2025-01-08 | 5903.7 | 2027-05-24 | 2596.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0130-L | Track Frame LEFT | 21000 |  | 2025-01-08 | 5903.7 | 2032-02-23 | 15096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0130-R | Track Frame RIGHT | 21000 |  | 2025-01-08 | 5903.7 | 2032-02-23 | 15096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0140 | Equalizer Bar | 10000 |  | 2025-01-08 | 5903.7 | 2027-12-18 | 4096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N0144 | Pivot Shaft | 36000 |  | 2025-01-08 | 5903.7 | 2037-11-06 | 30096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1000 | Engine | 12000 |  | 2025-10-06 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1002 | Engine Valve Adj | 4000 | 3957 | 2025-12-19 | 5903.7 | 2027-03-09 | 2053.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1002-01 | Engine Valve Adj - Initial | 500 | 695 | 2025-04-06 | 5903.7 | 2024-08-12 | -4708.7 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1004 | Engine Midlife | 6000 |  | 2025-01-08 | 5903.7 | 2026-06-10 | 96.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1310 | Radiator | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1312-LW | Aftercooler Core - LOWER | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1312-UP | Aftercooler Core - UPPER | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N1490 | Cam Shaft Inspection | 1000 | 3957 | 2025-12-19 | 5903.7 | 2026-01-17 | -946.7 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N2000 | Transmission | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N2002 | Oil Cooler - Transmission | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N2004 | Transmission Pump | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N2050 | Torque Convertor | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N4110-L | Steering Clutch/Brk LEFT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N4110-R | Steering Clutch/Brk RIGHT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N5000-L | Final Drive LEFT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N5000-R | Final Drive RIGHT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N6360 | Brake Control Valve | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7041 | Pump Cooling Fan Engine | 28000 |  | 2025-01-08 | 5903.7 | 2034-10-22 | 22096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7070-L | Pump Implement LEFT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7070-R | Pump Implement RIGHT | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7232 | Hyd Motor Engine Fan | 28000 |  | 2025-01-08 | 5903.7 | 2034-10-22 | 22096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7421-L | Hyd Cyl Blade Tilt LEFT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7421-R | Hyd Cyl Blade Tilt RIGHT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7510-L | Hyd Cyl Ripper Lift LEFT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7510-R | Hyd Cyl Ripper Lift RIGHT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7514-L | Hyd Cyl Ripper Pitch LEFT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 8000 |  | 2025-01-08 | 5903.7 | 2027-03-15 | 2096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7600 | Control Valve | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N7610 | Hyd Cooler Core | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 5903.7 | 2028-09-21 | 6096.3 | WA | McPhee Creek
DZ6661 | Cat D10T2 | N9500 | Air Cond'r-Serv |  | 4234 | 2026-01-08 | 5903.7 | 2027-01-08 |  | WA | McPhee Creek
DZ8029 | Cat D10T2 | N0066 | Fire Suppression Sys Cylinder |  | 18011.3 | 2021-11-15 | 31311 | 2026-11-14 |  | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0101-L | Track Chain LEFT | 8000 | 30378 | 2026-03-22 | 31226 | 2027-10-15 | 7152 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0101-R | Track Chain RIGHT | 8000 | 31167 | 2026-05-15 | 31311 | 2027-12-10 | 7856 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0102-L | Trk Chn Pin & Bush Trn LEFT | 4000 | 30378 | 2026-03-22 | 31226 | 2027-01-03 | 3152 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 4000 | 31167 | 2026-05-15 | 31311 | 2027-02-27 | 3856 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0103-L | Track Plates LEFT | 8000 | 30378 | 2026-03-22 | 31226 | 2027-10-15 | 7152 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0103-R | Track Plates RIGHT | 8000 | 31167 | 2026-05-15 | 31311 | 2027-12-10 | 7856 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0104-L | Sprockets LEFT | 4000 | 23635 | 2024-01-01 | 31311 | 2025-09-07 | -3676 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0104-R | Sprockets RIGHT | 4000 | 23635 | 2024-01-01 | 31311 | 2025-09-07 | -3676 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0105-LF | Idler LFT FRONT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0105-LR | Idler LFT REAR | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0105-RF | Idler RHT FRONT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0105-RR | Idler RHT REAR | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-1L | Track Roller 1 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-1R | Track Roller 1 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-2L | Track Roller 2 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-2R | Track Roller 2 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-3L | Track Roller 3 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-3R | Track Roller 3 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-4L | Track Roller 4 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-4R | Track Roller 4 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-5L | Track Roller 5 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-5R | Track Roller 5 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-6L | Track Roller 6 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-6R | Track Roller 6 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-7L | Track Roller 7 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-7R | Track Roller 7 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-8L | Track Roller 8 LEFT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0111-8R | Track Roller 8 RIGHT | 8000 | 20607 | 2023-05-06 | 31311 | 2025-11-16 | -2704 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0130-L | Track Frame LEFT | 36000 | 20607 | 2023-05-06 | 31311 | 2031-05-09 | 25296 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0130-R | Track Frame RIGHT | 36000 | 20607 | 2023-05-06 | 31311 | 2031-05-09 | 25296 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0134-L | Track Adjuster LEFT | 18000 | 20607 | 2023-05-06 | 31311 | 2027-10-31 | 7296 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0134-R | Track Adjuster RIGHT | 18000 | 30777 | 2026-04-26 | 31311 | 2029-10-27 | 17466 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0139-L | Track Frame Mid Life LEFT | 18000 | 20607 | 2023-05-06 | 31311 | 2027-10-31 | 7296 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0139-R | Track Frame Mid Life RIGHT | 18000 | 20607 | 2023-05-06 | 31311 | 2027-10-31 | 7296 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0140 | Equalizer Bar | 18000 | 29857 | 2026-02-01 | 31311 | 2029-08-22 | 16546 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0145 | Pivot Shaft Brgs | 18000 | 19914 | 2023-05-05 | 31311 | 2027-09-12 | 6603 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N0520 | Pre Lube Pump | 18000 | 18010 | 2022-09-06 | 31311 | 2027-04-29 | 4699 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1000 | Engine | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1002 | Engine Valve Adj | 4000 | 28840 | 2025-11-05 | 31311 | 2026-09-14 | 1529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1002-01 | Engine Valve Adj - Initial | 500 | 18318 | 2022-10-04 | 31311 | 2023-12-18 | -12493 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1100-L | Turbo Primary LEFT | 9000 | 28840 | 2025-11-05 | 31311 | 2027-09-06 | 6529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1100-R | Turbo Primary RIGHT | 9000 | 28840 | 2025-11-05 | 31311 | 2027-09-06 | 6529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1202 | Fuel Transfer Pump | 9000 | 28840 | 2025-11-05 | 31311 | 2027-09-06 | 6529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1300 | Cooling Sys Service | 9000 | 28840 | 2025-11-05 | 31311 | 2027-09-06 | 6529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1301 | Water Pump | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1310 | Radiator | 18000 | 18071 | 2022-09-06 | 31311 | 2027-05-03 | 4760 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1312-LW | Aftercooler Core - LOWER | 18000 | 18071 | 2022-09-06 | 31311 | 2027-05-03 | 4760 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1312-UP | Aftercooler Core - UPPER | 18000 | 18071 | 2022-09-06 | 31311 | 2027-05-03 | 4760 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1320 | Cooling Fan Engine | 36000 | 18011 | 2022-09-06 | 31311 | 2030-11-04 | 22700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N1490 | Cam Shaft Inspection | 2000 | 28840 | 2025-11-05 | 31311 | 2026-04-24 | -471 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N2000 | Transmission | 14000 | 30281 | 2026-03-04 | 31311 | 2028-12-09 | 12970 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N2002 | Oil Cooler - Transmission | 14000 | 30281 | 2026-03-07 | 31311 | 2028-12-09 | 12970 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N2020 | Powertrain Pump | 7000 | 24807 | 2025-02-11 | 31311 | 2026-07-02 | 496 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N2050 | Torque Convertor | 18000 | 14650 | 2021-11-14 | 31311 | 2026-09-01 | 1339 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N2450 | Drv Cpling Fan Pump-Trans Pump | 7000 | 23635 | 2023-12-14 | 31311 | 2026-04-09 | -676 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N3016 | Drv Shaft Fan Pump-Trans Pump | 14000 | 28840 | 2025-11-05 | 31311 | 2028-08-29 | 11529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N3028 | Drive Shaft T/C - Trans | 18000 | 18071 | 2022-09-07 | 31311 | 2027-05-03 | 4760 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N3029 | Uni's T/C - Trans | 9000 | 28840 | 2025-11-05 | 31311 | 2027-09-06 | 6529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N4000 | Bevel Gear | 14000 | 30281 | 2026-03-04 | 31311 | 2028-12-09 | 12970 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N4110-L | Steering Clutch/Brk LEFT | 18000 | 14650 | 2021-11-13 | 31311 | 2026-09-01 | 1339 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N4110-R | Steering Clutch/Brk RIGHT | 18000 | 14650 | 2021-11-13 | 31311 | 2026-09-01 | 1339 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N5000-L | Final Drive LEFT | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N5000-R | Final Drive RIGHT | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N6360 | Brake Control Valve | 36000 | 14650 | 2021-11-16 | 31311 | 2030-03-09 | 19339 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7041 | Pump Cooling Fan Engine | 18000 | 29608 | 2025-12-28 | 31311 | 2029-08-04 | 16297 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7070-L | Pump Implement LEFT | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7070-R | Pump Implement RIGHT | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7100 | Pump Charge | 9000 | 29979 | 2026-02-06 | 31311 | 2027-11-27 | 7668 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7232 | Hyd Motor Engine Fan | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 28840 | 2025-11-05 | 31311 | 2027-06-27 | 5529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 28840 | 2025-11-05 | 31311 | 2027-06-27 | 5529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7421-L | Hyd Cyl Blade Tilt LEFT | 12000 | 30378 | 2026-03-22 | 31311 | 2028-07-27 | 11067 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7421-R | Hyd Cyl Blade Tilt RIGHT | 12000 | 18071 | 2022-09-06 | 31311 | 2026-02-28 | -1240 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7510-L | Hyd Cyl Ripper Lift LEFT | 25000 | 28244 | 2025-09-21 | 31311 | 2030-09-11 | 21933 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7510-R | Hyd Cyl Ripper Lift RIGHT | 25000 |  |  | 31311 | 2025-03-04 | -6311 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7514-L | Hyd Cyl Ripper Pitch LEFT | 25000 | 28244 | 2025-09-21 | 31311 | 2030-09-11 | 21933 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 25000 | 27713 | 2025-08-15 | 31311 | 2030-08-04 | 21402 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7600 | Control Valve | 30000 |  |  | 31311 | 2026-02-23 | -1311 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N7610 | Hyd Cooler Core | 18000 | 18071 | 2022-09-06 | 31311 | 2027-05-03 | 4760 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N8000 | Main Frame/Chassis | 36000 |  |  | 31311 | 2027-04-28 | 4689 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N8995 | Operator Seat | 6000 | 23165 | 2023-12-09 | 31311 | 2025-12-28 | -2146 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9020 | Alternator | 9000 | 26075 | 2025-04-27 | 31311 | 2027-02-21 | 3764 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9050 | Starter Motor | 9000 | 28840 | 2025-11-05 | 31311 | 2027-09-06 | 6529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9500 | Air Cond'r-Serv | 6000 | 28840 | 2025-11-05 | 31311 | 2027-02-04 | 3529 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9500-MA | Air Cond'r-Serv - MAJOR | 18000 | 18012 | 2022-09-07 | 31311 | 2027-04-29 | 4701 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9501 | A/C Compressor | 9000 | 31134 | 2026-05-16 | 31311 | 2028-02-17 | 8823 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9502 | A/C Condenser | 18000 | 18011 | 2022-09-06 | 31311 | 2027-04-29 | 4700 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9998 | Extended Life Rebuild | 36000 |  |  | 31311 | 2027-04-28 | 4689 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9998-01 | Extended Life Rebuild ONE | 54000 |  |  | 31311 | 2030-11-04 | 22689 | WA | Iron Bridge
DZ8029 | Cat D10T2 | N9998-02 | Extended Life Rebuild TWO | 72000 |  | 2018-10-05 | 31311 | 2034-05-12 | 40689 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0066 | Fire Suppression Sys Cylinder |  | 20122 | 2023-03-10 | 34679 | 2028-03-08 |  | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0101-L | Track Chain LEFT | 8000 | 34081 | 2026-04-14 | 34679 | 2027-11-08 | 7402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0101-R | Track Chain RIGHT | 8000 | 34081 | 2026-04-13 | 34679 | 2027-11-08 | 7402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0102-L | Trk Chn Pin & Bush Trn LEFT | 4000 | 34081 | 2026-04-14 | 34679 | 2027-01-26 | 3402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 4000 | 34081 | 2026-04-13 | 34679 | 2027-01-26 | 3402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0103-L | Track Plates LEFT | 8000 | 34081 | 2026-04-14 | 34679 | 2027-11-08 | 7402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0103-R | Track Plates RIGHT | 8000 | 34081 | 2026-04-13 | 34679 | 2027-11-08 | 7402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0104-L | Sprockets LEFT | 4000 | 26697 | 2024-08-13 | 34679 | 2025-08-17 | -3982 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0104-R | Sprockets RIGHT | 4000 | 26706 | 2024-08-13 | 34679 | 2025-08-17 | -3973 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0105-LF | Idler LFT FRONT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0105-LR | Idler LFT REAR | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0105-RF | Idler RHT FRONT | 8000 | 31621 | 2025-11-19 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0105-RR | Idler RHT REAR | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-1L | Track Roller 1 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-1R | Track Roller 1 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-2L | Track Roller 2 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-2R | Track Roller 2 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-3L | Track Roller 3 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-3R | Track Roller 3 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-4L | Track Roller 4 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-4R | Track Roller 4 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-5L | Track Roller 5 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-5R | Track Roller 5 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-6L | Track Roller 6 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-6R | Track Roller 6 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-7L | Track Roller 7 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-7R | Track Roller 7 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-8L | Track Roller 8 LEFT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0111-8R | Track Roller 8 RIGHT | 8000 | 31621 | 2025-11-18 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0130-L | Track Frame LEFT | 36000 | 31621 | 2025-11-18 | 34679 | 2032-11-05 | 32942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0130-R | Track Frame RIGHT | 36000 | 31621 | 2025-11-18 | 34679 | 2032-11-05 | 32942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0134-L | Track Adjuster LEFT | 18000 | 31621 | 2025-11-18 | 34679 | 2029-04-29 | 14942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0134-R | Track Adjuster RIGHT | 18000 | 31621 | 2025-11-18 | 34679 | 2029-04-29 | 14942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0139-L | Track Frame Mid Life LEFT | 18000 | 31621 | 2025-11-19 | 34679 | 2029-04-29 | 14942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0139-R | Track Frame Mid Life RIGHT | 18000 | 31621 | 2025-11-19 | 34679 | 2029-04-29 | 14942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0140 | Equalizer Bar | 18000 | 26344 | 2024-07-16 | 34679 | 2028-04-17 | 9665 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0145 | Pivot Shaft Brgs | 18000 | 26086 | 2024-06-25 | 34679 | 2028-03-30 | 9407 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N0520 | Pre Lube Pump | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1000 | Engine | 18000 | 17615 | 2022-08-17 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1002 | Engine Valve Adj | 4000 | 29305 | 2025-06-14 | 34679 | 2026-02-19 | -1374 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1002-01 | Engine Valve Adj - Initial | 500 | 18076 | 2022-09-26 | 34679 | 2023-04-04 | -16103 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1100-L | Turbo Primary LEFT | 9000 | 27664 | 2024-10-12 | 34679 | 2026-10-17 | 1985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1100-R | Turbo Primary RIGHT | 9000 | 27664 | 2024-10-12 | 34679 | 2026-10-17 | 1985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1202 | Fuel Transfer Pump | 9000 | 27664 | 2024-10-14 | 34679 | 2026-10-17 | 1985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1300 | Cooling Sys Service | 9000 | 27664 | 2024-10-13 | 34679 | 2026-10-17 | 1985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1301 | Water Pump | 18000 | 17615 | 2022-08-17 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1310 | Radiator | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1312-LW | Aftercooler Core - LOWER | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1312-UP | Aftercooler Core - UPPER | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1320 | Cooling Fan Engine | 36000 | 17615 | 2022-08-21 | 34679 | 2030-02-09 | 18936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N1490 | Cam Shaft Inspection | 2000 | 29305 | 2025-06-14 | 34679 | 2025-09-29 | -3374 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N2000 | Transmission | 14000 | 27664 | 2024-10-18 | 34679 | 2027-10-09 | 6985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N2002 | Oil Cooler - Transmission | 14000 | 17615 | 2022-08-21 | 34679 | 2025-10-26 | -3064 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N2020 | Powertrain Pump | 7000 | 27664 | 2024-10-12 | 34679 | 2026-06-03 | -15 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N2050 | Torque Convertor | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N2450 | Drv Cpling Fan Pump-Trans Pump | 7000 | 31352 | 2025-10-27 | 34679 | 2027-02-14 | 3673 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N3016 | Drv Shaft Fan Pump-Trans Pump | 14000 | 24761 | 2024-03-18 | 34679 | 2027-03-16 | 4082 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N3028 | Drive Shaft T/C - Trans | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N3029 | Uni's T/C - Trans | 9000 | 27664 | 2024-10-13 | 34679 | 2026-10-17 | 1985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N4000 | Bevel Gear | 14000 | 27664 | 2024-10-18 | 34679 | 2027-10-09 | 6985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N4110-L | Steering Clutch/Brk LEFT | 18000 | 34119 | 2026-04-21 | 34679 | 2029-10-25 | 17440 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N4110-R | Steering Clutch/Brk RIGHT | 18000 | 28503 | 2025-04-09 | 34679 | 2028-09-19 | 11824 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N5000-L | Final Drive LEFT | 18000 | 34119 | 2026-04-21 | 34679 | 2029-10-25 | 17440 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N5000-R | Final Drive RIGHT | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N6360 | Brake Control Valve | 36000 | 28503 | 2025-04-09 | 34679 | 2032-03-27 | 29824 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7041 | Pump Cooling Fan Engine | 18000 | 31363 | 2025-10-27 | 34679 | 2029-04-11 | 14684 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7070-L | Pump Implement LEFT | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7070-R | Pump Implement RIGHT | 18000 | 17615 | 2022-08-21 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7100 | Pump Charge | 9000 | 27664 | 2024-10-14 | 34679 | 2026-10-17 | 1985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7232 | Hyd Motor Engine Fan | 18000 | 19881 | 2023-02-21 | 34679 | 2027-01-12 | 3202 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 31621 | 2025-11-16 | 34679 | 2027-05-16 | 4942 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 27664 | 2024-10-14 | 34679 | 2026-08-06 | 985 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7421-L | Hyd Cyl Blade Tilt LEFT | 12000 | 28486 | 2025-04-02 | 34679 | 2027-07-17 | 5807 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7421-R | Hyd Cyl Blade Tilt RIGHT | 12000 | 29177 | 2025-05-21 | 34679 | 2027-09-04 | 6498 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7510-L | Hyd Cyl Ripper Lift LEFT | 25000 | 32767 | 2026-01-28 | 34679 | 2030-12-02 | 23088 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7510-R | Hyd Cyl Ripper Lift RIGHT | 25000 |  |  | 34679 | 2024-07-06 | -9679 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7514-L | Hyd Cyl Ripper Pitch LEFT | 25000 |  |  | 34679 | 2024-07-09 | -9679 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 25000 |  |  | 34679 | 2024-07-09 | -9679 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7600 | Control Valve | 30000 | 14274 | 2021-10-17 | 34679 | 2028-04-12 | 9595 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N7610 | Hyd Cooler Core | 18000 | 17615 | 2022-08-12 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N8000 | Main Frame/Chassis | 36000 |  |  | 34679 | 2026-08-30 | 1321 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N8995 | Operator Seat | 6000 | 34081 | 2026-02-07 | 34679 | 2027-04-20 | 4580 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9020 | Alternator | 9000 | 34081 | 2026-04-12 | 34679 | 2028-01-18 | 8402 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9050 | Starter Motor | 9000 | 29657 | 2025-07-15 | 34679 | 2027-03-08 | 3978 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9500 | Air Cond'r-Serv | 6000 | 31352 | 2025-10-26 | 34679 | 2026-12-05 | 2673 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9500-MA | Air Cond'r-Serv - MAJOR | 18000 | 17617.9 | 2022-08-17 | 34679 | 2026-08-03 | 938.9 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9501 | A/C Compressor | 9000 | 29371 | 2025-06-21 | 34679 | 2027-02-16 | 3692 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9502 | A/C Condenser | 18000 | 17615 | 2022-08-10 | 34679 | 2026-08-03 | 936 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9998 | Extended Life Rebuild | 36000 |  |  | 34679 | 2026-08-30 | 1321 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9998-01 | Extended Life Rebuild ONE | 54000 |  |  | 34679 | 2030-03-08 | 19321 | WA | Iron Bridge
DZ8083 | Cat D10T2 | N9998-02 | Extended Life Rebuild TWO | 72000 |  | 2017-10-25 | 34679 | 2033-09-14 | 37321 | WA | Iron Bridge
EX2619 | Cat 6060 | N0010 | Excavator Boom | 32000 |  |  | 23424 | 2027-09-04 | 8576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0060 | Stick | 32000 |  |  | 23424 | 2027-09-04 | 8576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0066 | Fire Suppression Sys Cylinder |  | 22835 | 2026-04-29 | 23424 | 2031-04-28 |  | WA | Iron Bridge
EX2619 | Cat 6060 | N0091-01 | Grease Pump POS 01 | 18000 | 19637 | 2025-11-10 | 23424 | 2028-07-04 | 14213 | WA | Iron Bridge
EX2619 | Cat 6060 | N0091-02 | Grease Pump POS 02 | 18000 |  |  | 23424 | 2025-08-08 | -5424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0100-L | Track Group LEFT | 24000 | 20210 | 2025-12-11 | 23424 | 2029-06-25 | 20786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0100-R | Track Group RIGHT | 24000 | 20210 | 2025-12-11 | 23424 | 2029-06-25 | 20786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0104-L | Sprockets LEFT | 18000 | 20210 | 2025-12-09 | 23424 | 2028-08-04 | 14786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0104-R | Sprockets RIGHT | 18000 | 20210 | 2025-12-09 | 23424 | 2028-08-04 | 14786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0105-L | Idler LEFT | 12000 | 17666 | 2025-07-26 | 23424 | 2027-04-30 | 6242 | WA | Iron Bridge
EX2619 | Cat 6060 | N0105-R | Idler RIGHT | 12000 | 20210 | 2025-12-09 | 23424 | 2027-09-15 | 8786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-1L | Track Roller 1 LEFT | 12000 |  |  | 23424 | 2024-09-17 | -11424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-1R | Track Roller 1 RIGHT | 12000 |  |  | 23424 | 2024-09-17 | -11424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-2L | Track Roller 2 LEFT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-2R | Track Roller 2 RIGHT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-3L | Track Roller 3 LEFT | 24000 |  |  | 23424 | 2026-07-01 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-3R | Track Roller 3 RIGHT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-4L | Track Roller 4 LEFT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-4R | Track Roller 4 RIGHT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-5L | Track Roller 5 LEFT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-5R | Track Roller 5 RIGHT | 24000 |  |  | 23424 | 2026-07-01 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-6L | Track Roller 6 LEFT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-6R | Track Roller 6 RIGHT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-7L | Track Roller 7 LEFT | 12000 |  |  | 23424 | 2024-09-17 | -11424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0111-7R | Track Roller 7 RIGHT | 12000 |  |  | 23424 | 2024-09-17 | -11424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0121-L | Carrier Roller No 1 LEFT | 12000 |  |  | 23424 | 2024-09-17 | -11424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0121-R | Carrier Roller No 1 RIGHT | 12000 |  |  | 23424 | 2024-09-17 | -11424 | WA | Iron Bridge
EX2619 | Cat 6060 | N0122-L | Carrier Roller No 2 LEFT | 12000 | 16932 | 2025-06-15 | 23424 | 2027-03-22 | 5508 | WA | Iron Bridge
EX2619 | Cat 6060 | N0122-R | Carrier Roller No 2 RIGHT | 12000 | 18384 | 2025-09-01 | 23424 | 2027-06-08 | 6960 | WA | Iron Bridge
EX2619 | Cat 6060 | N0155-L | Track Tension Cyl LEFT | 12000 | 20210 | 2025-12-10 | 23424 | 2027-09-15 | 8786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0155-R | Track Tension Cyl RIGHT | 12000 | 20210 | 2025-12-10 | 23424 | 2027-09-15 | 8786 | WA | Iron Bridge
EX2619 | Cat 6060 | N0162-L | Track Accumulator LEFT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0162-R | Track Accumulator RIGHT | 24000 |  |  | 23424 | 2026-06-28 | 576 | WA | Iron Bridge
EX2619 | Cat 6060 | N0520-E1 | Pre Lube Pump EN1 | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N0520-E2 | Pre Lube Pump EN2 | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N0555-E1 | Cooler Fan Brgs EN1 | 15000 | 9161 | 2023-11-03 | 23424 | 2026-07-07 | 737 | WA | Iron Bridge
EX2619 | Cat 6060 | N0555-E2 | Cooler Fan Brgs EN2 | 15000 | 15426 | 2025-03-16 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N0555-FL | Cooler Fan Hyd Brgs FRNT LOWER | 15000 | 16936 | 2025-05-16 | 23424 | 2027-08-31 | 8512 | WA | Iron Bridge
EX2619 | Cat 6060 | N0555-FU | Cooler Fan Hyd Brgs FRNT UPPER | 15000 | 15426 | 2025-03-15 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N0555-RL | Cooler Fan Hyd Brgs REAR LOWER | 15000 | 15426 | 2025-03-16 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N0555-RU | Cooler Fan Hyd Brgs REAR UPPER | 15000 | 15426 | 2025-03-16 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N1000-01 | Engine EN1(L/F) | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1000-02 | Engine EN2(R/RE) | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1002-1 | Engine Valve Adj EN1 | 4000 | 19070 | 2025-10-09 | 23424 | 2026-05-09 | -354 | WA | Iron Bridge
EX2619 | Cat 6060 | N1002-1I | Engine Valve Adj Initial EN1 | 50 | 19131 | 2025-10-16 | 23424 | 2025-10-11 | -4243 | WA | Iron Bridge
EX2619 | Cat 6060 | N1002-2 | Engine Valve Adj EN2 | 4000 | 19070 | 2025-10-09 | 23424 | 2026-05-09 | -354 | WA | Iron Bridge
EX2619 | Cat 6060 | N1002-2I | Engine Valve Adj Initial EN2 | 50 | 19131 | 2025-10-16 | 23424 | 2025-10-11 | -4243 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-01 | Turbo Primary EN1 LHF | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-02 | Turbo Primary EN1 RHF | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-03 | Turbo Primary EN1 LHR | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-04 | Turbo Primary EN1 RHR | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-05 | Turbo Primary EN2 LHF | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-06 | Turbo Primary EN2 RHF | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-07 | Turbo Primary EN2 LHR | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1100-08 | Turbo Primary EN2 RHR | 18000 | 19070 | 2025-10-09 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1202-E1 | Fuel Transfer Pump EN 1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1202-E2 | Fuel Transfer Pump EN2 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1210-E1 | Fuel Injectors EN1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1210-E2 | Fuel Injectors EN2 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1300-E1 | Cooling Sys Service EN1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1300-E2 | Cooling Sys Service EN2 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1310-E1 | Radiator EN1 | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N1310-E2 | Radiator EN2 | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N1320-E1 | Cooling Fan Engine EN1 | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N1320-E2 | Cooling Fan Engine EN2 | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N1403-E1 | Jockey Pulley Brgs EN1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N1403-E2 | Jockey Pulley Brgs EN2 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N2400-E1 | Drv Coupling EN1 | 18000 | 19070 | 2025-10-04 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N2400-E2 | Drv Coupling EN2 | 18000 | 19070 | 2025-10-04 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N3200-E1 | Splitter Box EN1 | 18000 | 19070 | 2025-10-06 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N3200-E2 | Splitter Box EN2 | 18000 | 19070 | 2025-10-06 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N3201-E1 | Pump Spltr Box Lube EN1 | 18000 | 19070 | 2025-10-06 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N3201-E2 | Pump Spltr Box Lube EN2 | 18000 | 19070 | 2025-10-06 | 23424 | 2028-06-04 | 13646 | WA | Iron Bridge
EX2619 | Cat 6060 | N3205-F | Cooler Spltr Box FRONT | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N3205-RE | Cooler Spltr Box REAR | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N3220-LF | Swing Box LFT FRONT | 20000 | 22553 | 2026-04-11 | 23424 | 2029-03-27 | 19129 | WA | Iron Bridge
EX2619 | Cat 6060 | N3220-LR | Swing Box LFT REAR | 20000 | 22553 | 2026-04-11 | 23424 | 2029-03-27 | 19129 | WA | Iron Bridge
EX2619 | Cat 6060 | N3220-RF | Swing Box RHT FRONT | 20000 | 22553 | 2026-04-10 | 23424 | 2029-03-27 | 19129 | WA | Iron Bridge
EX2619 | Cat 6060 | N3220-RR | Swing Box RHT REAR | 20000 | 22553 | 2026-04-10 | 23424 | 2029-03-27 | 19129 | WA | Iron Bridge
EX2619 | Cat 6060 | N5000-L | Final Drive LEFT | 36000 |  |  | 23424 | 2028-04-07 | 12576 | WA | Iron Bridge
EX2619 | Cat 6060 | N5000-R | Final Drive RIGHT | 36000 |  |  | 23424 | 2028-04-07 | 12576 | WA | Iron Bridge
EX2619 | Cat 6060 | N5002-L | Final Drive Midlife LEFT | 18000 |  |  | 23424 | 2025-08-08 | -5424 | WA | Iron Bridge
EX2619 | Cat 6060 | N5002-R | Final Drive Midlife RIGHT | 18000 |  |  | 23424 | 2025-08-08 | -5424 | WA | Iron Bridge
EX2619 | Cat 6060 | N6015-LF | Brake Travel LFT FRONT | 18000 | 15426 | 2025-03-18 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N6015-LR | Brake Travel LFT REAR | 18000 | 15426 | 2025-03-18 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N6015-RF | Brake Travel RHT FRONT | 18000 | 15426 | 2025-03-21 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N6015-RR | Brake Travel RHT REAR | 18000 | 21272 | 2026-02-03 | 23424 | 2028-10-01 | 15848 | WA | Iron Bridge
EX2619 | Cat 6060 | N7001 | Hydraulic Tune | 6000 | 22553 | 2026-04-14 | 23424 | 2027-03-01 | 5129 | WA | Iron Bridge
EX2619 | Cat 6060 | N7002 | Boom Arch Hoses | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-07 | Hyd Hose Boom Cylinder | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-08 | Hyd Hose Stick Cylinder | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-09 | Hyd Hose Bucket Cylinder | 10000 | 9161 | 2023-11-24 | 23424 | 2025-10-12 | -4263 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-12 | Hyd Hose Swing Pump Swing Mtr | 10000 | 19070 | 2025-10-05 | 23424 | 2027-03-29 | 5646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-17 | Hyd Hose Eng Fan Mtr | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-19 | Hyd Hose Bucket Supply | 10000 | 9161 | 2023-07-15 | 23424 | 2025-10-12 | -4263 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-20 | Hyd Hose Clam Supply | 10000 | 20210 | 2025-12-10 | 23424 | 2027-05-30 | 6786 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-21 | Hyd Hose Clam Cylinder | 5000 | 15426 | 2025-03-18 | 23424 | 2025-12-17 | -2998 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-22 | Hyd Hose Work Pumps-Rot Joint | 15000 | 15426 | 2025-03-19 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-23 | Hyd Hose MCV Return | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-24 | Hyd Hose Cooler Pumps-Coolers | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-25 | Hyd Hose Oil Suction | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-30 | Hyd Hose Rotary Joint to Valve | 18000 |  |  | 23424 | 2025-08-08 | -5424 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-31 | Hyd Hose Valve to Trvl Mtr LH | 18000 | 9161 | 2023-10-13 | 23424 | 2026-12-16 | 3737 | WA | Iron Bridge
EX2619 | Cat 6060 | N7004-32 | Hyd Hose Valve to Trvl Mtr RH | 18000 | 9161 | 2023-10-13 | 23424 | 2026-12-16 | 3737 | WA | Iron Bridge
EX2619 | Cat 6060 | N7032-01 | Pump Cooler Fan Hyd POS 1 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7032-02 | Pump Cooler Fan Hyd POS 2 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7032-03 | Pump Cooler Fan Hyd POS 3 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7032-04 | Pump Cooler Fan Hyd POS 4 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7041-E1 | Pump Cooling Fan Eng EN1 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7041-E2 | Pump Cooling Fan Eng EN2 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7044-FL | Cooler Fan Hyd FRONT LOWER | 30000 | 21995 | 2026-03-14 | 23424 | 2030-08-19 | 28571 | WA | Iron Bridge
EX2619 | Cat 6060 | N7044-FU | Cooler Fan Hyd FRONT UPPER | 30000 | 21995 | 2026-03-14 | 23424 | 2030-08-19 | 28571 | WA | Iron Bridge
EX2619 | Cat 6060 | N7044-RL | Cooler Fan Hyd REAR LOWER | 30000 | 21995 | 2026-03-14 | 23424 | 2030-08-19 | 28571 | WA | Iron Bridge
EX2619 | Cat 6060 | N7044-RU | Cooler Fan Hyd REAR UPPER | 30000 | 21995 | 2026-03-14 | 23424 | 2030-08-19 | 28571 | WA | Iron Bridge
EX2619 | Cat 6060 | N7071-05 | Pump Imp 1&2 | 15000 | 14875 | 2025-02-08 | 23424 | 2027-05-12 | 6451 | WA | Iron Bridge
EX2619 | Cat 6060 | N7073-05 | Pump Imp 3&4 | 15000 | 14377 | 2025-01-06 | 23424 | 2027-04-15 | 5953 | WA | Iron Bridge
EX2619 | Cat 6060 | N7075-05 | Pump Imp 5&6 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 15000 | 11620 | 2024-08-05 | 23424 | 2026-11-17 | 3196 | WA | Iron Bridge
EX2619 | Cat 6060 | N7090-01 | Pump Pilot/Servo POS 1 | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7090-02 | Pump Pilot/Servo POS 2 | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7090-03 | Pump Pilot/Servo POS 3 | 15000 | 15426 | 2025-03-17 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7090-04 | Pump Pilot/Servo POS 4 | 15000 | 14412 | 2025-01-10 | 23424 | 2027-04-17 | 5988 | WA | Iron Bridge
EX2619 | Cat 6060 | N7092-E1 | Pump Replenishing EN1 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7092-E2 | Pump Replenishing EN2 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7095-E1 | Pump Aircon Drive EN1 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7095-E2 | Pump Aircon Drive EN2 | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7130-01 | Pump Swing POS 1 | 10000 | 19070 | 2025-10-06 | 23424 | 2027-03-29 | 5646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7130-02 | Pump Swing POS 2 | 10000 | 19070 | 2025-10-06 | 23424 | 2027-03-29 | 5646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7130-03 | Pump Swing POS 3 | 10000 | 19070 | 2025-10-06 | 23424 | 2027-03-29 | 5646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7130-04 | Pump Swing POS 4 | 10000 | 19070 | 2025-10-06 | 23424 | 2027-03-29 | 5646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7201-L | Hyd Motor Air Con LEFT | 9000 | 19070 | 2025-10-05 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7201-R | Hyd Motor Air Con RIGHT | 9000 | 19070 | 2025-10-06 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N7232-E1 | Hyd Motor Engine Fan EN1 | 15000 | 9161 | 2023-11-03 | 23424 | 2026-07-07 | 737 | WA | Iron Bridge
EX2619 | Cat 6060 | N7232-E2 | Hyd Motor Engine Fan EN2 | 15000 | 15426 | 2025-03-16 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7234-FL | Hyd Motor Cooler Fan FRONT LOW | 15000 | 16936 | 2025-05-15 | 23424 | 2027-08-31 | 8512 | WA | Iron Bridge
EX2619 | Cat 6060 | N7234-FU | Hyd Motor Cooler Fan FRONT UPP | 15000 | 15426 | 2025-03-15 | 23424 | 2027-06-11 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7234-RL | Hyd Motor Cooler Fan REAR LOW | 15000 | 15426 | 2025-03-16 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7234-RU | Hyd Motor Cooler Fan REAR UPP | 15000 | 15426 | 2025-03-16 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7320-LF | Hyd Motor Swing LFT FRONT | 20000 | 20725 | 2026-01-08 | 23424 | 2028-12-18 | 17301 | WA | Iron Bridge
EX2619 | Cat 6060 | N7320-LR | Hyd Motor Swing LFT REAR | 20000 | 22553 | 2026-04-12 | 23424 | 2029-03-27 | 19129 | WA | Iron Bridge
EX2619 | Cat 6060 | N7320-RF | Hyd Motor Swing RHT FRONT | 20000 | 14235 | 2024-12-26 | 23424 | 2028-01-02 | 10811 | WA | Iron Bridge
EX2619 | Cat 6060 | N7320-RR | Hyd Motor Swing RHT REAR | 20000 | 22553 | 2026-04-11 | 23424 | 2029-03-27 | 19129 | WA | Iron Bridge
EX2619 | Cat 6060 | N7330-LF | Hyd Motor Travel LFT FRONT | 18000 | 15426 | 2025-03-18 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7330-LR | Hyd Motor Travel LFT REAR | 18000 | 15426 | 2025-03-18 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7330-RF | Hyd Motor Travel RHT FRONT | 18000 | 15426 | 2025-03-21 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7330-RR | Hyd Motor Travel RHT REAR | 18000 | 15426 | 2025-03-21 | 23424 | 2027-11-20 | 10002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7426-L | Hyd Cyl Boom Lift LEFT | 15000 |  |  | 23424 | 2025-02-27 | -8424 | WA | Iron Bridge
EX2619 | Cat 6060 | N7426-R | Hyd Cyl Boom Lift RIGHT | 15000 |  |  | 23424 | 2025-02-27 | -8424 | WA | Iron Bridge
EX2619 | Cat 6060 | N7432-L | Hyd Cyl Bucket LEFT | 10000 | 9161 | 2023-11-23 | 23424 | 2025-10-10 | -4263 | WA | Iron Bridge
EX2619 | Cat 6060 | N7432-R | Hyd Cyl Bucket RIGHT | 10000 | 9161 | 2023-11-23 | 23424 | 2025-10-10 | -4263 | WA | Iron Bridge
EX2619 | Cat 6060 | N7434-L | Hyd Cyl Bucket Clam LEFT | 5000 | 21272 | 2026-02-03 | 23424 | 2026-10-29 | 2848 | WA | Iron Bridge
EX2619 | Cat 6060 | N7434-R | Hyd Cyl Bucket Clam RIGHT | 5000 | 22553 | 2026-04-16 | 23424 | 2027-01-06 | 4129 | WA | Iron Bridge
EX2619 | Cat 6060 | N7546-L | Hyd Cyl Stick LEFT | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N7546-R | Hyd Cyl Stick RIGHT | 15000 |  |  | 23424 | 2025-02-27 | -8424 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-BO | Control Valve Boom | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-CL | Control Valve Clam | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-LL | Control Valve LEFT LOWER | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-LU | Control Valve LEFT UPPER | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-RL | Control Valve RIGHT LOWER | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-RU | Control Valve RIGHT UPPER | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7600-ST | Control Valve Stick | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7610-F | Hyd Cooler Core FRONT | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7610-RE | Hyd Cooler Core REAR | 30000 |  |  | 23424 | 2027-05-18 | 6576 | WA | Iron Bridge
EX2619 | Cat 6060 | N7620 | Hyd Rotary Joint | 15000 | 15426 | 2025-03-18 | 23424 | 2027-06-10 | 7002 | WA | Iron Bridge
EX2619 | Cat 6060 | N8050 | Slew Ring | 40000 |  |  | 23424 | 2028-11-09 | 16576 | WA | Iron Bridge
EX2619 | Cat 6060 | N8061 | Slew Ring Bolts Check | 5000 | 22553 | 2026-04-14 | 23424 | 2027-01-06 | 4129 | WA | Iron Bridge
EX2619 | Cat 6060 | N8061-01 | Slew Ring Bolts Check -Initial | 500 |  |  | 23424 | 2023-01-05 | -22924 | WA | Iron Bridge
EX2619 | Cat 6060 | N8995 | Operator Seat | 6000 | 21759 | 2026-03-02 | 23424 | 2027-01-17 | 4335 | WA | Iron Bridge
EX2619 | Cat 6060 | N9020-E1 | Alternator EN1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N9020-E2 | Alternator EN2 | 9000 | 19070 | 2025-10-06 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N9151-E1 | Starter Motor Upper EN1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N9151-E2 | Starter Motor Upper EN2 | 9000 | 22553 | 2026-04-12 | 23424 | 2027-08-10 | 8129 | WA | Iron Bridge
EX2619 | Cat 6060 | N9152-E1 | Starter Motor Lower EN1 | 9000 | 19070 | 2025-10-09 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N9152-E2 | Starter Motor Lower EN2 | 9000 | 22835 | 2026-04-29 | 23424 | 2027-08-26 | 8411 | WA | Iron Bridge
EX2619 | Cat 6060 | N9500-L | Air Cond'r-Serv LEFT | 4500 | 20210 | 2025-10-09 | 23424 | 2026-08-06 | 1286 | WA | Iron Bridge
EX2619 | Cat 6060 | N9500-LM | Air Cond'r-Serv - MAJOR LEFT | 18000 | 20210 | 2025-10-09 | 23424 | 2028-08-04 | 14786 | WA | Iron Bridge
EX2619 | Cat 6060 | N9500-R | Air Cond'r-Serv RIGHT | 4500 | 20210 | 2025-10-09 | 23424 | 2026-08-06 | 1286 | WA | Iron Bridge
EX2619 | Cat 6060 | N9500-RM | Air Cond'r-Serv - MAJOR RIGHT | 18000 | 20210 | 2025-10-09 | 23424 | 2028-08-04 | 14786 | WA | Iron Bridge
EX2619 | Cat 6060 | N9501-L | A/C Compressor LEFT | 9000 | 19070 | 2025-10-04 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N9501-R | A/C Compressor RIGHT | 9000 | 19070 | 2025-10-05 | 23424 | 2027-02-03 | 4646 | WA | Iron Bridge
EX2619 | Cat 6060 | N9998 | Extended Life Rebuild | 52000 |  |  | 23424 | 2030-08-20 | 28576 | WA | Iron Bridge
EX2619 | Cat 6060 | N9998-01 | Extended Life Rebuild ONE | 72000 |  |  | 23424 | 2033-08-05 | 48576 | WA | Iron Bridge
EX2619 | Cat 6060 | N9998-02 | Extended Life Rebuild TWO | 90000 |  |  | 23424 | 2036-04-04 | 66576 | WA | Iron Bridge
EX2634 | Cat 336-XZ | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-09-01 | 4053 | 2028-08-30 |  | WA | Iron Bridge
EX4001 | Cat 374 | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-09-01 | 2591 | 2028-08-30 |  | WA | Iron Bridge
EX4001 | Cat 374 | N1002 | Engine Valve Adj | 2500 |  | 2024-02-20 | 2591 | 2026-05-13 | -91 | WA | Iron Bridge
EX4001 | Cat 374 | N9500 | Air Cond'r-Serv | 5000 |  |  | 2591 | 2027-07-04 | 2409 | WA | Iron Bridge
EX4115 | Cat 374 | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-01-01 | 2813 | 2028-12-30 |  | WA | Iron Bridge
EX4115 | Cat 374 | N1002 | Engine Valve Adj | 2500 | 2679 | 2026-05-03 | 2813 | 2027-06-26 | 2366 | WA | Iron Bridge
EX4115 | Cat 374 | N9500 | Air Cond'r-Serv | 5000 |  |  | 2813 | 2027-05-28 | 2187 | WA | Iron Bridge
EX6541 | Cat 336DL | N0008 | Boom | 22000 |  | 2022-06-01 | 14715.2 | 2032-10-18 | 7284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0020 | Bucket | 6000 |  | 2022-06-01 | 14715.2 | 2018-10-04 | -8715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0026 | Bucket H-Link | 12000 |  | 2022-06-01 | 14715.2 | 2024-01-09 | -2715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0060 | Stick | 22000 |  | 2022-06-01 | 14715.2 | 2032-10-18 | 7284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-10-14 | 14715.2 | 2028-10-12 |  | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0100-L | Track Group LEFT | 10000 | 11528.1 | 2023-03-07 | 14715.2 | 2032-05-20 | 6812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0100-R | Track Group RIGHT | 10000 | 11528.1 | 2023-03-07 | 14715.2 | 2032-05-20 | 6812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0104-L | Sprockets LEFT | 10000 | 11528.1 | 2023-03-08 | 14715.2 | 2032-05-20 | 6812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0104-R | Sprockets RIGHT | 10000 | 11528.1 | 2023-03-07 | 14715.2 | 2032-05-20 | 6812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0105-L | Idler LEFT | 10000 |  | 2022-06-01 | 14715.2 | 2022-04-08 | -4715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0105-R | Idler RIGHT | 10000 | 11528.1 | 2023-03-07 | 14715.2 | 2032-05-20 | 6812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-1L | Track Roller 1 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-1R | Track Roller 1 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-2L | Track Roller 2 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-2R | Track Roller 2 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-3L | Track Roller 3 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-3R | Track Roller 3 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-4L | Track Roller 4 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-4R | Track Roller 4 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-5L | Track Roller 5 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-5R | Track Roller 5 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-6L | Track Roller 6 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-6R | Track Roller 6 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-7L | Track Roller 7 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-7R | Track Roller 7 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-8L | Track Roller 8 LEFT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-8R | Track Roller 8 RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-9L | Track Roller 9 LEFT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0111-9R | Track Roller 9 RIGHT | 14000 | 13864 | 2025-04-10 | 14715.2 | 2037-12-10 | 13148.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0121-L | Carrier Roller No 1 LEFT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0121-R | Carrier Roller No 1 RIGHT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0122-L | Carrier Roller No 2 LEFT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0122-R | Carrier Roller No 2 RIGHT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0123-L | Carrier Roller No 3 LEFT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0123-R | Carrier Roller No 3 RIGHT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0134-L | Track Adjuster LEFT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N0134-R | Track Adjuster RIGHT | 14000 | 11528.1 | 2023-03-07 | 14715.2 | 2035-11-23 | 10812.9 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N1000 | Engine | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N1100 | Turbo Primary |  |  | 2022-06-01 | 14715.2 | 2041-07-31 |  | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N1301 | Water Pump |  |  | 2022-06-01 | 14715.2 | 2041-07-31 |  | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N1310 | Radiator | 14000 | 13620.4 | 2025-02-05 | 14715.2 | 2037-09-23 | 12905.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N3220 | Swing Box | 15000 |  | 2022-06-01 | 14715.2 | 2026-08-27 | 284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N3321 | Pump Drive | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N5000-L | Final Drive LEFT | 22000 | 12976.75 | 2024-11-03 | 14715.2 | 2044-03-08 | 20261.55 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N5000-R | Final Drive RIGHT | 22000 |  | 2022-06-01 | 14715.2 | 2032-10-18 | 7284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7001 | Hydraulic Tune | 12000 |  | 2022-06-01 | 14715.2 | 2024-01-09 | -2715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7091 | Pump Servo/Brg Lube | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7155 | Hyd Pump Main | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7320 | Hyd Motor Swing | 15000 |  | 2022-06-01 | 14715.2 | 2026-08-27 | 284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7330-L | Hyd Motor Travel LEFT | 14000 | 6014 | 2019-01-18 | 14715.2 | 2031-01-20 | 5298.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7330-R | Hyd Motor Travel RIGHT | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7426-L | Hyd Cyl Boom Lift LEFT | 10000 | 14318 | 2025-11-05 | 14715.2 | 2034-10-31 | 9602.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7426-R | Hyd Cyl Boom Lift RIGHT | 10000 |  | 2022-06-01 | 14715.2 | 2022-04-08 | -4715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7432 | Hyd Cyl Bucket | 10000 |  | 2022-06-01 | 14715.2 | 2022-04-08 | -4715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7546 | Hyd Cyl Stick | 10000 |  | 2022-06-01 | 14715.2 | 2022-04-08 | -4715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7610 | Hyd Cooler Core | 14000 |  | 2022-06-01 | 14715.2 | 2025-10-11 | -715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N7620 | Hyd Rotary Joint | 24000 |  | 2022-06-01 | 14715.2 | 2034-07-21 | 9284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N8410 | Bucket Pin Assembly | 12000 |  | 2022-06-01 | 14715.2 | 2024-01-09 | -2715.2 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N8810 | Pin & Bush BOOM | 16000 |  | 2022-06-01 | 14715.2 | 2027-07-14 | 1284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N8810-01 | Pin & Bush - BUCKET to STICK | 16000 |  | 2022-06-01 | 14715.2 | 2027-07-14 | 1284.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N8995 | Operator Seat | 9000 | 11981 | 2023-12-21 | 14715.2 | 2031-11-26 | 6265.8 | WA | Sanjiv Ridge
EX6541 | Cat 336DL | N9500 | Air Cond'r-Serv |  | 14368 | 2025-11-27 | 14715.2 | 2026-11-27 |  | WA | Sanjiv Ridge
EX8388 | Cat 6060 | N0010 | Excavator Boom | 32000 |  |  | 23756 | 2027-08-17 | 8244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0060 | Stick | 32000 |  |  | 23756 | 2027-08-17 | 8244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0066 | Fire Suppression Sys Cylinder |  | 1625 | 2022-10-27 | 23756 | 2027-10-26 |  | WA | Iron Bridge
EX8388 | Cat 6060 | N0091-01 | Grease Pump POS 01 | 18000 | 18482 | 2025-08-05 | 23756 | 2028-04-15 | 12726 | WA | Iron Bridge
EX8388 | Cat 6060 | N0091-02 | Grease Pump POS 02 | 18000 |  |  | 23756 | 2025-07-21 | -5756 | WA | Iron Bridge
EX8388 | Cat 6060 | N0100-L | Track Group LEFT | 24000 | 18270 | 2025-07-20 | 23756 | 2029-02-22 | 18514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0100-R | Track Group RIGHT | 24000 | 18270 | 2025-07-19 | 23756 | 2029-02-22 | 18514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0104-L | Sprockets LEFT | 18000 | 18270 | 2025-07-12 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0104-R | Sprockets RIGHT | 18000 | 18270 | 2025-07-12 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0105-L | Idler LEFT | 12000 |  |  | 23756 | 2024-08-31 | -11756 | WA | Iron Bridge
EX8388 | Cat 6060 | N0105-R | Idler RIGHT | 12000 |  |  | 23756 | 2024-08-31 | -11756 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-1L | Track Roller 1 LEFT | 12000 |  |  | 23756 | 2024-08-31 | -11756 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-1R | Track Roller 1 RIGHT | 12000 |  |  | 23756 | 2024-08-31 | -11756 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-2L | Track Roller 2 LEFT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-2R | Track Roller 2 RIGHT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-3L | Track Roller 3 LEFT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-3R | Track Roller 3 RIGHT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-4L | Track Roller 4 LEFT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-4R | Track Roller 4 RIGHT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-5L | Track Roller 5 LEFT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-5R | Track Roller 5 RIGHT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-6L | Track Roller 6 LEFT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-6R | Track Roller 6 RIGHT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-7L | Track Roller 7 LEFT | 12000 | 7750 | 2023-10-17 | 23756 | 2025-10-23 | -4006 | WA | Iron Bridge
EX8388 | Cat 6060 | N0111-7R | Track Roller 7 RIGHT | 12000 | 16318 | 2025-03-21 | 23756 | 2027-01-30 | 4562 | WA | Iron Bridge
EX8388 | Cat 6060 | N0121-L | Carrier Roller No 1 LEFT | 12000 | 8534 | 2023-11-21 | 23756 | 2025-12-05 | -3222 | WA | Iron Bridge
EX8388 | Cat 6060 | N0121-R | Carrier Roller No 1 RIGHT | 12000 | 19772 | 2025-10-13 | 23756 | 2027-08-04 | 8016 | WA | Iron Bridge
EX8388 | Cat 6060 | N0122-L | Carrier Roller No 2 LEFT | 12000 | 12088 | 2024-07-23 | 23756 | 2026-06-15 | 332 | WA | Iron Bridge
EX8388 | Cat 6060 | N0122-R | Carrier Roller No 2 RIGHT | 12000 | 19772 | 2025-10-13 | 23756 | 2027-08-04 | 8016 | WA | Iron Bridge
EX8388 | Cat 6060 | N0155-L | Track Tension Cyl LEFT | 12000 | 18270 | 2025-07-23 | 23756 | 2027-05-15 | 6514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0155-R | Track Tension Cyl RIGHT | 12000 | 18270 | 2025-07-12 | 23756 | 2027-05-15 | 6514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0162-L | Track Accumulator LEFT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0162-R | Track Accumulator RIGHT | 24000 |  |  | 23756 | 2026-06-10 | 244 | WA | Iron Bridge
EX8388 | Cat 6060 | N0520-E1 | Pre Lube Pump EN1 | 18000 | 18022 | 2025-06-29 | 23756 | 2028-03-21 | 12266 | WA | Iron Bridge
EX8388 | Cat 6060 | N0520-E2 | Pre Lube Pump EN2 | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N0555-E1 | Cooler Fan Brgs EN1 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N0555-E2 | Cooler Fan Brgs EN2 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N0555-FL | Cooler Fan Hyd Brgs FRNT LOWER | 15000 | 15589 | 2025-01-23 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N0555-FU | Cooler Fan Hyd Brgs FRNT UPPER | 15000 | 9763 | 2024-02-11 | 23756 | 2026-07-21 | 1007 | WA | Iron Bridge
EX8388 | Cat 6060 | N0555-RL | Cooler Fan Hyd Brgs REAR LOWER | 15000 | 15589 | 2025-01-28 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N0555-RU | Cooler Fan Hyd Brgs REAR UPPER | 15000 | 15589 | 2025-01-28 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N1000-01 | Engine EN1(L/F) | 18000 | 18022 | 2025-06-29 | 23756 | 2028-03-21 | 12266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1000-02 | Engine EN2(R/RE) | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1002-1 | Engine Valve Adj EN1 | 4000 | 18022 | 2025-06-29 | 23756 | 2026-02-23 | -1734 | WA | Iron Bridge
EX8388 | Cat 6060 | N1002-1I | Engine Valve Adj Initial EN1 | 50 | 18402 | 2025-08-01 | 23756 | 2025-08-14 | -5304 | WA | Iron Bridge
EX8388 | Cat 6060 | N1002-2 | Engine Valve Adj EN2 | 4000 | 18270 | 2025-07-24 | 23756 | 2026-03-09 | -1486 | WA | Iron Bridge
EX8388 | Cat 6060 | N1002-2I | Engine Valve Adj Initial EN2 | 50 | 18402 | 2025-08-01 | 23756 | 2025-08-14 | -5304 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-01 | Turbo Primary EN1 LHF | 18000 | 18022 | 2025-06-29 | 23756 | 2028-03-21 | 12266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-02 | Turbo Primary EN1 RHF | 18000 | 18022 | 2025-06-29 | 23756 | 2028-03-21 | 12266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-03 | Turbo Primary EN1 LHR | 18000 | 18022 | 2025-06-29 | 23756 | 2028-03-21 | 12266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-04 | Turbo Primary EN1 RHR | 18000 | 18022 | 2025-06-29 | 23756 | 2028-03-21 | 12266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-05 | Turbo Primary EN2 LHF | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-06 | Turbo Primary EN2 RHF | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-07 | Turbo Primary EN2 LHR | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1100-08 | Turbo Primary EN2 RHR | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1202-E1 | Fuel Transfer Pump EN 1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1202-E2 | Fuel Transfer Pump EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1210-E1 | Fuel Injectors EN1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1210-E2 | Fuel Injectors EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1300-E1 | Cooling Sys Service EN1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1300-E2 | Cooling Sys Service EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1310-E1 | Radiator EN1 | 30000 | 18270 | 2025-07-25 | 23756 | 2030-01-12 | 24514 | WA | Iron Bridge
EX8388 | Cat 6060 | N1310-E2 | Radiator EN2 | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N1320-E1 | Cooling Fan Engine EN1 | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N1320-E2 | Cooling Fan Engine EN2 | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N1403-E1 | Jockey Pulley Brgs EN1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N1403-E2 | Jockey Pulley Brgs EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N2400-E1 | Drv Coupling EN1 | 18000 | 18270 | 2025-07-13 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N2400-E2 | Drv Coupling EN2 | 18000 | 18270 | 2025-07-13 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N3200-E1 | Splitter Box EN1 | 18000 | 18270 | 2025-07-17 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N3200-E2 | Splitter Box EN2 | 18000 | 4538 | 2023-04-24 | 23756 | 2026-03-15 | -1218 | WA | Iron Bridge
EX8388 | Cat 6060 | N3201-E1 | Pump Spltr Box Lube EN1 | 18000 | 18270 | 2025-07-17 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N3201-E2 | Pump Spltr Box Lube EN2 | 18000 | 4538 | 2023-04-24 | 23756 | 2026-03-15 | -1218 | WA | Iron Bridge
EX8388 | Cat 6060 | N3205-F | Cooler Spltr Box FRONT | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N3205-RE | Cooler Spltr Box REAR | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N3220-LF | Swing Box LFT FRONT | 20000 | 21502 | 2026-01-19 | 23756 | 2029-01-11 | 17746 | WA | Iron Bridge
EX8388 | Cat 6060 | N3220-LR | Swing Box LFT REAR | 20000 | 21502 | 2026-01-20 | 23756 | 2029-01-11 | 17746 | WA | Iron Bridge
EX8388 | Cat 6060 | N3220-RF | Swing Box RHT FRONT | 20000 | 21502 | 2026-01-17 | 23756 | 2029-01-11 | 17746 | WA | Iron Bridge
EX8388 | Cat 6060 | N3220-RR | Swing Box RHT REAR | 20000 | 21502 | 2026-01-18 | 23756 | 2029-01-11 | 17746 | WA | Iron Bridge
EX8388 | Cat 6060 | N5000-L | Final Drive LEFT | 36000 |  |  | 23756 | 2028-03-20 | 12244 | WA | Iron Bridge
EX8388 | Cat 6060 | N5000-R | Final Drive RIGHT | 36000 |  |  | 23756 | 2028-03-20 | 12244 | WA | Iron Bridge
EX8388 | Cat 6060 | N5002-L | Final Drive Midlife LEFT | 18000 |  |  | 23756 | 2025-07-21 | -5756 | WA | Iron Bridge
EX8388 | Cat 6060 | N5002-R | Final Drive Midlife RIGHT | 18000 |  |  | 23756 | 2025-07-21 | -5756 | WA | Iron Bridge
EX8388 | Cat 6060 | N6015-LF | Brake Travel LFT FRONT | 18000 | 17057 | 2025-04-30 | 23756 | 2028-01-29 | 11301 | WA | Iron Bridge
EX8388 | Cat 6060 | N6015-LR | Brake Travel LFT REAR | 18000 | 17057 | 2025-04-30 | 23756 | 2028-01-29 | 11301 | WA | Iron Bridge
EX8388 | Cat 6060 | N6015-RF | Brake Travel RHT FRONT | 18000 | 13609 | 2024-10-12 | 23756 | 2027-07-26 | 7853 | WA | Iron Bridge
EX8388 | Cat 6060 | N6015-RR | Brake Travel RHT REAR | 18000 | 13609 | 2024-10-13 | 23756 | 2027-07-26 | 7853 | WA | Iron Bridge
EX8388 | Cat 6060 | N7001 | Hydraulic Tune | 6000 | 15589 | 2025-01-31 | 23756 | 2026-01-25 | -2167 | WA | Iron Bridge
EX8388 | Cat 6060 | N7002 | Boom Arch Hoses | 15000 | 15589 | 2025-01-27 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-07 | Hyd Hose Boom Cylinder | 15000 | 15589 | 2025-01-27 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-08 | Hyd Hose Stick Cylinder | 15000 | 15589 | 2025-01-27 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-09 | Hyd Hose Bucket Cylinder | 10000 | 15589 | 2025-01-27 | 23756 | 2026-09-04 | 1833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-12 | Hyd Hose Swing Pump Swing Mtr | 10000 | 21502 | 2026-01-18 | 23756 | 2027-07-21 | 7746 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-17 | Hyd Hose Eng Fan Mtr | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-19 | Hyd Hose Bucket Supply | 10000 | 21502 | 2026-01-20 | 23756 | 2027-07-21 | 7746 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-20 | Hyd Hose Clam Supply | 10000 | 10000 | 2024-02-04 | 23756 | 2025-11-06 | -3756 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-21 | Hyd Hose Clam Cylinder | 5000 | 5254 | 2023-05-26 | 23756 | 2024-05-28 | -13502 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-22 | Hyd Hose Work Pumps-Rot Joint | 15000 | 15589 | 2025-01-28 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-23 | Hyd Hose MCV Return | 15000 | 15589 | 2025-01-27 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-24 | Hyd Hose Cooler Pumps-Coolers | 15000 | 15589 | 2025-01-28 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-25 | Hyd Hose Oil Suction | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-30 | Hyd Hose Rotary Joint to Valve | 18000 | 18270 | 2025-07-16 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-31 | Hyd Hose Valve to Trvl Mtr LH | 18000 | 18270 | 2025-07-17 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7004-32 | Hyd Hose Valve to Trvl Mtr RH | 18000 | 18270 | 2025-07-17 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7032-01 | Pump Cooler Fan Hyd POS 1 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7032-02 | Pump Cooler Fan Hyd POS 2 | 15000 | 19772 | 2025-10-13 | 23756 | 2028-01-13 | 11016 | WA | Iron Bridge
EX8388 | Cat 6060 | N7032-03 | Pump Cooler Fan Hyd POS 3 | 15000 | 15589 | 2025-01-26 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7032-04 | Pump Cooler Fan Hyd POS 4 | 15000 | 15589 | 2025-01-26 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7041-E1 | Pump Cooling Fan Eng EN1 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7041-E2 | Pump Cooling Fan Eng EN2 | 15000 | 9367 | 2024-01-14 | 23756 | 2026-06-15 | 611 | WA | Iron Bridge
EX8388 | Cat 6060 | N7044-FL | Cooler Fan Hyd FRONT LOWER | 30000 | 18270 | 2025-07-11 | 23756 | 2030-01-12 | 24514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7044-FU | Cooler Fan Hyd FRONT UPPER | 30000 | 18270 | 2025-07-11 | 23756 | 2030-01-12 | 24514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7044-RL | Cooler Fan Hyd REAR LOWER | 30000 | 10047 | 2024-02-24 | 23756 | 2028-10-25 | 16291 | WA | Iron Bridge
EX8388 | Cat 6060 | N7044-RU | Cooler Fan Hyd REAR UPPER | 30000 | 10047 | 2024-02-24 | 23756 | 2028-10-25 | 16291 | WA | Iron Bridge
EX8388 | Cat 6060 | N7071-05 | Pump Imp 1&2 | 15000 | 12088 | 2024-07-22 | 23756 | 2026-11-24 | 3332 | WA | Iron Bridge
EX8388 | Cat 6060 | N7073-05 | Pump Imp 3&4 | 15000 | 22685 | 2026-03-25 | 23756 | 2028-06-19 | 13929 | WA | Iron Bridge
EX8388 | Cat 6060 | N7075-05 | Pump Imp 5&6 | 15000 | 19772 | 2025-10-13 | 23756 | 2028-01-13 | 11016 | WA | Iron Bridge
EX8388 | Cat 6060 | N7077-05 | Pump Imp 7&8 | 15000 | 8877 | 2023-12-11 | 23756 | 2026-05-21 | 121 | WA | Iron Bridge
EX8388 | Cat 6060 | N7090-01 | Pump Pilot/Servo POS 1 | 15000 | 18301 | 2025-07-26 | 23756 | 2027-10-26 | 9545 | WA | Iron Bridge
EX8388 | Cat 6060 | N7090-02 | Pump Pilot/Servo POS 2 | 15000 | 17083 | 2025-05-03 | 23756 | 2027-08-21 | 8327 | WA | Iron Bridge
EX8388 | Cat 6060 | N7090-03 | Pump Pilot/Servo POS 3 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7090-04 | Pump Pilot/Servo POS 4 | 15000 | 18301 | 2025-07-26 | 23756 | 2027-10-26 | 9545 | WA | Iron Bridge
EX8388 | Cat 6060 | N7092-E1 | Pump Replenishing EN1 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7092-E2 | Pump Replenishing EN2 | 15000 | 15589 | 2025-01-26 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7095-E1 | Pump Aircon Drive EN1 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7095-E2 | Pump Aircon Drive EN2 | 15000 | 15589 | 2025-01-25 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7130-01 | Pump Swing POS 1 | 10000 | 22685 | 2026-03-25 | 23756 | 2027-09-23 | 8929 | WA | Iron Bridge
EX8388 | Cat 6060 | N7130-02 | Pump Swing POS 2 | 10000 | 21501 | 2026-01-17 | 23756 | 2027-07-21 | 7745 | WA | Iron Bridge
EX8388 | Cat 6060 | N7130-03 | Pump Swing POS 3 | 10000 | 21502 | 2026-01-18 | 23756 | 2027-07-21 | 7746 | WA | Iron Bridge
EX8388 | Cat 6060 | N7130-04 | Pump Swing POS 4 | 10000 | 21327 | 2026-01-18 | 23756 | 2027-07-11 | 7571 | WA | Iron Bridge
EX8388 | Cat 6060 | N7201-L | Hyd Motor Air Con LEFT | 9000 | 18270 | 2025-07-19 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7201-R | Hyd Motor Air Con RIGHT | 9000 | 18270 | 2025-07-19 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N7232-E1 | Hyd Motor Engine Fan EN1 | 15000 | 15589 | 2025-01-24 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7232-E2 | Hyd Motor Engine Fan EN2 | 15000 | 15589 | 2025-01-24 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7234-FL | Hyd Motor Cooler Fan FRONT LOW | 15000 | 15589 | 2025-01-28 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7234-FU | Hyd Motor Cooler Fan FRONT UPP | 15000 | 9763 | 2024-02-11 | 23756 | 2026-07-21 | 1007 | WA | Iron Bridge
EX8388 | Cat 6060 | N7234-RL | Hyd Motor Cooler Fan REAR LOW | 15000 | 21286 | 2026-01-03 | 23756 | 2028-04-04 | 12530 | WA | Iron Bridge
EX8388 | Cat 6060 | N7234-RU | Hyd Motor Cooler Fan REAR UPP | 15000 | 15589 | 2025-01-28 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7320-LF | Hyd Motor Swing LFT FRONT | 20000 | 17057 | 2025-04-30 | 23756 | 2028-05-16 | 13301 | WA | Iron Bridge
EX8388 | Cat 6060 | N7320-LR | Hyd Motor Swing LFT REAR | 20000 | 15589 | 2025-01-29 | 23756 | 2028-02-27 | 11833 | WA | Iron Bridge
EX8388 | Cat 6060 | N7320-RF | Hyd Motor Swing RHT FRONT | 20000 | 21327 | 2026-01-05 | 23756 | 2029-01-02 | 17571 | WA | Iron Bridge
EX8388 | Cat 6060 | N7320-RR | Hyd Motor Swing RHT REAR | 20000 | 19075 | 2025-09-05 | 23756 | 2028-09-02 | 15319 | WA | Iron Bridge
EX8388 | Cat 6060 | N7330-LF | Hyd Motor Travel LFT FRONT | 18000 | 17057 | 2025-04-30 | 23756 | 2028-01-29 | 11301 | WA | Iron Bridge
EX8388 | Cat 6060 | N7330-LR | Hyd Motor Travel LFT REAR | 18000 | 17057 | 2025-04-29 | 23756 | 2028-01-29 | 11301 | WA | Iron Bridge
EX8388 | Cat 6060 | N7330-RF | Hyd Motor Travel RHT FRONT | 18000 | 10831 | 2024-05-18 | 23756 | 2027-02-26 | 5075 | WA | Iron Bridge
EX8388 | Cat 6060 | N7330-RR | Hyd Motor Travel RHT REAR | 18000 | 10831 | 2024-05-18 | 23756 | 2027-02-26 | 5075 | WA | Iron Bridge
EX8388 | Cat 6060 | N7426-L | Hyd Cyl Boom Lift LEFT | 15000 |  |  | 23756 | 2025-02-09 | -8756 | WA | Iron Bridge
EX8388 | Cat 6060 | N7426-R | Hyd Cyl Boom Lift RIGHT | 15000 |  |  | 23756 | 2025-02-09 | -8756 | WA | Iron Bridge
EX8388 | Cat 6060 | N7432-L | Hyd Cyl Bucket LEFT | 10000 | 12089 | 2024-07-23 | 23756 | 2026-02-24 | -1667 | WA | Iron Bridge
EX8388 | Cat 6060 | N7432-R | Hyd Cyl Bucket RIGHT | 10000 | 15411 | 2025-01-17 | 23756 | 2026-08-22 | 1655 | WA | Iron Bridge
EX8388 | Cat 6060 | N7434-L | Hyd Cyl Bucket Clam LEFT | 5000 | 23334 | 2026-04-30 | 23756 | 2027-01-30 | 4578 | WA | Iron Bridge
EX8388 | Cat 6060 | N7434-R | Hyd Cyl Bucket Clam RIGHT | 5000 | 22685 | 2026-03-28 | 23756 | 2026-12-26 | 3929 | WA | Iron Bridge
EX8388 | Cat 6060 | N7546-L | Hyd Cyl Stick LEFT | 15000 | 12088 | 2024-07-23 | 23756 | 2026-11-24 | 3332 | WA | Iron Bridge
EX8388 | Cat 6060 | N7546-R | Hyd Cyl Stick RIGHT | 15000 | 14366 | 2024-11-24 | 23756 | 2027-03-27 | 5610 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-BO | Control Valve Boom | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-CL | Control Valve Clam | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-LL | Control Valve LEFT LOWER | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-LU | Control Valve LEFT UPPER | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-RL | Control Valve RIGHT LOWER | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-RU | Control Valve RIGHT UPPER | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7600-ST | Control Valve Stick | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7610-F | Hyd Cooler Core FRONT | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7610-RE | Hyd Cooler Core REAR | 30000 |  |  | 23756 | 2027-05-01 | 6244 | WA | Iron Bridge
EX8388 | Cat 6060 | N7620 | Hyd Rotary Joint | 15000 | 15589 | 2025-01-27 | 23756 | 2027-06-01 | 6833 | WA | Iron Bridge
EX8388 | Cat 6060 | N8050 | Slew Ring | 40000 |  |  | 23756 | 2028-10-22 | 16244 | WA | Iron Bridge
EX8388 | Cat 6060 | N8061 | Slew Ring Bolts Check | 5000 | 21502 | 2026-01-16 | 23756 | 2026-10-23 | 2746 | WA | Iron Bridge
EX8388 | Cat 6060 | N8061-01 | Slew Ring Bolts Check -Initial | 500 | 659 | 2022-09-06 | 23756 | 2023-01-23 | -22597 | WA | Iron Bridge
EX8388 | Cat 6060 | N8995 | Operator Seat | 6000 | 17891 | 2025-06-20 | 23756 | 2026-05-22 | 135 | WA | Iron Bridge
EX8388 | Cat 6060 | N9020-E1 | Alternator EN1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N9020-E2 | Alternator EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9151-E1 | Starter Motor Upper EN1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N9151-E2 | Starter Motor Upper EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9152-E1 | Starter Motor Lower EN1 | 9000 | 18022 | 2025-06-29 | 23756 | 2026-11-21 | 3266 | WA | Iron Bridge
EX8388 | Cat 6060 | N9152-E2 | Starter Motor Lower EN2 | 9000 | 18270 | 2025-07-24 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9500-L | Air Cond'r-Serv LEFT | 4500 | 18270 | 2025-07-24 | 23756 | 2026-04-05 | -986 | WA | Iron Bridge
EX8388 | Cat 6060 | N9500-LM | Air Cond'r-Serv - MAJOR LEFT | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9500-R | Air Cond'r-Serv RIGHT | 4500 | 18270 | 2025-07-24 | 23756 | 2026-04-05 | -986 | WA | Iron Bridge
EX8388 | Cat 6060 | N9500-RM | Air Cond'r-Serv - MAJOR RIGHT | 18000 | 18270 | 2025-07-24 | 23756 | 2028-04-03 | 12514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9501-L | A/C Compressor LEFT | 9000 | 18270 | 2025-07-18 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9501-R | A/C Compressor RIGHT | 9000 | 18270 | 2025-07-18 | 23756 | 2026-12-04 | 3514 | WA | Iron Bridge
EX8388 | Cat 6060 | N9998 | Extended Life Rebuild | 52000 |  |  | 23756 | 2030-08-02 | 28244 | WA | Iron Bridge
EX8388 | Cat 6060 | N9998-01 | Extended Life Rebuild ONE | 72000 |  |  | 23756 | 2033-07-18 | 48244 | WA | Iron Bridge
EX8388 | Cat 6060 | N9998-02 | Extended Life Rebuild TWO | 90000 |  |  | 23756 | 2036-03-17 | 66244 | WA | Iron Bridge
EX8396 | Cat 336GC Excavator | N0066 | Fire Suppression Sys Cylinder |  | 2317 | 2025-03-13 | 3707 | 2030-03-12 |  | WA | Iron Bridge
GR0008 | Cat 16M | N0050 | Blade Assembly | 20000 |  |  | 25353 | 2025-03-26 | -5353 | WA | Iron Bridge
GR0008 | Cat 16M | N0066 | Fire Suppression Sys Cylinder |  | 19074 | 2024-12-02 | 25353 | 2029-12-01 |  | WA | Iron Bridge
GR0008 | Cat 16M | N0200 | A Frame Bearing | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N1000 | Engine | 16000 | 14878 | 2023-03-10 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N1002 | Engine Valve Adj | 2500 | 21687 | 2025-08-26 | 25353 | 2026-02-22 | -1166 | WA | Iron Bridge
GR0008 | Cat 16M | N1004 | Engine Midlife | 8000 | 23334 | 2025-12-09 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N1100 | Turbo Primary | 8000 | 23334 | 2025-12-09 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N1202 | Fuel Transfer Pump | 8000 | 23334 | 2025-12-07 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N1300 | Cooling Sys Service | 8000 | 23334 | 2025-12-09 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N1301 | Water Pump | 8000 | 25053 | 2026-05-01 | 25353 | 2028-02-03 | 7700 | WA | Iron Bridge
GR0008 | Cat 16M | N1310 | Radiator | 16000 | 6877 | 2020-07-27 | 25353 | 2025-11-11 | -2476 | WA | Iron Bridge
GR0008 | Cat 16M | N1312 | Aftercooler Core | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N1400 | Belt Tensioner Assembly | 8000 | 23334 | 2025-12-08 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N2000 | Transmission | 14000 | 14878 | 2023-04-06 | 25353 | 2027-03-06 | 3525 | WA | Iron Bridge
GR0008 | Cat 16M | N2004 | Transmission Pump | 14000 | 14878 | 2023-04-06 | 25353 | 2027-03-06 | 3525 | WA | Iron Bridge
GR0008 | Cat 16M | N2090 | Drv Coupling | 16000 | 14878 | 2023-03-24 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N3037 | Drive Shaft Trans - Bevel Gear | 14000 | 14878 | 2023-04-06 | 25353 | 2027-03-06 | 3525 | WA | Iron Bridge
GR0008 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 7000 | 23334 | 2025-12-07 | 25353 | 2027-06-30 | 4981 | WA | Iron Bridge
GR0008 | Cat 16M | N3210-03 | Tandem Drive Chain POS 3 | 16000 | 14878 | 2023-03-17 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N3210-04 | Tandem Drive Chain POS 4 | 16000 | 14878 | 2023-03-17 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N3210-05 | Tandem Drive Chain POS 5 | 16000 | 14878 | 2023-03-10 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N3210-06 | Tandem Drive Chain POS 6 | 16000 | 14878 | 2023-03-10 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N3300 | Circle Drive Box | 8000 | 18556 | 2024-10-21 | 25353 | 2026-09-01 | 1203 | WA | Iron Bridge
GR0008 | Cat 16M | N4000 | Bevel Gear | 14000 | 23334 | 2025-12-07 | 25353 | 2029-01-10 | 11981 | WA | Iron Bridge
GR0008 | Cat 16M | N4100-L | Rear Axle LEFT | 14000 | 23334 | 2025-12-07 | 25353 | 2029-01-10 | 11981 | WA | Iron Bridge
GR0008 | Cat 16M | N4100-R | Rear Axle RIGHT | 14000 | 23334 | 2025-12-07 | 25353 | 2029-01-10 | 11981 | WA | Iron Bridge
GR0008 | Cat 16M | N5000-L | Final Drive LEFT | 14000 | 23334 | 2025-12-07 | 25353 | 2029-01-10 | 11981 | WA | Iron Bridge
GR0008 | Cat 16M | N5000-R | Final Drive RIGHT | 14000 | 23334 | 2025-12-07 | 25353 | 2029-01-10 | 11981 | WA | Iron Bridge
GR0008 | Cat 16M | N5020-01 | Wheel Bearing POS 1 | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N5020-02 | Wheel Bearing POS 2 | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N6000-03 | Brake POS 3 | 16000 | 24694 | 2026-03-30 | 25353 | 2029-10-06 | 15341 | WA | Iron Bridge
GR0008 | Cat 16M | N6000-04 | Brake POS 4 | 16000 | 24701 | 2026-04-05 | 25353 | 2029-10-07 | 15348 | WA | Iron Bridge
GR0008 | Cat 16M | N6000-05 | Brake POS 5 | 16000 | 14878 | 2023-03-10 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N6000-06 | Brake POS 6 | 16000 | 14878 | 2023-03-10 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 16000 | 14878 | 2023-04-06 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7070 | Pump Implement | 16000 | 14878 | 2023-04-06 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 16000 | 14878 | 2023-03-02 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7230 | Hyd Motor Circle Drive | 8000 | 18556 | 2024-10-21 | 25353 | 2026-09-01 | 1203 | WA | Iron Bridge
GR0008 | Cat 16M | N7232 | Hyd Motor Engine Fan | 16000 | 14878 | 2023-02-15 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 16000 | 20870 | 2025-06-26 | 25353 | 2028-12-04 | 11517 | WA | Iron Bridge
GR0008 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 16000 | 20780 | 2025-06-26 | 25353 | 2028-11-27 | 11427 | WA | Iron Bridge
GR0008 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7422 | Hyd Cyl Blade Tip | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7440 | Hyd Cyl Centreshift | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 24000 |  |  | 25353 | 2026-02-09 | -1353 | WA | Iron Bridge
GR0008 | Cat 16M | N7540 | Hyd Cyl Sideshift | 16000 | 20780 | 2025-06-26 | 25353 | 2028-11-27 | 11427 | WA | Iron Bridge
GR0008 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N7600-FR | Control Valve FRONT | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7600-RE | Control Valve REAR | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7600-S | Control Valve - STEERING | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7610 | Hyd Cooler Core | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N7620 | Hyd Rotary Joint | 16000 | 22714 | 2025-11-01 | 25353 | 2029-05-01 | 13361 | WA | Iron Bridge
GR0008 | Cat 16M | N7650-F | Hyd Accum Blade Cushion FRONT | 16000 | 14878 | 2023-03-22 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7650-RE | Hyd Accum Blade Cushion REAR | 16000 | 14878 | 2023-03-22 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7654-F | Hyd Accum Service Brake - FR | 16000 | 14878 | 2023-03-07 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N7654-RE | Hyd Accum Service Brake - REAR | 16000 | 14878 | 2023-03-07 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N8040 | Circle & Drawbar | 16000 |  |  | 25353 | 2024-05-10 | -9353 | WA | Iron Bridge
GR0008 | Cat 16M | N8127-F | Axle Assembly FRONT | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N8131-01 | Steering Tie Rod Ends POS1 | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N8131-02 | Steering Tie Rod Ends POS2 | 12000 | 25144 | 2026-05-10 | 25353 | 2028-12-26 | 11791 | WA | Iron Bridge
GR0008 | Cat 16M | N8300 | Artic Hitch | 16000 | 20870 | 2025-06-26 | 25353 | 2028-12-04 | 11517 | WA | Iron Bridge
GR0008 | Cat 16M | N8995 | Operator Seat | 6000 | 22714 | 2025-10-31 | 25353 | 2027-02-21 | 3361 | WA | Iron Bridge
GR0008 | Cat 16M | N9020 | Alternator | 8000 | 22081 | 2025-09-20 | 25353 | 2027-06-10 | 4728 | WA | Iron Bridge
GR0008 | Cat 16M | N9050 | Starter Motor | 8000 | 23334 | 2025-12-08 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N9500 | Air Cond'r-Serv | 4000 | 23334 | 2025-12-10 | 25353 | 2026-11-02 | 1981 | WA | Iron Bridge
GR0008 | Cat 16M | N9500-MA | Air Cond'r-Serv - MAJOR | 16000 | 14878 | 2023-03-16 | 25353 | 2027-08-13 | 5525 | WA | Iron Bridge
GR0008 | Cat 16M | N9501 | A/C Compressor | 8000 | 23334 | 2025-12-08 | 25353 | 2027-09-18 | 5981 | WA | Iron Bridge
GR0008 | Cat 16M | N9998 | Extended Life Rebuild | 35000 |  |  | 25353 | 2028-07-08 | 9647 | WA | Iron Bridge
GR0008 | Cat 16M | N9998-01 | Extended Life Rebuild ONE | 50000 |  |  | 25353 | 2031-10-21 | 24647 | WA | Iron Bridge
GR0008 | Cat 16M | N9998-02 | Extended Life Rebuild TWO | 75000 |  |  | 25353 | 2037-04-12 | 49647 | WA | Iron Bridge
GR1271 | Cat 16M | N0050 | Blade Assembly | 20000 | 12174 | 2021-12-15 | 26541 | 2027-08-22 | 5633 | WA | Iron Bridge
GR1271 | Cat 16M | N0066 | Fire Suppression Sys Cylinder |  | 17673 | 2023-08-07 | 26541 | 2028-08-05 |  | WA | Iron Bridge
GR1271 | Cat 16M | N0200 | A Frame Bearing | 16000 | 17677 | 2023-07-21 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N1000 | Engine | 16000 | 16779 | 2023-03-10 | 26541 | 2027-10-09 | 6238 | WA | Iron Bridge
GR1271 | Cat 16M | N1002 | Engine Valve Adj | 2500 | 22000 | 2025-07-28 | 26541 | 2025-12-19 | -2041 | WA | Iron Bridge
GR1271 | Cat 16M | N1004 | Engine Midlife | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N1100 | Turbo Primary | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N1202 | Fuel Transfer Pump | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N1300 | Cooling Sys Service | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N1301 | Water Pump | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N1310 | Radiator | 16000 | 21665.95 | 2025-07-06 | 26541 | 2028-11-03 | 11124.95 | WA | Iron Bridge
GR1271 | Cat 16M | N1312 | Aftercooler Core | 16000 | 17677 | 2023-07-17 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N1400 | Belt Tensioner Assembly | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N2000 | Transmission | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N2004 | Transmission Pump | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N2090 | Drv Coupling | 16000 | 16779 | 2023-03-10 | 26541 | 2027-10-09 | 6238 | WA | Iron Bridge
GR1271 | Cat 16M | N3037 | Drive Shaft Trans - Bevel Gear | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 7000 | 23110 | 2025-10-20 | 26541 | 2027-03-10 | 3569 | WA | Iron Bridge
GR1271 | Cat 16M | N3210-03 | Tandem Drive Chain POS 3 | 16000 | 17692 | 2023-08-01 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N3210-04 | Tandem Drive Chain POS 4 | 16000 | 11564 | 2021-11-25 | 26541 | 2026-08-18 | 1023 | WA | Iron Bridge
GR1271 | Cat 16M | N3210-05 | Tandem Drive Chain POS 5 | 16000 | 17692 | 2023-08-01 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N3210-06 | Tandem Drive Chain POS 6 | 16000 | 11564 | 2021-11-25 | 26541 | 2026-08-18 | 1023 | WA | Iron Bridge
GR1271 | Cat 16M | N3300 | Circle Drive Box | 8000 | 22454 | 2025-09-09 | 26541 | 2027-04-06 | 3913 | WA | Iron Bridge
GR1271 | Cat 16M | N4000 | Bevel Gear | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N4100-L | Rear Axle LEFT | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N4100-R | Rear Axle RIGHT | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N5000-L | Final Drive LEFT | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N5000-R | Final Drive RIGHT | 14000 | 15034 | 2022-10-02 | 26541 | 2026-12-13 | 2493 | WA | Iron Bridge
GR1271 | Cat 16M | N5020-01 | Wheel Bearing POS 1 | 12000 | 15034 | 2022-10-02 | 26541 | 2026-07-06 | 493 | WA | Iron Bridge
GR1271 | Cat 16M | N5020-02 | Wheel Bearing POS 2 | 12000 | 15034 | 2022-10-02 | 26541 | 2026-07-06 | 493 | WA | Iron Bridge
GR1271 | Cat 16M | N6000-03 | Brake POS 3 | 16000 | 17692 | 2023-07-31 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N6000-04 | Brake POS 4 | 16000 | 23110 | 2025-10-21 | 26541 | 2029-02-27 | 12569 | WA | Iron Bridge
GR1271 | Cat 16M | N6000-05 | Brake POS 5 | 16000 | 17692 | 2023-07-31 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N6000-06 | Brake POS 6 | 16000 | 17692 | 2023-08-01 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 16000 | 17677 | 2023-07-13 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7070 | Pump Implement | 16000 | 17677 | 2023-07-11 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 16000 | 17692 | 2023-07-10 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7230 | Hyd Motor Circle Drive | 8000 | 22454 | 2025-09-09 | 26541 | 2027-04-06 | 3913 | WA | Iron Bridge
GR1271 | Cat 16M | N7232 | Hyd Motor Engine Fan | 16000 | 17677 | 2023-07-10 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 16000 | 15034 | 2022-10-13 | 26541 | 2027-05-22 | 4493 | WA | Iron Bridge
GR1271 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 16000 | 17692 | 2023-08-02 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 16000 | 17692 | 2023-08-02 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 16000 | 10657 | 2021-08-06 | 26541 | 2026-06-06 | 116 | WA | Iron Bridge
GR1271 | Cat 16M | N7422 | Hyd Cyl Blade Tip | 16000 | 17677 | 2023-07-21 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7440 | Hyd Cyl Centreshift | 16000 | 17677 | 2023-07-21 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 24000 |  |  | 26541 | 2025-11-06 | -2541 | WA | Iron Bridge
GR1271 | Cat 16M | N7540 | Hyd Cyl Sideshift | 16000 | 22207 | 2025-08-17 | 26541 | 2028-12-16 | 11666 | WA | Iron Bridge
GR1271 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 12000 | 22718 | 2025-09-25 | 26541 | 2028-03-15 | 8177 | WA | Iron Bridge
GR1271 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 22718 | 2025-09-25 | 26541 | 2028-03-12 | 8177 | WA | Iron Bridge
GR1271 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 12000 | 15034 | 2022-10-02 | 26541 | 2026-07-06 | 493 | WA | Iron Bridge
GR1271 | Cat 16M | N7600-FR | Control Valve FRONT | 16000 | 17692 | 2023-07-13 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7600-RE | Control Valve REAR | 16000 | 17692 | 2023-07-17 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7600-S | Control Valve - STEERING | 16000 | 17692 | 2023-07-17 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7610 | Hyd Cooler Core | 16000 | 17677 | 2023-07-10 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7620 | Hyd Rotary Joint | 16000 | 17677 | 2023-07-21 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N7650-F | Hyd Accum Blade Cushion FRONT | 16000 | 17692 | 2023-07-07 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7650-RE | Hyd Accum Blade Cushion REAR | 16000 | 17692 | 2023-07-07 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7654-F | Hyd Accum Service Brake - FR | 16000 | 17692 | 2023-07-27 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N7654-RE | Hyd Accum Service Brake - REAR | 16000 | 17692 | 2023-07-27 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N8040 | Circle & Drawbar | 16000 | 17677 | 2023-07-21 | 26541 | 2027-12-20 | 7136 | WA | Iron Bridge
GR1271 | Cat 16M | N8127-F | Axle Assembly FRONT | 12000 | 15034 | 2022-10-02 | 26541 | 2026-07-06 | 493 | WA | Iron Bridge
GR1271 | Cat 16M | N8131-01 | Steering Tie Rod Ends POS1 | 12000 | 21454 | 2025-06-10 | 26541 | 2027-12-02 | 6913 | WA | Iron Bridge
GR1271 | Cat 16M | N8131-02 | Steering Tie Rod Ends POS2 | 12000 | 15034 | 2022-10-02 | 26541 | 2026-07-06 | 493 | WA | Iron Bridge
GR1271 | Cat 16M | N8300 | Artic Hitch | 16000 | 17685 | 2023-07-27 | 26541 | 2027-12-21 | 7144 | WA | Iron Bridge
GR1271 | Cat 16M | N8995 | Operator Seat | 6000 | 18701 | 2024-10-31 | 26541 | 2026-01-09 | -1840 | WA | Iron Bridge
GR1271 | Cat 16M | N9020 | Alternator | 8000 | 20254 | 2025-03-14 | 26541 | 2026-10-12 | 1713 | WA | Iron Bridge
GR1271 | Cat 16M | N9050 | Starter Motor | 8000 | 16779 | 2023-03-10 | 26541 | 2026-01-10 | -1762 | WA | Iron Bridge
GR1271 | Cat 16M | N9500 | Air Cond'r-Serv | 4000 | 23100 | 2025-10-23 | 26541 | 2026-07-17 | 559 | WA | Iron Bridge
GR1271 | Cat 16M | N9500-MA | Air Cond'r-Serv - MAJOR | 16000 | 17692 | 2023-08-07 | 26541 | 2027-12-21 | 7151 | WA | Iron Bridge
GR1271 | Cat 16M | N9501 | A/C Compressor | 8000 | 23109 | 2025-10-22 | 26541 | 2027-05-28 | 4568 | WA | Iron Bridge
GR1271 | Cat 16M | N9998 | Extended Life Rebuild | 35000 | 2100 | 2012-09-03 | 26541 | 2028-09-19 | 10559 | WA | Iron Bridge
GR1271 | Cat 16M | N9998-01 | Extended Life Rebuild ONE | 50000 | 1600 | 2012-09-03 | 26541 | 2031-11-23 | 25059 | WA | Iron Bridge
GR1271 | Cat 16M | N9998-02 | Extended Life Rebuild TWO | 75000 |  | 2012-09-03 | 26541 | 2037-01-07 | 48459 | WA | Iron Bridge
GR1373 | Cat 16M | N0050 | Blade Assembly | 20000 | 25573 | 2018-06-11 | 49898.9 | 2025-03-21 | -4325.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N0066 | Fire Suppression Sys Cylinder |  | 46230 | 2025-04-19 | 49898.9 | 2030-04-18 |  | WA | Norrish Earthmoving
GR1373 | Cat 16M | N0200 | A Frame Bearing | 16000 | 42637 | 2024-04-03 | 49898.9 | 2028-10-18 | 8738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1000 | Engine | 16000 | 45978 | 2025-03-23 | 49898.9 | 2029-09-17 | 12079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1002 | Engine Valve Adj | 2500 | 48832 | 2025-11-27 | 49898.9 | 2026-10-18 | 1433.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1004 | Engine Midlife | 8000 | 45978 | 2025-03-23 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1100 | Turbo Primary | 8000 | 45978 | 2025-03-23 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1202 | Fuel Transfer Pump | 8000 | 45978 | 2025-03-23 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1300 | Cooling Sys Service | 8000 | 45978 | 2025-03-23 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1301 | Water Pump | 8000 | 45978 | 2025-03-23 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1310 | Radiator | 16000 | 45978 | 2025-03-21 | 49898.9 | 2029-09-17 | 12079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1312 | Aftercooler Core | 16000 | 45978 | 2025-03-22 | 49898.9 | 2029-09-17 | 12079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N1400 | Belt Tensioner Assembly | 8000 | 45978 | 2025-03-23 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N2000 | Transmission | 14000 | 42637 | 2024-03-28 | 49898.9 | 2028-04-01 | 6738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N2004 | Transmission Pump | 14000 | 42759.7 | 2024-04-23 | 49898.9 | 2028-04-13 | 6860.8 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N2090 | Drv Coupling | 16000 | 42759.7 | 2024-04-23 | 49898.9 | 2028-10-30 | 8860.8 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3037 | Drive Shaft Trans - Bevel Gear | 14000 | 34766 | 2021-10-22 | 49898.9 | 2026-02-04 | -1132.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 7000 | 41527 | 2023-11-02 | 49898.9 | 2026-01-11 | -1371.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3210-03 | Tandem Drive Chain POS 3 | 16000 | 34766 | 2021-10-22 | 49898.9 | 2026-08-23 | 867.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3210-04 | Tandem Drive Chain POS 4 | 16000 | 34766 | 2021-10-22 | 49898.9 | 2026-08-23 | 867.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3210-05 | Tandem Drive Chain POS 5 | 16000 | 34766 | 2021-10-22 | 49898.9 | 2026-08-23 | 867.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3210-06 | Tandem Drive Chain POS 6 | 16000 | 34766 | 2021-10-22 | 49898.9 | 2026-08-23 | 867.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N3300 | Circle Drive Box | 8000 | 42637 | 2024-02-28 | 49898.9 | 2026-08-10 | 738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N4000 | Bevel Gear | 14000 | 34766 | 2021-10-22 | 49898.9 | 2026-02-04 | -1132.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N4100-L | Rear Axle LEFT | 14000 | 34766 | 2021-10-22 | 49898.9 | 2026-02-04 | -1132.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N4100-R | Rear Axle RIGHT | 14000 | 34766 | 2021-10-22 | 49898.9 | 2026-02-04 | -1132.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N5000-L | Final Drive LEFT | 14000 | 34766 | 2021-10-22 | 49898.9 | 2026-02-04 | -1132.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N5000-R | Final Drive RIGHT | 14000 | 34766 | 2021-10-22 | 49898.9 | 2026-02-04 | -1132.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N5020-01 | Wheel Bearing POS 1 | 12000 | 41363 | 2023-10-20 | 49898.9 | 2027-05-09 | 3464.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N5020-02 | Wheel Bearing POS 2 | 12000 | 41363 | 2023-10-20 | 49898.9 | 2027-05-09 | 3464.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N6000-03 | Brake POS 3 | 16000 | 37477 | 2022-06-16 | 49898.9 | 2027-05-21 | 3578.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N6000-04 | Brake POS 4 | 16000 | 41333 | 2023-10-20 | 49898.9 | 2028-06-09 | 7434.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N6000-05 | Brake POS 5 | 16000 | 37480 | 2022-08-28 | 49898.9 | 2027-05-21 | 3581.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N6000-06 | Brake POS 6 | 16000 | 37477 | 2022-07-06 | 49898.9 | 2027-05-21 | 3578.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 16000 | 45978 | 2025-03-23 | 49898.9 | 2029-09-17 | 12079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7070 | Pump Implement | 16000 | 45978 | 2025-03-22 | 49898.9 | 2029-09-17 | 12079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 16000 | 37873 | 2023-02-03 | 49898.9 | 2027-06-29 | 3974.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7230 | Hyd Motor Circle Drive | 8000 | 42637 | 2024-02-28 | 49898.9 | 2026-08-10 | 738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7232 | Hyd Motor Engine Fan | 16000 | 45978 | 2025-03-23 | 49898.9 | 2029-09-17 | 12079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 16000 | 42637 | 2024-03-26 | 49898.9 | 2028-10-18 | 8738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 16000 | 49533 | 2026-01-21 | 49898.9 | 2030-09-07 | 15634.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 16000 | 49390 | 2026-01-10 | 49898.9 | 2030-08-24 | 15491.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 16000 | 23519 | 2016-12-05 | 49898.9 | 2023-07-25 | -10379.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7422 | Hyd Cyl Blade Tip | 16000 | 25573 | 2018-06-11 | 49898.9 | 2024-02-15 | -8325.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7440 | Hyd Cyl Centreshift | 16000 | 44205 | 2024-10-05 | 49898.9 | 2029-03-24 | 10306.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 24000 | 29557 | 2019-07-11 | 49898.9 | 2027-05-29 | 3658.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7540 | Hyd Cyl Sideshift | 16000 | 49579 | 2026-01-29 | 49898.9 | 2030-09-12 | 15680.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 12000 | 46753 | 2025-06-03 | 49898.9 | 2028-10-29 | 8854.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 41363 | 2023-10-20 | 49898.9 | 2027-05-09 | 3464.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 12000 | 41363 | 2023-10-20 | 49898.9 | 2027-05-09 | 3464.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7600-FR | Control Valve FRONT | 16000 | 25573 | 2018-06-11 | 49898.9 | 2024-02-15 | -8325.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7600-RE | Control Valve REAR | 16000 | 25573 | 2018-06-11 | 49898.9 | 2024-02-15 | -8325.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7600-S | Control Valve - STEERING | 16000 | 25573 | 2018-06-11 | 49898.9 | 2024-02-15 | -8325.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7610 | Hyd Cooler Core | 16000 | 41427 | 2023-10-27 | 49898.9 | 2028-06-19 | 7528.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7620 | Hyd Rotary Joint | 16000 | 41737 | 2023-11-19 | 49898.9 | 2028-07-20 | 7838.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7650-F | Hyd Accum Blade Cushion FRONT | 16000 | 41427 | 2023-10-27 | 49898.9 | 2028-06-19 | 7528.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7650-RE | Hyd Accum Blade Cushion REAR | 16000 | 41427 | 2023-10-27 | 49898.9 | 2028-06-19 | 7528.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7654-F | Hyd Accum Service Brake - FR | 16000 | 41427 | 2023-10-28 | 49898.9 | 2028-06-19 | 7528.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N7654-RE | Hyd Accum Service Brake - REAR | 16000 | 41427 | 2023-10-26 | 49898.9 | 2028-06-19 | 7528.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N8040 | Circle & Drawbar | 16000 | 37873 | 2022-10-21 | 49898.9 | 2027-06-29 | 3974.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N8127-F | Axle Assembly FRONT | 12000 | 41363 | 2023-10-20 | 49898.9 | 2027-05-09 | 3464.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N8131-01 | Steering Tie Rod Ends POS1 | 12000 | 46753 | 2025-06-01 | 49898.9 | 2028-10-29 | 8854.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N8131-02 | Steering Tie Rod Ends POS2 | 12000 | 46753 | 2025-06-03 | 49898.9 | 2028-10-29 | 8854.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N8300 | Artic Hitch | 16000 | 42637 | 2024-03-20 | 49898.9 | 2028-10-18 | 8738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N8995 | Operator Seat | 6000 | 48618 | 2025-11-06 | 49898.9 | 2027-09-12 | 4719.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9020 | Alternator | 8000 | 45978 | 2025-03-22 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9050 | Starter Motor | 8000 | 45978 | 2025-03-21 | 49898.9 | 2027-07-10 | 4079.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9500 | Air Cond'r-Serv | 4000 | 45978 | 2025-03-23 | 49898.9 | 2026-06-05 | 79.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9500-MA | Air Cond'r-Serv - MAJOR | 16000 | 42637 | 2024-03-29 | 49898.9 | 2028-10-18 | 8738.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9501 | A/C Compressor | 8000 | 44909 | 2024-12-15 | 49898.9 | 2027-03-25 | 3010.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9998 | Extended Life Rebuild | 35000 |  | 2010-03-27 | 49898.9 | 2022-04-29 | -14898.9 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9998-01 | Extended Life Rebuild ONE | 50000 |  | 2010-03-27 | 49898.9 | 2026-06-07 | 101.1 | WA | Norrish Earthmoving
GR1373 | Cat 16M | N9998-02 | Extended Life Rebuild TWO | 75000 |  | 2010-03-27 | 49898.9 | 2033-04-11 | 25101.1 | WA | Norrish Earthmoving
GR1475 | Cat 24M | N0050 | Blade Assembly | 20000 |  | 2022-09-04 | 14603 | 2027-04-30 | 5397 | WA | Iron Bridge
GR1475 | Cat 24M | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-09-04 | 14603 | 2027-09-03 |  | WA | Iron Bridge
GR1475 | Cat 24M | N0200 | A Frame Bearing | 20000 |  | 2022-09-04 | 14603 | 2027-04-30 | 5397 | WA | Iron Bridge
GR1475 | Cat 24M | N1000 | Engine | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N1002 | Engine Valve Adj | 2000 | 11884 | 2025-11-29 | 14603 | 2026-04-15 | -719 | WA | Iron Bridge
GR1475 | Cat 24M | N1002-01 | Engine Valve Adj - Initial | 250 | 12137 | 2025-12-17 | 14603 | 2026-01-09 | -2216 | WA | Iron Bridge
GR1475 | Cat 24M | N1100 | Turbo Primary | 6000 | 11367 | 2025-08-05 | 14603 | 2026-11-17 | 2764 | WA | Iron Bridge
GR1475 | Cat 24M | N1202 | Fuel Transfer Pump | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N1210 | Fuel Injectors | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N1300 | Cooling Sys Service | 6000 | 11884 | 2025-11-29 | 14603 | 2026-12-19 | 3281 | WA | Iron Bridge
GR1475 | Cat 24M | N1301 | Water Pump | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N1310 | Radiator | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N1312 | Aftercooler Core | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N1400 | Belt Tensioner Assembly | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N2000 | Transmission | 12000 | 11883 | 2025-11-22 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N2050 | Torque Convertor | 12000 | 11883 | 2025-11-22 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N2052 | Convertor/Trans Pump | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N3028 | Drive Shaft T/C - Trans | 12000 | 11883 | 2025-11-20 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N3029 | Uni's T/C - Trans | 6000 | 11883 | 2025-11-20 | 14603 | 2026-12-19 | 3280 | WA | Iron Bridge
GR1475 | Cat 24M | N3037 | Drive Shaft Trans - Bevel Gear | 12000 | 11883 | 2025-11-21 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N3038 | Uni's Trans - Bevel Gear | 6000 | 11883 | 2025-11-21 | 14603 | 2026-12-19 | 3280 | WA | Iron Bridge
GR1475 | Cat 24M | N3210-03 | Tandem Drive Chain POS 3 | 16000 | 11883 | 2025-10-28 | 14603 | 2028-09-04 | 13280 | WA | Iron Bridge
GR1475 | Cat 24M | N3210-04 | Tandem Drive Chain POS 4 | 16000 | 11883 | 2025-10-18 | 14603 | 2028-09-04 | 13280 | WA | Iron Bridge
GR1475 | Cat 24M | N3210-05 | Tandem Drive Chain POS 5 | 16000 | 11883 | 2025-10-13 | 14603 | 2028-09-04 | 13280 | WA | Iron Bridge
GR1475 | Cat 24M | N3210-06 | Tandem Drive Chain POS 6 | 16000 | 11883 | 2025-10-12 | 14603 | 2028-09-04 | 13280 | WA | Iron Bridge
GR1475 | Cat 24M | N3300-F | Circle Drive Box FRONT | 12000 | 10270 | 2025-05-21 | 14603 | 2027-09-19 | 7667 | WA | Iron Bridge
GR1475 | Cat 24M | N3300-RE | Circle Drive Box REAR | 12000 | 4727 | 2023-10-16 | 14603 | 2026-10-08 | 2124 | WA | Iron Bridge
GR1475 | Cat 24M | N4000 | Bevel Gear | 12000 | 11883 | 2025-10-29 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N4102-L | Axle Shaft LEFT | 12000 | 11883 | 2025-10-29 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N4102-R | Axle Shaft RIGHT | 12000 | 11883 | 2025-10-29 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N5000-L | Final Drive LEFT | 12000 | 11883 | 2025-10-29 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N5000-R | Final Drive RIGHT | 12000 | 11883 | 2025-10-29 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N5020-01 | Wheel Bearing POS 1 | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N5020-02 | Wheel Bearing POS 2 | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N6000-03 | Brake POS 3 | 16000 | 6496 | 2024-07-18 | 14603 | 2027-10-03 | 7893 | WA | Iron Bridge
GR1475 | Cat 24M | N6000-04 | Brake POS 4 | 16000 | 11883 | 2025-10-11 | 14603 | 2028-09-04 | 13280 | WA | Iron Bridge
GR1475 | Cat 24M | N6000-05 | Brake POS 5 | 16000 | 6496 | 2024-07-18 | 14603 | 2027-10-03 | 7893 | WA | Iron Bridge
GR1475 | Cat 24M | N6000-06 | Brake POS 6 | 16000 | 11883 | 2025-10-10 | 14603 | 2028-09-04 | 13280 | WA | Iron Bridge
GR1475 | Cat 24M | N6030-L | Brake Slack Adjuster LEFT | 8000 | 7651 | 2024-10-17 | 14603 | 2026-08-02 | 1048 | WA | Iron Bridge
GR1475 | Cat 24M | N6030-R | Brake Slack Adjuster RIGHT | 8000 | 7681 | 2024-10-17 | 14603 | 2026-08-03 | 1078 | WA | Iron Bridge
GR1475 | Cat 24M | N7029 | Pump Brake & Cooling Fan Eng | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7031 | Pump Diff Lock | 16000 | 5343 | 2023-11-10 | 14603 | 2027-07-23 | 6740 | WA | Iron Bridge
GR1475 | Cat 24M | N7070 | Pump Implement | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7088 | Pump Park Brk Rel | 32000 |  | 2022-09-04 | 14603 | 2029-05-19 | 17397 | WA | Iron Bridge
GR1475 | Cat 24M | N7120 | Pump Steering | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7122 | Pump Emerg/Sup Steering | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7230-F | Hyd Motor Circle Drive FRONT | 12000 | 10270 | 2025-05-21 | 14603 | 2027-09-19 | 7667 | WA | Iron Bridge
GR1475 | Cat 24M | N7230-RE | Hyd Motor Circle Drive REAR | 12000 | 5908 | 2024-05-01 | 14603 | 2026-12-21 | 3305 | WA | Iron Bridge
GR1475 | Cat 24M | N7232 | Hyd Motor Engine Fan | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7414-L | Hyd Cyl Artic LEFT | 16000 | 12927 | 2026-02-06 | 14603 | 2028-11-08 | 14324 | WA | Iron Bridge
GR1475 | Cat 24M | N7414-R | Hyd Cyl Artic RIGHT | 16000 | 11319 | 2025-07-21 | 14603 | 2028-07-31 | 12716 | WA | Iron Bridge
GR1475 | Cat 24M | N7420-L | Hyd Cyl Blade Lift LEFT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7420-R | Hyd Cyl Blade Lift RIGHT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7422-L | Hyd Cyl Blade Tip LEFT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7422-R | Hyd Cyl Blade Tip RIGHT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7440 | Hyd Cyl Centreshift | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7510-L | Hyd Cyl Ripper Lift LEFT | 24000 | 11319 | 2025-07-20 | 14603 | 2029-12-13 | 20716 | WA | Iron Bridge
GR1475 | Cat 24M | N7510-R | Hyd Cyl Ripper Lift RIGHT | 24000 |  | 2022-09-04 | 14603 | 2028-01-05 | 9397 | WA | Iron Bridge
GR1475 | Cat 24M | N7540 | Hyd Cyl Sideshift | 16000 | 8257 | 2024-11-26 | 14603 | 2028-01-21 | 9654 | WA | Iron Bridge
GR1475 | Cat 24M | N7542-L | Hyd Cyl Steer LEFT | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 12383 | 2026-01-07 | 14603 | 2028-01-29 | 9780 | WA | Iron Bridge
GR1475 | Cat 24M | N7580-L | Hyd Cyl Wheel Lean LEFT | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N7580-R | Hyd Cyl Wheel Lean RIGHT | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N7600-L | Control Valve LEFT | 24000 |  | 2022-09-04 | 14603 | 2028-01-05 | 9397 | WA | Iron Bridge
GR1475 | Cat 24M | N7600-R | Control Valve RIGHT | 24000 |  | 2022-09-04 | 14603 | 2028-01-05 | 9397 | WA | Iron Bridge
GR1475 | Cat 24M | N7600-S | Control Valve - STEERING | 12000 | 12163 | 2025-12-27 | 14603 | 2028-01-16 | 9560 | WA | Iron Bridge
GR1475 | Cat 24M | N7610 | Hyd Cooler Core | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7647-L | Hyd Accum Brake Reseal LEFT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7647-R | Hyd Accum Brake Reseal RIGHT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7650-F | Hyd Accum Blade Cushion FRONT | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N7650-RE | Hyd Accum Blade Cushion REAR | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N8000 | Main Frame/Chassis | 32000 |  | 2022-09-04 | 14603 | 2029-05-19 | 17397 | WA | Iron Bridge
GR1475 | Cat 24M | N8040 | Circle & Drawbar | 24000 |  | 2022-09-04 | 14603 | 2028-01-05 | 9397 | WA | Iron Bridge
GR1475 | Cat 24M | N8127-F | Axle Assembly FRONT | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N8131-01 | Steering Tie Rod Ends POS1 | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N8131-02 | Steering Tie Rod Ends POS2 | 12000 | 11883 | 2025-11-03 | 14603 | 2027-12-29 | 9280 | WA | Iron Bridge
GR1475 | Cat 24M | N8300 | Artic Hitch | 16000 |  | 2022-09-04 | 14603 | 2026-08-23 | 1397 | WA | Iron Bridge
GR1475 | Cat 24M | N8995 | Operator Seat | 6000 | 11952 | 2025-12-07 | 14603 | 2026-12-23 | 3349 | WA | Iron Bridge
GR1475 | Cat 24M | N9020 | Alternator | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N9050 | Starter Motor | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N9500 | Air Cond'r-Serv | 6000 | 11884 | 2025-11-29 | 14603 | 2026-12-19 | 3281 | WA | Iron Bridge
GR1475 | Cat 24M | N9500-MA | Air Cond'r-Serv - MAJOR | 12000 | 11884 | 2025-11-29 | 14603 | 2027-12-29 | 9281 | WA | Iron Bridge
GR1475 | Cat 24M | N9501 | A/C Compressor | 6000 | 13139 | 2026-02-22 | 14603 | 2027-03-08 | 4536 | WA | Iron Bridge
GR1475 | Cat 24M | N9998 | Extended Life Rebuild | 50000 |  | 2022-09-04 | 14603 | 2032-06-17 | 35397 | WA | Iron Bridge
GR1475 | Cat 24M | N9998-01 | Extended Life Rebuild ONE | 70000 |  | 2022-09-04 | 14603 | 2035-11-19 | 55397 | WA | Iron Bridge
GR1475 | Cat 24M | N9998-02 | Extended Life Rebuild TWO | 90000 |  | 2022-09-04 | 14603 | 2039-04-22 | 75397 | WA | Iron Bridge
GR1527 | Cat 140M | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-05-15 | 3320 | 2028-05-13 |  | WA | Iron Bridge
GR1527 | Cat 140M | N8995 | Operator Seat | 6000 |  |  | 3320 | 2027-04-28 | 2680 | WA | Iron Bridge
GR1527 | Cat 140M | N9500 | Air Cond'r-Serv | 5000 |  |  | 3320 | 2026-12-24 | 1680 | WA | Iron Bridge
GR1528 | Cat 14M | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-05-15 | 3973 | 2027-05-14 |  | WA | Iron Bridge
GR1528 | Cat 14M | N8995 | Operator Seat | 6000 |  |  | 3973 | 2027-02-05 | 2027 | WA | Iron Bridge
GR1528 | Cat 14M | N9500 | Air Cond'r-Serv | 5000 |  |  | 3973 | 2026-10-03 | 1027 | WA | Iron Bridge
GR1549 | Cat 16M | N0050 | Blade Assembly | 12000 | 14535 | 2023-03-16 | 23165.3 | 2027-04-30 | 3369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-12-15 | 23165.3 | 2028-12-13 |  | WA | Yilgarn Hub
GR1549 | Cat 16M | N0200 | A Frame Bearing | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1000 | Engine | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1002 | Engine Valve Adj | 2500 | 14535 | 2023-03-16 | 23165.3 | 2024-09-22 | -6130.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1100 | Turbo Primary | 7000 | 14535 | 2023-03-16 | 23165.3 | 2025-12-23 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1202 | Fuel Transfer Pump | 7000 | 14535 | 2023-03-16 | 23165.3 | 2025-12-16 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1300 | Cooling Sys Service | 7000 | 14535 | 2023-03-16 | 23165.3 | 2025-12-23 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1301 | Water Pump | 7000 | 14535 | 2023-03-16 | 23165.3 | 2025-12-23 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1310 | Radiator | 14000 | 13268 | 2022-08-08 | 23165.3 | 2027-07-12 | 4102.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1312 | Aftercooler Core | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1320 | Cooling Fan Engine | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N1400 | Belt Tensioner Assembly | 7000 | 14535 | 2023-03-16 | 23165.3 | 2025-12-23 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N2000 | Transmission | 14000 | 13268 | 2022-08-08 | 23165.3 | 2027-07-12 | 4102.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N2004 | Transmission Pump | 14000 | 13268 | 2022-08-08 | 23165.3 | 2027-07-12 | 4102.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N2090 | Drv Coupling | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3037 | Drive Shaft Trans - Bevel Gear | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 7000 | 14535 | 2021-04-04 | 23165.3 | 2025-12-23 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3210-03 | Tandem Drive Chain POS 3 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3210-04 | Tandem Drive Chain POS 4 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3210-05 | Tandem Drive Chain POS 5 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3210-06 | Tandem Drive Chain POS 6 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N3300 | Circle Drive Box | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N4000 | Bevel Gear | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N4100-L | Rear Axle LEFT | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N4100-R | Rear Axle RIGHT | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N5000-L | Final Drive LEFT | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N5000-R | Final Drive RIGHT | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N5020-01 | Wheel Bearing POS 1 | 14000 | 13459 | 2022-09-02 | 23165.3 | 2027-07-31 | 4293.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N5020-02 | Wheel Bearing POS 2 | 14000 | 13459 | 2022-09-02 | 23165.3 | 2027-07-31 | 4293.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N6000-03 | Brake POS 3 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N6000-04 | Brake POS 4 | 14000 | 16877 | 2023-09-12 | 23165.3 | 2028-07-07 | 7711.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N6000-05 | Brake POS 5 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N6000-06 | Brake POS 6 | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 8000 | 20239 | 2024-09-05 | 23165.3 | 2027-10-17 | 5073.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7070 | Pump Implement | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 16000 | 16000 | 2023-03-16 | 23165.3 | 2028-10-27 | 8834.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7230 | Hyd Motor Circle Drive | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7232 | Hyd Motor Engine Fan | 8000 | 20239 | 2024-09-05 | 23165.3 | 2027-10-17 | 5073.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 8000 | 14535 | 2023-03-16 | 23165.3 | 2026-04-02 | -630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 8000 | 14535 | 2023-03-16 | 23165.3 | 2026-04-02 | -630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 20264 | 2024-09-10 | 23165.3 | 2027-10-20 | 5098.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 20239 | 2024-09-05 | 23165.3 | 2027-10-17 | 5073.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7422 | Hyd Cyl Blade Tip | 8000 | 20239 | 2024-09-04 | 23165.3 | 2027-10-17 | 5073.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7440 | Hyd Cyl Centreshift | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7540 | Hyd Cyl Sideshift | 10000 | 17051 | 2024-09-05 | 23165.3 | 2027-06-21 | 3885.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 8000 | 13459 | 2022-09-02 | 23165.3 | 2025-12-08 | -1706.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 8000 | 13459 | 2022-09-02 | 23165.3 | 2025-12-08 | -1706.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 8000 | 13459 | 2022-09-02 | 23165.3 | 2025-12-08 | -1706.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7600-FR | Control Valve FRONT | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7600-RE | Control Valve REAR | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7600-S | Control Valve - STEERING | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7610 | Hyd Cooler Core | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7620 | Hyd Rotary Joint | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7650-F | Hyd Accum Blade Cushion FRONT | 16000 | 14535 | 2023-03-16 | 23165.3 | 2028-06-03 | 7369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7650-RE | Hyd Accum Blade Cushion REAR | 16000 | 14535 | 2023-03-16 | 23165.3 | 2028-06-03 | 7369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7654-F | Hyd Accum Service Brake - FR | 16000 | 14535 | 2023-03-16 | 23165.3 | 2028-06-03 | 7369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N7654-RE | Hyd Accum Service Brake - REAR | 16000 | 14535 | 2023-03-16 | 23165.3 | 2028-06-03 | 7369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N8127-F | Axle Assembly FRONT | 16000 | 19541 | 2024-05-13 | 23165.3 | 2029-10-17 | 12375.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N8131-01 | Steering Tie Rod Ends POS1 | 8000 | 13459 | 2022-09-02 | 23165.3 | 2025-12-08 | -1706.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N8131-02 | Steering Tie Rod Ends POS2 | 8000 | 13459 | 2022-09-02 | 23165.3 | 2025-12-08 | -1706.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N8300 | Artic Hitch | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N8995 | Operator Seat | 6000 | 20239 | 2024-09-05 | 23165.3 | 2027-03-31 | 3073.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N9020 | Alternator | 7000 | 21435 | 2026-01-22 | 23165.3 | 2027-11-06 | 5269.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N9050 | Starter Motor | 7000 | 14535 | 2023-03-16 | 23165.3 | 2025-12-16 | -1630.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N9500 | Air Cond'r-Serv | 3500 | 18517 | 2025-01-01 | 23165.3 | 2026-02-02 | -1148.3 | WA | Yilgarn Hub
GR1549 | Cat 16M | N9500-MA | Air Cond'r-Serv - MAJOR | 14000 | 18597 | 2025-01-01 | 23165.3 | 2028-12-26 | 9431.7 | WA | Yilgarn Hub
GR1549 | Cat 16M | N9501 | A/C Compressor | 14000 | 14535 | 2023-03-16 | 23165.3 | 2027-11-16 | 5369.7 | WA | Yilgarn Hub
GR1550 | Cat 16M | N0050 | Blade Assembly | 12000 |  | 2018-03-28 | 27110.6 | 2022-04-08 | -15110.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-08-15 | 27110.6 | 2029-08-14 |  | WA | Yilgarn Hub
GR1550 | Cat 16M | N0200 | A Frame Bearing | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1000 | Engine | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1002 | Engine Valve Adj | 2500 | 12845 | 2020-07-14 | 27110.6 | 2023-03-08 | -11765.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1100 | Turbo Primary | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1202 | Fuel Transfer Pump | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1300 | Cooling Sys Service | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1301 | Water Pump | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1310 | Radiator | 14000 | 24520 | 2024-11-02 | 27110.6 | 2029-07-12 | 11409.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1312 | Aftercooler Core | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1320 | Cooling Fan Engine | 14000 | 24520 | 2024-11-02 | 27110.6 | 2029-07-12 | 11409.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N1400 | Belt Tensioner Assembly | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N2000 | Transmission | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N2004 | Transmission Pump | 14000 | 1285 | 2020-07-14 | 27110.6 | 2023-03-02 | -11825.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N2090 | Drv Coupling | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3037 | Drive Shaft Trans - Bevel Gear | 14000 | 13896 | 2020-07-14 | 27110.6 | 2026-08-15 | 785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3038 | Uni's Trans - Bevel Gear | 7000 | 20896 | 2023-10-21 | 27110.6 | 2026-08-15 | 785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3210-03 | Tandem Drive Chain POS 3 | 14000 | 14962 | 2022-09-14 | 27110.6 | 2026-11-29 | 1851.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3210-04 | Tandem Drive Chain POS 4 | 14000 | 14962 | 2022-09-14 | 27110.6 | 2026-11-29 | 1851.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3210-05 | Tandem Drive Chain POS 5 | 14000 | 14442 | 2022-03-14 | 27110.6 | 2026-10-08 | 1331.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3210-06 | Tandem Drive Chain POS 6 | 14000 | 14442 | 2022-03-14 | 27110.6 | 2026-10-08 | 1331.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N3300 | Circle Drive Box | 14000 | 26248 | 2026-03-06 | 27110.6 | 2030-01-01 | 13137.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N4000 | Bevel Gear | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N4100-L | Rear Axle LEFT | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N4100-R | Rear Axle RIGHT | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N5000-L | Final Drive LEFT | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N5000-R | Final Drive RIGHT | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N5020-01 | Wheel Bearing POS 1 | 14000 | 24512 | 2024-10-27 | 27110.6 | 2029-07-11 | 11401.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N5020-02 | Wheel Bearing POS 2 | 14000 | 24502 | 2024-10-22 | 27110.6 | 2029-07-10 | 11391.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N6000-03 | Brake POS 3 | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N6000-04 | Brake POS 4 | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N6000-05 | Brake POS 5 | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N6000-06 | Brake POS 6 | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 8000 | 20896 | 2023-10-21 | 27110.6 | 2026-11-23 | 1785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7070 | Pump Implement | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 16000 | 20896 | 2023-10-24 | 27110.6 | 2029-01-31 | 9785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7230 | Hyd Motor Circle Drive | 14000 | 26248 | 2026-03-06 | 27110.6 | 2030-01-01 | 13137.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7232 | Hyd Motor Engine Fan | 8000 | 24520 | 2024-11-02 | 27110.6 | 2027-11-20 | 5409.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 8000 | 20896 | 2023-10-20 | 27110.6 | 2026-11-23 | 1785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 8000 | 24707 | 2024-11-27 | 27110.6 | 2027-12-09 | 5596.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 16660 | 2023-01-11 | 27110.6 | 2025-09-25 | -2450.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 20896 | 2023-10-21 | 27110.6 | 2026-11-23 | 1785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7422 | Hyd Cyl Blade Tip | 8000 | 20896 | 2023-10-21 | 27110.6 | 2026-11-23 | 1785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7440 | Hyd Cyl Centreshift | 14000 | 23087 | 2024-05-19 | 27110.6 | 2029-02-19 | 9976.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7540 | Hyd Cyl Sideshift | 10000 | 20896 | 2023-10-22 | 27110.6 | 2027-06-11 | 3785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 8000 | 20586 | 2023-09-16 | 27110.6 | 2026-10-23 | 1475.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 8000 | 20586 | 2023-09-16 | 27110.6 | 2026-10-23 | 1475.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 8000 | 20896 | 2023-10-21 | 27110.6 | 2026-11-23 | 1785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7600-FR | Control Valve FRONT | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7600-RE | Control Valve REAR | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7600-S | Control Valve - STEERING | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7610 | Hyd Cooler Core | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7620 | Hyd Rotary Joint | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7650-F | Hyd Accum Blade Cushion FRONT | 16000 | 20896 | 2023-10-23 | 27110.6 | 2029-01-31 | 9785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7650-RE | Hyd Accum Blade Cushion REAR | 16000 | 20896 | 2023-10-23 | 27110.6 | 2029-01-31 | 9785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7654-F | Hyd Accum Service Brake - FR | 16000 | 20896 | 2023-10-23 | 27110.6 | 2029-01-31 | 9785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N7654-RE | Hyd Accum Service Brake - REAR | 16000 | 20896 | 2023-10-23 | 27110.6 | 2029-01-31 | 9785.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N8127-F | Axle Assembly FRONT | 16000 | 11817 | 2019-11-27 | 27110.6 | 2026-08-07 | 706.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N8131-01 | Steering Tie Rod Ends POS1 | 8000 | 20586 | 2023-09-16 | 27110.6 | 2026-10-23 | 1475.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N8131-02 | Steering Tie Rod Ends POS2 | 8000 | 20586 | 2023-09-16 | 27110.6 | 2026-10-23 | 1475.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N8300 | Artic Hitch | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N8995 | Operator Seat | 6000 | 24930 | 2024-12-25 | 27110.6 | 2027-06-14 | 3819.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N9020 | Alternator | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N9050 | Starter Motor | 7000 | 12845 | 2020-07-14 | 27110.6 | 2024-05-31 | -7265.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N9500 | Air Cond'r-Serv | 3500 | 23479 | 2025-01-01 | 27110.6 | 2026-05-15 | -131.6 | WA | Yilgarn Hub
GR1550 | Cat 16M | N9500-MA | Air Cond'r-Serv - MAJOR | 12000 | 20799 | 2025-01-01 | 27110.6 | 2027-12-18 | 5688.4 | WA | Yilgarn Hub
GR1550 | Cat 16M | N9501 | A/C Compressor | 14000 | 12845 | 2020-07-14 | 27110.6 | 2026-05-01 | -265.6 | WA | Yilgarn Hub
GR6524 | Cat 16M | N0050 | Blade Assembly | 36000 |  | 2022-06-01 | 17448.6 | 2033-08-29 | 18551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N1000 | Engine | 18000 |  | 2022-06-01 | 17448.6 | 2026-08-15 | 551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N1100 | Turbo Primary | 18000 |  | 2022-06-01 | 17448.6 | 2026-08-15 | 551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N1301 | Water Pump | 18000 | 12388.3 | 2024-07-18 | 17448.6 | 2031-06-20 | 12939.7 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N1310 | Radiator | 18000 |  | 2022-06-01 | 17448.6 | 2026-08-15 | 551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N2000 | Transmission | 18000 |  | 2022-06-01 | 17448.6 | 2026-08-15 | 551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N2004 | Transmission Pump | 18000 |  | 2022-06-01 | 17448.6 | 2026-08-15 | 551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N3210-L | Tandem Drive Chain LEFT | 12000 | 11896.36 | 2024-05-17 | 17448.6 | 2028-12-04 | 6447.76 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N3210-R | Tandem Drive Chain RIGHT | 12000 | 12349.74 | 2024-07-13 | 17448.6 | 2029-02-07 | 6901.14 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N3300 | Circle Drive Box | 12000 | 16865 | 2026-03-31 | 17448.6 | 2030-11-14 | 11416.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N4000 | Bevel Gear | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N5000-L | Final Drive LEFT | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N5000-R | Final Drive RIGHT | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N6000-LF | Brake LEFT FRONT | 24000 | 13646.05 | 2025-01-11 | 17448.6 | 2034-04-21 | 20197.45 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N6000-LR | Brake LEFT REAR | 24000 | 7958.28 | 2023-02-09 | 17448.6 | 2032-01-30 | 14509.68 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N6000-RF | Brake RIGHT FRONT | 24000 | 16332 | 2026-01-19 | 17448.6 | 2035-05-10 | 22883.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N6000-RR | Brake RIGHT REAR | 24000 | 13878.09 | 2025-02-07 | 17448.6 | 2034-05-24 | 20429.49 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 12000 | 11896.36 | 2024-05-17 | 17448.6 | 2028-12-04 | 6447.76 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7120 | Pump Steering | 12000 | 11896.36 | 2024-05-17 | 17448.6 | 2028-12-04 | 6447.76 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 12000 | 13090.8 | 2024-11-07 | 17448.6 | 2029-05-24 | 7642.2 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7230 | Hyd Motor Circle Drive | 12000 | 7434.31 | 2022-11-25 | 17448.6 | 2027-03-08 | 1985.71 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7234 | Hyd Motor Cooler Fan | 12000 | 11896.36 | 2024-05-17 | 17448.6 | 2028-12-04 | 6447.76 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 24000 | 10085.99 | 2023-10-06 | 17448.6 | 2032-11-29 | 16637.39 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 24000 | 17354.3 | 2026-05-15 | 17448.6 | 2035-10-03 | 23905.7 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 24000 | 16903 | 2026-04-06 | 17448.6 | 2035-07-31 | 23454.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7421 | Hyd Cyl Blade Tilt | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7440 | Hyd Cyl Centreshift | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7540 | Hyd Cyl Sideshift | 24000 | 16843 | 2026-03-25 | 17448.6 | 2035-07-22 | 23394.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 12000 | 17173.2 | 2026-05-02 | 17448.6 | 2030-12-28 | 11724.6 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 15254 | 2025-07-25 | 17448.6 | 2030-03-29 | 9805.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8040 | Circle & Drawbar | 15000 | 15254 | 2025-07-25 | 17448.6 | 2031-05-31 | 12805.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8042 | Circle Bearing | 15000 | 14381.34 | 2025-04-12 | 17448.6 | 2031-01-27 | 11932.74 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8127-F | Axle Assembly FRONT | 12000 | 15254 | 2025-07-25 | 17448.6 | 2030-03-29 | 9805.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8128-03 | Spindle POS 3 | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8128-04 | Spindle POS 4 | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8128-05 | Spindle POS 5 | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8128-06 | Spindle POS 6 | 24000 |  | 2022-06-01 | 17448.6 | 2028-12-19 | 6551.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8300 | Artic Hitch | 36000 | 15254 | 2025-07-25 | 17448.6 | 2039-08-17 | 33805.4 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N8995 | Operator Seat | 10000 | 11660.98 | 2024-04-15 | 17448.6 | 2028-01-20 | 4212.38 | WA | Sanjiv Ridge
GR6524 | Cat 16M | N9500 | Air Cond'r-Serv |  |  | 2025-07-25 | 17448.6 | 2026-07-25 |  | WA | Sanjiv Ridge
GR6528 | Cat 16M | N0050 | Blade Assembly | 36000 |  | 2022-06-01 | 33341.1 | 2027-08-18 | 2658.9 | WA | Miralga Creek
GR6528 | Cat 16M | N1000 | Engine | 18000 | 26893.33 | 2022-09-14 | 33341.1 | 2031-09-21 | 11552.23 | WA | Miralga Creek
GR6528 | Cat 16M | N1002-01 | Engine Valve Adj - Initial | 250 | 26893.33 |  | 33341.1 | 2023-07-21 | -6197.77 | WA | Miralga Creek
GR6528 | Cat 16M | N1100 | Turbo Primary | 18000 |  | 2022-06-01 | 33341.1 | 2019-05-07 | -15341.1 | WA | Miralga Creek
GR6528 | Cat 16M | N1301 | Water Pump | 18000 |  | 2022-06-01 | 33341.1 | 2019-05-07 | -15341.1 | WA | Miralga Creek
GR6528 | Cat 16M | N1310 | Radiator | 18000 | 33080 | 2026-04-01 | 33341.1 | 2034-07-26 | 17738.9 | WA | Miralga Creek
GR6528 | Cat 16M | N2000 | Transmission | 18000 | 25244 | 2021-09-01 | 33341.1 | 2030-12-17 | 9902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N2004 | Transmission Pump | 18000 | 25244 | 2021-09-01 | 33341.1 | 2030-12-17 | 9902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N3210-L | Tandem Drive Chain LEFT | 12000 |  | 2016-02-08 | 33341.1 | 2016-08-01 | -21341.1 | WA | Miralga Creek
GR6528 | Cat 16M | N3210-R | Tandem Drive Chain RIGHT | 12000 |  | 2016-02-08 | 33341.1 | 2016-08-01 | -21341.1 | WA | Miralga Creek
GR6528 | Cat 16M | N3300 | Circle Drive Box | 12000 | 29429.88 | 2024-03-25 | 33341.1 | 2030-02-15 | 8088.78 | WA | Miralga Creek
GR6528 | Cat 16M | N4000 | Bevel Gear | 24000 |  | 2021-07-01 | 33341.1 | 2022-02-08 | -9341.1 | WA | Miralga Creek
GR6528 | Cat 16M | N5000-L | Final Drive LEFT | 24000 | 25244 | 2021-09-01 | 33341.1 | 2033-09-21 | 15902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N5000-R | Final Drive RIGHT | 24000 | 25244 | 2021-09-01 | 33341.1 | 2033-09-21 | 15902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N6000-LF | Brake LEFT FRONT | 24000 | 29963.62 | 2024-08-17 | 33341.1 | 2035-11-23 | 20622.52 | WA | Miralga Creek
GR6528 | Cat 16M | N6000-LR | Brake LEFT REAR | 24000 | 29963.62 | 2024-08-17 | 33341.1 | 2035-11-23 | 20622.52 | WA | Miralga Creek
GR6528 | Cat 16M | N6000-RF | Brake RIGHT FRONT | 24000 | 29982.6 | 2024-08-25 | 33341.1 | 2035-11-26 | 20641.5 | WA | Miralga Creek
GR6528 | Cat 16M | N6000-RR | Brake RIGHT REAR | 24000 | 30526.3 | 2025-01-18 | 33341.1 | 2036-02-26 | 21185.2 | WA | Miralga Creek
GR6528 | Cat 16M | N7029 | Pump Brake & Cooling Fan Eng | 12000 | 27439.73 | 2022-12-04 | 33341.1 | 2029-03-18 | 6098.63 | WA | Miralga Creek
GR6528 | Cat 16M | N7086 | Pump Implement & Steering | 12000 | 25244 | 2021-09-01 | 33341.1 | 2028-03-14 | 3902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7122 | Pump Emerg/Sup Steering | 12000 | 25244 | 2021-09-01 | 33341.1 | 2028-03-14 | 3902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7230 | Hyd Motor Circle Drive | 12000 | 25244 | 2021-09-01 | 33341.1 | 2028-03-14 | 3902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7232 | Hyd Motor Engine Fan | 12000 | 27439.83 | 2022-12-04 | 33341.1 | 2029-03-18 | 6098.73 | WA | Miralga Creek
GR6528 | Cat 16M | N7414-L | Hyd Cyl Artic LEFT | 24000 | 25244 | 2021-09-01 | 33341.1 | 2033-09-21 | 15902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7414-R | Hyd Cyl Artic RIGHT | 24000 | 25244 | 2021-09-01 | 33341.1 | 2033-09-21 | 15902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7420-L | Hyd Cyl Blade Lift LEFT | 24000 | 25366 | 2021-12-02 | 33341.1 | 2033-10-11 | 16024.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7420-R | Hyd Cyl Blade Lift RIGHT | 24000 | 29875.3 | 2024-07-23 | 33341.1 | 2035-11-08 | 20534.2 | WA | Miralga Creek
GR6528 | Cat 16M | N7421 | Hyd Cyl Blade Tilt | 24000 | 30375.48 | 2024-12-19 | 33341.1 | 2036-01-31 | 21034.38 | WA | Miralga Creek
GR6528 | Cat 16M | N7440 | Hyd Cyl Centreshift | 24000 | 25244 | 2021-09-01 | 33341.1 | 2033-09-21 | 15902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7510 | Hyd Cyl Ripper Lift | 24000 | 29000.08 | 2023-11-11 | 33341.1 | 2035-06-14 | 19658.98 | WA | Miralga Creek
GR6528 | Cat 16M | N7540 | Hyd Cyl Sideshift | 24000 | 32814 | 2026-02-03 | 33341.1 | 2037-03-16 | 23472.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7542-L | Hyd Cyl Steer LEFT | 12000 | 29225.17 | 2023-12-24 | 33341.1 | 2030-01-12 | 7884.07 | WA | Miralga Creek
GR6528 | Cat 16M | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 25244 | 2021-09-01 | 33341.1 | 2028-03-14 | 3902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N7580 | Hyd Cyl Wheel Lean | 24000 | 25244 | 2021-09-01 | 33341.1 | 2033-09-21 | 15902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N8040 | Circle & Drawbar | 12000 | 33193 | 2026-05-02 | 33341.1 | 2031-11-10 | 11851.9 | WA | Miralga Creek
GR6528 | Cat 16M | N8042 | Circle Bearing | 12000 | 25244 | 2021-09-01 | 33341.1 | 2028-03-14 | 3902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N8127-F | Axle Assembly FRONT | 12000 | 25244 | 2021-09-01 | 33341.1 | 2028-03-14 | 3902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N8128-03 | Spindle POS 3 | 24000 | 32957 | 2026-03-06 | 33341.1 | 2037-04-09 | 23615.9 | WA | Miralga Creek
GR6528 | Cat 16M | N8128-04 | Spindle POS 4 | 24000 | 26891.67 | 2022-09-14 | 33341.1 | 2034-06-25 | 17550.57 | WA | Miralga Creek
GR6528 | Cat 16M | N8128-05 | Spindle POS 5 | 24000 | 26891.67 | 2022-09-14 | 33341.1 | 2034-06-25 | 17550.57 | WA | Miralga Creek
GR6528 | Cat 16M | N8128-06 | Spindle POS 6 | 24000 | 26891.67 | 2022-09-14 | 33341.1 | 2034-06-25 | 17550.57 | WA | Miralga Creek
GR6528 | Cat 16M | N8300 | Artic Hitch | 36000 | 25244 | 2021-09-01 | 33341.1 | 2039-03-31 | 27902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N8995 | Operator Seat | 10000 | 25244 | 2021-09-01 | 33341.1 | 2027-04-13 | 1902.9 | WA | Miralga Creek
GR6528 | Cat 16M | N9500 | Air Cond'r-Serv |  |  | 2025-07-18 | 33341.1 | 2026-07-18 |  | WA | Miralga Creek
GR6655 | Cat 18M | N0050 | Blade Assembly | 36000 |  | 2025-01-08 | 4648.5 | 2038-08-19 | 31351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 4648.5 | 2030-01-07 |  | WA | McPhee Creek
GR6655 | Cat 18M | N1000 | Engine | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N1002 | Engine Valve Adj | 2500 | 2959.8 | 2025-12-14 | 4648.5 | 2026-09-21 | 811.3 | WA | McPhee Creek
GR6655 | Cat 18M | N1004 | Engine Midlife | 6000 |  | 2025-01-08 | 4648.5 | 2026-12-07 | 1351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N1310 | Radiator | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N2000 | Transmission | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N2004 | Transmission Pump | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N3210-L | Tandem Drive Chain LEFT | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N3210-R | Tandem Drive Chain RIGHT | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N3300 | Circle Drive Box | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N4000 | Bevel Gear | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N5000-L | Final Drive LEFT | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N5000-R | Final Drive RIGHT | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N6000-LF | Brake LEFT FRONT | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N6000-LR | Brake LEFT REAR | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N6000-RF | Brake RIGHT FRONT | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N6000-RR | Brake RIGHT REAR | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7029 | Pump Brake & Cooling Fan Eng | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7086 | Pump Implement & Steering | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7122 | Pump Emerg/Sup Steering | 16000 |  | 2025-01-08 | 4648.5 | 2030-10-31 | 11351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7230 | Hyd Motor Circle Drive | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7232 | Hyd Motor Engine Fan | 36000 |  | 2025-01-08 | 4648.5 | 2038-08-19 | 31351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7414-L | Hyd Cyl Artic LEFT | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7414-R | Hyd Cyl Artic RIGHT | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 1473 | 2025-05-09 | 4648.5 | 2028-04-14 | 4824.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7421 | Hyd Cyl Blade Tilt | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7440 | Hyd Cyl Centreshift | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7510 | Hyd Cyl Ripper Lift | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7540 | Hyd Cyl Sideshift | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7542-L | Hyd Cyl Steer LEFT | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7542-R | Hyd Cyl Steer RIGHT | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N7580 | Hyd Cyl Wheel Lean | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8040 | Circle & Drawbar | 24000 |  | 2025-01-08 | 4648.5 | 2033-12-14 | 19351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8042 | Circle Bearing | 24000 |  | 2025-01-08 | 4648.5 | 2033-12-14 | 19351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8127-F | Axle Assembly FRONT | 24000 |  | 2025-01-08 | 4648.5 | 2033-11-22 | 19351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8128-03 | Spindle POS 3 | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8128-04 | Spindle POS 4 | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8128-05 | Spindle POS 5 | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8128-06 | Spindle POS 6 | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8300 | Artic Hitch | 12000 |  | 2025-01-08 | 4648.5 | 2029-04-09 | 7351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N8995 | Operator Seat | 8000 |  | 2025-01-08 | 4648.5 | 2027-09-17 | 3351.5 | WA | McPhee Creek
GR6655 | Cat 18M | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 4648.5 | 2026-01-08 |  | WA | McPhee Creek
GR6656 | Cat 18M | N0050 | Blade Assembly | 36000 |  | 2024-05-21 | 10578.3 | 2036-04-26 | 25421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-05-21 | 10578.3 | 2029-05-20 |  | WA | McPhee Creek
GR6656 | Cat 18M | N1000 | Engine | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N1002 | Engine Valve Adj | 2500 | 7313.6 | 2025-03-01 | 10578.3 | 2026-02-08 | -764.7 | WA | McPhee Creek
GR6656 | Cat 18M | N1004 | Engine Midlife | 6000 | 7313.6 | 2025-03-01 | 10578.3 | 2027-06-22 | 2735.3 | WA | McPhee Creek
GR6656 | Cat 18M | N1310 | Radiator | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N2000 | Transmission | 12000 | 9395.4 | 2026-02-23 | 10578.3 | 2030-08-16 | 10817.1 | WA | McPhee Creek
GR6656 | Cat 18M | N2004 | Transmission Pump | 12000 | 9404 | 2026-02-23 | 10578.3 | 2030-08-17 | 10825.7 | WA | McPhee Creek
GR6656 | Cat 18M | N3210-L | Tandem Drive Chain LEFT | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N3210-R | Tandem Drive Chain RIGHT | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N3300 | Circle Drive Box | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N4000 | Bevel Gear | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N5000-L | Final Drive LEFT | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N5000-R | Final Drive RIGHT | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N6000-LF | Brake LEFT FRONT | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N6000-LR | Brake LEFT REAR | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N6000-RF | Brake RIGHT FRONT | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N6000-RR | Brake RIGHT REAR | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7029 | Pump Brake & Cooling Fan Eng | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7086 | Pump Implement & Steering | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7122 | Pump Emerg/Sup Steering | 16000 |  | 2024-05-21 | 10578.3 | 2028-07-08 | 5421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7230 | Hyd Motor Circle Drive | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7232 | Hyd Motor Engine Fan | 36000 |  | 2024-05-21 | 10578.3 | 2036-04-26 | 25421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7414-L | Hyd Cyl Artic LEFT | 8000 | 8985 | 2025-11-16 | 10578.3 | 2028-11-26 | 6406.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7414-R | Hyd Cyl Artic RIGHT | 8000 | 8606 | 2025-09-22 | 10578.3 | 2028-10-03 | 6027.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 | 8147.82 | 2025-07-04 | 10578.3 | 2028-07-29 | 5569.52 | WA | McPhee Creek
GR6656 | Cat 18M | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 | 8147.13 | 2025-07-04 | 10578.3 | 2028-07-29 | 5568.83 | WA | McPhee Creek
GR6656 | Cat 18M | N7421 | Hyd Cyl Blade Tilt | 8000 | 8147.13 | 2025-07-04 | 10578.3 | 2028-07-29 | 5568.83 | WA | McPhee Creek
GR6656 | Cat 18M | N7440 | Hyd Cyl Centreshift | 8000 | 8462 | 2025-08-30 | 10578.3 | 2028-09-12 | 5883.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7510 | Hyd Cyl Ripper Lift | 8000 | 8985 | 2025-11-17 | 10578.3 | 2028-11-26 | 6406.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7540 | Hyd Cyl Sideshift | 8000 | 9742 | 2026-03-24 | 10578.3 | 2029-03-13 | 7163.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7542-L | Hyd Cyl Steer LEFT | 8000 | 9742 | 2026-03-25 | 10578.3 | 2029-03-13 | 7163.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7542-R | Hyd Cyl Steer RIGHT | 8000 | 8506 | 2025-09-11 | 10578.3 | 2028-09-18 | 5927.7 | WA | McPhee Creek
GR6656 | Cat 18M | N7580 | Hyd Cyl Wheel Lean | 8000 | 8462 | 2025-08-30 | 10578.3 | 2028-09-12 | 5883.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8040 | Circle & Drawbar | 24000 |  | 2024-05-21 | 10578.3 | 2031-08-22 | 13421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8042 | Circle Bearing | 24000 |  | 2024-05-21 | 10578.3 | 2031-08-22 | 13421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8127-F | Axle Assembly FRONT | 24000 |  | 2024-05-21 | 10578.3 | 2031-08-22 | 13421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8128-03 | Spindle POS 3 | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8128-04 | Spindle POS 4 | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8128-05 | Spindle POS 5 | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8128-06 | Spindle POS 6 | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8300 | Artic Hitch | 12000 |  | 2024-05-21 | 10578.3 | 2026-12-17 | 1421.7 | WA | McPhee Creek
GR6656 | Cat 18M | N8995 | Operator Seat | 8000 | 8009.5 | 2025-06-22 | 10578.3 | 2028-07-10 | 5431.2 | WA | McPhee Creek
GR6656 | Cat 18M | N9500 | Air Cond'r-Serv |  |  | 2025-06-01 | 10578.3 | 2026-06-01 |  | WA | McPhee Creek
LO1965 | Cat 994H | N0066 | Fire Suppression Sys Cylinder |  | 28572 | 2025-04-20 | 34192 | 2030-04-19 |  | WA | Iron Bridge
LO1965 | Cat 994H | N0520 | Pre Lube Pump | 24000 | 19340 | 2022-05-20 | 34192 | 2028-06-28 | 9148 | WA | Iron Bridge
LO1965 | Cat 994H | N1000 | Engine | 24000 | 23607 | 2024-01-31 | 34192 | 2029-06-19 | 13415 | WA | Iron Bridge
LO1965 | Cat 994H | N1002 | Engine Valve Adj | 4000 | 33215 | 2026-03-15 | 34192 | 2027-02-04 | 3023 | WA | Iron Bridge
LO1965 | Cat 994H | N1002-01 | Engine Valve Adj - Initial | 250 | 24896 | 2024-07-25 | 34192 | 2024-05-04 | -9046 | WA | Iron Bridge
LO1965 | Cat 994H | N1004 | Engine Midlife | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1100-LF | Turbo Primary LFT FRONT | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1100-LR | Turbo Primary LFT REAR | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1100-RF | Turbo Primary RHT FRONT | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1100-RR | Turbo Primary RHT REAR | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1202 | Fuel Transfer Pump | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1210 | Fuel Injectors | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1300 | Cooling Sys Service | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1301 | Water Pump | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1302 | Aftercooler Pump | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1310 | Radiator | 24000 | 19499 | 2022-10-03 | 34192 | 2028-07-12 | 9307 | WA | Iron Bridge
LO1965 | Cat 994H | N1320 | Cooling Fan Engine | 24000 | 23612 | 2024-02-02 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N1400 | Belt Tensioner Assembly | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1420 | Air Compressor | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N1430 | Air Starter | 12000 | 19803 | 2022-11-09 | 34192 | 2025-11-10 | -2389 | WA | Iron Bridge
LO1965 | Cat 994H | N2000 | Transmission | 12000 | 23612 | 2024-01-29 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N2002-F | Oil Cooler -Transmission FRONT | 24000 | 23612 | 2024-02-01 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N2002-RE | Oil Cooler -Transmission REAR | 24000 | 23612 | 2024-02-02 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N2020 | Powertrain Pump | 12000 | 23612 | 2024-01-27 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N2050 | Torque Convertor | 12000 | 23612 | 2024-01-26 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N2090 | Drv Coupling | 24000 | 23612 | 2024-02-25 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N2100 | Transfer Case | 24000 | 30218 | 2025-08-18 | 34192 | 2030-12-22 | 20026 | WA | Iron Bridge
LO1965 | Cat 994H | N2440 | Drv Coupling PTO | 12000 | 23612 | 2024-01-26 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N3028 | Drive Shaft T/C - Trans | 24000 | 23612 | 2024-02-06 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N3029 | Uni's T/C - Trans | 12000 | 30218 | 2025-08-17 | 34192 | 2028-03-27 | 8026 | WA | Iron Bridge
LO1965 | Cat 994H | N3032 | Uni's Ctr Bearing - Bevel Gear | 12000 | 23612 | 2024-02-06 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N3037-RE | Drive Shft Trans - Bev Gear RE | 24000 | 30218 | 2025-08-08 | 34192 | 2030-12-22 | 20026 | WA | Iron Bridge
LO1965 | Cat 994H | N3038-RE | Uni's Trans - Bevel Gear REAR | 12000 | 30218 | 2025-08-08 | 34192 | 2028-03-27 | 8026 | WA | Iron Bridge
LO1965 | Cat 994H | N3042 | Driveline Ctr Bearing | 12000 | 23612 | 2024-01-29 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N3043 | Drv Shaft Trans-Ctr Bearing | 24000 | 31379 | 2025-11-07 | 34192 | 2031-03-29 | 21187 | WA | Iron Bridge
LO1965 | Cat 994H | N3044 | Drv Shaft C/Bearing-Bevel Gr | 24000 | 23863 | 2024-05-01 | 34192 | 2029-07-10 | 13671 | WA | Iron Bridge
LO1965 | Cat 994H | N3045-F | Drv Shft S/Bearing-Pump Drv FR | 24000 | 33215 | 2026-03-14 | 34192 | 2031-08-29 | 23023 | WA | Iron Bridge
LO1965 | Cat 994H | N3045-RE | Drv Shft S/Bearing-Pump Drv RE | 24000 | 23612 | 2024-01-29 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N3046-F | Uni's S/Bearing-Pmp Drv Box FR | 12000 | 23612 | 2024-02-06 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N3047 | Drv Shft S/Bearing Pump Drives | 12000 | 23612 | 2024-01-29 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N3052 | Uni's Trans- C/Bearing | 12000 | 31379 | 2025-11-07 | 34192 | 2028-07-02 | 9187 | WA | Iron Bridge
LO1965 | Cat 994H | N3320-01 | Pump Drive Box POS 1/FR | 12000 | 23612 | 2024-02-02 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N3320-02 | Pump Drive Box POS 2/RE | 12000 | 23612 | 2024-01-26 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N4000-F | Bevel Gear FRONT | 30000 | 33215 | 2026-03-15 | 34192 | 2033-01-10 | 29023 | WA | Iron Bridge
LO1965 | Cat 994H | N4000-RE | Bevel Gear REAR | 30000 | 33215 | 2026-03-13 | 34192 | 2033-01-10 | 29023 | WA | Iron Bridge
LO1965 | Cat 994H | N4102-01 | Axle Shaft - POS 1 | 30000 | 33215 | 2026-03-14 | 34192 | 2033-01-10 | 29023 | WA | Iron Bridge
LO1965 | Cat 994H | N4102-02 | Axle Shaft - POS 2 | 30000 | 33215 | 2026-03-14 | 34192 | 2033-01-10 | 29023 | WA | Iron Bridge
LO1965 | Cat 994H | N4102-03 | Axle Shaft - POS 3 | 30000 | 33215 | 2026-03-13 | 34192 | 2033-01-10 | 29023 | WA | Iron Bridge
LO1965 | Cat 994H | N4102-04 | Axle Shaft - POS 4 | 30000 | 33215 | 2026-03-13 | 34192 | 2033-01-10 | 29023 | WA | Iron Bridge
LO1965 | Cat 994H | N5000-01 | Final Drive POS 1 | 30000 | 21441 | 2023-06-05 | 34192 | 2030-05-04 | 17249 | WA | Iron Bridge
LO1965 | Cat 994H | N5000-02 | Final Drive POS 2 | 30000 | 33792 | 2026-04-25 | 34192 | 2033-02-27 | 29600 | WA | Iron Bridge
LO1965 | Cat 994H | N5000-03 | Final Drive POS 3 | 30000 | 21182 | 2023-04-27 | 34192 | 2030-04-13 | 16990 | WA | Iron Bridge
LO1965 | Cat 994H | N5000-04 | Final Drive POS 4 | 30000 | 25258 | 2024-08-21 | 34192 | 2031-03-19 | 21066 | WA | Iron Bridge
LO1965 | Cat 994H | N6020 | Park Brake | 12000 | 23863 | 2024-05-01 | 34192 | 2026-10-14 | 1671 | WA | Iron Bridge
LO1965 | Cat 994H | N6060-BC | Oil Cooler - Brake Cooling | 24000 | 23612 | 2024-01-30 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N6060-BS | Oil Cooler - Brakes & Steering | 24000 | 19340 | 2022-05-20 | 34192 | 2028-06-28 | 9148 | WA | Iron Bridge
LO1965 | Cat 994H | N7020 | Pump Brake | 12000 | 26611 | 2024-11-07 | 34192 | 2027-05-31 | 4419 | WA | Iron Bridge
LO1965 | Cat 994H | N7021 | Pump Brake Cooling | 12000 | 21855 | 2023-07-14 | 34192 | 2026-04-25 | -337 | WA | Iron Bridge
LO1965 | Cat 994H | N7071-00 | Pump Imp 1 | 12000 | 23612 | 2024-02-02 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N7072-00 | Pump Imp 2 | 12000 | 26808 | 2024-11-28 | 34192 | 2027-06-17 | 4616 | WA | Iron Bridge
LO1965 | Cat 994H | N7073-00 | Pump Imp 3 | 12000 | 29507 | 2025-06-21 | 34192 | 2028-01-28 | 7315 | WA | Iron Bridge
LO1965 | Cat 994H | N7087 | Pump Pilot | 12000 | 23612 | 2024-02-03 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N7120-L | Pump Steering LEFT | 12000 | 23612 | 2024-01-28 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N7120-R | Pump Steering RIGHT | 12000 | 23612 | 2024-01-28 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N7121 | Pump Steering/Braking | 12000 | 23612 | 2024-01-29 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N7122 | Pump Emerg/Sup Steering | 12000 | 23612 | 2024-01-28 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N7490-L | Hyd Cyl Lift LEFT | 12000 | 26981 | 2024-12-18 | 34192 | 2027-07-01 | 4789 | WA | Iron Bridge
LO1965 | Cat 994H | N7490-R | Hyd Cyl Lift RIGHT | 12000 | 26981 | 2024-12-18 | 34192 | 2027-07-01 | 4789 | WA | Iron Bridge
LO1965 | Cat 994H | N7542-L | Hyd Cyl Steer LEFT | 15000 | 32625 | 2026-02-01 | 34192 | 2029-06-20 | 13433 | WA | Iron Bridge
LO1965 | Cat 994H | N7542-R | Hyd Cyl Steer RIGHT | 15000 | 29086 | 2025-05-25 | 34192 | 2028-08-30 | 9894 | WA | Iron Bridge
LO1965 | Cat 994H | N7562-L | Hyd Cyl Tilt LEFT | 12000 | 29092 | 2025-05-26 | 34192 | 2027-12-24 | 6900 | WA | Iron Bridge
LO1965 | Cat 994H | N7562-R | Hyd Cyl Tilt RIGHT | 12000 | 19340 | 2022-05-20 | 34192 | 2025-09-28 | -2852 | WA | Iron Bridge
LO1965 | Cat 994H | N7600-L | Control Valve LEFT | 24000 |  |  | 34192 | 2026-04-15 | -10192 | WA | Iron Bridge
LO1965 | Cat 994H | N7600-R | Control Valve RIGHT | 24000 | 26802 | 2024-11-26 | 34192 | 2030-03-12 | 16610 | WA | Iron Bridge
LO1965 | Cat 994H | N7610 | Hyd Cooler Core | 24000 | 23612 | 2024-02-01 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N7647-F | Hyd Accum Brake Reseal FRONT | 12000 | 33215 | 2026-03-14 | 34192 | 2028-12-02 | 11023 | WA | Iron Bridge
LO1965 | Cat 994H | N7647-RE | Hyd Accum Brake Reseal REAR | 12000 | 33215 | 2026-03-14 | 34192 | 2028-12-02 | 11023 | WA | Iron Bridge
LO1965 | Cat 994H | N7655 | Hyd Accumulator Pilot | 24000 | 23612 | 2024-02-04 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N8300 | Artic Hitch | 22000 | 23227 | 2023-12-27 | 34192 | 2028-12-03 | 11035 | WA | Iron Bridge
LO1965 | Cat 994H | N8400 | Loader Frame Inspect | 24000 | 23612 | 2024-01-29 | 34192 | 2029-06-19 | 13420 | WA | Iron Bridge
LO1965 | Cat 994H | N8432 | Trunnion Axle Bearings REAR | 12000 | 23612 | 2024-01-28 | 34192 | 2026-09-23 | 1420 | WA | Iron Bridge
LO1965 | Cat 994H | N8995 | Operator Seat | 6000 | 28311 | 2025-04-02 | 34192 | 2026-06-02 | 119 | WA | Iron Bridge
LO1965 | Cat 994H | N9020-L | Alternator LEFT | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N9020-R | Alternator RIGHT | 12000 | 23607 | 2024-01-31 | 34192 | 2026-09-23 | 1415 | WA | Iron Bridge
LO1965 | Cat 994H | N9500 | Air Cond'r-Serv | 6000 | 31381 | 2025-11-07 | 34192 | 2027-02-18 | 3189 | WA | Iron Bridge
LO1965 | Cat 994H | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 17651 | 2021-08-12 | 34192 | 2028-02-09 | 7459 | WA | Iron Bridge
LO1965 | Cat 994H | N9501 | A/C Compressor | 12000 | 30296 | 2025-08-30 | 34192 | 2028-04-02 | 8104 | WA | Iron Bridge
LO2031 | Cat 972M Loader | N0066 | Fire Suppression Sys Cylinder |  | 4506 | 2025-12-08 | 5053 | 2030-12-07 |  | WA | Iron Bridge
LO2032 | Cat 930K Loader | N0066 | Fire Suppression Sys Cylinder |  | 5289 | 2025-12-06 | 5871 | 2030-12-05 |  | WA | Iron Bridge
LO2033 | Cat 982M Loader | N0066 | Fire Suppression Sys Cylinder |  | 6621 | 2025-06-27 | 9263 | 2030-06-26 |  | WA | Iron Bridge
LO2055 | Cat 962M | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-03-01 | 2074 | 2028-02-28 |  | WA | Iron Bridge
LO2055 | Cat 962M | N1002 | Engine Valve Adj | 1000 | 3237 | 2023-11-02 | 2074 | 2027-05-24 | 2163 | WA | Iron Bridge
LO2055 | Cat 962M | N8995 | Operator Seat | 6000 |  | 2023-07-01 | 2074 | 2028-03-12 | 3926 | WA | Iron Bridge
LO2055 | Cat 962M | N9500 | Air Cond'r-Serv | 5000 |  | 2023-07-01 | 2074 | 2027-09-28 | 2926 | WA | Iron Bridge
LO2089 | Cat 966M Wheel Loader | N0066 | Fire Suppression Sys Cylinder |  | 4387 | 2025-06-25 | 6543 | 2030-06-24 |  | WA | Iron Bridge
LO2089 | Cat 966M Wheel Loader | N8995 | Operator Seat | 6000 |  |  | 6543 | 2026-04-13 | -543 | WA | Iron Bridge
LO2089 | Cat 966M Wheel Loader | N9500 | Air Cond'r-Serv | 4000 |  |  | 6543 | 2025-10-28 | -2543 | WA | Iron Bridge
LO2121 | Cat 992K | N0020 | Bucket | 12000 | 22677 | 2025-03-29 | 33312 | 2026-09-29 | 1365 | WA | Yilgarn Hub
LO2121 | Cat 992K | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-04-15 | 33312 | 2027-04-14 |  | WA | Yilgarn Hub
LO2121 | Cat 992K | N1000 | Engine | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1002 | Engine Valve Adj | 3000 | 18565 | 2022-04-14 | 33312 | 2023-06-25 | -11747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1002-01 | Engine Valve Adj - Initial | 500 | 18565 | 2022-04-14 | 33312 | 2022-11-10 | -14247 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1100-L | Turbo Primary LEFT | 9000 | 28478 | 2025-03-02 | 33312 | 2027-06-11 | 4166 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1100-R | Turbo Primary RIGHT | 9000 | 28478 | 2025-03-02 | 33312 | 2027-06-11 | 4166 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1202 | Fuel Transfer Pump | 9000 | 28478 | 2026-03-02 | 33312 | 2027-06-11 | 4166 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1250 | Fuel Cooler | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1300 | Cooling Sys Service | 10000 | 28478 | 2025-03-02 | 33312 | 2027-09-10 | 5166 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1310 | Radiator | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1312-L | Aftercooler Core - LEFT | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1312-R | Aftercooler Core - RIGHT | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1400 | Belt Tensioner Assembly | 9000 | 18565 | 2022-04-14 | 33312 | 2024-12-22 | -5747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N1490 | Cam Shaft Inspection | 1500 | 18565 | 2022-04-14 | 33312 | 2023-02-09 | -13247 | WA | Yilgarn Hub
LO2121 | Cat 992K | N2000 | Transmission | 18000 | 18565 | 2022-04-15 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N2004 | Transmission Pump | 18000 | 16594 | 2021-08-31 | 33312 | 2026-09-22 | 1282 | WA | Yilgarn Hub
LO2121 | Cat 992K | N2050 | Torque Convertor | 18000 | 16983 | 2021-10-11 | 33312 | 2026-10-27 | 1671 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3028 | Drive Shaft T/C - Trans | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3029 | Uni's T/C - Trans | 9000 | 28479 | 2025-03-03 | 33312 | 2027-06-11 | 4167 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3032 | Uni's Ctr Bearing - Bevel Gear | 9000 | 28479 | 2025-03-03 | 33312 | 2027-06-11 | 4167 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3037-RE | Drive Shft Trans - Bev Gear RE | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3038-RE | Uni's Trans - Bevel Gear REAR | 9000 | 28479 | 2025-03-03 | 33312 | 2027-06-11 | 4167 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3042 | Driveline Ctr Bearing | 9000 | 28479 | 2025-03-03 | 33312 | 2027-06-11 | 4167 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3043 | Drv Shaft Trans-Ctr Bearing | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3044 | Drv Shaft C/Bearing-Bevel Gr | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3052 | Uni's Trans- C/Bearing | 9000 | 28479 | 2025-03-03 | 33312 | 2027-06-11 | 4167 | WA | Yilgarn Hub
LO2121 | Cat 992K | N3321 | Pump Drive | 18000 | 16983 | 2021-10-11 | 33312 | 2026-10-27 | 1671 | WA | Yilgarn Hub
LO2121 | Cat 992K | N4000-F | Bevel Gear FRONT | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N4000-RE | Bevel Gear REAR | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N4102-01 | Axle Shaft - POS 1 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N4102-02 | Axle Shaft - POS 2 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N4102-03 | Axle Shaft - POS 3 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N4102-04 | Axle Shaft - POS 4 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N5000-01 | Final Drive POS 1 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N5000-02 | Final Drive POS 2 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N5000-03 | Final Drive POS 3 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N5000-04 | Final Drive POS 4 | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N5015 | Oil Cooler AXLE | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N6020 | Park Brake | 18000 | 16594 | 2021-08-31 | 33312 | 2026-09-22 | 1282 | WA | Yilgarn Hub
LO2121 | Cat 992K | N6063 | Oil Cooler - Steering | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7020 | Pump Brake | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7041 | Pump Cooling Fan Engine | 12000 | 28478 | 2025-03-02 | 33312 | 2028-03-09 | 7166 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7070-C | Pump Implement CENTRE | 12000 | 31801 | 2026-01-18 | 33312 | 2029-01-06 | 10489 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7070-R | Pump Implement RIGHT | 12000 | 31801 | 2026-01-18 | 33312 | 2029-01-06 | 10489 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7106 | Pump Steering Pilot/Cooling | 12000 | 24150 | 2024-03-12 | 33312 | 2027-02-10 | 2838 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7120 | Pump Steering | 12000 | 31801 | 2026-01-18 | 33312 | 2029-01-06 | 10489 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7122 | Pump Emerg/Sup Steering | 12000 | 31801 | 2026-01-18 | 33312 | 2029-01-06 | 10489 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7164 | Pump & Motor Axle Cooler | 12000 | 24150 | 2024-03-12 | 33312 | 2027-02-10 | 2838 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7232 | Hyd Motor Engine Fan | 12000 | 18565 | 2022-04-15 | 33312 | 2025-09-24 | -2747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7490-L | Hyd Cyl Lift LEFT | 10000 | 28650 | 2025-03-18 | 33312 | 2027-09-25 | 5338 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7490-R | Hyd Cyl Lift RIGHT | 10000 | 28677 | 2025-03-30 | 33312 | 2027-09-28 | 5365 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7542-L | Hyd Cyl Steer LEFT | 12000 | 18565 | 2022-04-14 | 33312 | 2025-09-20 | -2747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 18565 | 2022-04-14 | 33312 | 2025-09-20 | -2747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7562 | Hyd Cyl Tilt | 10000 | 31837 | 2026-02-02 | 33312 | 2028-07-11 | 8525 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7600-S | Control Valve - STEERING | 12000 | 29614 | 2025-06-17 | 33312 | 2028-06-21 | 8302 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7603 | Control Valve Main Hydraulic | 12000 | 29614 | 2025-06-17 | 33312 | 2028-06-21 | 8302 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7610 | Hyd Cooler Core | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7647-L | Hyd Accum Brake Reseal LEFT | 12000 | 18565 | 2025-08-30 | 33312 | 2025-09-24 | -2747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7647-R | Hyd Accum Brake Reseal RIGHT | 12000 | 18565 | 2025-08-30 | 33312 | 2025-09-24 | -2747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7651-L | Hyd Accum Ride Control LEFT | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7651-R | Hyd Accum Ride Control RIGHT | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N7655 | Hyd Accumulator Pilot | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N8300 | Artic Hitch | 12000 | 18565 | 2022-04-14 | 33312 | 2025-09-20 | -2747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N8430-RE | Trunnion Axle REAR | 18000 | 18565 | 2022-04-14 | 33312 | 2027-03-20 | 3253 | WA | Yilgarn Hub
LO2121 | Cat 992K | N8995 | Operator Seat | 6000 | 28478 | 2025-03-02 | 33312 | 2026-09-11 | 1166 | WA | Yilgarn Hub
LO2121 | Cat 992K | N9020 | Alternator | 9000 | 31713 | 2025-12-11 | 33312 | 2028-03-31 | 7401 | WA | Yilgarn Hub
LO2121 | Cat 992K | N9050-L | Starter Motor LEFT | 9000 | 18565 | 2022-04-14 | 33312 | 2024-12-25 | -5747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N9050-R | Starter Motor RIGHT | 9000 | 18565 | 2022-04-14 | 33312 | 2024-12-25 | -5747 | WA | Yilgarn Hub
LO2121 | Cat 992K | N9500 | Air Cond'r-Serv | 6000 | 29988 | 2025-01-01 | 33312 | 2027-01-26 | 2676 | WA | Yilgarn Hub
LO2121 | Cat 992K | N9500-MA | Air Cond'r-Serv - MAJOR | 12000 | 29964 | 2025-01-01 | 33312 | 2028-07-23 | 8652 | WA | Yilgarn Hub
LO2121 | Cat 992K | N9501 | A/C Compressor | 9000 | 18565 | 2022-04-14 | 33312 | 2024-12-25 | -5747 | WA | Yilgarn Hub
LO2122 | Cat 992K | N0020 | Bucket | 12000 | 15288 | 2022-02-06 | 35041.1 | 2024-06-22 | -7753.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-07-15 | 35041.1 | 2028-07-13 |  | WA | Yilgarn Hub
LO2122 | Cat 992K | N1000 | Engine | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1002 | Engine Valve Adj | 3000 | 33891 | 2026-02-27 | 35041.1 | 2026-11-12 | 1849.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1002-01 | Engine Valve Adj - Initial | 500 | 19479 | 2023-02-24 | 35041.1 | 2022-08-28 | -15062.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1100-L | Turbo Primary LEFT | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1100-R | Turbo Primary RIGHT | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1202 | Fuel Transfer Pump | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1250 | Fuel Cooler | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1300 | Cooling Sys Service | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1310 | Radiator | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1312-L | Aftercooler Core - LEFT | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1312-R | Aftercooler Core - RIGHT | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1400 | Belt Tensioner Assembly | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N1490 | Cam Shaft Inspection | 1500 | 19479 | 2023-02-24 | 35041.1 | 2022-11-27 | -14062.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N2000 | Transmission | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N2004 | Transmission Pump | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N2050 | Torque Convertor | 18000 | 31713 | 2025-03-10 | 35041.1 | 2030-01-21 | 14671.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3028 | Drive Shaft T/C - Trans | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3029 | Uni's T/C - Trans | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3032 | Uni's Ctr Bearing - Bevel Gear | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3037-RE | Drive Shft Trans - Bev Gear RE | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3038-RE | Uni's Trans - Bevel Gear REAR | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3042 | Driveline Ctr Bearing | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3043 | Drv Shaft Trans-Ctr Bearing | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3044 | Drv Shaft C/Bearing-Bevel Gr | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3052 | Uni's Trans- C/Bearing | 9000 | 28400 | 2024-08-14 | 35041.1 | 2026-12-28 | 2358.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N3321 | Pump Drive | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N4000-F | Bevel Gear FRONT | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N4000-RE | Bevel Gear REAR | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N4102-01 | Axle Shaft - POS 1 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N4102-02 | Axle Shaft - POS 2 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N4102-03 | Axle Shaft - POS 3 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N4102-04 | Axle Shaft - POS 4 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N5000-01 | Final Drive POS 1 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N5000-02 | Final Drive POS 2 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N5000-03 | Final Drive POS 3 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N5000-04 | Final Drive POS 4 | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N5015 | Oil Cooler AXLE | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N6020 | Park Brake | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N6063 | Oil Cooler - Steering | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7020 | Pump Brake | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7041 | Pump Cooling Fan Engine | 12000 | 23376 | 2023-10-24 | 35041.1 | 2026-06-27 | 334.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7070-C | Pump Implement CENTRE | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7070-R | Pump Implement RIGHT | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7106 | Pump Steering Pilot/Cooling | 12000 | 27219 | 2024-06-02 | 35041.1 | 2027-06-12 | 4177.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7120 | Pump Steering | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7122 | Pump Emerg/Sup Steering | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7164 | Pump & Motor Axle Cooler | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7232 | Hyd Motor Engine Fan | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7490-L | Hyd Cyl Lift LEFT | 10000 | 31982 | 2025-03-27 | 35041.1 | 2028-02-18 | 6940.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7490-R | Hyd Cyl Lift RIGHT | 10000 | 27363 | 2024-06-10 | 35041.1 | 2026-12-25 | 2321.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7542-L | Hyd Cyl Steer LEFT | 12000 | 24638 | 2024-01-03 | 35041.1 | 2026-10-20 | 1596.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 23935 | 2024-01-04 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7562 | Hyd Cyl Tilt | 10000 | 33158 | 2025-06-09 | 35041.1 | 2028-06-04 | 8116.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7600-S | Control Valve - STEERING | 12000 | 23935 | 2023-11-23 | 35041.1 | 2026-08-17 | 893.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7603 | Control Valve Main Hydraulic | 12000 | 19479 | 2023-02-24 | 35041.1 | 2025-07-08 | -3562.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7610 | Hyd Cooler Core | 18000 | 19479 | 2023-02-24 | 35041.1 | 2027-01-05 | 2437.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7647-L | Hyd Accum Brake Reseal LEFT | 12000 | 31982 | 2025-03-27 | 35041.1 | 2028-08-18 | 8940.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7647-R | Hyd Accum Brake Reseal RIGHT | 12000 | 31982 | 2025-03-27 | 35041.1 | 2028-08-18 | 8940.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7651-L | Hyd Accum Ride Control LEFT | 18000 | 26267 | 2024-04-11 | 35041.1 | 2028-09-13 | 9225.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7651-R | Hyd Accum Ride Control RIGHT | 18000 | 26267 | 2024-04-11 | 35041.1 | 2028-09-13 | 9225.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N7655 | Hyd Accumulator Pilot | 18000 | 26267 | 2024-04-11 | 35041.1 | 2028-09-13 | 9225.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N8300 | Artic Hitch | 12000 | 19479 | 2023-02-24 | 35041.1 | 2025-07-08 | -3562.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N8430-RE | Trunnion Axle REAR | 18000 | 13479 | 2022-09-24 | 35041.1 | 2025-07-08 | -3562.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N8995 | Operator Seat | 6000 | 31982 | 2025-03-28 | 35041.1 | 2027-02-19 | 2940.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N9020 | Alternator | 9000 | 19479 | 2023-02-24 | 35041.1 | 2024-10-08 | -6562.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N9050-L | Starter Motor LEFT | 9000 | 19479 | 2023-02-24 | 35041.1 | 2024-10-08 | -6562.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N9050-R | Starter Motor RIGHT | 9000 | 19479 | 2023-02-24 | 35041.1 | 2024-10-08 | -6562.1 | WA | Yilgarn Hub
LO2122 | Cat 992K | N9500 | Air Cond'r-Serv | 6000 | 33275 | 2025-01-01 | 35041.1 | 2027-06-17 | 4233.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N9500-MA | Air Cond'r-Serv - MAJOR | 18000 | 33251 | 2025-01-01 | 35041.1 | 2030-06-10 | 16209.9 | WA | Yilgarn Hub
LO2122 | Cat 992K | N9501 | A/C Compressor | 9000 | 31477 | 2025-02-17 | 35041.1 | 2027-10-04 | 5435.9 | WA | Yilgarn Hub
LO2129 | Cat 992K | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-05-15 | 30374.9 | 2028-05-13 |  | WA | Yilgarn Hub
LO2129 | Cat 992K | N8995 | Operator Seat | 6000 |  | 2025-10-15 | 30374.9 | 2020-05-03 | -24374.9 | WA | Yilgarn Hub
LO2129 | Cat 992K | N9500 | Air Cond'r-Serv | 4000 |  | 2025-10-15 | 30374.9 | 2019-11-03 | -26374.9 | WA | Yilgarn Hub
LO2130 | Cat 992K | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-10-21 | 20270 | 2030-10-20 |  | WA | Yilgarn Hub
LO2130 | Cat 992K | N8995 | Operator Seat | 6000 |  | 2025-10-21 | 20270 | 2022-11-08 | -14270 | WA | Yilgarn Hub
LO2130 | Cat 992K | N9500 | Air Cond'r-Serv | 4000 |  | 2025-10-21 | 20270 | 2022-05-10 | -16270 | WA | Yilgarn Hub
LO6110 | Cat 993K | N0020 | Bucket | 10000 | 8850.1 | 2024-05-06 | 14154.15 | 2028-04-11 | 4695.95 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-10-17 | 14154.15 | 2027-10-16 |  | WA | Sanjiv Ridge
LO6110 | Cat 993K | N1000 | Engine | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N1002-01 | Engine Valve Adj - Initial | 500 | 423 | 2022-11-10 | 14154.15 | 2021-02-17 | -13231.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N1100-L | Turbo Primary LEFT | 9000 |  | 2022-10-17 | 14154.15 | 2024-05-08 | -5154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N1100-R | Turbo Primary RIGHT | 9000 |  | 2022-10-17 | 14154.15 | 2024-05-08 | -5154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N1310 | Radiator | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N1490 | Cam Shaft Inspection | 1500 | 12003.69 | 2025-09-05 | 14154.15 | 2026-02-22 | -650.46 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N2000 | Transmission | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N2002 | Oil Cooler - Transmission | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N2004 | Transmission Pump | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N2050 | Torque Convertor | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N3029 | Uni's T/C - Trans | 9000 | 10560.89 | 2025-01-26 | 14154.15 | 2028-07-23 | 5406.74 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N4000-F | Bevel Gear FRONT | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N4000-RE | Bevel Gear REAR | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5000-01 | Final Drive POS 1 | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5000-02 | Final Drive POS 2 | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5000-03 | Final Drive POS 3 | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5000-04 | Final Drive POS 4 | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5015-LF | Oil Cooler AXLE - LEFT FRONT | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5015-RE | Oil Cooler AXLE - REAR | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5015-RF | Oil Cooler AXLE - RIGHT FRONT | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5020-LF | Wheel Bearing LEFT FRONT | 10000 | 10874.17 | 2025-03-10 | 14154.15 | 2029-01-30 | 6720.02 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N5020-RF | Wheel Bearing RIGHT FRONT | 10000 | 10874.17 | 2025-03-10 | 14154.15 | 2029-01-30 | 6720.02 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N6020 | Park Brake | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N6063 | Oil Cooler - Steering | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7020 | Pump Brake | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7041 | Pump Cooling Fan Engine | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7070-L | Pump Implement LEFT | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7070-R | Pump Implement RIGHT | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7120 | Pump Steering | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7165 | Pump Axle Cooler | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7165-F | Pump Axle Cooler FRONT | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7165-RE | Pump Axle Cooler REAR | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7234 | Hyd Motor Cooler Fan | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7420-L | Hyd Cyl Blade Lift LEFT | 12000 |  | 2022-10-17 | 14154.15 | 2025-07-18 | -2154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7420-R | Hyd Cyl Blade Lift RIGHT | 12000 |  | 2022-10-17 | 14154.15 | 2025-07-18 | -2154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7421-L | Hyd Cyl Blade Tilt LEFT | 12000 |  | 2022-10-17 | 14154.15 | 2025-07-18 | -2154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7421-R | Hyd Cyl Blade Tilt RIGHT | 12000 |  | 2022-10-17 | 14154.15 | 2025-07-18 | -2154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7542-L | Hyd Cyl Steer LEFT | 16000 |  | 2022-10-17 | 14154.15 | 2027-02-21 | 1845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7542-R | Hyd Cyl Steer RIGHT | 16000 |  | 2022-10-17 | 14154.15 | 2027-02-21 | 1845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7610-L | Hyd Cooler Core LEFT | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7610-R | Hyd Cooler Core RIGHT | 18000 |  | 2022-10-17 | 14154.15 | 2027-12-09 | 3845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7651-L | Hyd Accum Ride Control LEFT | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7651-R | Hyd Accum Ride Control RIGHT | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7654-L | Hyd Accum Service Brake - LEFT | 30000 |  | 2022-10-17 | 14154.15 | 2032-09-20 | 15845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N7654-R | Hyd Accum Service Brake -RIGHT | 30000 | 12766 | 2025-12-05 | 14154.15 | 2037-10-22 | 28611.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N8000 | Main Frame/Chassis | 10000 |  | 2022-10-17 | 14154.15 | 2024-09-30 | -4154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N8300 | Artic Hitch | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N8410 | Bucket Pin Assembly | 20000 |  | 2022-10-17 | 14154.15 | 2028-09-25 | 5845.85 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N8432 | Trunnion Axle Bearings REAR | 10000 |  | 2022-10-17 | 14154.15 | 2024-09-30 | -4154.15 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N8995 | Operator Seat | 10000 | 10005.67 | 2024-12-07 | 14154.15 | 2028-09-26 | 5851.52 | WA | Sanjiv Ridge
LO6110 | Cat 993K | N9500 | Air Cond'r-Serv |  | 12981 | 2026-01-09 | 14154.15 | 2027-01-09 |  | WA | Sanjiv Ridge
LO6631 | Cat 972 | N1002 | Engine Valve Adj | 2500 |  | 2025-01-19 | 2188.6 | 2026-07-05 | 311.4 | WA | McPhee Creek
LO6631 | Cat 972 | N9500 | Air Cond'r-Serv |  |  | 2025-01-19 | 2188.6 | 2026-01-19 |  | WA | McPhee Creek
LO6670 | Cat 854K | N0050 | Blade Assembly | 20000 |  | 2025-01-08 | 2912.8 | 2031-08-15 | 17087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 2912.8 | 2030-01-07 |  | WA | McPhee Creek
LO6670 | Cat 854K | N1000 | Engine | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N1002 | Engine Valve Adj | 3000 |  |  | 2912.8 | 2026-06-07 | 87.2 | WA | McPhee Creek
LO6670 | Cat 854K | N1002-01 | Engine Valve Adj - Initial | 500 | 229.33 | 2025-06-05 | 2912.8 | 2025-09-27 | -2183.47 | WA | McPhee Creek
LO6670 | Cat 854K | N1004 | Engine Midlife | 7500 |  | 2025-01-08 | 2912.8 | 2027-10-21 | 4587.2 | WA | McPhee Creek
LO6670 | Cat 854K | N1310 | Radiator | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N1490 | Cam Shaft Inspection | 1500 |  | 2025-01-08 | 2912.8 | 2025-12-21 | -1412.8 | WA | McPhee Creek
LO6670 | Cat 854K | N2000 | Transmission | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N2004 | Transmission Pump | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N2050 | Torque Convertor | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-08 | 2912.8 | 2034-09-03 | 27087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N4000-F | Bevel Gear FRONT | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N4000-RE | Bevel Gear REAR | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N5015 | Oil Cooler AXLE | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N6020 | Park Brake | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N6063 | Oil Cooler - Steering | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7020 | Pump Brake | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7041 | Pump Cooling Fan Engine | 12000 |  | 2025-01-08 | 2912.8 | 2029-03-06 | 9087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7087 | Pump Pilot | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7120 | Pump Steering | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7122 | Pump Emerg/Sup Steering | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7155 | Hyd Pump Main | 12000 |  | 2025-01-08 | 2912.8 | 2029-03-06 | 9087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7165 | Pump Axle Cooler | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7232 | Hyd Motor Engine Fan | 12000 |  | 2025-01-08 | 2912.8 | 2029-03-06 | 9087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7420-L | Hyd Cyl Blade Lift LEFT | 8000 |  | 2025-01-08 | 2912.8 | 2027-12-16 | 5087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7420-R | Hyd Cyl Blade Lift RIGHT | 8000 |  | 2025-01-08 | 2912.8 | 2027-12-16 | 5087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7421-L | Hyd Cyl Blade Tilt LEFT | 8000 |  | 2025-01-08 | 2912.8 | 2027-12-16 | 5087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7421-R | Hyd Cyl Blade Tilt RIGHT | 8000 |  | 2025-01-08 | 2912.8 | 2027-12-16 | 5087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7542-L | Hyd Cyl Steer LEFT | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7542-R | Hyd Cyl Steer RIGHT | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N7610 | Hyd Cooler Core | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N8122-01 | Wheel Group POS 1 | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N8122-02 | Wheel Group POS 2 | 15000 |  | 2025-01-08 | 2912.8 | 2030-02-04 | 12087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N8300 | Artic Hitch | 14000 |  | 2025-01-08 | 2912.8 | 2029-10-15 | 11087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N8432 | Trunnion Axle Bearings REAR | 10000 |  | 2025-01-08 | 2912.8 | 2028-07-26 | 7087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 2912.8 | 2029-03-06 | 9087.2 | WA | McPhee Creek
LO6670 | Cat 854K | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 2912.8 | 2026-01-08 |  | WA | McPhee Creek
LW4073 | Cat 980H | N0066 | Fire Suppression Sys Cylinder |  | 19852 | 2025-04-15 | 21494.7 | 2030-04-14 |  | WA | Muchea
LW4073 | Cat 980H | N1000 | Engine | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N1002 | Engine Valve Adj | 2000 | 19915 | 2025-05-03 | 21494.7 | 2026-09-10 | 420.3 | WA | Muchea
LW4073 | Cat 980H | N1002-01 | Engine Valve Adj - Initial | 250 |  | 2012-09-12 | 21494.7 | 2011-11-12 | -21244.7 | WA | Muchea
LW4073 | Cat 980H | N1100 | Turbo Primary | 10000 | 18098 | 2024-03-16 | 21494.7 | 2030-12-04 | 6603.3 | WA | Muchea
LW4073 | Cat 980H | N1202 | Fuel Transfer Pump | 10000 | 18098 | 2024-03-16 | 21494.7 | 2030-12-04 | 6603.3 | WA | Muchea
LW4073 | Cat 980H | N1300 | Cooling Sys Service | 10000 | 15285 | 2020-05-12 | 21494.7 | 2028-12-31 | 3790.3 | WA | Muchea
LW4073 | Cat 980H | N1310 | Radiator | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N2000 | Transmission | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N2004 | Transmission Pump | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N2050 | Torque Convertor | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N3032-FR | Uni's C/Bear -Bevel Gear FRONT | 10000 | 15285 | 2020-05-12 | 21494.7 | 2028-12-31 | 3790.3 | WA | Muchea
LW4073 | Cat 980H | N3037-RE | Drive Shft Trans - Bev Gear RE | 20000 | 15285 | 2020-05-12 | 21494.7 | 2035-11-05 | 13790.3 | WA | Muchea
LW4073 | Cat 980H | N3038-RE | Uni's Trans - Bevel Gear REAR | 10000 | 15285 | 2020-05-12 | 21494.7 | 2028-12-31 | 3790.3 | WA | Muchea
LW4073 | Cat 980H | N3042 | Driveline Ctr Bearing | 10000 | 15285 | 2020-05-12 | 21494.7 | 2028-12-31 | 3790.3 | WA | Muchea
LW4073 | Cat 980H | N3043 | Drv Shaft Trans-Ctr Bearing | 20000 | 15285 | 2020-07-22 | 21494.7 | 2035-11-05 | 13790.3 | WA | Muchea
LW4073 | Cat 980H | N3044-FR | Drv Shaft C/Bear-Bev Gr FRONT | 20000 | 15285 | 2020-05-12 | 21494.7 | 2035-11-05 | 13790.3 | WA | Muchea
LW4073 | Cat 980H | N3052 | Uni's Trans- C/Bearing | 10000 | 15285 | 2020-05-12 | 21494.7 | 2028-12-31 | 3790.3 | WA | Muchea
LW4073 | Cat 980H | N4000-F | Bevel Gear FRONT | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N4000-RE | Bevel Gear REAR | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N5000-01 | Final Drive POS 1 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N5000-02 | Final Drive POS 2 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N5000-03 | Final Drive POS 3 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N5000-04 | Final Drive POS 4 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N6000-01 | Brake POS 1 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N6000-02 | Brake POS 2 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N6000-03 | Brake POS 3 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N6000-04 | Brake POS 4 | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N6020 | Park Brake | 20000 | 20692 | 2025-09-14 | 21494.7 | 2039-07-18 | 19197.3 | WA | Muchea
LW4073 | Cat 980H | N6021 | Park Brake Adjust | 5000 | 20692 | 2025-09-14 | 21494.7 | 2029-04-11 | 4197.3 | WA | Muchea
LW4073 | Cat 980H | N7023 | Pump Brake & Pilot | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7041 | Pump Cooling Fan Engine | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7070 | Pump Implement | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7120 | Pump Steering | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7122 | Pump Emerg/Sup Steering | 20000 | 19057 | 2024-11-01 | 21494.7 | 2038-06-05 | 17562.3 | WA | Muchea
LW4073 | Cat 980H | N7233 | Motor Cool Fan Eng | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7490-L | Hyd Cyl Lift LEFT | 20000 | 21048 | 2025-11-18 | 21494.7 | 2039-10-15 | 19553.3 | WA | Muchea
LW4073 | Cat 980H | N7490-R | Hyd Cyl Lift RIGHT | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7542-L | Hyd Cyl Steer LEFT | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7542-R | Hyd Cyl Steer RIGHT | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7562-L | Hyd Cyl Tilt LEFT | 20000 | 1111 | 2015-08-07 | 21494.7 | 2026-02-21 | -383.7 | WA | Muchea
LW4073 | Cat 980H | N7562-R | Hyd Cyl Tilt RIGHT | 20000 | 1111 | 2015-08-07 | 21494.7 | 2026-02-21 | -383.7 | WA | Muchea
LW4073 | Cat 980H | N7605 | Steering Hmu | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N7647-L | Hyd Accum Brake Reseal LEFT | 20000 | 18235 | 2024-04-03 | 21494.7 | 2037-11-11 | 16740.3 | WA | Muchea
LW4073 | Cat 980H | N7647-R | Hyd Accum Brake Reseal RIGHT | 20000 | 18235 | 2024-04-03 | 21494.7 | 2037-11-11 | 16740.3 | WA | Muchea
LW4073 | Cat 980H | N7652 | Hyd Accum Ride Ctrl Reseal | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N8300 | Artic Hitch | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N8400 | Loader Frame Inspect | 20000 | 15285 | 2020-05-12 | 21494.7 | 2035-11-05 | 13790.3 | WA | Muchea
LW4073 | Cat 980H | N8430-RE | Trunnion Axle REAR | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N8432 | Trunnion Axle Bearings REAR | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N8995 | Operator Seat | 6000 | 15776 | 2021-01-26 | 21494.7 | 2026-08-06 | 281.3 | WA | Muchea
LW4073 | Cat 980H | N9020 | Alternator | 20000 |  | 2012-09-12 | 21494.7 | 2025-05-19 | -1494.7 | WA | Muchea
LW4073 | Cat 980H | N9050 | Starter Motor | 10000 | 18098 | 2024-03-16 | 21494.7 | 2030-12-04 | 6603.3 | WA | Muchea
LW4073 | Cat 980H | N9500 | Air Cond'r-Serv | 5000 | 15285 | 2020-05-12 | 21494.7 | 2025-07-30 | -1209.7 | WA | Muchea
LW4073 | Cat 980H | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 15285 | 2020-05-12 | 21494.7 | 2035-11-05 | 13790.3 | WA | Muchea
LW4073 | Cat 980H | N9501 | A/C Compressor | 10000 | 17910 | 2024-02-11 | 21494.7 | 2030-10-18 | 6415.3 | WA | Muchea
RD1740 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 31730 | 2018-04-09 | 54615 | 2023-04-08 |  | WA | Karlawinda
RD1740 | Cat 789C | N0200 | A Frame Bearing | 20000 | 53773 | 2023-07-05 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 53773 | 2023-07-05 | 54615 | 2026-08-13 | 1158 | WA | Karlawinda
RD1740 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N1000 | Engine | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 53775 | 2023-09-19 | 54615 | 2026-12-25 | 3160 | WA | Karlawinda
RD1740 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 41547 | 2020-04-12 | 54615 | 2024-01-11 | -13018 | WA | Karlawinda
RD1740 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 51419 | 2021-11-26 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 51419 | 2021-11-26 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 48352 | 2021-06-18 | 54615 | 2027-02-01 | 3737 | WA | Karlawinda
RD1740 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 48352 | 2021-06-18 | 54615 | 2027-02-01 | 3737 | WA | Karlawinda
RD1740 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 51419 | 2021-11-28 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 51419 | 2021-11-28 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N1310 | Radiator | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 53773 | 2023-05-25 | 54615 | 2028-01-29 | 9158 | WA | Karlawinda
RD1740 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 53773 | 2023-05-25 | 54615 | 2028-01-29 | 9158 | WA | Karlawinda
RD1740 | Cat 789C | N1430 | Air Starter | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N2000 | Transmission | 20000 | 53773 | 2023-07-06 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 53773 | 2023-05-12 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N2004 | Transmission Pump | 20000 | 53773 | 2023-07-06 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N2050 | Torque Convertor | 20000 | 38267 | 2019-09-14 | 54615 | 2027-01-26 | 3652 | WA | Karlawinda
RD1740 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 41547 | 2020-04-29 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 51419 | 2021-11-29 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 53773 | 2023-07-05 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 51419 | 2021-11-29 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N3320 | Pump Drive Box | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N4000 | Bevel Gear | 20000 | 47826 | 2021-05-17 | 54615 | 2028-10-25 | 13211 | WA | Karlawinda
RD1740 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 47826 | 2021-05-17 | 54615 | 2028-10-25 | 13211 | WA | Karlawinda
RD1740 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 47826 | 2021-05-17 | 54615 | 2028-10-25 | 13211 | WA | Karlawinda
RD1740 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 53773 | 2023-07-14 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 46198 | 2021-02-21 | 54615 | 2028-07-08 | 11583 | WA | Karlawinda
RD1740 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 53773 | 2023-05-03 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 50921 | 2021-10-28 | 54615 | 2029-05-19 | 16306 | WA | Karlawinda
RD1740 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 53773 | 2023-05-03 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 50921 | 2021-10-28 | 54615 | 2029-05-19 | 16306 | WA | Karlawinda
RD1740 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 51419 | 2021-11-27 | 54615 | 2029-06-21 | 16804 | WA | Karlawinda
RD1740 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 51419 | 2021-11-28 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 47826 | 2021-05-16 | 54615 | 2026-12-28 | 3211 | WA | Karlawinda
RD1740 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 51419 | 2021-11-28 | 54615 | 2027-08-25 | 6804 | WA | Karlawinda
RD1740 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 38267 | 2019-09-14 | 54615 | 2027-01-26 | 3652 | WA | Karlawinda
RD1740 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 50921 | 2021-10-27 | 54615 | 2028-08-25 | 12306 | WA | Karlawinda
RD1740 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 31089 | 2018-04-09 | 54615 | 2029-05-30 | 16474 | WA | Karlawinda
RD1740 | Cat 789C | N7120 | Pump Steering | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 53785 | 2024-04-11 | 54615 | 2030-08-20 | 23170 | WA | Karlawinda
RD1740 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 35569 | 2018-08-24 | 54615 | 2027-04-23 | 4954 | WA | Karlawinda
RD1740 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 51428 | 2021-12-28 | 54615 | 2029-06-22 | 16813 | WA | Karlawinda
RD1740 | Cat 789C | N7605 | Steering Hmu | 20000 | 51419 | 2021-11-28 | 54615 | 2029-06-21 | 16804 | WA | Karlawinda
RD1740 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 55209 | 2026-02-10 | 54615 | 2030-03-01 | 20594 | WA | Karlawinda
RD1740 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 55209 | 2026-02-10 | 54615 | 2030-03-01 | 20594 | WA | Karlawinda
RD1740 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 54615 | 2020-12-31 | -29615 | WA | Karlawinda
RD1740 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 53773 | 2023-05-03 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 50921 | 2021-10-28 | 54615 | 2029-05-19 | 16306 | WA | Karlawinda
RD1740 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 51493 | 2021-12-08 | 54615 | 2029-06-26 | 16878 | WA | Karlawinda
RD1740 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 51493 | 2021-12-08 | 54615 | 2029-06-26 | 16878 | WA | Karlawinda
RD1740 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 51493 | 2021-12-08 | 54615 | 2029-06-26 | 16878 | WA | Karlawinda
RD1740 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N8140 | Steering Y Piece | 20000 | 47826 | 2021-05-16 | 54615 | 2028-10-25 | 13211 | WA | Karlawinda
RD1740 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 41547 | 2020-04-12 | 54615 | 2027-09-02 | 6932 | WA | Karlawinda
RD1740 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 34640 | 2019-01-20 | 54615 | 2028-03-26 | 10025 | WA | Karlawinda
RD1740 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 37748 | 2019-08-09 | 54615 | 2028-10-20 | 13133 | WA | Karlawinda
RD1740 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 47826 | 2021-05-18 | 54615 | 2027-11-26 | 8211 | WA | Karlawinda
RD1740 | Cat 789C | N8501 | Ball Stud Crack Test |  | 35276 | 2019-03-09 | 54615 | 2019-09-07 |  | WA | Karlawinda
RD1740 | Cat 789C | N8995 | Operator Seat | 6000 | 53773 | 2023-10-17 | 54615 | 2027-05-07 | 5158 | WA | Karlawinda
RD1740 | Cat 789C | N8999 | Cab Upgrade | 60000 | 53785 | 2023-02-14 | 54615 | 2037-03-16 | 59170 | WA | Karlawinda
RD1740 | Cat 789C | N9020 | Alternator | 10000 | 53773 | 2023-05-18 | 54615 | 2028-01-29 | 9158 | WA | Karlawinda
RD1740 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 53773 | 2023-06-29 | 54615 | 2027-03-01 | 4158 | WA | Karlawinda
RD1740 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 53773 | 2023-06-29 | 54615 | 2029-11-25 | 19158 | WA | Karlawinda
RD1740 | Cat 789C | N9501 | A/C Compressor | 10000 | 53773 | 2023-05-31 | 54615 | 2028-01-29 | 9158 | WA | Karlawinda
RD1740 | Cat 789C | N9998 | Extended Life Rebuild | 45000 |  | 2006-09-25 | 54615 | 2024-08-25 | -9615 | WA | Karlawinda
RD1740 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2006-09-25 | 54615 | 2028-04-19 | 10385 | WA | Karlawinda
RD1740 | Cat 789C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2006-09-25 | 54615 | 2031-12-14 | 30385 | WA | Karlawinda
RD2028 | Cat 793D | N0066 | Fire Suppression Sys Cylinder |  | 61972 | 2022-06-23 | 86119 | 2027-06-22 |  | WA | Iron Bridge
RD2028 | Cat 793D | N0200 | A Frame Bearing | 20000 | 84439 | 2026-02-04 | 86119 | 2029-02-11 | 18320 | WA | Iron Bridge
RD2028 | Cat 793D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 84439 | 2026-02-04 | 86119 | 2026-05-18 | 320 | WA | Iron Bridge
RD2028 | Cat 793D | N0520 | Pre Lube Pump | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N1000 | Engine | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N1002 | Engine Valve Adj | 4000 | 83491 | 2025-11-24 | 86119 | 2026-07-17 | 1372 | WA | Iron Bridge
RD2028 | Cat 793D | N1002-01 | Engine Valve Adj - Initial | 50 | 18649 | 2025-12-18 | 86119 | 2016-06-05 | -67420 | WA | Iron Bridge
RD2028 | Cat 793D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N1100-LR | Turbo Primary LFT REAR | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N1100-RR | Turbo Primary RHT REAR | 10000 | 84418 | 2026-01-28 | 86119 | 2027-08-20 | 8299 | WA | Iron Bridge
RD2028 | Cat 793D | N1202 | Fuel Transfer Pump | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N1300 | Cooling Sys Service | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N1310 | Radiator | 20000 | 83491 | 2025-11-20 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N1400 | Belt Tensioner Assembly | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N1420 | Air Compressor | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N2000 | Transmission | 20000 | 83491 | 2025-11-22 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N2050 | Torque Convertor | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N2052 | Convertor/Trans Pump | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N3021 | Uni's Eng - Pump Drive | 5000 | 81169 | 2025-07-19 | 86119 | 2026-05-31 | 50 | WA | Iron Bridge
RD2028 | Cat 793D | N3028 | Drive Shaft T/C - Trans | 20000 | 83491 | 2025-11-23 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N3029 | Uni's T/C - Trans | 10000 | 83491 | 2025-11-23 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N3320 | Pump Drive Box | 20000 | 83491 | 2025-11-23 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N4000 | Bevel Gear | 20000 | 83491 | 2025-11-22 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N4102-03 | Axle Shaft - POS 3 | 20000 | 83491 | 2025-11-26 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N4102-04 | Axle Shaft - POS 4 | 20000 | 83491 | 2025-11-27 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N5003-03 | Final Drive Ext Life POS 3 | 20000 | 83491 | 2025-11-26 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N5003-04 | Final Drive Ext Life POS 4 | 20000 | 83491 | 2025-11-27 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N5020-01 | Wheel Bearing POS 1 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N5020-02 | Wheel Bearing POS 2 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N6000-01 | Brake POS 1 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N6000-02 | Brake POS 2 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N6030-F | Brake Slack Adj FRONT | 24000 | 70713 | 2023-12-02 | 86119 | 2027-09-05 | 8594 | WA | Iron Bridge
RD2028 | Cat 793D | N6030-RE | Brake Slack Adj REAR | 20000 | 83491 | 2025-11-21 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N6061 | Oil Cooler Front Brakes | 24000 | 83491 | 2025-11-22 | 86119 | 2029-07-26 | 21372 | WA | Iron Bridge
RD2028 | Cat 793D | N6062-F | Oil Cooler Rear Brakes FRONT | 20000 | 84439 | 2026-02-04 | 86119 | 2029-02-11 | 18320 | WA | Iron Bridge
RD2028 | Cat 793D | N6062-RE | Oil Cooler Rear Brakes REAR | 20000 | 83491 | 2025-11-23 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N6200-01 | Press Convertor POS 1 | 12000 | 73613 | 2024-06-20 | 86119 | 2026-04-06 | -506 | WA | Iron Bridge
RD2028 | Cat 793D | N6200-02 | Press Convertor POS 2 | 12000 | 73613 | 2024-06-20 | 86119 | 2026-04-06 | -506 | WA | Iron Bridge
RD2028 | Cat 793D | N6200-03 | Press Convertor POS 3 | 10000 | 78086 | 2025-02-08 | 86119 | 2026-08-14 | 1967 | WA | Iron Bridge
RD2028 | Cat 793D | N6200-04 | Press Convertor POS 4 | 10000 | 71290 | 2024-01-13 | 86119 | 2026-03-18 | -4829 | WA | Iron Bridge
RD2028 | Cat 793D | N7021 | Pump Brake Cooling | 40000 | 61972 | 2022-07-17 | 86119 | 2028-10-01 | 15853 | WA | Iron Bridge
RD2028 | Cat 793D | N7024 | Hyd Motor Brake Cooling | 20000 | 75069 | 2024-08-29 | 86119 | 2027-09-03 | 8950 | WA | Iron Bridge
RD2028 | Cat 793D | N7027 | Pump Hoist/Brake Rel/Oil Cool | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7041 | Pump Cooling Fan Engine | 20000 | 83491 | 2025-11-24 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7088 | Pump Park Brk Rel | 40000 | 61972 | 2022-07-17 | 86119 | 2028-10-01 | 15853 | WA | Iron Bridge
RD2028 | Cat 793D | N7120 | Pump Steering | 20000 | 83491 | 2025-11-23 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7160 | Pump Axle Lube/Cooler | 20000 | 83491 | 2025-11-22 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 83491 | 2025-11-22 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7232 | Hyd Motor Engine Fan | 20000 | 83491 | 2025-11-20 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 61972 | 2022-07-17 | 86119 | 2027-04-09 | 5853 | WA | Iron Bridge
RD2028 | Cat 793D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 83491 | 2025-12-02 | 86119 | 2030-06-16 | 27372 | WA | Iron Bridge
RD2028 | Cat 793D | N7541 | Hyd Cyl Access Ladder | 20000 | 61972 | 2022-07-17 | 86119 | 2025-10-16 | -4147 | WA | Iron Bridge
RD2028 | Cat 793D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 65722 | 2023-02-28 | 86119 | 2026-04-12 | -397 | WA | Iron Bridge
RD2028 | Cat 793D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 83491 | 2025-11-23 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7605 | Steering Hmu | 20000 | 71520 | 2024-01-27 | 82579 | 2027-01-17 | 8941 | WA | Iron Bridge
RD2028 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 20000 | 83491 | 2025-11-22 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7647 | Hyd Accum Brake Reseal | 20000 | 83491 | 2025-11-30 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7657-C | Hyd Accum Steering CENTER | 20000 | 83491 | 2025-11-25 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N7657-F | Hyd Accum Steering FRONT | 20000 | 72807 | 2024-05-09 | 86119 | 2027-05-25 | 6688 | WA | Iron Bridge
RD2028 | Cat 793D | N7657-RE | Hyd Accum Steering REAR | 20000 | 83491 | 2025-11-25 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N8000 | Main Frame/Chassis | 30000 | 61972 | 2022-07-17 | 86119 | 2027-04-09 | 5853 | WA | Iron Bridge
RD2028 | Cat 793D | N8122-01 | Wheel Group POS 1 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N8122-02 | Wheel Group POS 2 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 80020 | 2025-05-20 | 86119 | 2028-06-17 | 13901 | WA | Iron Bridge
RD2028 | Cat 793D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 80020 | 2025-05-20 | 86119 | 2028-06-17 | 13901 | WA | Iron Bridge
RD2028 | Cat 793D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 80020 | 2025-05-20 | 86119 | 2028-06-17 | 13901 | WA | Iron Bridge
RD2028 | Cat 793D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 80020 | 2025-05-20 | 86119 | 2028-06-17 | 13901 | WA | Iron Bridge
RD2028 | Cat 793D | N8137-L | Steering Linkage Group LEFT | 20000 | 80020 | 2025-05-20 | 86119 | 2028-06-17 | 13901 | WA | Iron Bridge
RD2028 | Cat 793D | N8137-R | Steering Linkage Group RIGHT | 20000 | 80020 | 2025-05-20 | 86119 | 2028-06-17 | 13901 | WA | Iron Bridge
RD2028 | Cat 793D | N8140 | Steering Y Piece | 20000 | 84439 | 2026-01-31 | 86119 | 2029-02-11 | 18320 | WA | Iron Bridge
RD2028 | Cat 793D | N8200-01 | Ride Strut POS 1 | 24000 | 61972 | 2022-07-17 | 86119 | 2026-04-25 | -147 | WA | Iron Bridge
RD2028 | Cat 793D | N8200-02 | Ride Strut POS 2 | 24000 | 80568 | 2025-06-21 | 86119 | 2029-02-18 | 18449 | WA | Iron Bridge
RD2028 | Cat 793D | N8200-03 | Ride Strut POS 3 | 30000 | 61972 | 2022-07-17 | 86119 | 2027-04-09 | 5853 | WA | Iron Bridge
RD2028 | Cat 793D | N8200-04 | Ride Strut POS 4 | 30000 | 61972 | 2022-07-17 | 86119 | 2027-04-09 | 5853 | WA | Iron Bridge
RD2028 | Cat 793D | N8441 | Rear Axle Dog Bone | 15000 | 83491 | 2025-11-30 | 86119 | 2028-03-27 | 12372 | WA | Iron Bridge
RD2028 | Cat 793D | N8501 | Ball Stud Crack Test |  | 84417 | 2026-01-25 | 86119 | 2026-07-26 |  | WA | Iron Bridge
RD2028 | Cat 793D | N8995 | Operator Seat | 6000 | 83491 | 2025-11-27 | 86119 | 2026-11-26 | 3372 | WA | Iron Bridge
RD2028 | Cat 793D | N8999 | Cab Upgrade | 60000 | 61972 | 2022-07-17 | 86119 | 2031-09-17 | 35853 | WA | Iron Bridge
RD2028 | Cat 793D | N9020 | Alternator | 10000 | 83491 | 2025-11-24 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N9050-LW | Starter Motor LOWER | 10000 | 85982 | 2026-04-24 | 86119 | 2027-11-12 | 9863 | WA | Iron Bridge
RD2028 | Cat 793D | N9050-UP | Starter Motor UPPER | 10000 | 85982 | 2026-04-24 | 86119 | 2027-11-12 | 9863 | WA | Iron Bridge
RD2028 | Cat 793D | N9500 | Air Cond'r-Serv | 5000 | 83491 | 2025-12-04 | 86119 | 2026-10-03 | 2372 | WA | Iron Bridge
RD2028 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 83491 | 2025-12-04 | 86119 | 2028-12-22 | 17372 | WA | Iron Bridge
RD2028 | Cat 793D | N9501 | A/C Compressor | 10000 | 83491 | 2025-11-09 | 86119 | 2027-06-30 | 7372 | WA | Iron Bridge
RD2028 | Cat 793D | N9998 | Extended Life Rebuild | 45000 | 61972 | 2022-07-17 | 86119 | 2029-06-28 | 20853 | WA | Iron Bridge
RD2028 | Cat 793D | N9998-01 | Extended Life Rebuild ONE | 65000 | 61972 | 2022-07-17 | 86119 | 2032-06-13 | 40853 | WA | Iron Bridge
RD2028 | Cat 793D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-08-15 | 86119 | 2026-03-29 | -1119 | WA | Iron Bridge
RD2029 | Cat 793D | N0066 | Fire Suppression Sys Cylinder |  | 57865 | 2022-06-24 | 81805 | 2027-06-23 |  | WA | Iron Bridge
RD2029 | Cat 793D | N0200 | A Frame Bearing | 20000 | 80385 | 2026-02-19 | 81805 | 2029-02-25 | 18580 | WA | Iron Bridge
RD2029 | Cat 793D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 80385 | 2026-02-19 | 81805 | 2026-06-28 | 580 | WA | Iron Bridge
RD2029 | Cat 793D | N0520 | Pre Lube Pump | 20000 | 69126 | 2024-04-29 | 81805 | 2027-06-28 | 7321 | WA | Iron Bridge
RD2029 | Cat 793D | N1000 | Engine | 20000 | 77883 | 2025-10-02 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N1002 | Engine Valve Adj | 4000 | 77883 | 2025-10-02 | 81805 | 2026-06-01 | 78 | WA | Iron Bridge
RD2029 | Cat 793D | N1002-01 | Engine Valve Adj - Initial | 50 | 77914 | 2025-10-14 | 81805 | 2025-11-01 | -3841 | WA | Iron Bridge
RD2029 | Cat 793D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1100-LR | Turbo Primary LFT REAR | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1100-RR | Turbo Primary RHT REAR | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1202 | Fuel Transfer Pump | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1300 | Cooling Sys Service | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1310 | Radiator | 20000 | 77883 | 2025-10-05 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N1400 | Belt Tensioner Assembly | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N1420 | Air Compressor | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N2000 | Transmission | 20000 | 71053 | 2024-08-27 | 81805 | 2027-10-10 | 9248 | WA | Iron Bridge
RD2029 | Cat 793D | N2050 | Torque Convertor | 20000 | 77883 | 2025-10-02 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N2052 | Convertor/Trans Pump | 20000 | 77883 | 2025-10-02 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 77883 | 2025-10-10 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N3021 | Uni's Eng - Pump Drive | 5000 | 76420 | 2025-07-07 | 81805 | 2026-05-07 | -385 | WA | Iron Bridge
RD2029 | Cat 793D | N3028 | Drive Shaft T/C - Trans | 20000 | 77883 | 2025-10-06 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N3029 | Uni's T/C - Trans | 10000 | 77883 | 2025-10-06 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N3320 | Pump Drive Box | 20000 | 77883 | 2025-10-06 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N4000 | Bevel Gear | 20000 | 77883 | 2025-10-07 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N4102-03 | Axle Shaft - POS 3 | 20000 | 80925 | 2026-03-17 | 81805 | 2029-03-27 | 19120 | WA | Iron Bridge
RD2029 | Cat 793D | N4102-04 | Axle Shaft - POS 4 | 20000 | 77883 | 2025-10-10 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N5003-03 | Final Drive Ext Life POS 3 | 20000 | 57863 | 2022-07-17 | 81805 | 2025-10-27 | -3942 | WA | Iron Bridge
RD2029 | Cat 793D | N5003-04 | Final Drive Ext Life POS 4 | 20000 | 77882 | 2025-10-12 | 81805 | 2028-10-13 | 16077 | WA | Iron Bridge
RD2029 | Cat 793D | N5020-01 | Wheel Bearing POS 1 | 24000 | 57863 | 2022-07-17 | 81805 | 2026-05-31 | 58 | WA | Iron Bridge
RD2029 | Cat 793D | N5020-02 | Wheel Bearing POS 2 | 24000 | 80385 | 2026-02-18 | 81805 | 2029-09-30 | 22580 | WA | Iron Bridge
RD2029 | Cat 793D | N6000-01 | Brake POS 1 | 24000 | 57863 | 2022-07-17 | 81805 | 2026-05-31 | 58 | WA | Iron Bridge
RD2029 | Cat 793D | N6000-02 | Brake POS 2 | 24000 | 80385 | 2026-02-18 | 81805 | 2029-09-30 | 22580 | WA | Iron Bridge
RD2029 | Cat 793D | N6030-F | Brake Slack Adj FRONT | 24000 | 71038 | 2024-08-13 | 81805 | 2028-05-12 | 13233 | WA | Iron Bridge
RD2029 | Cat 793D | N6030-RE | Brake Slack Adj REAR | 20000 | 72619 | 2024-11-16 | 81805 | 2028-01-03 | 10814 | WA | Iron Bridge
RD2029 | Cat 793D | N6061 | Oil Cooler Front Brakes | 24000 | 77883 | 2025-10-01 | 81805 | 2029-05-17 | 20078 | WA | Iron Bridge
RD2029 | Cat 793D | N6062-F | Oil Cooler Rear Brakes FRONT | 20000 | 77883 | 2025-09-29 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N6062-RE | Oil Cooler Rear Brakes REAR | 20000 | 77883 | 2025-09-29 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N6200-01 | Press Convertor POS 1 | 12000 | 70513 | 2024-07-14 | 81805 | 2026-07-05 | 708 | WA | Iron Bridge
RD2029 | Cat 793D | N6200-02 | Press Convertor POS 2 | 12000 | 70513 | 2024-07-14 | 81805 | 2026-07-05 | 708 | WA | Iron Bridge
RD2029 | Cat 793D | N6200-03 | Press Convertor POS 3 | 10000 | 70513 | 2024-07-14 | 81805 | 2026-03-19 | -1292 | WA | Iron Bridge
RD2029 | Cat 793D | N6200-04 | Press Convertor POS 4 | 10000 | 77882 | 2025-10-11 | 81805 | 2027-04-21 | 6077 | WA | Iron Bridge
RD2029 | Cat 793D | N7021 | Pump Brake Cooling | 40000 | 57863 | 2022-07-17 | 81805 | 2028-10-12 | 16058 | WA | Iron Bridge
RD2029 | Cat 793D | N7024 | Hyd Motor Brake Cooling | 20000 | 77883 | 2025-10-11 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7027 | Pump Hoist/Brake Rel/Oil Cool | 20000 | 77883 | 2025-09-30 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7041 | Pump Cooling Fan Engine | 20000 | 77883 | 2025-10-05 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7088 | Pump Park Brk Rel | 40000 | 57863 | 2022-07-17 | 81805 | 2028-10-12 | 16058 | WA | Iron Bridge
RD2029 | Cat 793D | N7120 | Pump Steering | 20000 | 77883 | 2025-10-04 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7160 | Pump Axle Lube/Cooler | 20000 | 77883 | 2025-10-06 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 77883 | 2025-10-04 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7232 | Hyd Motor Engine Fan | 20000 | 77890 | 2025-10-12 | 81805 | 2028-10-13 | 16085 | WA | Iron Bridge
RD2029 | Cat 793D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 57863 | 2022-07-17 | 81805 | 2027-04-20 | 6058 | WA | Iron Bridge
RD2029 | Cat 793D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 57863 | 2022-07-17 | 81805 | 2027-04-20 | 6058 | WA | Iron Bridge
RD2029 | Cat 793D | N7541 | Hyd Cyl Access Ladder | 20000 | 57863 | 2022-07-17 | 81805 | 2025-10-27 | -3942 | WA | Iron Bridge
RD2029 | Cat 793D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 76260 | 2025-06-29 | 81805 | 2028-07-17 | 14455 | WA | Iron Bridge
RD2029 | Cat 793D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 65397 | 2023-09-14 | 81805 | 2026-12-08 | 3592 | WA | Iron Bridge
RD2029 | Cat 793D | N7605 | Steering Hmu | 20000 | 71050 | 2024-08-19 | 81805 | 2027-10-10 | 9245 | WA | Iron Bridge
RD2029 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 20000 | 77883 | 2025-10-04 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7647 | Hyd Accum Brake Reseal | 20000 | 77883 | 2025-10-08 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N7657-C | Hyd Accum Steering CENTER | 20000 | 80385 | 2026-02-18 | 81805 | 2029-02-25 | 18580 | WA | Iron Bridge
RD2029 | Cat 793D | N7657-F | Hyd Accum Steering FRONT | 20000 | 80385 | 2026-02-18 | 81805 | 2029-02-25 | 18580 | WA | Iron Bridge
RD2029 | Cat 793D | N7657-RE | Hyd Accum Steering REAR | 20000 | 80835 | 2026-02-18 | 81805 | 2029-03-22 | 19030 | WA | Iron Bridge
RD2029 | Cat 793D | N8000 | Main Frame/Chassis | 30000 | 57863 | 2022-07-17 | 81805 | 2027-04-20 | 6058 | WA | Iron Bridge
RD2029 | Cat 793D | N8122-01 | Wheel Group POS 1 | 24000 | 57863 | 2022-07-17 | 81805 | 2026-05-31 | 58 | WA | Iron Bridge
RD2029 | Cat 793D | N8122-02 | Wheel Group POS 2 | 24000 | 80385 | 2026-02-18 | 81805 | 2029-09-30 | 22580 | WA | Iron Bridge
RD2029 | Cat 793D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8137-L | Steering Linkage Group LEFT | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8137-R | Steering Linkage Group RIGHT | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8140 | Steering Y Piece | 20000 | 78198 | 2025-10-28 | 81805 | 2028-10-30 | 16393 | WA | Iron Bridge
RD2029 | Cat 793D | N8200-01 | Ride Strut POS 1 | 24000 | 57863 | 2022-07-17 | 81805 | 2026-05-31 | 58 | WA | Iron Bridge
RD2029 | Cat 793D | N8200-02 | Ride Strut POS 2 | 24000 | 80385 | 2026-02-19 | 81805 | 2029-09-30 | 22580 | WA | Iron Bridge
RD2029 | Cat 793D | N8200-03 | Ride Strut POS 3 | 30000 | 57863 | 2022-07-17 | 81805 | 2027-04-20 | 6058 | WA | Iron Bridge
RD2029 | Cat 793D | N8200-04 | Ride Strut POS 4 | 30000 | 57863 | 2022-07-17 | 81805 | 2027-04-20 | 6058 | WA | Iron Bridge
RD2029 | Cat 793D | N8441 | Rear Axle Dog Bone | 15000 | 80385 | 2026-02-16 | 81805 | 2028-05-31 | 13580 | WA | Iron Bridge
RD2029 | Cat 793D | N8501 | Ball Stud Crack Test |  | 80003 | 2026-01-25 | 81805 | 2026-07-26 |  | WA | Iron Bridge
RD2029 | Cat 793D | N8995 | Operator Seat | 6000 | 77883 | 2025-10-08 | 81805 | 2026-09-17 | 2078 | WA | Iron Bridge
RD2029 | Cat 793D | N8999 | Cab Upgrade | 60000 | 57863 | 2022-07-17 | 81805 | 2031-09-28 | 36058 | WA | Iron Bridge
RD2029 | Cat 793D | N9020 | Alternator | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N9050-LW | Starter Motor LOWER | 10000 | 77882 | 2025-10-08 | 81805 | 2027-03-31 | 6077 | WA | Iron Bridge
RD2029 | Cat 793D | N9050-UP | Starter Motor UPPER | 10000 | 77882 | 2025-10-08 | 81805 | 2027-03-31 | 6077 | WA | Iron Bridge
RD2029 | Cat 793D | N9500 | Air Cond'r-Serv | 5000 | 77883 | 2025-10-10 | 81805 | 2026-07-25 | 1078 | WA | Iron Bridge
RD2029 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 77883 | 2025-10-10 | 81805 | 2028-10-13 | 16078 | WA | Iron Bridge
RD2029 | Cat 793D | N9501 | A/C Compressor | 10000 | 77883 | 2025-10-02 | 81805 | 2027-04-22 | 6078 | WA | Iron Bridge
RD2029 | Cat 793D | N9998 | Extended Life Rebuild | 45000 | 57863 | 2022-07-17 | 81805 | 2029-07-09 | 21058 | WA | Iron Bridge
RD2029 | Cat 793D | N9998-01 | Extended Life Rebuild ONE | 65000 | 57863 | 2022-07-17 | 81805 | 2032-06-24 | 41058 | WA | Iron Bridge
RD2029 | Cat 793D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-08-29 | 81805 | 2026-11-17 | 3195 | WA | Iron Bridge
RD2030 | Cat 793D | N0066 | Fire Suppression Sys Cylinder |  | 61592 | 2022-09-28 | 82501 | 2027-09-27 |  | WA | Iron Bridge
RD2030 | Cat 793D | N0200 | A Frame Bearing | 20000 | 76449 | 2025-05-09 | 82501 | 2028-06-20 | 13948 | WA | Iron Bridge
RD2030 | Cat 793D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 79278 | 2025-10-02 | 82501 | 2026-03-23 | -1223 | WA | Iron Bridge
RD2030 | Cat 793D | N0520 | Pre Lube Pump | 20000 | 76449 | 2025-05-10 | 82501 | 2028-06-20 | 13948 | WA | Iron Bridge
RD2030 | Cat 793D | N1000 | Engine | 20000 | 62061 | 2022-10-01 | 82501 | 2026-04-24 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N1002 | Engine Valve Adj | 4000 | 76449 | 2025-05-09 | 82501 | 2026-01-29 | -2052 | WA | Iron Bridge
RD2030 | Cat 793D | N1002-01 | Engine Valve Adj - Initial | 50 | 62061 | 2022-10-01 | 82501 | 2023-06-09 | -20390 | WA | Iron Bridge
RD2030 | Cat 793D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 73121 | 2024-10-30 | 82501 | 2026-06-19 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N1100-LR | Turbo Primary LFT REAR | 10000 | 73121 | 2024-10-30 | 82501 | 2026-06-19 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 73121 | 2024-10-30 | 82501 | 2026-06-19 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N1100-RR | Turbo Primary RHT REAR | 10000 | 72462 | 2024-09-28 | 82501 | 2026-05-15 | -39 | WA | Iron Bridge
RD2030 | Cat 793D | N1202 | Fuel Transfer Pump | 10000 | 73121 | 2024-10-31 | 82501 | 2026-06-19 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N1300 | Cooling Sys Service | 10000 | 73111 | 2024-11-02 | 82501 | 2026-06-19 | 610 | WA | Iron Bridge
RD2030 | Cat 793D | N1310 | Radiator | 20000 | 67229 | 2023-12-08 | 82501 | 2027-02-02 | 4728 | WA | Iron Bridge
RD2030 | Cat 793D | N1400 | Belt Tensioner Assembly | 10000 | 73121 | 2024-10-30 | 82501 | 2026-06-19 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N1420 | Air Compressor | 10000 | 77738 | 2025-07-12 | 82501 | 2027-02-17 | 5237 | WA | Iron Bridge
RD2030 | Cat 793D | N2000 | Transmission | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N2050 | Torque Convertor | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N2052 | Convertor/Trans Pump | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 61407 | 2021-04-26 | 82501 | 2026-04-01 | -1094 | WA | Iron Bridge
RD2030 | Cat 793D | N3021 | Uni's Eng - Pump Drive | 5000 | 78251 | 2025-08-09 | 82501 | 2026-07-07 | 750 | WA | Iron Bridge
RD2030 | Cat 793D | N3028 | Drive Shaft T/C - Trans | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N3029 | Uni's T/C - Trans | 10000 | 77876 | 2025-07-22 | 82501 | 2027-03-08 | 5375 | WA | Iron Bridge
RD2030 | Cat 793D | N3320 | Pump Drive Box | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N4000 | Bevel Gear | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N4102-03 | Axle Shaft - POS 3 | 20000 | 67998 | 2024-01-21 | 82501 | 2027-03-21 | 5497 | WA | Iron Bridge
RD2030 | Cat 793D | N4102-04 | Axle Shaft - POS 4 | 20000 | 67998 | 2024-01-21 | 82501 | 2027-03-21 | 5497 | WA | Iron Bridge
RD2030 | Cat 793D | N5003-03 | Final Drive Ext Life POS 3 | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N5003-04 | Final Drive Ext Life POS 4 | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N5020-01 | Wheel Bearing POS 1 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N5020-02 | Wheel Bearing POS 2 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N6000-01 | Brake POS 1 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N6000-02 | Brake POS 2 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N6030-F | Brake Slack Adj FRONT | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N6030-RE | Brake Slack Adj REAR | 20000 | 76030 | 2025-04-10 | 82501 | 2028-05-28 | 13529 | WA | Iron Bridge
RD2030 | Cat 793D | N6061 | Oil Cooler Front Brakes | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N6062-F | Oil Cooler Rear Brakes FRONT | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N6062-RE | Oil Cooler Rear Brakes REAR | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N6200-01 | Press Convertor POS 1 | 12000 | 75138 | 2025-02-23 | 82501 | 2027-02-03 | 4637 | WA | Iron Bridge
RD2030 | Cat 793D | N6200-02 | Press Convertor POS 2 | 12000 | 75138 | 2025-02-23 | 82501 | 2027-02-03 | 4637 | WA | Iron Bridge
RD2030 | Cat 793D | N6200-03 | Press Convertor POS 3 | 10000 | 73121 | 2024-10-30 | 82501 | 2026-07-01 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N6200-04 | Press Convertor POS 4 | 10000 | 73121 | 2024-10-30 | 82501 | 2026-07-01 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N7021 | Pump Brake Cooling | 40000 | 62061 | 2022-10-01 | 82501 | 2029-04-19 | 19560 | WA | Iron Bridge
RD2030 | Cat 793D | N7024 | Hyd Motor Brake Cooling | 20000 | 74699 | 2025-01-23 | 82501 | 2028-03-17 | 12198 | WA | Iron Bridge
RD2030 | Cat 793D | N7027 | Pump Hoist/Brake Rel/Oil Cool | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7041 | Pump Cooling Fan Engine | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7088 | Pump Park Brk Rel | 40000 | 62061 | 2022-10-01 | 82501 | 2029-04-19 | 19560 | WA | Iron Bridge
RD2030 | Cat 793D | N7120 | Pump Steering | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7160 | Pump Axle Lube/Cooler | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7232 | Hyd Motor Engine Fan | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 62061 | 2022-10-01 | 82501 | 2027-10-27 | 9560 | WA | Iron Bridge
RD2030 | Cat 793D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 62061 | 2022-10-01 | 82501 | 2027-10-27 | 9560 | WA | Iron Bridge
RD2030 | Cat 793D | N7541 | Hyd Cyl Access Ladder | 20000 |  | 2013-12-17 | 82501 | 2017-02-26 | -62501 | WA | Iron Bridge
RD2030 | Cat 793D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 64160 | 2023-06-30 | 82501 | 2026-08-26 | 1659 | WA | Iron Bridge
RD2030 | Cat 793D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 63499 | 2023-02-20 | 82501 | 2026-07-21 | 998 | WA | Iron Bridge
RD2030 | Cat 793D | N7605 | Steering Hmu | 20000 | 79439 | 2025-12-11 | 82501 | 2028-11-29 | 16938 | WA | Iron Bridge
RD2030 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7647 | Hyd Accum Brake Reseal | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N7657-C | Hyd Accum Steering CENTER | 20000 | 21806 | 2026-04-22 | 82501 | 2020-05-19 | -40695 | WA | Iron Bridge
RD2030 | Cat 793D | N7657-F | Hyd Accum Steering FRONT | 20000 | 81806 | 2026-04-22 | 82501 | 2029-04-06 | 19305 | WA | Iron Bridge
RD2030 | Cat 793D | N7657-RE | Hyd Accum Steering REAR | 20000 | 81806 | 2026-04-22 | 82501 | 2029-04-06 | 19305 | WA | Iron Bridge
RD2030 | Cat 793D | N8000 | Main Frame/Chassis | 30000 | 62061 | 2022-10-01 | 82501 | 2027-10-27 | 9560 | WA | Iron Bridge
RD2030 | Cat 793D | N8122-01 | Wheel Group POS 1 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N8122-02 | Wheel Group POS 2 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8137-L | Steering Linkage Group LEFT | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8137-R | Steering Linkage Group RIGHT | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8140 | Steering Y Piece | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-04 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N8200-01 | Ride Strut POS 1 | 24000 | 62061 | 2022-10-01 | 82501 | 2026-12-06 | 3560 | WA | Iron Bridge
RD2030 | Cat 793D | N8200-02 | Ride Strut POS 2 | 24000 | 71610 | 2024-08-17 | 82501 | 2028-05-06 | 13109 | WA | Iron Bridge
RD2030 | Cat 793D | N8200-03 | Ride Strut POS 3 | 30000 | 79441 | 2025-12-12 | 82501 | 2030-05-23 | 26940 | WA | Iron Bridge
RD2030 | Cat 793D | N8200-04 | Ride Strut POS 4 | 30000 | 62061 | 2022-10-01 | 82501 | 2027-10-27 | 9560 | WA | Iron Bridge
RD2030 | Cat 793D | N8441 | Rear Axle Dog Bone | 15000 | 82275 | 2026-05-16 | 82501 | 2028-08-04 | 14774 | WA | Iron Bridge
RD2030 | Cat 793D | N8501 | Ball Stud Crack Test |  | 80126 | 2026-01-25 | 82501 | 2026-07-26 |  | WA | Iron Bridge
RD2030 | Cat 793D | N8995 | Operator Seat | 6000 | 75138 | 2025-02-23 | 82501 | 2026-03-15 | -1363 | WA | Iron Bridge
RD2030 | Cat 793D | N8999 | Cab Upgrade | 60000 | 62061 | 2022-10-01 | 82501 | 2032-04-04 | 39560 | WA | Iron Bridge
RD2030 | Cat 793D | N9020 | Alternator | 10000 | 73121 | 2024-10-29 | 82501 | 2026-06-30 | 620 | WA | Iron Bridge
RD2030 | Cat 793D | N9050-LW | Starter Motor LOWER | 10000 | 77739 | 2025-07-13 | 82501 | 2027-02-28 | 5238 | WA | Iron Bridge
RD2030 | Cat 793D | N9050-UP | Starter Motor UPPER | 10000 | 77739 | 2025-07-13 | 82501 | 2027-02-28 | 5238 | WA | Iron Bridge
RD2030 | Cat 793D | N9500 | Air Cond'r-Serv | 5000 | 78251 | 2025-08-09 | 82501 | 2026-07-07 | 750 | WA | Iron Bridge
RD2030 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 62061 | 2022-10-01 | 82501 | 2026-05-06 | -440 | WA | Iron Bridge
RD2030 | Cat 793D | N9501 | A/C Compressor | 10000 | 77141 | 2025-06-10 | 82501 | 2027-01-28 | 4640 | WA | Iron Bridge
RD2030 | Cat 793D | N9998 | Extended Life Rebuild | 45000 | 45000 | 2008-09-16 | 82501 | 2027-07-07 | 7499 | WA | Iron Bridge
RD2030 | Cat 793D | N9998-01 | Extended Life Rebuild ONE | 65000 | 62061 | 2022-10-01 | 82501 | 2032-12-31 | 44560 | WA | Iron Bridge
RD2030 | Cat 793D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-09-16 | 82501 | 2026-10-10 | 2499 | WA | Iron Bridge
RD2031 | Cat 793D | N0066 | Fire Suppression Sys Cylinder |  | 61041 | 2022-12-23 | 79726 | 2027-12-22 |  | WA | Iron Bridge
RD2031 | Cat 793D | N0200 | A Frame Bearing | 20000 | 73401 | 2025-05-05 | 79726 | 2028-06-05 | 13675 | WA | Iron Bridge
RD2031 | Cat 793D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 75688 | 2025-09-01 | 79726 | 2026-02-01 | -2038 | WA | Iron Bridge
RD2031 | Cat 793D | N0520 | Pre Lube Pump | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N1000 | Engine | 20000 | 79475 | 2026-05-12 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N1002 | Engine Valve Adj | 4000 | 79475 | 2026-05-12 | 79726 | 2026-12-17 | 3749 | WA | Iron Bridge
RD2031 | Cat 793D | N1002-01 | Engine Valve Adj - Initial | 50 | 59555 | 2022-08-22 | 79726 | 2023-06-06 | -20121 | WA | Iron Bridge
RD2031 | Cat 793D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1100-LR | Turbo Primary LFT REAR | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1100-RR | Turbo Primary RHT REAR | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1202 | Fuel Transfer Pump | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1300 | Cooling Sys Service | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1310 | Radiator | 20000 | 79475 | 2026-05-08 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N1400 | Belt Tensioner Assembly | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N1420 | Air Compressor | 10000 | 79475 | 2026-05-12 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N2000 | Transmission | 20000 | 65873 | 2024-03-14 | 79726 | 2027-04-25 | 6147 | WA | Iron Bridge
RD2031 | Cat 793D | N2050 | Torque Convertor | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N2052 | Convertor/Trans Pump | 20000 | 69117 | 2024-09-25 | 79726 | 2027-10-18 | 9391 | WA | Iron Bridge
RD2031 | Cat 793D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 79475 | 2026-05-11 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N3021 | Uni's Eng - Pump Drive | 5000 | 79475 | 2026-05-11 | 79726 | 2027-02-09 | 4749 | WA | Iron Bridge
RD2031 | Cat 793D | N3028 | Drive Shaft T/C - Trans | 20000 | 79475 | 2026-05-11 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N3029 | Uni's T/C - Trans | 10000 | 79475 | 2026-05-11 | 79726 | 2027-11-06 | 9749 | WA | Iron Bridge
RD2031 | Cat 793D | N3320 | Pump Drive Box | 20000 | 65281 | 2023-09-15 | 79726 | 2027-03-24 | 5555 | WA | Iron Bridge
RD2031 | Cat 793D | N4000 | Bevel Gear | 20000 | 79475 | 2026-05-11 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N4102-03 | Axle Shaft - POS 3 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-19 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N4102-04 | Axle Shaft - POS 4 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-19 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N5003-03 | Final Drive Ext Life POS 3 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N5003-04 | Final Drive Ext Life POS 4 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N5020-01 | Wheel Bearing POS 1 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N5020-02 | Wheel Bearing POS 2 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N6000-01 | Brake POS 1 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N6000-02 | Brake POS 2 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N6030-F | Brake Slack Adj FRONT | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N6030-RE | Brake Slack Adj REAR | 20000 | 71276 | 2025-02-28 | 79726 | 2028-02-11 | 11550 | WA | Iron Bridge
RD2031 | Cat 793D | N6061 | Oil Cooler Front Brakes | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N6062-F | Oil Cooler Rear Brakes FRONT | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-25 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N6062-RE | Oil Cooler Rear Brakes REAR | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-25 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N6200-01 | Press Convertor POS 1 | 12000 | 73063 | 2025-04-13 | 79726 | 2027-03-12 | 5337 | WA | Iron Bridge
RD2031 | Cat 793D | N6200-02 | Press Convertor POS 2 | 12000 | 73063 | 2025-04-13 | 79726 | 2027-03-12 | 5337 | WA | Iron Bridge
RD2031 | Cat 793D | N6200-03 | Press Convertor POS 3 | 10000 | 73063 | 2025-04-14 | 79726 | 2026-11-24 | 3337 | WA | Iron Bridge
RD2031 | Cat 793D | N6200-04 | Press Convertor POS 4 | 10000 | 73063 | 2025-04-14 | 79726 | 2026-11-24 | 3337 | WA | Iron Bridge
RD2031 | Cat 793D | N7021 | Pump Brake Cooling | 40000 | 58553 | 2022-07-17 | 79726 | 2029-03-11 | 18827 | WA | Iron Bridge
RD2031 | Cat 793D | N7024 | Hyd Motor Brake Cooling | 20000 | 71509 | 2025-01-19 | 79726 | 2028-02-24 | 11783 | WA | Iron Bridge
RD2031 | Cat 793D | N7027 | Pump Hoist/Brake Rel/Oil Cool | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N7041 | Pump Cooling Fan Engine | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N7088 | Pump Park Brk Rel | 40000 | 58553 | 2022-07-17 | 79726 | 2029-03-11 | 18827 | WA | Iron Bridge
RD2031 | Cat 793D | N7120 | Pump Steering | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N7160 | Pump Axle Lube/Cooler | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 79475 | 2026-05-10 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N7232 | Hyd Motor Engine Fan | 20000 | 78383 | 2026-03-14 | 79726 | 2029-03-01 | 18657 | WA | Iron Bridge
RD2031 | Cat 793D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 58553 | 2022-07-17 | 79726 | 2027-09-17 | 8827 | WA | Iron Bridge
RD2031 | Cat 793D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 58553 | 2022-07-17 | 79726 | 2027-09-17 | 8827 | WA | Iron Bridge
RD2031 | Cat 793D | N7541 | Hyd Cyl Access Ladder | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 78383 | 2025-09-29 | 79726 | 2029-03-01 | 18657 | WA | Iron Bridge
RD2031 | Cat 793D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 74144 | 2025-06-14 | 79726 | 2028-07-15 | 14418 | WA | Iron Bridge
RD2031 | Cat 793D | N7605 | Steering Hmu | 20000 | 76925 | 2025-12-21 | 79726 | 2028-12-13 | 17199 | WA | Iron Bridge
RD2031 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 20000 | 79475 | 2026-05-12 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N7647 | Hyd Accum Brake Reseal | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N7657-C | Hyd Accum Steering CENTER | 20000 | 77824 | 2026-02-15 | 79726 | 2028-09-15 | 15552 | WA | Iron Bridge
RD2031 | Cat 793D | N7657-F | Hyd Accum Steering FRONT | 20000 | 77824 | 2026-02-15 | 79726 | 2028-09-15 | 15552 | WA | Iron Bridge
RD2031 | Cat 793D | N7657-RE | Hyd Accum Steering REAR | 20000 | 77824 | 2026-02-15 | 79726 | 2028-09-15 | 15552 | WA | Iron Bridge
RD2031 | Cat 793D | N8000 | Main Frame/Chassis | 30000 | 58553 | 2022-07-17 | 79726 | 2027-09-17 | 8827 | WA | Iron Bridge
RD2031 | Cat 793D | N8122-01 | Wheel Group POS 1 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N8122-02 | Wheel Group POS 2 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 69117 | 2024-09-24 | 79726 | 2027-10-18 | 9391 | WA | Iron Bridge
RD2031 | Cat 793D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N8137-L | Steering Linkage Group LEFT | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N8137-R | Steering Linkage Group RIGHT | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N8140 | Steering Y Piece | 20000 | 58553 | 2022-07-17 | 79726 | 2026-03-26 | -1173 | WA | Iron Bridge
RD2031 | Cat 793D | N8200-01 | Ride Strut POS 1 | 24000 | 65252 | 2023-08-30 | 79726 | 2027-10-25 | 9526 | WA | Iron Bridge
RD2031 | Cat 793D | N8200-02 | Ride Strut POS 2 | 24000 | 58553 | 2022-07-17 | 79726 | 2026-10-28 | 2827 | WA | Iron Bridge
RD2031 | Cat 793D | N8200-03 | Ride Strut POS 3 | 30000 | 58553 | 2022-07-17 | 79726 | 2027-09-17 | 8827 | WA | Iron Bridge
RD2031 | Cat 793D | N8200-04 | Ride Strut POS 4 | 30000 | 68223 | 2024-08-12 | 79726 | 2029-02-21 | 18497 | WA | Iron Bridge
RD2031 | Cat 793D | N8441 | Rear Axle Dog Bone | 15000 | 74633 | 2025-07-10 | 79726 | 2027-11-15 | 9907 | WA | Iron Bridge
RD2031 | Cat 793D | N8501 | Ball Stud Crack Test |  | 77411 | 2026-01-26 | 79726 | 2026-07-27 |  | WA | Iron Bridge
RD2031 | Cat 793D | N8995 | Operator Seat | 6000 | 76243 | 2025-09-29 | 79726 | 2026-10-11 | 2517 | WA | Iron Bridge
RD2031 | Cat 793D | N8999 | Cab Upgrade | 60000 | 58553 | 2022-07-17 | 79726 | 2032-02-25 | 38827 | WA | Iron Bridge
RD2031 | Cat 793D | N9020 | Alternator | 10000 | 75860 | 2025-09-10 | 79726 | 2027-04-25 | 6134 | WA | Iron Bridge
RD2031 | Cat 793D | N9050-LW | Starter Motor LOWER | 10000 | 74636 | 2025-07-10 | 79726 | 2027-02-17 | 4910 | WA | Iron Bridge
RD2031 | Cat 793D | N9050-UP | Starter Motor UPPER | 10000 | 74636 | 2025-07-10 | 79726 | 2027-02-17 | 4910 | WA | Iron Bridge
RD2031 | Cat 793D | N9500 | Air Cond'r-Serv | 5000 | 79475 | 2026-05-13 | 79726 | 2027-02-09 | 4749 | WA | Iron Bridge
RD2031 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 79475 | 2026-05-13 | 79726 | 2029-04-30 | 19749 | WA | Iron Bridge
RD2031 | Cat 793D | N9501 | A/C Compressor | 10000 | 74703 | 2025-07-14 | 79726 | 2027-02-21 | 4977 | WA | Iron Bridge
RD2031 | Cat 793D | N9998 | Extended Life Rebuild | 45000 | 58553 | 2022-07-17 | 79726 | 2029-12-06 | 23827 | WA | Iron Bridge
RD2031 | Cat 793D | N9998-01 | Extended Life Rebuild ONE | 65000 | 58553 | 2022-07-17 | 79726 | 2032-11-21 | 43827 | WA | Iron Bridge
RD2031 | Cat 793D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-08-15 | 79726 | 2027-03-09 | 5274 | WA | Iron Bridge
RD2035 | Cat 793D | N0066 | Fire Suppression Sys Cylinder |  | 58192 | 2023-09-28 | 70515 | 2028-09-26 |  | WA | Iron Bridge
RD2035 | Cat 793D | N0200 | A Frame Bearing | 20000 | 56552 | 2022-11-16 | 70515 | 2027-04-11 | 6037 | WA | Iron Bridge
RD2035 | Cat 793D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 61431 | 2024-07-23 | 70515 | 2025-05-20 | -7084 | WA | Iron Bridge
RD2035 | Cat 793D | N0520 | Pre Lube Pump | 20000 | 58192 | 2023-06-14 | 70515 | 2027-07-06 | 7677 | WA | Iron Bridge
RD2035 | Cat 793D | N1000 | Engine | 20000 | 58192 | 2023-06-15 | 70515 | 2027-07-06 | 7677 | WA | Iron Bridge
RD2035 | Cat 793D | N1002 | Engine Valve Adj | 4000 | 66409 | 2025-05-05 | 70515 | 2026-05-22 | -106 | WA | Iron Bridge
RD2035 | Cat 793D | N1002-01 | Engine Valve Adj - Initial | 50 | 60601 | 2024-06-24 | 70515 | 2024-12-25 | -9864 | WA | Iron Bridge
RD2035 | Cat 793D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 69289 | 2025-12-17 | 70515 | 2027-09-02 | 8774 | WA | Iron Bridge
RD2035 | Cat 793D | N1100-LR | Turbo Primary LFT REAR | 10000 | 69289 | 2025-12-18 | 70515 | 2027-09-02 | 8774 | WA | Iron Bridge
RD2035 | Cat 793D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 69289 | 2025-12-17 | 70515 | 2027-09-02 | 8774 | WA | Iron Bridge
RD2035 | Cat 793D | N1100-RR | Turbo Primary RHT REAR | 10000 | 69289 | 2025-12-16 | 70515 | 2027-09-02 | 8774 | WA | Iron Bridge
RD2035 | Cat 793D | N1202 | Fuel Transfer Pump | 10000 | 59198 | 2023-06-15 | 70515 | 2026-02-20 | -1317 | WA | Iron Bridge
RD2035 | Cat 793D | N1300 | Cooling Sys Service | 10000 | 69728 | 2026-01-13 | 70515 | 2027-09-25 | 9213 | WA | Iron Bridge
RD2035 | Cat 793D | N1310 | Radiator | 20000 | 58192 | 2023-06-15 | 70515 | 2027-07-06 | 7677 | WA | Iron Bridge
RD2035 | Cat 793D | N1400 | Belt Tensioner Assembly | 10000 | 59198 | 2023-06-15 | 70515 | 2026-02-20 | -1317 | WA | Iron Bridge
RD2035 | Cat 793D | N1420 | Air Compressor | 10000 | 69289 | 2025-12-17 | 70515 | 2027-09-02 | 8774 | WA | Iron Bridge
RD2035 | Cat 793D | N2000 | Transmission | 20000 | 62763 | 2024-09-27 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N2050 | Torque Convertor | 20000 | 55002 | 2021-02-23 | 70515 | 2027-01-19 | 4487 | WA | Iron Bridge
RD2035 | Cat 793D | N2052 | Convertor/Trans Pump | 20000 | 58192 | 2023-06-05 | 70515 | 2027-07-06 | 7677 | WA | Iron Bridge
RD2035 | Cat 793D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 63875 | 2024-12-21 | 70515 | 2028-04-30 | 13360 | WA | Iron Bridge
RD2035 | Cat 793D | N3021 | Uni's Eng - Pump Drive | 5000 | 69319 | 2025-12-22 | 70515 | 2026-12-14 | 3804 | WA | Iron Bridge
RD2035 | Cat 793D | N3028 | Drive Shaft T/C - Trans | 20000 | 55002 | 2021-02-23 | 70515 | 2027-01-19 | 4487 | WA | Iron Bridge
RD2035 | Cat 793D | N3029 | Uni's T/C - Trans | 10000 | 66939 | 2025-06-03 | 70515 | 2027-05-01 | 6424 | WA | Iron Bridge
RD2035 | Cat 793D | N3320 | Pump Drive Box | 20000 | 63875 | 2024-12-21 | 70515 | 2028-04-30 | 13360 | WA | Iron Bridge
RD2035 | Cat 793D | N4000 | Bevel Gear | 20000 | 69000 | 2025-09-27 | 70515 | 2029-01-25 | 18485 | WA | Iron Bridge
RD2035 | Cat 793D | N4102-03 | Axle Shaft - POS 3 | 20000 | 62763 | 2024-09-28 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N4102-04 | Axle Shaft - POS 4 | 20000 | 62763 | 2024-09-29 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N5003-03 | Final Drive Ext Life POS 3 | 20000 | 52212 | 2021-09-15 | 70515 | 2026-08-25 | 1697 | WA | Iron Bridge
RD2035 | Cat 793D | N5003-04 | Final Drive Ext Life POS 4 | 20000 | 62763 | 2024-09-28 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N5020-01 | Wheel Bearing POS 1 | 24000 | 67570 | 2025-07-09 | 70515 | 2029-06-09 | 21055 | WA | Iron Bridge
RD2035 | Cat 793D | N5020-02 | Wheel Bearing POS 2 | 24000 | 69289 | 2025-12-17 | 70515 | 2029-09-08 | 22774 | WA | Iron Bridge
RD2035 | Cat 793D | N6000-01 | Brake POS 1 | 24000 | 67570 | 2025-07-09 | 70515 | 2029-06-09 | 21055 | WA | Iron Bridge
RD2035 | Cat 793D | N6000-02 | Brake POS 2 | 24000 | 69289 | 2025-12-17 | 70515 | 2029-09-08 | 22774 | WA | Iron Bridge
RD2035 | Cat 793D | N6030-F | Brake Slack Adj FRONT | 24000 | 66939 | 2025-06-04 | 70515 | 2029-05-07 | 20424 | WA | Iron Bridge
RD2035 | Cat 793D | N6030-RE | Brake Slack Adj REAR | 20000 | 62763 | 2024-09-28 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N6061 | Oil Cooler Front Brakes | 24000 | 69289 | 2025-12-17 | 70515 | 2029-09-08 | 22774 | WA | Iron Bridge
RD2035 | Cat 793D | N6062-F | Oil Cooler Rear Brakes FRONT | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N6062-RE | Oil Cooler Rear Brakes REAR | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N6200-01 | Press Convertor POS 1 | 12000 | 62763 | 2024-09-29 | 70515 | 2027-01-07 | 4248 | WA | Iron Bridge
RD2035 | Cat 793D | N6200-02 | Press Convertor POS 2 | 12000 | 62763 | 2024-09-29 | 70515 | 2027-01-07 | 4248 | WA | Iron Bridge
RD2035 | Cat 793D | N6200-03 | Press Convertor POS 3 | 10000 | 62763 | 2024-09-28 | 70515 | 2026-09-23 | 2248 | WA | Iron Bridge
RD2035 | Cat 793D | N6200-04 | Press Convertor POS 4 | 10000 | 62763 | 2024-09-28 | 70515 | 2026-09-23 | 2248 | WA | Iron Bridge
RD2035 | Cat 793D | N7021 | Pump Brake Cooling | 40000 | 69289 | 2025-12-17 | 70515 | 2031-12-29 | 38774 | WA | Iron Bridge
RD2035 | Cat 793D | N7024 | Hyd Motor Brake Cooling | 20000 | 63799 | 2024-11-24 | 70515 | 2028-04-26 | 13284 | WA | Iron Bridge
RD2035 | Cat 793D | N7027 | Pump Hoist/Brake Rel/Oil Cool | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N7041 | Pump Cooling Fan Engine | 20000 | 69289 | 2025-12-17 | 70515 | 2029-02-09 | 18774 | WA | Iron Bridge
RD2035 | Cat 793D | N7088 | Pump Park Brk Rel | 40000 | 42925 | 2019-06-01 | 70515 | 2028-03-11 | 12410 | WA | Iron Bridge
RD2035 | Cat 793D | N7120 | Pump Steering | 20000 | 69289 | 2025-12-17 | 70515 | 2029-02-09 | 18774 | WA | Iron Bridge
RD2035 | Cat 793D | N7160 | Pump Axle Lube/Cooler | 20000 | 52212 | 2021-09-08 | 70515 | 2026-08-25 | 1697 | WA | Iron Bridge
RD2035 | Cat 793D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 62763 | 2024-09-28 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N7232 | Hyd Motor Engine Fan | 20000 | 58192 | 2023-06-07 | 70515 | 2027-07-06 | 7677 | WA | Iron Bridge
RD2035 | Cat 793D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 41612 | 2019-02-06 | 70515 | 2026-07-25 | 1097 | WA | Iron Bridge
RD2035 | Cat 793D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 62763 | 2024-10-02 | 70515 | 2029-08-11 | 22248 | WA | Iron Bridge
RD2035 | Cat 793D | N7541 | Hyd Cyl Access Ladder | 20000 |  |  | 70515 | 2019-02-15 | -50515 | WA | Iron Bridge
RD2035 | Cat 793D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 58200 | 2023-11-20 | 70515 | 2027-07-06 | 7685 | WA | Iron Bridge
RD2035 | Cat 793D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 57008 | 2022-09-17 | 70515 | 2027-05-05 | 6493 | WA | Iron Bridge
RD2035 | Cat 793D | N7605 | Steering Hmu | 20000 | 61965 | 2024-08-20 | 70515 | 2028-01-21 | 11450 | WA | Iron Bridge
RD2035 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N7647 | Hyd Accum Brake Reseal | 20000 | 62763 | 2024-09-27 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N7657-C | Hyd Accum Steering CENTER | 20000 | 62763 | 2024-09-27 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N7657-F | Hyd Accum Steering FRONT | 20000 | 62763 | 2024-09-27 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N7657-RE | Hyd Accum Steering REAR | 20000 | 62763 | 2024-09-27 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8000 | Main Frame/Chassis | 30000 |  |  | 70515 | 2020-07-26 | -40515 | WA | Iron Bridge
RD2035 | Cat 793D | N8122-01 | Wheel Group POS 1 | 24000 | 67570 | 2025-07-09 | 70515 | 2029-06-09 | 21055 | WA | Iron Bridge
RD2035 | Cat 793D | N8122-02 | Wheel Group POS 2 | 24000 | 69289 | 2025-12-17 | 70515 | 2029-09-08 | 22774 | WA | Iron Bridge
RD2035 | Cat 793D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8137-L | Steering Linkage Group LEFT | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8137-R | Steering Linkage Group RIGHT | 20000 | 62763 | 2024-09-30 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8140 | Steering Y Piece | 20000 | 62763 | 2024-10-01 | 70515 | 2028-03-03 | 12248 | WA | Iron Bridge
RD2035 | Cat 793D | N8200-01 | Ride Strut POS 1 | 24000 | 62763 | 2024-10-03 | 70515 | 2028-09-29 | 16248 | WA | Iron Bridge
RD2035 | Cat 793D | N8200-02 | Ride Strut POS 2 | 24000 | 69289 | 2025-12-17 | 70515 | 2029-09-08 | 22774 | WA | Iron Bridge
RD2035 | Cat 793D | N8200-03 | Ride Strut POS 3 | 30000 | 52212 | 2021-09-20 | 70515 | 2028-02-03 | 11697 | WA | Iron Bridge
RD2035 | Cat 793D | N8200-04 | Ride Strut POS 4 | 30000 | 57008 | 2022-09-10 | 70515 | 2028-10-12 | 16493 | WA | Iron Bridge
RD2035 | Cat 793D | N8441 | Rear Axle Dog Bone | 15000 | 57008 | 2022-09-12 | 70515 | 2026-08-15 | 1493 | WA | Iron Bridge
RD2035 | Cat 793D | N8501 | Ball Stud Crack Test |  | 69975 | 2026-01-26 | 70515 | 2026-07-27 |  | WA | Iron Bridge
RD2035 | Cat 793D | N8995 | Operator Seat | 6000 | 69728 | 2026-01-14 | 70515 | 2027-02-26 | 5213 | WA | Iron Bridge
RD2035 | Cat 793D | N8999 | Cab Upgrade | 60000 |  |  | 70515 | 2024-11-21 | -10515 | WA | Iron Bridge
RD2035 | Cat 793D | N9020 | Alternator | 10000 | 59198 | 2023-06-15 | 70515 | 2026-02-20 | -1317 | WA | Iron Bridge
RD2035 | Cat 793D | N9050-LW | Starter Motor LOWER | 10000 | 69634 | 2026-01-08 | 70515 | 2027-09-20 | 9119 | WA | Iron Bridge
RD2035 | Cat 793D | N9050-UP | Starter Motor UPPER | 10000 | 69634 | 2026-01-08 | 70515 | 2027-09-20 | 9119 | WA | Iron Bridge
RD2035 | Cat 793D | N9500 | Air Cond'r-Serv | 5000 | 69726 | 2026-01-14 | 70515 | 2027-01-05 | 4211 | WA | Iron Bridge
RD2035 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 58192 | 2023-06-05 | 70515 | 2027-07-06 | 7677 | WA | Iron Bridge
RD2035 | Cat 793D | N9501 | A/C Compressor | 10000 | 69728 | 2026-01-14 | 70515 | 2027-09-25 | 9213 | WA | Iron Bridge
RD2035 | Cat 793D | N9998 | Extended Life Rebuild | 45000 |  | 2008-09-15 | 70515 | 2022-09-23 | -25515 | WA | Iron Bridge
RD2035 | Cat 793D | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2008-09-15 | 70515 | 2025-08-11 | -5515 | WA | Iron Bridge
RD2035 | Cat 793D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-09-15 | 70515 | 2028-06-28 | 14485 | WA | Iron Bridge
RD2131 | Cat 793D | N0066 | Fire Suppression Sys Cylinder |  | 64449 | 2024-02-15 | 75619 | 2029-02-13 |  | WA | Iron Bridge
RD2131 | Cat 793D | N0200 | A Frame Bearing | 20000 | 70837 | 2025-03-29 | 75619 | 2028-08-06 | 15218 | WA | Iron Bridge
RD2131 | Cat 793D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 70837 | 2025-03-29 | 75619 | 2025-11-13 | -2782 | WA | Iron Bridge
RD2131 | Cat 793D | N0520 | Pre Lube Pump | 20000 | 64859 | 2024-04-14 | 75619 | 2027-09-26 | 9240 | WA | Iron Bridge
RD2131 | Cat 793D | N1000 | Engine | 20000 | 75621 | 2026-03-08 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N1002 | Engine Valve Adj | 4000 | 75621 | 2026-03-08 | 75619 | 2026-12-25 | 4002 | WA | Iron Bridge
RD2131 | Cat 793D | N1002-01 | Engine Valve Adj - Initial | 50 | 75621 | 2026-03-08 | 75619 | 2026-05-31 | 52 | WA | Iron Bridge
RD2131 | Cat 793D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1100-LR | Turbo Primary LFT REAR | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1100-RR | Turbo Primary RHT REAR | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1202 | Fuel Transfer Pump | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1300 | Cooling Sys Service | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1310 | Radiator | 20000 | 75621 | 2026-03-07 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N1400 | Belt Tensioner Assembly | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N1420 | Air Compressor | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N2000 | Transmission | 20000 | 75621 | 2026-03-08 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N2050 | Torque Convertor | 20000 | 75621 | 2026-03-06 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N2052 | Convertor/Trans Pump | 20000 | 70404 | 2025-02-09 | 75619 | 2028-07-14 | 14785 | WA | Iron Bridge
RD2131 | Cat 793D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 64513 | 2024-02-22 | 75619 | 2027-09-08 | 8894 | WA | Iron Bridge
RD2131 | Cat 793D | N3021 | Uni's Eng - Pump Drive | 5000 | 75621 | 2026-03-08 | 75619 | 2027-02-15 | 5002 | WA | Iron Bridge
RD2131 | Cat 793D | N3028 | Drive Shaft T/C - Trans | 20000 | 64856 | 2024-04-10 | 75619 | 2027-09-26 | 9237 | WA | Iron Bridge
RD2131 | Cat 793D | N3029 | Uni's T/C - Trans | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N3320 | Pump Drive Box | 20000 | 69320 | 2024-12-09 | 75619 | 2026-11-10 | 3150 | WA | Iron Bridge
RD2131 | Cat 793D | N4000 | Bevel Gear | 20000 | 64856 | 2024-04-11 | 75619 | 2027-09-26 | 9237 | WA | Iron Bridge
RD2131 | Cat 793D | N4102-03 | Axle Shaft - POS 3 | 20000 | 75621 | 2026-03-06 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N4102-04 | Axle Shaft - POS 4 | 20000 | 75621 | 2026-03-10 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N5003-03 | Final Drive Ext Life POS 3 | 20000 | 60134 | 2022-09-26 | 75619 | 2027-01-21 | 4515 | WA | Iron Bridge
RD2131 | Cat 793D | N5003-04 | Final Drive Ext Life POS 4 | 20000 | 55489 | 2021-09-29 | 75619 | 2026-05-21 | -130 | WA | Iron Bridge
RD2131 | Cat 793D | N5020-01 | Wheel Bearing POS 1 | 24000 | 48790 | 2019-11-21 | 75619 | 2025-09-28 | -2829 | WA | Iron Bridge
RD2131 | Cat 793D | N5020-02 | Wheel Bearing POS 2 | 24000 | 48970 | 2019-11-21 | 75619 | 2025-10-07 | -2649 | WA | Iron Bridge
RD2131 | Cat 793D | N6000-01 | Brake POS 1 | 24000 | 48790 | 2019-11-21 | 75619 | 2025-09-28 | -2829 | WA | Iron Bridge
RD2131 | Cat 793D | N6000-02 | Brake POS 2 | 24000 | 48970 | 2019-11-21 | 75619 | 2025-10-07 | -2649 | WA | Iron Bridge
RD2131 | Cat 793D | N6030-F | Brake Slack Adj FRONT | 24000 | 64513 | 2024-02-25 | 75619 | 2028-04-06 | 12894 | WA | Iron Bridge
RD2131 | Cat 793D | N6030-RE | Brake Slack Adj REAR | 20000 | 75621 | 2026-03-09 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N6061 | Oil Cooler Front Brakes | 24000 | 75621 | 2026-03-07 | 75619 | 2029-11-11 | 24002 | WA | Iron Bridge
RD2131 | Cat 793D | N6062-F | Oil Cooler Rear Brakes FRONT | 20000 | 66210 | 2024-07-05 | 75619 | 2027-12-06 | 10591 | WA | Iron Bridge
RD2131 | Cat 793D | N6062-RE | Oil Cooler Rear Brakes REAR | 20000 | 66210 | 2024-07-05 | 75619 | 2027-12-06 | 10591 | WA | Iron Bridge
RD2131 | Cat 793D | N6200-01 | Press Convertor POS 1 | 12000 | 75621 | 2026-03-09 | 75619 | 2028-02-19 | 12002 | WA | Iron Bridge
RD2131 | Cat 793D | N6200-02 | Press Convertor POS 2 | 12000 | 75621 | 2026-03-09 | 75619 | 2028-02-19 | 12002 | WA | Iron Bridge
RD2131 | Cat 793D | N6200-03 | Press Convertor POS 3 | 10000 | 75621 | 2026-03-09 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N6200-04 | Press Convertor POS 4 | 10000 | 75621 | 2026-03-09 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N7021 | Pump Brake Cooling | 40000 | 46507 | 2019-04-30 | 75619 | 2027-12-22 | 10888 | WA | Iron Bridge
RD2131 | Cat 793D | N7024 | Hyd Motor Brake Cooling | 20000 | 64431 | 2024-01-07 | 75619 | 2027-09-04 | 8812 | WA | Iron Bridge
RD2131 | Cat 793D | N7027 | Pump Hoist/Brake Rel/Oil Cool | 20000 | 69320 | 2024-12-09 | 75619 | 2028-05-18 | 13701 | WA | Iron Bridge
RD2131 | Cat 793D | N7041 | Pump Cooling Fan Engine | 20000 | 64431 | 2024-02-18 | 75619 | 2027-09-04 | 8812 | WA | Iron Bridge
RD2131 | Cat 793D | N7088 | Pump Park Brk Rel | 40000 | 69320 | 2024-12-09 | 75619 | 2031-04-06 | 33701 | WA | Iron Bridge
RD2131 | Cat 793D | N7120 | Pump Steering | 20000 | 75621 | 2026-03-09 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N7160 | Pump Axle Lube/Cooler | 20000 | 69320 | 2024-12-10 | 75619 | 2028-05-18 | 13701 | WA | Iron Bridge
RD2131 | Cat 793D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 69320 | 2024-12-10 | 75619 | 2028-05-18 | 13701 | WA | Iron Bridge
RD2131 | Cat 793D | N7232 | Hyd Motor Engine Fan | 20000 | 65230 | 2024-05-08 | 75619 | 2027-10-16 | 9611 | WA | Iron Bridge
RD2131 | Cat 793D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 46507 | 2019-04-30 | 75619 | 2026-07-14 | 888 | WA | Iron Bridge
RD2131 | Cat 793D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 71211 | 2025-04-18 | 75619 | 2030-02-03 | 25592 | WA | Iron Bridge
RD2131 | Cat 793D | N7541 | Hyd Cyl Access Ladder | 20000 | 48694 | 2019-09-28 | 75619 | 2025-05-29 | -6925 | WA | Iron Bridge
RD2131 | Cat 793D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 53161 | 2020-10-10 | 75619 | 2025-10-16 | -2458 | WA | Iron Bridge
RD2131 | Cat 793D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 55489 | 2021-07-23 | 75619 | 2026-02-16 | -130 | WA | Iron Bridge
RD2131 | Cat 793D | N7605 | Steering Hmu | 20000 | 67363 | 2024-09-01 | 75619 | 2028-02-05 | 11744 | WA | Iron Bridge
RD2131 | Cat 793D | N7613 | Hyd Cooler Steering/Eng Fan | 20000 | 70089 | 2025-01-25 | 75619 | 2028-06-28 | 14470 | WA | Iron Bridge
RD2131 | Cat 793D | N7647 | Hyd Accum Brake Reseal | 20000 | 75621 | 2026-03-09 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N7657-C | Hyd Accum Steering CENTER | 20000 | 72832 | 2025-06-28 | 75619 | 2028-11-19 | 17213 | WA | Iron Bridge
RD2131 | Cat 793D | N7657-F | Hyd Accum Steering FRONT | 20000 | 72832 | 2025-06-28 | 75619 | 2028-11-19 | 17213 | WA | Iron Bridge
RD2131 | Cat 793D | N7657-RE | Hyd Accum Steering REAR | 20000 | 72832 | 2025-06-28 | 75619 | 2028-11-19 | 17213 | WA | Iron Bridge
RD2131 | Cat 793D | N8000 | Main Frame/Chassis | 30000 |  |  | 75619 | 2019-10-31 | -45619 | WA | Iron Bridge
RD2131 | Cat 793D | N8122-01 | Wheel Group POS 1 | 24000 | 48790 | 2019-11-21 | 75619 | 2025-09-28 | -2829 | WA | Iron Bridge
RD2131 | Cat 793D | N8122-02 | Wheel Group POS 2 | 24000 | 48970 | 2019-11-21 | 75619 | 2025-10-07 | -2649 | WA | Iron Bridge
RD2131 | Cat 793D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 75621 | 2026-03-10 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 75621 | 2026-03-10 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 60134 | 2022-09-21 | 75619 | 2026-10-18 | 4515 | WA | Iron Bridge
RD2131 | Cat 793D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 60134 | 2022-09-21 | 75619 | 2026-10-18 | 4515 | WA | Iron Bridge
RD2131 | Cat 793D | N8137-L | Steering Linkage Group LEFT | 20000 | 75621 | 2026-03-10 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N8137-R | Steering Linkage Group RIGHT | 20000 | 60134 | 2022-09-21 | 75619 | 2026-10-18 | 4515 | WA | Iron Bridge
RD2131 | Cat 793D | N8140 | Steering Y Piece | 20000 | 53161 | 2020-10-10 | 75619 | 2026-01-19 | -2458 | WA | Iron Bridge
RD2131 | Cat 793D | N8200-01 | Ride Strut POS 1 | 24000 | 54311 | 2020-12-28 | 75619 | 2026-07-15 | 2692 | WA | Iron Bridge
RD2131 | Cat 793D | N8200-02 | Ride Strut POS 2 | 24000 | 46507 | 2019-04-30 | 75619 | 2025-05-30 | -5112 | WA | Iron Bridge
RD2131 | Cat 793D | N8200-03 | Ride Strut POS 3 | 30000 | 70837 | 2025-03-12 | 75619 | 2030-01-14 | 25218 | WA | Iron Bridge
RD2131 | Cat 793D | N8200-04 | Ride Strut POS 4 | 30000 | 70837 | 2025-03-24 | 75619 | 2030-01-14 | 25218 | WA | Iron Bridge
RD2131 | Cat 793D | N8441 | Rear Axle Dog Bone | 15000 | 70830 | 2025-04-29 | 75619 | 2027-11-16 | 10211 | WA | Iron Bridge
RD2131 | Cat 793D | N8501 | Ball Stud Crack Test |  | 75074 | 2026-01-26 | 75619 | 2026-07-27 |  | WA | Iron Bridge
RD2131 | Cat 793D | N8995 | Operator Seat | 6000 | 70837 | 2025-03-23 | 75619 | 2026-07-31 | 1218 | WA | Iron Bridge
RD2131 | Cat 793D | N8999 | Cab Upgrade | 60000 |  |  | 75619 | 2024-02-26 | -15619 | WA | Iron Bridge
RD2131 | Cat 793D | N9020 | Alternator | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N9050-LW | Starter Motor LOWER | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N9050-UP | Starter Motor UPPER | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N9500 | Air Cond'r-Serv | 5000 | 75621 | 2026-03-12 | 75619 | 2027-02-15 | 5002 | WA | Iron Bridge
RD2131 | Cat 793D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 75621 | 2026-03-12 | 75619 | 2029-04-15 | 20002 | WA | Iron Bridge
RD2131 | Cat 793D | N9501 | A/C Compressor | 10000 | 75621 | 2026-03-08 | 75619 | 2027-11-05 | 10002 | WA | Iron Bridge
RD2131 | Cat 793D | N9998 | Extended Life Rebuild | 45000 |  | 2008-06-24 | 75619 | 2021-12-28 | -30619 | WA | Iron Bridge
RD2131 | Cat 793D | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2008-06-24 | 75619 | 2024-11-15 | -10619 | WA | Iron Bridge
RD2131 | Cat 793D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-06-24 | 75619 | 2027-10-04 | 9381 | WA | Iron Bridge
RD3830 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 49037 | 2022-07-15 | 60741 | 2027-07-14 |  | WA | Hazelmere
RD3830 | Cat 789C | N0200 | A Frame Bearing | 20000 | 58150 | 2024-07-10 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 58150 | 2024-07-10 | 60741 | 2026-04-16 | -591 | WA | Hazelmere
RD3830 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N1000 | Engine | 20000 | 59500 | 2024-10-16 | 60741 | 2030-01-27 | 18759 | WA | Hazelmere
RD3830 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 54204 | 2023-08-22 | 60741 | 2025-11-28 | -2537 | WA | Hazelmere
RD3830 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 39072 | 2020-02-20 | 60741 | 2022-03-06 | -21619 | WA | Hazelmere
RD3830 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1310 | Radiator | 20000 | 39072 | 2020-02-20 | 60741 | 2026-01-29 | -1669 | WA | Hazelmere
RD3830 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 59500 | 2024-10-16 | 60741 | 2028-02-13 | 8759 | WA | Hazelmere
RD3830 | Cat 789C | N1430 | Air Starter | 20000 | 49108 | 2022-07-15 | 60741 | 2028-01-16 | 8367 | WA | Hazelmere
RD3830 | Cat 789C | N2000 | Transmission | 20000 | 58146 | 2024-07-04 | 60741 | 2029-10-22 | 17405 | WA | Hazelmere
RD3830 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 58150 | 2024-07-04 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N2004 | Transmission Pump | 20000 | 58150 | 2024-06-29 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N2050 | Torque Convertor | 20000 | 58150 | 2024-07-09 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 51870 | 2023-03-22 | 60741 | 2028-07-31 | 11129 | WA | Hazelmere
RD3830 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 51870 | 2023-03-22 | 60741 | 2026-08-17 | 1129 | WA | Hazelmere
RD3830 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 58150 | 2024-07-06 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 58150 | 2024-07-06 | 60741 | 2027-11-08 | 7409 | WA | Hazelmere
RD3830 | Cat 789C | N3320 | Pump Drive Box | 20000 | 39072 | 2020-02-20 | 60741 | 2026-01-29 | -1669 | WA | Hazelmere
RD3830 | Cat 789C | N4000 | Bevel Gear | 20000 | 58150 | 2024-07-25 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 58150 | 2024-07-03 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 58150 | 2024-07-03 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 51486 | 2023-03-01 | 60741 | 2028-07-04 | 10745 | WA | Hazelmere
RD3830 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 58339 | 2024-07-27 | 60741 | 2029-11-05 | 17598 | WA | Hazelmere
RD3830 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 49108 | 2022-07-15 | 60741 | 2028-01-16 | 8367 | WA | Hazelmere
RD3830 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 56880 | 2024-03-24 | 60741 | 2029-07-24 | 16139 | WA | Hazelmere
RD3830 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 49108 | 2022-07-15 | 60741 | 2028-01-16 | 8367 | WA | Hazelmere
RD3830 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 56880 | 2024-03-24 | 60741 | 2029-07-24 | 16139 | WA | Hazelmere
RD3830 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 49108 | 2022-07-15 | 60741 | 2026-01-31 | -1633 | WA | Hazelmere
RD3830 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 49108 | 2022-07-15 | 60741 | 2026-01-31 | -1633 | WA | Hazelmere
RD3830 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 49108 | 2022-07-15 | 60741 | 2026-01-31 | -1633 | WA | Hazelmere
RD3830 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 58150 | 2024-07-09 | 60741 | 2029-10-23 | 17409 | WA | Hazelmere
RD3830 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 51870 | 2023-03-22 | 60741 | 2027-10-19 | 7129 | WA | Hazelmere
RD3830 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 28194 | 2018-05-02 | 60741 | 2027-11-11 | 7453 | WA | Hazelmere
RD3830 | Cat 789C | N7120 | Pump Steering | 20000 | 56328 | 2024-02-10 | 60741 | 2029-06-14 | 15587 | WA | Hazelmere
RD3830 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 52045 | 2023-05-20 | 60741 | 2029-05-25 | 15304 | WA | Hazelmere
RD3830 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 42513 | 2020-11-11 | 60741 | 2027-07-14 | 5772 | WA | Hazelmere
RD3830 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N7605 | Steering Hmu | 20000 | 39072 | 2020-02-20 | 60741 | 2026-01-29 | -1669 | WA | Hazelmere
RD3830 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 60741 | 2019-06-01 | -35741 | WA | Hazelmere
RD3830 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 49108 | 2022-07-15 | 60741 | 2028-01-16 | 8367 | WA | Hazelmere
RD3830 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 56880 | 2024-03-24 | 60741 | 2029-07-24 | 16139 | WA | Hazelmere
RD3830 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 39067 | 2020-02-20 | 60741 | 2026-01-28 | -1674 | WA | Hazelmere
RD3830 | Cat 789C | N8140 | Steering Y Piece | 20000 | 49108 | 2022-07-15 | 60741 | 2028-01-16 | 8367 | WA | Hazelmere
RD3830 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 39072 | 2020-02-20 | 60741 | 2026-01-29 | -1669 | WA | Hazelmere
RD3830 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 39072 | 2020-02-20 | 60741 | 2026-01-29 | -1669 | WA | Hazelmere
RD3830 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 58150 | 2024-07-02 | 60741 | 2031-10-07 | 27409 | WA | Hazelmere
RD3830 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 58150 | 2024-07-01 | 60741 | 2031-10-07 | 27409 | WA | Hazelmere
RD3830 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 49108 | 2022-07-15 | 60741 | 2027-01-24 | 3367 | WA | Hazelmere
RD3830 | Cat 789C | N8501 | Ball Stud Crack Test |  | 49037 | 2022-07-15 | 60741 | 2023-01-13 |  | WA | Hazelmere
RD3830 | Cat 789C | N8995 | Operator Seat | 6000 | 51989 | 2023-05-03 | 60741 | 2025-11-12 | -2752 | WA | Hazelmere
RD3830 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 60741 | 2026-04-05 | -741 | WA | Hazelmere
RD3830 | Cat 789C | N9020 | Alternator | 10000 | 49108 | 2022-07-15 | 60741 | 2026-01-31 | -1633 | WA | Hazelmere
RD3830 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 51989 | 2023-05-03 | 60741 | 2025-09-02 | -3752 | WA | Hazelmere
RD3830 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 49108 | 2022-07-15 | 60741 | 2028-01-16 | 8367 | WA | Hazelmere
RD3830 | Cat 789C | N9501 | A/C Compressor | 10000 | 49037 | 2021-11-26 | 60741 | 2026-01-26 | -1704 | WA | Hazelmere
RD3830 | Cat 789C | N9998 | Extended Life Rebuild | 45000 |  | 2013-12-17 | 60741 | 2023-04-30 | -15741 | WA | Hazelmere
RD3830 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2013-12-17 | 60741 | 2027-03-28 | 4259 | WA | Hazelmere
RD3830 | Cat 789C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2015-05-16 | 60741 | 2031-02-24 | 24259 | WA | Hazelmere
RD3831 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 48224 | 2022-04-28 | 59952 | 2027-04-27 |  | WA | Hazelmere
RD3831 | Cat 789C | N0200 | A Frame Bearing | 20000 | 57546 | 2024-07-12 | 59952 | 2029-11-05 | 17594 | WA | Hazelmere
RD3831 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 59961 | 2026-04-07 | 59952 | 2026-10-19 | 2009 | WA | Hazelmere
RD3831 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 57448 | 2024-06-10 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N1000 | Engine | 20000 | 57450 | 2024-06-26 | 59952 | 2029-10-29 | 17498 | WA | Hazelmere
RD3831 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 57450 | 2024-06-26 | 59952 | 2026-09-12 | 1498 | WA | Hazelmere
RD3831 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 58732 | 2024-10-15 | 59952 | 2026-03-05 | -1170 | WA | Hazelmere
RD3831 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1310 | Radiator | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N1430 | Air Starter | 20000 | 48450 | 2022-09-23 | 59952 | 2028-01-25 | 8498 | WA | Hazelmere
RD3831 | Cat 789C | N2000 | Transmission | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 57448 | 2024-06-14 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N2004 | Transmission Pump | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N2050 | Torque Convertor | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 57448 | 2024-06-18 | 59952 | 2027-11-14 | 7496 | WA | Hazelmere
RD3831 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 53942 | 2023-09-23 | 59952 | 2027-03-09 | 3990 | WA | Hazelmere
RD3831 | Cat 789C | N3320 | Pump Drive Box | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N4000 | Bevel Gear | 20000 | 53942 | 2023-09-16 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 57448 | 2024-06-18 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 57547 | 2024-07-20 | 59952 | 2029-11-05 | 17595 | WA | Hazelmere
RD3831 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 47048 | 2021-06-30 | 59952 | 2027-10-17 | 7096 | WA | Hazelmere
RD3831 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 57448 | 2024-06-18 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 57448 | 2024-06-19 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 57448 | 2024-06-18 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 57448 | 2024-06-17 | 59952 | 2027-11-14 | 7496 | WA | Hazelmere
RD3831 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 57448 | 2024-06-18 | 59952 | 2027-11-14 | 7496 | WA | Hazelmere
RD3831 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 57448 | 2024-06-19 | 59952 | 2027-11-14 | 7496 | WA | Hazelmere
RD3831 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 53942 | 2023-09-23 | 59952 | 2029-02-20 | 13990 | WA | Hazelmere
RD3831 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 50859 | 2023-03-11 | 59952 | 2027-10-03 | 6907 | WA | Hazelmere
RD3831 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 33318 | 2019-02-07 | 59952 | 2029-01-07 | 13366 | WA | Hazelmere
RD3831 | Cat 789C | N7120 | Pump Steering | 20000 | 57448 | 2024-06-16 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 38247 | 2020-02-18 | 59952 | 2026-10-30 | 2295 | WA | Hazelmere
RD3831 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 48370 | 2022-04-28 | 59952 | 2028-10-31 | 12418 | WA | Hazelmere
RD3831 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 48224 | 2022-08-01 | 59952 | 2028-01-09 | 8272 | WA | Hazelmere
RD3831 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 49873 | 2023-01-02 | 59952 | 2028-05-06 | 9921 | WA | Hazelmere
RD3831 | Cat 789C | N7605 | Steering Hmu | 20000 | 52396 | 2023-06-12 | 59952 | 2028-10-24 | 12444 | WA | Hazelmere
RD3831 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 57448 | 2024-06-18 | 59952 | 2029-10-20 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 48224 | 2022-05-01 | 59952 | 2027-12-31 | 8272 | WA | Hazelmere
RD3831 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 59952 | 2019-07-27 | -34952 | WA | Hazelmere
RD3831 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 47048 | 2021-06-30 | 59952 | 2027-10-17 | 7096 | WA | Hazelmere
RD3831 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 57448 | 2024-06-12 | 59952 | 2029-10-29 | 17496 | WA | Hazelmere
RD3831 | Cat 789C | N8140 | Steering Y Piece | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 57547 | 2024-07-20 | 59952 | 2029-11-05 | 17595 | WA | Hazelmere
RD3831 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 48370 | 2022-04-28 | 59952 | 2030-01-03 | 18418 | WA | Hazelmere
RD3831 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 48370 | 2022-04-28 | 59952 | 2030-01-03 | 18418 | WA | Hazelmere
RD3831 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 48370 | 2022-04-28 | 59952 | 2027-01-27 | 3418 | WA | Hazelmere
RD3831 | Cat 789C | N8501 | Ball Stud Crack Test |  | 48224 | 2022-04-28 | 59952 | 2022-10-27 |  | WA | Hazelmere
RD3831 | Cat 789C | N8995 | Operator Seat | 6000 | 53942 | 2023-09-23 | 59952 | 2026-05-18 | -10 | WA | Hazelmere
RD3831 | Cat 789C | N8999 | Cab Upgrade | 60000 | 29044 | 2018-04-10 | 59952 | 2032-02-04 | 29092 | WA | Hazelmere
RD3831 | Cat 789C | N9020 | Alternator | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 53942 | 2023-09-23 | 59952 | 2026-03-08 | -1010 | WA | Hazelmere
RD3831 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 48370 | 2022-04-28 | 59952 | 2028-01-19 | 8418 | WA | Hazelmere
RD3831 | Cat 789C | N9501 | A/C Compressor | 10000 | 57450 | 2024-06-26 | 59952 | 2027-11-15 | 7498 | WA | Hazelmere
RD3831 | Cat 789C | N9998 | Extended Life Rebuild | 45000 |  | 2013-12-17 | 59952 | 2023-06-25 | -14952 | WA | Hazelmere
RD3831 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2013-12-17 | 59952 | 2027-05-24 | 5048 | WA | Hazelmere
RD3831 | Cat 789C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2015-05-16 | 59952 | 2031-04-21 | 25048 | WA | Hazelmere
RD3977 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 49357 | 2025-11-11 | 50845.5 | 2030-11-10 |  | WA | Duketon South Operations
RD3977 | Cat 785C | N0200 | A Frame Bearing | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 46718 | 2025-05-16 | 50845.5 | 2025-12-24 | -2127.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 39503 | 2022-10-27 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1000 | Engine | 20000 | 39503 | 2022-10-30 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 48641 | 2025-09-26 | 50845.5 | 2026-10-06 | 1795.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 39907 | 2022-12-29 | 50845.5 | 2024-03-27 | -10888.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1004 | Engine Midlife | 10000 | 49801 | 2025-12-18 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 49801 | 2025-12-18 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 49801 | 2025-12-18 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 49801 | 2025-12-15 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 49801 | 2025-12-18 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1301 | Water Pump | 20000 | 39503 | 2022-10-30 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 39503 | 2022-10-30 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1310 | Radiator | 20000 | 39305 | 2022-10-28 | 50845.5 | 2028-02-02 | 8459.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 49801 | 2025-12-17 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 49801 | 2025-12-17 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1420 | Air Compressor | 10000 | 49801 | 2025-12-18 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N1430 | Air Starter | 10000 | 47990 | 2025-08-04 | 50845.5 | 2027-10-30 | 7144.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N2000 | Transmission | 20000 | 45226 | 2025-01-21 | 50845.5 | 2029-04-08 | 14380.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 45226 | 2025-01-28 | 50845.5 | 2029-04-08 | 14380.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N2004 | Transmission Pump | 20000 | 45226 | 2025-01-28 | 50845.5 | 2029-04-08 | 14380.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N2050 | Torque Convertor | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 39503 | 2022-10-29 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 49801 | 2025-12-15 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 39503 | 2022-10-26 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 49801 | 2025-12-15 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N3320 | Pump Drive Box | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N4000 | Bevel Gear | 20000 | 39503 | 2022-10-29 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 48641 | 2025-09-25 | 50845.5 | 2029-12-12 | 17795.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 45226 | 2025-01-22 | 50845.5 | 2029-04-08 | 14380.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 47219 | 2025-06-16 | 50845.5 | 2029-08-31 | 16373.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 48134 | 2025-08-26 | 50845.5 | 2029-11-05 | 17288.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 48134 | 2025-08-26 | 50845.5 | 2029-11-05 | 17288.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 48641 | 2025-09-26 | 50845.5 | 2029-12-12 | 17795.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 43968 | 2024-07-03 | 50845.5 | 2027-01-10 | 3122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 43968 | 2024-07-03 | 50845.5 | 2027-01-10 | 3122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 43968 | 2024-07-03 | 50845.5 | 2027-01-10 | 3122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 48184 | 2025-08-26 | 50845.5 | 2029-11-09 | 17338.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 39503 | 2022-10-27 | 50845.5 | 2032-02-10 | 28657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7120 | Pump Steering | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 18873 | 2017-12-05 | 50845.5 | 2024-10-25 | -7972.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 18873 | 2017-12-05 | 50845.5 | 2024-10-25 | -7972.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 50846 | 2026-02-27 | 50845.5 | 2030-05-22 | 20000.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7605 | Steering Hmu | 20000 | 33521 | 2020-06-15 | 50845.5 | 2026-12-09 | 2675.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 45400 | 2025-02-12 | 50845.5 | 2029-04-21 | 14554.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 45400 | 2025-02-12 | 50845.5 | 2029-04-21 | 14554.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8000 | Main Frame/Chassis | 25000 | 24854 | 2018-03-20 | 50845.5 | 2026-03-17 | -991.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 48134 | 2025-08-26 | 50845.5 | 2029-11-05 | 17288.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8140 | Steering Y Piece | 20000 | 43968 | 2024-07-03 | 50845.5 | 2029-01-06 | 13122.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 36190 | 2022-02-02 | 50845.5 | 2027-06-21 | 5344.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 24854 | 2018-03-20 | 50845.5 | 2025-03-18 | -5991.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 24854 | 2018-03-20 | 50845.5 | 2025-03-18 | -5991.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 24854 | 2018-03-20 | 50845.5 | 2026-03-17 | -991.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8501 | Ball Stud Crack Test |  | 50264.6 | 2026-01-20 | 50845.5 | 2026-07-21 |  | WA | Duketon South Operations
RD3977 | Cat 785C | N8995 | Operator Seat | 6000 | 49801 | 2025-12-15 | 50845.5 | 2027-05-23 | 4955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N8999 | Cab Upgrade | 25000 | 24854 | 2018-03-20 | 50845.5 | 2026-03-17 | -991.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9020 | Alternator | 10000 | 49801 | 2025-12-15 | 50845.5 | 2028-03-09 | 8955.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 50412 | 2026-01-29 | 50845.5 | 2027-04-25 | 4566.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 39503 | 2022-10-30 | 50845.5 | 2028-02-17 | 8657.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9501 | A/C Compressor | 10000 | 50412 | 2026-01-29 | 50845.5 | 2028-04-23 | 9566.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2013-01-01 | 50845.5 | 2025-03-29 | -5845.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2013-01-01 | 50845.5 | 2029-03-22 | 14154.5 | WA | Duketon South Operations
RD3977 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2013-01-01 | 50845.5 | 2033-03-16 | 34154.5 | WA | Duketon South Operations
RD4201 | Cat 777F | N0066 | Fire Suppression Sys Cylinder |  | 32460 | 2022-06-11 | 42291 | 2027-06-10 |  | WA | Iron Bridge
RD4201 | Cat 777F | N0200 | A Frame Bearing | 20000 | 35540 | 2024-03-10 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N0500 | Bulk Water Pump | 5000 | 25191 | 2019-09-04 | 42291 | 2023-02-03 | -12100 | WA | Iron Bridge
RD4201 | Cat 777F | N1000 | Engine | 20000 | 26705 | 2020-04-24 | 42291 | 2027-08-12 | 4414 | WA | Iron Bridge
RD4201 | Cat 777F | N1002 | Engine Valve Adj | 3000 | 38734 | 2025-06-02 | 42291 | 2026-04-02 | -557 | WA | Iron Bridge
RD4201 | Cat 777F | N1002-01 | Engine Valve Adj - Initial | 500 | 26863 | 2020-05-13 | 42291 | 2022-04-26 | -14928 | WA | Iron Bridge
RD4201 | Cat 777F | N1004 | Engine Midlife | 10000 | 35540 | 2024-03-14 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N1100-L | Turbo Primary LEFT | 10000 | 35540 | 2024-03-14 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N1100-R | Turbo Primary RIGHT | 10000 | 35540 | 2024-03-18 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N1202 | Fuel Transfer Pump | 10000 | 35540 | 2024-03-16 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N1300 | Cooling Sys Service | 10000 | 35540 | 2024-03-17 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N1301 | Water Pump | 10000 | 35540 | 2024-03-17 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N1310 | Radiator | 20000 | 16989 | 2012-05-10 | 42291 | 2024-12-14 | -5302 | WA | Iron Bridge
RD4201 | Cat 777F | N1312-L | Aftercooler Core - LEFT | 20000 | 16989 | 2012-05-10 | 42291 | 2024-12-14 | -5302 | WA | Iron Bridge
RD4201 | Cat 777F | N1312-R | Aftercooler Core - RIGHT | 20000 | 16989 | 2012-05-10 | 42291 | 2024-12-14 | -5302 | WA | Iron Bridge
RD4201 | Cat 777F | N1402 | Fan Pulley Brgs | 10000 | 32369 | 2021-11-08 | 42291 | 2026-04-30 | 78 | WA | Iron Bridge
RD4201 | Cat 777F | N1403 | Jockey Pulley Brgs | 10000 | 32369 | 2021-11-08 | 42291 | 2026-04-30 | 78 | WA | Iron Bridge
RD4201 | Cat 777F | N1490 | Cam Shaft Inspection | 1500 | 38734 | 2025-06-02 | 42291 | 2025-11-03 | -2057 | WA | Iron Bridge
RD4201 | Cat 777F | N2000 | Transmission | 20000 | 35540 | 2024-03-11 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N2002 | Oil Cooler - Transmission | 20000 | 26503 | 2020-01-31 | 42291 | 2027-07-23 | 4212 | WA | Iron Bridge
RD4201 | Cat 777F | N2004 | Transmission Pump | 20000 | 29732 | 2021-01-06 | 42291 | 2028-06-10 | 7441 | WA | Iron Bridge
RD4201 | Cat 777F | N2050 | Torque Convertor | 20000 | 35540 | 2024-03-14 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N2054 | Convertor Scav Pump | 20000 | 29732 | 2021-01-06 | 42291 | 2028-06-10 | 7441 | WA | Iron Bridge
RD4201 | Cat 777F | N3028 | Drive Shaft T/C - Trans | 20000 | 27980 | 2020-08-29 | 42291 | 2027-12-18 | 5689 | WA | Iron Bridge
RD4201 | Cat 777F | N3029 | Uni's T/C - Trans | 10000 | 35540 | 2024-03-17 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N4000 | Bevel Gear | 20000 | 35540 | 2024-03-11 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N4102-03 | Axle Shaft - POS 3 | 20000 | 35540 | 2024-03-15 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N4102-04 | Axle Shaft - POS 4 | 20000 | 35540 | 2024-03-15 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N5000-03 | Final Drive POS 3 | 20000 | 35540 | 2024-03-14 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N5000-04 | Final Drive POS 4 | 20000 | 31260 | 2021-07-01 | 42291 | 2028-11-10 | 8969 | WA | Iron Bridge
RD4201 | Cat 777F | N5020-01 | Wheel Bearing POS 1 | 20000 | 32469 | 2022-05-28 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N5020-02 | Wheel Bearing POS 2 | 20000 | 28766 | 2020-10-31 | 42291 | 2028-03-06 | 6475 | WA | Iron Bridge
RD4201 | Cat 777F | N6004-01 | Brake Disc/Drum POS 01 | 20000 | 32469 | 2022-05-28 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N6004-02 | Brake Disc/Drum POS 02 | 20000 | 28766 | 2020-10-31 | 42291 | 2028-03-06 | 6475 | WA | Iron Bridge
RD4201 | Cat 777F | N6006-10 | Brake Pads POS 01 | 20000 | 38735 | 2025-06-06 | 42291 | 2030-11-27 | 16444 | WA | Iron Bridge
RD4201 | Cat 777F | N6006-20 | Brake Pads POS 02 | 20000 | 38734 | 2025-06-06 | 42291 | 2030-11-27 | 16443 | WA | Iron Bridge
RD4201 | Cat 777F | N6030-RE | Brake Slack Adj REAR | 20000 | 28849 | 2020-11-07 | 42291 | 2028-03-14 | 6558 | WA | Iron Bridge
RD4201 | Cat 777F | N6070-01 | Brake Caliper POS 01 | 20000 | 32469 | 2022-06-04 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N6070-02 | Brake Caliper POS 02 | 20000 | 32469 | 2022-06-01 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N7035 | Pump Hoist, Brk Charge/Cooling | 5000 | 41839 | 2026-02-09 | 42291 | 2027-08-26 | 4548 | WA | Iron Bridge
RD4201 | Cat 777F | N7120 | Pump Steering | 20000 | 32469 | 2022-06-01 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N7128 | Pump Secondary Steer/Brake Rel | 20000 | 26705 | 2020-04-24 | 42291 | 2027-08-12 | 4414 | WA | Iron Bridge
RD4201 | Cat 777F | N7361 | Hyd Motor Water Pump | 10000 | 25144 | 2019-08-18 | 42291 | 2024-06-12 | -7147 | WA | Iron Bridge
RD4201 | Cat 777F | N7474-L | Hyd Cyl Hoist LEFT | 60000 |  |  | 42291 | 2031-04-03 | 17709 | WA | Iron Bridge
RD4201 | Cat 777F | N7474-R | Hyd Cyl Hoist RIGHT | 60000 |  |  | 42291 | 2031-04-03 | 17709 | WA | Iron Bridge
RD4201 | Cat 777F | N7542-L | Hyd Cyl Steer LEFT | 20000 | 28849 | 2020-11-08 | 42291 | 2028-03-14 | 6558 | WA | Iron Bridge
RD4201 | Cat 777F | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 28849 | 2020-11-08 | 42291 | 2028-03-14 | 6558 | WA | Iron Bridge
RD4201 | Cat 777F | N7605 | Steering Hmu | 20000 | 26705 | 2020-04-18 | 42291 | 2027-08-12 | 4414 | WA | Iron Bridge
RD4201 | Cat 777F | N7653 | Hyd Accum Park Brake | 20000 | 35540 | 2024-03-12 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N7654-F | Hyd Accum Service Brake - FR | 20000 | 35540 | 2024-03-12 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N7654-RE | Hyd Accum Service Brake - REAR | 20000 | 35540 | 2024-03-12 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 32469 | 2022-07-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 32469 | 2022-07-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 32469 | 2022-07-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 32469 | 2022-07-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8137-L | Steering Linkage Group LEFT | 20000 | 32469 | 2022-07-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8137-R | Steering Linkage Group RIGHT | 20000 | 32469 | 2022-07-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8140 | Steering Y Piece | 20000 | 35540 | 2024-03-18 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N8200-01 | Ride Strut POS 1 | 20000 | 34124 | 2023-01-25 | 42291 | 2029-08-23 | 11833 | WA | Iron Bridge
RD4201 | Cat 777F | N8200-02 | Ride Strut POS 2 | 20000 | 34124 | 2023-01-25 | 42291 | 2029-08-23 | 11833 | WA | Iron Bridge
RD4201 | Cat 777F | N8200-03 | Ride Strut POS 3 | 20000 | 32469 | 2022-06-11 | 42291 | 2029-03-11 | 10178 | WA | Iron Bridge
RD4201 | Cat 777F | N8200-04 | Ride Strut POS 4 | 20000 | 32850 | 2022-08-26 | 42291 | 2029-04-18 | 10559 | WA | Iron Bridge
RD4201 | Cat 777F | N8441 | Rear Axle Dog Bone | 20000 | 30584 | 2021-03-27 | 42291 | 2028-09-03 | 8293 | WA | Iron Bridge
RD4201 | Cat 777F | N8501 | Ball Stud Crack Test |  | 41763 | 2026-01-27 | 42291 | 2026-07-28 |  | WA | Iron Bridge
RD4201 | Cat 777F | N8995 | Operator Seat | 6000 | 38734 | 2025-06-03 | 42291 | 2027-01-27 | 2443 | WA | Iron Bridge
RD4201 | Cat 777F | N9020 | Alternator | 10000 | 35540 | 2024-03-13 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N9050-L | Starter Motor LEFT | 10000 | 35540 | 2024-03-16 | 42291 | 2027-04-18 | 3249 | WA | Iron Bridge
RD4201 | Cat 777F | N9050-R | Starter Motor RIGHT | 10000 | 41839 | 2026-02-08 | 42291 | 2029-01-07 | 9548 | WA | Iron Bridge
RD4201 | Cat 777F | N9500 | Air Cond'r-Serv | 5000 | 41719 | 2026-01-22 | 42291 | 2027-08-14 | 4428 | WA | Iron Bridge
RD4201 | Cat 777F | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 35540 | 2024-03-16 | 42291 | 2030-01-12 | 13249 | WA | Iron Bridge
RD4201 | Cat 777F | N9501 | A/C Compressor | 10000 | 37214 | 2024-12-12 | 42291 | 2027-10-02 | 4923 | WA | Iron Bridge
RD4208 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 45263 | 2025-04-18 | 47835.6 | 2030-04-17 |  | WA | Duketon South Operations
RD4208 | Cat 785C | N0200 | A Frame Bearing | 20000 | 45525 | 2024-08-23 | 47835.6 | 2030-02-17 | 17689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 47696 | 2026-02-21 | 47835.6 | 2026-10-18 | 1860.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1000 | Engine | 20000 | 44527 | 2024-07-05 | 47835.6 | 2029-12-02 | 16691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 44527 | 2024-07-05 | 47835.6 | 2026-07-20 | 691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 44527 | 2024-07-05 | 47835.6 | 2025-09-19 | -3258.6 | WA | Duketon South Operations
RD4208 | Cat 785C | N1004 | Engine Midlife | 10000 | 44527 | 2024-07-05 | 47835.6 | 2027-10-25 | 6691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 44527 | 2024-07-05 | 47835.6 | 2027-10-25 | 6691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 44527 | 2024-07-05 | 47835.6 | 2027-10-25 | 6691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 44527 | 2024-07-05 | 47835.6 | 2027-10-25 | 6691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 45525 | 2024-07-26 | 47835.6 | 2028-01-09 | 7689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1301 | Water Pump | 20000 | 44527 | 2024-07-05 | 47835.6 | 2029-12-02 | 16691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 44527 | 2024-07-05 | 47835.6 | 2029-12-02 | 16691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1310 | Radiator | 20000 | 45525 | 2024-07-15 | 47835.6 | 2030-02-17 | 17689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 44527 | 2024-07-05 | 47835.6 | 2027-10-25 | 6691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 44527 | 2024-07-05 | 47835.6 | 2027-10-25 | 6691.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1420 | Air Compressor | 10000 | 45525 | 2024-08-12 | 47835.6 | 2028-01-09 | 7689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N1430 | Air Starter | 10000 | 42370 | 2022-11-15 | 47835.6 | 2027-05-12 | 4534.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N2000 | Transmission | 20000 | 37693 | 2019-04-22 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 37693 | 2019-04-19 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N2004 | Transmission Pump | 20000 | 37693 | 2019-04-19 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N2050 | Torque Convertor | 20000 | 45525 | 2024-07-15 | 47835.6 | 2030-02-17 | 17689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 41006 | 2020-10-08 | 47835.6 | 2027-01-27 | 3170.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 40591 | 2019-12-12 | 47835.6 | 2026-12-26 | 2755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N3320 | Pump Drive Box | 20000 | 37693 | 2019-04-22 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N4000 | Bevel Gear | 20000 | 37693 | 2019-04-22 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 40591 | 2019-12-14 | 47835.6 | 2029-02-02 | 12755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 40591 | 2019-12-15 | 47835.6 | 2029-02-02 | 12755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 40239 | 2019-11-04 | 47835.6 | 2029-01-06 | 12403.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 37548 | 2019-04-02 | 47835.6 | 2028-06-13 | 9712.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 40239 | 2019-11-04 | 47835.6 | 2029-01-06 | 12403.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 37548 | 2019-04-02 | 47835.6 | 2028-06-13 | 9712.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 40591 | 2019-12-11 | 47835.6 | 2029-02-02 | 12755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 40591 | 2019-12-11 | 47835.6 | 2029-02-02 | 12755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 444077 | 2023-06-29 | 47835.6 | 2111-12-18 | 406241.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 40591 | 2019-12-11 | 47835.6 | 2026-12-26 | 2755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 40591 | 2019-12-15 | 47835.6 | 2026-12-26 | 2755.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 37693 | 2019-04-21 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 45525 | 2024-07-15 | 47835.6 | 2030-02-17 | 17689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 40590 | 2019-12-15 | 47835.6 | 2033-04-21 | 32754.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7120 | Pump Steering | 20000 | 41122 | 2020-10-26 | 47835.6 | 2029-03-15 | 13286.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 36893 | 2018-10-11 | 47835.6 | 2029-02-25 | 13057.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 36893 | 2018-10-10 | 47835.6 | 2029-02-25 | 13057.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 42370 | 2022-09-23 | 47835.6 | 2029-06-19 | 14534.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 45525 | 2024-07-30 | 47835.6 | 2030-02-17 | 17689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7605 | Steering Hmu | 20000 | 39262 | 2019-08-05 | 47835.6 | 2028-10-23 | 11426.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 45263 | 2025-02-22 | 47835.6 | 2030-01-28 | 17427.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 45263 | 2025-02-22 | 47835.6 | 2030-01-28 | 17427.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 47835.6 | 2021-08-05 | -22835.6 | WA | Duketon South Operations
RD4208 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 40239 | 2019-11-04 | 47835.6 | 2029-01-06 | 12403.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 37548 | 2019-04-02 | 47835.6 | 2028-06-13 | 9712.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 30599 | 2017-01-01 | 47835.6 | 2026-12-27 | 2763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8140 | Steering Y Piece | 20000 | 39988 | 2019-10-10 | 47835.6 | 2028-12-18 | 12152.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 37693 | 2019-04-22 | 47835.6 | 2028-06-24 | 9857.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 42370 | 2022-09-30 | 47835.6 | 2029-06-19 | 14534.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 42370 | 2022-10-20 | 47835.6 | 2029-06-19 | 14534.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 38024 | 2019-05-12 | 47835.6 | 2028-07-20 | 10188.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 30599 | 2017-01-01 | 47835.6 | 2028-01-15 | 7763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8501 | Ball Stud Crack Test |  | 47333.8 | 2026-01-21 | 47835.6 | 2026-07-22 |  | WA | Duketon South Operations
RD4208 | Cat 785C | N8995 | Operator Seat | 6000 | 45525 | 2024-08-07 | 47835.6 | 2027-03-08 | 3689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N8999 | Cab Upgrade | 25000 | 30599 | 2017-01-01 | 47835.6 | 2028-01-15 | 7763.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N9020 | Alternator | 10000 | 40590 | 2019-12-08 | 47835.6 | 2026-12-26 | 2754.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 45525 | 2024-08-08 | 47835.6 | 2026-12-21 | 2689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 45525 | 2024-08-08 | 47835.6 | 2030-02-17 | 17689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N9501 | A/C Compressor | 10000 | 45525 | 2024-06-28 | 47835.6 | 2028-01-09 | 7689.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2007-01-03 | 47835.6 | 2025-10-22 | -2835.6 | WA | Duketon South Operations
RD4208 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2007-01-03 | 47835.6 | 2030-01-07 | 17164.4 | WA | Duketon South Operations
RD4208 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  |  | 47835.6 | 2034-03-26 | 37164.4 | WA | Duketon South Operations
RD4210 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 34745 | 2020-03-30 | 49506 | 2025-03-29 |  | WA | Hazelmere
RD4210 | Cat 785C | N0200 | A Frame Bearing | 20000 | 46952 | 2025-02-14 | 49506 | 2029-09-12 | 17446 | WA | Hazelmere
RD4210 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 46952 | 2025-02-14 | 49506 | 2026-04-20 | -554 | WA | Hazelmere
RD4210 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 35727 | 2022-01-24 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N1000 | Engine | 20000 | 35727 | 2022-06-11 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 46953 | 2025-02-19 | 49506 | 2026-09-05 | 1447 | WA | Hazelmere
RD4210 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 35727 | 2022-06-11 | 49506 | 2023-10-24 | -13729 | WA | Hazelmere
RD4210 | Cat 785C | N1004 | Engine Midlife | 10000 | 46952 | 2025-02-15 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 46952 | 2025-02-15 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 46952 | 2025-02-16 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 46952 | 2025-02-12 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 46952 | 2025-02-18 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1301 | Water Pump | 20000 | 35727 | 2022-06-11 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 35727 | 2022-06-11 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N1310 | Radiator | 20000 | 35727 | 2022-02-04 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 46952 | 2025-02-15 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 46952 | 2025-02-15 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1420 | Air Compressor | 10000 | 46952 | 2025-02-14 | 49506 | 2027-10-24 | 7446 | WA | Hazelmere
RD4210 | Cat 785C | N1430 | Air Starter | 10000 | 34745 | 2020-03-30 | 49506 | 2025-07-04 | -4761 | WA | Hazelmere
RD4210 | Cat 785C | N2000 | Transmission | 20000 | 35727 | 2022-01-23 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 35727 | 2022-01-17 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N2004 | Transmission Pump | 20000 | 35727 | 2022-01-18 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N2050 | Torque Convertor | 20000 | 35727 | 2022-02-01 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 34783 | 2020-11-06 | 49506 | 2025-07-06 | -4723 | WA | Hazelmere
RD4210 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 43183 | 2024-05-25 | 49506 | 2028-12-26 | 13677 | WA | Hazelmere
RD4210 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 43183 | 2024-05-25 | 49506 | 2027-02-06 | 3677 | WA | Hazelmere
RD4210 | Cat 785C | N3320 | Pump Drive Box | 20000 | 35712 | 2021-02-06 | 49506 | 2027-07-30 | 6206 | WA | Hazelmere
RD4210 | Cat 785C | N4000 | Bevel Gear | 20000 | 35727 | 2022-01-23 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 31120 | 2019-07-10 | 49506 | 2026-09-16 | 1614 | WA | Hazelmere
RD4210 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 31120 | 2019-07-10 | 49506 | 2026-09-16 | 1614 | WA | Hazelmere
RD4210 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 29465 | 2019-02-24 | 49506 | 2026-05-25 | -41 | WA | Hazelmere
RD4210 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 35727 | 2022-01-20 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 29360 | 2017-11-14 | 49506 | 2026-05-18 | -146 | WA | Hazelmere
RD4210 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 29360 | 2017-11-14 | 49506 | 2026-05-18 | -146 | WA | Hazelmere
RD4210 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 29393 | 2017-11-22 | 49506 | 2026-05-20 | -113 | WA | Hazelmere
RD4210 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 29360 | 2017-11-14 | 49506 | 2026-05-18 | -146 | WA | Hazelmere
RD4210 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 33497 | 2019-12-31 | 49506 | 2027-02-27 | 3991 | WA | Hazelmere
RD4210 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 29461 | 2017-12-24 | 49506 | 2026-05-25 | -45 | WA | Hazelmere
RD4210 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 29461 | 2017-12-24 | 49506 | 2026-05-25 | -45 | WA | Hazelmere
RD4210 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 41044 | 2023-10-10 | 49506 | 2026-09-11 | 1538 | WA | Hazelmere
RD4210 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 34744 | 2020-08-07 | 49506 | 2025-07-04 | -4762 | WA | Hazelmere
RD4210 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 33497 | 2020-01-01 | 49506 | 2025-04-09 | -6009 | WA | Hazelmere
RD4210 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 35727 | 2022-02-01 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 35727 | 2022-01-17 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 35727 | 2022-02-02 | 49506 | 2030-10-04 | 26221 | WA | Hazelmere
RD4210 | Cat 785C | N7120 | Pump Steering | 20000 | 36155 | 2022-10-10 | 49506 | 2027-08-30 | 6649 | WA | Hazelmere
RD4210 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 29464 | 2019-01-31 | 49506 | 2027-02-25 | 3958 | WA | Hazelmere
RD4210 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 29464 | 2019-01-31 | 49506 | 2027-02-25 | 3958 | WA | Hazelmere
RD4210 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 35727 | 2022-01-25 | 49506 | 2027-07-31 | 6221 | WA | Hazelmere
RD4210 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 35591 | 2021-01-21 | 49506 | 2027-07-22 | 6085 | WA | Hazelmere
RD4210 | Cat 785C | N7605 | Steering Hmu | 20000 | 46993 | 2025-02-26 | 49506 | 2029-09-15 | 17487 | WA | Hazelmere
RD4210 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 28580 | 2017-09-24 | 49506 | 2026-03-25 | -926 | WA | Hazelmere
RD4210 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 28580 | 2017-09-24 | 49506 | 2026-03-25 | -926 | WA | Hazelmere
RD4210 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 49506 | 2021-10-11 | -24506 | WA | Hazelmere
RD4210 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 29393 | 2017-11-22 | 49506 | 2026-05-20 | -113 | WA | Hazelmere
RD4210 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 29360 | 2017-11-14 | 49506 | 2026-05-18 | -146 | WA | Hazelmere
RD4210 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 23231 | 2016-09-10 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8140 | Steering Y Piece | 20000 | 23231 | 2016-09-08 | 49506 | 2025-03-21 | -6275 | WA | Hazelmere
RD4210 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 46953 | 2025-02-19 | 49506 | 2029-09-12 | 17447 | WA | Hazelmere
RD4210 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 29360 | 2017-11-14 | 49506 | 2026-05-18 | -146 | WA | Hazelmere
RD4210 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 29461 | 2017-12-24 | 49506 | 2026-05-25 | -45 | WA | Hazelmere
RD4210 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 34467 | 2020-03-12 | 49506 | 2027-05-05 | 4961 | WA | Hazelmere
RD4210 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 29461 | 2017-12-28 | 49506 | 2027-05-05 | 4955 | WA | Hazelmere
RD4210 | Cat 785C | N8501 | Ball Stud Crack Test |  | 35727 | 2022-06-16 | 49506 | 2022-12-15 |  | WA | Hazelmere
RD4210 | Cat 785C | N8995 | Operator Seat | 6000 | 35727 | 2022-01-27 | 49506 | 2024-12-08 | -7779 | WA | Hazelmere
RD4210 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 49506 | 2021-10-11 | -24506 | WA | Hazelmere
RD4210 | Cat 785C | N9020 | Alternator | 10000 | 35727 | 2022-06-11 | 49506 | 2025-09-09 | -3779 | WA | Hazelmere
RD4210 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 35730 | 2022-06-09 | 49506 | 2024-09-30 | -8776 | WA | Hazelmere
RD4210 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 35730 | 2022-06-09 | 49506 | 2027-07-31 | 6224 | WA | Hazelmere
RD4210 | Cat 785C | N9501 | A/C Compressor | 10000 | 35727 | 2022-06-11 | 49506 | 2025-09-09 | -3779 | WA | Hazelmere
RD4210 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2011-02-04 | 49506 | 2025-07-21 | -4506 | WA | Hazelmere
RD4210 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-02-04 | 49506 | 2029-05-01 | 15494 | WA | Hazelmere
RD4210 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-02-04 | 49506 | 2033-02-08 | 35494 | WA | Hazelmere
RD4217 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 36545.2 | 2020-12-06 | 45745.5 | 2025-12-05 |  | WA | Duketon South Operations
RD4217 | Cat 785C | N0200 | A Frame Bearing | 20000 | 55935 | 2026-02-28 | 45745.5 | 2032-10-05 | 30189.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 45677 | 2026-02-21 | 45745.5 | 2026-10-24 | 1931.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1000 | Engine | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 44528 | 2025-11-23 | 45745.5 | 2026-12-28 | 2782.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 37661 | 2021-03-26 | 45745.5 | 2024-09-17 | -8034.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1004 | Engine Midlife | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1301 | Water Pump | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1310 | Radiator | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1420 | Air Compressor | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N1430 | Air Starter | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N2000 | Transmission | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N2004 | Transmission Pump | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N2050 | Torque Convertor | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 43043 | 2023-08-02 | 45745.5 | 2027-12-10 | 7297.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 43043 | 2023-08-02 | 45745.5 | 2027-12-10 | 7297.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N3320 | Pump Drive Box | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N4000 | Bevel Gear | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 37808 | 2022-06-17 | 45745.5 | 2028-12-11 | 12062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 37808 | 2022-06-17 | 45745.5 | 2028-12-11 | 12062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 37808 | 2022-06-17 | 45745.5 | 2028-12-11 | 12062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 37808 | 2022-06-17 | 45745.5 | 2028-12-11 | 12062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 48043 | 2023-08-02 | 45745.5 | 2028-12-29 | 12297.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 43043 | 2023-08-02 | 45745.5 | 2027-12-10 | 7297.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 43043 | 2023-08-02 | 45745.5 | 2027-12-10 | 7297.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 37138 | 2021-01-29 | 45745.5 | 2028-10-20 | 11392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 37808 | 2022-06-17 | 45745.5 | 2033-02-26 | 32062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7120 | Pump Steering | 20000 | 43375 | 2024-10-01 | 45745.5 | 2030-02-12 | 17629.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 34493 | 2020-01-01 | 45745.5 | 2029-02-02 | 12747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 34493 | 2020-01-01 | 45745.5 | 2029-02-02 | 12747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 44375 | 2024-10-01 | 45745.5 | 2030-04-30 | 18629.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 43882 | 2023-10-17 | 45745.5 | 2030-03-23 | 18136.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7605 | Steering Hmu | 20000 | 43375 | 2024-10-01 | 45745.5 | 2030-02-12 | 17629.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 49224 | 2025-03-23 | 45745.5 | 2031-05-08 | 23478.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 49224 | 2025-03-23 | 45745.5 | 2031-05-08 | 23478.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 45745.5 | 2022-01-13 | -20745.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 37808 | 2022-06-17 | 45745.5 | 2028-12-11 | 12062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 37808 | 2022-06-17 | 45745.5 | 2028-12-11 | 12062.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8140 | Steering Y Piece | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 33252 | 2019-02-01 | 45745.5 | 2027-12-26 | 7506.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 34924 | 2020-08-26 | 45745.5 | 2028-05-03 | 9178.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 28205 | 2017-08-01 | 45745.5 | 2026-12-03 | 2459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 28205 | 2017-08-01 | 45745.5 | 2027-12-23 | 7459.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8501 | Ball Stud Crack Test |  | 45241.8 | 2026-01-20 | 45745.5 | 2026-07-21 |  | WA | Duketon South Operations
RD4217 | Cat 785C | N8995 | Operator Seat | 6000 | 45677 | 2026-02-21 | 45745.5 | 2027-08-27 | 5931.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 45745.5 | 2022-01-13 | -20745.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9020 | Alternator | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 34493 | 2020-01-01 | 45745.5 | 2025-02-01 | -6252.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 34493 | 2020-01-01 | 45745.5 | 2028-03-31 | 8747.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9501 | A/C Compressor | 10000 | 37138 | 2021-01-29 | 45745.5 | 2026-09-12 | 1392.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2008-09-03 | 45745.5 | 2026-04-01 | -745.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2008-09-03 | 45745.5 | 2030-06-17 | 19254.5 | WA | Duketon South Operations
RD4217 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2008-09-03 | 45745.5 | 2034-09-03 | 39254.5 | WA | Duketon South Operations
RD4218 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 44322 | 2025-11-11 | 44852.3 | 2030-11-10 |  | WA | Duketon South Operations
RD4218 | Cat 785C | N0200 | A Frame Bearing | 20000 | 42983 | 2023-05-16 | 44852.3 | 2029-09-18 | 18130.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 42983.1 | 2023-05-16 | 44852.3 | 2026-06-06 | 130.8 | WA | Duketon South Operations
RD4218 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 36775 | 2021-10-03 | 44852.3 | 2028-07-31 | 11922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1000 | Engine | 20000 | 36775 | 2021-09-28 | 44852.3 | 2028-07-31 | 11922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 44852 | 2026-02-12 | 44852.3 | 2027-02-19 | 3999.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 36775 | 2021-09-28 | 44852.3 | 2024-12-09 | -8027.3 | WA | Duketon South Operations
RD4218 | Cat 785C | N1004 | Engine Midlife | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1301 | Water Pump | 20000 | 36775 | 2021-09-28 | 44852.3 | 2028-07-31 | 11922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 36775 | 2021-09-28 | 44852.3 | 2028-07-31 | 11922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1310 | Radiator | 20000 | 35260 | 2020-11-13 | 44852.3 | 2028-04-21 | 10407.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1420 | Air Compressor | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N1430 | Air Starter | 10000 | 44338 | 2023-12-20 | 44852.3 | 2028-02-19 | 9485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N2000 | Transmission | 20000 | 44338 | 2023-12-20 | 44852.3 | 2029-12-17 | 19485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 44338 | 2023-12-20 | 44852.3 | 2029-12-17 | 19485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N2004 | Transmission Pump | 20000 | 44338 | 2023-12-20 | 44852.3 | 2029-12-17 | 19485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N2050 | Torque Convertor | 20000 | 30677 | 2019-12-19 | 44852.3 | 2027-06-20 | 5824.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 34250 | 2020-09-05 | 44852.3 | 2028-02-14 | 9397.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 44634 | 2026-01-02 | 44852.3 | 2028-03-10 | 9781.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 25870 | 2018-01-02 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 36000 | 2021-01-07 | 44852.3 | 2026-08-13 | 1147.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N3320 | Pump Drive Box | 20000 | 25870 | 2018-12-31 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N4000 | Bevel Gear | 20000 | 36775 | 2021-09-27 | 44852.3 | 2028-07-31 | 11922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 25870 | 2017-12-30 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 31264 | 2020-02-12 | 44852.3 | 2027-07-29 | 6411.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 25870 | 2017-12-30 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 31264 | 2020-02-12 | 44852.3 | 2027-07-29 | 6411.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 25870 | 2018-01-05 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 25870 | 2018-01-05 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 33606 | 2020-07-21 | 44852.3 | 2028-01-02 | 8753.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 33606 | 2020-07-21 | 44852.3 | 2028-01-02 | 8753.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 25870 | 2017-12-31 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 42617 | 2023-02-19 | 44852.3 | 2027-10-28 | 7764.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 42617 | 2023-02-19 | 44852.3 | 2027-10-28 | 7764.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 42617 | 2023-02-19 | 44852.3 | 2027-10-28 | 7764.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 30677 | 2019-12-19 | 44852.3 | 2027-06-20 | 5824.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 30677 | 2019-12-19 | 44852.3 | 2027-06-20 | 5824.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 42617 | 2023-02-19 | 44852.3 | 2033-04-19 | 37764.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7120 | Pump Steering | 20000 | 41625 | 2022-11-08 | 44852.3 | 2029-06-19 | 16772.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 26486 | 2018-10-14 | 44852.3 | 2027-06-08 | 5633.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 35028.3 | 2020-10-23 | 44852.3 | 2028-12-28 | 14176 | WA | Duketon South Operations
RD4218 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 35697 | 2020-12-14 | 44852.3 | 2028-05-20 | 10844.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 35697 | 2020-12-15 | 44852.3 | 2028-05-20 | 10844.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7605 | Steering Hmu | 20000 | 25870 | 2017-12-31 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 44536 | 2026-01-12 | 44852.3 | 2029-12-30 | 19683.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 44536 | 2026-01-12 | 44852.3 | 2029-12-30 | 19683.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8000 | Main Frame/Chassis | 25000 | 44338 | 2023-12-20 | 44852.3 | 2030-11-15 | 24485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 25870 | 2018-01-05 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 25870 | 2018-01-04 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8140 | Steering Y Piece | 20000 | 25870 | 2018-01-02 | 44852.3 | 2026-08-04 | 1017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 44338 | 2023-12-20 | 44852.3 | 2029-12-17 | 19485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 36775 | 2021-10-02 | 44852.3 | 2028-07-31 | 11922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 27912 | 2019-03-18 | 44852.3 | 2026-12-18 | 3059.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 27912 | 2019-03-20 | 44852.3 | 2026-12-18 | 3059.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 25870 | 2018-01-04 | 44852.3 | 2027-07-03 | 6017.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8501 | Ball Stud Crack Test |  | 44630.1 | 2026-01-21 | 44852.3 | 2026-07-22 |  | WA | Duketon South Operations
RD4218 | Cat 785C | N8995 | Operator Seat | 6000 | 44338 | 2023-12-20 | 44852.3 | 2027-05-29 | 5485.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 44852.3 | 2022-10-13 | -19852.3 | WA | Duketon South Operations
RD4218 | Cat 785C | N9020 | Alternator | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 34249 | 2020-09-05 | 44852.3 | 2025-05-19 | -5603.3 | WA | Duketon South Operations
RD4218 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 29879 | 2019-09-19 | 44852.3 | 2027-04-28 | 5026.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N9501 | A/C Compressor | 10000 | 36775 | 2021-09-28 | 44852.3 | 2026-10-03 | 1922.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2010-09-02 | 44852.3 | 2026-06-07 | 147.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2010-09-02 | 44852.3 | 2030-01-30 | 20147.7 | WA | Duketon South Operations
RD4218 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2010-09-02 | 44852.3 | 2033-09-25 | 40147.7 | WA | Duketon South Operations
RD4219 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 39029 | 2025-11-11 | 39658.4 | 2030-11-10 |  | WA | Muchea
RD4219 | Cat 785C | N0200 | A Frame Bearing | 20000 | 39044 | 2023-12-20 | 39658.4 | 2029-12-10 | 19385.6 | WA | Muchea
RD4219 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 39044 | 2023-12-20 | 39658.4 | 2026-08-28 | 1385.6 | WA | Muchea
RD4219 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 22005 | 2019-02-11 | 39658.4 | 2026-10-31 | 2346.6 | WA | Muchea
RD4219 | Cat 785C | N1000 | Engine | 20000 | 30423.5 | 2020-12-09 | 39658.4 | 2028-05-15 | 10765.1 | WA | Muchea
RD4219 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 39044 | 2023-12-20 | 39658.4 | 2027-01-09 | 3385.6 | WA | Muchea
RD4219 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 30746 | 2021-01-28 | 39658.4 | 2024-10-14 | -8862.4 | WA | Muchea
RD4219 | Cat 785C | N1004 | Engine Midlife | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1301 | Water Pump | 20000 | 30423.5 | 2020-12-09 | 39658.4 | 2028-05-15 | 10765.1 | WA | Muchea
RD4219 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 30423.5 | 2020-12-09 | 39658.4 | 2028-05-15 | 10765.1 | WA | Muchea
RD4219 | Cat 785C | N1310 | Radiator | 20000 | 39659 | 2026-02-09 | 39658.4 | 2030-01-20 | 20000.6 | WA | Muchea
RD4219 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N1420 | Air Compressor | 10000 | 39505 | 2026-01-21 | 39658.4 | 2028-03-14 | 9846.6 | WA | Muchea
RD4219 | Cat 785C | N1430 | Air Starter | 10000 | 33107 | 2022-02-02 | 39658.4 | 2027-01-13 | 3448.6 | WA | Muchea
RD4219 | Cat 785C | N2000 | Transmission | 20000 | 22011 | 2019-02-17 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 22005 | 2019-02-11 | 39658.4 | 2026-10-31 | 2346.6 | WA | Muchea
RD4219 | Cat 785C | N2004 | Transmission Pump | 20000 | 22005 | 2019-02-06 | 39658.4 | 2026-10-31 | 2346.6 | WA | Muchea
RD4219 | Cat 785C | N2050 | Torque Convertor | 20000 | 23161 | 2019-05-21 | 39658.4 | 2027-01-17 | 3502.6 | WA | Muchea
RD4219 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 28639.1 | 2020-07-04 | 39658.4 | 2028-01-17 | 8980.7 | WA | Muchea
RD4219 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 36949 | 2023-02-16 | 39658.4 | 2027-09-26 | 7290.6 | WA | Muchea
RD4219 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 22011 | 2019-02-28 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 31605 | 2021-09-24 | 39658.4 | 2026-10-05 | 1946.6 | WA | Muchea
RD4219 | Cat 785C | N3320 | Pump Drive Box | 20000 | 22005 | 2019-02-11 | 39658.4 | 2026-10-31 | 2346.6 | WA | Muchea
RD4219 | Cat 785C | N4000 | Bevel Gear | 20000 | 22011 | 2019-02-17 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 22011 | 2019-02-17 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 22011 | 2019-02-17 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 22011 | 2019-02-16 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 22011 | 2019-02-17 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 39044 | 2023-12-20 | 39658.4 | 2029-12-10 | 19385.6 | WA | Muchea
RD4219 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 22011 | 2019-02-19 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 39044 | 2023-12-20 | 39658.4 | 2029-12-10 | 19385.6 | WA | Muchea
RD4219 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 22011 | 2019-02-19 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 25546 | 2019-11-22 | 39658.4 | 2027-06-25 | 5887.6 | WA | Muchea
RD4219 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 25546 | 2019-11-22 | 39658.4 | 2027-06-25 | 5887.6 | WA | Muchea
RD4219 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 22005 | 2019-02-11 | 39658.4 | 2026-10-31 | 2346.6 | WA | Muchea
RD4219 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 36949 | 2023-02-15 | 39658.4 | 2027-09-26 | 7290.6 | WA | Muchea
RD4219 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 36949 | 2023-02-15 | 39658.4 | 2027-09-26 | 7290.6 | WA | Muchea
RD4219 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 36949 | 2023-02-15 | 39658.4 | 2027-09-26 | 7290.6 | WA | Muchea
RD4219 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 23161 | 2019-05-21 | 39658.4 | 2027-01-17 | 3502.6 | WA | Muchea
RD4219 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 39044 | 2023-12-20 | 39658.4 | 2033-08-05 | 39385.6 | WA | Muchea
RD4219 | Cat 785C | N7120 | Pump Steering | 20000 | 29268 | 2020-02-22 | 39658.4 | 2028-02-28 | 9609.6 | WA | Muchea
RD4219 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 29426 | 2020-09-02 | 39658.4 | 2028-12-01 | 13767.6 | WA | Muchea
RD4219 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 39044 | 2023-12-20 | 39658.4 | 2030-09-03 | 23385.6 | WA | Muchea
RD4219 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 27905 | 2020-05-16 | 39658.4 | 2027-11-29 | 8246.6 | WA | Muchea
RD4219 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N7605 | Steering Hmu | 20000 | 25857 | 2019-12-20 | 39658.4 | 2027-07-15 | 6198.6 | WA | Muchea
RD4219 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 39469 | 2026-01-15 | 39658.4 | 2030-01-08 | 19810.6 | WA | Muchea
RD4219 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 39469 | 2026-01-15 | 39658.4 | 2030-01-08 | 19810.6 | WA | Muchea
RD4219 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 39658.4 | 2023-09-24 | -14658.4 | WA | Muchea
RD4219 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 39044 | 2023-12-20 | 39658.4 | 2029-12-10 | 19385.6 | WA | Muchea
RD4219 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 22011 | 2019-02-19 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8140 | Steering Y Piece | 20000 | 22011 | 2019-02-20 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 39044 | 2023-12-20 | 39658.4 | 2029-12-10 | 19385.6 | WA | Muchea
RD4219 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 36383 | 2023-01-19 | 39658.4 | 2029-06-16 | 16724.6 | WA | Muchea
RD4219 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 39044 | 2023-12-20 | 39658.4 | 2029-12-10 | 19385.6 | WA | Muchea
RD4219 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 30420 | 2020-11-03 | 39658.4 | 2028-05-14 | 10761.6 | WA | Muchea
RD4219 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 26992 | 2020-03-17 | 39658.4 | 2028-08-27 | 12333.6 | WA | Muchea
RD4219 | Cat 785C | N8501 | Ball Stud Crack Test |  | 39503.5 | 2026-01-20 | 39658.4 | 2026-07-21 |  | WA | Muchea
RD4219 | Cat 785C | N8995 | Operator Seat | 6000 | 39044 | 2023-12-20 | 39658.4 | 2027-05-22 | 5385.6 | WA | Muchea
RD4219 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 39658.4 | 2023-09-24 | -14658.4 | WA | Muchea
RD4219 | Cat 785C | N9020 | Alternator | 10000 | 39044 | 2023-12-20 | 39658.4 | 2028-02-13 | 9385.6 | WA | Muchea
RD4219 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 39044 | 2023-12-20 | 39658.4 | 2027-03-16 | 4385.6 | WA | Muchea
RD4219 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 22011 | 2019-02-16 | 39658.4 | 2026-11-01 | 2352.6 | WA | Muchea
RD4219 | Cat 785C | N9501 | A/C Compressor | 10000 | 22005 | 2019-02-11 | 39658.4 | 2025-01-03 | -7653.4 | WA | Muchea
RD4219 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2011-03-04 | 39658.4 | 2027-05-19 | 5341.6 | WA | Muchea
RD4219 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-03-04 | 39658.4 | 2031-01-11 | 25341.6 | WA | Muchea
RD4219 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-03-04 | 39658.4 | 2034-09-06 | 45341.6 | WA | Muchea
RD4220 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 34201 | 2022-03-04 | 52712 | 2027-03-03 |  | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N0200 | A Frame Bearing | 20000 | 48159 | 2025-05-07 | 52712 | 2029-06-24 | 15447 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 48159 | 2025-05-07 | 52712 | 2025-11-23 | -2553 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 45706 | 2024-09-16 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1000 | Engine | 20000 | 45706 | 2024-09-10 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 50341 | 2025-09-12 | 52712 | 2026-09-23 | 1629 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 45706 | 2024-09-10 | 52712 | 2025-01-07 | -6956 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1004 | Engine Midlife | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1301 | Water Pump | 20000 | 45706 | 2024-09-10 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 45706 | 2024-09-10 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1310 | Radiator | 20000 | 45706 | 2024-09-11 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1420 | Air Compressor | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N1430 | Air Starter | 10000 | 52655 | 2026-02-04 | 52712 | 2028-05-20 | 9943 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N2000 | Transmission | 20000 | 45047 | 2024-05-13 | 52712 | 2028-11-10 | 12335 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 45706 | 2024-09-08 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N2004 | Transmission Pump | 20000 | 45706 | 2024-09-08 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N2050 | Torque Convertor | 20000 | 38718 | 2023-01-24 | 52712 | 2027-08-08 | 6006 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 45706 | 2024-09-08 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 45706 | 2024-09-08 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 45047 | 2024-05-11 | 52712 | 2028-11-10 | 12335 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 45047 | 2024-05-11 | 52712 | 2026-11-14 | 2335 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N3320 | Pump Drive Box | 20000 | 45706 | 2024-09-08 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N4000 | Bevel Gear | 20000 | 45047 | 2024-05-10 | 52712 | 2028-11-10 | 12335 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 36585 | 2022-11-15 | 52712 | 2027-03-06 | 3873 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 45047 | 2024-05-12 | 52712 | 2028-11-10 | 12335 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 36586 | 2022-11-21 | 52712 | 2027-03-06 | 3874 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 47844 | 2025-04-11 | 52712 | 2029-06-02 | 15132 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 45701.7 | 2024-09-19 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 40010 | 2023-05-15 | 52712 | 2027-11-10 | 7298 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 45701.7 | 2024-09-19 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 40010 | 2023-05-15 | 52712 | 2027-11-10 | 7298 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 45706 | 2024-09-05 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 45706 | 2024-09-05 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 45706 | 2024-09-08 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 45706 | 2024-09-05 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 45706 | 2024-09-04 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 45706 | 2024-09-04 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 38718 | 2023-01-24 | 52712 | 2027-08-08 | 6006 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 45706 | 2024-09-08 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 40411 | 2023-06-15 | 52712 | 2031-12-02 | 27699 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7120 | Pump Steering | 20000 | 42062 | 2023-10-18 | 52712 | 2028-04-07 | 9350 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 30620 | 2020-06-09 | 52712 | 2026-10-14 | 1908 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 24006 | 2019-05-03 | 52712 | 2025-06-20 | -4706 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 48974 | 2025-06-24 | 52712 | 2029-08-23 | 16262 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 45701.7 | 2024-09-19 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7605 | Steering Hmu | 20000 | 34212 | 2022-03-04 | 52712 | 2026-09-14 | 1500 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 47129 | 2025-02-07 | 52712 | 2029-04-11 | 14417 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 47129 | 2025-02-07 | 52712 | 2029-04-11 | 14417 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 52712 | 2020-11-20 | -27712 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 45701.7 | 2024-09-19 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 40010 | 2023-05-15 | 52712 | 2027-11-10 | 7298 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 45706 | 2024-09-09 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 45706 | 2024-09-09 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 45701.7 | 2024-09-23 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 45701.7 | 2024-09-23 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 45706 | 2024-09-09 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 45701.7 | 2024-09-23 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8140 | Steering Y Piece | 20000 | 45701.7 | 2024-09-25 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 34212 | 2022-03-04 | 52712 | 2026-09-14 | 1500 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 45701.7 | 2024-09-20 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 34212 | 2022-03-04 | 52712 | 2026-09-14 | 1500 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 45701.7 | 2024-09-25 | 52712 | 2028-12-28 | 12989.7 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 45706 | 2024-09-14 | 52712 | 2029-12-27 | 17994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8501 | Ball Stud Crack Test |  | 52482 | 2026-01-21 | 52712 | 2026-07-22 |  | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8995 | Operator Seat | 6000 | 52655 | 2026-02-09 | 52712 | 2027-08-03 | 5943 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 52712 | 2020-11-20 | -27712 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9020 | Alternator | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 52186 | 2026-01-02 | 52712 | 2027-04-18 | 4474 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 45706 | 2024-09-17 | 52712 | 2028-12-28 | 12994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9501 | A/C Compressor | 10000 | 45706 | 2024-09-10 | 52712 | 2027-01-01 | 2994 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2011-03-04 | 52712 | 2024-11-13 | -7712 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-03-04 | 52712 | 2028-11-07 | 12288 | WA | Norrish Earthmoving Kalgoorlie
RD4220 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-03-04 | 52712 | 2032-10-31 | 32288 | WA | Norrish Earthmoving Kalgoorlie
RD4222 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 28979.4 | 2022-08-17 | 41444 | 2027-08-16 |  | WA | Hazelmere
RD4222 | Cat 785C | N0200 | A Frame Bearing | 20000 | 40801 | 2025-04-24 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 40801 | 2025-04-24 | 41444 | 2026-08-30 | 1357 | WA | Hazelmere
RD4222 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 40801 | 2025-04-21 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N1000 | Engine | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 40801 | 2025-04-28 | 41444 | 2027-01-15 | 3357 | WA | Hazelmere
RD4222 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 40947 | 2025-05-17 | 41444 | 2026-04-27 | -447 | WA | Hazelmere
RD4222 | Cat 785C | N1004 | Engine Midlife | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1301 | Water Pump | 20000 | 40801 | 2025-04-28 | 41444 | 2029-03-04 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N1310 | Radiator | 20000 | 40801 | 2025-04-29 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1420 | Air Compressor | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N1430 | Air Starter | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N2000 | Transmission | 20000 | 40801 | 2025-04-25 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 40801 | 2025-04-20 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N2004 | Transmission Pump | 20000 | 40801 | 2025-04-19 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N2050 | Torque Convertor | 20000 | 40801 | 2025-04-22 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 29075 | 2022-08-17 | 41444 | 2025-12-16 | -2369 | WA | Hazelmere
RD4222 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 40801 | 2025-04-26 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 40801 | 2025-04-26 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N3320 | Pump Drive Box | 20000 | 40801 | 2025-04-23 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N4000 | Bevel Gear | 20000 | 40801 | 2025-04-18 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 40801 | 2025-04-26 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 20445 | 2019-07-15 | 41444 | 2026-03-20 | -999 | WA | Hazelmere
RD4222 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 40801 | 2025-04-24 | 41444 | 2029-03-03 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 40801 | 2025-04-23 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 40801 | 2025-04-21 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 40801 | 2025-04-21 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 40801 | 2025-04-16 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 38025 | 2024-11-06 | 41444 | 2029-07-15 | 16581 | WA | Hazelmere
RD4222 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 40801 | 2025-04-17 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 40801 | 2025-04-22 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 40801 | 2025-04-22 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 40801 | 2025-04-22 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 40801 | 2025-04-22 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 40801 | 2025-04-22 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 40801 | 2025-04-28 | 41444 | 2033-11-01 | 39357 | WA | Hazelmere
RD4222 | Cat 785C | N7120 | Pump Steering | 20000 | 40801 | 2025-04-22 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 29075 | 2022-08-17 | 41444 | 2028-08-07 | 11631 | WA | Hazelmere
RD4222 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 29075 | 2022-08-19 | 41444 | 2028-08-07 | 11631 | WA | Hazelmere
RD4222 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 35445 | 2024-04-03 | 41444 | 2029-01-18 | 14001 | WA | Hazelmere
RD4222 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 40801 | 2025-04-29 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N7605 | Steering Hmu | 20000 | 29075 | 2022-08-17 | 41444 | 2027-11-05 | 7631 | WA | Hazelmere
RD4222 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 40801 | 2025-04-19 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 40801 | 2025-04-19 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 41444 | 2023-04-20 | -16444 | WA | Hazelmere
RD4222 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 40801 | 2025-04-21 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8140 | Steering Y Piece | 20000 | 40801 | 2025-04-27 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 40801 | 2025-04-18 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 27736 | 2020-11-10 | 41444 | 2027-08-05 | 6292 | WA | Hazelmere
RD4222 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 40801 | 2025-04-21 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 25887 | 2020-07-03 | 41444 | 2028-03-09 | 9443 | WA | Hazelmere
RD4222 | Cat 785C | N8501 | Ball Stud Crack Test |  | 28979.4 | 2022-08-17 | 41444 | 2023-02-15 |  | WA | Hazelmere
RD4222 | Cat 785C | N8995 | Operator Seat | 6000 | 34275 | 2024-01-05 | 41444 | 2026-03-08 | -1169 | WA | Hazelmere
RD4222 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 41444 | 2023-04-20 | -16444 | WA | Hazelmere
RD4222 | Cat 785C | N9020 | Alternator | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 40801 | 2025-04-28 | 41444 | 2027-03-24 | 4357 | WA | Hazelmere
RD4222 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 40801 | 2025-04-28 | 41444 | 2030-01-22 | 19357 | WA | Hazelmere
RD4222 | Cat 785C | N9501 | A/C Compressor | 10000 | 40801 | 2025-04-28 | 41444 | 2028-03-03 | 9357 | WA | Hazelmere
RD4222 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2011-03-04 | 41444 | 2027-01-28 | 3556 | WA | Hazelmere
RD4222 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-03-04 | 41444 | 2030-11-08 | 23556 | WA | Hazelmere
RD4222 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-03-04 | 41444 | 2034-08-18 | 43556 | WA | Hazelmere
RD4223 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 53950 | 2025-04-15 | 58874 | 2030-04-14 |  | WA | Norrish Earthmoving
RD4223 | Cat 785D | N0200 | A Frame Bearing | 20000 | 52228 | 2024-11-18 | 58874 | 2029-01-23 | 13354 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 55443 | 2025-07-16 | 58874 | 2026-02-13 | -1431 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N0520 | Pre Lube Pump | 20000 | 52547 | 2024-12-21 | 58874 | 2029-02-15 | 13673 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1000 | Engine | 20000 | 42466 | 2022-12-20 | 58874 | 2027-02-13 | 3592 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1002 | Engine Valve Adj | 4000 | 56311 | 2025-09-10 | 58874 | 2026-09-10 | 1437 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 50 | 42671 | 2023-01-04 | 58874 | 2023-03-10 | -16153 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1004 | Engine Midlife | 10000 | 52533 | 2024-12-14 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 52533 | 2024-12-14 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1100-LR | Turbo Primary LFT REAR | 10000 | 52533 | 2024-12-14 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 52533 | 2024-12-14 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1100-RR | Turbo Primary RHT REAR | 10000 | 52533 | 2024-12-14 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1202 | Fuel Transfer Pump | 10000 | 52533 | 2024-12-13 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1300 | Cooling Sys Service | 10000 | 52533 | 2024-12-15 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1301 | Water Pump | 10000 | 52533 | 2024-12-13 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1302 | Aftercooler Pump | 10000 | 52533 | 2024-12-17 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1310 | Radiator | 20000 | 42466 | 2022-12-20 | 58874 | 2027-02-13 | 3592 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1402 | Fan Pulley Brgs | 10000 | 52533 | 2024-12-17 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1403 | Jockey Pulley Brgs | 10000 | 52533 | 2024-12-17 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N1420 | Air Compressor | 10000 | 52533 | 2024-12-18 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N2000 | Transmission | 20000 | 44538 | 2023-05-05 | 58874 | 2027-07-14 | 5664 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N2002 | Oil Cooler - Transmission | 20000 | 42452 | 2022-11-29 | 58874 | 2027-02-12 | 3578 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N2004 | Transmission Pump | 20000 | 42466 | 2022-12-21 | 58874 | 2027-02-13 | 3592 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N2050 | Torque Convertor | 20000 | 50274 | 2024-06-26 | 58874 | 2028-09-03 | 11400 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 50896 | 2024-08-12 | 58874 | 2028-10-18 | 12022 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 50896 | 2024-08-15 | 58874 | 2026-10-22 | 2022 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 56655 | 2025-10-05 | 58874 | 2029-12-11 | 17781 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 56655 | 2025-10-05 | 58874 | 2027-12-15 | 7781 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N3320 | Pump Drive Box | 20000 | 42466 | 2022-12-20 | 58874 | 2027-02-13 | 3592 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N4000 | Bevel Gear | 20000 | 44538 | 2023-05-04 | 58874 | 2027-07-14 | 5664 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N4102-03 | Axle Shaft - POS 3 | 20000 | 44583 | 2023-05-04 | 58874 | 2027-07-17 | 5709 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N4102-04 | Axle Shaft - POS 4 | 20000 | 44583 | 2023-05-04 | 58874 | 2027-07-17 | 5709 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 44583 | 2023-05-05 | 58874 | 2027-07-17 | 5709 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 49710 | 2024-05-12 | 58874 | 2028-07-24 | 10836 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N5020-01 | Wheel Bearing POS 1 | 20000 | 44684 | 2023-05-17 | 58874 | 2027-07-25 | 5810 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N5020-02 | Wheel Bearing POS 2 | 20000 | 45571 | 2023-07-15 | 58874 | 2027-09-27 | 6697 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6000-01 | Brake POS 1 | 20000 | 44684 | 2023-05-17 | 58874 | 2027-07-25 | 5810 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6000-02 | Brake POS 2 | 20000 | 45571 | 2023-07-15 | 58874 | 2027-09-27 | 6697 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 20000 | 37813 | 2021-05-05 | 58874 | 2026-03-12 | -1061 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 37813 | 2021-05-05 | 58874 | 2026-03-12 | -1061 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 37813 | 2021-05-05 | 58874 | 2026-03-12 | -1061 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 | 37813 | 2021-05-05 | 58874 | 2026-03-12 | -1061 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6200-F | Press Converter FRONT | 10000 | 52533 | 2024-12-11 | 58874 | 2027-02-18 | 3659 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 10000 | 47147 | 2023-12-02 | 58874 | 2026-01-22 | -1727 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 10000 | 52057 | 2024-11-03 | 58874 | 2027-01-14 | 3183 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7037 | Pump Conv P/Brake Release | 20000 | 50274 | 2024-06-26 | 58874 | 2028-09-03 | 11400 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7065 | Pump Hoist/ Brk Cooling | 20000 | 50681 | 2024-07-22 | 58874 | 2028-10-03 | 11807 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7088 | Pump Park Brk Rel | 40000 | 42166 | 2022-10-24 | 58874 | 2031-01-16 | 23292 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7120 | Pump Steering | 20000 | 37813 | 2021-05-05 | 58874 | 2026-03-12 | -1061 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7160 | Pump Axle Lube/Cooler | 20000 | 42166 | 2022-10-23 | 58874 | 2027-01-22 | 3292 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 42166 | 2022-10-22 | 58874 | 2027-01-22 | 3292 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 20000 | 50519 | 2024-08-03 | 58874 | 2028-09-21 | 11645 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 20000 | 50519 | 2024-08-03 | 58874 | 2028-09-21 | 11645 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 42166 | 2022-10-23 | 58874 | 2027-01-22 | 3292 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 40006 | 2021-10-24 | 58874 | 2026-08-18 | 1132 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7605 | Steering Hmu | 20000 | 42166 | 2022-10-23 | 58874 | 2027-01-22 | 3292 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 20000 | 53953 | 2025-04-11 | 58874 | 2029-05-29 | 15079 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 20000 | 53933 | 2025-04-12 | 58874 | 2029-05-27 | 15059 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8000 | Main Frame/Chassis | 25000 |  |  | 58874 | 2019-08-29 | -33874 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8122-01 | Wheel Group POS 1 | 20000 | 44684 | 2023-05-17 | 58874 | 2027-07-25 | 5810 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8122-02 | Wheel Group POS 2 | 20000 | 45571 | 2023-07-15 | 58874 | 2027-09-27 | 6697 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 53180 | 2025-02-21 | 58874 | 2029-04-02 | 14306 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 53180 | 2025-02-21 | 58874 | 2029-04-02 | 14306 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 53180 | 2025-02-21 | 58874 | 2029-04-02 | 14306 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 53180 | 2025-02-21 | 58874 | 2029-04-02 | 14306 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8137-L | Steering Linkage Group LEFT | 20000 | 53180 | 2025-02-21 | 58874 | 2029-04-02 | 14306 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8137-R | Steering Linkage Group RIGHT | 20000 | 53180 | 2025-02-21 | 58874 | 2029-04-02 | 14306 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8140 | Steering Y Piece | 20000 | 42166 | 2022-10-23 | 58874 | 2027-01-22 | 3292 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8200-01 | Ride Strut POS 1 | 20000 | 46958 | 2023-10-31 | 58874 | 2028-01-06 | 8084 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8200-02 | Ride Strut POS 2 | 20000 | 45571 | 2023-07-15 | 58874 | 2027-09-27 | 6697 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8200-03 | Ride Strut POS 3 | 20000 | 34296 | 2020-08-04 | 58874 | 2025-06-29 | -4578 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8200-04 | Ride Strut POS 4 | 20000 | 40006 | 2021-10-25 | 58874 | 2026-08-18 | 1132 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8441 | Rear Axle Dog Bone | 25000 | 62917 | 2025-11-22 | 58874 | 2032-03-09 | 29043 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8501 | Ball Stud Crack Test |  | 58261 | 2026-01-21 | 58874 | 2026-07-22 |  | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8995 | Operator Seat | 6000 | 58875 | 2026-03-02 | 58874 | 2027-08-07 | 6001 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N8999 | Cab Upgrade | 25000 |  |  | 58874 | 2019-08-29 | -33874 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9020 | Alternator | 10000 | 58219 | 2025-01-11 | 58874 | 2028-04-07 | 9345 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9050-LW | Starter Motor LOWER | 10000 | 50543 | 2024-07-12 | 58874 | 2026-09-26 | 1669 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9050-UP | Starter Motor UPPER | 10000 | 50543 | 2024-07-12 | 58874 | 2026-09-26 | 1669 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9500 | Air Cond'r-Serv | 5000 | 52533 | 2024-12-17 | 58874 | 2026-02-19 | -1341 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 42466 | 2022-12-21 | 58874 | 2027-02-13 | 3592 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9501 | A/C Compressor | 10000 | 52548 | 2024-12-22 | 58874 | 2027-02-19 | 3674 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9998 | Extended Life Rebuild | 45000 |  | 2011-02-04 | 58874 | 2023-08-23 | -13874 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-02-04 | 58874 | 2027-08-17 | 6126 | WA | Norrish Earthmoving
RD4223 | Cat 785D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-02-04 | 58874 | 2031-08-10 | 26126 | WA | Norrish Earthmoving
RD4224 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 53205 | 2025-04-17 | 54402.5 | 2030-04-16 |  | WA | Hazelmere
RD4224 | Cat 785D | N0200 | A Frame Bearing | 20000 | 49137 | 2024-05-18 | 54402.5 | 2029-05-04 | 14734.5 | WA | Hazelmere
RD4224 | Cat 785D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 51994 | 2025-01-10 | 54402.5 | 2026-04-28 | -408.5 | WA | Hazelmere
RD4224 | Cat 785D | N0520 | Pre Lube Pump | 20000 | 43748 | 2023-04-29 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N1000 | Engine | 20000 | 43748 | 2023-05-04 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N1002 | Engine Valve Adj | 4000 | 52950 | 2025-03-27 | 54402.5 | 2026-11-29 | 2547.5 | WA | Hazelmere
RD4224 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 50 | 44185 | 2023-06-14 | 54402.5 | 2024-05-19 | -10167.5 | WA | Hazelmere
RD4224 | Cat 785D | N1004 | Engine Midlife | 10000 | 53784 | 2025-06-04 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 54074 | 2025-07-12 | 54402.5 | 2028-04-30 | 9671.5 | WA | Hazelmere
RD4224 | Cat 785D | N1100-LR | Turbo Primary LFT REAR | 10000 | 54074 | 2025-07-20 | 54402.5 | 2028-04-30 | 9671.5 | WA | Hazelmere
RD4224 | Cat 785D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 53784 | 2025-06-04 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1100-RR | Turbo Primary RHT REAR | 10000 | 53784 | 2025-06-04 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1202 | Fuel Transfer Pump | 10000 | 53784 | 2025-06-02 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1300 | Cooling Sys Service | 10000 | 53784 | 2025-06-06 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1301 | Water Pump | 10000 | 53784 | 2025-06-03 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1302 | Aftercooler Pump | 10000 | 53784 | 2025-06-04 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1310 | Radiator | 20000 | 43748 | 2023-04-29 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N1402 | Fan Pulley Brgs | 10000 | 53784 | 2025-06-05 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1403 | Jockey Pulley Brgs | 10000 | 53784 | 2025-06-05 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N1420 | Air Compressor | 10000 | 53784 | 2025-06-04 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N2000 | Transmission | 20000 | 40503 | 2022-09-18 | 54402.5 | 2027-08-15 | 6100.5 | WA | Hazelmere
RD4224 | Cat 785D | N2002 | Oil Cooler - Transmission | 20000 | 43905 | 2023-05-15 | 54402.5 | 2028-04-18 | 9502.5 | WA | Hazelmere
RD4224 | Cat 785D | N2004 | Transmission Pump | 20000 | 37702 | 2021-07-10 | 54402.5 | 2027-01-23 | 3299.5 | WA | Hazelmere
RD4224 | Cat 785D | N2050 | Torque Convertor | 20000 | 43748 | 2023-05-01 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 43748 | 2023-04-28 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 53784 | 2025-06-03 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 43748 | 2023-04-29 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 53784 | 2025-06-03 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N3320 | Pump Drive Box | 20000 | 43748 | 2023-04-27 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N4000 | Bevel Gear | 20000 | 40503 | 2022-09-18 | 54402.5 | 2027-08-15 | 6100.5 | WA | Hazelmere
RD4224 | Cat 785D | N4102-03 | Axle Shaft - POS 3 | 20000 | 43748 | 2023-04-26 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N4102-04 | Axle Shaft - POS 4 | 20000 | 43748 | 2023-04-26 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 43748 | 2023-04-26 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 43748 | 2023-04-27 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N5020-01 | Wheel Bearing POS 1 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N5020-02 | Wheel Bearing POS 2 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N6000-01 | Brake POS 1 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N6000-02 | Brake POS 2 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 20000 | 37483 | 2021-05-08 | 54402.5 | 2027-01-07 | 3080.5 | WA | Hazelmere
RD4224 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 37483 | 2021-05-08 | 54402.5 | 2027-01-07 | 3080.5 | WA | Hazelmere
RD4224 | Cat 785D | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 43748 | 2023-04-29 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 | 43748 | 2023-04-29 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N6200-F | Press Converter FRONT | 10000 | 49212 | 2024-05-27 | 54402.5 | 2027-05-13 | 4809.5 | WA | Hazelmere
RD4224 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 10000 | 49217 | 2024-05-27 | 54402.5 | 2027-05-13 | 4814.5 | WA | Hazelmere
RD4224 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 10000 | 49217 | 2024-05-27 | 54402.5 | 2027-05-13 | 4814.5 | WA | Hazelmere
RD4224 | Cat 785D | N7037 | Pump Conv P/Brake Release | 20000 | 43748 | 2023-05-01 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7065 | Pump Hoist/ Brk Cooling | 20000 | 43748 | 2023-04-27 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7088 | Pump Park Brk Rel | 40000 | 43748 | 2023-05-01 | 54402.5 | 2032-03-31 | 29345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7120 | Pump Steering | 20000 | 43748 | 2023-04-27 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7160 | Pump Axle Lube/Cooler | 20000 | 43748 | 2023-04-30 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 36836 | 2021-03-10 | 54402.5 | 2026-11-21 | 2433.5 | WA | Hazelmere
RD4224 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 20000 | 50725 | 2024-09-20 | 54402.5 | 2029-08-27 | 16322.5 | WA | Hazelmere
RD4224 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 20000 | 50725 | 2024-09-20 | 54402.5 | 2029-08-27 | 16322.5 | WA | Hazelmere
RD4224 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 43748 | 2023-05-01 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 43748 | 2023-05-01 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7605 | Steering Hmu | 20000 | 43748 | 2023-04-30 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 20000 | 53103 | 2025-04-07 | 54402.5 | 2030-02-16 | 18700.5 | WA | Hazelmere
RD4224 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 20000 | 53103 | 2025-04-07 | 54402.5 | 2030-02-16 | 18700.5 | WA | Hazelmere
RD4224 | Cat 785D | N8000 | Main Frame/Chassis | 25000 |  |  | 54402.5 | 2020-07-20 | -29402.5 | WA | Hazelmere
RD4224 | Cat 785D | N8122-01 | Wheel Group POS 1 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8122-02 | Wheel Group POS 2 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 43748 | 2023-05-03 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 43748 | 2023-05-03 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 43748 | 2023-05-04 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 43748 | 2023-05-04 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8137-L | Steering Linkage Group LEFT | 20000 | 43748 | 2023-05-03 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8137-R | Steering Linkage Group RIGHT | 20000 | 43748 | 2023-05-04 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8140 | Steering Y Piece | 20000 | 43748 | 2023-04-27 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8200-01 | Ride Strut POS 1 | 20000 | 51059.4 | 2024-10-11 | 54402.5 | 2029-09-20 | 16656.9 | WA | Hazelmere
RD4224 | Cat 785D | N8200-02 | Ride Strut POS 2 | 20000 | 43748 | 2023-05-02 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N8200-03 | Ride Strut POS 3 | 20000 | 51993 | 2025-01-15 | 54402.5 | 2029-11-27 | 17590.5 | WA | Hazelmere
RD4224 | Cat 785D | N8200-04 | Ride Strut POS 4 | 20000 | 44951 | 2023-08-05 | 54402.5 | 2028-07-03 | 10548.5 | WA | Hazelmere
RD4224 | Cat 785D | N8441 | Rear Axle Dog Bone | 25000 | 44562 | 2023-07-11 | 54402.5 | 2029-06-04 | 15159.5 | WA | Hazelmere
RD4224 | Cat 785D | N8501 | Ball Stud Crack Test |  | 54153.9 | 2025-07-17 | 54402.5 | 2026-01-15 |  | WA | Hazelmere
RD4224 | Cat 785D | N8995 | Operator Seat | 6000 | 51332 | 2024-11-10 | 54402.5 | 2026-12-27 | 2929.5 | WA | Hazelmere
RD4224 | Cat 785D | N8999 | Cab Upgrade | 25000 |  |  | 54402.5 | 2020-07-20 | -29402.5 | WA | Hazelmere
RD4224 | Cat 785D | N9020 | Alternator | 10000 | 53784 | 2025-06-06 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N9050-LW | Starter Motor LOWER | 10000 | 53784 | 2025-06-05 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N9050-UP | Starter Motor UPPER | 10000 | 53784 | 2025-06-05 | 54402.5 | 2028-04-09 | 9381.5 | WA | Hazelmere
RD4224 | Cat 785D | N9500 | Air Cond'r-Serv | 5000 | 53784 | 2025-06-05 | 54402.5 | 2027-04-12 | 4381.5 | WA | Hazelmere
RD4224 | Cat 785D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 43748 | 2023-05-03 | 54402.5 | 2028-04-07 | 9345.5 | WA | Hazelmere
RD4224 | Cat 785D | N9501 | A/C Compressor | 10000 | 53405 | 2025-05-11 | 54402.5 | 2028-03-13 | 9002.5 | WA | Hazelmere
RD4224 | Cat 785D | N9998 | Extended Life Rebuild | 45000 |  | 2011-08-05 | 54402.5 | 2024-07-13 | -9402.5 | WA | Hazelmere
RD4224 | Cat 785D | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-08-05 | 54402.5 | 2028-07-07 | 10597.5 | WA | Hazelmere
RD4224 | Cat 785D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-08-05 | 54402.5 | 2032-06-30 | 30597.5 | WA | Hazelmere
RD4225 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 56139.7 | 2025-04-17 | 60646.3 | 2030-04-16 |  | WA | Norrish Earthmoving
RD4225 | Cat 785D | N0200 | A Frame Bearing | 20000 | 59232 | 2025-11-21 | 60646.3 | 2030-02-08 | 18585.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 59232 | 2025-11-21 | 60646.3 | 2026-07-10 | 585.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N0520 | Pre Lube Pump | 20000 | 44883 | 2022-12-12 | 60646.3 | 2027-04-01 | 4236.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1000 | Engine | 20000 | 46144 | 2023-04-07 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1002 | Engine Valve Adj | 4000 | 58192 | 2025-09-01 | 60646.3 | 2026-09-17 | 1545.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 50 | 47042 | 2023-06-16 | 60646.3 | 2023-09-15 | -13554.3 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1004 | Engine Midlife | 10000 | 56274 | 2025-04-26 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 56274 | 2025-04-24 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1100-LR | Turbo Primary LFT REAR | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1100-RR | Turbo Primary RHT REAR | 10000 | 56274 | 2025-04-26 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1202 | Fuel Transfer Pump | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1300 | Cooling Sys Service | 10000 | 56274 | 2025-04-27 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1301 | Water Pump | 10000 | 56274 | 2025-04-26 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1302 | Aftercooler Pump | 10000 | 56274 | 2025-04-26 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1310 | Radiator | 20000 | 45169 | 2023-01-22 | 60646.3 | 2027-04-22 | 4522.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1402 | Fan Pulley Brgs | 10000 | 56471 | 2025-05-13 | 60646.3 | 2027-07-26 | 5824.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1403 | Jockey Pulley Brgs | 10000 | 56471 | 2025-05-13 | 60646.3 | 2027-07-26 | 5824.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N1420 | Air Compressor | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N2000 | Transmission | 20000 | 51576 | 2024-05-02 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N2002 | Oil Cooler - Transmission | 20000 | 51576 | 2024-05-02 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N2004 | Transmission Pump | 20000 | 51576 | 2024-05-02 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N2050 | Torque Convertor | 20000 | 46144 | 2023-04-17 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 41277 | 2021-07-06 | 60646.3 | 2026-07-13 | 630.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 51622 | 2024-05-05 | 60646.3 | 2026-08-07 | 975.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 45918 | 2023-03-19 | 60646.3 | 2027-06-15 | 5271.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N3320 | Pump Drive Box | 20000 | 46144 | 2023-04-08 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N4000 | Bevel Gear | 20000 | 59968 | 2026-01-10 | 60646.3 | 2030-04-02 | 19321.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N4102-03 | Axle Shaft - POS 3 | 20000 | 46144 | 2023-04-12 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N4102-04 | Axle Shaft - POS 4 | 20000 | 46144 | 2023-04-12 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 46144 | 2023-04-11 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 46144 | 2023-04-13 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N5020-01 | Wheel Bearing POS 1 | 20000 | 46144 | 2023-04-11 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N5020-02 | Wheel Bearing POS 2 | 20000 | 49080 | 2023-11-15 | 60646.3 | 2028-01-31 | 8433.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6000-01 | Brake POS 1 | 20000 | 46144 | 2023-04-11 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6000-02 | Brake POS 2 | 20000 | 49080 | 2023-11-15 | 60646.3 | 2028-01-31 | 8433.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 20000 | 41218 | 2021-05-15 | 60646.3 | 2026-07-09 | 571.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 41218 | 2021-05-15 | 60646.3 | 2026-07-09 | 571.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 46144 | 2023-04-08 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 | 56274 | 2025-04-26 | 60646.3 | 2029-07-08 | 15627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6200-F | Press Converter FRONT | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 10000 | 51601 | 2024-05-03 | 60646.3 | 2026-08-05 | 954.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 10000 | 51601 | 2024-05-03 | 60646.3 | 2026-08-05 | 954.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7037 | Pump Conv P/Brake Release | 20000 | 46138 | 2023-04-13 | 60646.3 | 2027-07-01 | 5491.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7065 | Pump Hoist/ Brk Cooling | 20000 | 46144 | 2023-04-07 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7088 | Pump Park Brk Rel | 40000 | 41218 | 2021-05-15 | 60646.3 | 2030-07-02 | 20571.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7120 | Pump Steering | 20000 | 46144 | 2023-04-06 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7160 | Pump Axle Lube/Cooler | 20000 | 46144 | 2023-04-06 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 46144 | 2023-04-06 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 20000 | 57421 | 2025-07-13 | 60646.3 | 2029-09-29 | 16774.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 20000 | 53741 | 2024-10-15 | 60646.3 | 2029-01-04 | 13094.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 56471 | 2025-05-11 | 60646.3 | 2029-07-22 | 15824.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 46144 | 2023-04-06 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7605 | Steering Hmu | 20000 | 46144 | 2023-04-08 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 20000 | 56274 | 2025-04-25 | 60646.3 | 2029-07-08 | 15627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 20000 | 56274 | 2025-04-25 | 60646.3 | 2029-07-08 | 15627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8000 | Main Frame/Chassis | 25000 |  |  | 60646.3 | 2019-04-23 | -35646.3 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8122-01 | Wheel Group POS 1 | 20000 | 46144 | 2023-04-11 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8122-02 | Wheel Group POS 2 | 20000 | 49080 | 2023-11-15 | 60646.3 | 2028-01-31 | 8433.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8137-L | Steering Linkage Group LEFT | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8137-R | Steering Linkage Group RIGHT | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8140 | Steering Y Piece | 20000 | 51576 | 2024-05-01 | 60646.3 | 2028-07-31 | 10929.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8200-01 | Ride Strut POS 1 | 20000 | 46144 | 2023-04-11 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8200-02 | Ride Strut POS 2 | 20000 | 46144 | 2023-04-11 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8200-03 | Ride Strut POS 3 | 20000 | 46144 | 2023-04-13 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8200-04 | Ride Strut POS 4 | 20000 | 35881 | 2020-06-04 | 60646.3 | 2025-06-15 | -4765.3 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8441 | Rear Axle Dog Bone | 25000 | 35253 | 2020-04-27 | 60646.3 | 2026-04-29 | -393.3 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8501 | Ball Stud Crack Test |  | 60078.7 | 2026-01-21 | 60646.3 | 2026-07-22 |  | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8995 | Operator Seat | 6000 | 59117 | 2025-11-07 | 60646.3 | 2027-04-18 | 4470.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N8999 | Cab Upgrade | 25000 |  |  | 60646.3 | 2019-04-23 | -35646.3 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9020 | Alternator | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9050-LW | Starter Motor LOWER | 10000 | 59824 | 2025-12-27 | 60646.3 | 2028-03-25 | 9177.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9050-UP | Starter Motor UPPER | 10000 | 51601 | 2024-05-04 | 60646.3 | 2026-08-05 | 954.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9500 | Air Cond'r-Serv | 5000 | 56274 | 2025-04-28 | 60646.3 | 2026-07-13 | 627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 46144 | 2023-04-13 | 60646.3 | 2027-07-02 | 5497.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9501 | A/C Compressor | 10000 | 56274 | 2025-04-25 | 60646.3 | 2027-07-11 | 5627.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9998 | Extended Life Rebuild | 45000 |  | 2011-08-05 | 60646.3 | 2023-04-16 | -15646.3 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2011-08-05 | 60646.3 | 2027-04-10 | 4353.7 | WA | Norrish Earthmoving
RD4225 | Cat 785D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2011-08-05 | 60646.3 | 2031-04-03 | 24353.7 | WA | Norrish Earthmoving
RD4231 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 30493 | 2021-03-24 | 39200 | 2026-03-23 |  | WA | Hazelmere
RD4231 | Cat 785D | N0200 | A Frame Bearing | 20000 | 21159 | 2018-06-14 | 39200 | 2026-10-15 | 1959 | WA | Hazelmere
RD4231 | Cat 785D | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 21159.1 | 2018-06-14 | 39200 | 2023-04-08 | -16040.9 | WA | Hazelmere
RD4231 | Cat 785D | N0520 | Pre Lube Pump | 20000 | 34840 | 2021-08-10 | 39200 | 2029-06-18 | 15640 | WA | Hazelmere
RD4231 | Cat 785D | N1000 | Engine | 20000 | 26979 | 2020-01-12 | 39200 | 2027-12-05 | 7779 | WA | Hazelmere
RD4231 | Cat 785D | N1002 | Engine Valve Adj | 4000 | 30756 | 2020-10-03 | 39200 | 2025-07-15 | -4444 | WA | Hazelmere
RD4231 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 50 | 27089 | 2020-01-28 | 39200 | 2024-01-17 | -12061 | WA | Hazelmere
RD4231 | Cat 785D | N1004 | Engine Midlife | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1100-LF | Turbo Primary LFT FRONT | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1100-LR | Turbo Primary LFT REAR | 10000 | 30756 | 2020-10-06 | 39200 | 2026-09-16 | 1556 | WA | Hazelmere
RD4231 | Cat 785D | N1100-RF | Turbo Primary RHT FRONT | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1100-RR | Turbo Primary RHT REAR | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1202 | Fuel Transfer Pump | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1300 | Cooling Sys Service | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1301 | Water Pump | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1302 | Aftercooler Pump | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1310 | Radiator | 20000 | 25175 | 2019-07-18 | 39200 | 2027-07-29 | 5975 | WA | Hazelmere
RD4231 | Cat 785D | N1402 | Fan Pulley Brgs | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1403 | Jockey Pulley Brgs | 10000 | 35359 | 2021-10-01 | 39200 | 2027-08-11 | 6159 | WA | Hazelmere
RD4231 | Cat 785D | N1420 | Air Compressor | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N1430 | Air Starter | 20000 | 35875 | 2021-11-11 | 39200 | 2029-08-31 | 16675 | WA | Hazelmere
RD4231 | Cat 785D | N2000 | Transmission | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N2002 | Oil Cooler - Transmission | 20000 | 21747 | 2018-10-06 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N2004 | Transmission Pump | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N2050 | Torque Convertor | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 27697 | 2020-03-13 | 39200 | 2028-01-25 | 8497 | WA | Hazelmere
RD4231 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 38385 | 2023-03-20 | 39200 | 2028-03-14 | 9185 | WA | Hazelmere
RD4231 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 21747 | 2018-09-25 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 32284 | 2021-01-22 | 39200 | 2027-01-03 | 3084 | WA | Hazelmere
RD4231 | Cat 785D | N3320 | Pump Drive Box | 20000 | 21747 | 2018-09-24 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N4000 | Bevel Gear | 20000 | 21747 | 2018-09-24 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N4102-03 | Axle Shaft - POS 3 | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N4102-04 | Axle Shaft - POS 4 | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 34381 | 2021-07-08 | 39200 | 2029-05-16 | 15181 | WA | Hazelmere
RD4231 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N5020-01 | Wheel Bearing POS 1 | 20000 | 29850 | 2020-08-06 | 39200 | 2028-06-27 | 10650 | WA | Hazelmere
RD4231 | Cat 785D | N5020-02 | Wheel Bearing POS 2 | 20000 | 34053 | 2021-06-08 | 39200 | 2029-04-23 | 14853 | WA | Hazelmere
RD4231 | Cat 785D | N6000-01 | Brake POS 1 | 20000 | 29850 | 2020-08-06 | 39200 | 2028-06-27 | 10650 | WA | Hazelmere
RD4231 | Cat 785D | N6000-02 | Brake POS 2 | 20000 | 34053 | 2021-06-08 | 39200 | 2029-04-23 | 14853 | WA | Hazelmere
RD4231 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 20000 | 33870 | 2021-05-22 | 39200 | 2029-04-10 | 14670 | WA | Hazelmere
RD4231 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 33868 | 2021-05-21 | 39200 | 2029-04-10 | 14668 | WA | Hazelmere
RD4231 | Cat 785D | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 21747 | 2018-10-06 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 | 21747 | 2018-10-06 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N6200-F | Press Converter FRONT | 10000 | 33870 | 2021-05-22 | 39200 | 2027-04-27 | 4670 | WA | Hazelmere
RD4231 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 10000 | 33868 | 2021-05-21 | 39200 | 2027-04-26 | 4668 | WA | Hazelmere
RD4231 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 10000 | 33868 | 2021-05-22 | 39200 | 2027-04-26 | 4668 | WA | Hazelmere
RD4231 | Cat 785D | N7037 | Pump Conv P/Brake Release | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7065 | Pump Hoist/ Brk Cooling | 20000 | 21747 | 2018-09-25 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7088 | Pump Park Brk Rel | 40000 |  |  | 39200 | 2026-07-24 | 800 | WA | Hazelmere
RD4231 | Cat 785D | N7120 | Pump Steering | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7160 | Pump Axle Lube/Cooler | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7169 | Hyd Mtr Axle Lube/Cooler | 20000 | 21747 | 2018-09-23 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 20000 | 21747 | 2018-09-21 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 20000 | 21747 | 2018-09-20 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 31218 | 2020-11-04 | 39200 | 2028-10-02 | 12018 | WA | Hazelmere
RD4231 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 28519 | 2020-05-06 | 39200 | 2028-03-24 | 9319 | WA | Hazelmere
RD4231 | Cat 785D | N7605 | Steering Hmu | 20000 | 21747 | 2018-09-26 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 20000 | 21747 | 2018-09-27 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 20000 | 21747 | 2018-09-26 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8000 | Main Frame/Chassis | 25000 |  |  | 39200 | 2021-06-10 | -14200 | WA | Hazelmere
RD4231 | Cat 785D | N8122-01 | Wheel Group POS 1 | 20000 | 29850 | 2020-08-06 | 39200 | 2028-06-27 | 10650 | WA | Hazelmere
RD4231 | Cat 785D | N8122-02 | Wheel Group POS 2 | 20000 | 34053 | 2021-06-08 | 39200 | 2029-04-23 | 14853 | WA | Hazelmere
RD4231 | Cat 785D | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 21747 | 2018-10-04 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 21747 | 2018-10-04 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 21747 | 2018-10-05 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 21747 | 2018-10-05 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8137-L | Steering Linkage Group LEFT | 20000 | 21747 | 2018-10-04 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8137-R | Steering Linkage Group RIGHT | 20000 | 21747 | 2018-10-05 | 39200 | 2026-11-26 | 2547 | WA | Hazelmere
RD4231 | Cat 785D | N8140 | Steering Y Piece | 20000 | 34912 | 2021-08-13 | 39200 | 2029-06-23 | 15712 | WA | Hazelmere
RD4231 | Cat 785D | N8200-01 | Ride Strut POS 1 | 20000 | 34625 | 2021-07-27 | 39200 | 2029-06-03 | 15425 | WA | Hazelmere
RD4231 | Cat 785D | N8200-02 | Ride Strut POS 2 | 20000 | 18270 | 2017-12-17 | 39200 | 2026-03-23 | -930 | WA | Hazelmere
RD4231 | Cat 785D | N8200-03 | Ride Strut POS 3 | 20000 | 28525 | 2020-05-09 | 39200 | 2028-03-24 | 9325 | WA | Hazelmere
RD4231 | Cat 785D | N8200-04 | Ride Strut POS 4 | 20000 | 31218 | 2020-11-05 | 39200 | 2028-10-02 | 12018 | WA | Hazelmere
RD4231 | Cat 785D | N8441 | Rear Axle Dog Bone | 25000 | 24000 | 2019-04-16 | 39200 | 2028-04-27 | 9800 | WA | Hazelmere
RD4231 | Cat 785D | N8501 | Ball Stud Crack Test |  | 35922 | 2022-08-17 | 39200 | 2023-02-15 |  | WA | Hazelmere
RD4231 | Cat 785D | N8995 | Operator Seat | 6000 | 32849 | 2021-03-07 | 39200 | 2026-05-03 | -351 | WA | Hazelmere
RD4231 | Cat 785D | N8999 | Cab Upgrade | 25000 |  |  | 39200 | 2023-08-18 | -14200 | WA | Hazelmere
RD4231 | Cat 785D | N9020 | Alternator | 10000 | 35926 | 2022-08-17 | 39200 | 2027-09-20 | 6726 | WA | Hazelmere
RD4231 | Cat 785D | N9500 | Air Cond'r-Serv | 5000 | 35926 | 2022-08-17 | 39200 | 2026-09-28 | 1726 | WA | Hazelmere
RD4231 | Cat 785D | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 21743 | 2018-09-11 | 39200 | 2026-11-26 | 2543 | WA | Hazelmere
RD4231 | Cat 785D | N9501 | A/C Compressor | 10000 | 30081 | 2020-08-22 | 39200 | 2026-07-30 | 881 | WA | Hazelmere
RD4231 | Cat 785D | N9998 | Extended Life Rebuild | 45000 |  | 2013-12-17 | 39200 | 2027-07-16 | 5800 | WA | Hazelmere
RD4231 | Cat 785D | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2013-12-17 | 39200 | 2031-06-14 | 25800 | WA | Hazelmere
RD4231 | Cat 785D | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2013-12-17 | 39200 | 2035-05-12 | 45800 | WA | Hazelmere
RD4235 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 63637 | 2026-03-20 | 63637 | 2031-03-19 |  | WA | Karlawinda
RD4235 | Cat 789C | N0200 | A Frame Bearing | 20000 | 58846 | 2022-09-15 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 58846.1 | 2022-09-15 | 63637 | 2025-11-10 | -2790.9 | WA | Karlawinda
RD4235 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 58845 | 2022-09-29 | 63637 | 2029-05-18 | 15208 | WA | Karlawinda
RD4235 | Cat 789C | N1000 | Engine | 20000 | 58846 | 2022-09-29 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 58846 | 2022-09-29 | 63637 | 2026-04-01 | -791 | WA | Karlawinda
RD4235 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 58846 | 2022-09-29 | 63637 | 2025-06-23 | -4741 | WA | Karlawinda
RD4235 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 58846 | 2022-09-20 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1310 | Radiator | 20000 | 55040 | 2021-08-29 | 63637 | 2028-08-20 | 11403 | WA | Karlawinda
RD4235 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N1430 | Air Starter | 20000 | 58846 | 2022-09-05 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N2000 | Transmission | 20000 | 64075 | 2026-03-20 | 63637 | 2030-05-27 | 20438 | WA | Karlawinda
RD4235 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 64075 | 2026-03-20 | 63637 | 2030-05-27 | 20438 | WA | Karlawinda
RD4235 | Cat 789C | N2004 | Transmission Pump | 20000 | 54045 | 2021-08-03 | 63637 | 2028-06-09 | 10408 | WA | Karlawinda
RD4235 | Cat 789C | N2050 | Torque Convertor | 20000 | 52412 | 2021-04-03 | 63637 | 2028-02-14 | 8775 | WA | Karlawinda
RD4235 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 58845 | 2022-09-29 | 63637 | 2029-05-18 | 15208 | WA | Karlawinda
RD4235 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 58845 | 2022-09-29 | 63637 | 2027-06-04 | 5208 | WA | Karlawinda
RD4235 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 52412 | 2021-04-03 | 63637 | 2028-02-14 | 8775 | WA | Karlawinda
RD4235 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 58845 | 2022-09-29 | 63637 | 2027-06-04 | 5208 | WA | Karlawinda
RD4235 | Cat 789C | N3320 | Pump Drive Box | 20000 | 58845 | 2022-09-22 | 63637 | 2029-05-18 | 15208 | WA | Karlawinda
RD4235 | Cat 789C | N4000 | Bevel Gear | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 58846 | 2022-08-30 | 63637 | 2029-05-05 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 58846 | 2022-08-30 | 63637 | 2029-05-05 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 49772 | 2020-10-10 | 63637 | 2027-08-09 | 6135 | WA | Karlawinda
RD4235 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 49772 | 2020-10-10 | 63637 | 2027-08-09 | 6135 | WA | Karlawinda
RD4235 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 58846 | 2022-09-16 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 58846 | 2022-09-05 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 58846 | 2022-09-05 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 58846 | 2022-09-05 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 52926 | 2021-05-17 | 63637 | 2028-03-22 | 9289 | WA | Karlawinda
RD4235 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 49772 | 2020-10-10 | 63637 | 2026-10-28 | 2135 | WA | Karlawinda
RD4235 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 38927 | 2018-05-01 | 63637 | 2029-05-24 | 15290 | WA | Karlawinda
RD4235 | Cat 789C | N7120 | Pump Steering | 20000 | 58846 | 2022-09-22 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 45852 | 2020-02-18 | 63637 | 2027-08-15 | 6215 | WA | Karlawinda
RD4235 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 58846 | 2022-10-11 | 63637 | 2030-02-28 | 19209 | WA | Karlawinda
RD4235 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 58846 | 2022-08-23 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N7605 | Steering Hmu | 20000 | 58846 | 2022-09-22 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 64075 | 2026-03-18 | 63637 | 2030-05-27 | 20438 | WA | Karlawinda
RD4235 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 64075 | 2026-03-18 | 63637 | 2030-05-27 | 20438 | WA | Karlawinda
RD4235 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 63637 | 2018-11-06 | -38637 | WA | Karlawinda
RD4235 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 58846 | 2022-08-30 | 63637 | 2029-05-05 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 58845 | 2022-08-23 | 63637 | 2029-05-18 | 15208 | WA | Karlawinda
RD4235 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 58845 | 2022-08-23 | 63637 | 2029-05-18 | 15208 | WA | Karlawinda
RD4235 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 58846 | 2022-08-23 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 58846 | 2022-08-23 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 58845 | 2022-08-23 | 63637 | 2029-05-18 | 15208 | WA | Karlawinda
RD4235 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 58846 | 2022-08-23 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N8140 | Steering Y Piece | 20000 | 58846 | 2022-08-23 | 63637 | 2029-05-18 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 58846 | 2022-08-30 | 63637 | 2029-05-05 | 15209 | WA | Karlawinda
RD4235 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 54568 | 2021-07-31 | 63637 | 2028-07-17 | 10931 | WA | Karlawinda
RD4235 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 58846 | 2022-09-14 | 63637 | 2031-05-03 | 25209 | WA | Karlawinda
RD4235 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 64075 | 2026-03-18 | 63637 | 2032-05-10 | 30438 | WA | Karlawinda
RD4235 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 64075 | 2026-03-20 | 63637 | 2029-06-04 | 15438 | WA | Karlawinda
RD4235 | Cat 789C | N8501 | Ball Stud Crack Test |  | 63637 | 2026-03-20 | 63637 | 2026-09-18 |  | WA | Karlawinda
RD4235 | Cat 789C | N8995 | Operator Seat | 6000 | 58546 | 2022-10-04 | 63637 | 2026-08-01 | 909 | WA | Karlawinda
RD4235 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 63637 | 2025-09-10 | -3637 | WA | Karlawinda
RD4235 | Cat 789C | N9020 | Alternator | 10000 | 64065 | 2026-02-02 | 63637 | 2028-06-11 | 10428 | WA | Karlawinda
RD4235 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 58860 | 2023-05-10 | 63637 | 2026-06-13 | 223 | WA | Karlawinda
RD4235 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 58860 | 2023-05-10 | 63637 | 2029-05-19 | 15223 | WA | Karlawinda
RD4235 | Cat 789C | N9501 | A/C Compressor | 10000 | 58846 | 2022-09-29 | 63637 | 2027-06-04 | 5209 | WA | Karlawinda
RD4235 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 14565 | 2013-12-17 | 63637 | 2028-07-17 | 10928 | WA | Karlawinda
RD4235 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 7515 | 2013-12-17 | 63637 | 2030-02-04 | 18878 | WA | Karlawinda
RD4240 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 62557 | 2023-10-03 | 64653 | 2028-10-01 |  | WA | Hazelmere
RD4240 | Cat 789C | N0200 | A Frame Bearing | 20000 | 53905 | 2021-10-11 | 64653 | 2028-03-19 | 9252 | WA | Hazelmere
RD4240 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 53905.1 | 2021-10-11 | 64653 | 2024-09-10 | -8747.9 | WA | Hazelmere
RD4240 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 54155 | 2021-10-15 | 64653 | 2028-04-06 | 9502 | WA | Hazelmere
RD4240 | Cat 789C | N1000 | Engine | 20000 | 62475 | 2023-12-01 | 64653 | 2029-11-21 | 17822 | WA | Hazelmere
RD4240 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 62475 | 2023-12-01 | 64653 | 2026-08-21 | 1822 | WA | Hazelmere
RD4240 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 62475 | 2023-12-01 | 64653 | 2025-12-27 | -2128 | WA | Hazelmere
RD4240 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1310 | Radiator | 20000 | 62475 | 2023-10-10 | 64653 | 2029-11-21 | 17822 | WA | Hazelmere
RD4240 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N1430 | Air Starter | 20000 | 41128 | 2019-11-30 | 64653 | 2025-09-18 | -3525 | WA | Hazelmere
RD4240 | Cat 789C | N2000 | Transmission | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N2004 | Transmission Pump | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N2050 | Torque Convertor | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 58880 | 2022-07-03 | 64653 | 2027-02-19 | 4227 | WA | Hazelmere
RD4240 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 58880 | 2022-07-04 | 64653 | 2027-03-26 | 4227 | WA | Hazelmere
RD4240 | Cat 789C | N3320 | Pump Drive Box | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N4000 | Bevel Gear | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 58222 | 2022-05-15 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 58222 | 2022-05-15 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 49595 | 2021-03-17 | 64653 | 2026-06-11 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 48250 | 2020-12-25 | 64653 | 2027-02-09 | 3597 | WA | Hazelmere
RD4240 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 62475 | 2023-10-10 | 64653 | 2029-11-21 | 17822 | WA | Hazelmere
RD4240 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 58880 | 2022-07-04 | 64653 | 2027-03-26 | 4227 | WA | Hazelmere
RD4240 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 58880 | 2022-07-04 | 64653 | 2027-03-26 | 4227 | WA | Hazelmere
RD4240 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 58880 | 2022-07-04 | 64653 | 2027-03-26 | 4227 | WA | Hazelmere
RD4240 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 62475 | 2023-12-01 | 64653 | 2029-02-08 | 13822 | WA | Hazelmere
RD4240 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 31922 | 2018-02-05 | 64653 | 2027-10-29 | 7269 | WA | Hazelmere
RD4240 | Cat 789C | N7120 | Pump Steering | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 43213 | 2020-03-18 | 64653 | 2026-11-27 | 2560 | WA | Hazelmere
RD4240 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 45861 | 2020-08-17 | 64653 | 2027-06-04 | 5208 | WA | Hazelmere
RD4240 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 58222 | 2022-05-15 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 58222 | 2022-05-15 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N7605 | Steering Hmu | 20000 | 50801 | 2021-05-16 | 64653 | 2027-08-10 | 6148 | WA | Hazelmere
RD4240 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 50801 | 2021-05-16 | 64653 | 2027-07-07 | 6148 | WA | Hazelmere
RD4240 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 50801 | 2021-05-16 | 64653 | 2027-08-10 | 6148 | WA | Hazelmere
RD4240 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 64653 | 2018-08-26 | -39653 | WA | Hazelmere
RD4240 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 58222 | 2022-05-14 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 58222 | 2022-05-14 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 58222 | 2022-05-14 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 58222 | 2022-05-14 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 58222 | 2022-05-14 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 58222 | 2022-05-14 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8140 | Steering Y Piece | 20000 | 58222 | 2022-05-15 | 64653 | 2029-01-21 | 13569 | WA | Hazelmere
RD4240 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 49595 | 2021-03-17 | 64653 | 2027-05-16 | 4942 | WA | Hazelmere
RD4240 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 62475 | 2023-10-10 | 64653 | 2031-11-05 | 27822 | WA | Hazelmere
RD4240 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 62472 | 2023-10-10 | 64653 | 2031-11-05 | 27819 | WA | Hazelmere
RD4240 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 62475 | 2023-10-10 | 64653 | 2028-11-29 | 12822 | WA | Hazelmere
RD4240 | Cat 789C | N8501 | Ball Stud Crack Test |  | 62557 | 2023-12-01 | 64653 | 2024-05-31 |  | WA | Hazelmere
RD4240 | Cat 789C | N8995 | Operator Seat | 6000 | 62475 | 2023-12-01 | 64653 | 2027-02-25 | 3822 | WA | Hazelmere
RD4240 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 64653 | 2025-06-30 | -4653 | WA | Hazelmere
RD4240 | Cat 789C | N9020 | Alternator | 10000 | 62475 | 2023-10-10 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 62475 | 2023-12-01 | 64653 | 2026-12-16 | 2822 | WA | Hazelmere
RD4240 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 62475 | 2023-12-01 | 64653 | 2029-11-21 | 17822 | WA | Hazelmere
RD4240 | Cat 789C | N9501 | A/C Compressor | 10000 | 62475 | 2023-12-01 | 64653 | 2027-12-08 | 7822 | WA | Hazelmere
RD4240 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 14004 | 2013-12-17 | 64653 | 2028-03-26 | 9351 | WA | Hazelmere
RD4240 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 7354 | 2013-12-17 | 64653 | 2029-11-12 | 17701 | WA | Hazelmere
RD4241 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 58065 | 2024-03-04 | 58852 | 2029-03-03 |  | WA | Hazelmere
RD4241 | Cat 789C | N0200 | A Frame Bearing | 20000 | 58529 | 2024-03-04 | 58852 | 2029-12-30 | 19677 | WA | Hazelmere
RD4241 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 58529 | 2024-03-04 | 58852 | 2026-09-17 | 1677 | WA | Hazelmere
RD4241 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 58529 | 2024-03-04 | 58852 | 2029-12-30 | 19677 | WA | Hazelmere
RD4241 | Cat 789C | N1000 | Engine | 20000 | 41876 | 2019-07-16 | 58852 | 2026-12-16 | 3024 | WA | Hazelmere
RD4241 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 41876 | 2019-07-16 | 58852 | 2024-01-14 | -12976 | WA | Hazelmere
RD4241 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 41876 | 2019-07-16 | 58852 | 2023-04-26 | -16926 | WA | Hazelmere
RD4241 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 48889 | 2020-10-07 | 58852 | 2026-05-30 | 37 | WA | Hazelmere
RD4241 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1310 | Radiator | 20000 | 37906 | 2018-08-24 | 58852 | 2026-03-26 | -946 | WA | Hazelmere
RD4241 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N1430 | Air Starter | 20000 | 41876 | 2019-07-16 | 58852 | 2026-12-16 | 3024 | WA | Hazelmere
RD4241 | Cat 789C | N2000 | Transmission | 20000 | 51805 | 2021-04-27 | 58852 | 2028-10-08 | 12953 | WA | Hazelmere
RD4241 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 51805 | 2021-04-27 | 58852 | 2028-10-08 | 12953 | WA | Hazelmere
RD4241 | Cat 789C | N2004 | Transmission Pump | 20000 | 51805 | 2021-04-27 | 58852 | 2028-10-08 | 12953 | WA | Hazelmere
RD4241 | Cat 789C | N2050 | Torque Convertor | 20000 | 51805 | 2021-04-27 | 58852 | 2028-10-08 | 12953 | WA | Hazelmere
RD4241 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 41425 | 2019-05-09 | 58852 | 2026-11-16 | 2573 | WA | Hazelmere
RD4241 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 40608 | 2019-03-29 | 58852 | 2026-09-22 | 1756 | WA | Hazelmere
RD4241 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 51805 | 2021-04-27 | 58852 | 2026-12-11 | 2953 | WA | Hazelmere
RD4241 | Cat 789C | N3320 | Pump Drive Box | 20000 | 58529 | 2024-03-04 | 58852 | 2029-12-30 | 19677 | WA | Hazelmere
RD4241 | Cat 789C | N4000 | Bevel Gear | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 51672 | 2021-04-11 | 58852 | 2028-09-29 | 12820 | WA | Hazelmere
RD4241 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 51672 | 2021-04-11 | 58852 | 2028-09-29 | 12820 | WA | Hazelmere
RD4241 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 48328 | 2020-08-23 | 58852 | 2028-02-19 | 9476 | WA | Hazelmere
RD4241 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 48328 | 2020-08-23 | 58852 | 2028-02-19 | 9476 | WA | Hazelmere
RD4241 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 51805 | 2021-04-27 | 58852 | 2028-10-08 | 12953 | WA | Hazelmere
RD4241 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 58529 | 2022-03-21 | 58852 | 2028-03-03 | 9677 | WA | Hazelmere
RD4241 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 58529 | 2022-03-21 | 58852 | 2028-03-03 | 9677 | WA | Hazelmere
RD4241 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 58529 | 2022-03-21 | 58852 | 2028-03-03 | 9677 | WA | Hazelmere
RD4241 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 58534 | 2025-04-10 | 58852 | 2029-12-30 | 19682 | WA | Hazelmere
RD4241 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 67934 | 2022-03-21 | 58852 | 2030-12-25 | 25082 | WA | Hazelmere
RD4241 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 35809 | 2018-04-12 | 58852 | 2029-07-01 | 16957 | WA | Hazelmere
RD4241 | Cat 789C | N7120 | Pump Steering | 20000 | 58529 | 2024-03-04 | 58852 | 2029-12-30 | 19677 | WA | Hazelmere
RD4241 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 58530 | 2024-04-10 | 58852 | 2030-09-23 | 23678 | WA | Hazelmere
RD4241 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 58534 | 2024-04-10 | 58852 | 2030-09-23 | 23682 | WA | Hazelmere
RD4241 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 57934 | 2022-03-20 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N7605 | Steering Hmu | 20000 | 58529 | 2024-03-04 | 58852 | 2029-12-30 | 19677 | WA | Hazelmere
RD4241 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 41876 | 2019-07-16 | 58852 | 2026-12-16 | 3024 | WA | Hazelmere
RD4241 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 41876 | 2019-07-16 | 58852 | 2026-12-16 | 3024 | WA | Hazelmere
RD4241 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 58852 | 2020-03-23 | -33852 | WA | Hazelmere
RD4241 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 53535 | 2021-07-25 | 58852 | 2029-01-31 | 14683 | WA | Hazelmere
RD4241 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 51672 | 2021-04-11 | 58852 | 2028-09-29 | 12820 | WA | Hazelmere
RD4241 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8140 | Steering Y Piece | 20000 | 57934 | 2022-03-21 | 58852 | 2029-11-20 | 19082 | WA | Hazelmere
RD4241 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 42584 | 2019-10-07 | 58852 | 2027-02-01 | 3732 | WA | Hazelmere
RD4241 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 49103 | 2020-10-21 | 58852 | 2028-04-07 | 10251 | WA | Hazelmere
RD4241 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 48914 | 2020-09-29 | 58852 | 2030-01-24 | 20062 | WA | Hazelmere
RD4241 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 58529 | 2023-04-04 | 58852 | 2031-10-27 | 29677 | WA | Hazelmere
RD4241 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 53535 | 2021-07-25 | 58852 | 2028-03-04 | 9683 | WA | Hazelmere
RD4241 | Cat 789C | N8501 | Ball Stud Crack Test |  | 58065 | 2023-07-07 | 58852 | 2024-01-05 |  | WA | Hazelmere
RD4241 | Cat 789C | N8995 | Operator Seat | 6000 | 58529 | 2024-03-04 | 58852 | 2027-06-10 | 5677 | WA | Hazelmere
RD4241 | Cat 789C | N8999 | Cab Upgrade | 60000 | 35809 | 2018-04-12 | 58852 | 2033-02-24 | 36957 | WA | Hazelmere
RD4241 | Cat 789C | N9020 | Alternator | 10000 | 41876 | 2019-07-16 | 58852 | 2025-02-17 | -6976 | WA | Hazelmere
RD4241 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 58529 | 2024-03-04 | 58852 | 2027-04-05 | 4677 | WA | Hazelmere
RD4241 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 58529 | 2024-03-04 | 58852 | 2029-12-30 | 19677 | WA | Hazelmere
RD4241 | Cat 789C | N9501 | A/C Compressor | 10000 | 41254 | 2019-05-09 | 58852 | 2025-01-06 | -7598 | WA | Hazelmere
RD4241 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 14295 | 2013-12-17 | 58852 | 2029-03-23 | 15443 | WA | Hazelmere
RD4241 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 7445 | 2013-12-17 | 58852 | 2030-09-17 | 23593 | WA | Hazelmere
RD4242 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 55769 | 2024-03-04 | 56457 | 2029-03-03 |  | WA | Muchea Yard
RD4242 | Cat 789C | N0200 | A Frame Bearing | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 55883 | 2024-03-04 | 56457 | 2026-08-07 | 1426 | WA | Muchea Yard
RD4242 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N1000 | Engine | 20000 | 39521 | 2019-03-12 | 56457 | 2027-01-02 | 3064 | WA | Muchea Yard
RD4242 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 38163 | 2018-11-25 | 56457 | 2023-08-11 | -14294 | WA | Muchea Yard
RD4242 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 39521 | 2019-03-12 | 56457 | 2023-02-07 | -16886 | WA | Muchea Yard
RD4242 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 51802 | 2021-03-19 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1310 | Radiator | 20000 | 39521 | 2019-03-12 | 56457 | 2027-01-02 | 3064 | WA | Muchea Yard
RD4242 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 51802 | 2021-03-17 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 51808 | 2021-03-17 | 56457 | 2027-06-14 | 5351 | WA | Muchea Yard
RD4242 | Cat 789C | N1430 | Air Starter | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N2000 | Transmission | 20000 | 44992 | 2020-02-16 | 56457 | 2028-01-28 | 8535 | WA | Muchea Yard
RD4242 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 44992 | 2020-02-16 | 56457 | 2028-01-28 | 8535 | WA | Muchea Yard
RD4242 | Cat 789C | N2004 | Transmission Pump | 20000 | 44992 | 2020-02-16 | 56457 | 2028-01-28 | 8535 | WA | Muchea Yard
RD4242 | Cat 789C | N2050 | Torque Convertor | 20000 | 54460 | 2021-08-19 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 39521 | 2019-03-15 | 56457 | 2027-01-02 | 3064 | WA | Muchea Yard
RD4242 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 51802 | 2021-03-22 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 55883 | 2024-03-04 | 56457 | 2028-03-31 | 9426 | WA | Muchea Yard
RD4242 | Cat 789C | N3320 | Pump Drive Box | 20000 | 39506 | 2019-03-12 | 56457 | 2027-01-01 | 3049 | WA | Muchea Yard
RD4242 | Cat 789C | N4000 | Bevel Gear | 20000 | 51802 | 2021-03-20 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 51802 | 2021-03-21 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 51802 | 2021-03-20 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 51802 | 2021-03-22 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 51802 | 2021-03-21 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 51802 | 2021-03-22 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 51802 | 2021-03-22 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 50986 | 2021-01-30 | 56457 | 2029-03-31 | 14529 | WA | Muchea Yard
RD4242 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 51802 | 2021-03-19 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 51802 | 2021-03-19 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 39292 | 2019-02-12 | 56457 | 2026-12-17 | 2835 | WA | Muchea Yard
RD4242 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 51802 | 2021-03-18 | 56457 | 2027-06-14 | 5345 | WA | Muchea Yard
RD4242 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 54460 | 2021-08-19 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 51802 | 2021-03-19 | 56457 | 2028-08-15 | 11345 | WA | Muchea Yard
RD4242 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 34793 | 2018-04-12 | 56457 | 2029-12-28 | 18336 | WA | Muchea Yard
RD4242 | Cat 789C | N7120 | Pump Steering | 20000 | 47478 | 2020-09-03 | 56457 | 2028-07-23 | 11021 | WA | Muchea Yard
RD4242 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 34793 | 2018-05-02 | 56457 | 2026-11-11 | 2336 | WA | Muchea Yard
RD4242 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 55883 | 2024-03-04 | 56457 | 2030-12-26 | 23426 | WA | Muchea Yard
RD4242 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N7605 | Steering Hmu | 20000 | 54460 | 2021-08-14 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 55883 | 2024-03-04 | 56457 | 2030-02-13 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 55883 | 2024-03-04 | 56457 | 2030-02-13 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 56457 | 2020-04-02 | -31457 | WA | Muchea Yard
RD4242 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 51802 | 2021-03-22 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 50986 | 2021-01-30 | 56457 | 2029-03-31 | 14529 | WA | Muchea Yard
RD4242 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8140 | Steering Y Piece | 20000 | 54460 | 2021-08-15 | 56457 | 2029-12-04 | 18003 | WA | Muchea Yard
RD4242 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 51802 | 2021-03-23 | 56457 | 2029-05-28 | 15345 | WA | Muchea Yard
RD4242 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 39423 | 2019-02-28 | 56457 | 2028-12-09 | 12966 | WA | Muchea Yard
RD4242 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 39521 | 2019-03-19 | 56457 | 2028-12-16 | 13064 | WA | Muchea Yard
RD4242 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 55769 | 2022-07-02 | 56457 | 2029-03-15 | 14312 | WA | Muchea Yard
RD4242 | Cat 789C | N8501 | Ball Stud Crack Test |  | 55769 | 2022-08-28 | 56457 | 2023-02-26 |  | WA | Muchea Yard
RD4242 | Cat 789C | N8995 | Operator Seat | 6000 | 55883 | 2024-03-04 | 56457 | 2027-06-20 | 5426 | WA | Muchea Yard
RD4242 | Cat 789C | N8999 | Cab Upgrade | 60000 | 34793 | 2018-04-12 | 56457 | 2033-11-25 | 38336 | WA | Muchea Yard
RD4242 | Cat 789C | N9020 | Alternator | 10000 | 55883 | 2024-03-04 | 56457 | 2028-03-31 | 9426 | WA | Muchea Yard
RD4242 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 55883 | 2024-03-04 | 56457 | 2027-04-09 | 4426 | WA | Muchea Yard
RD4242 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 55883 | 2024-03-04 | 56457 | 2030-03-16 | 19426 | WA | Muchea Yard
RD4242 | Cat 789C | N9501 | A/C Compressor | 10000 | 55883 | 2024-03-04 | 56457 | 2028-03-31 | 9426 | WA | Muchea Yard
RD4242 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 13919 | 2013-12-17 | 56457 | 2029-10-26 | 17462 | WA | Muchea Yard
RD4242 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 7669 | 2013-12-17 | 56457 | 2031-07-13 | 26212 | WA | Muchea Yard
RD4243 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 35915 | 2018-05-02 | 64230 | 2023-05-01 |  | WA | Hazelmere
RD4243 | Cat 789C | N0200 | A Frame Bearing | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 64242 | 2026-03-26 | 64230 | 2026-10-19 | 2012 | WA | Hazelmere
RD4243 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N1000 | Engine | 20000 | 60781 | 2024-03-03 | 64230 | 2029-08-22 | 16551 | WA | Hazelmere
RD4243 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 63400 | 2024-10-17 | 64230 | 2027-01-09 | 3170 | WA | Hazelmere
RD4243 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 60781 | 2024-03-03 | 64230 | 2025-09-27 | -3399 | WA | Hazelmere
RD4243 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1310 | Radiator | 20000 | 53654 | 2022-09-23 | 64230 | 2028-03-31 | 9424 | WA | Hazelmere
RD4243 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N1430 | Air Starter | 20000 | 59350 | 2023-10-29 | 64230 | 2029-05-12 | 15120 | WA | Hazelmere
RD4243 | Cat 789C | N2000 | Transmission | 20000 | 60439 | 2024-01-23 | 64230 | 2029-07-29 | 16209 | WA | Hazelmere
RD4243 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 60439 | 2024-01-23 | 64230 | 2029-07-29 | 16209 | WA | Hazelmere
RD4243 | Cat 789C | N2004 | Transmission Pump | 20000 | 60439 | 2024-01-23 | 64230 | 2029-07-29 | 16209 | WA | Hazelmere
RD4243 | Cat 789C | N2050 | Torque Convertor | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 60439 | 2024-01-23 | 64230 | 2029-07-29 | 16209 | WA | Hazelmere
RD4243 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 60439 | 2024-01-23 | 64230 | 2027-08-15 | 6209 | WA | Hazelmere
RD4243 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 53474 | 2022-07-15 | 64230 | 2026-03-25 | -756 | WA | Hazelmere
RD4243 | Cat 789C | N3320 | Pump Drive Box | 20000 | 60439 | 2024-01-23 | 64230 | 2029-07-29 | 16209 | WA | Hazelmere
RD4243 | Cat 789C | N4000 | Bevel Gear | 20000 | 50104 | 2021-04-25 | 64230 | 2027-07-22 | 5874 | WA | Hazelmere
RD4243 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 58688 | 2023-09-13 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 58688 | 2023-09-13 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 63288 | 2024-10-07 | 64230 | 2030-02-17 | 19058 | WA | Hazelmere
RD4243 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 63288 | 2024-10-07 | 64230 | 2030-02-17 | 19058 | WA | Hazelmere
RD4243 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 45537 | 2020-07-19 | 64230 | 2026-08-29 | 1307 | WA | Hazelmere
RD4243 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 45537 | 2020-07-19 | 64230 | 2026-08-29 | 1307 | WA | Hazelmere
RD4243 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 56210 | 2023-03-21 | 64230 | 2026-10-16 | 1980 | WA | Hazelmere
RD4243 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 56210 | 2024-03-21 | 64230 | 2026-10-16 | 1980 | WA | Hazelmere
RD4243 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 56210 | 2024-03-21 | 64230 | 2026-10-16 | 1980 | WA | Hazelmere
RD4243 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 50490 | 2021-05-20 | 64230 | 2026-11-05 | 2260 | WA | Hazelmere
RD4243 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 33695 | 2018-05-02 | 64230 | 2028-04-03 | 9465 | WA | Hazelmere
RD4243 | Cat 789C | N7120 | Pump Steering | 20000 | 58688 | 2023-09-13 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 49220 | 2021-03-17 | 64230 | 2028-02-29 | 8990 | WA | Hazelmere
RD4243 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 48532 | 2021-01-17 | 64230 | 2028-01-11 | 8302 | WA | Hazelmere
RD4243 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 58688 | 2023-09-11 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N7605 | Steering Hmu | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-08 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-08 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-08 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 64230 | 2018-09-25 | -39230 | WA | Hazelmere
RD4243 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 63288 | 2024-10-07 | 64230 | 2030-02-17 | 19058 | WA | Hazelmere
RD4243 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8140 | Steering Y Piece | 20000 | 58688 | 2023-09-12 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 58688 | 2023-09-14 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 58688 | 2023-09-14 | 64230 | 2029-03-26 | 14458 | WA | Hazelmere
RD4243 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 53474 | 2022-07-15 | 64230 | 2030-03-03 | 19244 | WA | Hazelmere
RD4243 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 53608 | 2022-09-12 | 64230 | 2030-03-12 | 19378 | WA | Hazelmere
RD4243 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 53474 | 2022-07-15 | 64230 | 2027-03-27 | 4244 | WA | Hazelmere
RD4243 | Cat 789C | N8501 | Ball Stud Crack Test |  | 53391 | 2022-07-15 | 64230 | 2023-01-13 |  | WA | Hazelmere
RD4243 | Cat 789C | N8995 | Operator Seat | 6000 | 53474 | 2022-07-15 | 64230 | 2025-06-12 | -4756 | WA | Hazelmere
RD4243 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 64230 | 2025-07-30 | -4230 | WA | Hazelmere
RD4243 | Cat 789C | N9020 | Alternator | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 58688 | 2023-09-14 | 64230 | 2026-04-09 | -542 | WA | Hazelmere
RD4243 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 53474 | 2022-07-15 | 64230 | 2028-03-18 | 9244 | WA | Hazelmere
RD4243 | Cat 789C | N9501 | A/C Compressor | 10000 | 60781 | 2024-03-03 | 64230 | 2027-09-08 | 6551 | WA | Hazelmere
RD4243 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 13341 | 2013-12-17 | 64230 | 2028-03-09 | 9111 | WA | Hazelmere
RD4243 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 7241 | 2013-12-17 | 64230 | 2029-12-05 | 18011 | WA | Hazelmere
RD4244 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 41697 | 2019-04-23 | 67187 | 2024-04-21 |  | WA | Hazelmere
RD4244 | Cat 789C | N0200 | A Frame Bearing | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 55435.1 | 2022-04-24 | 67187 | 2024-06-30 | -9751.9 | WA | Hazelmere
RD4244 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N1000 | Engine | 20000 | 51608 | 2021-01-17 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 60679 | 2023-08-23 | 67187 | 2025-11-30 | -2508 | WA | Hazelmere
RD4244 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 51608 | 2021-01-17 | 67187 | 2023-05-15 | -15529 | WA | Hazelmere
RD4244 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1310 | Radiator | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N1430 | Air Starter | 20000 | 51608 | 2021-01-17 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N2000 | Transmission | 20000 | 46133 | 2020-02-04 | 67187 | 2026-03-14 | -1054 | WA | Hazelmere
RD4244 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 52552 | 2021-03-30 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N2004 | Transmission Pump | 20000 | 46133 | 2020-02-04 | 67187 | 2026-03-14 | -1054 | WA | Hazelmere
RD4244 | Cat 789C | N2050 | Torque Convertor | 20000 | 46133 | 2020-02-04 | 67187 | 2026-03-14 | -1054 | WA | Hazelmere
RD4244 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 52552 | 2021-04-01 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N3320 | Pump Drive Box | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N4000 | Bevel Gear | 20000 | 52552 | 2021-04-01 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 52552 | 2021-04-01 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 52552 | 2021-04-01 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 52552 | 2021-04-01 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 52552 | 2021-04-01 | 67187 | 2027-06-15 | 5365 | WA | Hazelmere
RD4244 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 47198 | 2020-05-01 | 67187 | 2026-05-29 | 11 | WA | Hazelmere
RD4244 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 47198 | 2020-05-01 | 67187 | 2026-05-29 | 11 | WA | Hazelmere
RD4244 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 51608 | 2021-01-20 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 64666 | 2024-04-27 | 67187 | 2029-01-15 | 13479 | WA | Hazelmere
RD4244 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 34375 | 2014-08-05 | 67187 | 2027-10-23 | 7188 | WA | Hazelmere
RD4244 | Cat 789C | N7120 | Pump Steering | 20000 | 47198 | 2020-04-19 | 67187 | 2026-05-29 | 11 | WA | Hazelmere
RD4244 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 47111 | 2020-09-02 | 67187 | 2027-03-04 | 3924 | WA | Hazelmere
RD4244 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 46532 | 2020-03-09 | 67187 | 2027-01-22 | 3345 | WA | Hazelmere
RD4244 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 49576 | 2020-04-19 | 67187 | 2026-11-15 | 2389 | WA | Hazelmere
RD4244 | Cat 789C | N7605 | Steering Hmu | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 67187 | 2018-02-26 | -42187 | WA | Hazelmere
RD4244 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 47198 | 2020-05-01 | 67187 | 2026-05-29 | 11 | WA | Hazelmere
RD4244 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8140 | Steering Y Piece | 20000 | 64666 | 2024-04-27 | 67187 | 2029-10-28 | 17479 | WA | Hazelmere
RD4244 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 51608 | 2021-01-19 | 67187 | 2027-04-09 | 4421 | WA | Hazelmere
RD4244 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 60326 | 2024-03-02 | 67187 | 2028-12-22 | 13139 | WA | Hazelmere
RD4244 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 40057 | 2019-01-08 | 67187 | 2026-12-19 | 2870 | WA | Hazelmere
RD4244 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 40057 | 2019-01-08 | 67187 | 2026-12-19 | 2870 | WA | Hazelmere
RD4244 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 55435 | 2022-04-24 | 67187 | 2027-01-15 | 3248 | WA | Hazelmere
RD4244 | Cat 789C | N8501 | Ball Stud Crack Test |  | 55428 | 2022-04-24 | 67187 | 2022-10-23 |  | WA | Hazelmere
RD4244 | Cat 789C | N8995 | Operator Seat | 6000 | 56622 | 2022-12-20 | 67187 | 2025-07-06 | -4565 | WA | Hazelmere
RD4244 | Cat 789C | N8999 | Cab Upgrade | 60000 | 35990 | 2018-04-09 | 67187 | 2032-01-14 | 28803 | WA | Hazelmere
RD4244 | Cat 789C | N9020 | Alternator | 10000 | 61097 | 2023-09-23 | 67187 | 2027-03-03 | 3910 | WA | Hazelmere
RD4244 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 61097 | 2023-09-23 | 67187 | 2026-03-11 | -1090 | WA | Hazelmere
RD4244 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 55435 | 2022-04-24 | 67187 | 2028-01-07 | 8248 | WA | Hazelmere
RD4244 | Cat 789C | N9501 | A/C Compressor | 10000 | 51608 | 2021-01-17 | 67187 | 2025-04-24 | -5579 | WA | Hazelmere
RD4244 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 14028 | 2013-12-17 | 67187 | 2027-09-29 | 6841 | WA | Hazelmere
RD4244 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 7328 | 2013-12-17 | 67187 | 2029-05-14 | 15141 | WA | Hazelmere
RD4245 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 51116 | 2022-08-18 | 55805 | 2027-08-17 |  | WA | Muchea Yard
RD4245 | Cat 789C | N0200 | A Frame Bearing | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 42993.1 | 2020-07-14 | 55805 | 2024-04-16 | -10811.9 | WA | Muchea Yard
RD4245 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N1000 | Engine | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 51122 | 2022-05-07 | 55805 | 2026-04-09 | -683 | WA | Muchea Yard
RD4245 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 42993 | 2020-07-14 | 55805 | 2023-11-28 | -12762 | WA | Muchea Yard
RD4245 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 53263 | 2023-11-05 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 52742 | 2023-10-03 | 55805 | 2027-10-06 | 6937 | WA | Muchea Yard
RD4245 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 53263 | 2023-11-06 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 53263 | 2023-11-06 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 53263 | 2023-11-06 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 53263 | 2023-11-07 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1310 | Radiator | 20000 | 42993 | 2020-07-08 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 53263 | 2023-11-06 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 53263 | 2023-11-06 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N1430 | Air Starter | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N2000 | Transmission | 20000 | 55250 | 2024-04-26 | 55805 | 2030-03-17 | 19445 | WA | Muchea Yard
RD4245 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 55250 | 2024-04-25 | 55805 | 2030-03-17 | 19445 | WA | Muchea Yard
RD4245 | Cat 789C | N2004 | Transmission Pump | 20000 | 55250 | 2024-04-26 | 55805 | 2030-03-17 | 19445 | WA | Muchea Yard
RD4245 | Cat 789C | N2050 | Torque Convertor | 20000 | 42993 | 2020-07-06 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 53263 | 2023-11-06 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 39522 | 2019-12-06 | 55805 | 2027-02-18 | 3717 | WA | Muchea Yard
RD4245 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 51122 | 2022-08-18 | 55805 | 2027-06-12 | 5317 | WA | Muchea Yard
RD4245 | Cat 789C | N3320 | Pump Drive Box | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N4000 | Bevel Gear | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 53263 | 2023-11-06 | 55805 | 2029-10-26 | 17458 | WA | Muchea Yard
RD4245 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 53263 | 2023-11-08 | 55805 | 2029-10-26 | 17458 | WA | Muchea Yard
RD4245 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 53263 | 2023-11-07 | 55805 | 2029-10-26 | 17458 | WA | Muchea Yard
RD4245 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 53263 | 2023-11-07 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 53263 | 2023-11-07 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 53263 | 2023-11-07 | 55805 | 2027-11-12 | 7458 | WA | Muchea Yard
RD4245 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 42993 | 2020-07-06 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 53263 | 2023-11-05 | 55805 | 2029-01-13 | 13458 | WA | Muchea Yard
RD4245 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 31532 | 2018-05-01 | 55805 | 2029-06-24 | 15727 | WA | Muchea Yard
RD4245 | Cat 789C | N7120 | Pump Steering | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 51122 | 2022-08-18 | 55805 | 2030-03-08 | 19317 | WA | Muchea Yard
RD4245 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 41397 | 2020-03-25 | 55805 | 2028-04-12 | 9592 | WA | Muchea Yard
RD4245 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 48815 | 2021-06-28 | 55805 | 2028-12-12 | 13010 | WA | Muchea Yard
RD4245 | Cat 789C | N7605 | Steering Hmu | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 51145 | 2022-09-07 | 55805 | 2029-05-28 | 15340 | WA | Muchea Yard
RD4245 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 51145 | 2022-09-09 | 55805 | 2029-05-28 | 15340 | WA | Muchea Yard
RD4245 | Cat 789C | N8000 | Main Frame/Chassis | 25000 |  |  | 55805 | 2020-05-19 | -30805 | WA | Muchea Yard
RD4245 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 42926 | 2020-07-14 | 55805 | 2027-10-19 | 7121 | WA | Muchea Yard
RD4245 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 42926 | 2020-07-14 | 55805 | 2027-10-19 | 7121 | WA | Muchea Yard
RD4245 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 42993 | 2020-07-14 | 55805 | 2027-10-23 | 7188 | WA | Muchea Yard
RD4245 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 42926 | 2020-07-14 | 55805 | 2027-10-19 | 7121 | WA | Muchea Yard
RD4245 | Cat 789C | N8140 | Steering Y Piece | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 37234 | 2019-06-29 | 55805 | 2026-09-07 | 1429 | WA | Muchea Yard
RD4245 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 35141 | 2019-02-03 | 55805 | 2028-03-25 | 9336 | WA | Muchea Yard
RD4245 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 35141 | 2019-02-02 | 55805 | 2028-03-25 | 9336 | WA | Muchea Yard
RD4245 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 51122 | 2022-08-18 | 55805 | 2028-06-03 | 10317 | WA | Muchea Yard
RD4245 | Cat 789C | N8501 | Ball Stud Crack Test |  | 51116 | 2022-08-18 | 55805 | 2023-02-16 |  | WA | Muchea Yard
RD4245 | Cat 789C | N8995 | Operator Seat | 6000 | 51122 | 2022-08-18 | 55805 | 2026-08-30 | 1317 | WA | Muchea Yard
RD4245 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 55805 | 2027-03-24 | 4195 | WA | Muchea Yard
RD4245 | Cat 789C | N9020 | Alternator | 10000 | 42993 | 2020-07-14 | 55805 | 2025-11-08 | -2812 | WA | Muchea Yard
RD4245 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 51122 | 2022-08-18 | 55805 | 2026-06-20 | 317 | WA | Muchea Yard
RD4245 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 51122 | 2022-08-18 | 55805 | 2029-05-26 | 15317 | WA | Muchea Yard
RD4245 | Cat 789C | N9501 | A/C Compressor | 10000 | 51116 | 2021-11-27 | 55805 | 2027-06-11 | 5311 | WA | Muchea Yard
RD4245 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 12866 | 2013-12-17 | 55805 | 2029-09-28 | 17061 | WA | Muchea Yard
RD4245 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 6916 | 2013-12-17 | 55805 | 2031-07-06 | 26111 | WA | Muchea Yard
RD4248 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 57617 | 2024-07-08 | 57617 | 2029-07-07 |  | WA | Karlawinda
RD4248 | Cat 789C | N0200 | A Frame Bearing | 20000 | 57650 | 2024-05-26 | 57617 | 2029-02-23 | 20033 | WA | Karlawinda
RD4248 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 57650 | 2024-05-26 | 57617 | 2026-09-07 | 2033 | WA | Karlawinda
RD4248 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 48260 | 2021-09-15 | 57617 | 2027-11-11 | 10643 | WA | Karlawinda
RD4248 | Cat 789C | N1000 | Engine | 20000 | 40962 | 2020-09-10 | 57617 | 2026-11-11 | 3345 | WA | Karlawinda
RD4248 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 57650 | 2024-05-23 | 57617 | 2026-12-16 | 4033 | WA | Karlawinda
RD4248 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 41049 | 2020-09-15 | 57617 | 2024-02-22 | -16518 | WA | Karlawinda
RD4248 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 51906 | 2022-03-14 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 51906 | 2022-03-15 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 51906 | 2022-03-17 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 51906 | 2022-03-16 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 51906 | 2022-03-16 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 51906 | 2022-03-16 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1310 | Radiator | 20000 | 40962 | 2020-09-10 | 57617 | 2026-11-11 | 3345 | WA | Karlawinda
RD4248 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 51906 | 2022-03-20 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 51906 | 2022-03-20 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N1430 | Air Starter | 20000 | 40962 | 2020-09-10 | 57617 | 2026-11-11 | 3345 | WA | Karlawinda
RD4248 | Cat 789C | N2000 | Transmission | 20000 | 57474 | 2022-12-25 | 57617 | 2029-02-14 | 19857 | WA | Karlawinda
RD4248 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 57474 | 2022-12-25 | 57617 | 2029-02-14 | 19857 | WA | Karlawinda
RD4248 | Cat 789C | N2004 | Transmission Pump | 20000 | 57474 | 2022-12-25 | 57617 | 2029-02-14 | 19857 | WA | Karlawinda
RD4248 | Cat 789C | N2050 | Torque Convertor | 20000 | 57650 | 2024-05-15 | 57617 | 2029-02-23 | 20033 | WA | Karlawinda
RD4248 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 40962 | 2020-09-10 | 57617 | 2026-11-11 | 3345 | WA | Karlawinda
RD4248 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 51906 | 2022-03-21 | 57617 | 2026-12-28 | 4289 | WA | Karlawinda
RD4248 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 57650 | 2024-05-22 | 57617 | 2029-02-23 | 20033 | WA | Karlawinda
RD4248 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 57650 | 2024-05-22 | 57617 | 2027-10-12 | 10033 | WA | Karlawinda
RD4248 | Cat 789C | N3320 | Pump Drive Box | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N4000 | Bevel Gear | 20000 | 48256 | 2021-09-15 | 57617 | 2027-11-11 | 10639 | WA | Karlawinda
RD4248 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 48260 | 2021-09-15 | 57617 | 2027-11-11 | 10643 | WA | Karlawinda
RD4248 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 48260 | 2021-09-15 | 57617 | 2027-11-11 | 10643 | WA | Karlawinda
RD4248 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 48260 | 2021-09-15 | 57617 | 2027-11-11 | 10643 | WA | Karlawinda
RD4248 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 48260 | 2021-09-15 | 57617 | 2027-11-11 | 10643 | WA | Karlawinda
RD4248 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 57560 | 2024-05-16 | 57617 | 2029-02-18 | 19943 | WA | Karlawinda
RD4248 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 57650 | 2024-05-23 | 57617 | 2029-02-23 | 20033 | WA | Karlawinda
RD4248 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 57560 | 2024-05-16 | 57617 | 2029-02-18 | 19943 | WA | Karlawinda
RD4248 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 51906 | 2022-03-18 | 57617 | 2028-05-11 | 14289 | WA | Karlawinda
RD4248 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 46820 | 2021-06-14 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 57650 | 2024-06-10 | 57617 | 2029-02-23 | 20033 | WA | Karlawinda
RD4248 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 46820 | 2021-06-14 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 57650 | 2024-05-23 | 57617 | 2027-10-12 | 10033 | WA | Karlawinda
RD4248 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 57650 | 2024-05-23 | 57617 | 2027-10-12 | 10033 | WA | Karlawinda
RD4248 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 57650 | 2024-05-23 | 57617 | 2027-10-12 | 10033 | WA | Karlawinda
RD4248 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 57650 | 2024-05-15 | 57617 | 2029-02-23 | 20033 | WA | Karlawinda
RD4248 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 57650 | 2024-05-16 | 57617 | 2028-08-07 | 16033 | WA | Karlawinda
RD4248 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 26316 | 2017-11-16 | 57617 | 2027-08-06 | 8699 | WA | Karlawinda
RD4248 | Cat 789C | N7120 | Pump Steering | 20000 | 57560 | 2024-05-16 | 57617 | 2029-02-18 | 19943 | WA | Karlawinda
RD4248 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 51906 | 2022-03-20 | 57617 | 2028-11-27 | 18289 | WA | Karlawinda
RD4248 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 44086 | 2021-02-24 | 57617 | 2027-11-02 | 10469 | WA | Karlawinda
RD4248 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N7605 | Steering Hmu | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8000 | Main Frame/Chassis | 25000 | 26316 | 2017-11-16 | 57617 | 2025-07-17 | -6301 | WA | Karlawinda
RD4248 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 57560 | 2024-05-16 | 57617 | 2029-02-18 | 19943 | WA | Karlawinda
RD4248 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 51906 | 2022-03-18 | 57617 | 2028-05-11 | 14289 | WA | Karlawinda
RD4248 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 46820 | 2021-06-13 | 57617 | 2027-08-31 | 9203 | WA | Karlawinda
RD4248 | Cat 789C | N8140 | Steering Y Piece | 20000 | 57689 | 2025-04-13 | 57617 | 2029-02-25 | 20072 | WA | Karlawinda
RD4248 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 57560 | 2024-05-16 | 57617 | 2029-02-18 | 19943 | WA | Karlawinda
RD4248 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 57689 | 2025-04-13 | 57617 | 2029-02-25 | 20072 | WA | Karlawinda
RD4248 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 57560 | 2024-06-10 | 57617 | 2030-07-03 | 29943 | WA | Karlawinda
RD4248 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 57689 | 2025-04-13 | 57617 | 2030-07-10 | 30072 | WA | Karlawinda
RD4248 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 46820 | 2021-06-12 | 57617 | 2026-12-24 | 4203 | WA | Karlawinda
RD4248 | Cat 789C | N8501 | Ball Stud Crack Test |  | 57617 | 2026-02-10 | 57617 | 2026-08-11 |  | WA | Karlawinda
RD4248 | Cat 789C | N8995 | Operator Seat | 6000 | 57560 | 2024-06-01 | 57617 | 2027-03-21 | 5943 | WA | Karlawinda
RD4248 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 57617 | 2026-09-24 | 2383 | WA | Karlawinda
RD4248 | Cat 789C | N9020 | Alternator | 10000 | 57650 | 2024-05-10 | 57617 | 2027-10-12 | 10033 | WA | Karlawinda
RD4248 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 57560 | 2024-07-15 | 57617 | 2027-01-30 | 4943 | WA | Karlawinda
RD4248 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 57560 | 2024-07-15 | 57617 | 2029-02-18 | 19943 | WA | Karlawinda
RD4248 | Cat 789C | N9501 | A/C Compressor | 10000 | 57650 | 2024-05-23 | 57617 | 2027-10-12 | 10033 | WA | Karlawinda
RD4248 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 12917 | 2013-12-17 | 57617 | 2028-07-01 | 15300 | WA | Karlawinda
RD4248 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 6967 | 2013-12-17 | 57617 | 2029-09-27 | 24350 | WA | Karlawinda
RD4249 | Cat 789C | N0066 | Fire Suppression Sys Cylinder |  | 57576 | 2026-04-12 | 57576 | 2031-04-11 |  | WA | Hazelmere
RD4249 | Cat 789C | N0200 | A Frame Bearing | 20000 | 55626 | 2024-05-15 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 55626 | 2024-05-15 | 57576 | 2026-06-01 | 50 | WA | Hazelmere
RD4249 | Cat 789C | N0520 | Pre Lube Pump | 20000 | 47406 | 2021-10-29 | 57576 | 2028-04-29 | 9830 | WA | Hazelmere
RD4249 | Cat 789C | N1000 | Engine | 20000 | 42484 | 2021-03-02 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N1002 | Engine Valve Adj | 4000 | 55626 | 2024-04-18 | 57576 | 2026-10-21 | 2050 | WA | Hazelmere
RD4249 | Cat 789C | N1002-01 | Engine Valve Adj - Initial | 50 | 42484 | 2021-03-02 | 57576 | 2023-06-19 | -15042 | WA | Hazelmere
RD4249 | Cat 789C | N1100-LF | Turbo Primary LFT FRONT | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1100-LR | Turbo Primary LFT REAR | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1100-RF | Turbo Primary RHT FRONT | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1100-RR | Turbo Primary RHT REAR | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1202 | Fuel Transfer Pump | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1300 | Cooling Sys Service | 10000 | 52516 | 2022-07-12 | 57576 | 2027-05-16 | 4940 | WA | Hazelmere
RD4249 | Cat 789C | N1310 | Radiator | 20000 | 42484 | 2021-03-02 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N1402 | Fan Pulley Brgs | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1403 | Jockey Pulley Brgs | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N1430 | Air Starter | 20000 | 57888 | 2024-11-24 | 57576 | 2030-05-18 | 20312 | WA | Hazelmere
RD4249 | Cat 789C | N2000 | Transmission | 20000 | 55065 | 2022-12-05 | 57576 | 2029-10-28 | 17489 | WA | Hazelmere
RD4249 | Cat 789C | N2002 | Oil Cooler - Transmission | 20000 | 55626 | 2024-04-12 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N2004 | Transmission Pump | 20000 | 42484 | 2021-03-03 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N2050 | Torque Convertor | 20000 | 42484 | 2021-02-26 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 42484 | 2021-03-01 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N3021 | Uni's Eng - Pump Drive | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N3028 | Drive Shaft T/C - Trans | 20000 | 42484 | 2021-03-01 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N3029 | Uni's T/C - Trans | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N3320 | Pump Drive Box | 20000 | 57589 | 2026-04-12 | 57576 | 2030-04-27 | 20013 | WA | Hazelmere
RD4249 | Cat 789C | N4000 | Bevel Gear | 20000 | 50659 | 2022-04-22 | 57576 | 2028-12-18 | 13083 | WA | Hazelmere
RD4249 | Cat 789C | N4102-03 | Axle Shaft - POS 3 | 20000 | 50659 | 2022-04-22 | 57576 | 2028-12-18 | 13083 | WA | Hazelmere
RD4249 | Cat 789C | N4102-04 | Axle Shaft - POS 4 | 20000 | 50659 | 2022-04-22 | 57576 | 2028-12-18 | 13083 | WA | Hazelmere
RD4249 | Cat 789C | N5000-03 | Final Drive POS 3 | 20000 | 50659 | 2022-04-22 | 57576 | 2028-12-18 | 13083 | WA | Hazelmere
RD4249 | Cat 789C | N5000-04 | Final Drive POS 4 | 20000 | 50659 | 2022-04-22 | 57576 | 2028-12-18 | 13083 | WA | Hazelmere
RD4249 | Cat 789C | N5020-01 | Wheel Bearing POS 1 | 20000 | 55626 | 2024-04-15 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N5020-02 | Wheel Bearing POS 2 | 20000 | 39625 | 2020-10-30 | 57576 | 2026-10-21 | 2049 | WA | Hazelmere
RD4249 | Cat 789C | N6000-01 | Brake POS 1 | 20000 | 55626 | 2024-04-15 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N6000-02 | Brake POS 2 | 20000 | 39625 | 2020-10-30 | 57576 | 2026-10-21 | 2049 | WA | Hazelmere
RD4249 | Cat 789C | N6030-F | Brake Slack Adj FRONT | 20000 | 55631 | 2024-06-10 | 57576 | 2029-12-08 | 18055 | WA | Hazelmere
RD4249 | Cat 789C | N6030-RE | Brake Slack Adj REAR | 20000 | 55626 | 2024-04-11 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N6061 | Oil Cooler Front Brakes | 20000 | 42484 | 2021-02-26 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N6200-F | Press Converter FRONT | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N6200-LR | Press Converter LEFT REAR | 10000 | 52271 | 2022-07-10 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N6200-RR | Press Converter RIGHT REAR | 10000 | 52271 | 2022-07-18 | 57576 | 2027-04-28 | 4695 | WA | Hazelmere
RD4249 | Cat 789C | N7038 | Pump Conv,P/Brk Rel, Brk Cool | 20000 | 42484 | 2021-02-26 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N7065 | Pump Hoist/ Brk Cooling | 16000 | 42484 | 2021-02-27 | 57576 | 2026-08-01 | 908 | WA | Hazelmere
RD4249 | Cat 789C | N7088 | Pump Park Brk Rel | 40000 | 24686 | 2017-11-16 | 57576 | 2027-10-18 | 7110 | WA | Hazelmere
RD4249 | Cat 789C | N7120 | Pump Steering | 20000 | 42484 | 2021-03-01 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 47406 | 2021-10-29 | 57576 | 2029-02-09 | 13830 | WA | Hazelmere
RD4249 | Cat 789C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 55626 | 2024-05-22 | 57576 | 2030-09-19 | 22050 | WA | Hazelmere
RD4249 | Cat 789C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 55626 | 2024-04-09 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 55102 | 2022-10-20 | 57576 | 2029-10-31 | 17526 | WA | Hazelmere
RD4249 | Cat 789C | N7605 | Steering Hmu | 20000 | 43994 | 2021-05-18 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N7657-F | Hyd Accum Steering FRONT | 20000 | 43994 | 2021-05-17 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N7657-RE | Hyd Accum Steering REAR | 20000 | 43994 | 2021-05-17 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8000 | Main Frame/Chassis | 25000 | 24686 | 2017-11-16 | 57576 | 2024-11-10 | -7890 | WA | Hazelmere
RD4249 | Cat 789C | N8122-01 | Wheel Group POS 1 | 20000 | 55626 | 2024-04-15 | 57576 | 2029-12-07 | 18050 | WA | Hazelmere
RD4249 | Cat 789C | N8122-02 | Wheel Group POS 2 | 20000 | 39625 | 2020-10-30 | 57576 | 2026-10-21 | 2049 | WA | Hazelmere
RD4249 | Cat 789C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8137-L | Steering Linkage Group LEFT | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8137-R | Steering Linkage Group RIGHT | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8140 | Steering Y Piece | 20000 | 43994 | 2021-05-21 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8200-01 | Ride Strut POS 1 | 20000 | 43994 | 2021-05-20 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8200-02 | Ride Strut POS 2 | 20000 | 43994 | 2021-05-19 | 57576 | 2027-08-29 | 6418 | WA | Hazelmere
RD4249 | Cat 789C | N8200-03 | Ride Strut POS 3 | 30000 | 55626 | 2024-05-24 | 57576 | 2031-11-22 | 28050 | WA | Hazelmere
RD4249 | Cat 789C | N8200-04 | Ride Strut POS 4 | 30000 | 55626 | 2024-05-24 | 57576 | 2031-11-22 | 28050 | WA | Hazelmere
RD4249 | Cat 789C | N8441 | Rear Axle Dog Bone | 15000 | 52516 | 2022-04-28 | 57576 | 2028-05-07 | 9940 | WA | Hazelmere
RD4249 | Cat 789C | N8501 | Ball Stud Crack Test |  | 57576 | 2026-04-12 | 57576 | 2026-10-11 |  | WA | Hazelmere
RD4249 | Cat 789C | N8995 | Operator Seat | 6000 | 55626 | 2024-04-26 | 57576 | 2027-03-13 | 4050 | WA | Hazelmere
RD4249 | Cat 789C | N8999 | Cab Upgrade | 60000 |  |  | 57576 | 2026-11-17 | 2424 | WA | Hazelmere
RD4249 | Cat 789C | N9020 | Alternator | 10000 | 55626 | 2024-04-10 | 57576 | 2027-12-24 | 8050 | WA | Hazelmere
RD4249 | Cat 789C | N9500 | Air Cond'r-Serv | 5000 | 55626 | 2024-05-30 | 57576 | 2027-01-01 | 3050 | WA | Hazelmere
RD4249 | Cat 789C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 42484 | 2021-03-03 | 57576 | 2027-05-14 | 4908 | WA | Hazelmere
RD4249 | Cat 789C | N9501 | A/C Compressor | 10000 | 55626 | 2024-05-16 | 57576 | 2027-12-24 | 8050 | WA | Hazelmere
RD4249 | Cat 789C | N9998 | Extended Life Rebuild | 60000 | 12467 | 2013-12-17 | 57576 | 2029-04-26 | 14891 | WA | Hazelmere
RD4249 | Cat 789C | N9998-01 | Extended Life Rebuild ONE | 75000 | 6467 | 2013-12-17 | 57576 | 2031-01-29 | 23891 | WA | Hazelmere
RD4376 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 66519 | 2026-04-22 | 66519 | 2031-04-21 |  | WA | Hazelmere
RD4376 | Cat 785C | N0200 | A Frame Bearing | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 66550 | 2026-04-22 | 66519 | 2026-10-31 | 2031 | WA | Hazelmere
RD4376 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N1000 | Engine | 20000 | 54708 | 2019-11-12 | 66519 | 2028-02-17 | 8189 | WA | Hazelmere
RD4376 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 66528 | 2023-10-21 | 66519 | 2027-04-01 | 4009 | WA | Hazelmere
RD4376 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 54708 | 2019-11-12 | 66519 | 2023-12-05 | -11761 | WA | Hazelmere
RD4376 | Cat 785C | N1004 | Engine Midlife | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N1301 | Water Pump | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N1310 | Radiator | 20000 | 54708 | 2019-11-12 | 66519 | 2028-02-17 | 8189 | WA | Hazelmere
RD4376 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 63104 | 2022-11-01 | 66519 | 2027-10-17 | 6585 | WA | Hazelmere
RD4376 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 63104 | 2022-11-01 | 66519 | 2027-10-17 | 6585 | WA | Hazelmere
RD4376 | Cat 785C | N1420 | Air Compressor | 10000 | 64441 | 2023-02-13 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N1430 | Air Starter | 10000 | 54708 | 2019-11-12 | 66519 | 2026-01-09 | -1811 | WA | Hazelmere
RD4376 | Cat 785C | N2000 | Transmission | 20000 | 53069 | 2019-06-12 | 66519 | 2027-10-14 | 6550 | WA | Hazelmere
RD4376 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 52532 | 2019-05-01 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N2004 | Transmission Pump | 20000 | 52532 | 2019-05-01 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N2050 | Torque Convertor | 20000 | 58366 | 2020-06-12 | 66519 | 2028-11-24 | 11847 | WA | Hazelmere
RD4376 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 64441 | 2023-02-09 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 64441 | 2023-02-09 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 64441 | 2023-02-11 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 64441 | 2023-02-11 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N3320 | Pump Drive Box | 20000 | 54747 | 2019-11-12 | 66519 | 2028-02-20 | 8228 | WA | Hazelmere
RD4376 | Cat 785C | N4000 | Bevel Gear | 20000 | 63558 | 2022-12-10 | 66519 | 2029-12-29 | 17039 | WA | Hazelmere
RD4376 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 64441 | 2023-02-12 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 52532 | 2019-05-01 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 61460 | 2022-04-04 | 66519 | 2029-07-20 | 14941 | WA | Hazelmere
RD4376 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 52532 | 2019-05-01 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 55996 | 2020-02-08 | 66519 | 2028-05-26 | 9477 | WA | Hazelmere
RD4376 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 55996 | 2020-02-08 | 66519 | 2028-05-26 | 9477 | WA | Hazelmere
RD4376 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 64441 | 2023-02-09 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 64441 | 2023-02-10 | 66519 | 2028-01-27 | 7922 | WA | Hazelmere
RD4376 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 64441 | 2023-02-12 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 54708 | 2019-11-12 | 66519 | 2028-02-17 | 8189 | WA | Hazelmere
RD4376 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 54708 | 2019-11-12 | 66519 | 2032-05-04 | 28189 | WA | Hazelmere
RD4376 | Cat 785C | N7120 | Pump Steering | 20000 | 64441 | 2023-02-11 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 52532 | 2019-04-08 | 66519 | 2028-07-06 | 10013 | WA | Hazelmere
RD4376 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 41337.7 | 2012-03-14 | 66519 | 2026-02-26 | -1181.3 | WA | Hazelmere
RD4376 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 66550 | 2026-02-09 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 55492 | 2019-12-26 | 66519 | 2028-04-17 | 8973 | WA | Hazelmere
RD4376 | Cat 785C | N7605 | Steering Hmu | 20000 | 58713 | 2020-07-14 | 66519 | 2028-12-21 | 12194 | WA | Hazelmere
RD4376 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 66519 | 2017-08-29 | -41519 | WA | Hazelmere
RD4376 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-09-03 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 64441 | 2023-02-10 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8140 | Steering Y Piece | 20000 | 64441 | 2023-02-11 | 66519 | 2030-03-07 | 17922 | WA | Hazelmere
RD4376 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 52532 | 2019-05-17 | 66519 | 2027-04-30 | 6013 | WA | Hazelmere
RD4376 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 60898 | 2020-12-20 | 66519 | 2029-06-07 | 14379 | WA | Hazelmere
RD4376 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 66550 | 2026-04-22 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 66550 | 2026-02-07 | 66519 | 2030-08-16 | 20031 | WA | Hazelmere
RD4376 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 66550 | 2026-04-22 | 66519 | 2031-09-04 | 25031 | WA | Hazelmere
RD4376 | Cat 785C | N8501 | Ball Stud Crack Test |  | 66519 | 2026-04-22 | 66519 | 2026-10-21 |  | WA | Hazelmere
RD4376 | Cat 785C | N8995 | Operator Seat | 6000 | 66550 | 2026-04-22 | 66519 | 2027-09-04 | 6031 | WA | Hazelmere
RD4376 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 66519 | 2017-08-29 | -41519 | WA | Hazelmere
RD4376 | Cat 785C | N9020 | Alternator | 10000 | 66550 | 2026-04-22 | 66519 | 2028-07-08 | 10031 | WA | Hazelmere
RD4376 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 66564 | 2026-04-23 | 66519 | 2027-06-20 | 5045 | WA | Hazelmere
RD4376 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 66564 | 2026-04-23 | 66519 | 2030-08-17 | 20045 | WA | Hazelmere
RD4376 | Cat 785C | N9501 | A/C Compressor | 10000 | 66550 | 2026-04-22 | 66519 | 2028-07-08 | 10031 | WA | Hazelmere
RD4376 | Cat 785C | N9998 | Extended Life Rebuild | 45000 | 45000 | 2013-04-20 | 66519 | 2031-05-08 | 23481 | WA | Hazelmere
RD4376 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2013-04-20 | 66519 | 2026-01-31 | -1519 | WA | Hazelmere
RD4376 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2013-04-20 | 66519 | 2030-04-19 | 18481 | WA | Hazelmere
RD4377 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 60744 | 2022-04-03 | 65021 | 2027-04-02 |  | WA | Gold Fields St Ives
RD4377 | Cat 785C | N0200 | A Frame Bearing | 20000 | 60896 | 2022-04-10 | 65021 | 2031-07-09 | 15875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 63059 | 2025-06-28 | 65021 | 2026-06-01 | 38 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1000 | Engine | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 12 | 2025-10-03 | 65021 | 2006-10-02 | -61009 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 57177 | 2020-05-14 | 65021 | 2023-11-23 | -7794 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1004 | Engine Midlife | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1301 | Water Pump | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1310 | Radiator | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1420 | Air Compressor | 10000 | 62836 | 2025-03-03 | 65021 | 2028-12-02 | 7815 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N1430 | Air Starter | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N2000 | Transmission | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N2004 | Transmission Pump | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N2050 | Torque Convertor | 20000 | 60896 | 2022-03-17 | 65021 | 2031-07-09 | 15875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 57177 | 2020-05-14 | 65021 | 2027-02-06 | 2156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N3320 | Pump Drive Box | 20000 | 54067 | 2019-10-07 | 65021 | 2029-04-26 | 9046 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N4000 | Bevel Gear | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 55706 | 2020-02-06 | 65021 | 2029-11-05 | 10685 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 60896 | 2022-04-10 | 65021 | 2031-07-09 | 15875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 63059 | 2025-06-29 | 65021 | 2032-03-19 | 18038 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 55706 | 2020-02-06 | 65021 | 2029-11-05 | 10685 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 55706 | 2020-02-06 | 65021 | 2029-11-05 | 10685 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 55706 | 2020-02-06 | 65021 | 2026-08-17 | 685 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 55706 | 2020-02-06 | 65021 | 2026-08-17 | 685 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 55706 | 2020-02-06 | 65021 | 2026-08-17 | 685 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 54912 | 2019-11-21 | 65021 | 2029-08-04 | 9891 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 53188 | 2019-07-17 | 65021 | 2029-01-13 | 8167 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 54067 | 2019-10-07 | 65021 | 2035-10-05 | 29046 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7120 | Pump Steering | 20000 | 60896 | 2022-04-10 | 65021 | 2031-07-09 | 15875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 57177 | 2020-05-14 | 65021 | 2031-08-11 | 16156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 51408 | 2019-03-18 | 65021 | 2029-10-01 | 10387 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 57177 | 2020-05-14 | 65021 | 2030-04-27 | 12156 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7605 | Steering Hmu | 20000 | 58559 | 2020-07-27 | 65021 | 2030-10-07 | 13538 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 65021 | 2013-07-07 | -40021 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 52308 | 2019-05-08 | 65021 | 2028-10-01 | 7287 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 44622 |  | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 44622 |  | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8140 | Steering Y Piece | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 60896 | 2022-04-10 | 65021 | 2031-07-09 | 15875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 55212 | 2020-02-17 | 65021 | 2029-09-08 | 10191 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 44622 | 2017-08-01 | 65021 | 2026-04-11 | -399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 47265 | 2018-10-12 | 65021 | 2027-02-16 | 2244 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 44622 | 2017-08-01 | 65021 | 2027-11-20 | 4601 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8501 | Ball Stud Crack Test |  | 60744 | 2022-04-10 | 65021 | 2022-10-09 |  | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8995 | Operator Seat | 6000 | 60896 | 2022-04-10 | 65021 | 2027-01-04 | 1875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 65021 | 2013-07-07 | -40021 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9020 | Alternator | 10000 | 60744 | 2022-06-15 | 65021 | 2028-03-31 | 5723 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 60896 | 2022-04-10 | 65021 | 2026-09-08 | 875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 60896 | 2022-04-10 | 65021 | 2031-07-09 | 15875 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9501 | A/C Compressor | 10000 | 44622 | 2017-08-01 | 65021 | 2023-01-21 | -10399 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9998 | Extended Life Rebuild | 45000 | 45000 | 2013-04-20 | 65021 | 2034-06-14 | 24979 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2013-04-20 | 65021 | 2026-05-26 | -21 | WA | Gold Fields St Ives
RD4377 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2013-04-20 | 65021 | 2032-11-02 | 19979 | WA | Gold Fields St Ives
RD4378 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 36580.4 | 2023-03-27 | 54979 | 2028-03-25 |  | WA | Iron Bridge
RD4378 | Cat 785C | N0200 | A Frame Bearing | 20000 | 32110 | 2019-02-02 | 54979 | 2025-11-09 | -2869 | WA | Iron Bridge
RD4378 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 48214 | 2025-02-18 | 54979 | 2025-06-22 | -4765 | WA | Iron Bridge
RD4378 | Cat 785C | N0500 | Bulk Water Pump | 5000 | 50856 | 2025-10-26 | 54979 | 2026-07-30 | 877 | WA | Iron Bridge
RD4378 | Cat 785C | N1000 | Engine | 20000 | 36585 | 2023-01-12 | 54979 | 2026-09-20 | 1606 | WA | Iron Bridge
RD4378 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 48214 | 2025-06-15 | 54979 | 2025-11-11 | -2765 | WA | Iron Bridge
RD4378 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 | 37103 | 2023-08-03 | 54979 | 2022-12-02 | -17826 | WA | Iron Bridge
RD4378 | Cat 785C | N1004 | Engine Midlife | 10000 | 48214 | 2025-06-16 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 48214 | 2025-06-16 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 48214 | 2025-06-15 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 48214 | 2025-06-15 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 48214 | 2025-06-16 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1301 | Water Pump | 20000 | 36585 | 2023-01-12 | 54979 | 2026-09-20 | 1606 | WA | Iron Bridge
RD4378 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 36585 | 2023-01-12 | 54979 | 2026-09-20 | 1606 | WA | Iron Bridge
RD4378 | Cat 785C | N1310 | Radiator | 20000 | 51581 | 2025-11-29 | 54979 | 2029-08-26 | 16602 | WA | Iron Bridge
RD4378 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 48214 | 2025-06-14 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 48214 | 2025-06-14 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1420 | Air Compressor | 10000 | 48214 | 2025-06-15 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N1430 | Air Starter | 10000 | 36585 | 2023-01-23 | 54979 | 2024-10-05 | -8394 | WA | Iron Bridge
RD4378 | Cat 785C | N2000 | Transmission | 20000 | 33026 | 2019-08-29 | 54979 | 2026-01-14 | -1953 | WA | Iron Bridge
RD4378 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 32151 | 2019-04-04 | 54979 | 2025-11-12 | -2828 | WA | Iron Bridge
RD4378 | Cat 785C | N2004 | Transmission Pump | 20000 | 33026 | 2019-08-29 | 54979 | 2026-01-14 | -1953 | WA | Iron Bridge
RD4378 | Cat 785C | N2050 | Torque Convertor | 20000 | 49521 | 2025-08-24 | 54979 | 2029-04-01 | 14542 | WA | Iron Bridge
RD4378 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 41095 | 2024-05-06 | 54979 | 2027-08-08 | 6116 | WA | Iron Bridge
RD4378 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 52477 | 2026-01-12 | 54979 | 2027-11-15 | 7498 | WA | Iron Bridge
RD4378 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 52477 | 2026-01-12 | 54979 | 2027-11-15 | 7498 | WA | Iron Bridge
RD4378 | Cat 785C | N3320 | Pump Drive Box | 20000 | 31720 | 2022-12-18 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N4000 | Bevel Gear | 20000 | 35327 | 2017-08-01 | 54979 | 2026-06-27 | 348 | WA | Iron Bridge
RD4378 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 36580 | 2023-01-17 | 54979 | 2026-09-24 | 1601 | WA | Iron Bridge
RD4378 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 31720 | 2022-11-01 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 31721 | 2022-11-25 | 54979 | 2025-10-12 | -3258 | WA | Iron Bridge
RD4378 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 36580 | 2023-02-26 | 54979 | 2026-09-24 | 1601 | WA | Iron Bridge
RD4378 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 46018 | 2025-02-08 | 54979 | 2028-07-25 | 11039 | WA | Iron Bridge
RD4378 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 31720 | 2022-11-08 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 46018 | 2025-02-08 | 54979 | 2028-07-25 | 11039 | WA | Iron Bridge
RD4378 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 31720 | 2022-11-08 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 51899 | 2025-12-14 | 54979 | 2029-09-18 | 16920 | WA | Iron Bridge
RD4378 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 51899 | 2025-12-14 | 54979 | 2029-09-18 | 16920 | WA | Iron Bridge
RD4378 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 52477 | 2026-01-13 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 51898 | 2025-12-15 | 54979 | 2027-10-04 | 6919 | WA | Iron Bridge
RD4378 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 49521 | 2025-08-24 | 54979 | 2027-04-17 | 4542 | WA | Iron Bridge
RD4378 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 46018 | 2025-02-08 | 54979 | 2026-08-12 | 1039 | WA | Iron Bridge
RD4378 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 49521 | 2025-08-24 | 54979 | 2029-04-01 | 14542 | WA | Iron Bridge
RD4378 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 5000 | 49521 | 2025-08-24 | 54979 | 2026-04-30 | -458 | WA | Iron Bridge
RD4378 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 31721 | 2022-12-12 | 54979 | 2029-09-05 | 16742 | WA | Iron Bridge
RD4378 | Cat 785C | N7120 | Pump Steering | 20000 | 42293 | 2024-07-20 | 54979 | 2027-11-01 | 7314 | WA | Iron Bridge
RD4378 | Cat 785C | N7361 | Hyd Motor Water Pump | 10000 | 49159 | 2025-08-03 | 54979 | 2027-03-23 | 4180 | WA | Iron Bridge
RD4378 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 60000 | 31720 | 2022-11-28 | 54979 | 2033-08-03 | 36741 | WA | Iron Bridge
RD4378 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 60000 | 32197 | 2019-03-01 | 54979 | 2033-09-06 | 37218 | WA | Iron Bridge
RD4378 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 31720 | 2022-12-11 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 31720 | 2022-12-14 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N7605 | Steering Hmu | 20000 | 34829 | 2020-09-15 | 54979 | 2026-05-22 | -150 | WA | Iron Bridge
RD4378 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 35327 | 2017-08-01 | 54979 | 2026-06-22 | 348 | WA | Iron Bridge
RD4378 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 35327 | 2017-08-01 | 54979 | 2026-06-22 | 348 | WA | Iron Bridge
RD4378 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 54979 | 2020-07-17 | -29979 | WA | Iron Bridge
RD4378 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 46018 | 2025-02-08 | 54979 | 2028-07-25 | 11039 | WA | Iron Bridge
RD4378 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 31720 | 2022-11-08 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 52477 | 2026-01-12 | 54979 | 2029-10-29 | 17498 | WA | Iron Bridge
RD4378 | Cat 785C | N8140 | Steering Y Piece | 20000 | 53562 | 2026-03-12 | 54979 | 2030-01-14 | 18583 | WA | Iron Bridge
RD4378 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 31720 | 2022-11-23 | 54979 | 2025-10-07 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 31720 | 2022-11-24 | 54979 | 2025-10-12 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 34235 | 2020-06-22 | 54979 | 2026-04-05 | -744 | WA | Iron Bridge
RD4378 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 31720 | 2022-11-01 | 54979 | 2025-10-07 | -3259 | WA | Iron Bridge
RD4378 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 32110 | 2019-02-02 | 54979 | 2026-10-31 | 2131 | WA | Iron Bridge
RD4378 | Cat 785C | N8501 | Ball Stud Crack Test |  | 52704 | 2026-01-25 | 54979 | 2026-07-26 |  | WA | Iron Bridge
RD4378 | Cat 785C | N8995 | Operator Seat | 6000 | 51899 | 2025-12-14 | 54979 | 2026-12-23 | 2920 | WA | Iron Bridge
RD4378 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 54979 | 2020-07-17 | -29979 | WA | Iron Bridge
RD4378 | Cat 785C | N9020 | Alternator | 10000 | 48214 | 2025-06-15 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 50856 | 2025-10-26 | 54979 | 2026-08-04 | 877 | WA | Iron Bridge
RD4378 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 36585 | 2023-03-28 | 54979 | 2026-09-20 | 1606 | WA | Iron Bridge
RD4378 | Cat 785C | N9501 | A/C Compressor | 10000 | 48214 | 2025-06-14 | 54979 | 2027-01-14 | 3235 | WA | Iron Bridge
RD4378 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  | 2014-02-22 | 54979 | 2024-06-14 | -9979 | WA | Iron Bridge
RD4378 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  | 2014-02-22 | 54979 | 2028-05-13 | 10021 | WA | Iron Bridge
RD4378 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  | 2014-02-22 | 54979 | 2032-04-10 | 30021 | WA | Iron Bridge
RD4822 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 32202 | 2026-04-25 | 32755 | 2031-04-24 |  | WA | Iron Bridge
RD4822 | Cat 785C | N8501 | Ball Stud Crack Test |  | 31135 | 2026-01-25 | 32755 | 2026-07-26 |  | WA | Iron Bridge
RD4822 | Cat 785C | N8995 | Operator Seat | 6000 | 30826 | 2026-01-04 | 32755 | 2027-04-09 | 4071 | WA | Iron Bridge
RD4822 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 |  |  | 32755 | 2026-04-15 | -27755 | WA | Iron Bridge
RD4910 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 55429 | 2025-06-21 | 62106 | 2030-06-20 |  | WA | Iron Bridge
RD4910 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1000 | Engine | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 58142 | 2025-11-09 | 62106 | 2026-05-30 | 36 | WA | Iron Bridge
RD4910 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 47115 | 2023-10-27 | 62106 | 2024-03-11 | -14941 | WA | Iron Bridge
RD4910 | Cat 793F | N1004 | Engine Midlife | 12000 | 61492 | 2026-04-22 | 62106 | 2028-02-02 | 11386 | WA | Iron Bridge
RD4910 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 47115 | 2023-10-27 | 62106 | 2025-12-17 | -2991 | WA | Iron Bridge
RD4910 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 61492 | 2026-04-21 | 62106 | 2028-02-02 | 11386 | WA | Iron Bridge
RD4910 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1210 | Fuel Injectors | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 61492 | 2026-04-22 | 62106 | 2028-02-02 | 11386 | WA | Iron Bridge
RD4910 | Cat 793F | N1301 | Water Pump | 12000 | 61492 | 2026-04-21 | 62106 | 2028-02-02 | 11386 | WA | Iron Bridge
RD4910 | Cat 793F | N1310 | Radiator | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1315 | Thermostat | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 47115 | 2023-10-27 | 62106 | 2025-12-17 | -2991 | WA | Iron Bridge
RD4910 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 61492 | 2026-04-21 | 62106 | 2028-02-02 | 11386 | WA | Iron Bridge
RD4910 | Cat 793F | N2000 | Transmission | 18000 | 51600 | 2024-11-18 | 62106 | 2027-07-07 | 7494 | WA | Iron Bridge
RD4910 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 51600 | 2024-11-20 | 62106 | 2027-10-23 | 9494 | WA | Iron Bridge
RD4910 | Cat 793F | N2050 | Torque Convertor | 24000 | 57104 | 2025-09-14 | 62106 | 2029-03-20 | 18998 | WA | Iron Bridge
RD4910 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 57104 | 2025-09-14 | 62106 | 2028-04-30 | 12998 | WA | Iron Bridge
RD4910 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 61492 | 2026-04-21 | 62106 | 2028-02-02 | 11386 | WA | Iron Bridge
RD4910 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 51600 | 2024-11-18 | 62106 | 2027-03-21 | 5494 | WA | Iron Bridge
RD4910 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 61492 | 2026-04-22 | 62106 | 2027-07-01 | 7386 | WA | Iron Bridge
RD4910 | Cat 793F | N3320 | Pump Drive Box | 18000 | 57104 | 2025-09-14 | 62106 | 2028-04-30 | 12998 | WA | Iron Bridge
RD4910 | Cat 793F | N4000 | Bevel Gear | 18000 | 51600 | 2024-11-18 | 62106 | 2027-07-07 | 7494 | WA | Iron Bridge
RD4910 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 47115 | 2023-10-27 | 62106 | 2028-08-16 | 15009 | WA | Iron Bridge
RD4910 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 47115 | 2023-10-27 | 62106 | 2028-08-16 | 15009 | WA | Iron Bridge
RD4910 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 44894 | 2022-01-20 | 62106 | 2027-07-23 | 7788 | WA | Iron Bridge
RD4910 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 44894 | 2022-01-20 | 62106 | 2027-07-23 | 7788 | WA | Iron Bridge
RD4910 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 43882 | 2021-11-14 | 62106 | 2026-01-28 | -2224 | WA | Iron Bridge
RD4910 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 43882 | 2021-11-14 | 62106 | 2026-01-28 | -2224 | WA | Iron Bridge
RD4910 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 42900 | 2021-09-14 | 62106 | 2027-05-30 | 6794 | WA | Iron Bridge
RD4910 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 42900 | 2021-09-14 | 62106 | 2027-05-30 | 6794 | WA | Iron Bridge
RD4910 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 47115 | 2023-10-27 | 62106 | 2027-06-11 | 7009 | WA | Iron Bridge
RD4910 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 57104 | 2025-09-13 | 62106 | 2028-12-02 | 16998 | WA | Iron Bridge
RD4910 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 47115 | 2023-10-27 | 62106 | 2026-11-07 | 3009 | WA | Iron Bridge
RD4910 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 57104 | 2025-09-14 | 62106 | 2028-04-30 | 12998 | WA | Iron Bridge
RD4910 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 38283 | 2020-10-26 | 62106 | 2026-06-07 | 177 | WA | Iron Bridge
RD4910 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 38283 | 2020-10-26 | 62106 | 2026-06-07 | 177 | WA | Iron Bridge
RD4910 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 31770 | 2019-06-25 | 62106 | 2025-11-29 | -3336 | WA | Iron Bridge
RD4910 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 47115 | 2023-10-27 | 62106 | 2028-03-07 | 12009 | WA | Iron Bridge
RD4910 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 46875 | 2023-10-27 | 62106 | 2025-12-20 | -3231 | WA | Iron Bridge
RD4910 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 57104 | 2025-09-12 | 62106 | 2027-06-10 | 6998 | WA | Iron Bridge
RD4910 | Cat 793F | N7605 | Steering Hmu | 24000 | 38283 | 2020-10-26 | 62106 | 2026-06-07 | 177 | WA | Iron Bridge
RD4910 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 59411 | 2026-01-10 | 62106 | 2029-07-23 | 21305 | WA | Iron Bridge
RD4910 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 51600 | 2024-11-20 | 62106 | 2028-05-26 | 13494 | WA | Iron Bridge
RD4910 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 51600 | 2024-11-20 | 62106 | 2028-05-26 | 13494 | WA | Iron Bridge
RD4910 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 51600 | 2024-11-20 | 62106 | 2028-05-26 | 13494 | WA | Iron Bridge
RD4910 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 50386 | 2024-09-17 | 62106 | 2028-03-22 | 12280 | WA | Iron Bridge
RD4910 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 50386 | 2024-09-17 | 62106 | 2028-03-22 | 12280 | WA | Iron Bridge
RD4910 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 50386 | 2024-09-17 | 62106 | 2028-03-22 | 12280 | WA | Iron Bridge
RD4910 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 50386 | 2024-09-18 | 62106 | 2028-03-22 | 12280 | WA | Iron Bridge
RD4910 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 50386 | 2024-09-18 | 62106 | 2028-03-22 | 12280 | WA | Iron Bridge
RD4910 | Cat 793F | N8140 | Steering Y Piece | 24000 | 50387 | 2024-09-17 | 62106 | 2028-03-22 | 12281 | WA | Iron Bridge
RD4910 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 60938 | 2026-03-25 | 62106 | 2029-06-27 | 20832 | WA | Iron Bridge
RD4910 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 42900 | 2021-09-14 | 62106 | 2026-10-26 | 2794 | WA | Iron Bridge
RD4910 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 30403 | 2019-03-03 | 62106 | 2025-05-31 | -6703 | WA | Iron Bridge
RD4910 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 30403 | 2019-03-03 | 62106 | 2025-05-31 | -6703 | WA | Iron Bridge
RD4910 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 50386 | 2024-09-18 | 62106 | 2026-06-12 | 280 | WA | Iron Bridge
RD4910 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 50386 | 2024-09-18 | 62106 | 2026-06-12 | 280 | WA | Iron Bridge
RD4910 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 50386 | 2024-09-18 | 62106 | 2026-06-12 | 280 | WA | Iron Bridge
RD4910 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 50386 | 2024-09-18 | 62106 | 2026-06-12 | 280 | WA | Iron Bridge
RD4910 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 46875 | 2023-10-27 | 62106 | 2027-02-10 | 4769 | WA | Iron Bridge
RD4910 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 46875 | 2023-10-27 | 62106 | 2027-02-10 | 4769 | WA | Iron Bridge
RD4910 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 54986 | 2025-05-23 | 62106 | 2028-04-23 | 12880 | WA | Iron Bridge
RD4910 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 43882 | 2021-11-14 | 62106 | 2026-09-01 | 1776 | WA | Iron Bridge
RD4910 | Cat 793F | N8501 | Ball Stud Crack Test |  | 59805 | 2026-01-29 | 62106 | 2026-07-30 |  | WA | Iron Bridge
RD4910 | Cat 793F | N8995 | Operator Seat | 6000 | 53901 | 2025-03-28 | 62106 | 2026-02-17 | -2205 | WA | Iron Bridge
RD4910 | Cat 793F | N9020 | Alternator | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 55461 | 2025-06-23 | 62106 | 2028-12-21 | 17355 | WA | Iron Bridge
RD4910 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 57591 | 2025-10-20 | 62106 | 2029-04-15 | 19485 | WA | Iron Bridge
RD4910 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 57104 | 2025-09-14 | 62106 | 2026-04-04 | -1002 | WA | Iron Bridge
RD4910 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 47115 | 2023-10-27 | 62106 | 2027-09-27 | 9009 | WA | Iron Bridge
RD4910 | Cat 793F | N9501 | A/C Compressor | 12000 | 58027 | 2025-11-02 | 62106 | 2027-07-30 | 7921 | WA | Iron Bridge
RD4911 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 61969 | 2025-04-13 | 69656 | 2030-04-12 |  | WA | Iron Bridge
RD4911 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 54507 | 2024-03-21 | 69656 | 2027-09-18 | 8851 | WA | Iron Bridge
RD4911 | Cat 793F | N1000 | Engine | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 61412 | 2025-03-18 | 69656 | 2025-10-11 | -4244 | WA | Iron Bridge
RD4911 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 44390 | 2021-04-18 | 69656 | 2022-09-03 | -25216 | WA | Iron Bridge
RD4911 | Cat 793F | N1004 | Engine Midlife | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1210 | Fuel Injectors | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N1301 | Water Pump | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N1310 | Radiator | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1315 | Thermostat | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 55806 | 2023-10-27 | 69656 | 2026-02-17 | -1850 | WA | Iron Bridge
RD4911 | Cat 793F | N2000 | Transmission | 18000 | 50472 | 2022-07-13 | 69656 | 2026-03-25 | -1184 | WA | Iron Bridge
RD4911 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 50472 | 2022-07-13 | 69656 | 2026-07-11 | 816 | WA | Iron Bridge
RD4911 | Cat 793F | N2050 | Torque Convertor | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 64507 | 2025-07-04 | 69656 | 2028-04-22 | 12851 | WA | Iron Bridge
RD4911 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 58478 | 2024-10-06 | 69656 | 2026-07-11 | 822 | WA | Iron Bridge
RD4911 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 58478 | 2024-10-06 | 69656 | 2027-02-13 | 4822 | WA | Iron Bridge
RD4911 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 67185 | 2026-01-21 | 69656 | 2027-03-23 | 5529 | WA | Iron Bridge
RD4911 | Cat 793F | N3320 | Pump Drive Box | 18000 | 66349 | 2025-12-05 | 69656 | 2028-07-30 | 14693 | WA | Iron Bridge
RD4911 | Cat 793F | N4000 | Bevel Gear | 18000 | 50472 | 2022-07-13 | 69656 | 2026-03-25 | -1184 | WA | Iron Bridge
RD4911 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 54026 | 2023-03-09 | 69656 | 2028-07-13 | 14370 | WA | Iron Bridge
RD4911 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 54026 | 2023-03-09 | 69656 | 2028-07-13 | 14370 | WA | Iron Bridge
RD4911 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 41969 | 2020-10-22 | 69656 | 2026-01-03 | -2687 | WA | Iron Bridge
RD4911 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 44498 | 2021-05-03 | 69656 | 2026-05-19 | -158 | WA | Iron Bridge
RD4911 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 51466 | 2022-09-21 | 69656 | 2026-01-30 | -2190 | WA | Iron Bridge
RD4911 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 51466 | 2022-09-21 | 69656 | 2026-01-30 | -2190 | WA | Iron Bridge
RD4911 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 44498 | 2021-05-03 | 69656 | 2026-07-13 | 842 | WA | Iron Bridge
RD4911 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 63508 | 2025-07-05 | 69656 | 2029-05-05 | 19852 | WA | Iron Bridge
RD4911 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 66349 | 2025-12-05 | 69656 | 2029-03-03 | 18693 | WA | Iron Bridge
RD4911 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 69359 | 2026-05-12 | 69656 | 2029-08-13 | 21703 | WA | Iron Bridge
RD4911 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 55806 | 2023-10-27 | 69656 | 2027-01-07 | 4150 | WA | Iron Bridge
RD4911 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 58478 | 2024-10-06 | 69656 | 2027-06-01 | 6822 | WA | Iron Bridge
RD4911 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 66349 | 2025-12-05 | 69656 | 2029-06-20 | 20693 | WA | Iron Bridge
RD4911 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 66349 | 2025-12-05 | 69656 | 2029-06-20 | 20693 | WA | Iron Bridge
RD4911 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 40095 | 2020-06-14 | 69656 | 2025-07-31 | -5561 | WA | Iron Bridge
RD4911 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 63508 | 2025-07-03 | 69656 | 2029-06-28 | 20852 | WA | Iron Bridge
RD4911 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 55806 | 2023-10-27 | 69656 | 2028-05-08 | 13150 | WA | Iron Bridge
RD4911 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 63510 | 2025-07-09 | 69656 | 2027-04-09 | 5854 | WA | Iron Bridge
RD4911 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 63150 | 2025-07-09 | 69656 | 2027-03-21 | 5494 | WA | Iron Bridge
RD4911 | Cat 793F | N7605 | Steering Hmu | 24000 | 66214 | 2025-11-28 | 69656 | 2029-06-12 | 20558 | WA | Iron Bridge
RD4911 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 66249 | 2025-12-06 | 69656 | 2029-06-14 | 20593 | WA | Iron Bridge
RD4911 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 58478 | 2024-10-06 | 69656 | 2028-04-20 | 12822 | WA | Iron Bridge
RD4911 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 58478 | 2024-10-06 | 69656 | 2028-04-20 | 12822 | WA | Iron Bridge
RD4911 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 58478 | 2024-10-06 | 69656 | 2028-04-20 | 12822 | WA | Iron Bridge
RD4911 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 58478 | 2024-10-06 | 69656 | 2028-04-20 | 12822 | WA | Iron Bridge
RD4911 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 58478 | 2024-10-06 | 69656 | 2028-04-20 | 12822 | WA | Iron Bridge
RD4911 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 58478 | 2024-10-06 | 69656 | 2028-04-20 | 12822 | WA | Iron Bridge
RD4911 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 63510 | 2025-07-09 | 69656 | 2029-01-17 | 17854 | WA | Iron Bridge
RD4911 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 63150 | 2025-07-09 | 69656 | 2028-12-29 | 17494 | WA | Iron Bridge
RD4911 | Cat 793F | N8140 | Steering Y Piece | 24000 | 63510 | 2025-07-09 | 69656 | 2029-01-17 | 17854 | WA | Iron Bridge
RD4911 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 55873 | 2024-02-23 | 69656 | 2027-08-15 | 8217 | WA | Iron Bridge
RD4911 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 44498 | 2021-05-03 | 69656 | 2025-12-08 | -3158 | WA | Iron Bridge
RD4911 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 60962 | 2025-02-24 | 69656 | 2028-10-25 | 16306 | WA | Iron Bridge
RD4911 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 58843 | 2024-11-06 | 69656 | 2028-07-03 | 14187 | WA | Iron Bridge
RD4911 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 63150 | 2025-07-09 | 69656 | 2027-03-21 | 5494 | WA | Iron Bridge
RD4911 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 63150 | 2025-07-09 | 69656 | 2027-03-21 | 5494 | WA | Iron Bridge
RD4911 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 63510 | 2025-07-09 | 69656 | 2027-04-09 | 5854 | WA | Iron Bridge
RD4911 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 63510 | 2025-07-09 | 69656 | 2027-04-09 | 5854 | WA | Iron Bridge
RD4911 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 63163 | 2025-06-10 | 69656 | 2028-05-27 | 13507 | WA | Iron Bridge
RD4911 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 63163 | 2025-06-11 | 69656 | 2028-05-27 | 13507 | WA | Iron Bridge
RD4911 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 46958 | 2021-10-22 | 69656 | 2026-01-02 | -2698 | WA | Iron Bridge
RD4911 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 63163 | 2025-06-10 | 69656 | 2028-05-27 | 13507 | WA | Iron Bridge
RD4911 | Cat 793F | N8501 | Ball Stud Crack Test |  | 67246 | 2026-01-25 | 69656 | 2026-07-26 |  | WA | Iron Bridge
RD4911 | Cat 793F | N8995 | Operator Seat | 6000 | 65249 | 2025-09-22 | 69656 | 2026-08-22 | 1593 | WA | Iron Bridge
RD4911 | Cat 793F | N9020 | Alternator | 24000 | 59678 | 2024-12-16 | 69656 | 2028-06-24 | 14022 | WA | Iron Bridge
RD4911 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 63508 | 2025-07-01 | 69656 | 2026-02-01 | -2148 | WA | Iron Bridge
RD4911 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 44390 | 2021-04-18 | 69656 | 2026-03-21 | -1266 | WA | Iron Bridge
RD4911 | Cat 793F | N9501 | A/C Compressor | 12000 | 59679 | 2024-12-15 | 69656 | 2026-09-14 | 2023 | WA | Iron Bridge
RD4912 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 52024 | 2025-04-22 | 59538 | 2030-04-21 |  | WA | Iron Bridge
RD4912 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1000 | Engine | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 58508 | 2026-04-01 | 59538 | 2026-11-05 | 2970 | WA | Iron Bridge
RD4912 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 45504 | 2023-10-27 | 59538 | 2024-05-02 | -13984 | WA | Iron Bridge
RD4912 | Cat 793F | N1004 | Engine Midlife | 12000 | 45129 | 2023-10-27 | 59538 | 2026-01-20 | -2409 | WA | Iron Bridge
RD4912 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 56862 | 2026-01-05 | 59538 | 2029-06-27 | 20825 | WA | Iron Bridge
RD4912 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 45129 | 2023-10-27 | 59538 | 2026-01-20 | -2409 | WA | Iron Bridge
RD4912 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 58802 | 2026-04-20 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1210 | Fuel Injectors | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 58802 | 2026-04-20 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N1301 | Water Pump | 12000 | 58802 | 2026-04-19 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N1310 | Radiator | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1315 | Thermostat | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N2000 | Transmission | 18000 | 53141 | 2025-06-23 | 59538 | 2028-02-14 | 11603 | WA | Iron Bridge
RD4912 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 53141 | 2025-06-23 | 59538 | 2028-06-01 | 13603 | WA | Iron Bridge
RD4912 | Cat 793F | N2050 | Torque Convertor | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 45129 | 2023-10-27 | 59538 | 2026-12-08 | 3591 | WA | Iron Bridge
RD4912 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 58802 | 2026-04-19 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 53141 | 2025-06-23 | 59538 | 2027-10-29 | 9603 | WA | Iron Bridge
RD4912 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 53141 | 2025-06-23 | 59538 | 2026-08-23 | 1603 | WA | Iron Bridge
RD4912 | Cat 793F | N3320 | Pump Drive Box | 18000 | 58802 | 2026-04-18 | 59538 | 2028-12-16 | 17264 | WA | Iron Bridge
RD4912 | Cat 793F | N4000 | Bevel Gear | 18000 | 58802 | 2026-04-18 | 59538 | 2028-12-16 | 17264 | WA | Iron Bridge
RD4912 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 31246 | 2019-07-02 | 59538 | 2026-08-28 | 1708 | WA | Iron Bridge
RD4912 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 50004 | 2025-01-06 | 59538 | 2029-06-07 | 20466 | WA | Iron Bridge
RD4912 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 54232 | 2025-08-18 | 59538 | 2029-04-27 | 19694 | WA | Iron Bridge
RD4912 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 45129 | 2023-10-27 | 59538 | 2027-12-21 | 10591 | WA | Iron Bridge
RD4912 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 45486 | 2024-05-19 | 59538 | 2027-08-01 | 7948 | WA | Iron Bridge
RD4912 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 45105 | 2024-04-14 | 59538 | 2027-07-11 | 7567 | WA | Iron Bridge
RD4912 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 45486 | 2024-05-19 | 59538 | 2027-08-01 | 7948 | WA | Iron Bridge
RD4912 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 45105 | 2024-04-14 | 59538 | 2027-07-11 | 7567 | WA | Iron Bridge
RD4912 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 44625 | 2021-12-29 | 59538 | 2026-07-26 | 1087 | WA | Iron Bridge
RD4912 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 44102 | 2021-11-28 | 59538 | 2026-06-27 | 564 | WA | Iron Bridge
RD4912 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 52088 | 2025-05-01 | 59538 | 2029-02-24 | 18550 | WA | Iron Bridge
RD4912 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 52089 | 2025-05-01 | 59538 | 2029-02-24 | 18551 | WA | Iron Bridge
RD4912 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 58802 | 2026-04-17 | 59538 | 2029-07-20 | 21264 | WA | Iron Bridge
RD4912 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 53141 | 2025-06-23 | 59538 | 2028-09-17 | 15603 | WA | Iron Bridge
RD4912 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 58802 | 2026-04-18 | 59538 | 2028-12-16 | 17264 | WA | Iron Bridge
RD4912 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 58508 | 2026-04-02 | 59538 | 2028-11-30 | 16970 | WA | Iron Bridge
RD4912 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 40173 | 2021-03-28 | 59538 | 2027-02-03 | 4635 | WA | Iron Bridge
RD4912 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 40173 | 2021-03-28 | 59538 | 2027-02-03 | 4635 | WA | Iron Bridge
RD4912 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 24125 | 2017-09-14 | 59538 | 2025-02-27 | -8413 | WA | Iron Bridge
RD4912 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 32096 | 2019-10-02 | 59538 | 2026-05-04 | -442 | WA | Iron Bridge
RD4912 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N7605 | Steering Hmu | 24000 | 40173 | 2021-03-28 | 59538 | 2027-02-03 | 4635 | WA | Iron Bridge
RD4912 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 40173 | 2021-03-28 | 59538 | 2027-02-03 | 4635 | WA | Iron Bridge
RD4912 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 48394 | 2024-10-14 | 59538 | 2028-04-22 | 12856 | WA | Iron Bridge
RD4912 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 48394 | 2024-10-14 | 59538 | 2028-04-22 | 12856 | WA | Iron Bridge
RD4912 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 48394 | 2025-10-14 | 59538 | 2028-04-22 | 12856 | WA | Iron Bridge
RD4912 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 48437 | 2024-10-15 | 59538 | 2028-04-24 | 12899 | WA | Iron Bridge
RD4912 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 48437 | 2024-10-15 | 59538 | 2028-04-24 | 12899 | WA | Iron Bridge
RD4912 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 48437 | 2024-10-15 | 59538 | 2028-04-24 | 12899 | WA | Iron Bridge
RD4912 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 45486 | 2024-05-19 | 59538 | 2027-08-01 | 7948 | WA | Iron Bridge
RD4912 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 45129 | 2023-10-27 | 59538 | 2027-07-12 | 7591 | WA | Iron Bridge
RD4912 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 58802 | 2026-04-18 | 59538 | 2029-11-06 | 23264 | WA | Iron Bridge
RD4912 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 58802 | 2026-04-18 | 59538 | 2029-11-06 | 23264 | WA | Iron Bridge
RD4912 | Cat 793F | N8140 | Steering Y Piece | 24000 | 58802 | 2026-04-18 | 59538 | 2029-11-06 | 23264 | WA | Iron Bridge
RD4912 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 47098 | 2024-08-11 | 59538 | 2027-10-27 | 9560 | WA | Iron Bridge
RD4912 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 45105 | 2024-04-14 | 59538 | 2027-07-11 | 7567 | WA | Iron Bridge
RD4912 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 30940 | 2019-06-08 | 59538 | 2025-11-15 | -3598 | WA | Iron Bridge
RD4912 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 30940 | 2019-06-08 | 59538 | 2025-11-15 | -3598 | WA | Iron Bridge
RD4912 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 58802 | 2026-04-18 | 59538 | 2028-01-27 | 11264 | WA | Iron Bridge
RD4912 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 45129 | 2023-10-27 | 59538 | 2027-03-26 | 5591 | WA | Iron Bridge
RD4912 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 45129 | 2023-10-27 | 59538 | 2027-03-26 | 5591 | WA | Iron Bridge
RD4912 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 45129 | 2023-10-27 | 59538 | 2027-03-26 | 5591 | WA | Iron Bridge
RD4912 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 45129 | 2023-10-27 | 59538 | 2027-03-26 | 5591 | WA | Iron Bridge
RD4912 | Cat 793F | N8501 | Ball Stud Crack Test |  | 57281 | 2026-01-25 | 59538 | 2026-07-26 |  | WA | Iron Bridge
RD4912 | Cat 793F | N8995 | Operator Seat | 6000 | 55851 | 2025-11-10 | 59538 | 2026-09-30 | 2313 | WA | Iron Bridge
RD4912 | Cat 793F | N9020 | Alternator | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 56736 | 2025-12-23 | 59538 | 2029-07-17 | 21198 | WA | Iron Bridge
RD4912 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 56736 | 2025-12-23 | 59538 | 2029-07-17 | 21198 | WA | Iron Bridge
RD4912 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 54741 | 2025-09-11 | 59538 | 2026-04-15 | -797 | WA | Iron Bridge
RD4912 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 45129 | 2023-10-27 | 59538 | 2027-10-28 | 9591 | WA | Iron Bridge
RD4912 | Cat 793F | N9501 | A/C Compressor | 12000 | 53585 | 2025-07-15 | 59538 | 2027-04-20 | 6047 | WA | Iron Bridge
RD4913 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 48443 | 2024-10-10 | 59132 | 2029-10-09 |  | WA | Iron Bridge
RD4913 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 50386 | 2025-03-03 | 59132 | 2028-08-30 | 15254 | WA | Iron Bridge
RD4913 | Cat 793F | N1000 | Engine | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 49127 | 2024-12-06 | 59132 | 2025-07-07 | -6005 | WA | Iron Bridge
RD4913 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 50750 | 2025-03-25 | 59132 | 2025-03-04 | -8332 | WA | Iron Bridge
RD4913 | Cat 793F | N1004 | Engine Midlife | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1210 | Fuel Injectors | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N1301 | Water Pump | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N1310 | Radiator | 24000 | 50385 | 2025-03-03 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 50385 | 2025-03-03 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 50385 | 2025-03-03 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1315 | Thermostat | 24000 | 50385 | 2025-03-03 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 50385 | 2025-03-03 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 50385 | 2025-03-04 | 59132 | 2026-11-20 | 3253 | WA | Iron Bridge
RD4913 | Cat 793F | N2000 | Transmission | 18000 | 58084 | 2026-03-28 | 59132 | 2028-11-29 | 16952 | WA | Iron Bridge
RD4913 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 58084 | 2026-03-30 | 59132 | 2029-03-17 | 18952 | WA | Iron Bridge
RD4913 | Cat 793F | N2050 | Torque Convertor | 24000 | 40588 | 2021-05-13 | 59132 | 2027-03-19 | 5456 | WA | Iron Bridge
RD4913 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 58084 | 2026-03-28 | 59132 | 2028-11-29 | 16952 | WA | Iron Bridge
RD4913 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 58166 | 2026-04-05 | 59132 | 2029-10-24 | 23034 | WA | Iron Bridge
RD4913 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 58166 | 2026-04-05 | 59132 | 2028-01-14 | 11034 | WA | Iron Bridge
RD4913 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 56584 | 2026-01-05 | 59132 | 2028-05-24 | 13452 | WA | Iron Bridge
RD4913 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 58084 | 2026-03-30 | 59132 | 2027-06-08 | 6952 | WA | Iron Bridge
RD4913 | Cat 793F | N3320 | Pump Drive Box | 18000 | 43165 | 2021-10-27 | 59132 | 2026-09-15 | 2033 | WA | Iron Bridge
RD4913 | Cat 793F | N4000 | Bevel Gear | 18000 | 45524 | 2023-10-27 | 59132 | 2027-01-20 | 4392 | WA | Iron Bridge
RD4913 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 50386 | 2025-03-03 | 59132 | 2029-07-20 | 21254 | WA | Iron Bridge
RD4913 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 50386 | 2025-03-03 | 59132 | 2029-07-20 | 21254 | WA | Iron Bridge
RD4913 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 45524 | 2023-10-27 | 59132 | 2028-02-03 | 11392 | WA | Iron Bridge
RD4913 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 48824 | 2024-11-13 | 59132 | 2028-07-30 | 14692 | WA | Iron Bridge
RD4913 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 42772 | 2021-09-26 | 59132 | 2026-05-09 | -360 | WA | Iron Bridge
RD4913 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 43649 | 2021-11-24 | 59132 | 2026-06-25 | 517 | WA | Iron Bridge
RD4913 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 42819 | 2021-10-02 | 59132 | 2027-11-03 | 9687 | WA | Iron Bridge
RD4913 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 42819 | 2021-10-02 | 59132 | 2027-11-03 | 9687 | WA | Iron Bridge
RD4913 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 42686 | 2021-09-13 | 59132 | 2027-03-24 | 5554 | WA | Iron Bridge
RD4913 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 45524 | 2023-10-27 | 59132 | 2027-08-25 | 8392 | WA | Iron Bridge
RD4913 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 58084 | 2026-03-29 | 59132 | 2028-11-29 | 16952 | WA | Iron Bridge
RD4913 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 58084 | 2026-03-29 | 59132 | 2028-11-29 | 16952 | WA | Iron Bridge
RD4913 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 39026 | 2021-01-29 | 59132 | 2026-12-24 | 3894 | WA | Iron Bridge
RD4913 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 39026 | 2021-01-29 | 59132 | 2026-12-24 | 3894 | WA | Iron Bridge
RD4913 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 50385 | 2025-03-03 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 22474 | 2017-06-11 | 59132 | 2024-12-22 | -9658 | WA | Iron Bridge
RD4913 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 54953 | 2025-10-22 | 59132 | 2029-10-13 | 22821 | WA | Iron Bridge
RD4913 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 45524 | 2023-10-27 | 59132 | 2026-03-02 | -1608 | WA | Iron Bridge
RD4913 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 58084 | 2026-03-29 | 59132 | 2028-01-10 | 10952 | WA | Iron Bridge
RD4913 | Cat 793F | N7605 | Steering Hmu | 24000 | 56986 | 2026-01-27 | 59132 | 2029-08-21 | 21854 | WA | Iron Bridge
RD4913 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 39026 | 2021-01-29 | 59132 | 2026-12-24 | 3894 | WA | Iron Bridge
RD4913 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 49127 | 2024-12-07 | 59132 | 2028-06-22 | 13995 | WA | Iron Bridge
RD4913 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 49127 | 2024-12-07 | 59132 | 2028-06-22 | 13995 | WA | Iron Bridge
RD4913 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 49127 | 2024-12-07 | 59132 | 2028-06-22 | 13995 | WA | Iron Bridge
RD4913 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 49127 | 2024-12-03 | 59132 | 2028-06-22 | 13995 | WA | Iron Bridge
RD4913 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 49127 | 2024-12-03 | 59132 | 2028-06-22 | 13995 | WA | Iron Bridge
RD4913 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 49127 | 2024-12-04 | 59132 | 2028-06-22 | 13995 | WA | Iron Bridge
RD4913 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 58084 | 2026-03-28 | 59132 | 2029-10-20 | 22952 | WA | Iron Bridge
RD4913 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 58084 | 2026-03-29 | 59132 | 2029-10-20 | 22952 | WA | Iron Bridge
RD4913 | Cat 793F | N8140 | Steering Y Piece | 24000 | 53890 | 2025-08-13 | 59132 | 2029-03-07 | 18758 | WA | Iron Bridge
RD4913 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 42819 | 2021-10-02 | 59132 | 2027-03-31 | 5687 | WA | Iron Bridge
RD4913 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 50386 | 2025-03-06 | 59132 | 2028-10-23 | 16254 | WA | Iron Bridge
RD4913 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 50386 | 2025-03-06 | 59132 | 2028-10-23 | 16254 | WA | Iron Bridge
RD4913 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 58084 | 2026-03-29 | 59132 | 2028-01-10 | 10952 | WA | Iron Bridge
RD4913 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 58084 | 2026-03-29 | 59132 | 2028-01-10 | 10952 | WA | Iron Bridge
RD4913 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 45497 | 2023-10-27 | 59132 | 2026-03-01 | -1635 | WA | Iron Bridge
RD4913 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 45497 | 2023-10-27 | 59132 | 2026-03-01 | -1635 | WA | Iron Bridge
RD4913 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 49127 | 2024-12-04 | 59132 | 2027-11-19 | 9995 | WA | Iron Bridge
RD4913 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 44110 | 2021-12-22 | 59132 | 2027-02-21 | 4978 | WA | Iron Bridge
RD4913 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 49127 | 2024-12-05 | 59132 | 2027-11-19 | 9995 | WA | Iron Bridge
RD4913 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 49127 | 2024-12-06 | 59132 | 2027-11-19 | 9995 | WA | Iron Bridge
RD4913 | Cat 793F | N8501 | Ball Stud Crack Test |  | 56989 | 2026-01-27 | 59132 | 2026-07-28 |  | WA | Iron Bridge
RD4913 | Cat 793F | N8995 | Operator Seat | 6000 | 58084 | 2026-03-29 | 59132 | 2027-02-20 | 4952 | WA | Iron Bridge
RD4913 | Cat 793F | N9020 | Alternator | 24000 | 50385 | 2025-03-04 | 59132 | 2028-08-29 | 15253 | WA | Iron Bridge
RD4913 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 58037 | 2026-03-25 | 59132 | 2029-10-17 | 22905 | WA | Iron Bridge
RD4913 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 58037 | 2026-03-25 | 59132 | 2029-10-17 | 22905 | WA | Iron Bridge
RD4913 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 54678 | 2025-10-06 | 59132 | 2026-05-03 | -454 | WA | Iron Bridge
RD4913 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 50386 | 2025-03-03 | 59132 | 2028-08-30 | 15254 | WA | Iron Bridge
RD4913 | Cat 793F | N9501 | A/C Compressor | 12000 | 49127 | 2024-12-04 | 59132 | 2026-09-13 | 1995 | WA | Iron Bridge
RD4914 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 57643 | 2025-04-17 | 65591 | 2030-04-16 |  | WA | Iron Bridge
RD4914 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 55077 | 2024-11-09 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1000 | Engine | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 67698 | 2025-09-22 | 65591 | 2027-04-23 | 6107 | WA | Iron Bridge
RD4914 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 55555 | 2024-12-09 | 65591 | 2024-12-04 | -9986 | WA | Iron Bridge
RD4914 | Cat 793F | N1004 | Engine Midlife | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1210 | Fuel Injectors | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N1301 | Water Pump | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N1310 | Radiator | 24000 | 50629 | 2023-10-27 | 65591 | 2027-09-29 | 9038 | WA | Iron Bridge
RD4914 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 50629 | 2023-10-27 | 65591 | 2027-09-29 | 9038 | WA | Iron Bridge
RD4914 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 50629 | 2023-10-27 | 65591 | 2027-09-29 | 9038 | WA | Iron Bridge
RD4914 | Cat 793F | N1315 | Thermostat | 24000 | 52188 | 2024-06-21 | 65591 | 2027-12-22 | 10597 | WA | Iron Bridge
RD4914 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 50629 | 2023-10-27 | 65591 | 2027-09-29 | 9038 | WA | Iron Bridge
RD4914 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4914 | Cat 793F | N2000 | Transmission | 18000 | 55792 | 2025-01-02 | 65591 | 2027-08-14 | 8201 | WA | Iron Bridge
RD4914 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 50629 | 2023-10-27 | 65591 | 2027-02-24 | 5038 | WA | Iron Bridge
RD4914 | Cat 793F | N2050 | Torque Convertor | 24000 | 37677 | 2019-08-25 | 65591 | 2025-10-25 | -3914 | WA | Iron Bridge
RD4914 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 50629 | 2023-10-27 | 65591 | 2026-11-26 | 3038 | WA | Iron Bridge
RD4914 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 50629 | 2023-10-27 | 65591 | 2027-09-29 | 9038 | WA | Iron Bridge
RD4914 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 50629 | 2023-10-27 | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 55077 | 2024-11-11 | 65591 | 2027-03-21 | 5486 | WA | Iron Bridge
RD4914 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 55077 | 2024-11-10 | 65591 | 2026-01-13 | -2514 | WA | Iron Bridge
RD4914 | Cat 793F | N3320 | Pump Drive Box | 18000 | 50629 | 2023-10-27 | 65591 | 2026-11-08 | 3038 | WA | Iron Bridge
RD4914 | Cat 793F | N4000 | Bevel Gear | 18000 | 60253 | 2025-08-23 | 65591 | 2028-04-11 | 12662 | WA | Iron Bridge
RD4914 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 61339 | 2025-10-20 | 65591 | 2030-03-20 | 25748 | WA | Iron Bridge
RD4914 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 61339 | 2025-10-20 | 65591 | 2030-03-20 | 25748 | WA | Iron Bridge
RD4914 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 50629 | 2023-10-27 | 65591 | 2027-11-22 | 10038 | WA | Iron Bridge
RD4914 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 53753 | 2024-09-06 | 65591 | 2028-05-08 | 13162 | WA | Iron Bridge
RD4914 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 48746 | 2021-11-12 | 65591 | 2026-04-18 | -845 | WA | Iron Bridge
RD4914 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 63269 | 2026-01-26 | 65591 | 2028-06-05 | 13678 | WA | Iron Bridge
RD4914 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 47257 | 2021-08-10 | 65591 | 2027-07-16 | 7666 | WA | Iron Bridge
RD4914 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 47257 | 2021-08-10 | 65591 | 2027-07-16 | 7666 | WA | Iron Bridge
RD4914 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 47203 | 2021-07-29 | 65591 | 2026-12-09 | 3612 | WA | Iron Bridge
RD4914 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 50629 | 2023-10-27 | 65591 | 2027-06-12 | 7038 | WA | Iron Bridge
RD4914 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 50629 | 2023-10-27 | 65591 | 2026-11-08 | 3038 | WA | Iron Bridge
RD4914 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 63840 | 2026-02-25 | 65591 | 2028-10-22 | 16249 | WA | Iron Bridge
RD4914 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 45383 | 2021-03-13 | 65591 | 2026-12-19 | 3792 | WA | Iron Bridge
RD4914 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 45383 | 2021-03-13 | 65591 | 2026-12-19 | 3792 | WA | Iron Bridge
RD4914 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 50629 | 2023-10-27 | 65591 | 2027-09-29 | 9038 | WA | Iron Bridge
RD4914 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 29304 | 2018-01-19 | 65591 | 2025-01-11 | -9287 | WA | Iron Bridge
RD4914 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 69132 | 2026-05-04 | 65591 | 2030-12-04 | 30541 | WA | Iron Bridge
RD4914 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 60527 | 2025-09-09 | 65591 | 2027-06-07 | 6936 | WA | Iron Bridge
RD4914 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 50629 | 2023-10-27 | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N7605 | Steering Hmu | 24000 | 62427 | 2025-12-15 | 65591 | 2029-06-27 | 20836 | WA | Iron Bridge
RD4914 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 57042 | 2025-03-17 | 65591 | 2028-09-09 | 15451 | WA | Iron Bridge
RD4914 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 55077 | 2024-11-11 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 55077 | 2024-11-11 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 64842 | 2026-04-20 | 65591 | 2029-11-05 | 23251 | WA | Iron Bridge
RD4914 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 55077 | 2024-11-14 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 55077 | 2024-11-13 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 55077 | 2024-11-13 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 38629 |  | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 38629 |  | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N8140 | Steering Y Piece | 24000 | 38629 |  | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 47257 | 2021-08-10 | 65591 | 2026-12-12 | 3666 | WA | Iron Bridge
RD4914 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 45902 | 2021-04-22 | 65591 | 2027-03-11 | 5311 | WA | Iron Bridge
RD4914 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 45902 | 2021-04-22 | 65591 | 2027-03-11 | 5311 | WA | Iron Bridge
RD4914 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 50629 | 2023-10-27 | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 50629 | 2023-10-27 | 65591 | 2025-12-18 | -2962 | WA | Iron Bridge
RD4914 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 60527 | 2025-09-09 | 65591 | 2027-06-07 | 6936 | WA | Iron Bridge
RD4914 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 60527 | 2025-09-09 | 65591 | 2027-06-07 | 6936 | WA | Iron Bridge
RD4914 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 50629 | 2023-10-27 | 65591 | 2027-02-24 | 5038 | WA | Iron Bridge
RD4914 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 56995 | 2025-03-11 | 65591 | 2028-02-03 | 11404 | WA | Iron Bridge
RD4914 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 62427 |  | 65591 | 2028-11-24 | 16836 | WA | Iron Bridge
RD4914 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 62427 |  | 65591 | 2028-11-24 | 16836 | WA | Iron Bridge
RD4914 | Cat 793F | N8501 | Ball Stud Crack Test |  | 63355 | 2026-01-30 | 65591 | 2026-07-31 |  | WA | Iron Bridge
RD4914 | Cat 793F | N8995 | Operator Seat | 6000 | 65275 | 2026-05-12 | 65591 | 2027-03-31 | 5684 | WA | Iron Bridge
RD4914 | Cat 793F | N9020 | Alternator | 24000 | 55792 | 2025-01-02 | 65591 | 2028-07-04 | 14201 | WA | Iron Bridge
RD4914 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 55077 | 2024-11-12 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 59706 | 2025-07-26 | 65591 | 2026-02-17 | -1885 | WA | Iron Bridge
RD4914 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 55077 | 2024-11-15 | 65591 | 2028-05-26 | 13486 | WA | Iron Bridge
RD4914 | Cat 793F | N9501 | A/C Compressor | 12000 | 55077 | 2024-11-12 | 65591 | 2026-08-16 | 1486 | WA | Iron Bridge
RD4915 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 59668 | 2025-06-19 | 65324 | 2030-06-18 |  | WA | Iron Bridge
RD4915 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 63678 | 2026-02-28 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N1000 | Engine | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 63679 | 2026-03-04 | 65324 | 2026-10-02 | 2355 | WA | Iron Bridge
RD4915 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 63719 | 2026-03-06 | 65324 | 2026-03-05 | -1555 | WA | Iron Bridge
RD4915 | Cat 793F | N1004 | Engine Midlife | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1210 | Fuel Injectors | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N1301 | Water Pump | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N1310 | Radiator | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N1315 | Thermostat | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4915 | Cat 793F | N2000 | Transmission | 18000 | 63318 | 2026-02-07 | 65324 | 2028-10-09 | 15994 | WA | Iron Bridge
RD4915 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 58503 | 2025-03-05 | 65324 | 2028-05-09 | 13179 | WA | Iron Bridge
RD4915 | Cat 793F | N2050 | Torque Convertor | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 53653 | 2024-02-23 | 65324 | 2027-05-05 | 6329 | WA | Iron Bridge
RD4915 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 52063 | 2023-03-20 | 65324 | 2027-12-29 | 10739 | WA | Iron Bridge
RD4915 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 63678 | 2026-02-28 | 65324 | 2027-12-09 | 10354 | WA | Iron Bridge
RD4915 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 55877 | 2024-10-10 | 65324 | 2027-05-17 | 6553 | WA | Iron Bridge
RD4915 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 63678 | 2026-03-02 | 65324 | 2027-05-06 | 6354 | WA | Iron Bridge
RD4915 | Cat 793F | N3320 | Pump Drive Box | 18000 | 57383 | 2025-01-18 | 65324 | 2027-11-23 | 10059 | WA | Iron Bridge
RD4915 | Cat 793F | N4000 | Bevel Gear | 18000 | 63678 | 2026-03-02 | 65324 | 2028-10-28 | 16354 | WA | Iron Bridge
RD4915 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 63678 | 2026-03-02 | 65324 | 2030-08-08 | 28354 | WA | Iron Bridge
RD4915 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 63678 | 2026-03-02 | 65324 | 2030-08-08 | 28354 | WA | Iron Bridge
RD4915 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 52279 | 2023-10-31 | 65324 | 2028-03-04 | 11955 | WA | Iron Bridge
RD4915 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 52279 | 2023-10-31 | 65324 | 2028-03-04 | 11955 | WA | Iron Bridge
RD4915 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 61275 | 2025-09-19 | 65324 | 2029-01-22 | 17951 | WA | Iron Bridge
RD4915 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 52279 | 2023-10-31 | 65324 | 2027-09-24 | 8955 | WA | Iron Bridge
RD4915 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 61275 | 2025-09-19 | 65324 | 2029-01-22 | 17951 | WA | Iron Bridge
RD4915 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 52279 | 2023-10-31 | 65324 | 2027-09-24 | 8955 | WA | Iron Bridge
RD4915 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 50338 | 2022-01-23 | 65324 | 2026-07-22 | 1014 | WA | Iron Bridge
RD4915 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 59675 | 2025-06-18 | 65324 | 2027-12-09 | 10351 | WA | Iron Bridge
RD4915 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 52279 | 2023-10-31 | 65324 | 2028-04-27 | 12955 | WA | Iron Bridge
RD4915 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 52279 | 2023-10-31 | 65324 | 2028-04-27 | 12955 | WA | Iron Bridge
RD4915 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 62224 | 2025-11-17 | 65324 | 2029-03-15 | 18900 | WA | Iron Bridge
RD4915 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 62298 | 2025-11-22 | 65324 | 2029-03-19 | 18974 | WA | Iron Bridge
RD4915 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 57383 | 2025-01-17 | 65324 | 2027-11-23 | 10059 | WA | Iron Bridge
RD4915 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 57383 | 2025-01-17 | 65324 | 2027-11-23 | 10059 | WA | Iron Bridge
RD4915 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 63678 | 2026-03-02 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 29298 | 2018-03-12 | 65324 | 2025-01-25 | -9026 | WA | Iron Bridge
RD4915 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 63318 | 2026-02-08 | 65324 | 2030-02-07 | 24994 | WA | Iron Bridge
RD4915 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 57079 | 2025-01-03 | 65324 | 2026-12-17 | 3755 | WA | Iron Bridge
RD4915 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 57079 | 2025-01-03 | 65324 | 2026-12-17 | 3755 | WA | Iron Bridge
RD4915 | Cat 793F | N7605 | Steering Hmu | 24000 | 63678 | 2026-03-03 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 63678 | 2026-03-01 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 57388 | 2025-01-18 | 65324 | 2028-10-12 | 16064 | WA | Iron Bridge
RD4915 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 57388 | 2025-01-18 | 65324 | 2028-10-12 | 16064 | WA | Iron Bridge
RD4915 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 57388 | 2025-01-18 | 65324 | 2028-10-12 | 16064 | WA | Iron Bridge
RD4915 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 57383 | 2025-01-17 | 65324 | 2028-10-12 | 16059 | WA | Iron Bridge
RD4915 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 57383 | 2025-01-17 | 65324 | 2028-10-12 | 16059 | WA | Iron Bridge
RD4915 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 57383 | 2025-01-16 | 65324 | 2028-10-12 | 16059 | WA | Iron Bridge
RD4915 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 61275 | 2025-09-19 | 65324 | 2029-01-22 | 17951 | WA | Iron Bridge
RD4915 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 52279 | 2023-10-31 | 65324 | 2027-09-24 | 8955 | WA | Iron Bridge
RD4915 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 56861 | 2024-12-17 | 65324 | 2028-09-14 | 15537 | WA | Iron Bridge
RD4915 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 56861 | 2024-12-17 | 65324 | 2028-09-14 | 15537 | WA | Iron Bridge
RD4915 | Cat 793F | N8140 | Steering Y Piece | 24000 | 56861 | 2024-12-17 | 65324 | 2028-09-14 | 15537 | WA | Iron Bridge
RD4915 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 52279 | 2023-10-31 | 65324 | 2027-09-24 | 8955 | WA | Iron Bridge
RD4915 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 52279 | 2023-10-31 | 65324 | 2027-09-24 | 8955 | WA | Iron Bridge
RD4915 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 57388 | 2025-01-19 | 65324 | 2028-12-05 | 17064 | WA | Iron Bridge
RD4915 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 57388 | 2025-01-20 | 65324 | 2028-12-05 | 17064 | WA | Iron Bridge
RD4915 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 57079 | 2025-01-03 | 65324 | 2026-12-17 | 3755 | WA | Iron Bridge
RD4915 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 57079 | 2025-01-03 | 65324 | 2026-12-17 | 3755 | WA | Iron Bridge
RD4915 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 57079 | 2025-01-03 | 65324 | 2026-12-17 | 3755 | WA | Iron Bridge
RD4915 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 57079 | 2025-01-03 | 65324 | 2026-12-17 | 3755 | WA | Iron Bridge
RD4915 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 57984 | 2025-03-08 | 65324 | 2028-04-11 | 12660 | WA | Iron Bridge
RD4915 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 56265 | 2024-11-09 | 65324 | 2028-01-09 | 10941 | WA | Iron Bridge
RD4915 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 58503 | 2025-04-04 | 65324 | 2028-05-09 | 13179 | WA | Iron Bridge
RD4915 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 58503 | 2025-04-04 | 65324 | 2028-05-09 | 13179 | WA | Iron Bridge
RD4915 | Cat 793F | N8501 | Ball Stud Crack Test |  | 63071 | 2026-01-25 | 65324 | 2026-07-26 |  | WA | Iron Bridge
RD4915 | Cat 793F | N8995 | Operator Seat | 6000 | 62077 | 2025-11-04 | 65324 | 2026-10-24 | 2753 | WA | Iron Bridge
RD4915 | Cat 793F | N9020 | Alternator | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 63679 | 2026-03-04 | 65324 | 2029-09-17 | 22355 | WA | Iron Bridge
RD4915 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 61567 | 2025-10-07 | 65324 | 2026-06-10 | 243 | WA | Iron Bridge
RD4915 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 63678 | 2026-03-03 | 65324 | 2029-09-17 | 22354 | WA | Iron Bridge
RD4915 | Cat 793F | N9501 | A/C Compressor | 12000 | 63679 | 2026-03-04 | 65324 | 2027-12-09 | 10355 | WA | Iron Bridge
RD4916 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-08-01 | 69482 | 2028-07-30 |  | WA | Iron Bridge
RD4916 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 63301 | 2025-06-01 | 69482 | 2029-01-15 | 17819 | WA | Iron Bridge
RD4916 | Cat 793F | N1000 | Engine | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 64973 | 2025-09-21 | 69482 | 2026-05-06 | -509 | WA | Iron Bridge
RD4916 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 64973 | 2025-09-21 | 69482 | 2025-09-29 | -4459 | WA | Iron Bridge
RD4916 | Cat 793F | N1004 | Engine Midlife | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1210 | Fuel Injectors | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N1301 | Water Pump | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N1310 | Radiator | 24000 | 64267 | 2025-08-11 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 64267 | 2025-08-11 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 64267 | 2025-08-11 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1315 | Thermostat | 24000 | 64267 | 2025-08-11 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 64267 | 2025-08-11 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4916 | Cat 793F | N2000 | Transmission | 18000 | 59178 | 2024-10-05 | 69482 | 2027-07-18 | 7696 | WA | Iron Bridge
RD4916 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 59178 | 2024-10-06 | 69482 | 2027-11-03 | 9696 | WA | Iron Bridge
RD4916 | Cat 793F | N2050 | Torque Convertor | 24000 | 64267 | 2025-08-09 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 64267 | 2025-08-09 | 69482 | 2028-04-18 | 12785 | WA | Iron Bridge
RD4916 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 53317 | 2023-08-16 | 69482 | 2027-07-26 | 7835 | WA | Iron Bridge
RD4916 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 66298 | 2025-12-13 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 52539 | 2023-02-20 | 69482 | 2026-04-07 | -943 | WA | Iron Bridge
RD4916 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 66298 | 2025-12-13 | 69482 | 2027-02-12 | 4816 | WA | Iron Bridge
RD4916 | Cat 793F | N3320 | Pump Drive Box | 18000 | 79178 | 2024-10-06 | 69482 | 2030-07-03 | 27696 | WA | Iron Bridge
RD4916 | Cat 793F | N4000 | Bevel Gear | 18000 | 62524 | 2025-04-22 | 69482 | 2028-01-15 | 11042 | WA | Iron Bridge
RD4916 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 62524 | 2025-04-22 | 69482 | 2029-10-25 | 23042 | WA | Iron Bridge
RD4916 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 62524 | 2025-04-22 | 69482 | 2029-10-25 | 23042 | WA | Iron Bridge
RD4916 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 47451 | 2022-01-29 | 69482 | 2026-11-04 | 2969 | WA | Iron Bridge
RD4916 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 45851 | 2021-10-09 | 69482 | 2026-08-10 | 1369 | WA | Iron Bridge
RD4916 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 50567 | 2022-09-29 | 69482 | 2026-03-26 | -2915 | WA | Iron Bridge
RD4916 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 52539 | 2023-02-20 | 69482 | 2026-04-12 | -943 | WA | Iron Bridge
RD4916 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 64504 | 2025-08-30 | 69482 | 2029-07-07 | 21022 | WA | Iron Bridge
RD4916 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 65757 | 2025-11-15 | 69482 | 2029-09-13 | 22275 | WA | Iron Bridge
RD4916 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 43980 | 2021-05-24 | 69482 | 2026-03-26 | -3502 | WA | Iron Bridge
RD4916 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 59176 | 2024-10-05 | 69482 | 2028-02-19 | 11694 | WA | Iron Bridge
RD4916 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 59176 | 2024-10-06 | 69482 | 2027-07-18 | 7694 | WA | Iron Bridge
RD4916 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 52701 | 2023-03-06 | 69482 | 2026-08-02 | 1219 | WA | Iron Bridge
RD4916 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 52701 | 2023-03-06 | 69482 | 2027-06-22 | 7219 | WA | Iron Bridge
RD4916 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 52701 | 2023-03-06 | 69482 | 2027-06-22 | 7219 | WA | Iron Bridge
RD4916 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 64267 | 2025-08-11 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 50388 | 2022-09-20 | 69482 | 2027-07-29 | 7906 | WA | Iron Bridge
RD4916 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 37404 | 2020-02-27 | 69482 | 2025-08-27 | -5078 | WA | Iron Bridge
RD4916 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 66298 | 2025-12-12 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 66298 | 2025-12-12 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N7605 | Steering Hmu | 24000 | 52701 | 2023-03-06 | 69482 | 2027-06-22 | 7219 | WA | Iron Bridge
RD4916 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 60237 | 2024-12-08 | 69482 | 2028-08-03 | 14755 | WA | Iron Bridge
RD4916 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 59176 | 2024-10-07 | 69482 | 2028-06-06 | 13694 | WA | Iron Bridge
RD4916 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 59176 | 2024-10-07 | 69482 | 2028-06-06 | 13694 | WA | Iron Bridge
RD4916 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 59176 | 2024-10-07 | 69482 | 2028-06-06 | 13694 | WA | Iron Bridge
RD4916 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 59178 | 2024-10-06 | 69482 | 2028-06-06 | 13696 | WA | Iron Bridge
RD4916 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 59178 | 2024-10-07 | 69482 | 2028-06-06 | 13696 | WA | Iron Bridge
RD4916 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 59178 | 2024-10-07 | 69482 | 2028-06-06 | 13696 | WA | Iron Bridge
RD4916 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 63301 | 2025-06-01 | 69482 | 2029-01-15 | 17819 | WA | Iron Bridge
RD4916 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 63301 | 2025-06-02 | 69482 | 2029-01-15 | 17819 | WA | Iron Bridge
RD4916 | Cat 793F | N8140 | Steering Y Piece | 24000 | 58716 | 2024-09-13 | 69482 | 2028-05-12 | 13234 | WA | Iron Bridge
RD4916 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 66298 | 2025-12-15 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 66298 | 2025-12-14 | 69482 | 2029-03-10 | 18816 | WA | Iron Bridge
RD4916 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 62524 | 2025-04-22 | 69482 | 2029-01-27 | 18042 | WA | Iron Bridge
RD4916 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 42588 | 2021-01-29 | 69482 | 2026-02-15 | -1894 | WA | Iron Bridge
RD4916 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 66298 | 2025-12-12 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 66298 | 2025-12-12 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 66298 | 2025-12-12 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 66298 | 2025-12-12 | 69482 | 2027-09-17 | 8816 | WA | Iron Bridge
RD4916 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 59178 | 2024-10-07 | 69482 | 2027-11-03 | 9696 | WA | Iron Bridge
RD4916 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 59178 | 2024-10-09 | 69482 | 2027-11-03 | 9696 | WA | Iron Bridge
RD4916 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 59178 | 2024-10-09 | 69482 | 2027-11-03 | 9696 | WA | Iron Bridge
RD4916 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 59178 | 2024-10-09 | 69482 | 2027-11-03 | 9696 | WA | Iron Bridge
RD4916 | Cat 793F | N8501 | Ball Stud Crack Test |  | 67141 | 2026-01-28 | 69482 | 2026-07-29 |  | WA | Iron Bridge
RD4916 | Cat 793F | N8995 | Operator Seat | 6000 | 64973 | 2025-09-20 | 69482 | 2026-08-17 | 1491 | WA | Iron Bridge
RD4916 | Cat 793F | N9020 | Alternator | 24000 | 65188 | 2025-10-18 | 69482 | 2029-04-27 | 19706 | WA | Iron Bridge
RD4916 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 64267 | 2025-08-14 | 69482 | 2029-03-08 | 18785 | WA | Iron Bridge
RD4916 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 64973 | 2025-09-21 | 69482 | 2026-05-07 | -509 | WA | Iron Bridge
RD4916 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 43980 | 2021-05-24 | 69482 | 2026-03-08 | -1502 | WA | Iron Bridge
RD4916 | Cat 793F | N9501 | A/C Compressor | 12000 | 64267 | 2025-08-14 | 69482 | 2027-05-30 | 6785 | WA | Iron Bridge
RD4917 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 61786 | 2025-04-21 | 69200 | 2030-04-20 |  | WA | Iron Bridge
RD4917 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1000 | Engine | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 60448 | 2025-02-05 | 69200 | 2025-08-31 | -4752 | WA | Iron Bridge
RD4917 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 43464 | 2021-03-23 | 69200 | 2022-05-23 | -25686 | WA | Iron Bridge
RD4917 | Cat 793F | N1004 | Engine Midlife | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1210 | Fuel Injectors | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N1301 | Water Pump | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N1310 | Radiator | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1315 | Thermostat | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 53461 | 2023-08-16 | 69200 | 2025-10-28 | -3739 | WA | Iron Bridge
RD4917 | Cat 793F | N2000 | Transmission | 18000 | 61313 | 2025-03-26 | 69200 | 2027-11-26 | 10113 | WA | Iron Bridge
RD4917 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 61311 | 2025-03-03 | 69200 | 2028-03-13 | 12111 | WA | Iron Bridge
RD4917 | Cat 793F | N2050 | Torque Convertor | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 61415 | 2025-03-03 | 69200 | 2028-01-03 | 10215 | WA | Iron Bridge
RD4917 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 53461 | 2023-08-16 | 69200 | 2027-08-18 | 8261 | WA | Iron Bridge
RD4917 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 67144 | 2026-02-02 | 69200 | 2027-11-17 | 9944 | WA | Iron Bridge
RD4917 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 57974 | 2024-09-24 | 69200 | 2027-02-10 | 4774 | WA | Iron Bridge
RD4917 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 67144 | 2026-02-02 | 69200 | 2027-04-14 | 5944 | WA | Iron Bridge
RD4917 | Cat 793F | N3320 | Pump Drive Box | 18000 | 61415 | 2025-03-03 | 69200 | 2027-12-01 | 10215 | WA | Iron Bridge
RD4917 | Cat 793F | N4000 | Bevel Gear | 18000 | 61313 | 2025-03-25 | 69200 | 2027-11-26 | 10113 | WA | Iron Bridge
RD4917 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 61313 | 2025-03-25 | 69200 | 2029-09-04 | 22113 | WA | Iron Bridge
RD4917 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 61313 | 2025-03-25 | 69200 | 2029-09-04 | 22113 | WA | Iron Bridge
RD4917 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 62785 | 2025-06-17 | 69200 | 2029-02-26 | 18585 | WA | Iron Bridge
RD4917 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 67760 | 2026-03-09 | 69200 | 2029-11-22 | 23560 | WA | Iron Bridge
RD4917 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 44844 | 2021-07-04 | 69200 | 2026-01-15 | -2356 | WA | Iron Bridge
RD4917 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 47868 | 2022-01-07 | 69200 | 2026-07-07 | 668 | WA | Iron Bridge
RD4917 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 44844 | 2021-07-04 | 69200 | 2026-01-15 | -2356 | WA | Iron Bridge
RD4917 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 47868 | 2022-01-07 | 69200 | 2026-07-07 | 668 | WA | Iron Bridge
RD4917 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 50446 | 2022-08-28 | 69200 | 2025-12-23 | -2754 | WA | Iron Bridge
RD4917 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 50947 | 2022-10-02 | 69200 | 2026-01-21 | -2253 | WA | Iron Bridge
RD4917 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 44844 | 2021-07-04 | 69200 | 2026-09-01 | 1644 | WA | Iron Bridge
RD4917 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 47868 | 2022-01-07 | 69200 | 2027-02-04 | 4668 | WA | Iron Bridge
RD4917 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 43464 | 2021-03-23 | 69200 | 2025-10-28 | -3736 | WA | Iron Bridge
RD4917 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 53461 | 2023-08-16 | 69200 | 2027-05-01 | 6261 | WA | Iron Bridge
RD4917 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 66742 | 2026-01-14 | 69200 | 2028-09-14 | 15542 | WA | Iron Bridge
RD4917 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 57974 | 2024-09-24 | 69200 | 2027-05-29 | 6774 | WA | Iron Bridge
RD4917 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 61415 | 2025-03-03 | 69200 | 2028-10-20 | 16215 | WA | Iron Bridge
RD4917 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 66179 | 2025-12-07 | 69200 | 2029-07-05 | 20979 | WA | Iron Bridge
RD4917 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 57989 | 2024-09-24 | 69200 | 2028-09-27 | 15789 | WA | Iron Bridge
RD4917 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 66179 | 2025-12-08 | 69200 | 2029-12-14 | 23979 | WA | Iron Bridge
RD4917 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 64145 | 2025-08-20 | 69200 | 2027-06-07 | 6945 | WA | Iron Bridge
RD4917 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 64145 | 2025-08-20 | 69200 | 2027-06-07 | 6945 | WA | Iron Bridge
RD4917 | Cat 793F | N7605 | Steering Hmu | 24000 | 60961 | 2025-03-07 | 69200 | 2028-09-26 | 15761 | WA | Iron Bridge
RD4917 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 60054 | 2025-01-17 | 69200 | 2028-08-08 | 14854 | WA | Iron Bridge
RD4917 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 57974 | 2024-09-23 | 69200 | 2028-04-17 | 12774 | WA | Iron Bridge
RD4917 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 57974 | 2024-09-23 | 69200 | 2028-04-17 | 12774 | WA | Iron Bridge
RD4917 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 57974 | 2024-09-23 | 69200 | 2028-04-17 | 12774 | WA | Iron Bridge
RD4917 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 57974 | 2024-09-23 | 69200 | 2028-04-17 | 12774 | WA | Iron Bridge
RD4917 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 57974 | 2024-09-23 | 69200 | 2028-04-17 | 12774 | WA | Iron Bridge
RD4917 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 57974 | 2024-09-23 | 69200 | 2028-04-17 | 12774 | WA | Iron Bridge
RD4917 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 44844 | 2021-07-04 | 69200 | 2026-01-15 | -2356 | WA | Iron Bridge
RD4917 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 47868 | 2022-01-07 | 69200 | 2026-07-07 | 668 | WA | Iron Bridge
RD4917 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 64145 | 2025-08-20 | 69200 | 2029-03-17 | 18945 | WA | Iron Bridge
RD4917 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 64145 | 2025-08-20 | 69200 | 2029-03-17 | 18945 | WA | Iron Bridge
RD4917 | Cat 793F | N8140 | Steering Y Piece | 24000 | 64145 | 2025-08-20 | 69200 | 2029-03-17 | 18945 | WA | Iron Bridge
RD4917 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 68088 | 2026-04-01 | 69200 | 2029-06-30 | 20888 | WA | Iron Bridge
RD4917 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 47868 | 2022-01-07 | 69200 | 2026-07-07 | 668 | WA | Iron Bridge
RD4917 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 64642 | 2025-09-16 | 69200 | 2029-06-06 | 20442 | WA | Iron Bridge
RD4917 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 64642 | 2025-09-16 | 69200 | 2029-06-06 | 20442 | WA | Iron Bridge
RD4917 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 64145 | 2025-08-20 | 69200 | 2027-06-07 | 6945 | WA | Iron Bridge
RD4917 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 64145 | 2025-08-20 | 69200 | 2027-06-07 | 6945 | WA | Iron Bridge
RD4917 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 64145 | 2025-08-20 | 69200 | 2027-06-07 | 6945 | WA | Iron Bridge
RD4917 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 64145 | 2025-08-20 | 69200 | 2027-06-07 | 6945 | WA | Iron Bridge
RD4917 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 64145 | 2025-08-21 | 69200 | 2028-08-13 | 14945 | WA | Iron Bridge
RD4917 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 64145 | 2025-08-21 | 69200 | 2028-08-13 | 14945 | WA | Iron Bridge
RD4917 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 57974 | 2024-09-26 | 69200 | 2027-09-14 | 8774 | WA | Iron Bridge
RD4917 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 64146 | 2025-08-22 | 69200 | 2028-08-13 | 14946 | WA | Iron Bridge
RD4917 | Cat 793F | N8501 | Ball Stud Crack Test |  | 67093 | 2026-01-30 | 69200 | 2026-07-31 |  | WA | Iron Bridge
RD4917 | Cat 793F | N8995 | Operator Seat | 6000 | 68065 | 2026-03-31 | 69200 | 2027-02-15 | 4865 | WA | Iron Bridge
RD4917 | Cat 793F | N9020 | Alternator | 24000 | 62483 | 2025-05-25 | 69200 | 2029-02-10 | 17283 | WA | Iron Bridge
RD4917 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 58231 | 2024-10-10 | 69200 | 2028-06-12 | 13031 | WA | Iron Bridge
RD4917 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 58231 | 2024-10-10 | 69200 | 2028-06-12 | 13031 | WA | Iron Bridge
RD4917 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 64642 | 2025-04-17 | 69200 | 2026-04-28 | -558 | WA | Iron Bridge
RD4917 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 43464 | 2021-03-23 | 69200 | 2026-02-19 | -1736 | WA | Iron Bridge
RD4917 | Cat 793F | N9501 | A/C Compressor | 12000 | 60782 | 2025-02-25 | 69200 | 2026-12-20 | 3582 | WA | Iron Bridge
RD4918 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 58300 | 2024-10-16 | 68797 | 2029-10-15 |  | WA | Iron Bridge
RD4918 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 67625 | 2026-03-20 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1000 | Engine | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 67625 | 2026-03-26 | 68797 | 2026-10-28 | 2828 | WA | Iron Bridge
RD4918 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 67747 | 2026-04-02 | 68797 | 2026-04-04 | -1000 | WA | Iron Bridge
RD4918 | Cat 793F | N1004 | Engine Midlife | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1210 | Fuel Injectors | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N1301 | Water Pump | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N1310 | Radiator | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1315 | Thermostat | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4918 | Cat 793F | N2000 | Transmission | 18000 | 58892 | 2024-11-30 | 68797 | 2027-08-09 | 8095 | WA | Iron Bridge
RD4918 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 48413 | 2021-10-13 | 68797 | 2026-05-07 | -384 | WA | Iron Bridge
RD4918 | Cat 793F | N2050 | Torque Convertor | 24000 | 58892 | 2024-11-24 | 68797 | 2028-06-28 | 14095 | WA | Iron Bridge
RD4918 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 58892 | 2024-11-24 | 68797 | 2027-08-09 | 8095 | WA | Iron Bridge
RD4918 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 51558 | 2022-08-03 | 68797 | 2027-05-28 | 6761 | WA | Iron Bridge
RD4918 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 64950 | 2025-11-01 | 68797 | 2027-08-12 | 8153 | WA | Iron Bridge
RD4918 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 58892 | 2024-11-28 | 68797 | 2027-04-22 | 6095 | WA | Iron Bridge
RD4918 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 67625 | 2026-03-20 | 68797 | 2027-06-01 | 6828 | WA | Iron Bridge
RD4918 | Cat 793F | N3320 | Pump Drive Box | 18000 | 58892 | 2024-11-24 | 68797 | 2027-08-09 | 8095 | WA | Iron Bridge
RD4918 | Cat 793F | N4000 | Bevel Gear | 18000 | 58892 | 2024-11-21 | 68797 | 2027-08-09 | 8095 | WA | Iron Bridge
RD4918 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 58892 | 2024-11-26 | 68797 | 2029-05-18 | 20095 | WA | Iron Bridge
RD4918 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 58892 | 2024-11-29 | 68797 | 2029-05-18 | 20095 | WA | Iron Bridge
RD4918 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 51766 | 2022-08-18 | 68797 | 2027-08-02 | 7969 | WA | Iron Bridge
RD4918 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 59641 | 2025-01-31 | 68797 | 2028-09-30 | 15844 | WA | Iron Bridge
RD4918 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 67625 | 2026-03-20 | 68797 | 2028-08-07 | 14828 | WA | Iron Bridge
RD4918 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 67625 | 2026-03-21 | 68797 | 2028-08-07 | 14828 | WA | Iron Bridge
RD4918 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 51766 | 2022-08-18 | 68797 | 2027-09-25 | 8969 | WA | Iron Bridge
RD4918 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 51766 | 2022-08-18 | 68797 | 2027-09-25 | 8969 | WA | Iron Bridge
RD4918 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 47223 | 2021-07-18 | 68797 | 2026-06-20 | 426 | WA | Iron Bridge
RD4918 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 55135 | 2023-10-31 | 68797 | 2027-08-22 | 8338 | WA | Iron Bridge
RD4918 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 59473 | 2024-12-31 | 68797 | 2027-09-09 | 8676 | WA | Iron Bridge
RD4918 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 57735 | 2024-08-27 | 68797 | 2027-06-07 | 6938 | WA | Iron Bridge
RD4918 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 58904 | 2024-12-02 | 68797 | 2028-06-29 | 14107 | WA | Iron Bridge
RD4918 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 62767 | 2025-07-12 | 68797 | 2029-01-23 | 17970 | WA | Iron Bridge
RD4918 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 59643 | 2025-01-11 | 68797 | 2029-01-17 | 17846 | WA | Iron Bridge
RD4918 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 56633 | 2024-04-01 | 68797 | 2028-08-07 | 14836 | WA | Iron Bridge
RD4918 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 61299 | 2025-05-02 | 68797 | 2027-01-26 | 4502 | WA | Iron Bridge
RD4918 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 61299 | 2025-05-02 | 68797 | 2027-01-26 | 4502 | WA | Iron Bridge
RD4918 | Cat 793F | N7605 | Steering Hmu | 24000 | 62767 | 2025-07-12 | 68797 | 2029-01-23 | 17970 | WA | Iron Bridge
RD4918 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 56750 | 2024-05-13 | 68797 | 2028-03-04 | 11953 | WA | Iron Bridge
RD4918 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 66676 | 2026-01-28 | 68797 | 2029-08-23 | 21879 | WA | Iron Bridge
RD4918 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 58892 | 2024-11-28 | 68797 | 2028-06-28 | 14095 | WA | Iron Bridge
RD4918 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 58892 | 2024-11-29 | 68797 | 2028-06-28 | 14095 | WA | Iron Bridge
RD4918 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 68595 | 2026-05-17 | 68797 | 2029-12-04 | 23798 | WA | Iron Bridge
RD4918 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 58892 | 2024-11-30 | 68797 | 2028-06-28 | 14095 | WA | Iron Bridge
RD4918 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 58892 | 2024-11-30 | 68797 | 2028-06-28 | 14095 | WA | Iron Bridge
RD4918 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 61299 | 2025-05-02 | 68797 | 2028-11-05 | 16502 | WA | Iron Bridge
RD4918 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 61299 | 2025-05-02 | 68797 | 2028-11-05 | 16502 | WA | Iron Bridge
RD4918 | Cat 793F | N8140 | Steering Y Piece | 24000 | 61299 | 2025-04-13 | 68797 | 2028-11-05 | 16502 | WA | Iron Bridge
RD4918 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 51766 | 2022-08-18 | 68797 | 2027-02-21 | 4969 | WA | Iron Bridge
RD4918 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 32485 | 2018-12-11 | 68797 | 2024-09-22 | -11312 | WA | Iron Bridge
RD4918 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 32485 | 2018-12-11 | 68797 | 2024-09-22 | -11312 | WA | Iron Bridge
RD4918 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 61299 | 2025-05-02 | 68797 | 2027-01-26 | 4502 | WA | Iron Bridge
RD4918 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 61299 | 2025-05-02 | 68797 | 2027-01-26 | 4502 | WA | Iron Bridge
RD4918 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 61299 | 2025-05-02 | 68797 | 2027-01-26 | 4502 | WA | Iron Bridge
RD4918 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 61299 | 2025-05-02 | 68797 | 2027-01-26 | 4502 | WA | Iron Bridge
RD4918 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 61236 | 2025-04-08 | 68797 | 2028-03-30 | 12439 | WA | Iron Bridge
RD4918 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 50470 | 2022-05-07 | 68797 | 2026-08-26 | 1673 | WA | Iron Bridge
RD4918 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 61299 | 2025-04-15 | 68797 | 2028-04-03 | 12502 | WA | Iron Bridge
RD4918 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 63830 | 2025-09-07 | 68797 | 2028-08-18 | 15033 | WA | Iron Bridge
RD4918 | Cat 793F | N8501 | Ball Stud Crack Test |  | 66629 | 2026-01-27 | 68797 | 2026-07-28 |  | WA | Iron Bridge
RD4918 | Cat 793F | N8995 | Operator Seat | 6000 | 67625 | 2026-03-22 | 68797 | 2027-02-13 | 4828 | WA | Iron Bridge
RD4918 | Cat 793F | N9020 | Alternator | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 67625 | 2026-03-26 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 69950 | 2025-11-02 | 68797 | 2027-03-03 | 5153 | WA | Iron Bridge
RD4918 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 67625 | 2026-03-21 | 68797 | 2029-10-13 | 22828 | WA | Iron Bridge
RD4918 | Cat 793F | N9501 | A/C Compressor | 12000 | 67625 | 2026-03-26 | 68797 | 2028-01-03 | 10828 | WA | Iron Bridge
RD4919 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-06-27 | 67810 | 2027-06-26 |  | WA | Iron Bridge
RD4919 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 42612 | 2021-02-09 | 67810 | 2026-03-24 | -1198 | WA | Iron Bridge
RD4919 | Cat 793F | N1000 | Engine | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 66823 | 2026-04-08 | 67810 | 2026-11-07 | 3013 | WA | Iron Bridge
RD4919 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 66894 | 2026-04-13 | 67810 | 2026-04-11 | -866 | WA | Iron Bridge
RD4919 | Cat 793F | N1004 | Engine Midlife | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1210 | Fuel Injectors | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N1301 | Water Pump | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N1310 | Radiator | 24000 | 66822 | 2026-04-06 | 67810 | 2029-10-23 | 23012 | WA | Iron Bridge
RD4919 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 66822 | 2026-04-06 | 67810 | 2029-10-23 | 23012 | WA | Iron Bridge
RD4919 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 66822 | 2026-04-06 | 67810 | 2029-10-23 | 23012 | WA | Iron Bridge
RD4919 | Cat 793F | N1315 | Thermostat | 24000 | 66822 | 2026-04-06 | 67810 | 2029-10-23 | 23012 | WA | Iron Bridge
RD4919 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 66822 | 2026-04-06 | 67810 | 2029-10-23 | 23012 | WA | Iron Bridge
RD4919 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4919 | Cat 793F | N2000 | Transmission | 18000 | 55630 | 2024-08-02 | 67810 | 2027-04-08 | 5820 | WA | Iron Bridge
RD4919 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 55630 | 2024-07-28 | 67810 | 2027-07-25 | 7820 | WA | Iron Bridge
RD4919 | Cat 793F | N2050 | Torque Convertor | 24000 | 53046 | 2023-10-31 | 67810 | 2027-10-09 | 9236 | WA | Iron Bridge
RD4919 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 51248 | 2022-11-06 | 67810 | 2026-08-14 | 1438 | WA | Iron Bridge
RD4919 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 52985 | 2023-10-31 | 67810 | 2027-10-06 | 9175 | WA | Iron Bridge
RD4919 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 66536 | 2026-03-15 | 67810 | 2027-12-29 | 10726 | WA | Iron Bridge
RD4919 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 55630 | 2024-08-01 | 67810 | 2026-12-20 | 3820 | WA | Iron Bridge
RD4919 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 64377 | 2025-11-22 | 67810 | 2027-01-30 | 4567 | WA | Iron Bridge
RD4919 | Cat 793F | N3320 | Pump Drive Box | 18000 | 55630 | 2025-04-23 | 67810 | 2027-04-08 | 5820 | WA | Iron Bridge
RD4919 | Cat 793F | N4000 | Bevel Gear | 18000 | 55630 | 2024-08-03 | 67810 | 2027-04-08 | 5820 | WA | Iron Bridge
RD4919 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 55630 | 2024-08-02 | 67810 | 2029-01-15 | 17820 | WA | Iron Bridge
RD4919 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 55630 | 2024-08-02 | 67810 | 2029-01-15 | 17820 | WA | Iron Bridge
RD4919 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 66329 | 2026-03-03 | 67810 | 2029-11-19 | 23519 | WA | Iron Bridge
RD4919 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 52191 | 2023-02-23 | 67810 | 2027-10-17 | 9381 | WA | Iron Bridge
RD4919 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 57496 | 2024-11-07 | 67810 | 2027-03-31 | 5686 | WA | Iron Bridge
RD4919 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 49698 | 2022-07-25 | 67810 | 2026-02-03 | -2112 | WA | Iron Bridge
RD4919 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 53046 | 2023-10-31 | 67810 | 2028-01-25 | 11236 | WA | Iron Bridge
RD4919 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 53046 | 2023-10-31 | 67810 | 2028-01-25 | 11236 | WA | Iron Bridge
RD4919 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 46743 | 2021-11-06 | 67810 | 2026-07-17 | 933 | WA | Iron Bridge
RD4919 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 60396 | 2025-04-16 | 67810 | 2028-07-24 | 14586 | WA | Iron Bridge
RD4919 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 55630 | 2024-08-04 | 67810 | 2027-04-08 | 5820 | WA | Iron Bridge
RD4919 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 55630 | 2024-08-04 | 67810 | 2027-04-08 | 5820 | WA | Iron Bridge
RD4919 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 60396 | 2025-04-17 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 60396 | 2025-04-17 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 66822 | 2026-04-06 | 67810 | 2029-10-23 | 23012 | WA | Iron Bridge
RD4919 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 55306 | 2024-06-18 | 67810 | 2028-07-20 | 14496 | WA | Iron Bridge
RD4919 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 35329 | 2019-09-21 | 67810 | 2025-08-05 | -5481 | WA | Iron Bridge
RD4919 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 53598 | 2024-02-12 | 67810 | 2026-01-28 | -2212 | WA | Iron Bridge
RD4919 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 66249 | 2026-02-26 | 67810 | 2027-12-13 | 10439 | WA | Iron Bridge
RD4919 | Cat 793F | N7605 | Steering Hmu | 24000 | 60396 | 2025-04-17 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 60396 | 2025-04-17 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 55630 | 2024-08-05 | 67810 | 2028-02-26 | 11820 | WA | Iron Bridge
RD4919 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 55630 | 2024-08-05 | 67810 | 2028-02-26 | 11820 | WA | Iron Bridge
RD4919 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 55630 | 2024-08-06 | 67810 | 2028-02-26 | 11820 | WA | Iron Bridge
RD4919 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 55630 | 2024-08-06 | 67810 | 2028-02-26 | 11820 | WA | Iron Bridge
RD4919 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 55630 | 2024-08-06 | 67810 | 2028-02-26 | 11820 | WA | Iron Bridge
RD4919 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 55630 | 2024-08-06 | 67810 | 2028-02-26 | 11820 | WA | Iron Bridge
RD4919 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 60396 | 2025-04-18 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 60396 | 2025-04-17 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N8140 | Steering Y Piece | 24000 | 60396 | 2025-04-18 | 67810 | 2028-11-10 | 16586 | WA | Iron Bridge
RD4919 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 53046 | 2023-10-31 | 67810 | 2027-06-23 | 7236 | WA | Iron Bridge
RD4919 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 32316 | 2019-03-12 | 67810 | 2024-11-07 | -10494 | WA | Iron Bridge
RD4919 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 61325 | 2025-06-07 | 67810 | 2029-02-22 | 18515 | WA | Iron Bridge
RD4919 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 66249 | 2026-02-26 | 67810 | 2027-12-13 | 10439 | WA | Iron Bridge
RD4919 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 66249 | 2026-02-26 | 67810 | 2027-12-13 | 10439 | WA | Iron Bridge
RD4919 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 47216 | 2021-12-06 | 67810 | 2025-02-17 | -8594 | WA | Iron Bridge
RD4919 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 52985 | 2023-10-31 | 67810 | 2025-12-26 | -2825 | WA | Iron Bridge
RD4919 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 52985 | 2023-10-31 | 67810 | 2027-03-04 | 5175 | WA | Iron Bridge
RD4919 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 52985 | 2023-10-31 | 67810 | 2027-03-04 | 5175 | WA | Iron Bridge
RD4919 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 52985 | 2023-10-31 | 67810 | 2027-03-04 | 5175 | WA | Iron Bridge
RD4919 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 52985 | 2023-10-31 | 67810 | 2027-03-04 | 5175 | WA | Iron Bridge
RD4919 | Cat 793F | N8501 | Ball Stud Crack Test |  | 65867 | 2026-02-05 | 67810 | 2026-08-06 |  | WA | Iron Bridge
RD4919 | Cat 793F | N8995 | Operator Seat | 6000 | 60396 | 2025-04-17 | 67810 | 2026-03-13 | -1414 | WA | Iron Bridge
RD4919 | Cat 793F | N9020 | Alternator | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 66823 | 2026-04-08 | 67810 | 2029-10-23 | 23013 | WA | Iron Bridge
RD4919 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 64377 | 2025-11-23 | 67810 | 2026-06-28 | 567 | WA | Iron Bridge
RD4919 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 42612 | 2021-02-09 | 67810 | 2026-03-24 | -1198 | WA | Iron Bridge
RD4919 | Cat 793F | N9501 | A/C Compressor | 12000 | 66823 | 2026-04-08 | 67810 | 2028-01-13 | 11013 | WA | Iron Bridge
RD4920 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  | 48409 | 2024-04-08 | 61931 | 2029-04-07 |  | WA | Iron Bridge
RD4920 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1000 | Engine | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 55118 | 2025-05-27 | 61931 | 2025-12-28 | -2813 | WA | Iron Bridge
RD4920 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 48409 | 2023-10-31 | 61931 | 2024-05-30 | -13472 | WA | Iron Bridge
RD4920 | Cat 793F | N1004 | Engine Midlife | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-09 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1210 | Fuel Injectors | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N1301 | Water Pump | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N1310 | Radiator | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1315 | Thermostat | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N2000 | Transmission | 18000 | 48409 | 2023-10-31 | 61931 | 2027-01-25 | 4478 | WA | Iron Bridge
RD4920 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 48409 | 2023-10-31 | 61931 | 2027-05-13 | 6478 | WA | Iron Bridge
RD4920 | Cat 793F | N2050 | Torque Convertor | 24000 | 41343 | 2020-10-18 | 61931 | 2026-11-28 | 3412 | WA | Iron Bridge
RD4920 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 59284 | 2026-01-05 | 61931 | 2028-09-04 | 15353 | WA | Iron Bridge
RD4920 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 56780 | 2025-08-20 | 61931 | 2028-01-04 | 10849 | WA | Iron Bridge
RD4920 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 56780 | 2025-08-20 | 61931 | 2026-10-29 | 2849 | WA | Iron Bridge
RD4920 | Cat 793F | N3320 | Pump Drive Box | 18000 | 56780 | 2025-08-20 | 61931 | 2028-04-22 | 12849 | WA | Iron Bridge
RD4920 | Cat 793F | N4000 | Bevel Gear | 18000 | 39014 | 2020-05-27 | 61931 | 2025-08-28 | -4917 | WA | Iron Bridge
RD4920 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 28826 | 2018-07-06 | 61931 | 2025-12-10 | -3105 | WA | Iron Bridge
RD4920 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 28826 | 2018-07-06 | 61931 | 2025-12-10 | -3105 | WA | Iron Bridge
RD4920 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 48409 | 2023-10-31 | 61931 | 2028-02-07 | 11478 | WA | Iron Bridge
RD4920 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 48409 | 2023-10-31 | 61931 | 2028-02-07 | 11478 | WA | Iron Bridge
RD4920 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 48408 | 2023-10-31 | 61931 | 2027-08-29 | 8477 | WA | Iron Bridge
RD4920 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 55722 | 2025-06-26 | 61931 | 2027-11-08 | 9791 | WA | Iron Bridge
RD4920 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 48409 | 2023-10-31 | 61931 | 2026-10-09 | 2478 | WA | Iron Bridge
RD4920 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 48734 | 2024-07-03 | 61931 | 2028-04-19 | 12803 | WA | Iron Bridge
RD4920 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 48409 | 2023-10-31 | 61931 | 2028-04-01 | 12478 | WA | Iron Bridge
RD4920 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 49540 | 2024-08-14 | 61931 | 2027-10-29 | 9609 | WA | Iron Bridge
RD4920 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 46327 | 2021-09-27 | 61931 | 2026-10-05 | 2396 | WA | Iron Bridge
RD4920 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 57619 | 2025-10-10 | 61931 | 2028-06-06 | 13688 | WA | Iron Bridge
RD4920 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 47609 | 2021-12-29 | 61931 | 2027-11-02 | 9678 | WA | Iron Bridge
RD4920 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 47609 | 2021-12-29 | 61931 | 2027-11-02 | 9678 | WA | Iron Bridge
RD4920 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 56931 | 2025-09-04 | 61931 | 2029-08-29 | 22000 | WA | Iron Bridge
RD4920 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 29252 | 2018-08-11 | 61931 | 2025-07-25 | -5679 | WA | Iron Bridge
RD4920 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 48409 | 2023-10-31 | 61931 | 2026-03-10 | -1522 | WA | Iron Bridge
RD4920 | Cat 793F | N7605 | Steering Hmu | 24000 | 47609 | 2021-12-29 | 61931 | 2027-11-02 | 9678 | WA | Iron Bridge
RD4920 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 59320 | 2026-01-08 | 61931 | 2029-07-27 | 21389 | WA | Iron Bridge
RD4920 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 50195 | 2024-09-14 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 50195 | 2024-09-14 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 50195 | 2024-09-14 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 53040 | 2025-02-04 | 61931 | 2028-08-22 | 15109 | WA | Iron Bridge
RD4920 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 50195 | 2024-09-13 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 50195 | 2024-09-13 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 50195 | 2024-09-13 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 50195 | 2024-09-13 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N8140 | Steering Y Piece | 24000 | 50195 | 2024-09-14 | 61931 | 2028-03-21 | 12264 | WA | Iron Bridge
RD4920 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 48409 | 2023-10-31 | 61931 | 2027-08-29 | 8478 | WA | Iron Bridge
RD4920 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 28826 | 2018-07-06 | 61931 | 2025-02-27 | -8105 | WA | Iron Bridge
RD4920 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 28826 | 2018-07-06 | 61931 | 2025-02-27 | -8105 | WA | Iron Bridge
RD4920 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 50195 | 2024-09-13 | 61931 | 2026-06-20 | 264 | WA | Iron Bridge
RD4920 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 50195 | 2024-09-13 | 61931 | 2026-06-20 | 264 | WA | Iron Bridge
RD4920 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 50195 | 2024-09-13 | 61931 | 2026-06-20 | 264 | WA | Iron Bridge
RD4920 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 50195 | 2024-09-13 | 61931 | 2026-06-20 | 264 | WA | Iron Bridge
RD4920 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 54613 | 2025-05-01 | 61931 | 2028-04-13 | 12682 | WA | Iron Bridge
RD4920 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 54613 | 2025-04-30 | 61931 | 2028-04-13 | 12682 | WA | Iron Bridge
RD4920 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 54613 | 2025-04-30 | 61931 | 2028-04-13 | 12682 | WA | Iron Bridge
RD4920 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 54613 | 2025-05-01 | 61931 | 2028-04-13 | 12682 | WA | Iron Bridge
RD4920 | Cat 793F | N8501 | Ball Stud Crack Test |  | 59770 | 2026-01-31 | 61931 | 2026-08-01 |  | WA | Iron Bridge
RD4920 | Cat 793F | N8995 | Operator Seat | 6000 | 61503 | 2026-04-30 | 61931 | 2027-03-25 | 5572 | WA | Iron Bridge
RD4920 | Cat 793F | N9020 | Alternator | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 58764 | 2025-12-08 | 61931 | 2026-07-12 | 833 | WA | Iron Bridge
RD4920 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 48409 | 2023-10-31 | 61931 | 2027-12-15 | 10478 | WA | Iron Bridge
RD4920 | Cat 793F | N9501 | A/C Compressor | 12000 | 48409 | 2023-10-31 | 56829 | 2026-03-18 | 3580 | WA | Iron Bridge
RD4921 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  |  | 2021-02-15 | 71920 | 2026-02-14 |  | WA | Iron Bridge
RD4921 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-21 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1000 | Engine | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 63352 | 2025-02-11 | 71920 | 2025-09-18 | -4568 | WA | Iron Bridge
RD4921 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 45510 | 2021-06-17 | 71920 | 2022-07-03 | -26360 | WA | Iron Bridge
RD4921 | Cat 793F | N1004 | Engine Midlife | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1210 | Fuel Injectors | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N1301 | Water Pump | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N1310 | Radiator | 24000 | 45510 | 2021-06-11 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 45510 | 2021-06-11 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 45510 | 2021-06-11 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1315 | Thermostat | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 54858 | 2023-08-16 | 71920 | 2025-08-21 | -5062 | WA | Iron Bridge
RD4921 | Cat 793F | N2000 | Transmission | 18000 | 60249 | 2024-09-11 | 71920 | 2027-05-05 | 6329 | WA | Iron Bridge
RD4921 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 60249 | 2024-09-10 | 71920 | 2027-08-21 | 8329 | WA | Iron Bridge
RD4921 | Cat 793F | N2050 | Torque Convertor | 24000 | 66390 | 2025-07-28 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 66390 | 2025-07-28 | 71920 | 2028-04-01 | 12470 | WA | Iron Bridge
RD4921 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 60249 | 2024-09-08 | 71920 | 2026-06-25 | 329 | WA | Iron Bridge
RD4921 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 60249 | 2024-09-07 | 71920 | 2027-01-17 | 4329 | WA | Iron Bridge
RD4921 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 66390 | 2025-07-29 | 71920 | 2026-10-09 | 2470 | WA | Iron Bridge
RD4921 | Cat 793F | N3320 | Pump Drive Box | 18000 | 60249 | 2024-09-10 | 71920 | 2027-05-05 | 6329 | WA | Iron Bridge
RD4921 | Cat 793F | N4000 | Bevel Gear | 18000 | 66390 | 2025-07-30 | 71920 | 2028-04-01 | 12470 | WA | Iron Bridge
RD4921 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 66833 | 2025-08-27 | 71920 | 2030-02-03 | 24913 | WA | Iron Bridge
RD4921 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 66833 | 2025-08-27 | 71920 | 2030-02-03 | 24913 | WA | Iron Bridge
RD4921 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 66390 | 2025-07-29 | 71920 | 2029-04-14 | 19470 | WA | Iron Bridge
RD4921 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 66390 | 2025-07-28 | 71920 | 2029-04-14 | 19470 | WA | Iron Bridge
RD4921 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 68454 | 2025-11-22 | 71920 | 2029-02-23 | 18534 | WA | Iron Bridge
RD4921 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 69913 | 2026-02-11 | 71920 | 2029-05-13 | 19993 | WA | Iron Bridge
RD4921 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 68454 | 2025-11-22 | 71920 | 2029-02-23 | 18534 | WA | Iron Bridge
RD4921 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 69913 | 2026-02-11 | 71920 | 2029-05-13 | 19993 | WA | Iron Bridge
RD4921 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 66390 | 2025-07-30 | 71920 | 2027-12-15 | 10470 | WA | Iron Bridge
RD4921 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 57560 | 2024-04-14 | 71920 | 2026-08-25 | 1640 | WA | Iron Bridge
RD4921 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 66390 | 2025-07-30 | 71920 | 2029-06-07 | 20470 | WA | Iron Bridge
RD4921 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 66390 | 2025-07-29 | 71920 | 2029-06-07 | 20470 | WA | Iron Bridge
RD4921 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 66833 | 2025-08-27 | 71920 | 2028-11-27 | 16913 | WA | Iron Bridge
RD4921 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 54858 | 2023-08-16 | 71920 | 2027-02-19 | 4938 | WA | Iron Bridge
RD4921 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 54228 | 2023-02-10 | 71920 | 2026-06-24 | 308 | WA | Iron Bridge
RD4921 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 60249 | 2024-09-10 | 71920 | 2027-05-05 | 6329 | WA | Iron Bridge
RD4921 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 66390 | 2025-07-26 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 66390 | 2025-07-26 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 45510 | 2021-06-11 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 34693 | 2019-03-31 | 71920 | 2024-11-21 | -10227 | WA | Iron Bridge
RD4921 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 55056 | 2023-10-22 | 71920 | 2027-11-27 | 10136 | WA | Iron Bridge
RD4921 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 66390 | 2025-08-02 | 71920 | 2027-05-13 | 6470 | WA | Iron Bridge
RD4921 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 66390 | 2025-08-02 | 71920 | 2027-05-13 | 6470 | WA | Iron Bridge
RD4921 | Cat 793F | N7605 | Steering Hmu | 24000 | 66390 | 2025-07-30 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 66390 | 2025-07-31 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 60249 | 2024-09-08 | 71920 | 2028-03-24 | 12329 | WA | Iron Bridge
RD4921 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 60249 | 2024-09-08 | 71920 | 2028-03-24 | 12329 | WA | Iron Bridge
RD4921 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 60249 | 2024-09-07 | 71920 | 2028-03-24 | 12329 | WA | Iron Bridge
RD4921 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 60246 | 2024-09-07 | 71920 | 2028-03-24 | 12326 | WA | Iron Bridge
RD4921 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 60246 | 2024-09-07 | 71920 | 2028-03-24 | 12326 | WA | Iron Bridge
RD4921 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 60246 | 2024-09-07 | 71920 | 2028-03-24 | 12326 | WA | Iron Bridge
RD4921 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 68454 | 2025-11-22 | 71920 | 2029-02-23 | 18534 | WA | Iron Bridge
RD4921 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 69913 | 2026-02-11 | 71920 | 2029-05-13 | 19993 | WA | Iron Bridge
RD4921 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 66390 | 2025-08-02 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 66390 | 2025-08-02 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N8140 | Steering Y Piece | 24000 | 66390 | 2025-08-02 | 71920 | 2029-02-19 | 18470 | WA | Iron Bridge
RD4921 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 64377 | 2025-04-11 | 71920 | 2028-07-17 | 14457 | WA | Iron Bridge
RD4921 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 69913 | 2026-02-11 | 71920 | 2029-05-13 | 19993 | WA | Iron Bridge
RD4921 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 42418 | 2020-10-22 | 71920 | 2025-09-27 | -4502 | WA | Iron Bridge
RD4921 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 60249 | 2024-09-11 | 71920 | 2028-05-17 | 13329 | WA | Iron Bridge
RD4921 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 66390 | 2025-08-02 | 71920 | 2027-05-13 | 6470 | WA | Iron Bridge
RD4921 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 66390 | 2025-08-02 | 71920 | 2027-05-13 | 6470 | WA | Iron Bridge
RD4921 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 66390 | 2025-08-02 | 71920 | 2027-05-13 | 6470 | WA | Iron Bridge
RD4921 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 66390 | 2025-08-02 | 71920 | 2027-05-13 | 6470 | WA | Iron Bridge
RD4921 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 65429 | 2025-06-04 | 71920 | 2028-05-27 | 13509 | WA | Iron Bridge
RD4921 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 69913 | 2026-02-12 | 71920 | 2029-01-25 | 17993 | WA | Iron Bridge
RD4921 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 65429 | 2025-06-06 | 71920 | 2028-05-27 | 13509 | WA | Iron Bridge
RD4921 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 65429 | 2025-06-05 | 71920 | 2028-05-27 | 13509 | WA | Iron Bridge
RD4921 | Cat 793F | N8501 | Ball Stud Crack Test |  | 69665 | 2026-01-27 | 71920 | 2026-07-28 |  | WA | Iron Bridge
RD4921 | Cat 793F | N8995 | Operator Seat | 6000 | 68914 | 2025-12-16 | 71920 | 2026-11-06 | 2994 | WA | Iron Bridge
RD4921 | Cat 793F | N9020 | Alternator | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 66390 | 2025-07-31 | 71920 | 2026-03-11 | -1530 | WA | Iron Bridge
RD4921 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 45510 | 2021-06-17 | 71920 | 2026-01-20 | -2410 | WA | Iron Bridge
RD4921 | Cat 793F | N9501 | A/C Compressor | 12000 | 60249 | 2024-09-10 | 71920 | 2026-06-25 | 329 | WA | Iron Bridge
RD4922 | Cat 793F | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-06-15 | 70620 | 2028-06-13 |  | WA | Iron Bridge
RD4922 | Cat 793F | N0520 | Pre Lube Pump | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1000 | Engine | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1002 | Engine Valve Adj | 4000 | 69498 | 2026-03-15 | 70620 | 2026-10-31 | 2878 | WA | Iron Bridge
RD4922 | Cat 793F | N1002-01 | Engine Valve Adj - Initial | 50 | 44735 | 2021-01-12 | 70620 | 2022-07-30 | -25835 | WA | Iron Bridge
RD4922 | Cat 793F | N1004 | Engine Midlife | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N1100-LI | Turbo Primary LFT INNER | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1100-LO | Turbo Primary LFT OUTER | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1100-RI | Turbo Primary RHT INNER | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1100-RO | Turbo Primary RHT OUTER | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1202 | Fuel Transfer Pump | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N1205 | Fuel Pump - High Pressure | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N1206 | Fuel Priming Pump | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1210 | Fuel Injectors | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1300 | Cooling Sys Service | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N1301 | Water Pump | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N1310 | Radiator | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1312-L | Aftercooler Core - LEFT | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1312-R | Aftercooler Core - RIGHT | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1315 | Thermostat | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1320 | Cooling Fan Engine | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N1400-L | Belt Tensioner Assy - LEFT | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N1400-R | Belt Tensioner Assy - RIGHT | 12000 | 54999 | 2023-08-16 | 70620 | 2025-10-26 | -3621 | WA | Iron Bridge
RD4922 | Cat 793F | N2000 | Transmission | 18000 | 62743 | 2025-03-09 | 70620 | 2027-11-26 | 10123 | WA | Iron Bridge
RD4922 | Cat 793F | N2002 | Oil Cooler - Transmission | 20000 | 49669 | 2021-12-01 | 70620 | 2026-03-27 | -951 | WA | Iron Bridge
RD4922 | Cat 793F | N2050 | Torque Convertor | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N2052 | Convertor/Trans Pump | 18000 | 49669 | 2021-12-01 | 70620 | 2025-12-03 | -2951 | WA | Iron Bridge
RD4922 | Cat 793F | N3020 | Drive Shaft Eng - Pump Drive | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N3021 | Uni's Eng - Pump Drive | 12000 | 60664 | 2024-10-21 | 70620 | 2026-09-14 | 2044 | WA | Iron Bridge
RD4922 | Cat 793F | N3028 | Drive Shaft T/C - Trans | 16000 | 60664 | 2024-10-21 | 70620 | 2027-04-20 | 6044 | WA | Iron Bridge
RD4922 | Cat 793F | N3029 | Uni's T/C - Trans | 8000 | 60664 | 2024-10-22 | 70620 | 2026-01-29 | -1956 | WA | Iron Bridge
RD4922 | Cat 793F | N3320 | Pump Drive Box | 18000 | 53790 | 2023-01-13 | 70620 | 2026-07-30 | 1170 | WA | Iron Bridge
RD4922 | Cat 793F | N4000 | Bevel Gear | 18000 | 49669 | 2021-12-01 | 70620 | 2025-12-03 | -2951 | WA | Iron Bridge
RD4922 | Cat 793F | N4102-03 | Axle Shaft - POS 3 | 30000 | 62079 | 2025-01-22 | 70620 | 2029-07-31 | 21459 | WA | Iron Bridge
RD4922 | Cat 793F | N4102-04 | Axle Shaft - POS 4 | 30000 | 62079 | 2025-01-22 | 70620 | 2029-07-31 | 21459 | WA | Iron Bridge
RD4922 | Cat 793F | N5003-03 | Final Drive Ext Life POS 3 | 25000 | 63319 | 2025-04-08 | 70620 | 2029-01-09 | 17699 | WA | Iron Bridge
RD4922 | Cat 793F | N5003-04 | Final Drive Ext Life POS 4 | 25000 | 52642 | 2022-09-26 | 70620 | 2027-06-12 | 7022 | WA | Iron Bridge
RD4922 | Cat 793F | N5020-01 | Wheel Bearing POS 1 | 22000 | 69517 | 2026-03-22 | 70620 | 2029-07-01 | 20897 | WA | Iron Bridge
RD4922 | Cat 793F | N5020-02 | Wheel Bearing POS 2 | 22000 | 60664 | 2024-10-24 | 70620 | 2028-03-09 | 12044 | WA | Iron Bridge
RD4922 | Cat 793F | N6000-01 | Brake POS 1 | 22000 | 69517 | 2026-03-22 | 70620 | 2029-07-01 | 20897 | WA | Iron Bridge
RD4922 | Cat 793F | N6000-02 | Brake POS 2 | 22000 | 60664 | 2024-10-24 | 70620 | 2028-03-09 | 12044 | WA | Iron Bridge
RD4922 | Cat 793F | N6030-F | Brake Slack Adj FRONT | 16000 | 57060 | 2024-04-27 | 70620 | 2026-10-07 | 2440 | WA | Iron Bridge
RD4922 | Cat 793F | N6030-RE | Brake Slack Adj REAR | 16000 | 66993 | 2025-10-26 | 70620 | 2028-03-27 | 12373 | WA | Iron Bridge
RD4922 | Cat 793F | N6061 | Oil Cooler Front Brakes | 26000 | 63319 | 2025-04-07 | 70620 | 2029-03-04 | 18699 | WA | Iron Bridge
RD4922 | Cat 793F | N6062 | Oil Cooler Rear Brakes | 26000 | 63319 | 2025-04-07 | 70620 | 2029-03-04 | 18699 | WA | Iron Bridge
RD4922 | Cat 793F | N7021 | Pump Brake Cooling | 22000 | 65234 | 2025-07-27 | 70620 | 2028-11-11 | 16614 | WA | Iron Bridge
RD4922 | Cat 793F | N7024 | Hyd Motor Brake Cooling | 22000 | 67925 | 2025-12-12 | 70620 | 2029-04-06 | 19305 | WA | Iron Bridge
RD4922 | Cat 793F | N7035 | Pump Hoist, Brk Charge/Cooling | 18000 | 68194 | 2026-01-02 | 70620 | 2028-09-16 | 15574 | WA | Iron Bridge
RD4922 | Cat 793F | N7123 | Pump Steering & Fan | 18000 | 60664 | 2024-10-20 | 70620 | 2027-08-06 | 8044 | WA | Iron Bridge
RD4922 | Cat 793F | N7160 | Pump Axle Lube/Cooler | 24000 | 66444 | 2025-09-28 | 70620 | 2029-05-04 | 19824 | WA | Iron Bridge
RD4922 | Cat 793F | N7169 | Hyd Mtr Axle Lube/Cooler | 24000 | 56813 | 2024-02-29 | 70620 | 2027-11-30 | 10193 | WA | Iron Bridge
RD4922 | Cat 793F | N7232 | Hyd Motor Engine Fan | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N7474-L | Hyd Cyl Hoist LEFT | 27000 | 68585 | 2026-01-25 | 70620 | 2030-02-05 | 24965 | WA | Iron Bridge
RD4922 | Cat 793F | N7474-R | Hyd Cyl Hoist RIGHT | 27000 | 54999 | 2023-08-16 | 70620 | 2028-02-02 | 11379 | WA | Iron Bridge
RD4922 | Cat 793F | N7542-L | Hyd Cyl Steer LEFT | 12000 | 57060 | 2024-04-27 | 70620 | 2026-03-05 | -1560 | WA | Iron Bridge
RD4922 | Cat 793F | N7542-R | Hyd Cyl Steer RIGHT | 12000 | 57060 | 2024-04-27 | 70620 | 2026-03-05 | -1560 | WA | Iron Bridge
RD4922 | Cat 793F | N7605 | Steering Hmu | 24000 | 66444 | 2025-09-28 | 70620 | 2029-05-04 | 19824 | WA | Iron Bridge
RD4922 | Cat 793F | N7613 | Hyd Cooler Steering/Eng Fan | 24000 | 66444 | 2025-09-29 | 70620 | 2029-05-04 | 19824 | WA | Iron Bridge
RD4922 | Cat 793F | N7653-FR | Hyd Accum Park Brake - FRONT | 24000 | 60664 | 2024-10-20 | 70620 | 2028-06-25 | 14044 | WA | Iron Bridge
RD4922 | Cat 793F | N7653-RE | Hyd Accum Park Brake - REAR | 24000 | 60664 | 2024-10-20 | 70620 | 2028-06-25 | 14044 | WA | Iron Bridge
RD4922 | Cat 793F | N7654 | Hyd Accum Service Brake | 24000 | 60664 | 2024-10-21 | 70620 | 2028-06-25 | 14044 | WA | Iron Bridge
RD4922 | Cat 793F | N7657-C | Hyd Accum Steering CENTER | 24000 | 60664 | 2024-10-18 | 70620 | 2028-06-25 | 14044 | WA | Iron Bridge
RD4922 | Cat 793F | N7657-F | Hyd Accum Steering FRONT | 24000 | 60664 | 2024-10-18 | 70620 | 2028-06-25 | 14044 | WA | Iron Bridge
RD4922 | Cat 793F | N7657-RE | Hyd Accum Steering REAR | 24000 | 60664 | 2024-10-18 | 70620 | 2028-06-25 | 14044 | WA | Iron Bridge
RD4922 | Cat 793F | N8122-01 | Wheel Group POS 1 | 22000 | 69517 | 2026-03-22 | 70620 | 2029-07-01 | 20897 | WA | Iron Bridge
RD4922 | Cat 793F | N8122-02 | Wheel Group POS 2 | 22000 | 60664 | 2024-10-24 | 70620 | 2028-03-09 | 12044 | WA | Iron Bridge
RD4922 | Cat 793F | N8137-L | Steering Linkage Group LEFT | 24000 | 58043 | 2024-06-18 | 70620 | 2028-02-04 | 11423 | WA | Iron Bridge
RD4922 | Cat 793F | N8137-R | Steering Linkage Group RIGHT | 24000 | 57060 | 2024-04-27 | 70620 | 2027-12-13 | 10440 | WA | Iron Bridge
RD4922 | Cat 793F | N8140 | Steering Y Piece | 24000 | 57060 | 2024-04-27 | 70620 | 2027-12-13 | 10440 | WA | Iron Bridge
RD4922 | Cat 793F | N8200-01 | Ride Strut POS 1 | 22000 | 60664 | 2024-10-18 | 70620 | 2028-03-09 | 12044 | WA | Iron Bridge
RD4922 | Cat 793F | N8200-02 | Ride Strut POS 2 | 22000 | 60897 | 2024-11-16 | 70620 | 2028-03-22 | 12277 | WA | Iron Bridge
RD4922 | Cat 793F | N8200-03 | Ride Strut POS 3 | 25000 | 44552 | 2020-12-21 | 70620 | 2026-03-31 | -1068 | WA | Iron Bridge
RD4922 | Cat 793F | N8200-04 | Ride Strut POS 4 | 25000 | 60664 | 2024-10-19 | 70620 | 2028-08-18 | 15044 | WA | Iron Bridge
RD4922 | Cat 793F | N8442-05 | Steering Ball Studs POS 5 | 12000 | 58043 | 2024-06-18 | 70620 | 2026-04-27 | -577 | WA | Iron Bridge
RD4922 | Cat 793F | N8442-06 | Steering Ball Studs POS 6 | 12000 | 58043 | 2024-06-18 | 70620 | 2026-04-27 | -577 | WA | Iron Bridge
RD4922 | Cat 793F | N8442-07 | Steering Ball Studs POS 7 | 12000 | 57060 | 2024-04-27 | 70620 | 2026-03-05 | -1560 | WA | Iron Bridge
RD4922 | Cat 793F | N8442-08 | Steering Ball Studs POS 8 | 12000 | 57060 | 2024-04-27 | 70620 | 2026-03-05 | -1560 | WA | Iron Bridge
RD4922 | Cat 793F | N8443-LL | Rear Axle Control Arm L/LEFT | 20000 | 49611 | 2021-11-22 | 70620 | 2026-04-03 | -1009 | WA | Iron Bridge
RD4922 | Cat 793F | N8443-LR | Rear Axle Control Arm L/RIGHT | 20000 | 64357 | 2025-06-11 | 70620 | 2028-06-09 | 13737 | WA | Iron Bridge
RD4922 | Cat 793F | N8443-UL | Rear Axle Control Arm U/LEFT | 20000 | 49611 | 2021-11-22 | 70620 | 2026-04-03 | -1009 | WA | Iron Bridge
RD4922 | Cat 793F | N8443-UR | Rear Axle Control Arm U/RIGHT | 20000 | 49891 | 2021-12-18 | 70620 | 2026-04-09 | -729 | WA | Iron Bridge
RD4922 | Cat 793F | N8501 | Ball Stud Crack Test |  | 68584 | 2026-01-25 | 70620 | 2026-07-26 |  | WA | Iron Bridge
RD4922 | Cat 793F | N8995 | Operator Seat | 6000 | 63319 | 2025-04-07 | 70620 | 2026-03-07 | -1301 | WA | Iron Bridge
RD4922 | Cat 793F | N9020 | Alternator | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N9050-LW | Starter Motor LOWER | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N9050-UP | Starter Motor UPPER | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N9500 | Air Cond'r-Serv | 4000 | 65842 | 2025-08-30 | 70620 | 2026-04-06 | -778 | WA | Iron Bridge
RD4922 | Cat 793F | N9500-MA | Air Cond'r-Serv - MAJOR | 24000 | 44735 | 2021-01-12 | 70620 | 2026-02-02 | -1885 | WA | Iron Bridge
RD4922 | Cat 793F | N9501 | A/C Compressor | 12000 | 60664 | 2024-10-20 | 70620 | 2026-09-14 | 2044 | WA | Iron Bridge
RD5009 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 49079 | 2024-09-13 | 52309.6 | 2029-09-12 |  | WA | Norrish Earthmoving
RD5009 | Cat 785C | N0200 | A Frame Bearing | 20000 | 38442 | 2019-02-21 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 49079 | 2024-08-27 | 52309.6 | 2026-02-22 | -1230.6 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 49208 | 2024-09-03 | 52309.6 | 2029-12-18 | 16898.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1000 | Engine | 20000 | 38442 | 2018-11-10 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 48954 | 2023-10-22 | 52309.6 | 2026-07-17 | 644.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 50 |  |  | 52309.6 | 2015-05-26 | -52259.6 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1004 | Engine Midlife | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 42482 | 2021-01-01 | 52309.6 | 2026-06-10 | 172.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 42482 | 2021-01-01 | 52309.6 | 2026-06-10 | 172.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1301 | Water Pump | 20000 | 38442 | 2018-11-10 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 38442 | 2018-11-10 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1310 | Radiator | 20000 | 38442 | 2018-10-26 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1420 | Air Compressor | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N1430 | Air Starter | 10000 | 44693 | 2022-11-19 | 52309.6 | 2026-11-27 | 2383.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N2000 | Transmission | 20000 | 43346 | 2021-03-09 | 52309.6 | 2028-09-23 | 11036.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 | 43346 | 2021-03-06 | 52309.6 | 2028-09-23 | 11036.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N2004 | Transmission Pump | 20000 | 43346 | 2021-03-05 | 52309.6 | 2028-09-23 | 11036.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N2050 | Torque Convertor | 20000 | 38442 | 2019-02-22 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 38442 | 2018-10-24 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 43346 | 2021-03-06 | 52309.6 | 2028-09-23 | 11036.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 43346 | 2021-03-06 | 52309.6 | 2026-08-16 | 1036.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N3320 | Pump Drive Box | 20000 | 38442 | 2018-10-13 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N4000 | Bevel Gear | 20000 | 38442 | 2018-10-14 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 38441 | 2018-08-27 | 52309.6 | 2027-09-12 | 6131.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 38341 | 2018-08-28 | 52309.6 | 2027-09-04 | 6031.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 38442 | 2019-02-22 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 38442 | 2019-02-22 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 47755 | 2023-07-20 | 52309.6 | 2029-08-28 | 15445.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 48290 | 2024-08-27 | 52309.6 | 2029-10-08 | 15980.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 47755 | 2023-07-20 | 52309.6 | 2029-08-28 | 15445.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 48290 | 2024-08-27 | 52309.6 | 2029-10-08 | 15980.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 38589 | 2020-03-15 | 52309.6 | 2027-09-23 | 6279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 38589 | 2020-03-16 | 52309.6 | 2027-09-23 | 6279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 38589 | 2020-03-16 | 52309.6 | 2027-09-23 | 6279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 47527 | 2023-06-27 | 52309.6 | 2027-07-03 | 5217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 47527 | 2023-06-27 | 52309.6 | 2027-07-03 | 5217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 43346 | 2021-03-05 | 52309.6 | 2026-08-16 | 1036.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 38589 | 2020-03-16 | 52309.6 | 2027-09-23 | 6279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 38442 | 2018-10-21 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 | 29878.2 | 2015-04-26 | 52309.6 | 2030-02-07 | 17568.6 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7120 | Pump Steering | 20000 | 40721 | 2020-09-17 | 52309.6 | 2028-03-05 | 8411.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 44693 | 2022-11-19 | 52309.6 | 2029-11-08 | 16383.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 48503 | 2023-10-02 | 52309.6 | 2030-08-28 | 20193.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7605 | Steering Hmu | 20000 | 45275 | 2023-02-06 | 52309.6 | 2029-02-18 | 12965.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 49100 | 2025-02-22 | 52309.6 | 2029-12-10 | 16790.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 49100 | 2025-02-28 | 52309.6 | 2029-12-10 | 16790.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 52309.6 | 2020-08-26 | -27309.6 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 47424 | 2023-06-29 | 52309.6 | 2029-08-03 | 15114.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 48290 | 2024-08-27 | 52309.6 | 2029-10-08 | 15980.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8140 | Steering Y Piece | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 47527 | 2023-06-27 | 52309.6 | 2029-08-11 | 15217.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 38589 | 2020-01-13 | 52309.6 | 2027-09-23 | 6279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 38442 | 2019-02-22 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 38442 | 2019-02-22 | 52309.6 | 2027-09-12 | 6132.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 38589 | 2020-03-16 | 52309.6 | 2028-10-12 | 11279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8501 | Ball Stud Crack Test |  | 52063.8 | 2026-01-20 | 52309.6 | 2026-07-21 |  | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8995 | Operator Seat | 6000 | 49079 | 2024-08-27 | 52309.6 | 2026-12-27 | 2769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 52309.6 | 2020-08-26 | -27309.6 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9020 | Alternator | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 49079 | 2024-08-27 | 52309.6 | 2026-10-11 | 1769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 38589 | 2020-03-16 | 52309.6 | 2027-09-23 | 6279.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9501 | A/C Compressor | 10000 | 49079 | 2024-08-27 | 52309.6 | 2027-10-31 | 6769.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  |  | 52309.6 | 2024-11-12 | -7309.6 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  |  | 52309.6 | 2029-01-28 | 12690.4 | WA | Norrish Earthmoving
RD5009 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  |  | 52309.6 | 2033-04-16 | 32690.4 | WA | Norrish Earthmoving
RD6032 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 31328.6 | 2020-01-20 | 41713 | 2025-01-18 |  | WA | Mt Holland
RD6032 | Cat 785C | N0200 | A Frame Bearing | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N0201-01 | A Frame Bearing Reshim Initial | 2000 | 31328.1 | 2020-03-30 | 41713 | 2024-11-15 | -8384.9 | WA | Mt Holland
RD6032 | Cat 785C | N0520 | Pre Lube Pump | 20000 | 38923 | 2023-09-08 | 41713 | 2029-07-18 | 17210 | WA | Mt Holland
RD6032 | Cat 785C | N1000 | Engine | 20000 | 22248 |  | 41713 | 2026-07-03 | 535 | WA | Mt Holland
RD6032 | Cat 785C | N1002 | Engine Valve Adj | 4000 | 37314 | 2022-05-20 | 41713 | 2026-05-01 | -399 | WA | Mt Holland
RD6032 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 |  |  | 41713 | 2018-11-02 | -41463 | WA | Mt Holland
RD6032 | Cat 785C | N1004 | Engine Midlife | 10000 | 31328 | 2019-10-24 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1100-L | Turbo Primary LEFT | 10000 | 31328 | 2019-10-24 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1100-R | Turbo Primary RIGHT | 10000 | 31328 | 2019-10-18 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1202 | Fuel Transfer Pump | 10000 | 31328 | 2019-10-18 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1300 | Cooling Sys Service | 10000 | 31328 | 2020-03-30 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1301 | Water Pump | 20000 | 31328 | 2019-10-22 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N1302 | Aftercooler Pump | 20000 | 31328 | 2019-10-17 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N1310 | Radiator | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N1402 | Fan Pulley Brgs | 10000 | 31328 | 2019-10-22 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1403 | Jockey Pulley Brgs | 10000 | 31328 | 2019-10-22 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1420 | Air Compressor | 10000 | 31328 | 2019-10-16 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N1430 | Air Starter | 10000 | 38923 | 2023-09-06 | 41713 | 2027-09-21 | 7210 | WA | Mt Holland
RD6032 | Cat 785C | N2000 | Transmission | 20000 | 22248 |  | 41713 | 2026-07-03 | 535 | WA | Mt Holland
RD6032 | Cat 785C | N2002 | Oil Cooler - Transmission | 20000 |  |  | 41713 | 2022-06-10 | -21713 | WA | Mt Holland
RD6032 | Cat 785C | N2004 | Transmission Pump | 20000 | 37262 | 2022-05-12 | 41713 | 2027-02-13 | 3918 | WA | Mt Holland
RD6032 | Cat 785C | N2050 | Torque Convertor | 20000 | 22248 |  | 41713 | 2026-07-03 | 535 | WA | Mt Holland
RD6032 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 | 37262 | 2022-05-12 | 41713 | 2026-02-01 | -1735 | WA | Mt Holland
RD6032 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 37262 | 2022-05-12 | 41713 | 2026-08-30 | 1415 | WA | Mt Holland
RD6032 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 31328 | 2020-03-30 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N3320 | Pump Drive Box | 20000 | 37262 | 2022-05-12 | 41713 | 2029-02-27 | 15088 | WA | Mt Holland
RD6032 | Cat 785C | N4000 | Bevel Gear | 20000 | 22248 |  | 41713 | 2026-07-03 | 535 | WA | Mt Holland
RD6032 | Cat 785C | N4102-03 | Axle Shaft - POS 3 | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N4102-04 | Axle Shaft - POS 4 | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 37668 | 2022-08-06 | 41713 | 2029-04-26 | 15955 | WA | Mt Holland
RD6032 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 37655 | 2022-07-17 | 41713 | 2029-04-25 | 15942 | WA | Mt Holland
RD6032 | Cat 785C | N5020-01 | Wheel Bearing POS 1 | 20000 | 29359 | 2018-09-19 | 41713 | 2027-10-20 | 7646 | WA | Mt Holland
RD6032 | Cat 785C | N5020-02 | Wheel Bearing POS 2 | 20000 | 29359 | 2018-09-19 | 41713 | 2027-10-20 | 7646 | WA | Mt Holland
RD6032 | Cat 785C | N6000-01 | Brake POS 1 | 20000 | 30478.2 | 2018-12-15 | 41713 | 2028-01-02 | 8765.2 | WA | Mt Holland
RD6032 | Cat 785C | N6000-02 | Brake POS 2 | 20000 | 30478 | 2018-12-15 | 41713 | 2028-01-02 | 8765 | WA | Mt Holland
RD6032 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 20000 | 31328 | 2019-10-22 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 31328 | 2019-10-23 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N6060-F | Oil Cooler - Brakes FRONT | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N6200-F | Press Converter FRONT | 10000 | 31328 | 2019-10-22 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 10000 | 31328 | 2019-10-23 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 10000 | 31328 | 2019-10-23 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N7037 | Pump Conv P/Brake Release | 20000 | 29360 | 2018-09-22 | 41713 | 2027-10-20 | 7647 | WA | Mt Holland
RD6032 | Cat 785C | N7065 | Pump Hoist/ Brk Cooling | 20000 | 37262 | 2022-05-12 | 41713 | 2029-02-27 | 15088 | WA | Mt Holland
RD6032 | Cat 785C | N7088 | Pump Park Brk Rel | 40000 |  |  | 41713 | 2026-02-03 | -1713 | WA | Mt Holland
RD6032 | Cat 785C | N7120 | Pump Steering | 20000 | 37262 | 2022-05-12 | 41713 | 2027-06-23 | 5859 | WA | Mt Holland
RD6032 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 24000 | 37730 | 2023-03-17 | 41713 | 2030-01-21 | 20017 | WA | Mt Holland
RD6032 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 24000 | 15550 |  | 41713 | 2026-01-04 | -2163 | WA | Mt Holland
RD6032 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 37314 | 2022-05-20 | 41713 | 2029-04-02 | 15601 | WA | Mt Holland
RD6032 | Cat 785C | N7605 | Steering Hmu | 20000 | 31328 | 2019-10-23 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 20000 | 41713 | 2026-01-05 | 41713 | 2030-01-20 | 20000 | WA | Mt Holland
RD6032 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 20000 | 41713 | 2026-01-05 | 41713 | 2030-01-20 | 20000 | WA | Mt Holland
RD6032 | Cat 785C | N8000 | Main Frame/Chassis | 25000 |  |  | 41713 | 2023-05-10 | -16713 | WA | Mt Holland
RD6032 | Cat 785C | N8122-01 | Wheel Group POS 1 | 20000 | 30478.2 | 2018-12-15 | 41713 | 2028-01-02 | 8765.2 | WA | Mt Holland
RD6032 | Cat 785C | N8122-02 | Wheel Group POS 2 | 20000 | 30478 | 2018-12-15 | 41713 | 2028-01-02 | 8765 | WA | Mt Holland
RD6032 | Cat 785C | N8131-01 | Steering Tie Rod Ends POS1 | 20000 | 21206 | 2014-04-23 | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8131-02 | Steering Tie Rod Ends POS2 | 20000 | 21206 | 2014-04-23 | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8131-03 | Steering Tie Rod Ends POS3 | 20000 | 21206 | 2014-04-23 | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8131-04 | Steering Tie Rod Ends POS4 | 20000 | 21206 | 2014-04-23 | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8137-L | Steering Linkage Group LEFT | 20000 | 21206 |  | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8137-R | Steering Linkage Group RIGHT | 20000 | 21206 |  | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8140 | Steering Y Piece | 20000 | 21206 | 2014-04-23 | 41713 | 2026-04-24 | -507 | WA | Mt Holland
RD6032 | Cat 785C | N8200-01 | Ride Strut POS 1 | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N8200-02 | Ride Strut POS 2 | 20000 | 31328 | 2020-03-30 | 41713 | 2028-02-28 | 9615 | WA | Mt Holland
RD6032 | Cat 785C | N8200-03 | Ride Strut POS 3 | 20000 | 27171 | 2018-04-25 | 41713 | 2027-05-27 | 5458 | WA | Mt Holland
RD6032 | Cat 785C | N8200-04 | Ride Strut POS 4 | 20000 | 27173 | 2018-05-16 | 41713 | 2027-05-27 | 5460 | WA | Mt Holland
RD6032 | Cat 785C | N8441 | Rear Axle Dog Bone | 25000 | 31328 | 2020-03-30 | 41713 | 2029-01-26 | 14615 | WA | Mt Holland
RD6032 | Cat 785C | N8501 | Ball Stud Crack Test |  | 41713 | 2026-01-20 | 41713 | 2026-07-21 |  | WA | Mt Holland
RD6032 | Cat 785C | N8995 | Operator Seat | 6000 | 36712 | 2022-02-13 | 41713 | 2026-08-03 | 999 | WA | Mt Holland
RD6032 | Cat 785C | N8999 | Cab Upgrade | 25000 |  |  | 41713 | 2023-05-10 | -16713 | WA | Mt Holland
RD6032 | Cat 785C | N9020 | Alternator | 10000 | 31328 | 2019-10-21 | 41713 | 2026-05-02 | -385 | WA | Mt Holland
RD6032 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 | 37356 | 2022-05-27 | 41713 | 2026-07-10 | 643 | WA | Mt Holland
RD6032 | Cat 785C | N9500-MA | Air Cond'r-Serv - MAJOR | 20000 | 22248 | 2014-04-23 | 41713 | 2026-07-03 | 535 | WA | Mt Holland
RD6032 | Cat 785C | N9501 | A/C Compressor | 10000 | 22248 | 2014-04-23 | 41713 | 2024-09-04 | -9465 | WA | Mt Holland
RD6032 | Cat 785C | N9998 | Extended Life Rebuild | 45000 |  |  | 41713 | 2027-01-02 | 3287 | WA | Mt Holland
RD6032 | Cat 785C | N9998-01 | Extended Life Rebuild ONE | 65000 |  |  | 41713 | 2030-08-27 | 23287 | WA | Mt Holland
RD6032 | Cat 785C | N9998-02 | Extended Life Rebuild TWO | 85000 |  |  | 41713 | 2034-04-22 | 43287 | WA | Mt Holland
RD6194 | Cat 785D | N0030 | Truck Body | 20000 | 12562.71 | 2023-09-05 | 24344.16 | 2028-01-27 | 8218.55 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 21633.32 | 2025-10-23 | 24344.16 | 2030-10-22 |  | WA | Sanjiv Ridge
RD6194 | Cat 785D | N0200 | A Frame Bearing | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N0550 | Air End | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N1000 | Engine | 20000 | 16713.94 | 2024-09-21 | 24344.16 | 2026-05-12 | -176.22 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 20811.02 | 2025-08-30 | 24344.16 | 2025-09-24 | -3283.14 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-06 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 13663.05 | 2023-12-15 | 24344.16 | 2028-04-13 | 9318.89 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N1310 | Radiator | 20000 |  | 2022-06-01 | 24344.16 | 2026-02-11 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N2000 | Transmission | 20000 | 14662.84 | 2024-03-08 | 24344.16 | 2028-06-30 | 10318.68 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N2004 | Transmission Pump | 20000 | 14662.84 | 2024-03-08 | 24344.16 | 2028-06-30 | 10318.68 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N2050 | Torque Convertor | 20000 | 15495.69 | 2024-06-16 | 24344.16 | 2028-08-31 | 11151.53 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 21820 | 2025-11-07 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 10049.33 | 2023-03-04 | 24344.16 | 2026-05-01 | -4294.83 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 15495.69 | 2024-06-16 | 24344.16 | 2026-08-18 | 1151.53 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N3321 | Pump Drive | 20000 | 20088 | 2025-07-01 | 24344.16 | 2029-08-06 | 15743.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N4000 | Bevel Gear | 20000 | 21820 | 2025-11-06 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 16972.63 | 2024-11-07 | 24344.16 | 2028-12-18 | 12628.47 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 21848.8 | 2025-11-13 | 24344.16 | 2027-05-30 | 4958.64 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 14662.84 | 2024-03-08 | 24344.16 | 2027-06-26 | 5318.68 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 14662.84 | 2024-03-08 | 24344.16 | 2027-06-26 | 5318.68 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 | 24074 | 2026-05-09 | 24344.16 | 2032-06-07 | 29729.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 21838 | 2025-11-10 | 24344.16 | 2029-12-14 | 17493.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 15797.16 | 2024-07-18 | 24344.16 | 2027-09-18 | 6453 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 8965.34 | 2022-12-26 | 24344.16 | 2026-04-27 | -378.82 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 22869 | 2026-04-24 | 24344.16 | 2029-02-23 | 13524.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7064 | Pump Hoist | 20000 | 21821 | 2025-11-07 | 24344.16 | 2029-12-13 | 17476.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7120 | Pump Steering | 20000 | 21820 | 2025-11-05 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 21819 | 2025-11-05 | 24344.16 | 2029-12-12 | 17474.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 21819 | 2025-11-05 | 24344.16 | 2029-12-12 | 17474.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7602 | Relief Valve |  |  | 2024-04-02 | 24344.16 | 2028-04-01 |  | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7605 | Steering Hmu | 12000 | 11825.21 | 2023-07-16 | 24344.16 | 2026-04-16 | -518.95 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7610 | Hyd Cooler Core | 20000 |  | 2022-06-01 | 24344.16 | 2025-07-10 | -4344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 |  | 2022-06-01 | 24344.16 | 2024-07-05 | -9344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 |  | 2022-06-01 | 24344.16 | 2024-07-05 | -9344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 |  | 2022-06-01 | 24344.16 | 2024-07-05 | -9344.16 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 |  | 2022-06-01 | 24344.16 | 2027-07-21 | 5655.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 21820 | 2025-11-04 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 18902 | 2025-04-03 | 24344.16 | 2029-05-10 | 14557.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 18902 | 2025-04-03 | 24344.16 | 2029-05-10 | 14557.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 21820 | 2025-11-04 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 21820 | 2025-11-04 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 21820 | 2025-11-04 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 21820 | 2025-11-04 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 21820 | 2025-11-04 | 24344.16 | 2029-12-13 | 17475.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 24314 | 2026-05-26 | 24344.16 | 2027-01-03 | 2969.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N8995 | Operator Seat | 10000 | 21622 | 2025-10-22 | 24344.16 | 2027-11-18 | 7277.84 | WA | Sanjiv Ridge
RD6194 | Cat 785D | N9500 | Air Cond'r-Serv |  |  | 2025-07-01 | 24344.16 | 2026-07-01 |  | WA | Sanjiv Ridge
RD6195 | Cat 785D | N0030 | Truck Body | 20000 | 14647 | 2024-01-09 | 26206.72 | 2028-02-12 | 8440.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-04-17 | 26206.72 | 2030-04-16 |  | WA | Sanjiv Ridge
RD6195 | Cat 785D | N0200 | A Frame Bearing | 30000 | 24246 | 2026-01-10 | 26206.72 | 2032-02-03 | 28039.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N0550 | Air End | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N1000 | Engine | 20000 | 11250 | 2023-04-18 | 26206.72 | 2027-06-06 | 5043.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 11489.21 | 2023-05-25 | 26206.72 | 2023-06-21 | -14467.51 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N1310 | Radiator | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N2000 | Transmission | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N2004 | Transmission Pump | 20000 | 20023.05 | 2025-02-19 | 26206.72 | 2029-03-16 | 13816.33 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N2050 | Torque Convertor | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 21205.12 | 2025-05-28 | 26206.72 | 2027-06-02 | 4998.4 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 19477.18 | 2025-01-10 | 26206.72 | 2027-01-25 | 3270.46 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N3321 | Pump Drive | 20000 | 19186.4 | 2024-12-16 | 26206.72 | 2029-01-13 | 12979.68 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N4000 | Bevel Gear | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 16748.34 | 2024-06-14 | 26206.72 | 2028-07-17 | 10541.62 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 15272.32 | 2024-02-23 | 26206.72 | 2027-03-25 | 4065.6 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 15272.32 | 2024-02-23 | 26206.72 | 2027-03-25 | 4065.6 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 18058 | 2024-09-30 | 26206.72 | 2027-10-18 | 6851.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 18813.06 | 2024-11-18 | 26206.72 | 2027-12-12 | 7606.34 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 21005.29 | 2025-05-01 | 26206.72 | 2028-05-23 | 9798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7064 | Pump Hoist | 20000 | 20023.05 | 2025-02-19 | 26206.72 | 2029-03-16 | 13816.33 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7120 | Pump Steering | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7602 | Relief Valve |  |  | 2023-11-30 | 26206.72 | 2027-11-29 |  | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7605 | Steering Hmu | 12000 | 25434 | 2026-04-05 | 26206.72 | 2028-09-06 | 11227.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7610 | Hyd Cooler Core | 20000 |  | 2022-06-01 | 26206.72 | 2025-02-22 | -6206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 | 18821.2 | 2024-11-19 | 26206.72 | 2027-12-13 | 7614.48 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 |  | 2022-06-01 | 26206.72 | 2024-02-18 | -11206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 |  | 2022-06-01 | 26206.72 | 2024-02-18 | -11206.72 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 |  | 2022-06-01 | 26206.72 | 2027-03-05 | 3793.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 21005.29 | 2025-05-01 | 26206.72 | 2029-05-28 | 14798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 26173 | 2026-05-26 | 26206.72 | 2027-01-03 | 2966.28 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N8995 | Operator Seat | 10000 | 21005.29 | 2025-05-01 | 26206.72 | 2027-05-18 | 4798.57 | WA | Sanjiv Ridge
RD6195 | Cat 785D | N9500 | Air Cond'r-Serv |  | 23161.21 | 2025-10-13 | 26206.72 | 2026-10-13 |  | WA | Sanjiv Ridge
RD6196 | Cat 785D | N0030 | Truck Body | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 23463.75 | 2026-05-04 | 23844.2 | 2031-05-03 |  | WA | Sanjiv Ridge
RD6196 | Cat 785D | N0200 | A Frame Bearing | 30000 | 21354 | 2025-11-14 | 23844.2 | 2031-12-26 | 27509.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N0550 | Air End | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N1000 | Engine | 20000 | 17864.4 | 2025-01-05 | 23844.2 | 2029-04-01 | 14020.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 20708.57 | 2025-08-31 | 23844.2 | 2025-10-26 | -2885.63 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 | 20796.32 | 2025-09-05 | 23844.2 | 2029-11-04 | 16952.12 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 20796.32 | 2025-09-05 | 23844.2 | 2029-11-04 | 16952.12 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N1310 | Radiator | 20000 | 17864.4 | 2025-01-05 | 23844.2 | 2029-04-01 | 14020.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N2000 | Transmission | 20000 | 21089 | 2025-10-19 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N2004 | Transmission Pump | 20000 | 21089 | 2025-10-19 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N2050 | Torque Convertor | 20000 | 21089 | 2025-10-19 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 21089.54 | 2025-10-19 | 23844.2 | 2029-11-25 | 17245.34 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 13656.89 | 2023-12-08 | 23844.2 | 2026-05-18 | -187.31 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 21089 | 2025-10-19 | 23844.2 | 2027-11-16 | 7244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N3321 | Pump Drive | 20000 | 21089 | 2025-10-19 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N4000 | Bevel Gear | 20000 | 21089.54 | 2025-10-19 | 23844.2 | 2029-11-25 | 17245.34 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 | 19534.84 | 2025-05-24 | 23844.2 | 2029-08-02 | 15690.64 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 | 19534.84 | 2025-05-24 | 23844.2 | 2029-08-02 | 15690.64 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 19534.84 | 2025-05-24 | 23844.2 | 2029-08-02 | 15690.64 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 19534.84 | 2025-05-24 | 23844.2 | 2029-08-02 | 15690.64 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 14753.2 | 2024-05-06 | 23844.2 | 2027-08-09 | 5909 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 14753.2 | 2024-05-06 | 23844.2 | 2027-08-09 | 5909 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 12012.5 | 2023-07-21 | 23844.2 | 2028-01-23 | 8168.3 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 20834.52 | 2025-09-26 | 23844.2 | 2028-11-01 | 11990.32 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 9711.01 | 2023-01-30 | 23844.2 | 2026-08-04 | 866.81 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 23131 | 2026-03-30 | 23844.2 | 2029-04-20 | 14286.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7064 | Pump Hoist | 20000 | 21089 | 2025-10-19 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7120 | Pump Steering | 20000 | 21089 | 2025-10-19 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  | 2022-06-01 | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  | 2022-06-01 | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 20189 | 2025-10-16 | 23844.2 | 2029-09-20 | 16344.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7602 | Relief Valve |  | 21727 | 2025-12-12 | 23844.2 | 2029-12-11 |  | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7605 | Steering Hmu | 12000 | 12105.11 | 2023-07-31 | 23844.2 | 2026-06-20 | 260.91 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7610 | Hyd Cooler Core | 20000 |  | 2022-06-01 | 23844.2 | 2025-08-16 | -3844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 |  | 2022-06-01 | 23844.2 | 2024-08-11 | -8844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 |  | 2022-06-01 | 23844.2 | 2024-08-11 | -8844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 |  | 2022-06-01 | 23844.2 | 2024-08-11 | -8844.2 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 |  |  | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 |  | 2022-06-01 | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 |  | 2022-06-01 | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 |  | 2022-06-01 | 23844.2 | 2027-08-27 | 6155.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 | 21729 | 2025-12-13 | 23844.2 | 2032-01-23 | 27884.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 | 21729 | 2025-12-13 | 23844.2 | 2032-01-23 | 27884.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 21089 | 2025-10-16 | 23844.2 | 2029-11-25 | 17244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 23819 | 2026-05-26 | 23844.2 | 2027-01-03 | 2974.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N8995 | Operator Seat | 10000 | 21089 | 2025-10-19 | 23844.2 | 2027-11-16 | 7244.8 | WA | Sanjiv Ridge
RD6196 | Cat 785D | N9500 | Air Cond'r-Serv |  |  | 2025-07-21 | 23844.2 | 2026-07-21 |  | WA | Sanjiv Ridge
RD6197 | Cat 785D | N0030 | Truck Body | 20000 |  |  | 56902.96 | 2018-12-02 | -36902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-04-13 | 56902.96 | 2030-04-12 |  | WA | Sanjiv Ridge
RD6197 | Cat 785D | N0200 | A Frame Bearing | 30000 | 34800 | 2020-12-14 | 56902.96 | 2028-01-03 | 7897.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N0550 | Air End | 20000 | 46664.65 | 2024-04-25 | 56902.96 | 2028-05-20 | 9761.69 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N1000 | Engine | 20000 | 42520 | 2023-03-10 | 56902.96 | 2027-07-18 | 5617.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 42938 | 2023-05-12 | 56902.96 | 2023-08-16 | -13714.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 | 42520 | 2023-03-16 | 56902.96 | 2027-07-18 | 5617.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 42520 | 2023-03-16 | 56902.96 | 2027-07-18 | 5617.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N1310 | Radiator | 20000 | 42520 | 2023-03-10 | 56902.96 | 2027-07-18 | 5617.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N2000 | Transmission | 20000 | 51181 | 2025-03-29 | 56902.96 | 2029-04-20 | 14278.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N2004 | Transmission Pump | 20000 | 51181 | 2025-03-29 | 56902.96 | 2029-04-20 | 14278.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N2050 | Torque Convertor | 20000 | 42520 | 2023-03-10 | 56902.96 | 2027-07-18 | 5617.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 46022 | 2024-01-30 | 56902.96 | 2028-04-02 | 9119.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 56902.96 | 2018-12-02 | -36902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 34800 | 2020-12-14 | 56902.96 | 2026-02-26 | -12102.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 45692.65 | 2023-12-22 | 56902.96 | 2028-03-09 | 8789.69 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 51181 | 2025-03-29 | 56902.96 | 2027-04-10 | 4278.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N3321 | Pump Drive | 20000 | 52977.33 | 2025-08-02 | 56902.96 | 2029-08-31 | 16074.37 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N4000 | Bevel Gear | 20000 | 51181 | 2025-03-29 | 56902.96 | 2029-04-20 | 14278.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 56902.96 | 2018-12-02 | -36902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 56902.96 | 2018-12-02 | -36902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 56166 | 2026-03-30 | 56902.96 | 2030-04-24 | 19263.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 56166 | 2026-03-30 | 56902.96 | 2030-04-24 | 19263.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2022-06-01 | 56902.96 | 2018-12-02 | -36902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 41814 | 2023-01-17 | 56902.96 | 2026-05-16 | -88.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 40156 | 2022-08-24 | 56902.96 | 2026-01-13 | -1746.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 | 56855 | 2026-05-26 | 56902.96 | 2032-06-24 | 29952.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 50311.59 | 2025-01-18 | 56902.96 | 2029-02-14 | 13408.63 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 | 56169 | 2026-03-31 | 56902.96 | 2030-04-24 | 19266.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 | 34800 | 2020-12-14 | 56902.96 | 2025-12-23 | -2102.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 55896 | 2026-03-07 | 56902.96 | 2029-03-30 | 13993.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 41997 | 2023-02-02 | 56902.96 | 2026-05-29 | 94.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 41997 | 2023-02-02 | 56902.96 | 2026-05-29 | 94.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7064 | Pump Hoist | 20000 | 45897.41 | 2024-01-12 | 56902.96 | 2028-03-24 | 8994.45 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7120 | Pump Steering | 20000 | 48210.45 | 2024-08-23 | 56902.96 | 2028-09-12 | 11307.49 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  |  | 56902.96 | 2020-12-12 | -26902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  |  | 56902.96 | 2020-12-12 | -26902.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 51181 | 2025-03-29 | 56902.96 | 2029-04-20 | 14278.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 52977.33 | 2025-08-02 | 56902.96 | 2029-08-31 | 16074.37 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7602 | Relief Valve |  |  | 2023-11-19 | 56902.96 | 2027-11-18 |  | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7605 | Steering Hmu | 12000 | 48323.96 | 2024-09-03 | 56902.96 | 2027-02-05 | 3421 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7610 | Hyd Cooler Core | 20000 | 34800 | 2020-12-14 | 56902.96 | 2025-12-23 | -2102.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 | 56169 | 2026-03-29 | 56902.96 | 2029-04-19 | 14266.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 | 49759.75 | 2024-12-09 | 56902.96 | 2027-12-31 | 7856.79 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 | 49759.75 | 2024-12-09 | 56902.96 | 2027-12-31 | 7856.79 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 | 41814 | 2023-01-17 | 56902.96 | 2029-06-06 | 14911.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 | 40156 | 2022-08-24 | 56902.96 | 2029-02-03 | 13253.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 | 39864.02 | 2022-07-31 | 56902.96 | 2029-01-12 | 12961.06 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 | 40156 | 2022-08-24 | 56902.96 | 2029-02-03 | 13253.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 | 52977.33 | 2025-08-02 | 56902.96 | 2031-09-10 | 26074.37 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 | 52977.33 | 2025-08-02 | 56902.96 | 2031-09-10 | 26074.37 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 51181 | 2025-03-29 | 56902.96 | 2029-04-14 | 14278.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 35643 | 2021-08-22 | 56902.96 | 2026-02-26 | -1259.96 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 56874 | 2026-05-26 | 56902.96 | 2027-01-03 | 2971.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N8995 | Operator Seat | 10000 | 55503 | 2026-02-08 | 56902.96 | 2028-02-24 | 8600.04 | WA | Sanjiv Ridge
RD6197 | Cat 785D | N9500 | Air Cond'r-Serv |  |  | 2025-08-02 | 56902.96 | 2026-08-02 |  | WA | Sanjiv Ridge
RD6198 | Cat 785D | N0030 | Truck Body | 20000 | 43889.23 | 2024-03-03 | 53598.82 | 2028-06-28 | 10290.41 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-04-19 | 53598.82 | 2030-04-18 |  | WA | Sanjiv Ridge
RD6198 | Cat 785D | N0200 | A Frame Bearing | 30000 | 53370 | 2026-05-08 | 53598.82 | 2032-06-10 | 29771.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N0550 | Air End | 20000 |  | 2022-06-01 | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N1000 | Engine | 20000 | 52909 | 2026-03-30 | 53598.82 | 2030-04-27 | 19310.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 53121 | 2026-04-15 | 53598.82 | 2026-05-11 | -227.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 | 24467 | 2016-11-09 | 53598.82 | 2024-07-21 | -9131.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 24467 | 2016-11-09 | 53598.82 | 2024-07-21 | -9131.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N1310 | Radiator | 20000 | 48143.36 | 2025-01-18 | 53598.82 | 2029-05-09 | 14544.54 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N2000 | Transmission | 20000 | 34974 | 2022-02-27 | 53598.82 | 2026-09-07 | 1375.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N2004 | Transmission Pump | 20000 | 34974 | 2022-02-27 | 53598.82 | 2026-09-07 | 1375.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N2050 | Torque Convertor | 20000 | 34974 | 2022-02-27 | 53598.82 | 2026-09-07 | 1375.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 34974 | 2022-02-27 | 53598.82 | 2026-09-07 | 1375.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 32132 | 2021-07-08 | 53598.82 | 2024-01-30 | -11466.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 52912 | 2026-03-31 | 53598.82 | 2030-04-28 | 19313.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 40994.94 | 2023-07-04 | 53598.82 | 2025-11-16 | -2603.88 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N3321 | Pump Drive | 20000 | 32132 | 2021-07-08 | 53598.82 | 2026-02-08 | -1466.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N4000 | Bevel Gear | 20000 | 41076 | 2023-07-20 | 53598.82 | 2027-12-03 | 7477.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 | 51396 | 2025-10-21 | 53598.82 | 2030-01-05 | 17797.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 41076 | 2023-07-20 | 53598.82 | 2027-12-03 | 7477.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 41076 | 2023-07-20 | 53598.82 | 2027-12-03 | 7477.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2012-02-10 | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 50906.8 | 2025-09-08 | 53598.82 | 2028-11-25 | 12307.98 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 50906.8 | 2025-09-08 | 53598.82 | 2028-11-25 | 12307.98 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 53598.82 | 2021-08-14 | -23598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 41076 | 2023-07-20 | 53598.82 | 2027-12-03 | 7477.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 |  | 2012-02-10 | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 |  | 2012-02-10 | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 38886.1 | 2023-01-20 | 53598.82 | 2026-06-18 | 287.28 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 38886.1 | 2023-01-20 | 53598.82 | 2026-06-18 | 287.28 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 40905.94 | 2023-06-26 | 53598.82 | 2026-11-15 | 2307.12 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7064 | Pump Hoist | 20000 | 34974 | 2022-02-27 | 53598.82 | 2026-09-07 | 1375.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7120 | Pump Steering | 20000 | 34974 | 2022-02-27 | 53598.82 | 2026-09-07 | 1375.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  | 2012-02-10 | 53598.82 | 2021-08-14 | -23598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  | 2012-02-10 | 53598.82 | 2021-08-14 | -23598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 50217.44 | 2025-07-16 | 53598.82 | 2029-10-10 | 16618.62 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 35778 | 2022-05-06 | 53598.82 | 2026-11-05 | 2179.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7602 | Relief Valve |  | 51389 | 2025-10-22 | 53598.82 | 2029-10-21 |  | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7605 | Steering Hmu | 12000 | 47902 | 2024-12-27 | 53598.82 | 2027-09-07 | 6303.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7610 | Hyd Cooler Core | 20000 |  | 2012-02-10 | 53598.82 | 2019-08-04 | -33598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 |  | 2022-06-01 | 53598.82 | 2018-07-30 | -38598.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 | 47140.59 | 2024-11-04 | 53598.82 | 2028-02-20 | 8541.77 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 | 47140.59 | 2024-11-04 | 53598.82 | 2028-02-20 | 8541.77 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 | 50906.8 | 2025-09-08 | 53598.82 | 2031-12-11 | 27307.98 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 | 50906.8 | 2025-09-08 | 53598.82 | 2031-12-11 | 27307.98 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 | 50906.8 | 2025-09-08 | 53598.82 | 2031-12-11 | 27307.98 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 | 50906.8 | 2025-09-08 | 53598.82 | 2031-12-11 | 27307.98 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 | 51411 | 2025-10-24 | 53598.82 | 2032-01-17 | 27812.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 | 50217.44 | 2025-07-16 | 53598.82 | 2031-10-21 | 26618.62 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 50217.44 | 2025-07-16 | 53598.82 | 2029-10-10 | 16618.62 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 50217.44 | 2025-07-16 | 53598.82 | 2029-10-10 | 16618.62 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 32810 | 2021-09-11 | 53598.82 | 2026-03-31 | -788.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 32810 | 2021-09-11 | 53598.82 | 2026-03-31 | -788.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 32810 | 2021-09-11 | 53598.82 | 2026-03-31 | -788.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 32810 | 2021-09-11 | 53598.82 | 2026-03-31 | -788.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 32810 | 2021-09-11 | 53598.82 | 2026-03-31 | -788.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 32810 | 2021-09-11 | 53598.82 | 2026-03-31 | -788.82 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 53565 | 2026-05-26 | 53598.82 | 2027-01-03 | 2966.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N8995 | Operator Seat | 10000 | 52909 | 2026-03-31 | 53598.82 | 2028-04-17 | 9310.18 | WA | Sanjiv Ridge
RD6198 | Cat 785D | N9500 | Air Cond'r-Serv |  | 51753.76 | 2025-11-19 | 53598.82 | 2026-11-19 |  | WA | Sanjiv Ridge
RD6222 | Cat 740GC | N8995 | Operator Seat | 10000 |  | 2025-04-05 | 15335.9 | 2024-12-10 | -5335.9 | WA | Sanjiv Ridge
RD6260 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-10-02 | 57934 | 2028-09-30 |  | WA | Iron Bridge
RD6260 | Cat 785C | N8501 | Ball Stud Crack Test |  | 55838 | 2026-01-27 | 57934 | 2026-07-28 |  | WA | Iron Bridge
RD6260 | Cat 785C | N8995 | Operator Seat | 6000 |  |  | 57934 | 2017-07-08 | -51934 | WA | Iron Bridge
RD6260 | Cat 785C | N9500 | Air Cond'r-Serv | 5000 |  |  | 57934 | 2017-05-07 | -52934 | WA | Iron Bridge
RD6313 | Cat 785C | N0030 | Truck Body | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-12-14 | 66446.13 | 2027-12-13 |  | WA | Sanjiv Ridge
RD6313 | Cat 785C | N0200 | A Frame Bearing | 30000 | 55023.92 | 2023-02-10 | 66446.13 | 2030-06-22 | 18577.79 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N0550 | Air End | 20000 |  | 2021-02-01 | 66446.13 | 2016-03-25 | -46446.13 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N1000 | Engine | 20000 | 57411.54 | 2023-08-07 | 66446.13 | 2028-10-21 | 10965.41 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 57799.09 | 2025-08-30 | 66446.13 | 2024-07-25 | -8397.04 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 63340.98 | 2025-06-09 | 66446.13 | 2030-02-08 | 16894.85 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 42191.07 | 2015-03-05 | 66446.13 | 2025-06-22 | -4255.06 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N1310 | Radiator | 20000 | 57411.54 | 2023-08-07 | 66446.13 | 2028-10-21 | 10965.41 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N2000 | Transmission | 20000 | 66181 | 2026-04-19 | 66446.13 | 2030-09-23 | 19734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N2004 | Transmission Pump | 20000 | 66181 | 2026-04-19 | 66446.13 | 2030-09-23 | 19734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N2050 | Torque Convertor | 20000 | 63519.8 | 2025-07-08 | 66446.13 | 2030-02-22 | 17073.67 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 63519.8 | 2025-07-08 | 66446.13 | 2030-02-22 | 17073.67 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 66446.13 | 2016-03-25 | -46446.13 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 63519.8 | 2025-07-08 | 66446.13 | 2027-12-15 | 7073.67 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 46230.94 | 2018-01-27 | 66446.13 | 2026-05-11 | -215.19 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 60512 | 2024-10-18 | 66446.13 | 2027-04-18 | 4065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N3321 | Pump Drive | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N4000 | Bevel Gear | 20000 | 50928.86 | 2021-10-16 | 66446.13 | 2027-05-22 | 4482.73 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2021-02-01 | 66446.13 | 2016-03-25 | -46446.13 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2021-02-01 | 66446.13 | 2016-03-25 | -46446.13 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 |  | 2021-02-01 | 66446.13 | 2016-03-25 | -46446.13 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 64617 | 2025-11-29 | 66446.13 | 2029-04-16 | 13170.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 66181 | 2026-04-20 | 66446.13 | 2029-08-19 | 14734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 | 66181 | 2026-04-18 | 66446.13 | 2032-12-01 | 29734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 66181 | 2026-04-18 | 66446.13 | 2030-09-23 | 19734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 | 53973.31 | 2026-03-04 | 66446.13 | 2028-01-20 | 7527.18 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 66181 | 2026-04-20 | 66446.13 | 2029-08-19 | 14734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 55752.8 | 2023-04-26 | 66446.13 | 2027-05-08 | 4306.67 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 55752.8 | 2023-04-26 | 66446.13 | 2027-05-08 | 4306.67 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7064 | Pump Hoist | 20000 | 63577.5 | 2025-07-26 | 66446.13 | 2030-02-27 | 17131.37 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7120 | Pump Steering | 20000 | 50894.78 | 2021-10-12 | 66446.13 | 2027-05-19 | 4448.65 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 66243 | 2026-04-28 | 66446.13 | 2032-12-06 | 29796.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 54897.69 | 2023-01-29 | 66446.13 | 2030-06-12 | 18451.56 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7602 | Relief Valve |  |  | 2024-04-13 | 66446.13 | 2028-04-12 |  | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7605 | Steering Hmu | 12000 | 66181 | 2026-04-20 | 66446.13 | 2028-12-22 | 11734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7610 | Hyd Cooler Core | 20000 |  | 2021-02-01 | 66446.13 | 2016-03-25 | -46446.13 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7654 | Hyd Accum Service Brake | 30000 | 60512 | 2024-10-18 | 66446.13 | 2031-09-04 | 24065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 30000 | 60512 | 2024-10-18 | 66446.13 | 2031-09-04 | 24065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 30000 | 60512 | 2024-10-18 | 66446.13 | 2031-09-04 | 24065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 64617 | 2025-11-29 | 66446.13 | 2032-07-29 | 28170.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 66181 | 2026-04-20 | 66446.13 | 2032-12-01 | 29734.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 57411.54 | 2023-08-07 | 66446.13 | 2030-12-30 | 20965.41 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 57411.54 | 2023-08-07 | 66446.13 | 2030-12-30 | 20965.41 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 60512 | 2024-10-18 | 66446.13 | 2031-09-04 | 24065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 57799.09 | 2023-09-11 | 66446.13 | 2031-01-30 | 21352.96 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 54681.66 | 2023-01-04 | 66446.13 | 2028-03-17 | 8235.53 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 54681.66 | 2023-01-04 | 66446.13 | 2028-03-17 | 8235.53 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 60046.9 | 2024-03-26 | 66446.13 | 2029-05-20 | 13600.77 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 60512 | 2024-10-18 | 66446.13 | 2029-06-26 | 14065.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 66410 | 2026-05-26 | 66446.13 | 2027-01-20 | 2963.87 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N8995 | Operator Seat | 10000 | 60496.5 | 2024-04-29 | 66446.13 | 2027-04-17 | 4050.37 | WA | Sanjiv Ridge
RD6313 | Cat 785C | N9500 | Air Cond'r-Serv |  |  | 2025-07-08 | 66446.13 | 2026-07-08 |  | WA | Sanjiv Ridge
RD6314 | Cat 785C | N0030 | Truck Body | 20000 |  | 2022-06-01 | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-06-01 | 54833.54 | 2027-05-31 |  | WA | SANJIV RIDGE
RD6314 | Cat 785C | N0200 | A Frame Bearing | 30000 | 40399 | 2019-11-11 | 54833.54 | 2029-10-24 | 15565.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N0550 | Air End | 20000 | 53294 | 2024-04-08 | 54833.54 | 2030-06-13 | 18460.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N1000 | Engine | 20000 | 38762 | 2017-09-13 | 54833.54 | 2027-04-07 | 3928.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 |  | 2022-06-01 | 54833.54 | 2014-06-13 | -54583.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 38762 | 2017-09-13 | 54833.54 | 2027-04-07 | 3928.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 38762 | 2017-09-13 | 54833.54 | 2027-04-07 | 3928.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N1310 | Radiator | 20000 | 38762 | 2017-09-13 | 54833.54 | 2027-04-07 | 3928.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N2000 | Transmission | 20000 | 49117.86 | 2023-02-01 | 54833.54 | 2029-07-14 | 14284.32 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N2004 | Transmission Pump | 20000 | 41794 | 2020-09-07 | 54833.54 | 2027-12-06 | 6960.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N2050 | Torque Convertor | 20000 | 50377.46 | 2023-05-31 | 54833.54 | 2029-10-23 | 15543.92 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 35866 | 2014-07-17 | 54833.54 | 2026-08-19 | 1032.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 40293 | 2019-09-01 | 54833.54 | 2025-05-30 | -4540.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 49686.4 | 2023-04-13 | 54833.54 | 2029-08-28 | 14852.86 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 49685.97 | 2023-04-13 | 54833.54 | 2027-06-20 | 4852.43 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N3321 | Pump Drive | 20000 | 38762 | 2017-09-13 | 54833.54 | 2027-04-07 | 3928.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N4000 | Bevel Gear | 20000 | 49117.86 | 2023-02-01 | 54833.54 | 2029-07-14 | 14284.32 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 49117.86 | 2023-02-01 | 54833.54 | 2029-07-14 | 14284.32 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 50645.04 | 2023-06-24 | 54833.54 | 2029-11-13 | 15811.5 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 |  | 2022-06-01 | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 50377.46 | 2023-05-31 | 54833.54 | 2028-09-18 | 10543.92 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 53372.1 | 2025-10-27 | 54833.54 | 2029-05-15 | 13538.56 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 | 53644 | 2026-02-01 | 54833.54 | 2032-09-18 | 28810.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 53644 | 2026-02-01 | 54833.54 | 2030-07-11 | 18810.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 |  | 2022-06-01 | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 50377.46 | 2023-05-31 | 54833.54 | 2028-09-18 | 10543.92 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 50377.46 | 2023-05-31 | 54833.54 | 2028-09-18 | 10543.92 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 50377.46 | 2023-05-31 | 54833.54 | 2028-09-18 | 10543.92 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7064 | Pump Hoist | 20000 | 53372.1 | 2025-10-21 | 54833.54 | 2030-06-19 | 18538.56 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7120 | Pump Steering | 20000 | 53633 | 2026-01-29 | 54833.54 | 2030-07-10 | 18799.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 29155 | 2012-12-10 | 54833.54 | 2027-05-09 | 4321.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 41328 | 2020-06-06 | 54833.54 | 2030-01-07 | 16494.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 53294.3 | 2024-04-11 | 54833.54 | 2030-06-13 | 18460.76 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 53294.3 | 2024-04-11 | 54833.54 | 2030-06-13 | 18460.76 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7602 | Relief Valve |  |  | 2024-04-08 | 54833.54 | 2028-04-07 |  | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7605 | Steering Hmu | 12000 | 53362.7 | 2024-04-28 | 54833.54 | 2028-09-16 | 10529.16 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7610 | Hyd Cooler Core | 20000 |  | 2022-06-01 | 54833.54 | 2018-10-10 | -34833.54 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7654 | Hyd Accum Service Brake | 30000 | 53372.1 | 2025-10-23 | 54833.54 | 2032-08-27 | 28538.56 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 30000 | 53372.1 | 2025-10-23 | 54833.54 | 2032-08-27 | 28538.56 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 30000 | 53372.1 | 2025-10-23 | 54833.54 | 2032-08-27 | 28538.56 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 41328 | 2020-06-06 | 54833.54 | 2030-01-07 | 16494.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 37482 | 2014-10-14 | 54833.54 | 2029-03-05 | 12648.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 29783 | 2013-02-01 | 54833.54 | 2027-06-28 | 4949.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 51496.25 | 2023-10-05 | 54833.54 | 2032-03-30 | 26662.71 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 26906 | 2012-07-11 | 54833.54 | 2026-11-10 | 2072.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 26906 | 2012-07-11 | 54833.54 | 2026-11-10 | 2072.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 53294.3 | 2024-04-11 | 54833.54 | 2030-06-13 | 18460.76 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 53294.3 | 2024-04-11 | 54833.54 | 2030-06-13 | 18460.76 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 53294.3 | 2024-04-11 | 54833.54 | 2030-06-13 | 18460.76 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 53294.3 | 2024-04-11 | 54833.54 | 2030-06-13 | 18460.76 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 53362.7 | 2024-04-28 | 54833.54 | 2030-06-18 | 18529.16 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 53362.7 | 2024-04-28 | 54833.54 | 2030-06-18 | 18529.16 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 53362.7 | 2024-04-28 | 54833.54 | 2030-06-18 | 18529.16 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 53362.7 | 2024-04-28 | 54833.54 | 2030-06-18 | 18529.16 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 54813 | 2026-05-26 | 54833.54 | 2027-01-21 | 2979.46 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N8995 | Operator Seat | 10000 | 52068.99 | 2023-11-11 | 54833.54 | 2027-12-28 | 7235.45 | WA | SANJIV RIDGE
RD6314 | Cat 785C | N9500 | Air Cond'r-Serv |  | 53773.57 | 2026-02-20 | 54833.54 | 2027-02-20 |  | WA | SANJIV RIDGE
RD6502 | Cat 785C | N0030 | Truck Body | 20000 |  | 2022-06-01 | 67106.81 | 2016-02-01 | -47106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-06-01 | 67106.81 | 2027-05-31 |  | WA | Sanjiv Ridge
RD6502 | Cat 785C | N0200 | A Frame Bearing | 30000 | 57258.43 | 2022-10-09 | 67106.81 | 2030-10-26 | 20151.62 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N0550 | Air End | 20000 |  | 2022-06-01 | 67106.81 | 2016-02-01 | -47106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N1000 | Engine | 20000 | 61507.1 | 2024-01-04 | 67106.81 | 2029-07-23 | 14400.29 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 61507.1 | 2014-02-07 | 67106.81 | 2025-03-26 | -5349.71 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 43103 | 2018-01-25 | 67106.81 | 2025-07-12 | -4003.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 43103 | 2018-01-25 | 67106.81 | 2025-07-12 | -4003.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N1310 | Radiator | 20000 | 61507.1 | 2024-01-04 | 67106.81 | 2029-07-23 | 14400.29 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N2000 | Transmission | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N2004 | Transmission Pump | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N2050 | Torque Convertor | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 67106.81 | 2016-02-01 | -47106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 59402.31 | 2023-04-09 | 67106.81 | 2026-11-28 | 2295.5 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 |  | 2022-06-01 | 67106.81 | 2016-02-01 | -47106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 59402.31 | 2023-04-09 | 67106.81 | 2026-11-28 | 2295.5 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N3321 | Pump Drive | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N4000 | Bevel Gear | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 | 63952.26 | 2025-09-17 | 67106.81 | 2030-02-04 | 16845.45 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 | 62708.15 | 2025-06-20 | 67106.81 | 2029-10-27 | 15601.34 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 64631 | 2025-11-16 | 67106.81 | 2030-03-30 | 17524.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 64670 | 2025-11-24 | 67106.81 | 2030-04-02 | 17563.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 51920 | 2021-02-07 | 67106.81 | 2026-05-06 | -186.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 51920 | 2021-02-07 | 67106.81 | 2026-05-06 | -186.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 67106.81 | 2018-04-11 | -37106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 67106.81 | 2016-02-01 | -47106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 | 50093 | 2020-02-27 | 67106.81 | 2027-01-22 | 2986.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 57730.38 | 2022-11-19 | 67106.81 | 2027-08-21 | 5623.57 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 57730.38 | 2022-11-19 | 67106.81 | 2027-08-21 | 5623.57 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 57730.38 | 2022-11-19 | 67106.81 | 2027-08-21 | 5623.57 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7064 | Pump Hoist | 20000 | 61507.1 | 2024-01-04 | 67106.81 | 2029-07-23 | 14400.29 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7120 | Pump Steering | 20000 | 65996 | 2026-02-26 | 67106.81 | 2030-07-17 | 18889.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 57730.38 | 2022-11-19 | 67106.81 | 2030-12-03 | 20623.57 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 66928 | 2026-05-08 | 67106.81 | 2032-12-08 | 29821.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 62443.36 | 2025-06-02 | 67106.81 | 2029-10-06 | 15336.55 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 62443.36 | 2025-06-02 | 67106.81 | 2029-10-06 | 15336.55 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7602 | Relief Valve |  |  | 2025-04-30 | 67106.81 | 2029-04-29 |  | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7605 | Steering Hmu | 12000 | 57495.43 | 2022-10-26 | 67106.81 | 2026-12-05 | 2388.62 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7610 | Hyd Cooler Core | 20000 |  | 2022-06-01 | 67106.81 | 2016-02-01 | -47106.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7654 | Hyd Accum Service Brake | 15000 | 61706.52 | 2025-03-22 | 67106.81 | 2028-07-04 | 9599.71 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 15000 | 61646.51 | 2024-04-26 | 67106.81 | 2028-06-29 | 9539.7 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 15000 | 61646.51 | 2024-04-26 | 67106.81 | 2028-06-29 | 9539.7 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 51920 | 2021-02-07 | 67106.81 | 2029-08-25 | 14813.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 51920 | 2021-02-07 | 67106.81 | 2029-08-25 | 14813.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 61507.1 | 2024-01-04 | 67106.81 | 2031-10-01 | 24400.29 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 61507.1 | 2024-01-04 | 67106.81 | 2031-10-01 | 24400.29 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 60139.36 | 2023-07-27 | 67106.81 | 2031-06-14 | 23032.55 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 23503 | 2012-04-15 | 67106.81 | 2023-06-05 | -13603.81 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 59714.9 | 2023-05-04 | 67106.81 | 2029-03-02 | 12608.09 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 67089 | 2026-05-26 | 67106.81 | 2027-01-22 | 2982.19 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N8995 | Operator Seat | 10000 | 61439.51 | 2023-11-23 | 67106.81 | 2027-05-10 | 4332.7 | WA | Sanjiv Ridge
RD6502 | Cat 785C | N9500 | Air Cond'r-Serv |  |  | 2025-08-26 | 67106.81 | 2026-08-26 |  | WA | Sanjiv Ridge
RD6503 | Cat 785C | N0030 | Truck Body | 20000 |  |  | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-06-01 | 67683.26 | 2027-05-31 |  | WA | Sanjiv Ridge
RD6503 | Cat 785C | N0200 | A Frame Bearing | 30000 | 53179 | 2021-09-20 | 67683.26 | 2029-10-19 | 15495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N0550 | Air End | 20000 |  | 2022-06-01 | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N1000 | Engine | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 64047.63 | 2025-08-25 | 67683.26 | 2025-08-30 | -3385.63 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N1310 | Radiator | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N2000 | Transmission | 20000 | 52562 | 2019-06-28 | 67683.26 | 2027-06-22 | 4878.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N2004 | Transmission Pump | 20000 | 52562 | 2019-06-28 | 67683.26 | 2027-06-22 | 4878.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N2050 | Torque Convertor | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 60238 | 2023-08-03 | 67683.26 | 2026-12-18 | 2554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 |  | 2022-06-01 | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 62285.68 | 2025-03-24 | 67683.26 | 2027-05-31 | 4602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N3321 | Pump Drive | 20000 | 52562 | 2019-06-28 | 67683.26 | 2027-06-22 | 4878.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N4000 | Bevel Gear | 20000 | 49037 | 2018-08-21 | 67683.26 | 2026-09-13 | 1353.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 49037 | 2018-08-21 | 67683.26 | 2026-09-13 | 1353.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 49037 | 2018-08-21 | 67683.26 | 2026-09-13 | 1353.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 | 60238 | 2023-08-03 | 67683.26 | 2029-02-25 | 12554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 62285.68 | 2025-03-24 | 67683.26 | 2028-07-04 | 9602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 62285.68 | 2025-03-24 | 67683.26 | 2028-07-04 | 9602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 | 60238 | 2023-08-03 | 67683.26 | 2031-05-06 | 22554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 | 60238 | 2023-08-03 | 67683.26 | 2029-02-25 | 12554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 |  | 2022-06-01 | 67683.26 | 2015-12-17 | -47683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 60238 | 2023-08-03 | 67683.26 | 2028-01-22 | 7554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 60238 | 2023-08-03 | 67683.26 | 2028-01-22 | 7554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 60238 | 2023-08-03 | 67683.26 | 2028-01-22 | 7554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7064 | Pump Hoist | 20000 | 53179 | 2019-09-20 | 67683.26 | 2027-08-11 | 5495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7120 | Pump Steering | 20000 | 55201 | 2021-01-23 | 67683.26 | 2028-01-19 | 7517.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  |  | 67683.26 | 2018-02-24 | -37683.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 33105 | 2014-04-23 | 67683.26 | 2025-05-27 | -4578.26 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 55750 | 2021-03-18 | 67683.26 | 2028-03-03 | 8066.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 57015 | 2021-06-22 | 67683.26 | 2028-06-13 | 9331.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7602 | Relief Valve |  |  | 2022-12-04 | 67683.26 | 2026-12-03 |  | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7605 | Steering Hmu | 12000 | 60238 | 2023-08-03 | 67683.26 | 2027-05-27 | 4554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7610 | Hyd Cooler Core | 20000 | 60914.94 | 2023-12-11 | 67683.26 | 2029-04-21 | 13231.68 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7654 | Hyd Accum Service Brake | 15000 | 60238 | 2023-08-03 | 67683.26 | 2028-01-22 | 7554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 15000 | 60238 | 2023-08-03 | 67683.26 | 2028-01-22 | 7554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 15000 | 60238 | 2023-08-03 | 67683.26 | 2028-01-22 | 7554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 48017 | 2018-06-08 | 67683.26 | 2028-09-01 | 10333.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 48017 | 2018-06-08 | 67683.26 | 2028-09-01 | 10333.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 54272 | 2020-10-12 | 67683.26 | 2030-01-14 | 16588.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 60238 | 2023-08-03 | 67683.26 | 2031-05-06 | 22554.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 53179 | 2019-09-20 | 67683.26 | 2029-10-19 | 15495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 53179 | 2019-09-20 | 67683.26 | 2029-10-19 | 15495.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 60194 | 2022-11-10 | 67683.26 | 2029-02-22 | 12510.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 62285.68 | 2025-03-24 | 67683.26 | 2029-08-08 | 14602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 57015 | 2021-06-22 | 67683.26 | 2028-06-13 | 9331.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 57015 | 2021-06-22 | 67683.26 | 2028-06-13 | 9331.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 62285.68 | 2025-03-24 | 67683.26 | 2029-08-08 | 14602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 62285.68 | 2025-03-24 | 67683.26 | 2029-08-08 | 14602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 62285.68 | 2025-03-24 | 67683.26 | 2029-08-08 | 14602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 62285.68 | 2025-03-24 | 67683.26 | 2029-08-08 | 14602.42 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 67651 | 2026-05-26 | 67683.26 | 2027-01-20 | 2967.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N8995 | Operator Seat | 10000 | 60194 | 2022-10-07 | 67683.26 | 2026-12-15 | 2510.74 | WA | Sanjiv Ridge
RD6503 | Cat 785C | N9500 | Air Cond'r-Serv |  | 65727 | 2026-01-05 | 67683.26 | 2027-01-05 |  | WA | Sanjiv Ridge
RD6527 | Cat 777G | N0030 | Truck Body | 20000 |  | 2022-06-01 | 47332.5 | 2015-11-29 | -27332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N0066 | Fire Suppression Sys Cylinder |  |  | 2023-01-04 | 47332.5 | 2028-01-03 |  | WA | Miralga Creek
RD6527 | Cat 777G | N0200 | A Frame Bearing | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N1000 | Engine | 18000 | 38327 | 2021-10-25 | 47332.5 | 2029-11-10 | 8994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N1002-01 | Engine Valve Adj - Initial | 500 | 38327 |  | 47332.5 | 2023-02-20 | -8505.5 | WA | Miralga Creek
RD6527 | Cat 777G | N1100-L | Turbo Primary LEFT | 18000 | 38327 | 2021-10-25 | 47332.5 | 2029-11-10 | 8994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N1100-R | Turbo Primary RIGHT | 18000 | 38327 | 2021-10-25 | 47332.5 | 2029-11-10 | 8994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N1301 | Water Pump | 9000 |  | 2022-06-01 | 47332.5 | 2011-09-08 | -38332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N1310 | Radiator | 18000 | 38327 | 2021-10-25 | 47332.5 | 2029-11-10 | 8994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N2000 | Transmission | 18000 | 35633 | 2016-12-10 | 47332.5 | 2028-10-28 | 6300.5 | WA | Miralga Creek
RD6527 | Cat 777G | N2002 | Oil Cooler - Transmission | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N2025 | Pump Trans / T/C / Brk Cooling | 18000 | 38326 | 2021-11-01 | 47332.5 | 2029-11-09 | 8993.5 | WA | Miralga Creek
RD6527 | Cat 777G | N2050 | Torque Convertor | 18000 | 38327 | 2021-10-25 | 47332.5 | 2029-11-10 | 8994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N3029 | Uni's T/C - Trans | 9000 | 43341.1 | 2024-02-14 | 47332.5 | 2028-04-29 | 5008.6 | WA | Miralga Creek
RD6527 | Cat 777G | N4000 | Bevel Gear | 18000 | 47075 | 2026-03-27 | 47332.5 | 2033-03-20 | 17742.5 | WA | Miralga Creek
RD6527 | Cat 777G | N5000-03 | Final Drive POS 3 | 18000 | 38327 | 2021-10-25 | 47332.5 | 2029-11-10 | 8994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N5000-04 | Final Drive POS 4 | 18000 | 38316 | 2021-10-19 | 47332.5 | 2029-11-08 | 8983.5 | WA | Miralga Creek
RD6527 | Cat 777G | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 37923 | 2021-05-26 | 47332.5 | 2028-07-20 | 5590.5 | WA | Miralga Creek
RD6527 | Cat 777G | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 38327 | 2021-10-25 | 47332.5 | 2028-09-15 | 5994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N6030-RF | Brake Slack Adj RHT FRONT | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N6060-RE | Oil Cooler - Brakes REAR | 18000 |  | 2022-06-01 | 47332.5 | 2015-02-21 | -29332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7064 | Pump Hoist | 18000 | 38326 | 2021-11-01 | 47332.5 | 2029-11-09 | 8993.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7120 | Pump Steering | 18000 | 38326 | 2021-10-25 | 47332.5 | 2029-11-09 | 8993.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7122 | Pump Emerg/Sup Steering | 18000 | 38326 | 2021-11-01 | 47332.5 | 2029-11-09 | 8993.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7474-L | Hyd Cyl Hoist LEFT | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7542-L | Hyd Cyl Steer LEFT | 20000 | 38389 | 2021-11-10 | 47332.5 | 2030-08-26 | 11056.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 38389 | 2021-11-10 | 47332.5 | 2030-08-26 | 11056.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7605 | Steering Hmu | 12000 | 38326 | 2021-10-26 | 47332.5 | 2027-07-22 | 2993.5 | WA | Miralga Creek
RD6527 | Cat 777G | N7653 | Hyd Accum Park Brake | 30000 | 43341.1 | 2024-02-19 | 47332.5 | 2036-05-23 | 26008.6 | WA | Miralga Creek
RD6527 | Cat 777G | N7654 | Hyd Accum Service Brake | 30000 | 43341.1 | 2024-02-19 | 47332.5 | 2036-05-23 | 26008.6 | WA | Miralga Creek
RD6527 | Cat 777G | N8000 | Main Frame/Chassis | 10000 |  | 2022-06-01 | 47332.5 | 2012-01-26 | -37332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8122-01 | Wheel Group POS 1 | 30000 | 37923 | 2021-05-26 | 47332.5 | 2034-04-24 | 20590.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8122-02 | Wheel Group POS 2 | 30000 | 38327 | 2021-10-25 | 47332.5 | 2034-06-20 | 20994.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8130-L | Steering Tie Rods LEFT | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8130-R | Steering Tie Rods RIGHT | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8140 | Steering Y Piece | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8155-L | Steering Control Arm LEFT | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8155-R | Steering Control Arm RIGHT | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8200-01 | Ride Strut POS 1 | 30000 |  | 2022-06-01 | 47332.5 | 2019-10-01 | -17332.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8200-02 | Ride Strut POS 2 | 30000 | 16355 | 2015-08-22 | 47332.5 | 2026-01-11 | -977.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8200-03 | Ride Strut POS 3 | 30000 | 44596 | 2024-09-11 | 47332.5 | 2036-11-15 | 27263.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8200-04 | Ride Strut POS 4 | 30000 | 38326 | 2021-10-27 | 47332.5 | 2034-06-19 | 20993.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-01 | Steering Ball Studs POS 1 | 10000 | 38389 | 2021-11-10 | 47332.5 | 2026-10-23 | 1056.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-02 | Steering Ball Studs POS 2 | 10000 | 38389 | 2021-11-10 | 47332.5 | 2026-10-23 | 1056.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-03 | Steering Ball Studs POS 3 | 10000 | 38389 | 2021-11-10 | 47332.5 | 2026-10-23 | 1056.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-04 | Steering Ball Studs POS 4 | 10000 | 38389 | 2021-11-10 | 47332.5 | 2026-10-23 | 1056.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-05 | Steering Ball Studs POS 5 | 10000 | 39096 | 2022-01-10 | 47332.5 | 2027-01-30 | 1763.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-06 | Steering Ball Studs POS 6 | 10000 | 39096 | 2022-01-10 | 47332.5 | 2027-01-30 | 1763.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-07 | Steering Ball Studs POS 7 | 10000 | 39096 | 2022-01-10 | 47332.5 | 2027-01-30 | 1763.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8442-08 | Steering Ball Studs POS 8 | 10000 | 39096 | 2022-01-10 | 47332.5 | 2027-01-30 | 1763.5 | WA | Miralga Creek
RD6527 | Cat 777G | N8501 | Ball Stud Crack Test |  | 47332.5 | 2026-05-22 | 47332.5 | 2026-11-18 |  | WA | Miralga Creek
RD6527 | Cat 777G | N8995 | Operator Seat | 10000 | 47288 | 2026-05-11 | 47332.5 | 2030-03-24 | 9955.5 | WA | Miralga Creek
RD6527 | Cat 777G | N9500 | Air Cond'r-Serv |  |  | 2025-07-15 | 47332.5 | 2026-07-15 |  | WA | Miralga Creek
RD6530 | Cat 785C | N0030 | Truck Body | 20000 |  |  | 66379.67 | 2016-03-31 | -46379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-04-21 | 66379.67 | 2030-04-20 |  | WA | Sanjiv Ridge
RD6530 | Cat 785C | N0200 | A Frame Bearing | 30000 | 52052 | 2021-09-17 | 66379.67 | 2029-11-02 | 15672.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N0550 | Air End | 20000 |  | 2022-06-01 | 66379.67 | 2016-03-31 | -46379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N1000 | Engine | 20000 | 59841.74 | 2024-10-10 | 66379.67 | 2029-05-09 | 13462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 60496.2 | 2025-02-02 | 66379.67 | 2025-03-03 | -5633.47 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 56090.84 | 2022-07-16 | 66379.67 | 2028-07-13 | 9711.17 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 56090.84 | 2022-07-16 | 66379.67 | 2028-07-13 | 9711.17 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N1310 | Radiator | 20000 | 59841.74 | 2024-10-10 | 66379.67 | 2029-05-09 | 13462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N2000 | Transmission | 20000 | 55755 | 2022-06-07 | 66379.67 | 2028-06-16 | 9375.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N2004 | Transmission Pump | 20000 | 59841.74 | 2024-10-10 | 66379.67 | 2029-05-09 | 13462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N2050 | Torque Convertor | 20000 | 59841.74 | 2024-10-10 | 66379.67 | 2029-05-09 | 13462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 59841.74 | 2024-10-10 | 66379.67 | 2029-05-09 | 13462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 66379.67 | 2016-03-31 | -46379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 59841.74 | 2024-10-10 | 66379.67 | 2027-03-01 | 3462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 19000 | 2014-06-15 | 66379.67 | 2020-05-29 | -27379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 59841.74 | 2024-10-10 | 66379.67 | 2027-03-01 | 3462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N3321 | Pump Drive | 20000 | 58605.93 | 2023-12-16 | 66379.67 | 2029-01-30 | 12226.26 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N4000 | Bevel Gear | 20000 | 59841.74 | 2024-10-10 | 66379.67 | 2029-05-09 | 13462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 66379.67 | 2016-03-31 | -46379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 66379.67 | 2016-03-31 | -46379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 50214 | 2021-05-08 | 66379.67 | 2027-03-31 | 3834.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 49737 | 2021-01-18 | 66379.67 | 2027-02-21 | 3357.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 | 28229 | 2016-01-15 | 66379.67 | 2022-06-06 | -18150.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 59841.74 | 2024-10-10 | 66379.67 | 2028-04-04 | 8462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 59841.74 | 2024-10-10 | 66379.67 | 2028-04-04 | 8462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 66379.67 | 2018-06-09 | -36379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 66379.67 | 2016-03-31 | -46379.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 | 28229 | 2016-01-15 | 66379.67 | 2022-06-06 | -18150.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 59841.74 | 2024-10-10 | 66379.67 | 2028-04-04 | 8462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 65778 | 2026-04-14 | 66379.67 | 2029-07-23 | 14398.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 59841.74 | 2024-10-10 | 66379.67 | 2028-04-04 | 8462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7064 | Pump Hoist | 20000 | 50325 | 2021-05-20 | 66379.67 | 2027-04-09 | 3945.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7120 | Pump Steering | 20000 | 52287 | 2021-10-10 | 66379.67 | 2027-09-13 | 5907.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 32631 | 2017-05-06 | 66379.67 | 2025-08-01 | -3748.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 54684 | 2022-04-05 | 66379.67 | 2030-05-31 | 18304.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 50498 | 2021-06-04 | 66379.67 | 2027-04-22 | 4118.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 50498 | 2021-06-04 | 66379.67 | 2027-04-22 | 4118.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7602 | Relief Valve |  |  | 2025-04-21 | 66379.67 | 2029-04-20 |  | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7605 | Steering Hmu | 12000 | 60493.73 | 2025-01-31 | 66379.67 | 2027-09-29 | 6114.06 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7610 | Hyd Cooler Core | 20000 | 28229 | 2016-01-15 | 66379.67 | 2022-06-06 | -18150.67 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7654 | Hyd Accum Service Brake | 30000 | 59841.74 | 2024-10-10 | 66379.67 | 2031-07-18 | 23462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 30000 | 59841.74 | 2024-10-10 | 66379.67 | 2031-07-18 | 23462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 30000 | 59841.74 | 2024-10-10 | 66379.67 | 2031-07-18 | 23462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 45269 | 2019-12-16 | 66379.67 | 2028-05-08 | 8889.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 59841.74 | 2024-10-10 | 66379.67 | 2031-07-18 | 23462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 59841.74 | 2024-10-10 | 66379.67 | 2031-07-18 | 23462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 59841.74 | 2024-10-10 | 66379.67 | 2031-07-18 | 23462.07 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 50630 | 2021-06-15 | 66379.67 | 2029-07-11 | 14250.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 61448.92 | 2025-04-21 | 66379.67 | 2031-11-24 | 25069.25 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 50519 | 2021-06-07 | 66379.67 | 2027-04-24 | 4139.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 66344 | 2026-05-26 | 66379.67 | 2027-01-20 | 2964.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N8995 | Operator Seat | 10000 | 63970 | 2025-12-05 | 66379.67 | 2028-01-25 | 7590.33 | WA | Sanjiv Ridge
RD6530 | Cat 785C | N9500 | Air Cond'r-Serv |  |  | 2025-07-24 | 66379.67 | 2026-07-24 |  | WA | Sanjiv Ridge
RD6531 | Cat 785C | N0030 | Truck Body | 20000 |  |  | 58227.56 | 2018-01-12 | -38227.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2022-06-01 | 58227.56 | 2027-05-31 |  | WA | Sanjiv Ridge
RD6531 | Cat 785C | N0200 | A Frame Bearing | 30000 | 28263 | 2017-02-05 | 58227.56 | 2026-05-31 | 35.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N0550 | Air End | 20000 | 53356.7 | 2023-09-13 | 58227.56 | 2029-09-19 | 15129.14 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N1000 | Engine | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 40520 | 2025-11-13 | 58227.56 | 2022-07-31 | -17457.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N1310 | Radiator | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N2000 | Transmission | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N2004 | Transmission Pump | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N2050 | Torque Convertor | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 58227.56 | 2018-01-12 | -38227.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 56195 | 2025-10-23 | 58227.56 | 2028-02-24 | 7967.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 46421 | 2021-10-08 | 58227.56 | 2028-03-13 | 8193.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 56195 | 2025-10-23 | 58227.56 | 2028-02-24 | 7967.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N3321 | Pump Drive | 20000 | 40520 | 2020-01-12 | 58227.56 | 2026-11-27 | 2292.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N4000 | Bevel Gear | 20000 | 46421 | 2021-10-09 | 58227.56 | 2028-03-13 | 8193.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 58227.56 | 2018-01-12 | -38227.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 58227.56 | 2018-01-12 | -38227.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 51176.68 | 2023-02-17 | 58227.56 | 2029-03-29 | 12949.12 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 56277 | 2025-12-22 | 58227.56 | 2030-05-11 | 18049.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 | 19576 | 2015-01-15 | 58227.56 | 2022-04-27 | -18651.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 56195 | 2025-10-29 | 58227.56 | 2029-03-30 | 12967.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 50423.08 | 2022-11-27 | 58227.56 | 2027-12-25 | 7195.52 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 58227.56 | 2020-03-22 | -28227.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 58227.56 | 2018-01-12 | -38227.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 | 19576 | 2015-01-15 | 58227.56 | 2022-04-27 | -18651.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 51550.2 | 2023-04-21 | 58227.56 | 2028-03-24 | 8322.64 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 51550.2 | 2023-04-21 | 58227.56 | 2028-03-24 | 8322.64 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 51550.2 | 2023-04-21 | 58227.56 | 2028-03-24 | 8322.64 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7064 | Pump Hoist | 20000 | 50423.08 | 2022-11-27 | 58227.56 | 2029-01-28 | 12195.52 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7120 | Pump Steering | 20000 | 56246 | 2025-12-08 | 58227.56 | 2030-05-08 | 18018.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 48870.27 | 2022-07-12 | 58227.56 | 2030-12-04 | 20642.71 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 47022 | 2021-12-14 | 58227.56 | 2030-07-10 | 18794.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 56753 | 2026-02-01 | 58227.56 | 2030-06-18 | 18525.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 54333.21 | 2023-11-08 | 58227.56 | 2029-12-06 | 16105.65 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7602 | Relief Valve |  |  | 2024-03-29 | 58227.56 | 2028-03-28 |  | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7605 | Steering Hmu | 12000 | 51184.3 | 2023-03-16 | 58227.56 | 2027-06-29 | 4956.74 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7610 | Hyd Cooler Core | 20000 | 29202 | 2017-04-08 | 58227.56 | 2024-06-05 | -9025.56 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7654 | Hyd Accum Service Brake | 15000 | 56195 | 2025-10-23 | 58227.56 | 2029-03-30 | 12967.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 15000 | 56195 | 2025-10-23 | 58227.56 | 2029-03-30 | 12967.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 15000 | 56195 | 2025-10-23 | 58227.56 | 2029-03-30 | 12967.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 38557 | 2019-05-17 | 58227.56 | 2028-08-31 | 10329.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 50423.08 | 2022-11-27 | 58227.56 | 2031-04-08 | 22195.52 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 47022 | 2021-12-15 | 58227.56 | 2030-07-10 | 18794.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 50423.08 | 2022-11-27 | 58227.56 | 2031-04-08 | 22195.52 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 51184.3 | 2023-03-22 | 58227.56 | 2031-06-08 | 22956.74 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 29288 | 2017-04-15 | 58227.56 | 2026-08-21 | 1060.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 42545 | 2020-12-04 | 58227.56 | 2027-05-08 | 4317.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 42545 | 2020-12-04 | 58227.56 | 2027-05-08 | 4317.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 45594 | 2021-08-24 | 58227.56 | 2028-01-07 | 7366.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 45594 | 2021-08-24 | 58227.56 | 2028-01-07 | 7366.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 45719 | 2021-08-06 | 58227.56 | 2028-01-17 | 7491.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 45719 | 2021-08-06 | 58227.56 | 2028-01-17 | 7491.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 42545 | 2020-12-04 | 58227.56 | 2027-05-08 | 4317.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 42545 | 2020-12-04 | 58227.56 | 2027-05-08 | 4317.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 58190 | 2026-05-26 | 58227.56 | 2027-01-20 | 2962.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N8995 | Operator Seat | 10000 | 57413 | 2026-03-17 | 58227.56 | 2028-06-01 | 9185.44 | WA | Sanjiv Ridge
RD6531 | Cat 785C | N9500 | Air Cond'r-Serv |  |  | 2022-01-05 | 58227.56 | 2023-01-05 |  | WA | Sanjiv Ridge
RD6532 | Cat 785C | N0030 | Truck Body | 20000 | 54035.5 | 2024-10-01 | 60509.94 | 2029-05-14 | 13525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-10-26 | 60509.94 | 2030-10-25 |  | WA | Sanjiv Ridge
RD6532 | Cat 785C | N0200 | A Frame Bearing | 30000 | 54035.5 | 2024-10-01 | 60509.94 | 2031-07-23 | 23525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N0550 | Air End | 20000 | 51170.25 | 2023-08-10 | 60509.94 | 2028-09-27 | 10660.31 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N1000 | Engine | 20000 | 50538.34 | 2022-09-10 | 60509.94 | 2028-08-07 | 10028.4 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 57295.99 | 2025-09-02 | 60509.94 | 2025-10-03 | -2963.95 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 35882 | 2018-11-14 | 60509.94 | 2025-05-23 | -4627.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 35882 | 2018-11-14 | 60509.94 | 2025-05-23 | -4627.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N1310 | Radiator | 20000 | 41614 | 2020-04-19 | 60509.94 | 2026-08-24 | 1104.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N2000 | Transmission | 20000 | 56950 | 2025-07-24 | 60509.94 | 2030-01-02 | 16440.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N2004 | Transmission Pump | 20000 | 56950 | 2025-07-24 | 60509.94 | 2030-01-02 | 16440.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N2050 | Torque Convertor | 20000 | 55325.74 | 2025-03-11 | 60509.94 | 2029-08-25 | 14815.8 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 58663 | 2025-12-27 | 60509.94 | 2030-05-19 | 18153.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 60509.94 | 2017-07-13 | -40509.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 56950 | 2025-07-24 | 60509.94 | 2027-10-25 | 6440.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 54035.5 | 2024-10-01 | 60509.94 | 2029-05-14 | 13525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 54035.5 | 2024-10-01 | 60509.94 | 2027-03-06 | 3525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N3321 | Pump Drive | 20000 | 56950 | 2025-07-24 | 60509.94 | 2030-01-02 | 16440.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N4000 | Bevel Gear | 20000 | 50998.74 | 2023-07-06 | 60509.94 | 2028-09-13 | 10488.8 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 60509.94 | 2017-07-13 | -40509.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 60509.94 | 2017-07-13 | -40509.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 58706 | 2026-01-14 | 60509.94 | 2030-05-23 | 18196.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 58706 | 2026-01-14 | 60509.94 | 2030-05-23 | 18196.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 | 36799 | 2019-01-20 | 60509.94 | 2025-08-04 | -3710.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 50144 | 2022-07-16 | 60509.94 | 2027-06-03 | 4634.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 50144 | 2022-07-16 | 60509.94 | 2027-06-03 | 4634.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 60509.94 | 2019-09-21 | -30509.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 60509.94 | 2017-07-13 | -40509.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 | 50144 | 2022-07-18 | 60509.94 | 2028-07-07 | 9634.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 54035.5 | 2024-10-01 | 60509.94 | 2028-04-09 | 8525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 54035.5 | 2024-10-01 | 60509.94 | 2028-04-09 | 8525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 54035.5 | 2024-10-01 | 60509.94 | 2028-04-09 | 8525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7064 | Pump Hoist | 20000 | 54332.63 | 2024-11-18 | 60509.94 | 2029-06-07 | 13822.69 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7120 | Pump Steering | 20000 | 44000 | 2020-11-18 | 60509.94 | 2027-03-03 | 3490.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 34005 | 2018-04-29 | 60509.94 | 2027-03-04 | 3495.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 54035.5 | 2024-10-01 | 60509.94 | 2031-07-23 | 23525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 60215 | 2026-05-02 | 60509.94 | 2030-09-20 | 19705.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 54035.5 | 2024-10-01 | 60509.94 | 2029-05-14 | 13525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7605 | Steering Hmu | 12000 | 60215 | 2026-05-01 | 60509.94 | 2028-12-19 | 11705.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7610 | Hyd Cooler Core | 20000 | 59117 | 2026-02-14 | 60509.94 | 2030-06-25 | 18607.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7654 | Hyd Accum Service Brake | 30000 | 54035.5 | 2024-10-01 | 60509.94 | 2031-07-23 | 23525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 30000 | 54035.5 | 2024-10-01 | 60509.94 | 2031-07-23 | 23525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 30000 | 54035.5 | 2024-10-01 | 60509.94 | 2031-07-23 | 23525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 50144 | 2022-07-16 | 60509.94 | 2030-09-15 | 19634.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 50144 | 2022-07-16 | 60509.94 | 2030-09-15 | 19634.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 28403 | 2016-12-04 | 60509.94 | 2025-12-10 | -2106.94 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 34553 | 2018-06-21 | 60509.94 | 2027-04-16 | 4043.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 37577 | 2019-03-14 | 60509.94 | 2027-12-14 | 7067.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 32352 | 2017-09-16 | 60509.94 | 2026-10-22 | 1842.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 47190 | 2021-07-22 | 60509.94 | 2027-11-13 | 6680.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 60474 | 2026-05-26 | 60509.94 | 2027-01-20 | 2964.06 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N8995 | Operator Seat | 10000 | 54035.5 | 2024-10-01 | 60509.94 | 2027-03-06 | 3525.56 | WA | Sanjiv Ridge
RD6532 | Cat 785C | N9500 | Air Cond'r-Serv |  |  | 2025-07-24 | 60509.94 | 2026-07-24 |  | WA | Sanjiv Ridge
RD6533 | Cat 785C | N0030 | Truck Body | 20000 |  |  | 64732.59 | 2016-08-09 | -44732.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N0066 | Fire Suppression Sys Cylinder |  | 62723 | 2025-10-27 | 64732.59 | 2030-10-26 |  | WA | Sanjiv Ridge
RD6533 | Cat 785C | N0200 | A Frame Bearing | 30000 | 38860 | 2018-12-14 | 64732.59 | 2027-04-23 | 4127.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N0550 | Air End | 20000 | 58933 | 2024-02-20 | 64732.59 | 2029-07-07 | 14200.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N1000 | Engine | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N1002-01 | Engine Valve Adj - Initial | 250 | 59997.83 | 2025-01-31 | 64732.59 | 2025-06-03 | -4484.76 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N1100-L | Turbo Primary LEFT | 20000 | 64086 | 2026-03-07 | 64732.59 | 2030-08-23 | 19353.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N1100-R | Turbo Primary RIGHT | 20000 | 64092 | 2026-03-07 | 64732.59 | 2030-08-24 | 19359.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N1310 | Radiator | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N2000 | Transmission | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N2004 | Transmission Pump | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N2050 | Torque Convertor | 20000 | 64098 | 2026-03-04 | 64732.59 | 2030-08-24 | 19365.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N2055 | Convertor Charge Scav Pump | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 64732.59 | 2016-08-09 | -44732.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N3021 | Uni's Eng - Pump Drive | 10000 | 59430.99 | 2024-11-26 | 64732.59 | 2027-06-08 | 4698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N3028 | Drive Shaft T/C - Trans | 20000 | 18322 | 2014-03-15 | 64732.59 | 2020-08-14 | -26410.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N3029 | Uni's T/C - Trans | 10000 | 59430.99 | 2024-11-26 | 64732.59 | 2027-06-08 | 4698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N3321 | Pump Drive | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N4000 | Bevel Gear | 20000 | 64664 | 2026-05-20 | 64732.59 | 2030-10-09 | 19931.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N4100-L | Rear Axle LEFT | 20000 |  | 2022-06-01 | 64732.59 | 2016-08-09 | -44732.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N4100-R | Rear Axle RIGHT | 20000 |  | 2022-06-01 | 64732.59 | 2016-08-09 | -44732.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N5000-03 | Final Drive POS 3 | 20000 | 64086 | 2026-03-07 | 64732.59 | 2030-08-23 | 19353.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N5000-04 | Final Drive POS 4 | 20000 | 64080 | 2026-02-17 | 64732.59 | 2030-08-23 | 19347.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N5015 | Oil Cooler AXLE | 20000 | 13357 | 2013-06-15 | 64732.59 | 2019-07-14 | -31375.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 61922.52 | 2025-07-27 | 64732.59 | 2029-01-27 | 12189.93 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 61922.52 | 2025-07-27 | 64732.59 | 2029-01-27 | 12189.93 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 64732.59 | 2018-10-18 | -34732.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 64732.59 | 2016-08-09 | -44732.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N6060 | Oil Cooler - Brakes | 20000 | 13357 | 2013-06-15 | 64732.59 | 2019-07-14 | -31375.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N6200-F | Press Converter FRONT | 15000 | 59430.99 | 2024-11-26 | 64732.59 | 2028-07-12 | 9698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N6200-LR | Press Converter LEFT REAR | 15000 | 59430.99 | 2024-11-26 | 64732.59 | 2028-07-12 | 9698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N6200-RR | Press Converter RIGHT REAR | 15000 | 59430.99 | 2024-11-26 | 64732.59 | 2028-07-12 | 9698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7064 | Pump Hoist | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7120 | Pump Steering | 20000 | 47146 | 2020-10-24 | 64732.59 | 2026-12-07 | 2413.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 64095 | 2026-03-08 | 64732.59 | 2032-11-01 | 29362.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 64098 | 2026-03-09 | 64732.59 | 2032-11-01 | 29365.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7542-L | Hyd Cyl Steer LEFT | 20000 | 50756 | 2021-08-25 | 64732.59 | 2027-09-22 | 6023.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 54552 | 2022-06-12 | 64732.59 | 2028-07-22 | 9819.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7602 | Relief Valve |  |  | 2024-03-22 | 64732.59 | 2028-03-21 |  | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7605 | Steering Hmu | 12000 | 59430.1 | 2024-05-11 | 64732.59 | 2027-11-15 | 6697.51 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7610 | Hyd Cooler Core | 20000 | 64102 | 2026-03-03 | 64732.59 | 2030-08-25 | 19369.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7654 | Hyd Accum Service Brake | 30000 | 61044.22 | 2025-04-20 | 64732.59 | 2032-03-02 | 26311.63 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7657-L | Hyd Accum Steering LEFT | 30000 | 59430.99 | 2024-11-26 | 64732.59 | 2031-10-25 | 24698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N7657-R | Hyd Accum Steering RIGHT | 30000 | 59430.99 | 2024-11-26 | 64732.59 | 2031-10-25 | 24698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8122-01 | Wheel Group POS 1 | 30000 | 47445 | 2020-12-10 | 64732.59 | 2029-03-10 | 12712.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8122-02 | Wheel Group POS 2 | 30000 | 47445 | 2020-12-10 | 64732.59 | 2029-03-10 | 12712.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8200-01 | Ride Strut POS 1 | 30000 | 30841 | 2017-01-15 | 64732.59 | 2025-07-21 | -3891.59 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8200-02 | Ride Strut POS 2 | 30000 | 38594 | 2018-11-14 | 64732.59 | 2027-04-02 | 3861.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8200-03 | Ride Strut POS 3 | 30000 | 64556 | 2026-04-27 | 64732.59 | 2032-12-08 | 29823.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8200-04 | Ride Strut POS 4 | 30000 | 58933 | 2024-02-20 | 64732.59 | 2031-09-15 | 24200.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-01 | Steering Ball Studs POS 1 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-02 | Steering Ball Studs POS 2 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-03 | Steering Ball Studs POS 3 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-04 | Steering Ball Studs POS 4 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-05 | Steering Ball Studs POS 5 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-06 | Steering Ball Studs POS 6 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-07 | Steering Ball Studs POS 7 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8442-08 | Steering Ball Studs POS 8 | 20000 | 59430.99 | 2024-11-26 | 64732.59 | 2029-08-16 | 14698.4 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8501 | Ball Stud Crack Test | 3000 | 64716 | 2026-05-26 | 64732.59 | 2027-01-22 | 2983.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N8995 | Operator Seat | 10000 | 63373 | 2025-12-21 | 64732.59 | 2028-04-18 | 8640.41 | WA | Sanjiv Ridge
RD6533 | Cat 785C | N9500 | Air Cond'r-Serv |  |  | 2025-06-28 | 64732.59 | 2026-06-28 |  | WA | Sanjiv Ridge
RD6562 | Cat 785D | N0030 | Truck Body | 20000 | 49376.83 | 2023-05-19 | 62901.67 | 2027-09-20 | 6475.16 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-10-22 | 62901.67 | 2030-10-21 |  | WA | Sanjiv Ridge
RD6562 | Cat 785D | N0200 | A Frame Bearing | 30000 | 42605 | 2021-10-26 | 62901.67 | 2028-05-16 | 9703.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N0550 | Air End | 20000 | 52885.17 | 2024-04-02 | 62901.67 | 2028-06-06 | 9983.5 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N1000 | Engine | 20000 | 61479 | 2026-02-08 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 62006 | 2026-03-24 | 62901.67 | 2026-04-10 | -645.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 | 41405 | 2021-05-30 | 62901.67 | 2026-02-06 | -1496.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 50387.13 | 2023-08-16 | 62901.67 | 2027-12-03 | 7485.46 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N1310 | Radiator | 20000 | 61478 | 2026-02-07 | 62901.67 | 2030-03-04 | 18576.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N2000 | Transmission | 20000 | 61479 | 2026-02-07 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N2004 | Transmission Pump | 20000 | 61479 | 2026-02-08 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N2050 | Torque Convertor | 20000 | 61479 | 2026-02-08 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 61479 | 2026-02-08 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 62901.67 | 2017-09-14 | -42901.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 61479 | 2026-02-04 | 62901.67 | 2028-02-22 | 8577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 41405 | 2021-05-30 | 62901.67 | 2026-02-06 | -1496.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 61479 | 2026-02-08 | 62901.67 | 2028-02-22 | 8577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N3321 | Pump Drive | 20000 | 61479 | 2026-02-04 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N4000 | Bevel Gear | 20000 | 61479 | 2026-02-07 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 | 58365 | 2025-05-15 | 62901.67 | 2029-07-16 | 15463.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 | 58365 | 2025-05-15 | 62901.67 | 2029-07-16 | 15463.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 51931.68 | 2024-01-15 | 62901.67 | 2028-03-27 | 9030.01 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 58365 | 2025-05-15 | 62901.67 | 2029-07-16 | 15463.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 | 41405 | 2021-05-30 | 62901.67 | 2026-02-06 | -1496.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 55908 | 2024-10-31 | 62901.67 | 2028-01-11 | 8006.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 56853.92 | 2025-01-02 | 62901.67 | 2028-03-21 | 8952.25 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 62901.67 | 2019-09-25 | -32901.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 | 48753 | 2023-03-28 | 62901.67 | 2027-08-04 | 5851.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 | 41405 | 2021-05-30 | 62901.67 | 2026-02-06 | -1496.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 | 41405 | 2021-05-30 | 62901.67 | 2026-02-06 | -1496.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 61479 | 2026-02-08 | 62901.67 | 2029-02-27 | 13577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 61345 | 2026-01-04 | 62901.67 | 2029-02-17 | 13443.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 57617.21 | 2025-03-10 | 62901.67 | 2028-05-17 | 9715.54 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7064 | Pump Hoist | 20000 | 61479 | 2026-02-04 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7120 | Pump Steering | 20000 | 61479 | 2026-02-04 | 62901.67 | 2030-03-04 | 18577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 49520.92 | 2023-06-01 | 62901.67 | 2029-10-10 | 16619.25 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 60360 | 2025-10-23 | 62901.67 | 2031-12-22 | 27458.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 57353.88 | 2025-02-18 | 62901.67 | 2029-05-03 | 14452.21 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 57353.88 | 2025-02-18 | 62901.67 | 2029-05-03 | 14452.21 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7602 | Relief Valve |  |  | 2023-11-29 | 62901.67 | 2027-11-28 |  | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7605 | Steering Hmu | 12000 | 61478 | 2026-02-08 | 62901.67 | 2028-07-19 | 10576.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7610 | Hyd Cooler Core | 20000 | 41405 | 2021-05-30 | 62901.67 | 2026-02-06 | -1496.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 | 57836.99 | 2025-03-23 | 62901.67 | 2028-06-02 | 9935.32 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 | 56379.06 | 2024-12-01 | 62901.67 | 2028-02-15 | 8477.39 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 | 56379.06 | 2024-12-01 | 62901.67 | 2028-02-15 | 8477.39 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 | 41405 | 2021-05-30 | 62901.67 | 2028-02-17 | 8503.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 | 41405 | 2021-05-30 | 62901.67 | 2028-02-17 | 8503.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 | 32521 | 2018-10-22 | 62901.67 | 2026-04-30 | -380.67 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 | 41405 | 2021-04-30 | 62901.67 | 2028-02-17 | 8503.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 | 60360 | 2025-10-23 | 62901.67 | 2031-12-22 | 27458.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 | 60360 | 2025-10-22 | 62901.67 | 2031-12-22 | 27458.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 45308.36 | 2022-07-09 | 62901.67 | 2026-11-22 | 2406.69 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 62891 | 2026-05-26 | 62901.67 | 2027-01-04 | 2989.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N8995 | Operator Seat | 10000 | 61479 | 2026-02-08 | 62901.67 | 2028-02-22 | 8577.33 | WA | Sanjiv Ridge
RD6562 | Cat 785D | N9500 | Air Cond'r-Serv |  |  | 2025-08-09 | 62901.67 | 2026-08-09 |  | WA | Sanjiv Ridge
RD6564 | Cat 785D | N0030 | Truck Body | 20000 |  | 2022-06-01 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-04-13 | 63459.48 | 2030-04-12 |  | WA | Sanjiv Ridge
RD6564 | Cat 785D | N0200 | A Frame Bearing | 30000 | 59783.27 | 2025-08-30 | 63459.48 | 2031-09-29 | 26323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N0550 | Air End | 20000 |  | 2022-06-01 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N1000 | Engine | 20000 | 58778.75 | 2025-05-30 | 63459.48 | 2029-07-06 | 15319.27 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 59714 | 2025-08-23 | 63459.48 | 2025-09-11 | -3495.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 | 40230 | 2021-02-01 | 63459.48 | 2025-10-01 | -3229.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 40230 | 2021-02-01 | 63459.48 | 2025-10-01 | -3229.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N1310 | Radiator | 20000 | 58778.75 | 2025-05-30 | 63459.48 | 2029-07-06 | 15319.27 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N2000 | Transmission | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N2004 | Transmission Pump | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N2050 | Torque Convertor | 20000 | 58778.75 | 2025-05-30 | 63459.48 | 2029-07-06 | 15319.27 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 52513 | 2024-01-21 | 63459.48 | 2026-03-19 | -946.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 | 40230 | 2021-02-01 | 63459.48 | 2025-10-01 | -3229.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 59783.27 | 2025-08-30 | 63459.48 | 2027-09-08 | 6323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N3321 | Pump Drive | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N4000 | Bevel Gear | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2011-09-17 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 59783.27 | 2025-08-30 | 63459.48 | 2028-09-13 | 11323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 59783.27 | 2025-08-30 | 63459.48 | 2028-09-13 | 11323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 63459.48 | 2019-08-15 | -33459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 |  | 2011-09-17 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 |  | 2011-09-17 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 50034 | 2023-06-21 | 63459.48 | 2026-09-22 | 1574.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 49460 | 2023-05-13 | 63459.48 | 2026-08-10 | 1000.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 48948.96 | 2023-03-31 | 63459.48 | 2026-07-03 | 489.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7064 | Pump Hoist | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7120 | Pump Steering | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 40230 | 2021-02-01 | 63459.48 | 2027-10-12 | 6770.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 | 40230 | 2021-02-01 | 63459.48 | 2027-10-12 | 6770.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7602 | Relief Valve |  |  | 2023-11-18 | 63459.48 | 2027-11-17 |  | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7605 | Steering Hmu | 12000 | 55606.16 | 2024-09-23 | 63459.48 | 2027-03-31 | 4146.68 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7610 | Hyd Cooler Core | 20000 |  | 2011-09-17 | 63459.48 | 2017-08-04 | -43459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7654 | Hyd Accum Service Brake | 15000 |  | 2022-06-01 | 63459.48 | 2016-07-29 | -48459.48 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 15000 | 56574.43 | 2024-11-24 | 63459.48 | 2028-01-19 | 8114.95 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 15000 | 56574.43 | 2024-11-24 | 63459.48 | 2028-01-19 | 8114.95 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 | 44552 | 2022-04-08 | 63459.48 | 2028-08-27 | 11092.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 | 44552 | 2022-04-08 | 63459.48 | 2028-08-27 | 11092.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 | 50307.94 | 2023-07-13 | 63459.48 | 2029-10-27 | 16848.46 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 | 44690 | 2022-05-03 | 63459.48 | 2028-09-06 | 11230.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 | 58265 | 2025-04-13 | 63459.48 | 2031-06-08 | 24805.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 | 58265 | 2025-04-13 | 63459.48 | 2031-06-08 | 24805.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 59783.27 | 2025-08-30 | 63459.48 | 2029-09-18 | 16323.79 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 66444 | 2026-05-26 | 63459.48 | 2027-08-14 | 5984.52 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N8995 | Operator Seat | 10000 | 59515.87 | 2025-08-01 | 63459.48 | 2027-08-20 | 6056.39 | WA | Sanjiv Ridge
RD6564 | Cat 785D | N9500 | Air Cond'r-Serv |  |  | 2025-08-01 | 63459.48 | 2026-08-01 |  | WA | Sanjiv Ridge
RD6565 | Cat 785D | N0030 | Truck Body | 20000 | 50391 | 2023-11-26 | 60870.4 | 2028-05-02 | 9520.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N0066 | Fire Suppression Sys Cylinder |  | 58584.48 | 2025-10-29 | 60870.4 | 2030-10-28 |  | WA | Sanjiv Ridge
RD6565 | Cat 785D | N0200 | A Frame Bearing | 30000 | 42959 | 2021-10-10 | 60870.4 | 2028-11-08 | 12088.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N0550 | Air End | 20000 | 51877 | 2024-04-07 | 60870.4 | 2028-08-20 | 11006.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N1000 | Engine | 20000 | 59007 | 2025-12-17 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N1002-01 | Engine Valve Adj - Initial | 250 | 60181 | 2026-03-24 | 60870.4 | 2026-04-25 | -439.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N1100-L | Turbo Primary LEFT | 20000 | 59007 | 2025-12-17 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N1100-R | Turbo Primary RIGHT | 20000 | 59007 | 2025-12-17 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N1310 | Radiator | 20000 | 59007 | 2025-12-15 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N2000 | Transmission | 20000 | 59007 | 2025-12-11 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N2004 | Transmission Pump | 20000 | 59007 | 2025-12-12 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N2050 | Torque Convertor | 20000 | 54084.42 | 2024-10-22 | 60870.4 | 2029-01-31 | 13214.02 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N2055 | Convertor Charge Scav Pump | 20000 | 54084.42 | 2024-10-22 | 60870.4 | 2029-01-31 | 13214.02 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N3020 | Drive Shaft Eng - Pump Drive | 20000 |  |  | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N3021 | Uni's Eng - Pump Drive | 10000 | 59007 | 2025-12-14 | 60870.4 | 2028-01-21 | 8136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N3028 | Drive Shaft T/C - Trans | 20000 |  | 2022-06-01 | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N3029 | Uni's T/C - Trans | 10000 | 60174 | 2026-03-23 | 60870.4 | 2028-04-16 | 9303.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N3321 | Pump Drive | 20000 | 59007 | 2025-12-10 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N4000 | Bevel Gear | 20000 | 59007 | 2025-12-11 | 60870.4 | 2030-01-30 | 18136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N4100-L | Rear Axle LEFT | 20000 | 58615 | 2025-11-02 | 60870.4 | 2030-01-01 | 17744.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N4100-R | Rear Axle RIGHT | 20000 | 58615 | 2025-11-02 | 60870.4 | 2030-01-01 | 17744.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N5000-03 | Final Drive POS 3 | 20000 | 58926 | 2025-12-01 | 60870.4 | 2030-01-24 | 18055.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N5000-04 | Final Drive POS 4 | 20000 | 58926 | 2025-12-01 | 60870.4 | 2030-01-24 | 18055.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N5015 | Oil Cooler AXLE | 20000 |  | 2011-09-17 | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N5020-LF | Wheel Bearing LEFT FRONT | 15000 | 59007 | 2025-12-17 | 60870.4 | 2029-01-25 | 13136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N5020-RF | Wheel Bearing RIGHT FRONT | 15000 | 59007 | 2025-12-17 | 60870.4 | 2029-01-25 | 13136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6030-F | Brake Slack Adj FRONT | 30000 |  | 2022-06-01 | 60870.4 | 2020-02-22 | -30870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6030-RE | Brake Slack Adj REAR | 20000 |  | 2022-06-01 | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6060 | Oil Cooler - Brakes | 20000 |  | 2011-09-17 | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6063 | Oil Cooler - Steering | 20000 |  | 2011-09-17 | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6200-F | Press Converter FRONT | 15000 | 59150 | 2025-12-30 | 60870.4 | 2029-02-05 | 13279.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6200-LR | Press Converter LEFT REAR | 15000 | 59007 | 2025-12-11 | 60870.4 | 2029-01-25 | 13136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N6200-RR | Press Converter RIGHT REAR | 15000 | 59007 | 2025-12-11 | 60870.4 | 2029-01-25 | 13136.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7064 | Pump Hoist | 20000 | 43778 | 2022-03-07 | 60870.4 | 2026-12-29 | 2907.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7120 | Pump Steering | 20000 | 43778 | 2022-03-07 | 60870.4 | 2026-12-29 | 2907.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7474-L | Hyd Cyl Hoist LEFT | 30000 | 38748 | 2020-10-02 | 60870.4 | 2028-01-02 | 7877.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7474-R | Hyd Cyl Hoist RIGHT | 30000 |  | 2011-09-17 | 60870.4 | 2020-02-22 | -30870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7542-L | Hyd Cyl Steer LEFT | 20000 | 60859 | 2026-05-26 | 60870.4 | 2030-06-17 | 19988.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7542-R | Hyd Cyl Steer RIGHT | 20000 | 60859 | 2026-05-26 | 60870.4 | 2030-06-17 | 19988.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7602 | Relief Valve |  | 60857.89 | 2026-05-27 | 60870.4 | 2030-05-26 |  | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7605 | Steering Hmu | 12000 | 55656 | 2025-03-28 | 60870.4 | 2027-10-13 | 6785.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7610 | Hyd Cooler Core | 20000 |  | 2011-09-17 | 60870.4 | 2018-02-12 | -40870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7654 | Hyd Accum Service Brake | 30000 |  | 2022-06-01 | 60870.4 | 2020-02-22 | -30870.4 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7657-L | Hyd Accum Steering LEFT | 30000 | 54380.48 | 2024-12-02 | 60870.4 | 2031-03-04 | 23510.08 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N7657-R | Hyd Accum Steering RIGHT | 30000 | 54380.48 | 2024-12-02 | 60870.4 | 2031-03-04 | 23510.08 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8122-01 | Wheel Group POS 1 | 30000 | 43779 | 2022-03-06 | 60870.4 | 2029-01-08 | 12908.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8122-02 | Wheel Group POS 2 | 30000 | 43779 | 2022-03-06 | 60870.4 | 2029-01-08 | 12908.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8200-01 | Ride Strut POS 1 | 30000 | 52368 | 2024-06-07 | 60870.4 | 2030-10-06 | 21497.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8200-02 | Ride Strut POS 2 | 30000 | 42959 | 2021-10-18 | 60870.4 | 2028-11-08 | 12088.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8200-03 | Ride Strut POS 3 | 30000 | 42959 | 2021-10-12 | 60870.4 | 2028-11-08 | 12088.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8200-04 | Ride Strut POS 4 | 30000 | 38477 | 2020-07-17 | 60870.4 | 2027-12-12 | 7606.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-01 | Steering Ball Studs POS 1 | 20000 | 46563.42 | 2022-12-08 | 60870.4 | 2027-07-24 | 5693.02 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-02 | Steering Ball Studs POS 2 | 20000 | 46563.42 | 2022-12-08 | 60870.4 | 2027-07-24 | 5693.02 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-03 | Steering Ball Studs POS 3 | 20000 | 46563.42 | 2022-12-08 | 60870.4 | 2027-07-24 | 5693.02 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-04 | Steering Ball Studs POS 4 | 20000 | 46563.42 | 2022-12-08 | 60870.4 | 2027-07-24 | 5693.02 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-05 | Steering Ball Studs POS 5 | 20000 | 43778 | 2022-03-06 | 60870.4 | 2026-12-29 | 2907.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-06 | Steering Ball Studs POS 6 | 20000 | 43778 | 2022-03-06 | 60870.4 | 2026-12-29 | 2907.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-07 | Steering Ball Studs POS 7 | 20000 | 43778 | 2022-03-06 | 60870.4 | 2026-12-29 | 2907.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8442-08 | Steering Ball Studs POS 8 | 20000 | 43778 | 2022-03-06 | 60870.4 | 2026-12-29 | 2907.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8501 | Ball Stud Crack Test | 3000 | 60857 | 2026-05-26 | 60870.4 | 2027-01-04 | 2986.6 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N8995 | Operator Seat | 10000 | 53208.81 | 2024-08-16 | 60870.4 | 2026-11-17 | 2338.41 | WA | Sanjiv Ridge
RD6565 | Cat 785D | N9500 | Air Cond'r-Serv |  |  | 2025-08-03 | 60870.4 | 2026-08-03 |  | WA | Sanjiv Ridge
RD6601 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-19 | 3453.85 | 2030-01-18 |  | WA | McPhee Creek
RD6601 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N1002 | Engine Valve Adj | 4000 | 60.27 | 2025-06-04 | 3453.85 | 2026-07-21 | 606.42 | WA | McPhee Creek
RD6601 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 60.27 | 2025-06-03 | 3453.85 | 2025-08-20 | -3143.58 | WA | McPhee Creek
RD6601 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-19 | 3453.85 | 2027-10-06 | 5546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-19 | 3453.85 | 2027-10-06 | 5546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-19 | 3453.85 | 2034-05-15 | 32546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-19 | 3453.85 | 2032-11-24 | 26546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-19 | 3453.85 | 2032-11-24 | 26546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-19 | 3453.85 | 2032-11-24 | 26546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-19 | 3453.85 | 2029-03-25 | 11546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-19 | 3453.85 | 2029-06-22 | 12546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-19 | 3453.85 | 2029-06-22 | 12546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-19 | 3453.85 | 2029-01-18 |  | WA | McPhee Creek
RD6601 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-19 | 3453.85 | 2029-12-18 | 14546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-19 | 3453.85 | 2028-12-25 | 10546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-19 | 3453.85 | 2028-12-25 | 10546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-19 | 3453.85 | 2030-06-15 | 16546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 2993 | 2026-04-17 | 3453.85 | 2027-01-10 | 2539.15 | WA | McPhee Creek
RD6601 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-19 | 3453.85 | 2028-06-30 | 8546.15 | WA | McPhee Creek
RD6601 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-19 | 3453.85 | 2026-01-19 |  | WA | McPhee Creek
RD6602 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-19 | 4287.2 | 2030-01-18 |  | WA | McPhee Creek
RD6602 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N1002 | Engine Valve Adj | 4000 | 99 | 2025-06-09 | 4287.2 | 2026-05-11 | -188.2 | WA | McPhee Creek
RD6602 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 99 | 2025-06-09 | 4287.2 | 2025-06-10 | -3938.2 | WA | McPhee Creek
RD6602 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-19 | 4287.2 | 2027-07-23 | 4712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-19 | 4287.2 | 2027-07-23 | 4712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-19 | 4287.2 | 2034-03-01 | 31712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-19 | 4287.2 | 2032-09-11 | 25712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-19 | 4287.2 | 2032-09-11 | 25712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-19 | 4287.2 | 2032-09-11 | 25712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-19 | 4287.2 | 2029-01-09 | 10712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-19 | 4287.2 | 2029-04-09 | 11712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-19 | 4287.2 | 2029-04-09 | 11712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-19 | 4287.2 | 2029-01-18 |  | WA | McPhee Creek
RD6602 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-19 | 4287.2 | 2029-10-04 | 13712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-19 | 4287.2 | 2028-10-12 | 9712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-19 | 4287.2 | 2028-10-12 | 9712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-19 | 4287.2 | 2030-04-01 | 15712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 3732 | 2026-04-17 | 4287.2 | 2027-01-01 | 2444.8 | WA | McPhee Creek
RD6602 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-19 | 4287.2 | 2028-04-16 | 7712.8 | WA | McPhee Creek
RD6602 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-19 | 4287.2 | 2026-01-19 |  | WA | McPhee Creek
RD6603 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2026-02-01 | 7161 | 2031-01-31 |  | WA | McPhee Creek
RD6603 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2026-02-01 | 7161 | 2028-04-28 | 7839 | WA | McPhee Creek
RD6603 | Cat 789D | N1000 | Engine | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N1002 | Engine Valve Adj | 4000 | 4744.8 | 2024-06-13 | 7161 | 2026-10-17 | 1583.8 | WA | McPhee Creek
RD6603 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 5756.17 | 2025-11-22 | 7161 | 2026-02-14 | -1154.83 | WA | McPhee Creek
RD6603 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2026-02-01 | 7161 | 2026-11-08 | 1839 | WA | McPhee Creek
RD6603 | Cat 789D | N1310 | Radiator | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2026-02-01 | 7161 | 2026-11-08 | 1839 | WA | McPhee Creek
RD6603 | Cat 789D | N2000 | Transmission | 15000 |  | 2026-02-01 | 7161 | 2028-04-28 | 7839 | WA | McPhee Creek
RD6603 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2026-02-01 | 7161 | 2028-04-28 | 7839 | WA | McPhee Creek
RD6603 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2026-02-01 | 7161 | 2033-06-17 | 28839 | WA | McPhee Creek
RD6603 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2026-02-01 | 7161 | 2031-12-29 | 22839 | WA | McPhee Creek
RD6603 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 | 5720 | 2025-09-08 | 7161 | 2029-09-21 | 13559 | WA | McPhee Creek
RD6603 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2026-02-01 | 7161 | 2028-04-28 | 7839 | WA | McPhee Creek
RD6603 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2026-02-01 | 7161 | 2031-12-29 | 22839 | WA | McPhee Creek
RD6603 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2026-02-01 | 7161 | 2031-12-29 | 22839 | WA | McPhee Creek
RD6603 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2026-02-01 | 7161 | 2028-04-28 | 7839 | WA | McPhee Creek
RD6603 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2026-02-01 | 7161 | 2028-04-28 | 7839 | WA | McPhee Creek
RD6603 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2026-02-01 | 7161 | 2028-07-26 | 8839 | WA | McPhee Creek
RD6603 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2026-02-01 | 7161 | 2028-07-26 | 8839 | WA | McPhee Creek
RD6603 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N7602 | Relief Valve |  |  | 2026-02-01 | 7161 | 2030-01-31 |  | WA | McPhee Creek
RD6603 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2026-02-01 | 7161 | 2029-01-21 | 10839 | WA | McPhee Creek
RD6603 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2026-02-01 | 7161 | 2028-01-29 | 6839 | WA | McPhee Creek
RD6603 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2026-02-01 | 7161 | 2028-01-29 | 6839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2026-02-01 | 7161 | 2029-07-18 | 12839 | WA | McPhee Creek
RD6603 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 6597 | 2026-04-17 | 7161 | 2027-01-01 | 2436 | WA | McPhee Creek
RD6603 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2026-02-01 | 7161 | 2027-08-03 | 4839 | WA | McPhee Creek
RD6603 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2026-02-01 | 7161 | 2027-02-01 |  | WA | McPhee Creek
RD6604 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2026-02-01 | 6718.6 | 2031-01-31 |  | WA | McPhee Creek
RD6604 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N1000 | Engine | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N1002 | Engine Valve Adj | 4000 | 4695.4 | 2024-06-16 | 6718.6 | 2026-11-21 | 1976.8 | WA | McPhee Creek
RD6604 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 5607.86 | 2025-11-22 | 6718.6 | 2026-03-12 | -860.74 | WA | McPhee Creek
RD6604 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2026-02-01 | 6718.6 | 2026-12-18 | 2281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N1310 | Radiator | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2026-02-01 | 6718.6 | 2026-12-18 | 2281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N2000 | Transmission | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N2050 | Torque Convertor | 18000 | 5578 | 2025-09-16 | 6718.6 | 2030-07-13 | 16859.4 | WA | McPhee Creek
RD6604 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2026-02-01 | 6718.6 | 2033-07-27 | 29281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2026-02-01 | 6718.6 | 2032-02-07 | 23281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2026-02-01 | 6718.6 | 2032-02-07 | 23281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2026-02-01 | 6718.6 | 2032-02-07 | 23281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2026-02-01 | 6718.6 | 2028-06-06 | 8281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2026-02-01 | 6718.6 | 2028-09-03 | 9281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2026-02-01 | 6718.6 | 2028-09-03 | 9281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7602 | Relief Valve |  |  | 2026-02-01 | 6718.6 | 2030-01-31 |  | WA | McPhee Creek
RD6604 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2026-02-01 | 6718.6 | 2029-03-01 | 11281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2026-02-01 | 6718.6 | 2028-03-09 | 7281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2026-02-01 | 6718.6 | 2028-03-09 | 7281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2026-02-01 | 6718.6 | 2029-08-27 | 13281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 6289 | 2026-04-17 | 6718.6 | 2027-01-13 | 2570.4 | WA | McPhee Creek
RD6604 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2026-02-01 | 6718.6 | 2027-09-12 | 5281.4 | WA | McPhee Creek
RD6604 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2026-02-01 | 6718.6 | 2027-02-01 |  | WA | McPhee Creek
RD6605 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2026-02-01 | 4708.7 | 2031-01-31 |  | WA | McPhee Creek
RD6605 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N1000 | Engine | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N1002 | Engine Valve Adj | 4000 | 3289.9 | 2025-09-20 | 4708.7 | 2027-01-14 | 2581.2 | WA | McPhee Creek
RD6605 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 3305.52 | 2025-11-22 | 4708.7 | 2026-02-14 | -1153.18 | WA | McPhee Creek
RD6605 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2026-02-01 | 4708.7 | 2027-06-15 | 4291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N1310 | Radiator | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2026-02-01 | 4708.7 | 2027-06-15 | 4291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N2000 | Transmission | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2026-02-01 | 4708.7 | 2034-01-22 | 31291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2026-02-01 | 4708.7 | 2032-08-04 | 25291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2026-02-01 | 4708.7 | 2032-08-04 | 25291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2026-02-01 | 4708.7 | 2032-08-04 | 25291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2026-02-01 | 4708.7 | 2028-12-03 | 10291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 | 3289.9 | 2024-05-04 | 4708.7 | 2029-12-21 | 14581.2 | WA | McPhee Creek
RD6605 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2026-02-01 | 4708.7 | 2029-03-02 | 11291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7602 | Relief Valve |  |  | 2026-02-01 | 4708.7 | 2030-01-31 |  | WA | McPhee Creek
RD6605 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2026-02-01 | 4708.7 | 2029-08-28 | 13291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2026-02-01 | 4708.7 | 2028-09-04 | 9291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2026-02-01 | 4708.7 | 2028-09-04 | 9291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2026-02-01 | 4708.7 | 2030-02-23 | 15291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 4301 | 2026-04-17 | 4708.7 | 2027-01-15 | 2592.3 | WA | McPhee Creek
RD6605 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2026-02-01 | 4708.7 | 2028-03-10 | 7291.3 | WA | McPhee Creek
RD6605 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2026-02-01 | 4708.7 | 2027-02-01 |  | WA | McPhee Creek
RD6606 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2026-02-01 | 4532.2 | 2031-01-31 |  | WA | McPhee Creek
RD6606 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N1000 | Engine | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 4532.2 | 2026-04-10 | -532.2 | WA | McPhee Creek
RD6606 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 25 | 2025-09-25 | 4532.2 | 2025-05-13 | -4257.2 | WA | McPhee Creek
RD6606 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2026-02-01 | 4532.2 | 2027-07-01 | 4467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N1310 | Radiator | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2026-02-01 | 4532.2 | 2027-07-01 | 4467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N2000 | Transmission | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2026-02-01 | 4532.2 | 2034-02-07 | 31467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2026-02-01 | 4532.2 | 2032-08-20 | 25467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2026-02-01 | 4532.2 | 2032-08-20 | 25467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2026-02-01 | 4532.2 | 2032-08-20 | 25467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2026-02-01 | 4532.2 | 2028-12-18 | 10467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2026-02-01 | 4532.2 | 2029-03-18 | 11467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2026-02-01 | 4532.2 | 2029-03-18 | 11467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2026-02-01 | 4532.2 | 2028-03-25 | 7467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2026-02-01 | 4532.2 | 2028-03-25 | 7467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2026-02-01 | 4532.2 | 2028-03-25 | 7467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7602 | Relief Valve |  |  | 2026-02-01 | 4532.2 | 2030-01-31 |  | WA | McPhee Creek
RD6606 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2026-02-01 | 4532.2 | 2028-03-25 | 7467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2026-02-01 | 4532.2 | 2028-03-25 | 7467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2026-02-01 | 4532.2 | 2028-03-25 | 7467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2026-02-01 | 4532.2 | 2029-09-13 | 13467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2026-02-01 | 4532.2 | 2028-09-20 | 9467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2026-02-01 | 4532.2 | 2028-09-20 | 9467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2026-02-01 | 4532.2 | 2030-03-10 | 15467.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 3970 | 2026-04-17 | 4532.2 | 2027-01-01 | 2437.8 | WA | McPhee Creek
RD6606 | Cat 789D | N8995 | Operator Seat | 12000 | 1077.5 | 2024-02-03 | 4532.2 | 2028-06-30 | 8545.3 | WA | McPhee Creek
RD6606 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2026-02-01 | 4532.2 | 2027-02-01 |  | WA | McPhee Creek
RD6607 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-02-10 | 1690.45 | 2030-02-09 |  | WA | McPhee Creek
RD6607 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N1000 | Engine | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 1690.45 | 2026-12-20 | 2309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 65 | 2026-02-09 | 1690.45 | 2026-01-25 | -1375.45 | WA | McPhee Creek
RD6607 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-02-10 | 1690.45 | 2028-03-11 | 7309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-02-10 | 1690.45 | 2028-03-11 | 7309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-02-10 | 1690.45 | 2034-10-19 | 34309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-02-10 | 1690.45 | 2033-05-01 | 28309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-02-10 | 1690.45 | 2033-05-01 | 28309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-02-10 | 1690.45 | 2033-05-01 | 28309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-02-10 | 1690.45 | 2029-08-29 | 13309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-02-10 | 1690.45 | 2029-11-27 | 14309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-02-10 | 1690.45 | 2029-11-27 | 14309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7602 | Relief Valve |  |  | 2025-02-10 | 1690.45 | 2029-02-09 |  | WA | McPhee Creek
RD6607 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-02-10 | 1690.45 | 2030-05-25 | 16309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-02-10 | 1690.45 | 2029-06-01 | 12309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-02-10 | 1690.45 | 2029-06-01 | 12309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-02-10 | 1690.45 | 2030-11-19 | 18309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 1291 | 2026-04-17 | 1690.45 | 2027-01-15 | 2600.55 | WA | McPhee Creek
RD6607 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-02-10 | 1690.45 | 2028-12-04 | 10309.55 | WA | McPhee Creek
RD6607 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-02-10 | 1690.45 | 2026-02-10 |  | WA | McPhee Creek
RD6608 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-21 | 3150.15 | 2030-01-20 |  | WA | McPhee Creek
RD6608 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 3150.15 | 2026-08-12 | 849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 109.93 | 2025-06-07 | 3150.15 | 2025-09-21 | -2790.22 | WA | McPhee Creek
RD6608 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-21 | 3150.15 | 2027-11-02 | 5849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-21 | 3150.15 | 2027-11-02 | 5849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-21 | 3150.15 | 2034-06-11 | 32849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-21 | 3150.15 | 2032-12-21 | 26849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-21 | 3150.15 | 2032-12-21 | 26849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-21 | 3150.15 | 2032-12-21 | 26849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-21 | 3150.15 | 2029-04-21 | 11849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-21 | 3150.15 | 2029-07-19 | 12849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-21 | 3150.15 | 2029-07-19 | 12849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-21 | 3150.15 | 2029-01-20 |  | WA | McPhee Creek
RD6608 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-21 | 3150.15 | 2030-01-14 | 14849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-21 | 3150.15 | 2029-01-22 | 10849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-21 | 3150.15 | 2029-01-22 | 10849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-21 | 3150.15 | 2030-07-12 | 16849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 2630 | 2026-04-17 | 3150.15 | 2027-01-05 | 2479.85 | WA | McPhee Creek
RD6608 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-21 | 3150.15 | 2028-07-27 | 8849.85 | WA | McPhee Creek
RD6608 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-21 | 3150.15 | 2026-01-21 |  | WA | McPhee Creek
RD6609 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-21 | 3871 | 2030-01-20 |  | WA | McPhee Creek
RD6609 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 3871 | 2026-06-09 | 129 | WA | McPhee Creek
RD6609 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 61 | 2025-06-11 | 3871 | 2025-07-14 | -3560 | WA | McPhee Creek
RD6609 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-21 | 3871 | 2027-08-29 | 5129 | WA | McPhee Creek
RD6609 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-21 | 3871 | 2027-08-29 | 5129 | WA | McPhee Creek
RD6609 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-21 | 3871 | 2034-04-07 | 32129 | WA | McPhee Creek
RD6609 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-21 | 3871 | 2032-10-18 | 26129 | WA | McPhee Creek
RD6609 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-21 | 3871 | 2032-10-18 | 26129 | WA | McPhee Creek
RD6609 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-21 | 3871 | 2032-10-18 | 26129 | WA | McPhee Creek
RD6609 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-21 | 3871 | 2029-02-16 | 11129 | WA | McPhee Creek
RD6609 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-21 | 3871 | 2029-05-16 | 12129 | WA | McPhee Creek
RD6609 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-21 | 3871 | 2029-05-16 | 12129 | WA | McPhee Creek
RD6609 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-21 | 3871 | 2029-01-20 |  | WA | McPhee Creek
RD6609 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-21 | 3871 | 2029-11-11 | 14129 | WA | McPhee Creek
RD6609 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-21 | 3871 | 2028-11-18 | 10129 | WA | McPhee Creek
RD6609 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-21 | 3871 | 2028-11-18 | 10129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-21 | 3871 | 2030-05-08 | 16129 | WA | McPhee Creek
RD6609 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 3387 | 2026-04-17 | 3871 | 2027-01-08 | 2516 | WA | McPhee Creek
RD6609 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-21 | 3871 | 2028-05-23 | 8129 | WA | McPhee Creek
RD6609 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-21 | 3871 | 2026-01-21 |  | WA | McPhee Creek
RD6610 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-19 | 3606.6 | 2030-01-18 |  | WA | McPhee Creek
RD6610 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 3606.6 | 2026-07-02 | 393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 15.24 | 2025-03-10 | 3606.6 | 2025-08-02 | -3341.36 | WA | McPhee Creek
RD6610 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-19 | 3606.6 | 2027-09-22 | 5393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-19 | 3606.6 | 2027-09-22 | 5393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-19 | 3606.6 | 2034-05-01 | 32393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-19 | 3606.6 | 2032-11-11 | 26393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-19 | 3606.6 | 2032-11-11 | 26393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-19 | 3606.6 | 2032-11-11 | 26393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-19 | 3606.6 | 2029-03-11 | 11393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-19 | 3606.6 | 2029-06-09 | 12393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-19 | 3606.6 | 2029-06-09 | 12393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-19 | 3606.6 | 2029-01-18 |  | WA | McPhee Creek
RD6610 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-19 | 3606.6 | 2029-12-04 | 14393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-19 | 3606.6 | 2028-12-12 | 10393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-19 | 3606.6 | 2028-12-12 | 10393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-19 | 3606.6 | 2030-06-01 | 16393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 3067 | 2026-04-17 | 3606.6 | 2027-01-03 | 2460.4 | WA | McPhee Creek
RD6610 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-19 | 3606.6 | 2028-06-16 | 8393.4 | WA | McPhee Creek
RD6610 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-19 | 3606.6 | 2026-01-19 |  | WA | McPhee Creek
RD6611 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-20 | 3329.2 | 2030-01-19 |  | WA | McPhee Creek
RD6611 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 3329.2 | 2026-07-27 | 670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 22.29 | 2025-06-27 | 3329.2 | 2025-08-28 | -3056.91 | WA | McPhee Creek
RD6611 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-20 | 3329.2 | 2027-10-17 | 5670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-20 | 3329.2 | 2027-10-17 | 5670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-20 | 3329.2 | 2034-05-26 | 32670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-20 | 3329.2 | 2032-12-05 | 26670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-20 | 3329.2 | 2032-12-05 | 26670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-20 | 3329.2 | 2032-12-05 | 26670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-20 | 3329.2 | 2029-04-05 | 11670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-20 | 3329.2 | 2029-07-03 | 12670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-20 | 3329.2 | 2029-07-03 | 12670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-20 | 3329.2 | 2029-01-19 |  | WA | McPhee Creek
RD6611 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-20 | 3329.2 | 2029-12-29 | 14670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-20 | 3329.2 | 2029-01-06 | 10670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-20 | 3329.2 | 2029-01-06 | 10670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-20 | 3329.2 | 2030-06-26 | 16670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 3140 | 2026-04-17 | 3329.2 | 2027-02-03 | 2810.8 | WA | McPhee Creek
RD6611 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-20 | 3329.2 | 2028-07-11 | 8670.8 | WA | McPhee Creek
RD6611 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-20 | 3329.2 | 2026-01-20 |  | WA | McPhee Creek
RD6612 | Cat 789D | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-20 | 3903.15 | 2030-01-19 |  | WA | McPhee Creek
RD6612 | Cat 789D | N0200 | A Frame Bearing | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N1000 | Engine | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N1002 | Engine Valve Adj | 4000 |  | 2024-05-21 | 3903.15 | 2026-06-06 | 96.85 | WA | McPhee Creek
RD6612 | Cat 789D | N1002-01 | Engine Valve Adj - Initial | 250 | 89.28 | 2025-06-10 | 3903.15 | 2025-07-14 | -3563.87 | WA | McPhee Creek
RD6612 | Cat 789D | N1004 | Engine Midlife | 9000 |  | 2025-01-20 | 3903.15 | 2027-08-26 | 5096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N1310 | Radiator | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N1320 | Cooling Fan Engine | 9000 |  | 2025-01-20 | 3903.15 | 2027-08-26 | 5096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N2000 | Transmission | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N2004 | Transmission Pump | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N2050 | Torque Convertor | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N3020 | Drive Shaft Eng - Pump Drive | 36000 |  | 2025-01-20 | 3903.15 | 2034-04-04 | 32096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N3028 | Drive Shaft T/C - Trans | 30000 |  | 2025-01-20 | 3903.15 | 2032-10-15 | 26096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N3029 | Uni's T/C - Trans | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N3321 | Pump Drive | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N4000 | Bevel Gear | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N4100-L | Rear Axle LEFT | 30000 |  | 2025-01-20 | 3903.15 | 2032-10-15 | 26096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N4100-R | Rear Axle RIGHT | 30000 |  | 2025-01-20 | 3903.15 | 2032-10-15 | 26096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-20 | 3903.15 | 2029-02-13 | 11096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N6030-RE | Brake Slack Adj REAR | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N6060-F | Oil Cooler - Brakes FRONT | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N6200-F | Press Converter FRONT | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N6200-LR | Press Converter LEFT REAR | 16000 |  | 2025-01-20 | 3903.15 | 2029-05-13 | 12096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N6200-RR | Press Converter RIGHT REAR | 16000 |  | 2025-01-20 | 3903.15 | 2029-05-13 | 12096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7064 | Pump Hoist | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7120 | Pump Steering | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7474-L | Hyd Cyl Hoist LEFT | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7474-R | Hyd Cyl Hoist RIGHT | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7542-L | Hyd Cyl Steer LEFT | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7542-R | Hyd Cyl Steer RIGHT | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7602 | Relief Valve |  |  | 2025-01-20 | 3903.15 | 2029-01-19 |  | WA | McPhee Creek
RD6612 | Cat 789D | N7657-C | Hyd Accum Steering CENTER | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7657-F | Hyd Accum Steering FRONT | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N7657-RE | Hyd Accum Steering REAR | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8200-01 | Ride Strut POS 1 | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8200-02 | Ride Strut POS 2 | 18000 |  | 2025-01-20 | 3903.15 | 2029-11-08 | 14096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8200-03 | Ride Strut POS 3 | 14000 |  | 2025-01-20 | 3903.15 | 2028-11-15 | 10096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8200-04 | Ride Strut POS 4 | 14000 |  | 2025-01-20 | 3903.15 | 2028-11-15 | 10096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-20 | 3903.15 | 2030-05-06 | 16096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8501 | Ball Stud Crack Test | 3000 | 3503 | 2026-04-17 | 3903.15 | 2027-01-15 | 2599.85 | WA | McPhee Creek
RD6612 | Cat 789D | N8995 | Operator Seat | 12000 |  | 2025-01-20 | 3903.15 | 2028-05-21 | 8096.85 | WA | McPhee Creek
RD6612 | Cat 789D | N9500 | Air Cond'r-Serv |  |  | 2025-01-20 | 3903.15 | 2026-01-20 |  | WA | McPhee Creek
RD6621 | Cat 777 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 1431.1 | 2030-01-07 |  | WA | McPhee Creek
RD6621 | Cat 777 | N1000 | Engine | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N1002 | Engine Valve Adj | 3000 |  |  | 1431.1 | 2027-06-29 | 1568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N1002-01 | Engine Valve Adj - Initial | 500 | 257.81 | 2025-06-06 | 1431.1 | 2025-12-09 | -673.29 | WA | McPhee Creek
RD6621 | Cat 777 | N1004 | Engine Midlife | 10000 |  | 2025-01-08 | 1431.1 | 2032-05-05 | 8568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N1310 | Radiator | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N1490 | Cam Shaft Inspection | 1500 |  | 2025-01-08 | 1431.1 | 2026-06-14 | 68.9 | WA | McPhee Creek
RD6621 | Cat 777 | N2000 | Transmission | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N2050 | Torque Convertor | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N3029 | Uni's T/C - Trans | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N4000 | Bevel Gear | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-08 | 1431.1 | 2035-10-23 | 13568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-08 | 1431.1 | 2035-10-23 | 13568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N6060-F | Oil Cooler - Brakes FRONT | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N6060-RE | Oil Cooler - Brakes REAR | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7064 | Pump Hoist | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7120 | Pump Steering | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7122 | Pump Emerg/Sup Steering | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7474-L | Hyd Cyl Hoist LEFT | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7474-R | Hyd Cyl Hoist RIGHT | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7542-L | Hyd Cyl Steer LEFT | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7542-R | Hyd Cyl Steer RIGHT | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7602 | Relief Valve |  |  | 2025-01-08 | 1431.1 | 2029-01-07 |  | WA | McPhee Creek
RD6621 | Cat 777 | N7605 | Steering Hmu | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7653 | Hyd Accum Park Brake | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N7654 | Hyd Accum Service Brake | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-08 | 1431.1 | 2037-11-21 | 16568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8140 | Steering Y Piece | 12000 |  | 2025-01-08 | 1431.1 | 2033-09-24 | 10568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8155-L | Steering Control Arm LEFT | 12000 |  | 2025-01-08 | 1431.1 | 2033-09-24 | 10568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8155-R | Steering Control Arm RIGHT | 12000 |  | 2025-01-08 | 1431.1 | 2033-09-24 | 10568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8200-01 | Ride Strut POS 1 | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8200-02 | Ride Strut POS 2 | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8200-03 | Ride Strut POS 3 | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8200-04 | Ride Strut POS 4 | 9000 |  | 2025-01-08 | 1431.1 | 2031-08-26 | 7568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-08 | 1431.1 | 2039-04-11 | 18568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8501 | Ball Stud Crack Test | 3000 | 1163 | 2026-04-17 | 1431.1 | 2028-04-19 | 2731.9 | WA | McPhee Creek
RD6621 | Cat 777 | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 1431.1 | 2033-09-24 | 10568.9 | WA | McPhee Creek
RD6621 | Cat 777 | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 1431.1 | 2026-01-08 |  | WA | McPhee Creek
RD6622 | Cat 777 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 1608.3 | 2030-01-07 |  | WA | McPhee Creek
RD6622 | Cat 777 | N1000 | Engine | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N1002 | Engine Valve Adj | 3000 |  | 2024-05-21 | 1608.3 | 2026-11-18 | 1391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N1002-01 | Engine Valve Adj - Initial | 500 | 19.09 | 2025-03-02 | 1608.3 | 2026-01-12 | -1089.21 | WA | McPhee Creek
RD6622 | Cat 777 | N1004 | Engine Midlife | 10000 |  | 2025-01-08 | 1608.3 | 2029-04-11 | 8391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N1310 | Radiator | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N1490 | Cam Shaft Inspection | 1500 |  | 2025-01-08 | 1608.3 | 2026-05-14 | -108.3 | WA | McPhee Creek
RD6622 | Cat 777 | N2000 | Transmission | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N2050 | Torque Convertor | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N3029 | Uni's T/C - Trans | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N4000 | Bevel Gear | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-08 | 1608.3 | 2030-12-27 | 13391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-08 | 1608.3 | 2030-12-27 | 13391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N6060-F | Oil Cooler - Brakes FRONT | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N6060-RE | Oil Cooler - Brakes REAR | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7064 | Pump Hoist | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7120 | Pump Steering | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7122 | Pump Emerg/Sup Steering | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7474-L | Hyd Cyl Hoist LEFT | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7474-R | Hyd Cyl Hoist RIGHT | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7542-L | Hyd Cyl Steer LEFT | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7542-R | Hyd Cyl Steer RIGHT | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7602 | Relief Valve |  |  | 2025-01-08 | 1608.3 | 2029-01-07 |  | WA | McPhee Creek
RD6622 | Cat 777 | N7605 | Steering Hmu | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7653 | Hyd Accum Park Brake | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N7654 | Hyd Accum Service Brake | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-08 | 1608.3 | 2032-01-06 | 16391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8140 | Steering Y Piece | 12000 |  | 2025-01-08 | 1608.3 | 2029-12-17 | 10391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8155-L | Steering Control Arm LEFT | 12000 |  | 2025-01-08 | 1608.3 | 2029-12-17 | 10391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8155-R | Steering Control Arm RIGHT | 12000 |  | 2025-01-08 | 1608.3 | 2029-12-17 | 10391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8200-01 | Ride Strut POS 1 | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8200-02 | Ride Strut POS 2 | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8200-03 | Ride Strut POS 3 | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8200-04 | Ride Strut POS 4 | 9000 |  | 2025-01-08 | 1608.3 | 2028-12-07 | 7391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-08 | 1608.3 | 2032-09-12 | 18391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8501 | Ball Stud Crack Test | 3000 | 1295 | 2026-04-17 | 1608.3 | 2027-04-29 | 2686.7 | WA | McPhee Creek
RD6622 | Cat 777 | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 1608.3 | 2029-12-17 | 10391.7 | WA | McPhee Creek
RD6622 | Cat 777 | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 1608.3 | 2026-01-08 |  | WA | McPhee Creek
RD6623 | Cat 777 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 1958.65 | 2030-01-07 |  | WA | McPhee Creek
RD6623 | Cat 777 | N1000 | Engine | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N1002 | Engine Valve Adj | 3000 |  | 2024-05-21 | 1958.65 | 2026-10-05 | 1041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N1002-01 | Engine Valve Adj - Initial | 500 | 379.07 | 2025-06-04 | 1958.65 | 2026-01-13 | -1079.58 | WA | McPhee Creek
RD6623 | Cat 777 | N1004 | Engine Midlife | 10000 |  | 2025-01-08 | 1958.65 | 2029-02-26 | 8041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N1310 | Radiator | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N1490 | Cam Shaft Inspection | 1500 |  | 2025-01-08 | 1958.65 | 2026-04-01 | -458.65 | WA | McPhee Creek
RD6623 | Cat 777 | N2000 | Transmission | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N2050 | Torque Convertor | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N3029 | Uni's T/C - Trans | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N4000 | Bevel Gear | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-08 | 1958.65 | 2030-11-13 | 13041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-08 | 1958.65 | 2030-11-13 | 13041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N6060-F | Oil Cooler - Brakes FRONT | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N6060-RE | Oil Cooler - Brakes REAR | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7064 | Pump Hoist | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7120 | Pump Steering | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7122 | Pump Emerg/Sup Steering | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7474-L | Hyd Cyl Hoist LEFT | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7474-R | Hyd Cyl Hoist RIGHT | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7542-L | Hyd Cyl Steer LEFT | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7542-R | Hyd Cyl Steer RIGHT | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7602 | Relief Valve |  |  | 2025-01-08 | 1958.65 | 2029-01-07 |  | WA | McPhee Creek
RD6623 | Cat 777 | N7605 | Steering Hmu | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7653 | Hyd Accum Park Brake | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N7654 | Hyd Accum Service Brake | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-08 | 1958.65 | 2031-11-23 | 16041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8140 | Steering Y Piece | 12000 |  | 2025-01-08 | 1958.65 | 2029-11-03 | 10041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8155-L | Steering Control Arm LEFT | 12000 |  | 2025-01-08 | 1958.65 | 2029-11-03 | 10041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8155-R | Steering Control Arm RIGHT | 12000 |  | 2025-01-08 | 1958.65 | 2029-11-03 | 10041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8200-01 | Ride Strut POS 1 | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8200-02 | Ride Strut POS 2 | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8200-03 | Ride Strut POS 3 | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8200-04 | Ride Strut POS 4 | 9000 |  | 2025-01-08 | 1958.65 | 2028-10-24 | 7041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-08 | 1958.65 | 2032-07-30 | 18041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8501 | Ball Stud Crack Test | 3000 | 1700 | 2026-04-17 | 1958.65 | 2027-05-06 | 2741.35 | WA | McPhee Creek
RD6623 | Cat 777 | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 1958.65 | 2029-11-03 | 10041.35 | WA | McPhee Creek
RD6623 | Cat 777 | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 1958.65 | 2026-01-08 |  | WA | McPhee Creek
RD6624 | Cat 777 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 1889.7 | 2030-01-07 |  | WA | McPhee Creek
RD6624 | Cat 777 | N1000 | Engine | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N1002 | Engine Valve Adj | 3000 |  | 2024-05-21 | 1889.7 | 2026-10-14 | 1110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N1002-01 | Engine Valve Adj - Initial | 500 | 302 | 2025-06-06 | 1889.7 | 2026-01-12 | -1087.7 | WA | McPhee Creek
RD6624 | Cat 777 | N1004 | Engine Midlife | 10000 |  | 2025-01-08 | 1889.7 | 2029-03-07 | 8110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N1310 | Radiator | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N1490 | Cam Shaft Inspection | 1500 |  | 2025-01-08 | 1889.7 | 2026-04-09 | -389.7 | WA | McPhee Creek
RD6624 | Cat 777 | N2000 | Transmission | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N2050 | Torque Convertor | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N3029 | Uni's T/C - Trans | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N4000 | Bevel Gear | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-08 | 1889.7 | 2030-11-22 | 13110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-08 | 1889.7 | 2030-11-22 | 13110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N6060-F | Oil Cooler - Brakes FRONT | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N6060-RE | Oil Cooler - Brakes REAR | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7064 | Pump Hoist | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7120 | Pump Steering | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7122 | Pump Emerg/Sup Steering | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7474-L | Hyd Cyl Hoist LEFT | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7474-R | Hyd Cyl Hoist RIGHT | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7542-L | Hyd Cyl Steer LEFT | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7542-R | Hyd Cyl Steer RIGHT | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7602 | Relief Valve |  |  | 2025-01-08 | 1889.7 | 2029-01-07 |  | WA | McPhee Creek
RD6624 | Cat 777 | N7605 | Steering Hmu | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7653 | Hyd Accum Park Brake | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N7654 | Hyd Accum Service Brake | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-08 | 1889.7 | 2031-12-02 | 16110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8140 | Steering Y Piece | 12000 |  | 2025-01-08 | 1889.7 | 2029-11-12 | 10110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8155-L | Steering Control Arm LEFT | 12000 |  | 2025-01-08 | 1889.7 | 2029-11-12 | 10110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8155-R | Steering Control Arm RIGHT | 12000 |  | 2025-01-08 | 1889.7 | 2029-11-12 | 10110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8200-01 | Ride Strut POS 1 | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8200-02 | Ride Strut POS 2 | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8200-03 | Ride Strut POS 3 | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8200-04 | Ride Strut POS 4 | 9000 |  | 2025-01-08 | 1889.7 | 2028-11-02 | 7110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-08 | 1889.7 | 2032-08-08 | 18110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8501 | Ball Stud Crack Test | 3000 | 1606 | 2026-04-17 | 1889.7 | 2027-05-03 | 2716.3 | WA | McPhee Creek
RD6624 | Cat 777 | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 1889.7 | 2029-11-12 | 10110.3 | WA | McPhee Creek
RD6624 | Cat 777 | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 1889.7 | 2026-01-08 |  | WA | McPhee Creek
RD6650 | Cat 777 | N0066 | Fire Suppression Sys Cylinder |  |  | 2025-01-08 | 2531.3 | 2030-01-07 |  | WA | McPhee Creek
RD6650 | Cat 777 | N1000 | Engine | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N1002 | Engine Valve Adj | 3000 |  |  | 2531.3 | 2026-07-22 | 468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N1002-01 | Engine Valve Adj - Initial | 500 | 586 | 2025-11-21 | 2531.3 | 2025-12-10 | -1445.3 | WA | McPhee Creek
RD6650 | Cat 777 | N1004 | Engine Midlife | 10000 |  | 2025-01-08 | 2531.3 | 2028-10-18 | 7468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N1310 | Radiator | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N1490 | Cam Shaft Inspection | 1500 |  | 2025-01-08 | 2531.3 | 2026-01-27 | -1031.3 | WA | McPhee Creek
RD6650 | Cat 777 | N2000 | Transmission | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N2002 | Oil Cooler - Transmission | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N2050 | Torque Convertor | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N3029 | Uni's T/C - Trans | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N4000 | Bevel Gear | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N5000-03 | Final Drive POS 3 | 15000 |  | 2025-01-08 | 2531.3 | 2030-05-25 | 12468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N5000-04 | Final Drive POS 4 | 15000 |  | 2025-01-08 | 2531.3 | 2030-05-25 | 12468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N6060-F | Oil Cooler - Brakes FRONT | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N6060-RE | Oil Cooler - Brakes REAR | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7064 | Pump Hoist | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7120 | Pump Steering | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7122 | Pump Emerg/Sup Steering | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7474-L | Hyd Cyl Hoist LEFT | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7474-R | Hyd Cyl Hoist RIGHT | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7542-L | Hyd Cyl Steer LEFT | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7542-R | Hyd Cyl Steer RIGHT | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7602 | Relief Valve |  |  | 2025-01-08 | 2531.3 | 2029-01-07 |  | WA | McPhee Creek
RD6650 | Cat 777 | N7605 | Steering Hmu | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7653 | Hyd Accum Park Brake | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N7654 | Hyd Accum Service Brake | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8122-01 | Wheel Group POS 1 | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8122-02 | Wheel Group POS 2 | 18000 |  | 2025-01-08 | 2531.3 | 2031-05-11 | 15468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8140 | Steering Y Piece | 12000 |  | 2025-01-08 | 2531.3 | 2029-06-08 | 9468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8155-L | Steering Control Arm LEFT | 12000 |  | 2025-01-08 | 2531.3 | 2029-06-08 | 9468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8155-R | Steering Control Arm RIGHT | 12000 |  | 2025-01-08 | 2531.3 | 2029-06-08 | 9468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8200-01 | Ride Strut POS 1 | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8200-02 | Ride Strut POS 2 | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8200-03 | Ride Strut POS 3 | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8200-04 | Ride Strut POS 4 | 9000 |  | 2025-01-08 | 2531.3 | 2028-06-23 | 6468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2025-01-08 | 2531.3 | 2031-12-31 | 17468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8501 | Ball Stud Crack Test | 3000 | 2055 | 2026-04-17 | 2531.3 | 2027-03-19 | 2523.7 | WA | McPhee Creek
RD6650 | Cat 777 | N8995 | Operator Seat | 12000 |  | 2025-01-08 | 2531.3 | 2029-06-08 | 9468.7 | WA | McPhee Creek
RD6650 | Cat 777 | N9500 | Air Cond'r-Serv |  |  | 2025-01-08 | 2531.3 | 2026-01-08 |  | WA | McPhee Creek
RD6651 | Cat 777 | N0066 | Fire Suppression Sys Cylinder |  |  | 2024-05-21 | 2803.3 | 2029-05-20 |  | WA | McPhee Creek
RD6651 | Cat 777 | N1000 | Engine | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N1002 | Engine Valve Adj | 3000 |  | 2024-05-21 | 2803.3 | 2026-06-20 | 196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N1002-01 | Engine Valve Adj - Initial | 500 | 427 | 2025-11-20 | 2803.3 | 2025-10-21 | -1876.3 | WA | McPhee Creek
RD6651 | Cat 777 | N1004 | Engine Midlife | 10000 |  | 2024-05-21 | 2803.3 | 2028-09-16 | 7196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N1310 | Radiator | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N1490 | Cam Shaft Inspection | 1500 |  | 2024-05-21 | 2803.3 | 2025-12-27 | -1303.3 | WA | McPhee Creek
RD6651 | Cat 777 | N2000 | Transmission | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N2002 | Oil Cooler - Transmission | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N2025 | Pump Trans / T/C / Brk Cooling | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N2050 | Torque Convertor | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N3028 | Drive Shaft T/C - Trans | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N3029 | Uni's T/C - Trans | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N4000 | Bevel Gear | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N5000-03 | Final Drive POS 3 | 15000 |  | 2024-05-21 | 2803.3 | 2030-04-24 | 12196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N5000-04 | Final Drive POS 4 | 15000 |  | 2024-05-21 | 2803.3 | 2030-04-24 | 12196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N6030-F | Brake Slack Adj FRONT | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N6030-LR | Brake Slack Adj LFT REAR | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N6030-RR | Brake Slack Adj RHT REAR | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N6060-F | Oil Cooler - Brakes FRONT | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N6060-RE | Oil Cooler - Brakes REAR | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7064 | Pump Hoist | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7120 | Pump Steering | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7122 | Pump Emerg/Sup Steering | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7474-L | Hyd Cyl Hoist LEFT | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7474-R | Hyd Cyl Hoist RIGHT | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7542-L | Hyd Cyl Steer LEFT | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7542-R | Hyd Cyl Steer RIGHT | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7602 | Relief Valve |  |  | 2024-05-21 | 2803.3 | 2028-05-20 |  | WA | McPhee Creek
RD6651 | Cat 777 | N7605 | Steering Hmu | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7653 | Hyd Accum Park Brake | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N7654 | Hyd Accum Service Brake | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8122-01 | Wheel Group POS 1 | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8122-02 | Wheel Group POS 2 | 18000 |  | 2024-05-21 | 2803.3 | 2031-04-09 | 15196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8140 | Steering Y Piece | 12000 |  | 2024-05-21 | 2803.3 | 2029-05-08 | 9196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8155-L | Steering Control Arm LEFT | 12000 |  | 2024-05-21 | 2803.3 | 2029-05-08 | 9196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8155-R | Steering Control Arm RIGHT | 12000 |  | 2024-05-21 | 2803.3 | 2029-05-08 | 9196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8200-01 | Ride Strut POS 1 | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8200-02 | Ride Strut POS 2 | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8200-03 | Ride Strut POS 3 | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8200-04 | Ride Strut POS 4 | 9000 |  | 2024-05-21 | 2803.3 | 2028-05-22 | 6196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-01 | Steering Ball Studs POS 1 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-02 | Steering Ball Studs POS 2 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-03 | Steering Ball Studs POS 3 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-04 | Steering Ball Studs POS 4 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-05 | Steering Ball Studs POS 5 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-06 | Steering Ball Studs POS 6 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-07 | Steering Ball Studs POS 7 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8442-08 | Steering Ball Studs POS 8 | 20000 |  | 2024-05-21 | 2803.3 | 2031-11-29 | 17196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8501 | Ball Stud Crack Test | 3000 | 2277 | 2026-04-17 | 2803.3 | 2027-03-13 | 2473.7 | WA | McPhee Creek
RD6651 | Cat 777 | N8995 | Operator Seat | 12000 |  | 2024-05-21 | 2803.3 | 2029-05-08 | 9196.7 | WA | McPhee Creek
RD6651 | Cat 777 | N9500 | Air Cond'r-Serv |  |  | 2024-05-21 | 2803.3 | 2025-05-21 |  | WA | McPhee Creek
TC8137 | Cat D10T | N0066 | Fire Suppression Sys Cylinder |  | 43655.5 | 2025-04-22 | 46895 | 2030-04-21 |  | WA | Mt Holland
TC8137 | Cat D10T | N0101-L | Track Chain LEFT | 6000 | 44668 | 2025-07-03 | 46895 | 2027-03-03 | 3773 | WA | Mt Holland
TC8137 | Cat D10T | N0101-R | Track Chain RIGHT | 6000 | 44668 | 2025-07-03 | 46895 | 2027-03-03 | 3773 | WA | Mt Holland
TC8137 | Cat D10T | N0102-L | Trk Chn Pin & Bush Trn LEFT | 3000 | 44668 | 2025-07-03 | 46895 | 2026-07-24 | 773 | WA | Mt Holland
TC8137 | Cat D10T | N0102-R | Trk Chn Pin & Bush Trn RIGHT | 3000 | 44668 | 2025-07-03 | 46895 | 2026-07-24 | 773 | WA | Mt Holland
TC8137 | Cat D10T | N0103-L | Track Plates LEFT | 1500 | 44668 | 2025-07-03 | 46895 | 2026-04-04 | -727 | WA | Mt Holland
TC8137 | Cat D10T | N0103-R | Track Plates RIGHT | 1500 | 44668 | 2025-07-03 | 46895 | 2026-04-04 | -727 | WA | Mt Holland
TC8137 | Cat D10T | N0104-L | Sprockets LEFT | 6000 | 37165 | 2023-09-23 | 46895 | 2025-08-25 | -3730 | WA | Mt Holland
TC8137 | Cat D10T | N0104-R | Sprockets RIGHT | 6000 | 40981 | 2024-09-23 | 46895 | 2026-06-03 | 86 | WA | Mt Holland
TC8137 | Cat D10T | N0105-LF | Idler LFT FRONT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0105-LR | Idler LFT REAR | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0105-RF | Idler RHT FRONT | 9000 | 45562 | 2025-09-08 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0105-RR | Idler RHT REAR | 9000 | 45562 | 2025-09-08 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-1L | Track Roller 1 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-1R | Track Roller 1 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-2L | Track Roller 2 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-2R | Track Roller 2 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-3L | Track Roller 3 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-3R | Track Roller 3 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-4L | Track Roller 4 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-4R | Track Roller 4 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-5L | Track Roller 5 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-5R | Track Roller 5 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-6L | Track Roller 6 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-6R | Track Roller 6 RIGHT | 9000 | 45562 | 2025-09-07 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-7L | Track Roller 7 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-7R | Track Roller 7 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0111-8L | Track Roller 8 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0111-8R | Track Roller 8 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0121-L | Carrier Roller No 1 LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0121-R | Carrier Roller No 1 RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0130-L | Track Frame LEFT | 18000 | 44960 | 2025-07-23 | 46895 | 2029-08-30 | 16065 | WA | Mt Holland
TC8137 | Cat D10T | N0130-R | Track Frame RIGHT | 18000 | 45562 | 2025-09-05 | 46895 | 2029-10-14 | 16667 | WA | Mt Holland
TC8137 | Cat D10T | N0134-L | Track Adjuster LEFT | 18000 | 44960 | 2025-07-23 | 46895 | 2029-08-30 | 16065 | WA | Mt Holland
TC8137 | Cat D10T | N0134-R | Track Adjuster RIGHT | 18000 | 45562 | 2025-09-05 | 46895 | 2029-10-14 | 16667 | WA | Mt Holland
TC8137 | Cat D10T | N0139-L | Track Frame Mid Life LEFT | 9000 | 44960 | 2025-07-23 | 46895 | 2027-11-02 | 7065 | WA | Mt Holland
TC8137 | Cat D10T | N0139-R | Track Frame Mid Life RIGHT | 9000 | 45562 | 2025-09-05 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0140 | Equalizer Bar | 9000 | 45562 | 2025-09-07 | 46895 | 2027-12-17 | 7667 | WA | Mt Holland
TC8137 | Cat D10T | N0145 | Pivot Shaft Brgs | 18000 | 24113 | 2019-03-12 | 46895 | 2025-06-08 | -4782 | WA | Mt Holland
TC8137 | Cat D10T | N0520 | Pre Lube Pump | 15000 | 43401 | 2025-03-31 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N1000 | Engine | 15000 | 43401 | 2025-04-02 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N1002 | Engine Valve Adj | 4000 | 43401 | 2025-04-02 | 46895 | 2026-07-04 | 506 | WA | Mt Holland
TC8137 | Cat D10T | N1002-01 | Engine Valve Adj - Initial | 500 | 43825 | 2025-05-06 | 46895 | 2025-11-19 | -2570 | WA | Mt Holland
TC8137 | Cat D10T | N1004 | Engine Midlife | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N1100-L | Turbo Primary LEFT | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N1100-R | Turbo Primary RIGHT | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N1202 | Fuel Transfer Pump | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N1300 | Cooling Sys Service | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N1310 | Radiator | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N1312-L | Aftercooler Core - LEFT | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N1312-R | Aftercooler Core - RIGHT | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N2000 | Transmission | 15000 | 35684 | 2023-05-20 | 46895 | 2027-03-05 | 3789 | WA | Mt Holland
TC8137 | Cat D10T | N2020 | Powertrain Pump | 15000 | 45562 | 2025-09-08 | 46895 | 2029-03-05 | 13667 | WA | Mt Holland
TC8137 | Cat D10T | N2050 | Torque Convertor | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N2450 | Drv Cpling Fan Pump-Trans Pump | 7500 | 43401 | 2025-03-31 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N3016 | Drv Shaft Fan Pump-Trans Pump | 15000 | 43401 | 2025-03-31 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N3028 | Drive Shaft T/C - Trans | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N3029 | Uni's T/C - Trans | 7500 | 43401 | 2025-04-01 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N4000 | Bevel Gear | 15000 | 35684 | 2023-05-20 | 46895 | 2027-03-05 | 3789 | WA | Mt Holland
TC8137 | Cat D10T | N4110-L | Steering Clutch/Brk LEFT | 15000 | 44668 | 2025-07-03 | 46895 | 2028-12-29 | 12773 | WA | Mt Holland
TC8137 | Cat D10T | N4110-R | Steering Clutch/Brk RIGHT | 15000 | 44668 | 2025-07-04 | 46895 | 2028-12-29 | 12773 | WA | Mt Holland
TC8137 | Cat D10T | N5000-L | Final Drive LEFT | 15000 | 34438 | 2023-02-06 | 46895 | 2026-12-02 | 2543 | WA | Mt Holland
TC8137 | Cat D10T | N5000-R | Final Drive RIGHT | 15000 | 44668 | 2025-07-02 | 46895 | 2028-12-29 | 12773 | WA | Mt Holland
TC8137 | Cat D10T | N7041 | Pump Cooling Fan Engine | 15000 | 45562 | 2025-09-08 | 46895 | 2029-03-05 | 13667 | WA | Mt Holland
TC8137 | Cat D10T | N7070 | Pump Implement | 15000 | 45562 | 2025-09-08 | 46895 | 2029-03-05 | 13667 | WA | Mt Holland
TC8137 | Cat D10T | N7232 | Hyd Motor Engine Fan | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N7420-L | Hyd Cyl Blade Lift LEFT | 12000 | 40400 | 2024-07-28 | 46895 | 2027-07-10 | 5505 | WA | Mt Holland
TC8137 | Cat D10T | N7420-R | Hyd Cyl Blade Lift RIGHT | 12000 | 40398 | 2024-07-27 | 46895 | 2027-07-10 | 5503 | WA | Mt Holland
TC8137 | Cat D10T | N7421-L | Hyd Cyl Blade Tilt LEFT | 15000 | 28609 | 2020-07-03 | 46895 | 2025-09-27 | -3286 | WA | Mt Holland
TC8137 | Cat D10T | N7421-R | Hyd Cyl Blade Tilt RIGHT | 15000 | 42566 | 2025-01-19 | 46895 | 2028-07-26 | 10671 | WA | Mt Holland
TC8137 | Cat D10T | N7510-L | Hyd Cyl Ripper Lift LEFT | 25000 | 28609 | 2020-07-03 | 46895 | 2027-10-07 | 6714 | WA | Mt Holland
TC8137 | Cat D10T | N7510-R | Hyd Cyl Ripper Lift RIGHT | 25000 | 28609 | 2020-07-03 | 46895 | 2027-10-07 | 6714 | WA | Mt Holland
TC8137 | Cat D10T | N7514-L | Hyd Cyl Ripper Pitch LEFT | 25000 | 28609 | 2020-07-03 | 46895 | 2027-10-07 | 6714 | WA | Mt Holland
TC8137 | Cat D10T | N7514-R | Hyd Cyl Ripper Pitch RIGHT | 25000 | 28609 | 2020-07-03 | 46895 | 2027-10-07 | 6714 | WA | Mt Holland
TC8137 | Cat D10T | N7600 | Control Valve | 30000 | 14200.4 | 2017-02-22 | 46895 | 2025-11-09 | -2694.6 | WA | Mt Holland
TC8137 | Cat D10T | N7610 | Hyd Cooler Core | 15000 | 43401 | 2025-04-01 | 46895 | 2028-09-26 | 11506 | WA | Mt Holland
TC8137 | Cat D10T | N8000 | Main Frame/Chassis | 30000 |  | 2011-03-01 | 46895 | 2022-12-24 | -16895 | WA | Mt Holland
TC8137 | Cat D10T | N8995 | Operator Seat | 6000 | 43583 | 2025-04-16 | 46895 | 2026-12-13 | 2688 | WA | Mt Holland
TC8137 | Cat D10T | N9020 | Alternator | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N9050 | Starter Motor | 7500 | 43401 | 2025-04-02 | 46895 | 2027-03-21 | 4006 | WA | Mt Holland
TC8137 | Cat D10T | N9500 | Air Cond'r-Serv | 5000 | 44668 | 2025-07-02 | 46895 | 2026-12-19 | 2773 | WA | Mt Holland
TC8137 | Cat D10T | N9500-MA | Air Cond'r-Serv - MAJOR | 15000 | 44668 | 2025-07-02 | 46895 | 2028-12-29 | 12773 | WA | Mt Holland
TC8137 | Cat D10T | N9501 | A/C Compressor | 7500 | 41129 | 2024-10-05 | 46895 | 2026-10-03 | 1734 | WA | Mt Holland
TC8137 | Cat D10T | N9502 | A/C Condenser | 15000 | 34089 | 2023-01-06 | 46895 | 2026-11-07 | 2194 | WA | Mt Holland
TC8137 | Cat D10T | N9998 | Extended Life Rebuild | 30000 |  | 2011-03-01 | 46895 | 2022-12-24 | -16895 | WA | Mt Holland
TC8137 | Cat D10T | N9998-01 | Extended Life Rebuild ONE | 45000 |  | 2011-03-01 | 46895 | 2026-01-08 | -1895 | WA | Mt Holland
TC8137 | Cat D10T | N9998-02 | Extended Life Rebuild TWO | 60000 |  | 2011-03-01 | 46895 | 2029-01-23 | 13105 | WA | Mt Holland

## JDE Fleet List
Eq St | Unit Number | Asset Description | Serial Number | Location | Location Description | ST | Actual Location
CW | RD4377 | Cat 785C | CAT0785CCAPX00313 | 159304 | FleetCo Maintenance Recharge | WA | Gold Fields St Ives
CW | RD4211 | Cat 785C | APX01608 | 610337 | Prominent Hill ROM | WA | Prominent Hill
CW | RD4213 | Cat 785C | APX01619 | 610337 | Prominent Hill ROM | WA | Prominent Hill
CW | DR2114 | Cat MD6310 - ADS | CATMD631CDLK00146 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2115 | Cat MD6310 - ADS | CATMD631KDLK00149 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2116 | Cat MD6310 - ADS | CATMD631HDLK00161 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2117 | Cat MD6310 - ADS | CATMD631EDLK00162 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2118 | Cat MD6310 - ADS | CATMD631ADLK00156 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2119 | Cat MD6310 - ADS | CATMD631JDLK00167 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2120 | Cat MD6310 - ADS | DLK00187 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2121 | Cat MD6310 - ADS | DLK00191 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
AW | DR2122 | Cat MD6310 - ADS | DLK00189 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DR2123 | Cat MD6310 - ADS | DLK00190 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ1937 | Cat D10T | CAT0D10THRJG02355 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ3420 | Cat D10T | RJG04360 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ3453 | Cat D10T | RJG02867 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ3454 | Cat D10T2 | RAB01197 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ8029 | Cat D10T2 | CAT0D10TCRAB00481 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ8083 | Cat D10T2 | RAB00468 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX2619 | Cat 6060 | CAT06060K6D600105 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX2634 | Cat 336-XZ | GDY21650 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX4001 | Cat 374 | CAT00374AKHH10054 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX4115 | Cat 374 | CAT00374AKHH20022 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX8388 | Cat 6060 | CAT06060J6D600106 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX8396 | Cat 336GC Excavator | CAT00336JJFW10384 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | EX8410 | Cat 301.8 | CAT03018VH8X04227 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | GR0008 | Cat 16M | CAT0016MKB9H00845 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | GR1271 | Cat 16M | CAT0016MER9H00512 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | GR1475 | Cat 24M | B9K77001 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | GR1527 | Cat 140M | EB200761 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | GR1528 | Cat 14M | F5800100 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | LO1965 | Cat 994H | CAT0994HEDWC00385 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | LO2031 | Cat 972M Loader | CAT0972MVM8W20244 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | LO2032 | Cat 930K Loader | CAT0930KJP3K01156 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | LO2033 | Cat 982M Loader | CAT0982MTLRS20241 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | LO2055 | Cat 962M | CAT8962MPLSE20313 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | LO2089 | Cat 966M Wheel Loader | L8R10269 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD2030 | Cat 793D | FDB00792 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD2031 | Cat 793D | FDB00793 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4201 | Cat 777F | JRP00813 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4378 | Cat 785C | CAT0785CHAPX00826 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4822 | Cat 785C | CAT0785CHAPX02043 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4910 | Cat 793F | SSP00131 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4911 | Cat 793F | SSP00137 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4912 | Cat 793F | SSP00138 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4913 | Cat 793F | SSP00139 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4914 | Cat 793F | SSP00152 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4915 | Cat 793F | SSP00157 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4916 | Cat 793F | SSP00579 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4917 | Cat 793F | SSP00580 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4918 | Cat 793F | SSP00597 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4919 | Cat 793F | SSP00598 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4920 | Cat 793F | SSP00605 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4921 | Cat 793F | SSP00195 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD4922 | Cat 793F | SSP00196 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | RD6260 | Cat 785C | APX01630 | 610350 | Iron Bridge Magnetite Project | WA | Iron Bridge
CW | DZ6207 | Cat D9T BLADE |  | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | DZ6528 | Cat D9T | TWG00796 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | DZ6542 | Cat D10T | RJG01192 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | DZ6551 | Cat D9T | J3D00442 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | DZ6629 | Cat D10T BLADE ASSY |  | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | EX6541 | Cat 336DL | TWRK00574 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | GR6524 | Cat 16M | E9Y00317 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | LO6110 | Cat 993K | Z8Z00185 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6194 | Cat 785D | MSY00838 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6195 | Cat 785D | MSY00839 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6196 | Cat 785D | MSY00840 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6197 | Cat 785D | MSY00357 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6198 | Cat 785D | MSY00377 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6222 | Cat 740GC | 3F800081 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6262 | Cat 740GC | CAT00740T3F800069 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6313 | Cat 785C | APX00620 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6314 | Cat 785C | APX00621 | 655489 | Sanjiv Ridge | WA | SANJIV RIDGE
CW | RD6502 | Cat 785C | APX00750 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6503 | Cat 785C | APX01046 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6530 | Cat 785C | APX00821 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6531 | Cat 785C | APX00822 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6532 | Cat 785C | APX00823 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6533 | Cat 785C | APX00824 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6562 | Cat 785D | MSY00255 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6564 | Cat 785D | MSY00257 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | RD6565 | Cat 785D | MSY00258 | 655489 | Sanjiv Ridge | WA | Sanjiv Ridge
CW | DR1080 | Cat MD6250 | DN700134 | 655578 | McPhee Creek | WA | McPhee Creek
CW | DZ3429 | Cat D10 | CAT00D10CMGY00232 | 655578 | McPhee Creek | WA | McPhee Creek
CW | DZ3433 | Cat D10 | CAT00D10CMGY00277 | 655578 | McPhee Creek | WA | McPhee Creek
CW | DZ6661 | Cat D10T2 | RAB01375 | 655578 | McPhee Creek | WA | McPhee Creek
CW | GR6655 | Cat 18M | NN600216 | 655578 | McPhee Creek | WA | McPhee Creek
CW | GR6656 | Cat 18M | NN600215 | 655578 | McPhee Creek | WA | McPhee Creek
CW | LO6631 | Cat 972 | W99000240 | 655578 | McPhee Creek | WA | McPhee Creek
CW | LO6670 | Cat 854K | RM600335 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6601 | Cat 789D | XDT00125 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6602 | Cat 789D | XDT00126 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6603 | Cat 789D | XDT00127 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6604 | Cat 789D | XDT00128 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6605 | Cat 789D | XDT00134 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6606 | Cat 789D | XDT00135 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6607 | Cat 789D | XDT00136 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6608 | Cat 789D | XDT00141 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6609 | Cat 789D | XDT00137 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6610 | Cat 789D | XDT00143 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6611 | Cat 789D | XDT00142 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6612 | Cat 789D | XDT00144 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6621 | Cat 777 | 7M302501 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6622 | Cat 777 | 7M302502 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6623 | Cat 777 | 7M302511 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6624 | Cat 777 | 7M302512 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6650 | Cat 777 | 7M602513 | 655578 | McPhee Creek | WA | McPhee Creek
CW | RD6651 | Cat 777 | 7M602514 | 655578 | McPhee Creek | WA | McPhee Creek
CW | DZ6517 | Cat D9T | RJS01734 | 655583 | Miralga Creek | WA | Miralga Creek
CW | DZ6526 | Cat D9T | TWG00561 | 655583 | Miralga Creek | WA | Miralga Creek
CW | DZ6536 | Cat D10T2 | RAB00947 | 655583 | Miralga Creek | WA | Miralga Creek
CW | GR6528 | Cat 16M | B9H00167 | 655583 | Miralga Creek | WA | Miralga Creek
CW | RD6527 | Cat 777G | TNM00134 | 655583 | Miralga Creek | WA | Miralga Creek
AT | DU1047 | Cat 785C | CAT0785CVAPX00305 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | DZ1757 | Cat D10T | RJG02264 | 810061 | Plant Idle - Mining West | WA | Norrish Earthmoving
AT | GR1373 | Cat 16M | B9H00484 | 810061 | Plant Idle - Mining West | WA | Norrish Earthmoving
AT | LW4073 | Cat 980H | MHG06438 | 810061 | Plant Idle - Mining West | WA | Muchea
AT | RD1740 | Cat 789C | 2BW01200 | 810061 | Plant Idle - Mining West | WA | Karlawinda
AT | RD2028 | Cat 793D | CAT0793DVFDB00784 | 810061 | Plant Idle - Mining West | WA | Iron Bridge
AT | RD2029 | Cat 793D | CAT0793DEFDB00791 | 810061 | Plant Idle - Mining West | WA | Iron Bridge
AT | RD2035 | Cat 793D | CAT0793DJFDB00801 | 810061 | Plant Idle - Mining West | WA | Iron Bridge
AT | RD2131 | Cat 793D | FDB00984 | 810061 | Plant Idle - Mining West | WA | Iron Bridge
AT | RD3830 | Cat 789C | 2BW01435 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD3831 | Cat 789C | 2BW01436 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD3977 | Cat 785C | APX01538 | 810061 | Plant Idle - Mining West | WA | Duketon South Operations
AT | RD4208 | Cat 785C | APX00929 | 810061 | Plant Idle - Mining West | WA | Duketon South Operations
AT | RD4210 | Cat 785C | APX01143 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4217 | Cat 785C | APX01624 | 810061 | Plant Idle - Mining West | WA | Duketon South Operations
AT | RD4218 | Cat 785C | APX01638 | 810061 | Plant Idle - Mining West | WA | Duketon South Operations
AT | RD4219 | Cat 785C | APX01776 | 810061 | Plant Idle - Mining West | WA | Muchea
AT | RD4220 | Cat 785C | APX01777 | 810061 | Plant Idle - Mining West | WA | Norrish Earthmoving Kalgoorlie
AT | RD4222 | Cat 785C | APX01807 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4223 | Cat 785D | MSY00100 | 810061 | Plant Idle - Mining West | WA | Norrish Earthmoving
AT | RD4224 | Cat 785D | MSY00158 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4225 | Cat 785D | MSY00159 | 810061 | Plant Idle - Mining West | WA | Norrish Earthmoving
AT | RD4231 | Cat 785D | MSY00267 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4235 | Cat 789C | 2BW00623 | 810061 | Plant Idle - Mining West | WA | Karlawinda
AT | RD4240 | Cat 789C | 2BW00754 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4241 | Cat 789C | 2BW00755 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4242 | Cat 789C | 2BW00756 | 810061 | Plant Idle - Mining West | WA | Muchea Yard
AT | RD4243 | Cat 789C | 2BW00922 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4244 | Cat 789C | 2BW00923 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4245 | Cat 789C | 2BW00929 | 810061 | Plant Idle - Mining West | WA | Muchea Yard
AT | RD4248 | Cat 789C | CAT0789CJ2BW01120 | 810061 | Plant Idle - Mining West | WA | Karlawinda
AT | RD4249 | Cat 789C | 2BW01123 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD4376 | Cat 785C | APX00312 | 810061 | Plant Idle - Mining West | WA | Hazelmere
AT | RD5009 | Cat 785C | APX01689 | 810061 | Plant Idle - Mining West | WA | Norrish Earthmoving
AT | RD6032 | Cat 785C | APX01395 | 810061 | Plant Idle - Mining West | WA | Mt Holland
AT | TC8137 | Cat D10T | CAT0D10TLRJG02810 | 810061 | Plant Idle - Mining West | WA | Mt Holland
CW | DZ3430 | Cat D10T | RJG04569 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | DZ3431 | Cat D10T | RJG04501 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | GR1549 | Cat 16M | R9H00373 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | GR1550 | Cat 16M | R9H00793 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | LO2121 | Cat 992K | ZMX00469 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | LO2122 | Cat 992K | ZMX00636 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | LO2129 | Cat 992K | RM500154 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | LO2130 | Cat 992K | ZMX00637 | 810303 | Yilgarn Hub | WA | Yilgarn Hub
CW | DZ1932 | Cat D10T | RJG00801 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | GR0996 | Cat 16H | ATS00717 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | LO1543 | Cat 994D | 3TZ00284 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | LO1637 | Cat 994H | DWC00302 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | LO1645 | Cat 966G | ANZ01411 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | LO1931 | Cat 994H | DWC00374 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | LO2139 | Cat 988 XE | LVZ00305 | 610337 | Prominent Hill ROM | SA | Prominent Hill
CW | RD1210 | Cat 777D | AGC00809 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | RD2618 | Cat 793D | FDB01409 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | RD2619 | Cat 793D | FDB01410 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | RD2620 | Cat 793D | FDB01438 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | RD2621 | Cat 793D | FDB01452 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM
CW | RD2622 | Cat 793D | FDB01476 | 610337 | Prominent Hill ROM | SA | Prominent Hill ROM