## CB MM LTP
Type (A) | Program (B) | Department (C) | Vendor (D) | Equipment (E) | Task Name (F) | Start (G) | Finish (H) | Duration (I) | Period (J) | Work (K) | Group (L) | Group Counter (M) | Maint Item (N) | Component Due Date (O) | Strategy (P) | Function Location (Q) | Annual Estimate | Meas/TotCtrRdg | Counter reading
CB MM MAJOR COMPONENT REPLACEMENT SCHEDULE
| MCORS |  | Various |  | MCORS
| MCORS |  |  |  | FY27 - MCORS | 2026-07-01 | 2027-06-30 | 364 days | FY27
| MCORS | Haul | Various |  | HAUL | 2026-07-01 | 2027-06-30 | 364 days | FY27
785D | MCORS | Haul | Mader | WC012 | WC012 - MCORS | 2026-07-21 | 2026-09-03 | 44 days | FY27
785D | MCORS | Haul | Mader | WC012 | Decommissioning | 2026-07-21 | 2026-07-23 | 2 days | FY27
785D | MCORS | Haul | Mader | WC012 | Load & Transport | 2026-07-24 | 2026-07-27 | 3 days | FY27
785D | MCORS | Haul | Mader | WC012 | WC012 - Baseline Scope | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Engine | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 398 | 90028980 | A1 | 1000289417 | 24.08.2026 | 20000 | CLB-MP-SUPP-WC012 -ENGINE | 5000 | 67273 | 20856 | CLB-MP-SUPP-WC012 -ENGINE90028980
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Aftercooler | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 6 | 90004021 | 1 | 1000044576 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-AFTER | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-AFTER90004021
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Pump Drive | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 28 | 90003984 | 1 | 1000044578 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR90003984
785D | MCORS | Haul | Mader | WC012 | WC012 Repl PTO Uni's & Driveshaft | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90031094 | A1 | 1000307804 | 28.05.2026 | 10000 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT90031094
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Torque Converter | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 26 | 90003987 | 1 | 1000044579 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -TRNSYS-TRQUE | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -TRNSYS-TRQUE90003987
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Transmission | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 52 | 90003988 | 1 | 1000044580 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -TRNSYS-TRANS | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -TRNSYS-TRANS90003988
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Transmission Pump | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 6 | 90003991 | 1 | 1000044582 | 28.05.2026 | 10000 | CLB-MP-SUPP-WC012 -TRNSYS-TRPMP-TMCPP | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -TRNSYS-TRPMP-TMCPP90003991
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Transmission Oil Cooler | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 8 | 90003992 | 1 | 1000044615 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -TRNSYS-TROLC | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -TRNSYS-TROLC90003992
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Rear Axle Cooling Fan Motor | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90003997 | 1 | 1000044592 | 13.07.2026 | 10000 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-MTFAN | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-MTFAN90003997
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Rear Axle Oil Pump | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90003996 | 1 | 1000044591 | 13.07.2026 | 10000 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-HYPUM | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-HYPUM90003996
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Transmission Driveshaft | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 13 | 90003993 | 1 | 1000044583 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -FDRSYS-DRSHT | 5000 | 67273 | 4720 | CLB-MP-SUPP-WC012 -FDRSYS-DRSHT90003993
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Differential | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 28 | 90003994 | 1 | 1000044584 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -FDRSYS-DIFFL | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -FDRSYS-DIFFL90003994
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Final Drive LH | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 26 | 90003995 | 1 | 1000044589 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -FDRSYS-FDRVE-FDRLH | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -FDRSYS-FDRVE-FDRLH90003995
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Final Drive RH | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 26 | 90007346 | 1 | 1000044590 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -FDRSYS-FDRVE-FDRRH | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -FDRSYS-FDRVE-FDRRH90007346
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Brake Control Valves | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 48 | 90004000 | 1 | 1000044596 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-BRVLV | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-BRVLV90004000
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Brake Oil Cooler Front | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 6 | 90004002 | 1 | 1000044598 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-BROCO-BROCF | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-BROCO-BROCF90004002
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Brake Rotochamber Front | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90004017 | 1 | 1000044618 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTFR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTFR90004017
785D | MCORS | Haul | Mader | WC012 | WC012 Brake Rotochamber Left Hand Rear | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90004017 | 1 | 1000044619 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTLR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTLR90004017
785D | MCORS | Haul | Mader | WC012 | WC012 Brake Rotochamber Right Hand Rear | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90004017 | 1 | 1000044620 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTRR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTRR90004017
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Brake Slack Adjustor Front | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90004018 | 1 | 1000044621 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-SLACK-SLACF | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-SLACK-SLACF90004018
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Brake Slack Adjustor Rear | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 2 | 90004019 | 1 | 1000044622 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -BRKSYS-SLACK-SLACR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-SLACK-SLACR90004019
785D | MCORS | Haul | Mader | WC012 | WC012 Overhaul Airconditioner | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 24 | 90028727 | A1 | 1000289420 | 24.08.2026 | 10000 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN | 5000 | 67273 | 10760 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN90028727
785D | MCORS | Haul | Mader | WC012 | WC012 Replace Seat Operators | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 4 | 90004012 | 1 | 1000161839 | 09.10.2026 | 10000 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-SEATS | 5000 | 67273 | 10220 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-SEATS90004012
785D | MCORS | Haul | Mader | WC012 | WC012 Water Tank Module Midlife | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 0 | 90028967 | A1 | 1000289019 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -STRUCT-WTANK | 5000 | 67273 | 67273 | CLB-MP-SUPP-WC012 -STRUCT-WTANK90028967
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Suspension Cylinder LHF | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 28 | 90004013 | 1 | 1000044611 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYLF | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYLF90004013
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Suspension Cylinder RHF | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 28 | 90004013 | 1 | 1000044612 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYRF | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYRF90004013
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Suspension Cylinder LHR | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 28 | 90004014 | 1 | 1000044613 | 28.05.2026 | 20000 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYLR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYLR90004014
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Suspension Cylinder RHR | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 28 | 90004014 | 1 | 1000044614 | 06.07.2026 | 20000 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYRR | 5000 | 67273 | 21499 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYRR90004014
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Hub & Spindle LH | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 50 | 90004020 | 1 | 1000044593 | 17.12.2026 | 24000 | CLB-MP-SUPP-WC012 -STRUCT-AXLES-HUBLH | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -STRUCT-AXLES-HUBLH90004020
785D | MCORS | Haul | Mader | WC012 | WC012 Repl Hub & Spindle RH | 2026-07-28 | 2026-08-24 | 27 days | FY27 | 50 | 90026194 | A1 | 1000044594 | 17.12.2026 | 24000 | CLB-MP-SUPP-WC012 -STRUCT-AXLES-HUBRH | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -STRUCT-AXLES-HUBRH90026194
785D | MCORS | Haul | Mader | WC012 | Repurposed: SVA Harness Replacement | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Corroded Tubes and Pipes | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Repurposed: Access Ladders & Platforms | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | 789D Exhaust System and Lagging | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | CAT 789 Intake Piping | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | MCORS Transport | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Opex Variation | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Capex Variation | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Additional Baseline Opex Truck Fleet | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Additional Baseline Capex Truck Fleet | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Minor Hosing Opex | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Baseline Harness (Not on strategy) Capex | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Variation Opex - Corrosions/Repairs | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Capex Variation - Cab Overhaul (if applicable) | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | MCORS Site Labour Recovery - 785D | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | MCORS Watercart Module Refurbishment Midlife CAPEX | 2026-07-28 | 2026-08-24 | 27 days | FY27
785D | MCORS | Haul | Mader | WC012 | Transport & Unload | 2026-08-25 | 2026-08-28 | 3 days | FY27
785D | MCORS | Haul | Mader | WC012 | Recommissioning | 2026-08-29 | 2026-09-03 | 5 days | FY27
785D | MCORS | Haul | Mader | WC013 | WC013 - MCORS | 2026-09-13 | 2026-10-27 | 44 days | FY27
785D | MCORS | Haul | Mader | WC013 | Decommissioning | 2026-09-13 | 2026-09-15 | 2 days | FY27
785D | MCORS | Haul | Mader | WC013 | Load & Transport | 2026-09-16 | 2026-09-19 | 3 days | FY27
785D | MCORS | Haul | Mader | WC013 | WC013 - Baseline Scope | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Aftercooler | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 6 | 90004021 | 1 | 1000044640 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-AFTER | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-AFTER90004021
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Pump Drive | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 28 | 90003984 | 1 | 1000044642 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR90003984
785D | MCORS | Haul | Mader | WC013 | WC013 Repl PTO Uni's & Driveshaft | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90031094 | A1 | 1000307806 | 26.06.2026 | 10000 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT | 5000 | 63833 | 10962 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT90031094
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Transmission | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 52 | 90003988 | 1 | 1000044644 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -TRNSYS-TRANS | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -TRNSYS-TRANS90003988
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Transmission Pump | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 6 | 90003991 | 1 | 1000044646 | 26.06.2026 | 10000 | CLB-MP-SUPP-WC013 -TRNSYS-TRPMP-TMCPP | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -TRNSYS-TRPMP-TMCPP90003991
785D | MCORS | Haul | Mader | WC013 | WC013 Repl TC-Park Brake-Scavenge Pump | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 6 | 90003990 | 1 | 1000044659 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -TRNSYS-TRPMP-TCCPP | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -TRNSYS-TRPMP-TCCPP90003990
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Transmission Oil Cooler | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 8 | 90003992 | 1 | 1000044679 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -TRNSYS-TROLC | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -TRNSYS-TROLC90003992
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Rear Axle Cooling Fan Motor | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90003997 | 1 | 1000044656 | 26.06.2026 | 10000 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-MTFAN | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-MTFAN90003997
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Rear Axle Oil Pump | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90003996 | 1 | 1000044655 | 26.06.2026 | 10000 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-HYPUM | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-HYPUM90003996
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Differential | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 28 | 90003994 | 1 | 1000044648 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -FDRSYS-DIFFL | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -FDRSYS-DIFFL90003994
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Final Drive LH | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 26 | 90003995 | 1 | 1000044653 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -FDRSYS-FDRVE-FDRLH | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -FDRSYS-FDRVE-FDRLH90003995
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Final Drive RH | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 26 | 90007346 | 1 | 1000044654 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -FDRSYS-FDRVE-FDRRH | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -FDRSYS-FDRVE-FDRRH90007346
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Brake Control Valves | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 48 | 90004000 | 1 | 1000044660 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -BRKSYS-BRVLV | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-BRVLV90004000
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Brake Oil Cooler Front | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 6 | 90004002 | 1 | 1000044662 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -BRKSYS-BROCO-BROCF | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-BROCO-BROCF90004002
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Brake Rotochamber Front | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90004017 | 1 | 1000044682 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTFR | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTFR90004017
785D | MCORS | Haul | Mader | WC013 | WC013 Brake Rotochamber Left Hand Rear | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90004017 | 1 | 1000044683 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTLR | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTLR90004017
785D | MCORS | Haul | Mader | WC013 | WC013 Brake Rotochamber Right Hand Rear | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90004017 | 1 | 1000044684 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTRR | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTRR90004017
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Brake Slack Adjustor Front | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 2 | 90004018 | 1 | 1000044685 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -BRKSYS-SLACK-SLACF | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-SLACK-SLACF90004018
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Steering HMU | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 8 | 90004004 | 1 | 1000044666 | 23.08.2026 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STHMU | 5000 | 63833 | 15155 | CLB-MP-SUPP-WC013 -STRSYS-STHMU90004004
785D | MCORS | Haul | Mader | WC013 | WC013 Water Tank Module Midlife | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 0 | 90028967 | A1 | 1000289041 | 22.06.2026 | 20000 | CLB-MP-SUPP-WC013 -STRUCT-WTANK | 5000 | 63825 | 63825 | CLB-MP-SUPP-WC013 -STRUCT-WTANK90028967
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Suspension Cylinder LHF | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 28 | 90004013 | 1 | 1000044675 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYLF | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYLF90004013
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Suspension Cylinder RHF | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 28 | 90004013 | 1 | 1000044676 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYRF | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYRF90004013
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Suspension Cylinder LHR | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 28 | 90004014 | 1 | 1000044677 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYLR | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYLR90004014
785D | MCORS | Haul | Mader | WC013 | WC013 Repl Suspension Cylinder RHR | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 28 | 90004014 | 1 | 1000044678 | 26.06.2026 | 20000 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYRR | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYRR90004014
785D | MCORS | Haul | Mader | WC013 | WC013 Replace Water Cannon | 2026-09-20 | 2026-10-17 | 27 days | FY27 | 24 | 90015535 | 1 | 1000133453 | 17.09.2026 | 12 Monthly | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON90015535
785D | MCORS | Haul | Mader | WC013 | MCORS Transport | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Opex Variation | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Capex Variation | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Additional Baseline Opex Truck Fleet | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Additional Baseline Capex Truck Fleet | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Minor Hosing Opex | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Baseline Harness (Not on strategy) Capex | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Variation Opex - Corrosions/Repairs | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Capex Variation - Cab Overhaul (if applicable) | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | MCORS Site Labour Recovery - 785D | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | MCORS Watercart Module Refurbishment Midlife CAPEX | 2026-09-20 | 2026-10-17 | 27 days | FY27
785D | MCORS | Haul | Mader | WC013 | Transport & Unload | 2026-10-18 | 2026-10-21 | 3 days | FY27
785D | MCORS | Haul | Mader | WC013 | Recommissioning | 2026-10-22 | 2026-10-27 | 5 days | FY27
777F | MCORS | Haul | Mader | SV021 | SV021 - MCORS | 2027-01-02 | 2027-03-26 | 83 days | FY27
777F | MCORS | Haul | Mader | SV021 | Decommissioning | 2027-01-02 | 2027-01-04 | 2 days | FY27
777F | MCORS | Haul | Mader | SV021 | Load & Transport | 2027-01-05 | 2027-01-08 | 3 days | FY27
777F | MCORS | Haul | Mader | SV021 | SV021 - Baseline Scope | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Engine Radiator | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 48 | 90003023 | A1 | 1000033971 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -ENGINE-COSYS-RADTR | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -ENGINE-COSYS-RADTR90003023
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Engine Aftercooler | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 3 | 90003029 | A1 | 1000033972 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -ENGINE-INTEX-AFTER | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -ENGINE-INTEX-AFTER90003029
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Torque Converter | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 26 | 90003035 | A1 | 1000033973 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -TRNSYS-TRQUE | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -TRNSYS-TRQUE90003035
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Drive Shaft | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 2 | 90003041 | A1 | 1000033979 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -FDRSYS-DRSHT | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -FDRSYS-DRSHT90003041
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Differential | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 36 | 90003042 | A1 | 1000033980 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -FDRSYS-DIFFL | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -FDRSYS-DIFFL90003042
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Final Drive LH | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 48 | 90003043 | A1 | 1000033981 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE-FDRLH | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE-FDRLH90003043
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Final Drive RH | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 30 | 90007347 | 1 | 1000033982 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE-FDRRH | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE-FDRRH90007347
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Steering HMU | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 12 | 90003052 | A1 | 1000033992 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -STRSYS-STHMU | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -STRSYS-STHMU90003052
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Steering Hoses Lines | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 48 | 90003058 | A1 | 1000033999 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -STRSYS-STHLF | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -STRSYS-STHLF90003058
777F | MCORS | Haul | Mader | SV021 | SV021 Refurbish A Frame | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 48 | 90003067 | A1 | 1000034009 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -STRUCT-CHASS-AFRME | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -STRUCT-CHASS-AFRME90003067
777F | MCORS | Haul | Mader | SV021 | SV021 OverHaul Tag Link | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 48 | 90003068 | A1 | 1000034010 | 21.12.2026 | 18000 | CLB-MP-SUPP-SV021 -STRUCT-CHASS-TAGLK | 3300 | 54098 | 16520 | CLB-MP-SUPP-SV021 -STRUCT-CHASS-TAGLK90003068
777F | MCORS | Haul | Mader | SV021 | SV021 Replace Auto Lube Pump | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 4 | 90003064 | A1 | 1000034006 | 24.12.2026 | 6000 | CLB-MP-SUPP-SV021 -GRSYST-ALBPP | 3300 | 54098 | 4488 | CLB-MP-SUPP-SV021 -GRSYST-ALBPP90003064
777F | MCORS | Haul | Mader | SV021 | SV021 Steering Linkages | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 24 | 90003056 | A1 | 1000033997 | 02.10.2026 | 9000 | CLB-MP-SUPP-SV021 -STRSYS-STLTR | 3300 | 54098 | 8323 | CLB-MP-SUPP-SV021 -STRSYS-STLTR90003056
777F | MCORS | Haul | Mader | SV021 | SV021 Service Tank Module Midlife | 2027-01-11 | 2027-03-16 | 64 days | FY27 | 1 | 90028958 | A1 | 1000288849 | 29.06.2026 | 18000 | CLB-MP-SUPP-SV021 -STRUCT-SVTNK | 3300 | 54098 | 54098 | CLB-MP-SUPP-SV021 -STRUCT-SVTNK90028958
777F | MCORS | Haul | Mader | SV021 | MCORS Transport | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Opex Variation | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Capex Variation | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Additional Baseline Opex Truck Fleet | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Additional Baseline Capex Truck Fleet | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Minor Hosing Opex | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Baseline Harness (Not on strategy) Capex | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Variation Opex - Corrosions/Repairs | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | MCORS Site Labour Recovery - 777F | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | MCORS SV Module Refurbishment Midlife CAPEX | 2027-01-11 | 2027-03-16 | 64 days | FY27
777F | MCORS | Haul | Mader | SV021 | Transport & Unload | 2027-03-17 | 2027-03-20 | 3 days | FY27
777F | MCORS | Haul | Mader | SV021 | Recommissioning | 2027-03-21 | 2027-03-26 | 5 days | FY27
785D | MCORS | Haul | Mader | WC3108 | WC3108 - MCORS | 2027-01-10 | 2027-02-23 | 44 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Decommissioning | 2027-01-10 | 2027-01-12 | 2 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Load & Transport | 2027-01-13 | 2027-01-16 | 3 days | FY27
785D | MCORS | Haul | Mader | WC3108 | WC3108 - Baseline Scope | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl Rear Axle Cooling Fan Motor | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90003997 | 1 | 1000221748 | 02.01.2027 | 10000 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-MTFAN | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-MTFAN90003997
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Rear Axle Oil Pump | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90003996 | 1 | 1000221747 | 02.01.2027 | 10000 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-HYPUM | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-HYPUM90003996
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl Engine | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 398 | 90028980 | A1 | 1000289471 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-ENGINE | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-ENGINE90028980
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Radiator Assembly | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 38 | 90003977 | 1 | 1000221737 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-RADTR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-RADTR90003977
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Aftercooler | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 6 | 90004021 | 1 | 1000221736 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-AFTER | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-AFTER90004021
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl PTO Uni's & Driveshaft | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90031094 | A1 | 1000307812 | 15.01.2027 | 10000 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT90031094
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Torque Converter | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 26 | 90003987 | 1 | 1000221739 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-TRNSYS-TRQUE | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TRQUE90003987
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl Transmission | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 52 | 90003988 | 1 | 1000221740 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-TRNSYS-TRANS | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TRANS90003988
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl TC-Park Brake-Scavenge Pump | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 6 | 90003990 | 1 | 1000221751 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TCCPP | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TCCPP90003990
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Transmission Oil Cooler | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 8 | 90003992 | 1 | 1000221769 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-TRNSYS-TROLC | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TROLC90003992
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Transmission Driveshaft | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 13 | 90003993 | 1 | 1000221743 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-FDRSYS-DRSHT | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-FDRSYS-DRSHT90003993
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Differential | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 28 | 90003994 | 1 | 1000221744 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-FDRSYS-DIFFL | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-FDRSYS-DIFFL90003994
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Brake Control Valves | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 48 | 90004000 | 1 | 1000221752 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-BRVLV | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-BRVLV90004000
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl Brake Oil Cooler Front | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 6 | 90004002 | 1 | 1000221754 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-BROCO-BROCF | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-BROCO-BROCF90004002
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Brake Rotochamber Front | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90004017 | 1 | 1000221770 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTFR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTFR90004017
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Brake Rotochamber LHR | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90004017 | 1 | 1000221771 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTLR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTLR90004017
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Brake Rotochamber RHR | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90004017 | 1 | 1000221772 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTRR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTRR90004017
785D | MCORS | Haul | Mader | WC3108 | WC3108 Repl Brake Slack Adjustor Front | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90004018 | 1 | 1000221773 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-SLACK-SLACF | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-SLACK-SLACF90004018
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Brake Slack Adjustor Rear | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 2 | 90004019 | 1 | 1000221774 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-BRKSYS-SLACK-SLACR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-SLACK-SLACR90004019
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Hoist & Rear Brake Pump | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 5 | 90004008 | 1 | 1000221763 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-HYDSYS-HOPMP | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-HYDSYS-HOPMP90004008
785D | MCORS | Haul | Mader | WC3108 | WC3108 Overhaul Airconditioner | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 24 | 90028727 | A1 | 1000289474 | 15.01.2027 | 10000 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN90028727
785D | MCORS | Haul | Mader | WC3108 | WC3108 Water Tank Module Midlife | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 0 | 90028967 | A1 | 1000289058 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-STRUCT-WTANK | 5000 | 17735 | 17735 | CLB-MP-SUPP-WC3108-STRUCT-WTANK90028967
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Suspension Cylinder LHF | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 28 | 90004013 | 1 | 1000221765 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYLF | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYLF90004013
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Suspension Cylinder RHF | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 28 | 90004013 | 1 | 1000221766 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYRF | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYRF90004013
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Suspension Cylinder LHR | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 28 | 90004014 | 1 | 1000221767 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYLR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYLR90004014
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Suspension Cylinder RHR | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 28 | 90004014 | 1 | 1000221768 | 15.01.2027 | 20000 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYRR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYRR90004014
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Final Drive LH | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 26 | 90003995 | 1 | 1000221745 | 04.06.2027 | 20000 | CLB-MP-SUPP-WC3108-FDRSYS-FDRVE-FDRLH | 5000 | 17738 | 15820 | CLB-MP-SUPP-WC3108-FDRSYS-FDRVE-FDRLH90003995
785D | MCORS | Haul | Mader | WC3108 | WC3108 Replace Final Drive RH | 2027-01-17 | 2027-02-13 | 27 days | FY27 | 26 | 90007346 | 1 | 1000221746 | 04.06.2027 | 20000 | CLB-MP-SUPP-WC3108-FDRSYS-FDRVE-FDRRH | 5000 | 17738 | 15820 | CLB-MP-SUPP-WC3108-FDRSYS-FDRVE-FDRRH90007346
785D | MCORS | Haul | Mader | WC3108 | MCORS Transport | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Opex Variation | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Capex Variation | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Additional Baseline Opex Truck Fleet | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Additional Baseline Capex Truck Fleet | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Minor Hosing Opex | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Baseline Harness (Not on strategy) Capex | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Variation Opex - Corrosions/Repairs | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Capex Variation - Cab Overhaul (if applicable) | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | MCORS Site Labour Recovery - 785D | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | MCORS Watercart Module Refurbishment Midlife CAPEX | 2027-01-17 | 2027-02-13 | 27 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Transport & Unload | 2027-02-14 | 2027-02-17 | 3 days | FY27
785D | MCORS | Haul | Mader | WC3108 | Recommissioning | 2027-02-18 | 2027-02-23 | 5 days | FY27
| MCORS | Ancillary | Various |  | ANCILLARY | 2026-07-01 | 2027-06-30 | 364 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 - MCORS | 2026-06-22 | 2026-07-21 | 29.5 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Decommissioning | 2026-06-22 | 2026-06-22 | 0.5 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Load & Transport | 2026-06-23 | 2026-06-25 | 2 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 - Baseline Scope | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Engine Cat C18 | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 310 | 90015771 | 1 | 1000159874 | 02.07.2026 | 14000 | CLB-MP-GRDR-GR018 -ENGINE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE90015771
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Radiator Engine Cooling | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 38 | 90002618 | A1 | 1000028518 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-RADTR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-RADTR90002618
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Aftercooler Engine | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 32 | 90002623 | A1 | 1000080586 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-AFTER | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-AFTER90002623
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Electrical Harness | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 48 | 90010000 | 1 | 1000080068 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -ELCTLV-HARNS | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ELCTLV-HARNS90010000
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Replace Torque Converter | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 122 | 90002630 | A1 | 1000028521 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -TRNSYS-TRQUE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -TRNSYS-TRQUE90002630
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Transmission Oil Cooler | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 6 | 90002632 | A1 | 1000028523 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -TRNSYS-TROLC | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -TRNSYS-TROLC90002632
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Rear Axle Assembly | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 128 | 90030396 | A1 | 1000303551 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -FDRSYS-DIFFL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -FDRSYS-DIFFL90030396
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Service Brake LHF | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 36 | 90002640 | A1 | 1000028532 | 30.06.2026 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLF | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLF90002640
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Service Brake RHF | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 36 | 90002640 | A1 | 1000028533 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRF | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRF90002640
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Service Brake LHR | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 50 | 90004548 | 1 | 1000028534 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLR90004548
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Service Brake RHR | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 50 | 90004548 | 1 | 1000028535 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRR90004548
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Brake Slack Adjuster LH | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 4 | 90002641 | A1 | 1000085614 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACL90002641
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Brake Slack Adjuster Rear | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 4 | 90002641 | A1 | 1000085615 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACR90002641
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Hyd Pump Secondary Steering | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 12 | 90002645 | A1 | 1000028539 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -STRSYS-STEMG-SESPP | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRSYS-STEMG-SESPP90002645
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Hyd Pump Brake & Fan | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 12 | 90002648 | A1 | 1000028542 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-FANPP | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-FANPP90002648
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Hyd Pump Differential Lock | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 4 | 90002649 | A1 | 1000028543 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-DIFFL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-DIFFL90002649
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Hyd Fan Motor | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 16 | 90002651 | A1 | 1000028546 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT03 | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT0390002651
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Overhaul Auto Lubrication System | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 2 | 90002660 | A1 | 1000028559 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -GRSYST-ALBPP | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -GRSYST-ALBPP90002660
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Overhaul Air Conditioner | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 48 | 90017475 | 1 | 1000160707 | 02.07.2026 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN90017475
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Axle Assembly Front | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 98 | 90002666 | A1 | 1000180092 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-AXLES | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-AXLES90002666
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Overhaul Drawbar Group | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 96 | 90002668 | A1 | 1000028566 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-DRWBR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-DRWBR90002668
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Blade Mounting Bracket LH | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 48 | 90002671 | A1 | 1000028568 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBL90002671
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Blade Mounting Bracket RH | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 48 | 90002671 | A1 | 1000028569 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBR90002671
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Gearbox Circle Drive Rear | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 14 | 90011066 | 1 | 1000028571 | 20.11.2026 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXR90011066
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Steering System Hoses | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 24 | 90009996 | 1 | 1000080103 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-STRNG | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-STRNG90009996
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Replace Brake System Hoses | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 24 | 90009997 | 1 | 1000080100 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-BRKS | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-BRKS90009997
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Power Train System Hoses | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 36 | 90009999 | 1 | 1000080102 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-PWTRN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-PWTRN90009999
24M | MCORS | Ancillary | Force - Perth | GR018 | GR018 Repl Hydraulic System Hoses | 2026-06-26 | 2026-07-17 | 21 days | FY27 | 48 | 90009998 | 1 | 1000080101 | 29.06.2026 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-HYDSH | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-HYDSH90009998
24M | MCORS | Ancillary | Force - Perth | GR018 | MCORS Transport | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Opex Variation | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Capex Variation | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Additional Baseline Opex Ancillary Fleet | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Additional Baseline Capex Ancillary Fleet | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Minor Hosing Opex | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Major Hosing Price Variances - Capex | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Baseline Harness (Not on strategy) Capex | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Variation Opex - Corrosions/Repairs | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Capex Variation - Cab Overhaul (if applicable) | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | MCORS Site Labour Recovery - 24M | 2026-06-26 | 2026-07-17 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Transport & Unload | 2026-07-18 | 2026-07-20 | 2 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR018 | Recommissioning | 2026-07-21 | 2026-07-21 | 0.5 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 - MCORS | 2026-06-22 | 2026-08-07 | 46 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Decommissioning | 2026-06-22 | 2026-06-23 | 1 day | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Load & Transport | 2026-06-24 | 2026-06-27 | 3 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 - Baseline Scope | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Centre Output Drive Shaft | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 14 | 90033171 | A1 | 1000333615 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT03 | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0390033171
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Engine Midlife complete | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 170 | 90021253 | 1 | 1000222485 | 20.04.2026 | 10000 | CLB-MP-LOAD-WL028 -ENGINE | 6000 | 80034 | 11272 | CLB-MP-LOAD-WL028 -ENGINE90021253
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Electrical Harness | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 36 | 90010123 | 1 | 1000081878 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -ELCTLV-HARNS | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -ELCTLV-HARNS90010123
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Torque Converter | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 48 | 90002693 | A1 | 1000029186 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-TRQUE | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-TRQUE90002693
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Transmission Oil Cooler | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 36 | 90002695 | A1 | 1000029189 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-TROLC | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-TROLC90002695
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Gearbox Pump Drive Front | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 74 | 90002705 | A1 | 1000029199 | 07.11.2025 | 16000 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-FRPDR | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-FRPDR90002705
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Gearbox Pump Drive Rear | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 434 | 90002706 | A1 | 1000029200 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-RRPDR | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-RRPDR90002706
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Rear Output Drive Shaft Unis | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 8 | 90033167 | A1 | 1000333614 | 15.10.2026 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT02 | 6000 | 80034 | 8272 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0290033167
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Front Drive Shaft Unis | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 8 | 90033188 | A1 | 1000333618 | 14.06.2026 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT04 | 6000 | 80034 | 10044 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0490033188
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Rr PDrv Drive Shaft Ctr Brg | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 8 | 90033193 | A1 | 1000333620 | 29.06.2026 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT05 | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0590033193
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Centre Bearing Upper Shaft | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 24 | 90002702 | A1 | 1000029196 | 29.06.2026 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-UCTRB | 6000 | 80034 | 10044 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-UCTRB90002702
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Front Differential | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 98 | 90002707 | A1 | 1000029201 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -FDRSYS-FRDIF | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -FDRSYS-FRDIF90002707
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Rear Differential | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 98 | 90002708 | A1 | 1000029202 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -FDRSYS-RRDIF | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -FDRSYS-RRDIF90002708
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Overhaul Rear Axle Trunnion | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 96 | 90002709 | A1 | 1000029203 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -FDRSYS-RRDIF-TRNON | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -FDRSYS-RRDIF-TRNON90002709
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hyd Pump Brake | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 12 | 90002712 | A1 | 1000029208 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP01 | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP0190002712
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Reseal Brake Accumulator Front | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 12 | 90002714 | A1 | 1000257285 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC-BACCF | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC-BACCF90002714
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Reseal Brake Accumulator Rear | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 12 | 90002714 | A1 | 1000089010 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC-BACCR | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC-BACCR90002714
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Brake Oil Cooler | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 72 | 90002715 | A1 | 1000103787 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -BRKSYS-BROCC | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -BRKSYS-BROCC90002715
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Steer & Brake Oil Cooler Pump | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 8 | 90002718 | A1 | 1000029215 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP03 | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP0390002718
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Cyl Steering RH | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 20 | 90002722 | A1 | 1000029219 | 24.07.2026 | 12000 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYR | 6000 | 80034 | 11632 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYR90002722
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Reseal Steering & Brake Tank | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 36 | 90010963 | 1 | 1000090053 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STTNK | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRSYS-STTNK90010963
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hyd Pump Implement LH | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 24 | 90002723 | A1 | 1000029220 | 10.09.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP01 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0190002723
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hyd Pump Implement RH | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 24 | 90002724 | A1 | 1000029221 | 10.09.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP02 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0290002724
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hyd Pump Implement Centre | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 24 | 90002725 | A1 | 1000029222 | 10.09.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP03 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0390002725
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hyd Pump Pilot & Cooling | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 12 | 90002726 | A1 | 1000029223 | 10.09.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP04 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0490002726
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Cyl Lift LH High Lift | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 40 | 90002727 | A1 | 1000029224 | 10.09.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLL | 6000 | 80034 | 8837 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLL90002727
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Cyl Bucket LH High Lift | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 36 | 90017978 | A1 | 1000029226 | 29.06.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYL | 6000 | 80034 | 7256 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYL90017978
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Cyl Bucket RH High Lift | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 36 | 90017977 | A1 | 1000029227 | 08.12.2026 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYR | 6000 | 80034 | 7379 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYR90017977
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Reseal Tank Hyd | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 12 | 90010623 | 1 | 1000087661 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-HDTNK-HYT01 | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -HYDSYS-HDTNK-HYT0190010623
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hyd Pilot Accumulator | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 4 | 90012174 | 1 | 1000100313 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-PACCM | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -HYDSYS-PACCM90012174
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Main Airhoses & Valves | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 18 | 90011137 | A1 | 1000093197 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -PNEUMC-PNHLF |  |  |  | CLB-MP-LOAD-WL028 -PNEUMC-PNHLF90011137
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Overhaul Air Conditioner | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 48 | 90021132 | 1 | 1000222477 | 20.04.2026 | 10000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN90021132
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Overhaul Boom | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 96 | 90021334 | A1 | 1000223811 | 14.11.2026 | 40000 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-LIARM | 6000 | 80034 | 37765 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-LIARM90021334
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Steering Neutralizer Valves | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 6 | 90002720 | A1 | 1000076057 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STNVS | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRSYS-STNVS90002720
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Brake System Hoses | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 48 | 90026921 | A1 | 1000271639 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -BRKSYS-BRHLF-BRKHO | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -BRKSYS-BRHLF-BRKHO90026921
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Hydraulic System Hoses | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 96 | 90026922 | A1 | 1000271641 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-HYDHO | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-HYDHO90026922
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Repl Pilot System Hoses | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 96 | 90009731 | 2 | 1000076492 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-PILHO | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-PILHO90009731
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Replace Steering System Hoses | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 96 | 90009732 | 1 | 1000076493 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STHLF-STRHO | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRSYS-STHLF-STRHO90009732
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Fr Frame Grease Hoses | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 24 | 90010326 | 1 | 1000105484 | 08.07.2026 | 20000 | CLB-MP-LOAD-WL028 -GRSYST-FFGHO | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -GRSYST-FFGHO90010326
994H | MCORS | Ancillary | Force - Perth | WL028 | WL028 Replace Artic Area Hyd Hosing | 2026-06-28 | 2026-07-30 | 32 days | FY27 | 6 | 90020831 | 1 | 1000220522 | 25.04.2026 | 8 Monthly | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO90020831
994H | MCORS | Ancillary | Force - Perth | WL028 | 994H Safe Board Ladder Replace | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | 994 Hydraulic Tank Replacement | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | 994H Radiator Upgrade to Mesabi Cooling | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | MCORS Transport | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Opex Variation | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Capex Variation | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Additional Baseline Opex Ancillary Fleet | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Additional Baseline Capex Ancillary Fleet | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Minor Hosing Opex | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Major Hosing Price Variances - Capex | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Baseline Harness (Not on strategy) Capex | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Variation Opex - Corrosions/Repairs | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Capex Variation - Cab Overhaul (if applicable) | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | MCORS Site Labour Recovery - 994H | 2026-06-28 | 2026-07-30 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Transport & Unload | 2026-07-31 | 2026-08-03 | 3 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL028 | Recommissioning | 2026-08-04 | 2026-08-07 | 3 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 - MCORS | 2026-07-20 | 2026-08-18 | 29.5 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Decommissioning | 2026-07-20 | 2026-07-20 | 0.5 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Load & Transport | 2026-07-21 | 2026-07-23 | 2 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 - Baseline Scope | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Engine Cat C18 | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 310 | 90015771 | 1 | 1000159900 | 02.06.2026 | 14000 | CLB-MP-GRDR-GR021 -ENGINE | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE90015771
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Radiator Engine Cooling | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 38 | 90002618 | A1 | 1000028646 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-RADTR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-RADTR90002618
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Aftercooler Engine | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 32 | 90002623 | A1 | 1000080588 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-AFTER | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-AFTER90002623
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Electrical Harness | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 48 | 90010000 | 1 | 1000080070 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -ELCTLV-HARNS | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ELCTLV-HARNS90010000
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Output Drive Shaft Unis | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 8 | 90033264 | A1 | 1000333929 | 12.06.2026 | 7000 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT01 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT0190033264
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Trans Input Drive Shaft Unis | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 8 | 90033267 | A1 | 1000333931 | 12.06.2026 | 7000 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT02 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT0290033267
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Service Brake LHF | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 36 | 90002640 | A1 | 1000028660 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLF | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLF90002640
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Service Brake RHF | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 36 | 90002640 | A1 | 1000028661 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRF | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRF90002640
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Service Brake LHR | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 50 | 90004548 | 1 | 1000028662 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLR90004548
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Service Brake RHR | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 50 | 90004548 | 1 | 1000028663 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRR90004548
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Brake Slack Adjuster LH | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 4 | 90002641 | A1 | 1000085640 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACL | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACL90002641
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Brake Slack Adjuster Rear | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 4 | 90002641 | A1 | 1000085641 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACR90002641
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Hyd Pump Secondary Steering | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 12 | 90002645 | A1 | 1000028667 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -STRSYS-STEMG-SESPP | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRSYS-STEMG-SESPP90002645
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Hyd Pump Implement | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 12 | 90002646 | A1 | 1000028668 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYIMP | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYIMP90002646
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Hyd Pump Differential Lock | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 4 | 90002649 | A1 | 1000028671 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-DIFFL | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-DIFFL90002649
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Hyd Fan Motor | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 16 | 90002651 | A1 | 1000028674 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT03 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT0390002651
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Overhaul Auto Lubrication System | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 2 | 90002660 | A1 | 1000028687 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -GRSYST-ALBPP | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -GRSYST-ALBPP90002660
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Refurbish Cabin | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 12 | 90010318 | 1 | 1000085649 | 04.09.2026 | 28000 | CLB-MP-GRDR-GR021 -STRUCT-CABIN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN90010318
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Overhaul Air Conditioner | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 48 | 90017475 | 1 | 1000160709 | 02.06.2026 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN90017475
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Overhaul Drawbar Group | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 96 | 90002668 | A1 | 1000028694 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-DRWBR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-DRWBR90002668
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Blade Mounting Bracket LH | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 48 | 90002671 | A1 | 1000028696 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBL | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBL90002671
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Blade Mounting Bracket RH | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 48 | 90002671 | A1 | 1000028697 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBR90002671
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Steering System Hoses | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 24 | 90009996 | 1 | 1000080111 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-STRNG | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-STRNG90009996
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Power Train System Hoses | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 36 | 90009999 | 1 | 1000080110 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-PWTRN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-PWTRN90009999
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Replace Brake System Hoses | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 24 | 90009997 | 1 | 1000080108 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-BRKS | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-BRKS90009997
24M | MCORS | Ancillary | Force - Perth | GR021 | GR021 Repl Hydraulic System Hoses | 2026-07-24 | 2026-08-14 | 21 days | FY27 | 48 | 90009998 | 1 | 1000080109 | 12.06.2026 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-HYDSH | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-HYDSH90009998
24M | MCORS | Ancillary | Force - Perth | GR021 | MCORS Transport | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Opex Variation | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Capex Variation | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Additional Baseline Opex Ancillary Fleet | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Additional Baseline Capex Ancillary Fleet | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Minor Hosing Opex | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Major Hosing Price Variances - Capex | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Baseline Harness (Not on strategy) Capex | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Variation Opex - Corrosions/Repairs | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Capex Variation - Cab Overhaul (if applicable) | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | MCORS Site Labour Recovery - 24M | 2026-07-24 | 2026-08-14 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Transport & Unload | 2026-08-15 | 2026-08-17 | 2 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR021 | Recommissioning | 2026-08-18 | 2026-08-18 | 0.5 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 - MCORS | 2026-08-17 | 2026-09-12 | 26 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Decommissioning | 2026-08-17 | 2026-08-17 | 0.5 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Load & Transport | 2026-08-18 | 2026-08-20 | 2 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 - Baseline Scope | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Radiator Engine Cooling | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 72 | 90003332 | 1 | 1000038015 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-RADTR | 5100 | 66960 | 24511 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-RADTR90003332
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Drive Shaft | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 14 | 90033381 | A1 | 1000335066 | 03.07.2026 | 28000 | CLB-MP-DOZR-DZX025-TRNSYS | 4400 | 66960 | 13608 | CLB-MP-DOZR-DZX025-TRNSYS90033381
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Transmission | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 72 | 90003343 | 1 | 1000038026 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-TRNSYS-TRANS | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-TRNSYS-TRANS90003343
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Bevel Gear | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 96 | 90003344 | 1 | 1000038027 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-TRNSYS-TRANS-BEVEL | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-TRNSYS-TRANS-BEVEL90003344
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Final Drive LH | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 44 | 90003346 | 1 | 1000038029 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-FDRSYS-FDRLH | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-FDRSYS-FDRLH90003346
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Final Drive RH | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 44 | 90003346 | 1 | 1000038030 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-FDRSYS-FDRRH | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-FDRSYS-FDRRH90003346
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Steer Clutch & Brake Assm LH | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 32 | 90003348 | 1 | 1000038032 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-BRKSTR-SCABL | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-BRKSTR-SCABL90003348
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Steer Clutch & Brake Assm RH | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 32 | 90003348 | 1 | 1000038033 | 17.10.2026 | 14000 | CLB-MP-DOZR-DZX025-BRKSTR-SCABR | 4400 | 66960 | 11981 | CLB-MP-DOZR-DZX025-BRKSTR-SCABR90003348
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Hyd Pump Implement | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 12 | 90003349 | 1 | 1000038034 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYIPP | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYIPP90003349
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Hyd Pump Cooling Fan | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 10 | 90009272 | 1 | 1000071500 | 24.08.2026 | 7000 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYFPP | 4400 | 66960 | 5716 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYFPP90009272
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Implement Valves Hyd | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 18 | 90003350 | 1 | 1000089513 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-HYDSYS-HDCVL | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-HYDSYS-HDCVL90003350
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Hyd Oil Cooler | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 8 | 90009665 | 1 | 1000075384 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-HYDSYS-HDOCO | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-HYDSYS-HDOCO90009665
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Fan Cooling Motor Hyd | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 16 | 90003352 | 1 | 1000047859 | 24.08.2026 | 7000 | CLB-MP-DOZR-DZX025-HYDSYS-HDCFM | 4400 | 66960 | 5716 | CLB-MP-DOZR-DZX025-HYDSYS-HDCFM90003352
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Equaliser Bar | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 96 | 90010849 | 1 | 1000089523 | 14.08.2025 | 14000 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-EQUAL | 4400 | 66960 | 18368 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-EQUAL90010849
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Overhaul Pivot Shaft | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 96 | 90010854 | 1 | 1000089518 | 26.11.2026 | 21000 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-PIVOT | 4400 | 66960 | 18368 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-PIVOT90010854
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Track Frame LH | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 40 | 90010851 | 1 | 1000089538 | 23.10.2026 | 42000 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-TKFRL | 4400 | 66960 | 39919 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-TKFRL90010851
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Track Frame RH | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 40 | 90010852 | 1 | 1000089548 | 23.10.2026 | 42000 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-TKFRR | 4400 | 66960 | 39919 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-TKFRR90010852
D11T | MCORS | Ancillary | Force - Perth | DZX025 | DZX025 Repl Hood Mounts | 2026-08-21 | 2026-09-07 | 17 days | FY27 | 12 | 90010848 | 1 | 1000089498 | 04.02.2027 | 14000 | CLB-MP-DOZR-DZX025-STRUCT-PNLGU | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-STRUCT-PNLGU90010848
D11T | MCORS | Ancillary | Force - Perth | DZX025 | MCORS Transport | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Opex Variation | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Capex Variation | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Additional Baseline Opex Ancillary Fleet | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Additional Baseline Capex Ancillary Fleet | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Minor Hosing Opex | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Major Hosing Price Variances - Capex | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Baseline Harness (Not on strategy) Capex | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Variation Opex - Corrosions/Repairs | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Capex Variation - Cab Overhaul (if applicable) | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | MCORS Site Labour Recovery - D11T | 2026-08-21 | 2026-09-07 | 17 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Transport & Unload | 2026-09-08 | 2026-09-10 | 2 days | FY27
D11T | MCORS | Ancillary | Force - Perth | DZX025 | Recommissioning | 2026-09-11 | 2026-09-12 | 1 day | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 - MCORS | 2026-09-10 | 2026-10-18 | 38 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Decommissioning | 2026-09-10 | 2026-09-10 | 0.5 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Load & Transport | 2026-09-11 | 2026-09-14 | 3 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 - Baseline Scope | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Engine Cat C32 | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 398 | 90029020 | A1 | 1000289946 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -ENGINE | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -ENGINE90029020
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Radiator Engine Cooling | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 72 | 90002931 | A1 | 1000033509 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-RADTR | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-RADTR90002931
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Aftercooler Engine | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 16 | 90010216 | 1 | 1000082593 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -ENGINE-INTEX-AFTER | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -ENGINE-INTEX-AFTER90010216
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Shaft TConverter to Trans | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 6 | 90002947 | A1 | 1000268254 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT01 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0190002947
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Replace Shaft Trans to Rear Diff | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 6 | 90002948 | A1 | 1000268256 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT02 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0290002948
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Shaft Trans to Cntr Bearing | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 12 | 90002949 | A1 | 1000268258 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT03 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0390002949
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Shaft Centre Brg to Fr Diff | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 16 | 90002950 | A1 | 1000268420 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT04 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0490002950
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Front Differential | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 120 | 90002951 | A1 | 1000033520 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-FRDIF | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-FRDIF90002951
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Final Drive Position 1 | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 80 | 90002954 | A1 | 1000033523 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR01 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR0190002954
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Final Drive Position 2 | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 80 | 90002954 | A1 | 1000033524 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR02 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR0290002954
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Final Drive Position 3 | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 80 | 90002954 | A1 | 1000033525 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR03 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR0390002954
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Final Drive Position 4 | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 80 | 90002954 | A1 | 1000033526 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR04 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR0490002954
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Oil Cooler Front Axle Lube | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 24 | 90010219 | 1 | 1000082625 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC-OILCR | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC-OILCR90010219
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Brake Accumulator Front | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 6 | 90002955 | A1 | 1000033527 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM-BACCF | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM-BACCF90002955
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Brake Accumulator Rear | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 6 | 90002955 | A1 | 1000033528 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM-BACCR | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM-BACCR90002955
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Brake System Hoses | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 48 | 90013050 | A3 | 1000231967 | 09.09.2025 | 15000 | CLB-MP-DOZR-WD005 -BRKSYS-BRHLF | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -BRKSYS-BRHLF90013050
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Hoses Steering System | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 48 | 90013051 | A3 | 1000231969 | 09.09.2025 | 15000 | CLB-MP-DOZR-WD005 -STRSYS-STHLF | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRSYS-STHLF90013051
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Cylinder Steering RH | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 22 | 90002961 | A1 | 1000033534 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -STRSYS-STRCY-STCYR | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRSYS-STRCY-STCYR90002961
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Cylinder Blade Tilt LH | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 14 | 90002967 | A1 | 1000033540 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BTCYL | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BTCYL90002967
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Cylinder Blade Tilt RH | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 14 | 90002968 | A1 | 1000033541 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BTCYR | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BTCYR90002968
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Hyd & Steering Oil Cooler | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 36 | 90010218 | 1 | 1000082597 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -HYDSYS-HDOCO | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDOCO90010218
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Overhaul Auto Lubrication System | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 60 | 90002971 | A1 | 1000033544 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -GRSYST | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -GRSYST90002971
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Refurbish Operators Cabin | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 12 | 90002972 | A1 | 1000033545 | 18.12.2026 | 22000 | CLB-MP-DOZR-WD005 -STRUCT-CABIN | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRUCT-CABIN90002972
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Overhaul Airconditioner | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 48 | 90029026 | A1 | 1000289949 | 18.12.2026 | 11000 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN90029026
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Replace Hyd Pilot System Hoses | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 24 | 90013052 | A3 | 1000231924 | 09.09.2025 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHPS | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHPS90013052
854K | MCORS | Ancillary | Force - Perth | WD005 | WD005 Repl Hoses Main Hyd-Fan System | 2026-09-15 | 2026-10-12 | 27 days | FY27 | 48 | 90013053 | A3 | 1000231925 | 09.09.2025 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHMH | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHMH90013053
854K | MCORS | Ancillary | Force - Perth | WD005 | 854K Artic Overhaul | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | 854K Draft Arm Refurbishment | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | 854K Blade Refurb | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | MCORS Transport | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Opex Variation | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Capex Variation | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Additional Baseline Opex Ancillary Fleet | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Additional Baseline Capex Ancillary Fleet | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Minor Hosing Opex | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Major Hosing Price Variances - Capex | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Baseline Harness (Not on strategy) Capex | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Variation Opex - Corrosions/Repairs | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Capex Variation - Cab Overhaul (if applicable) | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | MCORS Site Labour Recovery - 854K | 2026-09-15 | 2026-10-12 | 27 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Transport & Unload | 2026-10-13 | 2026-10-16 | 3 days | FY27
854K | MCORS | Ancillary | Force - Perth | WD005 | Recommissioning | 2026-10-17 | 2026-10-18 | 1 day | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 - MCORS | 2026-09-25 | 2026-11-10 | 46 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Decommissioning | 2026-09-25 | 2026-09-26 | 1 day | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Load & Transport | 2026-09-27 | 2026-09-30 | 3 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 - Baseline Scope | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Brake System Hoses | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 48 | 90026921 | A1 | 1000271645 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -BRKSYS-BRHLF-BRKHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -BRKSYS-BRHLF-BRKHO90026921
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hyd Pump Brake Cooling | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 8 | 90002713 | A1 | 1000080043 | 26.07.2026 | 10000 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP02 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP0290002713
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Overhaul Park Brake & Centre Brg | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 36 | 90002711 | A1 | 1000087671 | 28.07.2026 | 10000 | CLB-MP-LOAD-WL264 -BRKSYS-BRPRK | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -BRKSYS-BRPRK90002711
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Electrical Harness | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 36 | 90010123 | 1 | 1000081879 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -ELCTLV-HARNS | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -ELCTLV-HARNS90010123
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Radiator Engine Cooling | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 54 | 90002682 | A1 | 1000079814 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-RADTR | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-RADTR90002682
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Thermostats | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 6 | 90021139 | 1 | 1000222576 | 06.09.2026 | 5000 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-THERM | 6000 | 67387 | 4805 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-THERM90021139
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Front Differential | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 98 | 90002707 | A1 | 1000079830 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -FDRSYS-FRDIF | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -FDRSYS-FRDIF90002707
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Cyl Bucket RH Lift | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 36 | 90017162 | A1 | 1000154659 | 17.09.2026 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYR | 6000 | 67352 | 10633 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYR90017162
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hydraulic System Hoses | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 96 | 90026922 | A1 | 1000271647 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-HYDHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-HYDHO90026922
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Pilot System Hoses | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 96 | 90009731 | 2 | 1000079860 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-PILHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-PILHO90009731
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hyd Oil Cooler | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 96 | 90002733 | A1 | 1000079850 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-HDOCO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDOCO90002733
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Reseal Tank Hyd | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 12 | 90010623 | 1 | 1000087662 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-HDTNK-HYT01 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDTNK-HYT0190010623
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hyd Valve Implement Ctrl LH | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 24 | 90010965 | 1 | 1000090191 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV-HYV01 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV-HYV0190010965
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hyd Pump Pilot & Cooling | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 12 | 90002726 | A1 | 1000079849 | 28.07.2026 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP04 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0490002726
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hyd Pilot Accumulator | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 4 | 90012174 | 1 | 1000100314 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-PACCM | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-PACCM90012174
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Main Airhoses & Valves | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 18 | 90011137 | A1 | 1000093198 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -PNEUMC-PNHLF | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -PNEUMC-PNHLF90011137
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Replace Steering System Hoses | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 96 | 90009732 | 1 | 1000079861 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STHLF-STRHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRSYS-STHLF-STRHO90009732
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Hyd Pump Steering LH | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 36 | 90002716 | A1 | 1000079840 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP01 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP0190002716
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Cyl Steering LH | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 18 | 90002721 | A1 | 1000079844 | 14.08.2026 | 12000 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYL | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYL90002721
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Reseal Steering & Brake Tank | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 36 | 90010963 | 1 | 1000090054 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STTNK | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRSYS-STTNK90010963
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Service Air Conditioner | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 24 | 90021130 | 1 | 1000222566 | 06.09.2026 | 5000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN90021130
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Operators Seat | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 4 | 90002741 | A1 | 1000103784 | 06.12.2026 | 7000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS | 6000 | 67352 | 5323 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS90002741
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Articulation Overhaul | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 360 | 90032991 | A1 | 1000330002 | 28.10.2026 | 16000 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-ARTIC | 6000 | 67352 | 14957 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-ARTIC90032991
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Rear Output Drive Shaft Unis | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 8 | 90033167 | A1 | 1000333626 | 10.08.2026 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT02 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0290033167
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Centre Output Drive Shaft | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 14 | 90033171 | A1 | 1000333627 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT03 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0390033171
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Shaft Rear PD To Cntr Brng | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 24 | 90033191 | A1 | 1000333631 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT05 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0590033191
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Gearbox Pump Drive Rear | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 434 | 90002706 | A1 | 1000079829 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR-RRPDR | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR-RRPDR90002706
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Transmission | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 74 | 90002692 | A1 | 1000079816 | 17.07.2026 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-TRANS | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-TRANS90002692
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Transmission System Hoses | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 96 | 90026923 | A1 | 1000271649 | 16.12.2025 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO90026923
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Transmission Oil Cooler | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 36 | 90002695 | A1 | 1000079818 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-TROLC | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-TROLC90002695
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Torque Converter | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 48 | 90002693 | A1 | 1000079815 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-TRQUE | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-TRQUE90002693
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Fr Frame Grease Hoses | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 24 | 90010325 | 1 | 1000105485 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -GRSYST-FFGHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -GRSYST-FFGHO90010325
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Repl Transmission Transfer Case | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 74 | 90017029 | A1 | 1000153368 | 17.07.2026 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-TRTRF | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-TRTRF90017029
994H | MCORS | Ancillary | Force - Perth | WL264 | WL264 Replace Artic Area Hyd Hosing | 2026-10-01 | 2026-11-02 | 32 days | FY27 | 6 | 90020831 | 1 | 1000220517 | 11.12.2026 | 8 Monthly | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO90020831
994H | MCORS | Ancillary | Force - Perth | WL264 | MCORS Transport | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Opex Variation | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Capex Variation | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Additional Baseline Opex Ancillary Fleet | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Additional Baseline Capex Ancillary Fleet | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Minor Hosing Opex | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Major Hosing Price Variances - Capex | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Baseline Harness (Not on strategy) Capex | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Variation Opex - Corrosions/Repairs | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Capex Variation - Cab Overhaul (if applicable) | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | MCORS Site Labour Recovery - 994H | 2026-10-01 | 2026-11-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Transport & Unload | 2026-11-03 | 2026-11-06 | 3 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL264 | Recommissioning | 2026-11-07 | 2026-11-10 | 3 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 - MCORS | 2026-11-05 | 2026-12-04 | 29.5 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Decommissioning | 2026-11-05 | 2026-11-05 | 0.5 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Load & Transport | 2026-11-06 | 2026-11-08 | 2 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 - Baseline Scope | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Engine Midlife complete | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 72 | 90015782 | 1 | 1000159873 | 21.01.2027 | 7000 | CLB-MP-GRDR-GR013 -ENGINE | 6000 | 71626 | 4169 | CLB-MP-GRDR-GR013 -ENGINE90015782
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Radiator Engine Cooling | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 38 | 90002618 | A1 | 1000028454 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-RADTR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-RADTR90002618
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Aftercooler Engine | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 32 | 90002623 | A1 | 1000080585 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-AFTER | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-AFTER90002623
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Electrical Harness | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 48 | 90010000 | 1 | 1000080067 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -ELCTLV-HARNS | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -ELCTLV-HARNS90010000
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Torque Converter | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 122 | 90002630 | A1 | 1000028457 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TRQUE | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TRQUE90002630
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Transmission | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 122 | 90002631 | A1 | 1000028458 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TRANS | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TRANS90002631
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Transmission Oil Cooler | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 6 | 90002632 | A1 | 1000028459 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TROLC | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TROLC90002632
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Pump Transmission | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 20 | 90002633 | A1 | 1000028460 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TRPMP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TRPMP90002633
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Output Drive Shaft Unis | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 8 | 90033264 | A1 | 1000333921 | 03.10.2026 | 7000 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT01 | 6000 | 71626 | 5974 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT0190033264
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Trans Input Drive Shaft Unis | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 8 | 90033267 | A1 | 1000333923 | 03.10.2026 | 7000 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT02 | 6000 | 71626 | 5974 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT0290033267
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Rear Axle Assembly | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 128 | 90030396 | A1 | 1000303549 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -FDRSYS-DIFFL | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -FDRSYS-DIFFL90030396
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Service Brake LHF | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 36 | 90002640 | A1 | 1000028468 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLF | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLF90002640
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Service Brake RHF | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 36 | 90002640 | A1 | 1000028469 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRF | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRF90002640
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Service Brake LHR | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 50 | 90004548 | 1 | 1000028470 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLR90004548
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Service Brake RHR | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 50 | 90004548 | 1 | 1000028471 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRR90004548
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Brake Slack Adjuster LH | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 4 | 90002641 | A1 | 1000085612 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACL | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACL90002641
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Brake Slack Adjuster Rear | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 4 | 90002641 | A1 | 1000085613 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACR90002641
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Hyd Pump Secondary Steering | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 12 | 90002645 | A1 | 1000028475 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -STRSYS-STEMG-SESPP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRSYS-STEMG-SESPP90002645
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Hyd Pump Steering Main | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 12 | 90002647 | A1 | 1000028477 | 11.10.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYSTP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYSTP90002647
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Hyd Pump Brake & Fan | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 12 | 90002648 | A1 | 1000028478 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-FANPP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-FANPP90002648
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Hyd Pump Differential Lock | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 4 | 90002649 | A1 | 1000028479 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-DIFFL | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-DIFFL90002649
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Hyd Fan Motor | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 16 | 90002651 | A1 | 1000028482 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT03 | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT0390002651
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Overhaul Auto Lubrication System | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 2 | 90002660 | A1 | 1000028495 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -GRSYST-ALBPP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -GRSYST-ALBPP90002660
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Refurbish Cabin | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 12 | 90010318 | 1 | 1000085645 | 29.03.2027 | 28000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN | 6000 | 71626 | 24065 | CLB-MP-GRDR-GR013 -STRUCT-CABIN90010318
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Service Major Air Conditioner | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 24 | 90017472 | 1 | 1000160700 | 21.01.2027 | 7000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN90017472
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Operators Seat | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 4 | 90002663 | A1 | 1000028497 | 13.12.2026 | 7000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS | 6000 | 71626 | 4801 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS90002663
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Axle Assembly Front | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 98 | 90002666 | A1 | 1000180091 | 03.10.2026 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-AXLES | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-AXLES90002666
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Overhaul Drawbar Group | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 96 | 90002668 | A1 | 1000028502 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-DRWBR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-DRWBR90002668
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Power Train System Hoses | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 36 | 90009999 | A1 | 1000080078 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-PWTRN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-PWTRN90009999
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Hydraulic System Hoses | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 48 | 90009998 | 1 | 1000080077 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-HYDSH | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-HYDSH90009998
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Replace Brake System Hoses | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 24 | 90009997 | 1 | 1000080076 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-BRKS | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-BRKS90009997
24M | MCORS | Ancillary | Force - Perth | GR013 | GR013 Repl Steering System Hoses | 2026-11-09 | 2026-11-30 | 21 days | FY27 | 24 | 90009996 | 1 | 1000080079 | 19.11.2026 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-STRNG | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-STRNG90009996
24M | MCORS | Ancillary | Force - Perth | GR013 | MCORS Transport | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Opex Variation | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Capex Variation | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Additional Baseline Opex Ancillary Fleet | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Additional Baseline Capex Ancillary Fleet | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Minor Hosing Opex | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Major Hosing Price Variances - Capex | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Baseline Harness (Not on strategy) Capex | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Variation Opex - Corrosions/Repairs | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Capex Variation - Cab Overhaul (if applicable) | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | MCORS Site Labour Recovery - 24M | 2026-11-09 | 2026-11-30 | 21 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Transport & Unload | 2026-12-01 | 2026-12-03 | 2 days | FY27
24M | MCORS | Ancillary | Force - Perth | GR013 | Recommissioning | 2026-12-04 | 2026-12-04 | 0.5 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 - MCORS | 2027-02-23 | 2027-04-10 | 46 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Decommissioning | 2027-02-23 | 2027-02-24 | 1 day | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Load & Transport | 2027-02-25 | 2027-02-28 | 3 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 - Baseline Scope | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Engine Midlife complete | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 170 | 90021253 | 1 | 1000222441 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -ENGINE | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -ENGINE90021253
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Transmission Charge Pump | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 12 | 90002694 | A1 | 1000029057 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-TRPMP | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -TRNSYS-TRPMP90002694
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Pump Implement LH | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90002723 | A1 | 1000029089 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP01 | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0190002723
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Pump Implement RH | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90002724 | A1 | 1000029090 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP02 | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0290002724
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Pump Implement Centre | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90002725 | A1 | 1000029091 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP03 | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0390002725
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Pump Pilot & Cooling | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 12 | 90002726 | A1 | 1000029092 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP04 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0490002726
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Auto Lube Pump | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 6 | 90002737 | A1 | 1000029100 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -GRSYST-ALBPP | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -GRSYST-ALBPP90002737
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Overhaul Air Conditioner | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 48 | 90021132 | 1 | 1000222433 | 16.01.2027 | 10000 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN90021132
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Overhaul Boom | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 96 | 90021334 | A1 | 1000223809 | 06.02.2027 | 40000 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-LIARM | 6000 | 78554 | 36970 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-LIARM90021334
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Radiator Engine Cooling | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 54 | 90002682 | A1 | 1000029053 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-RADTR | 5700 | 78554 | 16795 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-RADTR90002682
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Electrical Harness | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 36 | 90010123 | 1 | 1000081876 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -ELCTLV-HARNS | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -ELCTLV-HARNS90010123
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Transmission Oil Cooler | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 36 | 90002695 | A1 | 1000029058 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-TROLC | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -TRNSYS-TROLC90002695
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Front Drive Shaft | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 16 | 90033175 | A1 | 1000333593 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT04 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0490033175
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Front Differential | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 98 | 90002707 | A1 | 1000029070 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -FDRSYS-FRDIF | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-FRDIF90002707
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Rear Differential | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 98 | 90002708 | A1 | 1000029071 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -FDRSYS-RRDIF | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-RRDIF90002708
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Overhaul Rear Axle Trunnion | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 96 | 90002709 | A1 | 1000029072 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -FDRSYS-RRDIF-TRNON | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-RRDIF-TRNON90002709
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Reseal Brake Accumulator Front | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 12 | 90002714 | A1 | 1000257283 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -BRKSYS-BRACC-BACCF | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -BRKSYS-BRACC-BACCF90002714
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Reseal Brake Accumulator Rear | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 12 | 90002714 | A1 | 1000089008 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -BRKSYS-BRACC-BACCR | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -BRKSYS-BRACC-BACCR90002714
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Steer & Brake Oil Cooler Pump | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 8 | 90002718 | A1 | 1000029084 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP03 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP0390002718
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Steering Hyd Pump Secondary | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 8 | 90002719 | A1 | 1000029085 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP04 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP0490002719
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Reseal Steering & Brake Tank | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 36 | 90010963 | 1 | 1000090051 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STTNK | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRSYS-STTNK90010963
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Reseal Tank Hyd | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 12 | 90010623 | 1 | 1000087659 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -HYDSYS-HDTNK-HYT01 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HDTNK-HYT0190010623
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Valve Implement Ctrl LH | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90010965 | 1 | 1000090185 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -HYDSYS-HDVLV-HYV01 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HDVLV-HYV0190010965
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Pilot Accumulator | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 4 | 90012174 | 1 | 1000100311 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -HYDSYS-PACCM | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-PACCM90012174
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Main Airhoses & Valves | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 18 | 90011137 | A1 | 1000093195 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -PNEUMC-PNHLF |  |  |  | CLB-MP-LOAD-WL026 -PNEUMC-PNHLF90011137
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Steering Neutralizer Valves | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 6 | 90002720 | A1 | 1000076055 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STNVS | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRSYS-STNVS90002720
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Brake System Hoses | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 48 | 90026921 | A1 | 1000271627 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -BRKSYS-BRHLF-BRKHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -BRKSYS-BRHLF-BRKHO90026921
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hydraulic System Hoses | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 96 | 90026922 | A1 | 1000271629 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-HYDHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-HYDHO90026922
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Pilot System Hoses | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 96 | 90009731 | 1 | 1000076482 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-PILHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-PILHO90009731
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Replace Steering System Hoses | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 96 | 90009732 | 1 | 1000076483 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STHLF-STRHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRSYS-STHLF-STRHO90009732
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Fr Frame Grease Hoses | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90010326 | 1 | 1000105482 | 17.02.2027 | 20000 | CLB-MP-LOAD-WL026 -GRSYST-FFGHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -GRSYST-FFGHO90010326
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Hyd Pump Steering LH | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 36 | 90002716 | A1 | 1000029082 | 21.02.2027 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP01 | 6000 | 78554 | 16733 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP0190002716
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Cyl Lift LH High Lift | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 40 | 90002727 | A1 | 1000029093 | 23.01.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLL | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLL90002727
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Rr PDrv Drive Shaft Ctr Brg | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 8 | 90033193 | A1 | 1000333596 | 07.04.2027 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT05 | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0590033193
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Fr Pump Drv Shaft Unis | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 8 | 90033190 | A1 | 1000333598 | 07.04.2027 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT06 | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0690033190
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Centre Bearing Upper Shaft | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90002702 | A1 | 1000029065 | 07.04.2027 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-UCTRB | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-UCTRB90002702
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Overhaul Park Brake & Centre Brg | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 36 | 90002711 | A1 | 1000087668 | 09.05.2027 | 10000 | CLB-MP-LOAD-WL026 -BRKSYS-BRPRK | 6000 | 78554 | 5453 | CLB-MP-LOAD-WL026 -BRKSYS-BRPRK90002711
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Cyl Steering LH | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 18 | 90002721 | A1 | 1000029087 | 10.05.2027 | 12000 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYL | 6000 | 78554 | 7440 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYL90002721
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Trans System Hoses Midlife | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 24 | 90026915 | A1 | 1000271632 | 14.05.2027 | 8000 | CLB-MP-LOAD-WL026 -TRNSYS-TRHLF-TRNHO | 6000 | 78554 | 19377 | CLB-MP-LOAD-WL026 -TRNSYS-TRHLF-TRNHO90026915
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Gearbox Pump Drive Front | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 74 | 90002705 | A1 | 1000029068 | 15.06.2027 | 16000 | CLB-MP-LOAD-WL026 -TRNSYS-PMPDR-FRPDR | 6000 | 78554 | 10856 | CLB-MP-LOAD-WL026 -TRNSYS-PMPDR-FRPDR90002705
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Replace Artic Area Hyd Hosing | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 6 | 90020831 | 1 | 1000220520 | 18.06.2027 | 8 Monthly | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO90020831
994H | MCORS | Ancillary | Force - Perth | WL026 | WL026 Repl Ctr Output Drive Shaft Unis | 2027-03-01 | 2027-04-02 | 32 days | FY27 | 8 | 90033173 | A1 | 1000333592 | 23.06.2027 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT03 | 6000 | 78554 | 24710 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0390033173
994H | MCORS | Ancillary | Force - Perth | WL026 | MCORS Transport | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Opex Variation | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Capex Variation | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Additional Baseline Opex Ancillary Fleet | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Additional Baseline Capex Ancillary Fleet | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Minor Hosing Opex | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Major Hosing Price Variances - Capex | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Baseline Harness (Not on strategy) Capex | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Variation Opex - Corrosions/Repairs | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Capex Variation - Cab Overhaul (if applicable) | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | MCORS Site Labour Recovery - 994H | 2027-03-01 | 2027-04-02 | 32 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Transport & Unload | 2027-04-03 | 2027-04-06 | 3 days | FY27
994H | MCORS | Ancillary | Force - Perth | WL026 | Recommissioning | 2027-04-07 | 2027-04-10 | 3 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | GR102 - MCORS | 2027-03-30 | 2027-04-24 | 25.5 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Decommissioning | 2027-03-30 | 2027-03-30 | 0.5 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Load & Transport | 2027-03-31 | 2027-04-02 | 2 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | GR102 - Baseline Scope | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Engine Cat C13 Acert | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 154 | 90015725 | 1 | 1000269621 | 23.04.2027 | 14000 | CLB-MP-GRDR-GR102 -ENGINE | 4000 | 51814 | 11096 | CLB-MP-GRDR-GR102 -ENGINE90015725
16M | MCORS | Ancillary | Mader | GR102 | GR102 Replace High Risk Hoses | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 6 | 90021797 | 1 | 1000269639 | 23.04.2027 | 7000 | CLB-MP-GRDR-GR102 -ENGINE | 4000 | 51814 | 11096 | CLB-MP-GRDR-GR102 -ENGINE90021797
16M | MCORS | Ancillary | Mader | GR102 | GR102 Air Conditioner Overhaul | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 48 | 90017477 | 1 | 1000269637 | 23.04.2027 | 14000 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN90017477
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Brake System Hoses | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 24 | 90009928 | 1 | 1000091025 | 23.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-BRKS | 4000 | 51814 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-BRKS90009928
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Radiator Engine Cooling | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 36 | 90002444 | A1 | 1000090989 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-RADTR | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-RADTR90002444
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Electrical Harness | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 36 | 90009994 | 1 | 1000091038 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -ELCTLV-HARNS | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -ELCTLV-HARNS90009994
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Drive Shaft Unis | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 6 | 90033281 | A1 | 1000333783 | 24.04.2027 | 7000 | CLB-MP-GRDR-GR102 -TRNSYS | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -TRNSYS90033281
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Transmission | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 98 | 90002448 | A1 | 1000090993 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -TRNSYS-TRANS | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -TRNSYS-TRANS90002448
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Differential | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 106 | 90002451 | A1 | 1000090994 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -FDRSYS-DIFFL | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -FDRSYS-DIFFL90002451
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Pump Brake & Hyd Fan | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 6 | 90002457 | A1 | 1000090999 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -BRKSYS-BRPMP | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -BRKSYS-BRPMP90002457
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Hyd Pump Implement & Steer | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 16 | 90002460 | A1 | 1000091003 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HYDPP-HYISP | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HYDPP-HYISP90002460
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Implement Ctrl Valve Front | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 12 | 90002461 | A1 | 1000091004 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL-FRONT | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL-FRONT90002461
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Implement Control Valve Rear | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 12 | 90002462 | A1 | 1000091005 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL-REAR1 | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL-REAR190002462
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Hyd Motor Fan Hyd Cooler | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 16 | 90002464 | A1 | 1000091006 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HDMOT-MOFAN | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HDMOT-MOFAN90002464
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Auto Lube Pump | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 4 | 90009937 | 1 | 1000091036 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -GRSYST-ALBPP | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -GRSYST-ALBPP90009937
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Gearbox Circle Drive | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 14 | 90002481 | A1 | 1000091012 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -STRUCT-CIRCL-CDRBX | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-CIRCL-CDRBX90002481
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Drawbar Group | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 48 | 90002480 | A1 | 1000091018 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -STRUCT-DRWBR | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-DRWBR90002480
16M | MCORS | Ancillary | Mader | GR102 | GR102 Overhaul Ripper Assy | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 48 | 90002484 | A1 | 1000091020 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -STRUCT-RIPPR | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-RIPPR90002484
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Hydraulic System Hoses | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 48 | 90009930 | 1 | 1000091028 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-HYDSH | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-HYDSH90009930
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Powertrain System Hoses | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 36 | 90009931 | 1 | 1000091030 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-PWTRN | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-PWTRN90009931
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Tandem Chain LHF | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129917 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNLF | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNLF90015334
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Tandem Chain RHF | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129935 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNRF | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNRF90015334
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Tandem Chain LHR | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129952 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNLR | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNLR90015334
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Tandem Chain RHR | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129969 | 24.04.2027 | 14000 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNRR | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNRR90015334
16M | MCORS | Ancillary | Mader | GR102 | GR102 Repl Operators Seat | 2027-04-03 | 2027-04-20 | 17 days | FY27 | 4 | 90002475 | A1 | 1000107180 | 19.06.2027 | 7000 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-SEATS | 4000 | 51804 | 3348 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-SEATS90002475
16M | MCORS | Ancillary | Mader | GR102 | MCORS Transport | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Opex Variation | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Capex Variation | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Additional Baseline Opex Ancillary Fleet | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Additional Baseline Capex Ancillary Fleet | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Major Hosing Price Variances - Capex | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Baseline Harness (Not on strategy) Capex | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Variation Opex - Corrosions/Repairs | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Capex Variation - Cab Overhaul (if applicable) | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | MCORS Site Labour Recovery - 16M | 2027-04-03 | 2027-04-20 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Transport & Unload | 2027-04-21 | 2027-04-23 | 2 days | FY27
16M | MCORS | Ancillary | Mader | GR102 | Recommissioning | 2027-04-24 | 2027-04-24 | 0.5 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 - MCORS | 2027-04-11 | 2027-05-07 | 26 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Decommissioning | 2027-04-11 | 2027-04-11 | 0.5 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Load & Transport | 2027-04-12 | 2027-04-14 | 2 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 - Baseline Scope | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Steer Clutch & Brake Assm LH | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 32 | 90000313 | 1 | 1000016616 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -BRKSTR-SCABL | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -BRKSTR-SCABL90000313
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Steer Clutch & Brake Assm RH | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 32 | 90000313 | 1 | 1000016617 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -BRKSTR-SCABR | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -BRKSTR-SCABR90000313
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Engine Cat C27 | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 126 | 90015849 | 1 | 1000159427 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -ENGINE | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -ENGINE90015849
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Radiator Engine Cooling | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 48 | 90000307 | A1 | 1000016607 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-RADTR | 5100 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-RADTR90000307
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Aftercooler Engine | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 8 | 90010841 | 1 | 1000089370 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -ENGINE-INTEX-AFTER | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -ENGINE-INTEX-AFTER90010841
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Fan Cooling Motor Hyd | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 16 | 90002094 | 1 | 1000069920 | 27.05.2027 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCFM | 4700 | 70636 | 5309 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCFM90002094
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Cylinder Blade Lift RH | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 18 | 90000287 | 1 | 1000255507 | 01.04.2027 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYR | 4700 | 70636 | 6041 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYR90000287
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Hyd Oil Cooler | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 10 | 90009664 | 1 | 1000075350 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDOCO | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -HYDSYS-HDOCO90009664
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Ovhl Hydraulic & Fuel Tank | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 48 | 90010842 | 1 | 1000089414 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDTNK | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -HYDSYS-HDTNK90010842
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Hyd Pump Implement | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 10 | 90000301 | 1 | 1000016618 | 14.04.2027 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HYDPP-HYIPP | 4700 | 70636 | 5309 | CLB-MP-DOZR-DZ011 -HYDSYS-HYDPP-HYIPP90000301
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Overhaul Air Conditioner | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 48 | 90017468 | 1 | 1000160688 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN90017468
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Replace Operators Seat | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 8 | 90000318 | 1 | 1000089354 | 26.04.2027 | 6000 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-SEATS | 4700 | 70636 | 2639 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-SEATS90000318
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Transmission | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 48 | 90000308 | 1 | 1000016611 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -TRNSYS-TRANS | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -TRNSYS-TRANS90000308
D10T | MCORS | Ancillary | Force - Perth | DZ011 | DZ011 Repl Torque Converter | 2027-04-15 | 2027-05-02 | 17 days | FY27 | 60 | 90000309 | 1 | 1000016609 | 30.06.2027 | 18000 | CLB-MP-DOZR-DZ011 -TRNSYS-TRQUE | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -TRNSYS-TRQUE90000309
D10T | MCORS | Ancillary | Force - Perth | DZ011 | MCORS Transport | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Opex Variation | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Capex Variation | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Additional Baseline Opex Ancillary Fleet | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Additional Baseline Capex Ancillary Fleet | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Minor Hosing Opex | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Major Hosing Price Variances - Capex | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Baseline Harness (Not on strategy) Capex | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Variation Opex - Corrosions/Repairs | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Capex Variation - Cab Overhaul (if applicable) | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | MCORS Site Labour Recovery - D10T | 2027-04-15 | 2027-05-02 | 17 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Transport & Unload | 2027-05-03 | 2027-05-05 | 2 days | FY27
D10T | MCORS | Ancillary | Force - Perth | DZ011 | Recommissioning | 2027-05-06 | 2027-05-07 | 1 day | FY27
16M | MCORS | Ancillary | Mader | GR017 | GR017 - MCORS | 2027-04-20 | 2027-05-15 | 25.5 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Decommissioning | 2027-04-20 | 2027-04-20 | 0.5 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Load & Transport | 2027-04-21 | 2027-04-23 | 2 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | GR017 - Baseline Scope | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | GR017 Air Conditioner Minor Service | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 12 | 90019351 | 1 | 1000196835 | 21.04.2027 | 3500 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN90019351
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Radiator Engine Cooling | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 36 | 90002444 | A1 | 1000027526 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-RADTR | 4600 | 54668 | 25062 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-RADTR90002444
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Electrical Harness | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 36 | 90009994 | 1 | 1000080063 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -ELCTLV-HARNS | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -ELCTLV-HARNS90009994
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Drive Shaft Unis | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 6 | 90033281 | A1 | 1000333755 | 29.04.2027 | 7000 | CLB-MP-GRDR-GR017 -TRNSYS | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -TRNSYS90033281
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Differential | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 106 | 90002451 | A1 | 1000027533 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -FDRSYS-DIFFL | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -FDRSYS-DIFFL90002451
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Hyd Pump Implement & Steer | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 16 | 90002460 | A1 | 1000027546 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HYDPP-HYISP | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HYDPP-HYISP90002460
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Implement Ctrl Valve Front | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 12 | 90002461 | A1 | 1000027547 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDCVL-FRONT | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HDCVL-FRONT90002461
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Implement Control Valve Rear | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 12 | 90002462 | A1 | 1000027548 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDCVL-REAR1 | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HDCVL-REAR190002462
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Drawbar Group | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 48 | 90002480 | A1 | 1000078298 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -STRUCT-DRWBR | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -STRUCT-DRWBR90002480
16M | MCORS | Ancillary | Mader | GR017 | GR017 Overhaul Ripper Assy | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 48 | 90002484 | A1 | 1000027572 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -STRUCT-RIPPR | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -STRUCT-RIPPR90002484
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Brake System Hoses | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 24 | 90009928 | 1 | 1000078242 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-BRKS | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-BRKS90009928
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Hydraulic System Hoses | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 48 | 90009930 | 1 | 1000078262 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-HYDSH | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-HYDSH90009930
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Steering System Hoses | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 24 | 90009932 | 1 | 1000078257 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-STRNG | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-STRNG90009932
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Tandem Chain LHF | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129922 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNLF | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNLF90015334
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Tandem Chain RHF | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129940 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNRF | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNRF90015334
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Tandem Chain LHR | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129957 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNLR | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNLR90015334
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Tandem Chain RHR | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 18 | 90015334 | 1 | 1000129974 | 29.04.2027 | 14000 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNRR | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNRR90015334
16M | MCORS | Ancillary | Mader | GR017 | GR017 Refurbish Cabin | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 12 | 90009935 | 1 | 1000078293 | 01.05.2027 | 28000 | CLB-MP-GRDR-GR017 -STRUCT-CABIN | 4000 | 54668 | 25062 | CLB-MP-GRDR-GR017 -STRUCT-CABIN90009935
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Brake Assy RHF | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 36 | 90002455 | A1 | 1000027539 | 23.06.2027 | 8000 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRF | 4000 | 54668 | 4479 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRF90002455
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Brake Assy RHR | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 36 | 90002456 | A1 | 1000027541 | 23.06.2027 | 8000 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRR | 4000 | 54668 | 4479 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRR90002456
16M | MCORS | Ancillary | Mader | GR017 | GR017 Repl Operators Seat | 2027-04-24 | 2027-05-11 | 17 days | FY27 | 4 | 90002475 | A1 | 1000027562 | 23.08.2027 | 7000 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-SEATS | 4000 | 54668 | 2814 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-SEATS90002475
16M | MCORS | Ancillary | Mader | GR017 | MCORS Transport | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Opex Variation | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Capex Variation | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Additional Baseline Opex Ancillary Fleet | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Additional Baseline Capex Ancillary Fleet | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Major Hosing Price Variances - Capex | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Baseline Harness (Not on strategy) Capex | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Variation Opex - Corrosions/Repairs | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Capex Variation - Cab Overhaul (if applicable) | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | MCORS Site Labour Recovery - 16M | 2027-04-24 | 2027-05-11 | 17 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Transport & Unload | 2027-05-12 | 2027-05-14 | 2 days | FY27
16M | MCORS | Ancillary | Mader | GR017 | Recommissioning | 2027-05-15 | 2027-05-15 | 0.5 days | FY27
| MCORS |  |  |  | FY28 - MCORS | 2027-07-01 | 2028-06-30 | 365 days | FY28
| MCORS | Ancillary | Various |  | ANCILLARY | 2027-07-01 | 2028-06-30 | 365 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | WL027 - MCORS (EOL - 05/2026) | 2027-07-01 | 2027-08-16 | 46 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Decommissioning | 2027-07-01 | 2027-07-02 | 1 day | FY28
994H | MCORS | Ancillary | TBA | WL027 | Load & Transport | 2027-07-03 | 2027-07-06 | 3 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | WL027 - Baseline Scope | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Engine Cat 3516B | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 500 | 90021152 | 1 | 1000222457 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -ENGINE | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -ENGINE90021152
994H | MCORS | Ancillary | TBA | WL027 | WL027 Overhaul Engine Prelube | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 10 | 90021219 | 1 | 1000222465 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -ENGINE-LUBSY-PREPP | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -ENGINE-LUBSY-PREPP90021219
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Radiator Engine Cooling | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 54 | 90002682 | A1 | 1000029118 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-RADTR | 5700 | 81297 | 15300 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-RADTR90002682
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Electrical Harness | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 36 | 90010123 | 1 | 1000081877 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -ELCTLV-HARNS | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -ELCTLV-HARNS90010123
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Torque Converter | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 48 | 90002693 | A1 | 1000029120 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-TRQUE | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-TRQUE90002693
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Transmission Oil Cooler | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 36 | 90002695 | A1 | 1000029123 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-TROLC | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-TROLC90002695
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Gearbox Pump Drive Rear | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 434 | 90002706 | A1 | 1000029134 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-RRPDR | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-RRPDR90002706
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Front Drive Shaft | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 16 | 90033175 | A1 | 1000333605 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT04 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0490033175
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Shaft Rear PD To Cntr Brng | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 24 | 90033191 | A1 | 1000333607 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT05 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0590033191
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Front Differential | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 98 | 90002707 | A1 | 1000029135 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -FDRSYS-FRDIF | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -FDRSYS-FRDIF90002707
994H | MCORS | Ancillary | TBA | WL027 | WL027 Reseal Brake Accumulator Front | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 12 | 90002714 | A1 | 1000257284 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC-BACCF | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC-BACCF90002714
994H | MCORS | Ancillary | TBA | WL027 | WL027 Reseal Brake Accumulator Rear | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 12 | 90002714 | A1 | 1000089009 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC-BACCR | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC-BACCR90002714
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Hyd Pump Steering RH | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 36 | 90002717 | A1 | 1000029148 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP02 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP0290002717
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Steer & Brake Oil Cooler Pump | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 8 | 90002718 | A1 | 1000029149 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP03 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP0390002718
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Steering Hyd Pump Secondary | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 8 | 90002719 | A1 | 1000029150 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP04 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP0490002719
994H | MCORS | Ancillary | TBA | WL027 | WL027 Reseal Steering & Brake Tank | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 36 | 90010963 | 1 | 1000090052 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STTNK | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRSYS-STTNK90010963
994H | MCORS | Ancillary | TBA | WL027 | WL027 Reseal Tank Hyd | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 12 | 90010623 | 1 | 1000087660 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-HDTNK-HYT01 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDTNK-HYT0190010623
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Hyd Oil Cooler | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 96 | 90002733 | A1 | 1000029162 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-HDOCO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDOCO90002733
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Hyd Valve Implement Ctrl LH | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 24 | 90010965 | 1 | 1000090187 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-HDVLV-HYV01 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDVLV-HYV0190010965
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Hyd Valve Implement Ctrl RH | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 24 | 90010966 | 1 | 1000090188 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-HDVLV-HYV02 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDVLV-HYV0290010966
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Hyd Pilot Accumulator | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 4 | 90012174 | 1 | 1000100312 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-PACCM | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-PACCM90012174
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Main Airhoses & Valves | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 18 | 90011137 | A1 | 1000093196 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -PNEUMC-PNHLF |  |  |  | CLB-MP-LOAD-WL027 -PNEUMC-PNHLF90011137
994H | MCORS | Ancillary | TBA | WL027 | WL027 Overhaul Air Conditioner | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 48 | 90021132 | 1 | 1000222455 | 28.05.2027 | 10000 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN90021132
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Steering Neutralizer Valves | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 6 | 90002720 | A1 | 1000076056 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STNVS | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRSYS-STNVS90002720
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Brake System Hoses | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 48 | 90026921 | A1 | 1000271633 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -BRKSYS-BRHLF-BRKHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -BRKSYS-BRHLF-BRKHO90026921
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Hydraulic System Hoses | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 96 | 90026922 | A1 | 1000271635 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-HYDHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-HYDHO90026922
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Pilot System Hoses | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 96 | 90009731 | 2 | 1000076487 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-PILHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-PILHO90009731
994H | MCORS | Ancillary | TBA | WL027 | WL027 Replace Steering System Hoses | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 96 | 90009732 | 1 | 1000076488 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STHLF-STRHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRSYS-STHLF-STRHO90009732
994H | MCORS | Ancillary | TBA | WL027 | WL027 Fr Frame Grease Hoses | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 24 | 90010326 | 1 | 1000105483 | 28.05.2027 | 20000 | CLB-MP-LOAD-WL027 -GRSYST-FFGHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -GRSYST-FFGHO90010326
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Centre Bearing Upper Shaft | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 24 | 90002702 | A1 | 1000029130 | 05.06.2027 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-UCTRB | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-UCTRB90002702
994H | MCORS | Ancillary | TBA | WL027 | WL027 Adjust 250hr Initial Valve Set | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 24 | 90021246 | 1 | 1000222452 | 12.06.2027 | 250 | CLB-MP-LOAD-WL027 -ENGINE | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -ENGINE90021246
994H | MCORS | Ancillary | TBA | WL027 | WL027 Overhaul Park Brake & Centre Brg | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 36 | 90002711 | A1 | 1000087669 | 16.07.2027 | 10000 | CLB-MP-LOAD-WL027 -BRKSYS-BRPRK | 6000 | 81297 | 4486 | CLB-MP-LOAD-WL027 -BRKSYS-BRPRK90002711
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Cyl Lift RH High Lift | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 40 | 90002727 | A1 | 1000029159 | 19.08.2027 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLR | 6000 | 81297 | 3932 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLR90002727
994H | MCORS | Ancillary | TBA | WL027 | WL027 Repl Cyl Bucket RH High Lift | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 36 | 90017977 | A1 | 1000029161 | 19.08.2027 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYR | 6000 | 81297 | 3926 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYR90017977
994H | MCORS | Ancillary | TBA | WL027 | WL027 Replace Artic Area Hyd Hosing | 2027-07-07 | 2027-08-08 | 32 days | FY28 | 6 | 90020831 | 1 | 1000220521 | 25.08.2027 | 8 Monthly | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO90020831
994H | MCORS | Ancillary | TBA | WL027 | MCORS Transport | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Opex Variation | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Capex Variation | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Additional Baseline Opex Ancillary Fleet | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Additional Baseline Capex Ancillary Fleet | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Minor Hosing Opex | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Major Hosing Price Variances - Capex | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Baseline Harness (Not on strategy) Capex | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Variation Opex - Corrosions/Repairs | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Capex Variation - Cab Overhaul (if applicable) | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | MCORS Site Labour Recovery - 994H | 2027-07-07 | 2027-08-08 | 32 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Transport & Unload | 2027-08-09 | 2027-08-12 | 3 days | FY28
994H | MCORS | Ancillary | TBA | WL027 | Recommissioning | 2027-08-13 | 2027-08-16 | 3 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 - MCORS (EOL - 11/2025) | 2027-09-05 | 2027-10-01 | 26 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Decommissioning | 2027-09-05 | 2027-09-05 | 0.5 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Load & Transport | 2027-09-06 | 2027-09-08 | 2 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 - Baseline Scope | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Radiator Engine Cooling | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 72 | 90003332 | 1 | 1000037963 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-RADTR | 5100 | 59280 | 9271 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-RADTR90003332
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Aftercooler Engine | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 8 | 90010846 | 1 | 1000089491 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-ENGINE-INTEX-AFTER | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-ENGINE-INTEX-AFTER90010846
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Drive Shaft | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 14 | 90033381 | A1 | 1000335062 | 04.09.2027 | 28000 | CLB-MP-DOZR-DZX023-TRNSYS | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-TRNSYS90033381
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Torque Converter | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 72 | 90003342 | 1 | 1000037973 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-TRNSYS-TRQUE | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-TRNSYS-TRQUE90003342
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Bevel Gear | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 96 | 90003344 | 1 | 1000037975 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-TRNSYS-TRANS-BEVEL | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-TRNSYS-TRANS-BEVEL90003344
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Transmission Oil Cooler | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 14 | 90009667 | 1 | 1000075392 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-TRNSYS-TROLC | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-TRNSYS-TROLC90009667
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Final Drive LH | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 44 | 90003346 | 1 | 1000037977 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-FDRSYS-FDRLH | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-FDRSYS-FDRLH90003346
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Valve Hyd Steering | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 4 | 90003347 | 1 | 1000037979 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-BRKSTR-STVLV | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-BRKSTR-STVLV90003347
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Steer Clutch & Brake Assm LH | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 32 | 90003348 | 1 | 1000037980 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-BRKSTR-SCABL | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-BRKSTR-SCABL90003348
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Steer Clutch & Brake Assm RH | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 32 | 90003348 | 1 | 1000037981 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-BRKSTR-SCABR | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-BRKSTR-SCABR90003348
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Hyd Pump Implement | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 12 | 90003349 | 1 | 1000037982 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYIPP | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYIPP90003349
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Implement Valves Hyd | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 18 | 90003350 | 1 | 1000089511 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-HYDSYS-HDCVL | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-HYDSYS-HDCVL90003350
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Equaliser Bar | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 96 | 90010849 | 1 | 1000089521 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-EQUAL | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-EQUAL90010849
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Hood Mounts | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 12 | 90010848 | 1 | 1000089496 | 04.09.2027 | 14000 | CLB-MP-DOZR-DZX023-STRUCT-PNLGU | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-STRUCT-PNLGU90010848
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Engine Midlife Complete | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 130 | 90029037 | A1 | 1000290168 | 27.09.2027 | 7000 | CLB-MP-DOZR-DZX023-ENGINE | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-ENGINE90029037
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 T-Conv Trans Charge Pump Replace | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 10 | 90037704 | A1 | 1000374088 | 27.09.2027 | 14000 | CLB-MP-DOZR-DZX023-TRNSYS-TRPMP | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-TRNSYS-TRPMP90037704
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Hyd Pump Cooling Fan | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 10 | 90009272 | 1 | 1000071478 | 27.09.2027 | 7000 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYFPP | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYFPP90009272
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Fan Cooling Motor Hyd | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 16 | 90003352 | 1 | 1000037985 | 27.09.2027 | 7000 | CLB-MP-DOZR-DZX023-HYDSYS-HDCFM | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-HYDSYS-HDCFM90003352
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Service Airconditroner Major | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 24 | 90029040 | A1 | 1000290170 | 27.09.2027 | 7000 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN90029040
D11T | MCORS | Ancillary | TBA | DZX023 | DZX023 Repl Final Drive RH | 2027-09-09 | 2027-09-26 | 17 days | FY28 | 44 | 90003346 | 1 | 1000037978 | 17.12.2027 | 14000 | CLB-MP-DOZR-DZX023-FDRSYS-FDRRH | 4400 | 59280 | 8033 | CLB-MP-DOZR-DZX023-FDRSYS-FDRRH90003346
D11T | MCORS | Ancillary | TBA | DZX023 | MCORS Transport | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Opex Variation | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Capex Variation | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Additional Baseline Opex Ancillary Fleet | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Additional Baseline Capex Ancillary Fleet | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Minor Hosing Opex | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Major Hosing Price Variances - Capex | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Baseline Harness (Not on strategy) Capex | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Variation Opex - Corrosions/Repairs | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Capex Variation - Cab Overhaul (if applicable) | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | MCORS Site Labour Recovery - D11T | 2027-09-09 | 2027-09-26 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Transport & Unload | 2027-09-27 | 2027-09-29 | 2 days | FY28
D11T | MCORS | Ancillary | TBA | DZX023 | Recommissioning | 2027-09-30 | 2027-10-01 | 1 day | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 - MCORS (EOL - 07/2027) | 2027-09-20 | 2027-10-16 | 26 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Decommissioning | 2027-09-20 | 2027-09-20 | 0.5 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Load & Transport | 2027-09-21 | 2027-09-23 | 2 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 - Baseline Scope | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Steer Clutch & Brake Assm LH | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 32 | 90000313 | 1 | 1000020588 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -BRKSTR-SCABL | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -BRKSTR-SCABL90000313
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Steer Clutch & Brake Assm RH | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 32 | 90000313 | 1 | 1000020589 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -BRKSTR-SCABR | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -BRKSTR-SCABR90000313
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Engine Cat C27 | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 126 | 90015849 | 1 | 1000159571 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -ENGINE | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -ENGINE90015849
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Rad Engine Cooling SN 529 UP | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 48 | 90000307 | A1 | 1000020580 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-RADTR | 5100 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-RADTR90000307
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Aftercooler Engine | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 8 | 90010841 | 1 | 1000089377 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -ENGINE-INTEX-AFTER | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -ENGINE-INTEX-AFTER90010841
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Hyd Oil Cooler | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 10 | 90009664 | 1 | 1000075357 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -HYDSYS-HDOCO | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -HYDSYS-HDOCO90009664
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Ovhl Hydraulic & Fuel Tank | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 48 | 90010842 | 1 | 1000089421 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -HYDSYS-HDTNK | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -HYDSYS-HDTNK90010842
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Hyd Pump Cooling Fan | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 16 | 90004952 | 1 | 1000069907 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -HYDSYS-HYDPP-HYFPP | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -HYDSYS-HYDPP-HYFPP90004952
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Overhaul Air Conditioner | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 48 | 90017468 | 1 | 1000160695 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN90017468
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Equaliser Bar | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 96.5 | 90002097 | 1 | 1000089441 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-EQUAL | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-EQUAL90002097
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Transmission | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 48 | 90000308 | 1 | 1000020583 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -TRNSYS-TRANS | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -TRNSYS-TRANS90000308
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Pump Trans & TCon Charge | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 10 | 90000302 | 1 | 1000020585 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -TRNSYS-TRPMP | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -TRNSYS-TRPMP90000302
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Torque Converter | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 60 | 90000309 | 1 | 1000020582 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -TRNSYS-TRQUE | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -TRNSYS-TRQUE90000309
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Replace Operators Seat | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 8 | 90000318 | 1 | 1000089363 | 18.11.2027 | 6000 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS | 4700 | 66933 | 5461 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS90000318
D10T | MCORS | Ancillary | TBA | DZ018 | DZ018 Repl Hyd Pump Implement | 2027-09-24 | 2027-10-11 | 17 days | FY28 | 10 | 90000301 | 1 | 1000020590 | 28.11.2027 | 9000 | CLB-MP-DOZR-DZ018 -HYDSYS-HYDPP-HYIPP | 4700 | 66933 | 2856 | CLB-MP-DOZR-DZ018 -HYDSYS-HYDPP-HYIPP90000301
D10T | MCORS | Ancillary | TBA | DZ018 | MCORS Transport | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Opex Variation | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Capex Variation | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Additional Baseline Opex Ancillary Fleet | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Additional Baseline Capex Ancillary Fleet | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Minor Hosing Opex | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Major Hosing Price Variances - Capex | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Baseline Harness (Not on strategy) Capex | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Variation Opex - Corrosions/Repairs | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Capex Variation - Cab Overhaul (if applicable) | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | MCORS Site Labour Recovery - D10T | 2027-09-24 | 2027-10-11 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Transport & Unload | 2027-10-12 | 2027-10-14 | 2 days | FY28
D10T | MCORS | Ancillary | TBA | DZ018 | Recommissioning | 2027-10-15 | 2027-10-16 | 1 day | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 - MCORS (EOL - 01/2036) | 2027-09-25 | 2027-10-21 | 26 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Decommissioning | 2027-09-25 | 2027-09-25 | 0.5 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Load & Transport | 2027-09-26 | 2027-09-28 | 2 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 - Baseline Scope | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Steer Clutch & Brake Assm LH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 32 | 90018830 | A1 | 1000189113 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-BRKSTR-SCABL | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-BRKSTR-SCABL90018830
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Steer Clutch & Brake Assm RH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 32 | 90018830 | A1 | 1000189114 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-BRKSTR-SCABR | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-BRKSTR-SCABR90018830
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Engine Cat C27 | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 82 | 90018843 | A1 | 1000189127 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-ENGINE | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-ENGINE90018843
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Aftercooler Engine | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 8 | 90018836 | A1 | 1000189120 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-AFTER | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-AFTER90018836
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Wash Engine Pre Cleaners | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 2 | 90018848 | A1 | 1000189133 | 29.09.2027 | 9000 | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-AIRFL90018848
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Final Drive LH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 48 | 90018829 | A1 | 1000189111 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-FDRSYS-FDRLH | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-FDRSYS-FDRLH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Final Drive RH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 48 | 90018829 | A1 | 1000189112 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-FDRSYS-FDRRH | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-FDRSYS-FDRRH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Fan Cooling Motor Hyd | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 16 | 90018833 | A1 | 1000189117 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCFM | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCFM90018833
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Reseal Hydraulic Tank | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 48 | 90018838 | A1 | 1000189122 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-HYDSYS-HDTNK | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-HYDSYS-HDTNK90018838
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Hyd Pump Cooling Fan | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 16 | 90018832 | A1 | 1000189116 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYFPP | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYFPP90018832
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Overhaul Air Conditioner | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 48 | 90018854 | A1 | 1000189140 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN90018854
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Minor Overhaul Track Frame LH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 90 | 90033092 | A1 | 1000331947 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-TKFRL | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-TKFRL90033092
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Minor Overhaul Track Frame RH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 90 | 90033093 | A1 | 1000331949 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-TKFRR | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-TKFRR90033093
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Transmission | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 48 | 90018827 | A1 | 1000189109 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-TRNSYS-TRANS | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-TRNSYS-TRANS90018827
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Pump Trans & TCon Charge | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 10 | 90018828 | A1 | 1000189110 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-TRNSYS-TRPMP | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-TRNSYS-TRPMP90018828
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Torque Converter | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 60 | 90018826 | A1 | 1000189108 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-TRNSYS-TRQUE | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-TRNSYS-TRQUE90018826
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Drive Shaft | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 6 | 90033311 | A1 | 1000334034 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-TRNSYS-DRSHT | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-TRNSYS-DRSHT90033311
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Pump Hyd Variable Charge | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 4 | 90021620 | A1 | 1000226701 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYDVC | 4800 | 26699 | 12533 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYDVC90021620
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Pump Hyd Implement 2 | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 6 | 90021621 | A1 | 1000226711 | 29.09.2027 | 18000 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYIP2 | 4800 | 26699 | 12533 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYIP290021621
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Cylinder Blade Lift LH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 14 | 90018821 | A1 | 1000189142 | 18.12.2027 | 9000 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BLCYL | 4800 | 26747 | 2490 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BLCYL90018821
D10T2 | MCORS | Ancillary | TBA | DZ8223 | DZ8223 Repl Cylinder Blade Lift RH | 2027-09-29 | 2027-10-16 | 17 days | FY28 | 14 | 90018821 | A1 | 1000189143 | 18.12.2027 | 9000 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BLCYR | 4800 | 26747 | 1473 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BLCYR90018821
D10T2 | MCORS | Ancillary | TBA | DZ8223 | MCORS Transport | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Opex Variation | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Capex Variation | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Additional Baseline Opex Ancillary Fleet | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Additional Baseline Capex Ancillary Fleet | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Minor Hosing Opex | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Major Hosing Price Variances - Capex | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Baseline Harness (Not on strategy) Capex | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Variation Opex - Corrosions/Repairs | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Capex Variation - Cab Overhaul (if applicable) | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | MCORS Site Labour Recovery - D10T | 2027-09-29 | 2027-10-16 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Transport & Unload | 2027-10-17 | 2027-10-19 | 2 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8223 | Recommissioning | 2027-10-20 | 2027-10-21 | 1 day | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 - MCORS (EOL - 05/2024) | 2027-10-09 | 2027-11-04 | 26 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Decommissioning | 2027-10-09 | 2027-10-09 | 0.5 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Load & Transport | 2027-10-10 | 2027-10-12 | 2 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 - Baseline Scope | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Engine | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 246 | 90029036 | A1 | 1000290094 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-ENGINE | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-ENGINE90029036
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Radiator Engine Cooling | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 72 | 90003332 | 1 | 1000037911 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-RADTR | 5100 | 65875 | 7882 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-RADTR90003332
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Aftercooler Engine | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 8 | 90010846 | 1 | 1000089489 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-ENGINE-INTEX-AFTER | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-ENGINE-INTEX-AFTER90010846
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Drive Shaft | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 14 | 90033381 | A1 | 1000334898 | 21.10.2027 | 28000 | CLB-MP-DOZR-DZX021-TRNSYS | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS90033381
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Torque Converter | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 72 | 90003342 | 1 | 1000037921 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-TRNSYS-TRQUE | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TRQUE90003342
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Transmission | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 72 | 90003343 | 1 | 1000037922 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-TRNSYS-TRANS | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TRANS90003343
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Bevel Gear | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 96 | 90003344 | 1 | 1000037923 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-TRNSYS-TRANS-BEVEL | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TRANS-BEVEL90003344
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Transmission Oil Cooler | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 14 | 90009667 | 1 | 1000075390 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-TRNSYS-TROLC | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TROLC90009667
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 T-Conv Trans Charge Pump Replace | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 10 | 90037704 | A1 | 1000374084 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP90037704
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Final Drive LH | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 44 | 90003346 | 1 | 1000037925 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-FDRSYS-FDRLH | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-FDRSYS-FDRLH90003346
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Valve Hyd Steering | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 4 | 90003347 | 1 | 1000037927 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-BRKSTR-STVLV | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-BRKSTR-STVLV90003347
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Steer Clutch & Brake Assm LH | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 32 | 90003348 | 1 | 1000047856 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-BRKSTR-SCABL | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-BRKSTR-SCABL90003348
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Steer Clutch & Brake Assm RH | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 32 | 90003348 | 1 | 1000037929 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-BRKSTR-SCABR | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-BRKSTR-SCABR90003348
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Hyd Pump Implement | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 12 | 90003349 | 1 | 1000037930 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYIPP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYIPP90003349
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Hyd Pump Cooling Fan | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 10 | 90009272 | 1 | 1000071476 | 21.10.2027 | 7000 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP90009272
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Implement Valves Hyd | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 18 | 90003350 | 1 | 1000089509 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-HYDSYS-HDCVL | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HDCVL90003350
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Hyd Oil Cooler | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 8 | 90009665 | 1 | 1000075380 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-HYDSYS-HDOCO | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HDOCO90009665
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Repl Fan Cooling Motor Hyd | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 16 | 90003352 | 1 | 1000037933 | 21.10.2027 | 7000 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM90003352
D11T | MCORS | Ancillary | TBA | DZX021 | DZX021 Overhaul Airconditioner | 2027-10-13 | 2027-10-30 | 17 days | FY28 | 48 | 90029041 | A1 | 1000290098 | 21.10.2027 | 14000 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN90029041
D11T | MCORS | Ancillary | TBA | DZX021 | MCORS Transport | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Opex Variation | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Capex Variation | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Additional Baseline Opex Ancillary Fleet | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Additional Baseline Capex Ancillary Fleet | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Minor Hosing Opex | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Major Hosing Price Variances - Capex | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Baseline Harness (Not on strategy) Capex | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Variation Opex - Corrosions/Repairs | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Capex Variation - Cab Overhaul (if applicable) | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | MCORS Site Labour Recovery - D11T | 2027-10-13 | 2027-10-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Transport & Unload | 2027-10-31 | 2027-11-02 | 2 days | FY28
D11T | MCORS | Ancillary | TBA | DZX021 | Recommissioning | 2027-11-03 | 2027-11-04 | 1 day | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 - MCORS (EOL - 12/2035) | 2027-11-13 | 2027-12-09 | 26 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Decommissioning | 2027-11-13 | 2027-11-13 | 0.5 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Load & Transport | 2027-11-14 | 2027-11-16 | 2 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 - Baseline Scope | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Operators Seat | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 8 | 90018835 | A1 | 1000189168 | 04.11.2027 | 6000 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS | 4800 | 26987 | 6075 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS90018835
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Steer Clutch & Brake Assm LH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 32 | 90018830 | A1 | 1000189162 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-BRKSTR-SCABL | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-BRKSTR-SCABL90018830
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Steer Clutch & Brake Assm RH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 32 | 90018830 | A1 | 1000189163 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-BRKSTR-SCABR | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-BRKSTR-SCABR90018830
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Engine Cat C27 | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 82 | 90018843 | A1 | 1000189176 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-ENGINE | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-ENGINE90018843
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Radiator Engine Cooling | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 48 | 90018824 | A1 | 1000189155 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-ENGINE-COSYS-RADTR | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-ENGINE-COSYS-RADTR90018824
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Aftercooler Engine | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 8 | 90018836 | A1 | 1000189169 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-AFTER | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-AFTER90018836
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Wash Engine Pre Cleaners | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 2 | 90018848 | A1 | 1000189182 | 17.11.2027 | 9000 | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-AIRFL90018848
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Final Drive LH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 48 | 90018829 | A1 | 1000189160 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-FDRSYS-FDRLH | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-FDRSYS-FDRLH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Final Drive RH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 48 | 90018829 | A1 | 1000189161 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-FDRSYS-FDRRH | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-FDRSYS-FDRRH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Fan Cooling Motor Hyd | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 16 | 90018833 | A1 | 1000189166 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCFM | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCFM90018833
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Hyd Oil Cooler | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 10 | 90018834 | A1 | 1000189167 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-HYDSYS-HDOCO | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-HYDSYS-HDOCO90018834
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Reseal Hydraulic Tank | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 48 | 90018838 | A1 | 1000189171 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-HYDSYS-HDTNK | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-HYDSYS-HDTNK90018838
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Hyd Pump Cooling Fan | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 16 | 90018832 | A1 | 1000189165 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYFPP | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYFPP90018832
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Pump Hyd Implement 1 | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 10 | 90018831 | A1 | 1000189164 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYIP1 | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYIP190018831
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Overhaul Air Conditioner | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 48 | 90018854 | A1 | 1000189189 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN | 4800 | 26987 | 8028 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN90018854
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Equaliser Bar | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 96 | 90018840 | A1 | 1000189173 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-STRUCT-CHASS-EQUAL | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-STRUCT-CHASS-EQUAL90018840
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Minor Overhaul Track Frame LH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 90 | 90033092 | A1 | 1000331951 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-TKFRL | 4800 | 26987 | 1430 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-TKFRL90033092
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Minor Overhaul Track Frame RH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 90 | 90033093 | A1 | 1000331953 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-TKFRR | 4800 | 26987 | 1430 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-TKFRR90033093
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Transmission | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 48 | 90018827 | A1 | 1000189158 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-TRNSYS-TRANS | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-TRNSYS-TRANS90018827
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Pump Trans & TCon Charge | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 10 | 90018828 | A1 | 1000189159 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-TRNSYS-TRPMP | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-TRNSYS-TRPMP90018828
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Torque Converter | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 60 | 90018826 | A1 | 1000189157 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-TRNSYS-TRQUE | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-TRNSYS-TRQUE90018826
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Drive Shaft | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 6 | 90033311 | A1 | 1000334036 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-TRNSYS-DRSHT | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-TRNSYS-DRSHT90033311
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Pump Hyd Implement 2 | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 6 | 90021621 | A1 | 1000226712 | 17.11.2027 | 18000 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYIP2 | 4800 | 26941 | 11824 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYIP290021621
D10T2 | MCORS | Ancillary | TBA | DZ8224 | DZ8224 Repl Cylinder Blade Lift RH | 2027-11-17 | 2027-12-04 | 17 days | FY28 | 14 | 90018821 | A1 | 1000189192 | 28.01.2028 | 9000 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYR | 4800 | 26987 | 1876 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYR90018821
D10T2 | MCORS | Ancillary | TBA | DZ8224 | MCORS Transport | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Opex Variation | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Capex Variation | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Additional Baseline Opex Ancillary Fleet | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Additional Baseline Capex Ancillary Fleet | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Minor Hosing Opex | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Major Hosing Price Variances - Capex | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Baseline Harness (Not on strategy) Capex | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Variation Opex - Corrosions/Repairs | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Capex Variation - Cab Overhaul (if applicable) | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | MCORS Site Labour Recovery - D10T | 2027-11-17 | 2027-12-04 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Transport & Unload | 2027-12-05 | 2027-12-07 | 2 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8224 | Recommissioning | 2027-12-08 | 2027-12-09 | 1 day | FY28
854K | MCORS | Ancillary | TBA | WD004 | WD004 - MCORS (EOL - 02/2029) | 2028-01-02 | 2028-02-08 | 37 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Decommissioning | 2028-01-02 | 2028-01-02 | 0.5 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Transport & Load | 2028-01-03 | 2028-01-05 | 2 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | WD004 Baseline Scope | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Operators Seat | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 4 | 90002975 | A1 | 1000033494 | 05.12.2027 | 7000 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS | 5900 | 72896 | 6131 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS90002975
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Engine Cat C32 | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 398 | 90029020 | A1 | 1000289519 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -ENGINE | 5900 | 72896 | 13773 | CLB-MP-DOZR-WD004 -ENGINE90029020
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Radiator Engine Cooling | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 72 | 90002931 | A1 | 1000033455 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-RADTR | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-RADTR90002931
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Aftercooler Engine | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 16 | 90010216 | 1 | 1000082608 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -ENGINE-INTEX-AFTER | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -ENGINE-INTEX-AFTER90010216
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Shaft TConverter to Trans | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 6 | 90002947 | A1 | 1000268246 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT01 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT0190002947
854K | MCORS | Ancillary | TBA | WD004 | WD004 Replace Shaft Trans to Rear Diff | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 6 | 90002948 | A1 | 1000268248 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT02 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT0290002948
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Shaft Centre Brg to Fr Diff | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 16 | 90002950 | A1 | 1000268252 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT04 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT0490002950
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Front Differential | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 120 | 90002951 | A1 | 1000033466 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-FRDIF | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -FDRSYS-FRDIF90002951
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Final Drive Position 1 | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 80 | 90002954 | A1 | 1000033469 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR01 | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR0190002954
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Final Drive Position 2 | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 80 | 90002954 | A1 | 1000033470 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR02 | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR0290002954
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Final Drive Position 3 | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 80 | 90002954 | A1 | 1000033471 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR03 | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR0390002954
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Final Drive Position 4 | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 80 | 90002954 | A1 | 1000033472 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR04 | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR0490002954
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Oil Cooler Front Axle Lube | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 24 | 90010219 | 1 | 1000082624 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC-OILCR | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC-OILCR90010219
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Brake Accumulator Front | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 6 | 90002955 | A1 | 1000033473 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM-BACCF | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM-BACCF90002955
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Brake Accumulator Rear | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 6 | 90002955 | A1 | 1000033474 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM-BACCR | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM-BACCR90002955
854K | MCORS | Ancillary | TBA | WD004 | WD004 Repl Hyd & Steering Oil Cooler | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 36 | 90010218 | 1 | 1000082596 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -HYDSYS-HDOCO | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -HYDSYS-HDOCO90010218
854K | MCORS | Ancillary | TBA | WD004 | WD004 Overhaul Auto Lubrication System | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 60 | 90002971 | A1 | 1000033490 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -GRSYST | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -GRSYST90002971
854K | MCORS | Ancillary | TBA | WD004 | WD004 Refurbish Operators Cabin | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 12 | 90002972 | A1 | 1000033491 | 27.12.2027 | 22000 | CLB-MP-DOZR-WD004 -STRUCT-CABIN | 5900 | 72896 | 13602 | CLB-MP-DOZR-WD004 -STRUCT-CABIN90002972
854K | MCORS | Ancillary | TBA | WD004 | WD004 Overhaul Airconditioner | 2028-01-06 | 2028-02-03 | 28 days | FY28 | 48 | 90029026 | A1 | 1000289942 | 27.12.2027 | 11000 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN | 5900 | 72896 | 2306 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN90029026
854K | MCORS | Ancillary | TBA | WD004 | MCORS Transport | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Opex Variation | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Capex Variation | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Additional Baseline Opex Ancillary Fleet | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Additional Baseline Capex Ancillary Fleet | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Minor Hosing Opex | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Major Hosing Price Variances - Capex | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Baseline Harness (Not on strategy) Capex | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Variation Opex - Corrosions/Repairs | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Capex Variation - Cab Overhaul (if applicable) | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | MCORS Site Labour Recovery - 854K | 2028-01-06 | 2028-02-03 | 28 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Transport & Unload | 2028-02-04 | 2028-02-06 | 2 days | FY28
854K | MCORS | Ancillary | TBA | WD004 | Recommissioning | 2028-02-07 | 2028-02-08 | 1 day | FY28
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 - MCORS (EOL - 02/2033) | 2028-02-24 | 2028-03-20 | 25.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Decommissioning | 2028-02-24 | 2028-02-24 | 0.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Load & Transport | 2028-02-25 | 2028-02-27 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 - Baseline Scope | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Engine Cat C13 Acert | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 172 | 90019395 | A1 | 1000274166 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-ENGINE | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ENGINE90019395
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Radiator Engine Cooling | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 36 | 90019364 | A1 | 1000274163 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-RADTR | 5000 | 19846 | 19846 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-RADTR90019364
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Aftercooler | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 4 | 90029830 | A1 | 1000298535 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-ENGINE-INTEX-AFTER | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ENGINE-INTEX-AFTER90029830
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Electrical Harness | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 48 | 90019390 | A1 | 1000274150 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-ELCTLV-HARNS | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ELCTLV-HARNS90019390
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Drive Shaft Unis | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 6 | 90019365 | A1 | 1000274149 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-TRNSYS-DRSHT | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-TRNSYS-DRSHT90019365
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Transmission | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 98 | 90019366 | A1 | 1000274191 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-TRNSYS-TRANS | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-TRNSYS-TRANS90019366
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Rear Axle Group | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 114 | 90019367 | A1 | 1000274164 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-FDRSYS-DIFFL | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-FDRSYS-DIFFL90019367
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Brake Assy LHF | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274142 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBLF | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBLF90019369
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Brake Assy LHR | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 40 | 90019370 | A1 | 1000274144 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBLR | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBLR90019370
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Brake Assy RHF | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274143 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBRF | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBRF90019369
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Brake Assy RHR | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 40 | 90019370 | A1 | 1000274145 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBRR | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBRR90019370
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Hyd Pump Secondary Steering | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 6 | 90019373 | A1 | 1000274185 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-STRSYS-STEMG-SESPP | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRSYS-STEMG-SESPP90019373
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Implement Ctrl Valve Front | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 12 | 90019375 | A1 | 1000274155 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDCVL-FRONT | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDCVL-FRONT90019375
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Implement Control Valve Rear | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 12 | 90019376 | A1 | 1000274156 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDCVL-REAR1 | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDCVL-REAR190019376
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Brake System Hoses | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 24 | 90019384 | A1 | 1000274146 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-BRKSH | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-BRKSH90019384
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Hydraulic System Hoses | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 48 | 90019385 | A1 | 1000274157 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-HYDSH | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-HYDSH90019385
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Powertrain System Hoses | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 48 | 90019386 | A1 | 1000274162 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-PWTRN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-PWTRN90019386
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Steering System Hoses | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 48 | 90019387 | A1 | 1000274186 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-STRNG | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-STRNG90019387
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Hyd Motor Fan Hyd Cooler | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 8 | 90019377 | A1 | 1000274151 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDMOT-MOFAN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDMOT-MOFAN90019377
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Hydraulic Oil Cooler | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 4 | 90029813 | A1 | 1000298559 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDOCO | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HDOCO90029813
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Hyd Pump Implement & Steer | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 16 | 90019374 | A1 | 1000274158 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HYDPP-HYISP | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-HYDSYS-HYDPP-HYISP90019374
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Axle Assy Front | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 36 | 90019381 | A1 | 1000274153 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-STRUCT-AXLES | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-AXLES90019381
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Refurbish Cabin | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 6 | 90019388 | A1 | 1000315261 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN90019388
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Overhaul Air Conditioner | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 48 | 90019411 | A1 | 1000274182 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN90019411
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Operators Seat | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 8 | 90019380 | A1 | 1000274161 | 25.02.2028 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS90019380
18 | MCORS | Ancillary | TBA | GR6503 | GR6503 Repl Ripper Assy | 2028-02-28 | 2028-03-16 | 17 days | FY28 | 48 | 90019383 | A1 | 1000274184 | 25.02.2028 | 14000 | CLB-MP-GRDR-GR6503-STRUCT-RIPPR | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-RIPPR90019383
18 | MCORS | Ancillary | TBA | GR6503 | MCORS Transport | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Opex Variation | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Capex Variation | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Additional Baseline Opex Ancillary Fleet | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Additional Baseline Capex Ancillary Fleet | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Minor Hosing Opex | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Major Hosing Price Variances - Capex | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | MCORS Site Labour Recovery - 18 | 2028-02-28 | 2028-03-16 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Transport & Unload | 2028-03-17 | 2028-03-19 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6503 | Recommissioning | 2028-03-20 | 2028-03-20 | 0.5 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 - MCORS (EOL - 11/2024) | 2028-03-09 | 2028-04-04 | 26 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Decommissioning | 2028-03-09 | 2028-03-09 | 0.5 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Load & Transport | 2028-03-10 | 2028-03-12 | 2 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 - Baseline Scope | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Equaliser Bar | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 96 | 90010849 | 1 | 1000089520 | 20.02.2028 | 14000 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-EQUAL | 4400 | 63346 | 6717 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-EQUAL90010849
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Drive Shaft | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 14 | 90033381 | A1 | 1000335060 | 13.03.2028 | 28000 | CLB-MP-DOZR-DZX022-TRNSYS | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS90033381
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Torque Converter | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 72 | 90003342 | 1 | 1000037947 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-TRNSYS-TRQUE | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS-TRQUE90003342
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Transmission | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 72 | 90003343 | 1 | 1000037948 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-TRNSYS-TRANS | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS-TRANS90003343
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Bevel Gear | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 96 | 90003344 | 1 | 1000037949 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-TRNSYS-TRANS-BEVEL | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS-TRANS-BEVEL90003344
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Transmission Oil Cooler | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 14 | 90009667 | 1 | 1000075391 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-TRNSYS-TROLC | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS-TROLC90009667
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 T-Conv Trans Charge Pump Replace | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 10 | 90037704 | A1 | 1000374086 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-TRNSYS-TRPMP | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS-TRPMP90037704
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Implement Valves Hyd | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 18 | 90003350 | 1 | 1000089510 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-HYDSYS-HDCVL | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-HYDSYS-HDCVL90003350
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Hyd Oil Cooler | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 8 | 90009665 | 1 | 1000075381 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-HYDSYS-HDOCO | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-HYDSYS-HDOCO90009665
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Fan Cooling Motor Hyd | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 16 | 90003352 | 1 | 1000037959 | 13.03.2028 | 7000 | CLB-MP-DOZR-DZX022-HYDSYS-HDCFM | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-HYDSYS-HDCFM90003352
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Hood Mounts | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 12 | 90010848 | 1 | 1000089495 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-STRUCT-PNLGU | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-STRUCT-PNLGU90010848
D11T | MCORS | Ancillary | TBA | DZX022 | DZX022 Repl Actuator Brake HaulX Shield | 2028-03-13 | 2028-03-30 | 17 days | FY28 | 50 | 90033516 | A1 | 1000362573 | 13.03.2028 | 14000 | CLB-MP-DOZR-DZX022-CASSYS-CTRLH-ACTBK | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-CASSYS-CTRLH-ACTBK90033516
D11T | MCORS | Ancillary | TBA | DZX022 | MCORS Transport | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Opex Variation | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Capex Variation | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Additional Baseline Opex Ancillary Fleet | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Additional Baseline Capex Ancillary Fleet | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Minor Hosing Opex | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Major Hosing Price Variances - Capex | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Baseline Harness (Not on strategy) Capex | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Variation Opex - Corrosions/Repairs | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Capex Variation - Cab Overhaul (if applicable) | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | MCORS Site Labour Recovery - D11T | 2028-03-13 | 2028-03-30 | 17 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Transport & Unload | 2028-03-31 | 2028-04-02 | 2 days | FY28
D11T | MCORS | Ancillary | TBA | DZX022 | Recommissioning | 2028-04-03 | 2028-04-04 | 1 day | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 - MCORS (EOL - 12/2026) | 2028-04-12 | 2028-05-08 | 26 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Decommissioning | 2028-04-12 | 2028-04-12 | 0.5 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Load & Transport | 2028-04-13 | 2028-04-15 | 2 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 - Baseline Scope | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Fan Cooling Motor Hyd | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 16 | 90002094 | 1 | 1000069926 | 12.04.2028 | 9000 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCFM | 4700 | 70238 | 1105 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCFM90002094
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Steer Clutch & Brake Assm RH | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 32 | 90000313 | 1 | 1000020566 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -BRKSTR-SCABR | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -BRKSTR-SCABR90000313
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Rad Engine Cooling SN 529 UP | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 48 | 90000307 | A1 | 1000020557 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-RADTR | 5100 | 70238 | 24328 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-RADTR90000307
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Aftercooler Engine | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 8 | 90010841 | 1 | 1000089376 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -ENGINE-INTEX-AFTER | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -ENGINE-INTEX-AFTER90010841
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Ovhl Hydraulic & Fuel Tank | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 48 | 90010842 | 1 | 1000089420 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -HYDSYS-HDTNK | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -HYDSYS-HDTNK90010842
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Hyd Pump Cooling Fan | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 16 | 90004952 | 1 | 1000069906 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYFPP | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYFPP90004952
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Minor Overhaul Track Frame LH | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 96 | 90002098 | 1 | 1000171805 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-TKFRL | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-TKFRL90002098
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Minor Overhaul Track Frame RH | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 96 | 90010766 | 1 | 1000171806 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-TKFRR | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-TKFRR90010766
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Drive Shaft | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 6 | 90033296 | A1 | 1000334091 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -TRNSYS | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -TRNSYS90033296
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Transmission | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 48 | 90000308 | 1 | 1000020560 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -TRNSYS-TRANS | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -TRNSYS-TRANS90000308
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Pump Trans & TCon Charge | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 10 | 90000302 | 1 | 1000020562 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -TRNSYS-TRPMP | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -TRNSYS-TRPMP90000302
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Torque Converter | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 60 | 90000309 | 1 | 1000020559 | 13.04.2028 | 18000 | CLB-MP-DOZR-DZ017 -TRNSYS-TRQUE | 4700 | 70238 | 10138 | CLB-MP-DOZR-DZ017 -TRNSYS-TRQUE90000309
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Repl Engine Cat C27 | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 126 | 90015849 | 1 | 1000159559 | 08.05.2028 | 18000 | CLB-MP-DOZR-DZ017 -ENGINE | 4700 | 70238 | 9809 | CLB-MP-DOZR-DZ017 -ENGINE90015849
D10T | MCORS | Ancillary | TBA | DZ017 | DZ017 Overhaul Air Conditioner | 2028-04-16 | 2028-05-03 | 17 days | FY28 | 48 | 90017468 | 1 | 1000160694 | 08.05.2028 | 18000 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN | 4700 | 70238 | 1106 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN90017468
D10T | MCORS | Ancillary | TBA | DZ017 | MCORS Transport | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Opex Variation | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Capex Variation | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Additional Baseline Opex Ancillary Fleet | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Additional Baseline Capex Ancillary Fleet | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Minor Hosing Opex | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Major Hosing Price Variances - Capex | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Baseline Harness (Not on strategy) Capex | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Variation Opex - Corrosions/Repairs | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Capex Variation - Cab Overhaul (if applicable) | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | MCORS Site Labour Recovery - D10T | 2028-04-16 | 2028-05-03 | 17 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Transport & Unload | 2028-05-04 | 2028-05-06 | 2 days | FY28
D10T | MCORS | Ancillary | TBA | DZ017 | Recommissioning | 2028-05-07 | 2028-05-08 | 1 day | FY28
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 - MCORS (EOL - 03/2033) | 2028-05-07 | 2028-06-01 | 25.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Decommissioning | 2028-05-07 | 2028-05-07 | 0.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Load & Transport | 2028-05-08 | 2028-05-10 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 - Baseline Scope | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Engine Cat C13 Acert | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 172 | 90019395 | A1 | 1000274231 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-ENGINE | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-ENGINE90019395
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Radiator Engine Cooling | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 36 | 90019364 | A1 | 1000274228 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-RADTR | 5000 | 19712 | 19712 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-RADTR90019364
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Aftercooler | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 4 | 90029830 | A1 | 1000298536 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-ENGINE-INTEX-AFTER | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-ENGINE-INTEX-AFTER90029830
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Electrical Harness | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 48 | 90019390 | A1 | 1000274215 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-ELCTLV-HARNS | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-ELCTLV-HARNS90019390
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Drive Shaft Unis | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 6 | 90019365 | A1 | 1000274214 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-TRNSYS-DRSHT | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-TRNSYS-DRSHT90019365
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Transmission | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 98 | 90019366 | A1 | 1000274256 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-TRNSYS-TRANS | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-TRNSYS-TRANS90019366
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Rear Axle Group | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 114 | 90019367 | A1 | 1000274229 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-FDRSYS-DIFFL | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-FDRSYS-DIFFL90019367
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Brake Assy LHF | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274207 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBLF | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBLF90019369
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Brake Assy RHF | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274208 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBRF | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBRF90019369
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Brake Assy RHR | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 40 | 90019370 | A1 | 1000274210 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBRR | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBRR90019370
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Hyd Pump Secondary Steering | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 6 | 90019373 | A1 | 1000274250 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-STRSYS-STEMG-SESPP | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRSYS-STEMG-SESPP90019373
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Implement Ctrl Valve Front | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 12 | 90019375 | A1 | 1000274220 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDCVL-FRONT | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDCVL-FRONT90019375
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Implement Control Valve Rear | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 12 | 90019376 | A1 | 1000274221 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDCVL-REAR1 | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDCVL-REAR190019376
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Brake System Hoses | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 24 | 90019384 | A1 | 1000274211 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-BRKSH | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-BRKSH90019384
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Hydraulic System Hoses | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 48 | 90019385 | A1 | 1000274222 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-HYDSH | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-HYDSH90019385
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Powertrain System Hoses | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 48 | 90019386 | A1 | 1000274227 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-PWTRN | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-PWTRN90019386
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Steering System Hoses | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 48 | 90019387 | A1 | 1000274251 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-STRNG | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-STRNG90019387
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Hydraulic Oil Cooler | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 4 | 90029813 | A1 | 1000298620 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDOCO | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HDOCO90029813
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Hyd Pump Implement & Steer | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 16 | 90019374 | A1 | 1000274223 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HYDPP-HYISP | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-HYDSYS-HYDPP-HYISP90019374
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Auto Lube Pump | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 4 | 90019389 | A1 | 1000274205 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-GRSYST-ALBPP | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-GRSYST-ALBPP90019389
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Axle Assy Front | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 36 | 90019381 | A1 | 1000274218 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-STRUCT-AXLES | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-AXLES90019381
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Refurbish Cabin | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 6 | 90019388 | A1 | 1000315262 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-STRUCT-CABIN | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN90019388
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Overhaul Air Conditioner | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 48 | 90019411 | A1 | 1000274247 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN90019411
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Operators Seat | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 8 | 90019380 | A1 | 1000274226 | 11.05.2028 | 7000 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-SEATS | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-SEATS90019380
18 | MCORS | Ancillary | TBA | GR6504 | GR6504 Repl Ripper Assy | 2028-05-11 | 2028-05-28 | 17 days | FY28 | 48 | 90019383 | A1 | 1000274249 | 11.05.2028 | 14000 | CLB-MP-GRDR-GR6504-STRUCT-RIPPR | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-RIPPR90019383
18 | MCORS | Ancillary | TBA | GR6504 | MCORS Transport | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Opex Variation | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Capex Variation | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Additional Baseline Opex Ancillary Fleet | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Additional Baseline Capex Ancillary Fleet | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Minor Hosing Opex | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Major Hosing Price Variances - Capex | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | MCORS Site Labour Recovery - 18 | 2028-05-11 | 2028-05-28 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Transport & Unload | 2028-05-29 | 2028-05-31 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6504 | Recommissioning | 2028-06-01 | 2028-06-01 | 0.5 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 - MCORS (EOL - 06/2036) | 2028-05-12 | 2028-06-07 | 26 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Decommissioning | 2028-05-12 | 2028-05-12 | 0.5 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Load & Transport | 2028-05-13 | 2028-05-15 | 2 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 - Baseline Scope | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Cylinder Blade Lift LH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 14 | 90031953 | A1 | 1000202362 | 03.02.2028 | 9000 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BLCYL | 4800 | 24525 | 1786 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BLCYL90031953
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Cylinder Blade Tilt RH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 16 | 90018823 | A1 | 1000202365 | 24.02.2028 | 9000 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BTCYR | 4800 | 24525 | 1509 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BTCYR90018823
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Final Drive LH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 48 | 90018829 | A1 | 1000313522 | 09.04.2028 | 18000 | CLB-MP-DOZR-DZ8225-FDRSYS-FDRLH | 4800 | 24525 | 9917 | CLB-MP-DOZR-DZ8225-FDRSYS-FDRLH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Steer Clutch & Brake Assm LH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 32 | 90018830 | A1 | 1000202312 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-BRKSTR-SCABL | 4800 | 24542 | 9431 | CLB-MP-DOZR-DZ8225-BRKSTR-SCABL90018830
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Engine Cat C27 | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 82 | 90018843 | A1 | 1000202347 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-ENGINE | 4800 | 24542 | 9431 | CLB-MP-DOZR-DZ8225-ENGINE90018843
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Aftercooler Engine | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 8 | 90018836 | A1 | 1000202319 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AFTER | 4800 | 24542 | 9431 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AFTER90018836
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Wash Engine Pre Cleaners | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 2 | 90018848 | A1 | 1000202353 | 16.05.2028 | 9000 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AIRFL90018848
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Final Drive RH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 48 | 90018829 | A1 | 1000313523 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-FDRSYS-FDRRH | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-FDRSYS-FDRRH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Hyd Oil Cooler | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 10 | 90018834 | A1 | 1000202317 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HDOCO | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-HYDSYS-HDOCO90018834
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Reseal Hydraulic Tank | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 48 | 90018838 | A1 | 1000202341 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HDTNK | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-HYDSYS-HDTNK90018838
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Hyd Pump Cooling Fan | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 16 | 90018832 | A1 | 1000202315 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYFPP | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYFPP90018832
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Pump Hyd Implement 1 | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 10 | 90018831 | A1 | 1000202314 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYIP1 | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYIP190018831
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Overhaul Air Conditioner | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 48 | 90018854 | A1 | 1000202360 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN90018854
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Track Frame LH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 90 | 90033095 | A1 | 1000331956 | 16.05.2028 | 36000 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-TKFRL | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-TKFRL90033095
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Track Frame RH | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 90 | 90033096 | A1 | 1000331958 | 16.05.2028 | 36000 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-TKFRR | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-TKFRR90033096
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Transmission | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 48 | 90018827 | A1 | 1000202308 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-TRNSYS-TRANS | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-TRNSYS-TRANS90018827
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Pump Trans & TCon Charge | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 10 | 90018828 | A1 | 1000202309 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-TRNSYS-TRPMP | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-TRNSYS-TRPMP90018828
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Torque Converter | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 60 | 90018826 | A1 | 1000202307 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-TRNSYS-TRQUE | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-TRNSYS-TRQUE90018826
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Drive Shaft | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 6 | 90033311 | A1 | 1000334038 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-TRNSYS-DRSHT | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-TRNSYS-DRSHT90033311
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Pump Hyd Variable Charge | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 4 | 90021620 | A1 | 1000226597 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYDVC | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYDVC90021620
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Repl Pump Hyd Implement 2 | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 6 | 90021621 | A1 | 1000226707 | 16.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYIP2 | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYIP290021621
D10T2 | MCORS | Ancillary | TBA | DZ8225 | DZ8225 Adjust Engine 500hr Valve Set | 2028-05-16 | 2028-06-02 | 17 days | FY28 | 24 | 90018851 | A1 | 1000202356 | 23.06.2028 | 500 | CLB-MP-DOZR-DZ8225-ENGINE | 4800 | 24542 | 9431 | CLB-MP-DOZR-DZ8225-ENGINE90018851
D10T2 | MCORS | Ancillary | TBA | DZ8225 | MCORS Transport | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Opex Variation | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Capex Variation | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Additional Baseline Opex Ancillary Fleet | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Additional Baseline Capex Ancillary Fleet | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Minor Hosing Opex | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Major Hosing Price Variances - Capex | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Baseline Harness (Not on strategy) Capex | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Variation Opex - Corrosions/Repairs | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Capex Variation - Cab Overhaul (if applicable) | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | MCORS Site Labour Recovery - D10T | 2028-05-16 | 2028-06-02 | 17 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Transport & Unload | 2028-06-03 | 2028-06-05 | 2 days | FY28
D10T2 | MCORS | Ancillary | TBA | DZ8225 | Recommissioning | 2028-06-06 | 2028-06-07 | 1 day | FY28
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 - MCORS (EOL - 02/2033) | 2028-05-21 | 2028-06-15 | 25.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Decommissioning | 2028-05-21 | 2028-05-21 | 0.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Load & Transport | 2028-05-22 | 2028-05-24 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 - Baseline Scope | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Engine Cat C13 Acert | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 172 | 90019395 | A1 | 1000274551 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-ENGINE | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-ENGINE90019395
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Radiator Engine Cooling | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 36 | 90019364 | A1 | 1000274548 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-RADTR | 5000 | 20249 | 20249 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-RADTR90019364
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Aftercooler | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 4 | 90029830 | A1 | 1000298534 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-ENGINE-INTEX-AFTER | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-ENGINE-INTEX-AFTER90029830
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Electrical Harness | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 48 | 90019390 | A1 | 1000274295 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-ELCTLV-HARNS | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-ELCTLV-HARNS90019390
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Drive Shaft Unis | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 6 | 90019365 | A1 | 1000274294 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-TRNSYS-DRSHT | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-TRNSYS-DRSHT90019365
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Transmission | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 98 | 90019366 | A1 | 1000274576 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-TRNSYS-TRANS | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-TRNSYS-TRANS90019366
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Rear Axle Group | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 114 | 90019367 | A1 | 1000274549 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-FDRSYS-DIFFL | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-FDRSYS-DIFFL90019367
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Pump Brake & Hyd Fan | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 6 | 90019371 | A1 | 1000274286 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-BRKSYS-BRPMP | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-BRKSYS-BRPMP90019371
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Brake Assy LHF | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274287 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBLF | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBLF90019369
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Brake Assy LHR | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 40 | 90019370 | A1 | 1000274289 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBLR | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBLR90019370
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Brake Assy RHF | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274288 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBRF | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBRF90019369
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Brake Assy RHR | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 40 | 90019370 | A1 | 1000274290 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBRR | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBRR90019370
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Hyd Pump Secondary Steering | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 6 | 90019373 | A1 | 1000274570 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-STRSYS-STEMG-SESPP | 5500 | 20249 | 3802 | CLB-MP-GRDR-GR6501-STRSYS-STEMG-SESPP90019373
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Implement Ctrl Valve Front | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 12 | 90019375 | A1 | 1000274540 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDCVL-FRONT | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDCVL-FRONT90019375
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Implement Control Valve Rear | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 12 | 90019376 | A1 | 1000274541 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDCVL-REAR1 | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDCVL-REAR190019376
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Cyl Articulation RH | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 12 | 90019379 | A1 | 1000274284 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-ARCYR | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-ARCYR90019379
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Brake System Hoses | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 24 | 90019384 | A1 | 1000274291 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-BRKSH | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-BRKSH90019384
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Hydraulic System Hoses | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 48 | 90019385 | A1 | 1000274542 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-HYDSH | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-HYDSH90019385
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Powertrain System Hoses | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 48 | 90019386 | A1 | 1000274547 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-PWTRN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-PWTRN90019386
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Steering System Hoses | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 48 | 90019387 | A1 | 1000274571 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-STRNG | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-STRNG90019387
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Hyd Motor Fan Hyd Cooler | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 8 | 90019377 | A1 | 1000274296 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDMOT-MOFAN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDMOT-MOFAN90019377
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Hydraulic Oil Cooler | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 4 | 90029813 | A1 | 1000298558 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDOCO | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HDOCO90029813
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Hyd Pump Implement & Steer | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 16 | 90019374 | A1 | 1000274543 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HYDPP-HYISP | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-HYDSYS-HYDPP-HYISP90019374
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Auto Lube Pump | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 4 | 90019389 | A1 | 1000274285 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-GRSYST-ALBPP | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-GRSYST-ALBPP90019389
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Axle Assy Front | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 36 | 90019381 | A1 | 1000274298 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-STRUCT-AXLES | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-AXLES90019381
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Refurbish Cabin | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 6 | 90019388 | A1 | 1000315260 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-STRUCT-CABIN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN90019388
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Overhaul Air Conditioner | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 48 | 90019411 | A1 | 1000274567 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN90019411
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Operators Seat | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 8 | 90019380 | A1 | 1000274546 | 23.05.2028 | 7000 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-SEATS | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-SEATS90019380
18 | MCORS | Ancillary | TBA | GR6501 | GR6501 Repl Ripper Assy | 2028-05-25 | 2028-06-11 | 17 days | FY28 | 48 | 90019383 | A1 | 1000274569 | 23.05.2028 | 14000 | CLB-MP-GRDR-GR6501-STRUCT-RIPPR | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-RIPPR90019383
18 | MCORS | Ancillary | TBA | GR6501 | MCORS Transport | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Opex Variation | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Capex Variation | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Additional Baseline Opex Ancillary Fleet | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Additional Baseline Capex Ancillary Fleet | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Minor Hosing Opex | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Major Hosing Price Variances - Capex | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | MCORS Site Labour Recovery - 18 | 2028-05-25 | 2028-06-11 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Transport & Unload | 2028-06-12 | 2028-06-14 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6501 | Recommissioning | 2028-06-15 | 2028-06-15 | 0.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 - MCORS (EOL - 03/2033) | 2028-06-04 | 2028-06-29 | 25.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Decommissioning | 2028-06-04 | 2028-06-04 | 0.5 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Load & Transport | 2028-06-05 | 2028-06-07 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 - Baseline Scope | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Engine Cat C13 Acert | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 172 | 90019395 | A1 | 1000274637 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-ENGINE | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-ENGINE90019395
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Radiator Engine Cooling | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 36 | 90019364 | A1 | 1000274634 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-RADTR | 5000 | 19670 | 19670 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-RADTR90019364
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Aftercooler | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 4 | 90029830 | A1 | 1000298537 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-ENGINE-INTEX-AFTER | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-ENGINE-INTEX-AFTER90029830
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Electrical Harness | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 48 | 90019390 | A1 | 1000274621 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-ELCTLV-HARNS | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-ELCTLV-HARNS90019390
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Transmission | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 98 | 90019366 | A1 | 1000274662 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-TRNSYS-TRANS | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-TRNSYS-TRANS90019366
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Rear Axle Group | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 114 | 90019367 | A1 | 1000274635 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-FDRSYS-DIFFL | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-FDRSYS-DIFFL90019367
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Pump Brake & Hyd Fan | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 6 | 90019371 | A1 | 1000274532 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-BRKSYS-BRPMP | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-BRKSYS-BRPMP90019371
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Brake Assy LHF | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274533 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBLF | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBLF90019369
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Brake Assy RHF | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 40 | 90019369 | A1 | 1000274534 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBRF | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBRF90019369
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Brake Assy RHR | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 40 | 90019370 | A1 | 1000274536 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBRR | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBRR90019370
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Hyd Pump Secondary Steering | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 6 | 90019373 | A1 | 1000274656 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-STRSYS-STEMG-SESPP | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRSYS-STEMG-SESPP90019373
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Implement Ctrl Valve Front | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 12 | 90019375 | A1 | 1000274626 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDCVL-FRONT | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDCVL-FRONT90019375
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Implement Control Valve Rear | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 12 | 90019376 | A1 | 1000274627 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDCVL-REAR1 | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDCVL-REAR190019376
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Brake System Hoses | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 24 | 90019384 | A1 | 1000274537 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-BRKSH | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-BRKSH90019384
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Hydraulic System Hoses | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 48 | 90019385 | A1 | 1000274628 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-HYDSH | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-HYDSH90019385
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Powertrain System Hoses | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 48 | 90019386 | A1 | 1000274633 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-PWTRN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-PWTRN90019386
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Steering System Hoses | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 48 | 90019387 | A1 | 1000274657 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-STRNG | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-STRNG90019387
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Hyd Motor Fan Hyd Cooler | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 8 | 90019377 | A1 | 1000274622 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDMOT-MOFAN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDMOT-MOFAN90019377
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Hydraulic Oil Cooler | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 4 | 90029813 | A1 | 1000298621 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDOCO | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HDOCO90029813
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Hyd Pump Implement & Steer | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 16 | 90019374 | A1 | 1000274629 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HYDPP-HYISP | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-HYDSYS-HYDPP-HYISP90019374
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Auto Lube Pump | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 4 | 90019389 | A1 | 1000274531 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-GRSYST-ALBPP | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-GRSYST-ALBPP90019389
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Axle Assy Front | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 36 | 90019381 | A1 | 1000274624 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-STRUCT-AXLES | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-AXLES90019381
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Refurbish Cabin | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 6 | 90019388 | A1 | 1000315263 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-STRUCT-CABIN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN90019388
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Overhaul Air Conditioner | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 48 | 90019411 | A1 | 1000274653 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN90019411
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Operators Seat | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 8 | 90019380 | A1 | 1000274632 | 08.06.2028 | 7000 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-SEATS | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-SEATS90019380
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Gearbox Circle Drive | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 14 | 90019382 | A1 | 1000274538 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-STRUCT-CIRCL-CDRBX | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CIRCL-CDRBX90019382
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Ripper Assy | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 48 | 90019383 | A1 | 1000274655 | 08.06.2028 | 14000 | CLB-MP-GRDR-GR6505-STRUCT-RIPPR | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-RIPPR90019383
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Drive Shaft Unis | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 6 | 90019365 | A1 | 1000274620 | 16.06.2028 | 14000 | CLB-MP-GRDR-GR6505-TRNSYS-DRSHT | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-TRNSYS-DRSHT90019365
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Cyl Articulation RH | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 12 | 90019379 | A1 | 1000274530 | 23.08.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-ARCYR | 5500 | 19670 | 6800 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-ARCYR90019379
18 | MCORS | Ancillary | TBA | GR6505 | GR6505 Repl Cyl Articulation LH | 2028-06-08 | 2028-06-25 | 17 days | FY28 | 12 | 90019378 | A1 | 1000274529 | 01.09.2028 | 14000 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-ARCYL | 5500 | 19670 | 2578 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-ARCYL90019378
18 | MCORS | Ancillary | TBA | GR6505 | MCORS Transport | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Opex Variation | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Capex Variation | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Additional Baseline Opex Ancillary Fleet | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Additional Baseline Capex Ancillary Fleet | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Minor Hosing Opex | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Major Hosing Price Variances - Capex | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | MCORS Site Labour Recovery - 18 | 2028-06-08 | 2028-06-25 | 17 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Transport & Unload | 2028-06-26 | 2028-06-28 | 2 days | FY28
18 | MCORS | Ancillary | TBA | GR6505 | Recommissioning | 2028-06-29 | 2028-06-29 | 0.5 days | FY28
| MCORS | Haul | Various |  | HAUL | 2027-07-01 | 2028-06-30 | 365 days | FY28
789D | MCORS | Haul | TBA | DT194 | DT194 - MCORS (EOL - 09/2029) | 2027-07-04 | 2027-08-18 | 45 days | FY28
789D | MCORS | Haul | TBA | DT194 | Decommissioning | 2027-07-04 | 2027-07-06 | 2 days | FY28
789D | MCORS | Haul | TBA | DT194 | Load & Transport | 2027-07-07 | 2027-07-10 | 3 days | FY28
789D | MCORS | Haul | TBA | DT194 | DT194 - Baseline Scope | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Drive Line Axle LH | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 8 | 90014551 | 1 | 1000123539 | 24.04.2027 | 30000 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX-AXLLH | 7500 | 86451 | 24471 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX-AXLLH90014551
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Drive Line Axle RH | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 8 | 90014552 | 1 | 1000123600 | 24.04.2027 | 30000 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX-AXLRH | 7500 | 86451 | 24471 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX-AXLRH90014552
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Final Drive RH | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 56 | 90003100 | 1 | 1000035815 | 05.05.2027 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-FDRVE-FDRRH | 7500 | 86451 | 16196 | CLB-MP-HAUL-DT194 -FDRSYS-FDRVE-FDRRH90003100
789D | MCORS | Haul | TBA | DT194 | DT194 Spiders Transmission Driveshaft | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 8 | 90017135 | 1 | 1000154430 | 01.06.2027 | 11000 | CLB-MP-HAUL-DT194 -FDRSYS-DRSHT-UNVSL | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -FDRSYS-DRSHT-UNVSL90017135
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Engine Cat 3516B | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 142 | 90017315 | 1 | 1000156957 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -ENGINE | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE90017315
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Radiator Engine Cooling | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 85 | 90003081 | 1 | 1000035805 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-RADTR | 7400 | 86451 | 37638 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-RADTR90003081
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Fuel Tank Mounts | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 16 | 90009887 | 1 | 1000078828 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -ENGINE-FUSYS-FULTK | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE-FUSYS-FULTK90009887
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Engine Pump Drive | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 62 | 90003089 | 1 | 1000035807 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR90003089
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Torque Converter | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 62 | 90003092 | 1 | 1000035808 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -TRNSYS-TRQUE | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -TRNSYS-TRQUE90003092
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Transmission Oil Cooler | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 13 | 90003532 | 1 | 1000041003 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -TRNSYS-TROLC | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -TRNSYS-TROLC90003532
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Differential | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 66 | 90003098 | 1 | 1000035813 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-DIFFL | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -FDRSYS-DIFFL90003098
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Hyd Motor Axle Lube Rear | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 9 | 90003101 | 1 | 1000035816 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-HYM01 | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-HYM0190003101
789D | MCORS | Haul | TBA | DT194 | DT194 Overhaul Accumulator Brake | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 10 | 90009313 | 1 | 1000072214 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BACCM | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BACCM90009313
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Valve Brake | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 18 | 90003107 | 1 | 1000035823 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRVLV | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRVLV90003107
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Rotochamber Front | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 5 | 90009308 | 1 | 1000072404 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTFR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTFR90009308
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Rotochamber LHR | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072442 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTLR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTLR90009309
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Rotochamber RHR | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072480 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTRR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTRR90009309
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Valve Steering & AHS EH | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 10 | 90009881 | 1 | 1000078823 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRSYS-STVLV | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRSYS-STVLV90009881
789D | MCORS | Haul | TBA | DT194 | DT194 Ovhl Accumulator Hyd Steer Front | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072100 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCF90009314
789D | MCORS | Haul | TBA | DT194 | DT194 Ovhl Accumulator Hyd Steer Middle | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072138 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCM | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCM90009314
789D | MCORS | Haul | TBA | DT194 | DT194 Ovhl Accumulator Hyd Steering Rear | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072176 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCR90009314
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Air Dryer | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 14 | 90003115 | 1 | 1000035833 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -PNEUMC-AIRDR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -PNEUMC-AIRDR90003115
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Brake Wheel RH | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 61 | 90003105 | 2 | 1000035820 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-AXLES-HUBRH | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-AXLES-HUBRH90003105
789D | MCORS | Haul | TBA | DT194 | DT194 Service Suspension Cylinders | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 27 | 90012840 | 1 | 1000106943 | 05.06.2027 | 11000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN90012840
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Cyl Suspension LHF | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067882 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYLF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYLF90003121
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Cyl Suspension RHF | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067884 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYRF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYRF90003121
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Transmission System Hoses | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 8 | 90009871 | 1 | 1000078813 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -TRNSYS-TRANS-TRNHO | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -TRNSYS-TRANS-TRNHO90009871
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Torque Conv System Hoses | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 4 | 90009872 | 1 | 1000078814 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -TRNSYS-TRQUE-TRQHO | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -TRNSYS-TRQUE-TRQHO90009872
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Brake Oil Cooler Front | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 5 | 90003108 | 1 | 1000080298 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BROCO-BROCF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BROCO-BROCF90003108
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Brake System Hoses Rear | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 6 | 90009878 | 1 | 1000078820 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRHOR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRHOR90009878
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Brake System Hoses Front | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 12 | 90009879 | 1 | 1000078821 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRHOF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRHOF90009879
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Brake System Air Lines | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 24 | 90009880 | 1 | 1000078822 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRAIR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRAIR90009880
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Steering System Hoses | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 24 | 90009882 | 1 | 1000078824 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -STRSYS-STHLF-STRHO | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRSYS-STHLF-STRHO90009882
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Hoist System Hoses | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 12 | 90009903 | 1 | 1000078818 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-HSTHO | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-HSTHO90009903
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Differential System Hoses | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 2 | 90009873 | 1 | 1000078815 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-DIFFL-DIFHO | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -FDRSYS-DIFFL-DIFHO90009873
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Fast Fill & SOS Hose | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 36 | 90012188 | 1 | 1000103989 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-FFSOS | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-FFSOS90012188
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Ladder Hoses | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 4 | 90012189 | 1 | 1000104047 | 05.06.2027 | 22000 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-LADHO | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-LADHO90012189
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Pump Drive Driveshaft Unis | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 4 | 90009874 | 1 | 1000035810 | 14.06.2027 | 11000 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR-DRSHT | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR-DRSHT90009874
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Brake Relay Valve | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 6 | 90009877 | 1 | 1000078819 | 14.06.2027 | 11000 | CLB-MP-HAUL-DT194 -BRKSYS-BRVRL | 7500 | 86451 | 4331 | CLB-MP-HAUL-DT194 -BRKSYS-BRVRL90009877
789D | MCORS | Haul | TBA | DT194 | DT194 1Y Air Tank LH External Inspect | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 1.5 | 90038753 | A1 | 1000389430 | 24.08.2027 | 12 Monthly | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH | 7500 | 86244 | 37431 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH90038753
789D | MCORS | Haul | TBA | DT194 | DT194 1Y Air Tank RH External Inspect | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 1.5 | 90038753 | A1 | 1000389432 | 24.08.2027 | 12 Monthly | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH | 7500 | 86244 | 37431 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH90038753
789D | MCORS | Haul | TBA | DT194 | DT194 Repl Steering HMU | 2027-07-11 | 2027-08-09 | 29 days | FY28 | 14 | 90003110 | 1 | 1000035826 | 06.09.2027 | 15000 | CLB-MP-HAUL-DT194 -STRSYS-STHMU | 7500 | 86451 | 21821 | CLB-MP-HAUL-DT194 -STRSYS-STHMU90003110
789D | MCORS | Haul | TBA | DT194 | MCORS Transport | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Opex Variation | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Capex Variation | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Additional Baseline Opex Truck Fleet | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Additional Baseline Capex Truck Fleet | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Capex Variation - Steer Box (if applicable) | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Minor Hosing Opex | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Baseline Harness (Not on strategy) Capex | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Variation Opex - Corrosions/Repairs | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | MCORS Site Labour Recovery - 789D | 2027-07-11 | 2027-08-09 | 29 days | FY28
789D | MCORS | Haul | TBA | DT194 | Transport & Unload | 2027-08-10 | 2027-08-13 | 3 days | FY28
789D | MCORS | Haul | TBA | DT194 | Recommissioning | 2027-08-14 | 2027-08-18 | 4 days | FY28
789D | MCORS | Haul | TBA | DT199 | DT199 - MCORS (EOL - 10/2029) | 2027-10-21 | 2027-12-05 | 45 days | FY28
789D | MCORS | Haul | TBA | DT199 | Decommissioning | 2027-10-21 | 2027-10-23 | 2 days | FY28
789D | MCORS | Haul | TBA | DT199 | Load & Transport | 2027-10-24 | 2027-10-27 | 3 days | FY28
789D | MCORS | Haul | TBA | DT199 | DT199 - Baseline Scope | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Engine Cat 3516B | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 142 | 90017315 | 1 | 1000157037 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -ENGINE | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -ENGINE90017315
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Radiator Engine Cooling | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 85 | 90003081 | 1 | 1000036102 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-RADTR | 7400 | 85978 | 35622 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-RADTR90003081
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Engine Pump Drive | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 62 | 90003089 | 1 | 1000036104 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR90003089
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Torque Converter | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 62 | 90003092 | 1 | 1000036105 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -TRNSYS-TRQUE | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -TRNSYS-TRQUE90003092
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Transmission | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 48 | 90003093 | 1 | 1000036106 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -TRNSYS-TRANS | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -TRNSYS-TRANS90003093
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Pump Torque Converter Charge | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90003095 | 1 | 1000080220 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TCCPP | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TCCPP90003095
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Transmission Oil Cooler | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 13 | 90003532 | 1 | 1000041008 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -TRNSYS-TROLC | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -TRNSYS-TROLC90003532
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Drive Shaft Transmission | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 16 | 90017134 | 1 | 1000154439 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-DRSHT | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -FDRSYS-DRSHT90017134
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Differential | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 66 | 90003098 | 1 | 1000036110 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-DIFFL | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -FDRSYS-DIFFL90003098
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Final Drive RH | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 56 | 90003100 | 1 | 1000036112 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-FDRVE-FDRRH | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -FDRSYS-FDRVE-FDRRH90003100
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Hyd Motor Axle Lube Rear | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 9 | 90003101 | 1 | 1000036113 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-HYM01 | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-HYM0190003101
789D | MCORS | Haul | TBA | DT199 | DT199 Repl AOC Fan Motor | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90003102 | 1 | 1000036114 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-MTFAN | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-MTFAN90003102
789D | MCORS | Haul | TBA | DT199 | DT199 Overhaul Accumulator Brake | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 10 | 90009313 | 1 | 1000072219 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BACCM | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BACCM90009313
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Valve Brake | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 18 | 90003107 | 1 | 1000036120 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRVLV | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRVLV90003107
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Rotochamber Front | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90009308 | 1 | 1000072409 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTFR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTFR90009308
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Rotochamber LHR | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072447 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTLR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTLR90009309
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Rotochamber RHR | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072485 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTRR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTRR90009309
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Valve Steering & AHS EH | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 10 | 90009881 | 1 | 1000078880 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRSYS-STVLV | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRSYS-STVLV90009881
789D | MCORS | Haul | TBA | DT199 | DT199 Ovhl Accumulator Hyd Steer Front | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072105 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCF | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCF90009314
789D | MCORS | Haul | TBA | DT199 | DT199 Ovhl Accumulator Hyd Steer Middle | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072143 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCM | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCM90009314
789D | MCORS | Haul | TBA | DT199 | DT199 Ovhl Accumulator Hyd Steering Rear | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072181 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCR90009314
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Pump Hoist & Brake | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 10 | 90003113 | 1 | 1000036127 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -HYDSYS-HOPMP | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -HYDSYS-HOPMP90003113
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Air Dryer | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 14 | 90003115 | 1 | 1000036130 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -PNEUMC-AIRDR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -PNEUMC-AIRDR90003115
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Brake Wheel RH | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 61 | 90003105 | 2 | 1000036117 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-AXLES-HUBRH | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRUCT-AXLES-HUBRH90003105
789D | MCORS | Haul | TBA | DT199 | DT199 Service Suspension Cylinders | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 27 | 90012840 | 1 | 1000106948 | 28.10.2027 | 11000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN | 7500 | 85978 | 21221 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN90012840
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Cyl Suspension LHF | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067902 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYLF | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYLF90003121
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Cyl Suspension RHF | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067904 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYRF | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYRF90003121
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Cyl Suspension LHR | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 42 | 90003122 | 1 | 1000036138 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYLR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYLR90003122
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Cyl Suspension RHR | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 42 | 90003122 | 1 | 1000036139 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYRR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYRR90003122
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Transmission System Hoses | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 8 | 90009871 | 1 | 1000078870 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -TRNSYS-TRANS-TRNHO | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -TRNSYS-TRANS-TRNHO90009871
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Torque Conv System Hoses | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 4 | 90009872 | 1 | 1000078871 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -TRNSYS-TRQUE-TRQHO | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -TRNSYS-TRQUE-TRQHO90009872
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Brake Oil Cooler Front | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90003108 | 1 | 1000080303 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BROCO-BROCF | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BROCO-BROCF90003108
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Brake System Hoses Rear | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 6 | 90009878 | 1 | 1000078877 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRHOR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRHOR90009878
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Brake System Hoses Front | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 12 | 90009879 | 1 | 1000078878 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRHOF | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRHOF90009879
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Brake System Air Lines | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 24 | 90009880 | 1 | 1000078879 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRAIR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRAIR90009880
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Steering System Hoses | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 24 | 90009882 | 1 | 1000078881 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -STRSYS-STHLF-STRHO | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -STRSYS-STHLF-STRHO90009882
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Hoist System Hoses | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 12 | 90009903 | 1 | 1000078875 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-HSTHO | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-HSTHO90009903
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Differential System Hoses | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 2 | 90009873 | 1 | 1000078872 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-DIFFL-DIFHO | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -FDRSYS-DIFFL-DIFHO90009873
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Fast Fill & SOS Hose | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 36 | 90012188 | 1 | 1000103994 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-FFSOS | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-FFSOS90012188
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Ladder Hoses | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 4 | 90012189 | 1 | 1000104052 | 28.10.2027 | 22000 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-LADHO | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-LADHO90012189
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Pump Drive Driveshaft Unis | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 4 | 90009874 | 1 | 1000036107 | 24.11.2027 | 11000 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR-DRSHT | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR-DRSHT90009874
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Pump Brake Control | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 5 | 90003106 | 1 | 1000036119 | 24.11.2027 | 11000 | CLB-MP-HAUL-DT199 -BRKSYS-HYFPP | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -BRKSYS-HYFPP90003106
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Brake Relay Valve | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 6 | 90009877 | 1 | 1000078876 | 24.11.2027 | 11000 | CLB-MP-HAUL-DT199 -BRKSYS-BRVRL | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -BRKSYS-BRVRL90009877
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Hyd Pump Steering Main | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 8 | 90003109 | 1 | 1000036122 | 03.12.2027 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STPMP | 7500 | 85978 | 20031 | CLB-MP-HAUL-DT199 -STRSYS-STPMP90003109
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Steering HMU | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 14 | 90003110 | 1 | 1000036123 | 03.12.2027 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STHMU | 7500 | 85978 | 20031 | CLB-MP-HAUL-DT199 -STRSYS-STHMU90003110
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Steering Link & Arm Rebush | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 45 | 90038355 | A1 | 1000385471 | 03.12.2027 | 30000 | CLB-MP-HAUL-DT199 -STRSYS-STLTR | 7500 | 85978 | 20031 | CLB-MP-HAUL-DT199 -STRSYS-STLTR90038355
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Drive Line Axle LH | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 8 | 90014551 | 1 | 1000123544 | 10.07.2027 | 30000 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX-AXLLH | 7500 | 85978 | 23065 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX-AXLLH90014551
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Drive Line Axle RH | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 8 | 90014552 | 1 | 1000123605 | 05.08.2027 | 30000 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX-AXLRH | 7500 | 85978 | 22478 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX-AXLRH90014552
789D | MCORS | Haul | TBA | DT199 | DT199 Repl Cyl Steering RH | 2027-10-28 | 2027-11-26 | 29 days | FY28 | 28 | 90003111 | 3 | 1000036125 | 07.08.2027 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STRCY-STCYR | 7500 | 85978 | 7443 | CLB-MP-HAUL-DT199 -STRSYS-STRCY-STCYR90003111
789D | MCORS | Haul | TBA | DT199 | MCORS Transport | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Opex Variation | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Capex Variation | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Additional Baseline Opex Truck Fleet | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Additional Baseline Capex Truck Fleet | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Capex Variation - Steer Box (if applicable) | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Minor Hosing Opex | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Baseline Harness (Not on strategy) Capex | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Variation Opex - Corrosions/Repairs | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | MCORS Site Labour Recovery - 789D | 2027-10-28 | 2027-11-26 | 29 days | FY28
789D | MCORS | Haul | TBA | DT199 | Transport & Unload | 2027-11-27 | 2027-11-30 | 3 days | FY28
789D | MCORS | Haul | TBA | DT199 | Recommissioning | 2027-12-01 | 2027-12-05 | 4 days | FY28
789D | MCORS | Haul | TBA | DT164 | DT164 - MCORS (EOL - 05/2030) | 2027-12-25 | 2028-02-08 | 45 days | FY28
789D | MCORS | Haul | TBA | DT164 | Decommissioning | 2027-12-25 | 2027-12-27 | 2 days | FY28
789D | MCORS | Haul | TBA | DT164 | Transport & Unload | 2027-12-28 | 2027-12-31 | 3 days | FY28
789D | MCORS | Haul | TBA | DT164 | DT164 - Baseline Scope | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Engine Cat 3516B | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 142 | 90017315 | 1 | 1000156477 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -ENGINE | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE90017315
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Radiator Engine Cooling | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 85 | 90003081 | 1 | 1000034156 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-RADTR | 7400 | 81875 | 32833 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-RADTR90003081
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Fuel Tank Mounts | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 16 | 90009887 | 1 | 1000078372 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -ENGINE-FUSYS-FULTK | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE-FUSYS-FULTK90009887
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Engine Pump Drive | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 62 | 90003089 | 1 | 1000034158 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR90003089
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Pump Drive Driveshaft Unis | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 4 | 90009874 | 1 | 1000034161 | 01.01.2028 | 11000 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT90009874
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Torque Converter | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 62 | 90003092 | 1 | 1000034159 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -TRNSYS-TRQUE | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -TRNSYS-TRQUE90003092
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Pump Torque Converter Charge | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 5 | 90003095 | 1 | 1000080167 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TCCPP | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TCCPP90003095
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Transmission Oil Cooler | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 13 | 90003532 | 1 | 1000040973 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -TRNSYS-TROLC | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -TRNSYS-TROLC90003532
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Drive Shaft Transmission | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 16 | 90017134 | 1 | 1000154369 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT90017134
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Differential | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 66 | 90003098 | 1 | 1000034164 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-DIFFL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-DIFFL90003098
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Final Drive LH | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 56 | 90003099 | 1 | 1000034165 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-FDRVE-FDRLH | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-FDRVE-FDRLH90003099
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Final Drive RH | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 56 | 90003100 | 1 | 1000034166 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-FDRVE-FDRRH | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-FDRVE-FDRRH90003100
789D | MCORS | Haul | TBA | DT164 | DT164 Repl AOC Fan Motor | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 5 | 90003102 | 1 | 1000034168 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-MTFAN | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-MTFAN90003102
789D | MCORS | Haul | TBA | DT164 | DT164 Overhaul Accumulator Brake | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 10 | 90009313 | 1 | 1000072184 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BACCM | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BACCM90009313
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Pump Brake Control | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 5 | 90003106 | 1 | 1000034173 | 01.01.2028 | 11000 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP | 7500 | 81875 | 7647 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP90003106
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Valve Brake | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 18 | 90003107 | 1 | 1000034174 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRVLV | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRVLV90003107
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Rotochamber Front | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 5 | 90009308 | 1 | 1000072374 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTFR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTFR90009308
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Rotochamber LHR | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072412 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTLR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTLR90009309
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Rotochamber RHR | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072450 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTRR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTRR90009309
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Valve Steering & AHS EH | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 10 | 90009881 | 1 | 1000078367 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRSYS-STVLV | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRSYS-STVLV90009881
789D | MCORS | Haul | TBA | DT164 | DT164 Ovhl Accumulator Hyd Steer Front | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072070 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCF | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCF90009314
789D | MCORS | Haul | TBA | DT164 | DT164 Ovhl Accumulator Hyd Steer Middle | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072108 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCM | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCM90009314
789D | MCORS | Haul | TBA | DT164 | DT164 Ovhl Accumulator Hyd Steering Rear | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072146 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCR90009314
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Pump Hoist & Brake | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 10 | 90003113 | 1 | 1000034181 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -HYDSYS-HOPMP | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -HYDSYS-HOPMP90003113
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Air Dryer | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 14 | 90003115 | 1 | 1000034184 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -PNEUMC-AIRDR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -PNEUMC-AIRDR90003115
789D | MCORS | Haul | TBA | DT164 | DT164 Ovhl Axle A Frame | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 60 | 90015390 | 1 | 1000130636 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-AFRME | 7500 | 81875 | 81875 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-AFRME90015390
789D | MCORS | Haul | TBA | DT164 | DT164 Ovhl Axle Housing Dogbone | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 42 | 90003118 | 1 | 1000034187 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-TAGLK | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-TAGLK90003118
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Brake Wheel LH | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 38 | 90003104 | 2 | 1000034170 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-AXLES-HUBLH | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-AXLES-HUBLH90003104
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Brake Wheel RH | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 61 | 90003105 | 2 | 1000034171 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-AXLES-HUBRH | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-AXLES-HUBRH90003105
789D | MCORS | Haul | TBA | DT164 | DT164 Service Suspension Cylinders | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 27 | 90012840 | 1 | 1000106872 | 01.01.2028 | 11000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN90012840
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Cyl Suspension LHF | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067762 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYLF | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYLF90003121
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Cyl Suspension RHF | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067764 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYRF | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYRF90003121
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Cyl Suspension LHR | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 42 | 90003122 | 1 | 1000034192 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYLR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYLR90003122
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Cyl Suspension RHR | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 42 | 90003122 | 1 | 1000034193 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYRR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYRR90003122
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Transmission System Hoses | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 8 | 90009871 | 1 | 1000078357 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -TRNSYS-TRANS-TRNHO | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -TRNSYS-TRANS-TRNHO90009871
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Torque Conv System Hoses | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 4 | 90009872 | 1 | 1000078358 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -TRNSYS-TRQUE-TRQHO | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -TRNSYS-TRQUE-TRQHO90009872
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Brake Relay Valve | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 6 | 90009877 | 1 | 1000078363 | 01.01.2028 | 11000 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL90009877
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Brake System Hoses Rear | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 6 | 90009878 | 1 | 1000078364 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRHOR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRHOR90009878
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Brake System Hoses Front | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 12 | 90009879 | 1 | 1000078365 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRHOF | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRHOF90009879
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Brake System Air Lines | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 24 | 90009880 | 1 | 1000078366 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRAIR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRAIR90009880
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Steering System Hoses | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 24 | 90009882 | 1 | 1000078368 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -STRSYS-STHLF-STRHO | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRSYS-STHLF-STRHO90009882
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Hoist System Hoses | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 12 | 90009903 | 1 | 1000078362 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-HSTHO | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-HSTHO90009903
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Differential System Hoses | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 2 | 90009873 | 1 | 1000078359 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-DIFFL-DIFHO | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-DIFFL-DIFHO90009873
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Fast Fill & SOS Hose | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 36 | 90012188 | 1 | 1000116333 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-FFSOS | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-FFSOS90012188
789D | MCORS | Haul | TBA | DT164 | DT164 Repl Ladder Hoses | 2028-01-01 | 2028-01-30 | 29 days | FY28 | 4 | 90012189 | 1 | 1000103997 | 01.01.2028 | 22000 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-LADHO | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-LADHO90012189
789D | MCORS | Haul | TBA | DT164 | MCORS Transport | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Opex Variation | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Capex Variation | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Additional Baseline Opex Truck Fleet | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Additional Baseline Capex Truck Fleet | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Capex Variation - Steer Box (if applicable) | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Minor Hosing Opex | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Baseline Harness (Not on strategy) Capex | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Variation Opex - Corrosions/Repairs | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | MCORS Site Labour Recovery - 789D | 2028-01-01 | 2028-01-30 | 29 days | FY28
789D | MCORS | Haul | TBA | DT164 | Recommissioning | 2028-01-31 | 2028-02-04 | 4 days | FY28
789D | MCORS | Haul | TBA | DT164 | Load & Transport | 2028-02-05 | 2028-02-08 | 3 days | FY28
789D | MCORS | Haul | TBA | DT181 | DT181 - MCORS (EOL - 02/2030) | 2028-03-01 | 2028-04-15 | 45 days | FY28
789D | MCORS | Haul | TBA | DT181 | Decommissioning | 2028-03-01 | 2028-03-03 | 2 days | FY28
789D | MCORS | Haul | TBA | DT181 | Load & Transport | 2028-03-04 | 2028-03-07 | 3 days | FY28
789D | MCORS | Haul | TBA | DT181 | DT181 - Baseline Scope | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Engine Cat 3516B | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 142 | 90017315 | 1 | 1000156749 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -ENGINE | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -ENGINE90017315
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Radiator Engine Cooling | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 85 | 90003081 | 1 | 1000035094 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-RADTR | 7400 | 83441 | 33433 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-RADTR90003081
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Fuel Tank Mounts | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 16 | 90009887 | 1 | 1000079651 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -ENGINE-FUSYS-FULTK | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -ENGINE-FUSYS-FULTK90009887
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Engine Pump Drive | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 62 | 90003089 | 1 | 1000035096 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR90003089
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Torque Converter | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 62 | 90003092 | 1 | 1000035097 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -TRNSYS-TRQUE | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TRQUE90003092
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Transmission | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 48 | 90003093 | 1 | 1000035098 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -TRNSYS-TRANS | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TRANS90003093
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Pump Transmission | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 7 | 90003096 | 1 | 1000035100 | 08.03.2028 | 11000 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TMCPP | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TMCPP90003096
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Transmission Oil Cooler | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 13 | 90003532 | 1 | 1000040990 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -TRNSYS-TROLC | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TROLC90003532
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Drive Shaft Transmission | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 16 | 90017134 | 1 | 1000154403 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-DRSHT | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -FDRSYS-DRSHT90017134
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Differential | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 66 | 90003098 | 1 | 1000035102 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-DIFFL | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -FDRSYS-DIFFL90003098
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Hyd Motor Axle Lube Rear | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 9 | 90003101 | 1 | 1000035105 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-HYM01 | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-HYM0190003101
789D | MCORS | Haul | TBA | DT181 | DT181 Repl AOC Fan Motor | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 5 | 90003102 | 1 | 1000035106 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-MTFAN | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-MTFAN90003102
789D | MCORS | Haul | TBA | DT181 | DT181 Overhaul Accumulator Brake | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 10 | 90009313 | 1 | 1000072201 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BACCM | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BACCM90009313
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Valve Brake | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 18 | 90003107 | 1 | 1000035112 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRVLV | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRVLV90003107
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Rotochamber Front | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 5 | 90009308 | 1 | 1000072391 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTFR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTFR90009308
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Rotochamber LHR | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072429 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTLR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTLR90009309
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Rotochamber RHR | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072467 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTRR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTRR90009309
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Valve Steering & AHS EH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 10 | 90009881 | 1 | 1000079646 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRSYS-STVLV | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRSYS-STVLV90009881
789D | MCORS | Haul | TBA | DT181 | DT181 Ovhl Accumulator Hyd Steer Front | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072087 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCF | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCF90009314
789D | MCORS | Haul | TBA | DT181 | DT181 Ovhl Accumulator Hyd Steer Middle | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072125 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCM | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCM90009314
789D | MCORS | Haul | TBA | DT181 | DT181 Ovhl Accumulator Hyd Steering Rear | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072163 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCR90009314
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Pump Hoist & Brake | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 10 | 90003113 | 1 | 1000035119 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -HYDSYS-HOPMP | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -HYDSYS-HOPMP90003113
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Air Dryer | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 14 | 90003115 | 1 | 1000035122 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -PNEUMC-AIRDR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -PNEUMC-AIRDR90003115
789D | MCORS | Haul | TBA | DT181 | DT181 Ovhl Axle A Frame | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 60 | 90015390 | 1 | 1000130652 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-AFRME | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-AFRME90015390
789D | MCORS | Haul | TBA | DT181 | DT181 Ovhl Axle Housing Dogbone | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 42 | 90003118 | 1 | 1000035125 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-TAGLK | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-TAGLK90003118
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake Wheel LH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 38 | 90003104 | 2 | 1000035108 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-AXLES-HUBLH | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-AXLES-HUBLH90003104
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake Wheel RH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 61 | 90003105 | 2 | 1000035109 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-AXLES-HUBRH | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-AXLES-HUBRH90003105
789D | MCORS | Haul | TBA | DT181 | DT181 Service Suspension Cylinders | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 27 | 90012840 | 1 | 1000106890 | 08.03.2028 | 11000 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN | 7500 | 83441 | 10065 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN90012840
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Cyl Suspension LHF | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067830 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYLF | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYLF90003121
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Cyl Suspension RHF | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067832 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYRF | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYRF90003121
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Cyl Suspension LHR | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 42 | 90003122 | 1 | 1000035130 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYLR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYLR90003122
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Cyl Suspension RHR | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 42 | 90003122 | 1 | 1000035131 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYRR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYRR90003122
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Transmission System Hoses | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 8 | 90009871 | 1 | 1000079636 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -TRNSYS-TRANS-TRNHO | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TRANS-TRNHO90009871
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Torque Conv System Hoses | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 4 | 90009872 | 1 | 1000079637 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -TRNSYS-TRQUE-TRQHO | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TRQUE-TRQHO90009872
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake Relay Valve | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 6 | 90009877 | 1 | 1000079642 | 08.03.2028 | 11000 | CLB-MP-HAUL-DT181 -BRKSYS-BRVRL | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRVRL90009877
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake Oil Cooler Front | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 5 | 90003108 | 1 | 1000080274 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BROCO-BROCF | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BROCO-BROCF90003108
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake System Hoses Rear | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 6 | 90009878 | 1 | 1000079643 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRHOR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRHOR90009878
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake System Hoses Front | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 12 | 90009879 | 1 | 1000079644 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRHOF | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRHOF90009879
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Brake System Air Lines | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 24 | 90009880 | 1 | 1000079645 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRAIR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRAIR90009880
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Steering System Hoses | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 24 | 90009882 | 1 | 1000079647 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -STRSYS-STHLF-STRHO | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRSYS-STHLF-STRHO90009882
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Hoist System Hoses | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 12 | 90009903 | 1 | 1000079641 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-HSTHO | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-HSTHO90009903
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Differential System Hoses | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 2 | 90009873 | 1 | 1000079638 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-DIFFL-DIFHO | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -FDRSYS-DIFFL-DIFHO90009873
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Fast Fill & SOS Hose | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 36 | 90012188 | 1 | 1000103976 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-FFSOS | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-FFSOS90012188
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Ladder Hoses | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 4 | 90012189 | 1 | 1000104034 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-LADHO | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-LADHO90012189
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Cyl Steering RH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 28 | 90003111 | 3 | 1000035117 | 14.05.2028 | 15000 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYR | 7500 | 83441 | 1688 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYR90003111
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Pump Brake Control | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 5 | 90003106 | 1 | 1000035111 | 25.05.2028 | 11000 | CLB-MP-HAUL-DT181 -BRKSYS-HYFPP | 7500 | 83441 | 8454 | CLB-MP-HAUL-DT181 -BRKSYS-HYFPP90003106
789D | MCORS | Haul | TBA | DT181 | DT181 1Y Air Tank LH External Inspect | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 1.5 | 90038753 | A1 | 1000389382 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH | 7500 | 83200 | 57009 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH90038753
789D | MCORS | Haul | TBA | DT181 | DT181 1Y Air Tank RH External Inspect | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 1.5 | 90038753 | A1 | 1000389384 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH | 7500 | 83200 | 57009 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH90038753
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Drive Line Axle LH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 8 | 90014551 | 1 | 1000123526 | 02.06.2028 | 30000 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX-AXLLH | 7500 | 83441 | 16291 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX-AXLLH90014551
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Drive Line Axle RH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 8 | 90014552 | 1 | 1000123587 | 02.06.2028 | 30000 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX-AXLRH | 7500 | 83441 | 16291 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX-AXLRH90014552
789D | MCORS | Haul | TBA | DT181 | DT181 Repl Cyl Steering LH | 2028-03-08 | 2028-04-06 | 29 days | FY28 | 28 | 90003111 | 2 | 1000035116 | 03.06.2028 | 15000 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYL | 7500 | 83441 | 16291 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYL90003111
789D | MCORS | Haul | TBA | DT181 | MCORS Transport | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Opex Variation | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Capex Variation | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Additional Baseline Opex Truck Fleet | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Additional Baseline Capex Truck Fleet | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Capex Variation - Steer Box (if applicable) | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Minor Hosing Opex | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Baseline Harness (Not on strategy) Capex | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Variation Opex - Corrosions/Repairs | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | MCORS Site Labour Recovery - 789D | 2028-03-08 | 2028-04-06 | 29 days | FY28
789D | MCORS | Haul | TBA | DT181 | Transport & Unload | 2028-04-07 | 2028-04-10 | 3 days | FY28
789D | MCORS | Haul | TBA | DT181 | Recommissioning | 2028-04-11 | 2028-04-15 | 4 days | FY28
789D | MCORS | Haul | TBA | DT184 | DT184 - MCORS (EOL - 02/2030) | 2028-04-19 | 2028-06-03 | 45 days | FY28
789D | MCORS | Haul | TBA | DT184 | Decommissioning | 2028-04-19 | 2028-04-21 | 2 days | FY28
789D | MCORS | Haul | TBA | DT184 | Load & Transport | 2028-04-22 | 2028-04-25 | 3 days | FY28
789D | MCORS | Haul | TBA | DT184 | DT184 - Baseline Scope | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Final Drive RH | 2028-03-12 | 2028-04-10 | 29 days | FY28 | 56 | 90003100 | 1 | 1000034052 | 12.03.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-FDRVE-FDRRH | 7500 | 83473 | 9952 | CLB-MP-HAUL-DT184 -FDRSYS-FDRVE-FDRRH90003100
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Engine Cat 3516B | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 142 | 90017315 | 1 | 1000156797 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -ENGINE | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -ENGINE90017315
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Radiator Engine Cooling | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 85 | 90003081 | 1 | 1000034042 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-RADTR | 7400 | 83473 | 31706 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-RADTR90003081
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Fuel Tank Mounts | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 16 | 90009887 | 1 | 1000078676 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -ENGINE-FUSYS-FULTK | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -ENGINE-FUSYS-FULTK90009887
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Pump Drive Driveshaft Unis | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 4 | 90009874 | 1 | 1000116261 | 26.04.2028 | 11000 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR-DRSHT | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR-DRSHT90009874
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Torque Converter | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 62 | 90003092 | 1 | 1000034045 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -TRNSYS-TRQUE | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -TRNSYS-TRQUE90003092
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Transmission | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 48 | 90003093 | 1 | 1000034046 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -TRNSYS-TRANS | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -TRNSYS-TRANS90003093
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Pump Torque Converter Charge | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90003095 | 1 | 1000080206 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TCCPP | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TCCPP90003095
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Transmission Oil Cooler | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 13 | 90003532 | 1 | 1000040993 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -TRNSYS-TROLC | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -TRNSYS-TROLC90003532
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Drive Shaft Transmission | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 16 | 90017134 | 1 | 1000154409 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-DRSHT | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-DRSHT90017134
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Differential | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 66 | 90003098 | 1 | 1000034050 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-DIFFL | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-DIFFL90003098
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Hyd Motor Axle Lube Rear | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 9 | 90003101 | 1 | 1000034053 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-HYM01 | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-HYM0190003101
789D | MCORS | Haul | TBA | DT184 | DT184 Repl AOC Fan Motor | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90003102 | 1 | 1000034054 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-MTFAN | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-MTFAN90003102
789D | MCORS | Haul | TBA | DT184 | DT184 Overhaul Accumulator Brake | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 10 | 90009313 | 1 | 1000072204 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BACCM | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BACCM90009313
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Pump Brake Control | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90003106 | 1 | 1000034059 | 26.04.2028 | 11000 | CLB-MP-HAUL-DT184 -BRKSYS-HYFPP | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-HYFPP90003106
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Valve Brake | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 18 | 90003107 | 1 | 1000034063 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRVLV | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRVLV90003107
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Rotochamber Front | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90009308 | 1 | 1000072394 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTFR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTFR90009308
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Rotochamber LHR | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072432 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTLR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTLR90009309
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Rotochamber RHR | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072470 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTRR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTRR90009309
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Valve Steering & AHS EH | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 10 | 90009881 | 1 | 1000078671 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRSYS-STVLV | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STVLV90009881
789D | MCORS | Haul | TBA | DT184 | DT184 Ovhl Accumulator Hyd Steer Front | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072090 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCF | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCF90009314
789D | MCORS | Haul | TBA | DT184 | DT184 Ovhl Accumulator Hyd Steer Middle | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072128 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCM | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCM90009314
789D | MCORS | Haul | TBA | DT184 | DT184 Ovhl Accumulator Hyd Steering Rear | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072166 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCR90009314
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Pump Hoist & Brake | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 10 | 90003113 | 1 | 1000034070 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -HYDSYS-HOPMP | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -HYDSYS-HOPMP90003113
789D | MCORS | Haul | TBA | DT184 | DT184 Ovhl Axle A Frame | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 60 | 90015390 | 1 | 1000130655 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-AFRME | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-AFRME90015390
789D | MCORS | Haul | TBA | DT184 | DT184 Ovhl Axle Housing Dogbone | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 42 | 90003118 | 1 | 1000034076 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-TAGLK | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-TAGLK90003118
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake Wheel LH | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 38 | 90003104 | 2 | 1000116262 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-AXLES-HUBLH | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-AXLES-HUBLH90003104
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake Wheel RH | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 61 | 90003105 | 2 | 1000116263 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-AXLES-HUBRH | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-AXLES-HUBRH90003105
789D | MCORS | Haul | TBA | DT184 | DT184 Service Suspension Cylinders | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 27 | 90012840 | 1 | 1000106893 | 26.04.2028 | 11000 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN | 7500 | 83473 | 21188 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN90012840
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Cyl Suspension LHF | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067842 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYLF | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYLF90003121
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Cyl Suspension LHR | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 42 | 90003122 | 1 | 1000116264 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYLR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYLR90003122
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Transmission System Hoses | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 8 | 90009871 | 1 | 1000078661 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -TRNSYS-TRANS-TRNHO | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -TRNSYS-TRANS-TRNHO90009871
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Torque Conv System Hoses | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 4 | 90009872 | 1 | 1000078662 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -TRNSYS-TRQUE-TRQHO | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -TRNSYS-TRQUE-TRQHO90009872
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake Relay Valve | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 6 | 90009877 | 1 | 1000078667 | 26.04.2028 | 11000 | CLB-MP-HAUL-DT184 -BRKSYS-BRVRL | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRVRL90009877
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake Oil Cooler Front | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 5 | 90003108 | 1 | 1000080281 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BROCO-BROCF | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BROCO-BROCF90003108
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake System Hoses Rear | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 6 | 90009878 | 1 | 1000078668 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRHOR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRHOR90009878
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake System Hoses Front | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 12 | 90009879 | 1 | 1000078669 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRHOF | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRHOF90009879
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Brake System Air Lines | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 24 | 90009880 | 1 | 1000078670 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRAIR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRAIR90009880
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Steering System Hoses | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 24 | 90009882 | 1 | 1000078672 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -STRSYS-STHLF-STRHO | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STHLF-STRHO90009882
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Hoist System Hoses | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 12 | 90009903 | 1 | 1000078666 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-HSTHO | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-HSTHO90009903
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Differential System Hoses | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 2 | 90009873 | 1 | 1000078663 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-DIFFL-DIFHO | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-DIFFL-DIFHO90009873
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Fast Fill & SOS Hose | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 36 | 90012188 | 1 | 1000103979 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-FFSOS | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-FFSOS90012188
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Ladder Hoses | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 4 | 90012189 | 1 | 1000104037 | 26.04.2028 | 22000 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-LADHO | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-LADHO90012189
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Cyl Suspension RHR | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 42 | 90003122 | 1 | 1000034082 | 09.06.2028 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYRR | 7500 | 83473 | 8112 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYRR90003122
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Cyl Steering LH | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 28 | 90003111 | 2 | 1000034067 | 04.07.2028 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYL | 7500 | 83473 | 15556 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYL90003111
789D | MCORS | Haul | TBA | DT184 | DT184 Repl Final Drive LH | 2028-04-26 | 2028-05-25 | 29 days | FY28 | 56 | 90003099 | 1 | 1000034051 | 03.08.2028 | 22000 | CLB-MP-HAUL-DT184 -FDRSYS-FDRVE-FDRLH | 7500 | 83473 | 6975 | CLB-MP-HAUL-DT184 -FDRSYS-FDRVE-FDRLH90003099
789D | MCORS | Haul | TBA | DT184 | MCORS Transport | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Opex Variation | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Capex Variation | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Additional Baseline Opex Truck Fleet | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Additional Baseline Capex Truck Fleet | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Capex Variation - Steer Box (if applicable) | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Minor Hosing Opex | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Baseline Harness (Not on strategy) Capex | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Variation Opex - Corrosions/Repairs | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | MCORS Site Labour Recovery - 789D | 2028-04-26 | 2028-05-25 | 29 days | FY28
789D | MCORS | Haul | TBA | DT184 | Transport & Unload | 2028-05-26 | 2028-05-29 | 3 days | FY28
789D | MCORS | Haul | TBA | DT184 | Recommissioning | 2028-05-30 | 2028-06-03 | 4 days | FY28
789D | MCORS | Haul | TBA | DT165 | DT165 - MCORS (EOL - 09/2030) | 2028-05-23 | 2028-07-07 | 45 days | FY28
789D | MCORS | Haul | TBA | DT165 | Decommissioning | 2028-05-23 | 2028-05-25 | 2 days | FY28
789D | MCORS | Haul | TBA | DT165 | Load & Transport | 2028-05-26 | 2028-05-29 | 3 days | FY28
789D | MCORS | Haul | TBA | DT165 | DT165 - Baseline Scope | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | DT165 1Y Air Tank LH External Inspect | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 1.5 | 90038753 | A1 | 1000389318 | 27.04.2028 | 12 Monthly | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH | 7500 | 78739 | 40861 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH90038753
789D | MCORS | Haul | TBA | DT165 | DT165 1Y Air Tank RH External Inspect | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 1.5 | 90038753 | A1 | 1000389320 | 27.04.2028 | 12 Monthly | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH | 7500 | 78739 | 40861 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH90038753
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Radiator Engine Cooling | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 85 | 90003081 | 1 | 1000034211 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-RADTR | 7400 | 78966 | 30583 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-RADTR90003081
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Engine Pump Drive | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 62 | 90003089 | 1 | 1000034213 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR90003089
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Pump Drive Driveshaft Unis | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 4 | 90009874 | 1 | 1000034216 | 30.05.2028 | 11000 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR-DRSHT | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR-DRSHT90009874
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Transmission | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 48 | 90003093 | 1 | 1000034215 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -TRNSYS-TRANS | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -TRNSYS-TRANS90003093
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Pump Transmission | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 7 | 90003096 | 1 | 1000034217 | 30.05.2028 | 11000 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TMCPP | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TMCPP90003096
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Transmission Oil Cooler | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 13 | 90003532 | 1 | 1000040974 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -TRNSYS-TROLC | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -TRNSYS-TROLC90003532
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Drive Shaft Transmission | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 16 | 90017134 | 1 | 1000154371 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-DRSHT | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-DRSHT90017134
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Differential | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 66 | 90003098 | 1 | 1000034219 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-DIFFL | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-DIFFL90003098
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Final Drive LH | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 56 | 90003099 | 1 | 1000034220 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-FDRVE-FDRLH | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-FDRVE-FDRLH90003099
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Final Drive RH | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 56 | 90003100 | 1 | 1000034221 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-FDRVE-FDRRH | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-FDRVE-FDRRH90003100
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Hyd Motor Axle Lube Rear | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 9 | 90003101 | 1 | 1000034222 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-HYM01 | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-HYM0190003101
789D | MCORS | Haul | TBA | DT165 | DT165 Repl AOC Fan Motor | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 5 | 90003102 | 1 | 1000034223 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-MTFAN | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-MTFAN90003102
789D | MCORS | Haul | TBA | DT165 | DT165 Overhaul Accumulator Brake | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 10 | 90009313 | 1 | 1000072185 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BACCM | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BACCM90009313
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Pump Brake Control | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 5 | 90003106 | 1 | 1000034228 | 30.05.2028 | 11000 | CLB-MP-HAUL-DT165 -BRKSYS-HYFPP | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-HYFPP90003106
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Valve Brake | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 18 | 90003107 | 1 | 1000034229 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRVLV | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRVLV90003107
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Rotochamber Front | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 5 | 90009308 | 1 | 1000072375 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTFR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTFR90009308
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Rotochamber LHR | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072413 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTLR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTLR90009309
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Rotochamber RHR | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 5 | 90009309 | 1 | 1000072451 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTRR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTRR90009309
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Valve Steering & AHS EH | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 10 | 90009881 | 1 | 1000078386 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRSYS-STVLV | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRSYS-STVLV90009881
789D | MCORS | Haul | TBA | DT165 | DT165 Ovhl Accumulator Hyd Steer Front | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072071 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCF | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCF90009314
789D | MCORS | Haul | TBA | DT165 | DT165 Ovhl Accumulator Hyd Steer Middle | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072109 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCM | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCM90009314
789D | MCORS | Haul | TBA | DT165 | DT165 Ovhl Accumulator Hyd Steering Rear | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 7 | 90009314 | 1 | 1000072147 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCR90009314
789D | MCORS | Haul | TBA | DT165 | DT165 Ovhl Axle Housing Dogbone | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 42 | 90003118 | 1 | 1000034242 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-TAGLK | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-TAGLK90003118
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Brake Wheel LH | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 38 | 90003104 | 2 | 1000034225 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-AXLES-HUBLH | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-AXLES-HUBLH90003104
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Cyl Suspension LHF | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067766 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYLF | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYLF90003121
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Cyl Suspension RHF | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 66 | 90003121 | 1 | 1000067768 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYRF | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYRF90003121
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Cyl Suspension LHR | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 42 | 90003122 | 1 | 1000034247 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYLR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYLR90003122
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Cyl Suspension RHR | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 42 | 90003122 | 1 | 1000034248 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYRR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYRR90003122
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Transmission System Hoses | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 8 | 90009871 | 1 | 1000078376 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -TRNSYS-TRANS-TRNHO | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -TRNSYS-TRANS-TRNHO90009871
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Torque Conv System Hoses | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 4 | 90009872 | 1 | 1000078377 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -TRNSYS-TRQUE-TRQHO | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -TRNSYS-TRQUE-TRQHO90009872
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Brake Relay Valve | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 6 | 90009877 | 1 | 1000078382 | 30.05.2028 | 11000 | CLB-MP-HAUL-DT165 -BRKSYS-BRVRL | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRVRL90009877
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Brake Oil Cooler Front | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 5 | 90003108 | 1 | 1000080236 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BROCO-BROCF | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BROCO-BROCF90003108
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Brake System Hoses Rear | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 6 | 90009878 | 1 | 1000078383 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRHOR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRHOR90009878
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Brake System Hoses Front | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 12 | 90009879 | 1 | 1000078384 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRHOF | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRHOF90009879
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Brake System Air Lines | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 24 | 90009880 | 1 | 1000078385 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRAIR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRAIR90009880
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Steering System Hoses | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 24 | 90009882 | 1 | 1000078387 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -STRSYS-STHLF-STRHO | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRSYS-STHLF-STRHO90009882
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Hoist System Hoses | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 12 | 90009903 | 1 | 1000078381 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-HSTHO | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-HSTHO90009903
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Differential System Hoses | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 2 | 90009873 | 1 | 1000078378 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -FDRSYS-DIFFL-DIFHO | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-DIFFL-DIFHO90009873
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Fast Fill & SOS Hose | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 36 | 90012188 | 1 | 1000103960 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-FFSOS | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-FFSOS90012188
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Ladder Hoses | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 4 | 90012189 | 1 | 1000103998 | 30.05.2028 | 22000 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-LADHO | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-LADHO90012189
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Fuel Tank Mounts | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 16 | 90009887 | 1 | 1000078391 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT165 -ENGINE-FUSYS-FULTK | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -ENGINE-FUSYS-FULTK90009887
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Steering Link & Arm Rebush | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 45 | 90038355 | A1 | 1000385403 | 06.08.2028 | 30000 | CLB-MP-HAUL-DT165 -STRSYS-STLTR | 7500 | 78966 | 14957 | CLB-MP-HAUL-DT165 -STRSYS-STLTR90038355
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Hyd Pump Steering Main | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 8 | 90003109 | 1 | 1000034231 | 06.08.2028 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STPMP | 7500 | 78966 | 14957 | CLB-MP-HAUL-DT165 -STRSYS-STPMP90003109
789D | MCORS | Haul | TBA | DT165 | DT165 Repl Steering HMU | 2028-05-30 | 2028-06-28 | 29 days | FY28 | 14 | 90003110 | 1 | 1000034232 | 06.08.2028 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STHMU | 7500 | 78966 | 14957 | CLB-MP-HAUL-DT165 -STRSYS-STHMU90003110
789D | MCORS | Haul | TBA | DT165 | MCORS Transport | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Opex Variation | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Capex Variation | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Additional Baseline Opex Truck Fleet | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Additional Baseline Capex Truck Fleet | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Capex Variation - Steer Box (if applicable) | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Minor Hosing Opex | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Baseline Harness (Not on strategy) Capex | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Variation Opex - Corrosions/Repairs | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | MCORS Site Labour Recovery - 789D | 2028-05-30 | 2028-06-28 | 29 days | FY28
789D | MCORS | Haul | TBA | DT165 | Transport & Unload | 2028-06-29 | 2028-07-02 | 3 days | FY28
789D | MCORS | Haul | TBA | DT165 | Recommissioning | 2028-07-03 | 2028-07-07 | 4 days | FY28
| MCORS |  |  |  | FY29 - MCORS | 2028-07-01 | 2029-06-30 | 364 days | FY29
| MCORS | Haul | Various |  | HAUL | 2028-07-01 | 2029-06-30 | 364 days | FY29
777F | MCORS | Haul | TBA | SV019 | SV019 - MCORS (EOL - 02/2033) | 2029-03-06 | 2029-04-17 | 42 days | FY29
777F | MCORS | Haul | TBA | SV019 | Decommissioning | 2029-03-06 | 2029-03-08 | 2 days | FY29
777F | MCORS | Haul | TBA | SV019 | Load & Transport | 2029-03-09 | 2029-03-12 | 3 days | FY29
777F | MCORS | Haul | TBA | SV019 | SV019 - Baseline Scope | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | SV019 Service Tank Module Midlife | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 1 | 90028958 | A1 | 1000288845 | 22.07.2028 | 18000 | CLB-MP-SUPP-SV019 -STRUCT-SVTNK | 2500 | 48856 | 48856 | CLB-MP-SUPP-SV019 -STRUCT-SVTNK90028958
777F | MCORS | Haul | TBA | SV019 | SV019 Repl Engine Cat C32 | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 194 | 90029079 | A1 | 1000290587 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -ENGINE | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -ENGINE90029079
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Engine Radiator | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 48 | 90003023 | A1 | 1000033850 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -ENGINE-COSYS-RADTR | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -ENGINE-COSYS-RADTR90003023
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Engine Aftercooler | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 3 | 90003029 | A1 | 1000033851 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -ENGINE-INTEX-AFTER | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -ENGINE-INTEX-AFTER90003029
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Torque Converter | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 26 | 90003035 | A1 | 1000033852 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -TRNSYS-TRQUE | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -TRNSYS-TRQUE90003035
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Transmission | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 50 | 90003036 | A1 | 1000033853 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -TRNSYS-TRANS | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -TRNSYS-TRANS90003036
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Pump Transmission | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 4 | 90003037 | A1 | 1000033854 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -TRNSYS-TRPMP | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -TRNSYS-TRPMP90003037
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Oil Cooler Trans | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 6 | 90003040 | A1 | 1000033857 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -TRNSYS-TROLC | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -TRNSYS-TROLC90003040
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Drive Shaft | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 2 | 90003041 | A1 | 1000033858 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -FDRSYS-DRSHT | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -FDRSYS-DRSHT90003041
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Differential | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 36 | 90003042 | A1 | 1000033859 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -FDRSYS-DIFFL | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -FDRSYS-DIFFL90003042
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Final Drive LH | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 48 | 90003043 | A1 | 1000033860 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE-FDRLH | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE-FDRLH90003043
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Final Drive RH | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 30 | 90007347 | 1 | 1000033861 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE-FDRRH | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE-FDRRH90007347
777F | MCORS | Haul | TBA | SV019 | SV019 Valve Brake | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 6 | 90003049 | A1 | 1000033868 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -BRKSYS-BRVLV | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -BRKSYS-BRVLV90003049
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Steering HMU | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 12 | 90003052 | A1 | 1000033871 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -STRSYS-STHMU | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -STRSYS-STHMU90003052
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Steering Hoses Lines | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 48 | 90003058 | A1 | 1000033878 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -STRSYS-STHLF | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -STRSYS-STHLF90003058
777F | MCORS | Haul | TBA | SV019 | SV019 Overhaul Airconditioner | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 24 | 90029085 | A1 | 1000290590 | 26.03.2029 | 9000 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-AIRCN | 2500 | 48856 | 2844 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-AIRCN90029085
777F | MCORS | Haul | TBA | SV019 | SV019 Refurbish A Frame | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 48 | 90003067 | A1 | 1000033888 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -STRUCT-CHASS-AFRME | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -STRUCT-CHASS-AFRME90003067
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Cylinder Suspension RHF | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 56 | 90003070 | A1 | 1000033893 | 26.03.2029 | 18000 | CLB-MP-SUPP-SV019 -STRUCT-SUSPN-SCYRF | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -STRUCT-SUSPN-SCYRF90003070
777F | MCORS | Haul | TBA | SV019 | SV019 Replace Operators Seat | 2029-03-13 | 2029-04-07 | 25 days | FY29 | 8 | 90003066 | A1 | 1000033887 | 04.04.2029 | 6000 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-SEATS | 2500 | 48856 | 5106 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-SEATS90003066
777F | MCORS | Haul | TBA | SV019 | MCORS Transport | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Opex Variation | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Capex Variation | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Additional Baseline Opex Truck Fleet | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Additional Baseline Capex Truck Fleet | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Minor Hosing Opex | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Baseline Harness (Not on strategy) Capex | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Variation Opex - Corrosions/Repairs | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | MCORS Site Labour Recovery - 777F | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | MCORS SV Module Refurbishment Midlife CAPEX | 2029-03-13 | 2029-04-07 | 25 days | FY29
777F | MCORS | Haul | TBA | SV019 | Transport & Unload | 2029-04-08 | 2029-04-11 | 3 days | FY29
777F | MCORS | Haul | TBA | SV019 | Recommissioning | 2029-04-12 | 2029-04-17 | 5 days | FY29
777F | MCORS | Haul | TBA | SV020 | SV020 - MCORS (EOL - 07/2034) | 2029-04-26 | 2029-06-07 | 42 days | FY29
777F | MCORS | Haul | TBA | SV020 | Decommissioning | 2029-04-26 | 2029-04-28 | 2 days | FY29
777F | MCORS | Haul | TBA | SV020 | Load & Transport | 2029-04-29 | 2029-05-02 | 3 days | FY29
777F | MCORS | Haul | TBA | SV020 | SV020 - Baseline Scope | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Operators Seat | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 8 | 90003066 | A1 | 1000033947 | 11.02.2029 | 6000 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-SEATS | 3300 | 44025 | 3632 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-SEATS90003066
777F | MCORS | Haul | TBA | SV020 | SV020 Steering Linkages | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 24 | 90003056 | A1 | 1000033936 | 03.05.2029 | 9000 | CLB-MP-SUPP-SV020 -STRSYS-STLTR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STLTR90003056
777F | MCORS | Haul | TBA | SV020 | SV020 Repl Engine Cat C32 | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 194 | 90029079 | A1 | 1000290594 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -ENGINE | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -ENGINE90029079
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Engine Radiator | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 48 | 90003023 | A1 | 1000033910 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -ENGINE-COSYS-RADTR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -ENGINE-COSYS-RADTR90003023
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Engine Aftercooler | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 3 | 90003029 | A1 | 1000033911 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -ENGINE-INTEX-AFTER | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -ENGINE-INTEX-AFTER90003029
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Drive Shaft | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 2 | 90003041 | A1 | 1000033918 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -FDRSYS-DRSHT | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -FDRSYS-DRSHT90003041
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Differential | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 36 | 90003042 | A1 | 1000033919 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -FDRSYS-DIFFL | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -FDRSYS-DIFFL90003042
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Steering HMU | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 12 | 90003052 | A1 | 1000033931 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRSYS-STHMU | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STHMU90003052
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Cylinder Steering LH | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 26 | 90003054 | A1 | 1000033933 | 03.05.2029 | 9000 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYL | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYL90003054
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Cylinder Steering RH | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 26 | 90003054 | A1 | 1000033934 | 03.05.2029 | 9000 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYR90003054
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Steering Hoses Lines | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 48 | 90003058 | A1 | 1000033938 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRSYS-STHLF | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STHLF90003058
777F | MCORS | Haul | TBA | SV020 | SV020 Overhaul Airconditioner | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 24 | 90029085 | A1 | 1000290597 | 03.05.2029 | 9000 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN | 3300 | 44025 | 4749 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN90029085
777F | MCORS | Haul | TBA | SV020 | SV020 Refurbish A Frame | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 48 | 90003067 | A1 | 1000033948 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-CHASS-AFRME | 3300 | 44025 | 25732 | CLB-MP-SUPP-SV020 -STRUCT-CHASS-AFRME90003067
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Cylinder Suspension RHF | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 56 | 90003070 | A1 | 1000033953 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYRF | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYRF90003070
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Cylinder Suspension LHR | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 50 | 90003071 | A1 | 1000033954 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYLR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYLR90003071
777F | MCORS | Haul | TBA | SV020 | SV020 Replace Cylinder Suspension RHR | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 50 | 90003071 | A1 | 1000033955 | 03.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYRR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYRR90003071
777F | MCORS | Haul | TBA | SV020 | SV020 Service Tank Module Midlife | 2029-05-03 | 2029-05-28 | 25 days | FY29 | 1 | 90028958 | A1 | 1000288847 | 13.05.2029 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-SVTNK | 3300 | 44025 | 44025 | CLB-MP-SUPP-SV020 -STRUCT-SVTNK90028958
777F | MCORS | Haul | TBA | SV020 | MCORS Transport | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Opex Variation | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Capex Variation | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Additional Baseline Opex Truck Fleet | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Additional Baseline Capex Truck Fleet | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Minor Hosing Opex | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Baseline Harness (Not on strategy) Capex | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Variation Opex - Corrosions/Repairs | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | MCORS Site Labour Recovery - 777F | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | MCORS SV Module Refurbishment Midlife CAPEX | 2029-05-03 | 2029-05-28 | 25 days | FY29
777F | MCORS | Haul | TBA | SV020 | Transport & Unload | 2029-05-29 | 2029-06-01 | 3 days | FY29
777F | MCORS | Haul | TBA | SV020 | Recommissioning | 2029-06-02 | 2029-06-07 | 5 days | FY29
| MCORS | Ancillary | Various |  | ANCILLARY | 2028-07-01 | 2029-06-30 | 364 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 - MCORS (EOL - 05/2025) | 2028-09-09 | 2028-10-05 | 26 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Decommissioning | 2028-09-09 | 2028-09-09 | 0.5 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Load & Transport | 2028-09-10 | 2028-09-12 | 2 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 - Baseline Scope | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Engine | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 246 | 90029036 | A1 | 1000290174 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-ENGINE | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-ENGINE90029036
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Radiator Engine Cooling | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 73 | 90003332 | 2 | 1000037989 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-RADTR | 2000 | 61520 | 16252 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-RADTR90003332
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Aftercooler Engine | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 8 | 90010846 | 1 | 1000089492 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-ENGINE-INTEX-AFTER | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-ENGINE-INTEX-AFTER90010846
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Torque Converter | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 72 | 90003342 | 1 | 1000037999 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-TRNSYS-TRQUE | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-TRNSYS-TRQUE90003342
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Transmission | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 72 | 90003343 | 1 | 1000038000 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-TRNSYS-TRANS | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-TRNSYS-TRANS90003343
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Bevel Gear | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 96 | 90003344 | 1 | 1000038001 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-TRNSYS-TRANS-BEVEL | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-TRNSYS-TRANS-BEVEL90003344
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Transmission Oil Cooler | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 14 | 90009667 | 1 | 1000075393 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-TRNSYS-TROLC | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-TRNSYS-TROLC90009667
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 T-Conv Trans Charge Pump Replace | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 10 | 90037704 | A1 | 1000374090 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-TRNSYS-TRPMP | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-TRNSYS-TRPMP90037704
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Final Drive RH | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 44 | 90003346 | 1 | 1000038004 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-FDRSYS-FDRRH | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-FDRSYS-FDRRH90003346
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Steer Clutch & Brake Assm LH | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 32 | 90003348 | 1 | 1000038006 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-BRKSTR-SCABL | 4400 | 61516 | 4630 | CLB-MP-DOZR-DZX024-BRKSTR-SCABL90003348
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Steer Clutch & Brake Assm RH | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 32 | 90003348 | 1 | 1000038007 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-BRKSTR-SCABR | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-BRKSTR-SCABR90003348
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Hyd Pump Cooling Fan | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 10 | 90009272 | 1 | 1000071479 | 20.09.2028 | 7000 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYFPP | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYFPP90009272
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Implement Valves Hyd | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 18 | 90003350 | 1 | 1000089512 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-HYDSYS-HDCVL | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-HYDSYS-HDCVL90003350
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Fan Cooling Motor Hyd | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 16 | 90003352 | 1 | 1000038011 | 20.09.2028 | 7000 | CLB-MP-DOZR-DZX024-HYDSYS-HDCFM | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-HYDSYS-HDCFM90003352
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Overhaul Airconditioner | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 48 | 90029041 | A1 | 1000290178 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-AIRCN | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-AIRCN90029041
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Equaliser Bar | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 96 | 90010849 | 1 | 1000089522 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-EQUAL | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-EQUAL90010849
D11T | MCORS | Ancillary | TBA | DZX024 | DZX024 Repl Hood Mounts | 2028-09-13 | 2028-09-30 | 17 days | FY29 | 12 | 90010848 | 1 | 1000089497 | 20.09.2028 | 14000 | CLB-MP-DOZR-DZX024-STRUCT-PNLGU | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-STRUCT-PNLGU90010848
D11T | MCORS | Ancillary | TBA | DZX024 | MCORS Transport | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Opex Variation | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Capex Variation | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Additional Baseline Opex Ancillary Fleet | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Additional Baseline Capex Ancillary Fleet | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Minor Hosing Opex | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Major Hosing Price Variances - Capex | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Baseline Harness (Not on strategy) Capex | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Variation Opex - Corrosions/Repairs | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Capex Variation - Cab Overhaul (if applicable) | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | MCORS Site Labour Recovery - D11T | 2028-09-13 | 2028-09-30 | 17 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Transport & Unload | 2028-10-01 | 2028-10-03 | 2 days | FY29
D11T | MCORS | Ancillary | TBA | DZX024 | Recommissioning | 2028-10-04 | 2028-10-05 | 1 day | FY29
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 - MCORS (EOL - 02/2035) | 2028-09-10 | 2028-10-26 | 46 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Decommissioning | 2028-09-10 | 2028-09-11 | 1 day | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Load & Transport | 2028-09-12 | 2028-09-15 | 3 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 - Baseline Scope | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Cyl Lift LH | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 60 | 90021484 | A1 | 1000207963 | 09.08.2028 | 10000 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLL | 5000 | 21377 | 9901 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLL90021484
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Cyl Lift RH | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 60 | 90021485 | A1 | 1000207964 | 09.08.2028 | 10000 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLR | 5000 | 21377 | 9901 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLR90021485
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Pump Transmission | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 8 | 90021465 | A1 | 1000208013 | 01.09.2028 | 8000 | CLB-MP-LOAD-WL6103-TRNSYS-TRPMP | 5000 | 21377 | 5580 | CLB-MP-LOAD-WL6103-TRNSYS-TRPMP90021465
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Operators Seat | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 4 | 90002797 | A1 | 1000208003 | 02.09.2028 | 6000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-SEATS | 5000 | 21377 | 1570 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-SEATS90002797
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Valve Hyd Control RH | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 48 | 90010626 | 1 | 1000224259 | 16.09.2028 | 32000 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV01 | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV0190010626
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Valve Hyd Control LH | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 48 | 90010625 | 1 | 1000224264 | 16.09.2028 | 32000 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV02 | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV0290010625
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Overhaul Boom | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 120.5 | 90021386 | A1 | 1000223997 | 16.09.2028 | 32000 | CLB-MP-LOAD-WL6103-STRUCT-CHASS-LIARM | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-STRUCT-CHASS-LIARM90021386
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Replace Brake Hoses | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 72 | 90024262 | A1 | 1000207954 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-BRKSYS-BRHLF | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-BRKSYS-BRHLF90024262
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Pump Brake | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 12 | 90021503 | A1 | 1000208007 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-BRKSYS-BRPMP | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-BRKSYS-BRPMP90021503
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Electrical Harness | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 72 | 90024248 | A1 | 1000207975 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-ELCTLV-HARNS | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-ELCTLV-HARNS90024248
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Radiator Engine Cooling | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 72 | 90021459 | A1 | 1000208016 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-RADTR | 5000 | 21364 | 6684 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-RADTR90021459
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Drive Shaft TCon to Trans | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 12 | 90021468 | A1 | 1000207970 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT01 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT0190021468
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Drive Shaft Trans to Rr Diff | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 12 | 90021469 | A1 | 1000207972 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT02 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT0290021469
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Lube Oil Cooler Front Axle | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90021475 | A1 | 1000207960 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-FDRSYS-HDOCA-HYOCF | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-FDRSYS-HDOCA-HYOCF90021475
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Lube Oil Cooler Rear Axle | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90024228 | A1 | 1000247663 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-FDRSYS-HDOCA-HYOCR | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-FDRSYS-HDOCA-HYOCR90024228
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Overhaul Auto Lubrication System | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 48 | 90021491 | A1 | 1000208000 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-GRSYST | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-GRSYST90021491
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Replace Hydraulic Hoses | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 96 | 90024263 | A1 | 1000207999 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HDHLF-HYDHO | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HDHLF-HYDHO90024263
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Pilot System Hoses | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 72 | 90024264 | A1 | 1000208005 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HDHLF-PILHO | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HDHLF-PILHO90024264
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Oil Cooler | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 20 | 90021490 | A1 | 1000207961 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HDOCO | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HDOCO90021490
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Reseal Tank Hyd | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90021393 | A1 | 1000224272 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HDTNK | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HDTNK90021393
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Motor Fan | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90021486 | A1 | 1000208002 | 10.11.2028 | 8000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM01 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM0190021486
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Motor Axle Cooler Front | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 6 | 90021488 | A1 | 1000208014 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM02 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM0290021488
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Motor Axle Cooler Rear | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 6 | 90021488 | A1 | 1000208015 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM03 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM0390021488
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Pump Implement RHF | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90021525 | A1 | 1000208008 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP01 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP0190021525
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Pump Pilot & Axl Cooling | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 6 | 90024222 | A1 | 1000247261 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP02 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP0290024222
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Imp Pump LHF | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90021529 | A1 | 1000247018 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP04 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP0490021529
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Pump Hyd Implement RHR | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90021528 | A1 | 1000208009 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP06 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP0690021528
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Replace Steering Hoses | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 72 | 90024260 | A1 | 1000208017 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-STRSYS-STHLF | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRSYS-STHLF90024260
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Hyd Pump Steering | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 10 | 90021505 | A1 | 1000208011 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-STRSYS-STPMP | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRSYS-STPMP90021505
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Cyl Steering LH | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 24 | 90024037 | A1 | 1000207965 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-STRSYS-STRCY-STCYL | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRSYS-STRCY-STCYL90024037
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Repl Transmission | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 192 | 90021499 | A1 | 1000208019 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-TRNSYS-TRANS | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-TRNSYS-TRANS90021499
993K | MCORS | Ancillary | TBA | WL6103 | WL6103 Replace Powertrain Hoses | 2028-09-16 | 2028-10-18 | 32 days | FY29 | 72 | 90024259 | 1 | 1000208006 | 10.11.2028 | 16000 | CLB-MP-LOAD-WL6103-TRNSYS-TRHLF | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-TRNSYS-TRHLF90024259
993K | MCORS | Ancillary | TBA | WL6103 | MCORS Transport | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Opex Variation | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Capex Variation | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Additional Baseline Opex Ancillary Fleet | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Additional Baseline Capex Ancillary Fleet | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Major Hosing Price Variances - Capex | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Variation Opex - Corrosions/Repairs | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Capex Variation - Cab Overhaul (if applicable) | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | MCORS Site Labour Recovery - 994H | 2028-09-16 | 2028-10-18 | 32 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Transport & Unload | 2028-10-19 | 2028-10-22 | 3 days | FY29
993K | MCORS | Ancillary | TBA | WL6103 | Recommissioning | 2028-10-23 | 2028-10-26 | 3 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | GR021 - MCORS (EOL - 08/2023) | 2028-09-29 | 2028-10-28 | 29.5 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Decommissioning | 2028-09-29 | 2028-09-29 | 0.5 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Load & Transport | 2028-09-30 | 2028-10-02 | 2 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | GR021 - Baseline Scope | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Engine Cat C18 | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 310 | 90015771 | 1 | 1000159900 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -ENGINE | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE90015771
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Radiator Engine Cooling | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 38 | 90002618 | A1 | 1000028646 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-RADTR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-RADTR90002618
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Aftercooler Engine | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 32 | 90002623 | A1 | 1000080588 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-AFTER | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-AFTER90002623
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Electrical Harness | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 48 | 90010000 | 1 | 1000080070 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -ELCTLV-HARNS | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ELCTLV-HARNS90010000
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Output Drive Shaft Unis | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 8 | 90033264 | A1 | 1000333929 | 10.10.2028 | 7000 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT01 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT0190033264
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Trans Input Drive Shaft Unis | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 8 | 90033267 | A1 | 1000333931 | 10.10.2028 | 7000 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT02 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT0290033267
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Service Brake LHF | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 36 | 90002640 | A1 | 1000028660 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLF | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLF90002640
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Service Brake RHF | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 36 | 90002640 | A1 | 1000028661 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRF | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRF90002640
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Service Brake LHR | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 50 | 90004548 | 1 | 1000028662 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLR90004548
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Service Brake RHR | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 50 | 90004548 | 1 | 1000028663 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRR90004548
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Brake Slack Adjuster LH | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 4 | 90002641 | A1 | 1000085640 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACL | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACL90002641
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Brake Slack Adjuster Rear | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 4 | 90002641 | A1 | 1000085641 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACR90002641
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Hyd Pump Secondary Steering | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 12 | 90002645 | A1 | 1000028667 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRSYS-STEMG-SESPP | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRSYS-STEMG-SESPP90002645
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Hyd Pump Implement | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 12 | 90002646 | A1 | 1000028668 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYIMP | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYIMP90002646
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Hyd Pump Differential Lock | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 4 | 90002649 | A1 | 1000028671 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-DIFFL | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-DIFFL90002649
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Hyd Fan Motor | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 16 | 90002651 | A1 | 1000028674 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT03 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT0390002651
24M | MCORS | Ancillary | TBA | GR021 | GR021 Overhaul Auto Lubrication System | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 2 | 90002660 | A1 | 1000028687 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -GRSYST-ALBPP | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -GRSYST-ALBPP90002660
24M | MCORS | Ancillary | TBA | GR021 | GR021 Overhaul Air Conditioner | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 48 | 90017475 | 1 | 1000160709 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN90017475
24M | MCORS | Ancillary | TBA | GR021 | GR021 Overhaul Drawbar Group | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 96 | 90002668 | A1 | 1000028694 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-DRWBR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-DRWBR90002668
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Blade Mounting Bracket LH | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 48 | 90002671 | A1 | 1000028696 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBL | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBL90002671
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Blade Mounting Bracket RH | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 48 | 90002671 | A1 | 1000028697 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBR | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBR90002671
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Steering System Hoses | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 24 | 90009996 | 1 | 1000080111 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-STRNG | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-STRNG90009996
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Power Train System Hoses | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 36 | 90009999 | 1 | 1000080110 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-PWTRN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-PWTRN90009999
24M | MCORS | Ancillary | TBA | GR021 | GR021 Replace Brake System Hoses | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 24 | 90009997 | 1 | 1000080108 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-BRKS | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-BRKS90009997
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Hydraulic System Hoses | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 48 | 90009998 | 1 | 1000080109 | 10.10.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-HYDSH | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-HYDSH90009998
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Gearbox Circle Drive Front | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 14 | 90002672 | A1 | 1000028698 | 31.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-CDBXF | 6000 | 73692 | 334 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-CDBXF90002672
24M | MCORS | Ancillary | TBA | GR021 | GR021 Repl Gearbox Circle Drive Rear | 2028-10-03 | 2028-10-24 | 21 days | FY29 | 14 | 90011066 | 1 | 1000028699 | 31.10.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-CDBXR | 6000 | 73692 | 334 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-CDBXR90011066
24M | MCORS | Ancillary | TBA | GR021 | MCORS Transport | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Opex Variation | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Capex Variation | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Additional Baseline Opex Ancillary Fleet | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Additional Baseline Capex Ancillary Fleet | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Minor Hosing Opex | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Major Hosing Price Variances - Capex | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Baseline Harness (Not on strategy) Capex | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Variation Opex - Corrosions/Repairs | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Capex Variation - Cab Overhaul (if applicable) | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | MCORS Site Labour Recovery - 24M | 2028-10-03 | 2028-10-24 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Transport & Unload | 2028-10-25 | 2028-10-27 | 2 days | FY29
24M | MCORS | Ancillary | TBA | GR021 | Recommissioning | 2028-10-28 | 2028-10-28 | 0.5 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | WL026 - MCORS (EOL - 10/2026) | 2028-10-03 | 2028-11-18 | 46 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Decommissioning | 2028-10-03 | 2028-10-04 | 1 day | FY29
994H | MCORS | Ancillary | TBA | WL026 | Load & Transport | 2028-10-05 | 2028-10-08 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | WL026 - Baseline Scope | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Transmission System Hoses | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 96 | 90026923 | A2 | 1000271631 | 12.09.2028 | 16000 | CLB-MP-LOAD-WL026 -TRNSYS-TRHLF-TRNHO | 6000 | 78554 | 19377 | CLB-MP-LOAD-WL026 -TRNSYS-TRHLF-TRNHO90026923
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Engine Cat 3516B | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 500 | 90021152 | 1 | 1000222435 | 15.09.2028 | 20000 | CLB-MP-LOAD-WL026 -ENGINE | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -ENGINE90021152
994H | MCORS | Ancillary | TBA | WL026 | WL026 Overhaul Engine Prelube | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 10 | 90021219 | 1 | 1000222443 | 15.09.2028 | 20000 | CLB-MP-LOAD-WL026 -ENGINE-LUBSY-PREPP | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -ENGINE-LUBSY-PREPP90021219
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Transmission Charge Pump | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 12 | 90002694 | A1 | 1000029057 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-TRPMP | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -TRNSYS-TRPMP90002694
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Hyd Pump Implement LH | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 24 | 90002723 | A1 | 1000029089 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP01 | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0190002723
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Hyd Pump Implement RH | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 24 | 90002724 | A1 | 1000029090 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP02 | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0290002724
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Hyd Pump Implement Centre | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 24 | 90002725 | A1 | 1000029091 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP03 | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0390002725
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Hyd Pump Pilot & Cooling | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 12 | 90002726 | A1 | 1000029092 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP04 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP0490002726
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Cyl Lift LH High Lift | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 40 | 90002727 | A1 | 1000029093 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLL | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLL90002727
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Auto Lube Pump | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 6 | 90002737 | A1 | 1000029100 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -GRSYST-ALBPP | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -GRSYST-ALBPP90002737
994H | MCORS | Ancillary | TBA | WL026 | WL026 Overhaul Air Conditioner | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 48 | 90021132 | 1 | 1000222433 | 15.09.2028 | 10000 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN90021132
994H | MCORS | Ancillary | TBA | WL026 | WL026 Adjust 250hr Initial Valve Set | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 24 | 90021246 | 1 | 1000222430 | 30.09.2028 | 250 | CLB-MP-LOAD-WL026 -ENGINE | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -ENGINE90021246
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Final Drive Position 1 | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 83 | 90002710 | A1 | 1000029073 | 09.10.2028 | 16000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR01 | 6000 | 78554 | 2933 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR0190002710
994H | MCORS | Ancillary | TBA | WL026 | WL026 Replace Artic Area Hyd Hosing | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 6 | 90020831 | 1 | 1000220520 | 10.10.2028 | 8 Monthly | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO90020831
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Transmission | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 74 | 90002692 | A1 | 1000029056 | 17.10.2028 | 16000 | CLB-MP-LOAD-WL026 -TRNSYS-TRANS | 6000 | 78554 | 2800 | CLB-MP-LOAD-WL026 -TRNSYS-TRANS90002692
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Front Drive Shaft Unis | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 8 | 90033188 | A1 | 1000333594 | 17.10.2028 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT04 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0490033188
994H | MCORS | Ancillary | TBA | WL026 | WL026 Articulation Overhaul | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 360 | 90032991 | A1 | 1000329979 | 17.10.2028 | 16000 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-ARTIC | 6000 | 78554 | 20428 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-ARTIC90032991
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Brake System Hoses Midlife | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 10.5 | 90026908 | A1 | 1000271628 | 17.10.2028 | 10000 | CLB-MP-LOAD-WL026 -BRKSYS-BRHLF-BRKHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -BRKSYS-BRHLF-BRKHO90026908
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Hyd System Hoses Midlife | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 10.5 | 90026914 | A1 | 1000271630 | 17.10.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-HYDHO | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-HYDHO90026914
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Transmission Transfer Case | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 74 | 90017029 | A1 | 1000153365 | 17.10.2028 | 16000 | CLB-MP-LOAD-WL026 -TRNSYS-TRTRF | 6000 | 78554 | 2800 | CLB-MP-LOAD-WL026 -TRNSYS-TRTRF90017029
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Shaft Rear PD To Cntr Brng | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 24 | 90033191 | A1 | 1000333595 | 05.12.2028 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT05 | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0590033191
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Front Pump Drv Drive Shaft | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 16 | 90033189 | A1 | 1000333597 | 05.12.2028 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT06 | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0690033189
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Centre Bearing Upper Shaft | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 24 | 90002702 | A1 | 1000029065 | 05.12.2028 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-UCTRB | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-UCTRB90002702
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Hyd Pump Steering RH | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 36 | 90002717 | A1 | 1000029083 | 05.12.2028 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP02 | 6000 | 78554 | 5988 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP0290002717
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Gearbox Pump Drive Rear | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 434 | 90002706 | A1 | 1000029069 | 08.12.2028 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-PMPDR-RRPDR | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -TRNSYS-PMPDR-RRPDR90002706
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Operators Seat | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 4 | 90002741 | A1 | 1000029102 | 12.12.2028 | 7000 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS | 6000 | 78554 | 6878 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS90002741
994H | MCORS | Ancillary | TBA | WL026 | WL026 Overhaul Park Brake & Centre Brg | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 36 | 90002711 | A1 | 1000087668 | 07.01.2029 | 10000 | CLB-MP-LOAD-WL026 -BRKSYS-BRPRK | 6000 | 78554 | 5453 | CLB-MP-LOAD-WL026 -BRKSYS-BRPRK90002711
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Axle Shaft Position 1 | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 12 | 90012242 | 1 | 1000101214 | 16.02.2029 | 32000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP1 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP190012242
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Axle Shaft Position 2 | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 12 | 90012242 | 1 | 1000101215 | 16.02.2029 | 32000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP2 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP290012242
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Axle Shaft Position 3 | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 12 | 90012242 | 1 | 1000101216 | 16.02.2029 | 32000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP3 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP390012242
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Axle Shaft Position 4 | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 12 | 90012242 | 1 | 1000101217 | 16.02.2029 | 32000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP4 | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP490012242
994H | MCORS | Ancillary | TBA | WL026 | WL026 Repl Centre Output Drive Shaft | 2028-10-09 | 2028-11-10 | 32 days | FY29 | 14 | 90033171 | A1 | 1000333591 | 21.02.2029 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT03 | 6000 | 78554 | 24710 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0390033171
994H | MCORS | Ancillary | TBA | WL026 | MCORS Transport | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Opex Variation | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Capex Variation | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Additional Baseline Opex Ancillary Fleet | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Additional Baseline Capex Ancillary Fleet | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Minor Hosing Opex | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Major Hosing Price Variances - Capex | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Baseline Harness (Not on strategy) Capex | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Variation Opex - Corrosions/Repairs | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Capex Variation - Cab Overhaul (if applicable) | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | MCORS Site Labour Recovery - 994H | 2028-10-09 | 2028-11-10 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Transport & Unload | 2028-11-11 | 2028-11-14 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL026 | Recommissioning | 2028-11-15 | 2028-11-18 | 3 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 - MCORS (EOL - 04/2036) | 2028-10-22 | 2028-11-28 | 37 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Decommissioning | 2028-10-22 | 2028-10-22 | 0.5 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Transport & Load | 2028-10-23 | 2028-10-25 | 2 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 - Baseline Scope | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Engine Cat C32 | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 404 | 90015797 | A2 | 1000189962 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-ENGINE | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-ENGINE90015797
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Radiator Engine Cooling | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 72 | 90002931 | A2 | 1000189980 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-RADTR | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-RADTR90002931
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Aftercooler Engine | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 12 | 90010217 | A2 | 1000190010 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-AFTER | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-AFTER90010217
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Torque Converter | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 164 | 90002943 | A2 | 1000189981 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-TRNSYS-TRQUE | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-TRNSYS-TRQUE90002943
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Hoses Powertrain System | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 48 | 90013049 | A2 | 1000190019 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-TRNSYS-TRHLF | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-TRNSYS-TRHLF90013049
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Shaft Trans to Cntr Bearing | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 8 | 90002949 | A2 | 1000268514 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT03 | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0390002949
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Front Differential | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 116 | 90002951 | A2 | 1000189989 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-FRDIF | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-FRDIF90002951
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Final Drive Position 1 | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 56 | 90002954 | A2 | 1000189992 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR01 | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR0190002954
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Final Drive Position 2 | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 56 | 90002954 | A2 | 1000189993 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR02 | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR0290002954
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Final Drive Position 3 | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 56 | 90002954 | A2 | 1000189994 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR03 | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR0390002954
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Final Drive Position 4 | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 56 | 90002954 | A2 | 1000189995 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR04 | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR0490002954
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Oil Cooler Front Axle Lube | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 6 | 90010219 | A2 | 1000190012 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-AXLEC-OILCR | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-AXLEC-OILCR90010219
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Brake Accumulator Front | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 4 | 90002955 | A2 | 1000189996 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM-BACCF | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM-BACCF90002955
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Brake Accumulator Rear | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 4 | 90002955 | A2 | 1000189997 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM-BACCR | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM-BACCR90002955
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Cylinder Steering LH | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 22 | 90002961 | A2 | 1000190002 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-STRSYS-STRCY-STCYL | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-STRSYS-STRCY-STCYL90002961
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Cylinder Steering RH | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 22 | 90002961 | A2 | 1000190003 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-STRSYS-STRCY-STCYR | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-STRSYS-STRCY-STCYR90002961
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Cylinder Blade Lift LH | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 12 | 90002965 | A2 | 1000190023 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BLCYL | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BLCYL90002965
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Cylinder Blade Lift RH | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 12 | 90002966 | A2 | 1000190024 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BLCYR | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BLCYR90002966
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Cylinder Blade Tilt LH | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 14 | 90002967 | A2 | 1000190025 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BTCYL | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BTCYL90002967
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Cylinder Blade Tilt RH | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 14 | 90002968 | A2 | 1000190026 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BTCYR | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BTCYR90002968
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Hyd & Steering Oil Cooler | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 24 | 90010218 | A2 | 1000190011 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-HYDSYS-HDOCO | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-HYDSYS-HDOCO90010218
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Overhaul Auto Lubrication System | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 96 | 90002971 | A2 | 1000190009 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-GRSYST | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-GRSYST90002971
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Operator Cabin Dash Bulbs | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 32 | 90002972 | A2 | 1000190020 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-STRUCT-CABIN | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-STRUCT-CABIN90002972
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Chassis Articulation | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 160 | 90002978 | A2 | 1000190022 | 26.10.2028 | 22000 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-ARTIC | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-ARTIC90002978
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Transmission | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 167 | 90002944 | A2 | 1000189982 | 08.12.2028 | 15000 | CLB-MP-DOZR-WD6106-TRNSYS-TRANS | 5900 | 30649 | 1191 | CLB-MP-DOZR-WD6106-TRNSYS-TRANS90002944
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Rear Differential | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 118 | 90002952 | A2 | 1000189990 | 13.01.2029 | 15000 | CLB-MP-DOZR-WD6106-FDRSYS-RRDIF | 5900 | 30649 | 599 | CLB-MP-DOZR-WD6106-FDRSYS-RRDIF90002952
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Trunnion Rear Differential | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 48 | 90002953 | A2 | 1000189991 | 13.01.2029 | 15000 | CLB-MP-DOZR-WD6106-FDRSYS-RRDIF-TRNON | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-FDRSYS-RRDIF-TRNON90002953
854K | MCORS | Ancillary | TBA | WD6106 | WD6106 Repl Hyd Motor & Pump Axl Cooling | 2028-10-26 | 2028-11-23 | 28 days | FY29 | 4 | 90002970 | A2 | 1000190008 | 13.01.2029 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM02 | 5900 | 30649 | 13829 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM0290002970
854K | MCORS | Ancillary | TBA | WD6106 | MCORS Transport | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Opex Variation | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Capex Variation | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Additional Baseline Opex Ancillary Fleet | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Additional Baseline Capex Ancillary Fleet | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Minor Hosing Opex | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Major Hosing Price Variances - Capex | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Baseline Harness (Not on strategy) Capex | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Variation Opex - Corrosions/Repairs | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Capex Variation - Cab Overhaul (if applicable) | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | MCORS Site Labour Recovery - 854K | 2028-10-26 | 2028-11-23 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Transport & Unload | 2028-11-24 | 2028-11-26 | 2 days | FY29
854K | MCORS | Ancillary | TBA | WD6106 | Recommissioning | 2028-11-27 | 2028-11-28 | 1 day | FY29
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 - MCORS (EOL 01/2032) | 2028-12-14 | 2029-01-20 | 37 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Decommissioning | 2028-12-14 | 2028-12-14 | 0.5 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Transport & Load | 2028-12-15 | 2028-12-17 | 2 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Baseline Scope | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Replace Brake System Hoses | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 48 | 90013050 | 1 | 1000179080 | 11.12.2028 | 15000 | CLB-MP-DOZR-WD6105-BRKSYS-BRHLF | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-BRKSYS-BRHLF90013050
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hyd Motor Fan | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 24 | 90002969 | A1 | 1000179071 | 11.12.2028 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM01 | 5900 | 55835 | 16081 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM0190002969
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hoses Steering System | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 48 | 90013051 | 1 | 1000179081 | 11.12.2028 | 15000 | CLB-MP-DOZR-WD6105-STRSYS-STHLF | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-STRSYS-STHLF90013051
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Replace Hyd Pilot System Hoses | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 24 | 90013052 | 1 | 1000231946 | 11.12.2028 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHPS | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHPS90013052
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hoses Main Hyd-Fan System | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 48 | 90013053 | 1 | 1000231947 | 11.12.2028 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHMH | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHMH90013053
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Brake Accumulator Front | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 6 | 90002955 | A1 | 1000179060 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM-BACCF | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM-BACCF90002955
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Brake Accumulator Rear | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 6 | 90002955 | A1 | 1000179061 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM-BACCR | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM-BACCR90002955
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Engine Cat C32 | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 398 | 90015797 | 1 | 1000178989 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-ENGINE | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE90015797
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Radiator Engine Cooling | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 72 | 90002931 | A1 | 1000179044 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-RADTR | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-RADTR90002931
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Aftercooler Engine | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 16 | 90010217 | 1 | 1000179075 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AFTER | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AFTER90010217
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Clean Engine Pre Cleaners | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 6 | 90015808 | 1 | 1000179040 | 18.12.2028 | 5500 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL90015808
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Shaft TConverter to Trans | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 6 | 90002947 | A1 | 1000268502 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT01 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT0190002947
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Final Drive Position 1 | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 80 | 90002954 | A1 | 1000179056 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR01 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR0190002954
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Final Drive Position 2 | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 80 | 90002954 | A1 | 1000179057 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR02 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR0290002954
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Final Drive Position 3 | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 80 | 90002954 | A1 | 1000179058 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR03 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR0390002954
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Final Drive Position 4 | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 80 | 90002954 | A1 | 1000179059 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR04 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR0490002954
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Front Differential | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 120 | 90002951 | A1 | 1000179053 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-FRDIF | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-FRDIF90002951
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Overhaul Auto Lubrication System | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 60 | 90002971 | A1 | 1000179073 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-GRSYST | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-GRSYST90002971
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Cylinder Steering LH | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 22 | 90002961 | A1 | 1000179066 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-STRSYS-STRCY-STCYL | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRSYS-STRCY-STCYL90002961
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Cylinder Steering RH | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 22 | 90002961 | A1 | 1000179067 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-STRSYS-STRCY-STCYR | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRSYS-STRCY-STCYR90002961
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Overhaul Airconditioner | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 48 | 90013087 | 2 | 1000195981 | 18.12.2028 | 11000 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN90013087
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hoses Powertrain System | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 48 | 90013049 | 1 | 1000179086 | 18.12.2028 | 22000 | CLB-MP-DOZR-WD6105-TRNSYS-TRHLF | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-TRNSYS-TRHLF90013049
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Pump Brake | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 6 | 90002957 | A1 | 1000179062 | 28.01.2029 | 15000 | CLB-MP-DOZR-WD6105-BRKSYS-BRPMP | 5900 | 55835 | 304 | CLB-MP-DOZR-WD6105-BRKSYS-BRPMP90002957
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hyd Motor & Pump Axl Cooling | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 6 | 90002970 | A1 | 1000179072 | 28.01.2029 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM02 | 5900 | 55835 | 304 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM0290002970
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hyd Pump Implement | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 8 | 90002962 | A1 | 1000179068 | 28.01.2029 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP01 | 5900 | 55835 | 297 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP0190002962
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Hyd Pump Cooling Fan | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 10 | 90002964 | A1 | 1000179070 | 28.01.2029 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP03 | 5900 | 55835 | 304 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP0390002964
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Rear Differential | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 122 | 90002952 | A1 | 1000179054 | 07.03.2029 | 15000 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF | 5900 | 55835 | 14684 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF90002952
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Overhaul Axle Oscillation Rear | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 120 | 90002953 | A1 | 1000179055 | 08.03.2029 | 15000 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF-TRNON | 5900 | 55835 | 14684 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF-TRNON90002953
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Cylinder Blade Lift LH | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 12 | 90002965 | A1 | 1000228665 | 27.03.2029 | 22000 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BLCYL | 5900 | 55835 | 6342 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BLCYL90002965
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Cylinder Blade Lift RH | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 12 | 90002966 | A1 | 1000228666 | 27.03.2029 | 22000 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BLCYR | 5900 | 55835 | 6342 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BLCYR90002966
854K | MCORS | Ancillary | TBA | WD6105 | WD6105 Repl Cylinder Blade Tilt LH | 2028-12-18 | 2029-01-15 | 28 days | FY29 | 14 | 90002967 | A1 | 1000228667 | 29.03.2029 | 22000 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BTCYL | 5900 | 55835 | 6342 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BTCYL90002967
854K | MCORS | Ancillary | TBA | WD6105 | MCORS Transport | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Opex Variation | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Capex Variation | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Additional Baseline Opex Ancillary Fleet | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Additional Baseline Capex Ancillary Fleet | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Minor Hosing Opex | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Major Hosing Price Variances - Capex | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Baseline Harness (Not on strategy) Capex | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Variation Opex - Corrosions/Repairs | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Capex Variation - Cab Overhaul (if applicable) | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | MCORS Site Labour Recovery - 854K | 2028-12-18 | 2029-01-15 | 28 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Transport & Unload | 2029-01-16 | 2029-01-18 | 2 days | FY29
854K | MCORS | Ancillary | TBA | WD6105 | Recommissioning | 2029-01-19 | 2029-01-20 | 1 day | FY29
24M | MCORS | Ancillary | TBA | GR018 | GR018 - MCORS (EOL - 08/2023) | 2028-12-15 | 2029-01-13 | 29.5 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Decommissioning | 2028-12-15 | 2028-12-15 | 0.5 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Load & Transport | 2028-12-16 | 2028-12-18 | 2 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | GR018 - Baseline Scope | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hyd Pump Implement | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 12 | 90002646 | A1 | 1000028540 | 25.10.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-HYIMP | 6000 | 73365 | 415 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-HYIMP90002646
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hyd Pump Steering Main | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 12 | 90002647 | A1 | 1000028541 | 25.10.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-HYSTP | 6000 | 73365 | 415 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-HYSTP90002647
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Rear Axle Assembly | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 128 | 90030396 | A1 | 1000303551 | 18.12.2028 | 14000 | CLB-MP-GRDR-GR018 -FDRSYS-DIFFL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -FDRSYS-DIFFL90030396
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Engine Cat C18 | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 310 | 90015771 | 1 | 1000159874 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -ENGINE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE90015771
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Radiator Engine Cooling | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 38 | 90002618 | A1 | 1000028518 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-RADTR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-RADTR90002618
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Aftercooler Engine | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 32 | 90002623 | A1 | 1000080586 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-AFTER | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-AFTER90002623
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Electrical Harness | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 48 | 90010000 | 1 | 1000080068 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -ELCTLV-HARNS | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ELCTLV-HARNS90010000
24M | MCORS | Ancillary | TBA | GR018 | GR018 Replace Torque Converter | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 122 | 90002630 | A1 | 1000028521 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -TRNSYS-TRQUE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -TRNSYS-TRQUE90002630
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Transmission Oil Cooler | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 6 | 90002632 | A1 | 1000028523 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -TRNSYS-TROLC | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -TRNSYS-TROLC90002632
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Output Drive Shaft Unis | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 8 | 90033264 | A1 | 1000333925 | 19.12.2028 | 7000 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT01 | 6000 | 73365 | 3877 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT0190033264
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Service Brake LHF | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 36 | 90002640 | A1 | 1000028532 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLF | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLF90002640
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Service Brake RHF | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 36 | 90002640 | A1 | 1000028533 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRF | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRF90002640
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Service Brake LHR | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 50 | 90004548 | 1 | 1000028534 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLR90004548
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Service Brake RHR | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 50 | 90004548 | 1 | 1000028535 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRR90004548
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Brake Slack Adjuster LH | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 4 | 90002641 | A1 | 1000085614 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACL90002641
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Brake Slack Adjuster Rear | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 4 | 90002641 | A1 | 1000085615 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACR90002641
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hyd Pump Secondary Steering | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 12 | 90002645 | A1 | 1000028539 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -STRSYS-STEMG-SESPP | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRSYS-STEMG-SESPP90002645
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hyd Pump Brake & Fan | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 12 | 90002648 | A1 | 1000028542 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-FANPP | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-FANPP90002648
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hyd Pump Differential Lock | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 4 | 90002649 | A1 | 1000028543 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-DIFFL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-DIFFL90002649
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hyd Fan Motor | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 16 | 90002651 | A1 | 1000028546 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT03 | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT0390002651
24M | MCORS | Ancillary | TBA | GR018 | GR018 Overhaul Auto Lubrication System | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 2 | 90002660 | A1 | 1000028559 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -GRSYST-ALBPP | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -GRSYST-ALBPP90002660
24M | MCORS | Ancillary | TBA | GR018 | GR018 Overhaul Air Conditioner | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 48 | 90017475 | 1 | 1000160707 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN90017475
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Axle Assembly Front | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 98 | 90002666 | A1 | 1000180092 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-AXLES | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-AXLES90002666
24M | MCORS | Ancillary | TBA | GR018 | GR018 Overhaul Drawbar Group | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 96 | 90002668 | A1 | 1000028566 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-DRWBR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-DRWBR90002668
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Blade Mounting Bracket LH | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 48 | 90002671 | A1 | 1000028568 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBL | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBL90002671
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Blade Mounting Bracket RH | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 48 | 90002671 | A1 | 1000028569 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBR90002671
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Steering System Hoses | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 24 | 90009996 | 1 | 1000080103 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-STRNG | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-STRNG90009996
24M | MCORS | Ancillary | TBA | GR018 | GR018 Replace Brake System Hoses | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 24 | 90009997 | 1 | 1000080100 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-BRKS | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-BRKS90009997
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Power Train System Hoses | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 36 | 90009999 | 1 | 1000080102 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-PWTRN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-PWTRN90009999
24M | MCORS | Ancillary | TBA | GR018 | GR018 Repl Hydraulic System Hoses | 2028-12-19 | 2029-01-09 | 21 days | FY29 | 48 | 90009998 | 1 | 1000080101 | 19.12.2028 | 14000 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-HYDSH | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-HYDSH90009998
24M | MCORS | Ancillary | TBA | GR018 | MCORS Transport | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Opex Variation | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Capex Variation | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Additional Baseline Opex Ancillary Fleet | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Additional Baseline Capex Ancillary Fleet | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Minor Hosing Opex | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Major Hosing Price Variances - Capex | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Baseline Harness (Not on strategy) Capex | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Variation Opex - Corrosions/Repairs | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Capex Variation - Cab Overhaul (if applicable) | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | MCORS Site Labour Recovery - 24M | 2028-12-19 | 2029-01-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Transport & Unload | 2029-01-10 | 2029-01-12 | 2 days | FY29
24M | MCORS | Ancillary | TBA | GR018 | Recommissioning | 2029-01-13 | 2029-01-13 | 0.5 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 - MCORS (EOL - 10/2037) | 2029-02-05 | 2029-03-03 | 26 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Decommissioning | 2029-02-05 | 2029-02-05 | 0.5 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Load & Transport | 2029-02-06 | 2029-02-08 | 2 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 - Baseline Scope | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Steer Clutch & Brake Assm LH | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 32 | 90018830 | A1 | 1000221464 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-BRKSTR-SCABL | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-BRKSTR-SCABL90018830
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Steer Clutch & Brake Assm RH | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 32 | 90018830 | A1 | 1000221465 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-BRKSTR-SCABR | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-BRKSTR-SCABR90018830
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Engine Cat C27 | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 82 | 90018843 | A1 | 1000221479 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-ENGINE | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-ENGINE90018843
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Radiator Engine Cooling | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 48 | 90018824 | A1 | 1000221457 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-ENGINE-COSYS-RADTR | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-ENGINE-COSYS-RADTR90018824
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Aftercooler Engine | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 8 | 90018836 | A1 | 1000221471 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AFTER | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AFTER90018836
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Wash Engine Pre Cleaners | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 2 | 90018848 | A1 | 1000221485 | 09.02.2029 | 9000 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AIRFL90018848
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Final Drive LH | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 48 | 90018829 | A1 | 1000313526 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-FDRSYS-FDRLH | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-FDRSYS-FDRLH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Final Drive RH | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 48 | 90018829 | A1 | 1000313527 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-FDRSYS-FDRRH | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-FDRSYS-FDRRH90018829
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Fan Cooling Motor Hyd | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 16 | 90018833 | A1 | 1000221468 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCFM | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCFM90018833
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Overhaul Air Conditioner | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 48 | 90018854 | A1 | 1000221492 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN | 4800 | 18270 | 18270 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN90018854
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Transmission | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 48 | 90018827 | A1 | 1000221460 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-TRNSYS-TRANS | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-TRNSYS-TRANS90018827
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Pump Trans & TCon Charge | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 10 | 90018828 | A1 | 1000221461 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-TRNSYS-TRPMP | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-TRNSYS-TRPMP90018828
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Torque Converter | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 60 | 90018826 | A1 | 1000221459 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-TRNSYS-TRQUE | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-TRNSYS-TRQUE90018826
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Pump Hyd Implement 2 | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 6 | 90021621 | A1 | 1000226716 | 09.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-HYDSYS-HYDPP-HYIP2 | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-HYDSYS-HYDPP-HYIP290021621
D10T2 | MCORS | Ancillary | TBA | DZ8226 | DZ8226 Repl Drive Shaft | 2029-02-09 | 2029-02-26 | 17 days | FY29 | 6 | 90033311 | A1 | 1000334040 | 26.02.2029 | 18000 | CLB-MP-DOZR-DZ8226-TRNSYS-DRSHT | 4800 | 18270 | 18270 | CLB-MP-DOZR-DZ8226-TRNSYS-DRSHT90033311
D10T2 | MCORS | Ancillary | TBA | DZ8226 | MCORS Transport | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Opex Variation | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Capex Variation | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Additional Baseline Opex Ancillary Fleet | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Additional Baseline Capex Ancillary Fleet | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Minor Hosing Opex | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Major Hosing Price Variances - Capex | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Baseline Harness (Not on strategy) Capex | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Variation Opex - Corrosions/Repairs | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Capex Variation - Cab Overhaul (if applicable) | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | MCORS Site Labour Recovery - D10T | 2029-02-09 | 2029-02-26 | 17 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Transport & Unload | 2029-02-27 | 2029-03-01 | 2 days | FY29
D10T2 | MCORS | Ancillary | TBA | DZ8226 | Recommissioning | 2029-03-02 | 2029-03-03 | 1 day | FY29
24M | MCORS | Ancillary | TBA | GR013 | GR013 - MCORS (EOL - 12/2023) | 2029-03-15 | 2029-04-13 | 29.5 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Decommissioning | 2029-03-15 | 2029-03-15 | 0.5 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Load & Transport | 2029-03-16 | 2029-03-18 | 2 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | GR013 - Baseline Scope | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Hyd Pump Steering Main | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 12 | 90002647 | A1 | 1000028477 | 07.02.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYSTP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYSTP90002647
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Radiator Engine Cooling | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 38 | 90002618 | A1 | 1000028454 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-RADTR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-RADTR90002618
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Aftercooler Engine | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 32 | 90002623 | A1 | 1000080585 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-AFTER | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-AFTER90002623
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Electrical Harness | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 48 | 90010000 | 1 | 1000080067 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -ELCTLV-HARNS | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -ELCTLV-HARNS90010000
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Torque Converter | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 122 | 90002630 | A1 | 1000028457 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TRQUE | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TRQUE90002630
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Transmission | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 122 | 90002631 | A1 | 1000028458 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TRANS | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TRANS90002631
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Transmission Oil Cooler | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 6 | 90002632 | A1 | 1000028459 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TROLC | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TROLC90002632
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Pump Transmission | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 20 | 90002633 | A1 | 1000028460 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -TRNSYS-TRPMP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -TRNSYS-TRPMP90002633
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Rear Axle Assembly | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 128 | 90030396 | A1 | 1000303549 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -FDRSYS-DIFFL | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -FDRSYS-DIFFL90030396
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Service Brake LHF | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 36 | 90002640 | A1 | 1000028468 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLF | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLF90002640
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Service Brake RHF | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 36 | 90002640 | A1 | 1000028469 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRF | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRF90002640
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Service Brake LHR | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 50 | 90004548 | 1 | 1000028470 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLR90004548
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Service Brake RHR | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 50 | 90004548 | 1 | 1000028471 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRR90004548
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Brake Slack Adjuster LH | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 4 | 90002641 | A1 | 1000085612 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACL | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACL90002641
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Brake Slack Adjuster Rear | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 4 | 90002641 | A1 | 1000085613 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACR90002641
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Hyd Pump Secondary Steering | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 12 | 90002645 | A1 | 1000028475 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -STRSYS-STEMG-SESPP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRSYS-STEMG-SESPP90002645
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Hyd Pump Brake & Fan | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 12 | 90002648 | A1 | 1000028478 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-FANPP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-FANPP90002648
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Hyd Pump Differential Lock | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 4 | 90002649 | A1 | 1000028479 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-DIFFL | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-DIFFL90002649
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Hyd Fan Motor | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 16 | 90002651 | A1 | 1000028482 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT03 | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT0390002651
24M | MCORS | Ancillary | TBA | GR013 | GR013 Overhaul Auto Lubrication System | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 2 | 90002660 | A1 | 1000028495 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -GRSYST-ALBPP | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -GRSYST-ALBPP90002660
24M | MCORS | Ancillary | TBA | GR013 | GR013 Overhaul Drawbar Group | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 96 | 90002668 | A1 | 1000028502 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-DRWBR | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-DRWBR90002668
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Power Train System Hoses | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 36 | 90009999 | A1 | 1000080078 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-PWTRN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-PWTRN90009999
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Hydraulic System Hoses | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 48 | 90009998 | 1 | 1000080077 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-HYDSH | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-HYDSH90009998
24M | MCORS | Ancillary | TBA | GR013 | GR013 Replace Brake System Hoses | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 24 | 90009997 | 1 | 1000080076 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-BRKS | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-BRKS90009997
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Steering System Hoses | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 24 | 90009996 | 1 | 1000080079 | 19.03.2029 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-STRNG | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-STRNG90009996
24M | MCORS | Ancillary | TBA | GR013 | GR013 Repl Operators Seat | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 4 | 90002663 | A1 | 1000028497 | 11.04.2029 | 7000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS | 6000 | 71626 | 4801 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS90002663
24M | MCORS | Ancillary | TBA | GR013 | GR013 Engine Midlife complete | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 72 | 90015782 | 1 | 1000159873 | 20.05.2029 | 7000 | CLB-MP-GRDR-GR013 -ENGINE | 6000 | 71626 | 4169 | CLB-MP-GRDR-GR013 -ENGINE90015782
24M | MCORS | Ancillary | TBA | GR013 | GR013 Service Major Air Conditioner | 2029-03-19 | 2029-04-09 | 21 days | FY29 | 24 | 90017472 | 1 | 1000160700 | 20.05.2029 | 7000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN90017472
24M | MCORS | Ancillary | TBA | GR013 | MCORS Transport | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Opex Variation | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Capex Variation | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Additional Baseline Opex Ancillary Fleet | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Additional Baseline Capex Ancillary Fleet | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Minor Hosing Opex | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Major Hosing Price Variances - Capex | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Baseline Harness (Not on strategy) Capex | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Variation Opex - Corrosions/Repairs | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Capex Variation - Cab Overhaul (if applicable) | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | MCORS Site Labour Recovery - 24M | 2029-03-19 | 2029-04-09 | 21 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Transport & Unload | 2029-04-10 | 2029-04-12 | 2 days | FY29
24M | MCORS | Ancillary | TBA | GR013 | Recommissioning | 2029-04-13 | 2029-04-13 | 0.5 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | WL263 - MCORS (EOL (10/2029) | 2029-05-15 | 2029-06-30 | 46 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Decommissioning | 2029-05-15 | 2029-05-16 | 1 day | FY29
994H | MCORS | Ancillary | TBA | WL263 | Load & Transport | 2029-05-17 | 2029-05-20 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | WL026 - Baseline Scope | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Lift LH High Lift | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 40 | 90002727 | A1 | 1000112683 | 01.03.2029 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLL | 6000 | 60624 | 4601 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLL90002727
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Steering Hyd Pump Secondary | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 8 | 90002719 | A1 | 1000088579 | 16.03.2029 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP04 | 6000 | 60624 | 4273 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP0490002719
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Transmission Charge Pump | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 12 | 90002694 | A1 | 1000088551 | 16.03.2029 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-TRPMP | 6000 | 60624 | 4273 | CLB-MP-LOAD-WL263 -TRNSYS-TRPMP90002694
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Thermostats | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 6 | 90021139 | 1 | 1000222554 | 05.04.2029 | 5000 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-THERM | 6000 | 60721 | 11302 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-THERM90021139
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Service Air Conditioner | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90021130 | 1 | 1000222544 | 05.04.2029 | 5000 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN90021130
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Lift RH High Lift | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 40 | 90002727 | A1 | 1000112684 | 10.04.2029 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLR | 6000 | 60624 | 3938 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLR90002727
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Electrical Harness | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 36 | 90010123 | 1 | 1000088600 | 15.05.2029 | 20000 | CLB-MP-LOAD-WL263 -ELCTLV-HARNS | 6000 | 60721 | 3363 | CLB-MP-LOAD-WL263 -ELCTLV-HARNS90010123
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Radiator Engine Cooling | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 54 | 90002682 | A1 | 1000088548 | 15.05.2029 | 20000 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-RADTR | 6000 | 60721 | 3363 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-RADTR90002682
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Brake Accumulator Front | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 12 | 90002714 | A1 | 1000088573 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC-BACCF | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC-BACCF90002714
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Brake Accumulator Rear | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 12 | 90002714 | A1 | 1000088574 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC-BACCR | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC-BACCR90002714
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Brake System Hoses | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 48 | 90026921 | A1 | 1000271592 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -BRKSYS-BRHLF-BRKHO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRHLF-BRKHO90026921
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Brake Oil Cooler | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 72 | 90002715 | A1 | 1000088575 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -BRKSYS-BROCC | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BROCC90002715
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Brake Cooling | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 8 | 90002713 | A1 | 1000088572 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP0290002713
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Overhaul Park Brake & Centre Brg | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 36 | 90002711 | A1 | 1000088602 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL263 -BRKSYS-BRPRK | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRPRK90002711
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Front Differential | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 98 | 90002707 | A1 | 1000088564 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -FDRSYS-FRDIF | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -FDRSYS-FRDIF90002707
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Rear Differential | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 98 | 90002708 | A1 | 1000088565 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -FDRSYS-RRDIF | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -FDRSYS-RRDIF90002708
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Overhaul Rear Axle Trunnion | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 96 | 90002709 | A1 | 1000088566 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -FDRSYS-RRDIF-TRNON | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -FDRSYS-RRDIF-TRNON90002709
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Bucket LH High Lift | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 36 | 90017978 | A1 | 1000131516 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYL | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYL90017978
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hydraulic System Hoses | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 96 | 90026922 | A1 | 1000271594 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-HYDHO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-HYDHO90026922
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Replace Pilot System Hoses | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 96 | 90009731 | 2 | 1000088597 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-PILHO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-PILHO90009731
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Oil Cooler | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 96 | 90002733 | A1 | 1000088586 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-HDOCO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDOCO90002733
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Reseal Tank Hyd | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 12 | 90010623 | 1 | 1000088601 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-HDTNK-HYT01 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDTNK-HYT0190010623
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Valve Implement Ctrl LH | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90010965 | 1 | 1000112589 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV-HYV01 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV-HYV0190010965
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Valve Implement Ctrl RH | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90010966 | 1 | 1000112596 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV-HYV02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV-HYV0290010966
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Implement RH | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90002724 | A1 | 1000088583 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0290002724
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Implement Centre | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90002725 | A1 | 1000088584 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP03 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0390002725
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pilot Accumulator | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 4 | 90012174 | 1 | 1000112610 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -HYDSYS-PACCM | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-PACCM90012174
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Main Airhoses & Valves | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 18 | 90011137 | A1 | 1000112603 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -PNEUMC-PNHLF | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -PNEUMC-PNHLF90011137
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Replace Steering System Hoses | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 96 | 90009732 | 1 | 1000088598 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STHLF-STRHO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRSYS-STHLF-STRHO90009732
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Steering Neutralizer Valves | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 6 | 90002720 | A1 | 1000088594 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STNVS | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRSYS-STNVS90002720
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Steering RH | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 36 | 90002717 | A1 | 1000088577 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP0290002717
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Steer & Brake Oil Cooler Pump | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 8 | 90002718 | A1 | 1000088578 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP03 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP0390002718
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Reseal Steering & Brake Tank | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 36 | 90010963 | 1 | 1000112582 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STTNK | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRSYS-STTNK90010963
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Input Drive Shaft | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 12 | 90033166 | A1 | 1000333503 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT01 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0190033166
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Rear Output Drive Shaft | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 14 | 90033168 | A1 | 1000333505 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0290033168
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Centre Output Drive Shaft | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 14 | 90033171 | A1 | 1000333507 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT03 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0390033171
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Front Drive Shaft | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 16 | 90033175 | A1 | 1000333509 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT04 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0490033175
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Shaft Rear PD To Cntr Brng | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90033191 | A1 | 1000333511 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT05 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0590033191
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Front Pump Drv Drive Shaft | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 16 | 90033189 | A1 | 1000333513 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT06 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0690033189
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Centre Bearing Upper Shaft | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 24 | 90002702 | A1 | 1000088559 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-UCTRB | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-UCTRB90002702
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Gearbox Pump Drive Rear | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 434 | 90002706 | A1 | 1000088563 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR-RRPDR | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR-RRPDR90002706
994H | MCORS | Ancillary | Fortescue | WL263 | WL263 Repl Transmission Oil Cooler | 2029-05-21 | 2029-06-22 | 32 days | FY29 | 36 | 90002695 | A1 | 1000088552 | 21.05.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-TROLC | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-TROLC90002695
994H | MCORS | Ancillary | TBA | WL263 | MCORS Transport | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Opex Variation | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Capex Variation | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Additional Baseline Opex Ancillary Fleet | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Additional Baseline Capex Ancillary Fleet | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Minor Hosing Opex | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Major Hosing Price Variances - Capex | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Baseline Harness (Not on strategy) Capex | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Variation Opex - Corrosions/Repairs | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Capex Variation - Cab Overhaul (if applicable) | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | MCORS Site Labour Recovery - 994H | 2029-05-21 | 2029-06-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Transport & Unload | 2029-06-23 | 2029-06-26 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL263 | Recommissioning | 2029-06-27 | 2029-06-30 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | WL025 - MCORS (EOL - 02/2029) | 2029-06-14 | 2029-07-30 | 46 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Decommissioning | 2029-06-14 | 2029-06-15 | 1 day | FY29
994H | MCORS | Ancillary | TBA | WL025 | Load & Transport | 2029-06-16 | 2029-06-19 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | WL025 - Baseline Scope | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | WL025 Replace Artic Area Hyd Hosing | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 6 | 90020831 | 1 | 1000220519 | 30.05.2029 | 8 Monthly | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO90020831
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Engine Cat 3516B | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 500 | 90021152 | 1 | 1000222413 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -ENGINE | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ENGINE90021152
994H | MCORS | Ancillary | TBA | WL025 | WL025 Overhaul Engine Prelube | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 10 | 90021219 | 1 | 1000222421 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -ENGINE-LUBSY-PREPP | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ENGINE-LUBSY-PREPP90021219
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Electrical Harness | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90010123 | 1 | 1000081875 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -ELCTLV-HARNS | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ELCTLV-HARNS90010123
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Transmission Charge Pump | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 12 | 90002694 | A1 | 1000028992 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-TRPMP | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-TRPMP90002694
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Gearbox Pump Drive Rear | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 434 | 90002706 | A1 | 1000029004 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-PMPDR-RRPDR | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-PMPDR-RRPDR90002706
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Rear Output Drive Shaft | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 14 | 90033168 | A1 | 1000333577 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT02 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0290033168
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Shaft Rear PD To Cntr Brng | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90033191 | A1 | 1000333583 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT05 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0590033191
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Front Differential | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 98 | 90002707 | A1 | 1000029005 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -FDRSYS-FRDIF | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -FDRSYS-FRDIF90002707
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Rear Differential | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 98 | 90002708 | A1 | 1000029006 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -FDRSYS-RRDIF | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -FDRSYS-RRDIF90002708
994H | MCORS | Ancillary | TBA | WL025 | WL025 Overhaul Rear Axle Trunnion | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 96 | 90002709 | A1 | 1000029007 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -FDRSYS-RRDIF-TRNON | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -FDRSYS-RRDIF-TRNON90002709
994H | MCORS | Ancillary | TBA | WL025 | WL025 Overhaul Park Brake & Centre Brg | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90002711 | A1 | 1000087667 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -BRKSYS-BRPRK | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -BRKSYS-BRPRK90002711
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Brake Oil Cooler | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 72 | 90002715 | A1 | 1000029016 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -BRKSYS-BROCC | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -BRKSYS-BROCC90002715
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Pump Steering LH | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90002716 | A1 | 1000029017 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP01 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP0190002716
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Pump Steering RH | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90002717 | A1 | 1000029018 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP02 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP0290002717
994H | MCORS | Ancillary | TBA | WL025 | WL025 Reseal Steering & Brake Tank | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90010963 | 1 | 1000090050 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STTNK | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRSYS-STTNK90010963
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Pump Implement RH | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90002724 | A1 | 1000029025 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP02 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0290002724
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Pump Implement Centre | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90002725 | A1 | 1000029026 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP03 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0390002725
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Pump Pilot & Cooling | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 12 | 90002726 | A1 | 1000029027 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP04 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0490002726
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Cyl Lift RH High Lift | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 40 | 90002727 | A1 | 1000029029 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLR | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLR90002727
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Cyl Bucket LH High Lift | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90017978 | A1 | 1000029030 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYL | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYL90017978
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Cyl Bucket RH High Lift | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 36 | 90017977 | A1 | 1000029031 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYR | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYR90017977
994H | MCORS | Ancillary | TBA | WL025 | WL025 Reseal Tank Hyd | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 12 | 90010623 | 1 | 1000087658 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-HDTNK-HYT01 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDTNK-HYT0190010623
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Oil Cooler | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 96 | 90002733 | A1 | 1000029032 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-HDOCO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDOCO90002733
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Valve Implement Ctrl LH | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90010965 | 1 | 1000090183 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-HDVLV-HYV01 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDVLV-HYV0190010965
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Valve Implement Ctrl RH | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90010966 | 1 | 1000090184 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-HDVLV-HYV02 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDVLV-HYV0290010966
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hyd Pilot Accumulator | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 4 | 90012174 | 1 | 1000100310 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-PACCM | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-PACCM90012174
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Main Airhoses & Valves | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 18 | 90011137 | A1 | 1000093194 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -PNEUMC-PNHLF |  |  |  | CLB-MP-LOAD-WL025 -PNEUMC-PNHLF90011137
994H | MCORS | Ancillary | TBA | WL025 | WL025 Overhaul Air Conditioner | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 48 | 90021132 | 1 | 1000222411 | 16.06.2029 | 10000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN90021132
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Brake System Hoses | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 48 | 90026921 | A1 | 1000271621 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -BRKSYS-BRHLF-BRKHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -BRKSYS-BRHLF-BRKHO90026921
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Hydraulic System Hoses | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 96 | 90026922 | A1 | 1000271623 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-HYDHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-HYDHO90026922
994H | MCORS | Ancillary | TBA | WL025 | WL025 Fr Frame Grease Hoses | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90010326 | 1 | 1000105481 | 16.06.2029 | 20000 | CLB-MP-LOAD-WL025 -GRSYST-FFGHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -GRSYST-FFGHO90010326
994H | MCORS | Ancillary | TBA | WL025 | WL025 Adjust 250hr Initial Valve Set | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 24 | 90021246 | 1 | 1000222408 | 01.07.2029 | 250 | CLB-MP-LOAD-WL025 -ENGINE | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ENGINE90021246
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Ctr Output Drive Shaft Unis | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 8 | 90033173 | A1 | 1000333580 | 01.07.2029 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT03 | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0390033173
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Front Drive Shaft Unis | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 8 | 90033188 | A1 | 1000333582 | 01.07.2029 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT04 | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0490033188
994H | MCORS | Ancillary | TBA | WL025 | WL025 Articulation Overhaul | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 360 | 90032991 | A1 | 1000329978 | 14.08.2029 | 16000 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-ARTIC | 6000 | 64740 | 13629 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-ARTIC90032991
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Operators Seat | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 4 | 90002741 | A1 | 1000029037 | 16.08.2029 | 7000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS90002741
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Cyl Lift LH High Lift | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 40 | 90002727 | A1 | 1000029028 | 10.09.2029 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLL | 6000 | 64588 | 1336 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLL90002727
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Final Drive Position 1 | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 83 | 90002710 | A1 | 1000029008 | 24.06.2028 | 16000 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR01 | 6000 | 64740 | 4453 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR0190002710
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Final Drive Position 2 | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 83 | 90002710 | A1 | 1000029009 | 24.06.2028 | 16000 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR02 | 6000 | 64740 | 4453 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR0290002710
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Final Drive Position 3 | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 83 | 90002710 | A1 | 1000029010 | 24.06.2028 | 16000 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR03 | 6000 | 64740 | 4453 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR0390002710
994H | MCORS | Ancillary | TBA | WL025 | WL025 Repl Final Drive Position 4 | 2029-06-20 | 2029-07-22 | 32 days | FY29 | 83 | 90002710 | A1 | 1000029011 | 24.06.2028 | 16000 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR04 | 6000 | 64740 | 4453 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR0490002710
994H | MCORS | Ancillary | TBA | WL025 | MCORS Transport | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Opex Variation | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Capex Variation | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Additional Baseline Opex Ancillary Fleet | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Additional Baseline Capex Ancillary Fleet | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Minor Hosing Opex | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Major Hosing Price Variances - Capex | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Baseline Harness (Not on strategy) Capex | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Variation Opex - Corrosions/Repairs | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Capex Variation - Cab Overhaul (if applicable) | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | MCORS Site Labour Recovery - 994H | 2029-06-20 | 2029-07-22 | 32 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Transport & Unload | 2029-07-23 | 2029-07-26 | 3 days | FY29
994H | MCORS | Ancillary | TBA | WL025 | Recommissioning | 2029-07-27 | 2029-07-30 | 3 days | FY29
| Onsite Shut |  | Fortescue |  | ONSITE SHUTDOWNS
| Onsite Shut |  | Fortescue |  | FY27 - ONSITE SHUTDOWNS | 2026-07-01 | 2027-06-30 | 364 days | FY27
| Onsite Shut | Haul | Fortescue |  | HAUL | 2026-07-01 | 2027-06-30 | 364 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 - Onsite Shut | 2026-07-01 | 2026-07-22 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Engine Cat 3516B | 2026-07-01 | 2026-07-22 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156605 | 25.06.2026 | 22000 | CLB-MP-HAUL-DT172 -ENGINE | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Cyl Suspension RHF | 2026-07-01 | 2026-07-22 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067796 | 01.02.2028 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYRF | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 - Onsite Shut | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Fuel Tank Mounts | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078486 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -ENGINE-FUSYS-FULTK | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Pump Drive Driveshaft Unis | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 4 | 90009874 | 1 | 1000034493 | 19.10.2026 | 11000 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR-DRSHT | 7500 | 91119 | 24071 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Pump Transmission | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 7 | 90003096 | 1 | 1000034494 | 08.05.2026 | 11000 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP | 7500 | 91119 | 12852 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Drive Shaft Transmission | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 16 | 90017134 | 1 | 1000154381 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-DRSHT | 7500 | 91119 | 33937 | CLB-MP-HAUL-DT170 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Differential | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 66 | 90003098 | 1 | 1000034496 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-DIFFL | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Final Drive LH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 56 | 90003099 | 1 | 1000034497 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-FDRVE-FDRLH | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Final Drive RH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 56 | 90003100 | 1 | 1000034498 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-FDRVE-FDRRH | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Hyd Motor Axle Lube Rear | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 9 | 90003101 | 1 | 1000034499 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-HYM01 | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Overhaul Accumulator Brake | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072190 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BACCM | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Valve Brake | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 18 | 90003107 | 1 | 1000034506 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRVLV | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Rotochamber Front | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072380 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTFR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Rotochamber LHR | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072418 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTLR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Rotochamber RHR | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072456 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTRR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Pump Hoist & Brake | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 10 | 90003113 | 1 | 1000034513 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -HYDSYS-HOPMP | 7500 | 91119 | 29811 | CLB-MP-HAUL-DT170 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Ovhl Axle A Frame | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 60 | 90015390 | 1 | 1000130642 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-AFRME | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Ovhl Axle Housing Dogbone | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 42 | 90003118 | 1 | 1000034519 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-TAGLK | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Cyl Suspension LHR | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 42 | 90003122 | 1 | 1000034524 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYLR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Cyl Suspension RHR | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 42 | 90003122 | 1 | 1000034525 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYRR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Hoist System Hoses | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078476 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-HSTHO | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Differential System Hoses | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078473 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-DIFFL-DIFHO | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Engine Cat 3516B | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156573 | 15.08.2026 | 22000 | CLB-MP-HAUL-DT170 -ENGINE | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Radiator Engine Cooling | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 85 | 90003081 | 1 | 1000034488 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-RADTR | 7400 | 91119 | 21744 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Engine Pump Drive | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 62 | 90003089 | 1 | 1000106790 | 18.08.2026 | 22000 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Torque Converter | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 62 | 90003092 | 1 | 1000034491 | 25.08.2026 | 22000 | CLB-MP-HAUL-DT170 -TRNSYS-TRQUE | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Pump Torque Converter Charge | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 5 | 90003095 | 1 | 1000080172 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TCCPP | 7500 | 91119 | 33938 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Air Dryer | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 14 | 90003115 | 1 | 1000034516 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -PNEUMC-AIRDR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Transmission System Hoses | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078471 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -TRNSYS-TRANS-TRNHO | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Torque Conv System Hoses | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078472 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -TRNSYS-TRQUE-TRQHO | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake Oil Cooler Front | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080261 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BROCO-BROCF | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Service Suspension Cylinders | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 27 | 90012840 | 1 | 1000106879 | 10.08.2026 | 11000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN | 7500 | 91119 | 21730 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Steering Link & Arm Rebush | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 45 | 90038355 | A1 | 1000385413 | 15.08.2026 | 30000 | CLB-MP-HAUL-DT170 -STRSYS-STLTR | 7500 | 91119 | 29788 | CLB-MP-HAUL-DT170 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Pump Brake Control | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 5 | 90003106 | 1 | 1000106789 | 19.10.2026 | 11000 | CLB-MP-HAUL-DT170 -BRKSYS-HYFPP | 7500 | 91119 | 9337 | CLB-MP-HAUL-DT170 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Valve Steering & AHS EH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 10 | 90009881 | 1 | 1000078481 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRSYS-STVLV | 7500 | 91119 | 29788 | CLB-MP-HAUL-DT170 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Cyl Steering LH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 28 | 90003111 | 2 | 1000034510 | 19.10.2026 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYL | 7500 | 91119 | 13406 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Cyl Steering RH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 28 | 90003111 | 3 | 1000034511 | 19.10.2026 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYR | 7500 | 91119 | 13406 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Ovhl Accumulator Hyd Steer Front | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072076 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCF | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Ovhl Accumulator Hyd Steer Middle | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072114 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCM | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Ovhl Accumulator Hyd Steering Rear | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072152 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake Wheel LH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 38 | 90003104 | 2 | 1000034502 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-AXLES-HUBLH | 7500 | 91119 | 24782 | CLB-MP-HAUL-DT170 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake Wheel RH | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 61 | 90003105 | 2 | 1000034503 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-AXLES-HUBRH | 7500 | 91119 | 24782 | CLB-MP-HAUL-DT170 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Service Suspension Cylinders | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 27 | 90012840 | 1 | 1000106879 | 22.03.2025 | 11000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN | 7500 | 91119 | 21730 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Cyl Suspension LHF | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067786 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYLF | 7500 | 91119 | 24782 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake Relay Valve | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 6 | 90009877 | 1 | 1000078477 | 19.10.2026 | 11000 | CLB-MP-HAUL-DT170 -BRKSYS-BRVRL | 7500 | 91119 | 24132 | CLB-MP-HAUL-DT170 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake System Hoses Rear | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078478 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRHOR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake System Hoses Front | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078479 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRHOF | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Brake System Air Lines | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078480 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRAIR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Steering System Hoses | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078482 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -STRSYS-STHLF-STRHO | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Fast Fill & SOS Hose | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103965 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-FFSOS | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT170 | DT170 Repl Ladder Hoses | 2026-07-30 | 2026-08-20 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104023 | 14.08.2026 | 22000 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-LADHO | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT170 | CAT 789 Header Tank + Platforms | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | CAT 789D Fuel Tanks replacement | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | CAT 789 Chassis Harness Replacement | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | CAT 789 Axle Housing Replacement | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | CAT 789 Steering Arms | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | CAT 789 Air Boxes Replacement | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT170 | Repurposed: Cat 789D Coolant Expansion Tank | 2026-07-30 | 2026-08-20 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 - Onsite Shut | 2026-08-27 | 2026-09-17 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Engine Cat 3516B | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156765 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -ENGINE | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Radiator Engine Cooling | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 85 | 90003081 | 1 | 1000035149 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-RADTR | 7400 | 92002 | 21376 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Fuel Tank Mounts | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078657 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -ENGINE-FUSYS-FULTK | 7500 | 92002 | 4021 | CLB-MP-HAUL-DT182 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Engine Pump Drive | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 62 | 90003089 | 1 | 1000035151 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Pump Drive Driveshaft Unis | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035154 | 22.10.2026 | 11000 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR-DRSHT | 7500 | 92002 | 9389 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Torque Converter | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 62 | 90003092 | 1 | 1000035152 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TRQUE | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Transmission | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 48 | 90003093 | 1 | 1000035153 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TRANS | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Pump Transmission | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 7 | 90003096 | 1 | 1000035155 | 11.02.2026 | 11000 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP | 7500 | 92002 | 14699 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Transmission Oil Cooler | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 13 | 90003532 | 1 | 1000040991 | 02.01.2026 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TROLC | 7500 | 92002 | 26654 | CLB-MP-HAUL-DT182 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Drive Shaft Transmission | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 16 | 90017134 | 1 | 1000154405 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-DRSHT | 7500 | 92002 | 32209 | CLB-MP-HAUL-DT182 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Overhaul Accumulator Brake | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072202 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BACCM | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Valve Brake | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035167 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRVLV | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Rotochamber Front | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072392 | 03.07.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTFR | 7500 | 92002 | 22684 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Rotochamber LHR | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072430 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTLR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Hyd Pump Steering Main | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 8 | 90003109 | 1 | 1000035169 | 17.10.2026 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STPMP | 7500 | 92002 | 13503 | CLB-MP-HAUL-DT182 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Steering HMU | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 14 | 90003110 | 1 | 1000035170 | 14.10.2026 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STHMU | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Cyl Steering LH | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 28 | 90003111 | 2 | 1000035171 | 14.10.2026 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYL | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Cyl Steering RH | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 28 | 90003111 | 3 | 1000035172 | 14.10.2026 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYR | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Ovhl Accumulator Hyd Steer Front | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072088 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCF | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Ovhl Accumulator Hyd Steer Middle | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072126 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCM | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Ovhl Accumulator Hyd Steering Rear | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072164 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Steering Ball Studs | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 35 | 90038356 | A1 | 1000385436 | 19.10.2026 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STLTR | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STLTR90038356
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Cyl Hoist LH | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 49 | 90003114 | 1 | 1000035175 | 23.07.2026 | 28000 | CLB-MP-HAUL-DT182 -HYDSYS-HOCYL-HCYLL | 7500 | 92002 | 28258 | CLB-MP-HAUL-DT182 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Air Dryer | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 14 | 90003115 | 1 | 1000035177 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -PNEUMC-AIRDR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Ovhl Axle A Frame | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 60 | 90015390 | 1 | 1000130653 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-AFRME | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Ovhl Axle Housing Dogbone | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 42 | 90003118 | 1 | 1000035180 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-TAGLK | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Brake Wheel LH | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 38 | 90003104 | 2 | 1000035163 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-AXLES-HUBLH | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Cyl Suspension LHF | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067834 | 30.12.2026 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYLF | 7500 | 92002 | 18987 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Cyl Suspension LHR | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035185 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYLR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Transmission System Hoses | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078642 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TRANS-TRNHO | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Torque Conv System Hoses | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078643 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TRQUE-TRQHO | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Brake Oil Cooler Front | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080276 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BROCO-BROCF | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Brake System Hoses Rear | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078649 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRHOR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Brake System Hoses Front | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078650 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRHOF | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Brake System Air Lines | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078651 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRAIR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Steering System Hoses | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078653 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -STRSYS-STHLF-STRHO | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Hoist System Hoses | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078647 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-HSTHO | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Differential System Hoses | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078644 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-DIFFL-DIFHO | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Fast Fill & SOS Hose | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103977 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-FFSOS | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT182 | DT182 Repl Ladder Hoses | 2026-08-27 | 2026-09-17 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104035 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-LADHO | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT182 | CAT 789 Air Boxes Replacement | 2026-08-27 | 2026-09-17 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT182 | CAT 789 Chassis Harness Replacement | 2026-08-27 | 2026-09-17 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT182 | CAT 789 Header Tank + Platforms | 2026-08-27 | 2026-09-17 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT182 | CAT 789 Axle Housing Replacement | 2026-08-27 | 2026-09-17 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 - Onsite Shut | 2026-09-24 | 2026-10-15 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Engine Cat 3516B | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156813 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -ENGINE | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Radiator Engine Cooling | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 85 | 90003081 | 1 | 1000035259 | 07.03.2027 | 22000 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-RADTR | 7400 | 92088 | 92088 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Fuel Tank Mounts | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078695 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -ENGINE-FUSYS-FULTK | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Engine Pump Drive | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 62 | 90003089 | 1 | 1000035261 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Pump Drive Driveshaft Unis | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035264 | 08.10.2026 | 11000 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR-DRSHT | 7500 | 92088 | 9689 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Torque Converter | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 62 | 90003092 | 1 | 1000035262 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -TRNSYS-TRQUE | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Transmission | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 48 | 90003093 | 1 | 1000035263 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -TRNSYS-TRANS | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Pump Torque Converter Charge | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 5 | 90003095 | 1 | 1000080207 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TCCPP | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Transmission Oil Cooler | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 13 | 90003532 | 1 | 1000040994 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -TRNSYS-TROLC | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Differential | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 66 | 90003098 | 1 | 1000035267 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-DIFFL | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Final Drive LH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 56 | 90003099 | 1 | 1000035268 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-FDRVE-FDRLH | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Final Drive RH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 56 | 90003100 | 1 | 1000035269 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-FDRVE-FDRRH | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Hyd Motor Axle Lube Rear | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 9 | 90003101 | 1 | 1000035270 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-HYM01 | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Overhaul Accumulator Brake | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072205 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BACCM | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Valve Brake | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035277 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRVLV | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Rotochamber LHR | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072433 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTLR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Rotochamber RHR | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072471 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTRR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake Slack Adjuster Front | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 4 | 90009306 | 1 | 1000072243 | 24.07.2026 | 18000 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACF | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACF90009306
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake Slack Adjuster Rear | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 4 | 90009307 | 1 | 1000072281 | 24.07.2026 | 18000 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACR90009307
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Valve Steering & AHS EH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 10 | 90009881 | 1 | 1000078690 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRSYS-STVLV | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Cyl Steering LH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 28 | 90003111 | 2 | 1000035281 | 25.11.2026 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYL | 7500 | 92088 | 12790 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Cyl Steering RH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 28 | 90003111 | 3 | 1000035282 | 25.11.2026 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYR | 7500 | 92088 | 12790 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Ovhl Accumulator Hyd Steer Front | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072091 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCF | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Ovhl Accumulator Hyd Steer Middle | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072129 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCM | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Ovhl Accumulator Hyd Steering Rear | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072167 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Steering Ball Studs | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 35 | 90038356 | A1 | 1000385442 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STLTR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STLTR90038356
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Pump Hoist & Brake | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 10 | 90003113 | 1 | 1000035284 | 29.07.2026 | 22000 | CLB-MP-HAUL-DT185 -HYDSYS-HOPMP | 7500 | 92088 | 22242 | CLB-MP-HAUL-DT185 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Air Dryer | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 14 | 90003115 | 1 | 1000035287 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -PNEUMC-AIRDR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Service Air Conditioner | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 12 | 90017450 | 1 | 1000160391 | 11.05.2026 | 5500 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN | 7500 | 92088 | 7001 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN90017450
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Ovhl Axle A Frame | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 60 | 90015390 | 1 | 1000130656 | 26.06.2026 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-AFRME | 7500 | 92088 | 22899 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Ovhl Axle Housing Dogbone | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 42 | 90003118 | 1 | 1000035290 | 26.06.2026 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-TAGLK | 7500 | 92088 | 22899 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake Wheel LH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 38 | 90003104 | 1 | 1000035273 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-AXLES-HUBLH | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake Wheel RH | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 61 | 90003105 | 2 | 1000035274 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-AXLES-HUBRH | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Cyl Suspension RHF | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067848 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYRF | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Cyl Suspension LHR | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035295 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYLR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Transmission System Hoses | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078680 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -TRNSYS-TRANS-TRNHO | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Torque Conv System Hoses | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078681 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -TRNSYS-TRQUE-TRQHO | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake Oil Cooler Front | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080283 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BROCO-BROCF | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake System Hoses Rear | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078687 | 07.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRHOR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake System Hoses Front | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078688 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRHOF | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Brake System Air Lines | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078689 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRAIR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Steering System Hoses | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078691 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -STRSYS-STHLF-STRHO | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Hoist System Hoses | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078685 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-HSTHO | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Differential System Hoses | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078682 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-DIFFL-DIFHO | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Fast Fill & SOS Hose | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103980 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-FFSOS | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Ladder Hoses | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104038 | 03.02.2027 | 22000 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-LADHO | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Spiders Transmission Driveshaft | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 8 | 90017135 | 1 | 1000154412 | 03.12.2026 | 11000 | CLB-MP-HAUL-DT185 -FDRSYS-DRSHT-UNVSL | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite Shut | Haul | Fortescue | DT185 | DT185 Repl Tyre Sense Battery | 2026-09-24 | 2026-10-15 | 21 days | FY27 | 2 | 90017022 | 1 | 1000163960 | 31.12.2026 | 24 Monthly | CLB-MP-HAUL-DT185 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT185 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 - Onsite Shut | 2026-10-22 | 2026-11-12 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Engine Cat 3516B | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156829 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -ENGINE | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Fuel Tank Mounts | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078714 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -ENGINE-FUSYS-FULTK | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Engine Pump Drive | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 62 | 90003089 | 1 | 1000035316 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Pump Drive Driveshaft Unis | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035319 | 22.11.2026 | 11000 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR-DRSHT | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Torque Converter | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 62 | 90003092 | 1 | 1000116274 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TRQUE | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Transmission | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 48 | 90003093 | 1 | 1000035318 | 21.05.2026 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS | 7500 | 89749 | 23493 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Pump Transmission | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 7 | 90003096 | 1 | 1000035320 | 06.06.2026 | 11000 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Pump Torque Converter Charge | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 5 | 90003095 | 1 | 1000080208 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TCCPP | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Transmission Oil Cooler | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 13 | 90003532 | 1 | 1000040995 | 21.05.2026 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TROLC | 7500 | 89749 | 23484 | CLB-MP-HAUL-DT186 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Differential | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 66 | 90003098 | 1 | 1000035322 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-DIFFL | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Overhaul Accumulator Brake | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072206 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BACCM | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Valve Brake | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035332 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRVLV | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Rotochamber Front | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072396 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTFR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Rotochamber LHR | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072434 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTLR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Rotochamber RHR | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072472 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTRR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Hyd Pump Steering Main | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 8 | 90003109 | 1 | 1000035334 | 15.12.2026 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STPMP | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Steering HMU | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 14 | 90003110 | 1 | 1000035335 | 15.12.2026 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STHMU | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Valve Steering & AHS EH | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 10 | 90009881 | 1 | 1000078709 | 20.05.2026 | 22000 | CLB-MP-HAUL-DT186 -STRSYS-STVLV | 7500 | 89749 | 23484 | CLB-MP-HAUL-DT186 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Cyl Steering RH | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 28 | 90003111 | 3 | 1000035337 | 15.12.2026 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYR | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Ovhl Accumulator Hyd Steer Front | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072092 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCF | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Ovhl Accumulator Hyd Steer Middle | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072130 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCM | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Ovhl Accumulator Hyd Steering Rear | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072168 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Steering Ball Studs | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 35 | 90038356 | A1 | 1000385444 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STLTR | 7500 | 89749 | 26124 | CLB-MP-HAUL-DT186 -STRSYS-STLTR90038356
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Pump Hoist & Brake | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 10 | 90003113 | 1 | 1000035339 | 23.05.2026 | 22000 | CLB-MP-HAUL-DT186 -HYDSYS-HOPMP | 7500 | 89749 | 23493 | CLB-MP-HAUL-DT186 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Cyl Hoist RH | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 49 | 90003114 | 2 | 1000035341 | 10.07.2026 | 28000 | CLB-MP-HAUL-DT186 -HYDSYS-HOCYL-HCYLR | 7500 | 89749 | 28445 | CLB-MP-HAUL-DT186 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Air Dryer | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 14 | 90003115 | 1 | 1000366660 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -PNEUMC-AIRDR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Ovhl Axle A Frame | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 60 | 90015390 | 1 | 1000130657 | 18.09.2025 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-AFRME | 7500 | 89749 | 28445 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Ovhl Axle Housing Dogbone | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 42 | 90003118 | 1 | 1000035345 | 09.01.2026 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-TAGLK | 7500 | 89749 | 42779 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Brake Wheel LH | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 38 | 90003104 | 1 | 1000035328 | 19.06.2026 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBLH | 7500 | 89749 | 22897 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Brake Wheel RH | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 61 | 90003105 | 1 | 1000035329 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBRH | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Cyl Suspension LHF | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067850 | 19.06.2026 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLF | 7500 | 89749 | 22897 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Cyl Suspension RHF | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067852 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYRF | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Cyl Suspension RHR | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035351 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYRR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Transmission System Hoses | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078699 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS-TRNHO | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Torque Conv System Hoses | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078700 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TRQUE-TRQHO | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Brake Oil Cooler Front | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080286 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BROCO-BROCF | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Brake System Hoses Rear | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078706 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRHOR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Brake System Hoses Front | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078707 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRHOF | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Brake System Air Lines | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078708 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRAIR | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Steering System Hoses | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078710 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -STRSYS-STHLF-STRHO | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Hoist System Hoses | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078704 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-HSTHO | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Differential System Hoses | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078701 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-DIFFL-DIFHO | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Fast Fill & SOS Hose | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103981 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-FFSOS | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Repl Ladder Hoses | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104039 | 18.10.2026 | 22000 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-LADHO | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT186 | DT186 Spiders Transmission Driveshaft | 2026-10-22 | 2026-11-12 | 21 days | FY27 | 8 | 90017135 | 1 | 1000154414 | 29.09.2026 | 11000 | CLB-MP-HAUL-DT186 -FDRSYS-DRSHT-UNVSL | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite Shut | Haul | Fortescue | DT186 | CAT 789D Fuel Tanks Replacement | 2026-10-22 | 2026-11-12 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 - Onsite Shut | 2026-11-19 | 2026-12-10 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Engine Cat 3516B | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156781 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -ENGINE | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Radiator Engine Cooling | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 85 | 90003081 | 1 | 1000035204 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-RADTR | 7400 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Fuel Tank Mounts | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 16 | 90009887 | 1 | 1000079670 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -ENGINE-FUSYS-FULTK | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Pump Drive Driveshaft Unis | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035209 | 12.02.2027 | 11000 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR-DRSHT | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Torque Converter | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 62 | 90003092 | 1 | 1000035207 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -TRNSYS-TRQUE | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Pump Transmission | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 7 | 90003096 | 1 | 1000035210 | 13.02.2027 | 11000 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TMCPP | 7500 | 90364 | 7008 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Transmission Oil Cooler | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 13 | 90003532 | 1 | 1000040992 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -TRNSYS-TROLC | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Hyd Motor Axle Lube Rear | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 9 | 90003101 | 1 | 1000035215 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-HYM01 | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Overhaul Accumulator Brake | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072203 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BACCM | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Pump Brake Control | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 5 | 90003106 | 1 | 1000035221 | 13.02.2027 | 11000 | CLB-MP-HAUL-DT183 -BRKSYS-HYFPP | 7500 | 90364 | 7008 | CLB-MP-HAUL-DT183 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Valve Brake | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035222 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRVLV | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Rotochamber Front | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072393 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTFR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Rotochamber LHR | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072431 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTLR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Rotochamber RHR | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072469 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTRR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Hyd Pump Steering Main | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 8 | 90003109 | 1 | 1000035224 | 19.11.2026 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STPMP | 7500 | 90364 | 12780 | CLB-MP-HAUL-DT183 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Steering HMU | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 14 | 90003110 | 1 | 1000035225 | 19.11.2026 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STHMU | 7500 | 90364 | 12780 | CLB-MP-HAUL-DT183 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Ovhl Accumulator Hyd Steer Front | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072089 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Ovhl Accumulator Hyd Steer Middle | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072127 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCM | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Ovhl Accumulator Hyd Steering Rear | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072165 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Steering Ball Studs | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 35 | 90038356 | A1 | 1000385438 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STLTR | 7500 | 90364 | 20591 | CLB-MP-HAUL-DT183 -STRSYS-STLTR90038356
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Cyl Hoist LH | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 49 | 90003114 | 1 | 1000035230 | 27.11.2027 | 28000 | CLB-MP-HAUL-DT183 -HYDSYS-HOCYL-HCYLL | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Ovhl Axle A Frame | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 60 | 90015390 | 1 | 1000130654 | 09.08.2026 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-AFRME | 7500 | 90364 | 21856 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Ovhl Axle Housing Dogbone | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 42 | 90003118 | 1 | 1000035235 | 09.08.2026 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-TAGLK | 7500 | 90364 | 21853 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake Wheel LH | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 38 | 90003104 | 2 | 1000035218 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-AXLES-HUBLH | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake Wheel RH | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 61 | 90003105 | 2 | 1000035219 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-AXLES-HUBRH | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Cyl Suspension LHF | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067838 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYLF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Cyl Suspension RHF | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067840 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYRF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Cyl Suspension LHR | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035240 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYLR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Cyl Suspension RHR | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035241 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYRR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Transmission System Hoses | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 8 | 90009871 | 1 | 1000079655 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -TRNSYS-TRANS-TRNHO | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Torque Conv System Hoses | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 4 | 90009872 | 1 | 1000079656 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -TRNSYS-TRQUE-TRQHO | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake Relay Valve | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 6 | 90009877 | 1 | 1000079661 | 12.02.2027 | 11000 | CLB-MP-HAUL-DT183 -BRKSYS-BRVRL | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake Oil Cooler Front | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080278 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BROCO-BROCF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake System Hoses Rear | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 6 | 90009878 | 1 | 1000079662 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRHOR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake System Hoses Front | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 12 | 90009879 | 1 | 1000079663 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRHOF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Brake System Air Lines | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 24 | 90009880 | 1 | 1000079664 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRAIR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Steering System Hoses | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 24 | 90009882 | 1 | 1000079666 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -STRSYS-STHLF-STRHO | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Hoist System Hoses | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 12 | 90009903 | 1 | 1000079660 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-HSTHO | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Differential System Hoses | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 2 | 90009873 | 1 | 1000079657 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-DIFFL-DIFHO | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Fast Fill & SOS Hose | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103978 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-FFSOS | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT183 | DT183 Repl Ladder Hoses | 2026-11-19 | 2026-12-10 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104036 | 01.02.2027 | 22000 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-LADHO | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 - Onsite Shut | 2026-12-17 | 2027-01-07 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Engine Cat 3516B | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156925 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -ENGINE | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Radiator Engine Cooling | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 85 | 90003081 | 1 | 1000035689 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-RADTR | 7400 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Fuel Tank Mounts | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078809 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -ENGINE-FUSYS-FULTK | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Engine Pump Drive | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 62 | 90003089 | 1 | 1000035691 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Pump Drive Driveshaft Unis | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035694 | 13.01.2027 | 11000 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR-DRSHT | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Pump Transmission | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 7 | 90003096 | 1 | 1000035695 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TMCPP | 7500 | 91174 | 7657 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Transmission Oil Cooler | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 13 | 90003532 | 1 | 1000041001 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -TRNSYS-TROLC | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Drive Shaft Transmission | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 16 | 90017134 | 1 | 1000154425 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-DRSHT | 7500 | 91174 | 30870 | CLB-MP-HAUL-DT192 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Final Drive RH | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 56 | 90003100 | 1 | 1000035699 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-FDRVE-FDRRH | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Hyd Motor Axle Lube Rear | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 9 | 90003101 | 1 | 1000035700 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-HYM01 | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Overhaul Accumulator Brake | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072212 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BACCM | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Pump Brake Control | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 5 | 90003106 | 1 | 1000035706 | 13.01.2027 | 11000 | CLB-MP-HAUL-DT192 -BRKSYS-HYFPP | 7500 | 91174 | 19917 | CLB-MP-HAUL-DT192 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Valve Brake | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035707 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRVLV | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Rotochamber Front | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072402 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTFR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Rotochamber LHR | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072440 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTLR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Rotochamber RHR | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072478 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTRR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Cyl Steering LH | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 28 | 90003111 | 2 | 1000035711 | 12.12.2026 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYL | 7500 | 91174 | 12341 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Ovhl Accumulator Hyd Steer Front | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072098 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCF | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Ovhl Accumulator Hyd Steer Middle | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072136 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCM | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Ovhl Accumulator Hyd Steering Rear | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072174 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Steering Link & Arm Rebush | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 45 | 90038355 | A1 | 1000385457 | 10.11.2026 | 30000 | CLB-MP-HAUL-DT192 -STRSYS-STLTR | 7500 | 91174 | 27983 | CLB-MP-HAUL-DT192 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Air Dryer | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 14 | 90003115 | 1 | 1000035717 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -PNEUMC-AIRDR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Ovhl Axle Housing Dogbone | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 42 | 90003118 | 1 | 1000035720 | 25.02.2026 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-TAGLK | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Cyl Suspension LHF | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067874 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYLF | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Transmission System Hoses | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078794 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -TRNSYS-TRANS-TRNHO | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Torque Conv System Hoses | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078795 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -TRNSYS-TRQUE-TRQHO | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Brake Oil Cooler Front | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080296 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BROCO-BROCF | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Brake System Hoses Rear | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078801 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRHOR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Brake System Hoses Front | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078802 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRHOF | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Brake System Air Lines | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078803 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRAIR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Steering System Hoses | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078805 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -STRSYS-STHLF-STRHO | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Hoist System Hoses | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078799 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-HSTHO | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Differential System Hoses | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078796 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-DIFFL-DIFHO | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Fast Fill & SOS Hose | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103987 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-FFSOS | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT192 | DT192 Repl Ladder Hoses | 2026-12-17 | 2027-01-07 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104045 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-LADHO | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 - Onsite Shut | 2027-01-10 | 2027-01-31 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Engine Cat 3516B | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 142 | 90017315 | 1 | 1000156893 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -ENGINE | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Radiator Engine Cooling | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 85 | 90003081 | 1 | 1000035573 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-RADTR | 7400 | 90698 | 17590 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Fuel Tank Mounts | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078771 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -ENGINE-FUSYS-FULTK | 7500 | 90698 | 9317 | CLB-MP-HAUL-DT190 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Engine Pump Drive | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 62 | 90003089 | 1 | 1000035575 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Pump Drive Driveshaft Unis | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035578 | 25.03.2027 | 11000 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR-DRSHT | 7500 | 90698 | 6249 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Torque Converter | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 62 | 90003092 | 1 | 1000035576 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -TRNSYS-TRQUE | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Pump Transmission | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 7 | 90003096 | 1 | 1000035579 | 27.02.2027 | 11000 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TMCPP | 7500 | 90698 | 6776 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Transmission Oil Cooler | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 13 | 90003532 | 1 | 1000040999 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -TRNSYS-TROLC | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Hyd Motor Axle Lube Rear | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 9 | 90003101 | 1 | 1000035584 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-HYM01 | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Overhaul Accumulator Brake | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072210 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BACCM | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Pump Brake Control | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 5 | 90003106 | 1 | 1000035590 | 27.02.2027 | 11000 | CLB-MP-HAUL-DT190 -BRKSYS-HYFPP | 7500 | 90698 | 6776 | CLB-MP-HAUL-DT190 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Valve Brake | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035591 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRVLV | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Rotochamber Front | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072400 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTFR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Rotochamber LHR | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072438 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTLR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Rotochamber RHR | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072476 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTRR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Hyd Pump Steering Main | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 8 | 90003109 | 1 | 1000035593 | 20.03.2027 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STPMP | 7500 | 90698 | 10366 | CLB-MP-HAUL-DT190 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Ovhl Accumulator Hyd Steer Front | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072096 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCF | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Ovhl Accumulator Hyd Steer Middle | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072134 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCM | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Ovhl Accumulator Hyd Steering Rear | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072172 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Steering Ball Studs | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 35 | 90038356 | A1 | 1000385452 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STLTR | 7500 | 90698 | 24244 | CLB-MP-HAUL-DT190 -STRSYS-STLTR90038356
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Cyl Hoist RH | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 49 | 90003114 | 2 | 1000035600 | 24.02.2027 | 28000 | CLB-MP-HAUL-DT190 -HYDSYS-HOCYL-HCYLR | 7500 | 90698 | 23847 | CLB-MP-HAUL-DT190 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Ovhl Axle Housing Dogbone | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 42 | 90003118 | 1 | 1000035604 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-TAGLK | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Cyl Suspension LHR | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035609 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYLR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Cyl Suspension RHR | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 42 | 90003122 | 1 | 1000035610 | 14.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYRR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Transmission System Hoses | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078756 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -TRNSYS-TRANS-TRNHO | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Torque Conv System Hoses | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078757 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -TRNSYS-TRQUE-TRQHO | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Brake Oil Cooler Front | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080294 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BROCO-BROCF | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Brake System Hoses Rear | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078763 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRHOR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Brake System Hoses Front | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078764 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRHOF | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Brake System Air Lines | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078765 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRAIR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Steering System Hoses | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078767 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -STRSYS-STHLF-STRHO | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Hoist System Hoses | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078761 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-HSTHO | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Differential System Hoses | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078758 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-DIFFL-DIFHO | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Fast Fill & SOS Hose | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103985 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-FFSOS | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Ladder Hoses | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104043 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-LADHO | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Spiders Transmission Driveshaft | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 8 | 90017135 | 1 | 1000154422 | 05.01.2027 | 11000 | CLB-MP-HAUL-DT190 -FDRSYS-DRSHT-UNVSL | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite Shut | Haul | Fortescue | DT190 | DT190 Repl Tyre Sense Battery | 2027-01-10 | 2027-01-31 | 21 days | FY27 | 2 | 90017022 | 1 | 1000163965 | 26.04.2027 | 24 Monthly | CLB-MP-HAUL-DT190 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT190 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 - Onsite Shut | 2027-02-07 | 2027-02-28 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Engine Cat 3516B | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 142 | 90017315 | 1 | 1000157021 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -ENGINE | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Fuel Tank Mounts | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 16 | 90009887 | 1 | 1000078866 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -ENGINE-FUSYS-FULTK | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Engine Pump Drive | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 62 | 90003089 | 1 | 1000036039 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Torque Converter | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 62 | 90003092 | 1 | 1000036040 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -TRNSYS-TRQUE | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Transmission Oil Cooler | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 13 | 90003532 | 1 | 1000041007 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -TRNSYS-TROLC | 7500 | 88680 | 7548 | CLB-MP-HAUL-DT198 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Differential | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 66 | 90003098 | 1 | 1000036045 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-DIFFL | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Final Drive LH | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 56 | 90003099 | 1 | 1000036046 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-FDRVE-FDRLH | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Final Drive RH | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 56 | 90003100 | 1 | 1000036047 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-FDRVE-FDRRH | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Hyd Motor Axle Lube Rear | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 9 | 90003101 | 1 | 1000036048 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-HYM01 | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Overhaul Accumulator Brake | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072218 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BACCM | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Valve Brake | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 18 | 90003107 | 1 | 1000036055 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRVLV | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Rotochamber Front | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072408 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTFR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Rotochamber LHR | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072446 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTLR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Rotochamber RHR | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072484 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTRR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Valve Steering & AHS EH | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 10 | 90009881 | 1 | 1000078861 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRSYS-STVLV | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Ovhl Accumulator Hyd Steer Front | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072104 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Ovhl Accumulator Hyd Steer Middle | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072142 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCM | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Ovhl Accumulator Hyd Steering Rear | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072180 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Pump Hoist & Brake | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 10 | 90003113 | 1 | 1000036062 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -HYDSYS-HOPMP | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Air Dryer | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 14 | 90003115 | 1 | 1000366661 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -PNEUMC-AIRDR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Ovhl Axle A Frame | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 60 | 90015390 | 1 | 1000130668 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-AFRME | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Ovhl Axle Housing Dogbone | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 42 | 90003118 | 1 | 1000036068 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-TAGLK | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Service Suspension Cylinders | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 27 | 90012840 | 1 | 1000106947 | 23.04.2027 | 11000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Cyl Suspension LHF | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067898 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYLF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Cyl Suspension RHF | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067900 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYRF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Cyl Suspension LHR | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 42 | 90003122 | 1 | 1000036073 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYLR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Cyl Suspension RHR | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 42 | 90003122 | 1 | 1000036074 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYRR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Transmission System Hoses | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 8 | 90009871 | 1 | 1000078851 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -TRNSYS-TRANS-TRNHO | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Torque Conv System Hoses | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 4 | 90009872 | 1 | 1000078852 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -TRNSYS-TRQUE-TRQHO | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Brake Oil Cooler Front | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080302 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BROCO-BROCF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Brake System Hoses Rear | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 6 | 90009878 | 1 | 1000078858 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRHOR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Brake System Hoses Front | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 12 | 90009879 | 1 | 1000078859 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRHOF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Brake System Air Lines | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 24 | 90009880 | 1 | 1000078860 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRAIR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Steering System Hoses | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 24 | 90009882 | 1 | 1000078862 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -STRSYS-STHLF-STRHO | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Hoist System Hoses | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 12 | 90009903 | 1 | 1000078856 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-HSTHO | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Differential System Hoses | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 2 | 90009873 | 1 | 1000078853 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-DIFFL-DIFHO | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Fast Fill & SOS Hose | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103993 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-FFSOS | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Ladder Hoses | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104051 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-LADHO | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Pump Drive Driveshaft Unis | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 4 | 90009874 | 1 | 1000036042 | 26.04.2027 | 11000 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR-DRSHT | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Pump Transmission | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 7 | 90003096 | 1 | 1000036043 | 26.04.2027 | 11000 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TMCPP | 7500 | 88680 | 7548 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Pump Brake Control | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 5 | 90003106 | 1 | 1000036054 | 26.04.2027 | 11000 | CLB-MP-HAUL-DT198 -BRKSYS-HYFPP | 7500 | 88680 | 5576 | CLB-MP-HAUL-DT198 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Brake Relay Valve | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 6 | 90009877 | 1 | 1000078857 | 26.04.2027 | 11000 | CLB-MP-HAUL-DT198 -BRKSYS-BRVRL | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Drive Line Axle LH | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 8 | 90014551 | 1 | 1000123543 | 02.06.2027 | 30000 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX-AXLLH | 7500 | 88680 | 23807 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite Shut | Haul | Fortescue | DT198 | DT198 Repl Drive Line Axle RH | 2027-02-07 | 2027-02-28 | 21 days | FY27 | 8 | 90014552 | 1 | 1000123604 | 02.06.2027 | 30000 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX-AXLRH | 7500 | 88680 | 23807 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite Shut | Haul | Fortescue | DT198 | CAT 789 Axle Housing Replacement | 2027-02-07 | 2027-02-28 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 - Onsite Shut | 2027-04-23 | 2027-05-14 | 21 days | FY27
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Drive Line Axle LH | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 8 | 90014551 | 1 | 1000123542 | 23.02.2027 | 30000 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX-AXLLH | 7500 | 86259 | 25918 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Drive Line Axle RH | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 8 | 90014552 | 1 | 1000123603 | 23.02.2027 | 30000 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX-AXLRH | 7500 | 86259 | 25918 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Steering Link & Arm Rebush | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 45 | 90038355 | A1 | 1000385467 | 29.03.2027 | 30000 | CLB-MP-HAUL-DT197 -STRSYS-STLTR | 7500 | 86259 | 25173 | CLB-MP-HAUL-DT197 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Engine Cat 3516B | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 142 | 90017315 | 1 | 1000157005 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -ENGINE | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Radiator Engine Cooling | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 85 | 90003081 | 1 | 1000035979 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-RADTR | 7400 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Fuel Tank Mounts | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 16 | 90009887 | 1 | 1000079746 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -ENGINE-FUSYS-FULTK | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Engine Pump Drive | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 62 | 90003089 | 1 | 1000035981 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Torque Converter | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 62 | 90003092 | 1 | 1000035982 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -TRNSYS-TRQUE | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Differential | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 66 | 90003098 | 1 | 1000035987 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-DIFFL | 7500 | 86259 | 21386 | CLB-MP-HAUL-DT197 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Final Drive RH | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 56 | 90003100 | 1 | 1000035989 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-FDRVE-FDRRH | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Overhaul Accumulator Brake | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 10 | 90009313 | 1 | 1000072217 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BACCM | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Valve Brake | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 18 | 90003107 | 1 | 1000035997 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRVLV | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Rotochamber Front | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 5 | 90009308 | 1 | 1000072407 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTFR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Rotochamber LHR | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072445 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTLR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Rotochamber RHR | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 5 | 90009309 | 1 | 1000072483 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTRR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Valve Steering & AHS EH | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 10 | 90009881 | 1 | 1000079741 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRSYS-STVLV | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Ovhl Accumulator Hyd Steer Front | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072103 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCF | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Ovhl Accumulator Hyd Steer Middle | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072141 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCM | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Ovhl Accumulator Hyd Steering Rear | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 7 | 90009314 | 1 | 1000072179 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Pump Hoist & Brake | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 10 | 90003113 | 1 | 1000036004 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -HYDSYS-HOPMP | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Air Dryer | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 14 | 90003115 | 1 | 1000036007 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -PNEUMC-AIRDR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake Wheel LH | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 38 | 90003104 | 2 | 1000035993 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-AXLES-HUBLH | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake Wheel RH | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 61 | 90003105 | 2 | 1000035994 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-AXLES-HUBRH | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Cyl Suspension RHF | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 66 | 90003121 | 1 | 1000067896 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYRF | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Cyl Suspension LHR | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 42 | 90003122 | 1 | 1000036015 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYLR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Transmission System Hoses | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 8 | 90009871 | 1 | 1000079731 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -TRNSYS-TRANS-TRNHO | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Torque Conv System Hoses | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 4 | 90009872 | 1 | 1000079732 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -TRNSYS-TRQUE-TRQHO | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake Oil Cooler Front | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 5 | 90003108 | 1 | 1000080301 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BROCO-BROCF | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake System Hoses Rear | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 6 | 90009878 | 1 | 1000079738 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRHOR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake System Hoses Front | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 12 | 90009879 | 1 | 1000079739 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRHOF | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake System Air Lines | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 24 | 90009880 | 1 | 1000079740 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRAIR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Steering System Hoses | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 24 | 90009882 | 1 | 1000079742 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -STRSYS-STHLF-STRHO | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Hoist System Hoses | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 12 | 90009903 | 1 | 1000079736 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-HSTHO | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Differential System Hoses | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 2 | 90009873 | 1 | 1000079733 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-DIFFL-DIFHO | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Fast Fill & SOS Hose | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 36 | 90012188 | 1 | 1000103992 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-FFSOS | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Ladder Hoses | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 4 | 90012189 | 1 | 1000104050 | 23.04.2027 | 22000 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-LADHO | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Pump Brake Control | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 5 | 90003106 | 1 | 1000035996 | 29.04.2027 | 11000 | CLB-MP-HAUL-DT197 -BRKSYS-HYFPP | 7500 | 86259 | 5525 | CLB-MP-HAUL-DT197 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Brake Relay Valve | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 6 | 90009877 | 1 | 1000079737 | 29.04.2027 | 11000 | CLB-MP-HAUL-DT197 -BRKSYS-BRVRL | 7500 | 86259 | 5525 | CLB-MP-HAUL-DT197 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Spiders Transmission Driveshaft | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 8 | 90017135 | 1 | 1000154436 | 01.05.2027 | 11000 | CLB-MP-HAUL-DT197 -FDRSYS-DRSHT-UNVSL | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Pump Drive Driveshaft Unis | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 4 | 90009874 | 1 | 1000035984 | 26.05.2027 | 11000 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR-DRSHT | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT197 | DT197 Repl Tyre Sense Battery | 2027-04-23 | 2027-05-14 | 21 days | FY27 | 2 | 90017022 | 1 | 1000163972 | 04.06.2027 | 24 Monthly | CLB-MP-HAUL-DT197 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT197 -MANGMT-TYRSN90017022
| Onsite Shut |  | Fortescue |  | FY28 - ONSITE SHUTDOWNS | 2027-07-01 | 2028-06-30 | 365 days | FY28
| Onsite Shut | Haul | Fortescue |  | HAUL | 2027-07-01 | 2028-06-30 | 365 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 - Onsite Shut (EOL - 08/2029) | 2027-07-03 | 2027-07-24 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Tyre Sense Battery | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 2 | 90017022 | 1 | 1000163966 | 21.04.2027 | 24 Monthly | CLB-MP-HAUL-DT191 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT191 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Differential | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 66 | 90003098 | 1 | 1000035639 | 31.05.2027 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-DIFFL | 7500 | 87047 | 34521 | CLB-MP-HAUL-DT191 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 3Y Air Tank LH Int Insp & PRV Repl | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 4.5 | 90038754 | A1 | 1000389419 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH | 7500 | 86814 | 15453 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 3Y Air Tank RH Int Insp & PRV Repl | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 4.5 | 90038754 | A1 | 1000389421 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH | 7500 | 86814 | 15453 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Drive Line Axle LH | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 8 | 90014551 | 1 | 1000123536 | 06.06.2027 | 30000 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX-AXLLH | 7500 | 87047 | 23692 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Drive Line Axle RH | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 8 | 90014552 | 1 | 1000123597 | 06.06.2027 | 30000 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX-AXLRH | 7500 | 87047 | 23692 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Engine Cat 3516B | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156909 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -ENGINE | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Radiator Engine Cooling | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 85 | 90003081 | 1 | 1000035631 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-RADTR | 7400 | 87047 | 37615 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Fuel Tank Mounts | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078790 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -ENGINE-FUSYS-FULTK | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Engine Pump Drive | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 62 | 90003089 | 1 | 1000035633 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Torque Converter | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 62 | 90003092 | 1 | 1000035634 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -TRNSYS-TRQUE | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Pump Torque Converter Charge | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080213 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TCCPP | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Drive Shaft Transmission | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154423 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-DRSHT | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Final Drive LH | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 56 | 90003099 | 1 | 1000035640 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-FDRVE-FDRLH | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Hyd Motor Axle Lube Rear | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 9 | 90003101 | 1 | 1000035642 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-HYM01 | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Overhaul Accumulator Brake | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072211 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BACCM | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Rotochamber Front | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072401 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTFR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Rotochamber LHR | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072439 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTLR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Rotochamber RHR | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072477 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTRR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Valve Steering & AHS EH | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078785 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRSYS-STVLV | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Ovhl Accumulator Hyd Steer Front | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072097 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Ovhl Accumulator Hyd Steer Middle | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072135 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCM | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Ovhl Accumulator Hyd Steering Rear | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072173 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Pump Hoist & Brake | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 10 | 90003113 | 1 | 1000035656 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -HYDSYS-HOPMP | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Air Dryer | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 14 | 90003115 | 1 | 1000035659 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -PNEUMC-AIRDR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Ovhl Axle Housing Dogbone | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 42 | 90003118 | 1 | 1000035662 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-TAGLK | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake Wheel LH | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 38 | 90003104 | 2 | 1000035645 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-AXLES-HUBLH | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake Wheel RH | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 61 | 90003105 | 2 | 1000035646 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-AXLES-HUBRH | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Service Suspension Cylinders | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106940 | 07.06.2027 | 11000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Cyl Suspension LHF | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067870 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYLF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Cyl Suspension RHF | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067872 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYRF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Transmission System Hoses | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078775 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -TRNSYS-TRANS-TRNHO | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Torque Conv System Hoses | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078776 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -TRNSYS-TRQUE-TRQHO | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake Oil Cooler Front | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080295 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BROCO-BROCF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake System Hoses Rear | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078782 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRHOR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake System Hoses Front | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078783 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRHOF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake System Air Lines | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078784 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRAIR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Steering System Hoses | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078786 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -STRSYS-STHLF-STRHO | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Hoist System Hoses | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078780 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-HSTHO | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Differential System Hoses | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078777 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-DIFFL-DIFHO | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Fast Fill & SOS Hose | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103986 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-FFSOS | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Ladder Hoses | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104044 | 07.06.2027 | 22000 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-LADHO | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Pump Drive Driveshaft Unis | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 4 | 90009874 | 1 | 1000035636 | 16.07.2027 | 11000 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR-DRSHT | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Pump Transmission | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 7 | 90003096 | 1 | 1000035637 | 16.07.2027 | 11000 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TMCPP | 7500 | 87047 | 3873 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Steering Link & Arm Rebush | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 45 | 90038355 | A1 | 1000385455 | 07.08.2027 | 30000 | CLB-MP-HAUL-DT191 -STRSYS-STLTR | 7500 | 87047 | 22425 | CLB-MP-HAUL-DT191 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Brake Relay Valve | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078781 | 18.08.2027 | 11000 | CLB-MP-HAUL-DT191 -BRKSYS-BRVRL | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Pump Brake Control | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 5 | 90003106 | 1 | 1000035648 | 20.08.2027 | 11000 | CLB-MP-HAUL-DT191 -BRKSYS-HYFPP | 7500 | 87047 | 3166 | CLB-MP-HAUL-DT191 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Hyd Pump Steering Main | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 8 | 90003109 | 1 | 1000035651 | 31.08.2027 | 15000 | CLB-MP-HAUL-DT191 -STRSYS-STPMP | 7500 | 87047 | 6938 | CLB-MP-HAUL-DT191 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT191 | DT191 Repl Steering HMU | 2027-07-03 | 2027-07-24 | 21 days | FY28 | 14 | 90003110 | 1 | 1000035652 | 09.09.2027 | 15000 | CLB-MP-HAUL-DT191 -STRSYS-STHMU | 7500 | 87047 | 22420 | CLB-MP-HAUL-DT191 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 - Onsite Shut (EOL - 12/2029) | 2027-07-29 | 2027-08-19 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Engine Cat 3516B | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156877 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -ENGINE | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Radiator Engine Cooling | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 85 | 90003081 | 1 | 1000035501 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-RADTR | 7400 | 84546 | 36386 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Fuel Tank Mounts | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 16 | 90009887 | 1 | 1000079689 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -ENGINE-FUSYS-FULTK | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Engine Pump Drive | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 62 | 90003089 | 1 | 1000037280 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Torque Converter | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 62 | 90003092 | 1 | 1000035504 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -TRNSYS-TRQUE | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Transmission | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 48 | 90003093 | 1 | 1000035505 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -TRNSYS-TRANS | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Pump Torque Converter Charge | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080211 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TCCPP | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Transmission Oil Cooler | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 13 | 90003532 | 1 | 1000040998 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -TRNSYS-TROLC | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Drive Shaft Transmission | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154419 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-DRSHT | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Differential | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 66 | 90003098 | 1 | 1000035509 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-DIFFL | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Overhaul Accumulator Brake | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072209 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BACCM | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Valve Brake | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 18 | 90003107 | 1 | 1000035519 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRVLV | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Rotochamber Front | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072399 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTFR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Rotochamber LHR | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072437 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTLR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Rotochamber RHR | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072475 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTRR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Valve Steering & AHS EH | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 10 | 90009881 | 1 | 1000079684 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRSYS-STVLV | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Ovhl Accumulator Hyd Steer Front | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072095 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Ovhl Accumulator Hyd Steer Middle | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072133 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCM | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Ovhl Accumulator Hyd Steering Rear | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072171 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Pump Hoist & Brake | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 10 | 90003113 | 1 | 1000035526 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -HYDSYS-HOPMP | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Air Dryer | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 14 | 90003115 | 1 | 1000035529 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -PNEUMC-AIRDR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake Wheel LH | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 38 | 90003104 | 2 | 1000035515 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-AXLES-HUBLH | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake Wheel RH | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 61 | 90003105 | 2 | 1000035516 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-AXLES-HUBRH | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Service Suspension Cylinders | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106898 | 29.07.2027 | 11000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Cyl Suspension LHF | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067862 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYLF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Cyl Suspension RHF | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067864 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYRF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Cyl Suspension LHR | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035537 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYLR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Transmission System Hoses | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 8 | 90009871 | 1 | 1000079674 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -TRNSYS-TRANS-TRNHO | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Torque Conv System Hoses | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 4 | 90009872 | 1 | 1000079675 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -TRNSYS-TRQUE-TRQHO | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake Oil Cooler Front | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080293 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BROCO-BROCF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake System Hoses Rear | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 6 | 90009878 | 1 | 1000079681 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRHOR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake System Hoses Front | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 12 | 90009879 | 1 | 1000079682 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRHOF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake System Air Lines | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 24 | 90009880 | 1 | 1000079683 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRAIR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Steering System Hoses | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 24 | 90009882 | 1 | 1000079685 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -STRSYS-STHLF-STRHO | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Hoist System Hoses | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 12 | 90009903 | 1 | 1000079679 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-HSTHO | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Differential System Hoses | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 2 | 90009873 | 1 | 1000079676 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-DIFFL-DIFHO | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Fast Fill & SOS Hose | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103984 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-FFSOS | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Ladder Hoses | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104042 | 29.07.2027 | 22000 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-LADHO | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Pump Drive Driveshaft Unis | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 4 | 90009874 | 1 | 1000035506 | 10.08.2027 | 11000 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR-DRSHT | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Pump Brake Control | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 5 | 90003106 | 1 | 1000035518 | 10.08.2027 | 11000 | CLB-MP-HAUL-DT189 -BRKSYS-HYFPP | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT189 | DT189 Repl Brake Relay Valve | 2027-07-29 | 2027-08-19 | 21 days | FY28 | 6 | 90009877 | 1 | 1000079680 | 10.08.2027 | 11000 | CLB-MP-HAUL-DT189 -BRKSYS-BRVRL | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 - Onsite Shut (EOL - 11/2029) | 2027-08-23 | 2027-09-13 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Cyl Steering RH | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 28 | 90003111 | 3 | 1000035944 | 01.07.2027 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYR | 7500 | 85161 | 8199 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Differential | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 66 | 90003098 | 1 | 1000035929 | 23.07.2027 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-DIFFL | 7500 | 85161 | 16148 | CLB-MP-HAUL-DT196 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Spiders Transmission Driveshaft | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 8 | 90017135 | 1 | 1000154434 | 23.07.2027 | 11000 | CLB-MP-HAUL-DT196 -FDRSYS-DRSHT-UNVSL | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Engine Cat 3516B | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156989 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -ENGINE | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Radiator Engine Cooling | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 85 | 90003081 | 1 | 1000035921 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-RADTR | 7400 | 85161 | 36765 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Fuel Tank Mounts | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 16 | 90009887 | 1 | 1000079727 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -ENGINE-FUSYS-FULTK | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Torque Converter | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 62 | 90003092 | 1 | 1000035924 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -TRNSYS-TRQUE | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Transmission | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 48 | 90003093 | 1 | 1000035925 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -TRNSYS-TRANS | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Pump Torque Converter Charge | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080222 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TCCPP | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Transmission Oil Cooler | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 13 | 90003532 | 1 | 1000041005 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -TRNSYS-TROLC | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Hyd Motor Axle Lube Rear | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 9 | 90003101 | 1 | 1000035932 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-HYM01 | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl AOC Fan Motor | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90003102 | 1 | 1000035933 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-MTFAN | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Valve Brake | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 18 | 90003107 | 1 | 1000035939 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRVLV | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Rotochamber Front | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072406 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTFR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Rotochamber LHR | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072444 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTLR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Rotochamber RHR | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072482 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTRR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Valve Steering & AHS EH | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 10 | 90009881 | 1 | 1000079722 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRSYS-STVLV | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Ovhl Accumulator Hyd Steer Front | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072102 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCF | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Ovhl Accumulator Hyd Steer Middle | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072140 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCM | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Ovhl Accumulator Hyd Steering Rear | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072178 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Air Dryer | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 14 | 90003115 | 1 | 1000035949 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -PNEUMC-AIRDR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Ovhl Axle A Frame | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 60 | 90015390 | 1 | 1000130666 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-AFRME | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Ovhl Axle Housing Dogbone | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 42 | 90003118 | 1 | 1000035952 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-TAGLK | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Brake Wheel LH | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 38 | 90003104 | 2 | 1000035935 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-AXLES-HUBLH | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Service Suspension Cylinders | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106945 | 22.08.2027 | 11000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN | 7500 | 85161 | 14133 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Cyl Suspension RHF | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067892 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYRF | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Cyl Suspension LHR | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035957 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYLR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Cyl Suspension RHR | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035958 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYRR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Transmission System Hoses | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 8 | 90009871 | 1 | 1000079712 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -TRNSYS-TRANS-TRNHO | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Torque Conv System Hoses | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 4 | 90009872 | 1 | 1000079713 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -TRNSYS-TRQUE-TRQHO | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Brake Oil Cooler Front | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080300 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BROCO-BROCF | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Brake System Hoses Rear | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 6 | 90009878 | 1 | 1000079719 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRHOR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Brake System Hoses Front | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 12 | 90009879 | 1 | 1000079720 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRHOF | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Brake System Air Lines | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 24 | 90009880 | 1 | 1000079721 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRAIR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Steering System Hoses | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 24 | 90009882 | 1 | 1000079723 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -STRSYS-STHLF-STRHO | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Hoist System Hoses | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 12 | 90009903 | 1 | 1000079717 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-HSTHO | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Differential System Hoses | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 2 | 90009873 | 1 | 1000079714 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-DIFFL-DIFHO | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Fast Fill & SOS Hose | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103991 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-FFSOS | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Ladder Hoses | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104049 | 22.08.2027 | 22000 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-LADHO | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Pump Transmission | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 7 | 90003096 | 1 | 1000035927 | 03.10.2027 | 11000 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TMCPP | 7500 | 85161 | 2274 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Pump Brake Control | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 5 | 90003106 | 1 | 1000035938 | 03.10.2027 | 11000 | CLB-MP-HAUL-DT196 -BRKSYS-HYFPP | 7500 | 85161 | 2274 | CLB-MP-HAUL-DT196 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT196 | DT196 Repl Brake Relay Valve | 2027-08-23 | 2027-09-13 | 21 days | FY28 | 6 | 90009877 | 1 | 1000079718 | 03.10.2027 | 11000 | CLB-MP-HAUL-DT196 -BRKSYS-BRVRL | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 - Onsite Shut (EOL - 11/2029) | 2027-08-30 | 2027-09-20 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Engine Cat 3516B | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156669 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -ENGINE | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Radiator Engine Cooling | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 85 | 90003081 | 1 | 1000034818 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-RADTR | 7400 | 85284 | 35516 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Fuel Tank Mounts | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 16 | 90009887 | 1 | 1000079632 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -ENGINE-FUSYS-FULTK | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Engine Pump Drive | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 62 | 90003089 | 1 | 1000034820 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Pump Drive Driveshaft Unis | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 4 | 90009874 | 1 | 1000034823 | 30.08.2027 | 11000 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR-DRSHT | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Torque Converter | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 62 | 90003092 | 1 | 1000034821 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -TRNSYS-TRQUE | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Drive Shaft Transmission | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154393 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Differential | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 66 | 90003098 | 1 | 1000034826 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-DIFFL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Final Drive RH | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 56 | 90003100 | 1 | 1000034828 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-FDRVE-FDRRH | 7500 | 85284 | 13914 | CLB-MP-HAUL-DT176 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl AOC Fan Motor | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 5 | 90003102 | 1 | 1000034830 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-MTFAN | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Overhaul Accumulator Brake | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072196 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BACCM | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Pump Brake Control | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 5 | 90003106 | 1 | 1000034835 | 30.08.2027 | 11000 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP | 7500 | 85284 | 6894 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Valve Brake | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 18 | 90003107 | 1 | 1000034836 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRVLV | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Rotochamber Front | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072386 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTFR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Rotochamber LHR | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072424 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTLR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Rotochamber RHR | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072462 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTRR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Valve Steering & AHS EH | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 10 | 90009881 | 1 | 1000079627 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRSYS-STVLV | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Ovhl Accumulator Hyd Steer Front | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072082 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCF | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Ovhl Accumulator Hyd Steer Middle | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072120 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCM | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Ovhl Accumulator Hyd Steering Rear | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072158 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Pump Hoist & Brake | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 10 | 90003113 | 1 | 1000034843 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -HYDSYS-HOPMP | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Air Dryer | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 14 | 90003115 | 1 | 1000034846 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -PNEUMC-AIRDR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake Wheel LH | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 38 | 90003104 | 2 | 1000034832 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-AXLES-HUBLH | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake Wheel RH | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 61 | 90003105 | 2 | 1000034833 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-AXLES-HUBRH | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Service Suspension Cylinders | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106885 | 30.08.2027 | 11000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Cyl Suspension RHF | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067812 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYRF | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Cyl Suspension LHR | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034854 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYLR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Cyl Suspension RHR | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034855 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYRR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Transmission System Hoses | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 8 | 90009871 | 1 | 1000079617 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -TRNSYS-TRANS-TRNHO | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Torque Conv System Hoses | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 4 | 90009872 | 1 | 1000079618 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -TRNSYS-TRQUE-TRQHO | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake Relay Valve | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 6 | 90009877 | 1 | 1000079623 | 30.08.2027 | 11000 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake Oil Cooler Front | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080267 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BROCO-BROCF | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake System Hoses Rear | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 6 | 90009878 | 1 | 1000079624 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRHOR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake System Hoses Front | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 12 | 90009879 | 1 | 1000079625 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRHOF | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Brake System Air Lines | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 24 | 90009880 | 1 | 1000079626 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRAIR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Steering System Hoses | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 24 | 90009882 | 1 | 1000079628 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -STRSYS-STHLF-STRHO | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Hoist System Hoses | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 12 | 90009903 | 1 | 1000079622 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-HSTHO | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Differential System Hoses | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 2 | 90009873 | 1 | 1000079619 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-DIFFL-DIFHO | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Fast Fill & SOS Hose | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103971 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-FFSOS | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Ladder Hoses | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104029 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-LADHO | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT176 | DT176 Repl Hyd Pump Steering Main | 2027-08-30 | 2027-09-20 | 21 days | FY28 | 8 | 90003109 | 1 | 1000034838 | 25.10.2027 | 15000 | CLB-MP-HAUL-DT176 -STRSYS-STPMP | 7500 | 85284 | 5818 | CLB-MP-HAUL-DT176 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 - Onsite Shut (EOL - 03/2030) | 2027-09-30 | 2027-10-21 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Drive Line Axle LH | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 8 | 90014551 | 1 | 1000123538 | 29.08.2027 | 30000 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX-AXLLH | 7500 | 83140 | 21912 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Drive Line Axle RH | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 8 | 90014552 | 1 | 1000123599 | 29.08.2027 | 30000 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX-AXLRH | 7500 | 83140 | 21917 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Drive Shaft Transmission | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154427 | 26.09.2027 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-DRSHT | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Differential | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 66 | 90003098 | 1 | 1000035755 | 26.09.2027 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-DIFFL | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Engine Cat 3516B | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156941 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -ENGINE | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Radiator Engine Cooling | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 85 | 90003081 | 1 | 1000035747 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-RADTR | 7400 | 83140 | 35367 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Fuel Tank Mounts | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 16 | 90009887 | 1 | 1000079708 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -ENGINE-FUSYS-FULTK | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Engine Pump Drive | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 62 | 90003089 | 1 | 1000035749 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Torque Converter | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 62 | 90003092 | 1 | 1000035750 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -TRNSYS-TRQUE | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Pump Torque Converter Charge | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080215 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TCCPP | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Final Drive LH | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 56 | 90003099 | 1 | 1000035756 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-FDRVE-FDRLH | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl AOC Fan Motor | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90003102 | 1 | 1000035759 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-MTFAN | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Overhaul Accumulator Brake | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072213 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BACCM | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Pump Brake Control | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90003106 | 1 | 1000035764 | 30.09.2027 | 11000 | CLB-MP-HAUL-DT193 -BRKSYS-HYFPP | 7500 | 83140 | 592 | CLB-MP-HAUL-DT193 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Valve Brake | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 18 | 90003107 | 1 | 1000035765 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRVLV | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Rotochamber Front | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072403 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTFR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Rotochamber LHR | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072441 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTLR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Rotochamber RHR | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072479 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTRR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Ovhl Accumulator Hyd Steer Front | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072099 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCF | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Ovhl Accumulator Hyd Steer Middle | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072137 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCM | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Ovhl Accumulator Hyd Steering Rear | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072175 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Ovhl Axle Housing Dogbone | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 42 | 90003118 | 1 | 1000035778 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-TAGLK | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Cyl Suspension LHF | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067878 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYLF | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Cyl Suspension LHR | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035783 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYLR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Cyl Suspension RHR | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035784 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYRR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Transmission System Hoses | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 8 | 90009871 | 1 | 1000079693 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -TRNSYS-TRANS-TRNHO | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Torque Conv System Hoses | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 4 | 90009872 | 1 | 1000079694 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -TRNSYS-TRQUE-TRQHO | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Brake Relay Valve | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 6 | 90009877 | 1 | 1000079699 | 30.09.2027 | 11000 | CLB-MP-HAUL-DT193 -BRKSYS-BRVRL | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Brake Oil Cooler Front | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080297 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BROCO-BROCF | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Brake System Hoses Rear | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 6 | 90009878 | 1 | 1000079700 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRHOR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Brake System Hoses Front | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 12 | 90009879 | 1 | 1000079701 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRHOF | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Brake System Air Lines | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 24 | 90009880 | 1 | 1000079702 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRAIR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Steering System Hoses | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 24 | 90009882 | 1 | 1000079704 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -STRSYS-STHLF-STRHO | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Hoist System Hoses | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 12 | 90009903 | 1 | 1000079698 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-HSTHO | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Differential System Hoses | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 2 | 90009873 | 1 | 1000079695 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-DIFFL-DIFHO | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Fast Fill & SOS Hose | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103988 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-FFSOS | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Ladder Hoses | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104046 | 30.09.2027 | 22000 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-LADHO | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Service Suspension Cylinders | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106942 | 01.10.2027 | 11000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN | 7500 | 83140 | 13267 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Pump Drive Driveshaft Unis | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 4 | 90009874 | 1 | 1000035752 | 14.10.2027 | 11000 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR-DRSHT | 7500 | 83140 | 1989 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT193 | DT193 Repl Transmission | 2027-09-30 | 2027-10-21 | 21 days | FY28 | 48 | 90003093 | 1 | 1000035751 | 02.12.2027 | 22000 | CLB-MP-HAUL-DT193 -TRNSYS-TRANS | 7500 | 83140 | 11983 | CLB-MP-HAUL-DT193 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 - Onsite Shut (EOL - 03/2030) | 2027-11-01 | 2027-11-22 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Engine Cat 3516B | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156621 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -ENGINE | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Fuel Tank Mounts | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078543 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -ENGINE-FUSYS-FULTK | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Transmission | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 48 | 90003093 | 1 | 1000034657 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -TRNSYS-TRANS | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Drive Shaft Transmission | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154387 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-DRSHT | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Final Drive RH | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 56 | 90003100 | 1 | 1000034663 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-FDRVE-FDRRH | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Overhaul Accumulator Brake | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072193 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BACCM | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Valve Brake | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 18 | 90003107 | 1 | 1000034671 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRVLV | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Rotochamber Front | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072383 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTFR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Rotochamber LHR | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072421 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTLR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Rotochamber RHR | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072459 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTRR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Valve Steering & AHS EH | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078538 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRSYS-STVLV | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Ovhl Accumulator Hyd Steer Front | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072079 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCF | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Ovhl Accumulator Hyd Steer Middle | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072117 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCM | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Ovhl Accumulator Hyd Steering Rear | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072155 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Pump Hoist | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 10 | 90003113 | 1 | 1000116271 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -HYDSYS-HOPMP | 7500 | 82651 | 253 | CLB-MP-HAUL-DT173 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Air Dryer | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 14 | 90003115 | 1 | 1000034681 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -PNEUMC-AIRDR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Ovhl Axle Housing Dogbone | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 42 | 90003118 | 1 | 1000034684 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-TAGLK | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake Wheel LH | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 38 | 90003104 | 2 | 1000034667 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-AXLES-HUBLH | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake Wheel RH | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 61 | 90003105 | 2 | 1000034668 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-AXLES-HUBRH | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Cyl Suspension LHF | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067798 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYLF | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Cyl Suspension RHF | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067800 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYRF | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Transmission System Hoses | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078528 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -TRNSYS-TRANS-TRNHO | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Torque Conv System Hoses | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078529 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -TRNSYS-TRQUE-TRQHO | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake Oil Cooler Front | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080264 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BROCO-BROCF | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake System Hoses Rear | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078535 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRHOR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake System Hoses Front | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078536 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRHOF | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake System Air Lines | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078537 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRAIR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Steering System Hoses | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078539 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRSYS-STHLF-STRHO | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Hoist System Hoses | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078533 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-HSTHO | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Differential System Hoses | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078530 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-DIFFL-DIFHO | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Fast Fill & SOS Hose | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103968 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-FFSOS | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Ladder Hoses | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104026 | 01.11.2027 | 22000 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-LADHO | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Pump Brake Control | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 5 | 90003106 | 1 | 1000034670 | 02.11.2027 | 11000 | CLB-MP-HAUL-DT173 -BRKSYS-HYFPP | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Cyl Suspension LHR | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034689 | 02.11.2027 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYLR | 7500 | 82651 | 12553 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Pump Drive Driveshaft Unis | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 4 | 90009874 | 1 | 1000116270 | 03.11.2027 | 11000 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR-DRSHT | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Brake Relay Valve | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078534 | 03.11.2027 | 11000 | CLB-MP-HAUL-DT173 -BRKSYS-BRVRL | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Cyl Suspension RHR | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034690 | 07.01.2028 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYRR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT173 | DT173 Repl Drive Line Axle LH | 2027-11-01 | 2027-11-22 | 21 days | FY28 | 8 | 90014551 | 1 | 1000123518 | 04.02.2028 | 30000 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX-AXLLH | 7500 | 82651 | 18641 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 - Onsite Shut (EOL - 01/2030) | 2028-01-04 | 2028-01-25 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Engine Cat 3516B | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156717 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -ENGINE | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Radiator Engine Cooling | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 85 | 90003081 | 1 | 1000034983 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-RADTR | 7400 | 84079 | 33681 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Fuel Tank Mounts | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078619 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -ENGINE-FUSYS-FULTK | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Torque Converter | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 62 | 90003092 | 1 | 1000034986 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -TRNSYS-TRQUE | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Pump Torque Converter Charge | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080201 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TCCPP | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Drive Shaft Transmission | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154399 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Final Drive RH | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 56 | 90003100 | 1 | 1000034993 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-FDRVE-FDRRH | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Hyd Motor Axle Lube Rear | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 9 | 90003101 | 1 | 1000034994 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-HYM01 | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl AOC Fan Motor | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90003102 | 1 | 1000034995 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-MTFAN | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Overhaul Accumulator Brake | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072199 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BACCM | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Pump Brake Control | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90003106 | 1 | 1000035000 | 04.01.2028 | 11000 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Valve Brake | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 18 | 90003107 | 1 | 1000035001 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRVLV | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Rotochamber Front | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072389 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTFR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Rotochamber LHR | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072427 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTLR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Rotochamber RHR | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072465 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTRR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Valve Steering & AHS EH | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078614 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRSYS-STVLV | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Ovhl Accumulator Hyd Steer Front | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072085 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCF | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Ovhl Accumulator Hyd Steer Middle | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072123 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCM | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Ovhl Accumulator Hyd Steering Rear | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072161 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Air Dryer | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 14 | 90003115 | 1 | 1000035011 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -PNEUMC-AIRDR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Brake Wheel RH | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 61 | 90003105 | 2 | 1000034998 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-AXLES-HUBRH | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Cyl Suspension LHF | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067822 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYLF | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Cyl Suspension RHF | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067824 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYRF | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Cyl Suspension LHR | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035019 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYLR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Cyl Suspension RHR | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035020 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYRR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Transmission System Hoses | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078604 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -TRNSYS-TRANS-TRNHO | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Torque Conv System Hoses | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078605 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -TRNSYS-TRQUE-TRQHO | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Brake Relay Valve | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078610 | 04.01.2028 | 11000 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Brake Oil Cooler Front | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080271 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BROCO-BROCF | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Brake System Hoses Rear | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078611 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRHOR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Brake System Hoses Front | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078612 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRHOF | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Brake System Air Lines | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078613 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRAIR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Steering System Hoses | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078615 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -STRSYS-STHLF-STRHO | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Hoist System Hoses | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078609 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-HSTHO | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Differential System Hoses | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078606 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-DIFFL-DIFHO | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Fast Fill & SOS Hose | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103974 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-FFSOS | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Ladder Hoses | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104032 | 04.01.2028 | 22000 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-LADHO | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT179 | DT179 Repl Cyl Hoist RH | 2028-01-04 | 2028-01-25 | 21 days | FY28 | 49 | 90003114 | 2 | 1000035010 | 10.03.2028 | 28000 | CLB-MP-HAUL-DT179 -HYDSYS-HOCYL-HCYLR | 7500 | 84079 | 16016 | CLB-MP-HAUL-DT179 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 - Onsite Shut (EOL - 01/2030) | 2028-01-23 | 2028-02-13 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Brake System Hoses Front | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078745 | 30.11.2027 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRHOF | 7500 | 83931 | 61120 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Brake Wheel LH | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 38 | 90003104 | 2 | 1000035459 | 01.12.2027 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-AXLES-HUBLH | 7500 | 83931 | 12074 | CLB-MP-HAUL-DT188 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Engine Cat 3516B | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156861 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -ENGINE | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Radiator Engine Cooling | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 85 | 90003081 | 1 | 1000035445 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-RADTR | 7400 | 83931 | 33801 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Fuel Tank Mounts | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078752 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -ENGINE-FUSYS-FULTK | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Engine Pump Drive | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 62 | 90003089 | 1 | 1000035447 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Pump Drive Driveshaft Unis | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 4 | 90009874 | 1 | 1000035450 | 23.01.2028 | 11000 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR-DRSHT | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Torque Converter | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 62 | 90003092 | 1 | 1000035448 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -TRNSYS-TRQUE | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Transmission | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 48 | 90003093 | 1 | 1000035449 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -TRNSYS-TRANS | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Pump Torque Converter Charge | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080210 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TCCPP | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Transmission Oil Cooler | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 13 | 90003532 | 1 | 1000040997 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -TRNSYS-TROLC | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Drive Shaft Transmission | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154417 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-DRSHT | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Differential | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 66 | 90003098 | 1 | 1000035453 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-DIFFL | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Final Drive LH | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 56 | 90003099 | 1 | 1000035454 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-FDRVE-FDRLH | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Final Drive RH | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 56 | 90003100 | 1 | 1000035455 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-FDRVE-FDRRH | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Hyd Motor Axle Lube Rear | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 9 | 90003101 | 1 | 1000035456 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-HYM01 | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl AOC Fan Motor | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 5 | 90003102 | 1 | 1000035457 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-MTFAN | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Overhaul Accumulator Brake | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072208 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BACCM | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Pump Brake Control | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 5 | 90003106 | 1 | 1000035462 | 23.01.2028 | 11000 | CLB-MP-HAUL-DT188 -BRKSYS-HYFPP | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Valve Brake | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 18 | 90003107 | 1 | 1000035463 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRVLV | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Rotochamber Front | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072398 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTFR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Rotochamber LHR | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072436 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTLR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Rotochamber RHR | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072474 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTRR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Valve Steering & AHS EH | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078747 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRSYS-STVLV | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Ovhl Accumulator Hyd Steer Front | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072094 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCF | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Ovhl Accumulator Hyd Steer Middle | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072132 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCM | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Ovhl Accumulator Hyd Steering Rear | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072170 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Pump Hoist & Brake | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 10 | 90003113 | 1 | 1000035470 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -HYDSYS-HOPMP | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Air Dryer | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 14 | 90003115 | 1 | 1000035473 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -PNEUMC-AIRDR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Ovhl Axle Housing Dogbone | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 42 | 90003118 | 1 | 1000035476 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-TAGLK | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Service Suspension Cylinders | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106897 | 23.01.2028 | 11000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN | 7500 | 83931 | 10985 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Cyl Suspension LHF | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067858 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYLF | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Cyl Suspension LHR | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 42 | 90003122 | 1 | 1000035481 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYLR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Cyl Suspension RHR | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 42 | 90003122 | 1 | 1000116277 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Transmission System Hoses | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078737 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -TRNSYS-TRANS-TRNHO | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Torque Conv System Hoses | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078738 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -TRNSYS-TRQUE-TRQHO | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Brake Relay Valve | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078743 | 23.01.2028 | 11000 | CLB-MP-HAUL-DT188 -BRKSYS-BRVRL | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Brake System Hoses Rear | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078744 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRHOR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Brake System Air Lines | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078746 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRAIR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Steering System Hoses | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078748 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -STRSYS-STHLF-STRHO | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Hoist System Hoses | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078742 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-HSTHO | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Differential System Hoses | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078739 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -FDRSYS-DIFFL-DIFHO | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Fast Fill & SOS Hose | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103983 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-FFSOS | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Ladder Hoses | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104041 | 23.01.2028 | 22000 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-LADHO | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT188 | DT188 Repl Cyl Steering LH | 2028-01-23 | 2028-02-13 | 21 days | FY28 | 28 | 90003111 | 2 | 1000035467 | 02.02.2028 | 15000 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYL | 7500 | 83931 | 3835 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 - Onsite Shut (EOL - 02/2030) | 2028-02-18 | 2028-03-10 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Engine Cat 3516B | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156637 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -ENGINE | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Radiator Engine Cooling | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 85 | 90003081 | 1 | 1000034708 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-RADTR | 7400 | 83749 | 34457 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Fuel Tank Mounts | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078562 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -ENGINE-FUSYS-FULTK | 7500 | 83749 | 1854 | CLB-MP-HAUL-DT174 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Engine Pump Drive | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 62 | 90003089 | 1 | 1000034710 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Pump Drive Driveshaft Unis | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 4 | 90009874 | 1 | 1000116272 | 18.02.2028 | 11000 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR-DRSHT | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Torque Converter | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 62 | 90003092 | 1 | 1000034711 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -TRNSYS-TRQUE | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Pump Transmission | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 7 | 90003096 | 1 | 1000034714 | 18.02.2028 | 11000 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TMCPP | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Pump Torque Converter Charge | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080176 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TCCPP | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Drive Shaft Transmission | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154389 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-DRSHT | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Differential | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 66 | 90003098 | 1 | 1000034716 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-DIFFL | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Hyd Motor Axle Lube Rear | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 9 | 90003101 | 1 | 1000034719 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-HYM01 | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl AOC Fan Motor | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 5 | 90003102 | 1 | 1000034720 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-MTFAN | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Overhaul Accumulator Brake | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072194 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BACCM | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Valve Brake | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 18 | 90003107 | 1 | 1000034726 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRVLV | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Rotochamber Front | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072384 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTFR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Rotochamber LHR | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072422 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTLR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Rotochamber RHR | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072460 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTRR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Valve Steering & AHS EH | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078557 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRSYS-STVLV | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Ovhl Accumulator Hyd Steer Front | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072080 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCF | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Ovhl Accumulator Hyd Steer Middle | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072118 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCM | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Ovhl Accumulator Hyd Steering Rear | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072156 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Pump Hoist & Brake | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 10 | 90003113 | 1 | 1000034733 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -HYDSYS-HOPMP | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Ovhl Axle A Frame | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 60 | 90015390 | 1 | 1000152634 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-AFRME | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Ovhl Axle Housing Dogbone | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 42 | 90003118 | 1 | 1000034739 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-TAGLK | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake Wheel LH | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 38 | 90003104 | 2 | 1000034722 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-AXLES-HUBLH | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake Wheel RH | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 61 | 90003105 | 2 | 1000034723 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-AXLES-HUBRH | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Cyl Suspension LHF | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067802 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYLF | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Cyl Suspension RHF | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067804 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYRF | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Cyl Suspension LHR | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034744 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYLR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Cyl Suspension RHR | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034745 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYRR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Transmission System Hoses | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078547 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -TRNSYS-TRANS-TRNHO | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Torque Conv System Hoses | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078548 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -TRNSYS-TRQUE-TRQHO | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake Relay Valve | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078553 | 18.02.2028 | 11000 | CLB-MP-HAUL-DT174 -BRKSYS-BRVRL | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake Oil Cooler Front | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080265 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BROCO-BROCF | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake System Hoses Rear | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078554 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRHOR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake System Hoses Front | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078555 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRHOF | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Brake System Air Lines | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078556 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRAIR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Steering System Hoses | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078558 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -STRSYS-STHLF-STRHO | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Hoist System Hoses | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078552 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-HSTHO | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Differential System Hoses | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078549 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-DIFFL-DIFHO | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Fast Fill & SOS Hose | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103969 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-FFSOS | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Ladder Hoses | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104027 | 18.02.2028 | 22000 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-LADHO | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 1Y Air Tank LH External Inspect | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 1.5 | 90038753 | A1 | 1000389354 | 21.02.2028 | 12 Monthly | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH | 7500 | 83507 | 83507 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 1Y Air Tank RH External Inspect | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 1.5 | 90038753 | A1 | 1000389356 | 21.02.2028 | 12 Monthly | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH | 7500 | 83507 | 83507 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Cyl Steering LH | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 28 | 90003111 | 2 | 1000034730 | 25.02.2028 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYL | 7500 | 83749 | 3272 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT174 | DT174 Repl Cyl Steering RH | 2028-02-18 | 2028-03-10 | 21 days | FY28 | 28 | 90003111 | 3 | 1000034731 | 04.05.2028 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYR | 7500 | 83749 | 16824 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 - Onsite Shut (EOL - 02/2030) | 2028-04-03 | 2028-04-24 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Cyl Steering RH | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 28 | 90003111 | 3 | 1000034344 | 18.03.2028 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYR | 7500 | 83303 | 2776 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Engine Cat 3516B | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156525 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -ENGINE | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Radiator Engine Cooling | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 85 | 90003081 | 1 | 1000034321 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-RADTR | 7400 | 83302 | 31597 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Fuel Tank Mounts | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078429 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -ENGINE-FUSYS-FULTK | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Engine Pump Drive | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 62 | 90003089 | 1 | 1000034323 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Pump Drive Driveshaft Unis | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 4 | 90009874 | 1 | 1000116268 | 03.04.2028 | 11000 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR-DRSHT | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Torque Converter | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 62 | 90003092 | 1 | 1000034324 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -TRNSYS-TRQUE | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Transmission | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 48 | 90003093 | 1 | 1000034325 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -TRNSYS-TRANS | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Pump Transmission | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 7 | 90003096 | 1 | 1000034327 | 03.04.2028 | 11000 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TMCPP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Pump Torque Converter Charge | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080170 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TCCPP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Transmission Oil Cooler | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 13 | 90003532 | 1 | 1000040976 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -TRNSYS-TROLC | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Drive Shaft Transmission | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154375 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-DRSHT | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Differential | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 66 | 90003098 | 1 | 1000034329 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-DIFFL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Hyd Motor Axle Lube Rear | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 9 | 90003101 | 1 | 1000034332 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-HYM01 | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl AOC Fan Motor | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90003102 | 1 | 1000034333 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-MTFAN | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Overhaul Accumulator Brake | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072187 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BACCM | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Pump Brake Control | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90003106 | 1 | 1000034338 | 03.04.2028 | 11000 | CLB-MP-HAUL-DT167 -BRKSYS-HYFPP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Valve Brake | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 18 | 90003107 | 1 | 1000034339 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRVLV | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Rotochamber Front | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072377 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTFR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Rotochamber LHR | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072415 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTLR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Rotochamber RHR | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072453 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTRR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Valve Steering & AHS EH | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078424 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRSYS-STVLV | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Ovhl Accumulator Hyd Steer Front | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072073 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCF | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Ovhl Accumulator Hyd Steer Middle | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072111 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCM | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Ovhl Accumulator Hyd Steering Rear | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072149 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Pump Hoist & Brake | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 10 | 90003113 | 1 | 1000034346 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -HYDSYS-HOPMP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Air Dryer | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 14 | 90003115 | 1 | 1000034349 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -PNEUMC-AIRDR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Ovhl Axle Housing Dogbone | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 42 | 90003118 | 1 | 1000034352 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-TAGLK | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Service Suspension Cylinders | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106876 | 03.04.2028 | 11000 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN | 7500 | 83303 | 9432 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Cyl Suspension LHF | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067774 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYLF | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Cyl Suspension LHR | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034357 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYLR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Cyl Suspension RHR | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034358 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYRR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Transmission System Hoses | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078414 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -TRNSYS-TRANS-TRNHO | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Torque Conv System Hoses | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078415 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -TRNSYS-TRQUE-TRQHO | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Brake Relay Valve | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078420 | 03.04.2028 | 11000 | CLB-MP-HAUL-DT167 -BRKSYS-BRVRL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Brake Oil Cooler Front | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080238 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BROCO-BROCF | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Brake System Hoses Rear | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078421 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRHOR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Brake System Hoses Front | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078422 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRHOF | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Brake System Air Lines | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078423 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRAIR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Steering System Hoses | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078425 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -STRSYS-STHLF-STRHO | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Hoist System Hoses | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078419 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-HSTHO | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Differential System Hoses | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078416 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-DIFFL-DIFHO | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Fast Fill & SOS Hose | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103962 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-FFSOS | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT167 | DT167 Repl Ladder Hoses | 2028-04-03 | 2028-04-24 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104020 | 03.04.2028 | 22000 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-LADHO | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 - Onsite Shut (EOL - 05/2030) | 2028-05-09 | 2028-05-30 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Engine Cat 3516B | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156685 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -ENGINE | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Radiator Engine Cooling | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 85 | 90003081 | 1 | 1000034873 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-RADTR | 7400 | 81791 | 31511 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Fuel Tank Mounts | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078581 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -ENGINE-FUSYS-FULTK | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Engine Pump Drive | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 62 | 90003089 | 1 | 1000034875 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Pump Drive Driveshaft Unis | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 4 | 90009874 | 1 | 1000034878 | 09.05.2028 | 11000 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR-DRSHT | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Torque Converter | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 62 | 90003092 | 1 | 1000034876 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -TRNSYS-TRQUE | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Pump Torque Converter Charge | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080179 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TCCPP | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Transmission Oil Cooler | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 13 | 90003532 | 1 | 1000040986 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -TRNSYS-TROLC | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Drive Shaft Transmission | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154395 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-DRSHT | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Differential | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 66 | 90003098 | 1 | 1000034881 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-DIFFL | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Final Drive LH | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 56 | 90003099 | 1 | 1000034882 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-FDRVE-FDRLH | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Final Drive RH | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 56 | 90003100 | 1 | 1000034883 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-FDRVE-FDRRH | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Hyd Motor Axle Lube Rear | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 9 | 90003101 | 1 | 1000034884 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-HYM01 | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl AOC Fan Motor | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90003102 | 1 | 1000034885 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-MTFAN | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Overhaul Accumulator Brake | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072197 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BACCM | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Pump Brake Control | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90003106 | 1 | 1000034890 | 09.05.2028 | 11000 | CLB-MP-HAUL-DT177 -BRKSYS-HYFPP | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Valve Brake | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 18 | 90003107 | 1 | 1000034891 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRVLV | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Rotochamber Front | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072387 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTFR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Rotochamber RHR | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072463 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTRR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Valve Steering & AHS EH | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078576 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRSYS-STVLV | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Ovhl Accumulator Hyd Steer Front | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072083 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCF | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Ovhl Accumulator Hyd Steer Middle | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072121 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCM | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Ovhl Accumulator Hyd Steering Rear | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072159 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Pump Hoist & Brake | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 10 | 90003113 | 1 | 1000034898 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -HYDSYS-HOPMP | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Ovhl Axle A Frame | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 60 | 90015390 | 1 | 1000130648 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-AFRME | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Ovhl Axle Housing Dogbone | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 42 | 90003118 | 1 | 1000034904 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-TAGLK | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake Wheel RH | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 61 | 90003105 | 2 | 1000034888 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-AXLES-HUBRH | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Service Suspension Cylinders | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 27 | 90012840 | 1 | 1000106886 | 09.05.2028 | 11000 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN | 7500 | 81791 | 14442 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Cyl Suspension LHF | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067814 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYLF | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Cyl Suspension RHF | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067816 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYRF | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Cyl Suspension LHR | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034909 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYLR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Transmission System Hoses | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078566 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -TRNSYS-TRANS-TRNHO | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Torque Conv System Hoses | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078567 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -TRNSYS-TRQUE-TRQHO | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake Relay Valve | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078572 | 09.05.2028 | 11000 | CLB-MP-HAUL-DT177 -BRKSYS-BRVRL | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake Oil Cooler Front | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080268 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BROCO-BROCF | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake System Hoses Rear | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078573 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRHOR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake System Hoses Front | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078574 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRHOF | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake System Air Lines | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078575 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRAIR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Steering System Hoses | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078577 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRSYS-STHLF-STRHO | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Hoist System Hoses | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078571 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-HSTHO | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Differential System Hoses | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078568 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -FDRSYS-DIFFL-DIFHO | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Fast Fill & SOS Hose | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103972 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-FFSOS | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Ladder Hoses | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 4 | 90012189 | 1 | 1000104030 | 09.05.2028 | 22000 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-LADHO | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Pump Transmission | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 7 | 90003096 | 1 | 1000034879 | 15.05.2028 | 11000 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TMCPP | 7500 | 81791 | 3161 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Rotochamber LHR | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072425 | 15.05.2028 | 22000 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTLR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Brake Wheel LH | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 38 | 90003104 | 2 | 1000034887 | 15.05.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-AXLES-HUBLH | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 1Y Air Tank LH External Inspect | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 1.5 | 90038753 | A1 | 1000389366 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH | 7500 | 81529 | 8461 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 1Y Air Tank RH External Inspect | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 1.5 | 90038753 | A1 | 1000389368 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH | 7500 | 81529 | 8461 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Steering HMU | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 14 | 90003110 | 1 | 1000034894 | 21.06.2028 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STHMU | 7500 | 81791 | 15830 | CLB-MP-HAUL-DT177 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT177 | DT177 Repl Steering Link & Arm Rebush | 2028-05-09 | 2028-05-30 | 21 days | FY28 | 45 | 90038355 | A1 | 1000385427 | 21.06.2028 | 30000 | CLB-MP-HAUL-DT177 -STRSYS-STLTR | 7500 | 81791 | 15833 | CLB-MP-HAUL-DT177 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 - Onsite Shut (EOL - 05/2030) | 2028-05-31 | 2028-06-21 | 21 days | FY28
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Torque Converter | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 62 | 90003092 | 1 | 1000034104 | 01.04.2028 | 22000 | CLB-MP-HAUL-DT163 -TRNSYS-TRQUE | 7500 | 81237 | 9351 | CLB-MP-HAUL-DT163 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Final Drive RH | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 56 | 90003100 | 1 | 1000034111 | 01.04.2028 | 22000 | CLB-MP-HAUL-DT163 -FDRSYS-FDRVE-FDRRH | 7500 | 81237 | 9365 | CLB-MP-HAUL-DT163 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Transmission | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 48 | 90003093 | 1 | 1000034105 | 02.04.2028 | 22000 | CLB-MP-HAUL-DT163 -TRNSYS-TRANS | 7500 | 81237 | 9334 | CLB-MP-HAUL-DT163 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Pump Transmission | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 7 | 90003096 | 1 | 1000034107 | 02.04.2028 | 11000 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TMCPP | 7500 | 81237 | 9334 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Engine Cat 3516B | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 142 | 90017315 | 1 | 1000156461 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -ENGINE | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Radiator Engine Cooling | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 85 | 90003081 | 1 | 1000034101 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-RADTR | 7400 | 81237 | 29153 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Fuel Tank Mounts | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 16 | 90009887 | 1 | 1000078353 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -ENGINE-FUSYS-FULTK | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Engine Pump Drive | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 62 | 90003089 | 1 | 1000034103 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Pump Torque Converter Charge | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90003095 | 1 | 1000080164 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TCCPP | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Transmission Oil Cooler | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 13 | 90003532 | 1 | 1000040972 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -TRNSYS-TROLC | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Drive Shaft Transmission | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 16 | 90017134 | 1 | 1000154367 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -FDRSYS-DRSHT | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Differential | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 66 | 90003098 | 1 | 1000034109 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -FDRSYS-DIFFL | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Hyd Motor Axle Lube Rear | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 9 | 90003101 | 1 | 1000034112 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-HYM01 | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl AOC Fan Motor | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90003102 | 1 | 1000034113 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-MTFAN | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Overhaul Accumulator Brake | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 10 | 90009313 | 1 | 1000072183 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BACCM | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Pump Brake Control | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90003106 | 1 | 1000034118 | 31.05.2028 | 11000 | CLB-MP-HAUL-DT163 -BRKSYS-HYFPP | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Valve Brake | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 18 | 90003107 | 1 | 1000034119 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRVLV | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Rotochamber Front | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90009308 | 1 | 1000072373 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTFR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Rotochamber LHR | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072411 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTLR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Rotochamber RHR | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90009309 | 1 | 1000072449 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTRR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Valve Steering & AHS EH | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 10 | 90009881 | 1 | 1000078348 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRSYS-STVLV | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Ovhl Accumulator Hyd Steer Front | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072069 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCF | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Ovhl Accumulator Hyd Steer Middle | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072107 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCM | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Ovhl Accumulator Hyd Steering Rear | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 7 | 90009314 | 1 | 1000072145 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Pump Hoist & Brake | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 10 | 90003113 | 1 | 1000034126 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -HYDSYS-HOPMP | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Air Dryer | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 14 | 90003115 | 1 | 1000366597 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -PNEUMC-AIRDR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Ovhl Axle A Frame | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 60 | 90015390 | 1 | 1000130635 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-AFRME | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Ovhl Axle Housing Dogbone | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 42 | 90003118 | 1 | 1000034132 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-TAGLK | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Brake Wheel RH | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 61 | 90003105 | 2 | 1000034116 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-AXLES-HUBRH | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Cyl Suspension RHF | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 66 | 90003121 | 1 | 1000067760 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYRF | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Cyl Suspension LHR | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034137 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYLR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Cyl Suspension RHR | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 42 | 90003122 | 1 | 1000034138 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYRR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Brake System Air Lines | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 24 | 90009880 | 1 | 1000078347 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRAIR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Brake System Hoses Front | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 12 | 90009879 | 1 | 1000078346 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRHOF | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Brake System Hoses Rear | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 6 | 90009878 | 1 | 1000078345 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRHOR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Brake Oil Cooler Front | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 5 | 90003108 | 1 | 1000080234 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -BRKSYS-BROCO-BROCF | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Brake Relay Valve | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 6 | 90009877 | 1 | 1000078344 | 31.05.2028 | 11000 | CLB-MP-HAUL-DT163 -BRKSYS-BRVRL | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Steering System Hoses | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 24 | 90009882 | 1 | 1000078349 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -STRSYS-STHLF-STRHO | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Transmission System Hoses | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 8 | 90009871 | 1 | 1000078318 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -TRNSYS-TRANS-TRNHO | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Torque Conv System Hoses | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 4 | 90009872 | 1 | 1000078319 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -TRNSYS-TRQUE-TRQHO | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Hoist System Hoses | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 12 | 90009903 | 1 | 1000078343 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-HSTHO | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Differential System Hoses | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 2 | 90009873 | 1 | 1000078340 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -FDRSYS-DIFFL-DIFHO | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Fast Fill & SOS Hose | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 36 | 90012188 | 1 | 1000103900 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-FFSOS | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Ladder Hoses | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 4 | 90012189 | 1 | 1000103996 | 31.05.2028 | 22000 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-LADHO | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Pump Drive Driveshaft Unis | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 4 | 90009874 | 1 | 1000034106 | 02.06.2028 | 11000 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR-DRSHT | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Hyd Pump Steering Main | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 8 | 90003109 | 1 | 1000034121 | 09.06.2028 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STPMP | 7500 | 81237 | 895 | CLB-MP-HAUL-DT163 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT163 | DT163 Repl Steering HMU | 2028-05-31 | 2028-06-21 | 21 days | FY28 | 14 | 90003110 | 1 | 1000034122 | 11.06.2028 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STHMU | 7500 | 81237 | 895 | CLB-MP-HAUL-DT163 -STRSYS-STHMU90003110
| Onsite Shut |  | Fortescue |  | FY29 - ONSITE SHUTDOWNS | 2028-07-01 | 2029-06-30 | 364 days | FY29
| Onsite Shut | Haul | Fortescue |  | HAUL | 2028-07-01 | 2029-06-30 | 364 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 - Onsite Shut (EOL - 03/2030) | 2028-07-02 | 2028-07-23 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Engine Cat 3516B | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156653 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -ENGINE | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Engine Pump Drive | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 62 | 90003089 | 1 | 1000034765 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Pump Drive Driveshaft Unis | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034768 | 02.07.2028 | 11000 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR-DRSHT | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Transmission Oil Cooler | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040984 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -TRNSYS-TROLC | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Drive Shaft Transmission | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154391 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-DRSHT | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Differential | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 66 | 90003098 | 1 | 1000034771 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-DIFFL | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Hyd Motor Axle Lube Rear | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 9 | 90003101 | 1 | 1000034774 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-HYM01 | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl AOC Fan Motor | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 5 | 90003102 | 1 | 1000034775 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-MTFAN | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Overhaul Accumulator Brake | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072195 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BACCM | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Valve Brake | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034781 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRVLV | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Rotochamber Front | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072385 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTFR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Rotochamber LHR | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072423 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTLR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Rotochamber RHR | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072461 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTRR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Ovhl Accumulator Hyd Steer Front | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072081 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCF | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Ovhl Accumulator Hyd Steer Middle | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072119 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCM | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Ovhl Accumulator Hyd Steering Rear | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072157 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Pump Hoist & Brake | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 10 | 90003113 | 1 | 1000034788 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -HYDSYS-HOPMP | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Ovhl Axle A Frame | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130646 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-AFRME | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Ovhl Axle Housing Dogbone | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034794 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-TAGLK | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Cyl Suspension LHF | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067806 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYLF | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Cyl Suspension RHF | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067808 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYRF | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Cyl Suspension LHR | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034799 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYLR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Cyl Suspension RHR | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034800 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYRR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Transmission System Hoses | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 8 | 90009871 | 1 | 1000079598 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -TRNSYS-TRANS-TRNHO | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Torque Conv System Hoses | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 4 | 90009872 | 1 | 1000079599 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -TRNSYS-TRQUE-TRQHO | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Brake Relay Valve | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 6 | 90009877 | 1 | 1000079604 | 02.07.2028 | 11000 | CLB-MP-HAUL-DT175 -BRKSYS-BRVRL | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Brake System Hoses Rear | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 6 | 90009878 | 1 | 1000079605 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRHOR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Brake System Hoses Front | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 12 | 90009879 | 1 | 1000079606 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRHOF | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Brake System Air Lines | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 24 | 90009880 | 1 | 1000079607 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRAIR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Steering System Hoses | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 24 | 90009882 | 1 | 1000079609 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -STRSYS-STHLF-STRHO | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Hoist System Hoses | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 12 | 90009903 | 1 | 1000079603 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-HSTHO | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Differential System Hoses | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 2 | 90009873 | 1 | 1000079600 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-DIFFL-DIFHO | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Fast Fill & SOS Hose | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103970 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-FFSOS | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Ladder Hoses | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104028 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-LADHO | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Fuel Tank Mounts | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 16 | 90009887 | 1 | 1000079613 | 03.07.2028 | 22000 | CLB-MP-HAUL-DT175 -ENGINE-FUSYS-FULTK | 7500 | 82722 | 31520 | CLB-MP-HAUL-DT175 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Pump Transmission | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 7 | 90003096 | 1 | 1000034769 | 03.07.2028 | 11000 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TMCPP | 7500 | 82721 | 7663 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Pump Brake Control | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 5 | 90003106 | 1 | 1000034780 | 03.07.2028 | 11000 | CLB-MP-HAUL-DT175 -BRKSYS-HYFPP | 7500 | 82722 | 20002 | CLB-MP-HAUL-DT175 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Service Suspension Cylinders | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106884 | 03.07.2028 | 11000 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN | 7500 | 82722 | 11190 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT175 | DT175 Repl Brake Slack Adjuster Front | 2028-07-02 | 2028-07-23 | 21 days | FY29 | 4 | 90009306 | 1 | 1000072233 | 21.09.2028 | 18000 | CLB-MP-HAUL-DT175 -BRKSYS-SLACK-SLACF | 7500 | 82722 | 528 | CLB-MP-HAUL-DT175 -BRKSYS-SLACK-SLACF90009306
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 - Onsite Shut (EOL - 04/2030) | 2028-08-05 | 2028-08-26 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Drive Shaft Transmission | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154431 | 28.06.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-DRSHT | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Engine Cat 3516B | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156973 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -ENGINE | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Fuel Tank Mounts | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078847 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -ENGINE-FUSYS-FULTK | 7500 | 82554 | 54345 | CLB-MP-HAUL-DT195 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Engine Pump Drive | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 62 | 90003089 | 1 | 1000035865 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Torque Converter | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 62 | 90003092 | 1 | 1000035866 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -TRNSYS-TRQUE | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Transmission | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 48 | 90003093 | 1 | 1000035867 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -TRNSYS-TRANS | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Pump Transmission | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 7 | 90003096 | 1 | 1000035869 | 05.08.2028 | 11000 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TMCPP | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Pump Torque Converter Charge | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 5 | 90003095 | 1 | 1000080217 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TCCPP | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Transmission Oil Cooler | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 13 | 90003532 | 1 | 1000041004 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -TRNSYS-TROLC | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Differential | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 66 | 90003098 | 1 | 1000035871 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-DIFFL | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Final Drive LH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 56 | 90003099 | 1 | 1000035872 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-FDRVE-FDRLH | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Hyd Motor Axle Lube Rear | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 9 | 90003101 | 1 | 1000035874 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-HYM01 | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl AOC Fan Motor | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 5 | 90003102 | 1 | 1000035875 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-MTFAN | 7500 | 82554 | 7002 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Overhaul Accumulator Brake | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072215 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BACCM | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Pump Brake Control | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 5 | 90003106 | 1 | 1000035880 | 05.08.2028 | 11000 | CLB-MP-HAUL-DT195 -BRKSYS-HYFPP | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Valve Brake | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 18 | 90003107 | 1 | 1000035881 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRVLV | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Rotochamber LHR | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072443 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTLR | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Rotochamber RHR | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072481 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTRR | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Valve Steering & AHS EH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 10 | 90009881 | 1 | 1000078842 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRSYS-STVLV | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Ovhl Accumulator Hyd Steer Front | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072101 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCF | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Ovhl Accumulator Hyd Steer Middle | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072139 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCM | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Ovhl Accumulator Hyd Steering Rear | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072177 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCR | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Pump Hoist & Brake | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 10 | 90003113 | 1 | 1000035888 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -HYDSYS-HOPMP | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Air Dryer | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 14 | 90003115 | 1 | 1000035891 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -PNEUMC-AIRDR | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Ovhl Axle Housing Dogbone | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 42 | 90003118 | 1 | 1000035894 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-TAGLK | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake Wheel LH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 38 | 90003104 | 2 | 1000035877 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-AXLES-HUBLH | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake Wheel RH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 61 | 90003105 | 2 | 1000035878 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-AXLES-HUBRH | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Service Suspension Cylinders | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106944 | 05.08.2028 | 11000 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN | 7500 | 82554 | 11212 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Cyl Suspension LHF | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067886 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYLF | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Cyl Suspension RHF | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067888 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYRF | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Cyl Suspension LHR | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 42 | 90003122 | 1 | 1000035899 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYLR | 7500 | 82530 | 6982 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Cyl Suspension RHR | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 42 | 90003122 | 1 | 1000035900 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYRR | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Transmission System Hoses | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078832 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -TRNSYS-TRANS-TRNHO | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Torque Conv System Hoses | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078833 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -TRNSYS-TRQUE-TRQHO | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake Relay Valve | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078838 | 05.08.2028 | 11000 | CLB-MP-HAUL-DT195 -BRKSYS-BRVRL | 7500 | 82554 | 18183 | CLB-MP-HAUL-DT195 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake Oil Cooler Front | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080299 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BROCO-BROCF | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake System Hoses Rear | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078839 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRHOR | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake System Hoses Front | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078840 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRHOF | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Brake System Air Lines | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078841 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRAIR | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Steering System Hoses | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078843 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -STRSYS-STHLF-STRHO | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Hoist System Hoses | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078837 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-HSTHO | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Differential System Hoses | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078834 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-DIFFL-DIFHO | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Fast Fill & SOS Hose | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103990 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-FFSOS | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Ladder Hoses | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104048 | 05.08.2028 | 22000 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-LADHO | 7500 | 82554 | 29751 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Final Drive RH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 56 | 90003100 | 1 | 1000035873 | 07.08.2028 | 22000 | CLB-MP-HAUL-DT195 -FDRSYS-FDRVE-FDRRH | 7500 | 82554 | 6941 | CLB-MP-HAUL-DT195 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Hyd Pump Steering Main | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 8 | 90003109 | 1 | 1000035883 | 22.09.2028 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STPMP | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Steering HMU | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 14 | 90003110 | 1 | 1000035884 | 22.09.2028 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STHMU | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Cyl Steering LH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 28 | 90003111 | 2 | 1000035885 | 22.09.2028 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYL | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Cyl Steering RH | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 28 | 90003111 | 3 | 1000035886 | 22.09.2028 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYR | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT195 | DT195 Repl Steering Link & Arm Rebush | 2028-08-05 | 2028-08-26 | 21 days | FY29 | 45 | 90038355 | A1 | 1000385463 | 22.09.2028 | 30000 | CLB-MP-HAUL-DT195 -STRSYS-STLTR | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 - Onsite Shut (EOL - 05/2034) | 2028-09-10 | 2028-10-01 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 1Y Air Tank LH External Inspect | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389462 | 04.08.2028 | 12 Monthly | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH | 7500 | 51345 | 51345 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 1Y Air Tank RH External Inspect | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389464 | 04.08.2028 | 12 Monthly | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH | 7500 | 51345 | 51345 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Fuel Tank Mounts | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 16 | 90009887 | 1 | 1000150719 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -ENGINE-FUSYS-FULTK | 7500 | 51346 | 51346 | CLB-MP-HAUL-DT225 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Engine Pump Drive | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 62 | 90003089 | 1 | 1000150661 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Pump Drive Driveshaft Unis | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 4 | 90009874 | 1 | 1000150664 | 10.09.2028 | 11000 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR-DRSHT | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Torque Converter | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 62 | 90003092 | 1 | 1000150662 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -TRNSYS-TRQUE | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Torque Conv System Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 4 | 90009872 | 1 | 1000150707 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -TRNSYS-TRQUE-TRQHO | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Transmission | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 48 | 90003093 | 1 | 1000150663 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -TRNSYS-TRANS | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Transmission System Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 8 | 90009871 | 1 | 1000150706 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -TRNSYS-TRANS-TRNHO | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Pump Transmission | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 7 | 90003096 | 1 | 1000150665 | 10.09.2028 | 11000 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TMCPP | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Pump Torque Converter Charge | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90003095 | 1 | 1000150721 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TCCPP | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Transmission Oil Cooler | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 13 | 90003532 | 1 | 1000150690 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -TRNSYS-TROLC | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Differential System Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 2 | 90009873 | 1 | 1000150708 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-DIFFL-DIFHO | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Hyd Motor Axle Lube Rear | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 9 | 90003101 | 1 | 1000150670 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-HYM01 | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl AOC Fan Motor | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90003102 | 1 | 1000150671 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-MTFAN | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Brake Relay Valve | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 6 | 90009877 | 1 | 1000150711 | 10.09.2028 | 11000 | CLB-MP-HAUL-DT225 -BRKSYS-BRVRL | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Overhaul Accumulator Brake | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 10 | 90009313 | 1 | 1000150698 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BACCM | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Pump Brake Control | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90003106 | 1 | 1000150674 | 10.09.2028 | 11000 | CLB-MP-HAUL-DT225 -BRKSYS-HYFPP | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Valve Brake | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 18 | 90003107 | 1 | 1000150675 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRVLV | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Brake Oil Cooler Front | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90003108 | 1 | 1000150722 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BROCO-BROCF | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Rotochamber Front | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90009308 | 1 | 1000150702 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTFR | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Rotochamber LHR | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90009309 | 1 | 1000150703 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTLR | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Rotochamber RHR | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 5 | 90009309 | 1 | 1000150704 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTRR | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Brake System Air Lines | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 24 | 90027644 | A1 | 1000150714 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRAIR | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRAIR90027644
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Front Brake System Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 12 | 90009879 | 1 | 1000150713 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRHOF | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Brake System Hoses Rear | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 6 | 90009878 | 1 | 1000150712 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRHOR | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl AHS EH Steering Valve | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 10 | 90009881 | 1 | 1000150715 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -AHSYST-AHSTS-AHSEV |  |  |  | CLB-MP-HAUL-DT225 -AHSYST-AHSTS-AHSEV90009881
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Ovhl Accumulator Hyd Steer Front | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 7 | 90009314 | 1 | 1000150695 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCF | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Ovhl Accumulator Hyd Steer Middle | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 7 | 90009314 | 1 | 1000150696 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCM | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Ovhl Accumulator Hyd Steering Rear | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 7 | 90009314 | 1 | 1000150697 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCR | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Steering System Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 24 | 90009882 | 1 | 1000150716 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRSYS-STHLF-STRHO | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Pump Hoist | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 10 | 90003113 | 1 | 1000150681 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -HYDSYS-HOPMP | 7500 | 51346 | 1225 | CLB-MP-HAUL-DT225 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Fast Fill & SOS Hose | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 36 | 90012188 | 1 | 1000150724 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-FFSOS | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Hoist System Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 12 | 90009903 | 1 | 1000150710 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-HSTHO | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Ladder Hoses | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 4 | 90012189 | 1 | 1000150725 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-LADHO | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Air Dryer | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 16 | 90003115 | A2 | 1000150684 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -PNEUMC-AIRDR | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Ovhl Axle A Frame | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 60 | 90015390 | 1 | 1000150735 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-AFRME | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Ovhl Axle Housing Dogbone | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 42 | 90003118 | 1 | 1000150686 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-TAGLK | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Service Suspension Cylinders | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 27 | 90012840 | 1 | 1000150728 | 10.09.2028 | 11000 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN | 7500 | 51346 | 10798 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Cyl Suspension LHF | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 66 | 90003121 | 1 | 1000150693 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYLF | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Cyl Suspension RHF | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 66 | 90003121 | 1 | 1000150694 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYRF | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Cyl Suspension LHR | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 42 | 90003122 | 1 | 1000150687 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYLR | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Cyl Suspension RHR | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 42 | 90003122 | 1 | 1000150688 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYRR | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Engine Cat 3516B | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 361 | 90017317 | 1 | 1000157085 | 18.09.2028 | 22000 | CLB-MP-HAUL-DT225 -ENGINE | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -ENGINE90017317
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Drive Shaft Transmission | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154445 | 18.09.2028 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-DRSHT | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Differential | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 66 | 90003098 | 1 | 1000150667 | 18.09.2028 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-DIFFL | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Steering Link & Arm Rebush | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 45 | 90038355 | A1 | 1000385477 | 15.10.2028 | 30000 | CLB-MP-HAUL-DT225 -STRSYS-STLTR | 7500 | 51346 | 13495 | CLB-MP-HAUL-DT225 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT225 | DT225 Repl Tyre Sense Battery | 2028-09-10 | 2028-10-01 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163989 | 01.11.2028 | 24 Monthly | CLB-MP-HAUL-DT225 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT225 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 - Onsite Shut (EOL - 05/2030) | 2028-10-11 | 2028-11-01 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Engine Midlife complete | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 119.5 | 90017316 | 1 | 1000156715 | 04.09.2028 | 11000 | CLB-MP-HAUL-DT178 -ENGINE | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -ENGINE90017316
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Midlife Valve Set - Adjust | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 12 | 90017314 | 1 | 1000390942 | 04.09.2028 | 11000 | CLB-MP-HAUL-DT178 -ENGINE | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -ENGINE90017314
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Drive Shaft Transmission | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154397 | 07.09.2028 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-DRSHT | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Transmission | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 48 | 90003093 | 1 | 1000034932 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -TRNSYS-TRANS | 7500 | 81600 | 5739 | CLB-MP-HAUL-DT178 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Pump Transmission | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 7 | 90003096 | 1 | 1000034934 | 03.10.2028 | 11000 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TMCPP | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Pump Torque Converter Charge | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 5 | 90003095 | 1 | 1000080200 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TCCPP | 7500 | 81600 | 5739 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Transmission Oil Cooler | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040987 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -TRNSYS-TROLC | 7500 | 81600 | 5579 | CLB-MP-HAUL-DT178 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Final Drive LH | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 56 | 90003099 | 1 | 1000034937 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-FDRVE-FDRLH | 7500 | 81600 | 5739 | CLB-MP-HAUL-DT178 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Rotochamber Front | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072388 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTFR | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Rotochamber RHR | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072464 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTRR | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Ovhl Axle Housing Dogbone | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034959 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-TAGLK | 7500 | 81600 | 5739 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake Wheel RH | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 61 | 90003105 | 2 | 1000034943 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-AXLES-HUBRH | 7500 | 81600 | 5579 | CLB-MP-HAUL-DT178 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Cyl Suspension RHF | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067820 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYRF | 7500 | 81600 | 5579 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Cyl Suspension LHR | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034964 | 03.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYLR | 7500 | 81600 | 5739 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Valve Steering & AHS EH | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 10 | 90009881 | 1 | 1000078595 | 08.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRSYS-STVLV | 7500 | 81600 | 5579 | CLB-MP-HAUL-DT178 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Fuel Tank Mounts | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078600 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -ENGINE-FUSYS-FULTK | 7500 | 81600 | 53132 | CLB-MP-HAUL-DT178 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Engine Pump Drive | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 62 | 90003089 | 1 | 1000034930 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Pump Drive Driveshaft Unis | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034933 | 11.10.2028 | 11000 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR-DRSHT | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl AOC Fan Motor | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 5 | 90003102 | 1 | 1000034940 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-MTFAN | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Overhaul Accumulator Brake | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072198 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BACCM | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Valve Brake | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034946 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRVLV | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Ovhl Accumulator Hyd Steer Front | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072084 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCF | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Ovhl Accumulator Hyd Steer Middle | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072122 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCM | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Ovhl Accumulator Hyd Steering Rear | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072160 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCR | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Air Dryer | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 14 | 90003115 | 1 | 1000034956 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -PNEUMC-AIRDR | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Ovhl Axle A Frame | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130649 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-AFRME | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake Wheel LH | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 38 | 90003104 | 2 | 1000034942 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-AXLES-HUBLH | 7500 | 81600 | 5579 | CLB-MP-HAUL-DT178 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Service Suspension Cylinders | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106887 | 11.10.2028 | 11000 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Transmission System Hoses | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078585 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -TRNSYS-TRANS-TRNHO | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Torque Conv System Hoses | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078586 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -TRNSYS-TRQUE-TRQHO | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake Relay Valve | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078591 | 11.10.2028 | 11000 | CLB-MP-HAUL-DT178 -BRKSYS-BRVRL | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake Oil Cooler Front | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080269 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BROCO-BROCF | 7500 | 81600 | 4753 | CLB-MP-HAUL-DT178 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake System Hoses Rear | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078592 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRHOR | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake System Hoses Front | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078593 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRHOF | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Brake System Air Lines | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078594 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRAIR | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Steering System Hoses | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078596 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -STRSYS-STHLF-STRHO | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Hoist System Hoses | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078590 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-HSTHO | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Differential System Hoses | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078587 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-DIFFL-DIFHO | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Fast Fill & SOS Hose | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103973 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-FFSOS | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Ladder Hoses | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104031 | 11.10.2028 | 22000 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-LADHO | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Hyd Pump Steering Main | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 8 | 90003109 | 1 | 1000034948 | 15.11.2028 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STPMP | 7500 | 81600 | 12786 | CLB-MP-HAUL-DT178 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Steering HMU | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 14 | 90003110 | 1 | 1000034949 | 15.11.2028 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STHMU | 7500 | 81600 | 12786 | CLB-MP-HAUL-DT178 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Steering Link & Arm Rebush | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 45 | 90038355 | A1 | 1000385429 | 15.11.2028 | 30000 | CLB-MP-HAUL-DT178 -STRSYS-STLTR | 7500 | 81600 | 12900 | CLB-MP-HAUL-DT178 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT178 | DT178 Repl Tyre Sense Battery | 2028-10-11 | 2028-11-01 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163953 | 02.12.2028 | 24 Monthly | CLB-MP-HAUL-DT178 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT178 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 - Onsite Shut (EOL - 08/2034) | 2028-11-15 | 2028-12-06 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Cyl Hoist RH | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 49 | 90003114 | 2 | 1000150593 | 04.11.2028 | 28000 | CLB-MP-HAUL-DT224 -HYDSYS-HOCYL-HCYLR | 7500 | 49737 | 11104 | CLB-MP-HAUL-DT224 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Drive Shaft Transmission | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154443 | 13.11.2028 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-DRSHT | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Engine Cat 3516B | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 361 | 90017317 | 1 | 1000157069 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -ENGINE | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -ENGINE90017317
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Radiator Engine Cooling | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 91 | 90003562 | 1 | 1000150570 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-RADTR | 7400 | 49737 | 26914 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-RADTR90003562
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Fuel Tank Mounts | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 16 | 90009887 | 1 | 1000150629 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -ENGINE-FUSYS-FULTK | 7500 | 49737 | 28613 | CLB-MP-HAUL-DT224 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Engine Pump Drive | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 62 | 90003089 | 1 | 1000150571 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Pump Drive Driveshaft Unis | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 4 | 90009874 | 1 | 1000150574 | 15.11.2028 | 11000 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR-DRSHT | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Torque Converter | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 62 | 90003092 | 1 | 1000150572 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -TRNSYS-TRQUE | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Torque Conv System Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 4 | 90009872 | 1 | 1000150617 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -TRNSYS-TRQUE-TRQHO | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Transmission | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 48 | 90003093 | 1 | 1000150573 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -TRNSYS-TRANS | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Transmission System Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 8 | 90009871 | 1 | 1000150616 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -TRNSYS-TRANS-TRNHO | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Pump Transmission | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 7 | 90003096 | 1 | 1000150575 | 15.11.2028 | 11000 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TMCPP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Pump Torque Converter Charge | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90003095 | 1 | 1000150631 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TCCPP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Transmission Oil Cooler | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 13 | 90003532 | 1 | 1000150600 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -TRNSYS-TROLC | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Differential | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 66 | 90003098 | 1 | 1000150577 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-DIFFL | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Differential System Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 2 | 90009873 | 1 | 1000150618 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-DIFFL-DIFHO | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Hyd Motor Axle Lube Rear | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 9 | 90003101 | 1 | 1000150580 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-HYM01 | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl AOC Fan Motor | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90003102 | 1 | 1000150581 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-MTFAN | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Brake Relay Valve | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 6 | 90009877 | 1 | 1000150621 | 15.11.2028 | 11000 | CLB-MP-HAUL-DT224 -BRKSYS-BRVRL | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Overhaul Accumulator Brake | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 10 | 90009313 | 1 | 1000150608 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BACCM | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Pump Brake Control | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90003106 | 1 | 1000150584 | 15.11.2028 | 11000 | CLB-MP-HAUL-DT224 -BRKSYS-HYFPP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Valve Brake | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 18 | 90003107 | 1 | 1000150585 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRVLV | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Brake Oil Cooler Front | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90003108 | 1 | 1000150632 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BROCO-BROCF | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Rotochamber Front | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90009308 | 1 | 1000150612 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTFR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Rotochamber LHR | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90009309 | 1 | 1000150613 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTLR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Rotochamber RHR | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 5 | 90009309 | 1 | 1000150614 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTRR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Brake System Air Lines | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 24 | 90027644 | A1 | 1000150624 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRAIR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRAIR90027644
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Front Brake System Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 12 | 90009879 | 1 | 1000150623 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRHOF | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Brake System Hoses Rear | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 6 | 90009878 | 1 | 1000150622 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRHOR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl AHS EH Steering Valve | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 10 | 90009881 | 1 | 1000150625 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -AHSYST-AHSTS-AHSEV |  |  |  | CLB-MP-HAUL-DT224 -AHSYST-AHSTS-AHSEV90009881
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Ovhl Accumulator Hyd Steer Front | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 7 | 90009314 | 1 | 1000150605 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCF | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Ovhl Accumulator Hyd Steer Middle | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 7 | 90009314 | 1 | 1000150606 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCM | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Ovhl Accumulator Hyd Steering Rear | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 7 | 90009314 | 1 | 1000150607 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Steering System Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 24 | 90009882 | 1 | 1000150626 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRSYS-STHLF-STRHO | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Pump Hoist | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 10 | 90003113 | 1 | 1000150591 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -HYDSYS-HOPMP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Fast Fill & SOS Hose | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 36 | 90012188 | 1 | 1000150634 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-FFSOS | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Hoist System Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 12 | 90009903 | 1 | 1000150620 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-HSTHO | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Ladder Hoses | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 4 | 90012189 | 1 | 1000150635 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-LADHO | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Air Dryer | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 16 | 90003115 | A2 | 1000150594 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -PNEUMC-AIRDR | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Ovhl Axle A Frame | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 60 | 90015390 | 1 | 1000150645 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-AFRME | 7500 | 49737 | 49737 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Ovhl Axle Housing Dogbone | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 42 | 90003118 | 1 | 1000150596 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-TAGLK | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Brake Wheel LH | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 38 | 90003104 | 1 | 1000150582 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-AXLES-HUBLH | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Service Suspension Cylinders | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 27 | 90012840 | 1 | 1000150638 | 15.11.2028 | 11000 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN | 7500 | 49737 | 26842 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Cyl Suspension LHF | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 66 | 90003121 | 1 | 1000150603 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYLF | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Cyl Suspension LHR | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 42 | 90003122 | 1 | 1000150597 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYLR | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT224 | DT224 Repl Cyl Suspension RHR | 2028-11-15 | 2028-12-06 | 21 days | FY29 | 42 | 90003122 | 1 | 1000150598 | 15.11.2028 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYRR | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 - Onsite Shut (EOL - 11/2028) | 2028-12-05 | 2028-12-26 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Fuel Tank Mounts | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078448 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -ENGINE-FUSYS-FULTK | 7500 | 93142 | 50606 | CLB-MP-HAUL-DT168 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Engine Pump Drive | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 62 | 90003089 | 1 | 1000034378 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Pump Drive Driveshaft Unis | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034381 | 05.12.2028 | 11000 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR-DRSHT | 7500 | 93142 | 15366 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Torque Converter | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 62 | 90003092 | 1 | 1000034379 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -TRNSYS-TRQUE | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Transmission Oil Cooler | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040977 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -TRNSYS-TROLC | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Final Drive LH | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 56 | 90003099 | 1 | 1000034385 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-FDRVE-FDRLH | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Final Drive RH | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 56 | 90003100 | 1 | 1000034386 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-FDRVE-FDRRH | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Hyd Motor Axle Lube Rear | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 9 | 90003101 | 1 | 1000034387 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-HYM01 | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Overhaul Accumulator Brake | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072188 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BACCM | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Valve Brake | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034394 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRVLV | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Rotochamber Front | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072378 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTFR | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Rotochamber LHR | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072416 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTLR | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Rotochamber RHR | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072454 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTRR | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Ovhl Accumulator Hyd Steer Front | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072074 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCF | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Ovhl Accumulator Hyd Steer Middle | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072112 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCM | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Air Dryer | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 14 | 90003115 | 1 | 1000034404 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -PNEUMC-AIRDR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Ovhl Axle A Frame | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130640 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-AFRME | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Ovhl Axle Housing Dogbone | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034407 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-TAGLK | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Cyl Suspension RHR | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034413 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYRR | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Transmission System Hoses | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078433 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -TRNSYS-TRANS-TRNHO | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Torque Conv System Hoses | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078434 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -TRNSYS-TRQUE-TRQHO | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake Relay Valve | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078439 | 05.12.2028 | 11000 | CLB-MP-HAUL-DT168 -BRKSYS-BRVRL | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake Oil Cooler Front | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080239 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BROCO-BROCF | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake System Hoses Rear | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078440 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRHOR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake System Hoses Front | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078441 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRHOF | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake System Air Lines | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078442 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRAIR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Hoist System Hoses | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078438 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-HSTHO | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Differential System Hoses | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078435 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-DIFFL-DIFHO | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Fast Fill & SOS Hose | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103963 | 05.12.2028 | 22000 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-FFSOS | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Ovhl Accumulator Hyd Steering Rear | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072150 | 09.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake Wheel RH | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 61 | 90003105 | 2 | 1000034391 | 09.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-AXLES-HUBRH | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Engine Cat 3516B | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156541 | 10.12.2028 | 22000 | CLB-MP-HAUL-DT168 -ENGINE | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Radiator Engine Cooling | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 85 | 90003081 | 1 | 1000034376 | 11.12.2028 | 22000 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-RADTR | 7400 | 93142 | 26428 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Brake Wheel LH | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 38 | 90003104 | 2 | 1000034390 | 11.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-AXLES-HUBLH | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Cyl Suspension RHF | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067780 | 11.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYRF | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Steering System Hoses | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078444 | 11.12.2028 | 22000 | CLB-MP-HAUL-DT168 -STRSYS-STHLF-STRHO | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Ladder Hoses | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104021 | 11.12.2028 | 22000 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-LADHO | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Drive Shaft Transmission | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154377 | 25.12.2028 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-DRSHT | 7500 | 93142 | 32079 | CLB-MP-HAUL-DT168 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT168 | DT168 Repl Steering Ball Studs | 2028-12-05 | 2028-12-26 | 21 days | FY29 | 35 | 90038356 | A1 | 1000385408 | 27.01.2029 | 15000 | CLB-MP-HAUL-DT168 -STRSYS-STLTR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRSYS-STLTR90038356
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 - Onsite Shut (EOL - 11/2028) | 2029-01-19 | 2029-02-09 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Final Drive LH | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 56 | 90003099 | 1 | 1000035399 | 07.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-FDRVE-FDRLH | 7500 | 93170 | 3746 | CLB-MP-HAUL-DT187 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Final Drive RH | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 56 | 90003100 | 1 | 1000035400 | 07.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-FDRVE-FDRRH | 7500 | 93170 | 3746 | CLB-MP-HAUL-DT187 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Engine Cat 3516B | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156845 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -ENGINE | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Radiator Engine Cooling | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 85 | 90003081 | 1 | 1000035390 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-RADTR | 7400 | 93170 | 22807 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Fuel Tank Mounts | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078733 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -ENGINE-FUSYS-FULTK | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Engine Pump Drive | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 62 | 90003089 | 1 | 1000035392 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Pump Drive Driveshaft Unis | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 4 | 90009874 | 1 | 1000035395 | 19.01.2029 | 11000 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR-DRSHT | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Torque Converter | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 62 | 90003092 | 1 | 1000035393 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -TRNSYS-TRQUE | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Pump Transmission | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 7 | 90003096 | 1 | 1000035396 | 19.01.2029 | 11000 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TMCPP | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Transmission Oil Cooler | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040996 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -TRNSYS-TROLC | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Drive Shaft Transmission | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154415 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-DRSHT | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Differential | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 66 | 90003098 | 1 | 1000035398 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-DIFFL | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Hyd Motor Axle Lube Rear | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 9 | 90003101 | 1 | 1000035401 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-HYM01 | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl AOC Fan Motor | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 5 | 90003102 | 1 | 1000035402 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-MTFAN | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Overhaul Accumulator Brake | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072207 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BACCM | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Pump Brake Control | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 5 | 90003106 | 1 | 1000035407 | 19.01.2029 | 11000 | CLB-MP-HAUL-DT187 -BRKSYS-HYFPP | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Valve Brake | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 18 | 90003107 | 1 | 1000035408 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRVLV | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Rotochamber Front | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072397 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTFR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Rotochamber LHR | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072435 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTLR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Rotochamber RHR | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072473 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTRR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Ovhl Accumulator Hyd Steer Front | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072093 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCF | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Ovhl Accumulator Hyd Steer Middle | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072131 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCM | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Ovhl Accumulator Hyd Steering Rear | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072169 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Pump Hoist & Brake | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 10 | 90003113 | 1 | 1000035415 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -HYDSYS-HOPMP | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Ovhl Axle A Frame | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130658 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-AFRME | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Ovhl Axle Housing Dogbone | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 42 | 90003118 | 1 | 1000035421 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-TAGLK | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Brake Wheel RH | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 61 | 90003105 | 2 | 1000035405 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-AXLES-HUBRH | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Service Suspension Cylinders | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106896 | 19.01.2029 | 11000 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Cyl Suspension LHF | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067854 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYLF | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Cyl Suspension LHR | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 42 | 90003122 | 1 | 1000035426 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYLR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Cyl Suspension RHR | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 42 | 90003122 | 1 | 1000035427 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYRR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Transmission System Hoses | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078718 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -TRNSYS-TRANS-TRNHO | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Torque Conv System Hoses | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078719 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -TRNSYS-TRQUE-TRQHO | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Brake Relay Valve | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078724 | 19.01.2029 | 11000 | CLB-MP-HAUL-DT187 -BRKSYS-BRVRL | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Brake Oil Cooler Front | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080291 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BROCO-BROCF | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Brake System Hoses Rear | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078725 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRHOR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Brake System Hoses Front | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078726 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRHOF | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Brake System Air Lines | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078727 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRAIR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Steering System Hoses | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078729 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -STRSYS-STHLF-STRHO | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Hoist System Hoses | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078723 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-HSTHO | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Differential System Hoses | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078720 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -FDRSYS-DIFFL-DIFHO | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Fast Fill & SOS Hose | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103982 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-FFSOS | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Ladder Hoses | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104040 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-LADHO | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Transmission | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 48 | 90003093 | 1 | 1000035394 | 11.02.2029 | 22000 | CLB-MP-HAUL-DT187 -TRNSYS-TRANS | 7500 | 93170 | 3056 | CLB-MP-HAUL-DT187 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 1Y Air Tank LH External Inspect | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389402 | 08.03.2029 | 12 Monthly | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH | 7500 | 92907 | 46760 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 1Y Air Tank RH External Inspect | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389404 | 08.03.2029 | 12 Monthly | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH | 7500 | 92907 | 46760 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Cyl Hoist LH | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 49 | 90003114 | 1 | 1000035416 | 25.04.2029 | 28000 | CLB-MP-HAUL-DT187 -HYDSYS-HOCYL-HCYLL | 7500 | 93170 | 7550 | CLB-MP-HAUL-DT187 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Cyl Hoist RH | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 49 | 90003114 | 2 | 1000035417 | 25.04.2029 | 28000 | CLB-MP-HAUL-DT187 -HYDSYS-HOCYL-HCYLR | 7500 | 93170 | 7549 | CLB-MP-HAUL-DT187 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite Shut | Haul | Fortescue | DT187 | DT187 Repl Steering Link & Arm Rebush | 2029-01-19 | 2029-02-09 | 21 days | FY29 | 45 | 90038355 | A1 | 1000385447 | 15.05.2029 | 30000 | CLB-MP-HAUL-DT187 -STRSYS-STLTR | 7500 | 93170 | 9139 | CLB-MP-HAUL-DT187 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 - Onsite Shut (EOL - 03/2029) | 2029-01-24 | 2029-02-14 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Service Air Conditioner | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 12 | 90017450 | 1 | 1000160377 | 14.12.2028 | 5500 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-AIRCN | 7500 | 90182 | 8268 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-AIRCN90017450
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Service Suspension Cylinders | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106880 | 28.12.2028 | 11000 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN | 7500 | 90182 | 27315 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Tyre Sense Battery | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163946 | 03.01.2029 | 24 Monthly | CLB-MP-HAUL-DT171 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT171 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Steering Link & Arm Rebush | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 45 | 90038355 | A1 | 1000385415 | 13.01.2029 | 30000 | CLB-MP-HAUL-DT171 -STRSYS-STLTR | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STLTR90038355
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Hyd Pump Steering Main | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 8 | 90003109 | 1 | 1000034563 | 13.01.2029 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STPMP | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Steering HMU | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 14 | 90003110 | 1 | 1000034564 | 13.01.2029 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STHMU | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Cyl Steering LH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 28 | 90003111 | 2 | 1000034565 | 13.01.2029 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYL | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Cyl Steering RH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 28 | 90003111 | 3 | 1000034566 | 13.01.2029 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYR | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Radiator Engine Cooling | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 85 | 90003081 | 1 | 1000034543 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-RADTR | 7400 | 90182 | 27381 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Fuel Tank Mounts | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078505 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -ENGINE-FUSYS-FULTK | 7500 | 90182 | 34351 | CLB-MP-HAUL-DT171 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Pump Drive Driveshaft Unis | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034548 | 24.01.2029 | 11000 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR-DRSHT | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Torque Converter | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 62 | 90003092 | 1 | 1000034546 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -TRNSYS-TRQUE | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Transmission | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 48 | 90003093 | 1 | 1000034547 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -TRNSYS-TRANS | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Pump Transmission | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 7 | 90003096 | 1 | 1000116269 | 24.01.2029 | 11000 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TMCPP | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Pump Torque Converter Charge | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90003095 | 1 | 1000080173 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TCCPP | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Transmission Oil Cooler | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040980 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -TRNSYS-TROLC | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Differential | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 66 | 90003098 | 1 | 1000034551 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-DIFFL | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Final Drive LH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 56 | 90003099 | 1 | 1000034552 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-FDRVE-FDRLH | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Final Drive RH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 56 | 90003100 | 1 | 1000034553 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-FDRVE-FDRRH | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Hyd Motor Axle Lube Rear | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 9 | 90003101 | 1 | 1000034554 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-HYM01 | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl AOC Fan Motor | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90003102 | 1 | 1000034555 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-MTFAN | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Overhaul Accumulator Brake | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072191 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BACCM | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Pump Brake Control | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90003106 | 1 | 1000034560 | 24.01.2029 | 11000 | CLB-MP-HAUL-DT171 -BRKSYS-HYFPP | 7500 | 90182 | 15607 | CLB-MP-HAUL-DT171 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Valve Brake | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034561 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRVLV | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Rotochamber Front | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072381 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTFR | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Rotochamber LHR | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072419 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTLR | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Rotochamber RHR | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072457 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTRR | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Valve Steering & AHS EH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 10 | 90009881 | 1 | 1000078500 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRSYS-STVLV | 7500 | 90182 | 27381 | CLB-MP-HAUL-DT171 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Ovhl Accumulator Hyd Steer Front | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072077 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCF | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Ovhl Accumulator Hyd Steer Middle | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072115 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCM | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Ovhl Accumulator Hyd Steering Rear | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072153 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCR | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Pump Hoist & Brake | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 10 | 90003113 | 1 | 1000034568 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -HYDSYS-HOPMP | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Air Dryer | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 14 | 90003115 | 1 | 1000034571 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -PNEUMC-AIRDR | 7500 | 90182 | 27381 | CLB-MP-HAUL-DT171 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Ovhl Axle Housing Dogbone | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034574 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-TAGLK | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake Wheel LH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 38 | 90003104 | 1 | 1000034557 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-AXLES-HUBLH | 7500 | 90182 | 27381 | CLB-MP-HAUL-DT171 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake Wheel RH | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 61 | 90003105 | 1 | 1000034558 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-AXLES-HUBRH | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Cyl Suspension RHF | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067792 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYRF | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Transmission System Hoses | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078490 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -TRNSYS-TRANS-TRNHO | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Torque Conv System Hoses | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078491 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -TRNSYS-TRQUE-TRQHO | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake Relay Valve | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078496 | 24.01.2029 | 11000 | CLB-MP-HAUL-DT171 -BRKSYS-BRVRL | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake Oil Cooler Front | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080262 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BROCO-BROCF | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake System Hoses Rear | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078497 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRHOR | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake System Hoses Front | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078498 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRHOF | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Steering System Hoses | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078501 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRSYS-STHLF-STRHO | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Hoist System Hoses | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078495 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-HSTHO | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Differential System Hoses | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078492 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-DIFFL-DIFHO | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Fast Fill & SOS Hose | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103966 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-FFSOS | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Ladder Hoses | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104024 | 24.01.2029 | 22000 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-LADHO | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Cyl Suspension LHF | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067790 | 26.01.2029 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYLF | 7500 | 90182 | 20246 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake System Air Lines | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078499 | 26.01.2029 | 22000 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRAIR | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 1Y Air Tank LH External Inspect | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389342 | 21.04.2029 | 12 Monthly | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH | 7500 | 89925 | 89925 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 1Y Air Tank RH External Inspect | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389344 | 21.04.2029 | 12 Monthly | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH | 7500 | 89925 | 89925 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake Slack Adjuster Front | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 4 | 90009306 | 1 | 1000072229 | 23.04.2029 | 18000 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACF | 7500 | 90182 | 15607 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACF90009306
789D | Onsite Shut | Haul | Fortescue | DT171 | DT171 Repl Brake Slack Adjuster Rear | 2029-01-24 | 2029-02-14 | 21 days | FY29 | 4 | 90009307 | 1 | 1000072267 | 23.04.2029 | 18000 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACR | 7500 | 90182 | 15607 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACR90009307
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 - Onsite Shut (EOL - 07/2028) | 2029-02-23 | 2029-03-16 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Engine Cat 3516B | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156509 | 16.01.2029 | 22000 | CLB-MP-HAUL-DT166 -ENGINE | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Cyl Steering LH | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 28 | 90003111 | 2 | 1000034288 | 07.02.2029 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYL | 7500 | 95491 | 11151 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Engine Pump Drive | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 62 | 90003089 | 1 | 1000034268 | 23.02.2029 | 22000 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR | 7500 | 95491 | 2828 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Pump Drive Driveshaft Unis | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034271 | 31.03.2029 | 11000 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR-DRSHT | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Torque Converter | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 62 | 90003092 | 1 | 1000097922 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -TRNSYS-TRQUE | 7500 | 95490 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Transmission | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 48 | 90003093 | 1 | 1000034270 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -TRNSYS-TRANS | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Pump Transmission | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 7 | 90003096 | 1 | 1000034272 | 31.03.2029 | 11000 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TMCPP | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Pump Torque Converter Charge | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90003095 | 1 | 1000080169 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TCCPP | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Transmission Oil Cooler | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040975 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -TRNSYS-TROLC | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Hyd Motor Axle Lube Rear | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 9 | 90003101 | 1 | 1000034277 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-HYM01 | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl AOC Fan Motor | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90003102 | 1 | 1000034278 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-MTFAN | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Overhaul Accumulator Brake | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072186 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BACCM | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Pump Brake Control | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90003106 | 1 | 1000034283 | 31.03.2029 | 11000 | CLB-MP-HAUL-DT166 -BRKSYS-HYFPP | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Valve Brake | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034284 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRVLV | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Rotochamber Front | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072376 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTFR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Rotochamber LHR | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072414 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTLR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Rotochamber RHR | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072452 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTRR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Ovhl Accumulator Hyd Steer Front | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072072 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCF | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Ovhl Accumulator Hyd Steer Middle | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072110 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCM | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Ovhl Accumulator Hyd Steering Rear | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072148 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Air Dryer | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 14 | 90003115 | 1 | 1000034294 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -PNEUMC-AIRDR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Ovhl Axle A Frame | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130638 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-AFRME | 7500 | 95490 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Ovhl Axle Housing Dogbone | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034297 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-TAGLK | 7500 | 95473 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake Wheel LH | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 38 | 90003104 | 2 | 1000034280 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-AXLES-HUBLH | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake Wheel RH | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 61 | 90003105 | 2 | 1000034281 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-AXLES-HUBRH | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Cyl Suspension LHF | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067770 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYLF | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Cyl Suspension RHF | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067772 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYRF | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Cyl Suspension LHR | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034302 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYLR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Cyl Suspension RHR | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034303 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYRR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Transmission System Hoses | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078395 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -TRNSYS-TRANS-TRNHO | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Torque Conv System Hoses | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078396 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -TRNSYS-TRQUE-TRQHO | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake Relay Valve | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078401 | 31.03.2029 | 11000 | CLB-MP-HAUL-DT166 -BRKSYS-BRVRL | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake Oil Cooler Front | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080237 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BROCO-BROCF | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake System Hoses Rear | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078402 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRHOR | 7500 | 95491 | 1986 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake System Hoses Front | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078403 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRHOF | 7500 | 95491 | 1986 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Steering System Hoses | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078406 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -STRSYS-STHLF-STRHO | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Hoist System Hoses | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078400 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-HSTHO | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Differential System Hoses | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078397 | 31.03.2029 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-DIFFL-DIFHO | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Fuel Tank Mounts | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078410 | 01.04.2029 | 22000 | CLB-MP-HAUL-DT166 -ENGINE-FUSYS-FULTK | 7500 | 95491 | 25293 | CLB-MP-HAUL-DT166 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Service Suspension Cylinders | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106874 | 01.04.2029 | 11000 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake System Air Lines | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078404 | 01.04.2029 | 22000 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRAIR | 7500 | 95491 | 1986 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Ladder Hoses | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 4 | 90012189 | 1 | 1000103999 | 01.04.2029 | 22000 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-LADHO | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Fast Fill & SOS Hose | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103961 | 06.04.2029 | 22000 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-FFSOS | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Tyre Sense Battery | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163941 | 10.04.2029 | 24 Monthly | CLB-MP-HAUL-DT166 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT166 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 1Y Air Tank LH External Inspect | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389322 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH | 7500 | 95233 | 95233 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 1Y Air Tank RH External Inspect | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389324 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH | 7500 | 95233 | 95233 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake Slack Adjuster Front | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 4 | 90009306 | 1 | 1000072224 | 07.06.2029 | 18000 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACF | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACF90009306
789D | Onsite Shut | Haul | Fortescue | DT166 | DT166 Repl Brake Slack Adjuster Rear | 2029-02-23 | 2029-03-16 | 21 days | FY29 | 4 | 90009307 | 1 | 1000072262 | 07.06.2029 | 18000 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACR | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACR90009307
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 - Onsite Shut (EOL - 10/2028) | 2029-02-28 | 2029-03-21 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 1Y Air Tank LH External Inspect | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389334 | 03.02.2029 | 12 Monthly | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH | 7500 | 93147 | 93147 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 1Y Air Tank RH External Inspect | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389336 | 03.02.2029 | 12 Monthly | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH | 7500 | 93147 | 93147 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Pump Drive Driveshaft Unis | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034436 | 26.02.2029 | 11000 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR-DRSHT | 7500 | 93408 | 12173 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Radiator Engine Cooling | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 85 | 90003081 | 1 | 1000034431 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-RADTR | 7400 | 93410 | 25282 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Fuel Tank Mounts | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078467 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -ENGINE-FUSYS-FULTK | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Engine Pump Drive | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 62 | 90003089 | 1 | 1000034433 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Pump Transmission | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 7 | 90003096 | 1 | 1000034437 | 28.02.2029 | 11000 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TMCPP | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Differential | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 66 | 90003098 | 1 | 1000034439 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-DIFFL | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -FDRSYS-DIFFL90003098
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Final Drive LH | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 56 | 90003099 | 1 | 1000034440 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-FDRVE-FDRLH | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Final Drive RH | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 56 | 90003100 | 1 | 1000034441 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-FDRVE-FDRRH | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Overhaul Accumulator Brake | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072189 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BACCM | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Pump Brake Control | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 5 | 90003106 | 1 | 1000034448 | 28.02.2029 | 11000 | CLB-MP-HAUL-DT169 -BRKSYS-HYFPP | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Valve Brake | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034449 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRVLV | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Rotochamber Front | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072379 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTFR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Rotochamber LHR | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072417 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTLR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Rotochamber RHR | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072455 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTRR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Ovhl Accumulator Hyd Steer Front | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072075 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCF | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Ovhl Accumulator Hyd Steer Middle | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072113 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCM | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Ovhl Accumulator Hyd Steering Rear | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072151 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCR | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Pump Hoist & Brake | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 10 | 90003113 | 1 | 1000034456 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -HYDSYS-HOPMP | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -HYDSYS-HOPMP90003113
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Air Dryer | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 14 | 90003115 | 1 | 1000034459 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -PNEUMC-AIRDR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Ovhl Axle A Frame | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130641 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-AFRME | 7500 | 93409 | 37178 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Ovhl Axle Housing Dogbone | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034462 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-TAGLK | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Brake Wheel RH | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 61 | 90003105 | 2 | 1000034446 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-AXLES-HUBRH | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Cyl Suspension LHF | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067782 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYLF | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Cyl Suspension RHF | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067784 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYRF | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Cyl Suspension LHR | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034467 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYLR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Cyl Suspension RHR | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034468 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYRR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Transmission System Hoses | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078452 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -TRNSYS-TRANS-TRNHO | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Torque Conv System Hoses | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078453 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -TRNSYS-TRQUE-TRQHO | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Brake Relay Valve | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078458 | 28.02.2029 | 11000 | CLB-MP-HAUL-DT169 -BRKSYS-BRVRL | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Brake Oil Cooler Front | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080260 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BROCO-BROCF | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Brake System Hoses Rear | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078459 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRHOR | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Brake System Hoses Front | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078460 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRHOF | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Brake System Air Lines | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078461 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRAIR | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Steering System Hoses | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078463 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -STRSYS-STHLF-STRHO | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Hoist System Hoses | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078457 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-HSTHO | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Differential System Hoses | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078454 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-DIFFL-DIFHO | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Fast Fill & SOS Hose | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103964 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-FFSOS | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Ladder Hoses | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104022 | 28.02.2029 | 22000 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-LADHO | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Service Suspension Cylinders | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106878 | 08.03.2029 | 11000 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN | 7500 | 93410 | 23335 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Cyl Steering RH | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 28 | 90003111 | 3 | 1000034454 | 31.03.2029 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYR | 7500 | 93410 | 10097 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYR90003111
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Tyre Sense Battery | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163944 | 01.04.2029 | 24 Monthly | CLB-MP-HAUL-DT169 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT169 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Steering HMU | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 14 | 90003110 | 1 | 1000034452 | 01.05.2029 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STHMU | 7500 | 93410 | 9365 | CLB-MP-HAUL-DT169 -STRSYS-STHMU90003110
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Cyl Steering LH | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 28 | 90003111 | 2 | 1000034453 | 01.05.2029 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYL | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT169 | DT169 Repl Hyd Pump Steering Main | 2029-02-28 | 2029-03-21 | 21 days | FY29 | 8 | 90003109 | 1 | 1000034451 | 05.05.2029 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STPMP | 7500 | 93410 | 9339 | CLB-MP-HAUL-DT169 -STRSYS-STPMP90003109
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 - Onsite Shut (EOL - 11/2028) | 2029-04-18 | 2029-05-09 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Final Drive RH | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 56 | 90003100 | 1 | 1000036171 | 26.03.2029 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-FDRVE-FDRRH | 7500 | 92548 | 2191 | CLB-MP-HAUL-DT200 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Valve Steering & AHS EH | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 10 | 90009881 | 1 | 1000078899 | 18.04.2029 | 22000 | CLB-MP-HAUL-DT200 -STRSYS-STVLV | 7500 | 92548 | 1651 | CLB-MP-HAUL-DT200 -STRSYS-STVLV90009881
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Engine Cat 3516B | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 142 | 90017315 | 1 | 1000157053 | 28.04.2029 | 22000 | CLB-MP-HAUL-DT200 -ENGINE | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Drive Shaft Transmission | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 16 | 90017134 | 1 | 1000154441 | 28.04.2029 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-DRSHT | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -FDRSYS-DRSHT90017134
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 1Y Air Tank LH External Inspect | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389454 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH | 7500 | 92315 | 50047 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 1Y Air Tank RH External Inspect | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389456 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH | 7500 | 92315 | 50047 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Fuel Tank Mounts | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078904 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -ENGINE-FUSYS-FULTK | 7500 | 92548 | 23460 | CLB-MP-HAUL-DT200 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Pump Drive Driveshaft Unis | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 4 | 90009874 | 1 | 1000036166 | 31.05.2029 | 11000 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR-DRSHT | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Torque Converter | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 62 | 90003092 | 1 | 1000036164 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -TRNSYS-TRQUE | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Transmission | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 48 | 90003093 | 1 | 1000036165 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -TRNSYS-TRANS | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Pump Transmission | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 7 | 90003096 | 1 | 1000036167 | 31.05.2029 | 11000 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TMCPP | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Transmission Oil Cooler | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 13 | 90003532 | 1 | 1000041009 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -TRNSYS-TROLC | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Final Drive LH | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 56 | 90003099 | 1 | 1000036170 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-FDRVE-FDRLH | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Hyd Motor Axle Lube Rear | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 9 | 90003101 | 1 | 1000036172 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-HYM01 | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Overhaul Accumulator Brake | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072220 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BACCM | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Pump Brake Control | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 5 | 90003106 | 1 | 1000036178 | 31.05.2029 | 11000 | CLB-MP-HAUL-DT200 -BRKSYS-HYFPP | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Valve Brake | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 18 | 90003107 | 1 | 1000036179 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRVLV | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Rotochamber Front | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072410 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTFR | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Rotochamber LHR | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072448 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTLR | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Ovhl Accumulator Hyd Steer Front | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072106 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCF | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Ovhl Accumulator Hyd Steer Middle | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072144 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCM | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Ovhl Axle Housing Dogbone | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 42 | 90003118 | 1 | 1000036192 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-TAGLK | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Brake Wheel LH | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 38 | 90003104 | 2 | 1000036175 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-AXLES-HUBLH | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Service Suspension Cylinders | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106949 | 31.05.2029 | 11000 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Cyl Suspension RHR | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 42 | 90003122 | 1 | 1000036198 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYRR | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Transmission System Hoses | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078889 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -TRNSYS-TRANS-TRNHO | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Torque Conv System Hoses | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078890 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -TRNSYS-TRQUE-TRQHO | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Brake Relay Valve | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078895 | 31.05.2029 | 11000 | CLB-MP-HAUL-DT200 -BRKSYS-BRVRL | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Brake Oil Cooler Front | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080304 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BROCO-BROCF | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Brake System Hoses Rear | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078896 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRHOR | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Hoist System Hoses | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078894 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-HSTHO | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Differential System Hoses | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078891 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-DIFFL-DIFHO | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Fast Fill & SOS Hose | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103995 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-FFSOS | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Ladder Hoses | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104053 | 31.05.2029 | 22000 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-LADHO | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Ovhl Accumulator Hyd Steering Rear | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072182 | 01.06.2029 | 22000 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCR | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Brake System Hoses Front | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078897 | 01.06.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRHOF | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Brake System Air Lines | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078898 | 01.06.2029 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRAIR | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Steering System Hoses | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078900 | 01.06.2029 | 22000 | CLB-MP-HAUL-DT200 -STRSYS-STHLF-STRHO | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT200 | DT200 Repl Tyre Sense Battery | 2029-04-18 | 2029-05-09 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163975 | 11.06.2029 | 24 Monthly | CLB-MP-HAUL-DT200 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT200 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 - Onsite Shut (EOL - 04/2029) | 2029-05-01 | 2029-05-22 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Engine Cat 3516B | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156733 | 27.04.2029 | 22000 | CLB-MP-HAUL-DT180 -ENGINE | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Spiders Transmission Driveshaft | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 8 | 90017135 | 1 | 1000154402 | 27.04.2029 | 11000 | CLB-MP-HAUL-DT180 -FDRSYS-DRSHT-UNVSL | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Fuel Tank Mounts | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078638 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -ENGINE-FUSYS-FULTK | 7500 | 89560 | 23548 | CLB-MP-HAUL-DT180 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Engine Pump Drive | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 62 | 90003089 | 1 | 1000035041 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Pump Drive Driveshaft Unis | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 4 | 90009874 | 1 | 1000035044 | 01.05.2029 | 11000 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR-DRSHT | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Torque Converter | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 62 | 90003092 | 1 | 1000035042 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -TRNSYS-TRQUE | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Final Drive LH | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 56 | 90003099 | 1 | 1000035048 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -FDRSYS-FDRVE-FDRLH | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Final Drive RH | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 56 | 90003100 | 1 | 1000035049 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -FDRSYS-FDRVE-FDRRH | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Hyd Motor Axle Lube Rear | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 9 | 90003101 | 1 | 1000035050 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-HYM01 | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Overhaul Accumulator Brake | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072200 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BACCM | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Pump Brake Control | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 5 | 90003106 | 1 | 1000035056 | 01.05.2029 | 11000 | CLB-MP-HAUL-DT180 -BRKSYS-HYFPP | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-HYFPP90003106
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Valve Brake | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 18 | 90003107 | 1 | 1000035057 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRVLV | 7500 | 89519 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Rotochamber Front | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072390 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTFR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Rotochamber LHR | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072428 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTLR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Rotochamber RHR | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072466 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTRR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Ovhl Accumulator Hyd Steer Front | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072086 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCF | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Ovhl Accumulator Hyd Steer Middle | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072124 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCM | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Ovhl Accumulator Hyd Steering Rear | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072162 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Air Dryer | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 14 | 90003115 | 1 | 1000366599 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -PNEUMC-AIRDR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Ovhl Axle A Frame | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130651 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-AFRME | 7500 | 89560 | 23548 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Ovhl Axle Housing Dogbone | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 42 | 90003118 | 1 | 1000035070 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-TAGLK | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake Wheel LH | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 38 | 90003104 | 2 | 1000035053 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-AXLES-HUBLH | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRUCT-AXLES-HUBLH90003104
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake Wheel RH | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 61 | 90003105 | 2 | 1000035054 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-AXLES-HUBRH | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Cyl Suspension RHF | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 66 | 90003121 | 1 | 1000067828 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYRF | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Cyl Suspension LHR | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 42 | 90003122 | 1 | 1000035075 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYLR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Cyl Suspension RHR | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 42 | 90003122 | 1 | 1000035076 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYRR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Transmission System Hoses | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078623 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -TRNSYS-TRANS-TRNHO | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Torque Conv System Hoses | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078624 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -TRNSYS-TRQUE-TRQHO | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake Relay Valve | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078629 | 01.05.2029 | 11000 | CLB-MP-HAUL-DT180 -BRKSYS-BRVRL | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake Oil Cooler Front | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080272 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BROCO-BROCF | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake System Hoses Rear | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078630 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRHOR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake System Hoses Front | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078631 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRHOF | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Brake System Air Lines | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078632 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRAIR | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Steering System Hoses | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078634 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -STRSYS-STHLF-STRHO | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Hoist System Hoses | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078628 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-HSTHO | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Differential System Hoses | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078625 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -FDRSYS-DIFFL-DIFHO | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Fast Fill & SOS Hose | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103975 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-FFSOS | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Ladder Hoses | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104033 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-LADHO | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Tyre Sense Battery | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163955 | 03.06.2029 | 24 Monthly | CLB-MP-HAUL-DT180 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT180 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Radiator Engine Cooling | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 85 | 90003081 | 1 | 1000035039 | 07.06.2029 | 22000 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-RADTR | 7400 | 89560 | 23548 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 1Y Air Tank LH External Inspect | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389378 | 13.06.2029 | 12 Monthly | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH | 7500 | 89376 | 46929 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 1Y Air Tank RH External Inspect | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 1.5 | 90038753 | A1 | 1000389380 | 13.06.2029 | 12 Monthly | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH | 7500 | 89376 | 46929 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite Shut | Haul | Fortescue | DT180 | DT180 Repl Cyl Steering LH | 2029-05-01 | 2029-05-22 | 21 days | FY29 | 28 | 90003111 | 2 | 1000035061 | 27.07.2029 | 15000 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYL | 7500 | 89560 | 7664 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYL90003111
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 - Onsite Shut (EOL - 11/2028) | 2029-06-13 | 2029-07-04 | 21 days | FY29
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Tyre Sense Battery | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 2 | 90017022 | 1 | 1000163947 | 28.05.2029 | 24 Monthly | CLB-MP-HAUL-DT172 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT172 -MANGMT-TYRSN90017022
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Service Suspension Cylinders | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 27 | 90012840 | 1 | 1000106881 | 10.06.2029 | 11000 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN | 7500 | 92351 | 22391 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN90012840
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Engine Cat 3516B | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 142 | 90017315 | 1 | 1000156605 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -ENGINE | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE90017315
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Fuel Tank Mounts | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 16 | 90009887 | 1 | 1000078524 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -ENGINE-FUSYS-FULTK | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -ENGINE-FUSYS-FULTK90009887
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Ovhl Accumulator Hyd Steer Front | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072078 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCF | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCF90009314
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Ovhl Accumulator Hyd Steer Middle | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072116 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCM | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCM90009314
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Ovhl Accumulator Hyd Steering Rear | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 7 | 90009314 | 1 | 1000072154 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCR | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCR90009314
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Brake Wheel RH | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 61 | 90003105 | 2 | 1000034613 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-AXLES-HUBRH | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -STRUCT-AXLES-HUBRH90003105
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Cyl Suspension RHR | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 42 | 90003122 | 1 | 1000034635 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYRR | 7500 | 92351 | 400 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Transmission System Hoses | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 8 | 90009871 | 1 | 1000078509 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -TRNSYS-TRANS-TRNHO | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -TRNSYS-TRANS-TRNHO90009871
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Torque Conv System Hoses | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 4 | 90009872 | 1 | 1000078510 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -TRNSYS-TRQUE-TRQHO | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -TRNSYS-TRQUE-TRQHO90009872
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Brake System Hoses Rear | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 6 | 90009878 | 1 | 1000078516 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRHOR | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRHOR90009878
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Brake System Hoses Front | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 12 | 90009879 | 1 | 1000078517 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRHOF | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRHOF90009879
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Brake System Air Lines | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 24 | 90009880 | 1 | 1000078518 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRAIR | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRAIR90009880
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Steering System Hoses | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 24 | 90009882 | 1 | 1000078520 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRSYS-STHLF-STRHO | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRSYS-STHLF-STRHO90009882
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Fast Fill & SOS Hose | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 36 | 90012188 | 1 | 1000103967 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-FFSOS | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-FFSOS90012188
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Ladder Hoses | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 4 | 90012189 | 1 | 1000104025 | 13.06.2029 | 22000 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-LADHO | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-LADHO90012189
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Radiator Engine Cooling | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 85 | 90003081 | 1 | 1000034598 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-RADTR | 7400 | 92350 | 68444 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-RADTR90003081
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Engine Pump Drive | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 62 | 90003089 | 1 | 1000034600 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR90003089
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Pump Drive Driveshaft Unis | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 4 | 90009874 | 1 | 1000034603 | 21.06.2029 | 11000 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR-DRSHT | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Torque Converter | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 62 | 90003092 | 1 | 1000034601 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -TRNSYS-TRQUE | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -TRNSYS-TRQUE90003092
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Transmission | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 48 | 90003093 | 1 | 1000034602 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -TRNSYS-TRANS | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -TRNSYS-TRANS90003093
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Pump Transmission | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 7 | 90003096 | 1 | 1000034604 | 21.06.2029 | 11000 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TMCPP | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Transmission Oil Cooler | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 13 | 90003532 | 1 | 1000040981 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -TRNSYS-TROLC | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -TRNSYS-TROLC90003532
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Final Drive LH | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 56 | 90003099 | 1 | 1000034607 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -FDRSYS-FDRVE-FDRLH | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Final Drive RH | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 56 | 90003100 | 1 | 1000034608 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -FDRSYS-FDRVE-FDRRH | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Hyd Motor Axle Lube Rear | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 9 | 90003101 | 1 | 1000034609 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-HYM01 | 7500 | 92330 | 244 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Overhaul Accumulator Brake | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 10 | 90009313 | 1 | 1000072192 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BACCM | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BACCM90009313
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Valve Brake | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 18 | 90003107 | 1 | 1000034616 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRVLV | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BRVLV90003107
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Rotochamber Front | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 5 | 90009308 | 1 | 1000072382 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTFR | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Rotochamber LHR | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072420 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTLR | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Rotochamber RHR | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 5 | 90009309 | 1 | 1000072458 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTRR | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Air Dryer | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 14 | 90003115 | 1 | 1000366598 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -PNEUMC-AIRDR | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -PNEUMC-AIRDR90003115
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Ovhl Axle A Frame | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 60 | 90015390 | 1 | 1000130644 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-AFRME | 7500 | 92350 | 22401 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-AFRME90015390
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Ovhl Axle Housing Dogbone | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 42 | 90003118 | 1 | 1000034629 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-TAGLK | 7500 | 92350 | 244 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-TAGLK90003118
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Brake Relay Valve | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 6 | 90009877 | 1 | 1000078515 | 21.06.2029 | 11000 | CLB-MP-HAUL-DT172 -BRKSYS-BRVRL | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BRVRL90009877
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Brake Oil Cooler Front | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 5 | 90003108 | 1 | 1000080263 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -BRKSYS-BROCO-BROCF | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BROCO-BROCF90003108
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Hoist System Hoses | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 12 | 90009903 | 1 | 1000078514 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-HSTHO | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-HSTHO90009903
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Differential System Hoses | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 2 | 90009873 | 1 | 1000078511 | 21.06.2029 | 22000 | CLB-MP-HAUL-DT172 -FDRSYS-DIFFL-DIFHO | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -FDRSYS-DIFFL-DIFHO90009873
789D | Onsite Shut | Haul | Fortescue | DT172 | DT172 Repl Steering Ball Studs | 2029-06-13 | 2029-07-04 | 21 days | FY29 | 35 | 90038356 | A1 | 1000385416 | 01.08.2029 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STLTR | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRSYS-STLTR90038356
| Onsite PM | Ancillary | Fortescue |  | ANCILLARY - COMPONENTS DURING PM
| Onsite PM | Ancillary | Fortescue |  | FY27 - ANCILLARY - COMPONENTS DURING PM | 2026-07-01 |  |  | FY27
| Onsite PM | Ancillary | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-07-01 | 365 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Air Tank Replacement | 2026-07-01 | 2026-07-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Bucket Refurb | 2026-07-01 | 2026-07-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Blade Rebuild | 2026-07-01 | 2026-07-31 | 30 days | FY27
854K | Onsite PM | Ancillary | Fortescue | All - 854K | 854K Blade refurb | 2026-07-01 | 2026-07-31 | 30 days | FY27
16M | Onsite PM | Ancillary | Fortescue | All - Ancillary | Rotable Front Axle | 2026-07-01 | 2026-07-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | GR018 | 24M Blade Refurb | 2026-07-01 | 2026-07-31 | 30 days | FY27
24M | Onsite PM | Ancillary | Fortescue | GR021 | 24M Blade Refurb | 2026-07-01 | 2026-07-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10 Blade Refurbishment | 2026-07-01 | 2026-07-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Draft arm Rebuild | 2026-08-01 | 2026-08-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Fuel Tank Replacement | 2026-08-01 | 2026-08-31 | 30 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | D10T Ripper Shank | 2026-08-01 | 2026-08-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Ripper Box Overhaul | 2026-09-01 | 2026-09-30 | 29 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Ripper Shank | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Ancillary | Onsite PM | Ancillary | Fortescue | All - Ancillary | D10T/D11 Rated Recovery Points | 2026-09-01 | 2026-09-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10 Track Frame Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Track Frame Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Ancillary | Onsite PM | Ancillary | Fortescue | All - Ancillary | D10T/D11 Rated Recovery Points | 2026-11-01 | 2026-11-30 | 29 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Blade Refurb | 2026-11-01 | 2026-11-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic Overhaul | 2026-12-01 | 2026-12-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic Rebuild | 2026-12-01 | 2026-12-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Ripper Box Overhaul | 2026-12-01 | 2026-12-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10 Blade Refurbishment | 2026-12-01 | 2026-12-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
18 | Onsite PM | Ancillary | Fortescue | All - 18 | Rotable Front Axle | 2027-01-01 | 2027-01-31 | 30 days | FY27
18 | Onsite PM | Ancillary | Fortescue | All - 18 | 18M Artic Refurb | 2027-01-01 | 2027-01-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994 Rear Diff Housing Repairs | 2027-01-01 | 2027-01-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Radiator Upgrade to Mesabi Cooling | 2027-01-01 | 2027-01-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Ripper Shank | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Ancillary | Onsite PM | Ancillary | Fortescue | All - Ancillary | D10T/D11 Rated Recovery Points | 2027-01-01 | 2027-01-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994 Hydraulic Tank Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10 Track Frame Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Bucket Refurb | 2027-02-01 | 2027-02-28 | 27 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Blade Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Fuel Tank Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Ripper Box Overhaul | 2027-03-01 | 2027-03-31 | 30 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Ripper Shank | 2027-03-01 | 2027-03-31 | 30 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Track Frame Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Safe Board Ladder Replace | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Ancillary | Onsite PM | Ancillary | Fortescue | All - Ancillary | D10T/D11 Rated Recovery Points | 2027-03-01 | 2027-03-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic Overhaul | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Artic Rebuild | 2027-04-01 | 2027-04-30 | 29 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Boom Overhaul | 2027-04-01 | 2027-04-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
994H | Onsite PM | Ancillary | Fortescue | All - 994H | 994H Radiator Upgrade to Mesabi Cooling | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10 Track Frame Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10 Blade Refurbishment | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Blade Rebuild | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Draft Arm Rebuild | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Ancillary | Onsite PM | Ancillary | Fortescue | All - Ancillary | D10T/D11 Rated Recovery Points | 2027-05-01 | 2027-05-31 | 30 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Blade Refurb | 2027-05-01 | 2027-05-31 | 30 days | FY27
D11T | Onsite PM | Ancillary | Fortescue | All - Ancillary | D11 Draft Arm Rebuild | 2027-05-01 | 2027-05-31 | 30 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Ancillary | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
18 | Onsite PM | Ancillary | Fortescue | All - 18 | 18M Complete Circle/Drawbar/C Bracket Assy | 2027-06-01 | 2027-06-30 | 29 days | FY27
994K | Onsite PM | Ancillary | Fortescue | All - 994K | 994K Artic Rebuild | 2027-06-01 | 2027-06-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Ripper Box Overhaul | 2027-06-01 | 2027-06-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | D10T Ripper Shank | 2027-06-01 | 2027-06-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | All - D10T | MSR Strategy-Repl D10T Cylinders (All) | 2027-06-01 | 2027-06-30 | 29 days | FY27
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Final Drive RH | 2026-07-30 | 2026-07-30 | 14 hrs | FY27 | 28 | 90000312 | 1 | 1000018438 | 20.07.2028 | 18000 | CLB-MP-DOZR-DZ013 -FDRSYS-FDRRH | 4700 | 72325 | 8866 | CLB-MP-DOZR-DZ013 -FDRSYS-FDRRH90000312
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Trans Pump Drive Coupling Replace | 2026-07-31 | 2026-07-31 | 10 hrs | FY27 | 10 | 90037705 | A1 | 1000374083 | 09.05.2026 | 7000 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP90037705
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Hyd Pump Cooling Fan | 2026-07-31 | 2026-07-31 | 10 hrs | FY27 | 10 | 90009272 | 1 | 1000071476 | 11.05.2026 | 7000 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP90009272
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Fan Cooling Motor Hyd | 2026-07-31 | 2026-07-31 | 8 hrs | FY27 | 16 | 90003352 | 1 | 1000037933 | 11.05.2026 | 7000 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM90003352
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Service Minor Air Conditioner | 2026-08-01 | 2026-08-01 | 12 hrs | FY27 | 12 | 90019542 | 1 | 1000200120 | 30.06.2026 | 3500 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN90019542
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Adjust 250hr Initial Valve Set | 2026-08-05 | 2026-08-05 | 6 hrs | FY27 | 12 | 90015780 | 1 | 1000159910 | 17.06.2026 | 250 | CLB-MP-GRDR-GR021 -ENGINE | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE90015780
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Adjust 250hr Initial Valve Set | 2026-08-10 | 2026-08-10 | 6 hrs | FY27 | 12 | 90015780 | 1 | 1000159884 | 16.07.2026 | 250 | CLB-MP-GRDR-GR018 -ENGINE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE90015780
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Cyl Lift LH | 2026-08-16 | 2026-08-17 | 30 hrs | FY27 | 60 | 90021484 | A1 | 1000207963 | 17.08.2026 | 10000 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLL | 5000 | 21377 | 9901 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLL90021484
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Cyl Lift RH | 2026-08-16 | 2026-08-17 | 30 hrs | FY27 | 60 | 90021485 | A1 | 1000207964 | 17.08.2026 | 10000 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLR | 5000 | 21377 | 9901 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLR90021485
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Air Conditioner Service | 2026-08-16 | 2026-08-17 | 24 hrs | FY27 | 24 | 90017478 | A1 | 1000207979 | 28.10.2025 | 4000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN90017478
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Auto Lube Pump | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90019389 | A1 | 1000274140 | 03.06.2026 | 14000 | CLB-MP-GRDR-GR6503-GRSYST-ALBPP | 5500 | 19846 | 14857 | CLB-MP-GRDR-GR6503-GRSYST-ALBPP90019389
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Pump Brake | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 6 | 90002957 | A1 | 1000033475 | 04.02.2028 | 15000 | CLB-MP-DOZR-WD004 -BRKSYS-BRPMP | 5900 | 72896 | 6131 | CLB-MP-DOZR-WD004 -BRKSYS-BRPMP90002957
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Pump Steering Main | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 8 | 90002958 | A1 | 1000033476 | 10.03.2028 | 15000 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP01 | 5900 | 72896 | 5612 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP0190002958
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Repl Cylinder Blade Lift LH | 2026-08-17 | 2026-08-17 | 8 hrs | FY27 | 14 | 90018821 | A1 | 1000189191 | 10.08.2026 | 9000 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYL | 4800 | 26987 | 8732 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYL90018821
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Repl Operators Seat | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90018835 | A1 | 1000189168 | 22.07.2026 | 6000 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS | 4800 | 26987 | 6075 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS90018835
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Final Drive RH | 2026-08-17 | 2026-08-17 | 14 hrs | FY27 | 28 | 90000312 | 1 | 1000020587 | 24.09.2027 | 18000 | CLB-MP-DOZR-DZ018 -FDRSYS-FDRRH | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -FDRSYS-FDRRH90000312
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Replace Operators Seat | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90000318 | 1 | 1000089363 | 23.07.2026 | 6000 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS | 4700 | 66933 | 5461 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS90000318
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Equaliser Bar | 2026-08-18 | 2026-08-20 | 48 hrs | FY27 | 96 | 90010849 | 1 | 1000089519 | 10.01.2026 | 14000 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-EQUAL | 5000 | 65875 | 16847 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-EQUAL90010849
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Service Airconditioner | 2026-08-19 | 2026-08-20 | 24 hrs | FY27 | 24 | 90003915 | 2 | 1000195982 | 30.03.2026 | 5500 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN90003915
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Engine Midlife Complete | 2026-08-24 | 2026-08-26 | 53 hrs | FY27 | 61 | 90018853 | A1 | 1000202358 | 03.06.2026 | 9000 | CLB-MP-DOZR-DZ8225-ENGINE | 4800 | 24542 | 9431 | CLB-MP-DOZR-DZ8225-ENGINE90018853
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Radiator Engine Cooling | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 48 | 90018824 | A1 | 1000202305 | 19.05.2028 | 18000 | CLB-MP-DOZR-DZ8225-ENGINE-COSYS-RADTR | 4800 | 24542 | 9431 | CLB-MP-DOZR-DZ8225-ENGINE-COSYS-RADTR90018824
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Wash Engine Pre Cleaners | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 2 | 90018848 | A1 | 1000202353 | 03.06.2026 | 9000 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AIRFL90018848
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Service Major Air Conditioner | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 24 | 90018855 | A1 | 1000202359 | 03.06.2026 | 9000 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN90018855
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Drive Shaft Unis | 2026-08-24 | 2026-08-24 | 3 hrs | FY27 | 6 | 90033312 | A1 | 1000334039 | 20.06.2026 | 9000 | CLB-MP-DOZR-DZ8225-TRNSYS-DRSHT | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-TRNSYS-DRSHT90033312
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Air Conditioner Minor Service | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 12 | 90019351 | 1 | 1000269638 | 10.04.2026 | 3500 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN90019351
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Trans Pump Drive Coupling Replace | 2026-08-24 | 2026-08-24 | 10 hrs | FY27 | 10 | 90037705 | A1 | 1000374085 | 15.04.2026 | 7000 | CLB-MP-DOZR-DZX022-TRNSYS-TRPMP | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-TRNSYS-TRPMP90037705
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Fan Cooling Motor Hyd | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 16 | 90003352 | 1 | 1000037959 | 01.04.2026 | 7000 | CLB-MP-DOZR-DZX022-HYDSYS-HDCFM | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-HYDSYS-HDCFM90003352
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Service Airconditroner Major | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 24 | 90029040 | A1 | 1000290164 | 01.04.2026 | 7000 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-AIRCN | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-AIRCN90029040
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Hyd Pump Brake | 2026-08-30 | 2026-08-30 | 12 hrs | FY27 | 12 | 90002712 | A1 | 1000029077 | 17.10.2027 | 20000 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP01 | 6000 | 78554 | 12877 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP0190002712
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Operators Seat | 2026-08-30 | 2026-08-30 | 4 hrs | FY27 | 4 | 90002741 | A1 | 1000029102 | 17.08.2026 | 7000 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS | 6000 | 78554 | 6878 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS90002741
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Replace Brake System Hoses | 2026-08-31 | 2026-09-01 | 24 hrs | FY27 | 48 | 90013050 | 1 | 1000179080 | 14.06.2026 | 15000 | CLB-MP-DOZR-WD6105-BRKSYS-BRHLF | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-BRKSYS-BRHLF90013050
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Rear Differential | 2026-08-31 | 2026-09-02 | 62 hrs | FY27 | 122 | 90002952 | A1 | 1000179054 | 28.08.2026 | 15000 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF | 5900 | 55835 | 14684 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF90002952
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Overhaul Axle Oscillation Rear | 2026-08-31 | 2026-09-02 | 60 hrs | FY27 | 120 | 90002953 | A1 | 1000179055 | 30.08.2026 | 15000 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF-TRNON | 5900 | 55835 | 14684 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF-TRNON90002953
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Hyd Motor Fan | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 24 | 90002969 | A1 | 1000179071 | 14.06.2026 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM01 | 5900 | 55835 | 16081 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM0190002969
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Hoses Steering System | 2026-08-31 | 2026-09-01 | 24 hrs | FY27 | 48 | 90013051 | 1 | 1000179081 | 14.06.2026 | 15000 | CLB-MP-DOZR-WD6105-STRSYS-STHLF | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-STRSYS-STHLF90013051
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Replace Hyd Pilot System Hoses | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 24 | 90013052 | 1 | 1000231946 | 14.06.2026 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHPS | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHPS90013052
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Hoses Main Hyd-Fan System | 2026-08-31 | 2026-09-01 | 24 hrs | FY27 | 48 | 90013053 | 1 | 1000231947 | 14.06.2026 | 15000 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHMH | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHMH90013053
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Trunnions RrAxle Oscillation | 2026-08-31 | 2026-09-02 | 60 hrs | FY27 | 120 | 90021474 | A1 | 1000208020 | 28.04.2026 | 20000 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF-TRNON | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF-TRNON90021474
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Operators Seat | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90018835 | A1 | 1000189070 | 25.08.2026 | 6000 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS | 4800 | 25244 | 5824 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS90018835
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Minor Service Air Conditioner | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 6 | 90017699 | 1 | 1000162402 | 12.09.2026 | 4500 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN90017699
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Minor Service Air Conditioner | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 6 | 90017699 | 1 | 1000162399 | 16.09.2026 | 4500 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Bucket LH High Lift | 2026-08-31 | 2026-09-01 | 18 hrs | FY27 | 36 | 90017978 | A1 | 1000029160 | 23.05.2026 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYL | 6000 | 81297 | 11532 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYL90017978
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Lift LH High Lift | 2026-08-31 | 2026-09-01 | 20 hrs | FY27 | 40 | 90002727 | A1 | 1000029158 | 14.08.2026 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLL | 6000 | 81297 | 10089 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLL90002727
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Rear Output Drive Shaft Unis | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90033167 | A1 | 1000333602 | 29.08.2026 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT02 | 6000 | 81297 | 9807 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0290033167
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Rear Differential | 2026-08-31 | 2026-09-02 | 50 hrs | FY27 | 98 | 90002708 | A1 | 1000029136 | 25.07.2026 | 20000 | CLB-MP-LOAD-WL027 -FDRSYS-RRDIF | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -FDRSYS-RRDIF90002708
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Overhaul Rear Axle Trunnion | 2026-08-31 | 2026-09-02 | 48 hrs | FY27 | 96 | 90002709 | A1 | 1000029137 | 24.07.2026 | 20000 | CLB-MP-LOAD-WL027 -FDRSYS-RRDIF-TRNON | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -FDRSYS-RRDIF-TRNON90002709
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Final Drive Position 3 | 2026-08-31 | 2026-09-02 | 44 hrs | FY27 | 83 | 90002710 | A1 | 1000029140 | 13.03.2026 | 16000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR03 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR0390002710
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Final Drive Position 4 | 2026-08-31 | 2026-09-02 | 44 hrs | FY27 | 83 | 90002710 | A1 | 1000029141 | 15.12.2025 | 16000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR04 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR0490002710
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Axle Shaft Position 4 | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 12 | 90012242 | 1 | 1000101241 | 23.07.2028 | 32000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP4 | 6000 | 81297 | 20362 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP490012242
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Axle Shaft Position 3 | 2026-08-31 | 2026-08-31 | 6 hrs | FY27 | 12 | 90012242 | 1 | 1000101240 | 27.05.2029 | 32000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP3 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP390012242
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Radiator Engine Cooling | 2026-09-04 | 2026-09-05 | 30 hrs | FY27 | 54 | 90002682 | A1 | 1000028988 | 27.08.2026 | 20000 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-RADTR | 5700 | 64643 | 44220 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-RADTR90002682
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Centre Output Drive Shaft | 2026-09-04 | 2026-09-04 | 7 hrs | FY27 | 14 | 90033171 | A1 | 1000333579 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT03 | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0390033171
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Implement LH | 2026-09-04 | 2026-09-04 | 12 hrs | FY27 | 24 | 90002723 | A1 | 1000029024 | 13.08.2026 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP01 | 6000 | 64740 | 9769 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Replace Artic Area Hyd Hosing | 2026-09-04 | 2026-09-04 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220519 | 13.10.2026 | 8 Monthly | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO90020831
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Transmission Oil Cooler | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 6 | 90002945 | A2 | 1000189983 | 11.09.2026 | 15000 | CLB-MP-DOZR-WD6106-TRNSYS-TROLC | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-TRNSYS-TROLC90002945
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Pump Transmission | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90002946 | A2 | 1000189984 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-TRNSYS-TRPMP | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-TRNSYS-TRPMP90002946
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Shaft TConverter to Trans | 2026-09-07 | 2026-09-07 | 2 hrs | FY27 | 4 | 90002947 | A2 | 1000268510 | 10.09.2026 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT01 | 5900 | 30649 | 10308 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0190002947
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Shaft Trans to Rear Diff | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90002948 | A2 | 1000268512 | 10.09.2026 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT02 | 5900 | 30649 | 10308 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0290002948
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Shaft Centre Brg to Fr Diff | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90002950 | A2 | 1000268516 | 19.08.2026 | 22000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT04 | 5900 | 30649 | 10308 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0490002950
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Pump Brake | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 4 | 90002957 | A2 | 1000189998 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-BRKSYS-BRPMP | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-BRKSYS-BRPMP90002957
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Brake System Hoses | 2026-09-07 | 2026-09-08 | 24 hrs | FY27 | 48 | 90013050 | A2 | 1000190015 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-BRKSYS-BRHLF | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-BRKSYS-BRHLF90013050
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Steering Main | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 12 | 90002958 | A2 | 1000189999 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP01 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP0190002958
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Pump Str Pilot & Str Cooling | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 4 | 90002959 | A2 | 1000190000 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP02 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP0290002959
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Steer Secondary | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 4 | 90002960 | A2 | 1000190001 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP03 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP0390002960
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hoses Steering System | 2026-09-07 | 2026-09-08 | 24 hrs | FY27 | 48 | 90013051 | A2 | 1000190016 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STHLF | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-STRSYS-STHLF90013051
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Implement | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 12 | 90002962 | A2 | 1000190004 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP01 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP0190002962
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Cooling Fan | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90002964 | A2 | 1000190006 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP03 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP0390002964
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Motor Fan | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90002969 | A2 | 1000190007 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM01 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM0190002969
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Hyd Pilot System Hoses | 2026-09-07 | 2026-09-07 | 12 hrs | FY27 | 24 | 90013052 | A2 | 1000190017 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHPS | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHPS90013052
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hoses Main Hyd-Fan System | 2026-09-07 | 2026-09-08 | 24 hrs | FY27 | 48 | 90013053 | A2 | 1000229426 | 10.09.2026 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHMH | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHMH90013053
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Repl Cylinder Blade Lift RH | 2026-09-14 | 2026-09-14 | 8 hrs | FY27 | 14 | 90031953 | A1 | 1000221495 | 16.09.2026 | 9000 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYR | 4800 | 18270 | 8046 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYR90031953
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Input Drive Shaft | 2026-09-21 | 2026-09-21 | 6 hrs | FY27 | 12 | 90033166 | A1 | 1000333587 | 17.09.2026 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT01 | 6000 | 78554 | 19377 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0190033166
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Rear Output Drive Shaft Unis | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90033167 | A1 | 1000333590 | 17.09.2026 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT02 | 6000 | 78554 | 9502 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0290033167
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Hyd Pump Brake Cooling | 2026-09-21 | 2026-09-21 | 8 hrs | FY27 | 8 | 90002713 | A1 | 1000029078 | 26.09.2026 | 10000 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP02 | 6000 | 78554 | 9173 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP0290002713
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Fr Pump Drv Shaft Unis | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 8 | 90033190 | A1 | 1000333610 | 12.06.2026 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT06 | 6000 | 81297 | 11142 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0690033190
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Brake Cooling | 2026-09-21 | 2026-09-21 | 8 hrs | FY27 | 8 | 90002713 | A1 | 1000029143 | 23.05.2026 | 10000 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP02 | 6000 | 81297 | 11532 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP0290002713
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Steering LH | 2026-09-21 | 2026-09-22 | 18 hrs | FY27 | 36 | 90002716 | A1 | 1000029147 | 10.10.2025 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP01 | 6000 | 81297 | 25586 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP0190002716
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Replace Artic Area Hyd Hosing | 2026-09-21 | 2026-09-21 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220521 | 02.05.2026 | 8 Monthly | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO90020831
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Steer Clutch & Brake Assm LH | 2026-09-21 | 2026-09-21 | 16 hrs | FY27 | 32 | 90003348 | 1 | 1000037954 | 22.01.2026 | 14000 | CLB-MP-DOZR-DZX022-BRKSTR-SCABL | 4400 | 63346 | 14380 | CLB-MP-DOZR-DZX022-BRKSTR-SCABL90003348
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Steer Clutch & Brake Assm RH | 2026-09-21 | 2026-09-21 | 16 hrs | FY27 | 32 | 90003348 | 1 | 1000037955 | 22.01.2026 | 14000 | CLB-MP-DOZR-DZX022-BRKSTR-SCABR | 4400 | 63346 | 14380 | CLB-MP-DOZR-DZX022-BRKSTR-SCABR90003348
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Input Drive Shaft | 2026-09-21 | 2026-09-21 | 6 hrs | FY27 | 12 | 90033166 | A1 | 1000333599 | 24.07.2026 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT01 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0190033166
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Centre Output Drive Shaft | 2026-09-21 | 2026-09-21 | 7 hrs | FY27 | 14 | 90033171 | A1 | 1000333603 | 24.07.2026 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT03 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0390033171
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Transmission | 2026-09-21 | 2026-09-22 | 38 hrs | FY27 | 74 | 90002692 | A1 | 1000029121 | 27.09.2026 | 16000 | CLB-MP-LOAD-WL027 -TRNSYS-TRANS | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-TRANS90002692
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Articulation Overhaul | 2026-09-21 | 2026-09-29 | 194 hrs | FY27 | 360 | 90032991 | A1 | 1000330000 | 27.09.2026 | 16000 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-ARTIC | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-ARTIC90032991
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Transmission Transfer Case | 2026-09-21 | 2026-09-22 | 38 hrs | FY27 | 74 | 90017029 | A1 | 1000153366 | 27.09.2026 | 16000 | CLB-MP-LOAD-WL027 -TRNSYS-TRTRF | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-TRTRF90017029
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Operators Seat | 2026-09-21 | 2026-09-21 | 4 hrs | FY27 | 4 | 90002741 | A1 | 1000029167 | 14.10.2026 | 7000 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS | 6000 | 81297 | 6005 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS90002741
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Steering RH | 2026-09-21 | 2026-09-21 | 10 hrs | FY27 | 20 | 90002722 | A1 | 1000029153 | 31.10.2026 | 12000 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYR | 6000 | 81297 | 10741 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYR90002722
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Implement RH | 2026-09-25 | 2026-09-25 | 12 hrs | FY27 | 24 | 90002724 | A1 | 1000079847 | 16.04.2026 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP02 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Implement Centre | 2026-09-25 | 2026-09-25 | 12 hrs | FY27 | 24 | 90002725 | A1 | 1000079848 | 16.04.2026 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP03 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0390002725
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Steering RH | 2026-09-25 | 2026-09-26 | 18 hrs | FY27 | 36 | 90002717 | A1 | 1000079841 | 10.08.2026 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP02 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP0290002717
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Steering RH | 2026-09-25 | 2026-09-25 | 10 hrs | FY27 | 20 | 90002722 | A1 | 1000079845 | 14.08.2026 | 12000 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYR | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYR90002722
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Input Shaft Unis | 2026-09-25 | 2026-09-25 | 4 hrs | FY27 | 8 | 90033167 | A1 | 1000333624 | 10.04.2026 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT01 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0190033167
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Operators Seat | 2026-09-28 | 2026-09-28 | 4 hrs | FY27 | 4 | 90002975 | A1 | 1000033494 | 30.09.2026 | 7000 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS | 5900 | 72896 | 6131 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS90002975
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8223 | DZ8223 Service Minor Air Conditioner | 2026-09-28 | 2026-09-28 | 6 hrs | FY27 | 6 | 90018856 | A1 | 1000189141 | 11.10.2026 | 4500 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN90018856
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Lift RH High Lift | 2026-10-17 | 2026-10-18 | 20 hrs | FY27 | 40 | 90002727 | A1 | 1000029094 | 17.10.2026 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLR | 6000 | 78554 | 8785 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLR90002727
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Replace Artic Area Hyd Hosing | 2026-10-17 | 2026-10-17 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220520 | 21.10.2026 | 8 Monthly | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO90020831
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Operators Seat | 2026-10-23 | 2026-10-23 | 2 hrs | FY27 | 4 | 90002975 | A2 | 1000190021 | 23.10.2026 | 7000 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS | 5900 | 30649 | 5594 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS90002975
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Operators Seat | 2026-10-26 | 2026-10-26 | 4 hrs | FY27 | 8 | 90018835 | A1 | 1000202318 | 30.10.2026 | 6000 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS | 4800 | 24525 | 4908 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS90018835
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Brake Cooling | 2026-11-02 | 2026-11-02 | 8 hrs | FY27 | 8 | 90002713 | A1 | 1000029013 | 31.10.2026 | 10000 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP02 | 6000 | 64740 | 8466 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP0290002713
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Drive Shaft Unis | 2026-11-02 | 2026-11-02 | 3 hrs | FY27 | 6 | 90033292 | A1 | 1000334090 | 03.11.2026 | 9000 | CLB-MP-DOZR-DZ016 -TRNSYS | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -TRNSYS90033292
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Replace High Risk Hoses | 2026-11-07 | 2026-11-07 | 8 hrs | FY27 | 8 | 90024258 | A1 | 1000227474 | 07.11.2026 | 8000 | CLB-MP-LOAD-WL6103-ENGINE | 5000 | 21377 | 6697 | CLB-MP-LOAD-WL6103-ENGINE90024258
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Engine Midlife Complete | 2026-11-07 | 2026-11-10 | 68 hrs | FY27 | 80 | 90015824 | A2 | 1000207982 | 07.11.2026 | 8000 | CLB-MP-LOAD-WL6103-ENGINE | 5000 | 21377 | 6697 | CLB-MP-LOAD-WL6103-ENGINE90015824
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Wash Engine Pre Cleaners | 2026-11-07 | 2026-11-07 | 2 hrs | FY27 | 2 | 90017388 | 1 | 1000207983 | 07.11.2026 | 8000 | CLB-MP-LOAD-WL6103-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-LOAD-WL6103-ENGINE-INTEX-AIRFL90017388
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Air Conditioner Overhaul | 2026-11-07 | 2026-11-09 | 48 hrs | FY27 | 48 | 90017479 | A1 | 1000207978 | 07.11.2026 | 8000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN90017479
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Gearbox Pump Drive Front | 2026-11-11 | 2026-11-12 | 38 hrs | FY27 | 74 | 90002705 | A1 | 1000029133 | 15.12.2025 | 16000 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-FRPDR | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-FRPDR90002705
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Track Frame LH | 2026-11-12 | 2026-11-13 | 20 hrs | FY27 | 40 | 90002099 | 1 | 1000089459 | 12.11.2026 | 36000 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-TKFRL | 4700 | 66933 | 16763 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-TKFRL90002099
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Track Frame RH | 2026-11-12 | 2026-11-13 | 20 hrs | FY27 | 40 | 90002102 | 1 | 1000089479 | 12.11.2026 | 36000 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-TKFRR | 4700 | 66933 | 16763 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-TKFRR90002102
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Engine Midlife complete | 2026-11-17 | 2026-11-19 | 53 hrs | FY27 | 53 | 90019407 | A1 | 1000274180 | 17.11.2026 | 7000 | CLB-MP-GRDR-GR6503-ENGINE | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ENGINE90019407
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Front Axle Assy Midlife | 2026-11-17 | 2026-11-18 | 32 hrs | FY27 | 56 | 90027058 | A1 | 1000274154 | 17.11.2026 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-AXLES | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-AXLES90027058
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Major Service Air Conditioner | 2026-11-17 | 2026-11-18 | 24 hrs | FY27 | 24 | 90019410 | A1 | 1000274181 | 17.11.2026 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN90019410
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Operators Seat | 2026-11-17 | 2026-11-17 | 4 hrs | FY27 | 8 | 90019380 | A1 | 1000274161 | 17.11.2026 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS90019380
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Implement LH | 2026-11-19 | 2026-11-19 | 12 hrs | FY27 | 24 | 90002723 | A1 | 1000029154 | 19.11.2026 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP01 | 6000 | 81297 | 8428 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Implement RH | 2026-11-19 | 2026-11-19 | 12 hrs | FY27 | 24 | 90002724 | A1 | 1000029155 | 19.11.2026 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP02 | 6000 | 81297 | 8425 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Implement Centre | 2026-11-19 | 2026-11-19 | 12 hrs | FY27 | 24 | 90002725 | A1 | 1000029156 | 19.11.2026 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP03 | 6000 | 81297 | 8425 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0390002725
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Steer Clutch & Brake Assm LH | 2026-11-22 | 2026-11-22 | 16 hrs | FY27 | 32 | 90000313 | 1 | 1000020565 | 22.11.2026 | 18000 | CLB-MP-DOZR-DZ017 -BRKSTR-SCABL | 4700 | 70238 | 16673 | CLB-MP-DOZR-DZ017 -BRKSTR-SCABL90000313
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Final Drive LH | 2026-11-22 | 2026-11-22 | 14 hrs | FY27 | 28 | 90000312 | 1 | 1000020563 | 22.11.2026 | 18000 | CLB-MP-DOZR-DZ017 -FDRSYS-FDRLH | 4700 | 70238 | 16673 | CLB-MP-DOZR-DZ017 -FDRSYS-FDRLH90000312
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Hyd Oil Cooler | 2026-11-22 | 2026-11-22 | 10 hrs | FY27 | 10 | 90009664 | 1 | 1000075356 | 22.11.2026 | 18000 | CLB-MP-DOZR-DZ017 -HYDSYS-HDOCO | 4700 | 70238 | 16673 | CLB-MP-DOZR-DZ017 -HYDSYS-HDOCO90009664
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Trans System Hoses Midlife | 2026-11-29 | 2026-11-30 | 24 hrs | FY27 | 24 | 90026915 | A1 | 1000271656 | 29.11.2026 | 8000 | CLB-MP-LOAD-WL265 -TRNSYS-TRHLF-TRNHO | 6000 | 65007 | 5714 | CLB-MP-LOAD-WL265 -TRNSYS-TRHLF-TRNHO90026915
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Replace Artic Area Hyd Hosing | 2026-12-06 | 2026-12-06 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220518 | 06.12.2026 | 8 Monthly | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Steering RH | 2026-12-07 | 2026-12-07 | 10 hrs | FY27 | 20 | 90002722 | A1 | 1000029023 | 10.07.2026 | 12000 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYR | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYR90002722
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Service Minor Air Conditioner | 2026-12-10 | 2026-12-10 | 6 hrs | FY27 | 6 | 90018856 | A1 | 1000189190 | 10.12.2026 | 4500 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN | 4800 | 26987 | 8028 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN90018856
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Service Airconditoner Minor | 2026-12-11 | 2026-12-11 | 6 hrs | FY27 | 6 | 90029039 | A1 | 1000290169 | 11.12.2026 | 3500 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN90029039
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Articulation Overhaul | 2026-12-14 | 2026-12-22 | 194 hrs | FY27 | 360 | 90032991 | A1 | 1000329978 | 14.12.2026 | 16000 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-ARTIC | 6000 | 64740 | 13629 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-ARTIC90032991
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Final Drive RH | 2026-12-15 | 2026-12-16 | 22 hrs | FY27 | 44 | 90003346 | 1 | 1000037926 | 15.12.2026 | 14000 | CLB-MP-DOZR-DZX021-FDRSYS-FDRRH | 5000 | 65875 | 12123 | CLB-MP-DOZR-DZX021-FDRSYS-FDRRH90003346
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Engine Midlife complete | 2026-12-15 | 2026-12-18 | 75 hrs | FY27 | 102 | 90015811 | A2 | 1000189979 | 15.12.2026 | 11000 | CLB-MP-DOZR-WD6106-ENGINE | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-ENGINE90015811
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Shaft Universals Centre | 2026-12-15 | 2026-12-15 | 3 hrs | FY27 | 6 | 90026668 | A1 | 1000268515 | 15.12.2026 | 11000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT03 | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0390026668
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Thermostats | 2026-12-17 | 2026-12-17 | 6 hrs | FY27 | 6 | 90021139 | 1 | 1000222422 | 17.12.2026 | 5000 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-THERM | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Service Air Conditioner | 2026-12-17 | 2026-12-18 | 24 hrs | FY27 | 24 | 90021130 | 1 | 1000222412 | 17.12.2026 | 5000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN90021130
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Replace Artic Area Hyd Hosing | 2026-12-21 | 2026-12-21 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220522 | 21.12.2026 | 8 Monthly | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Steering RH | 2026-12-21 | 2026-12-21 | 10 hrs | FY27 | 20 | 90002722 | A1 | 1000079911 | 21.12.2026 | 12000 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYR | 6000 | 65007 | 9745 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYR90002722
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Transmission Charge Pump | 2026-12-23 | 2026-12-23 | 6 hrs | FY27 | 12 | 90002694 | A1 | 1000029122 | 23.12.2026 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-TRPMP | 6000 | 81297 | 7864 | CLB-MP-LOAD-WL027 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Steering LH | 2026-12-26 | 2026-12-26 | 10 hrs | FY27 | 18 | 90002721 | A1 | 1000029152 | 26.12.2026 | 12000 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYL | 6000 | 81297 | 9807 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYL90002721
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Replace Artic Area Hyd Hosing | 2026-12-28 | 2026-12-28 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220521 | 28.12.2026 | 8 Monthly | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Overhaul Boom | 2027-01-07 | 2027-01-09 | 48 hrs | FY27 | 96 | 90021334 | A1 | 1000223810 | 07.01.2027 | 40000 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-LIARM | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-LIARM90021334
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Pump Steering Main | 2027-01-09 | 2027-01-09 | 8 hrs | FY27 | 8 | 90002958 | A1 | 1000033530 | 09.01.2027 | 15000 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP01 | 5900 | 79354 | 12401 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP0190002958
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Pump Steer Secondary | 2027-01-09 | 2027-01-09 | 6 hrs | FY27 | 6 | 90002960 | A1 | 1000033532 | 09.01.2027 | 15000 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP03 | 5900 | 79354 | 12401 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP0390002960
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Pump Pilot | 2027-01-09 | 2027-01-09 | 6 hrs | FY27 | 6 | 90002963 | A1 | 1000033536 | 09.01.2027 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP02 | 5900 | 79354 | 12401 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP0290002963
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Engine Cat C27 | 2027-01-09 | 2027-01-11 | 46 hrs | FY27 | 82 | 90018843 | A1 | 1000189078 | 09.01.2027 | 18000 | CLB-MP-DOZR-DZ8222-ENGINE | 4800 | 25244 | 16002 | CLB-MP-DOZR-DZ8222-ENGINE90018843
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Wash Engine Pre Cleaners | 2027-01-09 | 2027-01-09 | 2 hrs | FY27 | 2 | 90018848 | A1 | 1000189084 | 09.01.2027 | 9000 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AIRFL90018848
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Overhaul Air Conditioner | 2027-01-09 | 2027-01-11 | 48 hrs | FY27 | 48 | 90018854 | A1 | 1000189091 | 09.01.2027 | 18000 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN90018854
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Pump Trans & TCon Charge | 2027-01-09 | 2027-01-09 | 10 hrs | FY27 | 10 | 90018828 | A1 | 1000189061 | 09.01.2027 | 18000 | CLB-MP-DOZR-DZ8222-TRNSYS-TRPMP | 4800 | 25244 | 16002 | CLB-MP-DOZR-DZ8222-TRNSYS-TRPMP90018828
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Brake Assy RHF | 2027-01-09 | 2027-01-10 | 18 hrs | FY27 | 36 | 90002455 | A1 | 1000090996 | 09.01.2027 | 8000 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRF | 4000 | 51804 | 6119 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRF90002455
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Drive Shaft Unis | 2027-01-10 | 2027-01-10 | 3 hrs | FY27 | 6 | 90033292 | A1 | 1000334080 | 10.01.2027 | 9000 | CLB-MP-DOZR-DZ011 -TRNSYS | 4700 | 70636 | 7204 | CLB-MP-DOZR-DZ011 -TRNSYS90033292
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Service Minor Air Conditioner | 2027-01-11 | 2027-01-11 | 12 hrs | FY27 | 12 | 90019542 | 1 | 1000200123 | 11.01.2027 | 3500 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN90019542
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Final Drive LH | 2027-01-11 | 2027-01-11 | 14 hrs | FY27 | 28 | 90000312 | 1 | 1000020586 | 11.01.2027 | 18000 | CLB-MP-DOZR-DZ018 -FDRSYS-FDRLH | 4700 | 66933 | 15995 | CLB-MP-DOZR-DZ018 -FDRSYS-FDRLH90000312
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Minor Service Air Conditioner | 2027-01-16 | 2027-01-16 | 6 hrs | FY27 | 6 | 90017699 | 1 | 1000162397 | 16.01.2027 | 4500 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN90017699
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Replace Operators Seat | 2027-01-18 | 2027-01-18 | 4 hrs | FY27 | 8 | 90000318 | 1 | 1000089358 | 18.01.2027 | 6000 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-SEATS | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-SEATS90000318
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Clean Engine Pre Cleaners | 2027-01-21 | 2027-01-21 | 1 hr | FY27 | 1 | 90029028 | A1 | 1000289943 | 21.01.2027 | 5500 | CLB-MP-DOZR-WD004 -ENGINE | 5900 | 72896 | 13773 | CLB-MP-DOZR-WD004 -ENGINE90029028
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Service Airconditioner | 2027-01-21 | 2027-01-22 | 24 hrs | FY27 | 24 | 90029025 | A1 | 1000289941 | 21.01.2027 | 5500 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN | 5900 | 72896 | 2306 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN90029025
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Lift LH Lift | 2027-01-22 | 2027-01-23 | 20 hrs | FY27 | 40 | 90017160 | A1 | 1000154656 | 22.01.2027 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLL | 6000 | 67352 | 8109 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLL90017160
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Lift RH Lift | 2027-01-22 | 2027-01-23 | 20 hrs | FY27 | 40 | 90017160 | A1 | 1000154657 | 22.01.2027 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLR | 6000 | 67352 | 8109 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLR90017160
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Pilot & Cooling | 2027-01-22 | 2027-01-22 | 6 hrs | FY27 | 12 | 90002726 | A1 | 1000088585 | 22.01.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP04 | 6000 | 60624 | 17971 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0490002726
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Bucket LH Lift | 2027-01-25 | 2027-01-26 | 18 hrs | FY27 | 36 | 90017161 | 1 | 1000154658 | 25.01.2027 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYL | 6000 | 67352 | 8062 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYL90017161
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Operators Seat | 2027-01-26 | 2027-01-26 | 4 hrs | FY27 | 4 | 90002741 | A1 | 1000029233 | 26.01.2027 | 7000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS | 6000 | 80034 | 3928 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS90002741
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Pump Transmission | 2027-01-26 | 2027-01-26 | 8 hrs | FY27 | 8 | 90021465 | A1 | 1000208013 | 26.01.2027 | 8000 | CLB-MP-LOAD-WL6103-TRNSYS-TRPMP | 5000 | 21377 | 5580 | CLB-MP-LOAD-WL6103-TRNSYS-TRPMP90021465
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Replace Artic Area Hyd Hosing | 2027-01-27 | 2027-01-27 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220500 | 27.01.2027 | 8 Monthly | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO90020831
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Engine Midlife complete | 2027-02-02 | 2027-02-04 | 53 hrs | FY27 | 53 | 90019407 | A1 | 1000274245 | 02.02.2027 | 7000 | CLB-MP-GRDR-GR6504-ENGINE | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-ENGINE90019407
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Front Axle Assy Midlife | 2027-02-02 | 2027-02-03 | 32 hrs | FY27 | 56 | 90027058 | A1 | 1000274219 | 02.02.2027 | 7000 | CLB-MP-GRDR-GR6504-STRUCT-AXLES | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-AXLES90027058
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Major Service Air Conditioner | 2027-02-02 | 2027-02-03 | 24 hrs | FY27 | 24 | 90019410 | A1 | 1000274246 | 02.02.2027 | 7000 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN90019410
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Operators Seat | 2027-02-02 | 2027-02-02 | 4 hrs | FY27 | 8 | 90019380 | A1 | 1000274226 | 02.02.2027 | 7000 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-SEATS | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-SEATS90019380
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Brake Oil Cooler | 2027-02-04 | 2027-02-05 | 36 hrs | FY27 | 72 | 90002715 | A1 | 1000029146 | 04.02.2027 | 20000 | CLB-MP-LOAD-WL027 -BRKSYS-BROCC | 6000 | 81297 | 17162 | CLB-MP-LOAD-WL027 -BRKSYS-BROCC90002715
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Shaft Ctr Bearing to Fr Diff | 2027-02-06 | 2027-02-06 | 6 hrs | FY27 | 12 | 90021472 | A1 | 1000207969 | 06.02.2027 | 12000 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT04 | 5000 | 21377 | 9436 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT0490021472
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Bucket Cyl Tilt RH | 2027-02-06 | 2027-02-06 | 13 hrs | FY27 | 26 | 90024039 | A1 | 1000207968 | 06.02.2027 | 12000 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-BUCYR | 5000 | 21377 | 9436 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-BUCYR90024039
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Engine Midlife complete | 2027-02-07 | 2027-02-09 | 59 hrs | FY27 | 82 | 90015811 | 1 | 1000179043 | 07.02.2027 | 11000 | CLB-MP-DOZR-WD6105-ENGINE | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE90015811
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Clean Engine Pre Cleaners | 2027-02-07 | 2027-02-07 | 6 hrs | FY27 | 6 | 90015808 | 1 | 1000179040 | 07.02.2027 | 5500 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL90015808
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Shaft Universals TC - Trans | 2027-02-07 | 2027-02-07 | 3 hrs | FY27 | 3 | 90026669 | A1 | 1000268503 | 07.02.2027 | 11000 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT01 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT0190026669
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Overhaul Airconditioner | 2027-02-07 | 2027-02-09 | 48 hrs | FY27 | 48 | 90013087 | 2 | 1000195981 | 07.02.2027 | 11000 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN90013087
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Thermostats | 2027-02-07 | 2027-02-07 | 6 hrs | FY27 | 6 | 90021139 | 1 | 1000222598 | 07.02.2027 | 5000 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-THERM | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Service Air Conditioner | 2027-02-07 | 2027-02-08 | 24 hrs | FY27 | 24 | 90021130 | 1 | 1000222588 | 07.02.2027 | 5000 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN90021130
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Overhaul Rear Axle Trunnion | 2027-02-09 | 2027-02-11 | 48 hrs | FY27 | 96 | 90002709 | A1 | 1000079897 | 09.02.2027 | 20000 | CLB-MP-LOAD-WL265 -FDRSYS-RRDIF-TRNON | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -FDRSYS-RRDIF-TRNON90002709
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Service Brake LHF | 2027-02-10 | 2027-02-12 | 48 hrs | FY27 | 96 | 90021477 | A1 | 1000207955 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBLF | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBLF90021477
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Service Brake LHR | 2027-02-10 | 2027-02-12 | 48 hrs | FY27 | 96 | 90021477 | A1 | 1000207956 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBLR | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBLR90021477
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Service Brake RHF | 2027-02-10 | 2027-02-12 | 48 hrs | FY27 | 96 | 90021477 | A1 | 1000207957 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBRF | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBRF90021477
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Service Brake RHR | 2027-02-10 | 2027-02-12 | 48 hrs | FY27 | 96 | 90021477 | A1 | 1000207958 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBRR | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBRR90021477
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Final Drive Position 1 | 2027-02-10 | 2027-02-11 | 27 hrs | FY27 | 54 | 90021476 | A1 | 1000207994 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR01 | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR0190021476
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Final Drive Position 2 | 2027-02-10 | 2027-02-11 | 27 hrs | FY27 | 54 | 90021476 | A1 | 1000207995 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR02 | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR0290021476
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Final Drive Position 3 | 2027-02-10 | 2027-02-11 | 27 hrs | FY27 | 54 | 90021476 | A1 | 1000207996 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR03 | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR0390021476
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Final Drive Position 4 | 2027-02-10 | 2027-02-11 | 27 hrs | FY27 | 54 | 90021476 | A1 | 1000207997 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR04 | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR0490021476
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Front Differential | 2027-02-10 | 2027-02-11 | 26 hrs | FY27 | 52 | 90021501 | A1 | 1000207973 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-FDRSYS-FRDIF | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-FRDIF90021501
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Rear Differential | 2027-02-10 | 2027-02-11 | 26 hrs | FY27 | 52 | 90021502 | A1 | 1000207974 | 10.02.2027 | 24000 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF | 5000 | 21377 | 21377 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF90021502
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 12M Inspection Isolator Panel | 2027-02-11 | 2027-02-11 | 2 hrs | FY27 | 2 | 90022525 | A2 | 1000236558 | 11.02.2027 | 12 Monthly | CLB-MP-LOAD-WL263 -ELCTLV | 6000 | 60721 | 60721 | CLB-MP-LOAD-WL263 -ELCTLV90022525
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Implement LH | 2027-02-13 | 2027-02-13 | 12 hrs | FY27 | 24 | 90002723 | A1 | 1000088582 | 13.02.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP01 | 6000 | 60624 | 6877 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0190002723
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Engine Midlife complete | 2027-02-13 | 2027-02-15 | 53 hrs | FY27 | 53 | 90019407 | A1 | 1000274565 | 13.02.2027 | 7000 | CLB-MP-GRDR-GR6501-ENGINE | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-ENGINE90019407
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Front Axle Assy Midlife | 2027-02-13 | 2027-02-14 | 32 hrs | FY27 | 56 | 90027058 | A1 | 1000274299 | 13.02.2027 | 7000 | CLB-MP-GRDR-GR6501-STRUCT-AXLES | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-AXLES90027058
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Major Service Air Conditioner | 2027-02-13 | 2027-02-14 | 24 hrs | FY27 | 24 | 90019410 | A1 | 1000274566 | 13.02.2027 | 7000 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN90019410
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Repl Operators Seat | 2027-02-13 | 2027-02-13 | 4 hrs | FY27 | 8 | 90019380 | A1 | 1000274546 | 13.02.2027 | 7000 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-SEATS | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-SEATS90019380
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Pump Cooling Fan | 2027-02-15 | 2027-02-15 | 10 hrs | FY27 | 10 | 90002964 | A1 | 1000033537 | 15.02.2027 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP03 | 5900 | 79354 | 11802 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP0390002964
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Batteries | 2027-02-15 | 2027-02-15 | 4 hrs | FY27 | 4 | 90023377 | A1 | 1000243622 | 15.02.2027 | 12 Monthly | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-BATTY |  |  |  | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-BATTY90023377
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Adjust Engine 500hr Valve Set | 2027-02-16 | 2027-02-16 | 12 hrs | FY27 | 24 | 90018851 | A1 | 1000189087 | 16.02.2027 | 500 | CLB-MP-DOZR-DZ8222-ENGINE | 4800 | 25244 | 16002 | CLB-MP-DOZR-DZ8222-ENGINE90018851
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Engine Midlife Complete | 2027-02-17 | 2027-02-21 | 98 hrs | FY27 | 130 | 90029037 | A1 | 1000290175 | 17.02.2027 | 7000 | CLB-MP-DOZR-DZX024-ENGINE | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-ENGINE90029037
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Trans Pump Drive Coupling Replace | 2027-02-17 | 2027-02-17 | 10 hrs | FY27 | 10 | 90037705 | A1 | 1000374089 | 17.02.2027 | 7000 | CLB-MP-DOZR-DZX024-TRNSYS-TRPMP | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-TRNSYS-TRPMP90037705
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Hyd Pump Cooling Fan | 2027-02-17 | 2027-02-17 | 10 hrs | FY27 | 10 | 90009272 | 1 | 1000071479 | 17.02.2027 | 7000 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYFPP | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYFPP90009272
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Fan Cooling Motor Hyd | 2027-02-17 | 2027-02-17 | 8 hrs | FY27 | 16 | 90003352 | 1 | 1000038011 | 17.02.2027 | 7000 | CLB-MP-DOZR-DZX024-HYDSYS-HDCFM | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-HYDSYS-HDCFM90003352
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Service Airconditroner Major | 2027-02-17 | 2027-02-18 | 24 hrs | FY27 | 24 | 90029040 | A1 | 1000290177 | 17.02.2027 | 7000 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-AIRCN | 4400 | 61520 | 4630 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-AIRCN90029040
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Brake | 2027-02-18 | 2027-02-18 | 12 hrs | FY27 | 12 | 90002712 | A1 | 1000079902 | 18.02.2027 | 20000 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP-BRP01 | 6000 | 65007 | 33503 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP-BRP0190002712
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Front Pump Drv Drive Shaft | 2027-02-19 | 2027-02-19 | 8 hrs | FY27 | 16 | 90033189 | A1 | 1000333633 | 19.02.2027 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT06 | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0690033189
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Cylinder Blade Tilt RH | 2027-02-22 | 2027-02-22 | 8 hrs | FY27 | 14 | 90002968 | A1 | 1000228668 | 22.02.2027 | 22000 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BTCYR | 5900 | 55835 | 18716 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BTCYR90002968
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Cylinder Blade Lift LH | 2027-02-23 | 2027-02-23 | 10 hrs | FY27 | 18 | 90000287 | 1 | 1000255574 | 23.02.2027 | 9000 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYL | 4700 | 70238 | 3490 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYL90000287
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Adjust Engine 500hr Valve Set | 2027-02-28 | 2027-02-28 | 12 hrs | FY27 | 24 | 90015857 | 1 | 1000159508 | 28.02.2027 | 500 | CLB-MP-DOZR-DZ012 -ENGINE | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -ENGINE90015857
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Operators Seat | 2027-03-01 | 2027-03-01 | 4 hrs | FY27 | 4 | 90010850 | 1 | 1000089527 | 01.03.2027 | 10000 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-SEATS | 4400 | 61520 | 7488 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-SEATS90010850
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Engine Midlife complete | 2027-03-02 | 2027-03-04 | 53 hrs | FY27 | 53 | 90019407 | A1 | 1000274651 | 02.03.2027 | 7000 | CLB-MP-GRDR-GR6505-ENGINE | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-ENGINE90019407
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Front Axle Assy Midlife | 2027-03-02 | 2027-03-03 | 32 hrs | FY27 | 56 | 90027058 | A1 | 1000274625 | 02.03.2027 | 7000 | CLB-MP-GRDR-GR6505-STRUCT-AXLES | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-AXLES90027058
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Major Service Air Conditioner | 2027-03-02 | 2027-03-03 | 24 hrs | FY27 | 24 | 90019410 | A1 | 1000274652 | 02.03.2027 | 7000 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN90019410
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Repl Operators Seat | 2027-03-02 | 2027-03-02 | 4 hrs | FY27 | 8 | 90019380 | A1 | 1000274632 | 02.03.2027 | 7000 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-SEATS | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-SEATS90019380
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Transmission Transfer Case | 2027-03-03 | 2027-03-04 | 38 hrs | FY27 | 74 | 90017029 | A1 | 1000153364 | 03.03.2027 | 16000 | CLB-MP-LOAD-WL025 -TRNSYS-TRTRF | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-TRTRF90017029
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Thermostats | 2027-03-07 | 2027-03-07 | 6 hrs | FY27 | 6 | 90021139 | 1 | 1000222488 | 07.03.2027 | 5000 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-THERM | 6000 | 80034 | 11272 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Service Air Conditioner | 2027-03-07 | 2027-03-08 | 24 hrs | FY27 | 24 | 90021130 | 1 | 1000222478 | 07.03.2027 | 5000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN90021130
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Final Drive LH | 2027-03-11 | 2027-03-11 | 14 hrs | FY27 | 28 | 90000312 | 1 | 1000018437 | 11.03.2027 | 18000 | CLB-MP-DOZR-DZ013 -FDRSYS-FDRLH | 4700 | 72325 | 15283 | CLB-MP-DOZR-DZ013 -FDRSYS-FDRLH90000312
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Input Drive Shaft | 2027-03-12 | 2027-03-12 | 6 hrs | FY27 | 12 | 90033166 | A1 | 1000333575 | 12.03.2027 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT01 | 6000 | 64740 | 16190 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0190033166
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Cyl Steering RH | 2027-03-12 | 2027-03-12 | 12 hrs | FY27 | 24 | 90024037 | A1 | 1000207966 | 12.03.2027 | 16000 | CLB-MP-LOAD-WL6103-STRSYS-STRCY-STCYR | 5000 | 21377 | 12966 | CLB-MP-LOAD-WL6103-STRSYS-STRCY-STCYR90024037
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Brake | 2027-03-13 | 2027-03-13 | 12 hrs | FY27 | 12 | 90002712 | A1 | 1000088571 | 13.03.2027 | 20000 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP01 | 6000 | 60624 | 16431 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP0190002712
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Auto Lube Pump | 2027-03-14 | 2027-03-14 | 6 hrs | FY27 | 6 | 90002737 | A1 | 1000029035 | 14.03.2027 | 10000 | CLB-MP-LOAD-WL025 -GRSYST-ALBPP | 6000 | 64740 | 6152 | CLB-MP-LOAD-WL025 -GRSYST-ALBPP90002737
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Transmission Charge Pump | 2027-03-18 | 2027-03-18 | 6 hrs | FY27 | 12 | 90002694 | A1 | 1000079817 | 18.03.2027 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-TRPMP | 6000 | 67352 | 6205 | CLB-MP-LOAD-WL264 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Gearbox Pump Drive Front | 2027-03-19 | 2027-03-20 | 38 hrs | FY27 | 74 | 90002705 | A1 | 1000079828 | 19.03.2027 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR-FRPDR | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR-FRPDR90002705
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Service Minor Air Conditioner | 2027-03-21 | 2027-03-21 | 12 hrs | FY27 | 12 | 90019542 | 1 | 1000200121 | 21.03.2027 | 3500 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN90019542
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Minor Service Air Conditioner | 2027-03-21 | 2027-03-21 | 6 hrs | FY27 | 6 | 90017699 | 1 | 1000162400 | 21.03.2027 | 4500 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Operators Seat | 2027-03-22 | 2027-03-22 | 4 hrs | FY27 | 4 | 90002741 | A1 | 1000088590 | 22.03.2027 | 7000 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-SEATS | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-SEATS90002741
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Operators Seat | 2027-03-22 | 2027-03-22 | 4 hrs | FY27 | 4 | 90002975 | A1 | 1000228701 | 22.03.2027 | 7000 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-SEATS | 5900 | 55835 | 3274 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-SEATS90002975
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Actuator Brake HaulX Shield | 2027-03-23 | 2027-03-24 | 26 hrs | FY27 | 50 | 90033499 | A1 | 1000337810 | 23.03.2027 | 14000 | CLB-MP-DOZR-DZ8222-CASSYS-CTRLH-ACTBK | 4800 | 25262 | 25262 | CLB-MP-DOZR-DZ8222-CASSYS-CTRLH-ACTBK90033499
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8223 | DZ8223 Repl Operators Seat | 2027-03-23 | 2027-03-23 | 4 hrs | FY27 | 8 | 90018835 | A1 | 1000189119 | 23.03.2027 | 6000 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-SEATS | 4800 | 26747 | 3032 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-SEATS90018835
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Engine Midlife Complete | 2027-03-28 | 2027-03-30 | 53 hrs | FY27 | 61 | 90018853 | A1 | 1000221490 | 28.03.2027 | 9000 | CLB-MP-DOZR-DZ8226-ENGINE | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-ENGINE90018853
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Wash Engine Pre Cleaners | 2027-03-28 | 2027-03-28 | 2 hrs | FY27 | 2 | 90018848 | A1 | 1000221485 | 28.03.2027 | 9000 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AIRFL90018848
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Service Major Air Conditioner | 2027-03-28 | 2027-03-29 | 24 hrs | FY27 | 24 | 90018855 | A1 | 1000221491 | 28.03.2027 | 9000 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN | 4800 | 18270 | 18270 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN90018855
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Trans System Hoses Midlife | 2027-03-30 | 2027-03-31 | 24 hrs | FY27 | 24 | 90026915 | A1 | 1000271644 | 30.03.2027 | 8000 | CLB-MP-LOAD-WL028 -TRNSYS-TRHLF-TRNHO | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-TRHLF-TRNHO90026915
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Trans Input Drive Shaft Unis | 2027-03-30 | 2027-03-30 | 4 hrs | FY27 | 8 | 90033267 | A1 | 1000333927 | 30.03.2027 | 7000 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT02 | 6000 | 73365 | 2853 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT0290033267
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Hyd Pump Implement | 2027-03-31 | 2027-03-31 | 10 hrs | FY27 | 10 | 90000301 | 1 | 1000020545 | 31.03.2027 | 9000 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYIPP | 4700 | 72846 | 4404 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYIPP90000301
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Implement LH | 2027-04-02 | 2027-04-02 | 12 hrs | FY27 | 24 | 90002723 | A1 | 1000079912 | 02.04.2027 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP01 | 6000 | 65007 | 6057 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Implement Centre | 2027-04-02 | 2027-04-02 | 12 hrs | FY27 | 24 | 90002725 | A1 | 1000079914 | 02.04.2027 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP03 | 6000 | 65007 | 6057 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP0390002725
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Drive Shaft Unis | 2027-04-04 | 2027-04-04 | 3 hrs | FY27 | 6 | 90033292 | A1 | 1000334094 | 04.04.2027 | 9000 | CLB-MP-DOZR-DZ018 -TRNSYS | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -TRNSYS90033292
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Hyd Motor Fan | 2027-04-06 | 2027-04-06 | 12 hrs | FY27 | 24 | 90021486 | A1 | 1000208002 | 06.04.2027 | 8000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM01 | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM0190021486
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Operators Seat | 2027-04-08 | 2027-04-08 | 4 hrs | FY27 | 4 | 90002975 | A1 | 1000033548 | 08.04.2027 | 7000 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-SEATS | 5900 | 79354 | 10152 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-SEATS90002975
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Trans System Hoses Midlife | 2027-04-11 | 2027-04-12 | 24 hrs | FY27 | 24 | 90026915 | A1 | 1000271650 | 11.04.2027 | 8000 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO90026915
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Repl Drive Shaft Unis | 2027-04-13 | 2027-04-13 | 3 hrs | FY27 | 6 | 90033312 | A1 | 1000334041 | 13.04.2027 | 9000 | CLB-MP-DOZR-DZ8226-TRNSYS-DRSHT | 4800 | 18270 | 18270 | CLB-MP-DOZR-DZ8226-TRNSYS-DRSHT90033312
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Front Axle Assembly Midlife | 2027-04-14 | 2027-04-15 | 38 hrs | FY27 | 44 | 90025907 | A1 | 1000255900 | 14.04.2027 | 7000 | CLB-MP-GRDR-GR021 -STRUCT-AXLES | 6000 | 73692 | 2651 | CLB-MP-GRDR-GR021 -STRUCT-AXLES90025907
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Blade Mounting Bracket LH | 2027-04-14 | 2027-04-15 | 24 hrs | FY27 | 48 | 90002671 | A1 | 1000028504 | 14.04.2027 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-BLMBL | 6000 | 71626 | 9777 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-BLMBL90002671
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Blade Mounting Bracket RH | 2027-04-14 | 2027-04-15 | 24 hrs | FY27 | 48 | 90002671 | A1 | 1000028505 | 14.04.2027 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-BLMBR | 6000 | 71626 | 9777 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-BLMBR90002671
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Bucket Cyl Tilt LH | 2027-04-15 | 2027-04-16 | 24 hrs | FY27 | 48 | 90024038 | A1 | 1000207967 | 15.04.2027 | 12000 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-BUCYL | 5000 | 21377 | 8494 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-BUCYL90024038
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Operators Seat | 2027-04-17 | 2027-04-17 | 4 hrs | FY27 | 4 | 90002741 | A1 | 1000029037 | 17.04.2027 | 7000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS90002741
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Operators Seat | 2027-04-17 | 2027-04-17 | 4 hrs | FY27 | 4 | 90010850 | 1 | 1000089525 | 17.04.2027 | 10000 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-SEATS | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-SEATS90010850
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Transmission Charge Pump | 2027-04-21 | 2027-04-21 | 6 hrs | FY27 | 12 | 90002694 | A1 | 1000079882 | 21.04.2027 | 10000 | CLB-MP-LOAD-WL265 -TRNSYS-TRPMP | 6000 | 65007 | 5751 | CLB-MP-LOAD-WL265 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Brake Oil Cooler | 2027-04-22 | 2027-04-23 | 36 hrs | FY27 | 72 | 90002715 | A1 | 1000090019 | 22.04.2027 | 20000 | CLB-MP-LOAD-WL265 -BRKSYS-BROCC | 6000 | 65007 | 15666 | CLB-MP-LOAD-WL265 -BRKSYS-BROCC90002715
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Refurbish Cabin | 2027-04-26 | 2027-04-26 | 12 hrs | FY27 | 12 | 90010318 | 1 | 1000085646 | 26.04.2027 | 28000 | CLB-MP-GRDR-GR018 -STRUCT-CABIN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CABIN90010318
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Oil Cooler | 2027-04-26 | 2027-04-28 | 48 hrs | FY27 | 96 | 90002733 | A1 | 1000079916 | 26.04.2027 | 20000 | CLB-MP-LOAD-WL265 -HYDSYS-HDOCO | 6000 | 65007 | 15666 | CLB-MP-LOAD-WL265 -HYDSYS-HDOCO90002733
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Fan Cooling Motor Hyd | 2027-04-27 | 2027-04-27 | 8 hrs | FY27 | 16 | 90002094 | 1 | 1000069924 | 27.04.2027 | 9000 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCFM | 4700 | 72405 | 5635 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCFM90002094
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Hyd Pump Implement | 2027-04-27 | 2027-04-27 | 10 hrs | FY27 | 10 | 90000301 | 1 | 1000020519 | 27.04.2027 | 9000 | CLB-MP-DOZR-DZ015 -HYDSYS-HYDPP-HYIPP | 4700 | 72405 | 5635 | CLB-MP-DOZR-DZ015 -HYDSYS-HYDPP-HYIPP90000301
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Hyd Pump Implement | 2027-05-01 | 2027-05-01 | 6 hrs | FY27 | 12 | 90002646 | A1 | 1000028476 | 01.05.2027 | 14000 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYIMP | 6000 | 71626 | 9489 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYIMP90002646
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Front Pump Drv Drive Shaft | 2027-05-08 | 2027-05-08 | 8 hrs | FY27 | 16 | 90033189 | A1 | 1000333585 | 08.05.2027 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT06 | 6000 | 64740 | 15246 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0690033189
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Operators Seat | 2027-05-12 | 2027-05-12 | 4 hrs | FY27 | 8 | 90000318 | 1 | 1000089356 | 12.05.2027 | 6000 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-SEATS | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-SEATS90000318
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Equaliser Bar | 2027-05-13 | 2027-05-15 | 48.5 hrs | FY27 | 96.5 | 90002097 | 1 | 1000089438 | 13.05.2027 | 18000 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-EQUAL | 4700 | 72405 | 17512 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-EQUAL90002097
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Cylinder Blade Tilt LH | 2027-05-20 | 2027-05-20 | 8 hrs | FY27 | 14 | 90002967 | A1 | 1000033486 | 20.05.2027 | 22000 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BTCYL | 5900 | 72896 | 17373 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BTCYL90002967
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Cylinder Blade Tilt RH | 2027-05-20 | 2027-05-20 | 8 hrs | FY27 | 14 | 90002968 | A1 | 1000033487 | 20.05.2027 | 22000 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BTCYR | 5900 | 72896 | 17373 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BTCYR90002968
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Minor Service Air Conditioner | 2027-05-25 | 2027-05-25 | 6 hrs | FY27 | 6 | 90017699 | 1 | 1000162401 | 25.05.2027 | 4500 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN | 4700 | 70238 | 1106 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN90017699
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Overhaul Pivot Shaft | 2027-05-30 | 2027-06-01 | 48 hrs | FY27 | 96 | 90010854 | 1 | 1000089514 | 30.05.2027 | 21000 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-PIVOT | 5000 | 65875 | 23207 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-PIVOT90010854
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Steer & Brake Oil Cooler Pump | 2027-06-02 | 2027-06-02 | 8 hrs | FY27 | 8 | 90002718 | A1 | 1000079908 | 02.06.2027 | 20000 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP03 | 6000 | 65007 | 30560 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP0390002718
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Repl Operators Seat | 2027-06-03 | 2027-06-03 | 4 hrs | FY27 | 8 | 90018835 | A1 | 1000221470 | 03.06.2027 | 6000 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-SEATS | 4800 | 18270 | 8040 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-SEATS90018835
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Operators Seat | 2027-06-04 | 2027-06-04 | 4 hrs | FY27 | 4 | 90002663 | A1 | 1000028689 | 04.06.2027 | 7000 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-SEATS | 6000 | 73692 | 1802 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-SEATS90002663
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Replace Operators Seat | 2027-06-08 | 2027-06-08 | 4 hrs | FY27 | 8 | 90000318 | 1 | 1000089355 | 08.06.2027 | 6000 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-SEATS | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-SEATS90000318
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Hyd Pump Implement | 2027-06-08 | 2027-06-08 | 10 hrs | FY27 | 10 | 90000301 | 1 | 1000018441 | 08.06.2027 | 9000 | CLB-MP-DOZR-DZ013 -HYDSYS-HYDPP-HYIPP | 4700 | 72325 | 5138 | CLB-MP-DOZR-DZ013 -HYDSYS-HYDPP-HYIPP90000301
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Operators Seat | 2027-06-09 | 2027-06-09 | 4 hrs | FY27 | 4 | 90002741 | A1 | 1000103785 | 09.06.2027 | 7000 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-SEATS | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-SEATS90002741
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Service Minor Air Conditioner | 2027-06-09 | 2027-06-09 | 6 hrs | FY27 | 6 | 90018856 | A1 | 1000202361 | 09.06.2027 | 4500 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN90018856
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Replace Artic Area Hyd Hosing | 2027-06-10 | 2027-06-10 | 6 hrs | FY27 | 6 | 90020831 | 1 | 1000220519 | 10.06.2027 | 8 Monthly | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Engine Midlife complete | 2027-06-11 | 2027-06-16 | 132 hrs | FY27 | 170 | 90021253 | 1 | 1000222574 | 11.06.2027 | 10000 | CLB-MP-LOAD-WL264 -ENGINE | 6000 | 67352 | 4805 | CLB-MP-LOAD-WL264 -ENGINE90021253
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Overhaul Air Conditioner | 2027-06-11 | 2027-06-13 | 48 hrs | FY27 | 48 | 90021132 | 1 | 1000222565 | 11.06.2027 | 10000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN90021132
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Centre Bearing Upper Shaft | 2027-06-15 | 2027-06-15 | 12 hrs | FY27 | 24 | 90002702 | A1 | 1000029000 | 15.06.2027 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-UCTRB | 6000 | 64740 | 4624 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-UCTRB90002702
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Cyl Articulation LH | 2027-06-16 | 2027-06-16 | 6 hrs | FY27 | 12 | 90019378 | A1 | 1000274203 | 16.06.2027 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-ARCYL | 5500 | 19712 | 19712 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-ARCYL90019378
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Trans System Hoses Midlife | 2027-06-17 | 2027-06-18 | 24 hrs | FY27 | 24 | 90026915 | A1 | 1000271626 | 17.06.2027 | 8000 | CLB-MP-LOAD-WL025 -TRNSYS-TRHLF-TRNHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-TRHLF-TRNHO90026915
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Brake | 2027-06-19 | 2027-06-19 | 12 hrs | FY27 | 12 | 90002712 | A1 | 1000029012 | 19.06.2027 | 20000 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP01 | 6000 | 64740 | 14554 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP0190002712
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Operators Seat | 2027-06-22 | 2027-06-22 | 4 hrs | FY27 | 4 | 90002797 | A1 | 1000208003 | 22.06.2027 | 6000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-SEATS | 5000 | 21377 | 1570 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-SEATS90002797
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Hyd Pump Steer Secondary | 2027-06-23 | 2027-06-23 | 6 hrs | FY27 | 6 | 90002960 | A1 | 1000179065 | 23.06.2027 | 15000 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP03 | 5900 | 55835 | 9760 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP0390002960
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Valve Hyd Steering | 2027-06-24 | 2027-06-24 | 4 hrs | FY27 | 4 | 90003347 | 1 | 1000038005 | 24.06.2027 | 14000 | CLB-MP-DOZR-DZX024-BRKSTR-STVLV | 4400 | 61520 | 10101 | CLB-MP-DOZR-DZX024-BRKSTR-STVLV90003347
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Front Drive Shaft | 2027-06-25 | 2027-06-25 | 8 hrs | FY27 | 16 | 90033175 | A1 | 1000333629 | 25.06.2027 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT04 | 6000 | 67352 | 14589 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0490033175
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Steering STIC Pilot Valve | 2027-06-26 | 2027-06-26 | 12 hrs | FY27 | 12 | 90026110 | A1 | 1000257367 | 26.06.2027 | 20000 | CLB-MP-LOAD-WL263 -STRSYS-STIPV | 6000 | 60624 | 33583 | CLB-MP-LOAD-WL263 -STRSYS-STIPV90026110
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Torque Converter | 2027-06-29 | 2027-07-02 | 86 hrs | FY27 | 170 | 90002943 | A1 | 1000033458 | 29.06.2027 | 22000 | CLB-MP-DOZR-WD004 -TRNSYS-TRQUE | 5900 | 72896 | 16688 | CLB-MP-DOZR-WD004 -TRNSYS-TRQUE90002943
| Onsite PM | Ancillary | Fortescue |  | FY28 - ANCILLARY - COMPONENTS DURING PM | 2027-07-01 |  |  | FY28
| Onsite PM | Ancillary | Fortescue | MOC | MAJOR ON CONDITION | 2027-07-01 | 2028-06-30 | 365 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | JULY | 2027-07-01 | 2027-07-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | AUGUST | 2027-08-01 | 2027-08-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | SEPTEMBER | 2027-09-01 | 2027-09-30 | 29 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | OCTOBER | 2027-10-01 | 2027-10-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | NOVEMBER | 2027-11-01 | 2027-11-30 | 29 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | DECEMBER | 2027-12-01 | 2027-12-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | JANUARY | 2028-01-01 | 2028-01-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | FEBRUARY | 2028-02-01 | 2028-02-28 | 27 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | MARCH | 2028-03-01 | 2028-03-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | APRIL | 2028-04-01 | 2028-04-30 | 29 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | MAY | 2028-05-01 | 2028-05-31 | 30 days | FY28
| Onsite PM | Ancillary | Fortescue | MOC | JUNE | 2028-06-01 | 2028-06-30 | 29 days | FY28
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Steering LH | 2027-07-01 | 2027-07-01 | 10 hrs | FY28 | 18 | 90002721 | A1 | 1000029218 | 01.07.2027 | 12000 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYL | 6000 | 80034 | 16614 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYL90002721
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Lift RH High Lift | 2027-07-01 | 2027-07-02 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000029225 | 01.07.2027 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLR | 6000 | 80034 | 4358 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLR90002727
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Lift LH High Lift | 2027-07-01 | 2027-07-02 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000112683 | 01.07.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLL | 6000 | 60624 | 4601 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLL90002727
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Steering RH | 2027-07-04 | 2027-07-04 | 10 hrs | FY28 | 20 | 90002722 | A1 | 1000029088 | 04.07.2027 | 12000 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYR | 6000 | 78554 | 409 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYR90002722
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Engine Thermostats | 2027-07-08 | 2027-07-08 | 4 hrs | FY28 | 4 | 90019397 | A1 | 1000298544 | 08.07.2027 | 3500 | CLB-MP-GRDR-GR6503-ENGINE | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Minor Service Air Conditioner | 2027-07-08 | 2027-07-08 | 12 hrs | FY28 | 12 | 90019412 | A1 | 1000274183 | 08.07.2027 | 3500 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN90019412
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Operators Seat | 2027-07-12 | 2027-07-12 | 4 hrs | FY28 | 4 | 90002663 | A1 | 1000028561 | 12.07.2027 | 7000 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-SEATS | 6000 | 73365 | 1135 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-SEATS90002663
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Replace Operators Seat | 2027-07-14 | 2027-07-14 | 4 hrs | FY28 | 8 | 90000318 | 1 | 1000089360 | 14.07.2027 | 6000 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-SEATS | 4700 | 72846 | 1567 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-SEATS90000318
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Transmission Charge Pump | 2027-07-17 | 2027-07-17 | 6 hrs | FY28 | 12 | 90002694 | A1 | 1000088551 | 17.07.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-TRPMP | 6000 | 60624 | 4273 | CLB-MP-LOAD-WL263 -TRNSYS-TRPMP90002694
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Hyd Pump Cooling Fan | 2027-07-27 | 2027-07-27 | 10 hrs | FY28 | 10 | 90009272 | 1 | 1000071477 | 27.07.2027 | 7000 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYFPP | 4400 | 63346 | 9901 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYFPP90009272
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Hyd Pump Implement | 2027-08-01 | 2027-08-01 | 10 hrs | FY28 | 10 | 90000301 | 1 | 1000020567 | 01.08.2027 | 9000 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYIPP | 4700 | 70238 | 4429 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYIPP90000301
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Replace Artic Area Hyd Hosing | 2027-08-03 | 2027-08-03 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220518 | 03.08.2027 | 8 Monthly | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO90020831
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Oil Cooler Front Axle Lube | 2027-08-04 | 2027-08-04 | 12 hrs | FY28 | 24 | 90010219 | 1 | 1000179077 | 04.08.2027 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC-OILCF | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC-OILCF90010219
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Thermostats | 2027-08-06 | 2027-08-06 | 6 hrs | FY28 | 6 | 90021139 | 1 | 1000222554 | 06.08.2027 | 5000 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-THERM | 6000 | 60721 | 11302 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Service Air Conditioner | 2027-08-06 | 2027-08-07 | 24 hrs | FY28 | 24 | 90021130 | 1 | 1000222544 | 06.08.2027 | 5000 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN90021130
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Cyl Articulation RH | 2027-08-07 | 2027-08-07 | 6 hrs | FY28 | 12 | 90019379 | A1 | 1000274204 | 07.08.2027 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-ARCYR | 5500 | 19712 | 8470 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-ARCYR90019379
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Replace Artic Area Hyd Hosing | 2027-08-08 | 2027-08-08 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220517 | 08.08.2027 | 8 Monthly | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO90020831
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Torque Converter | 2027-08-08 | 2027-08-11 | 72 hrs | FY28 | 144 | 90021500 | A1 | 1000208018 | 08.08.2027 | 16000 | CLB-MP-LOAD-WL6103-TRNSYS-TRQUE | 5000 | 21377 | 10927 | CLB-MP-LOAD-WL6103-TRNSYS-TRQUE90021500
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Engine Midlife complete | 2027-08-11 | 2027-08-13 | 60 hrs | FY28 | 72 | 90015782 | 1 | 1000159912 | 11.08.2027 | 7000 | CLB-MP-GRDR-GR021 -ENGINE | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE90015782
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Drive Shaft Trans to Rr Diff | 2027-08-11 | 2027-08-11 | 3 hrs | FY28 | 6 | 90033262 | A1 | 1000333928 | 11.08.2027 | 14000 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT01 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT0190033262
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Drive Shaft TCon to Trans | 2027-08-11 | 2027-08-11 | 4 hrs | FY28 | 4 | 90033265 | A1 | 1000333930 | 11.08.2027 | 14000 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT02 | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT0290033265
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Service Major Air Conditioner | 2027-08-11 | 2027-08-12 | 24 hrs | FY28 | 24 | 90017472 | 1 | 1000160704 | 11.08.2027 | 7000 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN90017472
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Lift RH High Lift | 2027-08-11 | 2027-08-12 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000112684 | 11.08.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLR | 6000 | 60624 | 3938 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLR90002727
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Gearbox Circle Drive Rear | 2027-08-11 | 2027-08-11 | 8 hrs | FY28 | 14 | 90011066 | 1 | 1000028507 | 11.08.2027 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-CDBXR | 6000 | 71626 | 7817 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-CDBXR90011066
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Replace Artic Area Hyd Hosing | 2027-08-18 | 2027-08-18 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220522 | 18.08.2027 | 8 Monthly | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO90020831
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Adjust Engine 500hr Valve Set | 2027-08-18 | 2027-08-18 | 12 hrs | FY28 | 24 | 90015857 | 1 | 1000159436 | 18.08.2027 | 500 | CLB-MP-DOZR-DZ011 -ENGINE | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -ENGINE90015857
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Service Minor Air Conditioner | 2027-08-20 | 2027-08-20 | 12 hrs | FY28 | 12 | 90019542 | 1 | 1000200120 | 20.08.2027 | 3500 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN90019542
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Gearbox Pump Drive Front | 2027-08-21 | 2027-08-22 | 38 hrs | FY28 | 74 | 90002705 | A1 | 1000079893 | 21.08.2027 | 16000 | CLB-MP-LOAD-WL265 -TRNSYS-PMPDR-FRPDR | 6000 | 65007 | 9745 | CLB-MP-LOAD-WL265 -TRNSYS-PMPDR-FRPDR90002705
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Transmission | 2027-08-21 | 2027-08-22 | 38 hrs | FY28 | 74 | 90002692 | A1 | 1000079881 | 21.08.2027 | 16000 | CLB-MP-LOAD-WL265 -TRNSYS-TRANS | 6000 | 65007 | 9745 | CLB-MP-LOAD-WL265 -TRNSYS-TRANS90002692
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Transmission | 2027-08-23 | 2027-08-25 | 62 hrs | FY28 | 122 | 90002631 | A1 | 1000028522 | 23.08.2027 | 14000 | CLB-MP-GRDR-GR018 -TRNSYS-TRANS | 6000 | 73365 | 7458 | CLB-MP-GRDR-GR018 -TRNSYS-TRANS90002631
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Pump Transmission | 2027-08-23 | 2027-08-23 | 10 hrs | FY28 | 20 | 90002633 | A1 | 1000028524 | 23.08.2027 | 14000 | CLB-MP-GRDR-GR018 -TRNSYS-TRPMP | 6000 | 73365 | 7458 | CLB-MP-GRDR-GR018 -TRNSYS-TRPMP90002633
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Transmission Charge Pump | 2027-08-25 | 2027-08-25 | 6 hrs | FY28 | 12 | 90002694 | A1 | 1000029188 | 25.08.2027 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-TRPMP | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Input Shaft Unis | 2027-08-25 | 2027-08-25 | 4 hrs | FY28 | 8 | 90033167 | A1 | 1000333612 | 25.08.2027 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT01 | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0190033167
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Brake Cooling | 2027-08-25 | 2027-08-25 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000029209 | 25.08.2027 | 10000 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP02 | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP0290002713
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Air Conditioner Service | 2027-08-25 | 2027-08-26 | 24 hrs | FY28 | 24 | 90017478 | A1 | 1000207979 | 25.08.2027 | 4000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN90017478
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Hyd Pump Cooling Fan | 2027-08-30 | 2027-08-30 | 8 hrs | FY28 | 16 | 90004952 | 1 | 1000069905 | 30.08.2027 | 18000 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYFPP | 4700 | 72846 | 12956 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYFPP90004952
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Cylinder Blade Lift LH | 2027-09-04 | 2027-09-04 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255566 | 04.09.2027 | 9000 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BLCYL | 4700 | 72846 | 3901 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BLCYL90000287
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Rear Differential | 2027-09-05 | 2027-09-07 | 62 hrs | FY28 | 122 | 90002952 | A1 | 1000033521 | 05.09.2027 | 15000 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF | 5900 | 79354 | 24532 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF90002952
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Pump Str Pilot & Str Cooling | 2027-09-05 | 2027-09-05 | 6 hrs | FY28 | 6 | 90002959 | A1 | 1000033531 | 05.09.2027 | 15000 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP02 | 5900 | 79354 | 8527 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP0290002959
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Overhaul Axle Oscillation Rear | 2027-09-05 | 2027-09-07 | 60 hrs | FY28 | 120 | 90002953 | A1 | 1000033522 | 05.09.2027 | 15000 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF-TRNON | 5900 | 79354 | 24532 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF-TRNON90002953
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hoses Powertrain System | 2027-09-05 | 2027-09-06 | 24 hrs | FY28 | 48 | 90013049 | A3 | 1000231965 | 05.09.2027 | 15000 | CLB-MP-DOZR-WD005 -TRNSYS-TRHLF | 5900 | 79354 | 79354 | CLB-MP-DOZR-WD005 -TRNSYS-TRHLF90013049
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Engine Midlife Complete | 2027-09-08 | 2027-09-11 | 71 hrs | FY28 | 103 | 90015859 | 1 | 1000159546 | 08.09.2027 | 9000 | CLB-MP-DOZR-DZ015 -ENGINE | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -ENGINE90015859
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Cylinder Blade Lift LH | 2027-09-08 | 2027-09-08 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255558 | 08.09.2027 | 9000 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BLCYL | 4700 | 72405 | 3716 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BLCYL90000287
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Major Service Air Conditioner | 2027-09-08 | 2027-09-09 | 24 hrs | FY28 | 24 | 90017469 | 1 | 1000160670 | 08.09.2027 | 9000 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN90017469
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Drive Shaft Unis | 2027-09-08 | 2027-09-08 | 3 hrs | FY28 | 6 | 90033292 | A1 | 1000334088 | 08.09.2027 | 9000 | CLB-MP-DOZR-DZ015 -TRNSYS | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -TRNSYS90033292
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Overhaul Park Brake & Centre Brg | 2027-09-20 | 2027-09-21 | 18 hrs | FY28 | 36 | 90002711 | A1 | 1000087670 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL028 -BRKSYS-BRPRK | 6000 | 80034 | 3017 | CLB-MP-LOAD-WL028 -BRKSYS-BRPRK90002711
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Brake System Hoses Midlife | 2027-09-20 | 2027-09-20 | 10.5 hrs | FY28 | 10.5 | 90026908 | A1 | 1000271593 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -BRKSYS-BRHLF-BRKHO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRHLF-BRKHO90026908
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Brake Cooling | 2027-09-20 | 2027-09-20 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000088572 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP0290002713
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Overhaul Park Brake & Centre Brg | 2027-09-20 | 2027-09-21 | 18 hrs | FY28 | 36 | 90002711 | A1 | 1000088602 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -BRKSYS-BRPRK | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -BRKSYS-BRPRK90002711
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Bucket LH High Lift | 2027-09-20 | 2027-09-21 | 18 hrs | FY28 | 36 | 90017978 | A1 | 1000131516 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYL | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYL90017978
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd System Hoses Midlife | 2027-09-20 | 2027-09-20 | 10.5 hrs | FY28 | 10.5 | 90026914 | A1 | 1000271595 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-HYDHO | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-HYDHO90026914
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Implement RH | 2027-09-20 | 2027-09-20 | 12 hrs | FY28 | 24 | 90002724 | A1 | 1000088583 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Implement Centre | 2027-09-20 | 2027-09-20 | 12 hrs | FY28 | 24 | 90002725 | A1 | 1000088584 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP03 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0390002725
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Input Shaft Unis | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90033167 | A1 | 1000333504 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT01 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0190033167
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Rear Output Drive Shaft Unis | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90033167 | A1 | 1000333506 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT02 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0290033167
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Ctr Output Drive Shaft Unis | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90033173 | A1 | 1000333508 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT03 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0390033173
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Front Drive Shaft Unis | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90033188 | A1 | 1000333510 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT04 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0490033188
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Rr PDrv Drive Shaft Ctr Brg | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90033193 | A1 | 1000333512 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT05 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0590033193
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Fr Pump Drv Shaft Unis | 2027-09-20 | 2027-09-20 | 4 hrs | FY28 | 8 | 90033190 | A1 | 1000333514 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT06 | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT0690033190
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Centre Bearing Upper Shaft | 2027-09-20 | 2027-09-20 | 12 hrs | FY28 | 24 | 90002702 | A1 | 1000088559 | 20.09.2027 | 10000 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-UCTRB | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-UCTRB90002702
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Engine Thermostats | 2027-09-22 | 2027-09-22 | 4 hrs | FY28 | 4 | 90019397 | A1 | 1000298545 | 22.09.2027 | 3500 | CLB-MP-GRDR-GR6504-ENGINE | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Minor Service Air Conditioner | 2027-09-22 | 2027-09-22 | 12 hrs | FY28 | 12 | 90019412 | A1 | 1000274248 | 22.09.2027 | 3500 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN90019412
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Steering Neutralizer Valves | 2027-09-23 | 2027-09-23 | 6 hrs | FY28 | 6 | 90002720 | A1 | 1000079923 | 23.09.2027 | 20000 | CLB-MP-LOAD-WL265 -STRSYS-STNVS | 6000 | 65007 | 33878 | CLB-MP-LOAD-WL265 -STRSYS-STNVS90002720
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Input Drive Shaft | 2027-09-23 | 2027-09-23 | 6 hrs | FY28 | 12 | 90033166 | A1 | 1000333635 | 23.09.2027 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT01 | 6000 | 65007 | 13203 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0190033166
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Cylinder Blade Lift RH | 2027-09-23 | 2027-09-23 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255559 | 23.09.2027 | 9000 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BLCYR | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BLCYR90000287
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Replace Artic Area Hyd Hosing | 2027-09-24 | 2027-09-24 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220500 | 24.09.2027 | 8 Monthly | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Final Drive Position 4 | 2027-09-25 | 2027-09-27 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000029076 | 25.09.2027 | 16000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR04 | 6000 | 78554 | 9173 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR0490002710
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Repl Engine Thermostats | 2027-10-03 | 2027-10-03 | 4 hrs | FY28 | 4 | 90019397 | A1 | 1000298546 | 03.10.2027 | 3500 | CLB-MP-GRDR-GR6501-ENGINE | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Minor Service Air Conditioner | 2027-10-03 | 2027-10-03 | 12 hrs | FY28 | 12 | 90019412 | A1 | 1000274568 | 03.10.2027 | 3500 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN90019412
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Bucket LH High Lift | 2027-10-04 | 2027-10-05 | 18 hrs | FY28 | 36 | 90017978 | A1 | 1000029095 | 04.10.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYL | 6000 | 78554 | 3032 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYL90017978
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Bucket RH High Lift | 2027-10-04 | 2027-10-05 | 18 hrs | FY28 | 36 | 90017977 | A1 | 1000029096 | 04.10.2027 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYR | 6000 | 78554 | 3032 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYR90017977
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Replace Operators Seat | 2027-10-04 | 2027-10-04 | 4 hrs | FY28 | 8 | 90000318 | 1 | 1000089361 | 04.10.2027 | 6000 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-SEATS | 4700 | 70238 | 522 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-SEATS90000318
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 T-Conv Trans Charge Pump Replace | 2027-10-06 | 2027-10-06 | 10 hrs | FY28 | 10 | 90037704 | A1 | 1000374092 | 06.10.2027 | 14000 | CLB-MP-DOZR-DZX025-TRNSYS-TRPMP | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-TRNSYS-TRPMP90037704
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Auto Lube Pump | 2027-10-09 | 2027-10-09 | 6 hrs | FY28 | 6 | 90002737 | A1 | 1000079853 | 09.10.2027 | 10000 | CLB-MP-LOAD-WL264 -GRSYST-ALBPP | 6000 | 67352 | 6205 | CLB-MP-LOAD-WL264 -GRSYST-ALBPP90002737
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Cylinder Blade Lift RH | 2027-10-11 | 2027-10-11 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255575 | 11.10.2027 | 9000 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYR | 4700 | 70238 | 3490 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYR90000287
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Hyd Pump Steering Main | 2027-10-12 | 2027-10-12 | 8 hrs | FY28 | 8 | 90002958 | A1 | 1000179063 | 12.10.2027 | 15000 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP01 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP0190002958
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Pump Str Pilot & Str Cooling | 2027-10-12 | 2027-10-12 | 6 hrs | FY28 | 6 | 90002959 | A1 | 1000179064 | 12.10.2027 | 15000 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP02 | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP0290002959
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Transmission | 2027-10-12 | 2027-10-14 | 57 hrs | FY28 | 167 | 90002944 | A2 | 1000179047 | 12.10.2027 | 15000 | CLB-MP-DOZR-WD6105-TRNSYS-TRANS | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-TRNSYS-TRANS90002944
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Transmission Oil Cooler | 2027-10-12 | 2027-10-12 | 12 hrs | FY28 | 12 | 90002945 | A1 | 1000179084 | 12.10.2027 | 15000 | CLB-MP-DOZR-WD6105-TRNSYS-TROLC | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-TRNSYS-TROLC90002945
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Pump Transmission | 2027-10-12 | 2027-10-12 | 8 hrs | FY28 | 8 | 90002946 | A1 | 1000179048 | 12.10.2027 | 15000 | CLB-MP-DOZR-WD6105-TRNSYS-TRPMP | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-TRNSYS-TRPMP90002946
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Operators Seat | 2027-10-13 | 2027-10-13 | 4 hrs | FY28 | 4 | 90002741 | A1 | 1000029102 | 13.10.2027 | 7000 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS | 6000 | 78554 | 6878 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS90002741
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Engine Midlife complete | 2027-10-17 | 2027-10-22 | 132 hrs | FY28 | 170 | 90021253 | 1 | 1000222419 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -ENGINE | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ENGINE90021253
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Transmission Charge Pump | 2027-10-17 | 2027-10-17 | 6 hrs | FY28 | 12 | 90002694 | A1 | 1000028992 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-TRPMP | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Rear Output Drive Shaft Unis | 2027-10-17 | 2027-10-17 | 4 hrs | FY28 | 8 | 90033167 | A1 | 1000333578 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT02 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0290033167
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Rr PDrv Drive Shaft Ctr Brg | 2027-10-17 | 2027-10-17 | 4 hrs | FY28 | 8 | 90033193 | A1 | 1000333584 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT05 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0590033193
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Overhaul Park Brake & Centre Brg | 2027-10-17 | 2027-10-18 | 18 hrs | FY28 | 36 | 90002711 | A1 | 1000087667 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -BRKSYS-BRPRK | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -BRKSYS-BRPRK90002711
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Implement RH | 2027-10-17 | 2027-10-17 | 12 hrs | FY28 | 24 | 90002724 | A1 | 1000029025 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP02 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Implement Centre | 2027-10-17 | 2027-10-17 | 12 hrs | FY28 | 24 | 90002725 | A1 | 1000029026 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP03 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0390002725
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Pilot & Cooling | 2027-10-17 | 2027-10-17 | 6 hrs | FY28 | 12 | 90002726 | A1 | 1000029027 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP04 | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0490002726
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Lift RH High Lift | 2027-10-17 | 2027-10-18 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000029029 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLR | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLR90002727
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Bucket LH High Lift | 2027-10-17 | 2027-10-18 | 18 hrs | FY28 | 36 | 90017978 | A1 | 1000029030 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYL | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYL90017978
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Bucket RH High Lift | 2027-10-17 | 2027-10-18 | 18 hrs | FY28 | 36 | 90017977 | A1 | 1000029031 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYR | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYR90017977
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Overhaul Air Conditioner | 2027-10-17 | 2027-10-19 | 48 hrs | FY28 | 48 | 90021132 | 1 | 1000222411 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN90021132
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Brake System Hoses Midlife | 2027-10-17 | 2027-10-17 | 10.5 hrs | FY28 | 10.5 | 90026908 | A1 | 1000271622 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -BRKSYS-BRHLF-BRKHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -BRKSYS-BRHLF-BRKHO90026908
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd System Hoses Midlife | 2027-10-17 | 2027-10-17 | 10.5 hrs | FY28 | 10.5 | 90026914 | A1 | 1000271624 | 17.10.2027 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-HYDHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-HYDHO90026914
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Aftercooler Engine | 2027-10-18 | 2027-10-18 | 8 hrs | FY28 | 8 | 90010841 | 1 | 1000089374 | 18.10.2027 | 18000 | CLB-MP-DOZR-DZ015 -ENGINE-INTEX-AFTER | 4700 | 72405 | 12392 | CLB-MP-DOZR-DZ015 -ENGINE-INTEX-AFTER90010841
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Engine Midlife complete | 2027-10-20 | 2027-10-22 | 60 hrs | FY28 | 72 | 90015782 | 1 | 1000159886 | 20.10.2027 | 7000 | CLB-MP-GRDR-GR018 -ENGINE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE90015782
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Drive Shaft Trans to Rr Diff | 2027-10-20 | 2027-10-20 | 3 hrs | FY28 | 6 | 90033262 | A1 | 1000333924 | 20.10.2027 | 14000 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT01 | 6000 | 73365 | 3877 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT0190033262
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Service Major Air Conditioner | 2027-10-20 | 2027-10-21 | 24 hrs | FY28 | 24 | 90017472 | 1 | 1000160702 | 20.10.2027 | 7000 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN90017472
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Front Axle Assembly Midlife | 2027-10-20 | 2027-10-21 | 38 hrs | FY28 | 44 | 90025907 | A1 | 1000255898 | 20.10.2027 | 7000 | CLB-MP-GRDR-GR018 -STRUCT-AXLES | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-AXLES90025907
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Repl Engine Thermostats | 2027-10-20 | 2027-10-20 | 4 hrs | FY28 | 4 | 90019397 | A1 | 1000298547 | 20.10.2027 | 3500 | CLB-MP-GRDR-GR6505-ENGINE | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Minor Service Air Conditioner | 2027-10-20 | 2027-10-20 | 12 hrs | FY28 | 12 | 90019412 | A1 | 1000274654 | 20.10.2027 | 3500 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN90019412
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Clean Engine Pre Cleaners | 2027-10-22 | 2027-10-22 | 1 hr | FY28 | 1 | 90029028 | A1 | 1000289950 | 22.10.2027 | 5500 | CLB-MP-DOZR-WD005 -ENGINE | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -ENGINE90029028
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Service Airconditioner | 2027-10-22 | 2027-10-23 | 24 hrs | FY28 | 24 | 90029025 | A1 | 1000289948 | 22.10.2027 | 5500 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN90029025
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Final Drive LH | 2027-10-28 | 2027-10-29 | 22 hrs | FY28 | 44 | 90003346 | 1 | 1000037951 | 28.10.2027 | 14000 | CLB-MP-DOZR-DZX022-FDRSYS-FDRLH | 4400 | 63346 | 8101 | CLB-MP-DOZR-DZX022-FDRSYS-FDRLH90003346
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Torque Converter | 2027-11-01 | 2027-11-02 | 24 hrs | FY28 | 48 | 90002693 | A1 | 1000028990 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-TRQUE | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-TRQUE90002693
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Transmission Oil Cooler | 2027-11-01 | 2027-11-02 | 18 hrs | FY28 | 36 | 90002695 | A1 | 1000028993 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-TROLC | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-TROLC90002695
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Front Drive Shaft | 2027-11-01 | 2027-11-01 | 8 hrs | FY28 | 16 | 90033175 | A1 | 1000333581 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT04 | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0490033175
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Reseal Brake Accumulator Front | 2027-11-01 | 2027-11-01 | 12 hrs | FY28 | 12 | 90002714 | A1 | 1000214433 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC-BACCF | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC-BACCF90002714
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Reseal Brake Accumulator Rear | 2027-11-01 | 2027-11-01 | 12 hrs | FY28 | 12 | 90002714 | A1 | 1000089007 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC-BACCR | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC-BACCR90002714
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Steer & Brake Oil Cooler Pump | 2027-11-01 | 2027-11-01 | 8 hrs | FY28 | 8 | 90002718 | A1 | 1000029019 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP03 | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP0390002718
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Steering Hyd Pump Secondary | 2027-11-01 | 2027-11-01 | 8 hrs | FY28 | 8 | 90002719 | A1 | 1000029020 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP04 | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP0490002719
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Steering Neutralizer Valves | 2027-11-01 | 2027-11-01 | 6 hrs | FY28 | 6 | 90002720 | A1 | 1000076054 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STNVS | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -STRSYS-STNVS90002720
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Pilot System Hoses | 2027-11-01 | 2027-11-03 | 48 hrs | FY28 | 96 | 90009731 | 1 | 1000076477 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-PILHO | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-PILHO90009731
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Replace Steering System Hoses | 2027-11-01 | 2027-11-03 | 48 hrs | FY28 | 96 | 90009732 | 1 | 1000076478 | 01.11.2027 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STHLF-STRHO | 6000 | 64740 | 23337 | CLB-MP-LOAD-WL025 -STRSYS-STHLF-STRHO90009732
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Brake Assy LHF | 2027-11-01 | 2027-11-02 | 18 hrs | FY28 | 36 | 90002455 | A1 | 1000090995 | 01.11.2027 | 8000 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBLF | 4000 | 51804 | 2872 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBLF90002455
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Brake Assy LHR | 2027-11-01 | 2027-11-02 | 18 hrs | FY28 | 36 | 90002456 | A1 | 1000090997 | 01.11.2027 | 8000 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBLR | 4000 | 51804 | 2872 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBLR90002456
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Brake Assy RHR | 2027-11-01 | 2027-11-02 | 18 hrs | FY28 | 36 | 90002456 | A1 | 1000090998 | 01.11.2027 | 8000 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRR | 4000 | 51804 | 2872 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRR90002456
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Adjust Engine 500hr Valve Set | 2027-11-02 | 2027-11-02 | 12 hrs | FY28 | 24 | 90015857 | 1 | 1000159580 | 02.11.2027 | 500 | CLB-MP-DOZR-DZ018 -ENGINE | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -ENGINE90015857
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Steer Clutch & Brake Assm LH | 2027-11-05 | 2027-11-05 | 16 hrs | FY28 | 32 | 90018830 | A1 | 1000189064 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-BRKSTR-SCABL | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-BRKSTR-SCABL90018830
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Steer Clutch & Brake Assm RH | 2027-11-05 | 2027-11-05 | 16 hrs | FY28 | 32 | 90018830 | A1 | 1000189065 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-BRKSTR-SCABR | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-BRKSTR-SCABR90018830
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Aftercooler Engine | 2027-11-05 | 2027-11-05 | 8 hrs | FY28 | 8 | 90018836 | A1 | 1000189071 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AFTER | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AFTER90018836
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Reseal Hydraulic Tank | 2027-11-05 | 2027-11-06 | 24 hrs | FY28 | 48 | 90018838 | A1 | 1000189073 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-HYDSYS-HDTNK | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-HYDSYS-HDTNK90018838
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Hyd Pump Cooling Fan | 2027-11-05 | 2027-11-05 | 8 hrs | FY28 | 16 | 90018832 | A1 | 1000189067 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYFPP | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYFPP90018832
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Pump Hyd Implement 1 | 2027-11-05 | 2027-11-05 | 10 hrs | FY28 | 10 | 90018831 | A1 | 1000189066 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYIP1 | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYIP190018831
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Track Frame LH | 2027-11-05 | 2027-11-07 | 46 hrs | FY28 | 90 | 90033095 | A1 | 1000331944 | 05.11.2027 | 36000 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-TKFRL | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-TKFRL90033095
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Track Frame RH | 2027-11-05 | 2027-11-07 | 46 hrs | FY28 | 90 | 90033096 | A1 | 1000331946 | 05.11.2027 | 36000 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-TKFRR | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-TKFRR90033096
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Transmission | 2027-11-05 | 2027-11-06 | 24 hrs | FY28 | 48 | 90018827 | A1 | 1000189060 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-TRNSYS-TRANS | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-TRNSYS-TRANS90018827
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Torque Converter | 2027-11-05 | 2027-11-06 | 30 hrs | FY28 | 60 | 90018826 | A1 | 1000189019 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-TRNSYS-TRQUE | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-TRNSYS-TRQUE90018826
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Drive Shaft | 2027-11-05 | 2027-11-05 | 3 hrs | FY28 | 6 | 90033311 | A1 | 1000334032 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-TRNSYS-DRSHT | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-TRNSYS-DRSHT90033311
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Pump Hyd Variable Charge | 2027-11-05 | 2027-11-05 | 4 hrs | FY28 | 4 | 90021620 | A1 | 1000226700 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYDVC | 4800 | 25166 | 12059 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYDVC90021620
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Pump Hyd Implement 2 | 2027-11-05 | 2027-11-05 | 6 hrs | FY28 | 6 | 90021621 | A1 | 1000226710 | 05.11.2027 | 18000 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYIP2 | 4800 | 25166 | 12059 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYIP290021621
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8223 | DZ8223 Adjust Engine 500hr Valve Set | 2027-11-06 | 2027-11-06 | 12 hrs | FY28 | 24 | 90018851 | A1 | 1000189136 | 06.11.2027 | 500 | CLB-MP-DOZR-DZ8223-ENGINE | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-ENGINE90018851
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Repl Brake Assy LHR | 2027-11-08 | 2027-11-09 | 20 hrs | FY28 | 40 | 90019370 | A1 | 1000274535 | 08.11.2027 | 14000 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBLR | 5500 | 19670 | 7059 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBLR90019370
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Auto Lube Pump | 2027-11-11 | 2027-11-11 | 6 hrs | FY28 | 6 | 90002737 | A1 | 1000029231 | 11.11.2027 | 10000 | CLB-MP-LOAD-WL028 -GRSYST-ALBPP | 6000 | 80034 | 2183 | CLB-MP-LOAD-WL028 -GRSYST-ALBPP90002737
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Brake Oil Cooler | 2027-11-12 | 2027-11-13 | 36 hrs | FY28 | 72 | 90002715 | A1 | 1000090018 | 12.11.2027 | 20000 | CLB-MP-LOAD-WL264 -BRKSYS-BROCC | 6000 | 67352 | 31688 | CLB-MP-LOAD-WL264 -BRKSYS-BROCC90002715
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Steering STIC Pilot Valve | 2027-11-12 | 2027-11-12 | 12 hrs | FY28 | 12 | 90026110 | A1 | 1000257372 | 12.11.2027 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STIPV | 6000 | 67352 | 33615 | CLB-MP-LOAD-WL264 -STRSYS-STIPV90026110
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Steering Neutralizer Valves | 2027-11-12 | 2027-11-12 | 6 hrs | FY28 | 6 | 90002720 | A1 | 1000079857 | 12.11.2027 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STNVS | 6000 | 67352 | 33911 | CLB-MP-LOAD-WL264 -STRSYS-STNVS90002720
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Input Drive Shaft | 2027-11-12 | 2027-11-12 | 6 hrs | FY28 | 12 | 90033166 | A1 | 1000333623 | 12.11.2027 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT01 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0190033166
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Steering LH | 2027-11-16 | 2027-11-16 | 10 hrs | FY28 | 18 | 90002721 | A1 | 1000088580 | 16.11.2027 | 12000 | CLB-MP-LOAD-WL263 -STRSYS-STRCY-STCYL | 6000 | 60624 | 4273 | CLB-MP-LOAD-WL263 -STRSYS-STRCY-STCYL90002721
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Thermostats | 2027-11-16 | 2027-11-16 | 6 hrs | FY28 | 6 | 90021139 | 1 | 1000222444 | 16.11.2027 | 5000 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-THERM | 6000 | 78554 | 7319 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Service Air Conditioner | 2027-11-16 | 2027-11-17 | 24 hrs | FY28 | 24 | 90021130 | 1 | 1000222434 | 16.11.2027 | 5000 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN | 6000 | 78554 | 16795 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN90021130
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Reseal Brake Accumulator Front | 2027-11-18 | 2027-11-18 | 12 hrs | FY28 | 12 | 90002714 | A1 | 1000257286 | 18.11.2027 | 20000 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC-BACCF | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC-BACCF90002714
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Brake | 2027-11-18 | 2027-11-18 | 12 hrs | FY28 | 12 | 90002712 | A1 | 1000079837 | 18.11.2027 | 20000 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP01 | 6000 | 67352 | 4805 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP0190002712
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Implement RH | 2027-11-18 | 2027-11-18 | 12 hrs | FY28 | 24 | 90002724 | A1 | 1000079847 | 18.11.2027 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP02 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Implement Centre | 2027-11-18 | 2027-11-18 | 12 hrs | FY28 | 24 | 90002725 | A1 | 1000079848 | 18.11.2027 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP03 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0390002725
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Reseal Brake Accumulator Rear | 2027-11-18 | 2027-11-18 | 12 hrs | FY28 | 12 | 90002714 | A1 | 1000257809 | 18.11.2027 | 20000 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC-BACCR | 6000 | 67351 | 12287 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC-BACCR90002714
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Hyd Pump Secondary Steering | 2027-11-19 | 2027-11-19 | 6 hrs | FY28 | 6 | 90002459 | A1 | 1000027545 | 19.11.2027 | 7000 | CLB-MP-GRDR-GR017 -STRSYS-STEMG-SESPP | 4000 | 54668 | 1845 | CLB-MP-GRDR-GR017 -STRSYS-STEMG-SESPP90002459
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Front Axle Assembly Midlife | 2027-11-20 | 2027-11-21 | 32 hrs | FY28 | 62 | 90026004 | A1 | 1000256563 | 20.11.2027 | 7000 | CLB-MP-GRDR-GR017 -STRUCT-AXLES | 4000 | 54668 | 1838 | CLB-MP-GRDR-GR017 -STRUCT-AXLES90026004
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Service Airconditioner | 2027-11-21 | 2027-11-22 | 24 hrs | FY28 | 24 | 90003915 | A2 | 1000189977 | 21.11.2027 | 5500 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-AIRCN | 5900 | 30649 | 8882 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-AIRCN90003915
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Final Drive Position 2 | 2027-11-22 | 2027-11-24 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000079834 | 22.11.2027 | 16000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR02 | 6000 | 67352 | 8109 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR0290002710
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Hyd Motor Fan Hyd Cooler | 2027-11-22 | 2027-11-22 | 8 hrs | FY28 | 8 | 90019377 | A1 | 1000274216 | 22.11.2027 | 14000 | CLB-MP-GRDR-GR6504-HYDSYS-HDMOT-MOFAN | 5500 | 19712 | 6868 | CLB-MP-GRDR-GR6504-HYDSYS-HDMOT-MOFAN90019377
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Operators Seat | 2027-11-24 | 2027-11-24 | 4 hrs | FY28 | 8 | 90018835 | A1 | 1000189070 | 24.11.2027 | 6000 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS | 4800 | 25244 | 5824 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS90018835
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Drive Shaft Centre Bearing | 2027-11-25 | 2027-11-25 | 6 hrs | FY28 | 12 | 90021473 | A1 | 1000207959 | 25.11.2027 | 16000 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-CTRBR | 5000 | 21377 | 9436 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-CTRBR90021473
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Hyd Pump Secondary Steering | 2027-11-27 | 2027-11-27 | 6 hrs | FY28 | 6 | 90002459 | A1 | 1000091002 | 27.11.2027 | 7000 | CLB-MP-GRDR-GR102 -STRSYS-STEMG-SESPP | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRSYS-STEMG-SESPP90002459
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Hyd Pump Implement | 2027-11-27 | 2027-11-27 | 12 hrs | FY28 | 12 | 90003349 | 1 | 1000037956 | 27.11.2027 | 14000 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYIPP | 4400 | 63346 | 7741 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYIPP90003349
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Axle Assembly Front | 2027-11-28 | 2027-11-29 | 24 hrs | FY28 | 48 | 90026002 | A1 | 1000256256 | 28.11.2027 | 14000 | CLB-MP-GRDR-GR102 -STRUCT-AXLES | 4000 | 51804 | 1584 | CLB-MP-GRDR-GR102 -STRUCT-AXLES90026002
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Drive Shaft Trans to Rr Diff | 2027-12-01 | 2027-12-01 | 3 hrs | FY28 | 6 | 90033262 | A1 | 1000333920 | 01.12.2027 | 14000 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT01 | 6000 | 71626 | 5974 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT0190033262
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Drive Shaft TCon to Trans | 2027-12-01 | 2027-12-01 | 4 hrs | FY28 | 4 | 90033265 | A1 | 1000333922 | 01.12.2027 | 14000 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT02 | 6000 | 71626 | 5974 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT0290033265
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Front Axle Assembly Midlife | 2027-12-01 | 2027-12-02 | 38 hrs | FY28 | 44 | 90025907 | A1 | 1000255897 | 01.12.2027 | 7000 | CLB-MP-GRDR-GR013 -STRUCT-AXLES | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-AXLES90025907
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Pump Brake & Hyd Fan | 2027-12-03 | 2027-12-03 | 6 hrs | FY28 | 6 | 90019371 | A1 | 1000274206 | 03.12.2027 | 14000 | CLB-MP-GRDR-GR6504-BRKSYS-BRPMP | 5500 | 19712 | 19712 | CLB-MP-GRDR-GR6504-BRKSYS-BRPMP90019371
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Pilot & Cooling | 2027-12-04 | 2027-12-04 | 6 hrs | FY28 | 12 | 90002726 | A1 | 1000029157 | 04.12.2027 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP04 | 6000 | 81297 | 2179 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0490002726
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Gearbox Circle Drive | 2027-12-05 | 2027-12-05 | 8 hrs | FY28 | 14 | 90019382 | A1 | 1000274212 | 05.12.2027 | 14000 | CLB-MP-GRDR-GR6504-STRUCT-CIRCL-CDRBX | 5500 | 19712 | 6665 | CLB-MP-GRDR-GR6504-STRUCT-CIRCL-CDRBX90019382
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Brake System Hoses Midlife | 2027-12-08 | 2027-12-08 | 10.5 hrs | FY28 | 10.5 | 90026908 | A1 | 1000271652 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -BRKSYS-BRHLF-BRKHO | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -BRKSYS-BRHLF-BRKHO90026908
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Brake Cooling | 2027-12-08 | 2027-12-08 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000112355 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP-BRP02 | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP-BRP0290002713
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Overhaul Park Brake & Centre Brg | 2027-12-08 | 2027-12-09 | 18 hrs | FY28 | 36 | 90002711 | A1 | 1000087672 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -BRKSYS-BRPRK | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -BRKSYS-BRPRK90002711
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Engine Midlife complete | 2027-12-08 | 2027-12-13 | 132 hrs | FY28 | 170 | 90021253 | 1 | 1000222596 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -ENGINE | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -ENGINE90021253
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Auto Lube Pump | 2027-12-08 | 2027-12-08 | 6 hrs | FY28 | 6 | 90002737 | A1 | 1000116282 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -GRSYST-ALBPP | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -GRSYST-ALBPP90002737
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd System Hoses Midlife | 2027-12-08 | 2027-12-08 | 10.5 hrs | FY28 | 10.5 | 90026914 | A1 | 1000271654 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-HYDHO | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-HYDHO90026914
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Implement RH | 2027-12-08 | 2027-12-08 | 12 hrs | FY28 | 24 | 90002724 | A1 | 1000079913 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP02 | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Pilot & Cooling | 2027-12-08 | 2027-12-08 | 6 hrs | FY28 | 12 | 90002726 | A1 | 1000079915 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP04 | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP0490002726
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Overhaul Air Conditioner | 2027-12-08 | 2027-12-10 | 48 hrs | FY28 | 48 | 90021132 | 1 | 1000222587 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN90021132
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Centre Bearing Upper Shaft | 2027-12-08 | 2027-12-08 | 12 hrs | FY28 | 24 | 90002702 | A1 | 1000079890 | 08.12.2027 | 10000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-UCTRB | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-UCTRB90002702
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Replace STIC Steering Valve | 2027-12-14 | 2027-12-14 | 12 hrs | FY28 | 12 | 90026110 | A1 | 1000029021 | 14.12.2027 | 20000 | CLB-MP-LOAD-WL025 -STRSYS-STIPV | 6000 | 64740 | 51755 | CLB-MP-LOAD-WL025 -STRSYS-STIPV90026110
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Operators Seat | 2027-12-14 | 2027-12-14 | 4 hrs | FY28 | 4 | 90002741 | A1 | 1000029167 | 14.12.2027 | 7000 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS | 6000 | 81297 | 6005 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS90002741
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Service Minor Air Conditioner | 2027-12-17 | 2027-12-17 | 6 hrs | FY28 | 6 | 90018856 | A1 | 1000189092 | 17.12.2027 | 4500 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN90018856
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Hyd Motor Fan Hyd Cooler | 2027-12-19 | 2027-12-19 | 8 hrs | FY28 | 16 | 90002464 | A1 | 1000027550 | 19.12.2027 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDMOT-MOFAN | 4000 | 54668 | 8517 | CLB-MP-GRDR-GR017 -HYDSYS-HDMOT-MOFAN90002464
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Refurbish Cabin | 2027-12-24 | 2027-12-25 | 18 hrs | FY28 | 18 | 90010844 | 1 | 1000089426 | 24.12.2027 | 36000 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN | 4700 | 72325 | 16426 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN90010844
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Adjust Engine 500hr Valve Set | 2027-12-25 | 2027-12-25 | 12 hrs | FY28 | 24 | 90018851 | A1 | 1000189185 | 25.12.2027 | 500 | CLB-MP-DOZR-DZ8224-ENGINE | 4800 | 26987 | 11824 | CLB-MP-DOZR-DZ8224-ENGINE90018851
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Implement LH | 2027-12-26 | 2027-12-26 | 12 hrs | FY28 | 24 | 90002723 | A1 | 1000079846 | 26.12.2027 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP01 | 6000 | 67352 | 1556 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Centre Bearing Upper Shaft | 2027-12-26 | 2027-12-26 | 12 hrs | FY28 | 24 | 90002702 | A1 | 1000079825 | 26.12.2027 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-UCTRB | 6000 | 67352 | 14859 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-UCTRB90002702
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Gearbox Circle Drive Front | 2027-12-26 | 2027-12-26 | 8 hrs | FY28 | 14 | 90002672 | A1 | 1000028506 | 26.12.2027 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-CDBXF | 6000 | 71626 | 5572 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-CDBXF90002672
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Brake Assy LHF | 2027-12-29 | 2027-12-30 | 18 hrs | FY28 | 36 | 90002455 | A1 | 1000027538 | 29.12.2027 | 8000 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBLF | 4000 | 54668 | 2410 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBLF90002455
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Brake Assy LHR | 2027-12-29 | 2027-12-30 | 18 hrs | FY28 | 36 | 90002456 | A1 | 1000027540 | 29.12.2027 | 8000 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBLR | 4000 | 54668 | 2410 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBLR90002456
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Steer Clutch & Brake Assm RH | 2027-12-31 | 2027-12-31 | 16 hrs | FY28 | 32 | 90018830 | A1 | 1000202313 | 31.12.2027 | 18000 | CLB-MP-DOZR-DZ8225-BRKSTR-SCABR | 4800 | 24542 | 11230 | CLB-MP-DOZR-DZ8225-BRKSTR-SCABR90018830
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Engine Midlife Complete | 2027-12-31 | 2028-01-03 | 71 hrs | FY28 | 103 | 90015859 | 1 | 1000159522 | 31.12.2027 | 9000 | CLB-MP-DOZR-DZ013 -ENGINE | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -ENGINE90015859
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Fan Cooling Motor Hyd | 2027-12-31 | 2027-12-31 | 8 hrs | FY28 | 16 | 90002094 | 1 | 1000069922 | 31.12.2027 | 9000 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCFM | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCFM90002094
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Cylinder Blade Lift RH | 2027-12-31 | 2027-12-31 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255543 | 31.12.2027 | 9000 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BLCYR | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BLCYR90000287
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Major Service Air Conditioner | 2027-12-31 | 2028-01-01 | 24 hrs | FY28 | 24 | 90017469 | 1 | 1000160668 | 31.12.2027 | 9000 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN90017469
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Drive Shaft Unis | 2027-12-31 | 2027-12-31 | 3 hrs | FY28 | 6 | 90033292 | A1 | 1000334084 | 31.12.2027 | 9000 | CLB-MP-DOZR-DZ013 -TRNSYS | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -TRNSYS90033292
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Operators Seat | 2028-01-04 | 2028-01-04 | 2 hrs | FY28 | 4 | 90002975 | A2 | 1000190021 | 04.01.2028 | 7000 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS | 5900 | 30649 | 5594 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS90002975
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Engine Cat 3516B | 2028-01-05 | 2028-01-16 | 272 hrs | FY28 | 500 | 90021152 | 1 | 1000222479 | 05.01.2028 | 20000 | CLB-MP-LOAD-WL028 -ENGINE | 6000 | 80034 | 11272 | CLB-MP-LOAD-WL028 -ENGINE90021152
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Overhaul Engine Prelube | 2028-01-05 | 2028-01-05 | 10 hrs | FY28 | 10 | 90021219 | 1 | 1000222487 | 05.01.2028 | 20000 | CLB-MP-LOAD-WL028 -ENGINE-LUBSY-PREPP | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -ENGINE-LUBSY-PREPP90021219
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Overhaul Air Conditioner | 2028-01-05 | 2028-01-07 | 48 hrs | FY28 | 48 | 90021132 | 1 | 1000222477 | 05.01.2028 | 10000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN90021132
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Minor Service Air Conditioner | 2028-01-05 | 2028-01-05 | 6 hrs | FY28 | 6 | 90017699 | 1 | 1000162396 | 05.01.2028 | 4500 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-AIRCN | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Steering Hyd Pump Secondary | 2028-01-06 | 2028-01-06 | 8 hrs | FY28 | 8 | 90002719 | A1 | 1000079843 | 06.01.2028 | 20000 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP04 | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP0490002719
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Operators Seat | 2028-01-09 | 2028-01-09 | 4 hrs | FY28 | 4 | 90002741 | A1 | 1000103784 | 09.01.2028 | 7000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS | 6000 | 67352 | 5323 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS90002741
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Replace Shaft Trans to Rear Diff | 2028-01-09 | 2028-01-09 | 6 hrs | FY28 | 6 | 90002948 | A1 | 1000268504 | 09.01.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT02 | 5900 | 55835 | 13525 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT0290002948
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Shaft Trans to Cntr Bearing | 2028-01-09 | 2028-01-09 | 6 hrs | FY28 | 12 | 90002949 | A1 | 1000268506 | 09.01.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT03 | 5900 | 55835 | 13525 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT0390002949
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Shaft Centre Brg to Fr Diff | 2028-01-09 | 2028-01-09 | 8 hrs | FY28 | 16 | 90002950 | A1 | 1000268508 | 09.01.2028 | 22000 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT04 | 5900 | 55835 | 13525 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT0490002950
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Lift LH High Lift | 2028-01-10 | 2028-01-11 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000029028 | 10.01.2028 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLL | 6000 | 64588 | 1336 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLL90002727
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Cylinder Blade Lift RH | 2028-01-10 | 2028-01-10 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255583 | 10.01.2028 | 9000 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BLCYR | 4700 | 66933 | 4145 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BLCYR90000287
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Brake Cooling | 2028-01-12 | 2028-01-12 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000029143 | 12.01.2028 | 10000 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP02 | 6000 | 81297 | 11532 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP0290002713
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Bucket LH High Lift | 2028-01-12 | 2028-01-13 | 18 hrs | FY28 | 36 | 90017978 | A1 | 1000029160 | 12.01.2028 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYL | 6000 | 81297 | 11532 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYL90017978
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Clean Engine Pre Cleaners | 2028-01-13 | 2028-01-13 | 6 hrs | FY28 | 6 | 90015808 | 1 | 1000179040 | 13.01.2028 | 5500 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL90015808
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Service Airconditioner | 2028-01-13 | 2028-01-14 | 24 hrs | FY28 | 24 | 90003915 | 2 | 1000195982 | 13.01.2028 | 5500 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN | 5900 | 55835 | 7966 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN90003915
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Final Drive Position 2 | 2028-01-15 | 2028-01-17 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000079899 | 15.01.2028 | 16000 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR02 | 6000 | 65007 | 7321 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR0290002710
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Adjust 250hr Initial Valve Set | 2028-01-20 | 2028-01-20 | 12 hrs | FY28 | 24 | 90021246 | 1 | 1000222474 | 20.01.2028 | 250 | CLB-MP-LOAD-WL028 -ENGINE | 6000 | 80034 | 11272 | CLB-MP-LOAD-WL028 -ENGINE90021246
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Steering RH | 2028-01-20 | 2028-01-20 | 10 hrs | FY28 | 20 | 90002722 | A1 | 1000088581 | 20.01.2028 | 12000 | CLB-MP-LOAD-WL263 -STRSYS-STRCY-STCYR | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRSYS-STRCY-STCYR90002722
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Front Drive Shaft | 2028-01-23 | 2028-01-23 | 8 hrs | FY28 | 16 | 90033175 | A1 | 1000333641 | 23.01.2028 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT04 | 6000 | 65007 | 11195 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0490033175
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Shaft Rear PD To Cntr Brng | 2028-01-23 | 2028-01-23 | 12 hrs | FY28 | 24 | 90033191 | A1 | 1000333643 | 23.01.2028 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT05 | 6000 | 65007 | 11195 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0590033191
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Front Pump Drv Drive Shaft | 2028-01-23 | 2028-01-23 | 8 hrs | FY28 | 16 | 90033189 | A1 | 1000333645 | 23.01.2028 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT06 | 6000 | 65007 | 11195 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0690033189
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Transmission | 2028-01-25 | 2028-01-29 | 98 hrs | FY28 | 194 | 90002944 | A1 | 1000033513 | 25.01.2028 | 15000 | CLB-MP-DOZR-WD005 -TRNSYS-TRANS | 5900 | 79354 | 6234 | CLB-MP-DOZR-WD005 -TRNSYS-TRANS90002944
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Operators Seat | 2028-01-25 | 2028-01-25 | 4 hrs | FY28 | 8 | 90018835 | A1 | 1000202318 | 25.01.2028 | 6000 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS | 4800 | 24525 | 4908 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS90018835
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Fan Cooling Motor Hyd | 2028-01-27 | 2028-01-27 | 8 hrs | FY28 | 16 | 90002094 | 1 | 1000069921 | 27.01.2028 | 9000 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCFM | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCFM90002094
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Cylinder Blade Lift LH | 2028-01-27 | 2028-01-27 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255514 | 27.01.2028 | 9000 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BLCYL | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BLCYL90000287
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Cylinder Blade Lift RH | 2028-01-27 | 2028-01-27 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255515 | 27.01.2028 | 9000 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BLCYR | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BLCYR90000287
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Hyd Pump Implement | 2028-01-27 | 2028-01-27 | 10 hrs | FY28 | 10 | 90000301 | 1 | 1000017706 | 27.01.2028 | 9000 | CLB-MP-DOZR-DZ012 -HYDSYS-HYDPP-HYIPP | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -HYDSYS-HYDPP-HYIPP90000301
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Pump Transmission | 2028-01-30 | 2028-01-30 | 8 hrs | FY28 | 8 | 90002946 | A1 | 1000033515 | 30.01.2028 | 15000 | CLB-MP-DOZR-WD005 -TRNSYS-TRPMP | 5900 | 79354 | 6159 | CLB-MP-DOZR-WD005 -TRNSYS-TRPMP90002946
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Transmission Oil Cooler | 2028-01-31 | 2028-01-31 | 12 hrs | FY28 | 12 | 90002945 | A1 | 1000033514 | 31.01.2028 | 15000 | CLB-MP-DOZR-WD005 -TRNSYS-TROLC | 5900 | 79354 | 6148 | CLB-MP-DOZR-WD005 -TRNSYS-TROLC90002945
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Pump Implement | 2028-01-31 | 2028-01-31 | 8 hrs | FY28 | 8 | 90002962 | A1 | 1000033535 | 31.01.2028 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP01 | 5900 | 79354 | 6148 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP0190002962
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Cylinder Blade Lift LH | 2028-02-04 | 2028-02-04 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255506 | 04.02.2028 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYL | 4700 | 70636 | 2182 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYL90000287
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Replace Artic Area Hyd Hosing | 2028-02-05 | 2028-02-05 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220519 | 05.02.2028 | 8 Monthly | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Front Pump Drv Drive Shaft | 2028-02-05 | 2028-02-05 | 8 hrs | FY28 | 16 | 90033189 | A1 | 1000333609 | 05.02.2028 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT06 | 6000 | 81297 | 11142 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0690033189
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Valve Implement Ctrl RH | 2028-02-06 | 2028-02-07 | 24 hrs | FY28 | 24 | 90010966 | 1 | 1000090192 | 06.02.2028 | 20000 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV-HYV02 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV-HYV0290010966
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 12M Inspection Isolator Panel | 2028-02-06 | 2028-02-06 | 2 hrs | FY28 | 2 | 90022525 | A2 | 1000236558 | 06.02.2028 | 12 Monthly | CLB-MP-LOAD-WL263 -ELCTLV | 6000 | 60721 | 60721 | CLB-MP-LOAD-WL263 -ELCTLV90022525
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Bucket LH Lift | 2028-02-07 | 2028-02-08 | 18 hrs | FY28 | 36 | 90017161 | 1 | 1000154740 | 07.02.2028 | 11000 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-BUCYL | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-BUCYL90017161
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Lift LH Lift | 2028-02-07 | 2028-02-08 | 20 hrs | FY28 | 40 | 90017160 | A1 | 1000154742 | 07.02.2028 | 11000 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-HCYLL | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-HCYLL90017160
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Lift RH Lift | 2028-02-07 | 2028-02-08 | 20 hrs | FY28 | 40 | 90017160 | A1 | 1000154743 | 07.02.2028 | 11000 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-HCYLR | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-HCYLR90017160
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Batteries | 2028-02-10 | 2028-02-10 | 4 hrs | FY28 | 4 | 90023377 | A1 | 1000243622 | 10.02.2028 | 12 Monthly | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-BATTY |  |  |  | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-BATTY90023377
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Operators Seat | 2028-02-10 | 2028-02-10 | 4 hrs | FY28 | 4 | 90002663 | A1 | 1000028497 | 10.02.2028 | 7000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS | 6000 | 71626 | 4801 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS90002663
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Replace Artic Area Hyd Hosing | 2028-02-13 | 2028-02-13 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220520 | 13.02.2028 | 8 Monthly | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO90020831
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Actuator Brake HaulX Shield | 2028-02-15 | 2028-02-16 | 26 hrs | FY28 | 50 | 90033498 | A1 | 1000362567 | 15.02.2028 | 14000 | CLB-MP-DOZR-DZ015 -CASSYS-CTRLH-ACTBK | 4700 | 72405 | 6850 | CLB-MP-DOZR-DZ015 -CASSYS-CTRLH-ACTBK90033498
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Final Drive Position 1 | 2028-02-16 | 2028-02-18 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000029138 | 16.02.2028 | 16000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR01 | 6000 | 81297 | 6952 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR0190002710
854K | Onsite PM | Ancillary | Fortescue | WD6105 | WD6105 Repl Hyd & Steering Oil Cooler | 2028-02-22 | 2028-02-23 | 18 hrs | FY28 | 36 | 90010218 | 1 | 1000179076 | 22.02.2028 | 22000 | CLB-MP-DOZR-WD6105-HYDSYS-HDOCO | 5900 | 55835 | 30849 | CLB-MP-DOZR-WD6105-HYDSYS-HDOCO90010218
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Final Drive RH | 2028-02-22 | 2028-02-22 | 14 hrs | FY28 | 28 | 90000312 | 1 | 1000020516 | 22.02.2028 | 18000 | CLB-MP-DOZR-DZ015 -FDRSYS-FDRRH | 4700 | 72405 | 10760 | CLB-MP-DOZR-DZ015 -FDRSYS-FDRRH90000312
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Cyl Bucket RH High Lift | 2028-02-25 | 2028-02-26 | 18 hrs | FY28 | 36 | 90017977 | A1 | 1000131517 | 25.02.2028 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYR | 6000 | 60624 | 670 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYR90017977
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Auto Lube Pump | 2028-02-27 | 2028-02-27 | 6 hrs | FY28 | 6 | 90002737 | A1 | 1000088589 | 27.02.2028 | 10000 | CLB-MP-LOAD-WL263 -GRSYST-ALBPP | 6000 | 60624 | 648 | CLB-MP-LOAD-WL263 -GRSYST-ALBPP90002737
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Brake Cooling | 2028-02-28 | 2028-02-28 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000080043 | 28.02.2028 | 10000 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP02 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP0290002713
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Final Drive LH | 2028-02-29 | 2028-03-01 | 24 hrs | FY28 | 48 | 90018829 | A1 | 1000313524 | 29.02.2028 | 18000 | CLB-MP-DOZR-DZ8222-FDRSYS-FDRLH | 4800 | 25207 | 10526 | CLB-MP-DOZR-DZ8222-FDRSYS-FDRLH90018829
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Fan Cooling Motor Hyd | 2028-02-29 | 2028-02-29 | 8 hrs | FY28 | 16 | 90018833 | A1 | 1000189068 | 29.02.2028 | 18000 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCFM | 4800 | 25244 | 10526 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCFM90018833
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Overhaul Park Brake & Centre Brg | 2028-03-01 | 2028-03-02 | 18 hrs | FY28 | 36 | 90002711 | A1 | 1000087671 | 01.03.2028 | 10000 | CLB-MP-LOAD-WL264 -BRKSYS-BRPRK | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -BRKSYS-BRPRK90002711
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd Pump Pilot & Cooling | 2028-03-01 | 2028-03-01 | 6 hrs | FY28 | 12 | 90002726 | A1 | 1000079849 | 01.03.2028 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP04 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP0490002726
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Cylinder Blade Lift RH | 2028-03-03 | 2028-03-03 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255567 | 03.03.2028 | 9000 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BLCYR | 4700 | 72846 | 1567 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BLCYR90000287
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Service Minor Air Conditioner | 2028-03-04 | 2028-03-04 | 6 hrs | FY28 | 6 | 90018856 | A1 | 1000221493 | 04.03.2028 | 4500 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN | 4800 | 18270 | 18270 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN90018856
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Engine Cat C27 | 2028-03-04 | 2028-03-07 | 66 hrs | FY28 | 126 | 90015849 | 1 | 1000159547 | 04.03.2028 | 18000 | CLB-MP-DOZR-DZ016 -ENGINE | 4700 | 72846 | 10547 | CLB-MP-DOZR-DZ016 -ENGINE90015849
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Overhaul Air Conditioner | 2028-03-04 | 2028-03-06 | 48 hrs | FY28 | 48 | 90017468 | 1 | 1000160693 | 04.03.2028 | 18000 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN90017468
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Front Drive Shaft | 2028-03-05 | 2028-03-05 | 8 hrs | FY28 | 16 | 90033175 | A1 | 1000333617 | 05.03.2028 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT04 | 6000 | 80034 | 10044 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0490033175
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Front Pump Drv Drive Shaft | 2028-03-05 | 2028-03-05 | 8 hrs | FY28 | 16 | 90033189 | A1 | 1000333621 | 05.03.2028 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT06 | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0690033189
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Replace High Risk Hoses | 2028-03-05 | 2028-03-05 | 6 hrs | FY28 | 6 | 90021797 | 1 | 1000227433 | 05.03.2028 | 7000 | CLB-MP-GRDR-GR017 -ENGINE | 4000 | 54668 | 671 | CLB-MP-GRDR-GR017 -ENGINE90021797
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Engine Midlife complete | 2028-03-05 | 2028-03-07 | 49 hrs | FY28 | 49 | 90015737 | 1 | 1000159845 | 05.03.2028 | 7000 | CLB-MP-GRDR-GR017 -ENGINE | 4000 | 54668 | 671 | CLB-MP-GRDR-GR017 -ENGINE90015737
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Major Service Air Conditioner | 2028-03-05 | 2028-03-06 | 24 hrs | FY28 | 24 | 90017476 | 1 | 1000160711 | 05.03.2028 | 7000 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN90017476
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Air Conditioner Minor Service | 2028-03-07 | 2028-03-07 | 12 hrs | FY28 | 12 | 90019351 | 1 | 1000269638 | 07.03.2028 | 3500 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN90019351
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Motor Fan | 2028-03-10 | 2028-03-10 | 12 hrs | FY28 | 24 | 90002969 | A1 | 1000033542 | 10.03.2028 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HYDMT-HYM01 | 5900 | 79354 | 5467 | CLB-MP-DOZR-WD005 -HYDSYS-HYDMT-HYM0190002969
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hyd Motor & Pump Axle Cooling | 2028-03-10 | 2028-03-10 | 6 hrs | FY28 | 6 | 90002970 | A1 | 1000033543 | 10.03.2028 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HYDMT-HYM02 | 5900 | 79354 | 5467 | CLB-MP-DOZR-WD005 -HYDSYS-HYDMT-HYM0290002970
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Service Minor Air Conditioner | 2028-03-11 | 2028-03-11 | 12 hrs | FY28 | 12 | 90019542 | 1 | 1000200123 | 11.03.2028 | 3500 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN90019542
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Brake System Hoses Midlife | 2028-03-14 | 2028-03-14 | 10.5 hrs | FY28 | 10.5 | 90026908 | A1 | 1000271646 | 14.03.2028 | 10000 | CLB-MP-LOAD-WL264 -BRKSYS-BRHLF-BRKHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -BRKSYS-BRHLF-BRKHO90026908
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Hyd System Hoses Midlife | 2028-03-14 | 2028-03-14 | 10.5 hrs | FY28 | 10.5 | 90026914 | A1 | 1000271648 | 14.03.2028 | 10000 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-HYDHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-HYDHO90026914
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Rear Output Drive Shaft | 2028-03-14 | 2028-03-14 | 7 hrs | FY28 | 14 | 90033168 | A1 | 1000333625 | 14.03.2028 | 20000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT02 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0290033168
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Ctr Output Drive Shaft Unis | 2028-03-14 | 2028-03-14 | 4 hrs | FY28 | 8 | 90033173 | A1 | 1000333628 | 14.03.2028 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT03 | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0390033173
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Rr PDrv Drive Shaft Ctr Brg | 2028-03-14 | 2028-03-14 | 4 hrs | FY28 | 8 | 90033193 | A1 | 1000333632 | 14.03.2028 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT05 | 6000 | 67352 | 10475 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0590033193
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Radiator Engine Cooling | 2028-03-20 | 2028-03-21 | 30 hrs | FY28 | 54 | 90002682 | A1 | 1000029184 | 20.03.2028 | 20000 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-RADTR | 5700 | 80034 | 37765 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-RADTR90002682
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Shaft Rear PD To Cntr Brng | 2028-03-20 | 2028-03-20 | 12 hrs | FY28 | 24 | 90033191 | A1 | 1000333619 | 20.03.2028 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT05 | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0590033191
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Centre Bearing Upper Shaft | 2028-03-20 | 2028-03-20 | 12 hrs | FY28 | 24 | 90002702 | A1 | 1000029196 | 20.03.2028 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-UCTRB | 6000 | 80034 | 10044 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-UCTRB90002702
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Bucket LH High Lift | 2028-03-20 | 2028-03-21 | 18 hrs | FY28 | 36 | 90017978 | A1 | 1000029226 | 20.03.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYL | 6000 | 80034 | 7256 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYL90017978
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Oil Cooler | 2028-03-20 | 2028-03-22 | 48 hrs | FY28 | 96 | 90002733 | A1 | 1000029228 | 20.03.2028 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-HDOCO | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -HYDSYS-HDOCO90002733
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Engine Cat C18 | 2028-03-20 | 2028-03-24 | 94 hrs | FY28 | 310 | 90015771 | 1 | 1000159861 | 20.03.2028 | 14000 | CLB-MP-GRDR-GR013 -ENGINE | 6000 | 71626 | 4169 | CLB-MP-GRDR-GR013 -ENGINE90015771
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Overhaul Air Conditioner | 2028-03-20 | 2028-03-22 | 48 hrs | FY28 | 48 | 90017475 | 1 | 1000160706 | 20.03.2028 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN90017475
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Hyd Pump Fan | 2028-03-23 | 2028-03-23 | 12 hrs | FY28 | 24 | 90021461 | A1 | 1000208010 | 23.03.2028 | 16000 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP03 | 5000 | 21377 | 7805 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP0390021461
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Service Airconditoner Minor | 2028-03-24 | 2028-03-24 | 6 hrs | FY28 | 6 | 90029039 | A1 | 1000290202 | 24.03.2028 | 3500 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-AIRCN | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-AIRCN90029039
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Input Shaft Unis | 2028-03-24 | 2028-03-24 | 4 hrs | FY28 | 8 | 90033167 | A1 | 1000333600 | 24.03.2028 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT01 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0190033167
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Ctr Output Drive Shaft Unis | 2028-03-24 | 2028-03-24 | 4 hrs | FY28 | 8 | 90033173 | A1 | 1000333604 | 24.03.2028 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT03 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0390033173
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Brake System Hoses | 2028-03-25 | 2028-03-26 | 24 hrs | FY28 | 48 | 90013050 | A3 | 1000231967 | 25.03.2028 | 15000 | CLB-MP-DOZR-WD005 -BRKSYS-BRHLF | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -BRKSYS-BRHLF90013050
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hoses Steering System | 2028-03-25 | 2028-03-26 | 24 hrs | FY28 | 48 | 90013051 | A3 | 1000231969 | 25.03.2028 | 15000 | CLB-MP-DOZR-WD005 -STRSYS-STHLF | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRSYS-STHLF90013051
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Replace Hyd Pilot System Hoses | 2028-03-25 | 2028-03-25 | 12 hrs | FY28 | 24 | 90013052 | A3 | 1000231924 | 25.03.2028 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHPS | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHPS90013052
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Hoses Main Hyd-Fan System | 2028-03-25 | 2028-03-26 | 24 hrs | FY28 | 48 | 90013053 | A3 | 1000231925 | 25.03.2028 | 15000 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHMH | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHMH90013053
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Operators Seat | 2028-03-27 | 2028-03-27 | 4 hrs | FY28 | 4 | 90002741 | A1 | 1000029233 | 27.03.2028 | 7000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS | 6000 | 80034 | 3928 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS90002741
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Thermostats | 2028-03-27 | 2028-03-27 | 6 hrs | FY28 | 6 | 90021139 | 1 | 1000222466 | 27.03.2028 | 5000 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-THERM | 6000 | 81297 | 2178 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Service Air Conditioner | 2028-03-27 | 2028-03-28 | 24 hrs | FY28 | 24 | 90021130 | 1 | 1000222456 | 27.03.2028 | 5000 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN90021130
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Ctr Output Drive Shaft Unis | 2028-03-29 | 2028-03-29 | 4 hrs | FY28 | 8 | 90033173 | A1 | 1000333616 | 29.03.2028 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT03 | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0390033173
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Brake System Hoses Midlife | 2028-03-29 | 2028-03-29 | 10.5 hrs | FY28 | 10.5 | 90026908 | A1 | 1000271640 | 29.03.2028 | 10000 | CLB-MP-LOAD-WL028 -BRKSYS-BRHLF-BRKHO | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -BRKSYS-BRHLF-BRKHO90026908
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd System Hoses Midlife | 2028-03-29 | 2028-03-29 | 10.5 hrs | FY28 | 10.5 | 90026914 | A1 | 1000271642 | 29.03.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-HYDHO | 6000 | 80034 | 10046 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-HYDHO90026914
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Transmission System Hoses | 2028-03-29 | 2028-03-31 | 48 hrs | FY28 | 96 | 90026923 | A1 | 1000271655 | 29.03.2028 | 16000 | CLB-MP-LOAD-WL265 -TRNSYS-TRHLF-TRNHO | 6000 | 65007 | 5714 | CLB-MP-LOAD-WL265 -TRNSYS-TRHLF-TRNHO90026923
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Replace Artic Area Hyd Hosing | 2028-03-30 | 2028-03-30 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220518 | 30.03.2028 | 8 Monthly | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Final Drive Position 1 | 2028-04-01 | 2028-04-03 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000079898 | 01.04.2028 | 16000 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR01 | 6000 | 65007 | 6057 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR0190002710
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Final Drive Position 4 | 2028-04-02 | 2028-04-04 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000029207 | 02.04.2028 | 16000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR04 | 6000 | 80034 | 5825 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR0490002710
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Repl Cylinder Blade Lift LH | 2028-04-03 | 2028-04-03 | 8 hrs | FY28 | 14 | 90031953 | A1 | 1000221494 | 03.04.2028 | 9000 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYL | 4800 | 18270 | 1025 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYL90031953
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Replace Artic Area Hyd Hosing | 2028-04-04 | 2028-04-04 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220517 | 04.04.2028 | 8 Monthly | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO90020831
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Adjust 250hr Initial Valve Set | 2028-04-04 | 2028-04-04 | 6 hrs | FY28 | 12 | 90015780 | 1 | 1000159871 | 04.04.2028 | 250 | CLB-MP-GRDR-GR013 -ENGINE | 6000 | 71626 | 4169 | CLB-MP-GRDR-GR013 -ENGINE90015780
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Implement LH | 2028-04-05 | 2028-04-05 | 12 hrs | FY28 | 24 | 90002723 | A1 | 1000029024 | 05.04.2028 | 10000 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP01 | 6000 | 64740 | 9769 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP0190002723
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Fan Cooling Motor Hyd | 2028-04-06 | 2028-04-06 | 8 hrs | FY28 | 16 | 90002094 | 1 | 1000069925 | 06.04.2028 | 9000 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCFM | 4700 | 72846 | 1124 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCFM90002094
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Lift LH High Lift | 2028-04-07 | 2028-04-08 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000029158 | 07.04.2028 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLL | 6000 | 81297 | 10089 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLL90002727
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Steering LH | 2028-04-08 | 2028-04-08 | 10 hrs | FY28 | 18 | 90002721 | A1 | 1000079910 | 08.04.2028 | 12000 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYL | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYL90002721
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Thermostats | 2028-04-11 | 2028-04-11 | 6 hrs | FY28 | 6 | 90021139 | 1 | 1000222576 | 11.04.2028 | 5000 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-THERM | 6000 | 67387 | 4805 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Service Air Conditioner | 2028-04-11 | 2028-04-12 | 24 hrs | FY28 | 24 | 90021130 | 1 | 1000222566 | 11.04.2028 | 5000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN90021130
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Adjust Engine 500hr Valve Set | 2028-04-12 | 2028-04-12 | 12 hrs | FY28 | 24 | 90015857 | 1 | 1000159556 | 12.04.2028 | 500 | CLB-MP-DOZR-DZ016 -ENGINE | 4700 | 72846 | 10547 | CLB-MP-DOZR-DZ016 -ENGINE90015857
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Final Drive Position 4 | 2028-04-13 | 2028-04-15 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000079836 | 13.04.2028 | 16000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR04 | 6000 | 67352 | 5772 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR0490002710
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Replace Artic Area Hyd Hosing | 2028-04-14 | 2028-04-14 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220522 | 14.04.2028 | 8 Monthly | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Rear Output Drive Shaft | 2028-04-20 | 2028-04-20 | 7 hrs | FY28 | 14 | 90033168 | A1 | 1000333637 | 20.04.2028 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT02 | 6000 | 65007 | 9745 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0290033168
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Centre Output Drive Shaft | 2028-04-20 | 2028-04-20 | 7 hrs | FY28 | 14 | 90033171 | A1 | 1000333639 | 20.04.2028 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT03 | 6000 | 65007 | 9745 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0390033171
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Transmission Transfer Case | 2028-04-20 | 2028-04-21 | 38 hrs | FY28 | 74 | 90017029 | A1 | 1000153369 | 20.04.2028 | 16000 | CLB-MP-LOAD-WL265 -TRNSYS-TRTRF | 6000 | 65007 | 5751 | CLB-MP-LOAD-WL265 -TRNSYS-TRTRF90017029
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Replace Artic Area Hyd Hosing | 2028-04-21 | 2028-04-21 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220521 | 21.04.2028 | 8 Monthly | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Articulation Overhaul | 2028-04-22 | 2028-04-30 | 194 hrs | FY28 | 360 | 90032991 | A1 | 1000330003 | 22.04.2028 | 16000 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-ARTIC | 6000 | 65007 | 5714 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-ARTIC90032991
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Cylinder Blade Lift LH | 2028-04-23 | 2028-04-23 | 8 hrs | FY28 | 14 | 90018821 | A1 | 1000189093 | 23.04.2028 | 9000 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BLCYL | 4800 | 25244 | 890 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BLCYL90018821
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Cylinder Blade Lift RH | 2028-04-23 | 2028-04-23 | 8 hrs | FY28 | 14 | 90018821 | A1 | 1000189094 | 23.04.2028 | 9000 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BLCYR | 4800 | 25244 | 890 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BLCYR90018821
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Cylinder Blade Lift LH | 2028-04-23 | 2028-04-23 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255582 | 23.04.2028 | 9000 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BLCYL | 4700 | 66933 | 47 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BLCYL90000287
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Rear Output Drive Shaft | 2028-04-26 | 2028-04-26 | 7 hrs | FY28 | 14 | 90033168 | A1 | 1000333601 | 26.04.2028 | 20000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT02 | 6000 | 81297 | 9807 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0290033168
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Replace Operators Seat | 2028-04-28 | 2028-04-28 | 4 hrs | FY28 | 8 | 90000318 | 1 | 1000089358 | 28.04.2028 | 6000 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-SEATS | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-SEATS90000318
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Bucket RH Lift | 2028-05-02 | 2028-05-03 | 18 hrs | FY28 | 36 | 90017162 | A1 | 1000154741 | 02.05.2028 | 11000 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-BUCYR | 6000 | 65007 | 548 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-BUCYR90017162
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Actuator Brake HaulX Shield | 2028-05-04 | 2028-05-05 | 26 hrs | FY28 | 50 | 90033498 | A1 | 1000362565 | 04.05.2028 | 14000 | CLB-MP-DOZR-DZ011 -CASSYS-CTRLH-ACTBK | 4700 | 70636 | 6032 | CLB-MP-DOZR-DZ011 -CASSYS-CTRLH-ACTBK90033498
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Transmission Oil Cooler | 2028-05-05 | 2028-05-05 | 6 hrs | FY28 | 6 | 90002632 | A1 | 1000028651 | 05.05.2028 | 14000 | CLB-MP-GRDR-GR021 -TRNSYS-TROLC | 6000 | 73692 | 19328 | CLB-MP-GRDR-GR021 -TRNSYS-TROLC90002632
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Pump Transmission | 2028-05-05 | 2028-05-05 | 10 hrs | FY28 | 20 | 90002633 | A1 | 1000028652 | 05.05.2028 | 14000 | CLB-MP-GRDR-GR021 -TRNSYS-TRPMP | 6000 | 73692 | 3215 | CLB-MP-GRDR-GR021 -TRNSYS-TRPMP90002633
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Hyd Pump Steering Main | 2028-05-05 | 2028-05-05 | 6 hrs | FY28 | 12 | 90002647 | A1 | 1000028669 | 05.05.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYSTP | 6000 | 73692 | 3215 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYSTP90002647
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Hyd Pump Brake & Fan | 2028-05-05 | 2028-05-05 | 6 hrs | FY28 | 12 | 90002648 | A1 | 1000028670 | 05.05.2028 | 14000 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-FANPP | 6000 | 73692 | 3215 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-FANPP90002648
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Torque Converter | 2028-05-05 | 2028-05-06 | 24 hrs | FY28 | 48 | 90002693 | A1 | 1000029055 | 05.05.2028 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-TRQUE | 6000 | 78554 | 9502 | CLB-MP-LOAD-WL026 -TRNSYS-TRQUE90002693
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Torque Converter | 2028-05-09 | 2028-05-11 | 62 hrs | FY28 | 122 | 90002630 | A1 | 1000028649 | 09.05.2028 | 14000 | CLB-MP-GRDR-GR021 -TRNSYS-TRQUE | 6000 | 73692 | 3215 | CLB-MP-GRDR-GR021 -TRNSYS-TRQUE90002630
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Transmission | 2028-05-09 | 2028-05-11 | 62 hrs | FY28 | 122 | 90002631 | A1 | 1000028650 | 09.05.2028 | 14000 | CLB-MP-GRDR-GR021 -TRNSYS-TRANS | 6000 | 73692 | 3215 | CLB-MP-GRDR-GR021 -TRNSYS-TRANS90002631
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Gearbox Circle Drive Front | 2028-05-12 | 2028-05-12 | 8 hrs | FY28 | 14 | 90002672 | A1 | 1000028570 | 12.05.2028 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXF | 6000 | 73365 | 3133 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXF90002672
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Input Shaft Unis | 2028-05-13 | 2028-05-13 | 4 hrs | FY28 | 8 | 90033167 | A1 | 1000333588 | 13.05.2028 | 10000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT01 | 6000 | 78554 | 19377 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0190033167
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Rear Output Drive Shaft | 2028-05-13 | 2028-05-13 | 7 hrs | FY28 | 14 | 90033168 | A1 | 1000333589 | 13.05.2028 | 20000 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT02 | 6000 | 78554 | 9502 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT0290033168
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Fan Cooling Motor Hyd | 2028-05-15 | 2028-05-15 | 8 hrs | FY28 | 16 | 90002094 | 1 | 1000069927 | 15.05.2028 | 9000 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCFM | 4700 | 66933 | 684 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCFM90002094
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Refurbish Cabin | 2028-05-16 | 2028-05-17 | 18 hrs | FY28 | 18 | 90010844 | 1 | 1000089424 | 16.05.2028 | 36000 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN | 4700 | 70636 | 27869 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN90010844
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Service Minor Air Conditioner | 2028-05-20 | 2028-05-20 | 12 hrs | FY28 | 12 | 90019542 | 1 | 1000200121 | 20.05.2028 | 3500 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN90019542
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Operators Seat | 2028-05-21 | 2028-05-21 | 4 hrs | FY28 | 4 | 90002741 | A1 | 1000088590 | 21.05.2028 | 7000 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-SEATS | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-SEATS90002741
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Replace Artic Area Hyd Hosing | 2028-05-21 | 2028-05-21 | 6 hrs | FY28 | 6 | 90020831 | 1 | 1000220500 | 21.05.2028 | 8 Monthly | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Final Drive Position 2 | 2028-05-24 | 2028-05-26 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000029074 | 24.05.2028 | 16000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR02 | 6000 | 78554 | 5195 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR0290002710
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Final Drive Position 1 | 2028-05-25 | 2028-05-27 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000088567 | 25.05.2028 | 16000 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR01 | 6000 | 60624 | 5204 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR0190002710
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Hyd Pump Brake Cooling | 2028-05-25 | 2028-05-25 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000029078 | 25.05.2028 | 10000 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP02 | 6000 | 78554 | 9173 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP0290002713
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Drive Shaft TCon to Trans | 2028-05-29 | 2028-05-29 | 4 hrs | FY28 | 4 | 90033265 | A1 | 1000333926 | 29.05.2028 | 14000 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT02 | 6000 | 73365 | 2853 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT0290033265
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Final Drive Position 1 | 2028-06-01 | 2028-06-03 | 44 hrs | FY28 | 83 | 90002710 | A1 | 1000029204 | 01.06.2028 | 16000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR01 | 6000 | 80034 | 4877 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR0190002710
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Lift LH High Lift | 2028-06-01 | 2028-06-02 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000029224 | 01.06.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLL | 6000 | 80034 | 8837 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLL90002727
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Implement LH | 2028-06-02 | 2028-06-02 | 12 hrs | FY28 | 24 | 90002723 | A1 | 1000029220 | 02.06.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP01 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Implement RH | 2028-06-02 | 2028-06-02 | 12 hrs | FY28 | 24 | 90002724 | A1 | 1000029221 | 02.06.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP02 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Implement Centre | 2028-06-02 | 2028-06-02 | 12 hrs | FY28 | 24 | 90002725 | A1 | 1000029222 | 02.06.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP03 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0390002725
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Pilot & Cooling | 2028-06-02 | 2028-06-02 | 6 hrs | FY28 | 12 | 90002726 | A1 | 1000029223 | 02.06.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP04 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP0490002726
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Valve Implement Ctrl LH | 2028-06-02 | 2028-06-03 | 24 hrs | FY28 | 24 | 90010965 | 1 | 1000090189 | 02.06.2028 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-HDVLV-HYV01 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HDVLV-HYV0190010965
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Valve Implement Ctrl RH | 2028-06-02 | 2028-06-03 | 24 hrs | FY28 | 24 | 90010966 | 1 | 1000090190 | 02.06.2028 | 20000 | CLB-MP-LOAD-WL028 -HYDSYS-HDVLV-HYV02 | 6000 | 80034 | 8830 | CLB-MP-LOAD-WL028 -HYDSYS-HDVLV-HYV0290010966
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Repl Operators Seat | 2028-06-02 | 2028-06-02 | 4 hrs | FY28 | 4 | 90010850 | 1 | 1000089526 | 02.06.2028 | 10000 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-SEATS | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-SEATS90010850
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Cylinder Blade Lift LH | 2028-06-03 | 2028-06-03 | 10 hrs | FY28 | 18 | 90000287 | 1 | 1000255542 | 03.06.2028 | 9000 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BLCYL | 4700 | 72325 | 503 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BLCYL90000287
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Engine Cat 3516B | 2028-06-05 | 2028-06-16 | 272 hrs | FY28 | 500 | 90021152 | 1 | 1000222545 | 05.06.2028 | 20000 | CLB-MP-LOAD-WL263 -ENGINE | 6000 | 60721 | 11302 | CLB-MP-LOAD-WL263 -ENGINE90021152
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Overhaul Engine Prelube | 2028-06-05 | 2028-06-05 | 10 hrs | FY28 | 10 | 90021219 | 1 | 1000222546 | 05.06.2028 | 20000 | CLB-MP-LOAD-WL263 -ENGINE-LUBSY-PREPP | 6000 | 60721 | 11302 | CLB-MP-LOAD-WL263 -ENGINE-LUBSY-PREPP90021219
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Overhaul Air Conditioner | 2028-06-05 | 2028-06-07 | 48 hrs | FY28 | 48 | 90021132 | 1 | 1000222543 | 05.06.2028 | 10000 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN90021132
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Final Drive RH | 2028-06-09 | 2028-06-09 | 14 hrs | FY28 | 28 | 90000312 | 1 | 1000016615 | 09.06.2028 | 18000 | CLB-MP-DOZR-DZ011 -FDRSYS-FDRRH | 4700 | 70636 | 9567 | CLB-MP-DOZR-DZ011 -FDRSYS-FDRRH90000312
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Axle Assembly Front | 2028-06-12 | 2028-06-14 | 50 hrs | FY28 | 98 | 90002666 | A1 | 1000180094 | 12.06.2028 | 14000 | CLB-MP-GRDR-GR021 -STRUCT-AXLES | 6000 | 73692 | 2651 | CLB-MP-GRDR-GR021 -STRUCT-AXLES90002666
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Replace High Risk Hoses | 2028-06-12 | 2028-06-12 | 8 hrs | FY28 | 8 | 90024258 | A1 | 1000227474 | 12.06.2028 | 8000 | CLB-MP-LOAD-WL6103-ENGINE | 5000 | 21377 | 6697 | CLB-MP-LOAD-WL6103-ENGINE90024258
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Engine Cat C32 | 2028-06-12 | 2028-06-18 | 154 hrs | FY28 | 304 | 90032102 | A1 | 1000207981 | 12.06.2028 | 16000 | CLB-MP-LOAD-WL6103-ENGINE | 5000 | 21377 | 6697 | CLB-MP-LOAD-WL6103-ENGINE90032102
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Wash Engine Pre Cleaners | 2028-06-12 | 2028-06-12 | 2 hrs | FY28 | 2 | 90017388 | 1 | 1000207983 | 12.06.2028 | 8000 | CLB-MP-LOAD-WL6103-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-LOAD-WL6103-ENGINE-INTEX-AIRFL90017388
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Air Conditioner Overhaul | 2028-06-12 | 2028-06-14 | 48 hrs | FY28 | 48 | 90017479 | A1 | 1000207978 | 12.06.2028 | 8000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN90017479
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Operators Seat | 2028-06-14 | 2028-06-14 | 4 hrs | FY28 | 4 | 90002975 | A1 | 1000033548 | 14.06.2028 | 7000 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-SEATS | 5900 | 79354 | 10152 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-SEATS90002975
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Final Drive RH | 2028-06-14 | 2028-06-14 | 14 hrs | FY28 | 28 | 90000312 | 1 | 1000017703 | 14.06.2028 | 18000 | CLB-MP-DOZR-DZ012 -FDRSYS-FDRRH | 4700 | 60154 | 9380 | CLB-MP-DOZR-DZ012 -FDRSYS-FDRRH90000312
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Hyd Pump Implement | 2028-06-14 | 2028-06-14 | 12 hrs | FY28 | 12 | 90003349 | 1 | 1000038008 | 14.06.2028 | 14000 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYIPP | 4400 | 61520 | 5812 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYIPP90003349
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Hyd Pump Cooling Fan | 2028-06-15 | 2028-06-15 | 10 hrs | FY28 | 10 | 90009272 | 1 | 1000071500 | 15.06.2028 | 7000 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYFPP | 4400 | 66960 | 5716 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYFPP90009272
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Fan Cooling Motor Hyd | 2028-06-15 | 2028-06-15 | 8 hrs | FY28 | 16 | 90003352 | 1 | 1000047859 | 15.06.2028 | 7000 | CLB-MP-DOZR-DZX025-HYDSYS-HDCFM | 4400 | 66960 | 5716 | CLB-MP-DOZR-DZX025-HYDSYS-HDCFM90003352
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Operators Seat | 2028-06-16 | 2028-06-16 | 4 hrs | FY28 | 4 | 90002741 | A1 | 1000029037 | 16.06.2028 | 7000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS90002741
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Adjust Engine 500hr Valve Set | 2028-06-16 | 2028-06-16 | 12 hrs | FY28 | 24 | 90015857 | 1 | 1000159568 | 16.06.2028 | 500 | CLB-MP-DOZR-DZ017 -ENGINE | 4700 | 70238 | 9809 | CLB-MP-DOZR-DZ017 -ENGINE90015857
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Lift RH High Lift | 2028-06-18 | 2028-06-19 | 20 hrs | FY28 | 40 | 90002727 | A1 | 1000029094 | 18.06.2028 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLR | 6000 | 78554 | 8785 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLR90002727
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Steering LH | 2028-06-19 | 2028-06-19 | 10 hrs | FY28 | 18 | 90002721 | A1 | 1000029022 | 19.06.2028 | 12000 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYL | 6000 | 64740 | 546 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYL90002721
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Final Drive RH | 2028-06-19 | 2028-06-19 | 14 hrs | FY28 | 28 | 90000312 | 1 | 1000020542 | 19.06.2028 | 18000 | CLB-MP-DOZR-DZ016 -FDRSYS-FDRRH | 4700 | 72846 | 9172 | CLB-MP-DOZR-DZ016 -FDRSYS-FDRRH90000312
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Adjust 250hr Initial Valve Set | 2028-06-20 | 2028-06-20 | 12 hrs | FY28 | 24 | 90021246 | 1 | 1000222540 | 20.06.2028 | 250 | CLB-MP-LOAD-WL263 -ENGINE | 6000 | 60721 | 11302 | CLB-MP-LOAD-WL263 -ENGINE90021246
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Refurbish Cabin | 2028-06-20 | 2028-06-21 | 18 hrs | FY28 | 18 | 90018839 | A1 | 1000189172 | 20.06.2028 | 36000 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN | 4800 | 26987 | 26987 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN90018839
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Bucket RH Lift | 2028-06-21 | 2028-06-22 | 18 hrs | FY28 | 36 | 90017162 | A1 | 1000154659 | 21.06.2028 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYR | 6000 | 67352 | 10633 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYR90017162
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8223 | DZ8223 Repl Operators Seat | 2028-06-21 | 2028-06-21 | 4 hrs | FY28 | 8 | 90018835 | A1 | 1000189119 | 21.06.2028 | 6000 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-SEATS | 4800 | 26747 | 3032 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-SEATS90018835
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Repl Actuator Brake HaulX Shield | 2028-06-23 | 2028-06-24 | 26 hrs | FY28 | 50 | 90033499 | A1 | 1000362570 | 23.06.2028 | 14000 | CLB-MP-DOZR-DZ8224-CASSYS-CTRLH-ACTBK | 4800 | 26987 | 4944 | CLB-MP-DOZR-DZ8224-CASSYS-CTRLH-ACTBK90033499
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Minor Service Air Conditioner | 2028-06-23 | 2028-06-23 | 6 hrs | FY28 | 6 | 90017699 | 1 | 1000162395 | 23.06.2028 | 4500 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Hyd Pump Brake Cooling | 2028-06-24 | 2028-06-24 | 8 hrs | FY28 | 8 | 90002713 | A1 | 1000029013 | 24.06.2028 | 10000 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP02 | 6000 | 64740 | 8466 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP0290002713
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Transmission | 2028-06-26 | 2028-06-27 | 24 hrs | FY28 | 48 | 90000308 | 1 | 1000017699 | 26.06.2028 | 18000 | CLB-MP-DOZR-DZ012 -TRNSYS-TRANS | 4700 | 60154 | 9226 | CLB-MP-DOZR-DZ012 -TRNSYS-TRANS90000308
| Onsite PM | Ancillary | Fortescue |  | FY29 - ANCILLARY - COMPONENTS DURING PM | 2028-07-01 |  |  | FY29
| Onsite PM | Ancillary | Fortescue | MOC | MAJOR ON CONDITION | 2028-07-01 | 2029-06-30 | 364 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | JULY | 2028-07-01 | 2028-07-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | AUGUST | 2028-08-01 | 2028-08-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | SEPTEMBER | 2028-09-01 | 2028-09-30 | 29 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | OCTOBER | 2028-10-01 | 2028-10-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | NOVEMBER | 2028-11-01 | 2028-11-30 | 29 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | DECEMBER | 2028-12-01 | 2028-12-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | JANUARY | 2029-01-01 | 2029-01-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | FEBRUARY | 2029-02-01 | 2029-02-28 | 27 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | MARCH | 2029-03-01 | 2029-03-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | APRIL | 2029-04-01 | 2029-04-30 | 29 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | MAY | 2029-05-01 | 2029-05-31 | 30 days | FY29
| Onsite PM | Ancillary | Fortescue | MOC | JUNE | 2029-06-01 | 2029-06-30 | 29 days | FY29
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Cyl Steering RH | 2028-07-01 | 2028-07-01 | 10 hrs | FY29 | 20 | 90002722 | A1 | 1000029023 | 01.07.2028 | 12000 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYR | 6000 | 64740 | 12341 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYR90002722
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Service Airconditoner Minor | 2028-07-02 | 2028-07-02 | 6 hrs | FY29 | 6 | 90029039 | A1 | 1000290096 | 02.07.2028 | 3500 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN90029039
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Steering LH | 2028-07-05 | 2028-07-06 | 18 hrs | FY29 | 36 | 90002716 | A1 | 1000029213 | 05.07.2028 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP01 | 6000 | 80034 | 8272 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP0190002716
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Steering RH | 2028-07-05 | 2028-07-06 | 18 hrs | FY29 | 36 | 90002717 | A1 | 1000029214 | 05.07.2028 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP02 | 6000 | 80034 | 8272 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP0290002717
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Rear Output Drive Shaft | 2028-07-06 | 2028-07-06 | 7 hrs | FY29 | 14 | 90033168 | A1 | 1000333613 | 06.07.2028 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT02 | 6000 | 80034 | 8272 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0290033168
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Shaft Universals Front | 2028-07-09 | 2028-07-09 | 3 hrs | FY29 | 6 | 90026667 | A1 | 1000268517 | 09.07.2028 | 11000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT04 | 5900 | 30649 | 10308 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0490026667
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Replace Hyd Pilot System Hoses | 2028-07-09 | 2028-07-09 | 12 hrs | FY29 | 24 | 90013052 | A3 | 1000231923 | 09.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HDHLF-HDHPS | 5900 | 72896 | 17339 | CLB-MP-DOZR-WD004 -HYDSYS-HDHLF-HDHPS90013052
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Repl Cylinder Blade Lift LH | 2028-07-09 | 2028-07-09 | 8 hrs | FY29 | 14 | 90018821 | A1 | 1000189191 | 09.07.2028 | 9000 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYL | 4800 | 26987 | 8732 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYL90018821
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Transmission | 2028-07-11 | 2028-07-15 | 98 hrs | FY29 | 194 | 90002944 | A1 | 1000033459 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -TRNSYS-TRANS | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -TRNSYS-TRANS90002944
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Transmission Oil Cooler | 2028-07-11 | 2028-07-11 | 12 hrs | FY29 | 12 | 90002945 | A1 | 1000033460 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -TRNSYS-TROLC | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -TRNSYS-TROLC90002945
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Pump Transmission | 2028-07-11 | 2028-07-11 | 8 hrs | FY29 | 8 | 90002946 | A1 | 1000033461 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -TRNSYS-TRPMP | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -TRNSYS-TRPMP90002946
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Rear Differential | 2028-07-11 | 2028-07-13 | 62 hrs | FY29 | 122 | 90002952 | A1 | 1000033467 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF90002952
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Brake System Hoses | 2028-07-11 | 2028-07-12 | 24 hrs | FY29 | 48 | 90013050 | A3 | 1000231966 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -BRKSYS-BRHLF | 5900 | 72896 | 17339 | CLB-MP-DOZR-WD004 -BRKSYS-BRHLF90013050
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Pump Str Pilot & Str Cooling | 2028-07-11 | 2028-07-11 | 6 hrs | FY29 | 6 | 90002959 | A1 | 1000033477 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP02 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP0290002959
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Pump Steer Secondary | 2028-07-11 | 2028-07-11 | 6 hrs | FY29 | 6 | 90002960 | A1 | 1000033478 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP03 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP0390002960
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hoses Steering System | 2028-07-11 | 2028-07-12 | 24 hrs | FY29 | 48 | 90013051 | A3 | 1000231968 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -STRSYS-STHLF | 5900 | 72896 | 17339 | CLB-MP-DOZR-WD004 -STRSYS-STHLF90013051
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Pump Implement | 2028-07-11 | 2028-07-11 | 8 hrs | FY29 | 8 | 90002962 | A1 | 1000033481 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP01 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP0190002962
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Pump Pilot | 2028-07-11 | 2028-07-11 | 6 hrs | FY29 | 6 | 90002963 | A1 | 1000033482 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP02 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP0290002963
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Pump Cooling Fan | 2028-07-11 | 2028-07-11 | 10 hrs | FY29 | 10 | 90002964 | A1 | 1000033483 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP03 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP0390002964
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Motor Fan | 2028-07-11 | 2028-07-11 | 12 hrs | FY29 | 24 | 90002969 | A1 | 1000033488 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HYDMT-HYM01 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -HYDSYS-HYDMT-HYM0190002969
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hyd Motor & Pump Axle Cooling | 2028-07-11 | 2028-07-11 | 6 hrs | FY29 | 6 | 90002970 | A1 | 1000033489 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HYDMT-HYM02 | 5900 | 72896 | 3579 | CLB-MP-DOZR-WD004 -HYDSYS-HYDMT-HYM0290002970
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Overhaul Axle Oscillation Rear | 2028-07-11 | 2028-07-13 | 60 hrs | FY29 | 120 | 90002953 | A1 | 1000033468 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF-TRNON | 5900 | 72896 | 18315 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF-TRNON90002953
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hoses Powertrain System | 2028-07-11 | 2028-07-12 | 24 hrs | FY29 | 48 | 90013049 | A3 | 1000231964 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -TRNSYS-TRHLF | 5900 | 72896 | 72896 | CLB-MP-DOZR-WD004 -TRNSYS-TRHLF90013049
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Hoses Main Hyd-Fan System | 2028-07-11 | 2028-07-12 | 24 hrs | FY29 | 48 | 90013053 | A3 | 1000231922 | 11.07.2028 | 15000 | CLB-MP-DOZR-WD004 -HYDSYS-HDHLF-HDHMH | 5900 | 72896 | 17339 | CLB-MP-DOZR-WD004 -HYDSYS-HDHLF-HDHMH90013053
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Final Drive Position 3 | 2028-07-11 | 2028-07-13 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000029140 | 11.07.2028 | 16000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR03 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR0390002710
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Operators Seat | 2028-07-13 | 2028-07-13 | 4 hrs | FY29 | 4 | 90010850 | 1 | 1000089524 | 13.07.2028 | 10000 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-SEATS | 5000 | 65875 | 228 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-SEATS90010850
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Transmission System Hoses | 2028-07-14 | 2028-07-16 | 48 hrs | FY29 | 96 | 90026923 | A1 | 1000271649 | 14.07.2028 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO90026923
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Cylinder Steering LH | 2028-07-15 | 2028-07-15 | 12 hrs | FY29 | 22 | 90002961 | A1 | 1000033533 | 15.07.2028 | 22000 | CLB-MP-DOZR-WD005 -STRSYS-STRCY-STCYL | 5900 | 79354 | 10451 | CLB-MP-DOZR-WD005 -STRSYS-STRCY-STCYL90002961
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Rear Axle Assembly | 2028-07-15 | 2028-07-17 | 64 hrs | FY29 | 128 | 90030396 | A1 | 1000303556 | 15.07.2028 | 14000 | CLB-MP-GRDR-GR021 -FDRSYS-DIFFL | 6000 | 73692 | 2113 | CLB-MP-GRDR-GR021 -FDRSYS-DIFFL90030396
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Final Drive LH | 2028-07-17 | 2028-07-17 | 14 hrs | FY29 | 28 | 90000312 | 1 | 1000016614 | 17.07.2028 | 18000 | CLB-MP-DOZR-DZ011 -FDRSYS-FDRLH | 4700 | 70636 | 9076 | CLB-MP-DOZR-DZ011 -FDRSYS-FDRLH90000312
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Steering LH | 2028-07-18 | 2028-07-18 | 10 hrs | FY29 | 18 | 90002721 | A1 | 1000079844 | 18.07.2028 | 12000 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYL | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYL90002721
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Steering RH | 2028-07-18 | 2028-07-18 | 10 hrs | FY29 | 20 | 90002722 | A1 | 1000079845 | 18.07.2028 | 12000 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYR | 6000 | 67352 | 12287 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYR90002722
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 500hr Initial Valve Set | 2028-07-18 | 2028-07-18 | 10 hrs | FY29 | 20 | 90015822 | 1 | 1000207976 | 18.07.2028 | 500 | CLB-MP-LOAD-WL6103-ENGINE | 5000 | 21377 | 6697 | CLB-MP-LOAD-WL6103-ENGINE90015822
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Final Drive LH | 2028-07-19 | 2028-07-20 | 22 hrs | FY29 | 44 | 90003346 | 1 | 1000038003 | 19.07.2028 | 14000 | CLB-MP-DOZR-DZX024-FDRSYS-FDRLH | 4400 | 61520 | 5385 | CLB-MP-DOZR-DZX024-FDRSYS-FDRLH90003346
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Implement LH | 2028-07-19 | 2028-07-19 | 12 hrs | FY29 | 24 | 90002723 | A1 | 1000029154 | 19.07.2028 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP01 | 6000 | 81297 | 8428 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Implement RH | 2028-07-19 | 2028-07-19 | 12 hrs | FY29 | 24 | 90002724 | A1 | 1000029155 | 19.07.2028 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP02 | 6000 | 81297 | 8425 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0290002724
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Implement Centre | 2028-07-19 | 2028-07-19 | 12 hrs | FY29 | 24 | 90002725 | A1 | 1000029156 | 19.07.2028 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP03 | 6000 | 81297 | 8425 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP0390002725
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Final Drive Position 3 | 2028-07-21 | 2028-07-23 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000029075 | 21.07.2028 | 16000 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR03 | 6000 | 78554 | 4238 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR0390002710
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Final Drive RH | 2028-07-21 | 2028-07-22 | 22 hrs | FY29 | 44 | 90003346 | 1 | 1000037952 | 21.07.2028 | 14000 | CLB-MP-DOZR-DZX022-FDRSYS-FDRRH | 4400 | 63346 | 4882 | CLB-MP-DOZR-DZX022-FDRSYS-FDRRH90003346
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Gearbox Pump Drive Front | 2028-07-23 | 2028-07-24 | 38 hrs | FY29 | 74 | 90002705 | A1 | 1000029133 | 23.07.2028 | 16000 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-FRPDR | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-FRPDR90002705
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Final Drive Position 4 | 2028-07-23 | 2028-07-25 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000029141 | 23.07.2028 | 16000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR04 | 6000 | 81297 | 20356 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR0490002710
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Articulation Overhaul | 2028-07-26 | 2028-08-03 | 194 hrs | FY29 | 360 | 90032991 | A1 | 1000330001 | 26.07.2028 | 16000 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-ARTIC | 6000 | 80034 | 3927 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-ARTIC90032991
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Gearbox Pump Drive Front | 2028-07-29 | 2028-07-30 | 38 hrs | FY29 | 74 | 90002705 | A1 | 1000029199 | 29.07.2028 | 16000 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-FRPDR | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-FRPDR90002705
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Transmission System Hoses | 2028-07-29 | 2028-07-31 | 48 hrs | FY29 | 96 | 90026923 | A1 | 1000271643 | 29.07.2028 | 16000 | CLB-MP-LOAD-WL028 -TRNSYS-TRHLF-TRNHO | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -TRNSYS-TRHLF-TRNHO90026923
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Cyl Articulation RH | 2028-07-29 | 2028-07-29 | 6 hrs | FY29 | 12 | 90019379 | A1 | 1000273139 | 29.07.2028 | 14000 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-ARCYR | 5500 | 19846 | 3088 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-ARCYR90019379
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Shaft Universals TC - Trans | 2028-07-31 | 2028-07-31 | 3 hrs | FY29 | 3 | 90026669 | A1 | 1000268511 | 31.07.2028 | 11000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT01 | 5900 | 30649 | 10308 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0190026669
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Shaft Universals Rear | 2028-07-31 | 2028-07-31 | 3 hrs | FY29 | 6 | 90026666 | A1 | 1000268513 | 31.07.2028 | 11000 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT02 | 5900 | 30649 | 10308 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT0290026666
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Repl Operators Seat | 2028-08-03 | 2028-08-03 | 4 hrs | FY29 | 4 | 90002663 | A1 | 1000028689 | 03.08.2028 | 7000 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-SEATS | 6000 | 73692 | 1802 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-SEATS90002663
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Operators Seat | 2028-08-08 | 2028-08-08 | 4 hrs | FY29 | 4 | 90002741 | A1 | 1000103785 | 08.08.2028 | 7000 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-SEATS | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-SEATS90002741
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Actuator Brake HaulX Shield | 2028-08-13 | 2028-08-14 | 26 hrs | FY29 | 50 | 90033498 | A1 | 1000362568 | 13.08.2028 | 14000 | CLB-MP-DOZR-DZ016 -CASSYS-CTRLH-ACTBK | 4700 | 72846 | 4459 | CLB-MP-DOZR-DZ016 -CASSYS-CTRLH-ACTBK90033498
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Steering RH | 2028-08-14 | 2028-08-14 | 10 hrs | FY29 | 20 | 90002722 | A1 | 1000029219 | 14.08.2028 | 12000 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYR | 6000 | 80034 | 11632 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYR90002722
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Replace Operators Seat | 2028-08-14 | 2028-08-14 | 4 hrs | FY29 | 8 | 90000318 | 1 | 1000089354 | 14.08.2028 | 6000 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-SEATS | 4700 | 70636 | 2639 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-SEATS90000318
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Pump Brake & Hyd Fan | 2028-08-15 | 2028-08-15 | 6 hrs | FY29 | 6 | 90002457 | A1 | 1000027542 | 15.08.2028 | 14000 | CLB-MP-GRDR-GR017 -BRKSYS-BRPMP | 4000 | 54668 | 5883 | CLB-MP-GRDR-GR017 -BRKSYS-BRPMP90002457
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Axle Shaft Position 1 | 2028-08-15 | 2028-08-15 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101218 | 15.08.2028 | 32000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP1 | 6000 | 81297 | 19944 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP190012242
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Thermostats | 2028-08-16 | 2028-08-16 | 6 hrs | FY29 | 6 | 90021139 | 1 | 1000222422 | 16.08.2028 | 5000 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-THERM | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Service Air Conditioner | 2028-08-16 | 2028-08-17 | 24 hrs | FY29 | 24 | 90021130 | 1 | 1000222412 | 16.08.2028 | 5000 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN90021130
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Final Drive Position 2 | 2028-08-18 | 2028-08-20 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000029139 | 18.08.2028 | 16000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR02 | 6000 | 81297 | 3932 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR0290002710
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Operators Seat | 2028-08-20 | 2028-08-20 | 4 hrs | FY29 | 8 | 90000318 | 1 | 1000089356 | 20.08.2028 | 6000 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-SEATS | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-SEATS90000318
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Minor Service Air Conditioner | 2028-08-22 | 2028-08-22 | 6 hrs | FY29 | 6 | 90017699 | 1 | 1000162399 | 22.08.2028 | 4500 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN | 4700 | 72405 | 3917 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Transmission Charge Pump | 2028-08-22 | 2028-08-22 | 6 hrs | FY29 | 12 | 90002694 | A1 | 1000029122 | 22.08.2028 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-TRPMP | 6000 | 81297 | 7864 | CLB-MP-LOAD-WL027 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Transmission | 2028-08-24 | 2028-08-25 | 38 hrs | FY29 | 74 | 90002692 | A1 | 1000029187 | 24.08.2028 | 16000 | CLB-MP-LOAD-WL028 -TRNSYS-TRANS | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -TRNSYS-TRANS90002692
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Final Drive Position 3 | 2028-08-24 | 2028-08-26 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000029206 | 24.08.2028 | 16000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR03 | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR0390002710
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Transmission Transfer Case | 2028-08-24 | 2028-08-25 | 38 hrs | FY29 | 74 | 90017029 | A1 | 1000153367 | 24.08.2028 | 16000 | CLB-MP-LOAD-WL028 -TRNSYS-TRTRF | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -TRNSYS-TRTRF90017029
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Steer Clutch & Brake Assm LH | 2028-08-26 | 2028-08-26 | 16 hrs | FY29 | 32 | 90000313 | 1 | 1000020543 | 26.08.2028 | 18000 | CLB-MP-DOZR-DZ016 -BRKSTR-SCABL | 4700 | 72846 | 8296 | CLB-MP-DOZR-DZ016 -BRKSTR-SCABL90000313
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Minor Overhaul Track Frame RH | 2028-08-27 | 2028-08-29 | 48 hrs | FY29 | 96 | 90010766 | 1 | 1000171804 | 27.08.2028 | 18000 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-TKFRR | 4700 | 72846 | 8287 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-TKFRR90010766
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Bucket RH High Lift | 2028-08-29 | 2028-08-30 | 18 hrs | FY29 | 36 | 90017977 | A1 | 1000029227 | 29.08.2028 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYR | 6000 | 80034 | 7379 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYR90017977
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Repl Cylinder Blade Lift RH | 2028-09-01 | 2028-09-01 | 8 hrs | FY29 | 14 | 90031953 | A1 | 1000221495 | 01.09.2028 | 9000 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYR | 4800 | 18270 | 8046 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYR90031953
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Repl Operators Seat | 2028-09-01 | 2028-09-01 | 4 hrs | FY29 | 8 | 90018835 | A1 | 1000221470 | 01.09.2028 | 6000 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-SEATS | 4800 | 18270 | 8040 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-SEATS90018835
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8223 | DZ8223 Service Minor Air Conditioner | 2028-09-05 | 2028-09-05 | 6 hrs | FY29 | 6 | 90018856 | A1 | 1000189141 | 05.09.2028 | 4500 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN | 4800 | 26747 | 12533 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN90018856
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Minor Service Air Conditioner | 2028-09-07 | 2028-09-07 | 6 hrs | FY29 | 6 | 90017699 | 1 | 1000162402 | 07.09.2028 | 4500 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN90017699
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Operators Seat | 2028-09-08 | 2028-09-08 | 4 hrs | FY29 | 4 | 90010850 | 1 | 1000089528 | 08.09.2028 | 10000 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-SEATS | 4400 | 66960 | 746 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-SEATS90010850
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Operators Seat | 2028-09-10 | 2028-09-10 | 4 hrs | FY29 | 4 | 90002663 | A1 | 1000028561 | 10.09.2028 | 7000 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-SEATS | 6000 | 73365 | 1135 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-SEATS90002663
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Pump Brake & Hyd Fan | 2028-09-14 | 2028-09-14 | 6 hrs | FY29 | 6 | 90019371 | A1 | 1000274141 | 14.09.2028 | 14000 | CLB-MP-GRDR-GR6503-BRKSYS-BRPMP | 5500 | 19846 | 2388 | CLB-MP-GRDR-GR6503-BRKSYS-BRPMP90019371
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Replace Operators Seat | 2028-09-16 | 2028-09-16 | 4 hrs | FY29 | 8 | 90000318 | 1 | 1000089355 | 16.09.2028 | 6000 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-SEATS | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-SEATS90000318
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Articulation Overhaul | 2028-09-19 | 2028-09-27 | 194 hrs | FY29 | 360 | 90032991 | A1 | 1000329972 | 19.09.2028 | 16000 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-ARTIC | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-ARTIC90032991
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Gearbox Pump Drive Front | 2028-09-19 | 2028-09-20 | 38 hrs | FY29 | 74 | 90002705 | A1 | 1000088562 | 19.09.2028 | 16000 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR-FRPDR | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR-FRPDR90002705
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Transmission | 2028-09-19 | 2028-09-20 | 38 hrs | FY29 | 74 | 90002692 | A1 | 1000088550 | 19.09.2028 | 16000 | CLB-MP-LOAD-WL263 -TRNSYS-TRANS | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-TRANS90002692
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Transmission Transfer Case | 2028-09-19 | 2028-09-20 | 38 hrs | FY29 | 74 | 90017029 | A1 | 1000153216 | 19.09.2028 | 16000 | CLB-MP-LOAD-WL263 -TRNSYS-TRTRF | 6000 | 60624 | 3265 | CLB-MP-LOAD-WL263 -TRNSYS-TRTRF90017029
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Final Drive Position 4 | 2028-09-21 | 2028-09-23 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000088570 | 21.09.2028 | 16000 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR04 | 6000 | 60624 | 3251 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR0490002710
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Pilot & Cooling | 2028-09-21 | 2028-09-21 | 6 hrs | FY29 | 12 | 90002726 | A1 | 1000088585 | 21.09.2028 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP04 | 6000 | 60624 | 17971 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0490002726
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Gearbox Circle Drive | 2028-09-23 | 2028-09-23 | 8 hrs | FY29 | 14 | 90019382 | A1 | 1000274147 | 23.09.2028 | 14000 | CLB-MP-GRDR-GR6503-STRUCT-CIRCL-CDRBX | 5500 | 19846 | 2271 | CLB-MP-GRDR-GR6503-STRUCT-CIRCL-CDRBX90019382
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Clean Engine Pre Cleaners | 2028-09-26 | 2028-09-26 | 1 hr | FY29 | 1 | 90029028 | A1 | 1000289950 | 26.09.2028 | 5500 | CLB-MP-DOZR-WD005 -ENGINE | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -ENGINE90029028
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Engine Midlife Complete | 2028-09-26 | 2028-09-28 | 61 hrs | FY29 | 84 | 90029023 | A1 | 1000289947 | 26.09.2028 | 11000 | CLB-MP-DOZR-WD005 -ENGINE | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -ENGINE90029023
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Shaft Universals TC - Trans | 2028-09-26 | 2028-09-26 | 3 hrs | FY29 | 3 | 90026669 | A1 | 1000268255 | 26.09.2028 | 11000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT01 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0190026669
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Replace Shaft Universals Rear | 2028-09-26 | 2028-09-26 | 3 hrs | FY29 | 6 | 90026666 | A1 | 1000268257 | 26.09.2028 | 11000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT02 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0290026666
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Replace Shaft Universals Centre | 2028-09-26 | 2028-09-26 | 3 hrs | FY29 | 6 | 90026668 | A1 | 1000268259 | 26.09.2028 | 11000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT03 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0390026668
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Replace Shaft Universals Front | 2028-09-26 | 2028-09-26 | 3 hrs | FY29 | 6 | 90026667 | A1 | 1000268421 | 26.09.2028 | 11000 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT04 | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT0490026667
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Overhaul Airconditioner | 2028-09-26 | 2028-09-28 | 48 hrs | FY29 | 48 | 90029026 | A1 | 1000289949 | 26.09.2028 | 11000 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN | 5900 | 79354 | 20272 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN90029026
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Replace Artic Area Hyd Hosing | 2028-10-02 | 2028-10-02 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220519 | 02.10.2028 | 8 Monthly | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-ARTHO90020831
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Steer Clutch & Brake Assm RH | 2028-10-02 | 2028-10-02 | 16 hrs | FY29 | 32 | 90000313 | 1 | 1000020544 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -BRKSTR-SCABR | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -BRKSTR-SCABR90000313
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Rad Engine Cooling SN 529 UP | 2028-10-02 | 2028-10-03 | 24 hrs | FY29 | 48 | 90000307 | A1 | 1000020529 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-RADTR | 5100 | 72846 | 23352 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-RADTR90000307
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Aftercooler Engine | 2028-10-02 | 2028-10-02 | 8 hrs | FY29 | 8 | 90010841 | 1 | 1000089375 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -ENGINE-INTEX-AFTER | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -ENGINE-INTEX-AFTER90010841
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Hyd Oil Cooler | 2028-10-02 | 2028-10-02 | 10 hrs | FY29 | 10 | 90009664 | 1 | 1000075355 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -HYDSYS-HDOCO | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -HYDSYS-HDOCO90009664
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Ovhl Hydraulic & Fuel Tank | 2028-10-02 | 2028-10-03 | 24 hrs | FY29 | 48 | 90010842 | 1 | 1000089419 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -HYDSYS-HDTNK | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -HYDSYS-HDTNK90010842
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Equaliser Bar | 2028-10-02 | 2028-10-04 | 48.5 hrs | FY29 | 96.5 | 90002097 | 1 | 1000089439 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-EQUAL | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-EQUAL90002097
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Minor Overhaul Track Frame LH | 2028-10-02 | 2028-10-04 | 48 hrs | FY29 | 96 | 90002098 | 1 | 1000171803 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-TKFRL | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-TKFRL90002098
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Drive Shaft | 2028-10-02 | 2028-10-02 | 3 hrs | FY29 | 6 | 90033296 | A1 | 1000334089 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -TRNSYS | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -TRNSYS90033296
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Transmission | 2028-10-02 | 2028-10-03 | 24 hrs | FY29 | 48 | 90000308 | 1 | 1000020536 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -TRNSYS-TRANS | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -TRNSYS-TRANS90000308
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Pump Trans & TCon Charge | 2028-10-02 | 2028-10-02 | 10 hrs | FY29 | 10 | 90000302 | 1 | 1000020538 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -TRNSYS-TRPMP | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -TRNSYS-TRPMP90000302
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Torque Converter | 2028-10-02 | 2028-10-03 | 30 hrs | FY29 | 60 | 90000309 | 1 | 1000020535 | 02.10.2028 | 18000 | CLB-MP-DOZR-DZ016 -TRNSYS-TRQUE | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -TRNSYS-TRQUE90000309
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Pump Brake | 2028-10-04 | 2028-10-04 | 6 hrs | FY29 | 6 | 90002957 | A1 | 1000033529 | 04.10.2028 | 15000 | CLB-MP-DOZR-WD005 -BRKSYS-BRPMP | 5900 | 79354 | 2149 | CLB-MP-DOZR-WD005 -BRKSYS-BRPMP90002957
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Thermostats | 2028-10-08 | 2028-10-08 | 6 hrs | FY29 | 6 | 90021139 | 1 | 1000222598 | 08.10.2028 | 5000 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-THERM | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Service Air Conditioner | 2028-10-08 | 2028-10-09 | 24 hrs | FY29 | 24 | 90021130 | 1 | 1000222588 | 08.10.2028 | 5000 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN90021130
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Final Drive Position 2 | 2028-10-09 | 2028-10-11 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000088568 | 09.10.2028 | 16000 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR02 | 6000 | 60624 | 2938 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR0290002710
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Final Drive Position 3 | 2028-10-09 | 2028-10-11 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000088569 | 09.10.2028 | 16000 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR03 | 6000 | 60624 | 2938 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR0390002710
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Equaliser Bar | 2028-10-12 | 2028-10-14 | 48 hrs | FY29 | 96 | 90010849 | 1 | 1000089523 | 12.10.2028 | 14000 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-EQUAL | 4400 | 66960 | 18368 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-EQUAL90010849
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Hyd Pump Implement LH | 2028-10-13 | 2028-10-13 | 12 hrs | FY29 | 24 | 90002723 | A1 | 1000088582 | 13.10.2028 | 10000 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP01 | 6000 | 60624 | 6877 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Final Drive Position 2 | 2028-10-14 | 2028-10-16 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000029205 | 14.10.2028 | 16000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR02 | 6000 | 80034 | 2615 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR0290002710
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Engine Thermostats | 2028-10-14 | 2028-10-14 | 4 hrs | FY29 | 4 | 90019397 | A1 | 1000298544 | 14.10.2028 | 3500 | CLB-MP-GRDR-GR6503-ENGINE | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Minor Service Air Conditioner | 2028-10-14 | 2028-10-14 | 12 hrs | FY29 | 12 | 90019412 | A1 | 1000274183 | 14.10.2028 | 3500 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN90019412
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Gearbox Pump Drive Front | 2028-10-16 | 2028-10-17 | 38 hrs | FY29 | 74 | 90002705 | A1 | 1000029003 | 16.10.2028 | 16000 | CLB-MP-LOAD-WL025 -TRNSYS-PMPDR-FRPDR | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-PMPDR-FRPDR90002705
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Transmission System Hoses | 2028-10-16 | 2028-10-18 | 48 hrs | FY29 | 96 | 90026923 | A2 | 1000271625 | 16.10.2028 | 16000 | CLB-MP-LOAD-WL025 -TRNSYS-TRHLF-TRNHO | 6000 | 64740 | 2590 | CLB-MP-LOAD-WL025 -TRNSYS-TRHLF-TRNHO90026923
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Service Minor Air Conditioner | 2028-10-19 | 2028-10-19 | 12 hrs | FY29 | 12 | 90019542 | 1 | 1000200120 | 19.10.2028 | 3500 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN90019542
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Fr Pump Drv Shaft Unis | 2028-10-20 | 2028-10-20 | 4 hrs | FY29 | 8 | 90033190 | A1 | 1000333634 | 20.10.2028 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT06 | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0690033190
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Equaliser Bar | 2028-10-22 | 2028-10-24 | 48 hrs | FY29 | 96 | 90010849 | 1 | 1000089519 | 22.10.2028 | 14000 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-EQUAL | 5000 | 65875 | 16847 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-EQUAL90010849
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Repl Cyl Articulation LH | 2028-10-22 | 2028-10-22 | 6 hrs | FY29 | 12 | 90019378 | A1 | 1000274283 | 22.10.2028 | 14000 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-ARCYL | 5500 | 20249 | 1782 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-ARCYL90019378
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Replace Operators Seat | 2028-10-22 | 2028-10-22 | 4 hrs | FY29 | 8 | 90000318 | 1 | 1000089360 | 22.10.2028 | 6000 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-SEATS | 4700 | 72846 | 1567 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-SEATS90000318
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Service Minor Air Conditioner | 2028-10-24 | 2028-10-24 | 6 hrs | FY29 | 6 | 90018856 | A1 | 1000189190 | 24.10.2028 | 4500 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN | 4800 | 26987 | 8028 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN90018856
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Adjust 250hr Initial Valve Set | 2028-10-25 | 2028-10-25 | 6 hrs | FY29 | 12 | 90015780 | 1 | 1000159910 | 25.10.2028 | 250 | CLB-MP-GRDR-GR021 -ENGINE | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -ENGINE90015780
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Drive Shaft | 2028-10-26 | 2028-10-26 | 3 hrs | FY29 | 6 | 90033296 | A1 | 1000334081 | 26.10.2028 | 18000 | CLB-MP-DOZR-DZ012 -TRNSYS | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -TRNSYS90033296
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Valve Hyd Steering | 2028-10-27 | 2028-10-27 | 4 hrs | FY29 | 4 | 90003347 | 1 | 1000038031 | 27.10.2028 | 14000 | CLB-MP-DOZR-DZX025-BRKSTR-STVLV | 4400 | 66960 | 4189 | CLB-MP-DOZR-DZX025-BRKSTR-STVLV90003347
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Steering RH | 2028-10-30 | 2028-10-30 | 10 hrs | FY29 | 20 | 90002722 | A1 | 1000029153 | 30.10.2028 | 12000 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYR | 6000 | 81297 | 10741 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYR90002722
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Thermostats | 2028-11-04 | 2028-11-04 | 6 hrs | FY29 | 6 | 90021139 | 1 | 1000222488 | 04.11.2028 | 5000 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-THERM | 6000 | 80034 | 11272 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-THERM90021139
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Service Air Conditioner | 2028-11-04 | 2028-11-05 | 24 hrs | FY29 | 24 | 90021130 | 1 | 1000222478 | 04.11.2028 | 5000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN | 6000 | 80034 | 19883 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN90021130
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Refurbish Cabin | 2028-11-05 | 2028-11-06 | 18 hrs | FY29 | 18 | 90018839 | A1 | 1000189074 | 05.11.2028 | 36000 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN | 4800 | 25244 | 25244 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN90018839
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Input Shaft Unis | 2028-11-09 | 2028-11-09 | 4 hrs | FY29 | 8 | 90033167 | A1 | 1000333576 | 09.11.2028 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT01 | 6000 | 64740 | 16190 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0190033167
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Auto Lube Pump | 2028-11-11 | 2028-11-11 | 6 hrs | FY29 | 6 | 90002737 | A1 | 1000029035 | 11.11.2028 | 10000 | CLB-MP-LOAD-WL025 -GRSYST-ALBPP | 6000 | 64740 | 6152 | CLB-MP-LOAD-WL025 -GRSYST-ALBPP90002737
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Transmission Charge Pump | 2028-11-16 | 2028-11-16 | 6 hrs | FY29 | 12 | 90002694 | A1 | 1000079817 | 16.11.2028 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-TRPMP | 6000 | 67352 | 6205 | CLB-MP-LOAD-WL264 -TRNSYS-TRPMP90002694
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Refurbish Cabin | 2028-11-19 | 2028-11-19 | 12 hrs | FY29 | 12 | 90010853 | 1 | 1000089501 | 19.11.2028 | 28000 | CLB-MP-DOZR-DZX023-STRUCT-CABIN | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-STRUCT-CABIN90010853
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Lift LH Lift | 2028-11-21 | 2028-11-22 | 20 hrs | FY29 | 40 | 90017160 | A1 | 1000154656 | 21.11.2028 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLL | 6000 | 67352 | 8109 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLL90017160
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Lift RH Lift | 2028-11-21 | 2028-11-22 | 20 hrs | FY29 | 40 | 90017160 | A1 | 1000154657 | 21.11.2028 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLR | 6000 | 67352 | 8109 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLR90017160
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Engine Midlife Complete | 2028-11-23 | 2028-11-25 | 53 hrs | FY29 | 61 | 90018853 | A1 | 1000189089 | 23.11.2028 | 9000 | CLB-MP-DOZR-DZ8222-ENGINE | 4800 | 25244 | 16002 | CLB-MP-DOZR-DZ8222-ENGINE90018853
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Wash Engine Pre Cleaners | 2028-11-23 | 2028-11-23 | 2 hrs | FY29 | 2 | 90018848 | A1 | 1000189084 | 23.11.2028 | 9000 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AIRFL |  |  |  | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AIRFL90018848
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Service Major Air Conditioner | 2028-11-23 | 2028-11-24 | 24 hrs | FY29 | 24 | 90018855 | A1 | 1000189090 | 23.11.2028 | 9000 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN | 4800 | 25244 | 12059 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN90018855
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Torque Converter | 2028-11-23 | 2028-11-24 | 36 hrs | FY29 | 72 | 90003342 | 1 | 1000038025 | 23.11.2028 | 14000 | CLB-MP-DOZR-DZX025-TRNSYS-TRQUE | 4400 | 66960 | 3862 | CLB-MP-DOZR-DZX025-TRNSYS-TRQUE90003342
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Cyl Bucket LH Lift | 2028-11-24 | 2028-11-25 | 18 hrs | FY29 | 36 | 90017161 | 1 | 1000154658 | 24.11.2028 | 11000 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYL | 6000 | 67352 | 8062 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYL90017161
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Replace Artic Area Hyd Hosing | 2028-11-25 | 2028-11-25 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220518 | 25.11.2028 | 8 Monthly | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-ARTHO90020831
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Brake Assy LHR | 2028-11-28 | 2028-11-29 | 20 hrs | FY29 | 40 | 90019370 | A1 | 1000274209 | 28.11.2028 | 14000 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBLR | 5500 | 19712 | 1251 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBLR90019370
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Replace Artic Area Hyd Hosing | 2028-11-30 | 2028-11-30 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220517 | 30.11.2028 | 8 Monthly | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-ARTHO90020831
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Cylinder Steering LH | 2028-11-30 | 2028-11-30 | 12 hrs | FY29 | 22 | 90002961 | A1 | 1000033479 | 30.11.2028 | 22000 | CLB-MP-DOZR-WD004 -STRSYS-STRCY-STCYL | 5900 | 72896 | 8156 | CLB-MP-DOZR-WD004 -STRSYS-STRCY-STCYL90002961
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Cylinder Steering RH | 2028-11-30 | 2028-11-30 | 12 hrs | FY29 | 22 | 90002961 | A1 | 1000033480 | 30.11.2028 | 22000 | CLB-MP-DOZR-WD004 -STRSYS-STRCY-STCYR | 5900 | 72896 | 8156 | CLB-MP-DOZR-WD004 -STRSYS-STRCY-STCYR90002961
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Implement LH | 2028-12-01 | 2028-12-01 | 12 hrs | FY29 | 24 | 90002723 | A1 | 1000079912 | 01.12.2028 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP01 | 6000 | 65007 | 6057 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP0190002723
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Hyd Pump Implement Centre | 2028-12-01 | 2028-12-01 | 12 hrs | FY29 | 24 | 90002725 | A1 | 1000079914 | 01.12.2028 | 10000 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP03 | 6000 | 65007 | 6057 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP0390002725
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Clean Engine Pre Cleaners | 2028-12-01 | 2028-12-01 | 1 hr | FY29 | 1 | 90029028 | A1 | 1000289943 | 01.12.2028 | 5500 | CLB-MP-DOZR-WD004 -ENGINE | 5900 | 72896 | 13773 | CLB-MP-DOZR-WD004 -ENGINE90029028
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Service Airconditioner | 2028-12-01 | 2028-12-02 | 24 hrs | FY29 | 24 | 90029025 | A1 | 1000289941 | 01.12.2028 | 5500 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN | 5900 | 72896 | 2306 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN90029025
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Final Drive Position 3 | 2028-12-07 | 2028-12-09 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000079900 | 07.12.2028 | 16000 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR03 | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR0390002710
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Final Drive Position 4 | 2028-12-07 | 2028-12-09 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000079901 | 07.12.2028 | 16000 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR04 | 6000 | 65007 | 1947 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR0490002710
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Drive Shaft | 2028-12-09 | 2028-12-09 | 3 hrs | FY29 | 6 | 90033296 | A1 | 1000334079 | 09.12.2028 | 18000 | CLB-MP-DOZR-DZ011 -TRNSYS | 4700 | 70636 | 7204 | CLB-MP-DOZR-DZ011 -TRNSYS90033296
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Replace Artic Area Hyd Hosing | 2028-12-10 | 2028-12-10 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220522 | 10.12.2028 | 8 Monthly | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-ARTHO90020831
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Equaliser Bar | 2028-12-11 | 2028-12-13 | 48.5 hrs | FY29 | 96.5 | 90002097 | 1 | 1000089436 | 11.12.2028 | 18000 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-EQUAL | 4700 | 72325 | 7031 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-EQUAL90002097
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Replace STIC Steering Valve | 2028-12-13 | 2028-12-13 | 12 hrs | FY29 | 12 | 90026110 | A1 | 1000029151 | 13.12.2028 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STIPV | 6000 | 81297 | 5987 | CLB-MP-LOAD-WL027 -STRSYS-STIPV90026110
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Auto Lube Pump | 2028-12-13 | 2028-12-13 | 6 hrs | FY29 | 6 | 90002737 | A1 | 1000029165 | 13.12.2028 | 10000 | CLB-MP-LOAD-WL027 -GRSYST-ALBPP | 6000 | 81297 | 6005 | CLB-MP-LOAD-WL027 -GRSYST-ALBPP90002737
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Minor Service Air Conditioner | 2028-12-15 | 2028-12-15 | 6 hrs | FY29 | 6 | 90017699 | 1 | 1000162397 | 15.12.2028 | 4500 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN | 4700 | 72325 | 2487 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Replace Artic Area Hyd Hosing | 2028-12-17 | 2028-12-17 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220521 | 17.12.2028 | 8 Monthly | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-ARTHO90020831
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Steering Hyd Pump Secondary | 2028-12-19 | 2028-12-19 | 8 hrs | FY29 | 8 | 90002719 | A1 | 1000079909 | 19.12.2028 | 20000 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP04 | 6000 | 65007 | 5751 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP0490002719
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Transmission Charge Pump | 2028-12-19 | 2028-12-19 | 6 hrs | FY29 | 12 | 90002694 | A1 | 1000079882 | 19.12.2028 | 10000 | CLB-MP-LOAD-WL265 -TRNSYS-TRPMP | 6000 | 65007 | 5751 | CLB-MP-LOAD-WL265 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Torque Converter | 2028-12-19 | 2028-12-20 | 24 hrs | FY29 | 48 | 90002693 | A1 | 1000079880 | 19.12.2028 | 20000 | CLB-MP-LOAD-WL265 -TRNSYS-TRQUE | 6000 | 65007 | 5751 | CLB-MP-LOAD-WL265 -TRNSYS-TRQUE90002693
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Cyl Steering RH | 2028-12-20 | 2028-12-20 | 10 hrs | FY29 | 20 | 90002722 | A1 | 1000079911 | 20.12.2028 | 12000 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYR | 6000 | 65007 | 9745 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYR90002722
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Engine Midlife Complete | 2028-12-20 | 2028-12-23 | 71 hrs | FY29 | 103 | 90015859 | 1 | 1000159510 | 20.12.2028 | 9000 | CLB-MP-DOZR-DZ012 -ENGINE | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -ENGINE90015859
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Major Service Air Conditioner | 2028-12-20 | 2028-12-21 | 24 hrs | FY29 | 24 | 90017469 | 1 | 1000160665 | 20.12.2028 | 9000 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-AIRCN | 4700 | 60154 | 2176 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-AIRCN90017469
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Repl Gearbox Circle Drive | 2028-12-21 | 2028-12-21 | 8 hrs | FY29 | 14 | 90019382 | A1 | 1000274292 | 21.12.2028 | 14000 | CLB-MP-GRDR-GR6501-STRUCT-CIRCL-CDRBX | 5500 | 20249 | 885 | CLB-MP-GRDR-GR6501-STRUCT-CIRCL-CDRBX90019382
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Transmission | 2028-12-21 | 2028-12-23 | 50 hrs | FY29 | 98 | 90002448 | A1 | 1000027530 | 21.12.2028 | 14000 | CLB-MP-GRDR-GR017 -TRNSYS-TRANS | 4000 | 54668 | 4479 | CLB-MP-GRDR-GR017 -TRNSYS-TRANS90002448
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Powertrain System Hoses | 2028-12-21 | 2028-12-22 | 36 hrs | FY29 | 36 | 90009931 | 1 | 1000078252 | 21.12.2028 | 14000 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-PWTRN | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-PWTRN90009931
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Refurbish Cabin | 2028-12-23 | 2028-12-24 | 18 hrs | FY29 | 18 | 90018839 | A1 | 1000202342 | 23.12.2028 | 36000 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN | 4800 | 24525 | 24525 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN90018839
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Auto Lube Pump | 2028-12-24 | 2028-12-24 | 4 hrs | FY29 | 4 | 90019389 | A1 | 1000274140 | 24.12.2028 | 14000 | CLB-MP-GRDR-GR6503-GRSYST-ALBPP | 5500 | 19846 | 14857 | CLB-MP-GRDR-GR6503-GRSYST-ALBPP90019389
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Pump Trans & TCon Charge | 2028-12-24 | 2028-12-24 | 10 hrs | FY29 | 10 | 90000302 | 1 | 1000017701 | 24.12.2028 | 18000 | CLB-MP-DOZR-DZ012 -TRNSYS-TRPMP | 4700 | 60154 | 6899 | CLB-MP-DOZR-DZ012 -TRNSYS-TRPMP90000302
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Final Drive Position 3 | 2028-12-25 | 2028-12-27 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000079835 | 25.12.2028 | 16000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR03 | 6000 | 67352 | 1556 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR0390002710
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Steering LH | 2028-12-25 | 2028-12-25 | 10 hrs | FY29 | 18 | 90002721 | A1 | 1000029152 | 25.12.2028 | 12000 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYL | 6000 | 81297 | 9807 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYL90002721
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Repl Engine Thermostats | 2028-12-29 | 2028-12-29 | 4 hrs | FY29 | 4 | 90019397 | A1 | 1000298545 | 29.12.2028 | 3500 | CLB-MP-GRDR-GR6504-ENGINE | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6504 | GR6504 Minor Service Air Conditioner | 2028-12-29 | 2028-12-29 | 12 hrs | FY29 | 12 | 90019412 | A1 | 1000274248 | 29.12.2028 | 3500 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN | 5500 | 19712 | 4282 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN90019412
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Service Airconditoner Minor | 2028-12-29 | 2028-12-29 | 6 hrs | FY29 | 6 | 90029039 | A1 | 1000290163 | 29.12.2028 | 3500 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-AIRCN | 4400 | 63346 | 6444 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-AIRCN90029039
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Adjust 250hr Initial Valve Set | 2029-01-03 | 2029-01-03 | 6 hrs | FY29 | 12 | 90015780 | 1 | 1000159884 | 03.01.2029 | 250 | CLB-MP-GRDR-GR018 -ENGINE | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -ENGINE90015780
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Repl Torque Converter | 2029-01-03 | 2029-01-04 | 24 hrs | FY29 | 48 | 90002693 | A1 | 1000088549 | 03.01.2029 | 20000 | CLB-MP-LOAD-WL263 -TRNSYS-TRQUE | 6000 | 60624 | 5531 | CLB-MP-LOAD-WL263 -TRNSYS-TRQUE90002693
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Fr Pump Drv Shaft Unis | 2029-01-06 | 2029-01-06 | 4 hrs | FY29 | 8 | 90033190 | A1 | 1000333586 | 06.01.2029 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT06 | 6000 | 64740 | 15246 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT0690033190
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Fan Cooling Motor Hyd | 2029-01-07 | 2029-01-07 | 8 hrs | FY29 | 16 | 90018833 | A1 | 1000202316 | 07.01.2029 | 18000 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCFM | 4800 | 24525 | 6330 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCFM90018833
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Brake Assy RHF | 2029-01-08 | 2029-01-09 | 18 hrs | FY29 | 36 | 90002455 | A1 | 1000090996 | 08.01.2029 | 8000 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRF | 4000 | 51804 | 6119 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRF90002455
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Engine Midlife Complete | 2029-01-08 | 2029-01-12 | 98 hrs | FY29 | 130 | 90029037 | A1 | 1000290201 | 08.01.2029 | 7000 | CLB-MP-DOZR-DZX025-ENGINE | 4400 | 66960 | 1289 | CLB-MP-DOZR-DZX025-ENGINE90029037
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Service Airconditroner Major | 2029-01-08 | 2029-01-09 | 24 hrs | FY29 | 24 | 90029040 | A1 | 1000290203 | 08.01.2029 | 7000 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-AIRCN | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-AIRCN90029040
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Steering LH | 2029-01-08 | 2029-01-09 | 18 hrs | FY29 | 36 | 90002716 | A1 | 1000029147 | 08.01.2029 | 20000 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP01 | 6000 | 81297 | 25586 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP0190002716
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Repl Engine Thermostats | 2029-01-10 | 2029-01-10 | 4 hrs | FY29 | 4 | 90019397 | A1 | 1000298546 | 10.01.2029 | 3500 | CLB-MP-GRDR-GR6501-ENGINE | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6501 | GR6501 Minor Service Air Conditioner | 2029-01-10 | 2029-01-10 | 12 hrs | FY29 | 12 | 90019412 | A1 | 1000274568 | 10.01.2029 | 3500 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN | 5500 | 20249 | 4082 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN90019412
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Replace Operators Seat | 2029-01-12 | 2029-01-12 | 4 hrs | FY29 | 8 | 90000318 | 1 | 1000089361 | 12.01.2029 | 6000 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-SEATS | 4700 | 70238 | 522 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-SEATS90000318
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 Replace Artic Area Hyd Hosing | 2029-01-16 | 2029-01-16 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220500 | 16.01.2029 | 8 Monthly | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-ARTHO90020831
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Air Conditioner Minor Service | 2029-01-18 | 2029-01-18 | 12 hrs | FY29 | 12 | 90019351 | 1 | 1000196835 | 18.01.2029 | 3500 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN90019351
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Replace High Risk Hoses | 2029-01-20 | 2029-01-20 | 6 hrs | FY29 | 6 | 90021797 | 1 | 1000269639 | 20.01.2029 | 7000 | CLB-MP-GRDR-GR102 -ENGINE | 4000 | 51814 | 11096 | CLB-MP-GRDR-GR102 -ENGINE90021797
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Engine Midlife complete | 2029-01-20 | 2029-01-22 | 49 hrs | FY29 | 49 | 90015737 | 1 | 1000269635 | 20.01.2029 | 7000 | CLB-MP-GRDR-GR102 -ENGINE | 4000 | 51814 | 11096 | CLB-MP-GRDR-GR102 -ENGINE90015737
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Air Conditioner Major Service | 2029-01-20 | 2029-01-21 | 24 hrs | FY29 | 24 | 90017476 | 1 | 1000269636 | 20.01.2029 | 7000 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN90017476
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Drive Shaft | 2029-01-21 | 2029-01-21 | 3 hrs | FY29 | 6 | 90033282 | A1 | 1000333784 | 21.01.2029 | 14000 | CLB-MP-GRDR-GR102 -TRNSYS | 4000 | 51804 | 11096 | CLB-MP-GRDR-GR102 -TRNSYS90033282
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Cylinder Blade Lift LH | 2029-01-22 | 2029-01-22 | 10 hrs | FY29 | 18 | 90000287 | 1 | 1000255574 | 22.01.2029 | 9000 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYL | 4700 | 70238 | 3490 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYL90000287
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Engine Midlife complete | 2029-01-25 | 2029-01-30 | 132 hrs | FY29 | 170 | 90021253 | 1 | 1000222463 | 25.01.2029 | 10000 | CLB-MP-LOAD-WL027 -ENGINE | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -ENGINE90021253
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Front Drive Shaft Unis | 2029-01-25 | 2029-01-25 | 4 hrs | FY29 | 8 | 90033188 | A1 | 1000333606 | 25.01.2029 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT04 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0490033188
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Rr PDrv Drive Shaft Ctr Brg | 2029-01-25 | 2029-01-25 | 4 hrs | FY29 | 8 | 90033193 | A1 | 1000333608 | 25.01.2029 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT05 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT0590033193
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Overhaul Air Conditioner | 2029-01-25 | 2029-01-27 | 48 hrs | FY29 | 48 | 90021132 | 1 | 1000222455 | 25.01.2029 | 10000 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN90021132
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Brake System Hoses Midlife | 2029-01-25 | 2029-01-25 | 10.5 hrs | FY29 | 10.5 | 90026908 | A1 | 1000271634 | 25.01.2029 | 10000 | CLB-MP-LOAD-WL027 -BRKSYS-BRHLF-BRKHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -BRKSYS-BRHLF-BRKHO90026908
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd System Hoses Midlife | 2029-01-25 | 2029-01-25 | 10.5 hrs | FY29 | 10.5 | 90026914 | A1 | 1000271636 | 25.01.2029 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-HYDHO | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-HYDHO90026914
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Repl Engine Thermostats | 2029-01-27 | 2029-01-27 | 4 hrs | FY29 | 4 | 90019397 | A1 | 1000298547 | 27.01.2029 | 3500 | CLB-MP-GRDR-GR6505-ENGINE | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-ENGINE90019397
18 | Onsite PM | Ancillary | Fortescue | GR6505 | GR6505 Minor Service Air Conditioner | 2029-01-27 | 2029-01-27 | 12 hrs | FY29 | 12 | 90019412 | A1 | 1000274654 | 27.01.2029 | 3500 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN | 5500 | 19670 | 3848 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN90019412
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Drive Shaft | 2029-01-27 | 2029-01-27 | 3 hrs | FY29 | 6 | 90033282 | A1 | 1000333756 | 27.01.2029 | 14000 | CLB-MP-GRDR-GR017 -TRNSYS | 4000 | 54668 | 11075 | CLB-MP-GRDR-GR017 -TRNSYS90033282
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Replace STIC Steering Valve | 2029-01-28 | 2029-01-28 | 12 hrs | FY29 | 12 | 90026110 | A1 | 1000029217 | 28.01.2029 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STIPV | 6000 | 80034 | 48900 | CLB-MP-LOAD-WL028 -STRSYS-STIPV90026110
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Replace Shaft Universals Centre | 2029-01-29 | 2029-01-29 | 3 hrs | FY29 | 6 | 90026668 | A1 | 1000268251 | 29.01.2029 | 11000 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT03 | 5900 | 72896 | 5612 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT0390026668
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Transmission | 2029-01-30 | 2029-01-31 | 38 hrs | FY29 | 74 | 90002692 | A1 | 1000028991 | 30.01.2029 | 16000 | CLB-MP-LOAD-WL025 -TRNSYS-TRANS | 6000 | 64740 | 843 | CLB-MP-LOAD-WL025 -TRNSYS-TRANS90002692
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Output Drive Shaft Unis | 2029-01-30 | 2029-01-30 | 4 hrs | FY29 | 8 | 90033264 | A1 | 1000333921 | 30.01.2029 | 7000 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT01 | 6000 | 71626 | 5974 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT0190033264
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Trans Input Drive Shaft Unis | 2029-01-30 | 2029-01-30 | 4 hrs | FY29 | 8 | 90033267 | A1 | 1000333923 | 30.01.2029 | 7000 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT02 | 6000 | 71626 | 5974 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT0290033267
24M | Onsite PM | Ancillary | Fortescue | GR013 | GR013 Repl Axle Assembly Front | 2029-01-30 | 2029-02-01 | 50 hrs | FY29 | 98 | 90002666 | A1 | 1000180091 | 30.01.2029 | 14000 | CLB-MP-GRDR-GR013 -STRUCT-AXLES | 6000 | 71626 | 12192 | CLB-MP-GRDR-GR013 -STRUCT-AXLES90002666
994H | Onsite PM | Ancillary | Fortescue | WL263 | WL263 12M Inspection Isolator Panel | 2029-01-31 | 2029-01-31 | 2 hrs | FY29 | 2 | 90022525 | A2 | 1000236558 | 31.01.2029 | 12 Monthly | CLB-MP-LOAD-WL263 -ELCTLV | 6000 | 60721 | 60721 | CLB-MP-LOAD-WL263 -ELCTLV90022525
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Centre Bearing Upper Shaft | 2029-02-02 | 2029-02-02 | 12 hrs | FY29 | 24 | 90002702 | A1 | 1000029130 | 02.02.2029 | 10000 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-UCTRB | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-UCTRB90002702
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Hyd Pump Brake | 2029-02-02 | 2029-02-02 | 12 hrs | FY29 | 12 | 90002712 | A1 | 1000029142 | 02.02.2029 | 20000 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP01 | 6000 | 81297 | 5170 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP0190002712
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8224 | DZ8224 Repl Operators Seat | 2029-02-03 | 2029-02-03 | 4 hrs | FY29 | 8 | 90018835 | A1 | 1000189168 | 03.02.2029 | 6000 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS | 4800 | 26987 | 6075 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS90018835
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Aftercooler Engine | 2029-02-03 | 2029-02-03 | 8 hrs | FY29 | 8 | 90010846 | 1 | 1000089493 | 03.02.2029 | 14000 | CLB-MP-DOZR-DZX025-ENGINE-INTEX-AFTER | 4400 | 66960 | 3002 | CLB-MP-DOZR-DZX025-ENGINE-INTEX-AFTER90010846
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Batteries | 2029-02-04 | 2029-02-04 | 4 hrs | FY29 | 4 | 90023377 | A1 | 1000243622 | 04.02.2029 | 12 Monthly | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-BATTY |  |  |  | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-BATTY90023377
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Engine Cat 3516B | 2029-02-09 | 2029-02-20 | 272 hrs | FY29 | 500 | 90021152 | 1 | 1000222567 | 09.02.2029 | 20000 | CLB-MP-LOAD-WL264 -ENGINE | 6000 | 67352 | 4805 | CLB-MP-LOAD-WL264 -ENGINE90021152
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Overhaul Engine Prelube | 2029-02-09 | 2029-02-09 | 10 hrs | FY29 | 10 | 90021219 | 1 | 1000222568 | 09.02.2029 | 20000 | CLB-MP-LOAD-WL264 -ENGINE-LUBSY-PREPP | 6000 | 67352 | 1556 | CLB-MP-LOAD-WL264 -ENGINE-LUBSY-PREPP90021219
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Overhaul Air Conditioner | 2029-02-09 | 2029-02-11 | 48 hrs | FY29 | 48 | 90021132 | 1 | 1000222565 | 09.02.2029 | 10000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN | 6000 | 67352 | 20251 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN90021132
854K | Onsite PM | Ancillary | Fortescue | WD004 | WD004 Repl Operators Seat | 2029-02-10 | 2029-02-10 | 4 hrs | FY29 | 4 | 90002975 | A1 | 1000033494 | 10.02.2029 | 7000 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS | 5900 | 72896 | 6131 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS90002975
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Cylinder Blade Lift RH | 2029-02-11 | 2029-02-11 | 6 hrs | FY29 | 12 | 90002966 | A1 | 1000033539 | 11.02.2029 | 22000 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BLCYR | 5900 | 79354 | 7041 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BLCYR90002966
994H | Onsite PM | Ancillary | Fortescue | WL025 | WL025 Repl Centre Bearing Upper Shaft | 2029-02-12 | 2029-02-12 | 12 hrs | FY29 | 24 | 90002702 | A1 | 1000029000 | 12.02.2029 | 10000 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-UCTRB | 6000 | 64740 | 4624 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-UCTRB90002702
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Operators Seat | 2029-02-12 | 2029-02-12 | 4 hrs | FY29 | 4 | 90002741 | A1 | 1000029167 | 12.02.2029 | 7000 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS | 6000 | 81297 | 6005 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS90002741
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Minor Service Air Conditioner | 2029-02-17 | 2029-02-17 | 6 hrs | FY29 | 6 | 90017699 | 1 | 1000162400 | 17.02.2029 | 4500 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN | 4700 | 72846 | 7825 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Transmission | 2029-02-18 | 2029-02-19 | 38 hrs | FY29 | 74 | 90002692 | A1 | 1000079816 | 18.02.2029 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-TRANS | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-TRANS90002692
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Transmission Transfer Case | 2029-02-18 | 2029-02-19 | 38 hrs | FY29 | 74 | 90017029 | A1 | 1000153368 | 18.02.2029 | 16000 | CLB-MP-LOAD-WL264 -TRNSYS-TRTRF | 6000 | 67352 | 16649 | CLB-MP-LOAD-WL264 -TRNSYS-TRTRF90017029
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Gearbox Circle Drive | 2029-02-21 | 2029-02-21 | 8 hrs | FY29 | 14 | 90002481 | A1 | 1000027569 | 21.02.2029 | 14000 | CLB-MP-GRDR-GR017 -STRUCT-CIRCL-CDRBX | 4000 | 54668 | 3800 | CLB-MP-GRDR-GR017 -STRUCT-CIRCL-CDRBX90002481
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Front Drive Shaft Unis | 2029-02-22 | 2029-02-22 | 4 hrs | FY29 | 8 | 90033188 | A1 | 1000333630 | 22.02.2029 | 10000 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT04 | 6000 | 67352 | 14589 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT0490033188
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Operators Seat | 2029-02-23 | 2029-02-23 | 4 hrs | FY29 | 8 | 90018835 | A1 | 1000189070 | 23.02.2029 | 6000 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS | 4800 | 25244 | 5824 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS90018835
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Adjust 250hr Initial Valve Set | 2029-02-24 | 2029-02-24 | 12 hrs | FY29 | 24 | 90021246 | 1 | 1000222562 | 24.02.2029 | 250 | CLB-MP-LOAD-WL264 -ENGINE | 6000 | 67352 | 4805 | CLB-MP-LOAD-WL264 -ENGINE90021246
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Replace Operators Seat | 2029-02-26 | 2029-02-26 | 4 hrs | FY29 | 8 | 90000318 | 1 | 1000089363 | 26.02.2029 | 6000 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS | 4700 | 66933 | 5461 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS90000318
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Final Drive LH | 2029-02-27 | 2029-02-27 | 14 hrs | FY29 | 28 | 90000312 | 1 | 1000020539 | 27.02.2029 | 18000 | CLB-MP-DOZR-DZ016 -FDRSYS-FDRLH | 4700 | 72846 | 5718 | CLB-MP-DOZR-DZ016 -FDRSYS-FDRLH90000312
D10T | Onsite PM | Ancillary | Fortescue | DZ016 | DZ016 Repl Hyd Pump Implement | 2029-02-27 | 2029-02-27 | 10 hrs | FY29 | 10 | 90000301 | 1 | 1000020545 | 27.02.2029 | 9000 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYIPP | 4700 | 72846 | 4404 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYIPP90000301
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Aftercooler Engine | 2029-02-27 | 2029-02-27 | 8 hrs | FY29 | 8 | 90010846 | 1 | 1000089490 | 27.02.2029 | 14000 | CLB-MP-DOZR-DZX022-ENGINE-INTEX-AFTER | 4400 | 63346 | 17518 | CLB-MP-DOZR-DZX022-ENGINE-INTEX-AFTER90010846
D11T | Onsite PM | Ancillary | Fortescue | DZX022 | DZX022 Repl Hyd Pump Cooling Fan | 2029-02-27 | 2029-02-27 | 10 hrs | FY29 | 10 | 90009272 | 1 | 1000071477 | 27.02.2029 | 7000 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYFPP | 4400 | 63346 | 9901 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYFPP90009272
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Lift RH High Lift | 2029-03-01 | 2029-03-02 | 20 hrs | FY29 | 40 | 90002727 | A1 | 1000029225 | 01.03.2029 | 10000 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLR | 6000 | 80034 | 4358 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLR90002727
D10T | Onsite PM | Ancillary | Fortescue | DZ018 | DZ018 Repl Drive Shaft | 2029-03-03 | 2029-03-03 | 3 hrs | FY29 | 6 | 90033296 | A1 | 1000334093 | 03.03.2029 | 18000 | CLB-MP-DOZR-DZ018 -TRNSYS | 4700 | 66933 | 12696 | CLB-MP-DOZR-DZ018 -TRNSYS90033296
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Cylinder Blade Lift RH | 2029-03-09 | 2029-03-09 | 10 hrs | FY29 | 18 | 90000287 | 1 | 1000255507 | 09.03.2029 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYR | 4700 | 70636 | 6041 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYR90000287
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Operators Seat | 2029-03-10 | 2029-03-10 | 4 hrs | FY29 | 4 | 90002741 | A1 | 1000103784 | 10.03.2029 | 7000 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS | 6000 | 67352 | 5323 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS90002741
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Actuator Brake HaulX Shield | 2029-03-11 | 2029-03-12 | 26 hrs | FY29 | 50 | 90033531 | A1 | 1000337811 | 11.03.2029 | 30000 | CLB-MP-LOAD-WL026 -CASSYS-CTRLH-ACTBK | 6000 | 78563 | 14408 | CLB-MP-LOAD-WL026 -CASSYS-CTRLH-ACTBK90033531
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Operators Seat | 2029-03-12 | 2029-03-12 | 2 hrs | FY29 | 4 | 90002975 | A2 | 1000190021 | 12.03.2029 | 7000 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS | 5900 | 30649 | 5594 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS90002975
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Engine Midlife Complete | 2029-03-15 | 2029-03-19 | 98 hrs | FY29 | 130 | 90029037 | A1 | 1000290095 | 15.03.2029 | 7000 | CLB-MP-DOZR-DZX021-ENGINE | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-ENGINE90029037
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Trans Pump Drive Coupling Replace | 2029-03-15 | 2029-03-15 | 10 hrs | FY29 | 10 | 90037705 | A1 | 1000374083 | 15.03.2029 | 7000 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP90037705
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Hyd Pump Cooling Fan | 2029-03-15 | 2029-03-15 | 10 hrs | FY29 | 10 | 90009272 | 1 | 1000071476 | 15.03.2029 | 7000 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP90009272
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Fan Cooling Motor Hyd | 2029-03-15 | 2029-03-15 | 8 hrs | FY29 | 16 | 90003352 | 1 | 1000037933 | 15.03.2029 | 7000 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM90003352
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Service Airconditroner Major | 2029-03-15 | 2029-03-16 | 24 hrs | FY29 | 24 | 90029040 | A1 | 1000290097 | 15.03.2029 | 7000 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN | 5000 | 65875 | 7882 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN90029040
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Overhaul Park Brake & Centre Brg | 2029-03-16 | 2029-03-17 | 18 hrs | FY29 | 36 | 90002711 | A1 | 1000087669 | 16.03.2029 | 10000 | CLB-MP-LOAD-WL027 -BRKSYS-BRPRK | 6000 | 81297 | 4486 | CLB-MP-LOAD-WL027 -BRKSYS-BRPRK90002711
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Replace STIC Steering Valve | 2029-03-18 | 2029-03-18 | 12 hrs | FY29 | 12 | 90026110 | A1 | 1000029086 | 18.03.2029 | 20000 | CLB-MP-LOAD-WL026 -STRSYS-STIPV | 6000 | 78554 | 5570 | CLB-MP-LOAD-WL026 -STRSYS-STIPV90026110
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8226 | DZ8226 Adjust Engine 500hr Valve Set | 2029-03-19 | 2029-03-19 | 12 hrs | FY29 | 24 | 90018851 | A1 | 1000221488 | 19.03.2029 | 500 | CLB-MP-DOZR-DZ8226-ENGINE | 4800 | 18270 | 5919 | CLB-MP-DOZR-DZ8226-ENGINE90018851
16M | Onsite PM | Ancillary | Fortescue | GR102 | GR102 Repl Operators Seat | 2029-03-19 | 2029-03-19 | 4 hrs | FY29 | 4 | 90002475 | A1 | 1000107180 | 19.03.2029 | 7000 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-SEATS | 4000 | 51804 | 3348 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-SEATS90002475
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8222 | DZ8222 Repl Equaliser Bar | 2029-03-21 | 2029-03-23 | 48 hrs | FY29 | 96 | 90018840 | A1 | 1000189075 | 21.03.2029 | 18000 | CLB-MP-DOZR-DZ8222-STRUCT-CHASS-EQUAL | 4800 | 25244 | 5453 | CLB-MP-DOZR-DZ8222-STRUCT-CHASS-EQUAL90018840
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Final Drive Position 1 | 2029-03-23 | 2029-03-25 | 44 hrs | FY29 | 83 | 90002710 | A1 | 1000079833 | 23.03.2029 | 16000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR01 | 6000 | 67352 | 122 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR0190002710
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Hyd Pump Implement | 2029-03-23 | 2029-03-23 | 10 hrs | FY29 | 10 | 90000301 | 1 | 1000016618 | 23.03.2029 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HYDPP-HYIPP | 4700 | 70636 | 5309 | CLB-MP-DOZR-DZ011 -HYDSYS-HYDPP-HYIPP90000301
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Fan Cooling Motor Hyd | 2029-03-26 | 2029-03-26 | 8 hrs | FY29 | 16 | 90002094 | 1 | 1000069924 | 26.03.2029 | 9000 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCFM | 4700 | 72405 | 5635 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCFM90002094
D10T | Onsite PM | Ancillary | Fortescue | DZ015 | DZ015 Repl Hyd Pump Implement | 2029-03-26 | 2029-03-26 | 10 hrs | FY29 | 10 | 90000301 | 1 | 1000020519 | 26.03.2029 | 9000 | CLB-MP-DOZR-DZ015 -HYDSYS-HYDPP-HYIPP | 4700 | 72405 | 5635 | CLB-MP-DOZR-DZ015 -HYDSYS-HYDPP-HYIPP90000301
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Axle Shaft Position 1 | 2029-03-27 | 2029-03-27 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101242 | 27.03.2029 | 32000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP1 | 6000 | 80034 | 15916 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP190012242
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Axle Shaft Position 2 | 2029-03-27 | 2029-03-27 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101243 | 27.03.2029 | 32000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP2 | 6000 | 80034 | 15916 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP290012242
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Air Conditioner Service | 2029-03-31 | 2029-04-01 | 24 hrs | FY29 | 24 | 90017478 | A1 | 1000207979 | 31.03.2029 | 4000 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | 5000 | 21377 | 4623 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN90017478
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hoses Steering System | 2029-04-04 | 2029-04-05 | 24 hrs | FY29 | 48 | 90013051 | A2 | 1000190016 | 04.04.2029 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STHLF | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-STRSYS-STHLF90013051
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Transmission Oil Cooler | 2029-04-05 | 2029-04-05 | 6 hrs | FY29 | 6 | 90002945 | A2 | 1000189983 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-TRNSYS-TROLC | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-TRNSYS-TROLC90002945
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Pump Transmission | 2029-04-05 | 2029-04-05 | 4 hrs | FY29 | 8 | 90002946 | A2 | 1000189984 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-TRNSYS-TRPMP | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-TRNSYS-TRPMP90002946
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Pump Brake | 2029-04-05 | 2029-04-05 | 4 hrs | FY29 | 4 | 90002957 | A2 | 1000189998 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-BRKSYS-BRPMP | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-BRKSYS-BRPMP90002957
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Brake System Hoses | 2029-04-05 | 2029-04-06 | 24 hrs | FY29 | 48 | 90013050 | A2 | 1000190015 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-BRKSYS-BRHLF | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-BRKSYS-BRHLF90013050
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Steering Main | 2029-04-05 | 2029-04-05 | 6 hrs | FY29 | 12 | 90002958 | A2 | 1000189999 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP01 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP0190002958
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Pump Str Pilot & Str Cooling | 2029-04-05 | 2029-04-05 | 4 hrs | FY29 | 4 | 90002959 | A2 | 1000190000 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP02 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP0290002959
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Steer Secondary | 2029-04-05 | 2029-04-05 | 4 hrs | FY29 | 4 | 90002960 | A2 | 1000190001 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP03 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP0390002960
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Implement | 2029-04-05 | 2029-04-05 | 6 hrs | FY29 | 12 | 90002962 | A2 | 1000190004 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP01 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP0190002962
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Pump Cooling Fan | 2029-04-05 | 2029-04-05 | 4 hrs | FY29 | 8 | 90002964 | A2 | 1000190006 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP03 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP0390002964
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hyd Motor Fan | 2029-04-05 | 2029-04-05 | 4 hrs | FY29 | 8 | 90002969 | A2 | 1000190007 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM01 | 5900 | 30649 | 14275 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM0190002969
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Replace Hyd Pilot System Hoses | 2029-04-05 | 2029-04-05 | 12 hrs | FY29 | 24 | 90013052 | A2 | 1000190017 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHPS | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHPS90013052
854K | Onsite PM | Ancillary | Fortescue | WD6106 | WD6106 Repl Hoses Main Hyd-Fan System | 2029-04-05 | 2029-04-06 | 24 hrs | FY29 | 48 | 90013053 | A2 | 1000229426 | 05.04.2029 | 15000 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHMH | 5900 | 30649 | 30649 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHMH90013053
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Drive Shaft | 2029-04-05 | 2029-04-05 | 14 hrs | FY29 | 14 | 90033381 | A1 | 1000335064 | 05.04.2029 | 28000 | CLB-MP-DOZR-DZX024-TRNSYS | 4400 | 61520 | 16252 | CLB-MP-DOZR-DZX024-TRNSYS90033381
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Overhaul Pivot Shaft | 2029-04-07 | 2029-04-09 | 48 hrs | FY29 | 96 | 90010854 | 1 | 1000089516 | 07.04.2029 | 21000 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-PIVOT | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-PIVOT90010854
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Overhaul Track Frame LH | 2029-04-07 | 2029-04-09 | 60 hrs | FY29 | 120 | 90010770 | 1 | 1000089533 | 07.04.2029 | 21000 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-TKFRL | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-TKFRL90010770
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Overhaul Track Frame RH | 2029-04-07 | 2029-04-09 | 60 hrs | FY29 | 120 | 90010770 | 1 | 1000089543 | 07.04.2029 | 21000 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-TKFRR | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-TKFRR90010770
854K | Onsite PM | Ancillary | Fortescue | WD005 | WD005 Repl Torque Converter | 2029-04-08 | 2029-04-11 | 86 hrs | FY29 | 170 | 90002943 | A1 | 1000033512 | 08.04.2029 | 22000 | CLB-MP-DOZR-WD005 -TRNSYS-TRQUE | 5900 | 79354 | 6148 | CLB-MP-DOZR-WD005 -TRNSYS-TRQUE90002943
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Lift RH High Lift | 2029-04-19 | 2029-04-20 | 20 hrs | FY29 | 40 | 90002727 | A1 | 1000029159 | 19.04.2029 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLR | 6000 | 81297 | 3932 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLR90002727
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Cyl Bucket RH High Lift | 2029-04-19 | 2029-04-20 | 18 hrs | FY29 | 36 | 90017977 | A1 | 1000029161 | 19.04.2029 | 10000 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYR | 6000 | 81297 | 3926 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYR90017977
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Service Minor Air Conditioner | 2029-04-23 | 2029-04-23 | 6 hrs | FY29 | 6 | 90018856 | A1 | 1000202361 | 23.04.2029 | 4500 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN | 4800 | 24525 | 9431 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN90018856
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Minor Service Air Conditioner | 2029-04-23 | 2029-04-23 | 6 hrs | FY29 | 6 | 90017699 | 1 | 1000162401 | 23.04.2029 | 4500 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN | 4700 | 70238 | 1106 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN90017699
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Axle Shaft Position 3 | 2029-04-24 | 2029-04-24 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101244 | 24.04.2029 | 32000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP3 | 6000 | 80034 | 15459 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP390012242
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Axle Shaft Position 4 | 2029-04-24 | 2029-04-24 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101245 | 24.04.2029 | 32000 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP4 | 6000 | 80034 | 15459 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP490012242
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8223 | DZ8223 Repl Pump Hyd Implement 1 | 2029-04-24 | 2029-04-24 | 10 hrs | FY29 | 10 | 90018831 | A1 | 1000189115 | 24.04.2029 | 18000 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYIP1 | 4800 | 26747 | 5003 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYIP190018831
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Transmission Charge Pump | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 12 | 90002694 | A1 | 1000029188 | 25.04.2029 | 10000 | CLB-MP-LOAD-WL028 -TRNSYS-TRPMP | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -TRNSYS-TRPMP90002694
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Input Drive Shaft | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 12 | 90033166 | A1 | 1000333611 | 25.04.2029 | 20000 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT01 | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT0190033166
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Hyd Pump Brake Cooling | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 8 | 90002713 | A1 | 1000029209 | 25.04.2029 | 10000 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP02 | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP0290002713
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Steering Hyd Pump Secondary | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 8 | 90002719 | A1 | 1000029216 | 25.04.2029 | 20000 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP04 | 6000 | 80034 | 3452 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP0490002719
D10T2 | Onsite PM | Ancillary | Fortescue | DZ8225 | DZ8225 Repl Operators Seat | 2029-04-25 | 2029-04-25 | 4 hrs | FY29 | 8 | 90018835 | A1 | 1000202318 | 25.04.2029 | 6000 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS | 4800 | 24525 | 4908 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS90018835
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Repl Engine | 2029-04-30 | 2029-05-06 | 138 hrs | FY29 | 246 | 90029036 | A1 | 1000290167 | 30.04.2029 | 14000 | CLB-MP-DOZR-DZX023-ENGINE | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-ENGINE90029036
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Trans Pump Drive Coupling Replace | 2029-04-30 | 2029-04-30 | 10 hrs | FY29 | 10 | 90037705 | A1 | 1000374087 | 30.04.2029 | 7000 | CLB-MP-DOZR-DZX023-TRNSYS-TRPMP | 4400 | 59280 | 9271 | CLB-MP-DOZR-DZX023-TRNSYS-TRPMP90037705
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Repl Hyd Pump Cooling Fan | 2029-04-30 | 2029-04-30 | 10 hrs | FY29 | 10 | 90009272 | 1 | 1000071478 | 30.04.2029 | 7000 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYFPP | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYFPP90009272
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Repl Hyd Oil Cooler | 2029-04-30 | 2029-04-30 | 8 hrs | FY29 | 8 | 90009665 | 1 | 1000075382 | 30.04.2029 | 14000 | CLB-MP-DOZR-DZX023-HYDSYS-HDOCO | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-HYDSYS-HDOCO90009665
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Repl Fan Cooling Motor Hyd | 2029-04-30 | 2029-04-30 | 8 hrs | FY29 | 16 | 90003352 | 1 | 1000037985 | 30.04.2029 | 7000 | CLB-MP-DOZR-DZX023-HYDSYS-HDCFM | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-HYDSYS-HDCFM90003352
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Overhaul Airconditioner | 2029-04-30 | 2029-05-02 | 48 hrs | FY29 | 48 | 90029041 | A1 | 1000290171 | 30.04.2029 | 14000 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN | 4400 | 59280 | 1992 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN90029041
D11T | Onsite PM | Ancillary | Fortescue | DZX021 | DZX021 Repl Hood Mounts | 2029-05-01 | 2029-05-01 | 6 hrs | FY29 | 12 | 90010848 | 1 | 1000089494 | 01.05.2029 | 14000 | CLB-MP-DOZR-DZX021-STRUCT-PNLGU | 5000 | 65875 | 228 | CLB-MP-DOZR-DZX021-STRUCT-PNLGU90010848
D11T | Onsite PM | Ancillary | Fortescue | DZX023 | DZX023 Repl Transmission | 2029-05-01 | 2029-05-02 | 36 hrs | FY29 | 72 | 90003343 | 1 | 1000037974 | 01.05.2029 | 14000 | CLB-MP-DOZR-DZX023-TRNSYS-TRANS | 4400 | 59280 | 1986 | CLB-MP-DOZR-DZX023-TRNSYS-TRANS90003343
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Fan Cooling Motor Hyd | 2029-05-05 | 2029-05-05 | 8 hrs | FY29 | 16 | 90002094 | 1 | 1000069920 | 05.05.2029 | 9000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCFM | 4700 | 70636 | 5309 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCFM90002094
D10T | Onsite PM | Ancillary | Fortescue | DZ013 | DZ013 Repl Hyd Pump Implement | 2029-05-07 | 2029-05-07 | 10 hrs | FY29 | 10 | 90000301 | 1 | 1000018441 | 07.05.2029 | 9000 | CLB-MP-DOZR-DZ013 -HYDSYS-HYDPP-HYIPP | 4700 | 72325 | 5138 | CLB-MP-DOZR-DZ013 -HYDSYS-HYDPP-HYIPP90000301
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Steering LH | 2029-05-09 | 2029-05-09 | 10 hrs | FY29 | 18 | 90002721 | A1 | 1000029087 | 09.05.2029 | 12000 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYL | 6000 | 78554 | 7440 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYL90002721
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Trans Pump Drive Coupling Replace | 2029-05-09 | 2029-05-09 | 10 hrs | FY29 | 10 | 90037705 | A1 | 1000374091 | 09.05.2029 | 7000 | CLB-MP-DOZR-DZX025-TRNSYS-TRPMP | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-TRNSYS-TRPMP90037705
24M | Onsite PM | Ancillary | Fortescue | GR021 | GR021 Service Minor Air Conditioner | 2029-05-11 | 2029-05-11 | 12 hrs | FY29 | 12 | 90019542 | 1 | 1000200123 | 11.05.2029 | 3500 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | 6000 | 73692 | 14685 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN90019542
24M | Onsite PM | Ancillary | Fortescue | GR018 | GR018 Repl Gearbox Circle Drive Rear | 2029-05-12 | 2029-05-12 | 8 hrs | FY29 | 14 | 90011066 | 1 | 1000028571 | 12.05.2029 | 14000 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXR | 6000 | 73365 | 77 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXR90011066
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Overhaul Park Brake & Centre Brg | 2029-05-21 | 2029-05-22 | 18 hrs | FY29 | 36 | 90002711 | A1 | 1000087670 | 21.05.2029 | 10000 | CLB-MP-LOAD-WL028 -BRKSYS-BRPRK | 6000 | 80034 | 3017 | CLB-MP-LOAD-WL028 -BRKSYS-BRPRK90002711
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Operators Seat | 2029-05-22 | 2029-05-22 | 4 hrs | FY29 | 4 | 90002475 | A1 | 1000027562 | 22.05.2029 | 7000 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-SEATS | 4000 | 54668 | 2814 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-SEATS90002475
994H | Onsite PM | Ancillary | Fortescue | WL265 | WL265 Repl Input Shaft Unis | 2029-05-23 | 2029-05-23 | 4 hrs | FY29 | 8 | 90033167 | A1 | 1000333636 | 23.05.2029 | 10000 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT01 | 6000 | 65007 | 13203 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT0190033167
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Operators Seat | 2029-05-27 | 2029-05-27 | 4 hrs | FY29 | 4 | 90002741 | A1 | 1000029233 | 27.05.2029 | 7000 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS | 6000 | 80034 | 3928 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS90002741
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Transmission | 2029-05-27 | 2029-05-28 | 38 hrs | FY29 | 74 | 90002692 | A1 | 1000029121 | 27.05.2029 | 16000 | CLB-MP-LOAD-WL027 -TRNSYS-TRANS | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-TRANS90002692
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Articulation Overhaul | 2029-05-27 | 2029-06-04 | 194 hrs | FY29 | 360 | 90032991 | A1 | 1000330000 | 27.05.2029 | 16000 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-ARTIC | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-ARTIC90032991
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Axle Shaft Position 2 | 2029-05-27 | 2029-05-27 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101219 | 27.05.2029 | 32000 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP2 | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP290012242
994H | Onsite PM | Ancillary | Fortescue | WL027 | WL027 Repl Transmission Transfer Case | 2029-05-27 | 2029-05-28 | 38 hrs | FY29 | 74 | 90017029 | A1 | 1000153366 | 27.05.2029 | 16000 | CLB-MP-LOAD-WL027 -TRNSYS-TRTRF | 6000 | 81297 | 15300 | CLB-MP-LOAD-WL027 -TRNSYS-TRTRF90017029
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Repl Cylinder Ripper Lift RH | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 10 | 90000291 | 1 | 1000255511 | 30.05.2029 | 18000 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RLCYR | 4700 | 70636 | 4990 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RLCYR90000291
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Articulation Overhaul | 2029-06-01 | 2029-06-09 | 194 hrs | FY29 | 360 | 90032991 | A1 | 1000330002 | 01.06.2029 | 16000 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-ARTIC | 6000 | 67352 | 14957 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-ARTIC90032991
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Engine Midlife complete | 2029-06-03 | 2029-06-05 | 53 hrs | FY29 | 53 | 90019407 | A1 | 1000274180 | 03.06.2029 | 7000 | CLB-MP-GRDR-GR6503-ENGINE | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-ENGINE90019407
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Front Axle Assy Midlife | 2029-06-03 | 2029-06-04 | 32 hrs | FY29 | 56 | 90027058 | A1 | 1000274154 | 03.06.2029 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-AXLES | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-AXLES90027058
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Major Service Air Conditioner | 2029-06-03 | 2029-06-04 | 24 hrs | FY29 | 24 | 90019410 | A1 | 1000274181 | 03.06.2029 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN90019410
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Operators Seat | 2029-06-03 | 2029-06-03 | 4 hrs | FY29 | 8 | 90019380 | A1 | 1000274161 | 03.06.2029 | 7000 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS90019380
18 | Onsite PM | Ancillary | Fortescue | GR6503 | GR6503 Repl Drawbar-Circle-Blade | 2029-06-03 | 2029-06-04 | 24 hrs | FY29 | 48 | 90019413 | A1 | 1000274148 | 03.06.2029 | 21000 | CLB-MP-GRDR-GR6503-STRUCT-DRWBR | 5500 | 19846 | 5430 | CLB-MP-GRDR-GR6503-STRUCT-DRWBR90019413
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Bucket LH High Lift | 2029-06-03 | 2029-06-04 | 18 hrs | FY29 | 36 | 90017978 | A1 | 1000029095 | 03.06.2029 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYL | 6000 | 78554 | 3032 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYL90017978
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Cyl Bucket RH High Lift | 2029-06-03 | 2029-06-04 | 18 hrs | FY29 | 36 | 90017977 | A1 | 1000029096 | 03.06.2029 | 10000 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYR | 6000 | 78554 | 3032 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYR90017977
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Replace Artic Area Hyd Hosing | 2029-06-07 | 2029-06-07 | 6 hrs | FY29 | 6 | 90020831 | 1 | 1000220520 | 07.06.2029 | 8 Monthly | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO |  |  |  | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-ARTHO90020831
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Operators Seat | 2029-06-07 | 2029-06-07 | 4 hrs | FY29 | 4 | 90010850 | 1 | 1000089527 | 07.06.2029 | 10000 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-SEATS | 4400 | 61520 | 7488 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-SEATS90010850
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Auto Lube Pump | 2029-06-08 | 2029-06-08 | 6 hrs | FY29 | 6 | 90002737 | A1 | 1000079853 | 08.06.2029 | 10000 | CLB-MP-LOAD-WL264 -GRSYST-ALBPP | 6000 | 67352 | 6205 | CLB-MP-LOAD-WL264 -GRSYST-ALBPP90002737
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Engine Midlife Complete | 2029-06-08 | 2029-06-11 | 71 hrs | FY29 | 103 | 90015859 | 1 | 1000159438 | 08.06.2029 | 9000 | CLB-MP-DOZR-DZ011 -ENGINE | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -ENGINE90015859
D10T | Onsite PM | Ancillary | Fortescue | DZ011 | DZ011 Major Service Air Conditioner | 2029-06-08 | 2029-06-09 | 24 hrs | FY29 | 24 | 90017469 | 1 | 1000160663 | 08.06.2029 | 9000 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN | 4700 | 70636 | 13876 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN90017469
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Final Drive LH | 2029-06-09 | 2029-06-09 | 14 hrs | FY29 | 28 | 90000312 | 1 | 1000017702 | 09.06.2029 | 18000 | CLB-MP-DOZR-DZ012 -FDRSYS-FDRLH | 4700 | 60154 | 4740 | CLB-MP-DOZR-DZ012 -FDRSYS-FDRLH90000312
D10T | Onsite PM | Ancillary | Fortescue | DZ012 | DZ012 Repl Equaliser Bar | 2029-06-09 | 2029-06-11 | 48.5 hrs | FY29 | 96.5 | 90002097 | 1 | 1000089435 | 09.06.2029 | 18000 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-EQUAL | 4700 | 60154 | 4740 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-EQUAL90002097
994H | Onsite PM | Ancillary | Fortescue | WL026 | WL026 Repl Hyd Valve Implement Ctrl RH | 2029-06-17 | 2029-06-18 | 24 hrs | FY29 | 24 | 90010966 | 1 | 1000090186 | 17.06.2029 | 20000 | CLB-MP-LOAD-WL026 -HYDSYS-HDVLV-HYV02 | 6000 | 78554 | 2800 | CLB-MP-LOAD-WL026 -HYDSYS-HDVLV-HYV0290010966
D11T | Onsite PM | Ancillary | Fortescue | DZX024 | DZX024 Repl Hyd Oil Cooler | 2029-06-18 | 2029-06-18 | 8 hrs | FY29 | 8 | 90009665 | 1 | 1000075383 | 18.06.2029 | 14000 | CLB-MP-DOZR-DZX024-HYDSYS-HDOCO | 4400 | 61520 | 1359 | CLB-MP-DOZR-DZX024-HYDSYS-HDOCO90009665
993K | Onsite PM | Ancillary | Fortescue | WL6103 | WL6103 Repl Fuel Cooler | 2029-06-20 | 2029-06-20 | 6 hrs | FY29 | 6 | 90024229 | A1 | 1000247660 | 20.06.2029 | 16000 | CLB-MP-LOAD-WL6103-ENGINE-FUSYS-FULCO | 5000 | 21377 | 5017 | CLB-MP-LOAD-WL6103-ENGINE-FUSYS-FULCO90024229
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Brake Assy RHF | 2029-06-22 | 2029-06-23 | 18 hrs | FY29 | 36 | 90002455 | A1 | 1000027539 | 22.06.2029 | 8000 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRF | 4000 | 54668 | 4479 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRF90002455
16M | Onsite PM | Ancillary | Fortescue | GR017 | GR017 Repl Brake Assy RHR | 2029-06-22 | 2029-06-23 | 18 hrs | FY29 | 36 | 90002456 | A1 | 1000027541 | 22.06.2029 | 8000 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRR | 4000 | 54668 | 4479 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRR90002456
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Axle Shaft Position 4 | 2029-06-24 | 2029-06-24 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101249 | 24.06.2029 | 32000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP4 | 6000 | 67352 | 14589 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP490012242
D11T | Onsite PM | Ancillary | Fortescue | DZX025 | DZX025 Repl Transmission Oil Cooler | 2029-06-25 | 2029-06-25 | 14 hrs | FY29 | 14 | 90009667 | 1 | 1000075394 | 25.06.2029 | 14000 | CLB-MP-DOZR-DZX025-TRNSYS-TROLC | 4400 | 66960 | 10306 | CLB-MP-DOZR-DZX025-TRNSYS-TROLC90009667
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Axle Shaft Position 1 | 2029-06-26 | 2029-06-26 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101246 | 26.06.2029 | 32000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP1 | 6000 | 67352 | 14589 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP190012242
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Axle Shaft Position 2 | 2029-06-26 | 2029-06-26 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101247 | 26.06.2029 | 32000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP2 | 6000 | 67352 | 14589 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP290012242
994H | Onsite PM | Ancillary | Fortescue | WL264 | WL264 Repl Axle Shaft Position 3 | 2029-06-26 | 2029-06-26 | 6 hrs | FY29 | 12 | 90012242 | 1 | 1000101248 | 26.06.2029 | 32000 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP3 | 6000 | 67352 | 14589 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP390012242
994H | Onsite PM | Ancillary | Fortescue | WL028 | WL028 Repl Cyl Steering LH | 2029-06-30 | 2029-06-30 | 10 hrs | FY29 | 18 | 90002721 | A1 | 1000029218 | 30.06.2029 | 12000 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYL | 6000 | 80034 | 16614 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYL90002721
D10T | Onsite PM | Ancillary | Fortescue | DZ017 | DZ017 Repl Hyd Pump Implement | 2029-06-30 | 2029-06-30 | 10 hrs | FY29 | 10 | 90000301 | 1 | 1000020567 | 30.06.2029 | 9000 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYIPP | 4700 | 70238 | 4429 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYIPP90000301
| Onsite PM | Excavators | Fortescue |  | EXCAVATORS - COMPONENTS DURING PM
| Onsite PM | Excavators | Fortescue |  | FY27 - EXCAVATORS - COMPONENTS DURING PM | 2026-07-01 |  |  | FY27
| Onsite PM | Excavators | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-07-01 | 8760 hrs | FY27
| Onsite PM | Excavators | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6040/6060 Bucket Refurbishments | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6040/6060 Bucket Refurbishments | 2026-07-01 | 2026-07-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Light Weight Bucket Trial | 2026-07-01 | 2026-07-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Shell Change Out / Size Increasing | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | 9400 Onsite Bucket Refurbishment | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Car Body | 2026-10-01 | 2026-10-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Track Frame Refurbishment | 2026-10-01 | 2026-10-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Wide Track Groups | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-10-01 | 2026-10-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Onsite Bucket Refurbishment | 2026-10-01 | 2026-10-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Shell Change Out / Size Increasing | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6060 Onsite Bucket Refurbishment | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-11-01 | 2026-11-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Bucket Shell/Lip Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6040/6060 Lightweight Pin Retainers | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Wide Track Groups | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6040/6060 Slew Bearing | 2027-01-01 | 2027-01-31 | 30 days | FY27
6060 | Onsite PM | Excavators | Fortescue | All - Excavators | 6060 Boom Transfer | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-01-01 | 2027-01-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Shell / Lip Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Shell Change Out / Size Increasing | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - R9400 | Onsite PM | Excavators | Fortescue | All - R9400 | R9400 Tipping Links | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-02-01 | 2027-02-28 | 27 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Onsite Bucket Refurbishment | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6040/6060 Lightweight Pin Retainers | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-04-01 | 2027-04-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Shell Change Out / Size Increasing | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6060 Onsite Bucket Refurbishment | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Excavators | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | All Diggers Rollers Provision | 2027-06-01 | 2027-06-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | All - 6040 | 6040 Onsite Bucket Refurbishment | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Excavators | Onsite PM | Excavators | Fortescue | All - Excavators | 6040/6060 Lightweight Pin Retainers | 2027-06-01 | 2027-06-30 | 29 days | FY27
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom Stick Bucket Cyl Hoses | 2026-07-25 | 2026-07-28 | 88 hrs | FY27 | 136 | 90027560 | A1 | 1000297366 | 10.11.2025 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC90027560
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Grease Injectors | 2026-08-03 | 2026-08-05 | 48 hrs | FY27 | 84 | 90030744 | A1 | 1000330540 | 02.05.2026 | 10000 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ90030744
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Svc 12M Air Conditioner Sys2 Hyd | 2026-08-08 | 2026-08-08 | 12 hrs | FY27 | 12 | 90035242 | A1 | 1000359803 | 12.03.2026 | 12 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC290035242
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Inspection Isolator Panel | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90029980 | 1 | 1000357484 | 22.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7148-ELCTLV |  |  |  | CLB-MP-EXCV-EX7148-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl 24V Batteries | 2026-08-10 | 2026-08-10 | 5 hrs | FY27 | 9 | 90029978 | A1 | 1000357483 | 11.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7148-ELCTLV-CHARG-BATST | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-ELCTLV-CHARG-BATST90029978
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Hydraulic Service & Repairs | 2026-08-10 | 2026-08-11 | 18 hrs | FY27 | 30 | 90029940 | A1 | 1000357445 | 11.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7148-HYDSYS |  |  |  | CLB-MP-EXCV-EX7148-HYDSYS90029940
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Service Air Conditioner Sys 1 | 2026-08-10 | 2026-08-10 | 12 hrs | FY27 | 12 | 90030498 | A1 | 1000357478 | 11.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7148-STRUCT-AIRC1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-AIRC190030498
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Service Air Conditioner Sys 2 | 2026-08-10 | 2026-08-10 | 12 hrs | FY27 | 12 | 90030536 | A1 | 1000357480 | 11.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7148-STRUCT-AIRC2 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-AIRC290030536
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Grease Tank Level Valve | 2026-08-10 | 2026-08-10 | 2 hrs | FY27 | 2 | 90029942 | A1 | 1000357447 | 11.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7148-GRSYST |  |  |  | CLB-MP-EXCV-EX7148-GRSYST90029942
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Auto Lube Pump | 2026-08-13 | 2026-08-13 | 6 hrs | FY27 | 6 | 90027592 | A1 | 1000284661 | 01.08.2026 | 6000 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP90027592
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Rotary Joint | 2026-08-13 | 2026-08-14 | 24 hrs | FY27 | 48 | 90027501 | A1 | 1000284613 | 02.04.2027 | 24000 | CLB-MP-EXCV-EX7124-HYDSYS-ROTRY | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-HYDSYS-ROTRY90027501
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Operators Seat | 2026-08-13 | 2026-08-13 | 2 hrs | FY27 | 2 | 90027613 | A1 | 1000284626 | 08.08.2026 | 10000 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-SEATS | 6700 | 19559 | 9696 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-SEATS90027613
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Gearbox Swing LHR | 2026-08-13 | 2026-08-15 | 50 hrs | FY27 | 82 | 90027580 | A1 | 1000284588 | 10.08.2026 | 20000 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBLR | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBLR90027580
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Gearbox Swing RHF | 2026-08-13 | 2026-08-15 | 50 hrs | FY27 | 82 | 90027580 | A1 | 1000284589 | 10.08.2026 | 20000 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBRF | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBRF90027580
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Gearbox Swing RHR | 2026-08-13 | 2026-08-15 | 50 hrs | FY27 | 82 | 90027580 | A1 | 1000284590 | 10.08.2026 | 20000 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBRR | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBRR90027580
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Stick LH | 2026-08-17 | 2026-08-18 | 30 hrs | FY27 | 54 | 90029971 | A1 | 1000359577 | 16.04.2028 | 16000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-STCLL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-STCLL90029971
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Grease System Audit | 2026-08-17 | 2026-08-18 | 24 hrs | FY27 | 36 | 90029934 | A1 | 1000359549 | 19.07.2026 | 5000 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ90029934
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Minestar Harness | 2026-08-17 | 2026-08-18 | 27.5 hrs | FY27 | 43.5 | 90029998 | A1 | 1000359599 | 18.05.2026 | 4000 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC90029998
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Boom Stick Bucket Cyl Hoses | 2026-08-17 | 2026-08-20 | 88 hrs | FY27 | 160 | 90009238 | 1 | 1000074231 | 18.08.2026 | 6000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-HBSBC | 7500 | 86287 | 5779 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-HBSBC90009238
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 2nd Speed Trvl/Brake Release Hoses | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 12 | 90009236 | 1 | 1000074229 | 23.08.2026 | 10000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-2STBR | 7500 | 86287 | 9687 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-2STBR90009236
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Bucket LH | 2026-08-20 | 2026-08-21 | 26 hrs | FY27 | 32 | 90003169 | A1 | 1000207112 | 03.06.2026 | 10000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL | 6700 | 31524 | 10817 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL90003169
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Minestar Harness | 2026-08-20 | 2026-08-21 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000369999 | 26.02.2026 | 4000 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Idler Track LH | 2026-08-20 | 2026-08-20 | 6 hrs | FY27 | 18 | 90003189 | A1 | 1000207170 | 16.07.2024 | 1500 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-IDLLH | 470 | 2622 | 1533 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-IDLLH90003189
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Idler Track RH | 2026-08-20 | 2026-08-20 | 6 hrs | FY27 | 18 | 90003189 | A1 | 1000207181 | 16.07.2024 | 1500 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-IDLRH | 470 | 2622 | 1697 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-IDLRH90003189
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Sprocket RH | 2026-08-20 | 2026-08-20 | 12 hrs | FY27 | 24 | 90003156 | A1 | 1000207189 | 16.07.2024 | 1500 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKR | 470 | 2622 | 2622 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKR90003156
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 4500hr Valve Set | 2026-08-20 | 2026-08-20 | 10 hrs | FY27 | 20 | 90017923 | A1 | 1000207070 | 18.07.2026 | 4500 | CLB-MP-EXCV-EX7112-LHENGN | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-LHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Fan Drive Eng Cooling Hose | 2026-08-20 | 2026-08-21 | 18 hrs | FY27 | 36 | 90009469 | A2 | 1000207133 | 26.07.2026 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDECH | 6700 | 31524 | 11872 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDECH90009469
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hydraulic Cooling Circ Hoses | 2026-08-20 | 2026-08-21 | 36 hrs | FY27 | 72 | 90009471 | A2 | 1000207135 | 26.07.2026 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HCCHH | 6700 | 31524 | 11872 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HCCHH90009471
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 4500hr Valve Set | 2026-08-20 | 2026-08-20 | 10 hrs | FY27 | 20 | 90017923 | A1 | 1000207085 | 27.07.2026 | 4500 | CLB-MP-EXCV-EX7112-RHENGN | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-RHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Wiper Blades | 2026-08-20 | 2026-08-20 | 2 hrs | FY27 | 2 | 90004684 | 1 | 1000207159 | 30.07.2026 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-CABIN90004684
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Bucket RH Lift | 2026-08-24 | 2026-08-25 | 30 hrs | FY27 | 54 | 90030726 | A1 | 1000340297 | 21.07.2026 | 10000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYR90030726
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Inspection Ext Static Line | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000359517 | 01.06.2026 | 6 Monthly | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029897
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Inspection Ext Static Line | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000357332 | 09.06.2026 | 6 Monthly | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029897
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000337317 | 04.06.2026 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Inspection Ext Static Line | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000304563 | 24.05.2026 | 6 Monthly | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029897
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000348588 | 07.06.2026 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000330578 | 07.06.2026 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Hyd Motor Travel LHR | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 12 | 90002538 | A1 | 1000028063 | 26.08.2026 | 10000 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-TRMLR | 7500 | 86287 | 9623 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-TRMLR90002538
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 6M Anritsu Test WiFi Cables | 2026-08-25 | 2026-08-25 | 2 hrs | FY27 | 2 | 90020303 | A1 | 1000210997 | 25.08.2026 | 6 Monthly | CLB-MP-EXCV-EX7112-COMMUN-FLMGT |  |  |  | CLB-MP-EXCV-EX7112-COMMUN-FLMGT90020303
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Valves Swing Blocking | 2026-08-27 | 2026-08-27 | 6 hrs | FY27 | 6 | 90018174 | A1 | 1000170102 | 22.05.2026 | 36000 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SWBVV | 7500 | 86287 | 37546 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SWBVV90018174
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Oil Suction Hoses | 2026-08-27 | 2026-08-28 | 24 hrs | FY27 | 48 | 90009244 | 1 | 1000074237 | 29.01.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-OILSC | 7500 | 86287 | 21570 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-OILSC90009244
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Hyd Oil | 2026-08-27 | 2026-08-27 | 12 hrs | FY27 | 12 | 90016794 | 1 | 1000151399 | 26.06.2026 | 5000 | CLB-MP-EXCV-EX109 -HYDSYS | 7500 | 86287 | 1478 | CLB-MP-EXCV-EX109 -HYDSYS90016794
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Track Tensioner LH | 2026-08-27 | 2026-08-27 | 14 hrs | FY27 | 28 | 90002553 | A1 | 1000028069 | 19.07.2026 | 20000 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-TENSR | 7500 | 86287 | 20307 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-TENSR90002553
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Track Tensioner RH | 2026-08-27 | 2026-08-27 | 14 hrs | FY27 | 28 | 90002553 | A1 | 1000028070 | 19.07.2026 | 20000 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-TENSR | 7500 | 86287 | 20307 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-TENSR90002553
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl PMS Proportional Valves | 2026-08-27 | 2026-08-27 | 6 hrs | FY27 | 6 | 90018173 | A1 | 1000170097 | 26.08.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-PROVV | 7500 | 86287 | 11607 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-PROVV90018173
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Hyd Motor Swing LHR | 2026-08-27 | 2026-08-27 | 3 hrs | FY27 | 6 | 90002535 | A1 | 1000028053 | 21.07.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMLR | 7500 | 86287 | 12366 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMLR90002535
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Hyd Motor Swing RHF | 2026-08-27 | 2026-08-27 | 3 hrs | FY27 | 6 | 90002535 | A1 | 1000028054 | 21.07.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMRF | 7500 | 86287 | 12366 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMRF90002535
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Hyd Motor Swing RHR | 2026-08-27 | 2026-08-27 | 3 hrs | FY27 | 6 | 90002535 | A1 | 1000028055 | 21.07.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMRR | 7500 | 86287 | 12366 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMRR90002535
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hyd Pump Swing Pos1 | 2026-08-31 | 2026-09-01 | 32 hrs | FY27 | 48 | 90002522 | A1 | 1000027932 | 31.08.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SWPP1 | 7500 | 79029 | 11173 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SWPP190002522
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Minestar Harness | 2026-08-31 | 2026-09-01 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000312852 | 07.07.2026 | 4000 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Fan Drive Eng Cooling Hoses | 2026-08-31 | 2026-09-01 | 18 hrs | FY27 | 36 | 90009469 | A2 | 1000158864 | 22.08.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDECH | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDECH90009469
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Pump to Rotor Hoses | 2026-08-31 | 2026-09-01 | 24 hrs | FY27 | 48 | 90009473 | 1 | 1000158868 | 22.08.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-MPRCH | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-MPRCH90009473
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Rotor & Logic Valve Hp Hoses | 2026-09-03 | 2026-09-04 | 18 hrs | FY27 | 36 | 90022734 | A1 | 1000345674 | 31.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCLVH | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCLVH90022734
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Swing Motor Case Drain Hoses | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 12 | 90022739 | A1 | 1000237065 | 31.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWMCD | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos1 | 2026-09-03 | 2026-09-05 | 42 hrs | FY27 | 54 | 90022637 | A1 | 1000237015 | 02.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP1 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP190022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos2 | 2026-09-03 | 2026-09-05 | 42 hrs | FY27 | 54 | 90022637 | A1 | 1000237016 | 02.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP2 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP290022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Pos1 & Pos2 | 2026-09-03 | 2026-09-04 | 26 hrs | FY27 | 42 | 90022641 | A1 | 1000237019 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP1P2 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP1P290022641
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Replenish LH | 2026-09-03 | 2026-09-03 | 2 hrs | FY27 | 2 | 90022643 | A1 | 1000237025 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPL | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPL90022643
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Auto Lube Pump | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 6 | 90022747 | A1 | 1000237084 | 31.03.2026 | 6000 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP90022747
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Grease Control Valving | 2026-09-03 | 2026-09-03 | 16 hrs | FY27 | 16 | 90022749 | A1 | 1000237086 | 31.03.2026 | 12000 | CLB-MP-EXCV-EX7118-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7118-GRSYST-ALCON90022749
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Fan Drive Eng Cooling Hose | 2026-09-03 | 2026-09-04 | 18 hrs | FY27 | 36 | 90022726 | A1 | 1000345665 | 31.03.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDECH | 6700 | 25925 | 14626 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDECH90022726
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Rotor to Drive Motor Hoses | 2026-09-03 | 2026-09-03 | 10 hrs | FY27 | 20 | 90022733 | A1 | 1000345673 | 31.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCDMH | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCDMH90022733
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 2nd Speed Trvl Brake Release Hose | 2026-09-03 | 2026-09-03 | 5 hrs | FY27 | 10 | 90022723 | A1 | 1000345662 | 31.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SSTBR | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SSTBR90022723
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Rep Travel Motor Case Drain Hoses | 2026-09-03 | 2026-09-03 | 5 hrs | FY27 | 10 | 90022740 | A1 | 1000237066 | 31.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TMCDH | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TMCDH90022740
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel LHF | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237043 | 02.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLF | 6700 | 25972 | 13317 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel LHR | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237044 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLR | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel RHF | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237045 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRF | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel RHR | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237046 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRR | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Rotary Joint | 2026-09-03 | 2026-09-04 | 24 hrs | FY27 | 48 | 90022651 | A1 | 1000237035 | 31.03.2026 | 24000 | CLB-MP-EXCV-EX7118-HYDSYS-ROTRY | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-HYDSYS-ROTRY90022651
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos4 | 2026-09-03 | 2026-09-05 | 42 hrs | FY27 | 54 | 90022637 | A1 | 1000237018 | 22.07.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP4 | 6700 | 25972 | 11914 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP490022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Stick RH | 2026-09-03 | 2026-09-04 | 30 hrs | FY27 | 54 | 90022646 | A1 | 1000237030 | 15.06.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLR | 6700 | 25972 | 12481 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLR90022646
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Boom Arch Hoses | 2026-09-03 | 2026-09-03 | 12 hrs | FY27 | 24 | 90022724 | A1 | 1000345663 | 18.07.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-BMARH | 6700 | 25972 | 11914 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-BMARH90022724
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Servo Hoses Cascade to Bulkhead | 2026-09-03 | 2026-09-03 | 8 hrs | FY27 | 16 | 90022735 | A1 | 1000345675 | 02.06.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHBLK | 6700 | 25972 | 12762 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHBLK90022735
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Servo Hoses Cascade to Trvl Valve | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 12 | 90022737 | A1 | 1000345677 | 03.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHTRV | 6700 | 25948 | 13851 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHTRV90022737
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Fan Engine Cool LH | 2026-09-03 | 2026-09-03 | 6 hrs | FY27 | 18 | 90022656 | A1 | 1000237041 | 05.04.2026 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECL | 6700 | 25972 | 18775 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECL90022656
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos3 | 2026-09-03 | 2026-09-05 | 42 hrs | FY27 | 54 | 90022637 | A1 | 1000237017 | 05.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP3 | 6700 | 25972 | 13291 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP390022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Pos3 & Pos4 | 2026-09-03 | 2026-09-04 | 26 hrs | FY27 | 42 | 90022641 | A1 | 1000237020 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP3P4 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP3P490022641
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Replenish RH | 2026-09-03 | 2026-09-03 | 2 hrs | FY27 | 2 | 90022643 | A1 | 1000237026 | 01.04.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPR | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPR90022643
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Pump Servo RH | 2026-09-03 | 2026-09-03 | 2 hrs | FY27 | 2 | 90022661 | A1 | 1000237024 | 31.05.2026 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPR | 6700 | 25972 | 12762 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPR90022661
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Wiper Blades | 2026-09-03 | 2026-09-03 | 2 hrs | FY27 | 2 | 90022722 | A1 | 1000237078 | 11.03.2026 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7118-STRUCT-CABIN90022722
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service RH | 2026-09-03 | 2026-09-03 | 12 hrs | FY27 | 12 | 90022660 | A1 | 1000237077 | 10.03.2026 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR | 6700 | 25972 | 6562 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR90022660
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service LH | 2026-09-03 | 2026-09-03 | 12 hrs | FY27 | 12 | 90022660 | A1 | 1000242609 | 22.05.2026 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL | 6700 | 17550 | 5056 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL90022660
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Main Hyd Pump Pos1 & Pos2 | 2026-09-07 | 2026-09-08 | 24 hrs | FY27 | 48 | 90002521 | A1 | 1000027928 | 18.03.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP1P2 | 7500 | 79029 | 14281 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP1P290002521
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Fan Drive Crct Hyd Cooling Hoses | 2026-09-07 | 2026-09-08 | 36 hrs | FY27 | 72 | 90009240 | 1 | 1000074214 | 26.11.2025 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HCFC | 7500 | 79029 | 16617 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HCFC90009240
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Oil Suction Hoses | 2026-09-07 | 2026-09-08 | 24 hrs | FY27 | 48 | 90009244 | 1 | 1000074218 | 26.09.2025 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-OILSC | 7500 | 79029 | 17852 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-OILSC90009244
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Servo Hoses Cascade to Bulkhead | 2026-09-07 | 2026-09-07 | 8 hrs | FY27 | 16 | 90009247 | 1 | 1000074221 | 26.09.2025 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHBLK | 7500 | 79029 | 17852 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHBLK90009247
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hyd Oil Cooler Front | 2026-09-07 | 2026-09-07 | 12 hrs | FY27 | 24 | 90018574 | 1 | 1000027956 | 03.04.2026 | 20000 | CLB-MP-EXCV-EX108 -HYDSYS-HDOCO-OCHFR | 7500 | 79029 | 21895 | CLB-MP-EXCV-EX108 -HYDSYS-HDOCO-OCHFR90018574
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Minestar Harness | 2026-09-07 | 2026-09-08 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000312854 | 08.04.2026 | 4000 | CLB-MP-EXCV-EX108 -MANGMT-UMMMC | 7500 | 79029 | 12738 | CLB-MP-EXCV-EX108 -MANGMT-UMMMC90031708
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Swing Circuit Hoses | 2026-09-07 | 2026-09-07 | 13 hrs | FY27 | 23 | 90009251 | 1 | 1000074225 | 14.07.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SWCRT | 7500 | 79029 | 6162 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SWCRT90009251
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hyd Motor Fan Hyd Cool Bot Fr | 2026-09-07 | 2026-09-07 | 8 hrs | FY27 | 24 | 90002536 | A1 | 1000027967 | 24.07.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCBF | 7500 | 79029 | 11955 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCBF90002536
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Flushing Valves | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 6 | 90018176 | A1 | 1000170087 | 26.08.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-FLUVV | 7500 | 79029 | 11173 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-FLUVV90018176
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Wiper Blades | 2026-09-07 | 2026-09-07 | 2 hrs | FY27 | 2 | 90004683 | 1 | 1000049865 | 08.09.2026 | 12 Monthly | CLB-MP-EXCV-EX108 -STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX108 -STRUCT-CABIN90004683
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Track Tensioning Hoses | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 12 | 90009254 | 1 | 1000074228 | 18.09.2026 | 10000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-TRTN | 7500 | 79029 | 18960 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-TRTN90009254
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Valves Swing Blocking | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 6 | 90018174 | A1 | 1000170093 | 05.09.2026 | 36000 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SWBVV | 7500 | 79029 | 35076 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SWBVV90018174
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hydraulic Ladder Accum | 2026-09-07 | 2026-09-07 | 3 hrs | FY27 | 3 | 90032720 | A1 | 1000324851 | 07.09.2026 | 10000 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC | 7500 | 79029 | 79029 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC90032720
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Emerg Lowering Accum | 2026-09-07 | 2026-09-07 | 3 hrs | FY27 | 3 | 90032721 | A1 | 1000324863 | 07.09.2026 | 10000 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC | 7500 | 79029 | 79029 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC90032721
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237081 | 20.06.2026 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237212 | 05.08.2026 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Servo Hose Bulkhead to MCV | 2026-09-10 | 2026-09-10 | 8 hrs | FY27 | 16 | 90022736 | A1 | 1000237193 | 17.01.2026 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHMCV | 6700 | 27054 | 8438 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHMCV90022736
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Case Drain Hoses | 2026-09-10 | 2026-09-10 | 8 hrs | FY27 | 16 | 90022729 | A1 | 1000237186 | 22.08.2026 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HPCDL | 6700 | 27054 | 14526 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HPCDL90022729
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Annual Air Con Service RH | 2026-09-10 | 2026-09-10 | 12 hrs | FY27 | 12 | 90022660 | A1 | 1000237208 | 09.08.2026 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR | 6700 | 27054 | 19941 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR90022660
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Auto Lube Pump P3 | 2026-09-14 | 2026-09-14 | 2 hrs | FY27 | 2 | 90035351 | A1 | 1000358624 | 21.09.2026 | 10000 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBP3 | 6200 | 13908 | 9063 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBP390035351
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Grease System Audit | 2026-09-14 | 2026-09-15 | 24 hrs | FY27 | 36 | 90029934 | A1 | 1000304595 | 02.09.2026 | 5000 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ90029934
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Auto Lube Pump | 2026-09-19 | 2026-09-19 | 6 hrs | FY27 | 6 | 90027592 | A1 | 1000297398 | 02.10.2026 | 6000 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP90027592
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Engine Cat C32 | 2026-09-19 | 2026-09-26 | 176.5 hrs | FY27 | 254.5 | 90027533 | A1 | 1000297273 | 09.10.2026 | 18000 | CLB-MP-EXCV-EX7122-LHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN90027533
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Drive Gearbox LH | 2026-09-19 | 2026-09-20 | 40 hrs | FY27 | 116 | 90027489 | A1 | 1000297328 | 28.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRL90027489
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Adjust 500hr Initial Valve Set | 2026-09-19 | 2026-09-19 | 10 hrs | FY27 | 20 | 90027550 | A1 | 1000297274 | 03.11.2026 | 500 | CLB-MP-EXCV-EX7122-LHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN90027550
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Radiator LH Engine Cooling | 2026-09-19 | 2026-09-19 | 12 hrs | FY27 | 12 | 90027552 | A1 | 1000297277 | 28.10.2026 | 18000 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-RADTR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-RADTR90027552
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl LH Aftercooler | 2026-09-19 | 2026-09-19 | 12 hrs | FY27 | 24 | 90023361 | A1 | 1000309288 | 28.10.2026 | 18000 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-AFTER | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-AFTER90023361
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Swing Motor Case Drain Hoses | 2026-09-24 | 2026-09-24 | 6 hrs | FY27 | 6 | 90009252 | 1 | 1000074207 | 16.07.2026 | 12000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWMCD | 7500 | 86684 | 14005 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWMCD90009252
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Oil Suction Hoses | 2026-09-24 | 2026-09-25 | 24 hrs | FY27 | 48 | 90009244 | 1 | 1000074199 | 16.07.2026 | 12000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-OILSC | 7500 | 86684 | 13235 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-OILSC90009244
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Hyd Pump Case Drain Hoses | 2026-09-24 | 2026-09-24 | 8 hrs | FY27 | 8 | 90009241 | 1 | 1000176912 | 16.07.2026 | 12000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-HPCDL | 7500 | 86684 | 15138 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-HPCDL90009241
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 PTO Cooling Hoses | 2026-09-24 | 2026-09-24 | 12 hrs | FY27 | 24 | 90009245 | 1 | 1000074200 | 16.07.2026 | 18000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-PTOCL | 7500 | 86684 | 19124 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-PTOCL90009245
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Main Pump to Rotor Hoses | 2026-09-24 | 2026-09-24 | 12 hrs | FY27 | 24 | 90009243 | 1 | 1000074198 | 24.07.2026 | 6000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MPRC | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MPRC90009243
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Swing Circuit Hoses | 2026-09-24 | 2026-09-24 | 13 hrs | FY27 | 23 | 90009251 | 1 | 1000074206 | 28.07.2026 | 6000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWCRT | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWCRT90009251
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Servo Hoses Bulkhead to MCV | 2026-09-24 | 2026-09-24 | 8 hrs | FY27 | 16 | 90009248 | 1 | 1000074203 | 28.07.2026 | 6000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHMCV | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHMCV90009248
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Repl Operators Seat | 2026-09-24 | 2026-09-24 | 3 hrs | FY27 | 6 | 90005246 | 1 | 1000055221 | 09.08.2026 | 8000 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-SEATS | 7500 | 86684 | 17032 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-SEATS90005246
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Servo Hoses Cascade to Bulkhead | 2026-09-24 | 2026-09-24 | 8 hrs | FY27 | 16 | 90009247 | 1 | 1000074202 | 14.08.2026 | 12000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHBLK | 7500 | 86684 | 11756 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHBLK90009247
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Rotor to Drive Motor Hoses | 2026-09-24 | 2026-09-25 | 18 hrs | FY27 | 36 | 90009246 | 1 | 1000074201 | 25.08.2026 | 10000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-RCDM | 7500 | 86684 | 9530 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-RCDM90009246
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Hydraulic System Tune Up | 2026-09-24 | 2026-09-24 | 12 hrs | FY27 | 24 | 90017867 | 1 | 1000163740 | 09.09.2026 | 5000 | CLB-MP-EXCV-EX107 -HYDSYS | 7500 | 86684 | 4212 | CLB-MP-EXCV-EX107 -HYDSYS90017867
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Hydraulic Service & Repairs | 2026-09-26 | 2026-09-27 | 18 hrs | FY27 | 30 | 90029940 | A1 | 1000359550 | 26.09.2026 | 12 Monthly | CLB-MP-EXCV-EX7149-HYDSYS |  |  |  | CLB-MP-EXCV-EX7149-HYDSYS90029940
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Minestar Harness | 2026-09-26 | 2026-09-27 | 27.5 hrs | FY27 | 43.5 | 90030746 | A1 | 1000337282 | 24.07.2026 | 5000 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC90030746
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Bucket Cyl | 2026-09-28 | 2026-09-29 | 18 hrs | FY27 | 54 | 90030738 | A1 | 1000330513 | 20.04.2026 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Boom Cyl | 2026-09-28 | 2026-09-28 | 8 hrs | FY27 | 24 | 90030735 | A1 | 1000330512 | 20.04.2026 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Stick Cyl | 2026-09-28 | 2026-09-28 | 12 hrs | FY27 | 24 | 90030737 | A1 | 1000330514 | 20.04.2026 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL90030737
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Minestar Harness | 2026-09-28 | 2026-09-29 | 27.5 hrs | FY27 | 43.5 | 90030746 | A1 | 1000330543 | 22.07.2026 | 5000 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC | 6200 | 11792 | 5210 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC90030746
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2026-09-28 | 2026-09-28 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359909 | 17.08.2026 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Grease Tank Level Valve | 2026-09-28 | 2026-09-28 | 2 hrs | FY27 | 2 | 90015003 | A1 | 1000330541 | 08.10.2026 | 12 Monthly | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Ovhl 24M Air Conditioner Sys1 Eng | 2026-09-28 | 2026-09-30 | 48 hrs | FY27 | 48 | 90035243 | A1 | 1000359794 | 29.09.2026 | 24 Monthly | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC1 | 6500 | 4530 | 4530 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC190035243
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Ovhl 24M Air Conditioner Sys2 Hyd | 2026-09-28 | 2026-09-29 | 36 hrs | FY27 | 36 | 90035267 | A1 | 1000359796 | 29.09.2026 | 24 Monthly | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC290035267
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Main Hyd Pump Pos5 & Pos6 | 2026-09-28 | 2026-09-29 | 24 hrs | FY27 | 48 | 90002521 | A1 | 1000027930 | 04.10.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP5P6 | 7500 | 79029 | 10473 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP5P690002521
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2026-10-05 | 2026-10-05 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359910 | 02.09.2026 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Boom Module Quarter Life | 2026-10-05 | 2026-10-06 | 30 hrs | FY27 | 48 | 90027377 | A1 | 1000348396 | 29.09.2026 | 10000 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90027377
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Track Tension Tuning-Adjust | 2026-10-05 | 2026-10-05 | 3 hrs | FY27 | 9 | 90020545 | A1 | 1000348591 | 29.09.2026 | 6 Monthly | CLB-MP-EXCV-EX7141-UNDERC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC90020545
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Adjust Track Tension Tuning | 2026-10-06 | 2026-10-06 | 3 hrs | FY27 | 9 | 90029977 | A1 | 1000304629 | 06.10.2026 | 6 Monthly | CLB-MP-EXCV-EX7133-UNDERC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC90029977
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Boom & MCV Hoses | 2026-10-08 | 2026-10-11 | 88 hrs | FY27 | 136 | 90032593 | A1 | 1000325062 | 23.08.2026 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC | 6700 | 19559 | 11480 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC90032593
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Boom Stick Bucket Cyl Hoses | 2026-10-08 | 2026-10-11 | 88 hrs | FY27 | 136 | 90027560 | A1 | 1000284629 | 23.08.2026 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC | 6700 | 19559 | 11480 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC90027560
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Bucket LH | 2026-10-08 | 2026-10-09 | 26 hrs | FY27 | 32 | 90027499 | A1 | 1000284609 | 03.10.2026 | 10000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYL | 6700 | 19559 | 8904 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYL90027499
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Minestar Harness | 2026-10-08 | 2026-10-09 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000370303 | 03.10.2026 | 4000 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Sprocket LH | 2026-10-08 | 2026-10-08 | 12 hrs | FY27 | 24 | 90027486 | A1 | 1000284673 | 14.01.2026 | 1500 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKL | 470 | 1756 | 1756 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKL90027486
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Sprocket RH | 2026-10-08 | 2026-10-08 | 12 hrs | FY27 | 24 | 90027486 | A1 | 1000284684 | 14.01.2026 | 1500 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKR | 470 | 1756 | 1756 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKR90027486
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Track Tension Tuning-Adjust | 2026-10-10 | 2026-10-10 | 3 hrs | FY27 | 9 | 90029977 | A1 | 1000357482 | 19.09.2026 | 6 Monthly | CLB-MP-EXCV-EX7148-UNDERC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-UNDERC90029977
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Boom Cyl | 2026-10-10 | 2026-10-10 | 8 hrs | FY27 | 24 | 90029908 | A1 | 1000357426 | 27.11.2026 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Stick Cyl | 2026-10-10 | 2026-10-10 | 12 hrs | FY27 | 24 | 90029909 | A1 | 1000357427 | 27.11.2026 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Bucket Cyl | 2026-10-10 | 2026-10-11 | 18 hrs | FY27 | 54 | 90029911 | A1 | 1000357428 | 27.11.2026 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL90029911
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hyd Motor Fan Hyd Cool Top Rr | 2026-10-12 | 2026-10-12 | 8 hrs | FY27 | 24 | 90002536 | A1 | 1000027970 | 14.10.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCTR | 7500 | 79029 | 10271 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCTR90002536
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Inspection Isolator Panel | 2026-10-13 | 2026-10-13 | 2 hrs | FY27 | 2 | 90029980 | 1 | 1000359589 | 26.09.2026 | 12 Monthly | CLB-MP-EXCV-EX7149-ELCTLV |  |  |  | CLB-MP-EXCV-EX7149-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl 24V Batteries | 2026-10-13 | 2026-10-13 | 5 hrs | FY27 | 9 | 90029978 | A1 | 1000359588 | 26.09.2026 | 12 Monthly | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST90029978
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Service Air Conditioner Sys 1 | 2026-10-13 | 2026-10-13 | 12 hrs | FY27 | 12 | 90030498 | A1 | 1000359583 | 26.09.2026 | 12 Monthly | CLB-MP-EXCV-EX7149-STRUCT-AIRC1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC190030498
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Service Air Conditioner Sys 2 | 2026-10-13 | 2026-10-13 | 12 hrs | FY27 | 12 | 90030536 | A1 | 1000359585 | 26.09.2026 | 12 Monthly | CLB-MP-EXCV-EX7149-STRUCT-AIRC2 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC290030536
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Grease Tank Level Valve | 2026-10-13 | 2026-10-13 | 2 hrs | FY27 | 2 | 90029942 | A1 | 1000359552 | 26.09.2026 | 12 Monthly | CLB-MP-EXCV-EX7149-GRSYST |  |  |  | CLB-MP-EXCV-EX7149-GRSYST90029942
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Minestar Harness | 2026-10-15 | 2026-10-16 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000369999 | 06.10.2026 | 4000 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Emergency Ladder | 2026-10-15 | 2026-10-15 | 3 hrs | FY27 | 6 | 90022513 | 1 | 1000307860 | 10.10.2026 | 24 Monthly | CLB-MP-EXCV-EX7112-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7112-STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic Oil Replacement | 2026-10-18 | 2026-10-18 | 12 hrs | FY27 | 12 | 90016793 | 1 | 1000158890 | 18.10.2026 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic System Tune Up | 2026-10-18 | 2026-10-18 | 12 hrs | FY27 | 24 | 90017865 | 1 | 1000163743 | 18.10.2026 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2026-10-18 | 2026-10-18 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237081 | 18.10.2026 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Auto Lube Pump Undercarriage | 2026-10-19 | 2026-10-19 | 10 hrs | FY27 | 10 | 90015556 | A1 | 1000169676 | 17.10.2026 | 6000 | CLB-MP-EXCV-EX108 -GRSYST-ALBPU | 7500 | 79029 | 4200 | CLB-MP-EXCV-EX108 -GRSYST-ALBPU90015556
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Main Pump to Rotor Hoses | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 24 | 90009243 | 1 | 1000074217 | 17.10.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-MPRC | 7500 | 79029 | 4200 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-MPRC90009243
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Pump Servo Pos1 | 2026-10-19 | 2026-10-19 | 2 hrs | FY27 | 2 | 90002525 | A1 | 1000027942 | 18.10.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP1 | 7500 | 79029 | 4200 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP190002525
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Pump Servo Pos2 | 2026-10-19 | 2026-10-19 | 2 hrs | FY27 | 2 | 90002525 | A1 | 1000027943 | 18.10.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP2 | 7500 | 79029 | 4200 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP290002525
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Pump Servo Pos3 | 2026-10-19 | 2026-10-19 | 2 hrs | FY27 | 2 | 90002525 | A1 | 1000027944 | 18.10.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP3 | 7500 | 79029 | 4200 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP390002525
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Pump Servo Pos4 | 2026-10-19 | 2026-10-19 | 2 hrs | FY27 | 2 | 90002525 | A1 | 1000027945 | 18.10.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP4 | 7500 | 79029 | 4200 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP490002525
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Pump Servo Pos2 | 2026-10-19 | 2026-10-19 | 2 hrs | FY27 | 2 | 90002525 | A1 | 1000028032 | 26.10.2026 | 6000 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP2 | 7500 | 86287 | 4238 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP290002525
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Alternator 24V RH Engine | 2026-10-19 | 2026-10-19 | 3 hrs | FY27 | 2 | 90004359 | 1 | 1000089305 | 26.09.2026 | 6000 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-ALTRH | 7500 | 86287 | 4965 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-ALTRH90004359
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Pump Servo Pos1 | 2026-10-19 | 2026-10-19 | 2 hrs | FY27 | 2 | 90002525 | A1 | 1000028031 | 26.09.2026 | 6000 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP1 | 7500 | 86287 | 4965 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP190002525
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Auto Lube Pump Superstructure | 2026-10-19 | 2026-10-19 | 10 hrs | FY27 | 10 | 90015555 | A1 | 1000169684 | 26.09.2026 | 6000 | CLB-MP-EXCV-EX109 -GRSYST-ALBPP | 7500 | 86287 | 4965 | CLB-MP-EXCV-EX109 -GRSYST-ALBPP90015555
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Auto Lube Pump Undercarriage | 2026-10-19 | 2026-10-19 | 10 hrs | FY27 | 10 | 90015556 | A1 | 1000169685 | 26.09.2026 | 6000 | CLB-MP-EXCV-EX109 -GRSYST-ALBPU | 7500 | 86287 | 4965 | CLB-MP-EXCV-EX109 -GRSYST-ALBPU90015556
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Fan Drive Crct Eng Cooling Hoses | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 24 | 90009239 | 1 | 1000074232 | 18.10.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-FDEC | 7500 | 86287 | 10544 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-FDEC90009239
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Swing Brake Hoses | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 8 | 90009250 | 1 | 1000074244 | 18.10.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWBRK | 7500 | 86287 | 10544 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWBRK90009250
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Swing Motor Case Drain Hoses | 2026-10-19 | 2026-10-19 | 6 hrs | FY27 | 6 | 90009252 | 1 | 1000074246 | 18.10.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWMCD | 7500 | 86287 | 10544 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWMCD90009252
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Swing Circuit Hoses | 2026-10-19 | 2026-10-19 | 13 hrs | FY27 | 23 | 90009251 | 1 | 1000074245 | 30.10.2026 | 6000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWCRT | 7500 | 86287 | 4238 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWCRT90009251
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Annual Air Con Service RH | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 12 | 90004142 | 1 | 1000155771 | 16.11.2026 | 12 Monthly | CLB-MP-EXCV-EX109 -STRUCT-CABIN-AIRCR | 7500 | 86287 | 4965 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-AIRCR90004142
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 MCV Cradle Hoses | 2026-10-19 | 2026-10-19 | 12 hrs | FY27 | 24 | 90009242 | 1 | 1000074235 | 19.11.2026 | 10000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-MCVCR | 7500 | 86287 | 7874 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-MCVCR90009242
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Servo Hoses Cascade to Bulkhead | 2026-10-19 | 2026-10-19 | 8 hrs | FY27 | 16 | 90009247 | 1 | 1000074241 | 28.11.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHBLK | 7500 | 86287 | 9687 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHBLK90009247
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Servo Hoses Cascade to Trvl Valve | 2026-10-19 | 2026-10-19 | 6 hrs | FY27 | 12 | 90009249 | 1 | 1000074243 | 28.11.2026 | 12000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHTRV | 7500 | 86287 | 9687 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHTRV90009249
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Emerg Lowering Accum | 2026-10-19 | 2026-10-19 | 3 hrs | FY27 | 3 | 90032721 | A1 | 1000324864 | 04.02.2027 | 10000 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC | 7500 | 86287 | 86287 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC90032721
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Hydraulic Ladder Accum | 2026-10-19 | 2026-10-19 | 3 hrs | FY27 | 3 | 90032720 | A1 | 1000324852 | 04.02.2027 | 10000 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC | 7500 | 86287 | 86287 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC90032720
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2026-10-20 | 2026-10-20 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359913 | 20.10.2026 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Boom Assembly | 2026-10-22 | 2026-10-27 | 116 hrs | FY27 | 324 | 90003181 | A1 | 1000231148 | 04.08.2025 | 36000 | CLB-MP-EXCV-EX014 -STRUCT-BOOMS | 6700 | 42775 | 42775 | CLB-MP-EXCV-EX014 -STRUCT-BOOMS90003181
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Stick Assembly | 2026-10-22 | 2026-10-26 | 99 hrs | FY27 | 291 | 90003183 | A1 | 1000231159 | 04.08.2025 | 36000 | CLB-MP-EXCV-EX014 -STRUCT-STICK | 6700 | 42775 | 42775 | CLB-MP-EXCV-EX014 -STRUCT-STICK90003183
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Servo Hoses Bulkhead to MCV | 2026-10-22 | 2026-10-22 | 8 hrs | FY27 | 16 | 90009479 | 1 | 1000158874 | 26.09.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHMCV | 6700 | 42775 | 10414 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHMCV90009479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Idler Track LH | 2026-10-22 | 2026-10-22 | 6 hrs | FY27 | 18 | 90003189 | A1 | 1000231309 | 02.02.2026 | 1500 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-IDLLH | 470 | 3415 | 2018 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-IDLLH90003189
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Idler Track RH | 2026-10-22 | 2026-10-22 | 6 hrs | FY27 | 18 | 90003189 | A1 | 1000231310 | 06.05.2026 | 1500 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-IDLRH | 470 | 3415 | 3415 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-IDLRH90003189
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Pos1 & Pos2 | 2026-10-22 | 2026-10-23 | 26 hrs | FY27 | 42 | 90003163 | A1 | 1000158828 | 02.11.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP1P2 | 6700 | 42775 | 9748 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP1P290003163
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Engine Midlife Complete LH | 2026-10-22 | 2026-10-24 | 54 hrs | FY27 | 76 | 90022685 | A1 | 1000236990 | 22.10.2026 | 9000 | CLB-MP-EXCV-EX7118-LHENGN | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-LHENGN90022685
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cyl Boom LH | 2026-10-23 | 2026-10-27 | 90 hrs | FY27 | 138 | 90027497 | A1 | 1000297342 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYL90027497
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cyl Boom RH | 2026-10-23 | 2026-10-27 | 90 hrs | FY27 | 138 | 90027497 | A1 | 1000297343 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYR90027497
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Oil Suction Hoses | 2026-10-23 | 2026-10-24 | 24 hrs | FY27 | 48 | 90027568 | A1 | 1000297372 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-OILSC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-OILSC90027568
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Hyd Cool Front | 2026-10-23 | 2026-10-23 | 6 hrs | FY27 | 12 | 90027504 | A1 | 1000297354 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHF | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHF90027504
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Hyd Cool Rear | 2026-10-23 | 2026-10-23 | 6 hrs | FY27 | 12 | 90027504 | A1 | 1000297355 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHR90027504
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Engine Cool LH | 2026-10-23 | 2026-10-23 | 6 hrs | FY27 | 18 | 90027505 | A1 | 1000297356 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECL90027505
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Engine Cool RH | 2026-10-23 | 2026-10-23 | 6 hrs | FY27 | 18 | 90027505 | A1 | 1000297357 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECR90027505
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Fan Engine Cool LH | 2026-10-23 | 2026-10-23 | 6 hrs | FY27 | 12 | 90027494 | A1 | 1000297336 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPL90027494
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Track Tensioner LH | 2026-10-23 | 2026-10-23 | 12 hrs | FY27 | 24 | 90027527 | A1 | 1000297389 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-TENSR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-TENSR90027527
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Track Tensioner RH | 2026-10-23 | 2026-10-23 | 12 hrs | FY27 | 24 | 90027527 | A1 | 1000297390 | 23.10.2026 | 18000 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-TENSR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-TENSR90027527
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Ovhl 24M Air Conditioner Sys1 Eng | 2026-10-25 | 2026-10-27 | 48 hrs | FY27 | 48 | 90035445 | A1 | 1000359798 | 25.10.2026 | 24 Monthly | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC1 | 6500 | 4257 | 4257 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC190035445
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Ovhl 24M Air Conditioner Sys2 Hyd | 2026-10-25 | 2026-10-26 | 36 hrs | FY27 | 36 | 90035446 | A1 | 1000359800 | 25.10.2026 | 24 Monthly | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC290035446
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Bucket RH | 2026-10-26 | 2026-10-27 | 26 hrs | FY27 | 32 | 90022647 | A1 | 1000237032 | 26.08.2026 | 10000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYR | 6700 | 25972 | 9228 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYR90022647
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Swing Circuit Hoses | 2026-10-26 | 2026-10-26 | 8 hrs | FY27 | 16 | 90022738 | A1 | 1000237064 | 02.09.2026 | 9000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT90022738
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Operators Seat | 2026-10-26 | 2026-10-26 | 2 hrs | FY27 | 2 | 90022750 | A1 | 1000237048 | 12.09.2026 | 10000 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-SEATS | 6700 | 25972 | 8861 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-SEATS90022750
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Case Drain Hoses | 2026-10-26 | 2026-10-26 | 8 hrs | FY27 | 16 | 90022729 | A1 | 1000345669 | 18.09.2026 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HPCDL | 6700 | 25948 | 13851 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HPCDL90022729
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Minestar Harness | 2026-10-26 | 2026-10-27 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000370300 | 03.11.2026 | 4000 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC90031708
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Adjust Track Tension Tuning | 2026-10-31 | 2026-10-31 | 3 hrs | FY27 | 9 | 90020545 | A1 | 1000337320 | 31.10.2026 | 6 Monthly | CLB-MP-EXCV-EX7140-UNDERC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Hydraulic Oil Replacement | 2026-10-31 | 2026-10-31 | 12 hrs | FY27 | 12 | 90016793 | 1 | 1000207153 | 31.10.2026 | 6000 | CLB-MP-EXCV-EX7112-HYDSYS | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Pump to Rotor Hose | 2026-11-01 | 2026-11-02 | 24 hrs | FY27 | 48 | 90027567 | A1 | 1000297371 | 01.11.2026 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-MPRCH | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-MPRCH90027567
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Servo Hose Bulkhead to MCV | 2026-11-01 | 2026-11-01 | 8 hrs | FY27 | 16 | 90027574 | A1 | 1000297377 | 01.11.2026 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHMCV | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHMCV90027574
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Engine Cat C32 | 2026-11-02 | 2026-11-09 | 176.5 hrs | FY27 | 254.5 | 90027534 | A1 | 1000297278 | 09.10.2026 | 18000 | CLB-MP-EXCV-EX7122-RHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN90027534
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Drive Gearbox RH | 2026-11-02 | 2026-11-03 | 40 hrs | FY27 | 116 | 90027489 | A1 | 1000297329 | 28.10.2026 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRR90027489
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Adjust 500hr Initial Valve Set | 2026-11-02 | 2026-11-02 | 10 hrs | FY27 | 20 | 90027550 | A1 | 1000297279 | 03.11.2026 | 500 | CLB-MP-EXCV-EX7122-RHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN90027550
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Radiator RH Engine Cooling | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 12 | 90027553 | A1 | 1000297322 | 28.10.2026 | 18000 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-RADTR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-RADTR90027553
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl RH Aftercooler | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 24 | 90023360 | A1 | 1000309289 | 28.10.2026 | 18000 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-AFTER | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-AFTER90023360
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Bucket RH | 2026-11-02 | 2026-11-03 | 30 hrs | FY27 | 54 | 90029967 | A1 | 1000304624 | 01.11.2026 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYR | 6200 | 13908 | 8495 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYR90029967
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Inspection Ext Static Line | 2026-11-02 | 2026-11-02 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000304563 | 20.11.2026 | 6 Monthly | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029897
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Grease Tank Level Valve | 2026-11-02 | 2026-11-02 | 2 hrs | FY27 | 2 | 90029942 | A1 | 1000304596 | 22.11.2026 | 12 Monthly | CLB-MP-EXCV-EX7133-GRSYST |  |  |  | CLB-MP-EXCV-EX7133-GRSYST90029942
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Auto Lube SStructure | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 12 | 90018988 | 1 | 1000207165 | 02.11.2026 | 6000 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP90018988
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Hydraulic System Tune Up | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 24 | 90017865 | 1 | 1000207164 | 02.11.2026 | 6000 | CLB-MP-EXCV-EX7112-HYDSYS | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Boom Arch Hoses | 2026-11-02 | 2026-11-02 | 12 hrs | FY27 | 24 | 90022724 | A1 | 1000237181 | 30.05.2026 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-BMARH | 6700 | 27054 | 11930 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-BMARH90022724
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel LHF | 2026-11-02 | 2026-11-02 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237174 | 28.10.2026 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLF | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel LHR | 2026-11-02 | 2026-11-02 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237175 | 28.10.2026 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLR | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel RHF | 2026-11-02 | 2026-11-02 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237176 | 28.10.2026 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRF | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel RHR | 2026-11-02 | 2026-11-02 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000237177 | 28.10.2026 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRR | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Fan Drive Hyd Cooling Hoses | 2026-11-07 | 2026-11-08 | 18 hrs | FY27 | 36 | 90027565 | A1 | 1000284631 | 07.11.2026 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDHCH | 6700 | 19559 | 10250 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDHCH90027565
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hydraulic Cooling Circ Hoses | 2026-11-07 | 2026-11-08 | 18 hrs | FY27 | 36 | 90031704 | A1 | 1000284632 | 07.11.2026 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HCCHH | 6700 | 19559 | 10250 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HCCHH90031704
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Track Tensioning Hoses | 2026-11-07 | 2026-11-07 | 3 hrs | FY27 | 3 | 90027579 | A1 | 1000284645 | 07.11.2026 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TRTNH | 6700 | 19559 | 10250 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TRTNH90027579
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 12M Inspection Isolator Panel | 2026-11-07 | 2026-11-07 | 2 hrs | FY27 | 2 | 90022525 | A2 | 1000336837 | 07.11.2026 | 12 Monthly | CLB-MP-EXCV-EX7140-ELCTLV |  |  |  | CLB-MP-EXCV-EX7140-ELCTLV90022525
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 12M Inspection Isolator Panel | 2026-11-07 | 2026-11-07 | 2 hrs | FY27 | 2 | 90022525 | A2 | 1000330357 | 07.11.2026 | 12 Monthly | CLB-MP-EXCV-EX7139-ELCTLV |  |  |  | CLB-MP-EXCV-EX7139-ELCTLV90022525
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 12M Hydraulic Service & Repairs | 2026-11-09 | 2026-11-10 | 18 hrs | FY27 | 30 | 90014448 | A1 | 1000330356 | 13.10.2026 | 12 Monthly | CLB-MP-EXCV-EX7139-HYDSYS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS90014448
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Static Line Inspection | 2026-11-10 | 2026-11-10 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000340340 | 10.11.2026 | 6 Monthly | CLB-MP-EXCV-EX7138-STRUCT | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT90014347
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Hydraulic System Tune Up | 2026-11-12 | 2026-11-12 | 12 hrs | FY27 | 24 | 90017867 | 1 | 1000163741 | 11.11.2026 | 5000 | CLB-MP-EXCV-EX108 -HYDSYS | 7500 | 79029 | 7920 | CLB-MP-EXCV-EX108 -HYDSYS90017867
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2026-11-13 | 2026-11-13 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359909 | 13.11.2026 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl PMS Proportional Valves | 2026-11-13 | 2026-11-13 | 6 hrs | FY27 | 6 | 90018173 | A1 | 1000170088 | 13.11.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-PROVV | 7500 | 79029 | 9644 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-PROVV90018173
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel LHF | 2026-11-14 | 2026-11-14 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000207124 | 14.11.2026 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLF | 6700 | 31524 | 9874 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLF90022657
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 2nd Speed Trvl/Brake Release Hoses | 2026-11-15 | 2026-11-15 | 6 hrs | FY27 | 12 | 90009236 | 1 | 1000074192 | 15.11.2026 | 10000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-2STBR | 7500 | 86684 | 7767 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-2STBR90009236
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Power Pack Module Midlife | 2026-11-16 | 2026-11-26 | 247.5 hrs | FY27 | 309.5 | 90031019 | A1 | 1000348537 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90031019
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Auto Lube Pump P1 | 2026-11-16 | 2026-11-16 | 2 hrs | FY27 | 2 | 90035369 | A1 | 1000348394 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBPP | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBPP90035369
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Grease Injectors | 2026-11-16 | 2026-11-18 | 48 hrs | FY27 | 84 | 90030744 | A1 | 1000348550 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ90030744
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Bucket LH Lift | 2026-11-16 | 2026-11-17 | 30 hrs | FY27 | 54 | 90030725 | A1 | 1000348544 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYL | 6200 | 8353 | 3074 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYL90030725
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Rotary Connection Hoses | 2026-11-16 | 2026-11-18 | 48 hrs | FY27 | 96 | 90030432 | A1 | 1000348585 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF |  |  |  | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF90030432
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Hyd Vlve Bank Module Quarter Life | 2026-11-16 | 2026-11-16 | 9 hrs | FY27 | 15 | 90027371 | A1 | 1000348527 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVLU | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVLU90027371
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Operators Seat | 2026-11-16 | 2026-11-16 | 9 hrs | FY27 | 17 | 90030739 | A1 | 1000348535 | 29.10.2026 | 10000 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-SEATO | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-SEATO90030739
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Grease Tank Level Valve | 2026-11-17 | 2026-11-17 | 2 hrs | FY27 | 2 | 90015003 | A1 | 1000337280 | 17.11.2026 | 12 Monthly | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK90015003
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Inspection Isolator Panel | 2026-11-22 | 2026-11-22 | 2 hrs | FY27 | 2 | 90029980 | 1 | 1000304631 | 22.11.2026 | 12 Monthly | CLB-MP-EXCV-EX7133-ELCTLV |  |  |  | CLB-MP-EXCV-EX7133-ELCTLV90029980
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hyd Motor Fan Hyd Cool Bot Rr | 2026-11-22 | 2026-11-22 | 8 hrs | FY27 | 24 | 90002536 | A1 | 1000027968 | 22.11.2026 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCBR | 7500 | 79029 | 9620 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCBR90002536
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Grease Tank Level Valve | 2026-11-24 | 2026-11-24 | 2 hrs | FY27 | 2 | 90015003 | A1 | 1000340303 | 24.11.2026 | 12 Monthly | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK | 6200 | 9369 | 2810 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK90015003
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Repl Valves Swing Blocking | 2026-11-24 | 2026-11-24 | 6 hrs | FY27 | 6 | 90018174 | A1 | 1000170084 | 24.11.2026 | 36000 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SWBVV | 7500 | 86684 | 33656 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SWBVV90018174
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Hydraulic Oil Replacement | 2026-11-26 | 2026-11-26 | 12 hrs | FY27 | 12 | 90016793 | 1 | 1000297387 | 26.11.2026 | 6000 | CLB-MP-EXCV-EX7122-HYDSYS | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Hydraulic System Tune Up | 2026-11-26 | 2026-11-26 | 12 hrs | FY27 | 24 | 90017865 | 1 | 1000297397 | 26.11.2026 | 6000 | CLB-MP-EXCV-EX7122-HYDSYS | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS90017865
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Ovhl 24M Air Conditioner Sys1 Eng | 2026-11-28 | 2026-11-30 | 48 hrs | FY27 | 48 | 90035243 | A1 | 1000359810 | 28.11.2026 | 24 Monthly | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC1 | 6000 | 3940 | 3940 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC190035243
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Ovhl 24M Air Conditioner Sys2 Hyd | 2026-11-28 | 2026-11-29 | 36 hrs | FY27 | 36 | 90035267 | A1 | 1000359812 | 28.11.2026 | 24 Monthly | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC290035267
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Inspection Ext Static Line | 2026-11-28 | 2026-11-28 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000359517 | 28.11.2026 | 6 Monthly | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Idler Track LH | 2026-11-29 | 2026-11-29 | 6 hrs | FY27 | 18 | 90027507 | A1 | 1000297402 | 29.11.2026 | 1500 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-IDLLH | 470 | 1344 | 1344 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-IDLLH90027507
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Idler Track RH | 2026-11-29 | 2026-11-29 | 6 hrs | FY27 | 18 | 90027507 | A1 | 1000297413 | 29.11.2026 | 1500 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-IDLRH | 470 | 1344 | 1344 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-IDLRH90027507
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Sprocket LH | 2026-11-29 | 2026-11-29 | 12 hrs | FY27 | 24 | 90027486 | A1 | 1000297410 | 29.11.2026 | 1500 | CLB-MP-EXCV-EX7122-TRAVEL-SPRKL | 470 | 1344 | 1344 | CLB-MP-EXCV-EX7122-TRAVEL-SPRKL90027486
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Sprocket RH | 2026-11-29 | 2026-11-29 | 12 hrs | FY27 | 24 | 90027486 | A1 | 1000297421 | 29.11.2026 | 1500 | CLB-MP-EXCV-EX7122-TRAVEL-SPRKR | 470 | 1344 | 1344 | CLB-MP-EXCV-EX7122-TRAVEL-SPRKR90027486
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2026-11-29 | 2026-11-29 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359910 | 29.11.2026 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Auto Lube Pump | 2026-11-29 | 2026-11-29 | 6 hrs | FY27 | 6 | 90022747 | A1 | 1000237215 | 29.11.2026 | 6000 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP90022747
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Engine Midlife Complete RH | 2026-11-30 | 2026-12-02 | 54 hrs | FY27 | 76 | 90018424 | A1 | 1000158813 | 03.11.2026 | 9000 | CLB-MP-EXCV-EX014 -RHENGN | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -RHENGN90018424
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2026-12-01 | 2026-12-01 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000337317 | 01.12.2026 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2026-12-03 | 2026-12-03 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237212 | 03.12.2026 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Track Tension Tuning-Adjust | 2026-12-04 | 2026-12-04 | 3 hrs | FY27 | 9 | 90020545 | A1 | 1000340343 | 04.12.2026 | 6 Monthly | CLB-MP-EXCV-EX7138-UNDERC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2026-12-04 | 2026-12-04 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000348588 | 04.12.2026 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2026-12-04 | 2026-12-04 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000330578 | 04.12.2026 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Wiper Blades | 2026-12-06 | 2026-12-06 | 2 hrs | FY27 | 2 | 90004684 | 1 | 1000163162 | 06.12.2026 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX014 -STRUCT-CABIN90004684
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Emergency Ladder | 2026-12-07 | 2026-12-07 | 3 hrs | FY27 | 6 | 90022513 | 1 | 1000309303 | 21.12.2026 | 24 Monthly | CLB-MP-EXCV-EX7122-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7122-STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Fan Drive Eng Cooling Hose | 2026-12-07 | 2026-12-08 | 18 hrs | FY27 | 36 | 90027564 | A1 | 1000284630 | 07.12.2026 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDECH | 6700 | 19559 | 9696 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDECH90027564
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Inspection Ext Static Line | 2026-12-09 | 2026-12-09 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000357332 | 09.12.2026 | 6 Monthly | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029897
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Batteries | 2026-12-09 | 2026-12-09 | 5 hrs | FY27 | 9 | 90017122 | A1 | 1000337269 | 09.12.2026 | 12 Monthly | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST | 6200 | 10954 | 3519 | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST90017122
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Minestar Harness | 2026-12-09 | 2026-12-10 | 27.5 hrs | FY27 | 43.5 | 90030746 | A1 | 1000348553 | 09.12.2026 | 5000 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC90030746
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Minestar Harness | 2026-12-10 | 2026-12-11 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000370301 | 10.12.2026 | 4000 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC90031708
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Hyd Oil | 2026-12-11 | 2026-12-11 | 12 hrs | FY27 | 12 | 90016794 | 1 | 1000151398 | 08.12.2026 | 5000 | CLB-MP-EXCV-EX108 -HYDSYS | 7500 | 79029 | 7920 | CLB-MP-EXCV-EX108 -HYDSYS90016794
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Track Tension Tuning-Adjust | 2026-12-12 | 2026-12-12 | 3 hrs | FY27 | 9 | 90029977 | A1 | 1000359587 | 12.12.2026 | 6 Monthly | CLB-MP-EXCV-EX7149-UNDERC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-UNDERC90029977
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Accumulator Track Hyd RH | 2026-12-12 | 2026-12-12 | 2 hrs | FY27 | 2 | 90002539 | A2 | 1000170013 | 12.12.2026 | 18000 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC-HACCR | 7500 | 79029 | 14990 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC-HACCR90002539
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Boom LH | 2026-12-14 | 2026-12-16 | 42 hrs | FY27 | 78 | 90029951 | A1 | 1000304619 | 08.12.2026 | 16000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BMCYL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BMCYL90029951
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Boom RH | 2026-12-14 | 2026-12-16 | 42 hrs | FY27 | 78 | 90029951 | A1 | 1000304620 | 08.12.2026 | 16000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BMCYR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BMCYR90029951
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Stick LH | 2026-12-14 | 2026-12-15 | 30 hrs | FY27 | 54 | 90029971 | A1 | 1000304621 | 08.12.2026 | 16000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-STCLL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-STCLL90029971
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Stick RH | 2026-12-14 | 2026-12-15 | 30 hrs | FY27 | 54 | 90029971 | A1 | 1000304622 | 08.12.2026 | 16000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-STCLR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-STCLR90029971
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Adjust 500hr Initial Valve Set | 2026-12-15 | 2026-12-15 | 10 hrs | FY27 | 20 | 90022680 | A1 | 1000237134 | 15.12.2026 | 500 | CLB-MP-EXCV-EX7119-RHENGN | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-RHENGN90022680
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Wiper Blades | 2026-12-17 | 2026-12-17 | 1 hr | FY27 | 1 | 90027557 | A1 | 1000297393 | 17.12.2026 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7122-STRUCT-CABIN90027557
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Final Drive LH | 2026-12-21 | 2026-12-23 | 48 hrs | FY27 | 144 | 90022634 | A1 | 1000237008 | 31.03.2026 | 24000 | CLB-MP-EXCV-EX7118-TRAVEL-FDRLH | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-TRAVEL-FDRLH90022634
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Final Drive RH | 2026-12-21 | 2026-12-23 | 48 hrs | FY27 | 144 | 90022634 | A1 | 1000237009 | 31.03.2026 | 24000 | CLB-MP-EXCV-EX7118-TRAVEL-FDRRH | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-TRAVEL-FDRRH90022634
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Emergency Ladder | 2026-12-24 | 2026-12-24 | 3 hrs | FY27 | 6 | 90022513 | 1 | 1000235857 | 24.12.2026 | 24 Monthly | CLB-MP-EXCV-EX014 -STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX014 -STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Rotor to Drive Motor Hoses | 2026-12-26 | 2026-12-26 | 10 hrs | FY27 | 20 | 90009476 | A2 | 1000158871 | 26.12.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCDMH | 6700 | 42775 | 8761 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCDMH90009476
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Travel Motor Case Drain Hoses | 2026-12-26 | 2026-12-26 | 5 hrs | FY27 | 10 | 90009483 | A2 | 1000158878 | 26.12.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TMCDH | 6700 | 42775 | 32631 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TMCDH90009483
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel RHR | 2026-12-26 | 2026-12-26 | 6 hrs | FY27 | 12 | 90003178 | A1 | 1000158855 | 26.12.2026 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRR | 6700 | 42775 | 21181 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRR90003178
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Repl Wiper Blades | 2026-12-27 | 2026-12-27 | 2 hrs | FY27 | 2 | 90004683 | 1 | 1000049864 | 27.12.2026 | 12 Monthly | CLB-MP-EXCV-EX107 -STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX107 -STRUCT-CABIN90004683
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Servo Hoses Bulkhead to MCV | 2026-12-30 | 2026-12-30 | 8 hrs | FY27 | 16 | 90009248 | 1 | 1000074222 | 30.12.2026 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHMCV | 7500 | 79029 | 2675 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHMCV90009248
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Minestar Harness | 2027-01-01 | 2027-01-02 | 27.5 hrs | FY27 | 43.5 | 90029998 | A1 | 1000357494 | 01.01.2027 | 4000 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC90029998
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Batteries | 2027-01-02 | 2027-01-02 | 5 hrs | FY27 | 9 | 90017122 | A1 | 1000348540 | 02.01.2027 | 12 Monthly | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST | 6200 | 8353 | 3485 | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST90017122
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Annual Air Con Service LH | 2027-01-03 | 2027-01-03 | 12 hrs | FY27 | 12 | 90004142 | 1 | 1000045371 | 03.01.2027 | 12 Monthly | CLB-MP-EXCV-EX109 -STRUCT-CABIN-AIRCL | 7500 | 27286 | 4238 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-AIRCL90004142
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Adjust 4500hr Valve Set | 2027-01-04 | 2027-01-04 | 10 hrs | FY27 | 20 | 90027549 | A1 | 1000284516 | 04.01.2027 | 4500 | CLB-MP-EXCV-EX7124-LHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-LHENGN90027549
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Adjust 4500hr Valve Set | 2027-01-04 | 2027-01-04 | 10 hrs | FY27 | 20 | 90027549 | A1 | 1000284582 | 04.01.2027 | 4500 | CLB-MP-EXCV-EX7124-RHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-RHENGN90027549
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Repl Accumulator Track Hyd LH | 2027-01-06 | 2027-01-06 | 2 hrs | FY27 | 2 | 90002539 | A1 | 1000170011 | 06.01.2027 | 18000 | CLB-MP-EXCV-EX107 -HYDSYS-HDACC-HACCL | 7500 | 86684 | 14652 | CLB-MP-EXCV-EX107 -HYDSYS-HDACC-HACCL90002539
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Repl Accumulator Track Hyd RH | 2027-01-06 | 2027-01-06 | 2 hrs | FY27 | 2 | 90002539 | A1 | 1000170010 | 06.01.2027 | 18000 | CLB-MP-EXCV-EX107 -HYDSYS-HDACC-HACCR | 7500 | 86684 | 14652 | CLB-MP-EXCV-EX107 -HYDSYS-HDACC-HACCR90002539
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Swing Circuit Hoses | 2027-01-07 | 2027-01-07 | 8 hrs | FY27 | 16 | 90022738 | A1 | 1000237195 | 07.01.2027 | 9000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWCRT | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWCRT90022738
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Hose Boom Cyl | 2027-01-08 | 2027-01-08 | 8 hrs | FY27 | 24 | 90029908 | A1 | 1000359531 | 08.01.2027 | 8000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Hose Stick Cyl | 2027-01-08 | 2027-01-08 | 12 hrs | FY27 | 24 | 90029909 | A1 | 1000359532 | 08.01.2027 | 8000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSTCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Hose Bucket Cyl | 2027-01-08 | 2027-01-09 | 18 hrs | FY27 | 54 | 90029911 | A1 | 1000359533 | 08.01.2027 | 8000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBKCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBKCL90029911
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Minestar Harness | 2027-01-08 | 2027-01-09 | 27.5 hrs | FY27 | 43.5 | 90029998 | A1 | 1000359599 | 08.01.2027 | 4000 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC90029998
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 12M Inspection Isolator Panel | 2027-01-09 | 2027-01-09 | 2 hrs | FY27 | 2 | 90022525 | A2 | 1000315896 | 09.01.2027 | 12 Monthly | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | 6200 | 9369 | 1820 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST90022525
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Auto Lube Pump | 2027-01-09 | 2027-01-09 | 6 hrs | FY27 | 6 | 90022747 | A1 | 1000237084 | 09.01.2027 | 6000 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP90022747
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Hydraulic Oil Replacement | 2027-01-09 | 2027-01-09 | 12 hrs | FY27 | 12 | 90022667 | A1 | 1000237072 | 09.01.2027 | 6000 | CLB-MP-EXCV-EX7118-HYDSYS | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS90022667
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Pump to Rotor Hoses | 2027-01-09 | 2027-01-10 | 24 hrs | FY27 | 48 | 90022730 | A1 | 1000345670 | 09.01.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-MPRCH | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-MPRCH90022730
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Swing LHR | 2027-01-10 | 2027-01-11 | 21 hrs | FY27 | 27 | 90022654 | A1 | 1000237167 | 10.01.2027 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMLR | 6700 | 27054 | 11941 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMLR90022654
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Swing RHF | 2027-01-10 | 2027-01-11 | 21 hrs | FY27 | 27 | 90022654 | A1 | 1000237168 | 10.01.2027 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRF | 6700 | 27054 | 11930 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRF90022654
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Swing RHR | 2027-01-10 | 2027-01-11 | 21 hrs | FY27 | 27 | 90022654 | A1 | 1000237169 | 10.01.2027 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRR | 6700 | 27054 | 11930 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRR90022654
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2027-01-12 | 2027-01-12 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359913 | 12.01.2027 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Final Drive LH | 2027-01-15 | 2027-01-17 | 48 hrs | FY27 | 144 | 90022634 | A1 | 1000207089 | 15.01.2027 | 24000 | CLB-MP-EXCV-EX7112-TRAVEL-FDRLH | 6700 | 31524 | 304 | CLB-MP-EXCV-EX7112-TRAVEL-FDRLH90022634
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Final Drive RH | 2027-01-15 | 2027-01-17 | 48 hrs | FY27 | 144 | 90022634 | A1 | 1000207090 | 15.01.2027 | 24000 | CLB-MP-EXCV-EX7112-TRAVEL-FDRRH | 6700 | 31524 | 20738 | CLB-MP-EXCV-EX7112-TRAVEL-FDRRH90022634
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Boom Module Quarter Life | 2027-01-16 | 2027-01-17 | 30 hrs | FY27 | 48 | 90029992 | A1 | 1000357492 | 16.01.2027 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029992
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Auto Lube Pump Superstructure | 2027-01-18 | 2027-01-18 | 12 hrs | FY27 | 12 | 90018988 | 1 | 1000190276 | 18.01.2027 | 6000 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP90018988
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Minestar Harness | 2027-01-19 | 2027-01-20 | 27.5 hrs | FY27 | 43.5 | 90029998 | A1 | 1000304641 | 19.01.2027 | 4000 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC90029998
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Accumulator Track Hyd LH | 2027-01-19 | 2027-01-19 | 2 hrs | FY27 | 2 | 90002539 | A1 | 1000170014 | 19.01.2027 | 18000 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC-HACCL | 7500 | 86287 | 14649 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC-HACCL90002539
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Hose Stick Cyl | 2027-01-21 | 2027-01-21 | 12 hrs | FY27 | 24 | 90030737 | A1 | 1000340277 | 21.01.2027 | 8000 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HSTCL | 6200 | 9369 | 4227 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HSTCL90030737
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 MCV Cradle Hoses | 2027-01-24 | 2027-01-24 | 12 hrs | FY27 | 24 | 90009242 | 1 | 1000074216 | 24.01.2027 | 10000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-MCVCR | 7500 | 79029 | 6162 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-MCVCR90009242
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Batteries | 2027-01-24 | 2027-01-24 | 8 hrs | FY27 | 8 | 90016788 | 1 | 1000152456 | 24.01.2027 | 10000 | CLB-MP-EXCV-EX108 -ELCTLV-CHARG-BATTY | 7500 | 79029 | 6162 | CLB-MP-EXCV-EX108 -ELCTLV-CHARG-BATTY90016788
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Travel LHF | 2027-01-25 | 2027-01-25 | 8 hrs | FY27 | 14 | 90027506 | A1 | 1000297358 | 25.01.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLF | 6700 | 16452 | 8735 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLF90027506
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Hydraulic System Tune Up | 2027-01-26 | 2027-01-26 | 12 hrs | FY27 | 24 | 90017867 | 1 | 1000163742 | 23.01.2027 | 5000 | CLB-MP-EXCV-EX109 -HYDSYS | 7500 | 86287 | 1478 | CLB-MP-EXCV-EX109 -HYDSYS90017867
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Swing LHR | 2027-01-26 | 2027-01-27 | 21 hrs | FY27 | 27 | 90022654 | A1 | 1000237036 | 26.01.2027 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMLR | 6700 | 25972 | 11422 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMLR90022654
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Swing RHF | 2027-01-26 | 2027-01-27 | 21 hrs | FY27 | 27 | 90022654 | A1 | 1000237037 | 26.01.2027 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRF | 6700 | 25972 | 11422 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRF90022654
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Swing RHR | 2027-01-26 | 2027-01-27 | 21 hrs | FY27 | 27 | 90022654 | A1 | 1000237038 | 26.01.2027 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRR | 6700 | 25972 | 11422 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRR90022654
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Engine Cat C32 | 2027-01-27 | 2027-02-03 | 174.5 hrs | FY27 | 252.5 | 90022671 | A1 | 1000236993 | 27.01.2027 | 18000 | CLB-MP-EXCV-EX7118-RHENGN | 6700 | 25972 | 14409 | CLB-MP-EXCV-EX7118-RHENGN90022671
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Swing LHR | 2027-01-28 | 2027-01-29 | 21 hrs | FY27 | 27 | 90003175 | A1 | 1000158845 | 28.01.2027 | 15000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMLR | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMLR90003175
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Swing RHF | 2027-01-28 | 2027-01-29 | 21 hrs | FY27 | 27 | 90003175 | A1 | 1000158846 | 28.01.2027 | 15000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRF | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRF90003175
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Servo Hoses Cascade to Bulkhead | 2027-02-01 | 2027-02-01 | 8 hrs | FY27 | 16 | 90009478 | 1 | 1000158873 | 01.02.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHBLK | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHBLK90009478
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Pos3 & Pos4 | 2027-02-01 | 2027-02-02 | 26 hrs | FY27 | 42 | 90003163 | A1 | 1000158829 | 01.02.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP3P4 | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP3P490003163
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Minestar Harness | 2027-02-03 | 2027-02-04 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000312852 | 03.02.2027 | 4000 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC90031708
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Boom arch hoses | 2027-02-04 | 2027-02-04 | 10 hrs | FY27 | 20 | 90009237 | 1 | 1000074211 | 04.02.2027 | 6000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-BMAR | 7500 | 79029 | 6162 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-BMAR90009237
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 MCV Cradle Hoses | 2027-02-04 | 2027-02-04 | 12 hrs | FY27 | 24 | 90009242 | 1 | 1000074197 | 04.02.2027 | 10000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MCVCR | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MCVCR90009242
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Hydraulic Oil Replacement | 2027-02-05 | 2027-02-05 | 12 hrs | FY27 | 12 | 90016793 | 1 | 1000284650 | 05.02.2027 | 6000 | CLB-MP-EXCV-EX7124-HYDSYS | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Hydraulic System Tune Up | 2027-02-05 | 2027-02-05 | 12 hrs | FY27 | 24 | 90017865 | 1 | 1000284660 | 05.02.2027 | 6000 | CLB-MP-EXCV-EX7124-HYDSYS | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS90017865
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 12M Hydraulic Service & Repairs | 2027-02-08 | 2027-02-09 | 18 hrs | FY27 | 30 | 90014448 | A1 | 1000336836 | 08.02.2027 | 12 Monthly | CLB-MP-EXCV-EX7140-HYDSYS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Minestar Harness | 2027-02-09 | 2027-02-10 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000370302 | 09.02.2027 | 4000 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Gearbox Swing LHR | 2027-02-09 | 2027-02-11 | 50 hrs | FY27 | 82 | 90027580 | A1 | 1000297325 | 09.02.2027 | 20000 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBLR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBLR90027580
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Gearbox Swing RHF | 2027-02-09 | 2027-02-11 | 50 hrs | FY27 | 82 | 90027580 | A1 | 1000297326 | 09.02.2027 | 20000 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBRF | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBRF90027580
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Gearbox Swing RHR | 2027-02-09 | 2027-02-11 | 50 hrs | FY27 | 82 | 90027580 | A1 | 1000297327 | 09.02.2027 | 20000 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBRR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBRR90027580
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2027-02-10 | 2027-02-10 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359909 | 10.02.2027 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Grease System Audit | 2027-02-10 | 2027-02-11 | 24 hrs | FY27 | 36 | 90030748 | A1 | 1000330538 | 10.02.2027 | 5000 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ90030748
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl 24V Batteries | 2027-02-12 | 2027-02-12 | 5 hrs | FY27 | 9 | 90029978 | A1 | 1000304630 | 12.02.2027 | 12 Monthly | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST | 6200 | 13908 | 8694 | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST90029978
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Repl Emergency Ladder | 2027-02-12 | 2027-02-12 | 3 hrs | FY27 | 6 | 90022515 | 1 | 1000235961 | 12.02.2027 | 24 Monthly | CLB-MP-EXCV-EX108 -STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX108 -STRUCT-STLAD-SLFXD90022515
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Engine Midlife Complete LH | 2027-02-12 | 2027-02-14 | 54 hrs | FY27 | 76 | 90022685 | A1 | 1000237121 | 12.02.2027 | 9000 | CLB-MP-EXCV-EX7119-LHENGN | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-LHENGN90022685
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Power Pack Module Qtr Life | 2027-02-15 | 2027-02-15 | 1 hr | FY27 | 1 | 90027378 | A1 | 1000337268 | 15.02.2027 | 5000 | CLB-MP-EXCV-EX7140-ENGINE | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-ENGINE90027378
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2027-02-15 | 2027-02-15 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237081 | 15.02.2027 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Wiper Blades | 2027-02-16 | 2027-02-16 | 2 hrs | FY27 | 2 | 90004683 | 1 | 1000049866 | 16.02.2027 | 12 Monthly | CLB-MP-EXCV-EX109 -STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX109 -STRUCT-CABIN90004683
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Batteries | 2027-02-18 | 2027-02-18 | 5 hrs | FY27 | 9 | 90017122 | A1 | 1000340292 | 18.02.2027 | 12 Monthly | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | 6200 | 9369 | 1820 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST90017122
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Hose Bucket Cyl | 2027-02-18 | 2027-02-19 | 18 hrs | FY27 | 54 | 90030738 | A1 | 1000340276 | 18.02.2027 | 8000 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBKCL | 6200 | 9369 | 3729 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Hose Boom Cyl | 2027-02-18 | 2027-02-18 | 8 hrs | FY27 | 24 | 90030735 | A1 | 1000340275 | 18.02.2027 | 8000 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBMCL | 6200 | 9369 | 3729 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBMCL90030735
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Rotor to Drive Motor Hoses | 2027-02-21 | 2027-02-22 | 20 hrs | FY27 | 40 | 90027570 | A1 | 1000284637 | 21.02.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCDMH | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCDMH90027570
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 2nd Speed Trvl Brake Release Hose | 2027-02-21 | 2027-02-21 | 5 hrs | FY27 | 10 | 90027559 | A1 | 1000284627 | 21.02.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SSTBR | 6700 | 19559 | 8190 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SSTBR90027559
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Swing Motor Case Drain Hoses | 2027-02-21 | 2027-02-21 | 6 hrs | FY27 | 12 | 90027577 | A1 | 1000284643 | 21.02.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWMCD | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWMCD90027577
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Travel Motor Case Drain Hoses | 2027-02-21 | 2027-02-21 | 5 hrs | FY27 | 10 | 90027578 | A1 | 1000284644 | 21.02.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TMCDH | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TMCDH90027578
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 6M Anritsu Test WiFi Cables | 2027-02-21 | 2027-02-21 | 2 hrs | FY27 | 2 | 90020303 | A1 | 1000210997 | 21.02.2027 | 6 Monthly | CLB-MP-EXCV-EX7112-COMMUN-FLMGT |  |  |  | CLB-MP-EXCV-EX7112-COMMUN-FLMGT90020303
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Service Air Conditioner Sys 1 | 2027-02-22 | 2027-02-22 | 12 hrs | FY27 | 12 | 90030498 | A1 | 1000304627 | 22.02.2027 | 12 Monthly | CLB-MP-EXCV-EX7133-STRUCT-AIRC1 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC190030498
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Service Air Conditioner Sys 2 | 2027-02-22 | 2027-02-22 | 12 hrs | FY27 | 12 | 90030536 | A1 | 1000304724 | 22.02.2027 | 12 Monthly | CLB-MP-EXCV-EX7133-STRUCT-AIRC2 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC290030536
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cyl Boom LH | 2027-02-22 | 2027-02-26 | 90 hrs | FY27 | 138 | 90003167 | A1 | 1000207108 | 22.02.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BMCYL | 6700 | 31524 | 14047 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BMCYL90003167
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Pump Drive Gearbox RH | 2027-02-22 | 2027-02-23 | 36 hrs | FY27 | 108 | 90003161 | A1 | 1000207095 | 22.02.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-PPDRR | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-HYDSYS-PPDRR90003161
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Radiator RH Engine | 2027-02-22 | 2027-02-22 | 12 hrs | FY27 | 24 | 90017957 | A1 | 1000207087 | 22.02.2027 | 18000 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-RADTR | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-RADTR90017957
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Adjust 500hr Initial Valve Set | 2027-02-23 | 2027-02-23 | 10 hrs | FY27 | 20 | 90022680 | A1 | 1000237003 | 23.02.2027 | 500 | CLB-MP-EXCV-EX7118-RHENGN | 6700 | 25972 | 14409 | CLB-MP-EXCV-EX7118-RHENGN90022680
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Engine Midlife Complete LH | 2027-02-24 | 2027-02-26 | 54 hrs | FY27 | 76 | 90018424 | A1 | 1000158798 | 24.02.2027 | 9000 | CLB-MP-EXCV-EX014 -LHENGN | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -LHENGN90018424
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Operators Seat | 2027-02-26 | 2027-02-26 | 2 hrs | FY27 | 2 | 90027613 | A1 | 1000297363 | 26.02.2027 | 10000 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-SEATS | 6700 | 16452 | 6191 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-SEATS90027613
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2027-02-26 | 2027-02-26 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359910 | 26.02.2027 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Batteries | 2027-02-26 | 2027-02-26 | 8 hrs | FY27 | 8 | 90022665 | A1 | 1000237073 | 26.02.2027 | 10000 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-BATTY | 6700 | 25972 | 5056 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-BATTY90022665
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Bucket RH | 2027-02-28 | 2027-03-01 | 26 hrs | FY27 | 32 | 90022647 | A1 | 1000237163 | 28.02.2027 | 10000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYR | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYR90022647
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Wiper Blades | 2027-03-01 | 2027-03-01 | 2 hrs | FY27 | 2 | 90022722 | A1 | 1000237209 | 01.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7119-STRUCT-CABIN90022722
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 12M Hydraulic Service & Repairs | 2027-03-05 | 2027-03-06 | 18 hrs | FY27 | 30 | 90014448 | A1 | 1000340261 | 05.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7138-HYDSYS | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Batteries | 2027-03-05 | 2027-03-05 | 8 hrs | FY27 | 8 | 90016788 | 1 | 1000158891 | 05.03.2027 | 10000 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-BATTY | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-BATTY90016788
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service RH | 2027-03-05 | 2027-03-05 | 12 hrs | FY27 | 12 | 90022660 | A1 | 1000237077 | 05.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR | 6700 | 25972 | 6562 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR90022660
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Wiper Blades | 2027-03-06 | 2027-03-06 | 2 hrs | FY27 | 2 | 90022722 | A1 | 1000237078 | 06.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7118-STRUCT-CABIN90022722
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Annual Air Con Service LH | 2027-03-07 | 2027-03-07 | 12 hrs | FY27 | 12 | 90027615 | A1 | 1000297422 | 07.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL90027615
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Annual Air Con Service RH | 2027-03-07 | 2027-03-07 | 12 hrs | FY27 | 12 | 90027615 | A1 | 1000297392 | 07.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR90027615
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Ovhl 24M Air Conditioner Sys1 Eng | 2027-03-07 | 2027-03-09 | 48 hrs | FY27 | 48 | 90035243 | A1 | 1000359802 | 07.03.2027 | 24 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC1 | 6500 | 1175 | 1175 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC190035243
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Ovhl 24M Air Conditioner Sys2 Hyd | 2027-03-07 | 2027-03-08 | 36 hrs | FY27 | 36 | 90035267 | A1 | 1000359804 | 07.03.2027 | 24 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC290035267
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Operator Seat Servo Valve | 2027-03-07 | 2027-03-07 | 4 hrs | FY27 | 4 | 90018171 | A1 | 1000170101 | 07.03.2027 | 24000 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SSEVV | 7500 | 86287 | 19651 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SSEVV90018171
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Sprocket LH | 2027-03-12 | 2027-03-12 | 12 hrs | FY27 | 24 | 90003156 | A1 | 1000231307 | 12.03.2027 | 1500 | CLB-MP-EXCV-EX014 -TRAVEL-SPRKL | 470 | 3415 | 1963 | CLB-MP-EXCV-EX014 -TRAVEL-SPRKL90003156
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Emergency Ladder | 2027-03-13 | 2027-03-13 | 3 hrs | FY27 | 6 | 90022513 | 1 | 1000307980 | 13.03.2027 | 24 Monthly | CLB-MP-EXCV-EX7124-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7124-STRUCT-STLAD-SLFXD90022513
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 12M Inspection Isolator Panel | 2027-03-15 | 2027-03-15 | 2 hrs | FY27 | 2 | 90022525 | A2 | 1000348387 | 15.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7141-ELCTLV |  |  |  | CLB-MP-EXCV-EX7141-ELCTLV90022525
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Oil Suction Hoses | 2027-03-17 | 2027-03-18 | 24 hrs | FY27 | 48 | 90009474 | A2 | 1000207138 | 17.03.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-OILSC | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-OILSC90009474
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl PTO Cooling Hoses | 2027-03-17 | 2027-03-17 | 6 hrs | FY27 | 12 | 90009475 | A2 | 1000207139 | 17.03.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-PTOCL | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-PTOCL90009475
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Engine Cool Fan LH | 2027-03-17 | 2027-03-17 | 6 hrs | FY27 | 12 | 90003164 | A1 | 1000207102 | 17.03.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HECPL | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HECPL90003164
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Engine Cool Fan RH | 2027-03-17 | 2027-03-17 | 6 hrs | FY27 | 12 | 90003164 | A1 | 1000207103 | 17.03.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HECPR | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HECPR90003164
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Pump Drive Gearbox LH | 2027-03-17 | 2027-03-18 | 36 hrs | FY27 | 108 | 90003161 | A1 | 1000207094 | 17.03.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-PPDRL | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-HYDSYS-PPDRL90003161
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Track Tension Cyl RH | 2027-03-17 | 2027-03-17 | 12 hrs | FY27 | 24 | 90032648 | A1 | 1000207156 | 17.03.2027 | 18000 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-TENSR | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-TENSR90032648
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Rotary Joint | 2027-03-18 | 2027-03-19 | 24 hrs | FY27 | 48 | 90003171 | A1 | 1000158844 | 18.03.2027 | 24000 | CLB-MP-EXCV-EX014 -HYDSYS-ROTRY | 6700 | 42775 | 19265 | CLB-MP-EXCV-EX014 -HYDSYS-ROTRY90003171
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Track Tension Tuning-Adjust | 2027-03-19 | 2027-03-19 | 3 hrs | FY27 | 9 | 90029977 | A1 | 1000357482 | 19.03.2027 | 6 Monthly | CLB-MP-EXCV-EX7148-UNDERC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-UNDERC90029977
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Hydraulic System Tune Up | 2027-03-19 | 2027-03-19 | 12 hrs | FY27 | 24 | 90022669 | A1 | 1000237214 | 19.03.2027 | 6000 | CLB-MP-EXCV-EX7119-HYDSYS | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS90022669
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Operators Seat | 2027-03-20 | 2027-03-20 | 3 hrs | FY27 | 6 | 90005246 | 1 | 1000055223 | 20.03.2027 | 8000 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-SEATS | 7500 | 86287 | 3339 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-SEATS90005246
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Boom Assembly | 2027-03-20 | 2027-03-25 | 116 hrs | FY27 | 324 | 90003181 | A1 | 1000231155 | 20.03.2027 | 36000 | CLB-MP-EXCV-EX7112-STRUCT-BOOMS | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-BOOMS90003181
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Stick Assembly | 2027-03-20 | 2027-03-24 | 99 hrs | FY27 | 291 | 90003183 | A1 | 1000231302 | 20.03.2027 | 36000 | CLB-MP-EXCV-EX7112-STRUCT-STICK | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-STRUCT-STICK90003183
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Slew Gear Bearing | 2027-03-20 | 2027-03-24 | 96 hrs | FY27 | 288 | 90003193 | A1 | 1000207128 | 20.03.2027 | 36000 | CLB-MP-EXCV-EX7112-STRUCT-UNDER-SLEWB | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-UNDER-SLEWB90003193
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Hydraulic Oil Replacement | 2027-03-20 | 2027-03-20 | 12 hrs | FY27 | 12 | 90022667 | A1 | 1000237203 | 20.03.2027 | 6000 | CLB-MP-EXCV-EX7119-HYDSYS | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS90022667
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Grease System Audit | 2027-03-22 | 2027-03-23 | 24 hrs | FY27 | 36 | 90030748 | A1 | 1000337277 | 22.03.2027 | 5000 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ | 6200 | 10954 | 672 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ90030748
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Batteries | 2027-03-23 | 2027-03-23 | 5 hrs | FY27 | 9 | 90017122 | A1 | 1000330530 | 23.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST | 6200 | 11792 | 2453 | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST90017122
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Pump Swing Combination | 2027-03-24 | 2027-03-25 | 24 hrs | FY27 | 36 | 90030252 | A1 | 1000357499 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SWPP1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SWPP190030252
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Bucket LH Lift | 2027-03-24 | 2027-03-25 | 30 hrs | FY27 | 54 | 90029964 | A1 | 1000357474 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYL90029964
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Bucket RH Lift | 2027-03-24 | 2027-03-25 | 30 hrs | FY27 | 54 | 90029967 | A1 | 1000357475 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYR90029967
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Vlve Bank Module Quarter Life | 2027-03-24 | 2027-03-24 | 6 hrs | FY27 | 12 | 90029987 | A1 | 1000357489 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVLU | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVLU90029987
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Valve pressure Limiting Y4 | 2027-03-24 | 2027-03-24 | 6 hrs | FY27 | 6 | 90030321 | A1 | 1000357507 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPLV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPLV90030321
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Accumulator Servo Hyd | 2027-03-24 | 2027-03-24 | 3 hrs | FY27 | 3 | 90030487 | A1 | 1000357490 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCS90030487
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Accumulator Ladder Hyd | 2027-03-24 | 2027-03-24 | 4 hrs | FY27 | 4 | 90030685 | A1 | 1000357516 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCB | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCB90030685
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Track Tensioning Hoses | 2027-03-24 | 2027-03-24 | 12 hrs | FY27 | 24 | 90030538 | A1 | 1000357515 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HHTTL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HHTTL90030538
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hyd Hose Work Pumps to Valves | 2027-03-24 | 2027-03-24 | 10.5 hrs | FY27 | 10.5 | 90030287 | A1 | 1000357504 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HWPVV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HWPVV90030287
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hyd Hose Swing Pump Swing Motor | 2027-03-24 | 2027-03-24 | 12 hrs | FY27 | 24 | 90030288 | A1 | 1000357505 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSPSM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSPSM90030288
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hyd Hose Rotary Con to Valve Bank | 2027-03-24 | 2027-03-24 | 12 hrs | FY27 | 24 | 90029912 | A1 | 1000357429 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCVV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCVV90029912
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hoses Rotary Conn to Travel Motor | 2027-03-24 | 2027-03-25 | 24 hrs | FY27 | 48 | 90029914 | A1 | 1000357430 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCTM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCTM90029914
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Operators Seat | 2027-03-24 | 2027-03-24 | 9 hrs | FY27 | 17 | 90029915 | A1 | 1000357431 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-CABIN-SEATO | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-CABIN-SEATO90029915
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Motor A/C Comp Drive | 2027-03-24 | 2027-03-24 | 2 hrs | FY27 | 2 | 90030714 | A1 | 1000357517 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-AIRC1-ACONM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-AIRC1-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Motor A/C Comp Drive | 2027-03-24 | 2027-03-24 | 2 hrs | FY27 | 2 | 90030714 | A1 | 1000357518 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-AIRC2-ACONM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-AIRC2-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Auto Lube Pump P1 | 2027-03-24 | 2027-03-24 | 2 hrs | FY27 | 2 | 90030312 | A1 | 1000357435 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBPP | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBPP90030312
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Auto Lube Pump P3 | 2027-03-24 | 2027-03-24 | 2 hrs | FY27 | 2 | 90035351 | A1 | 1000358642 | 24.03.2027 | 10000 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBP3 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBP390035351
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Engine Cat C32 LH | 2027-03-24 | 2027-03-31 | 168 hrs | FY27 | 250 | 90017913 | A1 | 1000207059 | 24.03.2027 | 18000 | CLB-MP-EXCV-EX7112-LHENGN | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-LHENGN90017913
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Grease Tank Level Valve | 2027-03-28 | 2027-03-28 | 2 hrs | FY27 | 2 | 90015003 | A1 | 1000348551 | 28.03.2027 | 12 Monthly | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Track Tension Tuning-Adjust | 2027-03-28 | 2027-03-28 | 3 hrs | FY27 | 9 | 90020545 | A1 | 1000348591 | 28.03.2027 | 6 Monthly | CLB-MP-EXCV-EX7141-UNDERC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC90020545
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Boom Module Quarter Life | 2027-03-30 | 2027-03-31 | 30 hrs | FY27 | 48 | 90029992 | A1 | 1000359597 | 30.03.2027 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029992
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Final Drive LH | 2027-04-02 | 2027-04-04 | 48 hrs | FY27 | 144 | 90027485 | A1 | 1000284586 | 02.04.2027 | 24000 | CLB-MP-EXCV-EX7124-TRAVEL-FDRLH | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-TRAVEL-FDRLH90027485
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Final Drive RH | 2027-04-02 | 2027-04-04 | 48 hrs | FY27 | 144 | 90027485 | A1 | 1000284587 | 02.04.2027 | 24000 | CLB-MP-EXCV-EX7124-TRAVEL-FDRRH | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-TRAVEL-FDRRH90027485
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2027-04-02 | 2027-04-02 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237212 | 02.04.2027 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Engine Cat C32 RH | 2027-04-03 | 2027-04-10 | 168 hrs | FY27 | 250 | 90017914 | A1 | 1000207074 | 03.04.2027 | 18000 | CLB-MP-EXCV-EX7112-RHENGN | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-RHENGN90017914
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Adjust Track Tension Tuning | 2027-04-04 | 2027-04-04 | 3 hrs | FY27 | 9 | 90029977 | A1 | 1000304629 | 04.04.2027 | 6 Monthly | CLB-MP-EXCV-EX7133-UNDERC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC90029977
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Hydraulic Service & Repairs | 2027-04-04 | 2027-04-05 | 18 hrs | FY27 | 30 | 90029940 | A1 | 1000304680 | 04.04.2027 | 12 Monthly | CLB-MP-EXCV-EX7133-HYDSYS |  |  |  | CLB-MP-EXCV-EX7133-HYDSYS90029940
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Hydraulic System Tune Up | 2027-04-04 | 2027-04-04 | 12 hrs | FY27 | 24 | 90022669 | A1 | 1000237083 | 04.04.2027 | 6000 | CLB-MP-EXCV-EX7118-HYDSYS | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS90022669
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Stick LH | 2027-04-04 | 2027-04-05 | 30 hrs | FY27 | 54 | 90022646 | A1 | 1000237029 | 04.04.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLL | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLL90022646
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Servo Hose Bulkhead to MCV | 2027-04-04 | 2027-04-04 | 8 hrs | FY27 | 16 | 90022736 | A1 | 1000345676 | 04.04.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHMCV | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHMCV90022736
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Accumulator Track Hyd RH | 2027-04-05 | 2027-04-05 | 2 hrs | FY27 | 2 | 90002539 | A1 | 1000170015 | 05.04.2027 | 18000 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC-HACCR | 7500 | 86287 | 13053 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC-HACCR90002539
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2027-04-07 | 2027-04-07 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359913 | 07.04.2027 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Bucket LH | 2027-04-07 | 2027-04-08 | 26 hrs | FY27 | 32 | 90022647 | A1 | 1000237162 | 07.04.2027 | 10000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYL | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYL90022647
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Batteries | 2027-04-10 | 2027-04-10 | 4 hrs | FY27 | 4 | 90027525 | A1 | 1000297388 | 10.04.2027 | 10000 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-BATTY | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-BATTY90027525
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Grease Injectors | 2027-04-10 | 2027-04-12 | 48 hrs | FY27 | 84 | 90029932 | A1 | 1000357442 | 10.04.2027 | 10000 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ90029932
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Boom LH | 2027-04-10 | 2027-04-12 | 42 hrs | FY27 | 78 | 90030723 | A1 | 1000330532 | 10.04.2027 | 16000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BMCYL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BMCYL90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Boom RH | 2027-04-10 | 2027-04-12 | 42 hrs | FY27 | 78 | 90030723 | A1 | 1000330533 | 10.04.2027 | 16000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BMCYR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BMCYR90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Stick LH | 2027-04-10 | 2027-04-11 | 30 hrs | FY27 | 54 | 90030724 | A1 | 1000330536 | 10.04.2027 | 16000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-STCLL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-STCLL90030724
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Stick RH | 2027-04-10 | 2027-04-11 | 30 hrs | FY27 | 54 | 90030724 | A1 | 1000330537 | 10.04.2027 | 16000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-STCLR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-STCLR90030724
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Servo Hoses Cascade to Bulkhead | 2027-04-14 | 2027-04-14 | 8 hrs | FY27 | 16 | 90009478 | 1 | 1000207142 | 14.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHBLK | 6700 | 31524 | 19618 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHBLK90009478
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Swing Circuit Hoses | 2027-04-14 | 2027-04-14 | 8 hrs | FY27 | 16 | 90009481 | 1 | 1000207145 | 14.04.2027 | 9000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWCRT | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWCRT90009481
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel RHR | 2027-04-14 | 2027-04-14 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000207127 | 14.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRR | 6700 | 31524 | 20738 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Fan Hyd Cool Front | 2027-04-15 | 2027-04-15 | 6 hrs | FY27 | 12 | 90022655 | A1 | 1000237170 | 15.04.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMCHF | 6700 | 27054 | 13200 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMCHF90022655
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Stick LH | 2027-04-16 | 2027-04-17 | 30 hrs | FY27 | 54 | 90027498 | A1 | 1000284607 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLL | 6700 | 19559 | 7278 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLL90027498
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Stick RH | 2027-04-16 | 2027-04-17 | 30 hrs | FY27 | 54 | 90027498 | A1 | 1000284608 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLR | 6700 | 19559 | 7304 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLR90027498
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Servo Hoses Cascade to Trvl Valve | 2027-04-16 | 2027-04-16 | 6 hrs | FY27 | 12 | 90022737 | A1 | 1000207144 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHTRV | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHTRV90022737
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Swing Motor Case Drain Hoses | 2027-04-16 | 2027-04-16 | 6 hrs | FY27 | 12 | 90022739 | A1 | 1000207146 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWMCD | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos1 | 2027-04-16 | 2027-04-18 | 42 hrs | FY27 | 54 | 90003162 | A1 | 1000207096 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP1 | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP190003162
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos2 | 2027-04-16 | 2027-04-18 | 42 hrs | FY27 | 54 | 90003162 | A1 | 1000207097 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP2 | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP290003162
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Replenish LH | 2027-04-16 | 2027-04-16 | 2 hrs | FY27 | 2 | 90022643 | A1 | 1000207106 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPL | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPL90022643
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Replenish RH | 2027-04-16 | 2027-04-16 | 2 hrs | FY27 | 2 | 90022643 | A1 | 1000207107 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPR | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPR90022643
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Pump Servo LH | 2027-04-16 | 2027-04-16 | 2 hrs | FY27 | 2 | 90010935 | 1 | 1000207104 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPL | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPL90010935
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Pump Servo RH | 2027-04-16 | 2027-04-16 | 2 hrs | FY27 | 2 | 90010935 | 1 | 1000207105 | 16.04.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPR | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPR90010935
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Sprocket RH | 2027-04-20 | 2027-04-20 | 12 hrs | FY27 | 24 | 90003156 | A1 | 1000231308 | 20.04.2027 | 1500 | CLB-MP-EXCV-EX014 -TRAVEL-SPRKR | 470 | 3415 | 1140 | CLB-MP-EXCV-EX014 -TRAVEL-SPRKR90003156
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 500hr Initial Valve Set | 2027-04-20 | 2027-04-20 | 10 hrs | FY27 | 20 | 90017925 | A1 | 1000207069 | 20.04.2027 | 500 | CLB-MP-EXCV-EX7112-LHENGN | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-LHENGN90017925
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Radiator LH Engine | 2027-04-21 | 2027-04-21 | 12 hrs | FY27 | 24 | 90017956 | A1 | 1000207072 | 21.04.2027 | 18000 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-RADTR | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-RADTR90017956
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Main Pump to Rotor Hoses | 2027-04-26 | 2027-04-26 | 12 hrs | FY27 | 24 | 90009243 | 1 | 1000074236 | 26.04.2027 | 6000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-MPRC | 7500 | 86287 | 627 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-MPRC90009243
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Servo Hoses Bulkhead to MCV | 2027-04-26 | 2027-04-26 | 8 hrs | FY27 | 16 | 90009248 | 1 | 1000074242 | 26.04.2027 | 6000 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHMCV | 7500 | 86287 | 627 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHMCV90009248
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Wiper Blades | 2027-04-29 | 2027-04-29 | 1 hr | FY27 | 1 | 90027557 | A1 | 1000284656 | 29.04.2027 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7124-STRUCT-CABIN90027557
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Adjust Track Tension Tuning | 2027-04-29 | 2027-04-29 | 3 hrs | FY27 | 9 | 90020545 | A1 | 1000337320 | 29.04.2027 | 6 Monthly | CLB-MP-EXCV-EX7140-UNDERC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Annual Air Con Service LH | 2027-04-30 | 2027-04-30 | 12 hrs | FY27 | 12 | 90027615 | A1 | 1000284685 | 30.04.2027 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL90027615
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Annual Air Con Service RH | 2027-04-30 | 2027-04-30 | 12 hrs | FY27 | 12 | 90027615 | A1 | 1000284655 | 30.04.2027 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR90027615
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 500hr Initial Valve Set | 2027-04-30 | 2027-04-30 | 10 hrs | FY27 | 20 | 90017925 | A1 | 1000207084 | 30.04.2027 | 500 | CLB-MP-EXCV-EX7112-RHENGN | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-RHENGN90017925
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Hyd Pump Case Drain Hoses | 2027-05-02 | 2027-05-02 | 8 hrs | FY27 | 8 | 90009241 | 1 | 1000074215 | 02.05.2027 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HPCDL | 7500 | 79029 | 6162 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HPCDL90009241
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Servo Hoses Cascade to Trvl Valve | 2027-05-03 | 2027-05-03 | 6 hrs | FY27 | 12 | 90022737 | A1 | 1000158875 | 03.05.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHTRV | 6700 | 42775 | 6421 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHTRV90022737
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Annual Air Con Service RH | 2027-05-03 | 2027-05-03 | 12 hrs | FY27 | 12 | 90004141 | 2 | 1000266975 | 03.05.2027 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR90004141
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Grease System Audit | 2027-05-05 | 2027-05-06 | 24 hrs | FY27 | 36 | 90030748 | A1 | 1000340300 | 05.05.2027 | 5000 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ90030748
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Motor HEPA Pressuriser | 2027-05-05 | 2027-05-05 | 1 hr | FY27 | 1 | 90033905 | A1 | 1000342974 | 05.05.2027 | 15000 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-CABPR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-CABPR90033905
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Pump Swing Combination | 2027-05-05 | 2027-05-06 | 24 hrs | FY27 | 36 | 90030252 | A1 | 1000359604 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SWPP1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SWPP190030252
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Bucket LH Lift | 2027-05-05 | 2027-05-06 | 30 hrs | FY27 | 54 | 90029964 | A1 | 1000359579 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYL90029964
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Bucket RH Lift | 2027-05-05 | 2027-05-06 | 30 hrs | FY27 | 54 | 90029967 | A1 | 1000359580 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYR90029967
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Vlve Bank Module Quarter Life | 2027-05-05 | 2027-05-05 | 6 hrs | FY27 | 12 | 90029987 | A1 | 1000359594 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVLU | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVLU90029987
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Valve pressure Limiting Y4 | 2027-05-05 | 2027-05-05 | 6 hrs | FY27 | 6 | 90030321 | A1 | 1000359612 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPLV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPLV90030321
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Accumulator Servo Hyd | 2027-05-05 | 2027-05-05 | 3 hrs | FY27 | 3 | 90030487 | A1 | 1000359595 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCS90030487
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Accumulator Ladder Hyd | 2027-05-05 | 2027-05-05 | 4 hrs | FY27 | 4 | 90030685 | A1 | 1000359621 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCB | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCB90030685
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Track Tensioning Hoses | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 24 | 90030538 | A1 | 1000359620 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HHTTL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HHTTL90030538
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hyd Hose Work Pumps to Valves | 2027-05-05 | 2027-05-05 | 10.5 hrs | FY27 | 10.5 | 90030287 | A1 | 1000359609 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HWPVV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HWPVV90030287
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hyd Hose Swing Pump Swing Motor | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 24 | 90030288 | A1 | 1000359610 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSPSM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSPSM90030288
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hyd Hose Rotary Con to Valve Bank | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 24 | 90029912 | A1 | 1000359534 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCVV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCVV90029912
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hoses Rotary Conn to Travel Motor | 2027-05-05 | 2027-05-06 | 24 hrs | FY27 | 48 | 90029914 | A1 | 1000359535 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCTM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCTM90029914
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Operators Seat | 2027-05-05 | 2027-05-05 | 9 hrs | FY27 | 17 | 90029915 | A1 | 1000359536 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-CABIN-SEATO | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-CABIN-SEATO90029915
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Motor A/C Comp Drive | 2027-05-05 | 2027-05-05 | 2 hrs | FY27 | 2 | 90030714 | A1 | 1000359622 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-AIRC1-ACONM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC1-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Motor A/C Comp Drive | 2027-05-05 | 2027-05-05 | 2 hrs | FY27 | 2 | 90030714 | A1 | 1000359623 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-AIRC2-ACONM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC2-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Auto Lube Pump P1 | 2027-05-05 | 2027-05-05 | 2 hrs | FY27 | 2 | 90030312 | A1 | 1000359540 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBPP | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBPP90030312
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Auto Lube Pump P3 | 2027-05-05 | 2027-05-05 | 2 hrs | FY27 | 2 | 90035351 | A1 | 1000369281 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBP3 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBP390035351
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Grease Injectors | 2027-05-05 | 2027-05-07 | 48 hrs | FY27 | 84 | 90029932 | A1 | 1000359547 | 05.05.2027 | 10000 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ90029932
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Idler Track LH | 2027-05-05 | 2027-05-05 | 6 hrs | FY27 | 18 | 90003189 | A1 | 1000207170 | 05.05.2027 | 1500 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-IDLLH | 470 | 2622 | 1533 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-IDLLH90003189
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Idler Track RH | 2027-05-05 | 2027-05-05 | 6 hrs | FY27 | 18 | 90003189 | A1 | 1000207181 | 05.05.2027 | 1500 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-IDLRH | 470 | 2622 | 1697 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-IDLRH90003189
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Sprocket LH | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 24 | 90003156 | A1 | 1000207178 | 05.05.2027 | 1500 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKL | 470 | 2622 | 26 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKL90003156
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Sprocket RH | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 24 | 90003156 | A1 | 1000207189 | 05.05.2027 | 1500 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKR | 470 | 2622 | 2622 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKR90003156
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 12M Hydraulic Service & Repairs | 2027-05-06 | 2027-05-07 | 18 hrs | FY27 | 30 | 90014448 | A1 | 1000348386 | 06.05.2027 | 12 Monthly | CLB-MP-EXCV-EX7141-HYDSYS | 6200 | 8353 | 1263 | CLB-MP-EXCV-EX7141-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Annual Air Con Service RH | 2027-05-07 | 2027-05-07 | 12 hrs | FY27 | 12 | 90004141 | 2 | 1000211117 | 07.05.2027 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR90004141
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Minestar Harness | 2027-05-08 | 2027-05-09 | 27.5 hrs | FY27 | 43.5 | 90030746 | A1 | 1000330543 | 08.05.2027 | 5000 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC | 6200 | 11792 | 5210 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC90030746
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Annual Air Con Service LH | 2027-05-08 | 2027-05-08 | 12 hrs | FY27 | 12 | 90004141 | 2 | 1000163161 | 08.05.2027 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL | 6700 | 19252 | 8084 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL90004141
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Minestar Harness | 2027-05-08 | 2027-05-09 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000369999 | 08.05.2027 | 4000 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC90031708
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Static Line Inspection | 2027-05-09 | 2027-05-09 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000340340 | 09.05.2027 | 6 Monthly | CLB-MP-EXCV-EX7138-STRUCT | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2027-05-09 | 2027-05-09 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359909 | 09.05.2027 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Repl Emergency Ladder | 2027-05-09 | 2027-05-09 | 3 hrs | FY27 | 6 | 90022515 | 1 | 1000235859 | 09.05.2027 | 24 Monthly | CLB-MP-EXCV-EX107 -STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX107 -STRUCT-STLAD-SLFXD90022515
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Hydraulic System Tune Up | 2027-05-11 | 2027-05-11 | 12 hrs | FY27 | 24 | 90017867 | 1 | 1000163740 | 11.05.2027 | 5000 | CLB-MP-EXCV-EX107 -HYDSYS | 7500 | 86684 | 4212 | CLB-MP-EXCV-EX107 -HYDSYS90017867
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Main Pump to Rotor Hoses | 2027-05-12 | 2027-05-12 | 12 hrs | FY27 | 24 | 90009243 | 1 | 1000074198 | 12.05.2027 | 6000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MPRC | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MPRC90009243
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Servo Hoses Cascade to Trvl Valve | 2027-05-12 | 2027-05-12 | 6 hrs | FY27 | 12 | 90009249 | 1 | 1000074204 | 12.05.2027 | 12000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHTRV | 7500 | 86684 | 20445 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHTRV90009249
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Batteries | 2027-05-13 | 2027-05-13 | 8 hrs | FY27 | 8 | 90016788 | 1 | 1000152457 | 13.05.2027 | 10000 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-BATTY | 7500 | 86287 | 4238 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-BATTY90016788
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl LH Aftercooler | 2027-05-13 | 2027-05-13 | 12 hrs | FY27 | 24 | 90023361 | A1 | 1000309244 | 13.05.2027 | 18000 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-AFTER | 6700 | 25972 | 12463 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-AFTER90023361
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Boom Module Quarter Life | 2027-05-14 | 2027-05-15 | 30 hrs | FY27 | 48 | 90029992 | A1 | 1000304639 | 14.05.2027 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029992
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Emergency Ladder | 2027-05-14 | 2027-05-14 | 3 hrs | FY27 | 6 | 90022513 | 1 | 1000241541 | 14.05.2027 | 24 Monthly | CLB-MP-EXCV-EX7119-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7119-STRUCT-STLAD-SLFXD90022513
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Swing Circuit Hoses | 2027-05-16 | 2027-05-16 | 13 hrs | FY27 | 23 | 90009251 | 1 | 1000074206 | 16.05.2027 | 6000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWCRT | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWCRT90009251
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Servo Hoses Bulkhead to MCV | 2027-05-16 | 2027-05-16 | 8 hrs | FY27 | 16 | 90009248 | 1 | 1000074203 | 16.05.2027 | 6000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHMCV | 7500 | 86684 | 6113 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHMCV90009248
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Emergency Ladder | 2027-05-16 | 2027-05-16 | 3 hrs | FY27 | 6 | 90022513 | 1 | 1000241540 | 16.05.2027 | 24 Monthly | CLB-MP-EXCV-EX7118-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7118-STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service LH | 2027-05-17 | 2027-05-17 | 12 hrs | FY27 | 12 | 90022660 | A1 | 1000242609 | 17.05.2027 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL | 6700 | 17550 | 5056 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL90022660
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Inspection Ext Static Line | 2027-05-19 | 2027-05-19 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000304563 | 19.05.2027 | 6 Monthly | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029897
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Cylinder Boom LH | 2027-05-20 | 2027-05-22 | 42 hrs | FY27 | 78 | 90030723 | A1 | 1000337271 | 20.05.2027 | 16000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BMCYL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BMCYL90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Cylinder Boom RH | 2027-05-20 | 2027-05-22 | 42 hrs | FY27 | 78 | 90030723 | A1 | 1000337272 | 20.05.2027 | 16000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BMCYR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BMCYR90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Cylinder Stick LH | 2027-05-20 | 2027-05-21 | 30 hrs | FY27 | 54 | 90030724 | A1 | 1000337275 | 20.05.2027 | 16000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-STCLL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-STCLL90030724
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Cylinder Stick RH | 2027-05-20 | 2027-05-21 | 30 hrs | FY27 | 54 | 90030724 | A1 | 1000337276 | 20.05.2027 | 16000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-STCLR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-STCLR90030724
6060 | Onsite PM | Excavators | Fortescue | EX109 | EX109 Repl Emergency Ladder | 2027-05-20 | 2027-05-20 | 3 hrs | FY27 | 6 | 90022515 | 1 | 1000235962 | 20.05.2027 | 24 Monthly | CLB-MP-EXCV-EX109 -STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX109 -STRUCT-STLAD-SLFXD90022515
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hydraulic Cooling Circ Hoses | 2027-05-20 | 2027-05-21 | 18 hrs | FY27 | 36 | 90028476 | A1 | 1000345667 | 20.05.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HCCHH | 6700 | 25972 | 15339 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HCCHH90028476
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Fan Engine Cool LH | 2027-05-23 | 2027-05-23 | 6 hrs | FY27 | 18 | 90003177 | A1 | 1000207122 | 23.05.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMECL | 6700 | 31524 | 12394 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMECL90003177
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Fan Engine Cool RH | 2027-05-23 | 2027-05-23 | 6 hrs | FY27 | 18 | 90003177 | A1 | 1000207123 | 23.05.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMECR | 6700 | 31524 | 12394 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMECR90003177
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Swing LHR | 2027-05-24 | 2027-05-25 | 21 hrs | FY27 | 27 | 90027503 | A1 | 1000284614 | 24.05.2027 | 15000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMLR | 6700 | 19559 | 9603 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMLR90027503
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cylinder Bucket LH | 2027-05-24 | 2027-05-25 | 26 hrs | FY27 | 32 | 90003169 | A1 | 1000158840 | 24.05.2027 | 10000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYL | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYL90003169
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos4 | 2027-05-24 | 2027-05-26 | 42 hrs | FY27 | 54 | 90003162 | A1 | 1000207099 | 24.05.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP4 | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP490003162
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Pos3 & Pos4 | 2027-05-24 | 2027-05-25 | 26 hrs | FY27 | 42 | 90003163 | A1 | 1000207101 | 24.05.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP3P4 | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP3P490003163
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Minestar Harness | 2027-05-25 | 2027-05-26 | 27.5 hrs | FY27 | 43.5 | 90030746 | A1 | 1000340305 | 25.05.2027 | 5000 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC90030746
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2027-05-25 | 2027-05-25 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359910 | 25.05.2027 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel RHF | 2027-05-25 | 2027-05-25 | 6 hrs | FY27 | 12 | 90022657 | A1 | 1000207126 | 25.05.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRF | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Minestar Harness | 2027-05-26 | 2027-05-27 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000370303 | 26.05.2027 | 4000 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Fan Hyd Cool Front | 2027-05-26 | 2027-05-26 | 6 hrs | FY27 | 12 | 90003176 | A1 | 1000207120 | 26.05.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMCHF | 6700 | 31524 | 12394 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMCHF90003176
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Servo Hoses Cascade to Bulkhead | 2027-05-27 | 2027-05-27 | 8 hrs | FY27 | 16 | 90027572 | A1 | 1000284639 | 27.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHBLK | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHBLK90027572
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Servo Hoses Cascade to Trvl Valve | 2027-05-27 | 2027-05-27 | 6 hrs | FY27 | 12 | 90027575 | A1 | 1000284641 | 27.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHTRV | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHTRV90027575
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos4 | 2027-05-27 | 2027-05-29 | 42 hrs | FY27 | 64 | 90027490 | A1 | 1000284596 | 27.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP4 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP490027490
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Inspection Ext Static Line | 2027-05-27 | 2027-05-27 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000359517 | 27.05.2027 | 6 Monthly | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Bucket LH | 2027-05-27 | 2027-05-28 | 26 hrs | FY27 | 32 | 90022647 | A1 | 1000237031 | 27.05.2027 | 10000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYL | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYL90022647
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Rotor & Logic Valve Hp Hoses | 2027-05-28 | 2027-05-29 | 18 hrs | FY27 | 36 | 90027571 | A1 | 1000284638 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCLVH | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCLVH90027571
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos1 | 2027-05-28 | 2027-05-30 | 42 hrs | FY27 | 64 | 90027490 | A1 | 1000284593 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP1 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP190027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos2 | 2027-05-28 | 2027-05-30 | 42 hrs | FY27 | 64 | 90027490 | A1 | 1000284594 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP2 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP290027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos3 | 2027-05-28 | 2027-05-30 | 42 hrs | FY27 | 64 | 90027490 | A1 | 1000284595 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP3 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP390027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Replenish LH | 2027-05-28 | 2027-05-28 | 2 hrs | FY27 | 2 | 90027495 | A1 | 1000284603 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPL | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPL90027495
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Replenish RH | 2027-05-28 | 2027-05-28 | 2 hrs | FY27 | 2 | 90027495 | A1 | 1000284604 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPR | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPR90027495
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Pump Servo LH | 2027-05-28 | 2027-05-28 | 2 hrs | FY27 | 2 | 90027496 | A1 | 1000284601 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPL | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPL90027496
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Pump Servo RH | 2027-05-28 | 2027-05-28 | 2 hrs | FY27 | 2 | 90027496 | A1 | 1000284602 | 28.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPR | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPR90027496
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Gearbox Swing RHF | 2027-05-28 | 2027-05-30 | 48 hrs | FY27 | 80 | 90012369 | 1 | 1000158820 | 28.05.2027 | 20000 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBRF | 6700 | 42775 | 13967 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBRF90012369
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Pos1 & Pos2 | 2027-05-29 | 2027-05-30 | 26 hrs | FY27 | 42 | 90027492 | A1 | 1000284597 | 29.05.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP1P2 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP1P290027492
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2027-05-30 | 2027-05-30 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000337317 | 30.05.2027 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Track Tension Tuning-Adjust | 2027-06-02 | 2027-06-02 | 3 hrs | FY27 | 9 | 90020545 | A1 | 1000340343 | 02.06.2027 | 6 Monthly | CLB-MP-EXCV-EX7138-UNDERC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2027-06-02 | 2027-06-02 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000348588 | 02.06.2027 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2027-06-02 | 2027-06-02 | 4 hrs | FY27 | 4 | 90014347 | A1 | 1000330578 | 02.06.2027 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Hose Bucket Cyl | 2027-06-05 | 2027-06-06 | 18 hrs | FY27 | 54 | 90030738 | A1 | 1000348523 | 05.06.2027 | 8000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBKCL | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Hose Boom Cyl | 2027-06-05 | 2027-06-05 | 8 hrs | FY27 | 24 | 90030735 | A1 | 1000348522 | 05.06.2027 | 8000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBMCL | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Hose Stick Cyl | 2027-06-05 | 2027-06-05 | 12 hrs | FY27 | 24 | 90030737 | A1 | 1000348524 | 05.06.2027 | 8000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HSTCL | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HSTCL90030737
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hyd Hose Work Pumps to Valves | 2027-06-07 | 2027-06-07 | 10.5 hrs | FY27 | 10.5 | 90030287 | A1 | 1000304651 | 07.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HWPVV | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HWPVV90030287
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hyd Hose Swing Pump Swing Motor | 2027-06-07 | 2027-06-07 | 12 hrs | FY27 | 24 | 90030288 | A1 | 1000304652 | 07.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSPSM | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSPSM90030288
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Operators Seat | 2027-06-07 | 2027-06-07 | 9 hrs | FY27 | 17 | 90029915 | A1 | 1000304582 | 07.06.2027 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-CABIN-SEATO | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-STRUCT-CABIN-SEATO90029915
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Inspection Ext Static Line | 2027-06-09 | 2027-06-09 | 4 hrs | FY27 | 4 | 90029897 | A1 | 1000357332 | 09.06.2027 | 6 Monthly | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029897
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Track Tension Tuning-Adjust | 2027-06-10 | 2027-06-10 | 3 hrs | FY27 | 9 | 90029977 | A1 | 1000359587 | 10.06.2027 | 6 Monthly | CLB-MP-EXCV-EX7149-UNDERC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-UNDERC90029977
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Minestar Harness | 2027-06-10 | 2027-06-11 | 27.5 hrs | FY27 | 43.5 | 90030746 | A1 | 1000337282 | 10.06.2027 | 5000 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC90030746
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Bucket LH Lift | 2027-06-11 | 2027-06-12 | 30 hrs | FY27 | 54 | 90030725 | A1 | 1000330534 | 11.06.2027 | 10000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYL | 6200 | 11792 | 4733 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYL90030725
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Minestar Harness | 2027-06-11 | 2027-06-12 | 24.5 hrs | FY27 | 40.5 | 90031708 | A1 | 1000370300 | 11.06.2027 | 4000 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC90031708
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Vlve Bank Module Quarter Life | 2027-06-12 | 2027-06-12 | 6 hrs | FY27 | 12 | 90029987 | A1 | 1000304636 | 12.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVLU | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVLU90029987
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Valve pressure Limiting Y4 | 2027-06-12 | 2027-06-12 | 6 hrs | FY27 | 6 | 90030321 | A1 | 1000304654 | 12.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPLV | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPLV90030321
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Accumulator Servo Hyd | 2027-06-12 | 2027-06-12 | 3 hrs | FY27 | 3 | 90030487 | A1 | 1000304637 | 12.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC90030487
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Accumulator Ladder Hyd | 2027-06-12 | 2027-06-12 | 4 hrs | FY27 | 4 | 90030685 | A1 | 1000305744 | 12.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC90030685
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hyd Hose Rotary Con to Valve Bank | 2027-06-12 | 2027-06-12 | 12 hrs | FY27 | 24 | 90029912 | A1 | 1000304580 | 12.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCVV | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCVV90029912
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Radiator LH Engine Cooling | 2027-06-12 | 2027-06-12 | 12 hrs | FY27 | 24 | 90022683 | A1 | 1000236991 | 12.06.2027 | 18000 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-RADTR | 6700 | 25972 | 11914 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-RADTR90022683
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2027-06-15 | 2027-06-15 | 4 hrs | FY27 | 4 | 90022746 | A1 | 1000237081 | 15.06.2027 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Annual Air Con Service LH | 2027-06-19 | 2027-06-19 | 12 hrs | FY27 | 12 | 90004141 | 2 | 1000207158 | 19.06.2027 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL | 6700 | 21488 | 7104 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL90004141
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Batteries | 2027-06-20 | 2027-06-20 | 4 hrs | FY27 | 4 | 90027525 | A1 | 1000284651 | 20.06.2027 | 10000 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-BATTY | 6700 | 19559 | 4086 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-BATTY90027525
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos3 | 2027-06-21 | 2027-06-23 | 42 hrs | FY27 | 54 | 90003162 | A1 | 1000158826 | 21.06.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP3 | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP390003162
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel RHF | 2027-06-23 | 2027-06-23 | 6 hrs | FY27 | 12 | 90003178 | A1 | 1000158854 | 23.06.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRF | 6700 | 42775 | 5487 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRF90003178
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Replenish RH | 2027-06-23 | 2027-06-23 | 2 hrs | FY27 | 2 | 90003166 | A1 | 1000158835 | 23.06.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPR | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPR90003166
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Adjust 4500hr Valve Set | 2027-06-24 | 2027-06-24 | 10 hrs | FY27 | 20 | 90022679 | A1 | 1000236989 | 24.06.2027 | 4500 | CLB-MP-EXCV-EX7118-LHENGN | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-LHENGN90022679
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Adjust 4500hr Valve Set | 2027-06-25 | 2027-06-25 | 10 hrs | FY27 | 20 | 90027549 | A1 | 1000297275 | 25.06.2027 | 4500 | CLB-MP-EXCV-EX7122-LHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN90027549
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Adjust 4500hr Valve Set | 2027-06-25 | 2027-06-25 | 10 hrs | FY27 | 20 | 90027549 | A1 | 1000297320 | 25.06.2027 | 4500 | CLB-MP-EXCV-EX7122-RHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN90027549
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Operators Seat | 2027-06-25 | 2027-06-25 | 3 hrs | FY27 | 6 | 90005246 | 1 | 1000158860 | 25.06.2027 | 8000 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-SEATS | 6700 | 42775 | 9748 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-SEATS90005246
6060 | Onsite PM | Excavators | Fortescue | EX107 | EX107 Swing Brake Hoses | 2027-06-28 | 2027-06-28 | 4 hrs | FY27 | 8 | 90009250 | 1 | 1000074205 | 28.06.2027 | 12000 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWBRK | 7500 | 86684 | 5213 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWBRK90009250
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Bucket LH | 2027-06-29 | 2027-06-30 | 30 hrs | FY27 | 54 | 90029964 | A1 | 1000304623 | 29.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYL | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYL90029964
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Tensioning Hoses | 2027-06-29 | 2027-06-29 | 12 hrs | FY27 | 24 | 90030538 | A1 | 1000304722 | 29.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HHTTL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HHTTL90030538
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hoses Rotary Conn to Travel Motor | 2027-06-29 | 2027-06-30 | 24 hrs | FY27 | 48 | 90029914 | A1 | 1000304581 | 29.06.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCTM | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCTM90029914
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Motor ACon Comp Drive | 2027-06-29 | 2027-06-29 | 2 hrs | FY27 | 2 | 90030714 | A1 | 1000305909 | 29.06.2027 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-AIRC1 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC190030714
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Grease Block & Injectors | 2027-06-29 | 2027-07-01 | 48 hrs | FY27 | 84 | 90029933 | A1 | 1000304594 | 29.06.2027 | 20000 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ90029933
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Motor ACon Comp Drive | 2027-06-29 | 2027-06-29 | 2 hrs | FY27 | 2 | 90030714 | A1 | 1000305910 | 29.06.2027 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-AIRC2 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC290030714
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Annual Air Con Service LH | 2027-06-29 | 2027-06-29 | 12 hrs | FY27 | 12 | 90022660 | A1 | 1000242610 | 29.06.2027 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL | 6700 | 19940 | 6054 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL90022660
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2027-06-30 | 2027-06-30 | 6 hrs | FY27 | 12 | 90035479 | A1 | 1000359913 | 30.06.2027 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Boom LH | 2027-06-30 | 2027-07-02 | 42 hrs | FY27 | 78 | 90030723 | A1 | 1000340294 | 30.06.2027 | 16000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BMCYL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BMCYL90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Boom RH | 2027-06-30 | 2027-07-02 | 42 hrs | FY27 | 78 | 90030723 | A1 | 1000340295 | 30.06.2027 | 16000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BMCYR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BMCYR90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Stick LH | 2027-06-30 | 2027-07-01 | 30 hrs | FY27 | 54 | 90030724 | A1 | 1000340298 | 30.06.2027 | 16000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-STCLL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-STCLL90030724
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Stick RH | 2027-06-30 | 2027-07-01 | 30 hrs | FY27 | 54 | 90030724 | A1 | 1000340299 | 30.06.2027 | 16000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-STCLR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-STCLR90030724
| Onsite PM | Excavators | Fortescue |  | FY28 - EXCAVATORS - COMPONENTS DURING PM | 2027-07-01 |  |  | FY28
| Onsite PM | Excavators | Fortescue | MOC | MAJOR ON CONDITION | 2027-07-01 | 2028-06-30 | 8760 hrs | FY28
| Onsite PM | Excavators | Fortescue | MOC | JULY | 2027-07-01 | 2027-07-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | AUGUST | 2027-08-01 | 2027-08-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | SEPTEMBER | 2027-09-01 | 2027-09-30 | 29 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | OCTOBER | 2027-10-01 | 2027-10-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | NOVEMBER | 2027-11-01 | 2027-11-30 | 29 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | DECEMBER | 2027-12-01 | 2027-12-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | JANUARY | 2028-01-01 | 2028-01-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | FEBRUARY | 2028-02-01 | 2028-02-28 | 27 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | MARCH | 2028-03-01 | 2028-03-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | APRIL | 2028-04-01 | 2028-04-30 | 29 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | MAY | 2028-05-01 | 2028-05-31 | 30 days | FY28
| Onsite PM | Excavators | Fortescue | MOC | JUNE | 2028-06-01 | 2028-06-30 | 29 days | FY28
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Adjust 4500hr Valve Set | 2027-07-04 | 2027-07-04 | 10 hrs | FY28 | 20 | 90017923 | A1 | 1000158812 | 04.07.2027 | 4500 | CLB-MP-EXCV-EX014 -RHENGN | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -RHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Batteries | 2027-07-05 | 2027-07-05 | 8 hrs | FY28 | 8 | 90022665 | A1 | 1000237204 | 05.07.2027 | 10000 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-BATTY | 6700 | 27054 | 3710 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-BATTY90022665
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Pos1 & Pos2 | 2027-07-08 | 2027-07-09 | 26 hrs | FY28 | 42 | 90003163 | A1 | 1000207100 | 08.07.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP1P2 | 6700 | 31524 | 5544 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP1P290003163
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Auto Lube Pump | 2027-07-11 | 2027-07-11 | 6 hrs | FY28 | 6 | 90027592 | A1 | 1000284661 | 11.07.2027 | 6000 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP90027592
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Grease Control Valving | 2027-07-11 | 2027-07-11 | 14 hrs | FY28 | 14 | 90027612 | A1 | 1000284662 | 11.07.2027 | 12000 | CLB-MP-EXCV-EX7124-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7124-GRSYST-ALCON90027612
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel RHF | 2027-07-11 | 2027-07-11 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000284623 | 11.07.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRF | 6700 | 19559 | 5733 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRF90027506
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel RHR | 2027-07-11 | 2027-07-11 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000284624 | 11.07.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRR | 6700 | 19559 | 5712 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRR90027506
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel LHF | 2027-07-12 | 2027-07-12 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000284621 | 12.07.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLF | 6700 | 19559 | 5733 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLF90027506
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Hose Boom Cyl | 2027-07-14 | 2027-07-14 | 8 hrs | FY28 | 24 | 90029908 | A1 | 1000304577 | 14.07.2027 | 8000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMCL | 6200 | 13908 | 208 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Hose Stick Cyl | 2027-07-14 | 2027-07-14 | 12 hrs | FY28 | 24 | 90029909 | A1 | 1000304578 | 14.07.2027 | 8000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSTCL | 6200 | 13908 | 208 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Hose Bucket Cyl | 2027-07-14 | 2027-07-15 | 18 hrs | FY28 | 54 | 90029911 | A1 | 1000304579 | 14.07.2027 | 8000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBKCL | 6200 | 13908 | 389 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBKCL90029911
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Bucket Cyl | 2027-07-15 | 2027-07-16 | 18 hrs | FY28 | 54 | 90030738 | A1 | 1000330513 | 15.07.2027 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Boom Cyl | 2027-07-15 | 2027-07-15 | 8 hrs | FY28 | 24 | 90030735 | A1 | 1000330512 | 15.07.2027 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Stick Cyl | 2027-07-15 | 2027-07-15 | 12 hrs | FY28 | 24 | 90030737 | A1 | 1000330514 | 15.07.2027 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL90030737
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Swing RHR | 2027-07-15 | 2027-07-16 | 21 hrs | FY28 | 27 | 90003175 | A1 | 1000158847 | 15.07.2027 | 15000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRR | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRR90003175
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Minestar Harness | 2027-07-16 | 2027-07-17 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000370301 | 16.07.2027 | 4000 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Operators Seat | 2027-07-17 | 2027-07-17 | 2 hrs | FY28 | 2 | 90003180 | A1 | 1000207129 | 17.07.2027 | 10000 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-SEATS | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-SEATS90003180
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Swing Circuit Hoses | 2027-07-19 | 2027-07-19 | 8 hrs | FY28 | 16 | 90027576 | A1 | 1000284642 | 19.07.2027 | 9000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWCRT | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWCRT90027576
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Batteries | 2027-07-20 | 2027-07-20 | 8 hrs | FY28 | 8 | 90016788 | 1 | 1000207154 | 20.07.2027 | 10000 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-BATTY | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-BATTY90016788
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Bucket RH | 2027-07-20 | 2027-07-21 | 26 hrs | FY28 | 32 | 90003169 | A1 | 1000207113 | 20.07.2027 | 10000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYR | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYR90003169
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Adjust 4500hr Valve Set | 2027-07-21 | 2027-07-21 | 10 hrs | FY28 | 20 | 90022679 | A1 | 1000237135 | 21.07.2027 | 4500 | CLB-MP-EXCV-EX7119-RHENGN | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-RHENGN90022679
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Wiper Blades | 2027-07-25 | 2027-07-25 | 2 hrs | FY28 | 2 | 90004684 | 1 | 1000207159 | 25.07.2027 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-CABIN90004684
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hydraulic Cooling Circ Hoses | 2027-07-25 | 2027-07-26 | 18 hrs | FY28 | 36 | 90028476 | A1 | 1000237185 | 25.07.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HCCHH | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HCCHH90028476
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl HV Motor Coupling | 2027-07-30 | 2027-07-31 | 20 hrs | FY28 | 30 | 90030128 | A1 | 1000304659 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-ELCTHV-HVMOT-COUPL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-ELCTHV-HVMOT-COUPL90030128
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Gearbox Swing P1 | 2027-07-30 | 2027-08-01 | 55 hrs | FY28 | 109 | 90029900 | A1 | 1000304566 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-SWGSYS-SWBOX-SGBPF | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-SWGSYS-SWBOX-SGBPF90029900
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Splitter Gearbox | 2027-07-30 | 2027-08-04 | 120 hrs | FY28 | 240 | 90030087 | A1 | 1000304644 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-PMPDR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-PMPDR90030087
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Pump Hyd Work Pos1 & Pos2 | 2027-07-30 | 2027-07-31 | 36 hrs | FY28 | 54 | 90030234 | A1 | 1000304645 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-WPPP1 | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-WPPP190030234
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Pump Hyd Work Pos3 & Pos4 | 2027-07-30 | 2027-07-31 | 36 hrs | FY28 | 54 | 90030286 | A1 | 1000304653 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-WPPP2 | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-WPPP290030286
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Pump Fan Hyd Oil Cooler | 2027-07-30 | 2027-07-31 | 24 hrs | FY28 | 36 | 90030278 | A1 | 1000304647 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-HECP1 | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-HECP190030278
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Pump Servo Bearing Lube | 2027-07-30 | 2027-07-30 | 4 hrs | FY28 | 4 | 90030280 | A1 | 1000304648 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-SVPP1 | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-SVPP190030280
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Lube Pump Splitter Gear Box | 2027-07-30 | 2027-07-30 | 4 hrs | FY28 | 4 | 90030281 | A1 | 1000304649 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-PTOLU | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-PTOLU90030281
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Pump Oil Replenishing | 2027-07-30 | 2027-07-30 | 4 hrs | FY28 | 4 | 90030285 | A1 | 1000304650 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-RPPP1 | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-RPPP190030285
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Ladder Raise | 2027-07-30 | 2027-07-30 | 3 hrs | FY28 | 6 | 90030320 | A1 | 1000304656 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-LACYL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-LACYL90030320
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Rotary Connection | 2027-07-30 | 2027-08-01 | 48 hrs | FY28 | 72 | 90029901 | A1 | 1000304568 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-ROTRY | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-ROTRY90029901
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Valve Pressure Reducing Y3 | 2027-07-30 | 2027-07-30 | 6 hrs | FY28 | 6 | 90030294 | A1 | 1000304655 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPRV | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPRV90030294
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Motor Swing Front | 2027-07-30 | 2027-07-31 | 18 hrs | FY28 | 26 | 90029905 | A1 | 1000304570 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-SWMOF | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-SWMOF90029905
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Motor Swing Rear | 2027-07-30 | 2027-07-31 | 18 hrs | FY28 | 26 | 90029905 | A1 | 1000304569 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-SWMOR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-SWMOR90029905
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Motor Travel LHF | 2027-07-30 | 2027-07-30 | 6 hrs | FY28 | 10 | 90029906 | A1 | 1000304571 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMLF | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMLF90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Motor Travel LHR | 2027-07-30 | 2027-07-30 | 6 hrs | FY28 | 10 | 90029906 | A1 | 1000304572 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMLR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMLR90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Motor Travel RHF | 2027-07-30 | 2027-07-30 | 6 hrs | FY28 | 10 | 90029906 | A1 | 1000304573 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMRF | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMRF90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Motor Travel RHR | 2027-07-30 | 2027-07-30 | 6 hrs | FY28 | 10 | 90029906 | A1 | 1000304574 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMRR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMRR90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Accumulator Track Hyd LH | 2027-07-30 | 2027-07-30 | 3 hrs | FY28 | 3 | 90029907 | A1 | 1000304575 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC90029907
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Accumulator Track Hyd RH | 2027-07-30 | 2027-07-30 | 3 hrs | FY28 | 3 | 90029907 | A1 | 1000304576 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC90029907
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Tank Module | 2027-07-30 | 2027-07-31 | 36 hrs | FY28 | 84 | 90030313 | A1 | 1000304640 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-STRUCT-HDTNK | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-STRUCT-HDTNK90030313
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Service Arm Locking Cyl | 2027-07-30 | 2027-07-30 | 12 hrs | FY28 | 20 | 90029983 | A1 | 1000304634 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-STRUCT-SRVCT | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-STRUCT-SRVCT90029983
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Service Module Hosing | 2027-07-30 | 2027-07-30 | 12 hrs | FY28 | 24 | 90029982 | A1 | 1000304633 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-STRUCT-SRVCT | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-STRUCT-SRVCT90029982
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Bucket Assembly | 2027-07-30 | 2027-08-01 | 42 hrs | FY28 | 78 | 90029975 | A1 | 1000304626 | 30.07.2027 | 20000 | CLB-MP-EXCV-EX7133-STRUCT-BUCKT | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-STRUCT-BUCKT90029975
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2027-07-31 | 2027-07-31 | 4 hrs | FY28 | 4 | 90022746 | A1 | 1000237212 | 31.07.2027 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos1 | 2027-08-01 | 2027-08-03 | 42 hrs | FY28 | 64 | 90027490 | A1 | 1000297330 | 01.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP1 | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP190027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos2 | 2027-08-01 | 2027-08-03 | 42 hrs | FY28 | 64 | 90027490 | A1 | 1000297331 | 01.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP2 | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP290027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Pos1 & Pos2 | 2027-08-01 | 2027-08-02 | 26 hrs | FY28 | 42 | 90027492 | A1 | 1000297334 | 01.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP1P2 | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP1P290027492
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Annual Air Con Service RH | 2027-08-04 | 2027-08-04 | 12 hrs | FY28 | 12 | 90022660 | A1 | 1000237208 | 04.08.2027 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR | 6700 | 27054 | 19941 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR90022660
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2027-08-05 | 2027-08-05 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359909 | 05.08.2027 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos2 | 2027-08-05 | 2027-08-07 | 42 hrs | FY28 | 54 | 90003162 | A1 | 1000158825 | 05.08.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP2 | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP290003162
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Track Tensioner LH | 2027-08-06 | 2027-08-06 | 12 hrs | FY28 | 24 | 90022668 | A1 | 1000237074 | 06.08.2027 | 18000 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-TENSR | 6700 | 25972 | 10895 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-TENSR90022668
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos1 | 2027-08-07 | 2027-08-09 | 42 hrs | FY28 | 54 | 90003162 | A1 | 1000158824 | 07.08.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP1 | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP190003162
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Replenish LH | 2027-08-07 | 2027-08-07 | 2 hrs | FY28 | 2 | 90003166 | A1 | 1000158834 | 07.08.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPL | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPL90003166
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Hose Bucket Cyl | 2027-08-09 | 2027-08-10 | 18 hrs | FY28 | 54 | 90030738 | A1 | 1000337253 | 09.08.2027 | 8000 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBKCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Hose Boom Cyl | 2027-08-09 | 2027-08-09 | 8 hrs | FY28 | 24 | 90030735 | A1 | 1000337252 | 09.08.2027 | 8000 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBMCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Hose Stick Cyl | 2027-08-09 | 2027-08-09 | 12 hrs | FY28 | 24 | 90030737 | A1 | 1000337254 | 09.08.2027 | 8000 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HSTCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HSTCL90030737
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl 24V Batteries | 2027-08-11 | 2027-08-11 | 5 hrs | FY28 | 9 | 90029978 | A1 | 1000357483 | 11.08.2027 | 12 Monthly | CLB-MP-EXCV-EX7148-ELCTLV-CHARG-BATST | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-ELCTLV-CHARG-BATST90029978
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Hydraulic Service & Repairs | 2027-08-11 | 2027-08-12 | 18 hrs | FY28 | 30 | 90029940 | A1 | 1000357445 | 11.08.2027 | 12 Monthly | CLB-MP-EXCV-EX7148-HYDSYS |  |  |  | CLB-MP-EXCV-EX7148-HYDSYS90029940
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Grease Tank Level Valve | 2027-08-11 | 2027-08-11 | 2 hrs | FY28 | 2 | 90029942 | A1 | 1000357447 | 11.08.2027 | 12 Monthly | CLB-MP-EXCV-EX7148-GRSYST |  |  |  | CLB-MP-EXCV-EX7148-GRSYST90029942
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Oil Cooler Front | 2027-08-16 | 2027-08-17 | 36 hrs | FY28 | 48 | 90003170 | A1 | 1000158842 | 16.08.2027 | 24000 | CLB-MP-EXCV-EX014 -HYDSYS-HDOCO-OCHYF | 6700 | 42775 | 16486 | CLB-MP-EXCV-EX014 -HYDSYS-HDOCO-OCHYF90003170
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Oil Cooler Rear | 2027-08-16 | 2027-08-17 | 36 hrs | FY28 | 48 | 90003170 | A1 | 1000158843 | 16.08.2027 | 24000 | CLB-MP-EXCV-EX014 -HYDSYS-HDOCO-OCHYR | 6700 | 42775 | 16486 | CLB-MP-EXCV-EX014 -HYDSYS-HDOCO-OCHYR90003170
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Swing Circuit Hoses | 2027-08-20 | 2027-08-20 | 8 hrs | FY28 | 16 | 90009481 | 1 | 1000158876 | 20.08.2027 | 9000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWCRT | 6700 | 42775 | 368 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWCRT90009481
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Fan Hyd Cool Rear | 2027-08-20 | 2027-08-20 | 6 hrs | FY28 | 12 | 90003176 | A1 | 1000158849 | 20.08.2027 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMCHR | 6700 | 42775 | 10414 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMCHR90003176
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 6M Anritsu Test WiFi Cables | 2027-08-20 | 2027-08-20 | 2 hrs | FY28 | 2 | 90020303 | A1 | 1000210997 | 20.08.2027 | 6 Monthly | CLB-MP-EXCV-EX7112-COMMUN-FLMGT |  |  |  | CLB-MP-EXCV-EX7112-COMMUN-FLMGT90020303
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2027-08-21 | 2027-08-21 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359910 | 21.08.2027 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Grease System Audit | 2027-08-21 | 2027-08-22 | 24 hrs | FY28 | 36 | 90030748 | A1 | 1000348548 | 21.08.2027 | 5000 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ90030748
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Inspection Isolator Panel | 2027-08-22 | 2027-08-22 | 2 hrs | FY28 | 2 | 90029980 | 1 | 1000357484 | 22.08.2027 | 12 Monthly | CLB-MP-EXCV-EX7148-ELCTLV |  |  |  | CLB-MP-EXCV-EX7148-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Minestar Harness | 2027-08-24 | 2027-08-25 | 27.5 hrs | FY28 | 43.5 | 90029998 | A1 | 1000357494 | 24.08.2027 | 4000 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC90029998
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Replenish LH | 2027-08-28 | 2027-08-28 | 2 hrs | FY28 | 2 | 90027495 | A1 | 1000297340 | 28.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPL90027495
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Servo LH | 2027-08-28 | 2027-08-28 | 2 hrs | FY28 | 2 | 90027496 | A1 | 1000297338 | 28.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPL | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPL90027496
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Servo RH | 2027-08-28 | 2027-08-28 | 2 hrs | FY28 | 2 | 90027496 | A1 | 1000297339 | 28.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPR | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPR90027496
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Auto Lube Pump | 2027-08-29 | 2027-08-29 | 6 hrs | FY28 | 6 | 90027592 | A1 | 1000297398 | 29.08.2027 | 6000 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP90027592
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Grease Control Valving | 2027-08-29 | 2027-08-29 | 14 hrs | FY28 | 14 | 90027612 | A1 | 1000297399 | 29.08.2027 | 12000 | CLB-MP-EXCV-EX7122-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7122-GRSYST-ALCON90027612
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Fan Drive Eng Cooling Hose | 2027-08-29 | 2027-08-30 | 18 hrs | FY28 | 36 | 90027564 | A1 | 1000297367 | 29.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDECH | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDECH90027564
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Swing Motor Case Drain Hoses | 2027-08-29 | 2027-08-29 | 6 hrs | FY28 | 12 | 90027577 | A1 | 1000297380 | 29.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWMCD | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWMCD90027577
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos3 | 2027-08-29 | 2027-08-31 | 42 hrs | FY28 | 64 | 90027490 | A1 | 1000297332 | 29.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP3 | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP390027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos4 | 2027-08-29 | 2027-08-31 | 42 hrs | FY28 | 64 | 90027490 | A1 | 1000297333 | 29.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP4 | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP490027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Pos3 & Pos4 | 2027-08-29 | 2027-08-30 | 26 hrs | FY28 | 42 | 90027492 | A1 | 1000297335 | 29.08.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP3P4 | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP3P490027492
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Minestar Harness | 2027-08-31 | 2027-09-01 | 27.5 hrs | FY28 | 43.5 | 90029998 | A1 | 1000359599 | 31.08.2027 | 4000 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC90029998
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Bucket LH Lift | 2027-09-04 | 2027-09-05 | 30 hrs | FY28 | 54 | 90030725 | A1 | 1000340296 | 04.09.2027 | 10000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYL | 6200 | 9369 | 2193 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYL90030725
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Minestar Harness | 2027-09-09 | 2027-09-10 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000312852 | 09.09.2027 | 4000 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Fan Drive Hyd Cooling Hoses | 2027-09-09 | 2027-09-10 | 18 hrs | FY28 | 36 | 90022727 | A1 | 1000345666 | 09.09.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDHCH | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDHCH90022727
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Track Tensioning Hoses | 2027-09-09 | 2027-09-09 | 3 hrs | FY28 | 3 | 90022741 | A1 | 1000237067 | 09.09.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TRTNH | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TRTNH90022741
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic Oil Replacement | 2027-09-10 | 2027-09-10 | 12 hrs | FY28 | 12 | 90016793 | 1 | 1000158890 | 10.09.2027 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic System Tune Up | 2027-09-10 | 2027-09-10 | 12 hrs | FY28 | 24 | 90017865 | 1 | 1000163743 | 10.09.2027 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Swing Motor Case Drain Hoses | 2027-09-10 | 2027-09-10 | 6 hrs | FY28 | 12 | 90022739 | A1 | 1000158877 | 10.09.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWMCD | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel LHR | 2027-09-10 | 2027-09-10 | 6 hrs | FY28 | 12 | 90003178 | A1 | 1000158853 | 10.09.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLR | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLR90003178
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Stick RH | 2027-09-11 | 2027-09-12 | 30 hrs | FY28 | 54 | 90022646 | A1 | 1000237161 | 11.09.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLR | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLR90022646
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Hyd Pump Pos3 | 2027-09-11 | 2027-09-13 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237148 | 11.09.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP3 | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP390022637
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Minestar Harness | 2027-09-12 | 2027-09-13 | 27.5 hrs | FY28 | 43.5 | 90029998 | A1 | 1000304641 | 12.09.2027 | 4000 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC90029998
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Engine Midlife Complete LH | 2027-09-13 | 2027-09-15 | 56 hrs | FY28 | 66 | 90027554 | A1 | 1000284517 | 13.09.2027 | 9000 | CLB-MP-EXCV-EX7124-LHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-LHENGN90027554
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Engine Midlife Complete RH | 2027-09-13 | 2027-09-15 | 56 hrs | FY28 | 66 | 90027554 | A1 | 1000284583 | 13.09.2027 | 9000 | CLB-MP-EXCV-EX7124-RHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-RHENGN90027554
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Boom Stick Bucket Cyl Hoses | 2027-09-13 | 2027-09-16 | 88 hrs | FY28 | 136 | 90022725 | A1 | 1000345664 | 13.09.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HBSBC | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HBSBC90022725
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom Stick Bucket Cyl Hoses | 2027-09-15 | 2027-09-18 | 88 hrs | FY28 | 136 | 90027560 | A1 | 1000297366 | 15.09.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC90027560
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom & MCV Hoses | 2027-09-15 | 2027-09-18 | 88 hrs | FY28 | 136 | 90032593 | A1 | 1000325060 | 15.09.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC90032593
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Oil Cooler Front | 2027-09-15 | 2027-09-16 | 36 hrs | FY28 | 48 | 90027500 | A1 | 1000297348 | 15.09.2027 | 24000 | CLB-MP-EXCV-EX7122-HYDSYS-HDOCO-OCHYF | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDOCO-OCHYF90027500
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Oil Cooler Rear | 2027-09-15 | 2027-09-16 | 36 hrs | FY28 | 48 | 90027500 | A1 | 1000297349 | 15.09.2027 | 24000 | CLB-MP-EXCV-EX7122-HYDSYS-HDOCO-OCHYR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDOCO-OCHYR90027500
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Rotary Joint | 2027-09-15 | 2027-09-16 | 24 hrs | FY28 | 48 | 90027501 | A1 | 1000297350 | 15.09.2027 | 24000 | CLB-MP-EXCV-EX7122-HYDSYS-ROTRY | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-ROTRY90027501
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Minestar Harness | 2027-09-15 | 2027-09-16 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000370302 | 15.09.2027 | 4000 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Final Drive LH | 2027-09-15 | 2027-09-17 | 48 hrs | FY28 | 144 | 90027485 | A1 | 1000297323 | 15.09.2027 | 24000 | CLB-MP-EXCV-EX7122-TRAVEL-FDRLH | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-TRAVEL-FDRLH90027485
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Final Drive RH | 2027-09-15 | 2027-09-17 | 48 hrs | FY28 | 144 | 90027485 | A1 | 1000297324 | 15.09.2027 | 24000 | CLB-MP-EXCV-EX7122-TRAVEL-FDRRH | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-TRAVEL-FDRRH90027485
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Operators Seat | 2027-09-17 | 2027-09-17 | 9 hrs | FY28 | 17 | 90030739 | A1 | 1000330525 | 17.09.2027 | 10000 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-SEATO | 6200 | 11792 | 3070 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-SEATO90030739
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Track Tension Tuning-Adjust | 2027-09-19 | 2027-09-19 | 3 hrs | FY28 | 9 | 90029977 | A1 | 1000357482 | 19.09.2027 | 6 Monthly | CLB-MP-EXCV-EX7148-UNDERC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-UNDERC90029977
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Track Tensioner LH | 2027-09-20 | 2027-09-20 | 12 hrs | FY28 | 24 | 90022668 | A1 | 1000237205 | 20.09.2027 | 18000 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-TENSR | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-TENSR90022668
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Track Tensioner RH | 2027-09-20 | 2027-09-20 | 12 hrs | FY28 | 24 | 90022668 | A1 | 1000237206 | 20.09.2027 | 18000 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-TENSR | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-TENSR90022668
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Inspection Isolator Panel | 2027-09-21 | 2027-09-21 | 2 hrs | FY28 | 2 | 90029980 | 1 | 1000359589 | 21.09.2027 | 12 Monthly | CLB-MP-EXCV-EX7149-ELCTLV |  |  |  | CLB-MP-EXCV-EX7149-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl 24V Batteries | 2027-09-21 | 2027-09-21 | 5 hrs | FY28 | 9 | 90029978 | A1 | 1000359588 | 21.09.2027 | 12 Monthly | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST90029978
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Hydraulic Service & Repairs | 2027-09-21 | 2027-09-22 | 18 hrs | FY28 | 30 | 90029940 | A1 | 1000359550 | 21.09.2027 | 12 Monthly | CLB-MP-EXCV-EX7149-HYDSYS |  |  |  | CLB-MP-EXCV-EX7149-HYDSYS90029940
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Grease Tank Level Valve | 2027-09-21 | 2027-09-21 | 2 hrs | FY28 | 2 | 90029942 | A1 | 1000359552 | 21.09.2027 | 12 Monthly | CLB-MP-EXCV-EX7149-GRSYST |  |  |  | CLB-MP-EXCV-EX7149-GRSYST90029942
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2027-09-22 | 2027-09-22 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359913 | 22.09.2027 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Hydraulic Oil Replacement | 2027-09-23 | 2027-09-23 | 12 hrs | FY28 | 12 | 90016793 | 1 | 1000207153 | 23.09.2027 | 6000 | CLB-MP-EXCV-EX7112-HYDSYS | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cylinder Bucket LH | 2027-09-24 | 2027-09-25 | 26 hrs | FY28 | 32 | 90027499 | A1 | 1000297346 | 24.09.2027 | 10000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYL | 6700 | 16452 | 2288 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYL90027499
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Track Tension Tuning-Adjust | 2027-09-24 | 2027-09-24 | 3 hrs | FY28 | 9 | 90020545 | A1 | 1000348591 | 24.09.2027 | 6 Monthly | CLB-MP-EXCV-EX7141-UNDERC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Svc 12M Air Conditioner Sys1 Eng | 2027-09-24 | 2027-09-24 | 12 hrs | FY28 | 12 | 90035241 | A1 | 1000359793 | 24.09.2027 | 12 Monthly | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC1 | 6500 | 4530 | 4530 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC190035241
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Svc 12M Air Conditioner Sys2 Hyd | 2027-09-24 | 2027-09-24 | 12 hrs | FY28 | 12 | 90035242 | A1 | 1000359795 | 24.09.2027 | 12 Monthly | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC290035242
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Auto Lube SStructure | 2027-09-25 | 2027-09-25 | 12 hrs | FY28 | 12 | 90018988 | 1 | 1000207165 | 25.09.2027 | 6000 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP90018988
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Grease Control Valving | 2027-09-25 | 2027-09-26 | 18 hrs | FY28 | 18 | 90018990 | 1 | 1000207167 | 25.09.2027 | 12000 | CLB-MP-EXCV-EX7112-GRSYST-ALCON | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-GRSYST-ALCON90018990
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Hydraulic System Tune Up | 2027-09-25 | 2027-09-25 | 12 hrs | FY28 | 24 | 90017865 | 1 | 1000207164 | 25.09.2027 | 6000 | CLB-MP-EXCV-EX7112-HYDSYS | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Travel Motor Case Drain Hose | 2027-09-25 | 2027-09-25 | 5 hrs | FY28 | 10 | 90022740 | A1 | 1000207147 | 25.09.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-TMCDH | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-TMCDH90022740
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Adjust 4500hr Valve Set | 2027-09-29 | 2027-09-29 | 10 hrs | FY28 | 20 | 90022679 | A1 | 1000237004 | 29.09.2027 | 4500 | CLB-MP-EXCV-EX7118-RHENGN | 6700 | 25972 | 14409 | CLB-MP-EXCV-EX7118-RHENGN90022679
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Bucket RH Lift | 2027-09-30 | 2027-10-01 | 30 hrs | FY28 | 54 | 90030726 | A1 | 1000348545 | 30.09.2027 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYR | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYR90030726
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Minestar Harness | 2027-09-30 | 2027-10-01 | 27.5 hrs | FY28 | 43.5 | 90030746 | A1 | 1000348553 | 30.09.2027 | 5000 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC90030746
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Adjust Track Tension Tuning | 2027-10-01 | 2027-10-01 | 3 hrs | FY28 | 9 | 90029977 | A1 | 1000304629 | 01.10.2027 | 6 Monthly | CLB-MP-EXCV-EX7133-UNDERC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC90029977
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Operators Seat | 2027-10-03 | 2027-10-03 | 9 hrs | FY28 | 17 | 90030739 | A1 | 1000340287 | 03.10.2027 | 10000 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-SEATO | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-SEATO90030739
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Grease Tank Level Valve | 2027-10-03 | 2027-10-03 | 2 hrs | FY28 | 2 | 90015003 | A1 | 1000330541 | 03.10.2027 | 12 Monthly | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 12M Hydraulic Service & Repairs | 2027-10-08 | 2027-10-09 | 18 hrs | FY28 | 30 | 90014448 | A1 | 1000330356 | 08.10.2027 | 12 Monthly | CLB-MP-EXCV-EX7139-HYDSYS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Swing Circuit Hoses | 2027-10-11 | 2027-10-11 | 8 hrs | FY28 | 16 | 90027576 | A1 | 1000297379 | 11.10.2027 | 9000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWCRT | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWCRT90027576
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2027-10-13 | 2027-10-13 | 4 hrs | FY28 | 4 | 90022746 | A1 | 1000237081 | 13.10.2027 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Adjust 4500hr Valve Set | 2027-10-15 | 2027-10-15 | 10 hrs | FY28 | 20 | 90022679 | A1 | 1000237120 | 15.10.2027 | 4500 | CLB-MP-EXCV-EX7119-LHENGN | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-LHENGN90022679
6060 | Onsite PM | Excavators | Fortescue | EX108 | EX108 Fan Drive Crct Eng Cooling Hoses | 2027-10-18 | 2027-10-18 | 12 hrs | FY28 | 24 | 90009239 | 1 | 1000074213 | 18.10.2027 | 12000 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-FDEC | 7500 | 79029 | 15911 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-FDEC90009239
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Hydraulic Oil Replacement | 2027-10-19 | 2027-10-19 | 12 hrs | FY28 | 12 | 90016793 | 1 | 1000297387 | 19.10.2027 | 6000 | CLB-MP-EXCV-EX7122-HYDSYS | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Hydraulic System Tune Up | 2027-10-19 | 2027-10-19 | 12 hrs | FY28 | 24 | 90017865 | 1 | 1000297397 | 19.10.2027 | 6000 | CLB-MP-EXCV-EX7122-HYDSYS | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Rotor to Drive Motor Hoses | 2027-10-19 | 2027-10-20 | 20 hrs | FY28 | 40 | 90027570 | A1 | 1000297374 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-RCDMH | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-RCDMH90027570
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 2nd Speed Trvl Brake Release Hose | 2027-10-19 | 2027-10-19 | 5 hrs | FY28 | 10 | 90027559 | A1 | 1000297364 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SSTBR | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SSTBR90027559
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Travel Motor Case Drain Hoses | 2027-10-19 | 2027-10-19 | 5 hrs | FY28 | 10 | 90027578 | A1 | 1000297381 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-TMCDH | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-TMCDH90027578
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Track Tensioning Hoses | 2027-10-19 | 2027-10-19 | 3 hrs | FY28 | 3 | 90027579 | A1 | 1000297382 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-TRTNH | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-TRTNH90027579
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Travel RHF | 2027-10-19 | 2027-10-19 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000297360 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMRF | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMRF90027506
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Travel RHR | 2027-10-19 | 2027-10-19 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000297361 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMRR | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMRR90027506
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Replenish RH | 2027-10-19 | 2027-10-19 | 2 hrs | FY28 | 2 | 90027495 | A1 | 1000297341 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPR90027495
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Boom LH | 2027-10-19 | 2027-10-21 | 42 hrs | FY28 | 78 | 90030723 | A1 | 1000348542 | 19.10.2027 | 16000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BMCYL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BMCYL90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Boom RH | 2027-10-19 | 2027-10-21 | 42 hrs | FY28 | 78 | 90030723 | A1 | 1000348543 | 19.10.2027 | 16000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BMCYR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BMCYR90030723
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Stick LH | 2027-10-19 | 2027-10-20 | 30 hrs | FY28 | 54 | 90030724 | A1 | 1000348546 | 19.10.2027 | 16000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-STCLL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-STCLL90030724
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Stick RH | 2027-10-19 | 2027-10-20 | 30 hrs | FY28 | 54 | 90030724 | A1 | 1000348547 | 19.10.2027 | 16000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-STCLR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-STCLR90030724
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Pump Servo LH | 2027-10-19 | 2027-10-19 | 2 hrs | FY28 | 2 | 90022661 | A1 | 1000237023 | 19.10.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPL | 6700 | 25972 | 3545 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPL90022661
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Svc 12M Air Conditioner Sys1 Eng | 2027-10-20 | 2027-10-20 | 12 hrs | FY28 | 12 | 90035236 | A1 | 1000359797 | 20.10.2027 | 12 Monthly | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC1 | 6500 | 4257 | 4257 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC190035236
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Svc 12M Air Conditioner Sys2 Hyd | 2027-10-20 | 2027-10-20 | 12 hrs | FY28 | 12 | 90035237 | A1 | 1000359799 | 20.10.2027 | 12 Monthly | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC290035237
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Fan Hyd Cool Rear | 2027-10-21 | 2027-10-21 | 6 hrs | FY28 | 12 | 90022655 | A1 | 1000237171 | 21.10.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMCHR | 6700 | 27054 | 9736 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMCHR90022655
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Fan Engine Cool LH | 2027-10-21 | 2027-10-21 | 6 hrs | FY28 | 12 | 90022642 | A1 | 1000237152 | 21.10.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HECPL | 6700 | 27054 | 9736 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HECPL90022642
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Fan Engine Cool RH | 2027-10-21 | 2027-10-21 | 6 hrs | FY28 | 12 | 90022642 | A1 | 1000237153 | 21.10.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HECPR | 6700 | 27054 | 9736 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HECPR90022642
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Boom Stick Bucket Cyl Hoses | 2027-10-22 | 2027-10-25 | 88 hrs | FY28 | 136 | 90009468 | 1 | 1000158863 | 22.10.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HBSBC | 6700 | 42775 | 16172 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HBSBC90009468
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Auto Lube Pump | 2027-10-22 | 2027-10-22 | 6 hrs | FY28 | 6 | 90022747 | A1 | 1000237215 | 22.10.2027 | 6000 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP90022747
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Grease Control Valving | 2027-10-22 | 2027-10-22 | 16 hrs | FY28 | 16 | 90022749 | A1 | 1000237217 | 22.10.2027 | 12000 | CLB-MP-EXCV-EX7119-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7119-GRSYST-ALCON90022749
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Boom Arch Hoses | 2027-10-24 | 2027-10-24 | 12 hrs | FY28 | 24 | 90022724 | A1 | 1000158862 | 24.10.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-BMARH | 6700 | 42775 | 746 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-BMARH90022724
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Adjust Track Tension Tuning | 2027-10-26 | 2027-10-26 | 3 hrs | FY28 | 9 | 90020545 | A1 | 1000337320 | 26.10.2027 | 6 Monthly | CLB-MP-EXCV-EX7140-UNDERC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Fan Drive Eng Cooling Hose | 2027-10-27 | 2027-10-28 | 18 hrs | FY28 | 36 | 90022726 | A1 | 1000237183 | 27.10.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-FDECH | 6700 | 27054 | 3710 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-FDECH90022726
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Fan Drive Hyd Cooling Hoses | 2027-10-27 | 2027-10-28 | 18 hrs | FY28 | 36 | 90022727 | A1 | 1000237184 | 27.10.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-FDHCH | 6700 | 27054 | 3710 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-FDHCH90022727
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Adjust 4500hr Valve Set | 2027-10-28 | 2027-10-28 | 10 hrs | FY28 | 20 | 90017923 | A1 | 1000158797 | 28.10.2027 | 4500 | CLB-MP-EXCV-EX014 -LHENGN | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -LHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos4 | 2027-10-31 | 2027-11-02 | 42 hrs | FY28 | 54 | 90003162 | A1 | 1000158827 | 31.10.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP4 | 6700 | 42775 | 3088 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP490003162
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Pump Servo LH | 2027-10-31 | 2027-10-31 | 2 hrs | FY28 | 2 | 90010935 | 1 | 1000158832 | 31.10.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SVPPL | 6700 | 42775 | 3088 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SVPPL90010935
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Pump Servo RH | 2027-10-31 | 2027-10-31 | 2 hrs | FY28 | 2 | 90010935 | 1 | 1000158833 | 31.10.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SVPPR | 6700 | 42775 | 3088 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SVPPR90010935
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cylinder Bucket RH | 2027-11-01 | 2027-11-02 | 26 hrs | FY28 | 32 | 90003169 | A1 | 1000158841 | 01.11.2027 | 10000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYR | 6700 | 42775 | 746 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYR90003169
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 12M Inspection Isolator Panel | 2027-11-02 | 2027-11-02 | 2 hrs | FY28 | 2 | 90022525 | A2 | 1000336837 | 02.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7140-ELCTLV |  |  |  | CLB-MP-EXCV-EX7140-ELCTLV90022525
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 12M Inspection Isolator Panel | 2027-11-02 | 2027-11-02 | 2 hrs | FY28 | 2 | 90022525 | A2 | 1000330357 | 02.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7139-ELCTLV |  |  |  | CLB-MP-EXCV-EX7139-ELCTLV90022525
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2027-11-02 | 2027-11-02 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359909 | 02.11.2027 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Final Drive LH | 2027-11-02 | 2027-11-04 | 48 hrs | FY28 | 144 | 90003155 | A1 | 1000158816 | 02.11.2027 | 24000 | CLB-MP-EXCV-EX014 -TRAVEL-FDRLH | 6700 | 42775 | 15061 | CLB-MP-EXCV-EX014 -TRAVEL-FDRLH90003155
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Operators Seat | 2027-11-02 | 2027-11-02 | 2 hrs | FY28 | 2 | 90022750 | A1 | 1000237179 | 02.11.2027 | 10000 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-SEATS | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-SEATS90022750
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 2nd Speed Trvl Brake Release Hose | 2027-11-03 | 2027-11-03 | 5 hrs | FY28 | 10 | 90022723 | A1 | 1000207130 | 03.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SSTBR | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SSTBR90022723
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Rotor to Drive Motor Hoses | 2027-11-03 | 2027-11-03 | 10 hrs | FY28 | 20 | 90022733 | A1 | 1000207140 | 03.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-RCDMH | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-RCDMH90022733
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel LHR | 2027-11-03 | 2027-11-03 | 6 hrs | FY28 | 12 | 90022657 | A1 | 1000207125 | 03.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLR | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLR90022657
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Static Line Inspection | 2027-11-05 | 2027-11-05 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000340340 | 05.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7138-STRUCT | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT90014347
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Stick LH | 2027-11-06 | 2027-11-07 | 30 hrs | FY28 | 54 | 90003168 | A1 | 1000207110 | 06.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-STCLL | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-STCLL90003168
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Stick RH | 2027-11-06 | 2027-11-07 | 30 hrs | FY28 | 54 | 90003168 | A1 | 1000207111 | 06.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-STCLR | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-STCLR90003168
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Rotor & Logic Valve Hp Hoses | 2027-11-06 | 2027-11-07 | 18 hrs | FY28 | 36 | 90009477 | 1 | 1000207141 | 06.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-RCLVH | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-RCLVH90009477
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos3 | 2027-11-06 | 2027-11-08 | 42 hrs | FY28 | 54 | 90003162 | A1 | 1000207098 | 06.11.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP3 | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP390003162
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Grease Tank Level Valve | 2027-11-12 | 2027-11-12 | 2 hrs | FY28 | 2 | 90015003 | A1 | 1000337280 | 12.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Boom Module Quarter Life | 2027-11-14 | 2027-11-15 | 30 hrs | FY28 | 48 | 90027377 | A1 | 1000330506 | 14.11.2027 | 10000 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90027377
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Inspection Ext Static Line | 2027-11-15 | 2027-11-15 | 4 hrs | FY28 | 4 | 90029897 | A1 | 1000304563 | 15.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Gearbox Swing LHR | 2027-11-16 | 2027-11-18 | 48 hrs | FY28 | 80 | 90012369 | 1 | 1000207091 | 16.11.2027 | 20000 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBLR | 6700 | 31524 | 11232 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBLR90012369
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Gearbox Swing RHF | 2027-11-16 | 2027-11-18 | 48 hrs | FY28 | 80 | 90012369 | 1 | 1000207092 | 16.11.2027 | 20000 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBRF | 6700 | 31524 | 11232 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBRF90012369
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Gearbox Swing RHR | 2027-11-16 | 2027-11-18 | 48 hrs | FY28 | 80 | 90012369 | 1 | 1000207093 | 16.11.2027 | 20000 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBRR | 6700 | 31524 | 11232 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBRR90012369
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Inspection Isolator Panel | 2027-11-17 | 2027-11-17 | 2 hrs | FY28 | 2 | 90029980 | 1 | 1000304631 | 17.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7133-ELCTLV |  |  |  | CLB-MP-EXCV-EX7133-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Grease Tank Level Valve | 2027-11-17 | 2027-11-17 | 2 hrs | FY28 | 2 | 90029942 | A1 | 1000304596 | 17.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7133-GRSYST |  |  |  | CLB-MP-EXCV-EX7133-GRSYST90029942
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2027-11-18 | 2027-11-18 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359910 | 18.11.2027 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cyl Boom LH | 2027-11-18 | 2027-11-22 | 90 hrs | FY28 | 138 | 90003167 | A1 | 1000158836 | 18.11.2027 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BMCYL | 6700 | 42775 | 9748 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BMCYL90003167
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cyl Boom RH | 2027-11-18 | 2027-11-22 | 90 hrs | FY28 | 138 | 90003167 | A1 | 1000158837 | 18.11.2027 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BMCYR | 6700 | 42775 | 8761 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BMCYR90003167
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Fan Hyd Cool Rear | 2027-11-18 | 2027-11-18 | 6 hrs | FY28 | 12 | 90003176 | A1 | 1000207121 | 18.11.2027 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMCHR | 6700 | 31524 | 9101 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMCHR90003176
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Grease Tank Level Valve | 2027-11-19 | 2027-11-19 | 2 hrs | FY28 | 2 | 90015003 | A1 | 1000340303 | 19.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK | 6200 | 9369 | 2810 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Svc 12M Air Conditioner Sys1 Eng | 2027-11-23 | 2027-11-23 | 12 hrs | FY28 | 12 | 90035241 | A1 | 1000359809 | 23.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC1 | 6000 | 3940 | 3940 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC190035241
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Svc 12M Air Conditioner Sys2 Hyd | 2027-11-23 | 2027-11-23 | 12 hrs | FY28 | 12 | 90035242 | A1 | 1000359811 | 23.11.2027 | 12 Monthly | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC290035242
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Servo Hoses Cascade to Trvl Valve | 2027-11-23 | 2027-11-23 | 6 hrs | FY28 | 12 | 90027575 | A1 | 1000297378 | 23.11.2027 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHTRV | 6700 | 16452 | 3193 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHTRV90027575
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Inspection Ext Static Line | 2027-11-23 | 2027-11-23 | 4 hrs | FY28 | 4 | 90029897 | A1 | 1000359517 | 23.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029897
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Pump Swing Combination | 2027-11-24 | 2027-11-25 | 24 hrs | FY28 | 36 | 90030252 | A1 | 1000304646 | 24.11.2027 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-SWPP1 | 6200 | 13908 | 1906 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-SWPP190030252
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Auto Lube Pump P1 | 2027-11-24 | 2027-11-24 | 2 hrs | FY28 | 2 | 90030312 | A1 | 1000304586 | 24.11.2027 | 10000 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBPP | 6200 | 13908 | 1906 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBPP90030312
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 4500hr Valve Set | 2027-11-24 | 2027-11-24 | 10 hrs | FY28 | 20 | 90017923 | A1 | 1000207070 | 24.11.2027 | 4500 | CLB-MP-EXCV-EX7112-LHENGN | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-LHENGN90017923
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Boom Module Quarter Life | 2027-11-25 | 2027-11-26 | 30 hrs | FY28 | 48 | 90027377 | A1 | 1000337246 | 25.11.2027 | 10000 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90027377
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Oil Suction Hoses | 2027-11-25 | 2027-11-26 | 24 hrs | FY28 | 48 | 90022731 | A1 | 1000237188 | 25.11.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-OILSC | 6700 | 27054 | 9084 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-OILSC90022731
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl PTO Cooling Hoses | 2027-11-25 | 2027-11-25 | 6 hrs | FY28 | 12 | 90022732 | A1 | 1000237189 | 25.11.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-PTOCL | 6700 | 27054 | 9084 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-PTOCL90022732
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Pump Drive Gearbox LH | 2027-11-25 | 2027-11-26 | 36 hrs | FY28 | 108 | 90022636 | A1 | 1000237144 | 25.11.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-PPDRL | 6700 | 27054 | 9084 | CLB-MP-EXCV-EX7119-HYDSYS-PPDRL90022636
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2027-11-26 | 2027-11-26 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000337317 | 26.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Control Valve Block LH | 2027-11-27 | 2027-11-28 | 34 hrs | FY28 | 50 | 90022653 | A1 | 1000237199 | 27.11.2027 | 36000 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-MCVVL | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-MCVVL90022653
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Control Valve Block RH | 2027-11-27 | 2027-11-28 | 34 hrs | FY28 | 50 | 90022653 | A1 | 1000237200 | 27.11.2027 | 36000 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-MCVVR | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-MCVVR90022653
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Boom Assy Dressed | 2027-11-27 | 2027-12-02 | 116 hrs | FY28 | 324 | 90003181 | A1 | 1000314264 | 27.11.2027 | 36000 | CLB-MP-EXCV-EX7119-STRUCT-BOOMS | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-BOOMS90003181
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Stick Assy Dressed | 2027-11-27 | 2027-12-01 | 99 hrs | FY28 | 291 | 90003183 | A1 | 1000314267 | 27.11.2027 | 36000 | CLB-MP-EXCV-EX7119-STRUCT-STICK | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-STICK90003183
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Slew Gear Bearing | 2027-11-27 | 2027-12-01 | 96 hrs | FY28 | 288 | 90022659 | A1 | 1000237178 | 27.11.2027 | 36000 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022659
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2027-11-28 | 2027-11-28 | 4 hrs | FY28 | 4 | 90022746 | A1 | 1000237212 | 28.11.2027 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Track Tension Tuning-Adjust | 2027-11-29 | 2027-11-29 | 3 hrs | FY28 | 9 | 90020545 | A1 | 1000340343 | 29.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7138-UNDERC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2027-11-29 | 2027-11-29 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000348588 | 29.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2027-11-29 | 2027-11-29 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000330578 | 29.11.2027 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Pos3 & Pos4 | 2027-12-01 | 2027-12-02 | 26 hrs | FY28 | 42 | 90027492 | A1 | 1000284598 | 01.12.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP3P4 | 6700 | 19559 | 3107 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP3P490027492
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Power Pack Module | 2027-12-01 | 2027-12-03 | 64 hrs | FY28 | 172 | 90030914 | A1 | 1000330526 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90030914
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Grease Block & Injectors | 2027-12-01 | 2027-12-03 | 48 hrs | FY28 | 84 | 90030749 | A1 | 1000330539 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ90030749
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Accumulator Track Hyd LH | 2027-12-01 | 2027-12-01 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000330500 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCL90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Accumulator Track Hyd RH | 2027-12-01 | 2027-12-01 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000330501 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCR90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Ladder Raise Cyl | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 24 | 90030750 | A1 | 1000330542 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-LACYL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-LACYL90030750
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Service Arm Locking Cyl | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 20 | 90030752 | A1 | 1000330570 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-SHCYL |  |  |  | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-SHCYL90030752
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Motor Swing Front | 2027-12-01 | 2027-12-02 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000330544 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-SWMOF | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-SWMOF90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Motor Swing Rear | 2027-12-01 | 2027-12-02 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000330545 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-SWMOR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-SWMOR90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Motor Travel LHF | 2027-12-01 | 2027-12-01 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000330521 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMLF | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMLF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Motor Travel LHR | 2027-12-01 | 2027-12-01 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000330522 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMLR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMLR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Motor Travel RHF | 2027-12-01 | 2027-12-01 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000330523 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMRF | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMRF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Motor Travel RHR | 2027-12-01 | 2027-12-01 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000330524 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMRR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMRR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Hyd Vlve Bank Module Quarter Life | 2027-12-01 | 2027-12-01 | 9 hrs | FY28 | 15 | 90027371 | A1 | 1000330517 | 01.12.2027 | 10000 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-MCVLU | 6200 | 11792 | 1367 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-MCVLU90027371
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Rotary Connection & Hoses | 2027-12-01 | 2027-12-05 | 96 hrs | FY28 | 168 | 90030430 | A1 | 1000330574 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-HYDSYS-ROTRY | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS-ROTRY90030430
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Bucket | 2027-12-01 | 2027-12-03 | 42 hrs | FY28 | 78 | 90030745 | A1 | 1000330531 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-STRUCT-BUCKT | 6200 | 11792 | 2318 | CLB-MP-EXCV-EX7139-STRUCT-BUCKT90030745
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Tank Module | 2027-12-01 | 2027-12-02 | 38 hrs | FY28 | 86 | 90036464 | A1 | 1000330515 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-STRUCT-HDTNK | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-HDTNK90036464
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Service Module Hosing | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 24 | 90030753 | A1 | 1000330569 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-STRUCT-SRVCT-SHHLF |  |  |  | CLB-MP-EXCV-EX7139-STRUCT-SRVCT-SHHLF90030753
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Gearbox Swing P1 | 2027-12-01 | 2027-12-03 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000330510 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-SWGSYS-SWBOX-SGBPF | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-SWGSYS-SWBOX-SGBPF90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Gearbox Swing P2 | 2027-12-01 | 2027-12-03 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000330511 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-SWGSYS-SWBOX-SGBPR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-SWGSYS-SWBOX-SGBPR90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Track Idler LH | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000330518 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-IDLLH | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-IDLLH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Sprocket LH | 2027-12-01 | 2027-12-02 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000330519 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-SPRKL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-SPRKL90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Track Hyd Tensioner LH | 2027-12-01 | 2027-12-02 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000330582 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-TENSL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Track Assembly LH | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000330579 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-TRKLH | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-TRKLH90030719
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Track Idler RH | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000330572 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-IDLRH | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-IDLRH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Sprocket RH | 2027-12-01 | 2027-12-02 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000330573 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-SPRKR | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-SPRKR90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Track Hyd Tensioner RH | 2027-12-01 | 2027-12-02 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000330583 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-TENSL | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Track Assembly RH | 2027-12-01 | 2027-12-01 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000330580 | 01.12.2027 | 20000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-TRKRH | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-TRKRH90030719
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Wiper Blades | 2027-12-01 | 2027-12-01 | 2 hrs | FY28 | 2 | 90004684 | 1 | 1000163162 | 01.12.2027 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX014 -STRUCT-CABIN90004684
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cyl Boom RH | 2027-12-01 | 2027-12-05 | 90 hrs | FY28 | 138 | 90022644 | A1 | 1000237028 | 01.12.2027 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BMCYR | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BMCYR90022644
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Fan Hyd Cool Rear | 2027-12-01 | 2027-12-01 | 6 hrs | FY28 | 12 | 90022655 | A1 | 1000237040 | 01.12.2027 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMCHR | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMCHR90022655
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Fan Engine Cool RH | 2027-12-01 | 2027-12-01 | 6 hrs | FY28 | 12 | 90022642 | A1 | 1000237022 | 01.12.2027 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HECPR | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HECPR90022642
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Auto Lube Pump | 2027-12-02 | 2027-12-02 | 6 hrs | FY28 | 6 | 90022747 | A1 | 1000237084 | 02.12.2027 | 6000 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP90022747
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Grease Control Valving | 2027-12-02 | 2027-12-02 | 16 hrs | FY28 | 16 | 90022749 | A1 | 1000237086 | 02.12.2027 | 12000 | CLB-MP-EXCV-EX7118-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7118-GRSYST-ALCON90022749
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Hydraulic Oil Replacement | 2027-12-02 | 2027-12-02 | 12 hrs | FY28 | 12 | 90022667 | A1 | 1000237072 | 02.12.2027 | 6000 | CLB-MP-EXCV-EX7118-HYDSYS | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS90022667
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Fan Engine Cool RH | 2027-12-02 | 2027-12-02 | 6 hrs | FY28 | 18 | 90022656 | A1 | 1000237042 | 02.12.2027 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECR | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECR90022656
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Batteries | 2027-12-04 | 2027-12-04 | 5 hrs | FY28 | 9 | 90017122 | A1 | 1000337269 | 04.12.2027 | 12 Monthly | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST | 6200 | 10954 | 3519 | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST90017122
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Bucket LH | 2027-12-04 | 2027-12-05 | 26 hrs | FY28 | 32 | 90003169 | A1 | 1000207112 | 04.12.2027 | 10000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL | 6700 | 31524 | 10817 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL90003169
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 4500hr Valve Set | 2027-12-04 | 2027-12-04 | 10 hrs | FY28 | 20 | 90017923 | A1 | 1000207085 | 04.12.2027 | 4500 | CLB-MP-EXCV-EX7112-RHENGN | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-RHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Radiator LH Engine Cooling | 2027-12-06 | 2027-12-06 | 12 hrs | FY28 | 24 | 90022683 | A1 | 1000237122 | 06.12.2027 | 18000 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-RADTR | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-RADTR90022683
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Track Tension Tuning-Adjust | 2027-12-07 | 2027-12-07 | 3 hrs | FY28 | 9 | 90029977 | A1 | 1000359587 | 07.12.2027 | 6 Monthly | CLB-MP-EXCV-EX7149-UNDERC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-UNDERC90029977
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Fan Drive Eng Cooling Hose | 2027-12-08 | 2027-12-09 | 18 hrs | FY28 | 36 | 90022726 | A1 | 1000345665 | 08.12.2027 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDECH | 6700 | 25925 | 14626 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDECH90022726
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Inspection Ext Static Line | 2027-12-09 | 2027-12-09 | 4 hrs | FY28 | 4 | 90029897 | A1 | 1000357332 | 09.12.2027 | 6 Monthly | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl LH Aftercooler | 2027-12-10 | 2027-12-10 | 12 hrs | FY28 | 24 | 90023361 | A1 | 1000309246 | 10.12.2027 | 18000 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-AFTER | 6700 | 27054 | 8823 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-AFTER90023361
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Auto Lube Pump Superstructure | 2027-12-11 | 2027-12-11 | 12 hrs | FY28 | 12 | 90018988 | 1 | 1000190276 | 11.12.2027 | 6000 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP90018988
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Grease Control Valving | 2027-12-11 | 2027-12-12 | 18 hrs | FY28 | 18 | 90018990 | 1 | 1000190322 | 11.12.2027 | 12000 | CLB-MP-EXCV-EX014 -GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX014 -GRSYST-ALCON90018990
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cylinder Stick LH | 2027-12-11 | 2027-12-12 | 30 hrs | FY28 | 54 | 90003168 | A1 | 1000158838 | 11.12.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-STCLL | 6700 | 42775 | 2343 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-STCLL90003168
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cylinder Stick RH | 2027-12-11 | 2027-12-12 | 30 hrs | FY28 | 54 | 90003168 | A1 | 1000158839 | 11.12.2027 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-STCLR | 6700 | 42775 | 2343 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-STCLR90003168
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Wiper Blades | 2027-12-12 | 2027-12-12 | 1 hr | FY28 | 1 | 90027557 | A1 | 1000297393 | 12.12.2027 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7122-STRUCT-CABIN90027557
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Bucket RH | 2027-12-12 | 2027-12-13 | 26 hrs | FY28 | 32 | 90027499 | A1 | 1000284610 | 12.12.2027 | 10000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYR | 6700 | 19559 | 899 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYR90027499
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Minestar Harness | 2027-12-12 | 2027-12-13 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000369999 | 12.12.2027 | 4000 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Track Tensioning Hoses | 2027-12-13 | 2027-12-13 | 3 hrs | FY28 | 3 | 90022741 | A1 | 1000207148 | 13.12.2027 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-TRTNH | 6700 | 31524 | 2640 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-TRTNH90022741
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2027-12-15 | 2027-12-15 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359913 | 15.12.2027 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Auto Lube Pump P3 | 2027-12-24 | 2027-12-24 | 2 hrs | FY28 | 2 | 90035368 | A1 | 1000358745 | 24.12.2027 | 10000 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-ALBP3 | 6200 | 11740 | 1367 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-ALBP390035368
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Auto Lube Pump P1 | 2027-12-24 | 2027-12-24 | 2 hrs | FY28 | 2 | 90035369 | A1 | 1000330504 | 24.12.2027 | 10000 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-ALBPP | 6200 | 11792 | 1367 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-ALBPP90035369
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Bucket RH Lift | 2027-12-24 | 2027-12-25 | 30 hrs | FY28 | 54 | 90030726 | A1 | 1000330535 | 24.12.2027 | 10000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYR | 6200 | 11792 | 1367 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYR90030726
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Rotor & Logic Valve Hp Hoses | 2027-12-26 | 2027-12-27 | 18 hrs | FY28 | 36 | 90022734 | A1 | 1000237191 | 26.12.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-RCLVH | 6700 | 27054 | 1021 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-RCLVH90022734
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Servo Hoses Cascade to Bulkhead | 2027-12-26 | 2027-12-26 | 8 hrs | FY28 | 16 | 90022735 | A1 | 1000237192 | 26.12.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHBLK | 6700 | 27054 | 1021 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHBLK90022735
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Servo Hoses Cascade to Trvl Valve | 2027-12-26 | 2027-12-26 | 6 hrs | FY28 | 12 | 90022737 | A1 | 1000237194 | 26.12.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHTRV | 6700 | 27054 | 1021 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHTRV90022737
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Auto Lube Pump P3 | 2027-12-28 | 2027-12-28 | 2 hrs | FY28 | 2 | 90035368 | A1 | 1000358746 | 28.12.2027 | 10000 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-ALBP3 | 6200 | 10954 | 1170 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-ALBP390035368
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Auto Lube Pump P1 | 2027-12-28 | 2027-12-28 | 2 hrs | FY28 | 2 | 90035369 | A1 | 1000337244 | 28.12.2027 | 10000 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-ALBPP | 6200 | 10954 | 1170 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-ALBPP90035369
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Operators Seat | 2027-12-28 | 2027-12-28 | 9 hrs | FY28 | 17 | 90030739 | A1 | 1000337265 | 28.12.2027 | 10000 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-SEATO | 6200 | 10954 | 1170 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-SEATO90030739
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Batteries | 2027-12-28 | 2027-12-28 | 5 hrs | FY28 | 9 | 90017122 | A1 | 1000348540 | 28.12.2027 | 12 Monthly | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST | 6200 | 8353 | 3485 | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST90017122
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Servo Hose Bulkhead to MCV | 2027-12-28 | 2027-12-28 | 8 hrs | FY28 | 16 | 90022736 | A1 | 1000237193 | 28.12.2027 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHMCV | 6700 | 27054 | 8438 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHMCV90022736
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl RH Aftercooler | 2027-12-28 | 2027-12-28 | 12 hrs | FY28 | 24 | 90023360 | A1 | 1000309247 | 28.12.2027 | 18000 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-AFTER | 6700 | 27054 | 8438 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-AFTER90023360
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Hydraulic Oil Replacement | 2027-12-29 | 2027-12-29 | 12 hrs | FY28 | 12 | 90016793 | 1 | 1000284650 | 29.12.2027 | 6000 | CLB-MP-EXCV-EX7124-HYDSYS | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Hydraulic System Tune Up | 2027-12-29 | 2027-12-29 | 12 hrs | FY28 | 24 | 90017865 | 1 | 1000284660 | 29.12.2027 | 6000 | CLB-MP-EXCV-EX7124-HYDSYS | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Pump to Rotor Hoses | 2027-12-30 | 2027-12-31 | 24 hrs | FY28 | 48 | 90027567 | A1 | 1000284634 | 30.12.2027 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-MPRCH | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-MPRCH90027567
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Minestar Harness | 2027-12-30 | 2027-12-31 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000370303 | 30.12.2027 | 4000 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC90031708
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 PP Initial 500Hr Valve Set | 2027-12-30 | 2027-12-30 | 6 hrs | FY28 | 12 | 90031022 | A1 | 1000330529 | 30.12.2027 | 500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90031022
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Final Drive RH | 2027-12-31 | 2028-01-02 | 48 hrs | FY28 | 144 | 90003155 | A1 | 1000158818 | 31.12.2027 | 24000 | CLB-MP-EXCV-EX014 -TRAVEL-FDRRH | 6700 | 42775 | 13967 | CLB-MP-EXCV-EX014 -TRAVEL-FDRRH90003155
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Pump Drive Gearbox RH | 2027-12-31 | 2028-01-01 | 36 hrs | FY28 | 108 | 90022636 | A1 | 1000237145 | 31.12.2027 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-PPDRR | 6700 | 27054 | 8476 | CLB-MP-EXCV-EX7119-HYDSYS-PPDRR90022636
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Cyl Bucket LH Lift | 2028-01-02 | 2028-01-03 | 30 hrs | FY28 | 54 | 90030725 | A1 | 1000337273 | 02.01.2028 | 10000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BUCYL | 6200 | 10954 | 1170 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BUCYL90030725
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Cyl Bucket RH Lift | 2028-01-02 | 2028-01-03 | 30 hrs | FY28 | 54 | 90030726 | A1 | 1000337274 | 02.01.2028 | 10000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BUCYR | 6200 | 10954 | 1170 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BUCYR90030726
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 12M Inspection Isolator Panel | 2028-01-04 | 2028-01-04 | 2 hrs | FY28 | 2 | 90022525 | A2 | 1000315896 | 04.01.2028 | 12 Monthly | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | 6200 | 9369 | 1820 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST90022525
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Auto Lube Pump P3 | 2028-01-06 | 2028-01-06 | 2 hrs | FY28 | 2 | 90035368 | A1 | 1000358749 | 06.01.2028 | 10000 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-ALBP3 | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-ALBP390035368
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Auto Lube Pump P1 | 2028-01-06 | 2028-01-06 | 2 hrs | FY28 | 2 | 90035369 | A1 | 1000340268 | 06.01.2028 | 10000 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-ALBPP | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-ALBPP90035369
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Swing Circuit Hoses | 2028-01-06 | 2028-01-06 | 8 hrs | FY28 | 16 | 90022738 | A1 | 1000237064 | 06.01.2028 | 9000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT90022738
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Fan Hyd Cool Front | 2028-01-06 | 2028-01-06 | 6 hrs | FY28 | 12 | 90022655 | A1 | 1000237039 | 06.01.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMCHF | 6700 | 25972 | 8070 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMCHF90022655
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Replace PTO Cooling Hoses | 2028-01-07 | 2028-01-07 | 6 hrs | FY28 | 12 | 90022732 | A1 | 1000345672 | 07.01.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-PTOCL | 6700 | 25972 | 8070 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-PTOCL90022732
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Fan Engine Cool LH | 2028-01-07 | 2028-01-07 | 6 hrs | FY28 | 12 | 90022642 | A1 | 1000237021 | 07.01.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HECPL | 6700 | 25972 | 8070 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HECPL90022642
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Power Pack Module | 2028-01-10 | 2028-01-12 | 64 hrs | FY28 | 172 | 90026482 | A1 | 1000337266 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-ENGINE | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-ENGINE90026482
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Grease Block & Injectors | 2028-01-10 | 2028-01-12 | 48 hrs | FY28 | 84 | 90030749 | A1 | 1000337278 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ | 6200 | 10954 | 672 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ90030749
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Accumulator Track Hyd LH | 2028-01-10 | 2028-01-10 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000337240 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCL90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Accumulator Track Hyd RH | 2028-01-10 | 2028-01-10 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000337241 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCR90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Ladder Raise Cyl | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 24 | 90030750 | A1 | 1000337281 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-LACYL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-LACYL90030750
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Service Arm Locking Cyl | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 20 | 90030752 | A1 | 1000337309 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-SHCYL |  |  |  | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-SHCYL90030752
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Motor Swing Front | 2028-01-10 | 2028-01-11 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000337283 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-SWMOF | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-SWMOF90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Motor Swing Rear | 2028-01-10 | 2028-01-11 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000337284 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-SWMOR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-SWMOR90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Motor Travel LHF | 2028-01-10 | 2028-01-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000337261 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMLF | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMLF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Motor Travel LHR | 2028-01-10 | 2028-01-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000337262 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMLR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMLR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Motor Travel RHF | 2028-01-10 | 2028-01-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000337263 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMRF | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMRF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Motor Travel RHR | 2028-01-10 | 2028-01-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000337264 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMRR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMRR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Hyd Vlve Bank Module Quarter Life | 2028-01-10 | 2028-01-10 | 9 hrs | FY28 | 15 | 90027371 | A1 | 1000337257 | 10.01.2028 | 10000 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-MCVLU | 6200 | 10954 | 1170 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-MCVLU90027371
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Rotary Connection & Hoses | 2028-01-10 | 2028-01-14 | 96 hrs | FY28 | 168 | 90030430 | A1 | 1000337313 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-HYDSYS-ROTRY | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-ROTRY90030430
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Bucket | 2028-01-10 | 2028-01-12 | 42 hrs | FY28 | 78 | 90030745 | A1 | 1000337270 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-STRUCT-BUCKT | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BUCKT90030745
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Tank Module | 2028-01-10 | 2028-01-11 | 38 hrs | FY28 | 86 | 90027374 | A1 | 1000337255 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-STRUCT-HDTNK | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-HDTNK90027374
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Service Module Hosing | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 24 | 90030753 | A1 | 1000337308 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-STRUCT-SRVCT-SHHLF |  |  |  | CLB-MP-EXCV-EX7140-STRUCT-SRVCT-SHHLF90030753
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Gearbox Swing P1 | 2028-01-10 | 2028-01-12 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000337250 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-SWGSYS-SWBOX-SGBPF | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-SWGSYS-SWBOX-SGBPF90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Gearbox Swing P2 | 2028-01-10 | 2028-01-12 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000337251 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-SWGSYS-SWBOX-SGBPR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-SWGSYS-SWBOX-SGBPR90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Track Idler LH | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000337258 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-IDLLH | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-IDLLH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Sprocket LH | 2028-01-10 | 2028-01-11 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000337259 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-SPRKL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-SPRKL90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Track Hyd Tensioner LH | 2028-01-10 | 2028-01-11 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000337321 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-TENSL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Track Assembly LH | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000337318 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-TRKLH | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-TRKLH90030719
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Track Idler RH | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000337311 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-IDLRH | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-IDLRH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Sprocket RH | 2028-01-10 | 2028-01-11 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000337312 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-SPRKR | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-SPRKR90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Track Hyd Tensioner RH | 2028-01-10 | 2028-01-11 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000337322 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-TENSL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Track Assembly RH | 2028-01-10 | 2028-01-10 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000337319 | 10.01.2028 | 20000 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-TRKRH | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-TRKRH90030719
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cylinder Stick LH | 2028-01-11 | 2028-01-12 | 30 hrs | FY28 | 54 | 90027498 | A1 | 1000297344 | 11.01.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-STCLL | 6700 | 16452 | 2288 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-STCLL90027498
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Servo Hoses Cascade to Bulkhead | 2028-01-11 | 2028-01-11 | 8 hrs | FY28 | 16 | 90027572 | A1 | 1000297376 | 11.01.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHBLK | 6700 | 16452 | 2288 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHBLK90027572
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Control Valve Block LH | 2028-01-12 | 2028-01-13 | 34 hrs | FY28 | 50 | 90022653 | A1 | 1000237068 | 12.01.2028 | 36000 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-MCVVL | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-MCVVL90022653
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Control Valve Block RH | 2028-01-12 | 2028-01-13 | 34 hrs | FY28 | 50 | 90022653 | A1 | 1000237069 | 12.01.2028 | 36000 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-MCVVR | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-MCVVR90022653
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Boom Assy Dressed | 2028-01-12 | 2028-01-17 | 116 hrs | FY28 | 324 | 90003181 | A1 | 1000314262 | 12.01.2028 | 36000 | CLB-MP-EXCV-EX7118-STRUCT-BOOMS | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-BOOMS90003181
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Stick Assy Dressed | 2028-01-12 | 2028-01-16 | 99 hrs | FY28 | 291 | 90003183 | A1 | 1000314263 | 12.01.2028 | 36000 | CLB-MP-EXCV-EX7118-STRUCT-STICK | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-STICK90003183
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Slew Gear Bearing | 2028-01-12 | 2028-01-16 | 96 hrs | FY28 | 288 | 90022659 | A1 | 1000237047 | 12.01.2028 | 36000 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022659
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom Arch Hoses | 2028-01-13 | 2028-01-13 | 12 hrs | FY28 | 24 | 90027558 | A1 | 1000297365 | 13.01.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-BMARH | 6700 | 16452 | 2288 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-BMARH90027558
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cyl Boom RH | 2028-01-13 | 2028-01-17 | 90 hrs | FY28 | 138 | 90003167 | A1 | 1000207109 | 13.01.2028 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BMCYR | 6700 | 31524 | 8103 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BMCYR90003167
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Minestar Harness | 2028-01-15 | 2028-01-16 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000370300 | 15.01.2028 | 4000 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Boom Arch Hoses | 2028-01-16 | 2028-01-16 | 12 hrs | FY28 | 24 | 90022724 | A1 | 1000207131 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-BMARH | 6700 | 31524 | 2019 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-BMARH90022724
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Pump to Rotor Hoses | 2028-01-16 | 2028-01-17 | 24 hrs | FY28 | 48 | 90009473 | 1 | 1000207137 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-MPRCH | 6700 | 31524 | 2019 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-MPRCH90009473
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Servo Hoses Bulkhead to MCV | 2028-01-16 | 2028-01-16 | 8 hrs | FY28 | 16 | 90009479 | 1 | 1000207143 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHMCV | 6700 | 31524 | 2019 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHMCV90009479
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel LHR | 2028-01-16 | 2028-01-16 | 6 hrs | FY28 | 12 | 90022657 | A1 | 1000237044 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLR | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel RHF | 2028-01-16 | 2028-01-16 | 6 hrs | FY28 | 12 | 90022657 | A1 | 1000237045 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRF | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel RHR | 2028-01-16 | 2028-01-16 | 6 hrs | FY28 | 12 | 90022657 | A1 | 1000237046 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRR | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Pos1 & Pos2 | 2028-01-16 | 2028-01-17 | 26 hrs | FY28 | 42 | 90022641 | A1 | 1000237019 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP1P2 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP1P290022641
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Pos3 & Pos4 | 2028-01-16 | 2028-01-17 | 26 hrs | FY28 | 42 | 90022641 | A1 | 1000237020 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP3P4 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP3P490022641
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Replenish LH | 2028-01-16 | 2028-01-16 | 2 hrs | FY28 | 2 | 90022643 | A1 | 1000237025 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPL | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPL90022643
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Swing Replenish RH | 2028-01-16 | 2028-01-16 | 2 hrs | FY28 | 2 | 90022643 | A1 | 1000237026 | 16.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPR | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPR90022643
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos1 | 2028-01-18 | 2028-01-20 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237015 | 18.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP1 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP190022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos2 | 2028-01-18 | 2028-01-20 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237016 | 18.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP2 | 6700 | 25972 | 13898 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP290022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Servo Hoses Cascade to Trvl Valve | 2028-01-19 | 2028-01-19 | 6 hrs | FY28 | 12 | 90022737 | A1 | 1000345677 | 19.01.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHTRV | 6700 | 25948 | 13851 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHTRV90022737
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Case Drain Hoses | 2028-01-20 | 2028-01-20 | 8 hrs | FY28 | 16 | 90009472 | A2 | 1000207136 | 20.01.2028 | 15000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HPCDL | 6700 | 31524 | 4949 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HPCDL90009472
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Swing RHR | 2028-01-20 | 2028-01-21 | 21 hrs | FY28 | 27 | 90003175 | A1 | 1000207119 | 20.01.2028 | 15000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMRR | 6700 | 31524 | 4949 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMRR90003175
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cyl Boom RH | 2028-01-20 | 2028-01-24 | 90 hrs | FY28 | 138 | 90022644 | A1 | 1000237159 | 20.01.2028 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BMCYR | 6700 | 27054 | 8059 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BMCYR90022644
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Boom Stick Bucket Cyl Hoses | 2028-01-24 | 2028-01-27 | 88 hrs | FY28 | 136 | 90022725 | A1 | 1000237182 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HBSBC | 6700 | 27054 | 14228 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HBSBC90022725
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Hyd Pump Pos4 | 2028-01-24 | 2028-01-26 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237149 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP4 | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP490022637
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Swing Pos1 & Pos2 | 2028-01-24 | 2028-01-25 | 26 hrs | FY28 | 42 | 90022641 | A1 | 1000237150 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SP1P2 | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SP1P290022641
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Swing Pos3 & Pos4 | 2028-01-24 | 2028-01-25 | 26 hrs | FY28 | 42 | 90022641 | A1 | 1000237151 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SP3P4 | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SP3P490022641
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Swing Replenish LH | 2028-01-24 | 2028-01-24 | 2 hrs | FY28 | 2 | 90022643 | A1 | 1000237156 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SRPPL | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SRPPL90022643
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Swing Replenish RH | 2028-01-24 | 2028-01-24 | 2 hrs | FY28 | 2 | 90022643 | A1 | 1000237157 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SRPPR | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SRPPR90022643
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Pump Servo LH | 2028-01-24 | 2028-01-24 | 2 hrs | FY28 | 2 | 90022661 | A1 | 1000237154 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SVPPL | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SVPPL90022661
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Pump Servo RH | 2028-01-24 | 2028-01-24 | 2 hrs | FY28 | 2 | 90022661 | A1 | 1000237155 | 24.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SVPPR | 6700 | 27054 | 1985 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SVPPR90022661
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Hyd Pump Pos1 | 2028-01-27 | 2028-01-29 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237146 | 27.01.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP1 | 6700 | 27054 | 1162 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP190022637
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2028-01-29 | 2028-01-29 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359909 | 29.01.2028 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Rotor & Logic Valve Hp Hoses | 2028-01-29 | 2028-01-30 | 18 hrs | FY28 | 36 | 90009477 | 1 | 1000158872 | 29.01.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCLVH | 6700 | 42775 | 15680 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCLVH90009477
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Grease System Audit | 2028-01-30 | 2028-01-31 | 24 hrs | FY28 | 36 | 90029934 | A1 | 1000357444 | 30.01.2028 | 5000 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ90029934
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Fan Drive Hyd Cooling Hoses | 2028-01-31 | 2028-02-01 | 18 hrs | FY28 | 36 | 90009470 | A2 | 1000158865 | 31.01.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDHCH | 6700 | 42775 | 368 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDHCH90009470
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hydraulic Cooling Circ Hoses | 2028-01-31 | 2028-02-01 | 36 hrs | FY28 | 72 | 90009471 | A2 | 1000158866 | 31.01.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HCCHH | 6700 | 42775 | 368 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HCCHH90009471
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Track Tensioning Hoses | 2028-01-31 | 2028-01-31 | 3 hrs | FY28 | 3 | 90009484 | A2 | 1000158879 | 31.01.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TRTNH | 6700 | 42775 | 757 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TRTNH90009484
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 12M Hydraulic Service & Repairs | 2028-02-03 | 2028-02-04 | 18 hrs | FY28 | 30 | 90014448 | A1 | 1000336836 | 03.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7140-HYDSYS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Fan Engine Cool LH | 2028-02-04 | 2028-02-04 | 6 hrs | FY28 | 18 | 90003177 | A1 | 1000158850 | 04.02.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMECL | 6700 | 42775 | 7327 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMECL90003177
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Fan Engine Cool RH | 2028-02-04 | 2028-02-04 | 6 hrs | FY28 | 18 | 90003177 | A1 | 1000158851 | 04.02.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMECR | 6700 | 42775 | 7327 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMECR90003177
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Pump to Rotor Hoses | 2028-02-04 | 2028-02-05 | 24 hrs | FY28 | 48 | 90022730 | A1 | 1000237187 | 04.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-MPRCH | 6700 | 27054 | 180 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-MPRCH90022730
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141Repl Auto Lube Pump P3 | 2028-02-05 | 2028-02-05 | 2 hrs | FY28 | 2 | 90035368 | A1 | 1000358747 | 05.02.2028 | 10000 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBP3 | 6200 | 8353 | 498 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBP390035368
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl 24V Batteries | 2028-02-07 | 2028-02-07 | 5 hrs | FY28 | 9 | 90029978 | A1 | 1000304630 | 07.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST | 6200 | 13908 | 8694 | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST90029978
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Radiator RH Engine Cooling | 2028-02-07 | 2028-02-07 | 12 hrs | FY28 | 24 | 90022684 | A1 | 1000237137 | 07.02.2028 | 18000 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-RADTR | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-RADTR90022684
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel LHF | 2028-02-08 | 2028-02-08 | 6 hrs | FY28 | 12 | 90003178 | A1 | 1000158852 | 08.02.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLF | 6700 | 42775 | 1209 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLF90003178
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Boom Stick Bucket Cyl Hoses | 2028-02-09 | 2028-02-12 | 88 hrs | FY28 | 136 | 90009468 | 1 | 1000207132 | 09.02.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HBSBC | 6700 | 31524 | 415 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HBSBC90009468
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Hydraulic Oil Replacement | 2028-02-09 | 2028-02-09 | 12 hrs | FY28 | 12 | 90022667 | A1 | 1000237203 | 09.02.2028 | 6000 | CLB-MP-EXCV-EX7119-HYDSYS | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS90022667
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Hydraulic System Tune Up | 2028-02-09 | 2028-02-09 | 12 hrs | FY28 | 24 | 90022669 | A1 | 1000237214 | 09.02.2028 | 6000 | CLB-MP-EXCV-EX7119-HYDSYS | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS90022669
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Power Pack Module | 2028-02-10 | 2028-02-12 | 64 hrs | FY28 | 172 | 90030914 | A1 | 1000340288 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90030914
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Grease Block & Injectors | 2028-02-10 | 2028-02-12 | 48 hrs | FY28 | 84 | 90030749 | A1 | 1000340301 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ90030749
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Accumulator Track Hyd LH | 2028-02-10 | 2028-02-10 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000340264 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCL90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Accumulator Track Hyd RH | 2028-02-10 | 2028-02-10 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000340265 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCR90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Bucket RH Lift | 2028-02-10 | 2028-02-11 | 30 hrs | FY28 | 54 | 90030726 | A1 | 1000340297 | 10.02.2028 | 10000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYR90030726
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Ladder Raise Cyl | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 24 | 90030750 | A1 | 1000340304 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-LACYL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-LACYL90030750
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Service Arm Locking Cyl | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 20 | 90030752 | A1 | 1000340332 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-SHCYL |  |  |  | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-SHCYL90030752
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Motor Swing Front | 2028-02-10 | 2028-02-11 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000340306 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-SWMOF | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-SWMOF90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Motor Swing Rear | 2028-02-10 | 2028-02-11 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000340307 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-SWMOR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-SWMOR90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Motor Travel LHF | 2028-02-10 | 2028-02-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000340283 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMLF | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMLF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Motor Travel LHR | 2028-02-10 | 2028-02-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000340284 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMLR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMLR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Motor Travel RHF | 2028-02-10 | 2028-02-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000340285 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMRF | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMRF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Motor Travel RHR | 2028-02-10 | 2028-02-10 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000340286 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMRR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMRR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Hyd Vlve Bank Module Quarter Life | 2028-02-10 | 2028-02-10 | 9 hrs | FY28 | 15 | 90027371 | A1 | 1000340280 | 10.02.2028 | 10000 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-MCVLU | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-MCVLU90027371
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Rotary Connection & Hoses | 2028-02-10 | 2028-02-14 | 96 hrs | FY28 | 168 | 90030430 | A1 | 1000340334 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-HYDSYS-ROTRY | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS-ROTRY90030430
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Bucket | 2028-02-10 | 2028-02-12 | 42 hrs | FY28 | 78 | 90030745 | A1 | 1000340293 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-STRUCT-BUCKT | 6200 | 9369 | 0 | CLB-MP-EXCV-EX7138-STRUCT-BUCKT90030745
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Tank Module | 2028-02-10 | 2028-02-11 | 38 hrs | FY28 | 86 | 90036464 | A1 | 1000340278 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-STRUCT-HDTNK | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT-HDTNK90036464
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Service Module Hosing | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 24 | 90030753 | A1 | 1000340331 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-STRUCT-SRVCT-SHHLF |  |  |  | CLB-MP-EXCV-EX7138-STRUCT-SRVCT-SHHLF90030753
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Gearbox Swing P1 | 2028-02-10 | 2028-02-12 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000340273 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-SWGSYS-SWBOX-SGBPF | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-SWGSYS-SWBOX-SGBPF90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Gearbox Swing P2 | 2028-02-10 | 2028-02-12 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000340274 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-SWGSYS-SWBOX-SGBPR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-SWGSYS-SWBOX-SGBPR90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Track Idler LH | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000340281 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-IDLLH | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-IDLLH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Sprocket LH | 2028-02-10 | 2028-02-11 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000340338 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-SPRKL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-SPRKL90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Track Hyd Tensioner LH | 2028-02-10 | 2028-02-11 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000340344 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-TENSL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Track Assembly LH | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000340341 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-TRKLH | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-TRKLH90030719
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Track Idler RH | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000340282 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-IDLRH | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-IDLRH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Sprocket RH | 2028-02-10 | 2028-02-11 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000340339 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-SPRKR | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-SPRKR90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Track Hyd Tensioner RH | 2028-02-10 | 2028-02-11 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000340345 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-TENSL | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Track Assembly RH | 2028-02-10 | 2028-02-10 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000340342 | 10.02.2028 | 20000 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-TRKRH | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-TRKRH90030719
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2028-02-10 | 2028-02-10 | 4 hrs | FY28 | 4 | 90022746 | A1 | 1000237081 | 10.02.2028 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Batteries | 2028-02-13 | 2028-02-13 | 5 hrs | FY28 | 9 | 90017122 | A1 | 1000340292 | 13.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | 6200 | 9369 | 1820 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST90017122
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2028-02-14 | 2028-02-14 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359910 | 14.02.2028 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel LHR | 2028-02-15 | 2028-02-15 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000284622 | 15.02.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLR | 6700 | 19559 | 1670 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLR90027506
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Operators Seat | 2028-02-16 | 2028-02-16 | 2 hrs | FY28 | 2 | 90027613 | A1 | 1000284626 | 16.02.2028 | 10000 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-SEATS | 6700 | 19559 | 9696 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-SEATS90027613
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 6M Anritsu Test WiFi Cables | 2028-02-16 | 2028-02-16 | 2 hrs | FY28 | 2 | 90020303 | A1 | 1000210997 | 16.02.2028 | 6 Monthly | CLB-MP-EXCV-EX7112-COMMUN-FLMGT |  |  |  | CLB-MP-EXCV-EX7112-COMMUN-FLMGT90020303
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Travel LHF | 2028-02-17 | 2028-02-17 | 6 hrs | FY28 | 12 | 90022657 | A1 | 1000237043 | 17.02.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLF | 6700 | 25972 | 13317 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Stick LH | 2028-02-18 | 2028-02-19 | 30 hrs | FY28 | 54 | 90022646 | A1 | 1000237160 | 18.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLL | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLL90022646
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Rotor to Drive Motor Hoses | 2028-02-18 | 2028-02-18 | 10 hrs | FY28 | 20 | 90022733 | A1 | 1000237190 | 18.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-RCDMH | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-RCDMH90022733
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 2nd Speed Trvl Brake Release Hose | 2028-02-18 | 2028-02-18 | 5 hrs | FY28 | 10 | 90022723 | A1 | 1000237180 | 18.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SSTBR | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SSTBR90022723
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Swing Motor Case Drain Hoses | 2028-02-18 | 2028-02-18 | 6 hrs | FY28 | 12 | 90022739 | A1 | 1000237196 | 18.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWMCD | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Travel Motor Case Drain Hoses | 2028-02-18 | 2028-02-18 | 5 hrs | FY28 | 10 | 90022740 | A1 | 1000237197 | 18.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-TMCDH | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-TMCDH90022740
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Track Tensioning Hoses | 2028-02-18 | 2028-02-18 | 3 hrs | FY28 | 3 | 90022741 | A1 | 1000237198 | 18.02.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-TRTNH | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-TRTNH90022741
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Fan Drive Hyd Cooling Hoses | 2028-02-19 | 2028-02-20 | 18 hrs | FY28 | 36 | 90027565 | A1 | 1000297368 | 19.02.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDHCH | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDHCH90027565
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hydraulic Cooling Circ Hoses | 2028-02-19 | 2028-02-20 | 18 hrs | FY28 | 36 | 90031704 | A1 | 1000297369 | 19.02.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HCCHH | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HCCHH90031704
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Rotor & Logic Valve Hp Hoses | 2028-02-19 | 2028-02-20 | 18 hrs | FY28 | 36 | 90027571 | A1 | 1000297375 | 19.02.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-RCLVH | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-RCLVH90027571
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos3 | 2028-02-19 | 2028-02-21 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237017 | 19.02.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP3 | 6700 | 25972 | 13291 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP390022637
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Minestar Harness | 2028-02-19 | 2028-02-20 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000370301 | 19.02.2028 | 4000 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Bucket RH | 2028-02-22 | 2028-02-23 | 26 hrs | FY28 | 32 | 90022647 | A1 | 1000237032 | 22.02.2028 | 10000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYR | 6700 | 25972 | 9228 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYR90022647
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Grease System Audit | 2028-02-24 | 2028-02-25 | 24 hrs | FY28 | 36 | 90029934 | A1 | 1000359549 | 24.02.2028 | 5000 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ90029934
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Hydraulic System Tune Up | 2028-02-24 | 2028-02-24 | 12 hrs | FY28 | 24 | 90022669 | A1 | 1000237083 | 24.02.2028 | 6000 | CLB-MP-EXCV-EX7118-HYDSYS | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS90022669
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Engine Cat C32 | 2028-02-24 | 2028-03-02 | 174.5 hrs | FY28 | 252.5 | 90022670 | A1 | 1000236958 | 24.02.2028 | 18000 | CLB-MP-EXCV-EX7118-LHENGN | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-LHENGN90022670
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Radiator RH Engine Cooling | 2028-02-24 | 2028-02-24 | 12 hrs | FY28 | 24 | 90022684 | A1 | 1000237006 | 24.02.2028 | 18000 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-RADTR | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-RADTR90022684
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl RH Aftercooler | 2028-02-24 | 2028-02-24 | 12 hrs | FY28 | 24 | 90023360 | A1 | 1000309245 | 24.02.2028 | 18000 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-AFTER | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-AFTER90023360
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Wiper Blades | 2028-02-24 | 2028-02-24 | 2 hrs | FY28 | 2 | 90022722 | A1 | 1000237209 | 24.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7119-STRUCT-CABIN90022722
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Engine Midlife Complete LH | 2028-02-26 | 2028-02-28 | 56 hrs | FY28 | 66 | 90027554 | A1 | 1000297276 | 26.02.2028 | 9000 | CLB-MP-EXCV-EX7122-LHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN90027554
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Engine Midlife Complete RH | 2028-02-26 | 2028-02-28 | 56 hrs | FY28 | 66 | 90027554 | A1 | 1000297321 | 26.02.2028 | 9000 | CLB-MP-EXCV-EX7122-RHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN90027554
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Minestar Harness | 2028-02-27 | 2028-02-28 | 27.5 hrs | FY28 | 43.5 | 90030746 | A1 | 1000330543 | 27.02.2028 | 5000 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC | 6200 | 11792 | 5210 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC90030746
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 12M Hydraulic Service & Repairs | 2028-02-28 | 2028-02-29 | 18 hrs | FY28 | 30 | 90014448 | A1 | 1000340261 | 28.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7138-HYDSYS | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service RH | 2028-02-28 | 2028-02-28 | 12 hrs | FY28 | 12 | 90022660 | A1 | 1000237077 | 28.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR | 6700 | 25972 | 6562 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR90022660
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Wiper Blades | 2028-02-29 | 2028-02-29 | 2 hrs | FY28 | 2 | 90022722 | A1 | 1000237078 | 29.02.2028 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7118-STRUCT-CABIN90022722
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Annual Air Con Service LH | 2028-03-01 | 2028-03-01 | 12 hrs | FY28 | 12 | 90027615 | A1 | 1000297422 | 01.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL90027615
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Annual Air Con Service RH | 2028-03-01 | 2028-03-01 | 12 hrs | FY28 | 12 | 90027615 | A1 | 1000297392 | 01.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR90027615
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Boom Arch Hoses | 2028-03-01 | 2028-03-01 | 12 hrs | FY28 | 24 | 90027558 | A1 | 1000284628 | 01.03.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-BMARH | 6700 | 19559 | 1440 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-BMARH90027558
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Servo Hose Bulkhead to MCV | 2028-03-01 | 2028-03-01 | 8 hrs | FY28 | 16 | 90027574 | A1 | 1000284640 | 01.03.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHMCV | 6700 | 19559 | 1440 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHMCV90027574
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Svc 12M Air Conditioner Sys1 Eng | 2028-03-01 | 2028-03-01 | 12 hrs | FY28 | 12 | 90035241 | A1 | 1000359801 | 01.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC1 | 6500 | 1175 | 1175 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC190035241
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Svc 12M Air Conditioner Sys2 Hyd | 2028-03-01 | 2028-03-01 | 12 hrs | FY28 | 12 | 90035242 | A1 | 1000359803 | 01.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC290035242
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Engine Cat C32 RH | 2028-03-05 | 2028-03-12 | 168 hrs | FY28 | 250 | 90017914 | A1 | 1000158801 | 05.03.2028 | 18000 | CLB-MP-EXCV-EX014 -RHENGN | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -RHENGN90017914
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Track Tension Accum LH | 2028-03-08 | 2028-03-08 | 2 hrs | FY28 | 2 | 90002539 | A1 | 1000324230 | 08.03.2028 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC90002539
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Track Tension Accum RH | 2028-03-08 | 2028-03-08 | 2 hrs | FY28 | 2 | 90002539 | A2 | 1000324841 | 08.03.2028 | 18000 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC90002539
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 PP Initial 500Hr Valve Set | 2028-03-09 | 2028-03-09 | 6 hrs | FY28 | 12 | 90031022 | A1 | 1000340291 | 09.03.2028 | 500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90031022
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2028-03-09 | 2028-03-09 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359913 | 09.03.2028 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 12M Inspection Isolator Panel | 2028-03-09 | 2028-03-09 | 2 hrs | FY28 | 2 | 90022525 | A2 | 1000348387 | 09.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7141-ELCTLV |  |  |  | CLB-MP-EXCV-EX7141-ELCTLV90022525
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Operators Seat | 2028-03-10 | 2028-03-10 | 2 hrs | FY28 | 2 | 90022750 | A1 | 1000237048 | 10.03.2028 | 10000 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-SEATS | 6700 | 25972 | 8861 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-SEATS90022750
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Boom LH | 2028-03-11 | 2028-03-13 | 42 hrs | FY28 | 78 | 90029951 | A1 | 1000357470 | 11.03.2028 | 16000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BMCYL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BMCYL90029951
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Boom RH | 2028-03-11 | 2028-03-13 | 42 hrs | FY28 | 78 | 90029951 | A1 | 1000357471 | 11.03.2028 | 16000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BMCYR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BMCYR90029951
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Stick LH | 2028-03-11 | 2028-03-12 | 30 hrs | FY28 | 54 | 90029971 | A1 | 1000357472 | 11.03.2028 | 16000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-STCLL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-STCLL90029971
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Stick RH | 2028-03-11 | 2028-03-12 | 30 hrs | FY28 | 54 | 90029971 | A1 | 1000357473 | 11.03.2028 | 16000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-STCLR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-STCLR90029971
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Boom Cyl | 2028-03-11 | 2028-03-11 | 8 hrs | FY28 | 24 | 90029908 | A1 | 1000357426 | 11.03.2028 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Stick Cyl | 2028-03-11 | 2028-03-11 | 12 hrs | FY28 | 24 | 90029909 | A1 | 1000357427 | 11.03.2028 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Bucket Cyl | 2028-03-11 | 2028-03-12 | 18 hrs | FY28 | 54 | 90029911 | A1 | 1000357428 | 11.03.2028 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL90029911
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Sprocket LH | 2028-03-16 | 2028-03-16 | 12 hrs | FY28 | 24 | 90022635 | A1 | 1000237097 | 16.03.2028 | 1500 | CLB-MP-EXCV-EX7118-TRAVEL-SPRKL | 470 | 1775 | 30 | CLB-MP-EXCV-EX7118-TRAVEL-SPRKL90022635
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Sprocket RH | 2028-03-16 | 2028-03-16 | 12 hrs | FY28 | 24 | 90022635 | A1 | 1000237108 | 16.03.2028 | 1500 | CLB-MP-EXCV-EX7118-TRAVEL-SPRKR | 470 | 1775 | 30 | CLB-MP-EXCV-EX7118-TRAVEL-SPRKR90022635
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Batteries | 2028-03-17 | 2028-03-17 | 5 hrs | FY28 | 9 | 90017122 | A1 | 1000330530 | 17.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST | 6200 | 11792 | 2453 | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST90017122
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Rotor to Drive Motor Hoses | 2028-03-17 | 2028-03-17 | 10 hrs | FY28 | 20 | 90022733 | A1 | 1000345673 | 17.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCDMH | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCDMH90022733
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Rotor & Logic Valve Hp Hoses | 2028-03-17 | 2028-03-18 | 18 hrs | FY28 | 36 | 90022734 | A1 | 1000345674 | 17.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCLVH | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCLVH90022734
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 2nd Speed Trvl Brake Release Hose | 2028-03-17 | 2028-03-17 | 5 hrs | FY28 | 10 | 90022723 | A1 | 1000345662 | 17.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SSTBR | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SSTBR90022723
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Swing Motor Case Drain Hoses | 2028-03-17 | 2028-03-17 | 6 hrs | FY28 | 12 | 90022739 | A1 | 1000237065 | 17.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWMCD | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Rep Travel Motor Case Drain Hoses | 2028-03-17 | 2028-03-17 | 5 hrs | FY28 | 10 | 90022740 | A1 | 1000237066 | 17.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TMCDH | 6700 | 25972 | 12789 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TMCDH90022740
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Pump Servo RH | 2028-03-17 | 2028-03-17 | 2 hrs | FY28 | 2 | 90022661 | A1 | 1000237024 | 17.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPR | 6700 | 25972 | 12762 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPR90022661
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Servo Hoses Cascade to Bulkhead | 2028-03-18 | 2028-03-18 | 8 hrs | FY28 | 16 | 90022735 | A1 | 1000345675 | 18.03.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHBLK | 6700 | 25972 | 12762 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHBLK90022735
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Case Drain Hoses | 2028-03-19 | 2028-03-19 | 8 hrs | FY28 | 16 | 90027566 | A1 | 1000284633 | 19.03.2028 | 15000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HPCDL | 6700 | 19559 | 4086 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HPCDL90027566
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Swing RHF | 2028-03-19 | 2028-03-20 | 21 hrs | FY28 | 27 | 90027503 | A1 | 1000284615 | 19.03.2028 | 15000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMRF | 6700 | 19559 | 4086 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMRF90027503
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Swing RHR | 2028-03-19 | 2028-03-20 | 21 hrs | FY28 | 27 | 90027503 | A1 | 1000284616 | 19.03.2028 | 15000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMRR | 6700 | 19559 | 4086 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMRR90027503
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Track Tension Tuning-Adjust | 2028-03-19 | 2028-03-19 | 3 hrs | FY28 | 9 | 90029977 | A1 | 1000357482 | 19.03.2028 | 6 Monthly | CLB-MP-EXCV-EX7148-UNDERC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-UNDERC90029977
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cyl Boom LH | 2028-03-19 | 2028-03-23 | 90 hrs | FY28 | 138 | 90022644 | A1 | 1000237158 | 19.03.2028 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BMCYL | 6700 | 27054 | 6979 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BMCYL90022644
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cylinder Stick RH | 2028-03-22 | 2028-03-23 | 30 hrs | FY28 | 54 | 90027498 | A1 | 1000297345 | 22.03.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-STCLR | 6700 | 16452 | 976 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-STCLR90027498
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Grease Tank Level Valve | 2028-03-22 | 2028-03-22 | 2 hrs | FY28 | 2 | 90015003 | A1 | 1000348551 | 22.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Track Tension Tuning-Adjust | 2028-03-22 | 2028-03-22 | 3 hrs | FY28 | 9 | 90020545 | A1 | 1000348591 | 22.03.2028 | 6 Monthly | CLB-MP-EXCV-EX7141-UNDERC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Engine Midlife Complete RH | 2028-03-22 | 2028-03-24 | 54 hrs | FY28 | 76 | 90022685 | A1 | 1000237136 | 22.03.2028 | 9000 | CLB-MP-EXCV-EX7119-RHENGN | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-RHENGN90022685
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Adjust 500hr Initial Valve Set | 2028-03-23 | 2028-03-23 | 10 hrs | FY28 | 20 | 90022680 | A1 | 1000236988 | 23.03.2028 | 500 | CLB-MP-EXCV-EX7118-LHENGN | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-LHENGN90022680
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Minestar Harness | 2028-03-25 | 2028-03-26 | 27.5 hrs | FY28 | 43.5 | 90030746 | A1 | 1000340305 | 25.03.2028 | 5000 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC90030746
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Track Tension Cyl LH | 2028-03-25 | 2028-03-25 | 12 hrs | FY28 | 24 | 90016983 | 1 | 1000158892 | 25.03.2028 | 18000 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-TENSR | 6700 | 42775 | 6421 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-TENSR90016983
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Track Tension Cyl RH | 2028-03-25 | 2028-03-25 | 12 hrs | FY28 | 24 | 90016983 | 1 | 1000158893 | 25.03.2028 | 18000 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-TENSR | 6700 | 42775 | 6421 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-TENSR90016983
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2028-03-27 | 2028-03-27 | 4 hrs | FY28 | 4 | 90022746 | A1 | 1000237212 | 27.03.2028 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Adjust Track Tension Tuning | 2028-03-29 | 2028-03-29 | 3 hrs | FY28 | 9 | 90029977 | A1 | 1000304629 | 29.03.2028 | 6 Monthly | CLB-MP-EXCV-EX7133-UNDERC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC90029977
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Hydraulic Service & Repairs | 2028-03-29 | 2028-03-30 | 18 hrs | FY28 | 30 | 90029940 | A1 | 1000304680 | 29.03.2028 | 12 Monthly | CLB-MP-EXCV-EX7133-HYDSYS |  |  |  | CLB-MP-EXCV-EX7133-HYDSYS90029940
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Pump Drive Gearbox RH | 2028-03-29 | 2028-03-30 | 36 hrs | FY28 | 108 | 90022636 | A1 | 1000237014 | 29.03.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-PPDRR | 6700 | 25972 | 6562 | CLB-MP-EXCV-EX7118-HYDSYS-PPDRR90022636
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Track Tensioner RH | 2028-03-29 | 2028-03-29 | 12 hrs | FY28 | 24 | 90022668 | A1 | 1000237075 | 29.03.2028 | 18000 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-TENSR | 6700 | 25972 | 403 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-TENSR90022668
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Bucket LH | 2028-03-30 | 2028-03-31 | 26 hrs | FY28 | 32 | 90027499 | A1 | 1000284609 | 30.03.2028 | 10000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYL | 6700 | 19559 | 8904 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYL90027499
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Minestar Harness | 2028-03-30 | 2028-03-31 | 27.5 hrs | FY28 | 43.5 | 90030746 | A1 | 1000337282 | 30.03.2028 | 5000 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC90030746
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Idler Track LH | 2028-03-30 | 2028-03-30 | 6 hrs | FY28 | 18 | 90022658 | A1 | 1000237220 | 30.03.2028 | 1500 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-IDLLH | 470 | 2901 | 1807 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-IDLLH90022658
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Idler Track RH | 2028-03-30 | 2028-03-30 | 6 hrs | FY28 | 18 | 90022658 | A1 | 1000237231 | 30.03.2028 | 1500 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-IDLRH | 470 | 2901 | 1807 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-IDLRH90022658
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Sprocket LH | 2028-03-30 | 2028-03-30 | 12 hrs | FY28 | 24 | 90022635 | A1 | 1000237228 | 30.03.2028 | 1500 | CLB-MP-EXCV-EX7119-TRAVEL-SPRKL | 470 | 2901 | 1807 | CLB-MP-EXCV-EX7119-TRAVEL-SPRKL90022635
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Sprocket RH | 2028-03-30 | 2028-03-30 | 12 hrs | FY28 | 24 | 90022635 | A1 | 1000237239 | 30.03.2028 | 1500 | CLB-MP-EXCV-EX7119-TRAVEL-SPRKR | 470 | 2901 | 1807 | CLB-MP-EXCV-EX7119-TRAVEL-SPRKR90022635
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Stick RH | 2028-04-01 | 2028-04-02 | 30 hrs | FY28 | 54 | 90022646 | A1 | 1000237030 | 01.04.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLR | 6700 | 25972 | 12481 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLR90022646
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Adjust 500hr Initial Valve Set | 2028-04-02 | 2028-04-02 | 10 hrs | FY28 | 20 | 90017925 | A1 | 1000158811 | 02.04.2028 | 500 | CLB-MP-EXCV-EX014 -RHENGN | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -RHENGN90017925
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Pump Drive Gearbox LH | 2028-04-06 | 2028-04-07 | 36 hrs | FY28 | 108 | 90022636 | A1 | 1000237013 | 06.04.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-PPDRL | 6700 | 25972 | 6562 | CLB-MP-EXCV-EX7118-HYDSYS-PPDRL90022636
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Hose Stick Cyl | 2028-04-14 | 2028-04-14 | 12 hrs | FY28 | 24 | 90030737 | A1 | 1000340277 | 14.04.2028 | 8000 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HSTCL | 6200 | 9369 | 4227 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HSTCL90030737
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Minestar Harness | 2028-04-14 | 2028-04-15 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000312852 | 14.04.2028 | 4000 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Fan Drive Hyd Cooling Hoses | 2028-04-14 | 2028-04-15 | 18 hrs | FY28 | 36 | 90009470 | A2 | 1000207134 | 14.04.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDHCH | 6700 | 31524 | 415 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDHCH90009470
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Hyd Pump Pos2 | 2028-04-14 | 2028-04-16 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237147 | 14.04.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP2 | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP290022637
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Minestar Harness | 2028-04-16 | 2028-04-17 | 27.5 hrs | FY28 | 43.5 | 90029998 | A1 | 1000357494 | 16.04.2028 | 4000 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC90029998
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Grease System Audit | 2028-04-19 | 2028-04-20 | 24 hrs | FY28 | 36 | 90029934 | A1 | 1000304595 | 19.04.2028 | 5000 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ90029934
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Minestar Harness | 2028-04-20 | 2028-04-21 | 24.5 hrs | FY28 | 40.5 | 90031708 | A1 | 1000370302 | 20.04.2028 | 4000 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Wiper Blades | 2028-04-23 | 2028-04-23 | 1 hr | FY28 | 1 | 90027557 | A1 | 1000284656 | 23.04.2028 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7124-STRUCT-CABIN90027557
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Boom LH | 2028-04-23 | 2028-04-25 | 42 hrs | FY28 | 78 | 90029951 | A1 | 1000359575 | 23.04.2028 | 16000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BMCYL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BMCYL90029951
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Boom RH | 2028-04-23 | 2028-04-25 | 42 hrs | FY28 | 78 | 90029951 | A1 | 1000359576 | 23.04.2028 | 16000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BMCYR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BMCYR90029951
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Stick RH | 2028-04-23 | 2028-04-24 | 30 hrs | FY28 | 54 | 90029971 | A1 | 1000359578 | 23.04.2028 | 16000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-STCLR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-STCLR90029971
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Hose Boom Cyl | 2028-04-23 | 2028-04-23 | 8 hrs | FY28 | 24 | 90029908 | A1 | 1000359531 | 23.04.2028 | 8000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Hose Stick Cyl | 2028-04-23 | 2028-04-23 | 12 hrs | FY28 | 24 | 90029909 | A1 | 1000359532 | 23.04.2028 | 8000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSTCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Hose Bucket Cyl | 2028-04-23 | 2028-04-24 | 18 hrs | FY28 | 54 | 90029911 | A1 | 1000359533 | 23.04.2028 | 8000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBKCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBKCL90029911
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Minestar Harness | 2028-04-23 | 2028-04-24 | 27.5 hrs | FY28 | 43.5 | 90029998 | A1 | 1000359599 | 23.04.2028 | 4000 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC90029998
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Adjust Track Tension Tuning | 2028-04-23 | 2028-04-23 | 3 hrs | FY28 | 9 | 90020545 | A1 | 1000337320 | 23.04.2028 | 6 Monthly | CLB-MP-EXCV-EX7140-UNDERC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Annual Air Con Service LH | 2028-04-24 | 2028-04-24 | 12 hrs | FY28 | 12 | 90027615 | A1 | 1000284685 | 24.04.2028 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL90027615
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Annual Air Con Service RH | 2028-04-24 | 2028-04-24 | 12 hrs | FY28 | 12 | 90027615 | A1 | 1000284655 | 24.04.2028 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR90027615
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2028-04-26 | 2028-04-26 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359909 | 26.04.2028 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Annual Air Con Service RH | 2028-04-27 | 2028-04-27 | 12 hrs | FY28 | 12 | 90004141 | 2 | 1000266975 | 27.04.2028 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR90004141
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 12M Hydraulic Service & Repairs | 2028-04-30 | 2028-05-01 | 18 hrs | FY28 | 30 | 90014448 | A1 | 1000348386 | 30.04.2028 | 12 Monthly | CLB-MP-EXCV-EX7141-HYDSYS | 6200 | 8353 | 1263 | CLB-MP-EXCV-EX7141-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Annual Air Con Service RH | 2028-05-01 | 2028-05-01 | 12 hrs | FY28 | 12 | 90004141 | 2 | 1000211117 | 01.05.2028 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR90004141
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Annual Air Con Service LH | 2028-05-02 | 2028-05-02 | 12 hrs | FY28 | 12 | 90004141 | 2 | 1000163161 | 02.05.2028 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL | 6700 | 19252 | 8084 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL90004141
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Static Line Inspection | 2028-05-03 | 2028-05-03 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000340340 | 03.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7138-STRUCT | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT90014347
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Travel LHR | 2028-05-03 | 2028-05-03 | 8 hrs | FY28 | 14 | 90027506 | A1 | 1000297359 | 03.05.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLR | 6700 | 16452 | 139 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLR90027506
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Boom Arch Hoses | 2028-05-03 | 2028-05-03 | 12 hrs | FY28 | 24 | 90022724 | A1 | 1000345663 | 03.05.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-BMARH | 6700 | 25972 | 11914 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-BMARH90022724
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Hyd Pump Pos4 | 2028-05-03 | 2028-05-05 | 42 hrs | FY28 | 54 | 90022637 | A1 | 1000237018 | 03.05.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP4 | 6700 | 25972 | 11914 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP490022637
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Minestar Harness | 2028-05-04 | 2028-05-05 | 27.5 hrs | FY28 | 43.5 | 90029998 | A1 | 1000304641 | 04.05.2028 | 4000 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC90029998
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Boom Module Quarter Life | 2028-05-07 | 2028-05-08 | 30 hrs | FY28 | 48 | 90027377 | A1 | 1000348396 | 07.05.2028 | 10000 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90027377
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Auto Lube Pump P3 | 2028-05-10 | 2028-05-10 | 2 hrs | FY28 | 2 | 90035351 | A1 | 1000358624 | 10.05.2028 | 10000 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBP3 | 6200 | 13908 | 9063 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBP390035351
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service LH | 2028-05-11 | 2028-05-11 | 12 hrs | FY28 | 12 | 90022660 | A1 | 1000242609 | 11.05.2028 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL | 6700 | 17550 | 5056 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL90022660
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Swing Circuit Hoses | 2028-05-11 | 2028-05-11 | 8 hrs | FY28 | 16 | 90022738 | A1 | 1000237195 | 11.05.2028 | 9000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWCRT | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWCRT90022738
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Hose Bucket Cyl | 2028-05-12 | 2028-05-13 | 18 hrs | FY28 | 54 | 90030738 | A1 | 1000340276 | 12.05.2028 | 8000 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBKCL | 6200 | 9369 | 3729 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Hyd Hose Boom Cyl | 2028-05-12 | 2028-05-12 | 8 hrs | FY28 | 24 | 90030735 | A1 | 1000340275 | 12.05.2028 | 8000 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBMCL | 6200 | 9369 | 3729 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2028-05-12 | 2028-05-12 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359910 | 12.05.2028 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Fan Drive Eng Cooling Hose | 2028-05-12 | 2028-05-13 | 18 hrs | FY28 | 36 | 90009469 | A2 | 1000207133 | 12.05.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDECH | 6700 | 31524 | 11872 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDECH90009469
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hydraulic Cooling Circ Hoses | 2028-05-12 | 2028-05-13 | 36 hrs | FY28 | 72 | 90009471 | A2 | 1000207135 | 12.05.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HCCHH | 6700 | 31524 | 11872 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HCCHH90009471
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Inspection Ext Static Line | 2028-05-13 | 2028-05-13 | 4 hrs | FY28 | 4 | 90029897 | A1 | 1000304563 | 13.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl PTO Cooling Hoses | 2028-05-14 | 2028-05-14 | 6 hrs | FY28 | 12 | 90009475 | A2 | 1000158870 | 14.05.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-PTOCL | 6700 | 42775 | 5487 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-PTOCL90009475
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Pump Drive Gearbox RH | 2028-05-14 | 2028-05-15 | 36 hrs | FY28 | 108 | 90003161 | A1 | 1000158823 | 14.05.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-PPDRR | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -HYDSYS-PPDRR90003161
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Adjust 4500hr Valve Set | 2028-05-15 | 2028-05-15 | 10 hrs | FY28 | 20 | 90027549 | A1 | 1000284516 | 15.05.2028 | 4500 | CLB-MP-EXCV-EX7124-LHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-LHENGN90027549
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Adjust 4500hr Valve Set | 2028-05-15 | 2028-05-15 | 10 hrs | FY28 | 20 | 90027549 | A1 | 1000284582 | 15.05.2028 | 4500 | CLB-MP-EXCV-EX7124-RHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-RHENGN90027549
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Engine Cool Fan RH | 2028-05-15 | 2028-05-15 | 6 hrs | FY28 | 12 | 90003164 | A1 | 1000158831 | 15.05.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HECPR | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HECPR90003164
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Radiator RH Engine | 2028-05-15 | 2028-05-15 | 12 hrs | FY28 | 24 | 90017957 | A1 | 1000158814 | 15.05.2028 | 18000 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-RADTR | 6700 | 42775 | 42775 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-RADTR90017957
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Boom Arch Hoses | 2028-05-15 | 2028-05-15 | 12 hrs | FY28 | 24 | 90022724 | A1 | 1000237181 | 15.05.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-BMARH | 6700 | 27054 | 11930 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-BMARH90022724
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Inspection Ext Static Line | 2028-05-21 | 2028-05-21 | 4 hrs | FY28 | 4 | 90029897 | A1 | 1000359517 | 21.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029897
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2028-05-24 | 2028-05-24 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000337317 | 24.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Track Tension Tuning-Adjust | 2028-05-27 | 2028-05-27 | 3 hrs | FY28 | 9 | 90020545 | A1 | 1000340343 | 27.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7138-UNDERC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2028-05-27 | 2028-05-27 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000348588 | 27.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2028-05-27 | 2028-05-27 | 4 hrs | FY28 | 4 | 90014347 | A1 | 1000330578 | 27.05.2028 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Engine Midlife Complete RH | 2028-05-31 | 2028-06-02 | 54 hrs | FY28 | 76 | 90022685 | A1 | 1000237005 | 31.05.2028 | 9000 | CLB-MP-EXCV-EX7118-RHENGN | 6700 | 25972 | 14409 | CLB-MP-EXCV-EX7118-RHENGN90022685
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2028-06-01 | 2028-06-01 | 6 hrs | FY28 | 12 | 90035479 | A1 | 1000359913 | 01.06.2028 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Fan Drive Eng Cooling Hoses | 2028-06-01 | 2028-06-02 | 18 hrs | FY28 | 36 | 90009469 | A2 | 1000158864 | 01.06.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDECH | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDECH90009469
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Pump to Rotor Hoses | 2028-06-01 | 2028-06-02 | 24 hrs | FY28 | 48 | 90009473 | 1 | 1000158868 | 01.06.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-MPRCH | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-MPRCH90009473
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Auto Lube Pump | 2028-06-02 | 2028-06-02 | 6 hrs | FY28 | 6 | 90027592 | A1 | 1000284661 | 02.06.2028 | 6000 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP90027592
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Track Tension Tuning-Adjust | 2028-06-04 | 2028-06-04 | 3 hrs | FY28 | 9 | 90029977 | A1 | 1000359587 | 04.06.2028 | 6 Monthly | CLB-MP-EXCV-EX7149-UNDERC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-UNDERC90029977
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Inspection Ext Static Line | 2028-06-09 | 2028-06-09 | 4 hrs | FY28 | 4 | 90029897 | A1 | 1000357332 | 09.06.2028 | 6 Monthly | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2028-06-09 | 2028-06-09 | 4 hrs | FY28 | 4 | 90022746 | A1 | 1000237081 | 09.06.2028 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Power Pack Module | 2028-06-11 | 2028-06-13 | 64 hrs | FY28 | 172 | 90030914 | A1 | 1000348536 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90030914
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Auto Lube Pump P1 | 2028-06-11 | 2028-06-11 | 2 hrs | FY28 | 2 | 90035369 | A1 | 1000348394 | 11.06.2028 | 10000 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBPP | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBPP90035369
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Grease Block & Injectors | 2028-06-11 | 2028-06-13 | 48 hrs | FY28 | 84 | 90030749 | A1 | 1000348549 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ90030749
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Accumulator Track Hyd LH | 2028-06-11 | 2028-06-11 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000348390 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCL90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Accumulator Track Hyd RH | 2028-06-11 | 2028-06-11 | 3 hrs | FY28 | 3 | 90030729 | A1 | 1000348391 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCR90030729
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Bucket LH Lift | 2028-06-11 | 2028-06-12 | 30 hrs | FY28 | 54 | 90030725 | A1 | 1000348544 | 11.06.2028 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYL | 6200 | 8353 | 3074 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYL90030725
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Ladder Raise Cyl | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 24 | 90030750 | A1 | 1000348552 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-LACYL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-LACYL90030750
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Service Arm Locking Cyl | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 20 | 90030752 | A1 | 1000348580 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-SHCYL |  |  |  | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-SHCYL90030752
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Motor Swing Front | 2028-06-11 | 2028-06-12 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000348554 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-SWMOF | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-SWMOF90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Motor Swing Rear | 2028-06-11 | 2028-06-12 | 18 hrs | FY28 | 26 | 90030727 | A1 | 1000348555 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-SWMOR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-SWMOR90030727
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Motor Travel LHF | 2028-06-11 | 2028-06-11 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000348531 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMLF | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMLF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Motor Travel LHR | 2028-06-11 | 2028-06-11 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000348532 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMLR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMLR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Motor Travel RHF | 2028-06-11 | 2028-06-11 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000348533 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMRF | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMRF90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Motor Travel RHR | 2028-06-11 | 2028-06-11 | 6 hrs | FY28 | 10 | 90030728 | A1 | 1000348534 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMRR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMRR90030728
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Hyd Vlve Bank Module Quarter Life | 2028-06-11 | 2028-06-11 | 9 hrs | FY28 | 15 | 90027371 | A1 | 1000348527 | 11.06.2028 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVLU | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVLU90027371
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Rotary Connection & Hoses | 2028-06-11 | 2028-06-15 | 96 hrs | FY28 | 168 | 90030430 | A1 | 1000348584 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-HYDSYS-ROTRY | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-HYDSYS-ROTRY90030430
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Bucket | 2028-06-11 | 2028-06-13 | 42 hrs | FY28 | 78 | 90030745 | A1 | 1000348541 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-STRUCT-BUCKT | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BUCKT90030745
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Operators Seat | 2028-06-11 | 2028-06-11 | 9 hrs | FY28 | 17 | 90030739 | A1 | 1000348535 | 11.06.2028 | 10000 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-SEATO | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-SEATO90030739
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Tank Module | 2028-06-11 | 2028-06-12 | 38 hrs | FY28 | 86 | 90036464 | A1 | 1000348525 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-STRUCT-HDTNK | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-HDTNK90036464
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Service Module Hosing | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 24 | 90030753 | A1 | 1000348579 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-STRUCT-SRVCT-SHHLF |  |  |  | CLB-MP-EXCV-EX7141-STRUCT-SRVCT-SHHLF90030753
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Gearbox Swing P1 | 2028-06-11 | 2028-06-13 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000348520 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-SWGSYS-SWBOX-SGBPF | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-SWGSYS-SWBOX-SGBPF90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Gearbox Swing P2 | 2028-06-11 | 2028-06-13 | 55 hrs | FY28 | 109 | 90030720 | A1 | 1000348521 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-SWGSYS-SWBOX-SGBPR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-SWGSYS-SWBOX-SGBPR90030720
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Track Idler LH | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000348528 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-IDLLH | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-IDLLH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Sprocket LH | 2028-06-11 | 2028-06-12 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000348529 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-SPRKL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-SPRKL90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Track Hyd Tensioner LH | 2028-06-11 | 2028-06-12 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000348592 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-TENSL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Track Assembly LH | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000348589 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-TRKLH | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-TRKLH90030719
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Track Idler RH | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 36 | 90030740 | A1 | 1000348582 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-IDLRH | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-IDLRH90030740
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Sprocket RH | 2028-06-11 | 2028-06-12 | 24 hrs | FY28 | 72 | 90030718 | A1 | 1000348583 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-SPRKR | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-SPRKR90030718
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Track Hyd Tensioner RH | 2028-06-11 | 2028-06-12 | 26 hrs | FY28 | 74 | 90024277 | A1 | 1000348593 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-TENSL | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-TENSL90024277
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Track Assembly RH | 2028-06-11 | 2028-06-11 | 12 hrs | FY28 | 36 | 90030719 | A1 | 1000348590 | 11.06.2028 | 20000 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-TRKRH | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-TRKRH90030719
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Bucket RH | 2028-06-12 | 2028-06-13 | 30 hrs | FY28 | 54 | 90029967 | A1 | 1000304624 | 12.06.2028 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYR | 6200 | 13908 | 8495 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYR90029967
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Annual Air Con Service LH | 2028-06-13 | 2028-06-13 | 12 hrs | FY28 | 12 | 90004141 | 2 | 1000207158 | 13.06.2028 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL | 6700 | 21488 | 7104 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL90004141
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Boom & MCV Hoses | 2028-06-15 | 2028-06-18 | 88 hrs | FY28 | 136 | 90032593 | A1 | 1000325062 | 15.06.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC | 6700 | 19559 | 11480 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC90032593
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Boom Stick Bucket Cyl Hoses | 2028-06-15 | 2028-06-18 | 88 hrs | FY28 | 136 | 90027560 | A1 | 1000284629 | 15.06.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC | 6700 | 19559 | 11480 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC90027560
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Engine Cat C32 | 2028-06-16 | 2028-06-23 | 174.5 hrs | FY28 | 252.5 | 90022670 | A1 | 1000237109 | 16.06.2028 | 18000 | CLB-MP-EXCV-EX7119-LHENGN | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-LHENGN90022670
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Case Drain Hoses | 2028-06-22 | 2028-06-22 | 8 hrs | FY28 | 16 | 90027566 | A1 | 1000297370 | 22.06.2028 | 15000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HPCDL | 6700 | 16452 | 2288 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HPCDL90027566
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Annual Air Con Service LH | 2028-06-23 | 2028-06-23 | 12 hrs | FY28 | 12 | 90022660 | A1 | 1000242610 | 23.06.2028 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL | 6700 | 19940 | 6054 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL90022660
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Engine Cool Fan LH | 2028-06-29 | 2028-06-29 | 6 hrs | FY28 | 12 | 90003164 | A1 | 1000158830 | 29.06.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HECPL | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HECPL90003164
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Pump Drive Gearbox LH | 2028-06-29 | 2028-06-30 | 36 hrs | FY28 | 108 | 90003161 | A1 | 1000158822 | 29.06.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-PPDRL | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-PPDRL90003161
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Engine Cat C32 LH | 2028-06-29 | 2028-07-06 | 168 hrs | FY28 | 250 | 90017913 | A1 | 1000158786 | 29.06.2028 | 18000 | CLB-MP-EXCV-EX014 -LHENGN | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -LHENGN90017913
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Radiator LH Engine | 2028-06-29 | 2028-06-29 | 12 hrs | FY28 | 24 | 90017956 | A1 | 1000158799 | 29.06.2028 | 18000 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-RADTR | 6700 | 42775 | 23025 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-RADTR90017956
| Onsite PM | Excavators | Fortescue |  | FY29 - EXCAVATORS - COMPONENTS DURING PM | 2028-07-01 |  |  | FY29
| Onsite PM | Excavators | Fortescue | MOC | MAJOR ON CONDITION | 2028-07-01 | 2029-06-30 | 364 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | AUGUST | 2028-08-01 | 2028-08-31 | 30 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | SEPTEMBER | 2028-09-01 | 2028-09-30 | 29 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | OCTOBER | 2028-10-01 | 2028-10-31 | 30 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | NOVEMBER | 2028-11-01 | 2028-11-30 | 29 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | DECEMBER | 2028-12-01 | 2028-12-31 | 30 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | JANUARY | 2029-01-01 | 2029-01-31 | 30 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | FEBRUARY | 2029-02-01 | 2029-02-28 | 27 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | MARCH | 2029-03-01 | 2029-03-31 | 30 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | APRIL | 2029-04-01 | 2029-04-30 | 29 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | MAY | 2029-05-01 | 2029-05-31 | 30 days | FY29
| Onsite PM | Excavators | Fortescue | MOC | JUNE | 2029-06-01 | 2029-06-30 | 29 days | FY29
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Case Drain Hoses | 2028-07-08 | 2028-07-08 | 8 hrs | FY29 | 16 | 90009472 | A2 | 1000158867 | 08.07.2028 | 15000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HPCDL | 6700 | 42775 | 368 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HPCDL90009472
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 PP Initial 500Hr Valve Set | 2028-07-10 | 2028-07-10 | 6 hrs | FY29 | 12 | 90031022 | A1 | 1000348539 | 10.07.2028 | 500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90031022
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Servo Hoses Bulkhead to MCV | 2028-07-12 | 2028-07-12 | 8 hrs | FY29 | 16 | 90009479 | 1 | 1000158874 | 12.07.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHMCV | 6700 | 42775 | 10414 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHMCV90009479
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Adjust 500hr Initial Valve Set | 2028-07-13 | 2028-07-13 | 10 hrs | FY29 | 20 | 90022680 | A1 | 1000237119 | 13.07.2028 | 500 | CLB-MP-EXCV-EX7119-LHENGN | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-LHENGN90022680
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Minestar Harness | 2028-07-17 | 2028-07-18 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000369999 | 17.07.2028 | 4000 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Wiper Blades | 2028-07-19 | 2028-07-19 | 2 hrs | FY29 | 2 | 90004684 | 1 | 1000207159 | 19.07.2028 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-CABIN90004684
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Fan Engine Cool RH | 2028-07-20 | 2028-07-20 | 6 hrs | FY29 | 12 | 90027494 | A1 | 1000297337 | 20.07.2028 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPR90027494
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Minestar Harness | 2028-07-20 | 2028-07-21 | 27.5 hrs | FY29 | 43.5 | 90030746 | A1 | 1000348553 | 20.07.2028 | 5000 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC90030746
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Auto Lube Pump | 2028-07-21 | 2028-07-21 | 6 hrs | FY29 | 6 | 90027592 | A1 | 1000297398 | 21.07.2028 | 6000 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP90027592
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 1500Hr Engine Valve Set | 2028-07-23 | 2028-07-23 | 6 hrs | FY29 | 12 | 90035479 | A1 | 1000359909 | 23.07.2028 | 1500 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2028-07-25 | 2028-07-25 | 4 hrs | FY29 | 4 | 90022746 | A1 | 1000237212 | 25.07.2028 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Adjust 500hr Initial Valve Set | 2028-07-26 | 2028-07-26 | 10 hrs | FY29 | 20 | 90017925 | A1 | 1000158796 | 26.07.2028 | 500 | CLB-MP-EXCV-EX014 -LHENGN | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -LHENGN90017925
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Engine Midlife Complete LH | 2028-07-26 | 2028-07-28 | 54 hrs | FY29 | 76 | 90018424 | A1 | 1000207071 | 26.07.2028 | 9000 | CLB-MP-EXCV-EX7112-LHENGN | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-LHENGN90018424
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Annual Air Con Service RH | 2028-07-29 | 2028-07-29 | 12 hrs | FY29 | 12 | 90022660 | A1 | 1000237208 | 29.07.2028 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR | 6700 | 27054 | 19941 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR90022660
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Swing LHR | 2028-07-30 | 2028-07-31 | 21 hrs | FY29 | 27 | 90027503 | A1 | 1000297351 | 30.07.2028 | 15000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMLR | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMLR90027503
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Swing RHF | 2028-07-30 | 2028-07-31 | 21 hrs | FY29 | 27 | 90027503 | A1 | 1000297352 | 30.07.2028 | 15000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMRF | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMRF90027503
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Swing RHR | 2028-07-30 | 2028-07-31 | 21 hrs | FY29 | 27 | 90027503 | A1 | 1000297353 | 30.07.2028 | 15000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMRR | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMRR90027503
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic Oil Replacement | 2028-08-02 | 2028-08-02 | 12 hrs | FY29 | 12 | 90016793 | 1 | 1000158890 | 02.08.2028 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic System Tune Up | 2028-08-02 | 2028-08-02 | 12 hrs | FY29 | 24 | 90017865 | 1 | 1000163743 | 02.08.2028 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Minestar Harness | 2028-08-04 | 2028-08-05 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370303 | 04.08.2028 | 4000 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Engine Midlife Complete RH | 2028-08-05 | 2028-08-07 | 54 hrs | FY29 | 76 | 90018424 | A1 | 1000207086 | 05.08.2028 | 9000 | CLB-MP-EXCV-EX7112-RHENGN | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-RHENGN90018424
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Oil Suction Hoses | 2028-08-06 | 2028-08-07 | 24 hrs | FY29 | 48 | 90009474 | A2 | 1000158869 | 06.08.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-OILSC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-OILSC90009474
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 1500Hr Engine Valve Set | 2028-08-08 | 2028-08-08 | 6 hrs | FY29 | 12 | 90035479 | A1 | 1000359910 | 08.08.2028 | 1500 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Swing LHR | 2028-08-10 | 2028-08-11 | 21 hrs | FY29 | 27 | 90003175 | A1 | 1000207117 | 10.08.2028 | 15000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMLR | 6700 | 31524 | 16212 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMLR90003175
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Swing RHF | 2028-08-10 | 2028-08-11 | 21 hrs | FY29 | 27 | 90003175 | A1 | 1000207118 | 10.08.2028 | 15000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMRF | 6700 | 31524 | 415 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMRF90003175
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 12M Hydraulic Service & Repairs | 2028-08-11 | 2028-08-12 | 18 hrs | FY29 | 30 | 90029940 | A1 | 1000357445 | 11.08.2028 | 12 Monthly | CLB-MP-EXCV-EX7148-HYDSYS |  |  |  | CLB-MP-EXCV-EX7148-HYDSYS90029940
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Grease Tank Level Valve | 2028-08-11 | 2028-08-11 | 2 hrs | FY29 | 2 | 90029942 | A1 | 1000357447 | 11.08.2028 | 12 Monthly | CLB-MP-EXCV-EX7148-GRSYST |  |  |  | CLB-MP-EXCV-EX7148-GRSYST90029942
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel LHF | 2028-08-12 | 2028-08-12 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000237174 | 12.08.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLF | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel LHR | 2028-08-12 | 2028-08-12 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000237175 | 12.08.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLR | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel RHF | 2028-08-12 | 2028-08-12 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000237176 | 12.08.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRF | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Travel RHR | 2028-08-12 | 2028-08-12 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000237177 | 12.08.2028 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRR | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRR90022657
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Final Drive LH | 2028-08-12 | 2028-08-14 | 48 hrs | FY29 | 144 | 90022634 | A1 | 1000237139 | 12.08.2028 | 24000 | CLB-MP-EXCV-EX7119-TRAVEL-FDRLH | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-TRAVEL-FDRLH90022634
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Final Drive RH | 2028-08-12 | 2028-08-14 | 48 hrs | FY29 | 144 | 90022634 | A1 | 1000237140 | 12.08.2028 | 24000 | CLB-MP-EXCV-EX7119-TRAVEL-FDRRH | 6700 | 27054 | 10337 | CLB-MP-EXCV-EX7119-TRAVEL-FDRRH90022634
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 6M Anritsu Test WiFi Cables | 2028-08-14 | 2028-08-14 | 2 hrs | FY29 | 2 | 90020303 | A1 | 1000210997 | 14.08.2028 | 6 Monthly | CLB-MP-EXCV-EX7112-COMMUN-FLMGT |  |  |  | CLB-MP-EXCV-EX7112-COMMUN-FLMGT90020303
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Pump to Rotor Hose | 2028-08-15 | 2028-08-16 | 24 hrs | FY29 | 48 | 90027567 | A1 | 1000297371 | 15.08.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-MPRCH | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-MPRCH90027567
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Servo Hose Bulkhead to MCV | 2028-08-15 | 2028-08-15 | 8 hrs | FY29 | 16 | 90027574 | A1 | 1000297377 | 15.08.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHMCV | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHMCV90027574
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Hydraulic Oil Replacement | 2028-08-15 | 2028-08-15 | 12 hrs | FY29 | 12 | 90016793 | 1 | 1000207153 | 15.08.2028 | 6000 | CLB-MP-EXCV-EX7112-HYDSYS | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Pos1 & Pos2 | 2028-08-17 | 2028-08-18 | 26 hrs | FY29 | 42 | 90003163 | A1 | 1000158828 | 17.08.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP1P2 | 6700 | 42775 | 9748 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP1P290003163
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Auto Lube SStructure | 2028-08-17 | 2028-08-17 | 12 hrs | FY29 | 12 | 90018988 | 1 | 1000207165 | 17.08.2028 | 6000 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP90018988
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Hydraulic System Tune Up | 2028-08-17 | 2028-08-17 | 12 hrs | FY29 | 24 | 90017865 | 1 | 1000207164 | 17.08.2028 | 6000 | CLB-MP-EXCV-EX7112-HYDSYS | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Swing Circuit Hoses | 2028-08-17 | 2028-08-17 | 8 hrs | FY29 | 16 | 90009481 | 1 | 1000207145 | 17.08.2028 | 9000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWCRT | 6700 | 31524 | 4098 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWCRT90009481
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Minestar Harness | 2028-08-20 | 2028-08-21 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370300 | 20.08.2028 | 4000 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Fan Drive Hyd Cooling Hoses | 2028-08-21 | 2028-08-22 | 18 hrs | FY29 | 36 | 90027565 | A1 | 1000284631 | 21.08.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDHCH | 6700 | 19559 | 10250 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDHCH90027565
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hydraulic Cooling Circ Hoses | 2028-08-21 | 2028-08-22 | 18 hrs | FY29 | 36 | 90031704 | A1 | 1000284632 | 21.08.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HCCHH | 6700 | 19559 | 10250 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HCCHH90031704
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Track Tensioning Hoses | 2028-08-21 | 2028-08-21 | 3 hrs | FY29 | 3 | 90027579 | A1 | 1000284645 | 21.08.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TRTNH | 6700 | 19559 | 10250 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TRTNH90027579
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Gearbox Swing LHR | 2028-08-21 | 2028-08-23 | 48 hrs | FY29 | 80 | 90022744 | A1 | 1000237010 | 21.08.2028 | 20000 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBLR | 6700 | 25972 | 5908 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBLR90022744
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Gearbox Swing RHF | 2028-08-21 | 2028-08-23 | 48 hrs | FY29 | 80 | 90022744 | A1 | 1000237011 | 21.08.2028 | 20000 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBRF | 6700 | 25972 | 5908 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBRF90022744
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Gearbox Swing RHR | 2028-08-21 | 2028-08-23 | 48 hrs | FY29 | 80 | 90022744 | A1 | 1000237012 | 21.08.2028 | 20000 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBRR | 6700 | 25972 | 5908 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBRR90022744
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 1500Hr Engine Valve Set | 2028-08-24 | 2028-08-24 | 6 hrs | FY29 | 12 | 90035479 | A1 | 1000359913 | 24.08.2028 | 1500 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90035479
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Operators Seat | 2028-08-24 | 2028-08-24 | 2 hrs | FY29 | 2 | 90027613 | A1 | 1000297363 | 24.08.2028 | 10000 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-SEATS | 6700 | 16452 | 6191 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-SEATS90027613
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Batteries | 2028-08-24 | 2028-08-24 | 8 hrs | FY29 | 8 | 90022665 | A1 | 1000237073 | 24.08.2028 | 10000 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-BATTY | 6700 | 25972 | 5056 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-BATTY90022665
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Bucket RH | 2028-08-25 | 2028-08-26 | 26 hrs | FY29 | 32 | 90022647 | A1 | 1000237163 | 25.08.2028 | 10000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYR | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYR90022647
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Gearbox Swing LHR | 2028-08-25 | 2028-08-27 | 48 hrs | FY29 | 80 | 90022744 | A1 | 1000237141 | 25.08.2028 | 20000 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBLR | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBLR90022744
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Gearbox Swing RHF | 2028-08-25 | 2028-08-27 | 48 hrs | FY29 | 80 | 90022744 | A1 | 1000237142 | 25.08.2028 | 20000 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBRF | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBRF90022744
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Gearbox Swing RHR | 2028-08-25 | 2028-08-27 | 48 hrs | FY29 | 80 | 90022744 | A1 | 1000237143 | 25.08.2028 | 20000 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBRR | 6700 | 27054 | 6054 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBRR90022744
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel LHF | 2028-08-29 | 2028-08-29 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000207124 | 29.08.2028 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLF | 6700 | 31524 | 9874 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLF90022657
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Batteries | 2028-08-31 | 2028-08-31 | 8 hrs | FY29 | 8 | 90016788 | 1 | 1000158891 | 31.08.2028 | 10000 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-BATTY | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-BATTY90016788
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Operators Seat | 2028-09-03 | 2028-09-03 | 3 hrs | FY29 | 6 | 90005246 | 1 | 1000158860 | 03.09.2028 | 8000 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-SEATS | 6700 | 42775 | 9748 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-SEATS90005246
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Hydraulic Oil Replacement | 2028-09-09 | 2028-09-09 | 12 hrs | FY29 | 12 | 90016793 | 1 | 1000297387 | 09.09.2028 | 6000 | CLB-MP-EXCV-EX7122-HYDSYS | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Hydraulic System Tune Up | 2028-09-09 | 2028-09-09 | 12 hrs | FY29 | 24 | 90017865 | 1 | 1000297397 | 09.09.2028 | 6000 | CLB-MP-EXCV-EX7122-HYDSYS | 6700 | 16452 | 3837 | CLB-MP-EXCV-EX7122-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cyl Boom LH | 2028-09-10 | 2028-09-14 | 90 hrs | FY29 | 138 | 90022644 | A1 | 1000237027 | 10.09.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BMCYL | 6700 | 25972 | 3545 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BMCYL90022644
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Auto Lube Pump | 2028-09-13 | 2028-09-13 | 6 hrs | FY29 | 6 | 90022747 | A1 | 1000237215 | 13.09.2028 | 6000 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP90022747
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Inspection Isolator Panel | 2028-09-15 | 2028-09-15 | 2 hrs | FY29 | 2 | 90029980 | 1 | 1000359589 | 15.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7149-ELCTLV |  |  |  | CLB-MP-EXCV-EX7149-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl 24V Batteries | 2028-09-15 | 2028-09-15 | 5 hrs | FY29 | 9 | 90029978 | A1 | 1000359588 | 15.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST90029978
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Hydraulic Service & Repairs | 2028-09-15 | 2028-09-16 | 18 hrs | FY29 | 30 | 90029940 | A1 | 1000359550 | 15.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7149-HYDSYS |  |  |  | CLB-MP-EXCV-EX7149-HYDSYS90029940
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Service Air Conditioner Sys 1 | 2028-09-15 | 2028-09-15 | 12 hrs | FY29 | 12 | 90030498 | A1 | 1000359583 | 15.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7149-STRUCT-AIRC1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC190030498
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 12M Service Air Conditioner Sys 2 | 2028-09-15 | 2028-09-15 | 12 hrs | FY29 | 12 | 90030536 | A1 | 1000359585 | 15.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7149-STRUCT-AIRC2 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC290030536
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Grease Tank Level Valve | 2028-09-15 | 2028-09-15 | 2 hrs | FY29 | 2 | 90029942 | A1 | 1000359552 | 15.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7149-GRSYST |  |  |  | CLB-MP-EXCV-EX7149-GRSYST90029942
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Hose Bucket Cyl | 2028-09-18 | 2028-09-19 | 18 hrs | FY29 | 54 | 90030738 | A1 | 1000348523 | 18.09.2028 | 8000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBKCL | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Hose Boom Cyl | 2028-09-18 | 2028-09-18 | 8 hrs | FY29 | 24 | 90030735 | A1 | 1000348522 | 18.09.2028 | 8000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBMCL | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Hyd Hose Stick Cyl | 2028-09-18 | 2028-09-18 | 12 hrs | FY29 | 24 | 90030737 | A1 | 1000348524 | 18.09.2028 | 8000 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HSTCL | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HSTCL90030737
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Track Tension Tuning-Adjust | 2028-09-18 | 2028-09-18 | 3 hrs | FY29 | 9 | 90020545 | A1 | 1000348591 | 18.09.2028 | 6 Monthly | CLB-MP-EXCV-EX7141-UNDERC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Ovhl 24M Air Conditioner Sys1 Eng | 2028-09-18 | 2028-09-20 | 48 hrs | FY29 | 48 | 90035243 | A1 | 1000359794 | 18.09.2028 | 24 Monthly | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC1 | 6500 | 4530 | 4530 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC190035243
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Ovhl 24M Air Conditioner Sys2 Hyd | 2028-09-18 | 2028-09-19 | 36 hrs | FY29 | 36 | 90035267 | A1 | 1000359796 | 18.09.2028 | 24 Monthly | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC290035267
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Power Pack Module Qtr Life | 2028-09-20 | 2028-09-20 | 7 hrs | FY29 | 13 | 90031021 | A1 | 1000330528 | 20.09.2028 | 5000 | CLB-MP-EXCV-EX7139-ENGINE | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-ENGINE90031021
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Grease System Audit | 2028-09-20 | 2028-09-21 | 24 hrs | FY29 | 36 | 90030748 | A1 | 1000330538 | 20.09.2028 | 5000 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ90030748
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Fan Drive Eng Cooling Hose | 2028-09-21 | 2028-09-22 | 18 hrs | FY29 | 36 | 90027564 | A1 | 1000284630 | 21.09.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDECH | 6700 | 19559 | 9696 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDECH90027564
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Minestar Harness | 2028-09-23 | 2028-09-24 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370301 | 23.09.2028 | 4000 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC90031708
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Adjust Track Tension Tuning | 2028-09-25 | 2028-09-25 | 3 hrs | FY29 | 9 | 90029977 | A1 | 1000304629 | 25.09.2028 | 6 Monthly | CLB-MP-EXCV-EX7133-UNDERC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC90029977
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Grease Tank Level Valve | 2028-09-27 | 2028-09-27 | 2 hrs | FY29 | 2 | 90015003 | A1 | 1000330541 | 27.09.2028 | 12 Monthly | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK90015003
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Emergency Ladder | 2028-09-29 | 2028-09-29 | 3 hrs | FY29 | 6 | 90022513 | 1 | 1000307860 | 29.09.2028 | 24 Monthly | CLB-MP-EXCV-EX7112-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7112-STRUCT-STLAD-SLFXD90022513
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 12M Hydraulic Service & Repairs | 2028-10-02 | 2028-10-03 | 18 hrs | FY29 | 30 | 90014448 | A1 | 1000330356 | 02.10.2028 | 12 Monthly | CLB-MP-EXCV-EX7139-HYDSYS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Bucket LH | 2028-10-03 | 2028-10-04 | 26 hrs | FY29 | 32 | 90022647 | A1 | 1000237162 | 03.10.2028 | 10000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYL | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYL90022647
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Batteries | 2028-10-06 | 2028-10-06 | 4 hrs | FY29 | 4 | 90027525 | A1 | 1000297388 | 06.10.2028 | 10000 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-BATTY | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-BATTY90027525
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2028-10-07 | 2028-10-07 | 4 hrs | FY29 | 4 | 90022746 | A1 | 1000237081 | 07.10.2028 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Rotor to Drive Motor Hoses | 2028-10-10 | 2028-10-10 | 10 hrs | FY29 | 20 | 90009476 | A2 | 1000158871 | 10.10.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCDMH | 6700 | 42775 | 8761 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCDMH90009476
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Travel Motor Case Drain Hoses | 2028-10-10 | 2028-10-10 | 5 hrs | FY29 | 10 | 90009483 | A2 | 1000158878 | 10.10.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TMCDH | 6700 | 42775 | 32631 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TMCDH90009483
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel RHR | 2028-10-10 | 2028-10-10 | 6 hrs | FY29 | 12 | 90003178 | A1 | 1000158855 | 10.10.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRR | 6700 | 42775 | 21181 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRR90003178
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Fan Engine Cool RH | 2028-10-12 | 2028-10-12 | 6 hrs | FY29 | 18 | 90022656 | A1 | 1000237173 | 12.10.2028 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMECR | 6700 | 27054 | 3277 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMECR90022656
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl PTO Cooling Hoses | 2028-10-14 | 2028-10-14 | 6 hrs | FY29 | 12 | 90027569 | A1 | 1000297373 | 14.10.2028 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-PTOCL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-PTOCL90027569
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Ovhl 24M Air Conditioner Sys1 Eng | 2028-10-14 | 2028-10-16 | 48 hrs | FY29 | 48 | 90035445 | A1 | 1000359798 | 14.10.2028 | 24 Monthly | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC1 | 6500 | 4257 | 4257 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC190035445
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Ovhl 24M Air Conditioner Sys2 Hyd | 2028-10-14 | 2028-10-15 | 36 hrs | FY29 | 36 | 90035446 | A1 | 1000359800 | 14.10.2028 | 24 Monthly | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC290035446
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Adjust Track Tension Tuning | 2028-10-20 | 2028-10-20 | 3 hrs | FY29 | 9 | 90020545 | A1 | 1000337320 | 20.10.2028 | 6 Monthly | CLB-MP-EXCV-EX7140-UNDERC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Auto Lube Pump | 2028-10-24 | 2028-10-24 | 6 hrs | FY29 | 6 | 90022747 | A1 | 1000237084 | 24.10.2028 | 6000 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP90022747
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Hydraulic Oil Replacement | 2028-10-24 | 2028-10-24 | 12 hrs | FY29 | 12 | 90022667 | A1 | 1000237072 | 24.10.2028 | 6000 | CLB-MP-EXCV-EX7118-HYDSYS | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS90022667
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Main Pump to Rotor Hoses | 2028-10-24 | 2028-10-25 | 24 hrs | FY29 | 48 | 90022730 | A1 | 1000345670 | 24.10.2028 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-MPRCH | 6700 | 25972 | 8726 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-MPRCH90022730
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 12M Inspection Isolator Panel | 2028-10-27 | 2028-10-27 | 2 hrs | FY29 | 2 | 90022525 | A2 | 1000336837 | 27.10.2028 | 12 Monthly | CLB-MP-EXCV-EX7140-ELCTLV |  |  |  | CLB-MP-EXCV-EX7140-ELCTLV90022525
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Hose Boom Cyl | 2028-10-27 | 2028-10-27 | 8 hrs | FY29 | 24 | 90029908 | A1 | 1000304577 | 27.10.2028 | 8000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMCL | 6200 | 13908 | 208 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Hose Stick Cyl | 2028-10-27 | 2028-10-27 | 12 hrs | FY29 | 24 | 90029909 | A1 | 1000304578 | 27.10.2028 | 8000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSTCL | 6200 | 13908 | 208 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Hyd Hose Bucket Cyl | 2028-10-27 | 2028-10-28 | 18 hrs | FY29 | 54 | 90029911 | A1 | 1000304579 | 27.10.2028 | 8000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBKCL | 6200 | 13908 | 389 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBKCL90029911
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 12M Inspection Isolator Panel | 2028-10-27 | 2028-10-27 | 2 hrs | FY29 | 2 | 90022525 | A2 | 1000330357 | 27.10.2028 | 12 Monthly | CLB-MP-EXCV-EX7139-ELCTLV |  |  |  | CLB-MP-EXCV-EX7139-ELCTLV90022525
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Adjust 4500hr Valve Set | 2028-10-27 | 2028-10-27 | 10 hrs | FY29 | 20 | 90022679 | A1 | 1000236989 | 27.10.2028 | 4500 | CLB-MP-EXCV-EX7118-LHENGN | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-LHENGN90022679
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Adjust 4500hr Valve Set | 2028-10-28 | 2028-10-28 | 10 hrs | FY29 | 20 | 90027549 | A1 | 1000297275 | 28.10.2028 | 4500 | CLB-MP-EXCV-EX7122-LHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN90027549
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Adjust 4500hr Valve Set | 2028-10-28 | 2028-10-28 | 10 hrs | FY29 | 20 | 90027549 | A1 | 1000297320 | 28.10.2028 | 4500 | CLB-MP-EXCV-EX7122-RHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN90027549
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Bucket Cyl | 2028-10-28 | 2028-10-29 | 18 hrs | FY29 | 54 | 90030738 | A1 | 1000330513 | 28.10.2028 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Boom Cyl | 2028-10-28 | 2028-10-28 | 8 hrs | FY29 | 24 | 90030735 | A1 | 1000330512 | 28.10.2028 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Hyd Hose Stick Cyl | 2028-10-28 | 2028-10-28 | 12 hrs | FY29 | 24 | 90030737 | A1 | 1000330514 | 28.10.2028 | 8000 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL | 6200 | 11792 | 7008 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL90030737
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Static Line Inspection | 2028-10-30 | 2028-10-30 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000340340 | 30.10.2028 | 6 Monthly | CLB-MP-EXCV-EX7138-STRUCT | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Power Pack Module Qtr Life | 2028-10-31 | 2028-10-31 | 1 hr | FY29 | 1 | 90027378 | A1 | 1000337268 | 31.10.2028 | 5000 | CLB-MP-EXCV-EX7140-ENGINE | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-ENGINE90027378
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Grease System Audit | 2028-10-31 | 2028-11-01 | 24 hrs | FY29 | 36 | 90030748 | A1 | 1000337277 | 31.10.2028 | 5000 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ | 6200 | 10954 | 672 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ90030748
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl HV Motor Coupling | 2028-11-02 | 2028-11-03 | 20 hrs | FY29 | 30 | 90030128 | A1 | 1000357514 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-ELCTHV-HVMOT-COUPL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-ELCTHV-HVMOT-COUPL90030128
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Gearbox Swing P1 | 2028-11-02 | 2028-11-04 | 55 hrs | FY29 | 109 | 90029900 | A1 | 1000357335 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-SWGSYS-SWBOX-SGBPF | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-SWGSYS-SWBOX-SGBPF90029900
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Gearbox Swing P2 | 2028-11-02 | 2028-11-04 | 55 hrs | FY29 | 109 | 90029900 | A1 | 1000357336 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-SWGSYS-SWBOX-SGBPR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-SWGSYS-SWBOX-SGBPR90029900
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Pump Drive/Splitter Gearbox | 2028-11-02 | 2028-11-07 | 120 hrs | FY29 | 240 | 90030087 | A1 | 1000357497 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-PMPDR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-PMPDR90030087
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Pump Hyd Work Pos1 & Pos2 | 2028-11-02 | 2028-11-03 | 36 hrs | FY29 | 54 | 90030234 | A1 | 1000357498 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-WPPP1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-WPPP190030234
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Pump Hyd Work Pos3 & Pos4 | 2028-11-02 | 2028-11-03 | 36 hrs | FY29 | 54 | 90030286 | A1 | 1000357506 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-WPPP2 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-WPPP290030286
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Pump Swing Combination | 2028-11-02 | 2028-11-03 | 24 hrs | FY29 | 36 | 90030252 | A1 | 1000357499 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SWPP1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SWPP190030252
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Pump Fan Hyd Oil Cooler | 2028-11-02 | 2028-11-03 | 24 hrs | FY29 | 36 | 90030278 | A1 | 1000357500 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-HECP1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-HECP190030278
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Pump Servo Bearing Lube | 2028-11-02 | 2028-11-02 | 4 hrs | FY29 | 4 | 90030280 | A1 | 1000357501 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SVPP1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SVPP190030280
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Lube Pump Splitter Gear Box | 2028-11-02 | 2028-11-02 | 4 hrs | FY29 | 4 | 90030281 | A1 | 1000357502 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-PTOLU | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-PTOLU90030281
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Pump Oil Replenishing | 2028-11-02 | 2028-11-02 | 4 hrs | FY29 | 4 | 90030285 | A1 | 1000357503 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-RPPP1 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-RPPP190030285
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Ladder Raise Cylinder | 2028-11-02 | 2028-11-02 | 3 hrs | FY29 | 6 | 90030320 | A1 | 1000357509 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-LACYL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-LACYL90030320
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Bucket LH Lift | 2028-11-02 | 2028-11-03 | 30 hrs | FY29 | 54 | 90029964 | A1 | 1000357474 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYL90029964
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Cyl Bucket RH Lift | 2028-11-02 | 2028-11-03 | 30 hrs | FY29 | 54 | 90029967 | A1 | 1000357475 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYR90029967
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Rotary Connection | 2028-11-02 | 2028-11-04 | 48 hrs | FY29 | 72 | 90029901 | A1 | 1000357337 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-ROTRY | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-ROTRY90029901
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Vlve Bank Module Quarter Life | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 12 | 90029987 | A1 | 1000357489 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVLU | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVLU90029987
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Valve Pressure Reducing Y3 | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 6 | 90030294 | A1 | 1000357508 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPRV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPRV90030294
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Valve pressure Limiting Y4 | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 6 | 90030321 | A1 | 1000357507 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPLV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPLV90030321
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Motor Swing Front | 2028-11-02 | 2028-11-03 | 18 hrs | FY29 | 26 | 90029905 | A1 | 1000357339 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-SWMOF | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-SWMOF90029905
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Motor Swing Rear | 2028-11-02 | 2028-11-03 | 18 hrs | FY29 | 26 | 90029905 | A1 | 1000357338 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-SWMOR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-SWMOR90029905
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Motor Travel LHF | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000357420 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMLF | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMLF90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Motor Travel LHR | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000357421 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMLR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMLR90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Motor Travel RHF | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000357422 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMRF | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMRF90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Motor Travel RHR | 2028-11-02 | 2028-11-02 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000357423 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMRR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMRR90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Accumulator Track Hyd LH | 2028-11-02 | 2028-11-02 | 3 hrs | FY29 | 3 | 90029907 | A1 | 1000357424 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCL90029907
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Accumulator Track Hyd RH | 2028-11-02 | 2028-11-02 | 3 hrs | FY29 | 3 | 90029907 | A1 | 1000357425 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCR90029907
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Accumulator Servo Hyd | 2028-11-02 | 2028-11-02 | 3 hrs | FY29 | 3 | 90030487 | A1 | 1000357490 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCS90030487
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Accumulator Ladder Hyd | 2028-11-02 | 2028-11-02 | 4 hrs | FY29 | 4 | 90030685 | A1 | 1000357516 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCB | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCB90030685
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Track Tensioning Hoses | 2028-11-02 | 2028-11-02 | 12 hrs | FY29 | 24 | 90030538 | A1 | 1000357515 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HHTTL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HHTTL90030538
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hyd Hose Work Pumps to Valves | 2028-11-02 | 2028-11-02 | 10.5 hrs | FY29 | 10.5 | 90030287 | A1 | 1000357504 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HWPVV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HWPVV90030287
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hyd Hose Swing Pump Swing Motor | 2028-11-02 | 2028-11-02 | 12 hrs | FY29 | 24 | 90030288 | A1 | 1000357505 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSPSM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSPSM90030288
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hyd Hose Rotary Con to Valve Bank | 2028-11-02 | 2028-11-02 | 12 hrs | FY29 | 24 | 90029912 | A1 | 1000357429 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCVV | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCVV90029912
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Hoses Rotary Conn to Travel Motor | 2028-11-02 | 2028-11-03 | 24 hrs | FY29 | 48 | 90029914 | A1 | 1000357430 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCTM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCTM90029914
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Operators Seat | 2028-11-02 | 2028-11-02 | 9 hrs | FY29 | 17 | 90029915 | A1 | 1000357431 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-CABIN-SEATO | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-CABIN-SEATO90029915
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Motor A/C Comp Drive | 2028-11-02 | 2028-11-02 | 2 hrs | FY29 | 2 | 90030714 | A1 | 1000357517 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-AIRC1-ACONM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-AIRC1-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Motor A/C Comp Drive | 2028-11-02 | 2028-11-02 | 2 hrs | FY29 | 2 | 90030714 | A1 | 1000357518 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-AIRC2-ACONM | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-AIRC2-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Tank Module | 2028-11-02 | 2028-11-03 | 36 hrs | FY29 | 84 | 90030313 | A1 | 1000357493 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-STRUCT-HDTNK | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-HDTNK90030313
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Boom Module Quarter Life | 2028-11-02 | 2028-11-03 | 30 hrs | FY29 | 48 | 90029992 | A1 | 1000357492 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS90029992
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Service Module Hosing | 2028-11-02 | 2028-11-02 | 12 hrs | FY29 | 24 | 90029982 | A1 | 1000357486 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-STRUCT-SRVCT | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-SRVCT90029982
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Service Arm Locking Cyl | 2028-11-02 | 2028-11-02 | 12 hrs | FY29 | 20 | 90029983 | A1 | 1000357487 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-STRUCT-SRVCT | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-SRVCT90029983
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Bucket Assembly | 2028-11-02 | 2028-11-04 | 42 hrs | FY29 | 78 | 90029975 | A1 | 1000357477 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-STRUCT-BUCKT | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-STRUCT-BUCKT90029975
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Auto Lube Pump P1 | 2028-11-02 | 2028-11-02 | 2 hrs | FY29 | 2 | 90030312 | A1 | 1000357435 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBPP | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBPP90030312
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Auto Lube Pump P3 | 2028-11-02 | 2028-11-02 | 2 hrs | FY29 | 2 | 90035351 | A1 | 1000358642 | 02.11.2028 | 10000 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBP3 | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBP390035351
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Air Compressor Unit | 2028-11-02 | 2028-11-02 | 9 hrs | FY29 | 9 | 90030086 | A1 | 1000357496 | 02.11.2028 | 20000 | CLB-MP-EXCV-EX7148-PNEUMC-COMPR | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-PNEUMC-COMPR90030086
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Auto Lube Pump Superstructure | 2028-11-02 | 2028-11-02 | 12 hrs | FY29 | 12 | 90018988 | 1 | 1000190276 | 02.11.2028 | 6000 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP90018988
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Grease Tank Level Valve | 2028-11-06 | 2028-11-06 | 2 hrs | FY29 | 2 | 90015003 | A1 | 1000337280 | 06.11.2028 | 12 Monthly | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK90015003
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Adjust 4500hr Valve Set | 2028-11-06 | 2028-11-06 | 10 hrs | FY29 | 20 | 90017923 | A1 | 1000158812 | 06.11.2028 | 4500 | CLB-MP-EXCV-EX014 -RHENGN | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -RHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Travel LHF | 2028-11-09 | 2028-11-09 | 8 hrs | FY29 | 14 | 90027506 | A1 | 1000297358 | 09.11.2028 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLF | 6700 | 16452 | 8735 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLF90027506
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Inspection Ext Static Line | 2028-11-09 | 2028-11-09 | 4 hrs | FY29 | 4 | 90029897 | A1 | 1000304563 | 09.11.2028 | 6 Monthly | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029897
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Inspection Isolator Panel | 2028-11-11 | 2028-11-11 | 2 hrs | FY29 | 2 | 90029980 | 1 | 1000304631 | 11.11.2028 | 12 Monthly | CLB-MP-EXCV-EX7133-ELCTLV |  |  |  | CLB-MP-EXCV-EX7133-ELCTLV90029980
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Grease Tank Level Valve | 2028-11-11 | 2028-11-11 | 2 hrs | FY29 | 2 | 90029942 | A1 | 1000304596 | 11.11.2028 | 12 Monthly | CLB-MP-EXCV-EX7133-GRSYST |  |  |  | CLB-MP-EXCV-EX7133-GRSYST90029942
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Grease Tank Level Valve | 2028-11-13 | 2028-11-13 | 2 hrs | FY29 | 2 | 90015003 | A1 | 1000340303 | 13.11.2028 | 12 Monthly | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK | 6200 | 9369 | 2810 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK90015003
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Servo Hoses Cascade to Bulkhead | 2028-11-16 | 2028-11-16 | 8 hrs | FY29 | 16 | 90009478 | 1 | 1000158873 | 16.11.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHBLK | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHBLK90009478
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Pos3 & Pos4 | 2028-11-16 | 2028-11-17 | 26 hrs | FY29 | 42 | 90003163 | A1 | 1000158829 | 16.11.2028 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP3P4 | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP3P490003163
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Power Pack Module Qtr Life | 2028-11-17 | 2028-11-17 | 7 hrs | FY29 | 13 | 90031021 | A1 | 1000340290 | 17.11.2028 | 5000 | CLB-MP-EXCV-EX7138-ENGINE | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-ENGINE90031021
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Grease System Audit | 2028-11-17 | 2028-11-18 | 24 hrs | FY29 | 36 | 90030748 | A1 | 1000340300 | 17.11.2028 | 5000 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ90030748
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Ovhl 24M Air Conditioner Sys1 Eng | 2028-11-17 | 2028-11-19 | 48 hrs | FY29 | 48 | 90035243 | A1 | 1000359810 | 17.11.2028 | 24 Monthly | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC1 | 6000 | 3940 | 3940 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC190035243
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Ovhl 24M Air Conditioner Sys2 Hyd | 2028-11-17 | 2028-11-18 | 36 hrs | FY29 | 36 | 90035267 | A1 | 1000359812 | 17.11.2028 | 24 Monthly | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC290035267
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Inspection Ext Static Line | 2028-11-17 | 2028-11-17 | 4 hrs | FY29 | 4 | 90029897 | A1 | 1000359517 | 17.11.2028 | 6 Monthly | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029897
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Pump Case Drain Hoses | 2028-11-17 | 2028-11-17 | 8 hrs | FY29 | 16 | 90022729 | A1 | 1000237186 | 17.11.2028 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HPCDL | 6700 | 27054 | 14526 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HPCDL90022729
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Minestar Harness | 2028-11-18 | 2028-11-19 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000312852 | 18.11.2028 | 4000 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC90031708
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Grease Block & Injectors | 2028-11-19 | 2028-11-21 | 48 hrs | FY29 | 84 | 90029933 | A1 | 1000357443 | 19.11.2028 | 20000 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ90029933
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cylinder Bucket LH | 2028-11-19 | 2028-11-20 | 26 hrs | FY29 | 32 | 90003169 | A1 | 1000158840 | 19.11.2028 | 10000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYL | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYL90003169
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Hydraulic Oil Replacement | 2028-11-20 | 2028-11-20 | 12 hrs | FY29 | 12 | 90016793 | 1 | 1000284650 | 20.11.2028 | 6000 | CLB-MP-EXCV-EX7124-HYDSYS | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Hydraulic System Tune Up | 2028-11-20 | 2028-11-20 | 12 hrs | FY29 | 24 | 90017865 | 1 | 1000284660 | 20.11.2028 | 6000 | CLB-MP-EXCV-EX7124-HYDSYS | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Swing Circuit Hoses | 2028-11-20 | 2028-11-20 | 8 hrs | FY29 | 16 | 90027576 | A1 | 1000284642 | 20.11.2028 | 9000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWCRT | 6700 | 19559 | 2589 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWCRT90027576
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2028-11-20 | 2028-11-20 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000337317 | 20.11.2028 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cyl Boom LH | 2028-11-21 | 2028-11-25 | 90 hrs | FY29 | 138 | 90027497 | A1 | 1000284605 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BMCYL | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BMCYL90027497
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cyl Boom RH | 2028-11-21 | 2028-11-25 | 90 hrs | FY29 | 138 | 90027497 | A1 | 1000284606 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BMCYR | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BMCYR90027497
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Oil Suction Hoses | 2028-11-21 | 2028-11-22 | 24 hrs | FY29 | 48 | 90027568 | A1 | 1000284635 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-OILSC | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-OILSC90027568
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl PTO Cooling Hoses | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 12 | 90027569 | A1 | 1000284636 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-PTOCL | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-PTOCL90027569
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Fan Hyd Cool Front | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 12 | 90027504 | A1 | 1000284617 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMCHF | 6700 | 19559 | 3275 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMCHF90027504
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Fan Hyd Cool Rear | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 12 | 90027504 | A1 | 1000284618 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMCHR | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMCHR90027504
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Fan Engine Cool LH | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 18 | 90027505 | A1 | 1000284619 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMECL | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMECL90027505
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Fan Engine Cool RH | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 18 | 90027505 | A1 | 1000284620 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMECR | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMECR90027505
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Fan Engine Cool LH | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 12 | 90027494 | A1 | 1000284599 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HECPL | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HECPL90027494
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Fan Engine Cool RH | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 12 | 90027494 | A1 | 1000284600 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HECPR | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HECPR90027494
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Pump Drive Gearbox LH | 2028-11-21 | 2028-11-22 | 40 hrs | FY29 | 116 | 90027489 | A1 | 1000284591 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-PPDRL | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-PPDRL90027489
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Pump Drive Gearbox RH | 2028-11-21 | 2028-11-22 | 40 hrs | FY29 | 116 | 90027489 | A1 | 1000284592 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-HYDSYS-PPDRR | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-HYDSYS-PPDRR90027489
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Radiator LH Engine Cooling | 2028-11-21 | 2028-11-21 | 12 hrs | FY29 | 12 | 90027552 | A1 | 1000284518 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-RADTR | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-RADTR90027552
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl LH Aftercooler | 2028-11-21 | 2028-11-21 | 12 hrs | FY29 | 24 | 90023361 | A1 | 1000309252 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-AFTER | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-AFTER90023361
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Radiator RH Engine Cooling | 2028-11-21 | 2028-11-21 | 12 hrs | FY29 | 12 | 90027553 | A1 | 1000284584 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-RADTR | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-RADTR90027553
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl RH Aftercooler | 2028-11-21 | 2028-11-21 | 12 hrs | FY29 | 24 | 90023360 | A1 | 1000309253 | 21.11.2028 | 18000 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-AFTER | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-AFTER90023360
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Hose Bucket Cyl | 2028-11-22 | 2028-11-23 | 18 hrs | FY29 | 54 | 90030738 | A1 | 1000337253 | 22.11.2028 | 8000 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBKCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBKCL90030738
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Hose Boom Cyl | 2028-11-22 | 2028-11-22 | 8 hrs | FY29 | 24 | 90030735 | A1 | 1000337252 | 22.11.2028 | 8000 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBMCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBMCL90030735
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Hyd Hose Stick Cyl | 2028-11-22 | 2028-11-22 | 12 hrs | FY29 | 24 | 90030737 | A1 | 1000337254 | 22.11.2028 | 8000 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HSTCL | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HSTCL90030737
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Bucket LH | 2028-11-22 | 2028-11-23 | 26 hrs | FY29 | 32 | 90022647 | A1 | 1000237031 | 22.11.2028 | 10000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYL | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYL90022647
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Adjust 4500hr Valve Set | 2028-11-22 | 2028-11-22 | 10 hrs | FY29 | 20 | 90022679 | A1 | 1000237135 | 22.11.2028 | 4500 | CLB-MP-EXCV-EX7119-RHENGN | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-RHENGN90022679
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2028-11-22 | 2028-11-22 | 4 hrs | FY29 | 4 | 90022746 | A1 | 1000237212 | 22.11.2028 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Track Tension Tuning-Adjust | 2028-11-23 | 2028-11-23 | 3 hrs | FY29 | 9 | 90020545 | A1 | 1000340343 | 23.11.2028 | 6 Monthly | CLB-MP-EXCV-EX7138-UNDERC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2028-11-23 | 2028-11-23 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000348588 | 23.11.2028 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2028-11-23 | 2028-11-23 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000330578 | 23.11.2028 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Minestar Harness | 2028-11-24 | 2028-11-25 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370302 | 24.11.2028 | 4000 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Wiper Blades | 2028-11-25 | 2028-11-25 | 2 hrs | FY29 | 2 | 90004684 | 1 | 1000163162 | 25.11.2028 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX014 -STRUCT-CABIN90004684
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Batteries | 2028-11-28 | 2028-11-28 | 5 hrs | FY29 | 9 | 90017122 | A1 | 1000337269 | 28.11.2028 | 12 Monthly | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST | 6200 | 10954 | 3519 | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST90017122
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Track Tension Tuning-Adjust | 2028-12-01 | 2028-12-01 | 3 hrs | FY29 | 9 | 90029977 | A1 | 1000359587 | 01.12.2028 | 6 Monthly | CLB-MP-EXCV-EX7149-UNDERC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-UNDERC90029977
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Fan Hyd Cool Front | 2028-12-04 | 2028-12-04 | 6 hrs | FY29 | 12 | 90003176 | A1 | 1000158848 | 04.12.2028 | 18000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMCHF | 6700 | 42775 | 1744 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMCHF90003176
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Wiper Blades | 2028-12-06 | 2028-12-06 | 1 hr | FY29 | 1 | 90027557 | A1 | 1000297393 | 06.12.2028 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7122-STRUCT-CABIN90027557
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Rotor to Drive Motor Hoses | 2028-12-06 | 2028-12-07 | 20 hrs | FY29 | 40 | 90027570 | A1 | 1000284637 | 06.12.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCDMH | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCDMH90027570
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 2nd Speed Trvl Brake Release Hose | 2028-12-06 | 2028-12-06 | 5 hrs | FY29 | 10 | 90027559 | A1 | 1000284627 | 06.12.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SSTBR | 6700 | 19559 | 8190 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SSTBR90027559
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Swing Motor Case Drain Hoses | 2028-12-06 | 2028-12-06 | 6 hrs | FY29 | 12 | 90027577 | A1 | 1000284643 | 06.12.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWMCD | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWMCD90027577
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Travel Motor Case Drain Hoses | 2028-12-06 | 2028-12-06 | 5 hrs | FY29 | 10 | 90027578 | A1 | 1000284644 | 06.12.2028 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TMCDH | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TMCDH90027578
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Minestar Harness | 2028-12-07 | 2028-12-08 | 27.5 hrs | FY29 | 43.5 | 90029998 | A1 | 1000357494 | 07.12.2028 | 4000 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC90029998
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Emergency Ladder | 2028-12-10 | 2028-12-10 | 3 hrs | FY29 | 6 | 90022513 | 1 | 1000309303 | 10.12.2028 | 24 Monthly | CLB-MP-EXCV-EX7122-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7122-STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Pump Case Drain Hoses | 2028-12-11 | 2028-12-11 | 8 hrs | FY29 | 16 | 90022729 | A1 | 1000345669 | 11.12.2028 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HPCDL | 6700 | 25948 | 13851 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HPCDL90022729
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Fan Engine Cool LH | 2028-12-12 | 2028-12-12 | 6 hrs | FY29 | 18 | 90022656 | A1 | 1000237041 | 12.12.2028 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECL | 6700 | 25972 | 18775 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECL90022656
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Emergency Ladder | 2028-12-13 | 2028-12-13 | 3 hrs | FY29 | 6 | 90022513 | 1 | 1000235857 | 13.12.2028 | 24 Monthly | CLB-MP-EXCV-EX014 -STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX014 -STRUCT-STLAD-SLFXD90022513
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl HV Motor Coupling | 2028-12-14 | 2028-12-15 | 20 hrs | FY29 | 30 | 90030128 | A1 | 1000359619 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-ELCTHV-HVMOT-COUPL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-ELCTHV-HVMOT-COUPL90030128
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Gearbox Swing P1 | 2028-12-14 | 2028-12-16 | 55 hrs | FY29 | 109 | 90029900 | A1 | 1000359520 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-SWGSYS-SWBOX-SGBPF | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-SWGSYS-SWBOX-SGBPF90029900
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Gearbox Swing P2 | 2028-12-14 | 2028-12-16 | 55 hrs | FY29 | 109 | 90029900 | A1 | 1000359521 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-SWGSYS-SWBOX-SGBPR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-SWGSYS-SWBOX-SGBPR90029900
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Pump Drive/Splitter Gearbox | 2028-12-14 | 2028-12-19 | 120 hrs | FY29 | 240 | 90030087 | A1 | 1000359602 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-PMPDR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-PMPDR90030087
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Pump Hyd Work Pos1 & Pos2 | 2028-12-14 | 2028-12-15 | 36 hrs | FY29 | 54 | 90030234 | A1 | 1000359603 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-WPPP1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-WPPP190030234
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Pump Hyd Work Pos3 & Pos4 | 2028-12-14 | 2028-12-15 | 36 hrs | FY29 | 54 | 90030286 | A1 | 1000359611 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-WPPP2 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-WPPP290030286
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Pump Swing Combination | 2028-12-14 | 2028-12-15 | 24 hrs | FY29 | 36 | 90030252 | A1 | 1000359604 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SWPP1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SWPP190030252
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Pump Fan Hyd Oil Cooler | 2028-12-14 | 2028-12-15 | 24 hrs | FY29 | 36 | 90030278 | A1 | 1000359605 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-HECP1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-HECP190030278
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Pump Servo Bearing Lube | 2028-12-14 | 2028-12-14 | 4 hrs | FY29 | 4 | 90030280 | A1 | 1000359606 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SVPP1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SVPP190030280
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Lube Pump Splitter Gear Box | 2028-12-14 | 2028-12-14 | 4 hrs | FY29 | 4 | 90030281 | A1 | 1000359607 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-PTOLU | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-PTOLU90030281
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Pump Oil Replenishing | 2028-12-14 | 2028-12-14 | 4 hrs | FY29 | 4 | 90030285 | A1 | 1000359608 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-RPPP1 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-RPPP190030285
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Ladder Raise Cylinder | 2028-12-14 | 2028-12-14 | 3 hrs | FY29 | 6 | 90030320 | A1 | 1000359614 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-LACYL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-LACYL90030320
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Bucket LH Lift | 2028-12-14 | 2028-12-15 | 30 hrs | FY29 | 54 | 90029964 | A1 | 1000359579 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYL90029964
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Cyl Bucket RH Lift | 2028-12-14 | 2028-12-15 | 30 hrs | FY29 | 54 | 90029967 | A1 | 1000359580 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYR90029967
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Rotary Connection | 2028-12-14 | 2028-12-16 | 48 hrs | FY29 | 72 | 90029901 | A1 | 1000359522 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-ROTRY | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-ROTRY90029901
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Vlve Bank Module Quarter Life | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 12 | 90029987 | A1 | 1000359594 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVLU | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVLU90029987
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Valve Pressure Reducing Y3 | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 6 | 90030294 | A1 | 1000359613 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPRV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPRV90030294
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Valve pressure Limiting Y4 | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 6 | 90030321 | A1 | 1000359612 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPLV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPLV90030321
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Motor Swing Front | 2028-12-14 | 2028-12-15 | 18 hrs | FY29 | 26 | 90029905 | A1 | 1000359524 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-SWMOF | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-SWMOF90029905
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Motor Swing Rear | 2028-12-14 | 2028-12-15 | 18 hrs | FY29 | 26 | 90029905 | A1 | 1000359523 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-SWMOR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-SWMOR90029905
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Motor Travel LHF | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000359525 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMLF | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMLF90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Motor Travel LHR | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000359526 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMLR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMLR90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Motor Travel RHF | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000359527 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMRF | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMRF90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Motor Travel RHR | 2028-12-14 | 2028-12-14 | 6 hrs | FY29 | 10 | 90029906 | A1 | 1000359528 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMRR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMRR90029906
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Accumulator Track Hyd LH | 2028-12-14 | 2028-12-14 | 3 hrs | FY29 | 3 | 90029907 | A1 | 1000359529 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCL90029907
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Accumulator Track Hyd RH | 2028-12-14 | 2028-12-14 | 3 hrs | FY29 | 3 | 90029907 | A1 | 1000359530 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCR90029907
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Accumulator Servo Hyd | 2028-12-14 | 2028-12-14 | 3 hrs | FY29 | 3 | 90030487 | A1 | 1000359595 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCS90030487
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Accumulator Ladder Hyd | 2028-12-14 | 2028-12-14 | 4 hrs | FY29 | 4 | 90030685 | A1 | 1000359621 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCB | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCB90030685
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Track Tensioning Hoses | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 24 | 90030538 | A1 | 1000359620 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HHTTL | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HHTTL90030538
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hyd Hose Work Pumps to Valves | 2028-12-14 | 2028-12-14 | 10.5 hrs | FY29 | 10.5 | 90030287 | A1 | 1000359609 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HWPVV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HWPVV90030287
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hyd Hose Swing Pump Swing Motor | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 24 | 90030288 | A1 | 1000359610 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSPSM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSPSM90030288
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hyd Hose Rotary Con to Valve Bank | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 24 | 90029912 | A1 | 1000359534 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCVV | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCVV90029912
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Hoses Rotary Conn to Travel Motor | 2028-12-14 | 2028-12-15 | 24 hrs | FY29 | 48 | 90029914 | A1 | 1000359535 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCTM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCTM90029914
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Operators Seat | 2028-12-14 | 2028-12-14 | 9 hrs | FY29 | 17 | 90029915 | A1 | 1000359536 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-CABIN-SEATO | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-CABIN-SEATO90029915
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Motor A/C Comp Drive | 2028-12-14 | 2028-12-14 | 2 hrs | FY29 | 2 | 90030714 | A1 | 1000359622 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-AIRC1-ACONM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC1-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Motor A/C Comp Drive | 2028-12-14 | 2028-12-14 | 2 hrs | FY29 | 2 | 90030714 | A1 | 1000359623 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-AIRC2-ACONM | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-AIRC2-ACONM90030714
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Hyd Tank Module | 2028-12-14 | 2028-12-15 | 36 hrs | FY29 | 84 | 90030313 | A1 | 1000359598 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-STRUCT-HDTNK | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-HDTNK90030313
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Boom Module Quarter Life | 2028-12-14 | 2028-12-15 | 30 hrs | FY29 | 48 | 90029992 | A1 | 1000359597 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS90029992
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Service Module Hosing | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 24 | 90029982 | A1 | 1000359591 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-STRUCT-SRVCT | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-SRVCT90029982
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Service Arm Locking Cyl | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 20 | 90029983 | A1 | 1000359592 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-STRUCT-SRVCT | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-SRVCT90029983
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Bucket Assembly | 2028-12-14 | 2028-12-16 | 42 hrs | FY29 | 78 | 90029975 | A1 | 1000359582 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-STRUCT-BUCKT | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-STRUCT-BUCKT90029975
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Auto Lube Pump P1 | 2028-12-14 | 2028-12-14 | 2 hrs | FY29 | 2 | 90030312 | A1 | 1000359540 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBPP | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBPP90030312
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Auto Lube Pump P3 | 2028-12-14 | 2028-12-14 | 2 hrs | FY29 | 2 | 90035351 | A1 | 1000369281 | 14.12.2028 | 10000 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBP3 | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBP390035351
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Grease Block & Injectors | 2028-12-14 | 2028-12-16 | 48 hrs | FY29 | 84 | 90029933 | A1 | 1000359548 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ90029933
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Air Compressor Unit | 2028-12-14 | 2028-12-14 | 9 hrs | FY29 | 9 | 90030086 | A1 | 1000359601 | 14.12.2028 | 20000 | CLB-MP-EXCV-EX7149-PNEUMC-COMPR | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-PNEUMC-COMPR90030086
R9400E | Onsite PM | Excavators | Fortescue | EX7149 | EX7149 Repl Minestar Harness | 2028-12-14 | 2028-12-15 | 27.5 hrs | FY29 | 43.5 | 90029998 | A1 | 1000359599 | 14.12.2028 | 4000 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC | 6200 | 5321 | 5321 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC90029998
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Batteries | 2028-12-16 | 2028-12-16 | 4 hrs | FY29 | 4 | 90027525 | A1 | 1000284651 | 16.12.2028 | 10000 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-BATTY | 6700 | 19559 | 4086 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-BATTY90027525
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Track Tensioner LH | 2028-12-17 | 2028-12-17 | 12 hrs | FY29 | 24 | 90027527 | A1 | 1000284652 | 17.12.2028 | 18000 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-TENSR | 6700 | 19559 | 2055 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-TENSR90027527
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Track Tensioner RH | 2028-12-17 | 2028-12-17 | 12 hrs | FY29 | 24 | 90027527 | A1 | 1000284653 | 17.12.2028 | 18000 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-TENSR | 6700 | 19559 | 2055 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-TENSR90027527
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Minestar Harness | 2028-12-17 | 2028-12-18 | 27.5 hrs | FY29 | 43.5 | 90030746 | A1 | 1000330543 | 17.12.2028 | 5000 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC | 6200 | 11792 | 5210 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC90030746
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Batteries | 2028-12-22 | 2028-12-22 | 5 hrs | FY29 | 9 | 90017122 | A1 | 1000348540 | 22.12.2028 | 12 Monthly | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST | 6200 | 8353 | 3485 | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST90017122
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Swing Circuit Hoses | 2028-12-22 | 2028-12-22 | 8 hrs | FY29 | 16 | 90009481 | 1 | 1000158876 | 22.12.2028 | 9000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWCRT | 6700 | 42775 | 368 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWCRT90009481
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Minestar Harness | 2028-12-26 | 2028-12-27 | 27.5 hrs | FY29 | 43.5 | 90029998 | A1 | 1000304641 | 26.12.2028 | 4000 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC90029998
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 12M Inspection Isolator Panel | 2028-12-29 | 2028-12-29 | 2 hrs | FY29 | 2 | 90022525 | A2 | 1000315896 | 29.12.2028 | 12 Monthly | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | 6200 | 9369 | 1820 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST90022525
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Fan Engine Cool LH | 2028-12-30 | 2028-12-30 | 6 hrs | FY29 | 18 | 90022656 | A1 | 1000237172 | 30.12.2028 | 18000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMECL | 6700 | 27054 | 1722 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMECL90022656
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Batteries | 2028-12-31 | 2028-12-31 | 8 hrs | FY29 | 8 | 90022665 | A1 | 1000237204 | 31.12.2028 | 10000 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-BATTY | 6700 | 27054 | 3710 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-BATTY90022665
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Hydraulic System Tune Up | 2028-12-31 | 2028-12-31 | 12 hrs | FY29 | 24 | 90022669 | A1 | 1000237214 | 31.12.2028 | 6000 | CLB-MP-EXCV-EX7119-HYDSYS | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS90022669
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Hydraulic Oil Replacement | 2029-01-01 | 2029-01-01 | 12 hrs | FY29 | 12 | 90022667 | A1 | 1000237203 | 01.01.2029 | 6000 | CLB-MP-EXCV-EX7119-HYDSYS | 6700 | 27054 | 322 | CLB-MP-EXCV-EX7119-HYDSYS90022667
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Gearbox Swing LHR | 2029-01-09 | 2029-01-11 | 48 hrs | FY29 | 80 | 90012369 | 1 | 1000158819 | 09.01.2029 | 20000 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBLR | 6700 | 42775 | 3088 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBLR90012369
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Gearbox Swing RHR | 2029-01-09 | 2029-01-11 | 48 hrs | FY29 | 80 | 90012369 | 1 | 1000158821 | 09.01.2029 | 20000 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBRR | 6700 | 42775 | 3088 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBRR90012369
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Operators Seat | 2029-01-12 | 2029-01-12 | 2 hrs | FY29 | 2 | 90003180 | A1 | 1000207129 | 12.01.2029 | 10000 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-SEATS | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-SEATS90003180
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Control Valve Block LH | 2029-01-15 | 2029-01-16 | 34 hrs | FY29 | 50 | 90027502 | A1 | 1000284646 | 15.01.2029 | 36000 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-MCVVL | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-MCVVL90027502
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Control Valve Block RH | 2029-01-15 | 2029-01-16 | 34 hrs | FY29 | 50 | 90027502 | A1 | 1000284647 | 15.01.2029 | 36000 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-MCVVR | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-MCVVR90027502
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Engine Cat C32 LH | 2029-01-15 | 2029-01-22 | 176.5 hrs | FY29 | 254.5 | 90027533 | A1 | 1000284514 | 15.01.2029 | 18000 | CLB-MP-EXCV-EX7124-LHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-LHENGN90027533
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Engine Cat C32 RH | 2029-01-15 | 2029-01-22 | 176.5 hrs | FY29 | 254.5 | 90027534 | A1 | 1000284580 | 15.01.2029 | 18000 | CLB-MP-EXCV-EX7124-RHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-RHENGN90027534
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Boom Assy Dressed | 2029-01-15 | 2029-01-20 | 116 hrs | FY29 | 324 | 90031798 | A1 | 1000314059 | 15.01.2029 | 36000 | CLB-MP-EXCV-EX7124-STRUCT-BOOMS | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-STRUCT-BOOMS90031798
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Stick Assy Dressed | 2029-01-15 | 2029-01-19 | 96 hrs | FY29 | 192 | 90031801 | A1 | 1000314255 | 15.01.2029 | 36000 | CLB-MP-EXCV-EX7124-STRUCT-STICK | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-STRUCT-STICK90031801
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Batteries | 2029-01-15 | 2029-01-15 | 8 hrs | FY29 | 8 | 90016788 | 1 | 1000207154 | 15.01.2029 | 10000 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-BATTY | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-BATTY90016788
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Bucket RH | 2029-01-15 | 2029-01-16 | 26 hrs | FY29 | 32 | 90003169 | A1 | 1000207113 | 15.01.2029 | 10000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYR | 6700 | 31524 | 3374 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYR90003169
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hyd Hose Work Pumps to Valves | 2029-01-16 | 2029-01-16 | 10.5 hrs | FY29 | 10.5 | 90030287 | A1 | 1000304651 | 16.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HWPVV | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HWPVV90030287
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hyd Hose Swing Pump Swing Motor | 2029-01-16 | 2029-01-16 | 12 hrs | FY29 | 24 | 90030288 | A1 | 1000304652 | 16.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSPSM | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSPSM90030288
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Operators Seat | 2029-01-16 | 2029-01-16 | 9 hrs | FY29 | 17 | 90029915 | A1 | 1000304582 | 16.01.2029 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-CABIN-SEATO | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-STRUCT-CABIN-SEATO90029915
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Hydraulic System Tune Up | 2029-01-16 | 2029-01-16 | 12 hrs | FY29 | 24 | 90022669 | A1 | 1000237083 | 16.01.2029 | 6000 | CLB-MP-EXCV-EX7118-HYDSYS | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS90022669
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Cylinder Stick LH | 2029-01-16 | 2029-01-17 | 30 hrs | FY29 | 54 | 90022646 | A1 | 1000237029 | 16.01.2029 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLL | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLL90022646
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Repl Minestar Harness | 2029-01-19 | 2029-01-20 | 27.5 hrs | FY29 | 43.5 | 90030746 | A1 | 1000337282 | 19.01.2029 | 5000 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC90030746
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Gearbox Swing P2 | 2029-01-20 | 2029-01-22 | 55 hrs | FY29 | 109 | 90029900 | A1 | 1000304567 | 20.01.2029 | 20000 | CLB-MP-EXCV-EX7133-SWGSYS-SWBOX-SGBPR | 6200 | 13908 | 4720 | CLB-MP-EXCV-EX7133-SWGSYS-SWBOX-SGBPR90029900
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Vlve Bank Module Quarter Life | 2029-01-20 | 2029-01-20 | 6 hrs | FY29 | 12 | 90029987 | A1 | 1000304636 | 20.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVLU | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVLU90029987
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Valve pressure Limiting Y4 | 2029-01-20 | 2029-01-20 | 6 hrs | FY29 | 6 | 90030321 | A1 | 1000304654 | 20.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPLV | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPLV90030321
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Accumulator Servo Hyd | 2029-01-20 | 2029-01-20 | 3 hrs | FY29 | 3 | 90030487 | A1 | 1000304637 | 20.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC90030487
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Accumulator Ladder Hyd | 2029-01-20 | 2029-01-20 | 4 hrs | FY29 | 4 | 90030685 | A1 | 1000305744 | 20.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC90030685
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hyd Hose Rotary Con to Valve Bank | 2029-01-20 | 2029-01-20 | 12 hrs | FY29 | 24 | 90029912 | A1 | 1000304580 | 20.01.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCVV | 6200 | 13908 | 4795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCVV90029912
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Cyl Bucket LH Lift | 2029-01-20 | 2029-01-21 | 30 hrs | FY29 | 54 | 90030725 | A1 | 1000330534 | 20.01.2029 | 10000 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYL | 6200 | 11792 | 4733 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYL90030725
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Minestar Harness | 2029-01-23 | 2029-01-24 | 27.5 hrs | FY29 | 43.5 | 90030746 | A1 | 1000340305 | 23.01.2029 | 5000 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC90030746
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Air Compressor Unit | 2029-01-24 | 2029-01-24 | 9 hrs | FY29 | 9 | 90030086 | A1 | 1000304643 | 24.01.2029 | 20000 | CLB-MP-EXCV-EX7133-PNEUMC-COMPR | 6200 | 13908 | 4700 | CLB-MP-EXCV-EX7133-PNEUMC-COMPR90030086
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Servo Hoses Cascade to Bulkhead | 2029-01-27 | 2029-01-27 | 8 hrs | FY29 | 16 | 90009478 | 1 | 1000207142 | 27.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHBLK | 6700 | 31524 | 19618 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHBLK90009478
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel RHR | 2029-01-27 | 2029-01-27 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000207127 | 27.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRR | 6700 | 31524 | 20738 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRR90022657
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 12M Hydraulic Service & Repairs | 2029-01-28 | 2029-01-29 | 18 hrs | FY29 | 30 | 90014448 | A1 | 1000336836 | 28.01.2029 | 12 Monthly | CLB-MP-EXCV-EX7140-HYDSYS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Oil Suction Hoses | 2029-01-28 | 2029-01-29 | 24 hrs | FY29 | 48 | 90022731 | A1 | 1000345671 | 28.01.2029 | 18000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-OILSC | 6700 | 25972 | 966 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-OILSC90022731
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Stick LH | 2029-01-29 | 2029-01-30 | 30 hrs | FY29 | 54 | 90027498 | A1 | 1000284607 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLL | 6700 | 19559 | 7278 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLL90027498
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Stick RH | 2029-01-29 | 2029-01-30 | 30 hrs | FY29 | 54 | 90027498 | A1 | 1000284608 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLR | 6700 | 19559 | 7304 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLR90027498
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Servo Hoses Cascade to Trvl Valve | 2029-01-29 | 2029-01-29 | 6 hrs | FY29 | 12 | 90022737 | A1 | 1000207144 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHTRV | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHTRV90022737
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Swing Motor Case Drain Hoses | 2029-01-29 | 2029-01-29 | 6 hrs | FY29 | 12 | 90022739 | A1 | 1000207146 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWMCD | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Oil Cooler Front | 2029-01-29 | 2029-01-30 | 36 hrs | FY29 | 48 | 90003170 | A1 | 1000207114 | 29.01.2029 | 24000 | CLB-MP-EXCV-EX7112-HYDSYS-HDOCO-OCHYF | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HDOCO-OCHYF90003170
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Oil Cooler Rear | 2029-01-29 | 2029-01-30 | 36 hrs | FY29 | 48 | 90003170 | A1 | 1000207115 | 29.01.2029 | 24000 | CLB-MP-EXCV-EX7112-HYDSYS-HDOCO-OCHYR | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HDOCO-OCHYR90003170
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos1 | 2029-01-29 | 2029-01-31 | 42 hrs | FY29 | 54 | 90003162 | A1 | 1000207096 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP1 | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP190003162
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos2 | 2029-01-29 | 2029-01-31 | 42 hrs | FY29 | 54 | 90003162 | A1 | 1000207097 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP2 | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP290003162
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Replenish LH | 2029-01-29 | 2029-01-29 | 2 hrs | FY29 | 2 | 90022643 | A1 | 1000207106 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPL | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPL90022643
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Replenish RH | 2029-01-29 | 2029-01-29 | 2 hrs | FY29 | 2 | 90022643 | A1 | 1000207107 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPR | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPR90022643
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Pump Servo LH | 2029-01-29 | 2029-01-29 | 2 hrs | FY29 | 2 | 90010935 | 1 | 1000207104 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPL | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPL90010935
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Pump Servo RH | 2029-01-29 | 2029-01-29 | 2 hrs | FY29 | 2 | 90010935 | 1 | 1000207105 | 29.01.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPR | 6700 | 31524 | 7104 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPR90010935
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Adjust 4500hr Valve Set | 2029-01-31 | 2029-01-31 | 10 hrs | FY29 | 20 | 90022679 | A1 | 1000237004 | 31.01.2029 | 4500 | CLB-MP-EXCV-EX7118-RHENGN | 6700 | 25972 | 14409 | CLB-MP-EXCV-EX7118-RHENGN90022679
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl 24V Batteries | 2029-02-01 | 2029-02-01 | 5 hrs | FY29 | 9 | 90029978 | A1 | 1000304630 | 01.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST | 6200 | 13908 | 8694 | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST90029978
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Idler Track LH | 2029-02-03 | 2029-02-03 | 6 hrs | FY29 | 18 | 90003189 | A1 | 1000231309 | 03.02.2029 | 1500 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-IDLLH | 470 | 3415 | 2018 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-IDLLH90003189
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2029-02-04 | 2029-02-04 | 4 hrs | FY29 | 4 | 90022746 | A1 | 1000237081 | 04.02.2029 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Batteries | 2029-02-07 | 2029-02-07 | 5 hrs | FY29 | 9 | 90017122 | A1 | 1000340292 | 07.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | 6200 | 9369 | 1820 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST90017122
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Cylinder Bucket LH | 2029-02-07 | 2029-02-08 | 30 hrs | FY29 | 54 | 90029964 | A1 | 1000304623 | 07.02.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYL | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYL90029964
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Tensioning Hoses | 2029-02-07 | 2029-02-07 | 12 hrs | FY29 | 24 | 90030538 | A1 | 1000304722 | 07.02.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HHTTL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HHTTL90030538
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Hoses Rotary Conn to Travel Motor | 2029-02-07 | 2029-02-08 | 24 hrs | FY29 | 48 | 90029914 | A1 | 1000304581 | 07.02.2029 | 10000 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCTM | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCTM90029914
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Motor ACon Comp Drive | 2029-02-07 | 2029-02-07 | 2 hrs | FY29 | 2 | 90030714 | A1 | 1000305909 | 07.02.2029 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-AIRC1 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC190030714
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Grease Injectors | 2029-02-07 | 2029-02-09 | 48 hrs | FY29 | 84 | 90029932 | A1 | 1000304593 | 07.02.2029 | 10000 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ90029932
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Motor ACon Comp Drive | 2029-02-07 | 2029-02-07 | 2 hrs | FY29 | 2 | 90030714 | A1 | 1000305910 | 07.02.2029 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-AIRC2 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC290030714
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 6M Anritsu Test WiFi Cables | 2029-02-10 | 2029-02-10 | 2 hrs | FY29 | 2 | 90020303 | A1 | 1000210997 | 10.02.2029 | 6 Monthly | CLB-MP-EXCV-EX7112-COMMUN-FLMGT |  |  |  | CLB-MP-EXCV-EX7112-COMMUN-FLMGT90020303
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Adjust 500hr Initial Valve Set | 2029-02-11 | 2029-02-11 | 10 hrs | FY29 | 20 | 90027550 | A1 | 1000284515 | 11.02.2029 | 500 | CLB-MP-EXCV-EX7124-LHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-LHENGN90027550
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Adjust 500hr Initial Valve Set | 2029-02-11 | 2029-02-11 | 10 hrs | FY29 | 20 | 90027550 | A1 | 1000284581 | 11.02.2029 | 500 | CLB-MP-EXCV-EX7124-RHENGN | 6700 | 19559 | 2565 | CLB-MP-EXCV-EX7124-RHENGN90027550
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Service Air Conditioner Sys 1 | 2029-02-11 | 2029-02-11 | 12 hrs | FY29 | 12 | 90030498 | A1 | 1000304627 | 11.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7133-STRUCT-AIRC1 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC190030498
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Service Air Conditioner Sys 2 | 2029-02-11 | 2029-02-11 | 12 hrs | FY29 | 12 | 90030536 | A1 | 1000304724 | 11.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7133-STRUCT-AIRC2 | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-AIRC290030536
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Swing Circuit Hoses | 2029-02-12 | 2029-02-12 | 8 hrs | FY29 | 16 | 90027576 | A1 | 1000297379 | 12.02.2029 | 9000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWCRT | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWCRT90027576
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Servo Hoses Cascade to Trvl Valve | 2029-02-15 | 2029-02-15 | 6 hrs | FY29 | 12 | 90022737 | A1 | 1000158875 | 15.02.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHTRV | 6700 | 42775 | 6421 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHTRV90022737
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Adjust 4500hr Valve Set | 2029-02-16 | 2029-02-16 | 10 hrs | FY29 | 20 | 90022679 | A1 | 1000237120 | 16.02.2029 | 4500 | CLB-MP-EXCV-EX7119-LHENGN | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-LHENGN90022679
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Wiper Blades | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 2 | 90022722 | A1 | 1000237209 | 18.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7119-STRUCT-CABIN90022722
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Minestar Harness | 2029-02-20 | 2029-02-21 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000369999 | 20.02.2029 | 4000 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC90031708
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 12M Hydraulic Service & Repairs | 2029-02-22 | 2029-02-23 | 18 hrs | FY29 | 30 | 90014448 | A1 | 1000340261 | 22.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7138-HYDSYS | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service RH | 2029-02-22 | 2029-02-22 | 12 hrs | FY29 | 12 | 90022660 | A1 | 1000237077 | 22.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR | 6700 | 25972 | 6562 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR90022660
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Wiper Blades | 2029-02-23 | 2029-02-23 | 2 hrs | FY29 | 2 | 90022722 | A1 | 1000237078 | 23.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7118-STRUCT-CABIN90022722
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Annual Air Con Service LH | 2029-02-24 | 2029-02-24 | 12 hrs | FY29 | 12 | 90027615 | A1 | 1000297422 | 24.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL90027615
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Annual Air Con Service RH | 2029-02-24 | 2029-02-24 | 12 hrs | FY29 | 12 | 90027615 | A1 | 1000297392 | 24.02.2029 | 12 Monthly | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR | 6700 | 16452 | 10297 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR90027615
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Ovhl 24M Air Conditioner Sys1 Eng | 2029-02-24 | 2029-02-26 | 48 hrs | FY29 | 48 | 90035243 | A1 | 1000359802 | 24.02.2029 | 24 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC1 | 6500 | 1175 | 1175 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC190035243
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Ovhl 24M Air Conditioner Sys2 Hyd | 2029-02-24 | 2029-02-25 | 36 hrs | FY29 | 36 | 90035267 | A1 | 1000359804 | 24.02.2029 | 24 Monthly | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC2 |  |  |  | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC290035267
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Idler Track LH | 2029-02-24 | 2029-02-24 | 6 hrs | FY29 | 18 | 90022658 | A1 | 1000237089 | 24.02.2029 | 1500 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-IDLLH | 470 | 1775 | 30 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-IDLLH90022658
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Idler Track RH | 2029-02-24 | 2029-02-24 | 6 hrs | FY29 | 18 | 90022658 | A1 | 1000237100 | 24.02.2029 | 1500 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-IDLRH | 470 | 1775 | 30 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-IDLRH90022658
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Adjust 4500hr Valve Set | 2029-03-01 | 2029-03-01 | 10 hrs | FY29 | 20 | 90017923 | A1 | 1000158797 | 01.03.2029 | 4500 | CLB-MP-EXCV-EX014 -LHENGN | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -LHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Emergency Ladder | 2029-03-02 | 2029-03-02 | 3 hrs | FY29 | 6 | 90022513 | 1 | 1000307980 | 02.03.2029 | 24 Monthly | CLB-MP-EXCV-EX7124-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7124-STRUCT-STLAD-SLFXD90022513
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 12M Inspection Isolator Panel | 2029-03-04 | 2029-03-04 | 2 hrs | FY29 | 2 | 90022525 | A2 | 1000348387 | 04.03.2029 | 12 Monthly | CLB-MP-EXCV-EX7141-ELCTLV |  |  |  | CLB-MP-EXCV-EX7141-ELCTLV90022525
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hydraulic Cooling Circ Hoses | 2029-03-04 | 2029-03-05 | 18 hrs | FY29 | 36 | 90028476 | A1 | 1000345667 | 04.03.2029 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HCCHH | 6700 | 25972 | 15339 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HCCHH90028476
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Main Hyd Pump Pos4 | 2029-03-08 | 2029-03-10 | 42 hrs | FY29 | 54 | 90003162 | A1 | 1000207099 | 08.03.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP4 | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP490003162
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Pos3 & Pos4 | 2029-03-08 | 2029-03-09 | 26 hrs | FY29 | 42 | 90003163 | A1 | 1000207101 | 08.03.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP3P4 | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP3P490003163
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Assembly LH | 2029-03-09 | 2029-03-09 | 12 hrs | FY29 | 36 | 90029928 | A1 | 1000304589 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-TRKLH | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-TRKLH90029928
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Final Drive LHS | 2029-03-09 | 2029-03-10 | 39 hrs | FY29 | 141 | 90029899 | A1 | 1000304564 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-FDRLH | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-FDRLH90029899
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Sprocket LH | 2029-03-09 | 2029-03-10 | 24 hrs | FY29 | 72 | 90029919 | A1 | 1000304587 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-SPRKL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-SPRKL90029919
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Idler LH | 2029-03-09 | 2029-03-09 | 12 hrs | FY29 | 36 | 90029931 | A1 | 1000304591 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-IDLLH | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-IDLLH90029931
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Hyd Tensioner LH | 2029-03-09 | 2029-03-10 | 26 hrs | FY29 | 74 | 90029917 | A1 | 1000304583 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-TENSL | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-TENSL90029917
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Assembly RH | 2029-03-09 | 2029-03-09 | 12 hrs | FY29 | 36 | 90029928 | A1 | 1000304590 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-TRKRH | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-TRKRH90029928
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Final Drive RHS | 2029-03-09 | 2029-03-10 | 39 hrs | FY29 | 141 | 90029899 | A1 | 1000304565 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-FDRRH | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-FDRRH90029899
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Sprocket RH | 2029-03-09 | 2029-03-10 | 24 hrs | FY29 | 72 | 90029919 | A1 | 1000304588 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-SPRKR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-SPRKR90029919
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Idler RH | 2029-03-09 | 2029-03-09 | 12 hrs | FY29 | 36 | 90029931 | A1 | 1000304592 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-IDLRH | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-IDLRH90029931
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Repl Track Hyd Tensioner RH | 2029-03-09 | 2029-03-10 | 26 hrs | FY29 | 74 | 90029917 | A1 | 1000304584 | 09.03.2029 | 30000 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-TENSR | 6200 | 13908 | 13908 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-TENSR90029917
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 Boom Module Quarter Life | 2029-03-09 | 2029-03-10 | 30 hrs | FY29 | 48 | 90029992 | A1 | 1000304639 | 09.03.2029 | 10000 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | 6200 | 13908 | 4116 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS90029992
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Motor Travel RHF | 2029-03-09 | 2029-03-09 | 6 hrs | FY29 | 12 | 90022657 | A1 | 1000207126 | 09.03.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRF | 6700 | 31524 | 6351 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRF90022657
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Minestar Harness | 2029-03-10 | 2029-03-11 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370303 | 10.03.2029 | 4000 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC | 6700 | 19559 | 19559 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Rotor & Logic Valve Hp Hoses | 2029-03-11 | 2029-03-12 | 18 hrs | FY29 | 36 | 90027571 | A1 | 1000284638 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCLVH | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCLVH90027571
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Servo Hoses Cascade to Bulkhead | 2029-03-11 | 2029-03-11 | 8 hrs | FY29 | 16 | 90027572 | A1 | 1000284639 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHBLK | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHBLK90027572
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Servo Hoses Cascade to Trvl Valve | 2029-03-11 | 2029-03-11 | 6 hrs | FY29 | 12 | 90027575 | A1 | 1000284641 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHTRV | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHTRV90027575
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos1 | 2029-03-11 | 2029-03-13 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000284593 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP1 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP190027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos2 | 2029-03-11 | 2029-03-13 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000284594 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP2 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP290027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos3 | 2029-03-11 | 2029-03-13 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000284595 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP3 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP390027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Main Hyd Pump Pos4 | 2029-03-11 | 2029-03-13 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000284596 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP4 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP490027490
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Replenish LH | 2029-03-11 | 2029-03-11 | 2 hrs | FY29 | 2 | 90027495 | A1 | 1000284603 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPL | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPL90027495
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Replenish RH | 2029-03-11 | 2029-03-11 | 2 hrs | FY29 | 2 | 90027495 | A1 | 1000284604 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPR | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPR90027495
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Pump Servo LH | 2029-03-11 | 2029-03-11 | 2 hrs | FY29 | 2 | 90027496 | A1 | 1000284601 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPL | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPL90027496
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Pump Servo RH | 2029-03-11 | 2029-03-11 | 2 hrs | FY29 | 2 | 90027496 | A1 | 1000284602 | 11.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPR | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPR90027496
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Pump Swing Pos1 & Pos2 | 2029-03-12 | 2029-03-13 | 26 hrs | FY29 | 42 | 90027492 | A1 | 1000284597 | 12.03.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP1P2 | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP1P290027492
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Batteries | 2029-03-12 | 2029-03-12 | 5 hrs | FY29 | 9 | 90017122 | A1 | 1000330530 | 12.03.2029 | 12 Monthly | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST | 6200 | 11792 | 2453 | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST90017122
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Grease Tank Level Valve | 2029-03-17 | 2029-03-17 | 2 hrs | FY29 | 2 | 90015003 | A1 | 1000348551 | 17.03.2029 | 12 Monthly | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK90015003
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Track Tension Tuning-Adjust | 2029-03-17 | 2029-03-17 | 3 hrs | FY29 | 9 | 90020545 | A1 | 1000348591 | 17.03.2029 | 6 Monthly | CLB-MP-EXCV-EX7141-UNDERC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Cyl Bucket LH Lift | 2029-03-19 | 2029-03-20 | 30 hrs | FY29 | 54 | 90030725 | A1 | 1000340296 | 19.03.2029 | 10000 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYL | 6200 | 9369 | 2193 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYL90030725
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cylinder Bucket LH | 2029-03-22 | 2029-03-23 | 26 hrs | FY29 | 32 | 90027499 | A1 | 1000297346 | 22.03.2029 | 10000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYL | 6700 | 16452 | 2288 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYL90027499
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 SADI Slew Bearing Inspection | 2029-03-22 | 2029-03-22 | 4 hrs | FY29 | 4 | 90022746 | A1 | 1000237212 | 22.03.2029 | 4 Monthly | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | 6700 | 27054 | 27054 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB90022746
R9400E | Onsite PM | Excavators | Fortescue | EX7133 | EX7133 12M Hydraulic Service & Repairs | 2029-03-24 | 2029-03-25 | 18 hrs | FY29 | 30 | 90029940 | A1 | 1000304680 | 24.03.2029 | 12 Monthly | CLB-MP-EXCV-EX7133-HYDSYS |  |  |  | CLB-MP-EXCV-EX7133-HYDSYS90029940
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Minestar Harness | 2029-03-25 | 2029-03-26 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370300 | 25.03.2029 | 4000 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 4500hr Valve Set | 2029-03-29 | 2029-03-29 | 10 hrs | FY29 | 20 | 90017923 | A1 | 1000207070 | 29.03.2029 | 4500 | CLB-MP-EXCV-EX7112-LHENGN | 6700 | 31524 | 13589 | CLB-MP-EXCV-EX7112-LHENGN90017923
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Sprocket LH | 2029-04-01 | 2029-04-01 | 12 hrs | FY29 | 24 | 90027486 | A1 | 1000284673 | 01.04.2029 | 1500 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKL | 470 | 1756 | 1756 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKL90027486
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Sprocket RH | 2029-04-01 | 2029-04-01 | 12 hrs | FY29 | 24 | 90027486 | A1 | 1000284684 | 01.04.2029 | 1500 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKR | 470 | 1756 | 1756 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKR90027486
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Power Pack Module Qtr Life | 2029-04-01 | 2029-04-01 | 7 hrs | FY29 | 13 | 90031021 | A1 | 1000348538 | 01.04.2029 | 5000 | CLB-MP-EXCV-EX7141-ENGINE | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-ENGINE90031021
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Grease System Audit | 2029-04-01 | 2029-04-02 | 24 hrs | FY29 | 36 | 90030748 | A1 | 1000348548 | 01.04.2029 | 5000 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ90030748
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos3 | 2029-04-04 | 2029-04-06 | 42 hrs | FY29 | 54 | 90003162 | A1 | 1000158826 | 04.04.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP3 | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP390003162
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel RHF | 2029-04-06 | 2029-04-06 | 6 hrs | FY29 | 12 | 90003178 | A1 | 1000158854 | 06.04.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRF | 6700 | 42775 | 5487 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRF90003178
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Replenish RH | 2029-04-06 | 2029-04-06 | 2 hrs | FY29 | 2 | 90003166 | A1 | 1000158835 | 06.04.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPR | 6700 | 42775 | 5523 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPR90003166
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Swing LHR | 2029-04-06 | 2029-04-07 | 21 hrs | FY29 | 27 | 90022654 | A1 | 1000237167 | 06.04.2029 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMLR | 6700 | 27054 | 11941 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMLR90022654
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Swing RHF | 2029-04-06 | 2029-04-07 | 21 hrs | FY29 | 27 | 90022654 | A1 | 1000237168 | 06.04.2029 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRF | 6700 | 27054 | 11930 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRF90022654
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hyd Motor Swing RHR | 2029-04-06 | 2029-04-07 | 21 hrs | FY29 | 27 | 90022654 | A1 | 1000237169 | 06.04.2029 | 15000 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRR | 6700 | 27054 | 11930 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRR90022654
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Adjust 4500hr Valve Set | 2029-04-07 | 2029-04-07 | 10 hrs | FY29 | 20 | 90017923 | A1 | 1000207085 | 07.04.2029 | 4500 | CLB-MP-EXCV-EX7112-RHENGN | 6700 | 31524 | 14061 | CLB-MP-EXCV-EX7112-RHENGN90017923
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Repl Operators Seat | 2029-04-17 | 2029-04-17 | 9 hrs | FY29 | 17 | 90030739 | A1 | 1000340287 | 17.04.2029 | 10000 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-SEATO | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-SEATO90030739
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Wiper Blades | 2029-04-18 | 2029-04-18 | 1 hr | FY29 | 1 | 90027557 | A1 | 1000284656 | 18.04.2029 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN |  |  |  | CLB-MP-EXCV-EX7124-STRUCT-CABIN90027557
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Adjust Track Tension Tuning | 2029-04-18 | 2029-04-18 | 3 hrs | FY29 | 9 | 90020545 | A1 | 1000337320 | 18.04.2029 | 6 Monthly | CLB-MP-EXCV-EX7140-UNDERC | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-UNDERC90020545
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Annual Air Con Service LH | 2029-04-19 | 2029-04-19 | 12 hrs | FY29 | 12 | 90027615 | A1 | 1000284685 | 19.04.2029 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL90027615
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Annual Air Con Service RH | 2029-04-19 | 2029-04-19 | 12 hrs | FY29 | 12 | 90027615 | A1 | 1000284655 | 19.04.2029 | 12 Monthly | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR | 6700 | 19559 | 8295 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR90027615
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Hyd Pump Swing Pos1 & Pos2 | 2029-04-22 | 2029-04-23 | 26 hrs | FY29 | 42 | 90003163 | A1 | 1000207100 | 22.04.2029 | 12000 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP1P2 | 6700 | 31524 | 5544 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP1P290003163
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Rotary Joint | 2029-04-22 | 2029-04-23 | 24 hrs | FY29 | 48 | 90022651 | A1 | 1000207116 | 22.04.2029 | 24000 | CLB-MP-EXCV-EX7112-HYDSYS-ROTRY | 6700 | 31524 | 5544 | CLB-MP-EXCV-EX7112-HYDSYS-ROTRY90022651
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Annual Air Con Service RH | 2029-04-22 | 2029-04-22 | 12 hrs | FY29 | 12 | 90004141 | 2 | 1000266975 | 22.04.2029 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR | 6700 | 31524 | 31524 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR90004141
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Swing LHR | 2029-04-22 | 2029-04-23 | 21 hrs | FY29 | 27 | 90022654 | A1 | 1000237036 | 22.04.2029 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMLR | 6700 | 25972 | 11422 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMLR90022654
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Swing RHF | 2029-04-22 | 2029-04-23 | 21 hrs | FY29 | 27 | 90022654 | A1 | 1000237037 | 22.04.2029 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRF | 6700 | 25972 | 11422 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRF90022654
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Hyd Motor Swing RHR | 2029-04-22 | 2029-04-23 | 21 hrs | FY29 | 27 | 90022654 | A1 | 1000237038 | 22.04.2029 | 15000 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRR | 6700 | 25972 | 11422 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRR90022654
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Swing LHR | 2029-04-24 | 2029-04-25 | 21 hrs | FY29 | 27 | 90003175 | A1 | 1000158845 | 24.04.2029 | 15000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMLR | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMLR90003175
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Swing RHF | 2029-04-24 | 2029-04-25 | 21 hrs | FY29 | 27 | 90003175 | A1 | 1000158846 | 24.04.2029 | 15000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRF | 6700 | 42775 | 11163 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRF90003175
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Auto Lube Pump | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 6 | 90027592 | A1 | 1000284661 | 25.04.2029 | 6000 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP | 6700 | 19559 | 6544 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP90027592
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Grease Control Valving | 2029-04-25 | 2029-04-25 | 14 hrs | FY29 | 14 | 90027612 | A1 | 1000284662 | 25.04.2029 | 12000 | CLB-MP-EXCV-EX7124-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7124-GRSYST-ALCON90027612
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel RHF | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 14 | 90027506 | A1 | 1000284623 | 25.04.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRF | 6700 | 19559 | 5733 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRF90027506
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel RHR | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 14 | 90027506 | A1 | 1000284624 | 25.04.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRR | 6700 | 19559 | 5712 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRR90027506
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 12M Hydraulic Service & Repairs | 2029-04-25 | 2029-04-26 | 18 hrs | FY29 | 30 | 90014448 | A1 | 1000348386 | 25.04.2029 | 12 Monthly | CLB-MP-EXCV-EX7141-HYDSYS | 6200 | 8353 | 1263 | CLB-MP-EXCV-EX7141-HYDSYS90014448
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Hyd Motor Travel LHF | 2029-04-26 | 2029-04-26 | 8 hrs | FY29 | 14 | 90027506 | A1 | 1000284621 | 26.04.2029 | 12000 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLF | 6700 | 19559 | 5733 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLF90027506
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Annual Air Con Service RH | 2029-04-26 | 2029-04-26 | 12 hrs | FY29 | 12 | 90004141 | 2 | 1000211117 | 26.04.2029 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR | 6700 | 42775 | 8084 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR90004141
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Repl Operators Seat | 2029-04-27 | 2029-04-27 | 9 hrs | FY29 | 17 | 90030739 | A1 | 1000330525 | 27.04.2029 | 10000 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-SEATO | 6200 | 11792 | 3070 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-SEATO90030739
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Annual Air Con Service LH | 2029-04-27 | 2029-04-27 | 12 hrs | FY29 | 12 | 90004141 | 2 | 1000163161 | 27.04.2029 | 12 Monthly | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL | 6700 | 19252 | 8084 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL90004141
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Static Line Inspection | 2029-04-28 | 2029-04-28 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000340340 | 28.04.2029 | 6 Monthly | CLB-MP-EXCV-EX7138-STRUCT | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-STRUCT90014347
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Cylinder Bucket RH | 2029-04-28 | 2029-04-29 | 26 hrs | FY29 | 32 | 90003169 | A1 | 1000158841 | 28.04.2029 | 10000 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYR | 6700 | 42775 | 746 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYR90003169
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Minestar Harness | 2029-04-29 | 2029-04-30 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370301 | 29.04.2029 | 4000 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Operators Seat | 2029-04-29 | 2029-04-29 | 2 hrs | FY29 | 2 | 90022750 | A1 | 1000237179 | 29.04.2029 | 10000 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-SEATS | 6700 | 27054 | 1520 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-SEATS90022750
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cylinder Bucket RH | 2029-04-30 | 2029-05-01 | 26 hrs | FY29 | 32 | 90027499 | A1 | 1000297347 | 30.04.2029 | 10000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYR | 6700 | 16452 | 1563 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYR90027499
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Emergency Ladder | 2029-05-03 | 2029-05-03 | 3 hrs | FY29 | 6 | 90022513 | 1 | 1000241541 | 03.05.2029 | 24 Monthly | CLB-MP-EXCV-EX7119-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7119-STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Emergency Ladder | 2029-05-05 | 2029-05-05 | 3 hrs | FY29 | 6 | 90022513 | 1 | 1000241540 | 05.05.2029 | 24 Monthly | CLB-MP-EXCV-EX7118-STRUCT-STLAD-SLFXD |  |  |  | CLB-MP-EXCV-EX7118-STRUCT-STLAD-SLFXD90022513
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Annual Air Con Service LH | 2029-05-06 | 2029-05-06 | 12 hrs | FY29 | 12 | 90022660 | A1 | 1000242609 | 06.05.2029 | 12 Monthly | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL | 6700 | 17550 | 5056 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL90022660
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Idler Track RH | 2029-05-07 | 2029-05-07 | 6 hrs | FY29 | 18 | 90027507 | A1 | 1000284676 | 07.05.2029 | 1500 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-IDLRH | 470 | 1756 | 206 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-IDLRH90027507
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Idler Track LH | 2029-05-09 | 2029-05-09 | 6 hrs | FY29 | 18 | 90027507 | A1 | 1000284665 | 09.05.2029 | 1500 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-IDLLH | 470 | 1756 | 206 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-IDLLH90027507
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Hydraulic Cooling Circ Hoses | 2029-05-09 | 2029-05-10 | 18 hrs | FY29 | 36 | 90028476 | A1 | 1000237185 | 09.05.2029 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HCCHH | 6700 | 27054 | 5348 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HCCHH90028476
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Swing Circuit Hoses | 2029-05-10 | 2029-05-10 | 8 hrs | FY29 | 16 | 90022738 | A1 | 1000237064 | 10.05.2029 | 9000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT90022738
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Cyl Bucket RH Lift | 2029-05-11 | 2029-05-12 | 30 hrs | FY29 | 54 | 90030726 | A1 | 1000348545 | 11.05.2029 | 10000 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYR | 6200 | 8353 | 2659 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYR90030726
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Repl Minestar Harness | 2029-05-11 | 2029-05-12 | 27.5 hrs | FY29 | 43.5 | 90030746 | A1 | 1000348553 | 11.05.2029 | 5000 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC90030746
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos1 | 2029-05-15 | 2029-05-17 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000297330 | 15.05.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP1 | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP190027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos2 | 2029-05-15 | 2029-05-17 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000297331 | 15.05.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP2 | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP290027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Pos1 & Pos2 | 2029-05-15 | 2029-05-16 | 26 hrs | FY29 | 42 | 90027492 | A1 | 1000297334 | 15.05.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP1P2 | 6700 | 16452 | 5351 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP1P290027492
R9400 | Onsite PM | Excavators | Fortescue | EX7140 | EX7140 Inspection Ext Static Line | 2029-05-19 | 2029-05-19 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000337317 | 19.05.2029 | 6 Monthly | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | 6200 | 10954 | 10954 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos2 | 2029-05-20 | 2029-05-22 | 42 hrs | FY29 | 54 | 90003162 | A1 | 1000158825 | 20.05.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP2 | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP290003162
R9400 | Onsite PM | Excavators | Fortescue | EX7138 | EX7138 Track Tension Tuning-Adjust | 2029-05-22 | 2029-05-22 | 3 hrs | FY29 | 9 | 90020545 | A1 | 1000340343 | 22.05.2029 | 6 Monthly | CLB-MP-EXCV-EX7138-UNDERC | 6200 | 9369 | 9369 | CLB-MP-EXCV-EX7138-UNDERC90020545
R9400 | Onsite PM | Excavators | Fortescue | EX7141 | EX7141 Inspection Ext Static Line | 2029-05-22 | 2029-05-22 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000348588 | 22.05.2029 | 6 Monthly | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | 6200 | 8353 | 8353 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS90014347
R9400 | Onsite PM | Excavators | Fortescue | EX7139 | EX7139 Inspection Ext Static Line | 2029-05-22 | 2029-05-22 | 4 hrs | FY29 | 4 | 90014347 | A1 | 1000330578 | 22.05.2029 | 6 Monthly | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | 6200 | 11792 | 11792 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS90014347
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Main Hyd Pump Pos1 | 2029-05-22 | 2029-05-24 | 42 hrs | FY29 | 54 | 90003162 | A1 | 1000158824 | 22.05.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP1 | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP190003162
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Pump Swing Replenish LH | 2029-05-22 | 2029-05-22 | 2 hrs | FY29 | 2 | 90003166 | A1 | 1000158834 | 22.05.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPL | 6700 | 42775 | 4657 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPL90003166
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Repl Cylinder Bucket LH | 2029-05-31 | 2029-06-01 | 26 hrs | FY29 | 32 | 90003169 | A1 | 1000207112 | 31.05.2029 | 10000 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL | 6700 | 31524 | 10817 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL90003169
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Idler Track RH | 2029-06-04 | 2029-06-04 | 6 hrs | FY29 | 18 | 90003189 | A1 | 1000231310 | 04.06.2029 | 1500 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-IDLRH | 470 | 3415 | 3415 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-IDLRH90003189
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 SADI Slew Bearing Inspection | 2029-06-04 | 2029-06-04 | 4 hrs | FY29 | 4 | 90022746 | A1 | 1000237081 | 04.06.2029 | 4 Monthly | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | 6700 | 25972 | 25972 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB90022746
6040 | Onsite PM | Excavators | Fortescue | EX7112 | EX7112 Annual Air Con Service LH | 2029-06-08 | 2029-06-08 | 12 hrs | FY29 | 12 | 90004141 | 2 | 1000207158 | 08.06.2029 | 12 Monthly | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL | 6700 | 21488 | 7104 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL90004141
6040 | Onsite PM | Excavators | Fortescue | EX7124 | EX7124 Repl Cylinder Bucket RH | 2029-06-09 | 2029-06-10 | 26 hrs | FY29 | 32 | 90027499 | A1 | 1000284610 | 09.06.2029 | 10000 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYR | 6700 | 19559 | 899 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYR90027499
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Replenish LH | 2029-06-12 | 2029-06-12 | 2 hrs | FY29 | 2 | 90027495 | A1 | 1000297340 | 12.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPL90027495
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Servo LH | 2029-06-12 | 2029-06-12 | 2 hrs | FY29 | 2 | 90027496 | A1 | 1000297338 | 12.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPL | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPL90027496
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Servo RH | 2029-06-12 | 2029-06-12 | 2 hrs | FY29 | 2 | 90027496 | A1 | 1000297339 | 12.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPR | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPR90027496
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Auto Lube Pump | 2029-06-13 | 2029-06-13 | 6 hrs | FY29 | 6 | 90027592 | A1 | 1000297398 | 13.06.2029 | 6000 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP90027592
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Grease Control Valving | 2029-06-13 | 2029-06-13 | 14 hrs | FY29 | 14 | 90027612 | A1 | 1000297399 | 13.06.2029 | 12000 | CLB-MP-EXCV-EX7122-GRSYST-ALCON |  |  |  | CLB-MP-EXCV-EX7122-GRSYST-ALCON90027612
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Fan Drive Eng Cooling Hose | 2029-06-13 | 2029-06-14 | 18 hrs | FY29 | 36 | 90027564 | A1 | 1000297367 | 13.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDECH | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDECH90027564
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Swing Motor Case Drain Hoses | 2029-06-13 | 2029-06-13 | 6 hrs | FY29 | 12 | 90027577 | A1 | 1000297380 | 13.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWMCD | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWMCD90027577
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos3 | 2029-06-13 | 2029-06-15 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000297332 | 13.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP3 | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP390027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Hyd Pump Pos4 | 2029-06-13 | 2029-06-15 | 42 hrs | FY29 | 64 | 90027490 | A1 | 1000297333 | 13.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP4 | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP490027490
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Swing Pos3 & Pos4 | 2029-06-13 | 2029-06-14 | 26 hrs | FY29 | 42 | 90027492 | A1 | 1000297335 | 13.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP3P4 | 6700 | 16452 | 4768 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP3P490027492
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Annual Air Con Service LH | 2029-06-18 | 2029-06-18 | 12 hrs | FY29 | 12 | 90022660 | A1 | 1000242610 | 18.06.2029 | 12 Monthly | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL | 6700 | 19940 | 6054 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL90022660
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Fan Drive Hyd Cooling Hoses | 2029-06-23 | 2029-06-24 | 18 hrs | FY29 | 36 | 90022727 | A1 | 1000345666 | 23.06.2029 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDHCH | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDHCH90022727
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Track Tensioning Hoses | 2029-06-23 | 2029-06-23 | 3 hrs | FY29 | 3 | 90022741 | A1 | 1000237067 | 23.06.2029 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TRTNH | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TRTNH90022741
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Minestar Harness | 2029-06-24 | 2029-06-25 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000312852 | 24.06.2029 | 4000 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC90031708
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Boom Cyl | 2029-06-25 | 2029-06-25 | 8 hrs | FY29 | 24 | 90029908 | A1 | 1000357426 | 25.06.2029 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL90029908
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Stick Cyl | 2029-06-25 | 2029-06-25 | 12 hrs | FY29 | 24 | 90029909 | A1 | 1000357427 | 25.06.2029 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL90029909
R9400E | Onsite PM | Excavators | Fortescue | EX7148 | EX7148 Repl Hyd Hose Bucket Cyl | 2029-06-25 | 2029-06-26 | 18 hrs | FY29 | 54 | 90029911 | A1 | 1000357428 | 25.06.2029 | 8000 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL | 6200 | 6057 | 6057 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL90029911
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic Oil Replacement | 2029-06-25 | 2029-06-25 | 12 hrs | FY29 | 12 | 90016793 | 1 | 1000158890 | 25.06.2029 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90016793
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Hydraulic System Tune Up | 2029-06-25 | 2029-06-25 | 12 hrs | FY29 | 24 | 90017865 | 1 | 1000163743 | 25.06.2029 | 6000 | CLB-MP-EXCV-EX014 -HYDSYS | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS90017865
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Swing Motor Case Drain Hoses | 2029-06-25 | 2029-06-25 | 6 hrs | FY29 | 12 | 90022739 | A1 | 1000158877 | 25.06.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWMCD | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWMCD90022739
6040 | Onsite PM | Excavators | Fortescue | EX014 | EX014 Repl Hyd Motor Travel LHR | 2029-06-25 | 2029-06-25 | 6 hrs | FY29 | 12 | 90003178 | A1 | 1000158853 | 25.06.2029 | 12000 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLR | 6700 | 42775 | 3932 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLR90003178
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Cylinder Stick RH | 2029-06-26 | 2029-06-27 | 30 hrs | FY29 | 54 | 90022646 | A1 | 1000237161 | 26.06.2029 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLR | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLR90022646
6040 | Onsite PM | Excavators | Fortescue | EX7119 | EX7119 Repl Main Hyd Pump Pos3 | 2029-06-26 | 2029-06-28 | 42 hrs | FY29 | 54 | 90022637 | A1 | 1000237148 | 26.06.2029 | 12000 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP3 | 6700 | 27054 | 4463 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP390022637
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Repl Boom Stick Bucket Cyl Hoses | 2029-06-28 | 2029-07-01 | 88 hrs | FY29 | 136 | 90022725 | A1 | 1000345664 | 28.06.2029 | 12000 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HBSBC | 6700 | 25972 | 4282 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HBSBC90022725
6040 | Onsite PM | Excavators | Fortescue | EX7118 | EX7118 Engine Midlife Complete LH | 2029-06-29 | 2029-07-01 | 54 hrs | FY29 | 76 | 90022685 | A1 | 1000236990 | 29.06.2029 | 9000 | CLB-MP-EXCV-EX7118-LHENGN | 6700 | 25972 | 7182 | CLB-MP-EXCV-EX7118-LHENGN90022685
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cyl Boom LH | 2029-06-30 | 2029-07-04 | 90 hrs | FY29 | 138 | 90027497 | A1 | 1000297342 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYL90027497
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Cyl Boom RH | 2029-06-30 | 2029-07-04 | 90 hrs | FY29 | 138 | 90027497 | A1 | 1000297343 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYR90027497
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom Stick Bucket Cyl Hoses | 2029-06-30 | 2029-07-03 | 88 hrs | FY29 | 136 | 90027560 | A1 | 1000297366 | 30.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC90027560
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom & MCV Hoses | 2029-06-30 | 2029-07-03 | 88 hrs | FY29 | 136 | 90032593 | A1 | 1000325060 | 30.06.2029 | 12000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC | 6700 | 16452 | 1021 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC90032593
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Oil Suction Hoses | 2029-06-30 | 2029-07-01 | 24 hrs | FY29 | 48 | 90027568 | A1 | 1000297372 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-OILSC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-OILSC90027568
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Hyd Cool Front | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 12 | 90027504 | A1 | 1000297354 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHF | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHF90027504
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Hyd Cool Rear | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 12 | 90027504 | A1 | 1000297355 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHR90027504
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Engine Cool LH | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 18 | 90027505 | A1 | 1000297356 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECL90027505
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Motor Fan Engine Cool RH | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 18 | 90027505 | A1 | 1000297357 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECR90027505
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Control Valve Block LH | 2029-06-30 | 2029-07-01 | 34 hrs | FY29 | 50 | 90027502 | A1 | 1000297383 | 30.06.2029 | 36000 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-MCVVL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-MCVVL90027502
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Main Control Valve Block RH | 2029-06-30 | 2029-07-01 | 34 hrs | FY29 | 50 | 90027502 | A1 | 1000297384 | 30.06.2029 | 36000 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-MCVVR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-MCVVR90027502
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Hyd Pump Fan Engine Cool LH | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 12 | 90027494 | A1 | 1000297336 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPL90027494
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Drive Gearbox LH | 2029-06-30 | 2029-07-01 | 40 hrs | FY29 | 116 | 90027489 | A1 | 1000297328 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRL | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRL90027489
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Pump Drive Gearbox RH | 2029-06-30 | 2029-07-01 | 40 hrs | FY29 | 116 | 90027489 | A1 | 1000297329 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRR90027489
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Engine Cat C32 | 2029-06-30 | 2029-07-07 | 176.5 hrs | FY29 | 254.5 | 90027533 | A1 | 1000297273 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-LHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN90027533
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Radiator LH Engine Cooling | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 12 | 90027552 | A1 | 1000297277 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-RADTR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-RADTR90027552
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl LH Aftercooler | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 24 | 90023361 | A1 | 1000309288 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-AFTER | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-AFTER90023361
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Minestar Harness | 2029-06-30 | 2029-07-01 | 24.5 hrs | FY29 | 40.5 | 90031708 | A1 | 1000370302 | 30.06.2029 | 4000 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC90031708
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Engine Cat C32 | 2029-06-30 | 2029-07-07 | 176.5 hrs | FY29 | 254.5 | 90027534 | A1 | 1000297278 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-RHENGN | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN90027534
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Radiator RH Engine Cooling | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 12 | 90027553 | A1 | 1000297322 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-RADTR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-RADTR90027553
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl RH Aftercooler | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 24 | 90023360 | A1 | 1000309289 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-AFTER | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-AFTER90023360
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Boom Assy Dressed | 2029-06-30 | 2029-07-05 | 116 hrs | FY29 | 324 | 90031798 | A1 | 1000314058 | 30.06.2029 | 36000 | CLB-MP-EXCV-EX7122-STRUCT-BOOMS | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-BOOMS90031798
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Stick Assy Dressed | 2029-06-30 | 2029-07-04 | 96 hrs | FY29 | 192 | 90031801 | A1 | 1000314254 | 30.06.2029 | 36000 | CLB-MP-EXCV-EX7122-STRUCT-STICK | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-STICK90031801
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Track Tensioner LH | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 24 | 90027527 | A1 | 1000297389 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-TENSR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-TENSR90027527
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Track Tensioner RH | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 24 | 90027527 | A1 | 1000297390 | 30.06.2029 | 18000 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-TENSR | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-TENSR90027527
6040 | Onsite PM | Excavators | Fortescue | EX7122 | EX7122 Repl Slew Gear Bearing | 2029-06-30 | 2029-07-04 | 96 hrs | FY29 | 288 | 90027508 | A1 | 1000297362 | 30.06.2029 | 36000 | CLB-MP-EXCV-EX7122-STRUCT-UNDER-SLEWB | 6700 | 16452 | 16452 | CLB-MP-EXCV-EX7122-STRUCT-UNDER-SLEWB90027508
| Onsite PM | Drills | Fortescue |  | DRILLS - COMPONENTS DURING PM
| Onsite PM | Drills | Fortescue |  | FY27 - DRILLS - COMPONENTS DURING PM | 2026-07-01 |  |  | FY27
| Onsite PM | Drills | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-07-01 | 365 days | FY27
| Onsite PM | Drills | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | MD6310 Cisco Radio Relocation | 2026-07-01 | 2026-07-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | Vehicle Loading Crane (Repurposed HOBO Assembly) | 2026-07-01 | 2026-07-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD6310 access ladders | 2026-07-01 | 2026-07-31 | 30 days | FY27
PV271 | Onsite PM | Drills | Fortescue | DR060 | Water Tank Refill Chute | 2026-07-01 | 2026-07-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | MD6310 Cisco Radio Relocation | 2026-07-01 | 2026-07-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | DR2136 | Vehicle Loading Crane (Repurposed HOBO Assembly) | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - PV271 | PV271 walkway corrosion | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | Pipe Positioner | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Drills | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD Head Slide Upgrade Kit and Labour for Initial Install | 2026-10-01 | 2026-10-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD6310 Carousel Onsite Refurb | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2026-10-01 | 2026-10-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | CAT Travelling Hose Net | 2026-10-01 | 2026-10-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Jack Leg Limit Switch MD Change Out | 2026-10-01 | 2026-10-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Platform VLC Modification | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD Head Slide Upgrade Kit and Labour for Initial Install | 2026-11-01 | 2026-11-30 | 29 days | FY27
PV271 | Onsite PM | Drills | Fortescue | All - PV271 | PV 4 Hole Pump Drive Gear Box Upgrade | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2026-11-01 | 2026-11-30 | 29 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | CAT Travelling Hose Net | 2026-11-01 | 2026-11-30 | 29 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Jack Leg Limit Switch MD Change Out | 2026-11-01 | 2026-11-30 | 29 days | FY27
D65 | Onsite PM | Drills | Fortescue | DR3126 | Mast Clamp | 2026-11-01 | 2026-11-30 | 29 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Pipe Positioner | 2026-11-01 | 2026-11-30 | 29 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Platform VLC Modification | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Drills | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
PV271 | Onsite PM | Drills | Fortescue | DR060 | C27, 2600cfm LP Conversion (Line up with Engine replacement) | 2026-12-01 | 2026-12-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD Head Slide Upgrade Kit and Labour for Initial Install | 2026-12-01 | 2026-12-31 | 30 days | FY27
PV271 | Onsite PM | Drills | Fortescue | DR061 | PV271 Cab Corrosion | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2026-12-01 | 2026-12-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | CAT Travelling Hose Net | 2026-12-01 | 2026-12-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Jack Leg Limit Switch MD Change Out | 2026-12-01 | 2026-12-31 | 30 days | FY27
D65 | Onsite PM | Drills | Fortescue | DR3126 | Mast Clamp | 2026-12-01 | 2026-12-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Platform VLC Modification | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD Head Slide Upgrade Kit and Labour for Initial Install | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2027-01-01 | 2027-01-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | CAT Travelling Hose Net | 2027-01-01 | 2027-01-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Jack Leg Limit Switch MD Change Out | 2027-01-01 | 2027-01-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Platform VLC Modification | 2027-01-01 | 2027-01-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Rod Wipe R&D | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Drills | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD Head Slide Upgrade Kit and Labour for Initial Install | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2027-02-01 | 2027-02-28 | 27 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | CAT Travelling Hose Net | 2027-02-01 | 2027-02-28 | 27 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Jack Leg Limit Switch MD Change Out | 2027-02-01 | 2027-02-28 | 27 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Platform VLC Modification | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Drills | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD Head Slide Upgrade Kit and Labour for Initial Install | 2027-03-01 | 2027-03-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | MD6310 Carousel Onsite Refurb | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Drills | Onsite PM | Drills | Fortescue | All - Drills | AC Drain to Washer Bottle Mod | 2027-03-01 | 2027-03-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | CAT Travelling Hose Net | 2027-03-01 | 2027-03-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Jack Leg Limit Switch MD Change Out | 2027-03-01 | 2027-03-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | All - MD6310 | Platform VLC Modification | 2027-03-01 | 2027-03-31 | 30 days | FY27
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS Vibration Sensors | 2026-07-06 | 2026-07-06 | 1 hr | FY27 | 1 | 90029062 | A1 | 1000296435 | 03.06.2027 | 10000 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS-DSVSN | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS LiDAR | 2026-07-06 | 2026-07-06 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000296439 | 03.06.2027 | 5000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR | 6700 | 15850 | 10602 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS LiDAR | 2026-07-21 | 2026-07-21 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000296439 | 16.08.2026 | 5000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR | 6700 | 15850 | 10602 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Engine Assy Caterpillar C32 | 2026-07-21 | 2026-07-23 | 50 hrs | FY27 | 150 | 90020393 | 1 | 1000296348 | 14.05.2026 | 15000 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cyl Mast Locking NCS | 2026-07-21 | 2026-07-21 | 12 hrs | FY27 | 24 | 90020197 | 1 | 1000296345 | 14.05.2026 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYL | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cyl Mast Locking CS | 2026-07-21 | 2026-07-21 | 12 hrs | FY27 | 24 | 90030657 | A1 | 1000296344 | 14.05.2026 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cyl Mast Raise CS | 2026-07-21 | 2026-07-21 | 16 hrs | FY27 | 32 | 90020198 | 1 | 1000296346 | 14.11.2027 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MRCYR | 6700 | 15850 | 5572 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MRCYR90020198
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Drive Gearbox | 2026-07-21 | 2026-07-22 | 30 hrs | FY27 | 78 | 90020181 | 1 | 1000296369 | 15.09.2026 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG90020181
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Adjust 500Hr Initial Valve Set | 2026-07-27 | 2026-07-27 | 12 hrs | FY27 | 24 | 90020604 | 1 | 1000256599 | 27.07.2026 | 500 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020604
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Hose Drum Sprocket | 2026-07-30 | 2026-07-30 | 6 hrs | FY27 | 6 | 90022031 | B1 | 1000231376 | 15.05.2026 | 6000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDS | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDS90022031
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Cyl Jack levelling Rear | 2026-07-30 | 2026-07-30 | 4 hrs | FY27 | 4 | 90012954 | B1 | 1000150440 | 24.02.2027 | 12000 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-JLCYR | 4200 | 30594 | 9692 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-JLCYR90012954
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Water & Fuel Tank Mount | 2026-08-02 | 2026-08-02 | 10 hrs | FY27 | 20 | 90017443 | 1 | 1000160296 | 24.07.2026 | 12 Monthly | CLB-MP-DRLL-DR061 -DSTSUP-WTTNK |  |  |  | CLB-MP-DRLL-DR061 -DSTSUP-WTTNK90017443
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Air Lubrication | 2026-08-06 | 2026-08-06 | 2 hrs | FY27 | 2 | 90021656 | A1 | 1000237302 | 24.08.2026 | 6000 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB | 4400 | 17885 | 6064 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB90021656
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2026-08-06 | 2026-08-06 | 1 hr | FY27 | 1 | 90020876 | A1 | 1000237255 | 17.09.2026 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cyl Mast Raise NCS | 2026-08-08 | 2026-08-08 | 16 hrs | FY27 | 32 | 90030659 | A1 | 1000296453 | 23.03.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MRCYL | 6700 | 15193 | 3176 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MRCYL90030659
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 24M Air Cond Rencool Overhaul | 2026-08-13 | 2026-08-14 | 24 hrs | FY27 | 24 | 90018580 | 1 | 1000180962 | 16.04.2026 | 24 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018580
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cabin ADS Components | 2026-08-13 | 2026-08-14 | 31.5 hrs | FY27 | 31.5 | 90029189 | A1 | 1000294226 | 27.01.2025 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-HMIJK | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-HMIJK90029189
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS Ace Cabinet Components | 2026-08-13 | 2026-08-15 | 44.5 hrs | FY27 | 44.5 | 90029187 | A1 | 1000294225 | 27.01.2025 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-CLXEN | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-CLXEN90029187
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Mast & A-Frame Harnesses | 2026-08-13 | 2026-08-16 | 70.5 hrs | FY27 | 70.5 | 90030429 | A1 | 1000303727 | 21.08.2025 | 20000 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO90030429
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Control Harnesses Chassis | 2026-08-13 | 2026-08-14 | 39 hrs | FY27 | 39 | 90029952 | A1 | 1000303819 | 21.08.2025 | 20000 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO90029952
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Compressor Coupling | 2026-08-20 | 2026-08-20 | 12 hrs | FY27 | 24 | 90030404 | A1 | 1000303536 | 14.07.2024 | 7500 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-COUPL | 6700 | 14786 | 8105 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-COUPL90030404
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Water Inj | 2026-08-20 | 2026-08-20 | 2 hrs | FY27 | 4 | 90031899 | A1 | 1000315429 | 19.01.2026 | 7500 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP | 6700 | 14786 | 7896 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Engine Assy Caterpillar C32 | 2026-08-20 | 2026-08-22 | 50 hrs | FY27 | 150 | 90020393 | 1 | 1000256598 | 15.03.2026 | 15000 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2026-08-20 | 2026-08-21 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302772 | 23.02.2026 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cyl Mast Locking NCS | 2026-08-20 | 2026-08-20 | 12 hrs | FY27 | 24 | 90020197 | 1 | 1000256595 | 14.07.2026 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYL | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cyl Mast Locking CS | 2026-08-20 | 2026-08-20 | 12 hrs | FY27 | 24 | 90030657 | A1 | 1000256594 | 14.07.2026 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Chassis Harnesses | 2026-08-20 | 2026-08-24 | 104 hrs | FY27 | 208 | 90028944 | A1 | 1000289062 | 14.07.2026 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cab Harnesses | 2026-08-20 | 2026-08-20 | 14 hrs | FY27 | 14 | 90028947 | A1 | 1000289063 | 14.07.2026 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Compressor Harnesses | 2026-08-20 | 2026-08-20 | 12 hrs | FY27 | 12 | 90028948 | A1 | 1000289064 | 14.07.2026 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Drive Gearbox | 2026-08-20 | 2026-08-21 | 30 hrs | FY27 | 78 | 90020181 | 1 | 1000256627 | 31.08.2026 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG | 6700 | 14781 | 14781 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG90020181
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 6M Static Line Inspection | 2026-08-20 | 2026-08-20 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000256585 | 01.09.2026 | 6 Monthly | CLB-MP-DRLL-DR2126-STRUCT |  |  |  | CLB-MP-DRLL-DR2126-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS LiDAR | 2026-08-20 | 2026-08-20 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000290914 | 20.09.2026 | 5000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS Vibration Sensors | 2026-08-24 | 2026-08-24 | 1 hr | FY27 | 1 | 90029062 | A1 | 1000296541 | 05.05.2027 | 10000 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS-DSVSN | 6700 | 15193 | 4538 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Washdown Pump | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 8 | 90030681 | A1 | 1000305735 | 01.08.2026 | 7500 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Water Inj | 2026-08-24 | 2026-08-24 | 2 hrs | FY27 | 4 | 90031899 | A1 | 1000315431 | 23.08.2026 | 7500 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP | 6700 | 17309 | 6755 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cab Harnesses | 2026-08-24 | 2026-08-24 | 14 hrs | FY27 | 14 | 90028947 | A1 | 1000294926 | 14.03.2026 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Chassis Harnesses | 2026-08-24 | 2026-08-28 | 104 hrs | FY27 | 208 | 90028944 | A1 | 1000294925 | 14.03.2026 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Compressor Harnesses | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 12 | 90028948 | A1 | 1000294927 | 14.03.2026 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cyl Mast Raise CS | 2026-08-24 | 2026-08-24 | 16 hrs | FY27 | 32 | 90020198 | 1 | 1000294846 | 07.04.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYR | 6700 | 17309 | 10627 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYR90020198
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Vehicle Loading Crane | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 12 | 90032931 | A1 | 1000331364 | 23.03.2030 | 40000 | CLB-MP-DRLL-DR2130-STRUCT-CRANE | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-CRANE90032931
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Sprocket LH | 2026-08-24 | 2026-08-24 | 10 hrs | FY27 | 20 | 90020186 | 1 | 1000303011 | 21.06.2025 | 10000 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKL | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKL90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Sprocket RH | 2026-08-24 | 2026-08-24 | 10 hrs | FY27 | 20 | 90020186 | 1 | 1000303012 | 21.06.2025 | 10000 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKR | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKR90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Fish Eye Camera | 2026-08-31 | 2026-08-31 | 16 hrs | FY27 | 16 | 90029067 | A1 | 1000296544 | 17.06.2027 | 10000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-HTCAM | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-HTCAM90029067
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Jack Leg NDE NCS | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90015956 | A1 | 1000152147 | 10.09.2026 | 15000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLF | 6300 | 43398 | 14180 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLF90015956
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Jack Leg NDE CS | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90015957 | A1 | 1000152148 | 10.09.2026 | 15000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRF | 6300 | 43398 | 14161 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRF90015957
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 6M Static Line Inspection | 2026-09-01 | 2026-09-01 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000296441 | 01.09.2026 | 6 Monthly | CLB-MP-DRLL-DR2133-STRUCT |  |  |  | CLB-MP-DRLL-DR2133-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack RHF NDE CS | 2026-09-06 | 2026-09-06 | 12 hrs | FY27 | 24 | 90030670 | A1 | 1000296170 | 02.10.2026 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF | 6700 | 16830 | 4546 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack RHR DE CS | 2026-09-06 | 2026-09-06 | 12 hrs | FY27 | 24 | 90030672 | A1 | 1000296171 | 14.04.2026 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRR90030672
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 6M Static Line Inspection | 2026-09-06 | 2026-09-06 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000296163 | 01.09.2026 | 6 Monthly | CLB-MP-DRLL-DR2131-STRUCT |  |  |  | CLB-MP-DRLL-DR2131-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Cables | 2026-09-06 | 2026-09-07 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302812 | 01.09.2026 | 2500 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Adjust 500Hr Initial Valve Set | 2026-09-11 | 2026-09-11 | 12 hrs | FY27 | 24 | 90020604 | 1 | 1000296349 | 08.06.2026 | 500 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020604
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack RHF NDE CS | 2026-09-11 | 2026-09-11 | 12 hrs | FY27 | 24 | 90030670 | A1 | 1000296342 | 28.09.2026 | 6000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF | 6700 | 15850 | 4205 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 6M Static Line Inspection | 2026-09-11 | 2026-09-11 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000296315 | 01.09.2026 | 6 Monthly | CLB-MP-DRLL-DR2132-STRUCT |  |  |  | CLB-MP-DRLL-DR2132-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Cables | 2026-09-11 | 2026-09-12 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302816 | 03.10.2026 | 2500 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pressure Safety Valve Cert | 2026-09-14 | 2026-09-14 | 3 hrs | FY27 | 3 | 90021719 | A1 | 1000237321 | 03.09.2026 | 18 Monthly | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK | 4400 | 17932 | 4496 | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK90021719
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Washdown Pump | 2026-09-24 | 2026-09-24 | 4 hrs | FY27 | 8 | 90030681 | A1 | 1000305731 | 24.09.2026 | 7500 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 6M Static Line Inspection | 2026-09-28 | 2026-09-28 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000294755 | 01.09.2026 | 6 Monthly | CLB-MP-DRLL-DR2130-STRUCT |  |  |  | CLB-MP-DRLL-DR2130-STRUCT90013246
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Pump Water Injection | 2026-10-13 | 2026-10-13 | 4 hrs | FY27 | 4 | 90013019 | B1 | 1000150468 | 13.10.2026 | 6000 | CLB-MP-DRLL-DR3110-DSTSUP-WTRPP | 4200 | 30594 | 772 | CLB-MP-DRLL-DR3110-DSTSUP-WTRPP90013019
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Cables | 2026-10-18 | 2026-10-19 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302880 | 18.10.2026 | 2500 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Wet Season Preparation | 2026-10-19 | 2026-10-20 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000303581 | 19.10.2026 | 12 Monthly | CLB-MP-DRLL-DR3126 | 4400 | 17885 | 17885 | CLB-MP-DRLL-DR312690030417
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Service Airconditioning System | 2026-10-20 | 2026-10-20 | 12 hrs | FY27 | 12 | 90023281 | A1 | 1000241272 | 20.10.2026 | 12 Monthly | CLB-MP-DRLL-DR3126-STRUCT-CABIN-ACCOM | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-ACCOM90023281
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Wet Season Preparation | 2026-10-22 | 2026-10-23 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000365892 | 22.10.2026 | 12 Monthly | CLB-MP-DRLL-DR3110 | 5400 | 30612 | 30612 | CLB-MP-DRLL-DR311090030417
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Operators Seat | 2026-10-23 | 2026-10-23 | 2 hrs | FY27 | 2 | 90016913 | 1 | 1000152169 | 22.06.2026 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-CABIN-SEATS | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-CABIN-SEATS90016913
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 PV271 Hydraulic Tune | 2026-10-23 | 2026-10-24 | 21 hrs | FY27 | 31.5 | 90017118 | 1 | 1000206785 | 23.10.2026 | 3000 | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190017118
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Cyl Oscillation RH | 2026-10-24 | 2026-10-24 | 4 hrs | FY27 | 8 | 90012956 | B1 | 1000150442 | 24.10.2026 | 12000 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-TFCOR | 4200 | 30594 | 5268 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-TFCOR90012956
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 XLF Repl Main Feed Chain | 2026-10-25 | 2026-10-25 | 8 hrs | FY27 | 16 | 90021711 | A1 | 1000237290 | 25.10.2026 | 2500 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH | 4400 | 17885 | 1481 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH90021711
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS LiDAR | 2026-10-26 | 2026-10-26 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000296545 | 26.10.2026 | 5000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR90029065
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Wet Season Preparation | 2026-10-29 | 2026-10-30 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000303395 | 29.10.2026 | 12 Monthly | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090030417
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2026-11-03 | 2026-11-04 | 21 hrs | FY27 | 31.5 | 90017118 | 1 | 1000145852 | 03.11.2026 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Service Airconditioning System | 2026-11-06 | 2026-11-06 | 12 hrs | FY27 | 12 | 90023280 | B1 | 1000241270 | 06.11.2026 | 12 Monthly | CLB-MP-DRLL-DR3110-STRUCT-CABIN-ACCOM | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-ACCOM90023280
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Wet Season Preparation | 2026-11-08 | 2026-11-09 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000303396 | 08.11.2026 | 12 Monthly | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190030417
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2026-11-11 | 2026-11-12 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302772 | 11.11.2026 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Wet Season Preparation | 2026-11-12 | 2026-11-13 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000303580 | 12.11.2026 | 12 Monthly | CLB-MP-DRLL-DR2130 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR213090030417
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Auto Lube Pump | 2026-11-16 | 2026-11-16 | 2 hrs | FY27 | 2 | 90013016 | B1 | 1000150465 | 16.11.2026 | 8000 | CLB-MP-DRLL-DR3110-GRSYST-ALBPP | 4200 | 30594 | 6871 | CLB-MP-DRLL-DR3110-GRSYST-ALBPP90013016
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Jack Leg DE CS | 2026-11-21 | 2026-11-21 | 16 hrs | FY27 | 20 | 90011674 | 1 | 1000098218 | 21.11.2026 | 15000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRR | 6300 | 69618 | 12921 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRR90011674
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Rod Thread lube Pump | 2026-11-23 | 2026-11-23 | 2 hrs | FY27 | 2 | 90011732 | 1 | 1000098265 | 25.06.2027 | 10000 | CLB-MP-DRLL-DR060 -GRSYST-RTLPP | 6300 | 69618 | 56678 | CLB-MP-DRLL-DR060 -GRSYST-RTLPP90011732
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2026-11-23 | 2026-11-24 | 21 hrs | FY27 | 31.5 | 90017118 | 1 | 1000145852 | 14.05.2026 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Power Pack Module | 2026-11-23 | 2026-11-30 | 162 hrs | FY27 | 294 | 90029571 | A1 | 1000295338 | 19.11.2026 | 20000 | CLB-MP-DRLL-DR060 -ENGINE | 6300 | 69618 | 16445 | CLB-MP-DRLL-DR060 -ENGINE90029571
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Service 12M Air Conditioner | 2026-11-28 | 2026-11-28 | 6 hrs | FY27 | 12 | 90028298 | A1 | 1000296528 | 28.11.2026 | 12 Monthly | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN90028298
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Overhaul 24M Air Conditioner | 2026-11-28 | 2026-11-28 | 12 hrs | FY27 | 24 | 90028299 | A1 | 1000283244 | 28.11.2026 | 24 Monthly | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN90028299
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast ADS Hardware | 2026-12-07 | 2026-12-09 | 49 hrs | FY27 | 49 | 90029071 | A1 | 1000294929 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW90029071
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Deck ADS Elec Hardware | 2026-12-07 | 2026-12-07 | 10 hrs | FY27 | 10 | 90029060 | A1 | 1000294930 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-ADSMF | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-ADSMF90029060
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cabin ADS Components | 2026-12-07 | 2026-12-09 | 58.5 hrs | FY27 | 58.5 | 90029058 | A1 | 1000294933 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-HMIJK | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-HMIJK90029058
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS Field Instruments | 2026-12-07 | 2026-12-07 | 7.5 hrs | FY27 | 7.5 | 90029064 | A1 | 1000294934 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS90029064
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS 3D Sensor Harness | 2026-12-07 | 2026-12-07 | 2 hrs | FY27 | 2 | 90029068 | A1 | 1000294937 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR90029068
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS LiDAR | 2026-12-07 | 2026-12-07 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000294939 | 09.12.2026 | 5000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS Harnesses | 2026-12-07 | 2026-12-09 | 43.5 hrs | FY27 | 43.5 | 90029073 | A1 | 1000294940 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-ADSYST-HARNC | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-HARNC90029073
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Mast Module Midlife | 2026-12-07 | 2026-12-11 | 113 hrs | FY27 | 229 | 90030336 | A1 | 1000302810 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030336
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Idler & Recoil Gp NCS | 2026-12-07 | 2026-12-07 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303493 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-IDLLH | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-IDLLH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Idler & Recoil Gp CS | 2026-12-07 | 2026-12-07 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303509 | 14.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-IDLRH | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-IDLRH90030377
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Initial 250Hr Valve Set | 2026-12-11 | 2026-12-11 | 12 hrs | FY27 | 24 | 90016058 | A1 | 1000295339 | 11.12.2026 | 250 | CLB-MP-DRLL-DR060 -ENGINE | 6300 | 69618 | 16445 | CLB-MP-DRLL-DR060 -ENGINE90016058
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Hyd Motor Propel NCS | 2026-12-17 | 2026-12-17 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000294864 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MPRPL | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MPRPL90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Hyd Motor Propel CS | 2026-12-17 | 2026-12-17 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000294863 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MPRPR | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MPRPR90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Carrier NCS NDE | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000294881 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLF | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Carrier NCS Middle | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000294882 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLM | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Carrier NCS DE | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000294883 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLR | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos1 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294885 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF01 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos2 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294895 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF02 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos3 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294897 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF03 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos4 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294899 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF04 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos5 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294901 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF05 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos6 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294903 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF06 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos7 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294905 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF07 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos8 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294907 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF08 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos9 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294909 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF09 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos10 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294887 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF10 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos11 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294889 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF11 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos12 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294891 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF12 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos13 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294893 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF13 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Carrier CS NDE | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000294880 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRF | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Carrier CS Middle | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000294879 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRM | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Carrier CS DE | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000294878 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRR | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos1 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294884 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF01 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos2 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294894 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF02 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos3 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294896 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF03 | 6700 | 17309 | 9651 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos4 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294898 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF04 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos5 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294900 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF05 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos6 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294902 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF06 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos7 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294904 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF07 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos8 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294906 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF08 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos10 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294886 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF10 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos11 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294888 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF11 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos12 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294890 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF12 | 6700 | 17309 | 9651 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos13 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000294892 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF13 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Final Drive & Sprocket LH | 2026-12-17 | 2026-12-17 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000294852 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-TRAVEL-FDRLH | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-TRAVEL-FDRLH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Final Drive & Sprocket RH | 2026-12-17 | 2026-12-17 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000294853 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-TRAVEL-FDRRH | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-TRAVEL-FDRRH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Track Assembly NCS | 2026-12-17 | 2026-12-17 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000294914 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-TRAVEL-TRKLH | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-TRAVEL-TRKLH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Track Assembly CS | 2026-12-17 | 2026-12-17 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000294913 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-TRAVEL-TRKRH | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-TRAVEL-TRKRH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load NCS Pos14 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313290 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF14 | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF1490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos14 | 2026-12-17 | 2026-12-17 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313289 | 17.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF14 | 6700 | 17309 | 11323 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF1490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Equaliser Bar | 2026-12-18 | 2026-12-18 | 16 hrs | FY27 | 32 | 90030390 | A1 | 1000303375 | 18.12.2026 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-UNDER-EQUAL | 6700 | 17285 | 17285 | CLB-MP-DRLL-DR2130-STRUCT-UNDER-EQUAL90030390
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack LHF NDE NCS | 2026-12-19 | 2026-12-19 | 12 hrs | FY27 | 24 | 90020196 | 1 | 1000294840 | 19.12.2026 | 6000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF | 6700 | 17309 | 3262 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Battery Cables | 2026-12-21 | 2026-12-22 | 24 hrs | FY27 | 24 | 90028942 | A1 | 1000294924 | 04.05.2027 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028942
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Hose Drum Assembly | 2026-12-21 | 2026-12-21 | 8 hrs | FY27 | 16 | 90022020 | B1 | 1000236710 | 21.12.2026 | 9000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDA | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDA90022020
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack LHF NDE NCS | 2026-12-22 | 2026-12-22 | 12 hrs | FY27 | 24 | 90020196 | 1 | 1000296168 | 22.12.2026 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF | 6700 | 16830 | 9883 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Washdown Pump | 2026-12-24 | 2026-12-24 | 4 hrs | FY27 | 8 | 90030681 | A1 | 1000305579 | 24.12.2026 | 7500 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP | 6700 | 15193 | 4539 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP90030681
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Engine Valve Set | 2026-12-26 | 2026-12-26 | 8 hrs | FY27 | 16 | 90021723 | A1 | 1000268663 | 26.12.2026 | 3000 | CLB-MP-DRLL-DR3126-ENGINE | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-ENGINE90021723
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Power Pack Module Midlife | 2026-12-26 | 2026-12-29 | 85 hrs | FY27 | 129 | 90026035 | A1 | 1000268664 | 26.12.2026 | 6000 | CLB-MP-DRLL-DR3126-ENGINE | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-ENGINE90026035
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Adjust 3750Hr Valve Set | 2026-12-28 | 2026-12-28 | 10.5 hrs | FY27 | 21 | 90020402 | 1 | 1000296350 | 28.12.2026 | 3750 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack RHF NDE CS | 2027-01-01 | 2027-01-01 | 12 hrs | FY27 | 24 | 90030670 | A1 | 1000294842 | 01.01.2027 | 6000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF | 6700 | 17309 | 9936 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Wet Season Preparation | 2027-01-03 | 2027-01-04 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000311758 | 03.01.2027 | 12 Monthly | CLB-MP-DRLL-DR2132 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR213290030417
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Adjust 3750Hr Valve Set | 2027-01-03 | 2027-01-03 | 10.5 hrs | FY27 | 21 | 90020402 | 1 | 1000294850 | 03.01.2027 | 3750 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR061 | STAT DR061 48M Pressure Vessel Insp Int | 2027-01-04 | 2027-01-04 | 4 hrs | FY27 | 4 | 90014200 | A1 | 1000211250 | 04.01.2027 | 48 Monthly | CLB-MP-DRLL-DR061 -AIRSYS-ARTNK | 6300 | 43460 | 43460 | CLB-MP-DRLL-DR061 -AIRSYS-ARTNK90014200
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Adjust 3750Hr Valve Set | 2027-01-12 | 2027-01-12 | 10.5 hrs | FY27 | 21 | 90020402 | 1 | 1000296178 | 12.01.2027 | 3750 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast ADS Hardware | 2027-01-13 | 2027-01-15 | 49 hrs | FY27 | 49 | 90029071 | A1 | 1000296297 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW90029071
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Deck ADS Elec Hardware | 2027-01-13 | 2027-01-13 | 10 hrs | FY27 | 10 | 90029060 | A1 | 1000296298 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-ADSMF | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-ADSMF90029060
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cabin ADS Components | 2027-01-13 | 2027-01-15 | 58.5 hrs | FY27 | 58.5 | 90029058 | A1 | 1000296301 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-HMIJK | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-HMIJK90029058
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS Field Instruments | 2027-01-13 | 2027-01-13 | 7.5 hrs | FY27 | 7.5 | 90029064 | A1 | 1000296302 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS90029064
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS 3D Sensor Harness | 2027-01-13 | 2027-01-13 | 2 hrs | FY27 | 2 | 90029068 | A1 | 1000296305 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR90029068
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Fish Eye Camera | 2027-01-13 | 2027-01-13 | 16 hrs | FY27 | 16 | 90029067 | A1 | 1000296306 | 13.01.2027 | 10000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-HTCAM | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-HTCAM90029067
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS Harnesses | 2027-01-13 | 2027-01-15 | 43.5 hrs | FY27 | 43.5 | 90029073 | A1 | 1000296308 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-ADSYST-HARNC | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-HARNC90029073
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Hyd Motor Propel NCS | 2027-01-13 | 2027-01-13 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000296232 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MPRPL | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MPRPL90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Hyd Motor Propel CS | 2027-01-13 | 2027-01-13 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000296231 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MPRPR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MPRPR90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Mast Module Midlife | 2027-01-13 | 2027-01-17 | 113 hrs | FY27 | 229 | 90030336 | A1 | 1000302814 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030336
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Carrier NCS NDE | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296249 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLF | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Carrier NCS Middle | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296250 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLM | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Carrier NCS DE | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296251 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos1 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296253 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF01 | 6700 | 16830 | 12446 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos2 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296263 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF02 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos3 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296265 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF03 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos4 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296267 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF04 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos5 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296269 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF05 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos6 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296271 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF06 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos7 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296273 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF07 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos8 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296275 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF08 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos9 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296277 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF09 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos10 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296255 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF10 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos11 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296257 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF11 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos12 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296259 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF12 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos13 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296261 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF13 | 6700 | 16830 | 12446 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Carrier CS NDE | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296248 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRF | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Carrier CS Middle | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296247 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRM | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Carrier CS DE | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296246 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Idler & Recoil Gp CS | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303511 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-IDLRH | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-IDLRH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos1 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296252 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF01 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos2 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296262 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF02 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos3 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296264 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF03 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos4 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296266 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF04 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos5 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296268 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF05 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos6 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296270 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF06 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos7 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296272 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF07 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos8 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296274 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF08 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos9 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296276 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF09 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos10 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296254 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF10 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos11 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296256 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF11 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos12 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296258 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF12 | 6700 | 16830 | 12446 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos13 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296260 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF13 | 6700 | 16830 | 12446 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Track Assembly NCS | 2027-01-13 | 2027-01-13 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000296282 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-TRAVEL-TRKLH | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-TRAVEL-TRKLH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Track Assembly CS | 2027-01-13 | 2027-01-13 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000296281 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-TRAVEL-TRKRH | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-TRAVEL-TRKRH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Equaliser Bar | 2027-01-13 | 2027-01-13 | 16 hrs | FY27 | 32 | 90030390 | A1 | 1000303377 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-UNDER-EQUAL | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-UNDER-EQUAL90030390
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load NCS Pos14 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313294 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF14 | 6700 | 16830 | 12446 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF1490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Roller Load CS Pos14 | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313293 | 13.01.2027 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF14 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF1490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack RHF NDE CS | 2027-01-15 | 2027-01-15 | 12 hrs | FY27 | 24 | 90030670 | A1 | 1000256592 | 15.01.2027 | 6000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF | 6700 | 14786 | 2078 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS Vibration Sensors | 2027-01-16 | 2027-01-16 | 1 hr | FY27 | 1 | 90029062 | A1 | 1000294935 | 16.01.2027 | 10000 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS-DSVSN | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Fish Eye Camera | 2027-01-16 | 2027-01-16 | 16 hrs | FY27 | 16 | 90029067 | A1 | 1000294938 | 16.01.2027 | 10000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-HTCAM | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-HTCAM90029067
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Sprocket RH | 2027-01-17 | 2027-01-17 | 10 hrs | FY27 | 20 | 90020186 | 1 | 1000303014 | 17.01.2027 | 10000 | CLB-MP-DRLL-DR2131-TRAVEL-SPRKR | 6700 | 16830 | 6761 | CLB-MP-DRLL-DR2131-TRAVEL-SPRKR90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Adjust 3750Hr Valve Set | 2027-01-20 | 2027-01-20 | 10.5 hrs | FY27 | 21 | 90020402 | 1 | 1000256606 | 20.01.2027 | 3750 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Adjust 3750Hr Valve Set | 2027-01-26 | 2027-01-26 | 10.5 hrs | FY27 | 21 | 90020402 | 1 | 1000296456 | 26.01.2027 | 3750 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack LHF NDE NCS | 2027-01-31 | 2027-01-31 | 12 hrs | FY27 | 24 | 90020196 | 1 | 1000296340 | 31.01.2027 | 6000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF | 6700 | 15850 | 2485 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF90020196
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 12M Inspection Isolator Panel | 2027-02-02 | 2027-02-02 | 2 hrs | FY27 | 2 | 90022525 | A1 | 1000236546 | 02.02.2027 | 12 Monthly | CLB-MP-DRLL-DR3110-ELCTLV |  |  |  | CLB-MP-DRLL-DR3110-ELCTLV90022525
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Wet Season Preparation | 2027-02-04 | 2027-02-05 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000303398 | 04.02.2027 | 12 Monthly | CLB-MP-DRLL-DR2126 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR212690030417
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Pump Water Injection | 2027-02-09 | 2027-02-09 | 2 hrs | FY27 | 2 | 90011733 | 1 | 1000098266 | 09.02.2027 | 5000 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP | 6300 | 69618 | 1540 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP90011733
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cyl Mast Raise NCS | 2027-02-10 | 2027-02-10 | 16 hrs | FY27 | 32 | 90030659 | A1 | 1000294847 | 10.02.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYL | 6700 | 17309 | 11323 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYL90030659
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack RHF NDE CS | 2027-02-13 | 2027-02-13 | 12 hrs | FY27 | 24 | 90030670 | A1 | 1000296448 | 13.02.2027 | 6000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF | 6700 | 15193 | 2198 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF90030670
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Pump Water Injection | 2027-02-15 | 2027-02-15 | 2 hrs | FY27 | 2 | 90016932 | 1 | 1000152195 | 15.02.2027 | 5000 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP | 6300 | 43398 | 240 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP90016932
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | STAT DR2130 Repl Receiver PRV | 2027-02-16 | 2027-02-16 | 1.5 hrs | FY27 | 1.5 | 90026270 | A1 | 1000294918 | 16.02.2027 | 18 Monthly | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK | 6700 | 17370 | 17370 | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK90026270
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 EncoderHarness Cab to Aframe Repl | 2027-02-16 | 2027-02-16 | 6 hrs | FY27 | 6 | 90036144 | A1 | 1000365257 | 16.02.2027 | 5000 | CLB-MP-DRLL-DR061 -ADSYST-HARNC | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ADSYST-HARNC90036144
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Wet Season Preparation | 2027-02-21 | 2027-02-22 | 22.5 hrs | FY27 | 22.5 | 90030417 | 1 | 1000311757 | 21.02.2027 | 12 Monthly | CLB-MP-DRLL-DR2131 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR213190030417
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Main Air Compressor LP | 2027-02-23 | 2027-02-24 | 24 hrs | FY27 | 48 | 90020192 | 1 | 1000296229 | 23.02.2027 | 15000 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR | 6700 | 16830 | 11673 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR90020192
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2027-02-27 | 2027-02-27 | 1 hr | FY27 | 1 | 90020876 | A1 | 1000237255 | 27.02.2027 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 EncoderHarness Cab to Aframe Repl | 2027-02-27 | 2027-02-27 | 6 hrs | FY27 | 6 | 90036144 | A1 | 1000365256 | 27.02.2027 | 5000 | CLB-MP-DRLL-DR060 -ADSYST-HARNC | 6300 | 69618 | 1221 | CLB-MP-DRLL-DR060 -ADSYST-HARNC90036144
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 6M Static Line Inspection | 2027-03-01 | 2027-03-01 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000296315 | 01.03.2027 | 6 Monthly | CLB-MP-DRLL-DR2132-STRUCT |  |  |  | CLB-MP-DRLL-DR2132-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 6M Static Line Inspection | 2027-03-01 | 2027-03-01 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000296441 | 01.03.2027 | 6 Monthly | CLB-MP-DRLL-DR2133-STRUCT |  |  |  | CLB-MP-DRLL-DR2133-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 6M Static Line Inspection | 2027-03-01 | 2027-03-01 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000294755 | 01.03.2027 | 6 Monthly | CLB-MP-DRLL-DR2130-STRUCT |  |  |  | CLB-MP-DRLL-DR2130-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 6M Static Line Inspection | 2027-03-01 | 2027-03-01 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000296163 | 01.03.2027 | 6 Monthly | CLB-MP-DRLL-DR2131-STRUCT |  |  |  | CLB-MP-DRLL-DR2131-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 6M Static Line Inspection | 2027-03-01 | 2027-03-01 | 4 hrs | FY27 | 4 | 90013246 | A1 | 1000256585 | 01.03.2027 | 6 Monthly | CLB-MP-DRLL-DR2126-STRUCT |  |  |  | CLB-MP-DRLL-DR2126-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast ADS Hardware | 2027-03-06 | 2027-03-08 | 49 hrs | FY27 | 49 | 90029071 | A1 | 1000296429 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW90029071
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Deck ADS Elec Hardware | 2027-03-06 | 2027-03-06 | 10 hrs | FY27 | 10 | 90029060 | A1 | 1000296430 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-ADSMF | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-ADSMF90029060
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cabin ADS Components | 2027-03-06 | 2027-03-08 | 58.5 hrs | FY27 | 58.5 | 90029058 | A1 | 1000296433 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-HMIJK | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-HMIJK90029058
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS Field Instruments | 2027-03-06 | 2027-03-06 | 7.5 hrs | FY27 | 7.5 | 90029064 | A1 | 1000296434 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS90029064
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS 3D Sensor Harness | 2027-03-06 | 2027-03-06 | 2 hrs | FY27 | 2 | 90029068 | A1 | 1000296437 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR90029068
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS Harnesses | 2027-03-06 | 2027-03-08 | 43.5 hrs | FY27 | 43.5 | 90029073 | A1 | 1000296440 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-ADSYST-HARNC | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-HARNC90029073
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Hyd Motor Propel NCS | 2027-03-06 | 2027-03-06 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000296364 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MPRPL | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MPRPL90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Hyd Motor Propel CS | 2027-03-06 | 2027-03-06 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000296363 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MPRPR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MPRPR90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Seat Operators | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020200 | A3 | 1000296410 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-SEATS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-SEATS90020200
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Mast Module Midlife | 2027-03-06 | 2027-03-10 | 113 hrs | FY27 | 229 | 90030336 | A1 | 1000302818 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030336
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Carrier NCS NDE | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296381 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLF | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Carrier NCS Middle | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296382 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLM | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Carrier NCS DE | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296383 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Idler & Recoil Gp NCS | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303496 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-IDLLH | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-IDLLH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos1 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296385 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF01 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos2 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296395 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF02 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos3 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296397 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF03 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos4 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296399 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF04 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos5 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296401 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF05 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos6 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296403 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF06 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos7 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296405 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF07 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos8 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296407 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF08 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos9 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296409 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF09 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos10 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296387 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF10 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos11 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296389 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF11 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos12 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296391 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF12 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos13 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296393 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF13 | 6700 | 15850 | 9904 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Carrier CS NDE | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296380 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRF | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Carrier CS Middle | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296379 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRM | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Carrier CS DE | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296378 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Idler & Recoil Gp CS | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303512 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-IDLRH | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-IDLRH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos1 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296384 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF01 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos2 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296394 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF02 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos3 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296396 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF03 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos4 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296398 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF04 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos5 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296400 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF05 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos6 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296402 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF06 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos7 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296404 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF07 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos8 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296406 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF08 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos9 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296408 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF09 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos10 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296386 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF10 | 6700 | 15850 | 3585 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos11 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296388 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF11 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos12 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296390 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF12 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos13 | 2027-03-06 | 2027-03-06 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296392 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF13 | 6700 | 15850 | 13055 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Final Drive & Sprocket LH | 2027-03-06 | 2027-03-06 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000296352 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-TRAVEL-FDRLH | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-TRAVEL-FDRLH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Final Drive & Sprocket RH | 2027-03-06 | 2027-03-06 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000296353 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-TRAVEL-FDRRH | 6700 | 15850 | 8291 | CLB-MP-DRLL-DR2132-TRAVEL-FDRRH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Track Assembly NCS | 2027-03-06 | 2027-03-06 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000296414 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-TRAVEL-TRKLH | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-TRAVEL-TRKLH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Track Assembly CS | 2027-03-06 | 2027-03-06 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000296413 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-TRAVEL-TRKRH | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-TRAVEL-TRKRH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Equaliser Bar | 2027-03-06 | 2027-03-06 | 16 hrs | FY27 | 32 | 90030390 | A1 | 1000303378 | 06.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-UNDER-EQUAL | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-STRUCT-UNDER-EQUAL90030390
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Engine Valve Set | 2027-03-07 | 2027-03-07 | 8 hrs | FY27 | 16 | 90016042 | B1 | 1000230306 | 07.03.2027 | 3000 | CLB-MP-DRLL-DR3110-ENGINE | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-ENGINE90016042
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load NCS Pos14 | 2027-03-08 | 2027-03-08 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313296 | 08.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF14 | 6700 | 15827 | 15827 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF1490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Roller Load CS Pos14 | 2027-03-08 | 2027-03-08 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313295 | 08.03.2027 | 20000 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF14 | 6700 | 15827 | 13055 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF1490020188
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Lubrication Air Pump | 2027-03-10 | 2027-03-10 | 2 hrs | FY27 | 2 | 90012947 | A1 | 1000150433 | 10.03.2027 | 6000 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-PALUB | 4200 | 30612 | 9932 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-PALUB90012947
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Rod Thread lube Pump | 2027-03-10 | 2027-03-10 | 2 hrs | FY27 | 2 | 90013018 | B1 | 1000150467 | 10.03.2027 | 6000 | CLB-MP-DRLL-DR3110-GRSYST-RTLPP | 4200 | 30594 | 208 | CLB-MP-DRLL-DR3110-GRSYST-RTLPP90013018
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Operators Seat | 2027-03-10 | 2027-03-10 | 2 hrs | FY27 | 2 | 90012992 | B1 | 1000150457 | 10.03.2027 | 6000 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-SEATS | 4200 | 30594 | 8770 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-SEATS90012992
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Drive Shaft Pump Drive | 2027-03-12 | 2027-03-12 | 6 hrs | FY27 | 12 | 90028862 | A1 | 1000294870 | 12.03.2027 | 5000 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT90028862
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Tower Raise NCS | 2027-03-15 | 2027-03-15 | 16 hrs | FY27 | 20 | 90011666 | 1 | 1000233129 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYL90011666
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Tower Raise CS | 2027-03-15 | 2027-03-15 | 16 hrs | FY27 | 20 | 90011667 | 1 | 1000233128 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYR90011667
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Hyd Motor Screw Jack NCS | 2027-03-15 | 2027-03-15 | 1 hr | FY27 | 1 | 90022221 | A1 | 1000232630 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTL90022221
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Hyd Motor Screw Jack CS | 2027-03-15 | 2027-03-15 | 1 hr | FY27 | 1 | 90022221 | A1 | 1000232629 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTR90022221
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Sheaves & Cables | 2027-03-15 | 2027-03-18 | 70 hrs | FY27 | 140 | 90029857 | A1 | 1000303723 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER | 6300 | 69618 | 25954 | CLB-MP-DRLL-DR060 -STRUCT-TOWER90029857
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Tower Cylinders | 2027-03-15 | 2027-03-16 | 34 hrs | FY27 | 58 | 90029866 | A1 | 1000303725 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER | 6300 | 69618 | 25954 | CLB-MP-DRLL-DR060 -STRUCT-TOWER90029866
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Grbx Powerhead Midlife | 2027-03-15 | 2027-03-15 | 6 hrs | FY27 | 6 | 90029861 | A1 | 1000303724 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PWRHD | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PWRHD90029861
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Rod Support | 2027-03-15 | 2027-03-16 | 24 hrs | FY27 | 36 | 90022208 | A1 | 1000232620 | 15.03.2027 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-RDSPT | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-RDSPT90022208
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Hyd Motor Fan Hyd Cooler | 2027-03-16 | 2027-03-16 | 6 hrs | FY27 | 6 | 90011697 | 1 | 1000098202 | 16.03.2027 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MFMCA | 6300 | 69618 | 18158 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MFMCA90011697
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack LHF NDE NCS | 2027-03-16 | 2027-03-16 | 12 hrs | FY27 | 24 | 90020196 | 1 | 1000256590 | 16.03.2027 | 6000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF | 6700 | 14786 | 889 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF90020196
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Jack Leg DE NCS | 2027-03-17 | 2027-03-17 | 12 hrs | FY27 | 16 | 90011673 | 1 | 1000098217 | 17.03.2027 | 15000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYLR | 6300 | 69618 | 10885 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYLR90011673
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS LiDAR | 2027-03-21 | 2027-03-21 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000296307 | 21.03.2027 | 5000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR | 6700 | 16830 | 11072 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Drive Shaft Pump Drive | 2027-03-21 | 2027-03-21 | 6 hrs | FY27 | 12 | 90028862 | A1 | 1000296238 | 21.03.2027 | 5000 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT90028862
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Main Feed Chain | 2027-03-22 | 2027-03-22 | 8 hrs | FY27 | 16 | 90012999 | B1 | 1000150460 | 22.03.2027 | 2500 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH | 4200 | 30594 | 2427 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH90012999
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 12M Air Cond Rencool Service | 2027-03-23 | 2027-03-23 | 8 hrs | FY27 | 16 | 90018579 | 1 | 1000180963 | 23.03.2027 | 12 Monthly | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN |  |  |  | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN90018579
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 12M Air Conditioner Service | 2027-03-23 | 2027-03-24 | 18 hrs | FY27 | 36 | 90018564 | 1 | 1000180532 | 23.03.2027 | 12 Monthly | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN |  |  |  | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN90018564
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Washdown Pump | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90030681 | A1 | 1000305578 | 27.03.2027 | 7500 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP | 6700 | 15850 | 2962 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Hyd Motor Propel NCS | 2027-03-27 | 2027-03-27 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000256622 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MPRPL | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MPRPL90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Hyd Motor Propel CS | 2027-03-27 | 2027-03-27 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000256621 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MPRPR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MPRPR90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Seat Operators | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020200 | A3 | 1000256667 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-SEATS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-SEATS90020200
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Mast Module Midlife | 2027-03-27 | 2027-03-31 | 113 hrs | FY27 | 229 | 90030336 | A1 | 1000302774 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030336
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Carrier NCS NDE | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000256638 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLF | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Carrier NCS Middle | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000256639 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLM | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Carrier NCS DE | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000256640 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Idler & Recoil Gp NCS | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303487 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-IDLLH | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-IDLLH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos1 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256642 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF01 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos2 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256652 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF02 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos3 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256654 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF03 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos4 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256656 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF04 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos5 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256658 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF05 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos6 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256660 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF06 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos7 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256662 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF07 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos8 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256664 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF08 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos9 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256666 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF09 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos10 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256644 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF10 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos11 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256646 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF11 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos12 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256648 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF12 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load NCS Pos13 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256650 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF13 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Carrier CS NDE | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000256637 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRF | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Carrier CS Middle | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000256636 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRM | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Carrier CS DE | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000256635 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Idler & Recoil Gp CS | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303503 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-IDLRH | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-IDLRH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos2 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256651 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF02 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos3 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256653 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF03 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos4 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256655 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF04 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos5 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256657 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF05 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos6 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256659 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF06 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos7 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256661 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF07 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos8 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256663 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF08 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos9 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256665 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF09 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos10 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256643 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF10 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos11 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256645 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF11 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos12 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256647 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF12 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos13 | 2027-03-27 | 2027-03-27 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000256649 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF13 | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Final Drive & Sprocket LH | 2027-03-27 | 2027-03-27 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000256610 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-TRAVEL-FDRLH | 6700 | 14786 | 2066 | CLB-MP-DRLL-DR2126-TRAVEL-FDRLH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Final Drive & Sprocket RH | 2027-03-27 | 2027-03-27 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000256611 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-TRAVEL-FDRRH | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-TRAVEL-FDRRH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Track Assembly NCS | 2027-03-27 | 2027-03-27 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000256671 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-TRAVEL-TRKLH | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-TRAVEL-TRKLH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Track Assembly CS | 2027-03-27 | 2027-03-27 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000256670 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-TRAVEL-TRKRH | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-TRAVEL-TRKRH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS Harnesses | 2027-03-27 | 2027-03-29 | 43.5 hrs | FY27 | 43.5 | 90029073 | A1 | 1000290915 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-ADSYST-HARNC | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-HARNC90029073
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS Field Instruments | 2027-03-27 | 2027-03-27 | 7.5 hrs | FY27 | 7.5 | 90029064 | A1 | 1000290909 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS90029064
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast ADS Hardware | 2027-03-27 | 2027-03-29 | 49 hrs | FY27 | 49 | 90029071 | A1 | 1000290904 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW90029071
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cabin ADS Components | 2027-03-27 | 2027-03-29 | 58.5 hrs | FY27 | 58.5 | 90029058 | A1 | 1000290908 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-HMIJK | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-HMIJK90029058
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Deck ADS Elec Hardware | 2027-03-27 | 2027-03-27 | 10 hrs | FY27 | 10 | 90029060 | A1 | 1000290905 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-ADSMF | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-ADSMF90029060
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS 3D Sensor | 2027-03-27 | 2027-03-27 | 2 hrs | FY27 | 2 | 90029068 | A1 | 1000290912 | 27.03.2027 | 20000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR90029068
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Equaliser Bar | 2027-03-28 | 2027-03-28 | 16 hrs | FY27 | 32 | 90030390 | A1 | 1000303372 | 28.03.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-UNDER-EQUAL | 6700 | 14763 | 14763 | CLB-MP-DRLL-DR2126-STRUCT-UNDER-EQUAL90030390
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack LHF NDE NCS | 2027-04-02 | 2027-04-02 | 12 hrs | FY27 | 24 | 90020196 | 1 | 1000296446 | 02.04.2027 | 6000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF | 6700 | 15193 | 1223 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF90020196
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Power Pack Quarter Life | 2027-04-02 | 2027-04-04 | 44 hrs | FY27 | 68 | 90029574 | A1 | 1000295365 | 02.04.2027 | 5000 | CLB-MP-DRLL-DR061 -ENGINE | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ENGINE90029574
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast ADS Hardware | 2027-04-04 | 2027-04-06 | 49 hrs | FY27 | 49 | 90029071 | A1 | 1000296535 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW90029071
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Deck ADS Elec Hardware | 2027-04-04 | 2027-04-04 | 10 hrs | FY27 | 10 | 90029060 | A1 | 1000296536 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-ADSMF | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-ADSMF90029060
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cabin ADS Components | 2027-04-04 | 2027-04-06 | 58.5 hrs | FY27 | 58.5 | 90029058 | A1 | 1000296539 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-HMIJK | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-HMIJK90029058
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS Field Instruments | 2027-04-04 | 2027-04-04 | 7.5 hrs | FY27 | 7.5 | 90029064 | A1 | 1000296540 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS90029064
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS 3D Sensor Harness | 2027-04-04 | 2027-04-04 | 2 hrs | FY27 | 2 | 90029068 | A1 | 1000296543 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR90029068
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS Harnesses | 2027-04-04 | 2027-04-06 | 43.5 hrs | FY27 | 43.5 | 90029073 | A1 | 1000296546 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-ADSYST-HARNC | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-HARNC90029073
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Hyd Motor Propel NCS | 2027-04-04 | 2027-04-04 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000296470 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MPRPL | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MPRPL90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Hyd Motor Propel CS | 2027-04-04 | 2027-04-04 | 6 hrs | FY27 | 12 | 90020190 | 1 | 1000296469 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MPRPR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MPRPR90020190
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Seat Operators | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020200 | A3 | 1000296516 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-SEATS | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-SEATS90020200
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Mast Module Midlfie | 2027-04-04 | 2027-04-08 | 113 hrs | FY27 | 229 | 90030336 | A1 | 1000302882 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030336
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Carrier NCS NDE | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296487 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLF | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Carrier NCS Middle | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296488 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLM | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Carrier NCS DE | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296489 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Idler & Recoil Gp NCS | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303497 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-IDLLH | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-IDLLH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos1 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296491 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF01 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos2 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296501 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF02 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos3 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296503 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF03 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos4 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296505 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF04 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos5 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296507 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF05 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos6 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296509 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF06 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos7 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296511 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF07 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos8 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296513 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF08 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos9 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296515 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF09 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos10 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296493 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF10 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos11 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296495 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF11 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos12 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296497 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF12 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos13 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296499 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF13 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Carrier CS NDE | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296486 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRF | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRF90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Carrier CS Middle | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296485 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRM | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRM90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Carrier CS DE | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020189 | 1 | 1000296484 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRR90020189
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Idler & Recoil Gp CS | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90030377 | A1 | 1000303513 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-IDLRH | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-IDLRH90030377
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos1 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296490 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF01 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos2 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296500 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF02 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos3 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296502 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF03 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos4 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296504 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF04 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0490020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos5 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296506 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF05 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0590020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos6 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296508 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF06 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0690020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos7 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296510 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF07 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0790020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos8 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296512 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF08 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0890020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos9 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296514 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF09 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF0990020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos10 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296492 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF10 | 6700 | 15193 | 12396 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF1090020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos11 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296494 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF11 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF1190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos12 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296496 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF12 | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF1290020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos13 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000296498 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF13 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF1390020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Final Drive & Sprocket LH | 2027-04-04 | 2027-04-04 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000296458 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-TRAVEL-FDRLH | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-TRAVEL-FDRLH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Final Drive & Sprocket RH | 2027-04-04 | 2027-04-04 | 12 hrs | FY27 | 22 | 90020182 | 1 | 1000296459 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-TRAVEL-FDRRH | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-TRAVEL-FDRRH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Track Assembly NCS | 2027-04-04 | 2027-04-04 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000296520 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-TRAVEL-TRKLH | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-TRAVEL-TRKLH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Track Assembly CS | 2027-04-04 | 2027-04-04 | 12.5 hrs | FY27 | 24.5 | 90020187 | 1 | 1000296519 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-TRAVEL-TRKRH | 6700 | 15193 | 10303 | CLB-MP-DRLL-DR2133-TRAVEL-TRKRH90020187
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Equaliser Bar | 2027-04-04 | 2027-04-04 | 16 hrs | FY27 | 32 | 90030390 | A1 | 1000303379 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-UNDER-EQUAL | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-UNDER-EQUAL90030390
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load CS Pos14 | 2027-04-04 | 2027-04-04 | 4 hrs | FY27 | 8 | 90020188 | 1 | 1000313297 | 04.04.2027 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF14 | 6700 | 15193 | 455 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF1490020188
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Valve Drill & Propel Control | 2027-04-06 | 2027-04-06 | 6 hrs | FY27 | 6 | 90016906 | 1 | 1000152161 | 06.04.2027 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDPC | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDPC90016906
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 12M Air Conditioner Service | 2027-04-11 | 2027-04-12 | 18 hrs | FY27 | 36 | 90018564 | 1 | 1000180531 | 11.04.2027 | 12 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018564
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 12M Air Cond Rencool Service | 2027-04-11 | 2027-04-11 | 8 hrs | FY27 | 16 | 90018579 | 1 | 1000180961 | 11.04.2027 | 12 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018579
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Drive Shaft Pump Drive | 2027-04-14 | 2027-04-14 | 6 hrs | FY27 | 12 | 90028862 | A1 | 1000296476 | 14.04.2027 | 5000 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG-DRSHT | 6700 | 15193 | 9653 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG-DRSHT90028862
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 PV271 Hydraulic Tune | 2027-04-15 | 2027-04-16 | 21 hrs | FY27 | 31.5 | 90017118 | 1 | 1000206785 | 15.04.2027 | 3000 | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190017118
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Timing Chain Maintenance | 2027-04-18 | 2027-04-18 | 7 hrs | FY27 | 14 | 90022023 | A1 | 1000361221 | 18.04.2027 | 3000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP90022023
D65 | Onsite PM | Drills | Fortescue | DR3126 | STAT DR3126 24M Pressure Vessel Insp Ext | 2027-04-21 | 2027-04-21 | 2 hrs | FY27 | 2 | 90025808 | A1 | 1000366607 | 21.04.2027 | 24 Monthly | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK | 4400 | 17932 | 4496 | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK90025808
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2027-04-26 | 2027-04-27 | 21 hrs | FY27 | 31.5 | 90017118 | 1 | 1000145852 | 26.04.2027 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | STAT DR2132 Repl Receiver PRV | 2027-04-27 | 2027-04-27 | 1.5 hrs | FY27 | 1.5 | 90026270 | A1 | 1000323451 | 27.04.2027 | 18 Monthly | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK90026270
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | STAT DR2130 48M Pressure Vessel Insp Int | 2027-04-27 | 2027-04-27 | 4 hrs | FY27 | 4 | 90014200 | A1 | 1000294919 | 27.04.2027 | 48 Monthly | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK | 6700 | 17370 | 17370 | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK90014200
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Compressor Coupling | 2027-05-02 | 2027-05-02 | 12 hrs | FY27 | 24 | 90030404 | A1 | 1000303544 | 02.05.2027 | 7500 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR-COUPL | 6700 | 17309 | 1426 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR-COUPL90030404
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast Cables | 2027-05-02 | 2027-05-03 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302808 | 02.05.2027 | 2500 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030334
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Water & Fuel Tank Mount | 2027-05-09 | 2027-05-09 | 10 hrs | FY27 | 20 | 90017443 | 1 | 1000160295 | 09.05.2027 | 12 Monthly | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK | 6300 | 69618 | 17116 | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK90017443
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Seat Operators | 2027-05-14 | 2027-05-14 | 4 hrs | FY27 | 8 | 90020200 | A3 | 1000294910 | 14.05.2027 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-SEATS | 6700 | 17309 | 14596 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-SEATS90020200
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 XLF Repl Main Feed Chain | 2027-05-21 | 2027-05-21 | 8 hrs | FY27 | 16 | 90021711 | A1 | 1000237290 | 21.05.2027 | 2500 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH | 4400 | 17885 | 1481 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH90021711
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Cables | 2027-05-29 | 2027-05-30 | 20 hrs | FY27 | 60 | 90030334 | A1 | 1000302812 | 29.05.2027 | 2500 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Drive Shaft Pump Drive | 2027-05-29 | 2027-05-29 | 6 hrs | FY27 | 12 | 90028862 | A1 | 1000287877 | 29.05.2027 | 5000 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG-DRSHT | 6700 | 14786 | 3637 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG-DRSHT90028862
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS LiDAR | 2027-05-31 | 2027-05-31 | 5 hrs | FY27 | 8 | 90029065 | A1 | 1000290914 | 31.05.2027 | 5000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Overhaul 24M Air Conditioner | 2027-06-15 | 2027-06-15 | 12 hrs | FY27 | 24 | 90028299 | A1 | 1000294923 | 15.06.2027 | 24 Monthly | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN | 6700 | 17309 | 6755 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN90028299
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Jack Leg DE CS | 2027-06-21 | 2027-06-21 | 4 hrs | FY27 | 8 | 90015959 | A1 | 1000152150 | 21.06.2027 | 15000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRR | 6300 | 43398 | 9387 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRR90015959
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Main Air Compressor LP | 2027-06-26 | 2027-06-27 | 24 hrs | FY27 | 48 | 90020192 | 1 | 1000256619 | 26.06.2027 | 15000 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR | 6700 | 14786 | 8105 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR90020192
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Operators Seat | 2027-06-27 | 2027-06-27 | 12 hrs | FY27 | 24 | 90011710 | A2 | 1000098238 | 27.06.2027 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-SEATS | 6300 | 69618 | 14152 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-SEATS90011710
| Onsite PM | Drills | Fortescue |  | FY28 - DRILLS - COMPONENTS DURING PM | 2027-07-01 |  |  | FY28
| Onsite PM | Drills | Fortescue | MOC | MAJOR ON CONDITION | 2027-07-01 | 2028-06-30 | 365 days | FY28
| Onsite PM | Drills | Fortescue | MOC | JULY | 2027-07-01 | 2027-07-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | AUGUST | 2027-08-01 | 2027-08-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | SEPTEMBER | 2027-09-01 | 2027-09-30 | 29 days | FY28
| Onsite PM | Drills | Fortescue | MOC | OCTOBER | 2027-10-01 | 2027-10-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | NOVEMBER | 2027-11-01 | 2027-11-30 | 29 days | FY28
| Onsite PM | Drills | Fortescue | MOC | DECEMBER | 2027-12-01 | 2027-12-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | JANUARY | 2028-01-01 | 2028-01-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | FEBRUARY | 2028-02-01 | 2028-02-28 | 27 days | FY28
| Onsite PM | Drills | Fortescue | MOC | MARCH | 2028-03-01 | 2028-03-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | APRIL | 2028-04-01 | 2028-04-30 | 29 days | FY28
| Onsite PM | Drills | Fortescue | MOC | MAY | 2028-05-01 | 2028-05-31 | 30 days | FY28
| Onsite PM | Drills | Fortescue | MOC | JUNE | 2028-06-01 | 2028-06-30 | 29 days | FY28
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Track Frame Module LH | 2027-07-01 | 2027-07-01 | 16 hrs | FY28 | 28 | 90021739 | A1 | 1000237336 | 29.05.2027 | 12000 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL | 4400 | 17885 | 8631 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL90021739
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Track Frame Module RH | 2027-07-01 | 2027-07-01 | 16 hrs | FY28 | 28 | 90021741 | A1 | 1000237351 | 29.05.2027 | 12000 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR | 4400 | 17885 | 8631 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR90021741
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS Vibration Sensors | 2027-07-01 | 2027-07-01 | 1 hr | FY28 | 1 | 90029062 | A1 | 1000296303 | 29.04.2027 | 10000 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS-DSVSN | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Washdown Pump | 2027-07-01 | 2027-07-01 | 4 hrs | FY28 | 8 | 90030681 | A1 | 1000305736 | 26.06.2027 | 7500 | CLB-MP-DRLL-DR2131-DSTSUP-WSHPP | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Water Inj | 2027-07-08 | 2027-07-08 | 2 hrs | FY28 | 4 | 90031899 | A1 | 1000315429 | 08.07.2027 | 7500 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP | 6700 | 14786 | 7896 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Drive Shaft Pump Drive | 2027-07-16 | 2027-07-16 | 6 hrs | FY28 | 12 | 90028862 | A1 | 1000296370 | 16.07.2027 | 5000 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG-DRSHT | 6700 | 15850 | 8503 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG-DRSHT90028862
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Water & Fuel Tank Mount | 2027-07-19 | 2027-07-19 | 10 hrs | FY28 | 20 | 90017443 | 1 | 1000160296 | 19.07.2027 | 12 Monthly | CLB-MP-DRLL-DR061 -DSTSUP-WTTNK |  |  |  | CLB-MP-DRLL-DR061 -DSTSUP-WTTNK90017443
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Adjust 3750Hr Valve Set | 2027-07-20 | 2027-07-20 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000296350 | 20.07.2027 | 3750 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Engine Midlife Complete | 2027-07-20 | 2027-07-21 | 36 hrs | FY28 | 54 | 90029233 | A1 | 1000296351 | 20.07.2027 | 7500 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90029233
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Cables | 2027-07-20 | 2027-07-21 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302816 | 20.07.2027 | 2500 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Fish Eye Camera | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 16 | 90029067 | A1 | 1000290913 | 22.07.2027 | 10000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-HTCAM | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-HTCAM90029067
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Pump Water Inj | 2027-07-27 | 2027-07-27 | 2 hrs | FY28 | 4 | 90031899 | A1 | 1000315434 | 27.07.2027 | 7500 | CLB-MP-DRLL-DR2133-DSTSUP-WTRPP | 6700 | 15193 | 610 | CLB-MP-DRLL-DR2133-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Engine Midlife Complete | 2027-07-27 | 2027-07-28 | 36 hrs | FY28 | 54 | 90029233 | A1 | 1000294851 | 27.07.2027 | 7500 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90029233
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Adjust 3750Hr Valve Set | 2027-07-27 | 2027-07-27 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000294850 | 27.07.2027 | 3750 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS Vibration Sensors | 2027-07-31 | 2027-07-31 | 1 hr | FY28 | 1 | 90029062 | A1 | 1000290910 | 31.07.2027 | 10000 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS-DSVSN | 6700 | 14786 | 2463 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS-DSVSN90029062
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Boom Module Assembly | 2027-07-31 | 2027-08-01 | 26 hrs | FY28 | 50 | 90021999 | B1 | 1000230858 | 31.07.2027 | 18000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BMASY | 4200 | 30594 | 13910 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BMASY90021999
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Pump Water Inj | 2027-08-05 | 2027-08-05 | 2 hrs | FY28 | 4 | 90031899 | A1 | 1000315432 | 05.08.2027 | 7500 | CLB-MP-DRLL-DR2131-DSTSUP-WTRPP | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Engine Midlife Complete | 2027-08-05 | 2027-08-06 | 36 hrs | FY28 | 54 | 90029233 | A1 | 1000296179 | 05.08.2027 | 7500 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90029233
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Adjust 3750Hr Valve Set | 2027-08-05 | 2027-08-05 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000296178 | 05.08.2027 | 3750 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90020402
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Water Injection | 2027-08-09 | 2027-08-09 | 4 hrs | FY28 | 4 | 90021716 | A1 | 1000237308 | 09.08.2027 | 6000 | CLB-MP-DRLL-DR3126-DSTSUP-WTRPP | 4400 | 17885 | 7491 | CLB-MP-DRLL-DR3126-DSTSUP-WTRPP90021716
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Cyl Jack levelling Rear | 2027-08-09 | 2027-08-09 | 3 hrs | FY28 | 6 | 90021661 | A1 | 1000237271 | 09.08.2027 | 12000 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-JLCYR | 4400 | 17885 | 7491 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-JLCYR90021661
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2027-08-10 | 2027-08-11 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302772 | 10.08.2027 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Primary Water Tank Anodes | 2027-08-11 | 2027-08-11 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377545 | 11.08.2027 | 10000 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKP | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Secondary Water Tank Anodes | 2027-08-11 | 2027-08-11 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377475 | 11.08.2027 | 10000 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKS90037834
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2027-08-12 | 2027-08-12 | 1 hr | FY28 | 1 | 90020876 | A1 | 1000237255 | 12.08.2027 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Engine Midlife Complete | 2027-08-12 | 2027-08-13 | 36 hrs | FY28 | 54 | 90029233 | A1 | 1000293342 | 12.08.2027 | 7500 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90029233
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Adjust 3750Hr Valve Set | 2027-08-12 | 2027-08-12 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000256606 | 12.08.2027 | 3750 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Tower Raise NCS | 2027-08-16 | 2027-08-16 | 16 hrs | FY28 | 20 | 90011666 | 1 | 1000233139 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYL | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYL90011666
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Tower Raise CS | 2027-08-16 | 2027-08-16 | 16 hrs | FY28 | 20 | 90011667 | 1 | 1000233138 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYR | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYR90011667
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Hyd Motor Screw Jack NCS | 2027-08-16 | 2027-08-16 | 1 hr | FY28 | 1 | 90022221 | A1 | 1000232658 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTL | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTL90022221
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Hyd Motor Screw Jack CS | 2027-08-16 | 2027-08-16 | 1 hr | FY28 | 1 | 90022221 | A1 | 1000232657 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTR | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTR90022221
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Sheaves & Cables | 2027-08-16 | 2027-08-19 | 70 hrs | FY28 | 140 | 90029857 | A1 | 1000303730 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER90029857
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Tower Cylinders | 2027-08-16 | 2027-08-17 | 34 hrs | FY28 | 58 | 90029866 | A1 | 1000303732 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER90029866
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Grbx Powerhead Midlife | 2027-08-16 | 2027-08-16 | 6 hrs | FY28 | 6 | 90029861 | A1 | 1000303731 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PWRHD | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PWRHD90029861
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Rod Support | 2027-08-16 | 2027-08-17 | 24 hrs | FY28 | 36 | 90022208 | A1 | 1000232648 | 16.08.2027 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-RDSPT | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-RDSPT90022208
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Roller Load CS Pos1 | 2027-08-17 | 2027-08-17 | 4 hrs | FY28 | 8 | 90020188 | 1 | 1000256641 | 17.08.2027 | 20000 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF01 | 6700 | 14786 | 12160 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF0190020188
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Compressor Coupling | 2027-08-18 | 2027-08-18 | 12 hrs | FY28 | 24 | 90030404 | A1 | 1000303548 | 18.08.2027 | 7500 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR-COUPL | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR-COUPL90030404
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Engine Midlife Complete | 2027-08-18 | 2027-08-19 | 36 hrs | FY28 | 54 | 90029233 | A1 | 1000296457 | 18.08.2027 | 7500 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90029233
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Adjust 3750Hr Valve Set | 2027-08-18 | 2027-08-18 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000296456 | 18.08.2027 | 3750 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Cables | 2027-08-18 | 2027-08-19 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302880 | 18.08.2027 | 2500 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Primary Water Tank Anodes | 2027-08-19 | 2027-08-19 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377547 | 19.08.2027 | 10000 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKP | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Secondary Water Tank Anodes | 2027-08-19 | 2027-08-19 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377477 | 19.08.2027 | 10000 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Primary Water Tank Anodes | 2027-08-22 | 2027-08-22 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377542 | 22.08.2027 | 10000 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKP | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Secondary Water Tank Anodes | 2027-08-22 | 2027-08-22 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377473 | 22.08.2027 | 10000 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKS90037834
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Power Pack Quarter Life | 2027-08-23 | 2027-08-25 | 44 hrs | FY28 | 68 | 90029578 | A1 | 1000295361 | 23.08.2027 | 5000 | CLB-MP-DRLL-DR060 -ENGINE | 6300 | 69618 | 16445 | CLB-MP-DRLL-DR060 -ENGINE90029578
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS LiDAR | 2027-08-24 | 2027-08-24 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000296545 | 24.08.2027 | 5000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 6M Static Line Inspection | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000296315 | 01.09.2027 | 6 Monthly | CLB-MP-DRLL-DR2132-STRUCT |  |  |  | CLB-MP-DRLL-DR2132-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 6M Static Line Inspection | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000296441 | 01.09.2027 | 6 Monthly | CLB-MP-DRLL-DR2133-STRUCT |  |  |  | CLB-MP-DRLL-DR2133-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 6M Static Line Inspection | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000294755 | 01.09.2027 | 6 Monthly | CLB-MP-DRLL-DR2130-STRUCT |  |  |  | CLB-MP-DRLL-DR2130-STRUCT90013246
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Engine Valve Set | 2027-09-01 | 2027-09-01 | 8 hrs | FY28 | 16 | 90021723 | A1 | 1000268663 | 01.09.2027 | 3000 | CLB-MP-DRLL-DR3126-ENGINE | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-ENGINE90021723
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack RHF NDE CS | 2027-09-01 | 2027-09-01 | 12 hrs | FY28 | 24 | 90030670 | A1 | 1000296170 | 01.09.2027 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF | 6700 | 16830 | 4546 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 6M Static Line Inspection | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000296163 | 01.09.2027 | 6 Monthly | CLB-MP-DRLL-DR2131-STRUCT |  |  |  | CLB-MP-DRLL-DR2131-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 6M Static Line Inspection | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000256585 | 01.09.2027 | 6 Monthly | CLB-MP-DRLL-DR2126-STRUCT |  |  |  | CLB-MP-DRLL-DR2126-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | STAT DR2126 Repl Receiver PRV | 2027-09-08 | 2027-09-08 | 1.5 hrs | FY28 | 1.5 | 90026270 | A1 | 1000259185 | 08.09.2027 | 18 Monthly | CLB-MP-DRLL-DR2126-AIRSYS-ARTNK | 6700 | 14849 | 2463 | CLB-MP-DRLL-DR2126-AIRSYS-ARTNK90026270
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Hyd Motor Feed | 2027-09-08 | 2027-09-08 | 6 hrs | FY28 | 6 | 90022024 | B1 | 1000231374 | 08.09.2027 | 6000 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MFEED | 4200 | 30594 | 1634 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MFEED90022024
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Valve Oscillation Relief | 2027-09-08 | 2027-09-08 | 4 hrs | FY28 | 4 | 90012979 | B1 | 1000150453 | 08.09.2027 | 12000 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOSR | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOSR90012979
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Valve Oscillation | 2027-09-08 | 2027-09-08 | 4 hrs | FY28 | 4 | 90012978 | B1 | 1000150452 | 08.09.2027 | 12000 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOST | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOST90012978
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Feed Chain Sprockets | 2027-09-08 | 2027-09-08 | 12 hrs | FY28 | 24 | 90022028 | B1 | 1000231377 | 08.09.2027 | 6000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHS | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHS90022028
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Hose Drum Sprocket | 2027-09-08 | 2027-09-08 | 6 hrs | FY28 | 6 | 90022031 | B1 | 1000231376 | 08.09.2027 | 6000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDS | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDS90022031
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Gearbox Power Head | 2027-09-08 | 2027-09-10 | 48 hrs | FY28 | 96 | 90012997 | B1 | 1000231378 | 08.09.2027 | 6000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-PWRHD | 4200 | 30472 | 3162 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-PWRHD90012997
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Washdown Pump | 2027-09-09 | 2027-09-09 | 4 hrs | FY28 | 8 | 90030681 | A1 | 1000305735 | 09.09.2027 | 7500 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS LiDAR | 2027-09-10 | 2027-09-10 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000294939 | 10.09.2027 | 5000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR90029065
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS PTZ Camera & LIDAR | 2027-09-13 | 2027-09-13 | 10 hrs | FY28 | 10 | 90029206 | A1 | 1000294229 | 13.09.2027 | 10000 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR-HTCAM | 6300 | 69618 | 8490 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR-HTCAM90029206
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast Cables | 2027-09-15 | 2027-09-16 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302808 | 15.09.2027 | 2500 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack RHR DE CS | 2027-09-17 | 2027-09-17 | 12 hrs | FY28 | 24 | 90030672 | A1 | 1000296343 | 17.09.2027 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRR | 6700 | 15850 | 7007 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRR90030672
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack RHF NDE CS | 2027-09-21 | 2027-09-21 | 12 hrs | FY28 | 24 | 90030670 | A1 | 1000296342 | 21.09.2027 | 6000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF | 6700 | 15850 | 4205 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Water Inj | 2027-10-01 | 2027-10-01 | 2 hrs | FY28 | 4 | 90031899 | A1 | 1000315433 | 01.10.2027 | 7500 | CLB-MP-DRLL-DR2132-DSTSUP-WTRPP | 6700 | 15850 | 7007 | CLB-MP-DRLL-DR2132-DSTSUP-WTRPP90031899
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Rod Thread Lube | 2027-10-05 | 2027-10-05 | 2 hrs | FY28 | 2 | 90021715 | A1 | 1000237320 | 05.10.2027 | 6000 | CLB-MP-DRLL-DR3126-GRSYST-RTLPP | 4400 | 17885 | 9803 | CLB-MP-DRLL-DR3126-GRSYST-RTLPP90021715
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Pressure Safety Valve Cert | 2027-10-05 | 2027-10-05 | 3 hrs | FY28 | 3 | 90021719 | A1 | 1000272908 | 05.10.2027 | 18 Monthly | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCSRL | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCSRL90021719
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 PV271 Hydraulic Tune | 2027-10-06 | 2027-10-07 | 21 hrs | FY28 | 31.5 | 90017118 | 1 | 1000206785 | 06.10.2027 | 3000 | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190017118
PV271 | Onsite PM | Drills | Fortescue | DR060 | STAT DR060 48M Pressure Vessel Insp-Int | 2027-10-09 | 2027-10-09 | 4 hrs | FY28 | 4 | 90014200 | A1 | 1000211243 | 09.10.2027 | 48 Monthly | CLB-MP-DRLL-DR060 -AIRSYS-ARTNK | 6300 | 69618 | 10169 | CLB-MP-DRLL-DR060 -AIRSYS-ARTNK90014200
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Cables | 2027-10-12 | 2027-10-13 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302812 | 12.10.2027 | 2500 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Wet Season Preparation | 2027-10-14 | 2027-10-15 | 22.5 hrs | FY28 | 22.5 | 90030417 | 1 | 1000303581 | 14.10.2027 | 12 Monthly | CLB-MP-DRLL-DR3126 | 4400 | 17885 | 17885 | CLB-MP-DRLL-DR312690030417
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | STAT DR2131 48M Pressure Vessel Insp Int | 2027-10-14 | 2027-10-14 | 4 hrs | FY28 | 4 | 90014200 | A1 | 1000323448 | 14.10.2027 | 48 Monthly | CLB-MP-DRLL-DR2131-AIRSYS-ARTNK | 6700 | 16896 | 3896 | CLB-MP-DRLL-DR2131-AIRSYS-ARTNK90014200
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Water Inj | 2027-10-16 | 2027-10-16 | 2 hrs | FY28 | 4 | 90031899 | A1 | 1000315431 | 16.10.2027 | 7500 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP | 6700 | 17309 | 6755 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP90031899
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2027-10-17 | 2027-10-18 | 21 hrs | FY28 | 31.5 | 90017118 | 1 | 1000145852 | 17.10.2027 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Wet Season Preparation | 2027-10-17 | 2027-10-18 | 22.5 hrs | FY28 | 22.5 | 90030417 | 1 | 1000365892 | 17.10.2027 | 12 Monthly | CLB-MP-DRLL-DR3110 | 5400 | 30612 | 30612 | CLB-MP-DRLL-DR311090030417
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Fish Eye Camera | 2027-10-23 | 2027-10-23 | 16 hrs | FY28 | 16 | 90029067 | A1 | 1000296438 | 23.10.2027 | 10000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-HTCAM | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-HTCAM90029067
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Main Feed Chain | 2027-10-25 | 2027-10-25 | 8 hrs | FY28 | 16 | 90012999 | B1 | 1000150460 | 25.10.2027 | 2500 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH | 4200 | 30594 | 2427 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH90012999
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Control Harnesses Chassis | 2027-10-27 | 2027-10-28 | 39 hrs | FY28 | 39 | 90029952 | A1 | 1000303820 | 27.10.2027 | 20000 | CLB-MP-DRLL-DR061 -ELCTLV-HARNS-HARCO | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ELCTLV-HARNS-HARCO90029952
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Washdown Pump | 2027-11-07 | 2027-11-07 | 4 hrs | FY28 | 8 | 90030681 | A1 | 1000305731 | 07.11.2027 | 7500 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack LHF NDE NCS | 2027-11-11 | 2027-11-11 | 12 hrs | FY28 | 24 | 90020196 | 1 | 1000294840 | 11.11.2027 | 6000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF | 6700 | 17309 | 3262 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Main Air Compressor LP | 2027-11-12 | 2027-11-13 | 24 hrs | FY28 | 48 | 90020192 | 1 | 1000296361 | 12.11.2027 | 15000 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR | 6700 | 15850 | 6250 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR90020192
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Operators Seat | 2027-11-12 | 2027-11-12 | 4 hrs | FY28 | 4 | 90021702 | A1 | 1000237296 | 12.11.2027 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-SEATS | 4400 | 17885 | 325 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-SEATS90021702
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack LHF NDE NCS | 2027-11-14 | 2027-11-14 | 12 hrs | FY28 | 24 | 90020196 | 1 | 1000296168 | 14.11.2027 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF | 6700 | 16830 | 9883 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Primary Water Tank Anodes | 2027-11-16 | 2027-11-16 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377551 | 16.11.2027 | 10000 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKP | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Secondary Water Tank Anodes | 2027-11-16 | 2027-11-16 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377481 | 16.11.2027 | 10000 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKS | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Main Hyd CS | 2027-11-17 | 2027-11-17 | 6 hrs | FY28 | 6 | 90020234 | 1 | 1000294874 | 17.11.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP2 | 6700 | 17309 | 6154 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP290020234
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Overhaul 24M Air Conditioner | 2027-11-23 | 2027-11-23 | 12 hrs | FY28 | 24 | 90028299 | A1 | 1000296529 | 23.11.2027 | 24 Monthly | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN90028299
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Service 12M Air Conditioner | 2027-11-23 | 2027-11-23 | 6 hrs | FY28 | 12 | 90028298 | A1 | 1000283243 | 23.11.2027 | 12 Monthly | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN90028298
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Power Pack Module | 2027-11-23 | 2027-11-24 | 30 hrs | FY28 | 60 | 90021957 | B1 | 1000230256 | 23.11.2027 | 12000 | CLB-MP-DRLL-DR3110-ENGINE | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-ENGINE90021957
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack RHF NDE CS | 2027-11-24 | 2027-11-24 | 12 hrs | FY28 | 24 | 90030670 | A1 | 1000294842 | 24.11.2027 | 6000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF | 6700 | 17309 | 9936 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF90030670
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Pump Water Injection | 2027-11-25 | 2027-11-25 | 2 hrs | FY28 | 2 | 90011733 | 1 | 1000098266 | 25.11.2027 | 5000 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP | 6300 | 69618 | 1540 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP90011733
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | STAT DR2131 Repl Receiver PRV | 2027-12-01 | 2027-12-01 | 1.5 hrs | FY28 | 1.5 | 90026270 | A1 | 1000323445 | 01.12.2027 | 18 Monthly | CLB-MP-DRLL-DR2131-AIRSYS-ARTNK | 6700 | 16896 | 3896 | CLB-MP-DRLL-DR2131-AIRSYS-ARTNK90026270
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Valve Dual Counter Balance | 2027-12-01 | 2027-12-01 | 2 hrs | FY28 | 2 | 90016902 | 1 | 1000152157 | 01.12.2027 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDCB | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDCB90016902
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Pump Water Injection | 2027-12-01 | 2027-12-01 | 2 hrs | FY28 | 2 | 90016932 | 1 | 1000152195 | 01.12.2027 | 5000 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP | 6300 | 43398 | 240 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP90016932
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl ADS PTZ Camera & LIDAR | 2027-12-01 | 2027-12-01 | 10 hrs | FY28 | 10 | 90029206 | A1 | 1000294238 | 01.12.2027 | 10000 | CLB-MP-DRLL-DR061 -ADSYST-ADSPR-HTCAM | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ADSYST-ADSPR-HTCAM90029206
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Main Hyd NCS | 2027-12-03 | 2027-12-03 | 6 hrs | FY28 | 6 | 90020235 | 1 | 1000294873 | 03.12.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP1 | 6700 | 17309 | 5872 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP190020235
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Charge | 2027-12-03 | 2027-12-03 | 2 hrs | FY28 | 2 | 90020232 | 1 | 1000294868 | 03.12.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP3 | 6700 | 17309 | 5872 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP390020232
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Hyd Pump Auxiliary | 2027-12-03 | 2027-12-03 | 4 hrs | FY28 | 4 | 90020236 | 1 | 1000294867 | 03.12.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-PPAUX | 6700 | 17309 | 5872 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-PPAUX90020236
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 EncoderHarness Cab to Aframe Repl | 2027-12-03 | 2027-12-03 | 6 hrs | FY28 | 6 | 90036144 | A1 | 1000365257 | 03.12.2027 | 5000 | CLB-MP-DRLL-DR061 -ADSYST-HARNC | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ADSYST-HARNC90036144
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Cables | 2027-12-04 | 2027-12-05 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302816 | 04.12.2027 | 2500 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Valve Main Block | 2027-12-04 | 2027-12-04 | 12 hrs | FY28 | 12 | 90012977 | B1 | 1000150451 | 04.12.2027 | 12000 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVMBK | 4200 | 30594 | 6461 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVMBK90012977
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | STAT DR2132 48M Pressure Vessel Insp Int | 2027-12-07 | 2027-12-07 | 4 hrs | FY28 | 4 | 90014200 | A1 | 1000323450 | 07.12.2027 | 48 Monthly | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK90014200
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | STAT DR2133 48M Pressure Vessel Insp Int | 2027-12-07 | 2027-12-07 | 4 hrs | FY28 | 4 | 90014200 | A1 | 1000323454 | 07.12.2027 | 48 Monthly | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK | 6700 | 15211 | 3277 | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK90014200
D65 | Onsite PM | Drills | Fortescue | DR3110 | STAT DR3110 48M Pressure Vessel Insp Int | 2027-12-07 | 2027-12-07 | 4 hrs | FY28 | 4 | 90014200 | A1 | 1000321667 | 07.12.2027 | 48 Monthly | CLB-MP-DRLL-DR3110-AIRSYS-ARTNK | 4200 | 30612 | 30612 | CLB-MP-DRLL-DR3110-AIRSYS-ARTNK90014200
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Primary Water Tank Anodes | 2027-12-08 | 2027-12-08 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377549 | 08.12.2027 | 10000 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKP | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Secondary Water Tank Anodes | 2027-12-08 | 2027-12-08 | 8 hrs | FY28 | 8 | 90037834 | A1 | 1000377479 | 08.12.2027 | 10000 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack RHF NDE CS | 2027-12-08 | 2027-12-08 | 12 hrs | FY28 | 24 | 90030670 | A1 | 1000256592 | 08.12.2027 | 6000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF | 6700 | 14786 | 2078 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | STAT DR2133 Repl Receiver PRV | 2027-12-09 | 2027-12-09 | 1.5 hrs | FY28 | 1.5 | 90026270 | A1 | 1000323452 | 09.12.2027 | 18 Monthly | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK | 6700 | 15211 | 3277 | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK90026270
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Drive Gearbox | 2027-12-09 | 2027-12-10 | 30 hrs | FY28 | 78 | 90020181 | 1 | 1000294869 | 09.12.2027 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG | 6700 | 17309 | 5941 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG90020181
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Auto Lube Pump | 2027-12-14 | 2027-12-14 | 2 hrs | FY28 | 2 | 90011731 | 1 | 1000098264 | 14.12.2027 | 12000 | CLB-MP-DRLL-DR060 -GRSYST-ALBPP | 6300 | 69618 | 15526 | CLB-MP-DRLL-DR060 -GRSYST-ALBPP90011731
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 EncoderHarness Cab to Aframe Repl | 2027-12-14 | 2027-12-14 | 6 hrs | FY28 | 6 | 90036144 | A1 | 1000365256 | 14.12.2027 | 5000 | CLB-MP-DRLL-DR060 -ADSYST-HARNC | 6300 | 69618 | 1221 | CLB-MP-DRLL-DR060 -ADSYST-HARNC90036144
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Engine Initial 250hrs Valve Set | 2027-12-14 | 2027-12-14 | 8 hrs | FY28 | 16 | 90016041 | B1 | 1000259953 | 14.12.2027 | 250 | CLB-MP-DRLL-DR3110-ENGINE | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-ENGINE90016041
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 XLF Repl Main Feed Chain | 2027-12-15 | 2027-12-15 | 8 hrs | FY28 | 16 | 90021711 | A1 | 1000237290 | 15.12.2027 | 2500 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH | 4400 | 17885 | 1481 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH90021711
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS LiDAR | 2027-12-19 | 2027-12-19 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000296307 | 19.12.2027 | 5000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR | 6700 | 16830 | 11072 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Pump Drive Gearbox | 2027-12-19 | 2027-12-20 | 30 hrs | FY28 | 78 | 90020181 | 1 | 1000296237 | 19.12.2027 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG90020181
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Hyd Motor Feed | 2027-12-23 | 2027-12-23 | 6 hrs | FY28 | 6 | 90022025 | A1 | 1000361223 | 23.12.2027 | 6000 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFEED | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFEED90022025
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Oscillation Valve | 2027-12-23 | 2027-12-23 | 4 hrs | FY28 | 4 | 90021664 | A1 | 1000237353 | 23.12.2027 | 12000 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVOST | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVOST90021664
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Timing Chain Maintenance | 2027-12-23 | 2027-12-23 | 7 hrs | FY28 | 14 | 90022023 | A1 | 1000361221 | 23.12.2027 | 3000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP90022023
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Feed Chain Sprockets | 2027-12-23 | 2027-12-23 | 12 hrs | FY28 | 24 | 90022030 | A1 | 1000361222 | 23.12.2027 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHS | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHS90022030
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Hose Drum Sprocket | 2027-12-23 | 2027-12-23 | 6 hrs | FY28 | 6 | 90022032 | A1 | 1000361226 | 23.12.2027 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDS | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDS90022032
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Gearbox Power Head | 2027-12-23 | 2027-12-23 | 16 hrs | FY28 | 32 | 90021707 | A1 | 1000361224 | 23.12.2027 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-PWRHD | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-PWRHD90021707
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack LHF NDE NCS | 2027-12-24 | 2027-12-24 | 12 hrs | FY28 | 24 | 90020196 | 1 | 1000296340 | 24.12.2027 | 6000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF | 6700 | 15850 | 2485 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2027-12-24 | 2027-12-25 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302772 | 24.12.2027 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Air Lubrication | 2027-12-28 | 2027-12-28 | 2 hrs | FY28 | 2 | 90021656 | A1 | 1000237302 | 28.12.2027 | 6000 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB | 4400 | 17885 | 6064 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB90021656
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cables & Hoses | 2027-12-30 | 2028-01-01 | 50 hrs | FY28 | 100 | 90029843 | A1 | 1000303722 | 30.12.2027 | 5000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER | 6300 | 69618 | 25954 | CLB-MP-DRLL-DR060 -STRUCT-TOWER90029843
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Cables | 2028-01-01 | 2028-01-02 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302880 | 01.01.2028 | 2500 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030334
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Dual Counter Balance | 2028-01-01 | 2028-01-01 | 2 hrs | FY28 | 2 | 90011690 | 1 | 1000098225 | 01.01.2028 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDCB | 6300 | 69618 | 20745 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDCB90011690
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Counter Balance | 2028-01-01 | 2028-01-01 | 1 hr | FY28 | 1 | 90011691 | 1 | 1000098226 | 01.01.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVCNB | 6300 | 69618 | 31403 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVCNB90011691
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Seat Operators | 2028-01-04 | 2028-01-04 | 4 hrs | FY28 | 8 | 90020200 | A3 | 1000296278 | 04.01.2028 | 20000 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-SEATS | 6700 | 16830 | 10291 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-SEATS90020200
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack RHF NDE CS | 2028-01-06 | 2028-01-06 | 12 hrs | FY28 | 24 | 90030670 | A1 | 1000296448 | 06.01.2028 | 6000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF | 6700 | 15193 | 2198 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Pump Drive Gearbox | 2028-01-11 | 2028-01-12 | 30 hrs | FY28 | 78 | 90020181 | 1 | 1000296475 | 11.01.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG90020181
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Power Pack Midlife | 2028-01-17 | 2028-01-22 | 125 hrs | FY28 | 197 | 90029572 | A1 | 1000295364 | 17.01.2028 | 10000 | CLB-MP-DRLL-DR061 -ENGINE | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ENGINE90029572
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Hyd Motor Fan Hyd Cooler | 2028-01-17 | 2028-01-17 | 6 hrs | FY28 | 6 | 90011697 | 1 | 1000152136 | 17.01.2028 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MFMCA | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MFMCA90011697
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Valve Counter Balance | 2028-01-18 | 2028-01-18 | 1 hr | FY28 | 1 | 90016903 | 1 | 1000152158 | 18.01.2028 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVCNB | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVCNB90016903
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cyl Mast Raise CS | 2028-01-22 | 2028-01-22 | 16 hrs | FY28 | 32 | 90020198 | 1 | 1000256596 | 22.01.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MRCYR | 6700 | 14786 | 4255 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MRCYR90020198
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Auto Lube Pump | 2028-01-24 | 2028-01-24 | 2 hrs | FY28 | 2 | 90016930 | 1 | 1000152194 | 24.01.2028 | 12000 | CLB-MP-DRLL-DR061 -GRSYST-ALBPP | 6300 | 43398 | 20754 | CLB-MP-DRLL-DR061 -GRSYST-ALBPP90016930
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump | 2028-01-25 | 2028-01-25 | 2 hrs | FY28 | 2 | 90020875 | A1 | 1000237254 | 25.01.2028 | 8000 | CLB-MP-DRLL-DR3126-GRSYST-ALBPP | 4400 | 17885 | 10500 | CLB-MP-DRLL-DR3126-GRSYST-ALBPP90020875
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2028-01-25 | 2028-01-25 | 1 hr | FY28 | 1 | 90020876 | A1 | 1000237255 | 25.01.2028 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack LHR DE NCS | 2028-01-26 | 2028-01-26 | 12 hrs | FY28 | 24 | 90020204 | 1 | 1000256591 | 26.01.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLR | 6700 | 14786 | 4172 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLR90020204
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Battery Cables | 2028-01-27 | 2028-01-28 | 24 hrs | FY28 | 24 | 90028942 | A1 | 1000289061 | 27.01.2028 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028942
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 12M Inspection Isolator Panel | 2028-01-28 | 2028-01-28 | 2 hrs | FY28 | 2 | 90022525 | A1 | 1000236546 | 28.01.2028 | 12 Monthly | CLB-MP-DRLL-DR3110-ELCTLV |  |  |  | CLB-MP-DRLL-DR3110-ELCTLV90022525
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast Cables | 2028-01-30 | 2028-01-31 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302808 | 30.01.2028 | 2500 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Washdown Pump | 2028-02-06 | 2028-02-06 | 4 hrs | FY28 | 8 | 90030681 | A1 | 1000305579 | 06.02.2028 | 7500 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP | 6700 | 15193 | 4539 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack LHF NDE NCS | 2028-02-06 | 2028-02-06 | 12 hrs | FY28 | 24 | 90020196 | 1 | 1000256590 | 06.02.2028 | 6000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF | 6700 | 14786 | 889 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Adjust 3750Hr Valve Set | 2028-02-10 | 2028-02-10 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000296350 | 10.02.2028 | 3750 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Adjust 3750Hr Valve Set | 2028-02-16 | 2028-02-16 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000294850 | 16.02.2028 | 3750 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack LHF NDE NCS | 2028-02-23 | 2028-02-23 | 12 hrs | FY28 | 24 | 90020196 | 1 | 1000296446 | 23.02.2028 | 6000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF | 6700 | 15193 | 1223 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF90020196
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pressure Safety Valve Cert | 2028-02-25 | 2028-02-25 | 3 hrs | FY28 | 3 | 90021719 | A1 | 1000237321 | 25.02.2028 | 18 Monthly | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK | 4400 | 17932 | 4496 | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK90021719
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Adjust 3750Hr Valve Set | 2028-02-25 | 2028-02-25 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000296178 | 25.02.2028 | 3750 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Cables | 2028-02-25 | 2028-02-26 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302812 | 25.02.2028 | 2500 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030334
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Operators Seat | 2028-02-25 | 2028-02-25 | 2 hrs | FY28 | 2 | 90016913 | 1 | 1000152169 | 25.02.2028 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-CABIN-SEATS | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-CABIN-SEATS90016913
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Hyd Pump Fan Engine Cool RH | 2028-02-25 | 2028-02-25 | 2 hrs | FY28 | 2 | 90020240 | 1 | 1000256629 | 25.02.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-FANP2 | 6700 | 14786 | 3626 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-FANP290020240
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Drive Shaft Pump Drive | 2028-02-25 | 2028-02-25 | 6 hrs | FY28 | 12 | 90028862 | A1 | 1000287877 | 25.02.2028 | 5000 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG-DRSHT | 6700 | 14786 | 3637 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG-DRSHT90028862
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS LiDAR | 2028-02-27 | 2028-02-27 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000290914 | 27.02.2028 | 5000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 6M Static Line Inspection | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000296315 | 01.03.2028 | 6 Monthly | CLB-MP-DRLL-DR2132-STRUCT |  |  |  | CLB-MP-DRLL-DR2132-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 6M Static Line Inspection | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000296441 | 01.03.2028 | 6 Monthly | CLB-MP-DRLL-DR2133-STRUCT |  |  |  | CLB-MP-DRLL-DR2133-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 6M Static Line Inspection | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000294755 | 01.03.2028 | 6 Monthly | CLB-MP-DRLL-DR2130-STRUCT |  |  |  | CLB-MP-DRLL-DR2130-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 6M Static Line Inspection | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000296163 | 01.03.2028 | 6 Monthly | CLB-MP-DRLL-DR2131-STRUCT |  |  |  | CLB-MP-DRLL-DR2131-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 6M Static Line Inspection | 2028-03-01 | 2028-03-01 | 4 hrs | FY28 | 4 | 90013246 | A1 | 1000256585 | 01.03.2028 | 6 Monthly | CLB-MP-DRLL-DR2126-STRUCT |  |  |  | CLB-MP-DRLL-DR2126-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS LiDAR | 2028-03-02 | 2028-03-02 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000296439 | 02.03.2028 | 5000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR | 6700 | 15850 | 10602 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Adjust 3750Hr Valve Set | 2028-03-04 | 2028-03-04 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000256606 | 04.03.2028 | 3750 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Adjust 3750Hr Valve Set | 2028-03-10 | 2028-03-10 | 10.5 hrs | FY28 | 21 | 90020402 | 1 | 1000296456 | 10.03.2028 | 3750 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS GPS Components | 2028-03-16 | 2028-03-16 | 3.5 hrs | FY28 | 3.5 | 90029191 | A1 | 1000294227 | 16.03.2028 | 40000 | CLB-MP-DRLL-DR060 -ADSYST-ADSPO | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSPO90029191
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cabin ADS Components | 2028-03-16 | 2028-03-17 | 31.5 hrs | FY28 | 31.5 | 90029189 | A1 | 1000294226 | 16.03.2028 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-HMIJK | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-HMIJK90029189
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS Ace Cabinet Components | 2028-03-16 | 2028-03-18 | 44.5 hrs | FY28 | 44.5 | 90029187 | A1 | 1000294225 | 16.03.2028 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-CLXEN | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-CLXEN90029187
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 24M Air Cond Rencool Overhaul | 2028-03-17 | 2028-03-18 | 24 hrs | FY28 | 24 | 90018580 | 1 | 1000180964 | 17.03.2028 | 24 Monthly | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN |  |  |  | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN90018580
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 24M Air Conditioner Overhaul | 2028-03-17 | 2028-03-18 | 24 hrs | FY28 | 24 | 90018566 | 1 | 1000180544 | 17.03.2028 | 24 Monthly | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN |  |  |  | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN90018566
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Pump Water Injection | 2028-03-17 | 2028-03-17 | 4 hrs | FY28 | 4 | 90013019 | B1 | 1000150468 | 17.03.2028 | 6000 | CLB-MP-DRLL-DR3110-DSTSUP-WTRPP | 4200 | 30594 | 772 | CLB-MP-DRLL-DR3110-DSTSUP-WTRPP90013019
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Track Frame Module LH | 2028-03-17 | 2028-03-18 | 18 hrs | FY28 | 36 | 90020417 | B1 | 1000211915 | 17.03.2028 | 12000 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL | 4200 | 30594 | 5268 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL90020417
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Track Frame Module RH | 2028-03-17 | 2028-03-18 | 18 hrs | FY28 | 36 | 90020754 | B1 | 1000211934 | 17.03.2028 | 12000 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR | 4200 | 30594 | 5268 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR90020754
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Pump Main Hyd CS | 2028-03-19 | 2028-03-19 | 6 hrs | FY28 | 6 | 90020234 | 1 | 1000296242 | 19.03.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP2 | 6700 | 16830 | 3896 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP290020234
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Pump Main Hyd NCS | 2028-03-24 | 2028-03-24 | 6 hrs | FY28 | 6 | 90020235 | 1 | 1000296241 | 24.03.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP1 | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP190020235
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Hyd Pump Fan Oil Cooler LH | 2028-03-25 | 2028-03-25 | 2 hrs | FY28 | 2 | 90020239 | 1 | 1000256628 | 25.03.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-FANP1 | 6700 | 14786 | 3110 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-FANP190020239
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 PV271 Hydraulic Tune | 2028-03-28 | 2028-03-29 | 21 hrs | FY28 | 31.5 | 90017118 | 1 | 1000206785 | 28.03.2028 | 3000 | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190017118
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Roller Load NCS Pos14 | 2028-04-03 | 2028-04-03 | 4 hrs | FY28 | 8 | 90020188 | 1 | 1000313298 | 03.04.2028 | 20000 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF14 | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF1490020188
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 24M Air Conditioner OverHaul | 2028-04-05 | 2028-04-06 | 24 hrs | FY28 | 24 | 90018566 | 1 | 1000180543 | 05.04.2028 | 24 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018566
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 24M Air Cond Rencool Overhaul | 2028-04-05 | 2028-04-06 | 24 hrs | FY28 | 24 | 90018580 | 1 | 1000180962 | 05.04.2028 | 24 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018580
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Compressor Coupling | 2028-04-07 | 2028-04-07 | 12 hrs | FY28 | 24 | 90030404 | A1 | 1000303546 | 07.04.2028 | 7500 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR-COUPL | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR-COUPL90030404
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2028-04-08 | 2028-04-09 | 21 hrs | FY28 | 31.5 | 90017118 | 1 | 1000145852 | 08.04.2028 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Drive Shaft Pump Drive | 2028-04-14 | 2028-04-14 | 6 hrs | FY28 | 12 | 90028862 | A1 | 1000296370 | 14.04.2028 | 5000 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG-DRSHT | 6700 | 15850 | 8503 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG-DRSHT90028862
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Valve Main Block | 2028-04-16 | 2028-04-16 | 9 hrs | FY28 | 18 | 90021692 | A1 | 1000237352 | 16.04.2028 | 12000 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVMBK | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVMBK90021692
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Cables | 2028-04-18 | 2028-04-19 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302816 | 18.04.2028 | 2500 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030334
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Water & Fuel Tank Mount | 2028-05-03 | 2028-05-03 | 10 hrs | FY28 | 20 | 90017443 | 1 | 1000160295 | 03.05.2028 | 12 Monthly | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK | 6300 | 69618 | 17116 | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK90017443
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Power Pack Module | 2028-05-07 | 2028-05-09 | 54 hrs | FY28 | 84 | 90026030 | A1 | 1000268661 | 07.05.2028 | 12000 | CLB-MP-DRLL-DR3126-ENGINE | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-ENGINE90026030
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Washdown Pump | 2028-05-08 | 2028-05-08 | 4 hrs | FY28 | 8 | 90030681 | A1 | 1000305578 | 08.05.2028 | 7500 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP | 6700 | 15850 | 2962 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2028-05-08 | 2028-05-09 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302772 | 08.05.2028 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Cables | 2028-05-17 | 2028-05-18 | 20 hrs | FY28 | 60 | 90030334 | A1 | 1000302880 | 17.05.2028 | 2500 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS LiDAR | 2028-05-22 | 2028-05-22 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000296545 | 22.05.2028 | 5000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR90029065
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Engine Initial 250hrs Valve Set | 2028-05-28 | 2028-05-28 | 8 hrs | FY28 | 16 | 90021722 | A1 | 1000268662 | 28.05.2028 | 250 | CLB-MP-DRLL-DR3126-ENGINE | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-ENGINE90021722
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Main Feed Chain | 2028-05-29 | 2028-05-29 | 8 hrs | FY28 | 16 | 90012999 | B1 | 1000150460 | 29.05.2028 | 2500 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH | 4200 | 30594 | 2427 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH90012999
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cables & Hoses | 2028-06-01 | 2028-06-03 | 50 hrs | FY28 | 100 | 90029843 | A1 | 1000303729 | 01.06.2028 | 5000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER90029843
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS LiDAR | 2028-06-08 | 2028-06-08 | 5 hrs | FY28 | 8 | 90029065 | A1 | 1000294939 | 08.06.2028 | 5000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR90029065
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Power Pack Midlife | 2028-06-08 | 2028-06-13 | 125 hrs | FY28 | 197 | 90029577 | A1 | 1000295360 | 08.06.2028 | 10000 | CLB-MP-DRLL-DR060 -ENGINE | 6300 | 69618 | 16445 | CLB-MP-DRLL-DR060 -ENGINE90029577
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Service 12M Air Conditioner | 2028-06-09 | 2028-06-09 | 6 hrs | FY28 | 12 | 90028298 | A1 | 1000294922 | 09.06.2028 | 12 Monthly | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN | 6700 | 17309 | 6755 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN90028298
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cyl Mast Locking NCS | 2028-06-12 | 2028-06-12 | 12 hrs | FY28 | 24 | 90020197 | 1 | 1000294845 | 12.06.2028 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MLCYL | 6700 | 17309 | 2411 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cyl Mast Locking CS | 2028-06-12 | 2028-06-12 | 12 hrs | FY28 | 24 | 90030657 | A1 | 1000294844 | 12.06.2028 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MLCYR | 6700 | 17309 | 2411 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS GPS Components | 2028-06-14 | 2028-06-14 | 3 hrs | FY28 | 3 | 90029061 | A1 | 1000294936 | 14.06.2028 | 30000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPO | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSPO90029061
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Main Air Compressor LP | 2028-06-14 | 2028-06-15 | 24 hrs | FY28 | 48 | 90020192 | 1 | 1000294861 | 14.06.2028 | 15000 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR | 6700 | 17309 | 1426 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR90020192
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Hydraulic Cooler Module | 2028-06-14 | 2028-06-14 | 12 hrs | FY28 | 24 | 90020220 | 1 | 1000294876 | 14.06.2028 | 30000 | CLB-MP-DRLL-DR2130-COOLER | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-COOLER90020220
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Chassis Harnesses | 2028-06-14 | 2028-06-18 | 104 hrs | FY28 | 208 | 90028944 | A1 | 1000294925 | 14.06.2028 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cab Harnesses | 2028-06-14 | 2028-06-14 | 14 hrs | FY28 | 14 | 90028947 | A1 | 1000294926 | 14.06.2028 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Compressor Harnesses | 2028-06-14 | 2028-06-14 | 12 hrs | FY28 | 12 | 90028948 | A1 | 1000294927 | 14.06.2028 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast Harnesses | 2028-06-14 | 2028-06-16 | 56 hrs | FY28 | 112 | 90028949 | A1 | 1000294928 | 14.06.2028 | 30000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028949
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Radiator Cooler Module | 2028-06-14 | 2028-06-14 | 12 hrs | FY28 | 24 | 90021617 | 1 | 1000294877 | 14.06.2028 | 30000 | CLB-MP-DRLL-DR2130-ENGINE-COSYS-RADTR | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ENGINE-COSYS-RADTR90021617
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Mast Module Qtr Life | 2028-06-14 | 2028-06-17 | 75 hrs | FY28 | 191 | 90030335 | A1 | 1000302809 | 14.06.2028 | 10000 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030335
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Sprocket LH | 2028-06-14 | 2028-06-14 | 10 hrs | FY28 | 20 | 90020186 | 1 | 1000303011 | 14.06.2028 | 10000 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKL | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKL90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Sprocket RH | 2028-06-14 | 2028-06-14 | 10 hrs | FY28 | 20 | 90020186 | 1 | 1000303012 | 14.06.2028 | 10000 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKR | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKR90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Hyd Pump Fan Oil Cooler LH | 2028-06-25 | 2028-06-25 | 2 hrs | FY28 | 2 | 90020239 | 1 | 1000296477 | 25.06.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-FANP1 | 6700 | 15193 | 1961 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-FANP190020239
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Hyd Pump Fan Engine Cool RH | 2028-06-25 | 2028-06-25 | 2 hrs | FY28 | 2 | 90020240 | 1 | 1000296478 | 25.06.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-FANP2 | 6700 | 15193 | 1961 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-FANP290020240
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | STAT DR2126 24M Pressure Vessel Insp Ext | 2028-06-27 | 2028-06-27 | 2 hrs | FY28 | 2 | 90025808 | A1 | 1000259213 | 27.06.2028 | 24 Monthly | CLB-MP-DRLL-DR2126-AIRSYS-ARTNK | 6700 | 14849 | 2463 | CLB-MP-DRLL-DR2126-AIRSYS-ARTNK90025808
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Pump Main Hyd NCS | 2028-06-28 | 2028-06-28 | 6 hrs | FY28 | 6 | 90020235 | 1 | 1000296479 | 28.06.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP1 | 6700 | 15193 | 1915 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP190020235
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Pump Main Hyd CS | 2028-06-28 | 2028-06-28 | 6 hrs | FY28 | 6 | 90020234 | 1 | 1000296480 | 28.06.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP2 | 6700 | 15193 | 1961 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP290020234
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Pump Charge | 2028-06-28 | 2028-06-28 | 2 hrs | FY28 | 2 | 90020232 | 1 | 1000296474 | 28.06.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP3 | 6700 | 15193 | 1922 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP390020232
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Hyd Pump Auxiliary | 2028-06-28 | 2028-06-28 | 4 hrs | FY28 | 4 | 90020236 | 1 | 1000296473 | 28.06.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-PPAUX | 6700 | 15193 | 1840 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-PPAUX90020236
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Jack Leg NDE CS | 2028-06-29 | 2028-06-29 | 16 hrs | FY28 | 20 | 90011672 | 1 | 1000098216 | 29.06.2028 | 15000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRF | 6300 | 69618 | 2790 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRF90011672
| Onsite PM | Drills | Fortescue |  | FY29 - DRILLS - COMPONENTS DURING PM | 2028-07-01 |  |  | FY29
| Onsite PM | Drills | Fortescue | MOC | MAJOR ON CONDITION | 2028-07-01 | 2029-07-01 | 365 days | FY29
| Onsite PM | Drills | Fortescue | MOC | JULY | 2028-07-01 | 2028-07-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | AUGUST | 2028-08-01 | 2028-08-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | SEPTEMBER | 2028-09-01 | 2028-09-30 | 29 days | FY29
| Onsite PM | Drills | Fortescue | MOC | OCTOBER | 2028-10-01 | 2028-10-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | NOVEMBER | 2028-11-01 | 2028-11-30 | 29 days | FY29
| Onsite PM | Drills | Fortescue | MOC | DECEMBER | 2028-12-01 | 2028-12-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | JANUARY | 2029-01-01 | 2029-01-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | FEBRUARY | 2029-02-01 | 2029-02-28 | 27 days | FY29
| Onsite PM | Drills | Fortescue | MOC | MARCH | 2029-03-01 | 2029-03-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | APRIL | 2029-04-01 | 2029-04-30 | 29 days | FY29
| Onsite PM | Drills | Fortescue | MOC | MAY | 2029-05-01 | 2029-05-31 | 30 days | FY29
| Onsite PM | Drills | Fortescue | MOC | JUNE | 2029-06-01 | 2029-06-30 | 29 days | FY29
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2028-07-09 | 2028-07-09 | 1 hr | FY29 | 1 | 90020876 | A1 | 1000237255 | 09.07.2028 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 XLF Repl Main Feed Chain | 2028-07-09 | 2028-07-09 | 8 hrs | FY29 | 16 | 90021711 | A1 | 1000237290 | 09.07.2028 | 2500 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH | 4400 | 17885 | 1481 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH90021711
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS GPS Components | 2028-07-10 | 2028-07-10 | 3 hrs | FY29 | 3 | 90029061 | A1 | 1000296304 | 10.07.2028 | 30000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPO | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ADSYST-ADSPO90029061
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Fish Eye Camera | 2028-07-10 | 2028-07-10 | 16 hrs | FY29 | 16 | 90029067 | A1 | 1000296306 | 10.07.2028 | 10000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-HTCAM | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-HTCAM90029067
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Hydraulic Cooler Module | 2028-07-10 | 2028-07-10 | 12 hrs | FY29 | 24 | 90020220 | 1 | 1000296244 | 10.07.2028 | 30000 | CLB-MP-DRLL-DR2131-COOLER | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-COOLER90020220
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Harnesses | 2028-07-10 | 2028-07-12 | 56 hrs | FY29 | 112 | 90028949 | A1 | 1000296296 | 10.07.2028 | 30000 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS90028949
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Chassis Harnesses | 2028-07-10 | 2028-07-14 | 104 hrs | FY29 | 208 | 90028944 | A1 | 1000296293 | 10.07.2028 | 15000 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Radiator Cooler Module | 2028-07-10 | 2028-07-10 | 12 hrs | FY29 | 24 | 90021617 | 1 | 1000296245 | 10.07.2028 | 30000 | CLB-MP-DRLL-DR2131-ENGINE-COSYS-RADTR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ENGINE-COSYS-RADTR90021617
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack RHR DE CS | 2028-07-10 | 2028-07-10 | 12 hrs | FY29 | 24 | 90030672 | A1 | 1000296171 | 10.07.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRR90030672
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cyl Mast Locking NCS | 2028-07-10 | 2028-07-10 | 12 hrs | FY29 | 24 | 90020197 | 1 | 1000296173 | 10.07.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MLCYL | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cyl Mast Locking CS | 2028-07-10 | 2028-07-10 | 12 hrs | FY29 | 24 | 90030657 | A1 | 1000296172 | 10.07.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MLCYR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cyl Mast Raise NCS | 2028-07-10 | 2028-07-10 | 16 hrs | FY29 | 32 | 90030659 | A1 | 1000296175 | 10.07.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MRCYL | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MRCYL90030659
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cyl Mast Raise CS | 2028-07-10 | 2028-07-10 | 16 hrs | FY29 | 32 | 90020198 | 1 | 1000296174 | 10.07.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MRCYR | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MRCYR90020198
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Mast Module Qtr Life | 2028-07-10 | 2028-07-13 | 75 hrs | FY29 | 191 | 90030335 | A1 | 1000302813 | 10.07.2028 | 10000 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030335
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Water & Fuel Tank Mount | 2028-07-13 | 2028-07-13 | 10 hrs | FY29 | 20 | 90017443 | 1 | 1000160296 | 13.07.2028 | 12 Monthly | CLB-MP-DRLL-DR061 -DSTSUP-WTTNK |  |  |  | CLB-MP-DRLL-DR061 -DSTSUP-WTTNK90017443
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS Vibration Sensors | 2028-07-14 | 2028-07-14 | 1 hr | FY29 | 1 | 90029062 | A1 | 1000294935 | 14.07.2028 | 10000 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS-DSVSN | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Fish Eye Camera | 2028-07-14 | 2028-07-14 | 16 hrs | FY29 | 16 | 90029067 | A1 | 1000294938 | 14.07.2028 | 10000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-HTCAM | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-HTCAM90029067
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Washdown Pump | 2028-07-15 | 2028-07-15 | 4 hrs | FY29 | 8 | 90030681 | A1 | 1000305736 | 15.07.2028 | 7500 | CLB-MP-DRLL-DR2131-DSTSUP-WSHPP | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Final Drive & Sprocket RH | 2028-07-15 | 2028-07-15 | 12 hrs | FY29 | 22 | 90020182 | 1 | 1000296221 | 15.07.2028 | 20000 | CLB-MP-DRLL-DR2131-TRAVEL-FDRRH | 6700 | 16830 | 13448 | CLB-MP-DRLL-DR2131-TRAVEL-FDRRH90020182
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Battery Cables | 2028-07-16 | 2028-07-17 | 24 hrs | FY29 | 24 | 90028942 | A1 | 1000294924 | 16.07.2028 | 15000 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS90028942
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Battery Cables | 2028-07-17 | 2028-07-18 | 24 hrs | FY29 | 24 | 90028942 | A1 | 1000296292 | 17.07.2028 | 15000 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS90028942
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cyl Mast Raise NCS | 2028-07-22 | 2028-07-22 | 16 hrs | FY29 | 32 | 90030659 | A1 | 1000296347 | 22.07.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MRCYL | 6700 | 15850 | 1601 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MRCYL90030659
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Diverter NCS | 2028-07-23 | 2028-07-23 | 4 hrs | FY29 | 4 | 90011692 | 1 | 1000098227 | 23.07.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDVL | 6300 | 69618 | 7361 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDVL90011692
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Diverter CS | 2028-07-23 | 2028-07-23 | 4 hrs | FY29 | 4 | 90011693 | 1 | 1000098228 | 23.07.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDVR | 6300 | 69618 | 7361 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDVR90011693
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Yoke Oscillation | 2028-07-23 | 2028-07-23 | 12 hrs | FY29 | 24 | 90011726 | 1 | 1000098259 | 23.07.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-UNDER-YKOSC | 6300 | 69618 | 7361 | CLB-MP-DRLL-DR060 -STRUCT-UNDER-YKOSC90011726
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack RHF NDE CS | 2028-07-24 | 2028-07-24 | 12 hrs | FY29 | 24 | 90030670 | A1 | 1000296170 | 24.07.2028 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF | 6700 | 16830 | 4546 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack RHR DE CS | 2028-07-31 | 2028-07-31 | 12 hrs | FY29 | 24 | 90030672 | A1 | 1000294843 | 31.07.2028 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRR | 6700 | 17309 | 1426 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRR90030672
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Battery Cables | 2028-08-08 | 2028-08-09 | 24 hrs | FY29 | 24 | 90028942 | A1 | 1000296424 | 08.08.2028 | 15000 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS90028942
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Compressor Coupling | 2028-08-08 | 2028-08-08 | 12 hrs | FY29 | 24 | 90030404 | A1 | 1000303536 | 08.08.2028 | 7500 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-COUPL | 6700 | 14786 | 8105 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-COUPL90030404
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | STAT DR2130 Repl Receiver PRV | 2028-08-09 | 2028-08-09 | 1.5 hrs | FY29 | 1.5 | 90026270 | A1 | 1000294918 | 09.08.2028 | 18 Monthly | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK | 6700 | 17370 | 17370 | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK90026270
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Engine Valve Set | 2028-08-09 | 2028-08-09 | 8 hrs | FY29 | 16 | 90016042 | B1 | 1000230306 | 09.08.2028 | 3000 | CLB-MP-DRLL-DR3110-ENGINE | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-ENGINE90016042
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Lubrication Air Pump | 2028-08-12 | 2028-08-12 | 2 hrs | FY29 | 2 | 90012947 | A1 | 1000150433 | 12.08.2028 | 6000 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-PALUB | 4200 | 30612 | 9932 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-PALUB90012947
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Rod Thread lube Pump | 2028-08-12 | 2028-08-12 | 2 hrs | FY29 | 2 | 90013018 | B1 | 1000150467 | 12.08.2028 | 6000 | CLB-MP-DRLL-DR3110-GRSYST-RTLPP | 4200 | 30594 | 208 | CLB-MP-DRLL-DR3110-GRSYST-RTLPP90013018
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Operators Seat | 2028-08-12 | 2028-08-12 | 2 hrs | FY29 | 2 | 90012992 | B1 | 1000150457 | 12.08.2028 | 6000 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-SEATS | 4200 | 30594 | 8770 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-SEATS90012992
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack RHF NDE CS | 2028-08-13 | 2028-08-13 | 12 hrs | FY29 | 24 | 90030670 | A1 | 1000296342 | 13.08.2028 | 6000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF | 6700 | 15850 | 4205 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Battery Cables | 2028-08-14 | 2028-08-15 | 24 hrs | FY29 | 24 | 90028942 | A1 | 1000296530 | 14.08.2028 | 15000 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS90028942
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack LHR DE NCS | 2028-08-15 | 2028-08-15 | 12 hrs | FY29 | 24 | 90020204 | 1 | 1000296169 | 15.08.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLR | 6700 | 16830 | 1171 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLR90020204
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Water Inj | 2028-08-19 | 2028-08-19 | 2 hrs | FY29 | 4 | 90031899 | A1 | 1000315429 | 19.08.2028 | 7500 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP | 6700 | 14786 | 7896 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP90031899
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Jack Leg NDE NCS | 2028-08-22 | 2028-08-22 | 16 hrs | FY29 | 20 | 90011671 | 1 | 1000098215 | 22.08.2028 | 15000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYLF | 6300 | 69618 | 1869 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYLF90011671
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Cyl Feed Holder Swing | 2028-08-27 | 2028-08-27 | 4 hrs | FY29 | 4 | 90022007 | A1 | 1000237311 | 27.08.2028 | 9000 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-FDHCS | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-FDHCS90022007
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Timing Chain Maintenance | 2028-08-27 | 2028-08-27 | 7 hrs | FY29 | 14 | 90022023 | A1 | 1000361221 | 27.08.2028 | 3000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP90022023
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Hose Drum Assembly | 2028-08-27 | 2028-08-27 | 10 hrs | FY29 | 18 | 90022021 | A1 | 1000361225 | 27.08.2028 | 9000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDA | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDA90022021
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS GPS Components | 2028-09-01 | 2028-09-01 | 3 hrs | FY29 | 3 | 90029061 | A1 | 1000296436 | 01.09.2028 | 30000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPO | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSPO90029061
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Hydraulic Cooler Module | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 24 | 90020220 | 1 | 1000296376 | 01.09.2028 | 30000 | CLB-MP-DRLL-DR2132-COOLER | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-COOLER90020220
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cab Harnesses | 2028-09-01 | 2028-09-01 | 14 hrs | FY29 | 14 | 90028947 | A1 | 1000296426 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Chassis Harnesses | 2028-09-01 | 2028-09-05 | 104 hrs | FY29 | 208 | 90028944 | A1 | 1000296425 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Compressor Harnesses | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 12 | 90028948 | A1 | 1000296427 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Harnesses | 2028-09-01 | 2028-09-03 | 56 hrs | FY29 | 112 | 90028949 | A1 | 1000296428 | 01.09.2028 | 30000 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS90028949
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Engine Assy Caterpillar C32 | 2028-09-01 | 2028-09-03 | 50 hrs | FY29 | 150 | 90020393 | 1 | 1000296348 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Radiator Cooler Module | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 24 | 90021617 | 1 | 1000296377 | 01.09.2028 | 30000 | CLB-MP-DRLL-DR2132-ENGINE-COSYS-RADTR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE-COSYS-RADTR90021617
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cyl Mast Locking NCS | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 24 | 90020197 | 1 | 1000296345 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYL | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cyl Mast Locking CS | 2028-09-01 | 2028-09-01 | 12 hrs | FY29 | 24 | 90030657 | A1 | 1000296344 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Hyd Pump Fan Oil Cooler LH | 2028-09-01 | 2028-09-01 | 2 hrs | FY29 | 2 | 90020239 | 1 | 1000296371 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-FANP1 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-FANP190020239
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Hyd Pump Fan Engine Cool RH | 2028-09-01 | 2028-09-01 | 2 hrs | FY29 | 2 | 90020240 | 1 | 1000296372 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-FANP2 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-FANP290020240
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Main Hyd NCS | 2028-09-01 | 2028-09-01 | 6 hrs | FY29 | 6 | 90020235 | 1 | 1000296373 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP1 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP190020235
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Main Hyd CS | 2028-09-01 | 2028-09-01 | 6 hrs | FY29 | 6 | 90020234 | 1 | 1000296374 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP2 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP290020234
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Charge | 2028-09-01 | 2028-09-01 | 2 hrs | FY29 | 2 | 90020232 | 1 | 1000296368 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP3 | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP390020232
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Hyd Pump Auxiliary | 2028-09-01 | 2028-09-01 | 4 hrs | FY29 | 4 | 90020236 | 1 | 1000296367 | 01.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-PPAUX | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-PPAUX90020236
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Mast Module Qtr Life | 2028-09-01 | 2028-09-04 | 75 hrs | FY29 | 191 | 90030335 | A1 | 1000302817 | 01.09.2028 | 10000 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030335
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Sprocket LH | 2028-09-01 | 2028-09-01 | 10 hrs | FY29 | 20 | 90020186 | 1 | 1000303015 | 01.09.2028 | 10000 | CLB-MP-DRLL-DR2132-TRAVEL-SPRKL | 6700 | 15850 | 4205 | CLB-MP-DRLL-DR2132-TRAVEL-SPRKL90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Sprocket RH | 2028-09-01 | 2028-09-01 | 10 hrs | FY29 | 20 | 90020186 | 1 | 1000303016 | 01.09.2028 | 10000 | CLB-MP-DRLL-DR2132-TRAVEL-SPRKR | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-TRAVEL-SPRKR90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 6M Static Line Inspection | 2028-09-01 | 2028-09-01 | 4 hrs | FY29 | 4 | 90013246 | A1 | 1000294755 | 01.09.2028 | 6 Monthly | CLB-MP-DRLL-DR2130-STRUCT |  |  |  | CLB-MP-DRLL-DR2130-STRUCT90013246
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS IO Modules | 2028-09-01 | 2028-09-01 | 4 hrs | FY29 | 4 | 90029208 | A1 | 1000294224 | 01.09.2028 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-ARDIO | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-ARDIO90029208
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Deck ADS Elec Hardware | 2028-09-01 | 2028-09-01 | 9.5 hrs | FY29 | 9.5 | 90029190 | A1 | 1000294223 | 01.09.2028 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-ADSMF | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-ADSMF90029190
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS 3D sensor | 2028-09-01 | 2028-09-01 | 1 hr | FY29 | 1 | 90029207 | A1 | 1000294228 | 01.09.2028 | 20000 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR | 6300 | 69618 | 33676 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR90029207
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack LHR DE NCS | 2028-09-06 | 2028-09-06 | 12 hrs | FY29 | 24 | 90020204 | 1 | 1000296341 | 06.09.2028 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLR | 6700 | 15850 | 735 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLR90020204
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Engine Assy Caterpillar C32 | 2028-09-07 | 2028-09-09 | 50 hrs | FY29 | 150 | 90020393 | 1 | 1000294848 | 07.09.2028 | 15000 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack LHR DE NCS | 2028-09-07 | 2028-09-07 | 12 hrs | FY29 | 24 | 90020204 | 1 | 1000294841 | 07.09.2028 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLR | 6700 | 17309 | 747 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLR90020204
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Hyd Pump Fan Oil Cooler LH | 2028-09-07 | 2028-09-07 | 2 hrs | FY29 | 2 | 90020239 | 1 | 1000294871 | 07.09.2028 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-FANP1 | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-FANP190020239
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Hyd Pump Fan Engine Cool RH | 2028-09-07 | 2028-09-07 | 2 hrs | FY29 | 2 | 90020240 | 1 | 1000294872 | 07.09.2028 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-FANP2 | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-FANP290020240
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Drive Shaft Pump Drive | 2028-09-07 | 2028-09-07 | 6 hrs | FY29 | 12 | 90028862 | A1 | 1000294870 | 07.09.2028 | 5000 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT90028862
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Pump Water Inj | 2028-09-08 | 2028-09-08 | 2 hrs | FY29 | 4 | 90031899 | A1 | 1000315434 | 08.09.2028 | 7500 | CLB-MP-DRLL-DR2133-DSTSUP-WTRPP | 6700 | 15193 | 610 | CLB-MP-DRLL-DR2133-DSTSUP-WTRPP90031899
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Pump Water Injection | 2028-09-10 | 2028-09-10 | 2 hrs | FY29 | 2 | 90011733 | 1 | 1000098266 | 10.09.2028 | 5000 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP | 6300 | 69618 | 1540 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP90011733
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS LiDAR | 2028-09-16 | 2028-09-16 | 5 hrs | FY29 | 8 | 90029065 | A1 | 1000296307 | 16.09.2028 | 5000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR | 6700 | 16830 | 11072 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Pump Water Inj | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 4 | 90031899 | A1 | 1000315432 | 16.09.2028 | 7500 | CLB-MP-DRLL-DR2131-DSTSUP-WTRPP | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cab Harnesses | 2028-09-16 | 2028-09-16 | 14 hrs | FY29 | 14 | 90028947 | A1 | 1000296294 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Compressor Harnesses | 2028-09-16 | 2028-09-16 | 12 hrs | FY29 | 12 | 90028948 | A1 | 1000296295 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Engine Assy Caterpillar C32 | 2028-09-16 | 2028-09-18 | 50 hrs | FY29 | 150 | 90020393 | 1 | 1000296176 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Hyd Pump Fan Oil Cooler LH | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 2 | 90020239 | 1 | 1000296239 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-FANP1 | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-FANP190020239
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Hyd Pump Fan Engine Cool RH | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 2 | 90020240 | 1 | 1000296240 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-FANP2 | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-FANP290020240
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Pump Charge | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 2 | 90020232 | 1 | 1000296236 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP3 | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP390020232
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Hyd Pump Auxiliary | 2028-09-16 | 2028-09-16 | 4 hrs | FY29 | 4 | 90020236 | 1 | 1000296235 | 16.09.2028 | 15000 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-PPAUX | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-PPAUX90020236
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Drive Shaft Pump Drive | 2028-09-16 | 2028-09-16 | 6 hrs | FY29 | 12 | 90028862 | A1 | 1000296238 | 16.09.2028 | 5000 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT90028862
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Pump Water Injection | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 2 | 90016932 | 1 | 1000152195 | 16.09.2028 | 5000 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP | 6300 | 43398 | 240 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP90016932
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Roller Load CS Pos9 | 2028-09-18 | 2028-09-18 | 4 hrs | FY29 | 8 | 90020188 | 1 | 1000294908 | 18.09.2028 | 20000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF09 | 6700 | 17309 | 5537 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF0990020188
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 PV271 Hydraulic Tune | 2028-09-18 | 2028-09-19 | 21 hrs | FY29 | 31.5 | 90017118 | 1 | 1000206785 | 18.09.2028 | 3000 | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190017118
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Jack Leg DE NCS | 2028-09-18 | 2028-09-18 | 4 hrs | FY29 | 8 | 90015958 | A1 | 1000152149 | 18.09.2028 | 15000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLR | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLR90015958
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 EncoderHarness Cab to Aframe Repl | 2028-09-18 | 2028-09-18 | 6 hrs | FY29 | 6 | 90036144 | A1 | 1000365257 | 18.09.2028 | 5000 | CLB-MP-DRLL-DR061 -ADSYST-HARNC | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ADSYST-HARNC90036144
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack RHR DE CS | 2028-09-22 | 2028-09-22 | 12 hrs | FY29 | 24 | 90030672 | A1 | 1000256593 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRR90030672
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cyl Mast Locking NCS | 2028-09-22 | 2028-09-22 | 12 hrs | FY29 | 24 | 90020197 | 1 | 1000256595 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYL | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cyl Mast Locking CS | 2028-09-22 | 2028-09-22 | 12 hrs | FY29 | 24 | 90030657 | A1 | 1000256594 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Main Hyd NCS | 2028-09-22 | 2028-09-22 | 6 hrs | FY29 | 6 | 90020235 | 1 | 1000256630 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP1 | 6700 | 14786 | 443 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP190020235
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Main Hyd CS | 2028-09-22 | 2028-09-22 | 6 hrs | FY29 | 6 | 90020234 | 1 | 1000256631 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP2 | 6700 | 14786 | 233 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP290020234
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Charge | 2028-09-22 | 2028-09-22 | 2 hrs | FY29 | 2 | 90020232 | 1 | 1000256626 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP3 | 6700 | 14786 | 443 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP390020232
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Hyd Pump Auxiliary | 2028-09-22 | 2028-09-22 | 4 hrs | FY29 | 4 | 90020236 | 1 | 1000256625 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-PPAUX | 6700 | 14786 | 443 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-PPAUX90020236
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Mast Module Qtr Life | 2028-09-22 | 2028-09-25 | 75 hrs | FY29 | 191 | 90030335 | A1 | 1000302773 | 22.09.2028 | 10000 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030335
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Sprocket LH | 2028-09-22 | 2028-09-22 | 10 hrs | FY29 | 20 | 90020186 | 1 | 1000303003 | 22.09.2028 | 10000 | CLB-MP-DRLL-DR2126-TRAVEL-SPRKL | 6700 | 14786 | 2066 | CLB-MP-DRLL-DR2126-TRAVEL-SPRKL90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Sprocket RH | 2028-09-22 | 2028-09-22 | 10 hrs | FY29 | 20 | 90020186 | 1 | 1000303004 | 22.09.2028 | 10000 | CLB-MP-DRLL-DR2126-TRAVEL-SPRKR | 6700 | 14786 | 9298 | CLB-MP-DRLL-DR2126-TRAVEL-SPRKR90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS GPS Components | 2028-09-22 | 2028-09-22 | 3 hrs | FY29 | 3 | 90029061 | A1 | 1000290911 | 22.09.2028 | 30000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPO | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPO90029061
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Chassis Harnesses | 2028-09-22 | 2028-09-26 | 104 hrs | FY29 | 208 | 90028944 | A1 | 1000289062 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cab Harnesses | 2028-09-22 | 2028-09-22 | 14 hrs | FY29 | 14 | 90028947 | A1 | 1000289063 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Compressor Harnesses | 2028-09-22 | 2028-09-22 | 12 hrs | FY29 | 12 | 90028948 | A1 | 1000289064 | 22.09.2028 | 15000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Harnesses | 2028-09-22 | 2028-09-24 | 56 hrs | FY29 | 112 | 90028949 | A1 | 1000289065 | 22.09.2028 | 30000 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS90028949
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Hydraulic Cooler Module | 2028-09-24 | 2028-09-24 | 12 hrs | FY29 | 24 | 90020220 | 1 | 1000256633 | 24.09.2028 | 30000 | CLB-MP-DRLL-DR2126-COOLER | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-COOLER90020220
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Engine Assy Caterpillar C32 | 2028-09-24 | 2028-09-26 | 50 hrs | FY29 | 150 | 90020393 | 1 | 1000256598 | 24.09.2028 | 15000 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Radiator Cooler Module | 2028-09-24 | 2028-09-24 | 12 hrs | FY29 | 24 | 90021617 | 1 | 1000256634 | 24.09.2028 | 30000 | CLB-MP-DRLL-DR2126-ENGINE-COSYS-RADTR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE-COSYS-RADTR90021617
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Adjust 500Hr Initial Valve Set | 2028-09-28 | 2028-09-28 | 12 hrs | FY29 | 24 | 90020604 | 1 | 1000296349 | 28.09.2028 | 500 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020604
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 EncoderHarness Cab to Aframe Repl | 2028-09-28 | 2028-09-28 | 6 hrs | FY29 | 6 | 90036144 | A1 | 1000365256 | 28.09.2028 | 5000 | CLB-MP-DRLL-DR060 -ADSYST-HARNC | 6300 | 69618 | 1221 | CLB-MP-DRLL-DR060 -ADSYST-HARNC90036144
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2028-09-29 | 2028-09-30 | 21 hrs | FY29 | 31.5 | 90017118 | 1 | 1000145852 | 29.09.2028 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS GPS Components | 2028-09-30 | 2028-09-30 | 3 hrs | FY29 | 3 | 90029061 | A1 | 1000296542 | 30.09.2028 | 30000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPO | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPO90029061
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Main Air Compressor LP | 2028-09-30 | 2028-10-01 | 24 hrs | FY29 | 48 | 90020192 | 1 | 1000296467 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR90020192
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Hydraulic Cooler Module | 2028-09-30 | 2028-09-30 | 12 hrs | FY29 | 24 | 90020220 | 1 | 1000296482 | 30.09.2028 | 30000 | CLB-MP-DRLL-DR2133-COOLER | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-COOLER90020220
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cab Harnesses | 2028-09-30 | 2028-09-30 | 14 hrs | FY29 | 14 | 90028947 | A1 | 1000296532 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS90028947
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Chassis Harnesses | 2028-09-30 | 2028-10-04 | 104 hrs | FY29 | 208 | 90028944 | A1 | 1000296531 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS90028944
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Compressor Harnesses | 2028-09-30 | 2028-09-30 | 12 hrs | FY29 | 12 | 90028948 | A1 | 1000296533 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS90028948
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Harnesses | 2028-09-30 | 2028-10-02 | 56 hrs | FY29 | 112 | 90028949 | A1 | 1000296534 | 30.09.2028 | 30000 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS90028949
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Engine Assy Caterpillar C32 | 2028-09-30 | 2028-10-02 | 50 hrs | FY29 | 150 | 90020393 | 1 | 1000296454 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90020393
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Radiator Cooler Module | 2028-09-30 | 2028-09-30 | 12 hrs | FY29 | 24 | 90021617 | 1 | 1000296483 | 30.09.2028 | 30000 | CLB-MP-DRLL-DR2133-ENGINE-COSYS-RADTR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ENGINE-COSYS-RADTR90021617
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack LHR DE NCS | 2028-09-30 | 2028-09-30 | 12 hrs | FY29 | 24 | 90020204 | 1 | 1000296447 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLR90020204
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cyl Mast Raise CS | 2028-09-30 | 2028-09-30 | 16 hrs | FY29 | 32 | 90020198 | 1 | 1000296452 | 30.09.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MRCYR | 6700 | 15193 | 9 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MRCYR90020198
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Mast Module Qtr Life | 2028-09-30 | 2028-10-03 | 75 hrs | FY29 | 191 | 90030335 | A1 | 1000302881 | 30.09.2028 | 10000 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030335
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Sprocket LH | 2028-09-30 | 2028-09-30 | 10 hrs | FY29 | 20 | 90020186 | 1 | 1000303017 | 30.09.2028 | 10000 | CLB-MP-DRLL-DR2133-TRAVEL-SPRKL | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-TRAVEL-SPRKL90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Sprocket RH | 2028-09-30 | 2028-09-30 | 10 hrs | FY29 | 20 | 90020186 | 1 | 1000303018 | 30.09.2028 | 10000 | CLB-MP-DRLL-DR2133-TRAVEL-SPRKR | 6700 | 15193 | 2584 | CLB-MP-DRLL-DR2133-TRAVEL-SPRKR90020186
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack LHF NDE NCS | 2028-10-03 | 2028-10-03 | 12 hrs | FY29 | 24 | 90020196 | 1 | 1000294840 | 03.10.2028 | 6000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF | 6700 | 17309 | 3262 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Adjust 500Hr Initial Valve Set | 2028-10-04 | 2028-10-04 | 12 hrs | FY29 | 24 | 90020604 | 1 | 1000294849 | 04.10.2028 | 500 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90020604
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS Vibration Sensors | 2028-10-05 | 2028-10-05 | 1 hr | FY29 | 1 | 90029062 | A1 | 1000296303 | 05.10.2028 | 10000 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS-DSVSN | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack LHF NDE NCS | 2028-10-06 | 2028-10-06 | 12 hrs | FY29 | 24 | 90020196 | 1 | 1000296168 | 06.10.2028 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF | 6700 | 16830 | 9883 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF90020196
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Wet Season Preparation | 2028-10-08 | 2028-10-09 | 22.5 hrs | FY29 | 22.5 | 90030417 | 1 | 1000303581 | 08.10.2028 | 12 Monthly | CLB-MP-DRLL-DR3126 | 4400 | 17885 | 17885 | CLB-MP-DRLL-DR312690030417
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cyl Mast Locking NCS | 2028-10-09 | 2028-10-09 | 12 hrs | FY29 | 24 | 90020197 | 1 | 1000296451 | 09.10.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MLCYL | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MLCYL90020197
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cyl Mast Locking CS | 2028-10-09 | 2028-10-09 | 12 hrs | FY29 | 24 | 90030657 | A1 | 1000296450 | 09.10.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MLCYR | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MLCYR90030657
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Drive Shaft Pump Drive | 2028-10-09 | 2028-10-09 | 6 hrs | FY29 | 12 | 90028862 | A1 | 1000296476 | 09.10.2028 | 5000 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG-DRSHT | 6700 | 15193 | 9653 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG-DRSHT90028862
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Service Airconditioning System | 2028-10-09 | 2028-10-09 | 12 hrs | FY29 | 12 | 90023281 | A1 | 1000241272 | 09.10.2028 | 12 Monthly | CLB-MP-DRLL-DR3126-STRUCT-CABIN-ACCOM | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-ACCOM90023281
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack RHR DE CS | 2028-10-10 | 2028-10-10 | 12 hrs | FY29 | 24 | 90030672 | A1 | 1000296449 | 10.10.2028 | 15000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRR | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRR90030672
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Wet Season Preparation | 2028-10-11 | 2028-10-12 | 22.5 hrs | FY29 | 22.5 | 90030417 | 1 | 1000365892 | 11.10.2028 | 12 Monthly | CLB-MP-DRLL-DR3110 | 5400 | 30612 | 30612 | CLB-MP-DRLL-DR311090030417
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Auto Lube Pump | 2028-10-11 | 2028-10-11 | 2 hrs | FY29 | 2 | 90013016 | B1 | 1000150465 | 11.10.2028 | 8000 | CLB-MP-DRLL-DR3110-GRSYST-ALBPP | 4200 | 30594 | 6871 | CLB-MP-DRLL-DR3110-GRSYST-ALBPP90013016
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Adjust 500Hr Initial Valve Set | 2028-10-13 | 2028-10-13 | 12 hrs | FY29 | 24 | 90020604 | 1 | 1000296177 | 13.10.2028 | 500 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90020604
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cooler Module Assembly | 2028-10-15 | 2028-10-17 | 42 hrs | FY29 | 53 | 90011659 | 1 | 1000098201 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -COOLER | 6300 | 69618 | 25954 | CLB-MP-DRLL-DR060 -COOLER90011659
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Tower Raise NCS | 2028-10-15 | 2028-10-15 | 16 hrs | FY29 | 20 | 90011666 | 1 | 1000233129 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYL90011666
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Tower Raise CS | 2028-10-15 | 2028-10-15 | 16 hrs | FY29 | 20 | 90011667 | 1 | 1000233128 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYR90011667
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Tower Angle Locking NCS | 2028-10-15 | 2028-10-15 | 4 hrs | FY29 | 4 | 90011670 | 1 | 1000242371 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TACYL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TACYL90011670
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Tower Angle Locking CS | 2028-10-15 | 2028-10-15 | 4 hrs | FY29 | 4 | 90011670 | 1 | 1000242372 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TACYR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TACYR90011670
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Stacking 8 Spool | 2028-10-15 | 2028-10-15 | 4 hrs | FY29 | 8 | 90011688 | 1 | 1000233124 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVS8S | 6300 | 69618 | 1869 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVS8S90011688
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Stacking 11 spool | 2028-10-15 | 2028-10-16 | 18 hrs | FY29 | 22 | 90011689 | 1 | 1000233125 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VV11S | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VV11S90011689
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Tension Cable | 2028-10-15 | 2028-10-15 | 2 hrs | FY29 | 2 | 90022224 | A1 | 1000232614 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVTNC | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVTNC90022224
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Hyd Motor Screw Jack NCS | 2028-10-15 | 2028-10-15 | 1 hr | FY29 | 1 | 90022221 | A1 | 1000232630 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTL90022221
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Hyd Motor Screw Jack CS | 2028-10-15 | 2028-10-15 | 1 hr | FY29 | 1 | 90022221 | A1 | 1000232629 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTR90022221
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Sheaves & Cables | 2028-10-15 | 2028-10-18 | 70 hrs | FY29 | 140 | 90029857 | A1 | 1000303723 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER | 6300 | 69618 | 25954 | CLB-MP-DRLL-DR060 -STRUCT-TOWER90029857
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Tower Cylinders | 2028-10-15 | 2028-10-16 | 34 hrs | FY29 | 58 | 90029866 | A1 | 1000303725 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER | 6300 | 69618 | 25954 | CLB-MP-DRLL-DR060 -STRUCT-TOWER90029866
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Gearbox Power Head | 2028-10-15 | 2028-10-17 | 50 hrs | FY29 | 69 | 90011716 | 1 | 1000232608 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PWRHD | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PWRHD90011716
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Screw Jack Cable Tension NCS | 2028-10-15 | 2028-10-15 | 6 hrs | FY29 | 12 | 90022222 | A1 | 1000232612 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SCBTL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SCBTL90022222
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Screw Jack Cable Tension CS | 2028-10-15 | 2028-10-15 | 6 hrs | FY29 | 12 | 90022222 | A1 | 1000232613 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SCBTR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SCBTR90022222
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Rod Support | 2028-10-15 | 2028-10-16 | 24 hrs | FY29 | 36 | 90022208 | A1 | 1000232620 | 15.10.2028 | 10000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-RDSPT | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-RDSPT90022208
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Overhaul Rod Changer & Carousel | 2028-10-15 | 2028-10-15 | 4 hrs | FY29 | 8 | 90029755 | A1 | 1000303726 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-CARAS | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-CARAS90029755
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Brkout Wrench & Fork Assy | 2028-10-15 | 2028-10-16 | 20 hrs | FY29 | 38 | 90029873 | A1 | 1000303728 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-BOWRH | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-BOWRH90029873
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Mast & A-Frame Harnesses | 2028-10-15 | 2028-10-18 | 70.5 hrs | FY29 | 70.5 | 90030429 | A1 | 1000303727 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO90030429
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Control Harnesses Chassis | 2028-10-15 | 2028-10-16 | 39 hrs | FY29 | 39 | 90029952 | A1 | 1000303819 | 15.10.2028 | 20000 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO90029952
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cylinder Jack RHF NDE CS | 2028-10-16 | 2028-10-16 | 12 hrs | FY29 | 24 | 90030670 | A1 | 1000294842 | 16.10.2028 | 6000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF | 6700 | 17309 | 9936 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF90030670
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Valve Drill & Propel Control | 2028-10-17 | 2028-10-17 | 6 hrs | FY29 | 6 | 90011694 | 1 | 1000098229 | 17.10.2028 | 20000 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDPC | 6300 | 69618 | 5892 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDPC90011694
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | STAT DR2132 Repl Receiver PRV | 2028-10-18 | 2028-10-18 | 1.5 hrs | FY29 | 1.5 | 90026270 | A1 | 1000323451 | 18.10.2028 | 18 Monthly | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK90026270
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Washdown Pump | 2028-10-21 | 2028-10-21 | 4 hrs | FY29 | 8 | 90030681 | A1 | 1000305735 | 21.10.2028 | 7500 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Adjust 500Hr Initial Valve Set | 2028-10-21 | 2028-10-21 | 12 hrs | FY29 | 24 | 90020604 | 1 | 1000256599 | 21.10.2028 | 500 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020604
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Service Airconditioning System | 2028-10-26 | 2028-10-26 | 12 hrs | FY29 | 12 | 90023280 | B1 | 1000241270 | 26.10.2028 | 12 Monthly | CLB-MP-DRLL-DR3110-STRUCT-CABIN-ACCOM | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-ACCOM90023280
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Adjust 500Hr Initial Valve Set | 2028-10-27 | 2028-10-27 | 12 hrs | FY29 | 24 | 90020604 | 1 | 1000296455 | 27.10.2028 | 500 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90020604
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast Cables | 2028-10-28 | 2028-10-29 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302808 | 28.10.2028 | 2500 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack RHF NDE CS | 2028-10-30 | 2028-10-30 | 12 hrs | FY29 | 24 | 90030670 | A1 | 1000256592 | 30.10.2028 | 6000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF | 6700 | 14786 | 2078 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF90030670
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Power Pack Quarter Life | 2028-11-01 | 2028-11-03 | 44 hrs | FY29 | 68 | 90029574 | A1 | 1000295365 | 01.11.2028 | 5000 | CLB-MP-DRLL-DR061 -ENGINE | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ENGINE90029574
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS Vibration Sensors | 2028-11-04 | 2028-11-04 | 1 hr | FY29 | 1 | 90029062 | A1 | 1000296541 | 04.11.2028 | 10000 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS-DSVSN | 6700 | 15193 | 4538 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Water Inj | 2028-11-13 | 2028-11-13 | 2 hrs | FY29 | 4 | 90031899 | A1 | 1000315433 | 13.11.2028 | 7500 | CLB-MP-DRLL-DR2132-DSTSUP-WTRPP | 6700 | 15850 | 7007 | CLB-MP-DRLL-DR2132-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Cylinder Jack LHF NDE NCS | 2028-11-14 | 2028-11-14 | 12 hrs | FY29 | 24 | 90020196 | 1 | 1000296340 | 14.11.2028 | 6000 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF | 6700 | 15850 | 2485 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Service 12M Air Conditioner | 2028-11-17 | 2028-11-17 | 6 hrs | FY29 | 12 | 90028298 | A1 | 1000296528 | 17.11.2028 | 12 Monthly | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN90028298
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Overhaul 24M Air Conditioner | 2028-11-17 | 2028-11-17 | 12 hrs | FY29 | 24 | 90028299 | A1 | 1000283244 | 17.11.2028 | 24 Monthly | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN90028299
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Cylinder Oscillation LH | 2028-11-19 | 2028-11-19 | 4 hrs | FY29 | 8 | 90021662 | A1 | 1000237273 | 19.11.2028 | 12000 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-TFCOL | 4400 | 17885 | 1925 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-TFCOL90021662
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Cylinder Oscillation RH | 2028-11-19 | 2028-11-19 | 4 hrs | FY29 | 8 | 90021663 | A1 | 1000237274 | 19.11.2028 | 12000 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-TFCOR | 4400 | 17885 | 1925 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-TFCOR90021663
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Cables | 2028-11-24 | 2028-11-25 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302812 | 24.11.2028 | 2500 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Pump Drive Gearbox | 2028-11-24 | 2028-11-25 | 30 hrs | FY29 | 78 | 90020181 | 1 | 1000256627 | 24.11.2028 | 15000 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG | 6700 | 14781 | 14781 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG90020181
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS LiDAR | 2028-11-26 | 2028-11-26 | 5 hrs | FY29 | 8 | 90029065 | A1 | 1000290914 | 26.11.2028 | 5000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Pump Water Inj | 2028-11-27 | 2028-11-27 | 2 hrs | FY29 | 4 | 90031899 | A1 | 1000315431 | 27.11.2028 | 7500 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP | 6700 | 17309 | 6755 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP90031899
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack RHF NDE CS | 2028-11-28 | 2028-11-28 | 12 hrs | FY29 | 24 | 90030670 | A1 | 1000296448 | 28.11.2028 | 6000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF | 6700 | 15193 | 2198 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS Vibration Sensors | 2028-11-29 | 2028-11-29 | 1 hr | FY29 | 1 | 90029062 | A1 | 1000296435 | 29.11.2028 | 10000 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS-DSVSN | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS-DSVSN90029062
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl ADS LiDAR | 2028-11-30 | 2028-11-30 | 5 hrs | FY29 | 8 | 90029065 | A1 | 1000296439 | 30.11.2028 | 5000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR | 6700 | 15850 | 10602 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR90029065
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Track Frame Module-NCS | 2028-11-30 | 2028-12-01 | 36 hrs | FY29 | 72 | 90022185 | A1 | 1000206315 | 30.11.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL90022185
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Track Frame Module CS | 2028-11-30 | 2028-12-01 | 36 hrs | FY29 | 72 | 90022183 | A1 | 1000206333 | 30.11.2028 | 20000 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR | 6300 | 69618 | 5134 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR90022183
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Fish Eye Camera | 2028-12-14 | 2028-12-14 | 16 hrs | FY29 | 16 | 90029067 | A1 | 1000296544 | 14.12.2028 | 10000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-HTCAM | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-HTCAM90029067
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Water Injection | 2028-12-19 | 2028-12-19 | 4 hrs | FY29 | 4 | 90021716 | A1 | 1000237308 | 19.12.2028 | 6000 | CLB-MP-DRLL-DR3126-DSTSUP-WTRPP | 4400 | 17885 | 7491 | CLB-MP-DRLL-DR3126-DSTSUP-WTRPP90021716
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Washdown Pump | 2028-12-19 | 2028-12-19 | 4 hrs | FY29 | 8 | 90030681 | A1 | 1000305731 | 19.12.2028 | 7500 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP90030681
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2028-12-22 | 2028-12-22 | 1 hr | FY29 | 1 | 90020876 | A1 | 1000237255 | 22.12.2028 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Compressor Coupling | 2028-12-24 | 2028-12-24 | 12 hrs | FY29 | 24 | 90030404 | A1 | 1000303547 | 24.12.2028 | 7500 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR-COUPL | 6700 | 15850 | 6250 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR-COUPL90030404
PV271 | Onsite PM | Drills | Fortescue | DR061 | STAT DR061 24M Pressure Vessel Insp Ext | 2028-12-24 | 2028-12-24 | 2 hrs | FY29 | 2 | 90025808 | A1 | 1000152199 | 24.12.2028 | 24 Monthly | CLB-MP-DRLL-DR061 -AIRSYS-ARTNK | 6300 | 43460 | 43460 | CLB-MP-DRLL-DR061 -AIRSYS-ARTNK90025808
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Cylinder Jack LHF NDE NCS | 2028-12-29 | 2028-12-29 | 12 hrs | FY29 | 24 | 90020196 | 1 | 1000256590 | 29.12.2028 | 6000 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF | 6700 | 14786 | 889 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF90020196
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Main Feed Chain | 2029-01-01 | 2029-01-01 | 8 hrs | FY29 | 16 | 90012999 | B1 | 1000150460 | 01.01.2029 | 2500 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH | 4200 | 30594 | 2427 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH90012999
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Rod Thread lube Pump | 2029-01-04 | 2029-01-04 | 2 hrs | FY29 | 2 | 90011732 | 1 | 1000098265 | 04.01.2029 | 10000 | CLB-MP-DRLL-DR060 -GRSYST-RTLPP | 6300 | 69618 | 56678 | CLB-MP-DRLL-DR060 -GRSYST-RTLPP90011732
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Pump Drive Gearbox | 2029-01-11 | 2029-01-12 | 30 hrs | FY29 | 78 | 90020181 | 1 | 1000296369 | 11.01.2029 | 15000 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG90020181
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Engine Valve Set | 2029-01-11 | 2029-01-11 | 8 hrs | FY29 | 16 | 90021723 | A1 | 1000268663 | 11.01.2029 | 3000 | CLB-MP-DRLL-DR3126-ENGINE | 4400 | 17885 | 4496 | CLB-MP-DRLL-DR3126-ENGINE90021723
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Cables | 2029-01-15 | 2029-01-16 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302816 | 15.01.2029 | 2500 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Cylinder Jack LHF NDE NCS | 2029-01-15 | 2029-01-15 | 12 hrs | FY29 | 24 | 90020196 | 1 | 1000296446 | 15.01.2029 | 6000 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF | 6700 | 15193 | 1223 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF90020196
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Fish Eye Camera | 2029-01-16 | 2029-01-16 | 16 hrs | FY29 | 16 | 90029067 | A1 | 1000290913 | 16.01.2029 | 10000 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-HTCAM | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-HTCAM90029067
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 12M Inspection Isolator Panel | 2029-01-22 | 2029-01-22 | 2 hrs | FY29 | 2 | 90022525 | A1 | 1000236546 | 22.01.2029 | 12 Monthly | CLB-MP-DRLL-DR3110-ELCTLV |  |  |  | CLB-MP-DRLL-DR3110-ELCTLV90022525
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl ADS Vibration Sensors | 2029-01-26 | 2029-01-26 | 1 hr | FY29 | 1 | 90029062 | A1 | 1000290910 | 26.01.2029 | 10000 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS-DSVSN | 6700 | 14786 | 2463 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS-DSVSN90029062
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Jack Leg NDE NCS | 2029-01-31 | 2029-01-31 | 4 hrs | FY29 | 8 | 90015956 | A1 | 1000152147 | 31.01.2029 | 15000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLF | 6300 | 43398 | 14180 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLF90015956
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Jack Leg NDE CS | 2029-01-31 | 2029-01-31 | 4 hrs | FY29 | 8 | 90015957 | A1 | 1000152148 | 31.01.2029 | 15000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRF | 6300 | 43398 | 14161 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRF90015957
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 XLF Repl Main Feed Chain | 2029-02-01 | 2029-02-01 | 8 hrs | FY29 | 16 | 90021711 | A1 | 1000237290 | 01.02.2029 | 2500 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH | 4400 | 17885 | 1481 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH90021711
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Primary Water Tank Anodes | 2029-02-05 | 2029-02-05 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377545 | 05.02.2029 | 10000 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKP | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Secondary Water Tank Anodes | 2029-02-05 | 2029-02-05 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377475 | 05.02.2029 | 10000 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKS | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2029-02-05 | 2029-02-06 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302772 | 05.02.2029 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3110 | DR3110 Repl Mast Beam Module | 2029-02-10 | 2029-02-12 | 48 hrs | FY29 | 96 | 90020410 | B1 | 1000231372 | 10.02.2029 | 18000 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-DMAST | 4200 | 30594 | 7471 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-DMAST90020410
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Cables | 2029-02-13 | 2029-02-14 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302880 | 13.02.2029 | 2500 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Rod Thread Lube | 2029-02-14 | 2029-02-14 | 2 hrs | FY29 | 2 | 90021715 | A1 | 1000237320 | 14.02.2029 | 6000 | CLB-MP-DRLL-DR3126-GRSYST-RTLPP | 4400 | 17885 | 9803 | CLB-MP-DRLL-DR3126-GRSYST-RTLPP90021715
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Primary Water Tank Anodes | 2029-02-14 | 2029-02-14 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377547 | 14.02.2029 | 10000 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKP | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Secondary Water Tank Anodes | 2029-02-14 | 2029-02-14 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377477 | 14.02.2029 | 10000 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKS | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Primary Water Tank Anodes | 2029-02-17 | 2029-02-17 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377542 | 17.02.2029 | 10000 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKP | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Secondary Water Tank Anodes | 2029-02-17 | 2029-02-17 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377473 | 17.02.2029 | 10000 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKS | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl ADS LiDAR | 2029-02-19 | 2029-02-19 | 5 hrs | FY29 | 8 | 90029065 | A1 | 1000296545 | 19.02.2029 | 5000 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 6M Static Line Inspection | 2029-03-01 | 2029-03-01 | 4 hrs | FY29 | 4 | 90013246 | A1 | 1000294755 | 01.03.2029 | 6 Monthly | CLB-MP-DRLL-DR2130-STRUCT |  |  |  | CLB-MP-DRLL-DR2130-STRUCT90013246
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl ADS LiDAR | 2029-03-08 | 2029-03-08 | 5 hrs | FY29 | 8 | 90029065 | A1 | 1000294939 | 08.03.2029 | 5000 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR | 6700 | 17309 | 10248 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR90029065
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 PV271 Hydraulic Tune | 2029-03-10 | 2029-03-11 | 21 hrs | FY29 | 31.5 | 90017118 | 1 | 1000206785 | 10.03.2029 | 3000 | CLB-MP-DRLL-DR061 | 6300 | 43421 | 43421 | CLB-MP-DRLL-DR06190017118
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 12M Air Cond Rencool Service | 2029-03-12 | 2029-03-12 | 8 hrs | FY29 | 16 | 90018579 | 1 | 1000180963 | 12.03.2029 | 12 Monthly | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN |  |  |  | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN90018579
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 12M Air Conditioner Service | 2029-03-12 | 2029-03-13 | 18 hrs | FY29 | 36 | 90018564 | 1 | 1000180532 | 12.03.2029 | 12 Monthly | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN |  |  |  | CLB-MP-DRLL-DR061 -STRUCT-CABIN-AIRCN90018564
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Mast Cables | 2029-03-13 | 2029-03-14 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302808 | 13.03.2029 | 2500 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | 6700 | 17309 | 17309 | CLB-MP-DRLL-DR2130-STRUCT-DMAST90030334
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Tower Raise NCS | 2029-03-18 | 2029-03-18 | 16 hrs | FY29 | 20 | 90011666 | 1 | 1000233139 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYL | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYL90011666
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Tower Raise CS | 2029-03-18 | 2029-03-18 | 16 hrs | FY29 | 20 | 90011667 | 1 | 1000233138 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYR | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYR90011667
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Tower Angle Locking NCS | 2029-03-18 | 2029-03-18 | 4 hrs | FY29 | 4 | 90011670 | 1 | 1000242376 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TACYL | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TACYL90011670
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Cyl Tower Angle Locking CS | 2029-03-18 | 2029-03-18 | 4 hrs | FY29 | 4 | 90011670 | 1 | 1000242377 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TACYR | 6300 | 43398 | 243 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TACYR90011670
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Valve Stacking 8 Spool | 2029-03-18 | 2029-03-18 | 4 hrs | FY29 | 8 | 90011688 | 1 | 1000233134 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVS8S | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVS8S90011688
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Valve Stacking 11 spool | 2029-03-18 | 2029-03-19 | 18 hrs | FY29 | 22 | 90011689 | 1 | 1000233135 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VV11S | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VV11S90011689
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Valve Tension Cable | 2029-03-18 | 2029-03-18 | 2 hrs | FY29 | 2 | 90022224 | A1 | 1000232642 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVTNC | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVTNC90022224
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Hyd Motor Screw Jack NCS | 2029-03-18 | 2029-03-18 | 1 hr | FY29 | 1 | 90022221 | A1 | 1000232658 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTL | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTL90022221
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Hyd Motor Screw Jack CS | 2029-03-18 | 2029-03-18 | 1 hr | FY29 | 1 | 90022221 | A1 | 1000232657 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTR | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTR90022221
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Tower Cylinders | 2029-03-18 | 2029-03-19 | 34 hrs | FY29 | 58 | 90029866 | A1 | 1000303732 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER90029866
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Sheaves & Cables | 2029-03-18 | 2029-03-21 | 70 hrs | FY29 | 140 | 90029857 | A1 | 1000303730 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER90029857
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Gearbox Power Head | 2029-03-18 | 2029-03-20 | 50 hrs | FY29 | 69 | 90011716 | 1 | 1000232636 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PWRHD | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PWRHD90011716
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Screw Jack Cable Tension NCS | 2029-03-18 | 2029-03-18 | 6 hrs | FY29 | 12 | 90022222 | A1 | 1000232640 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SCBTL | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SCBTL90022222
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Screw Jack Cable Tension CS | 2029-03-18 | 2029-03-18 | 6 hrs | FY29 | 12 | 90022222 | A1 | 1000232641 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SCBTR | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SCBTR90022222
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Rod Support | 2029-03-18 | 2029-03-19 | 24 hrs | FY29 | 36 | 90022208 | A1 | 1000232648 | 18.03.2029 | 10000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-RDSPT | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-RDSPT90022208
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Overhaul Rod Changer & Carousel | 2029-03-18 | 2029-03-18 | 4 hrs | FY29 | 8 | 90029755 | A1 | 1000303734 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-CARAS | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-CARAS90029755
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Brkout Wrench & Fork Assy | 2029-03-18 | 2029-03-19 | 20 hrs | FY29 | 38 | 90029873 | A1 | 1000303733 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-BOWRH | 6300 | 43398 | 1524 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-BOWRH90029873
PV271 | Onsite PM | Drills | Fortescue | DR061 | DR061 Repl Mast & A-Frame Harnesses | 2029-03-18 | 2029-03-21 | 70.5 hrs | FY29 | 70.5 | 90030429 | A1 | 1000303735 | 18.03.2029 | 20000 | CLB-MP-DRLL-DR061 -ELCTLV-HARNS-HARCO | 6300 | 43421 | 1524 | CLB-MP-DRLL-DR061 -ELCTLV-HARNS-HARCO90030429
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Washdown Pump | 2029-03-20 | 2029-03-20 | 4 hrs | FY29 | 8 | 90030681 | A1 | 1000305579 | 20.03.2029 | 7500 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP | 6700 | 15193 | 4539 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP90030681
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 PV271 Hydraulic Tune | 2029-03-21 | 2029-03-22 | 21 hrs | FY29 | 31.5 | 90017118 | 1 | 1000145852 | 21.03.2029 | 3000 | CLB-MP-DRLL-DR060 | 6300 | 69618 | 69618 | CLB-MP-DRLL-DR06090017118
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Operators Seat | 2029-03-23 | 2029-03-23 | 4 hrs | FY29 | 4 | 90021702 | A1 | 1000237296 | 23.03.2029 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-SEATS | 4400 | 17885 | 325 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-SEATS90021702
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Adjust 3750Hr Valve Set | 2029-03-24 | 2029-03-24 | 10.5 hrs | FY29 | 21 | 90020402 | 1 | 1000296350 | 24.03.2029 | 3750 | CLB-MP-DRLL-DR2132-ENGINE | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Power Pack Quarter Life | 2029-03-25 | 2029-03-27 | 44 hrs | FY29 | 68 | 90029578 | A1 | 1000295361 | 25.03.2029 | 5000 | CLB-MP-DRLL-DR060 -ENGINE | 6300 | 69618 | 16445 | CLB-MP-DRLL-DR060 -ENGINE90029578
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Adjust 3750Hr Valve Set | 2029-03-30 | 2029-03-30 | 10.5 hrs | FY29 | 21 | 90020402 | 1 | 1000294850 | 30.03.2029 | 3750 | CLB-MP-DRLL-DR2130-ENGINE | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 12M Air Conditioner Service | 2029-03-31 | 2029-04-01 | 18 hrs | FY29 | 36 | 90018564 | 1 | 1000180531 | 31.03.2029 | 12 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018564
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 12M Air Cond Rencool Service | 2029-03-31 | 2029-03-31 | 8 hrs | FY29 | 16 | 90018579 | 1 | 1000180961 | 31.03.2029 | 12 Monthly | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | 6300 | 69618 | 9798 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN90018579
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Adjust 3750Hr Valve Set | 2029-04-08 | 2029-04-08 | 10.5 hrs | FY29 | 21 | 90020402 | 1 | 1000296178 | 08.04.2029 | 3750 | CLB-MP-DRLL-DR2131-ENGINE | 6700 | 16830 | 586 | CLB-MP-DRLL-DR2131-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Cyl Jack Leg DE CS | 2029-04-08 | 2029-04-08 | 16 hrs | FY29 | 20 | 90011674 | 1 | 1000098218 | 08.04.2029 | 15000 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRR | 6300 | 69618 | 12921 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRR90011674
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Mast Cables | 2029-04-09 | 2029-04-10 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302812 | 09.04.2029 | 2500 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | 6700 | 16830 | 16830 | CLB-MP-DRLL-DR2131-STRUCT-DMAST90030334
D65 | Onsite PM | Drills | Fortescue | DR3126 | STAT DR3126 48M Pressure Vessel Insp Int | 2029-04-10 | 2029-04-10 | 4 hrs | FY29 | 4 | 90014200 | A1 | 1000366608 | 10.04.2029 | 48 Monthly | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK | 4400 | 17932 | 4496 | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK90014200
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl ADS PTZ Camera & LIDAR | 2029-04-15 | 2029-04-15 | 10 hrs | FY29 | 10 | 90029206 | A1 | 1000294229 | 15.04.2029 | 10000 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR-HTCAM | 6300 | 69618 | 8490 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR-HTCAM90029206
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | STAT DR2130 24M Pressure Vessel Insp Ext | 2029-04-16 | 2029-04-16 | 2 hrs | FY29 | 2 | 90025808 | A1 | 1000294920 | 16.04.2029 | 24 Monthly | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK | 6700 | 17370 | 17370 | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK90025808
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Adjust 3750Hr Valve Set | 2029-04-16 | 2029-04-16 | 10.5 hrs | FY29 | 21 | 90020402 | 1 | 1000256606 | 16.04.2029 | 3750 | CLB-MP-DRLL-DR2126-ENGINE | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-ENGINE90020402
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Fish Eye Camera | 2029-04-20 | 2029-04-20 | 16 hrs | FY29 | 16 | 90029067 | A1 | 1000296438 | 20.04.2029 | 10000 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-HTCAM | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-HTCAM90029067
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Adjust 3750Hr Valve Set | 2029-04-22 | 2029-04-22 | 10.5 hrs | FY29 | 21 | 90020402 | 1 | 1000296456 | 22.04.2029 | 3750 | CLB-MP-DRLL-DR2133-ENGINE | 6700 | 15193 | 13 | CLB-MP-DRLL-DR2133-ENGINE90020402
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Water & Fuel Tank Mount | 2029-04-28 | 2029-04-28 | 10 hrs | FY29 | 20 | 90017443 | 1 | 1000160295 | 28.04.2029 | 12 Monthly | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK | 6300 | 69618 | 17116 | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK90017443
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Hyd Motor Feed | 2029-05-03 | 2029-05-03 | 6 hrs | FY29 | 6 | 90022025 | A1 | 1000361223 | 03.05.2029 | 6000 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFEED | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFEED90022025
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Timing Chain Maintenance | 2029-05-03 | 2029-05-03 | 7 hrs | FY29 | 14 | 90022023 | A1 | 1000361221 | 03.05.2029 | 3000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP90022023
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Feed Chain Sprockets | 2029-05-03 | 2029-05-03 | 12 hrs | FY29 | 24 | 90022030 | A1 | 1000361222 | 03.05.2029 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHS | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHS90022030
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Hose Drum Sprocket | 2029-05-03 | 2029-05-03 | 6 hrs | FY29 | 6 | 90022032 | A1 | 1000361226 | 03.05.2029 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDS | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDS90022032
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Gearbox Power Head | 2029-05-03 | 2029-05-03 | 16 hrs | FY29 | 32 | 90021707 | A1 | 1000361224 | 03.05.2029 | 6000 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-PWRHD | 4400 | 17885 | 769 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-PWRHD90021707
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cyl Mast Raise NCS | 2029-05-08 | 2029-05-08 | 16 hrs | FY29 | 32 | 90030659 | A1 | 1000294847 | 08.05.2029 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYL | 6700 | 17309 | 11323 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYL90030659
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Pump Air Lubrication | 2029-05-09 | 2029-05-09 | 2 hrs | FY29 | 2 | 90021656 | A1 | 1000237302 | 09.05.2029 | 6000 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB | 4400 | 17885 | 6064 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB90021656
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Primary Water Tank Anodes | 2029-05-14 | 2029-05-14 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377551 | 14.05.2029 | 10000 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKP | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Secondary Water Tank Anodes | 2029-05-14 | 2029-05-14 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377481 | 14.05.2029 | 10000 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKS | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Main Air Compressor LP | 2029-05-20 | 2029-05-21 | 24 hrs | FY29 | 48 | 90020192 | 1 | 1000296229 | 20.05.2029 | 15000 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR | 6700 | 16830 | 11673 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR90020192
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Mast Cables | 2029-05-31 | 2029-06-01 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302816 | 31.05.2029 | 2500 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | 6700 | 15850 | 2252 | CLB-MP-DRLL-DR2132-STRUCT-DMAST90030334
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | STAT DR2133 Repl Receiver PRV | 2029-06-01 | 2029-06-01 | 1.5 hrs | FY29 | 1.5 | 90026270 | A1 | 1000323452 | 01.06.2029 | 18 Monthly | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK | 6700 | 15211 | 3277 | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK90026270
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Overhaul 24M Air Conditioner | 2029-06-04 | 2029-06-04 | 12 hrs | FY29 | 24 | 90028299 | A1 | 1000294923 | 04.06.2029 | 24 Monthly | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN | 6700 | 17309 | 6755 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN90028299
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Primary Water Tank Anodes | 2029-06-05 | 2029-06-05 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377549 | 05.06.2029 | 10000 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKP | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKP90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Secondary Water Tank Anodes | 2029-06-05 | 2029-06-05 | 8 hrs | FY29 | 8 | 90037834 | A1 | 1000377479 | 05.06.2029 | 10000 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKS | 6700 | 15850 | 15850 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKS90037834
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Drive Shaft Pump Drive | 2029-06-06 | 2029-06-06 | 6 hrs | FY29 | 12 | 90028862 | A1 | 1000294870 | 06.06.2029 | 5000 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT | 6700 | 17309 | 741 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT90028862
D65 | Onsite PM | Drills | Fortescue | DR3126 | DR3126 Repl Auto lube Pump Safety Valve | 2029-06-06 | 2029-06-06 | 1 hr | FY29 | 1 | 90020876 | A1 | 1000237255 | 06.06.2029 | 2000 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | 4400 | 17885 | 8607 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV90020876
MD6310 | Onsite PM | Drills | Fortescue | DR2130 | DR2130 Repl Cyl Mast Raise CS | 2029-06-13 | 2029-06-13 | 16 hrs | FY29 | 32 | 90020198 | 1 | 1000294846 | 13.06.2029 | 15000 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYR | 6700 | 17309 | 10627 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYR90020198
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl ADS LiDAR | 2029-06-15 | 2029-06-15 | 5 hrs | FY29 | 8 | 90029065 | A1 | 1000296307 | 15.06.2029 | 5000 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR | 6700 | 16830 | 11072 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR90029065
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Cylinder Jack RHF NDE CS | 2029-06-16 | 2029-06-16 | 12 hrs | FY29 | 24 | 90030670 | A1 | 1000296170 | 16.06.2029 | 6000 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF | 6700 | 16830 | 4546 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF90030670
MD6310 | Onsite PM | Drills | Fortescue | DR2131 | DR2131 Repl Drive Shaft Pump Drive | 2029-06-16 | 2029-06-16 | 6 hrs | FY29 | 12 | 90028862 | A1 | 1000296238 | 16.06.2029 | 5000 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT | 6700 | 16830 | 5228 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT90028862
MD6310 | Onsite PM | Drills | Fortescue | DR2132 | DR2132 Repl Washdown Pump | 2029-06-21 | 2029-06-21 | 4 hrs | FY29 | 8 | 90030681 | A1 | 1000305578 | 21.06.2029 | 7500 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP | 6700 | 15850 | 2962 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP90030681
MD6310 | Onsite PM | Drills | Fortescue | DR2126 | DR2126 Repl Mast Cables | 2029-06-21 | 2029-06-22 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302772 | 21.06.2029 | 2500 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | 6700 | 14786 | 14786 | CLB-MP-DRLL-DR2126-STRUCT-DMAST90030334
PV271 | Onsite PM | Drills | Fortescue | DR060 | DR060 Repl Pump Water Injection | 2029-06-27 | 2029-06-27 | 2 hrs | FY29 | 2 | 90011733 | 1 | 1000098266 | 27.06.2029 | 5000 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP | 6300 | 69618 | 1540 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP90011733
MD6310 | Onsite PM | Drills | Fortescue | DR2133 | DR2133 Repl Mast Cables | 2029-06-29 | 2029-06-30 | 20 hrs | FY29 | 60 | 90030334 | A1 | 1000302880 | 29.06.2029 | 2500 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | 6700 | 15193 | 15193 | CLB-MP-DRLL-DR2133-STRUCT-DMAST90030334
| Onsite PM | Haul | Fortescue |  | HAUL - COMPONENTS DURING PM
| Onsite PM | Haul | Fortescue |  | FY27 - HAUL - COMPONENTS DURING PM | 2026-07-01 |  |  | FY27
| Onsite PM | Haul | Fortescue | MOC | MAJOR ON CONDITION | 2026-07-01 | 2027-07-01 | 365 days | FY27
| Onsite PM | Haul | Fortescue | MOC | JULY | 2026-07-01 | 2026-07-31 | 30 days | FY27
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002/PM0004 Structural Repairs | 2026-07-01 | 2026-07-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | DT5404 | Liebherr T264 Engine Injector Harnesses | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | DT197 | 789D Haul Trucks Electrical MSR G20 - July assumption rolled forward | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | LL0003 | Repurposed: LL0003 Remote & Hardware Replacement | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | DT172 | 789D Haul Trucks Electrical MSR G20 - July assumption rolled forward | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2026-07-01 | 2026-07-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2026-07-01 | 2026-07-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 RH Fender Replacement | 2026-07-01 | 2026-07-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2026-07-01 | 2026-07-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 A- Frame Replacement | 2026-07-01 | 2026-07-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | AUGUST | 2026-08-01 | 2026-08-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2026-07-01 | 2026-07-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2026-08-01 | 2026-08-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | DT169 | CAT 789 Axle Housing Replacement | 2026-08-01 | 2026-08-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Fuel Tanks | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2026-08-01 | 2026-08-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2026-08-01 | 2026-08-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 RH Fender Replacement | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2026-08-01 | 2026-08-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2026-08-01 | 2026-08-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2026-08-01 | 2026-08-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | SEPTEMBER | 2026-09-01 | 2026-09-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2026-09-01 | 2026-09-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2026-09-01 | 2026-09-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2026-09-01 | 2026-09-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2026-09-01 | 2026-09-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2026-09-01 | 2026-09-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2026-09-01 | 2026-09-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2026-09-01 | 2026-09-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2026-09-01 | 2026-09-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2026-09-01 | 2026-09-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2026-09-01 | 2026-09-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2026-09-01 | 2026-09-30 | 29 days | FY27
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002/PM0004 Wood Decking Repairs | 2026-09-01 | 2026-09-30 | 29 days | FY27
| Onsite PM | Haul | Fortescue | MOC | OCTOBER | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2026-10-01 | 2026-10-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2026-10-01 | 2026-10-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 RH Fender Replacement | 2026-10-01 | 2026-10-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2026-10-01 | 2026-10-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2026-10-01 | 2026-10-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2026-10-01 | 2026-10-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2026-10-01 | 2026-10-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2026-10-01 | 2026-10-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | NOVEMBER | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 A- Frame Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2026-11-01 | 2026-11-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Fuel Tanks | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2026-11-01 | 2026-11-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2026-11-01 | 2026-11-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2026-11-01 | 2026-11-30 | 29 days | FY27
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003/PM0006 Wood decking Repairs | 2026-11-01 | 2026-11-30 | 29 days | FY27
| Onsite PM | Haul | Fortescue | MOC | DECEMBER | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | DT192 | 789D Haul Trucks Electrical MSR G20 - July assumption rolled forward | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2026-12-01 | 2026-12-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2026-12-01 | 2026-12-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2026-12-01 | 2026-12-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2026-12-01 | 2026-12-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2026-12-01 | 2026-12-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2026-12-01 | 2026-12-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2026-12-01 | 2026-12-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2026-12-01 | 2026-12-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2026-12-01 | 2026-12-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | JANUARY | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2027-01-01 | 2027-01-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2027-01-01 | 2027-01-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2027-01-01 | 2027-01-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 RH Fender Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Data Loggers | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2027-01-01 | 2027-01-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2027-01-01 | 2027-01-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2027-01-01 | 2027-01-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2027-01-01 | 2027-01-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2027-01-01 | 2027-01-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2027-01-01 | 2027-01-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | FEBRUARY | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 A- Frame Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2027-02-01 | 2027-02-28 | 27 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Fuel Tanks | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Data Loggers | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2027-02-01 | 2027-02-28 | 27 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2027-02-01 | 2027-02-28 | 27 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2027-02-01 | 2027-02-28 | 27 days | FY27
| Onsite PM | Haul | Fortescue | MOC | MARCH | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Bolt On Valve Guards | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789D Fuel Tanks replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2027-03-01 | 2027-03-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Data Loggers | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2027-03-01 | 2027-03-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2027-03-01 | 2027-03-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2027-03-01 | 2027-03-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | APRIL | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Axle Housing Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2027-04-01 | 2027-04-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2027-04-01 | 2027-04-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 RH Fender Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Data Loggers | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2027-04-01 | 2027-04-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2027-04-01 | 2027-04-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2027-04-01 | 2027-04-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2027-04-01 | 2027-04-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2027-04-01 | 2027-04-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2027-04-01 | 2027-04-30 | 29 days | FY27
| Onsite PM | Haul | Fortescue | MOC | MAY | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 A- Frame Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | IMU Replacement - BER Planning | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Fuel Tanks | 2027-05-01 | 2027-05-31 | 30 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | PCS Replacement - BER Planning | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Intake Piping | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Data Loggers | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2027-05-01 | 2027-05-31 | 30 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2027-05-01 | 2027-05-31 | 30 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2027-05-01 | 2027-05-31 | 30 days | FY27
| Onsite PM | Haul | Fortescue | MOC | JUNE | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | A6 Auto ECM Replacement - BER Planning | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Air Boxes Replacement | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Bell Crank Replacement | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Chassis Harness Replacement | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Steering Arms | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789D Fuel Tanks replacement | 2027-06-01 | 2027-06-30 | 29 days | FY27
All - Haul | Onsite PM | Haul | Fortescue | All - Haul | Lidar Replacements -BER Planning | 2027-06-01 | 2027-06-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Chassis Harnesses | 2027-06-01 | 2027-06-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | T264 Warranty Provision - CB | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | 789D Exhaust System and Lagging | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Cat 789 Access Ladder/ Platform/ Walkways Replacement | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Header Tank + Platforms | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CAT 789 Hydraulic Pipes | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Data Loggers | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D GPS Antennas | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | CMD 789D Radar Box Replacement | 2027-06-01 | 2027-06-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Access Ladders | 2027-06-01 | 2027-06-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Engine Injector Harnesses | 2027-06-01 | 2027-06-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Exhaust Components | 2027-06-01 | 2027-06-30 | 29 days | FY27
T264 | Onsite PM | Haul | Fortescue | All - T264 | Liebherr T264 Front Wheel Speed Sensor Harness | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | All - 789D | Light Weight Tray Wear Packages | 2027-06-01 | 2027-06-30 | 29 days | FY27
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Service Suspension Cylinders | 2026-07-09 | 2026-07-09 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106948 | 09.07.2026 | 11000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN | 7500 | 85978 | 21221 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN90012840
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Repl Engine Cat C32 | 2026-07-13 | 2026-07-15 | 50 hrs | FY27 | 194 | 90029079 | A1 | 1000290641 | 15.12.2026 | 18000 | CLB-MP-SUPP-SV021 -ENGINE | 3300 | 54098 | 5 | CLB-MP-SUPP-SV021 -ENGINE90029079
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Overhaul Airconditioner | 2026-07-13 | 2026-07-14 | 24 hrs | FY27 | 24 | 90029085 | A1 | 1000290644 | 15.12.2026 | 9000 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-AIRCN | 3300 | 54098 | 5 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-AIRCN90029085
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Hub & Spindle RH | 2026-07-16 | 2026-07-17 | 26 hrs | FY27 | 50 | 90026194 | A1 | 1000221750 | 19.03.2028 | 24000 | CLB-MP-SUPP-WC3108-STRUCT-AXLES-HUBRH | 5000 | 17738 | 232 | CLB-MP-SUPP-WC3108-STRUCT-AXLES-HUBRH90026194
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Engine Midlife complete | 2026-07-30 | 2026-08-03 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156491 | 28.07.2026 | 11000 | CLB-MP-HAUL-DT164 -ENGINE | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Pump Drive Driveshaft Unis | 2026-07-30 | 2026-07-30 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034161 | 26.07.2026 | 11000 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Pump Brake Control | 2026-07-30 | 2026-07-30 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034173 | 26.07.2026 | 11000 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP | 7500 | 81875 | 7647 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Brake Relay Valve | 2026-07-30 | 2026-07-30 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078363 | 26.07.2026 | 11000 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Spiders Transmission Driveshaft | 2026-07-30 | 2026-07-30 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154370 | 26.07.2026 | 11000 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT-UNVSL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Service Suspension Cylinders | 2026-08-05 | 2026-08-05 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106897 | 05.08.2026 | 11000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN | 7500 | 83931 | 10985 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Water Cannon | 2026-08-05 | 2026-08-05 | 12 hrs | FY27 | 24 | 90015535 | 1 | 1000133454 | 12.01.2026 | 12 Monthly | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | 5000 | 65823 | 12836 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON90015535
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Engine Midlife complete | 2026-08-06 | 2026-08-10 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156731 | 29.07.2026 | 11000 | CLB-MP-HAUL-DT179 -ENGINE | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Brake Control | 2026-08-06 | 2026-08-06 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035000 | 24.07.2026 | 11000 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Brake Relay Valve | 2026-08-06 | 2026-08-06 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078610 | 24.07.2026 | 11000 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Steering LH | 2026-08-07 | 2026-08-07 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000036001 | 23.05.2026 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYL | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Steering Ball Studs | 2026-08-07 | 2026-08-08 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385466 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STLTR | 7500 | 86259 | 25173 | CLB-MP-HAUL-DT197 -STRSYS-STLTR90038356
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Service Air Conditioner 12M | 2026-08-07 | 2026-08-07 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000362685 | 22.08.2026 | 12 Monthly | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Overhaul Air Conditioner 24M | 2026-08-10 | 2026-08-12 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000300051 | 17.02.2026 | 24 Monthly | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Fuel Tank Mounts | 2026-08-10 | 2026-08-10 | 8 hrs | FY27 | 16 | 90009887 | 1 | 1000078885 | 18.06.2026 | 22000 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULTK | 7500 | 85978 | 23065 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULTK90009887
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Hyd Pump Steering Main | 2026-08-10 | 2026-08-10 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000036122 | 18.12.2025 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STPMP | 7500 | 85978 | 20031 | CLB-MP-HAUL-DT199 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Steering HMU | 2026-08-10 | 2026-08-10 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000036123 | 18.12.2025 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STHMU | 7500 | 85978 | 20031 | CLB-MP-HAUL-DT199 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Service Suspension Cylinders | 2026-08-10 | 2026-08-10 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106948 | 08.01.2026 | 11000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN | 7500 | 85978 | 21221 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Transmission | 2026-08-10 | 2026-08-10 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034824 | 21.07.2026 | 11000 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP | 7500 | 85284 | 11308 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Brake Control | 2026-08-10 | 2026-08-10 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034835 | 21.03.2026 | 11000 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP | 7500 | 85284 | 6894 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Brake Relay Valve | 2026-08-10 | 2026-08-10 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000079623 | 21.03.2026 | 11000 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Spiders Transmission Driveshaft | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154394 | 21.03.2026 | 11000 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT-UNVSL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Transmission | 2026-08-10 | 2026-08-11 | 28 hrs | FY27 | 48 | 90003093 | 1 | 1000034712 | 16.08.2026 | 22000 | CLB-MP-HAUL-DT174 -TRNSYS-TRANS | 7500 | 83749 | 21827 | CLB-MP-HAUL-DT174 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Pump Transmission | 2026-08-10 | 2026-08-10 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034714 | 06.09.2026 | 11000 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TMCPP | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Transmission Oil Cooler | 2026-08-10 | 2026-08-10 | 13 hrs | FY27 | 13 | 90003532 | 1 | 1000040983 | 15.08.2026 | 22000 | CLB-MP-HAUL-DT174 -TRNSYS-TROLC | 7500 | 83749 | 21779 | CLB-MP-HAUL-DT174 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Cyl Steering RH | 2026-08-10 | 2026-08-10 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034731 | 17.05.2026 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYR | 7500 | 83749 | 16824 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Cyl Hoist RH | 2026-08-10 | 2026-08-11 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000034458 | 07.08.2026 | 28000 | CLB-MP-HAUL-DT169 -HYDSYS-HOCYL-HCYLR | 7500 | 93410 | 28092 | CLB-MP-HAUL-DT169 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Seat Operators | 2026-08-10 | 2026-08-10 | 4 hrs | FY27 | 4 | 90004012 | 1 | 1000161980 | 06.08.2026 | 10000 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-SEATS | 5000 | 63833 | 10370 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-SEATS90004012
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Service Air Conditioner 12M | 2026-08-17 | 2026-08-17 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000360961 | 25.07.2026 | 12 Monthly | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Service Air Conditioner 12M | 2026-08-17 | 2026-08-17 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000350428 | 25.04.2026 | 12 Monthly | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Brake Slack Adjuster Front | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072241 | 23.07.2026 | 18000 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Brake Slack Adjuster Rear | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072279 | 23.07.2026 | 18000 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Service Suspension Cylinders | 2026-08-17 | 2026-08-17 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106892 | 08.01.2026 | 11000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN | 7500 | 90364 | 10497 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Service Suspension Cylinders | 2026-08-17 | 2026-08-17 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106945 | 09.03.2026 | 11000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN | 7500 | 85161 | 14133 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Brake Wheel RH | 2026-08-17 | 2026-08-18 | 33 hrs | FY27 | 61 | 90003105 | 2 | 1000035936 | 25.08.2026 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-AXLES-HUBRH | 7500 | 85161 | 21658 | CLB-MP-HAUL-DT196 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Service Suspension Cylinders | 2026-08-17 | 2026-08-17 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106897 | 08.01.2026 | 11000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN | 7500 | 83931 | 10985 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Cyl Suspension RHF | 2026-08-17 | 2026-08-18 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067860 | 02.06.2026 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRF | 7500 | 83931 | 23419 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Engine Midlife complete | 2026-08-17 | 2026-08-21 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156875 | 11.08.2026 | 11000 | CLB-MP-HAUL-DT188 -ENGINE | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Pump Drive Driveshaft Unis | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000035450 | 10.08.2026 | 11000 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR-DRSHT | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Pump Brake Control | 2026-08-17 | 2026-08-17 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035462 | 10.08.2026 | 11000 | CLB-MP-HAUL-DT188 -BRKSYS-HYFPP | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Brake Relay Valve | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078743 | 10.08.2026 | 11000 | CLB-MP-HAUL-DT188 -BRKSYS-BRVRL | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Spiders Transmission Driveshaft | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154418 | 10.08.2026 | 11000 | CLB-MP-HAUL-DT188 -FDRSYS-DRSHT-UNVSL | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Cyl Steering LH | 2026-08-17 | 2026-08-17 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034067 | 09.07.2026 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYL | 7500 | 83473 | 15556 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Steering Ball Studs | 2026-08-17 | 2026-08-18 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385440 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STLTR | 7500 | 83473 | 34836 | CLB-MP-HAUL-DT184 -STRSYS-STLTR90038356
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Adjust Engine Valve Set | 2026-08-17 | 2026-08-17 | 6 hrs | FY27 | 6 | 90017451 | A1 | 1000290591 | 20.05.2026 | 3000 | CLB-MP-SUPP-SV019 -ENGINE | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -ENGINE90017451
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Operators Seat | 2026-08-17 | 2026-08-17 | 4 hrs | FY27 | 8 | 90003066 | A1 | 1000033887 | 26.05.2026 | 6000 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-SEATS | 2500 | 48856 | 5106 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-SEATS90003066
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Service Suspension Cylinders | 2026-08-21 | 2026-08-21 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106892 | 21.08.2026 | 11000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN | 7500 | 90364 | 10497 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN90012840
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Motor Brake O/Cooler Fan | 2026-08-21 | 2026-08-21 | 4 hrs | FY27 | 4 | 90013225 | A1 | 1000110288 | 29.08.2026 | 11000 | CLB-MP-SUPP-LL0002-BRKSYS-MBOCF | 3500 | 91736 | 10879 | CLB-MP-SUPP-LL0002-BRKSYS-MBOCF90013225
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Transmission Pump | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 6 | 90003991 | 1 | 1000221742 | 28.05.2026 | 10000 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP90003991
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Air Drier & Tank | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 24 | 90004010 | 1 | 1000221764 | 28.06.2026 | 9000 | CLB-MP-SUPP-WC3108-PNEUMC-AIRDR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-PNEUMC-AIRDR90004010
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Repl Water Cannon & Valves | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 48 | 90033662 | A1 | 1000339269 | 03.09.2026 | 24 Monthly | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | 5000 | 17738 | 8813 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON90033662
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Hyd Pump Steering Main | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034231 | 24.07.2026 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STPMP | 7500 | 78966 | 14957 | CLB-MP-HAUL-DT165 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Steering HMU | 2026-08-24 | 2026-08-24 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034232 | 24.07.2026 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STHMU | 7500 | 78966 | 14957 | CLB-MP-HAUL-DT165 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Service Suspension Cylinders | 2026-08-24 | 2026-08-24 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106872 | 26.07.2026 | 11000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Hyd Pump Steering Main | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034176 | 22.07.2026 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STPMP | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Steering HMU | 2026-08-24 | 2026-08-24 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034177 | 22.07.2026 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STHMU | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Brake Oil Cooler Front | 2026-08-24 | 2026-08-24 | 5 hrs | FY27 | 5 | 90003108 | 1 | 1000080235 | 02.09.2026 | 22000 | CLB-MP-HAUL-DT164 -BRKSYS-BROCO-BROCF | 7500 | 81875 | 21550 | CLB-MP-HAUL-DT164 -BRKSYS-BROCO-BROCF90003108
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Service Suspension Cylinders | 2026-08-24 | 2026-08-24 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106947 | 10.11.2025 | 11000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Service Air Conditioner | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160404 | 06.08.2026 | 5500 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-AIRCN | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 3Y Air Tank LH Int Insp & PRV Repl | 2026-08-24 | 2026-08-24 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389447 | 13.08.2026 | 36 Monthly | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH | 7500 | 88415 | 16378 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 3Y Air Tank RH Int Insp & PRV Repl | 2026-08-24 | 2026-08-24 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389449 | 13.08.2026 | 36 Monthly | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH | 7500 | 88415 | 16378 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Differential | 2026-08-24 | 2026-08-26 | 44 hrs | FY27 | 66 | 90003098 | 1 | 1000035581 | 05.07.2026 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-DIFFL | 7500 | 90698 | 21479 | CLB-MP-HAUL-DT190 -FDRSYS-DIFFL90003098
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Slack Adjuster Front | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072248 | 24.08.2026 | 18000 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACF | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Slack Adjuster Rear | 2026-08-24 | 2026-08-24 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072286 | 24.08.2026 | 18000 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACR90009307
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Steering Linkages | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 24 | 90003056 | A1 | 1000033936 | 26.08.2026 | 9000 | CLB-MP-SUPP-SV020 -STRSYS-STLTR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STLTR90003056
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Engine Midlife Complete | 2026-08-24 | 2026-08-26 | 52 hrs | FY27 | 66 | 90029080 | A1 | 1000290595 | 23.08.2026 | 9000 | CLB-MP-SUPP-SV020 -ENGINE | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -ENGINE90029080
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Transmission | 2026-08-24 | 2026-08-25 | 26 hrs | FY27 | 50 | 90003036 | A1 | 1000033913 | 10.09.2026 | 18000 | CLB-MP-SUPP-SV020 -TRNSYS-TRANS | 3300 | 44025 | 17710 | CLB-MP-SUPP-SV020 -TRNSYS-TRANS90003036
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Oil Cooler Trans | 2026-08-24 | 2026-08-24 | 6 hrs | FY27 | 6 | 90003040 | A1 | 1000033917 | 10.09.2026 | 18000 | CLB-MP-SUPP-SV020 -TRNSYS-TROLC | 3300 | 44025 | 17710 | CLB-MP-SUPP-SV020 -TRNSYS-TROLC90003040
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Cylinder Steering LH | 2026-08-24 | 2026-08-24 | 14 hrs | FY27 | 26 | 90003054 | A1 | 1000033933 | 26.08.2026 | 9000 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYL | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYL90003054
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Cylinder Steering RH | 2026-08-24 | 2026-08-24 | 14 hrs | FY27 | 26 | 90003054 | A1 | 1000033934 | 26.08.2026 | 9000 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYR | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYR90003054
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Overhaul Airconditioner | 2026-08-24 | 2026-08-25 | 24 hrs | FY27 | 24 | 90029085 | A1 | 1000290597 | 23.08.2026 | 9000 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN | 3300 | 44025 | 4749 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN90029085
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Service Air Conditioner 12M | 2026-08-24 | 2026-08-24 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000362640 | 20.08.2026 | 12 Monthly | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Steering LHS | 2026-08-24 | 2026-08-24 | 8 hrs | FY27 | 14 | 90029373 | A1 | 1000314548 | 09.04.2027 | 20000 | CLB-MP-HAUL-DT5411-STRSYS-STRCY-STCYL | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Overhaul Air Conditioner 24M | 2026-08-24 | 2026-08-26 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000314527 | 11.06.2026 | 24 Monthly | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Steering HMU | 2026-08-31 | 2026-08-31 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000036000 | 17.08.2025 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STHMU | 7500 | 86259 | 22691 | CLB-MP-HAUL-DT197 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Service Air Conditioner | 2026-08-31 | 2026-08-31 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160403 | 03.08.2026 | 5500 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-AIRCN | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Slack Adjuster Front | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000150699 | 18.09.2026 | 18000 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACF | 7500 | 51346 | 16991 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Slack Adjuster Rear | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000150700 | 18.09.2026 | 18000 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACR | 7500 | 51346 | 16991 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 3Y Air Tank LH Int Insp & PRV Repl | 2026-08-31 | 2026-08-31 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389463 | 15.08.2026 | 36 Monthly | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH | 7500 | 51345 | 51345 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 3Y Air Tank RH Int Insp & PRV Repl | 2026-08-31 | 2026-08-31 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389465 | 15.08.2026 | 36 Monthly | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH | 7500 | 51345 | 51345 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Spiders Transmission Driveshaft | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154400 | 24.07.2026 | 11000 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT-UNVSL | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Cyl Steering LH | 2026-08-31 | 2026-08-31 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000035005 | 26.06.2026 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYL | 7500 | 84079 | 16016 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Steering Ball Studs | 2026-08-31 | 2026-09-01 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385458 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT193 -STRSYS-STLTR | 7500 | 83140 | 19357 | CLB-MP-HAUL-DT193 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Air Dryer | 2026-08-31 | 2026-08-31 | 7 hrs | FY27 | 14 | 90003115 | 1 | 1000035775 | 09.11.2025 | 22000 | CLB-MP-HAUL-DT193 -PNEUMC-AIRDR | 7500 | 83140 | 27958 | CLB-MP-HAUL-DT193 -PNEUMC-AIRDR90003115
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Service Suspension Cylinders | 2026-08-31 | 2026-08-31 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106942 | 25.04.2026 | 11000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN | 7500 | 83140 | 13267 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Brake Wheel RH | 2026-08-31 | 2026-09-01 | 33 hrs | FY27 | 61 | 90003105 | 2 | 1000035762 | 09.07.2026 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBRH | 7500 | 83140 | 21307 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Service Suspension Cylinders | 2026-08-31 | 2026-08-31 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106898 | 15.02.2026 | 11000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 24M Timber Replacement | 2026-08-31 | 2026-09-01 | 36 hrs | FY27 | 72 | 90031571 | A1 | 1000311691 | 20.01.2026 | 24 Monthly | CLB-MP-SUPP-LL0003-STRUCT |  |  |  | CLB-MP-SUPP-LL0003-STRUCT90031571
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 3Y Air Tank Int Insp & PRV Repl | 2026-08-31 | 2026-08-31 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389211 | 16.07.2026 | 36 Monthly | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK | 4200 | 53807 | 16976 | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK90038750
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Final Drive RH | 2026-08-31 | 2026-08-31 | 17 hrs | FY27 | 33 | 90032602 | A1 | 1000110242 | 01.01.2028 | 22000 | CLB-MP-SUPP-PM0004-FDRSYS-FDRVE-FDRRH | 3500 | 91736 | 17196 | CLB-MP-SUPP-PM0004-FDRSYS-FDRVE-FDRRH90032602
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Brake Cool Pmp & Mtr - Repl | 2026-08-31 | 2026-08-31 | 4 hrs | FY27 | 8 | 90018286 | 1 | 1000174669 | 06.07.2026 | 10000 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM1 | 4200 | 71996 | 1615 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM190018286
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Service Suspension Cylinders | 2026-09-07 | 2026-09-07 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106885 | 20.03.2026 | 11000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Steering Ball Studs | 2026-09-07 | 2026-09-08 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385426 | 29.06.2026 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STLTR | 7500 | 81791 | 15833 | CLB-MP-HAUL-DT177 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Steering HMU | 2026-09-07 | 2026-09-07 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034894 | 22.06.2026 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STHMU | 7500 | 81791 | 15830 | CLB-MP-HAUL-DT177 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Cyl Steering LH | 2026-09-07 | 2026-09-07 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034785 | 05.06.2026 | 15000 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYL | 7500 | 82722 | 16512 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Service Suspension Cylinders | 2026-09-07 | 2026-09-07 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106883 | 08.01.2026 | 11000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN | 7500 | 83749 | 23899 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Pump Drive Driveshaft Unis | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000116272 | 05.09.2026 | 11000 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR-DRSHT | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Brake Relay Valve | 2026-09-07 | 2026-09-07 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078553 | 06.09.2026 | 11000 | CLB-MP-HAUL-DT174 -BRKSYS-BRVRL | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Spiders Transmission Driveshaft | 2026-09-07 | 2026-09-07 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154390 | 06.09.2026 | 11000 | CLB-MP-HAUL-DT174 -FDRSYS-DRSHT-UNVSL | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Engine Midlife complete | 2026-09-07 | 2026-09-11 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156651 | 09.09.2026 | 11000 | CLB-MP-HAUL-DT174 -ENGINE | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Cyl Hoist LH | 2026-09-07 | 2026-09-08 | 25 hrs | FY27 | 49 | 90003114 | 1 | 1000034569 | 11.09.2026 | 28000 | CLB-MP-HAUL-DT171 -HYDSYS-HOCYL-HCYLL | 7500 | 90182 | 27381 | CLB-MP-HAUL-DT171 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Cyl Hoist RH | 2026-09-07 | 2026-09-08 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000034570 | 11.09.2026 | 28000 | CLB-MP-HAUL-DT171 -HYDSYS-HOCYL-HCYLR | 7500 | 90182 | 27381 | CLB-MP-HAUL-DT171 -HYDSYS-HOCYL-HCYLR90003114
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 OverHaul Tag Link | 2026-09-07 | 2026-09-08 | 24 hrs | FY27 | 48 | 90003068 | A1 | 1000033889 | 10.09.2024 | 18000 | CLB-MP-SUPP-SV019 -STRUCT-CHASS-TAGLK | 2500 | 48856 | 20187 | CLB-MP-SUPP-SV019 -STRUCT-CHASS-TAGLK90003068
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 3Y Air Tank Int Insp & PRV Repl | 2026-09-07 | 2026-09-07 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389213 | 16.07.2026 | 36 Monthly | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK90038750
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Float Brake Control Valve - Cabin | 2026-09-09 | 2026-09-09 | 3 hrs | FY27 | 3 | 90018289 | 1 | 1000174671 | 09.09.2026 | 10000 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-FLBCV | 4200 | 53807 | 9242 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-FLBCV90018289
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Pump Brake Cooling LH | 2026-09-11 | 2026-09-11 | 6 hrs | FY27 | 6 | 90013223 | A1 | 1000110285 | 14.04.2026 | 11000 | CLB-MP-SUPP-LL0002-BRKSYS-PBCLH | 3500 | 91736 | 17126 | CLB-MP-SUPP-LL0002-BRKSYS-PBCLH90013223
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Auto Lube Pump | 2026-09-11 | 2026-09-11 | 2 hrs | FY27 | 2 | 90013205 | A1 | 1000110269 | 20.07.2026 | 6000 | CLB-MP-SUPP-PM0004-GRSYST-ALBPP | 3500 | 91736 | 6593 | CLB-MP-SUPP-PM0004-GRSYST-ALBPP90013205
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Service Air Conditioner 12M | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000349643 | 22.03.2026 | 12 Monthly | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Cyl Steering LH | 2026-09-14 | 2026-09-14 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000035943 | 28.12.2025 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYL | 7500 | 85161 | 19642 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Steering Ball Studs | 2026-09-14 | 2026-09-15 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385464 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STLTR | 7500 | 85161 | 19642 | CLB-MP-HAUL-DT196 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Service Suspension Cylinders | 2026-09-14 | 2026-09-14 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106943 | 29.12.2025 | 11000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Ovhl Axle A Frame | 2026-09-14 | 2026-09-15 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130664 | 08.09.2026 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-AFRME | 7500 | 86451 | 44175 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Ovhl Axle Housing Dogbone | 2026-09-14 | 2026-09-15 | 22 hrs | FY27 | 42 | 90003118 | 1 | 1000035836 | 08.09.2026 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-TAGLK | 7500 | 86451 | 21176 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Cyl Suspension LHR | 2026-09-14 | 2026-09-15 | 23 hrs | FY27 | 42 | 90003122 | 1 | 1000035841 | 08.09.2026 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYLR | 7500 | 86451 | 21176 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Cyl Suspension RHR | 2026-09-14 | 2026-09-15 | 23 hrs | FY27 | 42 | 90003122 | 1 | 1000035842 | 08.09.2026 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYRR | 7500 | 86451 | 21176 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 3Y Air Tank LH Int Insp & PRV Repl | 2026-09-14 | 2026-09-14 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389431 | 29.08.2026 | 36 Monthly | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH | 7500 | 86244 | 37431 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 3Y Air Tank RH Int Insp & PRV Repl | 2026-09-14 | 2026-09-14 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389433 | 29.08.2026 | 36 Monthly | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH | 7500 | 86244 | 37431 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Service Air Conditioner | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160384 | 05.07.2026 | 5500 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Brake Slack Adjuster Front | 2026-09-14 | 2026-09-14 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072236 | 21.09.2026 | 18000 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACF | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Brake Slack Adjuster Rear | 2026-09-14 | 2026-09-14 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072274 | 21.09.2026 | 18000 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACR | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Steering Ball Studs | 2026-09-14 | 2026-09-15 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385454 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT191 -STRSYS-STLTR | 7500 | 87047 | 22425 | CLB-MP-HAUL-DT191 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Ovhl Axle A Frame | 2026-09-14 | 2026-09-15 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130661 | 17.04.2026 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-AFRME | 7500 | 87047 | 40828 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Service Suspension Cylinders | 2026-09-14 | 2026-09-14 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106940 | 28.12.2025 | 11000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Service Air Conditioner | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160397 | 15.09.2026 | 5500 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-AIRCN | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Cyl Suspension RHR | 2026-09-14 | 2026-09-15 | 23 hrs | FY27 | 42 | 90003122 | 1 | 1000035668 | 20.08.2026 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYRR | 7500 | 87047 | 21779 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Cyl Steering LH | 2026-09-14 | 2026-09-14 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000035116 | 05.06.2026 | 15000 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYL | 7500 | 83441 | 16291 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Steering Ball Studs | 2026-09-14 | 2026-09-15 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385434 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT181 -STRSYS-STLTR | 7500 | 83441 | 22176 | CLB-MP-HAUL-DT181 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Steering Ball Studs | 2026-09-14 | 2026-09-15 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385418 | 11.09.2026 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STLTR | 7500 | 82651 | 14071 | CLB-MP-HAUL-DT173 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Hyd Pump Steering Main | 2026-09-14 | 2026-09-14 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034673 | 11.09.2026 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STPMP | 7500 | 82651 | 14071 | CLB-MP-HAUL-DT173 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Cyl Steering LH | 2026-09-14 | 2026-09-14 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034675 | 09.07.2026 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYL | 7500 | 82651 | 15446 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Ovhl Axle A Frame | 2026-09-14 | 2026-09-15 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130645 | 01.09.2026 | 22000 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-AFRME | 7500 | 82651 | 40795 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-AFRME90015390
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 3Y Air Tank Int Insp & PRV Repl | 2026-09-14 | 2026-09-14 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389219 | 25.07.2026 | 36 Monthly | CLB-MP-SUPP-WC014 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC014 -PNEUMC-PNTNK90038750
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 250Hr Initial Valve Set | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 24 | 90028724 | A1 | 1000289421 | 09.07.2026 | 250 | CLB-MP-SUPP-WC012 -ENGINE | 5000 | 67273 | 20856 | CLB-MP-SUPP-WC012 -ENGINE90028724
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Service Air Conditioner 12M | 2026-09-14 | 2026-09-14 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000342850 | 29.12.2025 | 12 Monthly | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 3Y Air Tank Int Insp & PRV Repl | 2026-09-16 | 2026-09-16 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389221 | 16.09.2026 | 36 Monthly | CLB-MP-SUPP-WC015 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC015 -PNEUMC-PNTNK90038750
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 3Y Air Tank Int Insp & PRV Repl | 2026-09-17 | 2026-09-17 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389223 | 17.09.2026 | 36 Monthly | CLB-MP-SUPP-WC3108-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC3108-PNEUMC-PNTNK90038750
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Service Air Conditioner 12M | 2026-09-17 | 2026-09-17 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000365677 | 17.09.2026 | 12 Monthly | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Service Air Conditioner 12M | 2026-09-17 | 2026-09-17 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000365627 | 17.09.2026 | 12 Monthly | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Service Air Conditioner | 2026-09-19 | 2026-09-19 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160400 | 19.09.2026 | 5500 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-AIRCN | 7500 | 86451 | 4331 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 3Y Air Tank Int Insp & PRV Repl | 2026-09-20 | 2026-09-20 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389217 | 25.08.2026 | 36 Monthly | CLB-MP-SUPP-WC013 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC013 -PNEUMC-PNTNK90038750
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Service Air Conditioner 12M | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000349687 | 22.03.2026 | 12 Monthly | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Service Air Conditioner | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 12 | 90017450 | 2 | 1000160407 | 13.09.2026 | 5500 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-AIRCN | 7500 | 49737 | 9540 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Steering Ball Studs | 2026-09-21 | 2026-09-22 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385400 | 23.07.2026 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STLTR | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Cyl Steering LH | 2026-09-21 | 2026-09-21 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034178 | 21.07.2026 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYL | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Cyl Steering RH | 2026-09-21 | 2026-09-21 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034179 | 21.07.2026 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYR | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Final Drive LH | 2026-09-21 | 2026-09-22 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000035582 | 30.08.2026 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-FDRVE-FDRLH | 7500 | 90698 | 21431 | CLB-MP-HAUL-DT190 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Final Drive RH | 2026-09-21 | 2026-09-22 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000035583 | 30.08.2026 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-FDRVE-FDRRH | 7500 | 90698 | 21431 | CLB-MP-HAUL-DT190 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Service Air Conditioner | 2026-09-21 | 2026-09-21 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160375 | 02.10.2026 | 5500 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-AIRCN | 7500 | 93142 | 15366 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Service Suspension Cylinders | 2026-09-24 | 2026-09-24 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106894 | 20.08.2025 | 11000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN | 7500 | 92088 | 41661 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN90012840
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 3Y Air Tank Int Insp & PRV Repl | 2026-09-26 | 2026-09-26 | 4.5 hrs | FY27 | 4.5 | 90038756 | A1 | 1000389471 | 26.09.2026 | 36 Monthly | CLB-MP-SUPP-PM0004-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-PM0004-PNEUMC-PNTNK90038756
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Overhaul Air Conditioner 24M | 2026-09-28 | 2026-09-30 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000300347 | 14.03.2026 | 24 Monthly | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN | 6500 | 11246 | 4814 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Overhaul Air Conditioner 24M | 2026-09-28 | 2026-09-30 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000314067 | 10.03.2026 | 24 Monthly | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Suspension LHR | 2026-09-28 | 2026-09-29 | 36 hrs | FY27 | 108 | 90029379 | A1 | 1000314092 | 18.07.2028 | 28000 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYLR | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Service Air Conditioner 12M | 2026-09-28 | 2026-09-28 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000357054 | 29.06.2026 | 12 Monthly | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Overhaul Air Conditioner 24M | 2026-09-28 | 2026-09-30 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000314217 | 10.04.2026 | 24 Monthly | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Ovhl Axle A Frame | 2026-09-28 | 2026-09-29 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130667 | 06.02.2026 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-AFRME | 7500 | 86259 | 25918 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Service Suspension Cylinders | 2026-09-28 | 2026-09-28 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106946 | 26.07.2026 | 11000 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN | 7500 | 86259 | 11085 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 3Y Air Tank LH Int Insp & PRV Repl | 2026-09-28 | 2026-09-28 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389443 | 09.08.2026 | 36 Monthly | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH | 7500 | 85995 | 85995 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 3Y Air Tank RH Int Insp & PRV Repl | 2026-09-28 | 2026-09-28 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389445 | 09.08.2026 | 36 Monthly | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH | 7500 | 85995 | 85995 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Pump Transmission | 2026-09-28 | 2026-09-28 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000116278 | 05.09.2026 | 11000 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TMCPP | 7500 | 86259 | 10405 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Hyd Motor Axle Lube Rear | 2026-09-28 | 2026-09-28 | 9 hrs | FY27 | 9 | 90003101 | 1 | 1000035990 | 06.09.2026 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-HYM01 | 7500 | 86259 | 21377 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Suspension LHF | 2026-09-28 | 2026-09-29 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067894 | 04.09.2026 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYLF | 7500 | 86259 | 21427 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 3Y Air Tank LH Int Insp & PRV Repl | 2026-09-28 | 2026-09-28 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389459 | 28.09.2026 | 36 Monthly | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH | 7500 | 49299 | 49299 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 3Y Air Tank RH Int Insp & PRV Repl | 2026-09-28 | 2026-09-28 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389461 | 28.09.2026 | 36 Monthly | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH | 7500 | 49299 | 49299 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Ovhl Axle A Frame | 2026-09-28 | 2026-09-29 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000152635 | 25.09.2026 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-AFRME | 7500 | 84546 | 36386 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Brake Slack Adjuster Front | 2026-09-28 | 2026-09-28 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072253 | 04.08.2026 | 18000 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACF | 7500 | 82554 | 18183 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Brake Slack Adjuster Rear | 2026-09-28 | 2026-09-28 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072291 | 04.08.2026 | 18000 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACR | 7500 | 82554 | 18183 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Hyd Pump Steering Main | 2026-09-28 | 2026-09-28 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000035883 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STPMP | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Steering HMU | 2026-09-28 | 2026-09-28 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000035884 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STHMU | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Steering Ball Studs | 2026-09-28 | 2026-09-29 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385462 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STLTR | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STLTR90038356
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Adjust Engine Valve Set | 2026-09-28 | 2026-09-28 | 12 hrs | FY27 | 24 | 90015645 | A1 | 1000238537 | 24.09.2026 | 4500 | CLB-MP-SUPP-SV4105-ENGINE | 2500 | 8917 | 8917 | CLB-MP-SUPP-SV4105-ENGINE90015645
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Engine Midlife complete | 2026-09-28 | 2026-09-30 | 58 hrs | FY27 | 70 | 90015646 | A1 | 1000238538 | 24.09.2026 | 9000 | CLB-MP-SUPP-SV4105-ENGINE | 2500 | 8917 | 8917 | CLB-MP-SUPP-SV4105-ENGINE90015646
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Repl Pump Brake Charge & Cooling | 2026-09-28 | 2026-09-28 | 6 hrs | FY27 | 6 | 90037883 | A1 | 1000379761 | 24.09.2026 | 9000 | CLB-MP-SUPP-SV4105-BRKSYS-BRPMP | 2500 | 8917 | 8917 | CLB-MP-SUPP-SV4105-BRKSYS-BRPMP90037883
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Overhaul Airconditioner | 2026-09-28 | 2026-09-29 | 24 hrs | FY27 | 24 | 90011566 | A1 | 1000238539 | 24.09.2026 | 9000 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-AIRCN | 2500 | 8917 | 5023 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-AIRCN90011566
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Service Air Conditioner 12M | 2026-09-28 | 2026-09-28 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000346232 | 30.01.2026 | 12 Monthly | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN90029300
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Replace Auto Lube Pump | 2026-09-29 | 2026-09-29 | 2 hrs | FY27 | 2 | 90011565 | A1 | 1000214378 | 29.09.2026 | 9000 | CLB-MP-SUPP-SV4105-GRSYST-ALBPP | 2500 | 8917 | 8917 | CLB-MP-SUPP-SV4105-GRSYST-ALBPP90011565
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Pump Drive Driveshaft Unis | 2026-10-02 | 2026-10-02 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000035926 | 02.10.2026 | 11000 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR-DRSHT | 7500 | 85161 | 22315 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Service Suspension Cylinders | 2026-10-02 | 2026-10-02 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106882 | 02.10.2026 | 11000 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN | 7500 | 82651 | 12558 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Hyd Pump Steering Main | 2026-10-05 | 2026-10-05 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034286 | 28.09.2026 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STPMP | 7500 | 95491 | 13970 | CLB-MP-HAUL-DT166 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Ovhl Axle A Frame | 2026-10-05 | 2026-10-06 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130669 | 11.04.2026 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-AFRME | 7500 | 85978 | 35622 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Ovhl Axle Housing Dogbone | 2026-10-05 | 2026-10-06 | 22 hrs | FY27 | 42 | 90003118 | 1 | 1000036133 | 11.04.2026 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-TAGLK | 7500 | 85978 | 24506 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Steering Ball Studs | 2026-10-05 | 2026-10-06 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385470 | 13.04.2026 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STLTR | 7500 | 85978 | 20031 | CLB-MP-HAUL-DT199 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Ovhl Axle A Frame | 2026-10-05 | 2026-10-06 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130647 | 16.02.2026 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-AFRME | 7500 | 85284 | 35516 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Cyl Hoist LH | 2026-10-05 | 2026-10-06 | 25 hrs | FY27 | 49 | 90003114 | 1 | 1000150592 | 05.10.2026 | 28000 | CLB-MP-HAUL-DT224 -HYDSYS-HOCYL-HCYLL | 7500 | 49737 | 26795 | CLB-MP-HAUL-DT224 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Service Air Conditioner | 2026-10-05 | 2026-10-05 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160385 | 12.04.2027 | 5500 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-AIRCN | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Brake Wheel LH | 2026-10-05 | 2026-10-06 | 32 hrs | FY27 | 38 | 90003104 | 2 | 1000034997 | 15.10.2026 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-AXLES-HUBLH | 7500 | 84079 | 20488 | CLB-MP-HAUL-DT179 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Engine Midlife complete | 2026-10-05 | 2026-10-09 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156763 | 18.09.2026 | 11000 | CLB-MP-HAUL-DT181 -ENGINE | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Service Suspension Cylinders | 2026-10-05 | 2026-10-05 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106890 | 19.09.2026 | 11000 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN | 7500 | 83441 | 10065 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Pump Transmission | 2026-10-05 | 2026-10-05 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035100 | 20.09.2026 | 11000 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TMCPP | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Brake Relay Valve | 2026-10-05 | 2026-10-05 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000079642 | 20.09.2026 | 11000 | CLB-MP-HAUL-DT181 -BRKSYS-BRVRL | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Spiders Transmission Driveshaft | 2026-10-05 | 2026-10-05 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154404 | 20.09.2026 | 11000 | CLB-MP-HAUL-DT181 -FDRSYS-DRSHT-UNVSL | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -FDRSYS-DRSHT-UNVSL90017135
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 3Y Air Tank Int Insp & PRV Repl | 2026-10-05 | 2026-10-05 | 4.5 hrs | FY27 | 4.5 | 90038750 | A1 | 1000389215 | 16.08.2026 | 36 Monthly | CLB-MP-SUPP-WC012 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC012 -PNEUMC-PNTNK90038750
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Slack Adjuster Front | 2026-10-10 | 2026-10-10 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072256 | 10.10.2026 | 18000 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Slack Adjuster Rear | 2026-10-10 | 2026-10-10 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072294 | 10.10.2026 | 18000 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Differential | 2026-10-12 | 2026-10-14 | 44 hrs | FY27 | 66 | 90003098 | 1 | 1000034936 | 28.08.2026 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-DIFFL | 7500 | 81600 | 20689 | CLB-MP-HAUL-DT178 -FDRSYS-DIFFL90003098
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Suspension LHF | 2026-10-12 | 2026-10-13 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067758 | 25.09.2026 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYLF | 7500 | 81237 | 20804 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Drive Line Axle LH | 2026-10-12 | 2026-10-12 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123508 | 25.09.2026 | 30000 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX-AXLLH | 7500 | 81237 | 29153 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Drive Line Axle RH | 2026-10-12 | 2026-10-12 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123569 | 25.09.2026 | 30000 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX-AXLRH | 7500 | 81237 | 29153 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Pump Transmission | 2026-10-12 | 2026-10-12 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034107 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TMCPP | 7500 | 81237 | 9334 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Steering Ball Studs | 2026-10-12 | 2026-10-13 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385476 | 17.10.2026 | 15000 | CLB-MP-HAUL-DT225 -STRSYS-STLTR | 7500 | 51346 | 13495 | CLB-MP-HAUL-DT225 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Engine Midlife complete | 2026-10-12 | 2026-10-16 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156603 | 12.10.2026 | 11000 | CLB-MP-HAUL-DT171 -ENGINE | 7500 | 90182 | 8268 | CLB-MP-HAUL-DT171 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Engine Midlife complete | 2026-10-12 | 2026-10-16 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156539 | 17.10.2026 | 11000 | CLB-MP-HAUL-DT167 -ENGINE | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Pump Drive Driveshaft Unis | 2026-10-12 | 2026-10-12 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000116268 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR-DRSHT | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Pump Transmission | 2026-10-12 | 2026-10-12 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034327 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TMCPP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Pump Brake Control | 2026-10-12 | 2026-10-12 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034338 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT167 -BRKSYS-HYFPP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Service Suspension Cylinders | 2026-10-12 | 2026-10-12 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106876 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN | 7500 | 83303 | 9432 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Brake Relay Valve | 2026-10-12 | 2026-10-12 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078420 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT167 -BRKSYS-BRVRL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Spiders Transmission Driveshaft | 2026-10-12 | 2026-10-12 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154376 | 16.10.2026 | 11000 | CLB-MP-HAUL-DT167 -FDRSYS-DRSHT-UNVSL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -FDRSYS-DRSHT-UNVSL90017135
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Operators Seat | 2026-10-19 | 2026-10-19 | 4 hrs | FY27 | 8 | 90003066 | A1 | 1000034008 | 19.10.2026 | 6000 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-SEATS | 3300 | 54098 | 5038 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-SEATS90003066
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Cyl Suspension LHF | 2026-10-19 | 2026-10-20 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067810 | 23.10.2026 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYLF | 7500 | 85284 | 20366 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Steering Ball Studs | 2026-10-19 | 2026-10-20 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385402 | 22.07.2026 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STLTR | 7500 | 78966 | 14957 | CLB-MP-HAUL-DT165 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Cyl Steering LH | 2026-10-19 | 2026-10-19 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034233 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYL | 7500 | 78966 | 13578 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Cyl Steering RH | 2026-10-19 | 2026-10-19 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034234 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYR | 7500 | 78966 | 13578 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Cyl Hoist LH | 2026-10-19 | 2026-10-20 | 25 hrs | FY27 | 49 | 90003114 | 1 | 1000034402 | 23.10.2026 | 28000 | CLB-MP-HAUL-DT168 -HYDSYS-HOCYL-HCYLL | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Cyl Hoist RH | 2026-10-19 | 2026-10-20 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000034403 | 23.10.2026 | 28000 | CLB-MP-HAUL-DT168 -HYDSYS-HOCYL-HCYLR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Water Cannon Inspect | 2026-10-19 | 2026-10-19 | 3 hrs | FY27 | 3 | 90033661 | A1 | 1000338796 | 19.10.2026 | 6 Monthly | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Brake Slack Adjuster Front | 2026-10-26 | 2026-10-26 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072255 | 12.10.2026 | 18000 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACF | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Brake Slack Adjuster Rear | 2026-10-26 | 2026-10-26 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072293 | 12.10.2026 | 18000 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Engine Midlife complete | 2026-10-26 | 2026-10-30 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156571 | 01.09.2026 | 11000 | CLB-MP-HAUL-DT169 -ENGINE | 7500 | 93410 | 9210 | CLB-MP-HAUL-DT169 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Cyl Steering LH | 2026-10-26 | 2026-10-26 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000035885 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYL | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Cyl Steering RH | 2026-10-26 | 2026-10-26 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000035886 | 25.09.2026 | 15000 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYR | 7500 | 82554 | 14001 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Cyl Steering RH | 2026-11-01 | 2026-11-01 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000036060 | 01.11.2026 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYR | 7500 | 88680 | 13193 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Differential | 2026-11-02 | 2026-11-04 | 44 hrs | FY27 | 66 | 90003098 | 1 | 1000034274 | 05.11.2026 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-DIFFL | 7500 | 95491 | 19244 | CLB-MP-HAUL-DT166 -FDRSYS-DIFFL90003098
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Torque Converter Charge | 2026-11-02 | 2026-11-02 | 5 hrs | FY27 | 5 | 90003095 | 1 | 1000080216 | 10.11.2026 | 22000 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TCCPP | 7500 | 86451 | 19761 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Drive Line Axle LH | 2026-11-02 | 2026-11-02 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123523 | 07.11.2026 | 30000 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX-AXLLH | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Drive Line Axle RH | 2026-11-02 | 2026-11-02 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123584 | 07.11.2026 | 30000 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX-AXLRH | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Service Suspension Cylinders | 2026-11-02 | 2026-11-02 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106871 | 13.10.2026 | 11000 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN | 7500 | 81237 | 42658 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Cyl Steering RH | 2026-11-02 | 2026-11-02 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000035468 | 09.11.2026 | 15000 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYR | 7500 | 83931 | 13040 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Engine Midlife complete | 2026-11-07 | 2026-11-11 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156811 | 07.11.2026 | 11000 | CLB-MP-HAUL-DT184 -ENGINE | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Service Air Conditioner | 2026-11-07 | 2026-11-07 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160395 | 07.11.2026 | 5500 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-AIRCN | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Pump Drive Driveshaft Unis | 2026-11-08 | 2026-11-08 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000116261 | 08.11.2026 | 11000 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR-DRSHT | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Pump Brake Control | 2026-11-08 | 2026-11-08 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034059 | 08.11.2026 | 11000 | CLB-MP-HAUL-DT184 -BRKSYS-HYFPP | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Service Suspension Cylinders | 2026-11-08 | 2026-11-08 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106893 | 08.11.2026 | 11000 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN | 7500 | 83473 | 21188 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Brake Relay Valve | 2026-11-08 | 2026-11-08 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078667 | 08.11.2026 | 11000 | CLB-MP-HAUL-DT184 -BRKSYS-BRVRL | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Spiders Transmission Driveshaft | 2026-11-08 | 2026-11-08 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154410 | 08.11.2026 | 11000 | CLB-MP-HAUL-DT184 -FDRSYS-DRSHT-UNVSL | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Service Air Conditioner | 2026-11-09 | 2026-11-09 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160373 | 09.11.2026 | 5500 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-AIRCN | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Drive Line Axle LH | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000150733 | 07.11.2026 | 30000 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX-AXLLH | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Drive Line Axle RH | 2026-11-09 | 2026-11-09 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000150734 | 07.11.2026 | 30000 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX-AXLRH | 7500 | 51346 | 28044 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX-AXLRH90014552
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Pump Steering | 2026-11-09 | 2026-11-09 | 6 hrs | FY27 | 6 | 90003051 | A1 | 1000033870 | 25.06.2026 | 18000 | CLB-MP-SUPP-SV019 -STRSYS-STPMP | 2500 | 48856 | 16821 | CLB-MP-SUPP-SV019 -STRSYS-STPMP90003051
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Valve Steering | 2026-11-09 | 2026-11-10 | 24 hrs | FY27 | 48 | 90003053 | A1 | 1000033872 | 25.06.2026 | 18000 | CLB-MP-SUPP-SV019 -STRSYS-STVLV | 2500 | 48856 | 16821 | CLB-MP-SUPP-SV019 -STRSYS-STVLV90003053
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Hub and Spindle LH | 2026-11-09 | 2026-11-10 | 22 hrs | FY27 | 42 | 90003069 | A1 | 1000033890 | 25.06.2026 | 18000 | CLB-MP-SUPP-SV019 -STRUCT-AXLES-HUBLH | 2500 | 48856 | 16821 | CLB-MP-SUPP-SV019 -STRUCT-AXLES-HUBLH90003069
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Hub and Spindle RH | 2026-11-09 | 2026-11-10 | 22 hrs | FY27 | 42 | 90003069 | A2 | 1000033891 | 25.06.2026 | 18000 | CLB-MP-SUPP-SV019 -STRUCT-AXLES-HUBRH | 2500 | 48856 | 16821 | CLB-MP-SUPP-SV019 -STRUCT-AXLES-HUBRH90003069
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Tyre Sense Battery | 2026-11-12 | 2026-11-12 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163989 | 12.11.2026 | 24 Monthly | CLB-MP-HAUL-DT225 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT225 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Service Air Conditioner | 2026-11-12 | 2026-11-12 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160393 | 12.11.2026 | 5500 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-AIRCN | 7500 | 93170 | 13899 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 3Y Air Tank LH Int Insp & PRV Repl | 2026-11-15 | 2026-11-15 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389339 | 15.11.2026 | 36 Monthly | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH | 7500 | 90894 | 90894 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 3Y Air Tank RH Int Insp & PRV Repl | 2026-11-15 | 2026-11-15 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389341 | 15.11.2026 | 36 Monthly | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH | 7500 | 90894 | 90894 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Hyd Pump Steering Main | 2026-11-16 | 2026-11-16 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034948 | 16.11.2026 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STPMP | 7500 | 81600 | 12786 | CLB-MP-HAUL-DT178 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Steering HMU | 2026-11-16 | 2026-11-16 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034949 | 16.11.2026 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STHMU | 7500 | 81600 | 12786 | CLB-MP-HAUL-DT178 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Steering Ball Studs | 2026-11-16 | 2026-11-17 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385428 | 16.11.2026 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STLTR | 7500 | 81600 | 12900 | CLB-MP-HAUL-DT178 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Brake Slack Adjuster Front | 2026-11-17 | 2026-11-17 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000150609 | 17.11.2026 | 18000 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACF | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Pump Drive Driveshaft Unis | 2026-11-21 | 2026-11-21 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034878 | 21.11.2026 | 11000 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR-DRSHT | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Pump Brake Control | 2026-11-21 | 2026-11-21 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034890 | 21.11.2026 | 11000 | CLB-MP-HAUL-DT177 -BRKSYS-HYFPP | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Service Suspension Cylinders | 2026-11-21 | 2026-11-21 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106886 | 21.11.2026 | 11000 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN | 7500 | 81791 | 14442 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Brake Relay Valve | 2026-11-21 | 2026-11-21 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078572 | 21.11.2026 | 11000 | CLB-MP-HAUL-DT177 -BRKSYS-BRVRL | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Spiders Transmission Driveshaft | 2026-11-21 | 2026-11-21 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154396 | 21.11.2026 | 11000 | CLB-MP-HAUL-DT177 -FDRSYS-DRSHT-UNVSL | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Brake Slack Adjuster Front | 2026-11-22 | 2026-11-22 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072252 | 22.11.2026 | 18000 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Brake Slack Adjuster Rear | 2026-11-22 | 2026-11-22 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072290 | 22.11.2026 | 18000 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Engine Midlife complete | 2026-11-24 | 2026-11-28 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156699 | 24.11.2026 | 11000 | CLB-MP-HAUL-DT177 -ENGINE | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Brake Slack Adjuster Front | 2026-11-24 | 2026-11-24 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072249 | 24.11.2026 | 18000 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Brake Slack Adjuster Rear | 2026-11-24 | 2026-11-24 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072287 | 24.11.2026 | 18000 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Steering HMU | 2026-11-25 | 2026-11-25 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034674 | 25.11.2026 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STHMU | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Cyl Steering RH | 2026-11-25 | 2026-11-25 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034676 | 25.11.2026 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Pump Transmission | 2026-11-26 | 2026-11-26 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034879 | 26.11.2026 | 11000 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TMCPP | 7500 | 81791 | 3161 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Steering Ball Studs | 2026-11-27 | 2026-11-28 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385472 | 27.11.2026 | 15000 | CLB-MP-HAUL-DT200 -STRSYS-STLTR | 7500 | 92548 | 12596 | CLB-MP-HAUL-DT200 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Cyl Steering LH | 2026-11-27 | 2026-11-27 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000036059 | 27.11.2026 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYL | 7500 | 88680 | 12630 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Service Air Conditioner | 2026-11-28 | 2026-11-28 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160402 | 28.11.2026 | 5500 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-AIRCN | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Transmission | 2026-11-28 | 2026-11-28 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034382 | 28.11.2026 | 11000 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TMCPP | 7500 | 93142 | 18709 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Brake Slack Adjuster Front | 2026-11-29 | 2026-11-29 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072229 | 29.11.2026 | 18000 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACF | 7500 | 90182 | 15607 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Brake Slack Adjuster Rear | 2026-11-29 | 2026-11-29 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072267 | 29.11.2026 | 18000 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACR | 7500 | 90182 | 15607 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Water Cannon | 2026-12-01 | 2026-12-01 | 12 hrs | FY27 | 24 | 90015535 | 1 | 1000133452 | 01.12.2026 | 12 Monthly | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | 5000 | 67273 | 3900 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON90015535
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Tyre Sense Battery | 2026-12-02 | 2026-12-02 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163974 | 02.12.2026 | 24 Monthly | CLB-MP-HAUL-DT199 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT199 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Tyre Sense Battery | 2026-12-02 | 2026-12-02 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163948 | 02.12.2026 | 24 Monthly | CLB-MP-HAUL-DT173 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT173 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Brake Slack Adjuster Front | 2026-12-04 | 2026-12-04 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072246 | 04.12.2026 | 18000 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACF | 7500 | 83931 | 15527 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACF90009306
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Oil Circulation Pump & Motor | 2026-12-04 | 2026-12-04 | 4 hrs | FY27 | 8 | 90018287 | 1 | 1000174670 | 04.12.2026 | 10000 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM2 | 4200 | 71996 | 1615 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM290018287
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Seat Operator | 2026-12-06 | 2026-12-06 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000326669 | 06.12.2026 | 14000 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-SEATS | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Steering Ball Studs | 2026-12-07 | 2026-12-08 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385398 | 07.12.2026 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STLTR | 7500 | 81237 | 12238 | CLB-MP-HAUL-DT163 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Steering LH | 2026-12-07 | 2026-12-07 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034123 | 07.12.2026 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYL | 7500 | 81237 | 12238 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Steering RH | 2026-12-07 | 2026-12-07 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034124 | 07.12.2026 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYR | 7500 | 81237 | 12238 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Pump Brake Control | 2026-12-07 | 2026-12-07 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035111 | 07.12.2026 | 11000 | CLB-MP-HAUL-DT181 -BRKSYS-HYFPP | 7500 | 83441 | 8454 | CLB-MP-HAUL-DT181 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Brake Control | 2026-12-08 | 2026-12-08 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035822 | 08.12.2026 | 11000 | CLB-MP-HAUL-DT194 -BRKSYS-HYFPP | 7500 | 86451 | 8189 | CLB-MP-HAUL-DT194 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Service Air Conditioner | 2026-12-08 | 2026-12-08 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160382 | 08.12.2026 | 5500 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-AIRCN | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Seat Operator | 2026-12-10 | 2026-12-10 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000314065 | 10.12.2026 | 14000 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-SEATS | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Pump Drive Driveshaft Unis | 2026-12-12 | 2026-12-12 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034216 | 12.12.2026 | 11000 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR-DRSHT | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Pump Transmission | 2026-12-12 | 2026-12-12 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034217 | 12.12.2026 | 11000 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TMCPP | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Pump Brake Control | 2026-12-12 | 2026-12-12 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034228 | 12.12.2026 | 11000 | CLB-MP-HAUL-DT165 -BRKSYS-HYFPP | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Brake Relay Valve | 2026-12-12 | 2026-12-12 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078382 | 12.12.2026 | 11000 | CLB-MP-HAUL-DT165 -BRKSYS-BRVRL | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Spiders Transmission Driveshaft | 2026-12-12 | 2026-12-12 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154372 | 12.12.2026 | 11000 | CLB-MP-HAUL-DT165 -FDRSYS-DRSHT-UNVSL | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Tyre Sense Battery | 2026-12-13 | 2026-12-13 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163953 | 13.12.2026 | 24 Monthly | CLB-MP-HAUL-DT178 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT178 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Pump Brake Control | 2026-12-13 | 2026-12-13 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034118 | 13.12.2026 | 11000 | CLB-MP-HAUL-DT163 -BRKSYS-HYFPP | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Brake Relay Valve | 2026-12-13 | 2026-12-13 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078344 | 13.12.2026 | 11000 | CLB-MP-HAUL-DT163 -BRKSYS-BRVRL | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Spiders Transmission Driveshaft | 2026-12-13 | 2026-12-13 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154368 | 13.12.2026 | 11000 | CLB-MP-HAUL-DT163 -FDRSYS-DRSHT-UNVSL | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -FDRSYS-DRSHT-UNVSL90017135
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Seat Operator | 2026-12-13 | 2026-12-13 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000326414 | 13.12.2026 | 14000 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-SEATS | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Final Drive LH | 2026-12-14 | 2026-12-15 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000035814 | 14.12.2026 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-FDRVE-FDRLH | 7500 | 86451 | 19128 | CLB-MP-HAUL-DT194 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Brake Slack Adjuster Front | 2026-12-14 | 2026-12-14 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072226 | 14.12.2026 | 18000 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACF | 7500 | 93142 | 15366 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Engine Midlife complete | 2026-12-15 | 2026-12-19 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156475 | 15.12.2026 | 11000 | CLB-MP-HAUL-DT163 -ENGINE | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Pump Drive Driveshaft Unis | 2026-12-15 | 2026-12-15 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034106 | 15.12.2026 | 11000 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR-DRSHT | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Cyl Hoist LH | 2026-12-15 | 2026-12-16 | 25 hrs | FY27 | 49 | 90003114 | 1 | 1000034457 | 15.12.2026 | 28000 | CLB-MP-HAUL-DT169 -HYDSYS-HOCYL-HCYLL | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -HYDSYS-HOCYL-HCYLL90003114
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Auto Lube Pump | 2026-12-15 | 2026-12-15 | 4 hrs | FY27 | 4 | 90003064 | A1 | 1000033945 | 15.12.2026 | 6000 | CLB-MP-SUPP-SV020 -GRSYST-ALBPP | 3300 | 44025 | 4749 | CLB-MP-SUPP-SV020 -GRSYST-ALBPP90003064
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 5000Hr Valve Set | 2026-12-15 | 2026-12-15 | 12 hrs | FY27 | 24 | 90028725 | A1 | 1000289428 | 15.12.2026 | 5000 | CLB-MP-SUPP-WC013 -ENGINE | 5000 | 63833 | 3387 | CLB-MP-SUPP-WC013 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Service Airconditioner | 2026-12-15 | 2026-12-15 | 12 hrs | FY27 | 12 | 90028728 | A1 | 1000289425 | 15.12.2026 | 5000 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN90028728
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 5000Hr Valve set | 2026-12-16 | 2026-12-16 | 12 hrs | FY27 | 24 | 90028725 | A1 | 1000289434 | 16.12.2026 | 5000 | CLB-MP-SUPP-WC014 -ENGINE | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Service Airconditioner | 2026-12-16 | 2026-12-16 | 12 hrs | FY27 | 12 | 90028728 | A1 | 1000289431 | 16.12.2026 | 5000 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN90028728
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Final Drive LH | 2026-12-17 | 2026-12-18 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000034275 | 17.12.2026 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-FDRVE-FDRLH | 7500 | 95491 | 19244 | CLB-MP-HAUL-DT166 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Final Drive RH | 2026-12-17 | 2026-12-18 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000034276 | 17.12.2026 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-FDRVE-FDRRH | 7500 | 95491 | 19244 | CLB-MP-HAUL-DT166 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Service Suspension Cylinders | 2026-12-17 | 2026-12-17 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106941 | 14.12.2025 | 11000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN | 7500 | 91174 | 15811 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN90012840
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Valve Steering | 2026-12-17 | 2026-12-18 | 24 hrs | FY27 | 48 | 90003053 | A1 | 1000033932 | 17.12.2026 | 18000 | CLB-MP-SUPP-SV020 -STRSYS-STVLV | 3300 | 44025 | 16743 | CLB-MP-SUPP-SV020 -STRSYS-STVLV90003053
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Hub and Spindle LH | 2026-12-17 | 2026-12-18 | 22 hrs | FY27 | 42 | 90003069 | A1 | 1000033950 | 17.12.2026 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-AXLES-HUBLH | 3300 | 44025 | 16743 | CLB-MP-SUPP-SV020 -STRUCT-AXLES-HUBLH90003069
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Hub and Spindle RH | 2026-12-17 | 2026-12-18 | 22 hrs | FY27 | 42 | 90003069 | A2 | 1000033951 | 17.12.2026 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-AXLES-HUBRH | 3300 | 44025 | 16743 | CLB-MP-SUPP-SV020 -STRUCT-AXLES-HUBRH90003069
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Ovhl Axle Housing Dogbone | 2026-12-19 | 2026-12-20 | 22 hrs | FY27 | 42 | 90003118 | 1 | 1000034849 | 19.12.2026 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-TAGLK | 7500 | 85284 | 42256 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Valve Brake | 2026-12-20 | 2026-12-21 | 18 hrs | FY27 | 18 | 90003107 | 1 | 1000035649 | 20.12.2026 | 22000 | CLB-MP-HAUL-DT191 -BRKSYS-BRVLV | 7500 | 87047 | 19116 | CLB-MP-HAUL-DT191 -BRKSYS-BRVLV90003107
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Brake Slack Adjuster Rear | 2026-12-21 | 2026-12-21 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000150610 | 21.12.2026 | 18000 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACR | 7500 | 49737 | 15155 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Water Cannon Inspect | 2026-12-22 | 2026-12-22 | 3 hrs | FY27 | 3 | 90033661 | A1 | 1000338995 | 22.12.2026 | 6 Monthly | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | 5000 | 64118 | 9073 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Tyre Sense Battery | 2026-12-24 | 2026-12-24 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163957 | 24.12.2026 | 24 Monthly | CLB-MP-HAUL-DT182 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT182 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Overhaul Air Conditioner 24M | 2026-12-24 | 2026-12-26 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000339690 | 24.12.2026 | 24 Monthly | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Seat Operator | 2026-12-25 | 2026-12-25 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000300345 | 25.12.2026 | 14000 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-SEATS | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Seat Operator | 2026-12-28 | 2026-12-28 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000326585 | 28.12.2026 | 14000 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-SEATS | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Drive Line Axle LH | 2027-01-02 | 2027-01-02 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000150643 | 02.01.2027 | 30000 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX-AXLLH | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Drive Line Axle RH | 2027-01-02 | 2027-01-02 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000150644 | 02.01.2027 | 30000 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX-AXLRH | 7500 | 49737 | 26914 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Final Drive LH | 2027-01-03 | 2027-01-04 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000035988 | 03.01.2027 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-FDRVE-FDRLH | 7500 | 86259 | 18915 | CLB-MP-HAUL-DT197 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Hyd Pump Steering Main | 2027-01-05 | 2027-01-05 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034618 | 05.01.2027 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STPMP | 7500 | 92351 | 11680 | CLB-MP-HAUL-DT172 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Steering HMU | 2027-01-05 | 2027-01-05 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034619 | 05.01.2027 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STHMU | 7500 | 92351 | 11680 | CLB-MP-HAUL-DT172 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Ovhl Axle A Frame | 2027-01-05 | 2027-01-06 | 36 hrs | FY27 | 60 | 90015390 | 1 | 1000130659 | 05.01.2027 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-AFRME | 7500 | 83931 | 42933 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Service Air Conditioner | 2027-01-06 | 2027-01-06 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160399 | 06.01.2027 | 5500 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-AIRCN | 7500 | 83140 | 6169 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Tyre Sense Battery | 2027-01-06 | 2027-01-06 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163970 | 06.01.2027 | 24 Monthly | CLB-MP-HAUL-DT195 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT195 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Final Drive LH | 2027-01-09 | 2027-01-10 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000034772 | 09.01.2027 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-FDRVE-FDRLH | 7500 | 82722 | 18747 | CLB-MP-HAUL-DT175 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Final Drive RH | 2027-01-09 | 2027-01-10 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000034773 | 09.01.2027 | 22000 | CLB-MP-HAUL-DT175 -FDRSYS-FDRVE-FDRRH | 7500 | 82722 | 18747 | CLB-MP-HAUL-DT175 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Valve Steering & AHS EH | 2027-01-09 | 2027-01-09 | 10 hrs | FY27 | 10 | 90009881 | 1 | 1000079608 | 09.01.2027 | 22000 | CLB-MP-HAUL-DT175 -STRSYS-STVLV | 7500 | 82722 | 18747 | CLB-MP-HAUL-DT175 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Brake Oil Cooler Front | 2027-01-09 | 2027-01-09 | 5 hrs | FY27 | 5 | 90003108 | 1 | 1000080266 | 09.01.2027 | 22000 | CLB-MP-HAUL-DT175 -BRKSYS-BROCO-BROCF | 7500 | 82722 | 18747 | CLB-MP-HAUL-DT175 -BRKSYS-BROCO-BROCF90003108
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Spiders Transmission Driveshaft | 2027-01-10 | 2027-01-10 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154432 | 10.01.2027 | 11000 | CLB-MP-HAUL-DT195 -FDRSYS-DRSHT-UNVSL | 7500 | 82554 | 20001 | CLB-MP-HAUL-DT195 -FDRSYS-DRSHT-UNVSL90017135
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Fan Assy Brake Oil Cooler | 2027-01-10 | 2027-01-10 | 4 hrs | FY27 | 4 | 90013226 | A1 | 1000110289 | 10.01.2027 | 11000 | CLB-MP-SUPP-LL0002-BRKSYS-BROCO-COFAN | 3500 | 91736 | 25890 | CLB-MP-SUPP-LL0002-BRKSYS-BROCO-COFAN90013226
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Hoist & Rear Brake Pump | 2027-01-10 | 2027-01-10 | 5 hrs | FY27 | 5 | 90004008 | 1 | 1000044609 | 10.01.2027 | 20000 | CLB-MP-SUPP-WC012 -HYDSYS-HOPMP | 5000 | 67273 | 17626 | CLB-MP-SUPP-WC012 -HYDSYS-HOPMP90004008
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Spiders Transmission Driveshaft | 2027-01-11 | 2027-01-11 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154380 | 11.01.2027 | 11000 | CLB-MP-HAUL-DT169 -FDRSYS-DRSHT-UNVSL | 7500 | 93410 | 19043 | CLB-MP-HAUL-DT169 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Slack Adjuster Front | 2027-01-12 | 2027-01-12 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072240 | 12.01.2027 | 18000 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACF | 7500 | 92002 | 14717 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Slack Adjuster Rear | 2027-01-12 | 2027-01-12 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072278 | 12.01.2027 | 18000 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACR | 7500 | 92002 | 14717 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Water Cannon & Valves Repl | 2027-01-12 | 2027-01-13 | 24 hrs | FY27 | 48 | 90033662 | A1 | 1000338795 | 12.01.2027 | 24 Monthly | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | 5000 | 65823 | 12836 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON90033662
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Brake Slack Adjuster Front | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072224 | 13.01.2027 | 18000 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACF | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Brake Slack Adjuster Rear | 2027-01-13 | 2027-01-13 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072262 | 13.01.2027 | 18000 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACR | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Midlife Valve Set - Adjust | 2027-01-14 | 2027-01-14 | 6 hrs | FY27 | 12 | 90017314 | 1 | 1000390899 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -ENGINE | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Engine Midlife complete | 2027-01-14 | 2027-01-18 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156667 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -ENGINE | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Pump Drive Driveshaft Unis | 2027-01-14 | 2027-01-14 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034768 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR-DRSHT | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Pump Transmission | 2027-01-14 | 2027-01-14 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034769 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TMCPP | 7500 | 82721 | 7663 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Pump Brake Control | 2027-01-14 | 2027-01-14 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034780 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -BRKSYS-HYFPP | 7500 | 82722 | 20002 | CLB-MP-HAUL-DT175 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Service Suspension Cylinders | 2027-01-14 | 2027-01-14 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106884 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN | 7500 | 82722 | 11190 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Brake Relay Valve | 2027-01-14 | 2027-01-14 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000079604 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -BRKSYS-BRVRL | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Spiders Transmission Driveshaft | 2027-01-14 | 2027-01-14 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154392 | 14.01.2027 | 11000 | CLB-MP-HAUL-DT175 -FDRSYS-DRSHT-UNVSL | 7500 | 82722 | 20002 | CLB-MP-HAUL-DT175 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Steering Ball Studs | 2027-01-14 | 2027-01-15 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385414 | 14.01.2027 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STLTR | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Hyd Pump Steering Main | 2027-01-14 | 2027-01-14 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034563 | 14.01.2027 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STPMP | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Steering HMU | 2027-01-14 | 2027-01-14 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034564 | 14.01.2027 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STHMU | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Cyl Steering LH | 2027-01-14 | 2027-01-14 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034565 | 14.01.2027 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYL | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Cyl Steering RH | 2027-01-14 | 2027-01-14 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034566 | 14.01.2027 | 15000 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYR | 7500 | 90182 | 11678 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Tyre Sense Battery | 2027-01-14 | 2027-01-14 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163946 | 14.01.2027 | 24 Monthly | CLB-MP-HAUL-DT171 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT171 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Transmission Pump | 2027-01-15 | 2027-01-15 | 6 hrs | FY27 | 6 | 90003991 | 1 | 1000221742 | 15.01.2027 | 10000 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP90003991
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Brake Slack Adjuster Front | 2027-01-15 | 2027-01-15 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072247 | 15.01.2027 | 18000 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Brake Slack Adjuster Rear | 2027-01-15 | 2027-01-15 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072285 | 15.01.2027 | 18000 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Brake Slack Adjuster Rear | 2027-01-16 | 2027-01-16 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072264 | 16.01.2027 | 18000 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACR | 7500 | 93142 | 14674 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Tyre Sense Battery | 2027-01-20 | 2027-01-20 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163942 | 20.01.2027 | 24 Monthly | CLB-MP-HAUL-DT167 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT167 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 3Y Air Tank LH Int Insp & PRV Repl | 2027-01-21 | 2027-01-21 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389423 | 21.01.2027 | 36 Monthly | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH | 7500 | 90973 | 42723 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 3Y Air Tank RH Int Insp & PRV Repl | 2027-01-21 | 2027-01-21 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389425 | 21.01.2027 | 36 Monthly | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH | 7500 | 90973 | 42723 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Cyl Steering RH | 2027-01-21 | 2027-01-21 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000035062 | 21.01.2027 | 15000 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYR | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Cyl Suspension RHR | 2027-01-22 | 2027-01-23 | 23 hrs | FY27 | 42 | 90003122 | 1 | 1000035538 | 22.01.2027 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYRR | 7500 | 84546 | 18522 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Brake Control | 2027-01-23 | 2027-01-23 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034393 | 23.01.2027 | 11000 | CLB-MP-HAUL-DT168 -BRKSYS-HYFPP | 7500 | 93142 | 7536 | CLB-MP-HAUL-DT168 -BRKSYS-HYFPP90003106
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Overhaul Air Conditioner 24M | 2027-01-25 | 2027-01-27 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000346231 | 25.01.2027 | 24 Monthly | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN90029460
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Cylinder Steering RH | 2027-01-26 | 2027-01-26 | 14 hrs | FY27 | 26 | 90003054 | A1 | 1000033874 | 26.01.2027 | 9000 | CLB-MP-SUPP-SV019 -STRSYS-STRCY-STCYR | 2500 | 48856 | 7577 | CLB-MP-SUPP-SV019 -STRSYS-STRCY-STCYR90003054
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Service Suspension Cylinders | 2027-01-28 | 2027-01-28 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106894 | 28.01.2027 | 11000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN | 7500 | 92088 | 41661 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 3Y Air Tank LH Int Insp & PRV Repl | 2027-01-28 | 2027-01-28 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389311 | 28.01.2027 | 36 Monthly | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH | 7500 | 80996 | 48008 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 3Y Air Tank RH Int Insp & PRV Repl | 2027-01-28 | 2027-01-28 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389313 | 28.01.2027 | 36 Monthly | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH | 7500 | 80996 | 48008 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Tyre Sense Battery | 2027-01-28 | 2027-01-28 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163988 | 28.01.2027 | 24 Monthly | CLB-MP-HAUL-DT224 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT224 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Hyd Pump Steering Main | 2027-01-28 | 2027-01-28 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000035003 | 28.01.2027 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STPMP | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Steering HMU | 2027-01-28 | 2027-01-28 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000035004 | 28.01.2027 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STHMU | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Steering Ball Studs | 2027-01-28 | 2027-01-29 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385430 | 28.01.2027 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STLTR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Steering Link & Arm Rebush | 2027-01-28 | 2027-01-29 | 27 hrs | FY27 | 45 | 90038355 | A1 | 1000385409 | 28.01.2027 | 30000 | CLB-MP-HAUL-DT168 -STRSYS-STLTR | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Tyre Sense Battery | 2027-01-29 | 2027-01-29 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163945 | 29.01.2027 | 24 Monthly | CLB-MP-HAUL-DT170 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT170 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 6000Hr Valve Set | 2027-01-29 | 2027-01-29 | 12 hrs | FY27 | 24 | 90028986 | A1 | 1000289410 | 29.01.2027 | 6000 | CLB-MP-SUPP-PM0006-ENGINE | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-ENGINE90028986
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Service Airconditioner | 2027-01-29 | 2027-01-29 | 12 hrs | FY27 | 12 | 90028999 | A1 | 1000289407 | 29.01.2027 | 6000 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-AIRCN | 4200 | 53807 | 3537 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-AIRCN90028999
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Tyre Sense Battery | 2027-01-30 | 2027-01-30 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163969 | 30.01.2027 | 24 Monthly | CLB-MP-HAUL-DT194 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT194 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Drive Line Axle LH | 2027-01-31 | 2027-01-31 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123513 | 31.01.2027 | 30000 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX-AXLLH | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Drive Line Axle RH | 2027-01-31 | 2027-01-31 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123574 | 31.01.2027 | 30000 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX-AXLRH | 7500 | 93142 | 26428 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX-AXLRH90014552
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Control Cabinet Coolant | 2027-01-31 | 2027-01-31 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332196 | 31.01.2027 | 15000 | CLB-MP-HAUL-DT5419-ELCTHV-HVCAB-COOLR | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-ELCTHV-HVCAB-COOLR90033128
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Valve Brake | 2027-02-01 | 2027-02-01 | 6 hrs | FY27 | 6 | 90003049 | A1 | 1000033928 | 01.02.2027 | 18000 | CLB-MP-SUPP-SV020 -BRKSYS-BRVLV | 3300 | 44025 | 16326 | CLB-MP-SUPP-SV020 -BRKSYS-BRVLV90003049
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 250Hr Initial Valve Set | 2027-02-02 | 2027-02-02 | 12 hrs | FY27 | 24 | 90028724 | A1 | 1000289475 | 02.02.2027 | 250 | CLB-MP-SUPP-WC3108-ENGINE | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-ENGINE90028724
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Service Air Conditioner | 2027-02-02 | 2027-02-02 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160405 | 02.02.2027 | 5500 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-AIRCN | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Air Drier and Tank | 2027-02-02 | 2027-02-02 | 12 hrs | FY27 | 24 | 90004010 | 1 | 1000082743 | 02.02.2027 | 9000 | CLB-MP-SUPP-PM0006-PNEUMC-AIRDR | 4200 | 53807 | 24746 | CLB-MP-SUPP-PM0006-PNEUMC-AIRDR90004010
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Control Cabinet Coolant | 2027-02-04 | 2027-02-04 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332190 | 04.02.2027 | 15000 | CLB-MP-HAUL-DT5405-ELCTHV-HVCAB-COOLR | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Service Air Conditioner | 2027-02-06 | 2027-02-06 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160379 | 06.02.2027 | 5500 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-AIRCN | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 3Y Air Tank LH Int Insp & PRV Repl | 2027-02-07 | 2027-02-07 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389327 | 07.02.2027 | 36 Monthly | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH | 7500 | 83047 | 18464 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 3Y Air Tank RH Int Insp & PRV Repl | 2027-02-07 | 2027-02-07 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389329 | 07.02.2027 | 36 Monthly | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH | 7500 | 83047 | 18464 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH90038754
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Control Cabinet Coolant | 2027-02-07 | 2027-02-07 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332194 | 07.02.2027 | 15000 | CLB-MP-HAUL-DT5417-ELCTHV-HVCAB-COOLR | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Cyl Steering LH | 2027-02-08 | 2027-02-08 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034288 | 08.02.2027 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYL | 7500 | 95491 | 11151 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Brake Slack Adjuster Front | 2027-02-08 | 2027-02-08 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072254 | 08.02.2027 | 18000 | CLB-MP-HAUL-DT196 -BRKSYS-SLACK-SLACF | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Brake Slack Adjuster Rear | 2027-02-08 | 2027-02-08 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072292 | 08.02.2027 | 18000 | CLB-MP-HAUL-DT196 -BRKSYS-SLACK-SLACR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Tyre Sense Battery | 2027-02-08 | 2027-02-08 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163954 | 08.02.2027 | 24 Monthly | CLB-MP-HAUL-DT179 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT179 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Tyre Sense Battery | 2027-02-08 | 2027-02-08 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163939 | 08.02.2027 | 24 Monthly | CLB-MP-HAUL-DT164 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT164 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 3Y Air Tank LH Int Insp & PRV Repl | 2027-02-09 | 2027-02-09 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389391 | 09.02.2027 | 36 Monthly | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH | 7500 | 83208 | 83208 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 3Y Air Tank RH Int Insp & PRV Repl | 2027-02-09 | 2027-02-09 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389393 | 09.02.2027 | 36 Monthly | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH | 7500 | 83208 | 83208 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Steering Link & Arm Rebush | 2027-02-09 | 2027-02-10 | 27 hrs | FY27 | 45 | 90038355 | A1 | 1000385445 | 09.02.2027 | 30000 | CLB-MP-HAUL-DT186 -STRSYS-STLTR | 7500 | 89749 | 26124 | CLB-MP-HAUL-DT186 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Transmission | 2027-02-10 | 2027-02-10 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035811 | 10.02.2027 | 11000 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TMCPP | 7500 | 86451 | 6933 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Steering Ball Studs | 2027-02-10 | 2027-02-11 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385474 | 10.02.2027 | 15000 | CLB-MP-HAUL-DT224 -STRSYS-STLTR | 7500 | 49737 | 11104 | CLB-MP-HAUL-DT224 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Tyre Sense Battery | 2027-02-10 | 2027-02-10 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163950 | 10.02.2027 | 24 Monthly | CLB-MP-HAUL-DT175 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT175 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Tyre Sense Battery | 2027-02-10 | 2027-02-10 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163961 | 10.02.2027 | 24 Monthly | CLB-MP-HAUL-DT186 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT186 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Transmission Oil Cooler | 2027-02-11 | 2027-02-11 | 13 hrs | FY27 | 13 | 90003532 | 1 | 1000040982 | 11.02.2027 | 22000 | CLB-MP-HAUL-DT173 -TRNSYS-TROLC | 7500 | 82651 | 17964 | CLB-MP-HAUL-DT173 -TRNSYS-TROLC90003532
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Service Air Conditioner 12M | 2027-02-12 | 2027-02-12 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000300050 | 12.02.2027 | 12 Monthly | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Overhaul Air Conditioner 24M | 2027-02-14 | 2027-02-16 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000346990 | 14.02.2027 | 24 Monthly | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Service Air Conditioner | 2027-02-14 | 2027-02-14 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160386 | 14.02.2027 | 5500 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-AIRCN | 7500 | 89560 | 17107 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 3Y Air Tank LH Int Insp & PRV Repl | 2027-02-14 | 2027-02-14 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389335 | 14.02.2027 | 36 Monthly | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH | 7500 | 93147 | 93147 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 3Y Air Tank RH Int Insp & PRV Repl | 2027-02-14 | 2027-02-14 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389337 | 14.02.2027 | 36 Monthly | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH | 7500 | 93147 | 93147 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Final Drive LH | 2027-02-15 | 2027-02-16 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000034992 | 15.02.2027 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-FDRVE-FDRLH | 7500 | 84079 | 18003 | CLB-MP-HAUL-DT179 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Pump Transmission | 2027-02-15 | 2027-02-15 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000116266 | 15.02.2027 | 11000 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TMCPP | 7500 | 81875 | 6988 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Service Air Conditioner | 2027-02-15 | 2027-02-15 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160406 | 15.02.2027 | 5500 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-AIRCN | 7500 | 92548 | 12117 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Brake Slack Adjuster Front | 2027-02-16 | 2027-02-16 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072234 | 16.02.2027 | 18000 | CLB-MP-HAUL-DT176 -BRKSYS-SLACK-SLACF | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Brake Slack Adjuster Rear | 2027-02-16 | 2027-02-16 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072272 | 16.02.2027 | 18000 | CLB-MP-HAUL-DT176 -BRKSYS-SLACK-SLACR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Steering Ball Studs | 2027-02-16 | 2027-02-17 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385448 | 16.02.2027 | 15000 | CLB-MP-HAUL-DT188 -STRSYS-STLTR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Midlife Valve Set - Adjust | 2027-02-17 | 2027-02-17 | 6 hrs | FY27 | 12 | 90017314 | 1 | 1000390959 | 17.02.2027 | 11000 | CLB-MP-HAUL-DT195 -ENGINE | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Engine Midlife complete | 2027-02-17 | 2027-02-21 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156987 | 17.02.2027 | 11000 | CLB-MP-HAUL-DT195 -ENGINE | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Pump Transmission | 2027-02-17 | 2027-02-17 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035869 | 17.02.2027 | 11000 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TMCPP | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Pump Brake Control | 2027-02-17 | 2027-02-17 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035880 | 17.02.2027 | 11000 | CLB-MP-HAUL-DT195 -BRKSYS-HYFPP | 7500 | 82554 | 6982 | CLB-MP-HAUL-DT195 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Service Suspension Cylinders | 2027-02-17 | 2027-02-17 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106944 | 17.02.2027 | 11000 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN | 7500 | 82554 | 11212 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Brake Relay Valve | 2027-02-17 | 2027-02-17 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078838 | 17.02.2027 | 11000 | CLB-MP-HAUL-DT195 -BRKSYS-BRVRL | 7500 | 82554 | 18183 | CLB-MP-HAUL-DT195 -BRKSYS-BRVRL90009877
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Control Cabinet Coolant | 2027-02-19 | 2027-02-19 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332188 | 19.02.2027 | 15000 | CLB-MP-HAUL-DT5391-ELCTHV-HVCAB-COOLR | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Tyre Sense Battery | 2027-02-19 | 2027-02-19 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163967 | 19.02.2027 | 24 Monthly | CLB-MP-HAUL-DT192 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT192 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Pump Transmission | 2027-02-20 | 2027-02-20 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034659 | 20.02.2027 | 11000 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TMCPP | 7500 | 82651 | 6802 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TMCPP90003096
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Control Cabinet Coolant | 2027-02-22 | 2027-02-22 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332195 | 22.02.2027 | 15000 | CLB-MP-HAUL-DT5418-ELCTHV-HVCAB-COOLR | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Tyre Sense Battery | 2027-02-24 | 2027-02-24 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163952 | 24.02.2027 | 24 Monthly | CLB-MP-HAUL-DT177 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT177 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Tyre Sense Battery | 2027-02-25 | 2027-02-25 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163959 | 25.02.2027 | 24 Monthly | CLB-MP-HAUL-DT184 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT184 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Tyre Sense Battery | 2027-02-26 | 2027-02-26 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163968 | 26.02.2027 | 24 Monthly | CLB-MP-HAUL-DT193 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT193 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 3Y Air Tank LH Int Insp & PRV Repl | 2027-02-26 | 2027-02-26 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389355 | 26.02.2027 | 36 Monthly | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH | 7500 | 83507 | 83507 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 3Y Air Tank RH Int Insp & PRV Repl | 2027-02-26 | 2027-02-26 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389357 | 26.02.2027 | 36 Monthly | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH | 7500 | 83507 | 83507 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH90038754
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Control Cabinet Coolant | 2027-02-27 | 2027-02-27 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332193 | 27.02.2027 | 15000 | CLB-MP-HAUL-DT5416-ELCTHV-HVCAB-COOLR | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Control Cabinet Coolant | 2027-02-28 | 2027-02-28 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332191 | 28.02.2027 | 15000 | CLB-MP-HAUL-DT5410-ELCTHV-HVCAB-COOLR | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-ELCTHV-HVCAB-COOLR90033128
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 5000Hr Valve Set | 2027-02-28 | 2027-02-28 | 12 hrs | FY27 | 24 | 90028725 | A1 | 1000289416 | 28.02.2027 | 5000 | CLB-MP-SUPP-WC011 -ENGINE | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl PTO Uni's | 2027-02-28 | 2027-02-28 | 4 hrs | FY27 | 4 | 90031093 | A1 | 1000307800 | 28.02.2027 | 5000 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT90031093
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Service Airconditioner | 2027-02-28 | 2027-02-28 | 12 hrs | FY27 | 12 | 90028728 | A1 | 1000289413 | 28.02.2027 | 5000 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN90028728
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl PTO Uni's | 2027-02-28 | 2027-02-28 | 4 hrs | FY27 | 4 | 90031093 | A1 | 1000307803 | 28.02.2027 | 5000 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT90031093
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Tyre Sense Battery | 2027-03-01 | 2027-03-01 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163963 | 01.03.2027 | 24 Monthly | CLB-MP-HAUL-DT188 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT188 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Inspect Water Cannon | 2027-03-02 | 2027-03-02 | 3 hrs | FY27 | 3 | 90033661 | A1 | 1000339268 | 02.03.2027 | 6 Monthly | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | 5000 | 17738 | 8813 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Pump Transmission | 2027-03-03 | 2027-03-03 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035451 | 03.03.2027 | 11000 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TMCPP | 7500 | 83931 | 6681 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Brake Control | 2027-03-03 | 2027-03-03 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035166 | 03.03.2027 | 11000 | CLB-MP-HAUL-DT182 -BRKSYS-HYFPP | 7500 | 92002 | 6691 | CLB-MP-HAUL-DT182 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Tyre Sense Battery | 2027-03-03 | 2027-03-03 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163964 | 03.03.2027 | 24 Monthly | CLB-MP-HAUL-DT189 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT189 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Brake Rotochamber Front | 2027-03-03 | 2027-03-03 | 2 hrs | FY27 | 2 | 90004017 | 1 | 1000082750 | 03.03.2027 | 20000 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTFR | 4200 | 53807 | 17402 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTFR90004017
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Drive Line Axle LH | 2027-03-04 | 2027-03-04 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123521 | 04.03.2027 | 30000 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX-AXLLH | 7500 | 85284 | 25686 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Drive Line Axle RH | 2027-03-04 | 2027-03-04 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123582 | 04.03.2027 | 30000 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX-AXLRH | 7500 | 85284 | 25686 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 3Y Air Tank LH Int Insp & PRV Repl | 2027-03-04 | 2027-03-04 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389399 | 04.03.2027 | 36 Monthly | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH | 7500 | 89493 | 42523 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 3Y Air Tank RH Int Insp & PRV Repl | 2027-03-04 | 2027-03-04 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389401 | 04.03.2027 | 36 Monthly | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH | 7500 | 89493 | 42523 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH90038754
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Service Air Conditioner 12M | 2027-03-05 | 2027-03-05 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000314066 | 05.03.2027 | 12 Monthly | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Brake Slack Adjuster Front | 2027-03-08 | 2027-03-08 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072227 | 08.03.2027 | 18000 | CLB-MP-HAUL-DT169 -BRKSYS-SLACK-SLACF | 7500 | 93410 | 13586 | CLB-MP-HAUL-DT169 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Brake Slack Adjuster Rear | 2027-03-08 | 2027-03-08 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072265 | 08.03.2027 | 18000 | CLB-MP-HAUL-DT169 -BRKSYS-SLACK-SLACR | 7500 | 93410 | 13586 | CLB-MP-HAUL-DT169 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Service Air Conditioner 12M | 2027-03-09 | 2027-03-09 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000300346 | 09.03.2027 | 12 Monthly | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN | 6500 | 11246 | 4814 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Pump Torque Converter Charge | 2027-03-09 | 2027-03-09 | 5 hrs | FY27 | 5 | 90003095 | 1 | 1000080175 | 09.03.2027 | 22000 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TCCPP | 7500 | 82651 | 17389 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Torque Converter | 2027-03-10 | 2027-03-11 | 32 hrs | FY27 | 62 | 90003092 | 1 | 1000034656 | 10.03.2027 | 22000 | CLB-MP-HAUL-DT173 -TRNSYS-TRQUE | 7500 | 82651 | 17389 | CLB-MP-HAUL-DT173 -TRNSYS-TRQUE90003092
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Drive Line Axle LH | 2027-03-11 | 2027-03-11 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123511 | 11.03.2027 | 30000 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX-AXLLH | 7500 | 95491 | 25609 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Drive Line Axle RH | 2027-03-11 | 2027-03-11 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123572 | 11.03.2027 | 30000 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX-AXLRH | 7500 | 95491 | 25609 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Differential | 2027-03-12 | 2027-03-14 | 44 hrs | FY27 | 66 | 90003098 | 1 | 1000034661 | 12.03.2027 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-DIFFL | 7500 | 82651 | 17389 | CLB-MP-HAUL-DT173 -FDRSYS-DIFFL90003098
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Alternator 24V | 2027-03-13 | 2027-03-13 | 2 hrs | FY27 | 2 | 90013161 | A1 | 1000110233 | 13.03.2027 | 11000 | CLB-MP-SUPP-PM0004-ELCTLV-CHARG-ALTER | 3500 | 91736 | 8891 | CLB-MP-SUPP-PM0004-ELCTLV-CHARG-ALTER90013161
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Spiders Transmission Driveshaft | 2027-03-14 | 2027-03-14 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154438 | 14.03.2027 | 11000 | CLB-MP-HAUL-DT198 -FDRSYS-DRSHT-UNVSL | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -FDRSYS-DRSHT-UNVSL90017135
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Cooling System Hoses | 2027-03-14 | 2027-03-14 | 12 hrs | FY27 | 12 | 90013152 | A1 | 1000110230 | 14.03.2027 | 11000 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-CSHLF | 3500 | 91736 | 15967 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-CSHLF90013152
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Hyd Pump Steering Main | 2027-03-15 | 2027-03-15 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034728 | 15.03.2027 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STPMP | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Steering HMU | 2027-03-15 | 2027-03-15 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034729 | 15.03.2027 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STHMU | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Steering Ball Studs | 2027-03-15 | 2027-03-16 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385420 | 15.03.2027 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STLTR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STLTR90038356
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Overhaul Air Conditioner 24M | 2027-03-16 | 2027-03-18 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000347362 | 16.03.2027 | 24 Monthly | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Brake Wheel LH | 2027-03-16 | 2027-03-17 | 32 hrs | FY27 | 38 | 90003104 | 2 | 1000035819 | 16.03.2027 | 22000 | CLB-MP-HAUL-DT194 -STRUCT-AXLES-HUBLH | 7500 | 88113 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-AXLES-HUBLH90003104
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Overhaul Air Conditioner 24M | 2027-03-17 | 2027-03-19 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000349686 | 17.03.2027 | 24 Monthly | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Overhaul Air Conditioner 24M | 2027-03-17 | 2027-03-19 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000349642 | 17.03.2027 | 24 Monthly | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN90029460
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Water Cannon Inspect | 2027-03-17 | 2027-03-17 | 3 hrs | FY27 | 3 | 90033661 | A1 | 1000338792 | 17.03.2027 | 6 Monthly | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Engine Cat 3516B | 2027-03-19 | 2027-03-23 | 96 hrs | FY27 | 142 | 90017315 | 1 | 1000156701 | 19.03.2027 | 22000 | CLB-MP-HAUL-DT178 -ENGINE | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -ENGINE90017315
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 3Y Air Tank LH Int Insp & PRV Repl | 2027-03-19 | 2027-03-19 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389403 | 19.03.2027 | 36 Monthly | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH | 7500 | 92907 | 46760 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 3Y Air Tank RH Int Insp & PRV Repl | 2027-03-19 | 2027-03-19 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389405 | 19.03.2027 | 36 Monthly | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH | 7500 | 92907 | 46760 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Brake Slack Adjuster Front | 2027-03-20 | 2027-03-20 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072251 | 20.03.2027 | 18000 | CLB-MP-HAUL-DT193 -BRKSYS-SLACK-SLACF | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Brake Slack Adjuster Rear | 2027-03-20 | 2027-03-20 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072289 | 20.03.2027 | 18000 | CLB-MP-HAUL-DT193 -BRKSYS-SLACK-SLACR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Spiders Transmission Driveshaft | 2027-03-22 | 2027-03-22 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154398 | 22.03.2027 | 11000 | CLB-MP-HAUL-DT178 -FDRSYS-DRSHT-UNVSL | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 3Y Air Tank LH Int Insp & PRV Repl | 2027-03-22 | 2027-03-22 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389467 | 22.03.2027 | 36 Monthly | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH | 7500 | 91739 | 50479 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 3Y Air Tank RH Int Insp & PRV Repl | 2027-03-22 | 2027-03-22 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389469 | 22.03.2027 | 36 Monthly | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH | 7500 | 91739 | 50479 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH90038754
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Pump Steering | 2027-03-22 | 2027-03-22 | 6 hrs | FY27 | 6 | 90003051 | A1 | 1000033930 | 22.03.2027 | 18000 | CLB-MP-SUPP-SV020 -STRSYS-STPMP | 3300 | 44025 | 15884 | CLB-MP-SUPP-SV020 -STRSYS-STPMP90003051
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Transmission | 2027-03-23 | 2027-03-23 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034989 | 23.03.2027 | 11000 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TMCPP | 7500 | 84079 | 6265 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Pump Drive Driveshaft Unis | 2027-03-24 | 2027-03-24 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000150664 | 24.03.2027 | 11000 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR-DRSHT | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Pump Transmission | 2027-03-24 | 2027-03-24 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000150665 | 24.03.2027 | 11000 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TMCPP | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Pump Brake Control | 2027-03-24 | 2027-03-24 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000150674 | 24.03.2027 | 11000 | CLB-MP-HAUL-DT225 -BRKSYS-HYFPP | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Pump Transmission | 2027-03-24 | 2027-03-24 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035753 | 24.03.2027 | 11000 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TMCPP | 7500 | 83140 | 6169 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Relay Valve | 2027-03-25 | 2027-03-25 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000150711 | 25.03.2027 | 11000 | CLB-MP-HAUL-DT225 -BRKSYS-BRVRL | 7500 | 51346 | 6220 | CLB-MP-HAUL-DT225 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Service Suspension Cylinders | 2027-03-25 | 2027-03-25 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000150728 | 25.03.2027 | 11000 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN | 7500 | 51346 | 10798 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Final Drive RH | 2027-03-25 | 2027-03-26 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000034718 | 25.03.2027 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-FDRVE-FDRRH | 7500 | 83749 | 17203 | CLB-MP-HAUL-DT174 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Radiator Engine Cooling | 2027-03-26 | 2027-03-28 | 55 hrs | FY27 | 85 | 90003081 | 1 | 1000034266 | 26.03.2027 | 22000 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-RADTR | 7400 | 95491 | 71350 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-RADTR90003081
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 3Y Air Tank LH Int Insp & PRV Repl | 2027-03-26 | 2027-03-26 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389315 | 26.03.2027 | 36 Monthly | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH | 7500 | 81612 | 11133 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 3Y Air Tank RH Int Insp & PRV Repl | 2027-03-26 | 2027-03-26 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389317 | 26.03.2027 | 36 Monthly | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH | 7500 | 81612 | 11133 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Drive Line Axle LH | 2027-03-26 | 2027-03-26 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123514 | 26.03.2027 | 30000 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX-AXLLH | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Drive Line Axle RH | 2027-03-26 | 2027-03-26 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123575 | 26.03.2027 | 30000 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX-AXLRH | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 3Y Air Tank LH Int Insp & PRV Repl | 2027-03-27 | 2027-03-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389411 | 27.03.2027 | 36 Monthly | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH | 7500 | 84322 | 84322 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 3Y Air Tank RH Int Insp & PRV Repl | 2027-03-27 | 2027-03-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389413 | 27.03.2027 | 36 Monthly | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH | 7500 | 84322 | 84322 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Service Air Conditioner | 2027-03-28 | 2027-03-28 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160372 | 28.03.2027 | 5500 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-AIRCN | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Cyl Hoist RH | 2027-03-30 | 2027-03-31 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000035286 | 30.03.2027 | 28000 | CLB-MP-HAUL-DT185 -HYDSYS-HOCYL-HCYLR | 7500 | 92088 | 23112 | CLB-MP-HAUL-DT185 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Hub & Spindle LH | 2027-03-30 | 2027-03-31 | 26 hrs | FY27 | 50 | 90004020 | 1 | 1000044657 | 30.03.2027 | 24000 | CLB-MP-SUPP-WC013 -STRUCT-AXLES-HUBLH | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRUCT-AXLES-HUBLH90004020
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Hub & Spindle RH | 2027-03-30 | 2027-03-31 | 26 hrs | FY27 | 50 | 90026194 | A1 | 1000044658 | 30.03.2027 | 24000 | CLB-MP-SUPP-WC013 -STRUCT-AXLES-HUBRH | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRUCT-AXLES-HUBRH90026194
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Service Suspension Cylinders | 2027-03-31 | 2027-03-31 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106877 | 31.03.2027 | 11000 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN | 7500 | 93142 | 26399 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Final Drive RH | 2027-04-01 | 2027-04-02 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000035641 | 01.04.2027 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-FDRVE-FDRRH | 7500 | 87047 | 17070 | CLB-MP-HAUL-DT191 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Cyl Steering RH | 2027-04-01 | 2027-04-01 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034454 | 01.04.2027 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYR | 7500 | 93410 | 10097 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Service Air Conditioner | 2027-04-02 | 2027-04-02 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160378 | 02.04.2027 | 5500 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-AIRCN | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Radiator Engine Cooling | 2027-04-02 | 2027-04-04 | 55 hrs | FY27 | 85 | 90003081 | 1 | 1000034928 | 02.04.2027 | 22000 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-RADTR | 7400 | 81600 | 39328 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-RADTR90003081
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Torque Converter | 2027-04-02 | 2027-04-03 | 32 hrs | FY27 | 62 | 90003092 | 1 | 1000034931 | 02.04.2027 | 22000 | CLB-MP-HAUL-DT178 -TRNSYS-TRQUE | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -TRNSYS-TRQUE90003092
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Hyd Motor Axle Lube Rear | 2027-04-02 | 2027-04-02 | 9 hrs | FY27 | 9 | 90003101 | 1 | 1000034939 | 02.04.2027 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-HYM01 | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Rotochamber LHR | 2027-04-02 | 2027-04-02 | 5 hrs | FY27 | 5 | 90009309 | 1 | 1000072426 | 02.04.2027 | 22000 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTLR | 7500 | 81600 | 17037 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTLR90009309
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Engine Midlife complete | 2027-04-02 | 2027-04-06 | 104.5 hrs | FY27 | 116.5 | 90017316 | 2 | 1000157099 | 02.04.2027 | 11000 | CLB-MP-HAUL-DT225 -ENGINE | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Midlife Valve Set - Adjust | 2027-04-02 | 2027-04-02 | 6 hrs | FY27 | 12 | 90017314 | 1 | 1000390986 | 02.04.2027 | 11000 | CLB-MP-HAUL-DT225 -ENGINE | 7500 | 51346 | 6222 | CLB-MP-HAUL-DT225 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Spiders Transmission Driveshaft | 2027-04-02 | 2027-04-02 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154446 | 02.04.2027 | 11000 | CLB-MP-HAUL-DT225 -FDRSYS-DRSHT-UNVSL | 7500 | 51346 | 16991 | CLB-MP-HAUL-DT225 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Drive Line Axle LH | 2027-04-02 | 2027-04-02 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123534 | 02.04.2027 | 30000 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX-AXLLH | 7500 | 84546 | 25091 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Drive Line Axle RH | 2027-04-02 | 2027-04-02 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123595 | 02.04.2027 | 30000 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX-AXLRH | 7500 | 84546 | 25091 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Tyre Sense Battery | 2027-04-02 | 2027-04-02 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163956 | 02.04.2027 | 24 Monthly | CLB-MP-HAUL-DT181 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT181 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Tyre Sense Battery | 2027-04-02 | 2027-04-02 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163949 | 02.04.2027 | 24 Monthly | CLB-MP-HAUL-DT174 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT174 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Overhaul Air Conditioner 24M | 2027-04-02 | 2027-04-04 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000346560 | 02.04.2027 | 24 Monthly | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Cyl Suspension LHF | 2027-04-04 | 2027-04-05 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067846 | 04.04.2027 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYLF | 7500 | 92088 | 17006 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYLF90003121
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Service Air Conditioner 12M | 2027-04-05 | 2027-04-05 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000314216 | 05.04.2027 | 12 Monthly | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Tyre Sense Battery | 2027-04-05 | 2027-04-05 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163938 | 05.04.2027 | 24 Monthly | CLB-MP-HAUL-DT163 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT163 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Tyre Sense Battery | 2027-04-07 | 2027-04-07 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163971 | 07.04.2027 | 24 Monthly | CLB-MP-HAUL-DT196 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT196 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Pump Transmission | 2027-04-08 | 2027-04-08 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035507 | 08.04.2027 | 11000 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TMCPP | 7500 | 84546 | 5964 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Final Drive LH | 2027-04-09 | 2027-04-10 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000035698 | 09.04.2027 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-FDRVE-FDRLH | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Tyre Sense Battery | 2027-04-09 | 2027-04-09 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163958 | 09.04.2027 | 24 Monthly | CLB-MP-HAUL-DT183 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT183 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Service Air Conditioner | 2027-04-09 | 2027-04-09 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160371 | 09.04.2027 | 5500 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-AIRCN | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Tyre Sense Battery | 2027-04-12 | 2027-04-12 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163944 | 12.04.2027 | 24 Monthly | CLB-MP-HAUL-DT169 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT169 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Brake Slack Adjuster Front | 2027-04-16 | 2027-04-16 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072257 | 16.04.2027 | 18000 | CLB-MP-HAUL-DT199 -BRKSYS-SLACK-SLACF | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Brake Slack Adjuster Rear | 2027-04-16 | 2027-04-16 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072295 | 16.04.2027 | 18000 | CLB-MP-HAUL-DT199 -BRKSYS-SLACK-SLACR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Pump Transmission | 2027-04-16 | 2027-04-16 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000034934 | 16.04.2027 | 11000 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TMCPP | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TMCPP90003096
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Overhaul Air Conditioner 24M | 2027-04-16 | 2027-04-18 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000346681 | 16.04.2027 | 24 Monthly | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Pump Brake Control | 2027-04-17 | 2027-04-17 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000034615 | 17.04.2027 | 11000 | CLB-MP-HAUL-DT172 -BRKSYS-HYFPP | 7500 | 92350 | 5598 | CLB-MP-HAUL-DT172 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Pump Transmission | 2027-04-18 | 2027-04-18 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035265 | 18.04.2027 | 11000 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TMCPP | 7500 | 92088 | 5719 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Pump Brake Control | 2027-04-18 | 2027-04-18 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035276 | 18.04.2027 | 11000 | CLB-MP-HAUL-DT185 -BRKSYS-HYFPP | 7500 | 92088 | 5719 | CLB-MP-HAUL-DT185 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Brake Relay Valve | 2027-04-18 | 2027-04-18 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078686 | 18.04.2027 | 11000 | CLB-MP-HAUL-DT185 -BRKSYS-BRVRL | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRVRL90009877
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Operators Seat | 2027-04-19 | 2027-04-19 | 4 hrs | FY27 | 8 | 90003066 | A1 | 1000033947 | 19.04.2027 | 6000 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-SEATS | 3300 | 44025 | 3632 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-SEATS90003066
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Water Cannon | 2027-04-19 | 2027-04-19 | 12 hrs | FY27 | 24 | 90015535 | 1 | 1000133455 | 19.04.2027 | 12 Monthly | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON90015535
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Overhaul Air Conditioner 24M | 2027-04-20 | 2027-04-22 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000350427 | 20.04.2027 | 24 Monthly | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Hyd Pump Steering Main | 2027-04-20 | 2027-04-20 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000035279 | 20.04.2027 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STPMP | 7500 | 92088 | 9689 | CLB-MP-HAUL-DT185 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Steering HMU | 2027-04-20 | 2027-04-20 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000035280 | 20.04.2027 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STHMU | 7500 | 92088 | 9689 | CLB-MP-HAUL-DT185 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Brake Slack Adjuster Front | 2027-04-20 | 2027-04-20 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072231 | 20.04.2027 | 18000 | CLB-MP-HAUL-DT173 -BRKSYS-SLACK-SLACF | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Brake Slack Adjuster Rear | 2027-04-20 | 2027-04-20 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072269 | 20.04.2027 | 18000 | CLB-MP-HAUL-DT173 -BRKSYS-SLACK-SLACR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Tyre Sense Battery | 2027-04-21 | 2027-04-21 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163941 | 21.04.2027 | 24 Monthly | CLB-MP-HAUL-DT166 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT166 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Overhaul Air Conditioner 24M | 2027-04-22 | 2027-04-24 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000347287 | 22.04.2027 | 24 Monthly | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Seat Operator | 2027-04-22 | 2027-04-22 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000346777 | 22.04.2027 | 14000 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-SEATS | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5475 | DT5475 Service Air Conditioner 12M | 2027-04-23 | 2027-04-23 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000363964 | 23.04.2027 | 12 Monthly | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN | 6500 | 211 | 211 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Overhaul Air Conditioner 24M | 2027-04-24 | 2027-04-26 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000346728 | 24.04.2027 | 24 Monthly | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Pump Drive Driveshaft Unis | 2027-04-24 | 2027-04-24 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034933 | 24.04.2027 | 11000 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR-DRSHT | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Service Suspension Cylinders | 2027-04-24 | 2027-04-24 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106887 | 24.04.2027 | 11000 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN | 7500 | 81600 | 28262 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Brake Relay Valve | 2027-04-24 | 2027-04-24 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078591 | 24.04.2027 | 11000 | CLB-MP-HAUL-DT178 -BRKSYS-BRVRL | 7500 | 81600 | 5737 | CLB-MP-HAUL-DT178 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Final Drive LH | 2027-04-25 | 2027-04-26 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000150578 | 25.04.2027 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-FDRVE-FDRLH | 7500 | 49737 | 16528 | CLB-MP-HAUL-DT224 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Final Drive RH | 2027-04-25 | 2027-04-26 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000150579 | 25.04.2027 | 22000 | CLB-MP-HAUL-DT224 -FDRSYS-FDRVE-FDRRH | 7500 | 49737 | 16528 | CLB-MP-HAUL-DT224 -FDRSYS-FDRVE-FDRRH90003100
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 5000Hr Valve Set | 2027-04-27 | 2027-04-27 | 12 hrs | FY27 | 24 | 90028725 | A1 | 1000289440 | 27.04.2027 | 5000 | CLB-MP-SUPP-WC015 -ENGINE | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl PTO Uni's | 2027-04-27 | 2027-04-27 | 4 hrs | FY27 | 4 | 90031093 | A1 | 1000307809 | 27.04.2027 | 5000 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT90031093
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Service Airconditioner | 2027-04-27 | 2027-04-27 | 12 hrs | FY27 | 12 | 90028728 | A1 | 1000289437 | 27.04.2027 | 5000 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN90028728
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Steering Ball Studs | 2027-04-28 | 2027-04-29 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385406 | 28.04.2027 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STLTR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Hyd Pump Steering Main | 2027-04-28 | 2027-04-28 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034341 | 28.04.2027 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STPMP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Steering HMU | 2027-04-28 | 2027-04-28 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034342 | 28.04.2027 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STHMU | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Cyl Steering LH | 2027-04-28 | 2027-04-28 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034343 | 28.04.2027 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Tyre Sense Battery | 2027-04-29 | 2027-04-29 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163951 | 29.04.2027 | 24 Monthly | CLB-MP-HAUL-DT176 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT176 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 3Y Air Tank LH Int Insp & PRV Repl | 2027-04-29 | 2027-04-29 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389363 | 29.04.2027 | 36 Monthly | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH | 7500 | 85021 | 13713 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 3Y Air Tank RH Int Insp & PRV Repl | 2027-04-29 | 2027-04-29 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389365 | 29.04.2027 | 36 Monthly | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH | 7500 | 85021 | 13713 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH90038754
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Seat Operator | 2027-04-30 | 2027-04-30 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000300049 | 30.04.2027 | 14000 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-SEATS | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Service Air Conditioner | 2027-04-30 | 2027-04-30 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160394 | 30.04.2027 | 5500 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-AIRCN | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Overhaul Air Conditioner 24M | 2027-05-01 | 2027-05-03 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000349046 | 01.05.2027 | 24 Monthly | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Final Drive LH | 2027-05-01 | 2027-05-02 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000034827 | 01.05.2027 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-FDRVE-FDRLH | 7500 | 85284 | 16434 | CLB-MP-HAUL-DT176 -FDRSYS-FDRVE-FDRLH90003099
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Seat Operator | 2027-05-01 | 2027-05-01 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000314525 | 01.05.2027 | 14000 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-SEATS | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-02 | 2027-05-02 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389343 | 02.05.2027 | 36 Monthly | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH | 7500 | 89925 | 89925 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-02 | 2027-05-02 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389345 | 02.05.2027 | 36 Monthly | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH | 7500 | 89925 | 89925 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Steering HMU | 2027-05-02 | 2027-05-02 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034452 | 02.05.2027 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STHMU | 7500 | 93410 | 9365 | CLB-MP-HAUL-DT169 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Cyl Steering LH | 2027-05-02 | 2027-05-02 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034453 | 02.05.2027 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYL | 7500 | 93410 | 25282 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYL90003111
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Fan Cooling System | 2027-05-02 | 2027-05-02 | 12 hrs | FY27 | 24 | 90013148 | A1 | 1000110229 | 02.05.2027 | 11000 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-COFAN | 3500 | 91736 | 8409 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-COFAN90013148
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-03 | 2027-05-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389319 | 03.05.2027 | 36 Monthly | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH | 7500 | 78739 | 40861 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-03 | 2027-05-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389321 | 03.05.2027 | 36 Monthly | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH | 7500 | 78739 | 40861 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Service Air Conditioner | 2027-05-04 | 2027-05-04 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160966 | 04.05.2027 | 5500 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-AIRCN | 7500 | 91119 | 14869 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Drive Line Axle LH | 2027-05-04 | 2027-05-04 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123524 | 04.05.2027 | 30000 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX-AXLLH | 7500 | 84079 | 24410 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Drive Line Axle RH | 2027-05-04 | 2027-05-04 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123585 | 04.05.2027 | 30000 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX-AXLRH | 7500 | 84079 | 24410 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX-AXLRH90014552
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Service Air Conditioner 12M | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000372488 | 05.05.2027 | 12 Monthly | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Service Air Conditioner 12M | 2027-05-05 | 2027-05-05 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000371819 | 05.05.2027 | 12 Monthly | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Hyd Pump Steering Main | 2027-05-05 | 2027-05-05 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000035709 | 05.05.2027 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STPMP | 7500 | 91174 | 9223 | CLB-MP-HAUL-DT192 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Pump Transmission | 2027-05-05 | 2027-05-05 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000036108 | 05.05.2027 | 11000 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TMCPP | 7500 | 85978 | 5385 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Transmission | 2027-05-05 | 2027-05-06 | 28 hrs | FY27 | 48 | 90003093 | 1 | 1000035043 | 05.05.2027 | 22000 | CLB-MP-HAUL-DT180 -TRNSYS-TRANS | 7500 | 89560 | 16391 | CLB-MP-HAUL-DT180 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Transmission Oil Cooler | 2027-05-05 | 2027-05-05 | 13 hrs | FY27 | 13 | 90003532 | 1 | 1000040989 | 05.05.2027 | 22000 | CLB-MP-HAUL-DT180 -TRNSYS-TROLC | 7500 | 89560 | 16391 | CLB-MP-HAUL-DT180 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Engine Pump Drive | 2027-05-05 | 2027-05-06 | 32 hrs | FY27 | 62 | 90003089 | 1 | 1000034985 | 05.05.2027 | 22000 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR | 7500 | 84079 | 16390 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR90003089
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Spiders Transmission Driveshaft | 2027-05-05 | 2027-05-05 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154384 | 05.05.2027 | 11000 | CLB-MP-HAUL-DT171 -FDRSYS-DRSHT-UNVSL | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Transmission | 2027-05-06 | 2027-05-07 | 28 hrs | FY27 | 48 | 90003093 | 1 | 1000034435 | 06.05.2027 | 22000 | CLB-MP-HAUL-DT169 -TRNSYS-TRANS | 7500 | 93410 | 16379 | CLB-MP-HAUL-DT169 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Transmission Oil Cooler | 2027-05-06 | 2027-05-06 | 13 hrs | FY27 | 13 | 90003532 | 1 | 1000097924 | 06.05.2027 | 22000 | CLB-MP-HAUL-DT169 -TRNSYS-TROLC | 7500 | 93410 | 16379 | CLB-MP-HAUL-DT169 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Hyd Pump Steering Main | 2027-05-06 | 2027-05-06 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034451 | 06.05.2027 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STPMP | 7500 | 93410 | 9339 | CLB-MP-HAUL-DT169 -STRSYS-STPMP90003109
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Seat Operator | 2027-05-06 | 2027-05-06 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000346710 | 06.05.2027 | 14000 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-SEATS | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Drive Line Axle LH | 2027-05-09 | 2027-05-09 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123522 | 09.05.2027 | 30000 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX-AXLLH | 7500 | 81791 | 24250 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Drive Line Axle RH | 2027-05-09 | 2027-05-09 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123583 | 09.05.2027 | 30000 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX-AXLRH | 7500 | 81791 | 24250 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Drive Line Axle LH | 2027-05-09 | 2027-05-09 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123535 | 09.05.2027 | 30000 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX-AXLLH | 7500 | 90698 | 24244 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Drive Line Axle RH | 2027-05-09 | 2027-05-09 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123596 | 09.05.2027 | 30000 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX-AXLRH | 7500 | 90698 | 24244 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Drive Line Axle LH | 2027-05-10 | 2027-05-10 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123509 | 10.05.2027 | 30000 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX-AXLLH | 7500 | 81875 | 24244 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Drive Line Axle RH | 2027-05-10 | 2027-05-10 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123570 | 10.05.2027 | 30000 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX-AXLRH | 7500 | 81875 | 24244 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX-AXLRH90014552
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Seat Operator | 2027-05-10 | 2027-05-10 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000346589 | 10.05.2027 | 14000 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-SEATS | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Cyl Hoist LH | 2027-05-11 | 2027-05-12 | 25 hrs | FY27 | 49 | 90003114 | 1 | 1000035285 | 11.05.2027 | 28000 | CLB-MP-HAUL-DT185 -HYDSYS-HOCYL-HCYLL | 7500 | 92088 | 22242 | CLB-MP-HAUL-DT185 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Drive Line Axle LH | 2027-05-12 | 2027-05-12 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123541 | 12.05.2027 | 30000 | CLB-MP-HAUL-DT196 -FDRSYS-DRLAX-AXLLH | 7500 | 85161 | 24249 | CLB-MP-HAUL-DT196 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Steering Link & Arm Rebush | 2027-05-12 | 2027-05-13 | 27 hrs | FY27 | 45 | 90038355 | A1 | 1000385453 | 12.05.2027 | 30000 | CLB-MP-HAUL-DT190 -STRSYS-STLTR | 7500 | 90698 | 24244 | CLB-MP-HAUL-DT190 -STRSYS-STLTR90038355
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Overhaul Air Conditioner 24M | 2027-05-14 | 2027-05-16 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000349733 | 14.05.2027 | 24 Monthly | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Seat Operator | 2027-05-15 | 2027-05-15 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000347391 | 15.05.2027 | 14000 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-SEATS | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Brake Wheel LH | 2027-05-15 | 2027-05-16 | 32 hrs | FY27 | 38 | 90003104 | 2 | 1000035761 | 15.05.2027 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBLH | 7500 | 83140 | 16066 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Brake Slack Adjuster Front | 2027-05-16 | 2027-05-16 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072258 | 16.05.2027 | 18000 | CLB-MP-HAUL-DT200 -BRKSYS-SLACK-SLACF | 7500 | 92548 | 12117 | CLB-MP-HAUL-DT200 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Brake Slack Adjuster Rear | 2027-05-16 | 2027-05-16 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072296 | 16.05.2027 | 18000 | CLB-MP-HAUL-DT200 -BRKSYS-SLACK-SLACR | 7500 | 92548 | 12117 | CLB-MP-HAUL-DT200 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Steering Ball Studs | 2027-05-16 | 2027-05-17 | 19 hrs | FY27 | 35 | 90038356 | A1 | 1000385446 | 16.05.2027 | 15000 | CLB-MP-HAUL-DT187 -STRSYS-STLTR | 7500 | 93170 | 9139 | CLB-MP-HAUL-DT187 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Final Drive RH | 2027-05-17 | 2027-05-18 | 30 hrs | FY27 | 56 | 90003100 | 1 | 1000150669 | 17.05.2027 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-FDRVE-FDRRH | 7500 | 51346 | 16093 | CLB-MP-HAUL-DT225 -FDRSYS-FDRVE-FDRRH90003100
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Seat Operator | 2027-05-19 | 2027-05-19 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000347316 | 19.05.2027 | 14000 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-SEATS | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Service Suspension Cylinders | 2027-05-19 | 2027-05-19 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106895 | 19.05.2027 | 11000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN90012840
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Overhaul Air Conditioner 24M | 2027-05-20 | 2027-05-22 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000349090 | 20.05.2027 | 24 Monthly | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Hyd Pump Steering Main | 2027-05-21 | 2027-05-21 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034065 | 21.05.2027 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STPMP | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Steering HMU | 2027-05-21 | 2027-05-21 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000034066 | 21.05.2027 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STHMU | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Cyl Steering RH | 2027-05-21 | 2027-05-21 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000034068 | 21.05.2027 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-21 | 2027-05-21 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389331 | 21.05.2027 | 36 Monthly | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH | 7500 | 92948 | 52765 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-21 | 2027-05-21 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389333 | 21.05.2027 | 36 Monthly | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH | 7500 | 92948 | 52765 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Final Drive LH | 2027-05-22 | 2027-05-23 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000150668 | 22.05.2027 | 22000 | CLB-MP-HAUL-DT225 -FDRSYS-FDRVE-FDRLH | 7500 | 51346 | 15978 | CLB-MP-HAUL-DT225 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Relay Valve | 2027-05-22 | 2027-05-22 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078762 | 22.05.2027 | 11000 | CLB-MP-HAUL-DT190 -BRKSYS-BRVRL | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Air Dryer | 2027-05-22 | 2027-05-22 | 7 hrs | FY27 | 14 | 90003115 | 1 | 1000034791 | 22.05.2027 | 22000 | CLB-MP-HAUL-DT175 -PNEUMC-AIRDR | 7500 | 82722 | 71526 | CLB-MP-HAUL-DT175 -PNEUMC-AIRDR90003115
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 5000Hr Valve Set | 2027-05-22 | 2027-05-22 | 12 hrs | FY27 | 24 | 90028725 | A1 | 1000289422 | 22.05.2027 | 5000 | CLB-MP-SUPP-WC012 -ENGINE | 5000 | 67273 | 20856 | CLB-MP-SUPP-WC012 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Service Airconditioner | 2027-05-22 | 2027-05-22 | 12 hrs | FY27 | 12 | 90028728 | A1 | 1000289419 | 22.05.2027 | 5000 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN | 5000 | 67273 | 10760 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN90028728
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Cyl Steering RH | 2027-05-23 | 2027-05-23 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000035770 | 23.05.2027 | 15000 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYR | 7500 | 83140 | 8872 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Drive Line Axle RH | 2027-05-23 | 2027-05-23 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123579 | 23.05.2027 | 30000 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX-AXLRH | 7500 | 82651 | 23913 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-23 | 2027-05-23 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389435 | 23.05.2027 | 36 Monthly | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH | 7500 | 82302 | 54081 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-23 | 2027-05-23 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389437 | 23.05.2027 | 36 Monthly | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH | 7500 | 82302 | 54081 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-24 | 2027-05-24 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389347 | 24.05.2027 | 36 Monthly | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH | 7500 | 92088 | 46179 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-24 | 2027-05-24 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389349 | 24.05.2027 | 36 Monthly | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH | 7500 | 92088 | 46179 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Pump Transmission | 2027-05-25 | 2027-05-25 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000035045 | 25.05.2027 | 11000 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TMCPP | 7500 | 89560 | 4986 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TMCPP90003096
T264 | Onsite PM | Haul | Fortescue | DT5476 | DT5476 Service Air Conditioner 12M | 2027-05-27 | 2027-05-27 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000364894 | 27.05.2027 | 12 Monthly | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN | 6500 | 920 | 920 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389323 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH | 7500 | 95233 | 95233 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389325 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH | 7500 | 95233 | 95233 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389451 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH | 7500 | 85715 | 85715 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389453 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH | 7500 | 85715 | 85715 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389367 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH | 7500 | 81529 | 8461 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389369 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH | 7500 | 81529 | 8461 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 3Y Air Tank LH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389427 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH | 7500 | 82926 | 82926 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 3Y Air Tank RH Int Insp & PRV Repl | 2027-05-27 | 2027-05-27 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389429 | 27.05.2027 | 36 Monthly | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH | 7500 | 82926 | 82926 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Service Air Conditioner | 2027-05-27 | 2027-05-27 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160380 | 27.05.2027 | 5500 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-AIRCN | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Tyre Sense Battery | 2027-05-27 | 2027-05-27 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163943 | 27.05.2027 | 24 Monthly | CLB-MP-HAUL-DT168 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT168 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Hub & Spindle LH | 2027-05-27 | 2027-05-28 | 26 hrs | FY27 | 50 | 90004020 | 1 | 1000044721 | 27.05.2027 | 24000 | CLB-MP-SUPP-WC014 -STRUCT-AXLES-HUBLH | 5000 | 65823 | 19464 | CLB-MP-SUPP-WC014 -STRUCT-AXLES-HUBLH90004020
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Hub & Spindle RH | 2027-05-27 | 2027-05-28 | 26 hrs | FY27 | 50 | 90026194 | A1 | 1000044722 | 27.05.2027 | 24000 | CLB-MP-SUPP-WC014 -STRUCT-AXLES-HUBRH | 5000 | 65823 | 19464 | CLB-MP-SUPP-WC014 -STRUCT-AXLES-HUBRH90026194
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Spiders Transmission Driveshaft | 2027-05-28 | 2027-05-28 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154444 | 28.05.2027 | 11000 | CLB-MP-HAUL-DT224 -FDRSYS-DRSHT-UNVSL | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Cyl Hoist LH | 2027-05-29 | 2027-05-30 | 25 hrs | FY27 | 49 | 90003114 | 1 | 1000034514 | 29.05.2027 | 28000 | CLB-MP-HAUL-DT170 -HYDSYS-HOCYL-HCYLL | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Cyl Hoist RH | 2027-05-29 | 2027-05-30 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000034515 | 29.05.2027 | 28000 | CLB-MP-HAUL-DT170 -HYDSYS-HOCYL-HCYLR | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Engine Midlife complete | 2027-05-29 | 2027-06-02 | 104.5 hrs | FY27 | 116.5 | 90017316 | 2 | 1000157083 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -ENGINE | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Midlife Valve Set - Adjust | 2027-05-29 | 2027-05-29 | 6 hrs | FY27 | 12 | 90017314 | 1 | 1000390985 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -ENGINE | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Pump Drive Driveshaft Unis | 2027-05-29 | 2027-05-29 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000150574 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR-DRSHT | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Pump Transmission | 2027-05-29 | 2027-05-29 | 7 hrs | FY27 | 7 | 90003096 | 1 | 1000150575 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TMCPP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Brake Relay Valve | 2027-05-29 | 2027-05-29 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000150621 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -BRKSYS-BRVRL | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Pump Brake Control | 2027-05-29 | 2027-05-29 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000150584 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -BRKSYS-HYFPP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Service Suspension Cylinders | 2027-05-29 | 2027-05-29 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000150638 | 29.05.2027 | 11000 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN | 7500 | 49737 | 26842 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Service Suspension Cylinders | 2027-05-30 | 2027-05-30 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106941 | 30.05.2027 | 11000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN | 7500 | 91174 | 15811 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Service Air Conditioner | 2027-05-30 | 2027-05-30 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160388 | 30.05.2027 | 5500 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-AIRCN | 7500 | 92002 | 14039 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Water Cannon Inspect | 2027-06-01 | 2027-06-01 | 3 hrs | FY27 | 3 | 90033661 | A1 | 1000338790 | 01.06.2027 | 6 Monthly | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | 5000 | 67273 | 3900 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Steering HMU | 2027-06-02 | 2027-06-02 | 14 hrs | FY27 | 14 | 90003110 | 1 | 1000035594 | 02.06.2027 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STHMU | 7500 | 90698 | 8800 | CLB-MP-HAUL-DT190 -STRSYS-STHMU90003110
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Suspension Cylinder LHR | 2027-06-02 | 2027-06-02 | 16 hrs | FY27 | 28 | 90004014 | 1 | 1000044805 | 02.06.2027 | 20000 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYLR | 5000 | 67897 | 15856 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYLR90004014
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-03 | 2027-06-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389407 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH | 7500 | 83734 | 10797 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-03 | 2027-06-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389409 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH | 7500 | 83734 | 10797 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Hyd Pump Steering Main | 2027-06-03 | 2027-06-03 | 8 hrs | FY27 | 8 | 90003109 | 1 | 1000034893 | 03.06.2027 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STPMP | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Cyl Steering LH | 2027-06-03 | 2027-06-03 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034895 | 03.06.2027 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYL | 7500 | 81791 | 29757 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-03 | 2027-06-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389383 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH | 7500 | 83200 | 57009 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-03 | 2027-06-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389385 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH | 7500 | 83200 | 57009 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-03 | 2027-06-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389351 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH | 7500 | 82388 | 82388 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-03 | 2027-06-03 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389353 | 03.06.2027 | 36 Monthly | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH | 7500 | 82388 | 82388 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Cyl Steering LH | 2027-06-04 | 2027-06-04 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000034950 | 04.06.2027 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYL | 7500 | 81600 | 8739 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-06 | 2027-06-06 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389375 | 06.06.2027 | 36 Monthly | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH | 7500 | 83820 | 11121 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-06 | 2027-06-06 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389377 | 06.06.2027 | 36 Monthly | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH | 7500 | 83820 | 11121 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Tyre Sense Battery | 2027-06-06 | 2027-06-06 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163940 | 06.06.2027 | 24 Monthly | CLB-MP-HAUL-DT165 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT165 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Spiders Driveshaft Pump | 2027-06-06 | 2027-06-06 | 4 hrs | FY27 | 4 | 90003989 | 1 | 1000082714 | 06.06.2027 | 10000 | CLB-MP-SUPP-PM0006-ENGINE-PMPDR-DRSHT | 4200 | 53807 | 6312 | CLB-MP-SUPP-PM0006-ENGINE-PMPDR-DRSHT90003989
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Rear Axle Oil Pump | 2027-06-06 | 2027-06-06 | 2 hrs | FY27 | 2 | 90003996 | 1 | 1000082724 | 06.06.2027 | 10000 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC-HYPUM | 4200 | 53807 | 6312 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC-HYPUM90003996
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Rear Axle Cooling Fan Motor | 2027-06-06 | 2027-06-06 | 2 hrs | FY27 | 2 | 90003997 | 1 | 1000082725 | 06.06.2027 | 10000 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC-MTFAN | 4200 | 53807 | 6312 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Seat Operators | 2027-06-06 | 2027-06-06 | 4 hrs | FY27 | 4 | 90004012 | 1 | 1000161835 | 06.06.2027 | 10000 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-SEATS | 4200 | 53807 | 6312 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-SEATS90004012
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Service Air Conditioner 12M | 2027-06-06 | 2027-06-06 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000314526 | 06.06.2027 | 12 Monthly | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Service Air Conditioner | 2027-06-07 | 2027-06-07 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160376 | 07.06.2027 | 5500 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-AIRCN | 7500 | 93410 | 14340 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Tyre Sense Battery | 2027-06-08 | 2027-06-08 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163947 | 08.06.2027 | 24 Monthly | CLB-MP-HAUL-DT172 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT172 -MANGMT-TYRSN90017022
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Service Airconditioner | 2027-06-08 | 2027-06-09 | 24 hrs | FY27 | 24 | 90029084 | A1 | 1000290589 | 08.06.2027 | 4500 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-AIRCN | 2500 | 48856 | 2844 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-AIRCN90029084
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Cyl Steering LH | 2027-06-09 | 2027-06-09 | 16 hrs | FY27 | 28 | 90003111 | 2 | 1000035336 | 09.06.2027 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYL | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYL90003111
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Seat Operator | 2027-06-10 | 2027-06-10 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000349075 | 10.06.2027 | 14000 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-SEATS | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389395 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH | 7500 | 91826 | 53019 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389397 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH | 7500 | 91826 | 53019 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389387 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH | 7500 | 90227 | 40762 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389389 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH | 7500 | 90227 | 40762 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389439 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH | 7500 | 84897 | 84897 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389441 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH | 7500 | 84897 | 84897 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389455 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH | 7500 | 92315 | 50047 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389457 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH | 7500 | 92315 | 50047 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389415 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH | 7500 | 90436 | 17328 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-10 | 2027-06-10 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389417 | 10.06.2027 | 36 Monthly | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH | 7500 | 90436 | 17328 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH90038754
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Overhaul Air Conditioner 24M | 2027-06-11 | 2027-06-13 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000350383 | 11.06.2027 | 24 Monthly | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN90029460
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl PTO Uni's | 2027-06-11 | 2027-06-11 | 4 hrs | FY27 | 4 | 90031093 | A1 | 1000307805 | 11.06.2027 | 5000 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT | 5000 | 63833 | 10962 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT90031093
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Seat Operator | 2027-06-12 | 2027-06-12 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000349119 | 12.06.2027 | 14000 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-SEATS | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Cyl Suspension RHR | 2027-06-12 | 2027-06-13 | 23 hrs | FY27 | 42 | 90003122 | 1 | 1000034580 | 12.06.2027 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYRR | 7500 | 90182 | 15620 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Engine Pump Drive | 2027-06-13 | 2027-06-14 | 32 hrs | FY27 | 62 | 90003089 | 1 | 1000034044 | 13.06.2027 | 22000 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR | 7500 | 83473 | 15555 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR90003089
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Tyre Sense Battery | 2027-06-14 | 2027-06-14 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163955 | 14.06.2027 | 24 Monthly | CLB-MP-HAUL-DT180 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT180 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Brake Wheel RH | 2027-06-14 | 2027-06-15 | 33 hrs | FY27 | 61 | 90003105 | 2 | 1000035460 | 14.06.2027 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-AXLES-HUBRH | 7500 | 83931 | 15531 | CLB-MP-HAUL-DT188 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Drive Line Axle LH | 2027-06-14 | 2027-06-14 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123510 | 14.06.2027 | 30000 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX-AXLLH | 7500 | 78966 | 23545 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Drive Line Axle RH | 2027-06-14 | 2027-06-14 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123571 | 14.06.2027 | 30000 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX-AXLRH | 7500 | 78966 | 23545 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Service Air Conditioner | 2027-06-14 | 2027-06-14 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160387 | 14.06.2027 | 5500 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-AIRCN | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Overhaul Air Conditioner 24M | 2027-06-14 | 2027-06-16 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000326640 | 14.06.2027 | 24 Monthly | CLB-MP-HAUL-DT5419-STRUCT-CABIN-AIRCN | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Drive Line Axle LH | 2027-06-15 | 2027-06-15 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123525 | 15.06.2027 | 30000 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX-AXLLH | 7500 | 89560 | 23548 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Brake Slack Adjuster Front | 2027-06-16 | 2027-06-16 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072238 | 16.06.2027 | 18000 | CLB-MP-HAUL-DT180 -BRKSYS-SLACK-SLACF | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Brake Slack Adjuster Rear | 2027-06-16 | 2027-06-16 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072276 | 16.06.2027 | 18000 | CLB-MP-HAUL-DT180 -BRKSYS-SLACK-SLACR | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Cyl Suspension RHF | 2027-06-16 | 2027-06-17 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067776 | 16.06.2027 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYRF | 7500 | 83303 | 15419 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYRF90003121
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Control Cabinet Coolant | 2027-06-17 | 2027-06-17 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000346784 | 17.06.2027 | 15000 | CLB-MP-HAUL-DT5444-ELCTHV-HVCAB-COOLR | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Spiders Transmission Driveshaft | 2027-06-17 | 2027-06-17 | 4 hrs | FY27 | 8 | 90017135 | 1 | 1000154408 | 17.06.2027 | 11000 | CLB-MP-HAUL-DT183 -FDRSYS-DRSHT-UNVSL | 7500 | 90364 | 14758 | CLB-MP-HAUL-DT183 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Drive Line Axle LH | 2027-06-17 | 2027-06-17 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123545 | 17.06.2027 | 30000 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX-AXLLH | 7500 | 92548 | 23460 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Drive Line Axle RH | 2027-06-17 | 2027-06-17 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123606 | 17.06.2027 | 30000 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX-AXLRH | 7500 | 92548 | 23460 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Final Drive LH | 2027-06-19 | 2027-06-20 | 30 hrs | FY27 | 56 | 90003099 | 1 | 1000035213 | 19.06.2027 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-FDRVE-FDRLH | 7500 | 90364 | 15384 | CLB-MP-HAUL-DT183 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Drive Driveshaft Unis | 2027-06-19 | 2027-06-19 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034381 | 19.06.2027 | 11000 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR-DRSHT | 7500 | 93142 | 15366 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Brake Relay Valve | 2027-06-19 | 2027-06-19 | 6 hrs | FY27 | 6 | 90009877 | 1 | 1000078439 | 19.06.2027 | 11000 | CLB-MP-HAUL-DT168 -BRKSYS-BRVRL | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Drive Line Axle LH | 2027-06-20 | 2027-06-20 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123533 | 20.06.2027 | 30000 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX-AXLLH | 7500 | 83931 | 23443 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Drive Line Axle RH | 2027-06-20 | 2027-06-20 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123594 | 20.06.2027 | 30000 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX-AXLRH | 7500 | 83931 | 23443 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Drive Driveshaft Unis | 2027-06-20 | 2027-06-20 | 4 hrs | FY27 | 4 | 90009874 | 1 | 1000034988 | 20.06.2027 | 11000 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR-DRSHT | 7500 | 84079 | 16664 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Midlife Valve Set - Adjust | 2027-06-20 | 2027-06-20 | 6 hrs | FY27 | 12 | 90017314 | 1 | 1000390892 | 20.06.2027 | 11000 | CLB-MP-HAUL-DT168 -ENGINE | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Engine Midlife complete | 2027-06-20 | 2027-06-24 | 107.5 hrs | FY27 | 119.5 | 90017316 | 1 | 1000156555 | 23.06.2027 | 11000 | CLB-MP-HAUL-DT168 -ENGINE | 7500 | 93142 | 4514 | CLB-MP-HAUL-DT168 -ENGINE90017316
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Engine Midlife complete | 2027-06-20 | 2027-06-22 | 51 hrs | FY27 | 83 | 90029500 | A1 | 1000326657 | 20.06.2027 | 17500 | CLB-MP-HAUL-DT5419-ENGINE | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Brake Slack Adjuster Front | 2027-06-21 | 2027-06-21 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072222 | 21.06.2027 | 18000 | CLB-MP-HAUL-DT164 -BRKSYS-SLACK-SLACF | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Brake Slack Adjuster Rear | 2027-06-21 | 2027-06-21 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072260 | 21.06.2027 | 18000 | CLB-MP-HAUL-DT164 -BRKSYS-SLACK-SLACR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Pump Brake Control | 2027-06-21 | 2027-06-21 | 5 hrs | FY27 | 5 | 90003106 | 1 | 1000035331 | 21.06.2027 | 11000 | CLB-MP-HAUL-DT186 -BRKSYS-HYFPP | 7500 | 89749 | 16218 | CLB-MP-HAUL-DT186 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-22 | 2027-06-22 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389371 | 22.06.2027 | 36 Monthly | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH | 7500 | 81378 | 16017 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-22 | 2027-06-22 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389373 | 22.06.2027 | 36 Monthly | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH | 7500 | 81378 | 16017 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Tyre Sense Battery | 2027-06-22 | 2027-06-22 | 2 hrs | FY27 | 2 | 90017022 | 1 | 1000163975 | 22.06.2027 | 24 Monthly | CLB-MP-HAUL-DT200 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT200 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Water Cannon & Valves Repl | 2027-06-22 | 2027-06-23 | 24 hrs | FY27 | 48 | 90033662 | A1 | 1000338996 | 22.06.2027 | 24 Monthly | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | 5000 | 64118 | 9073 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON90033662
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Seat Operator | 2027-06-23 | 2027-06-23 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000349962 | 23.06.2027 | 14000 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-SEATS | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Seat Operator | 2027-06-23 | 2027-06-23 | 2 hrs | FY27 | 2 | 90029285 | A1 | 1000349620 | 23.06.2027 | 14000 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-SEATS | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Steering RH | 2027-06-23 | 2027-06-23 | 16 hrs | FY27 | 28 | 90003111 | 3 | 1000035712 | 23.06.2027 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYR | 7500 | 91174 | 24285 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Brake Slack Adjuster Front | 2027-06-23 | 2027-06-23 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072237 | 23.06.2027 | 18000 | CLB-MP-HAUL-DT179 -BRKSYS-SLACK-SLACF | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Brake Slack Adjuster Rear | 2027-06-23 | 2027-06-23 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072275 | 23.06.2027 | 18000 | CLB-MP-HAUL-DT179 -BRKSYS-SLACK-SLACR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Cyl Hoist RH | 2027-06-23 | 2027-06-24 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000035121 | 23.06.2027 | 28000 | CLB-MP-HAUL-DT181 -HYDSYS-HOCYL-HCYLR | 7500 | 83441 | 21399 | CLB-MP-HAUL-DT181 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Drive Line Axle LH | 2027-06-23 | 2027-06-23 | 4 hrs | FY27 | 8 | 90014551 | 1 | 1000123540 | 23.06.2027 | 30000 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX-AXLLH | 7500 | 82554 | 23360 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Drive Line Axle RH | 2027-06-23 | 2027-06-23 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123601 | 23.06.2027 | 30000 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX-AXLRH | 7500 | 82554 | 23360 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX-AXLRH90014552
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Overhaul Air Conditioner 24M | 2027-06-24 | 2027-06-26 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000357053 | 24.06.2027 | 24 Monthly | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Overhaul Air Conditioner 24M | 2027-06-24 | 2027-06-26 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000349591 | 24.06.2027 | 24 Monthly | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Drive Line Axle RH | 2027-06-24 | 2027-06-24 | 4 hrs | FY27 | 8 | 90014552 | 1 | 1000123586 | 24.06.2027 | 30000 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX-AXLRH | 7500 | 89560 | 23548 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-24 | 2027-06-24 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389379 | 24.06.2027 | 36 Monthly | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH | 7500 | 89376 | 46929 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-24 | 2027-06-24 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389381 | 24.06.2027 | 36 Monthly | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH | 7500 | 89376 | 46929 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Cyl Hoist RH | 2027-06-24 | 2027-06-25 | 25 hrs | FY27 | 49 | 90003114 | 2 | 1000035176 | 24.06.2027 | 28000 | CLB-MP-HAUL-DT182 -HYDSYS-HOCYL-HCYLR | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Cyl Suspension RHF | 2027-06-24 | 2027-06-25 | 38 hrs | FY27 | 66 | 90003121 | 1 | 1000067880 | 24.06.2027 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYRF | 7500 | 83140 | 15299 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYRF90003121
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Control Cabinet Coolant | 2027-06-25 | 2027-06-25 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332187 | 25.06.2027 | 15000 | CLB-MP-HAUL-DT5390-ELCTHV-HVCAB-COOLR | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Engine Midlife complete | 2027-06-25 | 2027-06-27 | 51 hrs | FY27 | 83 | 90029500 | A1 | 1000314076 | 25.06.2027 | 17500 | CLB-MP-HAUL-DT5405-ENGINE | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Hoist & Brake | 2027-06-25 | 2027-06-25 | 10 hrs | FY27 | 10 | 90003113 | 1 | 1000035008 | 25.06.2027 | 22000 | CLB-MP-HAUL-DT179 -HYDSYS-HOPMP | 7500 | 84079 | 15349 | CLB-MP-HAUL-DT179 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Brake Slack Adjuster Front | 2027-06-25 | 2027-06-25 | 4 hrs | FY27 | 4 | 90009306 | 1 | 1000072245 | 25.06.2027 | 18000 | CLB-MP-HAUL-DT187 -BRKSYS-SLACK-SLACF | 7500 | 93170 | 11315 | CLB-MP-HAUL-DT187 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Brake Slack Adjuster Rear | 2027-06-25 | 2027-06-25 | 4 hrs | FY27 | 4 | 90009307 | 1 | 1000072283 | 25.06.2027 | 18000 | CLB-MP-HAUL-DT187 -BRKSYS-SLACK-SLACR | 7500 | 93170 | 11315 | CLB-MP-HAUL-DT187 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Torque Converter | 2027-06-25 | 2027-06-26 | 32 hrs | FY27 | 62 | 90003092 | 1 | 1000034766 | 25.06.2027 | 22000 | CLB-MP-HAUL-DT175 -TRNSYS-TRQUE | 7500 | 82722 | 15352 | CLB-MP-HAUL-DT175 -TRNSYS-TRQUE90003092
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Pump Torque Converter Charge | 2027-06-25 | 2027-06-25 | 5 hrs | FY27 | 5 | 90003095 | 1 | 1000080177 | 25.06.2027 | 22000 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TCCPP | 7500 | 82722 | 15352 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TCCPP90003095
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 5500Hr Valve Set | 2027-06-25 | 2027-06-25 | 8 hrs | FY27 | 16 | 90029173 | A1 | 1000291240 | 25.06.2027 | 5500 | CLB-MP-SUPP-PM0004-ENGINE | 3500 | 91736 | 13390 | CLB-MP-SUPP-PM0004-ENGINE90029173
T264 | Onsite PM | Haul | Fortescue | DT5477 | DT5477 Service Air Conditioner 12M | 2027-06-26 | 2027-06-26 | 12 hrs | FY27 | 12 | 90029300 | A1 | 1000365185 | 26.06.2027 | 12 Monthly | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN | 6500 | 630 | 630 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 3Y Air Tank LH Int Insp & PRV Repl | 2027-06-26 | 2027-06-26 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389359 | 26.06.2027 | 36 Monthly | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH | 7500 | 82478 | 82478 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH90038754
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 3Y Air Tank RH Int Insp & PRV Repl | 2027-06-26 | 2027-06-26 | 4.5 hrs | FY27 | 4.5 | 90038754 | A1 | 1000389361 | 26.06.2027 | 36 Monthly | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH | 7500 | 82478 | 82478 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH90038754
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Service Suspension Cylinders | 2027-06-26 | 2027-06-26 | 15 hrs | FY27 | 27 | 90012840 | 1 | 1000106883 | 26.06.2027 | 11000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN | 7500 | 83749 | 23899 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Radiator Engine Cooling | 2027-06-26 | 2027-06-28 | 55 hrs | FY27 | 85 | 90003081 | 1 | 1000035863 | 26.06.2027 | 22000 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-RADTR | 7400 | 82554 | 82554 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-RADTR90003081
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Control Cabinet Coolant | 2027-06-26 | 2027-06-26 | 1 hr | FY27 | 1 | 90033128 | A1 | 1000332192 | 26.06.2027 | 15000 | CLB-MP-HAUL-DT5411-ELCTHV-HVCAB-COOLR | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Service Air Conditioner | 2027-06-27 | 2027-06-27 | 12 hrs | FY27 | 12 | 90017450 | 1 | 1000160377 | 27.06.2027 | 5500 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-AIRCN | 7500 | 90182 | 8268 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Engine Midlife complete | 2027-06-27 | 2027-06-29 | 51 hrs | FY27 | 83 | 90029500 | A1 | 1000326402 | 27.06.2027 | 17500 | CLB-MP-HAUL-DT5417-ENGINE | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Overhaul Air Conditioner 24M | 2027-06-30 | 2027-07-02 | 48 hrs | FY27 | 48 | 90029460 | A1 | 1000326243 | 30.06.2027 | 24 Monthly | CLB-MP-HAUL-DT5416-STRUCT-CABIN-AIRCN | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-AIRCN90029460
| Onsite PM | Haul | Fortescue |  | FY28 - HAUL - COMPONENTS DURING PM | 2027-07-01 |  |  | FY28
| Onsite PM | Haul | Fortescue | MOC | MAJOR ON CONDITION | 2027-07-01 | 2028-06-30 | 365 days | FY28
| Onsite PM | Haul | Fortescue | MOC | JULY | 2027-07-01 | 2027-07-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | AUGUST | 2027-08-01 | 2027-08-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | SEPTEMBER | 2027-09-01 | 2027-09-30 | 29 days | FY28
| Onsite PM | Haul | Fortescue | MOC | OCTOBER | 2027-10-01 | 2027-10-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | NOVEMBER | 2027-11-01 | 2027-11-30 | 29 days | FY28
| Onsite PM | Haul | Fortescue | MOC | DECEMBER | 2027-12-01 | 2027-12-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | JANUARY | 2028-01-01 | 2028-01-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | FEBRUARY | 2028-02-01 | 2028-02-28 | 27 days | FY28
| Onsite PM | Haul | Fortescue | MOC | MARCH | 2028-03-01 | 2028-03-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | APRIL | 2028-04-01 | 2028-04-30 | 29 days | FY28
| Onsite PM | Haul | Fortescue | MOC | MAY | 2028-05-01 | 2028-05-31 | 30 days | FY28
| Onsite PM | Haul | Fortescue | MOC | JUNE | 2028-06-01 | 2028-06-30 | 29 days | FY28
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Control Cabinet Coolant | 2027-07-01 | 2027-07-01 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000346717 | 01.07.2027 | 15000 | CLB-MP-HAUL-DT5443-ELCTHV-HVCAB-COOLR | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Hyd Pump Steering Main | 2027-07-02 | 2027-07-02 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035999 | 02.07.2027 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STPMP | 7500 | 86259 | 8210 | CLB-MP-HAUL-DT197 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Drive Line Axle LH | 2027-07-02 | 2027-07-02 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123512 | 02.07.2027 | 30000 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX-AXLLH | 7500 | 83303 | 23066 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Drive Line Axle RH | 2027-07-02 | 2027-07-02 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123573 | 02.07.2027 | 30000 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX-AXLRH | 7500 | 83303 | 23066 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Transmission | 2027-07-04 | 2027-07-05 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000035693 | 04.07.2027 | 22000 | CLB-MP-HAUL-DT192 -TRNSYS-TRANS | 7500 | 91174 | 15068 | CLB-MP-HAUL-DT192 -TRNSYS-TRANS90003093
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Air Con System Service | 2027-07-04 | 2027-07-04 | 12 hrs | FY28 | 12 | 90028738 | A1 | 1000286361 | 04.07.2027 | 12 Monthly | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN | 3500 | 91736 | 186 | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN90028738
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Control Cabinet Coolant | 2027-07-05 | 2027-07-05 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000346596 | 05.07.2027 | 15000 | CLB-MP-HAUL-DT5442-ELCTHV-HVCAB-COOLR | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Seat Operator | 2027-07-06 | 2027-07-06 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000350412 | 06.07.2027 | 14000 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-SEATS | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Differential | 2027-07-06 | 2027-07-08 | 44 hrs | FY28 | 66 | 90003098 | 1 | 1000034991 | 06.07.2027 | 22000 | CLB-MP-HAUL-DT179 -FDRSYS-DIFFL | 7500 | 84079 | 13410 | CLB-MP-HAUL-DT179 -FDRSYS-DIFFL90003098
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Service Air Conditioner | 2027-07-07 | 2027-07-07 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160398 | 07.07.2027 | 5500 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-AIRCN | 7500 | 91174 | 8325 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Overhaul Air Conditioner 24M | 2027-07-07 | 2027-07-09 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000326476 | 07.07.2027 | 24 Monthly | CLB-MP-HAUL-DT5418-STRUCT-CABIN-AIRCN | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Tyre Sense Battery | 2027-07-08 | 2027-07-08 | 2 hrs | FY28 | 2 | 90017022 | 1 | 1000163973 | 08.07.2027 | 24 Monthly | CLB-MP-HAUL-DT198 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT198 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Engine Midlife complete | 2027-07-09 | 2027-07-11 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000300356 | 09.07.2027 | 17500 | CLB-MP-HAUL-DT5391-ENGINE | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Relay Valve | 2027-07-09 | 2027-07-09 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078648 | 09.07.2027 | 11000 | CLB-MP-HAUL-DT182 -BRKSYS-BRVRL | 7500 | 92002 | 16119 | CLB-MP-HAUL-DT182 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Spiders Transmission Driveshaft | 2027-07-09 | 2027-07-09 | 4 hrs | FY28 | 8 | 90017135 | 1 | 1000154378 | 09.07.2027 | 11000 | CLB-MP-HAUL-DT168 -FDRSYS-DRSHT-UNVSL | 7500 | 93142 | 17991 | CLB-MP-HAUL-DT168 -FDRSYS-DRSHT-UNVSL90017135
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Adjust Engine Valve Set | 2027-07-09 | 2027-07-09 | 6 hrs | FY28 | 6 | 90017451 | A1 | 1000290598 | 09.07.2027 | 3000 | CLB-MP-SUPP-SV020 -ENGINE | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -ENGINE90017451
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Control Cabinet Coolant | 2027-07-10 | 2027-07-10 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000347398 | 10.07.2027 | 15000 | CLB-MP-HAUL-DT5447-ELCTHV-HVCAB-COOLR | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Service Air Conditioner | 2027-07-10 | 2027-07-10 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160374 | 10.07.2027 | 5500 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-AIRCN | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Steering Ball Studs | 2027-07-11 | 2027-07-12 | 19 hrs | FY28 | 35 | 90038356 | A1 | 1000385404 | 11.07.2027 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STLTR | 7500 | 95491 | 8036 | CLB-MP-HAUL-DT166 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Steering HMU | 2027-07-11 | 2027-07-11 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000034287 | 11.07.2027 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STHMU | 7500 | 95491 | 25609 | CLB-MP-HAUL-DT166 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Service Suspension Cylinders | 2027-07-11 | 2027-07-11 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106880 | 11.07.2027 | 11000 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN | 7500 | 90182 | 27315 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 1Y Air Tank External Inspect | 2027-07-11 | 2027-07-11 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389210 | 11.07.2027 | 12 Monthly | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK | 4200 | 53807 | 16976 | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK90038749
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 1Y Air Tank External Inspect | 2027-07-11 | 2027-07-11 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389212 | 11.07.2027 | 12 Monthly | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK90038749
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Overhaul Air Conditioner 24M | 2027-07-12 | 2027-07-14 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000357137 | 12.07.2027 | 24 Monthly | CLB-MP-HAUL-DT5467-STRUCT-CABIN-AIRCN | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Brake Slack Adjuster Rear | 2027-07-12 | 2027-07-12 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072284 | 12.07.2027 | 18000 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Hyd Pump Steering Main | 2027-07-12 | 2027-07-12 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000036057 | 12.07.2027 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STPMP | 7500 | 88680 | 7977 | CLB-MP-HAUL-DT198 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Cyl Suspension LHR | 2027-07-12 | 2027-07-13 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000034579 | 12.07.2027 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYLR | 7500 | 90182 | 15013 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYLR90003122
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Rotochamber LH - Replace | 2027-07-12 | 2027-07-12 | 3 hrs | FY28 | 3 | 90018290 | 1 | 1000174672 | 12.07.2027 | 20000 | CLB-MP-SUPP-LL0003-BRKSYS-BRCYL-FROTL | 4200 | 71996 | 53807 | CLB-MP-SUPP-LL0003-BRKSYS-BRCYL-FROTL90018290
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Water Cannon Inspect | 2027-07-12 | 2027-07-12 | 3 hrs | FY28 | 3 | 90033661 | A1 | 1000338794 | 12.07.2027 | 6 Monthly | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | 5000 | 65823 | 12836 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON90033661
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Engine Midlife complete | 2027-07-12 | 2027-07-14 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000326573 | 12.07.2027 | 17500 | CLB-MP-HAUL-DT5418-ENGINE | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Control Cabinet Coolant | 2027-07-14 | 2027-07-14 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000332189 | 14.07.2027 | 15000 | CLB-MP-HAUL-DT5404-ELCTHV-HVCAB-COOLR | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Control Cabinet Coolant | 2027-07-15 | 2027-07-15 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000347323 | 15.07.2027 | 15000 | CLB-MP-HAUL-DT5446-ELCTHV-HVCAB-COOLR | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Service Air Conditioner | 2027-07-16 | 2027-07-16 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160392 | 16.07.2027 | 5500 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-AIRCN | 7500 | 89749 | 14154 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Drive Line Axle LH | 2027-07-16 | 2027-07-16 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123531 | 16.07.2027 | 30000 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX-AXLLH | 7500 | 89749 | 22897 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Drive Line Axle RH | 2027-07-16 | 2027-07-16 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123592 | 16.07.2027 | 30000 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX-AXLRH | 7500 | 89749 | 22897 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX-AXLRH90014552
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Seat Operator | 2027-07-17 | 2027-07-17 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000350456 | 17.07.2027 | 14000 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-SEATS | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Seat Operator | 2027-07-17 | 2027-07-17 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000347019 | 17.07.2027 | 14000 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-SEATS | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Cyl Hoist LH | 2027-07-17 | 2027-07-18 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035120 | 17.07.2027 | 28000 | CLB-MP-HAUL-DT181 -HYDSYS-HOCYL-HCYLL | 7500 | 83441 | 20906 | CLB-MP-HAUL-DT181 -HYDSYS-HOCYL-HCYLL90003114
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Engine Midlife complete | 2027-07-17 | 2027-07-19 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000326260 | 17.07.2027 | 17500 | CLB-MP-HAUL-DT5416-ENGINE | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Engine Midlife complete | 2027-07-19 | 2027-07-21 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000314346 | 19.07.2027 | 17500 | CLB-MP-HAUL-DT5410-ENGINE | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Overhaul Air Conditioner 24M | 2027-07-20 | 2027-07-22 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000360960 | 20.07.2027 | 24 Monthly | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Overhaul Air Conditioner 24M | 2027-07-20 | 2027-07-22 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000360810 | 20.07.2027 | 24 Monthly | CLB-MP-HAUL-DT5468-STRUCT-CABIN-AIRCN | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-AIRCN90029460
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 1Y Air Tank External Inspect | 2027-07-20 | 2027-07-20 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389218 | 20.07.2027 | 12 Monthly | CLB-MP-SUPP-WC014 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC014 -PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Service Suspension Cylinders | 2027-07-22 | 2027-07-22 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106873 | 22.07.2027 | 11000 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN | 7500 | 78966 | 10144 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Brake Rotochamber Left Hand Rear | 2027-07-22 | 2027-07-22 | 2 hrs | FY28 | 2 | 90004017 | 1 | 1000082751 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTLR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTLR90004017
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Brake Rotochamber Right Hand Rear | 2027-07-22 | 2027-07-22 | 2 hrs | FY28 | 2 | 90004017 | 1 | 1000082752 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTRR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTRR90004017
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Brake Control Valves | 2027-07-22 | 2027-07-23 | 24 hrs | FY28 | 48 | 90004000 | 1 | 1000082729 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-BRKSYS-BRVLV | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-BRKSYS-BRVLV90004000
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Brake Slack Adjustor Front | 2027-07-22 | 2027-07-22 | 2 hrs | FY28 | 2 | 90004018 | 1 | 1000082753 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK-SLACF | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK-SLACF90004018
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Brake Slack Adjustor Rear | 2027-07-22 | 2027-07-22 | 2 hrs | FY28 | 2 | 90004019 | 1 | 1000082754 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK-SLACR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK-SLACR90004019
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Radiator Assembly | 2027-07-22 | 2027-07-23 | 20 hrs | FY28 | 38 | 90003977 | 1 | 1000082710 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-RADTR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-RADTR90003977
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Aftercooler | 2027-07-22 | 2027-07-22 | 6 hrs | FY28 | 6 | 90004021 | 1 | 1000082709 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-AFTER | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-AFTER90004021
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Pump Drive | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 28 | 90003984 | 1 | 1000082711 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-ENGINE-PMPDR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-ENGINE-PMPDR90003984
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Differential | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 28 | 90003994 | 1 | 1000082717 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-FDRSYS-DIFFL | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-FDRSYS-DIFFL90003994
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Transmission Driveshaft | 2027-07-22 | 2027-07-22 | 7 hrs | FY28 | 13 | 90003993 | 1 | 1000082716 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-FDRSYS-DRSHT | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-FDRSYS-DRSHT90003993
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Final Drive LH | 2027-07-22 | 2027-07-22 | 14 hrs | FY28 | 26 | 90003995 | 1 | 1000082722 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE-FDRLH | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE-FDRLH90003995
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Final Drive RH | 2027-07-22 | 2027-07-22 | 14 hrs | FY28 | 26 | 90007346 | 1 | 1000082723 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE-FDRRH | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE-FDRRH90007346
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Suspension Cylinder LHF | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 28 | 90004013 | 1 | 1000082744 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYLF | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYLF90004013
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Suspension Cylinder LHR | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 28 | 90004014 | 1 | 1000082746 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYLR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYLR90004014
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Suspension Cylinder RHF | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 28 | 90004013 | 1 | 1000082745 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYRF | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYRF90004013
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Suspension Cylinder RHR | 2027-07-22 | 2027-07-22 | 16 hrs | FY28 | 28 | 90004014 | 1 | 1000082747 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYRR | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYRR90004014
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Transmission | 2027-07-22 | 2027-07-23 | 28 hrs | FY28 | 52 | 90003988 | 1 | 1000082713 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-TRNSYS-TRANS | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-TRNSYS-TRANS90003988
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Transmission Oil Cooler | 2027-07-22 | 2027-07-22 | 8 hrs | FY28 | 8 | 90003992 | 1 | 1000082748 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-TRNSYS-TROLC | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-TRNSYS-TROLC90003992
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl TC-Park Brake-Scavenge Pump | 2027-07-22 | 2027-07-22 | 6 hrs | FY28 | 6 | 90003990 | 1 | 1000082728 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP-TCCPP | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP-TCCPP90003990
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Transmission Pump | 2027-07-22 | 2027-07-22 | 6 hrs | FY28 | 6 | 90003991 | 1 | 1000082715 | 22.07.2027 | 10000 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP-TMCPP | 4200 | 53807 | 260 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP-TMCPP90003991
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Torque Converter | 2027-07-22 | 2027-07-22 | 14 hrs | FY28 | 26 | 90003987 | 1 | 1000082712 | 22.07.2027 | 20000 | CLB-MP-SUPP-PM0006-TRNSYS-TRQUE | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-TRNSYS-TRQUE90003987
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Transmission | 2027-07-26 | 2027-07-26 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000035155 | 26.07.2027 | 11000 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP | 7500 | 92002 | 14699 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Pump Hoist & Brake | 2027-07-27 | 2027-07-27 | 10 hrs | FY28 | 10 | 90003113 | 1 | 1000034291 | 27.07.2027 | 22000 | CLB-MP-HAUL-DT166 -HYDSYS-HOPMP | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Steering HMU | 2027-07-27 | 2027-07-27 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000036000 | 27.07.2027 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STHMU | 7500 | 86259 | 22691 | CLB-MP-HAUL-DT197 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Cyl Steering LH | 2027-07-28 | 2027-07-28 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035061 | 28.07.2027 | 15000 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYL | 7500 | 89560 | 7664 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Pump Transmission | 2027-07-28 | 2027-07-28 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034048 | 28.07.2027 | 11000 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TMCPP | 7500 | 83473 | 3577 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Hyd Pump Steering Main | 2027-07-28 | 2027-07-28 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000034783 | 28.07.2027 | 15000 | CLB-MP-HAUL-DT175 -STRSYS-STPMP | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Steering HMU | 2027-07-28 | 2027-07-28 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000034784 | 28.07.2027 | 15000 | CLB-MP-HAUL-DT175 -STRSYS-STHMU | 7500 | 82722 | 21106 | CLB-MP-HAUL-DT175 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Cyl Steering RH | 2027-07-28 | 2027-07-28 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000034786 | 28.07.2027 | 15000 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Steering Ball Studs | 2027-07-28 | 2027-07-29 | 19 hrs | FY28 | 35 | 90038356 | A1 | 1000385422 | 28.07.2027 | 15000 | CLB-MP-HAUL-DT175 -STRSYS-STLTR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -STRSYS-STLTR90038356
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Suspension Cylinder RHR | 2027-07-29 | 2027-07-29 | 16 hrs | FY28 | 28 | 90004014 | 1 | 1000044550 | 29.07.2027 | 20000 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYRR | 5000 | 64118 | 14683 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYRR90004014
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Engine Midlife complete | 2027-07-31 | 2027-08-04 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156523 | 31.07.2027 | 11000 | CLB-MP-HAUL-DT166 -ENGINE | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Midlife Valve Set - Adjust | 2027-07-31 | 2027-07-31 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390890 | 31.07.2027 | 11000 | CLB-MP-HAUL-DT166 -ENGINE | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Hoist LH | 2027-07-31 | 2027-08-01 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035715 | 31.07.2027 | 28000 | CLB-MP-HAUL-DT192 -HYDSYS-HOCYL-HCYLL | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Hoist RH | 2027-07-31 | 2027-08-01 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000035716 | 31.07.2027 | 28000 | CLB-MP-HAUL-DT192 -HYDSYS-HOCYL-HCYLR | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Final Drive LH | 2027-07-31 | 2027-08-01 | 30 hrs | FY28 | 56 | 90003099 | 1 | 1000034330 | 31.07.2027 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-FDRVE-FDRLH | 7500 | 83303 | 14525 | CLB-MP-HAUL-DT167 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Final Drive RH | 2027-07-31 | 2027-08-01 | 30 hrs | FY28 | 56 | 90003100 | 1 | 1000034331 | 31.07.2027 | 22000 | CLB-MP-HAUL-DT167 -FDRSYS-FDRVE-FDRRH | 7500 | 83303 | 14525 | CLB-MP-HAUL-DT167 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Cyl Steering LH | 2027-08-01 | 2027-08-01 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000150588 | 01.08.2027 | 15000 | CLB-MP-HAUL-DT224 -STRSYS-STRCY-STCYL | 7500 | 49737 | 7573 | CLB-MP-HAUL-DT224 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Steering Link & Arm Rebush | 2027-08-02 | 2027-08-03 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385417 | 02.08.2027 | 30000 | CLB-MP-HAUL-DT172 -STRSYS-STLTR | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Drive Line Axle LH | 2027-08-02 | 2027-08-02 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123517 | 02.08.2027 | 30000 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX-AXLLH | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Drive Line Axle RH | 2027-08-02 | 2027-08-02 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123578 | 02.08.2027 | 30000 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX-AXLRH | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Cyl Steering RH | 2027-08-02 | 2027-08-02 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000150589 | 02.08.2027 | 15000 | CLB-MP-HAUL-DT224 -STRSYS-STRCY-STCYR | 7500 | 49737 | 7563 | CLB-MP-HAUL-DT224 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Service Air Conditioner | 2027-08-02 | 2027-08-02 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160390 | 02.08.2027 | 5500 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-AIRCN | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Midlife Valve Set - Adjust | 2027-08-03 | 2027-08-03 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390951 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -ENGINE | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Engine Midlife complete | 2027-08-03 | 2027-08-07 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156859 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -ENGINE | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Pump Drive Driveshaft Unis | 2027-08-03 | 2027-08-03 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035395 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR-DRSHT | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Pump Transmission | 2027-08-03 | 2027-08-03 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000035396 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TMCPP | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Pump Brake Control | 2027-08-03 | 2027-08-03 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000035407 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -BRKSYS-HYFPP | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Service Suspension Cylinders | 2027-08-03 | 2027-08-03 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106896 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Brake Relay Valve | 2027-08-03 | 2027-08-03 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078724 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -BRKSYS-BRVRL | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Spiders Transmission Driveshaft | 2027-08-03 | 2027-08-03 | 4 hrs | FY28 | 8 | 90017135 | 1 | 1000154416 | 03.08.2027 | 11000 | CLB-MP-HAUL-DT187 -FDRSYS-DRSHT-UNVSL | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 1Y Air Tank LH External Inspect | 2027-08-04 | 2027-08-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389442 | 04.08.2027 | 12 Monthly | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH | 7500 | 85995 | 85995 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 1Y Air Tank RH External Inspect | 2027-08-04 | 2027-08-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389444 | 04.08.2027 | 12 Monthly | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH | 7500 | 85995 | 85995 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Control Cabinet Coolant | 2027-08-05 | 2027-08-05 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000349082 | 05.08.2027 | 15000 | CLB-MP-HAUL-DT5448-ELCTHV-HVCAB-COOLR | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Brake Wheel RH | 2027-08-05 | 2027-08-06 | 33 hrs | FY28 | 61 | 90003105 | 2 | 1000150583 | 05.08.2027 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-AXLES-HUBRH | 7500 | 49737 | 14457 | CLB-MP-HAUL-DT224 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Cyl Suspension RHF | 2027-08-05 | 2027-08-06 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000150604 | 05.08.2027 | 22000 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYRF | 7500 | 49737 | 14457 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYRF90003121
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Overhaul Air Conditioner 24M | 2027-08-05 | 2027-08-07 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000361764 | 05.08.2027 | 24 Monthly | CLB-MP-HAUL-DT5473-STRUCT-CABIN-AIRCN | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Brake Wheel LH | 2027-08-06 | 2027-08-07 | 32 hrs | FY28 | 38 | 90003104 | 2 | 1000034115 | 06.08.2027 | 22000 | CLB-MP-HAUL-DT163 -STRUCT-AXLES-HUBLH | 7500 | 81237 | 14273 | CLB-MP-HAUL-DT163 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Hyd Pump Steering Main | 2027-08-06 | 2027-08-06 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000034396 | 06.08.2027 | 15000 | CLB-MP-HAUL-DT168 -STRSYS-STPMP | 7500 | 93142 | 7536 | CLB-MP-HAUL-DT168 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Steering HMU | 2027-08-06 | 2027-08-06 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000034397 | 06.08.2027 | 15000 | CLB-MP-HAUL-DT168 -STRSYS-STHMU | 7500 | 93142 | 7534 | CLB-MP-HAUL-DT168 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Cyl Steering LH | 2027-08-06 | 2027-08-06 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000034398 | 06.08.2027 | 15000 | CLB-MP-HAUL-DT168 -STRSYS-STRCY-STCYL | 7500 | 93142 | 7536 | CLB-MP-HAUL-DT168 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Cyl Steering RH | 2027-08-06 | 2027-08-06 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000034399 | 06.08.2027 | 15000 | CLB-MP-HAUL-DT168 -STRSYS-STRCY-STCYR | 7500 | 93142 | 7536 | CLB-MP-HAUL-DT168 -STRSYS-STRCY-STCYR90003111
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Control Cabinet Coolant | 2027-08-07 | 2027-08-07 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000349126 | 07.08.2027 | 15000 | CLB-MP-HAUL-DT5449-ELCTHV-HVCAB-COOLR | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Pump Drive Driveshaft Unis | 2027-08-07 | 2027-08-07 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000034548 | 07.08.2027 | 11000 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR-DRSHT | 7500 | 90182 | 3445 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Pump Transmission | 2027-08-07 | 2027-08-07 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000116269 | 07.08.2027 | 11000 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TMCPP | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Pump Brake Control | 2027-08-07 | 2027-08-07 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000034560 | 07.08.2027 | 11000 | CLB-MP-HAUL-DT171 -BRKSYS-HYFPP | 7500 | 90182 | 15607 | CLB-MP-HAUL-DT171 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Brake Relay Valve | 2027-08-07 | 2027-08-07 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078496 | 07.08.2027 | 11000 | CLB-MP-HAUL-DT171 -BRKSYS-BRVRL | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -BRKSYS-BRVRL90009877
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Seat Operator | 2027-08-08 | 2027-08-08 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000349671 | 08.08.2027 | 14000 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-SEATS | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 1Y Air Tank LH External Inspect | 2027-08-08 | 2027-08-08 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389446 | 08.08.2027 | 12 Monthly | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH | 7500 | 88415 | 16378 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 1Y Air Tank RH External Inspect | 2027-08-08 | 2027-08-08 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389448 | 08.08.2027 | 12 Monthly | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH | 7500 | 88415 | 16378 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Brake Slack Adjuster Front | 2027-08-08 | 2027-08-08 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072232 | 08.08.2027 | 18000 | CLB-MP-HAUL-DT174 -BRKSYS-SLACK-SLACF | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Brake Slack Adjuster Rear | 2027-08-08 | 2027-08-08 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072270 | 08.08.2027 | 18000 | CLB-MP-HAUL-DT174 -BRKSYS-SLACK-SLACR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl PTO Uni's | 2027-08-08 | 2027-08-08 | 4 hrs | FY28 | 4 | 90031093 | A1 | 1000307807 | 08.08.2027 | 5000 | CLB-MP-SUPP-WC014 -ENGINE-PMPDR-DRSHT | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -ENGINE-PMPDR-DRSHT90031093
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Overhaul Air Conditioner 24M | 2027-08-08 | 2027-08-10 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000361811 | 08.08.2027 | 24 Monthly | CLB-MP-HAUL-DT5474-STRUCT-CABIN-AIRCN | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 1Y Air Tank LH External Inspect | 2027-08-10 | 2027-08-10 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389462 | 10.08.2027 | 12 Monthly | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH | 7500 | 51345 | 51345 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 1Y Air Tank RH External Inspect | 2027-08-10 | 2027-08-10 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389464 | 10.08.2027 | 12 Monthly | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH | 7500 | 51345 | 51345 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Overhaul Air Conditioner 24M | 2027-08-10 | 2027-08-12 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000326385 | 10.08.2027 | 24 Monthly | CLB-MP-HAUL-DT5417-STRUCT-CABIN-AIRCN | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Differential | 2027-08-11 | 2027-08-13 | 44 hrs | FY28 | 66 | 90003098 | 1 | 1000035697 | 11.08.2027 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-DIFFL | 7500 | 91174 | 14420 | CLB-MP-HAUL-DT192 -FDRSYS-DIFFL90003098
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 1Y Air Tank External Inspect | 2027-08-11 | 2027-08-11 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389214 | 11.08.2027 | 12 Monthly | CLB-MP-SUPP-WC012 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC012 -PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Drive Line Axle LH | 2027-08-12 | 2027-08-12 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123530 | 12.08.2027 | 30000 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX-AXLLH | 7500 | 92088 | 22308 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Drive Line Axle RH | 2027-08-12 | 2027-08-12 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123591 | 12.08.2027 | 30000 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX-AXLRH | 7500 | 92088 | 22308 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Engine Pump Drive | 2027-08-12 | 2027-08-13 | 32 hrs | FY28 | 62 | 90003089 | 1 | 1000034545 | 12.08.2027 | 22000 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR | 7500 | 90182 | 14363 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR90003089
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Pump Brake Control | 2027-08-13 | 2027-08-13 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000034725 | 13.08.2027 | 11000 | CLB-MP-HAUL-DT174 -BRKSYS-HYFPP | 7500 | 83749 | 14831 | CLB-MP-HAUL-DT174 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Service Air Conditioner | 2027-08-15 | 2027-08-15 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160383 | 15.08.2027 | 5500 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-AIRCN | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Overhaul Air Conditioner 24M | 2027-08-15 | 2027-08-17 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000362639 | 15.08.2027 | 24 Monthly | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN90029460
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering HMU | 2027-08-17 | 2027-08-17 | 8 hrs | FY28 | 8 | 90004004 | 1 | 1000221756 | 17.08.2027 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STHMU | 5000 | 17738 | 9808 | CLB-MP-SUPP-WC3108-STRSYS-STHMU90004004
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Overhaul Air Conditioner 24M | 2027-08-17 | 2027-08-19 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000362684 | 17.08.2027 | 24 Monthly | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Control Cabinet Coolant | 2027-08-18 | 2027-08-18 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000349969 | 18.08.2027 | 15000 | CLB-MP-HAUL-DT5453-ELCTHV-HVCAB-COOLR | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Control Cabinet Coolant | 2027-08-18 | 2027-08-18 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000349627 | 18.08.2027 | 15000 | CLB-MP-HAUL-DT5451-ELCTHV-HVCAB-COOLR | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Radiator Engine Cooling | 2027-08-20 | 2027-08-22 | 58 hrs | FY28 | 91 | 90003562 | 1 | 1000150660 | 20.08.2027 | 22000 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-RADTR | 7400 | 51346 | 28044 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-RADTR90003562
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 1Y Air Tank External Inspect | 2027-08-20 | 2027-08-20 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389216 | 20.08.2027 | 12 Monthly | CLB-MP-SUPP-WC013 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC013 -PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Hyd Pump Steering Main | 2027-08-21 | 2027-08-21 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000036181 | 21.08.2027 | 15000 | CLB-MP-HAUL-DT200 -STRSYS-STPMP | 7500 | 92548 | 7112 | CLB-MP-HAUL-DT200 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Steering RH | 2027-08-21 | 2027-08-21 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000036184 | 21.08.2027 | 15000 | CLB-MP-HAUL-DT200 -STRSYS-STRCY-STCYR | 7500 | 92548 | 7112 | CLB-MP-HAUL-DT200 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Steering Link & Arm Rebush | 2027-08-21 | 2027-08-22 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385435 | 21.08.2027 | 30000 | CLB-MP-HAUL-DT181 -STRSYS-STLTR | 7500 | 83441 | 22176 | CLB-MP-HAUL-DT181 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Radiator Engine Cooling | 2027-08-21 | 2027-08-23 | 55 hrs | FY28 | 85 | 90003081 | 1 | 1000034653 | 21.08.2027 | 22000 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-RADTR | 7400 | 82651 | 34724 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-RADTR90003081
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Brake Oil Cooler Front | 2027-08-25 | 2027-08-25 | 5 hrs | FY28 | 5 | 90003108 | 1 | 1000080292 | 25.08.2027 | 22000 | CLB-MP-HAUL-DT188 -BRKSYS-BROCO-BROCF | 7500 | 83931 | 14100 | CLB-MP-HAUL-DT188 -BRKSYS-BROCO-BROCF90003108
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Brake Slack Adjuster Front | 2027-08-26 | 2027-08-26 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072239 | 26.08.2027 | 18000 | CLB-MP-HAUL-DT181 -BRKSYS-SLACK-SLACF | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Brake Slack Adjuster Rear | 2027-08-26 | 2027-08-26 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072277 | 26.08.2027 | 18000 | CLB-MP-HAUL-DT181 -BRKSYS-SLACK-SLACR | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Water Cannon | 2027-08-29 | 2027-08-29 | 12 hrs | FY28 | 24 | 90015535 | 1 | 1000221778 | 29.08.2027 | 12 Monthly | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | 5000 | 17738 | 8813 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON90015535
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Cyl Hoist RH | 2027-08-29 | 2027-08-30 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000034790 | 29.08.2027 | 28000 | CLB-MP-HAUL-DT175 -HYDSYS-HOCYL-HCYLR | 7500 | 82722 | 20002 | CLB-MP-HAUL-DT175 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Rotochamber Front | 2027-08-29 | 2027-08-29 | 5 hrs | FY28 | 5 | 90009308 | 1 | 1000072405 | 29.08.2027 | 22000 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTFR | 7500 | 82554 | 14000 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Air Dryer | 2027-08-30 | 2027-08-30 | 7 hrs | FY28 | 14 | 90003115 | 1 | 1000036189 | 30.08.2027 | 22000 | CLB-MP-HAUL-DT200 -PNEUMC-AIRDR | 7500 | 92548 | 13887 | CLB-MP-HAUL-DT200 -PNEUMC-AIRDR90003115
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Control Cabinet Coolant | 2027-09-01 | 2027-09-01 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000350419 | 01.09.2027 | 15000 | CLB-MP-HAUL-DT5454-ELCTHV-HVCAB-COOLR | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Drive Line Axle LH | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123528 | 01.09.2027 | 30000 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX-AXLLH | 7500 | 90364 | 21853 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Drive Line Axle RH | 2027-09-01 | 2027-09-01 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123589 | 01.09.2027 | 30000 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX-AXLRH | 7500 | 90364 | 21853 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Steering HMU | 2027-09-01 | 2027-09-01 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000034509 | 01.09.2027 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STHMU | 7500 | 91119 | 29788 | CLB-MP-HAUL-DT170 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Drive Line Axle LH | 2027-09-03 | 2027-09-03 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123515 | 03.09.2027 | 30000 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX-AXLLH | 7500 | 91119 | 21125 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Drive Line Axle RH | 2027-09-03 | 2027-09-03 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123576 | 03.09.2027 | 30000 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX-AXLRH | 7500 | 91119 | 21125 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Service Suspension Cylinders | 2027-09-03 | 2027-09-03 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106889 | 03.09.2027 | 11000 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Service Suspension Cylinders | 2027-09-05 | 2027-09-05 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106888 | 05.09.2027 | 11000 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN | 7500 | 84079 | 11363 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Service Air Conditioner | 2027-09-07 | 2027-09-07 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160370 | 07.09.2027 | 5500 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-AIRCN | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Radiator Engine Cooling | 2027-09-08 | 2027-09-10 | 55 hrs | FY28 | 85 | 90003081 | 1 | 1000036161 | 08.09.2027 | 22000 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-RADTR | 7400 | 92548 | 29740 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-RADTR90003081
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Steering Ball Studs | 2027-09-09 | 2027-09-10 | 19 hrs | FY28 | 35 | 90038356 | A1 | 1000385468 | 09.09.2027 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STLTR | 7500 | 88680 | 6816 | CLB-MP-HAUL-DT198 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Pump Drive Driveshaft Unis | 2027-09-10 | 2027-09-10 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000034436 | 10.09.2027 | 11000 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR-DRSHT | 7500 | 93408 | 12173 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR-DRSHT90009874
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Control Cabinet Coolant | 2027-09-11 | 2027-09-11 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000347026 | 11.09.2027 | 15000 | CLB-MP-HAUL-DT5445-ELCTHV-HVCAB-COOLR | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Hyd Pump Steering Main | 2027-09-11 | 2027-09-11 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000034508 | 11.09.2027 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STPMP | 7500 | 91119 | 6569 | CLB-MP-HAUL-DT170 -STRSYS-STPMP90003109
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 1Y Air Tank External Inspect | 2027-09-11 | 2027-09-11 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389220 | 11.09.2027 | 12 Monthly | CLB-MP-SUPP-WC015 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC015 -PNEUMC-PNTNK90038749
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Control Cabinet Coolant | 2027-09-12 | 2027-09-12 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000350463 | 12.09.2027 | 15000 | CLB-MP-HAUL-DT5455-ELCTHV-HVCAB-COOLR | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-ELCTHV-HVCAB-COOLR90033128
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 1Y Air Tank External Inspect | 2027-09-12 | 2027-09-12 | 1.5 hrs | FY28 | 1.5 | 90038749 | A1 | 1000389222 | 12.09.2027 | 12 Monthly | CLB-MP-SUPP-WC3108-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC3108-PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Steering HMU | 2027-09-12 | 2027-09-12 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035115 | 12.09.2027 | 15000 | CLB-MP-HAUL-DT181 -STRSYS-STHMU | 7500 | 83441 | 22176 | CLB-MP-HAUL-DT181 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Pump Transmission | 2027-09-12 | 2027-09-12 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034437 | 12.09.2027 | 11000 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TMCPP | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Pump Brake Control | 2027-09-12 | 2027-09-12 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000034448 | 12.09.2027 | 11000 | CLB-MP-HAUL-DT169 -BRKSYS-HYFPP | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Brake Relay Valve | 2027-09-12 | 2027-09-12 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078458 | 12.09.2027 | 11000 | CLB-MP-HAUL-DT169 -BRKSYS-BRVRL | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -BRKSYS-BRVRL90009877
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Overhaul Air Conditioner 24M | 2027-09-12 | 2027-09-14 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000365676 | 12.09.2027 | 24 Monthly | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Overhaul Air Conditioner 24M | 2027-09-12 | 2027-09-14 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000365626 | 12.09.2027 | 24 Monthly | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Cyl Steering RH | 2027-09-14 | 2027-09-14 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000034896 | 14.09.2027 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYR | 7500 | 81791 | 6637 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Steering HMU | 2027-09-16 | 2027-09-16 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035710 | 16.09.2027 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STHMU | 7500 | 91174 | 27983 | CLB-MP-HAUL-DT192 -STRSYS-STHMU90003110
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Water Cannon & Valves Repl | 2027-09-17 | 2027-09-18 | 24 hrs | FY28 | 48 | 90033662 | A1 | 1000338793 | 17.09.2027 | 24 Monthly | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON90033662
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Seat Operator | 2027-09-18 | 2027-09-18 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000346280 | 18.09.2027 | 14000 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-SEATS | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Brake Slack Adjuster Front | 2027-09-19 | 2027-09-19 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072228 | 19.09.2027 | 18000 | CLB-MP-HAUL-DT170 -BRKSYS-SLACK-SLACF | 7500 | 91119 | 9406 | CLB-MP-HAUL-DT170 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Brake Slack Adjuster Rear | 2027-09-19 | 2027-09-19 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072266 | 19.09.2027 | 18000 | CLB-MP-HAUL-DT170 -BRKSYS-SLACK-SLACR | 7500 | 91119 | 9406 | CLB-MP-HAUL-DT170 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Pump Hoist & Brake | 2027-09-19 | 2027-09-19 | 10 hrs | FY28 | 10 | 90003113 | 1 | 1000034236 | 19.09.2027 | 22000 | CLB-MP-HAUL-DT165 -HYDSYS-HOPMP | 7500 | 78966 | 6162 | CLB-MP-HAUL-DT165 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Service Suspension Cylinders | 2027-09-20 | 2027-09-20 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106878 | 20.09.2027 | 11000 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN | 7500 | 93410 | 23335 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Steering HMU | 2027-09-21 | 2027-09-21 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000036058 | 21.09.2027 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STHMU | 7500 | 88680 | 23807 | CLB-MP-HAUL-DT198 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Brake Slack Adjuster Front | 2027-09-21 | 2027-09-21 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072225 | 21.09.2027 | 18000 | CLB-MP-HAUL-DT167 -BRKSYS-SLACK-SLACF | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Brake Slack Adjuster Rear | 2027-09-21 | 2027-09-21 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072263 | 21.09.2027 | 18000 | CLB-MP-HAUL-DT167 -BRKSYS-SLACK-SLACR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -BRKSYS-SLACK-SLACR90009307
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 1Y Air Tank External Inspect | 2027-09-21 | 2027-09-21 | 1.5 hrs | FY28 | 1.5 | 90038755 | A1 | 1000389470 | 21.09.2027 | 12 Monthly | CLB-MP-SUPP-PM0004-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-PM0004-PNEUMC-PNTNK90038755
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 1Y Air Tank LH External Inspect | 2027-09-23 | 2027-09-23 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389458 | 23.09.2027 | 12 Monthly | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH | 7500 | 49299 | 49299 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 1Y Air Tank RH External Inspect | 2027-09-23 | 2027-09-23 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389460 | 23.09.2027 | 12 Monthly | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH | 7500 | 49299 | 49299 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Ovhl Axle A Frame | 2027-09-27 | 2027-09-28 | 36 hrs | FY28 | 60 | 90015390 | 1 | 1000130650 | 27.09.2027 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-AFRME | 7500 | 84079 | 36609 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Ovhl Axle Housing Dogbone | 2027-09-27 | 2027-09-28 | 22 hrs | FY28 | 42 | 90003118 | 1 | 1000035014 | 27.09.2027 | 22000 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-TAGLK | 7500 | 84079 | 13410 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Drive Line Axle LH | 2027-09-29 | 2027-09-29 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123527 | 29.09.2027 | 30000 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX-AXLLH | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Drive Line Axle RH | 2027-09-29 | 2027-09-29 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123588 | 29.09.2027 | 30000 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX-AXLRH | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Cyl Steering LH | 2027-10-01 | 2027-10-01 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035412 | 01.10.2027 | 15000 | CLB-MP-HAUL-DT187 -STRSYS-STRCY-STCYL | 7500 | 93170 | 6296 | CLB-MP-HAUL-DT187 -STRSYS-STRCY-STCYL90003111
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Control Cabinet Coolant | 2027-10-03 | 2027-10-03 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000349678 | 03.10.2027 | 15000 | CLB-MP-HAUL-DT5450-ELCTHV-HVCAB-COOLR | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-ELCTHV-HVCAB-COOLR90033128
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Steering HMU | 2027-10-03 | 2027-10-03 | 8 hrs | FY28 | 8 | 90004004 | 1 | 1000044794 | 03.10.2027 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STHMU | 5000 | 67897 | 9224 | CLB-MP-SUPP-WC015 -STRSYS-STHMU90004004
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Tyre Sense Battery | 2027-10-04 | 2027-10-04 | 2 hrs | FY28 | 2 | 90017022 | 1 | 1000163962 | 04.10.2027 | 24 Monthly | CLB-MP-HAUL-DT187 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT187 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Brake Slack Adjuster Front | 2027-10-05 | 2027-10-05 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072230 | 05.10.2027 | 18000 | CLB-MP-HAUL-DT172 -BRKSYS-SLACK-SLACF | 7500 | 92351 | 9073 | CLB-MP-HAUL-DT172 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Brake Slack Adjuster Rear | 2027-10-05 | 2027-10-05 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072268 | 05.10.2027 | 18000 | CLB-MP-HAUL-DT172 -BRKSYS-SLACK-SLACR | 7500 | 92351 | 9073 | CLB-MP-HAUL-DT172 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Radiator Engine Cooling | 2027-10-07 | 2027-10-09 | 55 hrs | FY28 | 85 | 90003081 | 1 | 1000034763 | 07.10.2027 | 22000 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-RADTR | 7500 | 82722 | 13194 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-RADTR90003081
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Final Drive RH | 2027-10-07 | 2027-10-07 | 14 hrs | FY28 | 26 | 90007346 | 1 | 1000044526 | 07.10.2027 | 20000 | CLB-MP-SUPP-WC011 -FDRSYS-FDRVE-FDRRH | 5000 | 64118 | 13726 | CLB-MP-SUPP-WC011 -FDRSYS-FDRVE-FDRRH90007346
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Steering HMU | 2027-10-08 | 2027-10-08 | 4 hrs | FY28 | 4 | 90013191 | A1 | 1000110259 | 08.10.2027 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STHMU | 3500 | 91736 | 10879 | CLB-MP-SUPP-PM0004-STRSYS-STHMU90013191
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Cyl Steering LH | 2027-10-08 | 2027-10-08 | 6 hrs | FY28 | 12 | 90013194 | A1 | 1000110261 | 08.10.2027 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STRCY-STCYL | 3500 | 91736 | 19327 | CLB-MP-SUPP-PM0004-STRSYS-STRCY-STCYL90013194
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Cyl Steering RH | 2027-10-08 | 2027-10-08 | 6 hrs | FY28 | 12 | 90013194 | A1 | 1000110262 | 08.10.2027 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STRCY-STCYR | 3500 | 91736 | 19327 | CLB-MP-SUPP-PM0004-STRSYS-STRCY-STCYR90013194
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Valve Steering | 2027-10-08 | 2027-10-08 | 6 hrs | FY28 | 6 | 90013192 | A1 | 1000110260 | 08.10.2027 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STVLV | 3500 | 91736 | 10879 | CLB-MP-SUPP-PM0004-STRSYS-STVLV90013192
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Service Air Conditioner | 2027-10-09 | 2027-10-09 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160381 | 09.10.2027 | 5500 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-AIRCN | 7500 | 82722 | 14586 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Drive Shaft Transmission | 2027-10-10 | 2027-10-10 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154385 | 10.10.2027 | 22000 | CLB-MP-HAUL-DT172 -FDRSYS-DRSHT | 7500 | 92351 | 12975 | CLB-MP-HAUL-DT172 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Pump Hoist & Brake | 2027-10-10 | 2027-10-10 | 10 hrs | FY28 | 10 | 90003113 | 1 | 1000034623 | 10.10.2027 | 22000 | CLB-MP-HAUL-DT172 -HYDSYS-HOPMP | 7500 | 92351 | 12975 | CLB-MP-HAUL-DT172 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Suspension RHR | 2027-10-12 | 2027-10-13 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000035726 | 12.10.2027 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYRR | 7500 | 91174 | 13039 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Pump Drive Driveshaft Unis | 2027-10-13 | 2027-10-13 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000034271 | 13.10.2027 | 11000 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR-DRSHT | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Pump Transmission | 2027-10-13 | 2027-10-13 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034272 | 13.10.2027 | 11000 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TMCPP | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Pump Brake Control | 2027-10-13 | 2027-10-13 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000034283 | 13.10.2027 | 11000 | CLB-MP-HAUL-DT166 -BRKSYS-HYFPP | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Brake Relay Valve | 2027-10-13 | 2027-10-13 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078401 | 13.10.2027 | 11000 | CLB-MP-HAUL-DT166 -BRKSYS-BRVRL | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Service Suspension Cylinders | 2027-10-14 | 2027-10-14 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106874 | 14.10.2027 | 11000 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Brake Slack Adjuster Front | 2027-10-14 | 2027-10-14 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072242 | 14.10.2027 | 18000 | CLB-MP-HAUL-DT184 -BRKSYS-SLACK-SLACF | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Brake Slack Adjuster Rear | 2027-10-14 | 2027-10-14 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072280 | 14.10.2027 | 18000 | CLB-MP-HAUL-DT184 -BRKSYS-SLACK-SLACR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Transmission | 2027-10-16 | 2027-10-17 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000034492 | 16.10.2027 | 22000 | CLB-MP-HAUL-DT170 -TRNSYS-TRANS | 7500 | 91119 | 12852 | CLB-MP-HAUL-DT170 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Pump Transmission | 2027-10-16 | 2027-10-16 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034494 | 16.10.2027 | 11000 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP | 7500 | 91119 | 12852 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Transmission Oil Cooler | 2027-10-16 | 2027-10-16 | 13 hrs | FY28 | 13 | 90003532 | 1 | 1000040979 | 16.10.2027 | 22000 | CLB-MP-HAUL-DT170 -TRNSYS-TROLC | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Hyd Pump Steering Main | 2027-10-19 | 2027-10-19 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035825 | 19.10.2027 | 15000 | CLB-MP-HAUL-DT194 -STRSYS-STPMP | 7500 | 86451 | 21821 | CLB-MP-HAUL-DT194 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Cyl Steering LH | 2027-10-19 | 2027-10-19 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035827 | 19.10.2027 | 15000 | CLB-MP-HAUL-DT194 -STRSYS-STRCY-STCYL | 7500 | 86451 | 5774 | CLB-MP-HAUL-DT194 -STRSYS-STRCY-STCYL90003111
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Water Cannon Inspect | 2027-10-19 | 2027-10-19 | 3 hrs | FY28 | 3 | 90033661 | A1 | 1000338796 | 19.10.2027 | 6 Monthly | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Service Air Conditioner | 2027-10-22 | 2027-10-22 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160391 | 22.10.2027 | 5500 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN | 7500 | 92088 | 7001 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Cyl Steering LH | 2027-10-26 | 2027-10-26 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035226 | 26.10.2027 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STRCY-STCYL | 7500 | 90364 | 5723 | CLB-MP-HAUL-DT183 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Service Air Conditioner | 2027-10-26 | 2027-10-26 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160389 | 26.10.2027 | 5500 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-AIRCN | 7500 | 90364 | 6327 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Brake Slack Adjuster Front | 2027-10-27 | 2027-10-27 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072235 | 27.10.2027 | 18000 | CLB-MP-HAUL-DT177 -BRKSYS-SLACK-SLACF | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Brake Slack Adjuster Rear | 2027-10-27 | 2027-10-27 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072273 | 27.10.2027 | 18000 | CLB-MP-HAUL-DT177 -BRKSYS-SLACK-SLACR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Hyd Pump Steering Main | 2027-10-27 | 2027-10-27 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035114 | 27.10.2027 | 15000 | CLB-MP-HAUL-DT181 -STRSYS-STPMP | 7500 | 83441 | 5808 | CLB-MP-HAUL-DT181 -STRSYS-STPMP90003109
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Seat Operator | 2027-10-31 | 2027-10-31 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000349715 | 31.10.2027 | 14000 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-SEATS | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Cyl Steering RH | 2027-10-31 | 2027-10-31 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000035006 | 31.10.2027 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYR | 7500 | 84079 | 5709 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Cyl Steering LH | 2027-11-01 | 2027-11-01 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035653 | 01.11.2027 | 15000 | CLB-MP-HAUL-DT191 -STRSYS-STRCY-STCYL | 7500 | 87047 | 5642 | CLB-MP-HAUL-DT191 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Cyl Steering RH | 2027-11-01 | 2027-11-01 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000035654 | 01.11.2027 | 15000 | CLB-MP-HAUL-DT191 -STRSYS-STRCY-STCYR | 7500 | 87047 | 5642 | CLB-MP-HAUL-DT191 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Steering Link & Arm Rebush | 2027-11-02 | 2027-11-03 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385439 | 02.11.2027 | 30000 | CLB-MP-HAUL-DT183 -STRSYS-STLTR | 7500 | 90364 | 20591 | CLB-MP-HAUL-DT183 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Pump Drive Driveshaft Unis | 2027-11-02 | 2027-11-02 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035099 | 02.11.2027 | 11000 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR-DRSHT | 7500 | 83441 | 15445 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Brake Slack Adjuster Front | 2027-11-02 | 2027-11-02 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072244 | 02.11.2027 | 18000 | CLB-MP-HAUL-DT186 -BRKSYS-SLACK-SLACF | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Brake Slack Adjuster Rear | 2027-11-02 | 2027-11-02 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072282 | 02.11.2027 | 18000 | CLB-MP-HAUL-DT186 -BRKSYS-SLACK-SLACR | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Engine Midlife complete | 2027-11-04 | 2027-11-06 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000346765 | 04.11.2027 | 17500 | CLB-MP-HAUL-DT5444-ENGINE | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Drive Line Axle LH | 2027-11-05 | 2027-11-05 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123537 | 05.11.2027 | 30000 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX-AXLLH | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Drive Line Axle RH | 2027-11-05 | 2027-11-05 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123598 | 05.11.2027 | 30000 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX-AXLRH | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Brake Relay Valve | 2027-11-05 | 2027-11-05 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078705 | 05.11.2027 | 11000 | CLB-MP-HAUL-DT186 -BRKSYS-BRVRL | 7500 | 89749 | 1586 | CLB-MP-HAUL-DT186 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Cyl Hoist LH | 2027-11-06 | 2027-11-07 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000034292 | 06.11.2027 | 28000 | CLB-MP-HAUL-DT166 -HYDSYS-HOCYL-HCYLL | 7500 | 95491 | 18595 | CLB-MP-HAUL-DT166 -HYDSYS-HOCYL-HCYLL90003114
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Air Drier and Tank | 2027-11-07 | 2027-11-07 | 12 hrs | FY28 | 24 | 90004010 | 1 | 1000044610 | 07.11.2027 | 9000 | CLB-MP-SUPP-WC012 -PNEUMC-AIRDR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -PNEUMC-AIRDR90004010
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Midlife Valve Set - Adjust | 2027-11-08 | 2027-11-08 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390944 | 08.11.2027 | 11000 | CLB-MP-HAUL-DT180 -ENGINE | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Engine Midlife complete | 2027-11-08 | 2027-11-12 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156747 | 08.11.2027 | 11000 | CLB-MP-HAUL-DT180 -ENGINE | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Drive Shaft Transmission | 2027-11-08 | 2027-11-08 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154401 | 08.11.2027 | 22000 | CLB-MP-HAUL-DT180 -FDRSYS-DRSHT | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -FDRSYS-DRSHT90017134
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Brake & Steering Manifold | 2027-11-08 | 2027-11-08 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000326643 | 08.11.2027 | 20000 | CLB-MP-HAUL-DT5419-BRKSYS-BRVLV | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Gear Cooler Motor & Pump | 2027-11-08 | 2027-11-08 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000326662 | 08.11.2027 | 20000 | CLB-MP-HAUL-DT5419-FDRSYS-GRSOC-OCPPM | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Pump Airconditioner Drive | 2027-11-08 | 2027-11-08 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000326642 | 08.11.2027 | 20000 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-ACPMP | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Coupling Drive Pump | 2027-11-08 | 2027-11-08 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000326647 | 08.11.2027 | 20000 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-HYDPC | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Valve Flow Amplifier | 2027-11-08 | 2027-11-08 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000326661 | 08.11.2027 | 20000 | CLB-MP-HAUL-DT5419-STRSYS-STVLV | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 1Y Air Tank LH External Inspect | 2027-11-10 | 2027-11-10 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389338 | 10.11.2027 | 12 Monthly | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH | 7500 | 90894 | 90894 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 1Y Air Tank RH External Inspect | 2027-11-10 | 2027-11-10 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389340 | 10.11.2027 | 12 Monthly | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH | 7500 | 90894 | 90894 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Engine Midlife complete | 2027-11-10 | 2027-11-14 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000157067 | 10.11.2027 | 11000 | CLB-MP-HAUL-DT200 -ENGINE | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Midlife Valve Set - Adjust | 2027-11-10 | 2027-11-10 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390984 | 10.11.2027 | 11000 | CLB-MP-HAUL-DT200 -ENGINE | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Spiders Transmission Driveshaft | 2027-11-10 | 2027-11-10 | 4 hrs | FY28 | 8 | 90017135 | 1 | 1000154442 | 10.11.2027 | 11000 | CLB-MP-HAUL-DT200 -FDRSYS-DRSHT-UNVSL | 7500 | 92548 | 12117 | CLB-MP-HAUL-DT200 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Service Air Conditioner | 2027-11-11 | 2027-11-11 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160401 | 11.11.2027 | 5500 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-AIRCN | 7500 | 82554 | 15352 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Engine Midlife complete | 2027-11-12 | 2027-11-14 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000300320 | 12.11.2027 | 17500 | CLB-MP-HAUL-DT5390-ENGINE | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Gear Cooler Motor & Pump | 2027-11-12 | 2027-11-12 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000314082 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-FDRSYS-GRSOC-OCPPM | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Brake & Steering Manifold | 2027-11-12 | 2027-11-12 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000314095 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-BRKSYS-BRVLV | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Valve Flow Amplifier | 2027-11-12 | 2027-11-12 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000314085 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-STRSYS-STVLV | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Steering LHS | 2027-11-12 | 2027-11-12 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000314088 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-STRSYS-STRCY-STCYL | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Steering RHS | 2027-11-12 | 2027-11-12 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000314089 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-STRSYS-STRCY-STCYR | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Pump Main Hydraulic | 2027-11-12 | 2027-11-12 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000314084 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-HYPMP | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Pump Airconditioner Drive | 2027-11-12 | 2027-11-12 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000314083 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-ACPMP | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Coupling Drive Pump | 2027-11-12 | 2027-11-12 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000314081 | 12.11.2027 | 20000 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-HYDPC | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-HYDPC90029361
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Pump Drive Driveshaft Unis | 2027-11-12 | 2027-11-12 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035044 | 12.11.2027 | 11000 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR-DRSHT | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Pump Brake Control | 2027-11-12 | 2027-11-12 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000035056 | 12.11.2027 | 11000 | CLB-MP-HAUL-DT180 -BRKSYS-HYFPP | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Brake Relay Valve | 2027-11-12 | 2027-11-12 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078629 | 12.11.2027 | 11000 | CLB-MP-HAUL-DT180 -BRKSYS-BRVRL | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Pump Drive Driveshaft Unis | 2027-11-12 | 2027-11-12 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035868 | 12.11.2027 | 11000 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR-DRSHT | 7500 | 82554 | 12514 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Differential | 2027-11-13 | 2027-11-15 | 44 hrs | FY28 | 66 | 90003098 | 1 | 1000034384 | 13.11.2027 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-DIFFL | 7500 | 93142 | 5860 | CLB-MP-HAUL-DT168 -FDRSYS-DIFFL90003098
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Control Cabinet Coolant | 2027-11-14 | 2027-11-14 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000346287 | 14.11.2027 | 15000 | CLB-MP-HAUL-DT5441-ELCTHV-HVCAB-COOLR | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Engine Midlife complete | 2027-11-14 | 2027-11-16 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000314536 | 14.11.2027 | 17500 | CLB-MP-HAUL-DT5411-ENGINE | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Brake & Steering Manifold | 2027-11-15 | 2027-11-15 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000326388 | 15.11.2027 | 20000 | CLB-MP-HAUL-DT5417-BRKSYS-BRVLV | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Gear Cooler Motor & Pump | 2027-11-15 | 2027-11-15 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000326407 | 15.11.2027 | 20000 | CLB-MP-HAUL-DT5417-FDRSYS-GRSOC-OCPPM | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Pump Airconditioner Drive | 2027-11-15 | 2027-11-15 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000326387 | 15.11.2027 | 20000 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-ACPMP | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Coupling Drive Pump | 2027-11-15 | 2027-11-15 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000326392 | 15.11.2027 | 20000 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-HYDPC | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Pump Main Hydraulic | 2027-11-15 | 2027-11-15 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000326415 | 15.11.2027 | 20000 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-HYPMP | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Valve Flow Amplifier | 2027-11-15 | 2027-11-15 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000326406 | 15.11.2027 | 20000 | CLB-MP-HAUL-DT5417-STRSYS-STVLV | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRSYS-STVLV90029367
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Steering System Hoses | 2027-11-16 | 2027-11-16 | 12 hrs | FY28 | 24 | 90013199 | A1 | 1000110266 | 16.11.2027 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STHLF | 3500 | 91736 | 25890 | CLB-MP-SUPP-PM0004-STRSYS-STHLF90013199
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Adjust Engine Valve Set | 2027-11-17 | 2027-11-17 | 6 hrs | FY28 | 6 | 90017451 | A1 | 1000290645 | 17.11.2027 | 3000 | CLB-MP-SUPP-SV021 -ENGINE | 3300 | 54098 | 5 | CLB-MP-SUPP-SV021 -ENGINE90017451
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Ovhl Axle A Frame | 2027-11-17 | 2027-11-18 | 36 hrs | FY28 | 60 | 90015390 | 1 | 1000130637 | 17.11.2027 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-AFRME | 7500 | 78966 | 30583 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Pump Brake Control | 2027-11-18 | 2027-11-18 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000034945 | 18.11.2027 | 11000 | CLB-MP-HAUL-DT178 -BRKSYS-HYFPP | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Brake Slack Adjuster Front | 2027-11-18 | 2027-11-18 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072223 | 18.11.2027 | 18000 | CLB-MP-HAUL-DT165 -BRKSYS-SLACK-SLACF | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Brake Slack Adjuster Rear | 2027-11-18 | 2027-11-18 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072261 | 18.11.2027 | 18000 | CLB-MP-HAUL-DT165 -BRKSYS-SLACK-SLACR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Engine Midlife complete | 2027-11-18 | 2027-11-20 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000346698 | 18.11.2027 | 17500 | CLB-MP-HAUL-DT5443-ENGINE | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Cyl Hoist RH | 2027-11-19 | 2027-11-20 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000035231 | 19.11.2027 | 28000 | CLB-MP-HAUL-DT183 -HYDSYS-HOCYL-HCYLR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Brake Slack Adjuster Front | 2027-11-19 | 2027-11-19 | 4 hrs | FY28 | 4 | 90009306 | 1 | 1000072221 | 19.11.2027 | 18000 | CLB-MP-HAUL-DT163 -BRKSYS-SLACK-SLACF | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Brake Slack Adjuster Rear | 2027-11-19 | 2027-11-19 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072259 | 19.11.2027 | 18000 | CLB-MP-HAUL-DT163 -BRKSYS-SLACK-SLACR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -BRKSYS-SLACK-SLACR90009307
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Cylinder Steering LH | 2027-11-21 | 2027-11-21 | 14 hrs | FY28 | 26 | 90003054 | A1 | 1000033994 | 21.11.2027 | 9000 | CLB-MP-SUPP-SV021 -STRSYS-STRCY-STCYL | 3300 | 54098 | 4488 | CLB-MP-SUPP-SV021 -STRSYS-STRCY-STCYL90003054
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Cylinder Steering RH | 2027-11-21 | 2027-11-21 | 14 hrs | FY28 | 26 | 90003054 | A1 | 1000033995 | 21.11.2027 | 9000 | CLB-MP-SUPP-SV021 -STRSYS-STRCY-STCYR | 3300 | 54098 | 4488 | CLB-MP-SUPP-SV021 -STRSYS-STRCY-STCYR90003054
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Brake Wheel RH | 2027-11-21 | 2027-11-22 | 33 hrs | FY28 | 61 | 90003105 | 2 | 1000034226 | 21.11.2027 | 22000 | CLB-MP-HAUL-DT165 -STRUCT-AXLES-HUBRH | 7500 | 78966 | 12262 | CLB-MP-HAUL-DT165 -STRUCT-AXLES-HUBRH90003105
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Engine Midlife complete | 2027-11-22 | 2027-11-24 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000346577 | 22.11.2027 | 17500 | CLB-MP-HAUL-DT5442-ENGINE | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-ENGINE90029500
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl TC-Park Brake-Scavenge Pump | 2027-11-23 | 2027-11-23 | 6 hrs | FY28 | 6 | 90003990 | 1 | 1000044595 | 23.11.2027 | 20000 | CLB-MP-SUPP-WC012 -TRNSYS-TRPMP-TCCPP | 5000 | 67273 | 13332 | CLB-MP-SUPP-WC012 -TRNSYS-TRPMP-TCCPP90003990
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Brake Relay Valve | 2027-11-25 | 2027-11-25 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078800 | 25.11.2027 | 11000 | CLB-MP-HAUL-DT192 -BRKSYS-BRVRL | 7500 | 91174 | 1097 | CLB-MP-HAUL-DT192 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Final Drive RH | 2027-11-25 | 2027-11-26 | 30 hrs | FY28 | 56 | 90003100 | 1 | 1000035214 | 25.11.2027 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-FDRVE-FDRRH | 7500 | 90364 | 12098 | CLB-MP-HAUL-DT183 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Cyl Suspension RHR | 2027-11-25 | 2027-11-26 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000034965 | 25.11.2027 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYRR | 7500 | 81600 | 12157 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Service Suspension Cylinders | 2027-11-25 | 2027-11-25 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106891 | 25.11.2027 | 11000 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN | 7500 | 92002 | 16119 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Pump Transmission | 2027-11-25 | 2027-11-25 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000035320 | 25.11.2027 | 11000 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP90003096
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Steering Link & Arm Rebush | 2027-11-25 | 2027-11-25 | 14 hrs | FY28 | 22 | 90004007 | 1 | 1000044733 | 25.11.2027 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STLTR | 5000 | 65823 | 7973 | CLB-MP-SUPP-WC014 -STRSYS-STLTR90004007
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl AOC Fan Motor | 2027-11-26 | 2027-11-26 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000036173 | 26.11.2027 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-MTFAN | 7500 | 92548 | 12117 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Rotochamber RHR | 2027-11-26 | 2027-11-26 | 5 hrs | FY28 | 5 | 90009309 | 1 | 1000072486 | 26.11.2027 | 22000 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTRR | 7500 | 92548 | 12116 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTRR90009309
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Gear Cooler Motor & Pump | 2027-11-27 | 2027-11-27 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000300362 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-FDRSYS-GRSOC-OCPPM | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Brake & Steering Manifold | 2027-11-27 | 2027-11-27 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000300375 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-BRKSYS-BRVLV | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Valve Flow Amplifier | 2027-11-27 | 2027-11-27 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000300365 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-STRSYS-STVLV | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Steering LHS | 2027-11-27 | 2027-11-27 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000300368 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-STRSYS-STRCY-STCYL | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Steering RHS | 2027-11-27 | 2027-11-27 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000300369 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-STRSYS-STRCY-STCYR | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Pump Main Hydraulic | 2027-11-27 | 2027-11-27 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000300364 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-HYPMP | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Pump Airconditioner Drive | 2027-11-27 | 2027-11-27 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000300363 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-ACPMP | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Coupling Drive Pump | 2027-11-27 | 2027-11-27 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000300361 | 27.11.2027 | 20000 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-HYDPC | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Engine Midlife complete | 2027-11-27 | 2027-11-29 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000347379 | 27.11.2027 | 17500 | CLB-MP-HAUL-DT5447-ENGINE | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Hyd Motor Axle Lube Rear | 2027-11-28 | 2027-11-28 | 9 hrs | FY28 | 9 | 90003101 | 1 | 1000035325 | 28.11.2027 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-HYM01 | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-HYM0190003101
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Torque Converter | 2027-11-29 | 2027-11-29 | 12 hrs | FY28 | 24 | 90013164 | A1 | 1000110234 | 29.11.2027 | 18000 | CLB-MP-SUPP-PM0004-TRNSYS-TRQUE | 3500 | 91736 | 13390 | CLB-MP-SUPP-PM0004-TRNSYS-TRQUE90013164
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Brake & Steering Manifold | 2027-11-29 | 2027-11-29 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000326479 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-BRKSYS-BRVLV | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Gear Cooler Motor & Pump | 2027-11-29 | 2027-11-29 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000326578 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-FDRSYS-GRSOC-OCPPM | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Pump Airconditioner Drive | 2027-11-29 | 2027-11-29 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000326478 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-ACPMP | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Coupling Drive Pump | 2027-11-29 | 2027-11-29 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000326563 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-HYDPC | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Pump Main Hydraulic | 2027-11-29 | 2027-11-29 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000326586 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-HYPMP | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Steering RHS | 2027-11-29 | 2027-11-29 | 8 hrs | FY28 | 14 | 90029374 | A1 | 1000326567 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-STRSYS-STRCY-STCYR | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Valve Flow Amplifier | 2027-11-29 | 2027-11-29 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000326577 | 29.11.2027 | 20000 | CLB-MP-HAUL-DT5418-STRSYS-STVLV | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Service Air Conditioner | 2027-11-30 | 2027-11-30 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160396 | 30.11.2027 | 5500 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-AIRCN | 7500 | 90698 | 6249 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Engine Midlife complete | 2027-12-01 | 2027-12-03 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000313956 | 01.12.2027 | 17500 | CLB-MP-HAUL-DT5404-ENGINE | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-ENGINE90029500
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Water Cannon & Valves Repl | 2027-12-01 | 2027-12-02 | 24 hrs | FY28 | 48 | 90033662 | A1 | 1000338791 | 01.12.2027 | 24 Monthly | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | 5000 | 67273 | 3900 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON90033662
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Engine Midlife complete | 2027-12-02 | 2027-12-04 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000347304 | 02.12.2027 | 17500 | CLB-MP-HAUL-DT5446-ENGINE | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-ENGINE90029500
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Pump Transmission | 2027-12-04 | 2027-12-04 | 6 hrs | FY28 | 6 | 90013166 | A1 | 1000110236 | 04.12.2027 | 18000 | CLB-MP-SUPP-PM0004-TRNSYS-TRPMP-TMCPP | 3500 | 91736 | 13390 | CLB-MP-SUPP-PM0004-TRNSYS-TRPMP-TMCPP90013166
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Transmission | 2027-12-05 | 2027-12-06 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000034767 | 05.12.2027 | 22000 | CLB-MP-HAUL-DT175 -TRNSYS-TRANS | 7500 | 82722 | 11992 | CLB-MP-HAUL-DT175 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Brake Wheel LH | 2027-12-05 | 2027-12-06 | 32 hrs | FY28 | 38 | 90003104 | 2 | 1000034777 | 05.12.2027 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-AXLES-HUBLH | 7500 | 82722 | 11992 | CLB-MP-HAUL-DT175 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Brake Wheel RH | 2027-12-05 | 2027-12-06 | 33 hrs | FY28 | 61 | 90003105 | 2 | 1000034778 | 05.12.2027 | 22000 | CLB-MP-HAUL-DT175 -STRUCT-AXLES-HUBRH | 7500 | 82722 | 11992 | CLB-MP-HAUL-DT175 -STRUCT-AXLES-HUBRH90003105
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Repl Hub and Spindle LH | 2027-12-05 | 2027-12-05 | 12 hrs | FY28 | 24 | 90013216 | A1 | 1000110274 | 05.12.2027 | 22000 | CLB-MP-SUPP-PM0004-STRUCT-AXLES-HUBLH | 3500 | 91736 | 17182 | CLB-MP-SUPP-PM0004-STRUCT-AXLES-HUBLH90013216
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Brake & Steering Manifold | 2027-12-05 | 2027-12-05 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000326246 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-BRKSYS-BRVLV | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Gear Cooler Motor & Pump | 2027-12-05 | 2027-12-05 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000326265 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-FDRSYS-GRSOC-OCPPM | 6500 | 10405 | 5411 | CLB-MP-HAUL-DT5416-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Pump Airconditioner Drive | 2027-12-05 | 2027-12-05 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000326245 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-ACPMP | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Coupling Drive Pump | 2027-12-05 | 2027-12-05 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000326250 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-HYDPC | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Pump Main Hydraulic | 2027-12-05 | 2027-12-05 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000326273 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-HYPMP | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Cylinder Steering LHS | 2027-12-05 | 2027-12-05 | 8 hrs | FY28 | 14 | 90029373 | A1 | 1000326253 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-STRSYS-STRCY-STCYL | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Cylinder Steering RHS | 2027-12-05 | 2027-12-05 | 8 hrs | FY28 | 14 | 90029374 | A1 | 1000326254 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-STRSYS-STRCY-STCYR | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Valve Flow Amplifier | 2027-12-05 | 2027-12-05 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000326264 | 05.12.2027 | 20000 | CLB-MP-HAUL-DT5416-STRSYS-STVLV | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Gear Cooler Motor & Pump | 2027-12-06 | 2027-12-06 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000314352 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-FDRSYS-GRSOC-OCPPM | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Brake & Steering Manifold | 2027-12-06 | 2027-12-06 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000314365 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-BRKSYS-BRVLV | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Valve Flow Amplifier | 2027-12-06 | 2027-12-06 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000314355 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-STRSYS-STVLV | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Steering LHS | 2027-12-06 | 2027-12-06 | 8 hrs | FY28 | 14 | 90029373 | A1 | 1000314358 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-STRSYS-STRCY-STCYL | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Steering RHS | 2027-12-06 | 2027-12-06 | 8 hrs | FY28 | 14 | 90029374 | A1 | 1000314359 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-STRSYS-STRCY-STCYR | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Pump Airconditioner Drive | 2027-12-06 | 2027-12-06 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000314353 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-ACPMP | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Coupling Drive Pump | 2027-12-06 | 2027-12-06 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000314351 | 06.12.2027 | 20000 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-HYDPC | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-HYDPC90029361
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Steering Link & Arm Rebush | 2027-12-06 | 2027-12-07 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385441 | 06.12.2027 | 30000 | CLB-MP-HAUL-DT184 -STRSYS-STLTR | 7500 | 83473 | 34836 | CLB-MP-HAUL-DT184 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Steering RH | 2027-12-07 | 2027-12-07 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000036002 | 07.12.2027 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYR | 7500 | 86259 | 4965 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Air Dryer | 2027-12-08 | 2027-12-08 | 7 hrs | FY28 | 14 | 90003115 | 1 | 1000035601 | 08.12.2027 | 22000 | CLB-MP-HAUL-DT190 -PNEUMC-AIRDR | 7500 | 90698 | 57343 | CLB-MP-HAUL-DT190 -PNEUMC-AIRDR90003115
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Hyd Pump Steering Main | 2027-12-10 | 2027-12-10 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000150586 | 10.12.2027 | 15000 | CLB-MP-HAUL-DT224 -STRSYS-STPMP | 7500 | 49737 | 4881 | CLB-MP-HAUL-DT224 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Steering HMU | 2027-12-10 | 2027-12-10 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000150587 | 10.12.2027 | 15000 | CLB-MP-HAUL-DT224 -STRSYS-STHMU | 7500 | 49737 | 19248 | CLB-MP-HAUL-DT224 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Service Air Conditioner | 2027-12-11 | 2027-12-11 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160384 | 11.12.2027 | 5500 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN90017450
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 OverHaul Tag Link | 2027-12-11 | 2027-12-12 | 24 hrs | FY28 | 48 | 90003068 | A1 | 1000033949 | 11.12.2027 | 18000 | CLB-MP-SUPP-SV020 -STRUCT-CHASS-TAGLK | 3300 | 44025 | 24114 | CLB-MP-SUPP-SV020 -STRUCT-CHASS-TAGLK90003068
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Cyl Suspension LHF | 2027-12-12 | 2027-12-13 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000067794 | 12.12.2027 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYLF | 7500 | 92351 | 11680 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Pump Drive Driveshaft Unis | 2027-12-13 | 2027-12-13 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000036166 | 13.12.2027 | 11000 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR-DRSHT | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Pump Transmission | 2027-12-13 | 2027-12-13 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000036167 | 13.12.2027 | 11000 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TMCPP | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Pump Brake Control | 2027-12-13 | 2027-12-13 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000036178 | 13.12.2027 | 11000 | CLB-MP-HAUL-DT200 -BRKSYS-HYFPP | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Service Suspension Cylinders | 2027-12-13 | 2027-12-13 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106949 | 13.12.2027 | 11000 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Brake Relay Valve | 2027-12-13 | 2027-12-13 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078895 | 13.12.2027 | 11000 | CLB-MP-HAUL-DT200 -BRKSYS-BRVRL | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Cyl Suspension LHR | 2027-12-13 | 2027-12-14 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000034412 | 13.12.2027 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYLR | 7500 | 93142 | 11875 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Service Suspension Cylinders | 2027-12-15 | 2027-12-15 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106899 | 15.12.2027 | 11000 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN | 7500 | 90698 | 22083 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Engine Midlife Complete | 2027-12-15 | 2027-12-19 | 94 hrs | FY28 | 122 | 90028722 | A1 | 1000289424 | 15.12.2027 | 10000 | CLB-MP-SUPP-WC013 -ENGINE | 5000 | 63833 | 3387 | CLB-MP-SUPP-WC013 -ENGINE90028722
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Overhaul Airconditioner | 2027-12-15 | 2027-12-16 | 24 hrs | FY28 | 24 | 90028727 | A1 | 1000289426 | 15.12.2027 | 10000 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN90028727
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Engine Midlife Complete | 2027-12-16 | 2027-12-20 | 94 hrs | FY28 | 122 | 90028722 | A1 | 1000289430 | 16.12.2027 | 10000 | CLB-MP-SUPP-WC014 -ENGINE | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -ENGINE90028722
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Overhaul Airconditioner | 2027-12-16 | 2027-12-17 | 24 hrs | FY28 | 24 | 90028727 | A1 | 1000289432 | 16.12.2027 | 10000 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN90028727
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Service Air Conditioner 12M | 2027-12-19 | 2027-12-19 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000342850 | 19.12.2027 | 12 Monthly | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Engine Midlife complete | 2027-12-20 | 2027-12-24 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156507 | 20.12.2027 | 11000 | CLB-MP-HAUL-DT165 -ENGINE | 7500 | 78966 | 708 | CLB-MP-HAUL-DT165 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Midlife Valve Set - Adjust | 2027-12-20 | 2027-12-20 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390889 | 20.12.2027 | 11000 | CLB-MP-HAUL-DT165 -ENGINE | 7500 | 78966 | 708 | CLB-MP-HAUL-DT165 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Cyl Steering LH | 2027-12-21 | 2027-12-21 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035943 | 21.12.2027 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYL | 7500 | 85161 | 19642 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Brake Slack Adjuster Rear | 2027-12-21 | 2027-12-21 | 4 hrs | FY28 | 4 | 90009307 | 1 | 1000072271 | 21.12.2027 | 18000 | CLB-MP-HAUL-DT175 -BRKSYS-SLACK-SLACR | 7500 | 82722 | 7663 | CLB-MP-HAUL-DT175 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Steering Link & Arm Rebush | 2027-12-22 | 2027-12-23 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385465 | 22.12.2027 | 30000 | CLB-MP-HAUL-DT196 -STRSYS-STLTR | 7500 | 85161 | 19642 | CLB-MP-HAUL-DT196 -STRSYS-STLTR90038355
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Service Airconditioner | 2027-12-22 | 2027-12-23 | 24 hrs | FY28 | 24 | 90029084 | A1 | 1000290596 | 22.12.2027 | 4500 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN | 3300 | 44025 | 4749 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN90029084
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Water Cannon Inspect | 2027-12-22 | 2027-12-22 | 3 hrs | FY28 | 3 | 90033661 | A1 | 1000338995 | 22.12.2027 | 6 Monthly | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | 5000 | 64118 | 9073 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Service Suspension Cylinders | 2027-12-23 | 2027-12-23 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106881 | 23.12.2027 | 11000 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN | 7500 | 92351 | 22391 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN90012840
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Engine Midlife complete | 2027-12-24 | 2027-12-26 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000349063 | 24.12.2027 | 17500 | CLB-MP-HAUL-DT5448-ENGINE | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Control Cabinet Coolant | 2027-12-26 | 2027-12-26 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000349722 | 26.12.2027 | 15000 | CLB-MP-HAUL-DT5452-ELCTHV-HVCAB-COOLR | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Engine Midlife complete | 2027-12-26 | 2027-12-28 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000349107 | 26.12.2027 | 17500 | CLB-MP-HAUL-DT5449-ENGINE | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Midlife Valve Set - Adjust | 2027-12-26 | 2027-12-26 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390896 | 26.12.2027 | 11000 | CLB-MP-HAUL-DT172 -ENGINE | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Engine Midlife complete | 2027-12-26 | 2027-12-30 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156619 | 26.12.2027 | 11000 | CLB-MP-HAUL-DT172 -ENGINE | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Air Dryer | 2027-12-26 | 2027-12-26 | 7 hrs | FY28 | 14 | 90003115 | 1 | 1000035232 | 26.12.2027 | 22000 | CLB-MP-HAUL-DT183 -PNEUMC-AIRDR | 7500 | 90364 | 56923 | CLB-MP-HAUL-DT183 -PNEUMC-AIRDR90003115
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Service Air Conditioner | 2027-12-26 | 2027-12-26 | 12 hrs | FY28 | 12 | 90017450 | 2 | 1000160408 | 26.12.2027 | 5500 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-AIRCN | 7500 | 51346 | 576 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl AOC Fan Motor | 2027-12-28 | 2027-12-28 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000035051 | 28.12.2027 | 22000 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-MTFAN | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-MTFAN90003102
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Air Drier and Tank | 2027-12-30 | 2027-12-30 | 12 hrs | FY28 | 24 | 90004010 | 1 | 1000044674 | 30.12.2027 | 9000 | CLB-MP-SUPP-WC013 -PNEUMC-AIRDR | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -PNEUMC-AIRDR90004010
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Drive Shaft Transmission | 2027-12-31 | 2027-12-31 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154373 | 31.12.2027 | 22000 | CLB-MP-HAUL-DT166 -FDRSYS-DRSHT | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Pump Drive Driveshaft Unis | 2028-01-02 | 2028-01-02 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000034603 | 02.01.2028 | 11000 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR-DRSHT | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Pump Transmission | 2028-01-02 | 2028-01-02 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034604 | 02.01.2028 | 11000 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TMCPP | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Brake Relay Valve | 2028-01-02 | 2028-01-02 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078515 | 02.01.2028 | 11000 | CLB-MP-HAUL-DT172 -BRKSYS-BRVRL | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Steering Link & Arm Rebush | 2028-01-02 | 2028-01-03 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385459 | 02.01.2028 | 30000 | CLB-MP-HAUL-DT193 -STRSYS-STLTR | 7500 | 83140 | 19357 | CLB-MP-HAUL-DT193 -STRSYS-STLTR90038355
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Engine Midlife complete | 2028-01-05 | 2028-01-07 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000349950 | 05.01.2028 | 17500 | CLB-MP-HAUL-DT5453-ENGINE | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Engine Midlife complete | 2028-01-05 | 2028-01-07 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000349608 | 05.01.2028 | 17500 | CLB-MP-HAUL-DT5451-ENGINE | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Transmission | 2028-01-06 | 2028-01-07 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000034822 | 06.01.2028 | 22000 | CLB-MP-HAUL-DT176 -TRNSYS-TRANS | 7500 | 85284 | 11308 | CLB-MP-HAUL-DT176 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Transmission | 2028-01-06 | 2028-01-06 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034824 | 06.01.2028 | 11000 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP | 7500 | 85284 | 11308 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Transmission Oil Cooler | 2028-01-06 | 2028-01-06 | 13 hrs | FY28 | 13 | 90003532 | 1 | 1000040985 | 06.01.2028 | 22000 | CLB-MP-HAUL-DT176 -TRNSYS-TROLC | 7500 | 85284 | 11308 | CLB-MP-HAUL-DT176 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Brake Wheel LH | 2028-01-10 | 2028-01-11 | 32 hrs | FY28 | 38 | 90003104 | 2 | 1000034335 | 10.01.2028 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-AXLES-HUBLH | 7500 | 83303 | 11175 | CLB-MP-HAUL-DT167 -STRUCT-AXLES-HUBLH90003104
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 24M Timber Replacement | 2028-01-10 | 2028-01-11 | 36 hrs | FY28 | 72 | 90031571 | A1 | 1000311691 | 10.01.2028 | 24 Monthly | CLB-MP-SUPP-LL0003-STRUCT |  |  |  | CLB-MP-SUPP-LL0003-STRUCT90031571
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Steering HMU | 2028-01-11 | 2028-01-11 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000034839 | 11.01.2028 | 15000 | CLB-MP-HAUL-DT176 -STRSYS-STHMU | 7500 | 85284 | 19801 | CLB-MP-HAUL-DT176 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Ovhl Axle A Frame | 2028-01-11 | 2028-01-12 | 36 hrs | FY28 | 60 | 90015390 | 1 | 1000130665 | 11.01.2028 | 22000 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-AFRME | 7500 | 82554 | 32729 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-AFRME90015390
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Water Cannon | 2028-01-12 | 2028-01-12 | 12 hrs | FY28 | 24 | 90015535 | 1 | 1000133454 | 12.01.2028 | 12 Monthly | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | 5000 | 65823 | 12836 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON90015535
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Adjust Engine Valve Set | 2028-01-13 | 2028-01-13 | 6 hrs | FY28 | 6 | 90017451 | A1 | 1000290591 | 13.01.2028 | 3000 | CLB-MP-SUPP-SV019 -ENGINE | 2500 | 48856 | 11163 | CLB-MP-SUPP-SV019 -ENGINE90017451
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Service Suspension Cylinders | 2028-01-14 | 2028-01-14 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106946 | 14.01.2028 | 11000 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN | 7500 | 86259 | 11085 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Differential | 2028-01-14 | 2028-01-16 | 44 hrs | FY28 | 66 | 90003098 | 1 | 1000036169 | 14.01.2028 | 22000 | CLB-MP-HAUL-DT200 -FDRSYS-DIFFL | 7500 | 92548 | 10020 | CLB-MP-HAUL-DT200 -FDRSYS-DIFFL90003098
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 5000Hr Valve Set | 2028-01-15 | 2028-01-15 | 12 hrs | FY28 | 24 | 90028725 | A1 | 1000289476 | 15.01.2028 | 5000 | CLB-MP-SUPP-WC3108-ENGINE | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Repl PTO Uni's | 2028-01-15 | 2028-01-15 | 4 hrs | FY28 | 4 | 90031093 | A1 | 1000307811 | 15.01.2028 | 5000 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT90031093
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Service Airconditioner | 2028-01-15 | 2028-01-15 | 12 hrs | FY28 | 12 | 90028728 | A1 | 1000289473 | 15.01.2028 | 5000 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN90028728
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Cyl Suspension LHR | 2028-01-15 | 2028-01-16 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000034634 | 15.01.2028 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYLR | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Cyl Hoist RH | 2028-01-15 | 2028-01-16 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000034293 | 15.01.2028 | 28000 | CLB-MP-HAUL-DT166 -HYDSYS-HOCYL-HCYLR | 7500 | 95491 | 17159 | CLB-MP-HAUL-DT166 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Service Air Conditioner | 2028-01-15 | 2028-01-15 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160404 | 15.01.2028 | 5500 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-AIRCN | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 1Y Air Tank LH External Inspect | 2028-01-16 | 2028-01-16 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389422 | 16.01.2028 | 12 Monthly | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH | 7500 | 90973 | 42723 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 1Y Air Tank RH External Inspect | 2028-01-16 | 2028-01-16 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389424 | 16.01.2028 | 12 Monthly | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH | 7500 | 90973 | 42723 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Service Air Conditioner | 2028-01-16 | 2028-01-16 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160403 | 16.01.2028 | 5500 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-AIRCN | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Final Drive RH | 2028-01-18 | 2028-01-18 | 14 hrs | FY28 | 26 | 90007346 | 1 | 1000044718 | 18.01.2028 | 20000 | CLB-MP-SUPP-WC014 -FDRSYS-FDRVE-FDRRH | 5000 | 65823 | 12235 | CLB-MP-SUPP-WC014 -FDRSYS-FDRVE-FDRRH90007346
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Engine Midlife complete | 2028-01-19 | 2028-01-21 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000350400 | 19.01.2028 | 17500 | CLB-MP-HAUL-DT5454-ENGINE | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-ENGINE90029500
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Steering Cylinder RH | 2028-01-19 | 2028-01-19 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000044540 | 19.01.2028 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STRCY-STCYR | 5000 | 64118 | 7306 | CLB-MP-SUPP-WC011 -STRSYS-STRCY-STCYR90004005
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Seat Operators | 2028-01-20 | 2028-01-20 | 4 hrs | FY28 | 4 | 90004012 | 1 | 1000221780 | 20.01.2028 | 10000 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-SEATS | 5000 | 17738 | 2662 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-SEATS90004012
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Service Air Conditioner 12M | 2028-01-20 | 2028-01-20 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000346232 | 20.01.2028 | 12 Monthly | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Suspension Cylinder LHR | 2028-01-21 | 2028-01-21 | 16 hrs | FY28 | 28 | 90004014 | 1 | 1000044549 | 21.01.2028 | 20000 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYLR | 5000 | 64118 | 12272 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYLR90004014
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Cyl Hoist LH | 2028-01-22 | 2028-01-23 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000150682 | 22.01.2028 | 28000 | CLB-MP-HAUL-DT225 -HYDSYS-HOCYL-HCYLL | 7500 | 51346 | 16991 | CLB-MP-HAUL-DT225 -HYDSYS-HOCYL-HCYLL90003114
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Air Drier and Tank | 2028-01-22 | 2028-01-22 | 12 hrs | FY28 | 24 | 90004010 | 1 | 1000044546 | 22.01.2028 | 9000 | CLB-MP-SUPP-WC011 -PNEUMC-AIRDR | 5000 | 64118 | 21040 | CLB-MP-SUPP-WC011 -PNEUMC-AIRDR90004010
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 1Y Air Tank LH External Inspect | 2028-01-23 | 2028-01-23 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389310 | 23.01.2028 | 12 Monthly | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH | 7500 | 80996 | 48008 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 1Y Air Tank RH External Inspect | 2028-01-23 | 2028-01-23 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389312 | 23.01.2028 | 12 Monthly | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH | 7500 | 80996 | 48008 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Engine Midlife complete | 2028-01-27 | 2028-01-31 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156587 | 27.01.2028 | 11000 | CLB-MP-HAUL-DT170 -ENGINE | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Midlife Valve Set - Adjust | 2028-01-27 | 2028-01-27 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390894 | 27.01.2028 | 11000 | CLB-MP-HAUL-DT170 -ENGINE | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Service Suspension Cylinders | 2028-01-27 | 2028-01-27 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106879 | 27.01.2028 | 11000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN | 7500 | 91119 | 21730 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Spiders Transmission Driveshaft | 2028-01-27 | 2028-01-27 | 4 hrs | FY28 | 8 | 90017135 | 1 | 1000154382 | 27.01.2028 | 11000 | CLB-MP-HAUL-DT170 -FDRSYS-DRSHT-UNVSL | 7500 | 91119 | 21744 | CLB-MP-HAUL-DT170 -FDRSYS-DRSHT-UNVSL90017135
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Engine Midlife complete | 2028-01-29 | 2028-01-31 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000347007 | 29.01.2028 | 17500 | CLB-MP-HAUL-DT5445-ENGINE | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Engine Midlife complete | 2028-01-30 | 2028-02-01 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000350444 | 30.01.2028 | 17500 | CLB-MP-HAUL-DT5455-ENGINE | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Cyl Suspension RHF | 2028-02-01 | 2028-02-02 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000067836 | 01.02.2028 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYRF | 7500 | 92002 | 10817 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Hyd Motor Axle Lube Rear | 2028-02-02 | 2028-02-02 | 9 hrs | FY28 | 9 | 90003101 | 1 | 1000034442 | 02.02.2028 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-HYM01 | 7500 | 93410 | 10768 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 1Y Air Tank LH External Inspect | 2028-02-02 | 2028-02-02 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389326 | 02.02.2028 | 12 Monthly | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH | 7500 | 83047 | 18464 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 1Y Air Tank RH External Inspect | 2028-02-02 | 2028-02-02 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389328 | 02.02.2028 | 12 Monthly | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH | 7500 | 83047 | 18464 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Final Drive RH | 2028-02-03 | 2028-02-04 | 30 hrs | FY28 | 56 | 90003100 | 1 | 1000035757 | 03.02.2028 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-FDRVE-FDRRH | 7500 | 83140 | 10706 | CLB-MP-HAUL-DT193 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Drive Line Axle LH | 2028-02-03 | 2028-02-03 | 4 hrs | FY28 | 8 | 90014551 | 1 | 1000123520 | 03.02.2028 | 30000 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX-AXLLH | 7500 | 82722 | 18747 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Drive Line Axle RH | 2028-02-03 | 2028-02-03 | 4 hrs | FY28 | 8 | 90014552 | 1 | 1000123581 | 03.02.2028 | 30000 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX-AXLRH | 7500 | 82722 | 18747 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 1Y Air Tank LH External Inspect | 2028-02-04 | 2028-02-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389390 | 04.02.2028 | 12 Monthly | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH | 7500 | 83208 | 83208 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 1Y Air Tank RH External Inspect | 2028-02-04 | 2028-02-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389392 | 04.02.2028 | 12 Monthly | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH | 7500 | 83208 | 83208 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH90038753
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 24M Timber Replacement | 2028-02-05 | 2028-02-06 | 36 hrs | FY28 | 72 | 90037674 | A1 | 1000373516 | 05.02.2028 | 24 Monthly | CLB-MP-SUPP-LL0002-STRUCT |  |  |  | CLB-MP-SUPP-LL0002-STRUCT90037674
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Overhaul Air Conditioner 24M | 2028-02-07 | 2028-02-09 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000300051 | 07.02.2028 | 24 Monthly | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Service Suspension Cylinders | 2028-02-07 | 2028-02-07 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106892 | 07.02.2028 | 11000 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN | 7500 | 90364 | 10497 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Pump Torque Converter Charge | 2028-02-07 | 2028-02-07 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080202 | 07.02.2028 | 22000 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TCCPP | 7500 | 89560 | 10716 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TCCPP90003095
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Service Air Conditioner 12M | 2028-02-09 | 2028-02-09 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000346991 | 09.02.2028 | 12 Monthly | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Hoist LH | 2028-02-09 | 2028-02-10 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000036005 | 09.02.2028 | 28000 | CLB-MP-HAUL-DT197 -HYDSYS-HOCYL-HCYLL | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Hoist RH | 2028-02-09 | 2028-02-10 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000036006 | 09.02.2028 | 28000 | CLB-MP-HAUL-DT197 -HYDSYS-HOCYL-HCYLR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Cyl Hoist RH | 2028-02-09 | 2028-02-10 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000036064 | 09.02.2028 | 28000 | CLB-MP-HAUL-DT198 -HYDSYS-HOCYL-HCYLR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 1Y Air Tank LH External Inspect | 2028-02-09 | 2028-02-09 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389334 | 09.02.2028 | 12 Monthly | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH | 7500 | 93147 | 93147 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 1Y Air Tank RH External Inspect | 2028-02-09 | 2028-02-09 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389336 | 09.02.2028 | 12 Monthly | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH | 7500 | 93147 | 93147 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Seat Operator | 2028-02-10 | 2028-02-10 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000314215 | 10.02.2028 | 14000 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-SEATS | 6500 | 10949 | 3771 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-SEATS90029285
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Air Drier and Tank | 2028-02-13 | 2028-02-13 | 12 hrs | FY28 | 24 | 90004010 | 1 | 1000044802 | 13.02.2028 | 9000 | CLB-MP-SUPP-WC015 -PNEUMC-AIRDR | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -PNEUMC-AIRDR90004010
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Hyd Pump Steering Main | 2028-02-14 | 2028-02-14 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035410 | 14.02.2028 | 15000 | CLB-MP-HAUL-DT187 -STRSYS-STPMP | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Steering HMU | 2028-02-14 | 2028-02-14 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035411 | 14.02.2028 | 15000 | CLB-MP-HAUL-DT187 -STRSYS-STHMU | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Cyl Steering RH | 2028-02-14 | 2028-02-14 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000035413 | 14.02.2028 | 15000 | CLB-MP-HAUL-DT187 -STRSYS-STRCY-STCYR | 7500 | 93170 | 3514 | CLB-MP-HAUL-DT187 -STRSYS-STRCY-STCYR90003111
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Engine Midlife complete | 2028-02-21 | 2028-02-23 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000349659 | 21.02.2028 | 17500 | CLB-MP-HAUL-DT5450-ENGINE | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Steering Link & Arm Rebush | 2028-02-21 | 2028-02-22 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385443 | 21.02.2028 | 30000 | CLB-MP-HAUL-DT185 -STRSYS-STLTR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Transmission | 2028-02-21 | 2028-02-22 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000035983 | 21.02.2028 | 22000 | CLB-MP-HAUL-DT197 -TRNSYS-TRANS | 7500 | 86259 | 10405 | CLB-MP-HAUL-DT197 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Pump Transmission | 2028-02-21 | 2028-02-21 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000116278 | 21.02.2028 | 11000 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TMCPP | 7500 | 86259 | 10405 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Suspension RHR | 2028-02-21 | 2028-02-22 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000036016 | 21.02.2028 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYRR | 7500 | 86259 | 10402 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Service Air Conditioner | 2028-02-21 | 2028-02-21 | 12 hrs | FY28 | 12 | 90017450 | 2 | 1000160407 | 21.02.2028 | 5500 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-AIRCN | 7500 | 49737 | 9540 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Cyl Suspension LHF | 2028-02-22 | 2028-02-23 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000067818 | 22.02.2028 | 22000 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYLF | 7500 | 81600 | 10332 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Engine Midlife complete | 2028-02-22 | 2028-02-26 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156779 | 22.02.2028 | 11000 | CLB-MP-HAUL-DT182 -ENGINE | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Midlife Valve Set - Adjust | 2028-02-22 | 2028-02-22 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390946 | 22.02.2028 | 11000 | CLB-MP-HAUL-DT182 -ENGINE | 7500 | 92002 | 21376 | CLB-MP-HAUL-DT182 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Spiders Transmission Driveshaft | 2028-02-22 | 2028-02-22 | 4 hrs | FY28 | 8 | 90017135 | 1 | 1000154406 | 22.02.2028 | 11000 | CLB-MP-HAUL-DT182 -FDRSYS-DRSHT-UNVSL | 7500 | 92002 | 9389 | CLB-MP-HAUL-DT182 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Transmission Oil Cooler | 2028-02-23 | 2028-02-23 | 13 hrs | FY28 | 13 | 90003532 | 1 | 1000041006 | 23.02.2028 | 22000 | CLB-MP-HAUL-DT197 -TRNSYS-TROLC | 7500 | 86259 | 10403 | CLB-MP-HAUL-DT197 -TRNSYS-TROLC90003532
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Auto Lube Pump | 2028-02-23 | 2028-02-23 | 2 hrs | FY28 | 2 | 90013205 | A1 | 1000110269 | 23.02.2028 | 6000 | CLB-MP-SUPP-PM0004-GRSYST-ALBPP | 3500 | 91736 | 6593 | CLB-MP-SUPP-PM0004-GRSYST-ALBPP90013205
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Hyd Pump Steering Main | 2028-02-24 | 2028-02-24 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035767 | 24.02.2028 | 15000 | CLB-MP-HAUL-DT193 -STRSYS-STPMP | 7500 | 83140 | 3268 | CLB-MP-HAUL-DT193 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Steering HMU | 2028-02-24 | 2028-02-24 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035768 | 24.02.2028 | 15000 | CLB-MP-HAUL-DT193 -STRSYS-STHMU | 7500 | 83140 | 3268 | CLB-MP-HAUL-DT193 -STRSYS-STHMU90003110
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Inspect Water Cannon | 2028-02-25 | 2028-02-25 | 3 hrs | FY28 | 3 | 90033661 | A1 | 1000339268 | 25.02.2028 | 6 Monthly | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | 5000 | 17738 | 8813 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Cyl Steering LH | 2028-02-26 | 2028-02-26 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035769 | 26.02.2028 | 15000 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYL | 7500 | 83140 | 3346 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 1Y Air Tank LH External Inspect | 2028-02-27 | 2028-02-27 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389398 | 27.02.2028 | 12 Monthly | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH | 7500 | 89493 | 42523 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 1Y Air Tank RH External Inspect | 2028-02-27 | 2028-02-27 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389400 | 27.02.2028 | 12 Monthly | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH | 7500 | 89493 | 42523 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH90038753
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Steering Links Tie Rods | 2028-02-27 | 2028-02-27 | 12 hrs | FY28 | 24 | 90013196 | A1 | 1000110265 | 27.02.2028 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STLTR | 3500 | 91736 | 9521 | CLB-MP-SUPP-PM0004-STRSYS-STLTR90013196
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Overhaul Air Conditioner 24M | 2028-02-28 | 2028-03-01 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000314067 | 28.02.2028 | 24 Monthly | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Service Air Conditioner | 2028-02-28 | 2028-02-28 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160400 | 28.02.2028 | 5500 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-AIRCN | 7500 | 86451 | 4331 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Engine Midlife Complete | 2028-02-28 | 2028-03-03 | 94 hrs | FY28 | 122 | 90028722 | A1 | 1000289412 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC011 -ENGINE | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -ENGINE90028722
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl PTO Uni's & Driveshaft | 2028-02-28 | 2028-02-28 | 2 hrs | FY28 | 2 | 90031094 | A1 | 1000307801 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT90031094
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Rear Axle Cooling Fan Motor | 2028-02-28 | 2028-02-28 | 2 hrs | FY28 | 2 | 90003997 | 1 | 1000044528 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC011 -FDRSYS-AXLEC-MTFAN | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Rear Axle Oil Pump | 2028-02-28 | 2028-02-28 | 2 hrs | FY28 | 2 | 90003996 | 1 | 1000044527 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC011 -FDRSYS-AXLEC-HYPUM | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -FDRSYS-AXLEC-HYPUM90003996
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Overhaul Airconditioner | 2028-02-28 | 2028-02-29 | 24 hrs | FY28 | 24 | 90028727 | A1 | 1000289414 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN90028727
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Seat Operators | 2028-02-28 | 2028-02-28 | 4 hrs | FY28 | 4 | 90004012 | 1 | 1000161838 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-SEATS | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-SEATS90004012
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl PTO Uni's & Driveshaft | 2028-02-28 | 2028-02-28 | 2 hrs | FY28 | 2 | 90031094 | A1 | 1000307804 | 28.02.2028 | 10000 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT90031094
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Service Air Conditioner | 2028-03-01 | 2028-03-01 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160397 | 01.03.2028 | 5500 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-AIRCN | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Engine Cat 3516B | 2028-03-01 | 2028-03-05 | 96 hrs | FY28 | 142 | 90017315 | 1 | 1000156557 | 01.03.2028 | 22000 | CLB-MP-HAUL-DT169 -ENGINE | 7500 | 93410 | 9210 | CLB-MP-HAUL-DT169 -ENGINE90017315
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Overhaul Air Conditioner 24M | 2028-03-03 | 2028-03-05 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000300347 | 03.03.2028 | 24 Monthly | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN | 6500 | 11246 | 4814 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Cyl Hoist RH | 2028-03-03 | 2028-03-04 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000034680 | 03.03.2028 | 28000 | CLB-MP-HAUL-DT173 -HYDSYS-HOCYL-HCYLR | 7500 | 82651 | 16060 | CLB-MP-HAUL-DT173 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Seat Operator | 2028-03-05 | 2028-03-05 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000360989 | 05.03.2028 | 14000 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-SEATS | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Cyl Hoist RH | 2028-03-05 | 2028-03-06 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000150683 | 05.03.2028 | 28000 | CLB-MP-HAUL-DT225 -HYDSYS-HOCYL-HCYLR | 7500 | 51346 | 16098 | CLB-MP-HAUL-DT225 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Seat Operator | 2028-03-06 | 2028-03-06 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000361182 | 06.03.2028 | 14000 | CLB-MP-HAUL-DT5470-STRUCT-CABIN-SEATS | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Pump Torque Converter Charge | 2028-03-07 | 2028-03-07 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080221 | 07.03.2028 | 22000 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TCCPP | 7500 | 92548 | 10019 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Pump Hoist & Brake | 2028-03-07 | 2028-03-07 | 10 hrs | FY28 | 10 | 90003113 | 1 | 1000036186 | 07.03.2028 | 22000 | CLB-MP-HAUL-DT200 -HYDSYS-HOPMP | 7500 | 92548 | 10019 | CLB-MP-HAUL-DT200 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Ovhl Axle A Frame | 2028-03-08 | 2028-03-09 | 36 hrs | FY28 | 60 | 90015390 | 1 | 1000130670 | 08.03.2028 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-AFRME | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-AFRME90015390
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Seat Operator | 2028-03-10 | 2028-03-10 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000357166 | 10.03.2028 | 14000 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-SEATS | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Service Air Conditioner 12M | 2028-03-10 | 2028-03-10 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000347363 | 10.03.2028 | 12 Monthly | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Seat Operator | 2028-03-11 | 2028-03-11 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000360839 | 11.03.2028 | 14000 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-SEATS | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Service Air Conditioner 12M | 2028-03-11 | 2028-03-11 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000349687 | 11.03.2028 | 12 Monthly | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Service Air Conditioner 12M | 2028-03-11 | 2028-03-11 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000349643 | 11.03.2028 | 12 Monthly | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 1Y Air Tank LH External Inspect | 2028-03-13 | 2028-03-13 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389402 | 13.03.2028 | 12 Monthly | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH | 7500 | 92907 | 46760 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 1Y Air Tank RH External Inspect | 2028-03-13 | 2028-03-13 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389404 | 13.03.2028 | 12 Monthly | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH | 7500 | 92907 | 46760 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Cyl Steering RH | 2028-03-15 | 2028-03-15 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000035227 | 15.03.2028 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STRCY-STCYR | 7500 | 90364 | 2831 | CLB-MP-HAUL-DT183 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Air Dryer | 2028-03-15 | 2028-03-15 | 7 hrs | FY28 | 14 | 90003115 | 1 | 1000035418 | 15.03.2028 | 22000 | CLB-MP-HAUL-DT187 -PNEUMC-AIRDR | 7500 | 93170 | 33317 | CLB-MP-HAUL-DT187 -PNEUMC-AIRDR90003115
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 1Y Air Tank LH External Inspect | 2028-03-16 | 2028-03-16 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389466 | 16.03.2028 | 12 Monthly | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH | 7500 | 91739 | 50479 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 1Y Air Tank RH External Inspect | 2028-03-16 | 2028-03-16 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389468 | 16.03.2028 | 12 Monthly | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH | 7500 | 91739 | 50479 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH90038753
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Pump Hoist | 2028-03-16 | 2028-03-16 | 6 hrs | FY28 | 6 | 90003059 | A1 | 1000033939 | 16.03.2028 | 9000 | CLB-MP-SUPP-SV020 -HYDSYS-HOPMP | 3300 | 44025 | 3632 | CLB-MP-SUPP-SV020 -HYDSYS-HOPMP90003059
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Service Air Conditioner | 2028-03-17 | 2028-03-17 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160375 | 17.03.2028 | 5500 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-AIRCN | 7500 | 93142 | 15366 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Water Cannon Inspect | 2028-03-17 | 2028-03-17 | 3 hrs | FY28 | 3 | 90033661 | A1 | 1000338792 | 17.03.2028 | 6 Monthly | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Pump Drive Driveshaft Unis | 2028-03-20 | 2028-03-20 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035926 | 20.03.2028 | 11000 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR-DRSHT | 7500 | 85161 | 22315 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 1Y Air Tank LH External Inspect | 2028-03-20 | 2028-03-20 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389314 | 20.03.2028 | 12 Monthly | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH | 7500 | 81612 | 11133 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 1Y Air Tank RH External Inspect | 2028-03-20 | 2028-03-20 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389316 | 20.03.2028 | 12 Monthly | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH | 7500 | 81612 | 11133 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Service Suspension Cylinders | 2028-03-20 | 2028-03-20 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106882 | 20.03.2028 | 11000 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN | 7500 | 82651 | 12558 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 1Y Air Tank LH External Inspect | 2028-03-21 | 2028-03-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389410 | 21.03.2028 | 12 Monthly | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH | 7500 | 84322 | 84322 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 1Y Air Tank RH External Inspect | 2028-03-21 | 2028-03-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389412 | 21.03.2028 | 12 Monthly | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH | 7500 | 84322 | 84322 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Engine Cat 3516B | 2028-03-21 | 2028-03-25 | 96 hrs | FY28 | 142 | 90017315 | 1 | 1000156589 | 21.03.2028 | 22000 | CLB-MP-HAUL-DT171 -ENGINE | 7500 | 90182 | 8268 | CLB-MP-HAUL-DT171 -ENGINE90017315
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Drive Shaft Transmission | 2028-03-21 | 2028-03-21 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154413 | 21.03.2028 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-DRSHT | 7500 | 89736 | 8654 | CLB-MP-HAUL-DT186 -FDRSYS-DRSHT90017134
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Hub & Spindle LH | 2028-03-22 | 2028-03-23 | 26 hrs | FY28 | 50 | 90004020 | 3 | 1000221749 | 22.03.2028 | 24000 | CLB-MP-SUPP-WC3108-STRUCT-AXLES-HUBLH | 5000 | 17738 | 15820 | CLB-MP-SUPP-WC3108-STRUCT-AXLES-HUBLH90004020
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Cyl Hoist LH | 2028-03-23 | 2028-03-24 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035831 | 23.03.2028 | 28000 | CLB-MP-HAUL-DT194 -HYDSYS-HOCYL-HCYLL | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Cyl Hoist RH | 2028-03-23 | 2028-03-24 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000035832 | 23.03.2028 | 28000 | CLB-MP-HAUL-DT194 -HYDSYS-HOCYL-HCYLR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Cyl Hoist LH | 2028-03-23 | 2028-03-24 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035065 | 23.03.2028 | 28000 | CLB-MP-HAUL-DT180 -HYDSYS-HOCYL-HCYLL | 7500 | 89560 | 15760 | CLB-MP-HAUL-DT180 -HYDSYS-HOCYL-HCYLL90003114
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Brake & Steering Manifold | 2028-03-24 | 2028-03-24 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000346731 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-BRKSYS-BRVLV | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Gear Cooler Motor & Pump | 2028-03-24 | 2028-03-24 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000346770 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-FDRSYS-GRSOC-OCPPM | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Pump Airconditioner Drive | 2028-03-24 | 2028-03-24 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000346730 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-ACPMP | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Coupling Drive Pump | 2028-03-24 | 2028-03-24 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000346735 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-HYDPC | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Pump Main Hydraulic | 2028-03-24 | 2028-03-24 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000346778 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-HYPMP | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Steering LHS | 2028-03-24 | 2028-03-24 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000346738 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-STRSYS-STRCY-STCYL | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Steering RHS | 2028-03-24 | 2028-03-24 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000346739 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-STRSYS-STRCY-STCYR | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Valve Flow Amplifier | 2028-03-24 | 2028-03-24 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000346769 | 24.03.2028 | 20000 | CLB-MP-HAUL-DT5444-STRSYS-STVLV | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Steering Ball Studs | 2028-03-24 | 2028-03-25 | 19 hrs | FY28 | 35 | 90038356 | A1 | 1000385410 | 24.03.2028 | 15000 | CLB-MP-HAUL-DT169 -STRSYS-STLTR | 7500 | 93410 | 2730 | CLB-MP-HAUL-DT169 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Pump Drive Driveshaft Unis | 2028-03-25 | 2028-03-25 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035264 | 25.03.2028 | 11000 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR-DRSHT | 7500 | 92088 | 9689 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Cyl Hoist LH | 2028-03-25 | 2028-03-26 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035657 | 25.03.2028 | 28000 | CLB-MP-HAUL-DT191 -HYDSYS-HOCYL-HCYLL | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Cyl Hoist RH | 2028-03-25 | 2028-03-26 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000035658 | 25.03.2028 | 28000 | CLB-MP-HAUL-DT191 -HYDSYS-HOCYL-HCYLR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Service Air Conditioner 12M | 2028-03-27 | 2028-03-27 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000346561 | 27.03.2028 | 12 Monthly | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Air Drier and Tank | 2028-03-29 | 2028-03-29 | 12 hrs | FY28 | 24 | 90004010 | 1 | 1000044738 | 29.03.2028 | 9000 | CLB-MP-SUPP-WC014 -PNEUMC-AIRDR | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -PNEUMC-AIRDR90004010
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Steering Cylinder RH | 2028-03-29 | 2028-03-29 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000044668 | 29.03.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STRCY-STCYR | 5000 | 63833 | 6926 | CLB-MP-SUPP-WC013 -STRSYS-STRCY-STCYR90004005
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Overhaul Air Conditioner 24M | 2028-03-30 | 2028-04-01 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000314217 | 30.03.2028 | 24 Monthly | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Engine Midlife complete | 2028-03-30 | 2028-04-03 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156939 | 30.03.2028 | 11000 | CLB-MP-HAUL-DT192 -ENGINE | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Midlife Valve Set - Adjust | 2028-03-30 | 2028-03-30 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390956 | 30.03.2028 | 11000 | CLB-MP-HAUL-DT192 -ENGINE | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Spiders Transmission Driveshaft | 2028-03-30 | 2028-03-30 | 4 hrs | FY28 | 8 | 90017135 | 1 | 1000154426 | 30.03.2028 | 11000 | CLB-MP-HAUL-DT192 -FDRSYS-DRSHT-UNVSL | 7500 | 91174 | 7657 | CLB-MP-HAUL-DT192 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Service Suspension Cylinders | 2028-03-31 | 2028-03-31 | 15 hrs | FY28 | 27 | 90012840 | 1 | 1000106871 | 31.03.2028 | 11000 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN | 7500 | 81237 | 42658 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Brake Accumulator | 2028-03-31 | 2028-03-31 | 4 hrs | FY28 | 4 | 90004001 | 1 | 1000044597 | 31.03.2028 | 15000 | CLB-MP-SUPP-WC012 -BRKSYS-BACCM | 5000 | 22004 | 22004 | CLB-MP-SUPP-WC012 -BRKSYS-BACCM90004001
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Steering Pump | 2028-03-31 | 2028-03-31 | 4 hrs | FY28 | 4 | 90004003 | 1 | 1000044601 | 31.03.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STPMP | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STPMP90004003
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Steering HMU | 2028-03-31 | 2028-03-31 | 8 hrs | FY28 | 8 | 90004004 | 1 | 1000044602 | 31.03.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STHMU | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STHMU90004004
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl Steering Accumulator LH | 2028-03-31 | 2028-03-31 | 2 hrs | FY28 | 2 | 90004022 | 1 | 1000044607 | 31.03.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STACC-SACLH | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl Steering Accumulator RH | 2028-03-31 | 2028-03-31 | 2 hrs | FY28 | 2 | 90004022 | 1 | 1000044608 | 31.03.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STACC-SACRH | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Steering Oil Cooler | 2028-03-31 | 2028-03-31 | 5 hrs | FY28 | 5 | 90004006 | 1 | 1000044606 | 31.03.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STOLC | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STOLC90004006
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Gear Cooler Motor & Pump | 2028-04-01 | 2028-04-01 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000300326 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-FDRSYS-GRSOC-OCPPM | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Brake & Steering Manifold | 2028-04-01 | 2028-04-01 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000300339 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-BRKSYS-BRVLV | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Valve Flow Amplifier | 2028-04-01 | 2028-04-01 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000300329 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-STRSYS-STVLV | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Steering LHS | 2028-04-01 | 2028-04-01 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000300332 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-STRSYS-STRCY-STCYL | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Steering RHS | 2028-04-01 | 2028-04-01 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000300333 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-STRSYS-STRCY-STCYR | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Pump Main Hydraulic | 2028-04-01 | 2028-04-01 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000300328 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-HYPMP | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Pump Airconditioner Drive | 2028-04-01 | 2028-04-01 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000300327 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-ACPMP | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Coupling Drive Pump | 2028-04-01 | 2028-04-01 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000300325 | 01.04.2028 | 20000 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-HYDPC | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-HYDPC90029361
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Pump Drive Driveshaft Unis | 2028-04-01 | 2028-04-01 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000034493 | 01.04.2028 | 11000 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR-DRSHT | 7500 | 91119 | 24071 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl AOC Fan Motor | 2028-04-01 | 2028-04-01 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000034500 | 01.04.2028 | 22000 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-MTFAN | 7500 | 91119 | 9406 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Pump Brake Control | 2028-04-01 | 2028-04-01 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000106789 | 01.04.2028 | 11000 | CLB-MP-HAUL-DT170 -BRKSYS-HYFPP | 7500 | 91119 | 9337 | CLB-MP-HAUL-DT170 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Brake Relay Valve | 2028-04-01 | 2028-04-01 | 6 hrs | FY28 | 6 | 90009877 | 1 | 1000078477 | 01.04.2028 | 11000 | CLB-MP-HAUL-DT170 -BRKSYS-BRVRL | 7500 | 91119 | 24132 | CLB-MP-HAUL-DT170 -BRKSYS-BRVRL90009877
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Steering Cylinder RH | 2028-04-01 | 2028-04-01 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000044732 | 01.04.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STRCY-STCYR | 5000 | 65823 | 6147 | CLB-MP-SUPP-WC014 -STRSYS-STRCY-STCYR90004005
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl Steering Cylinder LH | 2028-04-01 | 2028-04-01 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000044603 | 01.04.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STRCY-STCYL | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl Steering Cylinder RH | 2028-04-01 | 2028-04-01 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000044604 | 01.04.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STRCY-STCYR | 5000 | 67273 | 6542 | CLB-MP-SUPP-WC012 -STRSYS-STRCY-STCYR90004005
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Torque Converter | 2028-04-02 | 2028-04-02 | 14 hrs | FY28 | 26 | 90003035 | A1 | 1000033912 | 02.04.2028 | 18000 | CLB-MP-SUPP-SV020 -TRNSYS-TRQUE | 3300 | 44025 | 12481 | CLB-MP-SUPP-SV020 -TRNSYS-TRQUE90003035
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Engine Midlife complete | 2028-04-02 | 2028-04-04 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000346268 | 02.04.2028 | 17500 | CLB-MP-HAUL-DT5441-ENGINE | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Gear Cooler Motor & Pump | 2028-04-02 | 2028-04-02 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000314542 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-FDRSYS-GRSOC-OCPPM | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Brake & Steering Manifold | 2028-04-02 | 2028-04-02 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000314555 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-BRKSYS-BRVLV | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Valve Flow Amplifier | 2028-04-02 | 2028-04-02 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000314545 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-STRSYS-STVLV | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Steering RHS | 2028-04-02 | 2028-04-02 | 8 hrs | FY28 | 14 | 90029374 | A1 | 1000314549 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-STRSYS-STRCY-STCYR | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Pump Main Hydraulic | 2028-04-02 | 2028-04-02 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000314544 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-HYPMP | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Pump Airconditioner Drive | 2028-04-02 | 2028-04-02 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000314543 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-ACPMP | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Coupling Drive Pump | 2028-04-02 | 2028-04-02 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000314541 | 02.04.2028 | 20000 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-HYDPC | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-HYDPC90029361
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Hoist RH | 2028-04-07 | 2028-04-08 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000036188 | 07.04.2028 | 28000 | CLB-MP-HAUL-DT200 -HYDSYS-HOCYL-HCYLR | 7500 | 92548 | 15383 | CLB-MP-HAUL-DT200 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Brake & Steering Manifold | 2028-04-07 | 2028-04-07 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000346684 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-BRKSYS-BRVLV | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Gear Cooler Motor & Pump | 2028-04-07 | 2028-04-07 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000346703 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-FDRSYS-GRSOC-OCPPM | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Pump Airconditioner Drive | 2028-04-07 | 2028-04-07 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000346683 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-ACPMP | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Coupling Drive Pump | 2028-04-07 | 2028-04-07 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000346688 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-HYDPC | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Pump Main Hydraulic | 2028-04-07 | 2028-04-07 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000346711 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-HYPMP | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Steering LHS | 2028-04-07 | 2028-04-07 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000346691 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-STRSYS-STRCY-STCYL | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Steering RHS | 2028-04-07 | 2028-04-07 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000346692 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-STRSYS-STRCY-STCYR | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Valve Flow Amplifier | 2028-04-07 | 2028-04-07 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000346702 | 07.04.2028 | 20000 | CLB-MP-HAUL-DT5443-STRSYS-STVLV | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Midlife Valve Set - Adjust | 2028-04-09 | 2028-04-09 | 6 hrs | FY28 | 12 | 90017314 | 1 | 1000390950 | 09.04.2028 | 11000 | CLB-MP-HAUL-DT186 -ENGINE | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Engine Midlife complete | 2028-04-09 | 2028-04-13 | 107.5 hrs | FY28 | 119.5 | 90017316 | 1 | 1000156843 | 09.04.2028 | 11000 | CLB-MP-HAUL-DT186 -ENGINE | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Drive Driveshaft Unis | 2028-04-10 | 2028-04-10 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035154 | 10.04.2028 | 11000 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR-DRSHT | 7500 | 92002 | 9389 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl AOC Fan Motor | 2028-04-10 | 2028-04-10 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000035161 | 10.04.2028 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-MTFAN | 7500 | 92002 | 9389 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-MTFAN90003102
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Service Air Conditioner 12M | 2028-04-10 | 2028-04-10 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000346682 | 10.04.2028 | 12 Monthly | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl Rear Axle Cooling Fan Motor | 2028-04-11 | 2028-04-11 | 2 hrs | FY28 | 2 | 90003997 | 1 | 1000044592 | 11.04.2028 | 10000 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-MTFAN | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Rear Axle Oil Pump | 2028-04-11 | 2028-04-11 | 2 hrs | FY28 | 2 | 90003996 | 1 | 1000044591 | 11.04.2028 | 10000 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-HYPUM | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-HYPUM90003996
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Brake & Steering Manifold | 2028-04-11 | 2028-04-11 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000346563 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-BRKSYS-BRVLV | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Gear Cooler Motor & Pump | 2028-04-11 | 2028-04-11 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000346582 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-FDRSYS-GRSOC-OCPPM | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Pump Airconditioner Drive | 2028-04-11 | 2028-04-11 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000346562 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-ACPMP | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Coupling Drive Pump | 2028-04-11 | 2028-04-11 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000346567 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-HYDPC | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Pump Main Hydraulic | 2028-04-11 | 2028-04-11 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000346590 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-HYPMP | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Cylinder Steering LHS | 2028-04-11 | 2028-04-11 | 8 hrs | FY28 | 14 | 90029373 | A1 | 1000346570 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-STRSYS-STRCY-STCYL | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Cylinder Steering RHS | 2028-04-11 | 2028-04-11 | 8 hrs | FY28 | 14 | 90029374 | A1 | 1000346571 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-STRSYS-STRCY-STCYR | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Valve Flow Amplifier | 2028-04-11 | 2028-04-11 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000346581 | 11.04.2028 | 20000 | CLB-MP-HAUL-DT5442-STRSYS-STVLV | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Brake Wheel RH | 2028-04-12 | 2028-04-13 | 33 hrs | FY28 | 61 | 90003105 | 2 | 1000036176 | 12.04.2028 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-AXLES-HUBRH | 7500 | 92548 | 8611 | CLB-MP-HAUL-DT200 -STRUCT-AXLES-HUBRH90003105
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Service Air Conditioner 12M | 2028-04-14 | 2028-04-14 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000350428 | 14.04.2028 | 12 Monthly | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Seat Operator | 2028-04-14 | 2028-04-14 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000339719 | 14.04.2028 | 14000 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-SEATS | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Brake & Steering Manifold | 2028-04-16 | 2028-04-16 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000347365 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-BRKSYS-BRVLV | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Gear Cooler Motor & Pump | 2028-04-16 | 2028-04-16 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000347384 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-FDRSYS-GRSOC-OCPPM | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Pump Airconditioner Drive | 2028-04-16 | 2028-04-16 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000347364 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-ACPMP | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Coupling Drive Pump | 2028-04-16 | 2028-04-16 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000347369 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-HYDPC | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Pump Main Hydraulic | 2028-04-16 | 2028-04-16 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000347392 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-HYPMP | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Cylinder Steering LHS | 2028-04-16 | 2028-04-16 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000347372 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-STRSYS-STRCY-STCYL | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Valve Flow Amplifier | 2028-04-16 | 2028-04-16 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000347383 | 16.04.2028 | 20000 | CLB-MP-HAUL-DT5447-STRSYS-STVLV | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Service Air Conditioner 12M | 2028-04-16 | 2028-04-16 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000347288 | 16.04.2028 | 12 Monthly | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Brake Accumulator | 2028-04-16 | 2028-04-16 | 4 hrs | FY28 | 4 | 90004001 | 1 | 1000082730 | 16.04.2028 | 15000 | CLB-MP-SUPP-PM0006-BRKSYS-ACCUM | 4200 | 53807 | 7693 | CLB-MP-SUPP-PM0006-BRKSYS-ACCUM90004001
T264 | Onsite PM | Haul | Fortescue | DT5475 | DT5475 Overhaul Air Conditioner 24M | 2028-04-17 | 2028-04-19 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000363963 | 17.04.2028 | 24 Monthly | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN | 6500 | 211 | 211 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Pump Torque Converter Charge | 2028-04-17 | 2028-04-17 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080174 | 17.04.2028 | 22000 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TCCPP | 7500 | 92351 | 9072 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl AOC Fan Motor | 2028-04-17 | 2028-04-17 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000034610 | 17.04.2028 | 22000 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-MTFAN | 7500 | 92351 | 9073 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-MTFAN90003102
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Service Air Conditioner 12M | 2028-04-18 | 2028-04-18 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000346729 | 18.04.2028 | 12 Monthly | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Radiator Assembly | 2028-04-19 | 2028-04-20 | 20 hrs | FY28 | 38 | 90003977 | 1 | 1000044577 | 19.04.2028 | 20000 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-RADTR | 5000 | 67273 | 11305 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-RADTR90003977
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Water Cannon & Valves Repl | 2028-04-19 | 2028-04-20 | 24 hrs | FY28 | 48 | 90033662 | A1 | 1000338797 | 19.04.2028 | 24 Monthly | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON90033662
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Gear Cooler Motor & Pump | 2028-04-20 | 2028-04-20 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000313962 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-FDRSYS-GRSOC-OCPPM | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Brake & Steering Manifold | 2028-04-20 | 2028-04-20 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000313975 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-BRKSYS-BRVLV | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Valve Flow Amplifier | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000313965 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-STRSYS-STVLV | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Cylinder Steering LHS | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000313968 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-STRSYS-STRCY-STCYL | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Cylinder Steering RHS | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000313969 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-STRSYS-STRCY-STCYR | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Pump Main Hydraulic | 2028-04-20 | 2028-04-20 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000313964 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-HYPMP | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Pump Airconditioner Drive | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000313963 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-ACPMP | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Coupling Drive Pump | 2028-04-20 | 2028-04-20 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000313961 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-HYDPC | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Brake & Steering Manifold | 2028-04-20 | 2028-04-20 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000347290 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-BRKSYS-BRVLV | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Gear Cooler Motor & Pump | 2028-04-20 | 2028-04-20 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000347309 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-FDRSYS-GRSOC-OCPPM | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Pump Airconditioner Drive | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000347289 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-ACPMP | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Coupling Drive Pump | 2028-04-20 | 2028-04-20 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000347294 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-HYDPC | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Pump Main Hydraulic | 2028-04-20 | 2028-04-20 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000347317 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-HYPMP | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Cylinder Steering RHS | 2028-04-20 | 2028-04-20 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000347298 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-STRSYS-STRCY-STCYR | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Valve Flow Amplifier | 2028-04-20 | 2028-04-20 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000347308 | 20.04.2028 | 20000 | CLB-MP-HAUL-DT5446-STRSYS-STVLV | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Pump Torque Converter Charge | 2028-04-20 | 2028-04-20 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080209 | 20.04.2028 | 22000 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TCCPP | 7500 | 93170 | 9139 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Cyl Steering LH | 2028-04-21 | 2028-04-21 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035595 | 21.04.2028 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STRCY-STCYL | 7500 | 90698 | 2142 | CLB-MP-HAUL-DT190 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Cyl Steering RH | 2028-04-21 | 2028-04-21 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000035596 | 21.04.2028 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STRCY-STCYR | 7500 | 90698 | 2142 | CLB-MP-HAUL-DT190 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Service Air Conditioner | 2028-04-21 | 2028-04-21 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160395 | 21.04.2028 | 5500 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-AIRCN | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Air Drier & Tank | 2028-04-22 | 2028-04-22 | 12 hrs | FY28 | 24 | 90004010 | 1 | 1000221764 | 22.04.2028 | 9000 | CLB-MP-SUPP-WC3108-PNEUMC-AIRDR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-PNEUMC-AIRDR90004010
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Service Air Conditioner | 2028-04-23 | 2028-04-23 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160373 | 23.04.2028 | 5500 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-AIRCN | 7500 | 95491 | 14683 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 1Y Air Tank LH External Inspect | 2028-04-23 | 2028-04-23 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389362 | 23.04.2028 | 12 Monthly | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH | 7500 | 85021 | 13713 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 1Y Air Tank RH External Inspect | 2028-04-23 | 2028-04-23 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389364 | 23.04.2028 | 12 Monthly | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH | 7500 | 85021 | 13713 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Cyl Steering RH | 2028-04-24 | 2028-04-24 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000034289 | 24.04.2028 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYR | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYR90003111
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Service Air Conditioner 12M | 2028-04-25 | 2028-04-25 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000349047 | 25.04.2028 | 12 Monthly | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Steering HMU | 2028-04-25 | 2028-04-25 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035522 | 25.04.2028 | 15000 | CLB-MP-HAUL-DT189 -STRSYS-STHMU | 7500 | 84546 | 17061 | CLB-MP-HAUL-DT189 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Steering Link & Arm Rebush | 2028-04-26 | 2028-04-27 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385451 | 26.04.2028 | 30000 | CLB-MP-HAUL-DT189 -STRSYS-STLTR | 7500 | 84546 | 17061 | CLB-MP-HAUL-DT189 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 1Y Air Tank LH External Inspect | 2028-04-26 | 2028-04-26 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389342 | 26.04.2028 | 12 Monthly | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH | 7500 | 89925 | 89925 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 1Y Air Tank RH External Inspect | 2028-04-26 | 2028-04-26 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389344 | 26.04.2028 | 12 Monthly | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH | 7500 | 89925 | 89925 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH90038753
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Engine Midlife Complete | 2028-04-26 | 2028-04-30 | 94 hrs | FY28 | 122 | 90028722 | A1 | 1000289436 | 26.04.2028 | 10000 | CLB-MP-SUPP-WC015 -ENGINE | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -ENGINE90028722
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl PTO Uni's & Driveshaft | 2028-04-26 | 2028-04-26 | 2 hrs | FY28 | 2 | 90031094 | A1 | 1000307810 | 26.04.2028 | 10000 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT90031094
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Rear Axle Cooling Fan Motor | 2028-04-26 | 2028-04-26 | 2 hrs | FY28 | 2 | 90003997 | 1 | 1000044784 | 26.04.2028 | 10000 | CLB-MP-SUPP-WC015 -FDRSYS-AXLEC-MTFAN | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Rear Axle Oil Pump | 2028-04-26 | 2028-04-26 | 2 hrs | FY28 | 2 | 90003996 | 1 | 1000044783 | 26.04.2028 | 10000 | CLB-MP-SUPP-WC015 -FDRSYS-AXLEC-HYPUM | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -FDRSYS-AXLEC-HYPUM90003996
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Overhaul Airconditioner | 2028-04-26 | 2028-04-27 | 24 hrs | FY28 | 24 | 90028727 | A1 | 1000289438 | 26.04.2028 | 10000 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN90028727
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Seat Operators | 2028-04-26 | 2028-04-26 | 4 hrs | FY28 | 4 | 90004012 | 1 | 1000161982 | 26.04.2028 | 10000 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-SEATS | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-SEATS90004012
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Hyd Pump Steering Main | 2028-04-27 | 2028-04-27 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000150676 | 27.04.2028 | 15000 | CLB-MP-HAUL-DT225 -STRSYS-STPMP | 7500 | 51346 | 576 | CLB-MP-HAUL-DT225 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Steering HMU | 2028-04-27 | 2028-04-27 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000150677 | 27.04.2028 | 15000 | CLB-MP-HAUL-DT225 -STRSYS-STHMU | 7500 | 51346 | 576 | CLB-MP-HAUL-DT225 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Service Air Conditioner | 2028-04-27 | 2028-04-27 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160393 | 27.04.2028 | 5500 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-AIRCN | 7500 | 93170 | 13899 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Overhaul Air Conditioner 24M | 2028-04-29 | 2028-05-01 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000372487 | 29.04.2028 | 24 Monthly | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Overhaul Air Conditioner 24M | 2028-04-29 | 2028-05-01 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000371818 | 29.04.2028 | 24 Monthly | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Control Cabinet Coolant | 2028-04-30 | 2028-04-30 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000360996 | 30.04.2028 | 15000 | CLB-MP-HAUL-DT5469-ELCTHV-HVCAB-COOLR | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Control Cabinet Coolant | 2028-05-01 | 2028-05-01 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000361189 | 01.05.2028 | 15000 | CLB-MP-HAUL-DT5470-ELCTHV-HVCAB-COOLR | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-ELCTHV-HVCAB-COOLR90033128
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Service Airconditioner | 2028-05-01 | 2028-05-02 | 24 hrs | FY28 | 24 | 90029084 | A1 | 1000290643 | 01.05.2028 | 4500 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-AIRCN | 3300 | 54098 | 5 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-AIRCN90029084
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Cyl Steering LH | 2028-05-02 | 2028-05-02 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000150678 | 02.05.2028 | 15000 | CLB-MP-HAUL-DT225 -STRSYS-STRCY-STCYL | 7500 | 51346 | 1914 | CLB-MP-HAUL-DT225 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Cyl Steering RH | 2028-05-02 | 2028-05-02 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000150679 | 02.05.2028 | 15000 | CLB-MP-HAUL-DT225 -STRSYS-STRCY-STCYR | 7500 | 51346 | 1914 | CLB-MP-HAUL-DT225 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Differential | 2028-05-02 | 2028-05-04 | 44 hrs | FY28 | 66 | 90003098 | 1 | 1000035157 | 02.05.2028 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-DIFFL | 7500 | 92002 | 7368 | CLB-MP-HAUL-DT182 -FDRSYS-DIFFL90003098
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Seat Operator | 2028-05-03 | 2028-05-03 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000362668 | 03.05.2028 | 14000 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-SEATS | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Cyl Suspension LHF | 2028-05-05 | 2028-05-06 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000067778 | 05.05.2028 | 22000 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYLF | 7500 | 93142 | 8931 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYLF90003121
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Control Cabinet Coolant | 2028-05-06 | 2028-05-06 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000357173 | 06.05.2028 | 15000 | CLB-MP-HAUL-DT5467-ELCTHV-HVCAB-COOLR | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Control Cabinet Coolant | 2028-05-07 | 2028-05-07 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000360846 | 07.05.2028 | 15000 | CLB-MP-HAUL-DT5468-ELCTHV-HVCAB-COOLR | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Seat Operator | 2028-05-07 | 2028-05-07 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000326272 | 07.05.2028 | 14000 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-SEATS | 6500 | 10405 | 1657 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Service Air Conditioner 12M | 2028-05-08 | 2028-05-08 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000349734 | 08.05.2028 | 12 Monthly | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Cyl Steering LH | 2028-05-08 | 2028-05-08 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000036124 | 08.05.2028 | 15000 | CLB-MP-HAUL-DT199 -STRSYS-STRCY-STCYL | 7500 | 85978 | 1801 | CLB-MP-HAUL-DT199 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Final Drive RH | 2028-05-10 | 2028-05-11 | 30 hrs | FY28 | 56 | 90003100 | 1 | 1000034938 | 10.05.2028 | 22000 | CLB-MP-HAUL-DT178 -FDRSYS-FDRVE-FDRRH | 7500 | 81600 | 8737 | CLB-MP-HAUL-DT178 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Steering Link & Arm Rebush | 2028-05-11 | 2028-05-12 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385461 | 11.05.2028 | 30000 | CLB-MP-HAUL-DT194 -STRSYS-STLTR | 7500 | 86451 | 25780 | CLB-MP-HAUL-DT194 -STRSYS-STLTR90038355
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Brake & Steering Manifold | 2028-05-12 | 2028-05-12 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000349049 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-BRKSYS-BRVLV | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Gear Cooler Motor & Pump | 2028-05-12 | 2028-05-12 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000349068 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-FDRSYS-GRSOC-OCPPM | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Pump Airconditioner Drive | 2028-05-12 | 2028-05-12 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000349048 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-ACPMP | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Coupling Drive Pump | 2028-05-12 | 2028-05-12 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000349053 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-HYDPC | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Pump Main Hydraulic | 2028-05-12 | 2028-05-12 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000349076 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-HYPMP | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Cylinder Steering LHS | 2028-05-12 | 2028-05-12 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000349056 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-STRSYS-STRCY-STCYL | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Valve Flow Amplifier | 2028-05-12 | 2028-05-12 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000349067 | 12.05.2028 | 20000 | CLB-MP-HAUL-DT5448-STRSYS-STVLV | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Engine Midlife complete | 2028-05-14 | 2028-05-16 | 51 hrs | FY28 | 83 | 90029500 | A1 | 1000349703 | 14.05.2028 | 17500 | CLB-MP-HAUL-DT5452-ENGINE | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Brake & Steering Manifold | 2028-05-14 | 2028-05-14 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000349093 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-BRKSYS-BRVLV | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Gear Cooler Motor & Pump | 2028-05-14 | 2028-05-14 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000349112 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-FDRSYS-GRSOC-OCPPM | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Pump Airconditioner Drive | 2028-05-14 | 2028-05-14 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000349092 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-ACPMP | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Coupling Drive Pump | 2028-05-14 | 2028-05-14 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000349097 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-HYDPC | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Pump Main Hydraulic | 2028-05-14 | 2028-05-14 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000349120 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-HYPMP | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Cylinder Steering LHS | 2028-05-14 | 2028-05-14 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000349100 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-STRSYS-STRCY-STCYL | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Cylinder Steering RHS | 2028-05-14 | 2028-05-14 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000349101 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-STRSYS-STRCY-STCYR | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Valve Flow Amplifier | 2028-05-14 | 2028-05-14 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000349111 | 14.05.2028 | 20000 | CLB-MP-HAUL-DT5449-STRSYS-STVLV | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Service Air Conditioner 12M | 2028-05-14 | 2028-05-14 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000349091 | 14.05.2028 | 12 Monthly | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Drive Shaft Transmission | 2028-05-14 | 2028-05-14 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154411 | 14.05.2028 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-DRSHT | 7500 | 92088 | 7001 | CLB-MP-HAUL-DT185 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Pump Drive Driveshaft Unis | 2028-05-14 | 2028-05-14 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035319 | 14.05.2028 | 11000 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR-DRSHT | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Suspension LHF | 2028-05-15 | 2028-05-16 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000067906 | 15.05.2028 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYLF | 7500 | 92548 | 7113 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Suspension RHF | 2028-05-15 | 2028-05-16 | 38 hrs | FY28 | 66 | 90003121 | 1 | 1000067908 | 15.05.2028 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYRF | 7500 | 92548 | 8611 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl AOC Fan Motor | 2028-05-15 | 2028-05-15 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000035326 | 15.05.2028 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-MTFAN | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 1Y Air Tank LH External Inspect | 2028-05-15 | 2028-05-15 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389330 | 15.05.2028 | 12 Monthly | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH | 7500 | 92948 | 52765 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 1Y Air Tank RH External Inspect | 2028-05-15 | 2028-05-15 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389332 | 15.05.2028 | 12 Monthly | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH | 7500 | 92948 | 52765 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Cyl Steering LH | 2028-05-16 | 2028-05-16 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000036001 | 16.05.2028 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYL | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Hyd Pump Steering Main | 2028-05-16 | 2028-05-16 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035941 | 16.05.2028 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STPMP | 7500 | 85161 | 19642 | CLB-MP-HAUL-DT196 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Steering HMU | 2028-05-16 | 2028-05-16 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035942 | 16.05.2028 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STHMU | 7500 | 85161 | 1639 | CLB-MP-HAUL-DT196 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Service Air Conditioner | 2028-05-16 | 2028-05-16 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160402 | 16.05.2028 | 5500 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-AIRCN | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Cyl Hoist LH | 2028-05-16 | 2028-05-17 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035527 | 16.05.2028 | 28000 | CLB-MP-HAUL-DT189 -HYDSYS-HOCYL-HCYLL | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Cyl Hoist RH | 2028-05-16 | 2028-05-17 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035528 | 16.05.2028 | 28000 | CLB-MP-HAUL-DT189 -HYDSYS-HOCYL-HCYLR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Steering Accumulator LH | 2028-05-16 | 2028-05-16 | 2 hrs | FY28 | 2 | 90004022 | 1 | 1000082740 | 16.05.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STACC-SACLH | 4200 | 53807 | 7340 | CLB-MP-SUPP-PM0006-STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Steering Accumulator RH | 2028-05-16 | 2028-05-16 | 2 hrs | FY28 | 2 | 90004022 | 1 | 1000082741 | 16.05.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STACC-SACRH | 4200 | 53807 | 7340 | CLB-MP-SUPP-PM0006-STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Steering Link & Arm Rebush | 2028-05-16 | 2028-05-16 | 14 hrs | FY28 | 22 | 90004007 | 1 | 1000082738 | 16.05.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STLTR | 4200 | 53807 | 7340 | CLB-MP-SUPP-PM0006-STRSYS-STLTR90004007
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Steering Cylinder LH | 2028-05-16 | 2028-05-16 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000082736 | 16.05.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STRCY-STCYL | 4200 | 53807 | 7340 | CLB-MP-SUPP-PM0006-STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Steering Cylinder RH | 2028-05-16 | 2028-05-16 | 10 hrs | FY28 | 10 | 90004005 | 1 | 1000082737 | 16.05.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STRCY-STCYR | 4200 | 53807 | 7340 | CLB-MP-SUPP-PM0006-STRSYS-STRCY-STCYR90004005
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 1Y Air Tank LH External Inspect | 2028-05-17 | 2028-05-17 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389434 | 17.05.2028 | 12 Monthly | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH | 7500 | 82302 | 54081 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 1Y Air Tank RH External Inspect | 2028-05-17 | 2028-05-17 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389436 | 17.05.2028 | 12 Monthly | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH | 7500 | 82302 | 54081 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Transmission | 2028-05-17 | 2028-05-18 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000034380 | 17.05.2028 | 22000 | CLB-MP-HAUL-DT168 -TRNSYS-TRANS | 7500 | 93142 | 8669 | CLB-MP-HAUL-DT168 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Transmission | 2028-05-17 | 2028-05-17 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000034382 | 17.05.2028 | 11000 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TMCPP | 7500 | 93142 | 18709 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl AOC Fan Motor | 2028-05-17 | 2028-05-17 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000034388 | 17.05.2028 | 22000 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-MTFAN | 7500 | 93142 | 8682 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 1Y Air Tank LH External Inspect | 2028-05-18 | 2028-05-18 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389346 | 18.05.2028 | 12 Monthly | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH | 7500 | 92088 | 46179 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 1Y Air Tank RH External Inspect | 2028-05-18 | 2028-05-18 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389348 | 18.05.2028 | 12 Monthly | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH | 7500 | 92088 | 46179 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Wheel RH | 2028-05-20 | 2028-05-21 | 33 hrs | FY28 | 61 | 90003105 | 2 | 1000150673 | 20.05.2028 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-AXLES-HUBRH | 7500 | 51346 | 9297 | CLB-MP-HAUL-DT225 -STRUCT-AXLES-HUBRH90003105
T264 | Onsite PM | Haul | Fortescue | DT5476 | DT5476 Overhaul Air Conditioner 24M | 2028-05-21 | 2028-05-23 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000364893 | 21.05.2028 | 24 Monthly | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN | 6500 | 920 | 920 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 1Y Air Tank LH External Inspect | 2028-05-21 | 2028-05-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389322 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH | 7500 | 95233 | 95233 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 1Y Air Tank RH External Inspect | 2028-05-21 | 2028-05-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389324 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH | 7500 | 95233 | 95233 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 1Y Air Tank LH External Inspect | 2028-05-21 | 2028-05-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389450 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH | 7500 | 85715 | 85715 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 1Y Air Tank RH External Inspect | 2028-05-21 | 2028-05-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389452 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH | 7500 | 85715 | 85715 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Cyl Steering RH | 2028-05-21 | 2028-05-21 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000034951 | 21.05.2028 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYR | 7500 | 81600 | 18127 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 1Y Air Tank LH External Inspect | 2028-05-21 | 2028-05-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389426 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH | 7500 | 82926 | 82926 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 1Y Air Tank RH External Inspect | 2028-05-21 | 2028-05-21 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389428 | 21.05.2028 | 12 Monthly | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH | 7500 | 82926 | 82926 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH90038753
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Brake Accumulator | 2028-05-21 | 2028-05-21 | 4 hrs | FY28 | 4 | 90004001 | 1 | 1000044533 | 21.05.2028 | 15000 | CLB-MP-SUPP-WC011 -BRKSYS-BACCM | 5000 | 21040 | 21040 | CLB-MP-SUPP-WC011 -BRKSYS-BACCM90004001
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Engine Midlife Complete | 2028-05-21 | 2028-05-25 | 94 hrs | FY28 | 122 | 90028722 | A1 | 1000289418 | 21.05.2028 | 10000 | CLB-MP-SUPP-WC012 -ENGINE | 5000 | 67273 | 20856 | CLB-MP-SUPP-WC012 -ENGINE90028722
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Overhaul Airconditioner | 2028-05-21 | 2028-05-22 | 24 hrs | FY28 | 24 | 90028727 | A1 | 1000289420 | 21.05.2028 | 10000 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN | 5000 | 67273 | 10760 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN90028727
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Cyl Steering LH | 2028-05-22 | 2028-05-22 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000034785 | 22.05.2028 | 15000 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYL | 7500 | 82722 | 16512 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYL90003111
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Seat Operator | 2028-05-23 | 2028-05-23 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000362713 | 23.05.2028 | 14000 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-SEATS | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Brake & Steering Manifold | 2028-05-24 | 2028-05-24 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000349736 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-BRKSYS-BRVLV | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Gear Cooler Motor & Pump | 2028-05-24 | 2028-05-24 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000349955 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-FDRSYS-GRSOC-OCPPM | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Pump Airconditioner Drive | 2028-05-24 | 2028-05-24 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000349735 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-ACPMP | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Coupling Drive Pump | 2028-05-24 | 2028-05-24 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000349940 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-HYDPC | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Pump Main Hydraulic | 2028-05-24 | 2028-05-24 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000349963 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-HYPMP | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Cylinder Steering RHS | 2028-05-24 | 2028-05-24 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000349944 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-STRSYS-STRCY-STCYR | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Valve Flow Amplifier | 2028-05-24 | 2028-05-24 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000349954 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5453-STRSYS-STVLV | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Brake & Steering Manifold | 2028-05-24 | 2028-05-24 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000349594 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-BRKSYS-BRVLV | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Gear Cooler Motor & Pump | 2028-05-24 | 2028-05-24 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000349613 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-FDRSYS-GRSOC-OCPPM | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Pump Airconditioner Drive | 2028-05-24 | 2028-05-24 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000349593 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-ACPMP | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Coupling Drive Pump | 2028-05-24 | 2028-05-24 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000349598 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-HYDPC | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Pump Main Hydraulic | 2028-05-24 | 2028-05-24 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000349621 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-HYPMP | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Cylinder Steering LHS | 2028-05-24 | 2028-05-24 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000349601 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-STRSYS-STRCY-STCYL | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Cylinder Steering RHS | 2028-05-24 | 2028-05-24 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000349602 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-STRSYS-STRCY-STCYR | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Valve Flow Amplifier | 2028-05-24 | 2028-05-24 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000349612 | 24.05.2028 | 20000 | CLB-MP-HAUL-DT5451-STRSYS-STVLV | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Service Air Conditioner | 2028-05-24 | 2028-05-24 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160382 | 24.05.2028 | 5500 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-AIRCN | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Hyd Pump Steering Main | 2028-05-25 | 2028-05-25 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035059 | 25.05.2028 | 15000 | CLB-MP-HAUL-DT180 -STRSYS-STPMP | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Steering HMU | 2028-05-25 | 2028-05-25 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035060 | 25.05.2028 | 15000 | CLB-MP-HAUL-DT180 -STRSYS-STHMU | 7500 | 89560 | 1469 | CLB-MP-HAUL-DT180 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Steering Link & Arm Rebush | 2028-05-25 | 2028-05-26 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385433 | 25.05.2028 | 30000 | CLB-MP-HAUL-DT180 -STRSYS-STLTR | 7500 | 89560 | 23548 | CLB-MP-HAUL-DT180 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Brake Control | 2028-05-27 | 2028-05-27 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000035822 | 27.05.2028 | 11000 | CLB-MP-HAUL-DT194 -BRKSYS-HYFPP | 7500 | 86451 | 8189 | CLB-MP-HAUL-DT194 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 1Y Air Tank LH External Inspect | 2028-05-28 | 2028-05-28 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389406 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH | 7500 | 83734 | 10797 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 1Y Air Tank RH External Inspect | 2028-05-28 | 2028-05-28 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389408 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH | 7500 | 83734 | 10797 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 1Y Air Tank LH External Inspect | 2028-05-28 | 2028-05-28 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389418 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH | 7500 | 86814 | 15453 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 1Y Air Tank RH External Inspect | 2028-05-28 | 2028-05-28 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389420 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH | 7500 | 86814 | 15453 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 1Y Air Tank LH External Inspect | 2028-05-28 | 2028-05-28 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389350 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH | 7500 | 82388 | 82388 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 1Y Air Tank RH External Inspect | 2028-05-28 | 2028-05-28 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389352 | 28.05.2028 | 12 Monthly | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH | 7500 | 82388 | 82388 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH90038753
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Steering Link & Arm Rebush | 2028-05-29 | 2028-05-29 | 14 hrs | FY28 | 22 | 90004007 | 1 | 1000044797 | 29.05.2028 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STLTR | 5000 | 67897 | 51 | CLB-MP-SUPP-WC015 -STRSYS-STLTR90004007
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Cyl Steering LH | 2028-05-30 | 2028-05-30 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000034840 | 30.05.2028 | 15000 | CLB-MP-HAUL-DT176 -STRSYS-STRCY-STCYL | 7500 | 85284 | 1339 | CLB-MP-HAUL-DT176 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Cyl Steering RH | 2028-05-30 | 2028-05-30 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000034841 | 30.05.2028 | 15000 | CLB-MP-HAUL-DT176 -STRSYS-STRCY-STCYR | 7500 | 85284 | 1339 | CLB-MP-HAUL-DT176 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Steering Link & Arm Rebush | 2028-05-30 | 2028-05-31 | 27 hrs | FY28 | 45 | 90038355 | A1 | 1000385425 | 30.05.2028 | 30000 | CLB-MP-HAUL-DT176 -STRSYS-STLTR | 7500 | 85284 | 19786 | CLB-MP-HAUL-DT176 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 1Y Air Tank LH External Inspect | 2028-05-31 | 2028-05-31 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389374 | 31.05.2028 | 12 Monthly | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH | 7500 | 83820 | 11121 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 1Y Air Tank RH External Inspect | 2028-05-31 | 2028-05-31 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389376 | 31.05.2028 | 12 Monthly | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH | 7500 | 83820 | 11121 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Overhaul Air Conditioner 24M | 2028-05-31 | 2028-06-02 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000314527 | 31.05.2028 | 24 Monthly | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN90029460
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Water Cannon Inspect | 2028-06-01 | 2028-06-01 | 3 hrs | FY28 | 3 | 90033661 | A1 | 1000338790 | 01.06.2028 | 6 Monthly | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | 5000 | 67273 | 3900 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Transmission | 2028-06-02 | 2028-06-03 | 28 hrs | FY28 | 48 | 90003093 | 1 | 1000035208 | 02.06.2028 | 22000 | CLB-MP-HAUL-DT183 -TRNSYS-TRANS | 7500 | 90364 | 8227 | CLB-MP-HAUL-DT183 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Pump Torque Converter Charge | 2028-06-02 | 2028-06-02 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080205 | 02.06.2028 | 22000 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TCCPP | 7500 | 90364 | 8227 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Ovhl Axle A Frame | 2028-06-02 | 2028-06-03 | 36 hrs | FY28 | 60 | 90015390 | 1 | 1000130643 | 02.06.2028 | 22000 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-AFRME | 7500 | 90182 | 90182 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 1Y Air Tank LH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389394 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH | 7500 | 91826 | 53019 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 1Y Air Tank RH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389396 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH | 7500 | 91826 | 53019 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 1Y Air Tank LH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389386 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH | 7500 | 90227 | 40762 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 1Y Air Tank RH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389388 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH | 7500 | 90227 | 40762 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 1Y Air Tank LH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389438 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH | 7500 | 84897 | 84897 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 1Y Air Tank RH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389440 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH | 7500 | 84897 | 84897 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 1Y Air Tank LH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389454 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH | 7500 | 92315 | 50047 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 1Y Air Tank RH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389456 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH | 7500 | 92315 | 50047 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 1Y Air Tank LH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389414 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH | 7500 | 90436 | 17328 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 1Y Air Tank RH External Inspect | 2028-06-04 | 2028-06-04 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389416 | 04.06.2028 | 12 Monthly | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH | 7500 | 90436 | 17328 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Engine Pump Drive | 2028-06-04 | 2028-06-05 | 32 hrs | FY28 | 62 | 90003089 | 1 | 1000034655 | 04.06.2028 | 22000 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR | 7500 | 82651 | 8157 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR90003089
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Service Air Conditioner 12M | 2028-06-05 | 2028-06-05 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000350384 | 05.06.2028 | 12 Monthly | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN90029300
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Adjust Engine Valve Set | 2028-06-05 | 2028-06-05 | 6 hrs | FY28 | 6 | 90017451 | A1 | 1000290598 | 05.06.2028 | 3000 | CLB-MP-SUPP-SV020 -ENGINE | 3300 | 44025 | 8900 | CLB-MP-SUPP-SV020 -ENGINE90017451
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Pump Hoist & Brake | 2028-06-06 | 2028-06-06 | 10 hrs | FY28 | 10 | 90003113 | 1 | 1000035946 | 06.06.2028 | 22000 | CLB-MP-HAUL-DT196 -HYDSYS-HOPMP | 7500 | 85161 | 8200 | CLB-MP-HAUL-DT196 -HYDSYS-HOPMP90003113
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Brake & Steering Manifold | 2028-06-07 | 2028-06-07 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000350386 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-BRKSYS-BRVLV | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Gear Cooler Motor & Pump | 2028-06-07 | 2028-06-07 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000350405 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-FDRSYS-GRSOC-OCPPM | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Pump Airconditioner Drive | 2028-06-07 | 2028-06-07 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000350385 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-ACPMP | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Coupling Drive Pump | 2028-06-07 | 2028-06-07 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000350390 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-HYDPC | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Pump Main Hydraulic | 2028-06-07 | 2028-06-07 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000350413 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-HYPMP | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Cylinder Steering LHS | 2028-06-07 | 2028-06-07 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000350393 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-STRSYS-STRCY-STCYL | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Cylinder Steering RHS | 2028-06-07 | 2028-06-07 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000350394 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-STRSYS-STRCY-STCYR | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Valve Flow Amplifier | 2028-06-07 | 2028-06-07 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000350404 | 07.06.2028 | 20000 | CLB-MP-HAUL-DT5454-STRSYS-STVLV | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Pump Torque Converter Charge | 2028-06-07 | 2028-06-07 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080218 | 07.06.2028 | 22000 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TCCPP | 7500 | 86259 | 8210 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Final Drive RH | 2028-06-09 | 2028-06-10 | 30 hrs | FY28 | 56 | 90003100 | 1 | 1000035931 | 09.06.2028 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-FDRVE-FDRRH | 7500 | 85161 | 8155 | CLB-MP-HAUL-DT196 -FDRSYS-FDRVE-FDRRH90003100
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Cyl Hoist LH | 2028-06-09 | 2028-06-10 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000035947 | 09.06.2028 | 28000 | CLB-MP-HAUL-DT196 -HYDSYS-HOCYL-HCYLL | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Cyl Hoist RH | 2028-06-09 | 2028-06-10 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000035948 | 09.06.2028 | 28000 | CLB-MP-HAUL-DT196 -HYDSYS-HOCYL-HCYLR | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Rear Axle Cooling Fan Motor | 2028-06-09 | 2028-06-09 | 2 hrs | FY28 | 2 | 90003997 | 1 | 1000044656 | 09.06.2028 | 10000 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-MTFAN | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Rear Axle Oil Pump | 2028-06-09 | 2028-06-09 | 2 hrs | FY28 | 2 | 90003996 | 1 | 1000044655 | 09.06.2028 | 10000 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-HYPUM | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-HYPUM90003996
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Control Cabinet Coolant | 2028-06-09 | 2028-06-09 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000339726 | 09.06.2028 | 15000 | CLB-MP-HAUL-DT5440-ELCTHV-HVCAB-COOLR | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-ELCTHV-HVCAB-COOLR90033128
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl PTO Uni's & Driveshaft | 2028-06-10 | 2028-06-10 | 2 hrs | FY28 | 2 | 90031094 | A1 | 1000307806 | 10.06.2028 | 10000 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT | 5000 | 63833 | 10962 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT90031094
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Brake Accumulator | 2028-06-11 | 2028-06-11 | 4 hrs | FY28 | 4 | 90004001 | 1 | 1000044789 | 11.06.2028 | 15000 | CLB-MP-SUPP-WC015 -BRKSYS-BACCM | 5000 | 67897 | 20934 | CLB-MP-SUPP-WC015 -BRKSYS-BACCM90004001
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Valve Steering & AHS EH | 2028-06-15 | 2028-06-15 | 10 hrs | FY28 | 10 | 90009881 | 1 | 1000078405 | 15.06.2028 | 22000 | CLB-MP-HAUL-DT166 -STRSYS-STVLV | 7500 | 95491 | 8004 | CLB-MP-HAUL-DT166 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Cyl Steering LH | 2028-06-15 | 2028-06-15 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000035005 | 15.06.2028 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYL | 7500 | 84079 | 16016 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 1Y Air Tank LH External Inspect | 2028-06-16 | 2028-06-16 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389370 | 16.06.2028 | 12 Monthly | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH | 7500 | 81378 | 16017 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 1Y Air Tank RH External Inspect | 2028-06-16 | 2028-06-16 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389372 | 16.06.2028 | 12 Monthly | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH | 7500 | 81378 | 16017 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Cyl Hoist LH | 2028-06-17 | 2028-06-18 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000034844 | 17.06.2028 | 28000 | CLB-MP-HAUL-DT176 -HYDSYS-HOCYL-HCYLL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Cyl Hoist RH | 2028-06-17 | 2028-06-18 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000034845 | 17.06.2028 | 28000 | CLB-MP-HAUL-DT176 -HYDSYS-HOCYL-HCYLR | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Wheel RH | 2028-06-17 | 2028-06-18 | 33 hrs | FY28 | 61 | 90003105 | 2 | 1000036052 | 17.06.2028 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-AXLES-HUBRH | 7500 | 88680 | 7985 | CLB-MP-HAUL-DT198 -STRUCT-AXLES-HUBRH90003105
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Auto Lube Pump | 2028-06-17 | 2028-06-17 | 4 hrs | FY28 | 4 | 90003064 | A1 | 1000033885 | 17.06.2028 | 6000 | CLB-MP-SUPP-SV019 -GRSYST-ALBPP | 2500 | 48856 | 6928 | CLB-MP-SUPP-SV019 -GRSYST-ALBPP90003064
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Service Air Conditioner 12M | 2028-06-18 | 2028-06-18 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000357054 | 18.06.2028 | 12 Monthly | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Brake & Steering Manifold | 2028-06-18 | 2028-06-18 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000350430 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-BRKSYS-BRVLV | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Gear Cooler Motor & Pump | 2028-06-18 | 2028-06-18 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000350449 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-FDRSYS-GRSOC-OCPPM | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Pump Airconditioner Drive | 2028-06-18 | 2028-06-18 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000350429 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-ACPMP | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Coupling Drive Pump | 2028-06-18 | 2028-06-18 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000350434 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-HYDPC | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Pump Main Hydraulic | 2028-06-18 | 2028-06-18 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000350457 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-HYPMP | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Cylinder Steering RHS | 2028-06-18 | 2028-06-18 | 8 hrs | FY28 | 14 | 90029374 | A2 | 1000350438 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-STRSYS-STRCY-STCYR | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Valve Flow Amplifier | 2028-06-18 | 2028-06-18 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000350448 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5455-STRSYS-STVLV | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Service Air Conditioner 12M | 2028-06-18 | 2028-06-18 | 12 hrs | FY28 | 12 | 90029300 | A1 | 1000349592 | 18.06.2028 | 12 Monthly | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Brake & Steering Manifold | 2028-06-18 | 2028-06-18 | 12 hrs | FY28 | 24 | 90029368 | A1 | 1000346993 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-BRKSYS-BRVLV | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Gear Cooler Motor & Pump | 2028-06-18 | 2028-06-18 | 6 hrs | FY28 | 6 | 90029363 | A1 | 1000347012 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-FDRSYS-GRSOC-OCPPM | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Pump Airconditioner Drive | 2028-06-18 | 2028-06-18 | 2 hrs | FY28 | 2 | 90029365 | A1 | 1000346992 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-ACPMP | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Coupling Drive Pump | 2028-06-18 | 2028-06-18 | 3 hrs | FY28 | 3 | 90029361 | A1 | 1000346997 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-HYDPC | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Pump Main Hydraulic | 2028-06-18 | 2028-06-18 | 6 hrs | FY28 | 12 | 90029366 | A1 | 1000347020 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-HYPMP | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Cylinder Steering LHS | 2028-06-18 | 2028-06-18 | 8 hrs | FY28 | 14 | 90029373 | A2 | 1000347000 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-STRSYS-STRCY-STCYL | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Valve Flow Amplifier | 2028-06-18 | 2028-06-18 | 2 hrs | FY28 | 2 | 90029367 | A1 | 1000347011 | 18.06.2028 | 20000 | CLB-MP-HAUL-DT5445-STRSYS-STVLV | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 1Y Air Tank LH External Inspect | 2028-06-18 | 2028-06-18 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389378 | 18.06.2028 | 12 Monthly | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH | 7500 | 89376 | 46929 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 1Y Air Tank RH External Inspect | 2028-06-18 | 2028-06-18 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389380 | 18.06.2028 | 12 Monthly | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH | 7500 | 89376 | 46929 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Cyl Suspension RHR | 2028-06-18 | 2028-06-19 | 23 hrs | FY28 | 42 | 90003122 | 1 | 1000035186 | 18.06.2028 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYRR | 7500 | 92002 | 36584 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Final Drive RH | 2028-06-19 | 2028-06-20 | 30 hrs | FY28 | 56 | 90003100 | 1 | 1000035159 | 19.06.2028 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-FDRVE-FDRRH | 7500 | 92002 | 7959 | CLB-MP-HAUL-DT182 -FDRSYS-FDRVE-FDRRH90003100
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Wheel Assembly LHF | 2028-06-19 | 2028-06-20 | 18 hrs | FY28 | 34 | 90029369 | A1 | 1000326673 | 19.06.2028 | 24000 | CLB-MP-HAUL-DT5419-STRUCT-AXLES-HUBLH | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Wheel Assembly RHF | 2028-06-19 | 2028-06-20 | 18 hrs | FY28 | 34 | 90029370 | A1 | 1000326674 | 19.06.2028 | 24000 | CLB-MP-HAUL-DT5419-STRUCT-AXLES-HUBRH | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5477 | DT5477 Overhaul Air Conditioner 24M | 2028-06-20 | 2028-06-22 | 48 hrs | FY28 | 48 | 90029460 | A1 | 1000365184 | 20.06.2028 | 24 Monthly | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN | 6500 | 630 | 630 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Cyl Hoist LH | 2028-06-20 | 2028-06-21 | 25 hrs | FY28 | 49 | 90003114 | 1 | 1000034624 | 20.06.2028 | 28000 | CLB-MP-HAUL-DT172 -HYDSYS-HOCYL-HCYLL | 7500 | 92351 | 13766 | CLB-MP-HAUL-DT172 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Cyl Hoist RH | 2028-06-20 | 2028-06-21 | 25 hrs | FY28 | 49 | 90003114 | 2 | 1000034625 | 20.06.2028 | 28000 | CLB-MP-HAUL-DT172 -HYDSYS-HOCYL-HCYLR | 7500 | 92351 | 13766 | CLB-MP-HAUL-DT172 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Final Drive LH | 2028-06-20 | 2028-06-21 | 30 hrs | FY28 | 56 | 90003099 | 1 | 1000035930 | 20.06.2028 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-FDRVE-FDRLH | 7500 | 85161 | 7457 | CLB-MP-HAUL-DT196 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 1Y Air Tank LH External Inspect | 2028-06-20 | 2028-06-20 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389358 | 20.06.2028 | 12 Monthly | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH | 7500 | 82478 | 82478 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 1Y Air Tank RH External Inspect | 2028-06-20 | 2028-06-20 | 1.5 hrs | FY28 | 1.5 | 90038753 | A1 | 1000389360 | 20.06.2028 | 12 Monthly | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH | 7500 | 82478 | 82478 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Drive Shaft Transmission | 2028-06-22 | 2028-06-22 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154421 | 22.06.2028 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-DRSHT | 7500 | 90698 | 7441 | CLB-MP-HAUL-DT190 -FDRSYS-DRSHT90017134
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Water Cannon | 2028-06-22 | 2028-06-22 | 12 hrs | FY28 | 24 | 90015535 | 1 | 1000133451 | 22.06.2028 | 12 Monthly | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | 5000 | 64118 | 9073 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON90015535
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Wheel Assembly LHF | 2028-06-24 | 2028-06-25 | 18 hrs | FY28 | 34 | 90029369 | A1 | 1000314086 | 24.06.2028 | 24000 | CLB-MP-HAUL-DT5405-STRUCT-AXLES-HUBLH | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Wheel Assembly RHF | 2028-06-24 | 2028-06-25 | 18 hrs | FY28 | 34 | 90029370 | A1 | 1000314087 | 24.06.2028 | 24000 | CLB-MP-HAUL-DT5405-STRUCT-AXLES-HUBRH | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Service Air Conditioner | 2028-06-24 | 2028-06-24 | 12 hrs | FY28 | 12 | 90017450 | 1 | 1000160399 | 24.06.2028 | 5500 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-AIRCN | 7500 | 83140 | 6169 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Brake Oil Cooler Front | 2028-06-24 | 2028-06-24 | 6 hrs | FY28 | 6 | 90004002 | 1 | 1000044534 | 24.06.2028 | 20000 | CLB-MP-SUPP-WC011 -BRKSYS-BROCO-BROCF | 5000 | 64118 | 10138 | CLB-MP-SUPP-WC011 -BRKSYS-BROCO-BROCF90004002
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Steering HMU | 2028-06-25 | 2028-06-25 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000036182 | 25.06.2028 | 15000 | CLB-MP-HAUL-DT200 -STRSYS-STHMU | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Steering LH | 2028-06-25 | 2028-06-25 | 16 hrs | FY28 | 28 | 90003111 | 2 | 1000036183 | 25.06.2028 | 15000 | CLB-MP-HAUL-DT200 -STRSYS-STRCY-STCYL | 7500 | 92548 | 769 | CLB-MP-HAUL-DT200 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Hyd Pump Steering Main | 2028-06-26 | 2028-06-26 | 8 hrs | FY28 | 8 | 90003109 | 1 | 1000035465 | 26.06.2028 | 15000 | CLB-MP-HAUL-DT188 -STRSYS-STPMP | 7500 | 83931 | 797 | CLB-MP-HAUL-DT188 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Steering HMU | 2028-06-26 | 2028-06-26 | 14 hrs | FY28 | 14 | 90003110 | 1 | 1000035466 | 26.06.2028 | 15000 | CLB-MP-HAUL-DT188 -STRSYS-STHMU | 7500 | 83931 | 797 | CLB-MP-HAUL-DT188 -STRSYS-STHMU90003110
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Wheel Assembly LHF | 2028-06-26 | 2028-06-27 | 18 hrs | FY28 | 34 | 90029369 | A1 | 1000326418 | 26.06.2028 | 24000 | CLB-MP-HAUL-DT5417-STRUCT-AXLES-HUBLH | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Wheel Assembly RHF | 2028-06-26 | 2028-06-27 | 18 hrs | FY28 | 34 | 90029370 | A1 | 1000326419 | 26.06.2028 | 24000 | CLB-MP-HAUL-DT5417-STRUCT-AXLES-HUBRH | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Seat Operator | 2028-06-27 | 2028-06-27 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000371452 | 27.06.2028 | 14000 | CLB-MP-HAUL-DT5485-STRUCT-CABIN-SEATS | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Pump Drive Driveshaft Unis | 2028-06-28 | 2028-06-28 | 4 hrs | FY28 | 4 | 90009874 | 1 | 1000035694 | 28.06.2028 | 11000 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR-DRSHT | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Pump Brake Control | 2028-06-28 | 2028-06-28 | 5 hrs | FY28 | 5 | 90003106 | 1 | 1000035706 | 28.06.2028 | 11000 | CLB-MP-HAUL-DT192 -BRKSYS-HYFPP | 7500 | 91174 | 19917 | CLB-MP-HAUL-DT192 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Cyl Steering RH | 2028-06-28 | 2028-06-28 | 16 hrs | FY28 | 28 | 90003111 | 3 | 1000035828 | 28.06.2028 | 15000 | CLB-MP-HAUL-DT194 -STRSYS-STRCY-STCYR | 7500 | 86451 | 56 | CLB-MP-HAUL-DT194 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl AOC Fan Motor | 2028-06-28 | 2028-06-28 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000034443 | 28.06.2028 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-MTFAN | 7500 | 93410 | 7769 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-MTFAN90003102
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Air Con System Overhaul | 2028-06-28 | 2028-06-29 | 18 hrs | FY28 | 18 | 90028737 | A1 | 1000286364 | 28.06.2028 | 24 Monthly | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN | 3500 | 91736 | 186 | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN90028737
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Control Cabinet Coolant | 2028-06-28 | 2028-06-28 | 1 hr | FY28 | 1 | 90033128 | A1 | 1000362675 | 28.06.2028 | 15000 | CLB-MP-HAUL-DT5471-ELCTHV-HVCAB-COOLR | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Seat Operator | 2028-06-28 | 2028-06-28 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000371381 | 28.06.2028 | 14000 | CLB-MP-HAUL-DT5484-STRUCT-CABIN-SEATS | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Seat Operator | 2028-06-28 | 2028-06-28 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000369116 | 28.06.2028 | 14000 | CLB-MP-HAUL-DT5483-STRUCT-CABIN-SEATS | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Seat Operator | 2028-06-28 | 2028-06-28 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000366500 | 28.06.2028 | 14000 | CLB-MP-HAUL-DT5481-STRUCT-CABIN-SEATS | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Seat Operator | 2028-06-28 | 2028-06-28 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000365705 | 28.06.2028 | 14000 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-SEATS | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Torque Converter | 2028-06-29 | 2028-06-30 | 32 hrs | FY28 | 62 | 90003092 | 1 | 1000034434 | 29.06.2028 | 22000 | CLB-MP-HAUL-DT169 -TRNSYS-TRQUE | 7500 | 93410 | 7748 | CLB-MP-HAUL-DT169 -TRNSYS-TRQUE90003092
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Pump Torque Converter Charge | 2028-06-29 | 2028-06-29 | 5 hrs | FY28 | 5 | 90003095 | 1 | 1000080165 | 29.06.2028 | 22000 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TCCPP | 7500 | 93410 | 7748 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Drive Shaft Transmission | 2028-06-29 | 2028-06-29 | 8 hrs | FY28 | 16 | 90017134 | 1 | 1000154379 | 29.06.2028 | 22000 | CLB-MP-HAUL-DT169 -FDRSYS-DRSHT | 7500 | 93410 | 29987 | CLB-MP-HAUL-DT169 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Brake Wheel LH | 2028-06-29 | 2028-06-30 | 32 hrs | FY28 | 38 | 90003104 | 2 | 1000034445 | 29.06.2028 | 22000 | CLB-MP-HAUL-DT169 -STRUCT-AXLES-HUBLH | 7500 | 93410 | 7748 | CLB-MP-HAUL-DT169 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Pump Transmission | 2028-06-30 | 2028-06-30 | 7 hrs | FY28 | 7 | 90003096 | 1 | 1000035695 | 30.06.2028 | 11000 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TMCPP | 7500 | 91174 | 7657 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl AOC Fan Motor | 2028-06-30 | 2028-06-30 | 5 hrs | FY28 | 5 | 90003102 | 1 | 1000035701 | 30.06.2028 | 22000 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-MTFAN | 7500 | 91174 | 7657 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-MTFAN90003102
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000377279 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5500-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000376492 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5499-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000375567 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5498-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000375434 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5497-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000374057 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5496-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000374006 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5495-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000373618 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5494-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000373360 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5493-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000373106 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5492-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000372737 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5491-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000367597 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5482-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000366365 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5480-STRUCT-CABIN-SEATS | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Seat Operator | 2028-06-30 | 2028-06-30 | 2 hrs | FY28 | 2 | 90029285 | A1 | 1000365655 | 30.06.2028 | 14000 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-SEATS90029285
| Onsite PM | Haul | Fortescue |  | FY29 - HAUL - COMPONENTS DURING PM | 2028-07-01 |  |  | FY29
| Onsite PM | Haul | Fortescue | MOC | MAJOR ON CONDITION | 2028-07-01 | 2029-06-30 | 364 days | FY29
| Onsite PM | Haul | Fortescue | MOC | AUGUST | 2028-08-01 | 2028-08-31 | 30 days | FY29
| Onsite PM | Haul | Fortescue | MOC | SEPTEMBER | 2028-09-01 | 2028-09-30 | 29 days | FY29
| Onsite PM | Haul | Fortescue | MOC | OCTOBER | 2028-10-01 | 2028-10-31 | 30 days | FY29
| Onsite PM | Haul | Fortescue | MOC | NOVEMBER | 2028-11-01 | 2028-11-30 | 29 days | FY29
| Onsite PM | Haul | Fortescue | MOC | DECEMBER | 2028-12-01 | 2028-12-31 | 30 days | FY29
| Onsite PM | Haul | Fortescue | MOC | JANUARY | 2029-01-01 | 2029-01-31 | 30 days | FY29
| Onsite PM | Haul | Fortescue | MOC | FEBRUARY | 2029-02-01 | 2029-02-28 | 27 days | FY29
| Onsite PM | Haul | Fortescue | MOC | MARCH | 2029-03-01 | 2029-03-31 | 30 days | FY29
| Onsite PM | Haul | Fortescue | MOC | APRIL | 2029-04-01 | 2029-04-30 | 29 days | FY29
| Onsite PM | Haul | Fortescue | MOC | MAY | 2029-05-01 | 2029-05-31 | 30 days | FY29
| Onsite PM | Haul | Fortescue | MOC | JUNE | 2029-06-01 | 2029-06-30 | 29 days | FY29
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Hyd Pump Steering Main | 2028-07-01 | 2028-07-01 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035521 | 01.07.2028 | 15000 | CLB-MP-HAUL-DT189 -STRSYS-STPMP | 7500 | 84546 | 718 | CLB-MP-HAUL-DT189 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Cyl Steering LH | 2028-07-01 | 2028-07-01 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000035523 | 01.07.2028 | 15000 | CLB-MP-HAUL-DT189 -STRSYS-STRCY-STCYL | 7500 | 84546 | 745 | CLB-MP-HAUL-DT189 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Cyl Steering RH | 2028-07-01 | 2028-07-01 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035524 | 01.07.2028 | 15000 | CLB-MP-HAUL-DT189 -STRSYS-STRCY-STCYR | 7500 | 84546 | 745 | CLB-MP-HAUL-DT189 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Pump Hoist & Brake | 2028-07-02 | 2028-07-02 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035064 | 02.07.2028 | 22000 | CLB-MP-HAUL-DT180 -HYDSYS-HOPMP | 7500 | 89560 | 7705 | CLB-MP-HAUL-DT180 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Cyl Suspension LHF | 2028-07-03 | 2028-07-04 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067826 | 03.07.2028 | 22000 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYLF | 7500 | 89560 | 7664 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYLF90003121
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Brake Oil Cooler Front | 2028-07-03 | 2028-07-03 | 4 hrs | FY29 | 4 | 90030665 | A1 | 1000082731 | 03.07.2028 | 24000 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BROCF | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BROCF90030665
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Engine | 2028-07-03 | 2028-07-07 | 108 hrs | FY29 | 406 | 90028979 | A1 | 1000289405 | 03.07.2028 | 24000 | CLB-MP-SUPP-PM0006-ENGINE | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-ENGINE90028979
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Hub & Spindle LH | 2028-07-03 | 2028-07-04 | 26 hrs | FY29 | 50 | 90004020 | 1 | 1000082726 | 03.07.2028 | 24000 | CLB-MP-SUPP-PM0006-STRUCT-AXLES-HUBLH | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-STRUCT-AXLES-HUBLH90004020
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Repl Hub & Spindle RH | 2028-07-03 | 2028-07-04 | 26 hrs | FY29 | 50 | 90026194 | A1 | 1000082727 | 03.07.2028 | 24000 | CLB-MP-SUPP-PM0006-STRUCT-AXLES-HUBRH | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-STRUCT-AXLES-HUBRH90026194
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Overhaul Airconditioner | 2028-07-03 | 2028-07-04 | 24 hrs | FY29 | 24 | 90028993 | A1 | 1000289408 | 03.07.2028 | 12000 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-AIRCN | 4200 | 53807 | 3537 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-AIRCN90028993
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Seat Operator | 2028-07-04 | 2028-07-04 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000371571 | 04.07.2028 | 14000 | CLB-MP-HAUL-DT5486-STRUCT-CABIN-SEATS | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-STRUCT-CABIN-SEATS90029285
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 1Y Air Tank External Inspect | 2028-07-05 | 2028-07-05 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389210 | 05.07.2028 | 12 Monthly | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK | 4200 | 53807 | 16976 | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK90038749
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 1Y Air Tank External Inspect | 2028-07-05 | 2028-07-05 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389212 | 05.07.2028 | 12 Monthly | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK90038749
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Seat Operators | 2028-07-05 | 2028-07-05 | 4 hrs | FY29 | 4 | 90004012 | 1 | 1000161839 | 05.07.2028 | 10000 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-SEATS | 5000 | 67273 | 10220 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-SEATS90004012
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Seat Operator | 2028-07-05 | 2028-07-05 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000361793 | 05.07.2028 | 14000 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-SEATS | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Service Air Conditioner 12M | 2028-07-06 | 2028-07-06 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000357138 | 06.07.2028 | 12 Monthly | CLB-MP-HAUL-DT5467-STRUCT-CABIN-AIRCN | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Transmission Oil Cooler | 2028-07-06 | 2028-07-06 | 13 hrs | FY29 | 13 | 90003532 | 1 | 1000041002 | 06.07.2028 | 22000 | CLB-MP-HAUL-DT193 -TRNSYS-TROLC | 7500 | 83140 | 7523 | CLB-MP-HAUL-DT193 -TRNSYS-TROLC90003532
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Seat Operator | 2028-07-06 | 2028-07-06 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000361840 | 06.07.2028 | 14000 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-SEATS | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Seat Operator | 2028-07-07 | 2028-07-07 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000313945 | 07.07.2028 | 14000 | CLB-MP-HAUL-DT5404-STRUCT-CABIN-SEATS | 6500 | 8870 | 1481 | CLB-MP-HAUL-DT5404-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Wheel Assembly LHF | 2028-07-08 | 2028-07-09 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000300366 | 08.07.2028 | 24000 | CLB-MP-HAUL-DT5391-STRUCT-AXLES-HUBLH | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Wheel Assembly RHF | 2028-07-08 | 2028-07-09 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000300367 | 08.07.2028 | 24000 | CLB-MP-HAUL-DT5391-STRUCT-AXLES-HUBRH | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Differential | 2028-07-08 | 2028-07-10 | 44 hrs | FY29 | 66 | 90003098 | 1 | 1000035212 | 08.07.2028 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-DIFFL | 7500 | 90364 | 5008 | CLB-MP-HAUL-DT183 -FDRSYS-DIFFL90003098
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Transmission | 2028-07-08 | 2028-07-09 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000036041 | 08.07.2028 | 22000 | CLB-MP-HAUL-DT198 -TRNSYS-TRANS | 7500 | 88680 | 7548 | CLB-MP-HAUL-DT198 -TRNSYS-TRANS90003093
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Steering Oil Cooler | 2028-07-08 | 2028-07-08 | 5 hrs | FY29 | 5 | 90004006 | 1 | 1000082739 | 08.07.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STOLC | 4200 | 53807 | 6738 | CLB-MP-SUPP-PM0006-STRSYS-STOLC90004006
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Seat Operator | 2028-07-08 | 2028-07-08 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000381340 | 08.07.2028 | 14000 | CLB-MP-HAUL-DT5504-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Seat Operator | 2028-07-08 | 2028-07-08 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000381272 | 08.07.2028 | 14000 | CLB-MP-HAUL-DT5503-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Cyl Steering LH | 2028-07-09 | 2028-07-09 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034178 | 09.07.2028 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYL | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Cyl Steering RH | 2028-07-09 | 2028-07-09 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034179 | 09.07.2028 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYR | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYR90003111
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Brake & Steering Manifold | 2028-07-10 | 2028-07-10 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000349645 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-BRKSYS-BRVLV | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Gear Cooler Motor & Pump | 2028-07-10 | 2028-07-10 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000349664 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-FDRSYS-GRSOC-OCPPM | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Pump Airconditioner Drive | 2028-07-10 | 2028-07-10 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000349644 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-ACPMP | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Coupling Drive Pump | 2028-07-10 | 2028-07-10 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000349649 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-HYDPC | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Pump Main Hydraulic | 2028-07-10 | 2028-07-10 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000349672 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-HYPMP | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Cylinder Steering LHS | 2028-07-10 | 2028-07-10 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000349652 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-STRSYS-STRCY-STCYL | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Cylinder Steering RHS | 2028-07-10 | 2028-07-10 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000349653 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-STRSYS-STRCY-STCYR | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Valve Flow Amplifier | 2028-07-10 | 2028-07-10 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000349663 | 10.07.2028 | 20000 | CLB-MP-HAUL-DT5450-STRSYS-STVLV | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Cyl Steering LH | 2028-07-10 | 2028-07-10 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034675 | 10.07.2028 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYL | 7500 | 82651 | 15446 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Hyd Pump Steering Main | 2028-07-11 | 2028-07-11 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034176 | 11.07.2028 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STPMP | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Steering HMU | 2028-07-11 | 2028-07-11 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000034177 | 11.07.2028 | 15000 | CLB-MP-HAUL-DT164 -STRSYS-STHMU | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Torque Converter Charge | 2028-07-11 | 2028-07-11 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080171 | 11.07.2028 | 22000 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TCCPP | 7500 | 93142 | 7534 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Brake Control | 2028-07-11 | 2028-07-11 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034393 | 11.07.2028 | 11000 | CLB-MP-HAUL-DT168 -BRKSYS-HYFPP | 7500 | 93142 | 7536 | CLB-MP-HAUL-DT168 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Valve Steering & AHS EH | 2028-07-11 | 2028-07-11 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078443 | 11.07.2028 | 22000 | CLB-MP-HAUL-DT168 -STRSYS-STVLV | 7500 | 93142 | 7534 | CLB-MP-HAUL-DT168 -STRSYS-STVLV90009881
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Wheel Assembly LHF | 2028-07-11 | 2028-07-12 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000326589 | 11.07.2028 | 24000 | CLB-MP-HAUL-DT5418-STRUCT-AXLES-HUBLH | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Wheel Assembly RHF | 2028-07-11 | 2028-07-12 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000326590 | 11.07.2028 | 24000 | CLB-MP-HAUL-DT5418-STRUCT-AXLES-HUBRH | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Steering Link & Arm Rebush | 2028-07-12 | 2028-07-13 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385401 | 12.07.2028 | 30000 | CLB-MP-HAUL-DT164 -STRSYS-STLTR | 7500 | 81875 | 15434 | CLB-MP-HAUL-DT164 -STRSYS-STLTR90038355
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Adjust Engine Valve Set | 2028-07-12 | 2028-07-12 | 12 hrs | FY29 | 24 | 90015645 | A1 | 1000238537 | 12.07.2028 | 4500 | CLB-MP-SUPP-SV4105-ENGINE | 2500 | 8917 | 8917 | CLB-MP-SUPP-SV4105-ENGINE90015645
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Service Airconditioner | 2028-07-12 | 2028-07-13 | 24 hrs | FY29 | 24 | 90018538 | A1 | 1000239740 | 12.07.2028 | 4500 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-AIRCN | 2500 | 8917 | 5023 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-AIRCN90018538
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Water Cannon Inspect | 2028-07-12 | 2028-07-12 | 3 hrs | FY29 | 3 | 90033661 | A1 | 1000338794 | 12.07.2028 | 6 Monthly | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | 5000 | 65823 | 12836 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Final Drive LH | 2028-07-13 | 2028-07-14 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000036111 | 13.07.2028 | 22000 | CLB-MP-HAUL-DT199 -FDRSYS-FDRVE-FDRLH | 7500 | 85978 | 7443 | CLB-MP-HAUL-DT199 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Pump Hoist & Brake | 2028-07-13 | 2028-07-13 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035598 | 13.07.2028 | 22000 | CLB-MP-HAUL-DT190 -HYDSYS-HOPMP | 7500 | 90698 | 7441 | CLB-MP-HAUL-DT190 -HYDSYS-HOPMP90003113
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Service Air Conditioner 12M | 2028-07-14 | 2028-07-14 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000360961 | 14.07.2028 | 12 Monthly | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Service Air Conditioner 12M | 2028-07-14 | 2028-07-14 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000360811 | 14.07.2028 | 12 Monthly | CLB-MP-HAUL-DT5468-STRUCT-CABIN-AIRCN | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-AIRCN90029300
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 1Y Air Tank External Inspect | 2028-07-14 | 2028-07-14 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389218 | 14.07.2028 | 12 Monthly | CLB-MP-SUPP-WC014 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC014 -PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Cyl Steering LH | 2028-07-15 | 2028-07-15 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034620 | 15.07.2028 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STRCY-STCYL | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Cyl Steering RH | 2028-07-15 | 2028-07-15 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034621 | 15.07.2028 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STRCY-STCYR | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Hyd Motor Axle Lube Rear | 2028-07-15 | 2028-07-15 | 9 hrs | FY29 | 9 | 90003101 | 1 | 1000035160 | 15.07.2028 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-HYM01 | 7500 | 92002 | 29474 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-HYM0190003101
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Cylinder Steering RHS | 2028-07-15 | 2028-07-15 | 8 hrs | FY29 | 14 | 90029374 | A1 | 1000326396 | 15.07.2028 | 20000 | CLB-MP-HAUL-DT5417-STRSYS-STRCY-STCYR | 6500 | 10618 | 6256 | CLB-MP-HAUL-DT5417-STRSYS-STRCY-STCYR90029374
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Midlife Valve Set - Adjust | 2028-07-16 | 2028-07-16 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390949 | 16.07.2028 | 11000 | CLB-MP-HAUL-DT185 -ENGINE | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Engine Midlife complete | 2028-07-16 | 2028-07-20 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156827 | 16.07.2028 | 11000 | CLB-MP-HAUL-DT185 -ENGINE | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Service Suspension Cylinders | 2028-07-16 | 2028-07-16 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106894 | 16.07.2028 | 11000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN | 7500 | 92088 | 41661 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Ovhl Axle A Frame | 2028-07-16 | 2028-07-17 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130663 | 16.07.2028 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-AFRME | 7500 | 83140 | 29332 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-AFRME90015390
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Wheel Assembly LHF | 2028-07-16 | 2028-07-17 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000326276 | 16.07.2028 | 24000 | CLB-MP-HAUL-DT5416-STRUCT-AXLES-HUBLH | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Wheel Assembly RHF | 2028-07-16 | 2028-07-17 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000326277 | 16.07.2028 | 24000 | CLB-MP-HAUL-DT5416-STRUCT-AXLES-HUBRH | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Wheel Assembly LHF | 2028-07-18 | 2028-07-19 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000314356 | 18.07.2028 | 24000 | CLB-MP-HAUL-DT5410-STRUCT-AXLES-HUBLH | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Wheel Assembly RHF | 2028-07-18 | 2028-07-19 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000314357 | 18.07.2028 | 24000 | CLB-MP-HAUL-DT5410-STRUCT-AXLES-HUBRH | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Cyl Suspension RHR | 2028-07-18 | 2028-07-19 | 23 hrs | FY29 | 42 | 90003122 | 1 | 1000034910 | 18.07.2028 | 22000 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYRR | 7500 | 81791 | 7294 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Cyl Hoist LH | 2028-07-18 | 2028-07-19 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000035773 | 18.07.2028 | 28000 | CLB-MP-HAUL-DT193 -HYDSYS-HOCYL-HCYLL | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Cyl Hoist RH | 2028-07-18 | 2028-07-19 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000035774 | 18.07.2028 | 28000 | CLB-MP-HAUL-DT193 -HYDSYS-HOCYL-HCYLR | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Control Cabinet Coolant | 2028-07-18 | 2028-07-18 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000362720 | 18.07.2028 | 15000 | CLB-MP-HAUL-DT5472-ELCTHV-HVCAB-COOLR | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Midlife Valve Set - Adjust | 2028-07-19 | 2028-07-19 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390947 | 19.07.2028 | 11000 | CLB-MP-HAUL-DT183 -ENGINE | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Engine Midlife complete | 2028-07-19 | 2028-07-23 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156795 | 19.07.2028 | 11000 | CLB-MP-HAUL-DT183 -ENGINE | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Brake Wheel LH | 2028-07-19 | 2028-07-20 | 32 hrs | FY29 | 38 | 90003104 | 2 | 1000035404 | 19.07.2028 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-AXLES-HUBLH | 7500 | 93170 | 22807 | CLB-MP-HAUL-DT187 -STRUCT-AXLES-HUBLH90003104
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Seat Operator | 2028-07-20 | 2028-07-20 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000371810 | 20.07.2028 | 14000 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-SEATS | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-SEATS90029285
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Seat Operators | 2028-07-20 | 2028-07-20 | 4 hrs | FY29 | 4 | 90004012 | 1 | 1000161980 | 20.07.2028 | 10000 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-SEATS | 5000 | 63833 | 10370 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-SEATS90004012
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Steering Accumulator LH | 2028-07-21 | 2028-07-21 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044799 | 21.07.2028 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STACC-SACLH | 5000 | 67897 | 20934 | CLB-MP-SUPP-WC015 -STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Steering Accumulator RH | 2028-07-21 | 2028-07-21 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044800 | 21.07.2028 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STACC-SACRH | 5000 | 67897 | 20934 | CLB-MP-SUPP-WC015 -STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Steering Oil Cooler | 2028-07-21 | 2028-07-21 | 5 hrs | FY29 | 5 | 90004006 | 1 | 1000044798 | 21.07.2028 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STOLC | 5000 | 67897 | 20934 | CLB-MP-SUPP-WC015 -STRSYS-STOLC90004006
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Seat Operator | 2028-07-22 | 2028-07-22 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000357122 | 22.07.2028 | 14000 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-SEATS | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Service Air Conditioner | 2028-07-22 | 2028-07-22 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160405 | 22.07.2028 | 5500 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-AIRCN | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Seat Operator | 2028-07-24 | 2028-07-24 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000372479 | 24.07.2028 | 14000 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-SEATS | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-SEATS90029285
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 250Hr Initial Valve Set | 2028-07-25 | 2028-07-25 | 12 hrs | FY29 | 24 | 90028984 | A1 | 1000289409 | 25.07.2028 | 250 | CLB-MP-SUPP-PM0006-ENGINE | 4200 | 53807 | 15788 | CLB-MP-SUPP-PM0006-ENGINE90028984
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Service Air Conditioner | 2028-07-26 | 2028-07-26 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160379 | 26.07.2028 | 5500 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-AIRCN | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Steering Pump | 2028-07-26 | 2028-07-26 | 4 hrs | FY29 | 4 | 90004003 | 1 | 1000044793 | 26.07.2028 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STPMP | 5000 | 67897 | 5147 | CLB-MP-SUPP-WC015 -STRSYS-STPMP90004003
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Steering Cylinder RH | 2028-07-26 | 2028-07-26 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000044796 | 26.07.2028 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STRCY-STCYR | 5000 | 67897 | 5147 | CLB-MP-SUPP-WC015 -STRSYS-STRCY-STCYR90004005
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 1Y Air Tank LH External Inspect | 2028-07-29 | 2028-07-29 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389442 | 29.07.2028 | 12 Monthly | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH | 7500 | 85995 | 85995 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 1Y Air Tank RH External Inspect | 2028-07-29 | 2028-07-29 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389444 | 29.07.2028 | 12 Monthly | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH | 7500 | 85995 | 85995 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Transmission | 2028-07-29 | 2028-07-29 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035811 | 29.07.2028 | 11000 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TMCPP | 7500 | 86451 | 6933 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Pump Drive Driveshaft Unis | 2028-07-30 | 2028-07-30 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035209 | 30.07.2028 | 11000 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR-DRSHT | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl AOC Fan Motor | 2028-07-30 | 2028-07-30 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035216 | 30.07.2028 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-MTFAN | 7500 | 90364 | 7023 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Brake Relay Valve | 2028-07-30 | 2028-07-30 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000079661 | 30.07.2028 | 11000 | CLB-MP-HAUL-DT183 -BRKSYS-BRVRL | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-BRVRL90009877
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Service Air Conditioner 12M | 2028-07-30 | 2028-07-30 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000361765 | 30.07.2028 | 12 Monthly | CLB-MP-HAUL-DT5473-STRUCT-CABIN-AIRCN | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Pump Transmission | 2028-07-31 | 2028-07-31 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035210 | 31.07.2028 | 11000 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TMCPP | 7500 | 90364 | 7008 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Pump Brake Control | 2028-07-31 | 2028-07-31 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035221 | 31.07.2028 | 11000 | CLB-MP-HAUL-DT183 -BRKSYS-HYFPP | 7500 | 90364 | 7008 | CLB-MP-HAUL-DT183 -BRKSYS-HYFPP90003106
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Replace Operator Seat | 2028-07-31 | 2028-07-31 | 4 hrs | FY29 | 4 | 90011567 | A1 | 1000214401 | 31.07.2028 | 6000 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-SEATS | 2500 | 8917 | 775 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-SEATS90011567
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Service Air Conditioner | 2028-08-02 | 2028-08-02 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160386 | 02.08.2028 | 5500 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-AIRCN | 7500 | 89560 | 17107 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 1Y Air Tank LH External Inspect | 2028-08-02 | 2028-08-02 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389446 | 02.08.2028 | 12 Monthly | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH | 7500 | 88415 | 16378 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 1Y Air Tank RH External Inspect | 2028-08-02 | 2028-08-02 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389448 | 02.08.2028 | 12 Monthly | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH | 7500 | 88415 | 16378 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Service Air Conditioner 12M | 2028-08-02 | 2028-08-02 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000361812 | 02.08.2028 | 12 Monthly | CLB-MP-HAUL-DT5474-STRUCT-CABIN-AIRCN | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Pump Transmission | 2028-08-03 | 2028-08-03 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000116266 | 03.08.2028 | 11000 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TMCPP | 7500 | 81875 | 6988 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Service Air Conditioner | 2028-08-03 | 2028-08-03 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160406 | 03.08.2028 | 5500 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-AIRCN | 7500 | 92548 | 12117 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5476 | DT5476 Repl Seat Operator | 2028-08-05 | 2028-08-05 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000365042 | 05.08.2028 | 14000 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-SEATS | 6500 | 920 | 920 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-SEATS90029285
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 1Y Air Tank External Inspect | 2028-08-05 | 2028-08-05 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389214 | 05.08.2028 | 12 Monthly | CLB-MP-SUPP-WC012 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC012 -PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Steering Ball Studs | 2028-08-06 | 2028-08-07 | 19 hrs | FY29 | 35 | 90038356 | A1 | 1000385412 | 06.08.2028 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STLTR | 7500 | 91119 | 29788 | CLB-MP-HAUL-DT170 -STRSYS-STLTR90038356
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl PTO Uni's & Driveshaft | 2028-08-07 | 2028-08-07 | 2 hrs | FY29 | 2 | 90031094 | A1 | 1000307808 | 07.08.2028 | 10000 | CLB-MP-SUPP-WC014 -ENGINE-PMPDR-DRSHT | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -ENGINE-PMPDR-DRSHT90031094
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Pump Transmission | 2028-08-08 | 2028-08-08 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000034659 | 08.08.2028 | 11000 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TMCPP | 7500 | 82651 | 6802 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TMCPP90003096
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Steering Pump | 2028-08-08 | 2028-08-08 | 4 hrs | FY29 | 4 | 90004003 | 1 | 1000044537 | 08.08.2028 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STPMP | 5000 | 64118 | 4490 | CLB-MP-SUPP-WC011 -STRSYS-STPMP90004003
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Steering HMU | 2028-08-08 | 2028-08-08 | 8 hrs | FY29 | 8 | 90004004 | 1 | 1000044538 | 08.08.2028 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STHMU | 5000 | 64118 | 4490 | CLB-MP-SUPP-WC011 -STRSYS-STHMU90004004
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Steering Accumulator LH | 2028-08-08 | 2028-08-08 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044543 | 08.08.2028 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STACC-SACLH | 5000 | 64118 | 4489 | CLB-MP-SUPP-WC011 -STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Replace Steering Oil Cooler | 2028-08-08 | 2028-08-08 | 5 hrs | FY29 | 5 | 90004006 | 1 | 1000044542 | 08.08.2028 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STOLC | 5000 | 64118 | 4490 | CLB-MP-SUPP-WC011 -STRSYS-STOLC90004006
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Torque Converter Charge | 2028-08-09 | 2028-08-09 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080178 | 09.08.2028 | 22000 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TCCPP | 7500 | 85284 | 6904 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TCCPP90003095
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Service Air Conditioner 12M | 2028-08-09 | 2028-08-09 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000362640 | 09.08.2028 | 12 Monthly | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Service Air Conditioner 12M | 2028-08-11 | 2028-08-11 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000362685 | 11.08.2028 | 12 Monthly | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN90029300
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Operators Seat | 2028-08-13 | 2028-08-13 | 4 hrs | FY29 | 8 | 90003066 | A1 | 1000034008 | 13.08.2028 | 6000 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-SEATS | 3300 | 54098 | 5038 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-SEATS90003066
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Pump Transmission | 2028-08-14 | 2028-08-14 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035579 | 14.08.2028 | 11000 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TMCPP | 7500 | 90698 | 6776 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Pump Brake Control | 2028-08-14 | 2028-08-14 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035590 | 14.08.2028 | 11000 | CLB-MP-HAUL-DT190 -BRKSYS-HYFPP | 7500 | 90698 | 6776 | CLB-MP-HAUL-DT190 -BRKSYS-HYFPP90003106
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Brake Relay Valve - Replace | 2028-08-14 | 2028-08-14 | 3 hrs | FY29 | 3 | 90018291 | 1 | 1000174674 | 14.08.2028 | 10000 | CLB-MP-SUPP-LL0003-BRKSYS-BRVLV-FTBRV | 4200 | 71996 | 11102 | CLB-MP-SUPP-LL0003-BRKSYS-BRVLV-FTBRV90018291
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Slack Adjuster - Replace | 2028-08-14 | 2028-08-14 | 3 hrs | FY29 | 3 | 90018295 | 1 | 1000174679 | 14.08.2028 | 10000 | CLB-MP-SUPP-LL0003-BRKSYS-SLACK | 4200 | 71996 | 11102 | CLB-MP-SUPP-LL0003-BRKSYS-SLACK90018295
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 1Y Air Tank External Inspect | 2028-08-14 | 2028-08-14 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389216 | 14.08.2028 | 12 Monthly | CLB-MP-SUPP-WC013 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC013 -PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Cyl Hoist LH | 2028-08-15 | 2028-08-16 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000036128 | 15.08.2028 | 28000 | CLB-MP-HAUL-DT199 -HYDSYS-HOCYL-HCYLL | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Cyl Hoist RH | 2028-08-15 | 2028-08-16 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000036129 | 15.08.2028 | 28000 | CLB-MP-HAUL-DT199 -HYDSYS-HOCYL-HCYLR | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Hoist & Rear Brake Pump | 2028-08-16 | 2028-08-16 | 5 hrs | FY29 | 5 | 90004008 | 1 | 1000044673 | 16.08.2028 | 20000 | CLB-MP-SUPP-WC013 -HYDSYS-HOPMP | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -HYDSYS-HOPMP90004008
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl Steering Link & Arm Rebush | 2028-08-17 | 2028-08-17 | 14 hrs | FY29 | 22 | 90004007 | 1 | 1000044605 | 17.08.2028 | 15000 | CLB-MP-SUPP-WC012 -STRSYS-STLTR | 5000 | 67273 | 22004 | CLB-MP-SUPP-WC012 -STRSYS-STLTR90004007
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 1Y Air Tank LH External Inspect | 2028-08-18 | 2028-08-18 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389430 | 18.08.2028 | 12 Monthly | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH | 7500 | 86244 | 37431 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 1Y Air Tank RH External Inspect | 2028-08-18 | 2028-08-18 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389432 | 18.08.2028 | 12 Monthly | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH | 7500 | 86244 | 37431 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Brake Control | 2028-08-19 | 2028-08-19 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035166 | 19.08.2028 | 11000 | CLB-MP-HAUL-DT182 -BRKSYS-HYFPP | 7500 | 92002 | 6691 | CLB-MP-HAUL-DT182 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Cyl Hoist LH | 2028-08-19 | 2028-08-20 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034679 | 19.08.2028 | 28000 | CLB-MP-HAUL-DT173 -HYDSYS-HOCYL-HCYLL | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Pump Transmission | 2028-08-20 | 2028-08-20 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035451 | 20.08.2028 | 11000 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TMCPP | 7500 | 83931 | 6681 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TMCPP90003096
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Brake & Steering Manifold | 2028-08-20 | 2028-08-20 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000346234 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-BRKSYS-BRVLV | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Gear Cooler Motor & Pump | 2028-08-20 | 2028-08-20 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000346273 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-FDRSYS-GRSOC-OCPPM | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Pump Airconditioner Drive | 2028-08-20 | 2028-08-20 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000346233 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-ACPMP | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Coupling Drive Pump | 2028-08-20 | 2028-08-20 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000346238 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-HYDPC | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Cylinder Steering LHS | 2028-08-20 | 2028-08-20 | 8 hrs | FY29 | 14 | 90029373 | A1 | 1000346261 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-STRSYS-STRCY-STCYL | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Cylinder Steering RHS | 2028-08-20 | 2028-08-20 | 8 hrs | FY29 | 14 | 90029374 | A1 | 1000346262 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-STRSYS-STRCY-STCYR | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Valve Flow Amplifier | 2028-08-20 | 2028-08-20 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000346272 | 20.08.2028 | 20000 | CLB-MP-HAUL-DT5441-STRSYS-STVLV | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Suspension LHR | 2028-08-22 | 2028-08-23 | 23 hrs | FY29 | 42 | 90003122 | 1 | 1000036197 | 22.08.2028 | 22000 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYLR | 7500 | 92548 | 6572 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYLR90003122
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Control Cabinet Coolant | 2028-08-22 | 2028-08-22 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000371457 | 22.08.2028 | 15000 | CLB-MP-HAUL-DT5485-ELCTHV-HVCAB-COOLR | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-ELCTHV-HVCAB-COOLR90033128
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Repl Water Cannon & Valves | 2028-08-23 | 2028-08-24 | 24 hrs | FY29 | 48 | 90033662 | A1 | 1000339269 | 23.08.2028 | 24 Monthly | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | 5000 | 17738 | 8813 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON90033662
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Radiator Assembly | 2028-08-23 | 2028-08-24 | 20 hrs | FY29 | 38 | 90003977 | 1 | 1000044705 | 23.08.2028 | 20000 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-RADTR | 5000 | 65823 | 9247 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-RADTR90003977
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Rear Axle Cooling Fan Motor | 2028-08-23 | 2028-08-23 | 2 hrs | FY29 | 2 | 90003997 | 1 | 1000044720 | 23.08.2028 | 10000 | CLB-MP-SUPP-WC014 -FDRSYS-AXLEC-MTFAN | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Rear Axle Oil Pump | 2028-08-23 | 2028-08-23 | 2 hrs | FY29 | 2 | 90003996 | 1 | 1000044719 | 23.08.2028 | 10000 | CLB-MP-SUPP-WC014 -FDRSYS-AXLEC-HYPUM | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -FDRSYS-AXLEC-HYPUM90003996
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Control Cabinet Coolant | 2028-08-23 | 2028-08-23 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000371386 | 23.08.2028 | 15000 | CLB-MP-HAUL-DT5484-ELCTHV-HVCAB-COOLR | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Control Cabinet Coolant | 2028-08-23 | 2028-08-23 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000369121 | 23.08.2028 | 15000 | CLB-MP-HAUL-DT5483-ELCTHV-HVCAB-COOLR | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Control Cabinet Coolant | 2028-08-23 | 2028-08-23 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000366507 | 23.08.2028 | 15000 | CLB-MP-HAUL-DT5481-ELCTHV-HVCAB-COOLR | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Control Cabinet Coolant | 2028-08-23 | 2028-08-23 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000365712 | 23.08.2028 | 15000 | CLB-MP-HAUL-DT5479-ELCTHV-HVCAB-COOLR | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Engine Midlife complete | 2028-08-24 | 2028-08-28 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156907 | 24.08.2028 | 11000 | CLB-MP-HAUL-DT190 -ENGINE | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Midlife Valve Set - Adjust | 2028-08-24 | 2028-08-24 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390954 | 24.08.2028 | 11000 | CLB-MP-HAUL-DT190 -ENGINE | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -ENGINE90017314
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Brake Accumulator | 2028-08-24 | 2028-08-24 | 4 hrs | FY29 | 4 | 90004001 | 1 | 1000044661 | 24.08.2028 | 15000 | CLB-MP-SUPP-WC013 -BRKSYS-BACCM | 5000 | 20952 | 20952 | CLB-MP-SUPP-WC013 -BRKSYS-BACCM90004001
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Steering Pump | 2028-08-24 | 2028-08-24 | 4 hrs | FY29 | 4 | 90004003 | 1 | 1000044665 | 24.08.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STPMP | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRSYS-STPMP90004003
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Steering Accumulator LH | 2028-08-24 | 2028-08-24 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044671 | 24.08.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STACC-SACLH | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Steering Accumulator RH | 2028-08-24 | 2028-08-24 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044672 | 24.08.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STACC-SACRH | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Steering Oil Cooler | 2028-08-24 | 2028-08-24 | 5 hrs | FY29 | 5 | 90004006 | 1 | 1000044670 | 24.08.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STOLC | 5000 | 63833 | 20952 | CLB-MP-SUPP-WC013 -STRSYS-STOLC90004006
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000377284 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5500-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000376497 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5499-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000375572 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5498-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000375439 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5497-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000374062 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5496-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000374011 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5495-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000373623 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5494-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000373365 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5493-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000373111 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5492-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000372742 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5491-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000367604 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5482-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000366372 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5480-ELCTHV-HVCAB-COOLR | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Control Cabinet Coolant | 2028-08-25 | 2028-08-25 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000365662 | 25.08.2028 | 15000 | CLB-MP-HAUL-DT5478-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-ELCTHV-HVCAB-COOLR90033128
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Steering Cylinder LH | 2028-08-26 | 2028-08-26 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000044667 | 26.08.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STRCY-STCYL | 5000 | 63833 | 4893 | CLB-MP-SUPP-WC013 -STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl Steering Link & Arm Rebush | 2028-08-26 | 2028-08-26 | 14 hrs | FY29 | 22 | 90004007 | 1 | 1000044669 | 26.08.2028 | 15000 | CLB-MP-SUPP-WC013 -STRSYS-STLTR | 5000 | 63833 | 4893 | CLB-MP-SUPP-WC013 -STRSYS-STLTR90004007
T264 | Onsite PM | Haul | Fortescue | DT5477 | DT5477 Repl Seat Operator | 2028-08-27 | 2028-08-27 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000365213 | 27.08.2028 | 14000 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-SEATS | 6500 | 630 | 630 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Repl Valve Steering & AHS EH | 2028-08-29 | 2028-08-29 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078462 | 29.08.2028 | 22000 | CLB-MP-HAUL-DT169 -STRSYS-STVLV | 7500 | 93410 | 6480 | CLB-MP-HAUL-DT169 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Ovhl Axle A Frame | 2028-08-30 | 2028-08-31 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130657 | 30.08.2028 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-AFRME | 7500 | 89749 | 28445 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-AFRME90015390
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Control Cabinet Coolant | 2028-08-30 | 2028-08-30 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000371576 | 30.08.2028 | 15000 | CLB-MP-HAUL-DT5486-ELCTHV-HVCAB-COOLR | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Drive Shaft Transmission | 2028-08-31 | 2028-08-31 | 8 hrs | FY29 | 16 | 90017134 | 1 | 1000154437 | 31.08.2028 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-DRSHT | 7500 | 88680 | 27582 | CLB-MP-HAUL-DT198 -FDRSYS-DRSHT90017134
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Control Cabinet Coolant | 2028-08-31 | 2028-08-31 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000361847 | 31.08.2028 | 15000 | CLB-MP-HAUL-DT5474-ELCTHV-HVCAB-COOLR | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Control Cabinet Coolant | 2028-08-31 | 2028-08-31 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000361800 | 31.08.2028 | 15000 | CLB-MP-HAUL-DT5473-ELCTHV-HVCAB-COOLR | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-ELCTHV-HVCAB-COOLR90033128
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Drive Shaft Pump Drive | 2028-09-01 | 2028-09-01 | 6 hrs | FY29 | 6 | 90013160 | A1 | 1000110232 | 01.09.2028 | 11000 | CLB-MP-SUPP-PM0004-ENGINE-PMPDR-DRSHT | 3500 | 91736 | 15427 | CLB-MP-SUPP-PM0004-ENGINE-PMPDR-DRSHT90013160
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Control Cabinet Coolant | 2028-09-02 | 2028-09-02 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000381345 | 02.09.2028 | 15000 | CLB-MP-HAUL-DT5504-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Control Cabinet Coolant | 2028-09-02 | 2028-09-02 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000381277 | 02.09.2028 | 15000 | CLB-MP-HAUL-DT5503-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Pump Torque Converter Charge | 2028-09-03 | 2028-09-03 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080214 | 03.09.2028 | 22000 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TCCPP | 7500 | 91174 | 6298 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Pump Hoist & Brake | 2028-09-03 | 2028-09-03 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035714 | 03.09.2028 | 22000 | CLB-MP-HAUL-DT192 -HYDSYS-HOPMP | 7500 | 91174 | 6298 | CLB-MP-HAUL-DT192 -HYDSYS-HOPMP90003113
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Brake Accumulator | 2028-09-03 | 2028-09-03 | 4 hrs | FY29 | 4 | 90004001 | 1 | 1000044725 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -BRKSYS-BACCM | 5000 | 65823 | 4096 | CLB-MP-SUPP-WC014 -BRKSYS-BACCM90004001
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Steering Pump | 2028-09-03 | 2028-09-03 | 4 hrs | FY29 | 4 | 90004003 | 1 | 1000044729 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STPMP | 5000 | 65823 | 4096 | CLB-MP-SUPP-WC014 -STRSYS-STPMP90004003
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Steering HMU | 2028-09-03 | 2028-09-03 | 8 hrs | FY29 | 8 | 90004004 | 1 | 1000044730 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STHMU | 5000 | 65823 | 4096 | CLB-MP-SUPP-WC014 -STRSYS-STHMU90004004
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Steering Cylinder LH | 2028-09-03 | 2028-09-03 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000044731 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STRCY-STCYL | 5000 | 65823 | 4096 | CLB-MP-SUPP-WC014 -STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Steering Accumulator LH | 2028-09-03 | 2028-09-03 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044735 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STACC-SACLH | 5000 | 65823 | 19464 | CLB-MP-SUPP-WC014 -STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Repl Steering Accumulator RH | 2028-09-03 | 2028-09-03 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044736 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STACC-SACRH | 5000 | 65823 | 19464 | CLB-MP-SUPP-WC014 -STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Steering Oil Cooler | 2028-09-03 | 2028-09-03 | 5 hrs | FY29 | 5 | 90004006 | 1 | 1000044734 | 03.09.2028 | 15000 | CLB-MP-SUPP-WC014 -STRSYS-STOLC | 5000 | 65823 | 19464 | CLB-MP-SUPP-WC014 -STRSYS-STOLC90004006
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Torque Converter | 2028-09-04 | 2028-09-05 | 32 hrs | FY29 | 62 | 90003092 | 1 | 1000035692 | 04.09.2028 | 22000 | CLB-MP-HAUL-DT192 -TRNSYS-TRQUE | 7500 | 91174 | 6298 | CLB-MP-HAUL-DT192 -TRNSYS-TRQUE90003092
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 1Y Air Tank External Inspect | 2028-09-05 | 2028-09-05 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389220 | 05.09.2028 | 12 Monthly | CLB-MP-SUPP-WC015 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC015 -PNEUMC-PNTNK90038749
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 1Y Air Tank External Inspect | 2028-09-06 | 2028-09-06 | 1.5 hrs | FY29 | 1.5 | 90038749 | A1 | 1000389222 | 06.09.2028 | 12 Monthly | CLB-MP-SUPP-WC3108-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC3108-PNEUMC-PNTNK90038749
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Valve Steering & AHS EH | 2028-09-06 | 2028-09-06 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078728 | 06.09.2028 | 22000 | CLB-MP-HAUL-DT187 -STRSYS-STVLV | 7500 | 93170 | 28555 | CLB-MP-HAUL-DT187 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT187 | DT187 Repl Cyl Suspension RHF | 2028-09-06 | 2028-09-07 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067856 | 06.09.2028 | 22000 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYRF | 7500 | 93170 | 6296 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYRF90003121
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Service Air Conditioner 12M | 2028-09-06 | 2028-09-06 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000365677 | 06.09.2028 | 12 Monthly | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Service Air Conditioner 12M | 2028-09-06 | 2028-09-06 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000365627 | 06.09.2028 | 12 Monthly | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Transmission | 2028-09-09 | 2028-09-10 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000034987 | 09.09.2028 | 22000 | CLB-MP-HAUL-DT179 -TRNSYS-TRANS | 7500 | 84079 | 6265 | CLB-MP-HAUL-DT179 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Transmission | 2028-09-09 | 2028-09-09 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000034989 | 09.09.2028 | 11000 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TMCPP | 7500 | 84079 | 6265 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Transmission Oil Cooler | 2028-09-09 | 2028-09-09 | 13 hrs | FY29 | 13 | 90003532 | 1 | 1000040988 | 09.09.2028 | 22000 | CLB-MP-HAUL-DT179 -TRNSYS-TROLC | 7500 | 84079 | 6265 | CLB-MP-HAUL-DT179 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Pump Drive Driveshaft Unis | 2028-09-09 | 2028-09-09 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035578 | 09.09.2028 | 11000 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR-DRSHT | 7500 | 90698 | 6249 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Transmission | 2028-09-09 | 2028-09-10 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000035577 | 09.09.2028 | 22000 | CLB-MP-HAUL-DT190 -TRNSYS-TRANS | 7500 | 90698 | 6250 | CLB-MP-HAUL-DT190 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Pump Torque Converter Charge | 2028-09-09 | 2028-09-09 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080212 | 09.09.2028 | 22000 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TCCPP | 7500 | 90698 | 6249 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Final Drive LH | 2028-09-09 | 2028-09-10 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000034717 | 09.09.2028 | 22000 | CLB-MP-HAUL-DT174 -FDRSYS-FDRVE-FDRLH | 7500 | 83749 | 6217 | CLB-MP-HAUL-DT174 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Pump Transmission | 2028-09-10 | 2028-09-10 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035753 | 10.09.2028 | 11000 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TMCPP | 7500 | 83140 | 6169 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Pump Hoist & Brake | 2028-09-10 | 2028-09-10 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035772 | 10.09.2028 | 22000 | CLB-MP-HAUL-DT193 -HYDSYS-HOPMP | 7500 | 83140 | 6169 | CLB-MP-HAUL-DT193 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Drive Line Axle LH | 2028-09-11 | 2028-09-11 | 4 hrs | FY29 | 8 | 90014551 | 1 | 1000123519 | 11.09.2028 | 30000 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX-AXLLH | 7500 | 83749 | 14201 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX-AXLLH90014551
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Drive Line Axle RH | 2028-09-11 | 2028-09-11 | 4 hrs | FY29 | 8 | 90014552 | 1 | 1000123580 | 11.09.2028 | 30000 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX-AXLRH | 7500 | 83749 | 14201 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Ovhl Axle A Frame | 2028-09-11 | 2028-09-12 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130639 | 11.09.2028 | 22000 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-AFRME | 7500 | 83302 | 83302 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-AFRME90015390
T264 | Onsite PM | Haul | Fortescue | DT5475 | DT5475 Repl Seat Operator | 2028-09-12 | 2028-09-12 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000363992 | 12.09.2028 | 14000 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-SEATS | 6500 | 211 | 211 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-SEATS90029285
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Service Air Conditioner | 2028-09-13 | 2028-09-13 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160372 | 13.09.2028 | 5500 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-AIRCN | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Steering Link & Arm Rebush | 2028-09-13 | 2028-09-14 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385419 | 13.09.2028 | 30000 | CLB-MP-HAUL-DT173 -STRSYS-STLTR | 7500 | 82651 | 14071 | CLB-MP-HAUL-DT173 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Hyd Pump Steering Main | 2028-09-13 | 2028-09-13 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034673 | 13.09.2028 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STPMP | 7500 | 82651 | 14071 | CLB-MP-HAUL-DT173 -STRSYS-STPMP90003109
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Control Cabinet Coolant | 2028-09-14 | 2028-09-14 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000371815 | 14.09.2028 | 15000 | CLB-MP-HAUL-DT5487-ELCTHV-HVCAB-COOLR | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Radiator Engine Cooling | 2028-09-15 | 2028-09-17 | 55 hrs | FY29 | 85 | 90003081 | 1 | 1000035314 | 15.09.2028 | 22000 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-RADTR | 7400 | 89749 | 28445 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-RADTR90003081
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Final Drive LH | 2028-09-15 | 2028-09-16 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000035323 | 15.09.2028 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-FDRVE-FDRLH | 7500 | 89749 | 6115 | CLB-MP-HAUL-DT186 -FDRSYS-FDRVE-FDRLH90003099
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 1Y Air Tank External Inspect | 2028-09-15 | 2028-09-15 | 1.5 hrs | FY29 | 1.5 | 90038755 | A1 | 1000389470 | 15.09.2028 | 12 Monthly | CLB-MP-SUPP-PM0004-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-PM0004-PNEUMC-PNTNK90038755
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Final Drive LH | 2028-09-15 | 2028-09-16 | 24 hrs | FY29 | 48 | 90003043 | A1 | 1000033920 | 15.09.2028 | 18000 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE-FDRLH | 3300 | 44025 | 10957 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE-FDRLH90003043
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Final Drive RH | 2028-09-15 | 2028-09-15 | 15 hrs | FY29 | 30 | 90007347 | 1 | 1000033921 | 15.09.2028 | 18000 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE-FDRRH | 3300 | 44025 | 10957 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE-FDRRH90007347
T264 | Onsite PM | Haul | Fortescue | DT5501 | DT5501 Repl Seat Operator | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000383532 | 16.09.2028 | 14000 | CLB-MP-HAUL-DT5501-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5501-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5502 | DT5502 Repl Seat Operator | 2028-09-16 | 2028-09-16 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000383623 | 16.09.2028 | 14000 | CLB-MP-HAUL-DT5502-STRUCT-CABIN-SEATS | 6500 | 1 | 1 | CLB-MP-HAUL-DT5502-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Control Cabinet Coolant | 2028-09-16 | 2028-09-16 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000357129 | 16.09.2028 | 15000 | CLB-MP-HAUL-DT5466-ELCTHV-HVCAB-COOLR | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Engine Midlife complete | 2028-09-17 | 2028-09-19 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000360977 | 17.09.2028 | 17500 | CLB-MP-HAUL-DT5469-ENGINE | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 1Y Air Tank LH External Inspect | 2028-09-17 | 2028-09-17 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389458 | 17.09.2028 | 12 Monthly | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH | 7500 | 49299 | 49299 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 1Y Air Tank RH External Inspect | 2028-09-17 | 2028-09-17 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389460 | 17.09.2028 | 12 Monthly | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH | 7500 | 49299 | 49299 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Service Suspension Cylinders | 2028-09-17 | 2028-09-17 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106877 | 17.09.2028 | 11000 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN | 7500 | 93142 | 26399 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN90012840
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Replace Water Cannon | 2028-09-17 | 2028-09-17 | 12 hrs | FY29 | 24 | 90015535 | 1 | 1000133453 | 17.09.2028 | 12 Monthly | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON90015535
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Control Cabinet Coolant | 2028-09-18 | 2028-09-18 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000372484 | 18.09.2028 | 15000 | CLB-MP-HAUL-DT5488-ELCTHV-HVCAB-COOLR | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Engine Midlife complete | 2028-09-18 | 2028-09-20 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000361170 | 18.09.2028 | 17500 | CLB-MP-HAUL-DT5470-ENGINE | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Pump Main Hydraulic | 2028-09-18 | 2028-09-18 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000314354 | 18.09.2028 | 20000 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-HYPMP | 6500 | 10949 | 5822 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-HYPMP90029366
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Service Air Conditioner | 2028-09-18 | 2028-09-18 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160378 | 18.09.2028 | 5500 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-AIRCN | 7500 | 92351 | 22401 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Air Dryer | 2028-09-20 | 2028-09-20 | 7 hrs | FY29 | 14 | 90003115 | 1 | 1000035775 | 20.09.2028 | 22000 | CLB-MP-HAUL-DT193 -PNEUMC-AIRDR | 7500 | 83140 | 27958 | CLB-MP-HAUL-DT193 -PNEUMC-AIRDR90003115
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Engine Midlife complete | 2028-09-23 | 2028-09-25 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000357154 | 23.09.2028 | 17500 | CLB-MP-HAUL-DT5467-ENGINE | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Repl Hyd Pump Steering Main | 2028-09-23 | 2028-09-23 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034286 | 23.09.2028 | 15000 | CLB-MP-HAUL-DT166 -STRSYS-STPMP | 7500 | 95491 | 13970 | CLB-MP-HAUL-DT166 -STRSYS-STPMP90003109
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Seat Operators | 2028-09-23 | 2028-09-23 | 4 hrs | FY29 | 4 | 90004012 | 1 | 1000161981 | 23.09.2028 | 10000 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-SEATS | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-SEATS90004012
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Engine Midlife complete | 2028-09-24 | 2028-09-26 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000360827 | 24.09.2028 | 17500 | CLB-MP-HAUL-DT5468-ENGINE | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Pump Transmission | 2028-09-24 | 2028-09-24 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035507 | 24.09.2028 | 11000 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TMCPP | 7500 | 84546 | 5964 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Service Air Conditioner | 2028-09-25 | 2028-09-25 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160371 | 25.09.2028 | 5500 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-AIRCN | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Service Air Conditioner | 2028-09-27 | 2028-09-27 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160385 | 27.09.2028 | 5500 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-AIRCN | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5476 | DT5476 Repl Control Cabinet Coolant | 2028-09-30 | 2028-09-30 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000365049 | 30.09.2028 | 15000 | CLB-MP-HAUL-DT5476-ELCTHV-HVCAB-COOLR | 6500 | 920 | 920 | CLB-MP-HAUL-DT5476-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Final Drive RH | 2028-10-01 | 2028-10-02 | 30 hrs | FY29 | 56 | 90003100 | 1 | 1000035104 | 01.10.2028 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-FDRVE-FDRRH | 7500 | 83441 | 5808 | CLB-MP-HAUL-DT181 -FDRSYS-FDRVE-FDRRH90003100
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Brake & Steering Manifold | 2028-10-02 | 2028-10-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000349689 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-BRKSYS-BRVLV | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Gear Cooler Motor & Pump | 2028-10-02 | 2028-10-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000349708 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-FDRSYS-GRSOC-OCPPM | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Pump Airconditioner Drive | 2028-10-02 | 2028-10-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000349688 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-ACPMP | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Coupling Drive Pump | 2028-10-02 | 2028-10-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000349693 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-HYDPC | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Pump Main Hydraulic | 2028-10-02 | 2028-10-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000349716 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-HYPMP | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Cylinder Steering LHS | 2028-10-02 | 2028-10-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000349696 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-STRSYS-STRCY-STCYL | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Cylinder Steering RHS | 2028-10-02 | 2028-10-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000349697 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-STRSYS-STRCY-STCYR | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Valve Flow Amplifier | 2028-10-02 | 2028-10-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000349707 | 02.10.2028 | 20000 | CLB-MP-HAUL-DT5452-STRSYS-STVLV | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Pump Brake Control | 2028-10-03 | 2028-10-03 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034615 | 03.10.2028 | 11000 | CLB-MP-HAUL-DT172 -BRKSYS-HYFPP | 7500 | 92350 | 5598 | CLB-MP-HAUL-DT172 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Pump Transmission | 2028-10-04 | 2028-10-04 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035265 | 04.10.2028 | 11000 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TMCPP | 7500 | 92088 | 5719 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl AOC Fan Motor | 2028-10-04 | 2028-10-04 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035271 | 04.10.2028 | 22000 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-MTFAN | 7500 | 92088 | 5725 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Pump Brake Control | 2028-10-04 | 2028-10-04 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035276 | 04.10.2028 | 11000 | CLB-MP-HAUL-DT185 -BRKSYS-HYFPP | 7500 | 92088 | 5719 | CLB-MP-HAUL-DT185 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Brake Relay Valve | 2028-10-04 | 2028-10-04 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078686 | 04.10.2028 | 11000 | CLB-MP-HAUL-DT185 -BRKSYS-BRVRL | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl AOC Fan Motor | 2028-10-07 | 2028-10-07 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000034665 | 07.10.2028 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-MTFAN | 7500 | 82651 | 5573 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Brake Wheel RH | 2028-10-09 | 2028-10-10 | 33 hrs | FY29 | 61 | 90003105 | 2 | 1000035704 | 09.10.2028 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-AXLES-HUBRH | 7500 | 91174 | 5567 | CLB-MP-HAUL-DT192 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Suspension RHF | 2028-10-09 | 2028-10-10 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067876 | 09.10.2028 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYRF | 7500 | 91174 | 5567 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Suspension LHR | 2028-10-09 | 2028-10-10 | 23 hrs | FY29 | 42 | 90003122 | 1 | 1000035725 | 09.10.2028 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYLR | 7500 | 91174 | 5567 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Midlife Valve Set - Adjust | 2028-10-09 | 2028-10-09 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390981 | 09.10.2028 | 11000 | CLB-MP-HAUL-DT197 -ENGINE | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Engine Midlife complete | 2028-10-09 | 2028-10-13 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000157019 | 09.10.2028 | 11000 | CLB-MP-HAUL-DT197 -ENGINE | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Engine Midlife complete | 2028-10-09 | 2028-10-13 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000157035 | 09.10.2028 | 11000 | CLB-MP-HAUL-DT198 -ENGINE | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Midlife Valve Set - Adjust | 2028-10-09 | 2028-10-09 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390982 | 09.10.2028 | 11000 | CLB-MP-HAUL-DT198 -ENGINE | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Service Suspension Cylinders | 2028-10-09 | 2028-10-09 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106947 | 09.10.2028 | 11000 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN90012840
777F | Onsite PM | Haul | Fortescue | SV020 | SV020 Replace Auto Lube Pump | 2028-10-09 | 2028-10-09 | 4 hrs | FY29 | 4 | 90003064 | A1 | 1000033945 | 09.10.2028 | 6000 | CLB-MP-SUPP-SV020 -GRSYST-ALBPP | 3300 | 44025 | 4749 | CLB-MP-SUPP-SV020 -GRSYST-ALBPP90003064
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Cyl Suspension LHF | 2028-10-10 | 2028-10-11 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067890 | 10.10.2028 | 22000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYLF | 7500 | 85161 | 5613 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYLF90003121
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Service Air Conditioner 12M | 2028-10-11 | 2028-10-11 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000326641 | 11.10.2028 | 12 Monthly | CLB-MP-HAUL-DT5419-STRUCT-CABIN-AIRCN | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Cyl Steering LH | 2028-10-12 | 2028-10-12 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034233 | 12.10.2028 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYL | 7500 | 78966 | 13578 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Cyl Steering RH | 2028-10-12 | 2028-10-12 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034234 | 12.10.2028 | 15000 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYR | 7500 | 78966 | 13578 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Pump Drive Driveshaft Unis | 2028-10-12 | 2028-10-12 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000036042 | 12.10.2028 | 11000 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR-DRSHT | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Pump Transmission | 2028-10-12 | 2028-10-12 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000036043 | 12.10.2028 | 11000 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TMCPP | 7500 | 88680 | 7548 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl AOC Fan Motor | 2028-10-12 | 2028-10-12 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000036049 | 12.10.2028 | 22000 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-MTFAN | 7500 | 88680 | 5577 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Pump Brake Control | 2028-10-12 | 2028-10-12 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000036054 | 12.10.2028 | 11000 | CLB-MP-HAUL-DT198 -BRKSYS-HYFPP | 7500 | 88680 | 5576 | CLB-MP-HAUL-DT198 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Relay Valve | 2028-10-12 | 2028-10-12 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078857 | 12.10.2028 | 11000 | CLB-MP-HAUL-DT198 -BRKSYS-BRVRL | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Cyl Steering LH | 2028-10-13 | 2028-10-13 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034510 | 13.10.2028 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYL | 7500 | 91119 | 13406 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Cyl Steering RH | 2028-10-13 | 2028-10-13 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034511 | 13.10.2028 | 15000 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYR | 7500 | 91119 | 13406 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYR90003111
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Cylinder Steering RHS | 2028-10-14 | 2028-10-14 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000347373 | 14.10.2028 | 20000 | CLB-MP-HAUL-DT5447-STRSYS-STRCY-STCYR | 6500 | 8949 | 5706 | CLB-MP-HAUL-DT5447-STRSYS-STRCY-STCYR90029374
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Adjust Engine Valve Set | 2028-10-14 | 2028-10-14 | 6 hrs | FY29 | 6 | 90017451 | A1 | 1000290645 | 14.10.2028 | 3000 | CLB-MP-SUPP-SV021 -ENGINE | 3300 | 54098 | 5 | CLB-MP-SUPP-SV021 -ENGINE90017451
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Steering HMU | 2028-10-14 | 2028-10-14 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000035170 | 14.10.2028 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STHMU | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Cyl Steering LH | 2028-10-14 | 2028-10-14 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000035171 | 14.10.2028 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYL | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Cyl Steering RH | 2028-10-14 | 2028-10-14 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035172 | 14.10.2028 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYR | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Cyl Hoist LH | 2028-10-14 | 2028-10-15 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000036187 | 14.10.2028 | 28000 | CLB-MP-HAUL-DT200 -HYDSYS-HOCYL-HCYLL | 7500 | 92548 | 11475 | CLB-MP-HAUL-DT200 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl AOC Fan Motor | 2028-10-15 | 2028-10-15 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035991 | 15.10.2028 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-MTFAN | 7500 | 86259 | 5525 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Pump Brake Control | 2028-10-15 | 2028-10-15 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035996 | 15.10.2028 | 11000 | CLB-MP-HAUL-DT197 -BRKSYS-HYFPP | 7500 | 86259 | 5525 | CLB-MP-HAUL-DT197 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Brake Relay Valve | 2028-10-15 | 2028-10-15 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000079737 | 15.10.2028 | 11000 | CLB-MP-HAUL-DT197 -BRKSYS-BRVRL | 7500 | 86259 | 5525 | CLB-MP-HAUL-DT197 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Service Air Conditioner | 2028-10-16 | 2028-10-16 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160394 | 16.10.2028 | 5500 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-AIRCN | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-AIRCN90017450
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Auto Lube Pump | 2028-10-17 | 2028-10-17 | 4 hrs | FY29 | 4 | 90003064 | A1 | 1000034006 | 17.10.2028 | 6000 | CLB-MP-SUPP-SV021 -GRSYST-ALBPP | 3300 | 54098 | 4488 | CLB-MP-SUPP-SV021 -GRSYST-ALBPP90003064
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Drive Shaft Transmission | 2028-10-17 | 2028-10-17 | 8 hrs | FY29 | 16 | 90017134 | 1 | 1000154435 | 17.10.2028 | 22000 | CLB-MP-HAUL-DT197 -FDRSYS-DRSHT | 7500 | 86259 | 4965 | CLB-MP-HAUL-DT197 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Hyd Pump Steering Main | 2028-10-17 | 2028-10-17 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035169 | 17.10.2028 | 15000 | CLB-MP-HAUL-DT182 -STRSYS-STPMP | 7500 | 92002 | 13503 | CLB-MP-HAUL-DT182 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Steering Link & Arm Rebush | 2028-10-17 | 2028-10-18 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385437 | 17.10.2028 | 30000 | CLB-MP-HAUL-DT182 -STRSYS-STLTR | 7500 | 92002 | 13490 | CLB-MP-HAUL-DT182 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Cyl Hoist LH | 2028-10-19 | 2028-10-20 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034182 | 19.10.2028 | 28000 | CLB-MP-HAUL-DT164 -HYDSYS-HOCYL-HCYLL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Cyl Hoist RH | 2028-10-19 | 2028-10-20 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034183 | 19.10.2028 | 28000 | CLB-MP-HAUL-DT164 -HYDSYS-HOCYL-HCYLR | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Water Cannon Inspect | 2028-10-19 | 2028-10-19 | 3 hrs | FY29 | 3 | 90033661 | A1 | 1000338796 | 19.10.2028 | 6 Monthly | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Service Air Conditioner | 2028-10-21 | 2028-10-21 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160966 | 21.10.2028 | 5500 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-AIRCN | 7500 | 91119 | 14869 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Pump Transmission | 2028-10-21 | 2028-10-21 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000036108 | 21.10.2028 | 11000 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TMCPP | 7500 | 85978 | 5385 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Final Drive LH | 2028-10-21 | 2028-10-22 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000035510 | 21.10.2028 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-FDRVE-FDRLH | 7500 | 84546 | 5379 | CLB-MP-HAUL-DT189 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Final Drive RH | 2028-10-21 | 2028-10-22 | 30 hrs | FY29 | 56 | 90003100 | 1 | 1000035511 | 21.10.2028 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-FDRVE-FDRRH | 7500 | 84546 | 5379 | CLB-MP-HAUL-DT189 -FDRSYS-FDRVE-FDRRH90003100
T264 | Onsite PM | Haul | Fortescue | DT5477 | DT5477 Repl Control Cabinet Coolant | 2028-10-22 | 2028-10-22 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000365220 | 22.10.2028 | 15000 | CLB-MP-HAUL-DT5477-ELCTHV-HVCAB-COOLR | 6500 | 630 | 630 | CLB-MP-HAUL-DT5477-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Cyl Hoist LH | 2028-10-22 | 2028-10-23 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000035009 | 22.10.2028 | 28000 | CLB-MP-HAUL-DT179 -HYDSYS-HOCYL-HCYLL | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT171 | DT171 Repl Drive Shaft Transmission | 2028-10-22 | 2028-10-22 | 8 hrs | FY29 | 16 | 90017134 | 1 | 1000154383 | 22.10.2028 | 22000 | CLB-MP-HAUL-DT171 -FDRSYS-DRSHT | 7500 | 90182 | 3449 | CLB-MP-HAUL-DT171 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Ovhl Axle A Frame | 2028-10-23 | 2028-10-24 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130660 | 23.10.2028 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-AFRME | 7500 | 90698 | 90698 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Valve Steering & AHS EH | 2028-10-24 | 2028-10-24 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078652 | 24.10.2028 | 22000 | CLB-MP-HAUL-DT182 -STRSYS-STVLV | 7500 | 92002 | 5357 | CLB-MP-HAUL-DT182 -STRSYS-STVLV90009881
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Float Brake Cooler Mdule Radiator | 2028-10-27 | 2028-10-28 | 36 hrs | FY29 | 72 | 90018288 | 1 | 1000174832 | 27.10.2028 | 10000 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BCOMR | 4200 | 53807 | 10731 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BCOMR90018288
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Cylinder Steering LHS | 2028-10-27 | 2028-10-27 | 8 hrs | FY29 | 14 | 90029373 | A1 | 1000326650 | 27.10.2028 | 20000 | CLB-MP-HAUL-DT5419-STRSYS-STRCY-STCYL | 6500 | 10988 | 4657 | CLB-MP-HAUL-DT5419-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Service Air Conditioner 12M | 2028-10-27 | 2028-10-27 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000326244 | 27.10.2028 | 12 Monthly | CLB-MP-HAUL-DT5416-STRUCT-CABIN-AIRCN | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Engine Midlife complete | 2028-10-28 | 2028-10-30 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000339707 | 28.10.2028 | 17500 | CLB-MP-HAUL-DT5440-ENGINE | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Cylinder Steering RHS | 2028-10-28 | 2028-10-28 | 8 hrs | FY29 | 14 | 90029374 | A1 | 1000326651 | 28.10.2028 | 20000 | CLB-MP-HAUL-DT5419-STRSYS-STRCY-STCYR | 6500 | 10988 | 4657 | CLB-MP-HAUL-DT5419-STRSYS-STRCY-STCYR90029374
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Final Drive LH Float | 2028-10-29 | 2028-10-30 | 18 hrs | FY29 | 36 | 90013172 | A1 | 1000110280 | 29.10.2028 | 22000 | CLB-MP-SUPP-LL0002-FDRSYS-FDRVE-FDRLH | 3500 | 91736 | 16791 | CLB-MP-SUPP-LL0002-FDRSYS-FDRVE-FDRLH90013172
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Final Drive RH Float | 2028-10-29 | 2028-10-30 | 18 hrs | FY29 | 36 | 90013172 | A1 | 1000110281 | 29.10.2028 | 22000 | CLB-MP-SUPP-LL0002-FDRSYS-FDRVE-FDRRH | 3500 | 91736 | 16791 | CLB-MP-SUPP-LL0002-FDRSYS-FDRVE-FDRRH90013172
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Clutch Pump Drive Rr | 2028-10-29 | 2028-10-29 | 12 hrs | FY29 | 24 | 90013221 | A1 | 1000110283 | 29.10.2028 | 22000 | CLB-MP-SUPP-LL0002-FDRSYS-PDRAX-CPDRA | 3500 | 91736 | 17126 | CLB-MP-SUPP-LL0002-FDRSYS-PDRAX-CPDRA90013221
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Pump Drive Rr Axle | 2028-10-29 | 2028-10-29 | 12 hrs | FY29 | 24 | 90013222 | A1 | 1000110284 | 29.10.2028 | 22000 | CLB-MP-SUPP-LL0002-FDRSYS-PDRAX | 3500 | 91736 | 17126 | CLB-MP-SUPP-LL0002-FDRSYS-PDRAX90013222
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Brake Slack Adjuster Front | 2028-10-30 | 2028-10-30 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072250 | 30.10.2028 | 18000 | CLB-MP-HAUL-DT192 -BRKSYS-SLACK-SLACF | 7500 | 91174 | 1097 | CLB-MP-HAUL-DT192 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Brake Slack Adjuster Rear | 2028-10-30 | 2028-10-30 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072288 | 30.10.2028 | 18000 | CLB-MP-HAUL-DT192 -BRKSYS-SLACK-SLACR | 7500 | 91174 | 1097 | CLB-MP-HAUL-DT192 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Cyl Steering RH | 2028-10-31 | 2028-10-31 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000036060 | 31.10.2028 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYR | 7500 | 88680 | 13193 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYR90003111
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Steering HMU | 2028-11-02 | 2028-11-02 | 8 hrs | FY29 | 8 | 90004004 | 1 | 1000082735 | 02.11.2028 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STHMU | 4200 | 53807 | 5388 | CLB-MP-SUPP-PM0006-STRSYS-STHMU90004004
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Wheel Assembly LHF | 2028-11-03 | 2028-11-04 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000346780 | 03.11.2028 | 24000 | CLB-MP-HAUL-DT5444-STRUCT-AXLES-HUBLH | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Wheel Assembly RHF | 2028-11-03 | 2028-11-04 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000346781 | 03.11.2028 | 24000 | CLB-MP-HAUL-DT5444-STRUCT-AXLES-HUBRH | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 1Y Air Tank LH External Inspect | 2028-11-04 | 2028-11-04 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389338 | 04.11.2028 | 12 Monthly | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH | 7500 | 90894 | 90894 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 1Y Air Tank RH External Inspect | 2028-11-04 | 2028-11-04 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389340 | 04.11.2028 | 12 Monthly | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH | 7500 | 90894 | 90894 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Cyl Suspension LHR | 2028-11-04 | 2028-11-05 | 23 hrs | FY29 | 42 | 90003122 | 1 | 1000035350 | 04.11.2028 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLR | 7500 | 89749 | 5084 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLR90003122
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Service Air Conditioner 12M | 2028-11-04 | 2028-11-04 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000326477 | 04.11.2028 | 12 Monthly | CLB-MP-HAUL-DT5418-STRUCT-CABIN-AIRCN | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Service Suspension Cylinders | 2028-11-05 | 2028-11-05 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106895 | 05.11.2028 | 11000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN | 7500 | 89749 | 20387 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN90012840
T264 | Onsite PM | Haul | Fortescue | DT5475 | DT5475 Repl Control Cabinet Coolant | 2028-11-07 | 2028-11-07 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000363999 | 07.11.2028 | 15000 | CLB-MP-HAUL-DT5475-ELCTHV-HVCAB-COOLR | 6500 | 211 | 211 | CLB-MP-HAUL-DT5475-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Steering Ball Studs | 2028-11-07 | 2028-11-08 | 19 hrs | FY29 | 35 | 90038356 | A1 | 1000385456 | 07.11.2028 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STLTR | 7500 | 91174 | 27983 | CLB-MP-HAUL-DT192 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Cyl Steering RH | 2028-11-08 | 2028-11-08 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035468 | 08.11.2028 | 15000 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYR | 7500 | 83931 | 13040 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl AOC Fan Motor | 2028-11-08 | 2028-11-08 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035585 | 08.11.2028 | 22000 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-MTFAN | 7500 | 90698 | 5026 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Valve Steering & AHS EH | 2028-11-08 | 2028-11-08 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078766 | 08.11.2028 | 22000 | CLB-MP-HAUL-DT190 -STRSYS-STVLV | 7500 | 90698 | 28565 | CLB-MP-HAUL-DT190 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Relay Valve | 2028-11-08 | 2028-11-08 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078762 | 08.11.2028 | 11000 | CLB-MP-HAUL-DT190 -BRKSYS-BRVRL | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Pump Transmission | 2028-11-10 | 2028-11-10 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035045 | 10.11.2028 | 11000 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TMCPP | 7500 | 89560 | 4986 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Cyl Hoist LH | 2028-11-10 | 2028-11-11 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000035471 | 10.11.2028 | 28000 | CLB-MP-HAUL-DT188 -HYDSYS-HOCYL-HCYLL | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -HYDSYS-HOCYL-HCYLL90003114
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Wheel Assembly LHF | 2028-11-11 | 2028-11-12 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000300330 | 11.11.2028 | 24000 | CLB-MP-HAUL-DT5390-STRUCT-AXLES-HUBLH | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Wheel Assembly RHF | 2028-11-11 | 2028-11-12 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000300331 | 11.11.2028 | 24000 | CLB-MP-HAUL-DT5390-STRUCT-AXLES-HUBRH | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5501 | DT5501 Repl Control Cabinet Coolant | 2028-11-11 | 2028-11-11 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000383537 | 11.11.2028 | 15000 | CLB-MP-HAUL-DT5501-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5501-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5502 | DT5502 Repl Control Cabinet Coolant | 2028-11-11 | 2028-11-11 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000383628 | 11.11.2028 | 15000 | CLB-MP-HAUL-DT5502-ELCTHV-HVCAB-COOLR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5502-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Pump Drive Driveshaft Unis | 2028-11-12 | 2028-11-12 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035984 | 12.11.2028 | 11000 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR-DRSHT | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Service Air Conditioner | 2028-11-12 | 2028-11-12 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160380 | 12.11.2028 | 5500 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-AIRCN | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Wheel Assembly LHF | 2028-11-13 | 2028-11-14 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000314546 | 13.11.2028 | 24000 | CLB-MP-HAUL-DT5411-STRUCT-AXLES-HUBLH | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Wheel Assembly RHF | 2028-11-13 | 2028-11-14 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000314547 | 13.11.2028 | 24000 | CLB-MP-HAUL-DT5411-STRUCT-AXLES-HUBRH | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Cylinder Steering RHS | 2028-11-15 | 2028-11-15 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000347001 | 15.11.2028 | 20000 | CLB-MP-HAUL-DT5445-STRSYS-STRCY-STCYR | 6500 | 7612 | 4933 | CLB-MP-HAUL-DT5445-STRSYS-STRCY-STCYR90029374
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Service Suspension Cylinders | 2028-11-15 | 2028-11-15 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106941 | 15.11.2028 | 11000 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN | 7500 | 91174 | 15811 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Hyd Pump Steering Main | 2028-11-16 | 2028-11-16 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035224 | 16.11.2028 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STPMP | 7500 | 90364 | 12780 | CLB-MP-HAUL-DT183 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Steering HMU | 2028-11-16 | 2028-11-16 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000035225 | 16.11.2028 | 15000 | CLB-MP-HAUL-DT183 -STRSYS-STHMU | 7500 | 90364 | 12780 | CLB-MP-HAUL-DT183 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Service Air Conditioner | 2028-11-16 | 2028-11-16 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160388 | 16.11.2028 | 5500 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-AIRCN | 7500 | 92002 | 14039 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Engine Midlife complete | 2028-11-16 | 2028-11-18 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000362656 | 16.11.2028 | 17500 | CLB-MP-HAUL-DT5471-ENGINE | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Cyl Steering LH | 2028-11-17 | 2028-11-17 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000035281 | 17.11.2028 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYL | 7500 | 92088 | 12790 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Cyl Steering RH | 2028-11-17 | 2028-11-17 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035282 | 17.11.2028 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYR | 7500 | 92088 | 12790 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Valve Steering & AHS EH | 2028-11-17 | 2028-11-17 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000079703 | 17.11.2028 | 22000 | CLB-MP-HAUL-DT193 -STRSYS-STVLV | 7500 | 83140 | 27982 | CLB-MP-HAUL-DT193 -STRSYS-STVLV90009881
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Wheel Assembly LHF | 2028-11-17 | 2028-11-18 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000346713 | 17.11.2028 | 24000 | CLB-MP-HAUL-DT5443-STRUCT-AXLES-HUBLH | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Wheel Assembly RHF | 2028-11-17 | 2028-11-18 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000346714 | 17.11.2028 | 24000 | CLB-MP-HAUL-DT5443-STRUCT-AXLES-HUBRH | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Drive Shaft Transmission | 2028-11-18 | 2028-11-18 | 8 hrs | FY29 | 16 | 90017134 | 1 | 1000154429 | 18.11.2028 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-DRSHT | 7500 | 86451 | 26367 | CLB-MP-HAUL-DT194 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Tyre Sense Battery | 2028-11-21 | 2028-11-21 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163974 | 21.11.2028 | 24 Monthly | CLB-MP-HAUL-DT199 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT199 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Midlife Valve Set - Adjust | 2028-11-21 | 2028-11-21 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390958 | 21.11.2028 | 11000 | CLB-MP-HAUL-DT194 -ENGINE | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Engine Midlife complete | 2028-11-21 | 2028-11-25 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156971 | 21.11.2028 | 11000 | CLB-MP-HAUL-DT194 -ENGINE | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Service Suspension Cylinders | 2028-11-21 | 2028-11-21 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106943 | 21.11.2028 | 11000 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Air Dryer | 2028-11-21 | 2028-11-21 | 7 hrs | FY29 | 14 | 90003115 | 1 | 1000034901 | 21.11.2028 | 22000 | CLB-MP-HAUL-DT177 -PNEUMC-AIRDR | 7500 | 81791 | 48217 | CLB-MP-HAUL-DT177 -PNEUMC-AIRDR90003115
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Tyre Sense Battery | 2028-11-21 | 2028-11-21 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163948 | 21.11.2028 | 24 Monthly | CLB-MP-HAUL-DT173 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT173 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Wheel Assembly LHF | 2028-11-21 | 2028-11-22 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000346592 | 21.11.2028 | 24000 | CLB-MP-HAUL-DT5442-STRUCT-AXLES-HUBLH | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Repl Wheel Assembly RHF | 2028-11-21 | 2028-11-22 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000346593 | 21.11.2028 | 24000 | CLB-MP-HAUL-DT5442-STRUCT-AXLES-HUBRH | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Drive Line Axle RH | 2028-11-22 | 2028-11-22 | 4 hrs | FY29 | 8 | 90014552 | 1 | 1000123590 | 22.11.2028 | 30000 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX-AXLRH | 7500 | 83473 | 12672 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX-AXLRH90014552
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Midlife Valve Set - Adjust | 2028-11-23 | 2028-11-23 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390955 | 23.11.2028 | 11000 | CLB-MP-HAUL-DT191 -ENGINE | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Engine Midlife complete | 2028-11-23 | 2028-11-27 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156923 | 23.11.2028 | 11000 | CLB-MP-HAUL-DT191 -ENGINE | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Service Suspension Cylinders | 2028-11-23 | 2028-11-23 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106940 | 23.11.2028 | 11000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Spiders Transmission Driveshaft | 2028-11-23 | 2028-11-23 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154424 | 23.11.2028 | 11000 | CLB-MP-HAUL-DT191 -FDRSYS-DRSHT-UNVSL | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Steering HMU | 2028-11-24 | 2028-11-24 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000034674 | 24.11.2028 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STHMU | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Cyl Steering RH | 2028-11-24 | 2028-11-24 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034676 | 24.11.2028 | 15000 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYR | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT169 | DT169 Service Air Conditioner | 2028-11-24 | 2028-11-24 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160376 | 24.11.2028 | 5500 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-AIRCN | 7500 | 93410 | 14340 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Hoist & Rear Brake Pump | 2028-11-24 | 2028-11-24 | 5 hrs | FY29 | 5 | 90004008 | 1 | 1000044737 | 24.11.2028 | 20000 | CLB-MP-SUPP-WC014 -HYDSYS-HOPMP | 5000 | 65823 | 7973 | CLB-MP-SUPP-WC014 -HYDSYS-HOPMP90004008
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Engine Pump Drive | 2028-11-25 | 2028-11-26 | 32 hrs | FY29 | 62 | 90003089 | 1 | 1000036163 | 25.11.2028 | 22000 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR | 7500 | 92548 | 4618 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR90003089
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Cylinder Steering LHS | 2028-11-26 | 2028-11-26 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000350437 | 26.11.2028 | 20000 | CLB-MP-HAUL-DT5455-STRSYS-STRCY-STCYL | 6500 | 7738 | 4869 | CLB-MP-HAUL-DT5455-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Wheel Assembly LHF | 2028-11-26 | 2028-11-27 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000347394 | 26.11.2028 | 24000 | CLB-MP-HAUL-DT5447-STRUCT-AXLES-HUBLH | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Repl Wheel Assembly RHF | 2028-11-26 | 2028-11-27 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000347395 | 26.11.2028 | 24000 | CLB-MP-HAUL-DT5447-STRUCT-AXLES-HUBRH | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT200 | DT200 Repl Steering Link & Arm Rebush | 2028-11-26 | 2028-11-27 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385473 | 26.11.2028 | 30000 | CLB-MP-HAUL-DT200 -STRSYS-STLTR | 7500 | 92548 | 12596 | CLB-MP-HAUL-DT200 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Cyl Steering LH | 2028-11-26 | 2028-11-26 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000036059 | 26.11.2028 | 15000 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYL | 7500 | 88680 | 12630 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Transmission Oil Cooler | 2028-11-27 | 2028-11-27 | 13 hrs | FY29 | 13 | 90003532 | 1 | 1000040991 | 27.11.2028 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TROLC | 7500 | 92002 | 26654 | CLB-MP-HAUL-DT182 -TRNSYS-TROLC90003532
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Brake Cool Pmp & Mtr - Repl | 2028-11-29 | 2028-11-29 | 4 hrs | FY29 | 8 | 90018286 | 1 | 1000174669 | 29.11.2028 | 10000 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM1 | 4200 | 71996 | 1615 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM190018286
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Wheel Assembly LHF | 2028-11-30 | 2028-12-01 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000313966 | 30.11.2028 | 24000 | CLB-MP-HAUL-DT5404-STRUCT-AXLES-HUBLH | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5404 | DT5404 Repl Wheel Assembly RHF | 2028-11-30 | 2028-12-01 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000313967 | 30.11.2028 | 24000 | CLB-MP-HAUL-DT5404-STRUCT-AXLES-HUBRH | 6500 | 8870 | 8870 | CLB-MP-HAUL-DT5404-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Wheel Assembly LHF | 2028-12-01 | 2028-12-02 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000347319 | 01.12.2028 | 24000 | CLB-MP-HAUL-DT5446-STRUCT-AXLES-HUBLH | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Wheel Assembly RHF | 2028-12-01 | 2028-12-02 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000347320 | 01.12.2028 | 24000 | CLB-MP-HAUL-DT5446-STRUCT-AXLES-HUBRH | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Drive Driveshaft Unis | 2028-12-01 | 2028-12-01 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035810 | 01.12.2028 | 11000 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR-DRSHT | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Brake Relay Valve | 2028-12-01 | 2028-12-01 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078819 | 01.12.2028 | 11000 | CLB-MP-HAUL-DT194 -BRKSYS-BRVRL | 7500 | 86451 | 4331 | CLB-MP-HAUL-DT194 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Service Air Conditioner | 2028-12-01 | 2028-12-01 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160387 | 01.12.2028 | 5500 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-AIRCN | 7500 | 83441 | 10076 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Replace Water Cannon | 2028-12-01 | 2028-12-01 | 12 hrs | FY29 | 24 | 90015535 | 1 | 1000133452 | 01.12.2028 | 12 Monthly | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | 5000 | 67273 | 3900 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON90015535
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl AOC Fan Motor | 2028-12-03 | 2028-12-03 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035817 | 03.12.2028 | 22000 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-MTFAN | 7500 | 86451 | 4331 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Drive Shaft Transmission | 2028-12-04 | 2028-12-04 | 8 hrs | FY29 | 16 | 90017134 | 1 | 1000154407 | 04.12.2028 | 22000 | CLB-MP-HAUL-DT183 -FDRSYS-DRSHT | 7500 | 90364 | 26375 | CLB-MP-HAUL-DT183 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Pump Hoist & Brake | 2028-12-04 | 2028-12-04 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035229 | 04.12.2028 | 22000 | CLB-MP-HAUL-DT183 -HYDSYS-HOPMP | 7500 | 90364 | 27555 | CLB-MP-HAUL-DT183 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Engine Pump Drive | 2028-12-06 | 2028-12-07 | 32 hrs | FY29 | 62 | 90003089 | 1 | 1000035206 | 06.12.2028 | 22000 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR | 7500 | 90364 | 4372 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR90003089
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Steering Link & Arm Rebush | 2028-12-06 | 2028-12-07 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385399 | 06.12.2028 | 30000 | CLB-MP-HAUL-DT163 -STRSYS-STLTR | 7500 | 81237 | 12238 | CLB-MP-HAUL-DT163 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Steering LH | 2028-12-06 | 2028-12-06 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034123 | 06.12.2028 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYL | 7500 | 81237 | 12238 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Steering RH | 2028-12-06 | 2028-12-06 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034124 | 06.12.2028 | 15000 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYR | 7500 | 81237 | 12238 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Drive Driveshaft Unis | 2028-12-06 | 2028-12-06 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000034988 | 06.12.2028 | 11000 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR-DRSHT | 7500 | 84079 | 16664 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Cyl Hoist LH | 2028-12-06 | 2028-12-07 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034734 | 06.12.2028 | 28000 | CLB-MP-HAUL-DT174 -HYDSYS-HOCYL-HCYLL | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Cyl Hoist RH | 2028-12-06 | 2028-12-07 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034735 | 06.12.2028 | 28000 | CLB-MP-HAUL-DT174 -HYDSYS-HOCYL-HCYLR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Engine Midlife complete | 2028-12-06 | 2028-12-08 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000362701 | 06.12.2028 | 17500 | CLB-MP-HAUL-DT5472-ENGINE | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Pump Brake Control | 2028-12-07 | 2028-12-07 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035331 | 07.12.2028 | 11000 | CLB-MP-HAUL-DT186 -BRKSYS-HYFPP | 7500 | 89749 | 16218 | CLB-MP-HAUL-DT186 -BRKSYS-HYFPP90003106
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Service Air Conditioner 12M | 2028-12-07 | 2028-12-07 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000326386 | 07.12.2028 | 12 Monthly | CLB-MP-HAUL-DT5417-STRUCT-CABIN-AIRCN | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Steering LH | 2028-12-08 | 2028-12-08 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000035711 | 08.12.2028 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYL | 7500 | 91174 | 12341 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Brake Slack Adjuster Front | 2028-12-09 | 2028-12-09 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072243 | 09.12.2028 | 18000 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACF | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Brake Slack Adjuster Rear | 2028-12-09 | 2028-12-09 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072281 | 09.12.2028 | 18000 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACR | 7500 | 92088 | 18375 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Transmission Pump | 2028-12-10 | 2028-12-10 | 6 hrs | FY29 | 6 | 90003991 | 1 | 1000044774 | 10.12.2028 | 10000 | CLB-MP-SUPP-WC015 -TRNSYS-TRPMP-TMCPP | 5000 | 67897 | 8275 | CLB-MP-SUPP-WC015 -TRNSYS-TRPMP-TMCPP90003991
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Brake Slack Adjuster Front | 2028-12-12 | 2028-12-12 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072241 | 12.12.2028 | 18000 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACF | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Brake Slack Adjuster Rear | 2028-12-12 | 2028-12-12 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072279 | 12.12.2028 | 18000 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACR | 7500 | 90364 | 18244 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Service Suspension Cylinders | 2028-12-12 | 2028-12-12 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106883 | 12.12.2028 | 11000 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN | 7500 | 83749 | 23899 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Tyre Sense Battery | 2028-12-13 | 2028-12-13 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163957 | 13.12.2028 | 24 Monthly | CLB-MP-HAUL-DT182 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT182 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Hyd Motor Axle Lube Rear | 2028-12-13 | 2028-12-13 | 9 hrs | FY29 | 9 | 90003101 | 1 | 1000034664 | 13.12.2028 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-HYM01 | 7500 | 82651 | 4203 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-HYM0190003101
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Overhaul Air Conditioner 24M | 2028-12-13 | 2028-12-15 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000339690 | 13.12.2028 | 24 Monthly | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN90029460
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 5000Hr Valve Set | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 24 | 90028725 | A1 | 1000289428 | 14.12.2028 | 5000 | CLB-MP-SUPP-WC013 -ENGINE | 5000 | 63833 | 3387 | CLB-MP-SUPP-WC013 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Service Airconditioner | 2028-12-14 | 2028-12-14 | 12 hrs | FY29 | 12 | 90028728 | A1 | 1000289425 | 14.12.2028 | 5000 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN | 5000 | 63833 | 10928 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN90028728
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 5000Hr Valve set | 2028-12-15 | 2028-12-15 | 12 hrs | FY29 | 24 | 90028725 | A1 | 1000289434 | 15.12.2028 | 5000 | CLB-MP-SUPP-WC014 -ENGINE | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Service Airconditioner | 2028-12-15 | 2028-12-15 | 12 hrs | FY29 | 12 | 90028728 | A1 | 1000289431 | 15.12.2028 | 5000 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN | 5000 | 65823 | 545 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN90028728
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Pump Main Hydraulic | 2028-12-16 | 2028-12-16 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000326670 | 16.12.2028 | 20000 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-HYPMP | 6500 | 10988 | 3763 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-HYPMP90029366
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Cyl Suspension RHR | 2028-12-17 | 2028-12-18 | 23 hrs | FY29 | 42 | 90003122 | 1 | 1000035296 | 17.12.2028 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYRR | 7500 | 92088 | 4203 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYRR90003122
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Ovhl Axle Housing Dogbone | 2028-12-17 | 2028-12-18 | 22 hrs | FY29 | 42 | 90003118 | 1 | 1000035345 | 17.12.2028 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-TAGLK | 7500 | 89749 | 42779 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-TAGLK90003118
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Steering Linkages | 2028-12-17 | 2028-12-17 | 12 hrs | FY29 | 24 | 90003056 | A1 | 1000033876 | 17.12.2028 | 9000 | CLB-MP-SUPP-SV019 -STRSYS-STLTR | 2500 | 48856 | 2844 | CLB-MP-SUPP-SV019 -STRSYS-STLTR90003056
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Cylinder Steering LH | 2028-12-17 | 2028-12-17 | 14 hrs | FY29 | 26 | 90003054 | A1 | 1000033873 | 17.12.2028 | 9000 | CLB-MP-SUPP-SV019 -STRSYS-STRCY-STCYL | 2500 | 48856 | 2844 | CLB-MP-SUPP-SV019 -STRSYS-STRCY-STCYL90003054
777F | Onsite PM | Haul | Fortescue | SV019 | SV019 Replace Pump Hoist | 2028-12-17 | 2028-12-17 | 6 hrs | FY29 | 6 | 90003059 | A1 | 1000033879 | 17.12.2028 | 9000 | CLB-MP-SUPP-SV019 -HYDSYS-HOPMP | 2500 | 48856 | 2844 | CLB-MP-SUPP-SV019 -HYDSYS-HOPMP90003059
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Hyd Motor Axle Lube Rear | 2028-12-18 | 2028-12-18 | 9 hrs | FY29 | 9 | 90003101 | 1 | 1000034829 | 18.12.2028 | 22000 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-HYM01 | 7500 | 85284 | 26295 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Hyd Pump Steering Main | 2028-12-18 | 2028-12-18 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035334 | 18.12.2028 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STPMP | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Steering HMU | 2028-12-18 | 2028-12-18 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000035335 | 18.12.2028 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STHMU | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Cyl Steering RH | 2028-12-18 | 2028-12-18 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035337 | 18.12.2028 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYR | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Pump Torque Converter Charge | 2028-12-19 | 2028-12-19 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080219 | 19.12.2028 | 22000 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TCCPP | 7500 | 88680 | 4182 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Wheel LH | 2028-12-19 | 2028-12-20 | 32 hrs | FY29 | 38 | 90003104 | 2 | 1000036051 | 19.12.2028 | 22000 | CLB-MP-HAUL-DT198 -STRUCT-AXLES-HUBLH | 7500 | 88680 | 4182 | CLB-MP-HAUL-DT198 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Brake Slack Adjuster Front | 2028-12-19 | 2028-12-19 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072253 | 19.12.2028 | 18000 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACF | 7500 | 82554 | 18183 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Brake Slack Adjuster Rear | 2028-12-19 | 2028-12-19 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072291 | 19.12.2028 | 18000 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACR | 7500 | 82554 | 18183 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Tyre Sense Battery | 2028-12-20 | 2028-12-20 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163960 | 20.12.2028 | 24 Monthly | CLB-MP-HAUL-DT185 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT185 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Water Cannon Inspect | 2028-12-22 | 2028-12-22 | 3 hrs | FY29 | 3 | 90033661 | A1 | 1000338995 | 22.12.2028 | 6 Monthly | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | 5000 | 64118 | 9073 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON90033661
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Wheel Assembly LHF | 2028-12-23 | 2028-12-24 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000349078 | 23.12.2028 | 24000 | CLB-MP-HAUL-DT5448-STRUCT-AXLES-HUBLH | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Wheel Assembly RHF | 2028-12-23 | 2028-12-24 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000349079 | 23.12.2028 | 24000 | CLB-MP-HAUL-DT5448-STRUCT-AXLES-HUBRH | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Service Air Conditioner | 2028-12-23 | 2028-12-23 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160398 | 23.12.2028 | 5500 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-AIRCN | 7500 | 91174 | 8325 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Wheel Assembly LHF | 2028-12-25 | 2028-12-26 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000349122 | 25.12.2028 | 24000 | CLB-MP-HAUL-DT5449-STRUCT-AXLES-HUBLH | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Repl Wheel Assembly RHF | 2028-12-25 | 2028-12-26 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000349123 | 25.12.2028 | 24000 | CLB-MP-HAUL-DT5449-STRUCT-AXLES-HUBRH | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Rotochamber RHR | 2028-12-25 | 2028-12-25 | 5 hrs | FY29 | 5 | 90009309 | 1 | 1000072468 | 25.12.2028 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTRR | 7500 | 92002 | 4021 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTRR90009309
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Hoist & Brake | 2028-12-25 | 2028-12-25 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035174 | 25.12.2028 | 22000 | CLB-MP-HAUL-DT182 -HYDSYS-HOPMP | 7500 | 92002 | 4017 | CLB-MP-HAUL-DT182 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Relay Valve | 2028-12-25 | 2028-12-25 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078648 | 25.12.2028 | 11000 | CLB-MP-HAUL-DT182 -BRKSYS-BRVRL | 7500 | 92002 | 16119 | CLB-MP-HAUL-DT182 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Tyre Sense Battery | 2028-12-26 | 2028-12-26 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163970 | 26.12.2028 | 24 Monthly | CLB-MP-HAUL-DT195 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT195 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Service Air Conditioner | 2028-12-27 | 2028-12-27 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160374 | 27.12.2028 | 5500 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-AIRCN | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-AIRCN90017450
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Repl Rear Axle Cooling Fan Motor | 2029-01-01 | 2029-01-01 | 2 hrs | FY29 | 2 | 90003997 | 1 | 1000221748 | 01.01.2029 | 10000 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-MTFAN | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-MTFAN90003997
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Rear Axle Oil Pump | 2029-01-01 | 2029-01-01 | 2 hrs | FY29 | 2 | 90003996 | 1 | 1000221747 | 01.01.2029 | 10000 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-HYPUM | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-HYPUM90003996
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Ovhl Axle A Frame | 2029-01-01 | 2029-01-02 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130667 | 01.01.2029 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-AFRME | 7500 | 86259 | 25918 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Transmission | 2029-01-01 | 2029-01-02 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000035635 | 01.01.2029 | 22000 | CLB-MP-HAUL-DT191 -TRNSYS-TRANS | 7500 | 87047 | 3873 | CLB-MP-HAUL-DT191 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Pump Transmission | 2029-01-01 | 2029-01-01 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035637 | 01.01.2029 | 11000 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TMCPP | 7500 | 87047 | 3873 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TMCPP90003096
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Cylinder Suspension RHR | 2029-01-02 | 2029-01-03 | 26 hrs | FY29 | 50 | 90003071 | A1 | 1000034016 | 02.01.2029 | 18000 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYRR | 3300 | 54098 | 9678 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYRR90003071
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Pump Drive Driveshaft Unis | 2029-01-02 | 2029-01-02 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035636 | 02.01.2029 | 11000 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR-DRSHT | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Transmission Oil Cooler | 2029-01-02 | 2029-01-02 | 13 hrs | FY29 | 13 | 90003532 | 1 | 1000041000 | 02.01.2029 | 22000 | CLB-MP-HAUL-DT191 -TRNSYS-TROLC | 7500 | 87047 | 3873 | CLB-MP-HAUL-DT191 -TRNSYS-TROLC90003532
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Service Air Conditioner | 2029-01-02 | 2029-01-02 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160392 | 02.01.2029 | 5500 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-AIRCN | 7500 | 89749 | 14154 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Wheel Assembly LHF | 2029-01-04 | 2029-01-05 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000349965 | 04.01.2029 | 24000 | CLB-MP-HAUL-DT5453-STRUCT-AXLES-HUBLH | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Wheel Assembly RHF | 2029-01-04 | 2029-01-05 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000349966 | 04.01.2029 | 24000 | CLB-MP-HAUL-DT5453-STRUCT-AXLES-HUBRH | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRUCT-AXLES-HUBRH90029370
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Wheel Assembly LHF | 2029-01-04 | 2029-01-05 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000349623 | 04.01.2029 | 24000 | CLB-MP-HAUL-DT5451-STRUCT-AXLES-HUBLH | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Repl Wheel Assembly RHF | 2029-01-04 | 2029-01-05 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000349624 | 04.01.2029 | 24000 | CLB-MP-HAUL-DT5451-STRUCT-AXLES-HUBRH | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Hyd Pump Steering Main | 2029-01-04 | 2029-01-04 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034618 | 04.01.2029 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STPMP | 7500 | 92351 | 11680 | CLB-MP-HAUL-DT172 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Steering HMU | 2029-01-04 | 2029-01-04 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000034619 | 04.01.2029 | 15000 | CLB-MP-HAUL-DT172 -STRSYS-STHMU | 7500 | 92351 | 11680 | CLB-MP-HAUL-DT172 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Service Suspension Cylinders | 2029-01-07 | 2029-01-07 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106873 | 07.01.2029 | 11000 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN | 7500 | 78966 | 10144 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Drive Shaft Transmission | 2029-01-09 | 2029-01-09 | 8 hrs | FY29 | 16 | 90017134 | 1 | 1000154433 | 09.01.2029 | 22000 | CLB-MP-HAUL-DT196 -FDRSYS-DRSHT | 7500 | 85161 | 25254 | CLB-MP-HAUL-DT196 -FDRSYS-DRSHT90017134
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Tyre Sense Battery | 2029-01-09 | 2029-01-09 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163942 | 09.01.2029 | 24 Monthly | CLB-MP-HAUL-DT167 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT167 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 1Y Air Tank LH External Inspect | 2029-01-10 | 2029-01-10 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389422 | 10.01.2029 | 12 Monthly | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH | 7500 | 90973 | 42723 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 1Y Air Tank RH External Inspect | 2029-01-10 | 2029-01-10 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389424 | 10.01.2029 | 12 Monthly | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH | 7500 | 90973 | 42723 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Engine Midlife complete | 2029-01-10 | 2029-01-12 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000371430 | 10.01.2029 | 17500 | CLB-MP-HAUL-DT5485-ENGINE | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Engine Midlife Complete | 2029-01-10 | 2029-01-12 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000371230 | 10.01.2029 | 17500 | CLB-MP-HAUL-DT5484-ENGINE | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Engine Midlife complete | 2029-01-10 | 2029-01-12 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000369074 | 10.01.2029 | 17500 | CLB-MP-HAUL-DT5483-ENGINE | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Engine Midlife complete | 2029-01-10 | 2029-01-12 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000366488 | 10.01.2029 | 17500 | CLB-MP-HAUL-DT5481-ENGINE | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Engine Midlife complete | 2029-01-10 | 2029-01-12 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000365693 | 10.01.2029 | 17500 | CLB-MP-HAUL-DT5479-ENGINE | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Valve Steering & AHS EH | 2029-01-11 | 2029-01-11 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078633 | 11.01.2029 | 22000 | CLB-MP-HAUL-DT180 -STRSYS-STVLV | 7500 | 89560 | 26227 | CLB-MP-HAUL-DT180 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Transmission | 2029-01-11 | 2029-01-11 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035155 | 11.01.2029 | 11000 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP | 7500 | 92002 | 14699 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Ovhl Axle A Frame | 2029-01-12 | 2029-01-13 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130647 | 12.01.2029 | 22000 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-AFRME | 7500 | 85284 | 35516 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-AFRME90015390
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Water Cannon & Valves Repl | 2029-01-12 | 2029-01-13 | 24 hrs | FY29 | 48 | 90033662 | A1 | 1000338795 | 12.01.2029 | 24 Monthly | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | 5000 | 65823 | 12836 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON90033662
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Valve Steering & AHS EH | 2029-01-13 | 2029-01-13 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078519 | 13.01.2029 | 22000 | CLB-MP-HAUL-DT172 -STRSYS-STVLV | 7500 | 92351 | 3470 | CLB-MP-HAUL-DT172 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Pump Transmission | 2029-01-13 | 2029-01-13 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000034048 | 13.01.2029 | 11000 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TMCPP | 7500 | 83473 | 3577 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Air Dryer | 2029-01-13 | 2029-01-13 | 7 hrs | FY29 | 14 | 90003115 | 1 | 1000034073 | 13.01.2029 | 22000 | CLB-MP-HAUL-DT184 -PNEUMC-AIRDR | 7500 | 83473 | 48934 | CLB-MP-HAUL-DT184 -PNEUMC-AIRDR90003115
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000376517 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5500-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000376470 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5499-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000375545 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5498-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000375412 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5497-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000374035 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5496-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000373984 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5495-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000373596 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5494-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000373338 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5493-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000373084 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5492-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000372695 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5491-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000367585 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5482-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000366353 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5480-ENGINE | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Engine Midlife complete | 2029-01-13 | 2029-01-15 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000365643 | 13.01.2029 | 17500 | CLB-MP-HAUL-DT5478-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-ENGINE90029500
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Engine Midlife Complete | 2029-01-14 | 2029-01-18 | 94 hrs | FY29 | 122 | 90028722 | A1 | 1000289472 | 14.01.2029 | 10000 | CLB-MP-SUPP-WC3108-ENGINE | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-ENGINE90028722
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Repl PTO Uni's & Driveshaft | 2029-01-14 | 2029-01-14 | 2 hrs | FY29 | 2 | 90031094 | A1 | 1000307812 | 14.01.2029 | 10000 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT90031094
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Transmission Pump | 2029-01-14 | 2029-01-14 | 6 hrs | FY29 | 6 | 90003991 | 1 | 1000221742 | 14.01.2029 | 10000 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP90003991
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Overhaul Airconditioner | 2029-01-14 | 2029-01-15 | 24 hrs | FY29 | 24 | 90028727 | A1 | 1000289474 | 14.01.2029 | 10000 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN | 5000 | 17738 | 7923 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN90028727
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Midlife Valve Set - Adjust | 2029-01-14 | 2029-01-14 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390953 | 14.01.2029 | 11000 | CLB-MP-HAUL-DT189 -ENGINE | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Engine Midlife complete | 2029-01-14 | 2029-01-18 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156891 | 14.01.2029 | 11000 | CLB-MP-HAUL-DT189 -ENGINE | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Service Suspension Cylinders | 2029-01-14 | 2029-01-14 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106898 | 14.01.2029 | 11000 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Spiders Transmission Driveshaft | 2029-01-14 | 2029-01-14 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154420 | 14.01.2029 | 11000 | CLB-MP-HAUL-DT189 -FDRSYS-DRSHT-UNVSL | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -FDRSYS-DRSHT-UNVSL90017135
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Overhaul Air Conditioner 24M | 2029-01-14 | 2029-01-16 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000346231 | 14.01.2029 | 24 Monthly | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 1Y Air Tank LH External Inspect | 2029-01-17 | 2029-01-17 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389310 | 17.01.2029 | 12 Monthly | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH | 7500 | 80996 | 48008 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 1Y Air Tank RH External Inspect | 2029-01-17 | 2029-01-17 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389312 | 17.01.2029 | 12 Monthly | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH | 7500 | 80996 | 48008 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Tyre Sense Battery | 2029-01-17 | 2029-01-17 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163988 | 17.01.2029 | 24 Monthly | CLB-MP-HAUL-DT224 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT224 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Slack Adjuster Front | 2029-01-17 | 2029-01-17 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072248 | 17.01.2029 | 18000 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACF | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Slack Adjuster Rear | 2029-01-17 | 2029-01-17 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072286 | 17.01.2029 | 18000 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACR | 7500 | 90698 | 17590 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Engine Midlife complete | 2029-01-17 | 2029-01-19 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000371549 | 17.01.2029 | 17500 | CLB-MP-HAUL-DT5486-ENGINE | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Wheel Assembly LHF | 2029-01-18 | 2029-01-19 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000350415 | 18.01.2029 | 24000 | CLB-MP-HAUL-DT5454-STRUCT-AXLES-HUBLH | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Repl Wheel Assembly RHF | 2029-01-18 | 2029-01-19 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000350416 | 18.01.2029 | 24000 | CLB-MP-HAUL-DT5454-STRUCT-AXLES-HUBRH | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Tyre Sense Battery | 2029-01-18 | 2029-01-18 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163945 | 18.01.2029 | 24 Monthly | CLB-MP-HAUL-DT170 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT170 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Cyl Hoist RH | 2029-01-18 | 2029-01-19 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034955 | 18.01.2029 | 28000 | CLB-MP-HAUL-DT178 -HYDSYS-HOCYL-HCYLR | 7500 | 81600 | 9538 | CLB-MP-HAUL-DT178 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Engine Midlife complete | 2029-01-18 | 2029-01-20 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000361781 | 18.01.2029 | 17500 | CLB-MP-HAUL-DT5473-ENGINE | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Engine Pump Drive | 2029-01-19 | 2029-01-20 | 32 hrs | FY29 | 62 | 90003089 | 1 | 1000035923 | 19.01.2029 | 22000 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR | 7500 | 85161 | 3510 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR90003089
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Tyre Sense Battery | 2029-01-19 | 2029-01-19 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163969 | 19.01.2029 | 24 Monthly | CLB-MP-HAUL-DT194 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT194 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Service Air Conditioner | 2029-01-19 | 2029-01-19 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160390 | 19.01.2029 | 5500 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-AIRCN | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-AIRCN90017450
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Repl Engine Assy 6516B | 2029-01-19 | 2029-01-21 | 51 hrs | FY29 | 198 | 90029172 | A1 | 1000290837 | 19.01.2029 | 22000 | CLB-MP-SUPP-PM0004-ENGINE | 3500 | 91736 | 13390 | CLB-MP-SUPP-PM0004-ENGINE90029172
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Suspension Cylinder RHR | 2029-01-19 | 2029-01-19 | 16 hrs | FY29 | 28 | 90004014 | 1 | 1000044806 | 19.01.2029 | 20000 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYRR | 5000 | 67897 | 7727 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYRR90004014
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Engine Midlife complete | 2029-01-19 | 2029-01-21 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000361828 | 19.01.2029 | 17500 | CLB-MP-HAUL-DT5474-ENGINE | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Repl Cyl Steering RH | 2029-01-20 | 2029-01-20 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035062 | 20.01.2029 | 15000 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYR | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Wheel RH | 2029-01-20 | 2029-01-21 | 33 hrs | FY29 | 61 | 90003105 | 2 | 1000035588 | 20.01.2029 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-AXLES-HUBRH | 7500 | 90698 | 3515 | CLB-MP-HAUL-DT190 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Cyl Suspension RHF | 2029-01-20 | 2029-01-21 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067868 | 20.01.2029 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYRF | 7500 | 90698 | 3515 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Cyl Hoist LH | 2029-01-20 | 2029-01-21 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034347 | 20.01.2029 | 28000 | CLB-MP-HAUL-DT167 -HYDSYS-HOCYL-HCYLL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Cyl Hoist RH | 2029-01-20 | 2029-01-21 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034348 | 20.01.2029 | 28000 | CLB-MP-HAUL-DT167 -HYDSYS-HOCYL-HCYLR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Engine Midlife complete | 2029-01-21 | 2029-01-23 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000381298 | 21.01.2029 | 17500 | CLB-MP-HAUL-DT5504-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Engine Midlife complete | 2029-01-21 | 2029-01-23 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000381250 | 21.01.2029 | 17500 | CLB-MP-HAUL-DT5503-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-ENGINE90029500
793C | Onsite PM | Haul | Fortescue | LL0002 | LL0002 Pump Brake Cooling LH | 2029-01-25 | 2029-01-25 | 6 hrs | FY29 | 6 | 90013223 | A1 | 1000110285 | 25.01.2029 | 11000 | CLB-MP-SUPP-LL0002-BRKSYS-PBCLH | 3500 | 91736 | 17126 | CLB-MP-SUPP-LL0002-BRKSYS-PBCLH90013223
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Pump Drive Driveshaft Unis | 2029-01-26 | 2029-01-26 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035506 | 26.01.2029 | 11000 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR-DRSHT | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl AOC Fan Motor | 2029-01-26 | 2029-01-26 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035513 | 26.01.2029 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-MTFAN | 7500 | 84546 | 3414 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Pump Brake Control | 2029-01-26 | 2029-01-26 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035518 | 26.01.2029 | 11000 | CLB-MP-HAUL-DT189 -BRKSYS-HYFPP | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Brake Relay Valve | 2029-01-26 | 2029-01-26 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000079680 | 26.01.2029 | 11000 | CLB-MP-HAUL-DT189 -BRKSYS-BRVRL | 7500 | 84546 | 3391 | CLB-MP-HAUL-DT189 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Hyd Pump Steering Main | 2029-01-27 | 2029-01-27 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035003 | 27.01.2029 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STPMP | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Steering HMU | 2029-01-27 | 2029-01-27 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000035004 | 27.01.2029 | 15000 | CLB-MP-HAUL-DT179 -STRSYS-STHMU | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Steering Link & Arm Rebush | 2029-01-27 | 2029-01-28 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385431 | 27.01.2029 | 30000 | CLB-MP-HAUL-DT179 -STRSYS-STLTR | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 1Y Air Tank LH External Inspect | 2029-01-27 | 2029-01-27 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389326 | 27.01.2029 | 12 Monthly | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH | 7500 | 83047 | 18464 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 1Y Air Tank RH External Inspect | 2029-01-27 | 2029-01-27 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389328 | 27.01.2029 | 12 Monthly | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH | 7500 | 83047 | 18464 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Wheel Assembly LHF | 2029-01-28 | 2029-01-29 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000347022 | 28.01.2029 | 24000 | CLB-MP-HAUL-DT5445-STRUCT-AXLES-HUBLH | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Repl Wheel Assembly RHF | 2029-01-28 | 2029-01-29 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000347023 | 28.01.2029 | 24000 | CLB-MP-HAUL-DT5445-STRUCT-AXLES-HUBRH | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Tyre Sense Battery | 2029-01-28 | 2029-01-28 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163954 | 28.01.2029 | 24 Monthly | CLB-MP-HAUL-DT179 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT179 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Tyre Sense Battery | 2029-01-28 | 2029-01-28 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163939 | 28.01.2029 | 24 Monthly | CLB-MP-HAUL-DT164 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT164 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Wheel Assembly LHF | 2029-01-29 | 2029-01-30 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000350459 | 29.01.2029 | 24000 | CLB-MP-HAUL-DT5455-STRUCT-AXLES-HUBLH | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Repl Wheel Assembly RHF | 2029-01-29 | 2029-01-30 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000350460 | 29.01.2029 | 24000 | CLB-MP-HAUL-DT5455-STRUCT-AXLES-HUBRH | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 1Y Air Tank LH External Inspect | 2029-01-29 | 2029-01-29 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389390 | 29.01.2029 | 12 Monthly | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH | 7500 | 83208 | 83208 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 1Y Air Tank RH External Inspect | 2029-01-29 | 2029-01-29 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389392 | 29.01.2029 | 12 Monthly | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH | 7500 | 83208 | 83208 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Pump Brake Control | 2029-01-29 | 2029-01-29 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034725 | 29.01.2029 | 11000 | CLB-MP-HAUL-DT174 -BRKSYS-HYFPP | 7500 | 83749 | 14831 | CLB-MP-HAUL-DT174 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Ovhl Axle A Frame | 2029-01-30 | 2029-01-31 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130662 | 30.01.2029 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-AFRME | 7500 | 91174 | 25241 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Ovhl Axle Housing Dogbone | 2029-01-30 | 2029-01-31 | 22 hrs | FY29 | 42 | 90003118 | 1 | 1000035720 | 30.01.2029 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-TAGLK | 7500 | 91174 | 20531 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Hyd Motor Axle Lube Rear | 2029-01-30 | 2029-01-30 | 9 hrs | FY29 | 9 | 90003101 | 1 | 1000035758 | 30.01.2029 | 22000 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-HYM01 | 7500 | 83140 | 3268 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Repl Tyre Sense Battery | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163950 | 30.01.2029 | 24 Monthly | CLB-MP-HAUL-DT175 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT175 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Tyre Sense Battery | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163961 | 30.01.2029 | 24 Monthly | CLB-MP-HAUL-DT186 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT186 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Blower Main Assembly | 2029-01-30 | 2029-01-30 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000326667 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-ELCTHV-HVBLW | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Motor Grid Box Blower | 2029-01-30 | 2029-01-30 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000326663 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-ELCTHV-HVGBM | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Cylinder Hoist LHS | 2029-01-30 | 2029-01-30 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000326648 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-HYDSYS-HOCYL-HCYLH | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Cylinder Hoist RHS | 2029-01-30 | 2029-01-31 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000326649 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-HYDSYS-HOCYL-HCYRH | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Hoist Manifold | 2029-01-30 | 2029-01-31 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000326665 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-HYDSYS-HOMAN | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Accumulator Pump Control | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000326597 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-HYDSYS-HDACC-PCACC | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Seat Operator | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000326669 | 30.01.2029 | 14000 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-SEATS | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Cylinder Suspension LHF | 2029-01-30 | 2029-02-01 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000326652 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-STRUCT-SUSPN-SCYLF | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Accumulator Brake Front DS | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370081 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC01 | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Accumulator Brake Front ODS | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370082 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC02 | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Accumulator Brake Rear DS | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370083 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC03 | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Accumulator Brake Rear ODS | 2029-01-30 | 2029-01-30 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370084 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC04 | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Accumulator Steering DS | 2029-01-30 | 2029-01-30 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370085 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-STRSYS-STACC-SACLH | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Accumulator Steering ODS | 2029-01-30 | 2029-01-30 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370086 | 30.01.2029 | 28000 | CLB-MP-HAUL-DT5419-STRSYS-STACC-SACRH | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-STRSYS-STACC-SACRH90029372
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Service Air Conditioner 12M | 2029-02-01 | 2029-02-01 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000300050 | 01.02.2029 | 12 Monthly | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Service Air Conditioner | 2029-02-01 | 2029-02-01 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160383 | 01.02.2029 | 5500 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-AIRCN | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Air Dryer | 2029-02-01 | 2029-02-01 | 7 hrs | FY29 | 14 | 90003115 | 1 | 1000116273 | 01.02.2029 | 22000 | CLB-MP-HAUL-DT174 -PNEUMC-AIRDR | 7500 | 83749 | 28501 | CLB-MP-HAUL-DT174 -PNEUMC-AIRDR90003115
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Engine Midlife complete | 2029-02-02 | 2029-02-04 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000371788 | 02.02.2029 | 17500 | CLB-MP-HAUL-DT5487-ENGINE | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Motor Grid Box Blower | 2029-02-03 | 2029-02-03 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000314072 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-ELCTHV-HVGBM | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Accumulator Pump Control | 2029-02-03 | 2029-02-03 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000314102 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-HYDSYS-HDACC-PCACC | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Hoist Manifold | 2029-02-03 | 2029-02-04 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000314080 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-HYDSYS-HOMAN | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Hoist LHS | 2029-02-03 | 2029-02-03 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000314062 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-HYDSYS-HOCYL-HCYLH | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Hoist RHS | 2029-02-03 | 2029-02-04 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000314079 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-HYDSYS-HOCYL-HCYRH | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Seat Operator | 2029-02-03 | 2029-02-03 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000314065 | 03.02.2029 | 14000 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-SEATS | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Suspension LHF | 2029-02-03 | 2029-02-05 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000314090 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYLF | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Cylinder Suspension RHF | 2029-02-03 | 2029-02-05 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000314091 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYRF | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Accumulator Brake Front DS | 2029-02-03 | 2029-02-03 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370045 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC01 | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Accumulator Brake Front ODS | 2029-02-03 | 2029-02-03 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370046 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC02 | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Accumulator Brake Rear DS | 2029-02-03 | 2029-02-03 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370047 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC03 | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Accumulator Brake Rear ODS | 2029-02-03 | 2029-02-03 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370048 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC04 | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Accumulator Steering DS | 2029-02-03 | 2029-02-03 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370049 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-STRSYS-STACC-SACLH | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Accumulator Steering ODS | 2029-02-03 | 2029-02-03 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370050 | 03.02.2029 | 28000 | CLB-MP-HAUL-DT5405-STRSYS-STACC-SACRH | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRSYS-STACC-SACRH90029372
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Engine Midlife complete | 2029-02-03 | 2029-02-05 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000357110 | 03.02.2029 | 17500 | CLB-MP-HAUL-DT5466-ENGINE | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5445 | DT5445 Overhaul Air Conditioner 24M | 2029-02-03 | 2029-02-05 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000346990 | 03.02.2029 | 24 Monthly | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN | 6500 | 7612 | 7612 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Brake Wheel LH | 2029-02-03 | 2029-02-04 | 32 hrs | FY29 | 38 | 90003104 | 2 | 1000035703 | 03.02.2029 | 22000 | CLB-MP-HAUL-DT192 -STRUCT-AXLES-HUBLH | 7500 | 91174 | 3163 | CLB-MP-HAUL-DT192 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl AOC Fan Motor | 2029-02-03 | 2029-02-03 | 5 hrs | FY29 | 5 | 90003102 | 1 | 1000035643 | 03.02.2029 | 22000 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-MTFAN | 7500 | 87047 | 3203 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-MTFAN90003102
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Brake Relay Valve | 2029-02-03 | 2029-02-03 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078781 | 03.02.2029 | 11000 | CLB-MP-HAUL-DT191 -BRKSYS-BRVRL | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Transmission | 2029-02-04 | 2029-02-05 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000034877 | 04.02.2029 | 22000 | CLB-MP-HAUL-DT177 -TRNSYS-TRANS | 7500 | 81791 | 3161 | CLB-MP-HAUL-DT177 -TRNSYS-TRANS90003093
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Engine Midlife complete | 2029-02-05 | 2029-02-07 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000372437 | 05.02.2029 | 17500 | CLB-MP-HAUL-DT5488-ENGINE | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Brake & Steering Manifold | 2029-02-05 | 2029-02-05 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000360963 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-BRKSYS-BRVLV | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Gear Cooler Motor & Pump | 2029-02-05 | 2029-02-05 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000360982 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-FDRSYS-GRSOC-OCPPM | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Pump Airconditioner Drive | 2029-02-05 | 2029-02-05 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000360962 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-ACPMP | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Coupling Drive Pump | 2029-02-05 | 2029-02-05 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000360967 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-HYDPC | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Pump Main Hydraulic | 2029-02-05 | 2029-02-05 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000360990 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-HYPMP | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Cylinder Steering LHS | 2029-02-05 | 2029-02-05 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000360970 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-STRSYS-STRCY-STCYL | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Cylinder Steering RHS | 2029-02-05 | 2029-02-05 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000360971 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-STRSYS-STRCY-STCYR | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5469 | DT5469 Repl Valve Flow Amplifier | 2029-02-05 | 2029-02-05 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000360981 | 05.02.2029 | 20000 | CLB-MP-HAUL-DT5469-STRSYS-STVLV | 6500 | 3686 | 3686 | CLB-MP-HAUL-DT5469-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Pump Brake Control | 2029-02-05 | 2029-02-05 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035648 | 05.02.2029 | 11000 | CLB-MP-HAUL-DT191 -BRKSYS-HYFPP | 7500 | 87047 | 3166 | CLB-MP-HAUL-DT191 -BRKSYS-HYFPP90003106
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Brake & Steering Manifold | 2029-02-06 | 2029-02-06 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000361136 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-BRKSYS-BRVLV | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Gear Cooler Motor & Pump | 2029-02-06 | 2029-02-06 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000361175 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-FDRSYS-GRSOC-OCPPM | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Pump Airconditioner Drive | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000361135 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-ACPMP | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Coupling Drive Pump | 2029-02-06 | 2029-02-06 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000361160 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-HYDPC | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Pump Main Hydraulic | 2029-02-06 | 2029-02-06 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000361183 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-HYPMP | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Cylinder Steering LHS | 2029-02-06 | 2029-02-06 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000361163 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-STRSYS-STRCY-STCYL | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Cylinder Steering RHS | 2029-02-06 | 2029-02-06 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000361164 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-STRSYS-STRCY-STCYR | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5470 | DT5470 Repl Valve Flow Amplifier | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000361174 | 06.02.2029 | 20000 | CLB-MP-HAUL-DT5470-STRSYS-STVLV | 6500 | 3597 | 3597 | CLB-MP-HAUL-DT5470-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Blower Main Assembly | 2029-02-06 | 2029-02-06 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000326412 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-ELCTHV-HVBLW | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Motor Grid Box Blower | 2029-02-06 | 2029-02-06 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000326408 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-ELCTHV-HVGBM | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Hoist Manifold | 2029-02-06 | 2029-02-07 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000326410 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-HYDSYS-HOMAN | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Accumulator Pump Control | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000326382 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-HYDSYS-HDACC-PCACC | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Seat Operator | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000326414 | 06.02.2029 | 14000 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-SEATS | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Cylinder Suspension LHR | 2029-02-06 | 2029-02-07 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000326398 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYLR | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Cylinder Suspension RHF | 2029-02-06 | 2029-02-08 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000326399 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYRF | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Cylinder Suspension RHR | 2029-02-06 | 2029-02-07 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000326400 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYRR | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Accumulator Brake Front DS | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370069 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC01 | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Accumulator Brake Front ODS | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370070 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC02 | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Accumulator Brake Rear DS | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370071 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC03 | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Accumulator Brake Rear ODS | 2029-02-06 | 2029-02-06 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370072 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC04 | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Accumulator Steering DS | 2029-02-06 | 2029-02-06 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370073 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-STRSYS-STACC-SACLH | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Accumulator Steering ODS | 2029-02-06 | 2029-02-06 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370074 | 06.02.2029 | 28000 | CLB-MP-HAUL-DT5417-STRSYS-STACC-SACRH | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-STRSYS-STACC-SACRH90029372
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Midlife Valve Set - Adjust | 2029-02-07 | 2029-02-07 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390980 | 07.02.2029 | 11000 | CLB-MP-HAUL-DT196 -ENGINE | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Engine Midlife complete | 2029-02-07 | 2029-02-11 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000157003 | 07.02.2029 | 11000 | CLB-MP-HAUL-DT196 -ENGINE | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Service Suspension Cylinders | 2029-02-07 | 2029-02-07 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106945 | 07.02.2029 | 11000 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN | 7500 | 85161 | 14133 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Tyre Sense Battery | 2029-02-08 | 2029-02-08 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163967 | 08.02.2029 | 24 Monthly | CLB-MP-HAUL-DT192 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT192 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Steering Ball Studs | 2029-02-08 | 2029-02-09 | 19 hrs | FY29 | 35 | 90038356 | A1 | 1000385444 | 08.02.2029 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STLTR | 7500 | 89749 | 26124 | CLB-MP-HAUL-DT186 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Steering Link & Arm Rebush | 2029-02-09 | 2029-02-10 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385475 | 09.02.2029 | 30000 | CLB-MP-HAUL-DT224 -STRSYS-STLTR | 7500 | 49737 | 11104 | CLB-MP-HAUL-DT224 -STRSYS-STLTR90038355
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Brake & Steering Manifold | 2029-02-10 | 2029-02-10 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000357140 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-BRKSYS-BRVLV | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Gear Cooler Motor & Pump | 2029-02-10 | 2029-02-10 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000357159 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-FDRSYS-GRSOC-OCPPM | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Pump Airconditioner Drive | 2029-02-10 | 2029-02-10 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000357139 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-ACPMP | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Coupling Drive Pump | 2029-02-10 | 2029-02-10 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000357144 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-HYDPC | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Pump Main Hydraulic | 2029-02-10 | 2029-02-10 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000357167 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-HYPMP | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Cylinder Steering LHS | 2029-02-10 | 2029-02-10 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000357147 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-STRSYS-STRCY-STCYL | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Cylinder Steering RHS | 2029-02-10 | 2029-02-10 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000357148 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-STRSYS-STRCY-STCYR | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5467 | DT5467 Repl Valve Flow Amplifier | 2029-02-10 | 2029-02-10 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000357158 | 10.02.2029 | 20000 | CLB-MP-HAUL-DT5467-STRSYS-STVLV | 6500 | 3380 | 3380 | CLB-MP-HAUL-DT5467-STRSYS-STVLV90029367
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Float Brake Control Valve - Cabin | 2029-02-10 | 2029-02-10 | 3 hrs | FY29 | 3 | 90018289 | 1 | 1000174671 | 10.02.2029 | 10000 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-FLBCV | 4200 | 53807 | 9242 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-FLBCV90018289
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Brake & Steering Manifold | 2029-02-11 | 2029-02-11 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000360813 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-BRKSYS-BRVLV | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Gear Cooler Motor & Pump | 2029-02-11 | 2029-02-11 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000360832 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-FDRSYS-GRSOC-OCPPM | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Pump Airconditioner Drive | 2029-02-11 | 2029-02-11 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000360812 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-ACPMP | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Coupling Drive Pump | 2029-02-11 | 2029-02-11 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000360817 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-HYDPC | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Pump Main Hydraulic | 2029-02-11 | 2029-02-11 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000360840 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-HYPMP | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Cylinder Steering LHS | 2029-02-11 | 2029-02-11 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000360820 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-STRSYS-STRCY-STCYL | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Cylinder Steering RHS | 2029-02-11 | 2029-02-11 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000360821 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-STRSYS-STRCY-STCYR | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5468 | DT5468 Repl Valve Flow Amplifier | 2029-02-11 | 2029-02-11 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000360831 | 11.02.2029 | 20000 | CLB-MP-HAUL-DT5468-STRSYS-STVLV | 6500 | 3720 | 3720 | CLB-MP-HAUL-DT5468-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Brake Slack Adjuster Front | 2029-02-11 | 2029-02-11 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072236 | 11.02.2029 | 18000 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACF | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Brake Slack Adjuster Rear | 2029-02-11 | 2029-02-11 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072274 | 11.02.2029 | 18000 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACR | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Cyl Hoist LH | 2029-02-12 | 2029-02-13 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034071 | 12.02.2029 | 28000 | CLB-MP-HAUL-DT184 -HYDSYS-HOCYL-HCYLL | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Cyl Hoist RH | 2029-02-12 | 2029-02-13 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034072 | 12.02.2029 | 28000 | CLB-MP-HAUL-DT184 -HYDSYS-HOCYL-HCYLR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Tyre Sense Battery | 2029-02-13 | 2029-02-13 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163952 | 13.02.2029 | 24 Monthly | CLB-MP-HAUL-DT177 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT177 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Slack Adjuster Front | 2029-02-14 | 2029-02-14 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000150699 | 14.02.2029 | 18000 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACF | 7500 | 51346 | 16991 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Slack Adjuster Rear | 2029-02-14 | 2029-02-14 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000150700 | 14.02.2029 | 18000 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACR | 7500 | 51346 | 16991 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Tyre Sense Battery | 2029-02-14 | 2029-02-14 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163959 | 14.02.2029 | 24 Monthly | CLB-MP-HAUL-DT184 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT184 -MANGMT-TYRSN90017022
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 250Hr Initial Valve Set | 2029-02-14 | 2029-02-14 | 8 hrs | FY29 | 16 | 90029174 | A1 | 1000290839 | 14.02.2029 | 250 | CLB-MP-SUPP-PM0004-ENGINE | 3500 | 91736 | 13390 | CLB-MP-SUPP-PM0004-ENGINE90029174
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Transmission | 2029-02-15 | 2029-02-16 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000035809 | 15.02.2029 | 22000 | CLB-MP-HAUL-DT194 -TRNSYS-TRANS | 7500 | 86451 | 2801 | CLB-MP-HAUL-DT194 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Midlife Valve Set - Adjust | 2029-02-15 | 2029-02-15 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390940 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -ENGINE | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Engine Midlife complete | 2029-02-15 | 2029-02-19 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156683 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -ENGINE | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Drive Driveshaft Unis | 2029-02-15 | 2029-02-15 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000034823 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR-DRSHT | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Brake Control | 2029-02-15 | 2029-02-15 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034835 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP | 7500 | 85284 | 6894 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Service Suspension Cylinders | 2029-02-15 | 2029-02-15 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106885 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Brake Relay Valve | 2029-02-15 | 2029-02-15 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000079623 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Spiders Transmission Driveshaft | 2029-02-15 | 2029-02-15 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154394 | 15.02.2029 | 11000 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT-UNVSL | 7500 | 85284 | 13976 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Steering Link & Arm Rebush | 2029-02-15 | 2029-02-16 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385449 | 15.02.2029 | 30000 | CLB-MP-HAUL-DT188 -STRSYS-STLTR | 7500 | 83931 | 10994 | CLB-MP-HAUL-DT188 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Transmission | 2029-02-15 | 2029-02-16 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000034160 | 15.02.2029 | 22000 | CLB-MP-HAUL-DT164 -TRNSYS-TRANS | 7500 | 81875 | 2963 | CLB-MP-HAUL-DT164 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Tyre Sense Battery | 2029-02-15 | 2029-02-15 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163968 | 15.02.2029 | 24 Monthly | CLB-MP-HAUL-DT193 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT193 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 1Y Air Tank LH External Inspect | 2029-02-15 | 2029-02-15 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389354 | 15.02.2029 | 12 Monthly | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH | 7500 | 83507 | 83507 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 1Y Air Tank RH External Inspect | 2029-02-15 | 2029-02-15 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389356 | 15.02.2029 | 12 Monthly | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH | 7500 | 83507 | 83507 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH90038753
777G | Onsite PM | Haul | Fortescue | SV4105 | SV4105 Replace Brake Oil Cooler | 2029-02-16 | 2029-02-16 | 6 hrs | FY29 | 6 | 90011549 | A1 | 1000214379 | 16.02.2029 | 15000 | CLB-MP-SUPP-SV4105-BRKSYS-BROCO | 2500 | 8917 | 8917 | CLB-MP-SUPP-SV4105-BRKSYS-BROCO90011549
T264 | Onsite PM | Haul | Fortescue | DT5476 | DT5476 Repl Engine Midlife complete | 2029-02-17 | 2029-02-19 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000365030 | 17.02.2029 | 17500 | CLB-MP-HAUL-DT5476-ENGINE | 6500 | 920 | 920 | CLB-MP-HAUL-DT5476-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Cyl Hoist LH | 2029-02-17 | 2029-02-18 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000035599 | 17.02.2029 | 28000 | CLB-MP-HAUL-DT190 -HYDSYS-HOCYL-HCYLL | 7500 | 90698 | 8940 | CLB-MP-HAUL-DT190 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Final Drive LH | 2029-02-17 | 2029-02-18 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000035103 | 17.02.2029 | 22000 | CLB-MP-HAUL-DT181 -FDRSYS-FDRVE-FDRLH | 7500 | 83441 | 2972 | CLB-MP-HAUL-DT181 -FDRSYS-FDRVE-FDRLH90003099
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Motor Grid Box Blower | 2029-02-18 | 2029-02-18 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000300352 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-ELCTHV-HVGBM | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Blower Main Assembly | 2029-02-18 | 2029-02-18 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000300354 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-ELCTHV-HVBLW | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Accumulator Pump Control | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000303969 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-HYDSYS-HDACC-PCACC | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Hoist Manifold | 2029-02-18 | 2029-02-19 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000300360 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-HYDSYS-HOMAN | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Hoist LHS | 2029-02-18 | 2029-02-18 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000300342 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-HYDSYS-HOCYL-HCYLH | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Hoist RHS | 2029-02-18 | 2029-02-19 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000300359 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-HYDSYS-HOCYL-HCYRH | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Seat Operator | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000300345 | 18.02.2029 | 14000 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-SEATS | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Suspension LHF | 2029-02-18 | 2029-02-20 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000300370 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYLF | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Suspension RHF | 2029-02-18 | 2029-02-20 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000300371 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYRF | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Cylinder Suspension RHR | 2029-02-18 | 2029-02-19 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000300373 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYRR | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Accumulator Brake Front DS | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000369973 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC01 | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Accumulator Brake Front ODS | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000369974 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC02 | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Accumulator Brake Rear DS | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000369975 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC03 | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Accumulator Brake Rear ODS | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000369976 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC04 | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Accumulator Steering DS | 2029-02-18 | 2029-02-18 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000369977 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-STRSYS-STACC-SACLH | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Accumulator Steering ODS | 2029-02-18 | 2029-02-18 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000369978 | 18.02.2029 | 28000 | CLB-MP-HAUL-DT5391-STRSYS-STACC-SACRH | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-STRSYS-STACC-SACRH90029372
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Tyre Sense Battery | 2029-02-18 | 2029-02-18 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163963 | 18.02.2029 | 24 Monthly | CLB-MP-HAUL-DT188 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT188 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Inspect Water Cannon | 2029-02-19 | 2029-02-19 | 3 hrs | FY29 | 3 | 90033661 | A1 | 1000339268 | 19.02.2029 | 6 Monthly | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | 5000 | 17738 | 8813 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT180 | DT180 Service Suspension Cylinders | 2029-02-19 | 2029-02-19 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106889 | 19.02.2029 | 11000 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN | 7500 | 89560 | 11534 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN90012840
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Wheel Assembly LHF | 2029-02-20 | 2029-02-21 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000349674 | 20.02.2029 | 24000 | CLB-MP-HAUL-DT5450-STRUCT-AXLES-HUBLH | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Repl Wheel Assembly RHF | 2029-02-20 | 2029-02-21 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000349675 | 20.02.2029 | 24000 | CLB-MP-HAUL-DT5450-STRUCT-AXLES-HUBRH | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Tyre Sense Battery | 2029-02-20 | 2029-02-20 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163964 | 20.02.2029 | 24 Monthly | CLB-MP-HAUL-DT189 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT189 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Service Suspension Cylinders | 2029-02-21 | 2029-02-21 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106888 | 21.02.2029 | 11000 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN | 7500 | 84079 | 11363 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 1Y Air Tank LH External Inspect | 2029-02-21 | 2029-02-21 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389398 | 21.02.2029 | 12 Monthly | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH | 7500 | 89493 | 42523 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 1Y Air Tank RH External Inspect | 2029-02-21 | 2029-02-21 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389400 | 21.02.2029 | 12 Monthly | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH | 7500 | 89493 | 42523 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Blower Main Assembly | 2029-02-21 | 2029-02-21 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000326583 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-ELCTHV-HVBLW | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Motor Grid Box Blower | 2029-02-21 | 2029-02-21 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000326579 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-ELCTHV-HVGBM | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Hoist LHS | 2029-02-21 | 2029-02-21 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000326564 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-HYDSYS-HOCYL-HCYLH | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Hoist RHS | 2029-02-21 | 2029-02-22 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000326565 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-HYDSYS-HOCYL-HCYRH | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Hoist Manifold | 2029-02-21 | 2029-02-22 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000326581 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-HYDSYS-HOMAN | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Accumulator Pump Control | 2029-02-21 | 2029-02-21 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000326473 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-HYDSYS-HDACC-PCACC | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Seat Operator | 2029-02-21 | 2029-02-21 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000326585 | 21.02.2029 | 14000 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-SEATS | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Suspension LHF | 2029-02-21 | 2029-02-23 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000326568 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYLF | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Suspension LHR | 2029-02-21 | 2029-02-22 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000326569 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYLR | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Suspension RHF | 2029-02-21 | 2029-02-23 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000326570 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYRF | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Suspension RHR | 2029-02-21 | 2029-02-22 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000326571 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYRR | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Accumulator Brake Front DS | 2029-02-21 | 2029-02-21 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370075 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC01 | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Accumulator Brake Front ODS | 2029-02-21 | 2029-02-21 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370076 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC02 | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Accumulator Brake Rear DS | 2029-02-21 | 2029-02-21 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370077 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC03 | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Accumulator Brake Rear ODS | 2029-02-21 | 2029-02-21 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370078 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC04 | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Accumulator Steering DS | 2029-02-21 | 2029-02-21 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370079 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-STRSYS-STACC-SACLH | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Accumulator Steering ODS | 2029-02-21 | 2029-02-21 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370080 | 21.02.2029 | 28000 | CLB-MP-HAUL-DT5418-STRSYS-STACC-SACRH | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-STRSYS-STACC-SACRH90029372
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Service Air Conditioner 12M | 2029-02-22 | 2029-02-22 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000314066 | 22.02.2029 | 12 Monthly | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Service Air Conditioner | 2029-02-23 | 2029-02-23 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160370 | 23.02.2029 | 5500 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-AIRCN | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Cyl Hoist LH | 2029-02-25 | 2029-02-26 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034899 | 25.02.2029 | 28000 | CLB-MP-HAUL-DT177 -HYDSYS-HOCYL-HCYLL | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Cyl Hoist RH | 2029-02-25 | 2029-02-26 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034900 | 25.02.2029 | 28000 | CLB-MP-HAUL-DT177 -HYDSYS-HOCYL-HCYLR | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -HYDSYS-HOCYL-HCYLR90003114
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Service Air Conditioner 12M | 2029-02-26 | 2029-02-26 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000300346 | 26.02.2029 | 12 Monthly | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN | 6500 | 11246 | 4814 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Blower Main Assembly | 2029-02-26 | 2029-02-26 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000326270 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-ELCTHV-HVBLW | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Motor Grid Box Blower | 2029-02-26 | 2029-02-26 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000326266 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-ELCTHV-HVGBM | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Cylinder Hoist LHS | 2029-02-26 | 2029-02-26 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000326251 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-HYDSYS-HOCYL-HCYLH | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Cylinder Hoist RHS | 2029-02-26 | 2029-02-27 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000326252 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-HYDSYS-HOCYL-HCYRH | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Hoist Manifold | 2029-02-26 | 2029-02-27 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000326268 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-HYDSYS-HOMAN | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Accumulator Pump Control | 2029-02-26 | 2029-02-26 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000326240 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-HYDSYS-HDACC-PCACC | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Cylinder Suspension LHR | 2029-02-26 | 2029-02-27 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000326256 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYLR | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Cylinder Suspension RHR | 2029-02-26 | 2029-02-27 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000326258 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYRR | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Accumulator Brake Front DS | 2029-02-26 | 2029-02-26 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370063 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC01 | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Accumulator Brake Front ODS | 2029-02-26 | 2029-02-26 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370064 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC02 | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Accumulator Brake Rear DS | 2029-02-26 | 2029-02-26 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370065 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC03 | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Accumulator Brake Rear ODS | 2029-02-26 | 2029-02-26 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370066 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC04 | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Accumulator Steering DS | 2029-02-26 | 2029-02-26 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370067 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-STRSYS-STACC-SACLH | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Accumulator Steering ODS | 2029-02-26 | 2029-02-26 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370068 | 26.02.2029 | 28000 | CLB-MP-HAUL-DT5416-STRSYS-STACC-SACRH | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-STRSYS-STACC-SACRH90029372
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Motor Grid Box Blower | 2029-02-27 | 2029-02-27 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000314342 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-ELCTHV-HVGBM | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Blower Main Assembly | 2029-02-27 | 2029-02-27 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000314344 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-ELCTHV-HVBLW | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Accumulator Pump Control | 2029-02-27 | 2029-02-27 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000314372 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-HYDSYS-HDACC-PCACC | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Hoist Manifold | 2029-02-27 | 2029-02-28 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000314350 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-HYDSYS-HOMAN | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Hoist LHS | 2029-02-27 | 2029-02-27 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000314212 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-HYDSYS-HOCYL-HCYLH | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Hoist RHS | 2029-02-27 | 2029-02-28 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000314349 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-HYDSYS-HOCYL-HCYRH | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Suspension LHF | 2029-02-27 | 2029-03-01 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000314360 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYLF | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Suspension RHF | 2029-02-27 | 2029-03-01 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000314361 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYRF | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Suspension LHR | 2029-02-27 | 2029-02-28 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000314362 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYLR | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Cylinder Suspension RHR | 2029-02-27 | 2029-02-28 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000314363 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYRR | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Accumulator Brake Front DS | 2029-02-27 | 2029-02-27 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370051 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC01 | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Accumulator Brake Front ODS | 2029-02-27 | 2029-02-27 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370052 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC02 | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Accumulator Brake Rear DS | 2029-02-27 | 2029-02-27 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370053 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC03 | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Accumulator Brake Rear ODS | 2029-02-27 | 2029-02-27 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370054 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC04 | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Accumulator Steering DS | 2029-02-27 | 2029-02-27 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370055 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-STRSYS-STACC-SACLH | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Accumulator Steering ODS | 2029-02-27 | 2029-02-27 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370056 | 27.02.2029 | 28000 | CLB-MP-HAUL-DT5410-STRSYS-STACC-SACRH | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRSYS-STACC-SACRH90029372
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 5000Hr Valve Set | 2029-02-27 | 2029-02-27 | 12 hrs | FY29 | 24 | 90028725 | A1 | 1000289416 | 27.02.2029 | 5000 | CLB-MP-SUPP-WC011 -ENGINE | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl PTO Uni's | 2029-02-27 | 2029-02-27 | 4 hrs | FY29 | 4 | 90031093 | A1 | 1000307800 | 27.02.2029 | 5000 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT90031093
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Steering Cylinder LH | 2029-02-27 | 2029-02-27 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000044539 | 27.02.2029 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STRCY-STCYL | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Steering Accumulator RH | 2029-02-27 | 2029-02-27 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000044544 | 27.02.2029 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STACC-SACRH | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Repl Steering Link & Arm Rebush | 2029-02-27 | 2029-02-27 | 14 hrs | FY29 | 22 | 90004007 | 1 | 1000044541 | 27.02.2029 | 15000 | CLB-MP-SUPP-WC011 -STRSYS-STLTR | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRSYS-STLTR90004007
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Service Airconditioner | 2029-02-27 | 2029-02-27 | 12 hrs | FY29 | 12 | 90028728 | A1 | 1000289413 | 27.02.2029 | 5000 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN | 5000 | 64118 | 1755 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN90028728
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Repl PTO Uni's | 2029-02-27 | 2029-02-27 | 4 hrs | FY29 | 4 | 90031093 | A1 | 1000307803 | 27.02.2029 | 5000 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT | 5000 | 67273 | 11372 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT90031093
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Cyl Hoist LH | 2029-03-03 | 2029-03-04 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000035340 | 03.03.2029 | 28000 | CLB-MP-HAUL-DT186 -HYDSYS-HOCYL-HCYLL | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Brake Slack Adjuster Front | 2029-03-04 | 2029-03-04 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072255 | 04.03.2029 | 18000 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACF | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Brake Slack Adjuster Rear | 2029-03-04 | 2029-03-04 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072293 | 04.03.2029 | 18000 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACR | 7500 | 86259 | 16648 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Wheel RH | 2029-03-04 | 2029-03-05 | 33 hrs | FY29 | 61 | 90003105 | 2 | 1000035164 | 04.03.2029 | 22000 | CLB-MP-HAUL-DT182 -STRUCT-AXLES-HUBRH | 7500 | 92002 | 2590 | CLB-MP-HAUL-DT182 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Slack Adjuster Front | 2029-03-04 | 2029-03-04 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072256 | 04.03.2029 | 18000 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACF | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Brake Slack Adjuster Rear | 2029-03-04 | 2029-03-04 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072294 | 04.03.2029 | 18000 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACR | 7500 | 88680 | 16643 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5447 | DT5447 Overhaul Air Conditioner 24M | 2029-03-05 | 2029-03-07 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000347362 | 05.03.2029 | 24 Monthly | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN | 6500 | 8949 | 8949 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Overhaul Air Conditioner 24M | 2029-03-06 | 2029-03-08 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000349686 | 06.03.2029 | 24 Monthly | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5450 | DT5450 Overhaul Air Conditioner 24M | 2029-03-06 | 2029-03-08 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000349642 | 06.03.2029 | 24 Monthly | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN | 6500 | 7211 | 7211 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Repl Brake Wheel LH | 2029-03-06 | 2029-03-07 | 32 hrs | FY29 | 38 | 90003104 | 2 | 1000034612 | 06.03.2029 | 22000 | CLB-MP-HAUL-DT172 -STRUCT-AXLES-HUBLH | 7500 | 92351 | 2439 | CLB-MP-HAUL-DT172 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Cyl Hoist RH | 2029-03-08 | 2029-03-09 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000035472 | 08.03.2029 | 28000 | CLB-MP-HAUL-DT188 -HYDSYS-HOCYL-HCYLR | 7500 | 83931 | 7989 | CLB-MP-HAUL-DT188 -HYDSYS-HOCYL-HCYLR90003114
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Brake Accumulator | 2029-03-10 | 2029-03-10 | 4 hrs | FY29 | 4 | 90004001 | 1 | 1000221753 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-BRKSYS-BACCM | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-BRKSYS-BACCM90004001
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering Pump | 2029-03-10 | 2029-03-10 | 4 hrs | FY29 | 4 | 90004003 | 1 | 1000221755 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STPMP | 5000 | 17738 | 1992 | CLB-MP-SUPP-WC3108-STRSYS-STPMP90004003
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering Cylinder LH | 2029-03-10 | 2029-03-10 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000221757 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STRCY-STCYL | 5000 | 17738 | 1992 | CLB-MP-SUPP-WC3108-STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering Cylinder RH | 2029-03-10 | 2029-03-10 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000221758 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STRCY-STCYR | 5000 | 17738 | 1992 | CLB-MP-SUPP-WC3108-STRSYS-STRCY-STCYR90004005
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering Accumulator LH | 2029-03-10 | 2029-03-10 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000221761 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STACC-SACLH | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRSYS-STACC-SACLH90004022
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering Accumulator RH | 2029-03-10 | 2029-03-10 | 2 hrs | FY29 | 2 | 90004022 | 1 | 1000221762 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STACC-SACRH | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRSYS-STACC-SACRH90004022
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Replace Steering Oil Cooler | 2029-03-10 | 2029-03-10 | 5 hrs | FY29 | 5 | 90004006 | 1 | 1000221760 | 10.03.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STOLC | 5000 | 17738 | 1992 | CLB-MP-SUPP-WC3108-STRSYS-STOLC90004006
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Ovhl Axle A Frame | 2029-03-10 | 2029-03-11 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130669 | 10.03.2029 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-AFRME | 7500 | 85978 | 35622 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Ovhl Axle Housing Dogbone | 2029-03-10 | 2029-03-11 | 22 hrs | FY29 | 42 | 90003118 | 1 | 1000036133 | 10.03.2029 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-TAGLK | 7500 | 85978 | 24506 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Brake Wheel LH | 2029-03-10 | 2029-03-11 | 32 hrs | FY29 | 38 | 90003104 | 2 | 1000036116 | 10.03.2029 | 22000 | CLB-MP-HAUL-DT199 -STRUCT-AXLES-HUBLH | 7500 | 85978 | 2499 | CLB-MP-HAUL-DT199 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 1Y Air Tank LH External Inspect | 2029-03-11 | 2029-03-11 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389466 | 11.03.2029 | 12 Monthly | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH | 7500 | 91739 | 50479 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 1Y Air Tank RH External Inspect | 2029-03-11 | 2029-03-11 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389468 | 11.03.2029 | 12 Monthly | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH | 7500 | 91739 | 50479 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5477 | DT5477 Repl Engine Midlife complete | 2029-03-12 | 2029-03-14 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000365201 | 12.03.2029 | 17500 | CLB-MP-HAUL-DT5477-ENGINE | 6500 | 630 | 630 | CLB-MP-HAUL-DT5477-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Final Drive LH | 2029-03-12 | 2029-03-13 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000034662 | 12.03.2029 | 22000 | CLB-MP-HAUL-DT173 -FDRSYS-FDRVE-FDRLH | 7500 | 82651 | 714 | CLB-MP-HAUL-DT173 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Cyl Suspension LHR | 2029-03-13 | 2029-03-14 | 23 hrs | FY29 | 42 | 90003122 | 1 | 1000035667 | 13.03.2029 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYLR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYLR90003122
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Cyl Suspension RHF | 2029-03-14 | 2029-03-15 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067788 | 14.03.2029 | 22000 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYRF | 7500 | 91119 | 2276 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Hyd Pump Steering Main | 2029-03-14 | 2029-03-14 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034728 | 14.03.2029 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STPMP | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Steering HMU | 2029-03-14 | 2029-03-14 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000034729 | 14.03.2029 | 15000 | CLB-MP-HAUL-DT174 -STRSYS-STHMU | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Steering Link & Arm Rebush | 2029-03-14 | 2029-03-15 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385421 | 14.03.2029 | 30000 | CLB-MP-HAUL-DT174 -STRSYS-STLTR | 7500 | 83749 | 10427 | CLB-MP-HAUL-DT174 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 1Y Air Tank LH External Inspect | 2029-03-15 | 2029-03-15 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389314 | 15.03.2029 | 12 Monthly | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH | 7500 | 81612 | 11133 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 1Y Air Tank RH External Inspect | 2029-03-15 | 2029-03-15 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389316 | 15.03.2029 | 12 Monthly | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH | 7500 | 81612 | 11133 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Spiders Transmission Driveshaft | 2029-03-15 | 2029-03-15 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154428 | 15.03.2029 | 11000 | CLB-MP-HAUL-DT193 -FDRSYS-DRSHT-UNVSL | 7500 | 83140 | 1989 | CLB-MP-HAUL-DT193 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 1Y Air Tank LH External Inspect | 2029-03-16 | 2029-03-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389410 | 16.03.2029 | 12 Monthly | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH | 7500 | 84322 | 84322 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 1Y Air Tank RH External Inspect | 2029-03-16 | 2029-03-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389412 | 16.03.2029 | 12 Monthly | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH | 7500 | 84322 | 84322 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Pump Hoist & Brake | 2029-03-17 | 2029-03-17 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035830 | 17.03.2029 | 22000 | CLB-MP-HAUL-DT194 -HYDSYS-HOPMP | 7500 | 86451 | 2190 | CLB-MP-HAUL-DT194 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Hyd Pump Steering Main | 2029-03-17 | 2029-03-17 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035593 | 17.03.2029 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STPMP | 7500 | 90698 | 10366 | CLB-MP-HAUL-DT190 -STRSYS-STPMP90003109
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Water Cannon Inspect | 2029-03-17 | 2029-03-17 | 3 hrs | FY29 | 3 | 90033661 | A1 | 1000338792 | 17.03.2029 | 6 Monthly | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | 5000 | 63833 | 10034 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON90033661
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Brake & Steering Manifold | 2029-03-17 | 2029-03-17 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000339693 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-BRKSYS-BRVLV | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Gear Cooler Motor & Pump | 2029-03-17 | 2029-03-17 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000339712 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-FDRSYS-GRSOC-OCPPM | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Pump Airconditioner Drive | 2029-03-17 | 2029-03-17 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000339692 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-ACPMP | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Coupling Drive Pump | 2029-03-17 | 2029-03-17 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000339697 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-HYDPC | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Pump Main Hydraulic | 2029-03-17 | 2029-03-17 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000339720 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-HYPMP | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Cylinder Steering LHS | 2029-03-17 | 2029-03-17 | 8 hrs | FY29 | 14 | 90029373 | A1 | 1000339700 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-STRSYS-STRCY-STCYL | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Cylinder Steering RHS | 2029-03-17 | 2029-03-17 | 8 hrs | FY29 | 14 | 90029374 | A1 | 1000339701 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-STRSYS-STRCY-STCYR | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5440 | DT5440 Repl Valve Flow Amplifier | 2029-03-17 | 2029-03-17 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000339711 | 17.03.2029 | 20000 | CLB-MP-HAUL-DT5440-STRSYS-STVLV | 6500 | 1513 | 1513 | CLB-MP-HAUL-DT5440-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Cyl Hoist LH | 2029-03-18 | 2029-03-19 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034237 | 18.03.2029 | 28000 | CLB-MP-HAUL-DT165 -HYDSYS-HOCYL-HCYLL | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Cyl Hoist RH | 2029-03-18 | 2029-03-19 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034238 | 18.03.2029 | 28000 | CLB-MP-HAUL-DT165 -HYDSYS-HOCYL-HCYLR | 7500 | 78966 | 8345 | CLB-MP-HAUL-DT165 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Hoist LH | 2029-03-19 | 2029-03-20 | 25 hrs | FY29 | 49 | 90003114 | 1 | 1000034127 | 19.03.2029 | 28000 | CLB-MP-HAUL-DT163 -HYDSYS-HOCYL-HCYLL | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -HYDSYS-HOCYL-HCYLL90003114
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Cyl Hoist RH | 2029-03-19 | 2029-03-20 | 25 hrs | FY29 | 49 | 90003114 | 2 | 1000034128 | 19.03.2029 | 28000 | CLB-MP-HAUL-DT163 -HYDSYS-HOCYL-HCYLR | 7500 | 81237 | 8119 | CLB-MP-HAUL-DT163 -HYDSYS-HOCYL-HCYLR90003114
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Midlife Valve Set - Adjust | 2029-03-19 | 2029-03-19 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390957 | 19.03.2029 | 11000 | CLB-MP-HAUL-DT193 -ENGINE | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Engine Midlife complete | 2029-03-19 | 2029-03-23 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156955 | 19.03.2029 | 11000 | CLB-MP-HAUL-DT193 -ENGINE | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Pump Brake Control | 2029-03-19 | 2029-03-19 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035764 | 19.03.2029 | 11000 | CLB-MP-HAUL-DT193 -BRKSYS-HYFPP | 7500 | 83140 | 592 | CLB-MP-HAUL-DT193 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Service Suspension Cylinders | 2029-03-19 | 2029-03-19 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106942 | 19.03.2029 | 11000 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN | 7500 | 83140 | 13267 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Brake Relay Valve | 2029-03-19 | 2029-03-19 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000079699 | 19.03.2029 | 11000 | CLB-MP-HAUL-DT193 -BRKSYS-BRVRL | 7500 | 83140 | 13282 | CLB-MP-HAUL-DT193 -BRKSYS-BRVRL90009877
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Repl Sec Str Pump & Motor | 2029-03-20 | 2029-03-20 | 6 hrs | FY29 | 6 | 90003057 | A1 | 1000033998 | 20.03.2029 | 15000 | CLB-MP-SUPP-SV021 -STRSYS-STEMG-SESPP | 3300 | 54098 | 6110 | CLB-MP-SUPP-SV021 -STRSYS-STEMG-SESPP90003057
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Ovhl Axle A Frame | 2029-03-20 | 2029-03-21 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130661 | 20.03.2029 | 22000 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-AFRME | 7500 | 87047 | 40828 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Overhaul Accumulator Brake | 2029-03-21 | 2029-03-21 | 10 hrs | FY29 | 10 | 90009313 | 1 | 1000072216 | 21.03.2029 | 22000 | CLB-MP-HAUL-DT196 -BRKSYS-BACCM | 7500 | 85161 | 25254 | CLB-MP-HAUL-DT196 -BRKSYS-BACCM90009313
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Brake Relay Valve | 2029-03-21 | 2029-03-21 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000079718 | 21.03.2029 | 11000 | CLB-MP-HAUL-DT196 -BRKSYS-BRVRL | 7500 | 85161 | 14148 | CLB-MP-HAUL-DT196 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Pump Transmission | 2029-03-22 | 2029-03-22 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035927 | 22.03.2029 | 11000 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TMCPP | 7500 | 85161 | 2274 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Pump Brake Control | 2029-03-22 | 2029-03-22 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035938 | 22.03.2029 | 11000 | CLB-MP-HAUL-DT196 -BRKSYS-HYFPP | 7500 | 85161 | 2274 | CLB-MP-HAUL-DT196 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Tyre Sense Battery | 2029-03-22 | 2029-03-22 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163956 | 22.03.2029 | 24 Monthly | CLB-MP-HAUL-DT181 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT181 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT174 | DT174 Repl Tyre Sense Battery | 2029-03-22 | 2029-03-22 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163949 | 22.03.2029 | 24 Monthly | CLB-MP-HAUL-DT174 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT174 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5442 | DT5442 Overhaul Air Conditioner 24M | 2029-03-22 | 2029-03-24 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000346560 | 22.03.2029 | 24 Monthly | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN | 6500 | 8565 | 8565 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Service Air Conditioner 12M | 2029-03-25 | 2029-03-25 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000314216 | 25.03.2029 | 12 Monthly | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT163 | DT163 Repl Tyre Sense Battery | 2029-03-25 | 2029-03-25 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163938 | 25.03.2029 | 24 Monthly | CLB-MP-HAUL-DT163 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT163 -MANGMT-TYRSN90017022
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Air Drier and Tank | 2029-03-25 | 2029-03-25 | 12 hrs | FY29 | 24 | 90004010 | 1 | 1000082743 | 25.03.2029 | 9000 | CLB-MP-SUPP-PM0006-PNEUMC-AIRDR | 4200 | 53807 | 24746 | CLB-MP-SUPP-PM0006-PNEUMC-AIRDR90004010
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Tyre Sense Battery | 2029-03-27 | 2029-03-27 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163971 | 27.03.2029 | 24 Monthly | CLB-MP-HAUL-DT196 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT196 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Radiator Engine Cooling | 2029-03-27 | 2029-03-29 | 55 hrs | FY29 | 85 | 90003081 | 1 | 1000036037 | 27.03.2029 | 22000 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-RADTR | 7400 | 88680 | 88680 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-RADTR90003081
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 Service Air Conditioner | 2029-03-27 | 2029-03-27 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160381 | 27.03.2029 | 5500 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-AIRCN | 7500 | 82722 | 14586 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5475 | DT5475 Repl Engine Midlife complete | 2029-03-28 | 2029-03-30 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000363980 | 28.03.2029 | 17500 | CLB-MP-HAUL-DT5475-ENGINE | 6500 | 211 | 211 | CLB-MP-HAUL-DT5475-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 Spiders Transmission Driveshaft | 2029-03-28 | 2029-03-28 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154386 | 28.03.2029 | 11000 | CLB-MP-HAUL-DT172 -FDRSYS-DRSHT-UNVSL | 7500 | 92351 | 244 | CLB-MP-HAUL-DT172 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Steering Ball Studs | 2029-03-28 | 2029-03-29 | 19 hrs | FY29 | 35 | 90038356 | A1 | 1000385466 | 28.03.2029 | 15000 | CLB-MP-HAUL-DT197 -STRSYS-STLTR | 7500 | 86259 | 25173 | CLB-MP-HAUL-DT197 -STRSYS-STLTR90038356
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Tyre Sense Battery | 2029-03-29 | 2029-03-29 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163958 | 29.03.2029 | 24 Monthly | CLB-MP-HAUL-DT183 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT183 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Pump Hoist & Brake | 2029-03-29 | 2029-03-29 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000034401 | 29.03.2029 | 22000 | CLB-MP-HAUL-DT168 -HYDSYS-HOPMP | 7500 | 93142 | 2151 | CLB-MP-HAUL-DT168 -HYDSYS-HOPMP90003113
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Repl Cylinder Steering LHS | 2029-03-30 | 2029-03-30 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000347297 | 30.03.2029 | 20000 | CLB-MP-HAUL-DT5446-STRSYS-STRCY-STCYL | 6500 | 8776 | 2651 | CLB-MP-HAUL-DT5446-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5501 | DT5501 Repl Engine Midlife complete | 2029-04-01 | 2029-04-03 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000383510 | 01.04.2029 | 17500 | CLB-MP-HAUL-DT5501-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5501-ENGINE90029500
T264 | Onsite PM | Haul | Fortescue | DT5502 | DT5502 Repl Engine Midlife complete | 2029-04-01 | 2029-04-03 | 51 hrs | FY29 | 83 | 90029500 | A1 | 1000383601 | 01.04.2029 | 17500 | CLB-MP-HAUL-DT5502-ENGINE | 6500 | 1 | 1 | CLB-MP-HAUL-DT5502-ENGINE90029500
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Pump Drive Driveshaft Unis | 2029-04-01 | 2029-04-01 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035752 | 01.04.2029 | 11000 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR-DRSHT | 7500 | 83140 | 1989 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR-DRSHT90009874
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Wheel Assembly LHF | 2029-04-02 | 2029-04-03 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000346283 | 02.04.2029 | 24000 | CLB-MP-HAUL-DT5441-STRUCT-AXLES-HUBLH | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Wheel Assembly RHF | 2029-04-02 | 2029-04-03 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000346284 | 02.04.2029 | 24000 | CLB-MP-HAUL-DT5441-STRUCT-AXLES-HUBRH | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT170 | DT170 Repl Pump Transmission | 2029-04-04 | 2029-04-04 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000034494 | 04.04.2029 | 11000 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP | 7500 | 91119 | 12852 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP90003096
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Ovhl Axle Housing Dogbone | 2029-04-05 | 2029-04-06 | 22 hrs | FY29 | 42 | 90003118 | 1 | 1000035532 | 05.04.2029 | 22000 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-TAGLK | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-TAGLK90003118
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Brake & Steering Manifold | 2029-04-05 | 2029-04-05 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000362642 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-BRKSYS-BRVLV | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Gear Cooler Motor & Pump | 2029-04-05 | 2029-04-05 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000362661 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-FDRSYS-GRSOC-OCPPM | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Pump Airconditioner Drive | 2029-04-05 | 2029-04-05 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000362641 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-ACPMP | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Coupling Drive Pump | 2029-04-05 | 2029-04-05 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000362646 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-HYDPC | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Pump Main Hydraulic | 2029-04-05 | 2029-04-05 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000362669 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-HYPMP | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Cylinder Steering LHS | 2029-04-05 | 2029-04-05 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000362649 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-STRSYS-STRCY-STCYL | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Cylinder Steering RHS | 2029-04-05 | 2029-04-05 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000362650 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-STRSYS-STRCY-STCYR | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5471 | DT5471 Repl Valve Flow Amplifier | 2029-04-05 | 2029-04-05 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000362660 | 05.04.2029 | 20000 | CLB-MP-HAUL-DT5471-STRSYS-STVLV | 6500 | 2418 | 2418 | CLB-MP-HAUL-DT5471-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Overhaul Air Conditioner 24M | 2029-04-05 | 2029-04-07 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000346681 | 05.04.2029 | 24 Monthly | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN | 6500 | 7896 | 7896 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5455 | DT5455 Overhaul Air Conditioner 24M | 2029-04-09 | 2029-04-11 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000350427 | 09.04.2029 | 24 Monthly | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN | 6500 | 7738 | 7738 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Service Air Conditioner | 2029-04-10 | 2029-04-10 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160391 | 10.04.2029 | 5500 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN | 7500 | 92088 | 7001 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Tyre Sense Battery | 2029-04-10 | 2029-04-10 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163966 | 10.04.2029 | 24 Monthly | CLB-MP-HAUL-DT191 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT191 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Repl Cylinder Steering RHS | 2029-04-11 | 2029-04-11 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000349057 | 11.04.2029 | 20000 | CLB-MP-HAUL-DT5448-STRSYS-STRCY-STCYR | 6500 | 8548 | 2653 | CLB-MP-HAUL-DT5448-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5446 | DT5446 Overhaul Air Conditioner 24M | 2029-04-11 | 2029-04-13 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000347287 | 11.04.2029 | 24 Monthly | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN | 6500 | 8776 | 8776 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Brake Slack Adjuster Front | 2029-04-11 | 2029-04-11 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000150609 | 11.04.2029 | 18000 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACF | 7500 | 49737 | 15864 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACF90009306
T264 | Onsite PM | Haul | Fortescue | DT5475 | DT5475 Service Air Conditioner 12M | 2029-04-12 | 2029-04-12 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000363964 | 12.04.2029 | 12 Monthly | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN | 6500 | 211 | 211 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Overhaul Air Conditioner 24M | 2029-04-13 | 2029-04-15 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000346728 | 13.04.2029 | 24 Monthly | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Service Air Conditioner | 2029-04-13 | 2029-04-13 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160389 | 13.04.2029 | 5500 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-AIRCN | 7500 | 90364 | 6327 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Repl Cylinder Steering LHS | 2029-04-14 | 2029-04-14 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000349943 | 14.04.2029 | 20000 | CLB-MP-HAUL-DT5453-STRSYS-STRCY-STCYL | 6500 | 8172 | 2397 | CLB-MP-HAUL-DT5453-STRSYS-STRCY-STCYL90029373
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Engine Midlife complete | 2029-04-15 | 2029-04-19 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000157051 | 15.04.2029 | 11000 | CLB-MP-HAUL-DT199 -ENGINE | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Midlife Valve Set - Adjust | 2029-04-15 | 2029-04-15 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390983 | 15.04.2029 | 11000 | CLB-MP-HAUL-DT199 -ENGINE | 7500 | 85978 | 12765 | CLB-MP-HAUL-DT199 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Service Suspension Cylinders | 2029-04-15 | 2029-04-15 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106948 | 15.04.2029 | 11000 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN | 7500 | 85978 | 21221 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Spiders Transmission Driveshaft | 2029-04-15 | 2029-04-15 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154440 | 15.04.2029 | 11000 | CLB-MP-HAUL-DT199 -FDRSYS-DRSHT-UNVSL | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -FDRSYS-DRSHT-UNVSL90017135
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Tyre Sense Battery | 2029-04-15 | 2029-04-15 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163965 | 15.04.2029 | 24 Monthly | CLB-MP-HAUL-DT190 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT190 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Brake Slack Adjuster Front | 2029-04-16 | 2029-04-16 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072252 | 16.04.2029 | 18000 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACF | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT194 | DT194 Repl Brake Slack Adjuster Rear | 2029-04-16 | 2029-04-16 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072290 | 16.04.2029 | 18000 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACR | 7500 | 86451 | 15565 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Tyre Sense Battery | 2029-04-18 | 2029-04-18 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163951 | 18.04.2029 | 24 Monthly | CLB-MP-HAUL-DT176 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT176 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 1Y Air Tank LH External Inspect | 2029-04-18 | 2029-04-18 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389362 | 18.04.2029 | 12 Monthly | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH | 7500 | 85021 | 13713 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 1Y Air Tank RH External Inspect | 2029-04-18 | 2029-04-18 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389364 | 18.04.2029 | 12 Monthly | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH | 7500 | 85021 | 13713 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Brake Slack Adjuster Front | 2029-04-18 | 2029-04-18 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072249 | 18.04.2029 | 18000 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACF | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 Repl Brake Slack Adjuster Rear | 2029-04-18 | 2029-04-18 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072287 | 18.04.2029 | 18000 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACR | 7500 | 87047 | 15686 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Hyd Pump Steering Main | 2029-04-19 | 2029-04-19 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035279 | 19.04.2029 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STPMP | 7500 | 92088 | 9689 | CLB-MP-HAUL-DT185 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Steering HMU | 2029-04-19 | 2029-04-19 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000035280 | 19.04.2029 | 15000 | CLB-MP-HAUL-DT185 -STRSYS-STHMU | 7500 | 92088 | 9689 | CLB-MP-HAUL-DT185 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Midlife Valve Set - Adjust | 2029-04-19 | 2029-04-19 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390897 | 19.04.2029 | 11000 | CLB-MP-HAUL-DT173 -ENGINE | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Engine Midlife complete | 2029-04-19 | 2029-04-23 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156635 | 19.04.2029 | 11000 | CLB-MP-HAUL-DT173 -ENGINE | 7500 | 82651 | 12585 | CLB-MP-HAUL-DT173 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Spiders Transmission Driveshaft | 2029-04-19 | 2029-04-19 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154388 | 19.04.2029 | 11000 | CLB-MP-HAUL-DT173 -FDRSYS-DRSHT-UNVSL | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -FDRSYS-DRSHT-UNVSL90017135
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Replace Water Cannon | 2029-04-19 | 2029-04-19 | 12 hrs | FY29 | 24 | 90015535 | 1 | 1000133455 | 19.04.2029 | 12 Monthly | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON90015535
T264 | Onsite PM | Haul | Fortescue | DT5448 | DT5448 Overhaul Air Conditioner 24M | 2029-04-20 | 2029-04-22 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000349046 | 20.04.2029 | 24 Monthly | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN | 6500 | 8548 | 8548 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Pump Drive Driveshaft Unis | 2029-04-20 | 2029-04-20 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035099 | 20.04.2029 | 11000 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR-DRSHT | 7500 | 83441 | 15445 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 Repl Pump Torque Converter Charge | 2029-04-20 | 2029-04-20 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080203 | 20.04.2029 | 22000 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TCCPP | 7500 | 83441 | 27802 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Pump Brake Control | 2029-04-20 | 2029-04-20 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034670 | 20.04.2029 | 11000 | CLB-MP-HAUL-DT173 -BRKSYS-HYFPP | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Pump Drive Driveshaft Unis | 2029-04-21 | 2029-04-21 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000116270 | 21.04.2029 | 11000 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR-DRSHT | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 Repl Brake Relay Valve | 2029-04-21 | 2029-04-21 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078534 | 21.04.2029 | 11000 | CLB-MP-HAUL-DT173 -BRKSYS-BRVRL | 7500 | 82651 | 1534 | CLB-MP-HAUL-DT173 -BRKSYS-BRVRL90009877
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Oil Circulation Pump & Motor | 2029-04-21 | 2029-04-21 | 4 hrs | FY29 | 8 | 90018287 | 1 | 1000174670 | 21.04.2029 | 10000 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM2 | 4200 | 71996 | 1615 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM290018287
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 1Y Air Tank LH External Inspect | 2029-04-22 | 2029-04-22 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389318 | 22.04.2029 | 12 Monthly | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH | 7500 | 78739 | 40861 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 1Y Air Tank RH External Inspect | 2029-04-22 | 2029-04-22 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389320 | 22.04.2029 | 12 Monthly | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH | 7500 | 78739 | 40861 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Rotochamber Front | 2029-04-23 | 2029-04-23 | 5 hrs | FY29 | 5 | 90009308 | 1 | 1000072395 | 23.04.2029 | 22000 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTFR | 7500 | 92088 | 25896 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTFR90009308
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 Repl Valve Steering & AHS EH | 2029-04-23 | 2029-04-23 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000079665 | 23.04.2029 | 22000 | CLB-MP-HAUL-DT183 -STRSYS-STVLV | 7500 | 90364 | 1547 | CLB-MP-HAUL-DT183 -STRSYS-STVLV90009881
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Service Air Conditioner 12M | 2029-04-24 | 2029-04-24 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000372488 | 24.04.2029 | 12 Monthly | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN90029300
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Service Air Conditioner 12M | 2029-04-24 | 2029-04-24 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000371819 | 24.04.2029 | 12 Monthly | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Valve Steering & AHS EH | 2029-04-24 | 2029-04-24 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078709 | 24.04.2029 | 22000 | CLB-MP-HAUL-DT186 -STRSYS-STVLV | 7500 | 89749 | 23484 | CLB-MP-HAUL-DT186 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Brake Relay Valve | 2029-04-24 | 2029-04-24 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078705 | 24.04.2029 | 11000 | CLB-MP-HAUL-DT186 -BRKSYS-BRVRL | 7500 | 89749 | 1586 | CLB-MP-HAUL-DT186 -BRKSYS-BRVRL90009877
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Ramp Cylinder RH - Replace | 2029-04-24 | 2029-04-24 | 6 hrs | FY29 | 12 | 90018292 | 1 | 1000174676 | 24.04.2029 | 20000 | CLB-MP-SUPP-LL0003-HYDSYS-HDCYL-RCYLR | 4200 | 71996 | 8281 | CLB-MP-SUPP-LL0003-HYDSYS-HDCYL-RCYLR90018292
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Brake & Steering Manifold | 2029-04-25 | 2029-04-25 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000362687 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-BRKSYS-BRVLV | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Gear Cooler Motor & Pump | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000362706 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-FDRSYS-GRSOC-OCPPM | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Pump Airconditioner Drive | 2029-04-25 | 2029-04-25 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000362686 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-ACPMP | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Coupling Drive Pump | 2029-04-25 | 2029-04-25 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000362691 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-HYDPC | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Pump Main Hydraulic | 2029-04-25 | 2029-04-25 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000362714 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-HYPMP | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Cylinder Steering LHS | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000362694 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-STRSYS-STRCY-STCYL | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Cylinder Steering RHS | 2029-04-25 | 2029-04-25 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000362695 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-STRSYS-STRCY-STCYR | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5472 | DT5472 Repl Valve Flow Amplifier | 2029-04-25 | 2029-04-25 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000362705 | 25.04.2029 | 20000 | CLB-MP-HAUL-DT5472-STRSYS-STVLV | 6500 | 2219 | 2219 | CLB-MP-HAUL-DT5472-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Hyd Motor Axle Lube Rear | 2029-04-26 | 2029-04-26 | 9 hrs | FY29 | 9 | 90003101 | 1 | 1000035512 | 26.04.2029 | 22000 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-HYM01 | 7500 | 84546 | 712 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Transmission | 2029-04-26 | 2029-04-27 | 28 hrs | FY29 | 48 | 90003093 | 1 | 1000035318 | 26.04.2029 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS | 7500 | 89749 | 23493 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS90003093
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Transmission Oil Cooler | 2029-04-26 | 2029-04-26 | 13 hrs | FY29 | 13 | 90003532 | 1 | 1000040995 | 26.04.2029 | 22000 | CLB-MP-HAUL-DT186 -TRNSYS-TROLC | 7500 | 89749 | 23484 | CLB-MP-HAUL-DT186 -TRNSYS-TROLC90003532
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 5000Hr Valve Set | 2029-04-26 | 2029-04-26 | 12 hrs | FY29 | 24 | 90028725 | A1 | 1000289440 | 26.04.2029 | 5000 | CLB-MP-SUPP-WC015 -ENGINE | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl PTO Uni's | 2029-04-26 | 2029-04-26 | 4 hrs | FY29 | 4 | 90031093 | A1 | 1000307809 | 26.04.2029 | 5000 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT90031093
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Repl Steering Cylinder LH | 2029-04-26 | 2029-04-26 | 10 hrs | FY29 | 10 | 90004005 | 1 | 1000044795 | 26.04.2029 | 15000 | CLB-MP-SUPP-WC015 -STRSYS-STRCY-STCYL | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRSYS-STRCY-STCYL90004005
785D | Onsite PM | Haul | Fortescue | WC015 | WC015 Service Airconditioner | 2029-04-26 | 2029-04-26 | 12 hrs | FY29 | 12 | 90028728 | A1 | 1000289437 | 26.04.2029 | 5000 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN | 5000 | 67897 | 1397 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN90028728
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Steering Link & Arm Rebush | 2029-04-27 | 2029-04-28 | 27 hrs | FY29 | 45 | 90038355 | A1 | 1000385407 | 27.04.2029 | 30000 | CLB-MP-HAUL-DT167 -STRSYS-STLTR | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STLTR90038355
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Hyd Pump Steering Main | 2029-04-27 | 2029-04-27 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034341 | 27.04.2029 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STPMP | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Steering HMU | 2029-04-27 | 2029-04-27 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000034342 | 27.04.2029 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STHMU | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT167 | DT167 Repl Cyl Steering LH | 2029-04-27 | 2029-04-27 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034343 | 27.04.2029 | 15000 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYL | 7500 | 83303 | 9443 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Brake Slack Adjuster Front | 2029-04-28 | 2029-04-28 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072246 | 28.04.2029 | 18000 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACF | 7500 | 83931 | 15527 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Pump Hoist & Brake | 2029-04-28 | 2029-04-28 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035339 | 28.04.2029 | 22000 | CLB-MP-HAUL-DT186 -HYDSYS-HOPMP | 7500 | 89749 | 23493 | CLB-MP-HAUL-DT186 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Ovhl Axle Housing Dogbone | 2029-04-29 | 2029-04-30 | 22 hrs | FY29 | 42 | 90003118 | 1 | 1000036010 | 29.04.2029 | 22000 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-TAGLK | 7500 | 86259 | 25922 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Brake Wheel LH | 2029-04-30 | 2029-05-01 | 32 hrs | FY29 | 38 | 90003104 | 2 | 1000035587 | 30.04.2029 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-AXLES-HUBLH | 7500 | 90698 | 714 | CLB-MP-HAUL-DT190 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Cyl Suspension LHF | 2029-04-30 | 2029-05-01 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067866 | 30.04.2029 | 22000 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYLF | 7500 | 90698 | 1469 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Repl Pump Drive Driveshaft Unis | 2029-04-30 | 2029-04-30 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000035868 | 30.04.2029 | 11000 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR-DRSHT | 7500 | 82554 | 12514 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 Service Air Conditioner | 2029-04-30 | 2029-04-30 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160401 | 30.04.2029 | 5500 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-AIRCN | 7500 | 82554 | 15352 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Hyd Motor Axle Lube Rear | 2029-05-01 | 2029-05-01 | 9 hrs | FY29 | 9 | 90003101 | 1 | 1000034167 | 01.05.2029 | 22000 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-HYM01 | 7500 | 81875 | 1384 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-HYM0190003101
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 Repl Cyl Suspension RHF | 2029-05-02 | 2029-05-03 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067860 | 02.05.2029 | 22000 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRF | 7500 | 83931 | 23419 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRF90003121
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Pump Steering | 2029-05-02 | 2029-05-02 | 6 hrs | FY29 | 6 | 90013190 | A1 | 1000110258 | 02.05.2029 | 15000 | CLB-MP-SUPP-PM0004-STRSYS-STPMP | 3500 | 91736 | 5405 | CLB-MP-SUPP-PM0004-STRSYS-STPMP90013190
T264 | Onsite PM | Haul | Fortescue | DT5453 | DT5453 Overhaul Air Conditioner 24M | 2029-05-03 | 2029-05-05 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000349733 | 03.05.2029 | 24 Monthly | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Hyd Pump Steering Main | 2029-05-04 | 2029-05-04 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000035709 | 04.05.2029 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STPMP | 7500 | 91174 | 9223 | CLB-MP-HAUL-DT192 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Pump Brake Control | 2029-05-07 | 2029-05-07 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034945 | 07.05.2029 | 11000 | CLB-MP-HAUL-DT178 -BRKSYS-HYFPP | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Pump Hoist & Brake | 2029-05-07 | 2029-05-07 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000034953 | 07.05.2029 | 22000 | CLB-MP-HAUL-DT178 -HYDSYS-HOPMP | 7500 | 81600 | 1294 | CLB-MP-HAUL-DT178 -HYDSYS-HOPMP90003113
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Brake Slack Adjuster Front | 2029-05-08 | 2029-05-08 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072226 | 08.05.2029 | 18000 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACF | 7500 | 93142 | 15366 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACF90009306
T264 | Onsite PM | Haul | Fortescue | DT5449 | DT5449 Overhaul Air Conditioner 24M | 2029-05-09 | 2029-05-11 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000349090 | 09.05.2029 | 24 Monthly | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN | 6500 | 8483 | 8483 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 1Y Air Tank LH External Inspect | 2029-05-10 | 2029-05-10 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389330 | 10.05.2029 | 12 Monthly | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH | 7500 | 92948 | 52765 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 1Y Air Tank RH External Inspect | 2029-05-10 | 2029-05-10 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389332 | 10.05.2029 | 12 Monthly | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH | 7500 | 92948 | 52765 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Repl Brake Wheel LH | 2029-05-11 | 2029-05-12 | 32 hrs | FY29 | 38 | 90003104 | 1 | 1000150672 | 11.05.2029 | 22000 | CLB-MP-HAUL-DT225 -STRUCT-AXLES-HUBLH | 7500 | 51346 | 1218 | CLB-MP-HAUL-DT225 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Steering Ball Studs | 2029-05-11 | 2029-05-12 | 19 hrs | FY29 | 35 | 90038356 | A1 | 1000385452 | 11.05.2029 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STLTR | 7500 | 90698 | 24244 | CLB-MP-HAUL-DT190 -STRSYS-STLTR90038356
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Cylinder Steering LHS | 2029-05-11 | 2029-05-11 | 8 hrs | FY29 | 14 | 90029373 | A1 | 1000326395 | 11.05.2029 | 20000 | CLB-MP-HAUL-DT5417-STRSYS-STRCY-STCYL | 6500 | 10618 | 942 | CLB-MP-HAUL-DT5417-STRSYS-STRCY-STCYL90029373
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Pump Torque Converter Charge | 2029-05-12 | 2029-05-12 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080204 | 12.05.2029 | 22000 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TCCPP | 7500 | 92002 | 1213 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TCCPP90003095
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Final Drive LH | 2029-05-12 | 2029-05-13 | 30 hrs | FY29 | 56 | 90003099 | 1 | 1000035158 | 12.05.2029 | 22000 | CLB-MP-HAUL-DT182 -FDRSYS-FDRVE-FDRLH | 7500 | 92002 | 1213 | CLB-MP-HAUL-DT182 -FDRSYS-FDRVE-FDRLH90003099
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 1Y Air Tank LH External Inspect | 2029-05-12 | 2029-05-12 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389434 | 12.05.2029 | 12 Monthly | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH | 7500 | 82302 | 54081 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT195 | DT195 1Y Air Tank RH External Inspect | 2029-05-12 | 2029-05-12 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389436 | 12.05.2029 | 12 Monthly | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH | 7500 | 82302 | 54081 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 1Y Air Tank LH External Inspect | 2029-05-13 | 2029-05-13 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389346 | 13.05.2029 | 12 Monthly | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH | 7500 | 92088 | 46179 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT172 | DT172 1Y Air Tank RH External Inspect | 2029-05-13 | 2029-05-13 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389348 | 13.05.2029 | 12 Monthly | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH | 7500 | 92088 | 46179 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Valve Steering & AHS EH | 2029-05-13 | 2029-05-13 | 10 hrs | FY29 | 10 | 90009881 | 1 | 1000078804 | 13.05.2029 | 22000 | CLB-MP-HAUL-DT192 -STRSYS-STVLV | 7500 | 91174 | 1097 | CLB-MP-HAUL-DT192 -STRSYS-STVLV90009881
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Brake Relay Valve | 2029-05-13 | 2029-05-13 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078800 | 13.05.2029 | 11000 | CLB-MP-HAUL-DT192 -BRKSYS-BRVRL | 7500 | 91174 | 1097 | CLB-MP-HAUL-DT192 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Pump Drive Driveshaft Unis | 2029-05-13 | 2029-05-13 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000036107 | 13.05.2029 | 11000 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR-DRSHT | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Pump Brake Control | 2029-05-13 | 2029-05-13 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000036119 | 13.05.2029 | 11000 | CLB-MP-HAUL-DT199 -BRKSYS-HYFPP | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Brake Relay Valve | 2029-05-13 | 2029-05-13 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078876 | 13.05.2029 | 11000 | CLB-MP-HAUL-DT199 -BRKSYS-BRVRL | 7500 | 85978 | 1188 | CLB-MP-HAUL-DT199 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Service Suspension Cylinders | 2029-05-13 | 2029-05-13 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106891 | 13.05.2029 | 11000 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN | 7500 | 92002 | 16119 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Pump Transmission | 2029-05-13 | 2029-05-13 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000035320 | 13.05.2029 | 11000 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP | 7500 | 89749 | 12127 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP90003096
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Wheel Assembly LHF | 2029-05-14 | 2029-05-15 | 18 hrs | FY29 | 34 | 90029369 | A1 | 1000349718 | 14.05.2029 | 24000 | CLB-MP-HAUL-DT5452-STRUCT-AXLES-HUBLH | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-AXLES-HUBLH90029369
T264 | Onsite PM | Haul | Fortescue | DT5452 | DT5452 Repl Wheel Assembly RHF | 2029-05-14 | 2029-05-15 | 18 hrs | FY29 | 34 | 90029370 | A1 | 1000349719 | 14.05.2029 | 24000 | CLB-MP-HAUL-DT5452-STRUCT-AXLES-HUBRH | 6500 | 5722 | 5722 | CLB-MP-HAUL-DT5452-STRUCT-AXLES-HUBRH90029370
789D | Onsite PM | Haul | Fortescue | DT224 | DT224 Repl Brake Slack Adjuster Rear | 2029-05-15 | 2029-05-15 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000150610 | 15.05.2029 | 18000 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACR | 7500 | 49737 | 15155 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5476 | DT5476 Service Air Conditioner 12M | 2029-05-16 | 2029-05-16 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000364894 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN | 6500 | 920 | 920 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 1Y Air Tank LH External Inspect | 2029-05-16 | 2029-05-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389450 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH | 7500 | 85715 | 85715 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 1Y Air Tank RH External Inspect | 2029-05-16 | 2029-05-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389452 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH | 7500 | 85715 | 85715 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 1Y Air Tank LH External Inspect | 2029-05-16 | 2029-05-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389366 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH | 7500 | 81529 | 8461 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 1Y Air Tank RH External Inspect | 2029-05-16 | 2029-05-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389368 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH | 7500 | 81529 | 8461 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 1Y Air Tank LH External Inspect | 2029-05-16 | 2029-05-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389426 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH | 7500 | 82926 | 82926 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 1Y Air Tank RH External Inspect | 2029-05-16 | 2029-05-16 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389428 | 16.05.2029 | 12 Monthly | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH | 7500 | 82926 | 82926 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Tyre Sense Battery | 2029-05-16 | 2029-05-16 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163943 | 16.05.2029 | 24 Monthly | CLB-MP-HAUL-DT168 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT168 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Service Air Conditioner | 2029-05-18 | 2029-05-18 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160396 | 18.05.2029 | 5500 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-AIRCN | 7500 | 90698 | 6249 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT199 | DT199 Repl Fuel Tank Mounts | 2029-05-19 | 2029-05-19 | 8 hrs | FY29 | 16 | 90009887 | 1 | 1000078885 | 19.05.2029 | 22000 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULTK | 7500 | 85978 | 23065 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULTK90009887
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Hyd Pump Steering Main | 2029-05-20 | 2029-05-20 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034065 | 20.05.2029 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STPMP | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Steering HMU | 2029-05-20 | 2029-05-20 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000034066 | 20.05.2029 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STHMU | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STHMU90003110
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Cyl Steering RH | 2029-05-20 | 2029-05-20 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000034068 | 20.05.2029 | 15000 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYR | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Drive Line Axle LH | 2029-05-20 | 2029-05-20 | 4 hrs | FY29 | 8 | 90014551 | 1 | 1000123529 | 20.05.2029 | 30000 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX-AXLLH | 7500 | 83473 | 9021 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX-AXLLH90014551
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 5000Hr Valve Set | 2029-05-21 | 2029-05-21 | 12 hrs | FY29 | 24 | 90028725 | A1 | 1000289422 | 21.05.2029 | 5000 | CLB-MP-SUPP-WC012 -ENGINE | 5000 | 67273 | 20856 | CLB-MP-SUPP-WC012 -ENGINE90028725
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Service Airconditioner | 2029-05-21 | 2029-05-21 | 12 hrs | FY29 | 12 | 90028728 | A1 | 1000289419 | 21.05.2029 | 5000 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN | 5000 | 67273 | 10760 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN90028728
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Cyl Steering RH | 2029-05-22 | 2029-05-22 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035770 | 22.05.2029 | 15000 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYR | 7500 | 83140 | 8872 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYR90003111
T264 | Onsite PM | Haul | Fortescue | DT5419 | DT5419 Repl Control Cabinet Coolant | 2029-05-22 | 2029-05-22 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332196 | 22.05.2029 | 15000 | CLB-MP-HAUL-DT5419-ELCTHV-HVCAB-COOLR | 6500 | 10988 | 10988 | CLB-MP-HAUL-DT5419-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 1Y Air Tank LH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389406 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH | 7500 | 83734 | 10797 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT188 | DT188 1Y Air Tank RH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389408 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH | 7500 | 83734 | 10797 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 1Y Air Tank LH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389418 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH | 7500 | 86814 | 15453 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT191 | DT191 1Y Air Tank RH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389420 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH | 7500 | 86814 | 15453 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 1Y Air Tank LH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389382 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH | 7500 | 83200 | 57009 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT181 | DT181 1Y Air Tank RH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389384 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH | 7500 | 83200 | 57009 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 1Y Air Tank LH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389350 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH | 7500 | 82388 | 82388 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT173 | DT173 1Y Air Tank RH External Inspect | 2029-05-23 | 2029-05-23 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389352 | 23.05.2029 | 12 Monthly | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH | 7500 | 82388 | 82388 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT197 | DT197 Repl Tyre Sense Battery | 2029-05-24 | 2029-05-24 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163972 | 24.05.2029 | 24 Monthly | CLB-MP-HAUL-DT197 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT197 -MANGMT-TYRSN90017022
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Ovhl Axle A Frame | 2029-05-26 | 2029-05-27 | 36 hrs | FY29 | 60 | 90015390 | 1 | 1000130656 | 26.05.2029 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-AFRME | 7500 | 92088 | 22899 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-AFRME90015390
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Ovhl Axle Housing Dogbone | 2029-05-26 | 2029-05-27 | 22 hrs | FY29 | 42 | 90003118 | 1 | 1000035290 | 26.05.2029 | 22000 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-TAGLK | 7500 | 92088 | 22899 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-TAGLK90003118
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 1Y Air Tank LH External Inspect | 2029-05-26 | 2029-05-26 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389374 | 26.05.2029 | 12 Monthly | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH | 7500 | 83820 | 11121 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 1Y Air Tank RH External Inspect | 2029-05-26 | 2029-05-26 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389376 | 26.05.2029 | 12 Monthly | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH | 7500 | 83820 | 11121 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Tyre Sense Battery | 2029-05-26 | 2029-05-26 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163940 | 26.05.2029 | 24 Monthly | CLB-MP-HAUL-DT165 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT165 -MANGMT-TYRSN90017022
T264 | Onsite PM | Haul | Fortescue | DT5405 | DT5405 Repl Control Cabinet Coolant | 2029-05-27 | 2029-05-27 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332190 | 27.05.2029 | 15000 | CLB-MP-HAUL-DT5405-ELCTHV-HVCAB-COOLR | 6500 | 11503 | 11503 | CLB-MP-HAUL-DT5405-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Brake Wheel LH | 2029-05-27 | 2029-05-28 | 32 hrs | FY29 | 38 | 90003104 | 1 | 1000035328 | 27.05.2029 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBLH | 7500 | 89749 | 22897 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBLH90003104
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Cyl Suspension LHF | 2029-05-27 | 2029-05-28 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067850 | 27.05.2029 | 22000 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLF | 7500 | 89749 | 22897 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLF90003121
789D | Onsite PM | Haul | Fortescue | DT184 | DT184 Repl Cyl Suspension RHF | 2029-05-28 | 2029-05-29 | 38 hrs | FY29 | 66 | 90003121 | 1 | 1000067844 | 28.05.2029 | 22000 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYRF | 7500 | 83473 | 864 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYRF90003121
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Final Drive RH | 2029-05-28 | 2029-05-29 | 30 hrs | FY29 | 56 | 90003100 | 1 | 1000035324 | 28.05.2029 | 22000 | CLB-MP-HAUL-DT186 -FDRSYS-FDRVE-FDRRH | 7500 | 89749 | 893 | CLB-MP-HAUL-DT186 -FDRSYS-FDRVE-FDRRH90003100
785D | Onsite PM | Haul | Fortescue | WC014 | WC014 Replace Differential | 2029-05-29 | 2029-05-29 | 16 hrs | FY29 | 28 | 90003994 | 1 | 1000044712 | 29.05.2029 | 20000 | CLB-MP-SUPP-WC014 -FDRSYS-DIFFL | 5000 | 65823 | 5401 | CLB-MP-SUPP-WC014 -FDRSYS-DIFFL90003994
T264 | Onsite PM | Haul | Fortescue | DT5417 | DT5417 Repl Control Cabinet Coolant | 2029-05-29 | 2029-05-29 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332194 | 29.05.2029 | 15000 | CLB-MP-HAUL-DT5417-ELCTHV-HVCAB-COOLR | 6500 | 10618 | 10618 | CLB-MP-HAUL-DT5417-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 1Y Air Tank LH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389394 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH | 7500 | 91826 | 53019 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 1Y Air Tank RH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389396 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH | 7500 | 91826 | 53019 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 1Y Air Tank LH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389386 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH | 7500 | 90227 | 40762 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT183 | DT183 1Y Air Tank RH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389388 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH | 7500 | 90227 | 40762 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 1Y Air Tank LH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389438 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH | 7500 | 84897 | 84897 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 1Y Air Tank RH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389440 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH | 7500 | 84897 | 84897 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH90038753
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Service Air Conditioner | 2029-05-30 | 2029-05-30 | 12 hrs | FY29 | 12 | 90017450 | 1 | 1000160384 | 30.05.2029 | 5500 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN | 7500 | 81600 | 17038 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN90017450
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 1Y Air Tank LH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389414 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH | 7500 | 90436 | 17328 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 1Y Air Tank RH External Inspect | 2029-05-30 | 2029-05-30 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389416 | 30.05.2029 | 12 Monthly | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH | 7500 | 90436 | 17328 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Brake & Steering Manifold | 2029-05-30 | 2029-05-30 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000371423 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-BRKSYS-BRVLV | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Gear Cooler Motor & Pump | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000371435 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-FDRSYS-GRSOC-OCPPM | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Pump Airconditioner Drive | 2029-05-30 | 2029-05-30 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000371441 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-ACPMP | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Coupling Drive Pump | 2029-05-30 | 2029-05-30 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000371442 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-HYDPC | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Pump Main Hydraulic | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000371443 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-HYPMP | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Cylinder Steering LHS | 2029-05-30 | 2029-05-30 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000371447 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-STRSYS-STRCY-STCYL | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Cylinder Steering RHS | 2029-05-30 | 2029-05-30 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000371448 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-STRSYS-STRCY-STCYR | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5485 | DT5485 Repl Valve Flow Amplifier | 2029-05-30 | 2029-05-30 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000371449 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5485-STRSYS-STVLV | 6500 | 55 | 55 | CLB-MP-HAUL-DT5485-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Brake & Steering Manifold | 2029-05-30 | 2029-05-30 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000366434 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-BRKSYS-BRVLV | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Gear Cooler Motor & Pump | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000366493 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-FDRSYS-GRSOC-OCPPM | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Pump Airconditioner Drive | 2029-05-30 | 2029-05-30 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000366433 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-ACPMP | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Coupling Drive Pump | 2029-05-30 | 2029-05-30 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000366438 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-HYDPC | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Pump Main Hydraulic | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000366501 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-HYPMP | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Cylinder Steering LHS | 2029-05-30 | 2029-05-30 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000366481 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-STRSYS-STRCY-STCYL | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Cylinder Steering RHS | 2029-05-30 | 2029-05-30 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000366482 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-STRSYS-STRCY-STCYR | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5481 | DT5481 Repl Valve Flow Amplifier | 2029-05-30 | 2029-05-30 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000366492 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5481-STRSYS-STVLV | 6500 | 46 | 46 | CLB-MP-HAUL-DT5481-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Brake & Steering Manifold | 2029-05-30 | 2029-05-30 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000365679 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-BRKSYS-BRVLV | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Gear Cooler Motor & Pump | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000365698 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-FDRSYS-GRSOC-OCPPM | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Pump Airconditioner Drive | 2029-05-30 | 2029-05-30 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000365678 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-ACPMP | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Coupling Drive Pump | 2029-05-30 | 2029-05-30 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000365683 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-HYDPC | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Pump Main Hydraulic | 2029-05-30 | 2029-05-30 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000365706 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-HYPMP | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Cylinder Steering LHS | 2029-05-30 | 2029-05-30 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000365686 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-STRSYS-STRCY-STCYL | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Cylinder Steering RHS | 2029-05-30 | 2029-05-30 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000365687 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-STRSYS-STRCY-STCYR | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5479 | DT5479 Repl Valve Flow Amplifier | 2029-05-30 | 2029-05-30 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000365697 | 30.05.2029 | 20000 | CLB-MP-HAUL-DT5479-STRSYS-STVLV | 6500 | 47 | 47 | CLB-MP-HAUL-DT5479-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5454 | DT5454 Overhaul Air Conditioner 24M | 2029-05-31 | 2029-06-02 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000350383 | 31.05.2029 | 24 Monthly | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN | 6500 | 8172 | 8172 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Brake & Steering Manifold | 2029-05-31 | 2029-05-31 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000371352 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-BRKSYS-BRVLV | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Gear Cooler Motor & Pump | 2029-05-31 | 2029-05-31 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000371364 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-FDRSYS-GRSOC-OCPPM | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Pump Airconditioner Drive | 2029-05-31 | 2029-05-31 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000371370 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-ACPMP | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Coupling Drive Pump | 2029-05-31 | 2029-05-31 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000371371 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-HYDPC | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Pump Main Hydraulic | 2029-05-31 | 2029-05-31 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000371372 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-HYPMP | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Cylinder Steering LHS | 2029-05-31 | 2029-05-31 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000371376 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-STRSYS-STRCY-STCYL | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Cylinder Steering RHS | 2029-05-31 | 2029-05-31 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000371377 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-STRSYS-STRCY-STCYR | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5484 | DT5484 Repl Valve Flow Amplifier | 2029-05-31 | 2029-05-31 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000371378 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5484-STRSYS-STVLV | 6500 | 44 | 44 | CLB-MP-HAUL-DT5484-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Brake & Steering Manifold | 2029-05-31 | 2029-05-31 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000369067 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-BRKSYS-BRVLV | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Gear Cooler Motor & Pump | 2029-05-31 | 2029-05-31 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000369079 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-FDRSYS-GRSOC-OCPPM | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Pump Airconditioner Drive | 2029-05-31 | 2029-05-31 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000369105 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-ACPMP | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Coupling Drive Pump | 2029-05-31 | 2029-05-31 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000369106 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-HYDPC | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Pump Main Hydraulic | 2029-05-31 | 2029-05-31 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000369107 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-HYPMP | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Cylinder Steering LHS | 2029-05-31 | 2029-05-31 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000369111 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-STRSYS-STRCY-STCYL | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Cylinder Steering RHS | 2029-05-31 | 2029-05-31 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000369112 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-STRSYS-STRCY-STCYR | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5483 | DT5483 Repl Valve Flow Amplifier | 2029-05-31 | 2029-05-31 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000369113 | 31.05.2029 | 20000 | CLB-MP-HAUL-DT5483-STRSYS-STVLV | 6500 | 449 | 449 | CLB-MP-HAUL-DT5483-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Repl Steering HMU | 2029-06-01 | 2029-06-01 | 14 hrs | FY29 | 14 | 90003110 | 1 | 1000035594 | 01.06.2029 | 15000 | CLB-MP-HAUL-DT190 -STRSYS-STHMU | 7500 | 90698 | 8800 | CLB-MP-HAUL-DT190 -STRSYS-STHMU90003110
785D | Onsite PM | Haul | Fortescue | WC012 | WC012 Water Cannon Inspect | 2029-06-01 | 2029-06-01 | 3 hrs | FY29 | 3 | 90033661 | A1 | 1000338790 | 01.06.2029 | 6 Monthly | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | 5000 | 67273 | 3900 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON90033661
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Hyd Pump Steering Main | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 8 | 90003109 | 1 | 1000034893 | 02.06.2029 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STPMP | 7500 | 81791 | 8723 | CLB-MP-HAUL-DT177 -STRSYS-STPMP90003109
789D | Onsite PM | Haul | Fortescue | DT177 | DT177 Repl Cyl Steering LH | 2029-06-02 | 2029-06-02 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034895 | 02.06.2029 | 15000 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYL | 7500 | 81791 | 29757 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYL90003111
789D | Onsite PM | Haul | Fortescue | DT190 | DT190 Service Suspension Cylinders | 2029-06-02 | 2029-06-02 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106899 | 02.06.2029 | 11000 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN | 7500 | 90698 | 22083 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN90012840
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000376510 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000377262 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000377268 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000377269 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000377270 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000377274 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000377275 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5500 | DT5500 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000377276 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5500-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5500-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000376463 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000376475 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000376481 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000376482 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000376483 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000376487 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000376488 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5499 | DT5499 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000376489 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5499-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5499-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000375458 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000375550 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000375556 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000375557 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000375558 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000375562 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000375563 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5498 | DT5498 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000375564 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5498-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5498-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000375405 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000375417 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000375423 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000375424 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000375425 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000375429 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000375430 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5497 | DT5497 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000375431 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5497-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5497-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000374028 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000374040 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000374046 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000374047 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000374048 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000374052 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000374053 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5496 | DT5496 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000374054 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5496-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5496-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000373937 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000373989 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000373995 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000373996 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000373997 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000374001 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000374002 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5495 | DT5495 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000374003 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5495-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5495-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000373589 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000373601 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000373607 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000373608 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000373609 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000373613 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000373614 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5494 | DT5494 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000373615 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5494-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5494-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000373331 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000373343 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000373349 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000373350 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000373351 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000373355 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000373356 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5493 | DT5493 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000373357 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5493-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5493-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000373017 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000373089 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000373095 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000373096 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000373097 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000373101 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000373102 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5492 | DT5492 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000373103 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5492-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5492-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000372688 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000372720 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000372726 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000372727 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000372728 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000372732 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000372733 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5491 | DT5491 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000372734 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5491-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5491-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000367432 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000367590 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000367431 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000367436 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000367598 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000367439 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000367580 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5482 | DT5482 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000367589 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5482-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5482-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000366199 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-BRKSYS-BRVLV | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000366358 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-FDRSYS-GRSOC-OCPPM | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000366198 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-ACPMP | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000366343 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-HYDPC | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000366366 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-HYPMP | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000366346 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-STRSYS-STRCY-STCYL | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000366347 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-STRSYS-STRCY-STCYR | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5480 | DT5480 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000366357 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5480-STRSYS-STVLV | 6500 | 2 | 2 | CLB-MP-HAUL-DT5480-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Brake & Steering Manifold | 2029-06-02 | 2029-06-02 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000365629 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Gear Cooler Motor & Pump | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000365648 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Pump Airconditioner Drive | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000365628 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Coupling Drive Pump | 2029-06-02 | 2029-06-02 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000365633 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Pump Main Hydraulic | 2029-06-02 | 2029-06-02 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000365656 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Cylinder Steering LHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000365636 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Cylinder Steering RHS | 2029-06-02 | 2029-06-02 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000365637 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5478 | DT5478 Repl Valve Flow Amplifier | 2029-06-02 | 2029-06-02 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000365647 | 02.06.2029 | 20000 | CLB-MP-HAUL-DT5478-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5478-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 Repl Cyl Steering LH | 2029-06-03 | 2029-06-03 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000034950 | 03.06.2029 | 15000 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYL | 7500 | 81600 | 8739 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYL90003111
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Cylinder Steering LHS | 2029-06-03 | 2029-06-03 | 8 hrs | FY29 | 14 | 90029373 | A1 | 1000326566 | 03.06.2029 | 20000 | CLB-MP-HAUL-DT5418-STRSYS-STRCY-STCYL | 6500 | 10719 | 851 | CLB-MP-HAUL-DT5418-STRSYS-STRCY-STCYL90029373
789D | Onsite PM | Haul | Fortescue | DT193 | DT193 Repl Brake Wheel RH | 2029-06-05 | 2029-06-06 | 33 hrs | FY29 | 61 | 90003105 | 2 | 1000035762 | 05.06.2029 | 22000 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBRH | 7500 | 83140 | 21307 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBRH90003105
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Slack Adjuster Front | 2029-06-06 | 2029-06-06 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072240 | 06.06.2029 | 18000 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACF | 7500 | 92002 | 14717 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Brake Slack Adjuster Rear | 2029-06-06 | 2029-06-06 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072278 | 06.06.2029 | 18000 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACR | 7500 | 92002 | 14717 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACR90009307
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Torque Converter | 2029-06-06 | 2029-06-07 | 32 hrs | FY29 | 62 | 90003092 | 1 | 1000034214 | 06.06.2029 | 22000 | CLB-MP-HAUL-DT165 -TRNSYS-TRQUE | 7500 | 78966 | 708 | CLB-MP-HAUL-DT165 -TRNSYS-TRQUE90003092
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Pump Torque Converter Charge | 2029-06-06 | 2029-06-06 | 5 hrs | FY29 | 5 | 90003095 | 1 | 1000080168 | 06.06.2029 | 22000 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TCCPP | 7500 | 78966 | 708 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TCCPP90003095
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Brake & Steering Manifold | 2029-06-06 | 2029-06-06 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000371542 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-BRKSYS-BRVLV | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Gear Cooler Motor & Pump | 2029-06-06 | 2029-06-06 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000371554 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-FDRSYS-GRSOC-OCPPM | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Pump Airconditioner Drive | 2029-06-06 | 2029-06-06 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000371560 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-ACPMP | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Coupling Drive Pump | 2029-06-06 | 2029-06-06 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000371561 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-HYDPC | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Pump Main Hydraulic | 2029-06-06 | 2029-06-06 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000371562 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-HYPMP | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Cylinder Steering LHS | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000371566 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-STRSYS-STRCY-STCYL | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Cylinder Steering RHS | 2029-06-06 | 2029-06-06 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000371567 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-STRSYS-STRCY-STCYR | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5486 | DT5486 Repl Valve Flow Amplifier | 2029-06-06 | 2029-06-06 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000371568 | 06.06.2029 | 20000 | CLB-MP-HAUL-DT5486-STRSYS-STVLV | 6500 | 66 | 66 | CLB-MP-HAUL-DT5486-STRSYS-STVLV90029367
785D | Onsite PM | Haul | Fortescue | WC3108 | WC3108 Repl Steering Link & Arm Rebush | 2029-06-07 | 2029-06-07 | 14 hrs | FY29 | 22 | 90004007 | 1 | 1000221759 | 07.06.2029 | 15000 | CLB-MP-SUPP-WC3108-STRSYS-STLTR | 5000 | 17738 | 17738 | CLB-MP-SUPP-WC3108-STRSYS-STLTR90004007
789D | Onsite PM | Haul | Fortescue | DT182 | DT182 Repl Rotochamber Front | 2029-06-07 | 2029-06-07 | 5 hrs | FY29 | 5 | 90009308 | 1 | 1000072392 | 07.06.2029 | 22000 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTFR | 7500 | 92002 | 22684 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTFR90009308
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Brake & Steering Manifold | 2029-06-07 | 2029-06-07 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000361767 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-BRKSYS-BRVLV | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Gear Cooler Motor & Pump | 2029-06-07 | 2029-06-07 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000361786 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-FDRSYS-GRSOC-OCPPM | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Pump Airconditioner Drive | 2029-06-07 | 2029-06-07 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000361766 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-ACPMP | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Coupling Drive Pump | 2029-06-07 | 2029-06-07 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000361771 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-HYDPC | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Pump Main Hydraulic | 2029-06-07 | 2029-06-07 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000361794 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-HYPMP | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Cylinder Steering LHS | 2029-06-07 | 2029-06-07 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000361774 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-STRSYS-STRCY-STCYL | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Cylinder Steering RHS | 2029-06-07 | 2029-06-07 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000361775 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-STRSYS-STRCY-STCYR | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5473 | DT5473 Repl Valve Flow Amplifier | 2029-06-07 | 2029-06-07 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000361785 | 07.06.2029 | 20000 | CLB-MP-HAUL-DT5473-STRSYS-STVLV | 6500 | 866 | 866 | CLB-MP-HAUL-DT5473-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Engine Cat 3516B | 2029-06-08 | 2029-06-12 | 96 hrs | FY29 | 142 | 90017315 | 1 | 1000156493 | 08.06.2029 | 22000 | CLB-MP-HAUL-DT165 -ENGINE | 7500 | 78966 | 708 | CLB-MP-HAUL-DT165 -ENGINE90017315
789D | Onsite PM | Haul | Fortescue | DT186 | DT186 Repl Cyl Steering LH | 2029-06-08 | 2029-06-08 | 16 hrs | FY29 | 28 | 90003111 | 2 | 1000035336 | 08.06.2029 | 15000 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYL | 7500 | 89749 | 8654 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYL90003111
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Brake & Steering Manifold | 2029-06-08 | 2029-06-08 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000361814 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-BRKSYS-BRVLV | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Gear Cooler Motor & Pump | 2029-06-08 | 2029-06-08 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000361833 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-FDRSYS-GRSOC-OCPPM | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Pump Airconditioner Drive | 2029-06-08 | 2029-06-08 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000361813 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-ACPMP | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Coupling Drive Pump | 2029-06-08 | 2029-06-08 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000361818 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-HYDPC | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Pump Main Hydraulic | 2029-06-08 | 2029-06-08 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000361841 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-HYPMP | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Cylinder Steering LHS | 2029-06-08 | 2029-06-08 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000361821 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-STRSYS-STRCY-STCYL | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Cylinder Steering RHS | 2029-06-08 | 2029-06-08 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000361822 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-STRSYS-STRCY-STCYR | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5474 | DT5474 Repl Valve Flow Amplifier | 2029-06-08 | 2029-06-08 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000361832 | 08.06.2029 | 20000 | CLB-MP-HAUL-DT5474-STRSYS-STVLV | 6500 | 537 | 537 | CLB-MP-HAUL-DT5474-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Brake Slack Adjuster Front | 2029-06-09 | 2029-06-09 | 4 hrs | FY29 | 4 | 90009306 | 1 | 1000072247 | 09.06.2029 | 18000 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACF | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACF90009306
789D | Onsite PM | Haul | Fortescue | DT189 | DT189 Repl Brake Slack Adjuster Rear | 2029-06-09 | 2029-06-09 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072285 | 09.06.2029 | 18000 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACR | 7500 | 84546 | 14655 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACR90009307
T264 | Onsite PM | Haul | Fortescue | DT5391 | DT5391 Repl Control Cabinet Coolant | 2029-06-10 | 2029-06-10 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332188 | 10.06.2029 | 15000 | CLB-MP-HAUL-DT5391-ELCTHV-HVCAB-COOLR | 6500 | 11246 | 11246 | CLB-MP-HAUL-DT5391-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT168 | DT168 Repl Brake Slack Adjuster Rear | 2029-06-10 | 2029-06-10 | 4 hrs | FY29 | 4 | 90009307 | 1 | 1000072264 | 10.06.2029 | 18000 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACR | 7500 | 93142 | 14674 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACR90009307
785D | Onsite PM | Haul | Fortescue | WC013 | WC013 Repl PTO Uni's | 2029-06-10 | 2029-06-10 | 4 hrs | FY29 | 4 | 90031093 | A1 | 1000307805 | 10.06.2029 | 5000 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT | 5000 | 63833 | 10962 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT90031093
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Brake & Steering Manifold | 2029-06-10 | 2029-06-10 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000381291 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Gear Cooler Motor & Pump | 2029-06-10 | 2029-06-10 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000381323 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Pump Airconditioner Drive | 2029-06-10 | 2029-06-10 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000381329 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Coupling Drive Pump | 2029-06-10 | 2029-06-10 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000381330 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Pump Main Hydraulic | 2029-06-10 | 2029-06-10 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000381331 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Cylinder Steering LHS | 2029-06-10 | 2029-06-10 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000381335 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Cylinder Steering RHS | 2029-06-10 | 2029-06-10 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000381336 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5504 | DT5504 Repl Valve Flow Amplifier | 2029-06-10 | 2029-06-10 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000381337 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5504-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5504-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Brake & Steering Manifold | 2029-06-10 | 2029-06-10 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000381243 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-BRKSYS-BRVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Gear Cooler Motor & Pump | 2029-06-10 | 2029-06-10 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000381255 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-FDRSYS-GRSOC-OCPPM | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Pump Airconditioner Drive | 2029-06-10 | 2029-06-10 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000381261 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-ACPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Coupling Drive Pump | 2029-06-10 | 2029-06-10 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000381262 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-HYDPC | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Pump Main Hydraulic | 2029-06-10 | 2029-06-10 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000381263 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-HYPMP | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Cylinder Steering LHS | 2029-06-10 | 2029-06-10 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000381267 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-STRSYS-STRCY-STCYL | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Cylinder Steering RHS | 2029-06-10 | 2029-06-10 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000381268 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-STRSYS-STRCY-STCYR | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5503 | DT5503 Repl Valve Flow Amplifier | 2029-06-10 | 2029-06-10 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000381269 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5503-STRSYS-STVLV | 6500 | 1 | 1 | CLB-MP-HAUL-DT5503-STRSYS-STVLV90029367
T264 | Onsite PM | Haul | Fortescue | DT5441 | DT5441 Repl Pump Main Hydraulic | 2029-06-10 | 2029-06-10 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000346281 | 10.06.2029 | 20000 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-HYPMP | 6500 | 6253 | 6253 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-HYPMP90029366
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 1Y Air Tank LH External Inspect | 2029-06-11 | 2029-06-11 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389370 | 11.06.2029 | 12 Monthly | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH | 7500 | 81378 | 16017 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT178 | DT178 1Y Air Tank RH External Inspect | 2029-06-11 | 2029-06-11 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389372 | 11.06.2029 | 12 Monthly | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH | 7500 | 81378 | 16017 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Overhaul Air Conditioner 24M | 2029-06-13 | 2029-06-15 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000357053 | 13.06.2029 | 24 Monthly | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN90029460
T264 | Onsite PM | Haul | Fortescue | DT5451 | DT5451 Overhaul Air Conditioner 24M | 2029-06-13 | 2029-06-15 | 48 hrs | FY29 | 48 | 90029460 | A1 | 1000349591 | 13.06.2029 | 24 Monthly | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN | 6500 | 8297 | 8297 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN90029460
789D | Onsite PM | Haul | Fortescue | DT225 | DT225 Service Air Conditioner | 2029-06-13 | 2029-06-13 | 12 hrs | FY29 | 12 | 90017450 | 2 | 1000160408 | 13.06.2029 | 5500 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-AIRCN | 7500 | 51346 | 576 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-AIRCN90017450
T264 | Onsite PM | Haul | Fortescue | DT5418 | DT5418 Repl Control Cabinet Coolant | 2029-06-13 | 2029-06-13 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332195 | 13.06.2029 | 15000 | CLB-MP-HAUL-DT5418-ELCTHV-HVCAB-COOLR | 6500 | 10719 | 10719 | CLB-MP-HAUL-DT5418-ELCTHV-HVCAB-COOLR90033128
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Steering Linkages | 2029-06-14 | 2029-06-14 | 12 hrs | FY29 | 24 | 90003056 | A1 | 1000033997 | 14.06.2029 | 9000 | CLB-MP-SUPP-SV021 -STRSYS-STLTR | 3300 | 54098 | 8323 | CLB-MP-SUPP-SV021 -STRSYS-STLTR90003056
777F | Onsite PM | Haul | Fortescue | SV021 | SV021 Replace Cylinder Suspension LHR | 2029-06-14 | 2029-06-15 | 26 hrs | FY29 | 50 | 90003071 | A1 | 1000034015 | 14.06.2029 | 18000 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYLR | 3300 | 54098 | 8323 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYLR90003071
T264 | Onsite PM | Haul | Fortescue | DT5477 | DT5477 Service Air Conditioner 12M | 2029-06-15 | 2029-06-15 | 12 hrs | FY29 | 12 | 90029300 | A1 | 1000365185 | 15.06.2029 | 12 Monthly | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN | 6500 | 630 | 630 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN90029300
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 1Y Air Tank LH External Inspect | 2029-06-15 | 2029-06-15 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389358 | 15.06.2029 | 12 Monthly | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH | 7500 | 82478 | 82478 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH90038753
789D | Onsite PM | Haul | Fortescue | DT175 | DT175 1Y Air Tank RH External Inspect | 2029-06-15 | 2029-06-15 | 1.5 hrs | FY29 | 1.5 | 90038753 | A1 | 1000389360 | 15.06.2029 | 12 Monthly | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH | 7500 | 82478 | 82478 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH90038753
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Blower Main Assembly | 2029-06-16 | 2029-06-16 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000346775 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-ELCTHV-HVBLW | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Motor Grid Box Blower | 2029-06-16 | 2029-06-16 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000346771 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-ELCTHV-HVGBM | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Hoist LHS | 2029-06-16 | 2029-06-16 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000346736 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-HYDSYS-HOCYL-HCYLH | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Hoist RHS | 2029-06-16 | 2029-06-17 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000346737 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-HYDSYS-HOCYL-HCYRH | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Hoist Manifold | 2029-06-16 | 2029-06-17 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000346773 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-HYDSYS-HOMAN | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Accumulator Pump Control | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000346725 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-HYDSYS-HDACC-PCACC | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Seat Operator | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000346777 | 16.06.2029 | 14000 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-SEATS | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Suspension LHF | 2029-06-16 | 2029-06-18 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000346760 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYLF | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Suspension LHR | 2029-06-16 | 2029-06-17 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000346761 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYLR | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Suspension RHF | 2029-06-16 | 2029-06-18 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000346762 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYRF | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Repl Cylinder Suspension RHR | 2029-06-16 | 2029-06-17 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000346763 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYRR | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Accumulator Brake Front DS | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370111 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC01 | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Accumulator Brake Front ODS | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370112 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC02 | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Accumulator Brake Rear DS | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370113 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC03 | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Accumulator Brake Rear ODS | 2029-06-16 | 2029-06-16 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370114 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC04 | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Accumulator Steering DS | 2029-06-16 | 2029-06-16 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370115 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-STRSYS-STACC-SACLH | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5444 | DT5444 Accumulator Steering ODS | 2029-06-16 | 2029-06-16 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370116 | 16.06.2029 | 28000 | CLB-MP-HAUL-DT5444-STRSYS-STACC-SACRH | 6500 | 9285 | 9285 | CLB-MP-HAUL-DT5444-STRSYS-STACC-SACRH90029372
789D | Onsite PM | Haul | Fortescue | DT166 | DT166 Spiders Transmission Driveshaft | 2029-06-18 | 2029-06-18 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154374 | 18.06.2029 | 11000 | CLB-MP-HAUL-DT166 -FDRSYS-DRSHT-UNVSL | 7500 | 95491 | 2090 | CLB-MP-HAUL-DT166 -FDRSYS-DRSHT-UNVSL90017135
T264 | Onsite PM | Haul | Fortescue | DT5416 | DT5416 Repl Control Cabinet Coolant | 2029-06-18 | 2029-06-18 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332193 | 18.06.2029 | 15000 | CLB-MP-HAUL-DT5416-ELCTHV-HVCAB-COOLR | 6500 | 10405 | 10405 | CLB-MP-HAUL-DT5416-ELCTHV-HVCAB-COOLR90033128
T264 | Onsite PM | Haul | Fortescue | DT5410 | DT5410 Repl Control Cabinet Coolant | 2029-06-20 | 2029-06-20 | 1 hr | FY29 | 1 | 90033128 | A1 | 1000332191 | 20.06.2029 | 15000 | CLB-MP-HAUL-DT5410-ELCTHV-HVCAB-COOLR | 6500 | 10949 | 10949 | CLB-MP-HAUL-DT5410-ELCTHV-HVCAB-COOLR90033128
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Engine Midlife complete | 2029-06-20 | 2029-06-24 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156491 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -ENGINE | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Midlife Valve Set - Adjust | 2029-06-20 | 2029-06-20 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390888 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -ENGINE | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Pump Drive Driveshaft Unis | 2029-06-20 | 2029-06-20 | 4 hrs | FY29 | 4 | 90009874 | 1 | 1000034161 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT90009874
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Pump Brake Control | 2029-06-20 | 2029-06-20 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000034173 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP | 7500 | 81875 | 7647 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Service Suspension Cylinders | 2029-06-20 | 2029-06-20 | 15 hrs | FY29 | 27 | 90012840 | 1 | 1000106872 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN90012840
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Repl Brake Relay Valve | 2029-06-20 | 2029-06-20 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078363 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT164 | DT164 Spiders Transmission Driveshaft | 2029-06-20 | 2029-06-20 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154370 | 20.06.2029 | 11000 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT-UNVSL | 7500 | 81875 | 11396 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT-UNVSL90017135
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Brake & Steering Manifold | 2029-06-22 | 2029-06-22 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000371781 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-BRKSYS-BRVLV | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Gear Cooler Motor & Pump | 2029-06-22 | 2029-06-22 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000371793 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-FDRSYS-GRSOC-OCPPM | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Pump Airconditioner Drive | 2029-06-22 | 2029-06-22 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000371799 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-ACPMP | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Coupling Drive Pump | 2029-06-22 | 2029-06-22 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000371800 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-HYDPC | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Pump Main Hydraulic | 2029-06-22 | 2029-06-22 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000371801 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-HYPMP | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Cylinder Steering LHS | 2029-06-22 | 2029-06-22 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000371805 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-STRSYS-STRCY-STCYL | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Cylinder Steering RHS | 2029-06-22 | 2029-06-22 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000371806 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-STRSYS-STRCY-STCYR | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5487 | DT5487 Repl Valve Flow Amplifier | 2029-06-22 | 2029-06-22 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000371807 | 22.06.2029 | 20000 | CLB-MP-HAUL-DT5487-STRSYS-STVLV | 6500 | 1030 | 1030 | CLB-MP-HAUL-DT5487-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT192 | DT192 Repl Cyl Steering RH | 2029-06-22 | 2029-06-22 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035712 | 22.06.2029 | 15000 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYR | 7500 | 91174 | 24285 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYR90003111
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Engine Midlife complete | 2029-06-22 | 2029-06-26 | 107.5 hrs | FY29 | 119.5 | 90017316 | 1 | 1000156731 | 22.06.2029 | 11000 | CLB-MP-HAUL-DT179 -ENGINE | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -ENGINE90017316
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Midlife Valve Set - Adjust | 2029-06-22 | 2029-06-22 | 6 hrs | FY29 | 12 | 90017314 | 1 | 1000390943 | 22.06.2029 | 11000 | CLB-MP-HAUL-DT179 -ENGINE | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -ENGINE90017314
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Pump Brake Control | 2029-06-22 | 2029-06-22 | 5 hrs | FY29 | 5 | 90003106 | 1 | 1000035000 | 22.06.2029 | 11000 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP90003106
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Repl Brake Relay Valve | 2029-06-22 | 2029-06-22 | 6 hrs | FY29 | 6 | 90009877 | 1 | 1000078610 | 22.06.2029 | 11000 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL90009877
789D | Onsite PM | Haul | Fortescue | DT179 | DT179 Spiders Transmission Driveshaft | 2029-06-22 | 2029-06-22 | 4 hrs | FY29 | 8 | 90017135 | 1 | 1000154400 | 22.06.2029 | 11000 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT-UNVSL | 7500 | 84079 | 11380 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT-UNVSL90017135
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 Water Cannon & Valves Repl | 2029-06-22 | 2029-06-23 | 24 hrs | FY29 | 48 | 90033662 | A1 | 1000338996 | 22.06.2029 | 24 Monthly | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | 5000 | 64118 | 9073 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON90033662
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Air Con System Service | 2029-06-23 | 2029-06-23 | 12 hrs | FY29 | 12 | 90028738 | A1 | 1000286361 | 23.06.2029 | 12 Monthly | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN | 3500 | 91736 | 186 | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN90028738
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Motor Grid Box Blower | 2029-06-24 | 2029-06-24 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000300056 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-ELCTHV-HVGBM | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Blower Main Assembly | 2029-06-24 | 2029-06-24 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000300058 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-ELCTHV-HVBLW | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Accumulator Pump Control | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000303962 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-HYDSYS-HDACC-PCACC | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Hoist Manifold | 2029-06-24 | 2029-06-25 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000300324 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-HYDSYS-HOMAN | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Hoist LHS | 2029-06-24 | 2029-06-24 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000300046 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-HYDSYS-HOCYL-HCYLH | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Hoist RHS | 2029-06-24 | 2029-06-25 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000300323 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-HYDSYS-HOCYL-HCYRH | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Seat Operator | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000300049 | 24.06.2029 | 14000 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-SEATS | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Suspension LHF | 2029-06-24 | 2029-06-26 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000300334 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYLF | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Suspension RHF | 2029-06-24 | 2029-06-26 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000300335 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYRF | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Repl Cylinder Suspension LHR | 2029-06-24 | 2029-06-25 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000300336 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYLR | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Accumulator Brake Front DS | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000369967 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC01 | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Accumulator Brake Front ODS | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000369968 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC02 | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Accumulator Brake Rear DS | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000369969 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC03 | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Accumulator Brake Rear ODS | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000369970 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC04 | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Accumulator Steering DS | 2029-06-24 | 2029-06-24 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000369971 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-STRSYS-STACC-SACLH | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5390 | DT5390 Accumulator Steering ODS | 2029-06-24 | 2029-06-24 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000369972 | 24.06.2029 | 28000 | CLB-MP-HAUL-DT5390-STRSYS-STACC-SACRH | 6500 | 9157 | 9157 | CLB-MP-HAUL-DT5390-STRSYS-STACC-SACRH90029372
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Brake & Steering Manifold | 2029-06-24 | 2029-06-24 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000357056 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-BRKSYS-BRVLV | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Gear Cooler Motor & Pump | 2029-06-24 | 2029-06-24 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000357115 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-FDRSYS-GRSOC-OCPPM | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Pump Airconditioner Drive | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000357055 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-ACPMP | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Coupling Drive Pump | 2029-06-24 | 2029-06-24 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000357100 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-HYDPC | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Pump Main Hydraulic | 2029-06-24 | 2029-06-24 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000357123 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-HYPMP | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Cylinder Steering LHS | 2029-06-24 | 2029-06-24 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000357103 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-STRSYS-STRCY-STCYL | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Cylinder Steering RHS | 2029-06-24 | 2029-06-24 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000357104 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-STRSYS-STRCY-STCYR | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5466 | DT5466 Repl Valve Flow Amplifier | 2029-06-24 | 2029-06-24 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000357114 | 24.06.2029 | 20000 | CLB-MP-HAUL-DT5466-STRSYS-STVLV | 6500 | 1342 | 1342 | CLB-MP-HAUL-DT5466-STRSYS-STVLV90029367
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 Replace Steering Pump | 2029-06-24 | 2029-06-24 | 4 hrs | FY29 | 4 | 90004003 | 1 | 1000082734 | 24.06.2029 | 15000 | CLB-MP-SUPP-PM0006-STRSYS-STPMP | 4200 | 53807 | 2698 | CLB-MP-SUPP-PM0006-STRSYS-STPMP90004003
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Transmission | 2029-06-24 | 2029-06-25 | 28 hrs | FY29 | 56 | 90013165 | A1 | 1000110235 | 24.06.2029 | 18000 | CLB-MP-SUPP-PM0004-TRNSYS-TRANS | 3500 | 91736 | 8412 | CLB-MP-SUPP-PM0004-TRNSYS-TRANS90013165
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Oil Cooler Transmission | 2029-06-24 | 2029-06-24 | 12 hrs | FY29 | 12 | 90013168 | A1 | 1000110238 | 24.06.2029 | 18000 | CLB-MP-SUPP-PM0004-TRNSYS-TROLC | 3500 | 91736 | 8412 | CLB-MP-SUPP-PM0004-TRNSYS-TROLC90013168
789D | Onsite PM | Haul | Fortescue | DT176 | DT176 Repl Pump Transmission | 2029-06-25 | 2029-06-25 | 7 hrs | FY29 | 7 | 90003096 | 1 | 1000034824 | 25.06.2029 | 11000 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP | 7500 | 85284 | 11308 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP90003096
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Motor Grid Box Blower | 2029-06-25 | 2029-06-25 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000314532 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-ELCTHV-HVGBM | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Blower Main Assembly | 2029-06-25 | 2029-06-25 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000314534 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-ELCTHV-HVBLW | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Accumulator Pump Control | 2029-06-25 | 2029-06-25 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000314562 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-HYDSYS-HDACC-PCACC | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Hoist Manifold | 2029-06-25 | 2029-06-26 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000314540 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-HYDSYS-HOMAN | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Hoist LHS | 2029-06-25 | 2029-06-25 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000314522 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-HYDSYS-HOCYL-HCYLH | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Hoist RHS | 2029-06-25 | 2029-06-26 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000314539 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-HYDSYS-HOCYL-HCYRH | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Seat Operator | 2029-06-25 | 2029-06-25 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000314525 | 25.06.2029 | 14000 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-SEATS | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Suspension LHF | 2029-06-25 | 2029-06-27 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000314550 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYLF | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Suspension RHF | 2029-06-25 | 2029-06-27 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000314551 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYRF | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Suspension LHR | 2029-06-25 | 2029-06-26 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000314552 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYLR | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Repl Cylinder Suspension RHR | 2029-06-25 | 2029-06-26 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000314553 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYRR | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Accumulator Brake Front DS | 2029-06-25 | 2029-06-25 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370057 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC01 | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Accumulator Brake Front ODS | 2029-06-25 | 2029-06-25 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370058 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC02 | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Accumulator Brake Rear DS | 2029-06-25 | 2029-06-25 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370059 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC03 | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Accumulator Brake Rear ODS | 2029-06-25 | 2029-06-25 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370060 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC04 | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Accumulator Steering DS | 2029-06-25 | 2029-06-25 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370061 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-STRSYS-STACC-SACLH | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5411 | DT5411 Accumulator Steering ODS | 2029-06-25 | 2029-06-25 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370062 | 25.06.2029 | 28000 | CLB-MP-HAUL-DT5411-STRSYS-STACC-SACRH | 6500 | 8255 | 8255 | CLB-MP-HAUL-DT5411-STRSYS-STACC-SACRH90029372
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Brake & Steering Manifold | 2029-06-26 | 2029-06-26 | 12 hrs | FY29 | 24 | 90029368 | A1 | 1000372430 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-BRKSYS-BRVLV | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-BRKSYS-BRVLV90029368
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Gear Cooler Motor & Pump | 2029-06-26 | 2029-06-26 | 6 hrs | FY29 | 6 | 90029363 | A1 | 1000372462 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-FDRSYS-GRSOC-OCPPM | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-FDRSYS-GRSOC-OCPPM90029363
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Pump Airconditioner Drive | 2029-06-26 | 2029-06-26 | 2 hrs | FY29 | 2 | 90029365 | A1 | 1000372468 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-ACPMP | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-ACPMP90029365
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Coupling Drive Pump | 2029-06-26 | 2029-06-26 | 3 hrs | FY29 | 3 | 90029361 | A1 | 1000372469 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-HYDPC | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-HYDPC90029361
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Pump Main Hydraulic | 2029-06-26 | 2029-06-26 | 6 hrs | FY29 | 12 | 90029366 | A1 | 1000372470 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-HYPMP | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-HYPMP90029366
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Cylinder Steering LHS | 2029-06-26 | 2029-06-26 | 8 hrs | FY29 | 14 | 90029373 | A2 | 1000372474 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-STRSYS-STRCY-STCYL | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRSYS-STRCY-STCYL90029373
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Cylinder Steering RHS | 2029-06-26 | 2029-06-26 | 8 hrs | FY29 | 14 | 90029374 | A2 | 1000372475 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-STRSYS-STRCY-STCYR | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRSYS-STRCY-STCYR90029374
T264 | Onsite PM | Haul | Fortescue | DT5488 | DT5488 Repl Valve Flow Amplifier | 2029-06-26 | 2029-06-26 | 2 hrs | FY29 | 2 | 90029367 | A1 | 1000372476 | 26.06.2029 | 20000 | CLB-MP-HAUL-DT5488-STRSYS-STVLV | 6500 | 968 | 968 | CLB-MP-HAUL-DT5488-STRSYS-STVLV90029367
789D | Onsite PM | Haul | Fortescue | DT165 | DT165 Repl Air Dryer | 2029-06-27 | 2029-06-27 | 7 hrs | FY29 | 14 | 90003115 | 1 | 1000034239 | 27.06.2029 | 22000 | CLB-MP-HAUL-DT165 -PNEUMC-AIRDR | 7500 | 78966 | 22268 | CLB-MP-HAUL-DT165 -PNEUMC-AIRDR90003115
789D | Onsite PM | Haul | Fortescue | DT198 | DT198 Repl Tyre Sense Battery | 2029-06-27 | 2029-06-27 | 2 hrs | FY29 | 2 | 90017022 | 1 | 1000163973 | 27.06.2029 | 24 Monthly | CLB-MP-HAUL-DT198 -MANGMT-TYRSN |  |  |  | CLB-MP-HAUL-DT198 -MANGMT-TYRSN90017022
793C | Onsite PM | Haul | Fortescue | PM0004 | PM0004 Operators Seat | 2029-06-27 | 2029-06-27 | 2 hrs | FY29 | 4 | 90013211 | A1 | 1000110271 | 27.06.2029 | 10000 | CLB-MP-SUPP-PM0004-STRUCT-CABIN-SEATS |  |  |  | CLB-MP-SUPP-PM0004-STRUCT-CABIN-SEATS90013211
789D | Onsite PM | Haul | Fortescue | DT185 | DT185 Repl Pump Hoist & Brake | 2029-06-28 | 2029-06-28 | 10 hrs | FY29 | 10 | 90003113 | 1 | 1000035284 | 28.06.2029 | 22000 | CLB-MP-HAUL-DT185 -HYDSYS-HOPMP |  |  |  | CLB-MP-HAUL-DT185 -HYDSYS-HOPMP90003113
785D | Onsite PM | Haul | Fortescue | LL0003 | LL0003 Suspension Cyl LH - Replace | 2029-06-29 | 2029-06-29 | 12 hrs | FY29 | 24 | 90018297 | 1 | 1000174680 | 29.06.2029 | 20000 | CLB-MP-SUPP-LL0003-STRUCT-SUSPN-SUCYL |  |  |  | CLB-MP-SUPP-LL0003-STRUCT-SUSPN-SUCYL90018297
789D | Onsite PM | Haul | Fortescue | DT196 | DT196 Repl Cyl Steering RH | 2029-06-30 | 2029-06-30 | 16 hrs | FY29 | 28 | 90003111 | 3 | 1000035944 | 30.06.2029 | 15000 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYR |  |  |  | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYR90003111
785D | Onsite PM | Haul | Fortescue | PM0006 | PM0006 3Y Air Tank Int Insp & PRV Repl | 2029-06-30 | 2029-06-30 | 4.5 hrs | FY29 | 4.5 | 90038750 | A1 | 1000389211 | 30.06.2029 | 36 Monthly | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK90038750
785D | Onsite PM | Haul | Fortescue | WC011 | WC011 3Y Air Tank Int Insp & PRV Repl | 2029-06-30 | 2029-06-30 | 4.5 hrs | FY29 | 4.5 | 90038750 | A1 | 1000389213 | 30.06.2029 | 36 Monthly | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK |  |  |  | CLB-MP-SUPP-WC011 -PNEUMC-PNTNK90038750
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Blower Main Assembly | 2029-06-30 | 2029-06-30 | 12 hrs | FY29 | 24 | 90029350 | A1 | 1000346708 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-ELCTHV-HVBLW |  |  |  | CLB-MP-HAUL-DT5443-ELCTHV-HVBLW90029350
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Motor Grid Box Blower | 2029-06-30 | 2029-06-30 | 14 hrs | FY29 | 14 | 90029309 | A1 | 1000346704 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-ELCTHV-HVGBM |  |  |  | CLB-MP-HAUL-DT5443-ELCTHV-HVGBM90029309
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Hoist LHS | 2029-06-30 | 2029-06-30 | 14 hrs | FY29 | 26 | 90029356 | A1 | 1000346689 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-HYDSYS-HOCYL-HCYLH |  |  |  | CLB-MP-HAUL-DT5443-HYDSYS-HOCYL-HCYLH90029356
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Hoist RHS | 2029-06-30 | 2029-07-01 | 20 hrs | FY29 | 38 | 90029358 | A1 | 1000346690 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-HYDSYS-HOCYL-HCYRH |  |  |  | CLB-MP-HAUL-DT5443-HYDSYS-HOCYL-HCYRH90029358
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Hoist Manifold | 2029-06-30 | 2029-07-01 | 24 hrs | FY29 | 48 | 90029359 | A1 | 1000346706 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-HYDSYS-HOMAN |  |  |  | CLB-MP-HAUL-DT5443-HYDSYS-HOMAN90029359
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Accumulator Pump Control | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90029360 | A1 | 1000346678 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-HYDSYS-HDACC-PCACC |  |  |  | CLB-MP-HAUL-DT5443-HYDSYS-HDACC-PCACC90029360
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Seat Operator | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 2 | 90029285 | A1 | 1000346710 | 30.06.2029 | 14000 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-SEATS |  |  |  | CLB-MP-HAUL-DT5443-STRUCT-CABIN-SEATS90029285
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Suspension LHF | 2029-06-30 | 2029-07-02 | 42 hrs | FY29 | 118 | 90029376 | A1 | 1000346693 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYLF |  |  |  | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYLF90029376
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Suspension LHR | 2029-06-30 | 2029-07-01 | 36 hrs | FY29 | 108 | 90029379 | A1 | 1000346694 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYLR |  |  |  | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYLR90029379
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Suspension RHF | 2029-06-30 | 2029-07-02 | 42 hrs | FY29 | 118 | 90029378 | A1 | 1000346695 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYRF |  |  |  | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYRF90029378
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Repl Cylinder Suspension RHR | 2029-06-30 | 2029-07-01 | 38 hrs | FY29 | 110 | 90029380 | A1 | 1000346696 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYRR |  |  |  | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYRR90029380
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Accumulator Brake Front DS | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370105 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC01 |  |  |  | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC0190029286
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Accumulator Brake Front ODS | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90029286 | A1 | 1000370106 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC02 |  |  |  | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC0290029286
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Accumulator Brake Rear DS | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370107 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC03 |  |  |  | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC0390029288
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Accumulator Brake Rear ODS | 2029-06-30 | 2029-06-30 | 2 hrs | FY29 | 4 | 90029288 | A1 | 1000370108 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC04 |  |  |  | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC0490029288
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Accumulator Steering DS | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 12 | 90029371 | A1 | 1000370109 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-STRSYS-STACC-SACLH |  |  |  | CLB-MP-HAUL-DT5443-STRSYS-STACC-SACLH90029371
T264 | Onsite PM | Haul | Fortescue | DT5443 | DT5443 Accumulator Steering ODS | 2029-06-30 | 2029-06-30 | 6 hrs | FY29 | 12 | 90029372 | A1 | 1000370110 | 30.06.2029 | 28000 | CLB-MP-HAUL-DT5443-STRSYS-STACC-SACRH |  |  |  | CLB-MP-HAUL-DT5443-STRSYS-STACC-SACRH90029372

## Measurement Points
Measuring point | Functional Location | Description of measuring point | Meas/TotCountrRdg _ | Counter reading | Annual estimate
500147182 | CLB-MP-HAUL-DT164 -STRSYS-STACC | Steering Accumulator Rear | 10955 | 10955 | 7500
500147181 | CLB-MP-HAUL-DT164 -STRSYS-STACC | Steering Accumulator Middle | 10955 | 10955 | 7500
500147180 | CLB-MP-HAUL-DT164 -STRSYS-STACC | Steering Accumulator Front | 10955 | 10955 | 7500
500127345 | CLB-MP-LOAD-WL6103-ENGINE-FUSYS-FULCO | WL6103 Fuel Cooler | 21377 | 5017 | 5000
500119975 | CLB-MP-LOAD-WL6103-HYDSYS-HDTNK | Hydraulic Tank | 21377 | 4623 | 5000
500115262 | CLB-MP-LOAD-WL6103 | Lube & Mechanical Services | 21377 | 21377 | 5000
500115261 | CLB-MP-LOAD-WL6103-TRNSYS-TRTRF | Transmission Transfer Case | 21377 | 21377 | 5000
500115260 | CLB-MP-LOAD-WL6103-TRNSYS-TRQUE | Torque Converter | 21377 | 10927 | 5000
500115259 | CLB-MP-LOAD-WL6103-TRNSYS-TRPMP | Pump Transmission | 21377 | 5580 | 5000
500115258 | CLB-MP-LOAD-WL6103-TRNSYS-TROLC | Transmission Oil Cooler | 21377 | 21377 | 5000
500115257 | CLB-MP-LOAD-WL6103-TRNSYS-TRHLF | Trans System Hoses Lines and Fittings | 21377 | 4623 | 5000
500115256 | CLB-MP-LOAD-WL6103-TRNSYS-TRANS | Transmission | 21377 | 4623 | 5000
500115255 | CLB-MP-LOAD-WL6103-STRUCT-CHASS-LNKGE | Linkage | 21377 | 21377 | 5000
500115254 | CLB-MP-LOAD-WL6103-STRUCT-CHASS-LIARM | Lift Arm | 21377 | 21377 | 5000
500115253 | CLB-MP-LOAD-WL6103-STRUCT-CHASS-LEVER | Lever | 21377 | 21377 | 5000
500115252 | CLB-MP-LOAD-WL6103-STRUCT-CHASS-ARTIC | Articulation | 21377 | 21377 | 5000
500115251 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-SEATS | Operators Seat | 21377 | 1570 | 5000
500115250 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-SBELT | Seat Belt | 21377 | 21377 | 5000
500115249 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 21377 | 21377 | 5000
500115248 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 21377 | 4623 | 5000
500115247 | CLB-MP-LOAD-WL6103-STRUCT-CABIN-AIRCN | Air Conditioning System | 21377 | 4623 | 5000
500115246 | CLB-MP-LOAD-WL6103-STRUCT-BUCKT-BWELM | Bucket Wear Elements GET | 21377 | 21377 | 5000
500115245 | CLB-MP-LOAD-WL6103-STRUCT-BUCKT | Bucket | 21377 | 21377 | 5000
500115244 | CLB-MP-LOAD-WL6103-STRSYS-STRCY-STCYR | Cylinder Steering RH | 21377 | 12966 | 5000
500115243 | CLB-MP-LOAD-WL6103-STRSYS-STRCY-STCYL | Cylinder Steering LH | 21377 | 4623 | 5000
500115242 | CLB-MP-LOAD-WL6103-STRSYS-STPMP-SESPP | Pump Secondary Steering | 21377 | 2840 | 5000
500115241 | CLB-MP-LOAD-WL6103-STRSYS-STPMP | Pumps Steering Centre | 21377 | 4623 | 5000
500115240 | CLB-MP-LOAD-WL6103-STRSYS-STOCO | Oil Cooler Steering | 21377 | 21377 | 5000
500115239 | CLB-MP-LOAD-WL6103-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 21377 | 4623 | 5000
500115238 | CLB-MP-LOAD-WL6103-STRSYS-STCON | Steering Controls | 21377 | 21377 | 5000
500115237 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP06 | Pump Hydraulic Imp RHR | 21377 | 4623 | 5000
500115236 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP05 | Pump Hydraulic Axle Cooler | 21377 | 21377 | 5000
500115235 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP04 | Hyd Imp Pump LHF | 21377 | 4623 | 5000
500115234 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 21377 | 7805 | 5000
500115233 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot & Axle Cooling | 21377 | 4623 | 5000
500115232 | CLB-MP-LOAD-WL6103-HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement RHF | 21377 | 4623 | 5000
500115231 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM03 | Motor Hydraulic Axle Cooler Rear | 21377 | 4623 | 5000
500115230 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM02 | Motor Hydraulic Axle Cooler Front | 21377 | 4623 | 5000
500115229 | CLB-MP-LOAD-WL6103-HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 21377 | 4623 | 5000
500115228 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV04 | Valve Hydraulic | 21377 | 21377 | 5000
500115227 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV03 | Valve Hydraulic | 21377 | 21377 | 5000
500115226 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV02 | Valve Hydraulic | 21377 | 21377 | 5000
500115225 | CLB-MP-LOAD-WL6103-HYDSYS-HDVLV-HYV01 | Valve Hydraulic | 21377 | 21377 | 5000
500115224 | CLB-MP-LOAD-WL6103-HYDSYS-HDOCO | Oil Cooler Hydraulic | 21377 | 4623 | 5000
500115221 | CLB-MP-LOAD-WL6103-HYDSYS-HDHLF-PILHO | Pilot System Hoses | 21377 | 4623 | 5000
500115220 | CLB-MP-LOAD-WL6103-HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 21377 | 4623 | 5000
500115219 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH | 21377 | 9901 | 5000
500115218 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH | 21377 | 9901 | 5000
500115217 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 21377 | 9436 | 5000
500115216 | CLB-MP-LOAD-WL6103-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 21377 | 8494 | 5000
500115215 | CLB-MP-LOAD-WL6103-GRSYST-GRINJ | Auto Lube Injectors | 21377 | 21377 | 5000
500115214 | CLB-MP-LOAD-WL6103-GRSYST-ALBPP | Auto Lube Pump | 21377 | 21377 | 5000
500115213 | CLB-MP-LOAD-WL6103-GRSYST | Auto Lube System Service | 21377 | 4623 | 5000
500115212 | CLB-MP-LOAD-WL6103-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 21377 | 21377 | 5000
500115211 | CLB-MP-LOAD-WL6103-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 21377 | 21377 | 5000
500115210 | CLB-MP-LOAD-WL6103-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 21377 | 21377 | 5000
500115209 | CLB-MP-LOAD-WL6103-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 21377 | 21377 | 5000
500115208 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF-TRNON | Trunnions Rear Axle Oscillation | 21377 | 21377 | 5000
500115207 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF | Rear Axle Oscillation Group | 21377 | 21377 | 5000
500115206 | CLB-MP-LOAD-WL6103-FDRSYS-RRDIF | Rear Differential | 21377 | 21377 | 5000
500115205 | CLB-MP-LOAD-WL6103-FDRSYS-HDOCA-HYOCR | Oil Cooler Axle Rear | 21377 | 4623 | 5000
500115204 | CLB-MP-LOAD-WL6103-FDRSYS-HDOCA-HYOCF | Oil Cooler Axle Front | 21377 | 4623 | 5000
500115203 | CLB-MP-LOAD-WL6103-FDRSYS-FRDIF | Front Differential | 21377 | 21377 | 5000
500115202 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 21377 | 21377 | 5000
500115201 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 21377 | 21377 | 5000
500115200 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 21377 | 21377 | 5000
500115199 | CLB-MP-LOAD-WL6103-FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 21377 | 21377 | 5000
500115198 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 21377 | 9436 | 5000
500115197 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 21377 | 670 | 5000
500115196 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 21377 | 4623 | 5000
500115195 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-SHT01 | Drive Shaft TC to Transmission | 21377 | 4623 | 5000
500115194 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT-CTRBR | Centre Bearing Drive Shaft | 21377 | 9436 | 5000
500115193 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT | Input Drive Shafts Group | 21377 | 21377 | 5000
500115192 | CLB-MP-LOAD-WL6103-FDRSYS-DRSHT | Drive Shafts Group | 21377 | 21377 | 5000
500115191 | CLB-MP-LOAD-WL6103-ENGINE-LUBSY-OILPP | Oil Pump Engine | 21377 | 6697 | 5000
500115190 | CLB-MP-LOAD-WL6103-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 21377 | 6697 | 5000
500115189 | CLB-MP-LOAD-WL6103-ENGINE-INTEX-TBORH | Turbocharger RH | 21377 | 6697 | 5000
500115188 | CLB-MP-LOAD-WL6103-ENGINE-INTEX-TBOLH | Turbocharger LH | 21377 | 6697 | 5000
500115187 | CLB-MP-LOAD-WL6103-ENGINE-INTEX-EXHST | Exhaust Mufflers | 21377 | 6697 | 5000
500115186 | CLB-MP-LOAD-WL6103-ENGINE-INTEX-AFTER | Aftercooler Engine | 21377 | 6697 | 5000
500115185 | CLB-MP-LOAD-WL6103-ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 21377 | 6697 | 5000
500115184 | CLB-MP-LOAD-WL6103-ENGINE-FUSYS-FULPP | Fuel Transfer Pump | 21377 | 6697 | 5000
500115183 | CLB-MP-LOAD-WL6103-ENGINE-FUSYS-FUINJ | Fuel Injectors | 21377 | 6697 | 5000
500115182 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-WTRPP | Water Pump Engine | 21377 | 6697 | 5000
500115181 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-THERM | ThermostatsRegulators | 21377 | 6697 | 5000
500115180 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-RADTR | Coolant Engine | 21364 | 6684 | 5000
500115179 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-RADTR | Radiator Engine | 21372 | 4623 | 5000
500115178 | CLB-MP-LOAD-WL6103-ENGINE-COSYS-COFAN | Fan Cooling System | 21377 | 6697 | 5000
500115176 | CLB-MP-LOAD-WL6103-ENGINE | Engine Assembly Caterpillar C32 | 21377 | 6697 | 5000
500115175 | CLB-MP-LOAD-WL6103-ELCTLV-START-STMRH | Starter Motor Upper | 21377 | 13468 | 5000
500115174 | CLB-MP-LOAD-WL6103-ELCTLV-START-STMLH | Starter Motor Lower | 21377 | 13468 | 5000
500115173 | CLB-MP-LOAD-WL6103-ELCTLV-HARNS | Electrical Harnesses | 21377 | 4623 | 5000
500115172 | CLB-MP-LOAD-WL6103-ELCTLV-CHARG-ALTER | Alternator 24V | 21377 | 13468 | 5000
500115171 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 21377 | 21377 | 5000
500115170 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 21377 | 21377 | 5000
500115169 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 21377 | 21377 | 5000
500115168 | CLB-MP-LOAD-WL6103-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 21377 | 21377 | 5000
500115167 | CLB-MP-LOAD-WL6103-BRKSYS-BRPRK | Park Brake Assembly | 21377 | 21377 | 5000
500115166 | CLB-MP-LOAD-WL6103-BRKSYS-BRPMP | Pump Brake | 21377 | 4623 | 5000
500115165 | CLB-MP-LOAD-WL6103-BRKSYS-BRHLF | Brake System Hoses | 21377 | 4623 | 5000
500115164 | CLB-MP-LOAD-WL6103-BRKSYS-BRACC-ACC02 | Accumulator Brake Right | 21377 | 21377 | 5000
500115163 | CLB-MP-LOAD-WL6103-BRKSYS-BRACC-ACC01 | Accumulator Brake Left | 21377 | 21377 | 5000
500115162 | CLB-MP-LOAD-WL6103 | Caterpillar 993K Wheel Loader WL6103 | 21377 | 21377 | 5000
500150699 | CLB-MP-LOAD-WL6102-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 23295 | 7003 | 5000
500127344 | CLB-MP-LOAD-WL6102-ENGINE-FUSYS-FULCO | WL6102 FUEL COOLER | 23283 | 3697 | 5000
500119974 | CLB-MP-LOAD-WL6102-HYDSYS-HDTNK | Hydraulic Tank | 23283 | 7168 | 5000
500115161 | CLB-MP-LOAD-WL6102 | Lube & Mechanical Services | 23283 | 23283 | 5000
500115160 | CLB-MP-LOAD-WL6102-TRNSYS-TRTRF | Transmission Transfer Case | 23283 | 23283 | 5000
500115159 | CLB-MP-LOAD-WL6102-TRNSYS-TRQUE | Torque Converter | 23283 | 8781 | 5000
500115158 | CLB-MP-LOAD-WL6102-TRNSYS-TRPMP | Pump Transmission | 23283 | 7168 | 5000
500115157 | CLB-MP-LOAD-WL6102-TRNSYS-TROLC | Transmission Oil Cooler | 23283 | 23283 | 5000
500115156 | CLB-MP-LOAD-WL6102-TRNSYS-TRHLF | Trans System Hoses Lines and Fittings | 23283 | 7168 | 5000
500115155 | CLB-MP-LOAD-WL6102-TRNSYS-TRANS | Transmission | 23283 | 7168 | 5000
500115154 | CLB-MP-LOAD-WL6102-STRUCT-CHASS-LNKGE | Linkage | 23283 | 23283 | 5000
500115153 | CLB-MP-LOAD-WL6102-STRUCT-CHASS-LIARM | Lift Arm | 23283 | 7168 | 5000
500115152 | CLB-MP-LOAD-WL6102-STRUCT-CHASS-LEVER | Lever | 23283 | 23283 | 5000
500115151 | CLB-MP-LOAD-WL6102-STRUCT-CHASS-ARTIC | Articulation | 23283 | 7168 | 5000
500115150 | CLB-MP-LOAD-WL6102-STRUCT-CABIN-SEATS | Operators Seat | 23283 | 7168 | 5000
500115149 | CLB-MP-LOAD-WL6102-STRUCT-CABIN-SBELT | Seat Belt | 23283 | 23283 | 5000
500115148 | CLB-MP-LOAD-WL6102-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 23283 | 23283 | 5000
500115147 | CLB-MP-LOAD-WL6102-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 23283 | 7168 | 5000
500115146 | CLB-MP-LOAD-WL6102-STRUCT-CABIN-AIRCN | Air Conditioning System | 23283 | 7168 | 5000
500115145 | CLB-MP-LOAD-WL6102-STRUCT-BUCKT-BWELM | Bucket Wear Elements GET | 23283 | 23283 | 5000
500115144 | CLB-MP-LOAD-WL6102-STRUCT-BUCKT | Bucket | 23283 | 23283 | 5000
500115143 | CLB-MP-LOAD-WL6102-STRSYS-STRCY-STCYR | Cylinder Steering RH | 23283 | 7168 | 5000
500115142 | CLB-MP-LOAD-WL6102-STRSYS-STRCY-STCYL | Cylinder Steering LH | 23283 | 7168 | 5000
500115141 | CLB-MP-LOAD-WL6102-STRSYS-STPMP-SESPP | Pump Secondary Steering | 23283 | 6689 | 5000
500115140 | CLB-MP-LOAD-WL6102-STRSYS-STPMP | Pumps Steering Centre | 23283 | 7168 | 5000
500115139 | CLB-MP-LOAD-WL6102-STRSYS-STOCO | Oil Cooler Steering | 23283 | 23283 | 5000
500115138 | CLB-MP-LOAD-WL6102-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 23283 | 7168 | 5000
500115137 | CLB-MP-LOAD-WL6102-STRSYS-STCON | Steering Controls | 23283 | 23283 | 5000
500115136 | CLB-MP-LOAD-WL6102-HYDSYS-HYDPP-HYP06 | Pump Hydraulic Imp RHR | 23283 | 7168 | 5000
500115135 | CLB-MP-LOAD-WL6102-HYDSYS-HYDPP-HYP05 | Pump Hydraulic Axle Cooler | 23283 | 23283 | 5000
500115134 | CLB-MP-LOAD-WL6102-HYDSYS-HYDPP-HYP04 | Hyd Imp Pump LHF | 23283 | 7168 | 5000
500115133 | CLB-MP-LOAD-WL6102-HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 23283 | 7168 | 5000
500115132 | CLB-MP-LOAD-WL6102-HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot & Axle Cooling | 23283 | 7168 | 5000
500115131 | CLB-MP-LOAD-WL6102-HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement RHF | 23283 | 7168 | 5000
500115130 | CLB-MP-LOAD-WL6102-HYDSYS-HYDMT-HYM03 | Motor Hydraulic Axle Cooler Rear | 23283 | 7168 | 5000
500115129 | CLB-MP-LOAD-WL6102-HYDSYS-HYDMT-HYM02 | Motor Hydraulic Axle Cooler Front | 23283 | 7168 | 5000
500115128 | CLB-MP-LOAD-WL6102-HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 23283 | 1718 | 5000
500115127 | CLB-MP-LOAD-WL6102-HYDSYS-HDVLV-HYV04 | Valve Hydraulic | 23283 | 23283 | 5000
500115126 | CLB-MP-LOAD-WL6102-HYDSYS-HDVLV-HYV03 | Valve Hydraulic | 23283 | 23283 | 5000
500115125 | CLB-MP-LOAD-WL6102-HYDSYS-HDVLV-HYV02 | Valve Hydraulic | 23283 | 23283 | 5000
500115124 | CLB-MP-LOAD-WL6102-HYDSYS-HDVLV-HYV01 | Valve Hydraulic | 23283 | 23283 | 5000
500115123 | CLB-MP-LOAD-WL6102-HYDSYS-HDOCO | Oil Cooler Hydraulic | 23283 | 7168 | 5000
500115120 | CLB-MP-LOAD-WL6102-HYDSYS-HDHLF-PILHO | Pilot System Hoses | 23283 | 7168 | 5000
500115119 | CLB-MP-LOAD-WL6102-HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 23283 | 7168 | 5000
500115118 | CLB-MP-LOAD-WL6102-HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH | 23283 | 10041 | 5000
500115117 | CLB-MP-LOAD-WL6102-HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH | 23283 | 7168 | 5000
500115116 | CLB-MP-LOAD-WL6102-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 23283 | 7168 | 5000
500115115 | CLB-MP-LOAD-WL6102-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 23283 | 13868 | 5000
500115114 | CLB-MP-LOAD-WL6102-GRSYST-GRINJ | Auto Lube Injectors | 23283 | 23283 | 5000
500115113 | CLB-MP-LOAD-WL6102-GRSYST-ALBPP | Auto Lube Pump | 23283 | 23283 | 5000
500115112 | CLB-MP-LOAD-WL6102-GRSYST | Auto Lube System Service | 23283 | 7168 | 5000
500115111 | CLB-MP-LOAD-WL6102-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 23283 | 23283 | 5000
500115110 | CLB-MP-LOAD-WL6102-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 23283 | 23283 | 5000
500115109 | CLB-MP-LOAD-WL6102-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 23283 | 23283 | 5000
500115108 | CLB-MP-LOAD-WL6102-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 23283 | 23283 | 5000
500115107 | CLB-MP-LOAD-WL6102-FDRSYS-RRDIF-TRNON | Trunnions Rear Axle Oscillation | 23283 | 7168 | 5000
500115106 | CLB-MP-LOAD-WL6102-FDRSYS-RRDIF | Rear Axle Oscillation Group | 23283 | 23283 | 5000
500115105 | CLB-MP-LOAD-WL6102-FDRSYS-RRDIF | Rear Differential | 23283 | 23283 | 5000
500115104 | CLB-MP-LOAD-WL6102-FDRSYS-HDOCA-HYOCR | Oil Cooler Axle Rear | 23283 | 7168 | 5000
500115103 | CLB-MP-LOAD-WL6102-FDRSYS-HDOCA-HYOCF | Oil Cooler Axle Front | 23283 | 7168 | 5000
500115102 | CLB-MP-LOAD-WL6102-FDRSYS-FRDIF | Front Differential | 23283 | 23283 | 5000
500115101 | CLB-MP-LOAD-WL6102-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 23283 | 23283 | 5000
500115100 | CLB-MP-LOAD-WL6102-FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 23283 | 23283 | 5000
500115099 | CLB-MP-LOAD-WL6102-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 23283 | 23283 | 5000
500115098 | CLB-MP-LOAD-WL6102-FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 23283 | 2753 | 5000
500115097 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 23283 | 7168 | 5000
500115096 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 23283 | 8781 | 5000
500115095 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 23283 | 7168 | 5000
500115094 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT-SHT01 | Drive Shaft TC to Transmission | 23283 | 7168 | 5000
500115093 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT-CTRBR | Centre Bearing Drive Shaft | 23283 | 7168 | 5000
500115092 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT | Input Drive Shafts Group | 23283 | 23283 | 5000
500115091 | CLB-MP-LOAD-WL6102-FDRSYS-DRSHT | Drive Shafts Group | 23283 | 23283 | 5000
500115090 | CLB-MP-LOAD-WL6102-ENGINE-LUBSY-OILPP | Oil Pump Engine | 23283 | 7168 | 5000
500115089 | CLB-MP-LOAD-WL6102-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 23283 | 23283 | 5000
500115088 | CLB-MP-LOAD-WL6102-ENGINE-INTEX-TBORH | Turbocharger RH | 23283 | 7168 | 5000
500115087 | CLB-MP-LOAD-WL6102-ENGINE-INTEX-TBOLH | Turbocharger LH | 23283 | 7168 | 5000
500115086 | CLB-MP-LOAD-WL6102-ENGINE-INTEX-EXHST | Exhaust Mufflers | 23283 | 23283 | 5000
500115085 | CLB-MP-LOAD-WL6102-ENGINE-INTEX-AFTER | Aftercooler Engine | 23283 | 23283 | 5000
500115084 | CLB-MP-LOAD-WL6102-ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 23283 | 23283 | 5000
500115083 | CLB-MP-LOAD-WL6102-ENGINE-FUSYS-FULPP | Fuel Transfer Pump | 23283 | 7168 | 5000
500115082 | CLB-MP-LOAD-WL6102-ENGINE-FUSYS-FUINJ | Fuel Injectors | 23283 | 7168 | 5000
500115081 | CLB-MP-LOAD-WL6102-ENGINE-COSYS-WTRPP | Water Pump Engine | 23283 | 7168 | 5000
500115080 | CLB-MP-LOAD-WL6102-ENGINE-COSYS-THERM | ThermostatsRegulators | 23283 | 7168 | 5000
500115079 | CLB-MP-LOAD-WL6102-ENGINE-COSYS-RADTR | Coolant Engine | 23283 | 23283 | 5000
500115078 | CLB-MP-LOAD-WL6102-ENGINE-COSYS-RADTR | Radiator Engine | 23283 | 7168 | 5000
500115077 | CLB-MP-LOAD-WL6102-ENGINE-COSYS-COFAN | Fan Cooling System | 23283 | 1718 | 5000
500115075 | CLB-MP-LOAD-WL6102-ENGINE | Engine Assembly Caterpillar C32 | 23283 | 7168 | 5000
500115074 | CLB-MP-LOAD-WL6102-ELCTLV-START-STMRH | Starter Motor Upper | 23283 | 7168 | 5000
500115073 | CLB-MP-LOAD-WL6102-ELCTLV-START-STMLH | Starter Motor Lower | 23283 | 7168 | 5000
500115072 | CLB-MP-LOAD-WL6102-ELCTLV-HARNS | Electrical Harnesses | 23283 | 7168 | 5000
500115071 | CLB-MP-LOAD-WL6102-ELCTLV-CHARG-ALTER | Alternator 24V | 23283 | 1565 | 5000
500115070 | CLB-MP-LOAD-WL6102-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 23283 | 23283 | 5000
500115069 | CLB-MP-LOAD-WL6102-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 23283 | 23283 | 5000
500115068 | CLB-MP-LOAD-WL6102-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 23283 | 23283 | 5000
500115067 | CLB-MP-LOAD-WL6102-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 23283 | 23283 | 5000
500115066 | CLB-MP-LOAD-WL6102-BRKSYS-BRPRK | Park Brake Assembly | 23283 | 23283 | 5000
500115065 | CLB-MP-LOAD-WL6102-BRKSYS-BRPMP | Pump Brake | 23283 | 7168 | 5000
500115064 | CLB-MP-LOAD-WL6102-BRKSYS-BRHLF | Brake System Hoses | 23283 | 7168 | 5000
500115063 | CLB-MP-LOAD-WL6102-BRKSYS-BRACC-ACC02 | Accumulator Brake Right | 23283 | 23283 | 5000
500115062 | CLB-MP-LOAD-WL6102-BRKSYS-BRACC-ACC01 | Accumulator Brake Left | 23283 | 23283 | 5000
500115061 | CLB-MP-LOAD-WL6102 | Caterpillar 993K Wheel Loader WL6102 | 23283 | 23283 | 5000
500150698 | CLB-MP-LOAD-WL265 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 65139 | 12209 | 6000
500148509 | CLB-MP-LOAD-WL265 -BRKSYS-BRACC | Brake Accumulator RH | 65007 | 22108 | 6000
500148508 | CLB-MP-LOAD-WL265 -BRKSYS-BRACC | Brake Accumulator LH | 65007 | 22108 | 6000
500102513 | CLB-MP-LOAD-WL265 -TRNSYS-TRTRF | Transmission Transfer Case | 65007 | 5751 | 6000
500079118 | CLB-MP-LOAD-WL265 -GRSYST-FFGHO | Front Frame - Grease Hoses | 65007 | 1947 | 6000
500077976 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 65007 | 9745 | 6000
500077975 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 65007 | 9745 | 6000
500077974 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 65007 | 9745 | 6000
500077973 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 65007 | 9745 | 6000
500073569 | CLB-MP-LOAD-WL265 -PNEUMC | Main Airhoses/Relay | 65007 | 65007 | 6000
500067437 | CLB-MP-LOAD-WL265 -STRSYS-STTNK | Stering and brake tank | 65007 | 1947 | 6000
500063978 | CLB-MP-LOAD-WL265 -ELCTLV-HARNS | Electrical Harness Low Voltage | 65007 | 1947 | 6000
500063142 | CLB-MP-LOAD-WL265 -TRNSYS-TRQUE | Torque Converter | 65007 | 5751 | 6000
500063141 | CLB-MP-LOAD-WL265 -TRNSYS-TRPMP | Transmission Charge Pump | 65007 | 5751 | 6000
500063140 | CLB-MP-LOAD-WL265 -TRNSYS-TROLC | Transmission Oil Cooler | 65007 | 1947 | 6000
500063139 | CLB-MP-LOAD-WL265 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 65007 | 5714 | 6000
500063138 | CLB-MP-LOAD-WL265 -TRNSYS-TRHLF | "Trans System Hoses, Lines and Fittings" | 65007 | 65007 | 6000
500063137 | CLB-MP-LOAD-WL265 -TRNSYS-TRANS | Transmission | 65007 | 9745 | 6000
500063136 | CLB-MP-LOAD-WL265 -TRNSYS-PMPDR-RRPDR | Pump Drive Gearbox Rear | 65007 | 1947 | 6000
500063135 | CLB-MP-LOAD-WL265 -TRNSYS-PMPDR-FRPDR | Pump Drive Gearbox Front | 65007 | 9745 | 6000
500063134 | CLB-MP-LOAD-WL265 -TRNSYS-PMPDR | Pump Drive Gearboxes | 65007 | 65007 | 6000
500063133 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-UCTRB | D-Shaft Upper Centre Bearing | 65007 | 1947 | 6000
500063132 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-TORCP | D-Shaft Torsional Coupling | 65007 | 1947 | 6000
500063131 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 65007 | 11195 | 6000
500063130 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 65007 | 11195 | 6000
500063129 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT04 | D-Shaft Cntr Bearing to Front Diff | 65007 | 11195 | 6000
500063128 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT03 | D-Shaft Transmission to Cntr Bearing | 65007 | 9745 | 6000
500063127 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT02 | D-Shaft Transmission to Rear Diff | 65007 | 9745 | 6000
500063126 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-SHT01 | D-Shaft T/C to Transmission | 65007 | 13203 | 6000
500063125 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT-LCTRB | D-Shaft Lower Centre Bearing | 65007 | 1947 | 6000
500063124 | CLB-MP-LOAD-WL265 -TRNSYS-DRSHT | Drive Shafts | 65007 | 65007 | 6000
500063123 | CLB-MP-LOAD-WL265 -TRNSYS | Transmission System | 65007 | 65007 | 6000
500063122 | CLB-MP-LOAD-WL265 -STRUCT-STLAD | Steps and Ladders | 65007 | 65007 | 6000
500063121 | CLB-MP-LOAD-WL265 -STRUCT-PNLGU | Panels and Guards | 65007 | 65007 | 6000
500063120 | CLB-MP-LOAD-WL265 -STRUCT-PLHAN | Platforms and Handrails | 65007 | 65007 | 6000
500063119 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-ROPSS | Chassis Rollover Protective Structure | 65007 | 65007 | 6000
500063118 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-REFRM | Chassis Rear Frame | 65007 | 65007 | 6000
500063117 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-LNKGE | Chassis Linkage | 65007 | 6057 | 6000
500063116 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-LIARM | Chassis Lift Arm | 65007 | 6057 | 6000
500063115 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-LEVER | Chassis Lever | 65007 | 6057 | 6000
500063114 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-FRFRM | Chassis Front Frame | 65007 | 65007 | 6000
500063113 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-CWEIG | Chassis Counterweight | 65007 | 65007 | 6000
500063112 | CLB-MP-LOAD-WL265 -STRUCT-CHASS-ARTIC | Chassis Articulation | 65007 | 5714 | 6000
500063111 | CLB-MP-LOAD-WL265 -STRUCT-CHASS | Chassis | 65007 | 65007 | 6000
500063110 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-SEATS | Cabin Operators Seat | 65007 | 1947 | 6000
500063109 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-SBELT | Cabin Seat Belt | 65007 | 65007 | 6000
500063108 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-GLASS | Cabin Glass | 65007 | 65007 | 6000
500063107 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 65007 | 65007 | 6000
500063106 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-CABES | Cabin Entertainment System | 65007 | 65007 | 6000
500063105 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-CABCO | Cabin Controls | 65007 | 65007 | 6000
500063104 | CLB-MP-LOAD-WL265 -STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 65007 | 1947 | 6000
500063103 | CLB-MP-LOAD-WL265 -STRUCT-CABIN | Cabin Operators | 65007 | 65007 | 6000
500063102 | CLB-MP-LOAD-WL265 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 65007 | 65007 | 6000
500063101 | CLB-MP-LOAD-WL265 -STRUCT-BUCKT | Bucket | 65007 | 6057 | 6000
500063100 | CLB-MP-LOAD-WL265 -STRUCT | Structure | 65007 | 65007 | 6000
500063099 | CLB-MP-LOAD-WL265 -STRSYS-STVLV | Steering Valve | 65007 | 65007 | 6000
500063098 | CLB-MP-LOAD-WL265 -STRSYS-STTNK | Steering and Brake Oil Tank | 65007 | 1947 | 6000
500063097 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYR | Steering Cylinder RH | 65007 | 9745 | 6000
500063096 | CLB-MP-LOAD-WL265 -STRSYS-STRCY-STCYL | Steering Cylinder LH | 65007 | 1947 | 6000
500063095 | CLB-MP-LOAD-WL265 -STRSYS-STRCY | Steering Cylinder | 65007 | 65007 | 6000
500063094 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 65007 | 5751 | 6000
500063093 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 65007 | 30560 | 6000
500063092 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP02 | Steering Pump RH | 65007 | 1947 | 6000
500063091 | CLB-MP-LOAD-WL265 -STRSYS-STPMP-STP01 | Steering Pump LH | 65007 | 1947 | 6000
500063090 | CLB-MP-LOAD-WL265 -STRSYS-STPMP | Steering System Pumps | 65007 | 65007 | 6000
500063089 | CLB-MP-LOAD-WL265 -STRSYS-STNVS | Steering Neutralizer Valves | 65007 | 33878 | 6000
500063088 | CLB-MP-LOAD-WL265 -STRSYS-STIPV | Steering STIC Pilot Valve | 65007 | 29221 | 6000
500063087 | CLB-MP-LOAD-WL265 -STRSYS-STHLF-STRHO | Steering System Hoses | 65007 | 1947 | 6000
500063086 | CLB-MP-LOAD-WL265 -STRSYS-STHLF | Steering System Hoses and Fittings | 65007 | 65007 | 6000
500063085 | CLB-MP-LOAD-WL265 -STRSYS-STBOC | Steering And Brake Oil Cooler | 65007 | 65007 | 6000
500063084 | CLB-MP-LOAD-WL265 -STRSYS | Steering System | 65007 | 65007 | 6000
500063083 | CLB-MP-LOAD-WL265 -PNEUMC-START | Pneumatic Starter Motor | 65007 | 1947 | 6000
500063082 | CLB-MP-LOAD-WL265 -PNEUMC-PNTNK-AIT03 | Pneumatic Air Tank Expansion RH | 65007 | 65007 | 6000
500063081 | CLB-MP-LOAD-WL265 -PNEUMC-PNTNK-AIT02 | Pneumatic Tank Expansion LH | 65007 | 65007 | 6000
500063080 | CLB-MP-LOAD-WL265 -PNEUMC-PNTNK-AIT01 | Pneumatic Tank Main Starting | 65007 | 65007 | 6000
500063079 | CLB-MP-LOAD-WL265 -PNEUMC-PNTNK | Pneumatic System Tanks | 65007 | 65007 | 6000
500063078 | CLB-MP-LOAD-WL265 -PNEUMC-PNHLF | Pneumatic System Hoses & Fittings | 65007 | 1947 | 6000
500063077 | CLB-MP-LOAD-WL265 -PNEUMC | Pneumatic System | 65007 | 65007 | 6000
500063076 | CLB-MP-LOAD-WL265 -MANGMT-UMMMC | Management Mine Monitoring and Control | 65007 | 65007 | 6000
500063075 | CLB-MP-LOAD-WL265 -MANGMT-UMMC | Management Machine System | 65007 | 65007 | 6000
500063074 | CLB-MP-LOAD-WL265 -MANGMT-UMENG | Management Engine System | 65007 | 65007 | 6000
500063073 | CLB-MP-LOAD-WL265 -MANGMT | Unit Management | 65007 | 65007 | 6000
500063072 | CLB-MP-LOAD-WL265 -HYDSYS-PACCM | Hydraulic Pilot Accumulator | 65007 | 1947 | 6000
500063071 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP04 | Hydraulic Pump Pilot & Cooling | 65007 | 1947 | 6000
500063070 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP03 | Hydraulic Pump Implement Centre | 65007 | 6057 | 6000
500063069 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP02 | Hydraulic Pump Implement RH | 65007 | 1947 | 6000
500063068 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP-HYP01 | Hydraulic Pump Implement LH | 65007 | 6057 | 6000
500063067 | CLB-MP-LOAD-WL265 -HYDSYS-HYDPP | Hydraulic Pumps | 65007 | 65007 | 6000
500063066 | CLB-MP-LOAD-WL265 -HYDSYS-HDVLV-HYV02 | Hydraulic Valve Implement Control RH | 65007 | 1947 | 6000
500063065 | CLB-MP-LOAD-WL265 -HYDSYS-HDVLV-HYV01 | Hydraulic Valve Implement Control LH | 65007 | 1947 | 6000
500063064 | CLB-MP-LOAD-WL265 -HYDSYS-HDVLV | Hydraulic Valves | 65007 | 65007 | 6000
500063063 | CLB-MP-LOAD-WL265 -HYDSYS-HDTNK-HYT03 | Hydraulic Tank Expansion RH | 65007 | 65007 | 6000
500063062 | CLB-MP-LOAD-WL265 -HYDSYS-HDTNK-HYT02 | Hydraulic Tank Expansion LH | 65007 | 65007 | 6000
500063061 | CLB-MP-LOAD-WL265 -HYDSYS-HDTNK-HYT01 | Hydraulic Tank Main | 65007 | 1947 | 6000
500063060 | CLB-MP-LOAD-WL265 -HYDSYS-HDTNK | Hydraulic Oil Tanks | 65007 | 65007 | 6000
500063059 | CLB-MP-LOAD-WL265 -HYDSYS-HDOCO | Hydraulic Oil Cooler | 65007 | 15666 | 6000
500063058 | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 65007 | 1947 | 6000
500063057 | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 65007 | 1947 | 6000
500063056 | CLB-MP-LOAD-WL265 -HYDSYS-HDHLF | Hydraulic System Hoses & Fittings | 65007 | 65007 | 6000
500063055 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 65007 | 1947 | 6000
500063054 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 65007 | 1947 | 6000
500063053 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 65007 | 548 | 6000
500063052 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 65007 | 1947 | 6000
500063051 | CLB-MP-LOAD-WL265 -HYDSYS-HDCYL | Hydraulic Cylinders | 65007 | 65007 | 6000
500063050 | CLB-MP-LOAD-WL265 -HYDSYS | Hydraulic System | 65007 | 65007 | 6000
500063049 | CLB-MP-LOAD-WL265 -GRSYST-GRTNK | Grease Resevoir | 65007 | 65007 | 6000
500063048 | CLB-MP-LOAD-WL265 -GRSYST-GRINJ | Grease Injectors | 65007 | 65007 | 6000
500063047 | CLB-MP-LOAD-WL265 -GRSYST-ALHLF | Grease Auto Lube Hoses & Fittings | 65007 | 65007 | 6000
500063046 | CLB-MP-LOAD-WL265 -GRSYST-ALELC | Grease Auto Lube Electrical | 65007 | 65007 | 6000
500063045 | CLB-MP-LOAD-WL265 -GRSYST-ALCON | Grease Auto Lube Controller | 65007 | 65007 | 6000
500063044 | CLB-MP-LOAD-WL265 -GRSYST-ALBPP | Grease Auto Lube Pump | 65007 | 1947 | 6000
500063043 | CLB-MP-LOAD-WL265 -GRSYST | Grease Lubrication System | 65007 | 65007 | 6000
500063042 | CLB-MP-LOAD-WL265 -FRSUPP-FSMAN-EXTIN | Fire Suppression Hand Held Extinguisher | 65007 | 65007 | 6000
500063041 | CLB-MP-LOAD-WL265 -FRSUPP-FSMAN | Fire Suppression Manual | 65007 | 65007 | 6000
500063040 | CLB-MP-LOAD-WL265 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 65007 | 65007 | 6000
500063039 | CLB-MP-LOAD-WL265 -FRSUPP-FSAUT | Fire Suppression Automatic | 65007 | 65007 | 6000
500063038 | CLB-MP-LOAD-WL265 -FRSUPP-FSALM | Fire Suppression System Alarm | 65007 | 65007 | 6000
500063037 | CLB-MP-LOAD-WL265 -FRSUPP | Fire Suppression System | 65007 | 1947 | 6000
500063036 | CLB-MP-LOAD-WL265 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 65007 | 65007 | 6000
500063035 | CLB-MP-LOAD-WL265 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 65007 | 65007 | 6000
500063034 | CLB-MP-LOAD-WL265 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 65007 | 65007 | 6000
500063033 | CLB-MP-LOAD-WL265 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 65007 | 65007 | 6000
500063032 | CLB-MP-LOAD-WL265 -FDRSYS-WHTYR | Wheels & Tyres and Rims | 65007 | 65007 | 6000
500063031 | CLB-MP-LOAD-WL265 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 65007 | 1947 | 6000
500063030 | CLB-MP-LOAD-WL265 -FDRSYS-RRDIF | Rear Differential | 65007 | 1947 | 6000
500063029 | CLB-MP-LOAD-WL265 -FDRSYS-FRDIF | Front Differential | 65007 | 1947 | 6000
500063028 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 65007 | 1947 | 6000
500063027 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 65007 | 1947 | 6000
500063026 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 65007 | 7321 | 6000
500063025 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 65007 | 6057 | 6000
500063024 | CLB-MP-LOAD-WL265 -FDRSYS-FDRVE | Final Drives | 65007 | 65007 | 6000
500063023 | CLB-MP-LOAD-WL265 -FDRSYS | Final Drive System | 65007 | 65007 | 6000
500063022 | CLB-MP-LOAD-WL265 -ENGINE-LUBSY-PREPP | Engine Prelube Oil Pump | 65007 | 1947 | 6000
500063021 | CLB-MP-LOAD-WL265 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 65007 | 55366 | 6000
500063020 | CLB-MP-LOAD-WL265 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 65007 | 65007 | 6000
500063019 | CLB-MP-LOAD-WL265 -ENGINE-LUBSY | Engine Lubrication System | 65007 | 65007 | 6000
500063018 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-TBORR | Engine Turbocharger RH Rear | 65007 | 1947 | 6000
500063017 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-TBORF | Engine Turbocharger RH Front | 65007 | 1947 | 6000
500063016 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-TBOLR | Engine Turbocharger LH Rear | 65007 | 1947 | 6000
500063015 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-TBOLF | Engine Turbocharger LH Front | 65007 | 1947 | 6000
500063014 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-EXHST | Engine Exhaust System | 65007 | 65007 | 6000
500063013 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-AIRFL | Engine Air Filtration System | 65007 | 41567 | 6000
500063012 | CLB-MP-LOAD-WL265 -ENGINE-INTEX-AFTER | Engine Aftercooler | 65007 | 65007 | 6000
500063011 | CLB-MP-LOAD-WL265 -ENGINE-INTEX | Engine Intake and Exhaust System | 65007 | 65007 | 6000
500063010 | CLB-MP-LOAD-WL265 -ENGINE-FUSYS-FULTP | Engine Fuel Transfer Pump | 65007 | 1947 | 6000
500063009 | CLB-MP-LOAD-WL265 -ENGINE-FUSYS-FULTK | Engine Fuel Tank | 65007 | 65007 | 6000
500063008 | CLB-MP-LOAD-WL265 -ENGINE-FUSYS-FULPP | Engine Fuel Priming Pump | 65007 | 55366 | 6000
500063007 | CLB-MP-LOAD-WL265 -ENGINE-FUSYS-FUINJ | Engine Fuel Injectors | 65007 | 1947 | 6000
500063006 | CLB-MP-LOAD-WL265 -ENGINE-FUSYS-FUHLF | Engine Fuel System Hoses and Fittings | 65007 | 65007 | 6000
500063005 | CLB-MP-LOAD-WL265 -ENGINE-FUSYS | Engine Fuel System | 65007 | 65007 | 6000
500063004 | CLB-MP-LOAD-WL265 -ENGINE-FNHUB | Engine Fan Hub | 65007 | 1947 | 6000
500063003 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-WTRPP | Engine Water Pump | 65007 | 1947 | 6000
500063002 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-THERM | Engine Thermostats-Regulators | 65007 | 1947 | 6000
500063001 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-RADTR | Engine Radiator | 65007 | 1947 | 6000
500063000 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-CSHLF | Engine Cooling Sys Hoses and Fittings | 65007 | 1947 | 6000
500062999 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-COFAN | Engine Fan Cooling System | 65007 | 15666 | 6000
500062998 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-BELTS | Engine Belts and Idler Pulleys | 65007 | 65007 | 6000
500062997 | CLB-MP-LOAD-WL265 -ENGINE-COSYS-ACWEP | Engine Water Pump Aftercooler | 65007 | 1947 | 6000
500062996 | CLB-MP-LOAD-WL265 -ENGINE-COSYS | Engine Cooling System | 65007 | 65007 | 6000
500062995 | CLB-MP-LOAD-WL265 -ENGINE-COMPR | Air Compressor | 65007 | 55366 | 6000
500062994 | CLB-MP-LOAD-WL265 -ENGINE | Engine Assembly Caterpillar 3516B | 65007 | 1947 | 6000
500062993 | CLB-MP-LOAD-WL265 -ELCTLV-LIGHT | Electrical Lighting Low Voltage | 65007 | 65007 | 6000
500062992 | CLB-MP-LOAD-WL265 -ELCTLV-HARNS | Electrical Harness Low Voltage | 65007 | 1947 | 6000
500062991 | CLB-MP-LOAD-WL265 -ELCTLV-CONTL | Electrical Controls Low Voltage | 65007 | 65007 | 6000
500062990 | CLB-MP-LOAD-WL265 -ELCTLV-CHARG-BATTY | Electrical Batteries | 65007 | 15056 | 6000
500062989 | CLB-MP-LOAD-WL265 -ELCTLV-CHARG-ALTER | Electrical Alternator 24V RH | 65007 | 1947 | 6000
500062988 | CLB-MP-LOAD-WL265 -ELCTLV-CHARG-ALTEL | Electrical Alternator 24V LH | 65007 | 1947 | 6000
500062987 | CLB-MP-LOAD-WL265 -ELCTLV-CHARG | Electrical Charging System Low Voltage | 65007 | 65007 | 6000
500062986 | CLB-MP-LOAD-WL265 -ELCTLV | Electrical System Low Voltage 24V | 65007 | 65007 | 6000
500062985 | CLB-MP-LOAD-WL265 -COMMUN-RADIO | Two Way Radio | 65007 | 65007 | 6000
500062984 | CLB-MP-LOAD-WL265 -COMMUN-FLMGT | Fleet Management | 65007 | 65007 | 6000
500062983 | CLB-MP-LOAD-WL265 -COMMUN | Communications | 65007 | 65007 | 6000
500062982 | CLB-MP-LOAD-WL265 -BRKSYS-SRVBK-SVBRR | Brake Service RH Rear | 65007 | 65007 | 6000
500062981 | CLB-MP-LOAD-WL265 -BRKSYS-SRVBK-SVBRF | Brake Service RH Front | 65007 | 65007 | 6000
500062980 | CLB-MP-LOAD-WL265 -BRKSYS-SRVBK-SVBLR | Brake Service LH Rear | 65007 | 65007 | 6000
500062979 | CLB-MP-LOAD-WL265 -BRKSYS-SRVBK-SVBLF | Brake Service LH Front | 65007 | 65007 | 6000
500062978 | CLB-MP-LOAD-WL265 -BRKSYS-SRVBK | Service Brakes | 65007 | 65007 | 6000
500062977 | CLB-MP-LOAD-WL265 -BRKSYS-BRPRK | Brake Park Assembly | 65007 | 1947 | 6000
500062976 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 65007 | 1947 | 6000
500062975 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP-BRP01 | Brake Pump | 65007 | 33503 | 6000
500062974 | CLB-MP-LOAD-WL265 -BRKSYS-BRPMP | Braking System Pumps | 65007 | 65007 | 6000
500062973 | CLB-MP-LOAD-WL265 -BRKSYS-BROCC | Brake Oil Cooler | 65007 | 15666 | 6000
500062972 | CLB-MP-LOAD-WL265 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 65007 | 1947 | 6000
500062971 | CLB-MP-LOAD-WL265 -BRKSYS-BRHLF | Brake System Hoses and Fittings | 65007 | 65007 | 6000
500062970 | CLB-MP-LOAD-WL265 -BRKSYS-BRCOT | Brake Cooling Oil Tank | 65007 | 65007 | 6000
500062969 | CLB-MP-LOAD-WL265 -BRKSYS-BRACC-BACCR | Brake Accumulator Rear | 65007 | 1947 | 6000
500062968 | CLB-MP-LOAD-WL265 -BRKSYS-BRACC-BACCF | Brake Accumulator Front | 65007 | 1947 | 6000
500062967 | CLB-MP-LOAD-WL265 -BRKSYS-BRACC | Brake Accumulators | 65007 | 65007 | 6000
500062966 | CLB-MP-LOAD-WL265 -BRKSYS | Braking System | 65007 | 65007 | 6000
500062784 | CLB-MP-LOAD-WL265 | WL265 Lubrication & Mechanical Services | 65007 | 65007 | 6000
500062783 | CLB-MP-LOAD-WL265 | Caterpillar 994H Wheel Loader WL265 | 65007 | 65007 | 6000
500150700 | CLB-MP-LOAD-WL264 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 67352 | 11872 | 6000
500148507 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC | Brake Accumulator RH | 67351 | 67351 | 6000
500148506 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC | Brake Accumulator LH | 31688 | 31688 | 6000
500127958 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC-BACCR | Brake Accumulator Rear | 67351 | 12287 | 6000
500102512 | CLB-MP-LOAD-WL264 -TRNSYS-TRTRF | Transmission Transfer Case | 67352 | 16649 | 6000
500079117 | CLB-MP-LOAD-WL264 -GRSYST-FFGHO | Front Frame - Grease Hoses | 67352 | 20251 | 6000
500077972 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 67352 | 14589 | 6000
500077971 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 67352 | 14589 | 6000
500077970 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 67352 | 14589 | 6000
500077969 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 67352 | 14589 | 6000
500073568 | CLB-MP-LOAD-WL264 -PNEUMC | Main Airhoses/Relay | 67352 | 67352 | 6000
500067436 | CLB-MP-LOAD-WL264 -STRSYS-STTNK | Stering and brake tank | 67352 | 20251 | 6000
500063977 | CLB-MP-LOAD-WL264 -ELCTLV-HARNS | Electrical Harness Low Voltage | 67352 | 20251 | 6000
500062965 | CLB-MP-LOAD-WL264 -TRNSYS-TRQUE | Torque Converter | 67352 | 20251 | 6000
500062964 | CLB-MP-LOAD-WL264 -TRNSYS-TRPMP | Transmission Charge Pump | 67352 | 6205 | 6000
500062963 | CLB-MP-LOAD-WL264 -TRNSYS-TROLC | Transmission Oil Cooler | 67352 | 16649 | 6000
500062962 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 67352 | 20251 | 6000
500062961 | CLB-MP-LOAD-WL264 -TRNSYS-TRHLF | "Trans System Hoses, Lines and Fittings" | 67352 | 67352 | 6000
500062960 | CLB-MP-LOAD-WL264 -TRNSYS-TRANS | Transmission | 67352 | 16649 | 6000
500062959 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR-RRPDR | Pump Drive Gearbox Rear | 67352 | 20251 | 6000
500062958 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR-FRPDR | Pump Drive Gearbox Front | 67352 | 12287 | 6000
500062957 | CLB-MP-LOAD-WL264 -TRNSYS-PMPDR | Pump Drive Gearboxes | 67352 | 67352 | 6000
500062956 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-UCTRB | D-Shaft Upper Centre Bearing | 67352 | 14859 | 6000
500062955 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-TORCP | D-Shaft Torsional Coupling | 67352 | 4805 | 6000
500062954 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 67352 | 16649 | 6000
500062953 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 67352 | 10475 | 6000
500062952 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT04 | D-Shaft Cntr Bearing to Front Diff | 67352 | 14589 | 6000
500062951 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT03 | D-Shaft Transmission to Cntr Bearing | 67352 | 20251 | 6000
500062950 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT02 | D-Shaft Transmission to Rear Diff | 67352 | 10475 | 6000
500062949 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-SHT01 | D-Shaft T/C to Transmission | 67352 | 12287 | 6000
500062948 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT-LCTRB | D-Shaft Lower Centre Bearing | 67352 | 10475 | 6000
500062947 | CLB-MP-LOAD-WL264 -TRNSYS-DRSHT | Drive Shafts | 67352 | 67352 | 6000
500062946 | CLB-MP-LOAD-WL264 -TRNSYS | Transmission System | 67352 | 67352 | 6000
500062945 | CLB-MP-LOAD-WL264 -STRUCT-STLAD | Steps and Ladders | 67352 | 67352 | 6000
500062944 | CLB-MP-LOAD-WL264 -STRUCT-PNLGU | Panels and Guards | 67352 | 67352 | 6000
500062943 | CLB-MP-LOAD-WL264 -STRUCT-PLHAN | Platforms and Handrails | 67352 | 67352 | 6000
500062942 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-ROPSS | Chassis Rollover Protective Structure | 67352 | 67352 | 6000
500062941 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-REFRM | Chassis Rear Frame | 67352 | 67352 | 6000
500062940 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-LNKGE | Chassis Linkage | 67352 | 67352 | 6000
500062939 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-LIARM | Chassis Lift Arm | 67352 | 20251 | 6000
500062938 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-LEVER | Chassis Lever | 67352 | 67352 | 6000
500062937 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-FRFRM | Chassis Front Frame | 67352 | 67352 | 6000
500062936 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-CWEIG | Chassis Counterweight | 67352 | 67352 | 6000
500062935 | CLB-MP-LOAD-WL264 -STRUCT-CHASS-ARTIC | Chassis Articulation | 67352 | 14957 | 6000
500062934 | CLB-MP-LOAD-WL264 -STRUCT-CHASS | Chassis | 67352 | 67352 | 6000
500062933 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SEATS | Cabin Operators Seat | 67352 | 5323 | 6000
500062932 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-SBELT | Cabin Seat Belt | 67352 | 67352 | 6000
500062931 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-GLASS | Cabin Glass | 67352 | 67352 | 6000
500062930 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 67352 | 67352 | 6000
500062929 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-CABES | Cabin Entertainment System | 67352 | 67352 | 6000
500062928 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-CABCO | Cabin Controls | 67352 | 67352 | 6000
500062927 | CLB-MP-LOAD-WL264 -STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 67352 | 20251 | 6000
500062926 | CLB-MP-LOAD-WL264 -STRUCT-CABIN | Cabin Operators | 67352 | 67352 | 6000
500062925 | CLB-MP-LOAD-WL264 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 67352 | 67352 | 6000
500062924 | CLB-MP-LOAD-WL264 -STRUCT-BUCKT | Bucket | 67352 | 8062 | 6000
500062923 | CLB-MP-LOAD-WL264 -STRUCT | Structure | 67352 | 67352 | 6000
500062922 | CLB-MP-LOAD-WL264 -STRSYS-STVLV | Steering Valve | 67352 | 67352 | 6000
500062921 | CLB-MP-LOAD-WL264 -STRSYS-STTNK | Steering and Brake Oil Tank | 67352 | 20251 | 6000
500062920 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYR | Steering Cylinder RH | 67352 | 12287 | 6000
500062919 | CLB-MP-LOAD-WL264 -STRSYS-STRCY-STCYL | Steering Cylinder LH | 67352 | 12287 | 6000
500062918 | CLB-MP-LOAD-WL264 -STRSYS-STRCY | Steering Cylinder | 67352 | 67352 | 6000
500062917 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 67352 | 12287 | 6000
500062916 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 67352 | 1556 | 6000
500062915 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP02 | Steering Pump RH | 67352 | 20251 | 6000
500062914 | CLB-MP-LOAD-WL264 -STRSYS-STPMP-STP01 | Steering Pump LH | 67352 | 20251 | 6000
500062913 | CLB-MP-LOAD-WL264 -STRSYS-STPMP | Steering System Pumps | 67352 | 67352 | 6000
500062912 | CLB-MP-LOAD-WL264 -STRSYS-STNVS | Steering Neutralizer Valves | 67352 | 33911 | 6000
500062911 | CLB-MP-LOAD-WL264 -STRSYS-STIPV | Steering STIC Pilot Valve | 67352 | 33615 | 6000
500062910 | CLB-MP-LOAD-WL264 -STRSYS-STHLF-STRHO | Steering System Hoses | 67352 | 20251 | 6000
500062909 | CLB-MP-LOAD-WL264 -STRSYS-STHLF | Steering System Hoses and Fittings | 67352 | 67352 | 6000
500062908 | CLB-MP-LOAD-WL264 -STRSYS-STBOC | Steering And Brake Oil Cooler | 67352 | 12287 | 6000
500062907 | CLB-MP-LOAD-WL264 -STRSYS | Steering System | 67352 | 67352 | 6000
500062906 | CLB-MP-LOAD-WL264 -PNEUMC-START | Pneumatic Starter Motor | 67387 | 4805 | 6000
500062905 | CLB-MP-LOAD-WL264 -PNEUMC-PNTNK-AIT03 | Pneumatic Air Tank Expansion RH | 67352 | 67352 | 6000
500062904 | CLB-MP-LOAD-WL264 -PNEUMC-PNTNK-AIT02 | Pneumatic Tank Expansion LH | 67352 | 67352 | 6000
500062903 | CLB-MP-LOAD-WL264 -PNEUMC-PNTNK-AIT01 | Pneumatic Tank Main Starting | 67352 | 67352 | 6000
500062902 | CLB-MP-LOAD-WL264 -PNEUMC-PNTNK | Pneumatic System Tanks | 67352 | 67352 | 6000
500062901 | CLB-MP-LOAD-WL264 -PNEUMC-PNHLF | Pneumatic System Hoses & Fittings | 67352 | 20251 | 6000
500062900 | CLB-MP-LOAD-WL264 -PNEUMC | Pneumatic System | 67352 | 4358 | 6000
500062899 | CLB-MP-LOAD-WL264 -MANGMT-UMMMC | Management Mine Monitoring and Control | 67352 | 67352 | 6000
500062898 | CLB-MP-LOAD-WL264 -MANGMT-UMMC | Management Machine System | 67352 | 67352 | 6000
500062897 | CLB-MP-LOAD-WL264 -MANGMT-UMENG | Management Engine System | 67352 | 67352 | 6000
500062896 | CLB-MP-LOAD-WL264 -MANGMT | Unit Management | 67352 | 67352 | 6000
500062895 | CLB-MP-LOAD-WL264 -HYDSYS-PACCM | Hydraulic Pilot Accumulator | 67352 | 20251 | 6000
500062894 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP04 | Hydraulic Pump Pilot & Cooling | 67352 | 10475 | 6000
500062893 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP03 | Hydraulic Pump Implement Centre | 67352 | 12287 | 6000
500062892 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP02 | Hydraulic Pump Implement RH | 67352 | 12287 | 6000
500062891 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP-HYP01 | Hydraulic Pump Implement LH | 67352 | 1556 | 6000
500062890 | CLB-MP-LOAD-WL264 -HYDSYS-HYDPP | Hydraulic Pumps | 67352 | 67352 | 6000
500062889 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV-HYV02 | Hydraulic Valve Implement Control RH | 67352 | 20251 | 6000
500062888 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV-HYV01 | Hydraulic Valve Implement Control LH | 67352 | 20251 | 6000
500062887 | CLB-MP-LOAD-WL264 -HYDSYS-HDVLV | Hydraulic Valves | 67352 | 67352 | 6000
500062886 | CLB-MP-LOAD-WL264 -HYDSYS-HDTNK-HYT03 | Hydraulic Tank Expansion RH | 67352 | 67352 | 6000
500062885 | CLB-MP-LOAD-WL264 -HYDSYS-HDTNK-HYT02 | Hydraulic Tank Expansion LH | 67352 | 67352 | 6000
500062884 | CLB-MP-LOAD-WL264 -HYDSYS-HDTNK-HYT01 | Hydraulic Tank Main | 67352 | 20251 | 6000
500062883 | CLB-MP-LOAD-WL264 -HYDSYS-HDTNK | Hydraulic Oil Tanks | 67352 | 67352 | 6000
500062882 | CLB-MP-LOAD-WL264 -HYDSYS-HDOCO | Hydraulic Oil Cooler | 67352 | 20251 | 6000
500062881 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 67352 | 20251 | 6000
500062880 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 67352 | 20251 | 6000
500062879 | CLB-MP-LOAD-WL264 -HYDSYS-HDHLF | Hydraulic System Hoses & Fittings | 67352 | 67352 | 6000
500062878 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 67352 | 8109 | 6000
500062877 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 67352 | 8109 | 6000
500062876 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 67352 | 10633 | 6000
500062875 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 67352 | 8062 | 6000
500062874 | CLB-MP-LOAD-WL264 -HYDSYS-HDCYL | Hydraulic Cylinders | 67352 | 67352 | 6000
500062873 | CLB-MP-LOAD-WL264 -HYDSYS | Hydraulic System | 67352 | 67352 | 6000
500062872 | CLB-MP-LOAD-WL264 -GRSYST-GRTNK | Grease Resevoir | 67352 | 67352 | 6000
500062871 | CLB-MP-LOAD-WL264 -GRSYST-GRINJ | Grease Injectors | 67352 | 67352 | 6000
500062870 | CLB-MP-LOAD-WL264 -GRSYST-ALHLF | Grease Auto Lube Hoses & Fittings | 67352 | 67352 | 6000
500062869 | CLB-MP-LOAD-WL264 -GRSYST-ALELC | Grease Auto Lube Electrical | 67352 | 67352 | 6000
500062868 | CLB-MP-LOAD-WL264 -GRSYST-ALCON | Grease Auto Lube Controller | 67352 | 67352 | 6000
500062867 | CLB-MP-LOAD-WL264 -GRSYST-ALBPP | Grease Auto Lube Pump | 67352 | 6205 | 6000
500062866 | CLB-MP-LOAD-WL264 -GRSYST | Grease Lubrication System | 67352 | 67352 | 6000
500062865 | CLB-MP-LOAD-WL264 -FRSUPP-FSMAN-EXTIN | Fire Suppression Hand Held Extinguisher | 67352 | 67352 | 6000
500062864 | CLB-MP-LOAD-WL264 -FRSUPP-FSMAN | Fire Suppression Manual | 67352 | 67352 | 6000
500062863 | CLB-MP-LOAD-WL264 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 67352 | 67352 | 6000
500062862 | CLB-MP-LOAD-WL264 -FRSUPP-FSAUT | Fire Suppression Automatic | 67352 | 67352 | 6000
500062861 | CLB-MP-LOAD-WL264 -FRSUPP-FSALM | Fire Suppression System Alarm | 67352 | 67352 | 6000
500062860 | CLB-MP-LOAD-WL264 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 67352 | 67352 | 6000
500062859 | CLB-MP-LOAD-WL264 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 67352 | 67352 | 6000
500062858 | CLB-MP-LOAD-WL264 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 67352 | 67352 | 6000
500062857 | CLB-MP-LOAD-WL264 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 67352 | 67352 | 6000
500062856 | CLB-MP-LOAD-WL264 -FDRSYS-WHTYR | Wheels & Tyres and Rims | 67352 | 67352 | 6000
500062855 | CLB-MP-LOAD-WL264 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 67352 | 1556 | 6000
500062854 | CLB-MP-LOAD-WL264 -FDRSYS-RRDIF | Rear Differential | 67352 | 1556 | 6000
500062853 | CLB-MP-LOAD-WL264 -FDRSYS-FRDIF | Front Differential | 67352 | 20251 | 6000
500062852 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 67352 | 5772 | 6000
500062851 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 67352 | 1556 | 6000
500062850 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 67352 | 8109 | 6000
500062849 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 67352 | 122 | 6000
500062848 | CLB-MP-LOAD-WL264 -FDRSYS-FDRVE | Final Drives | 67352 | 67352 | 6000
500062847 | CLB-MP-LOAD-WL264 -FDRSYS | Final Drive System | 67352 | 67352 | 6000
500062846 | CLB-MP-LOAD-WL264 -ENGINE-LUBSY-PREPP | Engine Prelube Oil Pump | 67352 | 1556 | 6000
500062845 | CLB-MP-LOAD-WL264 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 67352 | 67352 | 6000
500062844 | CLB-MP-LOAD-WL264 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 67352 | 67352 | 6000
500062843 | CLB-MP-LOAD-WL264 -ENGINE-LUBSY | Engine Lubrication System | 67352 | 67352 | 6000
500062842 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-TBORR | Engine Turbocharger RH Rear | 67387 | 4805 | 6000
500062841 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-TBORF | Engine Turbocharger RH Front | 67387 | 4805 | 6000
500062840 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-TBOLR | Engine Turbocharger LH Rear | 67387 | 4805 | 6000
500062839 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-TBOLF | Engine Turbocharger LH Front | 67387 | 4805 | 6000
500062838 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-EXHST | Engine Exhaust System | 67352 | 67352 | 6000
500062837 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-AIRFL | Engine Air Filtration System | 67352 | 20251 | 6000
500062836 | CLB-MP-LOAD-WL264 -ENGINE-INTEX-AFTER | Engine Aftercooler | 67352 | 67352 | 6000
500062835 | CLB-MP-LOAD-WL264 -ENGINE-INTEX | Engine Intake and Exhaust System | 67352 | 67352 | 6000
500062834 | CLB-MP-LOAD-WL264 -ENGINE-FUSYS-FULTP | Engine Fuel Transfer Pump | 67387 | 4805 | 6000
500062833 | CLB-MP-LOAD-WL264 -ENGINE-FUSYS-FULTK | Engine Fuel Tank | 67352 | 67352 | 6000
500062832 | CLB-MP-LOAD-WL264 -ENGINE-FUSYS-FULPP | Engine Fuel Priming Pump | 67352 | 38630 | 6000
500062831 | CLB-MP-LOAD-WL264 -ENGINE-FUSYS-FUINJ | Engine Fuel Injectors | 67387 | 4805 | 6000
500062830 | CLB-MP-LOAD-WL264 -ENGINE-FUSYS-FUHLF | Engine Fuel System Hoses and Fittings | 67352 | 67352 | 6000
500062829 | CLB-MP-LOAD-WL264 -ENGINE-FUSYS | Engine Fuel System | 67352 | 67352 | 6000
500062828 | CLB-MP-LOAD-WL264 -ENGINE-FNHUB | Engine Fan Hub | 67387 | 4805 | 6000
500062827 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-WTRPP | Engine Water Pump | 67387 | 4805 | 6000
500062826 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-THERM | Engine Thermostats-Regulators | 67387 | 4805 | 6000
500062825 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-RADTR | Engine Radiator | 67352 | 20251 | 6000
500062824 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-CSHLF | Engine Cooling Sys Hoses and Fittings | 67387 | 4805 | 6000
500062823 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-COFAN | Engine Fan Cooling System | 67352 | 67352 | 6000
500062822 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-BELTS | Engine Belts and Idler Pulleys | 67352 | 67352 | 6000
500062821 | CLB-MP-LOAD-WL264 -ENGINE-COSYS-ACWEP | Engine Water Pump Aftercooler | 67387 | 4805 | 6000
500062820 | CLB-MP-LOAD-WL264 -ENGINE-COSYS | Engine Cooling System | 67352 | 67352 | 6000
500062819 | CLB-MP-LOAD-WL264 -ENGINE-COMPR | Air Compressor | 67352 | 6618 | 6000
500062818 | CLB-MP-LOAD-WL264 -ENGINE | Engine Assembly Caterpillar 3516B | 67352 | 4805 | 6000
500062817 | CLB-MP-LOAD-WL264 -ELCTLV-LIGHT | Electrical Lighting Low Voltage | 67352 | 67352 | 6000
500062816 | CLB-MP-LOAD-WL264 -ELCTLV-HARNS | Electrical Harness Low Voltage | 67352 | 20251 | 6000
500062815 | CLB-MP-LOAD-WL264 -ELCTLV-CONTL | Electrical Controls Low Voltage | 67352 | 67352 | 6000
500062814 | CLB-MP-LOAD-WL264 -ELCTLV-CHARG-BATTY | Electrical Batteries | 67352 | 10510 | 6000
500062813 | CLB-MP-LOAD-WL264 -ELCTLV-CHARG-ALTER | Electrical Alternator 24V RH | 67387 | 712 | 6000
500062812 | CLB-MP-LOAD-WL264 -ELCTLV-CHARG-ALTEL | Electrical Alternator 24V LH | 67387 | 4805 | 6000
500062811 | CLB-MP-LOAD-WL264 -ELCTLV-CHARG | Electrical Charging System Low Voltage | 67352 | 67352 | 6000
500062810 | CLB-MP-LOAD-WL264 -ELCTLV | Electrical System Low Voltage 24V | 67352 | 67352 | 6000
500062809 | CLB-MP-LOAD-WL264 -COMMUN-RADIO | Two Way Radio | 67352 | 67352 | 6000
500062808 | CLB-MP-LOAD-WL264 -COMMUN-FLMGT | Fleet Management | 67352 | 67352 | 6000
500062807 | CLB-MP-LOAD-WL264 -COMMUN | Communications | 67352 | 67352 | 6000
500062806 | CLB-MP-LOAD-WL264 -BRKSYS-SRVBK-SVBRR | Brake Service RH Rear | 67352 | 47084 | 6000
500062805 | CLB-MP-LOAD-WL264 -BRKSYS-SRVBK-SVBRF | Brake Service RH Front | 67352 | 47084 | 6000
500062804 | CLB-MP-LOAD-WL264 -BRKSYS-SRVBK-SVBLR | Brake Service LH Rear | 67352 | 47084 | 6000
500062803 | CLB-MP-LOAD-WL264 -BRKSYS-SRVBK-SVBLF | Brake Service LH Front | 67352 | 47084 | 6000
500062802 | CLB-MP-LOAD-WL264 -BRKSYS-SRVBK | Service Brakes | 67352 | 67352 | 6000
500062801 | CLB-MP-LOAD-WL264 -BRKSYS-BRPRK | Brake Park Assembly | 67352 | 10475 | 6000
500062800 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 67352 | 10475 | 6000
500062799 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP-BRP01 | Brake Pump | 67352 | 4805 | 6000
500062798 | CLB-MP-LOAD-WL264 -BRKSYS-BRPMP | Braking System Pumps | 67352 | 67352 | 6000
500062797 | CLB-MP-LOAD-WL264 -BRKSYS-BROCC | Brake Oil Cooler | 67352 | 31688 | 6000
500062796 | CLB-MP-LOAD-WL264 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 67352 | 20251 | 6000
500062795 | CLB-MP-LOAD-WL264 -BRKSYS-BRHLF | Brake System Hoses and Fittings | 67352 | 67352 | 6000
500062794 | CLB-MP-LOAD-WL264 -BRKSYS-BRCOT | Brake Cooling Oil Tank | 67352 | 67352 | 6000
500062793 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC-BACCF | Brake Accumulator Front | 67352 | 12287 | 6000
500062792 | CLB-MP-LOAD-WL264 -BRKSYS-BRACC | Brake Accumulators | 67352 | 67352 | 6000
500062791 | CLB-MP-LOAD-WL264 -BRKSYS | Braking System | 67352 | 67352 | 6000
500057109 | CLB-MP-LOAD-WL264 | WL264 Lube & Mechanical Services | 67352 | 67352 | 6000
500057108 | CLB-MP-LOAD-WL264 | Caterpillar 994H Wheel Loader WL264 | 67352 | 67352 | 6000
500150678 | CLB-MP-LOAD-WL263 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 60643 | 10219 | 6000
500148469 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC | Brake Accumulator RH | 17971 | 17971 | 6000
500148468 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC | Brake Accumulator LH | 17971 | 17971 | 6000
500102499 | CLB-MP-LOAD-WL263 -TRNSYS-TRTRF | Transmission Transfer Case | 60624 | 3265 | 6000
500080522 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 60624 | 7539 | 6000
500080521 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 60624 | 7539 | 6000
500080520 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 60624 | 7539 | 6000
500080519 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 60624 | 39459 | 6000
500065794 | CLB-MP-LOAD-WL263 -TRNSYS-TRQUE | WL263 Torque Converter | 60624 | 5531 | 6000
500065793 | CLB-MP-LOAD-WL263 -TRNSYS-TRPMP | WL263 Transmission Charge Pump | 60624 | 4273 | 6000
500065792 | CLB-MP-LOAD-WL263 -TRNSYS-TROLC | WL263 Transmission Oil Cooler | 60624 | 3265 | 6000
500065791 | CLB-MP-LOAD-WL263 -TRNSYS-TRHLF-TRNHO | WL263 Transmission System Hoses | 60624 | 22185 | 6000
500065790 | CLB-MP-LOAD-WL263 -TRNSYS-TRHLF | WL263 Trans System Hoses, Lines and Fi | 60624 | 60624 | 6000
500065789 | CLB-MP-LOAD-WL263 -TRNSYS-TRANS | WL263 Transmission | 60624 | 3265 | 6000
500065788 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR-RRPDR | WL263 Pump Drive Gearbox Rear | 60624 | 3265 | 6000
500065787 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR-FRPDR | WL263 Pump Drive Gearbox Front | 60624 | 3265 | 6000
500065786 | CLB-MP-LOAD-WL263 -TRNSYS-PMPDR | WL263 Pump Drive Gearboxes | 60624 | 60624 | 6000
500065785 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-UCTRB | WL263 D-Shaft Upper Centre Bearing | 60624 | 3265 | 6000
500065784 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-TORCP | WL263 D-Shaft Torsional Coupling | 60624 | 11204 | 6000
500065783 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT06 | WL263 D-Shaft Front Pump Drive To Cntr | 60624 | 3265 | 6000
500065782 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT05 | WL263 D-Shaft Rear Pump Drive To Cntr B | 60624 | 3265 | 6000
500065781 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT04 | WL263 D-Shaft Cntr Bearing to Front Dif | 60624 | 3265 | 6000
500065780 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT03 | WL263 D-Shaft Transmission to Cntr Bear | 60624 | 3265 | 6000
500065779 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT02 | WL263 D-Shaft Transmission to Rear Diff | 60624 | 3265 | 6000
500065778 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-SHT01 | WL263 D-Shaft T/C to Transmission | 60624 | 3265 | 6000
500065777 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT-LCTRB | WL263 D-Shaft Lower Centre Bearing | 60624 | 3265 | 6000
500065776 | CLB-MP-LOAD-WL263 -TRNSYS-DRSHT | WL263 Drive Shafts | 60624 | 60624 | 6000
500065775 | CLB-MP-LOAD-WL263 -TRNSYS | WL263 Transmission System | 60624 | 60624 | 6000
500065774 | CLB-MP-LOAD-WL263 -STRUCT-STLAD | WL263 Steps and Ladders | 60624 | 60624 | 6000
500065773 | CLB-MP-LOAD-WL263 -STRUCT-PNLGU | WL263 Panels and Guards | 60624 | 60624 | 6000
500065772 | CLB-MP-LOAD-WL263 -STRUCT-PLHAN | WL263 Platforms and Handrails | 60624 | 60624 | 6000
500065771 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-ROPSS | WL263 Chassis Rollover Protective Struc | 60624 | 60624 | 6000
500065770 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-REFRM | WL263 Chassis Rear Frame | 60624 | 60624 | 6000
500065769 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-LNKGE | WL263 Chassis Linkage | 60624 | 60624 | 6000
500065768 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-LIARM | WL263 Chassis Lift Arm | 60624 | 22185 | 6000
500065767 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-LEVER | WL263 Chassis Lever | 60624 | 60624 | 6000
500065766 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-FRFRM | WL263 Chassis Front Frame | 60624 | 60624 | 6000
500065765 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-CWEIG | WL263 Chassis Counterweight | 60624 | 60624 | 6000
500065764 | CLB-MP-LOAD-WL263 -STRUCT-CHASS-ARTIC | WL263 Chassis Articulation | 60624 | 3265 | 6000
500065763 | CLB-MP-LOAD-WL263 -STRUCT-CHASS | WL263 Chassis | 60624 | 60624 | 6000
500065762 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-SEATS | WL263 Cabin Operators Seat | 60624 | 3265 | 6000
500065761 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-SBELT | WL263 Cabin Seat Belt | 60624 | 60624 | 6000
500065760 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-GLASS | WL263 Cabin Glass | 60624 | 60624 | 6000
500065759 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-CABPR | WL263 Cabin Pressurisation System | 60624 | 60624 | 6000
500065758 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-CABES | WL263 Cabin Entertainment System | 60624 | 60624 | 6000
500065757 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-CABCO | WL263 Cabin Controls | 60624 | 60624 | 6000
500065756 | CLB-MP-LOAD-WL263 -STRUCT-CABIN-AIRCN | WL263 Cabin Air Conditioning System | 60624 | 3265 | 6000
500065755 | CLB-MP-LOAD-WL263 -STRUCT-CABIN | WL263 Cabin Operators | 60624 | 60624 | 6000
500065753 | CLB-MP-LOAD-WL263 -STRUCT-BUCKT | WL263 Bucket | 60624 | 60624 | 6000
500065752 | CLB-MP-LOAD-WL263 -STRUCT | WL263 Structure | 60624 | 60624 | 6000
500065751 | CLB-MP-LOAD-WL263 -STRSYS-STVLV | WL263 Steering Valve | 60624 | 11941 | 6000
500065750 | CLB-MP-LOAD-WL263 -STRSYS-STTNK | WL263 Steering and Brake Oil Tank | 60624 | 3265 | 6000
500065749 | CLB-MP-LOAD-WL263 -STRSYS-STRCY-STCYR | WL263 Steering Cylinder RH | 60624 | 3265 | 6000
500065748 | CLB-MP-LOAD-WL263 -STRSYS-STRCY-STCYL | WL263 Steering Cylinder LH | 60624 | 4273 | 6000
500065747 | CLB-MP-LOAD-WL263 -STRSYS-STRCY | WL263 Steering Cylinder | 60624 | 60624 | 6000
500065746 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP04 | WL263 Steering Pump Secondary | 60624 | 4273 | 6000
500065745 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP03 | WL263 Steering and Brake Oil Cooler Pum | 60624 | 3265 | 6000
500065744 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP02 | WL263 Steering Pump RH | 60624 | 3265 | 6000
500065743 | CLB-MP-LOAD-WL263 -STRSYS-STPMP-STP01 | WL263 Steering Pump LH | 60624 | 1219 | 6000
500065742 | CLB-MP-LOAD-WL263 -STRSYS-STPMP | WL263 Steering System Pumps | 60624 | 60624 | 6000
500065741 | CLB-MP-LOAD-WL263 -STRSYS-STNVS | WL263 Steering Neutralizer Valves | 60624 | 3265 | 6000
500065740 | CLB-MP-LOAD-WL263 -STRSYS-STIPV | WL263 Steering STIC Pilot Valve | 60624 | 33583 | 6000
500065739 | CLB-MP-LOAD-WL263 -STRSYS-STHLF-STRHO | WL263 Steering System Hoses | 60624 | 3265 | 6000
500065738 | CLB-MP-LOAD-WL263 -STRSYS-STHLF | WL263 Steering System Hoses and Fitting | 60624 | 60624 | 6000
500065737 | CLB-MP-LOAD-WL263 -STRSYS-STBOC | WL263 Steering And Brake Oil Cooler | 60624 | 60624 | 6000
500065736 | CLB-MP-LOAD-WL263 -STRSYS | WL263 Steering System | 60624 | 60624 | 6000
500065735 | CLB-MP-LOAD-WL263 -PNEUMC-START | WL263 Pneumatic Starter Motor | 60624 | 11204 | 6000
500065734 | CLB-MP-LOAD-WL263 -PNEUMC-PNTNK-AIT03 | WL263 Pneumatic Air Tank Expansion RH | 60624 | 60624 | 6000
500065733 | CLB-MP-LOAD-WL263 -PNEUMC-PNTNK-AIT02 | WL263 Pneumatic Tank Expansion LH | 60624 | 60624 | 6000
500065732 | CLB-MP-LOAD-WL263 -PNEUMC-PNTNK-AIT01 | WL263 Pneumatic Tank Main Starting | 60624 | 60624 | 6000
500065731 | CLB-MP-LOAD-WL263 -PNEUMC-PNTNK | WL263 Pneumatic System Tanks | 60624 | 60624 | 6000
500065730 | CLB-MP-LOAD-WL263 -PNEUMC-PNHLF | WL263 Pneumatic System Hoses & Fittings | 60624 | 3265 | 6000
500065729 | CLB-MP-LOAD-WL263 -PNEUMC | WL263 Pneumatic System | 60624 | 60624 | 6000
500065728 | CLB-MP-LOAD-WL263 -MANGMT-UMMMC | WL263 Management Mine Monitoring and Co | 60624 | 60624 | 6000
500065727 | CLB-MP-LOAD-WL263 -MANGMT-UMMC | WL263 Management Machine System | 60624 | 60624 | 6000
500065726 | CLB-MP-LOAD-WL263 -MANGMT-UMENG | WL263 Management Engine System | 60624 | 60624 | 6000
500065725 | CLB-MP-LOAD-WL263 -MANGMT | WL263 Unit Management | 60624 | 60624 | 6000
500065724 | CLB-MP-LOAD-WL263 -HYDSYS-PACCM | WL263 Hydraulic Pilot Accumulator | 60624 | 3265 | 6000
500065723 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP04 | WL263 Hydraulic Pump Hydraulic Pilot & | 60624 | 17971 | 6000
500065722 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP03 | WL263 Hydraulic Pump Implement Centre | 60624 | 3265 | 6000
500065721 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP02 | WL263 Hydraulic Pump Implement RH | 60624 | 3265 | 6000
500065720 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP-HYP01 | WL263 Hydraulic Pump Implement LH | 60624 | 6877 | 6000
500065719 | CLB-MP-LOAD-WL263 -HYDSYS-HYDPP | WL263 Hydraulic Pumps | 60624 | 60624 | 6000
500065718 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV-HYV02 | WL263 Hydraulic Valve Implement Control | 60624 | 3265 | 6000
500065717 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV-HYV01 | WL263 Hydraulic Valve Implement Control | 60624 | 3265 | 6000
500065716 | CLB-MP-LOAD-WL263 -HYDSYS-HDVLV | WL263 Hydraulic Valves | 60624 | 60624 | 6000
500065715 | CLB-MP-LOAD-WL263 -HYDSYS-HDTNK-HYT03 | WL263 Hydraulic Tank Expansion RH | 60624 | 60624 | 6000
500065714 | CLB-MP-LOAD-WL263 -HYDSYS-HDTNK-HYT02 | WL263 Hydraulic Tank Expansion LH | 60624 | 60624 | 6000
500065713 | CLB-MP-LOAD-WL263 -HYDSYS-HDTNK-HYT01 | WL263 Hydraulic Tank Main | 60624 | 3265 | 6000
500065712 | CLB-MP-LOAD-WL263 -HYDSYS-HDTNK | WL263 Hydraulic Oil Tanks | 60624 | 60624 | 6000
500065711 | CLB-MP-LOAD-WL263 -HYDSYS-HDOCO | WL263 Hydraulic Oil Cooler | 60624 | 3265 | 6000
500065710 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-PILHO | WL263 Pilot System Hoses | 60624 | 3265 | 6000
500065709 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF-HYDHO | WL263 Hydraulic System Hoses | 60624 | 3265 | 6000
500065708 | CLB-MP-LOAD-WL263 -HYDSYS-HDHLF | WL263 Hydraulic System Hoses & Fittings | 60624 | 60624 | 6000
500065707 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLR | WL263 Cylinder Hoist RH High Lift | 60624 | 3938 | 6000
500065706 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-HCYLL | WL263 Cylinder Hoist LH High Lift | 60624 | 4601 | 6000
500065705 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYR | WL263 Cylinder Bucket RH High Lift | 60624 | 670 | 6000
500065704 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL-BUCYL | WL263 Cylinder Bucket LH High Lift | 60624 | 3265 | 6000
500065703 | CLB-MP-LOAD-WL263 -HYDSYS-HDCYL | WL263 Hydraulic Cylinders | 60624 | 60624 | 6000
500065702 | CLB-MP-LOAD-WL263 -HYDSYS | WL263 Hydraulic System | 60624 | 3265 | 6000
500065701 | CLB-MP-LOAD-WL263 -GRSYST-GRTNK | WL263 Grease Resevoir | 60624 | 60624 | 6000
500065700 | CLB-MP-LOAD-WL263 -GRSYST-GRINJ | WL263 Grease Injectors | 60624 | 60624 | 6000
500065699 | CLB-MP-LOAD-WL263 -GRSYST-ALHLF | WL263 Grease Auto Lube Hoses & Fittings | 60624 | 60624 | 6000
500065698 | CLB-MP-LOAD-WL263 -GRSYST-ALELC | WL263 Grease Auto Lube Electrical | 60624 | 60624 | 6000
500065697 | CLB-MP-LOAD-WL263 -GRSYST-ALCON | WL263 Grease Auto Lube Controller | 60624 | 60624 | 6000
500065696 | CLB-MP-LOAD-WL263 -GRSYST-ALBPP | WL263 Grease Auto Lube Pump | 60624 | 648 | 6000
500065695 | CLB-MP-LOAD-WL263 -GRSYST | WL263 Grease Lubrication System | 60624 | 60624 | 6000
500065694 | CLB-MP-LOAD-WL263 -FRSUPP-FSMAN-EXTIN | WL263 Fire Suppression Hand Held Exting | 60624 | 60624 | 6000
500065693 | CLB-MP-LOAD-WL263 -FRSUPP-FSMAN | WL263 Fire Suppression Manual | 60624 | 60624 | 6000
500065692 | CLB-MP-LOAD-WL263 -FRSUPP-FSAUT-FFOAM | WL263 Fire Suppression Foam | 60624 | 60624 | 6000
500065691 | CLB-MP-LOAD-WL263 -FRSUPP-FSAUT | WL263 Fire Suppression Automatic | 60624 | 60624 | 6000
500065690 | CLB-MP-LOAD-WL263 -FRSUPP-FSALM | WL263 Fire Suppression System Alarm | 60624 | 60624 | 6000
500065689 | CLB-MP-LOAD-WL263 -FRSUPP | WL263 Fire Suppression System | 60624 | 17971 | 6000
500065688 | CLB-MP-LOAD-WL263 -FDRSYS-WHTYR-POS04 | WL263 Tyre Position 4 | 60624 | 60624 | 6000
500065687 | CLB-MP-LOAD-WL263 -FDRSYS-WHTYR-POS03 | WL263 Tyre Position 3 | 60624 | 60624 | 6000
500065686 | CLB-MP-LOAD-WL263 -FDRSYS-WHTYR-POS02 | WL263 Tyre Position 2 | 60624 | 60624 | 6000
500065685 | CLB-MP-LOAD-WL263 -FDRSYS-WHTYR-POS01 | WL263 Tyre Position 1 | 60624 | 60624 | 6000
500065684 | CLB-MP-LOAD-WL263 -FDRSYS-WHTYR | WL263 Wheels & Tyres and Rims | 60624 | 60624 | 6000
500065683 | CLB-MP-LOAD-WL263 -FDRSYS-RRDIF-TRNON | WL263 Rear Axle Housing Trunnion | 60624 | 3265 | 6000
500065682 | CLB-MP-LOAD-WL263 -FDRSYS-RRDIF | WL263 Rear Differential | 60624 | 3265 | 6000
500065681 | CLB-MP-LOAD-WL263 -FDRSYS-FRDIF | WL263 Front Differential | 60624 | 3265 | 6000
500065680 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR04 | WL263 Final Drive Position 4 | 60624 | 3251 | 6000
500065679 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR03 | WL263 Final Drive Position 3 | 60624 | 2938 | 6000
500065678 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR02 | WL263 Final Drive Position 2 | 60624 | 2938 | 6000
500065677 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE-FDR01 | WL263 Final Drive Position 1 | 60624 | 5204 | 6000
500065676 | CLB-MP-LOAD-WL263 -FDRSYS-FDRVE | WL263 Final Drives | 60624 | 60624 | 6000
500065675 | CLB-MP-LOAD-WL263 -FDRSYS | WL263 Final Drive System | 60624 | 60624 | 6000
500065674 | CLB-MP-LOAD-WL263 -ENGINE-LUBSY-PREPP | WL263 Engine Prelube Oil Pump | 60721 | 11302 | 6000
500065673 | CLB-MP-LOAD-WL263 -ENGINE-LUBSY-OILPP | WL263 Engine Oil Pump | 60721 | 60721 | 6000
500065672 | CLB-MP-LOAD-WL263 -ENGINE-LUBSY-ENOLC | WL263 Engine Oil Cooler | 60721 | 60721 | 6000
500065671 | CLB-MP-LOAD-WL263 -ENGINE-LUBSY | WL263 Engine Lubrication System | 60721 | 60721 | 6000
500065670 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-TBORR | WL263 Engine Turbocharger RH Rear | 60721 | 11302 | 6000
500065669 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-TBORF | WL263 Engine Turbocharger RH Front | 60721 | 11302 | 6000
500065668 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-TBOLR | WL263 Engine Turbocharger LH Rear | 60721 | 11302 | 6000
500065667 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-TBOLF | WL263 Engine Turbocharger LH Front | 60721 | 11302 | 6000
500065666 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-EXHST | WL263 Engine Exhaust System | 60721 | 60721 | 6000
500065665 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-AIRFL | WL263 Engine Air Filtration System | 60721 | 18069 | 6000
500065664 | CLB-MP-LOAD-WL263 -ENGINE-INTEX-AFTER | WL263 Engine Aftercooler | 60721 | 39557 | 6000
500065663 | CLB-MP-LOAD-WL263 -ENGINE-INTEX | WL263 Engine Intake and Exhaust System | 60721 | 60721 | 6000
500065662 | CLB-MP-LOAD-WL263 -ENGINE-FUSYS-FULTP | WL263 Engine Fuel Transfer Pump | 60721 | 11302 | 6000
500065661 | CLB-MP-LOAD-WL263 -ENGINE-FUSYS-FULTK | WL263 Engine Fuel Tank | 60721 | 60721 | 6000
500065660 | CLB-MP-LOAD-WL263 -ENGINE-FUSYS-FULPP | WL263 Engine Fuel Priming Pump | 60721 | 60721 | 6000
500065659 | CLB-MP-LOAD-WL263 -ENGINE-FUSYS-FUINJ | WL263 Engine Fuel Injectors | 60721 | 11302 | 6000
500065658 | CLB-MP-LOAD-WL263 -ENGINE-FUSYS-FUHLF | WL263 Engine Fuel System Hoses and Fitt | 60721 | 60721 | 6000
500065657 | CLB-MP-LOAD-WL263 -ENGINE-FUSYS | WL263 Engine Fuel System | 60721 | 60721 | 6000
500065656 | CLB-MP-LOAD-WL263 -ENGINE-FNHUB | WL263 Engine Fan Hub | 60721 | 11302 | 6000
500065655 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-WTRPP | WL263 Engine Water Pump | 60721 | 11302 | 6000
500065654 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-THERM | WL263 Engine Thermostats-Regulators | 60721 | 11302 | 6000
500065653 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-RADTR | WL263 Engine Radiator | 60721 | 3363 | 6000
500065652 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-CSHLF | WL263 Engine Cooling Sys Hoses and Fitt | 60721 | 11302 | 6000
500065651 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-COFAN | WL263 Engine Fan Cooling System | 60721 | 60721 | 6000
500065650 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-BELTS | WL263 Engine Belts and Idler Pulleys | 60721 | 60721 | 6000
500065649 | CLB-MP-LOAD-WL263 -ENGINE-COSYS-ACWEP | WL263 Engine Water Pump Aftercooler | 60721 | 9077 | 6000
500065648 | CLB-MP-LOAD-WL263 -ENGINE-COSYS | WL263 Engine Cooling System | 60721 | 60721 | 6000
500065647 | CLB-MP-LOAD-WL263 -ENGINE-COMPR | WL263 Air Compressor | 60721 | 50674 | 6000
500065646 | CLB-MP-LOAD-WL263 -ENGINE | WL263 Engine Assembly Caterpillar 3516B | 60721 | 11302 | 6000
500065645 | CLB-MP-LOAD-WL263 -ELCTLV-LIGHT | WL263 Electrical Lighting Low Voltage | 60721 | 60721 | 6000
500065644 | CLB-MP-LOAD-WL263 -ELCTLV-HARNS | WL263 Electrical Harness Low Voltage | 60721 | 3363 | 6000
500065643 | CLB-MP-LOAD-WL263 -ELCTLV-CONTL | WL263 Electrical Controls Low Voltage | 60721 | 60721 | 6000
500065642 | CLB-MP-LOAD-WL263 -ELCTLV-CHARG-BATTY | WL263 Electrical Batteries | 60721 | 11302 | 6000
500065641 | CLB-MP-LOAD-WL263 -ELCTLV-CHARG-ALTER | WL263 Electrical Alternator 24V RH | 60721 | 11302 | 6000
500065640 | CLB-MP-LOAD-WL263 -ELCTLV-CHARG-ALTEL | WL263 Electrical Alternator 24V LH | 60721 | 11302 | 6000
500065639 | CLB-MP-LOAD-WL263 -ELCTLV-CHARG | WL263 Electrical Charging System Low Vo | 60721 | 60721 | 6000
500065638 | CLB-MP-LOAD-WL263 -ELCTLV | WL263 Electrical System Low Voltage 24V | 60721 | 60721 | 6000
500065637 | CLB-MP-LOAD-WL263 -COMMUN-RADIO | WL263 Two Way Radio | 60624 | 60624 | 6000
500065636 | CLB-MP-LOAD-WL263 -COMMUN-FLMGT | WL263 Fleet Management | 60624 | 60624 | 6000
500065635 | CLB-MP-LOAD-WL263 -COMMUN | WL263 Communications | 60624 | 60624 | 6000
500065634 | CLB-MP-LOAD-WL263 -BRKSYS-SRVBK-SVBRR | WL263 Brake Service RH Rear | 60624 | 60624 | 6000
500065633 | CLB-MP-LOAD-WL263 -BRKSYS-SRVBK-SVBRF | WL263 Brake Service RH Front | 60624 | 60624 | 6000
500065632 | CLB-MP-LOAD-WL263 -BRKSYS-SRVBK-SVBLR | WL263 Brake Service LH Rear | 60624 | 60624 | 6000
500065631 | CLB-MP-LOAD-WL263 -BRKSYS-SRVBK-SVBLF | WL263 Brake Service LH Front | 60624 | 60624 | 6000
500065630 | CLB-MP-LOAD-WL263 -BRKSYS-SRVBK | WL263 Service Brakes | 60624 | 60624 | 6000
500065629 | CLB-MP-LOAD-WL263 -BRKSYS-BRPRK | WL263 Brake Park Assembly | 60624 | 3265 | 6000
500065628 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP02 | WL263 Brake Cooling Pump | 60624 | 3265 | 6000
500065627 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP-BRP01 | WL263 Brake Pump | 60624 | 16431 | 6000
500065626 | CLB-MP-LOAD-WL263 -BRKSYS-BRPMP | WL263 Braking System Pumps | 60624 | 60624 | 6000
500065625 | CLB-MP-LOAD-WL263 -BRKSYS-BROCC | WL263 Brake Oil Cooler | 60624 | 3265 | 6000
500065624 | CLB-MP-LOAD-WL263 -BRKSYS-BRHLF-BRKHO | WL263 Brake System Hoses | 60624 | 3265 | 6000
500065623 | CLB-MP-LOAD-WL263 -BRKSYS-BRHLF | WL263 Brake System Hoses and Fittings | 60624 | 60624 | 6000
500065622 | CLB-MP-LOAD-WL263 -BRKSYS-BRCOT | WL263 Brake Cooling Oil Tank | 60624 | 60624 | 6000
500065621 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC-BACCR | WL263 Brake Accumulator Rear | 60624 | 3265 | 6000
500065620 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC-BACCF | WL263 Brake Accumulator Front | 60624 | 3265 | 6000
500065619 | CLB-MP-LOAD-WL263 -BRKSYS-BRACC | WL263 Brake Accumulators | 60624 | 60624 | 6000
500065618 | CLB-MP-LOAD-WL263 -BRKSYS | WL263 Braking System | 60624 | 60624 | 6000
500056948 | CLB-MP-LOAD-WL263 | WL263 Lube & Mechanical Services | 60721 | 60721 | 6000
500056947 | CLB-MP-LOAD-WL263 | Caterpillar 994H Wheel Loader WL263 | 60624 | 60624 | 6000
500159031 | CLB-MP-LOAD-WL028 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 80034 | 10026 | 6000
500148505 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC | Brake Accumulator RH | 19883 | 19883 | 6000
500148504 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC | Brake Accumulator LH | 19883 | 19883 | 6000
500102511 | CLB-MP-LOAD-WL028 -TRNSYS-TRTRF | Transmission Transfer Case | 80034 | 3452 | 6000
500079116 | CLB-MP-LOAD-WL028 -GRSYST-FFGHO | Front Frame - Grease Hoses | 80034 | 19883 | 6000
500077968 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 80034 | 15459 | 6000
500077967 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 80034 | 15459 | 6000
500077966 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 80034 | 15916 | 6000
500077965 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 80034 | 15916 | 6000
500073567 | CLB-MP-LOAD-WL028 -PNEUMC | Main Airhoses/Relay | 80034 | 37765 | 6000
500067435 | CLB-MP-LOAD-WL028 -STRSYS-STTNK | Steering and brake tank | 80034 | 19883 | 6000
500065267 | CLB-MP-LOAD-WL028 -HYDSYS-HDTNK-HYT01 | WL028 Hydraulic Tank | 80034 | 19883 | 6000
500063976 | CLB-MP-LOAD-WL028 -ELCTLV-HARNS | Electrical Harness Low Voltage | 80034 | 19883 | 6000
500060751 | CLB-MP-LOAD-WL028 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 80034 | 19883 | 6000
500060750 | CLB-MP-LOAD-WL028 -TRNSYS-TRHLF | Trans System Hoses, Lines and Fittings | 80034 | 80034 | 6000
500060749 | CLB-MP-LOAD-WL028 -STRSYS-STHLF-STRHO | Steering System Hoses | 80034 | 19883 | 6000
500060748 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 80034 | 19883 | 6000
500060747 | CLB-MP-LOAD-WL028 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 80034 | 10046 | 6000
500060746 | CLB-MP-LOAD-WL028 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 80034 | 10046 | 6000
500060649 | CLB-MP-LOAD-WL028 -STRSYS-STNVS | Steering Neutralizer Valves | 80034 | 19883 | 6000
500059990 | CLB-MP-LOAD-WL028 -ENGINE-FNHUB | Engine Fan Hub | 80034 | 11272 | 6000
500044377 | CLB-MP-LOAD-WL028 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 80034 | 80034 | 6000
500044376 | CLB-MP-LOAD-WL028 -STRUCT-BUCKT | Bucket | 80034 | 80034 | 6000
500044375 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-LNKGE | Linkage | 80034 | 80034 | 6000
500044374 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-LIARM | Lift Arm | 80034 | 37765 | 6000
500044373 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-ARTIC | Articulation | 80034 | 3927 | 6000
500044372 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-REFRM | Rear Frame | 80034 | 80034 | 6000
500044371 | CLB-MP-LOAD-WL028 -STRUCT-CHASS-FRFRM | Front Frame | 80034 | 80034 | 6000
500044370 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SBELT | Seat Belt | 80034 | 59812 | 6000
500044369 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-SEATS | Operators Seat | 80034 | 3928 | 6000
500044368 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 80034 | 80034 | 6000
500044367 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 80034 | 19883 | 6000
500044366 | CLB-MP-LOAD-WL028 -STRUCT-CABIN-AIRCN | Air Conditioning System | 80034 | 19883 | 6000
500044365 | CLB-MP-LOAD-WL028 -STRUCT-CABIN | Operators Cabin | 80034 | 80034 | 6000
500044364 | CLB-MP-LOAD-WL028 -GRSYST-ALBPP | Auto Lube Pump | 80034 | 2183 | 6000
500044363 | CLB-MP-LOAD-WL028 -GRSYST-GRINJ | Auto Lube Injectors | 80034 | 80034 | 6000
500044362 | CLB-MP-LOAD-WL028 -PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 80034 | 19883 | 6000
500044361 | CLB-MP-LOAD-WL028 -PNEUMC-START | Starter Motor Air | 80034 | 11271 | 6000
500044360 | CLB-MP-LOAD-WL028 -HYDSYS-PACCM | Pilot Accumulator | 80034 | 19883 | 6000
500044359 | CLB-MP-LOAD-WL028 -HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 80034 | 8830 | 6000
500044358 | CLB-MP-LOAD-WL028 -HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 80034 | 8830 | 6000
500044357 | CLB-MP-LOAD-WL028 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 80034 | 10046 | 6000
500044356 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 80034 | 7379 | 6000
500044355 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 80034 | 7256 | 6000
500044354 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 80034 | 4358 | 6000
500044353 | CLB-MP-LOAD-WL028 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 80034 | 8837 | 6000
500044352 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 80034 | 8830 | 6000
500044351 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 80034 | 8830 | 6000
500044350 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 80034 | 8830 | 6000
500044349 | CLB-MP-LOAD-WL028 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 80034 | 8830 | 6000
500044348 | CLB-MP-LOAD-WL028 -STRSYS-STBOC | Steering And Brake Oil Cooler | 80034 | 59812 | 6000
500044347 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 80034 | 11632 | 6000
500044346 | CLB-MP-LOAD-WL028 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 80034 | 16614 | 6000
500044345 | CLB-MP-LOAD-WL028 -STRSYS-STIPV | STIC Steering Pilot Valve | 80034 | 48900 | 6000
500044344 | CLB-MP-LOAD-WL028 -STRSYS-STVLV | Valve Steering | 80034 | 80034 | 6000
500044343 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 80034 | 3452 | 6000
500044342 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 80034 | 19883 | 6000
500044341 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP02 | Steering Pump RH | 80034 | 8272 | 6000
500044340 | CLB-MP-LOAD-WL028 -STRSYS-STPMP-STP01 | Steering Pump LH | 80034 | 8272 | 6000
500044339 | CLB-MP-LOAD-WL028 -BRKSYS-BROCC | Brake Oil Cooler | 80034 | 19883 | 6000
500044338 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 80034 | 19883 | 6000
500044337 | CLB-MP-LOAD-WL028 -BRKSYS-BRACC-BACCF | Front Brake Accumulator | 80034 | 19883 | 6000
500044336 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 80034 | 3452 | 6000
500044335 | CLB-MP-LOAD-WL028 -BRKSYS-BRPMP-BRP01 | Brake Pump | 80034 | 19883 | 6000
500044334 | CLB-MP-LOAD-WL028 -BRKSYS-BRPRK | Park Brake Assembly | 80034 | 3017 | 6000
500044333 | CLB-MP-LOAD-WL028 -BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 80034 | 59812 | 6000
500044332 | CLB-MP-LOAD-WL028 -BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 80034 | 59812 | 6000
500044331 | CLB-MP-LOAD-WL028 -BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 80034 | 59812 | 6000
500044330 | CLB-MP-LOAD-WL028 -BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 80034 | 59812 | 6000
500044329 | CLB-MP-LOAD-WL028 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 80034 | 80034 | 6000
500044328 | CLB-MP-LOAD-WL028 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 80034 | 80034 | 6000
500044327 | CLB-MP-LOAD-WL028 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 80034 | 80034 | 6000
500044326 | CLB-MP-LOAD-WL028 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 80034 | 80034 | 6000
500044325 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 80034 | 5825 | 6000
500044324 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 80034 | 3452 | 6000
500044323 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 80034 | 2615 | 6000
500044322 | CLB-MP-LOAD-WL028 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 80034 | 4877 | 6000
500044321 | CLB-MP-LOAD-WL028 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 80034 | 19883 | 6000
500044320 | CLB-MP-LOAD-WL028 -FDRSYS-RRDIF | Rear Differential | 80034 | 19883 | 6000
500044319 | CLB-MP-LOAD-WL028 -FDRSYS-FRDIF | Front Differential | 80034 | 19883 | 6000
500044318 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 80034 | 19883 | 6000
500044317 | CLB-MP-LOAD-WL028 -TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 80034 | 19883 | 6000
500044316 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 80034 | 11272 | 6000
500044315 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 80034 | 3017 | 6000
500044314 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 80034 | 10044 | 6000
500044313 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 80034 | 10046 | 6000
500044312 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 80034 | 10046 | 6000
500044311 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 80034 | 10044 | 6000
500044310 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 80034 | 19883 | 6000
500044309 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 80034 | 8272 | 6000
500044308 | CLB-MP-LOAD-WL028 -TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 80034 | 3452 | 6000
500044307 | CLB-MP-LOAD-WL028 -TRNSYS-TROLC | Transmission Oil Cooler | 80034 | 19883 | 6000
500044306 | CLB-MP-LOAD-WL028 -TRNSYS-TRPMP | Pump Transmission Charge | 80034 | 3452 | 6000
500044305 | CLB-MP-LOAD-WL028 -TRNSYS-TRQUE | Torque Converter | 80034 | 19883 | 6000
500044304 | CLB-MP-LOAD-WL028 -TRNSYS-TRANS | Transmission | 80034 | 3452 | 6000
500044303 | CLB-MP-LOAD-WL028 -ELCTLV-CHARG-ALTER | Alternator 24V RH | 80034 | 3452 | 6000
500044302 | CLB-MP-LOAD-WL028 -ELCTLV-CHARG-ALTEL | Alternator 24V LH | 80034 | 11272 | 6000
500044301 | CLB-MP-LOAD-WL028 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 80034 | 11272 | 6000
500044300 | CLB-MP-LOAD-WL028 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 80034 | 11272 | 6000
500044299 | CLB-MP-LOAD-WL028 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 80034 | 80034 | 6000
500044298 | CLB-MP-LOAD-WL028 -ENGINE-INTEX-AFTER | Aftercooler | 80034 | 59812 | 6000
500044297 | CLB-MP-LOAD-WL028 -ENGINE-INTEX-TBORR | Turbocharger RH Rear | 80034 | 11272 | 6000
500044296 | CLB-MP-LOAD-WL028 -ENGINE-INTEX-TBORF | Turbocharger RH Front | 80034 | 11272 | 6000
500044295 | CLB-MP-LOAD-WL028 -ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 80034 | 11272 | 6000
500044294 | CLB-MP-LOAD-WL028 -ENGINE-INTEX-TBOLF | Turbocharger LH Front | 80034 | 11272 | 6000
500044293 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-THERM | Thermostats-Regulators | 80034 | 11272 | 6000
500044292 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 80034 | 11272 | 6000
500044291 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-COFAN | Fan Cooling System | 80034 | 37854 | 6000
500044290 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-RADTR | Radiator Coolant | 80034 | 37765 | 5700
500044289 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-RADTR | Radiator Engine | 80034 | 10046 | 6000
500044288 | CLB-MP-LOAD-WL028 -ENGINE-COSYS-WTRPP | Water Pump Engine | 80034 | 11272 | 6000
500044287 | CLB-MP-LOAD-WL028 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 80034 | 59812 | 6000
500044286 | CLB-MP-LOAD-WL028 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 80034 | 10046 | 6000
500044285 | CLB-MP-LOAD-WL028 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 80034 | 59812 | 6000
500044284 | CLB-MP-LOAD-WL028 -ENGINE-COMPR | Air Compressor | 80034 | 59812 | 6000
500044282 | CLB-MP-LOAD-WL028 -ENGINE | Engine Assembly Caterpillar 3516B | 80034 | 11272 | 6000
500042585 | CLB-MP-LOAD-WL028 | WL028 Lubrication & Mechanical Services | 80034 | 80034 | 6000
500042584 | CLB-MP-LOAD-WL028 | Caterpillar 994H Wheel Loader WL028 | 80034 | 80034 | 6000
500159030 | CLB-MP-LOAD-WL027 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 81297 | 11450 | 6000
500148503 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC | Brake Accumulator RH | 15300 | 15300 | 6000
500148502 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC | Brake Accumulator LH | 15300 | 15300 | 6000
500102510 | CLB-MP-LOAD-WL027 -TRNSYS-TRTRF | Transmission Transfer Case | 81297 | 15300 | 6000
500079115 | CLB-MP-LOAD-WL027 -GRSYST-FFGHO | Front Frame - Grease Hoses | 81297 | 15300 | 6000
500077964 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 81297 | 20362 | 6000
500077963 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 81297 | 15300 | 6000
500077962 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 81297 | 15300 | 6000
500077961 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 81297 | 19944 | 6000
500073566 | CLB-MP-LOAD-WL027 -PNEUMC | Main Airhoses/Relay | 81297 | 37608 | 6000
500067434 | CLB-MP-LOAD-WL027 -STRSYS-STTNK | Stering and brake tank | 81297 | 15300 | 6000
500065266 | CLB-MP-LOAD-WL027 -HYDSYS-HDTNK-HYT01 | WL027 Hydraulic Tank | 81297 | 15300 | 6000
500063974 | CLB-MP-LOAD-WL027 -ELCTLV-HARNS | Electrical Harness Low Voltage | 81297 | 15300 | 6000
500060745 | CLB-MP-LOAD-WL027 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 81297 | 37608 | 6000
500060744 | CLB-MP-LOAD-WL027 -TRNSYS-TRHLF | Trans System Hoses, Lines and Fittings | 81297 | 81297 | 6000
500060743 | CLB-MP-LOAD-WL027 -STRSYS-STHLF-STRHO | Steering System Hoses | 81297 | 15300 | 6000
500060742 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 81297 | 15300 | 6000
500060741 | CLB-MP-LOAD-WL027 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 81297 | 15300 | 6000
500060740 | CLB-MP-LOAD-WL027 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 81297 | 15300 | 6000
500060648 | CLB-MP-LOAD-WL027 -STRSYS-STNVS | Steering Neutralizer Valves | 81297 | 15300 | 6000
500059989 | CLB-MP-LOAD-WL027 -ENGINE-FNHUB | Engine Fan Hub | 81297 | 2178 | 6000
500044281 | CLB-MP-LOAD-WL027 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 81297 | 81297 | 6000
500044280 | CLB-MP-LOAD-WL027 -STRUCT-BUCKT | Bucket | 81297 | 81297 | 6000
500044279 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-LNKGE | Linkage | 81297 | 81297 | 6000
500044278 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-LIARM | Lift Arm | 81297 | 15300 | 6000
500044277 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-ARTIC | Articulation | 81297 | 15300 | 6000
500044276 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-REFRM | Rear Frame | 81297 | 81297 | 6000
500044275 | CLB-MP-LOAD-WL027 -STRUCT-CHASS-FRFRM | Front Frame | 81297 | 81297 | 6000
500044274 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SBELT | Seat Belt | 81297 | 81297 | 6000
500044273 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-SEATS | Operators Seat | 81297 | 6005 | 6000
500044272 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81297 | 81297 | 6000
500044271 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 81297 | 15300 | 6000
500044270 | CLB-MP-LOAD-WL027 -STRUCT-CABIN-AIRCN | Air Conditioning System | 81297 | 15300 | 6000
500044269 | CLB-MP-LOAD-WL027 -STRUCT-CABIN | Operators Cabin | 81297 | 15300 | 6000
500044268 | CLB-MP-LOAD-WL027 -GRSYST-ALBPP | Auto Lube Pump | 81297 | 6005 | 6000
500044267 | CLB-MP-LOAD-WL027 -GRSYST-GRINJ | Auto Lube Injectors | 81297 | 15300 | 6000
500044266 | CLB-MP-LOAD-WL027 -PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 81297 | 81297 | 6000
500044265 | CLB-MP-LOAD-WL027 -PNEUMC-START | Starter Motor Air | 81297 | 2178 | 6000
500044264 | CLB-MP-LOAD-WL027 -HYDSYS-PACCM | Pilot Accumulator | 81297 | 15300 | 6000
500044263 | CLB-MP-LOAD-WL027 -HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 81297 | 15300 | 6000
500044262 | CLB-MP-LOAD-WL027 -HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 81297 | 15300 | 6000
500044261 | CLB-MP-LOAD-WL027 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81297 | 15300 | 6000
500044260 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 81297 | 3926 | 6000
500044259 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 81297 | 11532 | 6000
500044258 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 81297 | 3932 | 6000
500044257 | CLB-MP-LOAD-WL027 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 81297 | 10089 | 6000
500044256 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 81297 | 2179 | 6000
500044255 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 81297 | 8425 | 6000
500044254 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 81297 | 8425 | 6000
500044253 | CLB-MP-LOAD-WL027 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 81297 | 8428 | 6000
500044252 | CLB-MP-LOAD-WL027 -STRSYS-STBOC | Steering And Brake Oil Cooler | 81297 | 81297 | 6000
500044251 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 81297 | 10741 | 6000
500044250 | CLB-MP-LOAD-WL027 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 81297 | 9807 | 6000
500044249 | CLB-MP-LOAD-WL027 -STRSYS-STIPV | STIC Steering Pilot Valve | 81297 | 5987 | 6000
500044248 | CLB-MP-LOAD-WL027 -STRSYS-STVLV | Valve Steering | 81297 | 15300 | 6000
500044247 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 81297 | 15300 | 6000
500044246 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 81297 | 15300 | 6000
500044245 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP02 | Steering Pump RH | 81297 | 15300 | 6000
500044244 | CLB-MP-LOAD-WL027 -STRSYS-STPMP-STP01 | Steering Pump LH | 81297 | 25586 | 6000
500044243 | CLB-MP-LOAD-WL027 -BRKSYS-BROCC | Brake Oil Cooler | 81297 | 17162 | 6000
500044242 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 81297 | 15300 | 6000
500044241 | CLB-MP-LOAD-WL027 -BRKSYS-BRACC-BACCF | Front Brake Accumulator | 81297 | 15300 | 6000
500044240 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 81297 | 11532 | 6000
500044239 | CLB-MP-LOAD-WL027 -BRKSYS-BRPMP-BRP01 | Brake Pump | 81297 | 5170 | 6000
500044238 | CLB-MP-LOAD-WL027 -BRKSYS-BRPRK | Park Brake Assembly | 81297 | 4486 | 6000
500044237 | CLB-MP-LOAD-WL027 -BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 81297 | 81297 | 6000
500044236 | CLB-MP-LOAD-WL027 -BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 81297 | 81297 | 6000
500044235 | CLB-MP-LOAD-WL027 -BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 81297 | 81297 | 6000
500044234 | CLB-MP-LOAD-WL027 -BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 81297 | 81297 | 6000
500044233 | CLB-MP-LOAD-WL027 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 81297 | 81297 | 6000
500044232 | CLB-MP-LOAD-WL027 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 81297 | 81297 | 6000
500044231 | CLB-MP-LOAD-WL027 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 81297 | 81297 | 6000
500044230 | CLB-MP-LOAD-WL027 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 81297 | 81297 | 6000
500044229 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 81297 | 20356 | 6000
500044228 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 81297 | 20356 | 6000
500044227 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 81297 | 3932 | 6000
500044226 | CLB-MP-LOAD-WL027 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 81297 | 6952 | 6000
500044225 | CLB-MP-LOAD-WL027 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 81297 | 20356 | 6000
500044224 | CLB-MP-LOAD-WL027 -FDRSYS-RRDIF | Rear Differential | 81297 | 20356 | 6000
500044223 | CLB-MP-LOAD-WL027 -FDRSYS-FRDIF | Front Differential | 81297 | 15300 | 6000
500044222 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 81297 | 15300 | 6000
500044221 | CLB-MP-LOAD-WL027 -TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 81297 | 20356 | 6000
500044220 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 81297 | 15300 | 6000
500044219 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 81297 | 15300 | 6000
500044218 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 81297 | 15300 | 6000
500044217 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 81297 | 11142 | 6000
500044216 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 81297 | 15300 | 6000
500044215 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 81297 | 15300 | 6000
500044214 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 81297 | 20356 | 6000
500044213 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 81297 | 9807 | 6000
500044212 | CLB-MP-LOAD-WL027 -TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 81297 | 20356 | 6000
500044211 | CLB-MP-LOAD-WL027 -TRNSYS-TROLC | Transmission Oil Cooler | 81297 | 15300 | 6000
500044210 | CLB-MP-LOAD-WL027 -TRNSYS-TRPMP | Pump Transmission Charge | 81297 | 7864 | 6000
500044209 | CLB-MP-LOAD-WL027 -TRNSYS-TRQUE | Torque Converter | 81297 | 15300 | 6000
500044208 | CLB-MP-LOAD-WL027 -TRNSYS-TRANS | Transmission | 81297 | 15300 | 6000
500044207 | CLB-MP-LOAD-WL027 -ELCTLV-CHARG-ALTER | Alternator 24V RH | 81297 | 2178 | 6000
500044206 | CLB-MP-LOAD-WL027 -ELCTLV-CHARG-ALTEL | Alternator 24V LH | 81297 | 2178 | 6000
500044205 | CLB-MP-LOAD-WL027 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81297 | 2178 | 6000
500044204 | CLB-MP-LOAD-WL027 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81297 | 2178 | 6000
500044203 | CLB-MP-LOAD-WL027 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 81297 | 15300 | 6000
500044202 | CLB-MP-LOAD-WL027 -ENGINE-INTEX-AFTER | Aftercooler | 81297 | 59999 | 6000
500044201 | CLB-MP-LOAD-WL027 -ENGINE-INTEX-TBORR | Turbocharger RH Rear | 81297 | 2178 | 6000
500044200 | CLB-MP-LOAD-WL027 -ENGINE-INTEX-TBORF | Turbocharger RH Front | 81297 | 2178 | 6000
500044199 | CLB-MP-LOAD-WL027 -ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 81297 | 2178 | 6000
500044198 | CLB-MP-LOAD-WL027 -ENGINE-INTEX-TBOLF | Turbocharger LH Front | 81297 | 2178 | 6000
500044197 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-THERM | Thermostats-Regulators | 81297 | 2178 | 6000
500044196 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 81297 | 2178 | 6000
500044195 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-COFAN | Fan Cooling System | 81297 | 81297 | 6000
500044194 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-RADTR | Radiator Coolant | 81297 | 15300 | 5700
500044193 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-RADTR | Radiator Engine | 81297 | 15300 | 6000
500044192 | CLB-MP-LOAD-WL027 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81297 | 2178 | 6000
500044191 | CLB-MP-LOAD-WL027 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81297 | 59999 | 6000
500044190 | CLB-MP-LOAD-WL027 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81297 | 15300 | 6000
500044189 | CLB-MP-LOAD-WL027 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81297 | 59999 | 6000
500044188 | CLB-MP-LOAD-WL027 -ENGINE-COMPR | Air Compressor | 81297 | 59999 | 6000
500044186 | CLB-MP-LOAD-WL027 -ENGINE | Engine Assembly Caterpillar 3516B | 81297 | 15300 | 6000
500042583 | CLB-MP-LOAD-WL027 | WL027 Lubrication & Mechanical Services | 81386 | 81386 | 6000
500042582 | CLB-MP-LOAD-WL027 | Caterpillar 994H Wheel Loader WL027 | 81297 | 81297 | 6000
500150697 | CLB-MP-LOAD-WL026 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 78563 | 14408 | 6000
500102509 | CLB-MP-LOAD-WL026 -TRNSYS-TRTRF | Transmission Transfer Case | 78554 | 2800 | 6000
500079114 | CLB-MP-LOAD-WL026 -GRSYST-FFGHO | Front Frame - Grease Hoses | 78554 | 16795 | 6000
500077960 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 78554 | 16795 | 6000
500077959 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 78554 | 16795 | 6000
500077958 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 78554 | 16795 | 6000
500077957 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 78554 | 16795 | 6000
500073565 | CLB-MP-LOAD-WL026 -PNEUMC | Main Airhoses/Relay | 78554 | 36970 | 6000
500067433 | CLB-MP-LOAD-WL026 -STRSYS-STTNK | Stering and brake tank | 78554 | 16795 | 6000
500065265 | CLB-MP-LOAD-WL026 -HYDSYS-HDTNK-HYT01 | WL026 Hydraulic Tank | 78554 | 16795 | 6000
500063972 | CLB-MP-LOAD-WL026 -ELCTLV-HARNS | Electrical Harness Low Voltage | 78554 | 16795 | 6000
500060739 | CLB-MP-LOAD-WL026 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 78554 | 19377 | 6000
500060738 | CLB-MP-LOAD-WL026 -TRNSYS-TRHLF | Trans System Hoses, Lines and Fittings | 78554 | 78554 | 6000
500060737 | CLB-MP-LOAD-WL026 -STRSYS-STHLF-STRHO | Steering System Hoses | 78554 | 16795 | 6000
500060736 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 78554 | 16795 | 6000
500060735 | CLB-MP-LOAD-WL026 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 78554 | 16795 | 6000
500060734 | CLB-MP-LOAD-WL026 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 78554 | 16795 | 6000
500060647 | CLB-MP-LOAD-WL026 -STRSYS-STNVS | Steering Neutralizer Valves | 78554 | 16795 | 6000
500059988 | CLB-MP-LOAD-WL026 -ENGINE-FNHUB | Engine Fan Hub | 78554 | 7319 | 6000
500044185 | CLB-MP-LOAD-WL026 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 78554 | 78554 | 6000
500044184 | CLB-MP-LOAD-WL026 -STRUCT-BUCKT | Bucket | 78554 | 404 | 6000
500044183 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-LNKGE | Linkage | 78554 | 78554 | 6000
500044182 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-LIARM | Lift Arm | 78554 | 36970 | 6000
500044181 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-ARTIC | Articulation | 78554 | 20428 | 6000
500044180 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-REFRM | Rear Frame | 78554 | 78554 | 6000
500044179 | CLB-MP-LOAD-WL026 -STRUCT-CHASS-FRFRM | Front Frame | 78554 | 78554 | 6000
500044178 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SBELT | Seat Belt | 78554 | 14202 | 6000
500044177 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-SEATS | Operators Seat | 78554 | 6878 | 6000
500044176 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 78554 | 78554 | 6000
500044175 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 78554 | 16795 | 6000
500044174 | CLB-MP-LOAD-WL026 -STRUCT-CABIN-AIRCN | Air Conditioning System | 78554 | 7319 | 6000
500044173 | CLB-MP-LOAD-WL026 -STRUCT-CABIN | Operators Cabin | 78554 | 78554 | 6000
500044172 | CLB-MP-LOAD-WL026 -GRSYST-ALBPP | Auto Lube Pump | 78554 | 16795 | 6000
500044171 | CLB-MP-LOAD-WL026 -GRSYST-GRINJ | Auto Lube Injectors | 78554 | 78554 | 6000
500044170 | CLB-MP-LOAD-WL026 -PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 78554 | 78554 | 6000
500044169 | CLB-MP-LOAD-WL026 -PNEUMC-START | Starter Motor Air | 78554 | 7319 | 6000
500044168 | CLB-MP-LOAD-WL026 -HYDSYS-PACCM | Pilot Accumulator | 78554 | 16795 | 6000
500044167 | CLB-MP-LOAD-WL026 -HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 78554 | 2800 | 6000
500044166 | CLB-MP-LOAD-WL026 -HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 78554 | 16795 | 6000
500044165 | CLB-MP-LOAD-WL026 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 78554 | 2359 | 6000
500044164 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 78554 | 3032 | 6000
500044163 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 78554 | 3032 | 6000
500044162 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 78554 | 8785 | 6000
500044161 | CLB-MP-LOAD-WL026 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 78554 | 7319 | 6000
500044160 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 78554 | 16795 | 6000
500044159 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 78554 | 7319 | 6000
500044158 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 78554 | 7319 | 6000
500044157 | CLB-MP-LOAD-WL026 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 78554 | 7319 | 6000
500044156 | CLB-MP-LOAD-WL026 -STRSYS-STBOC | Steering And Brake Oil Cooler | 78554 | 39294 | 6000
500044155 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 78554 | 409 | 6000
500044154 | CLB-MP-LOAD-WL026 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 78554 | 7440 | 6000
500044153 | CLB-MP-LOAD-WL026 -STRSYS-STIPV | STIC Steering Pilot Valve | 78554 | 5570 | 6000
500044152 | CLB-MP-LOAD-WL026 -STRSYS-STVLV | Valve Steering | 78554 | 66729 | 6000
500044151 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 78554 | 16795 | 6000
500044150 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 78554 | 16795 | 6000
500044149 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP02 | Steering Pump RH | 78554 | 5988 | 6000
500044148 | CLB-MP-LOAD-WL026 -STRSYS-STPMP-STP01 | Steering Pump LH | 78554 | 16733 | 6000
500044147 | CLB-MP-LOAD-WL026 -BRKSYS-BROCC | Brake Oil Cooler | 78554 | 2359 | 6000
500044146 | CLB-MP-LOAD-WL026 -BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 78554 | 16795 | 6000
500044145 | CLB-MP-LOAD-WL026 -BRKSYS-BRACC-BACCF | Front Brake Accumulator | 78554 | 16795 | 6000
500044144 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 78554 | 9173 | 6000
500044143 | CLB-MP-LOAD-WL026 -BRKSYS-BRPMP-BRP01 | Brake Pump | 78554 | 12877 | 6000
500044142 | CLB-MP-LOAD-WL026 -BRKSYS-BRPRK | Park Brake Assembly | 78554 | 5453 | 6000
500044141 | CLB-MP-LOAD-WL026 -BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 78554 | 58681 | 6000
500044140 | CLB-MP-LOAD-WL026 -BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 78554 | 58681 | 6000
500044139 | CLB-MP-LOAD-WL026 -BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 78554 | 58681 | 6000
500044138 | CLB-MP-LOAD-WL026 -BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 78554 | 58681 | 6000
500044137 | CLB-MP-LOAD-WL026 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 78554 | 78554 | 6000
500044136 | CLB-MP-LOAD-WL026 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 78554 | 78554 | 6000
500044135 | CLB-MP-LOAD-WL026 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 78554 | 78554 | 6000
500044134 | CLB-MP-LOAD-WL026 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 78554 | 78554 | 6000
500044133 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 78554 | 9173 | 6000
500044132 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 78554 | 4238 | 6000
500044131 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 78554 | 5195 | 6000
500044130 | CLB-MP-LOAD-WL026 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 78554 | 2933 | 6000
500044129 | CLB-MP-LOAD-WL026 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 78554 | 16795 | 6000
500044128 | CLB-MP-LOAD-WL026 -FDRSYS-RRDIF | Rear Differential | 78554 | 16795 | 6000
500044127 | CLB-MP-LOAD-WL026 -FDRSYS-FRDIF | Front Differential | 78554 | 16795 | 6000
500044126 | CLB-MP-LOAD-WL026 -TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 78554 | 16795 | 6000
500044125 | CLB-MP-LOAD-WL026 -TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 78554 | 10856 | 6000
500044124 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 78554 | 7319 | 6000
500044123 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 78554 | 11349 | 6000
500044122 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 78554 | 5988 | 6000
500044121 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 78554 | 5988 | 6000
500044120 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 78554 | 5988 | 6000
500044119 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 78554 | 16795 | 6000
500044118 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 78554 | 24710 | 6000
500044117 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 78554 | 9502 | 6000
500044116 | CLB-MP-LOAD-WL026 -TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 78554 | 19377 | 6000
500044115 | CLB-MP-LOAD-WL026 -TRNSYS-TROLC | Transmission Oil Cooler | 78554 | 16795 | 6000
500044114 | CLB-MP-LOAD-WL026 -TRNSYS-TRPMP | Pump Transmission Charge | 78554 | 7319 | 6000
500044113 | CLB-MP-LOAD-WL026 -TRNSYS-TRQUE | Torque Converter | 78554 | 9502 | 6000
500044112 | CLB-MP-LOAD-WL026 -TRNSYS-TRANS | Transmission | 78554 | 2800 | 6000
500044111 | CLB-MP-LOAD-WL026 -ELCTLV-CHARG-ALTER | Alternator 24V RH | 78554 | 7319 | 6000
500044110 | CLB-MP-LOAD-WL026 -ELCTLV-CHARG-ALTEL | Alternator 24V LH | 78554 | 7319 | 6000
500044109 | CLB-MP-LOAD-WL026 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 78554 | 7319 | 6000
500044108 | CLB-MP-LOAD-WL026 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 78554 | 7319 | 6000
500044107 | CLB-MP-LOAD-WL026 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 78554 | 78554 | 6000
500044106 | CLB-MP-LOAD-WL026 -ENGINE-INTEX-AFTER | Aftercooler | 78554 | 39294 | 6000
500044105 | CLB-MP-LOAD-WL026 -ENGINE-INTEX-TBORR | Turbocharger RH Rear | 78554 | 7319 | 6000
500044104 | CLB-MP-LOAD-WL026 -ENGINE-INTEX-TBORF | Turbocharger RH Front | 78554 | 7319 | 6000
500044103 | CLB-MP-LOAD-WL026 -ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 78554 | 7319 | 6000
500044102 | CLB-MP-LOAD-WL026 -ENGINE-INTEX-TBOLF | Turbocharger LH Front | 78554 | 7319 | 6000
500044101 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-THERM | Thermostats-Regulators | 78554 | 7319 | 6000
500044100 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 78554 | 7319 | 6000
500044099 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-COFAN | Fan Cooling System | 78554 | 78554 | 6000
500044098 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-RADTR | Radiator Coolant | 78554 | 16795 | 5700
500044097 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-RADTR | Radiator Engine | 78554 | 16795 | 6000
500044096 | CLB-MP-LOAD-WL026 -ENGINE-COSYS-WTRPP | Water Pump Engine | 78554 | 7319 | 6000
500044095 | CLB-MP-LOAD-WL026 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 78554 | 39294 | 6000
500044094 | CLB-MP-LOAD-WL026 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 78554 | 7319 | 6000
500044093 | CLB-MP-LOAD-WL026 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 78554 | 39294 | 6000
500044092 | CLB-MP-LOAD-WL026 -ENGINE-COMPR | Air Compressor | 78554 | 39294 | 6000
500044090 | CLB-MP-LOAD-WL026 -ENGINE | Engine Assembly Caterpillar 3516B | 78554 | 7319 | 6000
500042581 | CLB-MP-LOAD-WL026 | WL026 Lubrication & Mechanical Services | 78554 | 78554 | 6000
500042580 | CLB-MP-LOAD-WL026 | Caterpillar 994H Wheel Loader WL026 | 78554 | 78554 | 6000
500148501 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC | Brake Accumulator RH | 12244 | 12244 | 6000
500148500 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC | Brake Accumulator LH | 12244 | 12244 | 6000
500102508 | CLB-MP-LOAD-WL025 -TRNSYS-TRTRF | Transmission Transfer Case | 64740 | 12341 | 6000
500079113 | CLB-MP-LOAD-WL025 -GRSYST-FFGHO | Front Frame - Grease Hoses | 64740 | 2590 | 6000
500077956 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-AXLP4 | Axle Shaft Position 4 | 64740 | 12341 | 6000
500077955 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-AXLP3 | Axle Shaft Position 3 | 64740 | 12341 | 6000
500077954 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-AXLP2 | Axle Shaft Position 2 | 64740 | 12341 | 6000
500077953 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-AXLP1 | Axle Shaft Position 1 | 64740 | 12341 | 6000
500073564 | CLB-MP-LOAD-WL025 -PNEUMC | Main Airhoses/Relay | 64740 | 44317 | 6000
500067432 | CLB-MP-LOAD-WL025 -STRSYS-STTNK | Stering and brake tank | 64740 | 2590 | 6000
500065264 | CLB-MP-LOAD-WL025 -HYDSYS-HDTNK-HYT01 | WL025 Hydraulic Tank | 64740 | 2590 | 6000
500063971 | CLB-MP-LOAD-WL025 -ELCTLV-HARNS | Electrical Harness Low Voltage | 64740 | 2590 | 6000
500060733 | CLB-MP-LOAD-WL025 -TRNSYS-TRHLF-TRNHO | Transmission System Hoses | 64740 | 2590 | 6000
500060732 | CLB-MP-LOAD-WL025 -TRNSYS-TRHLF | Trans System Hoses, Lines and Fittings | 64740 | 64740 | 6000
500060730 | CLB-MP-LOAD-WL025 -STRSYS-STHLF-STRHO | Steering System Hoses | 64740 | 23337 | 6000
500060729 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-PILHO | Pilot System Hoses | 64740 | 12341 | 6000
500060728 | CLB-MP-LOAD-WL025 -HYDSYS-HDHLF-HYDHO | Hydraulic System Hoses | 64740 | 2590 | 6000
500060727 | CLB-MP-LOAD-WL025 -BRKSYS-BRHLF-BRKHO | Brake System Hoses | 64740 | 2590 | 6000
500060646 | CLB-MP-LOAD-WL025 -STRSYS-STNVS | Steering Neutralizer Valves | 64740 | 12341 | 6000
500059986 | CLB-MP-LOAD-WL025 -ENGINE-FNHUB | Engine Fan Hub | 64740 | 2590 | 6000
500044089 | CLB-MP-LOAD-WL025 -STRUCT-BUCKT-BWELM | Bucket Wear Elements | 64740 | 64740 | 6000
500044088 | CLB-MP-LOAD-WL025 -STRUCT-BUCKT | Bucket | 64740 | 2590 | 6000
500044087 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-LNKGE | Linkage | 64740 | 64740 | 6000
500044086 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-LIARM | Lift Arm | 64740 | 12341 | 6000
500044085 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-ARTIC | Articulation | 64740 | 13629 | 6000
500044084 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-REFRM | Rear Frame | 64740 | 64740 | 6000
500044083 | CLB-MP-LOAD-WL025 -STRUCT-CHASS-FRFRM | Front Frame | 64740 | 64740 | 6000
500044082 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SBELT | Seat Belt | 64740 | 64740 | 6000
500044081 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-SEATS | Operators Seat | 64740 | 2590 | 6000
500044080 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 64740 | 64740 | 6000
500044079 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 64740 | 2590 | 6000
500044078 | CLB-MP-LOAD-WL025 -STRUCT-CABIN-AIRCN | Air Conditioning System | 64740 | 2590 | 6000
500044077 | CLB-MP-LOAD-WL025 -STRUCT-CABIN | Operators Cabin | 64740 | 12341 | 6000
500044076 | CLB-MP-LOAD-WL025 -GRSYST-ALBPP | Auto Lube Pump | 64740 | 6152 | 6000
500044075 | CLB-MP-LOAD-WL025 -GRSYST-GRINJ | Auto Lube Injectors | 64740 | 64740 | 6000
500044074 | CLB-MP-LOAD-WL025 -PNEUMC-PNTNK-AIT01 | Air Tank Main Starting | 64740 | 64740 | 6000
500044073 | CLB-MP-LOAD-WL025 -PNEUMC-START | Starter Motor Air | 64740 | 2590 | 6000
500044072 | CLB-MP-LOAD-WL025 -HYDSYS-PACCM | Pilot Accumulator | 64740 | 2590 | 6000
500044071 | CLB-MP-LOAD-WL025 -HYDSYS-HDVLV-HYV02 | Valve Implement Control RH | 64740 | 2590 | 6000
500044070 | CLB-MP-LOAD-WL025 -HYDSYS-HDVLV-HYV01 | Valve Implement Control LH | 64740 | 2590 | 6000
500044069 | CLB-MP-LOAD-WL025 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 64740 | 2590 | 6000
500044068 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH High Lift | 64740 | 2590 | 6000
500044067 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH High Lift | 64740 | 2590 | 6000
500044066 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLR | Cylinder Hoist RH High Lift | 64740 | 2590 | 6000
500044065 | CLB-MP-LOAD-WL025 -HYDSYS-HDCYL-HCYLL | Cylinder Hoist LH High Lift | 64588 | 1336 | 6000
500044064 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP04 | Pump Hydraulic Pilot & Cooling | 64740 | 2590 | 6000
500044063 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Implement Centre | 64740 | 2590 | 6000
500044062 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Implement RH | 64740 | 2590 | 6000
500044061 | CLB-MP-LOAD-WL025 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement LH | 64740 | 9769 | 6000
500044060 | CLB-MP-LOAD-WL025 -STRSYS-STBOC | Steering And Brake Oil Cooler | 64740 | 2590 | 6000
500044059 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYR | Cylinder Steering RH | 64740 | 12341 | 6000
500044058 | CLB-MP-LOAD-WL025 -STRSYS-STRCY-STCYL | Cylinder Steering LH | 64740 | 546 | 6000
500044057 | CLB-MP-LOAD-WL025 -STRSYS-STIPV | Steering STIC Pilot Valve | 64740 | 51755 | 6000
500044056 | CLB-MP-LOAD-WL025 -STRSYS-STVLV | Valve Steering | 64740 | 64740 | 6000
500044055 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP04 | Steering Pump Secondary | 64740 | 12341 | 6000
500044054 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP03 | Steering and Brake Oil Cooler Pump | 64740 | 12341 | 6000
500044053 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP02 | Steering Pump RH | 64740 | 2590 | 6000
500044052 | CLB-MP-LOAD-WL025 -STRSYS-STPMP-STP01 | Steering Pump LH | 64740 | 2590 | 6000
500044051 | CLB-MP-LOAD-WL025 -BRKSYS-BROCC | Brake Oil Cooler | 64740 | 2590 | 6000
500044050 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC-BACCR | Rear Brake Accumulator | 64740 | 12341 | 6000
500044049 | CLB-MP-LOAD-WL025 -BRKSYS-BRACC-BACCF | Front Brake Accumulator | 64740 | 12341 | 6000
500044048 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP02 | Brake Cooling Pump | 64740 | 8466 | 6000
500044047 | CLB-MP-LOAD-WL025 -BRKSYS-BRPMP-BRP01 | Brake Pump | 64740 | 14554 | 6000
500044046 | CLB-MP-LOAD-WL025 -BRKSYS-BRPRK | Park Brake Assembly | 64740 | 2590 | 6000
500044045 | CLB-MP-LOAD-WL025 -BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 64740 | 64740 | 6000
500044044 | CLB-MP-LOAD-WL025 -BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 64740 | 64740 | 6000
500044043 | CLB-MP-LOAD-WL025 -BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 64740 | 64740 | 6000
500044042 | CLB-MP-LOAD-WL025 -BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 64740 | 64740 | 6000
500044041 | CLB-MP-LOAD-WL025 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 64740 | 64740 | 6000
500044040 | CLB-MP-LOAD-WL025 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 64740 | 64740 | 6000
500044039 | CLB-MP-LOAD-WL025 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 64740 | 64740 | 6000
500044038 | CLB-MP-LOAD-WL025 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 64740 | 64740 | 6000
500044037 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 64740 | 4453 | 6000
500044036 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 64740 | 4453 | 6000
500044035 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 64740 | 4453 | 6000
500044034 | CLB-MP-LOAD-WL025 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 64740 | 4453 | 6000
500044033 | CLB-MP-LOAD-WL025 -FDRSYS-RRDIF-TRNON | Rear Axle Housing Trunnion | 64740 | 2590 | 6000
500044032 | CLB-MP-LOAD-WL025 -FDRSYS-RRDIF | Rear Differential | 64740 | 2590 | 6000
500044031 | CLB-MP-LOAD-WL025 -FDRSYS-FRDIF | Front Differential | 64740 | 2590 | 6000
500044030 | CLB-MP-LOAD-WL025 -TRNSYS-PMPDR-RRPDR | Rear Pump Drive Gearbox | 64740 | 2590 | 6000
500044029 | CLB-MP-LOAD-WL025 -TRNSYS-PMPDR-FRPDR | Front Pump Drive Gearbox | 64740 | 2590 | 6000
500044028 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-TORCP | Driveshaft Torsional Coupling | 64740 | 2590 | 6000
500044027 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-LCTRB | Lower Drive Shaft Centre Bearing | 64740 | 2590 | 6000
500044026 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-UCTRB | Upper Drive Shaft Centre Bearing | 64740 | 4624 | 6000
500044025 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT06 | D-Shaft Front Pump Drive To Cntr Bearing | 64740 | 15246 | 6000
500044024 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT05 | D-Shaft Rear Pump Drive To Cntr Bearing | 64740 | 2590 | 6000
500044023 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 64740 | 12341 | 6000
500044022 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 64740 | 12341 | 6000
500044021 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 64740 | 2590 | 6000
500044020 | CLB-MP-LOAD-WL025 -TRNSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 64740 | 16190 | 6000
500044019 | CLB-MP-LOAD-WL025 -TRNSYS-TROLC | Transmission Oil Cooler | 64740 | 12341 | 6000
500044018 | CLB-MP-LOAD-WL025 -TRNSYS-TRPMP | Pump Transmission Charge | 64740 | 2590 | 6000
500044017 | CLB-MP-LOAD-WL025 -TRNSYS-TRQUE | Torque Converter | 64740 | 12341 | 6000
500044016 | CLB-MP-LOAD-WL025 -TRNSYS-TRANS | Transmission | 64740 | 843 | 6000
500044015 | CLB-MP-LOAD-WL025 -ELCTLV-CHARG-ALTER | Alternator 24V RH | 64740 | 2590 | 6000
500044014 | CLB-MP-LOAD-WL025 -ELCTLV-CHARG-ALTEL | Alternator 24V LH | 64740 | 2590 | 6000
500044013 | CLB-MP-LOAD-WL025 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 64740 | 2590 | 6000
500044012 | CLB-MP-LOAD-WL025 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 64740 | 2590 | 6000
500044011 | CLB-MP-LOAD-WL025 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 64740 | 64740 | 6000
500044010 | CLB-MP-LOAD-WL025 -ENGINE-INTEX-AFTER | Aftercooler | 64740 | 64740 | 6000
500044009 | CLB-MP-LOAD-WL025 -ENGINE-INTEX-TBORR | Turbocharger RH Rear | 64740 | 2590 | 6000
500044008 | CLB-MP-LOAD-WL025 -ENGINE-INTEX-TBORF | Turbocharger RH Front | 64740 | 2590 | 6000
500044007 | CLB-MP-LOAD-WL025 -ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 64740 | 2590 | 6000
500044006 | CLB-MP-LOAD-WL025 -ENGINE-INTEX-TBOLF | Turbocharger LH Front | 64740 | 2590 | 6000
500044005 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-THERM | Thermostats-Regulators | 64740 | 2590 | 6000
500044004 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 64740 | 2590 | 6000
500044003 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-COFAN | Fan Cooling System | 64740 | 64740 | 6000
500044002 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-RADTR | Radiator Coolant | 64643 | 44220 | 5700
500044001 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-RADTR | Radiator Engine | 64740 | 19532 | 6000
500044000 | CLB-MP-LOAD-WL025 -ENGINE-COSYS-WTRPP | Water Pump Engine | 64740 | 2590 | 6000
500043999 | CLB-MP-LOAD-WL025 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 64740 | 64740 | 6000
500043998 | CLB-MP-LOAD-WL025 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 64740 | 2590 | 6000
500043997 | CLB-MP-LOAD-WL025 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 64740 | 64740 | 6000
500043996 | CLB-MP-LOAD-WL025 -ENGINE-COMPR | Air Compressor | 64740 | 64740 | 6000
500043994 | CLB-MP-LOAD-WL025 -ENGINE | Engine Assembly Caterpillar 3516B | 64740 | 2590 | 6000
500042579 | CLB-MP-LOAD-WL025 | WL025 Lubrication & Mechanical Services | 64740 | 64740 | 6000
500042578 | CLB-MP-LOAD-WL025 | Caterpillar 994H Wheel Loader WL025 | 64740 | 64740 | 6000
500148487 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM | Brake Accumulator Front RH | 30649 | 30649 | 5900
500148486 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM | Brake Accumulator Front LH | 30649 | 30649 | 5900
500108423 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHMH | WD6106 Hydraulic System Hoses Main | 30649 | 30649 | 5900
500108422 | CLB-MP-DOZR-WD6106-COMMUN-RADIO | WD6106 Two Way Radio | 30649 | 30649 | 5900
500108421 | CLB-MP-DOZR-WD6106-COMMUN-FLMGT | WD6106 Fleet Management | 30649 | 10786 | 5900
500108420 | CLB-MP-DOZR-WD6106-COMMUN | WD6106 Communications | 30649 | 30649 | 5900
500108419 | CLB-MP-DOZR-WD6106-MANGMT-UMMMC | WD6106 Mine Monitoring and Control | 30649 | 30649 | 5900
500108418 | CLB-MP-DOZR-WD6106-MANGMT-UMMC | WD6106 Machine Management System | 30649 | 30649 | 5900
500108417 | CLB-MP-DOZR-WD6106-MANGMT-UMENG | WD6106 Engine Management System | 30649 | 20692 | 5900
500108416 | CLB-MP-DOZR-WD6106-MANGMT | WD6106 Unit Management | 30649 | 30649 | 5900
500108415 | CLB-MP-DOZR-WD6106-FRSUPP-FSALM | WD6106 Fire System Alarm | 30649 | 30649 | 5900
500108414 | CLB-MP-DOZR-WD6106-FRSUPP-FSMAN-EXTIN | WD6106 Hand Held Fire Extinguisher | 30649 | 30649 | 5900
500108413 | CLB-MP-DOZR-WD6106-FRSUPP-FSMAN | WD6106 Fire Suppression Manual | 30649 | 30649 | 5900
500108412 | CLB-MP-DOZR-WD6106-FRSUPP-FSAUT-FFOAM | WD6106 Fire Suppression Foam | 30649 | 30649 | 5900
500108411 | CLB-MP-DOZR-WD6106-FRSUPP-FSAUT | WD6106 Fire Suppression Automatic | 30649 | 30649 | 5900
500108410 | CLB-MP-DOZR-WD6106-FRSUPP | WD6106 Fire Suppression System | 30649 | 8882 | 5900
500108409 | CLB-MP-DOZR-WD6106-STRUCT-PLHAN | WD6106 Platforms and Handrails | 30649 | 30649 | 5900
500108408 | CLB-MP-DOZR-WD6106-STRUCT-STLAD | WD6106 Steps and Ladders | 30649 | 8882 | 5900
500108407 | CLB-MP-DOZR-WD6106-STRUCT-PNLGU | WD6106 Panels and Guards | 30649 | 30649 | 5900
500108404 | CLB-MP-DOZR-WD6106-STRUCT-BLADE | WD6106 Blade | 30649 | 8882 | 5900
500108403 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-TRNON | WD6106 Trunnion | 30649 | 30649 | 5900
500108402 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-LNKGE | WD6106 Link Stabilizer | 30649 | 30649 | 5900
500108401 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-PUARM | WD6106 Push Arm | 30649 | 30649 | 5900
500108400 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-ARTIC | WD6106 Articulation | 30649 | 8882 | 5900
500108399 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-CWEIG | WD6106 Counterweight | 30649 | 30649 | 5900
500108398 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-ROPSS | WD6106 Roll Over Protective Structure | 30649 | 30649 | 5900
500108397 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-REFRM | WD6106 Rear Frame | 30649 | 30649 | 5900
500108396 | CLB-MP-DOZR-WD6106-STRUCT-CHASS-FRFRM | WD6106 Front Frame | 30649 | 30649 | 5900
500108395 | CLB-MP-DOZR-WD6106-STRUCT-CHASS | WD6106 Chassis | 30649 | 30649 | 5900
500108394 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-GLASS | WD6106 Glass | 30649 | 30649 | 5900
500108393 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SBELT | WD6106 Seat Belt | 30649 | 30649 | 5900
500108392 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-SEATS | WD6106 Operators Seat | 30649 | 5594 | 5900
500108391 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-CABES | WD6106 Cabin Entertainment System | 30649 | 30649 | 5900
500108390 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-CABCO | WD6106 Cabin Controls | 30649 | 30649 | 5900
500108389 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-CABPR | WD6106 Cabin Pressurisation System | 30649 | 30649 | 5900
500108388 | CLB-MP-DOZR-WD6106-STRUCT-CABIN-AIRCN | WD6106 Air Conditioning System | 30649 | 8882 | 5900
500108387 | CLB-MP-DOZR-WD6106-STRUCT-CABIN | WD6106 Operators Cabin | 30649 | 8882 | 5900
500108386 | CLB-MP-DOZR-WD6106-STRUCT | WD6106 Structure | 30649 | 30649 | 5900
500108385 | CLB-MP-DOZR-WD6106-GRSYST-ALHLF | WD6106 Auto Lube Hoses Lines Fittings | 30649 | 30649 | 5900
500108384 | CLB-MP-DOZR-WD6106-GRSYST-ALELC | WD6106 Auto Lube Electrical | 30649 | 30649 | 5900
500108383 | CLB-MP-DOZR-WD6106-GRSYST-ALCON | WD6106 Auto Lube Controller | 30649 | 30649 | 5900
500108382 | CLB-MP-DOZR-WD6106-GRSYST-ALBPP | WD6106 Auto Lube Pump | 30649 | 12324 | 5900
500108381 | CLB-MP-DOZR-WD6106-GRSYST-GRTNK | WD6106 Auto Lube Reservoir | 30649 | 30649 | 5900
500108380 | CLB-MP-DOZR-WD6106-GRSYST-GRINJ | WD6106 Auto Lube Injectors | 30649 | 30649 | 5900
500108379 | CLB-MP-DOZR-WD6106-GRSYST | WD6106 Grease Lubrication System | 30649 | 8882 | 5900
500108378 | CLB-MP-DOZR-WD6106-HYDSYS-HDHLF-HDHPS | WD6106 Hyd System Hoses Pilot Sys | 30649 | 30649 | 5900
500108377 | CLB-MP-DOZR-WD6106-HYDSYS-HDCON | WD6106 Controls Hydraulic | 30649 | 30649 | 5900
500108376 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV08 | WD6106 Valve Solenoid Hydraulic Lockout | 30649 | 30649 | 5900
500108375 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV07 | WD6106 Valve Pilot Relief | 30649 | 30649 | 5900
500108374 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV06 | WD6106 Valve Make Up Hydraulic Fan | 30649 | 30649 | 5900
500108373 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV05 | WD6106 Valve Demand Hydraulic Fan | 30649 | 30649 | 5900
500108372 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV04 | WD6106 Valve Hydraulic Fan | 30649 | 30649 | 5900
500108371 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV03 | WD6106 Valve Hyd Manual Lowering Control | 30649 | 30649 | 5900
500108370 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV02 | WD6106 Valve Hydraulic Dual Tilt Control | 30649 | 30649 | 5900
500108369 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV-HYV01 | WD6106 Valve Hydraulic Main Control | 30649 | 30649 | 5900
500108368 | CLB-MP-DOZR-WD6106-HYDSYS-HDVLV | WD6106 Valves Hydraulic | 30649 | 30649 | 5900
500108367 | CLB-MP-DOZR-WD6106-HYDSYS-HDOCO | WD6106 Oil Cooler Hydraulic | 30649 | 8882 | 5900
500108366 | CLB-MP-DOZR-WD6106-HYDSYS-HDTNK | WD6106 Tank Hydraulic | 30649 | 30649 | 5900
500108365 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM02 | WD6106 Motor / Pump Axle Cooling | 30649 | 13829 | 5900
500108364 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT-HYM01 | WD6106 Motor Hydraulic Fan High Temp | 30649 | 14275 | 5900
500108363 | CLB-MP-DOZR-WD6106-HYDSYS-HYDMT | WD6106 Hydraulic Motors | 30649 | 30649 | 5900
500108362 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BTCYR | WD6106 Cylinder Blade Tilt R/H | 30649 | 8882 | 5900
500108361 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BTCYL | WD6106 Cylinder Blade Tilt L/H | 30649 | 8882 | 5900
500108360 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BLCYR | WD6106 Cylinder Blade Lift R/H | 30649 | 8882 | 5900
500108359 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL-BLCYL | WD6106 Cylinder Blade Lift L/H | 30649 | 8882 | 5900
500108358 | CLB-MP-DOZR-WD6106-HYDSYS-HDCYL | WD6106 Cylinders Hydraulic | 30649 | 30649 | 5900
500108357 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP03 | WD6106 Pump Hydraulic Fan | 30649 | 14275 | 5900
500108356 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP02 | WD6106 Pump Hydraulic Pilot | 30649 | 30649 | 5900
500108355 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP-HYP01 | WD6106 Pump Hydraulic Implement | 30649 | 14275 | 5900
500108354 | CLB-MP-DOZR-WD6106-HYDSYS-HYDPP | WD6106 Pumps Hydraulic | 30649 | 30649 | 5900
500108353 | CLB-MP-DOZR-WD6106-STRSYS-STRCY-STCYR | WD6106 Cylinder Steering R/H | 30649 | 8882 | 5900
500108352 | CLB-MP-DOZR-WD6106-STRSYS-STRCY-STCYL | WD6106 Cylinder Steering L/H | 30649 | 8882 | 5900
500108351 | CLB-MP-DOZR-WD6106-STRSYS-STRCY | WD6106 Cylinders Steering | 30649 | 30649 | 5900
500108350 | CLB-MP-DOZR-WD6106-STRSYS-STTNK | WD6106 Tank Steering | 30649 | 30649 | 5900
500108349 | CLB-MP-DOZR-WD6106-STRSYS-STHLF | WD6106 Str System Hoses Lines & Fittings | 30649 | 30649 | 5900
500108348 | CLB-MP-DOZR-WD6106-STRSYS-STCON | WD6106 Steering Controls | 30649 | 30649 | 5900
500108347 | CLB-MP-DOZR-WD6106-STRSYS-STVLV-VLV04 | WD6106 Valve Steering Neutraliser R/H | 30649 | 30649 | 5900
500108346 | CLB-MP-DOZR-WD6106-STRSYS-STVLV-VLV03 | WD6106 Valve Steering Neutraliser L/H | 30649 | 30649 | 5900
500108345 | CLB-MP-DOZR-WD6106-STRSYS-STVLV-VLV02 | WD6106 Valve Steering Pilot (STIC ) | 30649 | 30649 | 5900
500108344 | CLB-MP-DOZR-WD6106-STRSYS-STVLV-VLV01 | WD6106 Valve Steering Control | 30649 | 30649 | 5900
500108343 | CLB-MP-DOZR-WD6106-STRSYS-STVLV | WD6106 Valve Steering | 30649 | 30649 | 5900
500108342 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP03 | WD6106 Pump Str Secondary / Emergency | 30649 | 14275 | 5900
500108341 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP02 | WD6106 Pump Str Pilot / Axle Oil Cooling | 30649 | 14275 | 5900
500108340 | CLB-MP-DOZR-WD6106-STRSYS-STPMP-STP01 | WD6106 Pump Steering Main | 30649 | 14275 | 5900
500108339 | CLB-MP-DOZR-WD6106-STRSYS-STPMP | WD6106 Pumps Steering | 30649 | 30649 | 5900
500108338 | CLB-MP-DOZR-WD6106-STRSYS | WD6106 Steering System | 30649 | 30649 | 5900
500108337 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV07 | WD6106 Parking Brake Control Valve | 30649 | 30649 | 5900
500108336 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV06 | WD6106 Brake Manifold Rear | 30649 | 30649 | 5900
500108335 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV05 | WD6106 Brake Manifold Front | 30649 | 30649 | 5900
500108334 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV04 | WD6106 Brake Pump Check Valve | 30649 | 30649 | 5900
500108333 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV03 | WD6106 Park Brake Release Check Valve | 30649 | 30649 | 5900
500108332 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV02 | WD6106 Brake Accumulator Charging Valve | 30649 | 30649 | 5900
500108331 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV-VLV01 | WD6106 Service Brake Control Valve | 30649 | 30649 | 5900
500108330 | CLB-MP-DOZR-WD6106-BRKSYS-BRVLV | WD6106 Valves Brake | 30649 | 30649 | 5900
500108329 | CLB-MP-DOZR-WD6106-BRKSYS-BRHLF | WD6106 Brake System Hoses & Fittings | 30649 | 30649 | 5900
500108328 | CLB-MP-DOZR-WD6106-BRKSYS-BRPMP | WD6106 Pump Brake | 30649 | 14275 | 5900
500108327 | CLB-MP-DOZR-WD6106-BRKSYS-BRPRK | WD6106 Park Brake Assembly | 30649 | 1191 | 5900
500108326 | CLB-MP-DOZR-WD6106-BRKSYS-SRVBK-SVBRR | WD6106 Service Brake R/H Rear | 30649 | 30649 | 5900
500108325 | CLB-MP-DOZR-WD6106-BRKSYS-SRVBK-SVBLR | WD6106 Service Brake L/H Rear | 30649 | 30649 | 5900
500108324 | CLB-MP-DOZR-WD6106-BRKSYS-SRVBK-SVBRF | WD6106 Service Brake R/H Front | 30649 | 30649 | 5900
500108323 | CLB-MP-DOZR-WD6106-BRKSYS-SRVBK-SVBLF | WD6106 Service Brake L/H Front | 30649 | 30649 | 5900
500108322 | CLB-MP-DOZR-WD6106-BRKSYS-SRVBK | WD6106 Service Brake | 30649 | 30649 | 5900
500108321 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM-BACCR | WD6106 Brake Accumulator Rear | 30649 | 8882 | 5900
500108320 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM-BACCF | WD6106 Brake Accumulator Front | 30649 | 8882 | 5900
500108319 | CLB-MP-DOZR-WD6106-BRKSYS-BACCM | WD6106 Brake Accumulators | 30649 | 30649 | 5900
500108318 | CLB-MP-DOZR-WD6106-BRKSYS | WD6106 Braking System | 30649 | 30649 | 5900
500108317 | CLB-MP-DOZR-WD6106-FDRSYS-WHTYR-POS04 | WD6106 Tyre Position 4 | 30649 | 30649 | 5900
500108316 | CLB-MP-DOZR-WD6106-FDRSYS-WHTYR-POS03 | WD6106 Tyre Position 3 | 30649 | 30649 | 5900
500108315 | CLB-MP-DOZR-WD6106-FDRSYS-WHTYR-POS02 | WD6106 Tyre Position 2 | 30649 | 30649 | 5900
500108314 | CLB-MP-DOZR-WD6106-FDRSYS-WHTYR-POS01 | WD6106 Tyre Position 1 | 30649 | 30649 | 5900
500108313 | CLB-MP-DOZR-WD6106-FDRSYS-WHTYR | WD6106 Wheels Tyres and Rims | 30649 | 30649 | 5900
500108312 | CLB-MP-DOZR-WD6106-FDRSYS-AXLEC-TVLVR | WD6106 Thermal Bypass Valve Rr Axle Cool | 30649 | 30649 | 5900
500108311 | CLB-MP-DOZR-WD6106-FDRSYS-AXLEC-TVLVF | WD6106 Thermal Bypass Valve Fr Axle Cool | 30649 | 30649 | 5900
500108310 | CLB-MP-DOZR-WD6106-FDRSYS-AXLEC-OILCR | WD6106 Oil Cooler Axle Rear | 30649 | 8882 | 5900
500108309 | CLB-MP-DOZR-WD6106-FDRSYS-AXLEC | WD6106 Axle Cooling | 30649 | 30649 | 5900
500108308 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR04 | WD6106 Final Drive Position 4 | 30649 | 8882 | 5900
500108307 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR03 | WD6106 Final Drive Position 3 | 30649 | 8882 | 5900
500108306 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR02 | WD6106 Final Drive Position 2 | 30649 | 8882 | 5900
500108305 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE-FDR01 | WD6106 Final Drive Position 1 | 30649 | 8882 | 5900
500108304 | CLB-MP-DOZR-WD6106-FDRSYS-FDRVE | WD6106 Final Drives | 30649 | 30649 | 5900
500108303 | CLB-MP-DOZR-WD6106-FDRSYS-RRDIF-TRNON | WD6106 Trunnions Rear Differential | 30649 | 30649 | 5900
500108302 | CLB-MP-DOZR-WD6106-FDRSYS-RRDIF | WD6106 Rear Differential | 30649 | 599 | 5900
500108301 | CLB-MP-DOZR-WD6106-FDRSYS-FRDIF | WD6106 Front Differential | 30649 | 8882 | 5900
500108300 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT04 | WD6106 Drive Shaft Cntr Bearing to Front | 30649 | 10308 | 5900
500108299 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT03 | WD6106 Drive Shaft Trans to Cntr Bearing | 30649 | 8882 | 5900
500108298 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT02 | WD6106 Drive Shaft Trans to Rear Diff | 30649 | 10308 | 5900
500108297 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT-SHT01 | WD6106 Drive Shaft T/C to Transmission | 30649 | 10308 | 5900
500108296 | CLB-MP-DOZR-WD6106-FDRSYS-DRSHT | WD6106 Drive Shafts | 30649 | 30649 | 5900
500108295 | CLB-MP-DOZR-WD6106-FDRSYS | WD6106 Final Drive System | 30649 | 30649 | 5900
500108294 | CLB-MP-DOZR-WD6106-TRNSYS-TRHLF | WD6106 Trans System Hoses Lines Fittings | 30649 | 8882 | 5900
500108293 | CLB-MP-DOZR-WD6106-TRNSYS-TRPMP | WD6106 Pump Transmission | 30649 | 14275 | 5900
500108292 | CLB-MP-DOZR-WD6106-TRNSYS-TROLC | WD6106 Transmission Oil Cooler | 30649 | 14275 | 5900
500108291 | CLB-MP-DOZR-WD6106-TRNSYS-TRTRF | WD6106 Transmission Transfer Case | 30649 | 30649 | 5900
500108290 | CLB-MP-DOZR-WD6106-TRNSYS-TRANS | WD6106 Transmission | 30649 | 1191 | 5900
500108289 | CLB-MP-DOZR-WD6106-TRNSYS-TRQUE | WD6106 Torque Converter | 30649 | 8882 | 5900
500108288 | CLB-MP-DOZR-WD6106-TRNSYS | WD6106 Transmission System | 30649 | 30649 | 5900
500108287 | CLB-MP-DOZR-WD6106-ELCTLV-START-STMRH | WD6106 Starter Motor R/H | 30649 | 8882 | 5900
500108286 | CLB-MP-DOZR-WD6106-ELCTLV-START-STMLH | WD6106 Starter Motor L/H | 30649 | 8882 | 5900
500108285 | CLB-MP-DOZR-WD6106-ELCTLV-START | WD6106 Starting System Low Voltage | 30649 | 30649 | 5900
500108284 | CLB-MP-DOZR-WD6106-ELCTLV-CHARG-BATTY | WD6106 Batteries | 30649 | 13829 | 5900
500108283 | CLB-MP-DOZR-WD6106-ELCTLV-CHARG-ALTER | WD6106 Alternator 24V | 30649 | 8882 | 5900
500108282 | CLB-MP-DOZR-WD6106-ELCTLV-CHARG | WD6106 Charging System Low Voltage | 30649 | 30649 | 5900
500108281 | CLB-MP-DOZR-WD6106-ELCTLV-LIGHT | WD6106 Lighting Low Voltage | 30649 | 30649 | 5900
500108280 | CLB-MP-DOZR-WD6106-ELCTLV-CONTL | WD6106 Electrical Controls Low Voltage | 30649 | 30649 | 5900
500108279 | CLB-MP-DOZR-WD6106-ELCTLV-HARNS | WD6106 Electrical Harness Low Voltage | 30649 | 30649 | 5900
500108278 | CLB-MP-DOZR-WD6106-ELCTLV | WD6106 Electrical System Low Voltage 24V | 30649 | 30649 | 5900
500108277 | CLB-MP-DOZR-WD6106-ENGINE-FUSYS-FUHLF | WD6106 Fuel System Hoses & Fittings | 30649 | 30649 | 5900
500108276 | CLB-MP-DOZR-WD6106-ENGINE-FUSYS-FUINJ | WD6106 Fuel Injectors | 30649 | 8882 | 5900
500108275 | CLB-MP-DOZR-WD6106-ENGINE-FUSYS-FULTP | WD6106 Fuel Transfer Pump | 30649 | 8882 | 5900
500108274 | CLB-MP-DOZR-WD6106-ENGINE-FUSYS-FULPP | WD6106 Fuel Priming Pump | 30649 | 8882 | 5900
500108273 | CLB-MP-DOZR-WD6106-ENGINE-FUSYS-FULTK | WD6106 Fuel Tank | 30649 | 30649 | 5900
500108272 | CLB-MP-DOZR-WD6106-ENGINE-FUSYS | WD6106 Fuel System | 30649 | 30649 | 5900
500108271 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-EXHST | WD6106 Exhaust System | 30649 | 30649 | 5900
500108270 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-AFTER | WD6106 Aftercooler | 30649 | 8882 | 5900
500108269 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-TBORH | WD6106 Turbocharger R/H | 30649 | 8882 | 5900
500108268 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-TBOLH | WD6106 Turbocharger L/H | 30649 | 8882 | 5900
500108267 | CLB-MP-DOZR-WD6106-ENGINE-INTEX-AIRFL | WD6106 Air Filtration System | 30649 | 30649 | 5900
500108266 | CLB-MP-DOZR-WD6106-ENGINE-INTEX | WD6106 Intake and Exhaust System | 30649 | 30649 | 5900
500108265 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-CSHLF | WD6106 Cooling System Hoses & Fittings | 30649 | 30649 | 5900
500108264 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-THERM | WD6106 Thermostats/Regulators | 30649 | 8882 | 5900
500108263 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-BELTS | WD6106 Engine Belts | 30649 | 8882 | 5900
500108262 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-COFAN | WD6106 Cooling Fan | 30649 | 30649 | 5900
500108261 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-RADTR | WD6106 Radiator Engine | 30649 | 8882 | 5900
500108260 | CLB-MP-DOZR-WD6106-ENGINE-COSYS-WTRPP | WD6106 Water Pump Engine | 30649 | 8882 | 5900
500108259 | CLB-MP-DOZR-WD6106-ENGINE-COSYS | WD6106 Engine Cooling System | 30649 | 30649 | 5900
500108258 | CLB-MP-DOZR-WD6106-ENGINE-LUBSY-ENOLC | WD6106 Oil Cooler Engine | 30649 | 8882 | 5900
500108257 | CLB-MP-DOZR-WD6106-ENGINE-LUBSY-OILPP | WD6106 Oil Pump Engine | 30649 | 8882 | 5900
500108256 | CLB-MP-DOZR-WD6106-ENGINE-LUBSY | WD6106 Engine Lubrication System | 30649 | 30649 | 5900
500108255 | CLB-MP-DOZR-WD6106-ENGINE | WD6106 Engine Assembly Caterpillar C32 | 30649 | 8882 | 5900
500108254 | CLB-MP-DOZR-WD6106 | WD6106 Lubrication & Mechanical Services | 30649 | 30649 | 5900
500108253 | CLB-MP-DOZR-WD6106 | WD6106 Caterpillar 854K Wheel Dozer | 30649 | 30649 | 5900
500159029 | CLB-MP-DOZR-WD6105-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 55835 | 7957 | 5900
500148485 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM | Brake Accumulator Front RH | 30849 | 30849 | 5900
500148484 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM | Brake Accumulator Front LH | 30849 | 30849 | 5900
500125126 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHMH | WD6105 Hydraulic System Hoses Main | 55835 | 30849 | 5900
500125113 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF-HDHPS | WD6105 Hyd System Hoses Pilot Sys | 55835 | 30849 | 5900
500107136 | CLB-MP-DOZR-WD6105-TRNSYS-TRTRF | Transmission Transfer Case | 55835 | 35465 | 5900
500107135 | CLB-MP-DOZR-WD6105-TRNSYS-TRQUE | Torque Converter | 55835 | 294 | 5900
500107134 | CLB-MP-DOZR-WD6105-TRNSYS-TRPMP | Pump Transmission | 55835 | 7966 | 5900
500107133 | CLB-MP-DOZR-WD6105-TRNSYS-TROLC | Transmission Oil Cooler | 55835 | 7966 | 5900
500107132 | CLB-MP-DOZR-WD6105-TRNSYS-TRHLF | WD6105 Trans System Hoses Lines Fittings | 55835 | 7966 | 5900
500107131 | CLB-MP-DOZR-WD6105-TRNSYS-TRANS | Transmission | 55835 | 7966 | 5900
500107130 | CLB-MP-DOZR-WD6105-TRNSYS | Transmission System | 55835 | 55835 | 5900
500107129 | CLB-MP-DOZR-WD6105-STRUCT-STLAD | Steps and Ladders | 55835 | 55835 | 5900
500107128 | CLB-MP-DOZR-WD6105-STRUCT-PNLGU | Panels and Guards | 55835 | 55835 | 5900
500107127 | CLB-MP-DOZR-WD6105-STRUCT-PLHAN | Platforms and Handrails | 55835 | 55835 | 5900
500107126 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-TRNON | Trunnion | 55835 | 55835 | 5900
500107125 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 55835 | 55835 | 5900
500107124 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-REFRM | Rear Frame | 55835 | 55835 | 5900
500107123 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-PUARM | Push Arm | 55835 | 55835 | 5900
500107122 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-LNKGE | Link Stabilizer | 55835 | 55835 | 5900
500107121 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-FRFRM | Front Frame | 55835 | 55835 | 5900
500107120 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-CWEIG | Counterweight | 55835 | 55835 | 5900
500107119 | CLB-MP-DOZR-WD6105-STRUCT-CHASS-ARTIC | Articulation | 55835 | 30849 | 5900
500107118 | CLB-MP-DOZR-WD6105-STRUCT-CHASS | Chassis | 55835 | 55835 | 5900
500107117 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-SEATS | WD6105 Operators Seat | 55835 | 3274 | 5900
500107116 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-SBELT | Seat Belt | 55835 | 55835 | 5900
500107115 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-GLASS | Glass | 55835 | 55835 | 5900
500107114 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 55835 | 55835 | 5900
500107113 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-CABES | Cabin Entertainment System | 55835 | 55835 | 5900
500107112 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-CABCO | Cabin Controls | 55835 | 55835 | 5900
500107111 | CLB-MP-DOZR-WD6105-STRUCT-CABIN-AIRCN | Air Conditioning System | 55835 | 7966 | 5900
500107110 | CLB-MP-DOZR-WD6105-STRUCT-CABIN | Operators Cabin | 55835 | 7966 | 5900
500107107 | CLB-MP-DOZR-WD6105-STRUCT-BLADE | Blade | 55835 | 7966 | 5900
500107106 | CLB-MP-DOZR-WD6105-STRUCT | Structure | 55835 | 55835 | 5900
500107105 | CLB-MP-DOZR-WD6105-STRSYS-STVLV-VLV04 | Valve Steering Neutraliser R/H | 55835 | 55835 | 5900
500107104 | CLB-MP-DOZR-WD6105-STRSYS-STVLV-VLV03 | Valve Steering Neutraliser L/H | 55835 | 55835 | 5900
500107103 | CLB-MP-DOZR-WD6105-STRSYS-STVLV-VLV02 | Valve Steering Pilot (STIC Steering) | 55835 | 55835 | 5900
500107102 | CLB-MP-DOZR-WD6105-STRSYS-STVLV-VLV01 | Valve Steering Control | 55835 | 55835 | 5900
500107101 | CLB-MP-DOZR-WD6105-STRSYS-STVLV | Valve Steering | 55835 | 55835 | 5900
500107100 | CLB-MP-DOZR-WD6105-STRSYS-STTNK | Tank Steering | 55835 | 55835 | 5900
500107099 | CLB-MP-DOZR-WD6105-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 55835 | 7966 | 5900
500107098 | CLB-MP-DOZR-WD6105-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 55835 | 7966 | 5900
500107097 | CLB-MP-DOZR-WD6105-STRSYS-STRCY | Cylinders Steering | 55835 | 55835 | 5900
500107096 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP03 | Pump Steering Secondary / Emergency | 55835 | 9760 | 5900
500107095 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP02 | Pump Steering Pilot / Axle Oil Cooling | 55835 | 7966 | 5900
500107094 | CLB-MP-DOZR-WD6105-STRSYS-STPMP-STP01 | Pump Steering Main | 55835 | 7966 | 5900
500107093 | CLB-MP-DOZR-WD6105-STRSYS-STPMP | Pumps Steering | 55835 | 55835 | 5900
500107092 | CLB-MP-DOZR-WD6105-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 55835 | 30849 | 5900
500107091 | CLB-MP-DOZR-WD6105-STRSYS-STCON | Steering Controls | 55835 | 55835 | 5900
500107090 | CLB-MP-DOZR-WD6105-STRSYS | Steering System | 55835 | 55835 | 5900
500107089 | CLB-MP-DOZR-WD6105-MANGMT-UMMMC | Mine Monitoring and Control | 55835 | 55835 | 5900
500107088 | CLB-MP-DOZR-WD6105-MANGMT-UMMC | Machine Management System | 55835 | 55835 | 5900
500107087 | CLB-MP-DOZR-WD6105-MANGMT-UMENG | Engine Management System | 55835 | 55835 | 5900
500107086 | CLB-MP-DOZR-WD6105-MANGMT | Unit Management | 55835 | 55835 | 5900
500107085 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 55835 | 304 | 5900
500107084 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot | 55835 | 30849 | 5900
500107083 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 55835 | 297 | 5900
500107082 | CLB-MP-DOZR-WD6105-HYDSYS-HYDPP | Pumps Hydraulic | 55835 | 55835 | 5900
500107081 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM02 | Motor / Pump Axle Cooling | 55835 | 304 | 5900
500107080 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 55835 | 16081 | 5900
500107079 | CLB-MP-DOZR-WD6105-HYDSYS-HYDMT | Hydraulic Motors | 55835 | 55835 | 5900
500107078 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV08 | Valve Solenoid Hydraulic Lockout | 55835 | 55835 | 5900
500107077 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV07 | Valve Pilot Relief | 55835 | 55835 | 5900
500107076 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV06 | Valve Make Up Hydraulic Fan | 55835 | 55835 | 5900
500107075 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV05 | Valve Demand Hydraulic Fan | 55835 | 55835 | 5900
500107074 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV04 | Valve Hydraulic Fan | 55835 | 55835 | 5900
500107073 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV03 | Valve Hydraulic Manual Lowering Control | 55835 | 55835 | 5900
500107072 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV02 | Valve Hydraulic Dual Tilt Control | 55835 | 55835 | 5900
500107071 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV-HYV01 | Valve Hydraulic Main Control | 55835 | 55835 | 5900
500107070 | CLB-MP-DOZR-WD6105-HYDSYS-HDVLV | Valves Hydraulic | 55835 | 55835 | 5900
500107069 | CLB-MP-DOZR-WD6105-HYDSYS-HDTNK | Tank Hydraulic | 55835 | 55835 | 5900
500107068 | CLB-MP-DOZR-WD6105-HYDSYS-HDOCO | Oil Cooler Hydraulic | 55835 | 30849 | 5900
500107067 | CLB-MP-DOZR-WD6105-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 55835 | 30849 | 5900
500107066 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 55835 | 18716 | 5900
500107065 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 55835 | 6342 | 5900
500107064 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 55835 | 6342 | 5900
500107063 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 55835 | 6342 | 5900
500107062 | CLB-MP-DOZR-WD6105-HYDSYS-HDCYL | Cylinders Hydraulic | 55835 | 55835 | 5900
500107061 | CLB-MP-DOZR-WD6105-HYDSYS-HDCON | Controls Hydraulic | 55835 | 55835 | 5900
500107060 | CLB-MP-DOZR-WD6105-HYDSYS | Hydraulic System | 55835 | 55835 | 5900
500107059 | CLB-MP-DOZR-WD6105-GRSYST-GRTNK | Auto Lube Reservoir | 55835 | 55835 | 5900
500107058 | CLB-MP-DOZR-WD6105-GRSYST-GRINJ | Auto Lube Injectors | 55835 | 55835 | 5900
500107057 | CLB-MP-DOZR-WD6105-GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 55835 | 55835 | 5900
500107056 | CLB-MP-DOZR-WD6105-GRSYST-ALELC | Auto Lube Electrical | 55835 | 55835 | 5900
500107055 | CLB-MP-DOZR-WD6105-GRSYST-ALCON | Auto Lube Controller | 55835 | 55835 | 5900
500107054 | CLB-MP-DOZR-WD6105-GRSYST-ALBPP | Auto Lube Pump | 55835 | 55835 | 5900
500107053 | CLB-MP-DOZR-WD6105-GRSYST | Grease Lubrication System | 55835 | 7966 | 5900
500107052 | CLB-MP-DOZR-WD6105-FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 55835 | 55835 | 5900
500107051 | CLB-MP-DOZR-WD6105-FRSUPP-FSMAN | Fire Suppression Manual | 55835 | 55835 | 5900
500107050 | CLB-MP-DOZR-WD6105-FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 55835 | 55835 | 5900
500107049 | CLB-MP-DOZR-WD6105-FRSUPP-FSAUT | Fire Suppression Automatic | 55835 | 55835 | 5900
500107048 | CLB-MP-DOZR-WD6105-FRSUPP-FSALM | Fire System Alarm | 55835 | 55835 | 5900
500107047 | CLB-MP-DOZR-WD6105-FRSUPP | Fire Suppression System | 55835 | 30849 | 5900
500107046 | CLB-MP-DOZR-WD6105-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 55835 | 55835 | 5900
500107045 | CLB-MP-DOZR-WD6105-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 55835 | 55835 | 5900
500107044 | CLB-MP-DOZR-WD6105-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 55835 | 55835 | 5900
500107043 | CLB-MP-DOZR-WD6105-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 55835 | 55835 | 5900
500107042 | CLB-MP-DOZR-WD6105-FDRSYS-WHTYR | Wheels Tyres and Rims | 55835 | 55835 | 5900
500107041 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF-TRNON | Trunnions Rear Differential | 55835 | 14684 | 5900
500107040 | CLB-MP-DOZR-WD6105-FDRSYS-RRDIF | Rear Differential | 55835 | 14684 | 5900
500107039 | CLB-MP-DOZR-WD6105-FDRSYS-FRDIF | Front Differential | 55835 | 7966 | 5900
500107038 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 55835 | 7966 | 5900
500107037 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 55835 | 7966 | 5900
500107036 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 55835 | 7966 | 5900
500107035 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 55835 | 7966 | 5900
500107034 | CLB-MP-DOZR-WD6105-FDRSYS-FDRVE | Final Drives | 55835 | 55835 | 5900
500107033 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 55835 | 13525 | 5900
500107032 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 55835 | 13525 | 5900
500107031 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 55835 | 13525 | 5900
500107030 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 55835 | 7966 | 5900
500107029 | CLB-MP-DOZR-WD6105-FDRSYS-DRSHT | Drive Shafts | 55835 | 55835 | 5900
500107028 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC-TVLVR | Thermal Bypass Valve Rear Axle Cooling | 55835 | 55835 | 5900
500107027 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC-TVLVF | Thermal Bypass Valve Front Axle Cooling | 55835 | 55835 | 5900
500107026 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC-OILCR | Oil Cooler Axle Rear | 55835 | 55835 | 5900
500107025 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC-OILCF | Oil Cooler Axle Front | 55835 | 30849 | 5900
500107024 | CLB-MP-DOZR-WD6105-FDRSYS-AXLEC | Axle Cooling | 55835 | 16081 | 5900
500107023 | CLB-MP-DOZR-WD6105-FDRSYS | Final Drive System | 55835 | 55835 | 5900
500107022 | CLB-MP-DOZR-WD6105-ENGINE-LUBSY-OILPP | Oil Pump Engine | 55835 | 55835 | 5900
500107021 | CLB-MP-DOZR-WD6105-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 55835 | 55835 | 5900
500107020 | CLB-MP-DOZR-WD6105-ENGINE-LUBSY | Engine Lubrication System | 55835 | 55835 | 5900
500107019 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-TBORH | Turbocharger R/H | 55835 | 16081 | 5900
500107018 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-TBOLH | Turbocharger L/H | 55835 | 5316 | 5900
500107017 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-EXHST | Exhaust System | 55835 | 30849 | 5900
500107016 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AIRFL | Air Filtration System | 55835 | 7966 | 5900
500107015 | CLB-MP-DOZR-WD6105-ENGINE-INTEX-AFTER | Aftercooler | 55835 | 7966 | 5900
500107014 | CLB-MP-DOZR-WD6105-ENGINE-INTEX | Intake and Exhaust System | 55835 | 55835 | 5900
500107013 | CLB-MP-DOZR-WD6105-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 55835 | 16081 | 5900
500107012 | CLB-MP-DOZR-WD6105-ENGINE-FUSYS-FULTK | Fuel Tank | 55835 | 55835 | 5900
500107011 | CLB-MP-DOZR-WD6105-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 55835 | 55835 | 5900
500107010 | CLB-MP-DOZR-WD6105-ENGINE-FUSYS-FUINJ | Fuel Injectors | 55835 | 16081 | 5900
500107009 | CLB-MP-DOZR-WD6105-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines and Fittings | 55835 | 55835 | 5900
500107008 | CLB-MP-DOZR-WD6105-ENGINE-FUSYS | Fuel System | 55835 | 55835 | 5900
500107007 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-WTRPP | Water Pump Engine | 55835 | 12418 | 5900
500107006 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-THERM | Thermostats/Regulators | 55835 | 16081 | 5900
500107005 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-RADTR | Radiator Engine | 55835 | 7966 | 5900
500107004 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-CSHLF | Cooling System Hoses Lines and Fittings | 55835 | 16081 | 5900
500107003 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-COFAN | Cooling Fan | 55835 | 55835 | 5900
500107002 | CLB-MP-DOZR-WD6105-ENGINE-COSYS-BELTS | Engine Belts | 55835 | 55835 | 5900
500107001 | CLB-MP-DOZR-WD6105-ENGINE-COSYS | Engine Cooling System | 55835 | 55835 | 5900
500107000 | CLB-MP-DOZR-WD6105-ENGINE | Engine Assembly Caterpillar C32 | 55835 | 7966 | 5900
500106999 | CLB-MP-DOZR-WD6105-ELCTLV-START-STMRH | Starter Motor R/H | 55835 | 16081 | 5900
500106998 | CLB-MP-DOZR-WD6105-ELCTLV-START-STMLH | Starter Motor L/H | 55835 | 16081 | 5900
500106997 | CLB-MP-DOZR-WD6105-ELCTLV-START | Starting System Low Voltage | 55835 | 55835 | 5900
500106996 | CLB-MP-DOZR-WD6105-ELCTLV-LIGHT | Lighting Low Voltage | 55835 | 55835 | 5900
500106995 | CLB-MP-DOZR-WD6105-ELCTLV-HARNS | Electrical Harness Low Voltage | 55835 | 55835 | 5900
500106994 | CLB-MP-DOZR-WD6105-ELCTLV-CONTL | Electrical Controls Low Voltage | 55835 | 55835 | 5900
500106993 | CLB-MP-DOZR-WD6105-ELCTLV-CHARG-BATTY | Batteries | 55835 | 16703 | 5900
500106992 | CLB-MP-DOZR-WD6105-ELCTLV-CHARG-ALTER | Alternator 24V | 55835 | 12372 | 5900
500106991 | CLB-MP-DOZR-WD6105-ELCTLV-CHARG | Charging System Low Voltage | 55835 | 55835 | 5900
500106990 | CLB-MP-DOZR-WD6105-ELCTLV | Electrical System Low Voltage 24V | 55835 | 55835 | 5900
500106989 | CLB-MP-DOZR-WD6105-COMMUN-RADIO | Two Way Radio | 55835 | 55835 | 5900
500106988 | CLB-MP-DOZR-WD6105-COMMUN-FLMGT | Fleet Management | 55835 | 55835 | 5900
500106987 | CLB-MP-DOZR-WD6105-COMMUN | Communications | 55835 | 55835 | 5900
500106986 | CLB-MP-DOZR-WD6105-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 55835 | 55835 | 5900
500106985 | CLB-MP-DOZR-WD6105-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 55835 | 55835 | 5900
500106984 | CLB-MP-DOZR-WD6105-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 55835 | 55835 | 5900
500106983 | CLB-MP-DOZR-WD6105-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 55835 | 55835 | 5900
500106982 | CLB-MP-DOZR-WD6105-BRKSYS-SRVBK | Service Brake | 55835 | 55835 | 5900
500106981 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV07 | Parking Brake Control Valve | 55835 | 55835 | 5900
500106980 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV06 | Brake Manifold Rear | 55835 | 55835 | 5900
500106979 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV05 | Brake Manifold Front | 55835 | 55835 | 5900
500106978 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV04 | Brake Pump Check Valve | 55835 | 55835 | 5900
500106977 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV03 | Park Brake Release Check Valve | 55835 | 55835 | 5900
500106976 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV02 | Brake Accumulator Charging Valve | 55835 | 55835 | 5900
500106975 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV-VLV01 | Service Brake Control Valve | 55835 | 7966 | 5900
500106974 | CLB-MP-DOZR-WD6105-BRKSYS-BRVLV | Valves Brake | 55835 | 55835 | 5900
500106973 | CLB-MP-DOZR-WD6105-BRKSYS-BRPRK | Park Brake Assembly | 55835 | 30849 | 5900
500106972 | CLB-MP-DOZR-WD6105-BRKSYS-BRPMP | Pump Brake | 55835 | 304 | 5900
500106971 | CLB-MP-DOZR-WD6105-BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 55835 | 30849 | 5900
500106970 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 55835 | 7966 | 5900
500106969 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM-BACCF | Brake Accumulator Front | 55835 | 7966 | 5900
500106968 | CLB-MP-DOZR-WD6105-BRKSYS-BACCM | Brake Accumulators | 55835 | 55835 | 5900
500106967 | CLB-MP-DOZR-WD6105-BRKSYS | Braking System | 55835 | 55835 | 5900
500106926 | CLB-MP-DOZR-WD6105 | Caterpillar 854K Wheel Dozer WD6105 | 55835 | 55835 | 5900
500148483 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM | Brake Accumulator Front RH | 20272 | 20272 | 5900
500148482 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM | Brake Accumulator Front LH | 20272 | 20272 | 5900
500125292 | CLB-MP-DOZR-WD005 -STRSYS-STHLF | WD005 Steering System Hoses & Fittings | 79354 | 20272 | 5900
500125150 | CLB-MP-DOZR-WD005 -BRKSYS-BRHLF | WD005 Brake Syst Hoses Lines & Fittings | 79354 | 20272 | 5900
500125138 | CLB-MP-DOZR-WD005 -TRNSYS-TRHLF | WD005 Trans System Hoses Lines Fittings | 79354 | 79354 | 5900
500125125 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHMH | WD005 Hydraulic System Hoses Main | 79354 | 20272 | 5900
500125112 | CLB-MP-DOZR-WD005 -HYDSYS-HDHLF-HDHPS | WD005 Hyd System Hoses Pilot Sys | 79354 | 20272 | 5900
500038032 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF-TRNON | Trunnions Rear Differential | 79354 | 24532 | 5900
500029424 | CLB-MP-DOZR-WD005 -MANGMT-UMMMC | Mine Monitoring and Control | 79354 | 79354 | 5900
500029423 | CLB-MP-DOZR-WD005 -MANGMT-UMMC | Machine Management System | 79354 | 79354 | 5900
500029422 | CLB-MP-DOZR-WD005 -MANGMT-UMENG | Engine Management System | 79354 | 79354 | 5900
500029421 | CLB-MP-DOZR-WD005 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 79354 | 79354 | 5900
500029420 | CLB-MP-DOZR-WD005 -FRSUPP | Fire Suppression System | 79242 | 20272 | 5900
500029417 | CLB-MP-DOZR-WD005 -STRUCT-BLADE | Blade Trunions | 79354 | 79354 | 5900
500029416 | CLB-MP-DOZR-WD005 -STRUCT-BLADE | Blade | 79354 | 20272 | 5900
500029415 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-TRNON | Trunnion | 79354 | 79354 | 5900
500029414 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-LNKGE | Link Stabilizer | 79354 | 79354 | 5900
500029413 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-PUARM | Push Arm | 79354 | 79354 | 5900
500029412 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-ARTIC | Articulation | 79354 | 79354 | 5900
500029411 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-CWEIG | Counterweight | 79354 | 20272 | 5900
500029410 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 79354 | 79354 | 5900
500029409 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-REFRM | Rear Frame | 79354 | 79354 | 5900
500029408 | CLB-MP-DOZR-WD005 -STRUCT-CHASS-FRFRM | Front Frame | 79354 | 79354 | 5900
500029407 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-SBELT | Seat Belt | 79354 | 79354 | 5900
500029406 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-SEATS | WD005 Operators Seat | 79354 | 10152 | 5900
500029405 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 79354 | 79354 | 5900
500029404 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 79354 | 20272 | 5900
500029403 | CLB-MP-DOZR-WD005 -STRUCT-CABIN-AIRCN | Air Conditioning System | 79354 | 20272 | 5900
500029402 | CLB-MP-DOZR-WD005 -STRUCT-CABIN | Operators Cabin | 79354 | 20272 | 5900
500029401 | CLB-MP-DOZR-WD005 -GRSYST-ALBPP | Auto Lube Pump | 79354 | 79354 | 5900
500029400 | CLB-MP-DOZR-WD005 -GRSYST-GRINJ | Auto Lube Injectors | 79354 | 79354 | 5900
500029399 | CLB-MP-DOZR-WD005 -GRSYST | Auto Lube System Service | 79354 | 20272 | 5900
500029398 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV08 | Valve Solenoid Hydraulic Lockout | 79354 | 79354 | 5900
500029397 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV07 | Valve Pilot Relief | 79354 | 79354 | 5900
500029396 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV06 | Valve Make Up Hydraulic Fan | 79354 | 79354 | 5900
500029395 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV05 | Valve Demand Hydraulic Fan | 79354 | 79354 | 5900
500029394 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV04 | Valve Hydraulic Fan | 79354 | 79354 | 5900
500029393 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV03 | Valve Hydraulic Manual Lowering Control | 79354 | 79354 | 5900
500029392 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV02 | Valve Hydraulic Dual Tilt Control | 79354 | 79354 | 5900
500029391 | CLB-MP-DOZR-WD005 -HYDSYS-HDVLV-HYV01 | Valve Hydraulic Main Control | 79354 | 79354 | 5900
500029390 | CLB-MP-DOZR-WD005 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 79354 | 20272 | 5900
500029389 | CLB-MP-DOZR-WD005 -HYDSYS-HYDMT-HYM02 | Motor / Pump Axle Cooling | 79354 | 5467 | 5900
500029388 | CLB-MP-DOZR-WD005 -HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 79354 | 5467 | 5900
500029387 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 79354 | 20272 | 5900
500029386 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 79354 | 20272 | 5900
500029385 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 79354 | 7041 | 5900
500029384 | CLB-MP-DOZR-WD005 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 79354 | 1821 | 5900
500029383 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 79354 | 11802 | 5900
500029382 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot | 79354 | 12401 | 5900
500029381 | CLB-MP-DOZR-WD005 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 79354 | 6148 | 5900
500029380 | CLB-MP-DOZR-WD005 -HYDSYS | Hydraulic System | 79354 | 79354 | 5900
500029379 | CLB-MP-DOZR-WD005 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 79354 | 20272 | 5900
500029378 | CLB-MP-DOZR-WD005 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 79354 | 10451 | 5900
500029377 | CLB-MP-DOZR-WD005 -STRSYS-STVLV-VLV04 | Valve Steering Neutraliser R/H | 79354 | 79354 | 5900
500029376 | CLB-MP-DOZR-WD005 -STRSYS-STVLV-VLV03 | Valve Steering Neutraliser L/H | 79354 | 79354 | 5900
500029375 | CLB-MP-DOZR-WD005 -STRSYS-STVLV-VLV02 | Valve Steering Pilot (STIC Steering) | 79354 | 79354 | 5900
500029374 | CLB-MP-DOZR-WD005 -STRSYS-STVLV-VLV01 | Valve Steering Control | 79354 | 79354 | 5900
500029373 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP03 | Pump Steering Secondary / Emergency | 79354 | 12401 | 5900
500029372 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP02 | Pump Steering Pilot / Axle Oil Cooling | 79354 | 8527 | 5900
500029371 | CLB-MP-DOZR-WD005 -STRSYS-STPMP-STP01 | Pump Steering Main | 79354 | 12401 | 5900
500029370 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV07 | Parking Brake Control Valve | 79354 | 79354 | 5900
500029369 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV06 | Brake Manifold Rear | 79354 | 79354 | 5900
500029368 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV05 | Brake Manifold Front | 79354 | 79354 | 5900
500029367 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV04 | Brake Pump Check Valve | 79354 | 79354 | 5900
500029366 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV03 | Park Brake Release Check Valve | 79354 | 79354 | 5900
500029365 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV02 | Brake Accumulator Charging Valve | 79354 | 79354 | 5900
500029364 | CLB-MP-DOZR-WD005 -BRKSYS-BRVLV-VLV01 | Service Brake Control Valve | 79354 | 79354 | 5900
500029363 | CLB-MP-DOZR-WD005 -BRKSYS-BRPMP | Pump Brake | 79354 | 2149 | 5900
500029362 | CLB-MP-DOZR-WD005 -BRKSYS-BRPRK | Park Brake Assembly | 79354 | 40862 | 5900
500029361 | CLB-MP-DOZR-WD005 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 79354 | 79354 | 5900
500029360 | CLB-MP-DOZR-WD005 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 79354 | 79354 | 5900
500029359 | CLB-MP-DOZR-WD005 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 79354 | 79354 | 5900
500029358 | CLB-MP-DOZR-WD005 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 79354 | 79354 | 5900
500029357 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 79354 | 20272 | 5900
500029356 | CLB-MP-DOZR-WD005 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 79354 | 20272 | 5900
500029355 | CLB-MP-DOZR-WD005 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 79354 | 79354 | 5900
500029354 | CLB-MP-DOZR-WD005 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 79354 | 79354 | 5900
500029353 | CLB-MP-DOZR-WD005 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 79354 | 79354 | 5900
500029352 | CLB-MP-DOZR-WD005 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 79354 | 79354 | 5900
500029351 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC-TVLVR | Axle Cooling Thermal Bypass Valve Rear | 79354 | 79354 | 5900
500029350 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC-TVLVF | Axle Cooling Thermal Bypass Valve Front | 79354 | 79354 | 5900
500029349 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC-OILCR | Axle Oil Cooler Rear | 79354 | 20272 | 5900
500029348 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC-OILCF | Axle Oil Cooler Front | 79354 | 61125 | 5900
500029347 | CLB-MP-DOZR-WD005 -FDRSYS-AXLEC | Axle Cooler Pump / Motor | 79354 | 79354 | 5900
500029346 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 79354 | 20272 | 5900
500029345 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 79354 | 20272 | 5900
500029344 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 79354 | 20272 | 5900
500029343 | CLB-MP-DOZR-WD005 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 79354 | 20272 | 5900
500029341 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF | Rear Differential | 79354 | 24532 | 5900
500029340 | CLB-MP-DOZR-WD005 -FDRSYS-FRDIF | Front Differential | 79354 | 20272 | 5900
500029339 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 79354 | 20272 | 5900
500029338 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 79354 | 20272 | 5900
500029337 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 79354 | 20272 | 5900
500029336 | CLB-MP-DOZR-WD005 -FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 79354 | 20272 | 5900
500029335 | CLB-MP-DOZR-WD005 -TRNSYS-TROLC | Transmission Oil Cooler | 79354 | 6148 | 5900
500029334 | CLB-MP-DOZR-WD005 -TRNSYS-TRPMP | Pump Transmission | 79354 | 6159 | 5900
500029333 | CLB-MP-DOZR-WD005 -TRNSYS-TRTRF | Transmission Transfer Case | 79354 | 61125 | 5900
500029332 | CLB-MP-DOZR-WD005 -TRNSYS-TRANS | Transmission | 79354 | 6234 | 5900
500029331 | CLB-MP-DOZR-WD005 -TRNSYS-TRQUE | Torque Converter | 79354 | 6148 | 5900
500029330 | CLB-MP-DOZR-WD005 -ELCTLV-START-STMRH | Starter Motor R/H | 79354 | 7041 | 5900
500029329 | CLB-MP-DOZR-WD005 -ELCTLV-START-STMLH | Starter Motor L/H | 79354 | 7041 | 5900
500029328 | CLB-MP-DOZR-WD005 -ELCTLV-CHARG-BATTY | Batteries | 79354 | 13490 | 5900
500029327 | CLB-MP-DOZR-WD005 -ELCTLV-CHARG-ALTER | Alternator 24V | 79354 | 7041 | 5900
500029326 | CLB-MP-DOZR-WD005 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 79354 | 7041 | 5900
500029325 | CLB-MP-DOZR-WD005 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 79354 | 7041 | 5900
500029324 | CLB-MP-DOZR-WD005 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 79354 | 61125 | 5900
500029323 | CLB-MP-DOZR-WD005 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 79354 | 20272 | 5900
500029322 | CLB-MP-DOZR-WD005 -ENGINE-INTEX-AFTER | Aftercooler | 79354 | 20272 | 5900
500029321 | CLB-MP-DOZR-WD005 -ENGINE-INTEX-TBORH | Turbocharger R/H | 79354 | 7041 | 5900
500029320 | CLB-MP-DOZR-WD005 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 79354 | 7041 | 5900
500029319 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-CSHLF | Cooling System Hoses | 79354 | 7041 | 5900
500029318 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-THERM | Thermostats/Regulators | 79354 | 7041 | 5900
500029317 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-COFAN | Cooling Fan | 79354 | 79354 | 5900
500029316 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-RADTR | Radiator Coolant | 79354 | 20272 | 5900
500029315 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-RADTR | Radiator Engine | 79354 | 20272 | 5900
500029314 | CLB-MP-DOZR-WD005 -ENGINE-COSYS-WTRPP | Water Pump Engine | 79354 | 7041 | 5900
500029313 | CLB-MP-DOZR-WD005 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 79354 | 54373 | 5900
500029312 | CLB-MP-DOZR-WD005 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 79354 | 61125 | 5900
500029310 | CLB-MP-DOZR-WD005 -ENGINE | Engine Assembly Caterpillar C32 | 79354 | 20272 | 5900
500029309 | CLB-MP-DOZR-WD005 | WD005 Lube & Mechanical Services | 79354 | 79354 | 5900
500029308 | CLB-MP-DOZR-WD005 | Caterpillar 854K Wheel Dozer WD005 | 79354 | 79354 | 5900
500148481 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM | Brake Accumulator Front RH | 13602 | 13602 | 5900
500148480 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM | Brake Accumulator Front LH | 13602 | 13602 | 5900
500125291 | CLB-MP-DOZR-WD004 -STRSYS-STHLF | WD004 Steering System Hoses & Fittings | 72896 | 17339 | 5900
500125149 | CLB-MP-DOZR-WD004 -BRKSYS-BRHLF | WD004 Brake Syst Hoses Lines & Fittings | 72896 | 17339 | 5900
500125137 | CLB-MP-DOZR-WD004 -TRNSYS-TRHLF | WD004 Trans System Hoses Lines Fittings | 72896 | 72896 | 5900
500125124 | CLB-MP-DOZR-WD004 -HYDSYS-HDHLF-HDHMH | WD004 Hydraulic System Hoses Main | 72896 | 17339 | 5900
500125111 | CLB-MP-DOZR-WD004 -HYDSYS-HDHLF-HDHPS | WD004 Hyd System Hoses Pilot Sys | 72896 | 17339 | 5900
500038031 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF-TRNON | Trunnions Rear Differential | 72896 | 18315 | 5900
500029307 | CLB-MP-DOZR-WD004 -MANGMT-UMMMC | Mine Monitoring and Control | 72896 | 72896 | 5900
500029306 | CLB-MP-DOZR-WD004 -MANGMT-UMMC | Machine Management System | 72896 | 72896 | 5900
500029305 | CLB-MP-DOZR-WD004 -MANGMT-UMENG | Engine Management System | 72896 | 72896 | 5900
500029304 | CLB-MP-DOZR-WD004 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 72896 | 72896 | 5900
500029303 | CLB-MP-DOZR-WD004 -FRSUPP | Fire Suppression System | 72896 | 72896 | 5900
500029300 | CLB-MP-DOZR-WD004 -STRUCT-BLADE | Blade Trunions | 72896 | 72896 | 5900
500029299 | CLB-MP-DOZR-WD004 -STRUCT-BLADE | Blade | 72896 | 15776 | 5900
500029298 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-TRNON | Trunnion | 72896 | 72896 | 5900
500029297 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-LNKGE | Link Stabilizer | 72896 | 72896 | 5900
500029296 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-PUARM | Push Arm | 72896 | 72896 | 5900
500029295 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-ARTIC | Articulation | 72896 | 21615 | 5900
500029294 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-CWEIG | Counterweight | 72896 | 72896 | 5900
500029293 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 72896 | 72896 | 5900
500029292 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-REFRM | Rear Frame | 72896 | 72896 | 5900
500029291 | CLB-MP-DOZR-WD004 -STRUCT-CHASS-FRFRM | Front Frame | 72896 | 72896 | 5900
500029290 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SBELT | Seat Belt | 72896 | 72896 | 5900
500029289 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-SEATS | WD004 Operators Seat | 72896 | 6131 | 5900
500029288 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 72896 | 72896 | 5900
500029287 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 72896 | 2306 | 5900
500029286 | CLB-MP-DOZR-WD004 -STRUCT-CABIN-AIRCN | Air Conditioning System | 72896 | 2306 | 5900
500029285 | CLB-MP-DOZR-WD004 -STRUCT-CABIN | Operators Cabin | 72896 | 13602 | 5900
500029284 | CLB-MP-DOZR-WD004 -GRSYST-ALBPP | Auto Lube Pump | 72896 | 33820 | 5900
500029283 | CLB-MP-DOZR-WD004 -GRSYST-GRINJ | Auto Lube Injectors | 72896 | 72896 | 5900
500029282 | CLB-MP-DOZR-WD004 -GRSYST | Auto Lube System Service | 72896 | 13602 | 5900
500029281 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV08 | Valve Solenoid Hydraulic Lockout | 72896 | 72896 | 5900
500029280 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV07 | Valve Pilot Relief | 72896 | 72896 | 5900
500029279 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV06 | Valve Make Up Hydraulic Fan | 72896 | 72896 | 5900
500029278 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV05 | Valve Demand Hydraulic Fan | 72896 | 72896 | 5900
500029277 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV04 | Valve Hydraulic Fan | 72896 | 72896 | 5900
500029276 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV03 | Valve Hydraulic Manual Lowering Control | 72896 | 72896 | 5900
500029275 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV02 | Valve Hydraulic Dual Tilt Control | 72896 | 72896 | 5900
500029274 | CLB-MP-DOZR-WD004 -HYDSYS-HDVLV-HYV01 | Valve Hydraulic Main Control | 72896 | 72896 | 5900
500029273 | CLB-MP-DOZR-WD004 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 72896 | 13602 | 5900
500029272 | CLB-MP-DOZR-WD004 -HYDSYS-HYDMT-HYM02 | Motor / Pump Axle Cooling | 72896 | 3579 | 5900
500029271 | CLB-MP-DOZR-WD004 -HYDSYS-HYDMT-HYM01 | Motor Hydraulic Fan High Temp | 72896 | 3579 | 5900
500029270 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 72896 | 17373 | 5900
500029269 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 72896 | 17373 | 5900
500029268 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 72896 | 3877 | 5900
500029267 | CLB-MP-DOZR-WD004 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 72896 | 3877 | 5900
500029266 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP03 | Pump Hydraulic Fan | 72896 | 3579 | 5900
500029265 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP02 | Pump Hydraulic Pilot | 72896 | 3579 | 5900
500029264 | CLB-MP-DOZR-WD004 -HYDSYS-HYDPP-HYP01 | Pump Hydraulic Implement | 72896 | 3579 | 5900
500029263 | CLB-MP-DOZR-WD004 -HYDSYS | Hydraulic System | 72896 | 72896 | 5900
500029262 | CLB-MP-DOZR-WD004 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 72896 | 8156 | 5900
500029261 | CLB-MP-DOZR-WD004 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 72896 | 8156 | 5900
500029260 | CLB-MP-DOZR-WD004 -STRSYS-STVLV-VLV04 | Valve Steering Neutraliser R/H | 72896 | 72896 | 5900
500029259 | CLB-MP-DOZR-WD004 -STRSYS-STVLV-VLV03 | Valve Steering Neutraliser L/H | 72896 | 72896 | 5900
500029258 | CLB-MP-DOZR-WD004 -STRSYS-STVLV-VLV02 | Valve Steering Pilot (STIC Steering) | 72896 | 72896 | 5900
500029257 | CLB-MP-DOZR-WD004 -STRSYS-STVLV-VLV01 | Valve Steering Control | 72896 | 13602 | 5900
500029256 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP03 | Pump Steering Secondary / Emergency | 72896 | 3579 | 5900
500029255 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP02 | Pump Steering Pilot / Axle Oil Cooling | 72896 | 3579 | 5900
500029254 | CLB-MP-DOZR-WD004 -STRSYS-STPMP-STP01 | Pump Steering Main | 72896 | 5612 | 5900
500029253 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV07 | Parking Brake Control Valve | 72896 | 72896 | 5900
500029252 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV06 | Brake Manifold Rear | 72896 | 72896 | 5900
500029251 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV05 | Brake Manifold Front | 72896 | 72896 | 5900
500029250 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV04 | Brake Pump Check Valve | 72896 | 72896 | 5900
500029249 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV03 | Park Brake Release Check Valve | 72896 | 72896 | 5900
500029248 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV02 | Brake Accumulator Charging Valve | 72896 | 72896 | 5900
500029247 | CLB-MP-DOZR-WD004 -BRKSYS-BRVLV-VLV01 | Service Brake Control Valve | 72896 | 72896 | 5900
500029246 | CLB-MP-DOZR-WD004 -BRKSYS-BRPMP | Pump Brake | 72896 | 6131 | 5900
500029245 | CLB-MP-DOZR-WD004 -BRKSYS-BRPRK | Park Brake Assembly | 72896 | 3579 | 5900
500029244 | CLB-MP-DOZR-WD004 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 72896 | 72896 | 5900
500029243 | CLB-MP-DOZR-WD004 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 72896 | 72896 | 5900
500029242 | CLB-MP-DOZR-WD004 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 72896 | 72896 | 5900
500029241 | CLB-MP-DOZR-WD004 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 72896 | 72896 | 5900
500029240 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 72896 | 13602 | 5900
500029239 | CLB-MP-DOZR-WD004 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 72896 | 13602 | 5900
500029238 | CLB-MP-DOZR-WD004 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 72896 | 72896 | 5900
500029237 | CLB-MP-DOZR-WD004 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 72896 | 72896 | 5900
500029236 | CLB-MP-DOZR-WD004 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 72896 | 72896 | 5900
500029235 | CLB-MP-DOZR-WD004 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 72896 | 72896 | 5900
500029234 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC-TVLVR | Axle Cooling Thermal Bypass Valve Rear | 72896 | 72896 | 5900
500029233 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC-TVLVF | Axle Cooling Thermal Bypass Valve Front | 72896 | 72896 | 5900
500029232 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC-OILCR | Axle Oil Cooler Rear | 72896 | 13602 | 5900
500029231 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC-OILCF | Axle Oil Cooler Front | 72896 | 72896 | 5900
500029230 | CLB-MP-DOZR-WD004 -FDRSYS-AXLEC | Axle Cooler Pump / Motor | 72896 | 72896 | 5900
500029229 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR04 | Final Drive Position 4 | 72896 | 13602 | 5900
500029228 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR03 | Final Drive Position 3 | 72896 | 13602 | 5900
500029227 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR02 | Final Drive Position 2 | 72896 | 13602 | 5900
500029226 | CLB-MP-DOZR-WD004 -FDRSYS-FDRVE-FDR01 | Final Drive Position 1 | 72896 | 13602 | 5900
500029224 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF | Rear Differential | 72896 | 3579 | 5900
500029223 | CLB-MP-DOZR-WD004 -FDRSYS-FRDIF | Front Differential | 72896 | 13602 | 5900
500029222 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT04 | Drive Shaft Cntr Bearing to Front Diff | 72896 | 3579 | 5900
500029221 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT03 | Drive Shaft Transmission to Cntr Bearing | 72896 | 5612 | 5900
500029220 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT02 | Drive Shaft Transmission to Rear Diff | 72896 | 3579 | 5900
500029219 | CLB-MP-DOZR-WD004 -FDRSYS-DRSHT-SHT01 | Drive Shaft T/C to Transmission | 72896 | 3579 | 5900
500029218 | CLB-MP-DOZR-WD004 -TRNSYS-TROLC | Transmission Oil Cooler | 72896 | 3579 | 5900
500029217 | CLB-MP-DOZR-WD004 -TRNSYS-TRPMP | Pump Transmission | 72896 | 3579 | 5900
500029216 | CLB-MP-DOZR-WD004 -TRNSYS-TRTRF | Transmission Transfer Case | 72896 | 72896 | 5900
500029215 | CLB-MP-DOZR-WD004 -TRNSYS-TRANS | Transmission | 72896 | 3579 | 5900
500029214 | CLB-MP-DOZR-WD004 -TRNSYS-TRQUE | Torque Converter | 72896 | 16688 | 5900
500029213 | CLB-MP-DOZR-WD004 -ELCTLV-START-STMRH | Starter Motor R/H | 72896 | 2306 | 5900
500029212 | CLB-MP-DOZR-WD004 -ELCTLV-START-STMLH | Starter Motor L/H | 72896 | 2306 | 5900
500029211 | CLB-MP-DOZR-WD004 -ELCTLV-CHARG-BATTY | Batteries | 72896 | 12474 | 5900
500029210 | CLB-MP-DOZR-WD004 -ELCTLV-CHARG-ALTER | Alternator 24V | 72896 | 2306 | 5900
500029209 | CLB-MP-DOZR-WD004 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 72896 | 2306 | 5900
500029208 | CLB-MP-DOZR-WD004 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 72896 | 2306 | 5900
500029207 | CLB-MP-DOZR-WD004 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 72896 | 13773 | 5900
500029206 | CLB-MP-DOZR-WD004 -ENGINE-INTEX-EXHST | Exhaust Mufflers | 72896 | 72896 | 5900
500029205 | CLB-MP-DOZR-WD004 -ENGINE-INTEX-AFTER | Aftercooler | 72896 | 13602 | 5900
500029204 | CLB-MP-DOZR-WD004 -ENGINE-INTEX-TBORH | Turbocharger R/H | 72896 | 2306 | 5900
500029203 | CLB-MP-DOZR-WD004 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 72896 | 2306 | 5900
500029202 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-CSHLF | Cooling System Hoses | 72896 | 39605 | 5900
500029201 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-THERM | Thermostats/Regulators | 72896 | 2306 | 5900
500029200 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-COFAN | Cooling Fan | 72896 | 72896 | 5900
500029199 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-RADTR | Radiator Coolant | 72896 | 13602 | 5900
500029198 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-RADTR | Radiator Engine | 72896 | 13602 | 5900
500029197 | CLB-MP-DOZR-WD004 -ENGINE-COSYS-WTRPP | Water Pump Engine | 72896 | 2306 | 5900
500029196 | CLB-MP-DOZR-WD004 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 72896 | 13773 | 5900
500029195 | CLB-MP-DOZR-WD004 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 72896 | 13773 | 5900
500029193 | CLB-MP-DOZR-WD004 -ENGINE | Engine Assembly Caterpillar C32 | 72896 | 13773 | 5900
500029192 | CLB-MP-DOZR-WD004 | WD004 Lube & Mechanical Services | 72896 | 72896 | 5900
500029191 | CLB-MP-DOZR-WD004 | Caterpillar 854K Wheel Dozer WD004 | 72896 | 72896 | 5900
500129911 | CLB-MP-GRDR-GR6505-TRNSYS-TRPMP | Pump Transmission | 19670 | 19670 | 5500
500129910 | CLB-MP-GRDR-GR6505-TRNSYS-TROLC | Transmission Oil Cooler | 19670 | 19670 | 5500
500129909 | CLB-MP-GRDR-GR6505-TRNSYS-TRANS | Transmission | 19670 | 3848 | 5500
500129908 | CLB-MP-GRDR-GR6505-TRNSYS-DRSHT | Drive Shaft | 19670 | 3848 | 5500
500129907 | CLB-MP-GRDR-GR6505-STRUCT-RIPPR-RIGET | Ripper Wear Elements GET | 19670 | 19670 | 5500
500129906 | CLB-MP-GRDR-GR6505-STRUCT-RIPPR | Ripper | 19670 | 3848 | 5500
500129905 | CLB-MP-GRDR-GR6505-STRUCT-DRWBR | Drawbar | 19670 | 3848 | 5500
500129904 | CLB-MP-GRDR-GR6505-STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 19670 | 3848 | 5500
500129903 | CLB-MP-GRDR-GR6505-STRUCT-CIRCL | Circle Assembly | 19670 | 19670 | 5500
500129902 | CLB-MP-GRDR-GR6505-STRUCT-CHASS-ARTIC | Articulation | 19670 | 19670 | 5500
500129901 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-SEATS | Operators Seat | 19670 | 3848 | 5500
500129900 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-SBELT | Seat Belt | 19670 | 19670 | 5500
500129899 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 19670 | 19670 | 5500
500129898 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 19670 | 3848 | 5500
500129897 | CLB-MP-GRDR-GR6505-STRUCT-CABIN-AIRCN | Air Conditioning System | 19670 | 3848 | 5500
500129896 | CLB-MP-GRDR-GR6505-STRUCT-CABIN | Cabin | 19670 | 3848 | 5500
500129895 | CLB-MP-GRDR-GR6505-STRUCT-BLADE-MOLDB | Moldboard Skin | 19670 | 19670 | 5500
500129894 | CLB-MP-GRDR-GR6505-STRUCT-BLADE-BLGET | Blade Wear Elements GET | 19670 | 19670 | 5500
500129893 | CLB-MP-GRDR-GR6505-STRUCT-BLADE | Blade Lift Trunnions | 19670 | 19670 | 5500
500129892 | CLB-MP-GRDR-GR6505-STRUCT-BLADE | Blade | 19670 | 1242 | 5500
500129891 | CLB-MP-GRDR-GR6505-STRUCT-AXLES-HUBRH | Hub and Spindle RH | 19670 | 3848 | 5500
500129890 | CLB-MP-GRDR-GR6505-STRUCT-AXLES-HUBLH | Hub and Spindle LH | 19670 | 3848 | 5500
500129889 | CLB-MP-GRDR-GR6505-STRUCT-AXLES | Front Axle Assembly | 19670 | 3848 | 5500
500129888 | CLB-MP-GRDR-GR6505-STRSYS-STRCY-STCYR | Cylinder Steering RH | 19670 | 3848 | 5500
500129887 | CLB-MP-GRDR-GR6505-STRSYS-STRCY-STCYL | Cylinder Steering LH | 19670 | 3848 | 5500
500129886 | CLB-MP-GRDR-GR6505-STRSYS-STMTR | Steering Metering Pump | 19670 | 19670 | 5500
500129885 | CLB-MP-GRDR-GR6505-STRSYS-STLTR | Steering Linkages & Tie Rods | 19670 | 19670 | 5500
500129884 | CLB-MP-GRDR-GR6505-STRSYS-STEMG-SESPP | Pump Secondary Steering | 19670 | 3848 | 5500
500129883 | CLB-MP-GRDR-GR6505-HYDSYS-HYDPP-HYISP | Pump Implement & Steering | 19670 | 3848 | 5500
500129882 | CLB-MP-GRDR-GR6505-HYDSYS-HDOCO | Oil Cooler Hydraulic | 19670 | 3848 | 5500
500129881 | CLB-MP-GRDR-GR6505-HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 19670 | 3848 | 5500
500129880 | CLB-MP-GRDR-GR6505-HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 19670 | 19670 | 5500
500129879 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-STRNG | Steering System Hoses | 19670 | 3848 | 5500
500129878 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 19670 | 3848 | 5500
500129877 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 19670 | 3848 | 5500
500129876 | CLB-MP-GRDR-GR6505-HYDSYS-HDHLF-BRKSH | Brake System Hoses | 19670 | 3848 | 5500
500129875 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 19670 | 3848 | 5500
500129874 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 19670 | 9855 | 5500
500129873 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 19670 | 19670 | 5500
500129872 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 19670 | 19670 | 5500
500129871 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 19670 | 19670 | 5500
500129870 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 19670 | 19670 | 5500
500129869 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 19670 | 8679 | 5500
500129868 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 19670 | 6800 | 5500
500129867 | CLB-MP-GRDR-GR6505-HYDSYS-HDCYL-ARCYL | Cylinder Articulation LH | 19670 | 2578 | 5500
500129866 | CLB-MP-GRDR-GR6505-HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 19670 | 3848 | 5500
500129865 | CLB-MP-GRDR-GR6505-HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 19670 | 3848 | 5500
500129864 | CLB-MP-GRDR-GR6505-HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator RH | 19670 | 19670 | 5500
500129863 | CLB-MP-GRDR-GR6505-HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator LH | 19670 | 19670 | 5500
500129862 | CLB-MP-GRDR-GR6505-GRSYST-GRINJ | Auto Lube Injectors | 19670 | 19670 | 5500
500129861 | CLB-MP-GRDR-GR6505-GRSYST-ALBPP | Auto Lube Pump | 19670 | 3848 | 5500
500129860 | CLB-MP-GRDR-GR6505-GRSYST | Grease Lubrication System | 19670 | 19670 | 5500
500129859 | CLB-MP-GRDR-GR6505-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 19670 | 19670 | 5500
500129858 | CLB-MP-GRDR-GR6505-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 19670 | 19670 | 5500
500129857 | CLB-MP-GRDR-GR6505-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 19670 | 19670 | 5500
500129856 | CLB-MP-GRDR-GR6505-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 19670 | 19670 | 5500
500129855 | CLB-MP-GRDR-GR6505-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 19670 | 19670 | 5500
500129854 | CLB-MP-GRDR-GR6505-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 19670 | 19670 | 5500
500129853 | CLB-MP-GRDR-GR6505-FDRSYS-TDRAX-TDARH | Tandem Drive Chains RH | 19670 | 19670 | 5500
500129852 | CLB-MP-GRDR-GR6505-FDRSYS-TDRAX-TDARH | Tandem Drive Assembly RH | 19670 | 19670 | 5500
500129851 | CLB-MP-GRDR-GR6505-FDRSYS-TDRAX-TDALH | Tandem Drive Chains LH | 19670 | 19670 | 5500
500129850 | CLB-MP-GRDR-GR6505-FDRSYS-TDRAX-TDALH | Tandem Drive Assembly LH | 19670 | 19670 | 5500
500129849 | CLB-MP-GRDR-GR6505-FDRSYS-FDRVE-FDRRH | Final Drive RH | 19670 | 3848 | 5500
500129848 | CLB-MP-GRDR-GR6505-FDRSYS-FDRVE-FDRLH | Final Drive LH | 19670 | 3848 | 5500
500129847 | CLB-MP-GRDR-GR6505-FDRSYS-DIFFL | Differential & Bevel Gear | 19670 | 3848 | 5500
500129846 | CLB-MP-GRDR-GR6505-FDRSYS-CHAIN-CHNRR | Drive Chain RH Rear | 19670 | 3848 | 5500
500129845 | CLB-MP-GRDR-GR6505-FDRSYS-CHAIN-CHNRF | Drive Chain RH Front | 19670 | 3848 | 5500
500129844 | CLB-MP-GRDR-GR6505-FDRSYS-CHAIN-CHNLR | Drive Chain LH Rear | 19670 | 3848 | 5500
500129843 | CLB-MP-GRDR-GR6505-FDRSYS-CHAIN-CHNLF | Drive Chain LH Front | 19670 | 3848 | 5500
500129842 | CLB-MP-GRDR-GR6505-ENGINE-LUBSY-OILPP | Oil Pump Engine | 19670 | 3848 | 5500
500129841 | CLB-MP-GRDR-GR6505-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 19670 | 3848 | 5500
500129840 | CLB-MP-GRDR-GR6505-ENGINE-LUBSY | Engine Lubrication System | 19670 | 19670 | 5500
500129839 | CLB-MP-GRDR-GR6505-ENGINE-INTEX-TURBO | Turbocharger | 19670 | 137 | 5500
500129838 | CLB-MP-GRDR-GR6505-ENGINE-INTEX-EXHST | Exhaust Muffler | 19670 | 19670 | 5500
500129837 | CLB-MP-GRDR-GR6505-ENGINE-INTEX-AFTER | Aftercooler | 19670 | 3848 | 5500
500129836 | CLB-MP-GRDR-GR6505-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 19670 | 3848 | 5500
500129835 | CLB-MP-GRDR-GR6505-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 19670 | 3848 | 5500
500129834 | CLB-MP-GRDR-GR6505-ENGINE-FUSYS-FUINJ | Fuel Injectors | 19670 | 3848 | 5500
500129833 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-WTRPP | Water Pump Engine | 19670 | 3848 | 5500
500129832 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-THERM | Thermostats | 19670 | 19670 | 5500
500129831 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-RADTR | Radiator Coolant | 19670 | 19670 | 5000
500129830 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-RADTR | Radiator Engine | 19670 | 3848 | 5500
500129829 | CLB-MP-GRDR-GR6505-ENGINE-COSYS-COFAN | Fan Cooling System | 19670 | 19670 | 5500
500129827 | CLB-MP-GRDR-GR6505-ENGINE | Engine Assembly Caterpillar C13 ACERT | 19670 | 3848 | 5500
500129826 | CLB-MP-GRDR-GR6505-ELCTLV-START-STRMR | Starter Motor | 19670 | 3848 | 5500
500129825 | CLB-MP-GRDR-GR6505-ELCTLV-HARNS | Electrical Harness | 19670 | 3848 | 5500
500129824 | CLB-MP-GRDR-GR6505-ELCTLV-CHARG-ALTER | Alternator 24V | 19670 | 1880 | 5500
500129823 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 19670 | 3848 | 5500
500129622 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 19670 | 3848 | 5500
500129621 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 19670 | 7059 | 5500
500129620 | CLB-MP-GRDR-GR6505-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 19670 | 3848 | 5500
500129619 | CLB-MP-GRDR-GR6505-BRKSYS-BRPRK | Park Brake Assembly | 19670 | 19670 | 5500
500129618 | CLB-MP-GRDR-GR6505-BRKSYS-BRPMP | Pump Brake Hydraulic Fan | 19670 | 3848 | 5500
500129617 | CLB-MP-GRDR-GR6505-BRKSYS-BKOCO | Oil Cooler Brake Hydraulic Fan | 19670 | 19670 | 5500
500129616 | CLB-MP-GRDR-GR6505-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 19670 | 19670 | 5500
500129615 | CLB-MP-GRDR-GR6505-BRKSYS-BACCM-BACCF | Brake Accumulator Front | 19670 | 19670 | 5500
500129614 | CLB-MP-GRDR-GR6505 | GR6505 Caterpillar 18 Grader | 19670 | 19670 | 5500
500129717 | CLB-MP-GRDR-GR6504-TRNSYS-TRPMP | Pump Transmission | 19712 | 19712 | 5500
500129716 | CLB-MP-GRDR-GR6504-TRNSYS-TROLC | Transmission Oil Cooler | 19712 | 19712 | 5500
500129715 | CLB-MP-GRDR-GR6504-TRNSYS-TRANS | Transmission | 19712 | 4282 | 5500
500129714 | CLB-MP-GRDR-GR6504-TRNSYS-DRSHT | Drive Shaft | 19712 | 4282 | 5500
500129713 | CLB-MP-GRDR-GR6504-STRUCT-RIPPR-RIGET | Ripper Wear Elements GET | 19712 | 19712 | 5500
500129712 | CLB-MP-GRDR-GR6504-STRUCT-RIPPR | Ripper | 19712 | 4282 | 5500
500129711 | CLB-MP-GRDR-GR6504-STRUCT-DRWBR | Drawbar | 19712 | 4282 | 5500
500129710 | CLB-MP-GRDR-GR6504-STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 19712 | 6665 | 5500
500129709 | CLB-MP-GRDR-GR6504-STRUCT-CIRCL | Circle Assembly | 19712 | 19712 | 5500
500129708 | CLB-MP-GRDR-GR6504-STRUCT-CHASS-ARTIC | Articulation | 19712 | 19712 | 5500
500129707 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-SEATS | Operators Seat | 19712 | 4282 | 5500
500129706 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-SBELT | Seat Belt | 19712 | 19712 | 5500
500129705 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 19712 | 19712 | 5500
500129704 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 19712 | 4282 | 5500
500129703 | CLB-MP-GRDR-GR6504-STRUCT-CABIN-AIRCN | Air Conditioning System | 19712 | 4282 | 5500
500129702 | CLB-MP-GRDR-GR6504-STRUCT-CABIN | Cabin | 19712 | 4282 | 5500
500129701 | CLB-MP-GRDR-GR6504-STRUCT-BLADE-MOLDB | Moldboard Skin | 19712 | 19712 | 5500
500129700 | CLB-MP-GRDR-GR6504-STRUCT-BLADE-BLGET | Blade Wear Elements GET | 19712 | 19712 | 5500
500129699 | CLB-MP-GRDR-GR6504-STRUCT-BLADE | Blade Lift Trunnions | 19712 | 19712 | 5500
500129698 | CLB-MP-GRDR-GR6504-STRUCT-BLADE | Blade | 19712 | 1292 | 5500
500129697 | CLB-MP-GRDR-GR6504-STRUCT-AXLES-HUBRH | Hub and Spindle RH | 19712 | 12344 | 5500
500129696 | CLB-MP-GRDR-GR6504-STRUCT-AXLES-HUBLH | Hub and Spindle LH | 19712 | 12344 | 5500
500129695 | CLB-MP-GRDR-GR6504-STRUCT-AXLES | Front Axle Assembly | 19712 | 4282 | 5500
500129694 | CLB-MP-GRDR-GR6504-STRSYS-STRCY-STCYR | Cylinder Steering RH | 19712 | 9287 | 5500
500129693 | CLB-MP-GRDR-GR6504-STRSYS-STRCY-STCYL | Cylinder Steering LH | 19712 | 12344 | 5500
500129692 | CLB-MP-GRDR-GR6504-STRSYS-STMTR | Steering Metering Pump | 19712 | 19712 | 5500
500129691 | CLB-MP-GRDR-GR6504-STRSYS-STLTR | Steering Linkages & Tie Rods | 19712 | 19712 | 5500
500129690 | CLB-MP-GRDR-GR6504-STRSYS-STEMG-SESPP | Pump Secondary Steering | 19712 | 4282 | 5500
500129689 | CLB-MP-GRDR-GR6504-HYDSYS-HYDPP-HYISP | Pump Implement & Steering | 19712 | 4282 | 5500
500129688 | CLB-MP-GRDR-GR6504-HYDSYS-HDOCO | Oil Cooler Hydraulic | 19712 | 4282 | 5500
500129687 | CLB-MP-GRDR-GR6504-HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 19712 | 6868 | 5500
500129686 | CLB-MP-GRDR-GR6504-HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 19712 | 6665 | 5500
500129685 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-STRNG | Steering System Hoses | 19712 | 4282 | 5500
500129684 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 19712 | 4282 | 5500
500129683 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 19712 | 4282 | 5500
500129682 | CLB-MP-GRDR-GR6504-HYDSYS-HDHLF-BRKSH | Brake System Hoses | 19712 | 4282 | 5500
500129681 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 19712 | 19712 | 5500
500129680 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 19712 | 6067 | 5500
500129679 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 19712 | 1564 | 5500
500129678 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 19712 | 19712 | 5500
500129677 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 19712 | 7836 | 5500
500129676 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 19712 | 1098 | 5500
500129675 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 19712 | 18021 | 5500
500129674 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 19712 | 8470 | 5500
500129673 | CLB-MP-GRDR-GR6504-HYDSYS-HDCYL-ARCYL | Cylinder Articulation LH | 19712 | 19712 | 5500
500129672 | CLB-MP-GRDR-GR6504-HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 19712 | 4282 | 5500
500129671 | CLB-MP-GRDR-GR6504-HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 19712 | 4282 | 5500
500129670 | CLB-MP-GRDR-GR6504-HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator RH | 19712 | 19712 | 5500
500129669 | CLB-MP-GRDR-GR6504-HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator LH | 19712 | 19712 | 5500
500129668 | CLB-MP-GRDR-GR6504-GRSYST-GRINJ | Auto Lube Injectors | 19712 | 19712 | 5500
500129667 | CLB-MP-GRDR-GR6504-GRSYST-ALBPP | Auto Lube Pump | 19712 | 4282 | 5500
500129666 | CLB-MP-GRDR-GR6504-GRSYST | Grease Lubrication System | 19712 | 19712 | 5500
500129665 | CLB-MP-GRDR-GR6504-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 19712 | 19712 | 5500
500129664 | CLB-MP-GRDR-GR6504-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 19712 | 19712 | 5500
500129663 | CLB-MP-GRDR-GR6504-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 19712 | 19712 | 5500
500129662 | CLB-MP-GRDR-GR6504-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 19712 | 19712 | 5500
500129661 | CLB-MP-GRDR-GR6504-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 19712 | 19712 | 5500
500129660 | CLB-MP-GRDR-GR6504-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 19712 | 19712 | 5500
500129659 | CLB-MP-GRDR-GR6504-FDRSYS-TDRAX-TDARH | Tandem Drive Chains RH | 19712 | 19712 | 5500
500129658 | CLB-MP-GRDR-GR6504-FDRSYS-TDRAX-TDARH | Tandem Drive Assembly RH | 19712 | 19712 | 5500
500129657 | CLB-MP-GRDR-GR6504-FDRSYS-TDRAX-TDALH | Tandem Drive Chains LH | 19712 | 19712 | 5500
500129656 | CLB-MP-GRDR-GR6504-FDRSYS-TDRAX-TDALH | Tandem Drive Assembly LH | 19712 | 19712 | 5500
500129655 | CLB-MP-GRDR-GR6504-FDRSYS-FDRVE-FDRRH | Final Drive RH | 19712 | 4282 | 5500
500129654 | CLB-MP-GRDR-GR6504-FDRSYS-FDRVE-FDRLH | Final Drive LH | 19712 | 4282 | 5500
500129653 | CLB-MP-GRDR-GR6504-FDRSYS-DIFFL | Differential & Bevel Gear | 19712 | 4282 | 5500
500129652 | CLB-MP-GRDR-GR6504-FDRSYS-CHAIN-CHNRR | Drive Chain RH Rear | 19712 | 4282 | 5500
500129651 | CLB-MP-GRDR-GR6504-FDRSYS-CHAIN-CHNRF | Drive Chain RH Front | 19712 | 4282 | 5500
500129650 | CLB-MP-GRDR-GR6504-FDRSYS-CHAIN-CHNLR | Drive Chain LH Rear | 19712 | 4282 | 5500
500129649 | CLB-MP-GRDR-GR6504-FDRSYS-CHAIN-CHNLF | Drive Chain LH Front | 19712 | 4282 | 5500
500129648 | CLB-MP-GRDR-GR6504-ENGINE-LUBSY-OILPP | Oil Pump Engine | 19712 | 4282 | 5500
500129647 | CLB-MP-GRDR-GR6504-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 19712 | 4282 | 5500
500129646 | CLB-MP-GRDR-GR6504-ENGINE-LUBSY | Engine Lubrication System | 19712 | 19712 | 5500
500129645 | CLB-MP-GRDR-GR6504-ENGINE-INTEX-TURBO | Turbocharger | 19712 | 4282 | 5500
500129644 | CLB-MP-GRDR-GR6504-ENGINE-INTEX-EXHST | Exhaust Muffler | 19712 | 19712 | 5500
500129643 | CLB-MP-GRDR-GR6504-ENGINE-INTEX-AFTER | Aftercooler | 19712 | 4282 | 5500
500129642 | CLB-MP-GRDR-GR6504-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 19712 | 4282 | 5500
500129641 | CLB-MP-GRDR-GR6504-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 19712 | 4282 | 5500
500129640 | CLB-MP-GRDR-GR6504-ENGINE-FUSYS-FUINJ | Fuel Injectors | 19712 | 4282 | 5500
500129639 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-WTRPP | Water Pump Engine | 19712 | 4282 | 5500
500129638 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-THERM | Thermostats | 19712 | 4282 | 5500
500129637 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-RADTR | Radiator Coolant | 19712 | 19712 | 5000
500129636 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-RADTR | Radiator Engine | 19712 | 4282 | 5500
500129635 | CLB-MP-GRDR-GR6504-ENGINE-COSYS-COFAN | Fan Cooling System | 19712 | 19712 | 5500
500129633 | CLB-MP-GRDR-GR6504-ENGINE | Engine Assembly Caterpillar C13 ACERT | 19712 | 4282 | 5500
500129632 | CLB-MP-GRDR-GR6504-ELCTLV-START-STRMR | Starter Motor | 19712 | 4282 | 5500
500129631 | CLB-MP-GRDR-GR6504-ELCTLV-HARNS | Electrical Harness | 19712 | 4282 | 5500
500129630 | CLB-MP-GRDR-GR6504-ELCTLV-CHARG-ALTER | Alternator 24V | 19712 | 4282 | 5500
500129629 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 19712 | 4282 | 5500
500129628 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 19712 | 4282 | 5500
500129627 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 19712 | 1251 | 5500
500129626 | CLB-MP-GRDR-GR6504-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 19712 | 4282 | 5500
500129625 | CLB-MP-GRDR-GR6504-BRKSYS-BRPRK | Park Brake Assembly | 19712 | 19712 | 5500
500129624 | CLB-MP-GRDR-GR6504-BRKSYS-BRPMP | Pump Brake Hydraulic Fan | 19712 | 19712 | 5500
500129623 | CLB-MP-GRDR-GR6504-BRKSYS-BKOCO | Oil Cooler Brake Hydraulic Fan | 19712 | 19712 | 5500
500129612 | CLB-MP-GRDR-GR6504-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 19712 | 19712 | 5500
500129611 | CLB-MP-GRDR-GR6504-BRKSYS-BACCM-BACCF | Brake Accumulator Front | 19712 | 19712 | 5500
500129610 | CLB-MP-GRDR-GR6504 | GR6504 Caterpillar 18 Grader | 19712 | 19712 | 5500
500129609 | CLB-MP-GRDR-GR6503-TRNSYS-TRPMP | Pump Transmission | 34262 | 34262 | 5500
500129608 | CLB-MP-GRDR-GR6503-TRNSYS-TROLC | Transmission Oil Cooler | 19846 | 19846 | 5500
500129607 | CLB-MP-GRDR-GR6503-TRNSYS-TRANS | Transmission | 19846 | 5430 | 5500
500129606 | CLB-MP-GRDR-GR6503-TRNSYS-DRSHT | Drive Shaft | 19846 | 5430 | 5500
500129605 | CLB-MP-GRDR-GR6503-STRUCT-RIPPR-RIGET | Ripper Wear Elements GET | 19846 | 19846 | 5500
500129604 | CLB-MP-GRDR-GR6503-STRUCT-RIPPR | Ripper | 19846 | 5430 | 5500
500129603 | CLB-MP-GRDR-GR6503-STRUCT-DRWBR | Drawbar | 19846 | 5430 | 5500
500129602 | CLB-MP-GRDR-GR6503-STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 19846 | 2271 | 5500
500129601 | CLB-MP-GRDR-GR6503-STRUCT-CIRCL | Circle Assembly | 19846 | 19846 | 5500
500129600 | CLB-MP-GRDR-GR6503-STRUCT-CHASS-ARTIC | Articulation | 19846 | 19846 | 5500
500129599 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SEATS | Operators Seat | 19846 | 5430 | 5500
500129598 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-SBELT | Seat Belt | 19846 | 19846 | 5500
500129597 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 19846 | 19846 | 5500
500129596 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 19846 | 5430 | 5500
500129595 | CLB-MP-GRDR-GR6503-STRUCT-CABIN-AIRCN | Air Conditioning System | 19846 | 5430 | 5500
500129594 | CLB-MP-GRDR-GR6503-STRUCT-CABIN | Cabin | 19846 | 5430 | 5500
500129593 | CLB-MP-GRDR-GR6503-STRUCT-BLADE-MOLDB | Moldboard Skin | 19846 | 19846 | 5500
500129592 | CLB-MP-GRDR-GR6503-STRUCT-BLADE-BLGET | Blade Wear Elements GET | 19846 | 19846 | 5500
500129591 | CLB-MP-GRDR-GR6503-STRUCT-BLADE | Blade Lift Trunnions | 19846 | 19846 | 5500
500129590 | CLB-MP-GRDR-GR6503-STRUCT-BLADE | Blade | 19846 | 19846 | 5500
500129589 | CLB-MP-GRDR-GR6503-STRUCT-AXLES-HUBRH | Hub and Spindle RH | 19846 | 5430 | 5500
500129588 | CLB-MP-GRDR-GR6503-STRUCT-AXLES-HUBLH | Hub and Spindle LH | 19846 | 5430 | 5500
500129587 | CLB-MP-GRDR-GR6503-STRUCT-AXLES | Front Axle Assembly | 19846 | 5430 | 5500
500129586 | CLB-MP-GRDR-GR6503-STRSYS-STRCY-STCYR | Cylinder Steering RH | 19846 | 5430 | 5500
500129585 | CLB-MP-GRDR-GR6503-STRSYS-STRCY-STCYL | Cylinder Steering LH | 19846 | 5430 | 5500
500129584 | CLB-MP-GRDR-GR6503-STRSYS-STMTR | Steering Metering Pump | 19846 | 19846 | 5500
500129583 | CLB-MP-GRDR-GR6503-STRSYS-STLTR | Steering Linkages & Tie Rods | 19846 | 19846 | 5500
500129582 | CLB-MP-GRDR-GR6503-STRSYS-STEMG-SESPP | Pump Secondary Steering | 19846 | 5430 | 5500
500129581 | CLB-MP-GRDR-GR6503-HYDSYS-HYDPP-HYISP | Pump Implement & Steering | 19846 | 5430 | 5500
500129580 | CLB-MP-GRDR-GR6503-HYDSYS-HDOCO | Oil Cooler Hydraulic | 19846 | 5430 | 5500
500129579 | CLB-MP-GRDR-GR6503-HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 19846 | 5430 | 5500
500129578 | CLB-MP-GRDR-GR6503-HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 19846 | 19846 | 5500
500129577 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-STRNG | Steering System Hoses | 19846 | 5430 | 5500
500129576 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 19846 | 5430 | 5500
500129575 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 19846 | 5430 | 5500
500129574 | CLB-MP-GRDR-GR6503-HYDSYS-HDHLF-BRKSH | Brake System Hoses | 19846 | 5430 | 5500
500129573 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 19846 | 5430 | 5500
500129572 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 19827 | 993 | 5500
500129571 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 19846 | 5430 | 5500
500129570 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 19846 | 19846 | 5500
500129569 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 19846 | 19846 | 5500
500129568 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 19846 | 19846 | 5500
500129567 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 19846 | 16680 | 5500
500129566 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 19846 | 3088 | 5500
500129565 | CLB-MP-GRDR-GR6503-HYDSYS-HDCYL-ARCYL | Cylinder Articulation LH | 19846 | 11345 | 5500
500129564 | CLB-MP-GRDR-GR6503-HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 19846 | 5430 | 5500
500129563 | CLB-MP-GRDR-GR6503-HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 19846 | 5430 | 5500
500129562 | CLB-MP-GRDR-GR6503-HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator RH | 19846 | 19846 | 5500
500129561 | CLB-MP-GRDR-GR6503-HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator LH | 19846 | 19846 | 5500
500129560 | CLB-MP-GRDR-GR6503-GRSYST-GRINJ | Auto Lube Injectors | 19846 | 19846 | 5500
500129559 | CLB-MP-GRDR-GR6503-GRSYST-ALBPP | Auto Lube Pump | 19846 | 14857 | 5500
500129558 | CLB-MP-GRDR-GR6503-GRSYST | Grease Lubrication System | 19846 | 19846 | 5500
500129557 | CLB-MP-GRDR-GR6503-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 19846 | 19846 | 5500
500129556 | CLB-MP-GRDR-GR6503-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 19846 | 19846 | 5500
500129555 | CLB-MP-GRDR-GR6503-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 19846 | 19846 | 5500
500129554 | CLB-MP-GRDR-GR6503-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 19846 | 19846 | 5500
500129553 | CLB-MP-GRDR-GR6503-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 19846 | 19846 | 5500
500129552 | CLB-MP-GRDR-GR6503-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 19846 | 19846 | 5500
500129551 | CLB-MP-GRDR-GR6503-FDRSYS-TDRAX-TDARH | Tandem Drive Chains RH | 19846 | 19846 | 5500
500129550 | CLB-MP-GRDR-GR6503-FDRSYS-TDRAX-TDARH | Tandem Drive Assembly RH | 19846 | 19846 | 5500
500129549 | CLB-MP-GRDR-GR6503-FDRSYS-TDRAX-TDALH | Tandem Drive Chains LH | 19846 | 19846 | 5500
500129548 | CLB-MP-GRDR-GR6503-FDRSYS-TDRAX-TDALH | Tandem Drive Assembly LH | 19846 | 19846 | 5500
500129547 | CLB-MP-GRDR-GR6503-FDRSYS-FDRVE-FDRRH | Final Drive RH | 19846 | 5430 | 5500
500129546 | CLB-MP-GRDR-GR6503-FDRSYS-FDRVE-FDRLH | Final Drive LH | 19846 | 5430 | 5500
500129545 | CLB-MP-GRDR-GR6503-FDRSYS-DIFFL | Differential & Bevel Gear | 19846 | 5430 | 5500
500129544 | CLB-MP-GRDR-GR6503-FDRSYS-CHAIN-CHNRR | Drive Chain RH Rear | 19846 | 5430 | 5500
500129543 | CLB-MP-GRDR-GR6503-FDRSYS-CHAIN-CHNRF | Drive Chain RH Front | 19846 | 5430 | 5500
500129542 | CLB-MP-GRDR-GR6503-FDRSYS-CHAIN-CHNLR | Drive Chain LH Rear | 19846 | 5430 | 5500
500129541 | CLB-MP-GRDR-GR6503-FDRSYS-CHAIN-CHNLF | Drive Chain LH Front | 19846 | 5430 | 5500
500129540 | CLB-MP-GRDR-GR6503-ENGINE-LUBSY-OILPP | Oil Pump Engine | 19846 | 5430 | 5500
500129539 | CLB-MP-GRDR-GR6503-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 19846 | 5430 | 5500
500129538 | CLB-MP-GRDR-GR6503-ENGINE-LUBSY | Engine Lubrication System | 19846 | 19846 | 5500
500129537 | CLB-MP-GRDR-GR6503-ENGINE-INTEX-TURBO | Turbocharger | 19846 | 5430 | 5500
500129536 | CLB-MP-GRDR-GR6503-ENGINE-INTEX-EXHST | Exhaust Muffler | 19846 | 19846 | 5500
500129535 | CLB-MP-GRDR-GR6503-ENGINE-INTEX-AFTER | Aftercooler | 19846 | 5430 | 5500
500129534 | CLB-MP-GRDR-GR6503-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 19846 | 5430 | 5500
500129533 | CLB-MP-GRDR-GR6503-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 19846 | 5430 | 5500
500129532 | CLB-MP-GRDR-GR6503-ENGINE-FUSYS-FUINJ | Fuel Injectors | 19846 | 5430 | 5500
500129531 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-WTRPP | Water Pump Engine | 19846 | 5430 | 5500
500129530 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-THERM | Thermostats | 19846 | 5430 | 5500
500129529 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-RADTR | Radiator Coolant | 19846 | 19846 | 5000
500129528 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-RADTR | Radiator Engine | 19846 | 5430 | 5500
500129527 | CLB-MP-GRDR-GR6503-ENGINE-COSYS-COFAN | Fan Cooling System | 19846 | 19846 | 5500
500129525 | CLB-MP-GRDR-GR6503-ENGINE | Engine Assembly Caterpillar C13 ACERT | 19846 | 5430 | 5500
500129524 | CLB-MP-GRDR-GR6503-ELCTLV-START-STRMR | Starter Motor | 19846 | 5430 | 5500
500129523 | CLB-MP-GRDR-GR6503-ELCTLV-HARNS | Electrical Harness | 19846 | 5430 | 5500
500129522 | CLB-MP-GRDR-GR6503-ELCTLV-CHARG-ALTER | Alternator 24V | 19846 | 5430 | 5500
500129521 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 19846 | 5430 | 5500
500129520 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 19846 | 5430 | 5500
500129519 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 19846 | 5430 | 5500
500129518 | CLB-MP-GRDR-GR6503-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 19846 | 5430 | 5500
500129517 | CLB-MP-GRDR-GR6503-BRKSYS-BRPRK | Park Brake Assembly | 19846 | 19846 | 5500
500129516 | CLB-MP-GRDR-GR6503-BRKSYS-BRPMP | Pump Brake Hydraulic Fan | 19846 | 2388 | 5500
500129515 | CLB-MP-GRDR-GR6503-BRKSYS-BKOCO | Oil Cooler Brake Hydraulic Fan | 19846 | 19846 | 5500
500129514 | CLB-MP-GRDR-GR6503-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 19846 | 19846 | 5500
500129513 | CLB-MP-GRDR-GR6503-BRKSYS-BACCM-BACCF | Brake Accumulator Front | 19846 | 19846 | 5500
500129512 | CLB-MP-GRDR-GR6503 | GR6503 Caterpillar 18 Grader | 19846 | 19846 | 5500
500129815 | CLB-MP-GRDR-GR6501-TRNSYS-TRPMP | Pump Transmission | 20249 | 20249 | 5500
500129814 | CLB-MP-GRDR-GR6501-TRNSYS-TROLC | Transmission Oil Cooler | 20249 | 20249 | 5500
500129813 | CLB-MP-GRDR-GR6501-TRNSYS-TRANS | Transmission | 20249 | 4082 | 5500
500129812 | CLB-MP-GRDR-GR6501-TRNSYS-DRSHT | Drive Shaft | 20249 | 4082 | 5500
500129811 | CLB-MP-GRDR-GR6501-STRUCT-RIPPR-RIGET | Ripper Wear Elements GET | 20249 | 20249 | 5500
500129810 | CLB-MP-GRDR-GR6501-STRUCT-RIPPR | Ripper | 20249 | 4082 | 5500
500129809 | CLB-MP-GRDR-GR6501-STRUCT-DRWBR | Drawbar | 20249 | 4082 | 5500
500129808 | CLB-MP-GRDR-GR6501-STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 20249 | 885 | 5500
500129807 | CLB-MP-GRDR-GR6501-STRUCT-CIRCL | Circle Assembly | 20249 | 20249 | 5500
500129806 | CLB-MP-GRDR-GR6501-STRUCT-CHASS-ARTIC | Articulation | 20249 | 20249 | 5500
500129805 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-SEATS | Operators Seat | 20249 | 4082 | 5500
500129804 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-SBELT | Seat Belt | 20249 | 20249 | 5500
500129803 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 20249 | 20249 | 5500
500129802 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 20249 | 4082 | 5500
500129801 | CLB-MP-GRDR-GR6501-STRUCT-CABIN-AIRCN | Air Conditioning System | 20249 | 4082 | 5500
500129800 | CLB-MP-GRDR-GR6501-STRUCT-CABIN | Cabin | 20249 | 4082 | 5500
500129799 | CLB-MP-GRDR-GR6501-STRUCT-BLADE-MOLDB | Moldboard Skin | 20249 | 20249 | 5500
500129798 | CLB-MP-GRDR-GR6501-STRUCT-BLADE-BLGET | Blade Wear Elements GET | 20249 | 20249 | 5500
500129797 | CLB-MP-GRDR-GR6501-STRUCT-BLADE | Blade Lift Trunnions | 20249 | 20249 | 5500
500129796 | CLB-MP-GRDR-GR6501-STRUCT-BLADE | Blade | 20249 | 20249 | 5500
500129795 | CLB-MP-GRDR-GR6501-STRUCT-AXLES-HUBRH | Hub and Spindle RH | 20249 | 4082 | 5500
500129794 | CLB-MP-GRDR-GR6501-STRUCT-AXLES-HUBLH | Hub and Spindle LH | 20249 | 4082 | 5500
500129793 | CLB-MP-GRDR-GR6501-STRUCT-AXLES | Front Axle Assembly | 20249 | 4082 | 5500
500129792 | CLB-MP-GRDR-GR6501-STRSYS-STRCY-STCYR | Cylinder Steering RH | 20249 | 4082 | 5500
500129791 | CLB-MP-GRDR-GR6501-STRSYS-STRCY-STCYL | Cylinder Steering LH | 20249 | 4082 | 5500
500129790 | CLB-MP-GRDR-GR6501-STRSYS-STMTR | Steering Metering Pump | 20249 | 20249 | 5500
500129789 | CLB-MP-GRDR-GR6501-STRSYS-STLTR | Steering Linkages & Tie Rods | 20249 | 20249 | 5500
500129788 | CLB-MP-GRDR-GR6501-STRSYS-STEMG-SESPP | Pump Secondary Steering | 20249 | 3802 | 5500
500129787 | CLB-MP-GRDR-GR6501-HYDSYS-HYDPP-HYISP | Pump Implement & Steering | 20249 | 4082 | 5500
500129786 | CLB-MP-GRDR-GR6501-HYDSYS-HDOCO | Oil Cooler Hydraulic | 20249 | 4082 | 5500
500129785 | CLB-MP-GRDR-GR6501-HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 20249 | 4082 | 5500
500129784 | CLB-MP-GRDR-GR6501-HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 20249 | 20249 | 5500
500129783 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-STRNG | Steering System Hoses | 20249 | 4082 | 5500
500129782 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 20249 | 4082 | 5500
500129781 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 20249 | 4082 | 5500
500129780 | CLB-MP-GRDR-GR6501-HYDSYS-HDHLF-BRKSH | Brake System Hoses | 20249 | 4082 | 5500
500129779 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 20249 | 4082 | 5500
500129778 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 20249 | 8093 | 5500
500129777 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 20249 | 20249 | 5500
500129776 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 20249 | 20249 | 5500
500129775 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 20249 | 20249 | 5500
500129774 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 20249 | 20249 | 5500
500129773 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 20249 | 15863 | 5500
500129772 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 20249 | 4082 | 5500
500129771 | CLB-MP-GRDR-GR6501-HYDSYS-HDCYL-ARCYL | Cylinder Articulation LH | 20249 | 1782 | 5500
500129770 | CLB-MP-GRDR-GR6501-HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 20249 | 4082 | 5500
500129769 | CLB-MP-GRDR-GR6501-HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 20249 | 4082 | 5500
500129768 | CLB-MP-GRDR-GR6501-HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator RH | 20249 | 20249 | 5500
500129767 | CLB-MP-GRDR-GR6501-HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator LH | 20249 | 20249 | 5500
500129766 | CLB-MP-GRDR-GR6501-GRSYST-GRINJ | Auto Lube Injectors | 20249 | 20249 | 5500
500129765 | CLB-MP-GRDR-GR6501-GRSYST-ALBPP | Auto Lube Pump | 20249 | 4082 | 5500
500129764 | CLB-MP-GRDR-GR6501-GRSYST | Grease Lubrication System | 20249 | 20249 | 5500
500129763 | CLB-MP-GRDR-GR6501-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 20249 | 20249 | 5500
500129762 | CLB-MP-GRDR-GR6501-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 20249 | 20249 | 5500
500129761 | CLB-MP-GRDR-GR6501-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 20249 | 20249 | 5500
500129760 | CLB-MP-GRDR-GR6501-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 20249 | 20249 | 5500
500129759 | CLB-MP-GRDR-GR6501-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 20249 | 20249 | 5500
500129758 | CLB-MP-GRDR-GR6501-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 20249 | 20249 | 5500
500129757 | CLB-MP-GRDR-GR6501-FDRSYS-TDRAX-TDARH | Tandem Drive Chains RH | 20249 | 20249 | 5500
500129756 | CLB-MP-GRDR-GR6501-FDRSYS-TDRAX-TDARH | Tandem Drive Assembly RH | 20249 | 20249 | 5500
500129755 | CLB-MP-GRDR-GR6501-FDRSYS-TDRAX-TDALH | Tandem Drive Chains LH | 20249 | 20249 | 5500
500129754 | CLB-MP-GRDR-GR6501-FDRSYS-TDRAX-TDALH | Tandem Drive Assembly LH | 20249 | 20249 | 5500
500129753 | CLB-MP-GRDR-GR6501-FDRSYS-FDRVE-FDRRH | Final Drive RH | 20249 | 4082 | 5500
500129752 | CLB-MP-GRDR-GR6501-FDRSYS-FDRVE-FDRLH | Final Drive LH | 20249 | 4082 | 5500
500129751 | CLB-MP-GRDR-GR6501-FDRSYS-DIFFL | Differential & Bevel Gear | 20249 | 4082 | 5500
500129750 | CLB-MP-GRDR-GR6501-FDRSYS-CHAIN-CHNRR | Drive Chain RH Rear | 20249 | 4082 | 5500
500129749 | CLB-MP-GRDR-GR6501-FDRSYS-CHAIN-CHNRF | Drive Chain RH Front | 20249 | 4082 | 5500
500129748 | CLB-MP-GRDR-GR6501-FDRSYS-CHAIN-CHNLR | Drive Chain LH Rear | 20249 | 4082 | 5500
500129747 | CLB-MP-GRDR-GR6501-FDRSYS-CHAIN-CHNLF | Drive Chain LH Front | 20249 | 4082 | 5500
500129746 | CLB-MP-GRDR-GR6501-ENGINE-LUBSY-OILPP | Oil Pump Engine | 20249 | 4082 | 5500
500129745 | CLB-MP-GRDR-GR6501-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 20249 | 4082 | 5500
500129744 | CLB-MP-GRDR-GR6501-ENGINE-LUBSY | Engine Lubrication System | 20249 | 20249 | 5500
500129743 | CLB-MP-GRDR-GR6501-ENGINE-INTEX-TURBO | Turbocharger | 20249 | 4082 | 5500
500129742 | CLB-MP-GRDR-GR6501-ENGINE-INTEX-EXHST | Exhaust Muffler | 20249 | 20249 | 5500
500129741 | CLB-MP-GRDR-GR6501-ENGINE-INTEX-AFTER | Aftercooler | 20249 | 4082 | 5500
500129740 | CLB-MP-GRDR-GR6501-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 20249 | 4082 | 5500
500129739 | CLB-MP-GRDR-GR6501-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 20249 | 4082 | 5500
500129738 | CLB-MP-GRDR-GR6501-ENGINE-FUSYS-FUINJ | Fuel Injectors | 20249 | 4082 | 5500
500129737 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-WTRPP | Water Pump Engine | 20249 | 4082 | 5500
500129736 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-THERM | Thermostats | 20249 | 4082 | 5500
500129735 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-RADTR | Radiator Coolant | 20249 | 20249 | 5000
500129734 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-RADTR | Radiator Engine | 20249 | 4082 | 5500
500129733 | CLB-MP-GRDR-GR6501-ENGINE-COSYS-COFAN | Fan Cooling System | 20249 | 20249 | 5500
500129731 | CLB-MP-GRDR-GR6501-ENGINE | Engine Assembly Caterpillar C13 ACERT | 20249 | 4082 | 5500
500129730 | CLB-MP-GRDR-GR6501-ELCTLV-START-STRMR | Starter Motor | 20249 | 4082 | 5500
500129729 | CLB-MP-GRDR-GR6501-ELCTLV-HARNS | Electrical Harness | 20249 | 4082 | 5500
500129728 | CLB-MP-GRDR-GR6501-ELCTLV-CHARG-ALTER | Alternator 24V | 20249 | 4082 | 5500
500129727 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 20249 | 4082 | 5500
500129726 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 20249 | 4082 | 5500
500129725 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 20249 | 4082 | 5500
500129724 | CLB-MP-GRDR-GR6501-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 20249 | 4082 | 5500
500129723 | CLB-MP-GRDR-GR6501-BRKSYS-BRPRK | Park Brake Assembly | 20249 | 20249 | 5500
500129722 | CLB-MP-GRDR-GR6501-BRKSYS-BRPMP | Pump Brake Hydraulic Fan | 20249 | 4082 | 5500
500129721 | CLB-MP-GRDR-GR6501-BRKSYS-BKOCO | Oil Cooler Brake Hydraulic Fan | 20249 | 20249 | 5500
500129720 | CLB-MP-GRDR-GR6501-BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 20249 | 20249 | 5500
500129719 | CLB-MP-GRDR-GR6501-BRKSYS-BACCM-BACCF | Brake Accumulator Front | 20249 | 20249 | 5500
500129718 | CLB-MP-GRDR-GR6501 | GR6501 Caterpillar 18 Grader | 20249 | 20249 | 5500
500083229 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 51804 | 11096 | 4000
500083211 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 51804 | 11096 | 4000
500083193 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNRF | Drive Chain R/H Front | 51804 | 11096 | 4000
500083165 | CLB-MP-GRDR-GR102 -FDRSYS-CHAIN-CHNLF | Drive Chain L/H Front | 51804 | 11096 | 4000
500068257 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-STRNG | GR102 Steering Hoses | 51804 | 17152 | 4000
500068255 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-PWTRN | GR102 Power Train Hoses | 51804 | 11096 | 4000
500068252 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-HYDSH | GR102 Hydraulic System Hoses | 51804 | 11096 | 4000
500068242 | CLB-MP-GRDR-GR102 -COMMUN-RADIO | GR102 Two Way Radio | 51804 | 51804 | 4000
500068241 | CLB-MP-GRDR-GR102 -COMMUN | GR102 Communications | 51804 | 51804 | 4000
500068240 | CLB-MP-GRDR-GR102 -MANGMT-UMMMC | GR102 Mine Monitoring and Control | 51804 | 51804 | 4000
500068239 | CLB-MP-GRDR-GR102 -MANGMT-UMTRN | GR102 Transmission Management System | 51804 | 51804 | 4000
500068238 | CLB-MP-GRDR-GR102 -MANGMT-UMENG | GR102 Engine Management System | 51804 | 51804 | 4000
500068237 | CLB-MP-GRDR-GR102 -MANGMT | GR102 Unit Management | 51804 | 51804 | 4000
500068236 | CLB-MP-GRDR-GR102 -FRSUPP-FSALM | GR102 Fire System Alarm | 51804 | 51804 | 4000
500068235 | CLB-MP-GRDR-GR102 -FRSUPP-FSMAN-EXTIN | GR102 Hand Held Fire Extinguisher | 51804 | 51804 | 4000
500068234 | CLB-MP-GRDR-GR102 -FRSUPP-FSMAN | GR102 Fire Suppression Manual | 51804 | 51804 | 4000
500068233 | CLB-MP-GRDR-GR102 -FRSUPP-FSAUT-FFOAM | GR102 Fire Suppression Foam | 51804 | 51804 | 4000
500068232 | CLB-MP-GRDR-GR102 -FRSUPP-FSAUT | GR102 Fire Suppression Automatic | 51804 | 51804 | 4000
500068231 | CLB-MP-GRDR-GR102 -FRSUPP | GR102 Fire Suppression System | 51804 | 11096 | 4000
500068230 | CLB-MP-GRDR-GR102 -STRUCT-PLHAN | GR102 Platforms and Handrails | 51804 | 51804 | 4000
500068229 | CLB-MP-GRDR-GR102 -STRUCT-STLAD-SLAUT | GR102 Automatic Access Systems | 51804 | 51804 | 4000
500068228 | CLB-MP-GRDR-GR102 -STRUCT-STLAD-SLFXD | GR102 Fixed Steps and Ladders | 51804 | 51804 | 4000
500068227 | CLB-MP-GRDR-GR102 -STRUCT-STLAD | GR102 Steps and Ladders | 51804 | 51804 | 4000
500068226 | CLB-MP-GRDR-GR102 -STRUCT-PNLGU | GR102 Panels and Guards | 51804 | 51804 | 4000
500068225 | CLB-MP-GRDR-GR102 -STRUCT-RIPPR-RIGET | GR102 Ripper Wear Elements (GET) | 51804 | 51804 | 4000
500068224 | CLB-MP-GRDR-GR102 -STRUCT-RIPPR | GR102 Ripper | 51804 | 11096 | 4000
500068223 | CLB-MP-GRDR-GR102 -STRUCT-BLADE-BLGET | GR102 Blade Wear Elements (GET) | 51804 | 51804 | 4000
500068222 | CLB-MP-GRDR-GR102 -STRUCT-BLADE-MOLDB | GR102 Moldboard Skin | 51804 | 51804 | 4000
500068221 | CLB-MP-GRDR-GR102 -STRUCT-BLADE | GR102 Blade | 51804 | 51804 | 4000
500068220 | CLB-MP-GRDR-GR102 -STRUCT-DRWBR | GR102 Drawbar Assembly | 51804 | 11096 | 4000
500068219 | CLB-MP-GRDR-GR102 -STRUCT-CIRCL-CDRBX | GR102 Gearbox Circle Drive | 51804 | 11096 | 4000
500068218 | CLB-MP-GRDR-GR102 -STRUCT-CIRCL-BLMBR | GR102 Blade Mounting Bracket R/H | 51804 | 51804 | 4000
500068217 | CLB-MP-GRDR-GR102 -STRUCT-CIRCL-BLMBL | GR102 Blade Mounting Bracket L/H | 51804 | 51804 | 4000
500068216 | CLB-MP-GRDR-GR102 -STRUCT-CIRCL | GR102 Circle Assembly | 51804 | 51804 | 4000
500068215 | CLB-MP-GRDR-GR102 -STRUCT-AXLES-HUBRH | GR102 Hub and Spindle R/H | 51804 | 1584 | 4000
500068214 | CLB-MP-GRDR-GR102 -STRUCT-AXLES-HUBLH | GR102 Hub and Spindle L/H | 51804 | 1584 | 4000
500068213 | CLB-MP-GRDR-GR102 -STRUCT-AXLES | GR102 Front Axle Assembly | 51804 | 1584 | 4000
500068212 | CLB-MP-GRDR-GR102 -STRUCT-CHASS-ROPSS | GR102 Rollover Protective Structure | 51804 | 51804 | 4000
500068211 | CLB-MP-GRDR-GR102 -STRUCT-CHASS-ARTIC | GR102 Articulation | 51804 | 11096 | 4000
500068210 | CLB-MP-GRDR-GR102 -STRUCT-CHASS-REFRM | GR102 Rear Frame | 51804 | 51804 | 4000
500068209 | CLB-MP-GRDR-GR102 -STRUCT-CHASS-FRFRM | GR102 Front Frame | 51804 | 51804 | 4000
500068208 | CLB-MP-GRDR-GR102 -STRUCT-CHASS | GR102 Chassis | 51804 | 51804 | 4000
500068207 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-SBELT | GR102 Seat Belt | 51804 | 51804 | 4000
500068206 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-GLASS | GR102 Glass | 51804 | 51804 | 4000
500068205 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-SEATS | GR102 Operators Seat | 51804 | 3348 | 4000
500068204 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-CABES | GR102 Cabin Entertainment System | 51804 | 51804 | 4000
500068203 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-CABCO | GR102 Cabin Controls | 51804 | 51804 | 4000
500068202 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-CABPR | GR102 Cabin Pressurisation System | 51804 | 51804 | 4000
500068201 | CLB-MP-GRDR-GR102 -STRUCT-CABIN-AIRCN | GR102 Air Conditioning System | 51804 | 11096 | 4000
500068200 | CLB-MP-GRDR-GR102 -STRUCT-CABIN | GR102 Operators Cabin | 51804 | 51804 | 4000
500068199 | CLB-MP-GRDR-GR102 -STRUCT | GR102 Structure | 51804 | 51804 | 4000
500068198 | CLB-MP-GRDR-GR102 -GRSYST-ALHLF | GR102 Auto Lube Hoses Lines Fittings | 51804 | 51804 | 4000
500068197 | CLB-MP-GRDR-GR102 -GRSYST-ALELC | GR102 Auto Lube Electrical | 51804 | 51804 | 4000
500068196 | CLB-MP-GRDR-GR102 -GRSYST-ALCON | GR102 Auto Lube Controller | 51804 | 51804 | 4000
500068195 | CLB-MP-GRDR-GR102 -GRSYST-ALBPP | GR102 Auto Lube Pump | 51804 | 11096 | 4000
500068194 | CLB-MP-GRDR-GR102 -GRSYST-GRTNK | GR102 Auto Lube Resevoir | 51804 | 51804 | 4000
500068193 | CLB-MP-GRDR-GR102 -GRSYST-GRINJ | GR102 Auto Lube Injectors | 51804 | 51804 | 4000
500068192 | CLB-MP-GRDR-GR102 -GRSYST | GR102 Grease Lubrication System | 51804 | 34862 | 4000
500068191 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF | GR102 Hydraulic System Hoses Lines Fitti | 51804 | 51804 | 4000
500068190 | CLB-MP-GRDR-GR102 -HYDSYS-HDOCO | GR102 Oil Cooler Hydraulic | 51804 | 51804 | 4000
500068189 | CLB-MP-GRDR-GR102 -HYDSYS-HDTNK | GR102 Tank Hydraulic | 51804 | 51804 | 4000
500068188 | CLB-MP-GRDR-GR102 -HYDSYS-HDACC-BLCUR | GR102 Blade Cushion Accumulator R/H | 51804 | 51804 | 4000
500068187 | CLB-MP-GRDR-GR102 -HYDSYS-HDACC-BLCUL | GR102 Blade Cushion Accumulator L/H | 51804 | 51804 | 4000
500068186 | CLB-MP-GRDR-GR102 -HYDSYS-HDACC | GR102 Blade Cushion Accumulators | 51804 | 51804 | 4000
500068185 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-WLCYL | GR102 Cylinder Wheel Lean | 51804 | 51804 | 4000
500068184 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-RICYL | GR102 Cylinder Ripper Lift | 51804 | 51804 | 4000
500068183 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-SSCYL | GR102 Cylinder Side Shift | 51804 | 1584 | 4000
500068182 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-CSCYL | GR102 Cylinder Centre Shift | 51804 | 51804 | 4000
500068181 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-ARCYR | GR102 Cylinder Articulation R/H | 51804 | 32491 | 4000
500068180 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-ARCYL | GR102 Cylinder Articulation L/H | 51804 | 13607 | 4000
500068179 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-BTICY | GR102 Cylinder Blade Tilt | 51804 | 31133 | 4000
500068178 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-BLCYR | GR102 Cylinder Blade Lift R/H | 51804 | 51804 | 4000
500068177 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL-BLCYL | GR102 Cylinder Blade Lift L/H | 51804 | 32420 | 4000
500068176 | CLB-MP-GRDR-GR102 -HYDSYS-HDCYL | GR102 Cylinders Hydraulic | 51804 | 29962 | 4000
500068175 | CLB-MP-GRDR-GR102 -HYDSYS-HDMOT-MOFAN | GR102 Motor Hydraulic Fan | 51804 | 11096 | 4000
500068174 | CLB-MP-GRDR-GR102 -HYDSYS-HDMOT-MOCDG | GR102 Motor Circle Drive Gearbox | 51804 | 51804 | 4000
500068173 | CLB-MP-GRDR-GR102 -HYDSYS-HDMOT | GR102 Motors Hydraulic | 51804 | 51804 | 4000
500068172 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL-REAR1 | GR102 Implement Control Valve Rear | 51804 | 11096 | 4000
500068171 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL-FRONT | GR102 Implement Control Valve Front | 51804 | 11096 | 4000
500068170 | CLB-MP-GRDR-GR102 -HYDSYS-HDCVL | GR102 Implement Control Valves Hydraulic | 51804 | 51804 | 4000
500068169 | CLB-MP-GRDR-GR102 -HYDSYS-HYDPP-HYISP | GR102 Pump Implement and Steering | 51804 | 11096 | 4000
500068168 | CLB-MP-GRDR-GR102 -HYDSYS-HYDPP | GR102 Pumps Hydraulic | 51804 | 51804 | 4000
500068167 | CLB-MP-GRDR-GR102 -HYDSYS | GR102 Hydraulic System | 51804 | 51804 | 4000
500068166 | CLB-MP-GRDR-GR102 -STRSYS-STHLF | GR102 Steering System Hoses Lines and Fi | 51804 | 24852 | 4000
500068165 | CLB-MP-GRDR-GR102 -STRSYS-STLTR | GR102 Steering Linkages and Tie Rods | 51804 | 31133 | 4000
500068164 | CLB-MP-GRDR-GR102 -STRSYS-STEMG-SESPP | GR102 Pump Secondary Steering | 51804 | 11096 | 4000
500068163 | CLB-MP-GRDR-GR102 -STRSYS-STEMG | GR102 Emergency Steering System | 51804 | 51804 | 4000
500068162 | CLB-MP-GRDR-GR102 -STRSYS-STMTR | GR102 Steering Metering Pump | 51804 | 51804 | 4000
500068161 | CLB-MP-GRDR-GR102 -STRSYS-STRCY-STCYR | GR102 Cylinder Steering R/H | 51804 | 1584 | 4000
500068160 | CLB-MP-GRDR-GR102 -STRSYS-STRCY-STCYL | GR102 Cylinder Steering L/H | 51804 | 1584 | 4000
500068159 | CLB-MP-GRDR-GR102 -STRSYS-STRCY | GR102 Cylinders Steering | 51804 | 51804 | 4000
500068158 | CLB-MP-GRDR-GR102 -STRSYS | GR102 Steering System | 51804 | 51804 | 4000
500068157 | CLB-MP-GRDR-GR102 -BRKSYS-BRHLF | GR102 Brake System Hoses Lines and Fitti | 51804 | 51804 | 4000
500068156 | CLB-MP-GRDR-GR102 -BRKSYS-BRPRK | GR102 Park Brake Assembly | 51804 | 51804 | 4000
500068155 | CLB-MP-GRDR-GR102 -BRKSYS-BRVSR | GR102 Valve Service Brake Control | 51804 | 51804 | 4000
500068154 | CLB-MP-GRDR-GR102 -BRKSYS-BRVLP | GR102 Valve Brake Pump Control | 51804 | 51804 | 4000
500068153 | CLB-MP-GRDR-GR102 -BRKSYS-BRPMP | GR102 Pump Brake / Hydraulic Fan | 51804 | 11096 | 4000
500068152 | CLB-MP-GRDR-GR102 -BRKSYS-BKOCO | GR102 Oil Cooler Brake / Hydraulic Fan | 51804 | 51804 | 4000
500068151 | CLB-MP-GRDR-GR102 -BRKSYS-BACCM-REAR1 | GR102 Brake Accumulator Rear | 51804 | 51804 | 4000
500068150 | CLB-MP-GRDR-GR102 -BRKSYS-BACCM-FRONT | GR102 Brake Accumulator Front | 51804 | 51804 | 4000
500068149 | CLB-MP-GRDR-GR102 -BRKSYS-BACCM | GR102 Brake Accumulators | 51804 | 11096 | 4000
500068148 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRR | GR102 Service Brake R/H Rear | 51804 | 2872 | 4000
500068147 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBLR | GR102 Service Brake L/H Rear | 51804 | 2872 | 4000
500068146 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBRF | GR102 Service Brake R/H Front | 51804 | 6119 | 4000
500068145 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK-SVBLF | GR102 Service Brake L/H Front | 51804 | 2872 | 4000
500068144 | CLB-MP-GRDR-GR102 -BRKSYS-SRVBK | GR102 Service Brake | 51804 | 51804 | 4000
500068143 | CLB-MP-GRDR-GR102 -BRKSYS | GR102 Braking System | 51804 | 51804 | 4000
500068142 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR-POS06 | GR102 Tyre Position 6 | 51804 | 51804 | 4000
500068141 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR-POS05 | GR102 Tyre Position 5 | 51804 | 51804 | 4000
500068140 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR-POS04 | GR102 Tyre Position 4 | 51804 | 51804 | 4000
500068139 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR-POS03 | GR102 Tyre Position 3 | 51804 | 51804 | 4000
500068138 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR-POS02 | GR102 Tyre Position 2 | 51804 | 51804 | 4000
500068137 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR-POS01 | GR102 Tyre Position 1 | 51804 | 51804 | 4000
500068136 | CLB-MP-GRDR-GR102 -FDRSYS-WHTYR | GR102 Wheels Tyres and Rims | 51804 | 51804 | 4000
500068135 | CLB-MP-GRDR-GR102 -FDRSYS-TDRAX-TDARH | GR102 Tandem Drive Assembly R/H | 51804 | 51804 | 4000
500068134 | CLB-MP-GRDR-GR102 -FDRSYS-TDRAX-TDALH | GR102 Tandem Drive Assembly L/H | 51804 | 51804 | 4000
500068133 | CLB-MP-GRDR-GR102 -FDRSYS-TDRAX | GR102 Tandem Drive Axles | 51804 | 51804 | 4000
500068132 | CLB-MP-GRDR-GR102 -FDRSYS-FDRVE-FDRRH | GR102 Final Drive R/H | 51804 | 24852 | 4000
500068131 | CLB-MP-GRDR-GR102 -FDRSYS-FDRVE-FDRLH | GR102 Final Drive L/H | 51804 | 24852 | 4000
500068130 | CLB-MP-GRDR-GR102 -FDRSYS-FDRVE | GR102 Final Drives | 51804 | 24852 | 4000
500068129 | CLB-MP-GRDR-GR102 -FDRSYS-DIFFL | GR102 Differential and Bevel Gear | 51804 | 11096 | 4000
500068128 | CLB-MP-GRDR-GR102 -FDRSYS | GR102 Final Drive System | 51804 | 51804 | 4000
500068127 | CLB-MP-GRDR-GR102 -TRNSYS-TRPMP | GR102 Pump Transmission | 51804 | 51804 | 4000
500068126 | CLB-MP-GRDR-GR102 -TRNSYS-TROLC | GR102 Oil Cooler Transmission | 51804 | 51804 | 4000
500068125 | CLB-MP-GRDR-GR102 -TRNSYS-TRANS | GR102 Transmission | 51804 | 11096 | 4000
500068124 | CLB-MP-GRDR-GR102 -TRNSYS | GR102 Transmission System | 51804 | 11096 | 4000
500068123 | CLB-MP-GRDR-GR102 -ELCTLV-START-STRMR | GR102 Starter Motor | 51804 | 3119 | 4000
500068122 | CLB-MP-GRDR-GR102 -ELCTLV-START | GR102 Electrical Starting System | 51804 | 51804 | 4000
500068121 | CLB-MP-GRDR-GR102 -ELCTLV-CHARG-BATTY | GR102 Batteries | 51804 | 9114 | 4000
500068120 | CLB-MP-GRDR-GR102 -ELCTLV-CHARG-ALTER | GR102 Alternator 24V | 51804 | 3119 | 4000
500068119 | CLB-MP-GRDR-GR102 -ELCTLV-CHARG | GR102 Charging System | 51804 | 51804 | 4000
500068118 | CLB-MP-GRDR-GR102 -ELCTLV-LIGHT | GR102 Lighting Low Voltage | 51804 | 51804 | 4000
500068117 | CLB-MP-GRDR-GR102 -ELCTLV-CONTL | GR102 Electrical Controls Low Voltage | 51804 | 51804 | 4000
500068116 | CLB-MP-GRDR-GR102 -ELCTLV-HARNS | GR102 Electrical Harness | 51804 | 11096 | 4000
500068115 | CLB-MP-GRDR-GR102 -ELCTLV | GR102 Electrical System Low Voltage 24V | 51804 | 51804 | 4000
500068114 | CLB-MP-GRDR-GR102 -ENGINE-FUSYS-FUHLF | GR102 Fuel System Hoses Lines and Fittin | 51804 | 51804 | 4000
500068113 | CLB-MP-GRDR-GR102 -ENGINE-FUSYS-FUINJ | GR102 Fuel Injectors | 51804 | 3119 | 4000
500068112 | CLB-MP-GRDR-GR102 -ENGINE-FUSYS-FULTP | GR102 Pump Fuel Transfer | 51804 | 3119 | 4000
500068111 | CLB-MP-GRDR-GR102 -ENGINE-FUSYS-FULPP | GR102 Pump Fuel Priming | 51804 | 3119 | 4000
500068110 | CLB-MP-GRDR-GR102 -ENGINE-FUSYS-FULTK | GR102 Fuel Tank | 51804 | 51804 | 4000
500068109 | CLB-MP-GRDR-GR102 -ENGINE-FUSYS | GR102 Fuel System | 51804 | 51804 | 4000
500068108 | CLB-MP-GRDR-GR102 -ENGINE-INTEX-EXHST | GR102 Exhaust System | 51804 | 11096 | 4000
500068107 | CLB-MP-GRDR-GR102 -ENGINE-INTEX-AFTER | GR102 Aftercooler | 51804 | 51804 | 4000
500068106 | CLB-MP-GRDR-GR102 -ENGINE-INTEX-TURBO | GR102 Turbocharger | 51804 | 3119 | 4000
500068105 | CLB-MP-GRDR-GR102 -ENGINE-INTEX-AIRFL | GR102 Air Filtration System | 51804 | 24852 | 4000
500068104 | CLB-MP-GRDR-GR102 -ENGINE-INTEX | GR102 Intake and Exhaust System | 51804 | 51804 | 4000
500068103 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-CSHLF | GR102 Cooling System Hoses Lines and Fit | 51804 | 3119 | 4000
500068102 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-THERM | GR102 Thermostats/Regulators | 51804 | 3119 | 4000
500068101 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-BELTS | GR102 Engine Belts | 51804 | 51804 | 4000
500068100 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-COFAN | GR102 Fan Cooling System | 51814 | 11096 | 4000
500068099 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-RADTR | GR102 Radiator Engine | 51804 | 11096 | 4000
500068098 | CLB-MP-GRDR-GR102 -ENGINE-COSYS-WTRPP | GR102 Water Pump Engine | 51804 | 3119 | 4000
500068097 | CLB-MP-GRDR-GR102 -ENGINE-COSYS | GR102 Engine Cooling System | 51814 | 51814 | 4000
500068096 | CLB-MP-GRDR-GR102 -ENGINE-LUBSY-ENOLC | GR102 Oil Cooler Engine | 51814 | 51814 | 4000
500068095 | CLB-MP-GRDR-GR102 -ENGINE-LUBSY-OILPP | GR102 Oil Pump Engine | 51804 | 51804 | 4000
500068094 | CLB-MP-GRDR-GR102 -ENGINE-LUBSY | GR102 Engine Lubrication System | 51814 | 51814 | 4000
500068093 | CLB-MP-GRDR-GR102 -ENGINE | GR102 Engine Assembly Caterpillar C13 AC | 51814 | 11096 | 4000
500067934 | CLB-MP-GRDR-GR102 -HYDSYS-HDHLF-BRKS | GR102 Brake System Hoses and Fittings | 51814 | 11096 | 4000
500052596 | CLB-MP-GRDR-GR102 | GR102 Lube & Mechanical Services | 51903 | 51903 | 4000
500052595 | CLB-MP-GRDR-GR102 | Caterpillar 16M Motor Grader GR102 | 51814 | 51814 | 4000
500148499 | CLB-MP-GRDR-GR021 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 73692 | 73692 | 6000
500148498 | CLB-MP-GRDR-GR021 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 73692 | 73692 | 6000
500148497 | CLB-MP-GRDR-GR021 -BRKSYS-BRACC | Brake Accumulator RH | 73692 | 73692 | 6000
500148496 | CLB-MP-GRDR-GR021 -BRKSYS-BRACC | Brake Accumulator LH | 73692 | 73692 | 6000
500125647 | CLB-MP-GRDR-GR021 -ELCTLV-START-STRMR | Starter Motor | 73692 | 14685 | 6000
500104456 | CLB-MP-GRDR-GR021 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 73692 | 31161 | 6000
500104455 | CLB-MP-GRDR-GR021 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 73692 | 31161 | 6000
500083244 | CLB-MP-GRDR-GR021 -BRKSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 73692 | 14685 | 6000
500083226 | CLB-MP-GRDR-GR021 -BRKSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 73692 | 14685 | 6000
500083208 | CLB-MP-GRDR-GR021 -BRKSYS-CHAIN-CHNRF | Drive Chain R/H Front | 73692 | 14685 | 6000
500083190 | CLB-MP-GRDR-GR021 -BRKSYS-CHAIN-CHNLF | Drive Chain L/H Front | 73692 | 14685 | 6000
500063199 | CLB-MP-GRDR-GR021 -ELCTLV-HARNS | Electrical Harness | 73692 | 14685 | 6000
500063191 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 73692 | 14685 | 6000
500063190 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 73692 | 14685 | 6000
500063189 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 73692 | 14685 | 6000
500063188 | CLB-MP-GRDR-GR021 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 73692 | 14685 | 6000
500043599 | CLB-MP-GRDR-GR021 -MANGMT-UMMMC | Mine Monitoring and Control | 73692 | 73692 | 6000
500043598 | CLB-MP-GRDR-GR021 -MANGMT-UMTRM | Transmission Management System | 73692 | 73692 | 6000
500043597 | CLB-MP-GRDR-GR021 -MANGMT-UMENG | Engine Management System | 73692 | 73692 | 6000
500043596 | CLB-MP-GRDR-GR021 -FRSUPP-FSMAN-EXTIN | Fire Extinguisher Hand Held | 73692 | 73692 | 6000
500043595 | CLB-MP-GRDR-GR021 -FRSUPP-FSAUT-FFOAM | Foam Fire Suppresion | 73692 | 73692 | 6000
500043594 | CLB-MP-GRDR-GR021 -STRUCT-RIPPR-RIGET | Ripper GET | 73692 | 73692 | 6000
500043593 | CLB-MP-GRDR-GR021 -STRUCT-RIPPR | Ripper Assembly | 73692 | 73692 | 6000
500043592 | CLB-MP-GRDR-GR021 -STRUCT-BLADE-BLGET | Blade GET | 73692 | 73692 | 6000
500043591 | CLB-MP-GRDR-GR021 -STRUCT-BLADE-MOLDB | Moldboard Skin | 73692 | 73692 | 6000
500043590 | CLB-MP-GRDR-GR021 -STRUCT-BLADE | Blade | 73692 | 57452 | 6000
500043589 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-CDBXR | Circle Drive Gearbox R/H | 73692 | 334 | 6000
500043588 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-CDBXF | Circle Drive Gearbox L/H | 73692 | 334 | 6000
500043587 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBR | Bracket Blade Mounting R/H | 73692 | 14685 | 6000
500043586 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL-BLMBL | Bracket Blade Mounting L/H | 73692 | 14685 | 6000
500043585 | CLB-MP-GRDR-GR021 -STRUCT-CIRCL | Circle Assembly | 73692 | 73692 | 6000
500043584 | CLB-MP-GRDR-GR021 -STRUCT-DRWBR | Trunnions Blade Lift | 73692 | 14685 | 6000
500043583 | CLB-MP-GRDR-GR021 -STRUCT-DRWBR | Drawbar Group | 73692 | 14685 | 6000
500043582 | CLB-MP-GRDR-GR021 -STRUCT-AXLES-HUBRH | Wheel Bearings RH Front | 73692 | 5153 | 6000
500043581 | CLB-MP-GRDR-GR021 -STRUCT-AXLES-HUBLH | Wheel Bearings LH Front | 73692 | 5153 | 6000
500043580 | CLB-MP-GRDR-GR021 -STRUCT-AXLES | Axle Assembly Front | 73692 | 2651 | 6000
500043579 | CLB-MP-GRDR-GR021 -STRUCT-CHASS-ARTIC | Articulation Hitch | 73692 | 14685 | 6000
500043578 | CLB-MP-GRDR-GR021 -STRUCT-CHASS-REFRM | Rear Frame | 73692 | 73692 | 6000
500043577 | CLB-MP-GRDR-GR021 -STRUCT-CHASS-FRFRM | Front Frame | 73692 | 73692 | 6000
500043576 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-SBELT | Belt Seat | 73692 | 73692 | 6000
500043575 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-SEATS | Seat Operator | 73692 | 1802 | 6000
500043574 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-CABES | Pressurisation System Cabin | 73692 | 73692 | 6000
500043573 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-CABCO | Condensor Air Conditioning | 73692 | 73692 | 6000
500043572 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-CABPR | Compressor Air Cond System | 73692 | 73692 | 6000
500043571 | CLB-MP-GRDR-GR021 -STRUCT-CABIN-AIRCN | Air Conditioning System | 73692 | 14685 | 6000
500043570 | CLB-MP-GRDR-GR021 -STRUCT-CABIN | Operators Cabin | 73692 | 14685 | 6000
500043569 | CLB-MP-GRDR-GR021 -GRSYST-ALCON | Controller Auto Lube | 73692 | 73692 | 6000
500043568 | CLB-MP-GRDR-GR021 -GRSYST-ALBPP | Pump Auto Lube | 73692 | 14685 | 6000
500043567 | CLB-MP-GRDR-GR021 -GRSYST-GRTNK | Resevoir Auto Lube | 73692 | 73692 | 6000
500043566 | CLB-MP-GRDR-GR021 -GRSYST-GRINJ | Injectors Auto Lube | 73692 | 73692 | 6000
500043565 | CLB-MP-GRDR-GR021 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 73692 | 73692 | 6000
500043564 | CLB-MP-GRDR-GR021 -HYDSYS-HDTNK | Tank Hydraulic | 73692 | 73692 | 6000
500043563 | CLB-MP-GRDR-GR021 -HYDSYS-HDACC | Accumulator Blade Cushion | 73692 | 73692 | 6000
500043562 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-WLCYR | Cylinder Wheel Lean R/H | 73692 | 31948 | 6000
500043561 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean L/H | 73692 | 43577 | 6000
500043560 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 73692 | 334 | 6000
500043559 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 73692 | 14685 | 6000
500043558 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-SSCYL | Cylinder Blade Side Shift | 73692 | 2651 | 6000
500043557 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 73692 | 29437 | 6000
500043556 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 73692 | 14685 | 6000
500043555 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-ARCYL | Clinder Articulation LH | 73692 | 14685 | 6000
500043554 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tip RH | 73692 | 14685 | 6000
500043553 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tip LH | 73692 | 14685 | 6000
500043552 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 73692 | 27312 | 6000
500043551 | CLB-MP-GRDR-GR021 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 73692 | 4143 | 6000
500043550 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT03 | Fan Motor | 73692 | 14685 | 6000
500043549 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT02 | Motor Circle Drive Rear | 73692 | 33039 | 6000
500043548 | CLB-MP-GRDR-GR021 -HYDSYS-HDMOT-MOT01 | Motor Circle Drive Front | 73692 | 42391 | 6000
500043547 | CLB-MP-GRDR-GR021 -HYDSYS-HDCVL-BK5RH | Valve Hyd Control R/H | 73692 | 73692 | 6000
500043546 | CLB-MP-GRDR-GR021 -HYDSYS-HDCVL-BK5LH | Valve Hyd Control | 73692 | 73692 | 6000
500043545 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-DIFFL | Pump Diff lock | 73692 | 14685 | 6000
500043544 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-FANPP | Pump Fan Motor & Brakes | 73692 | 3215 | 6000
500043543 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYSTP | Pump Steering | 73692 | 3215 | 6000
500043542 | CLB-MP-GRDR-GR021 -HYDSYS-HYDPP-HYIMP | Pump Implement | 73692 | 14685 | 6000
500043541 | CLB-MP-GRDR-GR021 -HYDSYS | Hydraulic System | 73692 | 73692 | 6000
500043540 | CLB-MP-GRDR-GR021 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 73692 | 14685 | 6000
500043539 | CLB-MP-GRDR-GR021 -STRSYS-STCON | Valve Steering Control | 73692 | 73692 | 6000
500043538 | CLB-MP-GRDR-GR021 -STRSYS-STLTR | Steering Linkage | 73692 | 14685 | 6000
500043537 | CLB-MP-GRDR-GR021 -STRSYS-STRCY-STCYR | Steering Cylinder RH | 73692 | 5153 | 6000
500043536 | CLB-MP-GRDR-GR021 -STRSYS-STRCY-STCYL | Steering Cylinder LH | 73692 | 5153 | 6000
500043535 | CLB-MP-GRDR-GR021 -BRKSYS-BRACC-ACC02 | Accumulator Brake Left | 73692 | 73692 | 6000
500043534 | CLB-MP-GRDR-GR021 -BRKSYS-BRACC-ACC01 | Accumulator Brake Right | 73692 | 73692 | 6000
500043533 | CLB-MP-GRDR-GR021 -BRKSYS-BRCON | Valve Brake Control | 73692 | 73692 | 6000
500043532 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACR | Slack Adjuster Brake Right | 73692 | 14685 | 6000
500043531 | CLB-MP-GRDR-GR021 -BRKSYS-SLACK-SLACL | Slack Adjuster Brake Left | 73692 | 14685 | 6000
500043530 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRR | Brake Assembly RHR | 73692 | 14685 | 6000
500043529 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLR | Brake Assembly LHR | 73692 | 14685 | 6000
500043528 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBRF | Brake Assembly RHF | 73692 | 14685 | 6000
500043527 | CLB-MP-GRDR-GR021 -BRKSYS-SRVBK-SVBLF | Brake Assembly LHF | 73692 | 14685 | 6000
500043526 | CLB-MP-GRDR-GR021 -FDRSYS-WHTYR-POS06 | POS 6 Tyre & Rim | 73692 | 73692 | 6000
500043525 | CLB-MP-GRDR-GR021 -FDRSYS-WHTYR-POS05 | POS 5 Tyre & Rim | 73692 | 73692 | 6000
500043524 | CLB-MP-GRDR-GR021 -FDRSYS-WHTYR-POS04 | POS 4 Tyre & Rim | 73692 | 73692 | 6000
500043523 | CLB-MP-GRDR-GR021 -FDRSYS-WHTYR-POS03 | POS 3 Tyre & Rim | 73692 | 73692 | 6000
500043522 | CLB-MP-GRDR-GR021 -FDRSYS-WHTYR-POS02 | POS 2 Tyre & Rim | 73692 | 73692 | 6000
500043521 | CLB-MP-GRDR-GR021 -FDRSYS-WHTYR-POS01 | POS 1 Tyre & Rim | 73692 | 73692 | 6000
500043520 | CLB-MP-GRDR-GR021 -FDRSYS-TDRAX-TDARH | Tandem RH | 73692 | 73692 | 6000
500043519 | CLB-MP-GRDR-GR021 -FDRSYS-TDRAX-TDALH | Tandem LH | 73692 | 73692 | 6000
500043518 | CLB-MP-GRDR-GR021 -FDRSYS-FDRVE-FDRRH | Final Drive RH | 73692 | 25022 | 6000
500043517 | CLB-MP-GRDR-GR021 -FDRSYS-FDRVE-FDRLH | Final Drive LH | 73692 | 17692 | 6000
500043516 | CLB-MP-GRDR-GR021 -FDRSYS-DIFFL | Differential | 73692 | 2113 | 6000
500043515 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT02 | Driveshaft - Trans to Torque Conv | 73692 | 14685 | 6000
500043514 | CLB-MP-GRDR-GR021 -FDRSYS-DRSHT-SHT01 | Driveshaft - Trans to Diff | 73692 | 14685 | 6000
500043513 | CLB-MP-GRDR-GR021 -TRNSYS-TRPMP | Transmission Pump | 73692 | 3215 | 6000
500043512 | CLB-MP-GRDR-GR021 -TRNSYS-TROLC | Transmission Oil Cooler | 73692 | 19328 | 6000
500043511 | CLB-MP-GRDR-GR021 -TRNSYS-TRANS | Transmission | 73692 | 3215 | 6000
500043510 | CLB-MP-GRDR-GR021 -TRNSYS-TRQUE | Torque Converter | 73692 | 3215 | 6000
500043509 | CLB-MP-GRDR-GR021 -ELCTLV-START | Motor Starter | 73692 | 24995 | 6000
500043508 | CLB-MP-GRDR-GR021 -ELCTLV-CHARG-BATTY | Batteries | 73692 | 73692 | 6000
500043507 | CLB-MP-GRDR-GR021 -ELCTLV-CHARG-ALTER | Alternator 24V | 73692 | 14685 | 6000
500043506 | CLB-MP-GRDR-GR021 -ENGINE-FUSYS-FUINJ | Injectors Fuel | 73692 | 14685 | 6000
500043505 | CLB-MP-GRDR-GR021 -ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 73692 | 14685 | 6000
500043504 | CLB-MP-GRDR-GR021 -ENGINE-FUSYS-FULPP | Pump Fuel Priming | 73692 | 14685 | 6000
500043503 | CLB-MP-GRDR-GR021 -ENGINE-FUSYS-FULTK | Fuel Tank | 73692 | 73692 | 6000
500043502 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-EXHST | Exhaust/Muffler Group | 73692 | 14685 | 6000
500043501 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-AFTER | Aftercooler | 73692 | 14685 | 6000
500043500 | CLB-MP-GRDR-GR021 -ENGINE-INTEX-TURBO | Turbocharger | 73692 | 9977 | 6000
500043499 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-THERM | Thermostat / Regulator | 73692 | 14685 | 6000
500043498 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-COFAN | Fan Cooling System | 73692 | 73692 | 6000
500043497 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-RADTR | Radiator | 73692 | 14685 | 6000
500043496 | CLB-MP-GRDR-GR021 -ENGINE-COSYS-WTRPP | Pump Water Engine | 73692 | 14685 | 6000
500043495 | CLB-MP-GRDR-GR021 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 73692 | 14685 | 6000
500043494 | CLB-MP-GRDR-GR021 -ENGINE-LUBSY-OILPP | Pump Oil | 73692 | 14685 | 6000
500037594 | CLB-MP-GRDR-GR021 -ENGINE | Engine Assembly, Caterpillar C18 | 73692 | 14685 | 6000
500036273 | CLB-MP-GRDR-GR021 | GR021 Lubrication & Mechanical Services | 73692 | 73692 | 6000
500036272 | CLB-MP-GRDR-GR021 | Caterpillar 24M Motor Grader, GR021 | 73692 | 73692 | 6000
500083235 | CLB-MP-GRDR-GR019 -BRKSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 50615 | 6839 | 4000
500083217 | CLB-MP-GRDR-GR019 -BRKSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 50615 | 4021 | 4000
500083199 | CLB-MP-GRDR-GR019 -BRKSYS-CHAIN-CHNRF | Drive Chain R/H Front | 50615 | 6839 | 4000
500083181 | CLB-MP-GRDR-GR019 -BRKSYS-CHAIN-CHNLF | Drive Chain L/H Front | 50615 | 4021 | 4000
500063171 | CLB-MP-GRDR-GR019 -ELCTLV-HARNS | Electrical Harness | 50615 | 8028 | 4000
500061490 | CLB-MP-GRDR-GR019 -STRUCT-DRWBR | Drawbar | 50615 | 8028 | 4000
500061485 | CLB-MP-GRDR-GR019 -STRUCT-CABIN | Cabin | 50615 | 50615 | 4000
500061480 | CLB-MP-GRDR-GR019 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 50615 | 8028 | 4000
500061479 | CLB-MP-GRDR-GR019 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 50615 | 8028 | 4000
500061478 | CLB-MP-GRDR-GR019 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 50615 | 8028 | 4000
500061477 | CLB-MP-GRDR-GR019 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 50615 | 8028 | 4000
500029190 | CLB-MP-GRDR-GR019 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 50615 | 50615 | 4000
500029189 | CLB-MP-GRDR-GR019 -STRUCT-RIPPR | Ripper | 50615 | 8028 | 4000
500029188 | CLB-MP-GRDR-GR019 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 50615 | 39964 | 4000
500029187 | CLB-MP-GRDR-GR019 -STRUCT-BLADE-MOLDB | Moldboard Skin | 50615 | 50615 | 4000
500029186 | CLB-MP-GRDR-GR019 -STRUCT-BLADE | Blade Lift Trunnions | 50615 | 50615 | 4000
500029185 | CLB-MP-GRDR-GR019 -STRUCT-BLADE | Blade | 50615 | 36953 | 4000
500029184 | CLB-MP-GRDR-GR019 -STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 50896 | 8309 | 4000
500029183 | CLB-MP-GRDR-GR019 -STRUCT-CIRCL | Circle Assembly | 50615 | 34476 | 4000
500029182 | CLB-MP-GRDR-GR019 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 50615 | 8028 | 4000
500029181 | CLB-MP-GRDR-GR019 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 50615 | 8028 | 4000
500029180 | CLB-MP-GRDR-GR019 -STRUCT-AXLES | GR019 Front Axle Assembly | 50615 | 8028 | 4000
500029179 | CLB-MP-GRDR-GR019 -STRUCT-CHASS-ARTIC | Articulation | 50615 | 8028 | 4000
500029178 | CLB-MP-GRDR-GR019 -STRUCT-CABIN-SBELT | Seat Belt | 50615 | 50615 | 4000
500029177 | CLB-MP-GRDR-GR019 -STRUCT-CABIN-SEATS | Operators Seat | 50615 | 4579 | 4000
500029176 | CLB-MP-GRDR-GR019 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 50615 | 50615 | 4000
500029175 | CLB-MP-GRDR-GR019 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 50615 | 27114 | 4000
500029174 | CLB-MP-GRDR-GR019 -STRUCT-CABIN-AIRCN | Air Conditioning System | 50615 | 15239 | 4000
500029173 | CLB-MP-GRDR-GR019 -GRSYST-ALBPP | Auto Lube Pump | 50615 | 8028 | 4000
500029172 | CLB-MP-GRDR-GR019 -GRSYST-GRINJ | Auto Lube Injectors | 50615 | 50615 | 4000
500029171 | CLB-MP-GRDR-GR019 -GRSYST | Grease Lubrication System | 50615 | 50615 | 4000
500029170 | CLB-MP-GRDR-GR019 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 50615 | 50615 | 4000
500029169 | CLB-MP-GRDR-GR019 -HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator R/H | 50615 | 50615 | 4000
500029168 | CLB-MP-GRDR-GR019 -HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator L/H | 50615 | 50615 | 4000
500029167 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 50615 | 34476 | 4000
500029166 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 50615 | 13071 | 4000
500029165 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 50615 | 8028 | 4000
500029164 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 50615 | 32845 | 4000
500029163 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation R/H | 50615 | 7832 | 4000
500029162 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-ARCYL | Cylinder Articulation L/H | 50615 | 22467 | 4000
500029161 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 50615 | 2659 | 4000
500029160 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 50615 | 18470 | 4000
500029159 | CLB-MP-GRDR-GR019 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 50615 | 19936 | 4000
500029158 | CLB-MP-GRDR-GR019 -HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 50615 | 8028 | 4000
500029157 | CLB-MP-GRDR-GR019 -HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 50615 | 39027 | 4000
500029156 | CLB-MP-GRDR-GR019 -HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 50615 | 8028 | 4000
500029155 | CLB-MP-GRDR-GR019 -HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 50615 | 8028 | 4000
500029154 | CLB-MP-GRDR-GR019 -HYDSYS-HYDPP-HYISP | Pump Implement and Steering | 50615 | 11277 | 4000
500029153 | CLB-MP-GRDR-GR019 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 50615 | 8028 | 4000
500029152 | CLB-MP-GRDR-GR019 -STRSYS-STMTR | Steering Metering Pump | 50615 | 50615 | 4000
500029151 | CLB-MP-GRDR-GR019 -STRSYS-STLTR | Steering Linkages and Tie Rods | 50615 | 50615 | 4000
500029150 | CLB-MP-GRDR-GR019 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 50615 | 11768 | 4000
500029149 | CLB-MP-GRDR-GR019 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 50615 | 11768 | 4000
500029148 | CLB-MP-GRDR-GR019 -BRKSYS-BRPRK | Park Brake Assembly | 50615 | 50615 | 4000
500029147 | CLB-MP-GRDR-GR019 -BRKSYS-BRPMP | Pump Brake / Hydraulic Fan | 50615 | 8028 | 4000
500029146 | CLB-MP-GRDR-GR019 -BRKSYS-BKOCO | Oil Cooler Brake / Hydraulic Fan | 50615 | 50615 | 4000
500029145 | CLB-MP-GRDR-GR019 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 50615 | 50615 | 4000
500029144 | CLB-MP-GRDR-GR019 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 50615 | 50615 | 4000
500029143 | CLB-MP-GRDR-GR019 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 50615 | 8028 | 4000
500029142 | CLB-MP-GRDR-GR019 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 50615 | 8028 | 4000
500029141 | CLB-MP-GRDR-GR019 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 50615 | 8028 | 4000
500029140 | CLB-MP-GRDR-GR019 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 50615 | 8028 | 4000
500029139 | CLB-MP-GRDR-GR019 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 50615 | 50615 | 4000
500029138 | CLB-MP-GRDR-GR019 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 50615 | 50615 | 4000
500029137 | CLB-MP-GRDR-GR019 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 50615 | 50615 | 4000
500029136 | CLB-MP-GRDR-GR019 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 50615 | 50615 | 4000
500029135 | CLB-MP-GRDR-GR019 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 50615 | 50615 | 4000
500029134 | CLB-MP-GRDR-GR019 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 50615 | 50615 | 4000
500029133 | CLB-MP-GRDR-GR019 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 50615 | 23562 | 4000
500029132 | CLB-MP-GRDR-GR019 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 50615 | 23562 | 4000
500029131 | CLB-MP-GRDR-GR019 -FDRSYS-TDRAX-TDARH | Tandem Drive Chains R/H | 50615 | 50615 | 4000
500029130 | CLB-MP-GRDR-GR019 -FDRSYS-TDRAX-TDARH | Tandem Drive Assembly R/H | 50615 | 50615 | 4000
500029129 | CLB-MP-GRDR-GR019 -FDRSYS-TDRAX-TDALH | Tandem Drive Chains L/H | 50615 | 50615 | 4000
500029128 | CLB-MP-GRDR-GR019 -FDRSYS-TDRAX-TDALH | Tandem Drive Assembly L/H | 50615 | 50615 | 4000
500029127 | CLB-MP-GRDR-GR019 -FDRSYS-DIFFL | Differential and Bevel Gear | 50615 | 8028 | 4000
500029126 | CLB-MP-GRDR-GR019 -TRNSYS-TRPMP | Pump Transmission | 50615 | 39027 | 4000
500029125 | CLB-MP-GRDR-GR019 -TRNSYS-TROLC | Transmission Oil Cooler | 50615 | 39027 | 4000
500029124 | CLB-MP-GRDR-GR019 -TRNSYS-TRANS | Transmission | 50615 | 1622 | 4000
500029123 | CLB-MP-GRDR-GR019 -TRNSYS | Drive Shaft | 50615 | 8028 | 4000
500029122 | CLB-MP-GRDR-GR019 -ELCTLV-START-STRMR | Starter Motor | 50615 | 8028 | 4000
500029121 | CLB-MP-GRDR-GR019 -ELCTLV-CHARG-ALTER | Alternator 24V | 50615 | 8028 | 4000
500029120 | CLB-MP-GRDR-GR019 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 50615 | 8028 | 4000
500029119 | CLB-MP-GRDR-GR019 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 50615 | 8028 | 4000
500029118 | CLB-MP-GRDR-GR019 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 50615 | 8028 | 4000
500029117 | CLB-MP-GRDR-GR019 -ENGINE-INTEX-EXHST | Exhaust Muffler | 50615 | 15239 | 4000
500029116 | CLB-MP-GRDR-GR019 -ENGINE-INTEX-AFTER | Aftercooler | 50615 | 50615 | 4000
500029115 | CLB-MP-GRDR-GR019 -ENGINE-INTEX-TURBO | Turbocharger | 50615 | 8028 | 4000
500029114 | CLB-MP-GRDR-GR019 -ENGINE-COSYS-THERM | Thermostats/Regulators | 50615 | 8028 | 4000
500029113 | CLB-MP-GRDR-GR019 -ENGINE-COSYS-COFAN | Fan Cooling System | 50615 | 50615 | 4000
500029112 | CLB-MP-GRDR-GR019 -ENGINE-COSYS-RADTR | Radiator Coolant | 50615 | 8028 | 4600
500029111 | CLB-MP-GRDR-GR019 -ENGINE-COSYS-RADTR | Radiator Engine | 50615 | 8028 | 4000
500029110 | CLB-MP-GRDR-GR019 -ENGINE-COSYS-WTRPP | Water Pump Engine | 50615 | 8028 | 4000
500029109 | CLB-MP-GRDR-GR019 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 50615 | 50615 | 4000
500029108 | CLB-MP-GRDR-GR019 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 50615 | 34476 | 4000
500029107 | CLB-MP-GRDR-GR019 -ENGINE-LUBSY | Engine Lubrication System | 50615 | 50615 | 4000
500029105 | CLB-MP-GRDR-GR019 -ENGINE | Engine Assembly Caterpillar C13 ASERT | 50615 | 593 | 4000
500029104 | CLB-MP-GRDR-GR019 | GR019 Lube & Mechanical Services | 50615 | 50615 | 4000
500029103 | CLB-MP-GRDR-GR019 | Caterpillar 16M Motor Grader GR019 | 50615 | 50615 | 4000
500148495 | CLB-MP-GRDR-GR018 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 73365 | 73365 | 6000
500148494 | CLB-MP-GRDR-GR018 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 73365 | 73365 | 6000
500148493 | CLB-MP-GRDR-GR018 -BRKSYS-BRACC | Brake Accumulator RH | 73365 | 73365 | 6000
500148492 | CLB-MP-GRDR-GR018 -BRKSYS-BRACC | Brake Accumulator LH | 73365 | 73365 | 6000
500125645 | CLB-MP-GRDR-GR018 -ELCTLV-START-STRMR | Starter Motor | 73365 | 77 | 6000
500104452 | CLB-MP-GRDR-GR018 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 73365 | 23410 | 6000
500104451 | CLB-MP-GRDR-GR018 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 73365 | 23410 | 6000
500083242 | CLB-MP-GRDR-GR018 -BRKSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 73365 | 77 | 6000
500083224 | CLB-MP-GRDR-GR018 -BRKSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 73365 | 77 | 6000
500083206 | CLB-MP-GRDR-GR018 -BRKSYS-CHAIN-CHNRF | Drive Chain R/H Front | 73365 | 77 | 6000
500083188 | CLB-MP-GRDR-GR018 -BRKSYS-CHAIN-CHNLF | Drive Chain L/H Front | 73365 | 77 | 6000
500063197 | CLB-MP-GRDR-GR018 -ELCTLV-HARNS | Electrical Harness | 73365 | 77 | 6000
500063183 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 73365 | 77 | 6000
500063182 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 73365 | 77 | 6000
500063181 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 73365 | 77 | 6000
500063180 | CLB-MP-GRDR-GR018 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 73365 | 77 | 6000
500043387 | CLB-MP-GRDR-GR018 -MANGMT-UMMMC | Mine Monitoring and Control | 73365 | 73365 | 6000
500043386 | CLB-MP-GRDR-GR018 -MANGMT-UMTRM | Transmission Management System | 73365 | 73365 | 6000
500043385 | CLB-MP-GRDR-GR018 -MANGMT-UMENG | Engine Management System | 73365 | 73365 | 6000
500043384 | CLB-MP-GRDR-GR018 -FRSUPP-FSMAN-EXTIN | Fire Extinguisher Hand Held | 73365 | 73365 | 6000
500043383 | CLB-MP-GRDR-GR018 -FRSUPP-FSAUT-FFOAM | Foam Fire Suppresion | 73365 | 73365 | 6000
500043382 | CLB-MP-GRDR-GR018 -STRUCT-RIPPR-RIGET | Ripper GET | 73365 | 73365 | 6000
500043381 | CLB-MP-GRDR-GR018 -STRUCT-RIPPR | Ripper Assembly | 73365 | 23410 | 6000
500043380 | CLB-MP-GRDR-GR018 -STRUCT-BLADE-BLGET | Blade GET | 73365 | 73365 | 6000
500043379 | CLB-MP-GRDR-GR018 -STRUCT-BLADE-MOLDB | Moldboard Skin | 73365 | 73365 | 6000
500043378 | CLB-MP-GRDR-GR018 -STRUCT-BLADE | Blade | 73365 | 54324 | 6000
500043377 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXR | Circle Drive Gearbox R/H | 73365 | 77 | 6000
500043376 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-CDBXF | Circle Drive Gearbox L/H | 73365 | 3133 | 6000
500043375 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBR | Bracket Blade Mounting R/H | 73365 | 77 | 6000
500043374 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL-BLMBL | Bracket Blade Mounting L/H | 73365 | 77 | 6000
500043373 | CLB-MP-GRDR-GR018 -STRUCT-CIRCL | Circle Assembly | 73365 | 73365 | 6000
500043372 | CLB-MP-GRDR-GR018 -STRUCT-DRWBR | Trunnions Blade Lift | 73365 | 77 | 6000
500043371 | CLB-MP-GRDR-GR018 -STRUCT-DRWBR | Drawbar Group | 73365 | 77 | 6000
500043370 | CLB-MP-GRDR-GR018 -STRUCT-AXLES-HUBRH | Wheel Bearings RH Front | 73365 | 77 | 6000
500043369 | CLB-MP-GRDR-GR018 -STRUCT-AXLES-HUBLH | Wheel Bearings LH Front | 73365 | 77 | 6000
500043368 | CLB-MP-GRDR-GR018 -STRUCT-AXLES | Axle Assembly Front | 73365 | 77 | 6000
500043367 | CLB-MP-GRDR-GR018 -STRUCT-CHASS-ARTIC | Articulation Hitch | 73365 | 38190 | 6000
500043366 | CLB-MP-GRDR-GR018 -STRUCT-CHASS-REFRM | Rear Frame | 73365 | 73365 | 6000
500043365 | CLB-MP-GRDR-GR018 -STRUCT-CHASS-FRFRM | Front Frame | 73365 | 73365 | 6000
500043364 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-SBELT | Belt Seat | 73365 | 73365 | 6000
500043363 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-SEATS | Seat Operator | 73365 | 1135 | 6000
500043362 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-CABES | Pressurisation System Cabin | 73365 | 73365 | 6000
500043361 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-CABCO | Condensor Air Conditioning | 73365 | 73365 | 6000
500043360 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-CABPR | Compressor Air Cond System | 73365 | 73365 | 6000
500043359 | CLB-MP-GRDR-GR018 -STRUCT-CABIN-AIRCN | Air Conditioning System | 73365 | 77 | 6000
500043358 | CLB-MP-GRDR-GR018 -STRUCT-CABIN | Operators Cabin | 73365 | 77 | 6000
500043357 | CLB-MP-GRDR-GR018 -GRSYST-ALCON | Controller Auto Lube | 73365 | 73365 | 6000
500043356 | CLB-MP-GRDR-GR018 -GRSYST-ALBPP | Pump Auto Lube | 73365 | 77 | 6000
500043355 | CLB-MP-GRDR-GR018 -GRSYST-GRTNK | Resevoir Auto Lube | 73365 | 73365 | 6000
500043354 | CLB-MP-GRDR-GR018 -GRSYST-GRINJ | Injectors Auto Lube | 73365 | 73365 | 6000
500043353 | CLB-MP-GRDR-GR018 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 73365 | 23410 | 6000
500043352 | CLB-MP-GRDR-GR018 -HYDSYS-HDTNK | Tank Hydraulic | 73365 | 73365 | 6000
500043351 | CLB-MP-GRDR-GR018 -HYDSYS-HDACC | Accumulator Blade Cushion | 73365 | 73365 | 6000
500043350 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-WLCYR | Cylinder Wheel Lean R/H | 73365 | 4223 | 6000
500043349 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean L/H | 73365 | 19966 | 6000
500043348 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 73365 | 24837 | 6000
500043347 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 73365 | 24837 | 6000
500043346 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-SSCYL | Cylinder Blade Side Shift | 73365 | 7284 | 6000
500043345 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 73365 | 13916 | 6000
500043344 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 73365 | 25231 | 6000
500043343 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-ARCYL | Clinder Articulation LH | 73365 | 8108 | 6000
500043342 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tip RH | 73365 | 27765 | 6000
500043341 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tip LH | 73365 | 27027 | 6000
500043340 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 73365 | 73365 | 6000
500043339 | CLB-MP-GRDR-GR018 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 73365 | 17286 | 6000
500043338 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT03 | Fan Motor | 73365 | 77 | 6000
500043337 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT02 | Motor Circle Drive Rear | 73365 | 31110 | 6000
500043336 | CLB-MP-GRDR-GR018 -HYDSYS-HDMOT-MOT01 | Motor Circle Drive Front | 73365 | 31110 | 6000
500043335 | CLB-MP-GRDR-GR018 -HYDSYS-HDCVL-BK5RH | Valve Hyd Control R/H | 73365 | 73365 | 6000
500043334 | CLB-MP-GRDR-GR018 -HYDSYS-HDCVL-BK5LH | Valve Hyd Control | 73365 | 73365 | 6000
500043333 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-DIFFL | Pump Diff lock | 73365 | 77 | 6000
500043332 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-FANPP | Pump Fan Motor & Brakes | 73365 | 77 | 6000
500043331 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-HYSTP | Pump Steering | 73365 | 415 | 6000
500043330 | CLB-MP-GRDR-GR018 -HYDSYS-HYDPP-HYIMP | Pump Implement | 73365 | 415 | 6000
500043329 | CLB-MP-GRDR-GR018 -HYDSYS | Hydraulic System | 73365 | 23410 | 6000
500043328 | CLB-MP-GRDR-GR018 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 73365 | 77 | 6000
500043327 | CLB-MP-GRDR-GR018 -STRSYS-STCON | Valve Steering Control | 73365 | 38614 | 6000
500043326 | CLB-MP-GRDR-GR018 -STRSYS-STLTR | Steering Linkage | 73365 | 23410 | 6000
500043325 | CLB-MP-GRDR-GR018 -STRSYS-STRCY-STCYR | Steering Cylinder RH | 73365 | 77 | 6000
500043324 | CLB-MP-GRDR-GR018 -STRSYS-STRCY-STCYL | Steering Cylinder LH | 73365 | 77 | 6000
500043323 | CLB-MP-GRDR-GR018 -BRKSYS-BRACC-ACC02 | Accumulator Brake Left | 73365 | 73365 | 6000
500043322 | CLB-MP-GRDR-GR018 -BRKSYS-BRACC-ACC01 | Accumulator Brake Right | 73365 | 73365 | 6000
500043321 | CLB-MP-GRDR-GR018 -BRKSYS-BRCON | Valve Brake Control | 73365 | 73365 | 6000
500043320 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACR | Slack Adjuster Brake Right | 73365 | 77 | 6000
500043319 | CLB-MP-GRDR-GR018 -BRKSYS-SLACK-SLACL | Slack Adjuster Brake Left | 73365 | 77 | 6000
500043318 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRR | Brake Assembly RHR | 73365 | 77 | 6000
500043317 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLR | Brake Assembly LHR | 73365 | 77 | 6000
500043316 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBRF | Brake Assembly RHF | 73365 | 77 | 6000
500043315 | CLB-MP-GRDR-GR018 -BRKSYS-SRVBK-SVBLF | Brake Assembly LHF | 73365 | 77 | 6000
500043314 | CLB-MP-GRDR-GR018 -FDRSYS-WHTYR-POS06 | POS 6 Tyre & Rim | 73365 | 73365 | 6000
500043313 | CLB-MP-GRDR-GR018 -FDRSYS-WHTYR-POS05 | POS 5 Tyre & Rim | 73365 | 73365 | 6000
500043312 | CLB-MP-GRDR-GR018 -FDRSYS-WHTYR-POS04 | POS 4 Tyre & Rim | 73365 | 73365 | 6000
500043311 | CLB-MP-GRDR-GR018 -FDRSYS-WHTYR-POS03 | POS 3 Tyre & Rim | 73365 | 73365 | 6000
500043310 | CLB-MP-GRDR-GR018 -FDRSYS-WHTYR-POS02 | POS 2 Tyre & Rim | 73365 | 73365 | 6000
500043309 | CLB-MP-GRDR-GR018 -FDRSYS-WHTYR-POS01 | POS 1 Tyre & Rim | 73365 | 73365 | 6000
500043308 | CLB-MP-GRDR-GR018 -FDRSYS-TDRAX-TDARH | Tandem RH | 73365 | 73365 | 6000
500043307 | CLB-MP-GRDR-GR018 -FDRSYS-TDRAX-TDALH | Tandem LH | 73365 | 23410 | 6000
500043306 | CLB-MP-GRDR-GR018 -FDRSYS-FDRVE-FDRRH | Final Drive RH | 73365 | 77 | 6000
500043305 | CLB-MP-GRDR-GR018 -FDRSYS-FDRVE-FDRLH | Final Drive LH | 73365 | 77 | 6000
500043304 | CLB-MP-GRDR-GR018 -FDRSYS-DIFFL | Differential | 73365 | 77 | 6000
500043303 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT02 | Driveshaft - Trans to Torque Conv | 73365 | 2853 | 6000
500043302 | CLB-MP-GRDR-GR018 -FDRSYS-DRSHT-SHT01 | Driveshaft - Trans to Diff | 73365 | 3877 | 6000
500043301 | CLB-MP-GRDR-GR018 -TRNSYS-TRPMP | Transmission Pump | 73365 | 7458 | 6000
500043300 | CLB-MP-GRDR-GR018 -TRNSYS-TROLC | Transmission Oil Cooler | 73365 | 77 | 6000
500043299 | CLB-MP-GRDR-GR018 -TRNSYS-TRANS | Transmission | 73365 | 7458 | 6000
500043298 | CLB-MP-GRDR-GR018 -TRNSYS-TRQUE | Torque Converter | 73365 | 77 | 6000
500043297 | CLB-MP-GRDR-GR018 -ELCTLV-START | Motor Starter | 73365 | 7881 | 6000
500043296 | CLB-MP-GRDR-GR018 -ELCTLV-CHARG-BATTY | Batteries | 73365 | 13504 | 6000
500043295 | CLB-MP-GRDR-GR018 -ELCTLV-CHARG-ALTER | Alternator 24V | 73365 | 77 | 6000
500043294 | CLB-MP-GRDR-GR018 -ENGINE-FUSYS-FUINJ | Injectors Fuel | 73365 | 77 | 6000
500043293 | CLB-MP-GRDR-GR018 -ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 73365 | 77 | 6000
500043292 | CLB-MP-GRDR-GR018 -ENGINE-FUSYS-FULPP | Pump Fuel Priming | 73365 | 77 | 6000
500043291 | CLB-MP-GRDR-GR018 -ENGINE-FUSYS-FULTK | Fuel Tank | 73365 | 73365 | 6000
500043290 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-EXHST | Exhaust/Muffler Group | 73365 | 13504 | 6000
500043289 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-AFTER | Aftercooler | 73365 | 77 | 6000
500043288 | CLB-MP-GRDR-GR018 -ENGINE-INTEX-TURBO | Turbocharger | 73365 | 77 | 6000
500043287 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-THERM | Thermostat / Regulator | 73365 | 77 | 6000
500043286 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-COFAN | Fan Cooling System | 73365 | 39395 | 6000
500043285 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-RADTR | Radiator | 73365 | 77 | 6000
500043284 | CLB-MP-GRDR-GR018 -ENGINE-COSYS-WTRPP | Pump Water Engine | 73365 | 77 | 6000
500043283 | CLB-MP-GRDR-GR018 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 73365 | 77 | 6000
500043282 | CLB-MP-GRDR-GR018 -ENGINE-LUBSY-OILPP | Pump Oil | 73365 | 77 | 6000
500037590 | CLB-MP-GRDR-GR018 -ENGINE | Engine Assembly, Caterpillar C18 | 73365 | 77 | 6000
500036269 | CLB-MP-GRDR-GR018 | GR018 Lubrication & Mechanical Services | 73365 | 73365 | 6000
500036268 | CLB-MP-GRDR-GR018 | Caterpillar 24M Motor Grader, GR018 | 73365 | 73365 | 6000
500083234 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 54668 | 11075 | 4000
500083216 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 54668 | 11075 | 4000
500083198 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNRF | Drive Chain R/H Front | 54668 | 11075 | 4000
500083170 | CLB-MP-GRDR-GR017 -BRKSYS-CHAIN-CHNLF | Drive Chain L/H Front | 54668 | 11075 | 4000
500063170 | CLB-MP-GRDR-GR017 -ELCTLV-HARNS | Electrical Harness | 54668 | 11075 | 4000
500061489 | CLB-MP-GRDR-GR017 -STRUCT-DRWBR | Drawbar | 54668 | 11075 | 4000
500061484 | CLB-MP-GRDR-GR017 -STRUCT-CABIN | Cabin | 54668 | 25062 | 4000
500061476 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 54668 | 11075 | 4000
500061475 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 54668 | 11075 | 4000
500061474 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 54668 | 11075 | 4000
500061473 | CLB-MP-GRDR-GR017 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 54668 | 11075 | 4000
500029102 | CLB-MP-GRDR-GR017 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 54668 | 54668 | 4000
500029101 | CLB-MP-GRDR-GR017 -STRUCT-RIPPR | Ripper | 54668 | 11075 | 4000
500029100 | CLB-MP-GRDR-GR017 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 54668 | 44804 | 4000
500029099 | CLB-MP-GRDR-GR017 -STRUCT-BLADE-MOLDB | Moldboard Skin | 54668 | 54668 | 4000
500029098 | CLB-MP-GRDR-GR017 -STRUCT-BLADE | Blade Lift Trunnions | 54668 | 54668 | 4000
500029097 | CLB-MP-GRDR-GR017 -STRUCT-BLADE | Blade | 54668 | 54668 | 4000
500029096 | CLB-MP-GRDR-GR017 -STRUCT-CIRCL-CDRBX | Gearbox Circle Drive | 54668 | 3800 | 4000
500029095 | CLB-MP-GRDR-GR017 -STRUCT-CIRCL | Circle Assembly | 54668 | 38189 | 4000
500029094 | CLB-MP-GRDR-GR017 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 54668 | 1838 | 4000
500029093 | CLB-MP-GRDR-GR017 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 54668 | 1838 | 4000
500029092 | CLB-MP-GRDR-GR017 -STRUCT-AXLES | GR017 Front Axle Assembly | 54668 | 1838 | 4000
500029091 | CLB-MP-GRDR-GR017 -STRUCT-CHASS-ARTIC | Articulation | 54668 | 11075 | 4000
500029090 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-SBELT | Seat Belt | 54668 | 54668 | 4000
500029089 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-SEATS | Operators Seat | 54668 | 2814 | 4000
500029088 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 54668 | 54668 | 4000
500029087 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN | Air Conditioning Compressor | 54668 | 11075 | 4000
500029086 | CLB-MP-GRDR-GR017 -STRUCT-CABIN-AIRCN | Air Conditioning System | 54668 | 11075 | 4000
500029085 | CLB-MP-GRDR-GR017 -GRSYST-ALBPP | Auto Lube Pump | 54668 | 1203 | 4000
500029084 | CLB-MP-GRDR-GR017 -GRSYST-GRINJ | Auto Lube Injectors | 54668 | 54668 | 4000
500029083 | CLB-MP-GRDR-GR017 -GRSYST | Grease Lubrication System | 54668 | 54668 | 4000
500029082 | CLB-MP-GRDR-GR017 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 54668 | 54668 | 4000
500029081 | CLB-MP-GRDR-GR017 -HYDSYS-HDACC-BLCUR | Blade Cushion Accumulator R/H | 54668 | 54668 | 4000
500029080 | CLB-MP-GRDR-GR017 -HYDSYS-HDACC-BLCUL | Blade Cushion Accumulator L/H | 54668 | 54668 | 4000
500029079 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean | 54668 | 38189 | 4000
500029078 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-RICYL | Cylinder Ripper Lift | 54668 | 54668 | 4000
500029077 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-SSCYL | Cylinder Side Shift | 54668 | 17156 | 4000
500029076 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 54668 | 54668 | 4000
500029075 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation R/H | 54668 | 1203 | 4000
500029074 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-ARCYL | Cylinder Articulation L/H | 54668 | 7639 | 4000
500029073 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-BTICY | Cylinder Blade Tilt | 54668 | 12072 | 4000
500029072 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 54668 | 9896 | 4000
500029071 | CLB-MP-GRDR-GR017 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 54668 | 54668 | 4000
500029070 | CLB-MP-GRDR-GR017 -HYDSYS-HDMOT-MOFAN | Motor Hydraulic Fan | 54668 | 8517 | 4000
500029069 | CLB-MP-GRDR-GR017 -HYDSYS-HDMOT-MOCDG | Motor Circle Drive Gearbox | 54668 | 30239 | 4000
500029068 | CLB-MP-GRDR-GR017 -HYDSYS-HDCVL-REAR1 | Implement Control Valve Rear | 54668 | 11075 | 4000
500029067 | CLB-MP-GRDR-GR017 -HYDSYS-HDCVL-FRONT | Implement Control Valve Front | 54668 | 11075 | 4000
500029066 | CLB-MP-GRDR-GR017 -HYDSYS-HYDPP-HYISP | Pump Implement and Steering | 54668 | 11075 | 4000
500029065 | CLB-MP-GRDR-GR017 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 54668 | 1845 | 4000
500029064 | CLB-MP-GRDR-GR017 -STRSYS-STMTR | Steering Metering Pump | 54668 | 54668 | 4000
500029063 | CLB-MP-GRDR-GR017 -STRSYS-STLTR | Steering Linkages and Tie Rods | 54668 | 38189 | 4000
500029062 | CLB-MP-GRDR-GR017 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 54668 | 1838 | 4000
500029061 | CLB-MP-GRDR-GR017 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 54668 | 1838 | 4000
500029060 | CLB-MP-GRDR-GR017 -BRKSYS-BRPRK | Park Brake Assembly | 54668 | 43583 | 4000
500029059 | CLB-MP-GRDR-GR017 -BRKSYS-BRPMP | Pump Brake / Hydraulic Fan | 54668 | 5883 | 4000
500029058 | CLB-MP-GRDR-GR017 -BRKSYS-BKOCO | Oil Cooler Brake / Hydraulic Fan | 54668 | 54668 | 4000
500029057 | CLB-MP-GRDR-GR017 -BRKSYS-BACCM-BACCR | Brake Accumulator Rear | 54668 | 54668 | 4000
500029056 | CLB-MP-GRDR-GR017 -BRKSYS-BACCM-BACCF | Brake Accumulator Front | 54668 | 54668 | 4000
500029055 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 54668 | 4479 | 4000
500029054 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 54668 | 2410 | 4000
500029053 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 54668 | 4479 | 4000
500029052 | CLB-MP-GRDR-GR017 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 54668 | 2410 | 4000
500029051 | CLB-MP-GRDR-GR017 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 54668 | 54668 | 4000
500029050 | CLB-MP-GRDR-GR017 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 54668 | 54668 | 4000
500029049 | CLB-MP-GRDR-GR017 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 54668 | 54668 | 4000
500029048 | CLB-MP-GRDR-GR017 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 54668 | 54668 | 4000
500029047 | CLB-MP-GRDR-GR017 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 54668 | 54668 | 4000
500029046 | CLB-MP-GRDR-GR017 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 54668 | 54668 | 4000
500029045 | CLB-MP-GRDR-GR017 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 54668 | 22780 | 4000
500029044 | CLB-MP-GRDR-GR017 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 54668 | 22780 | 4000
500029043 | CLB-MP-GRDR-GR017 -FDRSYS-TDRAX-TDARH | Tandem Drive Chains R/H | 54668 | 54668 | 4000
500029042 | CLB-MP-GRDR-GR017 -FDRSYS-TDRAX-TDARH | Tandem Drive Assembly R/H | 54668 | 54668 | 4000
500029041 | CLB-MP-GRDR-GR017 -FDRSYS-TDRAX-TDALH | Tandem Drive Chains L/H | 54668 | 54668 | 4000
500029040 | CLB-MP-GRDR-GR017 -FDRSYS-TDRAX-TDALH | Tandem Drive Assembly L/H | 54668 | 54668 | 4000
500029039 | CLB-MP-GRDR-GR017 -FDRSYS-DIFFL | Differential and Bevel Gear | 54668 | 11075 | 4000
500029038 | CLB-MP-GRDR-GR017 -TRNSYS-TRPMP | Pump Transmission | 54668 | 44435 | 4000
500029037 | CLB-MP-GRDR-GR017 -TRNSYS-TROLC | Transmission Oil Cooler | 54668 | 38189 | 4000
500029036 | CLB-MP-GRDR-GR017 -TRNSYS-TRANS | Transmission | 54668 | 4479 | 4000
500029035 | CLB-MP-GRDR-GR017 -TRNSYS | Drive Shaft | 54668 | 11075 | 4000
500029034 | CLB-MP-GRDR-GR017 -ELCTLV-START-STRMR | Starter Motor | 54668 | 671 | 4000
500029033 | CLB-MP-GRDR-GR017 -ELCTLV-CHARG-ALTER | Alternator 24V | 54668 | 671 | 4000
500029032 | CLB-MP-GRDR-GR017 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 54668 | 671 | 4000
500029031 | CLB-MP-GRDR-GR017 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 54668 | 671 | 4000
500029030 | CLB-MP-GRDR-GR017 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 54668 | 671 | 4000
500029029 | CLB-MP-GRDR-GR017 -ENGINE-INTEX-EXHST | Exhaust Muffler | 54668 | 25062 | 4000
500029028 | CLB-MP-GRDR-GR017 -ENGINE-INTEX-AFTER | Aftercooler | 54668 | 22400 | 4000
500029027 | CLB-MP-GRDR-GR017 -ENGINE-INTEX-TURBO | Turbocharger | 54668 | 671 | 4000
500029026 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-THERM | Thermostats/Regulators | 54668 | 671 | 4000
500029025 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-COFAN | Fan Cooling System | 54668 | 54668 | 4000
500029024 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-RADTR | Radiator Coolant | 54668 | 25062 | 4600
500029023 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-RADTR | Radiator Engine | 54668 | 11075 | 4000
500029022 | CLB-MP-GRDR-GR017 -ENGINE-COSYS-WTRPP | Water Pump Engine | 54668 | 671 | 4000
500029021 | CLB-MP-GRDR-GR017 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 54668 | 38189 | 4000
500029020 | CLB-MP-GRDR-GR017 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 54668 | 38189 | 4000
500029019 | CLB-MP-GRDR-GR017 -ENGINE-LUBSY | Engine Lubrication System | 54668 | 54668 | 4000
500029017 | CLB-MP-GRDR-GR017 -ENGINE | Engine Assembly Caterpillar C13 ACERT | 54668 | 671 | 4000
500029016 | CLB-MP-GRDR-GR017 | GR017 Lube & Mechanical Services | 54668 | 54668 | 4000
500029015 | CLB-MP-GRDR-GR017 | Caterpillar 16M Motor Grader GR017 | 54668 | 54668 | 4000
500148491 | CLB-MP-GRDR-GR013 -HYDSYS-HDACC | Blade Cushion Accumulator RH | 71626 | 71626 | 6000
500148490 | CLB-MP-GRDR-GR013 -HYDSYS-HDACC | Blade Cushion Accumulator LH | 71626 | 71626 | 6000
500148489 | CLB-MP-GRDR-GR013 -BRKSYS-BRACC | Brake Accumulator RH | 71626 | 71626 | 6000
500148488 | CLB-MP-GRDR-GR013 -BRKSYS-BRACC | Brake Accumulator LH | 71626 | 71626 | 6000
500104450 | CLB-MP-GRDR-GR013 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 71626 | 20582 | 6000
500104449 | CLB-MP-GRDR-GR013 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 71626 | 20582 | 6000
500083241 | CLB-MP-GRDR-GR013 -BRKSYS-CHAIN-CHNRR | Drive Chain R/H Rear | 71626 | 12192 | 6000
500083223 | CLB-MP-GRDR-GR013 -BRKSYS-CHAIN-CHNLR | Drive Chain L/H Rear | 71626 | 12192 | 6000
500083205 | CLB-MP-GRDR-GR013 -BRKSYS-CHAIN-CHNRF | Drive Chain R/H Front | 71626 | 12192 | 6000
500083187 | CLB-MP-GRDR-GR013 -BRKSYS-CHAIN-CHNLF | Drive Chain L/H Front | 71626 | 12192 | 6000
500063196 | CLB-MP-GRDR-GR013 -ELCTLV-HARNS | Electrical Harness | 71626 | 12192 | 6000
500063179 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-STRNG | Steering System Hoses | 71626 | 12192 | 6000
500063178 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-PWTRN | Powertrain System Hoses | 71626 | 12192 | 6000
500063177 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-HYDSH | Hydraulic System Hoses | 71626 | 12192 | 6000
500063176 | CLB-MP-GRDR-GR013 -HYDSYS-HDHLF-BRKS | Brake System Hoses | 71626 | 12192 | 6000
500058291 | CLB-MP-GRDR-GR013 -ELCTLV-START-STRMR | Starter Motor | 71626 | 4169 | 6000
500043281 | CLB-MP-GRDR-GR013 -MANGMT-UMMMC | Mine Monitoring and Control | 71626 | 71626 | 6000
500043280 | CLB-MP-GRDR-GR013 -MANGMT-UMTRM | Transmission Management System | 71626 | 71626 | 6000
500043279 | CLB-MP-GRDR-GR013 -MANGMT-UMENG | Engine Management System | 71626 | 71626 | 6000
500043278 | CLB-MP-GRDR-GR013 -FRSUPP-FSMAN-EXTIN | Fire Extinguisher Hand Held | 71626 | 71626 | 6000
500043277 | CLB-MP-GRDR-GR013 -FRSUPP-FSAUT-FFOAM | Foam Fire Suppresion | 71626 | 71626 | 6000
500043276 | CLB-MP-GRDR-GR013 -STRUCT-RIPPR-RIGET | Ripper GET | 71626 | 71626 | 6000
500043275 | CLB-MP-GRDR-GR013 -STRUCT-RIPPR | Ripper Assembly | 71626 | 71626 | 6000
500043274 | CLB-MP-GRDR-GR013 -STRUCT-BLADE-BLGET | Blade GET | 71626 | 71626 | 6000
500043273 | CLB-MP-GRDR-GR013 -STRUCT-BLADE-MOLDB | Moldboard Skin | 71626 | 71626 | 6000
500043272 | CLB-MP-GRDR-GR013 -STRUCT-BLADE | Blade | 71626 | 1383 | 6000
500043271 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-CDBXR | Circle Drive Gearbox R/H | 71626 | 7817 | 6000
500043270 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-CDBXF | Circle Drive Gearbox L/H | 71626 | 5572 | 6000
500043269 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-BLMBR | Bracket Blade Mounting R/H | 71626 | 9777 | 6000
500043268 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL-BLMBL | Bracket Blade Mounting L/H | 71626 | 9777 | 6000
500043267 | CLB-MP-GRDR-GR013 -STRUCT-CIRCL | Circle Assembly | 71626 | 71626 | 6000
500043266 | CLB-MP-GRDR-GR013 -STRUCT-DRWBR | Trunnions Blade Lift | 71626 | 12192 | 6000
500043265 | CLB-MP-GRDR-GR013 -STRUCT-DRWBR | Drawbar Group | 71626 | 12192 | 6000
500043264 | CLB-MP-GRDR-GR013 -STRUCT-AXLES-HUBRH | Wheel Bearings RH Front | 71626 | 12192 | 6000
500043263 | CLB-MP-GRDR-GR013 -STRUCT-AXLES-HUBLH | Wheel Bearings LH Front | 71626 | 12192 | 6000
500043262 | CLB-MP-GRDR-GR013 -STRUCT-AXLES | Axle Assembly Front | 71626 | 12192 | 6000
500043261 | CLB-MP-GRDR-GR013 -STRUCT-CHASS-ARTIC | Articulation Hitch | 71626 | 71626 | 6000
500043260 | CLB-MP-GRDR-GR013 -STRUCT-CHASS-REFRM | Rear Frame | 71626 | 71626 | 6000
500043259 | CLB-MP-GRDR-GR013 -STRUCT-CHASS-FRFRM | Front Frame | 71626 | 12192 | 6000
500043258 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SBELT | Belt Seat | 71626 | 71626 | 6000
500043257 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-SEATS | Seat Operator | 71626 | 4801 | 6000
500043256 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-CABES | Pressurisation System Cabin | 71626 | 71626 | 6000
500043255 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-CABCO | Condensor Air Conditioning | 71626 | 71626 | 6000
500043254 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-CABPR | Compressor Air Cond System | 71626 | 71626 | 6000
500043253 | CLB-MP-GRDR-GR013 -STRUCT-CABIN-AIRCN | Air Conditioning System | 71626 | 12192 | 6000
500043252 | CLB-MP-GRDR-GR013 -STRUCT-CABIN | Operators Cabin | 71626 | 24065 | 6000
500043251 | CLB-MP-GRDR-GR013 -GRSYST-ALCON | Controller Auto Lube | 71626 | 71626 | 6000
500043250 | CLB-MP-GRDR-GR013 -GRSYST-ALBPP | Pump Auto Lube | 71626 | 12192 | 6000
500043249 | CLB-MP-GRDR-GR013 -GRSYST-GRTNK | Resevoir Auto Lube | 71626 | 71626 | 6000
500043248 | CLB-MP-GRDR-GR013 -GRSYST-GRINJ | Injectors Auto Lube | 71626 | 71626 | 6000
500043247 | CLB-MP-GRDR-GR013 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 71626 | 71626 | 6000
500043246 | CLB-MP-GRDR-GR013 -HYDSYS-HDTNK | Tank Hydraulic | 71626 | 71626 | 6000
500043245 | CLB-MP-GRDR-GR013 -HYDSYS-HDACC | Accumulator Blade Cushion | 71626 | 71626 | 6000
500043244 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-WLCYR | Cylinder Wheel Lean R/H | 71626 | 29807 | 6000
500043243 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-WLCYL | Cylinder Wheel Lean L/H | 71626 | 34274 | 6000
500043242 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 71626 | 12192 | 6000
500043241 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 71626 | 12192 | 6000
500043240 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-SSCYL | Cylinder Blade Side Shift | 71626 | 12192 | 6000
500043239 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-CSCYL | Cylinder Centre Shift | 71626 | 19088 | 6000
500043238 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-ARCYR | Cylinder Articulation RH | 71626 | 12192 | 6000
500043237 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-ARCYL | Clinder Articulation LH | 71626 | 12192 | 6000
500043236 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-BTCYR | Cylinder Blade Tip RH | 71626 | 71626 | 6000
500043235 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-BTCYL | Cylinder Blade Tip LH | 71626 | 46146 | 6000
500043234 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift RH | 71626 | 18065 | 6000
500043233 | CLB-MP-GRDR-GR013 -HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift LH | 71626 | 19088 | 6000
500043232 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT03 | Fan Motor | 71626 | 12192 | 6000
500043231 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT02 | Motor Circle Drive Rear | 71626 | 32004 | 6000
500043230 | CLB-MP-GRDR-GR013 -HYDSYS-HDMOT-MOT01 | Motor Circle Drive Front | 71626 | 38189 | 6000
500043229 | CLB-MP-GRDR-GR013 -HYDSYS-HDCVL-BK5RH | Valve Hyd Control R/H | 71626 | 71626 | 6000
500043228 | CLB-MP-GRDR-GR013 -HYDSYS-HDCVL-BK5LH | Valve Hyd Control L/H | 71626 | 71626 | 6000
500043227 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-DIFFL | Pump Diff lock | 71626 | 12192 | 6000
500043226 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-FANPP | Pump Fan Motor & Brakes | 71626 | 12192 | 6000
500043225 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYSTP | Pump Steering | 71626 | 12192 | 6000
500043224 | CLB-MP-GRDR-GR013 -HYDSYS-HYDPP-HYIMP | Pump Implement | 71626 | 9489 | 6000
500043223 | CLB-MP-GRDR-GR013 -HYDSYS | Hydraulic System | 71626 | 71626 | 6000
500043222 | CLB-MP-GRDR-GR013 -STRSYS-STEMG-SESPP | Pump Secondary Steering | 71626 | 12192 | 6000
500043221 | CLB-MP-GRDR-GR013 -STRSYS-STCON | Valve Steering Control | 71626 | 71626 | 6000
500043220 | CLB-MP-GRDR-GR013 -STRSYS-STLTR | Steering Linkage | 71626 | 12192 | 6000
500043219 | CLB-MP-GRDR-GR013 -STRSYS-STRCY-STCYR | Steering Cylinder RH | 71626 | 12192 | 6000
500043218 | CLB-MP-GRDR-GR013 -STRSYS-STRCY-STCYL | Steering Cylinder LH | 71626 | 12192 | 6000
500043217 | CLB-MP-GRDR-GR013 -BRKSYS-BRACC-ACC02 | Accumulator Brake Left | 71626 | 71626 | 6000
500043216 | CLB-MP-GRDR-GR013 -BRKSYS-BRACC-ACC01 | Accumulator Brake Right | 71626 | 71626 | 6000
500043215 | CLB-MP-GRDR-GR013 -BRKSYS-BRCON | Valve Brake Control | 71626 | 71626 | 6000
500043214 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACR | Slack Adjuster Brake Right | 71626 | 12192 | 6000
500043213 | CLB-MP-GRDR-GR013 -BRKSYS-SLACK-SLACL | Slack Adjuster Brake Left | 71626 | 12192 | 6000
500043212 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRR | Brake Assembly RHR | 71626 | 12192 | 6000
500043211 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLR | Brake Assembly LHR | 71626 | 12192 | 6000
500043210 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBRF | Brake Assembly RHF | 71626 | 12192 | 6000
500043209 | CLB-MP-GRDR-GR013 -BRKSYS-SRVBK-SVBLF | Brake Assembly LHF | 71626 | 12192 | 6000
500043208 | CLB-MP-GRDR-GR013 -FDRSYS-WHTYR-POS06 | POS 6 Tyre & Rim | 71626 | 71626 | 6000
500043207 | CLB-MP-GRDR-GR013 -FDRSYS-WHTYR-POS05 | POS 5 Tyre & Rim | 71626 | 71626 | 6000
500043206 | CLB-MP-GRDR-GR013 -FDRSYS-WHTYR-POS04 | POS 4 Tyre & Rim | 71626 | 71626 | 6000
500043205 | CLB-MP-GRDR-GR013 -FDRSYS-WHTYR-POS03 | POS 3 Tyre & Rim | 71626 | 71626 | 6000
500043204 | CLB-MP-GRDR-GR013 -FDRSYS-WHTYR-POS02 | POS 2 Tyre & Rim | 71626 | 71626 | 6000
500043203 | CLB-MP-GRDR-GR013 -FDRSYS-WHTYR-POS01 | POS 1 Tyre & Rim | 71626 | 71626 | 6000
500043202 | CLB-MP-GRDR-GR013 -FDRSYS-TDRAX-TDARH | Tandem RH | 71626 | 71626 | 6000
500043201 | CLB-MP-GRDR-GR013 -FDRSYS-TDRAX-TDALH | Tandem LH | 71626 | 71626 | 6000
500043200 | CLB-MP-GRDR-GR013 -FDRSYS-FDRVE-FDRRH | Final Drive RH | 71626 | 12192 | 6000
500043199 | CLB-MP-GRDR-GR013 -FDRSYS-FDRVE-FDRLH | Final Drive LH | 71626 | 2335 | 6000
500043198 | CLB-MP-GRDR-GR013 -FDRSYS-DIFFL | Differential | 71626 | 12192 | 6000
500043197 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT02 | Driveshaft - Trans to Torque Conv | 71626 | 5974 | 6000
500043196 | CLB-MP-GRDR-GR013 -FDRSYS-DRSHT-SHT01 | Driveshaft - Trans to Diff | 71626 | 5974 | 6000
500043195 | CLB-MP-GRDR-GR013 -TRNSYS-TRPMP | Transmission Pump | 71626 | 12192 | 6000
500043194 | CLB-MP-GRDR-GR013 -TRNSYS-TROLC | Transmission Oil Cooler | 71626 | 12192 | 6000
500043193 | CLB-MP-GRDR-GR013 -TRNSYS-TRANS | Transmission | 71626 | 12192 | 6000
500043192 | CLB-MP-GRDR-GR013 -TRNSYS-TRQUE | Torque Converter | 71626 | 12192 | 6000
500043191 | CLB-MP-GRDR-GR013 -ELCTLV-START | Motor Starter | 71626 | 71626 | 6000
500043190 | CLB-MP-GRDR-GR013 -ELCTLV-CHARG-BATTY | Batteries | 71626 | 8272 | 6000
500043189 | CLB-MP-GRDR-GR013 -ELCTLV-CHARG-ALTER | Alternator 24V | 71626 | 4169 | 6000
500043188 | CLB-MP-GRDR-GR013 -ENGINE-FUSYS-FUINJ | Injectors Fuel | 71626 | 4169 | 6000
500043187 | CLB-MP-GRDR-GR013 -ENGINE-FUSYS-FULTP | Pump Fuel Transfer | 71626 | 4169 | 6000
500043186 | CLB-MP-GRDR-GR013 -ENGINE-FUSYS-FULPP | Pump Fuel Priming | 71626 | 4169 | 6000
500043185 | CLB-MP-GRDR-GR013 -ENGINE-FUSYS-FULTK | Fuel Tank | 71626 | 71626 | 6000
500043184 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-EXHST | Exhaust/Muffler Group | 71626 | 12192 | 6000
500043183 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-AFTER | Aftercooler | 71626 | 12192 | 6000
500043182 | CLB-MP-GRDR-GR013 -ENGINE-INTEX-TURBO | Turbocharger | 71626 | 2281 | 6000
500043181 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-THERM | Thermostat / Regulator | 71626 | 4169 | 6000
500043180 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-COFAN | Fan Cooling System | 71626 | 71626 | 6000
500043179 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-RADTR | Radiator | 71626 | 12192 | 6000
500043178 | CLB-MP-GRDR-GR013 -ENGINE-COSYS-WTRPP | Pump Water Engine | 71626 | 606 | 6000
500043177 | CLB-MP-GRDR-GR013 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 71626 | 4169 | 6000
500043176 | CLB-MP-GRDR-GR013 -ENGINE-LUBSY-OILPP | Pump Oil | 71626 | 4169 | 6000
500037588 | CLB-MP-GRDR-GR013 -ENGINE | Engine Assembly, Caterpillar C18 | 71626 | 4169 | 6000
500036267 | CLB-MP-GRDR-GR013 | GR013 Lubrication & Mechanical Services | 71626 | 71626 | 6000
500036266 | CLB-MP-GRDR-GR013 | Caterpillar 24M Motor Grader, GR013 | 71626 | 71626 | 6000
500120883 | CLB-MP-DOZR-DZ8226-HYDSYS-HYDPP-HYIP2 | DZ8226 Pump Hydraulic Implement 2 | 18270 | 5919 | 4800
500120873 | CLB-MP-DOZR-DZ8226-HYDSYS-HYDPP-HYDVC | DZ8226 Pump Hydraulic Variable Charge | 18270 | 3570 | 4800
500118762 | CLB-MP-DOZR-DZ8226-TRNSYS-TRQUE | DZ8226 Torque Converter | 18270 | 5919 | 4800
500118761 | CLB-MP-DOZR-DZ8226-TRNSYS-TRPMP | DZ8226 Pump Trans & TConverter Charge | 18270 | 5919 | 4800
500118760 | CLB-MP-DOZR-DZ8226-TRNSYS-TROLC | DZ8226 Oil Cooler Transmission | 18270 | 18270 | 4800
500118759 | CLB-MP-DOZR-DZ8226-TRNSYS-TRANS-BEVEL | DZ8226 Bevel Gear | 18270 | 18270 | 4800
500118758 | CLB-MP-DOZR-DZ8226-TRNSYS-TRANS | DZ8226 Transmission | 18270 | 5919 | 4800
500118757 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-TKFRR | DZ8226 Track Frame R/H | 18270 | 3570 | 4800
500118756 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-TKFRL | DZ8226 Track Frame L/H | 18270 | 3570 | 4800
500118755 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-PIVOT | DZ8226 Pivot Shaft | 18270 | 18270 | 4800
500118754 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-LDSFR | DZ8226 Rollers Load Single Flange RH | 18270 | 18270 | 4800
500118753 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-LDSFL | DZ8226 Rollers Load Single Flange LH | 18270 | 18270 | 4800
500118752 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-LDDFR | DZ8226 Rollers Load Double Flange RH | 18270 | 18270 | 4800
500118751 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-LDDFL | DZ8226 Rollers Load Double Flange LH | 18270 | 18270 | 4800
500118750 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-IDRHR | DZ8226 Idler Track R/H Rear | 18270 | 18270 | 4800
500118749 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-IDRHF | DZ8226 Idler Track R/H Front | 18270 | 18270 | 4800
500118748 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-IDLHR | DZ8226 Idler Track L/H Rear | 18270 | 18270 | 4800
500118747 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-IDLHF | DZ8226 Idler Track L/H Front | 18270 | 18270 | 4800
500118746 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-ADJRH | DZ8226 Track Adjuster R/H | 18270 | 18270 | 4800
500118745 | CLB-MP-DOZR-DZ8226-STRUCT-UNDER-ADJLH | DZ8226 Track Adjuster L/H | 18270 | 18270 | 4800
500118744 | CLB-MP-DOZR-DZ8226-STRUCT-RIPPR | DZ8226 Ripper | 18270 | 18270 | 4800
500118743 | CLB-MP-DOZR-DZ8226-STRUCT-CHASS-TRNON | DZ8226 Trunnions | 18270 | 18270 | 4800
500118742 | CLB-MP-DOZR-DZ8226-STRUCT-CHASS-PUARM | DZ8226 Push Arms | 18270 | 18270 | 4800
500118741 | CLB-MP-DOZR-DZ8226-TRNSYS-DRSHT | DZ8226 Drive Shaft | 18270 | 18270 | 4800
500118740 | CLB-MP-DOZR-DZ8226-STRUCT-CHASS-LNKGE | DZ8226 Link Stabiliser | 18270 | 18270 | 4800
500118739 | CLB-MP-DOZR-DZ8226-STRUCT-CHASS-EQUAL | DZ8226 Equaliser Bar | 18270 | 3571 | 4800
500118738 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-SEATS | DZ8226 Operators Seat | 18270 | 8040 | 4800
500118737 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-SBELT | DZ8226 Seat Belt | 18270 | 18270 | 4800
500118736 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN-AIRCN | DZ8226 Air Conditioning System | 18270 | 18270 | 4800
500118735 | CLB-MP-DOZR-DZ8226-STRUCT-CABIN | DZ8226 Operators Cabin | 18270 | 18270 | 4800
500118734 | CLB-MP-DOZR-DZ8226-STRUCT-BLADE | DZ8226 Blade | 18270 | 18270 | 4800
500118733 | CLB-MP-DOZR-DZ8226-HYDSYS-HYDPP-HYIP1 | DZ8226 Pump Hydraulic Implement 1 | 18270 | 3570 | 4800
500118732 | CLB-MP-DOZR-DZ8226-HYDSYS-HYDPP-HYFPP | DZ8226 Pump Hydraulic Fan | 18270 | 3570 | 4800
500118731 | CLB-MP-DOZR-DZ8226-HYDSYS-HDTNK | DZ8226 Tank Hydraulic | 18270 | 3570 | 4800
500118730 | CLB-MP-DOZR-DZ8226-HYDSYS-HDOCO | DZ8226 Oil Cooler Hydraulic | 18270 | 3570 | 4800
500118729 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-RTCYR | DZ8226 Cylinder Ripper Tilt RH | 18270 | 18270 | 4800
500118728 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-RTCYL | DZ8226 Cylinder Ripper Tilt LH | 18270 | 18270 | 4800
500118727 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-RPUCY | DZ8226 Cylinder Ripper Pin Puller | 18270 | 18270 | 4800
500118726 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-RLCYR | DZ8226 Cylinder Ripper Lift RH | 18270 | 3571 | 4800
500118725 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-RLCYL | DZ8226 Cylinder Ripper Lift LH | 18270 | 3571 | 4800
500118724 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BTCYR | DZ8226 Cylinder Blade Tilt RH | 18270 | 3570 | 4800
500118723 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BTCYL | DZ8226 Cylinder Blade Tilt LH | 18270 | 1984 | 4800
500118722 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYR | DZ8226 Cylinder Blade Lift RH | 18270 | 8046 | 4800
500118721 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCYL-BLCYL | DZ8226 Cylinder Blade Lift LH | 18270 | 1025 | 4800
500118720 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCVL | DZ8226 Implement Valves Hydraulic | 18270 | 18270 | 4800
500118719 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCON | DZ8226 Implement Control Hydraulic | 18270 | 18270 | 4800
500118718 | CLB-MP-DOZR-DZ8226-HYDSYS-HDCFM | DZ8226 Fan Cooling Motor Hydraulic | 18270 | 5919 | 4800
500118717 | CLB-MP-DOZR-DZ8226-GRSYST-GRINJ | DZ8226 Auto Lube Injectors | 18270 | 18270 | 4800
500118716 | CLB-MP-DOZR-DZ8226-GRSYST-ALBPP | DZ8226 Auto Lube Pump | 18270 | 18270 | 4800
500118715 | CLB-MP-DOZR-DZ8226-FRSUPP | DZ8226 Fire Suppression System | 18270 | 18270 | 4800
500118714 | CLB-MP-DOZR-DZ8226-FDRSYS-TRKRH | DZ8226 Track Assembly RH | 18270 | 1984 | 4800
500118713 | CLB-MP-DOZR-DZ8226-FDRSYS-TRKLH | DZ8226 Track Assembly LH | 18270 | 1984 | 4800
500118712 | CLB-MP-DOZR-DZ8226-FDRSYS-SEGRH | DZ8226 Segments RH | 18270 | 10385 | 4800
500118711 | CLB-MP-DOZR-DZ8226-FDRSYS-SEGLH | DZ8226 Segments LH | 18270 | 10385 | 4800
500118710 | CLB-MP-DOZR-DZ8226-FDRSYS-FDRRH | DZ8226 Final Drive RH | 18270 | 5919 | 4800
500118709 | CLB-MP-DOZR-DZ8226-FDRSYS-FDRLH | DZ8226 Final Drive LH | 18270 | 5919 | 4800
500118708 | CLB-MP-DOZR-DZ8226-ENGINE-LUBSY-PREPP | DZ8226 Oil Pump Pre-Lube Engine | 18270 | 18270 | 4800
500118707 | CLB-MP-DOZR-DZ8226-ENGINE-LUBSY-OILPP | DZ8226 Oil Pump Engine | 18270 | 18270 | 4800
500118706 | CLB-MP-DOZR-DZ8226-ENGINE-LUBSY-ENOLC | DZ8226 Oil Cooler Engine | 18270 | 18270 | 4800
500118705 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-TBORH | DZ8226 Turbocharger RH | 18270 | 5919 | 4800
500118704 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-TBOLH | DZ8226 Turbocharger LH | 18270 | 5919 | 4800
500118703 | CLB-MP-DOZR-DZ8226-ENGINE-INTEX-AFTER | DZ8226 Aftercooler | 18270 | 5919 | 4800
500118702 | CLB-MP-DOZR-DZ8226-ENGINE-FUSYS-FULTP | DZ8226 Fuel Transfer Pump | 18270 | 18270 | 4800
500118701 | CLB-MP-DOZR-DZ8226-ENGINE-FUSYS-FUINJ | DZ8226 Fuel Injectors | 18270 | 5919 | 4800
500118700 | CLB-MP-DOZR-DZ8226-ENGINE-COSYS-WTRPP | DZ8226 Water Pump Engine | 18270 | 5919 | 4800
500118699 | CLB-MP-DOZR-DZ8226-ENGINE-COSYS-THERM | DZ8226 Thermostats/Regulators | 18270 | 5919 | 4800
500118698 | CLB-MP-DOZR-DZ8226-ENGINE-COSYS-RADTR | DZ8226 Radiator Engine | 18270 | 5919 | 4800
500118697 | CLB-MP-DOZR-DZ8226-ENGINE-COSYS-COFAN | DZ8226 Fan Cooling System | 18270 | 5919 | 4800
500118696 | CLB-MP-DOZR-DZ8226-ENGINE | DZ8226 Engine Assembly Caterpillar C27 | 18270 | 5919 | 4800
500118695 | CLB-MP-DOZR-DZ8226-ELCTLV-START-STRMR | DZ8226 Starter Motor | 18270 | 5919 | 4800
500118694 | CLB-MP-DOZR-DZ8226-ELCTLV-CHARG-BATTY | DZ8226 Batteries | 18270 | 8310 | 4800
500118693 | CLB-MP-DOZR-DZ8226-ELCTLV-CHARG-ALTER | DZ8226 Alternator 24V | 18270 | 3570 | 4800
500118692 | CLB-MP-DOZR-DZ8226-BRKSTR-STVLV | DZ8226 Valve Hydraulic Steering | 18270 | 18270 | 4800
500118691 | CLB-MP-DOZR-DZ8226-BRKSTR-SCABR | DZ8226 Steering Clutch & Brake Assy RH | 18270 | 5919 | 4800
500118690 | CLB-MP-DOZR-DZ8226-BRKSTR-SCABL | DZ8226 Steering Clutch & Brake Assy LH | 18270 | 5919 | 4800
500118689 | CLB-MP-DOZR-DZ8226-BRKSTR-HYSPP | DZ8226 Pump Hydraulic Steering | 18270 | 18270 | 4800
500118688 | CLB-MP-DOZR-DZ8226 | DZ8226 Lubrication & Mechanical Services | 18270 | 18270 | 4800
500118687 | CLB-MP-DOZR-DZ8226 | DZ8226 Caterpillar D10T2 Dozer | 18270 | 18270 | 4800
500120874 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYIP2 | DZ8225 Pump Hydraulic Implement 2 | 24525 | 9431 | 4800
500120864 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYDVC | DZ8225 Pump Hydraulic Variable Charge | 24525 | 9431 | 4800
500112388 | CLB-MP-DOZR-DZ8225-TRNSYS-TRQUE | DZ8225 Torque Converter | 24525 | 9431 | 4800
500112387 | CLB-MP-DOZR-DZ8225-TRNSYS-TRPMP | DZ8225 Pump Trans & TConverter Charge | 24525 | 9431 | 4800
500112386 | CLB-MP-DOZR-DZ8225-TRNSYS-TROLC | DZ8225 Oil Cooler Transmission | 24525 | 9431 | 4800
500112385 | CLB-MP-DOZR-DZ8225-TRNSYS-TRANS-BEVEL | DZ8225 Bevel Gear | 24525 | 24525 | 4800
500112384 | CLB-MP-DOZR-DZ8225-TRNSYS-TRANS | DZ8225 Transmission | 24525 | 9431 | 4800
500112383 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-TKFRR | DZ8225 Track Frame Right Hand | 24525 | 9431 | 4800
500112382 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-TKFRL | DZ8225 Track Frame Left Hand | 24525 | 9431 | 4800
500112381 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-PIVOT | DZ8225 Pivot Shaft | 24525 | 9431 | 4800
500112380 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-LDSFR | DZ8225 Rollers Load Single Flange RH | 24525 | 24525 | 4800
500112379 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-LDSFL | DZ8225 Rollers Load Single Flange LH | 24525 | 24525 | 4800
500112378 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-LDDFR | DZ8225 Rollers Load Double Flange RH | 24525 | 24525 | 4800
500112377 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-LDDFL | DZ8225 Rollers Load Double Flange LH | 24525 | 24525 | 4800
500112376 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-IDRHR | DZ8225 Idler Track Right Hand Rear | 24525 | 24525 | 4800
500112375 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-IDRHF | DZ8225 Idler Track Right Hand Front | 24525 | 11561 | 4800
500112374 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-IDLHR | DZ8225 Idler Track Left Hand Rear | 24525 | 24525 | 4800
500112373 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-IDLHF | DZ8225 Idler Track Left Hand Front | 24525 | 24525 | 4800
500112372 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-ADJRH | DZ8225 Track Adjuster Right Hand | 24525 | 24525 | 4800
500112371 | CLB-MP-DOZR-DZ8225-STRUCT-UNDER-ADJLH | DZ8225 Track Adjuster Left Hand | 24525 | 24525 | 4800
500112370 | CLB-MP-DOZR-DZ8225-STRUCT-RIPPR | DZ8225 Ripper | 24525 | 9431 | 4800
500112369 | CLB-MP-DOZR-DZ8225-STRUCT-CHASS-TRNON | DZ8225 Trunnions | 24525 | 24525 | 4800
500112368 | CLB-MP-DOZR-DZ8225-STRUCT-CHASS-PUARM | DZ8225 Push Arms | 24525 | 24525 | 4800
500112367 | CLB-MP-DOZR-DZ8225-TRNSYS-DRSHT | DZ8225 Drive Shaft | 24525 | 9431 | 4800
500112366 | CLB-MP-DOZR-DZ8225-STRUCT-CHASS-LNKGE | DZ8225 Link Stabiliser | 24525 | 24525 | 4800
500112365 | CLB-MP-DOZR-DZ8225-STRUCT-CHASS-EQUAL | DZ8225 Equaliser Bar | 24525 | 232 | 4800
500112364 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SEATS | DZ8225 Operators Seat | 24525 | 4908 | 4800
500112363 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-SBELT | DZ8225 Seat Belt | 24525 | 16407 | 4800
500112362 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN-AIRCN | DZ8225 Air Conditioning System | 24525 | 9431 | 4800
500112361 | CLB-MP-DOZR-DZ8225-STRUCT-CABIN | DZ8225 Operators Cabin | 24525 | 24525 | 4800
500112360 | CLB-MP-DOZR-DZ8225-STRUCT-BLADE | DZ8225 Blade | 24525 | 24525 | 4800
500112359 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYIP1 | DZ8225 Pump Hydraulic Implement 1 | 24525 | 9431 | 4800
500112358 | CLB-MP-DOZR-DZ8225-HYDSYS-HYDPP-HYFPP | DZ8225 Pump Hydraulic Fan | 24525 | 9431 | 4800
500112357 | CLB-MP-DOZR-DZ8225-HYDSYS-HDTNK | DZ8225 Tank Hydraulic | 24525 | 9431 | 4800
500112356 | CLB-MP-DOZR-DZ8225-HYDSYS-HDOCO | DZ8225 Oil Cooler Hydraulic | 24525 | 9431 | 4800
500112355 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-RTCYR | DZ8225 Cylinder Ripper Tilt RH | 24525 | 9431 | 4800
500112354 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-RTCYL | DZ8225 Cylinder Ripper Tilt Left Hand | 24525 | 9431 | 4800
500112353 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-RPUCY | DZ8225 Cylinder Ripper Pin Puller | 24525 | 24525 | 4800
500112352 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-RLCYR | DZ8225 Cylinder Ripper Lift Right Hand | 24525 | 9431 | 4800
500112351 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-RLCYL | DZ8225 Cylinder Ripper Lift Left Hand | 24525 | 637 | 4800
500112350 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BTCYR | DZ8225 Cylinder Blade Tilt Right Hand | 24525 | 1509 | 4800
500112349 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BTCYL | DZ8225 Cylinder Blade Tilt Left Hand | 24525 | 1955 | 4800
500112348 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BLCYR | DZ8225 Cylinder Blade Lift Right Hand | 24525 | 232 | 4800
500112347 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCYL-BLCYL | DZ8225 Cylinder Blade Lift Left Hand | 24525 | 1786 | 4800
500112346 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCVL | DZ8225 Implement Valves Hydraulic | 24525 | 24525 | 4800
500112345 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCON | DZ8225 Implement Control Hydraulic | 24525 | 24525 | 4800
500112344 | CLB-MP-DOZR-DZ8225-HYDSYS-HDCFM | DZ8225 Fan Cooling Motor Hydraulic | 24525 | 6330 | 4800
500112343 | CLB-MP-DOZR-DZ8225-GRSYST-GRINJ | DZ8225 Auto Lube Injectors | 24525 | 24525 | 4800
500112342 | CLB-MP-DOZR-DZ8225-GRSYST-ALBPP | DZ8225 Auto Lube Pump | 24525 | 24525 | 4800
500112341 | CLB-MP-DOZR-DZ8225-FRSUPP | DZ8225 Fire Suppression System | 24525 | 9431 | 4800
500112340 | CLB-MP-DOZR-DZ8225-FDRSYS-TRKRH | DZ8225 Track Assembly Right Hand | 24525 | 1786 | 4800
500112339 | CLB-MP-DOZR-DZ8225-FDRSYS-TRKLH | DZ8225 Track Assembly Left Hand | 24525 | 1786 | 4800
500112338 | CLB-MP-DOZR-DZ8225-FDRSYS-SEGRH | DZ8225 Segments Right Hand | 24525 | 24525 | 4800
500112337 | CLB-MP-DOZR-DZ8225-FDRSYS-SEGLH | DZ8225 Segments Left Hand | 24525 | 24525 | 4800
500112336 | CLB-MP-DOZR-DZ8225-FDRSYS-FDRRH | DZ8225 Final Drive Right Hand | 24525 | 9431 | 4800
500112335 | CLB-MP-DOZR-DZ8225-FDRSYS-FDRLH | DZ8225 Final Drive Left Hand | 24525 | 9917 | 4800
500112334 | CLB-MP-DOZR-DZ8225-ENGINE-LUBSY-PREPP | DZ8225 Oil Pump Pre-Lube Engine | 24525 | 24525 | 4800
500112333 | CLB-MP-DOZR-DZ8225-ENGINE-LUBSY-OILPP | DZ8225 Oil Pump Engine | 24542 | 24542 | 4800
500112332 | CLB-MP-DOZR-DZ8225-ENGINE-LUBSY-ENOLC | DZ8225 Oil Cooler Engine | 24542 | 24542 | 4800
500112331 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-TBORH | DZ8225 Turbocharger Right Hand | 24542 | 9431 | 4800
500112330 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-TBOLH | DZ8225 Turbocharger Left Hand | 24542 | 9431 | 4800
500112329 | CLB-MP-DOZR-DZ8225-ENGINE-INTEX-AFTER | DZ8225 Aftercooler | 24542 | 9431 | 4800
500112328 | CLB-MP-DOZR-DZ8225-ENGINE-FUSYS-FULTP | DZ8225 Fuel Transfer Pump | 24542 | 16779 | 4800
500112327 | CLB-MP-DOZR-DZ8225-ENGINE-FUSYS-FUINJ | DZ8225 Fuel Injectors | 24542 | 9431 | 4800
500112326 | CLB-MP-DOZR-DZ8225-ENGINE-COSYS-WTRPP | DZ8225 Water Pump Engine | 24542 | 9431 | 4800
500112325 | CLB-MP-DOZR-DZ8225-ENGINE-COSYS-THERM | DZ8225 Thermostats & Regulators | 24542 | 9431 | 4800
500112324 | CLB-MP-DOZR-DZ8225-ENGINE-COSYS-RADTR | DZ8225 Radiator Engine | 24542 | 9431 | 4800
500112323 | CLB-MP-DOZR-DZ8225-ENGINE-COSYS-COFAN | DZ8225 Fan Cooling System | 24542 | 24542 | 4800
500112322 | CLB-MP-DOZR-DZ8225-ENGINE | DZ8225 Engine Assembly Caterpillar C27 | 24542 | 9431 | 4800
500112321 | CLB-MP-DOZR-DZ8225-ELCTLV-START-STRMR | DZ8225 Starter Motor | 24542 | 9431 | 4800
500112310 | CLB-MP-DOZR-DZ8225-ELCTLV-CHARG-BATTY | DZ8225 Batteries | 24542 | 6301 | 4800
500112309 | CLB-MP-DOZR-DZ8225-ELCTLV-CHARG-ALTER | DZ8225 Alternator 24V | 24542 | 9431 | 4800
500112308 | CLB-MP-DOZR-DZ8225-BRKSTR-STVLV | DZ8225 Valve Hydraulic Steering | 24542 | 24542 | 4800
500112307 | CLB-MP-DOZR-DZ8225-BRKSTR-SCABR | DZ8225 Steering Clutch & Brake Assy RH | 24542 | 11230 | 4800
500112306 | CLB-MP-DOZR-DZ8225-BRKSTR-SCABL | DZ8225 Steering Clutch & Brake Assy LH | 24542 | 9431 | 4800
500112305 | CLB-MP-DOZR-DZ8225-BRKSTR-HYSPP | DZ8225 Pump Hydraulic Steering | 24542 | 24542 | 4800
500112304 | CLB-MP-DOZR-DZ8225 | DZ8225 Lubrication & Mechanical Services | 24542 | 24542 | 4800
500112303 | CLB-MP-DOZR-DZ8225 | DZ8225 Caterpillar D10T2 Dozer | 24542 | 24542 | 4800
500159027 | CLB-MP-DOZR-DZ8224-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 26987 | 4944 | 4800
500120879 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYIP2 | DZ8224 Pump Hydraulic Implement 2 | 26941 | 11824 | 4800
500120869 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYDVC | DZ8224 Pump Hydraulic Variable Charge | 26941 | 1661 | 4800
500108208 | CLB-MP-DOZR-DZ8224-TRNSYS-TRQUE | DZ8224 Torque Converter | 26987 | 11824 | 4800
500108207 | CLB-MP-DOZR-DZ8224-TRNSYS-TRPMP | DZ8224 Pump Trans & TConverter Charge | 26987 | 11824 | 4800
500108206 | CLB-MP-DOZR-DZ8224-TRNSYS-TROLC | DZ8224 Oil Cooler Transmission | 26987 | 11824 | 4800
500108205 | CLB-MP-DOZR-DZ8224-TRNSYS-TRANS-BEVEL | DZ8224 Bevel Gear | 26987 | 26987 | 4800
500108204 | CLB-MP-DOZR-DZ8224-TRNSYS-TRANS | DZ8224 Transmission | 26987 | 11824 | 4800
500108203 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-TKFRR | DZ8224 Track Frame R/H | 26987 | 1430 | 4800
500108202 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-TKFRL | DZ8224 Track Frame L/H | 26987 | 1430 | 4800
500108201 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-PIVOT | DZ8224 Pivot Shaft | 26987 | 26987 | 4800
500108200 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-LDSFR | DZ8224 Rollers Load Single Flange RH | 26987 | 26987 | 4800
500108199 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-LDSFL | DZ8224 Rollers Load Single Flange LH | 26987 | 26987 | 4800
500108198 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-LDDFR | DZ8224 Rollers Load Double Flange RH | 26987 | 26987 | 4800
500108197 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-LDDFL | DZ8224 Rollers Load Double Flange LH | 26987 | 26987 | 4800
500108196 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-IDRHR | DZ8224 Idler Track R/H Rear | 26987 | 26987 | 4800
500108195 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-IDRHF | DZ8224 Idler Track R/H Front | 26987 | 26987 | 4800
500108194 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-IDLHR | DZ8224 Idler Track L/H Rear | 26987 | 26987 | 4800
500108193 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-IDLHF | DZ8224 Idler Track L/H Front | 26987 | 26987 | 4800
500108192 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-ADJRH | DZ8224 Track Adjuster R/H | 26987 | 26987 | 4800
500108191 | CLB-MP-DOZR-DZ8224-STRUCT-UNDER-ADJLH | DZ8224 Track Adjuster L/H | 26987 | 26987 | 4800
500108190 | CLB-MP-DOZR-DZ8224-STRUCT-RIPPR | DZ8224 Ripper | 26987 | 11824 | 4800
500108189 | CLB-MP-DOZR-DZ8224-STRUCT-CHASS-TRNON | DZ8224 Trunnions | 26987 | 26987 | 4800
500108188 | CLB-MP-DOZR-DZ8224-STRUCT-CHASS-PUARM | DZ8224 Push Arms | 26987 | 26987 | 4800
500108187 | CLB-MP-DOZR-DZ8224-TRNSYS-DRSHT | DZ8224 Drive Shaft | 26987 | 11824 | 4800
500108186 | CLB-MP-DOZR-DZ8224-STRUCT-CHASS-LNKGE | DZ8224 Link Stabiliser | 26987 | 26987 | 4800
500108185 | CLB-MP-DOZR-DZ8224-STRUCT-CHASS-EQUAL | DZ8224 Equaliser Bar | 26987 | 11824 | 4800
500108184 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SEATS | DZ8224 Operators Seat | 26987 | 6075 | 4800
500108183 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-SBELT | DZ8224 Seat Belt | 26987 | 26987 | 4800
500108182 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN-AIRCN | DZ8224 Air Conditioning System | 26987 | 8028 | 4800
500108181 | CLB-MP-DOZR-DZ8224-STRUCT-CABIN | DZ8224 Operators Cabin | 26987 | 26987 | 4800
500108180 | CLB-MP-DOZR-DZ8224-STRUCT-BLADE | DZ8224 Blade | 26987 | 26987 | 4800
500108179 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYIP1 | DZ8224 Pump Hydraulic Implement 1 | 26987 | 11824 | 4800
500108178 | CLB-MP-DOZR-DZ8224-HYDSYS-HYDPP-HYFPP | DZ8224 Pump Hydraulic Fan | 26987 | 11824 | 4800
500108177 | CLB-MP-DOZR-DZ8224-HYDSYS-HDTNK | DZ8224 Tank Hydraulic | 26987 | 11824 | 4800
500108176 | CLB-MP-DOZR-DZ8224-HYDSYS-HDOCO | DZ8224 Oil Cooler Hydraulic | 26987 | 11824 | 4800
500108175 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-RTCYR | DZ8224 Cylinder Ripper Tilt RH | 26987 | 1431 | 4800
500108174 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-RTCYL | DZ8224 Cylinder Ripper Tilt LH | 26987 | 11824 | 4800
500108173 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-RPUCY | DZ8224 Cylinder Ripper Pin Puller | 26987 | 26987 | 4800
500108172 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-RLCYR | DZ8224 Cylinder Ripper Lift R/H | 26987 | 9686 | 4800
500108171 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-RLCYL | DZ8224 Cylinder Ripper Lift L/H | 26987 | 11824 | 4800
500108170 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BTCYR | DZ8224 Cylinder Blade Tilt R/H | 26987 | 8471 | 4800
500108169 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BTCYL | DZ8224 Cylinder Blade Tilt L/H | 26987 | 1876 | 4800
500108168 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYR | DZ8224 Cylinder Blade Lift R/H | 26987 | 1876 | 4800
500108167 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCYL-BLCYL | DZ8224 Cylinder Blade Lift L/H | 26987 | 8732 | 4800
500108166 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCVL | DZ8224 Implement Valves Hydraulic | 26987 | 26987 | 4800
500108165 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCON | DZ8224 Implement Control Hydraulic | 26987 | 26987 | 4800
500108164 | CLB-MP-DOZR-DZ8224-HYDSYS-HDCFM | DZ8224 Fan Cooling Motor Hydraulic | 26987 | 11824 | 4800
500108163 | CLB-MP-DOZR-DZ8224-GRSYST-GRINJ | DZ8224 Auto Lube Injectors | 26987 | 26987 | 4800
500108162 | CLB-MP-DOZR-DZ8224-GRSYST-ALBPP | DZ8224 Auto Lube Pump | 26987 | 26987 | 4800
500108161 | CLB-MP-DOZR-DZ8224-FRSUPP | DZ8224 Fire Suppression System | 26987 | 26987 | 4800
500108160 | CLB-MP-DOZR-DZ8224-FDRSYS-TRKRH | DZ8224 Track Assembly R/H | 26987 | 8028 | 4800
500108159 | CLB-MP-DOZR-DZ8224-FDRSYS-TRKLH | DZ8224 Track Assembly L/H | 26987 | 8028 | 4800
500108158 | CLB-MP-DOZR-DZ8224-FDRSYS-SEGRH | DZ8224 Segments R/H | 26987 | 22081 | 4800
500108157 | CLB-MP-DOZR-DZ8224-FDRSYS-SEGLH | DZ8224 Segments L/H | 26987 | 22081 | 4800
500108156 | CLB-MP-DOZR-DZ8224-FDRSYS-FDRRH | DZ8224 Final Drive R/H | 26987 | 11824 | 4800
500108155 | CLB-MP-DOZR-DZ8224-FDRSYS-FDRLH | DZ8224 Final Drive L/H | 26987 | 11824 | 4800
500108154 | CLB-MP-DOZR-DZ8224-ENGINE-LUBSY-PREPP | DZ8224 Oil Pump Pre-Lube Engine | 26987 | 26987 | 4800
500108153 | CLB-MP-DOZR-DZ8224-ENGINE-LUBSY-OILPP | DZ8224 Oil Pump Engine | 26987 | 26987 | 4800
500108152 | CLB-MP-DOZR-DZ8224-ENGINE-LUBSY-ENOLC | DZ8224 Oil Cooler Engine | 26987 | 26987 | 4800
500108151 | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-TBORH | DZ8224 Turbocharger R/H | 26987 | 1431 | 4800
500108150 | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-TBOLH | DZ8224 Turbocharger L/H | 26987 | 1431 | 4800
500108149 | CLB-MP-DOZR-DZ8224-ENGINE-INTEX-AFTER | DZ8224 Aftercooler | 26987 | 11824 | 4800
500108148 | CLB-MP-DOZR-DZ8224-ENGINE-FUSYS-FULTP | DZ8224 Fuel Transfer Pump | 26987 | 26987 | 4800
500108147 | CLB-MP-DOZR-DZ8224-ENGINE-FUSYS-FUINJ | DZ8224 Fuel Injectors | 26987 | 1431 | 4800
500108146 | CLB-MP-DOZR-DZ8224-ENGINE-COSYS-WTRPP | DZ8224 Water Pump Engine | 26987 | 1431 | 4800
500108145 | CLB-MP-DOZR-DZ8224-ENGINE-COSYS-THERM | DZ8224 Thermostats/Regulators | 26987 | 1431 | 4800
500108144 | CLB-MP-DOZR-DZ8224-ENGINE-COSYS-RADTR | DZ8224 Radiator Engine | 26987 | 11824 | 4800
500108143 | CLB-MP-DOZR-DZ8224-ENGINE-COSYS-COFAN | DZ8224 Fan Cooling System | 26987 | 26987 | 4800
500108142 | CLB-MP-DOZR-DZ8224-ENGINE | DZ8224 Engine Assembly Caterpillar C27 | 26987 | 11824 | 4800
500108141 | CLB-MP-DOZR-DZ8224-ELCTLV-START-STRMR | DZ8224 Starter Motor | 26987 | 1431 | 4800
500108140 | CLB-MP-DOZR-DZ8224-ELCTLV-CHARG-BATTY | DZ8224 Batteries | 26987 | 11768 | 4800
500108139 | CLB-MP-DOZR-DZ8224-ELCTLV-CHARG-ALTER | DZ8224 Alternator 24V | 26987 | 1431 | 4800
500108138 | CLB-MP-DOZR-DZ8224-BRKSTR-STVLV | DZ8224 Valve Hydraulic Steering | 26987 | 26987 | 4800
500108137 | CLB-MP-DOZR-DZ8224-BRKSTR-SCABR | DZ8224 Steering Clutch & Brake Assy RH | 26987 | 11824 | 4800
500108136 | CLB-MP-DOZR-DZ8224-BRKSTR-SCABL | DZ8224 Steering Clutch & Brake Assy LH | 26987 | 11824 | 4800
500108135 | CLB-MP-DOZR-DZ8224-BRKSTR-HYSPP | DZ8224 Pump Hydraulic Steering | 26987 | 26987 | 4800
500108134 | CLB-MP-DOZR-DZ8224 | DZ8224 Lubrication & Mechanical Services | 26987 | 26987 | 4800
500108133 | CLB-MP-DOZR-DZ8224 | DZ8224 Caterpillar D10T2 Dozer | 26987 | 26987 | 4800
500120878 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYIP2 | DZ8223 Pump Hydraulic Implement 2 | 26699 | 12533 | 4800
500120868 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYDVC | DZ8223 Pump Hydraulic Variable Charge | 26699 | 12533 | 4800
500108132 | CLB-MP-DOZR-DZ8223-TRNSYS-TRQUE | DZ8223 Torque Converter | 26747 | 12533 | 4800
500108131 | CLB-MP-DOZR-DZ8223-TRNSYS-TRPMP | DZ8223 Pump Trans & TConverter Charge | 26747 | 12533 | 4800
500108130 | CLB-MP-DOZR-DZ8223-TRNSYS-TROLC | DZ8223 Oil Cooler Transmission | 26747 | 26747 | 4800
500108129 | CLB-MP-DOZR-DZ8223-TRNSYS-TRANS-BEVEL | DZ8223 Bevel Gear | 26747 | 26747 | 4800
500108128 | CLB-MP-DOZR-DZ8223-TRNSYS-TRANS | DZ8223 Transmission | 26747 | 12533 | 4800
500108127 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-TKFRR | DZ8223 Track Frame R/H | 26747 | 12533 | 4800
500108126 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-TKFRL | DZ8223 Track Frame L/H | 26747 | 12533 | 4800
500108125 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-PIVOT | DZ8223 Pivot Shaft | 26747 | 12533 | 4800
500108124 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-LDSFR | DZ8223 Rollers Load Single Flange RH | 26747 | 26747 | 4800
500108123 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-LDSFL | DZ8223 Rollers Load Single Flange LH | 26747 | 26747 | 4800
500108122 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-LDDFR | DZ8223 Rollers Load Double Flange RH | 26747 | 26747 | 4800
500108121 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-LDDFL | DZ8223 Rollers Load Double Flange LH | 26747 | 26747 | 4800
500108120 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-IDRHR | DZ8223 Idler Track R/H Rear | 26747 | 11055 | 4800
500108119 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-IDRHF | DZ8223 Idler Track R/H Front | 26747 | 26747 | 4800
500108118 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-IDLHR | DZ8223 Idler Track L/H Rear | 26747 | 11055 | 4800
500108117 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-IDLHF | DZ8223 Idler Track L/H Front | 26747 | 26747 | 4800
500108116 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-ADJRH | DZ8223 Track Adjuster R/H | 26747 | 26747 | 4800
500108115 | CLB-MP-DOZR-DZ8223-STRUCT-UNDER-ADJLH | DZ8223 Track Adjuster L/H | 26747 | 26747 | 4800
500108114 | CLB-MP-DOZR-DZ8223-STRUCT-RIPPR | DZ8223 Ripper | 26747 | 26747 | 4800
500108113 | CLB-MP-DOZR-DZ8223-STRUCT-CHASS-TRNON | DZ8223 Trunnions | 26747 | 26747 | 4800
500108112 | CLB-MP-DOZR-DZ8223-STRUCT-CHASS-PUARM | DZ8223 Push Arms | 26747 | 1473 | 4800
500108111 | CLB-MP-DOZR-DZ8223-TRNSYS-DRSHT | DZ8223 Drive Shaft | 26747 | 12533 | 4800
500108110 | CLB-MP-DOZR-DZ8223-STRUCT-CHASS-LNKGE | DZ8223 Link Stabiliser | 26747 | 26747 | 4800
500108109 | CLB-MP-DOZR-DZ8223-STRUCT-CHASS-EQUAL | DZ8223 Equaliser Bar | 26747 | 3004 | 4800
500108108 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-SEATS | DZ8223 Operators Seat | 26747 | 3032 | 4800
500108107 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-SBELT | DZ8223 Seat Belt | 26747 | 10711 | 4800
500108106 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN-AIRCN | DZ8223 Air Conditioning System | 26747 | 12533 | 4800
500108105 | CLB-MP-DOZR-DZ8223-STRUCT-CABIN | DZ8223 Operators Cabin | 26747 | 12533 | 4800
500108104 | CLB-MP-DOZR-DZ8223-STRUCT-BLADE | DZ8223 Blade | 26747 | 26747 | 4800
500108103 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYIP1 | DZ8223 Pump Hydraulic Implement 1 | 26747 | 5003 | 4800
500108102 | CLB-MP-DOZR-DZ8223-HYDSYS-HYDPP-HYFPP | DZ8223 Pump Hydraulic Fan | 26747 | 12533 | 4800
500108101 | CLB-MP-DOZR-DZ8223-HYDSYS-HDTNK | DZ8223 Tank Hydraulic | 26747 | 12533 | 4800
500108100 | CLB-MP-DOZR-DZ8223-HYDSYS-HDOCO | DZ8223 Oil Cooler Hydraulic | 26747 | 12533 | 4800
500108099 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-RTCYR | DZ8223 Cylinder Ripper Tilt RH | 26747 | 12533 | 4800
500108098 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-RTCYL | DZ8223 Cylinder Ripper Tilt LH | 26747 | 12533 | 4800
500108097 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-RPUCY | DZ8223 Cylinder Ripper Pin Puller | 26747 | 26747 | 4800
500108096 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-RLCYR | DZ8223 Cylinder Ripper Lift R/H | 26747 | 8895 | 4800
500108095 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-RLCYL | DZ8223 Cylinder Ripper Lift L/H | 26747 | 8895 | 4800
500108094 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BTCYR | DZ8223 Cylinder Blade Tilt R/H | 26747 | 14495 | 4800
500108093 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BTCYL | DZ8223 Cylinder Blade Tilt L/H | 26747 | 14154 | 4800
500108092 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BLCYR | DZ8223 Cylinder Blade Lift R/H | 26747 | 1473 | 4800
500108091 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCYL-BLCYL | DZ8223 Cylinder Blade Lift L/H | 26747 | 2490 | 4800
500108090 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCVL | DZ8223 Implement Valves Hydraulic | 26747 | 26747 | 4800
500108089 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCON | DZ8223 Implement Control Hydraulic | 26747 | 26747 | 4800
500108088 | CLB-MP-DOZR-DZ8223-HYDSYS-HDCFM | DZ8223 Fan Cooling Motor Hydraulic | 26747 | 12533 | 4800
500108087 | CLB-MP-DOZR-DZ8223-GRSYST-GRINJ | DZ8223 Auto Lube Injectors | 26747 | 26747 | 4800
500108086 | CLB-MP-DOZR-DZ8223-GRSYST-ALBPP | DZ8223 Auto Lube Pump | 26747 | 26747 | 4800
500108085 | CLB-MP-DOZR-DZ8223-FRSUPP | DZ8223 Fire Suppression System | 26747 | 26747 | 4800
500108084 | CLB-MP-DOZR-DZ8223-FDRSYS-TRKRH | DZ8223 Track Assembly R/H | 26747 | 386 | 4800
500108083 | CLB-MP-DOZR-DZ8223-FDRSYS-TRKLH | DZ8223 Track Assembly L/H | 26747 | 386 | 4800
500108082 | CLB-MP-DOZR-DZ8223-FDRSYS-SEGRH | DZ8223 Segments R/H | 26747 | 26747 | 4800
500108081 | CLB-MP-DOZR-DZ8223-FDRSYS-SEGLH | DZ8223 Segments L/H | 26747 | 26747 | 4800
500108080 | CLB-MP-DOZR-DZ8223-FDRSYS-FDRRH | DZ8223 Final Drive R/H | 26747 | 12533 | 4800
500108079 | CLB-MP-DOZR-DZ8223-FDRSYS-FDRLH | DZ8223 Final Drive L/H | 26747 | 12533 | 4800
500108078 | CLB-MP-DOZR-DZ8223-ENGINE-LUBSY-PREPP | DZ8223 Oil Pump Pre-Lube Engine | 26747 | 26747 | 4800
500108077 | CLB-MP-DOZR-DZ8223-ENGINE-LUBSY-OILPP | DZ8223 Oil Pump Engine | 26747 | 26747 | 4800
500108076 | CLB-MP-DOZR-DZ8223-ENGINE-LUBSY-ENOLC | DZ8223 Oil Cooler Engine | 26747 | 26747 | 4800
500108075 | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-TBORH | DZ8223 Turbocharger R/H | 26747 | 4676 | 4800
500108074 | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-TBOLH | DZ8223 Turbocharger L/H | 26747 | 4676 | 4800
500108073 | CLB-MP-DOZR-DZ8223-ENGINE-INTEX-AFTER | DZ8223 Aftercooler | 26747 | 12533 | 4800
500108072 | CLB-MP-DOZR-DZ8223-ENGINE-FUSYS-FULTP | DZ8223 Fuel Transfer Pump | 26747 | 26747 | 4800
500108071 | CLB-MP-DOZR-DZ8223-ENGINE-FUSYS-FUINJ | DZ8223 Fuel Injectors | 26747 | 4676 | 4800
500108070 | CLB-MP-DOZR-DZ8223-ENGINE-COSYS-WTRPP | DZ8223 Water Pump Engine | 26747 | 494 | 4800
500108069 | CLB-MP-DOZR-DZ8223-ENGINE-COSYS-THERM | DZ8223 Thermostats/Regulators | 26747 | 4676 | 4800
500108068 | CLB-MP-DOZR-DZ8223-ENGINE-COSYS-RADTR | DZ8223 Radiator Engine | 26747 | 12533 | 4800
500108067 | CLB-MP-DOZR-DZ8223-ENGINE-COSYS-COFAN | DZ8223 Fan Cooling System | 26747 | 21360 | 4800
500108066 | CLB-MP-DOZR-DZ8223-ENGINE | DZ8223 Engine Assembly Caterpillar C27 | 26747 | 12533 | 4800
500108065 | CLB-MP-DOZR-DZ8223-ELCTLV-START-STRMR | DZ8223 Starter Motor | 26747 | 4676 | 4800
500108064 | CLB-MP-DOZR-DZ8223-ELCTLV-CHARG-BATTY | DZ8223 Batteries | 26747 | 11369 | 4800
500108063 | CLB-MP-DOZR-DZ8223-ELCTLV-CHARG-ALTER | DZ8223 Alternator 24V | 26747 | 4676 | 4800
500108062 | CLB-MP-DOZR-DZ8223-BRKSTR-STVLV | DZ8223 Valve Hydraulic Steering | 26747 | 26747 | 4800
500108061 | CLB-MP-DOZR-DZ8223-BRKSTR-SCABR | DZ8223 Steering Clutch & Brake Assy RH | 26747 | 12533 | 4800
500108060 | CLB-MP-DOZR-DZ8223-BRKSTR-SCABL | DZ8223 Steering Clutch & Brake Assy LH | 26747 | 12533 | 4800
500108059 | CLB-MP-DOZR-DZ8223-BRKSTR-HYSPP | DZ8223 Pump Hydraulic Steering | 26747 | 26747 | 4800
500108058 | CLB-MP-DOZR-DZ8223 | DZ8223 Lubrication & Mechanical Services | 26747 | 26747 | 4800
500108057 | CLB-MP-DOZR-DZ8223 | DZ8223 Caterpillar D10T2 Dozer | 26747 | 26747 | 4800
500150696 | CLB-MP-DOZR-DZ8222-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 25262 | 25262 | 4800
500120877 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYIP2 | DZ8222 Pump Hydraulic Implement 2 | 25166 | 12059 | 4800
500120867 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYDVC | DZ8222 Pump Hydraulic Variable Charge | 25166 | 12059 | 4800
500108056 | CLB-MP-DOZR-DZ8222-TRNSYS-TRQUE | DZ8222 Torque Converter | 25244 | 12059 | 4800
500108055 | CLB-MP-DOZR-DZ8222-TRNSYS-TRPMP | DZ8222 Pump Trans & TConverter Charge | 25244 | 16002 | 4800
500108054 | CLB-MP-DOZR-DZ8222-TRNSYS-TROLC | DZ8222 Oil Cooler Transmission | 25244 | 12059 | 4800
500108053 | CLB-MP-DOZR-DZ8222-TRNSYS-TRANS-BEVEL | DZ8222 Bevel Gear | 25244 | 25244 | 4800
500108052 | CLB-MP-DOZR-DZ8222-TRNSYS-TRANS | DZ8222 Transmission | 25244 | 12059 | 4800
500108051 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-TKFRR | DZ8222 Track Frame R/H | 25244 | 12059 | 4800
500108050 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-TKFRL | DZ8222 Track Frame L/H | 25244 | 12059 | 4800
500108049 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-PIVOT | DZ8222 Pivot Shaft | 25244 | 12059 | 4800
500108048 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-LDSFR | DZ8222 Rollers Load Single Flange RH | 25244 | 25244 | 4800
500108047 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-LDSFL | DZ8222 Rollers Load Single Flange LH | 25244 | 25244 | 4800
500108046 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-LDDFR | DZ8222 Rollers Load Double Flange RH | 25244 | 25244 | 4800
500108045 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-LDDFL | DZ8222 Rollers Load Double Flange LH | 25244 | 25244 | 4800
500108044 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-IDRHR | DZ8222 Idler Track R/H Rear | 25244 | 25244 | 4800
500108043 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-IDRHF | DZ8222 Idler Track R/H Front | 25244 | 25244 | 4800
500108042 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-IDLHR | DZ8222 Idler Track L/H Rear | 25244 | 25244 | 4800
500108041 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-IDLHF | DZ8222 Idler Track L/H Front | 25244 | 452 | 4800
500108040 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-ADJRH | DZ8222 Track Adjuster R/H | 25244 | 25244 | 4800
500108039 | CLB-MP-DOZR-DZ8222-STRUCT-UNDER-ADJLH | DZ8222 Track Adjuster L/H | 25244 | 25244 | 4800
500108038 | CLB-MP-DOZR-DZ8222-STRUCT-RIPPR | DZ8222 Ripper | 25244 | 12059 | 4800
500108037 | CLB-MP-DOZR-DZ8222-STRUCT-CHASS-TRNON | DZ8222 Trunnions | 25244 | 25244 | 4800
500108036 | CLB-MP-DOZR-DZ8222-STRUCT-CHASS-PUARM | DZ8222 Push Arms | 25244 | 25244 | 4800
500108035 | CLB-MP-DOZR-DZ8222-TRNSYS-DRSHT | DZ8222 Drive Shaft | 25244 | 12059 | 4800
500108034 | CLB-MP-DOZR-DZ8222-STRUCT-CHASS-LNKGE | DZ8222 Link Stabiliser | 25244 | 25244 | 4800
500108033 | CLB-MP-DOZR-DZ8222-STRUCT-CHASS-EQUAL | DZ8222 Equaliser Bar | 25244 | 5453 | 4800
500108032 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SEATS | DZ8222 Operators Seat | 25244 | 5824 | 4800
500108031 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-SBELT | DZ8222 Seat Belt | 25244 | 25244 | 4800
500108030 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN-AIRCN | DZ8222 Air Conditioning System | 25244 | 12059 | 4800
500108029 | CLB-MP-DOZR-DZ8222-STRUCT-CABIN | DZ8222 Operators Cabin | 25244 | 25244 | 4800
500108028 | CLB-MP-DOZR-DZ8222-STRUCT-BLADE | DZ8222 Blade | 25244 | 25244 | 4800
500108027 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYIP1 | DZ8222 Pump Hydraulic Implement 1 | 25244 | 12059 | 4800
500108026 | CLB-MP-DOZR-DZ8222-HYDSYS-HYDPP-HYFPP | DZ8222 Pump Hydraulic Fan | 25244 | 12059 | 4800
500108025 | CLB-MP-DOZR-DZ8222-HYDSYS-HDTNK | DZ8222 Tank Hydraulic | 25244 | 12059 | 4800
500108024 | CLB-MP-DOZR-DZ8222-HYDSYS-HDOCO | DZ8222 Oil Cooler Hydraulic | 25244 | 825 | 4800
500108023 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-RTCYR | DZ8222 Cylinder Ripper Tilt RH | 25244 | 12059 | 4800
500108022 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-RTCYL | DZ8222 Cylinder Ripper Tilt LH | 25244 | 12059 | 4800
500108021 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-RPUCY | DZ8222 Cylinder Ripper Pin Puller | 25244 | 25244 | 4800
500108020 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-RLCYR | DZ8222 Cylinder Ripper Lift R/H | 25244 | 12059 | 4800
500108019 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-RLCYL | DZ8222 Cylinder Ripper Lift L/H | 25244 | 12059 | 4800
500108018 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BTCYR | DZ8222 Cylinder Blade Tilt R/H | 25244 | 12059 | 4800
500108017 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BTCYL | DZ8222 Cylinder Blade Tilt L/H | 25244 | 12059 | 4800
500108016 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BLCYR | DZ8222 Cylinder Blade Lift R/H | 25244 | 890 | 4800
500108015 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCYL-BLCYL | DZ8222 Cylinder Blade Lift L/H | 25244 | 890 | 4800
500108014 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCVL | DZ8222 Implement Valves Hydraulic | 25244 | 25244 | 4800
500108013 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCON | DZ8222 Implement Control Hydraulic | 25244 | 25244 | 4800
500108012 | CLB-MP-DOZR-DZ8222-HYDSYS-HDCFM | DZ8222 Fan Cooling Motor Hydraulic | 25244 | 10526 | 4800
500108011 | CLB-MP-DOZR-DZ8222-GRSYST-GRINJ | DZ8222 Auto Lube Injectors | 25244 | 25244 | 4800
500108010 | CLB-MP-DOZR-DZ8222-GRSYST-ALBPP | DZ8222 Auto Lube Pump | 25244 | 25244 | 4800
500108009 | CLB-MP-DOZR-DZ8222-FRSUPP | DZ8222 Fire Suppression System | 25244 | 25244 | 4800
500108008 | CLB-MP-DOZR-DZ8222-FDRSYS-TRKRH | DZ8222 Track Assembly R/H | 25244 | 5453 | 4800
500108007 | CLB-MP-DOZR-DZ8222-FDRSYS-TRKLH | DZ8222 Track Assembly L/H | 25244 | 5453 | 4800
500108006 | CLB-MP-DOZR-DZ8222-FDRSYS-SEGRH | DZ8222 Segments R/H | 25244 | 25244 | 4800
500108005 | CLB-MP-DOZR-DZ8222-FDRSYS-SEGLH | DZ8222 Segments L/H | 25244 | 25244 | 4800
500108004 | CLB-MP-DOZR-DZ8222-FDRSYS-FDRRH | DZ8222 Final Drive R/H | 25244 | 2571 | 4800
500108003 | CLB-MP-DOZR-DZ8222-FDRSYS-FDRLH | DZ8222 Final Drive L/H | 25207 | 10526 | 4800
500108002 | CLB-MP-DOZR-DZ8222-ENGINE-LUBSY-PREPP | DZ8222 Oil Pump Pre-Lube Engine | 25244 | 25244 | 4800
500108001 | CLB-MP-DOZR-DZ8222-ENGINE-LUBSY-OILPP | DZ8222 Oil Pump Engine | 25244 | 25244 | 4800
500108000 | CLB-MP-DOZR-DZ8222-ENGINE-LUBSY-ENOLC | DZ8222 Oil Cooler Engine | 25244 | 25244 | 4800
500107999 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-TBORH | DZ8222 Turbocharger R/H | 25244 | 9140 | 4800
500107998 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-TBOLH | DZ8222 Turbocharger L/H | 25244 | 9140 | 4800
500107997 | CLB-MP-DOZR-DZ8222-ENGINE-INTEX-AFTER | DZ8222 Aftercooler | 25244 | 12059 | 4800
500107996 | CLB-MP-DOZR-DZ8222-ENGINE-FUSYS-FULTP | DZ8222 Fuel Transfer Pump | 25244 | 9140 | 4800
500107995 | CLB-MP-DOZR-DZ8222-ENGINE-FUSYS-FUINJ | DZ8222 Fuel Injectors | 25244 | 9140 | 4800
500107994 | CLB-MP-DOZR-DZ8222-ENGINE-COSYS-WTRPP | DZ8222 Water Pump Engine | 25244 | 9140 | 4800
500107993 | CLB-MP-DOZR-DZ8222-ENGINE-COSYS-THERM | DZ8222 Thermostats/Regulators | 25244 | 9140 | 4800
500107992 | CLB-MP-DOZR-DZ8222-ENGINE-COSYS-RADTR | DZ8222 Radiator Engine | 25244 | 1687 | 4800
500107991 | CLB-MP-DOZR-DZ8222-ENGINE-COSYS-COFAN | DZ8222 Fan Cooling System | 25244 | 25244 | 4800
500107990 | CLB-MP-DOZR-DZ8222-ENGINE | DZ8222 Engine Assembly Caterpillar C27 | 25244 | 16002 | 4800
500107989 | CLB-MP-DOZR-DZ8222-ELCTLV-START-STRMR | DZ8222 Starter Motor | 25244 | 9140 | 4800
500107988 | CLB-MP-DOZR-DZ8222-ELCTLV-CHARG-BATTY | DZ8222 Batteries | 25244 | 13938 | 4800
500107987 | CLB-MP-DOZR-DZ8222-ELCTLV-CHARG-ALTER | DZ8222 Alternator 24V | 25244 | 9140 | 4800
500107986 | CLB-MP-DOZR-DZ8222-BRKSTR-STVLV | DZ8222 Valve Hydraulic Steering | 25244 | 25244 | 4800
500107985 | CLB-MP-DOZR-DZ8222-BRKSTR-SCABR | DZ8222 Steering Clutch & Brake Assy R/H | 25244 | 12059 | 4800
500107984 | CLB-MP-DOZR-DZ8222-BRKSTR-SCABL | DZ8222 Steering Clutch & Brake Assy L/H | 25244 | 12059 | 4800
500107983 | CLB-MP-DOZR-DZ8222-BRKSTR-HYSPP | DZ8222 Pump Hydraulic Steering | 25244 | 25244 | 4800
500107982 | CLB-MP-DOZR-DZ8222 | DZ8222 Lubrication & Mechanical Services | 25244 | 11018 | 4800
500107981 | CLB-MP-DOZR-DZ8222 | DZ8222 Caterpillar D10T2 Dozer | 25244 | 25244 | 4800
500066132 | CLB-MP-DOZR-DZX025-STRUCT-PNLGU | Panels and Guards | 66960 | 10306 | 4400
500066127 | CLB-MP-DOZR-DZX025-HYDSYS-HDTNK | Tank Hydraulic | 66960 | 10306 | 4400
500056911 | CLB-MP-DOZR-DZX025-STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 66960 | 66960 | 4400
500056910 | CLB-MP-DOZR-DZX025-STRUCT-RIPPR | Ripper | 66960 | 10306 | 4400
500056907 | CLB-MP-DOZR-DZX025-STRUCT-BLADE | Blade | 66960 | 66960 | 4400
500056906 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 66960 | 66960 | 4400
500056905 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 66960 | 66960 | 4400
500056904 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 66960 | 66960 | 4400
500056903 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 66960 | 66960 | 4400
500056902 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 66960 | 16249 | 4400
500056901 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-IDRHF | Idler Track R/H Front | 66960 | 34698 | 4400
500056900 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-ADJRH | Track Adjuster R/H | 66960 | 66960 | 4400
500056899 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-TKFRR | Track Frame R/H | 66960 | 39919 | 4400
500056898 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 66960 | 15033 | 4400
500056897 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-IDLHF | Idler Track L/H Front | 66960 | 14198 | 4400
500056896 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-ADJLH | Track Adjuster L/H | 66960 | 66960 | 4400
500056895 | CLB-MP-DOZR-DZX025-STRUCT-UNDER-TKFRL | Track Frame L/H | 66960 | 39919 | 4400
500056894 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-TRNON | Trunnion | 66960 | 66960 | 4400
500056893 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-LNKGE | Link Stabiliser | 66960 | 66960 | 4400
500056892 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-PUARM | Push Arms RH | 66960 | 66960 | 4400
500056891 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-PUARM | Push Arms LH | 66960 | 66960 | 4400
500056890 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-PIVOT | Pivot Shaft | 66960 | 18368 | 4400
500056889 | CLB-MP-DOZR-DZX025-STRUCT-CHASS-EQUAL | Equaliser Bar | 66960 | 18368 | 4400
500056888 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-SBELT | Seat Belt | 66960 | 66960 | 4400
500056887 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-SEATS | Operators Seat | 66960 | 746 | 4400
500056886 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 66960 | 66960 | 4400
500056885 | CLB-MP-DOZR-DZX025-STRUCT-CABIN-AIRCN | Air Conditioning System | 66960 | 10306 | 4400
500056884 | CLB-MP-DOZR-DZX025-STRUCT-CABIN | Operators Cabin | 66960 | 10306 | 4400
500056883 | CLB-MP-DOZR-DZX025-GRSYST-ALBPP | Auto Lube Pump | 66960 | 66960 | 4400
500056882 | CLB-MP-DOZR-DZX025-GRSYST | Grease Lubrication System | 66960 | 66960 | 4400
500056881 | CLB-MP-DOZR-DZX025-HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 66960 | 5716 | 4400
500056880 | CLB-MP-DOZR-DZX025-HYDSYS-HDOCO | Oil Cooler Hydraulic | 66960 | 10306 | 4400
500056879 | CLB-MP-DOZR-DZX025-HYDSYS-HDHLF | Hydraulic System Hoses lines Fittings | 66960 | 5567 | 4400
500056878 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 66960 | 10306 | 4400
500056877 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-RTCYR | Cylinder Ripper Tilt RH | 66960 | 1079 | 4400
500056876 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-RTCYL | Cylinder Ripper Tilt LH | 66960 | 10306 | 4400
500056875 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 66948 | 10306 | 4400
500056874 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 66960 | 3279 | 4400
500056873 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 66960 | 2154 | 4400
500056872 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 66960 | 3955 | 4400
500056871 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 66960 | 4973 | 4400
500056870 | CLB-MP-DOZR-DZX025-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 66960 | 3603 | 4400
500056869 | CLB-MP-DOZR-DZX025-HYDSYS-HDCON | Implement Control Hydraulic | 66960 | 66960 | 4400
500056868 | CLB-MP-DOZR-DZX025-HYDSYS-HDCVL | Implement Valves Hydraulic | 66960 | 10306 | 4400
500056867 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 66960 | 5716 | 4400
500056866 | CLB-MP-DOZR-DZX025-HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 66960 | 10306 | 4400
500056865 | CLB-MP-DOZR-DZX025-BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 66960 | 11981 | 4400
500056864 | CLB-MP-DOZR-DZX025-BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 66960 | 10306 | 4400
500056863 | CLB-MP-DOZR-DZX025-BRKSTR-STVLV | Valve Hydraulic Steering | 66960 | 4189 | 4400
500056862 | CLB-MP-DOZR-DZX025-FDRSYS-TRKRH | Track Assembly R/H | 66936 | 1282 | 4400
500056861 | CLB-MP-DOZR-DZX025-FDRSYS-SEGRH | Segments R/H | 66960 | 66960 | 4400
500056860 | CLB-MP-DOZR-DZX025-FDRSYS-FDRRH | Final Drive R/H | 66960 | 10306 | 4400
500056859 | CLB-MP-DOZR-DZX025-FDRSYS-TRKLH | Track Assembly L/H | 66960 | 1282 | 4400
500056858 | CLB-MP-DOZR-DZX025-FDRSYS-SEGLH | Segments L/H | 66960 | 66960 | 4400
500056857 | CLB-MP-DOZR-DZX025-FDRSYS-FDRLH | Final Drive L/H | 66960 | 10306 | 4400
500056856 | CLB-MP-DOZR-DZX025-TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 66960 | 10306 | 4400
500056855 | CLB-MP-DOZR-DZX025-TRNSYS-TROLC | Oil Cooler Transmission | 66960 | 10306 | 4400
500056854 | CLB-MP-DOZR-DZX025-TRNSYS-TRANS-BEVEL | Bevel Gear | 66960 | 10306 | 4400
500056853 | CLB-MP-DOZR-DZX025-TRNSYS-TRANS | Transmission | 66960 | 10306 | 4400
500056852 | CLB-MP-DOZR-DZX025-TRNSYS-TRQUE | Torque Converter | 66960 | 3862 | 4400
500056851 | CLB-MP-DOZR-DZX025-TRNSYS | Transmission Drive Line | 66960 | 13608 | 4400
500056850 | CLB-MP-DOZR-DZX025-ELCTLV-START-STMUP | Starter Motor R/H | 66960 | 1289 | 4400
500056849 | CLB-MP-DOZR-DZX025-ELCTLV-START-STMLO | Starter Motor L/H | 66960 | 1289 | 4400
500056848 | CLB-MP-DOZR-DZX025-ELCTLV-CHARG-ALTER | Alternator 24V | 66960 | 1289 | 4400
500056847 | CLB-MP-DOZR-DZX025-ENGINE-FUSYS-FUINJ | Fuel Injectors | 66960 | 1289 | 4400
500056846 | CLB-MP-DOZR-DZX025-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 66960 | 1289 | 4400
500056845 | CLB-MP-DOZR-DZX025-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 66960 | 1289 | 4400
500056844 | CLB-MP-DOZR-DZX025-ENGINE-INTEX-AFTER | Aftercooler | 66960 | 3002 | 4400
500056843 | CLB-MP-DOZR-DZX025-ENGINE-INTEX-TBORH | Turbocharger R/H | 66960 | 1289 | 4400
500056842 | CLB-MP-DOZR-DZX025-ENGINE-INTEX-TBOLH | Turbocharger L/H | 66960 | 1289 | 4400
500056841 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-THERM | Thermostats/Regulators | 66960 | 1289 | 4400
500056840 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-COFAN | Fan Cooling System | 66960 | 66960 | 4400
500056839 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-RADTR | Radiator Coolant | 66960 | 24511 | 5100
500056838 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-RADTR | Radiator Engine | 66960 | 10306 | 4400
500056837 | CLB-MP-DOZR-DZX025-ENGINE-COSYS-WTRPP | Water Pump Engine | 66960 | 1289 | 4400
500056836 | CLB-MP-DOZR-DZX025-ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 66960 | 1289 | 4400
500056835 | CLB-MP-DOZR-DZX025-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 66960 | 1289 | 4400
500056834 | CLB-MP-DOZR-DZX025-ENGINE-LUBSY-OILPP | Oil Pump Engine | 66960 | 1289 | 4400
500056832 | CLB-MP-DOZR-DZX025-ENGINE | Engine Assembly Caterpillar C32 | 66960 | 1289 | 4400
500053546 | CLB-MP-DOZR-DZX025 | DZX025 Lube & Mechanical Services | 66960 | 66960 | 4400
500053545 | CLB-MP-DOZR-DZX025 | Caterpillar D11T Dozer, DZX025 | 66960 | 66960 | 4400
500066131 | CLB-MP-DOZR-DZX024-STRUCT-PNLGU | Panels and Guards | 61520 | 4630 | 4400
500066126 | CLB-MP-DOZR-DZX024-HYDSYS-HDTNK | Tank Hydraulic | 61520 | 4630 | 4400
500056831 | CLB-MP-DOZR-DZX024-STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 61520 | 61520 | 4400
500056830 | CLB-MP-DOZR-DZX024-STRUCT-RIPPR | Ripper | 61520 | 4630 | 4400
500056827 | CLB-MP-DOZR-DZX024-STRUCT-BLADE | Blade | 61520 | 1824 | 4400
500056826 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 61520 | 61520 | 4400
500056825 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 61520 | 61520 | 4400
500056824 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 61520 | 61520 | 4400
500056823 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 61520 | 61520 | 4400
500056822 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 61520 | 19379 | 4400
500056821 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-IDRHF | Idler Track R/H Front | 61520 | 19969 | 4400
500056820 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-ADJRH | Track Adjuster R/H | 61520 | 61520 | 4400
500056819 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-TKFRR | Track Frame R/H | 61520 | 5385 | 4400
500056818 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 61520 | 19379 | 4400
500056817 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-IDLHF | Idler Track L/H Front | 61520 | 19969 | 4400
500056816 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-ADJLH | Track Adjuster L/H | 61520 | 61520 | 4400
500056815 | CLB-MP-DOZR-DZX024-STRUCT-UNDER-TKFRL | Track Frame L/H | 61520 | 5385 | 4400
500056814 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-TRNON | Trunnion | 61520 | 61520 | 4400
500056813 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-LNKGE | Link Stabiliser | 61520 | 61520 | 4400
500056812 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-PUARM | Push Arms RH | 61520 | 61520 | 4400
500056811 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-PUARM | Push Arms LH | 61520 | 61520 | 4400
500056810 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-PIVOT | Pivot Shaft | 61520 | 4630 | 4400
500056809 | CLB-MP-DOZR-DZX024-STRUCT-CHASS-EQUAL | Equaliser Bar | 61520 | 4630 | 4400
500056808 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-SBELT | Seat Belt | 61520 | 61520 | 4400
500056807 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-SEATS | Operators Seat | 61520 | 7488 | 4400
500056806 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 61520 | 61520 | 4400
500056805 | CLB-MP-DOZR-DZX024-STRUCT-CABIN-AIRCN | Air Conditioning System | 61520 | 4630 | 4400
500056804 | CLB-MP-DOZR-DZX024-STRUCT-CABIN | Operators Cabin | 61520 | 4630 | 4400
500056803 | CLB-MP-DOZR-DZX024-GRSYST-ALBPP | Auto Lube Pump | 61520 | 61520 | 4400
500056802 | CLB-MP-DOZR-DZX024-GRSYST | Grease Lubrication System | 61520 | 61520 | 4400
500056801 | CLB-MP-DOZR-DZX024-HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 61520 | 4630 | 4400
500056800 | CLB-MP-DOZR-DZX024-HYDSYS-HDOCO | Oil Cooler Hydraulic | 61520 | 1359 | 4400
500056799 | CLB-MP-DOZR-DZX024-HYDSYS-HDHLF | Hydraulic System Hoses lines Fittings | 61520 | 30398 | 4400
500056798 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 61520 | 61520 | 4400
500056797 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-RTCYR | Cylinder Ripper Tilt RH | 61520 | 5384 | 4400
500056796 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-RTCYL | Cylinder Ripper Tilt L/H | 61520 | 5812 | 4400
500056795 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 61520 | 463 | 4400
500056794 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 61520 | 4630 | 4400
500056793 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 61520 | 4630 | 4400
500056792 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 61520 | 463 | 4400
500056791 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 61520 | 1034 | 4400
500056790 | CLB-MP-DOZR-DZX024-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 61520 | 1527 | 4400
500056789 | CLB-MP-DOZR-DZX024-HYDSYS-HDCON | Implement Control Hydraulic | 61520 | 61520 | 4400
500056788 | CLB-MP-DOZR-DZX024-HYDSYS-HDCVL | Implement Valves Hydraulic | 61520 | 4630 | 4400
500056787 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 61520 | 4630 | 4400
500056786 | CLB-MP-DOZR-DZX024-HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 61520 | 5812 | 4400
500056785 | CLB-MP-DOZR-DZX024-BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 61520 | 4630 | 4400
500056784 | CLB-MP-DOZR-DZX024-BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 61516 | 4630 | 4400
500056783 | CLB-MP-DOZR-DZX024-BRKSTR-STVLV | Valve Hydraulic Steering | 61520 | 10101 | 4400
500056782 | CLB-MP-DOZR-DZX024-FDRSYS-TRKRH | Track Assembly R/H | 61520 | 3184 | 4400
500056781 | CLB-MP-DOZR-DZX024-FDRSYS-SEGRH | Segments R/H | 61520 | 61520 | 4400
500056780 | CLB-MP-DOZR-DZX024-FDRSYS-FDRRH | Final Drive R/H | 61520 | 4630 | 4400
500056779 | CLB-MP-DOZR-DZX024-FDRSYS-TRKLH | Track Assembly L/H | 61520 | 3184 | 4400
500056778 | CLB-MP-DOZR-DZX024-FDRSYS-SEGLH | Segments L/H | 61520 | 61520 | 4400
500056777 | CLB-MP-DOZR-DZX024-FDRSYS-FDRLH | Final Drive L/H | 61520 | 5385 | 4400
500056776 | CLB-MP-DOZR-DZX024-TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 61520 | 4630 | 4400
500056775 | CLB-MP-DOZR-DZX024-TRNSYS-TROLC | Oil Cooler Transmission | 61520 | 4630 | 4400
500056774 | CLB-MP-DOZR-DZX024-TRNSYS-TRANS-BEVEL | Bevel Gear | 61520 | 4630 | 4400
500056773 | CLB-MP-DOZR-DZX024-TRNSYS-TRANS | Transmission | 61520 | 4630 | 4400
500056772 | CLB-MP-DOZR-DZX024-TRNSYS-TRQUE | Torque Converter | 61520 | 4630 | 4400
500056771 | CLB-MP-DOZR-DZX024-TRNSYS | Transmission Drive Line | 61520 | 16252 | 4400
500056770 | CLB-MP-DOZR-DZX024-ELCTLV-START-STMUP | Starter Motor R/H | 61520 | 4630 | 4400
500056769 | CLB-MP-DOZR-DZX024-ELCTLV-START-STMLO | Starter Motor L/H | 61520 | 4630 | 4400
500056768 | CLB-MP-DOZR-DZX024-ELCTLV-CHARG-ALTER | Alternator 24V | 61520 | 4630 | 4400
500056767 | CLB-MP-DOZR-DZX024-ENGINE-FUSYS-FUINJ | Fuel Injectors | 61520 | 4630 | 4400
500056766 | CLB-MP-DOZR-DZX024-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 61520 | 4630 | 4400
500056765 | CLB-MP-DOZR-DZX024-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 61520 | 4630 | 4400
500056764 | CLB-MP-DOZR-DZX024-ENGINE-INTEX-AFTER | Aftercooler | 61520 | 4630 | 4400
500056763 | CLB-MP-DOZR-DZX024-ENGINE-INTEX-TBORH | Turbocharger R/H | 61520 | 4630 | 4400
500056762 | CLB-MP-DOZR-DZX024-ENGINE-INTEX-TBOLH | Turbocharger L/H | 61520 | 4630 | 4400
500056761 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-THERM | Thermostats/Regulators | 61520 | 4630 | 4400
500056760 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-COFAN | Fan Cooling System | 61520 | 61520 | 4400
500056759 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-RADTR | Radiator Coolant | 61520 | 16252 | 2000
500056758 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-RADTR | Radiator Engine | 61520 | 4630 | 4400
500056757 | CLB-MP-DOZR-DZX024-ENGINE-COSYS-WTRPP | Water Pump Engine | 61520 | 4630 | 4400
500056756 | CLB-MP-DOZR-DZX024-ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 61520 | 4630 | 4400
500056755 | CLB-MP-DOZR-DZX024-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 61520 | 4630 | 4400
500056754 | CLB-MP-DOZR-DZX024-ENGINE-LUBSY-OILPP | Oil Pump Engine | 61520 | 4630 | 4400
500056752 | CLB-MP-DOZR-DZX024-ENGINE | Engine Assembly Caterpillar C32 | 61520 | 4630 | 4400
500053544 | CLB-MP-DOZR-DZX024 | DZX024 Lube & Mechanical Services | 61529 | 61529 | 4400
500053543 | CLB-MP-DOZR-DZX024 | Caterpillar D11T Dozer, DZX024 | 61520 | 61520 | 4400
500066130 | CLB-MP-DOZR-DZX023-STRUCT-PNLGU | Panels and Guards | 59280 | 9271 | 4400
500066125 | CLB-MP-DOZR-DZX023-HYDSYS-HDTNK | Tank Hydraulic | 59280 | 9271 | 4400
500056751 | CLB-MP-DOZR-DZX023-STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 59280 | 59280 | 4400
500056750 | CLB-MP-DOZR-DZX023-STRUCT-RIPPR | Ripper | 59280 | 59280 | 4400
500056747 | CLB-MP-DOZR-DZX023-STRUCT-BLADE | Blade | 59280 | 9271 | 4400
500056746 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 59280 | 59280 | 4400
500056745 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 59280 | 59280 | 4400
500056744 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 59280 | 59280 | 4400
500056743 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 59280 | 59280 | 4400
500056742 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 59280 | 20330 | 4400
500056741 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-IDRHF | Idler Track R/H Front | 59280 | 20848 | 4400
500056740 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-ADJRH | Track Adjuster R/H | 59280 | 59280 | 4400
500056739 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-TKFRR | Track Frame R/H | 59280 | 9271 | 4400
500056738 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 59280 | 16486 | 4400
500056737 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-IDLHF | Idler Track L/H Front | 59280 | 21053 | 4400
500056736 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-ADJLH | Track Adjuster L/H | 59280 | 59280 | 4400
500056735 | CLB-MP-DOZR-DZX023-STRUCT-UNDER-TKFRL | Track Frame L/H | 59280 | 9271 | 4400
500056734 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-TRNON | Trunnion | 59280 | 59280 | 4400
500056733 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-LNKGE | Link Stabiliser | 59280 | 59280 | 4400
500056732 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-PUARM | Push Arms RH | 59280 | 59280 | 4400
500056731 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-PUARM | Push Arms LH | 59280 | 59280 | 4400
500056730 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-PIVOT | Pivot Shaft | 59280 | 9271 | 4400
500056729 | CLB-MP-DOZR-DZX023-STRUCT-CHASS-EQUAL | Equaliser Bar | 59280 | 9271 | 4400
500056728 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-SBELT | Seat Belt | 59280 | 59280 | 4400
500056727 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-SEATS | Operators Seat | 59280 | 1992 | 4400
500056726 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 59280 | 59280 | 4400
500056725 | CLB-MP-DOZR-DZX023-STRUCT-CABIN-AIRCN | Air Conditioning System | 59280 | 1992 | 4400
500056724 | CLB-MP-DOZR-DZX023-STRUCT-CABIN | Operators Cabin | 59280 | 9271 | 4400
500056723 | CLB-MP-DOZR-DZX023-GRSYST-ALBPP | Auto Lube Pump | 59280 | 59280 | 4400
500056722 | CLB-MP-DOZR-DZX023-GRSYST | Grease Lubrication System | 59280 | 59280 | 4400
500056721 | CLB-MP-DOZR-DZX023-HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 59280 | 1992 | 4400
500056720 | CLB-MP-DOZR-DZX023-HYDSYS-HDOCO | Oil Cooler Hydraulic | 59280 | 1992 | 4400
500056719 | CLB-MP-DOZR-DZX023-HYDSYS-HDHLF | Hydraulic System Hoses lines Fittings | 59280 | 49258 | 4400
500056718 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 59280 | 59280 | 4400
500056717 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-RTCYR | Cylinder Ripper Tilt RH | 59280 | 10596 | 4400
500056716 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-RTCYL | Cylinder Ripper Tilt L/H | 59280 | 9271 | 4400
500056715 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 59280 | 11103 | 4400
500056714 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 59280 | 9271 | 4400
500056713 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 59280 | 20330 | 4400
500056712 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 59280 | 14468 | 4400
500056711 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 59280 | 9271 | 4400
500056710 | CLB-MP-DOZR-DZX023-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 59280 | 246 | 4400
500056709 | CLB-MP-DOZR-DZX023-HYDSYS-HDCON | Implement Control Hydraulic | 59280 | 59280 | 4400
500056708 | CLB-MP-DOZR-DZX023-HYDSYS-HDCVL | Implement Valves Hydraulic | 59280 | 1992 | 4400
500056707 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 59280 | 1992 | 4400
500056706 | CLB-MP-DOZR-DZX023-HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 59280 | 9271 | 4400
500056705 | CLB-MP-DOZR-DZX023-BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 59280 | 9271 | 4400
500056704 | CLB-MP-DOZR-DZX023-BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 59280 | 9271 | 4400
500056703 | CLB-MP-DOZR-DZX023-BRKSTR-STVLV | Valve Hydraulic Steering | 59280 | 9271 | 4400
500056702 | CLB-MP-DOZR-DZX023-FDRSYS-TRKRH | Track Assembly R/H | 59280 | 3752 | 4400
500056701 | CLB-MP-DOZR-DZX023-FDRSYS-SEGRH | Segments R/H | 59280 | 59280 | 4400
500056700 | CLB-MP-DOZR-DZX023-FDRSYS-FDRRH | Final Drive R/H | 59280 | 8033 | 4400
500056699 | CLB-MP-DOZR-DZX023-FDRSYS-TRKLH | Track Assembly L/H | 59280 | 3752 | 4400
500056698 | CLB-MP-DOZR-DZX023-FDRSYS-SEGLH | Segments L/H | 59280 | 59280 | 4400
500056697 | CLB-MP-DOZR-DZX023-FDRSYS-FDRLH | Final Drive L/H | 59280 | 9271 | 4400
500056696 | CLB-MP-DOZR-DZX023-TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 59280 | 9271 | 4400
500056695 | CLB-MP-DOZR-DZX023-TRNSYS-TROLC | Oil Cooler Transmission | 59280 | 9271 | 4400
500056694 | CLB-MP-DOZR-DZX023-TRNSYS-TRANS-BEVEL | Bevel Gear | 59280 | 9271 | 4400
500056693 | CLB-MP-DOZR-DZX023-TRNSYS-TRANS | Transmission | 59280 | 1986 | 4400
500056692 | CLB-MP-DOZR-DZX023-TRNSYS-TRQUE | Torque Converter | 59280 | 9271 | 4400
500056691 | CLB-MP-DOZR-DZX023-TRNSYS | Transmission Drive Line | 59280 | 9271 | 4400
500056690 | CLB-MP-DOZR-DZX023-ELCTLV-START-STMUP | Starter Motor R/H | 59280 | 1992 | 4400
500056689 | CLB-MP-DOZR-DZX023-ELCTLV-START-STMLO | Starter Motor L/H | 59280 | 1992 | 4400
500056688 | CLB-MP-DOZR-DZX023-ELCTLV-CHARG-ALTER | Alternator 24V | 59280 | 1992 | 4400
500056687 | CLB-MP-DOZR-DZX023-ENGINE-FUSYS-FUINJ | Fuel Injectors | 59280 | 1992 | 4400
500056686 | CLB-MP-DOZR-DZX023-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 59280 | 1992 | 4400
500056685 | CLB-MP-DOZR-DZX023-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 59280 | 1992 | 4400
500056684 | CLB-MP-DOZR-DZX023-ENGINE-INTEX-AFTER | Aftercooler | 59280 | 9271 | 4400
500056683 | CLB-MP-DOZR-DZX023-ENGINE-INTEX-TBORH | Turbocharger R/H | 59280 | 1992 | 4400
500056682 | CLB-MP-DOZR-DZX023-ENGINE-INTEX-TBOLH | Turbocharger L/H | 59280 | 1992 | 4400
500056681 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-THERM | Thermostats/Regulators | 59280 | 1992 | 4400
500056680 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-COFAN | Fan Cooling System | 59280 | 31668 | 4400
500056679 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-RADTR | Radiator Coolant | 59280 | 9271 | 5100
500056678 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-RADTR | Radiator Engine | 59280 | 9271 | 4400
500056677 | CLB-MP-DOZR-DZX023-ENGINE-COSYS-WTRPP | Water Pump Engine | 59280 | 1992 | 4400
500056676 | CLB-MP-DOZR-DZX023-ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 59280 | 1992 | 4400
500056675 | CLB-MP-DOZR-DZX023-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 59280 | 1992 | 4400
500056674 | CLB-MP-DOZR-DZX023-ENGINE-LUBSY-OILPP | Oil Pump Engine | 59280 | 1992 | 4400
500056672 | CLB-MP-DOZR-DZX023-ENGINE | Engine Assembly Caterpillar C32 | 59280 | 1992 | 4400
500053542 | CLB-MP-DOZR-DZX023 | DZX023 Lube & Mechanical Services | 59280 | 59280 | 4400
500053541 | CLB-MP-DOZR-DZX023 | Caterpillar D11T Dozer, DZX023 | 59280 | 59280 | 4400
500159028 | CLB-MP-DOZR-DZX022-CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 63346 | 6444 | 4400
500066129 | CLB-MP-DOZR-DZX022-STRUCT-PNLGU | Panels and Guards | 63346 | 6444 | 4400
500066124 | CLB-MP-DOZR-DZX022-HYDSYS-HDTNK | Tank Hydraulic | 63346 | 6444 | 4400
500056671 | CLB-MP-DOZR-DZX022-STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 63346 | 63346 | 4400
500056670 | CLB-MP-DOZR-DZX022-STRUCT-RIPPR | Ripper | 63346 | 36250 | 4400
500056667 | CLB-MP-DOZR-DZX022-STRUCT-BLADE | Blade | 63346 | 175 | 4400
500056666 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 63346 | 63346 | 4400
500056665 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 63346 | 63346 | 4400
500056664 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 63346 | 63346 | 4400
500056663 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 63346 | 63346 | 4400
500056662 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 63346 | 22577 | 4400
500056661 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-IDRHF | Idler Track R/H Front | 63346 | 27100 | 4400
500056660 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-ADJRH | Track Adjuster R/H | 63346 | 63346 | 4400
500056659 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-TKFRR | Track Frame R/H | 63346 | 6444 | 4400
500056658 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 63346 | 4376 | 4400
500056657 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-IDLHF | Idler Track L/H Front | 63346 | 27100 | 4400
500056656 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-ADJLH | Track Adjuster L/H | 63346 | 63346 | 4400
500056655 | CLB-MP-DOZR-DZX022-STRUCT-UNDER-TKFRL | Track Frame L/H | 63346 | 6444 | 4400
500056654 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-TRNON | Trunnion | 63346 | 63346 | 4400
500056653 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-LNKGE | Link Stabiliser | 63346 | 63346 | 4400
500056652 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-PUARM | Push Arms RH | 63346 | 63346 | 4400
500056651 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-PUARM | Push Arms LH | 63346 | 63346 | 4400
500056650 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-PIVOT | Pivot Shaft | 63346 | 4376 | 4400
500056649 | CLB-MP-DOZR-DZX022-STRUCT-CHASS-EQUAL | Equaliser Bar | 63346 | 6717 | 4400
500056648 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-SBELT | Seat Belt | 63346 | 63346 | 4400
500056647 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-SEATS | Operators Seat | 63346 | 6444 | 4400
500056646 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 63346 | 63346 | 4400
500056645 | CLB-MP-DOZR-DZX022-STRUCT-CABIN-AIRCN | Air Conditioning System | 63346 | 6444 | 4400
500056644 | CLB-MP-DOZR-DZX022-STRUCT-CABIN | Operators Cabin | 63346 | 6444 | 4400
500056643 | CLB-MP-DOZR-DZX022-GRSYST-ALBPP | Auto Lube Pump | 63346 | 63346 | 4400
500056642 | CLB-MP-DOZR-DZX022-GRSYST | Grease Lubrication System | 63346 | 63346 | 4400
500056641 | CLB-MP-DOZR-DZX022-HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 63346 | 6444 | 4400
500056640 | CLB-MP-DOZR-DZX022-HYDSYS-HDOCO | Oil Cooler Hydraulic | 63346 | 6444 | 4400
500056639 | CLB-MP-DOZR-DZX022-HYDSYS-HDHLF | Hydraulic System Hoses lines Fittings | 63346 | 20095 | 4400
500056638 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 63346 | 63346 | 4400
500056637 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-RTCYR | Cylinder Ripper Tilt RH | 63346 | 6444 | 4400
500056636 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-RTCYL | Cylinder Ripper Tilt L/H | 63346 | 6444 | 4400
500056635 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 63346 | 6444 | 4400
500056634 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 63346 | 24655 | 4400
500056633 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 63346 | 175 | 4400
500056632 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 63346 | 175 | 4400
500056631 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 63346 | 17244 | 4400
500056630 | CLB-MP-DOZR-DZX022-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 63346 | 4223 | 4400
500056629 | CLB-MP-DOZR-DZX022-HYDSYS-HDCON | Implement Control Hydraulic | 63346 | 63346 | 4400
500056628 | CLB-MP-DOZR-DZX022-HYDSYS-HDCVL | Implement Valves Hydraulic | 63346 | 6444 | 4400
500056627 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 63346 | 9901 | 4400
500056626 | CLB-MP-DOZR-DZX022-HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 63346 | 7741 | 4400
500056625 | CLB-MP-DOZR-DZX022-BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 63346 | 14380 | 4400
500056624 | CLB-MP-DOZR-DZX022-BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 63346 | 14380 | 4400
500056623 | CLB-MP-DOZR-DZX022-BRKSTR-STVLV | Valve Hydraulic Steering | 63346 | 548 | 4400
500056622 | CLB-MP-DOZR-DZX022-FDRSYS-TRKRH | Track Assembly R/H | 63346 | 4376 | 4400
500056621 | CLB-MP-DOZR-DZX022-FDRSYS-SEGRH | Segments R/H | 63346 | 49086 | 4400
500056620 | CLB-MP-DOZR-DZX022-FDRSYS-FDRRH | Final Drive R/H | 63346 | 4882 | 4400
500056619 | CLB-MP-DOZR-DZX022-FDRSYS-TRKLH | Track Assembly L/H | 63346 | 4376 | 4400
500056618 | CLB-MP-DOZR-DZX022-FDRSYS-SEGLH | Segments L/H | 63346 | 49086 | 4400
500056617 | CLB-MP-DOZR-DZX022-FDRSYS-FDRLH | Final Drive L/H | 63346 | 8101 | 4400
500056616 | CLB-MP-DOZR-DZX022-TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 63346 | 6444 | 4400
500056615 | CLB-MP-DOZR-DZX022-TRNSYS-TROLC | Oil Cooler Transmission | 63346 | 6444 | 4400
500056614 | CLB-MP-DOZR-DZX022-TRNSYS-TRANS-BEVEL | Bevel Gear | 63346 | 6444 | 4400
500056613 | CLB-MP-DOZR-DZX022-TRNSYS-TRANS | Transmission | 63346 | 6444 | 4400
500056612 | CLB-MP-DOZR-DZX022-TRNSYS-TRQUE | Torque Converter | 63346 | 6444 | 4400
500056611 | CLB-MP-DOZR-DZX022-TRNSYS | Transmission Drive Line | 63346 | 6444 | 4400
500056610 | CLB-MP-DOZR-DZX022-ELCTLV-START-STMUP | Starter Motor R/H | 63346 | 175 | 4400
500056609 | CLB-MP-DOZR-DZX022-ELCTLV-START-STMLO | Starter Motor L/H | 63346 | 175 | 4400
500056608 | CLB-MP-DOZR-DZX022-ELCTLV-CHARG-ALTER | Alternator 24V | 63346 | 175 | 4400
500056607 | CLB-MP-DOZR-DZX022-ENGINE-FUSYS-FUINJ | Fuel Injectors | 63346 | 175 | 4400
500056606 | CLB-MP-DOZR-DZX022-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 63346 | 175 | 4400
500056605 | CLB-MP-DOZR-DZX022-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 63346 | 175 | 4400
500056604 | CLB-MP-DOZR-DZX022-ENGINE-INTEX-AFTER | Aftercooler | 63346 | 17518 | 4400
500056603 | CLB-MP-DOZR-DZX022-ENGINE-INTEX-TBORH | Turbocharger R/H | 63346 | 175 | 4400
500056602 | CLB-MP-DOZR-DZX022-ENGINE-INTEX-TBOLH | Turbocharger L/H | 63346 | 175 | 4400
500056601 | CLB-MP-DOZR-DZX022-ENGINE-COSYS-THERM | Thermostats/Regulators | 63346 | 175 | 4400
500056600 | CLB-MP-DOZR-DZX022-ENGINE-COSYS-COFAN | Fan Cooling System | 63346 | 20095 | 4400
500056599 | CLB-MP-DOZR-DZX022-ENGINE-COSYS-RADTR | Radiator Coolant | 63346 | 20095 | 5100
500056598 | CLB-MP-DOZR-DZX022-ENGINE-COSYS-RADTR | Radiator Engine | 63346 | 175 | 4400
500056597 | CLB-MP-DOZR-DZX022-ENGINE-COSYS-WTRPP | Water Pump Engine | 63346 | 175 | 4400
500056596 | CLB-MP-DOZR-DZX022-ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 63346 | 175 | 4400
500056595 | CLB-MP-DOZR-DZX022-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 63346 | 175 | 4400
500056594 | CLB-MP-DOZR-DZX022-ENGINE-LUBSY-OILPP | Oil Pump Engine | 63346 | 175 | 4400
500056592 | CLB-MP-DOZR-DZX022-ENGINE | Engine Assembly Caterpillar C32 | 63346 | 175 | 4400
500052657 | CLB-MP-DOZR-DZX022 | DZX022 Lube & Mechanical Services | 63346 | 63346 | 4400
500052656 | CLB-MP-DOZR-DZX022 | Caterpillar D11T Dozer, DZX022 | 63346 | 63346 | 4400
500066128 | CLB-MP-DOZR-DZX021-STRUCT-PNLGU | Panels and Guards | 65875 | 228 | 5000
500066123 | CLB-MP-DOZR-DZX021-HYDSYS-HDTNK | Tank Hydraulic | 65875 | 7882 | 5000
500056591 | CLB-MP-DOZR-DZX021-STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 65875 | 65875 | 5000
500056590 | CLB-MP-DOZR-DZX021-STRUCT-RIPPR | Ripper | 65875 | 65875 | 5000
500056587 | CLB-MP-DOZR-DZX021-STRUCT-BLADE | Blade | 65875 | 16002 | 5000
500056586 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 65875 | 65875 | 5000
500056585 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 65875 | 65875 | 5000
500056584 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 65875 | 65875 | 5000
500056583 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 65875 | 65875 | 5000
500056582 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 65875 | 18884 | 5000
500056581 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-IDRHF | Idler Track R/H Front | 65875 | 7882 | 5000
500056580 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-ADJRH | Track Adjuster R/H | 65875 | 65875 | 5000
500056579 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-TKFRR | Track Frame R/H | 65875 | 16847 | 5000
500056578 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 65875 | 5128 | 5000
500056577 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-IDLHF | Idler Track L/H Front | 65875 | 7882 | 5000
500056576 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-ADJLH | Track Adjuster L/H | 65875 | 65875 | 5000
500056575 | CLB-MP-DOZR-DZX021-STRUCT-UNDER-TKFRL | Track Frame L/H | 65875 | 16847 | 5000
500056574 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-TRNON | Trunnion | 65875 | 7882 | 5000
500056573 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-LNKGE | Link Stabiliser | 65875 | 65875 | 5000
500056572 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-PUARM | Push Arms RH | 65875 | 65875 | 5000
500056571 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-PUARM | Push Arms LH | 65875 | 65875 | 5000
500056570 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-PIVOT | Pivot Shaft | 65875 | 23207 | 5000
500056569 | CLB-MP-DOZR-DZX021-STRUCT-CHASS-EQUAL | Equaliser Bar | 65875 | 16847 | 5000
500056568 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-SBELT | Seat Belt | 65875 | 65875 | 5000
500056567 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-SEATS | Operators Seat | 65875 | 228 | 5000
500056566 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 65875 | 65875 | 5000
500056565 | CLB-MP-DOZR-DZX021-STRUCT-CABIN-AIRCN | Air Conditioning System | 65875 | 7882 | 5000
500056564 | CLB-MP-DOZR-DZX021-STRUCT-CABIN | Operators Cabin | 65875 | 7882 | 5000
500056563 | CLB-MP-DOZR-DZX021-GRSYST-ALBPP | Auto Lube Pump | 65875 | 65875 | 5000
500056562 | CLB-MP-DOZR-DZX021-GRSYST | Grease Lubrication System | 65875 | 65875 | 5000
500056561 | CLB-MP-DOZR-DZX021-HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 65875 | 7882 | 5000
500056560 | CLB-MP-DOZR-DZX021-HYDSYS-HDOCO | Oil Cooler Hydraulic | 65875 | 7882 | 5000
500056559 | CLB-MP-DOZR-DZX021-HYDSYS-HDHLF | Hydraulic System Hoses lines Fittings | 65875 | 16002 | 5000
500056558 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 65875 | 65875 | 5000
500056557 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-RTCYR | Cylinder Ripper Tilt RH | 65875 | 7882 | 5000
500056556 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-RTCYL | Cylinder Ripper Tilt L/H | 65875 | 7882 | 5000
500056555 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-RLCYR | Cylinder Ripper Lift R/H | 65875 | 7882 | 5000
500056554 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-RLCYL | Cylinder Ripper Lift L/H | 65875 | 7882 | 5000
500056553 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-BTCYR | Cylinder Blade Tilt R/H | 65875 | 4602 | 5000
500056552 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-BTCYL | Cylinder Blade Tilt L/H | 65875 | 1307 | 5000
500056551 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-BLCYR | Cylinder Blade Lift R/H | 65875 | 34164 | 5000
500056550 | CLB-MP-DOZR-DZX021-HYDSYS-HDCYL-BLCYL | Cylinder Blade Lift L/H | 65875 | 7882 | 5000
500056549 | CLB-MP-DOZR-DZX021-HYDSYS-HDCON | Implement Control Hydraulic | 65875 | 65875 | 5000
500056548 | CLB-MP-DOZR-DZX021-HYDSYS-HDCVL | Implement Valves Hydraulic | 65875 | 7882 | 5000
500056547 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 65875 | 7882 | 5000
500056546 | CLB-MP-DOZR-DZX021-HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 65875 | 7882 | 5000
500056545 | CLB-MP-DOZR-DZX021-BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 65875 | 7882 | 5000
500056544 | CLB-MP-DOZR-DZX021-BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 65875 | 7882 | 5000
500056543 | CLB-MP-DOZR-DZX021-BRKSTR-STVLV | Valve Hydraulic Steering | 65875 | 7882 | 5000
500056542 | CLB-MP-DOZR-DZX021-FDRSYS-TRKRH | Track Assembly R/H | 65875 | 3782 | 5000
500056541 | CLB-MP-DOZR-DZX021-FDRSYS-SEGRH | Segments R/H | 65875 | 65875 | 5000
500056540 | CLB-MP-DOZR-DZX021-FDRSYS-FDRRH | Final Drive R/H | 65875 | 12123 | 5000
500056539 | CLB-MP-DOZR-DZX021-FDRSYS-TRKLH | Track Assembly L/H | 65875 | 3782 | 5000
500056538 | CLB-MP-DOZR-DZX021-FDRSYS-SEGLH | Segments L/H | 65875 | 65875 | 5000
500056537 | CLB-MP-DOZR-DZX021-FDRSYS-FDRLH | Final Drive L/H | 65875 | 7882 | 5000
500056536 | CLB-MP-DOZR-DZX021-TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 65875 | 7882 | 5000
500056535 | CLB-MP-DOZR-DZX021-TRNSYS-TROLC | Oil Cooler Transmission | 65875 | 7882 | 5000
500056534 | CLB-MP-DOZR-DZX021-TRNSYS-TRANS-BEVEL | Bevel Gear | 65875 | 7882 | 5000
500056533 | CLB-MP-DOZR-DZX021-TRNSYS-TRANS | Transmission | 65875 | 7882 | 5000
500056532 | CLB-MP-DOZR-DZX021-TRNSYS-TRQUE | Torque Converter | 65875 | 7882 | 5000
500056531 | CLB-MP-DOZR-DZX021-TRNSYS | Transmission Drive Line | 65875 | 7882 | 5000
500056530 | CLB-MP-DOZR-DZX021-ELCTLV-START-STMUP | Starter Motor R/H | 65875 | 228 | 5000
500056529 | CLB-MP-DOZR-DZX021-ELCTLV-START-STMLO | Starter Motor L/H | 65875 | 228 | 5000
500056528 | CLB-MP-DOZR-DZX021-ELCTLV-CHARG-ALTER | Alternator 24V | 65875 | 228 | 5000
500056527 | CLB-MP-DOZR-DZX021-ENGINE-FUSYS-FUINJ | Fuel Injectors | 65875 | 228 | 5000
500056526 | CLB-MP-DOZR-DZX021-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 65875 | 228 | 5000
500056525 | CLB-MP-DOZR-DZX021-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 65875 | 228 | 5000
500056524 | CLB-MP-DOZR-DZX021-ENGINE-INTEX-AFTER | Aftercooler | 65875 | 7882 | 5000
500056523 | CLB-MP-DOZR-DZX021-ENGINE-INTEX-TBORH | Turbocharger R/H | 65875 | 228 | 5000
500056522 | CLB-MP-DOZR-DZX021-ENGINE-INTEX-TBOLH | Turbocharger L/H | 65875 | 228 | 5000
500056521 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-THERM | Thermostats/Regulators | 65875 | 228 | 5000
500056520 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-COFAN | Fan Cooling System | 65875 | 7882 | 5000
500056519 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-RADTR | Radiator Coolant | 65875 | 7882 | 5100
500056518 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-RADTR | Radiator Engine | 65875 | 7882 | 5000
500056517 | CLB-MP-DOZR-DZX021-ENGINE-COSYS-WTRPP | Water Pump Engine | 65875 | 228 | 5000
500056516 | CLB-MP-DOZR-DZX021-ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 65875 | 7882 | 5000
500056515 | CLB-MP-DOZR-DZX021-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 65875 | 7882 | 5000
500056514 | CLB-MP-DOZR-DZX021-ENGINE-LUBSY-OILPP | Oil Pump Engine | 65875 | 7882 | 5000
500056512 | CLB-MP-DOZR-DZX021-ENGINE | Engine Assembly Caterpillar C32 | 65875 | 7882 | 5000
500052655 | CLB-MP-DOZR-DZX021 | DZX021 Lube & Mechanical Services | 65875 | 65875 | 5000
500052654 | CLB-MP-DOZR-DZX021 | Caterpillar D11T Dozer, DZX021 | 65875 | 65875 | 5000
500156274 | CLB-MP-DOZR-DZ018 -ELCTLV-CHARG-BATTY | DZ018 Battery | 66933 | 10586 | 4700
500066120 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-PIVOT | Pivot Shaft | 66933 | 22310 | 4700
500066110 | CLB-MP-DOZR-DZ018 -HYDSYS-HDTNK | Hydraulic Tank | 66933 | 12696 | 4700
500037278 | CLB-MP-DOZR-DZ018 -TRNSYS-TRQUE | Torque Converter | 66933 | 12696 | 4700
500037277 | CLB-MP-DOZR-DZ018 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 66933 | 12696 | 4700
500037276 | CLB-MP-DOZR-DZ018 -TRNSYS-TROLC | Oil Cooler Transmission | 66933 | 66933 | 4700
500037275 | CLB-MP-DOZR-DZ018 -TRNSYS-TRANS-BEVEL | Bevel Gear | 66933 | 66933 | 4700
500037274 | CLB-MP-DOZR-DZ018 -TRNSYS-TRANS | Transmission | 66933 | 12696 | 4700
500037273 | CLB-MP-DOZR-DZ018 -TRNSYS | Transmission Drive Line | 66933 | 12696 | 4700
500037272 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-TKFRR | Track Frame R/H | 66933 | 16763 | 4700
500037271 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-TKFRL | Track Frame L/H | 66933 | 16763 | 4700
500037270 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 66933 | 66933 | 4700
500037269 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 66933 | 66933 | 4700
500037268 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 66933 | 66933 | 4700
500037267 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 66933 | 66933 | 4700
500037266 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 66933 | 66933 | 4700
500037265 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 66933 | 66933 | 4700
500037264 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 66933 | 66933 | 4700
500037263 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 66933 | 66933 | 4700
500037262 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 66933 | 66933 | 4700
500037261 | CLB-MP-DOZR-DZ018 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 66933 | 66933 | 4700
500037257 | CLB-MP-DOZR-DZ018 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 66933 | 66933 | 4700
500037256 | CLB-MP-DOZR-DZ018 -STRUCT-RIPPR | Ripper | 66933 | 12696 | 4700
500037253 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-TRNON | Trunnions | 66933 | 66933 | 4700
500037251 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-PUARM | Push Arms | 66933 | 66933 | 4700
500037250 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-PIVOT | Pivot Shaft | 66933 | 66933 | 4700
500037249 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-LNKGE | Link Stabiliser | 66933 | 66933 | 4700
500037248 | CLB-MP-DOZR-DZ018 -STRUCT-CHASS-EQUAL | Equaliser Bar | 66933 | 12696 | 4700
500037246 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SEATS | Operators Seat | 66933 | 5461 | 4700
500037245 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-SBELT | Seat Belt | 66933 | 66933 | 4700
500037243 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 66933 | 66933 | 4700
500037240 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN-AIRCN | Air Conditioning System | 66933 | 12696 | 4700
500037239 | CLB-MP-DOZR-DZ018 -STRUCT-CABIN | Operators Cabin | 66933 | 22310 | 4700
500037236 | CLB-MP-DOZR-DZ018 -STRUCT-BLADE | Blade | 66933 | 66933 | 4700
500037233 | CLB-MP-DOZR-DZ018 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 66933 | 2856 | 4700
500037232 | CLB-MP-DOZR-DZ018 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 66933 | 12696 | 4700
500037229 | CLB-MP-DOZR-DZ018 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 66933 | 12696 | 4700
500037227 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-RTCYR | DZ018 Cylinder Ripper Tilt RH | 66933 | 12696 | 4700
500037226 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-RTCYL | DZ018 Cylinder Ripper Tilt LH | 66933 | 12952 | 4700
500037225 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 66933 | 66933 | 4700
500037224 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-RLCYR | DZ018 Cylinder Ripper Lift RH | 66933 | 10586 | 4700
500037223 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-RLCYL | DZ018 Cylinder Ripper Lift LH | 66933 | 12696 | 4700
500037222 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BTCYR | DZ018 Cylinder Blade Tilt RH | 66933 | 3168 | 4700
500037221 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BTCYL | DZ018 Cylinder Blade Tilt LH | 66933 | 1565 | 4700
500037220 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BLCYR | DZ018 Cylinder Blade Lift RH | 66933 | 4145 | 4700
500037219 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCYL-BLCYL | DZ018 Cylinder Blade Lift LH | 66933 | 47 | 4700
500037217 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCVL | Implement Valves Hydraulic | 66933 | 12708 | 4700
500037216 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCON | Implement Control Hydraulic | 66933 | 22310 | 4700
500037215 | CLB-MP-DOZR-DZ018 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 66933 | 684 | 4700
500037213 | CLB-MP-DOZR-DZ018 -GRSYST-GRINJ | Auto Lube Injectors | 66933 | 66933 | 4700
500037210 | CLB-MP-DOZR-DZ018 -GRSYST-ALCON | Auto Lube Controller | 66933 | 66933 | 4700
500037209 | CLB-MP-DOZR-DZ018 -GRSYST-ALBPP | Auto Lube Pump | 66933 | 66933 | 4700
500037203 | CLB-MP-DOZR-DZ018 -FDRSYS-TRKRH | Track Assembly R/H | 66933 | 5833 | 4700
500037202 | CLB-MP-DOZR-DZ018 -FDRSYS-TRKLH | Track Assembly L/H | 66933 | 5833 | 4700
500037201 | CLB-MP-DOZR-DZ018 -FDRSYS-SEGRH | Segments R/H | 66933 | 66933 | 4700
500037200 | CLB-MP-DOZR-DZ018 -FDRSYS-SEGLH | Segments L/H | 66933 | 66933 | 4700
500037199 | CLB-MP-DOZR-DZ018 -FDRSYS-FDRRH | Final Drive R/H | 66933 | 12696 | 4700
500037198 | CLB-MP-DOZR-DZ018 -FDRSYS-FDRLH | Final Drive L/H | 66933 | 15995 | 4700
500037197 | CLB-MP-DOZR-DZ018 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 66933 | 51915 | 4700
500037196 | CLB-MP-DOZR-DZ018 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 66933 | 12696 | 4700
500037195 | CLB-MP-DOZR-DZ018 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 66933 | 66933 | 4700
500037193 | CLB-MP-DOZR-DZ018 -ENGINE-INTEX-TBORH | Turbocharger R/H | 66933 | 4412 | 4700
500037192 | CLB-MP-DOZR-DZ018 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 66933 | 4412 | 4700
500037189 | CLB-MP-DOZR-DZ018 -ENGINE-INTEX-AFTER | Aftercooler | 66933 | 12696 | 4700
500037187 | CLB-MP-DOZR-DZ018 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 66933 | 6417 | 4700
500037185 | CLB-MP-DOZR-DZ018 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 66933 | 4412 | 4700
500037182 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-WTRPP | Water Pump Engine | 66933 | 4412 | 4700
500037181 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-THERM | Thermostats/Regulators | 66933 | 4412 | 4700
500037180 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-RADTR | Radiator Coolant | 66933 | 12696 | 5100
500037179 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-RADTR | Radiator Engine | 66933 | 12696 | 4700
500037177 | CLB-MP-DOZR-DZ018 -ENGINE-COSYS-COFAN | Fan Cooling System | 66933 | 66933 | 4700
500037174 | CLB-MP-DOZR-DZ018 -ENGINE | Engine Assembly, Caterpillar C27 | 66933 | 12696 | 4700
500037173 | CLB-MP-DOZR-DZ018 -ELCTLV-START-STRMR | Starter Motor | 66933 | 4412 | 4700
500037167 | CLB-MP-DOZR-DZ018 -ELCTLV-CHARG-ALTER | Alternator 24V | 66933 | 4412 | 4700
500037164 | CLB-MP-DOZR-DZ018 -BRKSTR-STVLV | Valve Hydraulic Steering | 66933 | 66933 | 4700
500037161 | CLB-MP-DOZR-DZ018 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 66933 | 12696 | 4700
500037160 | CLB-MP-DOZR-DZ018 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 66933 | 12696 | 4700
500037159 | CLB-MP-DOZR-DZ018 -BRKSTR-HYSPP | Pump Hydraulic Steering | 66933 | 66933 | 4700
500037158 | CLB-MP-DOZR-DZ018 | DZ018 Lubrication & Mechanical Services | 66933 | 66933 | 4700
500037157 | CLB-MP-DOZR-DZ018 | Caterpillar D10T Dozer, DZ018 | 66933 | 66933 | 4700
500156273 | CLB-MP-DOZR-DZ017 -ELCTLV-CHARG-BATTY | DZ017 Battery | 70238 | 10138 | 4700
500066119 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-PIVOT | Pivot Shaft | 70238 | 24328 | 4700
500066109 | CLB-MP-DOZR-DZ017 -HYDSYS-HDTNK | Hydraulic Tank | 70238 | 10138 | 4700
500037156 | CLB-MP-DOZR-DZ017 -TRNSYS-TRQUE | Torque Converter | 70238 | 10138 | 4700
500037155 | CLB-MP-DOZR-DZ017 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 70238 | 10138 | 4700
500037154 | CLB-MP-DOZR-DZ017 -TRNSYS-TROLC | Oil Cooler Transmission | 70238 | 70238 | 4700
500037153 | CLB-MP-DOZR-DZ017 -TRNSYS-TRANS-BEVEL | Bevel Gear | 70238 | 70238 | 4700
500037152 | CLB-MP-DOZR-DZ017 -TRNSYS-TRANS | Transmission | 70238 | 10138 | 4700
500037151 | CLB-MP-DOZR-DZ017 -TRNSYS | Transmission Drive Line | 70238 | 10138 | 4700
500037150 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-TKFRR | Track Frame R/H | 70238 | 10138 | 4700
500037149 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-TKFRL | Track Frame L/H | 70238 | 10138 | 4700
500037148 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 70238 | 70238 | 4700
500037147 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 70238 | 70238 | 4700
500037146 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 70238 | 70238 | 4700
500037145 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 70238 | 70238 | 4700
500037144 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 70238 | 70238 | 4700
500037143 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 70238 | 17334 | 4700
500037142 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 70238 | 1638 | 4700
500037141 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 70238 | 52701 | 4700
500037140 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 70238 | 70238 | 4700
500037139 | CLB-MP-DOZR-DZ017 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 70238 | 70238 | 4700
500037135 | CLB-MP-DOZR-DZ017 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 70238 | 70238 | 4700
500037134 | CLB-MP-DOZR-DZ017 -STRUCT-RIPPR | Ripper | 70238 | 10138 | 4700
500037131 | CLB-MP-DOZR-DZ017 -STRUCT-CHASS-TRNON | Trunnions | 70238 | 70238 | 4700
500037129 | CLB-MP-DOZR-DZ017 -STRUCT-CHASS-PUARM | Push Arms | 70238 | 70238 | 4700
500037128 | CLB-MP-DOZR-DZ017 -STRUCT-CHASS-PIVOT | Pivot Shaft | 70238 | 70238 | 4700
500037127 | CLB-MP-DOZR-DZ017 -STRUCT-CHASS-LNKGE | Link Stabiliser | 70238 | 70238 | 4700
500037126 | CLB-MP-DOZR-DZ017 -STRUCT-CHASS-EQUAL | Equaliser Bar | 70238 | 3844 | 4700
500037124 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-SEATS | Operators Seat | 70238 | 522 | 4700
500037123 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-SBELT | Seat Belt | 70238 | 70238 | 4700
500037121 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 70238 | 70238 | 4700
500037118 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN-AIRCN | Air Conditioning System | 70238 | 1106 | 4700
500037117 | CLB-MP-DOZR-DZ017 -STRUCT-CABIN | Operators Cabin | 70238 | 10138 | 4700
500037114 | CLB-MP-DOZR-DZ017 -STRUCT-BLADE | Blade | 70238 | 10138 | 4700
500037111 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 70238 | 4429 | 4700
500037110 | CLB-MP-DOZR-DZ017 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 70238 | 10138 | 4700
500037107 | CLB-MP-DOZR-DZ017 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 70238 | 16673 | 4700
500037105 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-RTCYR | DZ017 Cylinder Ripper Tilt RH | 70238 | 10138 | 4700
500037104 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-RTCYL | DZ017 Cylinder Ripper Tilt LH | 70238 | 1638 | 4700
500037103 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 70238 | 70238 | 4700
500037102 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-RLCYR | DZ017 Cylinder Ripper Lift RH | 70238 | 14073 | 4700
500037101 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-RLCYL | DZ017 Cylinder Ripper Lift LH | 70238 | 2694 | 4700
500037100 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BTCYR | DZ017 Cylinder Blade Tilt RH | 70238 | 3490 | 4700
500037099 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BTCYL | DZ017 Cylinder Blade Tilt LH | 70218 | 3490 | 4700
500037098 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYR | DZ017 Cylinder Blade Lift RH | 70238 | 3490 | 4700
500037097 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCYL-BLCYL | DZ017 Cylinder Blade Lift LH | 70238 | 3490 | 4700
500037095 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCVL | Implement Valves Hydraulic | 70238 | 24804 | 4700
500037094 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCON | Implement Control Hydraulic | 70238 | 10138 | 4700
500037093 | CLB-MP-DOZR-DZ017 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 70238 | 1105 | 4700
500037091 | CLB-MP-DOZR-DZ017 -GRSYST-GRINJ | Auto Lube Injectors | 70238 | 70238 | 4700
500037088 | CLB-MP-DOZR-DZ017 -GRSYST-ALCON | Auto Lube Controller | 70238 | 70238 | 4700
500037087 | CLB-MP-DOZR-DZ017 -GRSYST-ALBPP | Auto Lube Pump | 70238 | 70238 | 4700
500037081 | CLB-MP-DOZR-DZ017 -FDRSYS-TRKRH | Track Assembly R/H | 70238 | 3489 | 4700
500037080 | CLB-MP-DOZR-DZ017 -FDRSYS-TRKLH | Track Assembly L/H | 70238 | 3489 | 4700
500037079 | CLB-MP-DOZR-DZ017 -FDRSYS-SEGRH | Segments R/H | 70238 | 3489 | 4700
500037078 | CLB-MP-DOZR-DZ017 -FDRSYS-SEGLH | Segments L/H | 70238 | 3489 | 4700
500037077 | CLB-MP-DOZR-DZ017 -FDRSYS-FDRRH | Final Drive R/H | 70238 | 2110 | 4700
500037076 | CLB-MP-DOZR-DZ017 -FDRSYS-FDRLH | Final Drive L/H | 70238 | 16673 | 4700
500037075 | CLB-MP-DOZR-DZ017 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 70238 | 55034 | 4700
500037074 | CLB-MP-DOZR-DZ017 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 70238 | 9809 | 4700
500037073 | CLB-MP-DOZR-DZ017 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 70238 | 70238 | 4700
500037071 | CLB-MP-DOZR-DZ017 -ENGINE-INTEX-TBORH | Turbocharger R/H | 70238 | 522 | 4700
500037070 | CLB-MP-DOZR-DZ017 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 70238 | 522 | 4700
500037067 | CLB-MP-DOZR-DZ017 -ENGINE-INTEX-AFTER | Aftercooler | 70238 | 10138 | 4700
500037065 | CLB-MP-DOZR-DZ017 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 70238 | 9809 | 4700
500037063 | CLB-MP-DOZR-DZ017 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 70238 | 522 | 4700
500037060 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-WTRPP | Water Pump Engine | 70238 | 522 | 4700
500037059 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-THERM | Thermostats/Regulators | 70238 | 522 | 4700
500037058 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-RADTR | Radiator Coolant | 70238 | 24328 | 5100
500037057 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-RADTR | Radiator Engine | 70238 | 10138 | 4700
500037055 | CLB-MP-DOZR-DZ017 -ENGINE-COSYS-COFAN | Fan Cooling System | 70238 | 70238 | 4700
500037052 | CLB-MP-DOZR-DZ017 -ENGINE | Engine Assembly, Caterpillar C27 | 70238 | 9809 | 4700
500037051 | CLB-MP-DOZR-DZ017 -ELCTLV-START-STRMR | Starter Motor | 70238 | 522 | 4700
500037045 | CLB-MP-DOZR-DZ017 -ELCTLV-CHARG-ALTER | Alternator 24V | 70238 | 522 | 4700
500037042 | CLB-MP-DOZR-DZ017 -BRKSTR-STVLV | Valve Hydraulic Steering | 70238 | 70238 | 4700
500037039 | CLB-MP-DOZR-DZ017 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 70238 | 10138 | 4700
500037038 | CLB-MP-DOZR-DZ017 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 70238 | 16673 | 4700
500037037 | CLB-MP-DOZR-DZ017 -BRKSTR-HYSPP | Pump Hydraulic Steering | 70238 | 70238 | 4700
500037036 | CLB-MP-DOZR-DZ017 | DZ017 Lubrication & Mechanical Services | 70238 | 70238 | 4700
500037035 | CLB-MP-DOZR-DZ017 | Caterpillar D10T Dozer, DZ017 | 70238 | 70238 | 4700
500159026 | CLB-MP-DOZR-DZ016 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 72846 | 4459 | 4700
500156272 | CLB-MP-DOZR-DZ016 -ELCTLV-CHARG-BATTY | DZ016 Battery | 72846 | 10130 | 4700
500066118 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-PIVOT | Pivot Shaft | 72846 | 38497 | 4700
500066108 | CLB-MP-DOZR-DZ016 -HYDSYS-HDTNK | Hydraulic Tank | 72846 | 7825 | 4700
500037034 | CLB-MP-DOZR-DZ016 -TRNSYS-TRQUE | Torque Converter | 72846 | 7825 | 4700
500037033 | CLB-MP-DOZR-DZ016 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 72846 | 7825 | 4700
500037032 | CLB-MP-DOZR-DZ016 -TRNSYS-TROLC | Oil Cooler Transmission | 72846 | 72846 | 4700
500037031 | CLB-MP-DOZR-DZ016 -TRNSYS-TRANS-BEVEL | Bevel Gear | 72846 | 72846 | 4700
500037030 | CLB-MP-DOZR-DZ016 -TRNSYS-TRANS | Transmission | 72846 | 7825 | 4700
500037029 | CLB-MP-DOZR-DZ016 -TRNSYS | Transmission Drive Line | 72846 | 7825 | 4700
500037028 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-TKFRR | Track Frame R/H | 72846 | 8287 | 4700
500037027 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-TKFRL | Track Frame L/H | 72846 | 7825 | 4700
500037026 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 72846 | 72846 | 4700
500037025 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 72846 | 72846 | 4700
500037024 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 72846 | 72846 | 4700
500037023 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 72846 | 72846 | 4700
500037022 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 72846 | 23658 | 4700
500037021 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 72846 | 72846 | 4700
500037020 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 72846 | 72846 | 4700
500037019 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 72846 | 72846 | 4700
500037018 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 72846 | 72846 | 4700
500037017 | CLB-MP-DOZR-DZ016 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 72846 | 72846 | 4700
500037013 | CLB-MP-DOZR-DZ016 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 72846 | 72846 | 4700
500037012 | CLB-MP-DOZR-DZ016 -STRUCT-RIPPR | Ripper | 72846 | 7825 | 4700
500037009 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-TRNON | Trunnions | 72846 | 72846 | 4700
500037007 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-PUARM | Push Arms | 72846 | 72846 | 4700
500037006 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-PIVOT | Pivot Shaft | 72846 | 7825 | 4700
500037005 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-LNKGE | Link Stabiliser | 72846 | 72846 | 4700
500037004 | CLB-MP-DOZR-DZ016 -STRUCT-CHASS-EQUAL | Equaliser Bar | 72846 | 7825 | 4700
500037002 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-SEATS | Operators Seat | 72846 | 1567 | 4700
500037001 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-SBELT | Seat Belt | 72846 | 72846 | 4700
500036999 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 72846 | 72846 | 4700
500036996 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN-AIRCN | Air Conditioning System | 72846 | 7825 | 4700
500036995 | CLB-MP-DOZR-DZ016 -STRUCT-CABIN | Operators Cabin | 72846 | 7825 | 4700
500036992 | CLB-MP-DOZR-DZ016 -STRUCT-BLADE | Blade | 72846 | 72846 | 4700
500036989 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 72846 | 4404 | 4700
500036988 | CLB-MP-DOZR-DZ016 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 72846 | 12956 | 4700
500036985 | CLB-MP-DOZR-DZ016 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 72846 | 7825 | 4700
500036983 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-RTCYR | DZ016 Cylinder Ripper Tilt RH | 72846 | 13189 | 4700
500036982 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-RTCYL | DZ016 Cylinder Ripper Tilt LH | 72846 | 5019 | 4700
500036981 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 72846 | 72846 | 4700
500036980 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-RLCYR | DZ016 Cylinder Ripper Lift RH | 72846 | 2758 | 4700
500036979 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-RLCYL | DZ016 Cylinder Ripper Lift LH | 72846 | 12669 | 4700
500036978 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BTCYR | DZ016 Cylinder Blade Tilt RH | 72846 | 1124 | 4700
500036977 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BTCYL | DZ016 Cylinder Blade Tilt LH | 72846 | 3673 | 4700
500036976 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BLCYR | DZ016 Cylinder Blade Lift RH | 72846 | 1567 | 4700
500036975 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCYL-BLCYL | DZ016 Cylinder Blade Lift LH | 72846 | 3901 | 4700
500036973 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCVL | Implement Valves Hydraulic | 72846 | 72846 | 4700
500036972 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCON | Implement Control Hydraulic | 72846 | 15503 | 4700
500036971 | CLB-MP-DOZR-DZ016 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 72846 | 1124 | 4700
500036969 | CLB-MP-DOZR-DZ016 -GRSYST-GRINJ | Auto Lube Injectors | 72846 | 72846 | 4700
500036966 | CLB-MP-DOZR-DZ016 -GRSYST-ALCON | Auto Lube Controller | 72846 | 72846 | 4700
500036965 | CLB-MP-DOZR-DZ016 -GRSYST-ALBPP | Auto Lube Pump | 72846 | 72846 | 4700
500036959 | CLB-MP-DOZR-DZ016 -FDRSYS-TRKRH | Track Assembly R/H | 72846 | 509 | 4700
500036958 | CLB-MP-DOZR-DZ016 -FDRSYS-TRKLH | Track Assembly L/H | 72846 | 509 | 4700
500036957 | CLB-MP-DOZR-DZ016 -FDRSYS-SEGRH | Segments R/H | 72846 | 72846 | 4700
500036956 | CLB-MP-DOZR-DZ016 -FDRSYS-SEGLH | Segments L/H | 72846 | 72846 | 4700
500036955 | CLB-MP-DOZR-DZ016 -FDRSYS-FDRRH | Final Drive R/H | 72846 | 9172 | 4700
500036954 | CLB-MP-DOZR-DZ016 -FDRSYS-FDRLH | Final Drive L/H | 72846 | 5718 | 4700
500036953 | CLB-MP-DOZR-DZ016 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 72846 | 10547 | 4700
500036952 | CLB-MP-DOZR-DZ016 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 72846 | 10547 | 4700
500036951 | CLB-MP-DOZR-DZ016 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 72846 | 10547 | 4700
500036949 | CLB-MP-DOZR-DZ016 -ENGINE-INTEX-TBORH | Turbocharger R/H | 72846 | 1567 | 4700
500036948 | CLB-MP-DOZR-DZ016 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 72846 | 1567 | 4700
500036945 | CLB-MP-DOZR-DZ016 -ENGINE-INTEX-AFTER | Aftercooler | 72846 | 7825 | 4700
500036943 | CLB-MP-DOZR-DZ016 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 72846 | 10547 | 4700
500036941 | CLB-MP-DOZR-DZ016 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 72846 | 1567 | 4700
500036938 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-WTRPP | Water Pump Engine | 72846 | 1567 | 4700
500036937 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-THERM | Thermostats/Regulators | 72846 | 1567 | 4700
500036936 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-RADTR | Do Not Use - Duplicate | 72846 | 23352 | 5100
500036935 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-RADTR | Radiator Engine | 72846 | 7825 | 4700
500036933 | CLB-MP-DOZR-DZ016 -ENGINE-COSYS-COFAN | Fan Cooling System | 72846 | 36899 | 4700
500036930 | CLB-MP-DOZR-DZ016 -ENGINE | Engine Assembly, Caterpillar C27 | 72846 | 10547 | 4700
500036929 | CLB-MP-DOZR-DZ016 -ELCTLV-START-STRMR | Starter Motor | 72846 | 1567 | 4700
500036923 | CLB-MP-DOZR-DZ016 -ELCTLV-CHARG-ALTER | Alternator 24V | 72846 | 8559 | 4700
500036920 | CLB-MP-DOZR-DZ016 -BRKSTR-STVLV | Valve Hydraulic Steering | 72846 | 72846 | 4700
500036917 | CLB-MP-DOZR-DZ016 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 72846 | 7825 | 4700
500036916 | CLB-MP-DOZR-DZ016 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 72846 | 8296 | 4700
500036915 | CLB-MP-DOZR-DZ016 -BRKSTR-HYSPP | Pump Hydraulic Steering | 72846 | 72846 | 4700
500036914 | CLB-MP-DOZR-DZ016 | DZ016 Lubrication & Mechanical Services | 72846 | 72846 | 4700
500036913 | CLB-MP-DOZR-DZ016 | Caterpillar D10T Dozer, DZ016 | 72846 | 72846 | 4700
500159025 | CLB-MP-DOZR-DZ015 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 72405 | 6850 | 4700
500156271 | CLB-MP-DOZR-DZ015 -ELCTLV-CHARG-BATTY | DZ015 Battery | 72405 | 11244 | 4700
500066117 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-PIVOT | Pivot Shaft | 72405 | 31421 | 4700
500066107 | CLB-MP-DOZR-DZ015 -HYDSYS-HDTNK | Hydraulic Tank | 72405 | 3917 | 4700
500036912 | CLB-MP-DOZR-DZ015 -TRNSYS-TRQUE | Torque Converter | 72405 | 3917 | 4700
500036911 | CLB-MP-DOZR-DZ015 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 72405 | 3917 | 4700
500036910 | CLB-MP-DOZR-DZ015 -TRNSYS-TROLC | Oil Cooler Transmission | 72405 | 72405 | 4700
500036909 | CLB-MP-DOZR-DZ015 -TRNSYS-TRANS-BEVEL | Bevel Gear | 72405 | 72405 | 4700
500036908 | CLB-MP-DOZR-DZ015 -TRNSYS-TRANS | Transmission | 72405 | 3917 | 4700
500036907 | CLB-MP-DOZR-DZ015 -TRNSYS | Transmission Drive Line | 72405 | 3917 | 4700
500036906 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-TKFRR | Track Frame R/H | 72405 | 3917 | 4700
500036905 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-TKFRL | Track Frame L/H | 72405 | 3917 | 4700
500036904 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 72405 | 72405 | 4700
500036903 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 72405 | 72405 | 4700
500036902 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 72405 | 72405 | 4700
500036901 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 72405 | 72405 | 4700
500036900 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 72405 | 22821 | 4700
500036899 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 72405 | 44002 | 4700
500036898 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 72405 | 33029 | 4700
500036897 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 72405 | 44002 | 4700
500036896 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 72405 | 72405 | 4700
500036895 | CLB-MP-DOZR-DZ015 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 72405 | 72405 | 4700
500036891 | CLB-MP-DOZR-DZ015 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 72405 | 72405 | 4700
500036890 | CLB-MP-DOZR-DZ015 -STRUCT-RIPPR | Ripper | 72405 | 72405 | 4700
500036887 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-TRNON | Trunnions | 72405 | 72405 | 4700
500036885 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-PUARM | Push Arms | 72405 | 72405 | 4700
500036884 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-PIVOT | Pivot Shaft | 72405 | 72405 | 4700
500036883 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-LNKGE | Link Stabiliser | 72405 | 72405 | 4700
500036882 | CLB-MP-DOZR-DZ015 -STRUCT-CHASS-EQUAL | Equaliser Bar | 72405 | 17512 | 4700
500036880 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-SEATS | Operators Seat | 72405 | 3917 | 4700
500036879 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-SBELT | Seat Belt | 72405 | 10991 | 4700
500036877 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 72405 | 72405 | 4700
500036874 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN-AIRCN | Air Conditioning System | 72405 | 3917 | 4700
500036873 | CLB-MP-DOZR-DZ015 -STRUCT-CABIN | Operators Cabin | 72405 | 3917 | 4700
500036870 | CLB-MP-DOZR-DZ015 -STRUCT-BLADE | Blade | 72405 | 5940 | 4700
500036867 | CLB-MP-DOZR-DZ015 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 72405 | 5635 | 4700
500036866 | CLB-MP-DOZR-DZ015 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 72405 | 3917 | 4700
500036863 | CLB-MP-DOZR-DZ015 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 72405 | 3917 | 4700
500036861 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-RTCYR | DZ015 Cylinder Ripper Tilt RH | 72405 | 3917 | 4700
500036860 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-RTCYL | DZ015 Cylinder Ripper Tilt LH | 72405 | 3917 | 4700
500036859 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 72405 | 72405 | 4700
500036858 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-RLCYR | DZ015 Cylinder Ripper Lift RH | 72405 | 3917 | 4700
500036857 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-RLCYL | DZ015 Cylinder Ripper Lift LH | 72405 | 10756 | 4700
500036856 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BTCYR | DZ015 Cylinder Blade Tilt RH | 72405 | 6850 | 4700
500036855 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BTCYL | DZ015 Cylinder Blade Tilt LH | 72405 | 10760 | 4700
500036854 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BLCYR | DZ015 Cylinder Blade Lift RH | 72405 | 3917 | 4700
500036853 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCYL-BLCYL | DZ015 Cylinder Blade Lift LH | 72405 | 3716 | 4700
500036851 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCVL | Implement Valves Hydraulic | 72405 | 72405 | 4700
500036850 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCON | Implement Control Hydraulic | 72405 | 72405 | 4700
500036849 | CLB-MP-DOZR-DZ015 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 72405 | 5635 | 4700
500036847 | CLB-MP-DOZR-DZ015 -GRSYST-GRINJ | Auto Lube Injectors | 72405 | 72405 | 4700
500036844 | CLB-MP-DOZR-DZ015 -GRSYST-ALCON | Auto Lube Controller | 72405 | 72405 | 4700
500036843 | CLB-MP-DOZR-DZ015 -GRSYST-ALBPP | Auto Lube Pump | 72405 | 72405 | 4700
500036837 | CLB-MP-DOZR-DZ015 -FDRSYS-TRKRH | Track Assembly R/H | 72405 | 238 | 4700
500036836 | CLB-MP-DOZR-DZ015 -FDRSYS-TRKLH | Track Assembly L/H | 72405 | 238 | 4700
500036835 | CLB-MP-DOZR-DZ015 -FDRSYS-SEGRH | Segments R/H | 72405 | 72405 | 4700
500036834 | CLB-MP-DOZR-DZ015 -FDRSYS-SEGLH | Segments L/H | 72405 | 72405 | 4700
500036833 | CLB-MP-DOZR-DZ015 -FDRSYS-FDRRH | Final Drive R/H | 72405 | 10760 | 4700
500036832 | CLB-MP-DOZR-DZ015 -FDRSYS-FDRLH | Final Drive L/H | 72405 | 3917 | 4700
500036831 | CLB-MP-DOZR-DZ015 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 72405 | 43363 | 4700
500036830 | CLB-MP-DOZR-DZ015 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 72405 | 3917 | 4700
500036829 | CLB-MP-DOZR-DZ015 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 72405 | 43363 | 4700
500036827 | CLB-MP-DOZR-DZ015 -ENGINE-INTEX-TBORH | Turbocharger R/H | 72405 | 3917 | 4700
500036826 | CLB-MP-DOZR-DZ015 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 72405 | 3917 | 4700
500036823 | CLB-MP-DOZR-DZ015 -ENGINE-INTEX-AFTER | Aftercooler | 72405 | 12392 | 4700
500036821 | CLB-MP-DOZR-DZ015 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 72405 | 3917 | 4700
500036819 | CLB-MP-DOZR-DZ015 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 72405 | 3917 | 4700
500036816 | CLB-MP-DOZR-DZ015 -ENGINE-COSYS-WTRPP | Water Pump Engine | 72405 | 3917 | 4700
500036815 | CLB-MP-DOZR-DZ015 -ENGINE-COSYS-THERM | Thermostats/Regulators | 72405 | 3917 | 4700
500036814 | CLB-MP-DOZR-DZ015 -ENGINE-COSYS-RADTR | Radiator Coolant | 72405 | 17512 | 5100
500036813 | CLB-MP-DOZR-DZ015 -ENGINE-COSYS-RADTR | Radiator Engine | 72405 | 3917 | 4700
500036811 | CLB-MP-DOZR-DZ015 -ENGINE-COSYS-COFAN | Fan Cooling System | 72405 | 43363 | 4700
500036808 | CLB-MP-DOZR-DZ015 -ENGINE | Engine Assembly, Caterpillar C27 | 72405 | 3917 | 4700
500036807 | CLB-MP-DOZR-DZ015 -ELCTLV-START-STRMR | Starter Motor | 72405 | 3917 | 4700
500036801 | CLB-MP-DOZR-DZ015 -ELCTLV-CHARG-ALTER | Alternator 24V | 72405 | 3917 | 4700
500036798 | CLB-MP-DOZR-DZ015 -BRKSTR-STVLV | Valve Hydraulic Steering | 72405 | 72405 | 4700
500036795 | CLB-MP-DOZR-DZ015 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 72405 | 3917 | 4700
500036794 | CLB-MP-DOZR-DZ015 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 72405 | 3917 | 4700
500036793 | CLB-MP-DOZR-DZ015 -BRKSTR-HYSPP | Pump Hydraulic Steering | 72405 | 72405 | 4700
500036572 | CLB-MP-DOZR-DZ015 | DZ015 Lubrication & Mechanical Services | 72405 | 72405 | 4700
500036571 | CLB-MP-DOZR-DZ015 | Caterpillar D10T Dozer, DZ015 | 72405 | 72405 | 4700
500066115 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-PIVOT | Pivot Shaft | 72325 | 16426 | 4700
500066105 | CLB-MP-DOZR-DZ013 -HYDSYS-HDTNK | Hydraulic Tank | 72325 | 2487 | 4700
500036654 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-TRNON | Trunnions | 72325 | 72325 | 4700
500036653 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-LNKGE | Link Stabiliser | 72325 | 72325 | 4700
500036652 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-PUARM | Push Arms | 72325 | 72325 | 4700
500036600 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-PIVOT | Pivot Shaft | 72325 | 3120 | 4700
500036599 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 72325 | 72325 | 4700
500036598 | CLB-MP-DOZR-DZ013 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 72325 | 2487 | 4700
500036597 | CLB-MP-DOZR-DZ013 -ENGINE-COSYS-RADTR | Radiator Coolant | 72325 | 16426 | 5100
500036596 | CLB-MP-DOZR-DZ013 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 72325 | 43120 | 4700
500028494 | CLB-MP-DOZR-DZ013 -TRNSYS-TRQUE | Torque Converter | 72325 | 2487 | 4700
500028493 | CLB-MP-DOZR-DZ013 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 72325 | 2487 | 4700
500028492 | CLB-MP-DOZR-DZ013 -TRNSYS-TROLC | Oil Cooler Transmission | 72325 | 72325 | 4700
500028491 | CLB-MP-DOZR-DZ013 -TRNSYS-TRANS-BEVEL | Bevel Gear | 72325 | 72325 | 4700
500028490 | CLB-MP-DOZR-DZ013 -TRNSYS-TRANS | Transmission | 72325 | 2487 | 4700
500028489 | CLB-MP-DOZR-DZ013 -TRNSYS | Transmission Drive Line | 72325 | 2487 | 4700
500028488 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-TKFRR | Track Frame R/H | 72325 | 2487 | 4700
500028487 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-TKFRL | Track Frame L/H | 72325 | 2487 | 4700
500028486 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 72325 | 20611 | 4700
500028485 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 72325 | 20611 | 4700
500028484 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 72325 | 72325 | 4700
500028483 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 72325 | 72325 | 4700
500028482 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 72325 | 20611 | 4700
500028481 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 72325 | 3134 | 4700
500028480 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 72325 | 20611 | 4700
500028479 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 72325 | 72325 | 4700
500028478 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 72325 | 72325 | 4700
500028477 | CLB-MP-DOZR-DZ013 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 72325 | 72325 | 4700
500028473 | CLB-MP-DOZR-DZ013 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 72325 | 72325 | 4700
500028472 | CLB-MP-DOZR-DZ013 -STRUCT-RIPPR | Ripper | 72325 | 72325 | 4700
500028469 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 72325 | 72325 | 4700
500028468 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS-EQUAL | Equaliser Bar | 72325 | 7031 | 4700
500028467 | CLB-MP-DOZR-DZ013 -STRUCT-CHASS | Chassis | 72325 | 72325 | 4700
500028466 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-SEATS | Operators Seat | 72325 | 2487 | 4700
500028465 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-SBELT | Seat Belt | 72325 | 72325 | 4700
500028463 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 72325 | 72325 | 4700
500028460 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN-AIRCN | Air Conditioning System | 72325 | 2487 | 4700
500028459 | CLB-MP-DOZR-DZ013 -STRUCT-CABIN | Operators Cabin | 72325 | 16426 | 4700
500028456 | CLB-MP-DOZR-DZ013 -STRUCT-BLADE | Blade | 72325 | 2487 | 4700
500028455 | CLB-MP-DOZR-DZ013 -MANGMT-UMMMC | Mine Monitoring and Control | 72325 | 72325 | 4700
500028454 | CLB-MP-DOZR-DZ013 -MANGMT-UMENG | Engine Management System | 72325 | 72325 | 4700
500028453 | CLB-MP-DOZR-DZ013 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 72325 | 5138 | 4700
500028452 | CLB-MP-DOZR-DZ013 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 72325 | 2487 | 4700
500028449 | CLB-MP-DOZR-DZ013 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 72325 | 2487 | 4700
500028447 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-RTCYR | DZ013 Cylinder Ripper Tilt RH | 72325 | 22040 | 4700
500028446 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-RTCYL | DZ013 Cylinder Ripper Tilt LH | 72325 | 8069 | 4700
500028445 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-RLCYR | DZ013 Cylinder Ripper Lift RH | 72325 | 16426 | 4700
500028444 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-RLCYL | DZ013 Cylinder Ripper Lift LH | 72325 | 10734 | 4700
500028443 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BTCYR | DZ013 Cylinder Blade Tilt RH | 72325 | 8810 | 4700
500028442 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BTCYL | DZ013 Cylinder Blade Tilt LH | 72325 | 6533 | 4700
500028441 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BLCYR | DZ013 Cylinder Blade Lift RH | 72325 | 2487 | 4700
500028440 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCYL-BLCYL | DZ013 Cylinder Blade Lift LH | 72325 | 503 | 4700
500028438 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCVL | Implement Valves Hydraulic | 72325 | 72325 | 4700
500028437 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCON | Implement Control Hydraulic | 72325 | 72325 | 4700
500028436 | CLB-MP-DOZR-DZ013 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 72325 | 2487 | 4700
500028435 | CLB-MP-DOZR-DZ013 -GRSYST-GRTNK | Auto Lube Resevoir | 72325 | 72325 | 4700
500028434 | CLB-MP-DOZR-DZ013 -GRSYST-GRINJ | Auto Lube Injectors | 72325 | 72325 | 4700
500028431 | CLB-MP-DOZR-DZ013 -GRSYST-ALCON | Auto Lube Controller | 72325 | 72325 | 4700
500028430 | CLB-MP-DOZR-DZ013 -GRSYST-ALBPP | Auto Lube Pump | 72325 | 72325 | 4700
500028427 | CLB-MP-DOZR-DZ013 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 72325 | 72325 | 4700
500028424 | CLB-MP-DOZR-DZ013 -FDRSYS-TRKRH | Track Assembly R/H | 72325 | 1977 | 4700
500028423 | CLB-MP-DOZR-DZ013 -FDRSYS-TRKLH | Track Assembly L/H | 72325 | 1977 | 4700
500028422 | CLB-MP-DOZR-DZ013 -FDRSYS-SEGRH | Segments R/H | 72325 | 72325 | 4700
500028421 | CLB-MP-DOZR-DZ013 -FDRSYS-SEGLH | Segments L/H | 72325 | 72325 | 4700
500028420 | CLB-MP-DOZR-DZ013 -FDRSYS-FDRRH | Final Drive R/H | 72325 | 8866 | 4700
500028419 | CLB-MP-DOZR-DZ013 -FDRSYS-FDRLH | Final Drive L/H | 72325 | 15283 | 4700
500028418 | CLB-MP-DOZR-DZ013 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 72325 | 2487 | 4700
500028417 | CLB-MP-DOZR-DZ013 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 72325 | 43120 | 4700
500028415 | CLB-MP-DOZR-DZ013 -ENGINE-INTEX-TBORH | Turbocharger R/H | 72325 | 2487 | 4700
500028414 | CLB-MP-DOZR-DZ013 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 72325 | 2487 | 4700
500028413 | CLB-MP-DOZR-DZ013 -ENGINE-INTEX-EXHST | Exhaust System | 72325 | 72325 | 4700
500028411 | CLB-MP-DOZR-DZ013 -ENGINE-INTEX-AFTER | Aftercooler | 72325 | 2487 | 4700
500028409 | CLB-MP-DOZR-DZ013 -ENGINE-FUSYS-FULTK | Fuel Tank | 72325 | 72325 | 4700
500028408 | CLB-MP-DOZR-DZ013 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 72325 | 2487 | 4700
500028405 | CLB-MP-DOZR-DZ013 -ENGINE-COSYS-WTRPP | Water Pump Engine | 72325 | 2487 | 4700
500028404 | CLB-MP-DOZR-DZ013 -ENGINE-COSYS-THERM | Thermostats/Regulators | 72325 | 2487 | 4700
500028403 | CLB-MP-DOZR-DZ013 -ENGINE-COSYS-RADTR | Radiator Engine | 72325 | 2487 | 4700
500028401 | CLB-MP-DOZR-DZ013 -ENGINE-COSYS-COFAN | Fan Cooling System | 72325 | 43120 | 4700
500028398 | CLB-MP-DOZR-DZ013 -ENGINE | Engine Assembly, Caterpillar C27 | 72325 | 2487 | 4700
500028397 | CLB-MP-DOZR-DZ013 -ELCTLV-START-STRMR | Starter Motor | 72325 | 2487 | 4700
500028392 | CLB-MP-DOZR-DZ013 -ELCTLV-CHARG-BATTY | Batteries | 72325 | 10734 | 4700
500028391 | CLB-MP-DOZR-DZ013 -ELCTLV-CHARG-ALTER | Alternator 24V | 72325 | 2487 | 4700
500028388 | CLB-MP-DOZR-DZ013 -BRKSTR-STVLV | Valve Hydraulic Steering | 72325 | 16426 | 4700
500028385 | CLB-MP-DOZR-DZ013 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 72325 | 2487 | 4700
500028384 | CLB-MP-DOZR-DZ013 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 72325 | 2487 | 4700
500028383 | CLB-MP-DOZR-DZ013 -BRKSTR-HYSPP | Pump Hydraulic Steering | 72325 | 72325 | 4700
500028382 | CLB-MP-DOZR-DZ013 | DZ013 Mechanical & Lube Services | 72351 | 72351 | 4700
500028381 | CLB-MP-DOZR-DZ013 | Caterpillar D10T Dozer, DZ013 | 72325 | 72325 | 4700
500066114 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-PIVOT | Pivot Shaft | 60154 | 30787 | 4700
500066104 | CLB-MP-DOZR-DZ012 -HYDSYS-HDTNK | Hydraulic Tank | 60154 | 2176 | 4700
500036651 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-TRNON | Trunnions | 60154 | 30787 | 4700
500036650 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-LNKGE | Link Stabiliser | 60154 | 60154 | 4700
500036649 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-PUARM | Push Arms | 60154 | 60154 | 4700
500036595 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-PIVOT | Pivot Shaft | 60154 | 15952 | 4700
500036594 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 60154 | 60154 | 4700
500036593 | CLB-MP-DOZR-DZ012 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 60154 | 2176 | 4700
500036592 | CLB-MP-DOZR-DZ012 -ENGINE-COSYS-RADTR | Radiator Coolant | 60154 | 15952 | 5100
500036591 | CLB-MP-DOZR-DZ012 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 60154 | 60154 | 4700
500027668 | CLB-MP-DOZR-DZ012 -TRNSYS-TRQUE | Torque Converter | 60154 | 4040 | 4700
500027667 | CLB-MP-DOZR-DZ012 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 60154 | 6899 | 4700
500027666 | CLB-MP-DOZR-DZ012 -TRNSYS-TROLC | Oil Cooler Transmission | 60154 | 60154 | 4700
500027665 | CLB-MP-DOZR-DZ012 -TRNSYS-TRANS-BEVEL | Bevel Gear | 60154 | 60154 | 4700
500027664 | CLB-MP-DOZR-DZ012 -TRNSYS-TRANS | Transmission | 60154 | 9226 | 4700
500027663 | CLB-MP-DOZR-DZ012 -TRNSYS | Transmission Drive Line | 60154 | 2176 | 4700
500027662 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-TKFRR | Track Frame R/H | 60154 | 2176 | 4700
500027661 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-TKFRL | Track Frame L/H | 60154 | 2176 | 4700
500027660 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 60154 | 60154 | 4700
500027659 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 60154 | 60154 | 4700
500027658 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 60154 | 60154 | 4700
500027657 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 60154 | 60154 | 4700
500027656 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 60154 | 60154 | 4700
500027655 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 60154 | 60154 | 4700
500027654 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 60154 | 60154 | 4700
500027653 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 60154 | 60154 | 4700
500027652 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 60154 | 60154 | 4700
500027651 | CLB-MP-DOZR-DZ012 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 60154 | 60154 | 4700
500027647 | CLB-MP-DOZR-DZ012 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 60154 | 60154 | 4700
500027646 | CLB-MP-DOZR-DZ012 -STRUCT-RIPPR | Ripper | 60154 | 37563 | 4700
500027643 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-ROPSS | Roll Over Protective Structure | 60154 | 60154 | 4700
500027642 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS-EQUAL | Equaliser Bar | 60154 | 4740 | 4700
500027641 | CLB-MP-DOZR-DZ012 -STRUCT-CHASS | Chassis | 60154 | 60154 | 4700
500027640 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-SEATS | Operators Seat | 60154 | 2176 | 4700
500027639 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-SBELT | Seat Belt | 60154 | 60154 | 4700
500027637 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 60154 | 60154 | 4700
500027634 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN-AIRCN | Air Conditioning System | 60154 | 2176 | 4700
500027633 | CLB-MP-DOZR-DZ012 -STRUCT-CABIN | Operators Cabin | 60154 | 15952 | 4700
500027630 | CLB-MP-DOZR-DZ012 -STRUCT-BLADE | Blade | 60154 | 60154 | 4700
500027629 | CLB-MP-DOZR-DZ012 -MANGMT-UMMMC | Mine Monitoring and Control | 60154 | 60154 | 4700
500027628 | CLB-MP-DOZR-DZ012 -MANGMT-UMENG | Engine Management System | 60154 | 32783 | 4700
500027627 | CLB-MP-DOZR-DZ012 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 60154 | 2176 | 4700
500027626 | CLB-MP-DOZR-DZ012 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 60154 | 2176 | 4700
500027623 | CLB-MP-DOZR-DZ012 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 60154 | 2176 | 4700
500027621 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-RTCYR | DZ012 Cylinder Ripper Tilt RH | 60154 | 15952 | 4700
500027620 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-RTCYL | DZ012 Cylinder Ripper Tilt LH | 60154 | 15952 | 4700
500027619 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-RLCYR | DZ012 Cylinder Ripper Lift RH | 60154 | 2176 | 4700
500027618 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-RLCYL | DZ012 Cylinder Ripper Lift LH | 60154 | 15952 | 4700
500027617 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BTCYR | DZ012 Cylinder Blade Tilt RH | 60154 | 4189 | 4700
500027616 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BTCYL | DZ012 Cylinder Blade Tilt LH | 60154 | 3808 | 4700
500027615 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BLCYR | DZ012 Cylinder Blade Lift RH | 60154 | 2176 | 4700
500027614 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCYL-BLCYL | DZ012 Cylinder Blade Lift LH | 60154 | 2176 | 4700
500027612 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCVL | Implement Valves Hydraulic | 60154 | 60154 | 4700
500027611 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCON | Implement Control Hydraulic | 60154 | 30787 | 4700
500027610 | CLB-MP-DOZR-DZ012 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 60154 | 2176 | 4700
500027609 | CLB-MP-DOZR-DZ012 -GRSYST-GRTNK | Auto Lube Resevoir | 60154 | 60154 | 4700
500027608 | CLB-MP-DOZR-DZ012 -GRSYST-GRINJ | Auto Lube Injectors | 60154 | 60154 | 4700
500027605 | CLB-MP-DOZR-DZ012 -GRSYST-ALCON | Auto Lube Controller | 60154 | 60154 | 4700
500027604 | CLB-MP-DOZR-DZ012 -GRSYST-ALBPP | Auto Lube Pump | 60154 | 60154 | 4700
500027601 | CLB-MP-DOZR-DZ012 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 60154 | 60154 | 4700
500027598 | CLB-MP-DOZR-DZ012 -FDRSYS-TRKRH | Track Assembly R/H | 60154 | 5089 | 4700
500027597 | CLB-MP-DOZR-DZ012 -FDRSYS-TRKLH | Track Assembly L/H | 60154 | 5089 | 4700
500027596 | CLB-MP-DOZR-DZ012 -FDRSYS-SEGRH | Segments R/H | 60154 | 60154 | 4700
500027595 | CLB-MP-DOZR-DZ012 -FDRSYS-SEGLH | Segments L/H | 60154 | 60154 | 4700
500027594 | CLB-MP-DOZR-DZ012 -FDRSYS-FDRRH | Final Drive R/H | 60154 | 9380 | 4700
500027593 | CLB-MP-DOZR-DZ012 -FDRSYS-FDRLH | Final Drive L/H | 60154 | 4740 | 4700
500027592 | CLB-MP-DOZR-DZ012 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 60154 | 2176 | 4700
500027591 | CLB-MP-DOZR-DZ012 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 60154 | 44058 | 4700
500027589 | CLB-MP-DOZR-DZ012 -ENGINE-INTEX-TBORH | Turbocharger R/H | 60154 | 2176 | 4700
500027588 | CLB-MP-DOZR-DZ012 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 60154 | 2176 | 4700
500027587 | CLB-MP-DOZR-DZ012 -ENGINE-INTEX-EXHST | Exhaust System | 60154 | 60154 | 4700
500027585 | CLB-MP-DOZR-DZ012 -ENGINE-INTEX-AFTER | Aftercooler | 60154 | 2176 | 4700
500027583 | CLB-MP-DOZR-DZ012 -ENGINE-FUSYS-FULTK | Fuel Tank | 60154 | 15952 | 4700
500027582 | CLB-MP-DOZR-DZ012 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 60154 | 2176 | 4700
500027579 | CLB-MP-DOZR-DZ012 -ENGINE-COSYS-WTRPP | Water Pump Engine | 60154 | 2176 | 4700
500027578 | CLB-MP-DOZR-DZ012 -ENGINE-COSYS-THERM | Thermostats/Regulators | 60154 | 2176 | 4700
500027577 | CLB-MP-DOZR-DZ012 -ENGINE-COSYS-RADTR | Radiator Engine | 60154 | 2176 | 4700
500027575 | CLB-MP-DOZR-DZ012 -ENGINE-COSYS-COFAN | Fan Cooling System | 60154 | 44058 | 4700
500027572 | CLB-MP-DOZR-DZ012 -ENGINE | Engine Assembly, Caterpillar C27 | 60154 | 2176 | 4700
500027571 | CLB-MP-DOZR-DZ012 -ELCTLV-START-STRMR | Starter Motor | 60154 | 2176 | 4700
500027566 | CLB-MP-DOZR-DZ012 -ELCTLV-CHARG-BATTY | Batteries | 60154 | 2176 | 4700
500027565 | CLB-MP-DOZR-DZ012 -ELCTLV-CHARG-ALTER | Alternator 24V | 60154 | 2176 | 4700
500027562 | CLB-MP-DOZR-DZ012 -BRKSTR-STVLV | Valve Hydraulic Steering | 60154 | 15952 | 4700
500027559 | CLB-MP-DOZR-DZ012 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 60154 | 2176 | 4700
500027558 | CLB-MP-DOZR-DZ012 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 60154 | 2176 | 4700
500027557 | CLB-MP-DOZR-DZ012 -BRKSTR-HYSPP | Pump Hydraulic Steering | 60154 | 60154 | 4700
500027556 | CLB-MP-DOZR-DZ012 | DZ012 Mechanical & Lube Services | 60154 | 60154 | 4700
500027555 | CLB-MP-DOZR-DZ012 | Caterpillar D10T Dozer, DZ012 | 60154 | 60154 | 4700
500159024 | CLB-MP-DOZR-DZ011 -CASSYS-CTRLH-ACTBK | Actuator Brake CAS | 70636 | 6032 | 4700
500156270 | CLB-MP-DOZR-DZ011 -ELCTLV-CHARG-BATTY | DZ011 Battery | 70636 | 5309 | 4700
500066113 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-PIVOT | Pivot Shaft | 70636 | 27869 | 4700
500066102 | CLB-MP-DOZR-DZ011 -HYDSYS-HDTNK | Hydraulic Tank | 70636 | 13876 | 4700
500036648 | CLB-MP-DOZR-DZ011 -STRUCT-CHASS-TRNON | Trunnions | 70636 | 70636 | 4700
500036647 | CLB-MP-DOZR-DZ011 -STRUCT-CHASS-LNKGE | Link Stabiliser | 70636 | 70636 | 4700
500036646 | CLB-MP-DOZR-DZ011 -STRUCT-CHASS-PUARM | Push Arms | 70636 | 70636 | 4700
500036590 | CLB-MP-DOZR-DZ011 -STRUCT-CHASS-PIVOT | Pivot Shaft | 70636 | 14966 | 4700
500036589 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RPUCY | Cylinder Ripper Pin Puller | 70636 | 70636 | 4700
500036588 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-RADTR | Radiator Coolant | 70636 | 13876 | 5100
500036587 | CLB-MP-DOZR-DZ011 -ENGINE-LUBSY-PREPP | Oil Pump Pre-Lube Engine | 70636 | 57036 | 4700
500036586 | CLB-MP-DOZR-DZ011 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 70636 | 13876 | 4700
500025594 | CLB-MP-DOZR-DZ011 | DZ011 Mechanical & Lube Services | 70636 | 70636 | 4700
500025592 | CLB-MP-DOZR-DZ011 -TRNSYS-TRQUE | Torque Converter | 70636 | 13876 | 4700
500025591 | CLB-MP-DOZR-DZ011 -TRNSYS-TRPMP | Pump Trans & Torque Converter Charge | 70636 | 3895 | 4700
500025590 | CLB-MP-DOZR-DZ011 -TRNSYS-TROLC | Oil Cooler Transmission | 70636 | 70636 | 4700
500025589 | CLB-MP-DOZR-DZ011 -TRNSYS-TRANS-BEVEL | Bevel Gear | 70636 | 70636 | 4700
500025588 | CLB-MP-DOZR-DZ011 -TRNSYS-TRANS | Transmission | 70636 | 13876 | 4700
500025587 | CLB-MP-DOZR-DZ011 -TRNSYS | Transmission Drive Line | 70636 | 7204 | 4700
500025586 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-TKFRR | Track Frame R/H | 70636 | 1038 | 4700
500025585 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-TKFRL | Track Frame L/H | 70636 | 1038 | 4700
500025584 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-LDSFR | Rollers Load Single Flange Right Hand | 70636 | 70636 | 4700
500025583 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-LDSFL | Rollers Load Single Flange Left Hand | 70636 | 70636 | 4700
500025582 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-LDDFR | Rollers Load Double Flange Right Hand | 70636 | 70636 | 4700
500025581 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-LDDFL | Rollers Load Double Flange Left Hand | 70636 | 70636 | 4700
500025580 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-IDRHR | Idler Track R/H Rear | 70636 | 39063 | 4700
500025579 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-IDRHF | Idler Track R/H Front | 70636 | 39063 | 4700
500025578 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-IDLHR | Idler Track L/H Rear | 70636 | 9057 | 4700
500025577 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-IDLHF | Idler Track L/H Front | 70636 | 39063 | 4700
500025576 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-ADJRH | Track Adjuster R/H | 70636 | 70636 | 4700
500025575 | CLB-MP-DOZR-DZ011 -STRUCT-UNDER-ADJLH | Track Adjuster L/H | 70636 | 33520 | 4700
500025571 | CLB-MP-DOZR-DZ011 -STRUCT-RIPPR-RIGET | Ripper Wear Elements (GET) | 70636 | 70636 | 4700
500025570 | CLB-MP-DOZR-DZ011 -STRUCT-RIPPR | Ripper | 70636 | 70636 | 4700
500025566 | CLB-MP-DOZR-DZ011 -STRUCT-CHASS-EQUAL | Equaliser Bar | 70636 | 3975 | 4700
500025564 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-SEATS | Operators Seat | 70636 | 2639 | 4700
500025563 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-SBELT | Seat Belt | 70636 | 70636 | 4700
500025561 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 70636 | 70636 | 4700
500025558 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN-AIRCN | Air Conditioning System | 70636 | 13876 | 4700
500025557 | CLB-MP-DOZR-DZ011 -STRUCT-CABIN | Operators Cabin | 70636 | 27869 | 4700
500025554 | CLB-MP-DOZR-DZ011 -STRUCT-BLADE | Blade | 70636 | 70636 | 4700
500025551 | CLB-MP-DOZR-DZ011 -HYDSYS-HYDPP-HYIPP | Pump Hydraulic Implement | 70636 | 5309 | 4700
500025550 | CLB-MP-DOZR-DZ011 -HYDSYS-HYDPP-HYFPP | Pump Hydraulic Fan | 70636 | 1285 | 4700
500025547 | CLB-MP-DOZR-DZ011 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 70636 | 13876 | 4700
500025545 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RTCYR | DZ011 Cylinder Ripper Tilt RH | 70636 | 13876 | 4700
500025544 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RTCYL | DZ011 Cylinder Ripper Tilt LH | 70636 | 5533 | 4700
500025543 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RLCYR | DZ011 Cylinder Ripper Lift RH | 70636 | 4990 | 4700
500025542 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-RLCYL | DZ011 Cylinder Ripper Lift LH | 70636 | 13876 | 4700
500025541 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BTCYR | DZ011 Cylinder Blade Tilt RH | 70636 | 6041 | 4700
500025540 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BTCYL | DZ011 Cylinder Blade Tilt LH | 70636 | 2090 | 4700
500025539 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYR | DZ011 Cylinder Blade Lift RH | 70636 | 6041 | 4700
500025538 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCYL-BLCYL | DZ011 Cylinder Blade Lift LH | 70636 | 2182 | 4700
500025536 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCVL | Implement Valves Hydraulic | 70636 | 70636 | 4700
500025535 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCON | Implement Control Hydraulic | 70636 | 70636 | 4700
500025534 | CLB-MP-DOZR-DZ011 -HYDSYS-HDCFM | Fan Cooling Motor Hydraulic | 70636 | 5309 | 4700
500025532 | CLB-MP-DOZR-DZ011 -GRSYST-GRINJ | Auto Lube Injectors | 70636 | 70636 | 4700
500025529 | CLB-MP-DOZR-DZ011 -GRSYST-ALCON | Auto Lube Controller | 70636 | 70636 | 4700
500025528 | CLB-MP-DOZR-DZ011 -GRSYST-ALBPP | Auto Lube Pump | 70636 | 70636 | 4700
500025522 | CLB-MP-DOZR-DZ011 -FDRSYS-TRKRH | Track Assembly R/H | 70636 | 5000 | 4700
500025521 | CLB-MP-DOZR-DZ011 -FDRSYS-TRKLH | Track Assembly L/H | 70636 | 5000 | 4700
500025520 | CLB-MP-DOZR-DZ011 -FDRSYS-SEGRH | Segments R/H | 70636 | 70636 | 4700
500025519 | CLB-MP-DOZR-DZ011 -FDRSYS-SEGLH | Segments L/H | 70636 | 70636 | 4700
500025518 | CLB-MP-DOZR-DZ011 -FDRSYS-FDRRH | Final Drive R/H | 70636 | 9567 | 4700
500025517 | CLB-MP-DOZR-DZ011 -FDRSYS-FDRLH | Final Drive L/H | 70636 | 9076 | 4700
500025516 | CLB-MP-DOZR-DZ011 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 70636 | 13876 | 4700
500025515 | CLB-MP-DOZR-DZ011 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 70636 | 42494 | 4700
500025513 | CLB-MP-DOZR-DZ011 -ENGINE-INTEX-TBORH | Turbocharger R/H | 70636 | 5308 | 4700
500025512 | CLB-MP-DOZR-DZ011 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 70636 | 5308 | 4700
500025509 | CLB-MP-DOZR-DZ011 -ENGINE-INTEX-AFTER | Aftercooler | 70636 | 13876 | 4700
500025506 | CLB-MP-DOZR-DZ011 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 70636 | 5308 | 4700
500025503 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-WTRPP | Water Pump Engine | 70636 | 5308 | 4700
500025502 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-THERM | Thermostats/Regulators | 70636 | 5308 | 4700
500025501 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-RADTR | Radiator Engine | 70636 | 13876 | 4700
500025499 | CLB-MP-DOZR-DZ011 -ENGINE-COSYS-COFAN | Fan Cooling System | 70636 | 42494 | 4700
500025496 | CLB-MP-DOZR-DZ011 -ENGINE | Engine Assembly, Caterpillar C27 | 70636 | 13876 | 4700
500025495 | CLB-MP-DOZR-DZ011 -ELCTLV-START-STRMR | Starter Motor | 70636 | 5308 | 4700
500025489 | CLB-MP-DOZR-DZ011 -ELCTLV-CHARG-ALTER | Alternator 24V | 70636 | 5308 | 4700
500025486 | CLB-MP-DOZR-DZ011 -BRKSTR-STVLV | Valve Hydraulic Steering | 70636 | 70636 | 4700
500025483 | CLB-MP-DOZR-DZ011 -BRKSTR-SCABR | Steering Clutch and Brake Assembly R/H | 70636 | 13876 | 4700
500025482 | CLB-MP-DOZR-DZ011 -BRKSTR-SCABL | Steering Clutch and Brake Assembly L/H | 70636 | 13876 | 4700
500025481 | CLB-MP-DOZR-DZ011 -BRKSTR-HYSPP | Pump Hydraulic Steering | 70636 | 70636 | 4700
500025593 | CLB-MP-DOZR-DZ011 | Caterpillar D10T Dozer, DZ011 | 70636 | 70636 | 4700
500146047 | CCK-MP-DRLL-DR2136-AIRSYS-ARTNK | DR2136 Receiver Tank | 13362 | 13362 | 6700
500142725 | CCK-MP-DRLL-DR2136-TRAVEL-TRKRH | Track Assembly Right Hand | 13361 | 13361 | 6700
500142724 | CCK-MP-DRLL-DR2136-TRAVEL-TRKLH | Track Assembly Left Hand | 13361 | 13361 | 6700
500142723 | CCK-MP-DRLL-DR2136-TRAVEL-TRBKR | Travel Brake Right Hand | 13361 | 13361 | 6700
500142722 | CCK-MP-DRLL-DR2136-TRAVEL-TRBKL | Travel Brake Left Hand | 13361 | 13361 | 6700
500142721 | CCK-MP-DRLL-DR2136-TRAVEL-SPRKR | Sprocket Right Hand | 13361 | 4130 | 6700
500142720 | CCK-MP-DRLL-DR2136-TRAVEL-SPRKL | Sprocket Left Hand | 13361 | 4373 | 6700
500142719 | CCK-MP-DRLL-DR2136-TRAVEL-FDRRH | Final Drive Right Hand | 13361 | 13361 | 6700
500142718 | CCK-MP-DRLL-DR2136-TRAVEL-FDRLH | Final Drive Left Hand | 13361 | 4373 | 6700
500142717 | CCK-MP-DRLL-DR2136-STRUCT-UNDER-EQUAL | Equaliser Bar | 13361 | 13361 | 6700
500142716 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 13361 | 4130 | 6700
500142715 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 13361 | 4130 | 6700
500142714 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 13361 | 13361 | 6700
500142713 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 13361 | 13361 | 6700
500142712 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 13361 | 13361 | 6700
500142711 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 13361 | 13361 | 6700
500142710 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 13361 | 13361 | 6700
500142709 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 13361 | 13361 | 6700
500142708 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 13361 | 13361 | 6700
500142707 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 13361 | 13361 | 6700
500142706 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 13361 | 13361 | 6700
500142705 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 13361 | 13361 | 6700
500142704 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 13361 | 4130 | 6700
500142703 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 13361 | 4130 | 6700
500142702 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 13361 | 13361 | 6700
500142701 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 13361 | 13361 | 6700
500142700 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 13361 | 13361 | 6700
500142699 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 13361 | 13361 | 6700
500142698 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 13361 | 13361 | 6700
500142697 | CCK-MP-DRLL-DR2136-STRUCT-TKFRR | Track Frame-Cab Side | 13361 | 13361 | 6700
500142696 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 13361 | 8814 | 6700
500142695 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 13361 | 13361 | 6700
500142694 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 13361 | 13361 | 6700
500142693 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 13361 | 13361 | 6700
500142692 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 13361 | 13361 | 6700
500142691 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 13361 | 13361 | 6700
500142690 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 13361 | 13361 | 6700
500142689 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 13361 | 13361 | 6700
500142688 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 13361 | 13361 | 6700
500142687 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 13361 | 13361 | 6700
500142686 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 13361 | 13361 | 6700
500142685 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 13361 | 13361 | 6700
500142684 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 13361 | 13361 | 6700
500142683 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 13361 | 13361 | 6700
500142682 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 13361 | 13361 | 6700
500142681 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 13361 | 13361 | 6700
500142680 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 13361 | 13361 | 6700
500142679 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 13361 | 13361 | 6700
500142678 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 13361 | 13361 | 6700
500142677 | CCK-MP-DRLL-DR2136-STRUCT-TKFRL | Track Frame-Non Cab Side | 13361 | 13361 | 6700
500142676 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 13361 | 13361 | 6700
500142675 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 13361 | 13361 | 6700
500142674 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 13361 | 13361 | 6700
500142673 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 13361 | 13361 | 6700
500142672 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 13361 | 3406 | 6700
500142671 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 13361 | 3406 | 6700
500142670 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 13361 | 3406 | 6700
500142669 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 13361 | 3406 | 6700
500142668 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 13361 | 13361 | 6700
500142667 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 13361 | 13361 | 6700
500142666 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 13361 | 3406 | 6700
500142665 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 13361 | 3406 | 6700
500142664 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 13361 | 13361 | 6700
500142663 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 13361 | 3406 | 6700
500142662 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 13361 | 3406 | 6700
500142661 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 13361 | 13361 | 6700
500142660 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 13361 | 13361 | 6700
500142659 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 13361 | 2703 | 6700
500142658 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 13361 | 2703 | 6700
500142657 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 13361 | 13361 | 6700
500142656 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-DSPAN | Deck Spanner | 13361 | 13361 | 6700
500142655 | CCK-MP-DRLL-DR2136-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 13361 | 13361 | 6700
500142654 | CCK-MP-DRLL-DR2136-STRUCT-DMAST | Mast | 13361 | 13361 | 6700
500142653 | CCK-MP-DRLL-DR2136-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 13361 | 13361 | 6700
500142652 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-SEATS | Operators Seat | 13361 | 13361 | 6700
500142651 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-AIRCN | Air Conditioning System | 13361 | 13361 | 6700
500142650 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 13361 | 13361 | 6700
500142649 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 13361 | 13361 | 6700
500142648 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 13361 | 13361 | 6700
500142647 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 13361 | 13361 | 6700
500142646 | CCK-MP-DRLL-DR2136-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 13361 | 13361 | 6700
500142645 | CCK-MP-DRLL-DR2136-STRUCT-CABIN | Operators Cabin | 13361 | 13361 | 6700
500142644 | CCK-MP-DRLL-DR2136-LUBSYS-DHTNK | DHD Reservoir | 13361 | 13361 | 6700
500142643 | CCK-MP-DRLL-DR2136-LUBSYS-DHDPP | DHD Oil Pump | 13361 | 13361 | 6700
500142642 | CCK-MP-DRLL-DR2136-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 13361 | 13361 | 6700
500142641 | CCK-MP-DRLL-DR2136-HYDSYS-PMPDG | Pump Drive Gearbox | 13361 | 13361 | 6700
500142640 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 13361 | 13361 | 6700
500142639 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 13361 | 13361 | 6700
500142638 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 13361 | 13361 | 6700
500142637 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 13361 | 13361 | 6700
500142636 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 13361 | 13361 | 6700
500142635 | CCK-MP-DRLL-DR2136-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 13361 | 13361 | 6700
500142634 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 13361 | 13361 | 6700
500142633 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 13361 | 13361 | 6700
500142632 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 13361 | 13361 | 6700
500142631 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 13361 | 13361 | 6700
500142630 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 13361 | 13361 | 6700
500142629 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 13361 | 13361 | 6700
500142628 | CCK-MP-DRLL-DR2136-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 13361 | 13361 | 6700
500142627 | CCK-MP-DRLL-DR2136-HYDSYS-HDTNK | Tank Hydraulic | 13361 | 13361 | 6700
500142626 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 13361 | 1840 | 6700
500142625 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 13361 | 4910 | 6700
500142624 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 13361 | 13361 | 6700
500142623 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 13361 | 13361 | 6700
500142622 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 13361 | 13361 | 6700
500142621 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 13361 | 13361 | 6700
500142620 | CCK-MP-DRLL-DR2136-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 13361 | 13361 | 6700
500142619 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 13361 | 13361 | 6700
500142618 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 13361 | 13361 | 6700
500142617 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 13361 | 7669 | 6700
500142616 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 13361 | 13361 | 6700
500142615 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 13361 | 13361 | 6700
500142614 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 13361 | 13361 | 6700
500142613 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 13361 | 13361 | 6700
500142612 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 13361 | 8546 | 6700
500142611 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 13361 | 13361 | 6700
500142610 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 13361 | 5509 | 6700
500142609 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 13361 | 13361 | 6700
500142608 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 13361 | 8077 | 6700
500142607 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 13361 | 13361 | 6700
500142606 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 13361 | 13361 | 6700
500142605 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 13361 | 13361 | 6700
500142604 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 13361 | 13361 | 6700
500142603 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 13361 | 13361 | 6700
500142602 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 13361 | 13361 | 6700
500142601 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 13361 | 13361 | 6700
500142600 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 13361 | 13361 | 6700
500142599 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 13361 | 13361 | 6700
500142598 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 13361 | 13361 | 6700
500142597 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 13361 | 13361 | 6700
500142596 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 13361 | 13361 | 6700
500142595 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 13361 | 13361 | 6700
500142594 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 13361 | 13361 | 6700
500142593 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 13361 | 6120 | 6700
500142592 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 13361 | 13361 | 6700
500142591 | CCK-MP-DRLL-DR2136-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 13361 | 13361 | 6700
500142590 | CCK-MP-DRLL-DR2136-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 13361 | 13361 | 6700
500142589 | CCK-MP-DRLL-DR2136-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 13361 | 13361 | 6700
500142588 | CCK-MP-DRLL-DR2136-GRSYST-RTTNK | Rod Thread Lube Reservoir | 13361 | 13361 | 6700
500142587 | CCK-MP-DRLL-DR2136-GRSYST-RTLPP | Rod Thread lube Pump | 13361 | 13361 | 6700
500142586 | CCK-MP-DRLL-DR2136-GRSYST-RTINJ | Rod Thread Grease Injector | 13361 | 13361 | 6700
500142585 | CCK-MP-DRLL-DR2136-GRSYST-GRTNK | Auto Lube Reservoir | 13361 | 13361 | 6700
500142584 | CCK-MP-DRLL-DR2136-GRSYST-GRINJ | Auto Lube Injectors | 13361 | 13361 | 6700
500142583 | CCK-MP-DRLL-DR2136-GRSYST-ALBPP | Auto lube Pump | 13361 | 13361 | 6700
500142582 | CCK-MP-DRLL-DR2136-FRSUPP | Fire Suppression System | 13361 | 13361 | 6700
500142581 | CCK-MP-DRLL-DR2136-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 13361 | 8815 | 6700
500142580 | CCK-MP-DRLL-DR2136-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 13361 | 8815 | 6700
500142579 | CCK-MP-DRLL-DR2136-ENGINE-INTEX-EXHST | Exhaust System Engine | 13361 | 13361 | 6700
500142578 | CCK-MP-DRLL-DR2136-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 13361 | 13361 | 6700
500142577 | CCK-MP-DRLL-DR2136-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 13361 | 13361 | 6700
500142576 | CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 13361 | 8815 | 6700
500142575 | CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 13361 | 13361 | 6700
500142574 | CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 13361 | 13361 | 6700
500142573 | CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 13361 | 13361 | 6700
500142572 | CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 13361 | 8815 | 6700
500142571 | CCK-MP-DRLL-DR2136-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 13361 | 13361 | 6700
500142570 | CCK-MP-DRLL-DR2136-ENGINE-COSYS-WTRPP | Water Pump Engine | 13361 | 8815 | 6700
500142569 | CCK-MP-DRLL-DR2136-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 13361 | 8815 | 6700
500142568 | CCK-MP-DRLL-DR2136-ENGINE-COSYS-RADTR | Radiator Engine | 13361 | 13361 | 6700
500142567 | CCK-MP-DRLL-DR2136-ENGINE | Engine Assembly CAT C32 | 13361 | 8815 | 6700
500142566 | CCK-MP-DRLL-DR2136-ELCTLV-START-STMRH | Starter Motor Engine Right | 13361 | 6120 | 6700
500142565 | CCK-MP-DRLL-DR2136-ELCTLV-START-STMLH | Starter Motor Engine Left | 13361 | 6120 | 6700
500142564 | CCK-MP-DRLL-DR2136-ELCTLV-HARNS | Wiring Harness | 13361 | 13361 | 6700
500142563 | CCK-MP-DRLL-DR2136-ELCTLV-CHARG-BATTY | Batteries Engine | 13361 | 13361 | 6700
500142562 | CCK-MP-DRLL-DR2136-ELCTLV-CHARG-ALTER | Alternator 24V | 13361 | 8815 | 6700
500142561 | CCK-MP-DRLL-DR2136-DSTSUP-WTRPP | Dynaset Water Pump | 13361 | 1577 | 6700
500142560 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKS | Water Tank Secondary | 13361 | 13361 | 6700
500142559 | CCK-MP-DRLL-DR2136-DSTSUP-WTNKP | Water Tank Primary | 13361 | 13361 | 6700
500142558 | CCK-MP-DRLL-DR2136-DSTSUP-WSHPP | Pump Wash Down | 13361 | 13361 | 6700
500142557 | CCK-MP-DRLL-DR2136-DSTSUP-WSHMT | Engine Wash Down | 13361 | 13361 | 6700
500142556 | CCK-MP-DRLL-DR2136-COOLER-HDOCO | Hydraulic Oil Cooler Core | 13361 | 13361 | 6700
500142555 | CCK-MP-DRLL-DR2136-COOLER-COOCO | Compressor Oil Cooler Core | 13361 | 13361 | 6700
500142554 | CCK-MP-DRLL-DR2136-COOLER | Cooler Module Assembly | 13361 | 13361 | 6700
500142553 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 13361 | 8815 | 6700
500142552 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 13361 | 2706 | 6700
500142551 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 13361 | 4800 | 6700
500142550 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR | Air Receiver Pressure Vessel | 13361 | 13361 | 6700
500142549 | CCK-MP-DRLL-DR2136-AIRSYS-COMPR | Main Air Compressor | 13361 | 8815 | 6700
500142548 | CCK-MP-DRLL-DR2136-ADSYST-HARNC | ADS Harnesses & Connectors | 13361 | 13361 | 6700
500142547 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 13361 | 13361 | 6700
500142546 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 13361 | 13361 | 6700
500142545 | CCK-MP-DRLL-DR2136-ADSYST-ADSPR | ADS HazTech | 13361 | 13361 | 6700
500142544 | CCK-MP-DRLL-DR2136-ADSYST-ADSPO | ADS Global Positioning System | 13361 | 13361 | 6700
500142543 | CCK-MP-DRLL-DR2136-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 13361 | 13361 | 6700
500142522 | CCK-MP-DRLL-DR2136-ADSYST-ADSIS | ADS Instrumentation & Sensors | 13361 | 13361 | 6700
500142521 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 13361 | 13361 | 6700
500142520 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 13361 | 13361 | 6700
500142519 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 13361 | 13361 | 6700
500142518 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 13361 | 13361 | 6700
500142517 | CCK-MP-DRLL-DR2136-ADSYST-ADSHW | ADS Hardware & Control System | 13361 | 13361 | 6700
500142516 | CCK-MP-DRLL-DR2136-ADSYST | ADS Autonomous Rig Control System | 13361 | 13361 | 6700
500142515 | CCK-MP-DRLL-DR2136 | CAT MD6310 Drill DR2136 | 13361 | 13361 | 6700
500146040 | CLB-MP-DRLL-DR060 -AIRSYS-ARTNK | DR060 Receiver Tank | 69618 | 10169 | 6300
500138260 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS-HARCO | Electrical Harness Control | 69618 | 69618 | 6300
500133727 | CLB-MP-DRLL-DR060 -ADSYST-HARNC | ADS Harnesses & Connectors | 69618 | 1221 | 6300
500133726 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR-LIDAR | ADS LiDAR System | 69618 | 33676 | 6300
500133725 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 69618 | 8490 | 6300
500133724 | CLB-MP-DRLL-DR060 -ADSYST-ADSPR | ADS HazTech | 69618 | 33676 | 6300
500133723 | CLB-MP-DRLL-DR060 -ADSYST-ADSPO | ADS Global Positioning System | 69618 | 33676 | 6300
500133722 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 69618 | 33676 | 6300
500133721 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 69618 | 33676 | 6300
500133720 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 69618 | 33676 | 6300
500133719 | CLB-MP-DRLL-DR060 -ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 69618 | 33676 | 6300
500133472 | CLB-MP-DRLL-DR060 -ADSYST | Autonomous Drilling System | 69618 | 33676 | 6300
500132385 | CLB-MP-DRLL-DR060 -ELCTLV-HARNS | Wiring Harness | 69618 | 69618 | 6300
500113549 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-AFRME | DR060 Tower A Frame | 69618 | 31403 | 6300
500107956 | CLB-MP-DRLL-DR060 -AIRSYS-EARCS-BDVVE | DR060 Blowdown Valve | 69618 | 69618 | 6300
500107955 | CLB-MP-DRLL-DR060 -AIRSYS-EARCS-ACTBD | DR060 Actuator Blowdown Valve | 69618 | 2790 | 6300
500107954 | CLB-MP-DRLL-DR060 -AIRSYS-EARCS-BFVVE | DR060 Comp Butterfly Valve | 69618 | 69618 | 6300
500107953 | CLB-MP-DRLL-DR060 -AIRSYS-EARCS-ACTBV | DR060 Actuator Butterfly Valve | 69618 | 2790 | 6300
500102163 | CLB-MP-DRLL-DR060 -TRAVEL-TRKRH | DR060 Track Assembly - CS | 69618 | 5134 | 6300
500102162 | CLB-MP-DRLL-DR060 -TRAVEL-TRKLH | DR060 Track Assembly - NCS | 69618 | 5134 | 6300
500102161 | CLB-MP-DRLL-DR060 -TRAVEL-TRBKR | DR060 Travel Brake R/H | 69618 | 69618 | 6300
500102160 | CLB-MP-DRLL-DR060 -TRAVEL-TRBKL | DR060 Travel Brake L/H | 69618 | 69618 | 6300
500102159 | CLB-MP-DRLL-DR060 -TRAVEL-SPRKR | DR060 Sprocket - CS | 69618 | 5134 | 6300
500102158 | CLB-MP-DRLL-DR060 -TRAVEL-SPRKL | DR060 Sprocket - NCS | 69618 | 5134 | 6300
500102157 | CLB-MP-DRLL-DR060 -TRAVEL | DR060 Travel System | 69618 | 69618 | 6300
500102156 | CLB-MP-DRLL-DR060 -STRUCT-WINCH-WIHLF | DR060 Winch System Hose Lines Fittings | 69618 | 69618 | 6300
500102155 | CLB-MP-DRLL-DR060 -STRUCT-UNDER | DR060 Undercarriage | 69618 | 69618 | 6300
500102154 | CLB-MP-DRLL-DR060 -STRUCT-TOWER | DR060 Tower | 69618 | 25954 | 6300
500102153 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 69618 | 5134 | 6300
500102152 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 69618 | 5134 | 6300
500102151 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 69618 | 5134 | 6300
500102150 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 69618 | 5134 | 6300
500102149 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF13 | Roller Load Pos 13 Double Flange CS | 69618 | 5134 | 6300
500102148 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF12 | Roller Load Pos 12 Double Flange CS | 69618 | 5134 | 6300
500102147 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF11 | Roller Load Pos 11 Double Flange CS | 69618 | 5134 | 6300
500102146 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF10 | Roller Load Pos 10 Double Flange CS | 69618 | 5134 | 6300
500102145 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF09 | Roller Load Pos 9 Double Flange CS | 69618 | 5134 | 6300
500102144 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF08 | Roller Load Pos 8 Double Flange CS | 69618 | 5134 | 6300
500102143 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF07 | Roller Load Pos 7 Double Flange CS | 69618 | 5134 | 6300
500102142 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF06 | Roller Load Pos 6 Double Flange CS | 69618 | 5134 | 6300
500102141 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-RDF05 | Roller Load Pos 5 Double Flange CS | 69618 | 5134 | 6300
500102140 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-IDLRH | DR060 Idler Track - CS | 69618 | 5134 | 6300
500102139 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-CARRR | DR060 Roller Carrier Rear - CS | 69618 | 5134 | 6300
500102138 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-CARRM | DR060 Roller Carrier Middle - CS | 69618 | 5134 | 6300
500102137 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-CARRF | DR060 Roller Carrier Front - CS | 69618 | 5134 | 6300
500102136 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR | DR060 Track Frame - CS | 69618 | 5134 | 6300
500102135 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 69618 | 5134 | 6300
500102134 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 69618 | 5134 | 6300
500102133 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 69618 | 5134 | 6300
500102132 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 69618 | 5134 | 6300
500102131 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF13 | Roller Load Pos 13 Double Flange NCS | 69618 | 5134 | 6300
500102130 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF12 | Roller Load Pos 12 Double Flange NCS | 69618 | 5134 | 6300
500102129 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF11 | Roller Load Pos 11 Double Flange NCS | 69618 | 5134 | 6300
500102128 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF10 | Roller Load Pos 10 Double Flange NCS | 69618 | 5134 | 6300
500102127 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF09 | Roller Load Pos 9 Double Flange NCS | 69618 | 5134 | 6300
500102126 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF08 | Roller Load Pos 8 Double Flange NCS | 69618 | 5134 | 6300
500102125 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF07 | Roller Load Pos 7 Double Flange NCS | 69618 | 5134 | 6300
500102124 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF06 | Roller Load Pos 6 Double Flange NCS | 69618 | 5134 | 6300
500102123 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-RDF05 | Roller Load Pos 5 Double Flange NCS | 69618 | 5134 | 6300
500102122 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-IDLLH | DR060 Idler Track NCS | 69618 | 5134 | 6300
500102121 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-CARLR | DR060 Roller Carrier Rear - NCS | 69618 | 5134 | 6300
500102120 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-CARLM | DR060 Roller Carrier Middle - NCS | 69618 | 5134 | 6300
500102119 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-CARLF | DR060 Roller Carrier Front - NCS | 69618 | 5134 | 6300
500102118 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL | DR060 Track Frame L/H | 69618 | 5134 | 6300
500102117 | CLB-MP-DRLL-DR060 -STRUCT-STLAD-SLFXD | DR060 Fixed Steps and Ladders | 69618 | 69618 | 6300
500102116 | CLB-MP-DRLL-DR060 -STRUCT-STLAD-SLAUT | DR060 Automatic Access Systems | 69618 | 69618 | 6300
500102115 | CLB-MP-DRLL-DR060 -STRUCT-STLAD | DR060 Steps and ladders | 69618 | 69618 | 6300
500102114 | CLB-MP-DRLL-DR060 -STRUCT-PLHAN | DR060 Platforms and Hand Rails | 69618 | 69618 | 6300
500102113 | CLB-MP-DRLL-DR060 -STRUCT-DRSTR-SHSUB | DR060 ShockSub Foremost | 69618 | 69618 | 6300
500102112 | CLB-MP-DRLL-DR060 -STRUCT-DRSTR | DR060 Drill String | 69618 | 69618 | 6300
500102111 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-SBELT | DR060 Seat belt | 69618 | 69618 | 6300
500102110 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-GLASS | DR060 Glass | 69618 | 69618 | 6300
500102109 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-CABPR | DR060 Cabin Pressurisation System | 69618 | 69618 | 6300
500102108 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-CABES | DR060 Cabin Entertainment System | 69618 | 69618 | 6300
500102107 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-CABCO | DR060 Cabin Controls | 69618 | 69618 | 6300
500102106 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-AIRCN | DR060 Air Conditioning System | 69618 | 9798 | 6300
500102105 | CLB-MP-DRLL-DR060 -STRUCT-CABIN | DR060 Operators Cabin | 69618 | 69618 | 6300
500102104 | CLB-MP-DRLL-DR060 -STRUCT | DR060 Structure | 69618 | 17116 | 6300
500102102 | CLB-MP-DRLL-DR060 -MANGMT-UMMMC | DR060 Mine Monitoring and Control | 69618 | 69618 | 6300
500102101 | CLB-MP-DRLL-DR060 -MANGMT-UMENG | DR060 Engine Management System | 69618 | 69618 | 6300
500102099 | CLB-MP-DRLL-DR060 -MANGMT-UMRIG | DR060 Board Control System | 69618 | 69618 | 6300
500102098 | CLB-MP-DRLL-DR060 -MANGMT | DR060 Unit Management | 69618 | 69618 | 6300
500102097 | CLB-MP-DRLL-DR060 -LUBSYS-DHTNK | DR060 DHD Reservoir | 69618 | 69618 | 6300
500102096 | CLB-MP-DRLL-DR060 -LUBSYS-DHTMR | DR060 DHD Timer | 69618 | 69618 | 6300
500102095 | CLB-MP-DRLL-DR060 -LUBSYS-DHHLF | DR060 DHD Hose Lines & Fittings | 69618 | 69618 | 6300
500102094 | CLB-MP-DRLL-DR060 -LUBSYS-DHELC | DR060 DHD Electrical | 69618 | 69618 | 6300
500102093 | CLB-MP-DRLL-DR060 -LUBSYS | DR060 Lubrication System DHD | 69618 | 69618 | 6300
500102092 | CLB-MP-DRLL-DR060 -HYDSYS-HYDPP | DR060 Pumps Hydraulic | 69618 | 69618 | 6300
500102091 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV | DR060 Valves Hydraulic | 69618 | 69618 | 6300
500102090 | CLB-MP-DRLL-DR060 -HYDSYS-HDTNK | DR060 Tank Hydraulic | 69618 | 69618 | 6300
500102089 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT | DR060 Motors Hydraulic | 69618 | 69618 | 6300
500102088 | CLB-MP-DRLL-DR060 -HYDSYS-HDHLF | Hydraulic System Hose Lines Fittings | 69618 | 69618 | 6300
500102087 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-RSSCY | DR060 Cylinder Swing Rod Support | 69618 | 25954 | 6300
500102086 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-RSCCY | DR060 Cylinder Rod Support Clamp | 69618 | 25954 | 6300
500102085 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-DSRCY | DR060 Cylinder Dust Skirt Raise | 69618 | 18317 | 6300
500102084 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-CSCYU | DR060 Cylinder Carousel Swing Upper | 69618 | 12369 | 6300
500102083 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-CSCYL | DR060 Cylinder Carousel Swing Lower | 69618 | 25954 | 6300
500102082 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-CRTCY | Cylinder Carousel Rotation indexing | 69618 | 25954 | 6300
500102081 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-BWSCY | DR060 Cylinder Swing Breakout Wrench | 69618 | 25954 | 6300
500102080 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-BWRCY | DR060 Cylinder Rotate Breakout Wrench | 69618 | 25954 | 6300
500102079 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-BWCCY | DR060 Cylinder Clamp Breakout Wrench | 69618 | 25954 | 6300
500102078 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-BKOCY | DR060 Cylinder Breakout Fork | 69618 | 25954 | 6300
500102077 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL | DR060 Cylinders Hydraulic | 69618 | 5877 | 6300
500102076 | CLB-MP-DRLL-DR060 -HYDSYS-COFAN | DR060 Fan Cooling | 69618 | 69618 | 6300
500102075 | CLB-MP-DRLL-DR060 -HYDSYS | DR060 Hydraulic Systems | 69618 | 69618 | 6300
500102074 | CLB-MP-DRLL-DR060 -GRSYST-RTTNK | DR060 Rod Thread Lube Reservoir | 69618 | 69618 | 6300
500102073 | CLB-MP-DRLL-DR060 -GRSYST-RTINJ | DR060 Rod Thread Grease Injector | 69618 | 69618 | 6300
500102072 | CLB-MP-DRLL-DR060 -GRSYST-RTHLF | Rod Thread Lube Hoses Line Fittings | 69618 | 69618 | 6300
500102071 | CLB-MP-DRLL-DR060 -GRSYST-RTELC | DR060 Rod Thread Lube Electrical | 69618 | 69618 | 6300
500102070 | CLB-MP-DRLL-DR060 -GRSYST-GRTNK | DR060 Auto Lube Reservoir | 69618 | 69618 | 6300
500102069 | CLB-MP-DRLL-DR060 -GRSYST-GRINJ | DR060 Auto Lube Injectors | 69618 | 69618 | 6300
500102068 | CLB-MP-DRLL-DR060 -GRSYST-ALHLF | DR060 Auto Lube Hoses Line Fittings | 69618 | 69618 | 6300
500102067 | CLB-MP-DRLL-DR060 -GRSYST-ALELC | DR060 Auto Lube Electrical | 69618 | 69618 | 6300
500102066 | CLB-MP-DRLL-DR060 -GRSYST-ALCON | DR060 Auto Lube Controller | 69618 | 69618 | 6300
500102065 | CLB-MP-DRLL-DR060 -GRSYST | DR060 Grease lubrication System | 69618 | 14369 | 6300
500102064 | CLB-MP-DRLL-DR060 -FRSUPP-FSMAN-EXTIN | DR060 Hand Held Fire Extinguisher | 69618 | 69618 | 6300
500102063 | CLB-MP-DRLL-DR060 -FRSUPP-FSMAN | DR060 Fire Suppression Manual | 69618 | 69618 | 6300
500102062 | CLB-MP-DRLL-DR060 -FRSUPP-FSAUT-FSHLF | DR060 Fire Sup Hose Lines Fittings | 69618 | 69618 | 6300
500102061 | CLB-MP-DRLL-DR060 -FRSUPP-FSAUT-FFOAM | DR060 Fire Suppression Foam | 69618 | 69618 | 6300
500102060 | CLB-MP-DRLL-DR060 -FRSUPP-FSAUT | DR060 Fire Suppression Automatic | 69618 | 69618 | 6300
500102059 | CLB-MP-DRLL-DR060 -FRSUPP-FSALM | DR060 Fire System Alarm | 69618 | 69618 | 6300
500102058 | CLB-MP-DRLL-DR060 -ENGINE-LUBSY | DR060 Engine Lubrication System | 69618 | 69618 | 6300
500102057 | CLB-MP-DRLL-DR060 -ENGINE-INTEX-EXHST | DR060 Exhaust System Engine | 69618 | 69618 | 6300
500102056 | CLB-MP-DRLL-DR060 -ENGINE-INTEX-AIRFL | DR060 Air Filtration Systems Engine | 69618 | 69618 | 6300
500102055 | CLB-MP-DRLL-DR060 -ENGINE-INTEX | DR060 Engine Intake and Exhaust System | 69618 | 69618 | 6300
500102054 | CLB-MP-DRLL-DR060 -ENGINE-FUSYS-FULTK | DR060 Fuel Tank Engine | 69618 | 69618 | 6300
500102053 | CLB-MP-DRLL-DR060 -ENGINE-FUSYS-FUHLF | Fuel System Hoses/Lines and Fittings | 69618 | 69618 | 6300
500102052 | CLB-MP-DRLL-DR060 -ENGINE-FUSYS | DR060 Engine Fuel System | 69618 | 69618 | 6300
500102051 | CLB-MP-DRLL-DR060 -ENGINE-COSYS-CSHLF | Cooling System Hoses/Lines and Fittings | 69618 | 69618 | 6300
500102050 | CLB-MP-DRLL-DR060 -ENGINE-COSYS | DR060 Engine Cooling System | 69618 | 69618 | 6300
500102049 | CLB-MP-DRLL-DR060 -ELCTLV-START | DR060 Electrical Starting System | 69618 | 69618 | 6300
500102048 | CLB-MP-DRLL-DR060 -ELCTLV-LIGHT | DR060 Lighting Low Voltage | 69618 | 69618 | 6300
500102047 | CLB-MP-DRLL-DR060 -ELCTLV-CONTL | DR060 Electrical Controls Low Volatge | 69618 | 69618 | 6300
500102046 | CLB-MP-DRLL-DR060 -ELCTLV-CHARG-BATTY | DR060 Batteries Engine | 69618 | 5877 | 6300
500102045 | CLB-MP-DRLL-DR060 -ELCTLV-CHARG | DR060 Charging System | 69618 | 69618 | 6300
500102044 | CLB-MP-DRLL-DR060 -ELCTLV | DR060 Electrical System Low Voltage 24V | 69618 | 69618 | 6300
500102043 | CLB-MP-DRLL-DR060 -DSTSUP-WTTNK | DR060 Water Tank | 69618 | 17116 | 6300
500102042 | CLB-MP-DRLL-DR060 -DSTSUP-WTHLF | Water Inj System Hose Lines Fittings | 69618 | 69618 | 6300
500102041 | CLB-MP-DRLL-DR060 -DSTSUP-DSTSK | DR060 Dust Skirt | 69618 | 69618 | 6300
500102040 | CLB-MP-DRLL-DR060 -DSTSUP | DR060 Dust Suppresion | 69618 | 69618 | 6300
500102039 | CLB-MP-DRLL-DR060 -COOLER-RADTR | DR060 Radiator Core | 69618 | 25954 | 6300
500102038 | CLB-MP-DRLL-DR060 -COOLER-HDOCO | DR060 Hydraulic Oil Cooler Core | 69618 | 25954 | 6300
500102037 | CLB-MP-DRLL-DR060 -COOLER-COOCO | DR060 Compressor Oil Cooler Core | 69618 | 12482 | 6300
500102036 | CLB-MP-DRLL-DR060 -COMMUN-RADIO | DR060 Two Way Radio | 69618 | 69618 | 6300
500102035 | CLB-MP-DRLL-DR060 -COMMUN | DR060 Communications | 69618 | 69618 | 6300
500102034 | RED-CB-MP-DRLL-DR060 -AOS | DR060 Drill Rig Air Oil Separator | 69618 | 69618 | 6700
500102033 | CLB-MP-DRLL-DR060 -AIRSYS-COMPR-PNHLF | Pneumatic System Hoses Lines Fittings | 69618 | 69618 | 6300
500102032 | CLB-MP-DRLL-DR060 -AIRSYS | DR060 Air Systems | 69618 | 69618 | 6300
500077138 | CLB-MP-DRLL-DR060 -FRSUPP | DR060 Fire Suppression System | 69618 | 69618 | 6300
500077137 | CLB-MP-DRLL-DR060 -DSTSUP-WTRPP | DR060 Pump Water Injection | 69618 | 1540 | 6300
500077136 | CLB-MP-DRLL-DR060 -GRSYST-RTLPP | DR060 Rod Thread lube Pump | 69618 | 56678 | 6300
500077135 | CLB-MP-DRLL-DR060 -GRSYST-ALBPP | DR060 Auto lube Pump | 69618 | 15526 | 6300
500077134 | CLB-MP-DRLL-DR060 -LUBSYS-DHDPP | DR060 DHD Oil Pump | 69618 | 56678 | 6300
500077133 | CLB-MP-DRLL-DR060 -STRUCT-WINCH-WINRP | DR060 Winch Rope | 69618 | 69618 | 6300
500077132 | CLB-MP-DRLL-DR060 -STRUCT-WINCH-WINSH | DR060 Winch Sheaves | 69618 | 69618 | 6300
500077131 | CLB-MP-DRLL-DR060 -STRUCT-WINCH | DR060 Winch Assembly | 69618 | 69618 | 6300
500077130 | CLB-MP-DRLL-DR060 -STRUCT-UNDER-YKOSC | DR060 Yoke Oscillation | 69618 | 7361 | 6300
500077129 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-BOFKA | DR060 Breakout Fork Sliding Assembly | 69618 | 25954 | 6300
500077128 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-BOWRH | DR060 Breakout Wrench Assy | 69618 | 5134 | 6300
500077127 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-CARAS | DR060 Rod Changer / Carousel | 69618 | 5134 | 6300
500077126 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-RDSPT | DR060 Rod support | 69618 | 5134 | 6300
500077125 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SCBTR | DR060 Screw Jack Cable Tension R/H | 69618 | 5134 | 6300
500077124 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SCBTL | DR060 Screw Jack Cable Tension L/H | 69618 | 5134 | 6300
500077123 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SHAUR | DR060 Sheave Assembly Upper R/H | 69618 | 5134 | 6300
500077122 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SHAUL | DR060 Sheave Assembly Upper L/H | 69618 | 5134 | 6300
500077121 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SHALR | DR060 Sheave Assembly Lower R/H | 69618 | 5134 | 6300
500077120 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-SHALL | DR060 Sheave Assembly Lower L/H | 69618 | 5134 | 6300
500077119 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-CSHAR | DR060 Carriage Sheave Assembly R/H | 69618 | 5134 | 6300
500077118 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-CSHAL | DR060 Carriage Sheave Assembly L/H | 69618 | 5134 | 6300
500077117 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PBCBR | DR060 Pullback Cable R/H | 69618 | 5134 | 6300
500077116 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PBCBL | DR060 Pullback Cable L/H | 69618 | 5134 | 6300
500077115 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PDCBR | DR060 Pulldown Cable R/H | 69618 | 5134 | 6300
500077114 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PDCBL | DR060 Pulldown Cable L/H | 69618 | 5134 | 6300
500077113 | CLB-MP-DRLL-DR060 -STRUCT-TOWER-PWRHD | DR060 Gearbox Power Head | 69618 | 5134 | 6300
500077112 | CLB-MP-DRLL-DR060 -STRUCT-TKFRR-ADJGR | DR060 Track Adjuster Grease R/H | 69618 | 25954 | 6300
500077111 | CLB-MP-DRLL-DR060 -STRUCT-TKFRL-ADJGL | DR060 Track Adjuster Grease L/H | 69618 | 25954 | 6300
500077110 | CLB-MP-DRLL-DR060 -STRUCT-CRANE | DR060 Hiab Crane | 69618 | 15526 | 6300
500077109 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-SEATS | DR060 Operators Seat | 69618 | 14152 | 6300
500077108 | CLB-MP-DRLL-DR060 -STRUCT-CABIN-ACCOM | DR060 Air Conditioning Compressor | 69618 | 30874 | 6300
500077107 | CLB-MP-DRLL-DR060 -HYDSYS-COFAN-FCCAC | DR060 Fan Cooling Charge Air Cooler | 69618 | 11648 | 6300
500077106 | CLB-MP-DRLL-DR060 -HYDSYS-COFAN-FCCMA | DR060 Fan Cooling Cooler Module Assy | 69618 | 6713 | 6300
500077105 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-ACONM | DR060 Motor Hyd Air Con | 69618 | 326 | 6300
500077104 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MWINJ | DR060 Motor Water Injection Pump | 69618 | 32786 | 6300
500077103 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MWINC | DR060 Motor Winch | 69618 | 69618 | 6300
500077102 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MRTNR | DR060 Motor Rotation R/H | 69618 | 5134 | 6300
500077101 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MRTNL | DR060 Motor Rotation L/H | 69618 | 5134 | 6300
500077100 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTR | DR060 Mtr 4.9 CID ScrewJack Tension R/H | 69618 | 5134 | 6300
500077099 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MSJTL | DR060 Mtr 4.9 CID ScrewJack Tension L/H | 69618 | 5134 | 6300
500077098 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MPRPR | DR060 Motor Propel R/H | 69618 | 5134 | 6300
500077097 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MPRPL | DR060 Motor Propel L/H | 69618 | 5134 | 6300
500077096 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MFCAC | DR060 Motor Fan CAC Cooler | 69618 | 7361 | 6300
500077095 | CLB-MP-DRLL-DR060 -HYDSYS-HDMOT-MFMCA | DR060 Motor Fan Main Cooler Assy | 69618 | 18158 | 6300
500077094 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VWIBR | DR060 Winch Valve Brake Hyd | 69618 | 69618 | 6300
500077093 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVTNC | DR060 Valve Tension Cable | 69618 | 5134 | 6300
500077092 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDPC | DR060 Valve Drill/Propel Control | 69618 | 5892 | 6300
500077091 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDVR | DR060 Valve Diverter RH | 69618 | 7361 | 6300
500077090 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDVL | DR060 Valve Diverter LH | 69618 | 7361 | 6300
500077089 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVCNB | DR060 Valve Counter Balance | 69618 | 31403 | 6300
500077088 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVDCB | DR060 Valve Dual Counter Balance | 69618 | 20745 | 6300
500077087 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VV11S | DR060 Valve Stacking 11 spool | 69618 | 5134 | 6300
500077086 | CLB-MP-DRLL-DR060 -HYDSYS-HDVLV-VVS8S | DR060 Valve Stacking 8 spool | 69618 | 1869 | 6300
500077085 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-CTCYR | DR060 Cylinder Cable Tension R/H | 69618 | 5134 | 6300
500077084 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-CTCYL | DR060 Cylinder Cable Tension L/H | 69618 | 5134 | 6300
500077083 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-FDCYR | DR060 Cylinder Feed Hyd R/H | 69618 | 5134 | 6300
500077082 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-FDCYL | DR060 Cylinder Feed Hyd L/H | 69618 | 5134 | 6300
500077081 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRR | DR060 Cylinder Jack Leg R/H/R | 69618 | 12921 | 6300
500077080 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYLR | DR060 Cylinder Jack Leg L/H/R | 69618 | 10885 | 6300
500077079 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYRF | DR060 Cylinder Jack Leg R/H/F | 69618 | 2790 | 6300
500077078 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-JCYLF | DR060 Cylinder Jack Leg L/H/F | 69618 | 1869 | 6300
500077077 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TACYR | DR060 Cyl Tower Support Angle Lock R/H | 69618 | 5134 | 6300
500077076 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TACYL | DR060 Cyl Tower Support Angle Lock L/H | 69618 | 5134 | 6300
500077075 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TLCYR | DR060 Cylinder Tower locking R/H | 69618 | 5134 | 6300
500077074 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TLCYL | DR060 Cylinder Tower locking L/H | 69618 | 5134 | 6300
500077073 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYR | DR060 Cylinder Tower Raise R/H | 69618 | 5134 | 6300
500077072 | CLB-MP-DRLL-DR060 -HYDSYS-HDCYL-TRCYL | DR060 Cylinder Tower Raise L/H | 69618 | 5134 | 6300
500077071 | CLB-MP-DRLL-DR060 -HYDSYS-HYDPP-PRHDL | DR060 Pump Self Revers Power Head Lube | 69618 | 12364 | 6300
500077070 | CLB-MP-DRLL-DR060 -HYDSYS-HYDPP-MNPP3 | DR060 Pump Hydraulic triple | 69618 | 4974 | 6300
500077069 | CLB-MP-DRLL-DR060 -HYDSYS-HYDPP-MNPP2 | DR060 Pump Hydraulic P7,9A CONT | 69618 | 7361 | 6300
500077068 | CLB-MP-DRLL-DR060 -HYDSYS-HYDPP-MNPP1 | DR060 Pump Hydraulic P7,9A CONT | 69618 | 7361 | 6300
500077067 | CLB-MP-DRLL-DR060 -HYDSYS-PMPDR-DRSHT | DR060 Pump Drive Drive Shaft | 69618 | 2640 | 6300
500077066 | CLB-MP-DRLL-DR060 -HYDSYS-PMPDR | DR060 Pump Drive Gearbox 3 Hole | 69618 | 2816 | 6300
500077065 | CLB-MP-DRLL-DR060 -COOLER | DR060 Cooler Module Assembly | 69618 | 25954 | 6300
500077064 | CLB-MP-DRLL-DR060 -AIRSYS-COMPR-COUPL | DR060 Compressor Coupling Ringfeeder | 69618 | 7361 | 6300
500077063 | CLB-MP-DRLL-DR060 -AIRSYS-COMPR | DR060 Main Air Compressor | 69618 | 12369 | 6300
500077062 | CLB-MP-DRLL-DR060 -TRAVEL-FDRRH | DR060 Final Drive R/H | 69618 | 5134 | 6300
500077061 | CLB-MP-DRLL-DR060 -TRAVEL-FDRLH | DR060 Final Drive L/H | 69618 | 5134 | 6300
500077060 | CLB-MP-DRLL-DR060 -ELCTLV-START-STMRH | DR060 Starter Motor Engine Right | 69618 | 2205 | 6300
500077059 | CLB-MP-DRLL-DR060 -ELCTLV-START-STMLH | DR060 Starter Motor Engine Left | 69618 | 3223 | 6300
500077058 | CLB-MP-DRLL-DR060 -ELCTLV-CHARG-ALTER | DR060 Alternator 24V | 69618 | 3005 | 6300
500077057 | CLB-MP-DRLL-DR060 -ENGINE-FUSYS-FULCO | DR060 Fuel Cooler Engine | 69618 | 38024 | 6300
500077056 | CLB-MP-DRLL-DR060 -ENGINE-FUSYS-FUINJ | DR060 Fuel Injectors Engine | 69618 | 7361 | 6300
500077055 | CLB-MP-DRLL-DR060 -ENGINE-FUSYS-FULPP | DR060 Fuel Pump Engine | 69618 | 16445 | 6300
500077054 | CLB-MP-DRLL-DR060 -ENGINE-INTEX-CACAS | DR060 Charge Air Cooler | 69618 | 18158 | 6300
500077053 | CLB-MP-DRLL-DR060 -ENGINE-INTEX-TBOP2 | DR060 Turbocharger Engine | 69618 | 6985 | 6300
500077052 | CLB-MP-DRLL-DR060 -ENGINE-INTEX-TBOP1 | DR060 Turbocharger Engine | 69618 | 6985 | 6300
500077051 | CLB-MP-DRLL-DR060 -ENGINE-COSYS-THERM | DR060 Thermostats/Regulators Engine | 69618 | 16445 | 6300
500077040 | CLB-MP-DRLL-DR060 -ENGINE-COSYS-WTRPP | DR060 Water pump Engine | 69618 | 7361 | 6300
500077039 | CLB-MP-DRLL-DR060 -ENGINE | DR060 Engine Assembly | 69618 | 16445 | 6300
500056431 | CLB-MP-DRLL-DR060 | Lubrication & Mechanical Services DR060 | 69618 | 69618 | 6300
500056430 | CLB-MP-DRLL-DR060 | Atlas Copco PV271HP Drill, DR060 | 69618 | 69618 | 6300
500169807 | CLB-MP-HAUL-DT5504-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500169806 | CLB-MP-HAUL-DT5504-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500169805 | CLB-MP-HAUL-DT5504-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500169804 | CLB-MP-HAUL-DT5504-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500169803 | CLB-MP-HAUL-DT5504-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500169802 | CLB-MP-HAUL-DT5504-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500169801 | CLB-MP-HAUL-DT5504-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500169800 | CLB-MP-HAUL-DT5504-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500169799 | CLB-MP-HAUL-DT5504-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500169798 | CLB-MP-HAUL-DT5504-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500169797 | CLB-MP-HAUL-DT5504-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500169796 | CLB-MP-HAUL-DT5504-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500169795 | CLB-MP-HAUL-DT5504-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500169794 | CLB-MP-HAUL-DT5504-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500169793 | CLB-MP-HAUL-DT5504-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500169792 | CLB-MP-HAUL-DT5504-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500169791 | CLB-MP-HAUL-DT5504-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500169790 | CLB-MP-HAUL-DT5504-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500169789 | CLB-MP-HAUL-DT5504-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500169788 | CLB-MP-HAUL-DT5504-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500169787 | CLB-MP-HAUL-DT5504-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500169786 | CLB-MP-HAUL-DT5504-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500169785 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500169784 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500169783 | CLB-MP-HAUL-DT5504-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500169782 | CLB-MP-HAUL-DT5504-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500169781 | CLB-MP-HAUL-DT5504-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500169780 | CLB-MP-HAUL-DT5504-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500169779 | CLB-MP-HAUL-DT5504-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500169778 | CLB-MP-HAUL-DT5504-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500169777 | CLB-MP-HAUL-DT5504-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500169776 | CLB-MP-HAUL-DT5504-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500169775 | CLB-MP-HAUL-DT5504-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500169774 | CLB-MP-HAUL-DT5504-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500169773 | CLB-MP-HAUL-DT5504-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500169772 | CLB-MP-HAUL-DT5504-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500169771 | CLB-MP-HAUL-DT5504-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500169770 | CLB-MP-HAUL-DT5504-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500169769 | CLB-MP-HAUL-DT5504-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500169768 | CLB-MP-HAUL-DT5504-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500169767 | CLB-MP-HAUL-DT5504-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500169766 | CLB-MP-HAUL-DT5504-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500169765 | CLB-MP-HAUL-DT5504-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500169764 | CLB-MP-HAUL-DT5504-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500169763 | CLB-MP-HAUL-DT5504-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500169762 | CLB-MP-HAUL-DT5504-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500169761 | CLB-MP-HAUL-DT5504-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500169760 | CLB-MP-HAUL-DT5504-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500169759 | CLB-MP-HAUL-DT5504-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500169758 | CLB-MP-HAUL-DT5504-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500169757 | CLB-MP-HAUL-DT5504-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500169756 | CLB-MP-HAUL-DT5504-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500169755 | CLB-MP-HAUL-DT5504-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500169754 | CLB-MP-HAUL-DT5504-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500169753 | CLB-MP-HAUL-DT5504-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500169752 | CLB-MP-HAUL-DT5504-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500169751 | CLB-MP-HAUL-DT5504-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500169750 | CLB-MP-HAUL-DT5504-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500169749 | CLB-MP-HAUL-DT5504-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500169748 | CLB-MP-HAUL-DT5504-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500169747 | CLB-MP-HAUL-DT5504-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500169746 | CLB-MP-HAUL-DT5504-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500169745 | CLB-MP-HAUL-DT5504-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500169744 | CLB-MP-HAUL-DT5504-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500169743 | CLB-MP-HAUL-DT5504-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500169742 | CLB-MP-HAUL-DT5504-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500169741 | CLB-MP-HAUL-DT5504-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500169740 | CLB-MP-HAUL-DT5504-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500169739 | CLB-MP-HAUL-DT5504-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500169738 | CLB-MP-HAUL-DT5504-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500169737 | CLB-MP-HAUL-DT5504-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500169736 | CLB-MP-HAUL-DT5504-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500169735 | CLB-MP-HAUL-DT5504-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500169734 | CLB-MP-HAUL-DT5504-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500169733 | CLB-MP-HAUL-DT5504-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500169732 | CLB-MP-HAUL-DT5504-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500169731 | CLB-MP-HAUL-DT5504-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500169730 | CLB-MP-HAUL-DT5504-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500169729 | CLB-MP-HAUL-DT5504-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500169728 | CLB-MP-HAUL-DT5504-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500169727 | CLB-MP-HAUL-DT5504-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500169726 | CLB-MP-HAUL-DT5504-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500169725 | CLB-MP-HAUL-DT5504-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500169724 | CLB-MP-HAUL-DT5504-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500169723 | CLB-MP-HAUL-DT5504-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500169722 | CLB-MP-HAUL-DT5504 | DT5504 Liebherr T264 OHT | 1 | 1 | 6500
500169720 | CLB-MP-HAUL-DT5503-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500169719 | CLB-MP-HAUL-DT5503-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500169718 | CLB-MP-HAUL-DT5503-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500169717 | CLB-MP-HAUL-DT5503-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500169716 | CLB-MP-HAUL-DT5503-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500169715 | CLB-MP-HAUL-DT5503-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500169714 | CLB-MP-HAUL-DT5503-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500169713 | CLB-MP-HAUL-DT5503-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500169712 | CLB-MP-HAUL-DT5503-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500169711 | CLB-MP-HAUL-DT5503-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500169710 | CLB-MP-HAUL-DT5503-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500169709 | CLB-MP-HAUL-DT5503-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500169708 | CLB-MP-HAUL-DT5503-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500169707 | CLB-MP-HAUL-DT5503-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500169706 | CLB-MP-HAUL-DT5503-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500169705 | CLB-MP-HAUL-DT5503-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500169704 | CLB-MP-HAUL-DT5503-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500169703 | CLB-MP-HAUL-DT5503-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500169702 | CLB-MP-HAUL-DT5503-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500169701 | CLB-MP-HAUL-DT5503-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500169700 | CLB-MP-HAUL-DT5503-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500169699 | CLB-MP-HAUL-DT5503-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500169698 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500169697 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500169696 | CLB-MP-HAUL-DT5503-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500169695 | CLB-MP-HAUL-DT5503-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500169694 | CLB-MP-HAUL-DT5503-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500169693 | CLB-MP-HAUL-DT5503-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500169692 | CLB-MP-HAUL-DT5503-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500169691 | CLB-MP-HAUL-DT5503-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500169690 | CLB-MP-HAUL-DT5503-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500169689 | CLB-MP-HAUL-DT5503-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500169688 | CLB-MP-HAUL-DT5503-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500169687 | CLB-MP-HAUL-DT5503-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500169686 | CLB-MP-HAUL-DT5503-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500169685 | CLB-MP-HAUL-DT5503-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500169684 | CLB-MP-HAUL-DT5503-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500169683 | CLB-MP-HAUL-DT5503-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500169682 | CLB-MP-HAUL-DT5503-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500169681 | CLB-MP-HAUL-DT5503-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500169680 | CLB-MP-HAUL-DT5503-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500169679 | CLB-MP-HAUL-DT5503-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500169678 | CLB-MP-HAUL-DT5503-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500169677 | CLB-MP-HAUL-DT5503-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500169676 | CLB-MP-HAUL-DT5503-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500169675 | CLB-MP-HAUL-DT5503-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500169674 | CLB-MP-HAUL-DT5503-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500169673 | CLB-MP-HAUL-DT5503-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500169672 | CLB-MP-HAUL-DT5503-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500169671 | CLB-MP-HAUL-DT5503-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500169670 | CLB-MP-HAUL-DT5503-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500169669 | CLB-MP-HAUL-DT5503-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500169668 | CLB-MP-HAUL-DT5503-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500169667 | CLB-MP-HAUL-DT5503-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500169666 | CLB-MP-HAUL-DT5503-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500169665 | CLB-MP-HAUL-DT5503-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500169664 | CLB-MP-HAUL-DT5503-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500169663 | CLB-MP-HAUL-DT5503-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500169662 | CLB-MP-HAUL-DT5503-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500169661 | CLB-MP-HAUL-DT5503-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500169660 | CLB-MP-HAUL-DT5503-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500169659 | CLB-MP-HAUL-DT5503-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500169658 | CLB-MP-HAUL-DT5503-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500169657 | CLB-MP-HAUL-DT5503-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500169656 | CLB-MP-HAUL-DT5503-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500169655 | CLB-MP-HAUL-DT5503-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500169654 | CLB-MP-HAUL-DT5503-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500169653 | CLB-MP-HAUL-DT5503-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500169652 | CLB-MP-HAUL-DT5503-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500169651 | CLB-MP-HAUL-DT5503-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500169650 | CLB-MP-HAUL-DT5503-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500169649 | CLB-MP-HAUL-DT5503-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500169648 | CLB-MP-HAUL-DT5503-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500169647 | CLB-MP-HAUL-DT5503-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500169646 | CLB-MP-HAUL-DT5503-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500169645 | CLB-MP-HAUL-DT5503-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500169644 | CLB-MP-HAUL-DT5503-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500169643 | CLB-MP-HAUL-DT5503-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500169632 | CLB-MP-HAUL-DT5503-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500169631 | CLB-MP-HAUL-DT5503-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500169630 | CLB-MP-HAUL-DT5503-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500169629 | CLB-MP-HAUL-DT5503-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500169628 | CLB-MP-HAUL-DT5503-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500169627 | CLB-MP-HAUL-DT5503-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500169626 | CLB-MP-HAUL-DT5503-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500169625 | CLB-MP-HAUL-DT5503 | DT5503 Liebherr T264 OHT | 1 | 1 | 6500
500170193 | CLB-MP-HAUL-DT5502-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500170192 | CLB-MP-HAUL-DT5502-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500170191 | CLB-MP-HAUL-DT5502-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500170190 | CLB-MP-HAUL-DT5502-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500170189 | CLB-MP-HAUL-DT5502-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500170188 | CLB-MP-HAUL-DT5502-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500170187 | CLB-MP-HAUL-DT5502-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500170186 | CLB-MP-HAUL-DT5502-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500170185 | CLB-MP-HAUL-DT5502-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500170184 | CLB-MP-HAUL-DT5502-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500170183 | CLB-MP-HAUL-DT5502-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500170182 | CLB-MP-HAUL-DT5502-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500170181 | CLB-MP-HAUL-DT5502-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500170180 | CLB-MP-HAUL-DT5502-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500170179 | CLB-MP-HAUL-DT5502-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500170178 | CLB-MP-HAUL-DT5502-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500170177 | CLB-MP-HAUL-DT5502-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500170176 | CLB-MP-HAUL-DT5502-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500170175 | CLB-MP-HAUL-DT5502-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500170174 | CLB-MP-HAUL-DT5502-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500170173 | CLB-MP-HAUL-DT5502-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500170172 | CLB-MP-HAUL-DT5502-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500170171 | CLB-MP-HAUL-DT5502-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500170170 | CLB-MP-HAUL-DT5502-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500170169 | CLB-MP-HAUL-DT5502-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500170168 | CLB-MP-HAUL-DT5502-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500170167 | CLB-MP-HAUL-DT5502-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500170166 | CLB-MP-HAUL-DT5502-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500170165 | CLB-MP-HAUL-DT5502-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500170164 | CLB-MP-HAUL-DT5502-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500170163 | CLB-MP-HAUL-DT5502-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500170162 | CLB-MP-HAUL-DT5502-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500170161 | CLB-MP-HAUL-DT5502-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500170160 | CLB-MP-HAUL-DT5502-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500170159 | CLB-MP-HAUL-DT5502-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500170158 | CLB-MP-HAUL-DT5502-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500170157 | CLB-MP-HAUL-DT5502-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500170156 | CLB-MP-HAUL-DT5502-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500170155 | CLB-MP-HAUL-DT5502-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500170154 | CLB-MP-HAUL-DT5502-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500170153 | CLB-MP-HAUL-DT5502-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500170152 | CLB-MP-HAUL-DT5502-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500170151 | CLB-MP-HAUL-DT5502-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500170150 | CLB-MP-HAUL-DT5502-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500170149 | CLB-MP-HAUL-DT5502-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500170148 | CLB-MP-HAUL-DT5502-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500170147 | CLB-MP-HAUL-DT5502-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500170146 | CLB-MP-HAUL-DT5502-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500170145 | CLB-MP-HAUL-DT5502-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500170144 | CLB-MP-HAUL-DT5502-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500170143 | CLB-MP-HAUL-DT5502-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500170142 | CLB-MP-HAUL-DT5502-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500170141 | CLB-MP-HAUL-DT5502-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500170140 | CLB-MP-HAUL-DT5502-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500170139 | CLB-MP-HAUL-DT5502-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500170138 | CLB-MP-HAUL-DT5502-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500170137 | CLB-MP-HAUL-DT5502-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500170136 | CLB-MP-HAUL-DT5502-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500170135 | CLB-MP-HAUL-DT5502-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500170134 | CLB-MP-HAUL-DT5502-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500170133 | CLB-MP-HAUL-DT5502-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500170132 | CLB-MP-HAUL-DT5502-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500170131 | CLB-MP-HAUL-DT5502-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500170130 | CLB-MP-HAUL-DT5502-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500170129 | CLB-MP-HAUL-DT5502-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500170128 | CLB-MP-HAUL-DT5502-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500170127 | CLB-MP-HAUL-DT5502-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500170126 | CLB-MP-HAUL-DT5502-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500170125 | CLB-MP-HAUL-DT5502-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500170124 | CLB-MP-HAUL-DT5502-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500170123 | CLB-MP-HAUL-DT5502-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500170122 | CLB-MP-HAUL-DT5502-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500170121 | CLB-MP-HAUL-DT5502-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500170120 | CLB-MP-HAUL-DT5502-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500170119 | CLB-MP-HAUL-DT5502-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500170118 | CLB-MP-HAUL-DT5502-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500170117 | CLB-MP-HAUL-DT5502-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500170116 | CLB-MP-HAUL-DT5502-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500170115 | CLB-MP-HAUL-DT5502-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500170114 | CLB-MP-HAUL-DT5502-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500170113 | CLB-MP-HAUL-DT5502-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500170112 | CLB-MP-HAUL-DT5502-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500170111 | CLB-MP-HAUL-DT5502-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500170110 | CLB-MP-HAUL-DT5502-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500170109 | CLB-MP-HAUL-DT5502-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500170108 | CLB-MP-HAUL-DT5502 | DT5502 Liebherr T264 OHT | 1 | 1 | 6500
500170107 | CLB-MP-HAUL-DT5501-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500170106 | CLB-MP-HAUL-DT5501-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500170105 | CLB-MP-HAUL-DT5501-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500170104 | CLB-MP-HAUL-DT5501-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500170103 | CLB-MP-HAUL-DT5501-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500170102 | CLB-MP-HAUL-DT5501-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500170101 | CLB-MP-HAUL-DT5501-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500170100 | CLB-MP-HAUL-DT5501-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500170099 | CLB-MP-HAUL-DT5501-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500170098 | CLB-MP-HAUL-DT5501-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500170097 | CLB-MP-HAUL-DT5501-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500170096 | CLB-MP-HAUL-DT5501-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500170095 | CLB-MP-HAUL-DT5501-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500170094 | CLB-MP-HAUL-DT5501-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500170093 | CLB-MP-HAUL-DT5501-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500170092 | CLB-MP-HAUL-DT5501-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500170091 | CLB-MP-HAUL-DT5501-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500170090 | CLB-MP-HAUL-DT5501-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500170089 | CLB-MP-HAUL-DT5501-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500170088 | CLB-MP-HAUL-DT5501-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500170087 | CLB-MP-HAUL-DT5501-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500170086 | CLB-MP-HAUL-DT5501-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500170085 | CLB-MP-HAUL-DT5501-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500170084 | CLB-MP-HAUL-DT5501-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500170083 | CLB-MP-HAUL-DT5501-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500170082 | CLB-MP-HAUL-DT5501-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500170081 | CLB-MP-HAUL-DT5501-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500170080 | CLB-MP-HAUL-DT5501-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500170079 | CLB-MP-HAUL-DT5501-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500170078 | CLB-MP-HAUL-DT5501-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500170077 | CLB-MP-HAUL-DT5501-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500170076 | CLB-MP-HAUL-DT5501-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500170075 | CLB-MP-HAUL-DT5501-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500170074 | CLB-MP-HAUL-DT5501-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500170073 | CLB-MP-HAUL-DT5501-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500170072 | CLB-MP-HAUL-DT5501-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500170071 | CLB-MP-HAUL-DT5501-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500170070 | CLB-MP-HAUL-DT5501-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500170069 | CLB-MP-HAUL-DT5501-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500170068 | CLB-MP-HAUL-DT5501-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500170067 | CLB-MP-HAUL-DT5501-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500170066 | CLB-MP-HAUL-DT5501-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500170065 | CLB-MP-HAUL-DT5501-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500170064 | CLB-MP-HAUL-DT5501-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500170063 | CLB-MP-HAUL-DT5501-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500170062 | CLB-MP-HAUL-DT5501-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500170061 | CLB-MP-HAUL-DT5501-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500170060 | CLB-MP-HAUL-DT5501-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500170059 | CLB-MP-HAUL-DT5501-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500170058 | CLB-MP-HAUL-DT5501-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500170057 | CLB-MP-HAUL-DT5501-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500170056 | CLB-MP-HAUL-DT5501-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500170055 | CLB-MP-HAUL-DT5501-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500170054 | CLB-MP-HAUL-DT5501-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500170053 | CLB-MP-HAUL-DT5501-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500170052 | CLB-MP-HAUL-DT5501-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500170051 | CLB-MP-HAUL-DT5501-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500170050 | CLB-MP-HAUL-DT5501-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500170049 | CLB-MP-HAUL-DT5501-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500170048 | CLB-MP-HAUL-DT5501-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500170047 | CLB-MP-HAUL-DT5501-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500170046 | CLB-MP-HAUL-DT5501-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500170045 | CLB-MP-HAUL-DT5501-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500170044 | CLB-MP-HAUL-DT5501-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500170043 | CLB-MP-HAUL-DT5501-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500170042 | CLB-MP-HAUL-DT5501-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500170041 | CLB-MP-HAUL-DT5501-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500170040 | CLB-MP-HAUL-DT5501-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500170039 | CLB-MP-HAUL-DT5501-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500170038 | CLB-MP-HAUL-DT5501-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500170037 | CLB-MP-HAUL-DT5501-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500170036 | CLB-MP-HAUL-DT5501-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500170035 | CLB-MP-HAUL-DT5501-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500170034 | CLB-MP-HAUL-DT5501-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500170033 | CLB-MP-HAUL-DT5501-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500170032 | CLB-MP-HAUL-DT5501-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500170031 | CLB-MP-HAUL-DT5501-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500170030 | CLB-MP-HAUL-DT5501-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500170029 | CLB-MP-HAUL-DT5501-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500170028 | CLB-MP-HAUL-DT5501-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500170027 | CLB-MP-HAUL-DT5501-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500170026 | CLB-MP-HAUL-DT5501-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500170025 | CLB-MP-HAUL-DT5501-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500170024 | CLB-MP-HAUL-DT5501-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500170023 | CLB-MP-HAUL-DT5501-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500169872 | CLB-MP-HAUL-DT5501 | DT5501 Liebherr T264 OHT | 1 | 1 | 6500
500167775 | CLB-MP-HAUL-DT5500-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167774 | CLB-MP-HAUL-DT5500-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167773 | CLB-MP-HAUL-DT5500-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167772 | CLB-MP-HAUL-DT5500-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167771 | CLB-MP-HAUL-DT5500-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167770 | CLB-MP-HAUL-DT5500-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167769 | CLB-MP-HAUL-DT5500-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167768 | CLB-MP-HAUL-DT5500-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167767 | CLB-MP-HAUL-DT5500-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167766 | CLB-MP-HAUL-DT5500-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167765 | CLB-MP-HAUL-DT5500-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167764 | CLB-MP-HAUL-DT5500-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167763 | CLB-MP-HAUL-DT5500-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167762 | CLB-MP-HAUL-DT5500-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167761 | CLB-MP-HAUL-DT5500-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167760 | CLB-MP-HAUL-DT5500-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167759 | CLB-MP-HAUL-DT5500-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167758 | CLB-MP-HAUL-DT5500-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167757 | CLB-MP-HAUL-DT5500-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167756 | CLB-MP-HAUL-DT5500-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167755 | CLB-MP-HAUL-DT5500-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167754 | CLB-MP-HAUL-DT5500-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167753 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167752 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167751 | CLB-MP-HAUL-DT5500-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167750 | CLB-MP-HAUL-DT5500-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167749 | CLB-MP-HAUL-DT5500-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167748 | CLB-MP-HAUL-DT5500-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167747 | CLB-MP-HAUL-DT5500-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500167746 | CLB-MP-HAUL-DT5500-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500167745 | CLB-MP-HAUL-DT5500-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500167744 | CLB-MP-HAUL-DT5500-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500167743 | CLB-MP-HAUL-DT5500-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500167742 | CLB-MP-HAUL-DT5500-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500167741 | CLB-MP-HAUL-DT5500-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500167740 | CLB-MP-HAUL-DT5500-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500167739 | CLB-MP-HAUL-DT5500-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500167738 | CLB-MP-HAUL-DT5500-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500167737 | CLB-MP-HAUL-DT5500-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500167736 | CLB-MP-HAUL-DT5500-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500167735 | CLB-MP-HAUL-DT5500-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500167734 | CLB-MP-HAUL-DT5500-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500167733 | CLB-MP-HAUL-DT5500-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500167732 | CLB-MP-HAUL-DT5500-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500167731 | CLB-MP-HAUL-DT5500-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500167730 | CLB-MP-HAUL-DT5500-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500167729 | CLB-MP-HAUL-DT5500-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500167728 | CLB-MP-HAUL-DT5500-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500167727 | CLB-MP-HAUL-DT5500-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500167726 | CLB-MP-HAUL-DT5500-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500167725 | CLB-MP-HAUL-DT5500-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500167724 | CLB-MP-HAUL-DT5500-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500167723 | CLB-MP-HAUL-DT5500-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500167722 | CLB-MP-HAUL-DT5500-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500167721 | CLB-MP-HAUL-DT5500-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500167720 | CLB-MP-HAUL-DT5500-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500167719 | CLB-MP-HAUL-DT5500-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500167718 | CLB-MP-HAUL-DT5500-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500167717 | CLB-MP-HAUL-DT5500-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500167716 | CLB-MP-HAUL-DT5500-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500167715 | CLB-MP-HAUL-DT5500-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500167714 | CLB-MP-HAUL-DT5500-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500167713 | CLB-MP-HAUL-DT5500-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500167712 | CLB-MP-HAUL-DT5500-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500167711 | CLB-MP-HAUL-DT5500-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500167710 | CLB-MP-HAUL-DT5500-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500167709 | CLB-MP-HAUL-DT5500-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500167708 | CLB-MP-HAUL-DT5500-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500167707 | CLB-MP-HAUL-DT5500-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500167706 | CLB-MP-HAUL-DT5500-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500167705 | CLB-MP-HAUL-DT5500-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500167704 | CLB-MP-HAUL-DT5500-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500167703 | CLB-MP-HAUL-DT5500-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500167702 | CLB-MP-HAUL-DT5500-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500167701 | CLB-MP-HAUL-DT5500-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500167700 | CLB-MP-HAUL-DT5500-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500167699 | CLB-MP-HAUL-DT5500-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500167698 | CLB-MP-HAUL-DT5500-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500167697 | CLB-MP-HAUL-DT5500-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500167696 | CLB-MP-HAUL-DT5500-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500167695 | CLB-MP-HAUL-DT5500-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500167694 | CLB-MP-HAUL-DT5500-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500167693 | CLB-MP-HAUL-DT5500-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500167692 | CLB-MP-HAUL-DT5500-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500167691 | CLB-MP-HAUL-DT5500-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500167690 | CLB-MP-HAUL-DT5500 | DT5500 Liebherr T264 OHT | 1 | 1 | 6500
500167689 | CLB-MP-HAUL-DT5499-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167688 | CLB-MP-HAUL-DT5499-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167687 | CLB-MP-HAUL-DT5499-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167686 | CLB-MP-HAUL-DT5499-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167685 | CLB-MP-HAUL-DT5499-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167684 | CLB-MP-HAUL-DT5499-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167683 | CLB-MP-HAUL-DT5499-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167682 | CLB-MP-HAUL-DT5499-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167681 | CLB-MP-HAUL-DT5499-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167680 | CLB-MP-HAUL-DT5499-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167679 | CLB-MP-HAUL-DT5499-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167678 | CLB-MP-HAUL-DT5499-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167677 | CLB-MP-HAUL-DT5499-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167676 | CLB-MP-HAUL-DT5499-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167675 | CLB-MP-HAUL-DT5499-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167674 | CLB-MP-HAUL-DT5499-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167673 | CLB-MP-HAUL-DT5499-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167672 | CLB-MP-HAUL-DT5499-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167671 | CLB-MP-HAUL-DT5499-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167670 | CLB-MP-HAUL-DT5499-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167669 | CLB-MP-HAUL-DT5499-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167668 | CLB-MP-HAUL-DT5499-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167667 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167666 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167665 | CLB-MP-HAUL-DT5499-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167664 | CLB-MP-HAUL-DT5499-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167663 | CLB-MP-HAUL-DT5499-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167662 | CLB-MP-HAUL-DT5499-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167661 | CLB-MP-HAUL-DT5499-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500167660 | CLB-MP-HAUL-DT5499-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500167659 | CLB-MP-HAUL-DT5499-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500167658 | CLB-MP-HAUL-DT5499-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500167657 | CLB-MP-HAUL-DT5499-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500167656 | CLB-MP-HAUL-DT5499-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500167655 | CLB-MP-HAUL-DT5499-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500167654 | CLB-MP-HAUL-DT5499-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500167653 | CLB-MP-HAUL-DT5499-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500167652 | CLB-MP-HAUL-DT5499-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500167651 | CLB-MP-HAUL-DT5499-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500167650 | CLB-MP-HAUL-DT5499-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500167649 | CLB-MP-HAUL-DT5499-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500167648 | CLB-MP-HAUL-DT5499-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500167647 | CLB-MP-HAUL-DT5499-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500167646 | CLB-MP-HAUL-DT5499-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500167645 | CLB-MP-HAUL-DT5499-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500167644 | CLB-MP-HAUL-DT5499-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500167643 | CLB-MP-HAUL-DT5499-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500167642 | CLB-MP-HAUL-DT5499-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500167641 | CLB-MP-HAUL-DT5499-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500167640 | CLB-MP-HAUL-DT5499-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500167639 | CLB-MP-HAUL-DT5499-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500167638 | CLB-MP-HAUL-DT5499-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500167637 | CLB-MP-HAUL-DT5499-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500167636 | CLB-MP-HAUL-DT5499-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500167635 | CLB-MP-HAUL-DT5499-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500167634 | CLB-MP-HAUL-DT5499-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500167633 | CLB-MP-HAUL-DT5499-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500167632 | CLB-MP-HAUL-DT5499-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500167631 | CLB-MP-HAUL-DT5499-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500167630 | CLB-MP-HAUL-DT5499-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500167629 | CLB-MP-HAUL-DT5499-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500167628 | CLB-MP-HAUL-DT5499-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500167627 | CLB-MP-HAUL-DT5499-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500167626 | CLB-MP-HAUL-DT5499-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500167625 | CLB-MP-HAUL-DT5499-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500167624 | CLB-MP-HAUL-DT5499-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500167623 | CLB-MP-HAUL-DT5499-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500167622 | CLB-MP-HAUL-DT5499-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500167621 | CLB-MP-HAUL-DT5499-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500167620 | CLB-MP-HAUL-DT5499-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500167619 | CLB-MP-HAUL-DT5499-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500167618 | CLB-MP-HAUL-DT5499-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500167617 | CLB-MP-HAUL-DT5499-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500167616 | CLB-MP-HAUL-DT5499-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500167615 | CLB-MP-HAUL-DT5499-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500167614 | CLB-MP-HAUL-DT5499-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500167613 | CLB-MP-HAUL-DT5499-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500167572 | CLB-MP-HAUL-DT5499-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500167571 | CLB-MP-HAUL-DT5499-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500167570 | CLB-MP-HAUL-DT5499-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500167569 | CLB-MP-HAUL-DT5499-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500167568 | CLB-MP-HAUL-DT5499-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500167567 | CLB-MP-HAUL-DT5499-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500167566 | CLB-MP-HAUL-DT5499-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500167565 | CLB-MP-HAUL-DT5499-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500167564 | CLB-MP-HAUL-DT5499 | DT5499 Liebherr T264 OHT | 1 | 1 | 6500
500167537 | CLB-MP-HAUL-DT5498-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167536 | CLB-MP-HAUL-DT5498-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167535 | CLB-MP-HAUL-DT5498-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167534 | CLB-MP-HAUL-DT5498-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167533 | CLB-MP-HAUL-DT5498-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167532 | CLB-MP-HAUL-DT5498-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167531 | CLB-MP-HAUL-DT5498-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167530 | CLB-MP-HAUL-DT5498-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167529 | CLB-MP-HAUL-DT5498-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167528 | CLB-MP-HAUL-DT5498-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167527 | CLB-MP-HAUL-DT5498-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167526 | CLB-MP-HAUL-DT5498-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167525 | CLB-MP-HAUL-DT5498-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167524 | CLB-MP-HAUL-DT5498-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167523 | CLB-MP-HAUL-DT5498-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167522 | CLB-MP-HAUL-DT5498-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167521 | CLB-MP-HAUL-DT5498-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167520 | CLB-MP-HAUL-DT5498-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167519 | CLB-MP-HAUL-DT5498-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167518 | CLB-MP-HAUL-DT5498-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167517 | CLB-MP-HAUL-DT5498-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167516 | CLB-MP-HAUL-DT5498-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167515 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167514 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167513 | CLB-MP-HAUL-DT5498-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167512 | CLB-MP-HAUL-DT5498-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167511 | CLB-MP-HAUL-DT5498-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167510 | CLB-MP-HAUL-DT5498-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167509 | CLB-MP-HAUL-DT5498-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500167508 | CLB-MP-HAUL-DT5498-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500167507 | CLB-MP-HAUL-DT5498-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500167506 | CLB-MP-HAUL-DT5498-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500167505 | CLB-MP-HAUL-DT5498-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500167504 | CLB-MP-HAUL-DT5498-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500167503 | CLB-MP-HAUL-DT5498-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500167502 | CLB-MP-HAUL-DT5498-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500167501 | CLB-MP-HAUL-DT5498-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500167500 | CLB-MP-HAUL-DT5498-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500167499 | CLB-MP-HAUL-DT5498-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500167498 | CLB-MP-HAUL-DT5498-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500167497 | CLB-MP-HAUL-DT5498-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500167496 | CLB-MP-HAUL-DT5498-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500167495 | CLB-MP-HAUL-DT5498-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500167494 | CLB-MP-HAUL-DT5498-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500167493 | CLB-MP-HAUL-DT5498-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500167492 | CLB-MP-HAUL-DT5498-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500167491 | CLB-MP-HAUL-DT5498-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500167490 | CLB-MP-HAUL-DT5498-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500167489 | CLB-MP-HAUL-DT5498-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500167488 | CLB-MP-HAUL-DT5498-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500167487 | CLB-MP-HAUL-DT5498-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500167486 | CLB-MP-HAUL-DT5498-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500167485 | CLB-MP-HAUL-DT5498-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500167484 | CLB-MP-HAUL-DT5498-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500167483 | CLB-MP-HAUL-DT5498-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500167482 | CLB-MP-HAUL-DT5498-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500167481 | CLB-MP-HAUL-DT5498-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500167480 | CLB-MP-HAUL-DT5498-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500167479 | CLB-MP-HAUL-DT5498-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500167478 | CLB-MP-HAUL-DT5498-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500167477 | CLB-MP-HAUL-DT5498-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500167476 | CLB-MP-HAUL-DT5498-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500167475 | CLB-MP-HAUL-DT5498-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500167474 | CLB-MP-HAUL-DT5498-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500167473 | CLB-MP-HAUL-DT5498-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500167472 | CLB-MP-HAUL-DT5498-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500167471 | CLB-MP-HAUL-DT5498-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500167470 | CLB-MP-HAUL-DT5498-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500167469 | CLB-MP-HAUL-DT5498-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500167468 | CLB-MP-HAUL-DT5498-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500167467 | CLB-MP-HAUL-DT5498-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500167466 | CLB-MP-HAUL-DT5498-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500167465 | CLB-MP-HAUL-DT5498-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500167464 | CLB-MP-HAUL-DT5498-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500167463 | CLB-MP-HAUL-DT5498-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500167462 | CLB-MP-HAUL-DT5498-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500167461 | CLB-MP-HAUL-DT5498-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500167460 | CLB-MP-HAUL-DT5498-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500167459 | CLB-MP-HAUL-DT5498-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500167458 | CLB-MP-HAUL-DT5498-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500167457 | CLB-MP-HAUL-DT5498-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500167456 | CLB-MP-HAUL-DT5498-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500167455 | CLB-MP-HAUL-DT5498-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500167454 | CLB-MP-HAUL-DT5498-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500167453 | CLB-MP-HAUL-DT5498-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500167452 | CLB-MP-HAUL-DT5498 | DT5498 Liebherr T264 OHT | 1 | 1 | 6500
500167451 | CLB-MP-HAUL-DT5497-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167450 | CLB-MP-HAUL-DT5497-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167449 | CLB-MP-HAUL-DT5497-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167448 | CLB-MP-HAUL-DT5497-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167447 | CLB-MP-HAUL-DT5497-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167446 | CLB-MP-HAUL-DT5497-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167445 | CLB-MP-HAUL-DT5497-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167444 | CLB-MP-HAUL-DT5497-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167443 | CLB-MP-HAUL-DT5497-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167442 | CLB-MP-HAUL-DT5497-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167441 | CLB-MP-HAUL-DT5497-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167440 | CLB-MP-HAUL-DT5497-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167439 | CLB-MP-HAUL-DT5497-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167438 | CLB-MP-HAUL-DT5497-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167437 | CLB-MP-HAUL-DT5497-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167436 | CLB-MP-HAUL-DT5497-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167435 | CLB-MP-HAUL-DT5497-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167434 | CLB-MP-HAUL-DT5497-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167433 | CLB-MP-HAUL-DT5497-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167432 | CLB-MP-HAUL-DT5497-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167431 | CLB-MP-HAUL-DT5497-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167430 | CLB-MP-HAUL-DT5497-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167429 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167428 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167427 | CLB-MP-HAUL-DT5497-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167426 | CLB-MP-HAUL-DT5497-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167425 | CLB-MP-HAUL-DT5497-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167424 | CLB-MP-HAUL-DT5497-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167423 | CLB-MP-HAUL-DT5497-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500167422 | CLB-MP-HAUL-DT5497-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500167421 | CLB-MP-HAUL-DT5497-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500167420 | CLB-MP-HAUL-DT5497-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500167419 | CLB-MP-HAUL-DT5497-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500167418 | CLB-MP-HAUL-DT5497-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500167417 | CLB-MP-HAUL-DT5497-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500167416 | CLB-MP-HAUL-DT5497-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500167415 | CLB-MP-HAUL-DT5497-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500167414 | CLB-MP-HAUL-DT5497-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500167413 | CLB-MP-HAUL-DT5497-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500167412 | CLB-MP-HAUL-DT5497-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500167411 | CLB-MP-HAUL-DT5497-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500167410 | CLB-MP-HAUL-DT5497-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500167409 | CLB-MP-HAUL-DT5497-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500167408 | CLB-MP-HAUL-DT5497-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500167407 | CLB-MP-HAUL-DT5497-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500167406 | CLB-MP-HAUL-DT5497-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500167405 | CLB-MP-HAUL-DT5497-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500167404 | CLB-MP-HAUL-DT5497-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500167403 | CLB-MP-HAUL-DT5497-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500167402 | CLB-MP-HAUL-DT5497-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500167401 | CLB-MP-HAUL-DT5497-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500167400 | CLB-MP-HAUL-DT5497-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500167399 | CLB-MP-HAUL-DT5497-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500167398 | CLB-MP-HAUL-DT5497-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500167397 | CLB-MP-HAUL-DT5497-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500167396 | CLB-MP-HAUL-DT5497-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500167395 | CLB-MP-HAUL-DT5497-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500167394 | CLB-MP-HAUL-DT5497-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500167393 | CLB-MP-HAUL-DT5497-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500167392 | CLB-MP-HAUL-DT5497-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500167391 | CLB-MP-HAUL-DT5497-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500167390 | CLB-MP-HAUL-DT5497-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500167389 | CLB-MP-HAUL-DT5497-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500167388 | CLB-MP-HAUL-DT5497-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500167387 | CLB-MP-HAUL-DT5497-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500167386 | CLB-MP-HAUL-DT5497-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500167385 | CLB-MP-HAUL-DT5497-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500167384 | CLB-MP-HAUL-DT5497-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500167383 | CLB-MP-HAUL-DT5497-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500167382 | CLB-MP-HAUL-DT5497-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500167381 | CLB-MP-HAUL-DT5497-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500167380 | CLB-MP-HAUL-DT5497-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500167379 | CLB-MP-HAUL-DT5497-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500167378 | CLB-MP-HAUL-DT5497-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500167377 | CLB-MP-HAUL-DT5497-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500167376 | CLB-MP-HAUL-DT5497-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500167375 | CLB-MP-HAUL-DT5497-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500167374 | CLB-MP-HAUL-DT5497-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500167373 | CLB-MP-HAUL-DT5497-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500167182 | CLB-MP-HAUL-DT5497-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500167181 | CLB-MP-HAUL-DT5497-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500167180 | CLB-MP-HAUL-DT5497-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500167179 | CLB-MP-HAUL-DT5497-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500167178 | CLB-MP-HAUL-DT5497-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500167177 | CLB-MP-HAUL-DT5497-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500167176 | CLB-MP-HAUL-DT5497 | DT5497 Liebherr T264 OHT | 1 | 1 | 6500
500167358 | CLB-MP-HAUL-DT5496-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167357 | CLB-MP-HAUL-DT5496-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167356 | CLB-MP-HAUL-DT5496-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167355 | CLB-MP-HAUL-DT5496-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167354 | CLB-MP-HAUL-DT5496-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167353 | CLB-MP-HAUL-DT5496-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167352 | CLB-MP-HAUL-DT5496-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167351 | CLB-MP-HAUL-DT5496-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167350 | CLB-MP-HAUL-DT5496-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167349 | CLB-MP-HAUL-DT5496-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167348 | CLB-MP-HAUL-DT5496-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167347 | CLB-MP-HAUL-DT5496-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167346 | CLB-MP-HAUL-DT5496-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167345 | CLB-MP-HAUL-DT5496-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167344 | CLB-MP-HAUL-DT5496-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167343 | CLB-MP-HAUL-DT5496-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167342 | CLB-MP-HAUL-DT5496-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167341 | CLB-MP-HAUL-DT5496-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167340 | CLB-MP-HAUL-DT5496-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167339 | CLB-MP-HAUL-DT5496-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167338 | CLB-MP-HAUL-DT5496-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167337 | CLB-MP-HAUL-DT5496-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167336 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167335 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167334 | CLB-MP-HAUL-DT5496-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167333 | CLB-MP-HAUL-DT5496-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167332 | CLB-MP-HAUL-DT5496-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167331 | CLB-MP-HAUL-DT5496-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167330 | CLB-MP-HAUL-DT5496-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500167329 | CLB-MP-HAUL-DT5496-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500167328 | CLB-MP-HAUL-DT5496-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500167327 | CLB-MP-HAUL-DT5496-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500167326 | CLB-MP-HAUL-DT5496-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500167325 | CLB-MP-HAUL-DT5496-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500167324 | CLB-MP-HAUL-DT5496-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500167323 | CLB-MP-HAUL-DT5496-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500167322 | CLB-MP-HAUL-DT5496-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500167321 | CLB-MP-HAUL-DT5496-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500167320 | CLB-MP-HAUL-DT5496-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500167319 | CLB-MP-HAUL-DT5496-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500167318 | CLB-MP-HAUL-DT5496-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500167317 | CLB-MP-HAUL-DT5496-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500167316 | CLB-MP-HAUL-DT5496-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500167315 | CLB-MP-HAUL-DT5496-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500167314 | CLB-MP-HAUL-DT5496-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500167313 | CLB-MP-HAUL-DT5496-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500167312 | CLB-MP-HAUL-DT5496-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500167311 | CLB-MP-HAUL-DT5496-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500167310 | CLB-MP-HAUL-DT5496-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500167309 | CLB-MP-HAUL-DT5496-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500167308 | CLB-MP-HAUL-DT5496-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500167307 | CLB-MP-HAUL-DT5496-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500167306 | CLB-MP-HAUL-DT5496-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500167305 | CLB-MP-HAUL-DT5496-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500167304 | CLB-MP-HAUL-DT5496-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500167303 | CLB-MP-HAUL-DT5496-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500167302 | CLB-MP-HAUL-DT5496-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500167301 | CLB-MP-HAUL-DT5496-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500167300 | CLB-MP-HAUL-DT5496-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500167299 | CLB-MP-HAUL-DT5496-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500167298 | CLB-MP-HAUL-DT5496-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500167297 | CLB-MP-HAUL-DT5496-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500167296 | CLB-MP-HAUL-DT5496-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500167295 | CLB-MP-HAUL-DT5496-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500167294 | CLB-MP-HAUL-DT5496-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500167293 | CLB-MP-HAUL-DT5496-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500167292 | CLB-MP-HAUL-DT5496-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500167291 | CLB-MP-HAUL-DT5496-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500167290 | CLB-MP-HAUL-DT5496-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500167289 | CLB-MP-HAUL-DT5496-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500167288 | CLB-MP-HAUL-DT5496-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500167287 | CLB-MP-HAUL-DT5496-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500167286 | CLB-MP-HAUL-DT5496-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500167285 | CLB-MP-HAUL-DT5496-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500167284 | CLB-MP-HAUL-DT5496-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500167283 | CLB-MP-HAUL-DT5496-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500167282 | CLB-MP-HAUL-DT5496-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500167281 | CLB-MP-HAUL-DT5496-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500167280 | CLB-MP-HAUL-DT5496-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500167279 | CLB-MP-HAUL-DT5496-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500167278 | CLB-MP-HAUL-DT5496-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500167277 | CLB-MP-HAUL-DT5496-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500167276 | CLB-MP-HAUL-DT5496-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500167275 | CLB-MP-HAUL-DT5496-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500167274 | CLB-MP-HAUL-DT5496-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500167273 | CLB-MP-HAUL-DT5496 | DT5496 Liebherr T264 OHT | 1 | 1 | 6500
500167272 | CLB-MP-HAUL-DT5495-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167271 | CLB-MP-HAUL-DT5495-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167270 | CLB-MP-HAUL-DT5495-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167269 | CLB-MP-HAUL-DT5495-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167268 | CLB-MP-HAUL-DT5495-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167267 | CLB-MP-HAUL-DT5495-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167266 | CLB-MP-HAUL-DT5495-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167265 | CLB-MP-HAUL-DT5495-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167264 | CLB-MP-HAUL-DT5495-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167263 | CLB-MP-HAUL-DT5495-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167262 | CLB-MP-HAUL-DT5495-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167261 | CLB-MP-HAUL-DT5495-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167260 | CLB-MP-HAUL-DT5495-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167259 | CLB-MP-HAUL-DT5495-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167258 | CLB-MP-HAUL-DT5495-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167257 | CLB-MP-HAUL-DT5495-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167256 | CLB-MP-HAUL-DT5495-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167255 | CLB-MP-HAUL-DT5495-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167254 | CLB-MP-HAUL-DT5495-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167253 | CLB-MP-HAUL-DT5495-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167252 | CLB-MP-HAUL-DT5495-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167251 | CLB-MP-HAUL-DT5495-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167250 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167249 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167248 | CLB-MP-HAUL-DT5495-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167247 | CLB-MP-HAUL-DT5495-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167246 | CLB-MP-HAUL-DT5495-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167245 | CLB-MP-HAUL-DT5495-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167244 | CLB-MP-HAUL-DT5495-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500167243 | CLB-MP-HAUL-DT5495-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500167242 | CLB-MP-HAUL-DT5495-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500167241 | CLB-MP-HAUL-DT5495-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500167240 | CLB-MP-HAUL-DT5495-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500167239 | CLB-MP-HAUL-DT5495-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500167238 | CLB-MP-HAUL-DT5495-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500167237 | CLB-MP-HAUL-DT5495-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500167236 | CLB-MP-HAUL-DT5495-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500167235 | CLB-MP-HAUL-DT5495-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500167234 | CLB-MP-HAUL-DT5495-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500167233 | CLB-MP-HAUL-DT5495-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500167232 | CLB-MP-HAUL-DT5495-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500167231 | CLB-MP-HAUL-DT5495-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500167230 | CLB-MP-HAUL-DT5495-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500167229 | CLB-MP-HAUL-DT5495-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500167228 | CLB-MP-HAUL-DT5495-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500167227 | CLB-MP-HAUL-DT5495-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500167226 | CLB-MP-HAUL-DT5495-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500167225 | CLB-MP-HAUL-DT5495-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500167224 | CLB-MP-HAUL-DT5495-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500167223 | CLB-MP-HAUL-DT5495-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500167222 | CLB-MP-HAUL-DT5495-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500167221 | CLB-MP-HAUL-DT5495-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500167220 | CLB-MP-HAUL-DT5495-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500167219 | CLB-MP-HAUL-DT5495-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500167218 | CLB-MP-HAUL-DT5495-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500167217 | CLB-MP-HAUL-DT5495-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500167216 | CLB-MP-HAUL-DT5495-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500167215 | CLB-MP-HAUL-DT5495-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500167214 | CLB-MP-HAUL-DT5495-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500167213 | CLB-MP-HAUL-DT5495-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500167212 | CLB-MP-HAUL-DT5495-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500167211 | CLB-MP-HAUL-DT5495-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500167210 | CLB-MP-HAUL-DT5495-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500167209 | CLB-MP-HAUL-DT5495-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500167208 | CLB-MP-HAUL-DT5495-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500167207 | CLB-MP-HAUL-DT5495-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500167206 | CLB-MP-HAUL-DT5495-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500167205 | CLB-MP-HAUL-DT5495-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500167204 | CLB-MP-HAUL-DT5495-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500167203 | CLB-MP-HAUL-DT5495-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500167202 | CLB-MP-HAUL-DT5495-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500167201 | CLB-MP-HAUL-DT5495-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500167200 | CLB-MP-HAUL-DT5495-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500167199 | CLB-MP-HAUL-DT5495-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500167198 | CLB-MP-HAUL-DT5495-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500167197 | CLB-MP-HAUL-DT5495-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500167196 | CLB-MP-HAUL-DT5495-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500167195 | CLB-MP-HAUL-DT5495-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500167194 | CLB-MP-HAUL-DT5495-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500167193 | CLB-MP-HAUL-DT5495-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500166932 | CLB-MP-HAUL-DT5495-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500166931 | CLB-MP-HAUL-DT5495-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500166930 | CLB-MP-HAUL-DT5495-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500166929 | CLB-MP-HAUL-DT5495-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500166928 | CLB-MP-HAUL-DT5495-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500166927 | CLB-MP-HAUL-DT5495 | DT5495 Liebherr T264 OHT | 1 | 1 | 6500
500167028 | CLB-MP-HAUL-DT5494-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500167027 | CLB-MP-HAUL-DT5494-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500167026 | CLB-MP-HAUL-DT5494-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500167025 | CLB-MP-HAUL-DT5494-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500167024 | CLB-MP-HAUL-DT5494-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500167023 | CLB-MP-HAUL-DT5494-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500167022 | CLB-MP-HAUL-DT5494-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500167021 | CLB-MP-HAUL-DT5494-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500167020 | CLB-MP-HAUL-DT5494-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500167019 | CLB-MP-HAUL-DT5494-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500167018 | CLB-MP-HAUL-DT5494-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500167017 | CLB-MP-HAUL-DT5494-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500167016 | CLB-MP-HAUL-DT5494-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500167015 | CLB-MP-HAUL-DT5494-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500167014 | CLB-MP-HAUL-DT5494-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500167013 | CLB-MP-HAUL-DT5494-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500167012 | CLB-MP-HAUL-DT5494-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500167011 | CLB-MP-HAUL-DT5494-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500167010 | CLB-MP-HAUL-DT5494-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500167009 | CLB-MP-HAUL-DT5494-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500167008 | CLB-MP-HAUL-DT5494-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500167007 | CLB-MP-HAUL-DT5494-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500167006 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500167005 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500167004 | CLB-MP-HAUL-DT5494-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500167003 | CLB-MP-HAUL-DT5494-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500167002 | CLB-MP-HAUL-DT5494-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500167001 | CLB-MP-HAUL-DT5494-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500167000 | CLB-MP-HAUL-DT5494-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500166999 | CLB-MP-HAUL-DT5494-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500166998 | CLB-MP-HAUL-DT5494-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500166997 | CLB-MP-HAUL-DT5494-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500166996 | CLB-MP-HAUL-DT5494-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500166995 | CLB-MP-HAUL-DT5494-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500166994 | CLB-MP-HAUL-DT5494-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500166993 | CLB-MP-HAUL-DT5494-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500166992 | CLB-MP-HAUL-DT5494-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500166991 | CLB-MP-HAUL-DT5494-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500166990 | CLB-MP-HAUL-DT5494-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500166989 | CLB-MP-HAUL-DT5494-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500166988 | CLB-MP-HAUL-DT5494-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500166987 | CLB-MP-HAUL-DT5494-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500166986 | CLB-MP-HAUL-DT5494-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500166985 | CLB-MP-HAUL-DT5494-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500166984 | CLB-MP-HAUL-DT5494-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500166983 | CLB-MP-HAUL-DT5494-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500166982 | CLB-MP-HAUL-DT5494-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500166981 | CLB-MP-HAUL-DT5494-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500166980 | CLB-MP-HAUL-DT5494-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500166979 | CLB-MP-HAUL-DT5494-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500166978 | CLB-MP-HAUL-DT5494-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500166977 | CLB-MP-HAUL-DT5494-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500166976 | CLB-MP-HAUL-DT5494-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500166975 | CLB-MP-HAUL-DT5494-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500166974 | CLB-MP-HAUL-DT5494-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500166973 | CLB-MP-HAUL-DT5494-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500166972 | CLB-MP-HAUL-DT5494-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500166971 | CLB-MP-HAUL-DT5494-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500166970 | CLB-MP-HAUL-DT5494-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500166969 | CLB-MP-HAUL-DT5494-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500166968 | CLB-MP-HAUL-DT5494-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500166967 | CLB-MP-HAUL-DT5494-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500166966 | CLB-MP-HAUL-DT5494-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500166965 | CLB-MP-HAUL-DT5494-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500166964 | CLB-MP-HAUL-DT5494-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500166963 | CLB-MP-HAUL-DT5494-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500166962 | CLB-MP-HAUL-DT5494-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500166961 | CLB-MP-HAUL-DT5494-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500166960 | CLB-MP-HAUL-DT5494-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500166959 | CLB-MP-HAUL-DT5494-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500166958 | CLB-MP-HAUL-DT5494-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500166957 | CLB-MP-HAUL-DT5494-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500166956 | CLB-MP-HAUL-DT5494-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500166955 | CLB-MP-HAUL-DT5494-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500166954 | CLB-MP-HAUL-DT5494-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500166953 | CLB-MP-HAUL-DT5494-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500166952 | CLB-MP-HAUL-DT5494-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500166951 | CLB-MP-HAUL-DT5494-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500166950 | CLB-MP-HAUL-DT5494-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500166949 | CLB-MP-HAUL-DT5494-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500166948 | CLB-MP-HAUL-DT5494-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500166947 | CLB-MP-HAUL-DT5494-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500166946 | CLB-MP-HAUL-DT5494-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500166945 | CLB-MP-HAUL-DT5494-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500166944 | CLB-MP-HAUL-DT5494-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500166943 | CLB-MP-HAUL-DT5494 | DT5494 Liebherr T264 OHT | 1 | 1 | 6500
500166922 | CLB-MP-HAUL-DT5493-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500166921 | CLB-MP-HAUL-DT5493-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500166920 | CLB-MP-HAUL-DT5493-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500166919 | CLB-MP-HAUL-DT5493-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500166918 | CLB-MP-HAUL-DT5493-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500166917 | CLB-MP-HAUL-DT5493-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500166916 | CLB-MP-HAUL-DT5493-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500166915 | CLB-MP-HAUL-DT5493-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500166914 | CLB-MP-HAUL-DT5493-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500166913 | CLB-MP-HAUL-DT5493-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500166912 | CLB-MP-HAUL-DT5493-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500166911 | CLB-MP-HAUL-DT5493-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500166910 | CLB-MP-HAUL-DT5493-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500166909 | CLB-MP-HAUL-DT5493-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500166908 | CLB-MP-HAUL-DT5493-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500166907 | CLB-MP-HAUL-DT5493-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500166906 | CLB-MP-HAUL-DT5493-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500166905 | CLB-MP-HAUL-DT5493-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500166904 | CLB-MP-HAUL-DT5493-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500166903 | CLB-MP-HAUL-DT5493-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500166902 | CLB-MP-HAUL-DT5493-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500166901 | CLB-MP-HAUL-DT5493-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500166900 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500166899 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500166898 | CLB-MP-HAUL-DT5493-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500166897 | CLB-MP-HAUL-DT5493-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500166896 | CLB-MP-HAUL-DT5493-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500166895 | CLB-MP-HAUL-DT5493-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500166894 | CLB-MP-HAUL-DT5493-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500166893 | CLB-MP-HAUL-DT5493-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500166892 | CLB-MP-HAUL-DT5493-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500166891 | CLB-MP-HAUL-DT5493-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500166890 | CLB-MP-HAUL-DT5493-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500166889 | CLB-MP-HAUL-DT5493-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500166888 | CLB-MP-HAUL-DT5493-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500166887 | CLB-MP-HAUL-DT5493-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500166886 | CLB-MP-HAUL-DT5493-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500166885 | CLB-MP-HAUL-DT5493-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500166884 | CLB-MP-HAUL-DT5493-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500166883 | CLB-MP-HAUL-DT5493-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500166882 | CLB-MP-HAUL-DT5493-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500166881 | CLB-MP-HAUL-DT5493-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500166880 | CLB-MP-HAUL-DT5493-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500166879 | CLB-MP-HAUL-DT5493-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500166878 | CLB-MP-HAUL-DT5493-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500166877 | CLB-MP-HAUL-DT5493-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500166876 | CLB-MP-HAUL-DT5493-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500166875 | CLB-MP-HAUL-DT5493-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500166874 | CLB-MP-HAUL-DT5493-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500166873 | CLB-MP-HAUL-DT5493-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500166872 | CLB-MP-HAUL-DT5493-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500166871 | CLB-MP-HAUL-DT5493-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500166870 | CLB-MP-HAUL-DT5493-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500166869 | CLB-MP-HAUL-DT5493-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500166868 | CLB-MP-HAUL-DT5493-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500166867 | CLB-MP-HAUL-DT5493-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500166866 | CLB-MP-HAUL-DT5493-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500166865 | CLB-MP-HAUL-DT5493-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500166864 | CLB-MP-HAUL-DT5493-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500166863 | CLB-MP-HAUL-DT5493-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500166862 | CLB-MP-HAUL-DT5493-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500166861 | CLB-MP-HAUL-DT5493-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500166860 | CLB-MP-HAUL-DT5493-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500166859 | CLB-MP-HAUL-DT5493-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500166858 | CLB-MP-HAUL-DT5493-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500166857 | CLB-MP-HAUL-DT5493-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500166856 | CLB-MP-HAUL-DT5493-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500166855 | CLB-MP-HAUL-DT5493-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500166854 | CLB-MP-HAUL-DT5493-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500166853 | CLB-MP-HAUL-DT5493-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500166852 | CLB-MP-HAUL-DT5493-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500166851 | CLB-MP-HAUL-DT5493-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500166850 | CLB-MP-HAUL-DT5493-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500166849 | CLB-MP-HAUL-DT5493-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500166848 | CLB-MP-HAUL-DT5493-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500166847 | CLB-MP-HAUL-DT5493-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500166846 | CLB-MP-HAUL-DT5493-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500166845 | CLB-MP-HAUL-DT5493-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500166844 | CLB-MP-HAUL-DT5493-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500166843 | CLB-MP-HAUL-DT5493-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500166752 | CLB-MP-HAUL-DT5493-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500166751 | CLB-MP-HAUL-DT5493-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500166750 | CLB-MP-HAUL-DT5493-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500166749 | CLB-MP-HAUL-DT5493-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500166748 | CLB-MP-HAUL-DT5493-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500166747 | CLB-MP-HAUL-DT5493 | DT5493 Liebherr T264 OHT | 1 | 1 | 6500
500166838 | CLB-MP-HAUL-DT5492-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500166837 | CLB-MP-HAUL-DT5492-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500166836 | CLB-MP-HAUL-DT5492-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500166835 | CLB-MP-HAUL-DT5492-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500166834 | CLB-MP-HAUL-DT5492-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500166833 | CLB-MP-HAUL-DT5492-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500166832 | CLB-MP-HAUL-DT5492-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500166831 | CLB-MP-HAUL-DT5492-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500166830 | CLB-MP-HAUL-DT5492-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500166829 | CLB-MP-HAUL-DT5492-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500166828 | CLB-MP-HAUL-DT5492-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500166827 | CLB-MP-HAUL-DT5492-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500166826 | CLB-MP-HAUL-DT5492-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500166825 | CLB-MP-HAUL-DT5492-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500166824 | CLB-MP-HAUL-DT5492-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500166823 | CLB-MP-HAUL-DT5492-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500166822 | CLB-MP-HAUL-DT5492-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500166821 | CLB-MP-HAUL-DT5492-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500166820 | CLB-MP-HAUL-DT5492-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500166819 | CLB-MP-HAUL-DT5492-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500166818 | CLB-MP-HAUL-DT5492-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500166817 | CLB-MP-HAUL-DT5492-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500166816 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500166815 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500166814 | CLB-MP-HAUL-DT5492-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500166813 | CLB-MP-HAUL-DT5492-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500166812 | CLB-MP-HAUL-DT5492-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500166811 | CLB-MP-HAUL-DT5492-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500166810 | CLB-MP-HAUL-DT5492-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500166809 | CLB-MP-HAUL-DT5492-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500166808 | CLB-MP-HAUL-DT5492-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500166807 | CLB-MP-HAUL-DT5492-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500166806 | CLB-MP-HAUL-DT5492-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500166805 | CLB-MP-HAUL-DT5492-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500166804 | CLB-MP-HAUL-DT5492-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500166803 | CLB-MP-HAUL-DT5492-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500166802 | CLB-MP-HAUL-DT5492-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500166801 | CLB-MP-HAUL-DT5492-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500166800 | CLB-MP-HAUL-DT5492-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500166799 | CLB-MP-HAUL-DT5492-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500166798 | CLB-MP-HAUL-DT5492-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500166797 | CLB-MP-HAUL-DT5492-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500166796 | CLB-MP-HAUL-DT5492-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500166795 | CLB-MP-HAUL-DT5492-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500166794 | CLB-MP-HAUL-DT5492-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500166793 | CLB-MP-HAUL-DT5492-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500166792 | CLB-MP-HAUL-DT5492-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500166791 | CLB-MP-HAUL-DT5492-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500166790 | CLB-MP-HAUL-DT5492-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500166789 | CLB-MP-HAUL-DT5492-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500166788 | CLB-MP-HAUL-DT5492-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500166787 | CLB-MP-HAUL-DT5492-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500166786 | CLB-MP-HAUL-DT5492-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500166785 | CLB-MP-HAUL-DT5492-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500166784 | CLB-MP-HAUL-DT5492-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500166783 | CLB-MP-HAUL-DT5492-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500166782 | CLB-MP-HAUL-DT5492-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500166781 | CLB-MP-HAUL-DT5492-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500166780 | CLB-MP-HAUL-DT5492-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500166779 | CLB-MP-HAUL-DT5492-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500166778 | CLB-MP-HAUL-DT5492-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500166777 | CLB-MP-HAUL-DT5492-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500166776 | CLB-MP-HAUL-DT5492-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500166775 | CLB-MP-HAUL-DT5492-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500166774 | CLB-MP-HAUL-DT5492-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500166773 | CLB-MP-HAUL-DT5492-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500166772 | CLB-MP-HAUL-DT5492-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500166771 | CLB-MP-HAUL-DT5492-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500166770 | CLB-MP-HAUL-DT5492-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500166769 | CLB-MP-HAUL-DT5492-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500166768 | CLB-MP-HAUL-DT5492-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500166767 | CLB-MP-HAUL-DT5492-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500166766 | CLB-MP-HAUL-DT5492-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500166765 | CLB-MP-HAUL-DT5492-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500166764 | CLB-MP-HAUL-DT5492-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500166763 | CLB-MP-HAUL-DT5492-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500166762 | CLB-MP-HAUL-DT5492-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500166761 | CLB-MP-HAUL-DT5492-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500166760 | CLB-MP-HAUL-DT5492-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500166759 | CLB-MP-HAUL-DT5492-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500166758 | CLB-MP-HAUL-DT5492-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500166757 | CLB-MP-HAUL-DT5492-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500166756 | CLB-MP-HAUL-DT5492-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500166755 | CLB-MP-HAUL-DT5492-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500166754 | CLB-MP-HAUL-DT5492-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500166753 | CLB-MP-HAUL-DT5492 | DT5492 Liebherr T264 OHT | 1 | 1 | 6500
500166698 | CLB-MP-HAUL-DT5491-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500166697 | CLB-MP-HAUL-DT5491-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500166696 | CLB-MP-HAUL-DT5491-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500166695 | CLB-MP-HAUL-DT5491-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500166694 | CLB-MP-HAUL-DT5491-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500166693 | CLB-MP-HAUL-DT5491-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500166692 | CLB-MP-HAUL-DT5491-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500166691 | CLB-MP-HAUL-DT5491-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500166690 | CLB-MP-HAUL-DT5491-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500166689 | CLB-MP-HAUL-DT5491-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500166688 | CLB-MP-HAUL-DT5491-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500166687 | CLB-MP-HAUL-DT5491-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500166686 | CLB-MP-HAUL-DT5491-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500166685 | CLB-MP-HAUL-DT5491-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500166684 | CLB-MP-HAUL-DT5491-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500166683 | CLB-MP-HAUL-DT5491-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500166682 | CLB-MP-HAUL-DT5491-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500166681 | CLB-MP-HAUL-DT5491-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500166680 | CLB-MP-HAUL-DT5491-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500166679 | CLB-MP-HAUL-DT5491-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500166678 | CLB-MP-HAUL-DT5491-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500166677 | CLB-MP-HAUL-DT5491-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500166676 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500166675 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500166674 | CLB-MP-HAUL-DT5491-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500166673 | CLB-MP-HAUL-DT5491-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500166672 | CLB-MP-HAUL-DT5491-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500166671 | CLB-MP-HAUL-DT5491-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500166670 | CLB-MP-HAUL-DT5491-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500166669 | CLB-MP-HAUL-DT5491-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500166668 | CLB-MP-HAUL-DT5491-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500166667 | CLB-MP-HAUL-DT5491-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500166666 | CLB-MP-HAUL-DT5491-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500166665 | CLB-MP-HAUL-DT5491-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500166664 | CLB-MP-HAUL-DT5491-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500166663 | CLB-MP-HAUL-DT5491-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500166662 | CLB-MP-HAUL-DT5491-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500166661 | CLB-MP-HAUL-DT5491-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500166660 | CLB-MP-HAUL-DT5491-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500166659 | CLB-MP-HAUL-DT5491-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500166658 | CLB-MP-HAUL-DT5491-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500166657 | CLB-MP-HAUL-DT5491-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500166656 | CLB-MP-HAUL-DT5491-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500166655 | CLB-MP-HAUL-DT5491-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500166654 | CLB-MP-HAUL-DT5491-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500166653 | CLB-MP-HAUL-DT5491-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500166652 | CLB-MP-HAUL-DT5491-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500166651 | CLB-MP-HAUL-DT5491-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500166650 | CLB-MP-HAUL-DT5491-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500166649 | CLB-MP-HAUL-DT5491-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500166648 | CLB-MP-HAUL-DT5491-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500166647 | CLB-MP-HAUL-DT5491-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500166646 | CLB-MP-HAUL-DT5491-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500166645 | CLB-MP-HAUL-DT5491-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500166644 | CLB-MP-HAUL-DT5491-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500166643 | CLB-MP-HAUL-DT5491-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500166642 | CLB-MP-HAUL-DT5491-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500166641 | CLB-MP-HAUL-DT5491-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500166640 | CLB-MP-HAUL-DT5491-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500166639 | CLB-MP-HAUL-DT5491-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500166638 | CLB-MP-HAUL-DT5491-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500166637 | CLB-MP-HAUL-DT5491-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500166636 | CLB-MP-HAUL-DT5491-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500166635 | CLB-MP-HAUL-DT5491-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500166634 | CLB-MP-HAUL-DT5491-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500166633 | CLB-MP-HAUL-DT5491-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500166632 | CLB-MP-HAUL-DT5491-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500166631 | CLB-MP-HAUL-DT5491-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500166630 | CLB-MP-HAUL-DT5491-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500166629 | CLB-MP-HAUL-DT5491-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500166628 | CLB-MP-HAUL-DT5491-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500166627 | CLB-MP-HAUL-DT5491-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500166626 | CLB-MP-HAUL-DT5491-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500166625 | CLB-MP-HAUL-DT5491-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500166624 | CLB-MP-HAUL-DT5491-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500166623 | CLB-MP-HAUL-DT5491-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500166622 | CLB-MP-HAUL-DT5491-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500166621 | CLB-MP-HAUL-DT5491-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500166620 | CLB-MP-HAUL-DT5491-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500166619 | CLB-MP-HAUL-DT5491-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500166618 | CLB-MP-HAUL-DT5491-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500166617 | CLB-MP-HAUL-DT5491-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500166616 | CLB-MP-HAUL-DT5491-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500166615 | CLB-MP-HAUL-DT5491-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500166614 | CLB-MP-HAUL-DT5491-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500166613 | CLB-MP-HAUL-DT5491 | DT5491 Liebherr T264 OHT | 1 | 1 | 6500
500166532 | CLB-MP-HAUL-DT5488-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 968 | 968 | 6500
500166531 | CLB-MP-HAUL-DT5488-STRUCT-TRAYS | Tray | 968 | 968 | 6500
500166530 | CLB-MP-HAUL-DT5488-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 968 | 968 | 6500
500166529 | CLB-MP-HAUL-DT5488-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 968 | 968 | 6500
500166528 | CLB-MP-HAUL-DT5488-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 968 | 968 | 6500
500166527 | CLB-MP-HAUL-DT5488-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 968 | 968 | 6500
500166526 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-SEATS | Operators Seat | 968 | 968 | 6500
500166525 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 968 | 968 | 6500
500166524 | CLB-MP-HAUL-DT5488-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 968 | 968 | 6500
500166523 | CLB-MP-HAUL-DT5488-STRUCT-CABIN | Operators Cabin | 968 | 968 | 6500
500166522 | CLB-MP-HAUL-DT5488-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 968 | 968 | 6500
500166521 | CLB-MP-HAUL-DT5488-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 968 | 968 | 6500
500166520 | CLB-MP-HAUL-DT5488-STRSYS-STVLV | Valve Flow Amplifier | 968 | 968 | 6500
500166519 | CLB-MP-HAUL-DT5488-STRSYS-STRIA | Steering Idler Arm | 968 | 968 | 6500
500166518 | CLB-MP-HAUL-DT5488-STRSYS-STRCY-STCYR | Steering Cylinder RH | 968 | 968 | 6500
500166517 | CLB-MP-HAUL-DT5488-STRSYS-STRCY-STCYL | Steering Cylinder LH | 968 | 968 | 6500
500166516 | CLB-MP-HAUL-DT5488-STRSYS-STLTR | Steering Linkages & Tie Rods | 968 | 968 | 6500
500166515 | CLB-MP-HAUL-DT5488-STRSYS-STCNT | Steering Control Unit | 968 | 968 | 6500
500166514 | CLB-MP-HAUL-DT5488-STRSYS-STACC-SACRH | Accumulator Steering ODS | 968 | 968 | 6500
500166513 | CLB-MP-HAUL-DT5488-STRSYS-STACC-SACLH | Accumulator Steering DS | 968 | 968 | 6500
500166512 | CLB-MP-HAUL-DT5488-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 968 | 968 | 6500
500166511 | CLB-MP-HAUL-DT5488-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 968 | 968 | 6500
500166510 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 968 | 968 | 6500
500166509 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 968 | 968 | 6500
500166508 | CLB-MP-HAUL-DT5488-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 968 | 968 | 6500
500166507 | CLB-MP-HAUL-DT5488-HYDSYS-HYDOC | Hydraulic Oil Cooler | 968 | 968 | 6500
500166506 | CLB-MP-HAUL-DT5488-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 968 | 968 | 6500
500166505 | CLB-MP-HAUL-DT5488-HYDSYS-HOMAN | Hoist Manifold | 968 | 968 | 6500
500166504 | CLB-MP-HAUL-DT5488-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 968 | 968 | 6500
500166503 | CLB-MP-HAUL-DT5488-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 968 | 968 | 6500
500166502 | CLB-MP-HAUL-DT5488-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 968 | 968 | 6500
500166501 | CLB-MP-HAUL-DT5488-HYDSYS-GROCL | Gear Oil Cooler | 968 | 968 | 6500
500166500 | CLB-MP-HAUL-DT5488-GRSYST-ALBPP | Auto Lube Pump | 968 | 968 | 6500
500166499 | CLB-MP-HAUL-DT5488-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 968 | 968 | 6500
500166498 | CLB-MP-HAUL-DT5488-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 968 | 968 | 6500
500166497 | CLB-MP-HAUL-DT5488-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 968 | 968 | 6500
500166496 | CLB-MP-HAUL-DT5488-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 968 | 968 | 6500
500166495 | CLB-MP-HAUL-DT5488-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 968 | 968 | 6500
500166494 | CLB-MP-HAUL-DT5488-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 968 | 968 | 6500
500166493 | CLB-MP-HAUL-DT5488-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 968 | 968 | 6500
500166492 | CLB-MP-HAUL-DT5488-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 968 | 968 | 6500
500166491 | CLB-MP-HAUL-DT5488-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 968 | 968 | 6500
500166490 | CLB-MP-HAUL-DT5488-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 968 | 968 | 6500
500166489 | CLB-MP-HAUL-DT5488-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 968 | 968 | 6500
500166488 | CLB-MP-HAUL-DT5488-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 968 | 968 | 6500
500166487 | CLB-MP-HAUL-DT5488-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 968 | 968 | 6500
500166486 | CLB-MP-HAUL-DT5488-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 968 | 968 | 6500
500166485 | CLB-MP-HAUL-DT5488-ENGINE-INTEX-TBORF | Turbocharger RH Front | 968 | 968 | 6500
500166484 | CLB-MP-HAUL-DT5488-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 968 | 968 | 6500
500166483 | CLB-MP-HAUL-DT5488-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 968 | 968 | 6500
500166482 | CLB-MP-HAUL-DT5488-ENGINE-INTEX-AFTER | Aftercooler Engine | 968 | 968 | 6500
500166481 | CLB-MP-HAUL-DT5488-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 968 | 968 | 6500
500166480 | CLB-MP-HAUL-DT5488-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 968 | 968 | 6500
500166479 | CLB-MP-HAUL-DT5488-ENGINE-FUSYS-FUINJ | Fuel Injectors | 968 | 968 | 6500
500166478 | CLB-MP-HAUL-DT5488-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 968 | 968 | 6500
500166477 | CLB-MP-HAUL-DT5488-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 968 | 968 | 6500
500166476 | CLB-MP-HAUL-DT5488-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 968 | 968 | 6500
500166475 | CLB-MP-HAUL-DT5488-ENGINE-COSYS-HTWPP | Engine Water Pump | 968 | 968 | 6500
500166474 | CLB-MP-HAUL-DT5488-ENGINE-COSYS-COFAN | Fan Cooling System | 968 | 968 | 6500
500166473 | CLB-MP-HAUL-DT5488-ENGINE | Engine Assembly Cummins QSK60 | 968 | 968 | 6500
500166472 | CLB-MP-HAUL-DT5488-ELCTLV-START-STMUP | Starter Motor Upper | 968 | 968 | 6500
500166471 | CLB-MP-HAUL-DT5488-ELCTLV-START-STMLO | Starter Motor Lower | 968 | 968 | 6500
500166470 | CLB-MP-HAUL-DT5488-ELCTLV-HARNS | Electrical Harness | 968 | 968 | 6500
500166469 | CLB-MP-HAUL-DT5488-ELCTLV-CHARG-BATTY | Batteries | 968 | 968 | 6500
500166468 | CLB-MP-HAUL-DT5488-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 968 | 968 | 6500
500166467 | CLB-MP-HAUL-DT5488-ELCTHV-HVGBX-HVRES | Grid Resistors | 968 | 968 | 6500
500166466 | CLB-MP-HAUL-DT5488-ELCTHV-HVGBM | Grid Box Blower Motor | 968 | 968 | 6500
500166465 | CLB-MP-HAUL-DT5488-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 968 | 968 | 6500
500166464 | CLB-MP-HAUL-DT5488-ELCTHV-HVBLW | Main High Voltage Blower | 968 | 968 | 6500
500166463 | CLB-MP-HAUL-DT5488-ELCTHV-HVALT | High Voltage Alternator | 968 | 968 | 6500
500166462 | CLB-MP-HAUL-DT5488-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 968 | 968 | 6500
500166461 | CLB-MP-HAUL-DT5488-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 968 | 968 | 6500
500166460 | CLB-MP-HAUL-DT5488-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 968 | 968 | 6500
500166459 | CLB-MP-HAUL-DT5488-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 968 | 968 | 6500
500166458 | CLB-MP-HAUL-DT5488-BRKSYS-BRVTR | Brake Treadle Valve | 968 | 968 | 6500
500166457 | CLB-MP-HAUL-DT5488-BRKSYS-BRVRL | Brake Dual Relay Valves | 968 | 968 | 6500
500166456 | CLB-MP-HAUL-DT5488-BRKSYS-BRVLV | Brake & Steering Manifold | 968 | 968 | 6500
500166455 | CLB-MP-HAUL-DT5488-BRKSYS-BRSTV | Brake & Steering Valve | 968 | 968 | 6500
500166454 | CLB-MP-HAUL-DT5488-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 968 | 968 | 6500
500166453 | CLB-MP-HAUL-DT5488-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 968 | 968 | 6500
500165472 | CLB-MP-HAUL-DT5488-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 968 | 968 | 6500
500165471 | CLB-MP-HAUL-DT5488-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 968 | 968 | 6500
500165470 | CLB-MP-HAUL-DT5488-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 968 | 968 | 6500
500165469 | CLB-MP-HAUL-DT5488-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 968 | 968 | 6500
500165468 | CLB-MP-HAUL-DT5488-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 968 | 968 | 6500
500165467 | CLB-MP-HAUL-DT5488 | DT5488 Liebherr T264 OHT | 968 | 968 | 6500
500165252 | CLB-MP-HAUL-DT5487-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1030 | 1030 | 6500
500165251 | CLB-MP-HAUL-DT5487-STRUCT-TRAYS | Tray | 1030 | 1030 | 6500
500165250 | CLB-MP-HAUL-DT5487-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1030 | 1030 | 6500
500165249 | CLB-MP-HAUL-DT5487-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1030 | 1030 | 6500
500165248 | CLB-MP-HAUL-DT5487-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1030 | 1030 | 6500
500165247 | CLB-MP-HAUL-DT5487-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1030 | 1030 | 6500
500165246 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-SEATS | Operators Seat | 1030 | 1030 | 6500
500165245 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1030 | 1030 | 6500
500165244 | CLB-MP-HAUL-DT5487-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1030 | 1030 | 6500
500165243 | CLB-MP-HAUL-DT5487-STRUCT-CABIN | Operators Cabin | 1030 | 1030 | 6500
500165242 | CLB-MP-HAUL-DT5487-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1030 | 1030 | 6500
500165241 | CLB-MP-HAUL-DT5487-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1030 | 1030 | 6500
500165240 | CLB-MP-HAUL-DT5487-STRSYS-STVLV | Valve Flow Amplifier | 1030 | 1030 | 6500
500165239 | CLB-MP-HAUL-DT5487-STRSYS-STRIA | Steering Idler Arm | 1030 | 1030 | 6500
500165238 | CLB-MP-HAUL-DT5487-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1030 | 1030 | 6500
500165237 | CLB-MP-HAUL-DT5487-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1030 | 1030 | 6500
500165236 | CLB-MP-HAUL-DT5487-STRSYS-STLTR | Steering Linkages & Tie Rods | 1030 | 1030 | 6500
500165235 | CLB-MP-HAUL-DT5487-STRSYS-STCNT | Steering Control Unit | 1030 | 1030 | 6500
500165234 | CLB-MP-HAUL-DT5487-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1030 | 1030 | 6500
500165233 | CLB-MP-HAUL-DT5487-STRSYS-STACC-SACLH | Accumulator Steering DS | 1030 | 1030 | 6500
500165232 | CLB-MP-HAUL-DT5487-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1030 | 1030 | 6500
500165231 | CLB-MP-HAUL-DT5487-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1030 | 1030 | 6500
500165230 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1030 | 1030 | 6500
500165229 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1030 | 1030 | 6500
500165228 | CLB-MP-HAUL-DT5487-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1030 | 1030 | 6500
500165227 | CLB-MP-HAUL-DT5487-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1030 | 1030 | 6500
500165226 | CLB-MP-HAUL-DT5487-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1030 | 1030 | 6500
500165225 | CLB-MP-HAUL-DT5487-HYDSYS-HOMAN | Hoist Manifold | 1030 | 1030 | 6500
500165224 | CLB-MP-HAUL-DT5487-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1030 | 1030 | 6500
500165223 | CLB-MP-HAUL-DT5487-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1030 | 1030 | 6500
500165222 | CLB-MP-HAUL-DT5487-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1030 | 1030 | 6500
500165221 | CLB-MP-HAUL-DT5487-HYDSYS-GROCL | Gear Oil Cooler | 1030 | 1030 | 6500
500165220 | CLB-MP-HAUL-DT5487-GRSYST-ALBPP | Auto Lube Pump | 1030 | 1030 | 6500
500165219 | CLB-MP-HAUL-DT5487-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1030 | 1030 | 6500
500165218 | CLB-MP-HAUL-DT5487-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1030 | 1030 | 6500
500165217 | CLB-MP-HAUL-DT5487-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1030 | 1030 | 6500
500165216 | CLB-MP-HAUL-DT5487-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1030 | 1030 | 6500
500165215 | CLB-MP-HAUL-DT5487-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1030 | 1030 | 6500
500165214 | CLB-MP-HAUL-DT5487-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1030 | 1030 | 6500
500165213 | CLB-MP-HAUL-DT5487-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1030 | 1030 | 6500
500165212 | CLB-MP-HAUL-DT5487-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1030 | 1030 | 6500
500165211 | CLB-MP-HAUL-DT5487-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1030 | 1030 | 6500
500165210 | CLB-MP-HAUL-DT5487-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1030 | 1030 | 6500
500165209 | CLB-MP-HAUL-DT5487-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1030 | 1030 | 6500
500165208 | CLB-MP-HAUL-DT5487-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1030 | 1030 | 6500
500165207 | CLB-MP-HAUL-DT5487-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1030 | 1030 | 6500
500165206 | CLB-MP-HAUL-DT5487-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1030 | 1030 | 6500
500165205 | CLB-MP-HAUL-DT5487-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1030 | 1030 | 6500
500165204 | CLB-MP-HAUL-DT5487-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1030 | 1030 | 6500
500165203 | CLB-MP-HAUL-DT5487-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1030 | 1030 | 6500
500165202 | CLB-MP-HAUL-DT5487-ENGINE-INTEX-AFTER | Aftercooler Engine | 1030 | 1030 | 6500
500165201 | CLB-MP-HAUL-DT5487-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1030 | 1030 | 6500
500165200 | CLB-MP-HAUL-DT5487-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1030 | 1030 | 6500
500165199 | CLB-MP-HAUL-DT5487-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1030 | 1030 | 6500
500165198 | CLB-MP-HAUL-DT5487-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1030 | 1030 | 6500
500165197 | CLB-MP-HAUL-DT5487-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1030 | 1030 | 6500
500165196 | CLB-MP-HAUL-DT5487-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1030 | 1030 | 6500
500165195 | CLB-MP-HAUL-DT5487-ENGINE-COSYS-HTWPP | Engine Water Pump | 1030 | 1030 | 6500
500165194 | CLB-MP-HAUL-DT5487-ENGINE-COSYS-COFAN | Fan Cooling System | 1030 | 1030 | 6500
500165193 | CLB-MP-HAUL-DT5487-ENGINE | Engine Assembly Cummins QSK60 | 1030 | 1030 | 6500
500165192 | CLB-MP-HAUL-DT5487-ELCTLV-START-STMUP | Starter Motor Upper | 1030 | 1030 | 6500
500165191 | CLB-MP-HAUL-DT5487-ELCTLV-START-STMLO | Starter Motor Lower | 1030 | 1030 | 6500
500165190 | CLB-MP-HAUL-DT5487-ELCTLV-HARNS | Electrical Harness | 1030 | 1030 | 6500
500165189 | CLB-MP-HAUL-DT5487-ELCTLV-CHARG-BATTY | Batteries | 1030 | 1030 | 6500
500165188 | CLB-MP-HAUL-DT5487-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1030 | 1030 | 6500
500165187 | CLB-MP-HAUL-DT5487-ELCTHV-HVGBX-HVRES | Grid Resistors | 1030 | 1030 | 6500
500165186 | CLB-MP-HAUL-DT5487-ELCTHV-HVGBM | Grid Box Blower Motor | 1030 | 1030 | 6500
500165185 | CLB-MP-HAUL-DT5487-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1030 | 1030 | 6500
500165184 | CLB-MP-HAUL-DT5487-ELCTHV-HVBLW | Main High Voltage Blower | 1030 | 1030 | 6500
500165183 | CLB-MP-HAUL-DT5487-ELCTHV-HVALT | High Voltage Alternator | 1030 | 1030 | 6500
500165182 | CLB-MP-HAUL-DT5487-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1030 | 1030 | 6500
500165181 | CLB-MP-HAUL-DT5487-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1030 | 1030 | 6500
500165180 | CLB-MP-HAUL-DT5487-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1030 | 1030 | 6500
500165179 | CLB-MP-HAUL-DT5487-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1030 | 1030 | 6500
500165178 | CLB-MP-HAUL-DT5487-BRKSYS-BRVTR | Brake Treadle Valve | 1030 | 1030 | 6500
500165177 | CLB-MP-HAUL-DT5487-BRKSYS-BRVRL | Brake Dual Relay Valves | 1030 | 1030 | 6500
500165176 | CLB-MP-HAUL-DT5487-BRKSYS-BRVLV | Brake & Steering Manifold | 1030 | 1030 | 6500
500165175 | CLB-MP-HAUL-DT5487-BRKSYS-BRSTV | Brake & Steering Valve | 1030 | 1030 | 6500
500165174 | CLB-MP-HAUL-DT5487-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1030 | 1030 | 6500
500165173 | CLB-MP-HAUL-DT5487-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1030 | 1030 | 6500
500164982 | CLB-MP-HAUL-DT5487-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1030 | 1030 | 6500
500164981 | CLB-MP-HAUL-DT5487-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1030 | 1030 | 6500
500164980 | CLB-MP-HAUL-DT5487-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1030 | 1030 | 6500
500164979 | CLB-MP-HAUL-DT5487-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1030 | 1030 | 6500
500164978 | CLB-MP-HAUL-DT5487-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1030 | 1030 | 6500
500164977 | CLB-MP-HAUL-DT5487 | DT5487 Liebherr T264 OHT | 1030 | 1030 | 6500
500165157 | CLB-MP-HAUL-DT5486-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 66 | 66 | 6500
500165156 | CLB-MP-HAUL-DT5486-STRUCT-TRAYS | Tray | 66 | 66 | 6500
500165155 | CLB-MP-HAUL-DT5486-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 66 | 66 | 6500
500165154 | CLB-MP-HAUL-DT5486-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 66 | 66 | 6500
500165153 | CLB-MP-HAUL-DT5486-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 66 | 66 | 6500
500165152 | CLB-MP-HAUL-DT5486-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 66 | 66 | 6500
500165151 | CLB-MP-HAUL-DT5486-STRUCT-CABIN-SEATS | Operators Seat | 66 | 66 | 6500
500165150 | CLB-MP-HAUL-DT5486-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 66 | 66 | 6500
500165149 | CLB-MP-HAUL-DT5486-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 66 | 66 | 6500
500165148 | CLB-MP-HAUL-DT5486-STRUCT-CABIN | Operators Cabin | 66 | 66 | 6500
500165147 | CLB-MP-HAUL-DT5486-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 66 | 66 | 6500
500165146 | CLB-MP-HAUL-DT5486-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 66 | 66 | 6500
500165145 | CLB-MP-HAUL-DT5486-STRSYS-STVLV | Valve Flow Amplifier | 66 | 66 | 6500
500165144 | CLB-MP-HAUL-DT5486-STRSYS-STRIA | Steering Idler Arm | 66 | 66 | 6500
500165143 | CLB-MP-HAUL-DT5486-STRSYS-STRCY-STCYR | Steering Cylinder RH | 66 | 66 | 6500
500165142 | CLB-MP-HAUL-DT5486-STRSYS-STRCY-STCYL | Steering Cylinder LH | 66 | 66 | 6500
500165141 | CLB-MP-HAUL-DT5486-STRSYS-STLTR | Steering Linkages & Tie Rods | 66 | 66 | 6500
500165140 | CLB-MP-HAUL-DT5486-STRSYS-STCNT | Steering Control Unit | 66 | 66 | 6500
500165139 | CLB-MP-HAUL-DT5486-STRSYS-STACC-SACRH | Accumulator Steering ODS | 66 | 66 | 6500
500165138 | CLB-MP-HAUL-DT5486-STRSYS-STACC-SACLH | Accumulator Steering DS | 66 | 66 | 6500
500165137 | CLB-MP-HAUL-DT5486-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 66 | 66 | 6500
500165136 | CLB-MP-HAUL-DT5486-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 66 | 66 | 6500
500165135 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 66 | 66 | 6500
500165134 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 66 | 66 | 6500
500165133 | CLB-MP-HAUL-DT5486-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 66 | 66 | 6500
500165132 | CLB-MP-HAUL-DT5486-HYDSYS-HYDOC | Hydraulic Oil Cooler | 66 | 66 | 6500
500165131 | CLB-MP-HAUL-DT5486-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 66 | 66 | 6500
500165130 | CLB-MP-HAUL-DT5486-HYDSYS-HOMAN | Hoist Manifold | 66 | 66 | 6500
500165129 | CLB-MP-HAUL-DT5486-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 66 | 66 | 6500
500165128 | CLB-MP-HAUL-DT5486-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 66 | 66 | 6500
500165127 | CLB-MP-HAUL-DT5486-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 66 | 66 | 6500
500165126 | CLB-MP-HAUL-DT5486-HYDSYS-GROCL | Gear Oil Cooler | 66 | 66 | 6500
500165125 | CLB-MP-HAUL-DT5486-GRSYST-ALBPP | Auto Lube Pump | 66 | 66 | 6500
500165124 | CLB-MP-HAUL-DT5486-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 66 | 66 | 6500
500165123 | CLB-MP-HAUL-DT5486-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 66 | 66 | 6500
500165122 | CLB-MP-HAUL-DT5486-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 66 | 66 | 6500
500165121 | CLB-MP-HAUL-DT5486-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 66 | 66 | 6500
500165120 | CLB-MP-HAUL-DT5486-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 66 | 66 | 6500
500165119 | CLB-MP-HAUL-DT5486-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 66 | 66 | 6500
500165118 | CLB-MP-HAUL-DT5486-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 66 | 66 | 6500
500165117 | CLB-MP-HAUL-DT5486-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 66 | 66 | 6500
500165116 | CLB-MP-HAUL-DT5486-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 66 | 66 | 6500
500165115 | CLB-MP-HAUL-DT5486-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 66 | 66 | 6500
500165114 | CLB-MP-HAUL-DT5486-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 66 | 66 | 6500
500165113 | CLB-MP-HAUL-DT5486-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 66 | 66 | 6500
500165112 | CLB-MP-HAUL-DT5486-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 66 | 66 | 6500
500165111 | CLB-MP-HAUL-DT5486-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 66 | 66 | 6500
500165110 | CLB-MP-HAUL-DT5486-ENGINE-INTEX-TBORF | Turbocharger RH Front | 66 | 66 | 6500
500165109 | CLB-MP-HAUL-DT5486-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 66 | 66 | 6500
500165108 | CLB-MP-HAUL-DT5486-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 66 | 66 | 6500
500165107 | CLB-MP-HAUL-DT5486-ENGINE-INTEX-AFTER | Aftercooler Engine | 66 | 66 | 6500
500165106 | CLB-MP-HAUL-DT5486-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 66 | 66 | 6500
500165105 | CLB-MP-HAUL-DT5486-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 66 | 66 | 6500
500165104 | CLB-MP-HAUL-DT5486-ENGINE-FUSYS-FUINJ | Fuel Injectors | 66 | 66 | 6500
500165103 | CLB-MP-HAUL-DT5486-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 66 | 66 | 6500
500165102 | CLB-MP-HAUL-DT5486-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 66 | 66 | 6500
500165101 | CLB-MP-HAUL-DT5486-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 66 | 66 | 6500
500165100 | CLB-MP-HAUL-DT5486-ENGINE-COSYS-HTWPP | Engine Water Pump | 66 | 66 | 6500
500165099 | CLB-MP-HAUL-DT5486-ENGINE-COSYS-COFAN | Fan Cooling System | 66 | 66 | 6500
500165098 | CLB-MP-HAUL-DT5486-ENGINE | Engine Assembly Cummins QSK60 | 66 | 66 | 6500
500165097 | CLB-MP-HAUL-DT5486-ELCTLV-START-STMUP | Starter Motor Upper | 66 | 66 | 6500
500165096 | CLB-MP-HAUL-DT5486-ELCTLV-START-STMLO | Starter Motor Lower | 66 | 66 | 6500
500165095 | CLB-MP-HAUL-DT5486-ELCTLV-HARNS | Electrical Harness | 66 | 66 | 6500
500165094 | CLB-MP-HAUL-DT5486-ELCTLV-CHARG-BATTY | Batteries | 66 | 66 | 6500
500165093 | CLB-MP-HAUL-DT5486-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 66 | 66 | 6500
500165092 | CLB-MP-HAUL-DT5486-ELCTHV-HVGBX-HVRES | Grid Resistors | 66 | 66 | 6500
500165091 | CLB-MP-HAUL-DT5486-ELCTHV-HVGBM | Grid Box Blower Motor | 66 | 66 | 6500
500165090 | CLB-MP-HAUL-DT5486-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 66 | 66 | 6500
500165089 | CLB-MP-HAUL-DT5486-ELCTHV-HVBLW | Main High Voltage Blower | 66 | 66 | 6500
500165088 | CLB-MP-HAUL-DT5486-ELCTHV-HVALT | High Voltage Alternator | 66 | 66 | 6500
500165087 | CLB-MP-HAUL-DT5486-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 66 | 66 | 6500
500165086 | CLB-MP-HAUL-DT5486-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 66 | 66 | 6500
500165085 | CLB-MP-HAUL-DT5486-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 66 | 66 | 6500
500165084 | CLB-MP-HAUL-DT5486-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 66 | 66 | 6500
500165083 | CLB-MP-HAUL-DT5486-BRKSYS-BRVTR | Brake Treadle Valve | 66 | 66 | 6500
500165082 | CLB-MP-HAUL-DT5486-BRKSYS-BRVRL | Brake Dual Relay Valves | 66 | 66 | 6500
500165081 | CLB-MP-HAUL-DT5486-BRKSYS-BRVLV | Brake & Steering Manifold | 66 | 66 | 6500
500165080 | CLB-MP-HAUL-DT5486-BRKSYS-BRSTV | Brake & Steering Valve | 66 | 66 | 6500
500165079 | CLB-MP-HAUL-DT5486-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 66 | 66 | 6500
500165078 | CLB-MP-HAUL-DT5486-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 66 | 66 | 6500
500165077 | CLB-MP-HAUL-DT5486-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 66 | 66 | 6500
500165076 | CLB-MP-HAUL-DT5486-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 66 | 66 | 6500
500165075 | CLB-MP-HAUL-DT5486-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 66 | 66 | 6500
500165074 | CLB-MP-HAUL-DT5486-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 66 | 66 | 6500
500165073 | CLB-MP-HAUL-DT5486-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 66 | 66 | 6500
500164862 | CLB-MP-HAUL-DT5486 | DT5486 Liebherr T264 OHT | 66 | 66 | 6500
500165065 | CLB-MP-HAUL-DT5485-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 55 | 55 | 6500
500165064 | CLB-MP-HAUL-DT5485-STRUCT-TRAYS | Tray | 55 | 55 | 6500
500165063 | CLB-MP-HAUL-DT5485-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 55 | 55 | 6500
500165062 | CLB-MP-HAUL-DT5485-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 55 | 55 | 6500
500165061 | CLB-MP-HAUL-DT5485-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 55 | 55 | 6500
500165060 | CLB-MP-HAUL-DT5485-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 55 | 55 | 6500
500165059 | CLB-MP-HAUL-DT5485-STRUCT-CABIN-SEATS | Operators Seat | 55 | 55 | 6500
500165058 | CLB-MP-HAUL-DT5485-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 55 | 55 | 6500
500165057 | CLB-MP-HAUL-DT5485-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 55 | 55 | 6500
500165056 | CLB-MP-HAUL-DT5485-STRUCT-CABIN | Operators Cabin | 55 | 55 | 6500
500165055 | CLB-MP-HAUL-DT5485-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 55 | 55 | 6500
500165054 | CLB-MP-HAUL-DT5485-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 55 | 55 | 6500
500165053 | CLB-MP-HAUL-DT5485-STRSYS-STVLV | Valve Flow Amplifier | 55 | 55 | 6500
500165052 | CLB-MP-HAUL-DT5485-STRSYS-STRIA | Steering Idler Arm | 55 | 55 | 6500
500165051 | CLB-MP-HAUL-DT5485-STRSYS-STRCY-STCYR | Steering Cylinder RH | 55 | 55 | 6500
500165050 | CLB-MP-HAUL-DT5485-STRSYS-STRCY-STCYL | Steering Cylinder LH | 55 | 55 | 6500
500165049 | CLB-MP-HAUL-DT5485-STRSYS-STLTR | Steering Linkages & Tie Rods | 55 | 55 | 6500
500165048 | CLB-MP-HAUL-DT5485-STRSYS-STCNT | Steering Control Unit | 55 | 55 | 6500
500165047 | CLB-MP-HAUL-DT5485-STRSYS-STACC-SACRH | Accumulator Steering ODS | 55 | 55 | 6500
500165046 | CLB-MP-HAUL-DT5485-STRSYS-STACC-SACLH | Accumulator Steering DS | 55 | 55 | 6500
500165045 | CLB-MP-HAUL-DT5485-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 55 | 55 | 6500
500165044 | CLB-MP-HAUL-DT5485-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 55 | 55 | 6500
500165043 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 55 | 55 | 6500
500165042 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 55 | 55 | 6500
500165041 | CLB-MP-HAUL-DT5485-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 55 | 55 | 6500
500165040 | CLB-MP-HAUL-DT5485-HYDSYS-HYDOC | Hydraulic Oil Cooler | 55 | 55 | 6500
500165039 | CLB-MP-HAUL-DT5485-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 55 | 55 | 6500
500165038 | CLB-MP-HAUL-DT5485-HYDSYS-HOMAN | Hoist Manifold | 55 | 55 | 6500
500165037 | CLB-MP-HAUL-DT5485-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 55 | 55 | 6500
500165036 | CLB-MP-HAUL-DT5485-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 55 | 55 | 6500
500165035 | CLB-MP-HAUL-DT5485-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 55 | 55 | 6500
500165034 | CLB-MP-HAUL-DT5485-HYDSYS-GROCL | Gear Oil Cooler | 55 | 55 | 6500
500165033 | CLB-MP-HAUL-DT5485-GRSYST-ALBPP | Auto Lube Pump | 55 | 55 | 6500
500165032 | CLB-MP-HAUL-DT5485-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 55 | 55 | 6500
500165031 | CLB-MP-HAUL-DT5485-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 55 | 55 | 6500
500165030 | CLB-MP-HAUL-DT5485-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 55 | 55 | 6500
500165029 | CLB-MP-HAUL-DT5485-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 55 | 55 | 6500
500165028 | CLB-MP-HAUL-DT5485-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 55 | 55 | 6500
500165027 | CLB-MP-HAUL-DT5485-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 55 | 55 | 6500
500165026 | CLB-MP-HAUL-DT5485-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 55 | 55 | 6500
500165025 | CLB-MP-HAUL-DT5485-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 55 | 55 | 6500
500165024 | CLB-MP-HAUL-DT5485-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 55 | 55 | 6500
500165023 | CLB-MP-HAUL-DT5485-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 55 | 55 | 6500
500165022 | CLB-MP-HAUL-DT5485-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 55 | 55 | 6500
500165021 | CLB-MP-HAUL-DT5485-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 55 | 55 | 6500
500165020 | CLB-MP-HAUL-DT5485-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 55 | 55 | 6500
500165019 | CLB-MP-HAUL-DT5485-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 55 | 55 | 6500
500165018 | CLB-MP-HAUL-DT5485-ENGINE-INTEX-TBORF | Turbocharger RH Front | 55 | 55 | 6500
500165017 | CLB-MP-HAUL-DT5485-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 55 | 55 | 6500
500165016 | CLB-MP-HAUL-DT5485-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 55 | 55 | 6500
500165015 | CLB-MP-HAUL-DT5485-ENGINE-INTEX-AFTER | Aftercooler Engine | 55 | 55 | 6500
500165014 | CLB-MP-HAUL-DT5485-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 55 | 55 | 6500
500165013 | CLB-MP-HAUL-DT5485-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 55 | 55 | 6500
500165012 | CLB-MP-HAUL-DT5485-ENGINE-FUSYS-FUINJ | Fuel Injectors | 55 | 55 | 6500
500165011 | CLB-MP-HAUL-DT5485-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 55 | 55 | 6500
500165010 | CLB-MP-HAUL-DT5485-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 55 | 55 | 6500
500165009 | CLB-MP-HAUL-DT5485-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 55 | 55 | 6500
500165008 | CLB-MP-HAUL-DT5485-ENGINE-COSYS-HTWPP | Engine Water Pump | 55 | 55 | 6500
500165007 | CLB-MP-HAUL-DT5485-ENGINE-COSYS-COFAN | Fan Cooling System | 55 | 55 | 6500
500165006 | CLB-MP-HAUL-DT5485-ENGINE | Engine Assembly Cummins QSK60 | 55 | 55 | 6500
500165005 | CLB-MP-HAUL-DT5485-ELCTLV-START-STMUP | Starter Motor Upper | 55 | 55 | 6500
500165004 | CLB-MP-HAUL-DT5485-ELCTLV-START-STMLO | Starter Motor Lower | 55 | 55 | 6500
500165003 | CLB-MP-HAUL-DT5485-ELCTLV-HARNS | Electrical Harness | 55 | 55 | 6500
500165002 | CLB-MP-HAUL-DT5485-ELCTLV-CHARG-BATTY | Batteries | 55 | 55 | 6500
500165001 | CLB-MP-HAUL-DT5485-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 55 | 55 | 6500
500165000 | CLB-MP-HAUL-DT5485-ELCTHV-HVGBX-HVRES | Grid Resistors | 55 | 55 | 6500
500164999 | CLB-MP-HAUL-DT5485-ELCTHV-HVGBM | Grid Box Blower Motor | 55 | 55 | 6500
500164998 | CLB-MP-HAUL-DT5485-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 55 | 55 | 6500
500164997 | CLB-MP-HAUL-DT5485-ELCTHV-HVBLW | Main High Voltage Blower | 55 | 55 | 6500
500164996 | CLB-MP-HAUL-DT5485-ELCTHV-HVALT | High Voltage Alternator | 55 | 55 | 6500
500164995 | CLB-MP-HAUL-DT5485-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 55 | 55 | 6500
500164994 | CLB-MP-HAUL-DT5485-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 55 | 55 | 6500
500164993 | CLB-MP-HAUL-DT5485-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 55 | 55 | 6500
500164992 | CLB-MP-HAUL-DT5485-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 55 | 55 | 6500
500164991 | CLB-MP-HAUL-DT5485-BRKSYS-BRVTR | Brake Treadle Valve | 55 | 55 | 6500
500164990 | CLB-MP-HAUL-DT5485-BRKSYS-BRVRL | Brake Dual Relay Valves | 55 | 55 | 6500
500164989 | CLB-MP-HAUL-DT5485-BRKSYS-BRVLV | Brake & Steering Manifold | 55 | 55 | 6500
500164988 | CLB-MP-HAUL-DT5485-BRKSYS-BRSTV | Brake & Steering Valve | 55 | 55 | 6500
500164987 | CLB-MP-HAUL-DT5485-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 55 | 55 | 6500
500164986 | CLB-MP-HAUL-DT5485-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 55 | 55 | 6500
500164985 | CLB-MP-HAUL-DT5485-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 55 | 55 | 6500
500164984 | CLB-MP-HAUL-DT5485-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 55 | 55 | 6500
500164983 | CLB-MP-HAUL-DT5485-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 55 | 55 | 6500
500164872 | CLB-MP-HAUL-DT5485-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 55 | 55 | 6500
500164871 | CLB-MP-HAUL-DT5485-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 55 | 55 | 6500
500164870 | CLB-MP-HAUL-DT5485 | DT5485 Liebherr T264 OHT | 55 | 55 | 6500
500164958 | CLB-MP-HAUL-DT5484-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 44 | 44 | 6500
500164957 | CLB-MP-HAUL-DT5484-STRUCT-TRAYS | Tray | 44 | 44 | 6500
500164956 | CLB-MP-HAUL-DT5484-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 44 | 44 | 6500
500164955 | CLB-MP-HAUL-DT5484-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 44 | 44 | 6500
500164954 | CLB-MP-HAUL-DT5484-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 44 | 44 | 6500
500164953 | CLB-MP-HAUL-DT5484-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 44 | 44 | 6500
500164952 | CLB-MP-HAUL-DT5484-STRUCT-CABIN-SEATS | Operators Seat | 44 | 44 | 6500
500164951 | CLB-MP-HAUL-DT5484-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 44 | 44 | 6500
500164950 | CLB-MP-HAUL-DT5484-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 44 | 44 | 6500
500164949 | CLB-MP-HAUL-DT5484-STRUCT-CABIN | Operators Cabin | 44 | 44 | 6500
500164948 | CLB-MP-HAUL-DT5484-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 44 | 44 | 6500
500164947 | CLB-MP-HAUL-DT5484-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 44 | 44 | 6500
500164946 | CLB-MP-HAUL-DT5484-STRSYS-STVLV | Valve Flow Amplifier | 44 | 44 | 6500
500164945 | CLB-MP-HAUL-DT5484-STRSYS-STRIA | Steering Idler Arm | 44 | 44 | 6500
500164944 | CLB-MP-HAUL-DT5484-STRSYS-STRCY-STCYR | Steering Cylinder RH | 44 | 44 | 6500
500164943 | CLB-MP-HAUL-DT5484-STRSYS-STRCY-STCYL | Steering Cylinder LH | 44 | 44 | 6500
500164942 | CLB-MP-HAUL-DT5484-STRSYS-STLTR | Steering Linkages & Tie Rods | 44 | 44 | 6500
500164941 | CLB-MP-HAUL-DT5484-STRSYS-STCNT | Steering Control Unit | 44 | 44 | 6500
500164940 | CLB-MP-HAUL-DT5484-STRSYS-STACC-SACRH | Accumulator Steering ODS | 44 | 44 | 6500
500164939 | CLB-MP-HAUL-DT5484-STRSYS-STACC-SACLH | Accumulator Steering DS | 44 | 44 | 6500
500164938 | CLB-MP-HAUL-DT5484-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 44 | 44 | 6500
500164937 | CLB-MP-HAUL-DT5484-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 44 | 44 | 6500
500164936 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 44 | 44 | 6500
500164935 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 44 | 44 | 6500
500164934 | CLB-MP-HAUL-DT5484-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 44 | 44 | 6500
500164933 | CLB-MP-HAUL-DT5484-HYDSYS-HYDOC | Hydraulic Oil Cooler | 44 | 44 | 6500
500164932 | CLB-MP-HAUL-DT5484-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 44 | 44 | 6500
500164931 | CLB-MP-HAUL-DT5484-HYDSYS-HOMAN | Hoist Manifold | 44 | 44 | 6500
500164930 | CLB-MP-HAUL-DT5484-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 44 | 44 | 6500
500164929 | CLB-MP-HAUL-DT5484-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 44 | 44 | 6500
500164928 | CLB-MP-HAUL-DT5484-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 44 | 44 | 6500
500164927 | CLB-MP-HAUL-DT5484-HYDSYS-GROCL | Gear Oil Cooler | 44 | 44 | 6500
500164926 | CLB-MP-HAUL-DT5484-GRSYST-ALBPP | Auto Lube Pump | 44 | 44 | 6500
500164925 | CLB-MP-HAUL-DT5484-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 44 | 44 | 6500
500164924 | CLB-MP-HAUL-DT5484-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 44 | 44 | 6500
500164923 | CLB-MP-HAUL-DT5484-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 44 | 44 | 6500
500164922 | CLB-MP-HAUL-DT5484-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 44 | 44 | 6500
500164921 | CLB-MP-HAUL-DT5484-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 44 | 44 | 6500
500164920 | CLB-MP-HAUL-DT5484-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 44 | 44 | 6500
500164919 | CLB-MP-HAUL-DT5484-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 44 | 44 | 6500
500164918 | CLB-MP-HAUL-DT5484-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 44 | 44 | 6500
500164917 | CLB-MP-HAUL-DT5484-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 44 | 44 | 6500
500164916 | CLB-MP-HAUL-DT5484-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 44 | 44 | 6500
500164915 | CLB-MP-HAUL-DT5484-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 44 | 44 | 6500
500164914 | CLB-MP-HAUL-DT5484-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 44 | 44 | 6500
500164913 | CLB-MP-HAUL-DT5484-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 44 | 44 | 6500
500164912 | CLB-MP-HAUL-DT5484-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 44 | 44 | 6500
500164911 | CLB-MP-HAUL-DT5484-ENGINE-INTEX-TBORF | Turbocharger RH Front | 44 | 44 | 6500
500164910 | CLB-MP-HAUL-DT5484-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 44 | 44 | 6500
500164909 | CLB-MP-HAUL-DT5484-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 44 | 44 | 6500
500164908 | CLB-MP-HAUL-DT5484-ENGINE-INTEX-AFTER | Aftercooler Engine | 44 | 44 | 6500
500164907 | CLB-MP-HAUL-DT5484-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 44 | 44 | 6500
500164906 | CLB-MP-HAUL-DT5484-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 44 | 44 | 6500
500164905 | CLB-MP-HAUL-DT5484-ENGINE-FUSYS-FUINJ | Fuel Injectors | 44 | 44 | 6500
500164904 | CLB-MP-HAUL-DT5484-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 44 | 44 | 6500
500164903 | CLB-MP-HAUL-DT5484-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 44 | 44 | 6500
500164902 | CLB-MP-HAUL-DT5484-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 44 | 44 | 6500
500164901 | CLB-MP-HAUL-DT5484-ENGINE-COSYS-HTWPP | Engine Water Pump | 44 | 44 | 6500
500164900 | CLB-MP-HAUL-DT5484-ENGINE-COSYS-COFAN | Fan Cooling System | 44 | 44 | 6500
500164899 | CLB-MP-HAUL-DT5484-ENGINE | Engine Assembly Cummins QSK60 | 44 | 44 | 6500
500164898 | CLB-MP-HAUL-DT5484-ELCTLV-START-STMUP | Starter Motor Upper | 44 | 44 | 6500
500164897 | CLB-MP-HAUL-DT5484-ELCTLV-START-STMLO | Starter Motor Lower | 44 | 44 | 6500
500164896 | CLB-MP-HAUL-DT5484-ELCTLV-HARNS | Electrical Harness | 44 | 44 | 6500
500164895 | CLB-MP-HAUL-DT5484-ELCTLV-CHARG-BATTY | Batteries | 44 | 44 | 6500
500164894 | CLB-MP-HAUL-DT5484-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 44 | 44 | 6500
500164893 | CLB-MP-HAUL-DT5484-ELCTHV-HVGBX-HVRES | Grid Resistors | 44 | 44 | 6500
500164892 | CLB-MP-HAUL-DT5484-ELCTHV-HVGBM | Grid Box Blower Motor | 44 | 44 | 6500
500164891 | CLB-MP-HAUL-DT5484-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 44 | 44 | 6500
500164890 | CLB-MP-HAUL-DT5484-ELCTHV-HVBLW | Main High Voltage Blower | 44 | 44 | 6500
500164889 | CLB-MP-HAUL-DT5484-ELCTHV-HVALT | High Voltage Alternator | 44 | 44 | 6500
500164888 | CLB-MP-HAUL-DT5484-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 44 | 44 | 6500
500164887 | CLB-MP-HAUL-DT5484-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 44 | 44 | 6500
500164886 | CLB-MP-HAUL-DT5484-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 44 | 44 | 6500
500164885 | CLB-MP-HAUL-DT5484-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 44 | 44 | 6500
500164884 | CLB-MP-HAUL-DT5484-BRKSYS-BRVTR | Brake Treadle Valve | 44 | 44 | 6500
500164883 | CLB-MP-HAUL-DT5484-BRKSYS-BRVRL | Brake Dual Relay Valves | 44 | 44 | 6500
500164882 | CLB-MP-HAUL-DT5484-BRKSYS-BRVLV | Brake & Steering Manifold | 44 | 44 | 6500
500164881 | CLB-MP-HAUL-DT5484-BRKSYS-BRSTV | Brake & Steering Valve | 44 | 44 | 6500
500164880 | CLB-MP-HAUL-DT5484-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 44 | 44 | 6500
500164879 | CLB-MP-HAUL-DT5484-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 44 | 44 | 6500
500164878 | CLB-MP-HAUL-DT5484-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 44 | 44 | 6500
500164877 | CLB-MP-HAUL-DT5484-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 44 | 44 | 6500
500164876 | CLB-MP-HAUL-DT5484-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 44 | 44 | 6500
500164875 | CLB-MP-HAUL-DT5484-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 44 | 44 | 6500
500164874 | CLB-MP-HAUL-DT5484-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 44 | 44 | 6500
500164873 | CLB-MP-HAUL-DT5484 | DT5484 Liebherr T264 OHT | 44 | 44 | 6500
500162179 | CLB-MP-HAUL-DT5483-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 449 | 449 | 6500
500162178 | CLB-MP-HAUL-DT5483-STRUCT-TRAYS | Tray | 449 | 449 | 6500
500162177 | CLB-MP-HAUL-DT5483-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 449 | 449 | 6500
500162176 | CLB-MP-HAUL-DT5483-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 449 | 449 | 6500
500162175 | CLB-MP-HAUL-DT5483-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 449 | 449 | 6500
500162174 | CLB-MP-HAUL-DT5483-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 449 | 449 | 6500
500162173 | CLB-MP-HAUL-DT5483-STRUCT-CABIN-SEATS | Operators Seat | 449 | 449 | 6500
500162172 | CLB-MP-HAUL-DT5483-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 449 | 449 | 6500
500162171 | CLB-MP-HAUL-DT5483-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 449 | 449 | 6500
500162170 | CLB-MP-HAUL-DT5483-STRUCT-CABIN | Operators Cabin | 449 | 449 | 6500
500162169 | CLB-MP-HAUL-DT5483-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 449 | 449 | 6500
500162168 | CLB-MP-HAUL-DT5483-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 449 | 449 | 6500
500162167 | CLB-MP-HAUL-DT5483-STRSYS-STVLV | Valve Flow Amplifier | 449 | 449 | 6500
500162166 | CLB-MP-HAUL-DT5483-STRSYS-STRIA | Steering Idler Arm | 449 | 449 | 6500
500162165 | CLB-MP-HAUL-DT5483-STRSYS-STRCY-STCYR | Steering Cylinder RH | 449 | 449 | 6500
500162164 | CLB-MP-HAUL-DT5483-STRSYS-STRCY-STCYL | Steering Cylinder LH | 449 | 449 | 6500
500162163 | CLB-MP-HAUL-DT5483-STRSYS-STLTR | Steering Linkages & Tie Rods | 449 | 449 | 6500
500162162 | CLB-MP-HAUL-DT5483-STRSYS-STCNT | Steering Control Unit | 449 | 449 | 6500
500162161 | CLB-MP-HAUL-DT5483-STRSYS-STACC-SACRH | Accumulator Steering ODS | 449 | 449 | 6500
500162160 | CLB-MP-HAUL-DT5483-STRSYS-STACC-SACLH | Accumulator Steering DS | 449 | 449 | 6500
500162159 | CLB-MP-HAUL-DT5483-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 449 | 449 | 6500
500162158 | CLB-MP-HAUL-DT5483-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 449 | 449 | 6500
500162157 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 449 | 449 | 6500
500162156 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 449 | 449 | 6500
500162155 | CLB-MP-HAUL-DT5483-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 449 | 449 | 6500
500162154 | CLB-MP-HAUL-DT5483-HYDSYS-HYDOC | Hydraulic Oil Cooler | 449 | 449 | 6500
500162153 | CLB-MP-HAUL-DT5483-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 449 | 449 | 6500
500162152 | CLB-MP-HAUL-DT5483-HYDSYS-HOMAN | Hoist Manifold | 449 | 449 | 6500
500162151 | CLB-MP-HAUL-DT5483-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 449 | 449 | 6500
500162150 | CLB-MP-HAUL-DT5483-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 449 | 449 | 6500
500162149 | CLB-MP-HAUL-DT5483-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 449 | 449 | 6500
500162148 | CLB-MP-HAUL-DT5483-HYDSYS-GROCL | Gear Oil Cooler | 449 | 449 | 6500
500162147 | CLB-MP-HAUL-DT5483-GRSYST-ALBPP | Auto Lube Pump | 449 | 449 | 6500
500162146 | CLB-MP-HAUL-DT5483-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 449 | 449 | 6500
500162145 | CLB-MP-HAUL-DT5483-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 449 | 449 | 6500
500162144 | CLB-MP-HAUL-DT5483-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 449 | 449 | 6500
500162143 | CLB-MP-HAUL-DT5483-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 449 | 449 | 6500
500162142 | CLB-MP-HAUL-DT5483-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 449 | 449 | 6500
500162141 | CLB-MP-HAUL-DT5483-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 449 | 449 | 6500
500162140 | CLB-MP-HAUL-DT5483-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 449 | 449 | 6500
500162139 | CLB-MP-HAUL-DT5483-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 449 | 449 | 6500
500162138 | CLB-MP-HAUL-DT5483-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 449 | 449 | 6500
500162137 | CLB-MP-HAUL-DT5483-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 449 | 449 | 6500
500162136 | CLB-MP-HAUL-DT5483-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 449 | 449 | 6500
500162135 | CLB-MP-HAUL-DT5483-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 449 | 449 | 6500
500162134 | CLB-MP-HAUL-DT5483-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 449 | 449 | 6500
500162133 | CLB-MP-HAUL-DT5483-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 449 | 449 | 6500
500162132 | CLB-MP-HAUL-DT5483-ENGINE-INTEX-TBORF | Turbocharger RH Front | 449 | 449 | 6500
500162131 | CLB-MP-HAUL-DT5483-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 449 | 449 | 6500
500162130 | CLB-MP-HAUL-DT5483-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 449 | 449 | 6500
500162129 | CLB-MP-HAUL-DT5483-ENGINE-INTEX-AFTER | Aftercooler Engine | 449 | 449 | 6500
500162128 | CLB-MP-HAUL-DT5483-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 449 | 449 | 6500
500162127 | CLB-MP-HAUL-DT5483-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 449 | 449 | 6500
500162126 | CLB-MP-HAUL-DT5483-ENGINE-FUSYS-FUINJ | Fuel Injectors | 449 | 449 | 6500
500162125 | CLB-MP-HAUL-DT5483-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 449 | 449 | 6500
500162124 | CLB-MP-HAUL-DT5483-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 449 | 449 | 6500
500162123 | CLB-MP-HAUL-DT5483-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 449 | 449 | 6500
500162122 | CLB-MP-HAUL-DT5483-ENGINE-COSYS-HTWPP | Engine Water Pump | 449 | 449 | 6500
500162121 | CLB-MP-HAUL-DT5483-ENGINE-COSYS-COFAN | Fan Cooling System | 449 | 449 | 6500
500162120 | CLB-MP-HAUL-DT5483-ENGINE | Engine Assembly Cummins QSK60 | 449 | 449 | 6500
500162119 | CLB-MP-HAUL-DT5483-ELCTLV-START-STMUP | Starter Motor Upper | 449 | 449 | 6500
500162118 | CLB-MP-HAUL-DT5483-ELCTLV-START-STMLO | Starter Motor Lower | 449 | 449 | 6500
500162117 | CLB-MP-HAUL-DT5483-ELCTLV-HARNS | Electrical Harness | 449 | 449 | 6500
500162116 | CLB-MP-HAUL-DT5483-ELCTLV-CHARG-BATTY | Batteries | 449 | 449 | 6500
500162115 | CLB-MP-HAUL-DT5483-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 449 | 449 | 6500
500162114 | CLB-MP-HAUL-DT5483-ELCTHV-HVGBX-HVRES | Grid Resistors | 449 | 449 | 6500
500162113 | CLB-MP-HAUL-DT5483-ELCTHV-HVGBM | Grid Box Blower Motor | 449 | 449 | 6500
500162112 | CLB-MP-HAUL-DT5483-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 449 | 449 | 6500
500162111 | CLB-MP-HAUL-DT5483-ELCTHV-HVBLW | Main High Voltage Blower | 449 | 449 | 6500
500162110 | CLB-MP-HAUL-DT5483-ELCTHV-HVALT | High Voltage Alternator | 449 | 449 | 6500
500162109 | CLB-MP-HAUL-DT5483-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 449 | 449 | 6500
500162108 | CLB-MP-HAUL-DT5483-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 449 | 449 | 6500
500162107 | CLB-MP-HAUL-DT5483-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 449 | 449 | 6500
500162106 | CLB-MP-HAUL-DT5483-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 449 | 449 | 6500
500162105 | CLB-MP-HAUL-DT5483-BRKSYS-BRVTR | Brake Treadle Valve | 449 | 449 | 6500
500162104 | CLB-MP-HAUL-DT5483-BRKSYS-BRVRL | Brake Dual Relay Valves | 449 | 449 | 6500
500162103 | CLB-MP-HAUL-DT5483-BRKSYS-BRVLV | Brake & Steering Manifold | 449 | 449 | 6500
500162092 | CLB-MP-HAUL-DT5483-BRKSYS-BRSTV | Brake & Steering Valve | 449 | 449 | 6500
500162091 | CLB-MP-HAUL-DT5483-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 449 | 449 | 6500
500162090 | CLB-MP-HAUL-DT5483-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 449 | 449 | 6500
500162089 | CLB-MP-HAUL-DT5483-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 449 | 449 | 6500
500162088 | CLB-MP-HAUL-DT5483-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 449 | 449 | 6500
500162087 | CLB-MP-HAUL-DT5483-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 449 | 449 | 6500
500162086 | CLB-MP-HAUL-DT5483-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 449 | 449 | 6500
500162085 | CLB-MP-HAUL-DT5483-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 449 | 449 | 6500
500162084 | CLB-MP-HAUL-DT5483 | DT5483 Liebherr T264 OHT | 449 | 449 | 6500
500160439 | CLB-MP-HAUL-DT5482-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500160438 | CLB-MP-HAUL-DT5482-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500160437 | CLB-MP-HAUL-DT5482-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500160436 | CLB-MP-HAUL-DT5482-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500160435 | CLB-MP-HAUL-DT5482-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500160434 | CLB-MP-HAUL-DT5482-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500160433 | CLB-MP-HAUL-DT5482-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500160432 | CLB-MP-HAUL-DT5482-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500160431 | CLB-MP-HAUL-DT5482-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500160430 | CLB-MP-HAUL-DT5482-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500160429 | CLB-MP-HAUL-DT5482-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500160428 | CLB-MP-HAUL-DT5482-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500160427 | CLB-MP-HAUL-DT5482-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500160426 | CLB-MP-HAUL-DT5482-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500160425 | CLB-MP-HAUL-DT5482-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500160424 | CLB-MP-HAUL-DT5482-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500160423 | CLB-MP-HAUL-DT5482-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500160422 | CLB-MP-HAUL-DT5482-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500160421 | CLB-MP-HAUL-DT5482-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500160420 | CLB-MP-HAUL-DT5482-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500160419 | CLB-MP-HAUL-DT5482-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500160418 | CLB-MP-HAUL-DT5482-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500160417 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500160416 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500160415 | CLB-MP-HAUL-DT5482-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500160414 | CLB-MP-HAUL-DT5482-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500160413 | CLB-MP-HAUL-DT5482-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500160412 | CLB-MP-HAUL-DT5482-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500160411 | CLB-MP-HAUL-DT5482-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500160410 | CLB-MP-HAUL-DT5482-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500160409 | CLB-MP-HAUL-DT5482-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500160408 | CLB-MP-HAUL-DT5482-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500160407 | CLB-MP-HAUL-DT5482-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500160406 | CLB-MP-HAUL-DT5482-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500160405 | CLB-MP-HAUL-DT5482-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500160404 | CLB-MP-HAUL-DT5482-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500160403 | CLB-MP-HAUL-DT5482-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500160402 | CLB-MP-HAUL-DT5482-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500160401 | CLB-MP-HAUL-DT5482-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500160400 | CLB-MP-HAUL-DT5482-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500160399 | CLB-MP-HAUL-DT5482-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500160398 | CLB-MP-HAUL-DT5482-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500160397 | CLB-MP-HAUL-DT5482-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500160396 | CLB-MP-HAUL-DT5482-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500160395 | CLB-MP-HAUL-DT5482-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500160394 | CLB-MP-HAUL-DT5482-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500160393 | CLB-MP-HAUL-DT5482-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500160392 | CLB-MP-HAUL-DT5482-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500160391 | CLB-MP-HAUL-DT5482-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500160390 | CLB-MP-HAUL-DT5482-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500160389 | CLB-MP-HAUL-DT5482-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500160388 | CLB-MP-HAUL-DT5482-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500160387 | CLB-MP-HAUL-DT5482-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500160386 | CLB-MP-HAUL-DT5482-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500160385 | CLB-MP-HAUL-DT5482-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500160384 | CLB-MP-HAUL-DT5482-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500160383 | CLB-MP-HAUL-DT5482-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500160382 | CLB-MP-HAUL-DT5482-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500160381 | CLB-MP-HAUL-DT5482-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500160380 | CLB-MP-HAUL-DT5482-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500160379 | CLB-MP-HAUL-DT5482-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500160378 | CLB-MP-HAUL-DT5482-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500160377 | CLB-MP-HAUL-DT5482-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500160376 | CLB-MP-HAUL-DT5482-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500160375 | CLB-MP-HAUL-DT5482-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500160374 | CLB-MP-HAUL-DT5482-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500160373 | CLB-MP-HAUL-DT5482-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500160372 | CLB-MP-HAUL-DT5482-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500160371 | CLB-MP-HAUL-DT5482-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500160370 | CLB-MP-HAUL-DT5482-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500160369 | CLB-MP-HAUL-DT5482-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500160368 | CLB-MP-HAUL-DT5482-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500160367 | CLB-MP-HAUL-DT5482-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500160366 | CLB-MP-HAUL-DT5482-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500160365 | CLB-MP-HAUL-DT5482-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500160364 | CLB-MP-HAUL-DT5482-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500160363 | CLB-MP-HAUL-DT5482-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500160352 | CLB-MP-HAUL-DT5482-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500160351 | CLB-MP-HAUL-DT5482-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500160350 | CLB-MP-HAUL-DT5482-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500160349 | CLB-MP-HAUL-DT5482-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500160348 | CLB-MP-HAUL-DT5482-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500160347 | CLB-MP-HAUL-DT5482-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500160346 | CLB-MP-HAUL-DT5482-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500160345 | CLB-MP-HAUL-DT5482-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500160344 | CLB-MP-HAUL-DT5482 | DT5482 Liebherr T264 OHT | 1 | 1 | 6500
500164806 | CLB-MP-HAUL-DT5481-STRSYS-STACC-SACRH | Accumulator Steering ODS | 46 | 46 | 6500
500164805 | CLB-MP-HAUL-DT5481-STRSYS-STACC-SACLH | Accumulator Steering DS | 46 | 46 | 6500
500164804 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 46 | 46 | 6500
500164803 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 46 | 46 | 6500
500164802 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 46 | 46 | 6500
500164801 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 46 | 46 | 6500
500160179 | CLB-MP-HAUL-DT5481-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 46 | 46 | 6500
500160178 | CLB-MP-HAUL-DT5481-STRUCT-TRAYS | Tray | 46 | 46 | 6500
500160177 | CLB-MP-HAUL-DT5481-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 46 | 46 | 6500
500160176 | CLB-MP-HAUL-DT5481-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 46 | 46 | 6500
500160175 | CLB-MP-HAUL-DT5481-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 46 | 46 | 6500
500160174 | CLB-MP-HAUL-DT5481-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 46 | 46 | 6500
500160173 | CLB-MP-HAUL-DT5481-STRUCT-CABIN-SEATS | Operators Seat | 46 | 46 | 6500
500160172 | CLB-MP-HAUL-DT5481-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 46 | 46 | 6500
500160171 | CLB-MP-HAUL-DT5481-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 46 | 46 | 6500
500160170 | CLB-MP-HAUL-DT5481-STRUCT-CABIN | Operators Cabin | 46 | 46 | 6500
500160169 | CLB-MP-HAUL-DT5481-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 46 | 46 | 6500
500160168 | CLB-MP-HAUL-DT5481-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 46 | 46 | 6500
500160167 | CLB-MP-HAUL-DT5481-STRSYS-STVLV | Valve Flow Amplifier | 46 | 46 | 6500
500160166 | CLB-MP-HAUL-DT5481-STRSYS-STRIA | Steering Idler Arm | 46 | 46 | 6500
500160165 | CLB-MP-HAUL-DT5481-STRSYS-STRCY-STCYR | Steering Cylinder RH | 46 | 46 | 6500
500160164 | CLB-MP-HAUL-DT5481-STRSYS-STRCY-STCYL | Steering Cylinder LH | 46 | 46 | 6500
500160163 | CLB-MP-HAUL-DT5481-STRSYS-STLTR | Steering Linkages & Tie Rods | 46 | 46 | 6500
500160162 | CLB-MP-HAUL-DT5481-STRSYS-STCNT | Steering Control Unit | 46 | 46 | 6500
500160161 | CLB-MP-HAUL-DT5481-STRSYS-STACC | Accumulator Steering RHS | 46 | 46 | 6500
500160160 | CLB-MP-HAUL-DT5481-STRSYS-STACC | Accumulator Steering LHS | 46 | 46 | 6500
500160159 | CLB-MP-HAUL-DT5481-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 46 | 46 | 6500
500160158 | CLB-MP-HAUL-DT5481-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 46 | 46 | 6500
500160157 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 46 | 46 | 6500
500160156 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 46 | 46 | 6500
500160155 | CLB-MP-HAUL-DT5481-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 46 | 46 | 6500
500160154 | CLB-MP-HAUL-DT5481-HYDSYS-HYDOC | Hydraulic Oil Cooler | 46 | 46 | 6500
500160153 | CLB-MP-HAUL-DT5481-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 46 | 46 | 6500
500160152 | CLB-MP-HAUL-DT5481-HYDSYS-HOMAN | Hoist Manifold | 46 | 46 | 6500
500160151 | CLB-MP-HAUL-DT5481-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 46 | 46 | 6500
500160150 | CLB-MP-HAUL-DT5481-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 46 | 46 | 6500
500160149 | CLB-MP-HAUL-DT5481-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 46 | 46 | 6500
500160148 | CLB-MP-HAUL-DT5481-HYDSYS-GROCL | Gear Oil Cooler | 46 | 46 | 6500
500160147 | CLB-MP-HAUL-DT5481-GRSYST-ALBPP | Auto Lube Pump | 46 | 46 | 6500
500160146 | CLB-MP-HAUL-DT5481-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 46 | 46 | 6500
500160145 | CLB-MP-HAUL-DT5481-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 46 | 46 | 6500
500160144 | CLB-MP-HAUL-DT5481-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 46 | 46 | 6500
500160143 | CLB-MP-HAUL-DT5481-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 46 | 46 | 6500
500160142 | CLB-MP-HAUL-DT5481-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 46 | 46 | 6500
500160141 | CLB-MP-HAUL-DT5481-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 46 | 46 | 6500
500160140 | CLB-MP-HAUL-DT5481-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 46 | 46 | 6500
500160139 | CLB-MP-HAUL-DT5481-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 46 | 46 | 6500
500160138 | CLB-MP-HAUL-DT5481-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 46 | 46 | 6500
500160137 | CLB-MP-HAUL-DT5481-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 46 | 46 | 6500
500160136 | CLB-MP-HAUL-DT5481-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 46 | 46 | 6500
500160135 | CLB-MP-HAUL-DT5481-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 46 | 46 | 6500
500160134 | CLB-MP-HAUL-DT5481-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 46 | 46 | 6500
500160133 | CLB-MP-HAUL-DT5481-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 46 | 46 | 6500
500160132 | CLB-MP-HAUL-DT5481-ENGINE-INTEX-TBORF | Turbocharger RH Front | 46 | 46 | 6500
500160131 | CLB-MP-HAUL-DT5481-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 46 | 46 | 6500
500160130 | CLB-MP-HAUL-DT5481-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 46 | 46 | 6500
500160129 | CLB-MP-HAUL-DT5481-ENGINE-INTEX-AFTER | Aftercooler Engine | 46 | 46 | 6500
500160128 | CLB-MP-HAUL-DT5481-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 46 | 46 | 6500
500160127 | CLB-MP-HAUL-DT5481-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 46 | 46 | 6500
500160126 | CLB-MP-HAUL-DT5481-ENGINE-FUSYS-FUINJ | Fuel Injectors | 46 | 46 | 6500
500160125 | CLB-MP-HAUL-DT5481-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 46 | 46 | 6500
500160124 | CLB-MP-HAUL-DT5481-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 46 | 46 | 6500
500160123 | CLB-MP-HAUL-DT5481-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 46 | 46 | 6500
500160122 | CLB-MP-HAUL-DT5481-ENGINE-COSYS-HTWPP | Engine Water Pump | 46 | 46 | 6500
500160121 | CLB-MP-HAUL-DT5481-ENGINE-COSYS-COFAN | Fan Cooling System | 46 | 46 | 6500
500160120 | CLB-MP-HAUL-DT5481-ENGINE | Engine Assembly Cummins QSK60 | 46 | 46 | 6500
500160119 | CLB-MP-HAUL-DT5481-ELCTLV-START-STMUP | Starter Motor Upper | 46 | 46 | 6500
500160118 | CLB-MP-HAUL-DT5481-ELCTLV-START-STMLO | Starter Motor Lower | 46 | 46 | 6500
500160117 | CLB-MP-HAUL-DT5481-ELCTLV-HARNS | Electrical Harness | 46 | 46 | 6500
500160116 | CLB-MP-HAUL-DT5481-ELCTLV-CHARG-BATTY | Batteries | 46 | 46 | 6500
500160115 | CLB-MP-HAUL-DT5481-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 46 | 46 | 6500
500160114 | CLB-MP-HAUL-DT5481-ELCTHV-HVGBX-HVRES | Grid Resistors | 46 | 46 | 6500
500160113 | CLB-MP-HAUL-DT5481-ELCTHV-HVGBM | Grid Box Blower Motor | 46 | 46 | 6500
500160112 | CLB-MP-HAUL-DT5481-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 46 | 46 | 6500
500160111 | CLB-MP-HAUL-DT5481-ELCTHV-HVBLW | Main High Voltage Blower | 46 | 46 | 6500
500160110 | CLB-MP-HAUL-DT5481-ELCTHV-HVALT | High Voltage Alternator | 46 | 46 | 6500
500160109 | CLB-MP-HAUL-DT5481-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 46 | 46 | 6500
500160108 | CLB-MP-HAUL-DT5481-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 46 | 46 | 6500
500160107 | CLB-MP-HAUL-DT5481-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 46 | 46 | 6500
500160106 | CLB-MP-HAUL-DT5481-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 46 | 46 | 6500
500160105 | CLB-MP-HAUL-DT5481-BRKSYS-BRVTR | Brake Treadle Valve | 46 | 46 | 6500
500160104 | CLB-MP-HAUL-DT5481-BRKSYS-BRVRL | Brake Dual Relay Valves | 46 | 46 | 6500
500160103 | CLB-MP-HAUL-DT5481-BRKSYS-BRVLV | Brake & Steering Manifold | 46 | 46 | 6500
500159982 | CLB-MP-HAUL-DT5481-BRKSYS-BRSTV | Brake & Steering Valve | 46 | 46 | 6500
500159981 | CLB-MP-HAUL-DT5481-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 46 | 46 | 6500
500159980 | CLB-MP-HAUL-DT5481-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 46 | 46 | 6500
500159979 | CLB-MP-HAUL-DT5481-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 46 | 46 | 6500
500159978 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC | Accumulator Brake Supply Rr | 46 | 46 | 6500
500159977 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 46 | 46 | 6500
500159976 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC | Accumulator Brake Supply Fr | 46 | 46 | 6500
500159975 | CLB-MP-HAUL-DT5481-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 46 | 46 | 6500
500159974 | CLB-MP-HAUL-DT5481 | DT5481 Liebherr T264 OHT | 46 | 46 | 6500
500164800 | CLB-MP-HAUL-DT5480-STRSYS-STACC-SACRH | Accumulator Steering ODS | 2 | 2 | 6500
500164799 | CLB-MP-HAUL-DT5480-STRSYS-STACC-SACLH | Accumulator Steering DS | 2 | 2 | 6500
500164798 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 2 | 2 | 6500
500164797 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 2 | 2 | 6500
500164796 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 2 | 2 | 6500
500164795 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 2 | 2 | 6500
500160091 | CLB-MP-HAUL-DT5480-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 2 | 2 | 6500
500160090 | CLB-MP-HAUL-DT5480-STRUCT-TRAYS | Tray | 2 | 2 | 6500
500160089 | CLB-MP-HAUL-DT5480-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 2 | 2 | 6500
500160088 | CLB-MP-HAUL-DT5480-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 2 | 2 | 6500
500160087 | CLB-MP-HAUL-DT5480-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 2 | 2 | 6500
500160086 | CLB-MP-HAUL-DT5480-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 2 | 2 | 6500
500160085 | CLB-MP-HAUL-DT5480-STRUCT-CABIN-SEATS | Operators Seat | 2 | 2 | 6500
500160084 | CLB-MP-HAUL-DT5480-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 2 | 2 | 6500
500160083 | CLB-MP-HAUL-DT5480-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 2 | 2 | 6500
500160082 | CLB-MP-HAUL-DT5480-STRUCT-CABIN | Operators Cabin | 2 | 2 | 6500
500160081 | CLB-MP-HAUL-DT5480-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 2 | 2 | 6500
500160080 | CLB-MP-HAUL-DT5480-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 2 | 2 | 6500
500160079 | CLB-MP-HAUL-DT5480-STRSYS-STVLV | Valve Flow Amplifier | 2 | 2 | 6500
500160078 | CLB-MP-HAUL-DT5480-STRSYS-STRIA | Steering Idler Arm | 2 | 2 | 6500
500160077 | CLB-MP-HAUL-DT5480-STRSYS-STRCY-STCYR | Steering Cylinder RH | 2 | 2 | 6500
500160076 | CLB-MP-HAUL-DT5480-STRSYS-STRCY-STCYL | Steering Cylinder LH | 2 | 2 | 6500
500160075 | CLB-MP-HAUL-DT5480-STRSYS-STLTR | Steering Linkages & Tie Rods | 2 | 2 | 6500
500160074 | CLB-MP-HAUL-DT5480-STRSYS-STCNT | Steering Control Unit | 2 | 2 | 6500
500160073 | CLB-MP-HAUL-DT5480-STRSYS-STACC | Accumulator Steering RHS | 2 | 2 | 6500
500160072 | CLB-MP-HAUL-DT5480-STRSYS-STACC | Accumulator Steering LHS | 2 | 2 | 6500
500160071 | CLB-MP-HAUL-DT5480-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 2 | 2 | 6500
500160070 | CLB-MP-HAUL-DT5480-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 2 | 2 | 6500
500160069 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 2 | 2 | 6500
500160068 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 2 | 2 | 6500
500160067 | CLB-MP-HAUL-DT5480-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 2 | 2 | 6500
500160066 | CLB-MP-HAUL-DT5480-HYDSYS-HYDOC | Hydraulic Oil Cooler | 2 | 2 | 6500
500160065 | CLB-MP-HAUL-DT5480-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 2 | 2 | 6500
500160064 | CLB-MP-HAUL-DT5480-HYDSYS-HOMAN | Hoist Manifold | 2 | 2 | 6500
500160063 | CLB-MP-HAUL-DT5480-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 2 | 2 | 6500
500160062 | CLB-MP-HAUL-DT5480-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 2 | 2 | 6500
500160061 | CLB-MP-HAUL-DT5480-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 2 | 2 | 6500
500160060 | CLB-MP-HAUL-DT5480-HYDSYS-GROCL | Gear Oil Cooler | 2 | 2 | 6500
500160059 | CLB-MP-HAUL-DT5480-GRSYST-ALBPP | Auto Lube Pump | 2 | 2 | 6500
500160058 | CLB-MP-HAUL-DT5480-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 2 | 2 | 6500
500160057 | CLB-MP-HAUL-DT5480-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 2 | 2 | 6500
500160056 | CLB-MP-HAUL-DT5480-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 2 | 2 | 6500
500160055 | CLB-MP-HAUL-DT5480-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 2 | 2 | 6500
500160054 | CLB-MP-HAUL-DT5480-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 2 | 2 | 6500
500160053 | CLB-MP-HAUL-DT5480-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 2 | 2 | 6500
500160052 | CLB-MP-HAUL-DT5480-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 2 | 2 | 6500
500160051 | CLB-MP-HAUL-DT5480-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 2 | 2 | 6500
500160050 | CLB-MP-HAUL-DT5480-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 2 | 2 | 6500
500160049 | CLB-MP-HAUL-DT5480-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 2 | 2 | 6500
500160048 | CLB-MP-HAUL-DT5480-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 2 | 2 | 6500
500160047 | CLB-MP-HAUL-DT5480-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 2 | 2 | 6500
500160046 | CLB-MP-HAUL-DT5480-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 2 | 2 | 6500
500160045 | CLB-MP-HAUL-DT5480-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 2 | 2 | 6500
500160044 | CLB-MP-HAUL-DT5480-ENGINE-INTEX-TBORF | Turbocharger RH Front | 2 | 2 | 6500
500160043 | CLB-MP-HAUL-DT5480-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 2 | 2 | 6500
500160042 | CLB-MP-HAUL-DT5480-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 2 | 2 | 6500
500160041 | CLB-MP-HAUL-DT5480-ENGINE-INTEX-AFTER | Aftercooler Engine | 2 | 2 | 6500
500160040 | CLB-MP-HAUL-DT5480-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 2 | 2 | 6500
500160039 | CLB-MP-HAUL-DT5480-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 2 | 2 | 6500
500160038 | CLB-MP-HAUL-DT5480-ENGINE-FUSYS-FUINJ | Fuel Injectors | 2 | 2 | 6500
500160037 | CLB-MP-HAUL-DT5480-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 2 | 2 | 6500
500160036 | CLB-MP-HAUL-DT5480-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 2 | 2 | 6500
500160035 | CLB-MP-HAUL-DT5480-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 2 | 2 | 6500
500160034 | CLB-MP-HAUL-DT5480-ENGINE-COSYS-HTWPP | Engine Water Pump | 2 | 2 | 6500
500160033 | CLB-MP-HAUL-DT5480-ENGINE-COSYS-COFAN | Fan Cooling System | 2 | 2 | 6500
500160032 | CLB-MP-HAUL-DT5480-ENGINE | Engine Assembly Cummins QSK60 | 2 | 2 | 6500
500160031 | CLB-MP-HAUL-DT5480-ELCTLV-START-STMUP | Starter Motor Upper | 2 | 2 | 6500
500160030 | CLB-MP-HAUL-DT5480-ELCTLV-START-STMLO | Starter Motor Lower | 2 | 2 | 6500
500160029 | CLB-MP-HAUL-DT5480-ELCTLV-HARNS | Electrical Harness | 2 | 2 | 6500
500160028 | CLB-MP-HAUL-DT5480-ELCTLV-CHARG-BATTY | Batteries | 2 | 2 | 6500
500160027 | CLB-MP-HAUL-DT5480-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 2 | 2 | 6500
500160026 | CLB-MP-HAUL-DT5480-ELCTHV-HVGBX-HVRES | Grid Resistors | 2 | 2 | 6500
500160025 | CLB-MP-HAUL-DT5480-ELCTHV-HVGBM | Grid Box Blower Motor | 2 | 2 | 6500
500160024 | CLB-MP-HAUL-DT5480-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 2 | 2 | 6500
500160023 | CLB-MP-HAUL-DT5480-ELCTHV-HVBLW | Main High Voltage Blower | 2 | 2 | 6500
500160022 | CLB-MP-HAUL-DT5480-ELCTHV-HVALT | High Voltage Alternator | 2 | 2 | 6500
500160021 | CLB-MP-HAUL-DT5480-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 2 | 2 | 6500
500160020 | CLB-MP-HAUL-DT5480-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 2 | 2 | 6500
500160019 | CLB-MP-HAUL-DT5480-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 2 | 2 | 6500
500160018 | CLB-MP-HAUL-DT5480-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 2 | 2 | 6500
500160017 | CLB-MP-HAUL-DT5480-BRKSYS-BRVTR | Brake Treadle Valve | 2 | 2 | 6500
500160016 | CLB-MP-HAUL-DT5480-BRKSYS-BRVRL | Brake Dual Relay Valves | 2 | 2 | 6500
500160015 | CLB-MP-HAUL-DT5480-BRKSYS-BRVLV | Brake & Steering Manifold | 2 | 2 | 6500
500160014 | CLB-MP-HAUL-DT5480-BRKSYS-BRSTV | Brake & Steering Valve | 2 | 2 | 6500
500160013 | CLB-MP-HAUL-DT5480-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 2 | 2 | 6500
500159992 | CLB-MP-HAUL-DT5480-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 2 | 2 | 6500
500159991 | CLB-MP-HAUL-DT5480-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 2 | 2 | 6500
500159990 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC | Accumulator Brake Supply Rr | 2 | 2 | 6500
500159989 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 2 | 2 | 6500
500159988 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC | Accumulator Brake Supply Fr | 2 | 2 | 6500
500159987 | CLB-MP-HAUL-DT5480-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 2 | 2 | 6500
500159986 | CLB-MP-HAUL-DT5480 | DT5480 Liebherr T264 OHT | 2 | 2 | 6500
500164794 | CLB-MP-HAUL-DT5479-STRSYS-STACC-SACRH | Accumulator Steering ODS | 47 | 47 | 6500
500164793 | CLB-MP-HAUL-DT5479-STRSYS-STACC-SACLH | Accumulator Steering DS | 47 | 47 | 6500
500164792 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 47 | 47 | 6500
500164791 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 47 | 47 | 6500
500164790 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 47 | 47 | 6500
500164789 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 47 | 47 | 6500
500159952 | CLB-MP-HAUL-DT5479-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 47 | 47 | 6500
500159951 | CLB-MP-HAUL-DT5479-STRUCT-TRAYS | Tray | 47 | 47 | 6500
500159950 | CLB-MP-HAUL-DT5479-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 47 | 47 | 6500
500159949 | CLB-MP-HAUL-DT5479-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 47 | 47 | 6500
500159948 | CLB-MP-HAUL-DT5479-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 47 | 47 | 6500
500159947 | CLB-MP-HAUL-DT5479-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 47 | 47 | 6500
500159946 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-SEATS | Operators Seat | 47 | 47 | 6500
500159945 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 47 | 47 | 6500
500159944 | CLB-MP-HAUL-DT5479-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 47 | 47 | 6500
500159943 | CLB-MP-HAUL-DT5479-STRUCT-CABIN | Operators Cabin | 47 | 47 | 6500
500159942 | CLB-MP-HAUL-DT5479-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 47 | 47 | 6500
500159941 | CLB-MP-HAUL-DT5479-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 47 | 47 | 6500
500159940 | CLB-MP-HAUL-DT5479-STRSYS-STVLV | Valve Flow Amplifier | 47 | 47 | 6500
500159939 | CLB-MP-HAUL-DT5479-STRSYS-STRIA | Steering Idler Arm | 47 | 47 | 6500
500159938 | CLB-MP-HAUL-DT5479-STRSYS-STRCY-STCYR | Steering Cylinder RH | 47 | 47 | 6500
500159937 | CLB-MP-HAUL-DT5479-STRSYS-STRCY-STCYL | Steering Cylinder LH | 47 | 47 | 6500
500159936 | CLB-MP-HAUL-DT5479-STRSYS-STLTR | Steering Linkages & Tie Rods | 47 | 47 | 6500
500159935 | CLB-MP-HAUL-DT5479-STRSYS-STCNT | Steering Control Unit | 47 | 47 | 6500
500159934 | CLB-MP-HAUL-DT5479-STRSYS-STACC | Accumulator Steering RHS | 47 | 47 | 6500
500159933 | CLB-MP-HAUL-DT5479-STRSYS-STACC | Accumulator Steering LHS | 47 | 47 | 6500
500159932 | CLB-MP-HAUL-DT5479-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 47 | 47 | 6500
500159931 | CLB-MP-HAUL-DT5479-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 47 | 47 | 6500
500159930 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 47 | 47 | 6500
500159929 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 47 | 47 | 6500
500159928 | CLB-MP-HAUL-DT5479-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 47 | 47 | 6500
500159927 | CLB-MP-HAUL-DT5479-HYDSYS-HYDOC | Hydraulic Oil Cooler | 47 | 47 | 6500
500159926 | CLB-MP-HAUL-DT5479-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 47 | 47 | 6500
500159925 | CLB-MP-HAUL-DT5479-HYDSYS-HOMAN | Hoist Manifold | 47 | 47 | 6500
500159924 | CLB-MP-HAUL-DT5479-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 47 | 47 | 6500
500159923 | CLB-MP-HAUL-DT5479-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 47 | 47 | 6500
500159922 | CLB-MP-HAUL-DT5479-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 47 | 47 | 6500
500159921 | CLB-MP-HAUL-DT5479-HYDSYS-GROCL | Gear Oil Cooler | 47 | 47 | 6500
500159920 | CLB-MP-HAUL-DT5479-GRSYST-ALBPP | Auto Lube Pump | 47 | 47 | 6500
500159919 | CLB-MP-HAUL-DT5479-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 47 | 47 | 6500
500159918 | CLB-MP-HAUL-DT5479-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 47 | 47 | 6500
500159917 | CLB-MP-HAUL-DT5479-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 47 | 47 | 6500
500159916 | CLB-MP-HAUL-DT5479-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 47 | 47 | 6500
500159915 | CLB-MP-HAUL-DT5479-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 47 | 47 | 6500
500159914 | CLB-MP-HAUL-DT5479-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 47 | 47 | 6500
500159913 | CLB-MP-HAUL-DT5479-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 47 | 47 | 6500
500159912 | CLB-MP-HAUL-DT5479-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 47 | 47 | 6500
500159911 | CLB-MP-HAUL-DT5479-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 47 | 47 | 6500
500159910 | CLB-MP-HAUL-DT5479-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 47 | 47 | 6500
500159909 | CLB-MP-HAUL-DT5479-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 47 | 47 | 6500
500159908 | CLB-MP-HAUL-DT5479-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 47 | 47 | 6500
500159907 | CLB-MP-HAUL-DT5479-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 47 | 47 | 6500
500159906 | CLB-MP-HAUL-DT5479-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 47 | 47 | 6500
500159905 | CLB-MP-HAUL-DT5479-ENGINE-INTEX-TBORF | Turbocharger RH Front | 47 | 47 | 6500
500159904 | CLB-MP-HAUL-DT5479-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 47 | 47 | 6500
500159903 | CLB-MP-HAUL-DT5479-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 47 | 47 | 6500
500159902 | CLB-MP-HAUL-DT5479-ENGINE-INTEX-AFTER | Aftercooler Engine | 47 | 47 | 6500
500159901 | CLB-MP-HAUL-DT5479-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 47 | 47 | 6500
500159900 | CLB-MP-HAUL-DT5479-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 47 | 47 | 6500
500159899 | CLB-MP-HAUL-DT5479-ENGINE-FUSYS-FUINJ | Fuel Injectors | 47 | 47 | 6500
500159898 | CLB-MP-HAUL-DT5479-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 47 | 47 | 6500
500159897 | CLB-MP-HAUL-DT5479-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 47 | 47 | 6500
500159896 | CLB-MP-HAUL-DT5479-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 47 | 47 | 6500
500159895 | CLB-MP-HAUL-DT5479-ENGINE-COSYS-HTWPP | Engine Water Pump | 47 | 47 | 6500
500159894 | CLB-MP-HAUL-DT5479-ENGINE-COSYS-COFAN | Fan Cooling System | 47 | 47 | 6500
500159893 | CLB-MP-HAUL-DT5479-ENGINE | Engine Assembly Cummins QSK60 | 47 | 47 | 6500
500159892 | CLB-MP-HAUL-DT5479-ELCTLV-START-STMUP | Starter Motor Upper | 47 | 47 | 6500
500159891 | CLB-MP-HAUL-DT5479-ELCTLV-START-STMLO | Starter Motor Lower | 47 | 47 | 6500
500159890 | CLB-MP-HAUL-DT5479-ELCTLV-HARNS | Electrical Harness | 47 | 47 | 6500
500159889 | CLB-MP-HAUL-DT5479-ELCTLV-CHARG-BATTY | Batteries | 47 | 47 | 6500
500159888 | CLB-MP-HAUL-DT5479-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 47 | 47 | 6500
500159887 | CLB-MP-HAUL-DT5479-ELCTHV-HVGBX-HVRES | Grid Resistors | 47 | 47 | 6500
500159886 | CLB-MP-HAUL-DT5479-ELCTHV-HVGBM | Grid Box Blower Motor | 47 | 47 | 6500
500159885 | CLB-MP-HAUL-DT5479-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 47 | 47 | 6500
500159884 | CLB-MP-HAUL-DT5479-ELCTHV-HVBLW | Main High Voltage Blower | 47 | 47 | 6500
500159883 | CLB-MP-HAUL-DT5479-ELCTHV-HVALT | High Voltage Alternator | 47 | 47 | 6500
500159882 | CLB-MP-HAUL-DT5479-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 47 | 47 | 6500
500159881 | CLB-MP-HAUL-DT5479-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 47 | 47 | 6500
500159880 | CLB-MP-HAUL-DT5479-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 47 | 47 | 6500
500159879 | CLB-MP-HAUL-DT5479-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 47 | 47 | 6500
500159878 | CLB-MP-HAUL-DT5479-BRKSYS-BRVTR | Brake Treadle Valve | 47 | 47 | 6500
500159877 | CLB-MP-HAUL-DT5479-BRKSYS-BRVRL | Brake Dual Relay Valves | 47 | 47 | 6500
500159876 | CLB-MP-HAUL-DT5479-BRKSYS-BRVLV | Brake & Steering Manifold | 47 | 47 | 6500
500159875 | CLB-MP-HAUL-DT5479-BRKSYS-BRSTV | Brake & Steering Valve | 47 | 47 | 6500
500159874 | CLB-MP-HAUL-DT5479-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 47 | 47 | 6500
500159873 | CLB-MP-HAUL-DT5479-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 47 | 47 | 6500
500159872 | CLB-MP-HAUL-DT5479-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 47 | 47 | 6500
500159871 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC | Accumulator Brake Supply Rr | 47 | 47 | 6500
500159870 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 47 | 47 | 6500
500159869 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC | Accumulator Brake Supply Fr | 47 | 47 | 6500
500159868 | CLB-MP-HAUL-DT5479-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 47 | 47 | 6500
500159867 | CLB-MP-HAUL-DT5479 | DT5479 Liebherr T264 OHT | 47 | 47 | 6500
500164788 | CLB-MP-HAUL-DT5478-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1 | 1 | 6500
500164787 | CLB-MP-HAUL-DT5478-STRSYS-STACC-SACLH | Accumulator Steering DS | 1 | 1 | 6500
500164786 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1 | 1 | 6500
500164785 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1 | 1 | 6500
500164784 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1 | 1 | 6500
500164783 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1 | 1 | 6500
500159866 | CLB-MP-HAUL-DT5478-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1 | 1 | 6500
500159865 | CLB-MP-HAUL-DT5478-STRUCT-TRAYS | Tray | 1 | 1 | 6500
500159864 | CLB-MP-HAUL-DT5478-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1 | 1 | 6500
500159863 | CLB-MP-HAUL-DT5478-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1 | 1 | 6500
500159862 | CLB-MP-HAUL-DT5478-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1 | 1 | 6500
500159861 | CLB-MP-HAUL-DT5478-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1 | 1 | 6500
500159860 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-SEATS | Operators Seat | 1 | 1 | 6500
500159859 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1 | 1 | 6500
500159858 | CLB-MP-HAUL-DT5478-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1 | 1 | 6500
500159857 | CLB-MP-HAUL-DT5478-STRUCT-CABIN | Operators Cabin | 1 | 1 | 6500
500159856 | CLB-MP-HAUL-DT5478-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1 | 1 | 6500
500159855 | CLB-MP-HAUL-DT5478-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1 | 1 | 6500
500159854 | CLB-MP-HAUL-DT5478-STRSYS-STVLV | Valve Flow Amplifier | 1 | 1 | 6500
500159853 | CLB-MP-HAUL-DT5478-STRSYS-STRIA | Steering Idler Arm | 1 | 1 | 6500
500159852 | CLB-MP-HAUL-DT5478-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1 | 1 | 6500
500159851 | CLB-MP-HAUL-DT5478-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1 | 1 | 6500
500159850 | CLB-MP-HAUL-DT5478-STRSYS-STLTR | Steering Linkages & Tie Rods | 1 | 1 | 6500
500159849 | CLB-MP-HAUL-DT5478-STRSYS-STCNT | Steering Control Unit | 1 | 1 | 6500
500159848 | CLB-MP-HAUL-DT5478-STRSYS-STACC | Accumulator Steering RHS | 1 | 1 | 6500
500159847 | CLB-MP-HAUL-DT5478-STRSYS-STACC | Accumulator Steering LHS | 1 | 1 | 6500
500159846 | CLB-MP-HAUL-DT5478-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1 | 1 | 6500
500159845 | CLB-MP-HAUL-DT5478-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1 | 1 | 6500
500159844 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1 | 1 | 6500
500159843 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1 | 1 | 6500
500159842 | CLB-MP-HAUL-DT5478-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1 | 1 | 6500
500159841 | CLB-MP-HAUL-DT5478-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1 | 1 | 6500
500159840 | CLB-MP-HAUL-DT5478-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1 | 1 | 6500
500159839 | CLB-MP-HAUL-DT5478-HYDSYS-HOMAN | Hoist Manifold | 1 | 1 | 6500
500159838 | CLB-MP-HAUL-DT5478-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1 | 1 | 6500
500159837 | CLB-MP-HAUL-DT5478-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1 | 1 | 6500
500159836 | CLB-MP-HAUL-DT5478-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1 | 1 | 6500
500159835 | CLB-MP-HAUL-DT5478-HYDSYS-GROCL | Gear Oil Cooler | 1 | 1 | 6500
500159834 | CLB-MP-HAUL-DT5478-GRSYST-ALBPP | Auto Lube Pump | 1 | 1 | 6500
500159833 | CLB-MP-HAUL-DT5478-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1 | 1 | 6500
500159832 | CLB-MP-HAUL-DT5478-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1 | 1 | 6500
500159831 | CLB-MP-HAUL-DT5478-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1 | 1 | 6500
500159830 | CLB-MP-HAUL-DT5478-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1 | 1 | 6500
500159829 | CLB-MP-HAUL-DT5478-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1 | 1 | 6500
500159828 | CLB-MP-HAUL-DT5478-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1 | 1 | 6500
500159827 | CLB-MP-HAUL-DT5478-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1 | 1 | 6500
500159826 | CLB-MP-HAUL-DT5478-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1 | 1 | 6500
500159825 | CLB-MP-HAUL-DT5478-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1 | 1 | 6500
500159824 | CLB-MP-HAUL-DT5478-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1 | 1 | 6500
500159823 | CLB-MP-HAUL-DT5478-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1 | 1 | 6500
500159822 | CLB-MP-HAUL-DT5478-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1 | 1 | 6500
500159821 | CLB-MP-HAUL-DT5478-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1 | 1 | 6500
500159820 | CLB-MP-HAUL-DT5478-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1 | 1 | 6500
500159819 | CLB-MP-HAUL-DT5478-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1 | 1 | 6500
500159818 | CLB-MP-HAUL-DT5478-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1 | 1 | 6500
500159817 | CLB-MP-HAUL-DT5478-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1 | 1 | 6500
500159816 | CLB-MP-HAUL-DT5478-ENGINE-INTEX-AFTER | Aftercooler Engine | 1 | 1 | 6500
500159815 | CLB-MP-HAUL-DT5478-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1 | 1 | 6500
500159814 | CLB-MP-HAUL-DT5478-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1 | 1 | 6500
500159813 | CLB-MP-HAUL-DT5478-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1 | 1 | 6500
500159812 | CLB-MP-HAUL-DT5478-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1 | 1 | 6500
500159811 | CLB-MP-HAUL-DT5478-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1 | 1 | 6500
500159810 | CLB-MP-HAUL-DT5478-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1 | 1 | 6500
500159809 | CLB-MP-HAUL-DT5478-ENGINE-COSYS-HTWPP | Engine Water Pump | 1 | 1 | 6500
500159808 | CLB-MP-HAUL-DT5478-ENGINE-COSYS-COFAN | Fan Cooling System | 1 | 1 | 6500
500159807 | CLB-MP-HAUL-DT5478-ENGINE | Engine Assembly Cummins QSK60 | 1 | 1 | 6500
500159806 | CLB-MP-HAUL-DT5478-ELCTLV-START-STMUP | Starter Motor Upper | 1 | 1 | 6500
500159805 | CLB-MP-HAUL-DT5478-ELCTLV-START-STMLO | Starter Motor Lower | 1 | 1 | 6500
500159804 | CLB-MP-HAUL-DT5478-ELCTLV-HARNS | Electrical Harness | 1 | 1 | 6500
500159803 | CLB-MP-HAUL-DT5478-ELCTLV-CHARG-BATTY | Batteries | 1 | 1 | 6500
500159802 | CLB-MP-HAUL-DT5478-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1 | 1 | 6500
500159801 | CLB-MP-HAUL-DT5478-ELCTHV-HVGBX-HVRES | Grid Resistors | 1 | 1 | 6500
500159800 | CLB-MP-HAUL-DT5478-ELCTHV-HVGBM | Grid Box Blower Motor | 1 | 1 | 6500
500159799 | CLB-MP-HAUL-DT5478-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1 | 1 | 6500
500159798 | CLB-MP-HAUL-DT5478-ELCTHV-HVBLW | Main High Voltage Blower | 1 | 1 | 6500
500159797 | CLB-MP-HAUL-DT5478-ELCTHV-HVALT | High Voltage Alternator | 1 | 1 | 6500
500159796 | CLB-MP-HAUL-DT5478-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1 | 1 | 6500
500159795 | CLB-MP-HAUL-DT5478-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1 | 1 | 6500
500159794 | CLB-MP-HAUL-DT5478-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1 | 1 | 6500
500159793 | CLB-MP-HAUL-DT5478-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1 | 1 | 6500
500159792 | CLB-MP-HAUL-DT5478-BRKSYS-BRVTR | Brake Treadle Valve | 1 | 1 | 6500
500159791 | CLB-MP-HAUL-DT5478-BRKSYS-BRVRL | Brake Dual Relay Valves | 1 | 1 | 6500
500159790 | CLB-MP-HAUL-DT5478-BRKSYS-BRVLV | Brake & Steering Manifold | 1 | 1 | 6500
500159789 | CLB-MP-HAUL-DT5478-BRKSYS-BRSTV | Brake & Steering Valve | 1 | 1 | 6500
500159788 | CLB-MP-HAUL-DT5478-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1 | 1 | 6500
500159787 | CLB-MP-HAUL-DT5478-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1 | 1 | 6500
500159786 | CLB-MP-HAUL-DT5478-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1 | 1 | 6500
500159785 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC | Accumulator Brake Supply Rr | 1 | 1 | 6500
500159784 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 1 | 1 | 6500
500159783 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC | Accumulator Brake Supply Fr | 1 | 1 | 6500
500159762 | CLB-MP-HAUL-DT5478-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 1 | 1 | 6500
500159761 | CLB-MP-HAUL-DT5478 | DT5478 Liebherr T264 OHT | 1 | 1 | 6500
500164782 | CLB-MP-HAUL-DT5477-STRSYS-STACC-SACRH | Accumulator Steering ODS | 630 | 630 | 6500
500164781 | CLB-MP-HAUL-DT5477-STRSYS-STACC-SACLH | Accumulator Steering DS | 630 | 630 | 6500
500164780 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 630 | 630 | 6500
500164779 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 630 | 630 | 6500
500164778 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 630 | 630 | 6500
500164777 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 630 | 630 | 6500
500159750 | CLB-MP-HAUL-DT5477-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 630 | 630 | 6500
500159749 | CLB-MP-HAUL-DT5477-STRUCT-TRAYS | Tray | 630 | 630 | 6500
500159748 | CLB-MP-HAUL-DT5477-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 630 | 630 | 6500
500159747 | CLB-MP-HAUL-DT5477-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 630 | 630 | 6500
500159746 | CLB-MP-HAUL-DT5477-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 630 | 630 | 6500
500159745 | CLB-MP-HAUL-DT5477-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 630 | 630 | 6500
500159744 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-SEATS | Operators Seat | 630 | 630 | 6500
500159743 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 630 | 630 | 6500
500159742 | CLB-MP-HAUL-DT5477-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 630 | 630 | 6500
500159741 | CLB-MP-HAUL-DT5477-STRUCT-CABIN | Operators Cabin | 630 | 630 | 6500
500159740 | CLB-MP-HAUL-DT5477-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 630 | 630 | 6500
500159739 | CLB-MP-HAUL-DT5477-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 630 | 630 | 6500
500159738 | CLB-MP-HAUL-DT5477-STRSYS-STVLV | Valve Flow Amplifier | 630 | 630 | 6500
500159737 | CLB-MP-HAUL-DT5477-STRSYS-STRIA | Steering Idler Arm | 630 | 630 | 6500
500159736 | CLB-MP-HAUL-DT5477-STRSYS-STRCY-STCYR | Steering Cylinder RH | 630 | 630 | 6500
500159735 | CLB-MP-HAUL-DT5477-STRSYS-STRCY-STCYL | Steering Cylinder LH | 630 | 630 | 6500
500159734 | CLB-MP-HAUL-DT5477-STRSYS-STLTR | Steering Linkages & Tie Rods | 630 | 630 | 6500
500159733 | CLB-MP-HAUL-DT5477-STRSYS-STCNT | Steering Control Unit | 630 | 630 | 6500
500159732 | CLB-MP-HAUL-DT5477-STRSYS-STACC | Accumulator Steering RHS | 630 | 630 | 6500
500159731 | CLB-MP-HAUL-DT5477-STRSYS-STACC | Accumulator Steering LHS | 630 | 630 | 6500
500159730 | CLB-MP-HAUL-DT5477-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 630 | 630 | 6500
500159729 | CLB-MP-HAUL-DT5477-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 630 | 630 | 6500
500159728 | CLB-MP-HAUL-DT5477-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 630 | 630 | 6500
500159727 | CLB-MP-HAUL-DT5477-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 630 | 630 | 6500
500159726 | CLB-MP-HAUL-DT5477-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 630 | 630 | 6500
500159725 | CLB-MP-HAUL-DT5477-HYDSYS-HYDOC | Hydraulic Oil Cooler | 630 | 630 | 6500
500159724 | CLB-MP-HAUL-DT5477-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 630 | 630 | 6500
500159723 | CLB-MP-HAUL-DT5477-HYDSYS-HOMAN | Hoist Manifold | 630 | 630 | 6500
500159722 | CLB-MP-HAUL-DT5477-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 630 | 630 | 6500
500159721 | CLB-MP-HAUL-DT5477-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 630 | 630 | 6500
500159720 | CLB-MP-HAUL-DT5477-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 630 | 630 | 6500
500159719 | CLB-MP-HAUL-DT5477-HYDSYS-GROCL | Gear Oil Cooler | 630 | 630 | 6500
500159718 | CLB-MP-HAUL-DT5477-GRSYST-ALBPP | Auto Lube Pump | 630 | 630 | 6500
500159717 | CLB-MP-HAUL-DT5477-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 630 | 630 | 6500
500159716 | CLB-MP-HAUL-DT5477-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 630 | 630 | 6500
500159715 | CLB-MP-HAUL-DT5477-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 630 | 630 | 6500
500159714 | CLB-MP-HAUL-DT5477-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 630 | 630 | 6500
500159713 | CLB-MP-HAUL-DT5477-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 630 | 630 | 6500
500159712 | CLB-MP-HAUL-DT5477-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 630 | 630 | 6500
500159711 | CLB-MP-HAUL-DT5477-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 630 | 630 | 6500
500159710 | CLB-MP-HAUL-DT5477-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 630 | 630 | 6500
500159709 | CLB-MP-HAUL-DT5477-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 630 | 630 | 6500
500159708 | CLB-MP-HAUL-DT5477-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 630 | 630 | 6500
500159707 | CLB-MP-HAUL-DT5477-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 630 | 630 | 6500
500159706 | CLB-MP-HAUL-DT5477-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 630 | 630 | 6500
500159705 | CLB-MP-HAUL-DT5477-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 630 | 630 | 6500
500159704 | CLB-MP-HAUL-DT5477-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 630 | 630 | 6500
500159703 | CLB-MP-HAUL-DT5477-ENGINE-INTEX-TBORF | Turbocharger RH Front | 630 | 630 | 6500
500159702 | CLB-MP-HAUL-DT5477-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 630 | 630 | 6500
500159701 | CLB-MP-HAUL-DT5477-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 630 | 630 | 6500
500159700 | CLB-MP-HAUL-DT5477-ENGINE-INTEX-AFTER | Aftercooler Engine | 630 | 630 | 6500
500159699 | CLB-MP-HAUL-DT5477-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 630 | 630 | 6500
500159698 | CLB-MP-HAUL-DT5477-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 630 | 630 | 6500
500159697 | CLB-MP-HAUL-DT5477-ENGINE-FUSYS-FUINJ | Fuel Injectors | 630 | 630 | 6500
500159696 | CLB-MP-HAUL-DT5477-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 630 | 630 | 6500
500159695 | CLB-MP-HAUL-DT5477-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 630 | 630 | 6500
500159694 | CLB-MP-HAUL-DT5477-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 630 | 630 | 6500
500159693 | CLB-MP-HAUL-DT5477-ENGINE-COSYS-HTWPP | Engine Water Pump | 630 | 630 | 6500
500159692 | CLB-MP-HAUL-DT5477-ENGINE-COSYS-COFAN | Fan Cooling System | 630 | 630 | 6500
500159691 | CLB-MP-HAUL-DT5477-ENGINE | Engine Assembly Cummins QSK60 | 630 | 630 | 6500
500159690 | CLB-MP-HAUL-DT5477-ELCTLV-START-STMUP | Starter Motor Upper | 630 | 630 | 6500
500159689 | CLB-MP-HAUL-DT5477-ELCTLV-START-STMLO | Starter Motor Lower | 630 | 630 | 6500
500159688 | CLB-MP-HAUL-DT5477-ELCTLV-HARNS | Electrical Harness | 630 | 630 | 6500
500159687 | CLB-MP-HAUL-DT5477-ELCTLV-CHARG-BATTY | Batteries | 630 | 630 | 6500
500159686 | CLB-MP-HAUL-DT5477-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 630 | 630 | 6500
500159685 | CLB-MP-HAUL-DT5477-ELCTHV-HVGBX-HVRES | Grid Resistors | 630 | 630 | 6500
500159684 | CLB-MP-HAUL-DT5477-ELCTHV-HVGBM | Grid Box Blower Motor | 630 | 630 | 6500
500159683 | CLB-MP-HAUL-DT5477-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 630 | 630 | 6500
500159682 | CLB-MP-HAUL-DT5477-ELCTHV-HVBLW | Main High Voltage Blower | 630 | 630 | 6500
500159681 | CLB-MP-HAUL-DT5477-ELCTHV-HVALT | High Voltage Alternator | 630 | 630 | 6500
500159680 | CLB-MP-HAUL-DT5477-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 630 | 630 | 6500
500159679 | CLB-MP-HAUL-DT5477-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 630 | 630 | 6500
500159678 | CLB-MP-HAUL-DT5477-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 630 | 630 | 6500
500159677 | CLB-MP-HAUL-DT5477-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 630 | 630 | 6500
500159676 | CLB-MP-HAUL-DT5477-BRKSYS-BRVTR | Brake Treadle Valve | 630 | 630 | 6500
500159675 | CLB-MP-HAUL-DT5477-BRKSYS-BRVRL | Brake Dual Relay Valves | 630 | 630 | 6500
500159674 | CLB-MP-HAUL-DT5477-BRKSYS-BRVLV | Brake & Steering Manifold | 630 | 630 | 6500
500159673 | CLB-MP-HAUL-DT5477-BRKSYS-BRSTV | Brake & Steering Valve | 630 | 630 | 6500
500159582 | CLB-MP-HAUL-DT5477-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 630 | 630 | 6500
500159581 | CLB-MP-HAUL-DT5477-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 630 | 630 | 6500
500159580 | CLB-MP-HAUL-DT5477-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 630 | 630 | 6500
500159579 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC | Accumulator Brake Supply Rr | 630 | 630 | 6500
500159578 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 630 | 630 | 6500
500159577 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC | Accumulator Brake Supply Fr | 630 | 630 | 6500
500159576 | CLB-MP-HAUL-DT5477-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 630 | 630 | 6500
500159575 | CLB-MP-HAUL-DT5477 | DT5477 Liebherr T264 OHT | 630 | 630 | 6500
500164776 | CLB-MP-HAUL-DT5476-STRSYS-STACC-SACRH | Accumulator Steering ODS | 920 | 920 | 6500
500164775 | CLB-MP-HAUL-DT5476-STRSYS-STACC-SACLH | Accumulator Steering DS | 920 | 920 | 6500
500164774 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 920 | 920 | 6500
500164773 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 920 | 920 | 6500
500164772 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 920 | 920 | 6500
500164771 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 920 | 920 | 6500
500159659 | CLB-MP-HAUL-DT5476-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 920 | 920 | 6500
500159658 | CLB-MP-HAUL-DT5476-STRUCT-TRAYS | Tray | 920 | 920 | 6500
500159657 | CLB-MP-HAUL-DT5476-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 920 | 920 | 6500
500159656 | CLB-MP-HAUL-DT5476-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 920 | 920 | 6500
500159655 | CLB-MP-HAUL-DT5476-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 920 | 920 | 6500
500159654 | CLB-MP-HAUL-DT5476-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 920 | 920 | 6500
500159653 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-SEATS | Operators Seat | 920 | 920 | 6500
500159652 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 920 | 920 | 6500
500159651 | CLB-MP-HAUL-DT5476-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 920 | 920 | 6500
500159650 | CLB-MP-HAUL-DT5476-STRUCT-CABIN | Operators Cabin | 920 | 920 | 6500
500159649 | CLB-MP-HAUL-DT5476-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 920 | 920 | 6500
500159648 | CLB-MP-HAUL-DT5476-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 920 | 920 | 6500
500159647 | CLB-MP-HAUL-DT5476-STRSYS-STVLV | Valve Flow Amplifier | 920 | 920 | 6500
500159646 | CLB-MP-HAUL-DT5476-STRSYS-STRIA | Steering Idler Arm | 920 | 920 | 6500
500159645 | CLB-MP-HAUL-DT5476-STRSYS-STRCY-STCYR | Steering Cylinder RH | 920 | 920 | 6500
500159644 | CLB-MP-HAUL-DT5476-STRSYS-STRCY-STCYL | Steering Cylinder LH | 920 | 920 | 6500
500159643 | CLB-MP-HAUL-DT5476-STRSYS-STLTR | Steering Linkages & Tie Rods | 920 | 920 | 6500
500159642 | CLB-MP-HAUL-DT5476-STRSYS-STCNT | Steering Control Unit | 920 | 920 | 6500
500159641 | CLB-MP-HAUL-DT5476-STRSYS-STACC | Accumulator Steering RHS | 920 | 920 | 6500
500159640 | CLB-MP-HAUL-DT5476-STRSYS-STACC | Accumulator Steering LHS | 920 | 920 | 6500
500159639 | CLB-MP-HAUL-DT5476-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 920 | 920 | 6500
500159638 | CLB-MP-HAUL-DT5476-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 920 | 920 | 6500
500159637 | CLB-MP-HAUL-DT5476-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 920 | 920 | 6500
500159636 | CLB-MP-HAUL-DT5476-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 920 | 920 | 6500
500159635 | CLB-MP-HAUL-DT5476-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 920 | 920 | 6500
500159634 | CLB-MP-HAUL-DT5476-HYDSYS-HYDOC | Hydraulic Oil Cooler | 920 | 920 | 6500
500159633 | CLB-MP-HAUL-DT5476-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 920 | 920 | 6500
500159632 | CLB-MP-HAUL-DT5476-HYDSYS-HOMAN | Hoist Manifold | 920 | 920 | 6500
500159631 | CLB-MP-HAUL-DT5476-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 920 | 920 | 6500
500159630 | CLB-MP-HAUL-DT5476-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 920 | 920 | 6500
500159629 | CLB-MP-HAUL-DT5476-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 920 | 920 | 6500
500159628 | CLB-MP-HAUL-DT5476-HYDSYS-GROCL | Gear Oil Cooler | 920 | 920 | 6500
500159627 | CLB-MP-HAUL-DT5476-GRSYST-ALBPP | Auto Lube Pump | 920 | 920 | 6500
500159626 | CLB-MP-HAUL-DT5476-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 920 | 920 | 6500
500159625 | CLB-MP-HAUL-DT5476-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 920 | 920 | 6500
500159624 | CLB-MP-HAUL-DT5476-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 920 | 920 | 6500
500159623 | CLB-MP-HAUL-DT5476-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 920 | 920 | 6500
500159622 | CLB-MP-HAUL-DT5476-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 920 | 920 | 6500
500159621 | CLB-MP-HAUL-DT5476-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 920 | 920 | 6500
500159620 | CLB-MP-HAUL-DT5476-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 920 | 920 | 6500
500159619 | CLB-MP-HAUL-DT5476-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 920 | 920 | 6500
500159618 | CLB-MP-HAUL-DT5476-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 920 | 920 | 6500
500159617 | CLB-MP-HAUL-DT5476-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 920 | 920 | 6500
500159616 | CLB-MP-HAUL-DT5476-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 920 | 920 | 6500
500159615 | CLB-MP-HAUL-DT5476-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 920 | 920 | 6500
500159614 | CLB-MP-HAUL-DT5476-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 920 | 920 | 6500
500159613 | CLB-MP-HAUL-DT5476-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 920 | 920 | 6500
500159612 | CLB-MP-HAUL-DT5476-ENGINE-INTEX-TBORF | Turbocharger RH Front | 920 | 920 | 6500
500159611 | CLB-MP-HAUL-DT5476-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 920 | 920 | 6500
500159610 | CLB-MP-HAUL-DT5476-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 920 | 920 | 6500
500159609 | CLB-MP-HAUL-DT5476-ENGINE-INTEX-AFTER | Aftercooler Engine | 920 | 920 | 6500
500159608 | CLB-MP-HAUL-DT5476-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 920 | 920 | 6500
500159607 | CLB-MP-HAUL-DT5476-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 920 | 920 | 6500
500159606 | CLB-MP-HAUL-DT5476-ENGINE-FUSYS-FUINJ | Fuel Injectors | 920 | 920 | 6500
500159605 | CLB-MP-HAUL-DT5476-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 920 | 920 | 6500
500159604 | CLB-MP-HAUL-DT5476-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 920 | 920 | 6500
500159603 | CLB-MP-HAUL-DT5476-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 920 | 920 | 6500
500159602 | CLB-MP-HAUL-DT5476-ENGINE-COSYS-HTWPP | Engine Water Pump | 920 | 920 | 6500
500159601 | CLB-MP-HAUL-DT5476-ENGINE-COSYS-COFAN | Fan Cooling System | 920 | 920 | 6500
500159600 | CLB-MP-HAUL-DT5476-ENGINE | Engine Assembly Cummins QSK60 | 920 | 920 | 6500
500159599 | CLB-MP-HAUL-DT5476-ELCTLV-START-STMUP | Starter Motor Upper | 920 | 920 | 6500
500159598 | CLB-MP-HAUL-DT5476-ELCTLV-START-STMLO | Starter Motor Lower | 920 | 920 | 6500
500159597 | CLB-MP-HAUL-DT5476-ELCTLV-HARNS | Electrical Harness | 920 | 920 | 6500
500159596 | CLB-MP-HAUL-DT5476-ELCTLV-CHARG-BATTY | Batteries | 920 | 920 | 6500
500159595 | CLB-MP-HAUL-DT5476-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 920 | 920 | 6500
500159594 | CLB-MP-HAUL-DT5476-ELCTHV-HVGBX-HVRES | Grid Resistors | 920 | 920 | 6500
500159593 | CLB-MP-HAUL-DT5476-ELCTHV-HVGBM | Grid Box Blower Motor | 920 | 920 | 6500
500159592 | CLB-MP-HAUL-DT5476-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 920 | 920 | 6500
500159591 | CLB-MP-HAUL-DT5476-ELCTHV-HVBLW | Main High Voltage Blower | 920 | 920 | 6500
500159590 | CLB-MP-HAUL-DT5476-ELCTHV-HVALT | High Voltage Alternator | 920 | 920 | 6500
500159589 | CLB-MP-HAUL-DT5476-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 920 | 920 | 6500
500159588 | CLB-MP-HAUL-DT5476-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 920 | 920 | 6500
500159587 | CLB-MP-HAUL-DT5476-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 920 | 920 | 6500
500159586 | CLB-MP-HAUL-DT5476-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 920 | 920 | 6500
500159585 | CLB-MP-HAUL-DT5476-BRKSYS-BRVTR | Brake Treadle Valve | 920 | 920 | 6500
500159584 | CLB-MP-HAUL-DT5476-BRKSYS-BRVRL | Brake Dual Relay Valves | 920 | 920 | 6500
500159583 | CLB-MP-HAUL-DT5476-BRKSYS-BRVLV | Brake & Steering Manifold | 920 | 920 | 6500
500159412 | CLB-MP-HAUL-DT5476-BRKSYS-BRSTV | Brake & Steering Valve | 920 | 920 | 6500
500159411 | CLB-MP-HAUL-DT5476-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 920 | 920 | 6500
500159410 | CLB-MP-HAUL-DT5476-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 920 | 920 | 6500
500159409 | CLB-MP-HAUL-DT5476-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 920 | 920 | 6500
500159408 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC | Accumulator Brake Supply Rr | 920 | 920 | 6500
500159407 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 920 | 920 | 6500
500159406 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC | Accumulator Brake Supply Fr | 920 | 920 | 6500
500159405 | CLB-MP-HAUL-DT5476-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 920 | 920 | 6500
500159404 | CLB-MP-HAUL-DT5476 | DT5476 Liebherr T264 OHT | 920 | 920 | 6500
500164770 | CLB-MP-HAUL-DT5475-STRSYS-STACC-SACRH | Accumulator Steering ODS | 211 | 211 | 6500
500164769 | CLB-MP-HAUL-DT5475-STRSYS-STACC-SACLH | Accumulator Steering DS | 211 | 211 | 6500
500164768 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 211 | 211 | 6500
500164767 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 211 | 211 | 6500
500164766 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 211 | 211 | 6500
500164765 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 211 | 211 | 6500
500159399 | CLB-MP-HAUL-DT5475-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 211 | 211 | 6500
500159398 | CLB-MP-HAUL-DT5475-STRUCT-TRAYS | Tray | 211 | 211 | 6500
500159397 | CLB-MP-HAUL-DT5475-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 211 | 211 | 6500
500159396 | CLB-MP-HAUL-DT5475-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 211 | 211 | 6500
500159395 | CLB-MP-HAUL-DT5475-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 211 | 211 | 6500
500159394 | CLB-MP-HAUL-DT5475-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 211 | 211 | 6500
500159393 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-SEATS | Operators Seat | 211 | 211 | 6500
500159392 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 211 | 211 | 6500
500159391 | CLB-MP-HAUL-DT5475-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 211 | 211 | 6500
500159390 | CLB-MP-HAUL-DT5475-STRUCT-CABIN | Operators Cabin | 211 | 211 | 6500
500159389 | CLB-MP-HAUL-DT5475-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 211 | 211 | 6500
500159388 | CLB-MP-HAUL-DT5475-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 211 | 211 | 6500
500159387 | CLB-MP-HAUL-DT5475-STRSYS-STVLV | Valve Flow Amplifier | 211 | 211 | 6500
500159386 | CLB-MP-HAUL-DT5475-STRSYS-STRIA | Steering Idler Arm | 211 | 211 | 6500
500159385 | CLB-MP-HAUL-DT5475-STRSYS-STRCY-STCYR | Steering Cylinder RH | 211 | 211 | 6500
500159384 | CLB-MP-HAUL-DT5475-STRSYS-STRCY-STCYL | Steering Cylinder LH | 211 | 211 | 6500
500159383 | CLB-MP-HAUL-DT5475-STRSYS-STLTR | Steering Linkages & Tie Rods | 211 | 211 | 6500
500159382 | CLB-MP-HAUL-DT5475-STRSYS-STCNT | Steering Control Unit | 211 | 211 | 6500
500159381 | CLB-MP-HAUL-DT5475-STRSYS-STACC | Accumulator Steering RHS | 211 | 211 | 6500
500159380 | CLB-MP-HAUL-DT5475-STRSYS-STACC | Accumulator Steering LHS | 211 | 211 | 6500
500159379 | CLB-MP-HAUL-DT5475-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 211 | 211 | 6500
500159378 | CLB-MP-HAUL-DT5475-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 211 | 211 | 6500
500159377 | CLB-MP-HAUL-DT5475-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 211 | 211 | 6500
500159376 | CLB-MP-HAUL-DT5475-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 211 | 211 | 6500
500159375 | CLB-MP-HAUL-DT5475-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 211 | 211 | 6500
500159374 | CLB-MP-HAUL-DT5475-HYDSYS-HYDOC | Hydraulic Oil Cooler | 211 | 211 | 6500
500159373 | CLB-MP-HAUL-DT5475-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 211 | 211 | 6500
500159372 | CLB-MP-HAUL-DT5475-HYDSYS-HOMAN | Hoist Manifold | 211 | 211 | 6500
500159371 | CLB-MP-HAUL-DT5475-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 211 | 211 | 6500
500159370 | CLB-MP-HAUL-DT5475-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 211 | 211 | 6500
500159369 | CLB-MP-HAUL-DT5475-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 211 | 211 | 6500
500159368 | CLB-MP-HAUL-DT5475-HYDSYS-GROCL | Gear Oil Cooler | 211 | 211 | 6500
500159367 | CLB-MP-HAUL-DT5475-GRSYST-ALBPP | Auto Lube Pump | 211 | 211 | 6500
500159366 | CLB-MP-HAUL-DT5475-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 211 | 211 | 6500
500159365 | CLB-MP-HAUL-DT5475-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 211 | 211 | 6500
500159364 | CLB-MP-HAUL-DT5475-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 211 | 211 | 6500
500159363 | CLB-MP-HAUL-DT5475-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 211 | 211 | 6500
500159362 | CLB-MP-HAUL-DT5475-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 211 | 211 | 6500
500159361 | CLB-MP-HAUL-DT5475-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 211 | 211 | 6500
500159360 | CLB-MP-HAUL-DT5475-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 211 | 211 | 6500
500159359 | CLB-MP-HAUL-DT5475-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 211 | 211 | 6500
500159358 | CLB-MP-HAUL-DT5475-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 211 | 211 | 6500
500159357 | CLB-MP-HAUL-DT5475-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 211 | 211 | 6500
500159356 | CLB-MP-HAUL-DT5475-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 211 | 211 | 6500
500159355 | CLB-MP-HAUL-DT5475-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 211 | 211 | 6500
500159354 | CLB-MP-HAUL-DT5475-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 211 | 211 | 6500
500159353 | CLB-MP-HAUL-DT5475-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 211 | 211 | 6500
500159352 | CLB-MP-HAUL-DT5475-ENGINE-INTEX-TBORF | Turbocharger RH Front | 211 | 211 | 6500
500159351 | CLB-MP-HAUL-DT5475-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 211 | 211 | 6500
500159350 | CLB-MP-HAUL-DT5475-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 211 | 211 | 6500
500159349 | CLB-MP-HAUL-DT5475-ENGINE-INTEX-AFTER | Aftercooler Engine | 211 | 211 | 6500
500159348 | CLB-MP-HAUL-DT5475-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 211 | 211 | 6500
500159347 | CLB-MP-HAUL-DT5475-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 211 | 211 | 6500
500159346 | CLB-MP-HAUL-DT5475-ENGINE-FUSYS-FUINJ | Fuel Injectors | 211 | 211 | 6500
500159345 | CLB-MP-HAUL-DT5475-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 211 | 211 | 6500
500159344 | CLB-MP-HAUL-DT5475-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 211 | 211 | 6500
500159343 | CLB-MP-HAUL-DT5475-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 211 | 211 | 6500
500159342 | CLB-MP-HAUL-DT5475-ENGINE-COSYS-HTWPP | Engine Water Pump | 211 | 211 | 6500
500159341 | CLB-MP-HAUL-DT5475-ENGINE-COSYS-COFAN | Fan Cooling System | 211 | 211 | 6500
500159340 | CLB-MP-HAUL-DT5475-ENGINE | Engine Assembly Cummins QSK60 | 211 | 211 | 6500
500159339 | CLB-MP-HAUL-DT5475-ELCTLV-START-STMUP | Starter Motor Upper | 211 | 211 | 6500
500159338 | CLB-MP-HAUL-DT5475-ELCTLV-START-STMLO | Starter Motor Lower | 211 | 211 | 6500
500159337 | CLB-MP-HAUL-DT5475-ELCTLV-HARNS | Electrical Harness | 211 | 211 | 6500
500159336 | CLB-MP-HAUL-DT5475-ELCTLV-CHARG-BATTY | Batteries | 211 | 211 | 6500
500159335 | CLB-MP-HAUL-DT5475-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 211 | 211 | 6500
500159334 | CLB-MP-HAUL-DT5475-ELCTHV-HVGBX-HVRES | Grid Resistors | 211 | 211 | 6500
500159333 | CLB-MP-HAUL-DT5475-ELCTHV-HVGBM | Grid Box Blower Motor | 211 | 211 | 6500
500159332 | CLB-MP-HAUL-DT5475-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 211 | 211 | 6500
500159331 | CLB-MP-HAUL-DT5475-ELCTHV-HVBLW | Main High Voltage Blower | 211 | 211 | 6500
500159330 | CLB-MP-HAUL-DT5475-ELCTHV-HVALT | High Voltage Alternator | 211 | 211 | 6500
500159329 | CLB-MP-HAUL-DT5475-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 211 | 211 | 6500
500159328 | CLB-MP-HAUL-DT5475-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 211 | 211 | 6500
500159327 | CLB-MP-HAUL-DT5475-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 211 | 211 | 6500
500159326 | CLB-MP-HAUL-DT5475-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 211 | 211 | 6500
500159325 | CLB-MP-HAUL-DT5475-BRKSYS-BRVTR | Brake Treadle Valve | 211 | 211 | 6500
500159324 | CLB-MP-HAUL-DT5475-BRKSYS-BRVRL | Brake Dual Relay Valves | 211 | 211 | 6500
500159323 | CLB-MP-HAUL-DT5475-BRKSYS-BRVLV | Brake & Steering Manifold | 211 | 211 | 6500
500159322 | CLB-MP-HAUL-DT5475-BRKSYS-BRSTV | Brake & Steering Valve | 211 | 211 | 6500
500159321 | CLB-MP-HAUL-DT5475-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 211 | 211 | 6500
500159320 | CLB-MP-HAUL-DT5475-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 211 | 211 | 6500
500159319 | CLB-MP-HAUL-DT5475-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 211 | 211 | 6500
500159318 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC | Accumulator Brake Supply Rr | 211 | 211 | 6500
500159317 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 211 | 211 | 6500
500159316 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC | Accumulator Brake Supply Fr | 211 | 211 | 6500
500159315 | CLB-MP-HAUL-DT5475-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 211 | 211 | 6500
500159314 | CLB-MP-HAUL-DT5475 | DT5475 Liebherr T264 OHT | 211 | 211 | 6500
500164764 | CLB-MP-HAUL-DT5474-STRSYS-STACC-SACRH | Accumulator Steering ODS | 537 | 537 | 6500
500164763 | CLB-MP-HAUL-DT5474-STRSYS-STACC-SACLH | Accumulator Steering DS | 537 | 537 | 6500
500164762 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 537 | 537 | 6500
500164761 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 537 | 537 | 6500
500164760 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 537 | 537 | 6500
500164759 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 537 | 537 | 6500
500158974 | CLB-MP-HAUL-DT5474-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 537 | 537 | 6500
500158973 | CLB-MP-HAUL-DT5474-STRUCT-TRAYS | Tray | 537 | 537 | 6500
500158972 | CLB-MP-HAUL-DT5474-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 537 | 537 | 6500
500158971 | CLB-MP-HAUL-DT5474-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 537 | 537 | 6500
500158970 | CLB-MP-HAUL-DT5474-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 537 | 537 | 6500
500158969 | CLB-MP-HAUL-DT5474-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 537 | 537 | 6500
500158968 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-SEATS | Operators Seat | 537 | 537 | 6500
500158967 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 537 | 537 | 6500
500158966 | CLB-MP-HAUL-DT5474-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 537 | 537 | 6500
500158965 | CLB-MP-HAUL-DT5474-STRUCT-CABIN | Operators Cabin | 537 | 537 | 6500
500158964 | CLB-MP-HAUL-DT5474-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 537 | 537 | 6500
500158963 | CLB-MP-HAUL-DT5474-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 537 | 537 | 6500
500158962 | CLB-MP-HAUL-DT5474-STRSYS-STVLV | Valve Flow Amplifier | 537 | 537 | 6500
500158961 | CLB-MP-HAUL-DT5474-STRSYS-STRIA | Steering Idler Arm | 537 | 537 | 6500
500158960 | CLB-MP-HAUL-DT5474-STRSYS-STRCY-STCYR | Steering Cylinder RH | 537 | 537 | 6500
500158959 | CLB-MP-HAUL-DT5474-STRSYS-STRCY-STCYL | Steering Cylinder LH | 537 | 537 | 6500
500158958 | CLB-MP-HAUL-DT5474-STRSYS-STLTR | Steering Linkages & Tie Rods | 537 | 537 | 6500
500158957 | CLB-MP-HAUL-DT5474-STRSYS-STCNT | Steering Control Unit | 537 | 537 | 6500
500158956 | CLB-MP-HAUL-DT5474-STRSYS-STACC | Accumulator Steering RHS | 537 | 537 | 6500
500158955 | CLB-MP-HAUL-DT5474-STRSYS-STACC | Accumulator Steering LHS | 537 | 537 | 6500
500158954 | CLB-MP-HAUL-DT5474-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 537 | 537 | 6500
500158953 | CLB-MP-HAUL-DT5474-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 537 | 537 | 6500
500158952 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 537 | 537 | 6500
500158951 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 537 | 537 | 6500
500158950 | CLB-MP-HAUL-DT5474-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 537 | 537 | 6500
500158949 | CLB-MP-HAUL-DT5474-HYDSYS-HYDOC | Hydraulic Oil Cooler | 537 | 537 | 6500
500158948 | CLB-MP-HAUL-DT5474-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 537 | 537 | 6500
500158947 | CLB-MP-HAUL-DT5474-HYDSYS-HOMAN | Hoist Manifold | 537 | 537 | 6500
500158946 | CLB-MP-HAUL-DT5474-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 537 | 537 | 6500
500158945 | CLB-MP-HAUL-DT5474-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 537 | 537 | 6500
500158944 | CLB-MP-HAUL-DT5474-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 537 | 537 | 6500
500158943 | CLB-MP-HAUL-DT5474-HYDSYS-GROCL | Gear Oil Cooler | 537 | 537 | 6500
500158942 | CLB-MP-HAUL-DT5474-GRSYST-ALBPP | Auto Lube Pump | 537 | 537 | 6500
500158941 | CLB-MP-HAUL-DT5474-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 537 | 537 | 6500
500158940 | CLB-MP-HAUL-DT5474-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 537 | 537 | 6500
500158939 | CLB-MP-HAUL-DT5474-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 537 | 537 | 6500
500158938 | CLB-MP-HAUL-DT5474-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 537 | 537 | 6500
500158937 | CLB-MP-HAUL-DT5474-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 537 | 537 | 6500
500158936 | CLB-MP-HAUL-DT5474-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 537 | 537 | 6500
500158935 | CLB-MP-HAUL-DT5474-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 537 | 537 | 6500
500158934 | CLB-MP-HAUL-DT5474-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 537 | 537 | 6500
500158933 | CLB-MP-HAUL-DT5474-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 537 | 537 | 6500
500158932 | CLB-MP-HAUL-DT5474-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 537 | 537 | 6500
500158931 | CLB-MP-HAUL-DT5474-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 537 | 537 | 6500
500158930 | CLB-MP-HAUL-DT5474-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 537 | 537 | 6500
500158929 | CLB-MP-HAUL-DT5474-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 537 | 537 | 6500
500158928 | CLB-MP-HAUL-DT5474-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 537 | 537 | 6500
500158927 | CLB-MP-HAUL-DT5474-ENGINE-INTEX-TBORF | Turbocharger RH Front | 537 | 537 | 6500
500158926 | CLB-MP-HAUL-DT5474-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 537 | 537 | 6500
500158925 | CLB-MP-HAUL-DT5474-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 537 | 537 | 6500
500158924 | CLB-MP-HAUL-DT5474-ENGINE-INTEX-AFTER | Aftercooler Engine | 537 | 537 | 6500
500158923 | CLB-MP-HAUL-DT5474-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 537 | 537 | 6500
500158922 | CLB-MP-HAUL-DT5474-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 537 | 537 | 6500
500158921 | CLB-MP-HAUL-DT5474-ENGINE-FUSYS-FUINJ | Fuel Injectors | 537 | 537 | 6500
500158920 | CLB-MP-HAUL-DT5474-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 537 | 537 | 6500
500158919 | CLB-MP-HAUL-DT5474-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 537 | 537 | 6500
500158918 | CLB-MP-HAUL-DT5474-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 537 | 537 | 6500
500158917 | CLB-MP-HAUL-DT5474-ENGINE-COSYS-HTWPP | Engine Water Pump | 537 | 537 | 6500
500158916 | CLB-MP-HAUL-DT5474-ENGINE-COSYS-COFAN | Fan Cooling System | 537 | 537 | 6500
500158915 | CLB-MP-HAUL-DT5474-ENGINE | Engine Assembly Cummins QSK60 | 537 | 537 | 6500
500158914 | CLB-MP-HAUL-DT5474-ELCTLV-START-STMUP | Starter Motor Upper | 537 | 537 | 6500
500158913 | CLB-MP-HAUL-DT5474-ELCTLV-START-STMLO | Starter Motor Lower | 537 | 537 | 6500
500158912 | CLB-MP-HAUL-DT5474-ELCTLV-HARNS | Electrical Harness | 537 | 537 | 6500
500158911 | CLB-MP-HAUL-DT5474-ELCTLV-CHARG-BATTY | Batteries | 537 | 537 | 6500
500158910 | CLB-MP-HAUL-DT5474-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 537 | 537 | 6500
500158909 | CLB-MP-HAUL-DT5474-ELCTHV-HVGBX-HVRES | Grid Resistors | 537 | 537 | 6500
500158908 | CLB-MP-HAUL-DT5474-ELCTHV-HVGBM | Grid Box Blower Motor | 537 | 537 | 6500
500158907 | CLB-MP-HAUL-DT5474-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 537 | 537 | 6500
500158906 | CLB-MP-HAUL-DT5474-ELCTHV-HVBLW | Main High Voltage Blower | 537 | 537 | 6500
500158905 | CLB-MP-HAUL-DT5474-ELCTHV-HVALT | High Voltage Alternator | 537 | 537 | 6500
500158904 | CLB-MP-HAUL-DT5474-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 537 | 537 | 6500
500158903 | CLB-MP-HAUL-DT5474-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 537 | 537 | 6500
500158902 | CLB-MP-HAUL-DT5474-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 537 | 537 | 6500
500158901 | CLB-MP-HAUL-DT5474-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 537 | 537 | 6500
500158900 | CLB-MP-HAUL-DT5474-BRKSYS-BRVTR | Brake Treadle Valve | 537 | 537 | 6500
500158899 | CLB-MP-HAUL-DT5474-BRKSYS-BRVRL | Brake Dual Relay Valves | 537 | 537 | 6500
500158898 | CLB-MP-HAUL-DT5474-BRKSYS-BRVLV | Brake & Steering Manifold | 537 | 537 | 6500
500158897 | CLB-MP-HAUL-DT5474-BRKSYS-BRSTV | Brake & Steering Valve | 537 | 537 | 6500
500158896 | CLB-MP-HAUL-DT5474-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 537 | 537 | 6500
500158895 | CLB-MP-HAUL-DT5474-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 537 | 537 | 6500
500158894 | CLB-MP-HAUL-DT5474-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 537 | 537 | 6500
500158893 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC | Accumulator Brake Supply Rr | 537 | 537 | 6500
500158892 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 537 | 537 | 6500
500158891 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC | Accumulator Brake Supply Fr | 537 | 537 | 6500
500158890 | CLB-MP-HAUL-DT5474-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 537 | 537 | 6500
500158889 | CLB-MP-HAUL-DT5474 | DT5474 Liebherr T264 OHT | 537 | 537 | 6500
500164758 | CLB-MP-HAUL-DT5473-STRSYS-STACC-SACRH | Accumulator Steering ODS | 866 | 866 | 6500
500164757 | CLB-MP-HAUL-DT5473-STRSYS-STACC-SACLH | Accumulator Steering DS | 866 | 866 | 6500
500164756 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 866 | 866 | 6500
500164755 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 866 | 866 | 6500
500164754 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 866 | 866 | 6500
500164753 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 866 | 866 | 6500
500158888 | CLB-MP-HAUL-DT5473-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 866 | 866 | 6500
500158887 | CLB-MP-HAUL-DT5473-STRUCT-TRAYS | Tray | 866 | 866 | 6500
500158886 | CLB-MP-HAUL-DT5473-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 866 | 866 | 6500
500158885 | CLB-MP-HAUL-DT5473-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 866 | 866 | 6500
500158884 | CLB-MP-HAUL-DT5473-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 866 | 866 | 6500
500158883 | CLB-MP-HAUL-DT5473-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 866 | 866 | 6500
500158882 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-SEATS | Operators Seat | 866 | 866 | 6500
500158881 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 866 | 866 | 6500
500158880 | CLB-MP-HAUL-DT5473-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 866 | 866 | 6500
500158879 | CLB-MP-HAUL-DT5473-STRUCT-CABIN | Operators Cabin | 866 | 866 | 6500
500158878 | CLB-MP-HAUL-DT5473-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 866 | 866 | 6500
500158877 | CLB-MP-HAUL-DT5473-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 866 | 866 | 6500
500158876 | CLB-MP-HAUL-DT5473-STRSYS-STVLV | Valve Flow Amplifier | 866 | 866 | 6500
500158875 | CLB-MP-HAUL-DT5473-STRSYS-STRIA | Steering Idler Arm | 866 | 866 | 6500
500158874 | CLB-MP-HAUL-DT5473-STRSYS-STRCY-STCYR | Steering Cylinder RH | 866 | 866 | 6500
500158873 | CLB-MP-HAUL-DT5473-STRSYS-STRCY-STCYL | Steering Cylinder LH | 866 | 866 | 6500
500158872 | CLB-MP-HAUL-DT5473-STRSYS-STLTR | Steering Linkages & Tie Rods | 866 | 866 | 6500
500158871 | CLB-MP-HAUL-DT5473-STRSYS-STCNT | Steering Control Unit | 866 | 866 | 6500
500158870 | CLB-MP-HAUL-DT5473-STRSYS-STACC | Accumulator Steering RHS | 866 | 866 | 6500
500158869 | CLB-MP-HAUL-DT5473-STRSYS-STACC | Accumulator Steering LHS | 866 | 866 | 6500
500158868 | CLB-MP-HAUL-DT5473-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 866 | 866 | 6500
500158867 | CLB-MP-HAUL-DT5473-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 866 | 866 | 6500
500158866 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 866 | 866 | 6500
500158865 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 866 | 866 | 6500
500158864 | CLB-MP-HAUL-DT5473-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 866 | 866 | 6500
500158863 | CLB-MP-HAUL-DT5473-HYDSYS-HYDOC | Hydraulic Oil Cooler | 866 | 866 | 6500
500158862 | CLB-MP-HAUL-DT5473-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 866 | 866 | 6500
500158861 | CLB-MP-HAUL-DT5473-HYDSYS-HOMAN | Hoist Manifold | 866 | 866 | 6500
500158860 | CLB-MP-HAUL-DT5473-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 866 | 866 | 6500
500158859 | CLB-MP-HAUL-DT5473-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 866 | 866 | 6500
500158858 | CLB-MP-HAUL-DT5473-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 866 | 866 | 6500
500158857 | CLB-MP-HAUL-DT5473-HYDSYS-GROCL | Gear Oil Cooler | 866 | 866 | 6500
500158856 | CLB-MP-HAUL-DT5473-GRSYST-ALBPP | Auto Lube Pump | 866 | 866 | 6500
500158855 | CLB-MP-HAUL-DT5473-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 866 | 866 | 6500
500158854 | CLB-MP-HAUL-DT5473-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 866 | 866 | 6500
500158853 | CLB-MP-HAUL-DT5473-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 866 | 866 | 6500
500158852 | CLB-MP-HAUL-DT5473-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 866 | 866 | 6500
500158851 | CLB-MP-HAUL-DT5473-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 866 | 866 | 6500
500158850 | CLB-MP-HAUL-DT5473-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 866 | 866 | 6500
500158849 | CLB-MP-HAUL-DT5473-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 866 | 866 | 6500
500158848 | CLB-MP-HAUL-DT5473-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 866 | 866 | 6500
500158847 | CLB-MP-HAUL-DT5473-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 866 | 866 | 6500
500158846 | CLB-MP-HAUL-DT5473-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 866 | 866 | 6500
500158845 | CLB-MP-HAUL-DT5473-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 866 | 866 | 6500
500158844 | CLB-MP-HAUL-DT5473-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 866 | 866 | 6500
500158843 | CLB-MP-HAUL-DT5473-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 866 | 866 | 6500
500158842 | CLB-MP-HAUL-DT5473-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 866 | 866 | 6500
500158841 | CLB-MP-HAUL-DT5473-ENGINE-INTEX-TBORF | Turbocharger RH Front | 866 | 866 | 6500
500158840 | CLB-MP-HAUL-DT5473-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 866 | 866 | 6500
500158839 | CLB-MP-HAUL-DT5473-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 866 | 866 | 6500
500158838 | CLB-MP-HAUL-DT5473-ENGINE-INTEX-AFTER | Aftercooler Engine | 866 | 866 | 6500
500158837 | CLB-MP-HAUL-DT5473-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 866 | 866 | 6500
500158836 | CLB-MP-HAUL-DT5473-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 866 | 866 | 6500
500158835 | CLB-MP-HAUL-DT5473-ENGINE-FUSYS-FUINJ | Fuel Injectors | 866 | 866 | 6500
500158834 | CLB-MP-HAUL-DT5473-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 866 | 866 | 6500
500158833 | CLB-MP-HAUL-DT5473-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 866 | 866 | 6500
500158832 | CLB-MP-HAUL-DT5473-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 866 | 866 | 6500
500158831 | CLB-MP-HAUL-DT5473-ENGINE-COSYS-HTWPP | Engine Water Pump | 866 | 866 | 6500
500158830 | CLB-MP-HAUL-DT5473-ENGINE-COSYS-COFAN | Fan Cooling System | 866 | 866 | 6500
500158829 | CLB-MP-HAUL-DT5473-ENGINE | Engine Assembly Cummins QSK60 | 866 | 866 | 6500
500158828 | CLB-MP-HAUL-DT5473-ELCTLV-START-STMUP | Starter Motor Upper | 866 | 866 | 6500
500158827 | CLB-MP-HAUL-DT5473-ELCTLV-START-STMLO | Starter Motor Lower | 866 | 866 | 6500
500158826 | CLB-MP-HAUL-DT5473-ELCTLV-HARNS | Electrical Harness | 866 | 866 | 6500
500158825 | CLB-MP-HAUL-DT5473-ELCTLV-CHARG-BATTY | Batteries | 866 | 866 | 6500
500158824 | CLB-MP-HAUL-DT5473-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 866 | 866 | 6500
500158823 | CLB-MP-HAUL-DT5473-ELCTHV-HVGBX-HVRES | Grid Resistors | 866 | 866 | 6500
500158822 | CLB-MP-HAUL-DT5473-ELCTHV-HVGBM | Grid Box Blower Motor | 866 | 866 | 6500
500158821 | CLB-MP-HAUL-DT5473-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 866 | 866 | 6500
500158820 | CLB-MP-HAUL-DT5473-ELCTHV-HVBLW | Main High Voltage Blower | 866 | 866 | 6500
500158819 | CLB-MP-HAUL-DT5473-ELCTHV-HVALT | High Voltage Alternator | 866 | 866 | 6500
500158818 | CLB-MP-HAUL-DT5473-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 866 | 866 | 6500
500158817 | CLB-MP-HAUL-DT5473-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 866 | 866 | 6500
500158816 | CLB-MP-HAUL-DT5473-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 866 | 866 | 6500
500158815 | CLB-MP-HAUL-DT5473-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 866 | 866 | 6500
500158814 | CLB-MP-HAUL-DT5473-BRKSYS-BRVTR | Brake Treadle Valve | 866 | 866 | 6500
500158813 | CLB-MP-HAUL-DT5473-BRKSYS-BRVRL | Brake Dual Relay Valves | 866 | 866 | 6500
500158812 | CLB-MP-HAUL-DT5473-BRKSYS-BRVLV | Brake & Steering Manifold | 866 | 866 | 6500
500158811 | CLB-MP-HAUL-DT5473-BRKSYS-BRSTV | Brake & Steering Valve | 866 | 866 | 6500
500158810 | CLB-MP-HAUL-DT5473-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 866 | 866 | 6500
500158809 | CLB-MP-HAUL-DT5473-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 866 | 866 | 6500
500158808 | CLB-MP-HAUL-DT5473-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 866 | 866 | 6500
500158807 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC | Accumulator Brake Supply Rr | 866 | 866 | 6500
500158806 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 866 | 866 | 6500
500158805 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC | Accumulator Brake Supply Fr | 866 | 866 | 6500
500158804 | CLB-MP-HAUL-DT5473-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 866 | 866 | 6500
500158803 | CLB-MP-HAUL-DT5473 | DT5473 Liebherr T264 OHT | 866 | 866 | 6500
500164752 | CLB-MP-HAUL-DT5472-STRSYS-STACC-SACRH | Accumulator Steering ODS | 2219 | 2219 | 6500
500164751 | CLB-MP-HAUL-DT5472-STRSYS-STACC-SACLH | Accumulator Steering DS | 2219 | 2219 | 6500
500164750 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 2219 | 2219 | 6500
500164749 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 2219 | 2219 | 6500
500164748 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 2219 | 2219 | 6500
500164747 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 2219 | 2219 | 6500
500159214 | CLB-MP-HAUL-DT5472-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 2219 | 2219 | 6500
500159213 | CLB-MP-HAUL-DT5472-STRUCT-TRAYS | Tray | 2219 | 2219 | 6500
500159212 | CLB-MP-HAUL-DT5472-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 2219 | 2219 | 6500
500159211 | CLB-MP-HAUL-DT5472-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 2219 | 2219 | 6500
500159210 | CLB-MP-HAUL-DT5472-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 2219 | 2219 | 6500
500159209 | CLB-MP-HAUL-DT5472-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 2219 | 2219 | 6500
500159208 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-SEATS | Operators Seat | 2219 | 2219 | 6500
500159207 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 2219 | 2219 | 6500
500159206 | CLB-MP-HAUL-DT5472-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 2219 | 2219 | 6500
500159205 | CLB-MP-HAUL-DT5472-STRUCT-CABIN | Operators Cabin | 2219 | 2219 | 6500
500159204 | CLB-MP-HAUL-DT5472-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 2219 | 2219 | 6500
500159203 | CLB-MP-HAUL-DT5472-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 2219 | 2219 | 6500
500159202 | CLB-MP-HAUL-DT5472-STRSYS-STVLV | Valve Flow Amplifier | 2219 | 2219 | 6500
500159201 | CLB-MP-HAUL-DT5472-STRSYS-STRIA | Steering Idler Arm | 2219 | 2219 | 6500
500159200 | CLB-MP-HAUL-DT5472-STRSYS-STRCY-STCYR | Steering Cylinder RH | 2219 | 2219 | 6500
500159199 | CLB-MP-HAUL-DT5472-STRSYS-STRCY-STCYL | Steering Cylinder LH | 2219 | 2219 | 6500
500159198 | CLB-MP-HAUL-DT5472-STRSYS-STLTR | Steering Linkages & Tie Rods | 2219 | 2219 | 6500
500159197 | CLB-MP-HAUL-DT5472-STRSYS-STCNT | Steering Control Unit | 2219 | 2219 | 6500
500159196 | CLB-MP-HAUL-DT5472-STRSYS-STACC | Accumulator Steering RHS | 2219 | 2219 | 6500
500159195 | CLB-MP-HAUL-DT5472-STRSYS-STACC | Accumulator Steering LHS | 2219 | 2219 | 6500
500159194 | CLB-MP-HAUL-DT5472-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 2219 | 2219 | 6500
500159193 | CLB-MP-HAUL-DT5472-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 2219 | 2219 | 6500
500159192 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 2219 | 2219 | 6500
500159191 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 2219 | 2219 | 6500
500159190 | CLB-MP-HAUL-DT5472-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 2219 | 2219 | 6500
500159189 | CLB-MP-HAUL-DT5472-HYDSYS-HYDOC | Hydraulic Oil Cooler | 2219 | 2219 | 6500
500159188 | CLB-MP-HAUL-DT5472-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 2219 | 2219 | 6500
500159187 | CLB-MP-HAUL-DT5472-HYDSYS-HOMAN | Hoist Manifold | 2219 | 2219 | 6500
500159186 | CLB-MP-HAUL-DT5472-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 2219 | 2219 | 6500
500159185 | CLB-MP-HAUL-DT5472-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 2219 | 1674 | 6500
500159184 | CLB-MP-HAUL-DT5472-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 2219 | 2219 | 6500
500159183 | CLB-MP-HAUL-DT5472-HYDSYS-GROCL | Gear Oil Cooler | 2219 | 2219 | 6500
500159182 | CLB-MP-HAUL-DT5472-GRSYST-ALBPP | Auto Lube Pump | 2219 | 2219 | 6500
500159181 | CLB-MP-HAUL-DT5472-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 2219 | 2219 | 6500
500159180 | CLB-MP-HAUL-DT5472-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 2219 | 2219 | 6500
500159179 | CLB-MP-HAUL-DT5472-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 2219 | 2219 | 6500
500159178 | CLB-MP-HAUL-DT5472-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 2219 | 2219 | 6500
500159177 | CLB-MP-HAUL-DT5472-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 2219 | 2219 | 6500
500159176 | CLB-MP-HAUL-DT5472-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 2219 | 2219 | 6500
500159175 | CLB-MP-HAUL-DT5472-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 2219 | 2219 | 6500
500159174 | CLB-MP-HAUL-DT5472-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 2219 | 2219 | 6500
500159173 | CLB-MP-HAUL-DT5472-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 2219 | 2219 | 6500
500159172 | CLB-MP-HAUL-DT5472-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 2219 | 2219 | 6500
500159171 | CLB-MP-HAUL-DT5472-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 2219 | 2219 | 6500
500159170 | CLB-MP-HAUL-DT5472-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 2219 | 2219 | 6500
500159169 | CLB-MP-HAUL-DT5472-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 2219 | 2219 | 6500
500159168 | CLB-MP-HAUL-DT5472-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 2219 | 2219 | 6500
500159167 | CLB-MP-HAUL-DT5472-ENGINE-INTEX-TBORF | Turbocharger RH Front | 2219 | 2219 | 6500
500159166 | CLB-MP-HAUL-DT5472-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 2219 | 2219 | 6500
500159165 | CLB-MP-HAUL-DT5472-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 2219 | 2219 | 6500
500159164 | CLB-MP-HAUL-DT5472-ENGINE-INTEX-AFTER | Aftercooler Engine | 2219 | 2219 | 6500
500159163 | CLB-MP-HAUL-DT5472-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 2219 | 2219 | 6500
500159162 | CLB-MP-HAUL-DT5472-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 2219 | 2219 | 6500
500159161 | CLB-MP-HAUL-DT5472-ENGINE-FUSYS-FUINJ | Fuel Injectors | 2219 | 2219 | 6500
500159160 | CLB-MP-HAUL-DT5472-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 2219 | 2219 | 6500
500159159 | CLB-MP-HAUL-DT5472-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 2219 | 2219 | 6500
500159158 | CLB-MP-HAUL-DT5472-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 2219 | 2219 | 6500
500159157 | CLB-MP-HAUL-DT5472-ENGINE-COSYS-HTWPP | Engine Water Pump | 2219 | 2219 | 6500
500159156 | CLB-MP-HAUL-DT5472-ENGINE-COSYS-COFAN | Fan Cooling System | 2219 | 2219 | 6500
500159155 | CLB-MP-HAUL-DT5472-ENGINE | Engine Assembly Cummins QSK60 | 2219 | 2219 | 6500
500159154 | CLB-MP-HAUL-DT5472-ELCTLV-START-STMUP | Starter Motor Upper | 2219 | 2219 | 6500
500159153 | CLB-MP-HAUL-DT5472-ELCTLV-START-STMLO | Starter Motor Lower | 2219 | 2219 | 6500
500159152 | CLB-MP-HAUL-DT5472-ELCTLV-HARNS | Electrical Harness | 2219 | 2219 | 6500
500159151 | CLB-MP-HAUL-DT5472-ELCTLV-CHARG-BATTY | Batteries | 2219 | 2219 | 6500
500159150 | CLB-MP-HAUL-DT5472-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 2219 | 2219 | 6500
500159149 | CLB-MP-HAUL-DT5472-ELCTHV-HVGBX-HVRES | Grid Resistors | 2219 | 2219 | 6500
500159148 | CLB-MP-HAUL-DT5472-ELCTHV-HVGBM | Grid Box Blower Motor | 2219 | 2219 | 6500
500159147 | CLB-MP-HAUL-DT5472-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 2219 | 2219 | 6500
500159146 | CLB-MP-HAUL-DT5472-ELCTHV-HVBLW | Main High Voltage Blower | 2219 | 2219 | 6500
500159145 | CLB-MP-HAUL-DT5472-ELCTHV-HVALT | High Voltage Alternator | 2219 | 2219 | 6500
500159144 | CLB-MP-HAUL-DT5472-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 2219 | 2219 | 6500
500159143 | CLB-MP-HAUL-DT5472-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 2219 | 2219 | 6500
500159142 | CLB-MP-HAUL-DT5472-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 2219 | 2219 | 6500
500159141 | CLB-MP-HAUL-DT5472-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 2219 | 2219 | 6500
500159140 | CLB-MP-HAUL-DT5472-BRKSYS-BRVTR | Brake Treadle Valve | 2219 | 2219 | 6500
500159139 | CLB-MP-HAUL-DT5472-BRKSYS-BRVRL | Brake Dual Relay Valves | 2219 | 2219 | 6500
500159138 | CLB-MP-HAUL-DT5472-BRKSYS-BRVLV | Brake & Steering Manifold | 2219 | 2219 | 6500
500159137 | CLB-MP-HAUL-DT5472-BRKSYS-BRSTV | Brake & Steering Valve | 2219 | 2219 | 6500
500159136 | CLB-MP-HAUL-DT5472-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 2219 | 2219 | 6500
500159135 | CLB-MP-HAUL-DT5472-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 2219 | 2219 | 6500
500159134 | CLB-MP-HAUL-DT5472-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 2219 | 2219 | 6500
500159133 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC | Accumulator Brake Supply Rr | 2219 | 2219 | 6500
500159132 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 2219 | 2219 | 6500
500159131 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC | Accumulator Brake Supply Fr | 2219 | 2219 | 6500
500159130 | CLB-MP-HAUL-DT5472-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 2219 | 2219 | 6500
500159129 | CLB-MP-HAUL-DT5472 | DT5472 Liebherr T264 OHT | 2219 | 2219 | 6500
500164746 | CLB-MP-HAUL-DT5471-STRSYS-STACC-SACRH | Accumulator Steering ODS | 2418 | 2418 | 6500
500164745 | CLB-MP-HAUL-DT5471-STRSYS-STACC-SACLH | Accumulator Steering DS | 2418 | 2418 | 6500
500164744 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 2418 | 2418 | 6500
500164743 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 2418 | 2418 | 6500
500164742 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 2418 | 2418 | 6500
500164741 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 2418 | 2418 | 6500
500159128 | CLB-MP-HAUL-DT5471-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 2418 | 2418 | 6500
500159127 | CLB-MP-HAUL-DT5471-STRUCT-TRAYS | Tray | 2418 | 2418 | 6500
500159126 | CLB-MP-HAUL-DT5471-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 2418 | 2418 | 6500
500159125 | CLB-MP-HAUL-DT5471-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 2418 | 2418 | 6500
500159124 | CLB-MP-HAUL-DT5471-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 2418 | 2418 | 6500
500159123 | CLB-MP-HAUL-DT5471-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 2418 | 2418 | 6500
500159122 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-SEATS | Operators Seat | 2418 | 2418 | 6500
500159121 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 2418 | 2418 | 6500
500159120 | CLB-MP-HAUL-DT5471-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 2418 | 2418 | 6500
500159119 | CLB-MP-HAUL-DT5471-STRUCT-CABIN | Operators Cabin | 2418 | 2418 | 6500
500159118 | CLB-MP-HAUL-DT5471-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 2418 | 2418 | 6500
500159117 | CLB-MP-HAUL-DT5471-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 2418 | 2418 | 6500
500159116 | CLB-MP-HAUL-DT5471-STRSYS-STVLV | Valve Flow Amplifier | 2418 | 2418 | 6500
500159115 | CLB-MP-HAUL-DT5471-STRSYS-STRIA | Steering Idler Arm | 2418 | 2418 | 6500
500159114 | CLB-MP-HAUL-DT5471-STRSYS-STRCY-STCYR | Steering Cylinder RH | 2418 | 2418 | 6500
500159113 | CLB-MP-HAUL-DT5471-STRSYS-STRCY-STCYL | Steering Cylinder LH | 2418 | 2418 | 6500
500159112 | CLB-MP-HAUL-DT5471-STRSYS-STLTR | Steering Linkages & Tie Rods | 2418 | 2418 | 6500
500159111 | CLB-MP-HAUL-DT5471-STRSYS-STCNT | Steering Control Unit | 2418 | 2418 | 6500
500159110 | CLB-MP-HAUL-DT5471-STRSYS-STACC | Accumulator Steering RHS | 2418 | 2418 | 6500
500159109 | CLB-MP-HAUL-DT5471-STRSYS-STACC | Accumulator Steering LHS | 2418 | 2418 | 6500
500159108 | CLB-MP-HAUL-DT5471-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 2418 | 2418 | 6500
500159107 | CLB-MP-HAUL-DT5471-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 2418 | 2418 | 6500
500159106 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 2418 | 2418 | 6500
500159105 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 2418 | 2418 | 6500
500159104 | CLB-MP-HAUL-DT5471-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 2418 | 2418 | 6500
500159103 | CLB-MP-HAUL-DT5471-HYDSYS-HYDOC | Hydraulic Oil Cooler | 2418 | 2418 | 6500
500159102 | CLB-MP-HAUL-DT5471-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 2418 | 2418 | 6500
500159101 | CLB-MP-HAUL-DT5471-HYDSYS-HOMAN | Hoist Manifold | 2418 | 2418 | 6500
500159100 | CLB-MP-HAUL-DT5471-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 2418 | 2418 | 6500
500159099 | CLB-MP-HAUL-DT5471-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 2418 | 2418 | 6500
500159098 | CLB-MP-HAUL-DT5471-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 2418 | 2418 | 6500
500159097 | CLB-MP-HAUL-DT5471-HYDSYS-GROCL | Gear Oil Cooler | 2418 | 2418 | 6500
500159096 | CLB-MP-HAUL-DT5471-GRSYST-ALBPP | Auto Lube Pump | 2418 | 2418 | 6500
500159095 | CLB-MP-HAUL-DT5471-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 2418 | 2418 | 6500
500159094 | CLB-MP-HAUL-DT5471-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 2418 | 2418 | 6500
500159093 | CLB-MP-HAUL-DT5471-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 2418 | 2418 | 6500
500159092 | CLB-MP-HAUL-DT5471-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 2418 | 2418 | 6500
500159091 | CLB-MP-HAUL-DT5471-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 2418 | 2418 | 6500
500159090 | CLB-MP-HAUL-DT5471-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 2418 | 2418 | 6500
500159089 | CLB-MP-HAUL-DT5471-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 2418 | 2418 | 6500
500159088 | CLB-MP-HAUL-DT5471-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 2418 | 2418 | 6500
500159087 | CLB-MP-HAUL-DT5471-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 2418 | 2418 | 6500
500159086 | CLB-MP-HAUL-DT5471-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 2418 | 2418 | 6500
500159085 | CLB-MP-HAUL-DT5471-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 2418 | 2418 | 6500
500159084 | CLB-MP-HAUL-DT5471-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 2418 | 2418 | 6500
500159083 | CLB-MP-HAUL-DT5471-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 2418 | 2418 | 6500
500159082 | CLB-MP-HAUL-DT5471-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 2418 | 2418 | 6500
500159081 | CLB-MP-HAUL-DT5471-ENGINE-INTEX-TBORF | Turbocharger RH Front | 2418 | 2418 | 6500
500159080 | CLB-MP-HAUL-DT5471-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 2418 | 2418 | 6500
500159079 | CLB-MP-HAUL-DT5471-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 2418 | 2418 | 6500
500159078 | CLB-MP-HAUL-DT5471-ENGINE-INTEX-AFTER | Aftercooler Engine | 2418 | 2418 | 6500
500159077 | CLB-MP-HAUL-DT5471-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 2418 | 2418 | 6500
500159076 | CLB-MP-HAUL-DT5471-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 2418 | 2418 | 6500
500159075 | CLB-MP-HAUL-DT5471-ENGINE-FUSYS-FUINJ | Fuel Injectors | 2418 | 2418 | 6500
500159074 | CLB-MP-HAUL-DT5471-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 2418 | 2418 | 6500
500159073 | CLB-MP-HAUL-DT5471-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 2418 | 2418 | 6500
500159072 | CLB-MP-HAUL-DT5471-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 2418 | 2418 | 6500
500159071 | CLB-MP-HAUL-DT5471-ENGINE-COSYS-HTWPP | Engine Water Pump | 2418 | 2418 | 6500
500159070 | CLB-MP-HAUL-DT5471-ENGINE-COSYS-COFAN | Fan Cooling System | 2418 | 2418 | 6500
500159069 | CLB-MP-HAUL-DT5471-ENGINE | Engine Assembly Cummins QSK60 | 2418 | 2418 | 6500
500159068 | CLB-MP-HAUL-DT5471-ELCTLV-START-STMUP | Starter Motor Upper | 2418 | 2418 | 6500
500159067 | CLB-MP-HAUL-DT5471-ELCTLV-START-STMLO | Starter Motor Lower | 2418 | 2418 | 6500
500159066 | CLB-MP-HAUL-DT5471-ELCTLV-HARNS | Electrical Harness | 2418 | 2418 | 6500
500159065 | CLB-MP-HAUL-DT5471-ELCTLV-CHARG-BATTY | Batteries | 2418 | 2418 | 6500
500159064 | CLB-MP-HAUL-DT5471-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 2418 | 2418 | 6500
500159063 | CLB-MP-HAUL-DT5471-ELCTHV-HVGBX-HVRES | Grid Resistors | 2418 | 2418 | 6500
500159062 | CLB-MP-HAUL-DT5471-ELCTHV-HVGBM | Grid Box Blower Motor | 2418 | 2418 | 6500
500159061 | CLB-MP-HAUL-DT5471-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 2418 | 2418 | 6500
500159060 | CLB-MP-HAUL-DT5471-ELCTHV-HVBLW | Main High Voltage Blower | 2418 | 2418 | 6500
500159059 | CLB-MP-HAUL-DT5471-ELCTHV-HVALT | High Voltage Alternator | 2418 | 2418 | 6500
500159058 | CLB-MP-HAUL-DT5471-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 2418 | 2418 | 6500
500159057 | CLB-MP-HAUL-DT5471-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 2418 | 2418 | 6500
500159056 | CLB-MP-HAUL-DT5471-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 2418 | 2418 | 6500
500159055 | CLB-MP-HAUL-DT5471-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 2418 | 2418 | 6500
500159054 | CLB-MP-HAUL-DT5471-BRKSYS-BRVTR | Brake Treadle Valve | 2418 | 2418 | 6500
500159053 | CLB-MP-HAUL-DT5471-BRKSYS-BRVRL | Brake Dual Relay Valves | 2418 | 2418 | 6500
500159052 | CLB-MP-HAUL-DT5471-BRKSYS-BRVLV | Brake & Steering Manifold | 2418 | 2418 | 6500
500159051 | CLB-MP-HAUL-DT5471-BRKSYS-BRSTV | Brake & Steering Valve | 2418 | 2418 | 6500
500159050 | CLB-MP-HAUL-DT5471-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 2418 | 2418 | 6500
500159049 | CLB-MP-HAUL-DT5471-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 2418 | 2418 | 6500
500159048 | CLB-MP-HAUL-DT5471-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 2418 | 2418 | 6500
500159047 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC | Accumulator Brake Supply Rr | 2418 | 2418 | 6500
500159046 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 2418 | 2418 | 6500
500159045 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC | Accumulator Brake Supply Fr | 2418 | 2418 | 6500
500159044 | CLB-MP-HAUL-DT5471-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 2418 | 2418 | 6500
500159043 | CLB-MP-HAUL-DT5471 | DT5471 Liebherr T264 OHT | 2418 | 2418 | 6500
500164740 | CLB-MP-HAUL-DT5470-STRSYS-STACC-SACRH | Accumulator Steering ODS | 3597 | 3597 | 6500
500164739 | CLB-MP-HAUL-DT5470-STRSYS-STACC-SACLH | Accumulator Steering DS | 3597 | 3597 | 6500
500164738 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 3597 | 3597 | 6500
500164737 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 3597 | 3597 | 6500
500164736 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 3597 | 3597 | 6500
500164735 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 3597 | 3597 | 6500
500158605 | CLB-MP-HAUL-DT5470-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 3597 | 3597 | 6500
500158604 | CLB-MP-HAUL-DT5470-STRUCT-TRAYS | Tray | 3597 | 3597 | 6500
500158603 | CLB-MP-HAUL-DT5470-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 3597 | 3597 | 6500
500158602 | CLB-MP-HAUL-DT5470-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 3597 | 3597 | 6500
500158601 | CLB-MP-HAUL-DT5470-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 3597 | 3597 | 6500
500158600 | CLB-MP-HAUL-DT5470-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 3597 | 3597 | 6500
500158599 | CLB-MP-HAUL-DT5470-STRUCT-CABIN-SEATS | Operators Seat | 3597 | 3597 | 6500
500158598 | CLB-MP-HAUL-DT5470-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 3597 | 3597 | 6500
500158597 | CLB-MP-HAUL-DT5470-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 3597 | 3597 | 6500
500158596 | CLB-MP-HAUL-DT5470-STRUCT-CABIN | Operators Cabin | 3597 | 3597 | 6500
500158595 | CLB-MP-HAUL-DT5470-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 3597 | 3597 | 6500
500158594 | CLB-MP-HAUL-DT5470-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 3597 | 3597 | 6500
500158593 | CLB-MP-HAUL-DT5470-STRSYS-STVLV | Valve Flow Amplifier | 3597 | 3597 | 6500
500158592 | CLB-MP-HAUL-DT5470-STRSYS-STRIA | Steering Idler Arm | 3597 | 3597 | 6500
500158591 | CLB-MP-HAUL-DT5470-STRSYS-STRCY-STCYR | Steering Cylinder RH | 3597 | 3597 | 6500
500158590 | CLB-MP-HAUL-DT5470-STRSYS-STRCY-STCYL | Steering Cylinder LH | 3597 | 3597 | 6500
500158589 | CLB-MP-HAUL-DT5470-STRSYS-STLTR | Steering Linkages & Tie Rods | 3597 | 3597 | 6500
500158588 | CLB-MP-HAUL-DT5470-STRSYS-STCNT | Steering Control Unit | 3597 | 3597 | 6500
500158587 | CLB-MP-HAUL-DT5470-STRSYS-STACC | Accumulator Steering RHS | 3597 | 3597 | 6500
500158586 | CLB-MP-HAUL-DT5470-STRSYS-STACC | Accumulator Steering LHS | 3597 | 3597 | 6500
500158585 | CLB-MP-HAUL-DT5470-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 3597 | 3597 | 6500
500158584 | CLB-MP-HAUL-DT5470-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 3597 | 3597 | 6500
500158583 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 3597 | 3597 | 6500
500158582 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 3597 | 3597 | 6500
500158581 | CLB-MP-HAUL-DT5470-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 3597 | 3597 | 6500
500158580 | CLB-MP-HAUL-DT5470-HYDSYS-HYDOC | Hydraulic Oil Cooler | 3597 | 3597 | 6500
500158579 | CLB-MP-HAUL-DT5470-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 3597 | 3597 | 6500
500158578 | CLB-MP-HAUL-DT5470-HYDSYS-HOMAN | Hoist Manifold | 3597 | 3597 | 6500
500158577 | CLB-MP-HAUL-DT5470-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 3597 | 1822 | 6500
500158576 | CLB-MP-HAUL-DT5470-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 3597 | 3597 | 6500
500158575 | CLB-MP-HAUL-DT5470-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 3597 | 3597 | 6500
500158574 | CLB-MP-HAUL-DT5470-HYDSYS-GROCL | Gear Oil Cooler | 3597 | 3597 | 6500
500158573 | CLB-MP-HAUL-DT5470-GRSYST-ALBPP | Auto Lube Pump | 3597 | 3597 | 6500
500158572 | CLB-MP-HAUL-DT5470-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 3597 | 3597 | 6500
500158571 | CLB-MP-HAUL-DT5470-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 3597 | 3597 | 6500
500158570 | CLB-MP-HAUL-DT5470-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 3597 | 3597 | 6500
500158569 | CLB-MP-HAUL-DT5470-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 3597 | 3597 | 6500
500158568 | CLB-MP-HAUL-DT5470-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 3597 | 3597 | 6500
500158567 | CLB-MP-HAUL-DT5470-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 3597 | 3597 | 6500
500158566 | CLB-MP-HAUL-DT5470-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 3597 | 3597 | 6500
500158565 | CLB-MP-HAUL-DT5470-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 3597 | 3597 | 6500
500158564 | CLB-MP-HAUL-DT5470-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 3597 | 3597 | 6500
500158563 | CLB-MP-HAUL-DT5470-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 3597 | 3597 | 6500
500158562 | CLB-MP-HAUL-DT5470-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 3597 | 3597 | 6500
500158561 | CLB-MP-HAUL-DT5470-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 3597 | 3597 | 6500
500158560 | CLB-MP-HAUL-DT5470-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 3597 | 3597 | 6500
500158559 | CLB-MP-HAUL-DT5470-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 3597 | 3597 | 6500
500158558 | CLB-MP-HAUL-DT5470-ENGINE-INTEX-TBORF | Turbocharger RH Front | 3597 | 3597 | 6500
500158557 | CLB-MP-HAUL-DT5470-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 3597 | 3597 | 6500
500158556 | CLB-MP-HAUL-DT5470-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 3597 | 3597 | 6500
500158555 | CLB-MP-HAUL-DT5470-ENGINE-INTEX-AFTER | Aftercooler Engine | 3597 | 3597 | 6500
500158554 | CLB-MP-HAUL-DT5470-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 3597 | 3597 | 6500
500158553 | CLB-MP-HAUL-DT5470-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 3597 | 3597 | 6500
500158552 | CLB-MP-HAUL-DT5470-ENGINE-FUSYS-FUINJ | Fuel Injectors | 3597 | 3597 | 6500
500158551 | CLB-MP-HAUL-DT5470-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 3597 | 3597 | 6500
500158550 | CLB-MP-HAUL-DT5470-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 3597 | 3597 | 6500
500158549 | CLB-MP-HAUL-DT5470-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 3597 | 3597 | 6500
500158548 | CLB-MP-HAUL-DT5470-ENGINE-COSYS-HTWPP | Engine Water Pump | 3597 | 3597 | 6500
500158547 | CLB-MP-HAUL-DT5470-ENGINE-COSYS-COFAN | Fan Cooling System | 3597 | 3597 | 6500
500158546 | CLB-MP-HAUL-DT5470-ENGINE | Engine Assembly Cummins QSK60 | 3597 | 3597 | 6500
500158545 | CLB-MP-HAUL-DT5470-ELCTLV-START-STMUP | Starter Motor Upper | 3597 | 3597 | 6500
500158544 | CLB-MP-HAUL-DT5470-ELCTLV-START-STMLO | Starter Motor Lower | 3597 | 3597 | 6500
500158543 | CLB-MP-HAUL-DT5470-ELCTLV-HARNS | Electrical Harness | 3597 | 3597 | 6500
500158542 | CLB-MP-HAUL-DT5470-ELCTLV-CHARG-BATTY | Batteries | 3597 | 3597 | 6500
500158541 | CLB-MP-HAUL-DT5470-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 3597 | 3597 | 6500
500158540 | CLB-MP-HAUL-DT5470-ELCTHV-HVGBX-HVRES | Grid Resistors | 3597 | 3597 | 6500
500158539 | CLB-MP-HAUL-DT5470-ELCTHV-HVGBM | Grid Box Blower Motor | 3597 | 3597 | 6500
500158538 | CLB-MP-HAUL-DT5470-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 3597 | 3597 | 6500
500158537 | CLB-MP-HAUL-DT5470-ELCTHV-HVBLW | Main High Voltage Blower | 3597 | 3597 | 6500
500158536 | CLB-MP-HAUL-DT5470-ELCTHV-HVALT | High Voltage Alternator | 3597 | 3597 | 6500
500158535 | CLB-MP-HAUL-DT5470-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 3597 | 3597 | 6500
500158534 | CLB-MP-HAUL-DT5470-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 3597 | 3597 | 6500
500158533 | CLB-MP-HAUL-DT5470-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 3597 | 3597 | 6500
500158532 | CLB-MP-HAUL-DT5470-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 3597 | 3597 | 6500
500158531 | CLB-MP-HAUL-DT5470-BRKSYS-BRVTR | Brake Treadle Valve | 3597 | 3597 | 6500
500158530 | CLB-MP-HAUL-DT5470-BRKSYS-BRVRL | Brake Dual Relay Valves | 3597 | 3597 | 6500
500158529 | CLB-MP-HAUL-DT5470-BRKSYS-BRVLV | Brake & Steering Manifold | 3597 | 3597 | 6500
500158528 | CLB-MP-HAUL-DT5470-BRKSYS-BRSTV | Brake & Steering Valve | 3597 | 3597 | 6500
500158527 | CLB-MP-HAUL-DT5470-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 3597 | 3597 | 6500
500158526 | CLB-MP-HAUL-DT5470-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 3597 | 3597 | 6500
500158525 | CLB-MP-HAUL-DT5470-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 3597 | 3597 | 6500
500158524 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC | Accumulator Brake Supply Rr | 3597 | 3597 | 6500
500158523 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 3597 | 3597 | 6500
500158342 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC | Accumulator Brake Supply Fr | 3597 | 3597 | 6500
500158341 | CLB-MP-HAUL-DT5470-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 3597 | 3597 | 6500
500158340 | CLB-MP-HAUL-DT5470 | DT5470 Liebherr T264 OHT | 3597 | 3597 | 6500
500164734 | CLB-MP-HAUL-DT5469-STRSYS-STACC-SACRH | Accumulator Steering ODS | 3686 | 3686 | 6500
500164733 | CLB-MP-HAUL-DT5469-STRSYS-STACC-SACLH | Accumulator Steering DS | 3686 | 3686 | 6500
500164732 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 3686 | 3686 | 6500
500164731 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 3686 | 3686 | 6500
500164730 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 3686 | 3686 | 6500
500164729 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 3686 | 3686 | 6500
500158521 | CLB-MP-HAUL-DT5469-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 3686 | 3686 | 6500
500158520 | CLB-MP-HAUL-DT5469-STRUCT-TRAYS | Tray | 3686 | 3686 | 6500
500158519 | CLB-MP-HAUL-DT5469-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 3686 | 3686 | 6500
500158518 | CLB-MP-HAUL-DT5469-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 3686 | 3686 | 6500
500158517 | CLB-MP-HAUL-DT5469-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 3686 | 3686 | 6500
500158516 | CLB-MP-HAUL-DT5469-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 3686 | 3686 | 6500
500158515 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-SEATS | Operators Seat | 3686 | 3686 | 6500
500158514 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 3686 | 3686 | 6500
500158513 | CLB-MP-HAUL-DT5469-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 3686 | 3686 | 6500
500158512 | CLB-MP-HAUL-DT5469-STRUCT-CABIN | Operators Cabin | 3686 | 3686 | 6500
500158511 | CLB-MP-HAUL-DT5469-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 3686 | 3686 | 6500
500158510 | CLB-MP-HAUL-DT5469-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 3686 | 3686 | 6500
500158509 | CLB-MP-HAUL-DT5469-STRSYS-STVLV | Valve Flow Amplifier | 3686 | 3686 | 6500
500158508 | CLB-MP-HAUL-DT5469-STRSYS-STRIA | Steering Idler Arm | 3686 | 3686 | 6500
500158507 | CLB-MP-HAUL-DT5469-STRSYS-STRCY-STCYR | Steering Cylinder RH | 3686 | 3686 | 6500
500158506 | CLB-MP-HAUL-DT5469-STRSYS-STRCY-STCYL | Steering Cylinder LH | 3686 | 3686 | 6500
500158505 | CLB-MP-HAUL-DT5469-STRSYS-STLTR | Steering Linkages & Tie Rods | 3686 | 3686 | 6500
500158504 | CLB-MP-HAUL-DT5469-STRSYS-STCNT | Steering Control Unit | 3686 | 3686 | 6500
500158503 | CLB-MP-HAUL-DT5469-STRSYS-STACC | Accumulator Steering RHS | 3686 | 3686 | 6500
500158502 | CLB-MP-HAUL-DT5469-STRSYS-STACC | Accumulator Steering LHS | 3686 | 3686 | 6500
500158501 | CLB-MP-HAUL-DT5469-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 3686 | 3686 | 6500
500158500 | CLB-MP-HAUL-DT5469-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 3686 | 3686 | 6500
500158499 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 3686 | 3686 | 6500
500158498 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 3686 | 3686 | 6500
500158497 | CLB-MP-HAUL-DT5469-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 3686 | 3686 | 6500
500158496 | CLB-MP-HAUL-DT5469-HYDSYS-HYDOC | Hydraulic Oil Cooler | 3686 | 3686 | 6500
500158495 | CLB-MP-HAUL-DT5469-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 3686 | 3686 | 6500
500158494 | CLB-MP-HAUL-DT5469-HYDSYS-HOMAN | Hoist Manifold | 3686 | 3686 | 6500
500158493 | CLB-MP-HAUL-DT5469-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 3686 | 3686 | 6500
500158492 | CLB-MP-HAUL-DT5469-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 3686 | 3686 | 6500
500158491 | CLB-MP-HAUL-DT5469-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 3686 | 3686 | 6500
500158490 | CLB-MP-HAUL-DT5469-HYDSYS-GROCL | Gear Oil Cooler | 3686 | 3686 | 6500
500158489 | CLB-MP-HAUL-DT5469-GRSYST-ALBPP | Auto Lube Pump | 3686 | 3686 | 6500
500158488 | CLB-MP-HAUL-DT5469-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 3686 | 3686 | 6500
500158487 | CLB-MP-HAUL-DT5469-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 3686 | 3686 | 6500
500158486 | CLB-MP-HAUL-DT5469-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 3686 | 3686 | 6500
500158485 | CLB-MP-HAUL-DT5469-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 3686 | 3686 | 6500
500158484 | CLB-MP-HAUL-DT5469-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 3686 | 3686 | 6500
500158483 | CLB-MP-HAUL-DT5469-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 3686 | 3686 | 6500
500158482 | CLB-MP-HAUL-DT5469-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 3686 | 3686 | 6500
500158481 | CLB-MP-HAUL-DT5469-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 3686 | 3686 | 6500
500158480 | CLB-MP-HAUL-DT5469-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 3686 | 3686 | 6500
500158479 | CLB-MP-HAUL-DT5469-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 3686 | 3686 | 6500
500158478 | CLB-MP-HAUL-DT5469-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 3686 | 3686 | 6500
500158477 | CLB-MP-HAUL-DT5469-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 3686 | 3686 | 6500
500158476 | CLB-MP-HAUL-DT5469-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 3686 | 3686 | 6500
500158475 | CLB-MP-HAUL-DT5469-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 3686 | 3686 | 6500
500158474 | CLB-MP-HAUL-DT5469-ENGINE-INTEX-TBORF | Turbocharger RH Front | 3686 | 3686 | 6500
500158473 | CLB-MP-HAUL-DT5469-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 3686 | 3686 | 6500
500158472 | CLB-MP-HAUL-DT5469-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 3686 | 3686 | 6500
500158471 | CLB-MP-HAUL-DT5469-ENGINE-INTEX-AFTER | Aftercooler Engine | 3686 | 3686 | 6500
500158470 | CLB-MP-HAUL-DT5469-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 3686 | 3686 | 6500
500158469 | CLB-MP-HAUL-DT5469-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 3686 | 3686 | 6500
500158468 | CLB-MP-HAUL-DT5469-ENGINE-FUSYS-FUINJ | Fuel Injectors | 3686 | 3686 | 6500
500158467 | CLB-MP-HAUL-DT5469-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 3686 | 3686 | 6500
500158466 | CLB-MP-HAUL-DT5469-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 3686 | 3686 | 6500
500158465 | CLB-MP-HAUL-DT5469-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 3686 | 3686 | 6500
500158464 | CLB-MP-HAUL-DT5469-ENGINE-COSYS-HTWPP | Engine Water Pump | 3686 | 3686 | 6500
500158463 | CLB-MP-HAUL-DT5469-ENGINE-COSYS-COFAN | Fan Cooling System | 3686 | 3686 | 6500
500158462 | CLB-MP-HAUL-DT5469-ENGINE | Engine Assembly Cummins QSK60 | 3686 | 3686 | 6500
500158461 | CLB-MP-HAUL-DT5469-ELCTLV-START-STMUP | Starter Motor Upper | 3686 | 3686 | 6500
500158460 | CLB-MP-HAUL-DT5469-ELCTLV-START-STMLO | Starter Motor Lower | 3686 | 3686 | 6500
500158459 | CLB-MP-HAUL-DT5469-ELCTLV-HARNS | Electrical Harness | 3686 | 3686 | 6500
500158458 | CLB-MP-HAUL-DT5469-ELCTLV-CHARG-BATTY | Batteries | 3686 | 3686 | 6500
500158457 | CLB-MP-HAUL-DT5469-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 3686 | 3686 | 6500
500158456 | CLB-MP-HAUL-DT5469-ELCTHV-HVGBX-HVRES | Grid Resistors | 3686 | 3686 | 6500
500158455 | CLB-MP-HAUL-DT5469-ELCTHV-HVGBM | Grid Box Blower Motor | 3686 | 3686 | 6500
500158454 | CLB-MP-HAUL-DT5469-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 3686 | 3686 | 6500
500158453 | CLB-MP-HAUL-DT5469-ELCTHV-HVBLW | Main High Voltage Blower | 3686 | 3686 | 6500
500158452 | CLB-MP-HAUL-DT5469-ELCTHV-HVALT | High Voltage Alternator | 3686 | 3686 | 6500
500158451 | CLB-MP-HAUL-DT5469-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 3686 | 3686 | 6500
500158450 | CLB-MP-HAUL-DT5469-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 3686 | 3686 | 6500
500158449 | CLB-MP-HAUL-DT5469-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 3686 | 3686 | 6500
500158448 | CLB-MP-HAUL-DT5469-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 3686 | 3686 | 6500
500158447 | CLB-MP-HAUL-DT5469-BRKSYS-BRVTR | Brake Treadle Valve | 3686 | 3686 | 6500
500158446 | CLB-MP-HAUL-DT5469-BRKSYS-BRVRL | Brake Dual Relay Valves | 3686 | 3686 | 6500
500158445 | CLB-MP-HAUL-DT5469-BRKSYS-BRVLV | Brake & Steering Manifold | 3686 | 3686 | 6500
500158444 | CLB-MP-HAUL-DT5469-BRKSYS-BRSTV | Brake & Steering Valve | 3686 | 3686 | 6500
500158443 | CLB-MP-HAUL-DT5469-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 3686 | 3686 | 6500
500158312 | CLB-MP-HAUL-DT5469-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 3686 | 3686 | 6500
500158311 | CLB-MP-HAUL-DT5469-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 3686 | 3686 | 6500
500158310 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC | Accumulator Brake Supply Rr | 3686 | 3686 | 6500
500158309 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 3686 | 3686 | 6500
500158308 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC | Accumulator Brake Supply Fr | 3686 | 3686 | 6500
500158307 | CLB-MP-HAUL-DT5469-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 3686 | 3686 | 6500
500158306 | CLB-MP-HAUL-DT5469 | DT5469 Liebherr T264 OHT | 3686 | 3686 | 6500
500164728 | CLB-MP-HAUL-DT5468-STRSYS-STACC-SACRH | Accumulator Steering ODS | 3720 | 3720 | 6500
500164727 | CLB-MP-HAUL-DT5468-STRSYS-STACC-SACLH | Accumulator Steering DS | 3720 | 3720 | 6500
500164726 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 3720 | 3720 | 6500
500164725 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 3720 | 3720 | 6500
500164724 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 3720 | 3720 | 6500
500164723 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 3720 | 3720 | 6500
500158439 | CLB-MP-HAUL-DT5468-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 3720 | 3720 | 6500
500158438 | CLB-MP-HAUL-DT5468-STRUCT-TRAYS | Tray | 3720 | 3720 | 6500
500158437 | CLB-MP-HAUL-DT5468-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 3720 | 3720 | 6500
500158436 | CLB-MP-HAUL-DT5468-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 3720 | 3720 | 6500
500158435 | CLB-MP-HAUL-DT5468-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 3720 | 3720 | 6500
500158434 | CLB-MP-HAUL-DT5468-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 3720 | 3720 | 6500
500158433 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-SEATS | Operators Seat | 3720 | 3720 | 6500
500158432 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 3720 | 3720 | 6500
500158431 | CLB-MP-HAUL-DT5468-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 3720 | 3720 | 6500
500158430 | CLB-MP-HAUL-DT5468-STRUCT-CABIN | Operators Cabin | 3720 | 3720 | 6500
500158429 | CLB-MP-HAUL-DT5468-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 3720 | 3720 | 6500
500158428 | CLB-MP-HAUL-DT5468-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 3720 | 3720 | 6500
500158427 | CLB-MP-HAUL-DT5468-STRSYS-STVLV | Valve Flow Amplifier | 3720 | 3720 | 6500
500158426 | CLB-MP-HAUL-DT5468-STRSYS-STRIA | Steering Idler Arm | 3720 | 3720 | 6500
500158425 | CLB-MP-HAUL-DT5468-STRSYS-STRCY-STCYR | Steering Cylinder RH | 3720 | 3720 | 6500
500158424 | CLB-MP-HAUL-DT5468-STRSYS-STRCY-STCYL | Steering Cylinder LH | 3720 | 3720 | 6500
500158423 | CLB-MP-HAUL-DT5468-STRSYS-STLTR | Steering Linkages & Tie Rods | 3720 | 3720 | 6500
500158422 | CLB-MP-HAUL-DT5468-STRSYS-STCNT | Steering Control Unit | 3720 | 3720 | 6500
500158421 | CLB-MP-HAUL-DT5468-STRSYS-STACC | Accumulator Steering RHS | 3720 | 3720 | 6500
500158420 | CLB-MP-HAUL-DT5468-STRSYS-STACC | Accumulator Steering LHS | 3720 | 3720 | 6500
500158419 | CLB-MP-HAUL-DT5468-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 3720 | 3720 | 6500
500158418 | CLB-MP-HAUL-DT5468-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 3720 | 3720 | 6500
500158417 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 3720 | 3720 | 6500
500158416 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 3720 | 3720 | 6500
500158415 | CLB-MP-HAUL-DT5468-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 3720 | 3720 | 6500
500158414 | CLB-MP-HAUL-DT5468-HYDSYS-HYDOC | Hydraulic Oil Cooler | 3720 | 3720 | 6500
500158413 | CLB-MP-HAUL-DT5468-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 3720 | 3720 | 6500
500158412 | CLB-MP-HAUL-DT5468-HYDSYS-HOMAN | Hoist Manifold | 3720 | 3720 | 6500
500158411 | CLB-MP-HAUL-DT5468-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 3720 | 3720 | 6500
500158410 | CLB-MP-HAUL-DT5468-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 3720 | 3720 | 6500
500158409 | CLB-MP-HAUL-DT5468-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 3720 | 3720 | 6500
500158408 | CLB-MP-HAUL-DT5468-HYDSYS-GROCL | Gear Oil Cooler | 3720 | 3720 | 6500
500158407 | CLB-MP-HAUL-DT5468-GRSYST-ALBPP | Auto Lube Pump | 3720 | 3720 | 6500
500158406 | CLB-MP-HAUL-DT5468-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 3720 | 3720 | 6500
500158405 | CLB-MP-HAUL-DT5468-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 3720 | 3720 | 6500
500158404 | CLB-MP-HAUL-DT5468-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 3720 | 3720 | 6500
500158403 | CLB-MP-HAUL-DT5468-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 3720 | 3720 | 6500
500158402 | CLB-MP-HAUL-DT5468-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 3720 | 3720 | 6500
500158401 | CLB-MP-HAUL-DT5468-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 3720 | 3720 | 6500
500158400 | CLB-MP-HAUL-DT5468-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 3720 | 3720 | 6500
500158399 | CLB-MP-HAUL-DT5468-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 3720 | 3720 | 6500
500158398 | CLB-MP-HAUL-DT5468-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 3720 | 3720 | 6500
500158397 | CLB-MP-HAUL-DT5468-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 3720 | 3720 | 6500
500158396 | CLB-MP-HAUL-DT5468-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 3720 | 3720 | 6500
500158395 | CLB-MP-HAUL-DT5468-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 3720 | 3720 | 6500
500158394 | CLB-MP-HAUL-DT5468-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 3720 | 3720 | 6500
500158393 | CLB-MP-HAUL-DT5468-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 3720 | 3720 | 6500
500158392 | CLB-MP-HAUL-DT5468-ENGINE-INTEX-TBORF | Turbocharger RH Front | 3720 | 3720 | 6500
500158391 | CLB-MP-HAUL-DT5468-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 3720 | 3720 | 6500
500158390 | CLB-MP-HAUL-DT5468-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 3720 | 3720 | 6500
500158389 | CLB-MP-HAUL-DT5468-ENGINE-INTEX-AFTER | Aftercooler Engine | 3720 | 3720 | 6500
500158388 | CLB-MP-HAUL-DT5468-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 3720 | 3720 | 6500
500158387 | CLB-MP-HAUL-DT5468-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 3720 | 3720 | 6500
500158386 | CLB-MP-HAUL-DT5468-ENGINE-FUSYS-FUINJ | Fuel Injectors | 3720 | 3720 | 6500
500158385 | CLB-MP-HAUL-DT5468-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 3720 | 3720 | 6500
500158384 | CLB-MP-HAUL-DT5468-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 3720 | 3720 | 6500
500158383 | CLB-MP-HAUL-DT5468-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 3720 | 3720 | 6500
500158382 | CLB-MP-HAUL-DT5468-ENGINE-COSYS-HTWPP | Engine Water Pump | 3720 | 3720 | 6500
500158381 | CLB-MP-HAUL-DT5468-ENGINE-COSYS-COFAN | Fan Cooling System | 3720 | 3720 | 6500
500158380 | CLB-MP-HAUL-DT5468-ENGINE | Engine Assembly Cummins QSK60 | 3720 | 3720 | 6500
500158379 | CLB-MP-HAUL-DT5468-ELCTLV-START-STMUP | Starter Motor Upper | 3720 | 3720 | 6500
500158378 | CLB-MP-HAUL-DT5468-ELCTLV-START-STMLO | Starter Motor Lower | 3720 | 3720 | 6500
500158377 | CLB-MP-HAUL-DT5468-ELCTLV-HARNS | Electrical Harness | 3720 | 3720 | 6500
500158376 | CLB-MP-HAUL-DT5468-ELCTLV-CHARG-BATTY | Batteries | 3720 | 3720 | 6500
500158375 | CLB-MP-HAUL-DT5468-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 3720 | 3720 | 6500
500158374 | CLB-MP-HAUL-DT5468-ELCTHV-HVGBX-HVRES | Grid Resistors | 3720 | 3720 | 6500
500158373 | CLB-MP-HAUL-DT5468-ELCTHV-HVGBM | Grid Box Blower Motor | 3720 | 3720 | 6500
500158372 | CLB-MP-HAUL-DT5468-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 3720 | 3720 | 6500
500158371 | CLB-MP-HAUL-DT5468-ELCTHV-HVBLW | Main High Voltage Blower | 3720 | 3720 | 6500
500158370 | CLB-MP-HAUL-DT5468-ELCTHV-HVALT | High Voltage Alternator | 3720 | 3720 | 6500
500158369 | CLB-MP-HAUL-DT5468-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 3720 | 3720 | 6500
500158368 | CLB-MP-HAUL-DT5468-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 3720 | 3720 | 6500
500158367 | CLB-MP-HAUL-DT5468-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 3720 | 3720 | 6500
500158366 | CLB-MP-HAUL-DT5468-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 3720 | 3720 | 6500
500158365 | CLB-MP-HAUL-DT5468-BRKSYS-BRVTR | Brake Treadle Valve | 3720 | 3720 | 6500
500158364 | CLB-MP-HAUL-DT5468-BRKSYS-BRVRL | Brake Dual Relay Valves | 3720 | 3720 | 6500
500158363 | CLB-MP-HAUL-DT5468-BRKSYS-BRVLV | Brake & Steering Manifold | 3720 | 3720 | 6500
500158362 | CLB-MP-HAUL-DT5468-BRKSYS-BRSTV | Brake & Steering Valve | 3720 | 3720 | 6500
500158361 | CLB-MP-HAUL-DT5468-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 3720 | 3720 | 6500
500158360 | CLB-MP-HAUL-DT5468-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 3720 | 3720 | 6500
500158359 | CLB-MP-HAUL-DT5468-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 3720 | 3720 | 6500
500158358 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC | Accumulator Brake Supply Rr | 3720 | 3720 | 6500
500158357 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 3720 | 3720 | 6500
500158356 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC | Accumulator Brake Supply Fr | 3720 | 3720 | 6500
500158355 | CLB-MP-HAUL-DT5468-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 3720 | 3720 | 6500
500158354 | CLB-MP-HAUL-DT5468 | DT5468 Liebherr T264 OHT | 3720 | 3720 | 6500
500164722 | CLB-MP-HAUL-DT5467-STRSYS-STACC-SACRH | Accumulator Steering ODS | 3380 | 3380 | 6500
500164721 | CLB-MP-HAUL-DT5467-STRSYS-STACC-SACLH | Accumulator Steering DS | 3380 | 3380 | 6500
500164720 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 3380 | 3380 | 6500
500164719 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 3380 | 3380 | 6500
500164718 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 3380 | 3380 | 6500
500164717 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 3380 | 3380 | 6500
500157307 | CLB-MP-HAUL-DT5467-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 3380 | 3380 | 6500
500157306 | CLB-MP-HAUL-DT5467-STRUCT-TRAYS | Tray | 3380 | 3380 | 6500
500157305 | CLB-MP-HAUL-DT5467-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 3380 | 3380 | 6500
500157304 | CLB-MP-HAUL-DT5467-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 3380 | 3380 | 6500
500157303 | CLB-MP-HAUL-DT5467-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 3380 | 3380 | 6500
500157302 | CLB-MP-HAUL-DT5467-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 3380 | 3380 | 6500
500157301 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-SEATS | Operators Seat | 3380 | 3380 | 6500
500157300 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 3380 | 3380 | 6500
500157299 | CLB-MP-HAUL-DT5467-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 3380 | 3380 | 6500
500157298 | CLB-MP-HAUL-DT5467-STRUCT-CABIN | Operators Cabin | 3380 | 3380 | 6500
500157297 | CLB-MP-HAUL-DT5467-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 3380 | 3380 | 6500
500157296 | CLB-MP-HAUL-DT5467-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 3380 | 3380 | 6500
500157295 | CLB-MP-HAUL-DT5467-STRSYS-STVLV | Valve Flow Amplifier | 3380 | 3380 | 6500
500157294 | CLB-MP-HAUL-DT5467-STRSYS-STRIA | Steering Idler Arm | 3380 | 3380 | 6500
500157293 | CLB-MP-HAUL-DT5467-STRSYS-STRCY-STCYR | Steering Cylinder RH | 3380 | 3380 | 6500
500157292 | CLB-MP-HAUL-DT5467-STRSYS-STRCY-STCYL | Steering Cylinder LH | 3380 | 3380 | 6500
500157291 | CLB-MP-HAUL-DT5467-STRSYS-STLTR | Steering Linkages & Tie Rods | 3380 | 3380 | 6500
500157290 | CLB-MP-HAUL-DT5467-STRSYS-STCNT | Steering Control Unit | 3380 | 3380 | 6500
500157289 | CLB-MP-HAUL-DT5467-STRSYS-STACC | Accumulator Steering RHS | 3380 | 3380 | 6500
500157288 | CLB-MP-HAUL-DT5467-STRSYS-STACC | Accumulator Steering LHS | 3380 | 3380 | 6500
500157287 | CLB-MP-HAUL-DT5467-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 3380 | 3380 | 6500
500157286 | CLB-MP-HAUL-DT5467-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 3380 | 3380 | 6500
500157285 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 3380 | 3380 | 6500
500157284 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 3380 | 3380 | 6500
500157283 | CLB-MP-HAUL-DT5467-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 3380 | 3380 | 6500
500157282 | CLB-MP-HAUL-DT5467-HYDSYS-HYDOC | Hydraulic Oil Cooler | 3380 | 3380 | 6500
500157281 | CLB-MP-HAUL-DT5467-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 3380 | 3380 | 6500
500157280 | CLB-MP-HAUL-DT5467-HYDSYS-HOMAN | Hoist Manifold | 3380 | 3380 | 6500
500157279 | CLB-MP-HAUL-DT5467-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 3380 | 3380 | 6500
500157278 | CLB-MP-HAUL-DT5467-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 3380 | 3380 | 6500
500157277 | CLB-MP-HAUL-DT5467-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 3380 | 3380 | 6500
500157276 | CLB-MP-HAUL-DT5467-HYDSYS-GROCL | Gear Oil Cooler | 3380 | 3380 | 6500
500157275 | CLB-MP-HAUL-DT5467-GRSYST-ALBPP | Auto Lube Pump | 3380 | 3380 | 6500
500157274 | CLB-MP-HAUL-DT5467-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 3380 | 3380 | 6500
500157273 | CLB-MP-HAUL-DT5467-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 3380 | 3380 | 6500
500157272 | CLB-MP-HAUL-DT5467-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 3380 | 3380 | 6500
500157271 | CLB-MP-HAUL-DT5467-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 3380 | 3380 | 6500
500157270 | CLB-MP-HAUL-DT5467-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 3380 | 3380 | 6500
500157269 | CLB-MP-HAUL-DT5467-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 3380 | 3380 | 6500
500157268 | CLB-MP-HAUL-DT5467-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 3380 | 3380 | 6500
500157267 | CLB-MP-HAUL-DT5467-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 3380 | 3380 | 6500
500157266 | CLB-MP-HAUL-DT5467-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 3380 | 3380 | 6500
500157265 | CLB-MP-HAUL-DT5467-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 3380 | 3380 | 6500
500157264 | CLB-MP-HAUL-DT5467-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 3380 | 3380 | 6500
500157263 | CLB-MP-HAUL-DT5467-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 3380 | 3380 | 6500
500157262 | CLB-MP-HAUL-DT5467-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 3380 | 3380 | 6500
500157261 | CLB-MP-HAUL-DT5467-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 3380 | 3380 | 6500
500157260 | CLB-MP-HAUL-DT5467-ENGINE-INTEX-TBORF | Turbocharger RH Front | 3380 | 3380 | 6500
500157259 | CLB-MP-HAUL-DT5467-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 3380 | 3380 | 6500
500157258 | CLB-MP-HAUL-DT5467-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 3380 | 3380 | 6500
500157257 | CLB-MP-HAUL-DT5467-ENGINE-INTEX-AFTER | Aftercooler Engine | 3380 | 3380 | 6500
500157256 | CLB-MP-HAUL-DT5467-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 3380 | 3380 | 6500
500157255 | CLB-MP-HAUL-DT5467-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 3380 | 3380 | 6500
500157254 | CLB-MP-HAUL-DT5467-ENGINE-FUSYS-FUINJ | Fuel Injectors | 3380 | 3380 | 6500
500157253 | CLB-MP-HAUL-DT5467-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 3380 | 3380 | 6500
500157252 | CLB-MP-HAUL-DT5467-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 3380 | 3380 | 6500
500157251 | CLB-MP-HAUL-DT5467-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 3380 | 3380 | 6500
500157250 | CLB-MP-HAUL-DT5467-ENGINE-COSYS-HTWPP | Engine Water Pump | 3380 | 3380 | 6500
500157249 | CLB-MP-HAUL-DT5467-ENGINE-COSYS-COFAN | Fan Cooling System | 3380 | 3380 | 6500
500157248 | CLB-MP-HAUL-DT5467-ENGINE | Engine Assembly Cummins QSK60 | 3380 | 3380 | 6500
500157247 | CLB-MP-HAUL-DT5467-ELCTLV-START-STMUP | Starter Motor Upper | 3380 | 3380 | 6500
500157246 | CLB-MP-HAUL-DT5467-ELCTLV-START-STMLO | Starter Motor Lower | 3380 | 3380 | 6500
500157245 | CLB-MP-HAUL-DT5467-ELCTLV-HARNS | Electrical Harness | 3380 | 3380 | 6500
500157244 | CLB-MP-HAUL-DT5467-ELCTLV-CHARG-BATTY | Batteries | 3380 | 3380 | 6500
500157243 | CLB-MP-HAUL-DT5467-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 3380 | 3380 | 6500
500157242 | CLB-MP-HAUL-DT5467-ELCTHV-HVGBX-HVRES | Grid Resistors | 3380 | 3380 | 6500
500157241 | CLB-MP-HAUL-DT5467-ELCTHV-HVGBM | Grid Box Blower Motor | 3380 | 3380 | 6500
500157240 | CLB-MP-HAUL-DT5467-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 3380 | 3380 | 6500
500157239 | CLB-MP-HAUL-DT5467-ELCTHV-HVBLW | Main High Voltage Blower | 3380 | 3380 | 6500
500157238 | CLB-MP-HAUL-DT5467-ELCTHV-HVALT | High Voltage Alternator | 3380 | 3380 | 6500
500157237 | CLB-MP-HAUL-DT5467-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 3380 | 3380 | 6500
500157236 | CLB-MP-HAUL-DT5467-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 3380 | 3380 | 6500
500157235 | CLB-MP-HAUL-DT5467-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 3380 | 3380 | 6500
500157234 | CLB-MP-HAUL-DT5467-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 3380 | 3380 | 6500
500157233 | CLB-MP-HAUL-DT5467-BRKSYS-BRVTR | Brake Treadle Valve | 3380 | 3380 | 6500
500157232 | CLB-MP-HAUL-DT5467-BRKSYS-BRVRL | Brake Dual Relay Valves | 3380 | 3380 | 6500
500157231 | CLB-MP-HAUL-DT5467-BRKSYS-BRVLV | Brake & Steering Manifold | 3380 | 3380 | 6500
500157230 | CLB-MP-HAUL-DT5467-BRKSYS-BRSTV | Brake & Steering Valve | 3380 | 3380 | 6500
500157229 | CLB-MP-HAUL-DT5467-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 3380 | 3380 | 6500
500157228 | CLB-MP-HAUL-DT5467-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 3380 | 3380 | 6500
500157227 | CLB-MP-HAUL-DT5467-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 3380 | 3380 | 6500
500157226 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC | Accumulator Brake Supply Rr | 3380 | 3380 | 6500
500157225 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 3380 | 3380 | 6500
500157224 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC | Accumulator Brake Supply Fr | 3380 | 3380 | 6500
500157223 | CLB-MP-HAUL-DT5467-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 3380 | 3380 | 6500
500157222 | CLB-MP-HAUL-DT5467 | DT5467 Liebherr T264 OHT | 3380 | 3380 | 6500
500164716 | CLB-MP-HAUL-DT5466-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1342 | 1342 | 6500
500164715 | CLB-MP-HAUL-DT5466-STRSYS-STACC-SACLH | Accumulator Steering DS | 1342 | 1342 | 6500
500164714 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1342 | 1342 | 6500
500164713 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1342 | 1342 | 6500
500164712 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1342 | 1342 | 6500
500164711 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1342 | 1342 | 6500
500157219 | CLB-MP-HAUL-DT5466-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1342 | 1342 | 6500
500157218 | CLB-MP-HAUL-DT5466-STRUCT-TRAYS | Tray | 1342 | 1342 | 6500
500157217 | CLB-MP-HAUL-DT5466-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1342 | 1342 | 6500
500157216 | CLB-MP-HAUL-DT5466-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1342 | 1342 | 6500
500157215 | CLB-MP-HAUL-DT5466-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1342 | 1342 | 6500
500157214 | CLB-MP-HAUL-DT5466-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1342 | 1342 | 6500
500157213 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-SEATS | Operators Seat | 1342 | 1342 | 6500
500157212 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1342 | 1342 | 6500
500157211 | CLB-MP-HAUL-DT5466-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1342 | 1342 | 6500
500157210 | CLB-MP-HAUL-DT5466-STRUCT-CABIN | Operators Cabin | 1342 | 1342 | 6500
500157209 | CLB-MP-HAUL-DT5466-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1342 | 1342 | 6500
500157208 | CLB-MP-HAUL-DT5466-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1342 | 1342 | 6500
500157207 | CLB-MP-HAUL-DT5466-STRSYS-STVLV | Valve Flow Amplifier | 1342 | 1342 | 6500
500157206 | CLB-MP-HAUL-DT5466-STRSYS-STRIA | Steering Idler Arm | 1342 | 1342 | 6500
500157205 | CLB-MP-HAUL-DT5466-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1342 | 1342 | 6500
500157204 | CLB-MP-HAUL-DT5466-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1342 | 1342 | 6500
500157203 | CLB-MP-HAUL-DT5466-STRSYS-STLTR | Steering Linkages & Tie Rods | 1342 | 1342 | 6500
500157202 | CLB-MP-HAUL-DT5466-STRSYS-STCNT | Steering Control Unit | 1342 | 1342 | 6500
500157201 | CLB-MP-HAUL-DT5466-STRSYS-STACC | Accumulator Steering RHS | 1342 | 1342 | 6500
500157200 | CLB-MP-HAUL-DT5466-STRSYS-STACC | Accumulator Steering LHS | 1342 | 1342 | 6500
500157199 | CLB-MP-HAUL-DT5466-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1342 | 1342 | 6500
500157198 | CLB-MP-HAUL-DT5466-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1342 | 1342 | 6500
500157197 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1342 | 1342 | 6500
500157196 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1342 | 1342 | 6500
500157195 | CLB-MP-HAUL-DT5466-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1342 | 1342 | 6500
500157194 | CLB-MP-HAUL-DT5466-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1342 | 1342 | 6500
500157193 | CLB-MP-HAUL-DT5466-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1342 | 1342 | 6500
500157192 | CLB-MP-HAUL-DT5466-HYDSYS-HOMAN | Hoist Manifold | 1342 | 1342 | 6500
500157191 | CLB-MP-HAUL-DT5466-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1342 | 1342 | 6500
500157190 | CLB-MP-HAUL-DT5466-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1342 | 1342 | 6500
500157189 | CLB-MP-HAUL-DT5466-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1342 | 1342 | 6500
500157188 | CLB-MP-HAUL-DT5466-HYDSYS-GROCL | Gear Oil Cooler | 1342 | 1342 | 6500
500157187 | CLB-MP-HAUL-DT5466-GRSYST-ALBPP | Auto Lube Pump | 1342 | 1342 | 6500
500157186 | CLB-MP-HAUL-DT5466-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1342 | 1342 | 6500
500157185 | CLB-MP-HAUL-DT5466-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1342 | 1342 | 6500
500157184 | CLB-MP-HAUL-DT5466-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1342 | 1342 | 6500
500157183 | CLB-MP-HAUL-DT5466-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1342 | 1342 | 6500
500157182 | CLB-MP-HAUL-DT5466-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1342 | 1342 | 6500
500157181 | CLB-MP-HAUL-DT5466-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1342 | 1342 | 6500
500157180 | CLB-MP-HAUL-DT5466-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1342 | 1342 | 6500
500157179 | CLB-MP-HAUL-DT5466-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1342 | 1342 | 6500
500157178 | CLB-MP-HAUL-DT5466-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1342 | 1342 | 6500
500157177 | CLB-MP-HAUL-DT5466-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1342 | 1342 | 6500
500157176 | CLB-MP-HAUL-DT5466-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1342 | 1342 | 6500
500157175 | CLB-MP-HAUL-DT5466-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1342 | 1342 | 6500
500157174 | CLB-MP-HAUL-DT5466-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1342 | 1342 | 6500
500157173 | CLB-MP-HAUL-DT5466-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1342 | 1342 | 6500
500157172 | CLB-MP-HAUL-DT5466-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1342 | 1342 | 6500
500157171 | CLB-MP-HAUL-DT5466-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1342 | 1342 | 6500
500157170 | CLB-MP-HAUL-DT5466-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1342 | 1342 | 6500
500157169 | CLB-MP-HAUL-DT5466-ENGINE-INTEX-AFTER | Aftercooler Engine | 1342 | 1342 | 6500
500157168 | CLB-MP-HAUL-DT5466-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1342 | 1342 | 6500
500157167 | CLB-MP-HAUL-DT5466-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1342 | 1342 | 6500
500157166 | CLB-MP-HAUL-DT5466-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1342 | 1342 | 6500
500157165 | CLB-MP-HAUL-DT5466-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1342 | 1342 | 6500
500157164 | CLB-MP-HAUL-DT5466-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1342 | 1342 | 6500
500157163 | CLB-MP-HAUL-DT5466-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1342 | 1342 | 6500
500157162 | CLB-MP-HAUL-DT5466-ENGINE-COSYS-HTWPP | Engine Water Pump | 1342 | 1342 | 6500
500157161 | CLB-MP-HAUL-DT5466-ENGINE-COSYS-COFAN | Fan Cooling System | 1342 | 1342 | 6500
500157160 | CLB-MP-HAUL-DT5466-ENGINE | Engine Assembly Cummins QSK60 | 1342 | 1342 | 6500
500157159 | CLB-MP-HAUL-DT5466-ELCTLV-START-STMUP | Starter Motor Upper | 1342 | 1342 | 6500
500157158 | CLB-MP-HAUL-DT5466-ELCTLV-START-STMLO | Starter Motor Lower | 1342 | 1342 | 6500
500157157 | CLB-MP-HAUL-DT5466-ELCTLV-HARNS | Electrical Harness | 1342 | 1342 | 6500
500157156 | CLB-MP-HAUL-DT5466-ELCTLV-CHARG-BATTY | Batteries | 1342 | 1342 | 6500
500157155 | CLB-MP-HAUL-DT5466-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1342 | 1342 | 6500
500157154 | CLB-MP-HAUL-DT5466-ELCTHV-HVGBX-HVRES | Grid Resistors | 1342 | 1342 | 6500
500157153 | CLB-MP-HAUL-DT5466-ELCTHV-HVGBM | Grid Box Blower Motor | 1342 | 1342 | 6500
500157152 | CLB-MP-HAUL-DT5466-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1342 | 1342 | 6500
500157151 | CLB-MP-HAUL-DT5466-ELCTHV-HVBLW | Main High Voltage Blower | 1342 | 1342 | 6500
500157150 | CLB-MP-HAUL-DT5466-ELCTHV-HVALT | High Voltage Alternator | 1342 | 1342 | 6500
500157149 | CLB-MP-HAUL-DT5466-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1342 | 1342 | 6500
500157148 | CLB-MP-HAUL-DT5466-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1342 | 1342 | 6500
500157147 | CLB-MP-HAUL-DT5466-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1342 | 1342 | 6500
500157146 | CLB-MP-HAUL-DT5466-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1342 | 1342 | 6500
500157145 | CLB-MP-HAUL-DT5466-BRKSYS-BRVTR | Brake Treadle Valve | 1342 | 1342 | 6500
500157144 | CLB-MP-HAUL-DT5466-BRKSYS-BRVRL | Brake Dual Relay Valves | 1342 | 1342 | 6500
500157143 | CLB-MP-HAUL-DT5466-BRKSYS-BRVLV | Brake & Steering Manifold | 1342 | 1342 | 6500
500157142 | CLB-MP-HAUL-DT5466-BRKSYS-BRSTV | Brake & Steering Valve | 1342 | 1342 | 6500
500157141 | CLB-MP-HAUL-DT5466-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1342 | 1342 | 6500
500157140 | CLB-MP-HAUL-DT5466-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1342 | 1342 | 6500
500157139 | CLB-MP-HAUL-DT5466-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1342 | 1342 | 6500
500157138 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC | Accumulator Brake Supply Rr | 1342 | 1342 | 6500
500157137 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 1342 | 1342 | 6500
500157136 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC | Accumulator Brake Supply Fr | 1342 | 1342 | 6500
500157135 | CLB-MP-HAUL-DT5466-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 1342 | 1342 | 6500
500157134 | CLB-MP-HAUL-DT5466 | DT5466 Liebherr T264 OHT | 1342 | 1342 | 6500
500164710 | CLB-MP-HAUL-DT5455-STRSYS-STACC-SACRH | Accumulator Steering ODS | 7738 | 7738 | 6500
500164709 | CLB-MP-HAUL-DT5455-STRSYS-STACC-SACLH | Accumulator Steering DS | 7738 | 7738 | 6500
500164708 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 7738 | 7738 | 6500
500164707 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 7738 | 7738 | 6500
500164706 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 7738 | 7738 | 6500
500164705 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 7738 | 7738 | 6500
500155895 | CLB-MP-HAUL-DT5455-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 7738 | 7738 | 6500
500155894 | CLB-MP-HAUL-DT5455-STRUCT-TRAYS | Tray | 7738 | 7738 | 6500
500155893 | CLB-MP-HAUL-DT5455-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 7738 | 7738 | 6500
500155892 | CLB-MP-HAUL-DT5455-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 7738 | 7738 | 6500
500155891 | CLB-MP-HAUL-DT5455-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 7738 | 7738 | 6500
500155890 | CLB-MP-HAUL-DT5455-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 7738 | 7738 | 6500
500155889 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-SEATS | Operators Seat | 7738 | 7738 | 6500
500155888 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 7738 | 7738 | 6500
500155887 | CLB-MP-HAUL-DT5455-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 7738 | 7738 | 6500
500155886 | CLB-MP-HAUL-DT5455-STRUCT-CABIN | Operators Cabin | 7738 | 7738 | 6500
500155885 | CLB-MP-HAUL-DT5455-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 7738 | 7738 | 6500
500155884 | CLB-MP-HAUL-DT5455-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 7738 | 7738 | 6500
500155883 | CLB-MP-HAUL-DT5455-STRSYS-STVLV | Valve Flow Amplifier | 7738 | 7738 | 6500
500155882 | CLB-MP-HAUL-DT5455-STRSYS-STRIA | Steering Idler Arm | 7738 | 7738 | 6500
500155881 | CLB-MP-HAUL-DT5455-STRSYS-STRCY-STCYR | Steering Cylinder RH | 7738 | 7738 | 6500
500155880 | CLB-MP-HAUL-DT5455-STRSYS-STRCY-STCYL | Steering Cylinder LH | 7738 | 4869 | 6500
500155879 | CLB-MP-HAUL-DT5455-STRSYS-STLTR | Steering Linkages & Tie Rods | 7738 | 7738 | 6500
500155878 | CLB-MP-HAUL-DT5455-STRSYS-STCNT | Steering Control Unit | 7738 | 7738 | 6500
500155877 | CLB-MP-HAUL-DT5455-STRSYS-STACC | Accumulator Steering RHS | 7738 | 7738 | 6500
500155876 | CLB-MP-HAUL-DT5455-STRSYS-STACC | Accumulator Steering LHS | 7738 | 7738 | 6500
500155875 | CLB-MP-HAUL-DT5455-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 7738 | 7738 | 6500
500155874 | CLB-MP-HAUL-DT5455-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 7738 | 7738 | 6500
500155873 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 7738 | 7738 | 6500
500155872 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 7738 | 7738 | 6500
500155871 | CLB-MP-HAUL-DT5455-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 7738 | 7738 | 6500
500155870 | CLB-MP-HAUL-DT5455-HYDSYS-HYDOC | Hydraulic Oil Cooler | 7738 | 7738 | 6500
500155869 | CLB-MP-HAUL-DT5455-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 7738 | 7738 | 6500
500155868 | CLB-MP-HAUL-DT5455-HYDSYS-HOMAN | Hoist Manifold | 7738 | 7738 | 6500
500155867 | CLB-MP-HAUL-DT5455-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 7738 | 7738 | 6500
500155866 | CLB-MP-HAUL-DT5455-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 7738 | 7738 | 6500
500155865 | CLB-MP-HAUL-DT5455-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 7738 | 7738 | 6500
500155864 | CLB-MP-HAUL-DT5455-HYDSYS-GROCL | Gear Oil Cooler | 7738 | 7738 | 6500
500155863 | CLB-MP-HAUL-DT5455-GRSYST-ALBPP | Auto Lube Pump | 7738 | 7738 | 6500
500155862 | CLB-MP-HAUL-DT5455-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 7738 | 7738 | 6500
500155861 | CLB-MP-HAUL-DT5455-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 7738 | 7738 | 6500
500155860 | CLB-MP-HAUL-DT5455-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 7738 | 7738 | 6500
500155859 | CLB-MP-HAUL-DT5455-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 7738 | 7738 | 6500
500155858 | CLB-MP-HAUL-DT5455-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 7738 | 7738 | 6500
500155857 | CLB-MP-HAUL-DT5455-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 7738 | 7738 | 6500
500155856 | CLB-MP-HAUL-DT5455-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 7738 | 7738 | 6500
500155855 | CLB-MP-HAUL-DT5455-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 7738 | 7738 | 6500
500155854 | CLB-MP-HAUL-DT5455-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 7738 | 7738 | 6500
500155853 | CLB-MP-HAUL-DT5455-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 7738 | 7738 | 6500
500155852 | CLB-MP-HAUL-DT5455-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 7738 | 7738 | 6500
500155851 | CLB-MP-HAUL-DT5455-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 7738 | 7738 | 6500
500155850 | CLB-MP-HAUL-DT5455-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 7738 | 7738 | 6500
500155849 | CLB-MP-HAUL-DT5455-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 7738 | 7738 | 6500
500155848 | CLB-MP-HAUL-DT5455-ENGINE-INTEX-TBORF | Turbocharger RH Front | 7738 | 7738 | 6500
500155847 | CLB-MP-HAUL-DT5455-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 7738 | 7738 | 6500
500155846 | CLB-MP-HAUL-DT5455-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 7738 | 7738 | 6500
500155845 | CLB-MP-HAUL-DT5455-ENGINE-INTEX-AFTER | Aftercooler Engine | 7738 | 7738 | 6500
500155844 | CLB-MP-HAUL-DT5455-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 7738 | 7738 | 6500
500155843 | CLB-MP-HAUL-DT5455-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 7738 | 7738 | 6500
500155842 | CLB-MP-HAUL-DT5455-ENGINE-FUSYS-FUINJ | Fuel Injectors | 7738 | 7738 | 6500
500155841 | CLB-MP-HAUL-DT5455-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 7738 | 7738 | 6500
500155840 | CLB-MP-HAUL-DT5455-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 7738 | 7738 | 6500
500155839 | CLB-MP-HAUL-DT5455-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 7738 | 7738 | 6500
500155838 | CLB-MP-HAUL-DT5455-ENGINE-COSYS-HTWPP | Engine Water Pump | 7738 | 7738 | 6500
500155837 | CLB-MP-HAUL-DT5455-ENGINE-COSYS-COFAN | Fan Cooling System | 7738 | 7738 | 6500
500155836 | CLB-MP-HAUL-DT5455-ENGINE | Engine Assembly Cummins QSK60 | 7738 | 7738 | 6500
500155835 | CLB-MP-HAUL-DT5455-ELCTLV-START-STMUP | Starter Motor Upper | 7738 | 7738 | 6500
500155834 | CLB-MP-HAUL-DT5455-ELCTLV-START-STMLO | Starter Motor Lower | 7738 | 7738 | 6500
500155833 | CLB-MP-HAUL-DT5455-ELCTLV-HARNS | Electrical Harness | 7738 | 7738 | 6500
500155832 | CLB-MP-HAUL-DT5455-ELCTLV-CHARG-BATTY | Batteries | 7738 | 7738 | 6500
500155831 | CLB-MP-HAUL-DT5455-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 7738 | 7738 | 6500
500155830 | CLB-MP-HAUL-DT5455-ELCTHV-HVGBX-HVRES | Grid Resistors | 7738 | 7738 | 6500
500155829 | CLB-MP-HAUL-DT5455-ELCTHV-HVGBM | Grid Box Blower Motor | 7738 | 7738 | 6500
500155828 | CLB-MP-HAUL-DT5455-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 7738 | 7738 | 6500
500155827 | CLB-MP-HAUL-DT5455-ELCTHV-HVBLW | Main High Voltage Blower | 7738 | 7738 | 6500
500155826 | CLB-MP-HAUL-DT5455-ELCTHV-HVALT | High Voltage Alternator | 7738 | 7738 | 6500
500155825 | CLB-MP-HAUL-DT5455-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 7738 | 7738 | 6500
500155824 | CLB-MP-HAUL-DT5455-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 7738 | 7738 | 6500
500155823 | CLB-MP-HAUL-DT5455-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 7738 | 7738 | 6500
500155822 | CLB-MP-HAUL-DT5455-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 7738 | 7738 | 6500
500155821 | CLB-MP-HAUL-DT5455-BRKSYS-BRVTR | Brake Treadle Valve | 7738 | 7738 | 6500
500155820 | CLB-MP-HAUL-DT5455-BRKSYS-BRVRL | Brake Dual Relay Valves | 7738 | 7738 | 6500
500155819 | CLB-MP-HAUL-DT5455-BRKSYS-BRVLV | Brake & Steering Manifold | 7738 | 7738 | 6500
500155818 | CLB-MP-HAUL-DT5455-BRKSYS-BRSTV | Brake & Steering Valve | 7738 | 7738 | 6500
500155817 | CLB-MP-HAUL-DT5455-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 7738 | 7738 | 6500
500155816 | CLB-MP-HAUL-DT5455-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 7738 | 7738 | 6500
500155815 | CLB-MP-HAUL-DT5455-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 7738 | 7738 | 6500
500155814 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC | Accumulator Brake Supply Rr | 7738 | 7738 | 6500
500155813 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 7738 | 7738 | 6500
500155812 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC | Accumulator Brake Supply Fr | 7738 | 7738 | 6500
500155811 | CLB-MP-HAUL-DT5455-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 7738 | 7738 | 6500
500155810 | CLB-MP-HAUL-DT5455 | DT5455 Liebherr T264 OHT | 7738 | 7738 | 6500
500164704 | CLB-MP-HAUL-DT5454-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8172 | 8172 | 6500
500164703 | CLB-MP-HAUL-DT5454-STRSYS-STACC-SACLH | Accumulator Steering DS | 8172 | 8172 | 6500
500164702 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8172 | 8172 | 6500
500164701 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8172 | 8172 | 6500
500164700 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8172 | 8172 | 6500
500164699 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8172 | 8172 | 6500
500155809 | CLB-MP-HAUL-DT5454-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8172 | 8172 | 6500
500155808 | CLB-MP-HAUL-DT5454-STRUCT-TRAYS | Tray | 8172 | 8172 | 6500
500155807 | CLB-MP-HAUL-DT5454-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8172 | 8172 | 6500
500155806 | CLB-MP-HAUL-DT5454-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8172 | 8172 | 6500
500155805 | CLB-MP-HAUL-DT5454-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8172 | 8172 | 6500
500155804 | CLB-MP-HAUL-DT5454-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8172 | 8172 | 6500
500155803 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-SEATS | Operators Seat | 8172 | 8172 | 6500
500155802 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8172 | 8172 | 6500
500155801 | CLB-MP-HAUL-DT5454-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8172 | 8172 | 6500
500155800 | CLB-MP-HAUL-DT5454-STRUCT-CABIN | Operators Cabin | 8172 | 8172 | 6500
500155799 | CLB-MP-HAUL-DT5454-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8172 | 8172 | 6500
500155798 | CLB-MP-HAUL-DT5454-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8172 | 8172 | 6500
500155797 | CLB-MP-HAUL-DT5454-STRSYS-STVLV | Valve Flow Amplifier | 8172 | 8172 | 6500
500155796 | CLB-MP-HAUL-DT5454-STRSYS-STRIA | Steering Idler Arm | 8172 | 8172 | 6500
500155795 | CLB-MP-HAUL-DT5454-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8172 | 8172 | 6500
500155794 | CLB-MP-HAUL-DT5454-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8172 | 8172 | 6500
500155793 | CLB-MP-HAUL-DT5454-STRSYS-STLTR | Steering Linkages & Tie Rods | 8172 | 8172 | 6500
500155792 | CLB-MP-HAUL-DT5454-STRSYS-STCNT | Steering Control Unit | 8172 | 8172 | 6500
500155791 | CLB-MP-HAUL-DT5454-STRSYS-STACC | Accumulator Steering RHS | 8172 | 8172 | 6500
500155790 | CLB-MP-HAUL-DT5454-STRSYS-STACC | Accumulator Steering LHS | 8172 | 8172 | 6500
500155789 | CLB-MP-HAUL-DT5454-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8172 | 8172 | 6500
500155788 | CLB-MP-HAUL-DT5454-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8172 | 8172 | 6500
500155787 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8172 | 8172 | 6500
500155786 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8172 | 8172 | 6500
500155785 | CLB-MP-HAUL-DT5454-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8172 | 8172 | 6500
500155784 | CLB-MP-HAUL-DT5454-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8172 | 8172 | 6500
500155783 | CLB-MP-HAUL-DT5454-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8172 | 8172 | 6500
500155782 | CLB-MP-HAUL-DT5454-HYDSYS-HOMAN | Hoist Manifold | 8172 | 8172 | 6500
500155781 | CLB-MP-HAUL-DT5454-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8172 | 8172 | 6500
500155780 | CLB-MP-HAUL-DT5454-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8172 | 8172 | 6500
500155779 | CLB-MP-HAUL-DT5454-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8172 | 8172 | 6500
500155778 | CLB-MP-HAUL-DT5454-HYDSYS-GROCL | Gear Oil Cooler | 8172 | 8172 | 6500
500155777 | CLB-MP-HAUL-DT5454-GRSYST-ALBPP | Auto Lube Pump | 8172 | 8172 | 6500
500155776 | CLB-MP-HAUL-DT5454-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8172 | 8172 | 6500
500155775 | CLB-MP-HAUL-DT5454-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8172 | 8172 | 6500
500155774 | CLB-MP-HAUL-DT5454-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8172 | 8172 | 6500
500155773 | CLB-MP-HAUL-DT5454-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8172 | 8172 | 6500
500155772 | CLB-MP-HAUL-DT5454-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8172 | 8172 | 6500
500155771 | CLB-MP-HAUL-DT5454-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8172 | 8172 | 6500
500155770 | CLB-MP-HAUL-DT5454-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8172 | 8172 | 6500
500155769 | CLB-MP-HAUL-DT5454-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8172 | 8172 | 6500
500155768 | CLB-MP-HAUL-DT5454-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8172 | 8172 | 6500
500155767 | CLB-MP-HAUL-DT5454-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8172 | 8172 | 6500
500155766 | CLB-MP-HAUL-DT5454-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8172 | 8172 | 6500
500155765 | CLB-MP-HAUL-DT5454-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8172 | 8172 | 6500
500155764 | CLB-MP-HAUL-DT5454-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8172 | 8172 | 6500
500155763 | CLB-MP-HAUL-DT5454-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8172 | 8172 | 6500
500155762 | CLB-MP-HAUL-DT5454-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8172 | 8172 | 6500
500155761 | CLB-MP-HAUL-DT5454-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8172 | 8172 | 6500
500155760 | CLB-MP-HAUL-DT5454-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8172 | 8172 | 6500
500155759 | CLB-MP-HAUL-DT5454-ENGINE-INTEX-AFTER | Aftercooler Engine | 8172 | 8172 | 6500
500155758 | CLB-MP-HAUL-DT5454-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8172 | 8172 | 6500
500155757 | CLB-MP-HAUL-DT5454-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8172 | 8172 | 6500
500155756 | CLB-MP-HAUL-DT5454-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8172 | 8172 | 6500
500155755 | CLB-MP-HAUL-DT5454-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8172 | 8172 | 6500
500155754 | CLB-MP-HAUL-DT5454-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8172 | 8172 | 6500
500155753 | CLB-MP-HAUL-DT5454-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8172 | 8172 | 6500
500155752 | CLB-MP-HAUL-DT5454-ENGINE-COSYS-HTWPP | Engine Water Pump | 8172 | 8172 | 6500
500155751 | CLB-MP-HAUL-DT5454-ENGINE-COSYS-COFAN | Fan Cooling System | 8172 | 8172 | 6500
500155750 | CLB-MP-HAUL-DT5454-ENGINE | Engine Assembly Cummins QSK60 | 8172 | 8172 | 6500
500155749 | CLB-MP-HAUL-DT5454-ELCTLV-START-STMUP | Starter Motor Upper | 8172 | 8172 | 6500
500155748 | CLB-MP-HAUL-DT5454-ELCTLV-START-STMLO | Starter Motor Lower | 8172 | 8172 | 6500
500155747 | CLB-MP-HAUL-DT5454-ELCTLV-HARNS | Electrical Harness | 8172 | 8172 | 6500
500155746 | CLB-MP-HAUL-DT5454-ELCTLV-CHARG-BATTY | Batteries | 8172 | 8172 | 6500
500155745 | CLB-MP-HAUL-DT5454-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8172 | 8172 | 6500
500155744 | CLB-MP-HAUL-DT5454-ELCTHV-HVGBX-HVRES | Grid Resistors | 8172 | 8172 | 6500
500155743 | CLB-MP-HAUL-DT5454-ELCTHV-HVGBM | Grid Box Blower Motor | 8172 | 8172 | 6500
500155742 | CLB-MP-HAUL-DT5454-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8172 | 8172 | 6500
500155741 | CLB-MP-HAUL-DT5454-ELCTHV-HVBLW | Main High Voltage Blower | 8172 | 8172 | 6500
500155740 | CLB-MP-HAUL-DT5454-ELCTHV-HVALT | High Voltage Alternator | 8172 | 8172 | 6500
500155739 | CLB-MP-HAUL-DT5454-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8172 | 8172 | 6500
500155738 | CLB-MP-HAUL-DT5454-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8172 | 8172 | 6500
500155737 | CLB-MP-HAUL-DT5454-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8172 | 8172 | 6500
500155736 | CLB-MP-HAUL-DT5454-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8172 | 8172 | 6500
500155735 | CLB-MP-HAUL-DT5454-BRKSYS-BRVTR | Brake Treadle Valve | 8172 | 8172 | 6500
500155734 | CLB-MP-HAUL-DT5454-BRKSYS-BRVRL | Brake Dual Relay Valves | 8172 | 8172 | 6500
500155733 | CLB-MP-HAUL-DT5454-BRKSYS-BRVLV | Brake & Steering Manifold | 8172 | 8172 | 6500
500155732 | CLB-MP-HAUL-DT5454-BRKSYS-BRSTV | Brake & Steering Valve | 8172 | 8172 | 6500
500155731 | CLB-MP-HAUL-DT5454-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8172 | 8172 | 6500
500155730 | CLB-MP-HAUL-DT5454-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8172 | 8172 | 6500
500155729 | CLB-MP-HAUL-DT5454-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8172 | 8172 | 6500
500155728 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8172 | 8172 | 6500
500155727 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8172 | 8172 | 6500
500155726 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8172 | 8172 | 6500
500155725 | CLB-MP-HAUL-DT5454-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8172 | 8172 | 6500
500155724 | CLB-MP-HAUL-DT5454 | DT5454 Liebherr T264 OHT | 8172 | 8172 | 6500
500164698 | CLB-MP-HAUL-DT5453-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8172 | 8172 | 6500
500164697 | CLB-MP-HAUL-DT5453-STRSYS-STACC-SACLH | Accumulator Steering DS | 8172 | 8172 | 6500
500164696 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8172 | 8172 | 6500
500164695 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8172 | 8172 | 6500
500164694 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8172 | 8172 | 6500
500164693 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8172 | 8172 | 6500
500155688 | CLB-MP-HAUL-DT5453-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8172 | 8172 | 6500
500155687 | CLB-MP-HAUL-DT5453-STRUCT-TRAYS | Tray | 8172 | 8172 | 6500
500155686 | CLB-MP-HAUL-DT5453-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8172 | 8172 | 6500
500155685 | CLB-MP-HAUL-DT5453-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8172 | 8172 | 6500
500155684 | CLB-MP-HAUL-DT5453-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8172 | 8172 | 6500
500155683 | CLB-MP-HAUL-DT5453-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8172 | 8172 | 6500
500155682 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-SEATS | Operators Seat | 8172 | 8172 | 6500
500155681 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8172 | 8172 | 6500
500155680 | CLB-MP-HAUL-DT5453-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8172 | 8172 | 6500
500155679 | CLB-MP-HAUL-DT5453-STRUCT-CABIN | Operators Cabin | 8172 | 8172 | 6500
500155678 | CLB-MP-HAUL-DT5453-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8172 | 8172 | 6500
500155677 | CLB-MP-HAUL-DT5453-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8172 | 8172 | 6500
500155676 | CLB-MP-HAUL-DT5453-STRSYS-STVLV | Valve Flow Amplifier | 8172 | 8172 | 6500
500155675 | CLB-MP-HAUL-DT5453-STRSYS-STRIA | Steering Idler Arm | 8172 | 8172 | 6500
500155674 | CLB-MP-HAUL-DT5453-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8172 | 8172 | 6500
500155673 | CLB-MP-HAUL-DT5453-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8172 | 2397 | 6500
500155672 | CLB-MP-HAUL-DT5453-STRSYS-STLTR | Steering Linkages & Tie Rods | 8172 | 8172 | 6500
500155671 | CLB-MP-HAUL-DT5453-STRSYS-STCNT | Steering Control Unit | 8172 | 8172 | 6500
500155670 | CLB-MP-HAUL-DT5453-STRSYS-STACC | Accumulator Steering RHS | 8172 | 8172 | 6500
500155669 | CLB-MP-HAUL-DT5453-STRSYS-STACC | Accumulator Steering LHS | 8172 | 8172 | 6500
500155668 | CLB-MP-HAUL-DT5453-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8172 | 8172 | 6500
500155667 | CLB-MP-HAUL-DT5453-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8172 | 8172 | 6500
500155666 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8172 | 8172 | 6500
500155665 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8172 | 8172 | 6500
500155664 | CLB-MP-HAUL-DT5453-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8172 | 8172 | 6500
500155663 | CLB-MP-HAUL-DT5453-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8172 | 8172 | 6500
500155662 | CLB-MP-HAUL-DT5453-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8172 | 8172 | 6500
500155661 | CLB-MP-HAUL-DT5453-HYDSYS-HOMAN | Hoist Manifold | 8172 | 8172 | 6500
500155660 | CLB-MP-HAUL-DT5453-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8172 | 8172 | 6500
500155659 | CLB-MP-HAUL-DT5453-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8172 | 8172 | 6500
500155658 | CLB-MP-HAUL-DT5453-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8172 | 8172 | 6500
500155657 | CLB-MP-HAUL-DT5453-HYDSYS-GROCL | Gear Oil Cooler | 8172 | 8172 | 6500
500155656 | CLB-MP-HAUL-DT5453-GRSYST-ALBPP | Auto Lube Pump | 8172 | 8172 | 6500
500155655 | CLB-MP-HAUL-DT5453-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8172 | 8172 | 6500
500155654 | CLB-MP-HAUL-DT5453-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8172 | 8172 | 6500
500155653 | CLB-MP-HAUL-DT5453-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8172 | 8172 | 6500
500155652 | CLB-MP-HAUL-DT5453-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8172 | 8172 | 6500
500155651 | CLB-MP-HAUL-DT5453-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8172 | 8172 | 6500
500155650 | CLB-MP-HAUL-DT5453-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8172 | 8172 | 6500
500155649 | CLB-MP-HAUL-DT5453-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8172 | 8172 | 6500
500155648 | CLB-MP-HAUL-DT5453-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8172 | 8172 | 6500
500155647 | CLB-MP-HAUL-DT5453-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8172 | 8172 | 6500
500155646 | CLB-MP-HAUL-DT5453-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8172 | 8172 | 6500
500155645 | CLB-MP-HAUL-DT5453-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8172 | 8172 | 6500
500155644 | CLB-MP-HAUL-DT5453-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8172 | 8172 | 6500
500155643 | CLB-MP-HAUL-DT5453-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8172 | 8172 | 6500
500155642 | CLB-MP-HAUL-DT5453-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8172 | 8172 | 6500
500155641 | CLB-MP-HAUL-DT5453-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8172 | 8172 | 6500
500155640 | CLB-MP-HAUL-DT5453-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8172 | 8172 | 6500
500155639 | CLB-MP-HAUL-DT5453-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8172 | 8172 | 6500
500155638 | CLB-MP-HAUL-DT5453-ENGINE-INTEX-AFTER | Aftercooler Engine | 8172 | 8172 | 6500
500155637 | CLB-MP-HAUL-DT5453-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8172 | 8172 | 6500
500155636 | CLB-MP-HAUL-DT5453-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8172 | 8172 | 6500
500155635 | CLB-MP-HAUL-DT5453-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8172 | 8172 | 6500
500155634 | CLB-MP-HAUL-DT5453-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8172 | 8172 | 6500
500155633 | CLB-MP-HAUL-DT5453-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8172 | 8172 | 6500
500155632 | CLB-MP-HAUL-DT5453-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8172 | 8172 | 6500
500155631 | CLB-MP-HAUL-DT5453-ENGINE-COSYS-HTWPP | Engine Water Pump | 8172 | 8172 | 6500
500155630 | CLB-MP-HAUL-DT5453-ENGINE-COSYS-COFAN | Fan Cooling System | 8172 | 8172 | 6500
500155629 | CLB-MP-HAUL-DT5453-ENGINE | Engine Assembly Cummins QSK60 | 8172 | 8172 | 6500
500155628 | CLB-MP-HAUL-DT5453-ELCTLV-START-STMUP | Starter Motor Upper | 8172 | 8172 | 6500
500155627 | CLB-MP-HAUL-DT5453-ELCTLV-START-STMLO | Starter Motor Lower | 8172 | 8172 | 6500
500155626 | CLB-MP-HAUL-DT5453-ELCTLV-HARNS | Electrical Harness | 8172 | 8172 | 6500
500155625 | CLB-MP-HAUL-DT5453-ELCTLV-CHARG-BATTY | Batteries | 8172 | 8172 | 6500
500155624 | CLB-MP-HAUL-DT5453-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8172 | 8172 | 6500
500155623 | CLB-MP-HAUL-DT5453-ELCTHV-HVGBX-HVRES | Grid Resistors | 8172 | 8172 | 6500
500155622 | CLB-MP-HAUL-DT5453-ELCTHV-HVGBM | Grid Box Blower Motor | 8172 | 8172 | 6500
500155621 | CLB-MP-HAUL-DT5453-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8172 | 8172 | 6500
500155620 | CLB-MP-HAUL-DT5453-ELCTHV-HVBLW | Main High Voltage Blower | 8172 | 8172 | 6500
500155619 | CLB-MP-HAUL-DT5453-ELCTHV-HVALT | High Voltage Alternator | 8172 | 8172 | 6500
500155618 | CLB-MP-HAUL-DT5453-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8172 | 8172 | 6500
500155617 | CLB-MP-HAUL-DT5453-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8172 | 8172 | 6500
500155616 | CLB-MP-HAUL-DT5453-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8172 | 8172 | 6500
500155615 | CLB-MP-HAUL-DT5453-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8172 | 8172 | 6500
500155614 | CLB-MP-HAUL-DT5453-BRKSYS-BRVTR | Brake Treadle Valve | 8172 | 8172 | 6500
500155613 | CLB-MP-HAUL-DT5453-BRKSYS-BRVRL | Brake Dual Relay Valves | 8172 | 8172 | 6500
500155612 | CLB-MP-HAUL-DT5453-BRKSYS-BRVLV | Brake & Steering Manifold | 8172 | 8172 | 6500
500155611 | CLB-MP-HAUL-DT5453-BRKSYS-BRSTV | Brake & Steering Valve | 8172 | 8172 | 6500
500155610 | CLB-MP-HAUL-DT5453-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8172 | 8172 | 6500
500155609 | CLB-MP-HAUL-DT5453-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8172 | 8172 | 6500
500155608 | CLB-MP-HAUL-DT5453-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8172 | 8172 | 6500
500155607 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8172 | 8172 | 6500
500155606 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8172 | 8172 | 6500
500155605 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8172 | 8172 | 6500
500155604 | CLB-MP-HAUL-DT5453-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8172 | 8172 | 6500
500155603 | CLB-MP-HAUL-DT5453 | DT5453 Liebherr T264 OHT | 8172 | 8172 | 6500
500164692 | CLB-MP-HAUL-DT5452-STRSYS-STACC-SACRH | Accumulator Steering ODS | 5722 | 5722 | 6500
500164691 | CLB-MP-HAUL-DT5452-STRSYS-STACC-SACLH | Accumulator Steering DS | 5722 | 5722 | 6500
500164690 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 5722 | 5722 | 6500
500164689 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 5722 | 5722 | 6500
500164688 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 5722 | 5722 | 6500
500164687 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 5722 | 5722 | 6500
500155582 | CLB-MP-HAUL-DT5452-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 5722 | 5722 | 6500
500155581 | CLB-MP-HAUL-DT5452-STRUCT-TRAYS | Tray | 5722 | 5722 | 6500
500155580 | CLB-MP-HAUL-DT5452-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 5722 | 5722 | 6500
500155579 | CLB-MP-HAUL-DT5452-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 5722 | 5722 | 6500
500155578 | CLB-MP-HAUL-DT5452-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 5722 | 5722 | 6500
500155577 | CLB-MP-HAUL-DT5452-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 5722 | 5722 | 6500
500155576 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-SEATS | Operators Seat | 5722 | 5722 | 6500
500155575 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 5722 | 5722 | 6500
500155574 | CLB-MP-HAUL-DT5452-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 5722 | 5722 | 6500
500155573 | CLB-MP-HAUL-DT5452-STRUCT-CABIN | Operators Cabin | 5722 | 5722 | 6500
500155572 | CLB-MP-HAUL-DT5452-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 5722 | 5722 | 6500
500155571 | CLB-MP-HAUL-DT5452-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 5722 | 5722 | 6500
500155570 | CLB-MP-HAUL-DT5452-STRSYS-STVLV | Valve Flow Amplifier | 5722 | 5722 | 6500
500155569 | CLB-MP-HAUL-DT5452-STRSYS-STRIA | Steering Idler Arm | 5722 | 5722 | 6500
500155568 | CLB-MP-HAUL-DT5452-STRSYS-STRCY-STCYR | Steering Cylinder RH | 5722 | 5722 | 6500
500155567 | CLB-MP-HAUL-DT5452-STRSYS-STRCY-STCYL | Steering Cylinder LH | 5722 | 5722 | 6500
500155566 | CLB-MP-HAUL-DT5452-STRSYS-STLTR | Steering Linkages & Tie Rods | 5722 | 5722 | 6500
500155565 | CLB-MP-HAUL-DT5452-STRSYS-STCNT | Steering Control Unit | 5722 | 5722 | 6500
500155564 | CLB-MP-HAUL-DT5452-STRSYS-STACC | Accumulator Steering RHS | 5722 | 5722 | 6500
500155563 | CLB-MP-HAUL-DT5452-STRSYS-STACC | Accumulator Steering LHS | 5722 | 5722 | 6500
500155562 | CLB-MP-HAUL-DT5452-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 5722 | 5722 | 6500
500155561 | CLB-MP-HAUL-DT5452-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 5722 | 5722 | 6500
500155560 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 5722 | 5722 | 6500
500155559 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 5722 | 5722 | 6500
500155558 | CLB-MP-HAUL-DT5452-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 5722 | 5722 | 6500
500155557 | CLB-MP-HAUL-DT5452-HYDSYS-HYDOC | Hydraulic Oil Cooler | 5722 | 5722 | 6500
500155556 | CLB-MP-HAUL-DT5452-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 5722 | 5722 | 6500
500155555 | CLB-MP-HAUL-DT5452-HYDSYS-HOMAN | Hoist Manifold | 5722 | 5722 | 6500
500155554 | CLB-MP-HAUL-DT5452-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 5722 | 5722 | 6500
500155553 | CLB-MP-HAUL-DT5452-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 5722 | 5722 | 6500
500155552 | CLB-MP-HAUL-DT5452-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 5722 | 5722 | 6500
500155551 | CLB-MP-HAUL-DT5452-HYDSYS-GROCL | Gear Oil Cooler | 5722 | 5722 | 6500
500155550 | CLB-MP-HAUL-DT5452-GRSYST-ALBPP | Auto Lube Pump | 5722 | 5722 | 6500
500155549 | CLB-MP-HAUL-DT5452-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 5722 | 5722 | 6500
500155548 | CLB-MP-HAUL-DT5452-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 5722 | 5722 | 6500
500155547 | CLB-MP-HAUL-DT5452-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 5722 | 5722 | 6500
500155546 | CLB-MP-HAUL-DT5452-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 5722 | 5722 | 6500
500155545 | CLB-MP-HAUL-DT5452-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 5722 | 5722 | 6500
500155544 | CLB-MP-HAUL-DT5452-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 5722 | 5722 | 6500
500155543 | CLB-MP-HAUL-DT5452-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 5722 | 5722 | 6500
500155542 | CLB-MP-HAUL-DT5452-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 5722 | 5722 | 6500
500155541 | CLB-MP-HAUL-DT5452-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 5722 | 5722 | 6500
500155540 | CLB-MP-HAUL-DT5452-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 5722 | 5722 | 6500
500155539 | CLB-MP-HAUL-DT5452-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 5722 | 5722 | 6500
500155538 | CLB-MP-HAUL-DT5452-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 5722 | 5722 | 6500
500155537 | CLB-MP-HAUL-DT5452-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 5722 | 5722 | 6500
500155536 | CLB-MP-HAUL-DT5452-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 5722 | 5722 | 6500
500155535 | CLB-MP-HAUL-DT5452-ENGINE-INTEX-TBORF | Turbocharger RH Front | 5722 | 5722 | 6500
500155534 | CLB-MP-HAUL-DT5452-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 5722 | 5722 | 6500
500155533 | CLB-MP-HAUL-DT5452-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 5722 | 5722 | 6500
500155532 | CLB-MP-HAUL-DT5452-ENGINE-INTEX-AFTER | Aftercooler Engine | 5722 | 5722 | 6500
500155531 | CLB-MP-HAUL-DT5452-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 5722 | 5722 | 6500
500155530 | CLB-MP-HAUL-DT5452-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 5722 | 5722 | 6500
500155529 | CLB-MP-HAUL-DT5452-ENGINE-FUSYS-FUINJ | Fuel Injectors | 5722 | 5722 | 6500
500155528 | CLB-MP-HAUL-DT5452-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 5722 | 5722 | 6500
500155527 | CLB-MP-HAUL-DT5452-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 5722 | 5722 | 6500
500155526 | CLB-MP-HAUL-DT5452-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 5722 | 5722 | 6500
500155525 | CLB-MP-HAUL-DT5452-ENGINE-COSYS-HTWPP | Engine Water Pump | 5722 | 5722 | 6500
500155524 | CLB-MP-HAUL-DT5452-ENGINE-COSYS-COFAN | Fan Cooling System | 5722 | 5722 | 6500
500155523 | CLB-MP-HAUL-DT5452-ENGINE | Engine Assembly Cummins QSK60 | 5722 | 5722 | 6500
500155522 | CLB-MP-HAUL-DT5452-ELCTLV-START-STMUP | Starter Motor Upper | 5722 | 5722 | 6500
500155521 | CLB-MP-HAUL-DT5452-ELCTLV-START-STMLO | Starter Motor Lower | 5722 | 5722 | 6500
500155520 | CLB-MP-HAUL-DT5452-ELCTLV-HARNS | Electrical Harness | 5722 | 5722 | 6500
500155519 | CLB-MP-HAUL-DT5452-ELCTLV-CHARG-BATTY | Batteries | 5722 | 5722 | 6500
500155518 | CLB-MP-HAUL-DT5452-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 5722 | 5722 | 6500
500155517 | CLB-MP-HAUL-DT5452-ELCTHV-HVGBX-HVRES | Grid Resistors | 5722 | 5722 | 6500
500155516 | CLB-MP-HAUL-DT5452-ELCTHV-HVGBM | Grid Box Blower Motor | 5722 | 5722 | 6500
500155515 | CLB-MP-HAUL-DT5452-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 5722 | 5722 | 6500
500155514 | CLB-MP-HAUL-DT5452-ELCTHV-HVBLW | Main High Voltage Blower | 5722 | 5722 | 6500
500155513 | CLB-MP-HAUL-DT5452-ELCTHV-HVALT | High Voltage Alternator | 5722 | 5722 | 6500
500155512 | CLB-MP-HAUL-DT5452-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 5722 | 5722 | 6500
500155511 | CLB-MP-HAUL-DT5452-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 5722 | 5722 | 6500
500155510 | CLB-MP-HAUL-DT5452-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 5722 | 5722 | 6500
500155509 | CLB-MP-HAUL-DT5452-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 5722 | 5722 | 6500
500155508 | CLB-MP-HAUL-DT5452-BRKSYS-BRVTR | Brake Treadle Valve | 5722 | 5722 | 6500
500155507 | CLB-MP-HAUL-DT5452-BRKSYS-BRVRL | Brake Dual Relay Valves | 5722 | 5722 | 6500
500155506 | CLB-MP-HAUL-DT5452-BRKSYS-BRVLV | Brake & Steering Manifold | 5722 | 5722 | 6500
500155505 | CLB-MP-HAUL-DT5452-BRKSYS-BRSTV | Brake & Steering Valve | 5722 | 5722 | 6500
500155504 | CLB-MP-HAUL-DT5452-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 5722 | 5722 | 6500
500155503 | CLB-MP-HAUL-DT5452-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 5722 | 5722 | 6500
500155502 | CLB-MP-HAUL-DT5452-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 5722 | 5722 | 6500
500155501 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC | Accumulator Brake Supply Rr | 5722 | 5722 | 6500
500155500 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 5722 | 5722 | 6500
500155499 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC | Accumulator Brake Supply Fr | 5722 | 5722 | 6500
500155498 | CLB-MP-HAUL-DT5452-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 5722 | 5722 | 6500
500155497 | CLB-MP-HAUL-DT5452 | DT5452 Liebherr T264 OHT | 5722 | 5722 | 6500
500164686 | CLB-MP-HAUL-DT5451-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8297 | 8297 | 6500
500164685 | CLB-MP-HAUL-DT5451-STRSYS-STACC-SACLH | Accumulator Steering DS | 8297 | 8297 | 6500
500164684 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8297 | 8297 | 6500
500164683 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8297 | 8297 | 6500
500164682 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8297 | 8297 | 6500
500164681 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8297 | 8297 | 6500
500155409 | CLB-MP-HAUL-DT5451-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8297 | 8297 | 6500
500155408 | CLB-MP-HAUL-DT5451-STRUCT-TRAYS | Tray | 8297 | 8297 | 6500
500155407 | CLB-MP-HAUL-DT5451-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8297 | 8297 | 6500
500155406 | CLB-MP-HAUL-DT5451-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8297 | 8297 | 6500
500155405 | CLB-MP-HAUL-DT5451-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8297 | 705 | 6500
500155404 | CLB-MP-HAUL-DT5451-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8297 | 8297 | 6500
500155403 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-SEATS | Operators Seat | 8297 | 8297 | 6500
500155402 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8297 | 8297 | 6500
500155401 | CLB-MP-HAUL-DT5451-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8297 | 8297 | 6500
500155400 | CLB-MP-HAUL-DT5451-STRUCT-CABIN | Operators Cabin | 8297 | 8297 | 6500
500155399 | CLB-MP-HAUL-DT5451-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8297 | 8297 | 6500
500155398 | CLB-MP-HAUL-DT5451-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8297 | 8297 | 6500
500155397 | CLB-MP-HAUL-DT5451-STRSYS-STVLV | Valve Flow Amplifier | 8297 | 8297 | 6500
500155396 | CLB-MP-HAUL-DT5451-STRSYS-STRIA | Steering Idler Arm | 8297 | 8297 | 6500
500155395 | CLB-MP-HAUL-DT5451-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8297 | 8297 | 6500
500155394 | CLB-MP-HAUL-DT5451-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8297 | 8297 | 6500
500155393 | CLB-MP-HAUL-DT5451-STRSYS-STLTR | Steering Linkages & Tie Rods | 8297 | 8297 | 6500
500155392 | CLB-MP-HAUL-DT5451-STRSYS-STCNT | Steering Control Unit | 8297 | 8297 | 6500
500155391 | CLB-MP-HAUL-DT5451-STRSYS-STACC | Accumulator Steering RHS | 8297 | 8297 | 6500
500155390 | CLB-MP-HAUL-DT5451-STRSYS-STACC | Accumulator Steering LHS | 8297 | 8297 | 6500
500155389 | CLB-MP-HAUL-DT5451-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8297 | 8297 | 6500
500155388 | CLB-MP-HAUL-DT5451-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8297 | 8297 | 6500
500155387 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8297 | 8297 | 6500
500155386 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8297 | 8297 | 6500
500155385 | CLB-MP-HAUL-DT5451-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8297 | 8297 | 6500
500155384 | CLB-MP-HAUL-DT5451-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8297 | 8297 | 6500
500155383 | CLB-MP-HAUL-DT5451-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8297 | 8297 | 6500
500155382 | CLB-MP-HAUL-DT5451-HYDSYS-HOMAN | Hoist Manifold | 8297 | 8297 | 6500
500155381 | CLB-MP-HAUL-DT5451-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8297 | 8297 | 6500
500155380 | CLB-MP-HAUL-DT5451-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8297 | 8297 | 6500
500155379 | CLB-MP-HAUL-DT5451-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8297 | 8297 | 6500
500155378 | CLB-MP-HAUL-DT5451-HYDSYS-GROCL | Gear Oil Cooler | 8297 | 8297 | 6500
500155377 | CLB-MP-HAUL-DT5451-GRSYST-ALBPP | Auto Lube Pump | 8297 | 8297 | 6500
500155376 | CLB-MP-HAUL-DT5451-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8297 | 8297 | 6500
500155375 | CLB-MP-HAUL-DT5451-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8297 | 8297 | 6500
500155374 | CLB-MP-HAUL-DT5451-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8297 | 8297 | 6500
500155373 | CLB-MP-HAUL-DT5451-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8297 | 8297 | 6500
500155372 | CLB-MP-HAUL-DT5451-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8297 | 8297 | 6500
500155371 | CLB-MP-HAUL-DT5451-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8297 | 8297 | 6500
500155370 | CLB-MP-HAUL-DT5451-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8297 | 8297 | 6500
500155369 | CLB-MP-HAUL-DT5451-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8297 | 8297 | 6500
500155368 | CLB-MP-HAUL-DT5451-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8297 | 8297 | 6500
500155367 | CLB-MP-HAUL-DT5451-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8297 | 8297 | 6500
500155366 | CLB-MP-HAUL-DT5451-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8297 | 8297 | 6500
500155365 | CLB-MP-HAUL-DT5451-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8297 | 8297 | 6500
500155364 | CLB-MP-HAUL-DT5451-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8297 | 8297 | 6500
500155363 | CLB-MP-HAUL-DT5451-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8297 | 8297 | 6500
500155362 | CLB-MP-HAUL-DT5451-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8297 | 8297 | 6500
500155361 | CLB-MP-HAUL-DT5451-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8297 | 8297 | 6500
500155360 | CLB-MP-HAUL-DT5451-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8297 | 8297 | 6500
500155359 | CLB-MP-HAUL-DT5451-ENGINE-INTEX-AFTER | Aftercooler Engine | 8297 | 8297 | 6500
500155358 | CLB-MP-HAUL-DT5451-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8297 | 8297 | 6500
500155357 | CLB-MP-HAUL-DT5451-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8297 | 8297 | 6500
500155356 | CLB-MP-HAUL-DT5451-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8297 | 8297 | 6500
500155355 | CLB-MP-HAUL-DT5451-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8297 | 8297 | 6500
500155354 | CLB-MP-HAUL-DT5451-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8297 | 8297 | 6500
500155353 | CLB-MP-HAUL-DT5451-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8297 | 8297 | 6500
500155352 | CLB-MP-HAUL-DT5451-ENGINE-COSYS-HTWPP | Engine Water Pump | 8297 | 8297 | 6500
500155351 | CLB-MP-HAUL-DT5451-ENGINE-COSYS-COFAN | Fan Cooling System | 8297 | 8297 | 6500
500155350 | CLB-MP-HAUL-DT5451-ENGINE | Engine Assembly Cummins QSK60 | 8297 | 8297 | 6500
500155349 | CLB-MP-HAUL-DT5451-ELCTLV-START-STMUP | Starter Motor Upper | 8297 | 8297 | 6500
500155348 | CLB-MP-HAUL-DT5451-ELCTLV-START-STMLO | Starter Motor Lower | 8297 | 8297 | 6500
500155347 | CLB-MP-HAUL-DT5451-ELCTLV-HARNS | Electrical Harness | 8297 | 8297 | 6500
500155346 | CLB-MP-HAUL-DT5451-ELCTLV-CHARG-BATTY | Batteries | 8297 | 8297 | 6500
500155345 | CLB-MP-HAUL-DT5451-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8297 | 8297 | 6500
500155344 | CLB-MP-HAUL-DT5451-ELCTHV-HVGBX-HVRES | Grid Resistors | 8297 | 8297 | 6500
500155343 | CLB-MP-HAUL-DT5451-ELCTHV-HVGBM | Grid Box Blower Motor | 8297 | 8297 | 6500
500155342 | CLB-MP-HAUL-DT5451-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8297 | 8297 | 6500
500155341 | CLB-MP-HAUL-DT5451-ELCTHV-HVBLW | Main High Voltage Blower | 8297 | 8297 | 6500
500155340 | CLB-MP-HAUL-DT5451-ELCTHV-HVALT | High Voltage Alternator | 8297 | 8297 | 6500
500155339 | CLB-MP-HAUL-DT5451-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8297 | 8297 | 6500
500155338 | CLB-MP-HAUL-DT5451-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8297 | 8297 | 6500
500155337 | CLB-MP-HAUL-DT5451-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8297 | 8297 | 6500
500155336 | CLB-MP-HAUL-DT5451-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8297 | 8297 | 6500
500155335 | CLB-MP-HAUL-DT5451-BRKSYS-BRVTR | Brake Treadle Valve | 8297 | 8297 | 6500
500155334 | CLB-MP-HAUL-DT5451-BRKSYS-BRVRL | Brake Dual Relay Valves | 8297 | 8297 | 6500
500155333 | CLB-MP-HAUL-DT5451-BRKSYS-BRVLV | Brake & Steering Manifold | 8297 | 8297 | 6500
500155332 | CLB-MP-HAUL-DT5451-BRKSYS-BRSTV | Brake & Steering Valve | 8297 | 8297 | 6500
500155331 | CLB-MP-HAUL-DT5451-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8297 | 8297 | 6500
500155330 | CLB-MP-HAUL-DT5451-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8297 | 8297 | 6500
500155329 | CLB-MP-HAUL-DT5451-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8297 | 8297 | 6500
500155328 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8297 | 8297 | 6500
500155327 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8297 | 8297 | 6500
500155326 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8297 | 8297 | 6500
500155325 | CLB-MP-HAUL-DT5451-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8297 | 8297 | 6500
500155324 | CLB-MP-HAUL-DT5451 | DT5451 Liebherr T264 OHT | 8297 | 8297 | 6500
500164680 | CLB-MP-HAUL-DT5450-STRSYS-STACC-SACRH | Accumulator Steering ODS | 7211 | 7211 | 6500
500164679 | CLB-MP-HAUL-DT5450-STRSYS-STACC-SACLH | Accumulator Steering DS | 7211 | 7211 | 6500
500164678 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 7211 | 7211 | 6500
500164677 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 7211 | 7211 | 6500
500164676 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 7211 | 7211 | 6500
500164675 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 7211 | 7211 | 6500
500155496 | CLB-MP-HAUL-DT5450-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 7211 | 7211 | 6500
500155495 | CLB-MP-HAUL-DT5450-STRUCT-TRAYS | Tray | 7211 | 7211 | 6500
500155494 | CLB-MP-HAUL-DT5450-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 7211 | 7211 | 6500
500155493 | CLB-MP-HAUL-DT5450-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 7211 | 7211 | 6500
500155492 | CLB-MP-HAUL-DT5450-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 7211 | 7211 | 6500
500155491 | CLB-MP-HAUL-DT5450-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 7211 | 7211 | 6500
500155490 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-SEATS | Operators Seat | 7211 | 7211 | 6500
500155489 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 7211 | 7211 | 6500
500155488 | CLB-MP-HAUL-DT5450-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 7211 | 7211 | 6500
500155487 | CLB-MP-HAUL-DT5450-STRUCT-CABIN | Operators Cabin | 7211 | 7211 | 6500
500155486 | CLB-MP-HAUL-DT5450-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 7211 | 7211 | 6500
500155485 | CLB-MP-HAUL-DT5450-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 7211 | 7211 | 6500
500155484 | CLB-MP-HAUL-DT5450-STRSYS-STVLV | Valve Flow Amplifier | 7211 | 7211 | 6500
500155483 | CLB-MP-HAUL-DT5450-STRSYS-STRIA | Steering Idler Arm | 7211 | 7211 | 6500
500155482 | CLB-MP-HAUL-DT5450-STRSYS-STRCY-STCYR | Steering Cylinder RH | 7211 | 7211 | 6500
500155481 | CLB-MP-HAUL-DT5450-STRSYS-STRCY-STCYL | Steering Cylinder LH | 7211 | 7211 | 6500
500155480 | CLB-MP-HAUL-DT5450-STRSYS-STLTR | Steering Linkages & Tie Rods | 7211 | 7211 | 6500
500155479 | CLB-MP-HAUL-DT5450-STRSYS-STCNT | Steering Control Unit | 7211 | 7211 | 6500
500155478 | CLB-MP-HAUL-DT5450-STRSYS-STACC | Accumulator Steering RHS | 7211 | 7211 | 6500
500155477 | CLB-MP-HAUL-DT5450-STRSYS-STACC | Accumulator Steering LHS | 7211 | 7211 | 6500
500155476 | CLB-MP-HAUL-DT5450-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 7211 | 7211 | 6500
500155475 | CLB-MP-HAUL-DT5450-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 7211 | 7211 | 6500
500155474 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 7211 | 7211 | 6500
500155473 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 7211 | 7211 | 6500
500155472 | CLB-MP-HAUL-DT5450-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 7211 | 7211 | 6500
500155471 | CLB-MP-HAUL-DT5450-HYDSYS-HYDOC | Hydraulic Oil Cooler | 7211 | 7211 | 6500
500155470 | CLB-MP-HAUL-DT5450-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 7211 | 7211 | 6500
500155469 | CLB-MP-HAUL-DT5450-HYDSYS-HOMAN | Hoist Manifold | 7211 | 7211 | 6500
500155468 | CLB-MP-HAUL-DT5450-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 7211 | 7211 | 6500
500155467 | CLB-MP-HAUL-DT5450-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 7211 | 7211 | 6500
500155466 | CLB-MP-HAUL-DT5450-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 7211 | 7211 | 6500
500155465 | CLB-MP-HAUL-DT5450-HYDSYS-GROCL | Gear Oil Cooler | 7211 | 7211 | 6500
500155464 | CLB-MP-HAUL-DT5450-GRSYST-ALBPP | Auto Lube Pump | 7211 | 7211 | 6500
500155463 | CLB-MP-HAUL-DT5450-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 7211 | 7211 | 6500
500155462 | CLB-MP-HAUL-DT5450-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 7211 | 7211 | 6500
500155461 | CLB-MP-HAUL-DT5450-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 7211 | 7211 | 6500
500155460 | CLB-MP-HAUL-DT5450-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 7211 | 7211 | 6500
500155459 | CLB-MP-HAUL-DT5450-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 7211 | 7211 | 6500
500155458 | CLB-MP-HAUL-DT5450-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 7211 | 7211 | 6500
500155457 | CLB-MP-HAUL-DT5450-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 7211 | 7211 | 6500
500155456 | CLB-MP-HAUL-DT5450-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 7211 | 7211 | 6500
500155455 | CLB-MP-HAUL-DT5450-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 7211 | 7211 | 6500
500155454 | CLB-MP-HAUL-DT5450-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 7211 | 7211 | 6500
500155453 | CLB-MP-HAUL-DT5450-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 7211 | 7211 | 6500
500155452 | CLB-MP-HAUL-DT5450-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 7211 | 7211 | 6500
500155451 | CLB-MP-HAUL-DT5450-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 7211 | 7211 | 6500
500155450 | CLB-MP-HAUL-DT5450-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 7211 | 7211 | 6500
500155449 | CLB-MP-HAUL-DT5450-ENGINE-INTEX-TBORF | Turbocharger RH Front | 7211 | 7211 | 6500
500155448 | CLB-MP-HAUL-DT5450-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 7211 | 7211 | 6500
500155447 | CLB-MP-HAUL-DT5450-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 7211 | 7211 | 6500
500155446 | CLB-MP-HAUL-DT5450-ENGINE-INTEX-AFTER | Aftercooler Engine | 7211 | 7211 | 6500
500155445 | CLB-MP-HAUL-DT5450-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 7211 | 7211 | 6500
500155444 | CLB-MP-HAUL-DT5450-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 7211 | 7211 | 6500
500155443 | CLB-MP-HAUL-DT5450-ENGINE-FUSYS-FUINJ | Fuel Injectors | 7211 | 7211 | 6500
500155442 | CLB-MP-HAUL-DT5450-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 7211 | 7211 | 6500
500155441 | CLB-MP-HAUL-DT5450-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 7211 | 7211 | 6500
500155440 | CLB-MP-HAUL-DT5450-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 7211 | 7211 | 6500
500155439 | CLB-MP-HAUL-DT5450-ENGINE-COSYS-HTWPP | Engine Water Pump | 7211 | 7211 | 6500
500155438 | CLB-MP-HAUL-DT5450-ENGINE-COSYS-COFAN | Fan Cooling System | 7211 | 7211 | 6500
500155437 | CLB-MP-HAUL-DT5450-ENGINE | Engine Assembly Cummins QSK60 | 7211 | 7211 | 6500
500155436 | CLB-MP-HAUL-DT5450-ELCTLV-START-STMUP | Starter Motor Upper | 7211 | 7211 | 6500
500155435 | CLB-MP-HAUL-DT5450-ELCTLV-START-STMLO | Starter Motor Lower | 7211 | 7211 | 6500
500155434 | CLB-MP-HAUL-DT5450-ELCTLV-HARNS | Electrical Harness | 7211 | 7211 | 6500
500155433 | CLB-MP-HAUL-DT5450-ELCTLV-CHARG-BATTY | Batteries | 7211 | 7211 | 6500
500155432 | CLB-MP-HAUL-DT5450-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 7211 | 7211 | 6500
500155431 | CLB-MP-HAUL-DT5450-ELCTHV-HVGBX-HVRES | Grid Resistors | 7211 | 7211 | 6500
500155430 | CLB-MP-HAUL-DT5450-ELCTHV-HVGBM | Grid Box Blower Motor | 7211 | 7211 | 6500
500155429 | CLB-MP-HAUL-DT5450-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 7211 | 7211 | 6500
500155428 | CLB-MP-HAUL-DT5450-ELCTHV-HVBLW | Main High Voltage Blower | 7211 | 7211 | 6500
500155427 | CLB-MP-HAUL-DT5450-ELCTHV-HVALT | High Voltage Alternator | 7211 | 7211 | 6500
500155426 | CLB-MP-HAUL-DT5450-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 7211 | 7211 | 6500
500155425 | CLB-MP-HAUL-DT5450-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 7211 | 7211 | 6500
500155424 | CLB-MP-HAUL-DT5450-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 7211 | 7211 | 6500
500155423 | CLB-MP-HAUL-DT5450-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 7211 | 7211 | 6500
500155422 | CLB-MP-HAUL-DT5450-BRKSYS-BRVTR | Brake Treadle Valve | 7211 | 7211 | 6500
500155421 | CLB-MP-HAUL-DT5450-BRKSYS-BRVRL | Brake Dual Relay Valves | 7211 | 7211 | 6500
500155420 | CLB-MP-HAUL-DT5450-BRKSYS-BRVLV | Brake & Steering Manifold | 7211 | 7211 | 6500
500155419 | CLB-MP-HAUL-DT5450-BRKSYS-BRSTV | Brake & Steering Valve | 7211 | 7211 | 6500
500155418 | CLB-MP-HAUL-DT5450-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 7211 | 7211 | 6500
500155417 | CLB-MP-HAUL-DT5450-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 7211 | 7211 | 6500
500155416 | CLB-MP-HAUL-DT5450-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 7211 | 7211 | 6500
500155415 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC | Accumulator Brake Supply Rr | 7211 | 7211 | 6500
500155414 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 7211 | 7211 | 6500
500155413 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC | Accumulator Brake Supply Fr | 7211 | 7211 | 6500
500155142 | CLB-MP-HAUL-DT5450-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 7211 | 7211 | 6500
500155141 | CLB-MP-HAUL-DT5450 | DT5450 Liebherr T264 OHT | 7211 | 7211 | 6500
500164674 | CLB-MP-HAUL-DT5449-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8483 | 8483 | 6500
500164673 | CLB-MP-HAUL-DT5449-STRSYS-STACC-SACLH | Accumulator Steering DS | 8483 | 8483 | 6500
500164672 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8483 | 8483 | 6500
500164671 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8483 | 8483 | 6500
500164670 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8483 | 8483 | 6500
500164669 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8483 | 8483 | 6500
500155136 | CLB-MP-HAUL-DT5449-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8483 | 8483 | 6500
500155135 | CLB-MP-HAUL-DT5449-STRUCT-TRAYS | Tray | 8483 | 8483 | 6500
500155134 | CLB-MP-HAUL-DT5449-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8483 | 8483 | 6500
500155133 | CLB-MP-HAUL-DT5449-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8483 | 8483 | 6500
500155132 | CLB-MP-HAUL-DT5449-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8483 | 8483 | 6500
500155131 | CLB-MP-HAUL-DT5449-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8483 | 8483 | 6500
500155130 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-SEATS | Operators Seat | 8483 | 8483 | 6500
500155129 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8483 | 8483 | 6500
500155128 | CLB-MP-HAUL-DT5449-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8483 | 8483 | 6500
500155127 | CLB-MP-HAUL-DT5449-STRUCT-CABIN | Operators Cabin | 8483 | 8483 | 6500
500155126 | CLB-MP-HAUL-DT5449-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8483 | 8483 | 6500
500155125 | CLB-MP-HAUL-DT5449-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8483 | 8483 | 6500
500155124 | CLB-MP-HAUL-DT5449-STRSYS-STVLV | Valve Flow Amplifier | 8483 | 8483 | 6500
500155123 | CLB-MP-HAUL-DT5449-STRSYS-STRIA | Steering Idler Arm | 8483 | 8483 | 6500
500155122 | CLB-MP-HAUL-DT5449-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8483 | 8483 | 6500
500155121 | CLB-MP-HAUL-DT5449-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8483 | 8483 | 6500
500155120 | CLB-MP-HAUL-DT5449-STRSYS-STLTR | Steering Linkages & Tie Rods | 8483 | 8483 | 6500
500155119 | CLB-MP-HAUL-DT5449-STRSYS-STCNT | Steering Control Unit | 8483 | 8483 | 6500
500155118 | CLB-MP-HAUL-DT5449-STRSYS-STACC | Accumulator Steering RHS | 8483 | 8483 | 6500
500155117 | CLB-MP-HAUL-DT5449-STRSYS-STACC | Accumulator Steering LHS | 8483 | 8483 | 6500
500155116 | CLB-MP-HAUL-DT5449-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8483 | 8483 | 6500
500155115 | CLB-MP-HAUL-DT5449-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8483 | 8483 | 6500
500155114 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8483 | 8483 | 6500
500155113 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8483 | 8483 | 6500
500155112 | CLB-MP-HAUL-DT5449-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8483 | 8483 | 6500
500155111 | CLB-MP-HAUL-DT5449-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8483 | 8483 | 6500
500155110 | CLB-MP-HAUL-DT5449-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8483 | 8483 | 6500
500155109 | CLB-MP-HAUL-DT5449-HYDSYS-HOMAN | Hoist Manifold | 8483 | 8483 | 6500
500155108 | CLB-MP-HAUL-DT5449-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8483 | 8483 | 6500
500155107 | CLB-MP-HAUL-DT5449-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8483 | 8483 | 6500
500155106 | CLB-MP-HAUL-DT5449-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8483 | 8483 | 6500
500155105 | CLB-MP-HAUL-DT5449-HYDSYS-GROCL | Gear Oil Cooler | 8483 | 8483 | 6500
500155104 | CLB-MP-HAUL-DT5449-GRSYST-ALBPP | Auto Lube Pump | 8483 | 8483 | 6500
500155103 | CLB-MP-HAUL-DT5449-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8483 | 8483 | 6500
500155102 | CLB-MP-HAUL-DT5449-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8483 | 8483 | 6500
500155101 | CLB-MP-HAUL-DT5449-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8483 | 8483 | 6500
500155100 | CLB-MP-HAUL-DT5449-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8483 | 8483 | 6500
500155099 | CLB-MP-HAUL-DT5449-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8483 | 8483 | 6500
500155098 | CLB-MP-HAUL-DT5449-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8483 | 8483 | 6500
500155097 | CLB-MP-HAUL-DT5449-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8483 | 8483 | 6500
500155096 | CLB-MP-HAUL-DT5449-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8483 | 8483 | 6500
500155095 | CLB-MP-HAUL-DT5449-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8483 | 8483 | 6500
500155094 | CLB-MP-HAUL-DT5449-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8483 | 8483 | 6500
500155093 | CLB-MP-HAUL-DT5449-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8483 | 8483 | 6500
500155092 | CLB-MP-HAUL-DT5449-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8483 | 8483 | 6500
500155091 | CLB-MP-HAUL-DT5449-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8483 | 8483 | 6500
500155090 | CLB-MP-HAUL-DT5449-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8483 | 8483 | 6500
500155089 | CLB-MP-HAUL-DT5449-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8483 | 8483 | 6500
500155088 | CLB-MP-HAUL-DT5449-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8483 | 8483 | 6500
500155087 | CLB-MP-HAUL-DT5449-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8483 | 8483 | 6500
500155086 | CLB-MP-HAUL-DT5449-ENGINE-INTEX-AFTER | Aftercooler Engine | 8483 | 8483 | 6500
500155085 | CLB-MP-HAUL-DT5449-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8483 | 8483 | 6500
500155084 | CLB-MP-HAUL-DT5449-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8483 | 8483 | 6500
500155083 | CLB-MP-HAUL-DT5449-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8483 | 8483 | 6500
500155082 | CLB-MP-HAUL-DT5449-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8483 | 8483 | 6500
500155081 | CLB-MP-HAUL-DT5449-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8483 | 8483 | 6500
500155080 | CLB-MP-HAUL-DT5449-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8483 | 8483 | 6500
500155079 | CLB-MP-HAUL-DT5449-ENGINE-COSYS-HTWPP | Engine Water Pump | 8483 | 8483 | 6500
500155078 | CLB-MP-HAUL-DT5449-ENGINE-COSYS-COFAN | Fan Cooling System | 8483 | 8483 | 6500
500155077 | CLB-MP-HAUL-DT5449-ENGINE | Engine Assembly Cummins QSK60 | 8483 | 8483 | 6500
500155076 | CLB-MP-HAUL-DT5449-ELCTLV-START-STMUP | Starter Motor Upper | 8483 | 8483 | 6500
500155075 | CLB-MP-HAUL-DT5449-ELCTLV-START-STMLO | Starter Motor Lower | 8483 | 8483 | 6500
500155074 | CLB-MP-HAUL-DT5449-ELCTLV-HARNS | Electrical Harness | 8483 | 8483 | 6500
500155073 | CLB-MP-HAUL-DT5449-ELCTLV-CHARG-BATTY | Batteries | 8483 | 8483 | 6500
500155072 | CLB-MP-HAUL-DT5449-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8483 | 8483 | 6500
500155071 | CLB-MP-HAUL-DT5449-ELCTHV-HVGBX-HVRES | Grid Resistors | 8483 | 8483 | 6500
500155070 | CLB-MP-HAUL-DT5449-ELCTHV-HVGBM | Grid Box Blower Motor | 8483 | 8483 | 6500
500155069 | CLB-MP-HAUL-DT5449-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8483 | 8483 | 6500
500155068 | CLB-MP-HAUL-DT5449-ELCTHV-HVBLW | Main High Voltage Blower | 8483 | 8483 | 6500
500155067 | CLB-MP-HAUL-DT5449-ELCTHV-HVALT | High Voltage Alternator | 8483 | 8483 | 6500
500155066 | CLB-MP-HAUL-DT5449-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8483 | 8483 | 6500
500155065 | CLB-MP-HAUL-DT5449-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8483 | 8483 | 6500
500155064 | CLB-MP-HAUL-DT5449-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8483 | 8483 | 6500
500155063 | CLB-MP-HAUL-DT5449-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8483 | 8483 | 6500
500155062 | CLB-MP-HAUL-DT5449-BRKSYS-BRVTR | Brake Treadle Valve | 8483 | 8483 | 6500
500155061 | CLB-MP-HAUL-DT5449-BRKSYS-BRVRL | Brake Dual Relay Valves | 8483 | 8483 | 6500
500155060 | CLB-MP-HAUL-DT5449-BRKSYS-BRVLV | Brake & Steering Manifold | 8483 | 8483 | 6500
500155059 | CLB-MP-HAUL-DT5449-BRKSYS-BRSTV | Brake & Steering Valve | 8483 | 8483 | 6500
500155058 | CLB-MP-HAUL-DT5449-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8483 | 8483 | 6500
500155057 | CLB-MP-HAUL-DT5449-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8483 | 8483 | 6500
500155056 | CLB-MP-HAUL-DT5449-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8483 | 8483 | 6500
500155055 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8483 | 8483 | 6500
500155054 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8483 | 8483 | 6500
500155053 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8483 | 8483 | 6500
500155052 | CLB-MP-HAUL-DT5449-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8483 | 8483 | 6500
500155051 | CLB-MP-HAUL-DT5449 | DT5449 Liebherr T264 OHT | 8483 | 8483 | 6500
500164668 | CLB-MP-HAUL-DT5448-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8548 | 8548 | 6500
500164667 | CLB-MP-HAUL-DT5448-STRSYS-STACC-SACLH | Accumulator Steering DS | 8548 | 8548 | 6500
500164666 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8548 | 8548 | 6500
500164665 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8548 | 8548 | 6500
500164664 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8548 | 8548 | 6500
500164663 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8548 | 8548 | 6500
500155050 | CLB-MP-HAUL-DT5448-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8548 | 8548 | 6500
500155049 | CLB-MP-HAUL-DT5448-STRUCT-TRAYS | Tray | 8548 | 8548 | 6500
500155048 | CLB-MP-HAUL-DT5448-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8548 | 8548 | 6500
500155047 | CLB-MP-HAUL-DT5448-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8548 | 8548 | 6500
500155046 | CLB-MP-HAUL-DT5448-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8548 | 8548 | 6500
500155045 | CLB-MP-HAUL-DT5448-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8548 | 8548 | 6500
500155044 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-SEATS | Operators Seat | 8548 | 8548 | 6500
500155043 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8548 | 8548 | 6500
500155042 | CLB-MP-HAUL-DT5448-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8548 | 8548 | 6500
500155041 | CLB-MP-HAUL-DT5448-STRUCT-CABIN | Operators Cabin | 8548 | 8548 | 6500
500155040 | CLB-MP-HAUL-DT5448-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8548 | 8548 | 6500
500155039 | CLB-MP-HAUL-DT5448-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8548 | 8548 | 6500
500155038 | CLB-MP-HAUL-DT5448-STRSYS-STVLV | Valve Flow Amplifier | 8548 | 8548 | 6500
500155037 | CLB-MP-HAUL-DT5448-STRSYS-STRIA | Steering Idler Arm | 8548 | 8548 | 6500
500155036 | CLB-MP-HAUL-DT5448-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8548 | 2653 | 6500
500155035 | CLB-MP-HAUL-DT5448-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8548 | 8548 | 6500
500155034 | CLB-MP-HAUL-DT5448-STRSYS-STLTR | Steering Linkages & Tie Rods | 8548 | 8548 | 6500
500155033 | CLB-MP-HAUL-DT5448-STRSYS-STCNT | Steering Control Unit | 8548 | 8548 | 6500
500155032 | CLB-MP-HAUL-DT5448-STRSYS-STACC | Accumulator Steering RHS | 8548 | 8548 | 6500
500155031 | CLB-MP-HAUL-DT5448-STRSYS-STACC | Accumulator Steering LHS | 8548 | 8548 | 6500
500155030 | CLB-MP-HAUL-DT5448-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8548 | 8548 | 6500
500155029 | CLB-MP-HAUL-DT5448-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8548 | 8548 | 6500
500155028 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8548 | 8548 | 6500
500155027 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8548 | 8548 | 6500
500155026 | CLB-MP-HAUL-DT5448-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8548 | 8548 | 6500
500155025 | CLB-MP-HAUL-DT5448-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8548 | 8548 | 6500
500155024 | CLB-MP-HAUL-DT5448-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8548 | 8548 | 6500
500155023 | CLB-MP-HAUL-DT5448-HYDSYS-HOMAN | Hoist Manifold | 8548 | 8548 | 6500
500155022 | CLB-MP-HAUL-DT5448-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8548 | 6492 | 6500
500155021 | CLB-MP-HAUL-DT5448-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8548 | 8548 | 6500
500155020 | CLB-MP-HAUL-DT5448-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8548 | 8548 | 6500
500155019 | CLB-MP-HAUL-DT5448-HYDSYS-GROCL | Gear Oil Cooler | 8548 | 8548 | 6500
500155018 | CLB-MP-HAUL-DT5448-GRSYST-ALBPP | Auto Lube Pump | 8548 | 8548 | 6500
500155017 | CLB-MP-HAUL-DT5448-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8548 | 8548 | 6500
500155016 | CLB-MP-HAUL-DT5448-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8548 | 8548 | 6500
500155015 | CLB-MP-HAUL-DT5448-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8548 | 8548 | 6500
500155014 | CLB-MP-HAUL-DT5448-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8548 | 8548 | 6500
500155013 | CLB-MP-HAUL-DT5448-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8548 | 8548 | 6500
500155012 | CLB-MP-HAUL-DT5448-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8548 | 8548 | 6500
500155011 | CLB-MP-HAUL-DT5448-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8548 | 8548 | 6500
500155010 | CLB-MP-HAUL-DT5448-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8548 | 8548 | 6500
500155009 | CLB-MP-HAUL-DT5448-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8548 | 8548 | 6500
500155008 | CLB-MP-HAUL-DT5448-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8548 | 8548 | 6500
500155007 | CLB-MP-HAUL-DT5448-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8548 | 8548 | 6500
500155006 | CLB-MP-HAUL-DT5448-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8548 | 8548 | 6500
500155005 | CLB-MP-HAUL-DT5448-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8548 | 8548 | 6500
500155004 | CLB-MP-HAUL-DT5448-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8548 | 8548 | 6500
500155003 | CLB-MP-HAUL-DT5448-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8548 | 8548 | 6500
500155002 | CLB-MP-HAUL-DT5448-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8548 | 8548 | 6500
500155001 | CLB-MP-HAUL-DT5448-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8548 | 8548 | 6500
500155000 | CLB-MP-HAUL-DT5448-ENGINE-INTEX-AFTER | Aftercooler Engine | 8548 | 8548 | 6500
500154999 | CLB-MP-HAUL-DT5448-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8548 | 8548 | 6500
500154998 | CLB-MP-HAUL-DT5448-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8548 | 8548 | 6500
500154997 | CLB-MP-HAUL-DT5448-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8548 | 8548 | 6500
500154996 | CLB-MP-HAUL-DT5448-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8548 | 8548 | 6500
500154995 | CLB-MP-HAUL-DT5448-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8548 | 8548 | 6500
500154994 | CLB-MP-HAUL-DT5448-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8548 | 8548 | 6500
500154993 | CLB-MP-HAUL-DT5448-ENGINE-COSYS-HTWPP | Engine Water Pump | 8548 | 8548 | 6500
500154992 | CLB-MP-HAUL-DT5448-ENGINE-COSYS-COFAN | Fan Cooling System | 8548 | 8548 | 6500
500154991 | CLB-MP-HAUL-DT5448-ENGINE | Engine Assembly Cummins QSK60 | 8548 | 8548 | 6500
500154990 | CLB-MP-HAUL-DT5448-ELCTLV-START-STMUP | Starter Motor Upper | 8548 | 8548 | 6500
500154989 | CLB-MP-HAUL-DT5448-ELCTLV-START-STMLO | Starter Motor Lower | 8548 | 8548 | 6500
500154988 | CLB-MP-HAUL-DT5448-ELCTLV-HARNS | Electrical Harness | 8548 | 8548 | 6500
500154987 | CLB-MP-HAUL-DT5448-ELCTLV-CHARG-BATTY | Batteries | 8548 | 8548 | 6500
500154986 | CLB-MP-HAUL-DT5448-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8548 | 8548 | 6500
500154985 | CLB-MP-HAUL-DT5448-ELCTHV-HVGBX-HVRES | Grid Resistors | 8548 | 8548 | 6500
500154984 | CLB-MP-HAUL-DT5448-ELCTHV-HVGBM | Grid Box Blower Motor | 8548 | 8548 | 6500
500154983 | CLB-MP-HAUL-DT5448-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8548 | 8548 | 6500
500154982 | CLB-MP-HAUL-DT5448-ELCTHV-HVBLW | Main High Voltage Blower | 8548 | 8548 | 6500
500154981 | CLB-MP-HAUL-DT5448-ELCTHV-HVALT | High Voltage Alternator | 8548 | 8548 | 6500
500154980 | CLB-MP-HAUL-DT5448-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8548 | 8548 | 6500
500154979 | CLB-MP-HAUL-DT5448-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8548 | 8548 | 6500
500154978 | CLB-MP-HAUL-DT5448-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8548 | 8548 | 6500
500154977 | CLB-MP-HAUL-DT5448-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8548 | 8548 | 6500
500154976 | CLB-MP-HAUL-DT5448-BRKSYS-BRVTR | Brake Treadle Valve | 8548 | 8548 | 6500
500154975 | CLB-MP-HAUL-DT5448-BRKSYS-BRVRL | Brake Dual Relay Valves | 8548 | 8548 | 6500
500154974 | CLB-MP-HAUL-DT5448-BRKSYS-BRVLV | Brake & Steering Manifold | 8548 | 8548 | 6500
500154973 | CLB-MP-HAUL-DT5448-BRKSYS-BRSTV | Brake & Steering Valve | 8548 | 8548 | 6500
500154952 | CLB-MP-HAUL-DT5448-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8548 | 8548 | 6500
500154951 | CLB-MP-HAUL-DT5448-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8548 | 8548 | 6500
500154950 | CLB-MP-HAUL-DT5448-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8548 | 8548 | 6500
500154949 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8548 | 8548 | 6500
500154948 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8548 | 8548 | 6500
500154947 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8548 | 8548 | 6500
500154946 | CLB-MP-HAUL-DT5448-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8548 | 8548 | 6500
500154945 | CLB-MP-HAUL-DT5448 | DT5448 Liebherr T264 OHT | 8548 | 8548 | 6500
500164662 | CLB-MP-HAUL-DT5447-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8949 | 8949 | 6500
500164661 | CLB-MP-HAUL-DT5447-STRSYS-STACC-SACLH | Accumulator Steering DS | 8949 | 8949 | 6500
500164660 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8949 | 8949 | 6500
500164659 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8949 | 8949 | 6500
500164658 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8949 | 8949 | 6500
500164657 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8949 | 8949 | 6500
500154307 | CLB-MP-HAUL-DT5447-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8949 | 8949 | 6500
500154306 | CLB-MP-HAUL-DT5447-STRUCT-TRAYS | Tray | 8949 | 8949 | 6500
500154305 | CLB-MP-HAUL-DT5447-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8949 | 8949 | 6500
500154304 | CLB-MP-HAUL-DT5447-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8949 | 8949 | 6500
500154303 | CLB-MP-HAUL-DT5447-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8949 | 8949 | 6500
500154302 | CLB-MP-HAUL-DT5447-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8949 | 8949 | 6500
500154301 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-SEATS | Operators Seat | 8949 | 8949 | 6500
500154300 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8949 | 8949 | 6500
500154299 | CLB-MP-HAUL-DT5447-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8949 | 8949 | 6500
500154298 | CLB-MP-HAUL-DT5447-STRUCT-CABIN | Operators Cabin | 8949 | 8949 | 6500
500154297 | CLB-MP-HAUL-DT5447-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8949 | 8949 | 6500
500154296 | CLB-MP-HAUL-DT5447-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8949 | 8949 | 6500
500154295 | CLB-MP-HAUL-DT5447-STRSYS-STVLV | Valve Flow Amplifier | 8949 | 8949 | 6500
500154294 | CLB-MP-HAUL-DT5447-STRSYS-STRIA | Steering Idler Arm | 8949 | 8949 | 6500
500154293 | CLB-MP-HAUL-DT5447-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8949 | 5706 | 6500
500154292 | CLB-MP-HAUL-DT5447-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8949 | 8949 | 6500
500154291 | CLB-MP-HAUL-DT5447-STRSYS-STLTR | Steering Linkages & Tie Rods | 8949 | 8949 | 6500
500154290 | CLB-MP-HAUL-DT5447-STRSYS-STCNT | Steering Control Unit | 8949 | 8949 | 6500
500154289 | CLB-MP-HAUL-DT5447-STRSYS-STACC | Accumulator Steering RHS | 8949 | 8949 | 6500
500154288 | CLB-MP-HAUL-DT5447-STRSYS-STACC | Accumulator Steering LHS | 8949 | 8949 | 6500
500154287 | CLB-MP-HAUL-DT5447-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8949 | 8949 | 6500
500154286 | CLB-MP-HAUL-DT5447-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8949 | 8949 | 6500
500154285 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8949 | 8949 | 6500
500154284 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8949 | 8949 | 6500
500154283 | CLB-MP-HAUL-DT5447-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8949 | 8949 | 6500
500154282 | CLB-MP-HAUL-DT5447-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8949 | 8949 | 6500
500154281 | CLB-MP-HAUL-DT5447-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8949 | 8949 | 6500
500154280 | CLB-MP-HAUL-DT5447-HYDSYS-HOMAN | Hoist Manifold | 8949 | 8949 | 6500
500154279 | CLB-MP-HAUL-DT5447-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8949 | 8949 | 6500
500154278 | CLB-MP-HAUL-DT5447-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8949 | 8949 | 6500
500154277 | CLB-MP-HAUL-DT5447-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8949 | 8949 | 6500
500154276 | CLB-MP-HAUL-DT5447-HYDSYS-GROCL | Gear Oil Cooler | 8949 | 8949 | 6500
500154275 | CLB-MP-HAUL-DT5447-GRSYST-ALBPP | Auto Lube Pump | 8949 | 8949 | 6500
500154274 | CLB-MP-HAUL-DT5447-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8949 | 8949 | 6500
500154273 | CLB-MP-HAUL-DT5447-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8949 | 8949 | 6500
500154272 | CLB-MP-HAUL-DT5447-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8949 | 8949 | 6500
500154271 | CLB-MP-HAUL-DT5447-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8949 | 8949 | 6500
500154270 | CLB-MP-HAUL-DT5447-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8949 | 8949 | 6500
500154269 | CLB-MP-HAUL-DT5447-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8949 | 8949 | 6500
500154268 | CLB-MP-HAUL-DT5447-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8949 | 8949 | 6500
500154267 | CLB-MP-HAUL-DT5447-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8949 | 8949 | 6500
500154266 | CLB-MP-HAUL-DT5447-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8949 | 8949 | 6500
500154265 | CLB-MP-HAUL-DT5447-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8949 | 8949 | 6500
500154264 | CLB-MP-HAUL-DT5447-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8949 | 8949 | 6500
500154263 | CLB-MP-HAUL-DT5447-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8949 | 8949 | 6500
500154262 | CLB-MP-HAUL-DT5447-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8949 | 8949 | 6500
500154261 | CLB-MP-HAUL-DT5447-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8949 | 8949 | 6500
500154260 | CLB-MP-HAUL-DT5447-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8949 | 8949 | 6500
500154259 | CLB-MP-HAUL-DT5447-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8949 | 8949 | 6500
500154258 | CLB-MP-HAUL-DT5447-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8949 | 8949 | 6500
500154257 | CLB-MP-HAUL-DT5447-ENGINE-INTEX-AFTER | Aftercooler Engine | 8949 | 8949 | 6500
500154256 | CLB-MP-HAUL-DT5447-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8949 | 8949 | 6500
500154255 | CLB-MP-HAUL-DT5447-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8949 | 8949 | 6500
500154254 | CLB-MP-HAUL-DT5447-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8949 | 8949 | 6500
500154253 | CLB-MP-HAUL-DT5447-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8949 | 8949 | 6500
500154252 | CLB-MP-HAUL-DT5447-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8949 | 8949 | 6500
500154251 | CLB-MP-HAUL-DT5447-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8949 | 8949 | 6500
500154250 | CLB-MP-HAUL-DT5447-ENGINE-COSYS-HTWPP | Engine Water Pump | 8949 | 8949 | 6500
500154249 | CLB-MP-HAUL-DT5447-ENGINE-COSYS-COFAN | Fan Cooling System | 8949 | 8949 | 6500
500154248 | CLB-MP-HAUL-DT5447-ENGINE | Engine Assembly Cummins QSK60 | 8949 | 8949 | 6500
500154247 | CLB-MP-HAUL-DT5447-ELCTLV-START-STMUP | Starter Motor Upper | 8949 | 8949 | 6500
500154246 | CLB-MP-HAUL-DT5447-ELCTLV-START-STMLO | Starter Motor Lower | 8949 | 8949 | 6500
500154245 | CLB-MP-HAUL-DT5447-ELCTLV-HARNS | Electrical Harness | 8949 | 8949 | 6500
500154244 | CLB-MP-HAUL-DT5447-ELCTLV-CHARG-BATTY | Batteries | 8949 | 8949 | 6500
500154243 | CLB-MP-HAUL-DT5447-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8949 | 8949 | 6500
500154242 | CLB-MP-HAUL-DT5447-ELCTHV-HVGBX-HVRES | Grid Resistors | 8949 | 8949 | 6500
500154241 | CLB-MP-HAUL-DT5447-ELCTHV-HVGBM | Grid Box Blower Motor | 8949 | 8949 | 6500
500154240 | CLB-MP-HAUL-DT5447-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8949 | 8949 | 6500
500154239 | CLB-MP-HAUL-DT5447-ELCTHV-HVBLW | Main High Voltage Blower | 8949 | 8949 | 6500
500154238 | CLB-MP-HAUL-DT5447-ELCTHV-HVALT | High Voltage Alternator | 8949 | 8949 | 6500
500154237 | CLB-MP-HAUL-DT5447-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8949 | 8949 | 6500
500154236 | CLB-MP-HAUL-DT5447-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8949 | 8949 | 6500
500154235 | CLB-MP-HAUL-DT5447-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8949 | 8949 | 6500
500154234 | CLB-MP-HAUL-DT5447-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8949 | 8949 | 6500
500154233 | CLB-MP-HAUL-DT5447-BRKSYS-BRVTR | Brake Treadle Valve | 8949 | 8949 | 6500
500154232 | CLB-MP-HAUL-DT5447-BRKSYS-BRVRL | Brake Dual Relay Valves | 8949 | 8949 | 6500
500154231 | CLB-MP-HAUL-DT5447-BRKSYS-BRVLV | Brake & Steering Manifold | 8949 | 8949 | 6500
500154230 | CLB-MP-HAUL-DT5447-BRKSYS-BRSTV | Brake & Steering Valve | 8949 | 8949 | 6500
500154229 | CLB-MP-HAUL-DT5447-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8949 | 8949 | 6500
500154228 | CLB-MP-HAUL-DT5447-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8949 | 8949 | 6500
500154227 | CLB-MP-HAUL-DT5447-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8949 | 8949 | 6500
500154226 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8949 | 8949 | 6500
500154225 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8949 | 8949 | 6500
500154224 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8949 | 8949 | 6500
500154223 | CLB-MP-HAUL-DT5447-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8949 | 8949 | 6500
500153682 | CLB-MP-HAUL-DT5447 | DT5447 Liebherr T264 OHT | 8949 | 8949 | 6500
500164656 | CLB-MP-HAUL-DT5446-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8776 | 8776 | 6500
500164655 | CLB-MP-HAUL-DT5446-STRSYS-STACC-SACLH | Accumulator Steering DS | 8776 | 8776 | 6500
500164654 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8776 | 8776 | 6500
500164653 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8776 | 8776 | 6500
500164652 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8776 | 8776 | 6500
500164651 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8776 | 8776 | 6500
500154213 | CLB-MP-HAUL-DT5446-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8776 | 8776 | 6500
500154212 | CLB-MP-HAUL-DT5446-STRUCT-TRAYS | Tray | 8776 | 8776 | 6500
500154211 | CLB-MP-HAUL-DT5446-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8776 | 8776 | 6500
500154210 | CLB-MP-HAUL-DT5446-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8776 | 8776 | 6500
500154209 | CLB-MP-HAUL-DT5446-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8776 | 8776 | 6500
500154208 | CLB-MP-HAUL-DT5446-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8776 | 8776 | 6500
500154207 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-SEATS | Operators Seat | 8776 | 8776 | 6500
500154206 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8776 | 8776 | 6500
500154205 | CLB-MP-HAUL-DT5446-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8776 | 8776 | 6500
500154204 | CLB-MP-HAUL-DT5446-STRUCT-CABIN | Operators Cabin | 8776 | 8776 | 6500
500154203 | CLB-MP-HAUL-DT5446-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8776 | 8776 | 6500
500154202 | CLB-MP-HAUL-DT5446-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8776 | 8776 | 6500
500154201 | CLB-MP-HAUL-DT5446-STRSYS-STVLV | Valve Flow Amplifier | 8776 | 8776 | 6500
500154200 | CLB-MP-HAUL-DT5446-STRSYS-STRIA | Steering Idler Arm | 8776 | 8776 | 6500
500154199 | CLB-MP-HAUL-DT5446-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8776 | 8776 | 6500
500154198 | CLB-MP-HAUL-DT5446-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8776 | 2651 | 6500
500154197 | CLB-MP-HAUL-DT5446-STRSYS-STLTR | Steering Linkages & Tie Rods | 8776 | 8776 | 6500
500154196 | CLB-MP-HAUL-DT5446-STRSYS-STCNT | Steering Control Unit | 8776 | 8776 | 6500
500154195 | CLB-MP-HAUL-DT5446-STRSYS-STACC | Accumulator Steering RHS | 8776 | 8776 | 6500
500154194 | CLB-MP-HAUL-DT5446-STRSYS-STACC | Accumulator Steering LHS | 8776 | 8776 | 6500
500154193 | CLB-MP-HAUL-DT5446-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8776 | 8776 | 6500
500154192 | CLB-MP-HAUL-DT5446-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8776 | 8776 | 6500
500154191 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8776 | 8776 | 6500
500154190 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8776 | 8776 | 6500
500154189 | CLB-MP-HAUL-DT5446-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8776 | 8776 | 6500
500154188 | CLB-MP-HAUL-DT5446-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8776 | 8776 | 6500
500154187 | CLB-MP-HAUL-DT5446-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8776 | 8776 | 6500
500154186 | CLB-MP-HAUL-DT5446-HYDSYS-HOMAN | Hoist Manifold | 8776 | 8776 | 6500
500154185 | CLB-MP-HAUL-DT5446-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8776 | 8776 | 6500
500154184 | CLB-MP-HAUL-DT5446-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8776 | 8776 | 6500
500154183 | CLB-MP-HAUL-DT5446-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8776 | 8776 | 6500
500154182 | CLB-MP-HAUL-DT5446-HYDSYS-GROCL | Gear Oil Cooler | 8776 | 8776 | 6500
500154181 | CLB-MP-HAUL-DT5446-GRSYST-ALBPP | Auto Lube Pump | 8776 | 8776 | 6500
500154180 | CLB-MP-HAUL-DT5446-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8776 | 8776 | 6500
500154179 | CLB-MP-HAUL-DT5446-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8776 | 8776 | 6500
500154178 | CLB-MP-HAUL-DT5446-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8776 | 8776 | 6500
500154177 | CLB-MP-HAUL-DT5446-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8776 | 8776 | 6500
500154176 | CLB-MP-HAUL-DT5446-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8776 | 8776 | 6500
500154175 | CLB-MP-HAUL-DT5446-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8776 | 8776 | 6500
500154174 | CLB-MP-HAUL-DT5446-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8776 | 8776 | 6500
500154173 | CLB-MP-HAUL-DT5446-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8776 | 8776 | 6500
500154172 | CLB-MP-HAUL-DT5446-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8776 | 8776 | 6500
500154171 | CLB-MP-HAUL-DT5446-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8776 | 8776 | 6500
500154170 | CLB-MP-HAUL-DT5446-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8776 | 8776 | 6500
500154169 | CLB-MP-HAUL-DT5446-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8776 | 8776 | 6500
500154168 | CLB-MP-HAUL-DT5446-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8776 | 8776 | 6500
500154167 | CLB-MP-HAUL-DT5446-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8776 | 8776 | 6500
500154166 | CLB-MP-HAUL-DT5446-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8776 | 8776 | 6500
500154165 | CLB-MP-HAUL-DT5446-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8776 | 8776 | 6500
500154164 | CLB-MP-HAUL-DT5446-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8776 | 8776 | 6500
500154163 | CLB-MP-HAUL-DT5446-ENGINE-INTEX-AFTER | Aftercooler Engine | 8776 | 8776 | 6500
500154162 | CLB-MP-HAUL-DT5446-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8776 | 8776 | 6500
500154161 | CLB-MP-HAUL-DT5446-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8776 | 8776 | 6500
500154160 | CLB-MP-HAUL-DT5446-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8776 | 8776 | 6500
500154159 | CLB-MP-HAUL-DT5446-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8776 | 8776 | 6500
500154158 | CLB-MP-HAUL-DT5446-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8776 | 8776 | 6500
500154157 | CLB-MP-HAUL-DT5446-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8776 | 8776 | 6500
500154156 | CLB-MP-HAUL-DT5446-ENGINE-COSYS-HTWPP | Engine Water Pump | 8776 | 8776 | 6500
500154155 | CLB-MP-HAUL-DT5446-ENGINE-COSYS-COFAN | Fan Cooling System | 8776 | 8776 | 6500
500154154 | CLB-MP-HAUL-DT5446-ENGINE | Engine Assembly Cummins QSK60 | 8776 | 8776 | 6500
500154153 | CLB-MP-HAUL-DT5446-ELCTLV-START-STMUP | Starter Motor Upper | 8776 | 8776 | 6500
500154152 | CLB-MP-HAUL-DT5446-ELCTLV-START-STMLO | Starter Motor Lower | 8776 | 8776 | 6500
500154151 | CLB-MP-HAUL-DT5446-ELCTLV-HARNS | Electrical Harness | 8776 | 8776 | 6500
500154150 | CLB-MP-HAUL-DT5446-ELCTLV-CHARG-BATTY | Batteries | 8776 | 8776 | 6500
500154149 | CLB-MP-HAUL-DT5446-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8776 | 8776 | 6500
500154148 | CLB-MP-HAUL-DT5446-ELCTHV-HVGBX-HVRES | Grid Resistors | 8776 | 8776 | 6500
500154147 | CLB-MP-HAUL-DT5446-ELCTHV-HVGBM | Grid Box Blower Motor | 8776 | 8776 | 6500
500154146 | CLB-MP-HAUL-DT5446-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8776 | 8776 | 6500
500154145 | CLB-MP-HAUL-DT5446-ELCTHV-HVBLW | Main High Voltage Blower | 8776 | 8776 | 6500
500154144 | CLB-MP-HAUL-DT5446-ELCTHV-HVALT | High Voltage Alternator | 8776 | 8776 | 6500
500154143 | CLB-MP-HAUL-DT5446-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8776 | 8776 | 6500
500154142 | CLB-MP-HAUL-DT5446-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8776 | 8776 | 6500
500154141 | CLB-MP-HAUL-DT5446-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8776 | 8776 | 6500
500154140 | CLB-MP-HAUL-DT5446-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8776 | 8776 | 6500
500154139 | CLB-MP-HAUL-DT5446-BRKSYS-BRVTR | Brake Treadle Valve | 8776 | 8776 | 6500
500154138 | CLB-MP-HAUL-DT5446-BRKSYS-BRVRL | Brake Dual Relay Valves | 8776 | 8776 | 6500
500154137 | CLB-MP-HAUL-DT5446-BRKSYS-BRVLV | Brake & Steering Manifold | 8776 | 8776 | 6500
500154136 | CLB-MP-HAUL-DT5446-BRKSYS-BRSTV | Brake & Steering Valve | 8776 | 8776 | 6500
500154135 | CLB-MP-HAUL-DT5446-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8776 | 8776 | 6500
500154134 | CLB-MP-HAUL-DT5446-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8776 | 8776 | 6500
500154133 | CLB-MP-HAUL-DT5446-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8776 | 8776 | 6500
500154042 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8776 | 8776 | 6500
500154041 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8776 | 8776 | 6500
500154040 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8776 | 8776 | 6500
500154039 | CLB-MP-HAUL-DT5446-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8776 | 8776 | 6500
500154038 | CLB-MP-HAUL-DT5446 | DT5446 Liebherr T264 OHT | 8776 | 8776 | 6500
500164650 | CLB-MP-HAUL-DT5445-STRSYS-STACC-SACRH | Accumulator Steering ODS | 7612 | 7612 | 6500
500164649 | CLB-MP-HAUL-DT5445-STRSYS-STACC-SACLH | Accumulator Steering DS | 7612 | 7612 | 6500
500164648 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 7612 | 7612 | 6500
500164647 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 7612 | 7612 | 6500
500164646 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 7612 | 7612 | 6500
500164645 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 7612 | 7612 | 6500
500154127 | CLB-MP-HAUL-DT5445-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 7612 | 7612 | 6500
500154126 | CLB-MP-HAUL-DT5445-STRUCT-TRAYS | Tray | 7612 | 7612 | 6500
500154125 | CLB-MP-HAUL-DT5445-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 7612 | 7612 | 6500
500154124 | CLB-MP-HAUL-DT5445-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 7612 | 7612 | 6500
500154123 | CLB-MP-HAUL-DT5445-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 7612 | 7612 | 6500
500154122 | CLB-MP-HAUL-DT5445-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 7612 | 7612 | 6500
500154121 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-SEATS | Operators Seat | 7612 | 7612 | 6500
500154120 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 7612 | 7612 | 6500
500154119 | CLB-MP-HAUL-DT5445-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 7612 | 7612 | 6500
500154118 | CLB-MP-HAUL-DT5445-STRUCT-CABIN | Operators Cabin | 7612 | 7612 | 6500
500154117 | CLB-MP-HAUL-DT5445-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 7612 | 7612 | 6500
500154116 | CLB-MP-HAUL-DT5445-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 7612 | 7612 | 6500
500154115 | CLB-MP-HAUL-DT5445-STRSYS-STVLV | Valve Flow Amplifier | 7612 | 7612 | 6500
500154114 | CLB-MP-HAUL-DT5445-STRSYS-STRIA | Steering Idler Arm | 7612 | 7612 | 6500
500154113 | CLB-MP-HAUL-DT5445-STRSYS-STRCY-STCYR | Steering Cylinder RH | 7612 | 4933 | 6500
500154112 | CLB-MP-HAUL-DT5445-STRSYS-STRCY-STCYL | Steering Cylinder LH | 7612 | 7612 | 6500
500154111 | CLB-MP-HAUL-DT5445-STRSYS-STLTR | Steering Linkages & Tie Rods | 7612 | 7612 | 6500
500154110 | CLB-MP-HAUL-DT5445-STRSYS-STCNT | Steering Control Unit | 7612 | 7612 | 6500
500154109 | CLB-MP-HAUL-DT5445-STRSYS-STACC | Accumulator Steering RHS | 7612 | 7612 | 6500
500154108 | CLB-MP-HAUL-DT5445-STRSYS-STACC | Accumulator Steering LHS | 7612 | 7612 | 6500
500154107 | CLB-MP-HAUL-DT5445-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 7612 | 7612 | 6500
500154106 | CLB-MP-HAUL-DT5445-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 7612 | 7612 | 6500
500154105 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 7612 | 7612 | 6500
500154104 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 7612 | 7612 | 6500
500154103 | CLB-MP-HAUL-DT5445-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 7612 | 7612 | 6500
500154102 | CLB-MP-HAUL-DT5445-HYDSYS-HYDOC | Hydraulic Oil Cooler | 7612 | 7612 | 6500
500154101 | CLB-MP-HAUL-DT5445-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 7612 | 7612 | 6500
500154100 | CLB-MP-HAUL-DT5445-HYDSYS-HOMAN | Hoist Manifold | 7612 | 7612 | 6500
500154099 | CLB-MP-HAUL-DT5445-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 7612 | 7612 | 6500
500154098 | CLB-MP-HAUL-DT5445-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 7612 | 7612 | 6500
500154097 | CLB-MP-HAUL-DT5445-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 7612 | 7612 | 6500
500154096 | CLB-MP-HAUL-DT5445-HYDSYS-GROCL | Gear Oil Cooler | 7612 | 7612 | 6500
500154095 | CLB-MP-HAUL-DT5445-GRSYST-ALBPP | Auto Lube Pump | 7612 | 7612 | 6500
500154094 | CLB-MP-HAUL-DT5445-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 7612 | 7612 | 6500
500154093 | CLB-MP-HAUL-DT5445-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 7612 | 7612 | 6500
500154092 | CLB-MP-HAUL-DT5445-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 7612 | 7612 | 6500
500154091 | CLB-MP-HAUL-DT5445-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 7612 | 7612 | 6500
500154090 | CLB-MP-HAUL-DT5445-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 7612 | 7612 | 6500
500154089 | CLB-MP-HAUL-DT5445-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 7612 | 7612 | 6500
500154088 | CLB-MP-HAUL-DT5445-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 7612 | 7612 | 6500
500154087 | CLB-MP-HAUL-DT5445-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 7612 | 7612 | 6500
500154086 | CLB-MP-HAUL-DT5445-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 7612 | 7612 | 6500
500154085 | CLB-MP-HAUL-DT5445-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 7612 | 7612 | 6500
500154084 | CLB-MP-HAUL-DT5445-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 7612 | 7612 | 6500
500154083 | CLB-MP-HAUL-DT5445-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 7612 | 7612 | 6500
500154082 | CLB-MP-HAUL-DT5445-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 7612 | 7612 | 6500
500154081 | CLB-MP-HAUL-DT5445-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 7612 | 7612 | 6500
500154080 | CLB-MP-HAUL-DT5445-ENGINE-INTEX-TBORF | Turbocharger RH Front | 7612 | 7612 | 6500
500154079 | CLB-MP-HAUL-DT5445-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 7612 | 7612 | 6500
500154078 | CLB-MP-HAUL-DT5445-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 7612 | 7612 | 6500
500154077 | CLB-MP-HAUL-DT5445-ENGINE-INTEX-AFTER | Aftercooler Engine | 7612 | 7612 | 6500
500154076 | CLB-MP-HAUL-DT5445-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 7612 | 7612 | 6500
500154075 | CLB-MP-HAUL-DT5445-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 7612 | 7612 | 6500
500154074 | CLB-MP-HAUL-DT5445-ENGINE-FUSYS-FUINJ | Fuel Injectors | 7612 | 7612 | 6500
500154073 | CLB-MP-HAUL-DT5445-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 7612 | 7612 | 6500
500154072 | CLB-MP-HAUL-DT5445-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 7612 | 7612 | 6500
500154071 | CLB-MP-HAUL-DT5445-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 7612 | 7612 | 6500
500154070 | CLB-MP-HAUL-DT5445-ENGINE-COSYS-HTWPP | Engine Water Pump | 7612 | 7612 | 6500
500154069 | CLB-MP-HAUL-DT5445-ENGINE-COSYS-COFAN | Fan Cooling System | 7612 | 7612 | 6500
500154068 | CLB-MP-HAUL-DT5445-ENGINE | Engine Assembly Cummins QSK60 | 7612 | 7612 | 6500
500154067 | CLB-MP-HAUL-DT5445-ELCTLV-START-STMUP | Starter Motor Upper | 7612 | 7612 | 6500
500154066 | CLB-MP-HAUL-DT5445-ELCTLV-START-STMLO | Starter Motor Lower | 7612 | 7612 | 6500
500154065 | CLB-MP-HAUL-DT5445-ELCTLV-HARNS | Electrical Harness | 7612 | 7612 | 6500
500154064 | CLB-MP-HAUL-DT5445-ELCTLV-CHARG-BATTY | Batteries | 7612 | 7612 | 6500
500154063 | CLB-MP-HAUL-DT5445-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 7612 | 7612 | 6500
500154062 | CLB-MP-HAUL-DT5445-ELCTHV-HVGBX-HVRES | Grid Resistors | 7612 | 7612 | 6500
500154061 | CLB-MP-HAUL-DT5445-ELCTHV-HVGBM | Grid Box Blower Motor | 7612 | 7612 | 6500
500154060 | CLB-MP-HAUL-DT5445-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 7612 | 7612 | 6500
500154059 | CLB-MP-HAUL-DT5445-ELCTHV-HVBLW | Main High Voltage Blower | 7612 | 7612 | 6500
500154058 | CLB-MP-HAUL-DT5445-ELCTHV-HVALT | High Voltage Alternator | 7612 | 7612 | 6500
500154057 | CLB-MP-HAUL-DT5445-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 7612 | 7612 | 6500
500154056 | CLB-MP-HAUL-DT5445-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 7612 | 7612 | 6500
500154055 | CLB-MP-HAUL-DT5445-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 7612 | 7612 | 6500
500154054 | CLB-MP-HAUL-DT5445-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 7612 | 7612 | 6500
500154053 | CLB-MP-HAUL-DT5445-BRKSYS-BRVTR | Brake Treadle Valve | 7612 | 7612 | 6500
500154052 | CLB-MP-HAUL-DT5445-BRKSYS-BRVRL | Brake Dual Relay Valves | 7612 | 7612 | 6500
500154051 | CLB-MP-HAUL-DT5445-BRKSYS-BRVLV | Brake & Steering Manifold | 7612 | 7612 | 6500
500154050 | CLB-MP-HAUL-DT5445-BRKSYS-BRSTV | Brake & Steering Valve | 7612 | 7612 | 6500
500154049 | CLB-MP-HAUL-DT5445-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 7612 | 7612 | 6500
500154048 | CLB-MP-HAUL-DT5445-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 7612 | 7612 | 6500
500154047 | CLB-MP-HAUL-DT5445-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 7612 | 7612 | 6500
500154046 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC | Accumulator Brake Supply Rr | 7612 | 7612 | 6500
500154045 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 7612 | 7612 | 6500
500154044 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC | Accumulator Brake Supply Fr | 7612 | 7612 | 6500
500154043 | CLB-MP-HAUL-DT5445-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 7612 | 7612 | 6500
500154032 | CLB-MP-HAUL-DT5445 | DT5445 Liebherr T264 OHT | 7612 | 7612 | 6500
500164644 | CLB-MP-HAUL-DT5444-STRSYS-STACC-SACRH | Accumulator Steering ODS | 9285 | 9285 | 6500
500164643 | CLB-MP-HAUL-DT5444-STRSYS-STACC-SACLH | Accumulator Steering DS | 9285 | 9285 | 6500
500164642 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 9285 | 9285 | 6500
500164641 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 9285 | 9285 | 6500
500164640 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 9285 | 9285 | 6500
500164639 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 9285 | 9285 | 6500
500154031 | CLB-MP-HAUL-DT5444-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 9285 | 9285 | 6500
500154030 | CLB-MP-HAUL-DT5444-STRUCT-TRAYS | Tray | 9285 | 9285 | 6500
500154029 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 9285 | 9285 | 6500
500154028 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 9285 | 9285 | 6500
500154027 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 9285 | 9285 | 6500
500154026 | CLB-MP-HAUL-DT5444-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 9285 | 9285 | 6500
500154025 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-SEATS | Operators Seat | 9285 | 9285 | 6500
500154024 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 9285 | 9285 | 6500
500154023 | CLB-MP-HAUL-DT5444-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 9285 | 9285 | 6500
500154022 | CLB-MP-HAUL-DT5444-STRUCT-CABIN | Operators Cabin | 9285 | 9285 | 6500
500154021 | CLB-MP-HAUL-DT5444-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 9285 | 9285 | 6500
500154020 | CLB-MP-HAUL-DT5444-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 9285 | 9285 | 6500
500154019 | CLB-MP-HAUL-DT5444-STRSYS-STVLV | Valve Flow Amplifier | 9285 | 9285 | 6500
500154018 | CLB-MP-HAUL-DT5444-STRSYS-STRIA | Steering Idler Arm | 9285 | 9285 | 6500
500154017 | CLB-MP-HAUL-DT5444-STRSYS-STRCY-STCYR | Steering Cylinder RH | 9285 | 9285 | 6500
500154016 | CLB-MP-HAUL-DT5444-STRSYS-STRCY-STCYL | Steering Cylinder LH | 9285 | 9285 | 6500
500154015 | CLB-MP-HAUL-DT5444-STRSYS-STLTR | Steering Linkages & Tie Rods | 9285 | 9285 | 6500
500154014 | CLB-MP-HAUL-DT5444-STRSYS-STCNT | Steering Control Unit | 9285 | 9285 | 6500
500154013 | CLB-MP-HAUL-DT5444-STRSYS-STACC | Accumulator Steering RHS | 9285 | 9285 | 6500
500154012 | CLB-MP-HAUL-DT5444-STRSYS-STACC | Accumulator Steering LHS | 9285 | 9285 | 6500
500154011 | CLB-MP-HAUL-DT5444-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 9285 | 9285 | 6500
500154010 | CLB-MP-HAUL-DT5444-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 9285 | 9285 | 6500
500154009 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 9285 | 9285 | 6500
500154008 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 9285 | 9285 | 6500
500154007 | CLB-MP-HAUL-DT5444-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 9285 | 9285 | 6500
500154006 | CLB-MP-HAUL-DT5444-HYDSYS-HYDOC | Hydraulic Oil Cooler | 9285 | 9285 | 6500
500154005 | CLB-MP-HAUL-DT5444-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 9285 | 9285 | 6500
500154004 | CLB-MP-HAUL-DT5444-HYDSYS-HOMAN | Hoist Manifold | 9285 | 9285 | 6500
500154003 | CLB-MP-HAUL-DT5444-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 9285 | 9285 | 6500
500154002 | CLB-MP-HAUL-DT5444-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 9285 | 9285 | 6500
500154001 | CLB-MP-HAUL-DT5444-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 9285 | 9285 | 6500
500154000 | CLB-MP-HAUL-DT5444-HYDSYS-GROCL | Gear Oil Cooler | 9285 | 9285 | 6500
500153999 | CLB-MP-HAUL-DT5444-GRSYST-ALBPP | Auto Lube Pump | 9285 | 9285 | 6500
500153998 | CLB-MP-HAUL-DT5444-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 9285 | 9285 | 6500
500153997 | CLB-MP-HAUL-DT5444-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 9285 | 9285 | 6500
500153996 | CLB-MP-HAUL-DT5444-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 9285 | 9285 | 6500
500153995 | CLB-MP-HAUL-DT5444-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 9285 | 9285 | 6500
500153994 | CLB-MP-HAUL-DT5444-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 9285 | 9285 | 6500
500153993 | CLB-MP-HAUL-DT5444-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 9285 | 9285 | 6500
500153992 | CLB-MP-HAUL-DT5444-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 9285 | 9285 | 6500
500153991 | CLB-MP-HAUL-DT5444-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 9285 | 9285 | 6500
500153990 | CLB-MP-HAUL-DT5444-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 9285 | 9285 | 6500
500153989 | CLB-MP-HAUL-DT5444-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 9285 | 9285 | 6500
500153988 | CLB-MP-HAUL-DT5444-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 9285 | 9285 | 6500
500153987 | CLB-MP-HAUL-DT5444-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 9285 | 9285 | 6500
500153986 | CLB-MP-HAUL-DT5444-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 9285 | 9285 | 6500
500153985 | CLB-MP-HAUL-DT5444-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 9285 | 9285 | 6500
500153984 | CLB-MP-HAUL-DT5444-ENGINE-INTEX-TBORF | Turbocharger RH Front | 9285 | 9285 | 6500
500153983 | CLB-MP-HAUL-DT5444-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 9285 | 9285 | 6500
500153982 | CLB-MP-HAUL-DT5444-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 9285 | 9285 | 6500
500153981 | CLB-MP-HAUL-DT5444-ENGINE-INTEX-AFTER | Aftercooler Engine | 9285 | 9285 | 6500
500153980 | CLB-MP-HAUL-DT5444-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 9285 | 9285 | 6500
500153979 | CLB-MP-HAUL-DT5444-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 9285 | 9285 | 6500
500153978 | CLB-MP-HAUL-DT5444-ENGINE-FUSYS-FUINJ | Fuel Injectors | 9285 | 9285 | 6500
500153977 | CLB-MP-HAUL-DT5444-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 9285 | 9285 | 6500
500153976 | CLB-MP-HAUL-DT5444-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 9285 | 9285 | 6500
500153975 | CLB-MP-HAUL-DT5444-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 9285 | 9285 | 6500
500153974 | CLB-MP-HAUL-DT5444-ENGINE-COSYS-HTWPP | Engine Water Pump | 9285 | 9285 | 6500
500153973 | CLB-MP-HAUL-DT5444-ENGINE-COSYS-COFAN | Fan Cooling System | 9285 | 9285 | 6500
500153972 | CLB-MP-HAUL-DT5444-ENGINE | Engine Assembly Cummins QSK60 | 9285 | 9285 | 6500
500153971 | CLB-MP-HAUL-DT5444-ELCTLV-START-STMUP | Starter Motor Upper | 9285 | 9285 | 6500
500153970 | CLB-MP-HAUL-DT5444-ELCTLV-START-STMLO | Starter Motor Lower | 9285 | 9285 | 6500
500153969 | CLB-MP-HAUL-DT5444-ELCTLV-HARNS | Electrical Harness | 9285 | 9285 | 6500
500153968 | CLB-MP-HAUL-DT5444-ELCTLV-CHARG-BATTY | Batteries | 9285 | 9285 | 6500
500153967 | CLB-MP-HAUL-DT5444-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 9285 | 9285 | 6500
500153966 | CLB-MP-HAUL-DT5444-ELCTHV-HVGBX-HVRES | Grid Resistors | 9285 | 9285 | 6500
500153965 | CLB-MP-HAUL-DT5444-ELCTHV-HVGBM | Grid Box Blower Motor | 9285 | 9285 | 6500
500153964 | CLB-MP-HAUL-DT5444-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 9285 | 9285 | 6500
500153963 | CLB-MP-HAUL-DT5444-ELCTHV-HVBLW | Main High Voltage Blower | 9285 | 9285 | 6500
500153962 | CLB-MP-HAUL-DT5444-ELCTHV-HVALT | High Voltage Alternator | 9285 | 9285 | 6500
500153961 | CLB-MP-HAUL-DT5444-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 9285 | 9285 | 6500
500153960 | CLB-MP-HAUL-DT5444-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 9285 | 9285 | 6500
500153959 | CLB-MP-HAUL-DT5444-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 9285 | 9285 | 6500
500153958 | CLB-MP-HAUL-DT5444-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 9285 | 9285 | 6500
500153957 | CLB-MP-HAUL-DT5444-BRKSYS-BRVTR | Brake Treadle Valve | 9285 | 9285 | 6500
500153956 | CLB-MP-HAUL-DT5444-BRKSYS-BRVRL | Brake Dual Relay Valves | 9285 | 9285 | 6500
500153955 | CLB-MP-HAUL-DT5444-BRKSYS-BRVLV | Brake & Steering Manifold | 9285 | 9285 | 6500
500153954 | CLB-MP-HAUL-DT5444-BRKSYS-BRSTV | Brake & Steering Valve | 9285 | 9285 | 6500
500153953 | CLB-MP-HAUL-DT5444-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 9285 | 9285 | 6500
500153952 | CLB-MP-HAUL-DT5444-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 9285 | 9285 | 6500
500153951 | CLB-MP-HAUL-DT5444-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 9285 | 9285 | 6500
500153950 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC | Accumulator Brake Supply Rr | 9285 | 9285 | 6500
500153949 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 9285 | 9285 | 6500
500153948 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC | Accumulator Brake Supply Fr | 9285 | 9285 | 6500
500153947 | CLB-MP-HAUL-DT5444-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 9285 | 9285 | 6500
500153946 | CLB-MP-HAUL-DT5444 | DT5444 Liebherr T264 OHT | 9285 | 9285 | 6500
500164638 | CLB-MP-HAUL-DT5443-STRSYS-STACC-SACRH | Accumulator Steering ODS | 7896 | 7896 | 6500
500164637 | CLB-MP-HAUL-DT5443-STRSYS-STACC-SACLH | Accumulator Steering DS | 7896 | 7896 | 6500
500164636 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 7896 | 7896 | 6500
500164635 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 7896 | 7896 | 6500
500164634 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 7896 | 7896 | 6500
500164633 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 7896 | 7896 | 6500
500153945 | CLB-MP-HAUL-DT5443-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 7896 | 7896 | 6500
500153944 | CLB-MP-HAUL-DT5443-STRUCT-TRAYS | Tray | 7896 | 7896 | 6500
500153943 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 7896 | 7896 | 6500
500153942 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 7896 | 7896 | 6500
500153941 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 7896 | 7896 | 6500
500153940 | CLB-MP-HAUL-DT5443-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 7896 | 7896 | 6500
500153939 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-SEATS | Operators Seat | 7896 | 7896 | 6500
500153938 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 7896 | 7896 | 6500
500153937 | CLB-MP-HAUL-DT5443-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 7896 | 7896 | 6500
500153936 | CLB-MP-HAUL-DT5443-STRUCT-CABIN | Operators Cabin | 7896 | 7896 | 6500
500153935 | CLB-MP-HAUL-DT5443-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 7896 | 7896 | 6500
500153934 | CLB-MP-HAUL-DT5443-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 7896 | 7896 | 6500
500153933 | CLB-MP-HAUL-DT5443-STRSYS-STVLV | Valve Flow Amplifier | 7896 | 7896 | 6500
500153932 | CLB-MP-HAUL-DT5443-STRSYS-STRIA | Steering Idler Arm | 7896 | 7896 | 6500
500153931 | CLB-MP-HAUL-DT5443-STRSYS-STRCY-STCYR | Steering Cylinder RH | 7896 | 7896 | 6500
500153930 | CLB-MP-HAUL-DT5443-STRSYS-STRCY-STCYL | Steering Cylinder LH | 7896 | 7896 | 6500
500153929 | CLB-MP-HAUL-DT5443-STRSYS-STLTR | Steering Linkages & Tie Rods | 7896 | 7896 | 6500
500153928 | CLB-MP-HAUL-DT5443-STRSYS-STCNT | Steering Control Unit | 7896 | 7896 | 6500
500153927 | CLB-MP-HAUL-DT5443-STRSYS-STACC | Accumulator Steering RHS | 7896 | 7896 | 6500
500153926 | CLB-MP-HAUL-DT5443-STRSYS-STACC | Accumulator Steering LHS | 7896 | 7896 | 6500
500153925 | CLB-MP-HAUL-DT5443-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 7896 | 7896 | 6500
500153924 | CLB-MP-HAUL-DT5443-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 7896 | 7896 | 6500
500153923 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 7896 | 7896 | 6500
500153922 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 7896 | 7896 | 6500
500153921 | CLB-MP-HAUL-DT5443-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 7896 | 7896 | 6500
500153920 | CLB-MP-HAUL-DT5443-HYDSYS-HYDOC | Hydraulic Oil Cooler | 7896 | 7896 | 6500
500153919 | CLB-MP-HAUL-DT5443-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 7896 | 7896 | 6500
500153918 | CLB-MP-HAUL-DT5443-HYDSYS-HOMAN | Hoist Manifold | 7896 | 7896 | 6500
500153917 | CLB-MP-HAUL-DT5443-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 7896 | 7896 | 6500
500153916 | CLB-MP-HAUL-DT5443-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 7896 | 7896 | 6500
500153915 | CLB-MP-HAUL-DT5443-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 7896 | 7896 | 6500
500153914 | CLB-MP-HAUL-DT5443-HYDSYS-GROCL | Gear Oil Cooler | 7896 | 7896 | 6500
500153913 | CLB-MP-HAUL-DT5443-GRSYST-ALBPP | Auto Lube Pump | 7896 | 7896 | 6500
500153912 | CLB-MP-HAUL-DT5443-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 7896 | 7896 | 6500
500153911 | CLB-MP-HAUL-DT5443-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 7896 | 7896 | 6500
500153910 | CLB-MP-HAUL-DT5443-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 7896 | 7896 | 6500
500153909 | CLB-MP-HAUL-DT5443-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 7896 | 7896 | 6500
500153908 | CLB-MP-HAUL-DT5443-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 7896 | 7896 | 6500
500153907 | CLB-MP-HAUL-DT5443-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 7896 | 7896 | 6500
500153906 | CLB-MP-HAUL-DT5443-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 7896 | 7896 | 6500
500153905 | CLB-MP-HAUL-DT5443-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 7896 | 7896 | 6500
500153904 | CLB-MP-HAUL-DT5443-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 7896 | 7896 | 6500
500153903 | CLB-MP-HAUL-DT5443-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 7896 | 246 | 6500
500153902 | CLB-MP-HAUL-DT5443-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 7896 | 7896 | 6500
500153901 | CLB-MP-HAUL-DT5443-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 7896 | 7896 | 6500
500153900 | CLB-MP-HAUL-DT5443-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 7896 | 7896 | 6500
500153899 | CLB-MP-HAUL-DT5443-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 7896 | 7896 | 6500
500153898 | CLB-MP-HAUL-DT5443-ENGINE-INTEX-TBORF | Turbocharger RH Front | 7896 | 7896 | 6500
500153897 | CLB-MP-HAUL-DT5443-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 7896 | 7896 | 6500
500153896 | CLB-MP-HAUL-DT5443-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 7896 | 7896 | 6500
500153895 | CLB-MP-HAUL-DT5443-ENGINE-INTEX-AFTER | Aftercooler Engine | 7896 | 7896 | 6500
500153894 | CLB-MP-HAUL-DT5443-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 7896 | 7896 | 6500
500153893 | CLB-MP-HAUL-DT5443-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 7896 | 7896 | 6500
500153892 | CLB-MP-HAUL-DT5443-ENGINE-FUSYS-FUINJ | Fuel Injectors | 7896 | 7896 | 6500
500153891 | CLB-MP-HAUL-DT5443-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 7896 | 7896 | 6500
500153890 | CLB-MP-HAUL-DT5443-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 7896 | 7896 | 6500
500153889 | CLB-MP-HAUL-DT5443-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 7896 | 7896 | 6500
500153888 | CLB-MP-HAUL-DT5443-ENGINE-COSYS-HTWPP | Engine Water Pump | 7896 | 7896 | 6500
500153887 | CLB-MP-HAUL-DT5443-ENGINE-COSYS-COFAN | Fan Cooling System | 7896 | 7896 | 6500
500153886 | CLB-MP-HAUL-DT5443-ENGINE | Engine Assembly Cummins QSK60 | 7896 | 7896 | 6500
500153885 | CLB-MP-HAUL-DT5443-ELCTLV-START-STMUP | Starter Motor Upper | 7896 | 7896 | 6500
500153884 | CLB-MP-HAUL-DT5443-ELCTLV-START-STMLO | Starter Motor Lower | 7896 | 7896 | 6500
500153883 | CLB-MP-HAUL-DT5443-ELCTLV-HARNS | Electrical Harness | 7896 | 7896 | 6500
500153882 | CLB-MP-HAUL-DT5443-ELCTLV-CHARG-BATTY | Batteries | 7896 | 7896 | 6500
500153881 | CLB-MP-HAUL-DT5443-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 7896 | 7896 | 6500
500153880 | CLB-MP-HAUL-DT5443-ELCTHV-HVGBX-HVRES | Grid Resistors | 7896 | 7896 | 6500
500153879 | CLB-MP-HAUL-DT5443-ELCTHV-HVGBM | Grid Box Blower Motor | 7896 | 7896 | 6500
500153878 | CLB-MP-HAUL-DT5443-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 7896 | 7896 | 6500
500153877 | CLB-MP-HAUL-DT5443-ELCTHV-HVBLW | Main High Voltage Blower | 7896 | 7896 | 6500
500153876 | CLB-MP-HAUL-DT5443-ELCTHV-HVALT | High Voltage Alternator | 7896 | 7896 | 6500
500153875 | CLB-MP-HAUL-DT5443-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 7896 | 7896 | 6500
500153874 | CLB-MP-HAUL-DT5443-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 7896 | 7896 | 6500
500153873 | CLB-MP-HAUL-DT5443-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 7896 | 7896 | 6500
500153872 | CLB-MP-HAUL-DT5443-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 7896 | 7896 | 6500
500153871 | CLB-MP-HAUL-DT5443-BRKSYS-BRVTR | Brake Treadle Valve | 7896 | 7896 | 6500
500153870 | CLB-MP-HAUL-DT5443-BRKSYS-BRVRL | Brake Dual Relay Valves | 7896 | 7896 | 6500
500153869 | CLB-MP-HAUL-DT5443-BRKSYS-BRVLV | Brake & Steering Manifold | 7896 | 7896 | 6500
500153868 | CLB-MP-HAUL-DT5443-BRKSYS-BRSTV | Brake & Steering Valve | 7896 | 7896 | 6500
500153867 | CLB-MP-HAUL-DT5443-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 7896 | 7896 | 6500
500153866 | CLB-MP-HAUL-DT5443-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 7896 | 7896 | 6500
500153865 | CLB-MP-HAUL-DT5443-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 7896 | 7896 | 6500
500153864 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC | Accumulator Brake Supply Rr | 7896 | 7896 | 6500
500153863 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 7896 | 7896 | 6500
500153862 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC | Accumulator Brake Supply Fr | 7896 | 7896 | 6500
500153861 | CLB-MP-HAUL-DT5443-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 7896 | 7896 | 6500
500153860 | CLB-MP-HAUL-DT5443 | DT5443 Liebherr T264 OHT | 7896 | 7896 | 6500
500164632 | CLB-MP-HAUL-DT5442-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8565 | 8565 | 6500
500164631 | CLB-MP-HAUL-DT5442-STRSYS-STACC-SACLH | Accumulator Steering DS | 8565 | 8565 | 6500
500164630 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8565 | 8565 | 6500
500164629 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8565 | 8565 | 6500
500164628 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8565 | 8565 | 6500
500164627 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8565 | 8565 | 6500
500153859 | CLB-MP-HAUL-DT5442-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8565 | 8565 | 6500
500153858 | CLB-MP-HAUL-DT5442-STRUCT-TRAYS | Tray | 8565 | 8565 | 6500
500153857 | CLB-MP-HAUL-DT5442-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8565 | 2891 | 6500
500153856 | CLB-MP-HAUL-DT5442-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8565 | 8565 | 6500
500153855 | CLB-MP-HAUL-DT5442-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8565 | 2891 | 6500
500153854 | CLB-MP-HAUL-DT5442-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8565 | 8565 | 6500
500153853 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-SEATS | Operators Seat | 8565 | 8565 | 6500
500153852 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8565 | 8565 | 6500
500153851 | CLB-MP-HAUL-DT5442-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8565 | 8565 | 6500
500153850 | CLB-MP-HAUL-DT5442-STRUCT-CABIN | Operators Cabin | 8565 | 8565 | 6500
500153849 | CLB-MP-HAUL-DT5442-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8565 | 8565 | 6500
500153848 | CLB-MP-HAUL-DT5442-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8565 | 8565 | 6500
500153847 | CLB-MP-HAUL-DT5442-STRSYS-STVLV | Valve Flow Amplifier | 8565 | 8565 | 6500
500153846 | CLB-MP-HAUL-DT5442-STRSYS-STRIA | Steering Idler Arm | 8565 | 8565 | 6500
500153845 | CLB-MP-HAUL-DT5442-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8565 | 8565 | 6500
500153844 | CLB-MP-HAUL-DT5442-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8565 | 8565 | 6500
500153843 | CLB-MP-HAUL-DT5442-STRSYS-STLTR | Steering Linkages & Tie Rods | 8565 | 8565 | 6500
500153842 | CLB-MP-HAUL-DT5442-STRSYS-STCNT | Steering Control Unit | 8565 | 8565 | 6500
500153841 | CLB-MP-HAUL-DT5442-STRSYS-STACC | Accumulator Steering RHS | 8565 | 8565 | 6500
500153840 | CLB-MP-HAUL-DT5442-STRSYS-STACC | Accumulator Steering LHS | 8565 | 8565 | 6500
500153839 | CLB-MP-HAUL-DT5442-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8565 | 8565 | 6500
500153838 | CLB-MP-HAUL-DT5442-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8565 | 8565 | 6500
500153837 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8565 | 8565 | 6500
500153836 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8565 | 8565 | 6500
500153835 | CLB-MP-HAUL-DT5442-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8565 | 8565 | 6500
500153834 | CLB-MP-HAUL-DT5442-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8565 | 8565 | 6500
500153833 | CLB-MP-HAUL-DT5442-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8565 | 8565 | 6500
500153832 | CLB-MP-HAUL-DT5442-HYDSYS-HOMAN | Hoist Manifold | 8565 | 8565 | 6500
500153831 | CLB-MP-HAUL-DT5442-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8565 | 2891 | 6500
500153830 | CLB-MP-HAUL-DT5442-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8565 | 8565 | 6500
500153829 | CLB-MP-HAUL-DT5442-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8565 | 8565 | 6500
500153828 | CLB-MP-HAUL-DT5442-HYDSYS-GROCL | Gear Oil Cooler | 8565 | 8565 | 6500
500153827 | CLB-MP-HAUL-DT5442-GRSYST-ALBPP | Auto Lube Pump | 8565 | 8565 | 6500
500153826 | CLB-MP-HAUL-DT5442-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8565 | 8565 | 6500
500153825 | CLB-MP-HAUL-DT5442-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8565 | 8565 | 6500
500153824 | CLB-MP-HAUL-DT5442-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8565 | 8565 | 6500
500153823 | CLB-MP-HAUL-DT5442-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8565 | 8565 | 6500
500153822 | CLB-MP-HAUL-DT5442-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8565 | 8565 | 6500
500153821 | CLB-MP-HAUL-DT5442-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8565 | 8565 | 6500
500153820 | CLB-MP-HAUL-DT5442-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8565 | 8565 | 6500
500153819 | CLB-MP-HAUL-DT5442-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8565 | 8565 | 6500
500153818 | CLB-MP-HAUL-DT5442-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8565 | 8565 | 6500
500153817 | CLB-MP-HAUL-DT5442-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8565 | 8565 | 6500
500153816 | CLB-MP-HAUL-DT5442-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8565 | 8565 | 6500
500153815 | CLB-MP-HAUL-DT5442-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8565 | 8565 | 6500
500153814 | CLB-MP-HAUL-DT5442-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8565 | 8565 | 6500
500153813 | CLB-MP-HAUL-DT5442-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8565 | 8565 | 6500
500153812 | CLB-MP-HAUL-DT5442-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8565 | 8565 | 6500
500153811 | CLB-MP-HAUL-DT5442-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8565 | 8565 | 6500
500153810 | CLB-MP-HAUL-DT5442-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8565 | 8565 | 6500
500153809 | CLB-MP-HAUL-DT5442-ENGINE-INTEX-AFTER | Aftercooler Engine | 8565 | 8565 | 6500
500153808 | CLB-MP-HAUL-DT5442-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8565 | 8565 | 6500
500153807 | CLB-MP-HAUL-DT5442-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8565 | 8565 | 6500
500153806 | CLB-MP-HAUL-DT5442-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8565 | 8565 | 6500
500153805 | CLB-MP-HAUL-DT5442-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8565 | 8565 | 6500
500153804 | CLB-MP-HAUL-DT5442-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8565 | 8565 | 6500
500153803 | CLB-MP-HAUL-DT5442-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8565 | 8565 | 6500
500153802 | CLB-MP-HAUL-DT5442-ENGINE-COSYS-HTWPP | Engine Water Pump | 8565 | 8565 | 6500
500153801 | CLB-MP-HAUL-DT5442-ENGINE-COSYS-COFAN | Fan Cooling System | 8565 | 8565 | 6500
500153800 | CLB-MP-HAUL-DT5442-ENGINE | Engine Assembly Cummins QSK60 | 8565 | 8565 | 6500
500153799 | CLB-MP-HAUL-DT5442-ELCTLV-START-STMUP | Starter Motor Upper | 8565 | 8565 | 6500
500153798 | CLB-MP-HAUL-DT5442-ELCTLV-START-STMLO | Starter Motor Lower | 8565 | 8565 | 6500
500153797 | CLB-MP-HAUL-DT5442-ELCTLV-HARNS | Electrical Harness | 8565 | 8565 | 6500
500153796 | CLB-MP-HAUL-DT5442-ELCTLV-CHARG-BATTY | Batteries | 8565 | 8565 | 6500
500153795 | CLB-MP-HAUL-DT5442-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8565 | 8565 | 6500
500153794 | CLB-MP-HAUL-DT5442-ELCTHV-HVGBX-HVRES | Grid Resistors | 8565 | 8565 | 6500
500153793 | CLB-MP-HAUL-DT5442-ELCTHV-HVGBM | Grid Box Blower Motor | 8565 | 8565 | 6500
500153792 | CLB-MP-HAUL-DT5442-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8565 | 8565 | 6500
500153791 | CLB-MP-HAUL-DT5442-ELCTHV-HVBLW | Main High Voltage Blower | 8565 | 8565 | 6500
500153790 | CLB-MP-HAUL-DT5442-ELCTHV-HVALT | High Voltage Alternator | 8565 | 8565 | 6500
500153789 | CLB-MP-HAUL-DT5442-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8565 | 8565 | 6500
500153788 | CLB-MP-HAUL-DT5442-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8565 | 8565 | 6500
500153787 | CLB-MP-HAUL-DT5442-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8565 | 8565 | 6500
500153786 | CLB-MP-HAUL-DT5442-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8565 | 8565 | 6500
500153785 | CLB-MP-HAUL-DT5442-BRKSYS-BRVTR | Brake Treadle Valve | 8565 | 8565 | 6500
500153784 | CLB-MP-HAUL-DT5442-BRKSYS-BRVRL | Brake Dual Relay Valves | 8565 | 8565 | 6500
500153783 | CLB-MP-HAUL-DT5442-BRKSYS-BRVLV | Brake & Steering Manifold | 8565 | 8565 | 6500
500153782 | CLB-MP-HAUL-DT5442-BRKSYS-BRSTV | Brake & Steering Valve | 8565 | 8565 | 6500
500153781 | CLB-MP-HAUL-DT5442-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8565 | 8565 | 6500
500153780 | CLB-MP-HAUL-DT5442-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8565 | 8565 | 6500
500153779 | CLB-MP-HAUL-DT5442-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8565 | 8565 | 6500
500153778 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8565 | 8565 | 6500
500153777 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8565 | 8565 | 6500
500153776 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8565 | 8565 | 6500
500153775 | CLB-MP-HAUL-DT5442-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8565 | 8565 | 6500
500153774 | CLB-MP-HAUL-DT5442 | DT5442 Liebherr T264 OHT | 8565 | 8565 | 6500
500164626 | CLB-MP-HAUL-DT5441-STRSYS-STACC-SACRH | Accumulator Steering ODS | 6253 | 6253 | 6500
500164625 | CLB-MP-HAUL-DT5441-STRSYS-STACC-SACLH | Accumulator Steering DS | 6253 | 6253 | 6500
500164624 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 6253 | 6253 | 6500
500164623 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 6253 | 6253 | 6500
500164622 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 6253 | 6253 | 6500
500164621 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 6253 | 6253 | 6500
500153768 | CLB-MP-HAUL-DT5441-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 6253 | 6253 | 6500
500153767 | CLB-MP-HAUL-DT5441-STRUCT-TRAYS | Tray | 6253 | 6253 | 6500
500153766 | CLB-MP-HAUL-DT5441-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 6253 | 6253 | 6500
500153765 | CLB-MP-HAUL-DT5441-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 6253 | 6253 | 6500
500153764 | CLB-MP-HAUL-DT5441-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 6253 | 6253 | 6500
500153763 | CLB-MP-HAUL-DT5441-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 6253 | 6253 | 6500
500153762 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-SEATS | Operators Seat | 6253 | 6253 | 6500
500153761 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 6253 | 6253 | 6500
500153760 | CLB-MP-HAUL-DT5441-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 6253 | 6253 | 6500
500153759 | CLB-MP-HAUL-DT5441-STRUCT-CABIN | Operators Cabin | 6253 | 6253 | 6500
500153758 | CLB-MP-HAUL-DT5441-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 6253 | 6253 | 6500
500153757 | CLB-MP-HAUL-DT5441-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 6253 | 6253 | 6500
500153756 | CLB-MP-HAUL-DT5441-STRSYS-STVLV | Valve Flow Amplifier | 6253 | 6253 | 6500
500153755 | CLB-MP-HAUL-DT5441-STRSYS-STRIA | Steering Idler Arm | 6253 | 6253 | 6500
500153754 | CLB-MP-HAUL-DT5441-STRSYS-STRCY-STCYR | Steering Cylinder RH | 6253 | 6253 | 6500
500153753 | CLB-MP-HAUL-DT5441-STRSYS-STRCY-STCYL | Steering Cylinder LH | 6253 | 6253 | 6500
500153752 | CLB-MP-HAUL-DT5441-STRSYS-STLTR | Steering Linkages & Tie Rods | 6253 | 6253 | 6500
500153751 | CLB-MP-HAUL-DT5441-STRSYS-STCNT | Steering Control Unit | 6253 | 6253 | 6500
500153750 | CLB-MP-HAUL-DT5441-STRSYS-STACC | Accumulator Steering RHS | 6253 | 6253 | 6500
500153749 | CLB-MP-HAUL-DT5441-STRSYS-STACC | Accumulator Steering LHS | 6253 | 6253 | 6500
500153748 | CLB-MP-HAUL-DT5441-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 6253 | 6253 | 6500
500153747 | CLB-MP-HAUL-DT5441-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 6253 | 6253 | 6500
500153746 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 6253 | 6253 | 6500
500153745 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 6253 | 6253 | 6500
500153744 | CLB-MP-HAUL-DT5441-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 6253 | 6253 | 6500
500153743 | CLB-MP-HAUL-DT5441-HYDSYS-HYDOC | Hydraulic Oil Cooler | 6253 | 6253 | 6500
500153742 | CLB-MP-HAUL-DT5441-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 6253 | 6253 | 6500
500153741 | CLB-MP-HAUL-DT5441-HYDSYS-HOMAN | Hoist Manifold | 6253 | 6253 | 6500
500153740 | CLB-MP-HAUL-DT5441-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 6253 | 6253 | 6500
500153739 | CLB-MP-HAUL-DT5441-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 6253 | 6253 | 6500
500153738 | CLB-MP-HAUL-DT5441-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 6253 | 6253 | 6500
500153737 | CLB-MP-HAUL-DT5441-HYDSYS-GROCL | Gear Oil Cooler | 6253 | 6253 | 6500
500153736 | CLB-MP-HAUL-DT5441-GRSYST-ALBPP | Auto Lube Pump | 6253 | 6253 | 6500
500153735 | CLB-MP-HAUL-DT5441-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 6253 | 6253 | 6500
500153734 | CLB-MP-HAUL-DT5441-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 6253 | 6253 | 6500
500153733 | CLB-MP-HAUL-DT5441-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 6253 | 6253 | 6500
500153732 | CLB-MP-HAUL-DT5441-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 6253 | 6253 | 6500
500153731 | CLB-MP-HAUL-DT5441-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 6253 | 6253 | 6500
500153730 | CLB-MP-HAUL-DT5441-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 6253 | 6253 | 6500
500153729 | CLB-MP-HAUL-DT5441-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 6253 | 6253 | 6500
500153728 | CLB-MP-HAUL-DT5441-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 6253 | 6253 | 6500
500153727 | CLB-MP-HAUL-DT5441-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 6253 | 6253 | 6500
500153726 | CLB-MP-HAUL-DT5441-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 6253 | 6253 | 6500
500153725 | CLB-MP-HAUL-DT5441-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 6253 | 6253 | 6500
500153724 | CLB-MP-HAUL-DT5441-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 6253 | 6253 | 6500
500153723 | CLB-MP-HAUL-DT5441-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 6253 | 6253 | 6500
500153722 | CLB-MP-HAUL-DT5441-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 6253 | 6253 | 6500
500153721 | CLB-MP-HAUL-DT5441-ENGINE-INTEX-TBORF | Turbocharger RH Front | 6253 | 6253 | 6500
500153720 | CLB-MP-HAUL-DT5441-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 6253 | 6253 | 6500
500153719 | CLB-MP-HAUL-DT5441-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 6253 | 6253 | 6500
500153718 | CLB-MP-HAUL-DT5441-ENGINE-INTEX-AFTER | Aftercooler Engine | 6253 | 6253 | 6500
500153717 | CLB-MP-HAUL-DT5441-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 6253 | 6253 | 6500
500153716 | CLB-MP-HAUL-DT5441-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 6253 | 6253 | 6500
500153715 | CLB-MP-HAUL-DT5441-ENGINE-FUSYS-FUINJ | Fuel Injectors | 6253 | 6253 | 6500
500153714 | CLB-MP-HAUL-DT5441-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 6253 | 6253 | 6500
500153713 | CLB-MP-HAUL-DT5441-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 6253 | 6253 | 6500
500153712 | CLB-MP-HAUL-DT5441-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 6253 | 6253 | 6500
500153711 | CLB-MP-HAUL-DT5441-ENGINE-COSYS-HTWPP | Engine Water Pump | 6253 | 6253 | 6500
500153710 | CLB-MP-HAUL-DT5441-ENGINE-COSYS-COFAN | Fan Cooling System | 6253 | 6253 | 6500
500153709 | CLB-MP-HAUL-DT5441-ENGINE | Engine Assembly Cummins QSK60 | 6253 | 6253 | 6500
500153708 | CLB-MP-HAUL-DT5441-ELCTLV-START-STMUP | Starter Motor Upper | 6253 | 6253 | 6500
500153707 | CLB-MP-HAUL-DT5441-ELCTLV-START-STMLO | Starter Motor Lower | 6253 | 6253 | 6500
500153706 | CLB-MP-HAUL-DT5441-ELCTLV-HARNS | Electrical Harness | 6253 | 6253 | 6500
500153705 | CLB-MP-HAUL-DT5441-ELCTLV-CHARG-BATTY | Batteries | 6253 | 6253 | 6500
500153704 | CLB-MP-HAUL-DT5441-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 6253 | 6253 | 6500
500153703 | CLB-MP-HAUL-DT5441-ELCTHV-HVGBX-HVRES | Grid Resistors | 6253 | 6253 | 6500
500153702 | CLB-MP-HAUL-DT5441-ELCTHV-HVGBM | Grid Box Blower Motor | 6253 | 6253 | 6500
500153701 | CLB-MP-HAUL-DT5441-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 6253 | 6253 | 6500
500153700 | CLB-MP-HAUL-DT5441-ELCTHV-HVBLW | Main High Voltage Blower | 6253 | 6253 | 6500
500153699 | CLB-MP-HAUL-DT5441-ELCTHV-HVALT | High Voltage Alternator | 6253 | 6253 | 6500
500153698 | CLB-MP-HAUL-DT5441-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 6253 | 6253 | 6500
500153697 | CLB-MP-HAUL-DT5441-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 6253 | 6253 | 6500
500153696 | CLB-MP-HAUL-DT5441-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 6253 | 6253 | 6500
500153695 | CLB-MP-HAUL-DT5441-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 6253 | 6253 | 6500
500153694 | CLB-MP-HAUL-DT5441-BRKSYS-BRVTR | Brake Treadle Valve | 6253 | 6253 | 6500
500153693 | CLB-MP-HAUL-DT5441-BRKSYS-BRVRL | Brake Dual Relay Valves | 6253 | 6253 | 6500
500153692 | CLB-MP-HAUL-DT5441-BRKSYS-BRVLV | Brake & Steering Manifold | 6253 | 6253 | 6500
500153691 | CLB-MP-HAUL-DT5441-BRKSYS-BRSTV | Brake & Steering Valve | 6253 | 6253 | 6500
500153690 | CLB-MP-HAUL-DT5441-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 6253 | 6253 | 6500
500153689 | CLB-MP-HAUL-DT5441-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 6253 | 6253 | 6500
500153688 | CLB-MP-HAUL-DT5441-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 6253 | 6253 | 6500
500153687 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC | Accumulator Brake Supply Rr | 6253 | 6253 | 6500
500153686 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 6253 | 6253 | 6500
500153685 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC | Accumulator Brake Supply Fr | 6253 | 6253 | 6500
500153684 | CLB-MP-HAUL-DT5441-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 6253 | 6253 | 6500
500153683 | CLB-MP-HAUL-DT5441 | DT5441 Liebherr T264 OHT | 6253 | 6253 | 6500
500164620 | CLB-MP-HAUL-DT5440-STRSYS-STACC-SACRH | Accumulator Steering ODS | 1513 | 1513 | 6500
500164619 | CLB-MP-HAUL-DT5440-STRSYS-STACC-SACLH | Accumulator Steering DS | 1513 | 1513 | 6500
500164618 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 1513 | 1513 | 6500
500164617 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 1513 | 1513 | 6500
500164616 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 1513 | 1513 | 6500
500164615 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 1513 | 1513 | 6500
500152039 | CLB-MP-HAUL-DT5440-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 1513 | 1513 | 6500
500152038 | CLB-MP-HAUL-DT5440-STRUCT-TRAYS | Tray | 1513 | 1513 | 6500
500152037 | CLB-MP-HAUL-DT5440-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 1513 | 1513 | 6500
500152036 | CLB-MP-HAUL-DT5440-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 1513 | 1513 | 6500
500152035 | CLB-MP-HAUL-DT5440-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 1513 | 1513 | 6500
500152034 | CLB-MP-HAUL-DT5440-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 1513 | 1513 | 6500
500152033 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-SEATS | Operators Seat | 1513 | 1513 | 6500
500152032 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 1513 | 1513 | 6500
500152031 | CLB-MP-HAUL-DT5440-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 1513 | 1513 | 6500
500152030 | CLB-MP-HAUL-DT5440-STRUCT-CABIN | Operators Cabin | 1513 | 1513 | 6500
500152029 | CLB-MP-HAUL-DT5440-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 1513 | 1513 | 6500
500152028 | CLB-MP-HAUL-DT5440-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 1513 | 1513 | 6500
500152027 | CLB-MP-HAUL-DT5440-STRSYS-STVLV | Valve Flow Amplifier | 1513 | 1513 | 6500
500152026 | CLB-MP-HAUL-DT5440-STRSYS-STRIA | Steering Idler Arm | 1513 | 1513 | 6500
500152025 | CLB-MP-HAUL-DT5440-STRSYS-STRCY-STCYR | Steering Cylinder RH | 1513 | 1513 | 6500
500152024 | CLB-MP-HAUL-DT5440-STRSYS-STRCY-STCYL | Steering Cylinder LH | 1513 | 1513 | 6500
500152023 | CLB-MP-HAUL-DT5440-STRSYS-STLTR | Steering Linkages & Tie Rods | 1513 | 1513 | 6500
500152022 | CLB-MP-HAUL-DT5440-STRSYS-STCNT | Steering Control Unit | 1513 | 1513 | 6500
500152021 | CLB-MP-HAUL-DT5440-STRSYS-STACC | Accumulator Steering RHS | 1513 | 1513 | 6500
500152020 | CLB-MP-HAUL-DT5440-STRSYS-STACC | Accumulator Steering LHS | 1513 | 1513 | 6500
500152019 | CLB-MP-HAUL-DT5440-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 1513 | 1513 | 6500
500152018 | CLB-MP-HAUL-DT5440-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 1513 | 1513 | 6500
500152017 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 1513 | 1513 | 6500
500152016 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 1513 | 1513 | 6500
500152015 | CLB-MP-HAUL-DT5440-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 1513 | 1513 | 6500
500152014 | CLB-MP-HAUL-DT5440-HYDSYS-HYDOC | Hydraulic Oil Cooler | 1513 | 1513 | 6500
500152013 | CLB-MP-HAUL-DT5440-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 1513 | 1513 | 6500
500152012 | CLB-MP-HAUL-DT5440-HYDSYS-HOMAN | Hoist Manifold | 1513 | 1513 | 6500
500152011 | CLB-MP-HAUL-DT5440-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 1513 | 1513 | 6500
500152010 | CLB-MP-HAUL-DT5440-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 1513 | 1513 | 6500
500152009 | CLB-MP-HAUL-DT5440-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 1513 | 1513 | 6500
500152008 | CLB-MP-HAUL-DT5440-HYDSYS-GROCL | Gear Oil Cooler | 1513 | 1513 | 6500
500152007 | CLB-MP-HAUL-DT5440-GRSYST-ALBPP | Auto Lube Pump | 1513 | 1513 | 6500
500152006 | CLB-MP-HAUL-DT5440-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 1513 | 1513 | 6500
500152005 | CLB-MP-HAUL-DT5440-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 1513 | 1513 | 6500
500152004 | CLB-MP-HAUL-DT5440-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 1513 | 1513 | 6500
500152003 | CLB-MP-HAUL-DT5440-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 1513 | 1513 | 6500
500152002 | CLB-MP-HAUL-DT5440-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 1513 | 1513 | 6500
500152001 | CLB-MP-HAUL-DT5440-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 1513 | 1513 | 6500
500152000 | CLB-MP-HAUL-DT5440-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 1513 | 1513 | 6500
500151999 | CLB-MP-HAUL-DT5440-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 1513 | 1513 | 6500
500151998 | CLB-MP-HAUL-DT5440-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 1513 | 1513 | 6500
500151997 | CLB-MP-HAUL-DT5440-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 1513 | 1513 | 6500
500151996 | CLB-MP-HAUL-DT5440-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 1513 | 1513 | 6500
500151995 | CLB-MP-HAUL-DT5440-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 1513 | 1513 | 6500
500151994 | CLB-MP-HAUL-DT5440-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 1513 | 1513 | 6500
500151993 | CLB-MP-HAUL-DT5440-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 1513 | 1513 | 6500
500151992 | CLB-MP-HAUL-DT5440-ENGINE-INTEX-TBORF | Turbocharger RH Front | 1513 | 1513 | 6500
500151991 | CLB-MP-HAUL-DT5440-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 1513 | 1513 | 6500
500151990 | CLB-MP-HAUL-DT5440-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 1513 | 1513 | 6500
500151989 | CLB-MP-HAUL-DT5440-ENGINE-INTEX-AFTER | Aftercooler Engine | 1513 | 1513 | 6500
500151988 | CLB-MP-HAUL-DT5440-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 1513 | 1513 | 6500
500151987 | CLB-MP-HAUL-DT5440-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 1513 | 1513 | 6500
500151986 | CLB-MP-HAUL-DT5440-ENGINE-FUSYS-FUINJ | Fuel Injectors | 1513 | 1513 | 6500
500151985 | CLB-MP-HAUL-DT5440-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 1513 | 1513 | 6500
500151984 | CLB-MP-HAUL-DT5440-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 1513 | 1513 | 6500
500151983 | CLB-MP-HAUL-DT5440-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 1513 | 1513 | 6500
500151982 | CLB-MP-HAUL-DT5440-ENGINE-COSYS-HTWPP | Engine Water Pump | 1513 | 1513 | 6500
500151981 | CLB-MP-HAUL-DT5440-ENGINE-COSYS-COFAN | Fan Cooling System | 1513 | 1513 | 6500
500151980 | CLB-MP-HAUL-DT5440-ENGINE | Engine Assembly Cummins QSK60 | 1513 | 1513 | 6500
500151979 | CLB-MP-HAUL-DT5440-ELCTLV-START-STMUP | Starter Motor Upper | 1513 | 1513 | 6500
500151978 | CLB-MP-HAUL-DT5440-ELCTLV-START-STMLO | Starter Motor Lower | 1513 | 1513 | 6500
500151977 | CLB-MP-HAUL-DT5440-ELCTLV-HARNS | Electrical Harness | 1513 | 1513 | 6500
500151976 | CLB-MP-HAUL-DT5440-ELCTLV-CHARG-BATTY | Batteries | 1513 | 1513 | 6500
500151975 | CLB-MP-HAUL-DT5440-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 1513 | 1513 | 6500
500151974 | CLB-MP-HAUL-DT5440-ELCTHV-HVGBX-HVRES | Grid Resistors | 1513 | 1513 | 6500
500151973 | CLB-MP-HAUL-DT5440-ELCTHV-HVGBM | Grid Box Blower Motor | 1513 | 1513 | 6500
500151972 | CLB-MP-HAUL-DT5440-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 1513 | 1513 | 6500
500151971 | CLB-MP-HAUL-DT5440-ELCTHV-HVBLW | Main High Voltage Blower | 1513 | 1513 | 6500
500151970 | CLB-MP-HAUL-DT5440-ELCTHV-HVALT | High Voltage Alternator | 1513 | 1513 | 6500
500151969 | CLB-MP-HAUL-DT5440-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 1513 | 1513 | 6500
500151968 | CLB-MP-HAUL-DT5440-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 1513 | 1513 | 6500
500151967 | CLB-MP-HAUL-DT5440-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 1513 | 1513 | 6500
500151966 | CLB-MP-HAUL-DT5440-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 1513 | 1513 | 6500
500151965 | CLB-MP-HAUL-DT5440-BRKSYS-BRVTR | Brake Treadle Valve | 1513 | 1513 | 6500
500151964 | CLB-MP-HAUL-DT5440-BRKSYS-BRVRL | Brake Dual Relay Valves | 1513 | 1513 | 6500
500151963 | CLB-MP-HAUL-DT5440-BRKSYS-BRVLV | Brake & Steering Manifold | 1513 | 1513 | 6500
500151962 | CLB-MP-HAUL-DT5440-BRKSYS-BRSTV | Brake & Steering Valve | 1513 | 1513 | 6500
500151961 | CLB-MP-HAUL-DT5440-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 1513 | 1513 | 6500
500151960 | CLB-MP-HAUL-DT5440-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 1513 | 1513 | 6500
500151959 | CLB-MP-HAUL-DT5440-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 1513 | 1513 | 6500
500151958 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC | Accumulator Brake Supply Rr | 1513 | 1513 | 6500
500151957 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 1513 | 1513 | 6500
500151956 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC | Accumulator Brake Supply Fr | 1513 | 1513 | 6500
500151955 | CLB-MP-HAUL-DT5440-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 1513 | 1513 | 6500
500151954 | CLB-MP-HAUL-DT5440 | DT5440 Liebherr T264 OHT | 1513 | 1513 | 6500
500164614 | CLB-MP-HAUL-DT5419-STRSYS-STACC-SACRH | Accumulator Steering ODS | 10988 | 10988 | 6500
500164613 | CLB-MP-HAUL-DT5419-STRSYS-STACC-SACLH | Accumulator Steering DS | 10988 | 10988 | 6500
500164612 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 10988 | 10988 | 6500
500164611 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 10988 | 10988 | 6500
500164610 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 10988 | 10988 | 6500
500164609 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 10988 | 10988 | 6500
500149229 | CLB-MP-HAUL-DT5419-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 10988 | 10988 | 6500
500148402 | CLB-MP-HAUL-DT5419-STRUCT-TRAYS | Tray | 10988 | 10988 | 6500
500148401 | CLB-MP-HAUL-DT5419-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 10988 | 137 | 6500
500148400 | CLB-MP-HAUL-DT5419-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 10988 | 1681 | 6500
500148399 | CLB-MP-HAUL-DT5419-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 10988 | 137 | 6500
500148398 | CLB-MP-HAUL-DT5419-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 10988 | 10988 | 6500
500148397 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-SEATS | Operators Seat | 10988 | 10988 | 6500
500148396 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 10988 | 10988 | 6500
500148395 | CLB-MP-HAUL-DT5419-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 10988 | 10988 | 6500
500148394 | CLB-MP-HAUL-DT5419-STRUCT-CABIN | Operators Cabin | 10988 | 10988 | 6500
500148393 | CLB-MP-HAUL-DT5419-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 10988 | 10988 | 6500
500148392 | CLB-MP-HAUL-DT5419-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 10988 | 10988 | 6500
500148391 | CLB-MP-HAUL-DT5419-STRSYS-STVLV | Valve Flow Amplifier | 10988 | 10988 | 6500
500148390 | CLB-MP-HAUL-DT5419-STRSYS-STRIA | Steering Idler Arm | 10988 | 10988 | 6500
500148389 | CLB-MP-HAUL-DT5419-STRSYS-STRCY-STCYR | Steering Cylinder RH | 10988 | 4657 | 6500
500148388 | CLB-MP-HAUL-DT5419-STRSYS-STRCY-STCYL | Steering Cylinder LH | 10988 | 4657 | 6500
500148387 | CLB-MP-HAUL-DT5419-STRSYS-STLTR | Steering Linkages & Tie Rods | 10988 | 10988 | 6500
500148386 | CLB-MP-HAUL-DT5419-STRSYS-STCNT | Steering Control Unit | 10988 | 6187 | 6500
500148385 | CLB-MP-HAUL-DT5419-STRSYS-STACC | Accumulator Steering RHS | 10988 | 10988 | 6500
500148384 | CLB-MP-HAUL-DT5419-STRSYS-STACC | Accumulator Steering LHS | 10988 | 10988 | 6500
500148383 | CLB-MP-HAUL-DT5419-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 10988 | 10988 | 6500
500148382 | CLB-MP-HAUL-DT5419-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 10988 | 10988 | 6500
500148381 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 10988 | 3763 | 6500
500148380 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 10988 | 10988 | 6500
500148379 | CLB-MP-HAUL-DT5419-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 10988 | 10988 | 6500
500148378 | CLB-MP-HAUL-DT5419-HYDSYS-HYDOC | Hydraulic Oil Cooler | 10988 | 10988 | 6500
500148377 | CLB-MP-HAUL-DT5419-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 10988 | 10988 | 6500
500148376 | CLB-MP-HAUL-DT5419-HYDSYS-HOMAN | Hoist Manifold | 10988 | 10988 | 6500
500148375 | CLB-MP-HAUL-DT5419-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 10988 | 10988 | 6500
500148374 | CLB-MP-HAUL-DT5419-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 10988 | 10988 | 6500
500148373 | CLB-MP-HAUL-DT5419-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 10988 | 10988 | 6500
500148372 | CLB-MP-HAUL-DT5419-HYDSYS-GROCL | Gear Oil Cooler | 10988 | 10988 | 6500
500148371 | CLB-MP-HAUL-DT5419-GRSYST-ALBPP | Auto Lube Pump | 10988 | 10988 | 6500
500148370 | CLB-MP-HAUL-DT5419-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 10988 | 10988 | 6500
500148369 | CLB-MP-HAUL-DT5419-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 10988 | 10988 | 6500
500148368 | CLB-MP-HAUL-DT5419-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 10988 | 10988 | 6500
500148367 | CLB-MP-HAUL-DT5419-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 10988 | 10988 | 6500
500148366 | CLB-MP-HAUL-DT5419-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 10988 | 10988 | 6500
500148365 | CLB-MP-HAUL-DT5419-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 10988 | 10988 | 6500
500148364 | CLB-MP-HAUL-DT5419-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 10988 | 10988 | 6500
500148363 | CLB-MP-HAUL-DT5419-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 10988 | 10988 | 6500
500148362 | CLB-MP-HAUL-DT5419-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 10988 | 10988 | 6500
500148361 | CLB-MP-HAUL-DT5419-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 10988 | 9282 | 6500
500148360 | CLB-MP-HAUL-DT5419-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 10988 | 10988 | 6500
500148359 | CLB-MP-HAUL-DT5419-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 10988 | 10988 | 6500
500148358 | CLB-MP-HAUL-DT5419-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 10988 | 10988 | 6500
500148357 | CLB-MP-HAUL-DT5419-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 10988 | 10988 | 6500
500148356 | CLB-MP-HAUL-DT5419-ENGINE-INTEX-TBORF | Turbocharger RH Front | 10988 | 10988 | 6500
500148355 | CLB-MP-HAUL-DT5419-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 10988 | 10988 | 6500
500148354 | CLB-MP-HAUL-DT5419-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 10988 | 10988 | 6500
500148353 | CLB-MP-HAUL-DT5419-ENGINE-INTEX-AFTER | Aftercooler Engine | 10988 | 10988 | 6500
500148352 | CLB-MP-HAUL-DT5419-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 10988 | 10988 | 6500
500148351 | CLB-MP-HAUL-DT5419-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 10988 | 10988 | 6500
500148350 | CLB-MP-HAUL-DT5419-ENGINE-FUSYS-FUINJ | Fuel Injectors | 10988 | 10988 | 6500
500148349 | CLB-MP-HAUL-DT5419-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 10988 | 10988 | 6500
500148348 | CLB-MP-HAUL-DT5419-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 10988 | 10988 | 6500
500148347 | CLB-MP-HAUL-DT5419-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 10988 | 10988 | 6500
500148346 | CLB-MP-HAUL-DT5419-ENGINE-COSYS-HTWPP | Engine Water Pump | 10988 | 10988 | 6500
500148345 | CLB-MP-HAUL-DT5419-ENGINE-COSYS-COFAN | Fan Cooling System | 10988 | 10988 | 6500
500148344 | CLB-MP-HAUL-DT5419-ENGINE | Engine Assembly Cummins QSK60 | 10988 | 10988 | 6500
500148343 | CLB-MP-HAUL-DT5419-ELCTLV-START-STMUP | Starter Motor Upper | 10988 | 10988 | 6500
500148342 | CLB-MP-HAUL-DT5419-ELCTLV-START-STMLO | Starter Motor Lower | 10988 | 10988 | 6500
500148341 | CLB-MP-HAUL-DT5419-ELCTLV-HARNS | Electrical Harness | 10988 | 10988 | 6500
500148340 | CLB-MP-HAUL-DT5419-ELCTLV-CHARG-BATTY | Batteries | 10988 | 10988 | 6500
500148339 | CLB-MP-HAUL-DT5419-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 10988 | 10988 | 6500
500148338 | CLB-MP-HAUL-DT5419-ELCTHV-HVGBX-HVRES | Grid Resistors | 10988 | 10988 | 6500
500148337 | CLB-MP-HAUL-DT5419-ELCTHV-HVGBM | Grid Box Blower Motor | 10988 | 10988 | 6500
500148336 | CLB-MP-HAUL-DT5419-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 10988 | 10988 | 6500
500148335 | CLB-MP-HAUL-DT5419-ELCTHV-HVBLW | Main High Voltage Blower | 10988 | 10988 | 6500
500148334 | CLB-MP-HAUL-DT5419-ELCTHV-HVALT | High Voltage Alternator | 10988 | 10988 | 6500
500148333 | CLB-MP-HAUL-DT5419-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 10988 | 10988 | 6500
500148332 | CLB-MP-HAUL-DT5419-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 10988 | 10988 | 6500
500148331 | CLB-MP-HAUL-DT5419-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 10988 | 10988 | 6500
500148330 | CLB-MP-HAUL-DT5419-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 10988 | 10988 | 6500
500148329 | CLB-MP-HAUL-DT5419-BRKSYS-BRVTR | Brake Treadle Valve | 10988 | 10988 | 6500
500148328 | CLB-MP-HAUL-DT5419-BRKSYS-BRVRL | Brake Dual Relay Valves | 10988 | 10988 | 6500
500148327 | CLB-MP-HAUL-DT5419-BRKSYS-BRVLV | Brake & Steering Manifold | 10988 | 10988 | 6500
500148326 | CLB-MP-HAUL-DT5419-BRKSYS-BRSTV | Brake & Steering Valve | 10988 | 10988 | 6500
500148325 | CLB-MP-HAUL-DT5419-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 10988 | 10988 | 6500
500148324 | CLB-MP-HAUL-DT5419-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 10988 | 10988 | 6500
500148323 | CLB-MP-HAUL-DT5419-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 10988 | 10988 | 6500
500148322 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC | Accumulator Brake Supply Rr | 10988 | 10988 | 6500
500148321 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 10988 | 10988 | 6500
500148320 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC | Accumulator Brake Supply Fr | 10988 | 10988 | 6500
500148319 | CLB-MP-HAUL-DT5419-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 10988 | 10988 | 6500
500148318 | CLB-MP-HAUL-DT5419 | DT5419 Liebherr T264 OHT | 10988 | 10988 | 6500
500164608 | CLB-MP-HAUL-DT5418-STRSYS-STACC-SACRH | Accumulator Steering ODS | 10719 | 10719 | 6500
500164607 | CLB-MP-HAUL-DT5418-STRSYS-STACC-SACLH | Accumulator Steering DS | 10719 | 10719 | 6500
500164606 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 10719 | 10719 | 6500
500164605 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 10719 | 10719 | 6500
500164604 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 10719 | 10719 | 6500
500164603 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 10719 | 10719 | 6500
500149228 | CLB-MP-HAUL-DT5418-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 10719 | 10719 | 6500
500148317 | CLB-MP-HAUL-DT5418-STRUCT-TRAYS | Tray | 10719 | 10719 | 6500
500148316 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 10719 | 10719 | 6500
500148315 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 10719 | 10719 | 6500
500148314 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 10719 | 10719 | 6500
500148313 | CLB-MP-HAUL-DT5418-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 10719 | 10719 | 6500
500148312 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-SEATS | Operators Seat | 10719 | 10719 | 6500
500148311 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 10719 | 10719 | 6500
500148310 | CLB-MP-HAUL-DT5418-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 10719 | 10719 | 6500
500148309 | CLB-MP-HAUL-DT5418-STRUCT-CABIN | Operators Cabin | 10719 | 10719 | 6500
500148308 | CLB-MP-HAUL-DT5418-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 10719 | 10719 | 6500
500148307 | CLB-MP-HAUL-DT5418-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 10719 | 10719 | 6500
500148306 | CLB-MP-HAUL-DT5418-STRSYS-STVLV | Valve Flow Amplifier | 10719 | 10719 | 6500
500148305 | CLB-MP-HAUL-DT5418-STRSYS-STRIA | Steering Idler Arm | 10719 | 10719 | 6500
500148304 | CLB-MP-HAUL-DT5418-STRSYS-STRCY-STCYR | Steering Cylinder RH | 10719 | 10719 | 6500
500148303 | CLB-MP-HAUL-DT5418-STRSYS-STRCY-STCYL | Steering Cylinder LH | 10719 | 851 | 6500
500148302 | CLB-MP-HAUL-DT5418-STRSYS-STLTR | Steering Linkages & Tie Rods | 10719 | 10719 | 6500
500148301 | CLB-MP-HAUL-DT5418-STRSYS-STCNT | Steering Control Unit | 10719 | 10719 | 6500
500148300 | CLB-MP-HAUL-DT5418-STRSYS-STACC | Accumulator Steering RHS | 10719 | 10719 | 6500
500148299 | CLB-MP-HAUL-DT5418-STRSYS-STACC | Accumulator Steering LHS | 10719 | 10719 | 6500
500148298 | CLB-MP-HAUL-DT5418-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 10719 | 10719 | 6500
500148297 | CLB-MP-HAUL-DT5418-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 10719 | 10719 | 6500
500148296 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 10719 | 10719 | 6500
500148295 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 10719 | 10719 | 6500
500148294 | CLB-MP-HAUL-DT5418-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 10719 | 10719 | 6500
500148293 | CLB-MP-HAUL-DT5418-HYDSYS-HYDOC | Hydraulic Oil Cooler | 10719 | 10719 | 6500
500148292 | CLB-MP-HAUL-DT5418-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 10719 | 10719 | 6500
500148291 | CLB-MP-HAUL-DT5418-HYDSYS-HOMAN | Hoist Manifold | 10719 | 10719 | 6500
500148290 | CLB-MP-HAUL-DT5418-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 10719 | 10719 | 6500
500148289 | CLB-MP-HAUL-DT5418-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 10719 | 10719 | 6500
500148288 | CLB-MP-HAUL-DT5418-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 10719 | 10719 | 6500
500148287 | CLB-MP-HAUL-DT5418-HYDSYS-GROCL | Gear Oil Cooler | 10719 | 10719 | 6500
500148286 | CLB-MP-HAUL-DT5418-GRSYST-ALBPP | Auto Lube Pump | 10719 | 10719 | 6500
500148285 | CLB-MP-HAUL-DT5418-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 10719 | 10719 | 6500
500148284 | CLB-MP-HAUL-DT5418-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 10719 | 10719 | 6500
500148283 | CLB-MP-HAUL-DT5418-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 10719 | 10719 | 6500
500148282 | CLB-MP-HAUL-DT5418-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 10719 | 10719 | 6500
500148281 | CLB-MP-HAUL-DT5418-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 10719 | 10719 | 6500
500148280 | CLB-MP-HAUL-DT5418-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 10719 | 10719 | 6500
500148279 | CLB-MP-HAUL-DT5418-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 10719 | 10719 | 6500
500148278 | CLB-MP-HAUL-DT5418-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 10719 | 10719 | 6500
500148277 | CLB-MP-HAUL-DT5418-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 10719 | 10719 | 6500
500148276 | CLB-MP-HAUL-DT5418-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 10719 | 10719 | 6500
500148275 | CLB-MP-HAUL-DT5418-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 10719 | 9374 | 6500
500148274 | CLB-MP-HAUL-DT5418-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 10719 | 10719 | 6500
500148273 | CLB-MP-HAUL-DT5418-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 10719 | 10719 | 6500
500148272 | CLB-MP-HAUL-DT5418-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 10719 | 10719 | 6500
500148271 | CLB-MP-HAUL-DT5418-ENGINE-INTEX-TBORF | Turbocharger RH Front | 10719 | 10719 | 6500
500148270 | CLB-MP-HAUL-DT5418-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 10719 | 10719 | 6500
500148269 | CLB-MP-HAUL-DT5418-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 10719 | 10445 | 6500
500148268 | CLB-MP-HAUL-DT5418-ENGINE-INTEX-AFTER | Aftercooler Engine | 10719 | 10719 | 6500
500148267 | CLB-MP-HAUL-DT5418-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 10719 | 10719 | 6500
500148266 | CLB-MP-HAUL-DT5418-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 10719 | 10719 | 6500
500148265 | CLB-MP-HAUL-DT5418-ENGINE-FUSYS-FUINJ | Fuel Injectors | 10719 | 10719 | 6500
500148264 | CLB-MP-HAUL-DT5418-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 10719 | 10719 | 6500
500148263 | CLB-MP-HAUL-DT5418-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 10719 | 10719 | 6500
500148262 | CLB-MP-HAUL-DT5418-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 10719 | 10719 | 6500
500148261 | CLB-MP-HAUL-DT5418-ENGINE-COSYS-HTWPP | Engine Water Pump | 10719 | 10719 | 6500
500148260 | CLB-MP-HAUL-DT5418-ENGINE-COSYS-COFAN | Fan Cooling System | 10719 | 10719 | 6500
500148259 | CLB-MP-HAUL-DT5418-ENGINE | Engine Assembly Cummins QSK60 | 10719 | 10719 | 6500
500148258 | CLB-MP-HAUL-DT5418-ELCTLV-START-STMUP | Starter Motor Upper | 10719 | 10719 | 6500
500148257 | CLB-MP-HAUL-DT5418-ELCTLV-START-STMLO | Starter Motor Lower | 10719 | 10719 | 6500
500148256 | CLB-MP-HAUL-DT5418-ELCTLV-HARNS | Electrical Harness | 10719 | 10719 | 6500
500148255 | CLB-MP-HAUL-DT5418-ELCTLV-CHARG-BATTY | Batteries | 10719 | 10719 | 6500
500148254 | CLB-MP-HAUL-DT5418-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 10719 | 10719 | 6500
500148253 | CLB-MP-HAUL-DT5418-ELCTHV-HVGBX-HVRES | Grid Resistors | 10719 | 10719 | 6500
500148252 | CLB-MP-HAUL-DT5418-ELCTHV-HVGBM | Grid Box Blower Motor | 10719 | 10719 | 6500
500148251 | CLB-MP-HAUL-DT5418-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 10719 | 10719 | 6500
500148250 | CLB-MP-HAUL-DT5418-ELCTHV-HVBLW | Main High Voltage Blower | 10719 | 10719 | 6500
500148249 | CLB-MP-HAUL-DT5418-ELCTHV-HVALT | High Voltage Alternator | 10719 | 10719 | 6500
500148248 | CLB-MP-HAUL-DT5418-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 10719 | 10719 | 6500
500148247 | CLB-MP-HAUL-DT5418-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 10719 | 10719 | 6500
500148246 | CLB-MP-HAUL-DT5418-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 10719 | 10719 | 6500
500148245 | CLB-MP-HAUL-DT5418-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 10719 | 10719 | 6500
500148244 | CLB-MP-HAUL-DT5418-BRKSYS-BRVTR | Brake Treadle Valve | 10719 | 10719 | 6500
500148243 | CLB-MP-HAUL-DT5418-BRKSYS-BRVRL | Brake Dual Relay Valves | 10719 | 10719 | 6500
500148242 | CLB-MP-HAUL-DT5418-BRKSYS-BRVLV | Brake & Steering Manifold | 10719 | 10719 | 6500
500148241 | CLB-MP-HAUL-DT5418-BRKSYS-BRSTV | Brake & Steering Valve | 10719 | 10719 | 6500
500148240 | CLB-MP-HAUL-DT5418-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 10719 | 10719 | 6500
500148239 | CLB-MP-HAUL-DT5418-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 10719 | 10719 | 6500
500148238 | CLB-MP-HAUL-DT5418-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 10719 | 10719 | 6500
500148237 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC | Accumulator Brake Supply Rr | 10719 | 10719 | 6500
500148236 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 10719 | 10719 | 6500
500148235 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC | Accumulator Brake Supply Fr | 10719 | 10719 | 6500
500148234 | CLB-MP-HAUL-DT5418-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 10719 | 10719 | 6500
500148233 | CLB-MP-HAUL-DT5418 | DT5418 Liebherr T264 OHT | 10719 | 10719 | 6500
500164602 | CLB-MP-HAUL-DT5417-STRSYS-STACC-SACRH | Accumulator Steering ODS | 10618 | 10618 | 6500
500164601 | CLB-MP-HAUL-DT5417-STRSYS-STACC-SACLH | Accumulator Steering DS | 10618 | 10618 | 6500
500164600 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 10618 | 10618 | 6500
500164599 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 10618 | 10618 | 6500
500164598 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 10618 | 10618 | 6500
500164597 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 10618 | 10618 | 6500
500149227 | CLB-MP-HAUL-DT5417-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 10618 | 10618 | 6500
500148199 | CLB-MP-HAUL-DT5417-STRUCT-TRAYS | Tray | 10618 | 10618 | 6500
500148198 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 10618 | 10618 | 6500
500148197 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 10618 | 10618 | 6500
500148196 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 10618 | 10618 | 6500
500148195 | CLB-MP-HAUL-DT5417-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 10618 | 4130 | 6500
500148194 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-SEATS | Operators Seat | 10618 | 10618 | 6500
500148193 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 10618 | 10618 | 6500
500148192 | CLB-MP-HAUL-DT5417-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 10618 | 10618 | 6500
500148191 | CLB-MP-HAUL-DT5417-STRUCT-CABIN | Operators Cabin | 10618 | 10618 | 6500
500148190 | CLB-MP-HAUL-DT5417-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 10618 | 10618 | 6500
500148189 | CLB-MP-HAUL-DT5417-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 10618 | 10618 | 6500
500148188 | CLB-MP-HAUL-DT5417-STRSYS-STVLV | Valve Flow Amplifier | 10618 | 10618 | 6500
500148187 | CLB-MP-HAUL-DT5417-STRSYS-STRIA | Steering Idler Arm | 10618 | 10618 | 6500
500148186 | CLB-MP-HAUL-DT5417-STRSYS-STRCY-STCYR | Steering Cylinder RH | 10618 | 6256 | 6500
500148185 | CLB-MP-HAUL-DT5417-STRSYS-STRCY-STCYL | Steering Cylinder LH | 10618 | 942 | 6500
500148184 | CLB-MP-HAUL-DT5417-STRSYS-STLTR | Steering Linkages & Tie Rods | 10618 | 10618 | 6500
500148183 | CLB-MP-HAUL-DT5417-STRSYS-STCNT | Steering Control Unit | 10618 | 10618 | 6500
500148182 | CLB-MP-HAUL-DT5417-STRSYS-STACC | Accumulator Steering RHS | 10618 | 10618 | 6500
500148181 | CLB-MP-HAUL-DT5417-STRSYS-STACC | Accumulator Steering LHS | 10618 | 10618 | 6500
500148180 | CLB-MP-HAUL-DT5417-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 10618 | 10618 | 6500
500148179 | CLB-MP-HAUL-DT5417-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 10618 | 10618 | 6500
500148178 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 10618 | 10618 | 6500
500148177 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 10618 | 10618 | 6500
500148176 | CLB-MP-HAUL-DT5417-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 10618 | 10618 | 6500
500148175 | CLB-MP-HAUL-DT5417-HYDSYS-HYDOC | Hydraulic Oil Cooler | 10618 | 3551 | 6500
500148174 | CLB-MP-HAUL-DT5417-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 10618 | 10618 | 6500
500148173 | CLB-MP-HAUL-DT5417-HYDSYS-HOMAN | Hoist Manifold | 10618 | 10618 | 6500
500148172 | CLB-MP-HAUL-DT5417-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 10618 | 2862 | 6500
500148171 | CLB-MP-HAUL-DT5417-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 10618 | 7221 | 6500
500148170 | CLB-MP-HAUL-DT5417-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 10618 | 10618 | 6500
500148169 | CLB-MP-HAUL-DT5417-HYDSYS-GROCL | Gear Oil Cooler | 10618 | 10618 | 6500
500148168 | CLB-MP-HAUL-DT5417-GRSYST-ALBPP | Auto Lube Pump | 10618 | 10618 | 6500
500148167 | CLB-MP-HAUL-DT5417-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 10618 | 10618 | 6500
500148166 | CLB-MP-HAUL-DT5417-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 10618 | 10618 | 6500
500148165 | CLB-MP-HAUL-DT5417-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 10618 | 10618 | 6500
500148164 | CLB-MP-HAUL-DT5417-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 10618 | 10618 | 6500
500148163 | CLB-MP-HAUL-DT5417-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 10618 | 10618 | 6500
500148162 | CLB-MP-HAUL-DT5417-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 10618 | 10618 | 6500
500148161 | CLB-MP-HAUL-DT5417-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 10618 | 10618 | 6500
500148160 | CLB-MP-HAUL-DT5417-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 10618 | 10618 | 6500
500148159 | CLB-MP-HAUL-DT5417-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 10618 | 10618 | 6500
500148158 | CLB-MP-HAUL-DT5417-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 10618 | 10618 | 6500
500148157 | CLB-MP-HAUL-DT5417-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 10618 | 8226 | 6500
500148156 | CLB-MP-HAUL-DT5417-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 10618 | 10618 | 6500
500148155 | CLB-MP-HAUL-DT5417-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 10618 | 10618 | 6500
500148154 | CLB-MP-HAUL-DT5417-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 10618 | 10618 | 6500
500148153 | CLB-MP-HAUL-DT5417-ENGINE-INTEX-TBORF | Turbocharger RH Front | 10618 | 10618 | 6500
500148152 | CLB-MP-HAUL-DT5417-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 10618 | 10618 | 6500
500148151 | CLB-MP-HAUL-DT5417-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 10618 | 10618 | 6500
500148150 | CLB-MP-HAUL-DT5417-ENGINE-INTEX-AFTER | Aftercooler Engine | 10618 | 10618 | 6500
500148149 | CLB-MP-HAUL-DT5417-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 10618 | 10618 | 6500
500148148 | CLB-MP-HAUL-DT5417-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 10618 | 10618 | 6500
500148147 | CLB-MP-HAUL-DT5417-ENGINE-FUSYS-FUINJ | Fuel Injectors | 10618 | 10618 | 6500
500148146 | CLB-MP-HAUL-DT5417-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 10618 | 10618 | 6500
500148145 | CLB-MP-HAUL-DT5417-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 10618 | 10618 | 6500
500148144 | CLB-MP-HAUL-DT5417-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 10618 | 10618 | 6500
500148143 | CLB-MP-HAUL-DT5417-ENGINE-COSYS-HTWPP | Engine Water Pump | 10618 | 10618 | 6500
500148142 | CLB-MP-HAUL-DT5417-ENGINE-COSYS-COFAN | Fan Cooling System | 10618 | 10618 | 6500
500148141 | CLB-MP-HAUL-DT5417-ENGINE | Engine Assembly Cummins QSK60 | 10618 | 10618 | 6500
500148140 | CLB-MP-HAUL-DT5417-ELCTLV-START-STMUP | Starter Motor Upper | 10618 | 10618 | 6500
500148139 | CLB-MP-HAUL-DT5417-ELCTLV-START-STMLO | Starter Motor Lower | 10618 | 10618 | 6500
500148138 | CLB-MP-HAUL-DT5417-ELCTLV-HARNS | Electrical Harness | 10618 | 10618 | 6500
500148137 | CLB-MP-HAUL-DT5417-ELCTLV-CHARG-BATTY | Batteries | 10618 | 10618 | 6500
500148136 | CLB-MP-HAUL-DT5417-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 10618 | 10618 | 6500
500148135 | CLB-MP-HAUL-DT5417-ELCTHV-HVGBX-HVRES | Grid Resistors | 10618 | 10618 | 6500
500148134 | CLB-MP-HAUL-DT5417-ELCTHV-HVGBM | Grid Box Blower Motor | 10618 | 10618 | 6500
500148133 | CLB-MP-HAUL-DT5417-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 10618 | 10618 | 6500
500148132 | CLB-MP-HAUL-DT5417-ELCTHV-HVBLW | Main High Voltage Blower | 10618 | 10618 | 6500
500148131 | CLB-MP-HAUL-DT5417-ELCTHV-HVALT | High Voltage Alternator | 10618 | 10618 | 6500
500148130 | CLB-MP-HAUL-DT5417-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 10618 | 10618 | 6500
500148129 | CLB-MP-HAUL-DT5417-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 10618 | 10618 | 6500
500148128 | CLB-MP-HAUL-DT5417-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 10618 | 10618 | 6500
500148127 | CLB-MP-HAUL-DT5417-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 10618 | 10618 | 6500
500148126 | CLB-MP-HAUL-DT5417-BRKSYS-BRVTR | Brake Treadle Valve | 10618 | 10618 | 6500
500148125 | CLB-MP-HAUL-DT5417-BRKSYS-BRVRL | Brake Dual Relay Valves | 10618 | 10618 | 6500
500148124 | CLB-MP-HAUL-DT5417-BRKSYS-BRVLV | Brake & Steering Manifold | 10618 | 10618 | 6500
500148123 | CLB-MP-HAUL-DT5417-BRKSYS-BRSTV | Brake & Steering Valve | 10618 | 10618 | 6500
500148112 | CLB-MP-HAUL-DT5417-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 10618 | 10618 | 6500
500148111 | CLB-MP-HAUL-DT5417-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 10618 | 10618 | 6500
500148110 | CLB-MP-HAUL-DT5417-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 10618 | 10618 | 6500
500148109 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC | Accumulator Brake Supply Rr | 10618 | 10618 | 6500
500148108 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 10618 | 10618 | 6500
500148107 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC | Accumulator Brake Supply Fr | 10618 | 10618 | 6500
500148106 | CLB-MP-HAUL-DT5417-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 10618 | 10618 | 6500
500148105 | CLB-MP-HAUL-DT5417 | DT5417 Liebherr T264 OHT | 10618 | 10618 | 6500
500164596 | CLB-MP-HAUL-DT5416-STRSYS-STACC-SACRH | Accumulator Steering ODS | 10405 | 10405 | 6500
500164595 | CLB-MP-HAUL-DT5416-STRSYS-STACC-SACLH | Accumulator Steering DS | 10405 | 10405 | 6500
500164594 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 10405 | 10405 | 6500
500164593 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 10405 | 10405 | 6500
500164592 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 10405 | 10405 | 6500
500164591 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 10405 | 10405 | 6500
500149226 | CLB-MP-HAUL-DT5416-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 10405 | 10405 | 6500
500148104 | CLB-MP-HAUL-DT5416-STRUCT-TRAYS | Tray | 10405 | 10405 | 6500
500148103 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 10405 | 10405 | 6500
500148102 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 10405 | 1852 | 6500
500148101 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 10405 | 10405 | 6500
500148100 | CLB-MP-HAUL-DT5416-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 10405 | 1657 | 6500
500148099 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-SEATS | Operators Seat | 10405 | 1657 | 6500
500148098 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 10405 | 10405 | 6500
500148097 | CLB-MP-HAUL-DT5416-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 10405 | 10405 | 6500
500148096 | CLB-MP-HAUL-DT5416-STRUCT-CABIN | Operators Cabin | 10405 | 10405 | 6500
500148095 | CLB-MP-HAUL-DT5416-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 10405 | 10405 | 6500
500148094 | CLB-MP-HAUL-DT5416-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 10405 | 10405 | 6500
500148093 | CLB-MP-HAUL-DT5416-STRSYS-STVLV | Valve Flow Amplifier | 10405 | 10405 | 6500
500148092 | CLB-MP-HAUL-DT5416-STRSYS-STRIA | Steering Idler Arm | 10405 | 10405 | 6500
500148091 | CLB-MP-HAUL-DT5416-STRSYS-STRCY-STCYR | Steering Cylinder RH | 10405 | 10405 | 6500
500148090 | CLB-MP-HAUL-DT5416-STRSYS-STRCY-STCYL | Steering Cylinder LH | 10405 | 10405 | 6500
500148089 | CLB-MP-HAUL-DT5416-STRSYS-STLTR | Steering Linkages & Tie Rods | 10405 | 10405 | 6500
500148088 | CLB-MP-HAUL-DT5416-STRSYS-STCNT | Steering Control Unit | 10405 | 10405 | 6500
500148087 | CLB-MP-HAUL-DT5416-STRSYS-STACC | Accumulator Steering RHS | 10405 | 10405 | 6500
500148086 | CLB-MP-HAUL-DT5416-STRSYS-STACC | Accumulator Steering LHS | 10405 | 10405 | 6500
500148085 | CLB-MP-HAUL-DT5416-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 10405 | 10405 | 6500
500148084 | CLB-MP-HAUL-DT5416-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 10405 | 10405 | 6500
500148083 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 10405 | 10405 | 6500
500148082 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 10405 | 10405 | 6500
500148081 | CLB-MP-HAUL-DT5416-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 10405 | 10405 | 6500
500148080 | CLB-MP-HAUL-DT5416-HYDSYS-HYDOC | Hydraulic Oil Cooler | 10405 | 10405 | 6500
500148079 | CLB-MP-HAUL-DT5416-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 10405 | 10405 | 6500
500148078 | CLB-MP-HAUL-DT5416-HYDSYS-HOMAN | Hoist Manifold | 10405 | 10405 | 6500
500148077 | CLB-MP-HAUL-DT5416-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 10405 | 10405 | 6500
500148076 | CLB-MP-HAUL-DT5416-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 10405 | 10405 | 6500
500148075 | CLB-MP-HAUL-DT5416-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 10405 | 10405 | 6500
500148074 | CLB-MP-HAUL-DT5416-HYDSYS-GROCL | Gear Oil Cooler | 10405 | 10405 | 6500
500148073 | CLB-MP-HAUL-DT5416-GRSYST-ALBPP | Auto Lube Pump | 10405 | 10405 | 6500
500148072 | CLB-MP-HAUL-DT5416-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 10405 | 10405 | 6500
500148071 | CLB-MP-HAUL-DT5416-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 10405 | 10405 | 6500
500148070 | CLB-MP-HAUL-DT5416-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 10405 | 10405 | 6500
500148069 | CLB-MP-HAUL-DT5416-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 10405 | 10405 | 6500
500148068 | CLB-MP-HAUL-DT5416-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 10405 | 10405 | 6500
500148067 | CLB-MP-HAUL-DT5416-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 10405 | 10405 | 6500
500148066 | CLB-MP-HAUL-DT5416-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 10405 | 10405 | 6500
500148065 | CLB-MP-HAUL-DT5416-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 10405 | 10405 | 6500
500148064 | CLB-MP-HAUL-DT5416-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 10405 | 5411 | 6500
500148063 | CLB-MP-HAUL-DT5416-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 10405 | 10405 | 6500
500148062 | CLB-MP-HAUL-DT5416-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 10405 | 10405 | 6500
500148061 | CLB-MP-HAUL-DT5416-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 10405 | 10405 | 6500
500148060 | CLB-MP-HAUL-DT5416-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 10405 | 10405 | 6500
500148059 | CLB-MP-HAUL-DT5416-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 10405 | 10405 | 6500
500148058 | CLB-MP-HAUL-DT5416-ENGINE-INTEX-TBORF | Turbocharger RH Front | 10405 | 10405 | 6500
500148057 | CLB-MP-HAUL-DT5416-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 10405 | 10405 | 6500
500148056 | CLB-MP-HAUL-DT5416-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 10405 | 10405 | 6500
500148055 | CLB-MP-HAUL-DT5416-ENGINE-INTEX-AFTER | Aftercooler Engine | 10405 | 10405 | 6500
500148054 | CLB-MP-HAUL-DT5416-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 10405 | 10405 | 6500
500148053 | CLB-MP-HAUL-DT5416-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 10405 | 10405 | 6500
500148052 | CLB-MP-HAUL-DT5416-ENGINE-FUSYS-FUINJ | Fuel Injectors | 10405 | 10405 | 6500
500148051 | CLB-MP-HAUL-DT5416-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 10405 | 10405 | 6500
500148050 | CLB-MP-HAUL-DT5416-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 10405 | 10405 | 6500
500148049 | CLB-MP-HAUL-DT5416-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 10405 | 10405 | 6500
500148048 | CLB-MP-HAUL-DT5416-ENGINE-COSYS-HTWPP | Engine Water Pump | 10405 | 10405 | 6500
500148047 | CLB-MP-HAUL-DT5416-ENGINE-COSYS-COFAN | Fan Cooling System | 10405 | 10405 | 6500
500148046 | CLB-MP-HAUL-DT5416-ENGINE | Engine Assembly Cummins QSK60 | 10405 | 10405 | 6500
500148045 | CLB-MP-HAUL-DT5416-ELCTLV-START-STMUP | Starter Motor Upper | 10405 | 10405 | 6500
500148044 | CLB-MP-HAUL-DT5416-ELCTLV-START-STMLO | Starter Motor Lower | 10405 | 10405 | 6500
500148043 | CLB-MP-HAUL-DT5416-ELCTLV-HARNS | Electrical Harness | 10405 | 10405 | 6500
500148042 | CLB-MP-HAUL-DT5416-ELCTLV-CHARG-BATTY | Batteries | 10405 | 10405 | 6500
500148041 | CLB-MP-HAUL-DT5416-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 10405 | 10405 | 6500
500148040 | CLB-MP-HAUL-DT5416-ELCTHV-HVGBX-HVRES | Grid Resistors | 10405 | 10405 | 6500
500148039 | CLB-MP-HAUL-DT5416-ELCTHV-HVGBM | Grid Box Blower Motor | 10405 | 10405 | 6500
500148038 | CLB-MP-HAUL-DT5416-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 10405 | 10405 | 6500
500148037 | CLB-MP-HAUL-DT5416-ELCTHV-HVBLW | Main High Voltage Blower | 10405 | 10405 | 6500
500148036 | CLB-MP-HAUL-DT5416-ELCTHV-HVALT | High Voltage Alternator | 10405 | 10405 | 6500
500148035 | CLB-MP-HAUL-DT5416-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 10405 | 10405 | 6500
500148034 | CLB-MP-HAUL-DT5416-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 10405 | 10405 | 6500
500148033 | CLB-MP-HAUL-DT5416-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 10405 | 10405 | 6500
500148032 | CLB-MP-HAUL-DT5416-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 10405 | 7972 | 6500
500148031 | CLB-MP-HAUL-DT5416-BRKSYS-BRVTR | Brake Treadle Valve | 10405 | 10405 | 6500
500148030 | CLB-MP-HAUL-DT5416-BRKSYS-BRVRL | Brake Dual Relay Valves | 10405 | 10405 | 6500
500148029 | CLB-MP-HAUL-DT5416-BRKSYS-BRVLV | Brake & Steering Manifold | 10405 | 10405 | 6500
500148028 | CLB-MP-HAUL-DT5416-BRKSYS-BRSTV | Brake & Steering Valve | 10405 | 10405 | 6500
500148027 | CLB-MP-HAUL-DT5416-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 10405 | 10405 | 6500
500148026 | CLB-MP-HAUL-DT5416-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 10405 | 10405 | 6500
500148025 | CLB-MP-HAUL-DT5416-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 10405 | 10405 | 6500
500148024 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC | Accumulator Brake Supply Rr | 10405 | 10405 | 6500
500148023 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 10405 | 10405 | 6500
500146672 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC | Accumulator Brake Supply Fr | 10405 | 10405 | 6500
500146671 | CLB-MP-HAUL-DT5416-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 10405 | 10405 | 6500
500146670 | CLB-MP-HAUL-DT5416 | DT5416 Liebherr T264 OHT | 10405 | 10405 | 6500
500164590 | CLB-MP-HAUL-DT5411-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8255 | 8255 | 6500
500164589 | CLB-MP-HAUL-DT5411-STRSYS-STACC-SACLH | Accumulator Steering DS | 8255 | 8255 | 6500
500164588 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8255 | 8255 | 6500
500164587 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8255 | 8255 | 6500
500164586 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8255 | 8255 | 6500
500164585 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8255 | 8255 | 6500
500149225 | CLB-MP-HAUL-DT5411-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8255 | 8255 | 6500
500141027 | CLB-MP-HAUL-DT5411-STRSYS-STACC | Accumulator Steering RHS | 8255 | 8255 | 6500
500141026 | CLB-MP-HAUL-DT5411-STRSYS-STACC | Accumulator Steering LHS | 8255 | 8255 | 6500
500141025 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC | Accumulator Brake Supply Rr | 8255 | 8255 | 6500
500141024 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8255 | 8255 | 6500
500141023 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC | Accumulator Brake Supply Fr | 8255 | 8255 | 6500
500141022 | CLB-MP-HAUL-DT5411-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 8255 | 8255 | 6500
500141021 | CLB-MP-HAUL-DT5411-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8255 | 8255 | 6500
500141020 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8255 | 8255 | 6500
500141019 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8255 | 8255 | 6500
500141018 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8255 | 8255 | 6500
500141017 | CLB-MP-HAUL-DT5411-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8255 | 8255 | 6500
500141016 | CLB-MP-HAUL-DT5411-STRUCT-TRAYS | Tray | 8255 | 8255 | 6500
500141015 | CLB-MP-HAUL-DT5411-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8255 | 8255 | 6500
500141014 | CLB-MP-HAUL-DT5411-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8255 | 8255 | 6500
500141013 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-SEATS | Operators Seat | 8255 | 8255 | 6500
500141012 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8255 | 8255 | 6500
500141011 | CLB-MP-HAUL-DT5411-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8255 | 8255 | 6500
500141010 | CLB-MP-HAUL-DT5411-STRUCT-CABIN | Operators Cabin | 8255 | 8255 | 6500
500141009 | CLB-MP-HAUL-DT5411-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8255 | 8255 | 6500
500141008 | CLB-MP-HAUL-DT5411-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8255 | 8255 | 6500
500141007 | CLB-MP-HAUL-DT5411-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8255 | 8255 | 6500
500141006 | CLB-MP-HAUL-DT5411-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8255 | 8255 | 6500
500141005 | CLB-MP-HAUL-DT5411-HYDSYS-HOMAN | Hoist Manifold | 8255 | 8255 | 6500
500141004 | CLB-MP-HAUL-DT5411-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8255 | 8255 | 6500
500141003 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8255 | 8255 | 6500
500141002 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8255 | 8255 | 6500
500141001 | CLB-MP-HAUL-DT5411-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steering | 8255 | 8255 | 6500
500141000 | CLB-MP-HAUL-DT5411-HYDSYS-GROCL | Gear Oil Cooler | 8255 | 8255 | 6500
500140999 | CLB-MP-HAUL-DT5411-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8255 | 8255 | 6500
500140998 | CLB-MP-HAUL-DT5411-GRSYST-ALBPP | Auto Lube Pump | 8255 | 8255 | 6500
500140997 | CLB-MP-HAUL-DT5411-STRSYS-STRIA | Steering Idler Arm | 8255 | 8255 | 6500
500140996 | CLB-MP-HAUL-DT5411-STRSYS-STLTR | Steering Linkages & Tie Rods | 8255 | 8255 | 6500
500140995 | CLB-MP-HAUL-DT5411-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8255 | 8255 | 6500
500140994 | CLB-MP-HAUL-DT5411-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8255 | 8255 | 6500
500140993 | CLB-MP-HAUL-DT5411-STRSYS-STCNT | Steering Control Unit | 8255 | 8255 | 6500
500140992 | CLB-MP-HAUL-DT5411-STRSYS-STVLV | Valve Flow Amplifier | 8255 | 8255 | 6500
500140991 | CLB-MP-HAUL-DT5411-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8255 | 8255 | 6500
500140990 | CLB-MP-HAUL-DT5411-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8255 | 8255 | 6500
500140989 | CLB-MP-HAUL-DT5411-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8255 | 8255 | 6500
500140988 | CLB-MP-HAUL-DT5411-BRKSYS-BRVTR | Brake Treadle Valve | 8255 | 8255 | 6500
500140987 | CLB-MP-HAUL-DT5411-BRKSYS-BRSTV | Brake & Steering Valve | 8255 | 8255 | 6500
500140986 | CLB-MP-HAUL-DT5411-BRKSYS-BRVLV | Brake & Steering Manifold | 8255 | 8255 | 6500
500140985 | CLB-MP-HAUL-DT5411-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8255 | 8255 | 6500
500140984 | CLB-MP-HAUL-DT5411-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8255 | 8255 | 6500
500140983 | CLB-MP-HAUL-DT5411-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8255 | 8255 | 6500
500140982 | CLB-MP-HAUL-DT5411-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8255 | 8255 | 6500
500140981 | CLB-MP-HAUL-DT5411-BRKSYS-BRVRL | Brake Dual Relay Valves | 8255 | 8255 | 6500
500140980 | CLB-MP-HAUL-DT5411-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8255 | 8255 | 6500
500140979 | CLB-MP-HAUL-DT5411-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8255 | 8255 | 6500
500140978 | CLB-MP-HAUL-DT5411-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8255 | 8255 | 6500
500140977 | CLB-MP-HAUL-DT5411-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8255 | 8255 | 6500
500140976 | CLB-MP-HAUL-DT5411-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8255 | 8255 | 6500
500140975 | CLB-MP-HAUL-DT5411-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8255 | 8255 | 6500
500140974 | CLB-MP-HAUL-DT5411-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8255 | 8255 | 6500
500140973 | CLB-MP-HAUL-DT5411-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8255 | 8255 | 6500
500140972 | CLB-MP-HAUL-DT5411-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8255 | 8255 | 6500
500140971 | CLB-MP-HAUL-DT5411-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8255 | 8255 | 6500
500140970 | CLB-MP-HAUL-DT5411-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8255 | 8255 | 6500
500140969 | CLB-MP-HAUL-DT5411-ELCTHV-HVBLW | Main High Voltage Blower | 8255 | 8255 | 6500
500140968 | CLB-MP-HAUL-DT5411-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8255 | 8255 | 6500
500140967 | CLB-MP-HAUL-DT5411-ELCTHV-HVALT | High Voltage Alternator | 8255 | 8255 | 6500
500140966 | CLB-MP-HAUL-DT5411-ELCTHV-HVGBM | Grid Box Blower Motor | 8255 | 8255 | 6500
500140965 | CLB-MP-HAUL-DT5411-ELCTHV-HVGBX-HVRES | Grid Resistors | 8255 | 8255 | 6500
500140964 | CLB-MP-HAUL-DT5411-ELCTLV-START-STMUP | Starter Motor Upper | 8255 | 8255 | 6500
500140963 | CLB-MP-HAUL-DT5411-ELCTLV-START-STMLO | Starter Motor Lower | 8255 | 8255 | 6500
500140962 | CLB-MP-HAUL-DT5411-ELCTLV-CHARG-BATTY | Batteries | 8255 | 8255 | 6500
500140961 | CLB-MP-HAUL-DT5411-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8255 | 8255 | 6500
500140960 | CLB-MP-HAUL-DT5411-ELCTLV-HARNS | Electrical Harness | 8255 | 8255 | 6500
500140959 | CLB-MP-HAUL-DT5411-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8255 | 8255 | 6500
500140958 | CLB-MP-HAUL-DT5411-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8255 | 8255 | 6500
500140957 | CLB-MP-HAUL-DT5411-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8255 | 8255 | 6500
500140956 | CLB-MP-HAUL-DT5411-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8255 | 8255 | 6500
500140955 | CLB-MP-HAUL-DT5411-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8255 | 8255 | 6500
500140954 | CLB-MP-HAUL-DT5411-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8255 | 8255 | 6500
500140953 | CLB-MP-HAUL-DT5411-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8255 | 8255 | 6500
500140952 | CLB-MP-HAUL-DT5411-ENGINE-INTEX-AFTER | Aftercooler Engine | 8255 | 8255 | 6500
500140951 | CLB-MP-HAUL-DT5411-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8255 | 8255 | 6500
500140950 | CLB-MP-HAUL-DT5411-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8255 | 8255 | 6500
500140949 | CLB-MP-HAUL-DT5411-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8255 | 8255 | 6500
500140948 | CLB-MP-HAUL-DT5411-ENGINE-COSYS-HTWPP | Engine Water Pump | 8255 | 8255 | 6500
500140947 | CLB-MP-HAUL-DT5411-ENGINE-COSYS-COFAN | Fan Cooling System | 8255 | 8255 | 6500
500140946 | CLB-MP-HAUL-DT5411-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8255 | 8255 | 6500
500140945 | CLB-MP-HAUL-DT5411-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8255 | 8255 | 6500
500140944 | CLB-MP-HAUL-DT5411-ENGINE | Engine Assembly Cummins QSK60 | 8255 | 8255 | 6500
500140943 | CLB-MP-HAUL-DT5411 | DT5411 Liebherr T264 OHT | 8255 | 8255 | 6500
500164584 | CLB-MP-HAUL-DT5410-STRSYS-STACC-SACRH | Accumulator Steering ODS | 10949 | 10949 | 6500
500164583 | CLB-MP-HAUL-DT5410-STRSYS-STACC-SACLH | Accumulator Steering DS | 10949 | 10949 | 6500
500164582 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 10949 | 10949 | 6500
500164581 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 10949 | 10949 | 6500
500164580 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 10949 | 10949 | 6500
500164579 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 10949 | 10949 | 6500
500149224 | CLB-MP-HAUL-DT5410-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 10949 | 10949 | 6500
500140919 | CLB-MP-HAUL-DT5410-STRSYS-STACC | Accumulator Steering RHS | 10949 | 10949 | 6500
500140918 | CLB-MP-HAUL-DT5410-STRSYS-STACC | Accumulator Steering LHS | 10949 | 10949 | 6500
500140917 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC | Accumulator Brake Supply Rr | 10949 | 10949 | 6500
500140916 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 10949 | 10949 | 6500
500140915 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC | Accumulator Brake Supply Fr | 10949 | 10949 | 6500
500140914 | CLB-MP-HAUL-DT5410-BRKSYS-BRACC | Accumulator Brake Pilot Fr | 10949 | 10949 | 6500
500140913 | CLB-MP-HAUL-DT5410-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 10949 | 10949 | 6500
500140912 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 10949 | 10949 | 6500
500140911 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 10949 | 10949 | 6500
500140910 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 10949 | 10949 | 6500
500140909 | CLB-MP-HAUL-DT5410-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 10949 | 10949 | 6500
500140908 | CLB-MP-HAUL-DT5410-STRUCT-TRAYS | Tray | 10949 | 10949 | 6500
500140907 | CLB-MP-HAUL-DT5410-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 10949 | 10949 | 6500
500140906 | CLB-MP-HAUL-DT5410-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 10949 | 10949 | 6500
500140905 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-SEATS | Operators Seat | 10949 | 3771 | 6500
500140904 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 10949 | 10949 | 6500
500140903 | CLB-MP-HAUL-DT5410-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 10949 | 10949 | 6500
500140902 | CLB-MP-HAUL-DT5410-STRUCT-CABIN | Operators Cabin | 10949 | 10949 | 6500
500140901 | CLB-MP-HAUL-DT5410-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 10949 | 10949 | 6500
500140900 | CLB-MP-HAUL-DT5410-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 10949 | 10949 | 6500
500140899 | CLB-MP-HAUL-DT5410-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 10949 | 10949 | 6500
500140898 | CLB-MP-HAUL-DT5410-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 10949 | 10949 | 6500
500140897 | CLB-MP-HAUL-DT5410-HYDSYS-HOMAN | Hoist Manifold | 10949 | 10949 | 6500
500140896 | CLB-MP-HAUL-DT5410-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 10949 | 10949 | 6500
500140895 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 10949 | 10949 | 6500
500140894 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 10949 | 10949 | 6500
500140893 | CLB-MP-HAUL-DT5410-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steer | 10949 | 5822 | 6500
500140892 | CLB-MP-HAUL-DT5410-HYDSYS-GROCL | Gear Oil Cooler | 10949 | 10949 | 6500
500140891 | CLB-MP-HAUL-DT5410-HYDSYS-HYDOC | Hydraulic Oil Cooler | 10949 | 10949 | 6500
500140890 | CLB-MP-HAUL-DT5410-GRSYST-ALBPP | Auto Lube Pump | 10949 | 10949 | 6500
500140889 | CLB-MP-HAUL-DT5410-STRSYS-STRIA | Steering Idler Arm | 10949 | 10949 | 6500
500140888 | CLB-MP-HAUL-DT5410-STRSYS-STLTR | Steering Linkages & Tie Rods | 10949 | 10949 | 6500
500140887 | CLB-MP-HAUL-DT5410-STRSYS-STRCY-STCYR | Steering Cylinder RH | 10949 | 10949 | 6500
500140886 | CLB-MP-HAUL-DT5410-STRSYS-STRCY-STCYL | Steering Cylinder LH | 10949 | 10949 | 6500
500140885 | CLB-MP-HAUL-DT5410-STRSYS-STCNT | Steering Control Unit | 10949 | 10949 | 6500
500140884 | CLB-MP-HAUL-DT5410-STRSYS-STVLV | Valve Flow Amplifier | 10949 | 10949 | 6500
500140883 | CLB-MP-HAUL-DT5410-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 10949 | 10949 | 6500
500140882 | CLB-MP-HAUL-DT5410-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 10949 | 10949 | 6500
500140881 | CLB-MP-HAUL-DT5410-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 10949 | 10949 | 6500
500140880 | CLB-MP-HAUL-DT5410-BRKSYS-BRVTR | Brake Treadle Valve | 10949 | 10949 | 6500
500140879 | CLB-MP-HAUL-DT5410-BRKSYS-BRSTV | Brake & Steering Valve | 10949 | 10949 | 6500
500140878 | CLB-MP-HAUL-DT5410-BRKSYS-BRVLV | Brake & Steering Manifold | 10949 | 10949 | 6500
500140877 | CLB-MP-HAUL-DT5410-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 10949 | 10949 | 6500
500140876 | CLB-MP-HAUL-DT5410-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 10949 | 10949 | 6500
500140875 | CLB-MP-HAUL-DT5410-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 10949 | 10949 | 6500
500140874 | CLB-MP-HAUL-DT5410-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 10949 | 10949 | 6500
500140873 | CLB-MP-HAUL-DT5410-BRKSYS-BRVRL | Brake Dual Relay Valves | 10949 | 10949 | 6500
500140872 | CLB-MP-HAUL-DT5410-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 10949 | 10949 | 6500
500140871 | CLB-MP-HAUL-DT5410-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 10949 | 10949 | 6500
500140870 | CLB-MP-HAUL-DT5410-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 10949 | 10949 | 6500
500140869 | CLB-MP-HAUL-DT5410-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 10949 | 10949 | 6500
500140868 | CLB-MP-HAUL-DT5410-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 10949 | 10949 | 6500
500140867 | CLB-MP-HAUL-DT5410-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 10949 | 10949 | 6500
500140866 | CLB-MP-HAUL-DT5410-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 10949 | 10949 | 6500
500140865 | CLB-MP-HAUL-DT5410-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 10949 | 10949 | 6500
500140864 | CLB-MP-HAUL-DT5410-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 10949 | 10949 | 6500
500140863 | CLB-MP-HAUL-DT5410-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 10949 | 10949 | 6500
500140862 | CLB-MP-HAUL-DT5410-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 10949 | 10949 | 6500
500140861 | CLB-MP-HAUL-DT5410-ELCTHV-HVBLW | Main High Voltage Blower | 10949 | 10949 | 6500
500140860 | CLB-MP-HAUL-DT5410-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 10949 | 10949 | 6500
500140859 | CLB-MP-HAUL-DT5410-ELCTHV-HVALT | High Voltage Alternator | 10949 | 10949 | 6500
500140858 | CLB-MP-HAUL-DT5410-ELCTHV-HVGBM | Grid Box Blower Motor | 10949 | 10949 | 6500
500140857 | CLB-MP-HAUL-DT5410-ELCTHV-HVGBX-HVRES | Grid Resistors | 10949 | 10949 | 6500
500140856 | CLB-MP-HAUL-DT5410-ELCTLV-START-STMUP | Starter Motor Upper | 10949 | 10949 | 6500
500140855 | CLB-MP-HAUL-DT5410-ELCTLV-START-STMLO | Starter Motor Lower | 10949 | 10949 | 6500
500140854 | CLB-MP-HAUL-DT5410-ELCTLV-CHARG-BATTY | Batteries | 10949 | 4855 | 6500
500140853 | CLB-MP-HAUL-DT5410-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 10949 | 10949 | 6500
500140852 | CLB-MP-HAUL-DT5410-ELCTLV-HARNS | Electrical Harness | 10949 | 10949 | 6500
500140851 | CLB-MP-HAUL-DT5410-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 10949 | 10949 | 6500
500140850 | CLB-MP-HAUL-DT5410-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 10949 | 10949 | 6500
500140849 | CLB-MP-HAUL-DT5410-ENGINE-FUSYS-FUINJ | Fuel Injectors | 10949 | 10949 | 6500
500140848 | CLB-MP-HAUL-DT5410-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 10949 | 10949 | 6500
500140847 | CLB-MP-HAUL-DT5410-ENGINE-INTEX-TBORF | Turbocharger RH Front | 10949 | 10949 | 6500
500140846 | CLB-MP-HAUL-DT5410-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 10949 | 10949 | 6500
500140845 | CLB-MP-HAUL-DT5410-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 10949 | 10949 | 6500
500140844 | CLB-MP-HAUL-DT5410-ENGINE-INTEX-AFTER | Aftercooler Engine | 10949 | 10949 | 6500
500140843 | CLB-MP-HAUL-DT5410-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 10949 | 10949 | 6500
500140842 | CLB-MP-HAUL-DT5410-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 10949 | 10949 | 6500
500140841 | CLB-MP-HAUL-DT5410-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 10949 | 10949 | 6500
500140840 | CLB-MP-HAUL-DT5410-ENGINE-COSYS-HTWPP | Engine Water Pump | 10949 | 10949 | 6500
500140839 | CLB-MP-HAUL-DT5410-ENGINE-COSYS-COFAN | Fan Cooling System | 10949 | 10949 | 6500
500140838 | CLB-MP-HAUL-DT5410-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 10949 | 10949 | 6500
500140837 | CLB-MP-HAUL-DT5410-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 10949 | 10949 | 6500
500140836 | CLB-MP-HAUL-DT5410-ENGINE | Engine Assembly Cummins QSK60 | 10949 | 10949 | 6500
500140835 | CLB-MP-HAUL-DT5410 | DT5410 Liebherr T264 OHT | 10949 | 10949 | 6500
500164578 | CLB-MP-HAUL-DT5405-STRSYS-STACC-SACRH | Accumulator Steering ODS | 11503 | 11503 | 6500
500164577 | CLB-MP-HAUL-DT5405-STRSYS-STACC-SACLH | Accumulator Steering DS | 11503 | 11503 | 6500
500164576 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 11503 | 11503 | 6500
500164575 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 11503 | 11503 | 6500
500164574 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 11503 | 11503 | 6500
500164573 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 11503 | 11503 | 6500
500149223 | CLB-MP-HAUL-DT5405-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 11503 | 11503 | 6500
500140790 | CLB-MP-HAUL-DT5405-STRSYS-STACC | Accumulator Steering RHS | 11503 | 11503 | 6500
500140789 | CLB-MP-HAUL-DT5405-STRSYS-STACC | Accumulator Steering LHS | 11503 | 11503 | 6500
500140788 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC | Accumulator Brake Supply Rear | 11503 | 11503 | 6500
500140787 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 11503 | 11503 | 6500
500140786 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC | Accumulator Brake Supply Front | 11503 | 11503 | 6500
500140785 | CLB-MP-HAUL-DT5405-BRKSYS-BRACC | Accumulator Brake Pilot Front | 11503 | 11503 | 6500
500140784 | CLB-MP-HAUL-DT5405-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 11503 | 11503 | 6500
500140783 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 11503 | 11503 | 6500
500140782 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 11503 | 11503 | 6500
500140781 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 11503 | 11503 | 6500
500140780 | CLB-MP-HAUL-DT5405-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 11503 | 11503 | 6500
500140779 | CLB-MP-HAUL-DT5405-STRUCT-TRAYS | Tray | 11503 | 11503 | 6500
500140778 | CLB-MP-HAUL-DT5405-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 11503 | 11503 | 6500
500140777 | CLB-MP-HAUL-DT5405-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 11503 | 11503 | 6500
500140776 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-SEATS | Operators Seat | 11503 | 11503 | 6500
500140775 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 11503 | 11503 | 6500
500140774 | CLB-MP-HAUL-DT5405-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 11503 | 11503 | 6500
500140773 | CLB-MP-HAUL-DT5405-STRUCT-CABIN | Operators Cabin | 11503 | 11503 | 6500
500140772 | CLB-MP-HAUL-DT5405-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 11503 | 11503 | 6500
500140771 | CLB-MP-HAUL-DT5405-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 11503 | 11503 | 6500
500140770 | CLB-MP-HAUL-DT5405-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 11503 | 11503 | 6500
500140769 | CLB-MP-HAUL-DT5405-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 11503 | 11503 | 6500
500140768 | CLB-MP-HAUL-DT5405-HYDSYS-HOMAN | Hoist Manifold | 11503 | 11503 | 6500
500140767 | CLB-MP-HAUL-DT5405-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 11503 | 11503 | 6500
500140766 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 11503 | 11503 | 6500
500140765 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 11503 | 11503 | 6500
500140764 | CLB-MP-HAUL-DT5405-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steer | 11503 | 11503 | 6500
500140763 | CLB-MP-HAUL-DT5405-HYDSYS-GROCL | Gear Oil Cooler | 11503 | 11503 | 6500
500140762 | CLB-MP-HAUL-DT5405-HYDSYS-HYDOC | Hydraulic Oil Cooler | 11503 | 11503 | 6500
500140761 | CLB-MP-HAUL-DT5405-GRSYST-ALBPP | Auto Lube Pump | 11503 | 11503 | 6500
500140760 | CLB-MP-HAUL-DT5405-STRSYS-STRIA | Steering Idler Arm | 11503 | 11503 | 6500
500140759 | CLB-MP-HAUL-DT5405-STRSYS-STLTR | Steering Linkages & Tie Rods | 11503 | 11503 | 6500
500140758 | CLB-MP-HAUL-DT5405-STRSYS-STRCY-STCYR | Steering Cylinder RH | 11503 | 11503 | 6500
500140757 | CLB-MP-HAUL-DT5405-STRSYS-STRCY-STCYL | Steering Cylinder LH | 11503 | 11503 | 6500
500140756 | CLB-MP-HAUL-DT5405-STRSYS-STCNT | Steering Control Unit | 11503 | 11503 | 6500
500140755 | CLB-MP-HAUL-DT5405-STRSYS-STVLV | Valve Flow Amplifier | 11503 | 11503 | 6500
500140754 | CLB-MP-HAUL-DT5405-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 11503 | 11503 | 6500
500140753 | CLB-MP-HAUL-DT5405-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 11503 | 11503 | 6500
500140752 | CLB-MP-HAUL-DT5405-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 11503 | 11503 | 6500
500140751 | CLB-MP-HAUL-DT5405-BRKSYS-BRVTR | Brake Treadle Valve | 11503 | 11503 | 6500
500140750 | CLB-MP-HAUL-DT5405-BRKSYS-BRSTV | Brake & Steering Valve | 11503 | 11503 | 6500
500140749 | CLB-MP-HAUL-DT5405-BRKSYS-BRVLV | Brake & Steering Manifold | 11503 | 11503 | 6500
500140748 | CLB-MP-HAUL-DT5405-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 11503 | 11503 | 6500
500140747 | CLB-MP-HAUL-DT5405-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 11503 | 11503 | 6500
500140746 | CLB-MP-HAUL-DT5405-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 11503 | 11503 | 6500
500140745 | CLB-MP-HAUL-DT5405-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 11503 | 11503 | 6500
500140744 | CLB-MP-HAUL-DT5405-BRKSYS-BRVRL | Brake Dual Relay Valves | 11503 | 11503 | 6500
500140743 | CLB-MP-HAUL-DT5405-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 11503 | 11503 | 6500
500140742 | CLB-MP-HAUL-DT5405-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 11503 | 11503 | 6500
500140741 | CLB-MP-HAUL-DT5405-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 11503 | 11503 | 6500
500140740 | CLB-MP-HAUL-DT5405-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 11503 | 11503 | 6500
500140739 | CLB-MP-HAUL-DT5405-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 11503 | 11503 | 6500
500140738 | CLB-MP-HAUL-DT5405-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 11503 | 11503 | 6500
500140737 | CLB-MP-HAUL-DT5405-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 11503 | 11503 | 6500
500140736 | CLB-MP-HAUL-DT5405-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 11503 | 11503 | 6500
500140735 | CLB-MP-HAUL-DT5405-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 11503 | 11503 | 6500
500140734 | CLB-MP-HAUL-DT5405-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 11503 | 4657 | 6500
500140733 | CLB-MP-HAUL-DT5405-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 11503 | 11503 | 6500
500140732 | CLB-MP-HAUL-DT5405-ELCTHV-HVBLW | Main High Voltage Blower | 11503 | 7938 | 6500
500140731 | CLB-MP-HAUL-DT5405-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 11503 | 11503 | 6500
500140730 | CLB-MP-HAUL-DT5405-ELCTHV-HVALT | High Voltage Alternator | 11503 | 11503 | 6500
500140729 | CLB-MP-HAUL-DT5405-ELCTHV-HVGBM | Grid Box Blower Motor | 11503 | 11503 | 6500
500140728 | CLB-MP-HAUL-DT5405-ELCTHV-HVGBX-HVRES | Grid Resistors | 11503 | 11503 | 6500
500140727 | CLB-MP-HAUL-DT5405-ELCTLV-START-STMUP | Starter Motor Upper | 11503 | 11503 | 6500
500140726 | CLB-MP-HAUL-DT5405-ELCTLV-START-STMLO | Starter Motor Lower | 11503 | 11503 | 6500
500140725 | CLB-MP-HAUL-DT5405-ELCTLV-CHARG-BATTY | Batteries | 11503 | 11503 | 6500
500140724 | CLB-MP-HAUL-DT5405-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 11503 | 11503 | 6500
500140723 | CLB-MP-HAUL-DT5405-ELCTLV-HARNS | Electrical Harness | 11503 | 11503 | 6500
500140720 | CLB-MP-HAUL-DT5405-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 11503 | 11503 | 6500
500140719 | CLB-MP-HAUL-DT5405-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 11503 | 11503 | 6500
500140718 | CLB-MP-HAUL-DT5405-ENGINE-FUSYS-FUINJ | Fuel Injectors | 11503 | 11503 | 6500
500140717 | CLB-MP-HAUL-DT5405-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 11503 | 11503 | 6500
500140716 | CLB-MP-HAUL-DT5405-ENGINE-INTEX-TBORF | Turbocharger RH Front | 11503 | 11503 | 6500
500140715 | CLB-MP-HAUL-DT5405-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 11503 | 11503 | 6500
500140714 | CLB-MP-HAUL-DT5405-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 11503 | 11503 | 6500
500140713 | CLB-MP-HAUL-DT5405-ENGINE-INTEX-AFTER | Aftercooler Engine | 11503 | 11503 | 6500
500140712 | CLB-MP-HAUL-DT5405-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 11503 | 11503 | 6500
500140711 | CLB-MP-HAUL-DT5405-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 11503 | 11503 | 6500
500140710 | CLB-MP-HAUL-DT5405-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 11503 | 11503 | 6500
500140709 | CLB-MP-HAUL-DT5405-ENGINE-COSYS-HTWPP | Engine Water Pump | 11503 | 11503 | 6500
500140708 | CLB-MP-HAUL-DT5405-ENGINE-COSYS-COFAN | Fan Cooling System | 11503 | 11503 | 6500
500140707 | CLB-MP-HAUL-DT5405-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 11503 | 11503 | 6500
500140706 | CLB-MP-HAUL-DT5405-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 11503 | 11503 | 6500
500140705 | CLB-MP-HAUL-DT5405-ENGINE | Engine Assembly Cummins QSK60 | 11503 | 11503 | 6500
500140704 | CLB-MP-HAUL-DT5405 | DT5405 Liebherr T264 OHT | 11503 | 11503 | 6500
500164572 | CLB-MP-HAUL-DT5404-STRSYS-STACC-SACRH | Accumulator Steering ODS | 8870 | 8870 | 6500
500164571 | CLB-MP-HAUL-DT5404-STRSYS-STACC-SACLH | Accumulator Steering DS | 8870 | 8870 | 6500
500164570 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 8870 | 8870 | 6500
500164569 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 8870 | 8870 | 6500
500164568 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 8870 | 8870 | 6500
500164567 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 8870 | 8870 | 6500
500149072 | CLB-MP-HAUL-DT5404-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 8870 | 8870 | 6500
500140677 | CLB-MP-HAUL-DT5404-STRSYS-STACC | Accumulator Steering RHS | 8870 | 8870 | 6500
500140676 | CLB-MP-HAUL-DT5404-STRSYS-STACC | Accumulator Steering LHS | 8870 | 8870 | 6500
500140675 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC | Accumulator Brake Supply Rear | 8870 | 8870 | 6500
500140674 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC | Accumulator Brake Pilot Rear | 8870 | 8870 | 6500
500140673 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC | Accumulator Brake Supply Front | 8870 | 8870 | 6500
500140672 | CLB-MP-HAUL-DT5404-BRKSYS-BRACC | Accumulator Brake Pilot Front | 8870 | 8870 | 6500
500140671 | CLB-MP-HAUL-DT5404-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 8870 | 8870 | 6500
500140670 | CLB-MP-HAUL-DT5404-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 8870 | 8870 | 6500
500140669 | CLB-MP-HAUL-DT5404-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 8870 | 8870 | 6500
500140668 | CLB-MP-HAUL-DT5404-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 8870 | 8870 | 6500
500140667 | CLB-MP-HAUL-DT5404-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 8870 | 1083 | 6500
500140666 | CLB-MP-HAUL-DT5404-STRUCT-TRAYS | Tray | 8870 | 8870 | 6500
500140665 | CLB-MP-HAUL-DT5404-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 8870 | 8870 | 6500
500140664 | CLB-MP-HAUL-DT5404-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 8870 | 8870 | 6500
500140663 | CLB-MP-HAUL-DT5404-STRUCT-CABIN-SEATS | Operators Seat | 8870 | 1481 | 6500
500140662 | CLB-MP-HAUL-DT5404-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 8870 | 8870 | 6500
500140661 | CLB-MP-HAUL-DT5404-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 8870 | 8870 | 6500
500140660 | CLB-MP-HAUL-DT5404-STRUCT-CABIN | Operators Cabin | 8870 | 8870 | 6500
500140659 | CLB-MP-HAUL-DT5404-HYDSYS-HDHLF | Hydraulic System Hoses Lines & Fittings | 8870 | 8870 | 6500
500140658 | CLB-MP-HAUL-DT5404-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 8870 | 8870 | 6500
500140657 | CLB-MP-HAUL-DT5404-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 8870 | 8870 | 6500
500140656 | CLB-MP-HAUL-DT5404-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 8870 | 8870 | 6500
500140655 | CLB-MP-HAUL-DT5404-HYDSYS-HOMAN | Hoist Manifold | 8870 | 8870 | 6500
500140654 | CLB-MP-HAUL-DT5404-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 8870 | 8870 | 6500
500140653 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 8870 | 8870 | 6500
500140652 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 8870 | 8870 | 6500
500140651 | CLB-MP-HAUL-DT5404-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steer | 8870 | 8870 | 6500
500140650 | CLB-MP-HAUL-DT5404-HYDSYS-GROCL | Gear Oil Cooler | 8870 | 8870 | 6500
500140649 | CLB-MP-HAUL-DT5404-HYDSYS-HYDOC | Hydraulic Oil Cooler | 8870 | 8870 | 6500
500140648 | CLB-MP-HAUL-DT5404-GRSYST-ALBPP | Auto Lube Pump | 8870 | 8870 | 6500
500140647 | CLB-MP-HAUL-DT5404-STRSYS-STRIA | Steering Idler Arm | 8870 | 8870 | 6500
500140646 | CLB-MP-HAUL-DT5404-STRSYS-STLTR | Steering Linkages & Tie Rods | 8870 | 8870 | 6500
500140645 | CLB-MP-HAUL-DT5404-STRSYS-STRCY-STCYR | Steering Cylinder RH | 8870 | 8870 | 6500
500140644 | CLB-MP-HAUL-DT5404-STRSYS-STRCY-STCYL | Steering Cylinder LH | 8870 | 8870 | 6500
500140643 | CLB-MP-HAUL-DT5404-STRSYS-STCNT | Steering Control Unit | 8870 | 8870 | 6500
500140642 | CLB-MP-HAUL-DT5404-STRSYS-STVLV | Valve Flow Amplifier | 8870 | 8870 | 6500
500140641 | CLB-MP-HAUL-DT5404-BRKSYS-BRHLF | Brake System Hoses Lines & Fittings | 8870 | 8870 | 6500
500140640 | CLB-MP-HAUL-DT5404-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 8870 | 8870 | 6500
500140639 | CLB-MP-HAUL-DT5404-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 8870 | 8870 | 6500
500140638 | CLB-MP-HAUL-DT5404-BRKSYS-BRVTR | Brake Treadle Valve | 8870 | 8870 | 6500
500140637 | CLB-MP-HAUL-DT5404-BRKSYS-BRSTV | Brake & Steering Valve | 8870 | 8870 | 6500
500140636 | CLB-MP-HAUL-DT5404-BRKSYS-BRVLV | Brake & Steering Manifold | 8870 | 8870 | 6500
500140635 | CLB-MP-HAUL-DT5404-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 8870 | 8870 | 6500
500140634 | CLB-MP-HAUL-DT5404-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 8870 | 8870 | 6500
500140633 | CLB-MP-HAUL-DT5404-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 8870 | 8870 | 6500
500140632 | CLB-MP-HAUL-DT5404-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 8870 | 8870 | 6500
500140631 | CLB-MP-HAUL-DT5404-BRKSYS-BRVRL | Brake Dual Relay Valves | 8870 | 8870 | 6500
500140630 | CLB-MP-HAUL-DT5404-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 8870 | 8870 | 6500
500140629 | CLB-MP-HAUL-DT5404-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 8870 | 8870 | 6500
500140628 | CLB-MP-HAUL-DT5404-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 8870 | 8870 | 6500
500140627 | CLB-MP-HAUL-DT5404-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 8870 | 8870 | 6500
500140626 | CLB-MP-HAUL-DT5404-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 8870 | 8870 | 6500
500140625 | CLB-MP-HAUL-DT5404-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 8870 | 8870 | 6500
500140624 | CLB-MP-HAUL-DT5404-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 8870 | 8870 | 6500
500140623 | CLB-MP-HAUL-DT5404-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 8870 | 3619 | 6500
500140622 | CLB-MP-HAUL-DT5404-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 8870 | 8870 | 6500
500140621 | CLB-MP-HAUL-DT5404-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 8870 | 8870 | 6500
500140620 | CLB-MP-HAUL-DT5404-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 8870 | 8870 | 6500
500140619 | CLB-MP-HAUL-DT5404-ELCTHV-HVBLW | Main High Voltage Blower | 8870 | 8870 | 6500
500140618 | CLB-MP-HAUL-DT5404-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 8870 | 8870 | 6500
500140617 | CLB-MP-HAUL-DT5404-ELCTHV-HVALT | High Voltage Alternator | 8870 | 8870 | 6500
500140616 | CLB-MP-HAUL-DT5404-ELCTHV-HVGBM | Grid Box Blower Motor | 8870 | 8870 | 6500
500140615 | CLB-MP-HAUL-DT5404-ELCTHV-HVGBX-HVRES | Grid Resistors | 8870 | 8870 | 6500
500140614 | CLB-MP-HAUL-DT5404-ELCTLV-START-STMUP | Starter Motor Upper | 8870 | 8870 | 6500
500140613 | CLB-MP-HAUL-DT5404-ELCTLV-START-STMLO | Starter Motor Lower | 8870 | 8870 | 6500
500140612 | CLB-MP-HAUL-DT5404-ELCTLV-CHARG-BATTY | Batteries | 8870 | 8870 | 6500
500140611 | CLB-MP-HAUL-DT5404-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8870 | 8870 | 6500
500140610 | CLB-MP-HAUL-DT5404-ELCTLV-HARNS | Electrical Harness | 8870 | 8870 | 6500
500140609 | CLB-MP-HAUL-DT5404-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 8870 | 8870 | 6500
500140608 | CLB-MP-HAUL-DT5404-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 8870 | 8870 | 6500
500140607 | CLB-MP-HAUL-DT5404-ENGINE-FUSYS-FUINJ | Fuel Injectors | 8870 | 8870 | 6500
500140606 | CLB-MP-HAUL-DT5404-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 8870 | 8870 | 6500
500140605 | CLB-MP-HAUL-DT5404-ENGINE-INTEX-TBORF | Turbocharger RH Front | 8870 | 8870 | 6500
500140604 | CLB-MP-HAUL-DT5404-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 8870 | 8870 | 6500
500140603 | CLB-MP-HAUL-DT5404-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 8870 | 8870 | 6500
500140602 | CLB-MP-HAUL-DT5404-ENGINE-INTEX-AFTER | Aftercooler Engine | 8870 | 8870 | 6500
500140601 | CLB-MP-HAUL-DT5404-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8870 | 8870 | 6500
500140600 | CLB-MP-HAUL-DT5404-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8870 | 8870 | 6500
500140599 | CLB-MP-HAUL-DT5404-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 8870 | 8870 | 6500
500140598 | CLB-MP-HAUL-DT5404-ENGINE-COSYS-HTWPP | Engine Water Pump | 8870 | 8870 | 6500
500140597 | CLB-MP-HAUL-DT5404-ENGINE-COSYS-COFAN | Fan Cooling System | 8870 | 8870 | 6500
500140596 | CLB-MP-HAUL-DT5404-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 8870 | 8870 | 6500
500140595 | CLB-MP-HAUL-DT5404-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 8870 | 8870 | 6500
500140594 | CLB-MP-HAUL-DT5404-ENGINE | Engine Assembly Cummins QSK60 | 8870 | 8870 | 6500
500140593 | CLB-MP-HAUL-DT5404 | DT5404 Liebherr T264 OHT | 8870 | 8870 | 6500
500164566 | CLB-MP-HAUL-DT5391-STRSYS-STACC-SACRH | Accumulator Steering ODS | 11246 | 11246 | 6500
500164565 | CLB-MP-HAUL-DT5391-STRSYS-STACC-SACLH | Accumulator Steering DS | 11246 | 11246 | 6500
500164564 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 11246 | 11246 | 6500
500164563 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 11246 | 11246 | 6500
500164562 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 11246 | 11246 | 6500
500164561 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 11246 | 11246 | 6500
500149071 | CLB-MP-HAUL-DT5391-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 11246 | 11246 | 6500
500138876 | CLB-MP-HAUL-DT5391-STRSYS-STACC | Accumulator Hyd Steering right | 11246 | 11246 | 6500
500138875 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC | Accumulator Rear Brake Supply | 11246 | 11246 | 6500
500138874 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC | Accumulator Rear Brake Pilot | 11246 | 11246 | 6500
500138873 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC | Accumulator Front Brake Supply | 11246 | 11246 | 6500
500138620 | CLB-MP-HAUL-DT5391-STRSYS-STACC | Accumulator Hyd Steering Left | 11246 | 11246 | 6500
500138619 | CLB-MP-HAUL-DT5391-BRKSYS-BRACC | Accumulator Front Brake Pilot | 11246 | 11246 | 6500
500138618 | CLB-MP-HAUL-DT5391-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 11246 | 11246 | 6500
500138617 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 11246 | 11246 | 6500
500138616 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 11246 | 2505 | 6500
500138615 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 11246 | 11246 | 6500
500138614 | CLB-MP-HAUL-DT5391-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 11246 | 11246 | 6500
500138613 | CLB-MP-HAUL-DT5391-STRUCT-TRAYS | Tray | 11246 | 11246 | 6500
500138612 | CLB-MP-HAUL-DT5391-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 11246 | 11246 | 6500
500138611 | CLB-MP-HAUL-DT5391-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 11246 | 11246 | 6500
500138610 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-SEATS | Operators Seat | 11246 | 11246 | 6500
500138609 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 11246 | 11246 | 6500
500138608 | CLB-MP-HAUL-DT5391-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 11246 | 4814 | 6500
500138607 | CLB-MP-HAUL-DT5391-STRUCT-CABIN | Operators Cabin | 11246 | 11246 | 6500
500138606 | CLB-MP-HAUL-DT5391-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 11246 | 11246 | 6500
500138605 | CLB-MP-HAUL-DT5391-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 11246 | 11246 | 6500
500138604 | CLB-MP-HAUL-DT5391-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 11246 | 11246 | 6500
500138603 | CLB-MP-HAUL-DT5391-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 11246 | 11246 | 6500
500138602 | CLB-MP-HAUL-DT5391-HYDSYS-HOMAN | Hoist Manifold | 11246 | 11246 | 6500
500138601 | CLB-MP-HAUL-DT5391-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 11246 | 11246 | 6500
500138600 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 11246 | 11246 | 6500
500138599 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 11246 | 11246 | 6500
500138598 | CLB-MP-HAUL-DT5391-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steer | 11246 | 11246 | 6500
500138597 | CLB-MP-HAUL-DT5391-HYDSYS-GROCL | Gear Oil Cooler | 11246 | 11246 | 6500
500138596 | CLB-MP-HAUL-DT5391-HYDSYS-HYDOC | Hydraulic Oil Cooler | 11246 | 11246 | 6500
500138595 | CLB-MP-HAUL-DT5391-GRSYST-ALBPP | Auto Lube Pump | 11246 | 11246 | 6500
500138594 | CLB-MP-HAUL-DT5391-STRSYS-STRIA | Steering Idler Arm | 11246 | 11246 | 6500
500138593 | CLB-MP-HAUL-DT5391-STRSYS-STLTR | Steering Linkages & Tie Rods | 11246 | 11246 | 6500
500138592 | CLB-MP-HAUL-DT5391-STRSYS-STRCY-STCYR | Steering Cylinder RH | 11246 | 11246 | 6500
500138591 | CLB-MP-HAUL-DT5391-STRSYS-STRCY-STCYL | Steering Cylinder LH | 11246 | 11246 | 6500
500138590 | CLB-MP-HAUL-DT5391-STRSYS-STCNT | Steering Control Unit | 11246 | 11246 | 6500
500138589 | CLB-MP-HAUL-DT5391-STRSYS-STVLV | Valve Flow Amplifier | 11246 | 11246 | 6500
500138588 | CLB-MP-HAUL-DT5391-BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 11246 | 11246 | 6500
500138587 | CLB-MP-HAUL-DT5391-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 11246 | 11246 | 6500
500138586 | CLB-MP-HAUL-DT5391-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 11246 | 11246 | 6500
500138585 | CLB-MP-HAUL-DT5391-BRKSYS-BRVTR | Brake Treadle Valve | 11246 | 11246 | 6500
500138584 | CLB-MP-HAUL-DT5391-BRKSYS-BRSTV | Brake & Steering Valve | 11246 | 11246 | 6500
500138583 | CLB-MP-HAUL-DT5391-BRKSYS-BRVLV | Brake & Steering Manifold | 11246 | 11246 | 6500
500138582 | CLB-MP-HAUL-DT5391-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 11246 | 11246 | 6500
500138581 | CLB-MP-HAUL-DT5391-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 11246 | 11246 | 6500
500138580 | CLB-MP-HAUL-DT5391-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 11246 | 11246 | 6500
500138579 | CLB-MP-HAUL-DT5391-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 11246 | 11246 | 6500
500138578 | CLB-MP-HAUL-DT5391-BRKSYS-BRVRL | Brake Dual Relay Valves | 11246 | 11246 | 6500
500138577 | CLB-MP-HAUL-DT5391-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 11246 | 11246 | 6500
500138576 | CLB-MP-HAUL-DT5391-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 11246 | 11246 | 6500
500138575 | CLB-MP-HAUL-DT5391-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 11246 | 11246 | 6500
500138574 | CLB-MP-HAUL-DT5391-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 11246 | 11246 | 6500
500138573 | CLB-MP-HAUL-DT5391-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 11246 | 11246 | 6500
500138572 | CLB-MP-HAUL-DT5391-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 11246 | 11246 | 6500
500138571 | CLB-MP-HAUL-DT5391-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 11246 | 11246 | 6500
500138570 | CLB-MP-HAUL-DT5391-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 11246 | 11246 | 6500
500138569 | CLB-MP-HAUL-DT5391-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 11246 | 11246 | 6500
500138568 | CLB-MP-HAUL-DT5391-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 11246 | 11246 | 6500
500138567 | CLB-MP-HAUL-DT5391-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 11246 | 11246 | 6500
500138566 | CLB-MP-HAUL-DT5391-ELCTHV-HVBLW | Main High Voltage Blower | 11246 | 11246 | 6500
500138565 | CLB-MP-HAUL-DT5391-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 11246 | 11246 | 6500
500138564 | CLB-MP-HAUL-DT5391-ELCTHV-HVALT | High Voltage Alternator | 11246 | 11246 | 6500
500138563 | CLB-MP-HAUL-DT5391-ELCTHV-HVGBM | Grid Box Blower Motor | 11246 | 11246 | 6500
500138562 | CLB-MP-HAUL-DT5391-ELCTHV-HVGBX-HVRES | Grid Resistors | 11246 | 11246 | 6500
500138561 | CLB-MP-HAUL-DT5391-ELCTLV-START-STMUP | Starter Motor Upper | 11246 | 11246 | 6500
500138560 | CLB-MP-HAUL-DT5391-ELCTLV-START-STMLO | Starter Motor Lower | 11246 | 11246 | 6500
500138559 | CLB-MP-HAUL-DT5391-ELCTLV-CHARG-BATTY | Batteries | 11246 | 11246 | 6500
500138558 | CLB-MP-HAUL-DT5391-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 11246 | 11246 | 6500
500138557 | CLB-MP-HAUL-DT5391-ELCTLV-HARNS | Electrical Harness | 11246 | 11246 | 6500
500138556 | CLB-MP-HAUL-DT5391-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 11246 | 11246 | 6500
500138555 | CLB-MP-HAUL-DT5391-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 11246 | 11246 | 6500
500138554 | CLB-MP-HAUL-DT5391-ENGINE-FUSYS-FUINJ | Fuel Injectors | 11246 | 11246 | 6500
500138553 | CLB-MP-HAUL-DT5391-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 11246 | 11246 | 6500
500138552 | CLB-MP-HAUL-DT5391-ENGINE-INTEX-TBORF | Turbocharger RH Front | 11246 | 11246 | 6500
500138551 | CLB-MP-HAUL-DT5391-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 11246 | 11246 | 6500
500138550 | CLB-MP-HAUL-DT5391-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 11246 | 11246 | 6500
500138549 | CLB-MP-HAUL-DT5391-ENGINE-INTEX-AFTER | Aftercooler Engine | 11246 | 11246 | 6500
500138548 | CLB-MP-HAUL-DT5391-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 11246 | 11246 | 6500
500138547 | CLB-MP-HAUL-DT5391-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 11246 | 11246 | 6500
500138546 | CLB-MP-HAUL-DT5391-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 11246 | 11246 | 6500
500138545 | CLB-MP-HAUL-DT5391-ENGINE-COSYS-HTWPP | Engine Water Pump | 11246 | 11246 | 6500
500138544 | CLB-MP-HAUL-DT5391-ENGINE-COSYS-COFAN | Fan Cooling System | 11246 | 11246 | 6500
500138543 | CLB-MP-HAUL-DT5391-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 11246 | 11246 | 6500
500138542 | CLB-MP-HAUL-DT5391-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 11246 | 11246 | 6500
500138541 | CLB-MP-HAUL-DT5391-ENGINE | Engine Assembly Cummins QSK60 | 11246 | 11246 | 6500
500138540 | CLB-MP-HAUL-DT5391 | DT5391 Liebherr T264 OHT | 11246 | 11246 | 6500
500164560 | CLB-MP-HAUL-DT5390-STRSYS-STACC-SACRH | Accumulator Steering ODS | 9157 | 9157 | 6500
500164559 | CLB-MP-HAUL-DT5390-STRSYS-STACC-SACLH | Accumulator Steering DS | 9157 | 9157 | 6500
500164558 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC04 | Accumulator Brake Rear ODS | 9157 | 9157 | 6500
500164557 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC03 | Accumulator Brake Rear DS | 9157 | 9157 | 6500
500164556 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC02 | Accumulator Brake Front ODS | 9157 | 9157 | 6500
500164555 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC-ACC01 | Accumulator Brake Front DS | 9157 | 9157 | 6500
500149070 | CLB-MP-HAUL-DT5390-ELCTHV-HVCAB-COOLR | High Voltage Cabinet Water Cooling Sys | 9157 | 9157 | 6500
500138872 | CLB-MP-HAUL-DT5390-STRSYS-STACC | Accumulator Hyd Steering right | 9157 | 9157 | 6500
500138871 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC | Accumulator Rear Brake Supply | 9157 | 9157 | 6500
500138870 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC | Accumulator Rear Brake Pilot | 9157 | 9157 | 6500
500138869 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC | Accumulator Front Brake Supply | 9157 | 9157 | 6500
500138539 | CLB-MP-HAUL-DT5390-STRSYS-STACC | Accumulator Hyd Steering Left | 9157 | 9157 | 6500
500138538 | CLB-MP-HAUL-DT5390-BRKSYS-BRACC | Accumulator Front Brake Pilot | 9157 | 9157 | 6500
500138537 | CLB-MP-HAUL-DT5390-MANGMT-TYRSN-HARNS | Electrical Harness Tyre Sense | 9157 | 9157 | 6500
500138536 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYRR | Cylinder Suspension RH Rear | 9157 | 1188 | 6500
500138535 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYLR | Cylinder Suspension LH Rear | 9157 | 9157 | 6500
500138534 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYRF | Cylinder Suspension RH Front | 9157 | 9157 | 6500
500138533 | CLB-MP-HAUL-DT5390-STRUCT-SUSPN-SCYLF | Cylinder Suspension LH Front | 9157 | 9157 | 6500
500138532 | CLB-MP-HAUL-DT5390-STRUCT-TRAYS | Tray | 9157 | 9157 | 6500
500138531 | CLB-MP-HAUL-DT5390-STRUCT-AXLES-HUBRH | Hub & Spindle RH | 9157 | 9157 | 6500
500138530 | CLB-MP-HAUL-DT5390-STRUCT-AXLES-HUBLH | Hub & Spindle LH | 9157 | 9157 | 6500
500138529 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-SEATS | Operators Seat | 9157 | 9157 | 6500
500138528 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 9157 | 9157 | 6500
500138527 | CLB-MP-HAUL-DT5390-STRUCT-CABIN-AIRCN | Cabin Air Conditioning System | 9157 | 9157 | 6500
500138526 | CLB-MP-HAUL-DT5390-STRUCT-CABIN | Operators Cabin | 9157 | 9157 | 6500
500138525 | CLB-MP-HAUL-DT5390-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 9157 | 9157 | 6500
500138524 | CLB-MP-HAUL-DT5390-HYDSYS-HOCYL-HCYRH | Cylinder Hoist RH | 9157 | 9157 | 6500
500138523 | CLB-MP-HAUL-DT5390-HYDSYS-HOCYL-HCYLH | Cylinder Hoist LH | 9157 | 9157 | 6500
500138522 | CLB-MP-HAUL-DT5390-HYDSYS-HOMAN-DCVLV | Hoist Directional Control Valve | 9157 | 9157 | 6500
500138521 | CLB-MP-HAUL-DT5390-HYDSYS-HOMAN | Hoist Manifold | 9157 | 9157 | 6500
500138520 | CLB-MP-HAUL-DT5390-HYDSYS-HDACC-PCACC | Accumulator Pump Control | 9157 | 9157 | 6500
500138519 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-HYDPC | Coupling Drive Pump | 9157 | 9157 | 6500
500138518 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-ACPMP | Hydraulic Pump Aircon Drive Motor | 9157 | 9157 | 6500
500138517 | CLB-MP-HAUL-DT5390-HYDSYS-HYDPP-HYPMP | Hydraulic Pump Hoist Brake & Steer | 9157 | 9157 | 6500
500138516 | CLB-MP-HAUL-DT5390-HYDSYS-GROCL | Gear Oil Cooler | 9157 | 9157 | 6500
500138515 | CLB-MP-HAUL-DT5390-HYDSYS-HYDOC | Hydraulic Oil Cooler | 9157 | 9157 | 6500
500138514 | CLB-MP-HAUL-DT5390-GRSYST-ALBPP | Auto Lube Pump | 9157 | 9157 | 6500
500138513 | CLB-MP-HAUL-DT5390-STRSYS-STRIA | Steering Idler Arm | 9157 | 9157 | 6500
500138512 | CLB-MP-HAUL-DT5390-STRSYS-STLTR | Steering Linkages & Tie Rods | 9157 | 9157 | 6500
500138511 | CLB-MP-HAUL-DT5390-STRSYS-STRCY-STCYR | Steering Cylinder RH | 9157 | 9157 | 6500
500138510 | CLB-MP-HAUL-DT5390-STRSYS-STRCY-STCYL | Steering Cylinder LH | 9157 | 9157 | 6500
500138509 | CLB-MP-HAUL-DT5390-STRSYS-STCNT | Steering Control Unit | 9157 | 9157 | 6500
500138508 | CLB-MP-HAUL-DT5390-STRSYS-STVLV | Valve Flow Amplifier | 9157 | 9157 | 6500
500138507 | CLB-MP-HAUL-DT5390-BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 9157 | 9157 | 6500
500138506 | CLB-MP-HAUL-DT5390-BRKSYS-BRPRK-PRKRH | Park Brake Assembly RH | 9157 | 9157 | 6500
500138505 | CLB-MP-HAUL-DT5390-BRKSYS-BRPRK-PRKLH | Park Brake Assembly LH | 9157 | 9157 | 6500
500138504 | CLB-MP-HAUL-DT5390-BRKSYS-BRVTR | Brake Treadle Valve | 9157 | 9157 | 6500
500138503 | CLB-MP-HAUL-DT5390-BRKSYS-BRSTV | Brake & Steering Valve | 9157 | 9157 | 6500
500138502 | CLB-MP-HAUL-DT5390-BRKSYS-BRVLV | Brake & Steering Manifold | 9157 | 9157 | 6500
500138501 | CLB-MP-HAUL-DT5390-BRKSYS-SRVBK-SVBRR | Service Brake RH Rear | 9157 | 9157 | 6500
500138500 | CLB-MP-HAUL-DT5390-BRKSYS-SRVBK-SVBLR | Service Brake LH Rear | 9157 | 9157 | 6500
500138499 | CLB-MP-HAUL-DT5390-BRKSYS-SRVBK-SVBRF | Service Brake RH Front | 9157 | 9157 | 6500
500138498 | CLB-MP-HAUL-DT5390-BRKSYS-SRVBK-SVBLF | Service Brake LH Front | 9157 | 9157 | 6500
500138497 | CLB-MP-HAUL-DT5390-BRKSYS-BRVRL | Brake Dual Relay Valves | 9157 | 9157 | 6500
500138496 | CLB-MP-HAUL-DT5390-FDRSYS-WHTYR-POS06 | Tyre & Rim Pos 6 | 9157 | 9157 | 6500
500138495 | CLB-MP-HAUL-DT5390-FDRSYS-WHTYR-POS05 | Tyre & Rim Pos 5 | 9157 | 9157 | 6500
500138494 | CLB-MP-HAUL-DT5390-FDRSYS-WHTYR-POS04 | Tyre & Rim Pos 4 | 9157 | 9157 | 6500
500138493 | CLB-MP-HAUL-DT5390-FDRSYS-WHTYR-POS03 | Tyre & Rim Pos 3 | 9157 | 9157 | 6500
500138492 | CLB-MP-HAUL-DT5390-FDRSYS-WHTYR-POS02 | Tyre & Rim Pos 2 | 9157 | 9157 | 6500
500138491 | CLB-MP-HAUL-DT5390-FDRSYS-WHTYR-POS01 | Tyre & Rim Pos 1 | 9157 | 9157 | 6500
500138490 | CLB-MP-HAUL-DT5390-FDRSYS-GRSOC-OCPPM | Gear Set Oil Cooling Pump & Motor | 9157 | 9157 | 6500
500138489 | CLB-MP-HAUL-DT5390-FDRSYS-FDRVE-GRSRH | Final Drive Gear Set RH | 9157 | 9157 | 6500
500138488 | CLB-MP-HAUL-DT5390-FDRSYS-FDRVE-GRSLH | Final Drive Gear Set LH | 9157 | 9157 | 6500
500138487 | CLB-MP-HAUL-DT5390-FDRSYS-WLMTR-WHMRH | Wheel Motor RH | 9157 | 9157 | 6500
500138486 | CLB-MP-HAUL-DT5390-FDRSYS-WLMTR-WHMLH | Wheel Motor LH | 9157 | 9157 | 6500
500138485 | CLB-MP-HAUL-DT5390-ELCTHV-HVBLW | Main High Voltage Blower | 9157 | 9157 | 6500
500138484 | CLB-MP-HAUL-DT5390-ELCTHV-HVCAB-PRESS | High Voltage Control Cabinet Pressuriser | 9157 | 9157 | 6500
500138483 | CLB-MP-HAUL-DT5390-ELCTHV-HVALT | High Voltage Alternator | 9157 | 9157 | 6500
500138482 | CLB-MP-HAUL-DT5390-ELCTHV-HVGBM | Grid Box Blower Motor | 9157 | 9157 | 6500
500138481 | CLB-MP-HAUL-DT5390-ELCTHV-HVGBX-HVRES | Grid Resistors | 9157 | 9157 | 6500
500138480 | CLB-MP-HAUL-DT5390-ELCTLV-START-STMUP | Starter Motor Upper | 9157 | 9157 | 6500
500138479 | CLB-MP-HAUL-DT5390-ELCTLV-START-STMLO | Starter Motor Lower | 9157 | 9157 | 6500
500138478 | CLB-MP-HAUL-DT5390-ELCTLV-CHARG-BATTY | Batteries | 9157 | 9157 | 6500
500138477 | CLB-MP-HAUL-DT5390-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 9157 | 9157 | 6500
500138476 | CLB-MP-HAUL-DT5390-ELCTLV-HARNS | Electrical Harness | 9157 | 9157 | 6500
500138475 | CLB-MP-HAUL-DT5390-ENGINE-FUSYS-FULTK | Diesel Fuel Tank | 9157 | 9157 | 6500
500138474 | CLB-MP-HAUL-DT5390-ENGINE-FUSYS-FULPP | Engine Fuel Pump | 9157 | 9157 | 6500
500138473 | CLB-MP-HAUL-DT5390-ENGINE-FUSYS-FUINJ | Fuel Injectors | 9157 | 9157 | 6500
500138472 | CLB-MP-HAUL-DT5390-ENGINE-INTEX-TBORR | Turbocharger RH Rear | 9157 | 9157 | 6500
500138471 | CLB-MP-HAUL-DT5390-ENGINE-INTEX-TBORF | Turbocharger RH Front | 9157 | 9157 | 6500
500138470 | CLB-MP-HAUL-DT5390-ENGINE-INTEX-TBOLR | Turbocharger LH Rear | 9157 | 9157 | 6500
500138469 | CLB-MP-HAUL-DT5390-ENGINE-INTEX-TBOLF | Turbocharger LH Front | 9157 | 9157 | 6500
500138468 | CLB-MP-HAUL-DT5390-ENGINE-INTEX-AFTER | Aftercooler Engine | 9157 | 9157 | 6500
500138467 | CLB-MP-HAUL-DT5390-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 9157 | 9157 | 6500
500138466 | CLB-MP-HAUL-DT5390-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 9157 | 9157 | 6500
500138465 | CLB-MP-HAUL-DT5390-ENGINE-COSYS-RADTR | Radiator Engine Cooling | 9157 | 9157 | 6500
500138464 | CLB-MP-HAUL-DT5390-ENGINE-COSYS-HTWPP | Engine Water Pump | 9157 | 9157 | 6500
500138463 | CLB-MP-HAUL-DT5390-ENGINE-COSYS-COFAN | Fan Cooling System | 9157 | 9157 | 6500
500138012 | CLB-MP-HAUL-DT5390-ENGINE-LUBSY-PLPMP | Engine PreLube Pump | 9157 | 9157 | 6500
500138011 | CLB-MP-HAUL-DT5390-ENGINE-LUBSY-CENTR | Lube Centrifugal Filter | 9157 | 9157 | 6500
500138010 | CLB-MP-HAUL-DT5390-ENGINE | Engine Assembly Cummins QSK60 | 9157 | 9157 | 6500
500138009 | CLB-MP-HAUL-DT5390 | DT5390 Liebherr T264 OHT | 9157 | 9157 | 6500
500132427 | CLB-MP-SUPP-WC3108-STRUCT-WTANK | WC3108 Water Tank Module | 17735 | 17735 | 5000
500118959 | CLB-MP-SUPP-WC3108-TRNSYS-TRQUE | Torque Converter | 17738 | 17738 | 5000
500118958 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TMCPP | Transmission Pump | 17738 | 17738 | 5000
500118957 | CLB-MP-SUPP-WC3108-TRNSYS-TRPMP-TCCPP | TC/Park Brake/Scavenge Pump | 17738 | 17738 | 5000
500118956 | CLB-MP-SUPP-WC3108-TRNSYS-TROLC | Transmission Oil Cooler | 17738 | 17738 | 5000
500118955 | CLB-MP-SUPP-WC3108-TRNSYS-TRANS | Transmission | 17738 | 17738 | 5000
500118954 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-WTPPM | Water Tank Pump/Motor | 17738 | 7958 | 5000
500118953 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-SPRAY | Water Tank Sprays | 17738 | 17738 | 5000
500118952 | CLB-MP-SUPP-WC3108-STRUCT-WTANK-CANON | Water Tank Cannon | 17738 | 8813 | 5000
500118951 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYRR | Suspension Cylinder Right Hand Rear | 17738 | 17738 | 5000
500118950 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYRF | Suspension Cylinder Right Hand Front | 17738 | 17738 | 5000
500118949 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYLR | Suspension Cylinder Left Hand Rear | 17738 | 17738 | 5000
500118948 | CLB-MP-SUPP-WC3108-STRUCT-SUSPN-SCYLF | Suspension Cylinder Left Hand Front | 17738 | 17738 | 5000
500118947 | CLB-MP-SUPP-WC3108-STRUCT-CHASS-TAGLK | Tag Link | 17738 | 17738 | 5000
500118946 | CLB-MP-SUPP-WC3108-STRUCT-CHASS-AFRME | A Frame | 17738 | 17738 | 5000
500118945 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-SEATS | Operators Seat | 17738 | 2662 | 5000
500118944 | CLB-MP-SUPP-WC3108-STRUCT-CABIN-AIRCN | Air Conditioning System | 17738 | 7923 | 5000
500118943 | CLB-MP-SUPP-WC3108-STRUCT-AXLES-HUBRH | Hub and Spindle Right Hand Front | 17738 | 232 | 5000
500118942 | CLB-MP-SUPP-WC3108-STRUCT-AXLES-HUBLH | Hub and Spindle Left Hand Front | 17738 | 15820 | 5000
500118941 | CLB-MP-SUPP-WC3108-STRSYS-STRCY-STCYR | Cylinder Steering Right Hand | 17738 | 1992 | 5000
500118940 | CLB-MP-SUPP-WC3108-STRSYS-STRCY-STCYL | Cylinder Steering Left Hand | 17738 | 1992 | 5000
500118939 | CLB-MP-SUPP-WC3108-STRSYS-STPMP | Steering Pump | 17738 | 1992 | 5000
500118938 | CLB-MP-SUPP-WC3108-STRSYS-STOLC | Steering Oil Cooler | 17738 | 1992 | 5000
500118937 | CLB-MP-SUPP-WC3108-STRSYS-STLTR | Steering Linkages and Tie Rods | 17738 | 17738 | 5000
500118936 | CLB-MP-SUPP-WC3108-STRSYS-STHMU | Steering HMU | 17738 | 9808 | 5000
500118935 | CLB-MP-SUPP-WC3108-STRSYS-STACC-SACRH | Steering Accumulator Right Hand | 17738 | 17738 | 5000
500118934 | CLB-MP-SUPP-WC3108-STRSYS-STACC-SACLH | Steering Accumulator Left Hand | 17738 | 17738 | 5000
500118933 | CLB-MP-SUPP-WC3108-PNEUMC-START | Pneumatic Starter Motor | 17738 | 17738 | 5000
500118932 | CLB-MP-SUPP-WC3108-PNEUMC-AIRDR | Air Drier | 17738 | 17738 | 5000
500118931 | CLB-MP-SUPP-WC3108-HYDSYS-HOVLV | Hoist Valve | 17738 | 17738 | 5000
500118930 | CLB-MP-SUPP-WC3108-HYDSYS-HOPMP | Hoist & Rear Brake Cooling Pump | 17738 | 17738 | 5000
500118929 | CLB-MP-SUPP-WC3108-HYDSYS-HOCYL-HCYLR | Hoist Cylinder Right Hand | 17738 | 17738 | 5000
500118928 | CLB-MP-SUPP-WC3108-HYDSYS-HOCYL-HCYLL | Hoist Cylinder Left Hand | 17738 | 17738 | 5000
500118927 | CLB-MP-SUPP-WC3108-GRSYST-GRINJ | Auto Lube Injectors | 17738 | 17738 | 5000
500118926 | CLB-MP-SUPP-WC3108-GRSYST-ALBPP | Auto Lube Pump | 17738 | 17738 | 5000
500118925 | CLB-MP-SUPP-WC3108-FRSUPP | Fire Suppression System | 17738 | 17738 | 5000
500118924 | CLB-MP-SUPP-WC3108-FDRSYS-FDRVE-FDRRH | Final Drive Right Hand | 17738 | 15820 | 5000
500118923 | CLB-MP-SUPP-WC3108-FDRSYS-FDRVE-FDRLH | Final Drive Left Hand | 17738 | 15820 | 5000
500118922 | CLB-MP-SUPP-WC3108-FDRSYS-DRSHT | Transmission Drive Shaft | 17738 | 17738 | 5000
500118921 | CLB-MP-SUPP-WC3108-FDRSYS-DRLAX-AXLRH | Drive Line Axle Right Hand | 17738 | 17738 | 5000
500118920 | CLB-MP-SUPP-WC3108-FDRSYS-DRLAX-AXLLH | Drive Line Axle Left Hand | 17738 | 17738 | 5000
500118919 | CLB-MP-SUPP-WC3108-FDRSYS-DIFFL | Differential | 17738 | 17738 | 5000
500118918 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-MTFAN | Rear Axle Cooling Fan Motor | 17738 | 7923 | 5000
500118917 | CLB-MP-SUPP-WC3108-FDRSYS-AXLEC-HYPUM | Rear Axle Oil Pump | 17738 | 7923 | 5000
500118916 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR-DRSHT | Drive Shaft Engine Pump Drive | 17738 | 7923 | 5000
500118915 | CLB-MP-SUPP-WC3108-ENGINE-PMPDR | Engine Pump Drive | 17738 | 1992 | 5000
500118914 | CLB-MP-SUPP-WC3108-ENGINE-LUBSY-PREPP | Pre-Lubrication Pump | 17738 | 8324 | 5000
500118913 | CLB-MP-SUPP-WC3108-ENGINE-LUBSY-OILPP | Engine Oil Pump | 17738 | 17738 | 5000
500118912 | CLB-MP-SUPP-WC3108-ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 17738 | 7923 | 5000
500118911 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-TBORR | Turbocharger Right Hand Rear | 17738 | 7923 | 5000
500118910 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-TBORF | Turbocharger Right Hand Front | 17738 | 7923 | 5000
500118909 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-TBOLR | Turbocharger Left Hand Rear | 17738 | 7923 | 5000
500118908 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-TBOLF | Turbocharger Left Hand Front | 17738 | 7923 | 5000
500118907 | CLB-MP-SUPP-WC3108-ENGINE-INTEX-AFTER | Aftercooler | 17738 | 17738 | 5000
500118906 | CLB-MP-SUPP-WC3108-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 17738 | 7923 | 5000
500118905 | CLB-MP-SUPP-WC3108-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 17738 | 7923 | 5000
500118904 | CLB-MP-SUPP-WC3108-ENGINE-FUSYS-FUINJ | Fuel Injectors | 17738 | 7923 | 5000
500118903 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-WTRPP | Water Pump Engine | 17738 | 7923 | 5000
500118902 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-THERM | Thermostats/Regulators | 17738 | 7923 | 5000
500118901 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-RADTR | Engine Radiator | 17738 | 17738 | 5000
500118900 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-COFAN | Fan Drive Cooling System | 17738 | 17738 | 5000
500118899 | CLB-MP-SUPP-WC3108-ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 17738 | 7923 | 5000
500118898 | CLB-MP-SUPP-WC3108-ENGINE-COMPR | Air Compressor | 17738 | 7923 | 5000
500118897 | CLB-MP-SUPP-WC3108-ENGINE | Engine Assembly Caterpillar 3512 | 17738 | 17738 | 5000
500118896 | CLB-MP-SUPP-WC3108-ELCTLV-CHARG-ALTER | Alternator 24V | 17738 | 3274 | 5000
500118895 | CLB-MP-SUPP-WC3108-BRKSYS-SRVBK-SVBRR | Service Brake Right Hand Rear | 17738 | 17738 | 5000
500118894 | CLB-MP-SUPP-WC3108-BRKSYS-SRVBK-SVBRF | Service Brake Right Hand Front | 17738 | 17738 | 5000
500118893 | CLB-MP-SUPP-WC3108-BRKSYS-SRVBK-SVBLR | Service Brake Left Hand Rear | 17738 | 17738 | 5000
500118892 | CLB-MP-SUPP-WC3108-BRKSYS-SRVBK-SVBLF | Service Brake Left Hand Front | 17738 | 17738 | 5000
500118891 | CLB-MP-SUPP-WC3108-BRKSYS-SLACK-SLACR | Slack Adjustor Rear | 17738 | 17738 | 5000
500118890 | CLB-MP-SUPP-WC3108-BRKSYS-SLACK-SLACF | Slack Adjustor Front | 17738 | 17738 | 5000
500118889 | CLB-MP-SUPP-WC3108-BRKSYS-MERTR | Mechanical Retarder | 17738 | 17738 | 5000
500118888 | CLB-MP-SUPP-WC3108-BRKSYS-BRVTR | Brake Treadle Valve | 17738 | 17738 | 5000
500118887 | CLB-MP-SUPP-WC3108-BRKSYS-BRVLV | Brake Valve | 17738 | 17738 | 5000
500118886 | CLB-MP-SUPP-WC3108-BRKSYS-BROCO-BROCT | Brake Oil Cooler Rear Top | 17738 | 17738 | 5000
500118885 | CLB-MP-SUPP-WC3108-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 17738 | 17738 | 5000
500118884 | CLB-MP-SUPP-WC3108-BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom | 17738 | 17738 | 5000
500118883 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTRR | Rotochamber Right Hand Rear | 17738 | 17738 | 5000
500118882 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTLR | Rotochamber Left Hand Rear | 17738 | 17738 | 5000
500118881 | CLB-MP-SUPP-WC3108-BRKSYS-BRCYL-ROTFR | Rotochamber Front | 17738 | 17738 | 5000
500118620 | CLB-MP-SUPP-WC3108-BRKSYS-BACCM | Brake Accumulator | 17738 | 17738 | 5000
500118619 | CLB-MP-SUPP-WC3108 | Caterpillar 785D Water Cart, WC3108 | 17738 | 17738 | 5000
500146813 | CLB-MP-SUPP-WC015 -BRKSYS-BACCM | CAT 785D Brake Accumulator | 67897 | 20934 | 5000
500146812 | CLB-MP-SUPP-WC015 -STRSYS-STACC | CAT 785D Steering Accumulator RH | 67897 | 20934 | 5000
500146811 | CLB-MP-SUPP-WC015 -STRSYS-STACC | CAT 785D Steering Accumulator LH | 67897 | 20934 | 5000
500132420 | CLB-MP-SUPP-WC015 -STRUCT-WTANK | WC015 Water Tank Module | 67897 | 67897 | 5000
500100662 | CLB-MP-SUPP-WC015 -TRNSYS | WC015 Transmission System | 67897 | 20934 | 5000
500081537 | CLB-MP-SUPP-WC015 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 67897 | 67897 | 5000
500081512 | CLB-MP-SUPP-WC015 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 67897 | 67897 | 5000
500058112 | CLB-MP-SUPP-WC015 -FRSUPP | Fire Suppression System | 67897 | 1397 | 5000
500058111 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-CANON | Water Tank Cannon | 67897 | 1397 | 5000
500058110 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-SPRAY | Water Tank Sprays | 67897 | 6354 | 5000
500058109 | CLB-MP-SUPP-WC015 -STRUCT-WTANK-WTPPM | Water Tank Pump/Motor | 67897 | 20934 | 5000
500058108 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYRR | Suspension Cylinder R/H/Rear | 67897 | 7727 | 5000
500058107 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYLR | Suspension Cylinder L/H/Rear | 67897 | 15856 | 5000
500058106 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYRF | Suspension Cylinder R/H/Front | 67897 | 1397 | 5000
500058105 | CLB-MP-SUPP-WC015 -STRUCT-SUSPN-SCYLF | Suspension Cylinder L/H/Front | 67897 | 1397 | 5000
500058104 | CLB-MP-SUPP-WC015 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H/Front | 67897 | 1397 | 5000
500058103 | CLB-MP-SUPP-WC015 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H/Front | 67897 | 1397 | 5000
500058102 | CLB-MP-SUPP-WC015 -STRUCT-CHASS-TAGLK | Tag Link | 67897 | 1397 | 5000
500058101 | CLB-MP-SUPP-WC015 -STRUCT-CHASS-AFRME | A Frame | 67897 | 1397 | 5000
500058100 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-AIRCN | Air Conditioning System | 67897 | 1397 | 5000
500058099 | CLB-MP-SUPP-WC015 -STRUCT-CABIN-SEATS | Operators Seat | 67897 | 1397 | 5000
500058098 | CLB-MP-SUPP-WC015 -PNEUMC-START | Pneumatic Starter Motor | 67897 | 1397 | 5000
500058097 | CLB-MP-SUPP-WC015 -PNEUMC-AIRDR | Air Drier | 67897 | 1397 | 5000
500058096 | CLB-MP-SUPP-WC015 -GRSYST-ALBPP | Auto Lube Pump | 67897 | 67897 | 5000
500058095 | CLB-MP-SUPP-WC015 -GRSYST-GRINJ | Auto Lube Injectors | 67897 | 67897 | 5000
500058094 | CLB-MP-SUPP-WC015 -HYDSYS-HOCYL-HCYLR | Hoist Cylinder R/H/S | 67897 | 1397 | 5000
500058093 | CLB-MP-SUPP-WC015 -HYDSYS-HOCYL-HCYLL | Hoist Cylinder L/H/S | 67897 | 20934 | 5000
500058092 | CLB-MP-SUPP-WC015 -HYDSYS-HOVLV | Hoist Valve | 67897 | 67897 | 5000
500058091 | CLB-MP-SUPP-WC015 -STRSYS-STLTR | Steering Linkages and Tie Rods | 67897 | 51 | 5000
500058090 | CLB-MP-SUPP-WC015 -STRSYS-STOLC | Steering Oil Cooler | 67897 | 20934 | 5000
500058089 | CLB-MP-SUPP-WC015 -STRSYS-STACC-SACRH | Steering Accumulator R/H/S | 67897 | 20934 | 5000
500058088 | CLB-MP-SUPP-WC015 -STRSYS-STACC-SACLH | Steering Accumulator L/H/S | 67897 | 20934 | 5000
500058087 | CLB-MP-SUPP-WC015 -STRSYS-STRCY-STCYR | Steering Cylinder R/H/S | 67897 | 5147 | 5000
500058086 | CLB-MP-SUPP-WC015 -STRSYS-STRCY-STCYL | Steering Cylinder L/H/S | 67897 | 1397 | 5000
500058085 | CLB-MP-SUPP-WC015 -STRSYS-STHMU | Steering HMU | 67897 | 9224 | 5000
500058084 | CLB-MP-SUPP-WC015 -STRSYS-STPMP | Steering Pump | 67897 | 5147 | 5000
500058083 | CLB-MP-SUPP-WC015 -BRKSYS-SLACK-SLACR | Slack Adjustor Rear | 67897 | 1397 | 5000
500058082 | CLB-MP-SUPP-WC015 -BRKSYS-SLACK-SLACF | Slack Adjustor Front | 67897 | 1397 | 5000
500058081 | CLB-MP-SUPP-WC015 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H/Rear | 67897 | 1397 | 5000
500058080 | CLB-MP-SUPP-WC015 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H/Rear | 67897 | 1397 | 5000
500058079 | CLB-MP-SUPP-WC015 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 67897 | 1397 | 5000
500058078 | CLB-MP-SUPP-WC015 -BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom | 67897 | 1397 | 5000
500058077 | CLB-MP-SUPP-WC015 -BRKSYS-BROCO-BROCT | Brake Oil Cooler Rear Top | 67897 | 1397 | 5000
500058076 | CLB-MP-SUPP-WC015 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 67897 | 1397 | 5000
500058075 | CLB-MP-SUPP-WC015 -BRKSYS-MERTR | Mechanical Retarder | 67897 | 67897 | 5000
500058074 | CLB-MP-SUPP-WC015 -BRKSYS-BRVTR | Brake Treadle Valve | 67897 | 25102 | 5000
500058073 | CLB-MP-SUPP-WC015 -BRKSYS-BRVLV | Brake Valve | 67897 | 1397 | 5000
500058072 | CLB-MP-SUPP-WC015 -HYDSYS-HOPMP | Hoist & Rear Brake Cooling Pump | 67897 | 51 | 5000
500058071 | CLB-MP-SUPP-WC015 -BRKSYS-BACCM | Brake Accumulator | 67897 | 20934 | 5000
500058070 | CLB-MP-SUPP-WC015 -BRKSYS-SRVBK-SVBRR | Service Brake R/H/Rear | 67897 | 67897 | 5000
500058069 | CLB-MP-SUPP-WC015 -BRKSYS-SRVBK-SVBLR | Service Brake L/H/Rear | 67897 | 67897 | 5000
500058068 | CLB-MP-SUPP-WC015 -BRKSYS-SRVBK-SVBRF | Service Brake R/H/Front | 67897 | 67897 | 5000
500058067 | CLB-MP-SUPP-WC015 -BRKSYS-SRVBK-SVBLF | Service Brake L/H/Front | 67897 | 67897 | 5000
500058066 | CLB-MP-SUPP-WC015 -FDRSYS-AXLEC-HYPUM | Rear Axle Oil Pump | 67897 | 1397 | 5000
500058065 | CLB-MP-SUPP-WC015 -FDRSYS-AXLEC-MTFAN | Rear Axle Cooling Fan Motor | 67897 | 1397 | 5000
500058064 | CLB-MP-SUPP-WC015 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 67897 | 1397 | 5000
500058063 | CLB-MP-SUPP-WC015 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 67897 | 1397 | 5000
500058062 | CLB-MP-SUPP-WC015 -FDRSYS-DIFFL | Differential | 67897 | 1397 | 5000
500058061 | CLB-MP-SUPP-WC015 -FDRSYS-DRSHT | Transmission Drive Shaft | 67897 | 1397 | 5000
500058060 | CLB-MP-SUPP-WC015 -TRNSYS-TROLC | Transmission Oil Cooler | 67897 | 1397 | 5000
500058059 | CLB-MP-SUPP-WC015 -TRNSYS-TRPMP-TCCPP | TC/Park Brake/Scavenge Pump | 67897 | 1397 | 5000
500058058 | CLB-MP-SUPP-WC015 -TRNSYS-TRPMP-TMCPP | Transmission Pump | 67897 | 8275 | 5000
500058057 | CLB-MP-SUPP-WC015 -TRNSYS-TRANS | Transmission | 67897 | 1397 | 5000
500058056 | CLB-MP-SUPP-WC015 -TRNSYS-TRQUE | Torque Converter | 67897 | 1397 | 5000
500058055 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR-DRSHT | Drive Shaft, Engine Pump Drive | 67897 | 1397 | 5000
500058054 | CLB-MP-SUPP-WC015 -ENGINE-PMPDR | Engine Pump Drive | 67897 | 1397 | 5000
500058053 | CLB-MP-SUPP-WC015 -ENGINE-COSYS-RADTR | Engine Radiator | 67897 | 1397 | 5000
500058052 | CLB-MP-SUPP-WC015 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 67897 | 1397 | 5000
500058051 | CLB-MP-SUPP-WC015 -ENGINE-LUBSY-PREPP | Pre-Lubrication Pump | 67897 | 1397 | 5000
500058050 | CLB-MP-SUPP-WC015 -ENGINE-COMPR | Air Compressor | 67897 | 1397 | 5000
500058049 | CLB-MP-SUPP-WC015 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 67897 | 67897 | 5000
500058048 | CLB-MP-SUPP-WC015 -ENGINE-INTEX-AFTER | Aftercooler | 67897 | 1397 | 5000
500058047 | CLB-MP-SUPP-WC015 -ELCTLV-CHARG-ALTER | Alternator 24V | 67897 | 1397 | 5000
500058046 | CLB-MP-SUPP-WC015 -ENGINE-COSYS-COFAN | Fan Drive, Cooling System | 67897 | 67897 | 5000
500058045 | CLB-MP-SUPP-WC015 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 67897 | 1397 | 5000
500058044 | CLB-MP-SUPP-WC015 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 67897 | 1397 | 5000
500058043 | CLB-MP-SUPP-WC015 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 67897 | 1397 | 5000
500058042 | CLB-MP-SUPP-WC015 -ENGINE-COSYS-THERM | Thermostats/Regulators | 67897 | 1397 | 5000
500058041 | CLB-MP-SUPP-WC015 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 67897 | 1397 | 5000
500058040 | CLB-MP-SUPP-WC015 -ENGINE-COSYS-WTRPP | Water Pump Engine | 67897 | 1397 | 5000
500058039 | CLB-MP-SUPP-WC015 -ENGINE-INTEX-TBORR | Turbocharger R/H/Rear | 67897 | 1397 | 5000
500058038 | CLB-MP-SUPP-WC015 -ENGINE-INTEX-TBORF | Turbocharger R/H/Front | 67897 | 1397 | 5000
500058037 | CLB-MP-SUPP-WC015 -ENGINE-INTEX-TBOLR | Turbocharger L/H/Rear | 67897 | 1397 | 5000
500058036 | CLB-MP-SUPP-WC015 -ENGINE-INTEX-TBOLF | Turbocharger L/H/Front | 67897 | 1397 | 5000
500058035 | CLB-MP-SUPP-WC015 -ENGINE | Engine Assembly, Caterpillar 3512 | 67897 | 1397 | 5000
500057189 | CLB-MP-SUPP-WC015 | WC015 Lubrication & Mechanical Services | 67897 | 67897 | 5000
500057188 | CLB-MP-SUPP-WC015 | Caterpillar 785D Water Truck, WC015 | 67897 | 67897 | 5000
500132419 | CLB-MP-SUPP-WC014 -STRUCT-WTANK | WC014 Water Tank Module | 65823 | 65823 | 5000
500100661 | CLB-MP-SUPP-WC014 -TRNSYS | WC014 Transmission System | 65823 | 19464 | 5000
500081536 | CLB-MP-SUPP-WC014 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 65823 | 65823 | 5000
500081511 | CLB-MP-SUPP-WC014 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 65823 | 65823 | 5000
500058034 | CLB-MP-SUPP-WC014 -FRSUPP | Fire Suppression System | 65823 | 545 | 5000
500058033 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-CANON | Water Tank Cannon | 65823 | 12836 | 5000
500058032 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-SPRAY | Water Tank Sprays | 65823 | 65823 | 5000
500058031 | CLB-MP-SUPP-WC014 -STRUCT-WTANK-WTPPM | Water Tank Pump/Motor | 65823 | 7973 | 5000
500058030 | CLB-MP-SUPP-WC014 -STRUCT-SUSPN-SCYRR | Suspension Cylinder R/H/Rear | 65823 | 545 | 5000
500058029 | CLB-MP-SUPP-WC014 -STRUCT-SUSPN-SCYLR | Suspension Cylinder L/H/Rear | 65823 | 545 | 5000
500058028 | CLB-MP-SUPP-WC014 -STRUCT-SUSPN-SCYRF | Suspension Cylinder R/H/Front | 65823 | 545 | 5000
500058027 | CLB-MP-SUPP-WC014 -STRUCT-SUSPN-SCYLF | Suspension Cylinder L/H/Front | 65823 | 545 | 5000
500058026 | CLB-MP-SUPP-WC014 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H/Front | 65823 | 19464 | 5000
500058025 | CLB-MP-SUPP-WC014 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H/Front | 65823 | 19464 | 5000
500058024 | CLB-MP-SUPP-WC014 -STRUCT-CHASS-TAGLK | Tag Link | 65823 | 41204 | 5000
500058023 | CLB-MP-SUPP-WC014 -STRUCT-CHASS-AFRME | A Frame | 65823 | 19464 | 5000
500058022 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-AIRCN | Air Conditioning System | 65823 | 545 | 5000
500058021 | CLB-MP-SUPP-WC014 -STRUCT-CABIN-SEATS | Operators Seat | 65823 | 545 | 5000
500058020 | CLB-MP-SUPP-WC014 -PNEUMC-START | Pneumatic Starter Motor | 65823 | 545 | 5000
500058019 | CLB-MP-SUPP-WC014 -PNEUMC-AIRDR | Air Drier | 65823 | 545 | 5000
500058018 | CLB-MP-SUPP-WC014 -GRSYST-ALBPP | Auto Lube Pump | 65823 | 35150 | 5000
500058017 | CLB-MP-SUPP-WC014 -GRSYST-GRINJ | Auto Lube Injectors | 65823 | 65823 | 5000
500058016 | CLB-MP-SUPP-WC014 -HYDSYS-HOCYL-HCYLR | Hoist Cylinder R/H/S | 65823 | 545 | 5000
500058015 | CLB-MP-SUPP-WC014 -HYDSYS-HOCYL-HCYLL | Hoist Cylinder L/H/S | 65823 | 19464 | 5000
500058014 | CLB-MP-SUPP-WC014 -HYDSYS-HOVLV | Hoist Valve | 65823 | 65823 | 5000
500058013 | CLB-MP-SUPP-WC014 -STRSYS-STLTR | Steering Linkages and Tie Rods | 65823 | 7973 | 5000
500058012 | CLB-MP-SUPP-WC014 -STRSYS-STOLC | Steering Oil Cooler | 65823 | 19464 | 5000
500058011 | CLB-MP-SUPP-WC014 -STRSYS-STACC-SACRH | Steering Accumulator R/H/S | 65823 | 19464 | 5000
500058010 | CLB-MP-SUPP-WC014 -STRSYS-STACC-SACLH | Steering Accumulator L/H/S | 65823 | 19464 | 5000
500058009 | CLB-MP-SUPP-WC014 -STRSYS-STRCY-STCYR | Steering Cylinder R/H/S | 65823 | 6147 | 5000
500058008 | CLB-MP-SUPP-WC014 -STRSYS-STRCY-STCYL | Steering Cylinder L/H/S | 65823 | 4096 | 5000
500058007 | CLB-MP-SUPP-WC014 -STRSYS-STHMU | Steering HMU | 65823 | 4096 | 5000
500058006 | CLB-MP-SUPP-WC014 -STRSYS-STPMP | Steering Pump | 65823 | 4096 | 5000
500058005 | CLB-MP-SUPP-WC014 -BRKSYS-SLACK-SLACR | Slack Adjustor Rear | 65823 | 545 | 5000
500058004 | CLB-MP-SUPP-WC014 -BRKSYS-SLACK-SLACF | Slack Adjustor Front | 65823 | 545 | 5000
500058003 | CLB-MP-SUPP-WC014 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H/Rear | 65823 | 545 | 5000
500058002 | CLB-MP-SUPP-WC014 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H/Rear | 65823 | 545 | 5000
500058001 | CLB-MP-SUPP-WC014 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 65823 | 545 | 5000
500058000 | CLB-MP-SUPP-WC014 -BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom | 65823 | 545 | 5000
500057999 | CLB-MP-SUPP-WC014 -BRKSYS-BROCO-BROCT | Brake Oil Cooler Rear Top | 65823 | 545 | 5000
500057998 | CLB-MP-SUPP-WC014 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 65823 | 545 | 5000
500057997 | CLB-MP-SUPP-WC014 -BRKSYS-MERTR | Mechanical Retarder | 65823 | 65823 | 5000
500057996 | CLB-MP-SUPP-WC014 -BRKSYS-BRVTR | Brake Treadle Valve | 65823 | 65823 | 5000
500057995 | CLB-MP-SUPP-WC014 -BRKSYS-BRVLV | Brake Valve | 65823 | 545 | 5000
500057994 | CLB-MP-SUPP-WC014 -HYDSYS-HOPMP | Hoist & Rear Brake Cooling Pump | 65823 | 7973 | 5000
500057993 | CLB-MP-SUPP-WC014 -BRKSYS-BACCM | Brake Accumulator | 65823 | 4096 | 5000
500057992 | CLB-MP-SUPP-WC014 -BRKSYS-SRVBK-SVBRR | Service Brake R/H/Rear | 65823 | 65823 | 5000
500057991 | CLB-MP-SUPP-WC014 -BRKSYS-SRVBK-SVBLR | Service Brake L/H/Rear | 65823 | 65823 | 5000
500057990 | CLB-MP-SUPP-WC014 -BRKSYS-SRVBK-SVBRF | Service Brake R/H/Front | 65823 | 65823 | 5000
500057989 | CLB-MP-SUPP-WC014 -BRKSYS-SRVBK-SVBLF | Service Brake L/H/Front | 65823 | 65823 | 5000
500057988 | CLB-MP-SUPP-WC014 -FDRSYS-AXLEC-HYPUM | Rear Axle Oil Pump | 65823 | 545 | 5000
500057987 | CLB-MP-SUPP-WC014 -FDRSYS-AXLEC-MTFAN | Rear Axle Cooling Fan Motor | 65823 | 545 | 5000
500057986 | CLB-MP-SUPP-WC014 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 65823 | 12235 | 5000
500057985 | CLB-MP-SUPP-WC014 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 65823 | 4755 | 5000
500057984 | CLB-MP-SUPP-WC014 -FDRSYS-DIFFL | Differential | 65823 | 5401 | 5000
500057983 | CLB-MP-SUPP-WC014 -FDRSYS-DRSHT | Transmission Drive Shaft | 65823 | 545 | 5000
500057982 | CLB-MP-SUPP-WC014 -TRNSYS-TROLC | Transmission Oil Cooler | 65823 | 545 | 5000
500057981 | CLB-MP-SUPP-WC014 -TRNSYS-TRPMP-TCCPP | TC/Park Brake/Scavenge Pump | 65823 | 545 | 5000
500057980 | CLB-MP-SUPP-WC014 -TRNSYS-TRPMP-TMCPP | Transmission Pump | 65823 | 545 | 5000
500057979 | CLB-MP-SUPP-WC014 -TRNSYS-TRANS | Transmission | 65823 | 545 | 5000
500057978 | CLB-MP-SUPP-WC014 -TRNSYS-TRQUE | Torque Converter | 65823 | 545 | 5000
500057977 | CLB-MP-SUPP-WC014 -ENGINE-PMPDR-DRSHT | Drive Shaft, Engine Pump Drive | 65823 | 545 | 5000
500057976 | CLB-MP-SUPP-WC014 -ENGINE-PMPDR | Engine Pump Drive | 65823 | 545 | 5000
500057975 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-RADTR | Engine Radiator | 65823 | 9247 | 5000
500057974 | CLB-MP-SUPP-WC014 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 65823 | 545 | 5000
500057973 | CLB-MP-SUPP-WC014 -ENGINE-LUBSY-PREPP | Pre-Lubrication Pump | 65823 | 545 | 5000
500057972 | CLB-MP-SUPP-WC014 -ENGINE-COMPR | Air Compressor | 65823 | 545 | 5000
500057971 | CLB-MP-SUPP-WC014 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 65823 | 545 | 5000
500057970 | CLB-MP-SUPP-WC014 -ENGINE-INTEX-AFTER | Aftercooler | 65823 | 545 | 5000
500057969 | CLB-MP-SUPP-WC014 -ELCTLV-CHARG-ALTER | Alternator 24V | 65823 | 545 | 5000
500057968 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-COFAN | Fan Drive, Cooling System | 65823 | 18558 | 5000
500057967 | CLB-MP-SUPP-WC014 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 65823 | 545 | 5000
500057966 | CLB-MP-SUPP-WC014 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 65823 | 545 | 5000
500057965 | CLB-MP-SUPP-WC014 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 65823 | 545 | 5000
500057964 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-THERM | Thermostats/Regulators | 65823 | 545 | 5000
500057963 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 65823 | 545 | 5000
500057962 | CLB-MP-SUPP-WC014 -ENGINE-COSYS-WTRPP | Water Pump Engine | 65823 | 545 | 5000
500057961 | CLB-MP-SUPP-WC014 -ENGINE-INTEX-TBORR | Turbocharger R/H/Rear | 65823 | 545 | 5000
500057960 | CLB-MP-SUPP-WC014 -ENGINE-INTEX-TBORF | Turbocharger R/H/Front | 65823 | 545 | 5000
500057959 | CLB-MP-SUPP-WC014 -ENGINE-INTEX-TBOLR | Turbocharger L/H/Rear | 65823 | 545 | 5000
500057958 | CLB-MP-SUPP-WC014 -ENGINE-INTEX-TBOLF | Turbocharger L/H/Front | 65823 | 545 | 5000
500057957 | CLB-MP-SUPP-WC014 -ENGINE | Engine Assembly, Caterpillar 3512 | 65823 | 545 | 5000
500057187 | CLB-MP-SUPP-WC014 | WC014 Lubrication & Mechanical Services | 65823 | 65823 | 5000
500057186 | CLB-MP-SUPP-WC014 | Caterpillar 785D Water Truck, WC014 | 65823 | 65823 | 5000
500146807 | CLB-MP-SUPP-WC013 -BRKSYS-BACCM | CAT 785D Brake Accumulator | 20952 | 20952 | 5000
500146806 | CLB-MP-SUPP-WC013 -STRSYS-STACC | CAT 785D Steering Accumulator RH | 20952 | 20952 | 5000
500146805 | CLB-MP-SUPP-WC013 -STRSYS-STACC | CAT 785D Steering Accumulator LH | 20952 | 20952 | 5000
500132418 | CLB-MP-SUPP-WC013 -STRUCT-WTANK | WC013 Water Tank Module | 63825 | 63825 | 5000
500100660 | CLB-MP-SUPP-WC013 -TRNSYS | WC013 Transmission System | 63833 | 20952 | 5000
500081535 | CLB-MP-SUPP-WC013 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 63833 | 63833 | 5000
500081510 | CLB-MP-SUPP-WC013 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 63833 | 63833 | 5000
500057956 | CLB-MP-SUPP-WC013 -FRSUPP | Fire Suppression System | 63833 | 63833 | 5000
500057955 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-CANON | Water Tank Cannon | 63833 | 10034 | 5000
500057954 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-SPRAY | Water Tank Sprays | 63833 | 63833 | 5000
500057953 | CLB-MP-SUPP-WC013 -STRUCT-WTANK-WTPPM | Water Tank Pump/Motor | 63833 | 8582 | 5000
500057952 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYRR | Suspension Cylinder R/H/Rear | 63833 | 20952 | 5000
500057951 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYLR | Suspension Cylinder L/H/Rear | 63833 | 20952 | 5000
500057950 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYRF | Suspension Cylinder R/H/Front | 63833 | 20952 | 5000
500057949 | CLB-MP-SUPP-WC013 -STRUCT-SUSPN-SCYLF | Suspension Cylinder L/H/Front | 63833 | 20952 | 5000
500057948 | CLB-MP-SUPP-WC013 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H/Front | 63833 | 20952 | 5000
500057947 | CLB-MP-SUPP-WC013 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H/Front | 63833 | 20952 | 5000
500057946 | CLB-MP-SUPP-WC013 -STRUCT-CHASS-TAGLK | Tag Link | 63833 | 14620 | 5000
500057945 | CLB-MP-SUPP-WC013 -STRUCT-CHASS-AFRME | A Frame | 63833 | 63833 | 5000
500057944 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-AIRCN | Air Conditioning System | 63833 | 10928 | 5000
500057943 | CLB-MP-SUPP-WC013 -STRUCT-CABIN-SEATS | Operators Seat | 63833 | 10370 | 5000
500057942 | CLB-MP-SUPP-WC013 -PNEUMC-START | Pneumatic Starter Motor | 63833 | 3387 | 5000
500057941 | CLB-MP-SUPP-WC013 -PNEUMC-AIRDR | Air Drier | 63833 | 10928 | 5000
500057940 | CLB-MP-SUPP-WC013 -GRSYST-ALBPP | Auto Lube Pump | 63833 | 23012 | 5000
500057939 | CLB-MP-SUPP-WC013 -GRSYST-GRINJ | Auto Lube Injectors | 63833 | 63833 | 5000
500057938 | CLB-MP-SUPP-WC013 -HYDSYS-HOCYL-HCYLR | Hoist Cylinder R/H/S | 63833 | 20952 | 5000
500057937 | CLB-MP-SUPP-WC013 -HYDSYS-HOCYL-HCYLL | Hoist Cylinder L/H/S | 63833 | 20952 | 5000
500057936 | CLB-MP-SUPP-WC013 -HYDSYS-HOVLV | Hoist Valve | 63833 | 63833 | 5000
500057935 | CLB-MP-SUPP-WC013 -STRSYS-STLTR | Steering Linkages and Tie Rods | 63833 | 4893 | 5000
500057934 | CLB-MP-SUPP-WC013 -STRSYS-STOLC | Steering Oil Cooler | 63833 | 20952 | 5000
500057933 | CLB-MP-SUPP-WC013 -STRSYS-STACC-SACRH | Steering Accumulator R/H/S | 63833 | 20952 | 5000
500057932 | CLB-MP-SUPP-WC013 -STRSYS-STACC-SACLH | Steering Accumulator L/H/S | 63833 | 20952 | 5000
500057931 | CLB-MP-SUPP-WC013 -STRSYS-STRCY-STCYR | Steering Cylinder R/H/S | 63833 | 6926 | 5000
500057930 | CLB-MP-SUPP-WC013 -STRSYS-STRCY-STCYL | Steering Cylinder L/H/S | 63833 | 4893 | 5000
500057929 | CLB-MP-SUPP-WC013 -STRSYS-STHMU | Steering HMU | 63833 | 15155 | 5000
500057928 | CLB-MP-SUPP-WC013 -STRSYS-STPMP | Steering Pump | 63833 | 20952 | 5000
500057927 | CLB-MP-SUPP-WC013 -BRKSYS-SLACK-SLACR | Slack Adjustor Rear | 63833 | 3391 | 5000
500057926 | CLB-MP-SUPP-WC013 -BRKSYS-SLACK-SLACF | Slack Adjustor Front | 63833 | 20952 | 5000
500057925 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H/Rear | 63833 | 20952 | 5000
500057924 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H/Rear | 63833 | 20952 | 5000
500057923 | CLB-MP-SUPP-WC013 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 63833 | 20952 | 5000
500057922 | CLB-MP-SUPP-WC013 -BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom | 63833 | 3387 | 5000
500057921 | CLB-MP-SUPP-WC013 -BRKSYS-BROCO-BROCT | Brake Oil Cooler Rear Top | 63833 | 3387 | 5000
500057920 | CLB-MP-SUPP-WC013 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 63833 | 20952 | 5000
500057919 | CLB-MP-SUPP-WC013 -BRKSYS-MERTR | Mechanical Retarder | 63833 | 63833 | 5000
500057918 | CLB-MP-SUPP-WC013 -BRKSYS-BRVTR | Brake Treadle Valve | 63833 | 63833 | 5000
500057917 | CLB-MP-SUPP-WC013 -BRKSYS-BRVLV | Brake Valve | 63833 | 20952 | 5000
500057916 | CLB-MP-SUPP-WC013 -HYDSYS-HOPMP | Hoist & Rear Brake Cooling Pump | 63833 | 10034 | 5000
500057915 | CLB-MP-SUPP-WC013 -BRKSYS-BACCM | Brake Accumulator | 63833 | 20952 | 5000
500057914 | CLB-MP-SUPP-WC013 -BRKSYS-SRVBK-SVBRR | Service Brake R/H/Rear | 63833 | 63833 | 5000
500057913 | CLB-MP-SUPP-WC013 -BRKSYS-SRVBK-SVBLR | Service Brake L/H/Rear | 63833 | 63833 | 5000
500057912 | CLB-MP-SUPP-WC013 -BRKSYS-SRVBK-SVBRF | Service Brake R/H/Front | 63833 | 63833 | 5000
500057911 | CLB-MP-SUPP-WC013 -BRKSYS-SRVBK-SVBLF | Service Brake L/H/Front | 63833 | 63833 | 5000
500057910 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-HYPUM | Rear Axle Oil Pump | 63833 | 10928 | 5000
500057909 | CLB-MP-SUPP-WC013 -FDRSYS-AXLEC-MTFAN | Rear Axle Cooling Fan Motor | 63833 | 10928 | 5000
500057908 | CLB-MP-SUPP-WC013 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 63833 | 20952 | 5000
500057907 | CLB-MP-SUPP-WC013 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 63833 | 20952 | 5000
500057906 | CLB-MP-SUPP-WC013 -FDRSYS-DIFFL | Differential | 63833 | 20952 | 5000
500057905 | CLB-MP-SUPP-WC013 -FDRSYS-DRSHT | Transmission Drive Shaft | 63833 | 20952 | 5000
500057904 | CLB-MP-SUPP-WC013 -TRNSYS-TROLC | Transmission Oil Cooler | 63833 | 20952 | 5000
500057903 | CLB-MP-SUPP-WC013 -TRNSYS-TRPMP-TCCPP | TC/Park Brake/Scavenge Pump | 63833 | 20952 | 5000
500057902 | CLB-MP-SUPP-WC013 -TRNSYS-TRPMP-TMCPP | Transmission Pump | 63833 | 20952 | 5000
500057901 | CLB-MP-SUPP-WC013 -TRNSYS-TRANS | Transmission | 63833 | 20952 | 5000
500057900 | CLB-MP-SUPP-WC013 -TRNSYS-TRQUE | Torque Converter | 63833 | 3387 | 5000
500057899 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR-DRSHT | Drive Shaft, Engine Pump Drive | 63833 | 10962 | 5000
500057898 | CLB-MP-SUPP-WC013 -ENGINE-PMPDR | Engine Pump Drive | 63833 | 20952 | 5000
500057897 | CLB-MP-SUPP-WC013 -ENGINE-COSYS-RADTR | Engine Radiator | 63833 | 3387 | 5000
500057896 | CLB-MP-SUPP-WC013 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 63833 | 3387 | 5000
500057895 | CLB-MP-SUPP-WC013 -ENGINE-LUBSY-PREPP | Pre-Lubrication Pump | 63833 | 3387 | 5000
500057894 | CLB-MP-SUPP-WC013 -ENGINE-COMPR | Air Compressor | 63833 | 3387 | 5000
500057893 | CLB-MP-SUPP-WC013 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 63833 | 3387 | 5000
500057892 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-AFTER | Aftercooler | 63833 | 20952 | 5000
500057891 | CLB-MP-SUPP-WC013 -ELCTLV-CHARG-ALTER | Alternator 24V | 63833 | 3387 | 5000
500057890 | CLB-MP-SUPP-WC013 -ENGINE-COSYS-COFAN | Fan Drive, Cooling System | 63833 | 63833 | 5000
500057889 | CLB-MP-SUPP-WC013 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 63833 | 3387 | 5000
500057888 | CLB-MP-SUPP-WC013 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 63833 | 3387 | 5000
500057887 | CLB-MP-SUPP-WC013 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 63833 | 3387 | 5000
500057886 | CLB-MP-SUPP-WC013 -ENGINE-COSYS-THERM | Thermostats/Regulators | 63833 | 3387 | 5000
500057885 | CLB-MP-SUPP-WC013 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 63833 | 3387 | 5000
500057884 | CLB-MP-SUPP-WC013 -ENGINE-COSYS-WTRPP | Water Pump Engine | 63833 | 3387 | 5000
500057883 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-TBORR | Turbocharger R/H/Rear | 63833 | 3387 | 5000
500057882 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-TBORF | Turbocharger R/H/Front | 63833 | 3387 | 5000
500057881 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-TBOLR | Turbocharger L/H/Rear | 63833 | 3387 | 5000
500057880 | CLB-MP-SUPP-WC013 -ENGINE-INTEX-TBOLF | Turbocharger L/H/Front | 63833 | 3387 | 5000
500057879 | CLB-MP-SUPP-WC013 -ENGINE | Engine Assembly, Caterpillar 3512 | 63833 | 3387 | 5000
500057185 | CLB-MP-SUPP-WC013 | WC013 Lubrication & Mechanical Services | 63833 | 63833 | 5000
500057184 | CLB-MP-SUPP-WC013 | Caterpillar 785D Water Truck, WC013 | 63833 | 63833 | 5000
500146804 | CLB-MP-SUPP-WC012 -BRKSYS-BACCM | CAT 785D Brake Accumulator | 22004 | 22004 | 5000
500146803 | CLB-MP-SUPP-WC012 -STRSYS-STACC | CAT 785D Steering Accumulator RH | 22004 | 22004 | 5000
500146682 | CLB-MP-SUPP-WC012 -STRSYS-STACC | CAT 785D Steering Accumulator LH | 22004 | 22004 | 5000
500132417 | CLB-MP-SUPP-WC012 -STRUCT-WTANK | WC012 Water Tank Module | 67273 | 67273 | 5000
500100659 | CLB-MP-SUPP-WC012 -TRNSYS | WC012 Transmission System | 67273 | 32686 | 5000
500081534 | CLB-MP-SUPP-WC012 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 67273 | 67273 | 5000
500081509 | CLB-MP-SUPP-WC012 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 67273 | 67273 | 5000
500057878 | CLB-MP-SUPP-WC012 -FRSUPP | Fire Suppression System | 67273 | 67273 | 5000
500057877 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-CANON | Water Tank Cannon | 67273 | 3900 | 5000
500057876 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-SPRAY | Water Tank Sprays | 67273 | 67273 | 5000
500057875 | CLB-MP-SUPP-WC012 -STRUCT-WTANK-WTPPM | Water Tank Pump/Motor | 67273 | 67273 | 5000
500057874 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYRR | Suspension Cylinder R/H/Rear | 67273 | 21499 | 5000
500057873 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYLR | Suspension Cylinder L/H/Rear | 67273 | 22004 | 5000
500057872 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYRF | Suspension Cylinder R/H/Front | 67273 | 22004 | 5000
500057871 | CLB-MP-SUPP-WC012 -STRUCT-SUSPN-SCYLF | Suspension Cylinder L/H/Front | 67273 | 22004 | 5000
500057870 | CLB-MP-SUPP-WC012 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H/Front | 67273 | 22004 | 5000
500057869 | CLB-MP-SUPP-WC012 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H/Front | 67273 | 22004 | 5000
500057868 | CLB-MP-SUPP-WC012 -STRUCT-CHASS-TAGLK | Tag Link | 67273 | 67273 | 5000
500057867 | CLB-MP-SUPP-WC012 -STRUCT-CHASS-AFRME | A Frame | 67273 | 67273 | 5000
500057866 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-AIRCN | Air Conditioning System | 67273 | 10760 | 5000
500057865 | CLB-MP-SUPP-WC012 -STRUCT-CABIN-SEATS | Operators Seat | 67273 | 10220 | 5000
500057864 | CLB-MP-SUPP-WC012 -PNEUMC-START | Pneumatic Starter Motor | 67273 | 10760 | 5000
500057863 | CLB-MP-SUPP-WC012 -PNEUMC-AIRDR | Air Drier | 67273 | 22004 | 5000
500057862 | CLB-MP-SUPP-WC012 -GRSYST-ALBPP | Auto Lube Pump | 67273 | 17190 | 5000
500057861 | CLB-MP-SUPP-WC012 -GRSYST-GRINJ | Auto Lube Injectors | 67273 | 67273 | 5000
500057860 | CLB-MP-SUPP-WC012 -HYDSYS-HOCYL-HCYLR | Hoist Cylinder R/H/S | 67273 | 22004 | 5000
500057859 | CLB-MP-SUPP-WC012 -HYDSYS-HOCYL-HCYLL | Hoist Cylinder L/H/S | 67273 | 22004 | 5000
500057858 | CLB-MP-SUPP-WC012 -HYDSYS-HOVLV | Hoist Valve | 67273 | 67273 | 5000
500057857 | CLB-MP-SUPP-WC012 -STRSYS-STLTR | Steering Linkages and Tie Rods | 67273 | 22004 | 5000
500057856 | CLB-MP-SUPP-WC012 -STRSYS-STOLC | Steering Oil Cooler | 67273 | 6542 | 5000
500057855 | CLB-MP-SUPP-WC012 -STRSYS-STACC-SACRH | Steering Accumulator R/H/S | 67273 | 6542 | 5000
500057854 | CLB-MP-SUPP-WC012 -STRSYS-STACC-SACLH | Steering Accumulator L/H/S | 67273 | 6542 | 5000
500057853 | CLB-MP-SUPP-WC012 -STRSYS-STRCY-STCYR | Steering Cylinder R/H/S | 67273 | 6542 | 5000
500057852 | CLB-MP-SUPP-WC012 -STRSYS-STRCY-STCYL | Steering Cylinder L/H/S | 67273 | 6542 | 5000
500057851 | CLB-MP-SUPP-WC012 -STRSYS-STHMU | Steering HMU | 67273 | 6542 | 5000
500057850 | CLB-MP-SUPP-WC012 -STRSYS-STPMP | Steering Pump | 67273 | 6542 | 5000
500057849 | CLB-MP-SUPP-WC012 -BRKSYS-SLACK-SLACR | Slack Adjustor Rear | 67273 | 22004 | 5000
500057848 | CLB-MP-SUPP-WC012 -BRKSYS-SLACK-SLACF | Slack Adjustor Front | 67273 | 22004 | 5000
500057847 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H/Rear | 67273 | 22004 | 5000
500057846 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H/Rear | 67273 | 22004 | 5000
500057845 | CLB-MP-SUPP-WC012 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 67273 | 22004 | 5000
500057844 | CLB-MP-SUPP-WC012 -BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom | 67273 | 67273 | 5000
500057843 | CLB-MP-SUPP-WC012 -BRKSYS-BROCO-BROCT | Brake Oil Cooler Rear Top | 67273 | 67273 | 5000
500057842 | CLB-MP-SUPP-WC012 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 67273 | 22004 | 5000
500057841 | CLB-MP-SUPP-WC012 -BRKSYS-MERTR | Mechanical Retarder | 67273 | 67273 | 5000
500057840 | CLB-MP-SUPP-WC012 -BRKSYS-BRVTR | Brake Treadle Valve | 67273 | 67273 | 5000
500057839 | CLB-MP-SUPP-WC012 -BRKSYS-BRVLV | Brake Valve | 67273 | 22004 | 5000
500057838 | CLB-MP-SUPP-WC012 -HYDSYS-HOPMP | Hoist & Rear Brake Cooling Pump | 67273 | 17626 | 5000
500057837 | CLB-MP-SUPP-WC012 -BRKSYS-BACCM | Brake Accumulator | 67273 | 6542 | 5000
500057836 | CLB-MP-SUPP-WC012 -BRKSYS-SRVBK-SVBRR | Service Brake R/H/Rear | 67273 | 67273 | 5000
500057835 | CLB-MP-SUPP-WC012 -BRKSYS-SRVBK-SVBLR | Service Brake L/H/Rear | 67273 | 67273 | 5000
500057834 | CLB-MP-SUPP-WC012 -BRKSYS-SRVBK-SVBRF | Service Brake R/H/Front | 67273 | 67273 | 5000
500057833 | CLB-MP-SUPP-WC012 -BRKSYS-SRVBK-SVBLF | Service Brake L/H/Front | 67273 | 67273 | 5000
500057832 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-HYPUM | Rear Axle Oil Pump | 67273 | 11372 | 5000
500057831 | CLB-MP-SUPP-WC012 -FDRSYS-AXLEC-MTFAN | Rear Axle Cooling Fan Motor | 67273 | 11372 | 5000
500057830 | CLB-MP-SUPP-WC012 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 67273 | 22004 | 5000
500057829 | CLB-MP-SUPP-WC012 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 67273 | 22004 | 5000
500057828 | CLB-MP-SUPP-WC012 -FDRSYS-DIFFL | Differential | 67273 | 22004 | 5000
500057827 | CLB-MP-SUPP-WC012 -FDRSYS-DRSHT | Transmission Drive Shaft | 67273 | 4720 | 5000
500057826 | CLB-MP-SUPP-WC012 -TRNSYS-TROLC | Transmission Oil Cooler | 67273 | 22004 | 5000
500057825 | CLB-MP-SUPP-WC012 -TRNSYS-TRPMP-TCCPP | TC/Park Brake/Scavenge Pump | 67273 | 13332 | 5000
500057824 | CLB-MP-SUPP-WC012 -TRNSYS-TRPMP-TMCPP | Transmission Pump | 67273 | 22004 | 5000
500057823 | CLB-MP-SUPP-WC012 -TRNSYS-TRANS | Transmission | 67273 | 22004 | 5000
500057822 | CLB-MP-SUPP-WC012 -TRNSYS-TRQUE | Torque Converter | 67273 | 22004 | 5000
500057821 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR-DRSHT | Drive Shaft, Engine Pump Drive | 67273 | 11372 | 5000
500057820 | CLB-MP-SUPP-WC012 -ENGINE-PMPDR | Engine Pump Drive | 67273 | 22004 | 5000
500057819 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-RADTR | Engine Radiator | 67273 | 11305 | 5000
500057818 | CLB-MP-SUPP-WC012 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 67273 | 10760 | 5000
500057817 | CLB-MP-SUPP-WC012 -ENGINE-LUBSY-PREPP | Pre-Lubrication Pump | 67273 | 19704 | 5000
500057816 | CLB-MP-SUPP-WC012 -ENGINE-COMPR | Air Compressor | 67273 | 10760 | 5000
500057815 | CLB-MP-SUPP-WC012 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 67273 | 20856 | 5000
500057814 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-AFTER | Aftercooler | 67273 | 22004 | 5000
500057813 | CLB-MP-SUPP-WC012 -ELCTLV-CHARG-ALTER | Alternator 24V | 67273 | 6542 | 5000
500057812 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-COFAN | Fan Drive, Cooling System | 67273 | 20856 | 5000
500057811 | CLB-MP-SUPP-WC012 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 67273 | 10760 | 5000
500057810 | CLB-MP-SUPP-WC012 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 67273 | 10760 | 5000
500057809 | CLB-MP-SUPP-WC012 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 67273 | 10760 | 5000
500057808 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-THERM | Thermostats/Regulators | 67273 | 10760 | 5000
500057807 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 67273 | 10760 | 5000
500057806 | CLB-MP-SUPP-WC012 -ENGINE-COSYS-WTRPP | Water Pump Engine | 67273 | 10760 | 5000
500057805 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-TBORR | Turbocharger R/H/Rear | 67273 | 10760 | 5000
500057804 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-TBORF | Turbocharger R/H/Front | 67273 | 10760 | 5000
500057803 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-TBOLR | Turbocharger L/H/Rear | 67273 | 10760 | 5000
500057802 | CLB-MP-SUPP-WC012 -ENGINE-INTEX-TBOLF | Turbocharger L/H/Front | 67273 | 10760 | 5000
500057801 | CLB-MP-SUPP-WC012 -ENGINE | Engine Assembly, Caterpillar 3512 | 67273 | 20856 | 5000
500057183 | CLB-MP-SUPP-WC012 | WC012 Lubrication & Mechanical Services | 67273 | 67273 | 5000
500057182 | CLB-MP-SUPP-WC012 | Caterpillar 785D Water Truck, WC012 | 67273 | 67273 | 5000
500146680 | CLB-MP-SUPP-WC011 -BRKSYS-BACCM | CAT 785D Brake Accumulator | 21040 | 21040 | 5000
500146679 | CLB-MP-SUPP-WC011 -STRSYS-STACC | CAT 785D Steering Accumulator RH | 21040 | 21040 | 5000
500146678 | CLB-MP-SUPP-WC011 -STRSYS-STACC | CAT 785D Steering Accumulator LH | 21040 | 21040 | 5000
500132416 | CLB-MP-SUPP-WC011 -STRUCT-WTANK | WC011 Water Tank Module | 64099 | 64099 | 5000
500100658 | CLB-MP-SUPP-WC011 -TRNSYS | WC011 Transmission System | 64118 | 31285 | 5000
500081533 | CLB-MP-SUPP-WC011 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 64118 | 64118 | 5000
500081508 | CLB-MP-SUPP-WC011 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 64118 | 64118 | 5000
500057800 | CLB-MP-SUPP-WC011 -FRSUPP | Fire Suppression System | 64118 | 1755 | 5000
500057799 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-CANON | Water Tank Cannon | 64118 | 9073 | 5000
500057798 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-SPRAY | Water Tank Sprays | 64118 | 18597 | 5000
500057797 | CLB-MP-SUPP-WC011 -STRUCT-WTANK-WTPPM | Water Tank Pump/Motor | 64118 | 1145 | 5000
500057796 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYRR | Suspension Cylinder R/H/Rear | 64118 | 14683 | 5000
500057795 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYLR | Suspension Cylinder L/H/Rear | 64118 | 12272 | 5000
500057794 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYRF | Suspension Cylinder R/H/Front | 64118 | 1755 | 5000
500057793 | CLB-MP-SUPP-WC011 -STRUCT-SUSPN-SCYLF | Suspension Cylinder L/H/Front | 64118 | 1755 | 5000
500057792 | CLB-MP-SUPP-WC011 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H/Front | 64118 | 2758 | 5000
500057791 | CLB-MP-SUPP-WC011 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H/Front | 64118 | 1755 | 5000
500057790 | CLB-MP-SUPP-WC011 -STRUCT-CHASS-TAGLK | Tag Link | 64118 | 7867 | 5000
500057789 | CLB-MP-SUPP-WC011 -STRUCT-CHASS-AFRME | A Frame | 64118 | 1755 | 5000
500057788 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-AIRCN | Air Conditioning System | 64118 | 1755 | 5000
500057787 | CLB-MP-SUPP-WC011 -STRUCT-CABIN-SEATS | Operators Seat | 64118 | 1755 | 5000
500057786 | CLB-MP-SUPP-WC011 -PNEUMC-START | Pneumatic Starter Motor | 64118 | 1755 | 5000
500057785 | CLB-MP-SUPP-WC011 -PNEUMC-AIRDR | Air Drier | 64118 | 21040 | 5000
500057784 | CLB-MP-SUPP-WC011 -GRSYST-ALBPP | Auto Lube Pump | 64118 | 1755 | 5000
500057783 | CLB-MP-SUPP-WC011 -GRSYST-GRINJ | Auto Lube Injectors | 64118 | 64118 | 5000
500057782 | CLB-MP-SUPP-WC011 -HYDSYS-HOCYL-HCYLR | Hoist Cylinder R/H/S | 64118 | 21040 | 5000
500057781 | CLB-MP-SUPP-WC011 -HYDSYS-HOCYL-HCYLL | Hoist Cylinder L/H/S | 64118 | 21040 | 5000
500057780 | CLB-MP-SUPP-WC011 -HYDSYS-HOVLV | Hoist Valve | 64118 | 64118 | 5000
500057779 | CLB-MP-SUPP-WC011 -STRSYS-STLTR | Steering Linkages and Tie Rods | 64118 | 1755 | 5000
500057778 | CLB-MP-SUPP-WC011 -STRSYS-STOLC | Steering Oil Cooler | 64118 | 4490 | 5000
500057777 | CLB-MP-SUPP-WC011 -STRSYS-STACC-SACRH | Steering Accumulator R/H/S | 64118 | 1755 | 5000
500057776 | CLB-MP-SUPP-WC011 -STRSYS-STACC-SACLH | Steering Accumulator L/H/S | 64118 | 4489 | 5000
500057775 | CLB-MP-SUPP-WC011 -STRSYS-STRCY-STCYR | Steering Cylinder R/H/S | 64118 | 7306 | 5000
500057774 | CLB-MP-SUPP-WC011 -STRSYS-STRCY-STCYL | Steering Cylinder L/H/S | 64118 | 1755 | 5000
500057773 | CLB-MP-SUPP-WC011 -STRSYS-STHMU | Steering HMU | 64118 | 4490 | 5000
500057772 | CLB-MP-SUPP-WC011 -STRSYS-STPMP | Steering Pump | 64118 | 4490 | 5000
500057771 | CLB-MP-SUPP-WC011 -BRKSYS-SLACK-SLACR | Slack Adjustor Rear | 64118 | 1755 | 5000
500057770 | CLB-MP-SUPP-WC011 -BRKSYS-SLACK-SLACF | Slack Adjustor Front | 64118 | 1755 | 5000
500057769 | CLB-MP-SUPP-WC011 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H/Rear | 64118 | 1755 | 5000
500057768 | CLB-MP-SUPP-WC011 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H/Rear | 64118 | 1755 | 5000
500057767 | CLB-MP-SUPP-WC011 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 64118 | 1755 | 5000
500057766 | CLB-MP-SUPP-WC011 -BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom | 64118 | 1755 | 5000
500057765 | CLB-MP-SUPP-WC011 -BRKSYS-BROCO-BROCT | Brake Oil Cooler Rear Top | 64118 | 1755 | 5000
500057764 | CLB-MP-SUPP-WC011 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 64118 | 10138 | 5000
500057763 | CLB-MP-SUPP-WC011 -BRKSYS-MERTR | Mechanical Retarder | 64118 | 64118 | 5000
500057762 | CLB-MP-SUPP-WC011 -BRKSYS-BRVTR | Brake Treadle Valve | 64118 | 64118 | 5000
500057761 | CLB-MP-SUPP-WC011 -BRKSYS-BRVLV | Brake Valve | 64118 | 1755 | 5000
500057760 | CLB-MP-SUPP-WC011 -HYDSYS-HOPMP | Hoist & Rear Brake Cooling Pump | 64118 | 624 | 5000
500057759 | CLB-MP-SUPP-WC011 -BRKSYS-BACCM | Brake Accumulator | 64118 | 5623 | 5000
500057758 | CLB-MP-SUPP-WC011 -BRKSYS-SRVBK-SVBRR | Service Brake R/H/Rear | 64118 | 64118 | 5000
500057757 | CLB-MP-SUPP-WC011 -BRKSYS-SRVBK-SVBLR | Service Brake L/H/Rear | 64118 | 64118 | 5000
500057756 | CLB-MP-SUPP-WC011 -BRKSYS-SRVBK-SVBRF | Service Brake R/H/Front | 64118 | 64118 | 5000
500057755 | CLB-MP-SUPP-WC011 -BRKSYS-SRVBK-SVBLF | Service Brake L/H/Front | 64118 | 64118 | 5000
500057754 | CLB-MP-SUPP-WC011 -FDRSYS-AXLEC-HYPUM | Rear Axle Oil Pump | 64118 | 1755 | 5000
500057753 | CLB-MP-SUPP-WC011 -FDRSYS-AXLEC-MTFAN | Rear Axle Cooling Fan Motor | 64118 | 1755 | 5000
500057752 | CLB-MP-SUPP-WC011 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 64118 | 13726 | 5000
500057751 | CLB-MP-SUPP-WC011 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 64118 | 1755 | 5000
500057750 | CLB-MP-SUPP-WC011 -FDRSYS-DIFFL | Differential | 64118 | 1755 | 5000
500057749 | CLB-MP-SUPP-WC011 -FDRSYS-DRSHT | Transmission Drive Shaft | 64118 | 1755 | 5000
500057748 | CLB-MP-SUPP-WC011 -TRNSYS-TROLC | Transmission Oil Cooler | 64118 | 1755 | 5000
500057747 | CLB-MP-SUPP-WC011 -TRNSYS-TRPMP-TCCPP | TC/Park Brake/Scavenge Pump | 64118 | 1755 | 5000
500057746 | CLB-MP-SUPP-WC011 -TRNSYS-TRPMP-TMCPP | Transmission Pump | 64118 | 1755 | 5000
500057745 | CLB-MP-SUPP-WC011 -TRNSYS-TRANS | Transmission | 64118 | 1755 | 5000
500057744 | CLB-MP-SUPP-WC011 -TRNSYS-TRQUE | Torque Converter | 64118 | 1755 | 5000
500057743 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR-DRSHT | Drive Shaft, Engine Pump Drive | 64118 | 1755 | 5000
500057742 | CLB-MP-SUPP-WC011 -ENGINE-PMPDR | Engine Pump Drive | 64118 | 4490 | 5000
500057741 | CLB-MP-SUPP-WC011 -ENGINE-COSYS-RADTR | Engine Radiator | 64118 | 1755 | 5000
500057740 | CLB-MP-SUPP-WC011 -ENGINE-LUBSY-ENOLC | Engine Oil Cooler | 64118 | 1755 | 5000
500057739 | CLB-MP-SUPP-WC011 -ENGINE-LUBSY-PREPP | Pre-Lubrication Pump | 64118 | 1755 | 5000
500057738 | CLB-MP-SUPP-WC011 -ENGINE-COMPR | Air Compressor | 64118 | 1755 | 5000
500057737 | CLB-MP-SUPP-WC011 -ENGINE-LUBSY-OILPP | Engine Oil Pump | 64118 | 1755 | 5000
500057736 | CLB-MP-SUPP-WC011 -ENGINE-INTEX-AFTER | Aftercooler | 64118 | 1755 | 5000
500057735 | CLB-MP-SUPP-WC011 -ELCTLV-CHARG-ALTER | Alternator 24V | 64118 | 1755 | 5000
500057734 | CLB-MP-SUPP-WC011 -ENGINE-COSYS-COFAN | Fan Drive, Cooling System | 64118 | 64118 | 5000
500057733 | CLB-MP-SUPP-WC011 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 64118 | 1755 | 5000
500057732 | CLB-MP-SUPP-WC011 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 64118 | 1755 | 5000
500057731 | CLB-MP-SUPP-WC011 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 64118 | 1755 | 5000
500057730 | CLB-MP-SUPP-WC011 -ENGINE-COSYS-THERM | Thermostats/Regulators | 64118 | 1755 | 5000
500057729 | CLB-MP-SUPP-WC011 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 64118 | 1755 | 5000
500057728 | CLB-MP-SUPP-WC011 -ENGINE-COSYS-WTRPP | Water Pump Engine | 64118 | 1755 | 5000
500057727 | CLB-MP-SUPP-WC011 -ENGINE-INTEX-TBORR | Turbocharger R/H/Rear | 64118 | 1755 | 5000
500057726 | CLB-MP-SUPP-WC011 -ENGINE-INTEX-TBORF | Turbocharger R/H/Front | 64118 | 1755 | 5000
500057725 | CLB-MP-SUPP-WC011 -ENGINE-INTEX-TBOLR | Turbocharger L/H/Rear | 64118 | 1755 | 5000
500057724 | CLB-MP-SUPP-WC011 -ENGINE-INTEX-TBOLF | Turbocharger L/H/Front | 64118 | 1755 | 5000
500057723 | CLB-MP-SUPP-WC011 -ENGINE | Engine Assembly, Caterpillar 3512 | 64118 | 1755 | 5000
500057181 | CLB-MP-SUPP-WC011 | WC011 Lubrication & Mechanical Services | 64118 | 64118 | 5000
500057180 | CLB-MP-SUPP-WC011 | Caterpillar 785D Water Truck, WC011 | 64118 | 64118 | 5000
500161610 | CLB-MP-SUPP-SV4105-BRKSYS-SLACK-SLARR | Brake Slack Adjuster Rear Right | 8917 | 8917 | 2500
500161609 | CLB-MP-SUPP-SV4105-BRKSYS-SLACK-SLARL | Brake Slack Adjuster Rear Left | 8917 | 8917 | 2500
500161608 | CLB-MP-SUPP-SV4105-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 8917 | 8917 | 2500
500160203 | CLB-MP-SUPP-SV4105-BRKSYS-BRACC-BAPKB | Accumulator Park Brake | 8873 | 8873 | 2500
500160202 | CLB-MP-SUPP-SV4105-BRKSYS-BRACC-BACSV | Accumulator Service Brake | 8873 | 8873 | 2500
500132375 | CLB-MP-SUPP-SV4105-STRUCT-SVTNK | SV4105 Service Tank Module | 8917 | 8917 | 2500
500116686 | CLB-MP-SUPP-SV4105-TRNSYS-TRQUE | SV4105 Torque Converter | 8917 | 8917 | 2500
500116685 | CLB-MP-SUPP-SV4105-TRNSYS-TRPMP-TMCPP | SV4105 Pump Charge Transmission | 8917 | 8917 | 2500
500116684 | CLB-MP-SUPP-SV4105-TRNSYS-TRPMP-TCCPP | SV4105 Pump Charge Torque Converter | 8917 | 8917 | 2500
500116683 | CLB-MP-SUPP-SV4105-TRNSYS-TRPMP | SV4105 Pump Transmission | 8917 | 8917 | 2500
500116682 | CLB-MP-SUPP-SV4105-TRNSYS-TROLC | SV4105 Oil Cooler Transmission | 8917 | 8917 | 2500
500116681 | CLB-MP-SUPP-SV4105-TRNSYS-TRANS | SV4105 Transmission | 8917 | 8917 | 2500
500116680 | CLB-MP-SUPP-SV4105-STRUCT-SVTNK-COMPR | SV4105 Auxiliary Compressor | 8917 | 8917 | 2500
500116679 | CLB-MP-SUPP-SV4105-STRUCT-SUSPN-SCYRR | SV4105 Cylinder Suspension RH Rear | 8917 | 8917 | 2500
500116678 | CLB-MP-SUPP-SV4105-STRUCT-SUSPN-SCYRF | SV4105 Cylinder Suspension RH Front | 8917 | 8917 | 2500
500116677 | CLB-MP-SUPP-SV4105-STRUCT-SUSPN-SCYLR | SV4105 Cylinder Suspension LH Rear | 8917 | 8917 | 2500
500116676 | CLB-MP-SUPP-SV4105-STRUCT-SUSPN-SCYLF | SV4105 Cylinder Suspension LH Front | 8917 | 8917 | 2500
500116675 | CLB-MP-SUPP-SV4105-STRUCT-CHASS-TAGLK | SV4105 Tag Link | 8917 | 8917 | 2500
500116674 | CLB-MP-SUPP-SV4105-STRUCT-CHASS-AFRME | SV4105 A Frame | 8917 | 8917 | 2500
500116673 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-SEATS | SV4105 Operators Seat | 8917 | 775 | 2500
500116672 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-SBELT | SV4105 Seat Belt | 8917 | 8917 | 2500
500116671 | CLB-MP-SUPP-SV4105-STRUCT-CABIN-AIRCN | SV4105 Air Con System Refurb | 8917 | 5023 | 2500
500116670 | CLB-MP-SUPP-SV4105-STRUCT-AXLES-HUBRH | SV4105 Hub and Spindle RH | 8917 | 8917 | 2500
500116669 | CLB-MP-SUPP-SV4105-STRUCT-AXLES-HUBLH | SV4105 Hub and Spindle LH | 8917 | 8917 | 2500
500116668 | CLB-MP-SUPP-SV4105-STRSYS-STVLV | SV4105 Valve Steering | 8917 | 8917 | 2500
500116667 | CLB-MP-SUPP-SV4105-STRSYS-STRCY-STCYR | SV4105 Cylinder Steering RH | 8917 | 8917 | 2500
500116666 | CLB-MP-SUPP-SV4105-STRSYS-STRCY-STCYL | SV4105 Cylinder Steering LH | 8917 | 8917 | 2500
500116665 | CLB-MP-SUPP-SV4105-STRSYS-STPMP | SV4105 Pump Steering | 8917 | 8917 | 2500
500116664 | CLB-MP-SUPP-SV4105-STRSYS-STLTR | SV4105 Steering Linkages | 8917 | 8917 | 2500
500116663 | CLB-MP-SUPP-SV4105-STRSYS-STHMU | SV4105 Steering HMU | 8917 | 8917 | 2500
500116662 | CLB-MP-SUPP-SV4105-STRSYS-STHLF | SV4105 Steering Hoses Lines | 8917 | 8917 | 2500
500116661 | CLB-MP-SUPP-SV4105-STRSYS-STEMG-SESPP | SV4105 Pump Electric Secondary Steering | 8917 | 8917 | 2500
500116660 | CLB-MP-SUPP-SV4105-HYDSYS-HOVLV | SV4105 Valve Hoist | 8917 | 8917 | 2500
500116659 | CLB-MP-SUPP-SV4105-HYDSYS-HOPMP | SV4105 Pump Hoist | 8917 | 8917 | 2500
500116658 | CLB-MP-SUPP-SV4105-HYDSYS-HOCYL-HCYLR | SV4105 Cylinder Hoist RH | 8917 | 8917 | 2500
500116657 | CLB-MP-SUPP-SV4105-HYDSYS-HOCYL-HCYLL | SV4105 Cylinder Hoist LH | 8917 | 8917 | 2500
500116656 | CLB-MP-SUPP-SV4105-HYDSYS-HDTNK | SV4105 Tank Hydraulic | 8917 | 8917 | 2500
500116655 | CLB-MP-SUPP-SV4105-HYDSYS-HDOCO | SV4105 Oil Cooler Hydraulic | 8917 | 8917 | 2500
500116654 | CLB-MP-SUPP-SV4105-HYDSYS-HDHLF | SV4105 Pump Hoist Lines | 8917 | 8917 | 2500
500116653 | CLB-MP-SUPP-SV4105-GRSYST-ALBPP | SV4105 Auto Lube Pump | 8917 | 8917 | 2500
500116652 | CLB-MP-SUPP-SV4105-FDRSYS-FDRVE-FDRRH | SV4105 Final Drive RH | 8917 | 8917 | 2500
500116651 | CLB-MP-SUPP-SV4105-FDRSYS-FDRVE-FDRLH | SV4105 Final Drive LH | 8917 | 8917 | 2500
500116650 | CLB-MP-SUPP-SV4105-FDRSYS-DRSHT | SV4105 Drive Shaft | 8917 | 8917 | 2500
500116649 | CLB-MP-SUPP-SV4105-FDRSYS-DRLAX-AXLRH | SV4105 Drive Line Axle RH | 8917 | 8917 | 2500
500116648 | CLB-MP-SUPP-SV4105-FDRSYS-DRLAX-AXLLH | SV4105 Drive Line Axle LH | 8917 | 8917 | 2500
500116647 | CLB-MP-SUPP-SV4105-FDRSYS-DIFFL | SV4105 Differential | 8917 | 8917 | 2500
500116646 | CLB-MP-SUPP-SV4105-ENGINE-LUBSY-PREPP | SV4105 Engine Pre Lube | 8917 | 8917 | 2500
500116645 | CLB-MP-SUPP-SV4105-ENGINE-LUBSY-OILPP | SV4105 Oil Pump Engine | 8917 | 8917 | 2500
500116644 | CLB-MP-SUPP-SV4105-ENGINE-LUBSY-ENOLC | SV4105 Oil Cooler Engine | 8917 | 8917 | 2500
500116643 | CLB-MP-SUPP-SV4105-ENGINE-INTEX-TBORH | SV4105 Turbocharger RH | 8917 | 8917 | 2500
500116642 | CLB-MP-SUPP-SV4105-ENGINE-INTEX-TBOLH | SV4105 Turbocharger LH | 8917 | 8917 | 2500
500116641 | CLB-MP-SUPP-SV4105-ENGINE-INTEX-AFTER | SV4105 Aftercooler | 8917 | 8917 | 2500
500116640 | CLB-MP-SUPP-SV4105-ENGINE-FUSYS-FULTP | SV4105 Fuel Transfer Pump | 8917 | 8917 | 2500
500116639 | CLB-MP-SUPP-SV4105-ENGINE-FUSYS-FULPP | SV4105 Fuel Priming Pump | 8917 | 8917 | 2500
500116638 | CLB-MP-SUPP-SV4105-ENGINE-FUSYS-FUINJ | SV4105 Fuel Injectors | 8917 | 8917 | 2500
500116637 | CLB-MP-SUPP-SV4105-ENGINE-COSYS-WTRPP | SV4105 Water Pump Engine | 8917 | 8917 | 2500
500116636 | CLB-MP-SUPP-SV4105-ENGINE-COSYS-THERM | SV4105 Thermostats/Regulators | 8917 | 8917 | 2500
500116635 | CLB-MP-SUPP-SV4105-ENGINE-COSYS-RADTR | SV4105 Radiator Engine | 8917 | 8917 | 2500
500116634 | CLB-MP-SUPP-SV4105-ENGINE-COSYS-COFAN | SV4105 Fan Cooling System | 8917 | 8917 | 2500
500116633 | CLB-MP-SUPP-SV4105-ENGINE | SV4105 Engine Assembly Caterpillar C32 | 8917 | 8917 | 2500
500116632 | CLB-MP-SUPP-SV4105-ELCTLV-START-STMUP | SV4105 Starter Motor Upper | 8917 | 8917 | 2500
500116631 | CLB-MP-SUPP-SV4105-ELCTLV-START-STMLO | SV4105 Starter Motor Lower | 8917 | 8917 | 2500
500116630 | CLB-MP-SUPP-SV4105-ELCTLV-CHARG-ALTER | SV4105 Alternator 24V | 8917 | 762 | 2500
500116629 | CLB-MP-SUPP-SV4105-BRKSYS-SRVBK-SVBRR | SV4105 Service Brake RH Rear Ext Life | 8917 | 8917 | 2500
500116628 | CLB-MP-SUPP-SV4105-BRKSYS-SRVBK-SVBRF | SV4105 Service Brake RH Front Ext Life | 8917 | 8917 | 2500
500116627 | CLB-MP-SUPP-SV4105-BRKSYS-SRVBK-SVBLR | SV4105 Service Brake LH Rear Ext Life | 8917 | 8917 | 2500
500116626 | CLB-MP-SUPP-SV4105-BRKSYS-SRVBK-SVBLF | SV4105 Service Brake LH Front Ext Life | 8917 | 8917 | 2500
500116625 | CLB-MP-SUPP-SV4105-BRKSYS-HYFPP | SV4105 Pump Brake Cooling | 8917 | 8917 | 2500
500116624 | CLB-MP-SUPP-SV4105-BRKSYS-BRVTR | SV4105 Valve Brake Treadle | 8917 | 8917 | 2500
500116623 | CLB-MP-SUPP-SV4105-BRKSYS-BRVLV | SV4105 Valve Brake | 8917 | 8917 | 2500
500116622 | CLB-MP-SUPP-SV4105-BRKSYS-BRPMP | SV4105 Pump Brake | 8917 | 8917 | 2500
500116621 | CLB-MP-SUPP-SV4105-BRKSYS-BROCO | SV4105 Brake Oil Cooler | 8917 | 8917 | 2500
500116610 | CLB-MP-SUPP-SV4105-BRKSYS-BRACC | SV4105 Accumulator Brake | 8917 | 8917 | 2500
500116609 | CLB-MP-SUPP-SV4105 | Caterpillar 777G Service Truck SV4105 | 8917 | 8917 | 2500
500160224 | CLB-MP-SUPP-SV021 -BRKSYS-BRACC-BACCR | Accumulator Brake Rear | 54025 | 54025 | 3300
500160223 | CLB-MP-SUPP-SV021 -BRKSYS-BRACC-BACCM | Accumulator Brake Middle | 54025 | 54025 | 3300
500160222 | CLB-MP-SUPP-SV021 -BRKSYS-BRACC-BACCF | Accumulator Brake Front | 54025 | 54025 | 3300
500132370 | CLB-MP-SUPP-SV021 -STRUCT-SVTNK | SV021 Service Tank Module | 54098 | 54098 | 3300
500081531 | CLB-MP-SUPP-SV021 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 54098 | 54098 | 3300
500081506 | CLB-MP-SUPP-SV021 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 54098 | 54098 | 3300
500053811 | CLB-MP-SUPP-SV021 -MANGMT-UMMMC | Mine Monitoring and Control | 54098 | 54098 | 3300
500053810 | CLB-MP-SUPP-SV021 -MANGMT-UMTRN | Power Train Management System | 54098 | 54098 | 3300
500053809 | CLB-MP-SUPP-SV021 -MANGMT-UMENG | Engine Management System | 54098 | 54098 | 3300
500053808 | CLB-MP-SUPP-SV021 -FRSUPP-FSALM | Fire System Alarm | 54098 | 54098 | 3300
500053807 | CLB-MP-SUPP-SV021 -FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 54098 | 54098 | 3300
500053806 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 54098 | 9678 | 3300
500053805 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 54098 | 8323 | 3300
500053804 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 54098 | 1010 | 3300
500053803 | CLB-MP-SUPP-SV021 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 54098 | 19010 | 3300
500053802 | CLB-MP-SUPP-SV021 -STRUCT-SVTNK-COMPR | Auxillary Compressor | 54098 | 54098 | 3300
500053801 | CLB-MP-SUPP-SV021 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 54098 | 1010 | 3300
500053800 | CLB-MP-SUPP-SV021 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 54098 | 1010 | 3300
500053799 | CLB-MP-SUPP-SV021 -STRUCT-CHASS-TAGLK | Tag Link | 54098 | 16520 | 3300
500053798 | CLB-MP-SUPP-SV021 -STRUCT-CHASS-AFRME | A Frame | 54098 | 16520 | 3300
500053797 | CLB-MP-SUPP-SV021 -STRUCT-CHASS | Chassis | 54098 | 54098 | 3300
500053796 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-SBELT | Seat Belt | 54098 | 54098 | 3300
500053795 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-SEATS | Operators Seat | 54098 | 5038 | 3300
500053794 | CLB-MP-SUPP-SV021 -STRUCT-CABIN-AIRCN | Air Conditioning System | 54098 | 5 | 3300
500053793 | CLB-MP-SUPP-SV021 -GRSYST-ALCON | Auto Lube Controller | 54098 | 54098 | 3300
500053792 | CLB-MP-SUPP-SV021 -GRSYST-ALBPP | Auto Lube Pump | 54098 | 4488 | 3300
500053791 | CLB-MP-SUPP-SV021 -GRSYST-GRINJ | Auto Lube Injectors | 54098 | 54098 | 3300
500053790 | CLB-MP-SUPP-SV021 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 54098 | 16520 | 3300
500053789 | CLB-MP-SUPP-SV021 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 54098 | 16520 | 3300
500053788 | CLB-MP-SUPP-SV021 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 54098 | 16520 | 3300
500053787 | CLB-MP-SUPP-SV021 -HYDSYS-HOVLV | Valve Hoist | 54098 | 54098 | 3300
500053786 | CLB-MP-SUPP-SV021 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 54098 | 54098 | 3300
500053785 | CLB-MP-SUPP-SV021 -HYDSYS-HOPMP | Pump Hoist | 54098 | 5 | 3300
500053784 | CLB-MP-SUPP-SV021 -STRSYS-STHLF | Steering System Hoses Lines and Fittings | 54098 | 16520 | 3300
500053783 | CLB-MP-SUPP-SV021 -STRSYS-STEMG-SESPP | Pump Electric Secondary Steering | 54098 | 6110 | 3300
500053782 | CLB-MP-SUPP-SV021 -STRSYS-STLTR | Steering Linkages and Tie Rods | 54098 | 8323 | 3300
500053781 | CLB-MP-SUPP-SV021 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 54098 | 4488 | 3300
500053780 | CLB-MP-SUPP-SV021 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 54098 | 4488 | 3300
500053779 | CLB-MP-SUPP-SV021 -STRSYS-STVLV | Valve Steering | 54098 | 20847 | 3300
500053778 | CLB-MP-SUPP-SV021 -STRSYS-STHMU | Steering HMU | 54098 | 16520 | 3300
500053777 | CLB-MP-SUPP-SV021 -STRSYS-STPMP | Pump Steering | 54098 | 5 | 3300
500053776 | CLB-MP-SUPP-SV021 -BRKSYS-BROCO | Brake Oil Cooler | 54098 | 37354 | 3300
500053775 | CLB-MP-SUPP-SV021 -BRKSYS-MERTR | Mechanical Retarder | 54098 | 54098 | 3300
500053774 | CLB-MP-SUPP-SV021 -BRKSYS-BRVTR | Valve Brake Treadle | 54098 | 54098 | 3300
500053773 | CLB-MP-SUPP-SV021 -BRKSYS-BRVLV | Valve Brake | 54098 | 20842 | 3300
500053772 | CLB-MP-SUPP-SV021 -BRKSYS-HYFPP | Pump Brake Cooling | 54098 | 37354 | 3300
500053771 | CLB-MP-SUPP-SV021 -BRKSYS-BRPMP | Pump Brake | 54098 | 37354 | 3300
500053770 | CLB-MP-SUPP-SV021 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 54098 | 54098 | 3300
500053769 | CLB-MP-SUPP-SV021 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 54098 | 54098 | 3300
500053768 | CLB-MP-SUPP-SV021 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 54098 | 37354 | 3300
500053767 | CLB-MP-SUPP-SV021 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 54098 | 37354 | 3300
500053766 | CLB-MP-SUPP-SV021 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 54098 | 54098 | 3300
500053765 | CLB-MP-SUPP-SV021 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 54098 | 54098 | 3300
500053764 | CLB-MP-SUPP-SV021 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 54098 | 54098 | 3300
500053763 | CLB-MP-SUPP-SV021 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 54098 | 54098 | 3300
500053762 | CLB-MP-SUPP-SV021 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 54098 | 54098 | 3300
500053761 | CLB-MP-SUPP-SV021 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 54098 | 54098 | 3300
500053760 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 54098 | 16520 | 3300
500053759 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 54098 | 16520 | 3300
500053758 | CLB-MP-SUPP-SV021 -FDRSYS-FDRVE | Final Drives | 54098 | 54098 | 3300
500053757 | CLB-MP-SUPP-SV021 -FDRSYS-DIFFL | Differential | 54098 | 16520 | 3300
500053756 | CLB-MP-SUPP-SV021 -FDRSYS-DRSHT | Drive Shaft | 54098 | 16520 | 3300
500053755 | CLB-MP-SUPP-SV021 -TRNSYS-TROLC | Oil Cooler Transmission | 54098 | 7651 | 3300
500053754 | CLB-MP-SUPP-SV021 -TRNSYS-TRPMP-TCCPP | Pump Charge Torque Converter | 54098 | 37354 | 3300
500053753 | CLB-MP-SUPP-SV021 -TRNSYS-TRPMP-TMCPP | Pump Charge Transmission | 54098 | 37354 | 3300
500053752 | CLB-MP-SUPP-SV021 -TRNSYS-TRPMP | Pumps Transmission | 54098 | 7651 | 3300
500053751 | CLB-MP-SUPP-SV021 -TRNSYS-TRANS | Transmission | 54098 | 7651 | 3300
500053750 | CLB-MP-SUPP-SV021 -TRNSYS-TRQUE | Torque Converter | 54098 | 16520 | 3300
500053749 | CLB-MP-SUPP-SV021 -ELCTLV-START-STMLO | Starter Motor Lower | 54098 | 5 | 3300
500053748 | CLB-MP-SUPP-SV021 -ELCTLV-START-STMUP | Starter Motor Upper | 54098 | 5 | 3300
500053747 | CLB-MP-SUPP-SV021 -ELCTLV-CHARG-BATTY | Batteries | 54098 | 9242 | 3300
500053746 | CLB-MP-SUPP-SV021 -ELCTLV-CHARG-ALTER | Alternator 24V | 54098 | 5 | 3300
500053745 | CLB-MP-SUPP-SV021 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 54098 | 5 | 3300
500053744 | CLB-MP-SUPP-SV021 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 54098 | 5 | 3300
500053743 | CLB-MP-SUPP-SV021 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 54098 | 5 | 3300
500053742 | CLB-MP-SUPP-SV021 -ENGINE-INTEX-EXHST | Exhaust System | 54098 | 54098 | 3300
500053741 | CLB-MP-SUPP-SV021 -ENGINE-INTEX-AFTER | Aftercooler | 54098 | 16520 | 3300
500053740 | CLB-MP-SUPP-SV021 -ENGINE-INTEX-TBORH | Turbocharger R/H | 54098 | 5 | 3300
500053739 | CLB-MP-SUPP-SV021 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 54098 | 5 | 3300
500053738 | CLB-MP-SUPP-SV021 -ENGINE-COSYS-THERM | Thermostats/Regulators | 54098 | 5 | 3300
500053737 | CLB-MP-SUPP-SV021 -ENGINE-COSYS-RADTR | Radiator Engine | 54098 | 16520 | 3300
500053736 | CLB-MP-SUPP-SV021 -ENGINE-COSYS-WTRPP | Water Pump Engine | 54098 | 5 | 3300
500053735 | CLB-MP-SUPP-SV021 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 54098 | 5 | 3300
500053734 | CLB-MP-SUPP-SV021 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 54098 | 5 | 3300
500053733 | CLB-MP-SUPP-SV021 -ENGINE-LUBSY-PREPP | Engine Pre Lube | 54098 | 16520 | 3300
500053732 | CLB-MP-SUPP-SV021 -ENGINE-LUBSY | Engine Lubrication System | 54098 | 54098 | 3300
500053730 | CLB-MP-SUPP-SV021 -ENGINE | Engine Assembly, Caterpillar C32 | 54098 | 5 | 3300
500053729 | CLB-MP-SUPP-SV021 | SV021 Lubrication & Mechanical Services | 54098 | 54098 | 3300
500053728 | CLB-MP-SUPP-SV021 | Caterpillar 777F Service Truck SV021 | 54098 | 54098 | 3300
500160221 | CLB-MP-SUPP-SV020 -BRKSYS-BRACC-BACCR | Accumulator Brake Rear | 43850 | 43850 | 3300
500160220 | CLB-MP-SUPP-SV020 -BRKSYS-BRACC-BACCM | Accumulator Brake Middle | 43850 | 43850 | 3300
500160219 | CLB-MP-SUPP-SV020 -BRKSYS-BRACC-BACCF | Accumulator Brake Front | 43850 | 43850 | 3300
500132369 | CLB-MP-SUPP-SV020 -STRUCT-SVTNK | SV020 Service Tank Module | 44025 | 44025 | 3300
500081530 | CLB-MP-SUPP-SV020 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 44025 | 44025 | 3300
500081505 | CLB-MP-SUPP-SV020 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 44025 | 44025 | 3300
500053727 | CLB-MP-SUPP-SV020 -MANGMT-UMMMC | Mine Monitoring and Control | 44025 | 44025 | 3300
500053726 | CLB-MP-SUPP-SV020 -MANGMT-UMTRN | Power Train Management System | 44025 | 44025 | 3300
500053725 | CLB-MP-SUPP-SV020 -MANGMT-UMENG | Engine Management System | 44025 | 44025 | 3300
500053724 | CLB-MP-SUPP-SV020 -FRSUPP-FSALM | Fire System Alarm | 44025 | 44025 | 3300
500053723 | CLB-MP-SUPP-SV020 -FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 44025 | 44025 | 3300
500053722 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 44025 | 8900 | 3300
500053721 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 44025 | 8900 | 3300
500053720 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 44025 | 8900 | 3300
500053719 | CLB-MP-SUPP-SV020 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 44025 | 5466 | 3300
500053718 | CLB-MP-SUPP-SV020 -STRUCT-SVTNK-COMPR | Auxillary Compressor | 44025 | 44025 | 3300
500053717 | CLB-MP-SUPP-SV020 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 44025 | 16743 | 3300
500053716 | CLB-MP-SUPP-SV020 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 44025 | 16743 | 3300
500053715 | CLB-MP-SUPP-SV020 -STRUCT-CHASS-TAGLK | Tag Link | 44025 | 24114 | 3300
500053714 | CLB-MP-SUPP-SV020 -STRUCT-CHASS-AFRME | A Frame | 44025 | 25732 | 3300
500053713 | CLB-MP-SUPP-SV020 -STRUCT-CHASS | Chassis | 44025 | 44025 | 3300
500053712 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-SBELT | Seat Belt | 44025 | 44025 | 3300
500053711 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-SEATS | Operators Seat | 44025 | 3632 | 3300
500053710 | CLB-MP-SUPP-SV020 -STRUCT-CABIN-AIRCN | Air Conditioning System | 44025 | 4749 | 3300
500053709 | CLB-MP-SUPP-SV020 -GRSYST-ALCON | Auto Lube Controller | 44025 | 44025 | 3300
500053708 | CLB-MP-SUPP-SV020 -GRSYST-ALBPP | Auto Lube Pump | 44025 | 4749 | 3300
500053707 | CLB-MP-SUPP-SV020 -GRSYST-GRINJ | Auto Lube Injectors | 44025 | 44025 | 3300
500053706 | CLB-MP-SUPP-SV020 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 44025 | 8900 | 3300
500053705 | CLB-MP-SUPP-SV020 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 44025 | 8900 | 3300
500053704 | CLB-MP-SUPP-SV020 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 44025 | 8900 | 3300
500053703 | CLB-MP-SUPP-SV020 -HYDSYS-HOVLV | Valve Hoist | 44025 | 44025 | 3300
500053702 | CLB-MP-SUPP-SV020 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 44025 | 25732 | 3300
500053701 | CLB-MP-SUPP-SV020 -HYDSYS-HOPMP | Pump Hoist | 44025 | 3632 | 3300
500053700 | CLB-MP-SUPP-SV020 -STRSYS-STHLF | Steering System Hoses Lines and Fittings | 44025 | 8900 | 3300
500053699 | CLB-MP-SUPP-SV020 -STRSYS-STEMG-SESPP | Pump Electric Secondary Steering | 44025 | 16743 | 3300
500053698 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 44025 | 8900 | 3300
500053697 | CLB-MP-SUPP-SV020 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 44025 | 8900 | 3300
500053696 | CLB-MP-SUPP-SV020 -STRSYS-STVLV | Valve Steering | 44025 | 16743 | 3300
500053695 | CLB-MP-SUPP-SV020 -STRSYS-STHMU | Steering HMU | 44025 | 8900 | 3300
500053694 | CLB-MP-SUPP-SV020 -STRSYS-STPMP | Pump Steering | 44025 | 15884 | 3300
500053693 | CLB-MP-SUPP-SV020 -BRKSYS-BROCO | Brake Oil Cooler | 44025 | 15729 | 3300
500053692 | CLB-MP-SUPP-SV020 -BRKSYS-MERTR | Mechanical Retarder | 44025 | 44025 | 3300
500053691 | CLB-MP-SUPP-SV020 -BRKSYS-BRVTR | Valve Brake Treadle | 44025 | 44025 | 3300
500053690 | CLB-MP-SUPP-SV020 -BRKSYS-BRVLV | Valve Brake | 44025 | 16326 | 3300
500053689 | CLB-MP-SUPP-SV020 -BRKSYS-HYFPP | Pump Brake Cooling | 44025 | 32030 | 3300
500053688 | CLB-MP-SUPP-SV020 -BRKSYS-BRPMP | Pump Brake | 44025 | 44025 | 3300
500053687 | CLB-MP-SUPP-SV020 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 44025 | 29521 | 3300
500053686 | CLB-MP-SUPP-SV020 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 44025 | 29521 | 3300
500053685 | CLB-MP-SUPP-SV020 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 44025 | 29984 | 3300
500053684 | CLB-MP-SUPP-SV020 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 44025 | 29984 | 3300
500053683 | CLB-MP-SUPP-SV020 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 44025 | 44025 | 3300
500053682 | CLB-MP-SUPP-SV020 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 44025 | 44025 | 3300
500053681 | CLB-MP-SUPP-SV020 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 44025 | 44025 | 3300
500053680 | CLB-MP-SUPP-SV020 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 44025 | 44025 | 3300
500053679 | CLB-MP-SUPP-SV020 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 44025 | 44025 | 3300
500053678 | CLB-MP-SUPP-SV020 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 44025 | 44025 | 3300
500053677 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 44025 | 10957 | 3300
500053676 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 44025 | 10957 | 3300
500053675 | CLB-MP-SUPP-SV020 -FDRSYS-FDRVE | Final Drives | 44025 | 44025 | 3300
500053674 | CLB-MP-SUPP-SV020 -FDRSYS-DIFFL | Differential | 44025 | 8900 | 3300
500053673 | CLB-MP-SUPP-SV020 -FDRSYS-DRSHT | Drive Shaft | 44025 | 8900 | 3300
500053672 | CLB-MP-SUPP-SV020 -TRNSYS-TROLC | Oil Cooler Transmission | 44025 | 17710 | 3300
500053671 | CLB-MP-SUPP-SV020 -TRNSYS-TRPMP-TCCPP | Pump Charge Torque Converter | 44025 | 25732 | 3300
500053670 | CLB-MP-SUPP-SV020 -TRNSYS-TRPMP-TMCPP | Pump Charge Transmission | 44025 | 25732 | 3300
500053669 | CLB-MP-SUPP-SV020 -TRNSYS-TRPMP | Pumps Transmission | 44025 | 1182 | 3300
500053668 | CLB-MP-SUPP-SV020 -TRNSYS-TRANS | Transmission | 44025 | 17710 | 3300
500053667 | CLB-MP-SUPP-SV020 -TRNSYS-TRQUE | Torque Converter | 44025 | 12481 | 3300
500053666 | CLB-MP-SUPP-SV020 -ELCTLV-START-STMLO | Starter Motor Lower | 44025 | 8900 | 3300
500053665 | CLB-MP-SUPP-SV020 -ELCTLV-START-STMUP | Starter Motor Upper | 44025 | 8900 | 3300
500053664 | CLB-MP-SUPP-SV020 -ELCTLV-CHARG-BATTY | Batteries | 44025 | 25732 | 3300
500053663 | CLB-MP-SUPP-SV020 -ELCTLV-CHARG-ALTER | Alternator 24V | 44025 | 8900 | 3300
500053662 | CLB-MP-SUPP-SV020 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 44025 | 8900 | 3300
500053661 | CLB-MP-SUPP-SV020 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 44025 | 8900 | 3300
500053660 | CLB-MP-SUPP-SV020 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 44025 | 8900 | 3300
500053659 | CLB-MP-SUPP-SV020 -ENGINE-INTEX-EXHST | Exhaust System | 44025 | 44025 | 3300
500053658 | CLB-MP-SUPP-SV020 -ENGINE-INTEX-AFTER | Aftercooler | 44025 | 8900 | 3300
500053657 | CLB-MP-SUPP-SV020 -ENGINE-INTEX-TBORH | Turbocharger R/H | 44025 | 8900 | 3300
500053656 | CLB-MP-SUPP-SV020 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 44025 | 8900 | 3300
500053655 | CLB-MP-SUPP-SV020 -ENGINE-COSYS-THERM | Thermostats/Regulators | 44025 | 8900 | 3300
500053654 | CLB-MP-SUPP-SV020 -ENGINE-COSYS-RADTR | Radiator Engine | 44025 | 8900 | 3300
500053653 | CLB-MP-SUPP-SV020 -ENGINE-COSYS-WTRPP | Water Pump Engine | 44025 | 8900 | 3300
500053652 | CLB-MP-SUPP-SV020 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 44025 | 25732 | 3300
500053651 | CLB-MP-SUPP-SV020 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 44025 | 25732 | 3300
500053650 | CLB-MP-SUPP-SV020 -ENGINE-LUBSY-PREPP | Engine Pre Lube | 44025 | 8900 | 3300
500053649 | CLB-MP-SUPP-SV020 -ENGINE-LUBSY | Engine Lubrication System | 44025 | 44025 | 3300
500053647 | CLB-MP-SUPP-SV020 -ENGINE | Engine Assembly, Caterpillar C32 | 44025 | 8900 | 3300
500053108 | CLB-MP-SUPP-SV020 -STRSYS-STLTR | Steering Linkages and Tie Rods | 44025 | 8900 | 3300
500053107 | CLB-MP-SUPP-SV020 -FRSUPP | Fire Suppression System | 44025 | 44025 | 3300
500053106 | CLB-MP-SUPP-SV020 | SV020 Lubrication/Mechanical Services | 44025 | 44025 | 3300
500042613 | CLB-MP-SUPP-SV020 | Caterpillar 777F Service Truck SV020 | 44025 | 44025 | 3300
500160218 | CLB-MP-SUPP-SV019 -BRKSYS-BRACC-BACCR | Accumulator Brake Rear | 48854 | 48854 | 2500
500160217 | CLB-MP-SUPP-SV019 -BRKSYS-BRACC-BACCM | Accumulator Brake Middle | 48854 | 48854 | 2500
500160216 | CLB-MP-SUPP-SV019 -BRKSYS-BRACC-BACCF | Accumulator Brake Front | 48854 | 48854 | 2500
500132368 | CLB-MP-SUPP-SV019 -STRUCT-SVTNK | SV019 Service Tank Module | 48856 | 48856 | 2500
500081529 | CLB-MP-SUPP-SV019 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 48856 | 48856 | 2500
500081504 | CLB-MP-SUPP-SV019 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 48856 | 48856 | 2500
500053646 | CLB-MP-SUPP-SV019 -MANGMT-UMMMC | Mine Monitoring and Control | 48856 | 48856 | 2500
500053645 | CLB-MP-SUPP-SV019 -MANGMT-UMTRN | Power Train Management System | 48856 | 48856 | 2500
500053644 | CLB-MP-SUPP-SV019 -MANGMT-UMENG | Engine Management System | 48856 | 48856 | 2500
500053643 | CLB-MP-SUPP-SV019 -FRSUPP-FSALM | Fire System Alarm | 48856 | 48856 | 2500
500053642 | CLB-MP-SUPP-SV019 -FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 48856 | 48856 | 2500
500053641 | CLB-MP-SUPP-SV019 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 48856 | 5811 | 2500
500053640 | CLB-MP-SUPP-SV019 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 48856 | 948 | 2500
500053639 | CLB-MP-SUPP-SV019 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 48856 | 11163 | 2500
500053638 | CLB-MP-SUPP-SV019 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 48856 | 3403 | 2500
500053637 | CLB-MP-SUPP-SV019 -STRUCT-SVTNK-COMPR | Auxillary Compressor | 48856 | 48856 | 2500
500053636 | CLB-MP-SUPP-SV019 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 48856 | 16821 | 2500
500053635 | CLB-MP-SUPP-SV019 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 48856 | 16821 | 2500
500053634 | CLB-MP-SUPP-SV019 -STRUCT-CHASS-TAGLK | Tag Link | 48856 | 20187 | 2500
500053633 | CLB-MP-SUPP-SV019 -STRUCT-CHASS-AFRME | A Frame | 48856 | 11163 | 2500
500053632 | CLB-MP-SUPP-SV019 -STRUCT-CHASS | Chassis | 48856 | 48856 | 2500
500053631 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-SBELT | Seat Belt | 48856 | 48856 | 2500
500053630 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-SEATS | Operators Seat | 48856 | 5106 | 2500
500053629 | CLB-MP-SUPP-SV019 -STRUCT-CABIN-AIRCN | Air Conditioning System | 48856 | 2844 | 2500
500053628 | CLB-MP-SUPP-SV019 -GRSYST-ALCON | Auto Lube Controller | 48856 | 48856 | 2500
500053627 | CLB-MP-SUPP-SV019 -GRSYST-ALBPP | Auto Lube Pump | 48856 | 6928 | 2500
500053626 | CLB-MP-SUPP-SV019 -GRSYST-GRINJ | Auto Lube Injectors | 48856 | 48856 | 2500
500053625 | CLB-MP-SUPP-SV019 -HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 48856 | 11163 | 2500
500053624 | CLB-MP-SUPP-SV019 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 48856 | 11163 | 2500
500053623 | CLB-MP-SUPP-SV019 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 48856 | 11163 | 2500
500053622 | CLB-MP-SUPP-SV019 -HYDSYS-HOVLV | Valve Hoist | 48856 | 48856 | 2500
500053621 | CLB-MP-SUPP-SV019 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 48856 | 31790 | 2500
500053620 | CLB-MP-SUPP-SV019 -HYDSYS-HOPMP | Pump Hoist | 48856 | 2844 | 2500
500053619 | CLB-MP-SUPP-SV019 -STRSYS-STHLF | Steering System Hoses Lines and Fittings | 48856 | 11163 | 2500
500053618 | CLB-MP-SUPP-SV019 -STRSYS-STEMG-SESPP | Pump Electric Secondary Steering | 48856 | 16552 | 2500
500053617 | CLB-MP-SUPP-SV019 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 48856 | 7577 | 2500
500053616 | CLB-MP-SUPP-SV019 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 48856 | 2844 | 2500
500053615 | CLB-MP-SUPP-SV019 -STRSYS-STVLV | Valve Steering | 48856 | 16821 | 2500
500053614 | CLB-MP-SUPP-SV019 -STRSYS-STHMU | Steering HMU | 48856 | 11163 | 2500
500053613 | CLB-MP-SUPP-SV019 -STRSYS-STPMP | Pump Steering | 48856 | 16821 | 2500
500053612 | CLB-MP-SUPP-SV019 -BRKSYS-BROCO | Brake Oil Cooler | 48856 | 16821 | 2500
500053611 | CLB-MP-SUPP-SV019 -BRKSYS-MERTR | Mechanical Retarder | 48856 | 31790 | 2500
500053610 | CLB-MP-SUPP-SV019 -BRKSYS-BRVTR | Valve Brake Treadle | 48856 | 11163 | 2500
500053609 | CLB-MP-SUPP-SV019 -BRKSYS-BRVLV | Valve Brake | 48856 | 11163 | 2500
500053608 | CLB-MP-SUPP-SV019 -BRKSYS-HYFPP | Pump Brake Cooling | 48856 | 31790 | 2500
500053607 | CLB-MP-SUPP-SV019 -BRKSYS-BRPMP | Pump Brake | 48856 | 31790 | 2500
500053606 | CLB-MP-SUPP-SV019 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 48856 | 31790 | 2500
500053605 | CLB-MP-SUPP-SV019 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 48856 | 31790 | 2500
500053604 | CLB-MP-SUPP-SV019 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 48856 | 31790 | 2500
500053603 | CLB-MP-SUPP-SV019 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 48856 | 31790 | 2500
500053602 | CLB-MP-SUPP-SV019 -FDRSYS-WHTYR-POS06 | Tyre Position 6 | 48856 | 48856 | 2500
500053601 | CLB-MP-SUPP-SV019 -FDRSYS-WHTYR-POS05 | Tyre Position 5 | 48856 | 48856 | 2500
500053600 | CLB-MP-SUPP-SV019 -FDRSYS-WHTYR-POS04 | Tyre Position 4 | 48856 | 48856 | 2500
500053599 | CLB-MP-SUPP-SV019 -FDRSYS-WHTYR-POS03 | Tyre Position 3 | 48856 | 48856 | 2500
500053598 | CLB-MP-SUPP-SV019 -FDRSYS-WHTYR-POS02 | Tyre Position 2 | 48856 | 48856 | 2500
500053597 | CLB-MP-SUPP-SV019 -FDRSYS-WHTYR-POS01 | Tyre Position 1 | 48856 | 48856 | 2500
500053596 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 48856 | 11163 | 2500
500053595 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 48856 | 11163 | 2500
500053594 | CLB-MP-SUPP-SV019 -FDRSYS-FDRVE | Final Drives | 48856 | 48856 | 2500
500053593 | CLB-MP-SUPP-SV019 -FDRSYS-DIFFL | Differential | 48856 | 11163 | 2500
500053592 | CLB-MP-SUPP-SV019 -FDRSYS-DRSHT | Drive Shaft | 48856 | 11163 | 2500
500053591 | CLB-MP-SUPP-SV019 -TRNSYS-TROLC | Oil Cooler Transmission | 48856 | 11163 | 2500
500053590 | CLB-MP-SUPP-SV019 -TRNSYS-TRPMP-TCCPP | Pump Charge Torque Converter | 48856 | 31790 | 2500
500053589 | CLB-MP-SUPP-SV019 -TRNSYS-TRPMP-TMCPP | Pump Charge Transmission | 48856 | 31790 | 2500
500053588 | CLB-MP-SUPP-SV019 -TRNSYS-TRPMP | Pumps Transmission | 48856 | 11163 | 2500
500053587 | CLB-MP-SUPP-SV019 -TRNSYS-TRANS | Transmission | 48856 | 11163 | 2500
500053586 | CLB-MP-SUPP-SV019 -TRNSYS-TRQUE | Torque Converter | 48856 | 11163 | 2500
500053585 | CLB-MP-SUPP-SV019 -ELCTLV-START-STMLO | Starter Motor Lower | 48856 | 2844 | 2500
500053584 | CLB-MP-SUPP-SV019 -ELCTLV-START-STMUP | Starter Motor Upper | 48856 | 2844 | 2500
500053583 | CLB-MP-SUPP-SV019 -ELCTLV-CHARG-BATTY | Batteries | 48856 | 7564 | 2500
500053582 | CLB-MP-SUPP-SV019 -ELCTLV-CHARG-ALTER | Alternator 24V | 48856 | 2844 | 2500
500053581 | CLB-MP-SUPP-SV019 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 48856 | 2844 | 2500
500053580 | CLB-MP-SUPP-SV019 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 48856 | 2844 | 2500
500053579 | CLB-MP-SUPP-SV019 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 48856 | 2844 | 2500
500053578 | CLB-MP-SUPP-SV019 -ENGINE-INTEX-EXHST | Exhaust System | 48856 | 48856 | 2500
500053577 | CLB-MP-SUPP-SV019 -ENGINE-INTEX-AFTER | Aftercooler | 48856 | 11163 | 2500
500053576 | CLB-MP-SUPP-SV019 -ENGINE-INTEX-TBORH | Turbocharger R/H | 48856 | 2844 | 2500
500053575 | CLB-MP-SUPP-SV019 -ENGINE-INTEX-TBOLH | Turbocharger L/H | 48856 | 2844 | 2500
500053574 | CLB-MP-SUPP-SV019 -ENGINE-COSYS-THERM | Thermostats/Regulators | 48856 | 2844 | 2500
500053573 | CLB-MP-SUPP-SV019 -ENGINE-COSYS-RADTR | Radiator Engine | 48856 | 11163 | 2500
500053572 | CLB-MP-SUPP-SV019 -ENGINE-COSYS-WTRPP | Water Pump Engine | 48856 | 2844 | 2500
500053571 | CLB-MP-SUPP-SV019 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 48856 | 31790 | 2500
500053570 | CLB-MP-SUPP-SV019 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 48856 | 31790 | 2500
500053569 | CLB-MP-SUPP-SV019 -ENGINE-LUBSY-PREPP | Engine Pre Lube | 48856 | 11163 | 2500
500053568 | CLB-MP-SUPP-SV019 -ENGINE-LUBSY | Engine Lubrication System | 48856 | 31790 | 2500
500053566 | CLB-MP-SUPP-SV019 -ENGINE | Engine Assembly, Caterpillar C32 | 48856 | 11163 | 2500
500053105 | CLB-MP-SUPP-SV019 -STRSYS-STLTR | Steering Linkages and Tie Rods | 48856 | 2844 | 2500
500053104 | CLB-MP-SUPP-SV019 -FRSUPP | Fire Suppression System | 48856 | 11163 | 2500
500053103 | CLB-MP-SUPP-SV019 | SV019 Lubrication/Mechanical Services | 48856 | 11163 | 2500
500053102 | CLB-MP-SUPP-SV019 | Caterpillar 777F Service Truck SV019 | 48856 | 48856 | 2500
500106865 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BCOMR | Float Brake Cooler Module (Radiator) | 53807 | 10731 | 4200
500106296 | CLB-MP-SUPP-LL0003-BRKSYS-SLACK | Slack Adjuster | 71996 | 11102 | 4200
500106295 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-FLBCV | Float Air Brake Control Valve - Cabin | 53807 | 9242 | 4200
500102996 | CLB-MP-SUPP-LL0003-BRKSYS-SRVBK-SVBRH | Service Brake R/H Rear | 71996 | 53807 | 4200
500102995 | CLB-MP-SUPP-LL0003-BRKSYS-SRVBK-SVBLH | Service Brake L/H Rear | 71996 | 53807 | 4200
500102994 | CLB-MP-SUPP-LL0003-STRUCT-SUSPN-SUCYR | Suspension Cylinder RH | 71996 | 605 | 4200
500102993 | CLB-MP-SUPP-LL0003-STRUCT-SUSPN-SUCYL | Suspension Cylinder LH | 71996 | 7522 | 4200
500102992 | CLB-MP-SUPP-LL0003-HYDSYS-HDCYL-SCYRH | Swing Cylinder RH | 71996 | 1615 | 4200
500102991 | CLB-MP-SUPP-LL0003-HYDSYS-HDCYL-SCYLH | Swing Cylinder LH | 71996 | 1615 | 4200
500102990 | CLB-MP-SUPP-LL0003-HYDSYS-HDCYL-RCYLR | Ramp Cylinder RH | 71996 | 8281 | 4200
500102989 | CLB-MP-SUPP-LL0003-HYDSYS-HDCYL-RCYLH | Ramp Cylinder LH | 71996 | 3801 | 4200
500102988 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-RAMPR | Loading Ramp Pins RH | 71996 | 20945 | 4200
500102987 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-RAMPL | Loading Ramp Pins LH | 71996 | 20945 | 4200
500102986 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-PIVOT | Pivot Group | 71996 | 53807 | 4200
500102985 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-HITCH | Hitch | 71996 | 53807 | 4200
500102984 | CLB-MP-SUPP-LL0003-BRKSYS-BRVLV-FTBRV | Brake Relay Valve | 71996 | 11102 | 4200
500102983 | CLB-MP-SUPP-LL0003-BRKSYS-BRCYL-FROTR | Rotochamber RH | 71996 | 6312 | 4200
500102982 | CLB-MP-SUPP-LL0003-BRKSYS-BRCYL-FROTL | Rotochamber LH | 71996 | 53807 | 4200
500102979 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT | Bed Structure | 71996 | 53807 | 4200
500102978 | CLB-MP-SUPP-LL0003-FDRSYS-FDRRH | Final Drive R/H | 71996 | 16879 | 4200
500102977 | CLB-MP-SUPP-LL0003-FDRSYS-FDRLH | Final Drive L/H | 71996 | 16879 | 4200
500102976 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-CLAMP | Clamp | 71996 | 19033 | 4200
500102975 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM2 | Oil Circulation Pump & Motor 200PSI | 71996 | 1615 | 4200
500102974 | CLB-MP-SUPP-LL0003-BRKSYS-BCPM1 | Brake Cooling Pump & Motor 40PSI | 71996 | 1615 | 4200
500081528 | CLB-MP-SUPP-PM0006-FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 53807 | 53807 | 4200
500081503 | CLB-MP-SUPP-PM0006-FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 53807 | 53807 | 4200
500064242 | CLB-MP-SUPP-PM0006-TRNSYS-TRQUE | Torque Converter | 53807 | 15788 | 4200
500064241 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP-TMCPP | Pump Transmission | 53807 | 260 | 4200
500064240 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP-TCCPP | Pump TC/Park Brake Release/Scavenge | 53807 | 15788 | 4200
500064239 | CLB-MP-SUPP-PM0006-TRNSYS-TRPMP | Pumps Transmission | 53807 | 53807 | 4200
500064238 | CLB-MP-SUPP-PM0006-TRNSYS-TROLC | Oil Cooler Transmission | 53807 | 15788 | 4200
500064237 | CLB-MP-SUPP-PM0006-TRNSYS-TRANS | Transmission | 53807 | 15788 | 4200
500064236 | CLB-MP-SUPP-PM0006-TRNSYS | Transmission System | 53807 | 8281 | 4200
500064232 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 53807 | 15788 | 4200
500064231 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 53807 | 15788 | 4200
500064230 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 53807 | 15788 | 4200
500064229 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 53807 | 15788 | 4200
500064228 | CLB-MP-SUPP-PM0006-STRUCT-SUSPN | Suspension | 53807 | 53807 | 4200
500064227 | CLB-MP-SUPP-PM0006-STRUCT-STLAD-SLFXD | Fixed Steps and Ladders | 53807 | 53807 | 4200
500064226 | CLB-MP-SUPP-PM0006-STRUCT-STLAD | Steps and Ladders | 53807 | 53807 | 4200
500064225 | CLB-MP-SUPP-PM0006-STRUCT-PNLGU | Panels and Guards | 53807 | 53807 | 4200
500064224 | CLB-MP-SUPP-PM0006-STRUCT-PLHAN | Platforms and Handrails | 53807 | 53807 | 4200
500064223 | CLB-MP-SUPP-PM0006-STRUCT-CHASS-TAGLK | Tag Link | 53807 | 53807 | 4200
500064222 | CLB-MP-SUPP-PM0006-STRUCT-CHASS-AFRME | A Frame | 53807 | 15788 | 4200
500064221 | CLB-MP-SUPP-PM0006-STRUCT-CHASS | Chassis | 53807 | 53807 | 4200
500064220 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-SEATS | Operators Seat | 53807 | 6312 | 4200
500064219 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-SBELT | Seat Belt | 53807 | 53807 | 4200
500064218 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-GLASS | Glass | 53807 | 53807 | 4200
500064217 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 53807 | 53807 | 4200
500064216 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-CABES | Cabin Entertainment System | 53807 | 53807 | 4200
500064215 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-CABCO | Cabin Controls | 53807 | 53807 | 4200
500064214 | CLB-MP-SUPP-PM0006-STRUCT-CABIN-AIRCN | Air Conditioning System | 53807 | 3537 | 4200
500064213 | CLB-MP-SUPP-PM0006-STRUCT-CABIN | Operators Cabin | 53807 | 53807 | 4200
500064212 | CLB-MP-SUPP-PM0006-STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 53807 | 15788 | 4200
500064211 | CLB-MP-SUPP-PM0006-STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 53807 | 15788 | 4200
500064210 | CLB-MP-SUPP-PM0006-STRUCT-AXLES | Axle Assembly Front | 53807 | 53807 | 4200
500064209 | CLB-MP-SUPP-PM0006-STRUCT | Structure | 53807 | 53807 | 4200
500064208 | CLB-MP-SUPP-PM0006-STRSYS-STVLV | Valve Steering | 53807 | 53807 | 4200
500064207 | CLB-MP-SUPP-PM0006-STRSYS-STTNK | Tank Steering | 53807 | 53807 | 4200
500064206 | CLB-MP-SUPP-PM0006-STRSYS-STRCY-STCYR | Cylinder Steering R/H | 53807 | 7340 | 4200
500064205 | CLB-MP-SUPP-PM0006-STRSYS-STRCY-STCYL | Cylinder Steering L/H | 53807 | 7340 | 4200
500064204 | CLB-MP-SUPP-PM0006-STRSYS-STRCY | Cylinders Steering | 53807 | 53807 | 4200
500064203 | CLB-MP-SUPP-PM0006-STRSYS-STPMP | Pump Steering | 53807 | 2698 | 4200
500064202 | CLB-MP-SUPP-PM0006-STRSYS-STOLC | Oil Cooler Steering | 53807 | 6738 | 4200
500064201 | CLB-MP-SUPP-PM0006-STRSYS-STLTR | Steering Linkages and Tie Rods | 53807 | 7340 | 4200
500064200 | CLB-MP-SUPP-PM0006-STRSYS-STHMU | Steering HMU | 53807 | 5388 | 4200
500064199 | CLB-MP-SUPP-PM0006-STRSYS-STHLF | Steering System Hoses Lines and Fittings | 53807 | 53807 | 4200
500064198 | CLB-MP-SUPP-PM0006-STRSYS-STCON-STWHL | Steering Wheel | 53807 | 53807 | 4200
500064197 | CLB-MP-SUPP-PM0006-STRSYS-STCON-STCOL | Steering Column | 53807 | 53807 | 4200
500064196 | CLB-MP-SUPP-PM0006-STRSYS-STCON | Controls Steering | 53807 | 53807 | 4200
500064195 | CLB-MP-SUPP-PM0006-STRSYS-STACC-SACRH | Accumulator Steering R/H Front | 53807 | 7340 | 4200
500064194 | CLB-MP-SUPP-PM0006-STRSYS-STACC-SACLH | Accumulator Steering L/H Front | 53807 | 7340 | 4200
500064193 | CLB-MP-SUPP-PM0006-STRSYS-STACC | Accumulators Steering | 53807 | 53807 | 4200
500064192 | CLB-MP-SUPP-PM0006-STRSYS | Steering System | 53807 | 53807 | 4200
500064191 | CLB-MP-SUPP-PM0006-PNEUMC-START | Pneumatic Starter Motor | 53807 | 15788 | 4200
500064190 | CLB-MP-SUPP-PM0006-PNEUMC-PNTNK | Air Tank | 53807 | 16976 | 4200
500064189 | CLB-MP-SUPP-PM0006-PNEUMC-PNHLF | Pneumatic System Hoses Lines Fittings | 53807 | 53807 | 4200
500064188 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-SVBRF | Brake Air Relay Valve | 53807 | 53807 | 4200
500064187 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR-ARCRR | Auto Retard Control | 53807 | 53807 | 4200
500064186 | CLB-MP-SUPP-PM0006-PNEUMC-BRVLR | Brake Control Valves | 53807 | 53807 | 4200
500064185 | CLB-MP-SUPP-PM0006-PNEUMC-AIRDR | Air Drier | 53807 | 24746 | 4200
500064184 | CLB-MP-SUPP-PM0006-PNEUMC | Pneumatic System | 53807 | 53807 | 4200
500064183 | CLB-MP-SUPP-PM0006-MANGMT-UMTRN | Power Train Management System | 53807 | 53807 | 4200
500064182 | CLB-MP-SUPP-PM0006-MANGMT-UMMMC | Mine Monitoring and Control | 53807 | 53807 | 4200
500064181 | CLB-MP-SUPP-PM0006-MANGMT-UMENG | Engine Management System | 53807 | 53807 | 4200
500064180 | CLB-MP-SUPP-PM0006-MANGMT | Unit Management | 53807 | 53807 | 4200
500064179 | CLB-MP-SUPP-PM0006-HYDSYS-TOWPP | Pump Towing | 53807 | 53807 | 4200
500064178 | CLB-MP-SUPP-PM0006-HYDSYS-HOVLV | Valve Hoist | 53807 | 53807 | 4200
500064177 | CLB-MP-SUPP-PM0006-HYDSYS-HOPMP | Pump Hoist & Rear Brake Cooling | 53807 | 2616 | 4200
500064176 | CLB-MP-SUPP-PM0006-HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 53807 | 53807 | 4200
500064175 | CLB-MP-SUPP-PM0006-HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 53807 | 53807 | 4200
500064174 | CLB-MP-SUPP-PM0006-HYDSYS-HOCYL | Cylinders Hoist | 53807 | 53807 | 4200
500064173 | CLB-MP-SUPP-PM0006-HYDSYS-HDTNK | Tank Hydraulic | 53807 | 53807 | 4200
500064172 | CLB-MP-SUPP-PM0006-HYDSYS-HDHLF | Hydraulic System Hoses Lines Fittings | 53807 | 53807 | 4200
500064171 | CLB-MP-SUPP-PM0006-HYDSYS | Hydraulic System | 53807 | 53807 | 4200
500064170 | CLB-MP-SUPP-PM0006-GRSYST-GRTNK | Auto Lube Resevoir | 53807 | 53807 | 4200
500064169 | CLB-MP-SUPP-PM0006-GRSYST-GRINJ | Auto Lube Injectors | 53807 | 53807 | 4200
500064168 | CLB-MP-SUPP-PM0006-GRSYST-ALHLF | Auto Lube Hoses Lines Fittings | 53807 | 53807 | 4200
500064167 | CLB-MP-SUPP-PM0006-GRSYST-ALELC | Auto Lube Electrical | 53807 | 53807 | 4200
500064166 | CLB-MP-SUPP-PM0006-GRSYST-ALCON | Auto Lube Controller | 53807 | 53807 | 4200
500064165 | CLB-MP-SUPP-PM0006-GRSYST-ALBPP | Auto Lube Pump | 53807 | 14148 | 4200
500064164 | CLB-MP-SUPP-PM0006-GRSYST | Grease Lubrication System | 53807 | 53807 | 4200
500064163 | CLB-MP-SUPP-PM0006-FRSUPP-FSMAN-EXTIN | Hand Held Fire Extinguisher | 53807 | 53807 | 4200
500064162 | CLB-MP-SUPP-PM0006-FRSUPP-FSMAN | Fire Suppression Manual | 53807 | 53807 | 4200
500064161 | CLB-MP-SUPP-PM0006-FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 53807 | 53807 | 4200
500064160 | CLB-MP-SUPP-PM0006-FRSUPP-FSAUT | Fire Suppression Automatic | 53807 | 53807 | 4200
500064159 | CLB-MP-SUPP-PM0006-FRSUPP-FSALM | Fire System Alarm | 53807 | 53807 | 4200
500064158 | CLB-MP-SUPP-PM0006-FRSUPP | Fire Suppression System | 53807 | 53807 | 4200
500064157 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR-POS06 | Tyre Position 6 | 53807 | 53807 | 4200
500064156 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR-POS05 | Tyre Position 5 | 53807 | 53807 | 4200
500064155 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR-POS04 | Tyre Position 4 | 53807 | 53807 | 4200
500064154 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR-POS03 | Tyre Position 3 | 53807 | 53807 | 4200
500064153 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR-POS02 | Tyre Position 2 | 53807 | 53807 | 4200
500064152 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR-POS01 | Tyre Position 1 | 53807 | 53807 | 4200
500064151 | CLB-MP-SUPP-PM0006-FDRSYS-WHTYR | Wheels, Tyres and Rims | 53807 | 53807 | 4200
500064150 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE-FDRRH | Final Drive R/H | 53807 | 15788 | 4200
500064149 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE-FDRLH | Final Drive L/H | 53807 | 15788 | 4200
500064148 | CLB-MP-SUPP-PM0006-FDRSYS-FDRVE | Final Drives | 53807 | 53807 | 4200
500064147 | CLB-MP-SUPP-PM0006-FDRSYS-DRSHT | Drive Shaft, Transmission | 53807 | 15788 | 4200
500064146 | CLB-MP-SUPP-PM0006-FDRSYS-DRLAX | Drive Line Axles | 53807 | 53807 | 4200
500064145 | CLB-MP-SUPP-PM0006-FDRSYS-DIFFL | Differential | 53807 | 15788 | 4200
500064144 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 53807 | 6312 | 4200
500064143 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 53807 | 6312 | 4200
500064142 | CLB-MP-SUPP-PM0006-FDRSYS-AXLEC | Rear Axle Oil Cooling | 53807 | 53807 | 4200
500064141 | CLB-MP-SUPP-PM0006-FDRSYS | Final Drive System | 53807 | 53807 | 4200
500064140 | CLB-MP-SUPP-PM0006-ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 53807 | 6312 | 4200
500064139 | CLB-MP-SUPP-PM0006-ENGINE-PMPDR | Pump Drive | 53807 | 15788 | 4200
500064138 | CLB-MP-SUPP-PM0006-ENGINE-LUBSY-PREPP | Oil Pump Prelube | 53807 | 53807 | 4200
500064137 | CLB-MP-SUPP-PM0006-ENGINE-LUBSY-OILPP | Oil Pump Engine | 53807 | 53807 | 4200
500064136 | CLB-MP-SUPP-PM0006-ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 53807 | 3537 | 4200
500064135 | CLB-MP-SUPP-PM0006-ENGINE-LUBSY | Engine Lubrication System | 53807 | 53807 | 4200
500064134 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 53807 | 3537 | 4200
500064133 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-TBORF | Turbocharger R/H Front | 53807 | 3537 | 4200
500064132 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 53807 | 3537 | 4200
500064131 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 53807 | 3537 | 4200
500064130 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-EXHST | Exhaust System | 53807 | 53807 | 4200
500064129 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-AIRFL | Air Filtration System | 53807 | 53807 | 4200
500064128 | CLB-MP-SUPP-PM0006-ENGINE-INTEX-AFTER | Aftercooler | 53807 | 15788 | 4200
500064127 | CLB-MP-SUPP-PM0006-ENGINE-INTEX | Intake and Exhaust System | 53807 | 53807 | 4200
500064126 | CLB-MP-SUPP-PM0006-ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 53807 | 3537 | 4200
500064125 | CLB-MP-SUPP-PM0006-ENGINE-FUSYS-FULTK | Fuel Tank | 53807 | 53807 | 4200
500064124 | CLB-MP-SUPP-PM0006-ENGINE-FUSYS-FULPP | Fuel Priming Pump | 53807 | 3537 | 4200
500064123 | CLB-MP-SUPP-PM0006-ENGINE-FUSYS-FUINJ | Fuel Injectors | 53807 | 3537 | 4200
500064122 | CLB-MP-SUPP-PM0006-ENGINE-FUSYS-FUHLF | Fuel System Hoses, Lines and Fittings | 53807 | 53807 | 4200
500064121 | CLB-MP-SUPP-PM0006-ENGINE-FUSYS | Fuel System | 53807 | 53807 | 4200
500064120 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-WTRPP | Water Pump Engine | 53807 | 3537 | 4200
500064119 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-THERM | Thermostats/Regulators | 53807 | 3537 | 4200
500064118 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-RADTR | Radiator Engine | 53807 | 15788 | 4200
500064117 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-CSHLF | Cooling System Hoses, Lines and Fitting | 53807 | 33815 | 4200
500064116 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-COFAN | Fan Cooling System | 53807 | 33815 | 4200
500064115 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-BELTS | Fan Belts Engine | 53807 | 33815 | 4200
500064114 | CLB-MP-SUPP-PM0006-ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 53807 | 3537 | 4200
500064113 | CLB-MP-SUPP-PM0006-ENGINE-COSYS | Engine Cooling System | 53807 | 33815 | 4200
500064112 | CLB-MP-SUPP-PM0006-ENGINE-COMPR | Air Compressor | 53807 | 3537 | 4200
500064111 | CLB-MP-SUPP-PM0006-ENGINE | Engine Assembly, Caterpillar 3512 | 53807 | 15788 | 4200
500064110 | CLB-MP-SUPP-PM0006-ELCTLV-LIGHT | Lighting Low Voltage | 53807 | 53807 | 4200
500064109 | CLB-MP-SUPP-PM0006-ELCTLV-HARNS | Electrical Harness | 53807 | 53807 | 4200
500064108 | CLB-MP-SUPP-PM0006-ELCTLV-CONTL | Electrical Controls Low Voltage | 53807 | 53807 | 4200
500064107 | CLB-MP-SUPP-PM0006-ELCTLV-CHARG-BATTY | Batteries | 53807 | 53807 | 4200
500064106 | CLB-MP-SUPP-PM0006-ELCTLV-CHARG-ALTER | Alternator 24V | 53807 | 15788 | 4200
500064105 | CLB-MP-SUPP-PM0006-ELCTLV-CHARG | Charging System | 53807 | 53807 | 4200
500064104 | CLB-MP-SUPP-PM0006-ELCTLV | Electrical System Low Voltage 24V | 53807 | 53807 | 4200
500064103 | CLB-MP-SUPP-PM0006-COMMUN-RADIO | Two Way Radio | 53807 | 53807 | 4200
500064102 | CLB-MP-SUPP-PM0006-COMMUN-FLMGT | Fleet Management | 53807 | 53807 | 4200
500064101 | CLB-MP-SUPP-PM0006-COMMUN | Communications | 53807 | 53807 | 4200
500064100 | CLB-MP-SUPP-PM0006-BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 53807 | 33815 | 4200
500064099 | CLB-MP-SUPP-PM0006-BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 53807 | 33815 | 4200
500064098 | CLB-MP-SUPP-PM0006-BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 53807 | 33815 | 4200
500064097 | CLB-MP-SUPP-PM0006-BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 53807 | 33815 | 4200
500064096 | CLB-MP-SUPP-PM0006-BRKSYS-SRVBK | Service Brake | 53807 | 53807 | 4200
500064095 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 53807 | 15788 | 4200
500064094 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 53807 | 15788 | 4200
500064093 | CLB-MP-SUPP-PM0006-BRKSYS-SLACK | Brake Slack Adjusters | 53807 | 53807 | 4200
500064092 | CLB-MP-SUPP-PM0006-BRKSYS-PRKPP | Pump Park Brake Release | 53807 | 53807 | 4200
500064091 | CLB-MP-SUPP-PM0006-BRKSYS-MERTR | Mechanical Retarder | 53807 | 53807 | 4200
500064090 | CLB-MP-SUPP-PM0006-BRKSYS-BRVTR | Valve Brake Treadle | 53807 | 53807 | 4200
500064089 | CLB-MP-SUPP-PM0006-BRKSYS-BRVLV | Valve Brake | 53807 | 15788 | 4200
500064088 | CLB-MP-SUPP-PM0006-BRKSYS-BRPMP | Pump Brake | 53807 | 53807 | 4200
500064087 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BROCT | Brake Oil Cooler Top Rear | 53807 | 53807 | 4200
500064086 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 53807 | 15788 | 4200
500064085 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO-BROCB | Brake Oil Cooler Rear Bottom Rear | 53807 | 53807 | 4200
500064084 | CLB-MP-SUPP-PM0006-BRKSYS-BROCO | Brake Oil Cooler | 53807 | 53807 | 4200
500064083 | CLB-MP-SUPP-PM0006-BRKSYS-BRHLF | Brake System Hoses Lines and Fittings | 53807 | 53807 | 4200
500064082 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 53807 | 15788 | 4200
500064081 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 53807 | 15788 | 4200
500064070 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL-ROTFR | Rotochamber Front | 53807 | 17402 | 4200
500064069 | CLB-MP-SUPP-PM0006-BRKSYS-BRCYL | Brake Cylinders | 53807 | 53807 | 4200
500064068 | CLB-MP-SUPP-PM0006-BRKSYS-ACCUM | Brake Accumulator | 53807 | 7693 | 4200
500064067 | CLB-MP-SUPP-PM0006-BRKSYS | Braking System | 53807 | 53807 | 4200
500002866 | CLB-MP-SUPP-LL0003 | LL0003 Bosich RAX 280 Tonne Float | 71996 | 71996 | 4200
500058616 | CLB-MP-SUPP-PM0006 | PM0006 Caterpillar 785D Prime Mover | 53807 | 53807 | 4200
500126971 | CLB-MP-SUPP-LL0002-PNEUMC-BRVLR-VALRE | LL0002 Valve Relay Emergency | 91736 | 30628 | 3500
500126970 | CLB-MP-SUPP-LL0002-PNEUMC-BRVLR-VALRB | LL0002 Valve Relay Booster | 91736 | 30628 | 3500
500126969 | CLB-MP-SUPP-PM0004-PNEUMC-BRVLR-SVBRR | PM0004 Service Brake Relay Rear | 91736 | 6608 | 3500
500126968 | CLB-MP-SUPP-PM0004-HYDSYS-TOWPP | PM0004 Pump Towing | 91736 | 3709 | 3500
500126967 | CLB-MP-SUPP-PM0004-BRKSYS-BROCO-BROCF | PM0004 Brake Oil Cooler Front | 91736 | 3709 | 3500
500126954 | CLB-MP-SUPP-LL0002 | LL0002 Towhaul 408T Float | 91736 | 91736 | 3500
500081542 | CLB-MP-SUPP-PM0004-FDRSYS-DRLAX-AXLRH | PM0004 Drive Line Axle RH | 91736 | 91736 | 3500
500081517 | CLB-MP-SUPP-PM0004-FDRSYS-DRLAX-AXLLH | PM0004 Drive Line Axle LH | 91736 | 91736 | 3500
500080090 | CLB-MP-SUPP-LL0002-HYDSYS-HDCYL-CYGNH | LL0002 Cylinder Grab Hook Gooseneck | 91736 | 6621 | 3500
500080089 | CLB-MP-SUPP-PM0004-HYDSYS-HDCYL-CYSLL | PM0004 Cylinder Slide Gooseneck LH | 91736 | 6593 | 3500
500080088 | CLB-MP-SUPP-PM0004-HYDSYS-HDCYL-CYSLR | PM0004 Cylinder Slide Gooseneck RH | 91736 | 6593 | 3500
500080087 | CLB-MP-SUPP-PM0004-HYDSYS-HDCYL-CYAPL | PM0004 Cylinder Apron Gooseneck LH | 91736 | 6593 | 3500
500080086 | CLB-MP-SUPP-PM0004-HYDSYS-HDCYL-CYAPR | PM0004 Cylinder Apron Gooseneck RH | 91736 | 91736 | 3500
500080085 | CLB-MP-SUPP-LL0002-HYDSYS-HDCYL-CYMLL | LL0002 Cyl Main Lower Lift Gooseneck LH | 91736 | 4497 | 3500
500080084 | CLB-MP-SUPP-LL0002-HYDSYS-HDCYL-CYMLR | LL0002 Cyl Main Lower Lift Gooseneck RH | 91736 | 6621 | 3500
500080083 | CLB-MP-SUPP-LL0002-HYDSYS-HDCYL-CYMUL | LL0002 Cyl Main Upper Lift Gooseneck LH | 91736 | 6621 | 3500
500080082 | CLB-MP-SUPP-LL0002-HYDSYS-HDCYL-CYMUR | LL0002 Cyl Main Upper Lift Gooseneck RH | 91736 | 6621 | 3500
500080081 | CLB-MP-SUPP-PM0004-STRUCT-CHASS-SBFRM | PM0004 Subframe Gooseneck | 91736 | 6621 | 3500
500080080 | CLB-MP-SUPP-LL0002-STRUCT-GNECK-HKGRB | LL0002 Hook Grab | 91736 | 91736 | 3500
500080079 | CLB-MP-SUPP-LL0002-STRUCT-GNECK-TTARM | LL0002 Toe Arm/Tee Bar Assembly | 91736 | 91736 | 3500
500080078 | CLB-MP-SUPP-PM0004-STRUCT-TTBLE | PM0004 Turntable | 91736 | 91736 | 3500
500080077 | CLB-MP-SUPP-LL0002-STRUCT-GNECK-HYDSY | LL002 Hydraulic System Gooseneck | 91736 | 91736 | 3500
500080076 | CLB-MP-SUPP-LL0002-BRKSYS-SLACK | LL0002 Brake Slack Adjuster Float Axle | 91736 | 3709 | 3500
500080075 | CLB-MP-SUPP-LL0002-BRKSYS-BRCYL-ROTPR | LL0002 Rotochamber Prk Brake Release Rr | 91736 | 25890 | 3500
500080074 | CLB-MP-SUPP-LL0002-BRKSYS-BRCYL-ROTPM | LL0002 Rotochamber Pk Brake Release Mid | 91736 | 25890 | 3500
500080073 | CLB-MP-SUPP-LL0002-BRKSYS-BRCYL-ROTPF | LL0002 Rotochamber Pk Brake Release Frnt | 91736 | 8845 | 3500
500080072 | CLB-MP-SUPP-LL0002-BRKSYS-BRCYL-ROTSR | LL0002 Rotochamber Service Brake Rear | 91736 | 25890 | 3500
500080071 | CLB-MP-SUPP-LL0002-BRKSYS-BRCYL-ROTSF | LL0002 Rotochamber Service Brake Front | 91736 | 25890 | 3500
500080070 | CLB-MP-SUPP-PM0004-BRKSYS-BACCM | PM0004 Accumulator Pk Brake Rel - Float | 91736 | 3709 | 3500
500080069 | CLB-MP-SUPP-LL0002-BRKSYS-BROCO | LL0002 Brake Oil Cooler | 91736 | 6593 | 3500
500080068 | CLB-MP-SUPP-LL0002-BRKSYS-BROCO-COFAN | LL0002 Fan Assy Brake Oil Cooler | 91736 | 25890 | 3500
500080067 | CLB-MP-SUPP-LL0002-BRKSYS-MBOCF | LL0002 Motor Brake Oil Cooler Fan | 91736 | 10879 | 3500
500080066 | CLB-MP-SUPP-LL0002-BRKSYS-PBCFA | LL0002 Pump Brake Oil Cooler Fan | 91736 | 780 | 3500
500080065 | CLB-MP-SUPP-LL0002-BRKSYS-PBCRH | LL0002 Pump Brake Cooling RH | 91736 | 780 | 3500
500080064 | CLB-MP-SUPP-LL0002-BRKSYS-PBCLH | LL0002 Pump Brake Cooling LH | 91736 | 17126 | 3500
500080063 | CLB-MP-SUPP-LL0002-FDRSYS-PDRAX | Pump Drive Rear Axle | 91736 | 17126 | 3500
500080062 | CLB-MP-SUPP-LL0002-FDRSYS-PDRAX-CPDRA | LL0002 Clutch Pump Drive Rear Axle | 91736 | 17126 | 3500
500080061 | CLB-MP-SUPP-LL0002-FDRSYS-DIFFL | Differential Rear Axle | 91736 | 8887 | 3500
500080060 | CLB-MP-SUPP-LL0002-FDRSYS-FDRVE-FDRRH | LL0002 Final Drive R/H | 91736 | 16791 | 3500
500080059 | CLB-MP-SUPP-LL0002-FDRSYS-FDRVE-FDRLH | LL0002 Final Drive L/H | 91736 | 16791 | 3500
500080058 | CLB-MP-SUPP-PM0004-STRUCT-SUSPN-SCYRR | PM0004 Cylinder Suspension R/H Rear | 91736 | 3709 | 3500
500080057 | CLB-MP-SUPP-PM0004-STRUCT-SUSPN-SCYLR | PM0004 Cylinder Suspension L/H Rear | 91736 | 3709 | 3500
500080056 | CLB-MP-SUPP-PM0004-STRUCT-SUSPN-SCYRF | PM0004 Cylinder Suspension R/H Front | 91736 | 3709 | 3500
500080055 | CLB-MP-SUPP-PM0004-STRUCT-SUSPN-SCYLF | PM0004 Cylinder Suspension L/H Front | 91736 | 3709 | 3500
500080054 | CLB-MP-SUPP-PM0004-STRUCT-AXLES-HUBRH | PM0004 Hub and Spindle R/H | 91736 | 22384 | 3500
500080053 | CLB-MP-SUPP-PM0004-STRUCT-AXLES-HUBLH | PM0004 Hub and Spindle L/H | 91736 | 17182 | 3500
500080052 | CLB-MP-SUPP-PM0004-STRUCT-CHASS-TAGLK | PM0004 Tag Link | 91736 | 4597 | 3500
500080051 | CLB-MP-SUPP-PM0004-STRUCT-CHASS-AFRME | PM0004 A Frame | 91736 | 6621 | 3500
500080050 | CLB-MP-SUPP-PM0004-STRUCT-CABIN-SEATS | PM0004 Operators Seat | 91736 | 101 | 3500
500080049 | CLB-MP-SUPP-PM0004-STRUCT-CABIN-AIRCN | PM0004 Air Conditioning System | 91736 | 186 | 3500
500080048 | CLB-MP-SUPP-PM0004-PNEUMC-AIRDR-DRYRR | Air Drier Rear | 91736 | 91736 | 3500
500080047 | CLB-MP-SUPP-PM0004-PNEUMC-AIRDR-DRYFR | Air Drier Front | 91736 | 91736 | 3500
500080046 | CLB-MP-SUPP-PM0004-PNEUMC-BRVLR-ARCRR | PM0004 Auto Retard Control Relay Rear | 91736 | 91736 | 3500
500080045 | CLB-MP-SUPP-PM0004-PNEUMC-BRVLR-SVBRF | PM0004 Service Brake Relay Front | 91736 | 6608 | 3500
500080044 | CLB-MP-SUPP-PM0004-GRSYST-ALBPP | PM0004 Auto Lube Pump | 91736 | 6593 | 3500
500080043 | CLB-MP-SUPP-PM0004-HYDSYS-HDHLF | PM0004 Hydraulic System Hoses | 91736 | 3709 | 3500
500080042 | CLB-MP-SUPP-PM0004-HYDSYS-VLVFT | PM0004 Valve Control (Float) | 91736 | 91736 | 3500
500080041 | CLB-MP-SUPP-PM0004-HYDSYS-VLVPM | PM0004 Valve Control (Prime Mover) | 91736 | 91736 | 3500
500080040 | CLB-MP-SUPP-PM0004-HYDSYS-HDOCO | LL002 Oil Cooler Hydraulic | 91736 | 91736 | 3500
500080039 | CLB-MP-SUPP-PM0004-HYDSYS-HOPMP | PM0004 Pump Hoist | 91736 | 5405 | 3500
500080038 | CLB-MP-SUPP-PM0004-STRSYS-STHLF | PM0004 Steering System Hoses | 91736 | 25890 | 3500
500080037 | CLB-MP-SUPP-PM0004-STRSYS-STLTR | PM0004 Steering Linkages and Tie Rods | 91736 | 9521 | 3500
500080036 | CLB-MP-SUPP-PM0004-STRSYS-STACC-SACCR | PM0004 Accumulator Steering Rear | 91736 | 20811 | 3500
500080035 | CLB-MP-SUPP-PM0004-STRSYS-STACC-SACCF | PM0004 Accumulator Steering Front | 91736 | 20811 | 3500
500080034 | CLB-MP-SUPP-PM0004-STRSYS-STRCY-STCYR | PM0004 Cylinder Steering R/H | 91736 | 19327 | 3500
500080033 | CLB-MP-SUPP-PM0004-STRSYS-STRCY-STCYL | PM0004 Cylinder Steering L/H | 91736 | 19327 | 3500
500080032 | CLB-MP-SUPP-PM0004-STRSYS-STVLV | PM0004 Valve Steering | 91736 | 10879 | 3500
500080031 | CLB-MP-SUPP-PM0004-STRSYS-STHMU | PM0004 Steering HMU | 91736 | 10879 | 3500
500080030 | CLB-MP-SUPP-PM0004-STRSYS-STPMP | PM0004 Pump Steering | 91736 | 5405 | 3500
500080029 | CLB-MP-SUPP-PM0004-BRKSYS-BRHLF | PM0004 Brake System Hoses | 91736 | 3709 | 3500
500080028 | CLB-MP-SUPP-PM0004-BRKSYS-BRCYL-ROTRR | PM0004 Rotochamber R/H Rear | 91736 | 3709 | 3500
500080027 | CLB-MP-SUPP-PM0004-BRKSYS-BRCYL-ROTLR | PM0004 Rotochamber L/H Rear | 91736 | 3709 | 3500
500080026 | CLB-MP-SUPP-PM0004-BRKSYS-BRCYL-ROTFR | PM0004 Rotochamber R/H Front | 91736 | 3709 | 3500
500080025 | CLB-MP-SUPP-PM0004-BRKSYS-BRCYL-ROTFL | PM0004 Rotochamber L/H Front | 91736 | 3709 | 3500
500080024 | CLB-MP-SUPP-PM0004-BRKSYS-SLACK-SLACR | PM0004 Brake Slack Adjuster Rear | 91736 | 3709 | 3500
500080023 | CLB-MP-SUPP-PM0004-BRKSYS-SLACK-SLACF | PM0004 Brake Slack Adjuster Front | 91736 | 3709 | 3500
500080022 | CLB-MP-SUPP-PM0004-BRKSYS-BROCO-BRCRR | PM0004 Brake Oil Cooler RH Rear | 91736 | 3709 | 3500
500080021 | CLB-MP-SUPP-PM0004-BRKSYS-BROCO-BRCLR | PM0004 Brake Oil Cooler LH Rear | 91736 | 25890 | 3500
500080020 | CLB-MP-SUPP-PM0004-BRKSYS-BRVLV | PM0004 Valve Brake | 91736 | 3709 | 3500
500080019 | CLB-MP-SUPP-PM0004-BRKSYS-BRPMP-HYFPP | PM0004 Pump Brake Cooling | 91736 | 186 | 3500
500080018 | CLB-MP-SUPP-PM0004-BRKSYS-BRPMP-PRKPP | PM0004 Pump Park Brake Release | 91736 | 3709 | 3500
500080017 | CLB-MP-SUPP-PM0004-BRKSYS-BRPMP | PM0004 Pump Brake | 91736 | 3709 | 3500
500080016 | CLB-MP-SUPP-PM0004-FDRSYS-AXLEC-OILCO | PM0004 Axle Oil Cooler Core | 91736 | 25890 | 3500
500080015 | CLB-MP-SUPP-PM0004-FDRSYS-AXLEC-HYPUM | PM0004 Axle Lube Pump | 91736 | 91736 | 3500
500080014 | CLB-MP-SUPP-PM0004-FDRSYS-AXLEC-MTFAN | PM0004 Axle Oil Cooler Fan Motor | 91736 | 25890 | 3500
500080013 | CLB-MP-SUPP-PM0004-FDRSYS-FDRVE-FDRRH | PM0004 Final Drive R/H | 91736 | 17196 | 3500
500080012 | CLB-MP-SUPP-PM0004-FDRSYS-FDRVE-FDRLH | PM0004 Final Drive L/H | 91736 | 6621 | 3500
500080011 | CLB-MP-SUPP-PM0004-FDRSYS-DIFFL | PM0004 Differential | 91736 | 8412 | 3500
500080010 | CLB-MP-SUPP-PM0004-FDRSYS-DRSHT | PM0004 Drive Shaft, Transmission | 91736 | 12901 | 3500
500080009 | CLB-MP-SUPP-PM0004-TRNSYS-TROLC | PM0004 Oil Cooler Transmission | 91736 | 8412 | 3500
500080008 | CLB-MP-SUPP-PM0004-TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 91736 | 13342 | 3500
500080007 | CLB-MP-SUPP-PM0004-TRNSYS-TRPMP-TMCPP | PM0004 Pump Transmission & T/C | 91736 | 13390 | 3500
500080006 | CLB-MP-SUPP-PM0004-TRNSYS-TRANS | PM0004 Transmission | 91736 | 8412 | 3500
500080005 | CLB-MP-SUPP-PM0004-TRNSYS-TRQUE | PM0004 Torque Converter | 91736 | 13390 | 3500
500080003 | CLB-MP-SUPP-PM0004-ELCTLV-START-STMUP | LL002 Starter Motor Upper | 91736 | 1450 | 3500
500080002 | CLB-MP-SUPP-PM0004-ELCTLV-CHARG-ALTER | PM0004 Alternator 24V | 91736 | 8891 | 3500
500080001 | CLB-MP-SUPP-PM0004-ENGINE-PMPDR-DRSHT | PM0004 Drive Shaft, Pump Drive | 91736 | 15427 | 3500
500080000 | CLB-MP-SUPP-PM0004-ENGINE-PMPDR | PM0004 Pump Drive | 91736 | 5405 | 3500
500079999 | CLB-MP-SUPP-PM0004-ENGINE-FUSYS-FUINJ | PM0004 Fuel Injectors | 91736 | 1450 | 3500
500079998 | CLB-MP-SUPP-PM0004-ENGINE-FUSYS-FULTP | PM0004 Fuel Transfer Pump | 91736 | 1450 | 3500
500079997 | CLB-MP-SUPP-PM0004-ENGINE-INTEX-AFTER | PM0004 Aftercooler | 91736 | 91736 | 3500
500079996 | CLB-MP-SUPP-PM0004-ENGINE-INTEX-TBORR | PM0004 Turbocharger RH Rear | 91736 | 1190 | 3500
500079995 | CLB-MP-SUPP-PM0004-ENGINE-INTEX-TBORF | PM0004 Turbocharger RH Front | 91736 | 1190 | 3500
500079994 | CLB-MP-SUPP-PM0004-ENGINE-INTEX-TBOLR | PM0004 Turbocharger LH Rear | 91736 | 1190 | 3500
500079993 | CLB-MP-SUPP-PM0004-ENGINE-INTEX-TBOLF | PM0004 Turbocharger LH Front | 91736 | 1190 | 3500
500079992 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-CSHLF | PM0004 Cooling System Hoses | 91736 | 15967 | 3500
500079991 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-THERM | PM0004 Thermostats/Regulators | 91736 | 1450 | 3500
500079990 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-BELTS | PM0004 Fan Belts Engine | 91736 | 1450 | 3500
500079989 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-ACWEP | PM0004 Water Pump Aftercooler | 91736 | 1450 | 3500
500079988 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-COFAN | PM0004 Fan Cooling System | 91736 | 8409 | 3500
500079987 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-RADTR | PM0004 Radiator Engine | 91736 | 12562 | 3500
500079986 | CLB-MP-SUPP-PM0004-ENGINE-COSYS-WTRPP | PM0004 Water Pump Engine | 91736 | 1450 | 3500
500079985 | CLB-MP-SUPP-PM0004-ENGINE-LUBSY-ENOLC | PM0004 Oil Cooler Engine | 91736 | 1450 | 3500
500079984 | CLB-MP-SUPP-PM0004-ENGINE-LUBSY-PREPP | PM0004 Oil Pump Prelube | 91736 | 1450 | 3500
500079983 | CLB-MP-SUPP-PM0004-ENGINE-LUBSY-OILPP | PM0004 Oil Pump Engine | 91736 | 91736 | 3500
500079982 | CLB-MP-SUPP-PM0004-ENGINE-COMPR | PM0004 Air Compressor | 91736 | 1450 | 3500
500079981 | CLB-MP-SUPP-PM0004-ENGINE | PM0004 Engine Assembly | 91736 | 13390 | 3500
500077256 | CLB-MP-SUPP-PM0004 | PM0004 Lube & Mechanical Services | 91736 | 91736 | 3500
500077254 | CLB-MP-SUPP-PM0004 | Caterpillar 793C Prime Mover PM0004 | 91736 | 91736 | 3500
500160307 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITRH | Air Tank Right | 51345 | 51345 | 7500
500160306 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK-AITLH | Air Tank Left | 51345 | 51345 | 7500
500147348 | CLB-MP-HAUL-DT225 -STRSYS-STACC | Steering Accumulator Rear | 28044 | 28044 | 7500
500147347 | CLB-MP-HAUL-DT225 -STRSYS-STACC | Steering Accumulator Middle | 28044 | 28044 | 7500
500147346 | CLB-MP-HAUL-DT225 -STRSYS-STACC | Steering Accumulator Front | 28044 | 28044 | 7500
500118589 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-AFRME | A Frame Housing | 51346 | 28044 | 7500
500117957 | CLB-MP-HAUL-DT225 -ELCTLV-LIGHT | Lighting Low Voltage | 51346 | 45155 | 7500
500117917 | CLB-MP-HAUL-DT225 -ELCTLV-HARNS | Electrical Harness | 51346 | 45155 | 7500
500117877 | CLB-MP-HAUL-DT225 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 51346 | 45155 | 7500
500117441 | CLB-MP-HAUL-DT225 -ELCTLV-LIGHT-AHSYS | AHS Lights | 51346 | 45155 | 7500
500117321 | CLB-MP-HAUL-DT225 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 51346 | 45155 | 7500
500111251 | CLB-MP-HAUL-DT225 -STRUCT-RAXHO | Rear Axle Housing | 51346 | 51346 | 7500
500110573 | CLB-MP-HAUL-DT225 -GRSYST | Grease Lubrication System | 51346 | 13495 | 7500
500107637 | CLB-MP-HAUL-DT225 -ELCTLV-START-STMLO | DT225 Starter Motor Lower | 51346 | 6222 | 7500
500107636 | CLB-MP-HAUL-DT225 -ELCTLV-START-STMUP | DT225 Starter Motor Upper | 51346 | 6222 | 7500
500102823 | CLB-MP-HAUL-DT225 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 51346 | 16991 | 7500
500101424 | CLB-MP-HAUL-DT225 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 51346 | 6220 | 7500
500101423 | CLB-MP-HAUL-DT225 -TRNSYS-TRQUE | Torque Converter | 51346 | 6222 | 7500
500101422 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 51346 | 6222 | 7500
500101421 | CLB-MP-HAUL-DT225 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 51346 | 6222 | 7500
500101420 | CLB-MP-HAUL-DT225 -TRNSYS-TROLC | Oil Cooler Transmission | 51346 | 6222 | 7500
500101419 | CLB-MP-HAUL-DT225 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 51346 | 6220 | 7500
500101418 | CLB-MP-HAUL-DT225 -TRNSYS-TRANS | Transmission | 51346 | 6222 | 7500
500101417 | CLB-MP-HAUL-DT225 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 51346 | 28044 | 7500
500101415 | CLB-MP-HAUL-DT225 -STRUCT-TRAYS | Tray | 51346 | 18989 | 7500
500101414 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 51346 | 6222 | 7500
500101413 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 51346 | 6222 | 7500
500101412 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 51346 | 6222 | 7500
500101411 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 51346 | 6222 | 7500
500101410 | CLB-MP-HAUL-DT225 -STRUCT-SUSPN | Suspension Service | 51346 | 10798 | 7500
500101409 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-TAGLK | Tag Link | 51346 | 6222 | 7500
500101408 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-ELECT | Chassis Electrical System | 51346 | 51346 | 7500
500101406 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-SEATS | Operators Seat | 51346 | 36201 | 7500
500101405 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-SBELT | Seat Belt | 51346 | 51346 | 7500
500101404 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-ELECT | Cabin Electrical System | 51346 | 51346 | 7500
500101403 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 51346 | 51346 | 7500
500101402 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-AIRCN | Air Conditioning System | 51346 | 576 | 7500
500101401 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 51346 | 51346 | 7500
500101400 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 51346 | 51346 | 7500
500101399 | CLB-MP-HAUL-DT225 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 51346 | 51346 | 7500
500101398 | CLB-MP-HAUL-DT225 -STRUCT-CABIN | Operators Cabin | 51346 | 51346 | 7500
500101397 | CLB-MP-HAUL-DT225 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 51346 | 9297 | 7500
500101396 | CLB-MP-HAUL-DT225 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 51346 | 1218 | 7500
500101395 | CLB-MP-HAUL-DT225 -STRUCT-CHASS-AFRME | A Frame Bearing | 51346 | 6222 | 7500
500101393 | CLB-MP-HAUL-DT225 -STRSYS-STTNK | Tank Steering | 51346 | 51346 | 7500
500101392 | CLB-MP-HAUL-DT225 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 51346 | 1914 | 7500
500101391 | CLB-MP-HAUL-DT225 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 51346 | 1914 | 7500
500101390 | CLB-MP-HAUL-DT225 -STRSYS-STPMP | Pump Steering | 51346 | 576 | 7500
500101389 | CLB-MP-HAUL-DT225 -STRSYS-STLTR-STBST | Ball Studs | 51346 | 51346 | 7500
500101388 | CLB-MP-HAUL-DT225 -STRSYS-STLTR | Steering Linkages and Tie Rods | 51346 | 13495 | 7500
500101387 | CLB-MP-HAUL-DT225 -STRSYS-STHMU | Steering HMU | 51346 | 576 | 7500
500101386 | CLB-MP-HAUL-DT225 -STRSYS-STHLF-STRHO | Steering System Hoses | 51346 | 6220 | 7500
500101385 | CLB-MP-HAUL-DT225 -STRSYS-STCON-STWHL | Steering Wheel | 51346 | 51346 | 7500
500101384 | CLB-MP-HAUL-DT225 -STRSYS-STCON-STCOL | Steering Column | 51346 | 51346 | 7500
500101383 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 51346 | 28044 | 7500
500101382 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 51346 | 28044 | 7500
500101381 | CLB-MP-HAUL-DT225 -STRSYS-STACC-SACCF | Accumulator Steering Front | 51346 | 28044 | 7500
500101379 | CLB-MP-HAUL-DT225 -PNEUMC-PNTNK | No Not Use | 51346 | 51346 | 7500
500101378 | CLB-MP-HAUL-DT225 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 51346 | 51346 | 7500
500101377 | CLB-MP-HAUL-DT225 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 51346 | 51346 | 7500
500101376 | CLB-MP-HAUL-DT225 -PNEUMC-AIRDR | Air Drier | 51346 | 28044 | 7500
500101375 | CLB-MP-HAUL-DT225 -MANGMT-UMTRN | Power Train Management System | 51346 | 51346 | 7500
500101374 | CLB-MP-HAUL-DT225 -MANGMT-UMMMC | Mine Monitoring and Control | 51346 | 51346 | 7500
500101373 | CLB-MP-HAUL-DT225 -MANGMT-UMENG | Engine Management System | 51346 | 51346 | 7500
500101372 | CLB-MP-HAUL-DT225 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 51346 | 51346 | 7500
500101371 | CLB-MP-HAUL-DT225 -HYDSYS-HOVLV | Valve Hoist | 51346 | 6220 | 7500
500101370 | CLB-MP-HAUL-DT225 -HYDSYS-HOPMP | Pump Hoist | 51346 | 1225 | 7500
500101369 | CLB-MP-HAUL-DT225 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 51346 | 16098 | 7500
500101368 | CLB-MP-HAUL-DT225 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 51346 | 16991 | 7500
500101367 | CLB-MP-HAUL-DT225 -HYDSYS-HDTNK | Tank Hydraulic | 51346 | 51346 | 7500
500101366 | CLB-MP-HAUL-DT225 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 51346 | 51346 | 7500
500101365 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 51346 | 6220 | 7500
500101364 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 51346 | 6220 | 7500
500101363 | CLB-MP-HAUL-DT225 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 51346 | 6220 | 7500
500101362 | CLB-MP-HAUL-DT225 -HYDSYS | Hydraulic System | 51346 | 51346 | 7500
500101361 | CLB-MP-HAUL-DT225 -GRSYST-GRTNK | Auto Lube Resevoir | 51346 | 51346 | 7500
500101360 | CLB-MP-HAUL-DT225 -GRSYST-GRINJ | Auto Lube Injectors | 51346 | 51346 | 7500
500101359 | CLB-MP-HAUL-DT225 -GRSYST-ALCON | Auto Lube Controller | 51346 | 51346 | 7500
500101358 | CLB-MP-HAUL-DT225 -GRSYST-ALBPP | Auto Lube Pump | 51346 | 23582 | 7500
500101357 | CLB-MP-HAUL-DT225 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 51346 | 16093 | 7500
500101356 | CLB-MP-HAUL-DT225 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 51346 | 15978 | 7500
500101355 | CLB-MP-HAUL-DT225 -FDRSYS-DRSHT | Transmission Drive Shaft | 51346 | 6222 | 7500
500101354 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 51346 | 28044 | 7500
500101353 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 51346 | 28044 | 7500
500101352 | CLB-MP-HAUL-DT225 -FDRSYS-DRLAX | Drive Line Axles | 51346 | 51346 | 7500
500101351 | CLB-MP-HAUL-DT225 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 51346 | 6220 | 7500
500101350 | CLB-MP-HAUL-DT225 -FDRSYS-DIFFL | Differential | 51346 | 6222 | 7500
500101349 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 51346 | 51346 | 7500
500101348 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 51346 | 6222 | 7500
500101347 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 51346 | 576 | 7500
500101346 | CLB-MP-HAUL-DT225 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 51346 | 6222 | 7500
500101345 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 51346 | 6222 | 7500
500101344 | CLB-MP-HAUL-DT225 -ENGINE-PMPDR | Pump Drive | 51346 | 6222 | 7500
500101343 | CLB-MP-HAUL-DT225 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 51346 | 6222 | 7500
500101342 | CLB-MP-HAUL-DT225 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 51346 | 6222 | 7500
500101341 | CLB-MP-HAUL-DT225 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 51346 | 6222 | 7500
500101340 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 51346 | 6222 | 7500
500101339 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 51346 | 6222 | 7500
500101338 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 51346 | 6222 | 7500
500101337 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 51346 | 6222 | 7500
500101336 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-EXHST | Exhaust System | 51346 | 51346 | 7500
500101335 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-AIRFL | Air Filtration System | 51346 | 51346 | 7500
500101334 | CLB-MP-HAUL-DT225 -ENGINE-INTEX-AFTER | Aftercooler | 51346 | 51346 | 7500
500101333 | CLB-MP-HAUL-DT225 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 51346 | 6222 | 7500
500101332 | CLB-MP-HAUL-DT225 -ENGINE-FUSYS-FULTK | Fuel Tank | 51346 | 51346 | 7500
500101331 | CLB-MP-HAUL-DT225 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 51346 | 6222 | 7500
500101330 | CLB-MP-HAUL-DT225 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 51346 | 6222 | 7500
500101329 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-WTRPP | Water Pump Engine | 51346 | 6222 | 7500
500101328 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-THERM | Thermostats/Regulators | 51346 | 6222 | 7500
500101327 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-RADTR | Coolant Engine | 51346 | 28044 | 7400
500101326 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-RADTR | Radiator Engine | 51346 | 14140 | 7500
500101325 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-COFAN | Fan Cooling System | 51346 | 10800 | 7500
500101324 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-BELTS | Fan Belts Engine | 51346 | 51346 | 7500
500101323 | CLB-MP-HAUL-DT225 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 51346 | 6222 | 7500
500101322 | CLB-MP-HAUL-DT225 -ENGINE-COMPR | Air Compressor | 51346 | 6222 | 7500
500101320 | CLB-MP-HAUL-DT225 -ENGINE | Engine Assembly Caterpillar 3516B | 51346 | 6222 | 7500
500101319 | CLB-MP-HAUL-DT225 -ELCTLV-CHARG-BATTY | Batteries | 51346 | 51346 | 7500
500101318 | CLB-MP-HAUL-DT225 -ELCTLV-CHARG-ALTER | Alternator 24V | 51346 | 16991 | 7500
500101317 | CLB-MP-HAUL-DT225 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 51346 | 51346 | 7500
500101316 | CLB-MP-HAUL-DT225 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 51346 | 51346 | 7500
500101315 | CLB-MP-HAUL-DT225 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 51346 | 51346 | 7500
500101314 | CLB-MP-HAUL-DT225 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 51346 | 51346 | 7500
500101313 | CLB-MP-HAUL-DT225 -BRKSYS-SRVBK | Service Brake | 51346 | 51346 | 7500
500101312 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 51346 | 16991 | 7500
500101311 | CLB-MP-HAUL-DT225 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 51346 | 16991 | 7500
500101310 | CLB-MP-HAUL-DT225 -BRKSYS-PRKPP | Pump Park Brake Release | 51346 | 51346 | 7500
500101309 | CLB-MP-HAUL-DT225 -BRKSYS-MERTR | Mechanical Retarder | 51346 | 51346 | 7500
500101308 | CLB-MP-HAUL-DT225 -BRKSYS-HYFPP | Pump Brake Control | 51346 | 6222 | 7500
500101307 | CLB-MP-HAUL-DT225 -BRKSYS-BRVTR | Valve Brake Treadle | 51346 | 51346 | 7500
500101306 | CLB-MP-HAUL-DT225 -BRKSYS-BRVRL | Brake Relay Valve | 51346 | 6220 | 7500
500101305 | CLB-MP-HAUL-DT225 -BRKSYS-BRVLV | Valve Brake | 51346 | 6220 | 7500
500101304 | CLB-MP-HAUL-DT225 -BRKSYS-BRPMP | Pump Brake | 51346 | 15512 | 7500
500101303 | CLB-MP-HAUL-DT225 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 51346 | 51346 | 7500
500101302 | CLB-MP-HAUL-DT225 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 51346 | 6222 | 7500
500101301 | CLB-MP-HAUL-DT225 -BRKSYS-BROCO | Brake Oil Cooler | 51346 | 51346 | 7500
500101300 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 51346 | 6220 | 7500
500101299 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 51346 | 6220 | 7500
500101298 | CLB-MP-HAUL-DT225 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 51346 | 28044 | 7500
500101297 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 51346 | 6222 | 7500
500101296 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 51346 | 6222 | 7500
500101295 | CLB-MP-HAUL-DT225 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 51346 | 6222 | 7500
500101294 | CLB-MP-HAUL-DT225 -BRKSYS-BACCM | Brake Accumulator | 51346 | 28044 | 7500
500101293 | CLB-MP-HAUL-DT225 | DT225 Lubrication & Mechanical Services | 51346 | 51346 | 7500
500101292 | CLB-MP-HAUL-DT225 | Caterpillar 789D Haul Truck DT225 | 51346 | 51346 | 7500
500160305 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITRH | Air Tank Right | 49299 | 49299 | 7500
500160304 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK-AITLH | Air Tank Left | 49299 | 49299 | 7500
500147344 | CLB-MP-HAUL-DT224 -STRSYS-STACC | Steering Accumulator Rear | 26914 | 26914 | 7500
500147343 | CLB-MP-HAUL-DT224 -STRSYS-STACC | Steering Accumulator Middle | 26914 | 26914 | 7500
500147342 | CLB-MP-HAUL-DT224 -STRSYS-STACC | Steering Accumulator Front | 26914 | 26914 | 7500
500118588 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-AFRME | A Frame Housing | 49737 | 49737 | 7500
500117956 | CLB-MP-HAUL-DT224 -ELCTLV-LIGHT | Lighting Low Voltage | 49737 | 43586 | 7500
500117916 | CLB-MP-HAUL-DT224 -ELCTLV-HARNS | Electrical Harness | 49737 | 43586 | 7500
500117876 | CLB-MP-HAUL-DT224 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 49737 | 43586 | 7500
500117440 | CLB-MP-HAUL-DT224 -ELCTLV-LIGHT-AHSYS | AHS Lights | 49737 | 43586 | 7500
500117320 | CLB-MP-HAUL-DT224 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 49737 | 43586 | 7500
500111250 | CLB-MP-HAUL-DT224 -STRUCT-RAXHO | Rear Axle Housing | 49737 | 26914 | 7500
500110572 | CLB-MP-HAUL-DT224 -GRSYST | Grease Lubrication System | 49737 | 29818 | 7500
500107635 | CLB-MP-HAUL-DT224 -ELCTLV-START-STMLO | DT224 Starter Motor Lower | 49737 | 4881 | 7500
500107634 | CLB-MP-HAUL-DT224 -ELCTLV-START-STMUP | DT224 Starter Motor Upper | 49737 | 4881 | 7500
500102822 | CLB-MP-HAUL-DT224 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 49737 | 15864 | 7500
500101291 | CLB-MP-HAUL-DT224 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 49737 | 26914 | 7500
500101290 | CLB-MP-HAUL-DT224 -TRNSYS-TRQUE | Torque Converter | 49737 | 4881 | 7500
500101289 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 49737 | 4881 | 7500
500101288 | CLB-MP-HAUL-DT224 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 49737 | 4881 | 7500
500101287 | CLB-MP-HAUL-DT224 -TRNSYS-TROLC | Oil Cooler Transmission | 49737 | 26914 | 7500
500101286 | CLB-MP-HAUL-DT224 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 49737 | 26914 | 7500
500101285 | CLB-MP-HAUL-DT224 -TRNSYS-TRANS | Transmission | 49737 | 4881 | 7500
500101284 | CLB-MP-HAUL-DT224 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 49737 | 49737 | 7500
500101282 | CLB-MP-HAUL-DT224 -STRUCT-TRAYS | Tray | 49737 | 20498 | 7500
500101281 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 49737 | 4881 | 7500
500101280 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 49737 | 14457 | 7500
500101279 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 49737 | 4881 | 7500
500101278 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 49737 | 4881 | 7500
500101277 | CLB-MP-HAUL-DT224 -STRUCT-SUSPN | Suspension Service | 49737 | 26842 | 7500
500101276 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-TAGLK | Tag Link | 49737 | 26914 | 7500
500101275 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-ELECT | Chassis Electrical System | 49737 | 49737 | 7500
500101274 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-AFRME | A Frame | 49428 | 49428 | 7200
500101273 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-SEATS | Operators Seat | 49737 | 19248 | 7500
500101272 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-SBELT | Seat Belt | 49737 | 49737 | 7500
500101271 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-ELECT | Cabin Electrical System | 49737 | 49737 | 7500
500101270 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 49737 | 49737 | 7500
500101269 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-AIRCN | Air Conditioning System | 49737 | 9540 | 7500
500101268 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 49737 | 49737 | 7500
500101267 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 49737 | 49737 | 7500
500101266 | CLB-MP-HAUL-DT224 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 49737 | 49737 | 7500
500101265 | CLB-MP-HAUL-DT224 -STRUCT-CABIN | Operators Cabin | 49737 | 49737 | 7500
500101264 | CLB-MP-HAUL-DT224 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 49737 | 14457 | 7500
500101263 | CLB-MP-HAUL-DT224 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 49737 | 4881 | 7500
500101262 | CLB-MP-HAUL-DT224 -STRUCT-CHASS-AFRME | A Frame Bearing | 49737 | 39563 | 7500
500101260 | CLB-MP-HAUL-DT224 -STRSYS-STTNK | Tank Steering | 49737 | 49737 | 7500
500101259 | CLB-MP-HAUL-DT224 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 49737 | 7563 | 7500
500101258 | CLB-MP-HAUL-DT224 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 49737 | 7573 | 7500
500101257 | CLB-MP-HAUL-DT224 -STRSYS-STPMP | Pump Steering | 49737 | 4881 | 7500
500101256 | CLB-MP-HAUL-DT224 -STRSYS-STLTR-STBST | Ball Studs | 49737 | 49737 | 7500
500101255 | CLB-MP-HAUL-DT224 -STRSYS-STLTR | Steering Linkages and Tie Rods | 49737 | 11104 | 7500
500101254 | CLB-MP-HAUL-DT224 -STRSYS-STHMU | Steering HMU | 49737 | 19248 | 7500
500101253 | CLB-MP-HAUL-DT224 -STRSYS-STHLF-STRHO | Steering System Hoses | 49737 | 26914 | 7500
500101252 | CLB-MP-HAUL-DT224 -STRSYS-STCON-STWHL | Steering Wheel | 49737 | 49737 | 7500
500101251 | CLB-MP-HAUL-DT224 -STRSYS-STCON-STCOL | Steering Column | 49737 | 49737 | 7500
500101250 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 49737 | 26914 | 7500
500101249 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 49737 | 26914 | 7500
500101248 | CLB-MP-HAUL-DT224 -STRSYS-STACC-SACCF | Accumulator Steering Front | 49737 | 26914 | 7500
500101246 | CLB-MP-HAUL-DT224 -PNEUMC-PNTNK | No Not Use | 49737 | 49737 | 7500
500101245 | CLB-MP-HAUL-DT224 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 49737 | 49737 | 7500
500101244 | CLB-MP-HAUL-DT224 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 49737 | 49737 | 7500
500101243 | CLB-MP-HAUL-DT224 -PNEUMC-AIRDR | Air Drier | 49737 | 26914 | 7500
500101242 | CLB-MP-HAUL-DT224 -MANGMT-UMTRN | Power Train Management System | 49737 | 49737 | 7500
500101241 | CLB-MP-HAUL-DT224 -MANGMT-UMMMC | Mine Monitoring and Control | 49737 | 49737 | 7500
500101240 | CLB-MP-HAUL-DT224 -MANGMT-UMENG | Engine Management System | 49737 | 49737 | 7500
500101239 | CLB-MP-HAUL-DT224 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 49737 | 26914 | 7500
500101238 | CLB-MP-HAUL-DT224 -HYDSYS-HOVLV | Valve Hoist | 49737 | 4881 | 7500
500101237 | CLB-MP-HAUL-DT224 -HYDSYS-HOPMP | Pump Hoist | 49737 | 4881 | 7500
500101236 | CLB-MP-HAUL-DT224 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 49737 | 11104 | 7500
500101235 | CLB-MP-HAUL-DT224 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 49737 | 26795 | 7500
500101234 | CLB-MP-HAUL-DT224 -HYDSYS-HDTNK | Tank Hydraulic | 49737 | 49737 | 7500
500101233 | CLB-MP-HAUL-DT224 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 49737 | 49737 | 7500
500101232 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 49737 | 26914 | 7500
500101231 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 49737 | 26914 | 7500
500101230 | CLB-MP-HAUL-DT224 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 49737 | 26914 | 7500
500101229 | CLB-MP-HAUL-DT224 -HYDSYS | Hydraulic System | 49737 | 49737 | 7500
500101228 | CLB-MP-HAUL-DT224 -GRSYST-GRTNK | Auto Lube Resevoir | 49737 | 49737 | 7500
500101227 | CLB-MP-HAUL-DT224 -GRSYST-GRINJ | Auto Lube Injectors | 49737 | 49737 | 7500
500101226 | CLB-MP-HAUL-DT224 -GRSYST-ALCON | Auto Lube Controller | 49737 | 49737 | 7500
500101225 | CLB-MP-HAUL-DT224 -GRSYST-ALBPP | Auto Lube Pump | 49737 | 49737 | 7500
500101224 | CLB-MP-HAUL-DT224 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 49737 | 16528 | 7500
500101223 | CLB-MP-HAUL-DT224 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 49737 | 16528 | 7500
500101222 | CLB-MP-HAUL-DT224 -FDRSYS-DRSHT | Transmission Drive Shaft | 49737 | 26914 | 7500
500101221 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 49737 | 26914 | 7500
500101220 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 49737 | 26914 | 7500
500101219 | CLB-MP-HAUL-DT224 -FDRSYS-DRLAX | Drive Line Axles | 49737 | 49737 | 7500
500101218 | CLB-MP-HAUL-DT224 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 49737 | 26914 | 7500
500101217 | CLB-MP-HAUL-DT224 -FDRSYS-DIFFL | Differential | 49737 | 4881 | 7500
500101216 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 49737 | 49737 | 7500
500101215 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 49737 | 4881 | 7500
500101214 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 49737 | 49737 | 7500
500101213 | CLB-MP-HAUL-DT224 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 49737 | 4881 | 7500
500101212 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 49737 | 15864 | 7500
500101211 | CLB-MP-HAUL-DT224 -ENGINE-PMPDR | Pump Drive | 49737 | 4881 | 7500
500101210 | CLB-MP-HAUL-DT224 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 49737 | 4881 | 7500
500101209 | CLB-MP-HAUL-DT224 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 49737 | 45722 | 7500
500101208 | CLB-MP-HAUL-DT224 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 49737 | 45722 | 7500
500101207 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 49737 | 4881 | 7500
500101206 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 49737 | 4881 | 7500
500101205 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 49737 | 4881 | 7500
500101204 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 49737 | 4881 | 7500
500101203 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-EXHST | Exhaust System | 49737 | 49737 | 7500
500101202 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-AIRFL | Air Filtration System | 49737 | 49737 | 7500
500101201 | CLB-MP-HAUL-DT224 -ENGINE-INTEX-AFTER | Aftercooler | 49737 | 45722 | 7500
500101200 | CLB-MP-HAUL-DT224 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 49737 | 4881 | 7500
500101199 | CLB-MP-HAUL-DT224 -ENGINE-FUSYS-FULTK | Fuel Tank | 49737 | 28613 | 7500
500101198 | CLB-MP-HAUL-DT224 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 49737 | 4881 | 7500
500101197 | CLB-MP-HAUL-DT224 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 49737 | 4881 | 7500
500101196 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-WTRPP | Water Pump Engine | 49737 | 4881 | 7500
500101195 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-THERM | Thermostats/Regulators | 49737 | 4881 | 7500
500101194 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-RADTR | Coolant Engine | 49737 | 26914 | 7400
500101193 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-RADTR | Radiator Engine | 49737 | 4881 | 7500
500101192 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-COFAN | Fan Cooling System | 49737 | 4881 | 7500
500101191 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-BELTS | Fan Belts Engine | 49737 | 45722 | 7500
500101190 | CLB-MP-HAUL-DT224 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 49737 | 4881 | 7500
500101189 | CLB-MP-HAUL-DT224 -ENGINE-COMPR | Air Compressor | 49737 | 4881 | 7500
500101187 | CLB-MP-HAUL-DT224 -ENGINE | Engine Assembly Caterpillar 3516B | 49737 | 4881 | 7500
500101186 | CLB-MP-HAUL-DT224 -ELCTLV-CHARG-BATTY | Batteries | 49737 | 26137 | 7500
500101185 | CLB-MP-HAUL-DT224 -ELCTLV-CHARG-ALTER | Alternator 24V | 49737 | 4881 | 7500
500101184 | CLB-MP-HAUL-DT224 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 49737 | 49737 | 7500
500101183 | CLB-MP-HAUL-DT224 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 49737 | 49737 | 7500
500101182 | CLB-MP-HAUL-DT224 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 49737 | 49737 | 7500
500101181 | CLB-MP-HAUL-DT224 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 49737 | 49737 | 7500
500101180 | CLB-MP-HAUL-DT224 -BRKSYS-SRVBK | Service Brake | 49737 | 49737 | 7500
500101179 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 49737 | 15155 | 7500
500101178 | CLB-MP-HAUL-DT224 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 49737 | 15864 | 7500
500101177 | CLB-MP-HAUL-DT224 -BRKSYS-PRKPP | Pump Park Brake Release | 49737 | 49737 | 7500
500101176 | CLB-MP-HAUL-DT224 -BRKSYS-MERTR | Mechanical Retarder | 49737 | 49737 | 7500
500101175 | CLB-MP-HAUL-DT224 -BRKSYS-HYFPP | Pump Brake Control | 49737 | 4881 | 7500
500101174 | CLB-MP-HAUL-DT224 -BRKSYS-BRVTR | Valve Brake Treadle | 49737 | 49737 | 7500
500101173 | CLB-MP-HAUL-DT224 -BRKSYS-BRVRL | Brake Relay Valve | 49737 | 15864 | 7500
500101172 | CLB-MP-HAUL-DT224 -BRKSYS-BRVLV | Valve Brake | 49737 | 26914 | 7500
500101171 | CLB-MP-HAUL-DT224 -BRKSYS-BRPMP | Pump Brake | 49737 | 49737 | 7500
500101170 | CLB-MP-HAUL-DT224 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 49737 | 4881 | 7500
500101169 | CLB-MP-HAUL-DT224 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 49737 | 4881 | 7500
500101168 | CLB-MP-HAUL-DT224 -BRKSYS-BROCO | Brake Oil Cooler | 49737 | 49737 | 7500
500101167 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 49737 | 26914 | 7500
500101166 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 49737 | 26914 | 7500
500101165 | CLB-MP-HAUL-DT224 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 49737 | 26914 | 7500
500101164 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 49737 | 26914 | 7500
500101163 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 49737 | 26914 | 7500
500101162 | CLB-MP-HAUL-DT224 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 49737 | 26914 | 7500
500101161 | CLB-MP-HAUL-DT224 -BRKSYS-BACCM | Brake Accumulator | 49737 | 26914 | 7500
500101150 | CLB-MP-HAUL-DT224 | DT224 Lubrication & Mechanical Services | 49737 | 49737 | 7500
500101149 | CLB-MP-HAUL-DT224 | Caterpillar 789D Haul Truck DT224 | 49737 | 49737 | 7500
500160303 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITRH | Air Tank Right | 92315 | 50047 | 7500
500160302 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK-AITLH | Air Tank Left | 92315 | 50047 | 7500
500147322 | CLB-MP-HAUL-DT200 -STRSYS-STACC | Steering Accumulator Rear | 23460 | 23460 | 7500
500147321 | CLB-MP-HAUL-DT200 -STRSYS-STACC | Steering Accumulator Middle | 23460 | 23460 | 7500
500147320 | CLB-MP-HAUL-DT200 -STRSYS-STACC | Steering Accumulator Front | 23460 | 23460 | 7500
500118579 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-AFRME | A Frame Housing | 92548 | 769 | 7500
500117955 | CLB-MP-HAUL-DT200 -ELCTLV-LIGHT | Lighting Low Voltage | 92548 | 45804 | 7500
500117915 | CLB-MP-HAUL-DT200 -ELCTLV-HARNS | Electrical Harness | 92548 | 45804 | 7500
500117875 | CLB-MP-HAUL-DT200 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 92548 | 45804 | 7500
500117439 | CLB-MP-HAUL-DT200 -ELCTLV-LIGHT-AHSYS | AHS Lights | 92548 | 45804 | 7500
500117319 | CLB-MP-HAUL-DT200 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 92548 | 45804 | 7500
500111241 | CLB-MP-HAUL-DT200 -STRUCT-RAXHO | Rear Axle Housing | 92548 | 766 | 7500
500110571 | CLB-MP-HAUL-DT200 -GRSYST | Grease Lubrication System | 92548 | 12596 | 7500
500102821 | CLB-MP-HAUL-DT200 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 92548 | 12117 | 7500
500100648 | CLB-MP-HAUL-DT200 -TRNSYS | DT200 Transmission System | 92548 | 47018 | 7500
500081425 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 92548 | 23460 | 7500
500081285 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 92548 | 23460 | 7500
500079458 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN | Suspension Service | 92548 | 769 | 7500
500078524 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 92548 | 769 | 7500
500078487 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 92548 | 769 | 7500
500061443 | CLB-MP-HAUL-DT200 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 92548 | 769 | 7500
500061413 | CLB-MP-HAUL-DT200 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 92548 | 769 | 7500
500061383 | CLB-MP-HAUL-DT200 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 92548 | 23460 | 7500
500061382 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-ELECT | Chassis Electrical System | 92548 | 23460 | 7500
500061381 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-ELECT | Cabin Electrical System | 92548 | 92548 | 7500
500061380 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 92548 | 23460 | 7500
500061379 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 92548 | 23460 | 7500
500061378 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 92548 | 23460 | 7500
500061377 | CLB-MP-HAUL-DT200 -STRSYS-STHLF-STRHO | Steering System Hoses | 92548 | 769 | 7500
500061376 | CLB-MP-HAUL-DT200 -STRSYS-STLTR-STBST | Ball Studs | 92548 | 92548 | 7500
500061375 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 92548 | 769 | 7500
500061374 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 92548 | 769 | 7500
500061373 | CLB-MP-HAUL-DT200 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 92548 | 769 | 7500
500061372 | CLB-MP-HAUL-DT200 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 92548 | 769 | 7500
500061371 | CLB-MP-HAUL-DT200 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 92548 | 769 | 7500
500061370 | CLB-MP-HAUL-DT200 -BRKSYS-BRVRL | Brake Relay Valve | 92548 | 769 | 7500
500061368 | CLB-MP-HAUL-DT200 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 92548 | 769 | 7500
500061367 | CLB-MP-HAUL-DT200 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 92548 | 769 | 7500
500060138 | CLB-MP-HAUL-DT200 -STRSYS-STTNK | Tank Steering | 92527 | 69272 | 7500
500053863 | CLB-MP-HAUL-DT200 -BRKSYS-BRVLV | Valve Brake | 92548 | 769 | 7500
500052532 | CLB-MP-HAUL-DT200 -MANGMT-UMMMC | Mine Monitoring and Control | 92548 | 92548 | 7500
500052531 | CLB-MP-HAUL-DT200 -MANGMT-UMTRN | Power Train Management System | 92548 | 92548 | 7500
500052530 | CLB-MP-HAUL-DT200 -MANGMT-UMENG | Engine Management System | 92548 | 92548 | 7500
500052529 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 92548 | 769 | 7500
500052528 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 92548 | 6572 | 7500
500052527 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 92548 | 8611 | 7500
500052526 | CLB-MP-HAUL-DT200 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 92548 | 7113 | 7500
500052523 | CLB-MP-HAUL-DT200 -STRUCT-TRAYS | Tray | 92548 | 27269 | 7500
500052522 | CLB-MP-HAUL-DT200 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 92548 | 8611 | 7500
500052521 | CLB-MP-HAUL-DT200 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 92548 | 769 | 7500
500052520 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-TAGLK | Tag Link | 92548 | 769 | 7500
500052519 | CLB-MP-HAUL-DT200 -STRUCT-CHASS-AFRME | A Frame Bearing | 92548 | 769 | 7500