500052518 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-SBELT | Seat Belt | 92548 | 53306 | 7500
500052517 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-SEATS | Operators Seat | 92548 | 769 | 7500
500052516 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 92548 | 92548 | 7500
500052515 | CLB-MP-HAUL-DT200 -STRUCT-CABIN-AIRCN | Air Conditioning System | 92548 | 12117 | 7500
500052514 | CLB-MP-HAUL-DT200 -STRUCT-CABIN | Operators Cabin | 92548 | 46665 | 7500
500052513 | CLB-MP-HAUL-DT200 -PNEUMC-START | Air Starter | 92548 | 769 | 7500
500052512 | CLB-MP-HAUL-DT200 -PNEUMC-AIRDR | Air Drier | 92548 | 13887 | 7500
500052511 | CLB-MP-HAUL-DT200 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 92548 | 92548 | 7500
500052510 | CLB-MP-HAUL-DT200 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 92548 | 92548 | 7500
500052509 | CLB-MP-HAUL-DT200 -PNEUMC-PNTNK | No Not Use | 92548 | 50280 | 7500
500052508 | CLB-MP-HAUL-DT200 -GRSYST-ALCON | Auto Lube Controller | 92548 | 92548 | 7500
500052507 | CLB-MP-HAUL-DT200 -GRSYST-ALBPP | Auto Lube Pump | 92548 | 69289 | 7500
500052506 | CLB-MP-HAUL-DT200 -GRSYST-GRTNK | Auto Lube Resevoir | 92548 | 92548 | 7500
500052505 | CLB-MP-HAUL-DT200 -GRSYST-GRINJ | Auto Lube Injectors | 92548 | 92548 | 7500
500052504 | CLB-MP-HAUL-DT200 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 92548 | 15383 | 7500
500052503 | CLB-MP-HAUL-DT200 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 92548 | 11475 | 7500
500052502 | CLB-MP-HAUL-DT200 -HYDSYS-HOVLV | Valve Hoist | 92548 | 32502 | 7500
500052501 | CLB-MP-HAUL-DT200 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 92548 | 92548 | 7500
500052500 | CLB-MP-HAUL-DT200 -HYDSYS-HDTNK | Tank Hydraulic | 92548 | 69293 | 7500
500052499 | CLB-MP-HAUL-DT200 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 92548 | 23460 | 7500
500052498 | CLB-MP-HAUL-DT200 -HYDSYS-HOPMP | Pump Hoist | 92548 | 10019 | 7500
500052497 | CLB-MP-HAUL-DT200 -HYDSYS | Hydraulic System | 92548 | 92548 | 7500
500052496 | CLB-MP-HAUL-DT200 -STRSYS-STCON-STCOL | Steering Column | 92548 | 46665 | 7500
500052495 | CLB-MP-HAUL-DT200 -STRSYS-STCON-STWHL | Steering Wheel | 92548 | 46665 | 7500
500052494 | CLB-MP-HAUL-DT200 -STRSYS-STLTR | Steering Linkages and Tie Rods | 92548 | 12596 | 7500
500052493 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 92548 | 769 | 7500
500052492 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 92548 | 769 | 7500
500052491 | CLB-MP-HAUL-DT200 -STRSYS-STACC-SACCF | Accumulator Steering Front | 92548 | 769 | 7500
500052490 | CLB-MP-HAUL-DT200 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 92548 | 7112 | 7500
500052489 | CLB-MP-HAUL-DT200 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 92548 | 769 | 7500
500052488 | CLB-MP-HAUL-DT200 -STRSYS-STVLV | Valve Steering | 92548 | 1651 | 7500
500052487 | CLB-MP-HAUL-DT200 -STRSYS-STHMU | Steering HMU | 92548 | 769 | 7500
500052486 | CLB-MP-HAUL-DT200 -STRSYS-STPMP | Pump Steering | 92548 | 7112 | 7500
500052485 | CLB-MP-HAUL-DT200 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 92548 | 12117 | 7500
500052484 | CLB-MP-HAUL-DT200 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 92548 | 12117 | 7500
500052483 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 92548 | 12116 | 7500
500052482 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 92548 | 769 | 7500
500052481 | CLB-MP-HAUL-DT200 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 92548 | 769 | 7500
500052480 | CLB-MP-HAUL-DT200 -BRKSYS-BACCM | Brake Accumulator | 92548 | 769 | 7500
500052479 | CLB-MP-HAUL-DT200 -BRKSYS-BROCO | Brake Oil Cooler | 92548 | 69293 | 7500
500052478 | CLB-MP-HAUL-DT200 -BRKSYS-MERTR | Mechanical Retarder | 92548 | 92548 | 7500
500052477 | CLB-MP-HAUL-DT200 -BRKSYS-BRVTR | Valve Brake Treadle | 92548 | 68124 | 7500
500052476 | CLB-MP-HAUL-DT200 -BRKSYS-HYFPP | Pump Brake Control | 92548 | 769 | 7500
500052475 | CLB-MP-HAUL-DT200 -BRKSYS-PRKPP | Pump Park Brake Release | 92548 | 92548 | 7500
500052474 | CLB-MP-HAUL-DT200 -BRKSYS-BRPMP | Pump Brake | 92548 | 92548 | 7500
500052473 | CLB-MP-HAUL-DT200 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 92548 | 69293 | 7500
500052472 | CLB-MP-HAUL-DT200 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 92548 | 69293 | 7500
500052471 | CLB-MP-HAUL-DT200 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 92548 | 69289 | 7500
500052470 | CLB-MP-HAUL-DT200 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 92548 | 69289 | 7500
500052469 | CLB-MP-HAUL-DT200 -BRKSYS-SRVBK | Service Brake | 92548 | 92548 | 7500
500052468 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 92548 | 92548 | 7500
500052467 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 92548 | 92548 | 7500
500052466 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 92548 | 12117 | 7500
500052465 | CLB-MP-HAUL-DT200 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 92548 | 769 | 7500
500052464 | CLB-MP-HAUL-DT200 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 92548 | 2191 | 7500
500052463 | CLB-MP-HAUL-DT200 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 92548 | 769 | 7500
500052462 | CLB-MP-HAUL-DT200 -FDRSYS-DRLAX | Drive Line Axles | 92548 | 92548 | 7500
500052461 | CLB-MP-HAUL-DT200 -FDRSYS-DIFFL | Differential | 92548 | 10020 | 7500
500052460 | CLB-MP-HAUL-DT200 -FDRSYS-DRSHT | Transmission Drive Shaft | 92548 | 769 | 7500
500052459 | CLB-MP-HAUL-DT200 -TRNSYS-TROLC | Oil Cooler Transmission | 92548 | 769 | 7500
500052458 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 92548 | 10019 | 7500
500052457 | CLB-MP-HAUL-DT200 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 92548 | 769 | 7500
500052456 | CLB-MP-HAUL-DT200 -TRNSYS-TRANS | Transmission | 92548 | 769 | 7500
500052455 | CLB-MP-HAUL-DT200 -TRNSYS-TRQUE | Torque Converter | 92548 | 769 | 7500
500052454 | CLB-MP-HAUL-DT200 -ELCTLV-CHARG-BATTY | Batteries | 92548 | 92548 | 7500
500052453 | CLB-MP-HAUL-DT200 -ELCTLV-CHARG-ALTER | Alternator 24V | 92548 | 769 | 7500
500052452 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 92548 | 769 | 7500
500052451 | CLB-MP-HAUL-DT200 -ENGINE-PMPDR | Pump Drive | 92548 | 4618 | 7500
500052450 | CLB-MP-HAUL-DT200 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 92548 | 769 | 7500
500052449 | CLB-MP-HAUL-DT200 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 92548 | 769 | 7500
500052448 | CLB-MP-HAUL-DT200 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 92548 | 769 | 7500
500052447 | CLB-MP-HAUL-DT200 -ENGINE-FUSYS-FULTK | Fuel Tank | 92548 | 23460 | 7500
500052446 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-EXHST | Exhaust System | 92548 | 92548 | 7500
500052445 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-AFTER | Aftercooler | 92548 | 69293 | 7500
500052444 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 92548 | 769 | 7500
500052443 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 92548 | 769 | 7500
500052442 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 92548 | 769 | 7500
500052441 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 92548 | 769 | 7500
500052440 | CLB-MP-HAUL-DT200 -ENGINE-INTEX-AIRFL | Air Filtration System | 92548 | 92548 | 7500
500052439 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-THERM | Thermostats/Regulators | 92548 | 769 | 7500
500052438 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-BELTS | Fan Belts Engine | 92548 | 92548 | 7500
500052437 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 92548 | 769 | 7500
500052436 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-COFAN | Fan Cooling System | 92548 | 769 | 7500
500052435 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-RADTR | Coolant Engine | 92548 | 29740 | 7400
500052434 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-RADTR | Radiator Engine | 92548 | 13736 | 7500
500052433 | CLB-MP-HAUL-DT200 -ENGINE-COSYS-WTRPP | Water Pump Engine | 92548 | 769 | 7500
500052432 | CLB-MP-HAUL-DT200 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 92548 | 69293 | 7500
500052431 | CLB-MP-HAUL-DT200 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 92548 | 769 | 7500
500052430 | CLB-MP-HAUL-DT200 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 92548 | 69293 | 7500
500052429 | CLB-MP-HAUL-DT200 -ENGINE-COMPR | Air Compressor | 92548 | 99 | 7500
500052427 | CLB-MP-HAUL-DT200 -ENGINE | Engine Assembly Caterpillar 3516B | 92548 | 769 | 7500
500052426 | CLB-MP-HAUL-DT200 | DT200 Lubrication & Mechanical Services | 92548 | 92548 | 7500
500052425 | CLB-MP-HAUL-DT200 | Caterpillar 789D Haul Truck DT200 | 92548 | 92548 | 7500
500160301 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITRH | Air Tank Right | 85715 | 85715 | 7500
500160300 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK-AITLH | Air Tank Left | 85715 | 85715 | 7500
500147318 | CLB-MP-HAUL-DT199 -STRSYS-STACC | Steering Accumulator Rear | 35622 | 35622 | 7500
500147317 | CLB-MP-HAUL-DT199 -STRSYS-STACC | Steering Accumulator Middle | 35622 | 35622 | 7500
500147316 | CLB-MP-HAUL-DT199 -STRSYS-STACC | Steering Accumulator Front | 35622 | 35622 | 7500
500118578 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-AFRME | A Frame Housing | 85978 | 35622 | 7500
500117954 | CLB-MP-HAUL-DT199 -ELCTLV-LIGHT | Lighting Low Voltage | 85978 | 54282 | 7500
500117914 | CLB-MP-HAUL-DT199 -ELCTLV-HARNS | Electrical Harness | 85978 | 54282 | 7500
500117874 | CLB-MP-HAUL-DT199 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85978 | 54282 | 7500
500117438 | CLB-MP-HAUL-DT199 -ELCTLV-LIGHT-AHSYS | AHS Lights | 85978 | 54282 | 7500
500117318 | CLB-MP-HAUL-DT199 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 85978 | 54282 | 7500
500111240 | CLB-MP-HAUL-DT199 -STRUCT-RAXHO | Rear Axle Housing | 85978 | 85978 | 7500
500110570 | CLB-MP-HAUL-DT199 -GRSYST | Grease Lubrication System | 85978 | 35622 | 7500
500102820 | CLB-MP-HAUL-DT199 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85978 | 1188 | 7500
500100647 | CLB-MP-HAUL-DT199 -TRNSYS | DT199 Transmission System | 85978 | 53888 | 7500
500081424 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85978 | 22478 | 7500
500081284 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85978 | 23065 | 7500
500079457 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN | Suspension Service | 85978 | 21221 | 7500
500078523 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 85978 | 12765 | 7500
500078486 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 85978 | 12765 | 7500
500061442 | CLB-MP-HAUL-DT199 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85978 | 12765 | 7500
500061412 | CLB-MP-HAUL-DT199 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85978 | 12765 | 7500
500061366 | CLB-MP-HAUL-DT199 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 85978 | 12765 | 7500
500061365 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-ELECT | Chassis Electrical System | 85978 | 35622 | 7500
500061364 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85978 | 85978 | 7500
500061363 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 85978 | 12765 | 7500
500061362 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 85978 | 12765 | 7500
500061361 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 85978 | 12765 | 7500
500061360 | CLB-MP-HAUL-DT199 -STRSYS-STHLF-STRHO | Steering System Hoses | 85978 | 12765 | 7500
500061359 | CLB-MP-HAUL-DT199 -STRSYS-STLTR-STBST | Ball Studs | 85978 | 85978 | 7500
500061358 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 85978 | 12765 | 7500
500061357 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 85978 | 12765 | 7500
500061356 | CLB-MP-HAUL-DT199 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 85978 | 12765 | 7500
500061355 | CLB-MP-HAUL-DT199 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85978 | 12765 | 7500
500061354 | CLB-MP-HAUL-DT199 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85978 | 12765 | 7500
500061353 | CLB-MP-HAUL-DT199 -BRKSYS-BRVRL | Brake Relay Valve | 85978 | 1188 | 7500
500061351 | CLB-MP-HAUL-DT199 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85978 | 12765 | 7500
500061350 | CLB-MP-HAUL-DT199 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85978 | 12765 | 7500
500060137 | CLB-MP-HAUL-DT199 -STRSYS-STTNK | Tank Steering | 85978 | 85978 | 7500
500053862 | CLB-MP-HAUL-DT199 -BRKSYS-BRVLV | Valve Brake | 85978 | 12765 | 7500
500052424 | CLB-MP-HAUL-DT199 -MANGMT-UMMMC | Mine Monitoring and Control | 85978 | 85978 | 7500
500052423 | CLB-MP-HAUL-DT199 -MANGMT-UMTRN | Power Train Management System | 85978 | 85978 | 7500
500052422 | CLB-MP-HAUL-DT199 -MANGMT-UMENG | Engine Management System | 85978 | 85978 | 7500
500052421 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85978 | 12765 | 7500
500052420 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85978 | 12765 | 7500
500052419 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85978 | 12765 | 7500
500052418 | CLB-MP-HAUL-DT199 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85978 | 12765 | 7500
500052415 | CLB-MP-HAUL-DT199 -STRUCT-TRAYS | Tray | 85978 | 24506 | 7500
500052414 | CLB-MP-HAUL-DT199 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85978 | 12765 | 7500
500052413 | CLB-MP-HAUL-DT199 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85978 | 2499 | 7500
500052412 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-TAGLK | Tag Link | 85978 | 24506 | 7500
500052411 | CLB-MP-HAUL-DT199 -STRUCT-CHASS-AFRME | A Frame Bearing | 85978 | 24506 | 7500
500052410 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-SBELT | Seat Belt | 85978 | 85978 | 7500
500052409 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-SEATS | Operators Seat | 85978 | 4036 | 7500
500052408 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85978 | 85978 | 7500
500052407 | CLB-MP-HAUL-DT199 -STRUCT-CABIN-AIRCN | Air Conditioning System | 85978 | 1188 | 7500
500052406 | CLB-MP-HAUL-DT199 -STRUCT-CABIN | Operators Cabin | 85978 | 12765 | 7500
500052405 | CLB-MP-HAUL-DT199 -PNEUMC-START | Air Starter | 85978 | 1188 | 7500
500052404 | CLB-MP-HAUL-DT199 -PNEUMC-AIRDR | Air Drier | 85978 | 12765 | 7500
500052403 | CLB-MP-HAUL-DT199 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 85978 | 85978 | 7500
500052402 | CLB-MP-HAUL-DT199 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 85978 | 85978 | 7500
500052401 | CLB-MP-HAUL-DT199 -PNEUMC-PNTNK | No Not Use | 85978 | 85978 | 7500
500052400 | CLB-MP-HAUL-DT199 -GRSYST-ALCON | Auto Lube Controller | 85978 | 85978 | 7500
500052399 | CLB-MP-HAUL-DT199 -GRSYST-ALBPP | Auto Lube Pump | 85978 | 85978 | 7500
500052398 | CLB-MP-HAUL-DT199 -GRSYST-GRTNK | Auto Lube Resevoir | 85978 | 85978 | 7500
500052397 | CLB-MP-HAUL-DT199 -GRSYST-GRINJ | Auto Lube Injectors | 85978 | 85978 | 7500
500052396 | CLB-MP-HAUL-DT199 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85978 | 12765 | 7500
500052395 | CLB-MP-HAUL-DT199 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85978 | 12765 | 7500
500052394 | CLB-MP-HAUL-DT199 -HYDSYS-HOVLV | Valve Hoist | 85978 | 35622 | 7500
500052393 | CLB-MP-HAUL-DT199 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85978 | 85978 | 7500
500052392 | CLB-MP-HAUL-DT199 -HYDSYS-HDTNK | Tank Hydraulic | 85978 | 85978 | 7500
500052391 | CLB-MP-HAUL-DT199 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 85978 | 12765 | 7500
500052390 | CLB-MP-HAUL-DT199 -HYDSYS-HOPMP | Pump Hoist | 85978 | 12765 | 7500
500052389 | CLB-MP-HAUL-DT199 -HYDSYS | Hydraulic System | 85978 | 85978 | 7500
500052388 | CLB-MP-HAUL-DT199 -STRSYS-STCON-STCOL | Steering Column | 85978 | 85978 | 7500
500052387 | CLB-MP-HAUL-DT199 -STRSYS-STCON-STWHL | Steering Wheel | 85978 | 85978 | 7500
500052386 | CLB-MP-HAUL-DT199 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85978 | 20031 | 7500
500052385 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85978 | 12765 | 7500
500052384 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85978 | 12765 | 7500
500052383 | CLB-MP-HAUL-DT199 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85978 | 12765 | 7500
500052382 | CLB-MP-HAUL-DT199 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85978 | 7443 | 7500
500052381 | CLB-MP-HAUL-DT199 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85978 | 1801 | 7500
500052380 | CLB-MP-HAUL-DT199 -STRSYS-STVLV | Valve Steering | 85978 | 12765 | 7500
500052379 | CLB-MP-HAUL-DT199 -STRSYS-STHMU | Steering HMU | 85978 | 20031 | 7500
500052378 | CLB-MP-HAUL-DT199 -STRSYS-STPMP | Pump Steering | 85978 | 20031 | 7500
500052377 | CLB-MP-HAUL-DT199 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85978 | 12765 | 7500
500052376 | CLB-MP-HAUL-DT199 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85978 | 12765 | 7500
500052375 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 85978 | 12765 | 7500
500052374 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 85978 | 12765 | 7500
500052373 | CLB-MP-HAUL-DT199 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 85978 | 12765 | 7500
500052372 | CLB-MP-HAUL-DT199 -BRKSYS-BACCM | Brake Accumulator | 85978 | 12765 | 7500
500052371 | CLB-MP-HAUL-DT199 -BRKSYS-BROCO | Brake Oil Cooler | 85978 | 85978 | 7500
500052370 | CLB-MP-HAUL-DT199 -BRKSYS-MERTR | Mechanical Retarder | 85978 | 85978 | 7500
500052369 | CLB-MP-HAUL-DT199 -BRKSYS-BRVTR | Valve Brake Treadle | 85978 | 85978 | 7500
500052368 | CLB-MP-HAUL-DT199 -BRKSYS-HYFPP | Pump Brake Control | 85978 | 1188 | 7500
500052367 | CLB-MP-HAUL-DT199 -BRKSYS-PRKPP | Pump Park Brake Release | 85978 | 85978 | 7500
500052366 | CLB-MP-HAUL-DT199 -BRKSYS-BRPMP | Pump Brake | 85978 | 85978 | 7500
500052365 | CLB-MP-HAUL-DT199 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85978 | 85978 | 7500
500052364 | CLB-MP-HAUL-DT199 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85978 | 85978 | 7500
500052363 | CLB-MP-HAUL-DT199 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85978 | 85978 | 7500
500052362 | CLB-MP-HAUL-DT199 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85978 | 85978 | 7500
500052361 | CLB-MP-HAUL-DT199 -BRKSYS-SRVBK | Service Brake | 85978 | 85978 | 7500
500052360 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85978 | 85978 | 7500
500052359 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85978 | 85978 | 7500
500052358 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 85978 | 12765 | 7500
500052357 | CLB-MP-HAUL-DT199 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85978 | 12765 | 7500
500052356 | CLB-MP-HAUL-DT199 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85978 | 12765 | 7500
500052355 | CLB-MP-HAUL-DT199 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85978 | 7443 | 7500
500052354 | CLB-MP-HAUL-DT199 -FDRSYS-DRLAX | Drive Line Axles | 85978 | 85978 | 7500
500052353 | CLB-MP-HAUL-DT199 -FDRSYS-DIFFL | Differential | 85978 | 12765 | 7500
500052352 | CLB-MP-HAUL-DT199 -FDRSYS-DRSHT | Transmission Drive Shaft | 85978 | 12765 | 7500
500052351 | CLB-MP-HAUL-DT199 -TRNSYS-TROLC | Oil Cooler Transmission | 85978 | 12765 | 7500
500052350 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85978 | 12765 | 7500
500052349 | CLB-MP-HAUL-DT199 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85978 | 5385 | 7500
500052348 | CLB-MP-HAUL-DT199 -TRNSYS-TRANS | Transmission | 85978 | 12765 | 7500
500052347 | CLB-MP-HAUL-DT199 -TRNSYS-TRQUE | Torque Converter | 85978 | 12765 | 7500
500052346 | CLB-MP-HAUL-DT199 -ELCTLV-CHARG-BATTY | Batteries | 85978 | 85978 | 7500
500052345 | CLB-MP-HAUL-DT199 -ELCTLV-CHARG-ALTER | Alternator 24V | 85955 | 1188 | 7500
500052344 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85978 | 1188 | 7500
500052343 | CLB-MP-HAUL-DT199 -ENGINE-PMPDR | Pump Drive | 85978 | 12765 | 7500
500052342 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 85978 | 12765 | 7500
500052341 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 85978 | 1188 | 7500
500052340 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 85978 | 1188 | 7500
500052339 | CLB-MP-HAUL-DT199 -ENGINE-FUSYS-FULTK | Fuel Tank | 85978 | 23065 | 7500
500052338 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-EXHST | Exhaust System | 85978 | 85978 | 7500
500052337 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-AFTER | Aftercooler | 85978 | 85978 | 7500
500052336 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 85978 | 1188 | 7500
500052335 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 85978 | 1188 | 7500
500052334 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 85978 | 1188 | 7500
500052333 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 85978 | 1188 | 7500
500052332 | CLB-MP-HAUL-DT199 -ENGINE-INTEX-AIRFL | Air Filtration System | 85978 | 85978 | 7500
500052331 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-THERM | Thermostats/Regulators | 85978 | 1188 | 7500
500052330 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-BELTS | Fan Belts Engine | 85978 | 85978 | 7500
500052329 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 85978 | 1188 | 7500
500052328 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-COFAN | Fan Cooling System | 85978 | 12765 | 7500
500052327 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-RADTR | Coolant Engine | 85978 | 35622 | 7400
500052326 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-RADTR | Radiator Engine | 85978 | 12765 | 7500
500052325 | CLB-MP-HAUL-DT199 -ENGINE-COSYS-WTRPP | Water Pump Engine | 85978 | 1188 | 7500
500052324 | CLB-MP-HAUL-DT199 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 85978 | 85978 | 7500
500052323 | CLB-MP-HAUL-DT199 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 85978 | 12765 | 7500
500052322 | CLB-MP-HAUL-DT199 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 85978 | 85978 | 7500
500052321 | CLB-MP-HAUL-DT199 -ENGINE-COMPR | Air Compressor | 85978 | 1188 | 7500
500052319 | CLB-MP-HAUL-DT199 -ENGINE | Engine Assembly Caterpillar 3516B | 85978 | 12765 | 7500
500052318 | CLB-MP-HAUL-DT199 | DT199 Lubrication & Mechanical Services | 85978 | 85978 | 7500
500052317 | CLB-MP-HAUL-DT199 | Caterpillar 789D Haul Truck DT199 | 85978 | 85978 | 7500
500160299 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITRH | Air Tank Right | 88415 | 16378 | 7500
500160298 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK-AITLH | Air Tank Left | 88415 | 16378 | 7500
500147314 | CLB-MP-HAUL-DT198 -STRSYS-STACC | Steering Accumulator Rear | 16643 | 16643 | 7500
500147313 | CLB-MP-HAUL-DT198 -STRSYS-STACC | Steering Accumulator Middle | 16643 | 16643 | 7500
500147312 | CLB-MP-HAUL-DT198 -STRSYS-STACC | Steering Accumulator Front | 16643 | 16643 | 7500
500118577 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-AFRME | A Frame Housing | 88680 | 16643 | 7500
500117953 | CLB-MP-HAUL-DT198 -ELCTLV-LIGHT | Lighting Low Voltage | 88680 | 30671 | 7500
500117913 | CLB-MP-HAUL-DT198 -ELCTLV-HARNS | Electrical Harness | 88680 | 47644 | 7500
500117873 | CLB-MP-HAUL-DT198 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 88680 | 47644 | 7500
500117437 | CLB-MP-HAUL-DT198 -ELCTLV-LIGHT-AHSYS | AHS Lights | 88680 | 47644 | 7500
500117317 | CLB-MP-HAUL-DT198 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 88680 | 47644 | 7500
500111239 | CLB-MP-HAUL-DT198 -STRUCT-RAXHO | Rear Axle Housing | 88680 | 39454 | 7500
500110569 | CLB-MP-HAUL-DT198 -GRSYST | Grease Lubrication System | 88680 | 12627 | 7500
500102819 | CLB-MP-HAUL-DT198 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 88680 | 16643 | 7500
500100646 | CLB-MP-HAUL-DT198 -TRNSYS | DT198 Transmission System | 88680 | 43252 | 7500
500081423 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 88680 | 23807 | 7500
500081283 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 88680 | 23807 | 7500
500079456 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN | Suspension Service | 88680 | 16643 | 7500
500078522 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 88680 | 16643 | 7500
500078485 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 88680 | 16643 | 7500
500061441 | CLB-MP-HAUL-DT198 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 88680 | 16643 | 7500
500061411 | CLB-MP-HAUL-DT198 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 88680 | 16643 | 7500
500061349 | CLB-MP-HAUL-DT198 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 88680 | 16643 | 7500
500061348 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-ELECT | Chassis Electrical System | 88680 | 39454 | 7500
500061347 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-ELECT | Cabin Electrical System | 88680 | 88680 | 7500
500061346 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 88680 | 16643 | 7500
500061345 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 88680 | 16643 | 7500
500061344 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 88680 | 16643 | 7500
500061343 | CLB-MP-HAUL-DT198 -STRSYS-STHLF-STRHO | Steering System Hoses | 88680 | 16643 | 7500
500061342 | CLB-MP-HAUL-DT198 -STRSYS-STLTR-STBST | Ball Studs | 88680 | 88680 | 7500
500061341 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 88680 | 16643 | 7500
500061340 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 88680 | 16643 | 7500
500061339 | CLB-MP-HAUL-DT198 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 88680 | 16643 | 7500
500061338 | CLB-MP-HAUL-DT198 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 88680 | 16643 | 7500
500061337 | CLB-MP-HAUL-DT198 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 88680 | 16643 | 7500
500061336 | CLB-MP-HAUL-DT198 -BRKSYS-BRVRL | Brake Relay Valve | 88680 | 16643 | 7500
500061334 | CLB-MP-HAUL-DT198 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 88680 | 16643 | 7500
500061333 | CLB-MP-HAUL-DT198 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 88680 | 16643 | 7500
500060136 | CLB-MP-HAUL-DT198 -STRSYS-STTNK | Tank Steering | 88680 | 88680 | 7500
500053861 | CLB-MP-HAUL-DT198 -BRKSYS-BRVLV | Valve Brake | 88680 | 16643 | 7500
500052316 | CLB-MP-HAUL-DT198 -MANGMT-UMMMC | Mine Monitoring and Control | 88680 | 88680 | 7500
500052315 | CLB-MP-HAUL-DT198 -MANGMT-UMTRN | Power Train Management System | 88680 | 88680 | 7500
500052314 | CLB-MP-HAUL-DT198 -MANGMT-UMENG | Engine Management System | 88680 | 88680 | 7500
500052313 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 88680 | 16643 | 7500
500052312 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 88680 | 16643 | 7500
500052311 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 88680 | 16643 | 7500
500052310 | CLB-MP-HAUL-DT198 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 88680 | 16643 | 7500
500052307 | CLB-MP-HAUL-DT198 -STRUCT-TRAYS | Tray | 88680 | 16643 | 7500
500052306 | CLB-MP-HAUL-DT198 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 88680 | 7985 | 7500
500052305 | CLB-MP-HAUL-DT198 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88680 | 4182 | 7500
500052304 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-TAGLK | Tag Link | 88680 | 16643 | 7500
500052303 | CLB-MP-HAUL-DT198 -STRUCT-CHASS-AFRME | A Frame Bearing | 88680 | 16643 | 7500
500052302 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-SBELT | Seat Belt | 88680 | 88680 | 7500
500052301 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-SEATS | Operators Seat | 88680 | 13193 | 7500
500052300 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 88680 | 88680 | 7500
500052299 | CLB-MP-HAUL-DT198 -STRUCT-CABIN-AIRCN | Air Conditioning System | 88680 | 16643 | 7500
500052298 | CLB-MP-HAUL-DT198 -STRUCT-CABIN | Operators Cabin | 88680 | 16643 | 7500
500052297 | CLB-MP-HAUL-DT198 -PNEUMC-START | Air Starter | 88680 | 5576 | 7500
500052296 | CLB-MP-HAUL-DT198 -PNEUMC-AIRDR | Air Drier | 88680 | 16643 | 7500
500052295 | CLB-MP-HAUL-DT198 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 88680 | 88680 | 7500
500052294 | CLB-MP-HAUL-DT198 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 88680 | 88680 | 7500
500052293 | CLB-MP-HAUL-DT198 -PNEUMC-PNTNK | No Not Use | 88680 | 16643 | 7500
500052292 | CLB-MP-HAUL-DT198 -GRSYST-ALCON | Auto Lube Controller | 88680 | 88680 | 7500
500052291 | CLB-MP-HAUL-DT198 -GRSYST-ALBPP | Auto Lube Pump | 88680 | 23172 | 7500
500052290 | CLB-MP-HAUL-DT198 -GRSYST-GRTNK | Auto Lube Resevoir | 88680 | 88680 | 7500
500052289 | CLB-MP-HAUL-DT198 -GRSYST-GRINJ | Auto Lube Injectors | 88680 | 88680 | 7500
500052288 | CLB-MP-HAUL-DT198 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 88680 | 16643 | 7500
500052287 | CLB-MP-HAUL-DT198 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 88680 | 5575 | 7500
500052286 | CLB-MP-HAUL-DT198 -HYDSYS-HOVLV | Valve Hoist | 88680 | 39454 | 7500
500052285 | CLB-MP-HAUL-DT198 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 88680 | 88680 | 7500
500052284 | CLB-MP-HAUL-DT198 -HYDSYS-HDTNK | Tank Hydraulic | 88680 | 88680 | 7500
500052283 | CLB-MP-HAUL-DT198 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 88680 | 16643 | 7500
500052282 | CLB-MP-HAUL-DT198 -HYDSYS-HOPMP | Pump Hoist | 88680 | 16643 | 7500
500052281 | CLB-MP-HAUL-DT198 -HYDSYS | Hydraulic System | 88680 | 88680 | 7500
500052280 | CLB-MP-HAUL-DT198 -STRSYS-STCON-STCOL | Steering Column | 88680 | 88680 | 7500
500052279 | CLB-MP-HAUL-DT198 -STRSYS-STCON-STWHL | Steering Wheel | 88680 | 88680 | 7500
500052278 | CLB-MP-HAUL-DT198 -STRSYS-STLTR | Steering Linkages and Tie Rods | 88680 | 6816 | 7500
500052277 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 88680 | 16643 | 7500
500052276 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 88680 | 16643 | 7500
500052275 | CLB-MP-HAUL-DT198 -STRSYS-STACC-SACCF | Accumulator Steering Front | 88680 | 16643 | 7500
500052274 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 88680 | 13193 | 7500
500052273 | CLB-MP-HAUL-DT198 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 88680 | 12630 | 7500
500052272 | CLB-MP-HAUL-DT198 -STRSYS-STVLV | Valve Steering | 88680 | 16643 | 7500
500052271 | CLB-MP-HAUL-DT198 -STRSYS-STHMU | Steering HMU | 88680 | 23807 | 7500
500052270 | CLB-MP-HAUL-DT198 -STRSYS-STPMP | Pump Steering | 88680 | 7977 | 7500
500052269 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 88680 | 16643 | 7500
500052268 | CLB-MP-HAUL-DT198 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 88680 | 16643 | 7500
500052267 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 88680 | 16643 | 7500
500052266 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 88680 | 16643 | 7500
500052265 | CLB-MP-HAUL-DT198 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 88680 | 16643 | 7500
500052264 | CLB-MP-HAUL-DT198 -BRKSYS-BACCM | Brake Accumulator | 88680 | 16643 | 7500
500052263 | CLB-MP-HAUL-DT198 -BRKSYS-BROCO | Brake Oil Cooler | 88680 | 62676 | 7500
500052262 | CLB-MP-HAUL-DT198 -BRKSYS-MERTR | Mechanical Retarder | 88680 | 88680 | 7500
500052261 | CLB-MP-HAUL-DT198 -BRKSYS-BRVTR | Valve Brake Treadle | 88680 | 88680 | 7500
500052260 | CLB-MP-HAUL-DT198 -BRKSYS-HYFPP | Pump Brake Control | 88680 | 5576 | 7500
500052259 | CLB-MP-HAUL-DT198 -BRKSYS-PRKPP | Pump Park Brake Release | 88680 | 88680 | 7500
500052258 | CLB-MP-HAUL-DT198 -BRKSYS-BRPMP | Pump Brake | 88680 | 88680 | 7500
500052257 | CLB-MP-HAUL-DT198 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 88680 | 88680 | 7500
500052256 | CLB-MP-HAUL-DT198 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 88680 | 88680 | 7500
500052255 | CLB-MP-HAUL-DT198 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 88680 | 48901 | 7500
500052254 | CLB-MP-HAUL-DT198 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 88680 | 48901 | 7500
500052253 | CLB-MP-HAUL-DT198 -BRKSYS-SRVBK | Service Brake | 88680 | 88680 | 7500
500052252 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 88680 | 88680 | 7500
500052251 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 88680 | 88680 | 7500
500052250 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 88680 | 5577 | 7500
500052249 | CLB-MP-HAUL-DT198 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 88680 | 16643 | 7500
500052248 | CLB-MP-HAUL-DT198 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 88680 | 16643 | 7500
500052247 | CLB-MP-HAUL-DT198 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 88680 | 16643 | 7500
500052246 | CLB-MP-HAUL-DT198 -FDRSYS-DRLAX | Drive Line Axles | 88680 | 88680 | 7500
500052245 | CLB-MP-HAUL-DT198 -FDRSYS-DIFFL | Differential | 88680 | 16643 | 7500
500052244 | CLB-MP-HAUL-DT198 -FDRSYS-DRSHT | Transmission Drive Shaft | 88680 | 27582 | 7500
500052243 | CLB-MP-HAUL-DT198 -TRNSYS-TROLC | Oil Cooler Transmission | 88680 | 7548 | 7500
500052242 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 88680 | 4182 | 7500
500052241 | CLB-MP-HAUL-DT198 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 88680 | 7548 | 7500
500052240 | CLB-MP-HAUL-DT198 -TRNSYS-TRANS | Transmission | 88680 | 7548 | 7500
500052239 | CLB-MP-HAUL-DT198 -TRNSYS-TRQUE | Torque Converter | 88680 | 16643 | 7500
500052238 | CLB-MP-HAUL-DT198 -ELCTLV-CHARG-BATTY | Batteries | 88680 | 88680 | 7500
500052237 | CLB-MP-HAUL-DT198 -ELCTLV-CHARG-ALTER | Alternator 24V | 88680 | 5576 | 7500
500052236 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 88680 | 16643 | 7500
500052235 | CLB-MP-HAUL-DT198 -ENGINE-PMPDR | Pump Drive | 88680 | 16643 | 7500
500052234 | CLB-MP-HAUL-DT198 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 88680 | 16643 | 7500
500052233 | CLB-MP-HAUL-DT198 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 88680 | 5576 | 7500
500052232 | CLB-MP-HAUL-DT198 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 88680 | 16643 | 7500
500052231 | CLB-MP-HAUL-DT198 -ENGINE-FUSYS-FULTK | Fuel Tank | 88680 | 16643 | 7500
500052230 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-EXHST | Exhaust System | 88680 | 88680 | 7500
500052229 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-AFTER | Aftercooler | 88680 | 88680 | 7500
500052228 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 88680 | 5576 | 7500
500052227 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 88680 | 5576 | 7500
500052226 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 88680 | 5576 | 7500
500052225 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 88680 | 5576 | 7500
500052224 | CLB-MP-HAUL-DT198 -ENGINE-INTEX-AIRFL | Air Filtration System | 88680 | 88680 | 7500
500052223 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-THERM | Thermostats/Regulators | 88680 | 5576 | 7500
500052222 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-BELTS | Fan Belts Engine | 88680 | 88680 | 7500
500052221 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 88680 | 5576 | 7500
500052220 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-COFAN | Fan Cooling System | 88680 | 16643 | 7500
500052219 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-RADTR | Coolant Engine | 88680 | 88680 | 7400
500052218 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-RADTR | Radiator Engine | 88680 | 2125 | 7500
500052217 | CLB-MP-HAUL-DT198 -ENGINE-COSYS-WTRPP | Water Pump Engine | 88680 | 5576 | 7500
500052216 | CLB-MP-HAUL-DT198 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 88680 | 88680 | 7500
500052215 | CLB-MP-HAUL-DT198 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 88680 | 16643 | 7500
500052214 | CLB-MP-HAUL-DT198 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 88680 | 27592 | 7500
500052213 | CLB-MP-HAUL-DT198 -ENGINE-COMPR | Air Compressor | 88680 | 5576 | 7500
500052211 | CLB-MP-HAUL-DT198 -ENGINE | Engine Assembly Caterpillar 3516B | 88680 | 16643 | 7500
500052210 | CLB-MP-HAUL-DT198 | DT198 Lubrication & Mechanical Services | 88680 | 88680 | 7500
500052209 | CLB-MP-HAUL-DT198 | Caterpillar 789D Haul Truck DT198 | 88680 | 88680 | 7500
500160297 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITRH | Air Tank Right | 85995 | 85995 | 7500
500160296 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK-AITLH | Air Tank Left | 85995 | 85995 | 7500
500147310 | CLB-MP-HAUL-DT197 -STRSYS-STACC | Steering Accumulator Rear | 16648 | 16648 | 7500
500147309 | CLB-MP-HAUL-DT197 -STRSYS-STACC | Steering Accumulator Middle | 16648 | 16648 | 7500
500147308 | CLB-MP-HAUL-DT197 -STRSYS-STACC | Steering Accumulator Front | 16648 | 16648 | 7500
500118576 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-AFRME | A Frame Housing | 86259 | 25918 | 7500
500117952 | CLB-MP-HAUL-DT197 -ELCTLV-LIGHT | Lighting Low Voltage | 86259 | 47730 | 7500
500117912 | CLB-MP-HAUL-DT197 -ELCTLV-HARNS | Electrical Harness | 86259 | 47730 | 7500
500117872 | CLB-MP-HAUL-DT197 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 86259 | 47730 | 7500
500117436 | CLB-MP-HAUL-DT197 -ELCTLV-LIGHT-AHSYS | AHS Lights | 86259 | 47730 | 7500
500117316 | CLB-MP-HAUL-DT197 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 86259 | 47730 | 7500
500111238 | CLB-MP-HAUL-DT197 -STRUCT-RAXHO | Rear Axle Housing | 86259 | 38496 | 7500
500110568 | CLB-MP-HAUL-DT197 -GRSYST | Grease Lubrication System | 86259 | 13951 | 7500
500102818 | CLB-MP-HAUL-DT197 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 86259 | 16648 | 7500
500100645 | CLB-MP-HAUL-DT197 -TRNSYS | DT197 Transmission System | 86259 | 51439 | 7500
500081422 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 86259 | 25918 | 7500
500081282 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 86259 | 25918 | 7500
500079455 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN | Suspension Service | 86259 | 11085 | 7500
500078521 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 86259 | 16648 | 7500
500078484 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 86259 | 16648 | 7500
500062766 | CLB-MP-HAUL-DT197 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 86259 | 16648 | 7500
500062765 | CLB-MP-HAUL-DT197 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 86259 | 16648 | 7500
500062764 | CLB-MP-HAUL-DT197 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 86259 | 16648 | 7500
500062763 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-ELECT | Chassis Electrical System | 86259 | 38496 | 7500
500062762 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-ELECT | Cabin Electrical System | 86259 | 86259 | 7500
500062761 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 86259 | 16648 | 7500
500062760 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 86259 | 16648 | 7500
500062759 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 86259 | 16648 | 7500
500062758 | CLB-MP-HAUL-DT197 -STRSYS-STHLF-STRHO | Steering System Hoses | 86259 | 16648 | 7500
500062757 | CLB-MP-HAUL-DT197 -STRSYS-STLTR-STBST | Ball Studs | 86259 | 86259 | 7500
500062756 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 86259 | 16648 | 7500
500062755 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 86259 | 16648 | 7500
500062754 | CLB-MP-HAUL-DT197 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 86259 | 16648 | 7500
500062753 | CLB-MP-HAUL-DT197 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 86259 | 16648 | 7500
500062752 | CLB-MP-HAUL-DT197 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 86259 | 16648 | 7500
500062751 | CLB-MP-HAUL-DT197 -BRKSYS-BRVRL | Brake Relay Valve | 86259 | 5525 | 7500
500062749 | CLB-MP-HAUL-DT197 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 86259 | 16648 | 7500
500062748 | CLB-MP-HAUL-DT197 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 86259 | 16648 | 7500
500060135 | CLB-MP-HAUL-DT197 -STRSYS-STTNK | Tank Steering | 86259 | 16648 | 7500
500053860 | CLB-MP-HAUL-DT197 -BRKSYS-BRVLV | Valve Brake | 86259 | 16648 | 7500
500052208 | CLB-MP-HAUL-DT197 -MANGMT-UMMMC | Mine Monitoring and Control | 86259 | 86259 | 7500
500052207 | CLB-MP-HAUL-DT197 -MANGMT-UMTRN | Power Train Management System | 86259 | 86259 | 7500
500052206 | CLB-MP-HAUL-DT197 -MANGMT-UMENG | Engine Management System | 86259 | 86259 | 7500
500052205 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 86259 | 10402 | 7500
500052204 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 86259 | 16648 | 7500
500052203 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 86259 | 16648 | 7500
500052202 | CLB-MP-HAUL-DT197 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 86259 | 21427 | 7500
500052199 | CLB-MP-HAUL-DT197 -STRUCT-TRAYS | Tray | 86259 | 20846 | 7500
500052198 | CLB-MP-HAUL-DT197 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 86259 | 16648 | 7500
500052197 | CLB-MP-HAUL-DT197 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 86259 | 16648 | 7500
500052196 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-TAGLK | Tag Link | 86259 | 25922 | 7500
500052195 | CLB-MP-HAUL-DT197 -STRUCT-CHASS-AFRME | A Frame Bearing | 86259 | 25918 | 7500
500052194 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-SBELT | Seat Belt | 86259 | 86259 | 7500
500052193 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-SEATS | Operators Seat | 86259 | 23439 | 7500
500052192 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86259 | 86259 | 7500
500052191 | CLB-MP-HAUL-DT197 -STRUCT-CABIN-AIRCN | Air Conditioning System | 86259 | 16648 | 7500
500052190 | CLB-MP-HAUL-DT197 -STRUCT-CABIN | Operators Cabin | 86259 | 38496 | 7500
500052189 | CLB-MP-HAUL-DT197 -PNEUMC-START | Air Starter | 86259 | 4965 | 7500
500052188 | CLB-MP-HAUL-DT197 -PNEUMC-AIRDR | Air Drier | 86259 | 16648 | 7500
500052187 | CLB-MP-HAUL-DT197 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 86259 | 86259 | 7500
500052186 | CLB-MP-HAUL-DT197 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 86259 | 86259 | 7500
500052185 | CLB-MP-HAUL-DT197 -PNEUMC-PNTNK | No Not Use | 86259 | 86259 | 7500
500052184 | CLB-MP-HAUL-DT197 -GRSYST-ALCON | Auto Lube Controller | 86259 | 86259 | 7500
500052183 | CLB-MP-HAUL-DT197 -GRSYST-ALBPP | Auto Lube Pump | 86259 | 86259 | 7500
500052182 | CLB-MP-HAUL-DT197 -GRSYST-GRTNK | Auto Lube Resevoir | 86259 | 86259 | 7500
500052181 | CLB-MP-HAUL-DT197 -GRSYST-GRINJ | Auto Lube Injectors | 86259 | 86259 | 7500
500052180 | CLB-MP-HAUL-DT197 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 86259 | 16648 | 7500
500052179 | CLB-MP-HAUL-DT197 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 86259 | 16648 | 7500
500052178 | CLB-MP-HAUL-DT197 -HYDSYS-HOVLV | Valve Hoist | 86259 | 16648 | 7500
500052177 | CLB-MP-HAUL-DT197 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 86259 | 86259 | 7500
500052176 | CLB-MP-HAUL-DT197 -HYDSYS-HDTNK | Tank Hydraulic | 86259 | 86259 | 7500
500052175 | CLB-MP-HAUL-DT197 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 86259 | 16648 | 7500
500052174 | CLB-MP-HAUL-DT197 -HYDSYS-HOPMP | Pump Hoist | 86259 | 16648 | 7500
500052173 | CLB-MP-HAUL-DT197 -HYDSYS | Hydraulic System | 86259 | 86259 | 7500
500052172 | CLB-MP-HAUL-DT197 -STRSYS-STCON-STCOL | Steering Column | 86259 | 86259 | 7500
500052171 | CLB-MP-HAUL-DT197 -STRSYS-STCON-STWHL | Steering Wheel | 86259 | 86259 | 7500
500052170 | CLB-MP-HAUL-DT197 -STRSYS-STLTR | Steering Linkages and Tie Rods | 86259 | 25173 | 7500
500052169 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 86259 | 16648 | 7500
500052168 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 86259 | 16648 | 7500
500052167 | CLB-MP-HAUL-DT197 -STRSYS-STACC-SACCF | Accumulator Steering Front | 86259 | 16648 | 7500
500052166 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 86259 | 4965 | 7500
500052165 | CLB-MP-HAUL-DT197 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 86259 | 16648 | 7500
500052164 | CLB-MP-HAUL-DT197 -STRSYS-STVLV | Valve Steering | 86259 | 16648 | 7500
500052163 | CLB-MP-HAUL-DT197 -STRSYS-STHMU | Steering HMU | 86259 | 22691 | 7500
500052162 | CLB-MP-HAUL-DT197 -STRSYS-STPMP | Pump Steering | 86259 | 8210 | 7500
500052161 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 86259 | 16648 | 7500
500052160 | CLB-MP-HAUL-DT197 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 86259 | 16648 | 7500
500052159 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 86259 | 16648 | 7500
500052158 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 86259 | 16648 | 7500
500052157 | CLB-MP-HAUL-DT197 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 86259 | 16648 | 7500
500052156 | CLB-MP-HAUL-DT197 -BRKSYS-BACCM | Brake Accumulator | 86259 | 16648 | 7500
500052155 | CLB-MP-HAUL-DT197 -BRKSYS-BROCO | Brake Oil Cooler | 86259 | 62896 | 7500
500052154 | CLB-MP-HAUL-DT197 -BRKSYS-MERTR | Mechanical Retarder | 86259 | 86259 | 7500
500052153 | CLB-MP-HAUL-DT197 -BRKSYS-BRVTR | Valve Brake Treadle | 86259 | 86259 | 7500
500052152 | CLB-MP-HAUL-DT197 -BRKSYS-HYFPP | Pump Brake Control | 86259 | 5525 | 7500
500052151 | CLB-MP-HAUL-DT197 -BRKSYS-PRKPP | Pump Park Brake Release | 86259 | 86259 | 7500
500052150 | CLB-MP-HAUL-DT197 -BRKSYS-BRPMP | Pump Brake | 86259 | 38038 | 7500
500052149 | CLB-MP-HAUL-DT197 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 86259 | 86259 | 7500
500052148 | CLB-MP-HAUL-DT197 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 86259 | 86259 | 7500
500052147 | CLB-MP-HAUL-DT197 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 86259 | 86259 | 7500
500052146 | CLB-MP-HAUL-DT197 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 86259 | 86259 | 7500
500052145 | CLB-MP-HAUL-DT197 -BRKSYS-SRVBK | Service Brake | 86259 | 86259 | 7500
500052144 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 86259 | 86259 | 7500
500052143 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 86259 | 86259 | 7500
500052142 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 86259 | 5525 | 7500
500052141 | CLB-MP-HAUL-DT197 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 86259 | 21377 | 7500
500052140 | CLB-MP-HAUL-DT197 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 86259 | 16648 | 7500
500052139 | CLB-MP-HAUL-DT197 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 86259 | 18915 | 7500
500052138 | CLB-MP-HAUL-DT197 -FDRSYS-DRLAX | Drive Line Axles | 86259 | 86259 | 7500
500052137 | CLB-MP-HAUL-DT197 -FDRSYS-DIFFL | Differential | 86259 | 21386 | 7500
500052136 | CLB-MP-HAUL-DT197 -FDRSYS-DRSHT | Transmission Drive Shaft | 86259 | 4965 | 7500
500052135 | CLB-MP-HAUL-DT197 -TRNSYS-TROLC | Oil Cooler Transmission | 86259 | 10403 | 7500
500052134 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 86259 | 8210 | 7500
500052133 | CLB-MP-HAUL-DT197 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 86259 | 10405 | 7500
500052132 | CLB-MP-HAUL-DT197 -TRNSYS-TRANS | Transmission | 86259 | 10405 | 7500
500052131 | CLB-MP-HAUL-DT197 -TRNSYS-TRQUE | Torque Converter | 86259 | 16648 | 7500
500052130 | CLB-MP-HAUL-DT197 -ELCTLV-CHARG-BATTY | Batteries | 86259 | 86259 | 7500
500052129 | CLB-MP-HAUL-DT197 -ELCTLV-CHARG-ALTER | Alternator 24V | 86259 | 4965 | 7500
500052128 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 86259 | 16648 | 7500
500052127 | CLB-MP-HAUL-DT197 -ENGINE-PMPDR | Pump Drive | 86259 | 16648 | 7500
500052126 | CLB-MP-HAUL-DT197 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 86259 | 16648 | 7500
500052125 | CLB-MP-HAUL-DT197 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 86259 | 4965 | 7500
500052124 | CLB-MP-HAUL-DT197 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 86259 | 4965 | 7500
500052123 | CLB-MP-HAUL-DT197 -ENGINE-FUSYS-FULTK | Fuel Tank | 86259 | 16648 | 7500
500052122 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-EXHST | Exhaust System | 86259 | 60507 | 7500
500052121 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-AFTER | Aftercooler | 86259 | 86259 | 7500
500052120 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 86259 | 4965 | 7500
500052119 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 86259 | 4965 | 7500
500052118 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 86259 | 4965 | 7500
500052117 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 86259 | 4965 | 7500
500052116 | CLB-MP-HAUL-DT197 -ENGINE-INTEX-AIRFL | Air Filtration System | 86259 | 86259 | 7500
500052115 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-THERM | Thermostats/Regulators | 86259 | 4965 | 7500
500052114 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-BELTS | Fan Belts Engine | 86259 | 86259 | 7500
500052113 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 86259 | 4965 | 7500
500052112 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-COFAN | Fan Cooling System | 86259 | 16648 | 7500
500052111 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-RADTR | Coolant Engine | 86259 | 16648 | 7400
500052110 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-RADTR | Radiator Engine | 86259 | 16648 | 7500
500052109 | CLB-MP-HAUL-DT197 -ENGINE-COSYS-WTRPP | Water Pump Engine | 86259 | 4965 | 7500
500052108 | CLB-MP-HAUL-DT197 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 86259 | 86259 | 7500
500052107 | CLB-MP-HAUL-DT197 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 86259 | 16648 | 7500
500052106 | CLB-MP-HAUL-DT197 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 86259 | 86259 | 7500
500052105 | CLB-MP-HAUL-DT197 -ENGINE-COMPR | Air Compressor | 86259 | 4965 | 7500
500052103 | CLB-MP-HAUL-DT197 -ENGINE | Engine Assembly Caterpillar 3516B | 86259 | 16648 | 7500
500052102 | CLB-MP-HAUL-DT197 | DT197 Lubrication & Mechanical Services | 86259 | 86259 | 7500
500052101 | CLB-MP-HAUL-DT197 | Caterpillar 789D Haul Truck DT197 | 86259 | 86259 | 7500
500160295 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITRH | Air Tank Right | 84897 | 84897 | 7500
500160294 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK-AITLH | Air Tank Left | 84897 | 84897 | 7500
500147306 | CLB-MP-HAUL-DT196 -STRSYS-STACC | Steering Accumulator Rear | 36765 | 36765 | 7500
500147305 | CLB-MP-HAUL-DT196 -STRSYS-STACC | Steering Accumulator Middle | 36765 | 36765 | 7500
500147304 | CLB-MP-HAUL-DT196 -STRSYS-STACC | Steering Accumulator Front | 36765 | 36765 | 7500
500118575 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-AFRME | A Frame Housing | 85161 | 14148 | 7500
500117951 | CLB-MP-HAUL-DT196 -ELCTLV-LIGHT | Lighting Low Voltage | 85161 | 52659 | 7500
500117911 | CLB-MP-HAUL-DT196 -ELCTLV-HARNS | Electrical Harness | 85161 | 52659 | 7500
500117871 | CLB-MP-HAUL-DT196 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85161 | 52659 | 7500
500117435 | CLB-MP-HAUL-DT196 -ELCTLV-LIGHT-AHSYS | AHS Lights | 85161 | 52659 | 7500
500117315 | CLB-MP-HAUL-DT196 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 85161 | 52659 | 7500
500111237 | CLB-MP-HAUL-DT196 -STRUCT-RAXHO | Rear Axle Housing | 81359 | 81359 | 7500
500110567 | CLB-MP-HAUL-DT196 -GRSYST | Grease Lubrication System | 85161 | 13354 | 7500
500102817 | CLB-MP-HAUL-DT196 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85161 | 14148 | 7500
500100644 | CLB-MP-HAUL-DT196 -TRNSYS | DT196 Transmission System | 85161 | 53383 | 7500
500081421 | CLB-MP-HAUL-DT196 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85161 | 25252 | 7500
500081281 | CLB-MP-HAUL-DT196 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85161 | 24249 | 7500
500079454 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN | Suspension Service | 85161 | 14133 | 7500
500078520 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 85161 | 14148 | 7500
500078483 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 85161 | 14148 | 7500
500062747 | CLB-MP-HAUL-DT196 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85161 | 14148 | 7500
500062746 | CLB-MP-HAUL-DT196 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85161 | 14148 | 7500
500062745 | CLB-MP-HAUL-DT196 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 85161 | 14148 | 7500
500062744 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-ELECT | Chassis Electrical System | 85161 | 36765 | 7500
500062743 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85161 | 85161 | 7500
500062742 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 85161 | 14148 | 7500
500062741 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 85161 | 14148 | 7500
500062740 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 85161 | 14148 | 7500
500062739 | CLB-MP-HAUL-DT196 -STRSYS-STHLF-STRHO | Steering System Hoses | 85161 | 14148 | 7500
500062738 | CLB-MP-HAUL-DT196 -STRSYS-STLTR-STBST | Ball Studs | 85161 | 85161 | 7500
500062737 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 85161 | 14148 | 7500
500062736 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 85161 | 14148 | 7500
500062735 | CLB-MP-HAUL-DT196 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 85161 | 14148 | 7500
500062734 | CLB-MP-HAUL-DT196 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85161 | 14148 | 7500
500062733 | CLB-MP-HAUL-DT196 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85161 | 14148 | 7500
500062732 | CLB-MP-HAUL-DT196 -BRKSYS-BRVRL | Brake Relay Valve | 85161 | 14148 | 7500
500062730 | CLB-MP-HAUL-DT196 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85161 | 14148 | 7500
500062729 | CLB-MP-HAUL-DT196 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85161 | 14148 | 7500
500060134 | CLB-MP-HAUL-DT196 -STRSYS-STTNK | Tank Steering | 85161 | 85161 | 7500
500053859 | CLB-MP-HAUL-DT196 -BRKSYS-BRVLV | Valve Brake | 85161 | 14148 | 7500
500052100 | CLB-MP-HAUL-DT196 -MANGMT-UMMMC | Mine Monitoring and Control | 85161 | 85161 | 7500
500052099 | CLB-MP-HAUL-DT196 -MANGMT-UMTRN | Power Train Management System | 85161 | 85161 | 7500
500052098 | CLB-MP-HAUL-DT196 -MANGMT-UMENG | Engine Management System | 85161 | 85161 | 7500
500052097 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85161 | 14148 | 7500
500052096 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85161 | 14148 | 7500
500052095 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85161 | 14148 | 7500
500052094 | CLB-MP-HAUL-DT196 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85161 | 5613 | 7500
500052091 | CLB-MP-HAUL-DT196 -STRUCT-TRAYS | Tray | 85161 | 23686 | 7500
500052090 | CLB-MP-HAUL-DT196 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85161 | 21658 | 7500
500052089 | CLB-MP-HAUL-DT196 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85161 | 14148 | 7500
500052088 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-TAGLK | Tag Link | 85161 | 14148 | 7500
500052087 | CLB-MP-HAUL-DT196 -STRUCT-CHASS-AFRME | A Frame Bearing | 85161 | 14148 | 7500
500052086 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-SBELT | Seat Belt | 85161 | 85161 | 7500
500052085 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-SEATS | Operators Seat | 85161 | 19642 | 7500
500052084 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85161 | 85161 | 7500
500052083 | CLB-MP-HAUL-DT196 -STRUCT-CABIN-AIRCN | Air Conditioning System | 85161 | 14148 | 7500
500052082 | CLB-MP-HAUL-DT196 -STRUCT-CABIN | Operators Cabin | 85161 | 36765 | 7500
500052081 | CLB-MP-HAUL-DT196 -PNEUMC-START | Air Starter | 85161 | 2834 | 7500
500052080 | CLB-MP-HAUL-DT196 -PNEUMC-AIRDR | Air Drier | 85161 | 14148 | 7500
500052079 | CLB-MP-HAUL-DT196 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 85161 | 85161 | 7500
500052078 | CLB-MP-HAUL-DT196 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 85161 | 85161 | 7500
500052077 | CLB-MP-HAUL-DT196 -PNEUMC-PNTNK | No Not Use | 85161 | 85161 | 7500
500052076 | CLB-MP-HAUL-DT196 -GRSYST-ALCON | Auto Lube Controller | 85161 | 85161 | 7500
500052075 | CLB-MP-HAUL-DT196 -GRSYST-ALBPP | Auto Lube Pump | 85161 | 22315 | 7500
500052074 | CLB-MP-HAUL-DT196 -GRSYST-GRTNK | Auto Lube Resevoir | 85161 | 85161 | 7500
500052073 | CLB-MP-HAUL-DT196 -GRSYST-GRINJ | Auto Lube Injectors | 85161 | 85161 | 7500
500052072 | CLB-MP-HAUL-DT196 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85161 | 14148 | 7500
500052071 | CLB-MP-HAUL-DT196 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85161 | 14148 | 7500
500052070 | CLB-MP-HAUL-DT196 -HYDSYS-HOVLV | Valve Hoist | 85161 | 36765 | 7500
500052069 | CLB-MP-HAUL-DT196 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85161 | 85161 | 7500
500052068 | CLB-MP-HAUL-DT196 -HYDSYS-HDTNK | Tank Hydraulic | 85161 | 85161 | 7500
500052067 | CLB-MP-HAUL-DT196 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 85161 | 14148 | 7500
500052066 | CLB-MP-HAUL-DT196 -HYDSYS-HOPMP | Pump Hoist | 85161 | 8200 | 7500
500052065 | CLB-MP-HAUL-DT196 -HYDSYS | Hydraulic System | 85161 | 85161 | 7500
500052064 | CLB-MP-HAUL-DT196 -STRSYS-STCON-STCOL | Steering Column | 85161 | 85161 | 7500
500052063 | CLB-MP-HAUL-DT196 -STRSYS-STCON-STWHL | Steering Wheel | 85161 | 42981 | 7500
500052062 | CLB-MP-HAUL-DT196 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85161 | 19642 | 7500
500052061 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85161 | 14148 | 7500
500052060 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85161 | 14148 | 7500
500052059 | CLB-MP-HAUL-DT196 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85161 | 14148 | 7500
500052058 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85161 | 8199 | 7500
500052057 | CLB-MP-HAUL-DT196 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85161 | 19642 | 7500
500052056 | CLB-MP-HAUL-DT196 -STRSYS-STVLV | Valve Steering | 85161 | 14148 | 7500
500052055 | CLB-MP-HAUL-DT196 -STRSYS-STHMU | Steering HMU | 85161 | 1639 | 7500
500052054 | CLB-MP-HAUL-DT196 -STRSYS-STPMP | Pump Steering | 85161 | 19642 | 7500
500052053 | CLB-MP-HAUL-DT196 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85161 | 14148 | 7500
500052052 | CLB-MP-HAUL-DT196 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85161 | 14148 | 7500
500052051 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 85161 | 14148 | 7500
500052050 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 85161 | 14148 | 7500
500052049 | CLB-MP-HAUL-DT196 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 85161 | 14148 | 7500
500052048 | CLB-MP-HAUL-DT196 -BRKSYS-BACCM | Brake Accumulator | 85161 | 25254 | 7500
500052047 | CLB-MP-HAUL-DT196 -BRKSYS-BROCO | Brake Oil Cooler | 85161 | 56900 | 7500
500052046 | CLB-MP-HAUL-DT196 -BRKSYS-MERTR | Mechanical Retarder | 85161 | 85161 | 7500
500052045 | CLB-MP-HAUL-DT196 -BRKSYS-BRVTR | Valve Brake Treadle | 85161 | 85161 | 7500
500052044 | CLB-MP-HAUL-DT196 -BRKSYS-HYFPP | Pump Brake Control | 85161 | 2274 | 7500
500052043 | CLB-MP-HAUL-DT196 -BRKSYS-PRKPP | Pump Park Brake Release | 85161 | 85161 | 7500
500052042 | CLB-MP-HAUL-DT196 -BRKSYS-BRPMP | Pump Brake | 85161 | 85161 | 7500
500052041 | CLB-MP-HAUL-DT196 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85161 | 85161 | 7500
500052040 | CLB-MP-HAUL-DT196 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85161 | 85161 | 7500
500052039 | CLB-MP-HAUL-DT196 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85161 | 85161 | 7500
500052038 | CLB-MP-HAUL-DT196 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85161 | 85161 | 7500
500052037 | CLB-MP-HAUL-DT196 -BRKSYS-SRVBK | Service Brake | 85161 | 85161 | 7500
500052036 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85161 | 85161 | 7500
500052035 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85161 | 85161 | 7500
500052034 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 85161 | 14148 | 7500
500052033 | CLB-MP-HAUL-DT196 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85161 | 14148 | 7500
500052032 | CLB-MP-HAUL-DT196 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85161 | 8155 | 7500
500052031 | CLB-MP-HAUL-DT196 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85161 | 7457 | 7500
500052030 | CLB-MP-HAUL-DT196 -FDRSYS-DRLAX | Drive Line Axles | 85161 | 85161 | 7500
500052029 | CLB-MP-HAUL-DT196 -FDRSYS-DIFFL | Differential | 85161 | 16148 | 7500
500052028 | CLB-MP-HAUL-DT196 -FDRSYS-DRSHT | Transmission Drive Shaft | 85161 | 25254 | 7500
500052027 | CLB-MP-HAUL-DT196 -TRNSYS-TROLC | Oil Cooler Transmission | 85161 | 14148 | 7500
500052026 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85161 | 14148 | 7500
500052025 | CLB-MP-HAUL-DT196 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85161 | 2274 | 7500
500052024 | CLB-MP-HAUL-DT196 -TRNSYS-TRANS | Transmission | 85161 | 14148 | 7500
500052023 | CLB-MP-HAUL-DT196 -TRNSYS-TRQUE | Torque Converter | 85161 | 14148 | 7500
500052022 | CLB-MP-HAUL-DT196 -ELCTLV-CHARG-BATTY | Batteries | 85161 | 20970 | 7500
500052021 | CLB-MP-HAUL-DT196 -ELCTLV-CHARG-ALTER | Alternator 24V | 85161 | 2834 | 7500
500052020 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85161 | 22315 | 7500
500052019 | CLB-MP-HAUL-DT196 -ENGINE-PMPDR | Pump Drive | 85161 | 3510 | 7500
500052018 | CLB-MP-HAUL-DT196 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 85161 | 14148 | 7500
500052017 | CLB-MP-HAUL-DT196 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 85161 | 2834 | 7500
500052016 | CLB-MP-HAUL-DT196 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 85161 | 2834 | 7500
500052015 | CLB-MP-HAUL-DT196 -ENGINE-FUSYS-FULTK | Fuel Tank | 85161 | 14148 | 7500
500052014 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-EXHST | Exhaust System | 85161 | 85161 | 7500
500052013 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-AFTER | Aftercooler | 85161 | 56900 | 7500
500052012 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 85161 | 2834 | 7500
500052011 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 85161 | 2834 | 7500
500052010 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 85161 | 2834 | 7500
500052009 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 85161 | 2834 | 7500
500052008 | CLB-MP-HAUL-DT196 -ENGINE-INTEX-AIRFL | Air Filtration System | 85161 | 56900 | 7500
500052007 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-THERM | Thermostats/Regulators | 85161 | 2834 | 7500
500052006 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-BELTS | Fan Belts Engine | 85161 | 56900 | 7500
500052005 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 85161 | 2834 | 7500
500052004 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-COFAN | Fan Cooling System | 85161 | 14148 | 7500
500052003 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-RADTR | Coolant Engine | 85161 | 36765 | 7400
500052002 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-RADTR | Radiator Engine | 85161 | 14148 | 7500
500052001 | CLB-MP-HAUL-DT196 -ENGINE-COSYS-WTRPP | Water Pump Engine | 85161 | 2834 | 7500
500052000 | CLB-MP-HAUL-DT196 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 85161 | 56900 | 7500
500051999 | CLB-MP-HAUL-DT196 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 85161 | 14148 | 7500
500051998 | CLB-MP-HAUL-DT196 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 85161 | 56900 | 7500
500051997 | CLB-MP-HAUL-DT196 -ENGINE-COMPR | Air Compressor | 85161 | 2834 | 7500
500051995 | CLB-MP-HAUL-DT196 -ENGINE | Engine Assembly Caterpillar 3516B | 85161 | 14148 | 7500
500051994 | CLB-MP-HAUL-DT196 | DT196 Lubrication & Mechanical Services | 85161 | 85161 | 7500
500051993 | CLB-MP-HAUL-DT196 | Caterpillar 789D Haul Truck DT196 | 85161 | 85161 | 7500
500160293 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITRH | Air Tank Right | 82302 | 54081 | 7500
500160292 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK-AITLH | Air Tank Left | 82302 | 54081 | 7500
500147302 | CLB-MP-HAUL-DT195 -STRSYS-STACC | Steering Accumulator Rear | 29751 | 29751 | 7500
500147301 | CLB-MP-HAUL-DT195 -STRSYS-STACC | Steering Accumulator Middle | 29751 | 29751 | 7500
500147300 | CLB-MP-HAUL-DT195 -STRSYS-STACC | Steering Accumulator Front | 29751 | 29751 | 7500
500118574 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-AFRME | A Frame Housing | 82554 | 32729 | 7500
500117950 | CLB-MP-HAUL-DT195 -ELCTLV-LIGHT | Lighting Low Voltage | 82554 | 50171 | 7500
500117910 | CLB-MP-HAUL-DT195 -ELCTLV-HARNS | Electrical Harness | 82554 | 50171 | 7500
500117870 | CLB-MP-HAUL-DT195 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 82554 | 50171 | 7500
500117434 | CLB-MP-HAUL-DT195 -ELCTLV-LIGHT-AHSYS | AHS Lights | 82554 | 50171 | 7500
500117314 | CLB-MP-HAUL-DT195 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 82554 | 50171 | 7500
500111236 | CLB-MP-HAUL-DT195 -STRUCT-RAXHO | Rear Axle Housing | 44413 | 44413 | 7500
500110566 | CLB-MP-HAUL-DT195 -GRSYST | Grease Lubrication System | 82554 | 11866 | 7500
500102816 | CLB-MP-HAUL-DT195 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 82554 | 20001 | 7500
500100643 | CLB-MP-HAUL-DT195 -TRNSYS | DT195 Transmission System | 82554 | 51258 | 7500
500081420 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 82554 | 23360 | 7500
500081280 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 82554 | 23360 | 7500
500079453 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN | Suspension Service | 82554 | 11212 | 7500
500078519 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 82554 | 29751 | 7500
500078482 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 82554 | 29751 | 7500
500061440 | CLB-MP-HAUL-DT195 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 82554 | 29751 | 7500
500061410 | CLB-MP-HAUL-DT195 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 82554 | 29751 | 7500
500061332 | CLB-MP-HAUL-DT195 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 82554 | 54345 | 7500
500061331 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-ELECT | Chassis Electrical System | 82554 | 29751 | 7500
500061330 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-ELECT | Cabin Electrical System | 82554 | 82554 | 7500
500061329 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 82554 | 15352 | 7500
500061328 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 82554 | 15352 | 7500
500061327 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 82554 | 15352 | 7500
500061326 | CLB-MP-HAUL-DT195 -STRSYS-STHLF-STRHO | Steering System Hoses | 82554 | 29751 | 7500
500061325 | CLB-MP-HAUL-DT195 -STRSYS-STLTR-STBST | Ball Studs | 82554 | 82554 | 7500
500061324 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 82554 | 29751 | 7500
500061323 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 82554 | 29751 | 7500
500061322 | CLB-MP-HAUL-DT195 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 82554 | 29751 | 7500
500061321 | CLB-MP-HAUL-DT195 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 82554 | 6982 | 7500
500061320 | CLB-MP-HAUL-DT195 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 82554 | 6982 | 7500
500061319 | CLB-MP-HAUL-DT195 -BRKSYS-BRVRL | Brake Relay Valve | 82554 | 18183 | 7500
500061317 | CLB-MP-HAUL-DT195 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 82554 | 29751 | 7500
500061316 | CLB-MP-HAUL-DT195 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 82554 | 29751 | 7500
500060133 | CLB-MP-HAUL-DT195 -STRSYS-STTNK | Tank Steering | 82554 | 82554 | 7500
500053858 | CLB-MP-HAUL-DT195 -BRKSYS-BRVLV | Valve Brake | 82554 | 6982 | 7500
500051992 | CLB-MP-HAUL-DT195 -MANGMT-UMMMC | Mine Monitoring and Control | 82554 | 82554 | 7500
500051991 | CLB-MP-HAUL-DT195 -MANGMT-UMTRN | Power Train Management System | 82554 | 82554 | 7500
500051990 | CLB-MP-HAUL-DT195 -MANGMT-UMENG | Engine Management System | 82554 | 82554 | 7500
500051989 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 82554 | 6982 | 7500
500051988 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 82530 | 6982 | 7500
500051987 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 82554 | 6982 | 7500
500051986 | CLB-MP-HAUL-DT195 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 82554 | 6982 | 7500
500051983 | CLB-MP-HAUL-DT195 -STRUCT-TRAYS | Tray | 82554 | 18183 | 7500
500051982 | CLB-MP-HAUL-DT195 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 82554 | 6982 | 7500
500051981 | CLB-MP-HAUL-DT195 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 82554 | 6982 | 7500
500051980 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-TAGLK | Tag Link | 82554 | 29751 | 7500
500051979 | CLB-MP-HAUL-DT195 -STRUCT-CHASS-AFRME | A Frame Bearing | 82554 | 11239 | 7500
500051978 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-SBELT | Seat Belt | 82554 | 82554 | 7500
500051977 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-SEATS | Operators Seat | 82554 | 14615 | 7500
500051976 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 82554 | 82554 | 7500
500051975 | CLB-MP-HAUL-DT195 -STRUCT-CABIN-AIRCN | Air Conditioning System | 82554 | 15352 | 7500
500051974 | CLB-MP-HAUL-DT195 -STRUCT-CABIN | Operators Cabin | 82554 | 29751 | 7500
500051973 | CLB-MP-HAUL-DT195 -PNEUMC-START | Air Starter | 82554 | 6982 | 7500
500051972 | CLB-MP-HAUL-DT195 -PNEUMC-AIRDR | Air Drier | 82554 | 29751 | 7500
500051971 | CLB-MP-HAUL-DT195 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 82554 | 82554 | 7500
500051970 | CLB-MP-HAUL-DT195 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 82554 | 82554 | 7500
500051969 | CLB-MP-HAUL-DT195 -PNEUMC-PNTNK | No Not Use | 82554 | 54333 | 7500
500051968 | CLB-MP-HAUL-DT195 -GRSYST-ALCON | Auto Lube Controller | 82554 | 82554 | 7500
500051967 | CLB-MP-HAUL-DT195 -GRSYST-ALBPP | Auto Lube Pump | 82554 | 82554 | 7500
500051966 | CLB-MP-HAUL-DT195 -GRSYST-GRTNK | Auto Lube Resevoir | 82554 | 82554 | 7500
500051965 | CLB-MP-HAUL-DT195 -GRSYST-GRINJ | Auto Lube Injectors | 82554 | 82554 | 7500
500051964 | CLB-MP-HAUL-DT195 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 82554 | 1452 | 7500
500051963 | CLB-MP-HAUL-DT195 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 82554 | 5119 | 7500
500051962 | CLB-MP-HAUL-DT195 -HYDSYS-HOVLV | Valve Hoist | 82554 | 29751 | 7500
500051961 | CLB-MP-HAUL-DT195 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 82554 | 82554 | 7500
500051960 | CLB-MP-HAUL-DT195 -HYDSYS-HDTNK | Tank Hydraulic | 82554 | 82554 | 7500
500051959 | CLB-MP-HAUL-DT195 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 82554 | 29751 | 7500
500051958 | CLB-MP-HAUL-DT195 -HYDSYS-HOPMP | Pump Hoist | 82554 | 6982 | 7500
500051957 | CLB-MP-HAUL-DT195 -HYDSYS | Hydraulic System | 82554 | 82554 | 7500
500051956 | CLB-MP-HAUL-DT195 -STRSYS-STCON-STCOL | Steering Column | 82554 | 82554 | 7500
500051955 | CLB-MP-HAUL-DT195 -STRSYS-STCON-STWHL | Steering Wheel | 82554 | 82554 | 7500
500051954 | CLB-MP-HAUL-DT195 -STRSYS-STLTR | Steering Linkages and Tie Rods | 82554 | 14001 | 7500
500051953 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 82554 | 29751 | 7500
500051952 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 82554 | 29751 | 7500
500051951 | CLB-MP-HAUL-DT195 -STRSYS-STACC-SACCF | Accumulator Steering Front | 82554 | 29751 | 7500
500051950 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 82554 | 14001 | 7500
500051949 | CLB-MP-HAUL-DT195 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 82554 | 14001 | 7500
500051948 | CLB-MP-HAUL-DT195 -STRSYS-STVLV | Valve Steering | 82554 | 29751 | 7500
500051947 | CLB-MP-HAUL-DT195 -STRSYS-STHMU | Steering HMU | 82554 | 14001 | 7500
500051946 | CLB-MP-HAUL-DT195 -STRSYS-STPMP | Pump Steering | 82554 | 14001 | 7500
500051945 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 82554 | 18183 | 7500
500051944 | CLB-MP-HAUL-DT195 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 82554 | 18183 | 7500
500051943 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 82554 | 29751 | 7500
500051942 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 82554 | 29751 | 7500
500051941 | CLB-MP-HAUL-DT195 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 82554 | 14000 | 7500
500051940 | CLB-MP-HAUL-DT195 -BRKSYS-BACCM | Brake Accumulator | 82554 | 29751 | 7500
500051939 | CLB-MP-HAUL-DT195 -BRKSYS-BROCO | Brake Oil Cooler | 82554 | 82554 | 7500
500051938 | CLB-MP-HAUL-DT195 -BRKSYS-MERTR | Mechanical Retarder | 82554 | 82554 | 7500
500051937 | CLB-MP-HAUL-DT195 -BRKSYS-BRVTR | Valve Brake Treadle | 82554 | 82554 | 7500
500051936 | CLB-MP-HAUL-DT195 -BRKSYS-HYFPP | Pump Brake Control | 82554 | 6982 | 7500
500051935 | CLB-MP-HAUL-DT195 -BRKSYS-PRKPP | Pump Park Brake Release | 82554 | 82554 | 7500
500051934 | CLB-MP-HAUL-DT195 -BRKSYS-BRPMP | Pump Brake | 82554 | 82554 | 7500
500051933 | CLB-MP-HAUL-DT195 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 82554 | 82554 | 7500
500051932 | CLB-MP-HAUL-DT195 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 82554 | 82554 | 7500
500051931 | CLB-MP-HAUL-DT195 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 82554 | 82554 | 7500
500051930 | CLB-MP-HAUL-DT195 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 82554 | 82554 | 7500
500051929 | CLB-MP-HAUL-DT195 -BRKSYS-SRVBK | Service Brake | 82554 | 82554 | 7500
500051928 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 82554 | 82554 | 7500
500051927 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 82554 | 82554 | 7500
500051926 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 82554 | 7002 | 7500
500051925 | CLB-MP-HAUL-DT195 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 82554 | 29751 | 7500
500051924 | CLB-MP-HAUL-DT195 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 82554 | 6941 | 7500
500051923 | CLB-MP-HAUL-DT195 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 82554 | 6982 | 7500
500051922 | CLB-MP-HAUL-DT195 -FDRSYS-DRLAX | Drive Line Axles | 82554 | 82554 | 7500
500051921 | CLB-MP-HAUL-DT195 -FDRSYS-DIFFL | Differential | 82554 | 6982 | 7500
500051920 | CLB-MP-HAUL-DT195 -FDRSYS-DRSHT | Transmission Drive Shaft | 82554 | 29751 | 7500
500051919 | CLB-MP-HAUL-DT195 -TRNSYS-TROLC | Oil Cooler Transmission | 82554 | 6982 | 7500
500051918 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 82554 | 6982 | 7500
500051917 | CLB-MP-HAUL-DT195 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 82554 | 6982 | 7500
500051916 | CLB-MP-HAUL-DT195 -TRNSYS-TRANS | Transmission | 82554 | 6982 | 7500
500051915 | CLB-MP-HAUL-DT195 -TRNSYS-TRQUE | Torque Converter | 82554 | 6982 | 7500
500051914 | CLB-MP-HAUL-DT195 -ELCTLV-CHARG-BATTY | Batteries | 82554 | 82554 | 7500
500051913 | CLB-MP-HAUL-DT195 -ELCTLV-CHARG-ALTER | Alternator 24V | 82554 | 6982 | 7500
500051912 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 82554 | 12514 | 7500
500051911 | CLB-MP-HAUL-DT195 -ENGINE-PMPDR | Pump Drive | 82554 | 6982 | 7500
500051910 | CLB-MP-HAUL-DT195 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 82554 | 6982 | 7500
500051909 | CLB-MP-HAUL-DT195 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 82554 | 6982 | 7500
500051908 | CLB-MP-HAUL-DT195 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 82554 | 6982 | 7500
500051907 | CLB-MP-HAUL-DT195 -ENGINE-FUSYS-FULTK | Fuel Tank | 82554 | 54345 | 7500
500051906 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-EXHST | Exhaust System | 82554 | 82554 | 7500
500051905 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-AFTER | Aftercooler | 82554 | 82554 | 7500
500051904 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 82554 | 6982 | 7500
500051903 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 82554 | 6982 | 7500
500051902 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 82554 | 6982 | 7500
500051901 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 82554 | 6982 | 7500
500051900 | CLB-MP-HAUL-DT195 -ENGINE-INTEX-AIRFL | Air Filtration System | 82554 | 82554 | 7500
500051899 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-THERM | Thermostats/Regulators | 82554 | 6982 | 7500
500051898 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-BELTS | Fan Belts Engine | 82554 | 82554 | 7500
500051897 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 82554 | 6982 | 7500
500051896 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-COFAN | Fan Cooling System | 82554 | 6982 | 7500
500051895 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-RADTR | Coolant Engine | 82554 | 82554 | 7400
500051894 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-RADTR | Radiator Engine | 82554 | 15319 | 7500
500051893 | CLB-MP-HAUL-DT195 -ENGINE-COSYS-WTRPP | Water Pump Engine | 82554 | 6982 | 7500
500051892 | CLB-MP-HAUL-DT195 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 82554 | 82554 | 7500
500051891 | CLB-MP-HAUL-DT195 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 82554 | 6982 | 7500
500051890 | CLB-MP-HAUL-DT195 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 82554 | 82554 | 7500
500051889 | CLB-MP-HAUL-DT195 -ENGINE-COMPR | Air Compressor | 82554 | 6982 | 7500
500051887 | CLB-MP-HAUL-DT195 -ENGINE | Engine Assembly Caterpillar 3516B | 82554 | 6982 | 7500
500051886 | CLB-MP-HAUL-DT195 | DT195 Lubrication & Mechanical Services | 82554 | 82554 | 7500
500051885 | CLB-MP-HAUL-DT195 | Caterpillar 789D Haul Truck DT195 | 82554 | 82554 | 7500
500160291 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITRH | Air Tank Right | 86244 | 37431 | 7500
500160290 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK-AITLH | Air Tank Left | 86244 | 37431 | 7500
500147298 | CLB-MP-HAUL-DT194 -STRSYS-STACC | Steering Accumulator Rear | 37638 | 37638 | 7500
500147297 | CLB-MP-HAUL-DT194 -STRSYS-STACC | Steering Accumulator Middle | 37638 | 37638 | 7500
500147296 | CLB-MP-HAUL-DT194 -STRSYS-STACC | Steering Accumulator Front | 37638 | 37638 | 7500
500118573 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-AFRME | A Frame Housing | 86451 | 44175 | 7500
500117949 | CLB-MP-HAUL-DT194 -ELCTLV-LIGHT | Lighting Low Voltage | 86451 | 46687 | 7500
500117909 | CLB-MP-HAUL-DT194 -ELCTLV-HARNS | Electrical Harness | 86451 | 46687 | 7500
500117869 | CLB-MP-HAUL-DT194 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 86451 | 46687 | 7500
500117433 | CLB-MP-HAUL-DT194 -ELCTLV-LIGHT-AHSYS | AHS Lights | 86451 | 46687 | 7500
500117313 | CLB-MP-HAUL-DT194 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 86451 | 46687 | 7500
500111235 | CLB-MP-HAUL-DT194 -STRUCT-RAXHO | Rear Axle Housing | 86451 | 15565 | 7500
500110565 | CLB-MP-HAUL-DT194 -GRSYST | Grease Lubrication System | 86451 | 41915 | 7500
500102815 | CLB-MP-HAUL-DT194 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 86451 | 15565 | 7500
500100642 | CLB-MP-HAUL-DT194 -TRNSYS | DT194 Transmission System | 86451 | 48264 | 7500
500081419 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 86451 | 24471 | 7500
500081279 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 86451 | 24471 | 7500
500079452 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN | Suspension Service | 86451 | 15565 | 7500
500078518 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 86451 | 15565 | 7500
500078481 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 86451 | 15565 | 7500
500061439 | CLB-MP-HAUL-DT194 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 86451 | 15565 | 7500
500061409 | CLB-MP-HAUL-DT194 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 86451 | 15565 | 7500
500061315 | CLB-MP-HAUL-DT194 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 86451 | 15565 | 7500
500061314 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-ELECT | Chassis Electrical System | 86451 | 37638 | 7500
500061313 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-ELECT | Cabin Electrical System | 86451 | 86451 | 7500
500061312 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 86451 | 86451 | 7500
500061311 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 86451 | 86451 | 7500
500061310 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 86451 | 86451 | 7500
500061309 | CLB-MP-HAUL-DT194 -STRSYS-STHLF-STRHO | Steering System Hoses | 86451 | 15565 | 7500
500061308 | CLB-MP-HAUL-DT194 -STRSYS-STLTR-STBST | Ball Studs | 86451 | 86451 | 7500
500061307 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 86451 | 15565 | 7500
500061306 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 86451 | 15565 | 7500
500061305 | CLB-MP-HAUL-DT194 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 86451 | 15565 | 7500
500061304 | CLB-MP-HAUL-DT194 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 86451 | 15565 | 7500
500061303 | CLB-MP-HAUL-DT194 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 86451 | 15565 | 7500
500061302 | CLB-MP-HAUL-DT194 -BRKSYS-BRVRL | Brake Relay Valve | 86451 | 4331 | 7500
500061300 | CLB-MP-HAUL-DT194 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 86451 | 15565 | 7500
500061299 | CLB-MP-HAUL-DT194 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 86451 | 15565 | 7500
500060132 | CLB-MP-HAUL-DT194 -STRSYS-STTNK | Tank Steering | 86451 | 86451 | 7500
500053857 | CLB-MP-HAUL-DT194 -BRKSYS-BRVLV | Valve Brake | 86451 | 15565 | 7500
500051884 | CLB-MP-HAUL-DT194 -MANGMT-UMMMC | Mine Monitoring and Control | 86451 | 86451 | 7500
500051883 | CLB-MP-HAUL-DT194 -MANGMT-UMTRN | Power Train Management System | 86451 | 86451 | 7500
500051882 | CLB-MP-HAUL-DT194 -MANGMT-UMENG | Engine Management System | 86451 | 86451 | 7500
500051881 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 86451 | 21176 | 7500
500051880 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 86451 | 21176 | 7500
500051879 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 86451 | 15565 | 7500
500051878 | CLB-MP-HAUL-DT194 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 86451 | 15565 | 7500
500051875 | CLB-MP-HAUL-DT194 -STRUCT-TRAYS | Tray | 86451 | 20417 | 7500
500051874 | CLB-MP-HAUL-DT194 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 86451 | 15565 | 7500
500051873 | CLB-MP-HAUL-DT194 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 88113 | 15565 | 7500
500051872 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-TAGLK | Tag Link | 86451 | 21176 | 7500
500051871 | CLB-MP-HAUL-DT194 -STRUCT-CHASS-AFRME | A Frame Bearing | 86451 | 21176 | 7500
500051870 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-SBELT | Seat Belt | 86451 | 86451 | 7500
500051869 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-SEATS | Operators Seat | 86451 | 22463 | 7500
500051868 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86451 | 86451 | 7500
500051867 | CLB-MP-HAUL-DT194 -STRUCT-CABIN-AIRCN | Air Conditioning System | 86451 | 4331 | 7500
500051866 | CLB-MP-HAUL-DT194 -STRUCT-CABIN | Operators Cabin | 86451 | 15565 | 7500
500051865 | CLB-MP-HAUL-DT194 -PNEUMC-START | Air Starter | 86451 | 4331 | 7500
500051864 | CLB-MP-HAUL-DT194 -PNEUMC-AIRDR | Air Drier | 86451 | 15565 | 7500
500051863 | CLB-MP-HAUL-DT194 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 86451 | 86451 | 7500
500051862 | CLB-MP-HAUL-DT194 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 86451 | 86451 | 7500
500051861 | CLB-MP-HAUL-DT194 -PNEUMC-PNTNK | No Not Use | 86451 | 37638 | 7500
500051860 | CLB-MP-HAUL-DT194 -GRSYST-ALCON | Auto Lube Controller | 86451 | 86451 | 7500
500051859 | CLB-MP-HAUL-DT194 -GRSYST-ALBPP | Auto Lube Pump | 86451 | 86451 | 7500
500051858 | CLB-MP-HAUL-DT194 -GRSYST-GRTNK | Auto Lube Resevoir | 86451 | 86451 | 7500
500051857 | CLB-MP-HAUL-DT194 -GRSYST-GRINJ | Auto Lube Injectors | 86451 | 86451 | 7500
500051856 | CLB-MP-HAUL-DT194 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 86451 | 15565 | 7500
500051855 | CLB-MP-HAUL-DT194 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 86451 | 15565 | 7500
500051854 | CLB-MP-HAUL-DT194 -HYDSYS-HOVLV | Valve Hoist | 86451 | 37638 | 7500
500051853 | CLB-MP-HAUL-DT194 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 86451 | 86451 | 7500
500051852 | CLB-MP-HAUL-DT194 -HYDSYS-HDTNK | Tank Hydraulic | 86451 | 86451 | 7500
500051851 | CLB-MP-HAUL-DT194 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 86451 | 15565 | 7500
500051850 | CLB-MP-HAUL-DT194 -HYDSYS-HOPMP | Pump Hoist | 86451 | 2190 | 7500
500051849 | CLB-MP-HAUL-DT194 -HYDSYS | Hydraulic System | 86451 | 86451 | 7500
500051848 | CLB-MP-HAUL-DT194 -STRSYS-STCON-STCOL | Steering Column | 86451 | 86451 | 7500
500051847 | CLB-MP-HAUL-DT194 -STRSYS-STCON-STWHL | Steering Wheel | 86451 | 86451 | 7500
500051846 | CLB-MP-HAUL-DT194 -STRSYS-STLTR | Steering Linkages and Tie Rods | 86451 | 25780 | 7500
500051845 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 86451 | 15565 | 7500
500051844 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 86451 | 15565 | 7500
500051843 | CLB-MP-HAUL-DT194 -STRSYS-STACC-SACCF | Accumulator Steering Front | 86451 | 15565 | 7500
500051842 | CLB-MP-HAUL-DT194 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 86451 | 56 | 7500
500051841 | CLB-MP-HAUL-DT194 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 86451 | 5774 | 7500
500051840 | CLB-MP-HAUL-DT194 -STRSYS-STVLV | Valve Steering | 86451 | 15565 | 7500
500051839 | CLB-MP-HAUL-DT194 -STRSYS-STHMU | Steering HMU | 86451 | 21821 | 7500
500051838 | CLB-MP-HAUL-DT194 -STRSYS-STPMP | Pump Steering | 86451 | 21821 | 7500
500051837 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 86451 | 15565 | 7500
500051836 | CLB-MP-HAUL-DT194 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 86451 | 15565 | 7500
500051835 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 86451 | 15565 | 7500
500051834 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 86451 | 15565 | 7500
500051833 | CLB-MP-HAUL-DT194 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 86451 | 15565 | 7500
500051832 | CLB-MP-HAUL-DT194 -BRKSYS-BACCM | Brake Accumulator | 86451 | 15565 | 7500
500051831 | CLB-MP-HAUL-DT194 -BRKSYS-BROCO | Brake Oil Cooler | 86451 | 61715 | 7500
500051830 | CLB-MP-HAUL-DT194 -BRKSYS-MERTR | Mechanical Retarder | 86451 | 86451 | 7500
500051829 | CLB-MP-HAUL-DT194 -BRKSYS-BRVTR | Valve Brake Treadle | 86451 | 86451 | 7500
500051828 | CLB-MP-HAUL-DT194 -BRKSYS-HYFPP | Pump Brake Control | 86451 | 8189 | 7500
500051827 | CLB-MP-HAUL-DT194 -BRKSYS-PRKPP | Pump Park Brake Release | 86451 | 86451 | 7500
500051826 | CLB-MP-HAUL-DT194 -BRKSYS-BRPMP | Pump Brake | 86451 | 86451 | 7500
500051825 | CLB-MP-HAUL-DT194 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 86451 | 86451 | 7500
500051824 | CLB-MP-HAUL-DT194 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 86451 | 86451 | 7500
500051823 | CLB-MP-HAUL-DT194 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 86451 | 86451 | 7500
500051822 | CLB-MP-HAUL-DT194 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 86451 | 86451 | 7500
500051821 | CLB-MP-HAUL-DT194 -BRKSYS-SRVBK | Service Brake | 86451 | 86451 | 7500
500051820 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 86451 | 86451 | 7500
500051819 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 86451 | 86451 | 7500
500051818 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 86451 | 4331 | 7500
500051817 | CLB-MP-HAUL-DT194 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 86451 | 15565 | 7500
500051816 | CLB-MP-HAUL-DT194 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 86451 | 16196 | 7500
500051815 | CLB-MP-HAUL-DT194 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 86451 | 19128 | 7500
500051814 | CLB-MP-HAUL-DT194 -FDRSYS-DRLAX | Drive Line Axles | 86451 | 86451 | 7500
500051813 | CLB-MP-HAUL-DT194 -FDRSYS-DIFFL | Differential | 86451 | 15565 | 7500
500051812 | CLB-MP-HAUL-DT194 -FDRSYS-DRSHT | Transmission Drive Shaft | 86451 | 26367 | 7500
500051811 | CLB-MP-HAUL-DT194 -TRNSYS-TROLC | Oil Cooler Transmission | 86451 | 15565 | 7500
500051810 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 86451 | 19761 | 7500
500051809 | CLB-MP-HAUL-DT194 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 86451 | 6933 | 7500
500051808 | CLB-MP-HAUL-DT194 -TRNSYS-TRANS | Transmission | 86451 | 2801 | 7500
500051807 | CLB-MP-HAUL-DT194 -TRNSYS-TRQUE | Torque Converter | 86451 | 15565 | 7500
500051806 | CLB-MP-HAUL-DT194 -ELCTLV-CHARG-BATTY | Batteries | 86451 | 86451 | 7500
500051805 | CLB-MP-HAUL-DT194 -ELCTLV-CHARG-ALTER | Alternator 24V | 86451 | 4331 | 7500
500051804 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 86451 | 15565 | 7500
500051803 | CLB-MP-HAUL-DT194 -ENGINE-PMPDR | Pump Drive | 86451 | 15565 | 7500
500051802 | CLB-MP-HAUL-DT194 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 86451 | 15565 | 7500
500051801 | CLB-MP-HAUL-DT194 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 86451 | 4331 | 7500
500051800 | CLB-MP-HAUL-DT194 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 86451 | 4331 | 7500
500051799 | CLB-MP-HAUL-DT194 -ENGINE-FUSYS-FULTK | Fuel Tank | 86451 | 15565 | 7500
500051798 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-EXHST | Exhaust System | 86451 | 86451 | 7500
500051797 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-AFTER | Aftercooler | 86451 | 86451 | 7500
500051796 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 86451 | 4331 | 7500
500051795 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 86451 | 4331 | 7500
500051794 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 86451 | 4331 | 7500
500051793 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 86451 | 4331 | 7500
500051792 | CLB-MP-HAUL-DT194 -ENGINE-INTEX-AIRFL | Air Filtration System | 86451 | 86451 | 7500
500051791 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-THERM | Thermostats/Regulators | 86451 | 4331 | 7500
500051790 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-BELTS | Fan Belts Engine | 86451 | 86451 | 7500
500051789 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 86428 | 4331 | 7500
500051788 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-COFAN | Fan Cooling System | 86451 | 15565 | 7500
500051787 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-RADTR | Coolant Engine | 86451 | 37638 | 7400
500051786 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-RADTR | Radiator Engine | 86451 | 15565 | 7500
500051785 | CLB-MP-HAUL-DT194 -ENGINE-COSYS-WTRPP | Water Pump Engine | 86451 | 4331 | 7500
500051784 | CLB-MP-HAUL-DT194 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 86451 | 86451 | 7500
500051783 | CLB-MP-HAUL-DT194 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 86451 | 15565 | 7500
500051782 | CLB-MP-HAUL-DT194 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 86451 | 86451 | 7500
500051781 | CLB-MP-HAUL-DT194 -ENGINE-COMPR | Air Compressor | 86451 | 4331 | 7500
500051779 | CLB-MP-HAUL-DT194 -ENGINE | Engine Assembly Caterpillar 3516B | 86451 | 15565 | 7500
500051778 | CLB-MP-HAUL-DT194 | DT194 Lubrication & Mechanical Services | 86451 | 86451 | 7500
500051777 | CLB-MP-HAUL-DT194 | Caterpillar 789D Haul Truck DT194 | 86451 | 86451 | 7500
500160289 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITRH | Air Tank Right | 82926 | 82926 | 7500
500160288 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK-AITLH | Air Tank Left | 82926 | 82926 | 7500
500147294 | CLB-MP-HAUL-DT193 -STRSYS-STACC | Steering Accumulator Rear | 35367 | 35367 | 7500
500147293 | CLB-MP-HAUL-DT193 -STRSYS-STACC | Steering Accumulator Middle | 35367 | 35367 | 7500
500147292 | CLB-MP-HAUL-DT193 -STRSYS-STACC | Steering Accumulator Front | 35367 | 35367 | 7500
500118572 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-AFRME | A Frame Housing | 83140 | 29332 | 7500
500117948 | CLB-MP-HAUL-DT193 -ELCTLV-LIGHT | Lighting Low Voltage | 83140 | 52644 | 7500
500117908 | CLB-MP-HAUL-DT193 -ELCTLV-HARNS | Electrical Harness | 83140 | 52644 | 7500
500117868 | CLB-MP-HAUL-DT193 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83140 | 52644 | 7500
500117432 | CLB-MP-HAUL-DT193 -ELCTLV-LIGHT-AHSYS | AHS Lights | 83140 | 52644 | 7500
500117312 | CLB-MP-HAUL-DT193 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 83140 | 52644 | 7500
500111234 | CLB-MP-HAUL-DT193 -STRUCT-RAXHO | Rear Axle Housing | 83140 | 39079 | 7500
500110564 | CLB-MP-HAUL-DT193 -GRSYST | Grease Lubrication System | 83140 | 11913 | 7500
500102814 | CLB-MP-HAUL-DT193 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83140 | 1989 | 7500
500100641 | CLB-MP-HAUL-DT193 -TRNSYS | DT193 Transmission System | 83140 | 47741 | 7500
500081418 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83140 | 21917 | 7500
500081278 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83140 | 21912 | 7500
500079451 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN | Suspension Service | 83140 | 13267 | 7500
500078517 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 83140 | 13282 | 7500
500078480 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 83140 | 13282 | 7500
500062728 | CLB-MP-HAUL-DT193 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83140 | 13282 | 7500
500062727 | CLB-MP-HAUL-DT193 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83140 | 13282 | 7500
500062726 | CLB-MP-HAUL-DT193 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 83140 | 13282 | 7500
500062725 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-ELECT | Chassis Electrical System | 83140 | 35367 | 7500
500062724 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83140 | 83140 | 7500
500062723 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83140 | 13282 | 7500
500062722 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 83140 | 13282 | 7500
500062721 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83140 | 13282 | 7500
500062720 | CLB-MP-HAUL-DT193 -STRSYS-STHLF-STRHO | Steering System Hoses | 83140 | 13282 | 7500
500062719 | CLB-MP-HAUL-DT193 -STRSYS-STLTR-STBST | Ball Studs | 83140 | 83140 | 7500
500062718 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 83140 | 13282 | 7500
500062717 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 83140 | 13282 | 7500
500062716 | CLB-MP-HAUL-DT193 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 83140 | 13282 | 7500
500062715 | CLB-MP-HAUL-DT193 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83140 | 13282 | 7500
500062714 | CLB-MP-HAUL-DT193 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83140 | 13282 | 7500
500062713 | CLB-MP-HAUL-DT193 -BRKSYS-BRVRL | Brake Relay Valve | 83140 | 13282 | 7500
500062711 | CLB-MP-HAUL-DT193 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83140 | 13282 | 7500
500062710 | CLB-MP-HAUL-DT193 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83140 | 13282 | 7500
500060131 | CLB-MP-HAUL-DT193 -STRSYS-STTNK | Tank Steering | 83140 | 83140 | 7500
500053856 | CLB-MP-HAUL-DT193 -BRKSYS-BRVLV | Valve Brake | 83140 | 13282 | 7500
500051776 | CLB-MP-HAUL-DT193 -MANGMT-UMMMC | Mine Monitoring and Control | 83140 | 83140 | 7500
500051775 | CLB-MP-HAUL-DT193 -MANGMT-UMTRN | Power Train Management System | 83140 | 83140 | 7500
500051774 | CLB-MP-HAUL-DT193 -MANGMT-UMENG | Engine Management System | 83140 | 83140 | 7500
500051773 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83140 | 13282 | 7500
500051772 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83140 | 13282 | 7500
500051771 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83140 | 15299 | 7500
500051770 | CLB-MP-HAUL-DT193 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83140 | 13282 | 7500
500051767 | CLB-MP-HAUL-DT193 -STRUCT-TRAYS | Tray | 83140 | 18782 | 7500
500051766 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83140 | 21307 | 7500
500051765 | CLB-MP-HAUL-DT193 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83140 | 16066 | 7500
500051764 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-TAGLK | Tag Link | 83140 | 13282 | 7500
500051763 | CLB-MP-HAUL-DT193 -STRUCT-CHASS-AFRME | A Frame Bearing | 83140 | 29332 | 7500
500051762 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-SBELT | Seat Belt | 83140 | 83140 | 7500
500051761 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-SEATS | Operators Seat | 83140 | 13282 | 7500
500051760 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83140 | 83140 | 7500
500051759 | CLB-MP-HAUL-DT193 -STRUCT-CABIN-AIRCN | Air Conditioning System | 83140 | 6169 | 7500
500051758 | CLB-MP-HAUL-DT193 -STRUCT-CABIN | Operators Cabin | 83140 | 13282 | 7500
500051757 | CLB-MP-HAUL-DT193 -PNEUMC-START | Air Starter | 83140 | 1989 | 7500
500051756 | CLB-MP-HAUL-DT193 -PNEUMC-AIRDR | Air Drier | 83140 | 27958 | 7500
500051755 | CLB-MP-HAUL-DT193 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 83140 | 83140 | 7500
500051754 | CLB-MP-HAUL-DT193 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 83140 | 83140 | 7500
500051753 | CLB-MP-HAUL-DT193 -PNEUMC-PNTNK | No Not Use | 83140 | 83140 | 7500
500051752 | CLB-MP-HAUL-DT193 -GRSYST-ALCON | Auto Lube Controller | 83140 | 83140 | 7500
500051751 | CLB-MP-HAUL-DT193 -GRSYST-ALBPP | Auto Lube Pump | 83140 | 1989 | 7500
500051750 | CLB-MP-HAUL-DT193 -GRSYST-GRTNK | Auto Lube Resevoir | 83140 | 83140 | 7500
500051749 | CLB-MP-HAUL-DT193 -GRSYST-GRINJ | Auto Lube Injectors | 83140 | 83140 | 7500
500051748 | CLB-MP-HAUL-DT193 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83140 | 13282 | 7500
500051747 | CLB-MP-HAUL-DT193 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83140 | 13282 | 7500
500051746 | CLB-MP-HAUL-DT193 -HYDSYS-HOVLV | Valve Hoist | 83140 | 35367 | 7500
500051745 | CLB-MP-HAUL-DT193 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83140 | 83140 | 7500
500051744 | CLB-MP-HAUL-DT193 -HYDSYS-HDTNK | Tank Hydraulic | 83140 | 83140 | 7500
500051743 | CLB-MP-HAUL-DT193 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 83140 | 13282 | 7500
500051742 | CLB-MP-HAUL-DT193 -HYDSYS-HOPMP | Pump Hoist | 83140 | 6169 | 7500
500051741 | CLB-MP-HAUL-DT193 -HYDSYS | Hydraulic System | 83140 | 83140 | 7500
500051740 | CLB-MP-HAUL-DT193 -STRSYS-STCON-STCOL | Steering Column | 83140 | 83140 | 7500
500051739 | CLB-MP-HAUL-DT193 -STRSYS-STCON-STWHL | Steering Wheel | 83140 | 83140 | 7500
500051738 | CLB-MP-HAUL-DT193 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83140 | 19357 | 7500
500051737 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83140 | 13282 | 7500
500051736 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83140 | 13282 | 7500
500051735 | CLB-MP-HAUL-DT193 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83140 | 13282 | 7500
500051734 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83140 | 8872 | 7500
500051733 | CLB-MP-HAUL-DT193 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83140 | 3346 | 7500
500051732 | CLB-MP-HAUL-DT193 -STRSYS-STVLV | Valve Steering | 83140 | 27982 | 7500
500051731 | CLB-MP-HAUL-DT193 -STRSYS-STHMU | Steering HMU | 83140 | 3268 | 7500
500051730 | CLB-MP-HAUL-DT193 -STRSYS-STPMP | Pump Steering | 83140 | 3268 | 7500
500051729 | CLB-MP-HAUL-DT193 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83140 | 13282 | 7500
500051728 | CLB-MP-HAUL-DT193 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83140 | 13282 | 7500
500051727 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 83140 | 13282 | 7500
500051726 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 83140 | 13282 | 7500
500051725 | CLB-MP-HAUL-DT193 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 83140 | 13282 | 7500
500051724 | CLB-MP-HAUL-DT193 -BRKSYS-BACCM | Brake Accumulator | 83140 | 13282 | 7500
500051723 | CLB-MP-HAUL-DT193 -BRKSYS-BROCO | Brake Oil Cooler | 83140 | 83140 | 7500
500051722 | CLB-MP-HAUL-DT193 -BRKSYS-MERTR | Mechanical Retarder | 83140 | 83140 | 7500
500051721 | CLB-MP-HAUL-DT193 -BRKSYS-BRVTR | Valve Brake Treadle | 83140 | 83140 | 7500
500051720 | CLB-MP-HAUL-DT193 -BRKSYS-HYFPP | Pump Brake Control | 83140 | 592 | 7500
500051719 | CLB-MP-HAUL-DT193 -BRKSYS-PRKPP | Pump Park Brake Release | 83140 | 83140 | 7500
500051718 | CLB-MP-HAUL-DT193 -BRKSYS-BRPMP | Pump Brake | 83140 | 83140 | 7500
500051717 | CLB-MP-HAUL-DT193 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83140 | 83140 | 7500
500051716 | CLB-MP-HAUL-DT193 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83140 | 83140 | 7500
500051715 | CLB-MP-HAUL-DT193 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83140 | 83140 | 7500
500051714 | CLB-MP-HAUL-DT193 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83140 | 83140 | 7500
500051713 | CLB-MP-HAUL-DT193 -BRKSYS-SRVBK | Service Brake | 83140 | 83140 | 7500
500051712 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83140 | 83140 | 7500
500051711 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83140 | 83140 | 7500
500051710 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 83140 | 13282 | 7500
500051709 | CLB-MP-HAUL-DT193 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83140 | 3268 | 7500
500051708 | CLB-MP-HAUL-DT193 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83140 | 10706 | 7500
500051707 | CLB-MP-HAUL-DT193 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83140 | 13282 | 7500
500051706 | CLB-MP-HAUL-DT193 -FDRSYS-DRLAX | Drive Line Axles | 83140 | 83140 | 7500
500051705 | CLB-MP-HAUL-DT193 -FDRSYS-DIFFL | Differential | 83140 | 13282 | 7500
500051704 | CLB-MP-HAUL-DT193 -FDRSYS-DRSHT | Transmission Drive Shaft | 83140 | 13282 | 7500
500051703 | CLB-MP-HAUL-DT193 -TRNSYS-TROLC | Oil Cooler Transmission | 83140 | 7523 | 7500
500051702 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83140 | 13282 | 7500
500051701 | CLB-MP-HAUL-DT193 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83140 | 6169 | 7500
500051700 | CLB-MP-HAUL-DT193 -TRNSYS-TRANS | Transmission | 83140 | 11983 | 7500
500051699 | CLB-MP-HAUL-DT193 -TRNSYS-TRQUE | Torque Converter | 83140 | 13282 | 7500
500051698 | CLB-MP-HAUL-DT193 -ELCTLV-CHARG-BATTY | Batteries | 83140 | 83140 | 7500
500051697 | CLB-MP-HAUL-DT193 -ELCTLV-CHARG-ALTER | Alternator 24V | 83140 | 1989 | 7500
500051696 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83140 | 1989 | 7500
500051695 | CLB-MP-HAUL-DT193 -ENGINE-PMPDR | Pump Drive | 83140 | 13282 | 7500
500051694 | CLB-MP-HAUL-DT193 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83140 | 13282 | 7500
500051693 | CLB-MP-HAUL-DT193 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83140 | 1989 | 7500
500051692 | CLB-MP-HAUL-DT193 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83140 | 1989 | 7500
500051691 | CLB-MP-HAUL-DT193 -ENGINE-FUSYS-FULTK | Fuel Tank | 83140 | 13282 | 7500
500051690 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-EXHST | Exhaust System | 83140 | 83140 | 7500
500051689 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-AFTER | Aftercooler | 83140 | 75827 | 7500
500051688 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 83140 | 1989 | 7500
500051687 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 83140 | 1989 | 7500
500051686 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 83140 | 1989 | 7500
500051685 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 83140 | 1989 | 7500
500051684 | CLB-MP-HAUL-DT193 -ENGINE-INTEX-AIRFL | Air Filtration System | 83140 | 83140 | 7500
500051683 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-THERM | Thermostats/Regulators | 83140 | 1989 | 7500
500051682 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-BELTS | Fan Belts Engine | 83140 | 83140 | 7500
500051681 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 83140 | 1989 | 7500
500051680 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-COFAN | Fan Cooling System | 83140 | 13282 | 7500
500051679 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-RADTR | Coolant Engine | 83140 | 35367 | 7400
500051678 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-RADTR | Radiator Engine | 83140 | 13282 | 7500
500051677 | CLB-MP-HAUL-DT193 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83140 | 1989 | 7500
500051676 | CLB-MP-HAUL-DT193 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83140 | 83140 | 7500
500051675 | CLB-MP-HAUL-DT193 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83140 | 13282 | 7500
500051674 | CLB-MP-HAUL-DT193 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83140 | 83140 | 7500
500051673 | CLB-MP-HAUL-DT193 -ENGINE-COMPR | Air Compressor | 83140 | 1989 | 7500
500051671 | CLB-MP-HAUL-DT193 -ENGINE | Engine Assembly Caterpillar 3516B | 83140 | 13282 | 7500
500051670 | CLB-MP-HAUL-DT193 | DT193 Lubrication & Mechanical Services | 83140 | 83140 | 7500
500051669 | CLB-MP-HAUL-DT193 | Caterpillar 789D Haul Truck DT193 | 83140 | 83140 | 7500
500160287 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITRH | Air Tank Right | 90973 | 42723 | 7500
500160286 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK-AITLH | Air Tank Left | 90973 | 42723 | 7500
500147290 | CLB-MP-HAUL-DT192 -STRSYS-STACC | Steering Accumulator Rear | 20531 | 20531 | 7500
500147289 | CLB-MP-HAUL-DT192 -STRSYS-STACC | Steering Accumulator Middle | 20531 | 20531 | 7500
500147288 | CLB-MP-HAUL-DT192 -STRSYS-STACC | Steering Accumulator Front | 20531 | 20531 | 7500
500118571 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-AFRME | A Frame Housing | 91174 | 25241 | 7500
500117947 | CLB-MP-HAUL-DT192 -ELCTLV-LIGHT | Lighting Low Voltage | 91174 | 44354 | 7500
500117907 | CLB-MP-HAUL-DT192 -ELCTLV-HARNS | Electrical Harness | 91174 | 44354 | 7500
500117867 | CLB-MP-HAUL-DT192 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 91174 | 44354 | 7500
500117431 | CLB-MP-HAUL-DT192 -ELCTLV-LIGHT-AHSYS | AHS Lights | 91174 | 44354 | 7500
500117311 | CLB-MP-HAUL-DT192 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 91174 | 44354 | 7500
500111233 | CLB-MP-HAUL-DT192 -STRUCT-RAXHO | Rear Axle Housing | 91174 | 42924 | 7500
500110563 | CLB-MP-HAUL-DT192 -GRSYST | Grease Lubrication System | 91174 | 19939 | 7500
500102813 | CLB-MP-HAUL-DT192 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 91174 | 7657 | 7500
500100640 | CLB-MP-HAUL-DT192 -TRNSYS | DT192 Transmission System | 91174 | 45312 | 7500
500081417 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 91174 | 20531 | 7500
500081277 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 91174 | 20531 | 7500
500079450 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN | Suspension Service | 91174 | 15811 | 7500
500078516 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 91174 | 20531 | 7500
500078479 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 91174 | 20531 | 7500
500061438 | CLB-MP-HAUL-DT192 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 91174 | 20531 | 7500
500061408 | CLB-MP-HAUL-DT192 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 91174 | 20531 | 7500
500061298 | CLB-MP-HAUL-DT192 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 91174 | 20531 | 7500
500061297 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-ELECT | Chassis Electrical System | 91174 | 20531 | 7500
500061296 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-ELECT | Cabin Electrical System | 91174 | 91174 | 7500
500061295 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 91174 | 20531 | 7500
500061294 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 91174 | 20531 | 7500
500061293 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 91174 | 20531 | 7500
500061292 | CLB-MP-HAUL-DT192 -STRSYS-STHLF-STRHO | Steering System Hoses | 91174 | 20531 | 7500
500061291 | CLB-MP-HAUL-DT192 -STRSYS-STLTR-STBST | Ball Studs | 91174 | 91174 | 7500
500061290 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 91174 | 20531 | 7500
500061289 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 91174 | 20531 | 7500
500061288 | CLB-MP-HAUL-DT192 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 91174 | 20531 | 7500
500061287 | CLB-MP-HAUL-DT192 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 91174 | 20531 | 7500
500061286 | CLB-MP-HAUL-DT192 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 91174 | 20531 | 7500
500061285 | CLB-MP-HAUL-DT192 -BRKSYS-BRVRL | Brake Relay Valve | 91174 | 1097 | 7500
500061283 | CLB-MP-HAUL-DT192 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 91174 | 20531 | 7500
500061282 | CLB-MP-HAUL-DT192 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 91174 | 20531 | 7500
500060130 | CLB-MP-HAUL-DT192 -STRSYS-STTNK | Tank Steering | 91174 | 66539 | 7500
500053855 | CLB-MP-HAUL-DT192 -BRKSYS-BRVLV | Valve Brake | 91174 | 20531 | 7500
500051668 | CLB-MP-HAUL-DT192 -MANGMT-UMMMC | Mine Monitoring and Control | 91174 | 91174 | 7500
500051667 | CLB-MP-HAUL-DT192 -MANGMT-UMTRN | Power Train Management System | 91174 | 91174 | 7500
500051666 | CLB-MP-HAUL-DT192 -MANGMT-UMENG | Engine Management System | 91174 | 91174 | 7500
500051665 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 91174 | 13039 | 7500
500051664 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 91174 | 5567 | 7500
500051663 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 91174 | 5567 | 7500
500051662 | CLB-MP-HAUL-DT192 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 91174 | 20531 | 7500
500051659 | CLB-MP-HAUL-DT192 -STRUCT-TRAYS | Tray | 91174 | 24141 | 7500
500051658 | CLB-MP-HAUL-DT192 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 91174 | 5567 | 7500
500051657 | CLB-MP-HAUL-DT192 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 91174 | 3163 | 7500
500051656 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-TAGLK | Tag Link | 91174 | 20531 | 7500
500051655 | CLB-MP-HAUL-DT192 -STRUCT-CHASS-AFRME | A Frame Bearing | 91174 | 25241 | 7500
500051654 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-SBELT | Seat Belt | 91174 | 50902 | 7500
500051653 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-SEATS | Operators Seat | 91174 | 35798 | 7500
500051652 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 91174 | 91174 | 7500
500051651 | CLB-MP-HAUL-DT192 -STRUCT-CABIN-AIRCN | Air Conditioning System | 91174 | 8325 | 7500
500051650 | CLB-MP-HAUL-DT192 -STRUCT-CABIN | Operators Cabin | 91174 | 20531 | 7500
500051649 | CLB-MP-HAUL-DT192 -PNEUMC-START | Air Starter | 91174 | 8325 | 7500
500051648 | CLB-MP-HAUL-DT192 -PNEUMC-AIRDR | Air Drier | 91174 | 20531 | 7500
500051647 | CLB-MP-HAUL-DT192 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 91174 | 91174 | 7500
500051646 | CLB-MP-HAUL-DT192 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 91174 | 91174 | 7500
500051645 | CLB-MP-HAUL-DT192 -PNEUMC-PNTNK | No Not Use | 91174 | 42924 | 7500
500051644 | CLB-MP-HAUL-DT192 -GRSYST-ALCON | Auto Lube Controller | 91174 | 91174 | 7500
500051643 | CLB-MP-HAUL-DT192 -GRSYST-ALBPP | Auto Lube Pump | 91174 | 48218 | 7500
500051642 | CLB-MP-HAUL-DT192 -GRSYST-GRTNK | Auto Lube Resevoir | 91174 | 91174 | 7500
500051641 | CLB-MP-HAUL-DT192 -GRSYST-GRINJ | Auto Lube Injectors | 91174 | 91174 | 7500
500051640 | CLB-MP-HAUL-DT192 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 91174 | 20531 | 7500
500051639 | CLB-MP-HAUL-DT192 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 91174 | 20531 | 7500
500051638 | CLB-MP-HAUL-DT192 -HYDSYS-HOVLV | Valve Hoist | 91174 | 20531 | 7500
500051637 | CLB-MP-HAUL-DT192 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 91174 | 91174 | 7500
500051636 | CLB-MP-HAUL-DT192 -HYDSYS-HDTNK | Tank Hydraulic | 91174 | 66539 | 7500
500051635 | CLB-MP-HAUL-DT192 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 91174 | 20531 | 7500
500051634 | CLB-MP-HAUL-DT192 -HYDSYS-HOPMP | Pump Hoist | 91174 | 6298 | 7500
500051633 | CLB-MP-HAUL-DT192 -HYDSYS | Hydraulic System | 91174 | 91174 | 7500
500051632 | CLB-MP-HAUL-DT192 -STRSYS-STCON-STCOL | Steering Column | 132025 | 91523 | 7500
500051631 | CLB-MP-HAUL-DT192 -STRSYS-STCON-STWHL | Steering Wheel | 91174 | 91174 | 7500
500051630 | CLB-MP-HAUL-DT192 -STRSYS-STLTR | Steering Linkages and Tie Rods | 91174 | 27983 | 7500
500051629 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 91174 | 20531 | 7500
500051628 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 91174 | 20531 | 7500
500051627 | CLB-MP-HAUL-DT192 -STRSYS-STACC-SACCF | Accumulator Steering Front | 91174 | 20531 | 7500
500051626 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 91174 | 24285 | 7500
500051625 | CLB-MP-HAUL-DT192 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 91174 | 12341 | 7500
500051624 | CLB-MP-HAUL-DT192 -STRSYS-STVLV | Valve Steering | 91174 | 1097 | 7500
500051623 | CLB-MP-HAUL-DT192 -STRSYS-STHMU | Steering HMU | 91174 | 27983 | 7500
500051622 | CLB-MP-HAUL-DT192 -STRSYS-STPMP | Pump Steering | 91174 | 9223 | 7500
500051621 | CLB-MP-HAUL-DT192 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 91174 | 1097 | 7500
500051620 | CLB-MP-HAUL-DT192 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 91174 | 1097 | 7500
500051619 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 91174 | 20531 | 7500
500051618 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 91174 | 20531 | 7500
500051617 | CLB-MP-HAUL-DT192 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 91174 | 20531 | 7500
500051616 | CLB-MP-HAUL-DT192 -BRKSYS-BACCM | Brake Accumulator | 91174 | 20531 | 7500
500051615 | CLB-MP-HAUL-DT192 -BRKSYS-BROCO | Brake Oil Cooler | 91174 | 66539 | 7500
500051614 | CLB-MP-HAUL-DT192 -BRKSYS-MERTR | Mechanical Retarder | 91174 | 91174 | 7500
500051613 | CLB-MP-HAUL-DT192 -BRKSYS-BRVTR | Valve Brake Treadle | 91174 | 66539 | 7500
500051612 | CLB-MP-HAUL-DT192 -BRKSYS-HYFPP | Pump Brake Control | 91174 | 19917 | 7500
500051611 | CLB-MP-HAUL-DT192 -BRKSYS-PRKPP | Pump Park Brake Release | 91174 | 91174 | 7500
500051610 | CLB-MP-HAUL-DT192 -BRKSYS-BRPMP | Pump Brake | 91174 | 6298 | 7500
500051609 | CLB-MP-HAUL-DT192 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 91174 | 66539 | 7500
500051608 | CLB-MP-HAUL-DT192 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 91174 | 66539 | 7500
500051607 | CLB-MP-HAUL-DT192 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 91174 | 66539 | 7500
500051606 | CLB-MP-HAUL-DT192 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 91174 | 66539 | 7500
500051605 | CLB-MP-HAUL-DT192 -BRKSYS-SRVBK | Service Brake | 91174 | 91174 | 7500
500051604 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 91174 | 91174 | 7500
500051603 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 91174 | 91174 | 7500
500051602 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 91174 | 7657 | 7500
500051601 | CLB-MP-HAUL-DT192 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 91174 | 20531 | 7500
500051600 | CLB-MP-HAUL-DT192 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 91174 | 20531 | 7500
500051599 | CLB-MP-HAUL-DT192 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 91174 | 20531 | 7500
500051598 | CLB-MP-HAUL-DT192 -FDRSYS-DRLAX | Drive Line Axles | 91174 | 91174 | 7500
500051597 | CLB-MP-HAUL-DT192 -FDRSYS-DIFFL | Differential | 91174 | 14420 | 7500
500051596 | CLB-MP-HAUL-DT192 -FDRSYS-DRSHT | Transmission Drive Shaft | 91174 | 30870 | 7500
500051595 | CLB-MP-HAUL-DT192 -TRNSYS-TROLC | Oil Cooler Transmission | 91174 | 20531 | 7500
500051594 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 91174 | 6298 | 7500
500051593 | CLB-MP-HAUL-DT192 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 91174 | 7657 | 7500
500051592 | CLB-MP-HAUL-DT192 -TRNSYS-TRANS | Transmission | 91174 | 15068 | 7500
500051591 | CLB-MP-HAUL-DT192 -TRNSYS-TRQUE | Torque Converter | 91174 | 6298 | 7500
500051590 | CLB-MP-HAUL-DT192 -ELCTLV-CHARG-BATTY | Batteries | 91174 | 91174 | 7500
500051589 | CLB-MP-HAUL-DT192 -ELCTLV-CHARG-ALTER | Alternator 24V | 91174 | 8325 | 7500
500051588 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 91174 | 20531 | 7500
500051587 | CLB-MP-HAUL-DT192 -ENGINE-PMPDR | Pump Drive | 91174 | 20531 | 7500
500051586 | CLB-MP-HAUL-DT192 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 91174 | 20531 | 7500
500051585 | CLB-MP-HAUL-DT192 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 91174 | 8325 | 7500
500051584 | CLB-MP-HAUL-DT192 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 91174 | 8325 | 7500
500051583 | CLB-MP-HAUL-DT192 -ENGINE-FUSYS-FULTK | Fuel Tank | 91174 | 20531 | 7500
500051582 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-EXHST | Exhaust System | 91174 | 91174 | 7500
500051581 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-AFTER | Aftercooler | 91174 | 66539 | 7500
500051580 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 91174 | 8325 | 7500
500051579 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 91174 | 8325 | 7500
500051578 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 91174 | 8325 | 7500
500051577 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 91174 | 8325 | 7500
500051576 | CLB-MP-HAUL-DT192 -ENGINE-INTEX-AIRFL | Air Filtration System | 91174 | 91174 | 7500
500051575 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-THERM | Thermostats/Regulators | 91174 | 8325 | 7500
500051574 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-BELTS | Fan Belts Engine | 91174 | 91174 | 7500
500051573 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 91174 | 8325 | 7500
500051572 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-COFAN | Fan Cooling System | 91174 | 20531 | 7500
500051571 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-RADTR | Coolant Engine | 91174 | 20531 | 7400
500051570 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-RADTR | Radiator Engine | 91174 | 20531 | 7500
500051569 | CLB-MP-HAUL-DT192 -ENGINE-COSYS-WTRPP | Water Pump Engine | 91174 | 8325 | 7500
500051568 | CLB-MP-HAUL-DT192 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 91174 | 66539 | 7500
500051567 | CLB-MP-HAUL-DT192 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 91174 | 13729 | 7500
500051566 | CLB-MP-HAUL-DT192 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 91174 | 66539 | 7500
500051565 | CLB-MP-HAUL-DT192 -ENGINE-COMPR | Air Compressor | 91174 | 8325 | 7500
500051563 | CLB-MP-HAUL-DT192 -ENGINE | Engine Assembly Caterpillar 3516B | 91174 | 20531 | 7500
500051562 | CLB-MP-HAUL-DT192 | DT192 Lubrication & Mechanical Services | 91174 | 91174 | 7500
500051561 | CLB-MP-HAUL-DT192 | Caterpillar 789D Haul Truck DT192 | 91174 | 91174 | 7500
500160285 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITRH | Air Tank Right | 86814 | 15453 | 7500
500160284 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK-AITLH | Air Tank Left | 86814 | 15453 | 7500
500147286 | CLB-MP-HAUL-DT191 -STRSYS-STACC | Steering Accumulator Rear | 37615 | 37615 | 7500
500147285 | CLB-MP-HAUL-DT191 -STRSYS-STACC | Steering Accumulator Middle | 37615 | 37615 | 7500
500147284 | CLB-MP-HAUL-DT191 -STRSYS-STACC | Steering Accumulator Front | 37615 | 37615 | 7500
500118570 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-AFRME | A Frame Housing | 87047 | 40828 | 7500
500117946 | CLB-MP-HAUL-DT191 -ELCTLV-LIGHT | Lighting Low Voltage | 87047 | 53732 | 7500
500117906 | CLB-MP-HAUL-DT191 -ELCTLV-HARNS | Electrical Harness | 87047 | 53732 | 7500
500117866 | CLB-MP-HAUL-DT191 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 87047 | 53732 | 7500
500117430 | CLB-MP-HAUL-DT191 -ELCTLV-LIGHT-AHSYS | AHS Lights | 87047 | 53732 | 7500
500117310 | CLB-MP-HAUL-DT191 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 87047 | 53732 | 7500
500111232 | CLB-MP-HAUL-DT191 -STRUCT-RAXHO | Rear Axle Housing | 87047 | 40828 | 7500
500110562 | CLB-MP-HAUL-DT191 -GRSYST | Grease Lubrication System | 87047 | 14310 | 7500
500102812 | CLB-MP-HAUL-DT191 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 87047 | 15686 | 7500
500100639 | CLB-MP-HAUL-DT191 -TRNSYS | DT191 Transmission System | 87047 | 50285 | 7500
500081416 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 87047 | 23692 | 7500
500081276 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 87047 | 23692 | 7500
500079449 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN | Suspension Service | 87047 | 15686 | 7500
500078515 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 87047 | 15686 | 7500
500078478 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 87047 | 15686 | 7500
500061437 | CLB-MP-HAUL-DT191 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 87047 | 15686 | 7500
500061407 | CLB-MP-HAUL-DT191 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 87047 | 15686 | 7500
500061281 | CLB-MP-HAUL-DT191 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 87047 | 15686 | 7500
500061280 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-ELECT | Chassis Electrical System | 87047 | 37615 | 7500
500061279 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-ELECT | Cabin Electrical System | 87047 | 87047 | 7500
500061278 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 87047 | 15686 | 7500
500061277 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 87047 | 15686 | 7500
500061276 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 87047 | 15686 | 7500
500061275 | CLB-MP-HAUL-DT191 -STRSYS-STHLF-STRHO | Steering System Hoses | 87047 | 15686 | 7500
500061274 | CLB-MP-HAUL-DT191 -STRSYS-STLTR-STBST | Ball Studs | 87047 | 87047 | 7500
500061273 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 87047 | 15686 | 7500
500061272 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 87047 | 15686 | 7500
500061271 | CLB-MP-HAUL-DT191 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 87047 | 15686 | 7500
500061270 | CLB-MP-HAUL-DT191 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 87047 | 15686 | 7500
500061269 | CLB-MP-HAUL-DT191 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 87047 | 15686 | 7500
500061268 | CLB-MP-HAUL-DT191 -BRKSYS-BRVRL | Brake Relay Valve | 87047 | 15686 | 7500
500061266 | CLB-MP-HAUL-DT191 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 87047 | 15686 | 7500
500061265 | CLB-MP-HAUL-DT191 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 87047 | 15686 | 7500
500060129 | CLB-MP-HAUL-DT191 -STRSYS-STTNK | Tank Steering | 87047 | 87047 | 7500
500053854 | CLB-MP-HAUL-DT191 -BRKSYS-BRVLV | Valve Brake | 87047 | 19116 | 7500
500051560 | CLB-MP-HAUL-DT191 -MANGMT-UMMMC | Mine Monitoring and Control | 87047 | 87047 | 7500
500051559 | CLB-MP-HAUL-DT191 -MANGMT-UMTRN | Power Train Management System | 87047 | 87047 | 7500
500051558 | CLB-MP-HAUL-DT191 -MANGMT-UMENG | Engine Management System | 87047 | 87047 | 7500
500051557 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 87047 | 21779 | 7500
500051556 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 87047 | 15686 | 7500
500051555 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 87047 | 15686 | 7500
500051554 | CLB-MP-HAUL-DT191 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 87047 | 15686 | 7500
500051551 | CLB-MP-HAUL-DT191 -STRUCT-TRAYS | Tray | 87047 | 27717 | 7500
500051550 | CLB-MP-HAUL-DT191 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 87047 | 15686 | 7500
500051549 | CLB-MP-HAUL-DT191 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 87047 | 15686 | 7500
500051548 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-TAGLK | Tag Link | 87047 | 15686 | 7500
500051547 | CLB-MP-HAUL-DT191 -STRUCT-CHASS-AFRME | A Frame Bearing | 87047 | 24289 | 7500
500051546 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-SBELT | Seat Belt | 87047 | 87047 | 7500
500051545 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-SEATS | Operators Seat | 87047 | 22425 | 7500
500051544 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 87047 | 87047 | 7500
500051543 | CLB-MP-HAUL-DT191 -STRUCT-CABIN-AIRCN | Air Conditioning System | 87047 | 15686 | 7500
500051542 | CLB-MP-HAUL-DT191 -STRUCT-CABIN | Operators Cabin | 87047 | 15686 | 7500
500051541 | CLB-MP-HAUL-DT191 -PNEUMC-START | Air Starter | 87047 | 3836 | 7500
500051540 | CLB-MP-HAUL-DT191 -PNEUMC-AIRDR | Air Drier | 87047 | 15686 | 7500
500051539 | CLB-MP-HAUL-DT191 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 87047 | 87047 | 7500
500051538 | CLB-MP-HAUL-DT191 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 87047 | 87047 | 7500
500051537 | CLB-MP-HAUL-DT191 -PNEUMC-PNTNK | No Not Use | 87047 | 15686 | 7500
500051536 | CLB-MP-HAUL-DT191 -GRSYST-ALCON | Auto Lube Controller | 87047 | 87047 | 7500
500051535 | CLB-MP-HAUL-DT191 -GRSYST-ALBPP | Auto Lube Pump | 87047 | 24282 | 7500
500051534 | CLB-MP-HAUL-DT191 -GRSYST-GRTNK | Auto Lube Resevoir | 87047 | 87047 | 7500
500051533 | CLB-MP-HAUL-DT191 -GRSYST-GRINJ | Auto Lube Injectors | 87047 | 87047 | 7500
500051532 | CLB-MP-HAUL-DT191 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 87047 | 15686 | 7500
500051531 | CLB-MP-HAUL-DT191 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 87047 | 15686 | 7500
500051530 | CLB-MP-HAUL-DT191 -HYDSYS-HOVLV | Valve Hoist | 87047 | 37615 | 7500
500051529 | CLB-MP-HAUL-DT191 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 87047 | 87047 | 7500
500051528 | CLB-MP-HAUL-DT191 -HYDSYS-HDTNK | Tank Hydraulic | 87047 | 87047 | 7500
500051527 | CLB-MP-HAUL-DT191 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 87047 | 15686 | 7500
500051526 | CLB-MP-HAUL-DT191 -HYDSYS-HOPMP | Pump Hoist | 87047 | 15686 | 7500
500051525 | CLB-MP-HAUL-DT191 -HYDSYS | Hydraulic System | 87047 | 87047 | 7500
500051524 | CLB-MP-HAUL-DT191 -STRSYS-STCON-STCOL | Steering Column | 87047 | 87047 | 7500
500051523 | CLB-MP-HAUL-DT191 -STRSYS-STCON-STWHL | Steering Wheel | 87047 | 87047 | 7500
500051522 | CLB-MP-HAUL-DT191 -STRSYS-STLTR | Steering Linkages and Tie Rods | 87047 | 22425 | 7500
500051521 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 87047 | 15686 | 7500
500051520 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 87047 | 15686 | 7500
500051519 | CLB-MP-HAUL-DT191 -STRSYS-STACC-SACCF | Accumulator Steering Front | 87047 | 15686 | 7500
500051518 | CLB-MP-HAUL-DT191 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 87047 | 5642 | 7500
500051517 | CLB-MP-HAUL-DT191 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 87047 | 5642 | 7500
500051516 | CLB-MP-HAUL-DT191 -STRSYS-STVLV | Valve Steering | 87047 | 15686 | 7500
500051515 | CLB-MP-HAUL-DT191 -STRSYS-STHMU | Steering HMU | 87047 | 22420 | 7500
500051514 | CLB-MP-HAUL-DT191 -STRSYS-STPMP | Pump Steering | 87047 | 6938 | 7500
500051513 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 87047 | 15686 | 7500
500051512 | CLB-MP-HAUL-DT191 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 87047 | 15686 | 7500
500051511 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 87047 | 15686 | 7500
500051510 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 87047 | 15686 | 7500
500051509 | CLB-MP-HAUL-DT191 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 87047 | 15686 | 7500
500051508 | CLB-MP-HAUL-DT191 -BRKSYS-BACCM | Brake Accumulator | 87047 | 15686 | 7500
500051507 | CLB-MP-HAUL-DT191 -BRKSYS-BROCO | Brake Oil Cooler | 87047 | 57580 | 7500
500051506 | CLB-MP-HAUL-DT191 -BRKSYS-MERTR | Mechanical Retarder | 87047 | 87047 | 7500
500051505 | CLB-MP-HAUL-DT191 -BRKSYS-BRVTR | Valve Brake Treadle | 87047 | 65047 | 7500
500051504 | CLB-MP-HAUL-DT191 -BRKSYS-HYFPP | Pump Brake Control | 87047 | 3166 | 7500
500051503 | CLB-MP-HAUL-DT191 -BRKSYS-PRKPP | Pump Park Brake Release | 87047 | 87047 | 7500
500051502 | CLB-MP-HAUL-DT191 -BRKSYS-BRPMP | Pump Brake | 87047 | 42643 | 7500
500051501 | CLB-MP-HAUL-DT191 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 87047 | 57580 | 7500
500051500 | CLB-MP-HAUL-DT191 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 87047 | 57580 | 7500
500051499 | CLB-MP-HAUL-DT191 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 87047 | 57580 | 7500
500051498 | CLB-MP-HAUL-DT191 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 87047 | 57580 | 7500
500051497 | CLB-MP-HAUL-DT191 -BRKSYS-SRVBK | Service Brake | 87047 | 87047 | 7500
500051496 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 87047 | 87047 | 7500
500051495 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 87047 | 87047 | 7500
500051494 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 87047 | 3203 | 7500
500051493 | CLB-MP-HAUL-DT191 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 87047 | 15686 | 7500
500051492 | CLB-MP-HAUL-DT191 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 87047 | 17070 | 7500
500051491 | CLB-MP-HAUL-DT191 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 87047 | 15686 | 7500
500051490 | CLB-MP-HAUL-DT191 -FDRSYS-DRLAX | Drive Line Axles | 87047 | 87047 | 7500
500051489 | CLB-MP-HAUL-DT191 -FDRSYS-DIFFL | Differential | 87047 | 34521 | 7500
500051488 | CLB-MP-HAUL-DT191 -FDRSYS-DRSHT | Transmission Drive Shaft | 87047 | 15686 | 7500
500051487 | CLB-MP-HAUL-DT191 -TRNSYS-TROLC | Oil Cooler Transmission | 87047 | 3873 | 7500
500051486 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 87047 | 15686 | 7500
500051485 | CLB-MP-HAUL-DT191 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 87047 | 3873 | 7500
500051484 | CLB-MP-HAUL-DT191 -TRNSYS-TRANS | Transmission | 87047 | 3873 | 7500
500051483 | CLB-MP-HAUL-DT191 -TRNSYS-TRQUE | Torque Converter | 87047 | 15686 | 7500
500051482 | CLB-MP-HAUL-DT191 -ELCTLV-CHARG-BATTY | Batteries | 87047 | 26731 | 7500
500051481 | CLB-MP-HAUL-DT191 -ELCTLV-CHARG-ALTER | Alternator 24V | 87047 | 3836 | 7500
500051480 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 87047 | 15686 | 7500
500051479 | CLB-MP-HAUL-DT191 -ENGINE-PMPDR | Pump Drive | 87047 | 15686 | 7500
500051478 | CLB-MP-HAUL-DT191 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 87047 | 15686 | 7500
500051477 | CLB-MP-HAUL-DT191 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 87047 | 3836 | 7500
500051476 | CLB-MP-HAUL-DT191 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 87047 | 3836 | 7500
500051475 | CLB-MP-HAUL-DT191 -ENGINE-FUSYS-FULTK | Fuel Tank | 87047 | 15686 | 7500
500051474 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-EXHST | Exhaust System | 87047 | 87047 | 7500
500051473 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-AFTER | Aftercooler | 87047 | 57580 | 7500
500051472 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 87047 | 3836 | 7500
500051471 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 87047 | 3836 | 7500
500051470 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 87047 | 3836 | 7500
500051469 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 87047 | 3836 | 7500
500051468 | CLB-MP-HAUL-DT191 -ENGINE-INTEX-AIRFL | Air Filtration System | 87047 | 57580 | 7500
500051467 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-THERM | Thermostats/Regulators | 87047 | 3836 | 7500
500051466 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-BELTS | Fan Belts Engine | 87047 | 57580 | 7500
500051465 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 87047 | 3836 | 7500
500051464 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-COFAN | Fan Cooling System | 87047 | 15686 | 7500
500051463 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-RADTR | Coolant Engine | 87047 | 37615 | 7400
500051462 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-RADTR | Radiator Engine | 87047 | 15686 | 7500
500051461 | CLB-MP-HAUL-DT191 -ENGINE-COSYS-WTRPP | Water Pump Engine | 87047 | 3836 | 7500
500051460 | CLB-MP-HAUL-DT191 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 87047 | 57580 | 7500
500051459 | CLB-MP-HAUL-DT191 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 87047 | 15686 | 7500
500051458 | CLB-MP-HAUL-DT191 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 87047 | 57580 | 7500
500051457 | CLB-MP-HAUL-DT191 -ENGINE-COMPR | Air Compressor | 87047 | 3836 | 7500
500051455 | CLB-MP-HAUL-DT191 -ENGINE | Engine Assembly Caterpillar 3516B | 87047 | 15686 | 7500
500051454 | CLB-MP-HAUL-DT191 | DT191 Lubrication & Mechanical Services | 87047 | 87047 | 7500
500051453 | CLB-MP-HAUL-DT191 | Caterpillar 789D Haul Truck DT191 | 87047 | 87047 | 7500
500160283 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITRH | Air Tank Right | 90436 | 17328 | 7500
500160282 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK-AITLH | Air Tank Left | 90436 | 17328 | 7500
500147282 | CLB-MP-HAUL-DT190 -STRSYS-STACC | Steering Accumulator Rear | 17590 | 17590 | 7500
500147281 | CLB-MP-HAUL-DT190 -STRSYS-STACC | Steering Accumulator Middle | 17590 | 17590 | 7500
500147280 | CLB-MP-HAUL-DT190 -STRSYS-STACC | Steering Accumulator Front | 17590 | 17590 | 7500
500118569 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-AFRME | A Frame Housing | 90698 | 90698 | 7500
500117945 | CLB-MP-HAUL-DT190 -ELCTLV-LIGHT | Lighting Low Voltage | 90698 | 46859 | 7500
500117905 | CLB-MP-HAUL-DT190 -ELCTLV-HARNS | Electrical Harness | 90698 | 46859 | 7500
500117865 | CLB-MP-HAUL-DT190 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 90698 | 46859 | 7500
500117429 | CLB-MP-HAUL-DT190 -ELCTLV-LIGHT-AHSYS | AHS Lights | 90698 | 46859 | 7500
500117309 | CLB-MP-HAUL-DT190 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 90698 | 46859 | 7500
500111231 | CLB-MP-HAUL-DT190 -STRUCT-RAXHO | Rear Axle Housing | 90698 | 64460 | 7500
500110561 | CLB-MP-HAUL-DT190 -GRSYST | Grease Lubrication System | 90698 | 10366 | 7500
500102811 | CLB-MP-HAUL-DT190 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 90698 | 17590 | 7500
500100638 | CLB-MP-HAUL-DT190 -TRNSYS | DT190 Transmission System | 90698 | 40868 | 7500
500081415 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 90698 | 24244 | 7500
500081275 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 90698 | 24244 | 7500
500079448 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN | Suspension Service | 90698 | 22083 | 7500
500078514 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 90698 | 17590 | 7500
500078477 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 90698 | 17590 | 7500
500061436 | CLB-MP-HAUL-DT190 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 90698 | 17590 | 7500
500061406 | CLB-MP-HAUL-DT190 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 90698 | 17590 | 7500
500061264 | CLB-MP-HAUL-DT190 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 90698 | 17590 | 7500
500061263 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-ELECT | Chassis Electrical System | 90698 | 40868 | 7500
500061262 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-ELECT | Cabin Electrical System | 90698 | 90698 | 7500
500061261 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 90698 | 17590 | 7500
500061260 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 90698 | 17590 | 7500
500061259 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 90698 | 17590 | 7500
500061258 | CLB-MP-HAUL-DT190 -STRSYS-STHLF-STRHO | Steering System Hoses | 90698 | 17590 | 7500
500061257 | CLB-MP-HAUL-DT190 -STRSYS-STLTR-STBST | Ball Studs | 90698 | 90698 | 7500
500061256 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 90698 | 17590 | 7500
500061255 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 90698 | 17590 | 7500
500061254 | CLB-MP-HAUL-DT190 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 90698 | 17590 | 7500
500061253 | CLB-MP-HAUL-DT190 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 90698 | 17590 | 7500
500061252 | CLB-MP-HAUL-DT190 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 90698 | 17590 | 7500
500061251 | CLB-MP-HAUL-DT190 -BRKSYS-BRVRL | Brake Relay Valve | 90698 | 17590 | 7500
500061249 | CLB-MP-HAUL-DT190 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 90698 | 17590 | 7500
500061248 | CLB-MP-HAUL-DT190 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 90698 | 17590 | 7500
500060128 | CLB-MP-HAUL-DT190 -STRSYS-STTNK | Tank Steering | 90698 | 90698 | 7500
500053853 | CLB-MP-HAUL-DT190 -BRKSYS-BRVLV | Valve Brake | 90698 | 17590 | 7500
500051452 | CLB-MP-HAUL-DT190 -MANGMT-UMMMC | Mine Monitoring and Control | 90698 | 90698 | 7500
500051451 | CLB-MP-HAUL-DT190 -MANGMT-UMTRN | Power Train Management System | 90698 | 90698 | 7500
500051450 | CLB-MP-HAUL-DT190 -MANGMT-UMENG | Engine Management System | 90698 | 90698 | 7500
500051449 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 90698 | 17590 | 7500
500051448 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 90698 | 17590 | 7500
500051447 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 90698 | 3515 | 7500
500051446 | CLB-MP-HAUL-DT190 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 90698 | 1469 | 7500
500051443 | CLB-MP-HAUL-DT190 -STRUCT-TRAYS | Tray | 90698 | 25577 | 7500
500051442 | CLB-MP-HAUL-DT190 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 90698 | 3515 | 7500
500051441 | CLB-MP-HAUL-DT190 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 90698 | 714 | 7500
500051440 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-TAGLK | Tag Link | 90698 | 17590 | 7500
500051439 | CLB-MP-HAUL-DT190 -STRUCT-CHASS-AFRME | A Frame Bearing | 90698 | 28545 | 7500
500051438 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-SBELT | Seat Belt | 90698 | 90698 | 7500
500051437 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-SEATS | Operators Seat | 90698 | 11866 | 7500
500051436 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 90698 | 90698 | 7500
500051435 | CLB-MP-HAUL-DT190 -STRUCT-CABIN-AIRCN | Air Conditioning System | 90698 | 6249 | 7500
500051434 | CLB-MP-HAUL-DT190 -STRUCT-CABIN | Operators Cabin | 90698 | 40868 | 7500
500051433 | CLB-MP-HAUL-DT190 -PNEUMC-START | Air Starter | 90698 | 6249 | 7500
500051432 | CLB-MP-HAUL-DT190 -PNEUMC-AIRDR | Air Drier | 90698 | 57343 | 7500
500051431 | CLB-MP-HAUL-DT190 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 90698 | 90698 | 7500
500051430 | CLB-MP-HAUL-DT190 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 90698 | 90698 | 7500
500051429 | CLB-MP-HAUL-DT190 -PNEUMC-PNTNK | No Not Use | 90698 | 17590 | 7500
500051428 | CLB-MP-HAUL-DT190 -GRSYST-ALCON | Auto Lube Controller | 90698 | 90698 | 7500
500051427 | CLB-MP-HAUL-DT190 -GRSYST-ALBPP | Auto Lube Pump | 90698 | 71639 | 7500
500051426 | CLB-MP-HAUL-DT190 -GRSYST-GRTNK | Auto Lube Resevoir | 90698 | 90698 | 7500
500051425 | CLB-MP-HAUL-DT190 -GRSYST-GRINJ | Auto Lube Injectors | 90698 | 90698 | 7500
500051424 | CLB-MP-HAUL-DT190 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 90698 | 23847 | 7500
500051423 | CLB-MP-HAUL-DT190 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 90698 | 8940 | 7500
500051422 | CLB-MP-HAUL-DT190 -HYDSYS-HOVLV | Valve Hoist | 90698 | 17590 | 7500
500051421 | CLB-MP-HAUL-DT190 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 90698 | 90698 | 7500
500051420 | CLB-MP-HAUL-DT190 -HYDSYS-HDTNK | Tank Hydraulic | 90698 | 90698 | 7500
500051419 | CLB-MP-HAUL-DT190 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 90698 | 17590 | 7500
500051418 | CLB-MP-HAUL-DT190 -HYDSYS-HOPMP | Pump Hoist | 90698 | 7441 | 7500
500051417 | CLB-MP-HAUL-DT190 -HYDSYS | Hydraulic System | 90698 | 90698 | 7500
500051416 | CLB-MP-HAUL-DT190 -STRSYS-STCON-STCOL | Steering Column | 90698 | 90698 | 7500
500051415 | CLB-MP-HAUL-DT190 -STRSYS-STCON-STWHL | Steering Wheel | 90698 | 90698 | 7500
500051414 | CLB-MP-HAUL-DT190 -STRSYS-STLTR | Steering Linkages and Tie Rods | 90698 | 24244 | 7500
500051413 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 90698 | 17590 | 7500
500051412 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 90698 | 17590 | 7500
500051411 | CLB-MP-HAUL-DT190 -STRSYS-STACC-SACCF | Accumulator Steering Front | 90698 | 17590 | 7500
500051410 | CLB-MP-HAUL-DT190 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 90698 | 2142 | 7500
500051409 | CLB-MP-HAUL-DT190 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 90698 | 2142 | 7500
500051408 | CLB-MP-HAUL-DT190 -STRSYS-STVLV | Valve Steering | 90698 | 28565 | 7500
500051407 | CLB-MP-HAUL-DT190 -STRSYS-STHMU | Steering HMU | 90698 | 8800 | 7500
500051406 | CLB-MP-HAUL-DT190 -STRSYS-STPMP | Pump Steering | 90698 | 10366 | 7500
500051405 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 90698 | 17590 | 7500
500051404 | CLB-MP-HAUL-DT190 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 90698 | 17590 | 7500
500051403 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 90698 | 17590 | 7500
500051402 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 90698 | 17590 | 7500
500051401 | CLB-MP-HAUL-DT190 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 90698 | 17590 | 7500
500051400 | CLB-MP-HAUL-DT190 -BRKSYS-BACCM | Brake Accumulator | 90698 | 17590 | 7500
500051399 | CLB-MP-HAUL-DT190 -BRKSYS-BROCO | Brake Oil Cooler | 90698 | 6249 | 7500
500051398 | CLB-MP-HAUL-DT190 -BRKSYS-MERTR | Mechanical Retarder | 90698 | 90698 | 7500
500051397 | CLB-MP-HAUL-DT190 -BRKSYS-BRVTR | Valve Brake Treadle | 90698 | 90698 | 7500
500051396 | CLB-MP-HAUL-DT190 -BRKSYS-HYFPP | Pump Brake Control | 90698 | 6776 | 7500
500051395 | CLB-MP-HAUL-DT190 -BRKSYS-PRKPP | Pump Park Brake Release | 90698 | 90698 | 7500
500051394 | CLB-MP-HAUL-DT190 -BRKSYS-BRPMP | Pump Brake | 90698 | 90698 | 7500
500051393 | CLB-MP-HAUL-DT190 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 90698 | 90698 | 7500
500051392 | CLB-MP-HAUL-DT190 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 90698 | 90698 | 7500
500051391 | CLB-MP-HAUL-DT190 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 90698 | 90698 | 7500
500051390 | CLB-MP-HAUL-DT190 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 90698 | 90698 | 7500
500051389 | CLB-MP-HAUL-DT190 -BRKSYS-SRVBK | Service Brake | 90698 | 90698 | 7500
500051388 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 90698 | 90698 | 7500
500051387 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 90698 | 90698 | 7500
500051386 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 90698 | 5026 | 7500
500051385 | CLB-MP-HAUL-DT190 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 90698 | 17590 | 7500
500051384 | CLB-MP-HAUL-DT190 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 90698 | 21431 | 7500
500051383 | CLB-MP-HAUL-DT190 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 90698 | 21431 | 7500
500051382 | CLB-MP-HAUL-DT190 -FDRSYS-DRLAX | Drive Line Axles | 90698 | 90698 | 7500
500051381 | CLB-MP-HAUL-DT190 -FDRSYS-DIFFL | Differential | 90698 | 21479 | 7500
500051380 | CLB-MP-HAUL-DT190 -FDRSYS-DRSHT | Transmission Drive Shaft | 90698 | 7441 | 7500
500051379 | CLB-MP-HAUL-DT190 -TRNSYS-TROLC | Oil Cooler Transmission | 90698 | 17590 | 7500
500051378 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 90698 | 6249 | 7500
500051377 | CLB-MP-HAUL-DT190 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 90698 | 6776 | 7500
500051376 | CLB-MP-HAUL-DT190 -TRNSYS-TRANS | Transmission | 90698 | 6250 | 7500
500051375 | CLB-MP-HAUL-DT190 -TRNSYS-TRQUE | Torque Converter | 90698 | 17590 | 7500
500051374 | CLB-MP-HAUL-DT190 -ELCTLV-CHARG-BATTY | Batteries | 90698 | 90698 | 7500
500051373 | CLB-MP-HAUL-DT190 -ELCTLV-CHARG-ALTER | Alternator 24V | 90698 | 6249 | 7500
500051372 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 90698 | 6249 | 7500
500051371 | CLB-MP-HAUL-DT190 -ENGINE-PMPDR | Pump Drive | 90698 | 17590 | 7500
500051370 | CLB-MP-HAUL-DT190 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 90698 | 17590 | 7500
500051369 | CLB-MP-HAUL-DT190 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 90698 | 6249 | 7500
500051368 | CLB-MP-HAUL-DT190 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 90698 | 6249 | 7500
500051367 | CLB-MP-HAUL-DT190 -ENGINE-FUSYS-FULTK | Fuel Tank | 90698 | 9317 | 7500
500051366 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-EXHST | Exhaust System | 90698 | 90698 | 7500
500051365 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-AFTER | Aftercooler | 90698 | 90698 | 7500
500051364 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 90698 | 6249 | 7500
500051363 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 90698 | 6249 | 7500
500051362 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 90698 | 17590 | 7500
500051361 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 90698 | 6249 | 7500
500051360 | CLB-MP-HAUL-DT190 -ENGINE-INTEX-AIRFL | Air Filtration System | 90698 | 90698 | 7500
500051359 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-THERM | Thermostats/Regulators | 90698 | 6249 | 7500
500051358 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-BELTS | Fan Belts Engine | 90698 | 90698 | 7500
500051357 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 90698 | 6249 | 7500
500051356 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-COFAN | Fan Cooling System | 90698 | 6249 | 7500
500051355 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-RADTR | Coolant Engine | 90698 | 17590 | 7400
500051354 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-RADTR | Radiator Engine | 90698 | 17590 | 7500
500051353 | CLB-MP-HAUL-DT190 -ENGINE-COSYS-WTRPP | Water Pump Engine | 90698 | 6249 | 7500
500051352 | CLB-MP-HAUL-DT190 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 90698 | 90698 | 7500
500051351 | CLB-MP-HAUL-DT190 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 90698 | 17590 | 7500
500051350 | CLB-MP-HAUL-DT190 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 90698 | 90698 | 7500
500051349 | CLB-MP-HAUL-DT190 -ENGINE-COMPR | Air Compressor | 90698 | 6249 | 7500
500051347 | CLB-MP-HAUL-DT190 -ENGINE | Engine Assembly Caterpillar 3516B | 90698 | 17590 | 7500
500051346 | CLB-MP-HAUL-DT190 | DT190 Lubrication & Mechanical Services | 90698 | 90698 | 7500
500051345 | CLB-MP-HAUL-DT190 | Caterpillar 789D Haul Truck DT190 | 90698 | 90698 | 7500
500160281 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITRH | Air Tank Right | 84322 | 84322 | 7500
500160280 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK-AITLH | Air Tank Left | 84322 | 84322 | 7500
500147278 | CLB-MP-HAUL-DT189 -STRSYS-STACC | Steering Accumulator Rear | 84546 | 36386 | 7500
500147277 | CLB-MP-HAUL-DT189 -STRSYS-STACC | Steering Accumulator Middle | 84546 | 36386 | 7500
500147276 | CLB-MP-HAUL-DT189 -STRSYS-STACC | Steering Accumulator Front | 84546 | 36386 | 7500
500118568 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-AFRME | A Frame Housing | 84546 | 36386 | 7500
500117944 | CLB-MP-HAUL-DT189 -ELCTLV-LIGHT | Lighting Low Voltage | 84546 | 53215 | 7500
500117904 | CLB-MP-HAUL-DT189 -ELCTLV-HARNS | Electrical Harness | 84546 | 53215 | 7500
500117864 | CLB-MP-HAUL-DT189 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84546 | 53215 | 7500
500117428 | CLB-MP-HAUL-DT189 -ELCTLV-LIGHT-AHSYS | AHS Lights | 84546 | 53215 | 7500
500117308 | CLB-MP-HAUL-DT189 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 84546 | 53215 | 7500
500111230 | CLB-MP-HAUL-DT189 -STRUCT-RAXHO | Rear Axle Housing | 84546 | 14655 | 7500
500110560 | CLB-MP-HAUL-DT189 -GRSYST | Grease Lubrication System | 84546 | 36386 | 7500
500102810 | CLB-MP-HAUL-DT189 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84546 | 3391 | 7500
500100637 | CLB-MP-HAUL-DT189 -TRNSYS | DT189 Transmission System | 84546 | 84546 | 7500
500081414 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84546 | 25091 | 7500
500081274 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84546 | 25091 | 7500
500079447 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN | Suspension | 84546 | 14655 | 7500
500078513 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 84546 | 14655 | 7500
500078476 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 84546 | 14655 | 7500
500062709 | CLB-MP-HAUL-DT189 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84546 | 14655 | 7500
500062708 | CLB-MP-HAUL-DT189 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84546 | 14655 | 7500
500062707 | CLB-MP-HAUL-DT189 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 84546 | 14655 | 7500
500062706 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-ELECT | Chassis Electrical System | 84546 | 36386 | 7500
500062705 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84546 | 84546 | 7500
500062704 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84546 | 14655 | 7500
500062703 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 84546 | 14655 | 7500
500062702 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84546 | 14655 | 7500
500062701 | CLB-MP-HAUL-DT189 -STRSYS-STHLF-STRHO | Steering System Hoses | 84546 | 14655 | 7500
500062700 | CLB-MP-HAUL-DT189 -STRSYS-STLTR-STBST | Ball Studs | 84546 | 84546 | 7500
500062699 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 84546 | 14655 | 7500
500062698 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 84546 | 14655 | 7500
500062697 | CLB-MP-HAUL-DT189 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 84546 | 14655 | 7500
500062696 | CLB-MP-HAUL-DT189 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84546 | 14655 | 7500
500062695 | CLB-MP-HAUL-DT189 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84546 | 14655 | 7500
500062694 | CLB-MP-HAUL-DT189 -BRKSYS-BRVRL | Brake Relay Valve | 84546 | 3391 | 7500
500062692 | CLB-MP-HAUL-DT189 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84546 | 14655 | 7500
500062691 | CLB-MP-HAUL-DT189 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84546 | 14655 | 7500
500060127 | CLB-MP-HAUL-DT189 -STRSYS-STTNK | Tank Steering | 84546 | 84546 | 7500
500053852 | CLB-MP-HAUL-DT189 -BRKSYS-BRVLV | Valve Brake | 84546 | 14655 | 7500
500051344 | CLB-MP-HAUL-DT189 -MANGMT-UMMMC | Mine Monitoring and Control | 84546 | 84546 | 7500
500051343 | CLB-MP-HAUL-DT189 -MANGMT-UMTRN | Power Train Management System | 84546 | 84546 | 7500
500051342 | CLB-MP-HAUL-DT189 -MANGMT-UMENG | Engine Management System | 84546 | 57499 | 7500
500051341 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84546 | 18522 | 7500
500051340 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84546 | 14655 | 7500
500051339 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84546 | 14655 | 7500
500051338 | CLB-MP-HAUL-DT189 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84546 | 14655 | 7500
500051335 | CLB-MP-HAUL-DT189 -STRUCT-TRAYS | Tray | 84546 | 27564 | 7500
500051334 | CLB-MP-HAUL-DT189 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84546 | 14655 | 7500
500051333 | CLB-MP-HAUL-DT189 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84546 | 14655 | 7500
500051332 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-TAGLK | Tag Link | 84546 | 14655 | 7500
500051331 | CLB-MP-HAUL-DT189 -STRUCT-CHASS-AFRME | A Frame Bearing | 84546 | 20986 | 7500
500051330 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-SBELT | Seat Belt | 84546 | 84546 | 7500
500051329 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-SEATS | Operators Seat | 84546 | 20986 | 7500
500051328 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84546 | 84546 | 7500
500051327 | CLB-MP-HAUL-DT189 -STRUCT-CABIN-AIRCN | Air Conditioning System | 84546 | 14655 | 7500
500051326 | CLB-MP-HAUL-DT189 -STRUCT-CABIN | Operators Cabin | 84546 | 14655 | 7500
500051325 | CLB-MP-HAUL-DT189 -PNEUMC-START | Air Starter | 84546 | 3417 | 7500
500051324 | CLB-MP-HAUL-DT189 -PNEUMC-AIRDR | Air Drier | 84546 | 14655 | 7500
500051323 | CLB-MP-HAUL-DT189 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 84546 | 84546 | 7500
500051322 | CLB-MP-HAUL-DT189 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 84546 | 84546 | 7500
500051321 | CLB-MP-HAUL-DT189 -PNEUMC-PNTNK | No Not Use | 84546 | 84546 | 7500
500051320 | CLB-MP-HAUL-DT189 -GRSYST-ALCON | Auto Lube Controller | 84546 | 84546 | 7500
500051319 | CLB-MP-HAUL-DT189 -GRSYST-ALBPP | Auto Lube Pump | 84546 | 27939 | 7500
500051318 | CLB-MP-HAUL-DT189 -GRSYST-GRTNK | Auto Lube Resevoir | 84546 | 84546 | 7500
500051317 | CLB-MP-HAUL-DT189 -GRSYST-GRINJ | Auto Lube Injectors | 84546 | 84546 | 7500
500051316 | CLB-MP-HAUL-DT189 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84546 | 14655 | 7500
500051315 | CLB-MP-HAUL-DT189 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84546 | 14655 | 7500
500051314 | CLB-MP-HAUL-DT189 -HYDSYS-HOVLV | Valve Hoist | 84546 | 36386 | 7500
500051313 | CLB-MP-HAUL-DT189 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84546 | 84546 | 7500
500051312 | CLB-MP-HAUL-DT189 -HYDSYS-HDTNK | Tank Hydraulic | 84546 | 14655 | 7500
500051311 | CLB-MP-HAUL-DT189 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 84546 | 14655 | 7500
500051310 | CLB-MP-HAUL-DT189 -HYDSYS-HOPMP | Pump Hoist | 84546 | 14655 | 7500
500051309 | CLB-MP-HAUL-DT189 -HYDSYS | Hydraulic System | 84546 | 84546 | 7500
500051308 | CLB-MP-HAUL-DT189 -STRSYS-STCON-STCOL | Steering Column | 84546 | 84546 | 7500
500051307 | CLB-MP-HAUL-DT189 -STRSYS-STCON-STWHL | Steering Wheel | 84546 | 84546 | 7500
500051306 | CLB-MP-HAUL-DT189 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84546 | 17061 | 7500
500051305 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84546 | 14655 | 7500
500051304 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84546 | 14655 | 7500
500051303 | CLB-MP-HAUL-DT189 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84546 | 14655 | 7500
500051302 | CLB-MP-HAUL-DT189 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84546 | 745 | 7500
500051301 | CLB-MP-HAUL-DT189 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84546 | 745 | 7500
500051300 | CLB-MP-HAUL-DT189 -STRSYS-STVLV | Valve Steering | 84546 | 14655 | 7500
500051299 | CLB-MP-HAUL-DT189 -STRSYS-STHMU | Steering HMU | 84546 | 17061 | 7500
500051298 | CLB-MP-HAUL-DT189 -STRSYS-STPMP | Pump Steering | 84546 | 718 | 7500
500051297 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84546 | 14655 | 7500
500051296 | CLB-MP-HAUL-DT189 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84546 | 14655 | 7500
500051295 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 84546 | 14655 | 7500
500051294 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 84546 | 14655 | 7500
500051293 | CLB-MP-HAUL-DT189 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 84546 | 14655 | 7500
500051292 | CLB-MP-HAUL-DT189 -BRKSYS-BACCM | Brake Accumulator | 84546 | 14655 | 7500
500051291 | CLB-MP-HAUL-DT189 -BRKSYS-BROCO | Brake Oil Cooler | 84546 | 84546 | 7500
500051290 | CLB-MP-HAUL-DT189 -BRKSYS-MERTR | Mechanical Retarder | 84546 | 84546 | 7500
500051289 | CLB-MP-HAUL-DT189 -BRKSYS-BRVTR | Valve Brake Treadle | 84546 | 84546 | 7500
500051288 | CLB-MP-HAUL-DT189 -BRKSYS-HYFPP | Pump Brake Control | 84546 | 3391 | 7500
500051287 | CLB-MP-HAUL-DT189 -BRKSYS-PRKPP | Pump Park Brake Release | 84546 | 84546 | 7500
500051286 | CLB-MP-HAUL-DT189 -BRKSYS-BRPMP | Pump Brake | 84546 | 17061 | 7500
500051285 | CLB-MP-HAUL-DT189 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84546 | 57499 | 7500
500051284 | CLB-MP-HAUL-DT189 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84546 | 57499 | 7500
500051283 | CLB-MP-HAUL-DT189 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84546 | 57499 | 7500
500051282 | CLB-MP-HAUL-DT189 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84546 | 57499 | 7500
500051281 | CLB-MP-HAUL-DT189 -BRKSYS-SRVBK | Service Brake | 84546 | 57499 | 7500
500051280 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84546 | 84546 | 7500
500051279 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84546 | 57499 | 7500
500051278 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 84546 | 3414 | 7500
500051277 | CLB-MP-HAUL-DT189 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84546 | 712 | 7500
500051276 | CLB-MP-HAUL-DT189 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84546 | 5379 | 7500
500051275 | CLB-MP-HAUL-DT189 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84546 | 5379 | 7500
500051274 | CLB-MP-HAUL-DT189 -FDRSYS-DRLAX | Drive Line Axles | 84546 | 57499 | 7500
500051273 | CLB-MP-HAUL-DT189 -FDRSYS-DIFFL | Differential | 84546 | 14655 | 7500
500051272 | CLB-MP-HAUL-DT189 -FDRSYS-DRSHT | Transmission Drive Shaft | 84546 | 14655 | 7500
500051271 | CLB-MP-HAUL-DT189 -TRNSYS-TROLC | Oil Cooler Transmission | 84546 | 14655 | 7500
500051270 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84546 | 14655 | 7500
500051269 | CLB-MP-HAUL-DT189 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84546 | 5964 | 7500
500051268 | CLB-MP-HAUL-DT189 -TRNSYS-TRANS | Transmission | 84546 | 14655 | 7500
500051267 | CLB-MP-HAUL-DT189 -TRNSYS-TRQUE | Torque Converter | 84546 | 14655 | 7500
500051266 | CLB-MP-HAUL-DT189 -ELCTLV-CHARG-BATTY | Batteries | 84546 | 84546 | 7500
500051265 | CLB-MP-HAUL-DT189 -ELCTLV-CHARG-ALTER | Alternator 24V | 84546 | 3417 | 7500
500051264 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84546 | 3391 | 7500
500051263 | CLB-MP-HAUL-DT189 -ENGINE-PMPDR | Pump Drive | 84546 | 14655 | 7500
500051262 | CLB-MP-HAUL-DT189 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84546 | 14655 | 7500
500051261 | CLB-MP-HAUL-DT189 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84546 | 3417 | 7500
500051260 | CLB-MP-HAUL-DT189 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84546 | 3417 | 7500
500051259 | CLB-MP-HAUL-DT189 -ENGINE-FUSYS-FULTK | Fuel Tank | 84546 | 14655 | 7500
500051258 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-EXHST | Exhaust System | 84546 | 57499 | 7500
500051257 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-AFTER | Aftercooler | 84546 | 14655 | 7500
500051256 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 84546 | 3417 | 7500
500051255 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 84546 | 3417 | 7500
500051254 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 84546 | 3417 | 7500
500051253 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 84546 | 3417 | 7500
500051252 | CLB-MP-HAUL-DT189 -ENGINE-INTEX-AIRFL | Air Filtration System | 84546 | 84546 | 7500
500051251 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-THERM | Thermostats/Regulators | 84546 | 3417 | 7500
500051250 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-BELTS | Fan Belts Engine | 84546 | 14655 | 7500
500051249 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 84546 | 3417 | 7500
500051248 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-COFAN | Fan Cooling System | 84546 | 14655 | 7500
500051247 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-RADTR | Coolant Engine | 84546 | 36386 | 7400
500051246 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-RADTR | Radiator Engine | 84546 | 14655 | 7500
500051245 | CLB-MP-HAUL-DT189 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84546 | 3417 | 7500
500051244 | CLB-MP-HAUL-DT189 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84546 | 14655 | 7500
500051243 | CLB-MP-HAUL-DT189 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84546 | 14655 | 7500
500051242 | CLB-MP-HAUL-DT189 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84546 | 14655 | 7500
500051241 | CLB-MP-HAUL-DT189 -ENGINE-COMPR | Air Compressor | 84546 | 3417 | 7500
500051239 | CLB-MP-HAUL-DT189 -ENGINE | Engine Assembly Caterpillar 3516B | 84546 | 14655 | 7500
500051238 | CLB-MP-HAUL-DT189 | DT189 Lubrication & Mechanical Services | 84546 | 84546 | 7500
500051237 | CLB-MP-HAUL-DT189 | Caterpillar 789D Haul Truck DT189 | 84546 | 84546 | 7500
500160279 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITRH | Air Tank Right | 83734 | 10797 | 7500
500160278 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK-AITLH | Air Tank Left | 83734 | 10797 | 7500
500147274 | CLB-MP-HAUL-DT188 -STRSYS-STACC | Steering Accumulator Rear | 33801 | 33801 | 7500
500147273 | CLB-MP-HAUL-DT188 -STRSYS-STACC | Steering Accumulator Middle | 33801 | 33801 | 7500
500147272 | CLB-MP-HAUL-DT188 -STRSYS-STACC | Steering Accumulator Front | 33801 | 33801 | 7500
500118567 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-AFRME | A Frame Housing | 83931 | 42933 | 7500
500117943 | CLB-MP-HAUL-DT188 -ELCTLV-LIGHT | Lighting Low Voltage | 83931 | 52332 | 7500
500117903 | CLB-MP-HAUL-DT188 -ELCTLV-HARNS | Electrical Harness | 83931 | 52332 | 7500
500117863 | CLB-MP-HAUL-DT188 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83931 | 52332 | 7500
500117427 | CLB-MP-HAUL-DT188 -ELCTLV-LIGHT-AHSYS | AHS Lights | 83931 | 52332 | 7500
500117307 | CLB-MP-HAUL-DT188 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 83931 | 52332 | 7500
500111229 | CLB-MP-HAUL-DT188 -STRUCT-RAXHO | Rear Axle Housing | 83931 | 42930 | 7500
500110559 | CLB-MP-HAUL-DT188 -GRSYST | Grease Lubrication System | 83931 | 6681 | 7500
500102809 | CLB-MP-HAUL-DT188 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83931 | 10994 | 7500
500100636 | CLB-MP-HAUL-DT188 -TRNSYS | DT188 Transmission System | 83931 | 43891 | 7500
500081413 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83931 | 23443 | 7500
500081273 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83931 | 23443 | 7500
500079446 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN | Suspension Service | 83931 | 10985 | 7500
500078512 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 83931 | 10994 | 7500
500078475 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 83931 | 10994 | 7500
500061435 | CLB-MP-HAUL-DT188 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83931 | 10994 | 7500
500061405 | CLB-MP-HAUL-DT188 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83931 | 10994 | 7500
500061247 | CLB-MP-HAUL-DT188 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 83931 | 10994 | 7500
500061246 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-ELECT | Chassis Electrical System | 83931 | 33801 | 7500
500061245 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83931 | 83931 | 7500
500061244 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83931 | 10994 | 7500
500061243 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 83931 | 10994 | 7500
500061242 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83931 | 10994 | 7500
500061241 | CLB-MP-HAUL-DT188 -STRSYS-STHLF-STRHO | Steering System Hoses | 83931 | 10994 | 7500
500061240 | CLB-MP-HAUL-DT188 -STRSYS-STLTR-STBST | Ball Studs | 83931 | 83931 | 7500
500061239 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 83931 | 10994 | 7500
500061238 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 83931 | 61120 | 7500
500061237 | CLB-MP-HAUL-DT188 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 83931 | 10994 | 7500
500061236 | CLB-MP-HAUL-DT188 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83931 | 10994 | 7500
500061235 | CLB-MP-HAUL-DT188 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83931 | 14100 | 7500
500061234 | CLB-MP-HAUL-DT188 -BRKSYS-BRVRL | Brake Relay Valve | 83931 | 10994 | 7500
500061232 | CLB-MP-HAUL-DT188 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83931 | 10994 | 7500
500061231 | CLB-MP-HAUL-DT188 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83931 | 10994 | 7500
500060126 | CLB-MP-HAUL-DT188 -STRSYS-STTNK | Tank Steering | 83931 | 83931 | 7500
500053851 | CLB-MP-HAUL-DT188 -BRKSYS-BRVLV | Valve Brake | 83931 | 10994 | 7500
500051236 | CLB-MP-HAUL-DT188 -MANGMT-UMMMC | Mine Monitoring and Control | 83931 | 83931 | 7500
500051235 | CLB-MP-HAUL-DT188 -MANGMT-UMTRN | Power Train Management System | 83931 | 83931 | 7500
500051234 | CLB-MP-HAUL-DT188 -MANGMT-UMENG | Engine Management System | 83931 | 83931 | 7500
500051233 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83931 | 10994 | 7500
500051232 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83931 | 10994 | 7500
500051231 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83931 | 23419 | 7500
500051230 | CLB-MP-HAUL-DT188 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83931 | 10994 | 7500
500051227 | CLB-MP-HAUL-DT188 -STRUCT-TRAYS | Tray | 83931 | 27859 | 7500
500051226 | CLB-MP-HAUL-DT188 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83931 | 15531 | 7500
500051225 | CLB-MP-HAUL-DT188 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83931 | 12074 | 7500
500051224 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-TAGLK | Tag Link | 83931 | 10994 | 7500
500051223 | CLB-MP-HAUL-DT188 -STRUCT-CHASS-AFRME | A Frame Bearing | 83931 | 18843 | 7500
500051222 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-SBELT | Seat Belt | 83931 | 83931 | 7500
500051221 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-SEATS | Operators Seat | 83931 | 10994 | 7500
500051220 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83931 | 83931 | 7500
500051219 | CLB-MP-HAUL-DT188 -STRUCT-CABIN-AIRCN | Air Conditioning System | 83931 | 10994 | 7500
500051218 | CLB-MP-HAUL-DT188 -STRUCT-CABIN | Operators Cabin | 83931 | 10994 | 7500
500051217 | CLB-MP-HAUL-DT188 -PNEUMC-START | Air Starter | 83931 | 10994 | 7500
500051216 | CLB-MP-HAUL-DT188 -PNEUMC-AIRDR | Air Drier | 83931 | 10994 | 7500
500051215 | CLB-MP-HAUL-DT188 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 83931 | 83931 | 7500
500051214 | CLB-MP-HAUL-DT188 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 83931 | 83931 | 7500
500051213 | CLB-MP-HAUL-DT188 -PNEUMC-PNTNK | No Not Use | 83931 | 10994 | 7500
500051212 | CLB-MP-HAUL-DT188 -GRSYST-ALCON | Auto Lube Controller | 83931 | 83931 | 7500
500051211 | CLB-MP-HAUL-DT188 -GRSYST-ALBPP | Auto Lube Pump | 83931 | 55183 | 7500
500051210 | CLB-MP-HAUL-DT188 -GRSYST-GRTNK | Auto Lube Resevoir | 83931 | 83931 | 7500
500051209 | CLB-MP-HAUL-DT188 -GRSYST-GRINJ | Auto Lube Injectors | 83931 | 83931 | 7500
500051208 | CLB-MP-HAUL-DT188 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83931 | 7989 | 7500
500051207 | CLB-MP-HAUL-DT188 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83931 | 10994 | 7500
500051206 | CLB-MP-HAUL-DT188 -HYDSYS-HOVLV | Valve Hoist | 83931 | 33801 | 7500
500051205 | CLB-MP-HAUL-DT188 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83931 | 83931 | 7500
500051204 | CLB-MP-HAUL-DT188 -HYDSYS-HDTNK | Tank Hydraulic | 83931 | 83931 | 7500
500051203 | CLB-MP-HAUL-DT188 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 83931 | 10994 | 7500
500051202 | CLB-MP-HAUL-DT188 -HYDSYS-HOPMP | Pump Hoist | 83931 | 10994 | 7500
500051201 | CLB-MP-HAUL-DT188 -HYDSYS | Hydraulic System | 83931 | 83931 | 7500
500051200 | CLB-MP-HAUL-DT188 -STRSYS-STCON-STCOL | Steering Column | 83931 | 83931 | 7500
500051199 | CLB-MP-HAUL-DT188 -STRSYS-STCON-STWHL | Steering Wheel | 83931 | 83931 | 7500
500051198 | CLB-MP-HAUL-DT188 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83931 | 10994 | 7500
500051197 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83931 | 10994 | 7500
500051196 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83931 | 10994 | 7500
500051195 | CLB-MP-HAUL-DT188 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83931 | 10994 | 7500
500051194 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83931 | 13040 | 7500
500051193 | CLB-MP-HAUL-DT188 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83931 | 3835 | 7500
500051192 | CLB-MP-HAUL-DT188 -STRSYS-STVLV | Valve Steering | 83931 | 10994 | 7500
500051191 | CLB-MP-HAUL-DT188 -STRSYS-STHMU | Steering HMU | 83931 | 797 | 7500
500051190 | CLB-MP-HAUL-DT188 -STRSYS-STPMP | Pump Steering | 83931 | 797 | 7500
500051189 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83931 | 10994 | 7500
500051188 | CLB-MP-HAUL-DT188 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83931 | 15527 | 7500
500051187 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 83931 | 10994 | 7500
500051186 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 83931 | 10994 | 7500
500051185 | CLB-MP-HAUL-DT188 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 83931 | 10994 | 7500
500051184 | CLB-MP-HAUL-DT188 -BRKSYS-BACCM | Brake Accumulator | 83931 | 10994 | 7500
500051183 | CLB-MP-HAUL-DT188 -BRKSYS-BROCO | Brake Oil Cooler | 83931 | 61121 | 7500
500051182 | CLB-MP-HAUL-DT188 -BRKSYS-MERTR | Mechanical Retarder | 83931 | 83931 | 7500
500051181 | CLB-MP-HAUL-DT188 -BRKSYS-BRVTR | Valve Brake Treadle | 83931 | 83931 | 7500
500051180 | CLB-MP-HAUL-DT188 -BRKSYS-HYFPP | Pump Brake Control | 83931 | 10994 | 7500
500051179 | CLB-MP-HAUL-DT188 -BRKSYS-PRKPP | Pump Park Brake Release | 83931 | 83931 | 7500
500051178 | CLB-MP-HAUL-DT188 -BRKSYS-BRPMP | Pump Brake | 83931 | 42776 | 7500
500051177 | CLB-MP-HAUL-DT188 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83931 | 83931 | 7500
500051176 | CLB-MP-HAUL-DT188 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83931 | 83931 | 7500
500051175 | CLB-MP-HAUL-DT188 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83931 | 83931 | 7500
500051174 | CLB-MP-HAUL-DT188 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83931 | 83931 | 7500
500051173 | CLB-MP-HAUL-DT188 -BRKSYS-SRVBK | Service Brake | 83931 | 83931 | 7500
500051172 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83931 | 83931 | 7500
500051171 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83931 | 797 | 7500
500051170 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 83931 | 10994 | 7500
500051169 | CLB-MP-HAUL-DT188 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83931 | 10994 | 7500
500051168 | CLB-MP-HAUL-DT188 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83931 | 10994 | 7500
500051167 | CLB-MP-HAUL-DT188 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83931 | 10994 | 7500
500051166 | CLB-MP-HAUL-DT188 -FDRSYS-DRLAX | Drive Line Axles | 83931 | 83931 | 7500
500051165 | CLB-MP-HAUL-DT188 -FDRSYS-DIFFL | Differential | 83931 | 10994 | 7500
500051164 | CLB-MP-HAUL-DT188 -FDRSYS-DRSHT | Transmission Drive Shaft | 83931 | 10994 | 7500
500051163 | CLB-MP-HAUL-DT188 -TRNSYS-TROLC | Oil Cooler Transmission | 83931 | 10994 | 7500
500051162 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83931 | 10994 | 7500
500051161 | CLB-MP-HAUL-DT188 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83931 | 6681 | 7500
500051160 | CLB-MP-HAUL-DT188 -TRNSYS-TRANS | Transmission | 83931 | 10994 | 7500
500051159 | CLB-MP-HAUL-DT188 -TRNSYS-TRQUE | Torque Converter | 83931 | 10994 | 7500
500051158 | CLB-MP-HAUL-DT188 -ELCTLV-CHARG-BATTY | Batteries | 83931 | 83931 | 7500
500051157 | CLB-MP-HAUL-DT188 -ELCTLV-CHARG-ALTER | Alternator 24V | 83931 | 10994 | 7500
500051156 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83931 | 10994 | 7500
500051155 | CLB-MP-HAUL-DT188 -ENGINE-PMPDR | Pump Drive | 83931 | 10994 | 7500
500051154 | CLB-MP-HAUL-DT188 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83931 | 10994 | 7500
500051153 | CLB-MP-HAUL-DT188 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83931 | 10994 | 7500
500051152 | CLB-MP-HAUL-DT188 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83931 | 10994 | 7500
500051151 | CLB-MP-HAUL-DT188 -ENGINE-FUSYS-FULTK | Fuel Tank | 83931 | 10994 | 7500
500051150 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-EXHST | Exhaust System | 83931 | 83931 | 7500
500051149 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-AFTER | Aftercooler | 83931 | 83931 | 7500
500051148 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 83931 | 10994 | 7500
500051147 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 83931 | 10994 | 7500
500051146 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 83931 | 10994 | 7500
500051145 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 83931 | 10994 | 7500
500051144 | CLB-MP-HAUL-DT188 -ENGINE-INTEX-AIRFL | Air Filtration System | 83931 | 83931 | 7500
500051143 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-THERM | Thermostats/Regulators | 83931 | 10994 | 7500
500051142 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-BELTS | Fan Belts Engine | 83931 | 83931 | 7500
500051141 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 83931 | 10994 | 7500
500051140 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-COFAN | Fan Cooling System | 83931 | 10994 | 7500
500051139 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-RADTR | Coolant Engine | 83931 | 33801 | 7400
500051138 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-RADTR | Radiator Engine | 83931 | 10994 | 7500
500051137 | CLB-MP-HAUL-DT188 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83931 | 10994 | 7500
500051136 | CLB-MP-HAUL-DT188 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83931 | 83931 | 7500
500051135 | CLB-MP-HAUL-DT188 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83931 | 10994 | 7500
500051134 | CLB-MP-HAUL-DT188 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83931 | 83931 | 7500
500051133 | CLB-MP-HAUL-DT188 -ENGINE-COMPR | Air Compressor | 83931 | 10994 | 7500
500051131 | CLB-MP-HAUL-DT188 -ENGINE | Engine Assembly Caterpillar 3516B | 83931 | 10994 | 7500
500051130 | CLB-MP-HAUL-DT188 | DT188 Lubrication & Mechanical Services | 83931 | 83931 | 7500
500051129 | CLB-MP-HAUL-DT188 | Caterpillar 789D Haul Truck DT188 | 83931 | 83931 | 7500
500160277 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITRH | Air Tank Right | 92907 | 46760 | 7500
500160276 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK-AITLH | Air Tank Left | 92907 | 46760 | 7500
500147270 | CLB-MP-HAUL-DT187 -STRSYS-STACC | Steering Accumulator Rear | 22807 | 22807 | 7500
500147269 | CLB-MP-HAUL-DT187 -STRSYS-STACC | Steering Accumulator Middle | 22807 | 22807 | 7500
500147268 | CLB-MP-HAUL-DT187 -STRSYS-STACC | Steering Accumulator Front | 22807 | 22807 | 7500
500118566 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-AFRME | A Frame Housing | 93170 | 3514 | 7500
500117942 | CLB-MP-HAUL-DT187 -ELCTLV-LIGHT | Lighting Low Voltage | 93170 | 45801 | 7500
500117902 | CLB-MP-HAUL-DT187 -ELCTLV-HARNS | Electrical Harness | 93170 | 45801 | 7500
500117862 | CLB-MP-HAUL-DT187 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 93170 | 45801 | 7500
500117426 | CLB-MP-HAUL-DT187 -ELCTLV-LIGHT-AHSYS | AHS Lights | 93170 | 45801 | 7500
500117306 | CLB-MP-HAUL-DT187 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 93170 | 45801 | 7500
500111228 | CLB-MP-HAUL-DT187 -STRUCT-RAXHO | Rear Axle Housing | 93170 | 3514 | 7500
500110558 | CLB-MP-HAUL-DT187 -GRSYST | Grease Lubrication System | 93170 | 36452 | 7500
500102808 | CLB-MP-HAUL-DT187 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 93170 | 3514 | 7500
500100635 | CLB-MP-HAUL-DT187 -TRNSYS | DT187 Transmission System | 93170 | 47023 | 7500
500081412 | CLB-MP-HAUL-DT187 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 93170 | 3514 | 7500
500081272 | CLB-MP-HAUL-DT187 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 93170 | 3514 | 7500
500079445 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN | Suspension Service | 93170 | 3514 | 7500
500078511 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 93170 | 3514 | 7500
500078474 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 93170 | 3514 | 7500
500061434 | CLB-MP-HAUL-DT187 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 93170 | 3514 | 7500
500061404 | CLB-MP-HAUL-DT187 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 93170 | 3514 | 7500
500061230 | CLB-MP-HAUL-DT187 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 93170 | 22807 | 7500
500061229 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-ELECT | Chassis Electrical System | 93170 | 22807 | 7500
500061228 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-ELECT | Cabin Electrical System | 93170 | 93170 | 7500
500061227 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 93170 | 11312 | 7500
500061226 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 93170 | 11312 | 7500
500061225 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 93170 | 11312 | 7500
500061224 | CLB-MP-HAUL-DT187 -STRSYS-STHLF-STRHO | Steering System Hoses | 93170 | 3514 | 7500
500061223 | CLB-MP-HAUL-DT187 -STRSYS-STLTR-STBST | Ball Studs | 93170 | 93170 | 7500
500061222 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 93170 | 3514 | 7500
500061221 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 93170 | 3514 | 7500
500061220 | CLB-MP-HAUL-DT187 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 93170 | 3514 | 7500
500061219 | CLB-MP-HAUL-DT187 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 93170 | 3514 | 7500
500061218 | CLB-MP-HAUL-DT187 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 93170 | 3514 | 7500
500061217 | CLB-MP-HAUL-DT187 -BRKSYS-BRVRL | Brake Relay Valve | 93170 | 3514 | 7500
500061215 | CLB-MP-HAUL-DT187 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 93170 | 3514 | 7500
500061214 | CLB-MP-HAUL-DT187 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 93170 | 3514 | 7500
500060125 | CLB-MP-HAUL-DT187 -STRSYS-STTNK | Tank Steering | 93170 | 69585 | 7500
500053850 | CLB-MP-HAUL-DT187 -BRKSYS-BRVLV | Valve Brake | 93170 | 3514 | 7500
500051128 | CLB-MP-HAUL-DT187 -MANGMT-UMMMC | Mine Monitoring and Control | 93170 | 93170 | 7500
500051127 | CLB-MP-HAUL-DT187 -MANGMT-UMTRN | Power Train Management System | 93170 | 93170 | 7500
500051126 | CLB-MP-HAUL-DT187 -MANGMT-UMENG | Engine Management System | 93170 | 93170 | 7500
500051125 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 93170 | 3514 | 7500
500051124 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 93170 | 3514 | 7500
500051123 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 93170 | 6296 | 7500
500051122 | CLB-MP-HAUL-DT187 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 93170 | 3514 | 7500
500051119 | CLB-MP-HAUL-DT187 -STRUCT-TRAYS | Tray | 93170 | 93170 | 7500
500051118 | CLB-MP-HAUL-DT187 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 93170 | 3514 | 7500
500051117 | CLB-MP-HAUL-DT187 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 93170 | 22807 | 7500
500051116 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-TAGLK | Tag Link | 93170 | 3514 | 7500
500051115 | CLB-MP-HAUL-DT187 -STRUCT-CHASS-AFRME | A Frame Bearing | 93170 | 3514 | 7500
500051114 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-SBELT | Seat Belt | 93170 | 93170 | 7500
500051113 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-SEATS | Operators Seat | 93170 | 22807 | 7500
500051112 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 93170 | 93170 | 7500
500051111 | CLB-MP-HAUL-DT187 -STRUCT-CABIN-AIRCN | Air Conditioning System | 93170 | 13899 | 7500
500051110 | CLB-MP-HAUL-DT187 -STRUCT-CABIN | Operators Cabin | 93170 | 47023 | 7500
500051109 | CLB-MP-HAUL-DT187 -PNEUMC-START | Air Starter | 93170 | 3514 | 7500
500051108 | CLB-MP-HAUL-DT187 -PNEUMC-AIRDR | Air Drier | 93170 | 33317 | 7500
500051107 | CLB-MP-HAUL-DT187 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 93170 | 93170 | 7500
500051106 | CLB-MP-HAUL-DT187 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 93170 | 93170 | 7500
500051105 | CLB-MP-HAUL-DT187 -PNEUMC-PNTNK | No Not Use | 93170 | 47023 | 7500
500051104 | CLB-MP-HAUL-DT187 -GRSYST-ALCON | Auto Lube Controller | 93170 | 93170 | 7500
500051103 | CLB-MP-HAUL-DT187 -GRSYST-ALBPP | Auto Lube Pump | 93170 | 41373 | 7500
500051102 | CLB-MP-HAUL-DT187 -GRSYST-GRTNK | Auto Lube Resevoir | 93170 | 93170 | 7500
500051101 | CLB-MP-HAUL-DT187 -GRSYST-GRINJ | Auto Lube Injectors | 93170 | 93170 | 7500
500051100 | CLB-MP-HAUL-DT187 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 93170 | 7549 | 7500
500051099 | CLB-MP-HAUL-DT187 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 93170 | 7550 | 7500
500051098 | CLB-MP-HAUL-DT187 -HYDSYS-HOVLV | Valve Hoist | 93170 | 22807 | 7500
500051097 | CLB-MP-HAUL-DT187 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 93170 | 93170 | 7500
500051096 | CLB-MP-HAUL-DT187 -HYDSYS-HDTNK | Tank Hydraulic | 93170 | 69585 | 7500
500051095 | CLB-MP-HAUL-DT187 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 93170 | 22807 | 7500
500051094 | CLB-MP-HAUL-DT187 -HYDSYS-HOPMP | Pump Hoist | 93170 | 3514 | 7500
500051093 | CLB-MP-HAUL-DT187 -HYDSYS | Hydraulic System | 93170 | 93170 | 7500
500051092 | CLB-MP-HAUL-DT187 -STRSYS-STCON-STCOL | Steering Column | 93170 | 93170 | 7500
500051091 | CLB-MP-HAUL-DT187 -STRSYS-STCON-STWHL | Steering Wheel | 93170 | 93170 | 7500
500051090 | CLB-MP-HAUL-DT187 -STRSYS-STLTR | Steering Linkages and Tie Rods | 93170 | 9139 | 7500
500051089 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 93170 | 3514 | 7500
500051088 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 93170 | 3514 | 7500
500051087 | CLB-MP-HAUL-DT187 -STRSYS-STACC-SACCF | Accumulator Steering Front | 93170 | 3514 | 7500
500051086 | CLB-MP-HAUL-DT187 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 93170 | 3514 | 7500
500051085 | CLB-MP-HAUL-DT187 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 93170 | 6296 | 7500
500051084 | CLB-MP-HAUL-DT187 -STRSYS-STVLV | Valve Steering | 93170 | 28555 | 7500
500051083 | CLB-MP-HAUL-DT187 -STRSYS-STHMU | Steering HMU | 93170 | 3514 | 7500
500051082 | CLB-MP-HAUL-DT187 -STRSYS-STPMP | Pump Steering | 93170 | 3514 | 7500
500051081 | CLB-MP-HAUL-DT187 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 93170 | 11315 | 7500
500051080 | CLB-MP-HAUL-DT187 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 93170 | 11315 | 7500
500051079 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 93170 | 3514 | 7500
500051078 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 93170 | 3514 | 7500
500051077 | CLB-MP-HAUL-DT187 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 93170 | 3514 | 7500
500051076 | CLB-MP-HAUL-DT187 -BRKSYS-BACCM | Brake Accumulator | 93170 | 3514 | 7500
500051075 | CLB-MP-HAUL-DT187 -BRKSYS-BROCO | Brake Oil Cooler | 93170 | 69596 | 7500
500051074 | CLB-MP-HAUL-DT187 -BRKSYS-MERTR | Mechanical Retarder | 93170 | 93170 | 7500
500051073 | CLB-MP-HAUL-DT187 -BRKSYS-BRVTR | Valve Brake Treadle | 93170 | 69585 | 7500
500051072 | CLB-MP-HAUL-DT187 -BRKSYS-HYFPP | Pump Brake Control | 93170 | 3514 | 7500
500051071 | CLB-MP-HAUL-DT187 -BRKSYS-PRKPP | Pump Park Brake Release | 93170 | 93170 | 7500
500051070 | CLB-MP-HAUL-DT187 -BRKSYS-BRPMP | Pump Brake | 93170 | 25208 | 7500
500051069 | CLB-MP-HAUL-DT187 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 93170 | 93170 | 7500
500051068 | CLB-MP-HAUL-DT187 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 93170 | 69585 | 7500
500051067 | CLB-MP-HAUL-DT187 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 93170 | 93170 | 7500
500051066 | CLB-MP-HAUL-DT187 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 93170 | 69585 | 7500
500051065 | CLB-MP-HAUL-DT187 -BRKSYS-SRVBK | Service Brake | 93170 | 93170 | 7500
500051064 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 93170 | 93170 | 7500
500051063 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 93170 | 93170 | 7500
500051062 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 93170 | 3514 | 7500
500051061 | CLB-MP-HAUL-DT187 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 93170 | 3514 | 7500
500051060 | CLB-MP-HAUL-DT187 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 93170 | 3746 | 7500
500051059 | CLB-MP-HAUL-DT187 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 93170 | 3746 | 7500
500051058 | CLB-MP-HAUL-DT187 -FDRSYS-DRLAX | Drive Line Axles | 93170 | 93170 | 7500
500051057 | CLB-MP-HAUL-DT187 -FDRSYS-DIFFL | Differential | 93170 | 3514 | 7500
500051056 | CLB-MP-HAUL-DT187 -FDRSYS-DRSHT | Transmission Drive Shaft | 93170 | 3514 | 7500
500051055 | CLB-MP-HAUL-DT187 -TRNSYS-TROLC | Oil Cooler Transmission | 93170 | 3514 | 7500
500051054 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 93170 | 9139 | 7500
500051053 | CLB-MP-HAUL-DT187 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 93170 | 3514 | 7500
500051052 | CLB-MP-HAUL-DT187 -TRNSYS-TRANS | Transmission | 93170 | 3056 | 7500
500051051 | CLB-MP-HAUL-DT187 -TRNSYS-TRQUE | Torque Converter | 93170 | 3514 | 7500
500051050 | CLB-MP-HAUL-DT187 -ELCTLV-CHARG-BATTY | Batteries | 93170 | 40423 | 7500
500051049 | CLB-MP-HAUL-DT187 -ELCTLV-CHARG-ALTER | Alternator 24V | 93170 | 3514 | 7500
500051048 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 93170 | 3514 | 7500
500051047 | CLB-MP-HAUL-DT187 -ENGINE-PMPDR | Pump Drive | 93170 | 3514 | 7500
500051046 | CLB-MP-HAUL-DT187 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 93170 | 3514 | 7500
500051045 | CLB-MP-HAUL-DT187 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 93170 | 3514 | 7500
500051044 | CLB-MP-HAUL-DT187 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 93170 | 3514 | 7500
500051043 | CLB-MP-HAUL-DT187 -ENGINE-FUSYS-FULTK | Fuel Tank | 93170 | 3514 | 7500
500051042 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-EXHST | Exhaust System | 93170 | 93170 | 7500
500051041 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-AFTER | Aftercooler | 93170 | 69585 | 7500
500051040 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 93170 | 3514 | 7500
500051039 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 93170 | 3514 | 7500
500051038 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 93170 | 3514 | 7500
500051037 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 93170 | 3514 | 7500
500051036 | CLB-MP-HAUL-DT187 -ENGINE-INTEX-AIRFL | Air Filtration System | 93170 | 93170 | 7500
500051035 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-THERM | Thermostats/Regulators | 93170 | 3514 | 7500
500051034 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-BELTS | Fan Belts Engine | 93170 | 69585 | 7500
500051033 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 93170 | 3514 | 7500
500051032 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-COFAN | Fan Cooling System | 93170 | 3514 | 7500
500051031 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-RADTR | Coolant Engine | 93170 | 22807 | 7400
500051030 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-RADTR | Radiator Engine | 93170 | 3514 | 7500
500051029 | CLB-MP-HAUL-DT187 -ENGINE-COSYS-WTRPP | Water Pump Engine | 93170 | 3514 | 7500
500051028 | CLB-MP-HAUL-DT187 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 93170 | 69585 | 7500
500051027 | CLB-MP-HAUL-DT187 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 93170 | 3514 | 7500
500051026 | CLB-MP-HAUL-DT187 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 93170 | 69585 | 7500
500051025 | CLB-MP-HAUL-DT187 -ENGINE-COMPR | Air Compressor | 93169 | 3514 | 7500
500051023 | CLB-MP-HAUL-DT187 -ENGINE | Engine Assembly Caterpillar 3516B | 93170 | 3514 | 7500
500051022 | CLB-MP-HAUL-DT187 | DT187 Lubrication & Mechanical Services | 93170 | 93170 | 7500
500051021 | CLB-MP-HAUL-DT187 | Caterpillar 789D Haul Truck DT187 | 93170 | 93170 | 7500
500160275 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITRH | Air Tank Right | 89493 | 42523 | 7500
500160274 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK-AITLH | Air Tank Left | 89493 | 42523 | 7500
500147266 | CLB-MP-HAUL-DT186 -STRSYS-STACC | Steering Accumulator Rear | 20387 | 20387 | 7500
500147265 | CLB-MP-HAUL-DT186 -STRSYS-STACC | Steering Accumulator Middle | 20387 | 20387 | 7500
500147264 | CLB-MP-HAUL-DT186 -STRSYS-STACC | Steering Accumulator Front | 20387 | 20387 | 7500
500118565 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-AFRME | A Frame Housing | 89749 | 28445 | 7500
500117941 | CLB-MP-HAUL-DT186 -ELCTLV-LIGHT | Lighting Low Voltage | 89749 | 43115 | 7500
500117901 | CLB-MP-HAUL-DT186 -ELCTLV-HARNS | Electrical Harness | 89749 | 43115 | 7500
500117861 | CLB-MP-HAUL-DT186 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 89749 | 43115 | 7500
500117425 | CLB-MP-HAUL-DT186 -ELCTLV-LIGHT-AHSYS | AHS Lights | 89749 | 43115 | 7500
500117305 | CLB-MP-HAUL-DT186 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 89749 | 43115 | 7500
500111227 | CLB-MP-HAUL-DT186 -STRUCT-RAXHO | Rear Axle Housing | 89749 | 20387 | 7500
500110557 | CLB-MP-HAUL-DT186 -GRSYST | Grease Lubrication System | 89749 | 8654 | 7500
500102807 | CLB-MP-HAUL-DT186 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 89749 | 20387 | 7500
500100634 | CLB-MP-HAUL-DT186 -TRNSYS | DT186 Transmission System | 89749 | 20387 | 7500
500081411 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 89749 | 22897 | 7500
500081271 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 89749 | 22897 | 7500
500079444 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN | Suspension Service | 89749 | 20387 | 7500
500078510 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 89749 | 20387 | 7500
500078473 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 89749 | 20387 | 7500
500061433 | CLB-MP-HAUL-DT186 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 89749 | 20387 | 7500
500061403 | CLB-MP-HAUL-DT186 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 89749 | 20387 | 7500
500061213 | CLB-MP-HAUL-DT186 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 89749 | 20387 | 7500
500061212 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-ELECT | Chassis Electrical System | 89749 | 42779 | 7500
500061211 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-ELECT | Cabin Electrical System | 89749 | 89749 | 7500
500061210 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 89749 | 8654 | 7500
500061209 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 89749 | 8654 | 7500
500061208 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 89749 | 8654 | 7500
500061207 | CLB-MP-HAUL-DT186 -STRSYS-STHLF-STRHO | Steering System Hoses | 89749 | 20387 | 7500
500061206 | CLB-MP-HAUL-DT186 -STRSYS-STLTR-STBST | Ball Studs | 89749 | 89749 | 7500
500061205 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 89749 | 20387 | 7500
500061204 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 89749 | 20387 | 7500
500061203 | CLB-MP-HAUL-DT186 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 89749 | 20387 | 7500
500061202 | CLB-MP-HAUL-DT186 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 89749 | 20387 | 7500
500061201 | CLB-MP-HAUL-DT186 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 89749 | 20387 | 7500
500061200 | CLB-MP-HAUL-DT186 -BRKSYS-BRVRL | Brake Relay Valve | 89749 | 1586 | 7500
500061198 | CLB-MP-HAUL-DT186 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 89749 | 20387 | 7500
500061197 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 89749 | 20387 | 7500
500060124 | CLB-MP-HAUL-DT186 -STRSYS-STTNK | Tank Steering | 89749 | 89749 | 7500
500053849 | CLB-MP-HAUL-DT186 -BRKSYS-BRVLV | Valve Brake | 89749 | 20387 | 7500
500051020 | CLB-MP-HAUL-DT186 -MANGMT-UMMMC | Mine Monitoring and Control | 89749 | 89749 | 7500
500051019 | CLB-MP-HAUL-DT186 -MANGMT-UMTRN | Power Train Management System | 89749 | 89749 | 7500
500051018 | CLB-MP-HAUL-DT186 -MANGMT-UMENG | Engine Management System | 89749 | 89749 | 7500
500051017 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 89749 | 20387 | 7500
500051016 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 89749 | 5084 | 7500
500051015 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 89749 | 20387 | 7500
500051014 | CLB-MP-HAUL-DT186 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 89749 | 22897 | 7500
500051011 | CLB-MP-HAUL-DT186 -STRUCT-TRAYS | Tray | 89749 | 89749 | 7500
500051010 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 89749 | 20387 | 7500
500051009 | CLB-MP-HAUL-DT186 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 89749 | 22897 | 7500
500051008 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-TAGLK | Tag Link | 89749 | 42779 | 7500
500051007 | CLB-MP-HAUL-DT186 -STRUCT-CHASS-AFRME | A Frame Bearing | 89749 | 28445 | 7500
500051006 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-SBELT | Seat Belt | 89749 | 54679 | 7500
500051005 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-SEATS | Operators Seat | 89749 | 21558 | 7500
500051004 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 89749 | 89749 | 7500
500051003 | CLB-MP-HAUL-DT186 -STRUCT-CABIN-AIRCN | Air Conditioning System | 89749 | 14154 | 7500
500051002 | CLB-MP-HAUL-DT186 -STRUCT-CABIN | Operators Cabin | 89749 | 20387 | 7500
500051001 | CLB-MP-HAUL-DT186 -PNEUMC-START | Air Starter | 89749 | 8654 | 7500
500051000 | CLB-MP-HAUL-DT186 -PNEUMC-AIRDR | Air Drier | 89749 | 20387 | 7500
500050999 | CLB-MP-HAUL-DT186 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 89749 | 89749 | 7500
500050998 | CLB-MP-HAUL-DT186 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 89749 | 89749 | 7500
500050997 | CLB-MP-HAUL-DT186 -PNEUMC-PNTNK | No Not Use | 89749 | 42779 | 7500
500050996 | CLB-MP-HAUL-DT186 -GRSYST-ALCON | Auto Lube Controller | 89749 | 89749 | 7500
500050995 | CLB-MP-HAUL-DT186 -GRSYST-ALBPP | Auto Lube Pump | 89749 | 89749 | 7500
500050994 | CLB-MP-HAUL-DT186 -GRSYST-GRTNK | Auto Lube Resevoir | 89749 | 89749 | 7500
500050993 | CLB-MP-HAUL-DT186 -GRSYST-GRINJ | Auto Lube Injectors | 89749 | 89749 | 7500
500050992 | CLB-MP-HAUL-DT186 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 89749 | 28445 | 7500
500050991 | CLB-MP-HAUL-DT186 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 89749 | 8654 | 7500
500050990 | CLB-MP-HAUL-DT186 -HYDSYS-HOVLV | Valve Hoist | 89749 | 20387 | 7500
500050989 | CLB-MP-HAUL-DT186 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 89749 | 89749 | 7500
500050988 | CLB-MP-HAUL-DT186 -HYDSYS-HDTNK | Tank Hydraulic | 89749 | 89749 | 7500
500050987 | CLB-MP-HAUL-DT186 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 89749 | 20387 | 7500
500050986 | CLB-MP-HAUL-DT186 -HYDSYS-HOPMP | Pump Hoist | 89749 | 23493 | 7500
500050985 | CLB-MP-HAUL-DT186 -HYDSYS | Hydraulic System | 89749 | 89749 | 7500
500050984 | CLB-MP-HAUL-DT186 -STRSYS-STCON-STCOL | Steering Column | 89749 | 91146 | 7500
500050983 | CLB-MP-HAUL-DT186 -STRSYS-STCON-STWHL | Steering Wheel | 89749 | 89749 | 7500
500050982 | CLB-MP-HAUL-DT186 -STRSYS-STLTR | Steering Linkages and Tie Rods | 89749 | 26124 | 7500
500050981 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 89749 | 20387 | 7500
500050980 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 89749 | 20387 | 7500
500050979 | CLB-MP-HAUL-DT186 -STRSYS-STACC-SACCF | Accumulator Steering Front | 89749 | 20387 | 7500
500050978 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 89749 | 12127 | 7500
500050977 | CLB-MP-HAUL-DT186 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 89749 | 8654 | 7500
500050976 | CLB-MP-HAUL-DT186 -STRSYS-STVLV | Valve Steering | 89749 | 23484 | 7500
500050975 | CLB-MP-HAUL-DT186 -STRSYS-STHMU | Steering HMU | 89749 | 12127 | 7500
500050974 | CLB-MP-HAUL-DT186 -STRSYS-STPMP | Pump Steering | 89749 | 12127 | 7500
500050973 | CLB-MP-HAUL-DT186 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 89749 | 8654 | 7500
500050972 | CLB-MP-HAUL-DT186 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 89749 | 8654 | 7500
500050971 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 89749 | 20387 | 7500
500050970 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 89749 | 20387 | 7500
500050969 | CLB-MP-HAUL-DT186 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 89749 | 20387 | 7500
500050968 | CLB-MP-HAUL-DT186 -BRKSYS-BACCM | Brake Accumulator | 89749 | 20387 | 7500
500050967 | CLB-MP-HAUL-DT186 -BRKSYS-BROCO | Brake Oil Cooler | 89749 | 65937 | 7500
500050966 | CLB-MP-HAUL-DT186 -BRKSYS-MERTR | Mechanical Retarder | 89749 | 89749 | 7500
500050965 | CLB-MP-HAUL-DT186 -BRKSYS-BRVTR | Valve Brake Treadle | 89749 | 89749 | 7500
500050964 | CLB-MP-HAUL-DT186 -BRKSYS-HYFPP | Pump Brake Control | 89749 | 16218 | 7500
500050963 | CLB-MP-HAUL-DT186 -BRKSYS-PRKPP | Pump Park Brake Release | 89749 | 89749 | 7500
500050962 | CLB-MP-HAUL-DT186 -BRKSYS-BRPMP | Pump Brake | 89749 | 89749 | 7500
500050961 | CLB-MP-HAUL-DT186 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 89749 | 65939 | 7500
500050960 | CLB-MP-HAUL-DT186 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 89749 | 65939 | 7500
500050959 | CLB-MP-HAUL-DT186 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 89749 | 89749 | 7500
500050958 | CLB-MP-HAUL-DT186 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 89749 | 89749 | 7500
500050957 | CLB-MP-HAUL-DT186 -BRKSYS-SRVBK | Service Brake | 89749 | 89749 | 7500
500050956 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 89749 | 89749 | 7500
500050955 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 89749 | 89749 | 7500
500050954 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 89749 | 8654 | 7500
500050953 | CLB-MP-HAUL-DT186 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 89749 | 12127 | 7500
500050952 | CLB-MP-HAUL-DT186 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 89749 | 893 | 7500
500050951 | CLB-MP-HAUL-DT186 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 89749 | 6115 | 7500
500050950 | CLB-MP-HAUL-DT186 -FDRSYS-DRLAX | Drive Line Axles | 89749 | 89749 | 7500
500050949 | CLB-MP-HAUL-DT186 -FDRSYS-DIFFL | Differential | 89749 | 20387 | 7500
500050948 | CLB-MP-HAUL-DT186 -FDRSYS-DRSHT | Transmission Drive Shaft | 89736 | 8654 | 7500
500050947 | CLB-MP-HAUL-DT186 -TRNSYS-TROLC | Oil Cooler Transmission | 89749 | 23484 | 7500
500050946 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 89749 | 20387 | 7500
500050945 | CLB-MP-HAUL-DT186 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 89749 | 12127 | 7500
500050944 | CLB-MP-HAUL-DT186 -TRNSYS-TRANS | Transmission | 89749 | 23493 | 7500
500050943 | CLB-MP-HAUL-DT186 -TRNSYS-TRQUE | Torque Converter | 89749 | 20387 | 7500
500050942 | CLB-MP-HAUL-DT186 -ELCTLV-CHARG-BATTY | Batteries | 89749 | 32250 | 7500
500050941 | CLB-MP-HAUL-DT186 -ELCTLV-CHARG-ALTER | Alternator 24V | 89749 | 8654 | 7500
500050940 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 89749 | 8654 | 7500
500050939 | CLB-MP-HAUL-DT186 -ENGINE-PMPDR | Pump Drive | 89749 | 20387 | 7500
500050938 | CLB-MP-HAUL-DT186 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 89749 | 20387 | 7500
500050937 | CLB-MP-HAUL-DT186 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 89749 | 8654 | 7500
500050936 | CLB-MP-HAUL-DT186 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 89749 | 8654 | 7500
500050935 | CLB-MP-HAUL-DT186 -ENGINE-FUSYS-FULTK | Fuel Tank | 89749 | 20387 | 7500
500050934 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-EXHST | Exhaust System | 89749 | 65939 | 7500
500050933 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-AFTER | Aftercooler | 89749 | 89749 | 7500
500050932 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 89749 | 8654 | 7500
500050931 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 89749 | 8654 | 7500
500050930 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 89749 | 8654 | 7500
500050929 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 89749 | 8654 | 7500
500050928 | CLB-MP-HAUL-DT186 -ENGINE-INTEX-AIRFL | Air Filtration System | 89749 | 20387 | 7500
500050927 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-THERM | Thermostats/Regulators | 89749 | 8654 | 7500
500050926 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-BELTS | Fan Belts Engine | 89749 | 89749 | 7500
500050925 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 89749 | 8654 | 7500
500050924 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-COFAN | Fan Cooling System | 89749 | 8654 | 7500
500050923 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-RADTR | Coolant Engine | 89749 | 28445 | 7400
500050922 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-RADTR | Radiator Engine | 89749 | 6115 | 7500
500050921 | CLB-MP-HAUL-DT186 -ENGINE-COSYS-WTRPP | Water Pump Engine | 89749 | 8654 | 7500
500050920 | CLB-MP-HAUL-DT186 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 89749 | 65939 | 7500
500050919 | CLB-MP-HAUL-DT186 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 89749 | 20387 | 7500
500050918 | CLB-MP-HAUL-DT186 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 89749 | 89749 | 7500
500050917 | CLB-MP-HAUL-DT186 -ENGINE-COMPR | Air Compressor | 89749 | 8654 | 7500
500050915 | CLB-MP-HAUL-DT186 -ENGINE | Engine Assembly Caterpillar 3516B | 89749 | 20387 | 7500
500050914 | CLB-MP-HAUL-DT186 | DT186 Lubrication & Mechanical Services | 89749 | 89749 | 7500
500050913 | CLB-MP-HAUL-DT186 | Caterpillar 789D Haul Truck DT186 | 89749 | 89749 | 7500
500160273 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITRH | Air Tank Right | 91826 | 53019 | 7500
500160272 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK-AITLH | Air Tank Left | 91826 | 53019 | 7500
500147262 | CLB-MP-HAUL-DT185 -STRSYS-STACC | Steering Accumulator Rear | 18375 | 18375 | 7500
500147261 | CLB-MP-HAUL-DT185 -STRSYS-STACC | Steering Accumulator Middle | 18375 | 18375 | 7500
500147260 | CLB-MP-HAUL-DT185 -STRSYS-STACC | Steering Accumulator Front | 18375 | 18375 | 7500
500118564 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-AFRME | A Frame Housing | 92088 | 22899 | 7500
500117940 | CLB-MP-HAUL-DT185 -ELCTLV-LIGHT | Lighting Low Voltage | 92088 | 44065 | 7500
500117900 | CLB-MP-HAUL-DT185 -ELCTLV-HARNS | Electrical Harness | 92088 | 44065 | 7500
500117860 | CLB-MP-HAUL-DT185 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 92088 | 44065 | 7500
500117424 | CLB-MP-HAUL-DT185 -ELCTLV-LIGHT-AHSYS | AHS Lights | 92088 | 44065 | 7500
500117304 | CLB-MP-HAUL-DT185 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 92088 | 44065 | 7500
500111226 | CLB-MP-HAUL-DT185 -STRUCT-RAXHO | Rear Axle Housing | 92088 | 41661 | 7500
500110556 | CLB-MP-HAUL-DT185 -GRSYST | Grease Lubrication System | 92088 | 11315 | 7500
500102806 | CLB-MP-HAUL-DT185 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 92088 | 18375 | 7500
500100633 | CLB-MP-HAUL-DT185 -TRNSYS | DT185 Transmission System | 92088 | 44391 | 7500
500081410 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 92088 | 22308 | 7500
500081270 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 92088 | 22308 | 7500
500079443 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN | Suspension Service | 92088 | 41661 | 7500
500078509 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 92088 | 18375 | 7500
500078472 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 92088 | 18375 | 7500
500061432 | CLB-MP-HAUL-DT185 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 92088 | 18375 | 7500
500061402 | CLB-MP-HAUL-DT185 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 92088 | 18375 | 7500
500061196 | CLB-MP-HAUL-DT185 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 92088 | 18375 | 7500
500061195 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-ELECT | Chassis Electrical System | 92088 | 41661 | 7500
500061194 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-ELECT | Cabin Electrical System | 92088 | 92088 | 7500
500061193 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 92088 | 18375 | 7500
500061192 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 92088 | 18375 | 7500
500061191 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 92088 | 18375 | 7500
500061190 | CLB-MP-HAUL-DT185 -STRSYS-STHLF-STRHO | Steering System Hoses | 92088 | 18375 | 7500
500061189 | CLB-MP-HAUL-DT185 -STRSYS-STLTR-STBST | Ball Studs | 92088 | 92088 | 7500
500061188 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 92088 | 18375 | 7500
500061187 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 92088 | 18375 | 7500
500061186 | CLB-MP-HAUL-DT185 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 92088 | 18375 | 7500
500061185 | CLB-MP-HAUL-DT185 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 92088 | 18375 | 7500
500061184 | CLB-MP-HAUL-DT185 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 92088 | 18375 | 7500
500061183 | CLB-MP-HAUL-DT185 -BRKSYS-BRVRL | Brake Relay Valve | 92088 | 18375 | 7500
500061181 | CLB-MP-HAUL-DT185 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 92088 | 18375 | 7500
500061180 | CLB-MP-HAUL-DT185 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 92088 | 18375 | 7500
500060123 | CLB-MP-HAUL-DT185 -STRSYS-STTNK | Tank Steering | 92088 | 66168 | 7500
500053848 | CLB-MP-HAUL-DT185 -BRKSYS-BRVLV | Valve Brake | 92088 | 18375 | 7500
500050912 | CLB-MP-HAUL-DT185 -MANGMT-UMMMC | Mine Monitoring and Control | 92088 | 92088 | 7500
500050911 | CLB-MP-HAUL-DT185 -MANGMT-UMTRN | Power Train Management System | 92088 | 92088 | 7500
500050910 | CLB-MP-HAUL-DT185 -MANGMT-UMENG | Engine Management System | 92088 | 92088 | 7500
500050909 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 92088 | 4203 | 7500
500050908 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 92088 | 18375 | 7500
500050907 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 92088 | 18375 | 7500
500050906 | CLB-MP-HAUL-DT185 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 92088 | 17006 | 7500
500050903 | CLB-MP-HAUL-DT185 -STRUCT-TRAYS | Tray | 92088 | 26084 | 7500
500050902 | CLB-MP-HAUL-DT185 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 92088 | 18375 | 7500
500050901 | CLB-MP-HAUL-DT185 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 92088 | 18375 | 7500
500050900 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-TAGLK | Tag Link | 92088 | 22899 | 7500
500050899 | CLB-MP-HAUL-DT185 -STRUCT-CHASS-AFRME | A Frame Bearing | 92088 | 22899 | 7500
500050898 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-SBELT | Seat Belt | 92088 | 47921 | 7500
500050897 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-SEATS | Operators Seat | 92088 | 18375 | 7500
500050896 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 92088 | 92088 | 7500
500050895 | CLB-MP-HAUL-DT185 -STRUCT-CABIN-AIRCN | Air Conditioning System | 92088 | 7001 | 7500
500050894 | CLB-MP-HAUL-DT185 -STRUCT-CABIN | Operators Cabin | 92088 | 18375 | 7500
500050893 | CLB-MP-HAUL-DT185 -PNEUMC-START | Air Starter | 92088 | 7001 | 7500
500050892 | CLB-MP-HAUL-DT185 -PNEUMC-AIRDR | Air Drier | 92088 | 18375 | 7500
500050891 | CLB-MP-HAUL-DT185 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 92088 | 92088 | 7500
500050890 | CLB-MP-HAUL-DT185 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 92088 | 92088 | 7500
500050889 | CLB-MP-HAUL-DT185 -PNEUMC-PNTNK | No Not Use | 92088 | 53281 | 7500
500050888 | CLB-MP-HAUL-DT185 -GRSYST-ALCON | Auto Lube Controller | 92088 | 92088 | 7500
500050887 | CLB-MP-HAUL-DT185 -GRSYST-ALBPP | Auto Lube Pump | 92088 | 21691 | 7500
500050886 | CLB-MP-HAUL-DT185 -GRSYST-GRTNK | Auto Lube Resevoir | 92088 | 92088 | 7500
500050885 | CLB-MP-HAUL-DT185 -GRSYST-GRINJ | Auto Lube Injectors | 92088 | 92088 | 7500
500050884 | CLB-MP-HAUL-DT185 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 92088 | 23112 | 7500
500050883 | CLB-MP-HAUL-DT185 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 92088 | 22242 | 7500
500050882 | CLB-MP-HAUL-DT185 -HYDSYS-HOVLV | Valve Hoist | 92088 | 18375 | 7500
500050881 | CLB-MP-HAUL-DT185 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 92088 | 92088 | 7500
500050880 | CLB-MP-HAUL-DT185 -HYDSYS-HDTNK | Tank Hydraulic | 92088 | 66168 | 7500
500050879 | CLB-MP-HAUL-DT185 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 92088 | 18375 | 7500
500050878 | CLB-MP-HAUL-DT185 -HYDSYS-HOPMP | Pump Hoist | 92088 | 22242 | 7500
500050877 | CLB-MP-HAUL-DT185 -HYDSYS | Hydraulic System | 92088 | 92088 | 7500
500050876 | CLB-MP-HAUL-DT185 -STRSYS-STCON-STCOL | Steering Column | 92088 | 50375 | 7500
500050875 | CLB-MP-HAUL-DT185 -STRSYS-STCON-STWHL | Steering Wheel | 92088 | 92088 | 7500
500050874 | CLB-MP-HAUL-DT185 -STRSYS-STLTR | Steering Linkages and Tie Rods | 92088 | 18375 | 7500
500050873 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 92088 | 18375 | 7500
500050872 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 92088 | 18375 | 7500
500050871 | CLB-MP-HAUL-DT185 -STRSYS-STACC-SACCF | Accumulator Steering Front | 92088 | 18375 | 7500
500050870 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 92088 | 12790 | 7500
500050869 | CLB-MP-HAUL-DT185 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 92088 | 12790 | 7500
500050868 | CLB-MP-HAUL-DT185 -STRSYS-STVLV | Valve Steering | 92088 | 18375 | 7500
500050867 | CLB-MP-HAUL-DT185 -STRSYS-STHMU | Steering HMU | 92088 | 9689 | 7500
500050866 | CLB-MP-HAUL-DT185 -STRSYS-STPMP | Pump Steering | 92088 | 9689 | 7500
500050865 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 92088 | 18375 | 7500
500050864 | CLB-MP-HAUL-DT185 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 92088 | 18375 | 7500
500050863 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 92088 | 18375 | 7500
500050862 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 92088 | 18375 | 7500
500050861 | CLB-MP-HAUL-DT185 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 92088 | 25896 | 7500
500050860 | CLB-MP-HAUL-DT185 -BRKSYS-BACCM | Brake Accumulator | 92088 | 18375 | 7500
500050859 | CLB-MP-HAUL-DT185 -BRKSYS-BROCO | Brake Oil Cooler | 92088 | 66168 | 7500
500050858 | CLB-MP-HAUL-DT185 -BRKSYS-MERTR | Mechanical Retarder | 92088 | 92088 | 7500
500050857 | CLB-MP-HAUL-DT185 -BRKSYS-BRVTR | Valve Brake Treadle | 92088 | 66168 | 7500
500050856 | CLB-MP-HAUL-DT185 -BRKSYS-HYFPP | Pump Brake Control | 92088 | 5719 | 7500
500050855 | CLB-MP-HAUL-DT185 -BRKSYS-PRKPP | Pump Park Brake Release | 92088 | 92088 | 7500
500050854 | CLB-MP-HAUL-DT185 -BRKSYS-BRPMP | Pump Brake | 92088 | 92088 | 7500
500050853 | CLB-MP-HAUL-DT185 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 92088 | 92088 | 7500
500050852 | CLB-MP-HAUL-DT185 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 92088 | 66177 | 7500
500050851 | CLB-MP-HAUL-DT185 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 92088 | 92088 | 7500
500050850 | CLB-MP-HAUL-DT185 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 92088 | 66177 | 7500
500050849 | CLB-MP-HAUL-DT185 -BRKSYS-SRVBK | Service Brake | 92088 | 92088 | 7500
500050848 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 92088 | 92088 | 7500
500050847 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 92088 | 92088 | 7500
500050846 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 92088 | 5725 | 7500
500050845 | CLB-MP-HAUL-DT185 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 92088 | 18375 | 7500
500050844 | CLB-MP-HAUL-DT185 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 92088 | 18375 | 7500
500050843 | CLB-MP-HAUL-DT185 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 92088 | 18375 | 7500
500050842 | CLB-MP-HAUL-DT185 -FDRSYS-DRLAX | Drive Line Axles | 92088 | 92088 | 7500
500050841 | CLB-MP-HAUL-DT185 -FDRSYS-DIFFL | Differential | 92088 | 18375 | 7500
500050840 | CLB-MP-HAUL-DT185 -FDRSYS-DRSHT | Transmission Drive Shaft | 92088 | 7001 | 7500
500050839 | CLB-MP-HAUL-DT185 -TRNSYS-TROLC | Oil Cooler Transmission | 92088 | 18375 | 7500
500050838 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 92088 | 18375 | 7500
500050837 | CLB-MP-HAUL-DT185 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 92088 | 5719 | 7500
500050836 | CLB-MP-HAUL-DT185 -TRNSYS-TRANS | Transmission | 92088 | 18375 | 7500
500050835 | CLB-MP-HAUL-DT185 -TRNSYS-TRQUE | Torque Converter | 92088 | 18375 | 7500
500050834 | CLB-MP-HAUL-DT185 -ELCTLV-CHARG-BATTY | Batteries | 92088 | 92088 | 7500
500050833 | CLB-MP-HAUL-DT185 -ELCTLV-CHARG-ALTER | Alternator 24V | 92088 | 7001 | 7500
500050832 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 92088 | 9689 | 7500
500050831 | CLB-MP-HAUL-DT185 -ENGINE-PMPDR | Pump Drive | 92088 | 18375 | 7500
500050830 | CLB-MP-HAUL-DT185 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 92088 | 18375 | 7500
500050829 | CLB-MP-HAUL-DT185 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 92088 | 7001 | 7500
500050828 | CLB-MP-HAUL-DT185 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 92088 | 7001 | 7500
500050827 | CLB-MP-HAUL-DT185 -ENGINE-FUSYS-FULTK | Fuel Tank | 92088 | 18375 | 7500
500050826 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-EXHST | Exhaust System | 92088 | 44928 | 7500
500050825 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-AFTER | Aftercooler | 92088 | 92088 | 7500
500050824 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 92088 | 7001 | 7500
500050823 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 92088 | 7001 | 7500
500050822 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 92088 | 7001 | 7500
500050821 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 92088 | 7001 | 7500
500050820 | CLB-MP-HAUL-DT185 -ENGINE-INTEX-AIRFL | Air Filtration System | 92088 | 92088 | 7500
500050819 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-THERM | Thermostats/Regulators | 92088 | 7001 | 7500
500050818 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-BELTS | Fan Belts Engine | 92088 | 29631 | 7500
500050817 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 92088 | 7001 | 7500
500050816 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-COFAN | Fan Cooling System | 92088 | 18375 | 7500
500050815 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-RADTR | Coolant Engine | 92088 | 92088 | 7400
500050814 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-RADTR | Radiator Engine | 92088 | 17708 | 7500
500050813 | CLB-MP-HAUL-DT185 -ENGINE-COSYS-WTRPP | Water Pump Engine | 92088 | 7001 | 7500
500050812 | CLB-MP-HAUL-DT185 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 92088 | 66177 | 7500
500050811 | CLB-MP-HAUL-DT185 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 92088 | 17708 | 7500
500050810 | CLB-MP-HAUL-DT185 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 92088 | 92088 | 7500
500050809 | CLB-MP-HAUL-DT185 -ENGINE-COMPR | Air Compressor | 92088 | 7001 | 7500
500050807 | CLB-MP-HAUL-DT185 -ENGINE | Engine Assembly Caterpillar 3516B | 92088 | 18375 | 7500
500050806 | CLB-MP-HAUL-DT185 | DT185 Lubrication & Mechanical Services | 92088 | 92088 | 7500
500050805 | CLB-MP-HAUL-DT185 | Caterpillar 789D Haul Truck DT185 | 92088 | 92088 | 7500
500160271 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITRH | Air Tank Right | 83208 | 83208 | 7500
500160270 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK-AITLH | Air Tank Left | 83208 | 83208 | 7500
500147258 | CLB-MP-HAUL-DT184 -STRSYS-STACC | Steering Accumulator Rear | 31706 | 31706 | 7500
500147257 | CLB-MP-HAUL-DT184 -STRSYS-STACC | Steering Accumulator Middle | 31706 | 31706 | 7500
500147256 | CLB-MP-HAUL-DT184 -STRSYS-STACC | Steering Accumulator Front | 31706 | 31706 | 7500
500118563 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-AFRME | A Frame Housing | 83473 | 9021 | 7500
500117939 | CLB-MP-HAUL-DT184 -ELCTLV-LIGHT | Lighting Low Voltage | 83473 | 50815 | 7500
500117899 | CLB-MP-HAUL-DT184 -ELCTLV-HARNS | Electrical Harness | 83473 | 50815 | 7500
500117859 | CLB-MP-HAUL-DT184 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83473 | 50815 | 7500
500117423 | CLB-MP-HAUL-DT184 -ELCTLV-LIGHT-AHSYS | AHS Lights | 83473 | 50815 | 7500
500117303 | CLB-MP-HAUL-DT184 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 83473 | 50815 | 7500
500111225 | CLB-MP-HAUL-DT184 -STRUCT-RAXHO | Rear Axle Housing | 83473 | 83473 | 7500
500110555 | CLB-MP-HAUL-DT184 -GRSYST | Grease Lubrication System | 83473 | 9451 | 7500
500102805 | CLB-MP-HAUL-DT184 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83473 | 9021 | 7500
500100632 | CLB-MP-HAUL-DT184 -TRNSYS | DT184 Transmission System | 83473 | 52386 | 7500
500081409 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83473 | 12672 | 7500
500081269 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83473 | 9021 | 7500
500079442 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN | Suspension Service | 83473 | 21188 | 7500
500078508 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 83473 | 9021 | 7500
500078471 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 83473 | 9021 | 7500
500061431 | CLB-MP-HAUL-DT184 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83473 | 9021 | 7500
500061401 | CLB-MP-HAUL-DT184 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83473 | 9021 | 7500
500061179 | CLB-MP-HAUL-DT184 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 83473 | 9021 | 7500
500061178 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-ELECT | Chassis Electrical System | 83473 | 31706 | 7500
500061177 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83473 | 83473 | 7500
500061176 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83473 | 9021 | 7500
500061175 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 83473 | 9021 | 7500
500061174 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83473 | 9021 | 7500
500061173 | CLB-MP-HAUL-DT184 -STRSYS-STHLF-STRHO | Steering System Hoses | 83473 | 9021 | 7500
500061172 | CLB-MP-HAUL-DT184 -STRSYS-STLTR-STBST | Ball Studs | 83473 | 83473 | 7500
500061171 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 83473 | 9021 | 7500
500061170 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 83473 | 9021 | 7500
500061169 | CLB-MP-HAUL-DT184 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 83473 | 9021 | 7500
500061168 | CLB-MP-HAUL-DT184 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83473 | 9021 | 7500
500061167 | CLB-MP-HAUL-DT184 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83473 | 9021 | 7500
500061166 | CLB-MP-HAUL-DT184 -BRKSYS-BRVRL | Brake Relay Valve | 83473 | 9021 | 7500
500061164 | CLB-MP-HAUL-DT184 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83473 | 9021 | 7500
500061163 | CLB-MP-HAUL-DT184 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83473 | 9021 | 7500
500060122 | CLB-MP-HAUL-DT184 -STRSYS-STTNK | Tank Steering | 83473 | 83473 | 7500
500053826 | CLB-MP-HAUL-DT184 -BRKSYS-BRVLV | Valve Brake | 83473 | 9021 | 7500
500050804 | CLB-MP-HAUL-DT184 -MANGMT-UMMMC | Mine Monitoring and Control | 83473 | 83473 | 7500
500050803 | CLB-MP-HAUL-DT184 -MANGMT-UMTRN | Power Train Management System | 83473 | 83473 | 7500
500050802 | CLB-MP-HAUL-DT184 -MANGMT-UMENG | Engine Management System | 83473 | 83473 | 7500
500050801 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83473 | 8112 | 7500
500050800 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83473 | 9021 | 7500
500050799 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83473 | 864 | 7500
500050798 | CLB-MP-HAUL-DT184 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83473 | 9021 | 7500
500050795 | CLB-MP-HAUL-DT184 -STRUCT-TRAYS | Tray | 83473 | 23883 | 7500
500050794 | CLB-MP-HAUL-DT184 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83473 | 9021 | 7500
500050793 | CLB-MP-HAUL-DT184 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83473 | 9021 | 7500
500050792 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-TAGLK | Tag Link | 83473 | 9021 | 7500
500050791 | CLB-MP-HAUL-DT184 -STRUCT-CHASS-AFRME | A Frame Bearing | 83473 | 9021 | 7500
500050790 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-SBELT | Seat Belt | 83473 | 83473 | 7500
500050789 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-SEATS | Operators Seat | 83473 | 9021 | 7500
500050788 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83473 | 57843 | 7500
500050787 | CLB-MP-HAUL-DT184 -STRUCT-CABIN-AIRCN | Air Conditioning System | 83473 | 9021 | 7500
500050786 | CLB-MP-HAUL-DT184 -STRUCT-CABIN | Operators Cabin | 83473 | 9021 | 7500
500050785 | CLB-MP-HAUL-DT184 -PNEUMC-START | Air Starter | 83473 | 9021 | 7500
500050784 | CLB-MP-HAUL-DT184 -PNEUMC-AIRDR | Air Drier | 83473 | 48934 | 7500
500050783 | CLB-MP-HAUL-DT184 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 83473 | 83473 | 7500
500050782 | CLB-MP-HAUL-DT184 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 83473 | 83473 | 7500
500050781 | CLB-MP-HAUL-DT184 -PNEUMC-PNTNK | No Not Use | 83473 | 83473 | 7500
500050780 | CLB-MP-HAUL-DT184 -GRSYST-ALCON | Auto Lube Controller | 83473 | 83473 | 7500
500050779 | CLB-MP-HAUL-DT184 -GRSYST-ALBPP | Auto Lube Pump | 83473 | 83473 | 7500
500050778 | CLB-MP-HAUL-DT184 -GRSYST-GRTNK | Auto Lube Resevoir | 83473 | 83473 | 7500
500050777 | CLB-MP-HAUL-DT184 -GRSYST-GRINJ | Auto Lube Injectors | 83473 | 83473 | 7500
500050776 | CLB-MP-HAUL-DT184 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83473 | 9021 | 7500
500050775 | CLB-MP-HAUL-DT184 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83473 | 9021 | 7500
500050774 | CLB-MP-HAUL-DT184 -HYDSYS-HOVLV | Valve Hoist | 83473 | 31706 | 7500
500050773 | CLB-MP-HAUL-DT184 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83473 | 83473 | 7500
500050772 | CLB-MP-HAUL-DT184 -HYDSYS-HDTNK | Tank Hydraulic | 83473 | 83473 | 7500
500050771 | CLB-MP-HAUL-DT184 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 83473 | 9021 | 7500
500050770 | CLB-MP-HAUL-DT184 -HYDSYS-HOPMP | Pump Hoist | 83473 | 9021 | 7500
500050769 | CLB-MP-HAUL-DT184 -HYDSYS | Hydraulic System | 83473 | 83473 | 7500
500050768 | CLB-MP-HAUL-DT184 -STRSYS-STCON-STCOL | Steering Column | 83473 | 83473 | 7500
500050767 | CLB-MP-HAUL-DT184 -STRSYS-STCON-STWHL | Steering Wheel | 83473 | 83473 | 7500
500050766 | CLB-MP-HAUL-DT184 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83473 | 34836 | 7500
500050765 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83473 | 9021 | 7500
500050764 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83473 | 9021 | 7500
500050763 | CLB-MP-HAUL-DT184 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83473 | 9021 | 7500
500050762 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83473 | 9021 | 7500
500050761 | CLB-MP-HAUL-DT184 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83473 | 15556 | 7500
500050760 | CLB-MP-HAUL-DT184 -STRSYS-STVLV | Valve Steering | 83473 | 9021 | 7500
500050759 | CLB-MP-HAUL-DT184 -STRSYS-STHMU | Steering HMU | 83473 | 9021 | 7500
500050758 | CLB-MP-HAUL-DT184 -STRSYS-STPMP | Pump Steering | 83473 | 9021 | 7500
500050757 | CLB-MP-HAUL-DT184 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83473 | 9021 | 7500
500050756 | CLB-MP-HAUL-DT184 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83473 | 9021 | 7500
500050755 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 83473 | 9021 | 7500
500050754 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 83473 | 9021 | 7500
500050753 | CLB-MP-HAUL-DT184 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 83473 | 9021 | 7500
500050752 | CLB-MP-HAUL-DT184 -BRKSYS-BACCM | Brake Accumulator | 83473 | 9021 | 7500
500050751 | CLB-MP-HAUL-DT184 -BRKSYS-BROCO | Brake Oil Cooler | 83473 | 83473 | 7500
500050750 | CLB-MP-HAUL-DT184 -BRKSYS-MERTR | Mechanical Retarder | 83473 | 83473 | 7500
500050749 | CLB-MP-HAUL-DT184 -BRKSYS-BRVTR | Valve Brake Treadle | 83473 | 83473 | 7500
500050748 | CLB-MP-HAUL-DT184 -BRKSYS-HYFPP | Pump Brake Control | 83473 | 9021 | 7500
500050747 | CLB-MP-HAUL-DT184 -BRKSYS-PRKPP | Pump Park Brake Release | 83473 | 83473 | 7500
500050746 | CLB-MP-HAUL-DT184 -BRKSYS-BRPMP | Pump Brake | 83473 | 83473 | 7500
500050745 | CLB-MP-HAUL-DT184 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83473 | 83473 | 7500
500050744 | CLB-MP-HAUL-DT184 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83473 | 83473 | 7500
500050743 | CLB-MP-HAUL-DT184 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83473 | 83473 | 7500
500050742 | CLB-MP-HAUL-DT184 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83473 | 83473 | 7500
500050741 | CLB-MP-HAUL-DT184 -BRKSYS-SRVBK | Service Brake | 83473 | 83473 | 7500
500050740 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83473 | 83473 | 7500
500050739 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83473 | 83473 | 7500
500050738 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 83473 | 9021 | 7500
500050737 | CLB-MP-HAUL-DT184 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83473 | 9021 | 7500
500050736 | CLB-MP-HAUL-DT184 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83473 | 9952 | 7500
500050735 | CLB-MP-HAUL-DT184 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83473 | 6975 | 7500
500050734 | CLB-MP-HAUL-DT184 -FDRSYS-DRLAX | Drive Line Axles | 83473 | 83473 | 7500
500050733 | CLB-MP-HAUL-DT184 -FDRSYS-DIFFL | Differential | 83473 | 9021 | 7500
500050732 | CLB-MP-HAUL-DT184 -FDRSYS-DRSHT | Transmission Drive Shaft | 83473 | 9021 | 7500
500050731 | CLB-MP-HAUL-DT184 -TRNSYS-TROLC | Oil Cooler Transmission | 83473 | 9021 | 7500
500050730 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83473 | 9021 | 7500
500050729 | CLB-MP-HAUL-DT184 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83473 | 3577 | 7500
500050728 | CLB-MP-HAUL-DT184 -TRNSYS-TRANS | Transmission | 83473 | 9021 | 7500
500050727 | CLB-MP-HAUL-DT184 -TRNSYS-TRQUE | Torque Converter | 83473 | 9021 | 7500
500050726 | CLB-MP-HAUL-DT184 -ELCTLV-CHARG-BATTY | Batteries | 83473 | 83473 | 7500
500050725 | CLB-MP-HAUL-DT184 -ELCTLV-CHARG-ALTER | Alternator 24V | 83473 | 9021 | 7500
500050724 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83473 | 9021 | 7500
500050723 | CLB-MP-HAUL-DT184 -ENGINE-PMPDR | Pump Drive | 83473 | 15555 | 7500
500050722 | CLB-MP-HAUL-DT184 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83473 | 9021 | 7500
500050721 | CLB-MP-HAUL-DT184 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83473 | 9021 | 7500
500050720 | CLB-MP-HAUL-DT184 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83473 | 9021 | 7500
500050719 | CLB-MP-HAUL-DT184 -ENGINE-FUSYS-FULTK | Fuel Tank | 83473 | 9021 | 7500
500050718 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-EXHST | Exhaust System | 83473 | 83473 | 7500
500050717 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-AFTER | Aftercooler | 83473 | 83473 | 7500
500050716 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 83473 | 9021 | 7500
500050715 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 83473 | 9021 | 7500
500050714 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 83473 | 9021 | 7500
500050713 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 83473 | 9021 | 7500
500050712 | CLB-MP-HAUL-DT184 -ENGINE-INTEX-AIRFL | Air Filtration System | 83473 | 83473 | 7500
500050711 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-THERM | Thermostats/Regulators | 83473 | 9021 | 7500
500050710 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-BELTS | Fan Belts Engine | 83473 | 83473 | 7500
500050709 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 83473 | 9021 | 7500
500050708 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-COFAN | Fan Cooling System | 83473 | 9021 | 7500
500050707 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-RADTR | Coolant Engine | 83473 | 31706 | 7400
500050706 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-RADTR | Radiator Engine | 83473 | 9021 | 7500
500050705 | CLB-MP-HAUL-DT184 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83473 | 9021 | 7500
500050704 | CLB-MP-HAUL-DT184 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83473 | 83473 | 7500
500050703 | CLB-MP-HAUL-DT184 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83473 | 9021 | 7500
500050702 | CLB-MP-HAUL-DT184 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83473 | 83473 | 7500
500050701 | CLB-MP-HAUL-DT184 -ENGINE-COMPR | Air Compressor | 83473 | 9021 | 7500
500050699 | CLB-MP-HAUL-DT184 -ENGINE | Engine Assembly Caterpillar 3516B | 83473 | 9021 | 7500
500050698 | CLB-MP-HAUL-DT184 | DT184 Lubrication & Mechanical Services | 83473 | 83473 | 7500
500050697 | CLB-MP-HAUL-DT184 | Caterpillar 789D Haul Truck DT184 | 83473 | 83473 | 7500
500160269 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITRH | Air Tank Right | 90227 | 40762 | 7500
500160268 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK-AITLH | Air Tank Left | 90227 | 40762 | 7500
500147254 | CLB-MP-HAUL-DT183 -STRSYS-STACC | Steering Accumulator Rear | 18244 | 18244 | 7500
500147253 | CLB-MP-HAUL-DT183 -STRSYS-STACC | Steering Accumulator Middle | 18244 | 18244 | 7500
500147252 | CLB-MP-HAUL-DT183 -STRSYS-STACC | Steering Accumulator Front | 18244 | 18244 | 7500
500118562 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-AFRME | A Frame Housing | 90364 | 21856 | 7500
500117938 | CLB-MP-HAUL-DT183 -ELCTLV-LIGHT | Lighting Low Voltage | 90364 | 46333 | 7500
500117898 | CLB-MP-HAUL-DT183 -ELCTLV-HARNS | Electrical Harness | 90364 | 46333 | 7500
500117858 | CLB-MP-HAUL-DT183 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 90364 | 46333 | 7500
500117422 | CLB-MP-HAUL-DT183 -ELCTLV-LIGHT-AHSYS | AHS Lights | 90364 | 46333 | 7500
500117302 | CLB-MP-HAUL-DT183 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 90364 | 46333 | 7500
500111224 | CLB-MP-HAUL-DT183 -STRUCT-RAXHO | Rear Axle Housing | 90364 | 40899 | 7500
500110554 | CLB-MP-HAUL-DT183 -GRSYST | Grease Lubrication System | 90364 | 25648 | 7500
500102804 | CLB-MP-HAUL-DT183 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 90364 | 14758 | 7500
500100631 | CLB-MP-HAUL-DT183 -TRNSYS | DT183 Transmission System | 90364 | 40899 | 7500
500081408 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 90364 | 21853 | 7500
500081268 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 90364 | 21853 | 7500
500079441 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN | Suspension Service | 90364 | 10497 | 7500
500078507 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 90364 | 18244 | 7500
500078470 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 90364 | 18244 | 7500
500062690 | CLB-MP-HAUL-DT183 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 90364 | 18244 | 7500
500062689 | CLB-MP-HAUL-DT183 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 90364 | 18244 | 7500
500062688 | CLB-MP-HAUL-DT183 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 90364 | 18244 | 7500
500062687 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-ELECT | Chassis Electrical System | 90364 | 40899 | 7500
500062686 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-ELECT | Cabin Electrical System | 90364 | 90364 | 7500
500062685 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 90364 | 18244 | 7500
500062684 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 90364 | 18244 | 7500
500062683 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 90364 | 18244 | 7500
500062682 | CLB-MP-HAUL-DT183 -STRSYS-STHLF-STRHO | Steering System Hoses | 90364 | 18244 | 7500
500062681 | CLB-MP-HAUL-DT183 -STRSYS-STLTR-STBST | Ball Studs | 90364 | 90364 | 7500
500062680 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 90364 | 18244 | 7500
500062679 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 90364 | 18244 | 7500
500062678 | CLB-MP-HAUL-DT183 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 90364 | 18244 | 7500
500062677 | CLB-MP-HAUL-DT183 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 90364 | 18244 | 7500
500062676 | CLB-MP-HAUL-DT183 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 90364 | 18244 | 7500
500062675 | CLB-MP-HAUL-DT183 -BRKSYS-BRVRL | Brake Relay Valve | 90364 | 18244 | 7500
500062673 | CLB-MP-HAUL-DT183 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 90364 | 18244 | 7500
500062672 | CLB-MP-HAUL-DT183 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 90364 | 18244 | 7500
500060121 | CLB-MP-HAUL-DT183 -STRSYS-STTNK | Tank Steering | 90364 | 90364 | 7500
500053847 | CLB-MP-HAUL-DT183 -BRKSYS-BRVLV | Valve Brake | 90364 | 18244 | 7500
500050696 | CLB-MP-HAUL-DT183 -MANGMT-UMMMC | Mine Monitoring and Control | 90364 | 90364 | 7500
500050695 | CLB-MP-HAUL-DT183 -MANGMT-UMTRN | Power Train Management System | 90364 | 90364 | 7500
500050694 | CLB-MP-HAUL-DT183 -MANGMT-UMENG | Engine Management System | 90364 | 90364 | 7500
500050693 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 90364 | 18244 | 7500
500050692 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 90364 | 18244 | 7500
500050691 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 90364 | 18244 | 7500
500050690 | CLB-MP-HAUL-DT183 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 90364 | 18244 | 7500
500050687 | CLB-MP-HAUL-DT183 -STRUCT-TRAYS | Tray | 90364 | 27199 | 7500
500050686 | CLB-MP-HAUL-DT183 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 90364 | 18244 | 7500
500050685 | CLB-MP-HAUL-DT183 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 90364 | 18244 | 7500
500050684 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-TAGLK | Tag Link | 90364 | 21853 | 7500
500050683 | CLB-MP-HAUL-DT183 -STRUCT-CHASS-AFRME | A Frame Bearing | 90364 | 21856 | 7500
500050682 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-SBELT | Seat Belt | 90364 | 90364 | 7500
500050681 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-SEATS | Operators Seat | 90364 | 40899 | 7500
500050680 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 90364 | 90364 | 7500
500050679 | CLB-MP-HAUL-DT183 -STRUCT-CABIN-AIRCN | Air Conditioning System | 90364 | 6327 | 7500
500050678 | CLB-MP-HAUL-DT183 -STRUCT-CABIN | Operators Cabin | 90364 | 18244 | 7500
500050677 | CLB-MP-HAUL-DT183 -PNEUMC-START | Air Starter | 90364 | 6327 | 7500
500050676 | CLB-MP-HAUL-DT183 -PNEUMC-AIRDR | Air Drier | 90364 | 56923 | 7500
500050675 | CLB-MP-HAUL-DT183 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 90364 | 90364 | 7500
500050674 | CLB-MP-HAUL-DT183 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 90364 | 90364 | 7500
500050673 | CLB-MP-HAUL-DT183 -PNEUMC-PNTNK | No Not Use | 90364 | 40899 | 7500
500050672 | CLB-MP-HAUL-DT183 -GRSYST-ALCON | Auto Lube Controller | 90364 | 90364 | 7500
500050671 | CLB-MP-HAUL-DT183 -GRSYST-ALBPP | Auto Lube Pump | 90364 | 39470 | 7500
500050670 | CLB-MP-HAUL-DT183 -GRSYST-GRTNK | Auto Lube Resevoir | 90364 | 90364 | 7500
500050669 | CLB-MP-HAUL-DT183 -GRSYST-GRINJ | Auto Lube Injectors | 90364 | 90364 | 7500
500050668 | CLB-MP-HAUL-DT183 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 90364 | 18244 | 7500
500050667 | CLB-MP-HAUL-DT183 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 90364 | 18244 | 7500
500050666 | CLB-MP-HAUL-DT183 -HYDSYS-HOVLV | Valve Hoist | 90364 | 18244 | 7500
500050665 | CLB-MP-HAUL-DT183 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 90364 | 90364 | 7500
500050664 | CLB-MP-HAUL-DT183 -HYDSYS-HDTNK | Tank Hydraulic | 90364 | 90364 | 7500
500050663 | CLB-MP-HAUL-DT183 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 90364 | 18244 | 7500
500050662 | CLB-MP-HAUL-DT183 -HYDSYS-HOPMP | Pump Hoist | 90364 | 27555 | 7500
500050661 | CLB-MP-HAUL-DT183 -HYDSYS | Hydraulic System | 90364 | 90364 | 7500
500050660 | CLB-MP-HAUL-DT183 -STRSYS-STCON-STCOL | Steering Column | 90364 | 90364 | 7500
500050659 | CLB-MP-HAUL-DT183 -STRSYS-STCON-STWHL | Steering Wheel | 90364 | 90364 | 7500
500050658 | CLB-MP-HAUL-DT183 -STRSYS-STLTR | Steering Linkages and Tie Rods | 90364 | 20591 | 7500
500050657 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 90364 | 18244 | 7500
500050656 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 90364 | 18244 | 7500
500050655 | CLB-MP-HAUL-DT183 -STRSYS-STACC-SACCF | Accumulator Steering Front | 90364 | 18244 | 7500
500050654 | CLB-MP-HAUL-DT183 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 90364 | 2831 | 7500
500050653 | CLB-MP-HAUL-DT183 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 90364 | 5723 | 7500
500050652 | CLB-MP-HAUL-DT183 -STRSYS-STVLV | Valve Steering | 90364 | 1547 | 7500
500050651 | CLB-MP-HAUL-DT183 -STRSYS-STHMU | Steering HMU | 90364 | 12780 | 7500
500050650 | CLB-MP-HAUL-DT183 -STRSYS-STPMP | Pump Steering | 90364 | 12780 | 7500
500050649 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 90364 | 18244 | 7500
500050648 | CLB-MP-HAUL-DT183 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 90364 | 18244 | 7500
500050647 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 90364 | 18244 | 7500
500050646 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 90364 | 18244 | 7500
500050645 | CLB-MP-HAUL-DT183 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 90364 | 18244 | 7500
500050644 | CLB-MP-HAUL-DT183 -BRKSYS-BACCM | Brake Accumulator | 90364 | 18244 | 7500
500050643 | CLB-MP-HAUL-DT183 -BRKSYS-BROCO | Brake Oil Cooler | 90364 | 90364 | 7500
500050642 | CLB-MP-HAUL-DT183 -BRKSYS-MERTR | Mechanical Retarder | 90364 | 90364 | 7500
500050641 | CLB-MP-HAUL-DT183 -BRKSYS-BRVTR | Valve Brake Treadle | 90364 | 90364 | 7500
500050640 | CLB-MP-HAUL-DT183 -BRKSYS-HYFPP | Pump Brake Control | 90364 | 7008 | 7500
500050639 | CLB-MP-HAUL-DT183 -BRKSYS-PRKPP | Pump Park Brake Release | 90364 | 90364 | 7500
500050638 | CLB-MP-HAUL-DT183 -BRKSYS-BRPMP | Pump Brake | 90364 | 90364 | 7500
500050637 | CLB-MP-HAUL-DT183 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 90364 | 90364 | 7500
500050636 | CLB-MP-HAUL-DT183 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 90364 | 90364 | 7500
500050635 | CLB-MP-HAUL-DT183 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 90364 | 90364 | 7500
500050634 | CLB-MP-HAUL-DT183 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 90364 | 90364 | 7500
500050633 | CLB-MP-HAUL-DT183 -BRKSYS-SRVBK | Service Brake | 90364 | 90364 | 7500
500050632 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 90364 | 90364 | 7500
500050631 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 90364 | 90364 | 7500
500050630 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 90364 | 7023 | 7500
500050629 | CLB-MP-HAUL-DT183 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 90364 | 18244 | 7500
500050628 | CLB-MP-HAUL-DT183 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 90364 | 12098 | 7500
500050627 | CLB-MP-HAUL-DT183 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 90364 | 15384 | 7500
500050626 | CLB-MP-HAUL-DT183 -FDRSYS-DRLAX | Drive Line Axles | 90364 | 90364 | 7500
500050625 | CLB-MP-HAUL-DT183 -FDRSYS-DIFFL | Differential | 90364 | 5008 | 7500
500050624 | CLB-MP-HAUL-DT183 -FDRSYS-DRSHT | Transmission Drive Shaft | 90364 | 26375 | 7500
500050623 | CLB-MP-HAUL-DT183 -TRNSYS-TROLC | Oil Cooler Transmission | 90364 | 18244 | 7500
500050622 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 90364 | 8227 | 7500
500050621 | CLB-MP-HAUL-DT183 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 90364 | 7008 | 7500
500050620 | CLB-MP-HAUL-DT183 -TRNSYS-TRANS | Transmission | 90364 | 8227 | 7500
500050619 | CLB-MP-HAUL-DT183 -TRNSYS-TRQUE | Torque Converter | 90364 | 18244 | 7500
500050618 | CLB-MP-HAUL-DT183 -ELCTLV-CHARG-BATTY | Batteries | 90364 | 90364 | 7500
500050617 | CLB-MP-HAUL-DT183 -ELCTLV-CHARG-ALTER | Alternator 24V | 90364 | 6327 | 7500
500050616 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 90364 | 18244 | 7500
500050615 | CLB-MP-HAUL-DT183 -ENGINE-PMPDR | Pump Drive | 90364 | 4372 | 7500
500050614 | CLB-MP-HAUL-DT183 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 90364 | 18244 | 7500
500050613 | CLB-MP-HAUL-DT183 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 90364 | 6327 | 7500
500050612 | CLB-MP-HAUL-DT183 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 90364 | 6327 | 7500
500050611 | CLB-MP-HAUL-DT183 -ENGINE-FUSYS-FULTK | Fuel Tank | 90364 | 18244 | 7500
500050610 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-EXHST | Exhaust System | 90364 | 40899 | 7500
500050609 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-AFTER | Aftercooler | 90364 | 90364 | 7500
500050608 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 90364 | 6327 | 7500
500050607 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 90364 | 6327 | 7500
500050606 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 90364 | 6327 | 7500
500050605 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 90364 | 6327 | 7500
500050604 | CLB-MP-HAUL-DT183 -ENGINE-INTEX-AIRFL | Air Filtration System | 90364 | 90364 | 7500
500050603 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-THERM | Thermostats/Regulators | 90364 | 6327 | 7500
500050602 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-BELTS | Fan Belts Engine | 90364 | 90364 | 7500
500050601 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 90364 | 6327 | 7500
500050600 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-COFAN | Fan Cooling System | 90364 | 4126 | 7500
500050599 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-RADTR | Coolant Engine | 90364 | 18244 | 7400
500050598 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-RADTR | Radiator Engine | 90364 | 18244 | 7500
500050597 | CLB-MP-HAUL-DT183 -ENGINE-COSYS-WTRPP | Water Pump Engine | 90364 | 3630 | 7500
500050596 | CLB-MP-HAUL-DT183 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 90364 | 90364 | 7500
500050595 | CLB-MP-HAUL-DT183 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 90364 | 18244 | 7500
500050594 | CLB-MP-HAUL-DT183 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 90364 | 40899 | 7500
500050593 | CLB-MP-HAUL-DT183 -ENGINE-COMPR | Air Compressor | 90364 | 6327 | 7500
500050591 | CLB-MP-HAUL-DT183 -ENGINE | Engine Assembly Caterpillar 3516B | 90364 | 18244 | 7500
500050590 | CLB-MP-HAUL-DT183 | DT183 Lubrication & Mechanical Services | 90364 | 90364 | 7500
500050589 | CLB-MP-HAUL-DT183 | Caterpillar 789D Haul Truck DT183 | 90364 | 90364 | 7500
500160267 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITRH | Air Tank Right | 91739 | 50479 | 7500
500160266 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK-AITLH | Air Tank Left | 91739 | 50479 | 7500
500118561 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-AFRME | A Frame Housing | 92002 | 21376 | 7500
500117937 | CLB-MP-HAUL-DT182 -ELCTLV-LIGHT | Lighting Low Voltage | 92002 | 45995 | 7500
500117897 | CLB-MP-HAUL-DT182 -ELCTLV-HARNS | Electrical Harness | 92002 | 45995 | 7500
500117857 | CLB-MP-HAUL-DT182 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 92002 | 45995 | 7500
500117421 | CLB-MP-HAUL-DT182 -ELCTLV-LIGHT-AHSYS | AHS Lights | 92002 | 45995 | 7500
500117301 | CLB-MP-HAUL-DT182 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 92002 | 45995 | 7500
500111223 | CLB-MP-HAUL-DT182 -STRUCT-RAXHO | Rear Axle Housing | 92002 | 44136 | 7500
500110553 | CLB-MP-HAUL-DT182 -GRSYST | Grease Lubrication System | 92002 | 31577 | 7500
500102803 | CLB-MP-HAUL-DT182 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 92002 | 9389 | 7500
500100630 | CLB-MP-HAUL-DT182 -TRNSYS | DT182 Transmission System | 92002 | 46671 | 7500
500081407 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 92002 | 21376 | 7500
500081267 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 92002 | 21376 | 7500
500079440 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN | Suspension Service | 92002 | 16119 | 7500
500078506 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 92002 | 21376 | 7500
500078469 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 92002 | 21376 | 7500
500061430 | CLB-MP-HAUL-DT182 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 92002 | 21376 | 7500
500061400 | CLB-MP-HAUL-DT182 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 92002 | 21376 | 7500
500061162 | CLB-MP-HAUL-DT182 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 92002 | 21376 | 7500
500061161 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-ELECT | Chassis Electrical System | 92002 | 44136 | 7500
500061160 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-ELECT | Cabin Electrical System | 92002 | 92002 | 7500
500061159 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 92002 | 21376 | 7500
500061158 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 92002 | 21376 | 7500
500061157 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 92002 | 21376 | 7500
500061156 | CLB-MP-HAUL-DT182 -STRSYS-STHLF-STRHO | Steering System Hoses | 92002 | 21376 | 7500
500061155 | CLB-MP-HAUL-DT182 -STRSYS-STLTR-STBST | Ball Studs | 92002 | 92002 | 7500
500061154 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 92002 | 21376 | 7500
500061153 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 92002 | 21376 | 7500
500061152 | CLB-MP-HAUL-DT182 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 92002 | 21376 | 7500
500061151 | CLB-MP-HAUL-DT182 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 92002 | 21376 | 7500
500061150 | CLB-MP-HAUL-DT182 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 92002 | 21376 | 7500
500061149 | CLB-MP-HAUL-DT182 -BRKSYS-BRVRL | Brake Relay Valve | 92002 | 16119 | 7500
500061147 | CLB-MP-HAUL-DT182 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 92002 | 21376 | 7500
500061146 | CLB-MP-HAUL-DT182 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 92002 | 21376 | 7500
500060120 | CLB-MP-HAUL-DT182 -STRSYS-STTNK | Tank Steering | 92002 | 92002 | 7500
500053846 | CLB-MP-HAUL-DT182 -BRKSYS-BRVLV | Valve Brake | 92002 | 21376 | 7500
500050588 | CLB-MP-HAUL-DT182 -MANGMT-UMMMC | Mine Monitoring and Control | 92002 | 92002 | 7500
500050587 | CLB-MP-HAUL-DT182 -MANGMT-UMTRN | Power Train Management System | 92002 | 92002 | 7500
500050586 | CLB-MP-HAUL-DT182 -MANGMT-UMENG | Engine Management System | 92002 | 92002 | 7500
500050585 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 92002 | 36584 | 7500
500050584 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 92002 | 21376 | 7500
500050583 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 92002 | 10817 | 7500
500050582 | CLB-MP-HAUL-DT182 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 92002 | 18987 | 7500
500050579 | CLB-MP-HAUL-DT182 -STRUCT-TRAYS | Tray | 92002 | 26683 | 7500
500050578 | CLB-MP-HAUL-DT182 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 92002 | 2590 | 7500
500050577 | CLB-MP-HAUL-DT182 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 92002 | 21376 | 7500
500050576 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-TAGLK | Tag Link | 92002 | 21376 | 7500
500050575 | CLB-MP-HAUL-DT182 -STRUCT-CHASS-AFRME | A Frame Bearing | 92002 | 21376 | 7500
500050574 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-SBELT | Seat Belt | 92002 | 92002 | 7500
500050573 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-SEATS | Operators Seat | 92002 | 14717 | 7500
500050572 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 92002 | 92002 | 7500
500050571 | CLB-MP-HAUL-DT182 -STRUCT-CABIN-AIRCN | Air Conditioning System | 92002 | 14039 | 7500
500050570 | CLB-MP-HAUL-DT182 -STRUCT-CABIN | Operators Cabin | 92002 | 19592 | 7500
500050569 | CLB-MP-HAUL-DT182 -PNEUMC-START | Air Starter | 92002 | 4686 | 7500
500050568 | CLB-MP-HAUL-DT182 -PNEUMC-AIRDR | Air Drier | 92002 | 21376 | 7500
500050567 | CLB-MP-HAUL-DT182 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 92002 | 92002 | 7500
500050566 | CLB-MP-HAUL-DT182 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 92002 | 92002 | 7500
500050565 | CLB-MP-HAUL-DT182 -PNEUMC-PNTNK | No Not Use | 92002 | 50742 | 7500
500050564 | CLB-MP-HAUL-DT182 -GRSYST-ALCON | Auto Lube Controller | 92002 | 92002 | 7500
500050563 | CLB-MP-HAUL-DT182 -GRSYST-ALBPP | Auto Lube Pump | 92002 | 71210 | 7500
500050562 | CLB-MP-HAUL-DT182 -GRSYST-GRTNK | Auto Lube Resevoir | 92002 | 92002 | 7500
500050561 | CLB-MP-HAUL-DT182 -GRSYST-GRINJ | Auto Lube Injectors | 92002 | 92002 | 7500
500050560 | CLB-MP-HAUL-DT182 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 92002 | 21376 | 7500
500050559 | CLB-MP-HAUL-DT182 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 92002 | 28258 | 7500
500050558 | CLB-MP-HAUL-DT182 -HYDSYS-HOVLV | Valve Hoist | 92002 | 34492 | 7500
500050557 | CLB-MP-HAUL-DT182 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 92002 | 92002 | 7500
500050556 | CLB-MP-HAUL-DT182 -HYDSYS-HDTNK | Tank Hydraulic | 92002 | 92002 | 7500
500050555 | CLB-MP-HAUL-DT182 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 92002 | 21376 | 7500
500050554 | CLB-MP-HAUL-DT182 -HYDSYS-HOPMP | Pump Hoist | 92002 | 4017 | 7500
500050553 | CLB-MP-HAUL-DT182 -HYDSYS | Hydraulic System | 92002 | 92002 | 7500
500050552 | CLB-MP-HAUL-DT182 -STRSYS-STCON-STCOL | Steering Column | 92002 | 92002 | 7500
500050551 | CLB-MP-HAUL-DT182 -STRSYS-STCON-STWHL | Steering Wheel | 92002 | 92002 | 7500
500050550 | CLB-MP-HAUL-DT182 -STRSYS-STLTR | Steering Linkages and Tie Rods | 92002 | 13490 | 7500
500050549 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 92002 | 21376 | 7500
500050548 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 92002 | 21376 | 7500
500050547 | CLB-MP-HAUL-DT182 -STRSYS-STACC-SACCF | Accumulator Steering Front | 92002 | 21376 | 7500
500050546 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 92002 | 13490 | 7500
500050545 | CLB-MP-HAUL-DT182 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 92002 | 13490 | 7500
500050544 | CLB-MP-HAUL-DT182 -STRSYS-STVLV | Valve Steering | 92002 | 5357 | 7500
500050543 | CLB-MP-HAUL-DT182 -STRSYS-STHMU | Steering HMU | 92002 | 13490 | 7500
500050542 | CLB-MP-HAUL-DT182 -STRSYS-STPMP | Pump Steering | 92002 | 13503 | 7500
500050541 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 92002 | 14717 | 7500
500050540 | CLB-MP-HAUL-DT182 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 92002 | 14717 | 7500
500050539 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 92002 | 4021 | 7500
500050538 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 92002 | 21376 | 7500
500050537 | CLB-MP-HAUL-DT182 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 92002 | 22684 | 7500
500050536 | CLB-MP-HAUL-DT182 -BRKSYS-BACCM | Brake Accumulator | 92002 | 21376 | 7500
500050535 | CLB-MP-HAUL-DT182 -BRKSYS-BROCO | Brake Oil Cooler | 92002 | 92002 | 7500
500050534 | CLB-MP-HAUL-DT182 -BRKSYS-MERTR | Mechanical Retarder | 92002 | 92002 | 7500
500050533 | CLB-MP-HAUL-DT182 -BRKSYS-BRVTR | Valve Brake Treadle | 92002 | 92002 | 7500
500050532 | CLB-MP-HAUL-DT182 -BRKSYS-HYFPP | Pump Brake Control | 92002 | 6691 | 7500
500050531 | CLB-MP-HAUL-DT182 -BRKSYS-PRKPP | Pump Park Brake Release | 92002 | 92002 | 7500
500050530 | CLB-MP-HAUL-DT182 -BRKSYS-BRPMP | Pump Brake | 92002 | 30841 | 7500
500050529 | CLB-MP-HAUL-DT182 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 92002 | 92002 | 7500
500050528 | CLB-MP-HAUL-DT182 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 92002 | 77336 | 7500
500050527 | CLB-MP-HAUL-DT182 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 92002 | 92002 | 7500
500050526 | CLB-MP-HAUL-DT182 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 92002 | 92002 | 7500
500050525 | CLB-MP-HAUL-DT182 -BRKSYS-SRVBK | Service Brake | 92002 | 92002 | 7500
500050524 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 92002 | 92002 | 7500
500050523 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 92002 | 92002 | 7500
500050522 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 92002 | 9389 | 7500
500050521 | CLB-MP-HAUL-DT182 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 92002 | 29474 | 7500
500050520 | CLB-MP-HAUL-DT182 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 92002 | 7959 | 7500
500050519 | CLB-MP-HAUL-DT182 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 92002 | 1213 | 7500
500050518 | CLB-MP-HAUL-DT182 -FDRSYS-DRLAX | Drive Line Axles | 92002 | 92002 | 7500
500050517 | CLB-MP-HAUL-DT182 -FDRSYS-DIFFL | Differential | 92002 | 7368 | 7500
500050516 | CLB-MP-HAUL-DT182 -FDRSYS-DRSHT | Transmission Drive Shaft | 92002 | 32209 | 7500
500050515 | CLB-MP-HAUL-DT182 -TRNSYS-TROLC | Oil Cooler Transmission | 92002 | 26654 | 7500
500050514 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 92002 | 1213 | 7500
500050513 | CLB-MP-HAUL-DT182 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 92002 | 14699 | 7500
500050512 | CLB-MP-HAUL-DT182 -TRNSYS-TRANS | Transmission | 92002 | 21376 | 7500
500050511 | CLB-MP-HAUL-DT182 -TRNSYS-TRQUE | Torque Converter | 92002 | 21376 | 7500
500050510 | CLB-MP-HAUL-DT182 -ELCTLV-CHARG-BATTY | Batteries | 92002 | 29474 | 7500
500050509 | CLB-MP-HAUL-DT182 -ELCTLV-CHARG-ALTER | Alternator 24V | 92002 | 9389 | 7500
500050508 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 92002 | 9389 | 7500
500050507 | CLB-MP-HAUL-DT182 -ENGINE-PMPDR | Pump Drive | 92002 | 21376 | 7500
500050506 | CLB-MP-HAUL-DT182 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 92002 | 21376 | 7500
500050505 | CLB-MP-HAUL-DT182 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 92002 | 9389 | 7500
500050504 | CLB-MP-HAUL-DT182 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 92002 | 9389 | 7500
500050503 | CLB-MP-HAUL-DT182 -ENGINE-FUSYS-FULTK | Fuel Tank | 92002 | 4021 | 7500
500050502 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-EXHST | Exhaust System | 92002 | 92002 | 7500
500050501 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-AFTER | Aftercooler | 92002 | 92002 | 7500
500050500 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 92002 | 3513 | 7500
500050499 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 92002 | 3513 | 7500
500050498 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 92002 | 9389 | 7500
500050497 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 92002 | 9389 | 7500
500050496 | CLB-MP-HAUL-DT182 -ENGINE-INTEX-AIRFL | Air Filtration System | 92002 | 92002 | 7500
500050495 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-THERM | Thermostats/Regulators | 92002 | 9389 | 7500
500050494 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-BELTS | Fan Belts Engine | 92002 | 9389 | 7500
500050493 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 92002 | 9389 | 7500
500050492 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-COFAN | Fan Cooling System | 92002 | 21376 | 7500
500050491 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-RADTR | Coolant Engine | 92002 | 21376 | 7400
500050490 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-RADTR | Radiator Engine | 92002 | 21376 | 7500
500050489 | CLB-MP-HAUL-DT182 -ENGINE-COSYS-WTRPP | Water Pump Engine | 92002 | 9389 | 7500
500050488 | CLB-MP-HAUL-DT182 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 92002 | 92002 | 7500
500050487 | CLB-MP-HAUL-DT182 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 92002 | 21376 | 7500
500050486 | CLB-MP-HAUL-DT182 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 92002 | 92002 | 7500
500050485 | CLB-MP-HAUL-DT182 -ENGINE-COMPR | Air Compressor | 92002 | 9389 | 7500
500050483 | CLB-MP-HAUL-DT182 -ENGINE | Engine Assembly Caterpillar 3516B | 92002 | 21376 | 7500
500050482 | CLB-MP-HAUL-DT182 | DT182 Lubrication & Mechanical Services | 92002 | 92002 | 7500
500050481 | CLB-MP-HAUL-DT182 | Caterpillar 789D Haul Truck DT182 | 92002 | 92002 | 7500
500160265 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITRH | Air Tank Right | 83200 | 57009 | 7500
500160264 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK-AITLH | Air Tank Left | 83200 | 57009 | 7500
500147250 | CLB-MP-HAUL-DT181 -STRSYS-STACC | Steering Accumulator Rear | 33433 | 33433 | 7500
500147249 | CLB-MP-HAUL-DT181 -STRSYS-STACC | Steering Accumulator Middle | 33433 | 33433 | 7500
500147248 | CLB-MP-HAUL-DT181 -STRSYS-STACC | Steering Accumulator Front | 33433 | 33433 | 7500
500118560 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-AFRME | A Frame Housing | 83441 | 10076 | 7500
500117936 | CLB-MP-HAUL-DT181 -ELCTLV-LIGHT | Lighting Low Voltage | 83441 | 50282 | 7500
500117896 | CLB-MP-HAUL-DT181 -ELCTLV-HARNS | Electrical Harness | 83441 | 50282 | 7500
500117856 | CLB-MP-HAUL-DT181 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83441 | 50282 | 7500
500117420 | CLB-MP-HAUL-DT181 -ELCTLV-LIGHT-AHSYS | AHS Lights | 83441 | 50282 | 7500
500117300 | CLB-MP-HAUL-DT181 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 83441 | 50282 | 7500
500111222 | CLB-MP-HAUL-DT181 -STRUCT-RAXHO | Rear Axle Housing | 83441 | 10076 | 7500
500110552 | CLB-MP-HAUL-DT181 -GRSYST | Grease Lubrication System | 83441 | 10382 | 7500
500102802 | CLB-MP-HAUL-DT181 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83441 | 10076 | 7500
500100629 | CLB-MP-HAUL-DT181 -TRNSYS | DT181 Transmission System | 83441 | 41898 | 7500
500081406 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83441 | 16291 | 7500
500081266 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83441 | 16291 | 7500
500079439 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN | Suspension Service | 83441 | 10065 | 7500
500078505 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 83441 | 10076 | 7500
500078468 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 83441 | 10076 | 7500
500062671 | CLB-MP-HAUL-DT181 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83441 | 10076 | 7500
500062670 | CLB-MP-HAUL-DT181 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83441 | 10076 | 7500
500062669 | CLB-MP-HAUL-DT181 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 83441 | 10076 | 7500
500062668 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-ELECT | Chassis Electrical System | 83441 | 33433 | 7500
500062667 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83441 | 83441 | 7500
500062666 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83441 | 10076 | 7500
500062665 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 83441 | 10076 | 7500
500062664 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83441 | 10076 | 7500
500062663 | CLB-MP-HAUL-DT181 -STRSYS-STHLF-STRHO | Steering System Hoses | 83441 | 10076 | 7500
500062662 | CLB-MP-HAUL-DT181 -STRSYS-STLTR-STBST | Ball Studs | 83441 | 83441 | 7500
500062661 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 83441 | 10076 | 7500
500062660 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 83441 | 10076 | 7500
500062659 | CLB-MP-HAUL-DT181 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 83441 | 10076 | 7500
500062658 | CLB-MP-HAUL-DT181 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83441 | 10076 | 7500
500062657 | CLB-MP-HAUL-DT181 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83441 | 10076 | 7500
500062656 | CLB-MP-HAUL-DT181 -BRKSYS-BRVRL | Brake Relay Valve | 83441 | 10076 | 7500
500062654 | CLB-MP-HAUL-DT181 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83441 | 10076 | 7500
500062653 | CLB-MP-HAUL-DT181 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83441 | 10076 | 7500
500060119 | CLB-MP-HAUL-DT181 -STRSYS-STTNK | Tank Steering | 83441 | 83441 | 7500
500053845 | CLB-MP-HAUL-DT181 -BRKSYS-BRVLV | Valve Brake | 83441 | 10076 | 7500
500050480 | CLB-MP-HAUL-DT181 -MANGMT-UMMMC | Mine Monitoring and Control | 83441 | 83441 | 7500
500050479 | CLB-MP-HAUL-DT181 -MANGMT-UMTRN | Power Train Management System | 83441 | 83441 | 7500
500050478 | CLB-MP-HAUL-DT181 -MANGMT-UMENG | Engine Management System | 83441 | 83441 | 7500
500050477 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83441 | 10076 | 7500
500050476 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83441 | 10076 | 7500
500050475 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83441 | 10076 | 7500
500050474 | CLB-MP-HAUL-DT181 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83441 | 10076 | 7500
500050471 | CLB-MP-HAUL-DT181 -STRUCT-TRAYS | Tray | 83441 | 33433 | 7500
500050470 | CLB-MP-HAUL-DT181 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83441 | 10076 | 7500
500050469 | CLB-MP-HAUL-DT181 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83441 | 10076 | 7500
500050468 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-TAGLK | Tag Link | 83441 | 10076 | 7500
500050467 | CLB-MP-HAUL-DT181 -STRUCT-CHASS-AFRME | A Frame Bearing | 83441 | 10076 | 7500
500050466 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-SBELT | Seat Belt | 83441 | 83441 | 7500
500050465 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-SEATS | Operators Seat | 83441 | 10076 | 7500
500050464 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83441 | 83441 | 7500
500050463 | CLB-MP-HAUL-DT181 -STRUCT-CABIN-AIRCN | Air Conditioning System | 83441 | 10076 | 7500
500050462 | CLB-MP-HAUL-DT181 -STRUCT-CABIN | Operators Cabin | 83441 | 10076 | 7500
500050461 | CLB-MP-HAUL-DT181 -PNEUMC-START | Air Starter | 83441 | 10076 | 7500
500050460 | CLB-MP-HAUL-DT181 -PNEUMC-AIRDR | Air Drier | 83441 | 10076 | 7500
500050459 | CLB-MP-HAUL-DT181 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 83441 | 83441 | 7500
500050458 | CLB-MP-HAUL-DT181 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 83441 | 83441 | 7500
500050457 | CLB-MP-HAUL-DT181 -PNEUMC-PNTNK | No Not Use | 83441 | 57250 | 7500
500050456 | CLB-MP-HAUL-DT181 -GRSYST-ALCON | Auto Lube Controller | 83441 | 83441 | 7500
500050455 | CLB-MP-HAUL-DT181 -GRSYST-ALBPP | Auto Lube Pump | 83441 | 83441 | 7500
500050454 | CLB-MP-HAUL-DT181 -GRSYST-GRTNK | Auto Lube Resevoir | 83441 | 83441 | 7500
500050453 | CLB-MP-HAUL-DT181 -GRSYST-GRINJ | Auto Lube Injectors | 83441 | 83441 | 7500
500050452 | CLB-MP-HAUL-DT181 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83441 | 21399 | 7500
500050451 | CLB-MP-HAUL-DT181 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83441 | 20906 | 7500
500050450 | CLB-MP-HAUL-DT181 -HYDSYS-HOVLV | Valve Hoist | 83441 | 33433 | 7500
500050449 | CLB-MP-HAUL-DT181 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83441 | 83441 | 7500
500050448 | CLB-MP-HAUL-DT181 -HYDSYS-HDTNK | Tank Hydraulic | 83441 | 83441 | 7500
500050447 | CLB-MP-HAUL-DT181 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 83441 | 10076 | 7500
500050446 | CLB-MP-HAUL-DT181 -HYDSYS-HOPMP | Pump Hoist | 83441 | 10076 | 7500
500050445 | CLB-MP-HAUL-DT181 -HYDSYS | Hydraulic System | 83441 | 83441 | 7500
500050444 | CLB-MP-HAUL-DT181 -STRSYS-STCON-STCOL | Steering Column | 83441 | 48219 | 7500
500050443 | CLB-MP-HAUL-DT181 -STRSYS-STCON-STWHL | Steering Wheel | 83441 | 83441 | 7500
500050442 | CLB-MP-HAUL-DT181 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83441 | 22176 | 7500
500050441 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83441 | 10076 | 7500
500050440 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83441 | 10076 | 7500
500050439 | CLB-MP-HAUL-DT181 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83441 | 10076 | 7500
500050438 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83441 | 1688 | 7500
500050437 | CLB-MP-HAUL-DT181 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83441 | 16291 | 7500
500050436 | CLB-MP-HAUL-DT181 -STRSYS-STVLV | Valve Steering | 83441 | 10076 | 7500
500050435 | CLB-MP-HAUL-DT181 -STRSYS-STHMU | Steering HMU | 83441 | 22176 | 7500
500050434 | CLB-MP-HAUL-DT181 -STRSYS-STPMP | Pump Steering | 83441 | 5808 | 7500
500050433 | CLB-MP-HAUL-DT181 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83441 | 10076 | 7500
500050432 | CLB-MP-HAUL-DT181 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83441 | 10076 | 7500
500050431 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 83441 | 10076 | 7500
500050430 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 83441 | 10076 | 7500
500050429 | CLB-MP-HAUL-DT181 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 83441 | 10076 | 7500
500050428 | CLB-MP-HAUL-DT181 -BRKSYS-BACCM | Brake Accumulator | 83441 | 10076 | 7500
500050427 | CLB-MP-HAUL-DT181 -BRKSYS-BROCO | Brake Oil Cooler | 83441 | 54752 | 7500
500050426 | CLB-MP-HAUL-DT181 -BRKSYS-MERTR | Mechanical Retarder | 83441 | 83441 | 7500
500050425 | CLB-MP-HAUL-DT181 -BRKSYS-BRVTR | Valve Brake Treadle | 83441 | 83441 | 7500
500050424 | CLB-MP-HAUL-DT181 -BRKSYS-HYFPP | Pump Brake Control | 83441 | 8454 | 7500
500050423 | CLB-MP-HAUL-DT181 -BRKSYS-PRKPP | Pump Park Brake Release | 83441 | 83441 | 7500
500050422 | CLB-MP-HAUL-DT181 -BRKSYS-BRPMP | Pump Brake | 83441 | 83441 | 7500
500050421 | CLB-MP-HAUL-DT181 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83441 | 83441 | 7500
500050420 | CLB-MP-HAUL-DT181 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83441 | 83441 | 7500
500050419 | CLB-MP-HAUL-DT181 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83441 | 83441 | 7500
500050418 | CLB-MP-HAUL-DT181 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83441 | 83441 | 7500
500050417 | CLB-MP-HAUL-DT181 -BRKSYS-SRVBK | Service Brake | 83441 | 83441 | 7500
500050416 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83441 | 83441 | 7500
500050415 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83441 | 83441 | 7500
500050414 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 83441 | 10076 | 7500
500050413 | CLB-MP-HAUL-DT181 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83441 | 10076 | 7500
500050412 | CLB-MP-HAUL-DT181 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83441 | 5808 | 7500
500050411 | CLB-MP-HAUL-DT181 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83441 | 2972 | 7500
500050410 | CLB-MP-HAUL-DT181 -FDRSYS-DRLAX | Drive Line Axles | 83441 | 83441 | 7500
500050409 | CLB-MP-HAUL-DT181 -FDRSYS-DIFFL | Differential | 83441 | 10076 | 7500
500050408 | CLB-MP-HAUL-DT181 -FDRSYS-DRSHT | Transmission Drive Shaft | 83441 | 10076 | 7500
500050407 | CLB-MP-HAUL-DT181 -TRNSYS-TROLC | Oil Cooler Transmission | 83441 | 10076 | 7500
500050406 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83441 | 27802 | 7500
500050405 | CLB-MP-HAUL-DT181 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83441 | 10076 | 7500
500050404 | CLB-MP-HAUL-DT181 -TRNSYS-TRANS | Transmission | 83441 | 10076 | 7500
500050403 | CLB-MP-HAUL-DT181 -TRNSYS-TRQUE | Torque Converter | 83441 | 10076 | 7500
500050402 | CLB-MP-HAUL-DT181 -ELCTLV-CHARG-BATTY | Batteries | 83441 | 83441 | 7500
500050401 | CLB-MP-HAUL-DT181 -ELCTLV-CHARG-ALTER | Alternator 24V | 83441 | 10076 | 7500
500050400 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83441 | 15445 | 7500
500050399 | CLB-MP-HAUL-DT181 -ENGINE-PMPDR | Pump Drive | 83441 | 10076 | 7500
500050398 | CLB-MP-HAUL-DT181 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83441 | 10076 | 7500
500050397 | CLB-MP-HAUL-DT181 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83441 | 10076 | 7500
500050396 | CLB-MP-HAUL-DT181 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83441 | 10076 | 7500
500050395 | CLB-MP-HAUL-DT181 -ENGINE-FUSYS-FULTK | Fuel Tank | 83441 | 10076 | 7500
500050394 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-EXHST | Exhaust System | 83441 | 83441 | 7500
500050393 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-AFTER | Aftercooler | 83441 | 37512 | 7500
500050392 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 83441 | 10076 | 7500
500050391 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 83441 | 10076 | 7500
500050390 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 83441 | 861 | 7500
500050389 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 83441 | 861 | 7500
500050388 | CLB-MP-HAUL-DT181 -ENGINE-INTEX-AIRFL | Air Filtration System | 83441 | 83441 | 7500
500050387 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-THERM | Thermostats/Regulators | 83441 | 10076 | 7500
500050386 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-BELTS | Fan Belts Engine | 83441 | 83441 | 7500
500050385 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 83441 | 10076 | 7500
500050384 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-COFAN | Fan Cooling System | 83441 | 10076 | 7500
500050383 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-RADTR | Coolant Engine | 83441 | 33433 | 7400
500050382 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-RADTR | Radiator Engine | 83441 | 10076 | 7500
500050381 | CLB-MP-HAUL-DT181 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83441 | 10076 | 7500
500050380 | CLB-MP-HAUL-DT181 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83441 | 83441 | 7500
500050379 | CLB-MP-HAUL-DT181 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83441 | 10076 | 7500
500050378 | CLB-MP-HAUL-DT181 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83441 | 83441 | 7500
500050377 | CLB-MP-HAUL-DT181 -ENGINE-COMPR | Air Compressor | 83441 | 10076 | 7500
500050375 | CLB-MP-HAUL-DT181 -ENGINE | Engine Assembly Caterpillar 3516B | 83441 | 10076 | 7500
500050374 | CLB-MP-HAUL-DT181 | DT181 Lubrication & Mechanical Services | 83441 | 83441 | 7500
500050373 | CLB-MP-HAUL-DT181 | Caterpillar 789D Haul Truck DT181 | 83441 | 83441 | 7500
500160263 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITRH | Air Tank Right | 89376 | 46929 | 7500
500160262 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK-AITLH | Air Tank Left | 89376 | 46929 | 7500
500147246 | CLB-MP-HAUL-DT180 -STRSYS-STACC | Steering Accumulator Rear | 23548 | 23548 | 7500
500147245 | CLB-MP-HAUL-DT180 -STRSYS-STACC | Steering Accumulator Middle | 23548 | 23548 | 7500
500147244 | CLB-MP-HAUL-DT180 -STRSYS-STACC | Steering Accumulator Front | 23548 | 23548 | 7500
500118559 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-AFRME | A Frame Housing | 89560 | 23548 | 7500
500117935 | CLB-MP-HAUL-DT180 -ELCTLV-LIGHT | Lighting Low Voltage | 89560 | 46231 | 7500
500117895 | CLB-MP-HAUL-DT180 -ELCTLV-HARNS | Electrical Harness | 89560 | 46231 | 7500
500117855 | CLB-MP-HAUL-DT180 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 89560 | 46231 | 7500
500117419 | CLB-MP-HAUL-DT180 -ELCTLV-LIGHT-AHSYS | AHS Lights | 89560 | 46231 | 7500
500117299 | CLB-MP-HAUL-DT180 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 89560 | 46231 | 7500
500111221 | CLB-MP-HAUL-DT180 -STRUCT-RAXHO | Rear Axle Housing | 89560 | 47113 | 7500
500110551 | CLB-MP-HAUL-DT180 -GRSYST | Grease Lubrication System | 89560 | 1469 | 7500
500102801 | CLB-MP-HAUL-DT180 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 89560 | 1469 | 7500
500100628 | CLB-MP-HAUL-DT180 -TRNSYS | DT180 Transmission System | 89560 | 47113 | 7500
500081405 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 89560 | 23548 | 7500
500081265 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 89560 | 23548 | 7500
500079438 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN | Suspension Service | 89560 | 11534 | 7500
500078504 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 89560 | 1469 | 7500
500078467 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 89560 | 1469 | 7500
500061429 | CLB-MP-HAUL-DT180 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 89560 | 1469 | 7500
500061399 | CLB-MP-HAUL-DT180 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 89560 | 1469 | 7500
500061145 | CLB-MP-HAUL-DT180 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 89560 | 23548 | 7500
500061144 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-ELECT | Chassis Electrical System | 89560 | 23548 | 7500
500061143 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-ELECT | Cabin Electrical System | 89560 | 89560 | 7500
500061142 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 89560 | 12137 | 7500
500061141 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 89560 | 12137 | 7500
500061140 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 89560 | 12137 | 7500
500061139 | CLB-MP-HAUL-DT180 -STRSYS-STHLF-STRHO | Steering System Hoses | 89560 | 1469 | 7500
500061138 | CLB-MP-HAUL-DT180 -STRSYS-STLTR-STBST | Ball Studs | 89560 | 89560 | 7500
500061137 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 89560 | 1469 | 7500
500061136 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 89560 | 1469 | 7500
500061135 | CLB-MP-HAUL-DT180 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 89560 | 1469 | 7500
500061134 | CLB-MP-HAUL-DT180 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 89560 | 1469 | 7500
500061133 | CLB-MP-HAUL-DT180 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 89560 | 1469 | 7500
500061132 | CLB-MP-HAUL-DT180 -BRKSYS-BRVRL | Brake Relay Valve | 89560 | 1469 | 7500
500061130 | CLB-MP-HAUL-DT180 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 89560 | 1469 | 7500
500061129 | CLB-MP-HAUL-DT180 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 89560 | 1469 | 7500
500060118 | CLB-MP-HAUL-DT180 -STRSYS-STTNK | Tank Steering | 89560 | 68414 | 7500
500053844 | CLB-MP-HAUL-DT180 -BRKSYS-BRVLV | Valve Brake | 89519 | 1469 | 7500
500050372 | CLB-MP-HAUL-DT180 -MANGMT-UMMMC | Mine Monitoring and Control | 89560 | 89560 | 7500
500050371 | CLB-MP-HAUL-DT180 -MANGMT-UMTRN | Power Train Management System | 89560 | 89560 | 7500
500050370 | CLB-MP-HAUL-DT180 -MANGMT-UMENG | Engine Management System | 89560 | 89560 | 7500
500050369 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 89560 | 1469 | 7500
500050368 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 89560 | 1469 | 7500
500050367 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 89560 | 1469 | 7500
500050366 | CLB-MP-HAUL-DT180 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 89560 | 7664 | 7500
500050363 | CLB-MP-HAUL-DT180 -STRUCT-TRAYS | Tray | 89560 | 89560 | 7500
500050362 | CLB-MP-HAUL-DT180 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 89560 | 1469 | 7500
500050361 | CLB-MP-HAUL-DT180 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 89560 | 1469 | 7500
500050360 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-TAGLK | Tag Link | 89560 | 1469 | 7500
500050359 | CLB-MP-HAUL-DT180 -STRUCT-CHASS-AFRME | A Frame Bearing | 89560 | 1469 | 7500
500050358 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-SBELT | Seat Belt | 89560 | 89560 | 7500
500050357 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-SEATS | Operators Seat | 89560 | 23548 | 7500
500050356 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 89560 | 89560 | 7500
500050355 | CLB-MP-HAUL-DT180 -STRUCT-CABIN-AIRCN | Air Conditioning System | 89560 | 17107 | 7500
500050354 | CLB-MP-HAUL-DT180 -STRUCT-CABIN | Operators Cabin | 89560 | 23548 | 7500
500050353 | CLB-MP-HAUL-DT180 -PNEUMC-START | Air Starter | 89560 | 1469 | 7500
500050352 | CLB-MP-HAUL-DT180 -PNEUMC-AIRDR | Air Drier | 89560 | 1469 | 7500
500050351 | CLB-MP-HAUL-DT180 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 89560 | 89560 | 7500
500050350 | CLB-MP-HAUL-DT180 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 89560 | 89560 | 7500
500050349 | CLB-MP-HAUL-DT180 -PNEUMC-PNTNK | No Not Use | 89560 | 47113 | 7500
500050348 | CLB-MP-HAUL-DT180 -GRSYST-ALCON | Auto Lube Controller | 89560 | 89560 | 7500
500050347 | CLB-MP-HAUL-DT180 -GRSYST-ALBPP | Auto Lube Pump | 89560 | 68414 | 7500
500050346 | CLB-MP-HAUL-DT180 -GRSYST-GRTNK | Auto Lube Resevoir | 89560 | 89560 | 7500
500050345 | CLB-MP-HAUL-DT180 -GRSYST-GRINJ | Auto Lube Injectors | 89560 | 89560 | 7500
500050344 | CLB-MP-HAUL-DT180 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 89560 | 1469 | 7500
500050343 | CLB-MP-HAUL-DT180 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 89560 | 15760 | 7500
500050342 | CLB-MP-HAUL-DT180 -HYDSYS-HOVLV | Valve Hoist | 89560 | 23548 | 7500
500050341 | CLB-MP-HAUL-DT180 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 89560 | 89560 | 7500
500050340 | CLB-MP-HAUL-DT180 -HYDSYS-HDTNK | Tank Hydraulic | 89560 | 68414 | 7500
500050339 | CLB-MP-HAUL-DT180 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 89560 | 23548 | 7500
500050338 | CLB-MP-HAUL-DT180 -HYDSYS-HOPMP | Pump Hoist | 89560 | 7705 | 7500
500050337 | CLB-MP-HAUL-DT180 -HYDSYS | Hydraulic System | 89560 | 89560 | 7500
500050336 | CLB-MP-HAUL-DT180 -STRSYS-STCON-STCOL | Steering Column | 89560 | 89560 | 7500
500050335 | CLB-MP-HAUL-DT180 -STRSYS-STCON-STWHL | Steering Wheel | 89560 | 89560 | 7500
500050334 | CLB-MP-HAUL-DT180 -STRSYS-STLTR | Steering Linkages and Tie Rods | 89560 | 23548 | 7500
500050333 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 89560 | 1469 | 7500
500050332 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 89560 | 1469 | 7500
500050331 | CLB-MP-HAUL-DT180 -STRSYS-STACC-SACCF | Accumulator Steering Front | 89560 | 1469 | 7500
500050330 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 89560 | 11534 | 7500
500050329 | CLB-MP-HAUL-DT180 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 89560 | 7664 | 7500
500050328 | CLB-MP-HAUL-DT180 -STRSYS-STVLV | Valve Steering | 89560 | 26227 | 7500
500050327 | CLB-MP-HAUL-DT180 -STRSYS-STHMU | Steering HMU | 89560 | 1469 | 7500
500050326 | CLB-MP-HAUL-DT180 -STRSYS-STPMP | Pump Steering | 89560 | 1469 | 7500
500050325 | CLB-MP-HAUL-DT180 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 89560 | 11534 | 7500
500050324 | CLB-MP-HAUL-DT180 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 89560 | 11534 | 7500
500050323 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 89560 | 1469 | 7500
500050322 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 89560 | 1469 | 7500
500050321 | CLB-MP-HAUL-DT180 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 89560 | 1469 | 7500
500050320 | CLB-MP-HAUL-DT180 -BRKSYS-BACCM | Brake Accumulator | 89560 | 1469 | 7500
500050319 | CLB-MP-HAUL-DT180 -BRKSYS-BROCO | Brake Oil Cooler | 89560 | 68414 | 7500
500050318 | CLB-MP-HAUL-DT180 -BRKSYS-MERTR | Mechanical Retarder | 89560 | 89560 | 7500
500050317 | CLB-MP-HAUL-DT180 -BRKSYS-BRVTR | Valve Brake Treadle | 89560 | 68414 | 7500
500050316 | CLB-MP-HAUL-DT180 -BRKSYS-HYFPP | Pump Brake Control | 89560 | 1469 | 7500
500050315 | CLB-MP-HAUL-DT180 -BRKSYS-PRKPP | Pump Park Brake Release | 89560 | 89560 | 7500
500050314 | CLB-MP-HAUL-DT180 -BRKSYS-BRPMP | Pump Brake | 89560 | 89560 | 7500
500050313 | CLB-MP-HAUL-DT180 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 89560 | 68414 | 7500
500050312 | CLB-MP-HAUL-DT180 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 89560 | 68414 | 7500
500050311 | CLB-MP-HAUL-DT180 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 89560 | 68414 | 7500
500050310 | CLB-MP-HAUL-DT180 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 89560 | 68414 | 7500
500050309 | CLB-MP-HAUL-DT180 -BRKSYS-SRVBK | Service Brake | 89560 | 89560 | 7500
500050308 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 89560 | 89560 | 7500
500050307 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 89560 | 89560 | 7500
500050306 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 89560 | 1469 | 7500
500050305 | CLB-MP-HAUL-DT180 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 89560 | 1469 | 7500
500050304 | CLB-MP-HAUL-DT180 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 89560 | 1469 | 7500
500050303 | CLB-MP-HAUL-DT180 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 89560 | 1469 | 7500
500050302 | CLB-MP-HAUL-DT180 -FDRSYS-DRLAX | Drive Line Axles | 89560 | 89560 | 7500
500050301 | CLB-MP-HAUL-DT180 -FDRSYS-DIFFL | Differential | 89560 | 1469 | 7500
500050300 | CLB-MP-HAUL-DT180 -FDRSYS-DRSHT | Transmission Drive Shaft | 89560 | 11534 | 7500
500050299 | CLB-MP-HAUL-DT180 -TRNSYS-TROLC | Oil Cooler Transmission | 89560 | 16391 | 7500
500050298 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 89560 | 10716 | 7500
500050297 | CLB-MP-HAUL-DT180 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 89560 | 4986 | 7500
500050296 | CLB-MP-HAUL-DT180 -TRNSYS-TRANS | Transmission | 89560 | 16391 | 7500
500050295 | CLB-MP-HAUL-DT180 -TRNSYS-TRQUE | Torque Converter | 89560 | 1469 | 7500
500050294 | CLB-MP-HAUL-DT180 -ELCTLV-CHARG-BATTY | Batteries | 89560 | 89560 | 7500
500050293 | CLB-MP-HAUL-DT180 -ELCTLV-CHARG-ALTER | Alternator 24V | 89560 | 1469 | 7500
500050292 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 89560 | 1469 | 7500
500050291 | CLB-MP-HAUL-DT180 -ENGINE-PMPDR | Pump Drive | 89560 | 1469 | 7500
500050290 | CLB-MP-HAUL-DT180 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 89560 | 1469 | 7500
500050289 | CLB-MP-HAUL-DT180 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 89560 | 1469 | 7500
500050288 | CLB-MP-HAUL-DT180 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 89560 | 1469 | 7500
500050287 | CLB-MP-HAUL-DT180 -ENGINE-FUSYS-FULTK | Fuel Tank | 89560 | 23548 | 7500
500050286 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-EXHST | Exhaust System | 89560 | 58723 | 7500
500050285 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-AFTER | Aftercooler | 89560 | 68414 | 7500
500050284 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 89560 | 1469 | 7500
500050283 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 89560 | 1469 | 7500
500050282 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 89560 | 1469 | 7500
500050281 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 89560 | 1469 | 7500
500050280 | CLB-MP-HAUL-DT180 -ENGINE-INTEX-AIRFL | Air Filtration System | 89560 | 89560 | 7500
500050279 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-THERM | Thermostats/Regulators | 89560 | 1469 | 7500
500050278 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-BELTS | Fan Belts Engine | 89560 | 89560 | 7500
500050277 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 89560 | 1469 | 7500
500050276 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-COFAN | Fan Cooling System | 89560 | 1469 | 7500
500050275 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-RADTR | Coolant Engine | 89560 | 23548 | 7400
500050274 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-RADTR | Radiator Engine | 89560 | 23548 | 7500
500050273 | CLB-MP-HAUL-DT180 -ENGINE-COSYS-WTRPP | Water Pump Engine | 89560 | 1469 | 7500
500050272 | CLB-MP-HAUL-DT180 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 89560 | 68414 | 7500
500050271 | CLB-MP-HAUL-DT180 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 89560 | 1469 | 7500
500050270 | CLB-MP-HAUL-DT180 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 89560 | 68414 | 7500
500050269 | CLB-MP-HAUL-DT180 -ENGINE-COMPR | Air Compressor | 89560 | 1469 | 7500
500050267 | CLB-MP-HAUL-DT180 -ENGINE | Engine Assembly Caterpillar 3516B | 89560 | 1469 | 7500
500050266 | CLB-MP-HAUL-DT180 | DT180 Lubrication & Mechanical Services | 89560 | 89560 | 7500
500050265 | CLB-MP-HAUL-DT180 | Caterpillar 789D Haul Truck DT180 | 89560 | 89560 | 7500
500160261 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITRH | Air Tank Right | 83820 | 11121 | 7500
500160260 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK-AITLH | Air Tank Left | 83820 | 11121 | 7500
500147242 | CLB-MP-HAUL-DT179 -STRSYS-STACC | Steering Accumulator Rear | 33681 | 33681 | 7500
500147241 | CLB-MP-HAUL-DT179 -STRSYS-STACC | Steering Accumulator Middle | 33681 | 33681 | 7500
500147240 | CLB-MP-HAUL-DT179 -STRSYS-STACC | Steering Accumulator Front | 33681 | 33681 | 7500
500118558 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-AFRME | A Frame Housing | 84079 | 36609 | 7500
500117934 | CLB-MP-HAUL-DT179 -ELCTLV-LIGHT | Lighting Low Voltage | 84079 | 51973 | 7500
500117894 | CLB-MP-HAUL-DT179 -ELCTLV-HARNS | Electrical Harness | 84079 | 51973 | 7500
500117854 | CLB-MP-HAUL-DT179 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 84079 | 51973 | 7500
500117418 | CLB-MP-HAUL-DT179 -ELCTLV-LIGHT-AHSYS | AHS Lights | 84079 | 51973 | 7500
500117298 | CLB-MP-HAUL-DT179 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 84079 | 51973 | 7500
500111220 | CLB-MP-HAUL-DT179 -STRUCT-RAXHO | Rear Axle Housing | 84079 | 13410 | 7500
500110550 | CLB-MP-HAUL-DT179 -GRSYST | Grease Lubrication System | 84079 | 12039 | 7500
500102800 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 84079 | 11380 | 7500
500100627 | CLB-MP-HAUL-DT179 -TRNSYS | DT179 Transmission System | 84079 | 47130 | 7500
500081404 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 84079 | 24410 | 7500
500081264 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 84079 | 24410 | 7500
500079437 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN | Suspension Service | 84079 | 11363 | 7500
500078503 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 84079 | 11380 | 7500
500078466 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 84079 | 11380 | 7500
500061428 | CLB-MP-HAUL-DT179 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 84079 | 11380 | 7500
500061398 | CLB-MP-HAUL-DT179 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 84079 | 11380 | 7500
500061128 | CLB-MP-HAUL-DT179 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 84079 | 11380 | 7500
500061127 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-ELECT | Chassis Electrical System | 84079 | 33681 | 7500
500061126 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-ELECT | Cabin Electrical System | 84079 | 84079 | 7500
500061125 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 84079 | 11380 | 7500
500061124 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 84079 | 11380 | 7500
500061123 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 84079 | 11380 | 7500
500061122 | CLB-MP-HAUL-DT179 -STRSYS-STHLF-STRHO | Steering System Hoses | 84079 | 11380 | 7500
500061121 | CLB-MP-HAUL-DT179 -STRSYS-STLTR-STBST | Ball Studs | 84079 | 84079 | 7500
500061120 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 84079 | 11380 | 7500
500061119 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 84079 | 11380 | 7500
500061118 | CLB-MP-HAUL-DT179 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 84079 | 11380 | 7500
500061117 | CLB-MP-HAUL-DT179 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 84079 | 11380 | 7500
500061116 | CLB-MP-HAUL-DT179 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 84079 | 11380 | 7500
500061115 | CLB-MP-HAUL-DT179 -BRKSYS-BRVRL | Brake Relay Valve | 84079 | 11380 | 7500
500061113 | CLB-MP-HAUL-DT179 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 84079 | 11380 | 7500
500061112 | CLB-MP-HAUL-DT179 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 84079 | 11380 | 7500
500060117 | CLB-MP-HAUL-DT179 -STRSYS-STTNK | Tank Steering | 84079 | 84079 | 7500
500053843 | CLB-MP-HAUL-DT179 -BRKSYS-BRVLV | Valve Brake | 84079 | 11380 | 7500
500050264 | CLB-MP-HAUL-DT179 -MANGMT-UMMMC | Mine Monitoring and Control | 84079 | 84079 | 7500
500050263 | CLB-MP-HAUL-DT179 -MANGMT-UMTRN | Power Train Management System | 84079 | 84079 | 7500
500050262 | CLB-MP-HAUL-DT179 -MANGMT-UMENG | Engine Management System | 84079 | 84079 | 7500
500050261 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 84079 | 11380 | 7500
500050260 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 84079 | 11380 | 7500
500050259 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 84079 | 11380 | 7500
500050258 | CLB-MP-HAUL-DT179 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 84079 | 11380 | 7500
500050255 | CLB-MP-HAUL-DT179 -STRUCT-TRAYS | Tray | 84079 | 33681 | 7500
500050254 | CLB-MP-HAUL-DT179 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 84079 | 11380 | 7500
500050253 | CLB-MP-HAUL-DT179 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 84079 | 20488 | 7500
500050252 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-TAGLK | Tag Link | 84079 | 13410 | 7500
500050251 | CLB-MP-HAUL-DT179 -STRUCT-CHASS-AFRME | A Frame Bearing | 84079 | 13410 | 7500
500050250 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-SBELT | Seat Belt | 84079 | 84079 | 7500
500050249 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-SEATS | Operators Seat | 84079 | 11380 | 7500
500050248 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 84079 | 84079 | 7500
500050247 | CLB-MP-HAUL-DT179 -STRUCT-CABIN-AIRCN | Air Conditioning System | 84079 | 11380 | 7500
500050246 | CLB-MP-HAUL-DT179 -STRUCT-CABIN | Operators Cabin | 84079 | 11380 | 7500
500050245 | CLB-MP-HAUL-DT179 -PNEUMC-START | Air Starter | 84079 | 11380 | 7500
500050244 | CLB-MP-HAUL-DT179 -PNEUMC-AIRDR | Air Drier | 84079 | 11380 | 7500
500050243 | CLB-MP-HAUL-DT179 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 84079 | 84079 | 7500
500050242 | CLB-MP-HAUL-DT179 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 84079 | 84079 | 7500
500050241 | CLB-MP-HAUL-DT179 -PNEUMC-PNTNK | No Not Use | 84079 | 11380 | 7500
500050240 | CLB-MP-HAUL-DT179 -GRSYST-ALCON | Auto Lube Controller | 84079 | 84079 | 7500
500050239 | CLB-MP-HAUL-DT179 -GRSYST-ALBPP | Auto Lube Pump | 84079 | 43903 | 7500
500050238 | CLB-MP-HAUL-DT179 -GRSYST-GRTNK | Auto Lube Resevoir | 84079 | 84079 | 7500
500050237 | CLB-MP-HAUL-DT179 -GRSYST-GRINJ | Auto Lube Injectors | 84079 | 84079 | 7500
500050236 | CLB-MP-HAUL-DT179 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 84079 | 16016 | 7500
500050235 | CLB-MP-HAUL-DT179 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 84079 | 11380 | 7500
500050234 | CLB-MP-HAUL-DT179 -HYDSYS-HOVLV | Valve Hoist | 84079 | 33681 | 7500
500050233 | CLB-MP-HAUL-DT179 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 84079 | 84079 | 7500
500050232 | CLB-MP-HAUL-DT179 -HYDSYS-HDTNK | Tank Hydraulic | 84079 | 84079 | 7500
500050231 | CLB-MP-HAUL-DT179 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 84079 | 11380 | 7500
500050230 | CLB-MP-HAUL-DT179 -HYDSYS-HOPMP | Pump Hoist | 84079 | 15349 | 7500
500050229 | CLB-MP-HAUL-DT179 -HYDSYS | Hydraulic System | 84079 | 84079 | 7500
500050228 | CLB-MP-HAUL-DT179 -STRSYS-STCON-STCOL | Steering Column | 84079 | 84079 | 7500
500050227 | CLB-MP-HAUL-DT179 -STRSYS-STCON-STWHL | Steering Wheel | 84079 | 84079 | 7500
500050226 | CLB-MP-HAUL-DT179 -STRSYS-STLTR | Steering Linkages and Tie Rods | 84079 | 11380 | 7500
500050225 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 84079 | 11380 | 7500
500050224 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 84079 | 11380 | 7500
500050223 | CLB-MP-HAUL-DT179 -STRSYS-STACC-SACCF | Accumulator Steering Front | 84079 | 11380 | 7500
500050222 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 84079 | 5709 | 7500
500050221 | CLB-MP-HAUL-DT179 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 84079 | 16016 | 7500
500050220 | CLB-MP-HAUL-DT179 -STRSYS-STVLV | Valve Steering | 84079 | 11380 | 7500
500050219 | CLB-MP-HAUL-DT179 -STRSYS-STHMU | Steering HMU | 84079 | 11380 | 7500
500050218 | CLB-MP-HAUL-DT179 -STRSYS-STPMP | Pump Steering | 84079 | 11380 | 7500
500050217 | CLB-MP-HAUL-DT179 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 84079 | 11380 | 7500
500050216 | CLB-MP-HAUL-DT179 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 84079 | 11380 | 7500
500050215 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 84079 | 11380 | 7500
500050214 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 84079 | 11380 | 7500
500050213 | CLB-MP-HAUL-DT179 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 84079 | 11380 | 7500
500050212 | CLB-MP-HAUL-DT179 -BRKSYS-BACCM | Brake Accumulator | 84079 | 11380 | 7500
500050211 | CLB-MP-HAUL-DT179 -BRKSYS-BROCO | Brake Oil Cooler | 84079 | 84079 | 7500
500050210 | CLB-MP-HAUL-DT179 -BRKSYS-MERTR | Mechanical Retarder | 84079 | 84079 | 7500
500050209 | CLB-MP-HAUL-DT179 -BRKSYS-BRVTR | Valve Brake Treadle | 84079 | 84079 | 7500
500050208 | CLB-MP-HAUL-DT179 -BRKSYS-HYFPP | Pump Brake Control | 84079 | 11380 | 7500
500050207 | CLB-MP-HAUL-DT179 -BRKSYS-PRKPP | Pump Park Brake Release | 84079 | 84079 | 7500
500050206 | CLB-MP-HAUL-DT179 -BRKSYS-BRPMP | Pump Brake | 84079 | 39212 | 7500
500050205 | CLB-MP-HAUL-DT179 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 84079 | 84079 | 7500
500050204 | CLB-MP-HAUL-DT179 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 84079 | 84079 | 7500
500050203 | CLB-MP-HAUL-DT179 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 84079 | 84079 | 7500
500050202 | CLB-MP-HAUL-DT179 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 84079 | 84079 | 7500
500050201 | CLB-MP-HAUL-DT179 -BRKSYS-SRVBK | Service Brake | 84079 | 84079 | 7500
500050200 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 84079 | 84079 | 7500
500050199 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 84079 | 84079 | 7500
500050198 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 84079 | 11380 | 7500
500050197 | CLB-MP-HAUL-DT179 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 84079 | 11380 | 7500
500050196 | CLB-MP-HAUL-DT179 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 84079 | 11380 | 7500
500050195 | CLB-MP-HAUL-DT179 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 84079 | 18003 | 7500
500050194 | CLB-MP-HAUL-DT179 -FDRSYS-DRLAX | Drive Line Axles | 84079 | 84079 | 7500
500050193 | CLB-MP-HAUL-DT179 -FDRSYS-DIFFL | Differential | 84079 | 13410 | 7500
500050192 | CLB-MP-HAUL-DT179 -FDRSYS-DRSHT | Transmission Drive Shaft | 84079 | 11380 | 7500
500050191 | CLB-MP-HAUL-DT179 -TRNSYS-TROLC | Oil Cooler Transmission | 84079 | 6265 | 7500
500050190 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 84079 | 11380 | 7500
500050189 | CLB-MP-HAUL-DT179 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 84079 | 6265 | 7500
500050188 | CLB-MP-HAUL-DT179 -TRNSYS-TRANS | Transmission | 84079 | 6265 | 7500
500050187 | CLB-MP-HAUL-DT179 -TRNSYS-TRQUE | Torque Converter | 84079 | 11380 | 7500
500050186 | CLB-MP-HAUL-DT179 -ELCTLV-CHARG-BATTY | Batteries | 84079 | 84079 | 7500
500050185 | CLB-MP-HAUL-DT179 -ELCTLV-CHARG-ALTER | Alternator 24V | 84079 | 11380 | 7500
500050184 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 84079 | 16664 | 7500
500050183 | CLB-MP-HAUL-DT179 -ENGINE-PMPDR | Pump Drive | 84079 | 16390 | 7500
500050182 | CLB-MP-HAUL-DT179 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 84079 | 11380 | 7500
500050181 | CLB-MP-HAUL-DT179 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 84079 | 11380 | 7500
500050180 | CLB-MP-HAUL-DT179 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 84079 | 11380 | 7500
500050179 | CLB-MP-HAUL-DT179 -ENGINE-FUSYS-FULTK | Fuel Tank | 84079 | 11380 | 7500
500050178 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-EXHST | Exhaust System | 84079 | 84079 | 7500
500050177 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-AFTER | Aftercooler | 84079 | 55189 | 7500
500050176 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 84079 | 9878 | 7500
500050175 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 84079 | 9878 | 7500
500050174 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 84079 | 4000 | 7500
500050173 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 84079 | 4000 | 7500
500050172 | CLB-MP-HAUL-DT179 -ENGINE-INTEX-AIRFL | Air Filtration System | 84079 | 84079 | 7500
500050171 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-THERM | Thermostats/Regulators | 84079 | 11380 | 7500
500050170 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-BELTS | Fan Belts Engine | 84079 | 84079 | 7500
500050169 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 84079 | 11380 | 7500
500050168 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-COFAN | Fan Cooling System | 84079 | 11380 | 7500
500050167 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-RADTR | Coolant Engine | 84079 | 33681 | 7400
500050166 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-RADTR | Radiator Engine | 84079 | 11380 | 7500
500050165 | CLB-MP-HAUL-DT179 -ENGINE-COSYS-WTRPP | Water Pump Engine | 84079 | 11380 | 7500
500050164 | CLB-MP-HAUL-DT179 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 84079 | 55189 | 7500
500050163 | CLB-MP-HAUL-DT179 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 84079 | 11380 | 7500
500050162 | CLB-MP-HAUL-DT179 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 84079 | 55189 | 7500
500050161 | CLB-MP-HAUL-DT179 -ENGINE-COMPR | Air Compressor | 84079 | 11380 | 7500
500050159 | CLB-MP-HAUL-DT179 -ENGINE | Engine Assembly Caterpillar 3516B | 84079 | 11380 | 7500
500050158 | CLB-MP-HAUL-DT179 | DT179 Lubrication & Mechanical Services | 84079 | 74262 | 7500
500050157 | CLB-MP-HAUL-DT179 | Caterpillar 789D Haul Truck DT179 | 84079 | 84079 | 7500
500160259 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITRH | Air Tank Right | 81378 | 16017 | 7500
500160258 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK-AITLH | Air Tank Left | 81378 | 16017 | 7500
500147238 | CLB-MP-HAUL-DT178 -STRSYS-STACC | Steering Accumulator Rear | 28262 | 28262 | 7500
500147237 | CLB-MP-HAUL-DT178 -STRSYS-STACC | Steering Accumulator Middle | 28262 | 28262 | 7500
500147236 | CLB-MP-HAUL-DT178 -STRSYS-STACC | Steering Accumulator Front | 28262 | 28262 | 7500
500118557 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-AFRME | A Frame Housing | 81600 | 28262 | 7500
500117933 | CLB-MP-HAUL-DT178 -ELCTLV-LIGHT | Lighting Low Voltage | 81600 | 49274 | 7500
500117893 | CLB-MP-HAUL-DT178 -ELCTLV-HARNS | Electrical Harness | 81600 | 49274 | 7500
500117853 | CLB-MP-HAUL-DT178 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 81600 | 49274 | 7500
500117417 | CLB-MP-HAUL-DT178 -ELCTLV-LIGHT-AHSYS | AHS Lights | 81600 | 49274 | 7500
500117297 | CLB-MP-HAUL-DT178 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 81600 | 49274 | 7500
500111219 | CLB-MP-HAUL-DT178 -STRUCT-RAXHO | Rear Axle Housing | 81600 | 43534 | 7500
500110549 | CLB-MP-HAUL-DT178 -GRSYST | Grease Lubrication System | 81600 | 38107 | 7500
500102799 | CLB-MP-HAUL-DT178 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 81600 | 17038 | 7500
500100626 | CLB-MP-HAUL-DT178 -TRNSYS | DT178 Transmission System | 81600 | 49321 | 7500
500081403 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 81600 | 28262 | 7500
500081263 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 81600 | 28262 | 7500
500079436 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN | Suspension Service | 81600 | 28262 | 7500
500078502 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 81600 | 28262 | 7500
500078465 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 81600 | 28262 | 7500
500061427 | CLB-MP-HAUL-DT178 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 81600 | 28262 | 7500
500061397 | CLB-MP-HAUL-DT178 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 81600 | 28262 | 7500
500061111 | CLB-MP-HAUL-DT178 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 81600 | 28262 | 7500
500061110 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-ELECT | Chassis Electrical System | 81600 | 39328 | 7500
500061109 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-ELECT | Cabin Electrical System | 81600 | 81600 | 7500
500061108 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 81600 | 17038 | 7500
500061107 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 81600 | 17038 | 7500
500061106 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 81600 | 17038 | 7500
500061105 | CLB-MP-HAUL-DT178 -STRSYS-STHLF-STRHO | Steering System Hoses | 81600 | 28262 | 7500
500061104 | CLB-MP-HAUL-DT178 -STRSYS-STLTR-STBST | Ball Studs | 81600 | 81600 | 7500
500061103 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 81600 | 28262 | 7500
500061102 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 81600 | 28262 | 7500
500061101 | CLB-MP-HAUL-DT178 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 81600 | 28262 | 7500
500061100 | CLB-MP-HAUL-DT178 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 81600 | 17038 | 7500
500061099 | CLB-MP-HAUL-DT178 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 81600 | 4753 | 7500
500061098 | CLB-MP-HAUL-DT178 -BRKSYS-BRVRL | Brake Relay Valve | 81600 | 5737 | 7500
500061096 | CLB-MP-HAUL-DT178 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 81600 | 28262 | 7500
500061095 | CLB-MP-HAUL-DT178 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 81600 | 28262 | 7500
500060116 | CLB-MP-HAUL-DT178 -STRSYS-STTNK | Tank Steering | 81600 | 81600 | 7500
500053842 | CLB-MP-HAUL-DT178 -BRKSYS-BRVLV | Valve Brake | 81600 | 5737 | 7500
500050156 | CLB-MP-HAUL-DT178 -MANGMT-UMMMC | Mine Monitoring and Control | 81600 | 81600 | 7500
500050155 | CLB-MP-HAUL-DT178 -MANGMT-UMTRN | Power Train Management System | 81600 | 81600 | 7500
500050154 | CLB-MP-HAUL-DT178 -MANGMT-UMENG | Engine Management System | 81600 | 81600 | 7500
500050153 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 81600 | 12157 | 7500
500050152 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 81600 | 5739 | 7500
500050151 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 81600 | 5579 | 7500
500050150 | CLB-MP-HAUL-DT178 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 81600 | 10332 | 7500
500050147 | CLB-MP-HAUL-DT178 -STRUCT-TRAYS | Tray | 81600 | 23973 | 7500
500050146 | CLB-MP-HAUL-DT178 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 81600 | 5579 | 7500
500050145 | CLB-MP-HAUL-DT178 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 81600 | 5579 | 7500
500050144 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-TAGLK | Tag Link | 81600 | 5739 | 7500
500050143 | CLB-MP-HAUL-DT178 -STRUCT-CHASS-AFRME | A Frame Bearing | 81600 | 28262 | 7500
500050142 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-SBELT | Seat Belt | 81600 | 81600 | 7500
500050141 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-SEATS | Operators Seat | 81600 | 28262 | 7500
500050140 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81600 | 81600 | 7500
500050139 | CLB-MP-HAUL-DT178 -STRUCT-CABIN-AIRCN | Air Conditioning System | 81600 | 17038 | 7500
500050138 | CLB-MP-HAUL-DT178 -STRUCT-CABIN | Operators Cabin | 81600 | 39328 | 7500
500050137 | CLB-MP-HAUL-DT178 -PNEUMC-START | Air Starter | 81600 | 5579 | 7500
500050136 | CLB-MP-HAUL-DT178 -PNEUMC-AIRDR | Air Drier | 81600 | 28262 | 7500
500050135 | CLB-MP-HAUL-DT178 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 81600 | 81600 | 7500
500050134 | CLB-MP-HAUL-DT178 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 81600 | 81600 | 7500
500050133 | CLB-MP-HAUL-DT178 -PNEUMC-PNTNK | No Not Use | 81600 | 16239 | 7500
500050132 | CLB-MP-HAUL-DT178 -GRSYST-ALCON | Auto Lube Controller | 81600 | 81600 | 7500
500050131 | CLB-MP-HAUL-DT178 -GRSYST-ALBPP | Auto Lube Pump | 81600 | 81600 | 7500
500050130 | CLB-MP-HAUL-DT178 -GRSYST-GRTNK | Auto Lube Resevoir | 81600 | 81600 | 7500
500050129 | CLB-MP-HAUL-DT178 -GRSYST-GRINJ | Auto Lube Injectors | 81600 | 81600 | 7500
500050128 | CLB-MP-HAUL-DT178 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 81600 | 9538 | 7500
500050127 | CLB-MP-HAUL-DT178 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 81600 | 173 | 7500
500050126 | CLB-MP-HAUL-DT178 -HYDSYS-HOVLV | Valve Hoist | 81600 | 28262 | 7500
500050125 | CLB-MP-HAUL-DT178 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81600 | 81600 | 7500
500050124 | CLB-MP-HAUL-DT178 -HYDSYS-HDTNK | Tank Hydraulic | 81600 | 81600 | 7500
500050123 | CLB-MP-HAUL-DT178 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 81600 | 27672 | 7500
500050122 | CLB-MP-HAUL-DT178 -HYDSYS-HOPMP | Pump Hoist | 81600 | 1294 | 7500
500050121 | CLB-MP-HAUL-DT178 -HYDSYS | Hydraulic System | 81600 | 81600 | 7500
500050120 | CLB-MP-HAUL-DT178 -STRSYS-STCON-STCOL | Steering Column | 81600 | 81600 | 7500
500050119 | CLB-MP-HAUL-DT178 -STRSYS-STCON-STWHL | Steering Wheel | 81600 | 81600 | 7500
500050118 | CLB-MP-HAUL-DT178 -STRSYS-STLTR | Steering Linkages and Tie Rods | 81600 | 12900 | 7500
500050117 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 81600 | 28262 | 7500
500050116 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 81600 | 28262 | 7500
500050115 | CLB-MP-HAUL-DT178 -STRSYS-STACC-SACCF | Accumulator Steering Front | 81600 | 28262 | 7500
500050114 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 81600 | 18127 | 7500
500050113 | CLB-MP-HAUL-DT178 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 81600 | 8739 | 7500
500050112 | CLB-MP-HAUL-DT178 -STRSYS-STVLV | Valve Steering | 81600 | 5579 | 7500
500050111 | CLB-MP-HAUL-DT178 -STRSYS-STHMU | Steering HMU | 81600 | 12786 | 7500
500050110 | CLB-MP-HAUL-DT178 -STRSYS-STPMP | Pump Steering | 81600 | 12786 | 7500
500050109 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 81600 | 17038 | 7500
500050108 | CLB-MP-HAUL-DT178 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 81600 | 17038 | 7500
500050107 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 81600 | 5737 | 7500
500050106 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 81600 | 17037 | 7500
500050105 | CLB-MP-HAUL-DT178 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 81600 | 5737 | 7500
500050104 | CLB-MP-HAUL-DT178 -BRKSYS-BACCM | Brake Accumulator | 81600 | 5737 | 7500
500050103 | CLB-MP-HAUL-DT178 -BRKSYS-BROCO | Brake Oil Cooler | 81600 | 81600 | 7500
500050102 | CLB-MP-HAUL-DT178 -BRKSYS-MERTR | Mechanical Retarder | 81600 | 81600 | 7500
500050101 | CLB-MP-HAUL-DT178 -BRKSYS-BRVTR | Valve Brake Treadle | 81600 | 81600 | 7500
500050100 | CLB-MP-HAUL-DT178 -BRKSYS-HYFPP | Pump Brake Control | 81600 | 17038 | 7500
500050099 | CLB-MP-HAUL-DT178 -BRKSYS-PRKPP | Pump Park Brake Release | 81600 | 81600 | 7500
500050098 | CLB-MP-HAUL-DT178 -BRKSYS-BRPMP | Pump Brake | 81600 | 1294 | 7500
500050097 | CLB-MP-HAUL-DT178 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 81600 | 81600 | 7500
500050096 | CLB-MP-HAUL-DT178 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 81600 | 81600 | 7500
500050095 | CLB-MP-HAUL-DT178 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 81600 | 56543 | 7500
500050094 | CLB-MP-HAUL-DT178 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 81600 | 81600 | 7500
500050093 | CLB-MP-HAUL-DT178 -BRKSYS-SRVBK | Service Brake | 81600 | 81600 | 7500
500050092 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 81600 | 81600 | 7500
500050091 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 81600 | 81600 | 7500
500050090 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 81600 | 5737 | 7500
500050089 | CLB-MP-HAUL-DT178 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 81600 | 17038 | 7500
500050088 | CLB-MP-HAUL-DT178 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 81600 | 8737 | 7500
500050087 | CLB-MP-HAUL-DT178 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 81600 | 5739 | 7500
500050086 | CLB-MP-HAUL-DT178 -FDRSYS-DRLAX | Drive Line Axles | 81600 | 81600 | 7500
500050085 | CLB-MP-HAUL-DT178 -FDRSYS-DIFFL | Differential | 81600 | 20689 | 7500
500050084 | CLB-MP-HAUL-DT178 -FDRSYS-DRSHT | Transmission Drive Shaft | 81600 | 5737 | 7500
500050083 | CLB-MP-HAUL-DT178 -TRNSYS-TROLC | Oil Cooler Transmission | 81600 | 5579 | 7500
500050082 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 81600 | 5739 | 7500
500050081 | CLB-MP-HAUL-DT178 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 81600 | 17038 | 7500
500050080 | CLB-MP-HAUL-DT178 -TRNSYS-TRANS | Transmission | 81600 | 5739 | 7500
500050079 | CLB-MP-HAUL-DT178 -TRNSYS-TRQUE | Torque Converter | 81600 | 17038 | 7500
500050078 | CLB-MP-HAUL-DT178 -ELCTLV-CHARG-BATTY | Batteries | 81600 | 81600 | 7500
500050077 | CLB-MP-HAUL-DT178 -ELCTLV-CHARG-ALTER | Alternator 24V | 81600 | 5579 | 7500
500050076 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 81600 | 17038 | 7500
500050075 | CLB-MP-HAUL-DT178 -ENGINE-PMPDR | Pump Drive | 81600 | 28262 | 7500
500050074 | CLB-MP-HAUL-DT178 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81600 | 17038 | 7500
500050073 | CLB-MP-HAUL-DT178 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81600 | 5579 | 7500
500050072 | CLB-MP-HAUL-DT178 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 81600 | 5579 | 7500
500050071 | CLB-MP-HAUL-DT178 -ENGINE-FUSYS-FULTK | Fuel Tank | 81600 | 53132 | 7500
500050070 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-EXHST | Exhaust System | 81600 | 81600 | 7500
500050069 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-AFTER | Aftercooler | 81600 | 63191 | 7500
500050068 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 81600 | 5579 | 7500
500050067 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 81600 | 5579 | 7500
500050066 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 81600 | 5579 | 7500
500050065 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 81600 | 5579 | 7500
500050064 | CLB-MP-HAUL-DT178 -ENGINE-INTEX-AIRFL | Air Filtration System | 81600 | 81600 | 7500
500050063 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-THERM | Thermostats/Regulators | 81600 | 17038 | 7500
500050062 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-BELTS | Fan Belts Engine | 81600 | 81600 | 7500
500050061 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 81600 | 5579 | 7500
500050060 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-COFAN | Fan Cooling System | 81600 | 17038 | 7500
500050059 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-RADTR | Coolant Engine | 81600 | 39328 | 7400
500050058 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-RADTR | Radiator Engine | 81600 | 17038 | 7500
500050057 | CLB-MP-HAUL-DT178 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81600 | 5579 | 7500
500050056 | CLB-MP-HAUL-DT178 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81600 | 63191 | 7500
500050055 | CLB-MP-HAUL-DT178 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81600 | 17038 | 7500
500050054 | CLB-MP-HAUL-DT178 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81600 | 63191 | 7500
500050053 | CLB-MP-HAUL-DT178 -ENGINE-COMPR | Air Compressor | 81600 | 5579 | 7500
500050051 | CLB-MP-HAUL-DT178 -ENGINE | Engine Assembly Caterpillar 3516B | 81600 | 17038 | 7500
500050050 | CLB-MP-HAUL-DT178 | DT178 Lubrication & Mechanical Services | 81442 | 81442 | 7500
500050049 | CLB-MP-HAUL-DT178 | Caterpillar 789D Haul Truck DT178 | 81600 | 81600 | 7500
500160257 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITRH | Air Tank Right | 81529 | 8461 | 7500
500160256 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK-AITLH | Air Tank Left | 81529 | 8461 | 7500
500147234 | CLB-MP-HAUL-DT177 -STRSYS-STACC | Steering Accumulator Rear | 31511 | 31511 | 7500
500147233 | CLB-MP-HAUL-DT177 -STRSYS-STACC | Steering Accumulator Middle | 31511 | 31511 | 7500
500147232 | CLB-MP-HAUL-DT177 -STRSYS-STACC | Steering Accumulator Front | 31511 | 31511 | 7500
500118556 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-AFRME | A Frame Housing | 81791 | 8723 | 7500
500117932 | CLB-MP-HAUL-DT177 -ELCTLV-LIGHT | Lighting Low Voltage | 81791 | 50728 | 7500
500117892 | CLB-MP-HAUL-DT177 -ELCTLV-HARNS | Electrical Harness | 81791 | 50728 | 7500
500117852 | CLB-MP-HAUL-DT177 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 81791 | 50728 | 7500
500117416 | CLB-MP-HAUL-DT177 -ELCTLV-LIGHT-AHSYS | AHS Lights | 81791 | 50728 | 7500
500117296 | CLB-MP-HAUL-DT177 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 81791 | 50728 | 7500
500111218 | CLB-MP-HAUL-DT177 -STRUCT-RAXHO | Rear Axle Housing | 81791 | 28488 | 7500
500110548 | CLB-MP-HAUL-DT177 -GRSYST | Grease Lubrication System | 81791 | 8930 | 7500
500102798 | CLB-MP-HAUL-DT177 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 81791 | 8723 | 7500
500100625 | CLB-MP-HAUL-DT177 -TRNSYS | DT177 Transmission System | 81791 | 51846 | 7500
500081402 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 81791 | 24250 | 7500
500081262 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 81791 | 24250 | 7500
500079435 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN | Suspension Service | 81791 | 14442 | 7500
500078501 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 81791 | 8723 | 7500
500078464 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 81791 | 8723 | 7500
500061426 | CLB-MP-HAUL-DT177 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 81791 | 8723 | 7500
500061396 | CLB-MP-HAUL-DT177 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 81791 | 8723 | 7500
500061094 | CLB-MP-HAUL-DT177 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 81791 | 8723 | 7500
500061093 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-ELECT | Chassis Electrical System | 81791 | 31511 | 7500
500061092 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-ELECT | Cabin Electrical System | 81791 | 81791 | 7500
500061091 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 81791 | 8723 | 7500
500061090 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 81791 | 8723 | 7500
500061089 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 81791 | 8723 | 7500
500061088 | CLB-MP-HAUL-DT177 -STRSYS-STHLF-STRHO | Steering System Hoses | 81791 | 8723 | 7500
500061087 | CLB-MP-HAUL-DT177 -STRSYS-STLTR-STBST | Ball Studs | 81791 | 81791 | 7500
500061086 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 81791 | 8723 | 7500
500061085 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 81791 | 8723 | 7500
500061084 | CLB-MP-HAUL-DT177 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 81791 | 8723 | 7500
500061083 | CLB-MP-HAUL-DT177 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 81791 | 8723 | 7500
500061082 | CLB-MP-HAUL-DT177 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 81791 | 8723 | 7500
500061081 | CLB-MP-HAUL-DT177 -BRKSYS-BRVRL | Brake Relay Valve | 81791 | 8723 | 7500
500061079 | CLB-MP-HAUL-DT177 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 81791 | 8723 | 7500
500061078 | CLB-MP-HAUL-DT177 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 81791 | 8723 | 7500
500060115 | CLB-MP-HAUL-DT177 -STRSYS-STTNK | Tank Steering | 81791 | 81791 | 7500
500053841 | CLB-MP-HAUL-DT177 -BRKSYS-BRVLV | Valve Brake | 81791 | 8723 | 7500
500050048 | CLB-MP-HAUL-DT177 -MANGMT-UMMMC | Mine Monitoring and Control | 81791 | 81791 | 7500
500050047 | CLB-MP-HAUL-DT177 -MANGMT-UMTRN | Power Train Management System | 81791 | 81791 | 7500
500050046 | CLB-MP-HAUL-DT177 -MANGMT-UMENG | Engine Management System | 81791 | 81791 | 7500
500050045 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 81791 | 7294 | 7500
500050044 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 81791 | 8723 | 7500
500050043 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 81791 | 8723 | 7500
500050042 | CLB-MP-HAUL-DT177 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 81791 | 8723 | 7500
500050039 | CLB-MP-HAUL-DT177 -STRUCT-TRAYS | Tray | 81791 | 19848 | 7500
500050038 | CLB-MP-HAUL-DT177 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 81791 | 8723 | 7500
500050037 | CLB-MP-HAUL-DT177 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 81791 | 8723 | 7500
500050036 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-TAGLK | Tag Link | 81791 | 8723 | 7500
500050035 | CLB-MP-HAUL-DT177 -STRUCT-CHASS-AFRME | A Frame Bearing | 81791 | 8723 | 7500
500050034 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-SBELT | Seat Belt | 81791 | 81791 | 7500
500050033 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-SEATS | Operators Seat | 81791 | 13700 | 7500
500050032 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81791 | 81791 | 7500
500050031 | CLB-MP-HAUL-DT177 -STRUCT-CABIN-AIRCN | Air Conditioning System | 81791 | 8723 | 7500
500050030 | CLB-MP-HAUL-DT177 -STRUCT-CABIN | Operators Cabin | 81791 | 8723 | 7500
500050029 | CLB-MP-HAUL-DT177 -PNEUMC-START | Air Starter | 81791 | 8723 | 7500
500050028 | CLB-MP-HAUL-DT177 -PNEUMC-AIRDR | Air Drier | 81791 | 48217 | 7500
500050027 | CLB-MP-HAUL-DT177 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 81791 | 81791 | 7500
500050026 | CLB-MP-HAUL-DT177 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 81791 | 81791 | 7500
500050025 | CLB-MP-HAUL-DT177 -PNEUMC-PNTNK | No Not Use | 81791 | 8723 | 7500
500050024 | CLB-MP-HAUL-DT177 -GRSYST-ALCON | Auto Lube Controller | 81791 | 81791 | 7500
500050023 | CLB-MP-HAUL-DT177 -GRSYST-ALBPP | Auto Lube Pump | 81791 | 81791 | 7500
500050022 | CLB-MP-HAUL-DT177 -GRSYST-GRTNK | Auto Lube Resevoir | 81791 | 81791 | 7500
500050021 | CLB-MP-HAUL-DT177 -GRSYST-GRINJ | Auto Lube Injectors | 81791 | 81791 | 7500
500050020 | CLB-MP-HAUL-DT177 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 81791 | 8723 | 7500
500050019 | CLB-MP-HAUL-DT177 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 81791 | 8723 | 7500
500050018 | CLB-MP-HAUL-DT177 -HYDSYS-HOVLV | Valve Hoist | 81791 | 8723 | 7500
500050017 | CLB-MP-HAUL-DT177 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81791 | 81791 | 7500
500050016 | CLB-MP-HAUL-DT177 -HYDSYS-HDTNK | Tank Hydraulic | 81791 | 81791 | 7500
500050015 | CLB-MP-HAUL-DT177 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 81791 | 8723 | 7500
500050014 | CLB-MP-HAUL-DT177 -HYDSYS-HOPMP | Pump Hoist | 81791 | 8723 | 7500
500050013 | CLB-MP-HAUL-DT177 -HYDSYS | Hydraulic System | 81791 | 81791 | 7500
500050012 | CLB-MP-HAUL-DT177 -STRSYS-STCON-STCOL | Steering Column | 81791 | 81791 | 7500
500050011 | CLB-MP-HAUL-DT177 -STRSYS-STCON-STWHL | Steering Wheel | 81791 | 81791 | 7500
500050010 | CLB-MP-HAUL-DT177 -STRSYS-STLTR | Steering Linkages and Tie Rods | 81791 | 15833 | 7500
500050009 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 81791 | 8723 | 7500
500050008 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 81791 | 8723 | 7500
500050007 | CLB-MP-HAUL-DT177 -STRSYS-STACC-SACCF | Accumulator Steering Front | 81791 | 8723 | 7500
500050006 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 81791 | 6637 | 7500
500050005 | CLB-MP-HAUL-DT177 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 81791 | 29757 | 7500
500050004 | CLB-MP-HAUL-DT177 -STRSYS-STVLV | Valve Steering | 81791 | 8723 | 7500
500050003 | CLB-MP-HAUL-DT177 -STRSYS-STHMU | Steering HMU | 81791 | 15830 | 7500
500050002 | CLB-MP-HAUL-DT177 -STRSYS-STPMP | Pump Steering | 81791 | 8723 | 7500
500050001 | CLB-MP-HAUL-DT177 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 81791 | 8723 | 7500
500050000 | CLB-MP-HAUL-DT177 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 81791 | 8723 | 7500
500049999 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 81791 | 8723 | 7500
500049998 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 81791 | 8723 | 7500
500049997 | CLB-MP-HAUL-DT177 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 81791 | 8723 | 7500
500049996 | CLB-MP-HAUL-DT177 -BRKSYS-BACCM | Brake Accumulator | 81791 | 8723 | 7500
500049995 | CLB-MP-HAUL-DT177 -BRKSYS-BROCO | Brake Oil Cooler | 81791 | 81791 | 7500
500049994 | CLB-MP-HAUL-DT177 -BRKSYS-MERTR | Mechanical Retarder | 81791 | 81791 | 7500
500049993 | CLB-MP-HAUL-DT177 -BRKSYS-BRVTR | Valve Brake Treadle | 81791 | 81791 | 7500
500049992 | CLB-MP-HAUL-DT177 -BRKSYS-HYFPP | Pump Brake Control | 81791 | 8723 | 7500
500049991 | CLB-MP-HAUL-DT177 -BRKSYS-PRKPP | Pump Park Brake Release | 81791 | 81791 | 7500
500049990 | CLB-MP-HAUL-DT177 -BRKSYS-BRPMP | Pump Brake | 81791 | 81791 | 7500
500049989 | CLB-MP-HAUL-DT177 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 81791 | 81791 | 7500
500049988 | CLB-MP-HAUL-DT177 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 81791 | 81791 | 7500
500049987 | CLB-MP-HAUL-DT177 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 81791 | 81791 | 7500
500049986 | CLB-MP-HAUL-DT177 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 81791 | 81791 | 7500
500049985 | CLB-MP-HAUL-DT177 -BRKSYS-SRVBK | Service Brake | 81791 | 81791 | 7500
500049984 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 81791 | 81791 | 7500
500049983 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 81791 | 81791 | 7500
500049982 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 81791 | 8723 | 7500
500049981 | CLB-MP-HAUL-DT177 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 81791 | 8723 | 7500
500049980 | CLB-MP-HAUL-DT177 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 81791 | 8723 | 7500
500049979 | CLB-MP-HAUL-DT177 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 81791 | 8723 | 7500
500049978 | CLB-MP-HAUL-DT177 -FDRSYS-DRLAX | Drive Line Axles | 81791 | 81791 | 7500
500049977 | CLB-MP-HAUL-DT177 -FDRSYS-DIFFL | Differential | 81791 | 8723 | 7500
500049976 | CLB-MP-HAUL-DT177 -FDRSYS-DRSHT | Transmission Drive Shaft | 81791 | 8723 | 7500
500049975 | CLB-MP-HAUL-DT177 -TRNSYS-TROLC | Oil Cooler Transmission | 81791 | 8723 | 7500
500049974 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 81791 | 8723 | 7500
500049973 | CLB-MP-HAUL-DT177 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 81791 | 3161 | 7500
500049972 | CLB-MP-HAUL-DT177 -TRNSYS-TRANS | Transmission | 81791 | 3161 | 7500
500049971 | CLB-MP-HAUL-DT177 -TRNSYS-TRQUE | Torque Converter | 81791 | 8723 | 7500
500049970 | CLB-MP-HAUL-DT177 -ELCTLV-CHARG-BATTY | Batteries | 81791 | 81791 | 7500
500049969 | CLB-MP-HAUL-DT177 -ELCTLV-CHARG-ALTER | Alternator 24V | 81791 | 8723 | 7500
500049968 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 81791 | 8723 | 7500
500049967 | CLB-MP-HAUL-DT177 -ENGINE-PMPDR | Pump Drive | 81791 | 8723 | 7500
500049966 | CLB-MP-HAUL-DT177 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81791 | 8723 | 7500
500049965 | CLB-MP-HAUL-DT177 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81791 | 8723 | 7500
500049964 | CLB-MP-HAUL-DT177 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 81791 | 8723 | 7500
500049963 | CLB-MP-HAUL-DT177 -ENGINE-FUSYS-FULTK | Fuel Tank | 81791 | 8723 | 7500
500049962 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-EXHST | Exhaust System | 81791 | 81791 | 7500
500049961 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-AFTER | Aftercooler | 81791 | 81791 | 7500
500049960 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 81791 | 8723 | 7500
500049959 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 81791 | 8608 | 7500
500049958 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 81791 | 8723 | 7500
500049957 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 81791 | 8723 | 7500
500049956 | CLB-MP-HAUL-DT177 -ENGINE-INTEX-AIRFL | Air Filtration System | 81791 | 81791 | 7500
500049955 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-THERM | Thermostats/Regulators | 81791 | 8723 | 7500
500049954 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-BELTS | Fan Belts Engine | 81791 | 81791 | 7500
500049953 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 81791 | 8723 | 7500
500049952 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-COFAN | Fan Cooling System | 81791 | 8723 | 7500
500049951 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-RADTR | Coolant Engine | 81791 | 31511 | 7400
500049950 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-RADTR | Radiator Engine | 81791 | 8723 | 7500
500049949 | CLB-MP-HAUL-DT177 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81791 | 8723 | 7500
500049948 | CLB-MP-HAUL-DT177 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81791 | 81791 | 7500
500049947 | CLB-MP-HAUL-DT177 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81791 | 8723 | 7500
500049946 | CLB-MP-HAUL-DT177 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81791 | 81791 | 7500
500049945 | CLB-MP-HAUL-DT177 -ENGINE-COMPR | Air Compressor | 81791 | 8723 | 7500
500049943 | CLB-MP-HAUL-DT177 -ENGINE | Engine Assembly Caterpillar 3516B | 81791 | 8723 | 7500
500049942 | CLB-MP-HAUL-DT177 | DT177 Lubrication & Mechanical Services | 81791 | 81791 | 7500
500049941 | CLB-MP-HAUL-DT177 | Caterpillar 789D Haul Truck DT177 | 81791 | 81791 | 7500
500160255 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITRH | Air Tank Right | 85021 | 13713 | 7500
500160254 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK-AITLH | Air Tank Left | 85021 | 13713 | 7500
500147230 | CLB-MP-HAUL-DT176 -STRSYS-STACC | Steering Accumulator Rear | 35516 | 35516 | 7500
500147229 | CLB-MP-HAUL-DT176 -STRSYS-STACC | Steering Accumulator Middle | 35516 | 35516 | 7500
500147228 | CLB-MP-HAUL-DT176 -STRSYS-STACC | Steering Accumulator Front | 35516 | 35516 | 7500
500118555 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-AFRME | A Frame Housing | 85284 | 35516 | 7500
500117931 | CLB-MP-HAUL-DT176 -ELCTLV-LIGHT | Lighting Low Voltage | 85284 | 52270 | 7500
500117891 | CLB-MP-HAUL-DT176 -ELCTLV-HARNS | Electrical Harness | 85284 | 52270 | 7500
500117851 | CLB-MP-HAUL-DT176 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 85284 | 52270 | 7500
500117415 | CLB-MP-HAUL-DT176 -ELCTLV-LIGHT-AHSYS | AHS Lights | 85284 | 52270 | 7500
500117295 | CLB-MP-HAUL-DT176 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 85284 | 52270 | 7500
500111217 | CLB-MP-HAUL-DT176 -STRUCT-RAXHO | Rear Axle Housing | 85272 | 85272 | 7500
500110547 | CLB-MP-HAUL-DT176 -GRSYST | Grease Lubrication System | 85284 | 13295 | 7500
500102797 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 85284 | 13976 | 7500
500100624 | CLB-MP-HAUL-DT176 -TRNSYS | DT176 Transmission System | 85284 | 85284 | 7500
500081401 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 85284 | 25686 | 7500
500081261 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 85284 | 25686 | 7500
500079434 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN | Suspension Service | 85284 | 13976 | 7500
500078500 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 85284 | 13976 | 7500
500078463 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 85284 | 13976 | 7500
500062652 | CLB-MP-HAUL-DT176 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 85284 | 13976 | 7500
500062651 | CLB-MP-HAUL-DT176 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 85284 | 13976 | 7500
500062650 | CLB-MP-HAUL-DT176 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 85284 | 13976 | 7500
500062649 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-ELECT | Chassis Electrical System | 85284 | 35516 | 7500
500062648 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-ELECT | Cabin Electrical System | 85284 | 85284 | 7500
500062647 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 85284 | 13976 | 7500
500062646 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 85284 | 13976 | 7500
500062645 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 85284 | 13976 | 7500
500062644 | CLB-MP-HAUL-DT176 -STRSYS-STHLF-STRHO | Steering System Hoses | 85284 | 13976 | 7500
500062643 | CLB-MP-HAUL-DT176 -STRSYS-STLTR-STBST | Ball Studs | 85284 | 85284 | 7500
500062642 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 85284 | 13976 | 7500
500062641 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 85284 | 13976 | 7500
500062640 | CLB-MP-HAUL-DT176 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 85284 | 13976 | 7500
500062639 | CLB-MP-HAUL-DT176 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 85284 | 13976 | 7500
500062638 | CLB-MP-HAUL-DT176 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 85284 | 13976 | 7500
500062637 | CLB-MP-HAUL-DT176 -BRKSYS-BRVRL | Brake Relay Valve | 85284 | 13976 | 7500
500062635 | CLB-MP-HAUL-DT176 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 85284 | 13976 | 7500
500062634 | CLB-MP-HAUL-DT176 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 85284 | 13976 | 7500
500060114 | CLB-MP-HAUL-DT176 -STRSYS-STTNK | Tank Steering | 85284 | 85284 | 7500
500053840 | CLB-MP-HAUL-DT176 -BRKSYS-BRVLV | Valve Brake | 85284 | 13976 | 7500
500049940 | CLB-MP-HAUL-DT176 -MANGMT-UMMMC | Mine Monitoring and Control | 85284 | 85284 | 7500
500049939 | CLB-MP-HAUL-DT176 -MANGMT-UMTRN | Power Train Management System | 85284 | 85284 | 7500
500049938 | CLB-MP-HAUL-DT176 -MANGMT-UMENG | Engine Management System | 85284 | 85284 | 7500
500049937 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 85284 | 13976 | 7500
500049936 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 85284 | 13976 | 7500
500049935 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 85284 | 13976 | 7500
500049934 | CLB-MP-HAUL-DT176 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 85284 | 20366 | 7500
500049931 | CLB-MP-HAUL-DT176 -STRUCT-TRAYS | Tray | 85284 | 35516 | 7500
500049930 | CLB-MP-HAUL-DT176 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 85284 | 13976 | 7500
500049929 | CLB-MP-HAUL-DT176 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 85284 | 13976 | 7500
500049928 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-TAGLK | Tag Link | 85284 | 42256 | 7500
500049927 | CLB-MP-HAUL-DT176 -STRUCT-CHASS-AFRME | A Frame Bearing | 85284 | 35516 | 7500
500049926 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-SBELT | Seat Belt | 85284 | 85284 | 7500
500049925 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-SEATS | Operators Seat | 85284 | 22334 | 7500
500049924 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 85284 | 85284 | 7500
500049923 | CLB-MP-HAUL-DT176 -STRUCT-CABIN-AIRCN | Air Conditioning System | 85284 | 13976 | 7500
500049922 | CLB-MP-HAUL-DT176 -STRUCT-CABIN | Operators Cabin | 85284 | 35516 | 7500
500049921 | CLB-MP-HAUL-DT176 -PNEUMC-START | Air Starter | 85284 | 2613 | 7500
500049920 | CLB-MP-HAUL-DT176 -PNEUMC-AIRDR | Air Drier | 85284 | 13976 | 7500
500049919 | CLB-MP-HAUL-DT176 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 85284 | 85284 | 7500
500049918 | CLB-MP-HAUL-DT176 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 85284 | 85284 | 7500
500049917 | CLB-MP-HAUL-DT176 -PNEUMC-PNTNK | No Not Use | 85284 | 13976 | 7500
500049916 | CLB-MP-HAUL-DT176 -GRSYST-ALCON | Auto Lube Controller | 85284 | 85284 | 7500
500049915 | CLB-MP-HAUL-DT176 -GRSYST-ALBPP | Auto Lube Pump | 85284 | 59238 | 7500
500049914 | CLB-MP-HAUL-DT176 -GRSYST-GRTNK | Auto Lube Resevoir | 85284 | 85284 | 7500
500049913 | CLB-MP-HAUL-DT176 -GRSYST-GRINJ | Auto Lube Injectors | 85284 | 85284 | 7500
500049912 | CLB-MP-HAUL-DT176 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 85284 | 13976 | 7500
500049911 | CLB-MP-HAUL-DT176 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 85284 | 13976 | 7500
500049910 | CLB-MP-HAUL-DT176 -HYDSYS-HOVLV | Valve Hoist | 85284 | 35516 | 7500
500049909 | CLB-MP-HAUL-DT176 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 85284 | 85284 | 7500
500049908 | CLB-MP-HAUL-DT176 -HYDSYS-HDTNK | Tank Hydraulic | 85284 | 85284 | 7500
500049907 | CLB-MP-HAUL-DT176 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 85284 | 13976 | 7500
500049906 | CLB-MP-HAUL-DT176 -HYDSYS-HOPMP | Pump Hoist | 85284 | 13976 | 7500
500049905 | CLB-MP-HAUL-DT176 -HYDSYS | Hydraulic System | 85284 | 85284 | 7500
500049904 | CLB-MP-HAUL-DT176 -STRSYS-STCON-STCOL | Steering Column | 85284 | 46857 | 7500
500049903 | CLB-MP-HAUL-DT176 -STRSYS-STCON-STWHL | Steering Wheel | 85284 | 85284 | 7500
500049902 | CLB-MP-HAUL-DT176 -STRSYS-STLTR | Steering Linkages and Tie Rods | 85284 | 19786 | 7500
500049901 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 85284 | 13976 | 7500
500049900 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 85284 | 13976 | 7500
500049899 | CLB-MP-HAUL-DT176 -STRSYS-STACC-SACCF | Accumulator Steering Front | 85284 | 13976 | 7500
500049898 | CLB-MP-HAUL-DT176 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 85284 | 1339 | 7500
500049897 | CLB-MP-HAUL-DT176 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 85284 | 1339 | 7500
500049896 | CLB-MP-HAUL-DT176 -STRSYS-STVLV | Valve Steering | 85284 | 13976 | 7500
500049895 | CLB-MP-HAUL-DT176 -STRSYS-STHMU | Steering HMU | 85284 | 19801 | 7500
500049894 | CLB-MP-HAUL-DT176 -STRSYS-STPMP | Pump Steering | 85284 | 5818 | 7500
500049893 | CLB-MP-HAUL-DT176 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 85284 | 13976 | 7500
500049892 | CLB-MP-HAUL-DT176 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 85284 | 13976 | 7500
500049891 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 85284 | 13976 | 7500
500049890 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 85284 | 13976 | 7500
500049889 | CLB-MP-HAUL-DT176 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 85284 | 13976 | 7500
500049888 | CLB-MP-HAUL-DT176 -BRKSYS-BACCM | Brake Accumulator | 85284 | 13976 | 7500
500049887 | CLB-MP-HAUL-DT176 -BRKSYS-BROCO | Brake Oil Cooler | 85284 | 85284 | 7500
500049886 | CLB-MP-HAUL-DT176 -BRKSYS-MERTR | Mechanical Retarder | 85284 | 85284 | 7500
500049885 | CLB-MP-HAUL-DT176 -BRKSYS-BRVTR | Valve Brake Treadle | 85284 | 85284 | 7500
500049884 | CLB-MP-HAUL-DT176 -BRKSYS-HYFPP | Pump Brake Control | 85284 | 6894 | 7500
500049883 | CLB-MP-HAUL-DT176 -BRKSYS-PRKPP | Pump Park Brake Release | 85284 | 85284 | 7500
500049882 | CLB-MP-HAUL-DT176 -BRKSYS-BRPMP | Pump Brake | 85284 | 85284 | 7500
500049881 | CLB-MP-HAUL-DT176 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 85284 | 85284 | 7500
500049880 | CLB-MP-HAUL-DT176 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 85284 | 85284 | 7500
500049879 | CLB-MP-HAUL-DT176 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 85284 | 85284 | 7500
500049878 | CLB-MP-HAUL-DT176 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 85284 | 85284 | 7500
500049877 | CLB-MP-HAUL-DT176 -BRKSYS-SRVBK | Service Brake | 85284 | 85284 | 7500
500049876 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 85284 | 13955 | 7500
500049875 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 85284 | 85284 | 7500
500049874 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 85284 | 13976 | 7500
500049873 | CLB-MP-HAUL-DT176 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 85284 | 26295 | 7500
500049872 | CLB-MP-HAUL-DT176 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 85284 | 13914 | 7500
500049871 | CLB-MP-HAUL-DT176 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 85284 | 16434 | 7500
500049870 | CLB-MP-HAUL-DT176 -FDRSYS-DRLAX | Drive Line Axles | 85284 | 85284 | 7500
500049869 | CLB-MP-HAUL-DT176 -FDRSYS-DIFFL | Differential | 85284 | 13976 | 7500
500049868 | CLB-MP-HAUL-DT176 -FDRSYS-DRSHT | Transmission Drive Shaft | 85284 | 13976 | 7500
500049867 | CLB-MP-HAUL-DT176 -TRNSYS-TROLC | Oil Cooler Transmission | 85284 | 11308 | 7500
500049866 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 85284 | 6904 | 7500
500049865 | CLB-MP-HAUL-DT176 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 85284 | 11308 | 7500
500049864 | CLB-MP-HAUL-DT176 -TRNSYS-TRANS | Transmission | 85284 | 11308 | 7500
500049863 | CLB-MP-HAUL-DT176 -TRNSYS-TRQUE | Torque Converter | 85284 | 13976 | 7500
500049862 | CLB-MP-HAUL-DT176 -ELCTLV-CHARG-BATTY | Batteries | 85284 | 29425 | 7500
500049861 | CLB-MP-HAUL-DT176 -ELCTLV-CHARG-ALTER | Alternator 24V | 85284 | 2613 | 7500
500049860 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 85284 | 13976 | 7500
500049859 | CLB-MP-HAUL-DT176 -ENGINE-PMPDR | Pump Drive | 85284 | 13976 | 7500
500049858 | CLB-MP-HAUL-DT176 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 85284 | 13976 | 7500
500049857 | CLB-MP-HAUL-DT176 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 85284 | 2613 | 7500
500049856 | CLB-MP-HAUL-DT176 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 85284 | 2613 | 7500
500049855 | CLB-MP-HAUL-DT176 -ENGINE-FUSYS-FULTK | Fuel Tank | 85284 | 13976 | 7500
500049854 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-EXHST | Exhaust System | 85284 | 85284 | 7500
500049853 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-AFTER | Aftercooler | 85284 | 85284 | 7500
500049852 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 85284 | 2613 | 7500
500049851 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 85284 | 2613 | 7500
500049850 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 85284 | 2613 | 7500
500049849 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 85284 | 2613 | 7500
500049848 | CLB-MP-HAUL-DT176 -ENGINE-INTEX-AIRFL | Air Filtration System | 85284 | 85284 | 7500
500049847 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-THERM | Thermostats/Regulators | 85284 | 2613 | 7500
500049846 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-BELTS | Fan Belts Engine | 85284 | 85284 | 7500
500049845 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 85284 | 2613 | 7500
500049844 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-COFAN | Fan Cooling System | 85284 | 13976 | 7500
500049843 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-RADTR | Coolant Engine | 85284 | 35516 | 7400
500049842 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-RADTR | Radiator Engine | 85284 | 13976 | 7500
500049841 | CLB-MP-HAUL-DT176 -ENGINE-COSYS-WTRPP | Water Pump Engine | 85284 | 2613 | 7500
500049840 | CLB-MP-HAUL-DT176 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 85284 | 85284 | 7500
500049839 | CLB-MP-HAUL-DT176 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 85284 | 11281 | 7500
500049838 | CLB-MP-HAUL-DT176 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 85284 | 85284 | 7500
500049837 | CLB-MP-HAUL-DT176 -ENGINE-COMPR | Air Compressor | 85284 | 2613 | 7500
500049835 | CLB-MP-HAUL-DT176 -ENGINE | Engine Assembly Caterpillar 3516B | 85284 | 13976 | 7500
500049834 | CLB-MP-HAUL-DT176 | DT176 Lubrication & Mechanical Services | 85284 | 85284 | 7500
500049833 | CLB-MP-HAUL-DT176 | Caterpillar 789D Haul Truck DT176 | 85284 | 85284 | 7500
500160253 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITLH | Air Tank Right | 82478 | 82478 | 7500
500160252 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK-AITRH | Air Tank Left | 82478 | 82478 | 7500
500147226 | CLB-MP-HAUL-DT175 -STRSYS-STACC | Steering Accumulator Rear | 31520 | 31520 | 7500
500147225 | CLB-MP-HAUL-DT175 -STRSYS-STACC | Steering Accumulator Middle | 31520 | 31520 | 7500
500147224 | CLB-MP-HAUL-DT175 -STRSYS-STACC | Steering Accumulator Front | 31520 | 31520 | 7500
500118554 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-AFRME | A Frame Housing | 82722 | 7663 | 7500
500117930 | CLB-MP-HAUL-DT175 -ELCTLV-LIGHT | Lighting Low Voltage | 82722 | 50707 | 7500
500117890 | CLB-MP-HAUL-DT175 -ELCTLV-HARNS | Electrical Harness | 82722 | 50707 | 7500
500117850 | CLB-MP-HAUL-DT175 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 82722 | 50707 | 7500
500117414 | CLB-MP-HAUL-DT175 -ELCTLV-LIGHT-AHSYS | AHS Lights | 82722 | 50707 | 7500
500117294 | CLB-MP-HAUL-DT175 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 82722 | 50707 | 7500
500111215 | CLB-MP-HAUL-DT175 -STRUCT-RAXHO | Rear Axle Housing | 82644 | 7663 | 7500
500110546 | CLB-MP-HAUL-DT175 -GRSYST | Grease Lubrication System | 82722 | 7663 | 7500
500102796 | CLB-MP-HAUL-DT175 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 82722 | 20002 | 7500
500100623 | CLB-MP-HAUL-DT175 -TRNSYS | DT175 Transmission System | 82722 | 44607 | 7500
500081400 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 82722 | 18747 | 7500
500081260 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 82722 | 18747 | 7500
500079433 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN | Suspension Service | 82722 | 11190 | 7500
500078499 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 82722 | 7663 | 7500
500078462 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 82722 | 7663 | 7500
500062633 | CLB-MP-HAUL-DT175 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 82722 | 7663 | 7500
500062632 | CLB-MP-HAUL-DT175 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 82722 | 7663 | 7500
500062631 | CLB-MP-HAUL-DT175 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 82722 | 7663 | 7500
500062630 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-ELECT | Chassis Electrical System | 82722 | 31520 | 7500
500062629 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-ELECT | Cabin Electrical System | 82722 | 82722 | 7500
500062628 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 82722 | 82722 | 7500
500062627 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 82722 | 82722 | 7500
500062626 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 82722 | 82722 | 7500
500062625 | CLB-MP-HAUL-DT175 -STRSYS-STHLF-STRHO | Steering System Hoses | 82722 | 7663 | 7500
500062624 | CLB-MP-HAUL-DT175 -STRSYS-STLTR-STBST | Ball Studs | 82722 | 39949 | 7500
500062623 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 82722 | 7663 | 7500
500062622 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 82722 | 7663 | 7500
500062621 | CLB-MP-HAUL-DT175 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 82722 | 7663 | 7500
500062620 | CLB-MP-HAUL-DT175 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 82722 | 7663 | 7500
500062619 | CLB-MP-HAUL-DT175 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 82722 | 18747 | 7500
500062618 | CLB-MP-HAUL-DT175 -BRKSYS-BRVRL | Brake Relay Valve | 82722 | 7663 | 7500
500062616 | CLB-MP-HAUL-DT175 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 82722 | 7663 | 7500
500062615 | CLB-MP-HAUL-DT175 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 82722 | 7663 | 7500
500060113 | CLB-MP-HAUL-DT175 -STRSYS-STTNK | Tank Steering | 82722 | 82722 | 7500
500053839 | CLB-MP-HAUL-DT175 -BRKSYS-BRVLV | Valve Brake | 82722 | 7663 | 7500
500048677 | CLB-MP-HAUL-DT175 -MANGMT-UMMMC | Mine Monitoring and Control | 82722 | 82722 | 7500
500048676 | CLB-MP-HAUL-DT175 -MANGMT-UMTRN | Power Train Management System | 82722 | 82722 | 7500
500048675 | CLB-MP-HAUL-DT175 -MANGMT-UMENG | Engine Management System | 82722 | 82722 | 7500
500048674 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 82722 | 7663 | 7500
500048673 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 82722 | 7663 | 7500
500048672 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 82722 | 7663 | 7500
500048671 | CLB-MP-HAUL-DT175 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 82722 | 7663 | 7500
500048668 | CLB-MP-HAUL-DT175 -STRUCT-TRAYS | Tray | 82722 | 7663 | 7500
500048667 | CLB-MP-HAUL-DT175 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 82722 | 11992 | 7500
500048666 | CLB-MP-HAUL-DT175 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 82722 | 11992 | 7500
500048665 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-TAGLK | Tag Link | 82722 | 7663 | 7500
500048664 | CLB-MP-HAUL-DT175 -STRUCT-CHASS-AFRME | A Frame Bearing | 82722 | 7663 | 7500
500048663 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-SBELT | Seat Belt | 82722 | 82722 | 7500
500048662 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-SEATS | Operators Seat | 82722 | 14586 | 7500
500048661 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 82722 | 82722 | 7500
500048657 | CLB-MP-HAUL-DT175 -STRUCT-CABIN-AIRCN | Air Conditioning System | 82722 | 14586 | 7500
500048656 | CLB-MP-HAUL-DT175 -STRUCT-CABIN | Operators Cabin | 82722 | 31520 | 7500
500048655 | CLB-MP-HAUL-DT175 -PNEUMC-START | Air Starter | 82722 | 7663 | 7500
500048654 | CLB-MP-HAUL-DT175 -PNEUMC-AIRDR | Air Drier | 82722 | 71526 | 7500
500048653 | CLB-MP-HAUL-DT175 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 82722 | 82722 | 7500
500048652 | CLB-MP-HAUL-DT175 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 82722 | 82722 | 7500
500048651 | CLB-MP-HAUL-DT175 -PNEUMC-PNTNK | No Not Use | 82722 | 82722 | 7500
500048650 | CLB-MP-HAUL-DT175 -GRSYST-ALCON | Auto Lube Controller | 82722 | 82722 | 7500
500048649 | CLB-MP-HAUL-DT175 -GRSYST-ALBPP | Auto Lube Pump | 82722 | 39511 | 7500
500048648 | CLB-MP-HAUL-DT175 -GRSYST-GRTNK | Auto Lube Resevoir | 82722 | 82722 | 7500
500048647 | CLB-MP-HAUL-DT175 -GRSYST-GRINJ | Auto Lube Injectors | 82722 | 82722 | 7500
500048646 | CLB-MP-HAUL-DT175 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 82722 | 20002 | 7500
500048645 | CLB-MP-HAUL-DT175 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 82722 | 2653 | 7500
500048644 | CLB-MP-HAUL-DT175 -HYDSYS-HOVLV | Valve Hoist | 82722 | 31520 | 7500
500048643 | CLB-MP-HAUL-DT175 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 82722 | 82722 | 7500
500048642 | CLB-MP-HAUL-DT175 -HYDSYS-HDTNK | Tank Hydraulic | 82722 | 82722 | 7500
500048641 | CLB-MP-HAUL-DT175 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 82722 | 7663 | 7500
500048640 | CLB-MP-HAUL-DT175 -HYDSYS-HOPMP | Pump Hoist | 82722 | 7663 | 7500
500048639 | CLB-MP-HAUL-DT175 -HYDSYS | Hydraulic System | 82722 | 82722 | 7500
500048638 | CLB-MP-HAUL-DT175 -STRSYS-STCON-STCOL | Steering Column | 82722 | 82722 | 7500
500048637 | CLB-MP-HAUL-DT175 -STRSYS-STCON-STWHL | Steering Wheel | 82722 | 82722 | 7500
500048636 | CLB-MP-HAUL-DT175 -STRSYS-STLTR | Steering Linkages and Tie Rods | 82722 | 7663 | 7500
500048635 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 82722 | 7663 | 7500
500048634 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 82722 | 7663 | 7500
500048633 | CLB-MP-HAUL-DT175 -STRSYS-STACC-SACCF | Accumulator Steering Front | 82722 | 7663 | 7500
500048632 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 82722 | 7663 | 7500
500048631 | CLB-MP-HAUL-DT175 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 82722 | 16512 | 7500
500048630 | CLB-MP-HAUL-DT175 -STRSYS-STVLV | Valve Steering | 82722 | 18747 | 7500
500048629 | CLB-MP-HAUL-DT175 -STRSYS-STHMU | Steering HMU | 82722 | 21106 | 7500
500048628 | CLB-MP-HAUL-DT175 -STRSYS-STPMP | Pump Steering | 82722 | 7663 | 7500
500048627 | CLB-MP-HAUL-DT175 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 82722 | 7663 | 7500
500048626 | CLB-MP-HAUL-DT175 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 82722 | 528 | 7500
500048625 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 82722 | 7663 | 7500
500048624 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 82722 | 7663 | 7500
500048623 | CLB-MP-HAUL-DT175 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 82722 | 7663 | 7500
500048622 | CLB-MP-HAUL-DT175 -BRKSYS-BACCM | Brake Accumulator | 82722 | 7663 | 7500
500048621 | CLB-MP-HAUL-DT175 -BRKSYS-BROCO | Brake Oil Cooler | 82722 | 62172 | 7500
500048620 | CLB-MP-HAUL-DT175 -BRKSYS-MERTR | Mechanical Retarder | 82722 | 82722 | 7500
500048619 | CLB-MP-HAUL-DT175 -BRKSYS-BRVTR | Valve Brake Treadle | 82722 | 82722 | 7500
500048618 | CLB-MP-HAUL-DT175 -BRKSYS-HYFPP | Pump Brake Control | 82722 | 20002 | 7500
500048617 | CLB-MP-HAUL-DT175 -BRKSYS-PRKPP | Pump Park Brake Release | 82722 | 60127 | 7500
500048616 | CLB-MP-HAUL-DT175 -BRKSYS-BRPMP | Pump Brake | 82722 | 82722 | 7500
500048615 | CLB-MP-HAUL-DT175 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 82722 | 82722 | 7500
500048614 | CLB-MP-HAUL-DT175 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 82722 | 82722 | 7500
500048613 | CLB-MP-HAUL-DT175 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 82722 | 82722 | 7500
500048612 | CLB-MP-HAUL-DT175 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 82722 | 82722 | 7500
500048611 | CLB-MP-HAUL-DT175 -BRKSYS-SRVBK | Service Brake | 82722 | 82722 | 7500
500048610 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 82722 | 82722 | 7500
500048609 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 82722 | 82722 | 7500
500048608 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 82722 | 7663 | 7500
500048607 | CLB-MP-HAUL-DT175 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 82722 | 7663 | 7500
500048606 | CLB-MP-HAUL-DT175 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 82722 | 18747 | 7500
500048605 | CLB-MP-HAUL-DT175 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 82722 | 18747 | 7500
500048604 | CLB-MP-HAUL-DT175 -FDRSYS-DRLAX | Drive Line Axles | 82722 | 82722 | 7500
500048603 | CLB-MP-HAUL-DT175 -FDRSYS-DIFFL | Differential | 82722 | 7663 | 7500
500048602 | CLB-MP-HAUL-DT175 -FDRSYS-DRSHT | Transmission Drive Shaft | 82722 | 7663 | 7500
500048601 | CLB-MP-HAUL-DT175 -TRNSYS-TROLC | Oil Cooler Transmission | 82722 | 7663 | 7500
500048600 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 82722 | 15352 | 7500
500048599 | CLB-MP-HAUL-DT175 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 82721 | 7663 | 7500
500048598 | CLB-MP-HAUL-DT175 -TRNSYS-TRANS | Transmission | 82722 | 11992 | 7500
500048597 | CLB-MP-HAUL-DT175 -TRNSYS-TRQUE | Torque Converter | 82722 | 15352 | 7500
500048596 | CLB-MP-HAUL-DT175 -ELCTLV-CHARG-BATTY | Batteries | 82722 | 11190 | 7500
500048595 | CLB-MP-HAUL-DT175 -ELCTLV-CHARG-ALTER | Alternator 24V | 82722 | 7663 | 7500
500048594 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 82722 | 7663 | 7500
500048593 | CLB-MP-HAUL-DT175 -ENGINE-PMPDR | Pump Drive | 82722 | 7663 | 7500
500048592 | CLB-MP-HAUL-DT175 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 82722 | 7663 | 7500
500048591 | CLB-MP-HAUL-DT175 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 82722 | 7663 | 7500
500048590 | CLB-MP-HAUL-DT175 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 82722 | 7663 | 7500
500048589 | CLB-MP-HAUL-DT175 -ENGINE-FUSYS-FULTK | Fuel Tank | 82722 | 31520 | 7500
500048588 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-EXHST | Exhaust System | 82722 | 82722 | 7500
500048587 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-AFTER | Aftercooler | 82722 | 82722 | 7500
500048586 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 82722 | 7663 | 7500
500048585 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 82722 | 7663 | 7500
500048584 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 82722 | 7663 | 7500
500048583 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 82722 | 7663 | 7500
500048582 | CLB-MP-HAUL-DT175 -ENGINE-INTEX-AIRFL | Air Filtration System | 82722 | 82722 | 7500
500048581 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-THERM | Thermostats/Regulators | 82722 | 7663 | 7500
500048580 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-BELTS | Fan Belts Engine | 82722 | 82722 | 7500
500048579 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 82722 | 7663 | 7500
500048578 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-COFAN | Fan Cooling System | 82722 | 7663 | 7500
500048576 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-RADTR | Radiator Engine | 82722 | 13194 | 7500
500048575 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-WTRPP | Water Pump Engine | 82722 | 7663 | 7500
500048574 | CLB-MP-HAUL-DT175 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 82722 | 82722 | 7500
500048573 | CLB-MP-HAUL-DT175 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 82722 | 7663 | 7500
500048572 | CLB-MP-HAUL-DT175 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 82722 | 82722 | 7500
500048571 | CLB-MP-HAUL-DT175 -ENGINE-COMPR | Air Compressor | 82722 | 7663 | 7500
500048569 | CLB-MP-HAUL-DT175 -ENGINE | Engine Assembly Caterpillar 3516B | 82722 | 7663 | 7500
500048568 | CLB-MP-HAUL-DT175 | DT175 Lubrication & Mechanical Services | 82722 | 82722 | 7500
500048567 | CLB-MP-HAUL-DT175 | Caterpillar 789D Haul Truck DT175 | 82722 | 82722 | 7500
500160251 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITRH | Air Tank Right | 83507 | 83507 | 7500
500160250 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK-AITLH | Air Tank Left | 83507 | 83507 | 7500
500147222 | CLB-MP-HAUL-DT174 -STRSYS-STACC | Steering Accumulator Rear | 34457 | 34457 | 7500
500147221 | CLB-MP-HAUL-DT174 -STRSYS-STACC | Steering Accumulator Middle | 34457 | 34457 | 7500
500147220 | CLB-MP-HAUL-DT174 -STRSYS-STACC | Steering Accumulator Front | 34457 | 34457 | 7500
500118553 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-AFRME | A Frame Housing | 83749 | 10427 | 7500
500117929 | CLB-MP-HAUL-DT174 -ELCTLV-LIGHT | Lighting Low Voltage | 83749 | 52051 | 7500
500117889 | CLB-MP-HAUL-DT174 -ELCTLV-HARNS | Electrical Harness | 83749 | 52051 | 7500
500117849 | CLB-MP-HAUL-DT174 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 86107 | 54409 | 7500
500117413 | CLB-MP-HAUL-DT174 -ELCTLV-LIGHT-AHSYS | AHS Lights | 83749 | 52051 | 7500
500117293 | CLB-MP-HAUL-DT174 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 83749 | 52051 | 7500
500111216 | CLB-MP-HAUL-DT174 -STRUCT-RAXHO | Rear Axle Housing | 83690 | 46260 | 7500
500110545 | CLB-MP-HAUL-DT174 -GRSYST | Grease Lubrication System | 83749 | 11362 | 7500
500102795 | CLB-MP-HAUL-DT174 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83749 | 10427 | 7500
500100622 | CLB-MP-HAUL-DT174 -TRNSYS | DT174 Transmission System | 83749 | 49326 | 7500
500081399 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83749 | 14201 | 7500
500081259 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83749 | 14201 | 7500
500079432 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN | Suspension | 83749 | 23899 | 7500
500078498 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 83749 | 10427 | 7500
500078461 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 83749 | 10427 | 7500
500061425 | CLB-MP-HAUL-DT174 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83749 | 10427 | 7500
500061395 | CLB-MP-HAUL-DT174 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83749 | 10427 | 7500
500061077 | CLB-MP-HAUL-DT174 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 83749 | 10427 | 7500
500061076 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-ELECT | Chassis Electrical System | 83749 | 34457 | 7500
500061075 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83749 | 56158 | 7500
500061074 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83749 | 10427 | 7500
500061073 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 83749 | 10427 | 7500
500061072 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83749 | 10427 | 7500
500061071 | CLB-MP-HAUL-DT174 -STRSYS-STHLF-STRHO | Steering System Hoses | 83749 | 10427 | 7500
500061070 | CLB-MP-HAUL-DT174 -STRSYS-STLTR-STBST | Ball Studs | 83749 | 83749 | 7500
500061069 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 83749 | 10427 | 7500
500061068 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 83749 | 10427 | 7500
500061067 | CLB-MP-HAUL-DT174 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 83749 | 10427 | 7500
500061066 | CLB-MP-HAUL-DT174 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83749 | 10427 | 7500
500061065 | CLB-MP-HAUL-DT174 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83749 | 10427 | 7500
500061064 | CLB-MP-HAUL-DT174 -BRKSYS-BRVRL | Brake Relay Valve | 83749 | 10427 | 7500
500061062 | CLB-MP-HAUL-DT174 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83749 | 10427 | 7500
500061061 | CLB-MP-HAUL-DT174 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83749 | 10427 | 7500
500060112 | CLB-MP-HAUL-DT174 -STRSYS-STTNK | Tank Steering | 83749 | 83749 | 7500
500053838 | CLB-MP-HAUL-DT174 -BRKSYS-BRVLV | Valve Brake | 83749 | 10427 | 7500
500048566 | CLB-MP-HAUL-DT174 -MANGMT-UMMMC | Mine Monitoring and Control | 83749 | 83749 | 7500
500048565 | CLB-MP-HAUL-DT174 -MANGMT-UMTRN | Power Train Management System | 83749 | 83749 | 7500
500048564 | CLB-MP-HAUL-DT174 -MANGMT-UMENG | Engine Management System | 83749 | 83749 | 7500
500048563 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83749 | 10427 | 7500
500048562 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83749 | 10427 | 7500
500048561 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83749 | 10427 | 7500
500048560 | CLB-MP-HAUL-DT174 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83749 | 10427 | 7500
500048557 | CLB-MP-HAUL-DT174 -STRUCT-TRAYS | Tray | 83749 | 14389 | 7500
500048556 | CLB-MP-HAUL-DT174 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83749 | 10427 | 7500
500048555 | CLB-MP-HAUL-DT174 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83749 | 10427 | 7500
500048554 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-TAGLK | Tag Link | 83749 | 10427 | 7500
500048553 | CLB-MP-HAUL-DT174 -STRUCT-CHASS-AFRME | A Frame Bearing | 83749 | 10427 | 7500
500048552 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-SBELT | Seat Belt | 83749 | 51093 | 7500
500048551 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-SEATS | Operators Seat | 83749 | 18817 | 7500
500048550 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83749 | 83749 | 7500
500048546 | CLB-MP-HAUL-DT174 -STRUCT-CABIN-AIRCN | Air Conditioning System | 83749 | 10427 | 7500
500048545 | CLB-MP-HAUL-DT174 -STRUCT-CABIN | Operators Cabin | 83749 | 10427 | 7500
500048544 | CLB-MP-HAUL-DT174 -PNEUMC-START | Air Starter | 83749 | 10427 | 7500
500048543 | CLB-MP-HAUL-DT174 -PNEUMC-AIRDR | Air Drier | 83749 | 28501 | 7500
500048542 | CLB-MP-HAUL-DT174 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 83749 | 83749 | 7500
500048541 | CLB-MP-HAUL-DT174 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 83749 | 83749 | 7500
500048540 | CLB-MP-HAUL-DT174 -PNEUMC-PNTNK | No Not Use | 83749 | 83749 | 7500
500048539 | CLB-MP-HAUL-DT174 -GRSYST-ALCON | Auto Lube Controller | 83749 | 83749 | 7500
500048538 | CLB-MP-HAUL-DT174 -GRSYST-ALBPP | Auto Lube Pump | 83749 | 50455 | 7500
500048537 | CLB-MP-HAUL-DT174 -GRSYST-GRTNK | Auto Lube Resevoir | 83749 | 83749 | 7500
500048536 | CLB-MP-HAUL-DT174 -GRSYST-GRINJ | Auto Lube Injectors | 83749 | 83749 | 7500
500048535 | CLB-MP-HAUL-DT174 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83749 | 10427 | 7500
500048534 | CLB-MP-HAUL-DT174 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83749 | 10427 | 7500
500048533 | CLB-MP-HAUL-DT174 -HYDSYS-HOVLV | Valve Hoist | 83749 | 34457 | 7500
500048532 | CLB-MP-HAUL-DT174 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83749 | 83749 | 7500
500048531 | CLB-MP-HAUL-DT174 -HYDSYS-HDTNK | Tank Hydraulic | 83749 | 83749 | 7500
500048530 | CLB-MP-HAUL-DT174 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 83749 | 10427 | 7500
500048529 | CLB-MP-HAUL-DT174 -HYDSYS-HOPMP | Pump Hoist | 83749 | 10427 | 7500
500048528 | CLB-MP-HAUL-DT174 -HYDSYS | Hydraulic System | 83749 | 83749 | 7500
500048527 | CLB-MP-HAUL-DT174 -STRSYS-STCON-STCOL | Steering Column | 83749 | 56158 | 7500
500048526 | CLB-MP-HAUL-DT174 -STRSYS-STCON-STWHL | Steering Wheel | 83749 | 56158 | 7500
500048525 | CLB-MP-HAUL-DT174 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83749 | 10427 | 7500
500048524 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83749 | 10427 | 7500
500048523 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83749 | 10427 | 7500
500048522 | CLB-MP-HAUL-DT174 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83749 | 10427 | 7500
500048521 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83749 | 16824 | 7500
500048520 | CLB-MP-HAUL-DT174 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83749 | 3272 | 7500
500048519 | CLB-MP-HAUL-DT174 -STRSYS-STVLV | Valve Steering | 83749 | 10427 | 7500
500048518 | CLB-MP-HAUL-DT174 -STRSYS-STHMU | Steering HMU | 83749 | 10427 | 7500
500048517 | CLB-MP-HAUL-DT174 -STRSYS-STPMP | Pump Steering | 83749 | 10427 | 7500
500048516 | CLB-MP-HAUL-DT174 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83749 | 10427 | 7500
500048515 | CLB-MP-HAUL-DT174 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83749 | 10427 | 7500
500048514 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 83749 | 10427 | 7500
500048513 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 83749 | 10427 | 7500
500048512 | CLB-MP-HAUL-DT174 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 83749 | 10427 | 7500
500048511 | CLB-MP-HAUL-DT174 -BRKSYS-BACCM | Brake Accumulator | 83749 | 10427 | 7500
500048510 | CLB-MP-HAUL-DT174 -BRKSYS-BROCO | Brake Oil Cooler | 83749 | 56158 | 7500
500048509 | CLB-MP-HAUL-DT174 -BRKSYS-MERTR | Mechanical Retarder | 83749 | 56158 | 7500
500048508 | CLB-MP-HAUL-DT174 -BRKSYS-BRVTR | Valve Brake Treadle | 83749 | 54496 | 7500
500048507 | CLB-MP-HAUL-DT174 -BRKSYS-HYFPP | Pump Brake Control | 83749 | 14831 | 7500
500048506 | CLB-MP-HAUL-DT174 -BRKSYS-PRKPP | Pump Park Brake Release | 83749 | 83749 | 7500
500048505 | CLB-MP-HAUL-DT174 -BRKSYS-BRPMP | Pump Brake | 83749 | 21804 | 7500
500048504 | CLB-MP-HAUL-DT174 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83749 | 83749 | 7500
500048503 | CLB-MP-HAUL-DT174 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83749 | 83749 | 7500
500048502 | CLB-MP-HAUL-DT174 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83749 | 83749 | 7500
500048501 | CLB-MP-HAUL-DT174 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83749 | 83749 | 7500
500048500 | CLB-MP-HAUL-DT174 -BRKSYS-SRVBK | Service Brake | 83749 | 83749 | 7500
500048499 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83749 | 83749 | 7500
500048498 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83749 | 83749 | 7500
500048497 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 83749 | 10427 | 7500
500048496 | CLB-MP-HAUL-DT174 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83749 | 10427 | 7500
500048495 | CLB-MP-HAUL-DT174 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83749 | 17203 | 7500
500048494 | CLB-MP-HAUL-DT174 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83749 | 6217 | 7500
500048493 | CLB-MP-HAUL-DT174 -FDRSYS-DRLAX | Drive Line Axles | 83749 | 83749 | 7500
500048492 | CLB-MP-HAUL-DT174 -FDRSYS-DIFFL | Differential | 83749 | 10427 | 7500
500048491 | CLB-MP-HAUL-DT174 -FDRSYS-DRSHT | Transmission Drive Shaft | 83749 | 10427 | 7500
500048490 | CLB-MP-HAUL-DT174 -TRNSYS-TROLC | Oil Cooler Transmission | 83749 | 21779 | 7500
500048489 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83749 | 10427 | 7500
500048488 | CLB-MP-HAUL-DT174 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83749 | 10427 | 7500
500048487 | CLB-MP-HAUL-DT174 -TRNSYS-TRANS | Transmission | 83749 | 21827 | 7500
500048486 | CLB-MP-HAUL-DT174 -TRNSYS-TRQUE | Torque Converter | 83749 | 10427 | 7500
500048485 | CLB-MP-HAUL-DT174 -ELCTLV-CHARG-BATTY | Batteries | 83749 | 32358 | 7500
500048484 | CLB-MP-HAUL-DT174 -ELCTLV-CHARG-ALTER | Alternator 24V | 83749 | 10427 | 7500
500048483 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83749 | 10427 | 7500
500048482 | CLB-MP-HAUL-DT174 -ENGINE-PMPDR | Pump Drive | 83749 | 10427 | 7500
500048481 | CLB-MP-HAUL-DT174 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83749 | 10427 | 7500
500048480 | CLB-MP-HAUL-DT174 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83749 | 10427 | 7500
500048479 | CLB-MP-HAUL-DT174 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83749 | 10427 | 7500
500048478 | CLB-MP-HAUL-DT174 -ENGINE-FUSYS-FULTK | Fuel Tank | 83749 | 1854 | 7500
500048477 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-EXHST | Exhaust System | 83749 | 56158 | 7500
500048476 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-AFTER | Aftercooler | 83749 | 56158 | 7500
500048475 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 83749 | 10427 | 7500
500048474 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 83749 | 10427 | 7500
500048473 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 83749 | 10427 | 7500
500048472 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 83749 | 10427 | 7500
500048471 | CLB-MP-HAUL-DT174 -ENGINE-INTEX-AIRFL | Air Filtration System | 83749 | 56158 | 7500
500048470 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-THERM | Thermostats/Regulators | 83749 | 10427 | 7500
500048469 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-BELTS | Fan Belts Engine | 83749 | 56158 | 7500
500048468 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 83749 | 10427 | 7500
500048467 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-COFAN | Fan Cooling System | 83749 | 10427 | 7500
500048466 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-RADTR | Radiator Coolant | 83749 | 34457 | 7400
500048465 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-RADTR | Radiator Engine | 83749 | 10427 | 7500
500048464 | CLB-MP-HAUL-DT174 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83749 | 10427 | 7500
500048463 | CLB-MP-HAUL-DT174 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83749 | 56158 | 7500
500048462 | CLB-MP-HAUL-DT174 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83749 | 10427 | 7500
500048461 | CLB-MP-HAUL-DT174 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83749 | 56158 | 7500
500048460 | CLB-MP-HAUL-DT174 -ENGINE-COMPR | Air Compressor | 83749 | 10427 | 7500
500048458 | CLB-MP-HAUL-DT174 -ENGINE | Engine Assembly Caterpillar 3516B | 83749 | 10427 | 7500
500048457 | CLB-MP-HAUL-DT174 | DT174 Lubrication & Mechanical Services | 83749 | 83749 | 7500
500048456 | CLB-MP-HAUL-DT174 | Caterpillar 789D Haul Truck DT174 | 83749 | 83749 | 7500
500160249 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITRH | Air Tank Right | 82388 | 82388 | 7500
500160248 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK-AITLH | Air Tank Left | 82388 | 82388 | 7500
500147217 | CLB-MP-HAUL-DT173 -STRSYS-STACC | Steering Accumulator Rear | 34724 | 34724 | 7500
500147216 | CLB-MP-HAUL-DT173 -STRSYS-STACC | Steering Accumulator Middle | 34724 | 34724 | 7500
500147215 | CLB-MP-HAUL-DT173 -STRSYS-STACC | Steering Accumulator Front | 34724 | 34724 | 7500
500118552 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-AFRME | A Frame Housing | 82651 | 40795 | 7500
500117928 | CLB-MP-HAUL-DT173 -ELCTLV-LIGHT | Lighting Low Voltage | 82651 | 49785 | 7500
500117888 | CLB-MP-HAUL-DT173 -ELCTLV-HARNS | Electrical Harness | 82651 | 49785 | 7500
500117848 | CLB-MP-HAUL-DT173 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 82651 | 49785 | 7500
500117412 | CLB-MP-HAUL-DT173 -ELCTLV-LIGHT-AHSYS | AHS Lights | 82651 | 49785 | 7500
500117292 | CLB-MP-HAUL-DT173 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 82651 | 49785 | 7500
500111214 | CLB-MP-HAUL-DT173 -STRUCT-RAXHO | Rear Axle Housing | 82635 | 40795 | 7500
500110544 | CLB-MP-HAUL-DT173 -GRSYST | Grease Lubrication System | 82651 | 11964 | 7500
500102794 | CLB-MP-HAUL-DT173 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 82651 | 1534 | 7500
500100621 | CLB-MP-HAUL-DT173 -TRNSYS | DT173 Transmission System | 82651 | 51039 | 7500
500081398 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 82651 | 23913 | 7500
500081258 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 82651 | 18641 | 7500
500079431 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN | Suspension Service | 82651 | 12558 | 7500
500078497 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 82651 | 12585 | 7500
500078460 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 82651 | 12585 | 7500
500061424 | CLB-MP-HAUL-DT173 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 82651 | 12585 | 7500
500061394 | CLB-MP-HAUL-DT173 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 82651 | 12585 | 7500
500061060 | CLB-MP-HAUL-DT173 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 82651 | 12585 | 7500
500061059 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-ELECT | Chassis Electrical System | 82651 | 34724 | 7500
500061058 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-ELECT | Cabin Electrical System | 82651 | 55642 | 7500
500061057 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 82651 | 12585 | 7500
500061056 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 82651 | 12585 | 7500
500061055 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 82651 | 12585 | 7500
500061054 | CLB-MP-HAUL-DT173 -STRSYS-STHLF-STRHO | Steering System Hoses | 82651 | 12585 | 7500
500061053 | CLB-MP-HAUL-DT173 -STRSYS-STLTR-STBST | Ball Studs | 82651 | 82651 | 7500
500061052 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 82651 | 12585 | 7500
500061051 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 82651 | 12585 | 7500
500061050 | CLB-MP-HAUL-DT173 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 82651 | 12585 | 7500
500061049 | CLB-MP-HAUL-DT173 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 82651 | 12585 | 7500
500061048 | CLB-MP-HAUL-DT173 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 82651 | 12585 | 7500
500061047 | CLB-MP-HAUL-DT173 -BRKSYS-BRVRL | Brake Relay Valve | 82651 | 1534 | 7500
500061045 | CLB-MP-HAUL-DT173 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 82651 | 12585 | 7500
500061044 | CLB-MP-HAUL-DT173 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 82651 | 12585 | 7500
500060111 | CLB-MP-HAUL-DT173 -STRSYS-STTNK | Tank Steering | 82651 | 82651 | 7500
500053837 | CLB-MP-HAUL-DT173 -BRKSYS-BRVLV | Valve Brake | 82651 | 12585 | 7500
500049832 | CLB-MP-HAUL-DT173 -MANGMT-UMMMC | Mine Monitoring and Control | 82651 | 82651 | 7500
500049831 | CLB-MP-HAUL-DT173 -MANGMT-UMTRN | Power Train Management System | 82651 | 82651 | 7500
500049830 | CLB-MP-HAUL-DT173 -MANGMT-UMENG | Engine Management System | 82651 | 82651 | 7500
500049829 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 82651 | 12585 | 7500
500049828 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 82651 | 12553 | 7500
500049827 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 82651 | 12585 | 7500
500049826 | CLB-MP-HAUL-DT173 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 82651 | 12585 | 7500
500049823 | CLB-MP-HAUL-DT173 -STRUCT-TRAYS | Tray | 82651 | 25952 | 7500
500049822 | CLB-MP-HAUL-DT173 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 82651 | 12585 | 7500
500049821 | CLB-MP-HAUL-DT173 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 82651 | 12585 | 7500
500049820 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-TAGLK | Tag Link | 82651 | 12585 | 7500
500049819 | CLB-MP-HAUL-DT173 -STRUCT-CHASS-AFRME | A Frame Bearing | 82651 | 21240 | 7500
500049818 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-SBELT | Seat Belt | 82651 | 82651 | 7500
500049817 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-SEATS | Operators Seat | 82651 | 12585 | 7500
500049816 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 82651 | 82651 | 7500
500049815 | CLB-MP-HAUL-DT173 -STRUCT-CABIN-AIRCN | Air Conditioning System | 82651 | 1534 | 7500
500049814 | CLB-MP-HAUL-DT173 -STRUCT-CABIN | Operators Cabin | 82651 | 12585 | 7500
500049813 | CLB-MP-HAUL-DT173 -PNEUMC-START | Air Starter | 82651 | 1534 | 7500
500049812 | CLB-MP-HAUL-DT173 -PNEUMC-AIRDR | Air Drier | 82651 | 12585 | 7500
500049811 | CLB-MP-HAUL-DT173 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 82651 | 82651 | 7500
500049810 | CLB-MP-HAUL-DT173 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 82651 | 82651 | 7500
500049809 | CLB-MP-HAUL-DT173 -PNEUMC-PNTNK | No Not Use | 82651 | 82651 | 7500
500049808 | CLB-MP-HAUL-DT173 -GRSYST-ALCON | Auto Lube Controller | 82651 | 82651 | 7500
500049807 | CLB-MP-HAUL-DT173 -GRSYST-ALBPP | Auto Lube Pump | 82651 | 82651 | 7500
500049806 | CLB-MP-HAUL-DT173 -GRSYST-GRTNK | Auto Lube Resevoir | 82651 | 82651 | 7500
500049805 | CLB-MP-HAUL-DT173 -GRSYST-GRINJ | Auto Lube Injectors | 82651 | 82651 | 7500
500049804 | CLB-MP-HAUL-DT173 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 82651 | 16060 | 7500
500049803 | CLB-MP-HAUL-DT173 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 82651 | 12585 | 7500
500049802 | CLB-MP-HAUL-DT173 -HYDSYS-HOVLV | Valve Hoist | 82651 | 34724 | 7500
500049801 | CLB-MP-HAUL-DT173 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 82651 | 82651 | 7500
500049800 | CLB-MP-HAUL-DT173 -HYDSYS-HDTNK | Tank Hydraulic | 82651 | 82651 | 7500
500049799 | CLB-MP-HAUL-DT173 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 82651 | 12585 | 7500
500049798 | CLB-MP-HAUL-DT173 -HYDSYS-HOPMP | Pump Hoist | 82651 | 253 | 7500
500049797 | CLB-MP-HAUL-DT173 -HYDSYS | Hydraulic System | 82651 | 82651 | 7500
500049796 | CLB-MP-HAUL-DT173 -STRSYS-STCON-STCOL | Steering Column | 82651 | 55642 | 7500
500049795 | CLB-MP-HAUL-DT173 -STRSYS-STCON-STWHL | Steering Wheel | 82651 | 55642 | 7500
500049794 | CLB-MP-HAUL-DT173 -STRSYS-STLTR | Steering Linkages and Tie Rods | 82651 | 14071 | 7500
500049793 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 82651 | 12585 | 7500
500049792 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 82651 | 12585 | 7500
500049791 | CLB-MP-HAUL-DT173 -STRSYS-STACC-SACCF | Accumulator Steering Front | 82651 | 12585 | 7500
500049790 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 82651 | 12585 | 7500
500049789 | CLB-MP-HAUL-DT173 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 82651 | 15446 | 7500
500049788 | CLB-MP-HAUL-DT173 -STRSYS-STVLV | Valve Steering | 82651 | 12585 | 7500
500049787 | CLB-MP-HAUL-DT173 -STRSYS-STHMU | Steering HMU | 82651 | 12585 | 7500
500049786 | CLB-MP-HAUL-DT173 -STRSYS-STPMP | Pump Steering | 82651 | 14071 | 7500
500049785 | CLB-MP-HAUL-DT173 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 82651 | 12585 | 7500
500049784 | CLB-MP-HAUL-DT173 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 82651 | 12585 | 7500
500049783 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 82651 | 12585 | 7500
500049782 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 82651 | 12585 | 7500
500049781 | CLB-MP-HAUL-DT173 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 82651 | 12585 | 7500
500049780 | CLB-MP-HAUL-DT173 -BRKSYS-BACCM | Brake Accumulator | 82651 | 12585 | 7500
500049779 | CLB-MP-HAUL-DT173 -BRKSYS-BROCO | Brake Oil Cooler | 82651 | 82651 | 7500
500049778 | CLB-MP-HAUL-DT173 -BRKSYS-MERTR | Mechanical Retarder | 82651 | 55642 | 7500
500049777 | CLB-MP-HAUL-DT173 -BRKSYS-BRVTR | Valve Brake Treadle | 82651 | 55642 | 7500
500049776 | CLB-MP-HAUL-DT173 -BRKSYS-HYFPP | Pump Brake Control | 82651 | 1534 | 7500
500049775 | CLB-MP-HAUL-DT173 -BRKSYS-PRKPP | Pump Park Brake Release | 82651 | 82651 | 7500
500049774 | CLB-MP-HAUL-DT173 -BRKSYS-BRPMP | Pump Brake | 82651 | 82651 | 7500
500049773 | CLB-MP-HAUL-DT173 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 82651 | 82651 | 7500
500049772 | CLB-MP-HAUL-DT173 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 82651 | 82651 | 7500
500049771 | CLB-MP-HAUL-DT173 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 82651 | 82651 | 7500
500049770 | CLB-MP-HAUL-DT173 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 82651 | 82651 | 7500
500049769 | CLB-MP-HAUL-DT173 -BRKSYS-SRVBK | Service Brake | 82651 | 82651 | 7500
500049768 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 82651 | 82651 | 7500
500049767 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 82651 | 82651 | 7500
500049766 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 82651 | 5573 | 7500
500049765 | CLB-MP-HAUL-DT173 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 82651 | 4203 | 7500
500049764 | CLB-MP-HAUL-DT173 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 82651 | 12585 | 7500
500049763 | CLB-MP-HAUL-DT173 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 82651 | 714 | 7500
500049762 | CLB-MP-HAUL-DT173 -FDRSYS-DRLAX | Drive Line Axles | 82651 | 82651 | 7500
500049761 | CLB-MP-HAUL-DT173 -FDRSYS-DIFFL | Differential | 82651 | 17389 | 7500
500049760 | CLB-MP-HAUL-DT173 -FDRSYS-DRSHT | Transmission Drive Shaft | 82651 | 12585 | 7500
500049759 | CLB-MP-HAUL-DT173 -TRNSYS-TROLC | Oil Cooler Transmission | 82651 | 17964 | 7500
500049758 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 82651 | 17389 | 7500
500049757 | CLB-MP-HAUL-DT173 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 82651 | 6802 | 7500
500049756 | CLB-MP-HAUL-DT173 -TRNSYS-TRANS | Transmission | 82651 | 12585 | 7500
500049755 | CLB-MP-HAUL-DT173 -TRNSYS-TRQUE | Torque Converter | 82651 | 17389 | 7500
500049754 | CLB-MP-HAUL-DT173 -ELCTLV-CHARG-BATTY | Batteries | 82651 | 32152 | 7500
500049753 | CLB-MP-HAUL-DT173 -ELCTLV-CHARG-ALTER | Alternator 24V | 82651 | 1534 | 7500
500049752 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 82651 | 1534 | 7500
500049751 | CLB-MP-HAUL-DT173 -ENGINE-PMPDR | Pump Drive | 82651 | 8157 | 7500
500049750 | CLB-MP-HAUL-DT173 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 82651 | 12585 | 7500
500049749 | CLB-MP-HAUL-DT173 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 82651 | 1534 | 7500
500049748 | CLB-MP-HAUL-DT173 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 82651 | 1534 | 7500
500049747 | CLB-MP-HAUL-DT173 -ENGINE-FUSYS-FULTK | Fuel Tank | 82651 | 12585 | 7500
500049746 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-EXHST | Exhaust System | 82651 | 55642 | 7500
500049745 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-AFTER | Aftercooler | 82651 | 82651 | 7500
500049744 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 82651 | 1534 | 7500
500049743 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 82651 | 1534 | 7500
500049742 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 82651 | 1534 | 7500
500049741 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 82651 | 1534 | 7500
500049740 | CLB-MP-HAUL-DT173 -ENGINE-INTEX-AIRFL | Air Filtration System | 82651 | 82651 | 7500
500049739 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-THERM | Thermostats/Regulators | 82651 | 1534 | 7500
500049738 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-BELTS | Fan Belts Engine | 82651 | 82651 | 7500
500049737 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 82651 | 1534 | 7500
500049736 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-COFAN | Fan Cooling System | 82651 | 1534 | 7500
500049735 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-RADTR | Coolant Engine | 82651 | 34724 | 7400
500049734 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-RADTR | Radiator Engine | 82651 | 14063 | 7500
500049733 | CLB-MP-HAUL-DT173 -ENGINE-COSYS-WTRPP | Water Pump Engine | 82651 | 1534 | 7500
500049732 | CLB-MP-HAUL-DT173 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 82651 | 82651 | 7500
500049731 | CLB-MP-HAUL-DT173 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 82651 | 12585 | 7500
500049730 | CLB-MP-HAUL-DT173 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 82651 | 82651 | 7500
500049729 | CLB-MP-HAUL-DT173 -ENGINE-COMPR | Air Compressor | 82651 | 1534 | 7500
500046675 | CLB-MP-HAUL-DT173 -ENGINE | Engine Assembly Caterpillar 3516B | 82651 | 12585 | 7500
500046674 | CLB-MP-HAUL-DT173 | DT173 Lube & Mechanical Services | 82651 | 82651 | 7500
500046673 | CLB-MP-HAUL-DT173 | Caterpillar 789D Haul Truck, DT173 | 82651 | 82651 | 7500
500160247 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITRH | Air Tank Right | 92088 | 46179 | 7500
500160246 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK-AITLH | Air Tank Left | 92088 | 46179 | 7500
500147214 | CLB-MP-HAUL-DT172 -STRSYS-STACC | Steering Accumulator Rear | 22401 | 22401 | 7500
500147213 | CLB-MP-HAUL-DT172 -STRSYS-STACC | Steering Accumulator Middle | 22401 | 22401 | 7500
500147212 | CLB-MP-HAUL-DT172 -STRSYS-STACC | Steering Accumulator Front | 22401 | 22401 | 7500
500118551 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-AFRME | A Frame Housing | 92350 | 22401 | 7500
500117927 | CLB-MP-HAUL-DT172 -ELCTLV-LIGHT | Lighting Low Voltage | 92351 | 45552 | 7500
500117887 | CLB-MP-HAUL-DT172 -ELCTLV-HARNS | Electrical Harness | 92351 | 45552 | 7500
500117847 | CLB-MP-HAUL-DT172 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 92351 | 45552 | 7500
500117411 | CLB-MP-HAUL-DT172 -ELCTLV-LIGHT-AHSYS | AHS Lights | 92351 | 45552 | 7500
500117291 | CLB-MP-HAUL-DT172 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 92351 | 45552 | 7500
500111213 | CLB-MP-HAUL-DT172 -STRUCT-RAXHO | Rear Axle Housing | 92341 | 46442 | 7500
500110543 | CLB-MP-HAUL-DT172 -GRSYST | Grease Lubrication System | 92351 | 12975 | 7500
500102793 | CLB-MP-HAUL-DT172 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 92351 | 244 | 7500
500100620 | CLB-MP-HAUL-DT172 -TRNSYS | DT172 Transmission System | 92351 | 49297 | 7500
500081397 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 92351 | 22401 | 7500
500081257 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 92351 | 22401 | 7500
500079430 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN | Suspension Service | 92351 | 22391 | 7500
500078496 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 92351 | 22401 | 7500
500078459 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 92351 | 22401 | 7500
500061423 | CLB-MP-HAUL-DT172 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 92351 | 244 | 7500
500061393 | CLB-MP-HAUL-DT172 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 92351 | 244 | 7500
500061043 | CLB-MP-HAUL-DT172 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 92351 | 22401 | 7500
500061042 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-ELECT | Chassis Electrical System | 92351 | 46442 | 7500
500061041 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-ELECT | Cabin Electrical System | 92351 | 92351 | 7500
500061040 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 92351 | 22401 | 7500
500061039 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 92351 | 22401 | 7500
500061038 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 92351 | 22401 | 7500
500061037 | CLB-MP-HAUL-DT172 -STRSYS-STHLF-STRHO | Steering System Hoses | 92351 | 22401 | 7500
500061036 | CLB-MP-HAUL-DT172 -STRSYS-STLTR-STBST | Ball Studs | 92351 | 92351 | 7500
500061035 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 92351 | 22401 | 7500
500061034 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 92351 | 22401 | 7500
500061033 | CLB-MP-HAUL-DT172 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 92351 | 22401 | 7500
500061032 | CLB-MP-HAUL-DT172 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 92351 | 244 | 7500
500061031 | CLB-MP-HAUL-DT172 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 92351 | 244 | 7500
500061030 | CLB-MP-HAUL-DT172 -BRKSYS-BRVRL | Brake Relay Valve | 92351 | 244 | 7500
500061028 | CLB-MP-HAUL-DT172 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 92351 | 22401 | 7500
500061027 | CLB-MP-HAUL-DT172 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 92351 | 22401 | 7500
500060110 | CLB-MP-HAUL-DT172 -STRSYS-STTNK | Tank Steering | 92351 | 68444 | 7500
500053836 | CLB-MP-HAUL-DT172 -BRKSYS-BRVLV | Valve Brake | 92351 | 244 | 7500
500049728 | CLB-MP-HAUL-DT172 -MANGMT-UMMMC | Mine Monitoring and Control | 92351 | 92351 | 7500
500049727 | CLB-MP-HAUL-DT172 -MANGMT-UMTRN | Power Train Management System | 92351 | 92351 | 7500
500049726 | CLB-MP-HAUL-DT172 -MANGMT-UMENG | Engine Management System | 92351 | 92351 | 7500
500049725 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 92351 | 400 | 7500
500049724 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 92351 | 22401 | 7500
500049723 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 92351 | 244 | 7500
500049722 | CLB-MP-HAUL-DT172 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 92351 | 11680 | 7500
500049719 | CLB-MP-HAUL-DT172 -STRUCT-TRAYS | Tray | 92350 | 92350 | 7500
500049718 | CLB-MP-HAUL-DT172 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 92351 | 244 | 7500
500049717 | CLB-MP-HAUL-DT172 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 92351 | 2439 | 7500
500049716 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-TAGLK | Tag Link | 92350 | 244 | 7500
500049715 | CLB-MP-HAUL-DT172 -STRUCT-CHASS-AFRME | A Frame Bearing | 92351 | 244 | 7500
500049714 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-SBELT | Seat Belt | 92351 | 46739 | 7500
500049713 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-SEATS | Operators Seat | 92351 | 9850 | 7500
500049712 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 92351 | 92351 | 7500
500049711 | CLB-MP-HAUL-DT172 -STRUCT-CABIN-AIRCN | Air Conditioning System | 92351 | 22401 | 7500
500049710 | CLB-MP-HAUL-DT172 -STRUCT-CABIN | Operators Cabin | 92351 | 22401 | 7500
500049709 | CLB-MP-HAUL-DT172 -PNEUMC-START | Air Starter | 92351 | 244 | 7500
500049708 | CLB-MP-HAUL-DT172 -PNEUMC-AIRDR | Air Drier | 92351 | 244 | 7500
500049707 | CLB-MP-HAUL-DT172 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 92351 | 92351 | 7500
500049706 | CLB-MP-HAUL-DT172 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 92351 | 92351 | 7500
500049705 | CLB-MP-HAUL-DT172 -PNEUMC-PNTNK | No Not Use | 92351 | 46442 | 7500
500049704 | CLB-MP-HAUL-DT172 -GRSYST-ALCON | Auto Lube Controller | 92351 | 92351 | 7500
500049703 | CLB-MP-HAUL-DT172 -GRSYST-ALBPP | Auto Lube Pump | 92351 | 68444 | 7500
500049702 | CLB-MP-HAUL-DT172 -GRSYST-GRTNK | Auto Lube Resevoir | 92351 | 92351 | 7500
500049701 | CLB-MP-HAUL-DT172 -GRSYST-GRINJ | Auto Lube Injectors | 92351 | 92351 | 7500
500049700 | CLB-MP-HAUL-DT172 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 92351 | 13766 | 7500
500049699 | CLB-MP-HAUL-DT172 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 92351 | 13766 | 7500
500049698 | CLB-MP-HAUL-DT172 -HYDSYS-HOVLV | Valve Hoist | 92351 | 34482 | 7500
500049697 | CLB-MP-HAUL-DT172 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 92351 | 92351 | 7500
500049696 | CLB-MP-HAUL-DT172 -HYDSYS-HDTNK | Tank Hydraulic | 92351 | 68444 | 7500
500049695 | CLB-MP-HAUL-DT172 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 92351 | 22401 | 7500
500049694 | CLB-MP-HAUL-DT172 -HYDSYS-HOPMP | Pump Hoist | 92351 | 12975 | 7500
500049693 | CLB-MP-HAUL-DT172 -HYDSYS | Hydraulic System | 92351 | 92351 | 7500
500049692 | CLB-MP-HAUL-DT172 -STRSYS-STCON-STCOL | Steering Column | 92351 | 92316 | 7500
500049691 | CLB-MP-HAUL-DT172 -STRSYS-STCON-STWHL | Steering Wheel | 92351 | 92316 | 7500
500049690 | CLB-MP-HAUL-DT172 -STRSYS-STLTR | Steering Linkages and Tie Rods | 92351 | 22401 | 7500
500049689 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 92351 | 22401 | 7500
500049688 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 92351 | 22401 | 7500
500049687 | CLB-MP-HAUL-DT172 -STRSYS-STACC-SACCF | Accumulator Steering Front | 92351 | 22401 | 7500
500049686 | CLB-MP-HAUL-DT172 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 92351 | 244 | 7500
500049685 | CLB-MP-HAUL-DT172 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 92351 | 244 | 7500
500049684 | CLB-MP-HAUL-DT172 -STRSYS-STVLV | Valve Steering | 92351 | 3470 | 7500
500049683 | CLB-MP-HAUL-DT172 -STRSYS-STHMU | Steering HMU | 92351 | 11680 | 7500
500049682 | CLB-MP-HAUL-DT172 -STRSYS-STPMP | Pump Steering | 92351 | 11680 | 7500
500049681 | CLB-MP-HAUL-DT172 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 92351 | 9073 | 7500
500049680 | CLB-MP-HAUL-DT172 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 92351 | 9073 | 7500
500049679 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 92351 | 244 | 7500
500049678 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 92351 | 244 | 7500
500049677 | CLB-MP-HAUL-DT172 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 92351 | 244 | 7500
500049676 | CLB-MP-HAUL-DT172 -BRKSYS-BACCM | Brake Accumulator | 92351 | 244 | 7500
500049675 | CLB-MP-HAUL-DT172 -BRKSYS-BROCO | Brake Oil Cooler | 92351 | 68444 | 7500
500049674 | CLB-MP-HAUL-DT172 -BRKSYS-MERTR | Mechanical Retarder | 92351 | 42692 | 7500
500049673 | CLB-MP-HAUL-DT172 -BRKSYS-BRVTR | Valve Brake Treadle | 92351 | 68444 | 7500
500049672 | CLB-MP-HAUL-DT172 -BRKSYS-HYFPP | Pump Brake Control | 92350 | 5598 | 7500
500049671 | CLB-MP-HAUL-DT172 -BRKSYS-PRKPP | Pump Park Brake Release | 92351 | 92351 | 7500
500049670 | CLB-MP-HAUL-DT172 -BRKSYS-BRPMP | Pump Brake | 92351 | 92351 | 7500
500049669 | CLB-MP-HAUL-DT172 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 92351 | 68455 | 7500
500049668 | CLB-MP-HAUL-DT172 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 92351 | 68455 | 7500
500049667 | CLB-MP-HAUL-DT172 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 92351 | 68444 | 7500
500049666 | CLB-MP-HAUL-DT172 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 92351 | 68444 | 7500
500049665 | CLB-MP-HAUL-DT172 -BRKSYS-SRVBK | Service Brake | 92351 | 92351 | 7500
500049664 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 92351 | 92351 | 7500
500049663 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 92351 | 92351 | 7500
500049662 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 92351 | 9073 | 7500
500049661 | CLB-MP-HAUL-DT172 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 92330 | 244 | 7500
500049660 | CLB-MP-HAUL-DT172 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 92351 | 244 | 7500
500049659 | CLB-MP-HAUL-DT172 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 92351 | 244 | 7500
500049658 | CLB-MP-HAUL-DT172 -FDRSYS-DRLAX | Drive Line Axles | 92351 | 92351 | 7500
500049657 | CLB-MP-HAUL-DT172 -FDRSYS-DIFFL | Differential | 92351 | 244 | 7500
500049656 | CLB-MP-HAUL-DT172 -FDRSYS-DRSHT | Transmission Drive Shaft | 92351 | 12975 | 7500
500049655 | CLB-MP-HAUL-DT172 -TRNSYS-TROLC | Oil Cooler Transmission | 92351 | 244 | 7500
500049654 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 92351 | 9072 | 7500
500049653 | CLB-MP-HAUL-DT172 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 92351 | 244 | 7500
500049652 | CLB-MP-HAUL-DT172 -TRNSYS-TRANS | Transmission | 92351 | 244 | 7500
500049651 | CLB-MP-HAUL-DT172 -TRNSYS-TRQUE | Torque Converter | 92351 | 244 | 7500
500049650 | CLB-MP-HAUL-DT172 -ELCTLV-CHARG-BATTY | Batteries | 92351 | 10939 | 7500
500049649 | CLB-MP-HAUL-DT172 -ELCTLV-CHARG-ALTER | Alternator 24V | 92351 | 244 | 7500
500049648 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 92351 | 244 | 7500
500049647 | CLB-MP-HAUL-DT172 -ENGINE-PMPDR | Pump Drive | 92351 | 244 | 7500
500049646 | CLB-MP-HAUL-DT172 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 92351 | 244 | 7500
500049645 | CLB-MP-HAUL-DT172 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 92351 | 244 | 7500
500049644 | CLB-MP-HAUL-DT172 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 92351 | 244 | 7500
500049643 | CLB-MP-HAUL-DT172 -ENGINE-FUSYS-FULTK | Fuel Tank | 92351 | 22401 | 7500
500049642 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-EXHST | Exhaust System | 92351 | 92351 | 7500
500049641 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-AFTER | Aftercooler | 92351 | 68444 | 7500
500049640 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 92351 | 244 | 7500
500049639 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 92351 | 244 | 7500
500049638 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 92351 | 244 | 7500
500049637 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 92351 | 244 | 7500
500049636 | CLB-MP-HAUL-DT172 -ENGINE-INTEX-AIRFL | Air Filtration System | 92351 | 92351 | 7500
500049635 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-THERM | Thermostats/Regulators | 92351 | 244 | 7500
500049634 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-BELTS | Fan Belts Engine | 92351 | 92351 | 7500
500049633 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 92351 | 244 | 7500
500049632 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-COFAN | Fan Cooling System | 92351 | 244 | 7500
500049631 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-RADTR | Coolant Engine | 92350 | 68444 | 7400
500049630 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-RADTR | Radiator Engine | 92351 | 244 | 7500
500049629 | CLB-MP-HAUL-DT172 -ENGINE-COSYS-WTRPP | Water Pump Engine | 92351 | 244 | 7500
500049628 | CLB-MP-HAUL-DT172 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 92351 | 68455 | 7500
500049627 | CLB-MP-HAUL-DT172 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 92351 | 244 | 7500
500049626 | CLB-MP-HAUL-DT172 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 92351 | 68444 | 7500
500049625 | CLB-MP-HAUL-DT172 -ENGINE-COMPR | Air Compressor | 92351 | 244 | 7500
500046670 | CLB-MP-HAUL-DT172 -ENGINE | Engine Assembly Caterpillar 3516B | 92351 | 244 | 7500
500046669 | CLB-MP-HAUL-DT172 | DT172 Lube & Mechanical Services | 92351 | 92351 | 7500
500046668 | CLB-MP-HAUL-DT172 | Caterpillar 789D Haul Truck, DT172 | 92351 | 92351 | 7500
500160245 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITRH | Air Tank Right | 89925 | 89925 | 7500
500160244 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK-AITLH | Air Tank Left | 89925 | 89925 | 7500
500147210 | CLB-MP-HAUL-DT171 -STRSYS-STACC | Steering Accumulator Rear | 27381 | 27381 | 7500
500147209 | CLB-MP-HAUL-DT171 -STRSYS-STACC | Steering Accumulator Middle | 27381 | 27381 | 7500
500147208 | CLB-MP-HAUL-DT171 -STRSYS-STACC | Steering Accumulator Front | 27381 | 27381 | 7500
500118550 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-AFRME | A Frame Housing | 90182 | 90182 | 7500
500117926 | CLB-MP-HAUL-DT171 -ELCTLV-LIGHT | Lighting Low Voltage | 90182 | 43380 | 7500
500117886 | CLB-MP-HAUL-DT171 -ELCTLV-HARNS | Electrical Harness | 90182 | 43380 | 7500
500117846 | CLB-MP-HAUL-DT171 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 90182 | 43380 | 7500
500117410 | CLB-MP-HAUL-DT171 -ELCTLV-LIGHT-AHSYS | AHS Lights | 90182 | 43380 | 7500
500117290 | CLB-MP-HAUL-DT171 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 90182 | 43380 | 7500
500111212 | CLB-MP-HAUL-DT171 -STRUCT-RAXHO | Rear Axle Housing | 90182 | 50046 | 7500
500110542 | CLB-MP-HAUL-DT171 -GRSYST | Grease Lubrication System | 90182 | 14995 | 7500
500102792 | CLB-MP-HAUL-DT171 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 90182 | 3449 | 7500
500100619 | CLB-MP-HAUL-DT171 -TRNSYS | DT171 Transmission System | 90182 | 39094 | 7500
500081396 | CLB-MP-HAUL-DT171 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 90182 | 3449 | 7500
500081256 | CLB-MP-HAUL-DT171 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 90182 | 3449 | 7500
500079429 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN | Suspension Service | 90182 | 27315 | 7500
500078495 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 90182 | 3445 | 7500
500078458 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 90182 | 3445 | 7500
500061422 | CLB-MP-HAUL-DT171 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 90182 | 3449 | 7500
500061392 | CLB-MP-HAUL-DT171 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 90182 | 3449 | 7500
500061026 | CLB-MP-HAUL-DT171 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 90182 | 45613 | 7500
500061025 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-ELECT | Chassis Electrical System | 90182 | 27381 | 7500
500061024 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-ELECT | Cabin Electrical System | 90182 | 90182 | 7500
500061023 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 90182 | 90182 | 7500
500061022 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 90182 | 52656 | 7500
500061021 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 90182 | 52656 | 7500
500061020 | CLB-MP-HAUL-DT171 -STRSYS-STHLF-STRHO | Steering System Hoses | 90182 | 3445 | 7500
500061019 | CLB-MP-HAUL-DT171 -STRSYS-STLTR-STBST | Ball Studs | 90182 | 90182 | 7500
500061018 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 90182 | 3445 | 7500
500061017 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 90182 | 3445 | 7500
500061016 | CLB-MP-HAUL-DT171 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 90182 | 3449 | 7500
500061015 | CLB-MP-HAUL-DT171 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 90182 | 66505 | 7500
500061014 | CLB-MP-HAUL-DT171 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 90182 | 3449 | 7500
500061013 | CLB-MP-HAUL-DT171 -BRKSYS-BRVRL | Brake Relay Valve | 90182 | 3449 | 7500
500061011 | CLB-MP-HAUL-DT171 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 90182 | 3449 | 7500
500061010 | CLB-MP-HAUL-DT171 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 90182 | 3449 | 7500
500060109 | CLB-MP-HAUL-DT171 -STRSYS-STTNK | Tank Steering | 90182 | 66505 | 7500
500053835 | CLB-MP-HAUL-DT171 -BRKSYS-BRVLV | Valve Brake | 90182 | 3449 | 7500
500049624 | CLB-MP-HAUL-DT171 -MANGMT-UMMMC | Mine Monitoring and Control | 90182 | 90182 | 7500
500049623 | CLB-MP-HAUL-DT171 -MANGMT-UMTRN | Power Train Management System | 90182 | 90182 | 7500
500049622 | CLB-MP-HAUL-DT171 -MANGMT-UMENG | Engine Management System | 90182 | 90182 | 7500
500049621 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 90182 | 15620 | 7500
500049620 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 90182 | 15013 | 7500
500049619 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 90182 | 3449 | 7500
500049618 | CLB-MP-HAUL-DT171 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 90182 | 20246 | 7500
500049615 | CLB-MP-HAUL-DT171 -STRUCT-TRAYS | Tray | 90182 | 90182 | 7500
500049614 | CLB-MP-HAUL-DT171 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 90182 | 3449 | 7500
500049613 | CLB-MP-HAUL-DT171 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 90182 | 27381 | 7500
500049612 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-TAGLK | Tag Link | 90182 | 3449 | 7500
500049611 | CLB-MP-HAUL-DT171 -STRUCT-CHASS-AFRME | A Frame Bearing | 90182 | 36963 | 7500
500049610 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-SBELT | Seat Belt | 90182 | 46212 | 7500
500049609 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-SEATS | Operators Seat | 90182 | 14995 | 7500
500049608 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 90182 | 90182 | 7500
500049607 | CLB-MP-HAUL-DT171 -STRUCT-CABIN-AIRCN | Air Conditioning System | 90182 | 8268 | 7500
500049606 | CLB-MP-HAUL-DT171 -STRUCT-CABIN | Operators Cabin | 90182 | 27381 | 7500
500049605 | CLB-MP-HAUL-DT171 -PNEUMC-START | Air Starter | 90182 | 8268 | 7500
500049604 | CLB-MP-HAUL-DT171 -PNEUMC-AIRDR | Air Drier | 90182 | 27381 | 7500
500049603 | CLB-MP-HAUL-DT171 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 90182 | 90182 | 7500
500049602 | CLB-MP-HAUL-DT171 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 90182 | 90182 | 7500
500049601 | CLB-MP-HAUL-DT171 -PNEUMC-PNTNK | No Not Use | 90182 | 90182 | 7500
500049600 | CLB-MP-HAUL-DT171 -GRSYST-ALCON | Auto Lube Controller | 90182 | 90182 | 7500
500049599 | CLB-MP-HAUL-DT171 -GRSYST-ALBPP | Auto Lube Pump | 90182 | 66505 | 7500
500049598 | CLB-MP-HAUL-DT171 -GRSYST-GRTNK | Auto Lube Resevoir | 90182 | 90182 | 7500
500049597 | CLB-MP-HAUL-DT171 -GRSYST-GRINJ | Auto Lube Injectors | 90182 | 90182 | 7500
500049596 | CLB-MP-HAUL-DT171 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 90182 | 27381 | 7500
500049595 | CLB-MP-HAUL-DT171 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 90182 | 27381 | 7500
500049594 | CLB-MP-HAUL-DT171 -HYDSYS-HOVLV | Valve Hoist | 90182 | 32458 | 7500
500049593 | CLB-MP-HAUL-DT171 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 90182 | 90182 | 7500
500049592 | CLB-MP-HAUL-DT171 -HYDSYS-HDTNK | Tank Hydraulic | 90182 | 66505 | 7500
500049591 | CLB-MP-HAUL-DT171 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 90182 | 27381 | 7500
500049590 | CLB-MP-HAUL-DT171 -HYDSYS-HOPMP | Pump Hoist | 90182 | 3449 | 7500
500049589 | CLB-MP-HAUL-DT171 -HYDSYS | Hydraulic System | 90182 | 90182 | 7500
500049588 | CLB-MP-HAUL-DT171 -STRSYS-STCON-STCOL | Steering Column | 90182 | 40594 | 7500
500049587 | CLB-MP-HAUL-DT171 -STRSYS-STCON-STWHL | Steering Wheel | 90182 | 90182 | 7500
500049586 | CLB-MP-HAUL-DT171 -STRSYS-STLTR | Steering Linkages and Tie Rods | 90182 | 11678 | 7500
500049585 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 90182 | 3445 | 7500
500049584 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 90182 | 3445 | 7500
500049583 | CLB-MP-HAUL-DT171 -STRSYS-STACC-SACCF | Accumulator Steering Front | 90182 | 3445 | 7500
500049582 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 90182 | 11678 | 7500
500049581 | CLB-MP-HAUL-DT171 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 90182 | 11678 | 7500
500049580 | CLB-MP-HAUL-DT171 -STRSYS-STVLV | Valve Steering | 90182 | 27381 | 7500
500049579 | CLB-MP-HAUL-DT171 -STRSYS-STHMU | Steering HMU | 90182 | 11678 | 7500
500049578 | CLB-MP-HAUL-DT171 -STRSYS-STPMP | Pump Steering | 90182 | 11678 | 7500
500049577 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 90182 | 15607 | 7500
500049576 | CLB-MP-HAUL-DT171 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 90182 | 15607 | 7500
500049575 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 90182 | 3449 | 7500
500049574 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 90182 | 3449 | 7500
500049573 | CLB-MP-HAUL-DT171 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 90182 | 3449 | 7500
500049572 | CLB-MP-HAUL-DT171 -BRKSYS-BACCM | Brake Accumulator | 90182 | 3449 | 7500
500049571 | CLB-MP-HAUL-DT171 -BRKSYS-BROCO | Brake Oil Cooler | 90182 | 66505 | 7500
500049570 | CLB-MP-HAUL-DT171 -BRKSYS-MERTR | Mechanical Retarder | 90182 | 90182 | 7500
500049569 | CLB-MP-HAUL-DT171 -BRKSYS-BRVTR | Valve Brake Treadle | 90182 | 66501 | 7500
500049568 | CLB-MP-HAUL-DT171 -BRKSYS-HYFPP | Pump Brake Control | 90182 | 15607 | 7500
500049567 | CLB-MP-HAUL-DT171 -BRKSYS-PRKPP | Pump Park Brake Release | 90182 | 90182 | 7500
500049566 | CLB-MP-HAUL-DT171 -BRKSYS-BRPMP | Pump Brake | 90182 | 90182 | 7500
500049565 | CLB-MP-HAUL-DT171 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 90182 | 90182 | 7500
500049564 | CLB-MP-HAUL-DT171 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 90182 | 90182 | 7500
500049563 | CLB-MP-HAUL-DT171 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 90182 | 66505 | 7500
500049562 | CLB-MP-HAUL-DT171 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 90182 | 66505 | 7500
500049561 | CLB-MP-HAUL-DT171 -BRKSYS-SRVBK | Service Brake | 90182 | 90182 | 7500
500049560 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 90182 | 90182 | 7500
500049559 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 90182 | 90182 | 7500
500049558 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 90182 | 3449 | 7500
500049557 | CLB-MP-HAUL-DT171 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 90182 | 3449 | 7500
500049556 | CLB-MP-HAUL-DT171 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 90182 | 3449 | 7500
500049555 | CLB-MP-HAUL-DT171 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 90182 | 3449 | 7500
500049554 | CLB-MP-HAUL-DT171 -FDRSYS-DRLAX | Drive Line Axles | 90182 | 90182 | 7500
500049553 | CLB-MP-HAUL-DT171 -FDRSYS-DIFFL | Differential | 90182 | 3449 | 7500
500049552 | CLB-MP-HAUL-DT171 -FDRSYS-DRSHT | Transmission Drive Shaft | 90182 | 3449 | 7500
500049551 | CLB-MP-HAUL-DT171 -TRNSYS-TROLC | Oil Cooler Transmission | 90182 | 3449 | 7500
500049550 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 90182 | 3449 | 7500
500049549 | CLB-MP-HAUL-DT171 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 90182 | 3449 | 7500
500049548 | CLB-MP-HAUL-DT171 -TRNSYS-TRANS | Transmission | 90182 | 3449 | 7500
500049547 | CLB-MP-HAUL-DT171 -TRNSYS-TRQUE | Torque Converter | 90182 | 3449 | 7500
500049546 | CLB-MP-HAUL-DT171 -ELCTLV-CHARG-BATTY | Batteries | 90182 | 90182 | 7500
500049545 | CLB-MP-HAUL-DT171 -ELCTLV-CHARG-ALTER | Alternator 24V | 90182 | 8268 | 7500
500049544 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 90182 | 3445 | 7500
500049543 | CLB-MP-HAUL-DT171 -ENGINE-PMPDR | Pump Drive | 90182 | 14363 | 7500
500049542 | CLB-MP-HAUL-DT171 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 90182 | 8268 | 7500
500049541 | CLB-MP-HAUL-DT171 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 90182 | 8268 | 7500
500049540 | CLB-MP-HAUL-DT171 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 90182 | 8268 | 7500
500049539 | CLB-MP-HAUL-DT171 -ENGINE-FUSYS-FULTK | Fuel Tank | 90182 | 34351 | 7500
500049538 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-EXHST | Exhaust System | 90182 | 31795 | 7500
500049537 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-AFTER | Aftercooler | 90182 | 31795 | 7500
500049536 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 90182 | 8268 | 7500
500049535 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 90182 | 8268 | 7500
500049534 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 90182 | 8268 | 7500
500049533 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 90182 | 8268 | 7500
500049532 | CLB-MP-HAUL-DT171 -ENGINE-INTEX-AIRFL | Air Filtration System | 90182 | 90182 | 7500
500049531 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-THERM | Thermostats/Regulators | 90182 | 8268 | 7500
500049530 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-BELTS | Fan Belts Engine | 90182 | 31795 | 7500
500049529 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 90182 | 8268 | 7500
500049528 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-COFAN | Fan Cooling System | 90182 | 8268 | 7500
500049527 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-RADTR | Coolant Engine | 90182 | 27381 | 7400
500049526 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-RADTR | Radiator Engine | 90182 | 3449 | 7500
500049525 | CLB-MP-HAUL-DT171 -ENGINE-COSYS-WTRPP | Water Pump Engine | 90182 | 8268 | 7500
500049524 | CLB-MP-HAUL-DT171 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 90182 | 31795 | 7500
500049523 | CLB-MP-HAUL-DT171 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 90182 | 8268 | 7500
500049522 | CLB-MP-HAUL-DT171 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 90182 | 31795 | 7500
500049521 | CLB-MP-HAUL-DT171 -ENGINE-COMPR | Air Compressor | 90182 | 8268 | 7500
500046624 | CLB-MP-HAUL-DT171 -ENGINE | Engine Assembly Caterpillar 3516B | 90182 | 8268 | 7500
500046623 | CLB-MP-HAUL-DT171 | DT171 Lube & Mechanical Services | 90182 | 90182 | 7500
500046622 | CLB-MP-HAUL-DT171 | Caterpillar 789D Haul Truck, DT171 | 90182 | 90182 | 7500
500160243 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITRH | Air Tank Right | 90894 | 90894 | 7500
500160242 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK-AITLH | Air Tank Left | 90894 | 90894 | 7500
500147206 | CLB-MP-HAUL-DT170 -STRSYS-STACC | Steering Accumulator Rear | 21744 | 21744 | 7500
500147205 | CLB-MP-HAUL-DT170 -STRSYS-STACC | Steering Accumulator Middle | 21744 | 21744 | 7500
500147204 | CLB-MP-HAUL-DT170 -STRSYS-STACC | Steering Accumulator Front | 21744 | 21744 | 7500
500118549 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-AFRME | A Frame Housing | 91119 | 21744 | 7500
500117925 | CLB-MP-HAUL-DT170 -ELCTLV-LIGHT | Lighting Low Voltage | 91119 | 46751 | 7500
500117885 | CLB-MP-HAUL-DT170 -ELCTLV-HARNS | Electrical Harness | 91119 | 46751 | 7500
500117845 | CLB-MP-HAUL-DT170 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 91119 | 46751 | 7500
500117409 | CLB-MP-HAUL-DT170 -ELCTLV-LIGHT-AHSYS | AHS Lights | 91119 | 46751 | 7500
500117289 | CLB-MP-HAUL-DT170 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 91119 | 46751 | 7500
500111211 | CLB-MP-HAUL-DT170 -STRUCT-RAXHO | Rear Axle Housing | 91119 | 45447 | 7500
500110541 | CLB-MP-HAUL-DT170 -GRSYST | Grease Lubrication System | 91119 | 37796 | 7500
500102791 | CLB-MP-HAUL-DT170 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 91119 | 21744 | 7500
500100618 | CLB-MP-HAUL-DT170 -TRNSYS | DT170 Transmission System | 91119 | 45447 | 7500
500081395 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 91119 | 21125 | 7500
500081255 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 91119 | 21125 | 7500
500079428 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN | Suspension Service | 91119 | 21730 | 7500
500078494 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 91119 | 21744 | 7500
500078457 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 91119 | 21744 | 7500
500061421 | CLB-MP-HAUL-DT170 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 91119 | 21744 | 7500
500061391 | CLB-MP-HAUL-DT170 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 91119 | 21744 | 7500
500061009 | CLB-MP-HAUL-DT170 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 91119 | 21744 | 7500
500061008 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-ELECT | Chassis Electrical System | 91119 | 45447 | 7500
500061007 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-ELECT | Cabin Electrical System | 91119 | 91119 | 7500
500061006 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 91119 | 21744 | 7500
500061005 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 91119 | 21744 | 7500
500061004 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 91119 | 21744 | 7500
500061003 | CLB-MP-HAUL-DT170 -STRSYS-STHLF-STRHO | Steering System Hoses | 91119 | 21744 | 7500
500061002 | CLB-MP-HAUL-DT170 -STRSYS-STLTR-STBST | Ball Studs | 91119 | 91119 | 7500
500061001 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 91119 | 21744 | 7500
500061000 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 91119 | 21744 | 7500
500060999 | CLB-MP-HAUL-DT170 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 91119 | 21744 | 7500
500060998 | CLB-MP-HAUL-DT170 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 91119 | 21744 | 7500
500060997 | CLB-MP-HAUL-DT170 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 91119 | 21744 | 7500
500060996 | CLB-MP-HAUL-DT170 -BRKSYS-BRVRL | Brake Relay Valve | 91119 | 24132 | 7500
500060994 | CLB-MP-HAUL-DT170 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 91119 | 21744 | 7500
500060993 | CLB-MP-HAUL-DT170 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 91119 | 21744 | 7500
500060108 | CLB-MP-HAUL-DT170 -STRSYS-STTNK | Tank Steering | 91119 | 68128 | 7500
500053834 | CLB-MP-HAUL-DT170 -BRKSYS-BRVLV | Valve Brake | 91119 | 21744 | 7500
500049520 | CLB-MP-HAUL-DT170 -MANGMT-UMMMC | Mine Monitoring and Control | 91119 | 91119 | 7500
500049519 | CLB-MP-HAUL-DT170 -MANGMT-UMTRN | Power Train Management System | 91119 | 91119 | 7500
500049518 | CLB-MP-HAUL-DT170 -MANGMT-UMENG | Engine Management System | 91119 | 91119 | 7500
500049517 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 91119 | 21744 | 7500
500049516 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 91119 | 21744 | 7500
500049515 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 91119 | 2276 | 7500
500049514 | CLB-MP-HAUL-DT170 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 91119 | 24782 | 7500
500049511 | CLB-MP-HAUL-DT170 -STRUCT-TRAYS | Tray | 91119 | 26948 | 7500
500049510 | CLB-MP-HAUL-DT170 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 91119 | 24782 | 7500
500049509 | CLB-MP-HAUL-DT170 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 91119 | 24782 | 7500
500049508 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-TAGLK | Tag Link | 91119 | 21744 | 7500
500049507 | CLB-MP-HAUL-DT170 -STRUCT-CHASS-AFRME | A Frame Bearing | 91119 | 21744 | 7500
500049506 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-SBELT | Seat Belt | 91119 | 91119 | 7500
500049505 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-SEATS | Operators Seat | 91119 | 29811 | 7500
500049504 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 91119 | 91119 | 7500
500049503 | CLB-MP-HAUL-DT170 -STRUCT-CABIN-AIRCN | Air Conditioning System | 91119 | 14869 | 7500
500049502 | CLB-MP-HAUL-DT170 -STRUCT-CABIN | Operators Cabin | 91119 | 21744 | 7500
500049501 | CLB-MP-HAUL-DT170 -PNEUMC-START | Air Starter | 91119 | 6570 | 7500
500049500 | CLB-MP-HAUL-DT170 -PNEUMC-AIRDR | Air Drier | 91119 | 21744 | 7500
500049499 | CLB-MP-HAUL-DT170 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 91119 | 91119 | 7500
500049498 | CLB-MP-HAUL-DT170 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 91119 | 91119 | 7500
500049497 | CLB-MP-HAUL-DT170 -PNEUMC-PNTNK | No Not Use | 91119 | 91119 | 7500
500049496 | CLB-MP-HAUL-DT170 -GRSYST-ALCON | Auto Lube Controller | 91119 | 91119 | 7500
500049495 | CLB-MP-HAUL-DT170 -GRSYST-ALBPP | Auto Lube Pump | 91119 | 91119 | 7500
500049494 | CLB-MP-HAUL-DT170 -GRSYST-GRTNK | Auto Lube Resevoir | 91119 | 91119 | 7500
500049493 | CLB-MP-HAUL-DT170 -GRSYST-GRINJ | Auto Lube Injectors | 91119 | 91119 | 7500
500049492 | CLB-MP-HAUL-DT170 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 91119 | 21744 | 7500
500049491 | CLB-MP-HAUL-DT170 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 91119 | 21744 | 7500
500049490 | CLB-MP-HAUL-DT170 -HYDSYS-HOVLV | Valve Hoist | 91119 | 33938 | 7500
500049489 | CLB-MP-HAUL-DT170 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 91119 | 91119 | 7500
500049488 | CLB-MP-HAUL-DT170 -HYDSYS-HDTNK | Tank Hydraulic | 91119 | 68128 | 7500
500049487 | CLB-MP-HAUL-DT170 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 91119 | 21744 | 7500
500049486 | CLB-MP-HAUL-DT170 -HYDSYS-HOPMP | Pump Hoist | 91119 | 29811 | 7500
500049485 | CLB-MP-HAUL-DT170 -HYDSYS | Hydraulic System | 91119 | 91119 | 7500
500049484 | CLB-MP-HAUL-DT170 -STRSYS-STCON-STCOL | Steering Column | 91119 | 91119 | 7500
500049483 | CLB-MP-HAUL-DT170 -STRSYS-STCON-STWHL | Steering Wheel | 91119 | 91119 | 7500
500049482 | CLB-MP-HAUL-DT170 -STRSYS-STLTR | Steering Linkages and Tie Rods | 91119 | 29788 | 7500
500049481 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 91119 | 21744 | 7500
500049480 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 91119 | 21744 | 7500
500049479 | CLB-MP-HAUL-DT170 -STRSYS-STACC-SACCF | Accumulator Steering Front | 91119 | 21744 | 7500
500049478 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 91119 | 13406 | 7500
500049477 | CLB-MP-HAUL-DT170 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 91119 | 13406 | 7500
500049476 | CLB-MP-HAUL-DT170 -STRSYS-STVLV | Valve Steering | 91119 | 29788 | 7500
500049475 | CLB-MP-HAUL-DT170 -STRSYS-STHMU | Steering HMU | 91119 | 29788 | 7500
500049474 | CLB-MP-HAUL-DT170 -STRSYS-STPMP | Pump Steering | 91119 | 6569 | 7500
500049473 | CLB-MP-HAUL-DT170 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 91119 | 9406 | 7500
500049472 | CLB-MP-HAUL-DT170 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 91119 | 9406 | 7500
500049471 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 91119 | 21744 | 7500
500049470 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 91119 | 21744 | 7500
500049469 | CLB-MP-HAUL-DT170 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 91119 | 21744 | 7500
500049468 | CLB-MP-HAUL-DT170 -BRKSYS-BACCM | Brake Accumulator | 91119 | 21744 | 7500
500049467 | CLB-MP-HAUL-DT170 -BRKSYS-BROCO | Brake Oil Cooler | 91119 | 68128 | 7500
500049466 | CLB-MP-HAUL-DT170 -BRKSYS-MERTR | Mechanical Retarder | 91119 | 91119 | 7500
500049465 | CLB-MP-HAUL-DT170 -BRKSYS-BRVTR | Valve Brake Treadle | 91119 | 53564 | 7500
500049464 | CLB-MP-HAUL-DT170 -BRKSYS-HYFPP | Pump Brake Control | 91119 | 9337 | 7500
500049463 | CLB-MP-HAUL-DT170 -BRKSYS-PRKPP | Pump Park Brake Release | 91119 | 91119 | 7500
500049462 | CLB-MP-HAUL-DT170 -BRKSYS-BRPMP | Pump Brake | 91119 | 91119 | 7500
500049461 | CLB-MP-HAUL-DT170 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 91119 | 91119 | 7500
500049460 | CLB-MP-HAUL-DT170 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 91119 | 91119 | 7500
500049459 | CLB-MP-HAUL-DT170 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 91119 | 91119 | 7500
500049458 | CLB-MP-HAUL-DT170 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 91119 | 91119 | 7500
500049457 | CLB-MP-HAUL-DT170 -BRKSYS-SRVBK | Service Brake | 91119 | 91119 | 7500
500049456 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 91119 | 91119 | 7500
500049455 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 91119 | 6569 | 7500
500049454 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 91119 | 9406 | 7500
500049453 | CLB-MP-HAUL-DT170 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 91119 | 21744 | 7500
500049452 | CLB-MP-HAUL-DT170 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 91119 | 21744 | 7500
500049451 | CLB-MP-HAUL-DT170 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 91119 | 21744 | 7500
500049450 | CLB-MP-HAUL-DT170 -FDRSYS-DRLAX | Drive Line Axles | 91119 | 91119 | 7500
500049449 | CLB-MP-HAUL-DT170 -FDRSYS-DIFFL | Differential | 91119 | 21744 | 7500
500049448 | CLB-MP-HAUL-DT170 -FDRSYS-DRSHT | Transmission Drive Shaft | 91119 | 33937 | 7500
500049447 | CLB-MP-HAUL-DT170 -TRNSYS-TROLC | Oil Cooler Transmission | 91119 | 21744 | 7500
500049446 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 91119 | 33938 | 7500
500049445 | CLB-MP-HAUL-DT170 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 91119 | 12852 | 7500
500049444 | CLB-MP-HAUL-DT170 -TRNSYS-TRANS | Transmission | 91119 | 12852 | 7500
500049443 | CLB-MP-HAUL-DT170 -TRNSYS-TRQUE | Torque Converter | 91119 | 21744 | 7500
500049442 | CLB-MP-HAUL-DT170 -ELCTLV-CHARG-BATTY | Batteries | 91119 | 91119 | 7500
500049441 | CLB-MP-HAUL-DT170 -ELCTLV-CHARG-ALTER | Alternator 24V | 91119 | 9337 | 7500
500049440 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 91119 | 24071 | 7500
500049439 | CLB-MP-HAUL-DT170 -ENGINE-PMPDR | Pump Drive | 91119 | 21744 | 7500
500049438 | CLB-MP-HAUL-DT170 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 91119 | 21744 | 7500
500049437 | CLB-MP-HAUL-DT170 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 91119 | 9337 | 7500
500049436 | CLB-MP-HAUL-DT170 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 91119 | 21744 | 7500
500049435 | CLB-MP-HAUL-DT170 -ENGINE-FUSYS-FULTK | Fuel Tank | 91119 | 21744 | 7500
500049434 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-EXHST | Exhaust System | 91119 | 91119 | 7500
500049433 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-AFTER | Aftercooler | 91119 | 68128 | 7500
500049432 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 91119 | 9337 | 7500
500049431 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 91119 | 9337 | 7500
500049430 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 91119 | 9337 | 7500
500049429 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 91119 | 9337 | 7500
500049428 | CLB-MP-HAUL-DT170 -ENGINE-INTEX-AIRFL | Air Filtration System | 91119 | 91119 | 7500
500049427 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-THERM | Thermostats/Regulators | 91119 | 21744 | 7500
500049426 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-BELTS | Fan Belts Engine | 91119 | 68128 | 7500
500049425 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 91119 | 21744 | 7500
500049424 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-COFAN | Fan Cooling System | 91119 | 21744 | 7500
500049423 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-RADTR | Coolant Engine | 91119 | 21744 | 7400
500049422 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-RADTR | Radiator Engine | 91119 | 21744 | 7500
500049421 | CLB-MP-HAUL-DT170 -ENGINE-COSYS-WTRPP | Water Pump Engine | 91119 | 9337 | 7500
500049420 | CLB-MP-HAUL-DT170 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 91119 | 68128 | 7500
500049419 | CLB-MP-HAUL-DT170 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 91119 | 21744 | 7500
500049418 | CLB-MP-HAUL-DT170 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 91119 | 68128 | 7500
500049417 | CLB-MP-HAUL-DT170 -ENGINE-COMPR | Air Compressor | 91119 | 9337 | 7500
500046620 | CLB-MP-HAUL-DT170 -ENGINE | Engine Assembly Caterpillar 3516B | 91119 | 21744 | 7500
500046619 | CLB-MP-HAUL-DT170 | DT170 Lube & Mechanical Services | 91119 | 91119 | 7500
500046618 | CLB-MP-HAUL-DT170 | Caterpillar 789D Haul Truck, DT170 | 91119 | 91119 | 7500
500160241 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITRH | Air Tank Right | 93147 | 93147 | 7500
500160240 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK-AITLH | Air Tank Left | 93147 | 93147 | 7500
500147202 | CLB-MP-HAUL-DT169 -STRSYS-STACC | Steering Accumulator Rear | 25282 | 25282 | 7500
500147201 | CLB-MP-HAUL-DT169 -STRSYS-STACC | Steering Accumulator Middle | 25282 | 25282 | 7500
500147200 | CLB-MP-HAUL-DT169 -STRSYS-STACC | Steering Accumulator Front | 25282 | 25282 | 7500
500118548 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-AFRME | A Frame Housing | 93409 | 37178 | 7500
500117924 | CLB-MP-HAUL-DT169 -ELCTLV-LIGHT | Lighting Low Voltage | 93410 | 48615 | 7500
500117884 | CLB-MP-HAUL-DT169 -ELCTLV-HARNS | Electrical Harness | 93410 | 48615 | 7500
500117844 | CLB-MP-HAUL-DT169 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 93410 | 48615 | 7500
500117408 | CLB-MP-HAUL-DT169 -ELCTLV-LIGHT-AHSYS | AHS Lights | 93410 | 48615 | 7500
500117288 | CLB-MP-HAUL-DT169 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 93410 | 48615 | 7500
500111210 | CLB-MP-HAUL-DT169 -STRUCT-RAXHO | Rear Axle Housing | 93385 | 48626 | 7500
500110540 | CLB-MP-HAUL-DT169 -GRSYST | Grease Lubrication System | 93410 | 9365 | 7500
500102790 | CLB-MP-HAUL-DT169 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 93410 | 19043 | 7500
500100617 | CLB-MP-HAUL-DT169 -TRNSYS | DT169 Transmission System | 93410 | 42842 | 7500
500081394 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 93410 | 25282 | 7500
500081254 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 93410 | 25282 | 7500
500079427 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN | Suspension Service | 93410 | 23335 | 7500
500078493 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 93410 | 25282 | 7500
500078456 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 93410 | 25282 | 7500
500061420 | CLB-MP-HAUL-DT169 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 93410 | 25282 | 7500
500061390 | CLB-MP-HAUL-DT169 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 93410 | 25282 | 7500
500060992 | CLB-MP-HAUL-DT169 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 93410 | 48734 | 7500
500060991 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-ELECT | Chassis Electrical System | 93410 | 25282 | 7500
500060990 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-ELECT | Cabin Electrical System | 93410 | 93410 | 7500
500060989 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 93410 | 9210 | 7500
500060988 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 93410 | 9210 | 7500
500060987 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 93410 | 9210 | 7500
500060986 | CLB-MP-HAUL-DT169 -STRSYS-STHLF-STRHO | Steering System Hoses | 93410 | 25282 | 7500
500060985 | CLB-MP-HAUL-DT169 -STRSYS-STLTR-STBST | Ball Studs | 93410 | 93410 | 7500
500060984 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 93410 | 25282 | 7500
500060983 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 93410 | 25282 | 7500
500060982 | CLB-MP-HAUL-DT169 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 93410 | 25282 | 7500
500060981 | CLB-MP-HAUL-DT169 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 93410 | 9210 | 7500
500060980 | CLB-MP-HAUL-DT169 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 93410 | 2730 | 7500
500060979 | CLB-MP-HAUL-DT169 -BRKSYS-BRVRL | Brake Relay Valve | 93410 | 2730 | 7500
500060977 | CLB-MP-HAUL-DT169 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 93410 | 25282 | 7500
500060976 | CLB-MP-HAUL-DT169 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 93410 | 25282 | 7500
500060107 | CLB-MP-HAUL-DT169 -STRSYS-STTNK | Tank Steering | 93410 | 70326 | 7500
500053833 | CLB-MP-HAUL-DT169 -BRKSYS-BRVLV | Valve Brake | 93410 | 2730 | 7500
500049416 | CLB-MP-HAUL-DT169 -MANGMT-UMMMC | Mine Monitoring and Control | 93410 | 93410 | 7500
500049415 | CLB-MP-HAUL-DT169 -MANGMT-UMTRN | Power Train Management System | 93410 | 93410 | 7500
500049414 | CLB-MP-HAUL-DT169 -MANGMT-UMENG | Engine Management System | 93410 | 93410 | 7500
500049413 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 93410 | 2730 | 7500
500049412 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 93410 | 2730 | 7500
500049411 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 93410 | 2730 | 7500
500049410 | CLB-MP-HAUL-DT169 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 93410 | 2730 | 7500
500049407 | CLB-MP-HAUL-DT169 -STRUCT-TRAYS | Tray | 93409 | 25282 | 7500
500049406 | CLB-MP-HAUL-DT169 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 93410 | 2730 | 7500
500049405 | CLB-MP-HAUL-DT169 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 93410 | 7748 | 7500
500049404 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-TAGLK | Tag Link | 93410 | 2730 | 7500
500049403 | CLB-MP-HAUL-DT169 -STRUCT-CHASS-AFRME | A Frame Bearing | 93410 | 2730 | 7500
500049402 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-SBELT | Seat Belt | 93410 | 93410 | 7500
500049401 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-SEATS | Operators Seat | 93410 | 14340 | 7500
500049400 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 93410 | 93410 | 7500
500049399 | CLB-MP-HAUL-DT169 -STRUCT-CABIN-AIRCN | Air Conditioning System | 93410 | 14340 | 7500
500049398 | CLB-MP-HAUL-DT169 -STRUCT-CABIN | Operators Cabin | 93410 | 48734 | 7500
500049397 | CLB-MP-HAUL-DT169 -PNEUMC-START | Air Starter | 93410 | 9210 | 7500
500049396 | CLB-MP-HAUL-DT169 -PNEUMC-AIRDR | Air Drier | 93410 | 2730 | 7500
500049395 | CLB-MP-HAUL-DT169 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 93410 | 93410 | 7500
500049394 | CLB-MP-HAUL-DT169 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 93410 | 93410 | 7500
500049393 | CLB-MP-HAUL-DT169 -PNEUMC-PNTNK | No Not Use | 93410 | 93410 | 7500
500049392 | CLB-MP-HAUL-DT169 -GRSYST-ALCON | Auto Lube Controller | 93410 | 93410 | 7500
500049391 | CLB-MP-HAUL-DT169 -GRSYST-ALBPP | Auto Lube Pump | 93410 | 52382 | 7500
500049390 | CLB-MP-HAUL-DT169 -GRSYST-GRTNK | Auto Lube Resevoir | 93410 | 93410 | 7500
500049389 | CLB-MP-HAUL-DT169 -GRSYST-GRINJ | Auto Lube Injectors | 93410 | 93410 | 7500
500049388 | CLB-MP-HAUL-DT169 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 93410 | 28092 | 7500
500049387 | CLB-MP-HAUL-DT169 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 93410 | 25282 | 7500
500049386 | CLB-MP-HAUL-DT169 -HYDSYS-HOVLV | Valve Hoist | 93410 | 37178 | 7500
500049385 | CLB-MP-HAUL-DT169 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 93410 | 93410 | 7500
500049384 | CLB-MP-HAUL-DT169 -HYDSYS-HDTNK | Tank Hydraulic | 93410 | 70326 | 7500
500049383 | CLB-MP-HAUL-DT169 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 93410 | 25282 | 7500
500049382 | CLB-MP-HAUL-DT169 -HYDSYS-HOPMP | Pump Hoist | 93410 | 2730 | 7500
500049381 | CLB-MP-HAUL-DT169 -HYDSYS | Hydraulic System | 93410 | 93410 | 7500
500049380 | CLB-MP-HAUL-DT169 -STRSYS-STCON-STCOL | Steering Column | 93410 | 93410 | 7500
500049379 | CLB-MP-HAUL-DT169 -STRSYS-STCON-STWHL | Steering Wheel | 93410 | 93410 | 7500
500049378 | CLB-MP-HAUL-DT169 -STRSYS-STLTR | Steering Linkages and Tie Rods | 93410 | 2730 | 7500
500049377 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 93410 | 25282 | 7500
500049376 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 93410 | 25282 | 7500
500049375 | CLB-MP-HAUL-DT169 -STRSYS-STACC-SACCF | Accumulator Steering Front | 93410 | 25282 | 7500
500049374 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 93410 | 10097 | 7500
500049373 | CLB-MP-HAUL-DT169 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 93410 | 25282 | 7500
500049372 | CLB-MP-HAUL-DT169 -STRSYS-STVLV | Valve Steering | 93410 | 6480 | 7500
500049371 | CLB-MP-HAUL-DT169 -STRSYS-STHMU | Steering HMU | 93410 | 9365 | 7500
500049370 | CLB-MP-HAUL-DT169 -STRSYS-STPMP | Pump Steering | 93410 | 9339 | 7500
500049369 | CLB-MP-HAUL-DT169 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 93410 | 13586 | 7500
500049368 | CLB-MP-HAUL-DT169 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 93410 | 13586 | 7500
500049367 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 93410 | 2730 | 7500
500049366 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 93410 | 2730 | 7500
500049365 | CLB-MP-HAUL-DT169 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 93410 | 2730 | 7500
500049364 | CLB-MP-HAUL-DT169 -BRKSYS-BACCM | Brake Accumulator | 93410 | 2730 | 7500
500049363 | CLB-MP-HAUL-DT169 -BRKSYS-BROCO | Brake Oil Cooler | 93410 | 70326 | 7500
500049362 | CLB-MP-HAUL-DT169 -BRKSYS-MERTR | Mechanical Retarder | 93410 | 93410 | 7500
500049361 | CLB-MP-HAUL-DT169 -BRKSYS-BRVTR | Valve Brake Treadle | 93410 | 70326 | 7500
500049360 | CLB-MP-HAUL-DT169 -BRKSYS-HYFPP | Pump Brake Control | 93410 | 2730 | 7500
500049359 | CLB-MP-HAUL-DT169 -BRKSYS-PRKPP | Pump Park Brake Release | 93410 | 70326 | 7500
500049358 | CLB-MP-HAUL-DT169 -BRKSYS-BRPMP | Pump Brake | 93410 | 37179 | 7500
500049357 | CLB-MP-HAUL-DT169 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 93410 | 70326 | 7500
500049356 | CLB-MP-HAUL-DT169 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 93410 | 70326 | 7500
500049355 | CLB-MP-HAUL-DT169 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 93410 | 70326 | 7500
500049354 | CLB-MP-HAUL-DT169 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 93410 | 73426 | 7500
500049353 | CLB-MP-HAUL-DT169 -BRKSYS-SRVBK | Service Brake | 93410 | 93410 | 7500
500049352 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 93410 | 93410 | 7500
500049351 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 93410 | 93410 | 7500
500049350 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 93410 | 7769 | 7500
500049349 | CLB-MP-HAUL-DT169 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 93410 | 10768 | 7500
500049348 | CLB-MP-HAUL-DT169 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 93410 | 2730 | 7500
500049347 | CLB-MP-HAUL-DT169 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 93410 | 2730 | 7500
500049346 | CLB-MP-HAUL-DT169 -FDRSYS-DRLAX | Drive Line Axles | 93410 | 93410 | 7500
500049345 | CLB-MP-HAUL-DT169 -FDRSYS-DIFFL | Differential | 93410 | 2730 | 7500
500049344 | CLB-MP-HAUL-DT169 -FDRSYS-DRSHT | Transmission Drive Shaft | 93410 | 29987 | 7500
500049343 | CLB-MP-HAUL-DT169 -TRNSYS-TROLC | Oil Cooler Transmission | 93410 | 16379 | 7500
500049342 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 93410 | 7748 | 7500
500049341 | CLB-MP-HAUL-DT169 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 93410 | 2730 | 7500
500049340 | CLB-MP-HAUL-DT169 -TRNSYS-TRANS | Transmission | 93410 | 16379 | 7500
500049339 | CLB-MP-HAUL-DT169 -TRNSYS-TRQUE | Torque Converter | 93410 | 7748 | 7500
500049338 | CLB-MP-HAUL-DT169 -ELCTLV-CHARG-BATTY | Batteries | 93410 | 10768 | 7500
500049337 | CLB-MP-HAUL-DT169 -ELCTLV-CHARG-ALTER | Alternator 24V | 93410 | 9210 | 7500
500049336 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 93408 | 12173 | 7500
500049335 | CLB-MP-HAUL-DT169 -ENGINE-PMPDR | Pump Drive | 93410 | 2730 | 7500
500049334 | CLB-MP-HAUL-DT169 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 93410 | 9210 | 7500
500049333 | CLB-MP-HAUL-DT169 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 93410 | 9210 | 7500
500049332 | CLB-MP-HAUL-DT169 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 93410 | 9210 | 7500
500049331 | CLB-MP-HAUL-DT169 -ENGINE-FUSYS-FULTK | Fuel Tank | 93410 | 25282 | 7500
500049330 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-EXHST | Exhaust System | 93410 | 93410 | 7500
500049329 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-AFTER | Aftercooler | 93410 | 54209 | 7500
500049328 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 93410 | 9210 | 7500
500049327 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 93410 | 9210 | 7500
500049326 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 93410 | 9210 | 7500
500049325 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 93410 | 9210 | 7500
500049324 | CLB-MP-HAUL-DT169 -ENGINE-INTEX-AIRFL | Air Filtration System | 93410 | 93410 | 7500
500049323 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-THERM | Thermostats/Regulators | 93410 | 9210 | 7500
500049322 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-BELTS | Fan Belts Engine | 93410 | 29988 | 7500
500049321 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 93410 | 9210 | 7500
500049320 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-COFAN | Fan Cooling System | 93410 | 9210 | 7500
500049319 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-RADTR | Coolant Engine | 93410 | 25282 | 7400
500049318 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-RADTR | Radiator Engine | 93410 | 2730 | 7500
500049317 | CLB-MP-HAUL-DT169 -ENGINE-COSYS-WTRPP | Water Pump Engine | 93410 | 9210 | 7500
500049316 | CLB-MP-HAUL-DT169 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 93410 | 54209 | 7500
500049315 | CLB-MP-HAUL-DT169 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 93410 | 9210 | 7500
500049314 | CLB-MP-HAUL-DT169 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 93410 | 29988 | 7500
500049313 | CLB-MP-HAUL-DT169 -ENGINE-COMPR | Air Compressor | 93410 | 9210 | 7500
500046666 | CLB-MP-HAUL-DT169 -ENGINE | Engine Assembly Caterpillar 3516B | 93410 | 9210 | 7500
500046665 | CLB-MP-HAUL-DT169 | DT169 Lube & Mechanical Services | 93410 | 93410 | 7500
500046664 | CLB-MP-HAUL-DT169 | Caterpillar 789D Haul Truck, DT169 | 93410 | 93410 | 7500
500160239 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITRH | Air Tank Right | 92948 | 52765 | 7500
500160238 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK-AITLH | Air Tank Left | 92948 | 52765 | 7500
500147198 | CLB-MP-HAUL-DT168 -STRSYS-STACC | Steering Accumulator Rear | 26428 | 26428 | 7500
500147197 | CLB-MP-HAUL-DT168 -STRSYS-STACC | Steering Accumulator Middle | 26428 | 26428 | 7500
500147196 | CLB-MP-HAUL-DT168 -STRSYS-STACC | Steering Accumulator Front | 26428 | 26428 | 7500
500118547 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-AFRME | A Frame Housing | 93142 | 4514 | 7500
500117923 | CLB-MP-HAUL-DT168 -ELCTLV-LIGHT | Lighting Low Voltage | 93142 | 50342 | 7500
500117883 | CLB-MP-HAUL-DT168 -ELCTLV-HARNS | Electrical Harness | 93142 | 50342 | 7500
500117843 | CLB-MP-HAUL-DT168 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 93142 | 50342 | 7500
500117407 | CLB-MP-HAUL-DT168 -ELCTLV-LIGHT-AHSYS | AHS Lights | 93142 | 50342 | 7500
500117287 | CLB-MP-HAUL-DT168 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 93142 | 50342 | 7500
500111209 | CLB-MP-HAUL-DT168 -STRUCT-RAXHO | Rear Axle Housing | 93142 | 4514 | 7500
500110539 | CLB-MP-HAUL-DT168 -GRSYST | Grease Lubrication System | 93142 | 20521 | 7500
500102789 | CLB-MP-HAUL-DT168 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 93142 | 17991 | 7500
500100616 | CLB-MP-HAUL-DT168 -TRNSYS | DT168 Transmission System | 93142 | 44217 | 7500
500081393 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 93142 | 26428 | 7500
500081253 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 93142 | 26428 | 7500
500079426 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN | Suspension Service | 93142 | 26399 | 7500
500078492 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 93142 | 26428 | 7500
500078455 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 93142 | 26428 | 7500
500061419 | CLB-MP-HAUL-DT168 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 93142 | 4514 | 7500
500061389 | CLB-MP-HAUL-DT168 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 93142 | 26428 | 7500
500060975 | CLB-MP-HAUL-DT168 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 93142 | 26428 | 7500
500060974 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-ELECT | Chassis Electrical System | 93142 | 26428 | 7500
500060973 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-ELECT | Cabin Electrical System | 93142 | 93142 | 7500
500060972 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 93142 | 15365 | 7500
500060971 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 93142 | 15365 | 7500
500060970 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 93142 | 15365 | 7500
500060969 | CLB-MP-HAUL-DT168 -STRSYS-STHLF-STRHO | Steering System Hoses | 93142 | 26428 | 7500
500060968 | CLB-MP-HAUL-DT168 -STRSYS-STLTR-STBST | Ball Studs | 93142 | 93142 | 7500
500060967 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 93142 | 26428 | 7500
500060966 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 93142 | 26428 | 7500
500060965 | CLB-MP-HAUL-DT168 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 93142 | 26428 | 7500
500060964 | CLB-MP-HAUL-DT168 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 93142 | 4514 | 7500
500060963 | CLB-MP-HAUL-DT168 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 93142 | 26428 | 7500
500060962 | CLB-MP-HAUL-DT168 -BRKSYS-BRVRL | Brake Relay Valve | 93142 | 4514 | 7500
500060960 | CLB-MP-HAUL-DT168 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 93142 | 26428 | 7500
500060959 | CLB-MP-HAUL-DT168 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 93142 | 26428 | 7500
500060106 | CLB-MP-HAUL-DT168 -STRSYS-STTNK | Tank Steering | 93142 | 71952 | 7500
500053832 | CLB-MP-HAUL-DT168 -BRKSYS-BRVLV | Valve Brake | 93142 | 4514 | 7500
500049312 | CLB-MP-HAUL-DT168 -MANGMT-UMMMC | Mine Monitoring and Control | 93142 | 93142 | 7500
500049311 | CLB-MP-HAUL-DT168 -MANGMT-UMTRN | Power Train Management System | 93142 | 93142 | 7500
500049310 | CLB-MP-HAUL-DT168 -MANGMT-UMENG | Engine Management System | 93142 | 93142 | 7500
500049309 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 93142 | 4514 | 7500
500049308 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 93142 | 11875 | 7500
500049307 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 93142 | 26428 | 7500
500049306 | CLB-MP-HAUL-DT168 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 93142 | 8931 | 7500
500049303 | CLB-MP-HAUL-DT168 -STRUCT-TRAYS | Tray | 93142 | 26428 | 7500
500049302 | CLB-MP-HAUL-DT168 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 93142 | 4514 | 7500
500049301 | CLB-MP-HAUL-DT168 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 93142 | 4514 | 7500
500049300 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-TAGLK | Tag Link | 93142 | 4514 | 7500
500049299 | CLB-MP-HAUL-DT168 -STRUCT-CHASS-AFRME | A Frame Bearing | 93142 | 4514 | 7500
500049298 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-SBELT | Seat Belt | 93142 | 93142 | 7500
500049297 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-SEATS | Operators Seat | 93142 | 12586 | 7500
500049296 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 93142 | 93142 | 7500
500049295 | CLB-MP-HAUL-DT168 -STRUCT-CABIN-AIRCN | Air Conditioning System | 93142 | 15366 | 7500
500049294 | CLB-MP-HAUL-DT168 -STRUCT-CABIN | Operators Cabin | 93142 | 50606 | 7500
500049293 | CLB-MP-HAUL-DT168 -PNEUMC-START | Air Starter | 93142 | 4514 | 7500
500049292 | CLB-MP-HAUL-DT168 -PNEUMC-AIRDR | Air Drier | 93142 | 26428 | 7500
500049291 | CLB-MP-HAUL-DT168 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 93142 | 93142 | 7500
500049290 | CLB-MP-HAUL-DT168 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 93142 | 71952 | 7500
500049289 | CLB-MP-HAUL-DT168 -PNEUMC-PNTNK | No Not Use | 93142 | 52959 | 7500
500049288 | CLB-MP-HAUL-DT168 -GRSYST-ALCON | Auto Lube Controller | 93142 | 93142 | 7500
500049287 | CLB-MP-HAUL-DT168 -GRSYST-ALBPP | Auto Lube Pump | 93142 | 23160 | 7500
500049286 | CLB-MP-HAUL-DT168 -GRSYST-GRTNK | Auto Lube Resevoir | 93142 | 93142 | 7500
500049285 | CLB-MP-HAUL-DT168 -GRSYST-GRINJ | Auto Lube Injectors | 93142 | 93142 | 7500
500049284 | CLB-MP-HAUL-DT168 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 93142 | 26428 | 7500
500049283 | CLB-MP-HAUL-DT168 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 93142 | 26428 | 7500
500049282 | CLB-MP-HAUL-DT168 -HYDSYS-HOVLV | Valve Hoist | 93142 | 26428 | 7500
500049281 | CLB-MP-HAUL-DT168 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 93142 | 93142 | 7500
500049280 | CLB-MP-HAUL-DT168 -HYDSYS-HDTNK | Tank Hydraulic | 93142 | 71952 | 7500
500049279 | CLB-MP-HAUL-DT168 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 93142 | 26428 | 7500
500049278 | CLB-MP-HAUL-DT168 -HYDSYS-HOPMP | Pump Hoist | 93142 | 2151 | 7500
500049277 | CLB-MP-HAUL-DT168 -HYDSYS | Hydraulic System | 93142 | 93142 | 7500
500049276 | CLB-MP-HAUL-DT168 -STRSYS-STCON-STCOL | Steering Column | 93142 | 93142 | 7500
500049275 | CLB-MP-HAUL-DT168 -STRSYS-STCON-STWHL | Steering Wheel | 93142 | 93142 | 7500
500049274 | CLB-MP-HAUL-DT168 -STRSYS-STLTR | Steering Linkages and Tie Rods | 93142 | 26428 | 7500
500049273 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 93142 | 26428 | 7500
500049272 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 93142 | 26428 | 7500
500049271 | CLB-MP-HAUL-DT168 -STRSYS-STACC-SACCF | Accumulator Steering Front | 93142 | 26428 | 7500
500049270 | CLB-MP-HAUL-DT168 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 93142 | 7536 | 7500
500049269 | CLB-MP-HAUL-DT168 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 93142 | 7536 | 7500
500049268 | CLB-MP-HAUL-DT168 -STRSYS-STVLV | Valve Steering | 93142 | 7534 | 7500
500049267 | CLB-MP-HAUL-DT168 -STRSYS-STHMU | Steering HMU | 93142 | 7534 | 7500
500049266 | CLB-MP-HAUL-DT168 -STRSYS-STPMP | Pump Steering | 93142 | 7536 | 7500
500049265 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 93142 | 14674 | 7500
500049264 | CLB-MP-HAUL-DT168 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 93142 | 15366 | 7500
500049263 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 93142 | 4514 | 7500
500049262 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 93142 | 4514 | 7500
500049261 | CLB-MP-HAUL-DT168 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 93142 | 4514 | 7500
500049260 | CLB-MP-HAUL-DT168 -BRKSYS-BACCM | Brake Accumulator | 93142 | 4514 | 7500
500049259 | CLB-MP-HAUL-DT168 -BRKSYS-BROCO | Brake Oil Cooler | 93142 | 93142 | 7500
500049258 | CLB-MP-HAUL-DT168 -BRKSYS-MERTR | Mechanical Retarder | 93142 | 93142 | 7500
500049257 | CLB-MP-HAUL-DT168 -BRKSYS-BRVTR | Valve Brake Treadle | 93142 | 71952 | 7500
500049256 | CLB-MP-HAUL-DT168 -BRKSYS-HYFPP | Pump Brake Control | 93142 | 7536 | 7500
500049255 | CLB-MP-HAUL-DT168 -BRKSYS-PRKPP | Pump Park Brake Release | 93142 | 93142 | 7500
500049254 | CLB-MP-HAUL-DT168 -BRKSYS-BRPMP | Pump Brake | 93142 | 93142 | 7500
500049253 | CLB-MP-HAUL-DT168 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 93142 | 71952 | 7500
500049252 | CLB-MP-HAUL-DT168 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 93142 | 71952 | 7500
500049251 | CLB-MP-HAUL-DT168 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 93142 | 71952 | 7500
500049250 | CLB-MP-HAUL-DT168 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 93142 | 71907 | 7500
500049249 | CLB-MP-HAUL-DT168 -BRKSYS-SRVBK | Service Brake | 93142 | 93142 | 7500
500049248 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 93142 | 93142 | 7500
500049247 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 93142 | 93142 | 7500
500049246 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 93142 | 8682 | 7500
500049245 | CLB-MP-HAUL-DT168 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 93142 | 4514 | 7500
500049244 | CLB-MP-HAUL-DT168 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 93142 | 4514 | 7500
500049243 | CLB-MP-HAUL-DT168 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 93142 | 4514 | 7500
500049242 | CLB-MP-HAUL-DT168 -FDRSYS-DRLAX | Drive Line Axles | 93142 | 93142 | 7500
500049241 | CLB-MP-HAUL-DT168 -FDRSYS-DIFFL | Differential | 93142 | 5860 | 7500
500049240 | CLB-MP-HAUL-DT168 -FDRSYS-DRSHT | Transmission Drive Shaft | 93142 | 32079 | 7500
500049239 | CLB-MP-HAUL-DT168 -TRNSYS-TROLC | Oil Cooler Transmission | 93142 | 26428 | 7500
500049238 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 93142 | 7534 | 7500
500049237 | CLB-MP-HAUL-DT168 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 93142 | 18709 | 7500
500049236 | CLB-MP-HAUL-DT168 -TRNSYS-TRANS | Transmission | 93142 | 8669 | 7500
500049235 | CLB-MP-HAUL-DT168 -TRNSYS-TRQUE | Torque Converter | 93142 | 4514 | 7500
500049234 | CLB-MP-HAUL-DT168 -ELCTLV-CHARG-BATTY | Batteries | 93142 | 93142 | 7500
500049233 | CLB-MP-HAUL-DT168 -ELCTLV-CHARG-ALTER | Alternator 24V | 93142 | 4514 | 7500
500049232 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 93142 | 15366 | 7500
500049231 | CLB-MP-HAUL-DT168 -ENGINE-PMPDR | Pump Drive | 93142 | 4514 | 7500
500049230 | CLB-MP-HAUL-DT168 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 93142 | 4514 | 7500
500049229 | CLB-MP-HAUL-DT168 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 93142 | 4514 | 7500
500049228 | CLB-MP-HAUL-DT168 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 93142 | 4514 | 7500
500049227 | CLB-MP-HAUL-DT168 -ENGINE-FUSYS-FULTK | Fuel Tank | 93142 | 50606 | 7500
500049226 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-EXHST | Exhaust System | 93142 | 93142 | 7500
500049225 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-AFTER | Aftercooler | 93142 | 71952 | 7500
500049224 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 93142 | 4514 | 7500
500049223 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 93142 | 4514 | 7500
500049222 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 93142 | 4514 | 7500
500049221 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 93142 | 4514 | 7500
500049220 | CLB-MP-HAUL-DT168 -ENGINE-INTEX-AIRFL | Air Filtration System | 93142 | 93142 | 7500
500049219 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-THERM | Thermostats/Regulators | 93142 | 4514 | 7500
500049218 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-BELTS | Fan Belts Engine | 93142 | 50606 | 7500
500049217 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 93142 | 4514 | 7500
500049216 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-COFAN | Fan Cooling System | 93142 | 4514 | 7500
500049215 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-RADTR | Coolant Engine | 93142 | 26428 | 7400
500049214 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-RADTR | Radiator Engine | 93142 | 26428 | 7500
500049213 | CLB-MP-HAUL-DT168 -ENGINE-COSYS-WTRPP | Water Pump Engine | 93142 | 4514 | 7500
500049212 | CLB-MP-HAUL-DT168 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 93142 | 50606 | 7500
500049211 | CLB-MP-HAUL-DT168 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 93142 | 4514 | 7500
500049210 | CLB-MP-HAUL-DT168 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 93142 | 50606 | 7500
500049209 | CLB-MP-HAUL-DT168 -ENGINE-COMPR | Air Compressor | 93142 | 4514 | 7500
500046616 | CLB-MP-HAUL-DT168 -ENGINE | Engine Assembly Caterpillar 3516B | 93142 | 4514 | 7500
500046615 | CLB-MP-HAUL-DT168 | DT168 Lube & Mechanical Services | 93142 | 93142 | 7500
500046614 | CLB-MP-HAUL-DT168 | Caterpillar 789D Haul Truck, DT168 | 93142 | 93142 | 7500
500160237 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITRH | Air Tank Right | 83047 | 18464 | 7500
500160236 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK-AITLH | Air Tank Left | 83047 | 18464 | 7500
500147194 | CLB-MP-HAUL-DT167 -STRSYS-STACC | Steering Accumulator Rear | 31597 | 31597 | 7500
500147193 | CLB-MP-HAUL-DT167 -STRSYS-STACC | Steering Accumulator Middle | 31597 | 31597 | 7500
500147192 | CLB-MP-HAUL-DT167 -STRSYS-STACC | Steering Accumulator Front | 31597 | 31597 | 7500
500118546 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-AFRME | A Frame Housing | 83302 | 83302 | 7500
500117922 | CLB-MP-HAUL-DT167 -ELCTLV-LIGHT | Lighting Low Voltage | 83303 | 50661 | 7500
500117882 | CLB-MP-HAUL-DT167 -ELCTLV-HARNS | Electrical Harness | 83303 | 50661 | 7500
500117842 | CLB-MP-HAUL-DT167 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 83303 | 50661 | 7500
500117406 | CLB-MP-HAUL-DT167 -ELCTLV-LIGHT-AHSYS | AHS Lights | 83303 | 50661 | 7500
500117286 | CLB-MP-HAUL-DT167 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 83303 | 50661 | 7500
500111208 | CLB-MP-HAUL-DT167 -STRUCT-RAXHO | Rear Axle Housing | 83290 | 72465 | 7500
500110538 | CLB-MP-HAUL-DT167 -GRSYST | Grease Lubrication System | 83303 | 14675 | 7500
500102788 | CLB-MP-HAUL-DT167 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 83303 | 9443 | 7500
500100615 | CLB-MP-HAUL-DT167 -TRNSYS | DT167 Transmission System | 83303 | 52852 | 7500
500081392 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 83303 | 23066 | 7500
500081252 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 83303 | 23066 | 7500
500079425 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN | Suspension Service | 83303 | 9432 | 7500
500078491 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 83303 | 9443 | 7500
500078454 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 83303 | 9443 | 7500
500061418 | CLB-MP-HAUL-DT167 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 83303 | 9443 | 7500
500061388 | CLB-MP-HAUL-DT167 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 83303 | 9443 | 7500
500060958 | CLB-MP-HAUL-DT167 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 83303 | 9443 | 7500
500060957 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-ELECT | Chassis Electrical System | 83303 | 31597 | 7500
500060956 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-ELECT | Cabin Electrical System | 83303 | 83303 | 7500
500060955 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 83303 | 9443 | 7500
500060954 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 83303 | 9443 | 7500
500060953 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 83303 | 9443 | 7500
500060952 | CLB-MP-HAUL-DT167 -STRSYS-STHLF-STRHO | Steering System Hoses | 83303 | 9443 | 7500
500060951 | CLB-MP-HAUL-DT167 -STRSYS-STLTR-STBST | Ball Studs | 83303 | 83303 | 7500
500060950 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 83303 | 9443 | 7500
500060949 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 83303 | 9443 | 7500
500060948 | CLB-MP-HAUL-DT167 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 83303 | 9443 | 7500
500060947 | CLB-MP-HAUL-DT167 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 83303 | 9443 | 7500
500060946 | CLB-MP-HAUL-DT167 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 83303 | 9443 | 7500
500060945 | CLB-MP-HAUL-DT167 -BRKSYS-BRVRL | Brake Relay Valve | 83303 | 9443 | 7500
500060943 | CLB-MP-HAUL-DT167 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 83303 | 9443 | 7500
500060942 | CLB-MP-HAUL-DT167 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 83303 | 9443 | 7500
500060105 | CLB-MP-HAUL-DT167 -STRSYS-STTNK | Tank Steering | 83303 | 83303 | 7500
500053831 | CLB-MP-HAUL-DT167 -BRKSYS-BRVLV | Valve Brake | 83303 | 9443 | 7500
500049208 | CLB-MP-HAUL-DT167 -MANGMT-UMMMC | Mine Monitoring and Control | 83303 | 83303 | 7500
500049207 | CLB-MP-HAUL-DT167 -MANGMT-UMTRN | Power Train Management System | 83303 | 83303 | 7500
500049206 | CLB-MP-HAUL-DT167 -MANGMT-UMENG | Engine Management System | 83303 | 83303 | 7500
500049205 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 83303 | 9443 | 7500
500049204 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 83303 | 9443 | 7500
500049203 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 83303 | 15419 | 7500
500049202 | CLB-MP-HAUL-DT167 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 83303 | 9443 | 7500
500049199 | CLB-MP-HAUL-DT167 -STRUCT-TRAYS | Tray | 83302 | 19386 | 7500
500049198 | CLB-MP-HAUL-DT167 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 83303 | 599 | 7500
500049197 | CLB-MP-HAUL-DT167 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 83303 | 11175 | 7500
500049196 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-TAGLK | Tag Link | 83303 | 9443 | 7500
500049195 | CLB-MP-HAUL-DT167 -STRUCT-CHASS-AFRME | A Frame Bearing | 83303 | 33418 | 7500
500049194 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-SBELT | Seat Belt | 83303 | 83303 | 7500
500049193 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-SEATS | Operators Seat | 83303 | 9443 | 7500
500049192 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 83303 | 83303 | 7500
500049191 | CLB-MP-HAUL-DT167 -STRUCT-CABIN-AIRCN | Air Conditioning System | 83303 | 9443 | 7500
500049190 | CLB-MP-HAUL-DT167 -STRUCT-CABIN | Operators Cabin | 83303 | 9443 | 7500
500049189 | CLB-MP-HAUL-DT167 -PNEUMC-START | Air Starter | 83303 | 9443 | 7500
500049188 | CLB-MP-HAUL-DT167 -PNEUMC-AIRDR | Air Drier | 83303 | 9443 | 7500
500049187 | CLB-MP-HAUL-DT167 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 83303 | 83303 | 7500
500049186 | CLB-MP-HAUL-DT167 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 83303 | 83303 | 7500
500049185 | CLB-MP-HAUL-DT167 -PNEUMC-PNTNK | No Not Use | 83303 | 18720 | 7500
500049184 | CLB-MP-HAUL-DT167 -GRSYST-ALCON | Auto Lube Controller | 83303 | 83303 | 7500
500049183 | CLB-MP-HAUL-DT167 -GRSYST-ALBPP | Auto Lube Pump | 83303 | 52202 | 7500
500049182 | CLB-MP-HAUL-DT167 -GRSYST-GRTNK | Auto Lube Resevoir | 83303 | 83303 | 7500
500049181 | CLB-MP-HAUL-DT167 -GRSYST-GRINJ | Auto Lube Injectors | 83303 | 83303 | 7500
500049180 | CLB-MP-HAUL-DT167 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 83303 | 9443 | 7500
500049179 | CLB-MP-HAUL-DT167 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 83303 | 9443 | 7500
500049178 | CLB-MP-HAUL-DT167 -HYDSYS-HOVLV | Valve Hoist | 83303 | 31597 | 7500
500049177 | CLB-MP-HAUL-DT167 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 83303 | 83303 | 7500
500049176 | CLB-MP-HAUL-DT167 -HYDSYS-HDTNK | Tank Hydraulic | 83303 | 83303 | 7500
500049175 | CLB-MP-HAUL-DT167 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 83303 | 9443 | 7500
500049174 | CLB-MP-HAUL-DT167 -HYDSYS-HOPMP | Pump Hoist | 83303 | 9443 | 7500
500049173 | CLB-MP-HAUL-DT167 -HYDSYS | Hydraulic System | 83303 | 83303 | 7500
500049172 | CLB-MP-HAUL-DT167 -STRSYS-STCON-STCOL | Steering Column | 83303 | 83303 | 7500
500049171 | CLB-MP-HAUL-DT167 -STRSYS-STCON-STWHL | Steering Wheel | 83303 | 83303 | 7500
500049170 | CLB-MP-HAUL-DT167 -STRSYS-STLTR | Steering Linkages and Tie Rods | 83303 | 9443 | 7500
500049169 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 83303 | 9443 | 7500
500049168 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 83303 | 9443 | 7500
500049167 | CLB-MP-HAUL-DT167 -STRSYS-STACC-SACCF | Accumulator Steering Front | 83303 | 9443 | 7500
500049166 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 83303 | 2776 | 7500
500049165 | CLB-MP-HAUL-DT167 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 83303 | 9443 | 7500
500049164 | CLB-MP-HAUL-DT167 -STRSYS-STVLV | Valve Steering | 83303 | 9443 | 7500
500049163 | CLB-MP-HAUL-DT167 -STRSYS-STHMU | Steering HMU | 83303 | 9443 | 7500
500049162 | CLB-MP-HAUL-DT167 -STRSYS-STPMP | Pump Steering | 83303 | 9443 | 7500
500049161 | CLB-MP-HAUL-DT167 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 83303 | 9443 | 7500
500049160 | CLB-MP-HAUL-DT167 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 83303 | 9443 | 7500
500049159 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 83303 | 9443 | 7500
500049158 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 83303 | 9443 | 7500
500049157 | CLB-MP-HAUL-DT167 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 83303 | 9443 | 7500
500049156 | CLB-MP-HAUL-DT167 -BRKSYS-BACCM | Brake Accumulator | 83303 | 9443 | 7500
500049155 | CLB-MP-HAUL-DT167 -BRKSYS-BROCO | Brake Oil Cooler | 83303 | 83303 | 7500
500049154 | CLB-MP-HAUL-DT167 -BRKSYS-MERTR | Mechanical Retarder | 83303 | 83303 | 7500
500049153 | CLB-MP-HAUL-DT167 -BRKSYS-BRVTR | Valve Brake Treadle | 83303 | 83303 | 7500
500049152 | CLB-MP-HAUL-DT167 -BRKSYS-HYFPP | Pump Brake Control | 83303 | 9443 | 7500
500049151 | CLB-MP-HAUL-DT167 -BRKSYS-PRKPP | Pump Park Brake Release | 83303 | 83303 | 7500
500049150 | CLB-MP-HAUL-DT167 -BRKSYS-BRPMP | Pump Brake | 83303 | 83303 | 7500
500049149 | CLB-MP-HAUL-DT167 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 83303 | 83303 | 7500
500049148 | CLB-MP-HAUL-DT167 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 83303 | 83303 | 7500
500049147 | CLB-MP-HAUL-DT167 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 83303 | 83303 | 7500
500049146 | CLB-MP-HAUL-DT167 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 83303 | 83303 | 7500
500049145 | CLB-MP-HAUL-DT167 -BRKSYS-SRVBK | Service Brake | 83303 | 83303 | 7500
500049144 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 83303 | 9443 | 7500
500049143 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 83303 | 53904 | 7500
500049142 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 83303 | 9443 | 7500
500049141 | CLB-MP-HAUL-DT167 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 83303 | 9443 | 7500
500049140 | CLB-MP-HAUL-DT167 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 83303 | 14525 | 7500
500049139 | CLB-MP-HAUL-DT167 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 83303 | 14525 | 7500
500049138 | CLB-MP-HAUL-DT167 -FDRSYS-DRLAX | Drive Line Axles | 83303 | 83303 | 7500
500049137 | CLB-MP-HAUL-DT167 -FDRSYS-DIFFL | Differential | 83303 | 9443 | 7500
500049136 | CLB-MP-HAUL-DT167 -FDRSYS-DRSHT | Transmission Drive Shaft | 83303 | 9443 | 7500
500049135 | CLB-MP-HAUL-DT167 -TRNSYS-TROLC | Oil Cooler Transmission | 83303 | 9443 | 7500
500049134 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 83303 | 9443 | 7500
500049133 | CLB-MP-HAUL-DT167 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 83303 | 9443 | 7500
500049132 | CLB-MP-HAUL-DT167 -TRNSYS-TRANS | Transmission | 83303 | 9443 | 7500
500049131 | CLB-MP-HAUL-DT167 -TRNSYS-TRQUE | Torque Converter | 83303 | 9443 | 7500
500049130 | CLB-MP-HAUL-DT167 -ELCTLV-CHARG-BATTY | Batteries | 83303 | 83303 | 7500
500049129 | CLB-MP-HAUL-DT167 -ELCTLV-CHARG-ALTER | Alternator 24V | 83303 | 9443 | 7500
500049128 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 83303 | 9443 | 7500
500049127 | CLB-MP-HAUL-DT167 -ENGINE-PMPDR | Pump Drive | 83303 | 9443 | 7500
500049126 | CLB-MP-HAUL-DT167 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 83303 | 9443 | 7500
500049125 | CLB-MP-HAUL-DT167 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 83303 | 9443 | 7500
500049124 | CLB-MP-HAUL-DT167 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 83303 | 9443 | 7500
500049123 | CLB-MP-HAUL-DT167 -ENGINE-FUSYS-FULTK | Fuel Tank | 83303 | 9443 | 7500
500049122 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-EXHST | Exhaust System | 83303 | 58410 | 7500
500049121 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-AFTER | Aftercooler | 83303 | 41526 | 7500
500049120 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 83303 | 9443 | 7500
500049119 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 83303 | 9443 | 7500
500049118 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 83303 | 9443 | 7500
500049117 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 83303 | 9443 | 7500
500049116 | CLB-MP-HAUL-DT167 -ENGINE-INTEX-AIRFL | Air Filtration System | 83303 | 83303 | 7500
500049115 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-THERM | Thermostats/Regulators | 83303 | 9443 | 7500
500049114 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-BELTS | Fan Belts Engine | 83303 | 83303 | 7500
500049113 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 83303 | 7941 | 7500
500049112 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-COFAN | Fan Cooling System | 83303 | 9443 | 7500
500049111 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-RADTR | Coolant Engine | 83302 | 31597 | 7400
500049110 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-RADTR | Radiator Engine | 83303 | 9443 | 7500
500049109 | CLB-MP-HAUL-DT167 -ENGINE-COSYS-WTRPP | Water Pump Engine | 83303 | 9443 | 7500
500049108 | CLB-MP-HAUL-DT167 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 83303 | 83303 | 7500
500049107 | CLB-MP-HAUL-DT167 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 83303 | 9443 | 7500
500049106 | CLB-MP-HAUL-DT167 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 83303 | 83303 | 7500
500049105 | CLB-MP-HAUL-DT167 -ENGINE-COMPR | Air Compressor | 83303 | 7941 | 7500
500046662 | CLB-MP-HAUL-DT167 -ENGINE | Engine Assembly Caterpillar 3516B | 83303 | 9443 | 7500
500046661 | CLB-MP-HAUL-DT167 | DT167 Lube & Mechanical Services | 83303 | 83303 | 7500
500046660 | CLB-MP-HAUL-DT167 | Caterpillar 789D Haul Truck, DT167 | 83303 | 83303 | 7500
500160235 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITRH | Air Tank Right | 95233 | 95233 | 7500
500160234 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK-AITLH | Air Tank Left | 95233 | 95233 | 7500
500147190 | CLB-MP-HAUL-DT166 -STRSYS-STACC | Steering Accumulator Rear | 25609 | 25609 | 7500
500147189 | CLB-MP-HAUL-DT166 -STRSYS-STACC | Steering Accumulator Middle | 25609 | 25609 | 7500
500147188 | CLB-MP-HAUL-DT166 -STRSYS-STACC | Steering Accumulator Front | 25609 | 25609 | 7500
500118545 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-AFRME | A Frame Housing | 95490 | 2090 | 7500
500117921 | CLB-MP-HAUL-DT166 -ELCTLV-LIGHT | Lighting Low Voltage | 95491 | 48816 | 7500
500117881 | CLB-MP-HAUL-DT166 -ELCTLV-HARNS | Electrical Harness | 95491 | 48816 | 7500
500117841 | CLB-MP-HAUL-DT166 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 95491 | 48816 | 7500
500117405 | CLB-MP-HAUL-DT166 -ELCTLV-LIGHT-AHSYS | AHS Lights | 95491 | 48816 | 7500
500117285 | CLB-MP-HAUL-DT166 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 95491 | 48816 | 7500
500111207 | CLB-MP-HAUL-DT166 -STRUCT-RAXHO | Rear Axle Housing | 95490 | 2090 | 7500
500110537 | CLB-MP-HAUL-DT166 -GRSYST | Grease Lubrication System | 95491 | 13964 | 7500
500102787 | CLB-MP-HAUL-DT166 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 95491 | 2090 | 7500
500100614 | CLB-MP-HAUL-DT166 -TRNSYS | DT166 Transmission System | 95491 | 49136 | 7500
500081391 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 95491 | 25609 | 7500
500081251 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 95491 | 25609 | 7500
500079424 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN | Suspension Service | 95491 | 2090 | 7500
500078490 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 95491 | 2090 | 7500
500078453 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 95491 | 2090 | 7500
500061417 | CLB-MP-HAUL-DT166 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 95491 | 2090 | 7500
500061387 | CLB-MP-HAUL-DT166 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 95491 | 2090 | 7500
500060941 | CLB-MP-HAUL-DT166 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 95491 | 25609 | 7500
500060940 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-ELECT | Chassis Electrical System | 95491 | 49136 | 7500
500060939 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-ELECT | Cabin Electrical System | 95491 | 95491 | 7500
500060938 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 95491 | 14683 | 7500
500060937 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 95491 | 14683 | 7500
500060936 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 95491 | 14683 | 7500
500060935 | CLB-MP-HAUL-DT166 -STRSYS-STHLF-STRHO | Steering System Hoses | 95491 | 2090 | 7500
500060934 | CLB-MP-HAUL-DT166 -STRSYS-STLTR-STBST | Ball Studs | 95491 | 95491 | 7500
500060933 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 95491 | 1986 | 7500
500060932 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 95491 | 1986 | 7500
500060931 | CLB-MP-HAUL-DT166 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 95491 | 1986 | 7500
500060930 | CLB-MP-HAUL-DT166 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 95491 | 2090 | 7500
500060929 | CLB-MP-HAUL-DT166 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 95491 | 2090 | 7500
500060928 | CLB-MP-HAUL-DT166 -BRKSYS-BRVRL | Brake Relay Valve | 95491 | 2090 | 7500
500060926 | CLB-MP-HAUL-DT166 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 95491 | 2090 | 7500
500060925 | CLB-MP-HAUL-DT166 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 95491 | 2090 | 7500
500060104 | CLB-MP-HAUL-DT166 -STRSYS-STTNK | Tank Steering | 95491 | 71350 | 7500
500053830 | CLB-MP-HAUL-DT166 -BRKSYS-BRVLV | Valve Brake | 95491 | 2090 | 7500
500049104 | CLB-MP-HAUL-DT166 -MANGMT-UMMMC | Mine Monitoring and Control | 95491 | 95491 | 7500
500049103 | CLB-MP-HAUL-DT166 -MANGMT-UMTRN | Power Train Management System | 95491 | 95491 | 7500
500049102 | CLB-MP-HAUL-DT166 -MANGMT-UMENG | Engine Management System | 95491 | 95491 | 7500
500049101 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 95491 | 2090 | 7500
500049100 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 95491 | 2090 | 7500
500049099 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 95491 | 2090 | 7500
500049098 | CLB-MP-HAUL-DT166 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 95491 | 2090 | 7500
500049095 | CLB-MP-HAUL-DT166 -STRUCT-TRAYS | Tray | 95490 | 2087 | 7500
500049094 | CLB-MP-HAUL-DT166 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 95491 | 2090 | 7500
500049093 | CLB-MP-HAUL-DT166 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 95491 | 2090 | 7500
500049092 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-TAGLK | Tag Link | 95473 | 2090 | 7500
500049091 | CLB-MP-HAUL-DT166 -STRUCT-CHASS-AFRME | A Frame Bearing | 95491 | 2090 | 7500
500049090 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-SBELT | Seat Belt | 95491 | 95491 | 7500
500049089 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-SEATS | Operators Seat | 95491 | 9539 | 7500
500049088 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 95491 | 95491 | 7500
500049087 | CLB-MP-HAUL-DT166 -STRUCT-CABIN-AIRCN | Air Conditioning System | 95491 | 14683 | 7500
500049086 | CLB-MP-HAUL-DT166 -STRUCT-CABIN | Operators Cabin | 95491 | 25609 | 7500
500049085 | CLB-MP-HAUL-DT166 -PNEUMC-START | Air Starter | 95491 | 2090 | 7500
500049084 | CLB-MP-HAUL-DT166 -PNEUMC-AIRDR | Air Drier | 95491 | 2090 | 7500
500049083 | CLB-MP-HAUL-DT166 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 95491 | 95491 | 7500
500049082 | CLB-MP-HAUL-DT166 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 95491 | 95491 | 7500
500049081 | CLB-MP-HAUL-DT166 -PNEUMC-PNTNK | No Not Use | 95491 | 95491 | 7500
500049080 | CLB-MP-HAUL-DT166 -GRSYST-ALCON | Auto Lube Controller | 95491 | 95491 | 7500
500049079 | CLB-MP-HAUL-DT166 -GRSYST-ALBPP | Auto Lube Pump | 95491 | 41581 | 7500
500049078 | CLB-MP-HAUL-DT166 -GRSYST-GRTNK | Auto Lube Resevoir | 95491 | 95491 | 7500
500049077 | CLB-MP-HAUL-DT166 -GRSYST-GRINJ | Auto Lube Injectors | 95491 | 95491 | 7500
500049076 | CLB-MP-HAUL-DT166 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 95491 | 17159 | 7500
500049075 | CLB-MP-HAUL-DT166 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 95491 | 18595 | 7500
500049074 | CLB-MP-HAUL-DT166 -HYDSYS-HOVLV | Valve Hoist | 95491 | 25609 | 7500
500049073 | CLB-MP-HAUL-DT166 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 95491 | 95491 | 7500
500049072 | CLB-MP-HAUL-DT166 -HYDSYS-HDTNK | Tank Hydraulic | 95491 | 71350 | 7500
500049071 | CLB-MP-HAUL-DT166 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 95491 | 25609 | 7500
500049070 | CLB-MP-HAUL-DT166 -HYDSYS-HOPMP | Pump Hoist | 95491 | 14683 | 7500
500049069 | CLB-MP-HAUL-DT166 -HYDSYS | Hydraulic System | 95491 | 95491 | 7500
500049068 | CLB-MP-HAUL-DT166 -STRSYS-STCON-STCOL | Steering Column | 95491 | 95491 | 7500
500049067 | CLB-MP-HAUL-DT166 -STRSYS-STCON-STWHL | Steering Wheel | 95491 | 95491 | 7500
500049066 | CLB-MP-HAUL-DT166 -STRSYS-STLTR | Steering Linkages and Tie Rods | 95491 | 8036 | 7500
500049065 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 95491 | 2090 | 7500
500049064 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 95491 | 2090 | 7500
500049063 | CLB-MP-HAUL-DT166 -STRSYS-STACC-SACCF | Accumulator Steering Front | 95491 | 2090 | 7500
500049062 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 95491 | 2090 | 7500
500049061 | CLB-MP-HAUL-DT166 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 95491 | 11151 | 7500
500049060 | CLB-MP-HAUL-DT166 -STRSYS-STVLV | Valve Steering | 95491 | 8004 | 7500
500049059 | CLB-MP-HAUL-DT166 -STRSYS-STHMU | Steering HMU | 95491 | 25609 | 7500
500049058 | CLB-MP-HAUL-DT166 -STRSYS-STPMP | Pump Steering | 95491 | 13970 | 7500
500049057 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 95491 | 14683 | 7500
500049056 | CLB-MP-HAUL-DT166 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 95491 | 14683 | 7500
500049055 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 95491 | 2090 | 7500
500049054 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 95491 | 2090 | 7500
500049053 | CLB-MP-HAUL-DT166 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 95491 | 2090 | 7500
500049052 | CLB-MP-HAUL-DT166 -BRKSYS-BACCM | Brake Accumulator | 95491 | 2090 | 7500
500049051 | CLB-MP-HAUL-DT166 -BRKSYS-BROCO | Brake Oil Cooler - Rear | 95491 | 71350 | 7500
500049050 | CLB-MP-HAUL-DT166 -BRKSYS-MERTR | Mechanical Retarder | 95491 | 95491 | 7500
500049049 | CLB-MP-HAUL-DT166 -BRKSYS-BRVTR | Valve Brake Treadle | 95491 | 71350 | 7500
500049048 | CLB-MP-HAUL-DT166 -BRKSYS-HYFPP | Pump Brake Control | 95491 | 2090 | 7500
500049047 | CLB-MP-HAUL-DT166 -BRKSYS-PRKPP | Pump Park Brake Release | 95491 | 71350 | 7500
500049046 | CLB-MP-HAUL-DT166 -BRKSYS-BRPMP | Pump Brake | 95491 | 71350 | 7500
500049045 | CLB-MP-HAUL-DT166 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 95491 | 71350 | 7500
500049044 | CLB-MP-HAUL-DT166 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 95491 | 71350 | 7500
500049043 | CLB-MP-HAUL-DT166 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 95491 | 71350 | 7500
500049042 | CLB-MP-HAUL-DT166 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 95491 | 71350 | 7500
500049041 | CLB-MP-HAUL-DT166 -BRKSYS-SRVBK | Service Brake | 95491 | 95491 | 7500
500049040 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 95491 | 25609 | 7500
500049039 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 95491 | 71350 | 7500
500049038 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 95491 | 2090 | 7500
500049037 | CLB-MP-HAUL-DT166 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 95491 | 2090 | 7500
500049036 | CLB-MP-HAUL-DT166 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 95491 | 19244 | 7500
500049035 | CLB-MP-HAUL-DT166 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 95491 | 19244 | 7500
500049034 | CLB-MP-HAUL-DT166 -FDRSYS-DRLAX | Drive Line Axles | 95491 | 95491 | 7500
500049033 | CLB-MP-HAUL-DT166 -FDRSYS-DIFFL | Differential | 95491 | 19244 | 7500
500049032 | CLB-MP-HAUL-DT166 -FDRSYS-DRSHT | Transmission Drive Shaft | 95491 | 2090 | 7500
500049031 | CLB-MP-HAUL-DT166 -TRNSYS-TROLC | Oil Cooler Transmission | 95491 | 2090 | 7500
500049030 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 95491 | 2090 | 7500
500049029 | CLB-MP-HAUL-DT166 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 95491 | 2090 | 7500
500049028 | CLB-MP-HAUL-DT166 -TRNSYS-TRANS | Transmission | 95491 | 2090 | 7500
500049027 | CLB-MP-HAUL-DT166 -TRNSYS-TRQUE | Torque Converter | 95490 | 2090 | 7500
500049026 | CLB-MP-HAUL-DT166 -ELCTLV-CHARG-BATTY | Batteries | 95491 | 95491 | 7500
500049025 | CLB-MP-HAUL-DT166 -ELCTLV-CHARG-ALTER | Alternator 24V | 95491 | 2090 | 7500
500049024 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 95491 | 2090 | 7500
500049023 | CLB-MP-HAUL-DT166 -ENGINE-PMPDR | Pump Drive | 95491 | 2828 | 7500
500049022 | CLB-MP-HAUL-DT166 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 95491 | 2090 | 7500
500049021 | CLB-MP-HAUL-DT166 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 95491 | 2090 | 7500
500049020 | CLB-MP-HAUL-DT166 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 95491 | 2090 | 7500
500049019 | CLB-MP-HAUL-DT166 -ENGINE-FUSYS-FULTK | Fuel Tank | 95491 | 25293 | 7500
500049018 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-EXHST | Exhaust System | 95491 | 95491 | 7500
500049017 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-AFTER | Aftercooler | 95491 | 71350 | 7500
500049016 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 95491 | 2090 | 7500
500049015 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 95491 | 2090 | 7500
500049014 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 95491 | 2090 | 7500
500049013 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 95491 | 2090 | 7500
500049012 | CLB-MP-HAUL-DT166 -ENGINE-INTEX-AIRFL | Air Filtration System | 95491 | 95491 | 7500
500049011 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-THERM | Thermostats/Regulators | 95491 | 2090 | 7500
500049010 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-BELTS | Fan Belts Engine | 95491 | 71350 | 7500
500049009 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 95491 | 2090 | 7500
500049008 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-COFAN | Fan Cooling System | 95491 | 2090 | 7500
500049007 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-RADTR | Coolant Engine | 95491 | 71350 | 7400
500049006 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-RADTR | Radiator Engine | 95491 | 17157 | 7500
500049005 | CLB-MP-HAUL-DT166 -ENGINE-COSYS-WTRPP | Water Pump Engine | 95491 | 2090 | 7500
500049004 | CLB-MP-HAUL-DT166 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 95491 | 71350 | 7500
500049003 | CLB-MP-HAUL-DT166 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 95491 | 2090 | 7500
500049002 | CLB-MP-HAUL-DT166 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 95491 | 71350 | 7500
500049001 | CLB-MP-HAUL-DT166 -ENGINE-COMPR | Air Compressor | 95491 | 2090 | 7500
500042640 | CLB-MP-HAUL-DT166 -ENGINE | Engine Assembly Caterpillar 3516B | 95491 | 2090 | 7500
500042629 | CLB-MP-HAUL-DT166 | DT166 Lube & Mechanical Services | 95491 | 95491 | 7500
500042628 | CLB-MP-HAUL-DT166 | Caterpillar 789D Haul Truck, DT166 | 95491 | 95491 | 7500
500160233 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITRH | Air Tank Right | 78739 | 40861 | 7500
500160232 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK-AITLH | Air Tank Left | 78739 | 40861 | 7500
500147186 | CLB-MP-HAUL-DT165 -STRSYS-STACC | Steering Accumulator Rear | 30583 | 30583 | 7500
500147185 | CLB-MP-HAUL-DT165 -STRSYS-STACC | Steering Accumulator Middle | 30583 | 30583 | 7500
500147184 | CLB-MP-HAUL-DT165 -STRSYS-STACC | Steering Accumulator Front | 30583 | 30583 | 7500
500118544 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-AFRME | A Frame Housing | 78966 | 30583 | 7500
500117920 | CLB-MP-HAUL-DT165 -ELCTLV-LIGHT | Lighting Low Voltage | 78966 | 50741 | 7500
500117880 | CLB-MP-HAUL-DT165 -ELCTLV-HARNS | Electrical Harness | 78966 | 50741 | 7500
500117840 | CLB-MP-HAUL-DT165 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 78966 | 35179 | 7500
500117404 | CLB-MP-HAUL-DT165 -ELCTLV-LIGHT-AHSYS | AHS Lights | 78966 | 50741 | 7500
500117284 | CLB-MP-HAUL-DT165 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 78966 | 50741 | 7500
500111206 | CLB-MP-HAUL-DT165 -STRUCT-RAXHO | Rear Axle Housing | 78966 | 30583 | 7500
500110536 | CLB-MP-HAUL-DT165 -GRSYST | Grease Lubrication System | 78966 | 24195 | 7500
500102786 | CLB-MP-HAUL-DT165 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 78966 | 8345 | 7500
500100613 | CLB-MP-HAUL-DT165 -TRNSYS | DT165 Transmission System | 78966 | 51251 | 7500
500081390 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 78966 | 23545 | 7500
500081250 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 78966 | 23545 | 7500
500079423 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN | Suspension Service | 78966 | 10144 | 7500
500078489 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 78966 | 8345 | 7500
500078452 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 78966 | 8345 | 7500
500061416 | CLB-MP-HAUL-DT165 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 78966 | 8345 | 7500
500061386 | CLB-MP-HAUL-DT165 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 78966 | 8345 | 7500
500060924 | CLB-MP-HAUL-DT165 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 78966 | 8345 | 7500
500060923 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-ELECT | Chassis Electrical System | 78966 | 30583 | 7500
500060922 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-ELECT | Cabin Electrical System | 78966 | 78966 | 7500
500060921 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 78966 | 8345 | 7500
500060920 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 78966 | 8345 | 7500
500060919 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 78966 | 8345 | 7500
500060918 | CLB-MP-HAUL-DT165 -STRSYS-STHLF-STRHO | Steering System Hoses | 78966 | 8345 | 7500
500060917 | CLB-MP-HAUL-DT165 -STRSYS-STLTR-STBST | Ball Studs | 78966 | 78966 | 7500
500060916 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 78966 | 8345 | 7500
500060915 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 78966 | 8345 | 7500
500060914 | CLB-MP-HAUL-DT165 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 78966 | 8345 | 7500
500060913 | CLB-MP-HAUL-DT165 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 78966 | 708 | 7500
500060912 | CLB-MP-HAUL-DT165 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 78966 | 8345 | 7500
500060911 | CLB-MP-HAUL-DT165 -BRKSYS-BRVRL | Brake Relay Valve | 78966 | 8345 | 7500
500060909 | CLB-MP-HAUL-DT165 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 78966 | 8345 | 7500
500060908 | CLB-MP-HAUL-DT165 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 78966 | 8345 | 7500
500060103 | CLB-MP-HAUL-DT165 -STRSYS-STTNK | Tank Steering | 78966 | 78966 | 7500
500053829 | CLB-MP-HAUL-DT165 -BRKSYS-BRVLV | Valve Brake | 78966 | 8345 | 7500
500049000 | CLB-MP-HAUL-DT165 -MANGMT-UMMMC | Mine Monitoring and Control | 78966 | 78966 | 7500
500048999 | CLB-MP-HAUL-DT165 -MANGMT-UMTRN | Power Train Management System | 78966 | 78966 | 7500
500048998 | CLB-MP-HAUL-DT165 -MANGMT-UMENG | Engine Management System | 78966 | 78966 | 7500
500048997 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 78966 | 8345 | 7500
500048996 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 78966 | 8345 | 7500
500048995 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 78966 | 8345 | 7500
500048994 | CLB-MP-HAUL-DT165 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 78966 | 8345 | 7500
500048991 | CLB-MP-HAUL-DT165 -STRUCT-TRAYS | Tray | 78966 | 15572 | 7500
500048990 | CLB-MP-HAUL-DT165 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 78966 | 12262 | 7500
500048989 | CLB-MP-HAUL-DT165 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 78966 | 8345 | 7500
500048988 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-TAGLK | Tag Link | 78966 | 8345 | 7500
500048987 | CLB-MP-HAUL-DT165 -STRUCT-CHASS-AFRME | A Frame Bearing | 78966 | 12284 | 7500
500048986 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-SBELT | Seat Belt | 78966 | 78966 | 7500
500048985 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-SEATS | Operators Seat | 78966 | 8345 | 7500
500048984 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 78966 | 78966 | 7500
500048983 | CLB-MP-HAUL-DT165 -STRUCT-CABIN-AIRCN | Air Conditioning System | 78966 | 8345 | 7500
500048982 | CLB-MP-HAUL-DT165 -STRUCT-CABIN | Operators Cabin | 78966 | 8345 | 7500
500048981 | CLB-MP-HAUL-DT165 -PNEUMC-START | Air Starter | 78966 | 708 | 7500
500048980 | CLB-MP-HAUL-DT165 -PNEUMC-AIRDR | Air Drier | 78966 | 22268 | 7500
500048979 | CLB-MP-HAUL-DT165 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 78966 | 78966 | 7500
500048978 | CLB-MP-HAUL-DT165 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 78966 | 78966 | 7500
500048977 | CLB-MP-HAUL-DT165 -PNEUMC-PNTNK | No Not Use | 78966 | 41088 | 7500
500048976 | CLB-MP-HAUL-DT165 -GRSYST-ALCON | Auto Lube Controller | 78966 | 78966 | 7500
500048975 | CLB-MP-HAUL-DT165 -GRSYST-ALBPP | Auto Lube Pump | 78966 | 54164 | 7500
500048974 | CLB-MP-HAUL-DT165 -GRSYST-GRTNK | Auto Lube Resevoir | 78966 | 78966 | 7500
500048973 | CLB-MP-HAUL-DT165 -GRSYST-GRINJ | Auto Lube Injectors | 78966 | 78966 | 7500
500048972 | CLB-MP-HAUL-DT165 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 78966 | 8345 | 7500
500048971 | CLB-MP-HAUL-DT165 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 78966 | 8345 | 7500
500048970 | CLB-MP-HAUL-DT165 -HYDSYS-HOVLV | Valve Hoist | 78966 | 8345 | 7500
500048969 | CLB-MP-HAUL-DT165 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 78966 | 78966 | 7500
500048968 | CLB-MP-HAUL-DT165 -HYDSYS-HDTNK | Tank Hydraulic | 78966 | 78966 | 7500
500048967 | CLB-MP-HAUL-DT165 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 78966 | 8345 | 7500
500048966 | CLB-MP-HAUL-DT165 -HYDSYS-HOPMP | Pump Hoist | 78966 | 6162 | 7500
500048965 | CLB-MP-HAUL-DT165 -HYDSYS | Hydraulic System | 78966 | 78966 | 7500
500048964 | CLB-MP-HAUL-DT165 -STRSYS-STCON-STCOL | Steering Column | 78966 | 78966 | 7500
500048963 | CLB-MP-HAUL-DT165 -STRSYS-STCON-STWHL | Steering Wheel | 78966 | 78966 | 7500
500048962 | CLB-MP-HAUL-DT165 -STRSYS-STLTR | Steering Linkages and Tie Rods | 78966 | 14957 | 7500
500048961 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 78966 | 8345 | 7500
500048960 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 78966 | 8345 | 7500
500048959 | CLB-MP-HAUL-DT165 -STRSYS-STACC-SACCF | Accumulator Steering Front | 78966 | 8345 | 7500
500048958 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 78966 | 13578 | 7500
500048957 | CLB-MP-HAUL-DT165 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 78966 | 13578 | 7500
500048956 | CLB-MP-HAUL-DT165 -STRSYS-STVLV | Valve Steering | 78966 | 8345 | 7500
500048955 | CLB-MP-HAUL-DT165 -STRSYS-STHMU | Steering HMU | 78966 | 14957 | 7500
500048954 | CLB-MP-HAUL-DT165 -STRSYS-STPMP | Pump Steering | 78966 | 14957 | 7500
500048953 | CLB-MP-HAUL-DT165 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 78966 | 8345 | 7500
500048952 | CLB-MP-HAUL-DT165 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 78966 | 8345 | 7500
500048951 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 78966 | 8345 | 7500
500048950 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 78966 | 8345 | 7500
500048949 | CLB-MP-HAUL-DT165 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 78966 | 8345 | 7500
500048948 | CLB-MP-HAUL-DT165 -BRKSYS-BACCM | Brake Accumulator | 78966 | 8345 | 7500
500048947 | CLB-MP-HAUL-DT165 -BRKSYS-BROCO | Brake Oil Cooler | 78966 | 57893 | 7500
500048946 | CLB-MP-HAUL-DT165 -BRKSYS-MERTR | Mechanical Retarder | 78966 | 78966 | 7500
500048945 | CLB-MP-HAUL-DT165 -BRKSYS-BRVTR | Valve Brake Treadle | 78966 | 78966 | 7500
500048944 | CLB-MP-HAUL-DT165 -BRKSYS-HYFPP | Pump Brake Control | 78966 | 8345 | 7500
500048943 | CLB-MP-HAUL-DT165 -BRKSYS-PRKPP | Pump Park Brake Release | 78966 | 78966 | 7500
500048942 | CLB-MP-HAUL-DT165 -BRKSYS-BRPMP | Pump Brake | 78966 | 78966 | 7500
500048941 | CLB-MP-HAUL-DT165 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 78966 | 78966 | 7500
500048940 | CLB-MP-HAUL-DT165 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 78966 | 78966 | 7500
500048939 | CLB-MP-HAUL-DT165 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 78966 | 78966 | 7500
500048938 | CLB-MP-HAUL-DT165 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 78966 | 78966 | 7500
500048937 | CLB-MP-HAUL-DT165 -BRKSYS-SRVBK | Service Brake | 78966 | 78966 | 7500
500048936 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 78966 | 78966 | 7500
500048935 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 78966 | 78966 | 7500
500048934 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 78966 | 8345 | 7500
500048933 | CLB-MP-HAUL-DT165 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 78966 | 8345 | 7500
500048932 | CLB-MP-HAUL-DT165 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 78966 | 8345 | 7500
500048931 | CLB-MP-HAUL-DT165 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 78966 | 8345 | 7500
500048930 | CLB-MP-HAUL-DT165 -FDRSYS-DRLAX | Drive Line Axles | 78966 | 78966 | 7500
500048929 | CLB-MP-HAUL-DT165 -FDRSYS-DIFFL | Differential | 78966 | 8345 | 7500
500048928 | CLB-MP-HAUL-DT165 -FDRSYS-DRSHT | Transmission Drive Shaft | 78966 | 8345 | 7500
500048927 | CLB-MP-HAUL-DT165 -TRNSYS-TROLC | Oil Cooler Transmission | 78966 | 8345 | 7500
500048926 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 78966 | 708 | 7500
500048925 | CLB-MP-HAUL-DT165 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 78966 | 8345 | 7500
500048924 | CLB-MP-HAUL-DT165 -TRNSYS-TRANS | Transmission | 78966 | 8345 | 7500
500048923 | CLB-MP-HAUL-DT165 -TRNSYS-TRQUE | Torque Converter | 78966 | 708 | 7500
500048922 | CLB-MP-HAUL-DT165 -ELCTLV-CHARG-BATTY | Batteries | 78966 | 78966 | 7500
500048921 | CLB-MP-HAUL-DT165 -ELCTLV-CHARG-ALTER | Alternator 24V | 78966 | 708 | 7500
500048920 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 78966 | 8345 | 7500
500048919 | CLB-MP-HAUL-DT165 -ENGINE-PMPDR | Pump Drive | 78966 | 8345 | 7500
500048918 | CLB-MP-HAUL-DT165 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 78966 | 708 | 7500
500048917 | CLB-MP-HAUL-DT165 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 78966 | 708 | 7500
500048916 | CLB-MP-HAUL-DT165 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 78966 | 708 | 7500
500048915 | CLB-MP-HAUL-DT165 -ENGINE-FUSYS-FULTK | Fuel Tank | 78966 | 8345 | 7500
500048914 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-EXHST | Exhaust System | 78966 | 78966 | 7500
500048913 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-AFTER | Aftercooler | 78966 | 78966 | 7500
500048912 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 78966 | 708 | 7500
500048911 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 78966 | 708 | 7500
500048910 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 78966 | 708 | 7500
500048909 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 78966 | 708 | 7500
500048908 | CLB-MP-HAUL-DT165 -ENGINE-INTEX-AIRFL | Air Filtration System | 78966 | 78966 | 7500
500048907 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-THERM | Thermostats/Regulators | 78966 | 708 | 7500
500048906 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-BELTS | Fan Belts Engine | 78966 | 78966 | 7500
500048905 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 78966 | 708 | 7500
500048904 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-COFAN | Fan Cooling System | 78966 | 708 | 7500
500048903 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-RADTR | Coolant Engine | 78966 | 30583 | 7400
500048902 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-RADTR | Radiator Engine | 78966 | 8345 | 7500
500048901 | CLB-MP-HAUL-DT165 -ENGINE-COSYS-WTRPP | Water Pump Engine | 78966 | 708 | 7500
500048900 | CLB-MP-HAUL-DT165 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 78966 | 78966 | 7500
500048899 | CLB-MP-HAUL-DT165 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 78966 | 708 | 7500
500048898 | CLB-MP-HAUL-DT165 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 78966 | 78966 | 7500
500048897 | CLB-MP-HAUL-DT165 -ENGINE-COMPR | Air Compressor | 78966 | 708 | 7500
500042638 | CLB-MP-HAUL-DT165 -ENGINE | Engine Assembly Caterpillar 3516B | 78966 | 708 | 7500
500042627 | CLB-MP-HAUL-DT165 | DT165 Lube & Mechanical Services | 78966 | 78966 | 7500
500042626 | CLB-MP-HAUL-DT165 | Caterpillar 789D Haul Truck, DT165 | 78966 | 78966 | 7500
500160231 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITRH | Air Tank Right | 81612 | 11133 | 7500
500160230 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK-AITLH | Air Tank Left | 81612 | 11133 | 7500
500118543 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-AFRME | A Frame Housing | 81875 | 81875 | 7500
500117919 | CLB-MP-HAUL-DT164 -ELCTLV-LIGHT | Lighting Low Voltage | 81875 | 50437 | 7500
500117879 | CLB-MP-HAUL-DT164 -ELCTLV-HARNS | Electrical Harness | 81875 | 50437 | 7500
500117839 | CLB-MP-HAUL-DT164 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 81875 | 50437 | 7500
500117403 | CLB-MP-HAUL-DT164 -ELCTLV-LIGHT-AHSYS | AHS Lights | 81875 | 50437 | 7500
500117283 | CLB-MP-HAUL-DT164 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 81875 | 50437 | 7500
500111205 | CLB-MP-HAUL-DT164 -STRUCT-RAXHO | Rear Axle Housing | 81875 | 47364 | 7500
500110535 | CLB-MP-HAUL-DT164 -GRSYST | Grease Lubrication System | 81875 | 32833 | 7500
500102785 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 81875 | 11396 | 7500
500100612 | CLB-MP-HAUL-DT164 -TRNSYS | DT164 Transmission System | 81875 | 51780 | 7500
500081389 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 81875 | 24244 | 7500
500081249 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 81875 | 24244 | 7500
500079422 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN | Suspension Service | 81875 | 11396 | 7500
500078488 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 81875 | 11396 | 7500
500078451 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 81875 | 11396 | 7500
500061415 | CLB-MP-HAUL-DT164 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 81875 | 11396 | 7500
500061385 | CLB-MP-HAUL-DT164 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 81875 | 11396 | 7500
500060907 | CLB-MP-HAUL-DT164 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 81875 | 11396 | 7500
500060906 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-ELECT | Chassis Electrical System | 81875 | 32833 | 7500
500060905 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-ELECT | Cabin Electrical System | 81875 | 81875 | 7500
500060904 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 81875 | 11396 | 7500
500060903 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 81875 | 11396 | 7500
500060902 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 81875 | 11396 | 7500
500060901 | CLB-MP-HAUL-DT164 -STRSYS-STHLF-STRHO | Steering System Hoses | 81875 | 11396 | 7500
500060900 | CLB-MP-HAUL-DT164 -STRSYS-STLTR-STBST | Ball Studs | 81875 | 81875 | 7500
500060899 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 81875 | 11396 | 7500
500060898 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 81875 | 11396 | 7500
500060897 | CLB-MP-HAUL-DT164 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 81875 | 11396 | 7500
500060896 | CLB-MP-HAUL-DT164 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 81875 | 11396 | 7500
500060895 | CLB-MP-HAUL-DT164 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 81875 | 21550 | 7500
500060894 | CLB-MP-HAUL-DT164 -BRKSYS-BRVRL | Brake Relay Valve | 81875 | 11396 | 7500
500060892 | CLB-MP-HAUL-DT164 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 81875 | 11396 | 7500
500060891 | CLB-MP-HAUL-DT164 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 81875 | 11396 | 7500
500060102 | CLB-MP-HAUL-DT164 -STRSYS-STTNK | Tank Steering | 81875 | 81875 | 7500
500053828 | CLB-MP-HAUL-DT164 -BRKSYS-BRVLV | Valve Brake | 81875 | 11396 | 7500
500048896 | CLB-MP-HAUL-DT164 -MANGMT-UMMMC | Mine Monitoring and Control | 81875 | 81875 | 7500
500048895 | CLB-MP-HAUL-DT164 -MANGMT-UMTRN | Power Train Management System | 81875 | 81875 | 7500
500048894 | CLB-MP-HAUL-DT164 -MANGMT-UMENG | Engine Management System | 81875 | 81875 | 7500
500048893 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 81875 | 11396 | 7500
500048892 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 81875 | 11396 | 7500
500048891 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 81875 | 11396 | 7500
500048890 | CLB-MP-HAUL-DT164 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 81875 | 11396 | 7500
500048887 | CLB-MP-HAUL-DT164 -STRUCT-TRAYS | Tray | 81875 | 20145 | 7500
500048886 | CLB-MP-HAUL-DT164 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 81875 | 11396 | 7500
500048885 | CLB-MP-HAUL-DT164 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 81875 | 11396 | 7500
500048884 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-TAGLK | Tag Link | 81875 | 11396 | 7500
500048883 | CLB-MP-HAUL-DT164 -STRUCT-CHASS-AFRME | A Frame Bearing | 81875 | 11396 | 7500
500048882 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-SBELT | Seat Belt | 81875 | 42699 | 7500
500048881 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-SEATS | Operators Seat | 81875 | 11396 | 7500
500048880 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81875 | 81875 | 7500
500048879 | CLB-MP-HAUL-DT164 -STRUCT-CABIN-AIRCN | Air Conditioning System | 81875 | 11396 | 7500
500048878 | CLB-MP-HAUL-DT164 -STRUCT-CABIN | Operators Cabin | 81875 | 11396 | 7500
500048877 | CLB-MP-HAUL-DT164 -PNEUMC-START | Air Starter | 81875 | 11396 | 7500
500048876 | CLB-MP-HAUL-DT164 -PNEUMC-AIRDR | Air Drier | 81875 | 11396 | 7500
500048875 | CLB-MP-HAUL-DT164 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 81875 | 81875 | 7500
500048874 | CLB-MP-HAUL-DT164 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 81875 | 81875 | 7500
500048873 | CLB-MP-HAUL-DT164 -PNEUMC-PNTNK | No Not Use | 81875 | 11396 | 7500
500048872 | CLB-MP-HAUL-DT164 -GRSYST-ALCON | Auto Lube Controller | 81875 | 81875 | 7500
500048871 | CLB-MP-HAUL-DT164 -GRSYST-ALBPP | Auto Lube Pump | 81875 | 81875 | 7500
500048870 | CLB-MP-HAUL-DT164 -GRSYST-GRTNK | Auto Lube Resevoir | 81875 | 81875 | 7500
500048869 | CLB-MP-HAUL-DT164 -GRSYST-GRINJ | Auto Lube Injectors | 81875 | 81875 | 7500
500048868 | CLB-MP-HAUL-DT164 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 81875 | 11396 | 7500
500048867 | CLB-MP-HAUL-DT164 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 81875 | 11396 | 7500
500048866 | CLB-MP-HAUL-DT164 -HYDSYS-HOVLV | Valve Hoist | 81875 | 32833 | 7500
500048865 | CLB-MP-HAUL-DT164 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81875 | 81875 | 7500
500048864 | CLB-MP-HAUL-DT164 -HYDSYS-HDTNK | Tank Hydraulic | 81875 | 81875 | 7500
500048863 | CLB-MP-HAUL-DT164 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 81875 | 11396 | 7500
500048862 | CLB-MP-HAUL-DT164 -HYDSYS-HOPMP | Pump Hoist | 81875 | 11396 | 7500
500048861 | CLB-MP-HAUL-DT164 -HYDSYS | Hydraulic System | 81875 | 81875 | 7500
500048860 | CLB-MP-HAUL-DT164 -STRSYS-STCON-STCOL | Steering Column | 81875 | 81875 | 7500
500048859 | CLB-MP-HAUL-DT164 -STRSYS-STCON-STWHL | Steering Wheel | 81875 | 81875 | 7500
500048858 | CLB-MP-HAUL-DT164 -STRSYS-STLTR | Steering Linkages and Tie Rods | 81875 | 15434 | 7500
500048857 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 81875 | 11396 | 7500
500048856 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 81875 | 11396 | 7500
500048855 | CLB-MP-HAUL-DT164 -STRSYS-STACC-SACCF | Accumulator Steering Front | 81875 | 11396 | 7500
500048854 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 81875 | 15434 | 7500
500048853 | CLB-MP-HAUL-DT164 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 81875 | 15434 | 7500
500048852 | CLB-MP-HAUL-DT164 -STRSYS-STVLV | Valve Steering | 81875 | 11396 | 7500
500048851 | CLB-MP-HAUL-DT164 -STRSYS-STHMU | Steering HMU | 81875 | 15434 | 7500
500048850 | CLB-MP-HAUL-DT164 -STRSYS-STPMP | Pump Steering | 81875 | 15434 | 7500
500048849 | CLB-MP-HAUL-DT164 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 81875 | 11396 | 7500
500048848 | CLB-MP-HAUL-DT164 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 81875 | 11396 | 7500
500048847 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 81875 | 11396 | 7500
500048846 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 81875 | 11396 | 7500
500048845 | CLB-MP-HAUL-DT164 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 81875 | 11396 | 7500
500048844 | CLB-MP-HAUL-DT164 -BRKSYS-BACCM | Brake Accumulator | 81875 | 11396 | 7500
500048843 | CLB-MP-HAUL-DT164 -BRKSYS-BROCO | Brake Oil Cooler | 81875 | 45063 | 7500
500048842 | CLB-MP-HAUL-DT164 -BRKSYS-MERTR | Mechanical Retarder | 81875 | 81875 | 7500
500048841 | CLB-MP-HAUL-DT164 -BRKSYS-BRVTR | Valve Brake Treadle | 81875 | 81875 | 7500
500048840 | CLB-MP-HAUL-DT164 -BRKSYS-HYFPP | Pump Brake Control | 81875 | 7647 | 7500
500048839 | CLB-MP-HAUL-DT164 -BRKSYS-PRKPP | Pump Park Brake Release | 81875 | 81875 | 7500
500048838 | CLB-MP-HAUL-DT164 -BRKSYS-BRPMP | Pump Brake | 81875 | 16735 | 7500
500048837 | CLB-MP-HAUL-DT164 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 81875 | 81875 | 7500
500048836 | CLB-MP-HAUL-DT164 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 81875 | 81875 | 7500
500048835 | CLB-MP-HAUL-DT164 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 81875 | 81875 | 7500
500048834 | CLB-MP-HAUL-DT164 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 81875 | 81875 | 7500
500048833 | CLB-MP-HAUL-DT164 -BRKSYS-SRVBK | Service Brake | 81875 | 81875 | 7500
500048832 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 81875 | 81875 | 7500
500048831 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 81875 | 81875 | 7500
500048830 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 81875 | 11396 | 7500
500048829 | CLB-MP-HAUL-DT164 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 81875 | 1384 | 7500
500048828 | CLB-MP-HAUL-DT164 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 81875 | 11396 | 7500
500048827 | CLB-MP-HAUL-DT164 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 81875 | 11396 | 7500
500048826 | CLB-MP-HAUL-DT164 -FDRSYS-DRLAX | Drive Line Axles | 81875 | 81875 | 7500
500048825 | CLB-MP-HAUL-DT164 -FDRSYS-DIFFL | Differential | 81875 | 11396 | 7500
500048824 | CLB-MP-HAUL-DT164 -FDRSYS-DRSHT | Transmission Drive Shaft | 81875 | 11396 | 7500
500048823 | CLB-MP-HAUL-DT164 -TRNSYS-TROLC | Oil Cooler Transmission | 81875 | 11396 | 7500
500048822 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 81875 | 11396 | 7500
500048821 | CLB-MP-HAUL-DT164 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 81875 | 6988 | 7500
500048820 | CLB-MP-HAUL-DT164 -TRNSYS-TRANS | Transmission | 81875 | 2963 | 7500
500048819 | CLB-MP-HAUL-DT164 -TRNSYS-TRQUE | Torque Converter | 81875 | 11396 | 7500
500048818 | CLB-MP-HAUL-DT164 -ELCTLV-CHARG-BATTY | Batteries | 81875 | 81875 | 7500
500048817 | CLB-MP-HAUL-DT164 -ELCTLV-CHARG-ALTER | Alternator 24V | 81875 | 11396 | 7500
500048816 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 81875 | 11396 | 7500
500048815 | CLB-MP-HAUL-DT164 -ENGINE-PMPDR | Pump Drive | 81875 | 11396 | 7500
500048814 | CLB-MP-HAUL-DT164 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81875 | 11396 | 7500
500048813 | CLB-MP-HAUL-DT164 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81875 | 11396 | 7500
500048812 | CLB-MP-HAUL-DT164 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 81875 | 11396 | 7500
500048811 | CLB-MP-HAUL-DT164 -ENGINE-FUSYS-FULTK | Fuel Tank | 81875 | 11396 | 7500
500048810 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-EXHST | Exhaust System | 81875 | 81875 | 7500
500048809 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-AFTER | Aftercooler | 81875 | 17521 | 7500
500048808 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 81875 | 11396 | 7500
500048807 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 81875 | 11396 | 7500
500048806 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 81875 | 11396 | 7500
500048805 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 81875 | 11396 | 7500
500048804 | CLB-MP-HAUL-DT164 -ENGINE-INTEX-AIRFL | Air Filtration System | 81875 | 81875 | 7500
500048803 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-THERM | Thermostats/Regulators | 81875 | 11396 | 7500
500048802 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-BELTS | Fan Belts Engine | 81875 | 81875 | 7500
500048801 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 81875 | 11396 | 7500
500048800 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-COFAN | Fan Cooling System | 81875 | 11396 | 7500
500048799 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-RADTR | Coolant Engine | 81875 | 32833 | 7400
500048798 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-RADTR | Radiator Engine | 81875 | 11396 | 7500
500048797 | CLB-MP-HAUL-DT164 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81875 | 11396 | 7500
500048796 | CLB-MP-HAUL-DT164 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81875 | 81875 | 7500
500048795 | CLB-MP-HAUL-DT164 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81875 | 11396 | 7500
500048794 | CLB-MP-HAUL-DT164 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81875 | 81875 | 7500
500048793 | CLB-MP-HAUL-DT164 -ENGINE-COMPR | Air Compressor | 81875 | 11396 | 7500
500042636 | CLB-MP-HAUL-DT164 -ENGINE | Engine Assembly Caterpillar 3516B | 81875 | 11396 | 7500
500042625 | CLB-MP-HAUL-DT164 | DT164 Lube & Mechanical Services | 81875 | 81875 | 7500
500042624 | CLB-MP-HAUL-DT164 | Caterpillar 789D Haul Truck, DT164 | 81875 | 81875 | 7500
500160229 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITRH | Air Tank Right | 80996 | 48008 | 7500
500160228 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK-AITLH | Air Tank Left | 80996 | 48008 | 7500
500147178 | CLB-MP-HAUL-DT163 -STRSYS-STACC | Steering Accumulator Rear | 29153 | 29153 | 7500
500147177 | CLB-MP-HAUL-DT163 -STRSYS-STACC | Steering Accumulator Middle | 29153 | 29153 | 7500
500147176 | CLB-MP-HAUL-DT163 -STRSYS-STACC | Steering Accumulator Front | 29153 | 29153 | 7500
500118542 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-AFRME | A Frame Housing | 81237 | 8119 | 7500
500117918 | CLB-MP-HAUL-DT163 -ELCTLV-LIGHT | Lighting Low Voltage | 81237 | 49805 | 7500
500117878 | CLB-MP-HAUL-DT163 -ELCTLV-HARNS | Electrical Harness | 81237 | 49805 | 7500
500117838 | CLB-MP-HAUL-DT163 -AHSYST-HACAB-HATRU | Harness AHS to Truck | 81237 | 49805 | 7500
500117402 | CLB-MP-HAUL-DT163 -ELCTLV-LIGHT-AHSYS | AHS Lights | 81237 | 49805 | 7500
500117282 | CLB-MP-HAUL-DT163 -ELCTLV-HARNS-BATTY | Chassis Battery Cables | 81237 | 49805 | 7500
500111204 | CLB-MP-HAUL-DT163 -STRUCT-RAXHO | Rear Axle Housing | 83120 | 43542 | 7500
500110534 | CLB-MP-HAUL-DT163 -GRSYST | Grease Lubrication System | 81237 | 23217 | 7500
500102784 | CLB-MP-HAUL-DT163 -FDRSYS-DRSHT-UNVSL | Transmission Driveshaft Universal Joint | 81237 | 8119 | 7500
500100611 | CLB-MP-HAUL-DT163 -TRNSYS | DT163 Transmission System | 81237 | 43226 | 7500
500081388 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX-AXLRH | Drive Line Axle RH | 81237 | 29153 | 7500
500081248 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX-AXLLH | Drive Line Axle LH | 81237 | 29153 | 7500
500079421 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN | Suspension Service | 81237 | 42658 | 7500
500077922 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-FFSOS | Fast Fill and SOS Hoses | 81237 | 8119 | 7500
500077921 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-LADHO | Ladder Hoses | 81237 | 8119 | 7500
500061414 | CLB-MP-HAUL-DT163 -FDRSYS-DIFFL-DIFHO | Differential System Hoses | 81237 | 8119 | 7500
500061384 | CLB-MP-HAUL-DT163 -HYDSYS-HDHLF-HSTHO | Hoist System Hoses | 81237 | 8119 | 7500
500060884 | CLB-MP-HAUL-DT163 -STRUCT-TRAYS-TRPBU | Tray Pins And Bushes | 81237 | 53625 | 7500
500060883 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-ELECT | Chassis Electrical System | 81237 | 29153 | 7500
500060882 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-ELECT | Cabin Electrical System | 81237 | 81237 | 7500
500060881 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 81237 | 8119 | 7500
500060880 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-ACCND | Air Conditioning Condensor | 81237 | 8119 | 7500
500060879 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 81237 | 8119 | 7500
500060878 | CLB-MP-HAUL-DT163 -STRSYS-STHLF-STRHO | Steering System Hoses | 81237 | 8119 | 7500
500060877 | CLB-MP-HAUL-DT163 -STRSYS-STLTR-STBST | Ball Studs | 81237 | 81237 | 7500
500060876 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRAIR | Brake System Air Lines | 81237 | 8119 | 7500
500060875 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRHOF | Front Brake System Hoses | 81237 | 8119 | 7500
500060874 | CLB-MP-HAUL-DT163 -BRKSYS-BRHLF-BRHOR | Rear Brake System Hoses | 81237 | 8119 | 7500
500060873 | CLB-MP-HAUL-DT163 -BRKSYS-BROCO-BROCR | Brake Oil Cooler Rear | 81237 | 8119 | 7500
500060872 | CLB-MP-HAUL-DT163 -BRKSYS-BROCO-BROCF | Brake Oil Cooler Front | 81237 | 8119 | 7500
500060871 | CLB-MP-HAUL-DT163 -BRKSYS-BRVRL | Brake Relay Valve | 81237 | 8119 | 7500
500060869 | CLB-MP-HAUL-DT163 -TRNSYS-TRQUE-TRQHO | Torque Converter System Hoses | 81237 | 8119 | 7500
500060868 | CLB-MP-HAUL-DT163 -TRNSYS-TRANS-TRNHO | Transmission System Hoses | 81237 | 8119 | 7500
500060101 | CLB-MP-HAUL-DT163 -STRSYS-STTNK | Tank Steering | 81237 | 81237 | 7500
500053827 | CLB-MP-HAUL-DT163 -BRKSYS-BRVLV | Valve Brake | 81237 | 8119 | 7500
500048792 | CLB-MP-HAUL-DT163 -MANGMT-UMMMC | Mine Monitoring and Control | 81237 | 81237 | 7500
500048791 | CLB-MP-HAUL-DT163 -MANGMT-UMTRN | Power Train Management System | 81237 | 81237 | 7500
500048790 | CLB-MP-HAUL-DT163 -MANGMT-UMENG | Engine Management System | 81237 | 81237 | 7500
500048789 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYRR | Cylinder Suspension R/H Rear | 81237 | 8119 | 7500
500048788 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYLR | Cylinder Suspension L/H Rear | 81237 | 8119 | 7500
500048787 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYRF | Cylinder Suspension R/H Front | 81237 | 8119 | 7500
500048786 | CLB-MP-HAUL-DT163 -STRUCT-SUSPN-SCYLF | Cylinder Suspension L/H Front | 81237 | 20804 | 7500
500048783 | CLB-MP-HAUL-DT163 -STRUCT-TRAYS | Tray | 81237 | 21179 | 7500
500048782 | CLB-MP-HAUL-DT163 -STRUCT-AXLES-HUBRH | Hub and Spindle R/H | 81237 | 8119 | 7500
500048781 | CLB-MP-HAUL-DT163 -STRUCT-AXLES-HUBLH | Hub and Spindle L/H | 81237 | 14273 | 7500
500048780 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-TAGLK | Tag Link | 81237 | 8119 | 7500
500048779 | CLB-MP-HAUL-DT163 -STRUCT-CHASS-AFRME | A Frame Bearing | 81237 | 8119 | 7500
500048778 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-SBELT | Seat Belt | 81237 | 81237 | 7500
500048777 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-SEATS | Operators Seat | 81237 | 35534 | 7500
500048776 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 81237 | 81237 | 7500
500048775 | CLB-MP-HAUL-DT163 -STRUCT-CABIN-AIRCN | Air Conditioning System | 81237 | 8119 | 7500
500048774 | CLB-MP-HAUL-DT163 -STRUCT-CABIN | Operators Cabin | 81237 | 8119 | 7500
500048773 | CLB-MP-HAUL-DT163 -PNEUMC-START | Air Starter | 81237 | 8119 | 7500
500048772 | CLB-MP-HAUL-DT163 -PNEUMC-AIRDR | Air Drier | 81237 | 8119 | 7500
500048771 | CLB-MP-HAUL-DT163 -PNEUMC-BRVLR-ARCRR | Auto Retard Control Relay Rear | 81237 | 81237 | 7500
500048770 | CLB-MP-HAUL-DT163 -PNEUMC-BRVLR-SVBRF | Service Brake Relay Front | 81237 | 81237 | 7500
500048769 | CLB-MP-HAUL-DT163 -PNEUMC-PNTNK | No Not Use | 81237 | 48249 | 7500
500048768 | CLB-MP-HAUL-DT163 -GRSYST-ALCON | Auto Lube Controller | 81237 | 81237 | 7500
500048767 | CLB-MP-HAUL-DT163 -GRSYST-ALBPP | Auto Lube Pump | 81237 | 20136 | 7500
500048766 | CLB-MP-HAUL-DT163 -GRSYST-GRTNK | Auto Lube Resevoir | 81237 | 81237 | 7500
500048765 | CLB-MP-HAUL-DT163 -GRSYST-GRINJ | Auto Lube Injectors | 81237 | 81237 | 7500
500048764 | CLB-MP-HAUL-DT163 -HYDSYS-HOCYL-HCYLR | Cylinder Hoist R/H | 81237 | 8119 | 7500
500048763 | CLB-MP-HAUL-DT163 -HYDSYS-HOCYL-HCYLL | Cylinder Hoist L/H | 81237 | 8119 | 7500
500048762 | CLB-MP-HAUL-DT163 -HYDSYS-HOVLV | Valve Hoist | 81237 | 8119 | 7500
500048761 | CLB-MP-HAUL-DT163 -HYDSYS-HDOCO | Oil Cooler Hydraulic | 81237 | 81237 | 7500
500048760 | CLB-MP-HAUL-DT163 -HYDSYS-HDTNK | Tank Hydraulic | 81237 | 81237 | 7500
500048759 | CLB-MP-HAUL-DT163 -HYDSYS-TOWPP | Pump Towing (Electric Brake Release) | 81237 | 8119 | 7500
500048758 | CLB-MP-HAUL-DT163 -HYDSYS-HOPMP | Pump Hoist | 81237 | 8119 | 7500
500048757 | CLB-MP-HAUL-DT163 -HYDSYS | Hydraulic System | 81237 | 81237 | 7500
500048756 | CLB-MP-HAUL-DT163 -STRSYS-STCON-STCOL | Steering Column | 81237 | 81237 | 7500
500048755 | CLB-MP-HAUL-DT163 -STRSYS-STCON-STWHL | Steering Wheel | 81237 | 81237 | 7500
500048754 | CLB-MP-HAUL-DT163 -STRSYS-STLTR | Steering Linkages and Tie Rods | 81237 | 12238 | 7500
500048753 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCR | Accumulator Steering Rear | 81237 | 8119 | 7500
500048752 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCM | Accumulator Steering Middle | 81237 | 8119 | 7500
500048751 | CLB-MP-HAUL-DT163 -STRSYS-STACC-SACCF | Accumulator Steering Front | 81237 | 8119 | 7500
500048750 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYR | Cylinder Steering R/H | 81237 | 12238 | 7500
500048749 | CLB-MP-HAUL-DT163 -STRSYS-STRCY-STCYL | Cylinder Steering L/H | 81237 | 12238 | 7500
500048748 | CLB-MP-HAUL-DT163 -STRSYS-STVLV | Valve Steering | 81237 | 8119 | 7500
500048747 | CLB-MP-HAUL-DT163 -STRSYS-STHMU | Steering HMU | 81237 | 895 | 7500
500048746 | CLB-MP-HAUL-DT163 -STRSYS-STPMP | Pump Steering | 81237 | 895 | 7500
500048745 | CLB-MP-HAUL-DT163 -BRKSYS-SLACK-SLACR | Brake Slack Adjuster Rear | 81237 | 8119 | 7500
500048744 | CLB-MP-HAUL-DT163 -BRKSYS-SLACK-SLACF | Brake Slack Adjuster Front | 81237 | 8119 | 7500
500048743 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTRR | Rotochamber R/H Rear | 81237 | 8119 | 7500
500048742 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTLR | Rotochamber L/H Rear | 81237 | 8119 | 7500
500048741 | CLB-MP-HAUL-DT163 -BRKSYS-BRCYL-ROTFR | Rotochamber Front | 81237 | 8119 | 7500
500048740 | CLB-MP-HAUL-DT163 -BRKSYS-BACCM | Brake Accumulator | 81237 | 8119 | 7500
500048739 | CLB-MP-HAUL-DT163 -BRKSYS-BROCO | Brake Oil Cooler | 81237 | 81237 | 7500
500048738 | CLB-MP-HAUL-DT163 -BRKSYS-MERTR | Mechanical Retarder | 81237 | 81237 | 7500
500048737 | CLB-MP-HAUL-DT163 -BRKSYS-BRVTR | Valve Brake Treadle | 81237 | 81237 | 7500
500048736 | CLB-MP-HAUL-DT163 -BRKSYS-HYFPP | Pump Brake Control | 81237 | 8119 | 7500
500048735 | CLB-MP-HAUL-DT163 -BRKSYS-PRKPP | Pump Park Brake Release | 81237 | 81237 | 7500
500048734 | CLB-MP-HAUL-DT163 -BRKSYS-BRPMP | Pump Brake | 81237 | 81237 | 7500
500048733 | CLB-MP-HAUL-DT163 -BRKSYS-SRVBK-SVBRR | Service Brake R/H Rear | 81237 | 81237 | 7500
500048732 | CLB-MP-HAUL-DT163 -BRKSYS-SRVBK-SVBLR | Service Brake L/H Rear | 81237 | 81237 | 7500
500048731 | CLB-MP-HAUL-DT163 -BRKSYS-SRVBK-SVBRF | Service Brake R/H Front | 81237 | 81237 | 7500
500048730 | CLB-MP-HAUL-DT163 -BRKSYS-SRVBK-SVBLF | Service Brake L/H Front | 81237 | 81237 | 7500
500048729 | CLB-MP-HAUL-DT163 -BRKSYS-SRVBK | Service Brake | 81237 | 81237 | 7500
500048728 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-OILCO | Axle Oil Cooler Core | 81237 | 81237 | 7500
500048727 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-HYPUM | Axle Lube Pump | 81237 | 81237 | 7500
500048726 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-MTFAN | Axle Oil Cooler Fan Motor | 81237 | 8119 | 7500
500048725 | CLB-MP-HAUL-DT163 -FDRSYS-AXLEC-HYM01 | Axle Lube Motor | 81237 | 8119 | 7500
500048724 | CLB-MP-HAUL-DT163 -FDRSYS-FDRVE-FDRRH | Final Drive R/H | 81237 | 9365 | 7500
500048723 | CLB-MP-HAUL-DT163 -FDRSYS-FDRVE-FDRLH | Final Drive L/H | 81237 | 116 | 7500
500048722 | CLB-MP-HAUL-DT163 -FDRSYS-DRLAX | Drive Line Axles | 81237 | 81237 | 7500
500048721 | CLB-MP-HAUL-DT163 -FDRSYS-DIFFL | Differential | 81237 | 8119 | 7500
500048720 | CLB-MP-HAUL-DT163 -FDRSYS-DRSHT | Transmission Drive Shaft | 81237 | 8119 | 7500
500048719 | CLB-MP-HAUL-DT163 -TRNSYS-TROLC | Oil Cooler Transmission | 81237 | 8119 | 7500
500048718 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TCCPP | Pump Torque Converter | 81237 | 8119 | 7500
500048717 | CLB-MP-HAUL-DT163 -TRNSYS-TRPMP-TMCPP | Pump Transmission | 81237 | 9334 | 7500
500048716 | CLB-MP-HAUL-DT163 -TRNSYS-TRANS | Transmission | 81237 | 9334 | 7500
500048715 | CLB-MP-HAUL-DT163 -TRNSYS-TRQUE | Torque Converter | 81237 | 9351 | 7500
500048714 | CLB-MP-HAUL-DT163 -ELCTLV-CHARG-BATTY | Batteries | 81237 | 52986 | 7500
500048713 | CLB-MP-HAUL-DT163 -ELCTLV-CHARG-ALTER | Alternator 24V | 81237 | 1581 | 7500
500048712 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR-DRSHT | Drive Shaft Pump Drive | 81237 | 8119 | 7500
500048711 | CLB-MP-HAUL-DT163 -ENGINE-PMPDR | Pump Drive | 81237 | 8119 | 7500
500048710 | CLB-MP-HAUL-DT163 -ENGINE-FUSYS-FUINJ | Fuel Injectors | 81237 | 8119 | 7500
500048709 | CLB-MP-HAUL-DT163 -ENGINE-FUSYS-FULTP | Fuel Transfer Pump | 81237 | 8119 | 7500
500048708 | CLB-MP-HAUL-DT163 -ENGINE-FUSYS-FULPP | Fuel Priming Pump | 81237 | 8119 | 7500
500048707 | CLB-MP-HAUL-DT163 -ENGINE-FUSYS-FULTK | Fuel Tank | 81237 | 8119 | 7500
500048706 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-EXHST | Exhaust System | 81237 | 81237 | 7500
500048705 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-AFTER | Aftercooler | 81237 | 81237 | 7500
500048704 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-TBORR | Turbocharger R/H Rear | 81237 | 8119 | 7500
500048703 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-TBORF | Turbocharger R/H Front | 81237 | 8119 | 7500
500048702 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-TBOLR | Turbocharger L/H Rear | 81237 | 8119 | 7500
500048701 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-TBOLF | Turbocharger L/H Front | 81237 | 8119 | 7500
500048700 | CLB-MP-HAUL-DT163 -ENGINE-INTEX-AIRFL | Air Filtration System | 81237 | 81237 | 7500
500048699 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-THERM | Thermostats/Regulators | 81237 | 8119 | 7500
500048698 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-BELTS | Fan Belts Engine | 81237 | 81237 | 7500
500048697 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-ACWEP | Water Pump Aftercooler | 81237 | 8119 | 7500
500048696 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-COFAN | Fan Cooling System | 81237 | 8119 | 7500
500048695 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-RADTR | Coolant Engine | 81237 | 29153 | 7400
500048694 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-RADTR | Radiator Engine | 81237 | 8119 | 7500
500048693 | CLB-MP-HAUL-DT163 -ENGINE-COSYS-WTRPP | Water Pump Engine | 81237 | 8119 | 7500
500048692 | CLB-MP-HAUL-DT163 -ENGINE-LUBSY-ENOLC | Oil Cooler Engine | 81237 | 81237 | 7500
500048691 | CLB-MP-HAUL-DT163 -ENGINE-LUBSY-PREPP | Oil Pump Prelube | 81237 | 8119 | 7500
500048690 | CLB-MP-HAUL-DT163 -ENGINE-LUBSY-OILPP | Oil Pump Engine | 81237 | 81237 | 7500
500048689 | CLB-MP-HAUL-DT163 -ENGINE-COMPR | Air Compressor | 81237 | 8119 | 7500
500042634 | CLB-MP-HAUL-DT163 -ENGINE | Engine Assembly Caterpillar 3516B | 81237 | 8119 | 7500
500042623 | CLB-MP-HAUL-DT163 | DT163 Lube & Mechanical Services | 81237 | 81237 | 7500
500042622 | CLB-MP-HAUL-DT163 | Caterpillar 789D Haul Truck, DT163 | 81237 | 81237 | 7500
500043044 | CLB-MP-EXCV-EX109 -TRAVEL-TRKRH | Track Assembly RH | 7886 | 5149 | 530
500043037 | CLB-MP-EXCV-EX109 -TRAVEL-TRKLH | Track Assembly LH | 7886 | 5149 | 530
500065150 | CLB-MP-EXCV-EX109 -TRAVEL | 6060 Excavator, EX109 TRAVEL HOURS | 7886 | 7886 | 530
500146756 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC | Hydraulic Ladder Accumulator | 86287 | 86287 | 7500
500146755 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 86287 | 86287 | 7500
500146754 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC | Track Tension Accumulator RH | 31705 | 31705 | 7500
500146753 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC | Track Tension Accumulator LH | 32371 | 32371 | 7500
500139320 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 27286 | 4238 | 7500
500106257 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-CBMNT | Cabin Mount | 86287 | 86287 | 7500
500106256 | CLB-MP-EXCV-EX109 -STRUCT-HLINK-LINKR | Banana Linkage R/H | 86287 | 12366 | 7500
500106255 | CLB-MP-EXCV-EX109 -STRUCT-HLINK-LINKL | Banana Linkage L/H | 86287 | 12366 | 7500
500106197 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-FLUVV | Flushing Valves | 86287 | 8815 | 7500
500106196 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SCBVV | Swing Counterbalance Valve | 86287 | 6790 | 7500
500106195 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SWBVV | Swing Blocking Valves | 86287 | 37546 | 7500
500106194 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-PROVV | PMS Proportional Valves | 86287 | 11607 | 7500
500106193 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SWSVV | Swing Safety Valves | 86287 | 11607 | 7500
500106192 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SSEVV | Seat/Servo Valve | 86287 | 19651 | 7500
500106191 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SSBVV | Second Speed and Swing Brake release Val | 86287 | 7874 | 7500
500106190 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SPRVV | Servo Proportional Valve | 86287 | 37546 | 7500
500106189 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-BFLVV | Boom Float Valve | 86287 | 17119 | 7500
500106188 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-MRVMC | Main Hydraulic Relief Valves | 86287 | 86287 | 7500
500106165 | CLB-MP-EXCV-EX109 -STRUCT-SRVCT | Service Centre | 86287 | 22258 | 7500
500106058 | CLB-MP-EXCV-EX109 -GRSYST-STGRS | Stick Grease System | 86287 | 86287 | 7500
500106057 | CLB-MP-EXCV-EX109 -GRSYST-HLGRS | H-Link Grease System | 86287 | 86287 | 7500
500106056 | CLB-MP-EXCV-EX109 -GRSYST-BOGRS | Boom Grease System | 86287 | 86287 | 7500
500106055 | CLB-MP-EXCV-EX109 -GRSYST-ALBSS | Grease system Super Structure | 86287 | 627 | 7500
500105940 | CLB-MP-EXCV-EX109 -HYDSYS-PPDRR-PDOCR | PDrive Gbox Oil Cooler RH | 86287 | 627 | 7500
500105939 | CLB-MP-EXCV-EX109 -HYDSYS-PPDRL-PDOCL | PDrive Gbox Oil Cooler LH | 86287 | 627 | 7500
500105938 | CLB-MP-EXCV-EX109 -RHENGN-FUSYS-FUCRH | Fuel Cooler RH | 86287 | 86287 | 7500
500105937 | CLB-MP-EXCV-EX109 -LHENGN-FUSYS-FUCLH | Fuel Cooler LH | 86287 | 86287 | 7500
500104286 | CLB-MP-EXCV-EX109 -HYDSYS | Hydraulic System | 86287 | 1478 | 7500
500102363 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-BATTY | EX109 Batteries | 86287 | 4238 | 7500
500101494 | CLB-MP-EXCV-EX109 -HYDSYS | Hydraulic Oil | 86287 | 5779 | 7500
500079331 | CLB-MP-EXCV-EX109 -STRUCT-HLINK | H Link Assembly | 86287 | 12366 | 7500
500063166 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-TCVVR | Travel Control Valve RH | 86287 | 45146 | 7500
500063165 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-TCVVL | Travel Control Valve LH | 86287 | 45146 | 7500
500060078 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-TRTN | Track Tensioning Hoses | 86287 | 2578 | 7500
500060077 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-TMCD | Travel Motor Case Drain Hoses | 86287 | 2578 | 7500
500060076 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 86287 | 10544 | 7500
500060075 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 86287 | 4238 | 7500
500060074 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SWBRK | Swing Brake Hoses | 86287 | 10544 | 7500
500060073 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 86287 | 9687 | 7500
500060072 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 86287 | 627 | 7500
500060071 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 86287 | 9687 | 7500
500060070 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-RCDM | Rotary Coupling to Drive Motor Hoses | 86287 | 2578 | 7500
500060069 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 86287 | 8815 | 7500
500060068 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 86287 | 21570 | 7500
500060067 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-MPRC | Main Pump to Rotary Coupling HP Hoses | 86287 | 627 | 7500
500060066 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-MCVCR | MCV Cradle Hoses | 86287 | 7874 | 7500
500060065 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 86287 | 627 | 7500
500060064 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-HCFC | Hydraulic Cooling Fan Circulation Hoses | 86287 | 4238 | 7500
500060063 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-FDEC | Fan Drive Circut for Eng Cooling Hoses | 86287 | 10544 | 7500
500060062 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 86287 | 5779 | 7500
500060061 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-BMAR | Boom Arch Hoses | 86287 | 4238 | 7500
500060060 | CLB-MP-EXCV-EX109 -HYDSYS-HDHLF-2STBR | 2nd Speed Travel / Brake Release Hoses | 86287 | 9687 | 7500
500059816 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SRVRU | Secondary Relief Valves R/H Upper MCV | 86264 | 55856 | 7500
500059815 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SRVRL | Secondary Relief Valves R/H Lower MCV | 86264 | 55856 | 7500
500059814 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SRVLU | Secondary Relief Valves L/H Upper MCV | 86264 | 55856 | 7500
500059813 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-SRVLL | Secondary Relief Valves L/H Lower MCV | 86264 | 55856 | 7500
500059328 | CLB-MP-EXCV-EX109 -GRSYST-ALBPU | Auto Lube Pump Undercarriage | 86287 | 4965 | 7500
500043149 | CLB-MP-EXCV-EX109 -MANGMT-UMPMP | Pump Management System | 86287 | 86287 | 7500
500043148 | CLB-MP-EXCV-EX109 -MANGMT-UMBRD | Board Control System | 86287 | 86287 | 7500
500043147 | CLB-MP-EXCV-EX109 -MANGMT-UMMMC | Mine Monitoring and Control | 86287 | 4238 | 7500
500043146 | CLB-MP-EXCV-EX109 -MANGMT-UMENG | Engine Management System | 86287 | 86287 | 7500
500043145 | CLB-MP-EXCV-EX109 -FRSUPP-FSALM | Fire System Alarm | 86287 | 86287 | 7500
500043144 | CLB-MP-EXCV-EX109 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 86287 | 86287 | 7500
500043143 | CLB-MP-EXCV-EX109 -GRSYST-ALCON | Auto Lube Controller | 86287 | 86287 | 7500
500043142 | CLB-MP-EXCV-EX109 -GRSYST-ALBPP | Auto Lube Pump | 86287 | 4965 | 7500
500043141 | CLB-MP-EXCV-EX109 -GRSYST-GRINJ | Auto Lube Injectors | 86287 | 86287 | 7500
500043140 | CLB-MP-EXCV-EX109 -STRUCT-UNDER-SLEWB | Slew Bearing | 86287 | 43736 | 7500
500043139 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-CARRR | Roller Carrier RH Rear | 86287 | 14630 | 7500
500043138 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-CARRF | Roller Carrier RH Front | 86287 | 24205 | 7500
500043137 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH7 | Roller Load Pos 7 RH | 86287 | 27980 | 7500
500043136 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH6 | Roller Load Pos 6 RH | 86287 | 28638 | 7500
500043135 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH5 | Roller Load Pos 5 RH | 86287 | 21570 | 7500
500043134 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH4 | Roller Load Pos 4 RH | 86287 | 12366 | 7500
500043133 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH3 | Roller Load Pos 3 RH | 86287 | 12366 | 7500
500043132 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH2 | Roller Load Pos 2 RH | 86287 | 86287 | 7500
500043131 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-LORH1 | Roller Load Pos 1 RH | 86287 | 14162 | 7500
500043130 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-TENSR | Track Tensioner RH | 86287 | 20307 | 7500
500043129 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR-IDLRH | Idler Track RH | 86287 | 14630 | 7500
500043128 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-CARLR | Roller Carrier LH Rear | 86287 | 24205 | 7500
500043127 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-CARLF | Roller Carrier LH Front | 86287 | 25352 | 7500
500043126 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 LH | 86287 | 30403 | 7500
500043125 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 LH | 86287 | 30403 | 7500
500043124 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 LH | 86287 | 33672 | 7500
500043123 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 LH | 86287 | 20557 | 7500
500043122 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 LH | 86287 | 40654 | 7500
500043121 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 LH | 86287 | 31705 | 7500
500043120 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 LH | 86287 | 48924 | 7500
500043119 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-TENSR | Track Tensioner LH | 86287 | 20307 | 7500
500043118 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL-IDLLH | Idler Track LH | 86287 | 23004 | 7500
500043116 | CLB-MP-EXCV-EX109 -STRUCT-BUCKT | Bucket | 86287 | 12366 | 7500
500043115 | CLB-MP-EXCV-EX109 -STRUCT-STICK | Stick Assembly | 86287 | 49603 | 7500
500043114 | CLB-MP-EXCV-EX109 -STRUCT-BOOMS | Boom Assembly | 86287 | 49603 | 7500
500043113 | CLB-MP-EXCV-EX109 -STRUCT-STLAD-SLAUT | Automatic Access Systems | 86287 | 8845 | 7500
500043112 | CLB-MP-EXCV-EX109 -STRUCT-SUPER-ROLTK | Reserve Oil Tank | 86287 | 86287 | 7500
500043111 | CLB-MP-EXCV-EX109 -STRUCT-SUPER-CWEIG | Counterweight | 86287 | 86287 | 7500
500043110 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-GLASS | Seat Belt | 86287 | 86287 | 7500
500043109 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-SEATS | Operators Seat | 86287 | 3339 | 7500
500043108 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86287 | 86287 | 7500
500043107 | CLB-MP-EXCV-EX109 -STRUCT-CABIN-AIRCR | Air Conditioning System | 86287 | 4965 | 7500
500043106 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC-HACCR | Accumulator Hydraulic RH | 86287 | 13053 | 7500
500043105 | CLB-MP-EXCV-EX109 -HYDSYS-HDACC-HACCL | Accumulator Hydraulic LH | 86287 | 14649 | 7500
500043104 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-TRMRR | Motor Travel RH Rear | 86287 | 5779 | 7500
500043103 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-TRMRF | Motor Travel RH Front | 86287 | 5779 | 7500
500043102 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-TRMLR | Motor Travel LH Rear | 86287 | 9623 | 7500
500043101 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-TRMLF | Motor Travel LH Front | 86287 | 5779 | 7500
500043100 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-FMECR | Motor Fan Engine Cooling RH | 86287 | 2590 | 7500
500043099 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-FMECL | Motor Fan Engine Cooling LH | 86287 | 2590 | 7500
500043098 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-FHCTR | Motor Fan Hydraulic Cooling Top Rear | 86287 | 6808 | 7500
500043097 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-FHCTF | Motor Fan Hydraulic Cooling Top Front | 86287 | 3339 | 7500
500043096 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-FHCBR | Motor Fan Hydraulic Cooling Bottom Rear | 86287 | 627 | 7500
500043095 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-FHCBF | Motor Fan Hydraulic Cooling Bottom Front | 86287 | 7874 | 7500
500043094 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMRR | Motor Swing RH Rear | 86287 | 12366 | 7500
500043093 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMRF | Motor Swing RH Front | 86287 | 12366 | 7500
500043092 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMLR | Motor Swing LH Rear | 86287 | 12366 | 7500
500043091 | CLB-MP-EXCV-EX109 -HYDSYS-HDMOT-SWMLF | Motor Swing LH Front | 86287 | 5779 | 7500
500043090 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-MCVRU | Main Control Valve Block RH Upper | 86287 | 26028 | 7500
500043089 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-MCVRL | Main Control Valve Block RH Lower | 86287 | 26028 | 7500
500043088 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-MCVLU | Main Control Valve Block LH Upper | 86287 | 26028 | 7500
500043087 | CLB-MP-EXCV-EX109 -HYDSYS-HDVLV-MCVLL | Main Control Valve Block LH Lower | 86287 | 26028 | 7500
500043086 | CLB-MP-EXCV-EX109 -HYDSYS-ROTRY | Rotary Joint | 86287 | 21523 | 7500
500043085 | CLB-MP-EXCV-EX109 -HYDSYS-HDOCO-OCHRR | Oil Cooler Hydraulic Rear | 86287 | 4238 | 7500
500043084 | CLB-MP-EXCV-EX109 -HYDSYS-HDOCO-OCHFR | Oil Cooler Hydraulic Front | 86287 | 16471 | 7500
500043081 | CLB-MP-EXCV-EX109 -HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 86287 | 11544 | 7500
500043080 | CLB-MP-EXCV-EX109 -HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 86254 | 7874 | 7500
500043079 | CLB-MP-EXCV-EX109 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 86287 | 4238 | 7500
500043078 | CLB-MP-EXCV-EX109 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 86287 | 6790 | 7500
500043077 | CLB-MP-EXCV-EX109 -HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 86287 | 17119 | 7500
500043076 | CLB-MP-EXCV-EX109 -HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 86287 | 5779 | 7500
500043075 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing RH | 86287 | 6790 | 7500
500043074 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing LH | 86287 | 4965 | 7500
500043073 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP4 | Pump Servo Position 4 | 86287 | 627 | 7500
500043072 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP3 | Pump Servo Position 3 | 86287 | 627 | 7500
500043071 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP2 | Pump Servo Position 2 | 86287 | 4238 | 7500
500043070 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SVPP1 | Pump Servo Position 1 | 86287 | 4965 | 7500
500043069 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-FPECR | Pump Fan Engine Cooling RH | 86287 | 627 | 7500
500043068 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-FPECL | Pump Fan Engine Cooling LH | 86287 | 627 | 7500
500043067 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-FPHC4 | Pump Fan Hydraulic Cooling Pos 4 | 86276 | 6790 | 7500
500043066 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-FPHC3 | Pump Fan Hydraulic Cooling Pos 3 | 86287 | 6790 | 7500
500043065 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-FPHC2 | Pump Fan Hydraulic Cooling Pos 2 | 86287 | 6808 | 7500
500043064 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-FPHC1 | Pump Fan Hydraulic Cooling Pos 1 | 86287 | 5779 | 7500
500043063 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SWPP4 | Pump Swing Position 4 | 86287 | 627 | 7500
500043062 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SWPP3 | Pump Swing Position 3 | 86287 | 78 | 7500
500043061 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SWPP2 | Pump Swing Position 2 | 86287 | 6808 | 7500
500043060 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-SWPP1 | Pump Swing Position 1 | 86287 | 627 | 7500
500043059 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-MP7P8 | Pump Main Position 4 | 86287 | 4965 | 7500
500043058 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-MP5P6 | Pump Main Position 3 | 86287 | 627 | 7500
500043057 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-MP3P4 | Pump Main Position 2 | 86287 | 627 | 7500
500043056 | CLB-MP-EXCV-EX109 -HYDSYS-HYDPP-MP1P2 | Pump Main Position 1 | 86287 | 627 | 7500
500043055 | CLB-MP-EXCV-EX109 -HYDSYS-PPDRR | Pump Drive Gearbox RH | 86287 | 6808 | 7500
500043054 | CLB-MP-EXCV-EX109 -HYDSYS-PPDRL | Pump Drive Gearbox LH | 86282 | 17797 | 7500
500043053 | CLB-MP-EXCV-EX109 -SWGSYS-SWLUB | Swing System Lubrication | 86287 | 86287 | 7500
500043052 | CLB-MP-EXCV-EX109 -SWGSYS-SWBRK-SBKRR | Brake Swing RH Rear | 86287 | 19651 | 7500
500043051 | CLB-MP-EXCV-EX109 -SWGSYS-SWBRK-SBKRF | Brake Swing RH Front | 86287 | 19093 | 7500
500043050 | CLB-MP-EXCV-EX109 -SWGSYS-SWBRK-SBKLR | Brake Swing LH Front | 86287 | 1478 | 7500
500043049 | CLB-MP-EXCV-EX109 -SWGSYS-SWBRK-SBKLF | Brake Swing LH Rear | 86287 | 19651 | 7500
500043048 | CLB-MP-EXCV-EX109 -SWGSYS-SWBOX-SGBRR | Gearbox Swing RH Rear | 86287 | 17797 | 7500
500043047 | CLB-MP-EXCV-EX109 -SWGSYS-SWBOX-SGBRF | Gearbox Swing RH Front | 86287 | 19093 | 7500
500043046 | CLB-MP-EXCV-EX109 -SWGSYS-SWBOX-SGBLR | Gearbox Swing LH Rear | 86287 | 12366 | 7500
500043045 | CLB-MP-EXCV-EX109 -SWGSYS-SWBOX-SGBLF | Gearbox Swing LH Front | 86287 | 19093 | 7500
500043043 | CLB-MP-EXCV-EX109 -TRAVEL-TRBKR-TBKRR | Brake Travel RH Rear | 86287 | 86287 | 7500
500043042 | CLB-MP-EXCV-EX109 -TRAVEL-TRBKR-TBKRF | Brake Travel RH Front | 86287 | 86287 | 7500
500043041 | CLB-MP-EXCV-EX109 -TRAVEL-SPRKR | Sprocket RH | 86287 | 27980 | 7500
500043040 | CLB-MP-EXCV-EX109 -TRAVEL-FDRRH | Final Drive RH | 86287 | 27980 | 7500
500043039 | CLB-MP-EXCV-EX109 -TRAVEL-TRBKL-TBKLR | Brake Travel LH Rear | 86287 | 86287 | 7500
500043038 | CLB-MP-EXCV-EX109 -TRAVEL-TRBKL-TBKLF | Brake Travel LH Front | 86287 | 86287 | 7500
500043036 | CLB-MP-EXCV-EX109 -TRAVEL-SPRKL | Sprocket LH | 86287 | 37043 | 7500
500043035 | CLB-MP-EXCV-EX109 -TRAVEL-FDRLH | Final Drive LH | 86287 | 13053 | 7500
500043034 | CLB-MP-EXCV-EX109 -ELCTLV-START-STMRU | Starter Motor RH Engine Upper | 86287 | 5779 | 7500
500043033 | CLB-MP-EXCV-EX109 -ELCTLV-START-STMRL | Starter Motor RH Engine Lower | 86287 | 5779 | 7500
500043032 | CLB-MP-EXCV-EX109 -ELCTLV-START-STMLU | Starter Motor LH Engine Upper | 86287 | 7874 | 7500
500043031 | CLB-MP-EXCV-EX109 -ELCTLV-START-STMLL | Starter Motor LH Engine Lower | 86287 | 7874 | 7500
500043028 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-ALTRH | Alternator 24V RH Engine | 86287 | 4965 | 7500
500043027 | CLB-MP-EXCV-EX109 -ELCTLV-CHARG-ALTLH | Alternator 24V LH Engine | 86287 | 627 | 7500
500043026 | CLB-MP-EXCV-EX109 -RHENGN-COUPL | RH Engine Coupling | 86287 | 17797 | 7500
500043025 | CLB-MP-EXCV-EX109 -RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 86287 | 5779 | 7500
500043024 | CLB-MP-EXCV-EX109 -RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 86287 | 5779 | 7500
500043023 | CLB-MP-EXCV-EX109 -RHENGN-INTEX-AFTER | RH Engine Aftercooler | 86287 | 36731 | 7500
500043022 | CLB-MP-EXCV-EX109 -RHENGN-INTEX-TBORH | RH EngineTurbocharger RH Side | 86287 | 5779 | 7500
500043021 | CLB-MP-EXCV-EX109 -RHENGN-INTEX-TBOLH | RH EngineTurbocharger LH Side | 86287 | 5779 | 7500
500043020 | CLB-MP-EXCV-EX109 -RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 86287 | 5779 | 7500
500043019 | CLB-MP-EXCV-EX109 -RHENGN-COSYS-RADTR | RH Engine Radiator | 86287 | 8516 | 7500
500043018 | CLB-MP-EXCV-EX109 -RHENGN-COSYS-AWPRH | RH Engine Water Pump Aftercooler | 86287 | 5779 | 7500
500043017 | CLB-MP-EXCV-EX109 -RHENGN-COSYS-WTRPP | RH Engine Water Pump | 86287 | 5779 | 7500
500043016 | CLB-MP-EXCV-EX109 -RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 86287 | 36731 | 7500
500043015 | CLB-MP-EXCV-EX109 -RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 86287 | 17797 | 7500
500043013 | CLB-MP-EXCV-EX109 -RHENGN | RH Engine Assembly Cummins QSK45 | 86287 | 17797 | 7500
500043012 | CLB-MP-EXCV-EX109 -LHENGN-COUPL | LH Engine Coupling | 86287 | 17797 | 7500
500043011 | CLB-MP-EXCV-EX109 -LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 86287 | 7874 | 7500
500043010 | CLB-MP-EXCV-EX109 -LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 86287 | 7874 | 7500
500043009 | CLB-MP-EXCV-EX109 -LHENGN-INTEX-AFTER | LH Engine Aftercooler | 86287 | 38684 | 7500
500043008 | CLB-MP-EXCV-EX109 -LHENGN-INTEX-TBORH | LH Engine Turbocharger RH Side | 86287 | 7874 | 7500
500043007 | CLB-MP-EXCV-EX109 -LHENGN-INTEX-TBOLH | LH Engine Turbocharger LH Side | 86287 | 7874 | 7500
500043006 | CLB-MP-EXCV-EX109 -LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 86287 | 7874 | 7500
500043005 | CLB-MP-EXCV-EX109 -LHENGN-COSYS-RADTR | LH Engine Radiator | 86287 | 10544 | 7500
500043004 | CLB-MP-EXCV-EX109 -LHENGN-COSYS-AWPLH | LH Engine Water Pump Aftercooler | 86287 | 7874 | 7500
500043003 | CLB-MP-EXCV-EX109 -LHENGN-COSYS-WTRPP | LH Engine Water Pump | 86287 | 7874 | 7500
500043002 | CLB-MP-EXCV-EX109 -LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 86287 | 38684 | 7500
500043001 | CLB-MP-EXCV-EX109 -LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 86287 | 17797 | 7500
500042999 | CLB-MP-EXCV-EX109 -LHENGN | LH Engine Assembly Cummins QSK45 | 86287 | 17797 | 7500
500036293 | CLB-MP-EXCV-EX109 | EX109 Lubrication & Mechanical Services | 86287 | 86287 | 7500
500036292 | CLB-MP-EXCV-EX109 | Caterpillar 6060 Excavator, EX109 | 86287 | 86287 | 7500
500042893 | CLB-MP-EXCV-EX108 -TRAVEL-TRKRH | Track Assembly RH | 30899 | 2810 | 530
500042886 | CLB-MP-EXCV-EX108 -TRAVEL-TRKLH | Track Assembly LH | 30899 | 2810 | 530
500065149 | CLB-MP-EXCV-EX108 -TRAVEL | 6060 Excavator, EX108 TRAVEL HOURS | 7398 | 7398 | 530
500146752 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC | Hydraulic Ladder Accumulator | 79029 | 79029 | 7500
500146751 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 79029 | 79029 | 7500
500146750 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC | Track Tension Accumulator RH | 14990 | 14990 | 7500
500146749 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC | Track Tension Accumulator LH | 33833 | 33833 | 7500
500139319 | CLB-MP-EXCV-EX108 -STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 27163 | 11955 | 7500
500106254 | CLB-MP-EXCV-EX108 -STRUCT-CABIN-CBMNT | Cabin Mount | 79029 | 79029 | 7500
500106253 | CLB-MP-EXCV-EX108 -STRUCT-HLINK-LINKR | Banana Linkage R/H | 79029 | 79029 | 7500
500106252 | CLB-MP-EXCV-EX108 -STRUCT-HLINK-LINKL | Banana Linkage L/H | 79029 | 79029 | 7500
500106187 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-FLUVV | Flushing Valves | 79029 | 11173 | 7500
500106186 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SCBVV | Swing Counterbalance Valve | 79029 | 79029 | 7500
500106185 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SWBVV | Swing Blocking Valves | 79029 | 35076 | 7500
500106184 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-PROVV | PMS Proportional Valves | 79029 | 9644 | 7500
500106183 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SWSVV | Swing Safety Valves | 79029 | 9644 | 7500
500106182 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SSEVV | Seat/Servo Valve | 79029 | 11173 | 7500
500106181 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SSBVV | Second Speed and Swing Brake release Val | 79029 | 9644 | 7500
500106180 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SPRVV | Servo Proportional Valve | 79029 | 9644 | 7500
500106179 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-BFLVV | Boom Float Valve | 79029 | 15911 | 7500
500106178 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-MRVMC | Main Hydraulic Relief Valves | 79029 | 79029 | 7500
500106164 | CLB-MP-EXCV-EX108 -STRUCT-SRVCT | Service Centre | 79029 | 12704 | 7500
500106054 | CLB-MP-EXCV-EX108 -GRSYST-STGRS | Stick Grease System | 79029 | 79029 | 7500
500106053 | CLB-MP-EXCV-EX108 -GRSYST-HLGRS | H-Link Grease System | 79029 | 79029 | 7500
500106052 | CLB-MP-EXCV-EX108 -GRSYST-BOGRS | Boom Grease System | 79029 | 79029 | 7500
500106051 | CLB-MP-EXCV-EX108 -GRSYST-ALBSS | Grease system Super Structure | 79014 | 27163 | 7500
500105936 | CLB-MP-EXCV-EX108 -HYDSYS-PPDRR-PDOCR | PDrive Gbox Oil Cooler RH | 79029 | 176 | 7500
500105935 | CLB-MP-EXCV-EX108 -HYDSYS-PPDRL-PDOCL | PDrive Gbox Oil Cooler LH | 79029 | 176 | 7500
500105934 | CLB-MP-EXCV-EX108 -RHENGN-FUSYS-FUCRH | Fuel Cooler RH | 79029 | 79029 | 7500
500105933 | CLB-MP-EXCV-EX108 -LHENGN-FUSYS-FUCLH | Fuel Cooler LH | 79029 | 37387 | 7500
500104285 | CLB-MP-EXCV-EX108 -HYDSYS | Hydraulic System | 79029 | 7920 | 7500
500102362 | CLB-MP-EXCV-EX108 -ELCTLV-CHARG-BATTY | EX108 Batteries | 79029 | 6162 | 7500
500101493 | CLB-MP-EXCV-EX108 -HYDSYS | Hydraulic Oil | 79029 | 176 | 7500
500079333 | CLB-MP-EXCV-EX108 -STRUCT-HLINK | H Link Assembly | 79029 | 17314 | 7500
500063164 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-TCVVL | Travel Control Valve LH | 79029 | 17852 | 7500
500063163 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-TCVVR | Travel Control Valve RH | 79029 | 17852 | 7500
500060059 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-TRTN | Track Tensioning Hoses | 79029 | 18960 | 7500
500060058 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-TMCD | Travel Motor Case Drain Hoses | 79029 | 1129 | 7500
500060057 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 79029 | 2675 | 7500
500060056 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 79029 | 6162 | 7500
500060055 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SWBRK | Swing Brake Hoses | 79029 | 176 | 7500
500060054 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 79029 | 3475 | 7500
500060053 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 79029 | 2675 | 7500
500060052 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 79029 | 17852 | 7500
500060051 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-RCDM | Rotary Coupling to Drive Motor Hoses | 79029 | 1129 | 7500
500060050 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 79029 | 7027 | 7500
500060049 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 79029 | 17852 | 7500
500060048 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-MPRC | Main Pump to Rotary Coupling HP Hoses | 79029 | 4200 | 7500
500060047 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-MCVCR | MCV Cradle Hoses | 79029 | 6162 | 7500
500060046 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 79029 | 6162 | 7500
500060045 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HCFC | Hydraulic Cooling Fan Circulation Hoses | 79029 | 16617 | 7500
500060044 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-FDEC | Fan Drive Circut for Eng Cooling Hoses | 79029 | 15911 | 7500
500060043 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 79029 | 1900 | 7500
500060042 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-BMAR | Boom Arch Hoses | 79029 | 6162 | 7500
500060041 | CLB-MP-EXCV-EX108 -HYDSYS-HDHLF-2STBR | 2nd Speed Travel / Brake Release Hoses | 79029 | 1129 | 7500
500059812 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SRVRU | Secondary Relief Valves R/H Upper MCV | 78998 | 49101 | 7500
500059811 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SRVRL | Secondary Relief Valves R/H Lower MCV | 78998 | 49101 | 7500
500059810 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SRVLU | Secondary Relief Valves L/H Upper MCV | 78998 | 49101 | 7500
500059809 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-SRVLL | Secondary Relief Valves L/H Lower MCV | 78998 | 49101 | 7500
500059327 | CLB-MP-EXCV-EX108 -GRSYST-ALBPU | Auto Lube Pump Undercarriage | 79029 | 4200 | 7500
500042998 | CLB-MP-EXCV-EX108 -MANGMT-UMPMP | Pump Management System | 79029 | 79029 | 7500
500042997 | CLB-MP-EXCV-EX108 -MANGMT-UMBRD | Board Control System | 79029 | 79029 | 7500
500042996 | CLB-MP-EXCV-EX108 -MANGMT-UMMMC | Mine Monitoring and Control | 79029 | 12738 | 7500
500042995 | CLB-MP-EXCV-EX108 -MANGMT-UMENG | Engine Management System | 79029 | 79029 | 7500
500042994 | CLB-MP-EXCV-EX108 -FRSUPP-FSALM | Fire System Alarm | 79029 | 79029 | 7500
500042993 | CLB-MP-EXCV-EX108 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 79029 | 79029 | 7500
500042992 | CLB-MP-EXCV-EX108 -GRSYST-ALCON | Auto Lube Controller | 79029 | 79029 | 7500
500042991 | CLB-MP-EXCV-EX108 -GRSYST-ALBPP | Auto Lube Pump | 79029 | 1129 | 7500
500042990 | CLB-MP-EXCV-EX108 -GRSYST-GRINJ | Auto Lube Injectors | 79029 | 79029 | 7500
500042989 | CLB-MP-EXCV-EX108 -STRUCT-UNDER-SLEWB | Slew Bearing | 79029 | 24907 | 7500
500042988 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-CARRR | Roller Carrier RH Rear | 79029 | 79029 | 7500
500042987 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-CARRF | Roller Carrier RH Front | 79029 | 28997 | 7500
500042986 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH7 | Roller Load Pos 7 RH | 79029 | 79029 | 7500
500042985 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH6 | Roller Load Pos 6 RH | 79029 | 79029 | 7500
500042984 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH5 | Roller Load Pos 5 RH | 79029 | 19486 | 7500
500042983 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH4 | Roller Load Pos 4 RH | 79029 | 79029 | 7500
500042982 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH3 | Roller Load Pos 3 RH | 79029 | 79029 | 7500
500042981 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH2 | Roller Load Pos 2 RH | 79029 | 79029 | 7500
500042980 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-LORH1 | Roller Load Pos 1 RH | 79029 | 79029 | 7500
500042979 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-TENSR | Track Tensioner RH | 79029 | 7027 | 7500
500042978 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR-IDLRH | Idler Track RH | 79029 | 24317 | 7500
500042977 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-CARLR | Roller Carrier LH Rear | 79029 | 79029 | 7500
500042976 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-CARLF | Roller Carrier LH Front | 79029 | 34525 | 7500
500042975 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 LH | 79029 | 73280 | 7500
500042974 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 LH | 79029 | 79029 | 7500
500042973 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 LH | 79029 | 28997 | 7500
500042972 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 LH | 79029 | 58312 | 7500
500042971 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 LH | 79029 | 19486 | 7500
500042970 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 LH | 79029 | 79029 | 7500
500042969 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 LH | 79029 | 36700 | 7500
500042968 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-TENSR | Track Tensioner LH | 79029 | 7027 | 7500
500042967 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL-IDLLH | Idler Track LH | 79029 | 5200 | 7500
500042965 | CLB-MP-EXCV-EX108 -STRUCT-BUCKT | Bucket | 79029 | 2675 | 7500
500042964 | CLB-MP-EXCV-EX108 -STRUCT-STICK | Stick Assembly | 79029 | 1900 | 7500
500042963 | CLB-MP-EXCV-EX108 -STRUCT-BOOMS | Boom Assembly | 79029 | 52308 | 7500
500042962 | CLB-MP-EXCV-EX108 -STRUCT-STLAD-SLAUT | Automatic Access Systems | 79029 | 11173 | 7500
500042961 | CLB-MP-EXCV-EX108 -STRUCT-SUPER-ROLTK | Reserve Oil Tank | 79029 | 79029 | 7500
500042960 | CLB-MP-EXCV-EX108 -STRUCT-SUPER-CWEIG | Counterweight | 79029 | 79029 | 7500
500042959 | CLB-MP-EXCV-EX108 -STRUCT-CABIN-GLASS | Seat Belt | 79029 | 79029 | 7500
500042958 | CLB-MP-EXCV-EX108 -STRUCT-CABIN-SEATS | Operators Seat | 79029 | 1129 | 7500
500042957 | CLB-MP-EXCV-EX108 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 79029 | 79029 | 7500
500042956 | CLB-MP-EXCV-EX108 -STRUCT-CABIN-AIRCR | Air Conditioning System | 79029 | 33858 | 7500
500042955 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC-HACCR | Accumulator Hydraulic RH | 79029 | 14990 | 7500
500042954 | CLB-MP-EXCV-EX108 -HYDSYS-HDACC-HACCL | Accumulator Hydraulic LH | 79029 | 10271 | 7500
500042953 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-TRMRR | Motor Travel RH Rear | 79029 | 1129 | 7500
500042952 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-TRMRF | Motor Travel RH Front | 79029 | 1129 | 7500
500042951 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-TRMLR | Motor Travel LH Rear | 79029 | 2675 | 7500
500042950 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-TRMLF | Motor Travel LH Front | 79029 | 2675 | 7500
500042949 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FMECR | Motor Fan Engine Cooling RH | 79029 | 176 | 7500
500042948 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FMECL | Motor Fan Engine Cooling LH | 79029 | 6162 | 7500
500042947 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCTR | Motor Fan Hydraulic Cooling Top Rear | 79029 | 10271 | 7500
500042946 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCTF | Motor Fan Hydraulic Cooling Top Front | 79029 | 6162 | 7500
500042945 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCBR | Motor Fan Hydraulic Cooling Bottom Rear | 79029 | 9620 | 7500
500042944 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-FHCBF | Motor Fan Hydraulic Cooling Bottom Front | 79029 | 11955 | 7500
500042943 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-SWMRR | Motor Swing RH Rear | 79029 | 5200 | 7500
500042942 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-SWMRF | Motor Swing RH Front | 79029 | 5200 | 7500
500042941 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-SWMLR | Motor Swing LH Rear | 79029 | 5200 | 7500
500042940 | CLB-MP-EXCV-EX108 -HYDSYS-HDMOT-SWMLF | Motor Swing LH Front | 79029 | 6162 | 7500
500042939 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-MCVRU | Main Control Valve Block RH Upper | 79029 | 13550 | 7500
500042938 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-MCVRL | Main Control Valve Block RH Lower | 79029 | 24317 | 7500
500042937 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-MCVLU | Main Control Valve Block LH Upper | 79029 | 13550 | 7500
500042936 | CLB-MP-EXCV-EX108 -HYDSYS-HDVLV-MCVLL | Main Control Valve Block LH Lower | 79029 | 23724 | 7500
500042935 | CLB-MP-EXCV-EX108 -HYDSYS-ROTRY | Rotary Joint | 79029 | 9779 | 7500
500042934 | CLB-MP-EXCV-EX108 -HYDSYS-HDOCO-OCHRR | Oil Cooler Hydraulic Rear | 79029 | 9644 | 7500
500042933 | CLB-MP-EXCV-EX108 -HYDSYS-HDOCO-OCHFR | Oil Cooler Hydraulic Front | 79029 | 21895 | 7500
500042930 | CLB-MP-EXCV-EX108 -HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 79029 | 1900 | 7500
500042929 | CLB-MP-EXCV-EX108 -HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 79029 | 6162 | 7500
500042928 | CLB-MP-EXCV-EX108 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 79029 | 5200 | 7500
500042927 | CLB-MP-EXCV-EX108 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 79029 | 1900 | 7500
500042926 | CLB-MP-EXCV-EX108 -HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 79029 | 18960 | 7500
500042925 | CLB-MP-EXCV-EX108 -HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 79015 | 5200 | 7500
500042924 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing RH | 79029 | 7920 | 7500
500042923 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing LH | 79029 | 176 | 7500
500042922 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP4 | Pump Servo Position 4 | 79029 | 4200 | 7500
500042921 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP3 | Pump Servo Position 3 | 79029 | 4200 | 7500
500042920 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP2 | Pump Servo Position 2 | 79029 | 4200 | 7500
500042919 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SVPP1 | Pump Servo Position 1 | 79029 | 4200 | 7500
500042918 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-FPECR | Pump Fan Engine Cooling RH | 79029 | 1129 | 7500
500042917 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-FPECL | Pump Fan Engine Cooling LH | 79029 | 4200 | 7500
500042916 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-FPHC4 | Pump Fan Hydraulic Cooling Pos 4 | 79029 | 4200 | 7500
500042915 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-FPHC3 | Pump Fan Hydraulic Cooling Pos 3 | 79029 | 4200 | 7500
500042914 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-FPHC2 | Pump Fan Hydraulic Cooling Pos 2 | 79029 | 6558 | 7500
500042913 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-FPHC1 | Pump Fan Hydraulic Cooling Pos 1 | 79029 | 242 | 7500
500042912 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SWPP4 | Pump Swing Position 4 | 79029 | 1900 | 7500
500042911 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SWPP3 | Pump Swing Position 3 | 79029 | 1900 | 7500
500042910 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SWPP2 | Pump Swing Position 2 | 79029 | 5200 | 7500
500042909 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-SWPP1 | Pump Swing Position 1 | 79029 | 11173 | 7500
500042908 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP7P8 | Pump Main Position 4 | 79029 | 7027 | 7500
500042907 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP5P6 | Pump Main Position 3 | 79029 | 10473 | 7500
500042906 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP3P4 | Pump Main Position 2 | 79029 | 5200 | 7500
500042905 | CLB-MP-EXCV-EX108 -HYDSYS-HYDPP-MP1P2 | Pump Main Position 1 | 79029 | 14281 | 7500
500042904 | CLB-MP-EXCV-EX108 -HYDSYS-PPDRR | Pump Drive Gearbox RH | 79029 | 7027 | 7500
500042903 | CLB-MP-EXCV-EX108 -HYDSYS-PPDRL | Pump Drive Gearbox LH | 79029 | 7920 | 7500
500042902 | CLB-MP-EXCV-EX108 -SWGSYS-SWLUB | Swing System Lubrication | 79029 | 79029 | 7500
500042901 | CLB-MP-EXCV-EX108 -SWGSYS-SWBRK-SBKRR | Brake Swing RH Rear | 79029 | 39226 | 7500
500042900 | CLB-MP-EXCV-EX108 -SWGSYS-SWBRK-SBKRF | Brake Swing RH Front | 79029 | 39226 | 7500
500042899 | CLB-MP-EXCV-EX108 -SWGSYS-SWBRK-SBKLR | Brake Swing LH Front | 79029 | 39226 | 7500
500042898 | CLB-MP-EXCV-EX108 -SWGSYS-SWBRK-SBKLF | Brake Swing LH Rear | 79029 | 39226 | 7500
500042897 | CLB-MP-EXCV-EX108 -SWGSYS-SWBOX-SGBRR | Gearbox Swing RH Rear | 79029 | 16783 | 7500
500042896 | CLB-MP-EXCV-EX108 -SWGSYS-SWBOX-SGBRF | Gearbox Swing RH Front | 79029 | 14990 | 7500
500042895 | CLB-MP-EXCV-EX108 -SWGSYS-SWBOX-SGBLR | Gearbox Swing LH Rear | 79029 | 16617 | 7500
500042894 | CLB-MP-EXCV-EX108 -SWGSYS-SWBOX-SGBLF | Gearbox Swing LH Front | 79029 | 14990 | 7500
500042892 | CLB-MP-EXCV-EX108 -TRAVEL-TRBKR-TBKRR | Brake Travel RH Rear | 79029 | 79029 | 7500
500042891 | CLB-MP-EXCV-EX108 -TRAVEL-TRBKR-TBKRF | Brake Travel RH Front | 79029 | 79029 | 7500
500042890 | CLB-MP-EXCV-EX108 -TRAVEL-SPRKR | Sprocket RH | 79029 | 28997 | 7500
500042889 | CLB-MP-EXCV-EX108 -TRAVEL-FDRRH | Final Drive RH | 79029 | 18960 | 7500
500042888 | CLB-MP-EXCV-EX108 -TRAVEL-TRBKL-TBKLR | Brake Travel LH Rear | 79029 | 48894 | 7500
500042887 | CLB-MP-EXCV-EX108 -TRAVEL-TRBKL-TBKLF | Brake Travel LH Front | 79029 | 48894 | 7500
500042885 | CLB-MP-EXCV-EX108 -TRAVEL-SPRKL | Sprocket LH | 79029 | 28997 | 7500
500042884 | CLB-MP-EXCV-EX108 -TRAVEL-FDRLH | Final Drive LH | 79029 | 18960 | 7500
500042883 | CLB-MP-EXCV-EX108 -ELCTLV-START-STMRU | Starter Motor RH Engine Upper | 79029 | 138 | 7500
500042882 | CLB-MP-EXCV-EX108 -ELCTLV-START-STMRL | Starter Motor RH Engine Lower | 79029 | 138 | 7500
500042881 | CLB-MP-EXCV-EX108 -ELCTLV-START-STMLU | Starter Motor LH Engine Upper | 79029 | 7920 | 7500
500042880 | CLB-MP-EXCV-EX108 -ELCTLV-START-STMLL | Starter Motor LH Engine Lower | 79029 | 1129 | 7500
500042877 | CLB-MP-EXCV-EX108 -ELCTLV-CHARG-ALTRH | Alternator 24V RH Engine | 79029 | 138 | 7500
500042876 | CLB-MP-EXCV-EX108 -ELCTLV-CHARG-ALTLH | Alternator 24V LH Engine | 79029 | 1084 | 7500
500042875 | CLB-MP-EXCV-EX108 -RHENGN-COUPL | RH Engine Coupling | 79029 | 138 | 7500
500042874 | CLB-MP-EXCV-EX108 -RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 79029 | 138 | 7500
500042873 | CLB-MP-EXCV-EX108 -RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 79029 | 138 | 7500
500042872 | CLB-MP-EXCV-EX108 -RHENGN-INTEX-AFTER | RH Engine Aftercooler | 79029 | 79029 | 7500
500042871 | CLB-MP-EXCV-EX108 -RHENGN-INTEX-TBORH | RH EngineTurbocharger RH Side | 79029 | 138 | 7500
500042870 | CLB-MP-EXCV-EX108 -RHENGN-INTEX-TBOLH | RH EngineTurbocharger LH Side | 79029 | 138 | 7500
500042869 | CLB-MP-EXCV-EX108 -RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 79029 | 138 | 7500
500042868 | CLB-MP-EXCV-EX108 -RHENGN-COSYS-RADTR | RH Engine Radiator | 79029 | 3475 | 7500
500042867 | CLB-MP-EXCV-EX108 -RHENGN-COSYS-AWPRH | RH Engine Water Pump Aftercooler | 79029 | 138 | 7500
500042866 | CLB-MP-EXCV-EX108 -RHENGN-COSYS-WTRPP | RH Engine Water Pump | 79029 | 138 | 7500
500042865 | CLB-MP-EXCV-EX108 -RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 79029 | 40382 | 7500
500042864 | CLB-MP-EXCV-EX108 -RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 79029 | 138 | 7500
500042862 | CLB-MP-EXCV-EX108 -RHENGN | RH Engine Assembly Cummins QSK45 | 79029 | 138 | 7500
500042861 | CLB-MP-EXCV-EX108 -LHENGN-COUPL | LH Engine Coupling | 79029 | 7920 | 7500
500042860 | CLB-MP-EXCV-EX108 -LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 79029 | 7920 | 7500
500042859 | CLB-MP-EXCV-EX108 -LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 79029 | 7920 | 7500
500042858 | CLB-MP-EXCV-EX108 -LHENGN-INTEX-AFTER | LH Engine Aftercooler | 79029 | 43305 | 7500
500042857 | CLB-MP-EXCV-EX108 -LHENGN-INTEX-TBORH | LH Engine Turbocharger RH Side | 79029 | 7920 | 7500
500042856 | CLB-MP-EXCV-EX108 -LHENGN-INTEX-TBOLH | LH Engine Turbocharger LH Side | 79029 | 7920 | 7500
500042855 | CLB-MP-EXCV-EX108 -LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 79029 | 7920 | 7500
500042854 | CLB-MP-EXCV-EX108 -LHENGN-COSYS-RADTR | LH Engine Radiator | 79029 | 7920 | 7500
500042853 | CLB-MP-EXCV-EX108 -LHENGN-COSYS-AWPLH | LH Engine Water Pump Aftercooler | 79029 | 7920 | 7500
500042852 | CLB-MP-EXCV-EX108 -LHENGN-COSYS-WTRPP | LH Engine Water Pump | 79029 | 7920 | 7500
500042851 | CLB-MP-EXCV-EX108 -LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 79029 | 37387 | 7500
500042850 | CLB-MP-EXCV-EX108 -LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 79029 | 7920 | 7500
500042848 | CLB-MP-EXCV-EX108 -LHENGN | LH Engine Assembly Cummins QSK45 | 79029 | 7920 | 7500
500036291 | CLB-MP-EXCV-EX108 | EX108 Lubrication & Mechanical Services | 79029 | 79029 | 7500
500036290 | CLB-MP-EXCV-EX108 | Caterpillar 6060 Excavator, EX108 | 79029 | 79029 | 7500
500042742 | CLB-MP-EXCV-EX107 -TRAVEL-TRKRH | Track Assembly RH | 7249 | 1947 | 530
500042735 | CLB-MP-EXCV-EX107 -TRAVEL-TRKLH | Track Assembly LH | 7249 | 1947 | 530
500065148 | CLB-MP-EXCV-EX107 -TRAVEL | 6060 Excavator, EX107 TRAVEL HOURS | 7257 | 7257 | 530
500139318 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 19110 | 5213 | 7500
500106251 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-CBMNT | Cabin Mount | 86684 | 86684 | 7500
500106250 | CLB-MP-EXCV-EX107 -STRUCT-HLINK-LINKR | Banana Linkage R/H | 86684 | 86684 | 7500
500106249 | CLB-MP-EXCV-EX107 -STRUCT-HLINK-LINKL | Banana Linkage L/H | 86684 | 86684 | 7500
500106177 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-FLUVV | Flushing Valves | 86684 | 7767 | 7500
500106176 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SCBVV | Swing Counterbalance Valve | 86684 | 4212 | 7500
500106175 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SWBVV | Swing Blocking Valves | 86684 | 33656 | 7500
500106174 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-PROVV | PMS Proportional Valves | 86684 | 5213 | 7500
500106173 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SWSVV | Swing Safety Valves | 86684 | 7016 | 7500
500106172 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SSEVV | Seat/Servo Valve | 86684 | 33656 | 7500
500106171 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SSBVV | Second Speed and Swing Brake release Val | 86684 | 5213 | 7500
500106170 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SPRVV | Servo Proportional Valve | 86684 | 7767 | 7500
500106169 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-BFLVV | Boom Float Valve | 86684 | 13235 | 7500
500106168 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-MRVMC | Main Hydraulic Relief Valves | 86684 | 86684 | 7500
500106163 | CLB-MP-EXCV-EX107 -STRUCT-SRVCT | Service Centre | 86684 | 7767 | 7500
500105970 | CLB-MP-EXCV-EX107 -GRSYST-STGRS | Stick Grease System | 86684 | 86684 | 7500
500105969 | CLB-MP-EXCV-EX107 -GRSYST-HLGRS | H-Link Grease System | 86684 | 86684 | 7500
500105968 | CLB-MP-EXCV-EX107 -GRSYST-BOGRS | Boom Grease System | 86684 | 86684 | 7500
500105967 | CLB-MP-EXCV-EX107 -GRSYST-ALBSS | Grease system Super Structure | 86684 | 12488 | 7500
500105932 | CLB-MP-EXCV-EX107 -HYDSYS-PPDRR-PDOCR | PDrive Gbox Oil Cooler RH | 86684 | 33656 | 7500
500105931 | CLB-MP-EXCV-EX107 -HYDSYS-PPDRL-PDOCL | PDrive Gbox Oil Cooler LH | 86684 | 33656 | 7500
500105930 | CLB-MP-EXCV-EX107 -RHENGN-FUSYS-FUCRH | Fuel Cooler RH | 86684 | 31211 | 7500
500105929 | CLB-MP-EXCV-EX107 -LHENGN-FUSYS-FUCLH | Fuel Cooler LH | 86684 | 86684 | 7500
500104284 | CLB-MP-EXCV-EX107 -HYDSYS | Hydraulic System | 86684 | 4212 | 7500
500102361 | CLB-MP-EXCV-EX107 -ELCTLV-CHARG-BATTY | EX107 Batteries | 86684 | 6113 | 7500
500101492 | CLB-MP-EXCV-EX107 -HYDSYS | Hydraulic Oil | 86684 | 6180 | 7500
500079334 | CLB-MP-EXCV-EX107 -STRUCT-HLINK | H Link Assembly | 86684 | 14646 | 7500
500063162 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-TCVVR | Travel Control Valve RH | 86684 | 16363 | 7500
500063161 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-TCVVL | Travel Control Valve LH | 86684 | 16363 | 7500
500060032 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-TRTN | Track Tensioning Hoses | 86684 | 7036 | 7500
500060031 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-TMCD | Travel Motor Case Drain Hoses | 86684 | 10230 | 7500
500060030 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 86684 | 14005 | 7500
500060029 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 86684 | 6113 | 7500
500060028 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SWBRK | Swing Brake Hoses | 86684 | 5213 | 7500
500060027 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 86684 | 20445 | 7500
500060026 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 86684 | 6113 | 7500
500060025 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 86684 | 11756 | 7500
500060024 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-RCDM | Rotary Coupling to Drive Motor Hoses | 86684 | 9530 | 7500
500060023 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 86684 | 19124 | 7500
500060022 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 86684 | 13235 | 7500
500060021 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MPRC | Main Pump to Rotarty Coupling HP Hoses | 86684 | 6113 | 7500
500060020 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-MCVCR | MCV Cradle Hoses | 86684 | 6113 | 7500
500060019 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 86684 | 15138 | 7500
500060018 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-HCFC | Hydraulic Cooling Fan Circulation Hoses | 86684 | 5213 | 7500
500060017 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-FDEC | Fan Drive Circut for Eng Cooling Hoses | 86684 | 14652 | 7500
500060016 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 86684 | 4212 | 7500
500060015 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-BMAR | Boom Arch Hoses | 86684 | 6113 | 7500
500060014 | CLB-MP-EXCV-EX107 -HYDSYS-HDHLF-2STBR | 2nd Speed Travel / Brake Release Hoses | 86684 | 7767 | 7500
500059808 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SRVRU | Secondary Relief Valves R/H Upper MCV | 86662 | 49961 | 7500
500059807 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SRVRL | Secondary Relief Valves R/H Lower MCV | 86662 | 49961 | 7500
500059806 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SRVLU | Secondary Relief Valves L/H Upper MCV | 86662 | 49961 | 7500
500059805 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-SRVLL | Secondary Relief Valves L/H Lower MCV | 86662 | 49961 | 7500
500059326 | CLB-MP-EXCV-EX107 -GRSYST-ALBPU | Auto Lube Pump Undercarriage | 86684 | 7036 | 7500
500042847 | CLB-MP-EXCV-EX107 -MANGMT-UMPMP | Pump Management System | 86684 | 86684 | 7500
500042846 | CLB-MP-EXCV-EX107 -MANGMT-UMBRD | Board Control System | 86684 | 86684 | 7500
500042845 | CLB-MP-EXCV-EX107 -MANGMT-UMMMC | Mine Monitoring and Control | 86684 | 17400 | 7500
500042844 | CLB-MP-EXCV-EX107 -MANGMT-UMENG | Engine Management System | 86684 | 86684 | 7500
500042843 | CLB-MP-EXCV-EX107 -FRSUPP-FSALM | Fire System Alarm | 86684 | 86684 | 7500
500042842 | CLB-MP-EXCV-EX107 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 86684 | 86684 | 7500
500042841 | CLB-MP-EXCV-EX107 -GRSYST-ALCON | Auto Lube Controller | 86684 | 86684 | 7500
500042840 | CLB-MP-EXCV-EX107 -GRSYST-ALBPP | Auto Lube Pump | 86684 | 7036 | 7500
500042839 | CLB-MP-EXCV-EX107 -GRSYST-GRINJ | Auto Lube Injectors | 86684 | 86684 | 7500
500042838 | CLB-MP-EXCV-EX107 -STRUCT-UNDER-SLEWB | Slew Bearing | 86684 | 17889 | 7500
500042837 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-CARRR | Roller Carrier RH Rear | 86684 | 22303 | 7500
500042836 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-CARRF | Roller Carrier RH Front | 86684 | 44031 | 7500
500042835 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH7 | Roller Load Pos 7 RH | 86684 | 46623 | 7500
500042834 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH6 | Roller Load Pos 6 RH | 86684 | 86684 | 7500
500042833 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH5 | Roller Load Pos 5 RH | 86684 | 23802 | 7500
500042832 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH4 | Roller Load Pos 4 RH | 86684 | 13985 | 7500
500042831 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH3 | Roller Load Pos 3 RH | 86684 | 86684 | 7500
500042830 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH2 | Roller Load Pos 2 RH | 86684 | 26750 | 7500
500042829 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-LORH1 | Roller Load Pos 1 RH | 86684 | 48337 | 7500
500042828 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-TENSR | Track Tensioner RH | 86684 | 19877 | 7500
500042827 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR-IDLRH | Idler Track RH | 86684 | 46748 | 7500
500042826 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-CARLR | Roller Carrier LH Rear | 86684 | 20800 | 7500
500042825 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-CARLF | Roller Carrier LH Front | 86684 | 11337 | 7500
500042824 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 LH | 86684 | 13329 | 7500
500042823 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 LH | 86684 | 15929 | 7500
500042822 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 LH | 86684 | 40782 | 7500
500042821 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 LH | 86684 | 13329 | 7500
500042820 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 LH | 86684 | 86684 | 7500
500042819 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 LH | 86684 | 27427 | 7500
500042818 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 LH | 86684 | 13329 | 7500
500042817 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-TENSR | Track Tensioner LH | 86684 | 19877 | 7500
500042816 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL-IDLLH | Idler Track LH | 86684 | 20132 | 7500
500042814 | CLB-MP-EXCV-EX107 -STRUCT-BUCKT | Bucket | 86684 | 3300 | 7500
500042813 | CLB-MP-EXCV-EX107 -STRUCT-STICK | Stick Assembly | 86684 | 3300 | 7500
500042812 | CLB-MP-EXCV-EX107 -STRUCT-BOOMS | Boom Assembly | 86684 | 4212 | 7500
500042811 | CLB-MP-EXCV-EX107 -STRUCT-STLAD-SLAUT | Automatic Access Systems | 86684 | 33656 | 7500
500042810 | CLB-MP-EXCV-EX107 -STRUCT-SUPER-ROLTK | Reserve Oil Tank | 86684 | 86684 | 7500
500042809 | CLB-MP-EXCV-EX107 -STRUCT-SUPER-CWEIG | Counterweight | 86684 | 86684 | 7500
500042808 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-GLASS | Seat Belt | 86684 | 86684 | 7500
500042807 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-SEATS | Operators Seat | 86684 | 17032 | 7500
500042806 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 86684 | 86684 | 7500
500042805 | CLB-MP-EXCV-EX107 -STRUCT-CABIN-AIRCR | Air Conditioning System | 86684 | 5213 | 7500
500042804 | CLB-MP-EXCV-EX107 -HYDSYS-HDACC-HACCR | Accumulator Hydraulic RH | 86684 | 14652 | 7500
500042803 | CLB-MP-EXCV-EX107 -HYDSYS-HDACC-HACCL | Accumulator Hydraulic LH | 86684 | 14652 | 7500
500042802 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-TRMRR | Motor Travel RH Rear | 86684 | 7036 | 7500
500042801 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-TRMRF | Motor Travel RH Front | 86684 | 7036 | 7500
500042800 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-TRMLR | Motor Travel LH Rear | 86684 | 9530 | 7500
500042799 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-TRMLF | Motor Travel LH Front | 86684 | 9530 | 7500
500042798 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-FMECR | Motor Fan Engine Cooling RH | 86684 | 14005 | 7500
500042797 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-FMECL | Motor Fan Engine Cooling LH | 86684 | 5213 | 7500
500042796 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-FHCTR | Motor Fan Hydraulic Cooling Top Rear | 86684 | 3422 | 7500
500042795 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-FHCTF | Motor Fan Hydraulic Cooling Top Front | 86684 | 10617 | 7500
500042794 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-FHCBR | Motor Fan Hydraulic Cooling Bottom Rear | 86684 | 3422 | 7500
500042793 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-FHCBF | Motor Fan Hydraulic Cooling Bottom Front | 86684 | 9997 | 7500
500042792 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-SWMRR | Motor Swing RH Rear | 86684 | 10230 | 7500
500042791 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-SWMRF | Motor Swing RH Front | 86684 | 2331 | 7500
500042790 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-SWMLR | Motor Swing LH Rear | 86684 | 11756 | 7500
500042789 | CLB-MP-EXCV-EX107 -HYDSYS-HDMOT-SWMLF | Motor Swing LH Front | 86684 | 11756 | 7500
500042788 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-MCVRU | Main Control Valve Block RH Upper | 86684 | 25616 | 7500
500042787 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-MCVRL | Main Control Valve Block RH Lower | 86684 | 25616 | 7500
500042786 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-MCVLU | Main Control Valve Block LH Upper | 86684 | 25616 | 7500
500042785 | CLB-MP-EXCV-EX107 -HYDSYS-HDVLV-MCVLL | Main Control Valve Block LH Lower | 86684 | 25616 | 7500
500042784 | CLB-MP-EXCV-EX107 -HYDSYS-ROTRY | Rotary Joint | 86576 | 25616 | 7500
500042783 | CLB-MP-EXCV-EX107 -HYDSYS-HDOCO-OCHRR | Oil Cooler Hydraulic Rear | 86684 | 8701 | 7500
500042782 | CLB-MP-EXCV-EX107 -HYDSYS-HDOCO-OCHFR | Oil Cooler Hydraulic Front | 86684 | 11756 | 7500
500042779 | CLB-MP-EXCV-EX107 -HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 86684 | 14652 | 7500
500042778 | CLB-MP-EXCV-EX107 -HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 86684 | 1002 | 7500
500042777 | CLB-MP-EXCV-EX107 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 86684 | 62 | 7500
500042776 | CLB-MP-EXCV-EX107 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 86684 | 62 | 7500
500042775 | CLB-MP-EXCV-EX107 -HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 86684 | 4212 | 7500
500042774 | CLB-MP-EXCV-EX107 -HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 86684 | 11081 | 7500
500042773 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing RH | 86684 | 5213 | 7500
500042772 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing LH | 86684 | 5213 | 7500
500042771 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SVPP4 | Pump Servo Position 4 | 86684 | 7016 | 7500
500042770 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SVPP3 | Pump Servo Position 3 | 86684 | 7036 | 7500
500042769 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SVPP2 | Pump Servo Position 2 | 86684 | 7036 | 7500
500042768 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SVPP1 | Pump Servo Position 1 | 86684 | 7036 | 7500
500042767 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-FPECR | Pump Fan Engine Cooling RH | 86684 | 5213 | 7500
500042766 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-FPECL | Pump Fan Engine Cooling LH | 86684 | 11756 | 7500
500042765 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-FPHC4 | Pump Fan Hydraulic Cooling Pos 4 | 86684 | 15762 | 7500
500042764 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-FPHC3 | Pump Fan Hydraulic Cooling Pos 3 | 86684 | 15762 | 7500
500042763 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-FPHC2 | Pump Fan Hydraulic Cooling Pos 2 | 86684 | 15762 | 7500
500042762 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-FPHC1 | Pump Fan Hydraulic Cooling Pos 1 | 86684 | 5213 | 7500
500042761 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SWPP4 | Pump Swing Position 4 | 86684 | 3300 | 7500
500042760 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SWPP3 | Pump Swing Position 3 | 86684 | 3300 | 7500
500042759 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SWPP2 | Pump Swing Position 2 | 86684 | 5213 | 7500
500042758 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-SWPP1 | Pump Swing Position 1 | 86684 | 5213 | 7500
500042757 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-MP7P8 | Pump Main Position 4 | 86684 | 13235 | 7500
500042756 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-MP5P6 | Pump Main Position 3 | 86684 | 13235 | 7500
500042755 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-MP3P4 | Pump Main Position 2 | 86684 | 13235 | 7500
500042754 | CLB-MP-EXCV-EX107 -HYDSYS-HYDPP-MP1P2 | Pump Main Position 1 | 86684 | 11756 | 7500
500042753 | CLB-MP-EXCV-EX107 -HYDSYS-PPDRR | Pump Drive Gearbox RH | 86684 | 18565 | 7500
500042752 | CLB-MP-EXCV-EX107 -HYDSYS-PPDRL | Pump Drive Gearbox LH | 86684 | 17032 | 7500
500042751 | CLB-MP-EXCV-EX107 -SWGSYS-SWLUB | Swing System Lubrication | 86684 | 86684 | 7500
500042750 | CLB-MP-EXCV-EX107 -SWGSYS-SWBRK-SBKRR | Brake Swing RH Rear | 86684 | 56436 | 7500
500042749 | CLB-MP-EXCV-EX107 -SWGSYS-SWBRK-SBKRF | Brake Swing RH Front | 86684 | 2331 | 7500
500042748 | CLB-MP-EXCV-EX107 -SWGSYS-SWBRK-SBKLR | Brake Swing LH Front | 86684 | 33656 | 7500
500042747 | CLB-MP-EXCV-EX107 -SWGSYS-SWBRK-SBKLF | Brake Swing LH Rear | 86684 | 86684 | 7500
500042746 | CLB-MP-EXCV-EX107 -SWGSYS-SWBOX-SGBRR | Gearbox Swing RH Rear | 86684 | 13235 | 7500
500042745 | CLB-MP-EXCV-EX107 -SWGSYS-SWBOX-SGBRF | Gearbox Swing RH Front | 86684 | 2297 | 7500
500042744 | CLB-MP-EXCV-EX107 -SWGSYS-SWBOX-SGBLR | Gearbox Swing LH Rear | 86684 | 15762 | 7500
500042743 | CLB-MP-EXCV-EX107 -SWGSYS-SWBOX-SGBLF | Gearbox Swing LH Front | 86684 | 21198 | 7500
500042741 | CLB-MP-EXCV-EX107 -TRAVEL-TRBKR-TBKRR | Brake Travel RH Rear | 86684 | 86684 | 7500
500042740 | CLB-MP-EXCV-EX107 -TRAVEL-TRBKR-TBKRF | Brake Travel RH Front | 86684 | 86684 | 7500
500042739 | CLB-MP-EXCV-EX107 -TRAVEL-SPRKR | Sprocket RH | 86684 | 27427 | 7500
500042738 | CLB-MP-EXCV-EX107 -TRAVEL-FDRRH | Final Drive RH | 86684 | 27427 | 7500
500042737 | CLB-MP-EXCV-EX107 -TRAVEL-TRBKL-TBKLR | Brake Travel LH Rear | 86684 | 86684 | 7500
500042736 | CLB-MP-EXCV-EX107 -TRAVEL-TRBKL-TBKLF | Brake Travel LH Front | 86684 | 86684 | 7500
500042734 | CLB-MP-EXCV-EX107 -TRAVEL-SPRKL | Sprocket LH | 86684 | 18565 | 7500
500042733 | CLB-MP-EXCV-EX107 -TRAVEL-FDRLH | Final Drive LH | 86684 | 18565 | 7500
500042732 | CLB-MP-EXCV-EX107 -ELCTLV-START-STMRU | Starter Motor RH Engine Upper | 86684 | 12488 | 7500
500042731 | CLB-MP-EXCV-EX107 -ELCTLV-START-STMRL | Starter Motor RH Engine Lower | 86640 | 12488 | 7500
500042730 | CLB-MP-EXCV-EX107 -ELCTLV-START-STMLU | Starter Motor LH Engine Upper | 86684 | 62 | 7500
500042729 | CLB-MP-EXCV-EX107 -ELCTLV-START-STMLL | Starter Motor LH Engine Lower | 86684 | 62 | 7500
500042726 | CLB-MP-EXCV-EX107 -ELCTLV-CHARG-ALTRH | Alternator 24V RH Engine | 86684 | 9530 | 7500
500042725 | CLB-MP-EXCV-EX107 -ELCTLV-CHARG-ALTLH | Alternator 24V LH Engine | 86684 | 62 | 7500
500042724 | CLB-MP-EXCV-EX107 -RHENGN-COUPL | RH Engine Coupling | 86684 | 12488 | 7500
500042723 | CLB-MP-EXCV-EX107 -RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 86684 | 12488 | 7500
500042722 | CLB-MP-EXCV-EX107 -RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 86684 | 12488 | 7500
500042721 | CLB-MP-EXCV-EX107 -RHENGN-INTEX-AFTER | RH Engine Aftercooler | 86684 | 31211 | 7500
500042720 | CLB-MP-EXCV-EX107 -RHENGN-INTEX-TBORH | RH EngineTurbocharger RH Side | 86684 | 12488 | 7500
500042719 | CLB-MP-EXCV-EX107 -RHENGN-INTEX-TBOLH | RH EngineTurbocharger LH Side | 86684 | 12488 | 7500
500042718 | CLB-MP-EXCV-EX107 -RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 86684 | 12488 | 7500
500042717 | CLB-MP-EXCV-EX107 -RHENGN-COSYS-RADTR | RH Engine Radiator | 86684 | 11081 | 7500
500042716 | CLB-MP-EXCV-EX107 -RHENGN-COSYS-AWPRH | RH Engine Water Pump Aftercooler | 86684 | 12488 | 7500
500042715 | CLB-MP-EXCV-EX107 -RHENGN-COSYS-WTRPP | RH Engine Water Pump | 86684 | 12488 | 7500
500042714 | CLB-MP-EXCV-EX107 -RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 86684 | 31211 | 7500
500042713 | CLB-MP-EXCV-EX107 -RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 86684 | 12488 | 7500
500042711 | CLB-MP-EXCV-EX107 -RHENGN | RH Engine Assembly Cummins QSK45 | 86684 | 12488 | 7500
500042710 | CLB-MP-EXCV-EX107 -LHENGN-COUPL | LH Engine Coupling | 86684 | 17032 | 7500
500042709 | CLB-MP-EXCV-EX107 -LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 86684 | 62 | 7500
500042708 | CLB-MP-EXCV-EX107 -LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 86684 | 62 | 7500
500042707 | CLB-MP-EXCV-EX107 -LHENGN-INTEX-AFTER | LH Engine Aftercooler | 86684 | 35812 | 7500
500042706 | CLB-MP-EXCV-EX107 -LHENGN-INTEX-TBORH | LH Engine Turbocharger RH Side | 86684 | 62 | 7500
500042705 | CLB-MP-EXCV-EX107 -LHENGN-INTEX-TBOLH | LH Engine Turbocharger LH Side | 86684 | 62 | 7500
500042704 | CLB-MP-EXCV-EX107 -LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 86684 | 62 | 7500
500042703 | CLB-MP-EXCV-EX107 -LHENGN-COSYS-RADTR | LH Engine Radiator | 86684 | 19110 | 7500
500042702 | CLB-MP-EXCV-EX107 -LHENGN-COSYS-AWPLH | LH Engine Water Pump Aftercooler | 86684 | 7767 | 7500
500042701 | CLB-MP-EXCV-EX107 -LHENGN-COSYS-WTRPP | LH Engine Water Pump | 86684 | 62 | 7500
500042700 | CLB-MP-EXCV-EX107 -LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 86684 | 35812 | 7500
500042699 | CLB-MP-EXCV-EX107 -LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 86684 | 35812 | 7500
500042697 | CLB-MP-EXCV-EX107 -LHENGN | LH Engine Assembly Cummins QSK45 | 86684 | 62 | 7500
500036289 | CLB-MP-EXCV-EX107 | EX107 Lubrication & Mechanical Services | 86684 | 86684 | 7500
500036288 | CLB-MP-EXCV-EX107 | Caterpillar 6060 Excavator, EX107 | 86684 | 86684 | 7500
500159251 | CLB-MP-EXCV-EX7149 | R9400E Excavator, EX7149 Travel Hours | 273 | 273 | 325
500158233 | CLB-MP-EXCV-EX7149-STRUCT-AIRC2-ACONM | Motor Comp Drive Rear Aircon Unit | 5321 | 5321 | 6200
500158232 | CLB-MP-EXCV-EX7149-STRUCT-AIRC1-ACONM | Motor Comp Drive Side Aircon Unit | 5321 | 5321 | 6200
500158231 | CLB-MP-EXCV-EX7149-ELCTHV-HVC02-CABPR | S2 Cabinet Pressuriser Unit | 5321 | 5321 | 6200
500158230 | CLB-MP-EXCV-EX7149-ELCTHV-HVC01-CABPR | S1 Cabinet Pressuriser Unit | 5321 | 5321 | 6200
500158229 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCB | Accumulator Boarding Ladder Hyd | 5321 | 5321 | 6200
500158228 | CLB-MP-EXCV-EX7149-COMMUN-FLMGT | Fleet Management | 5321 | 5321 | 6200
500158227 | CLB-MP-EXCV-EX7149-MANGMT-UMMMC | Mine Monitoring & Control | 5321 | 5321 | 6200
500158226 | CLB-MP-EXCV-EX7149-FRSUPP | Fire Suppression System | 5321 | 5321 | 6200
500158225 | CLB-MP-EXCV-EX7149-PNEUMC-COMPR | Compressor Air System | 5321 | 5321 | 6200
500158224 | CLB-MP-EXCV-EX7149-PNEUMC-AIRDR | Drier Air System | 5321 | 5321 | 6200
500158223 | CLB-MP-EXCV-EX7149-PNEUMC-PNTNK | Tank Air System | 5321 | 5321 | 6200
500158222 | CLB-MP-EXCV-EX7149-GRSYST-GRINJ | Auto Lube Injectors | 5321 | 5321 | 6200
500158221 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 5321 | 5321 | 6200
500158220 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-ALBPP | Auto Lube Pump P1 Attachment Slew | 5321 | 5321 | 6200
500158219 | CLB-MP-EXCV-EX7149-GRSYST-AUTLU-GRTNK | Reservoir Grease Auto Lube | 5321 | 5321 | 6200
500158218 | CLB-MP-EXCV-EX7149-STRUCT-BUCKT | Bucket Assembly | 5321 | 5321 | 6200
500158217 | CLB-MP-EXCV-EX7149-STRUCT-SRVCT | Service Centre | 5321 | 5321 | 6200
500158216 | CLB-MP-EXCV-EX7149-STRUCT-STICK-SLVRR | Linkage Bucket Link- Shift Lever RH | 5321 | 5321 | 6200
500158215 | CLB-MP-EXCV-EX7149-STRUCT-STICK-SLVRL | Linkage Bucket Link- Shift Lever LH | 5321 | 5321 | 6200
500158214 | CLB-MP-EXCV-EX7149-STRUCT-STICK-LINKR | Linkage Stick To Bucket RH | 5321 | 5321 | 6200
500158213 | CLB-MP-EXCV-EX7149-STRUCT-STICK-LINKL | Linkage Stick To Bucket LH | 5321 | 5321 | 6200
500158212 | CLB-MP-EXCV-EX7149-STRUCT-STICK | Stick Assembly | 5321 | 5321 | 6200
500158211 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS-LKBST | Linkage Boom to Stick | 5321 | 5321 | 6200
500158210 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS-LKBSS | Linkage Boom to Superstructure | 5321 | 5321 | 6200
500158209 | CLB-MP-EXCV-EX7149-STRUCT-BOOMS | Boom Assembly | 5321 | 5321 | 6200
500158208 | CLB-MP-EXCV-EX7149-STRUCT-HDTNK | Tank Hydraulic | 5321 | 5321 | 6200
500158207 | CLB-MP-EXCV-EX7149-STRUCT-CABIN-SEATO | Operators Seat | 5321 | 5321 | 6200
500158206 | CLB-MP-EXCV-EX7149-STRUCT-AIRC2 | Cab Airconditioning System Rear Unit | 5321 | 5321 | 6200
500158205 | CLB-MP-EXCV-EX7149-STRUCT-AIRC1 | Cab Airconditioning System Side Unit | 5321 | 5321 | 6200
500158204 | CLB-MP-EXCV-EX7149-STRUCT-CABIN | Operators Cabin | 5321 | 5321 | 6200
500158203 | CLB-MP-EXCV-EX7149-STRUCT | Structure | 5321 | 5321 | 6200
500158202 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 5321 | 5321 | 6200
500158201 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 5321 | 5321 | 6200
500158200 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSPSM | Hose Hyd Swing Pump to Swing Motor | 5321 | 5321 | 6200
500158199 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps | 5321 | 5321 | 6200
500158198 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HMCVV | Hose Hyd Main Valve Bank | 5321 | 5321 | 6200
500158197 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBKCL | Hose Hyd Bucket Cylinder | 5321 | 5321 | 6200
500158196 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSTCL | Hose Hyd Stick Cylinder | 5321 | 5321 | 6200
500158194 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMCL | Hose Hyd Boom Cylinder | 5321 | 5321 | 6200
500158193 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HLFPH | Hose Hyd Pilot | 5321 | 5321 | 6200
500158192 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HLFCR | Hoses Hyd Cascade Room | 5321 | 5321 | 6200
500158191 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HLFCO | Hoses Hyd Cooler | 5321 | 5321 | 6200
500158189 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 5321 | 5321 | 6200
500158186 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMAR | Hoses Hyd Boom Arch | 5321 | 5321 | 6200
500158185 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCS | Accumulator Servo Hydraulic | 5321 | 5321 | 6200
500158184 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCR | Accumulator Track Hydraulic RH | 5321 | 5321 | 6200
500158183 | CLB-MP-EXCV-EX7149-HYDSYS-HDACC-HACCL | Accumulator Track Hydraulic LH | 5321 | 5321 | 6200
500158182 | CLB-MP-EXCV-EX7149-HYDSYS-HDCFM-CFHP2 | Fan Hyd Cooling System Pos 2 | 5321 | 5321 | 6200
500158181 | CLB-MP-EXCV-EX7149-HYDSYS-HDCFM-CFHP1 | Fan Hyd Cooling System Pos 1 | 5321 | 5321 | 6200
500158180 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMRR | Hyd Motor Travel RH Rear | 5321 | 5321 | 6200
500158179 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMRF | Hyd Motor Travel RH Front | 5321 | 5321 | 6200
500158178 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMLR | Hyd Motor Travel LH Rear | 5321 | 5321 | 6200
500158177 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-TRMLF | Hyd Motor Travel LH Front | 5321 | 5321 | 6200
500158176 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-FMCH2 | Hyd Motor Fan Hyd Cooling Rear | 5321 | 5321 | 6200
500158175 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-FMCH1 | Hyd Motor Fan Hyd Cooling Front | 5321 | 5321 | 6200
500158174 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 5321 | 5321 | 6200
500158173 | CLB-MP-EXCV-EX7149-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 5321 | 5321 | 6200
500158172 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 5321 | 5321 | 6200
500158171 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 5321 | 5321 | 6200
500158170 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVRU | Valve Main Control RH Upper | 5321 | 5321 | 6200
500158169 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVRL | Valve Main Control RH Lower | 5321 | 5321 | 6200
500158168 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVLU | Valve Main Control LH Upper | 5321 | 5321 | 6200
500158167 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MCVLL | Valve Main Control LH Lower | 5321 | 5321 | 6200
500158166 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VLVSR | Valve Hyd Secondary Relief | 5321 | 5321 | 6200
500158165 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VLVPR | Valve Primary Hyd Relief | 5321 | 5321 | 6200
500158164 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-VLVAU | Valve Hyd Auxiliary Control | 5321 | 5321 | 6200
500158163 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MONO2 | Valve Monoblock Boom RH | 5321 | 5321 | 6200
500158162 | CLB-MP-EXCV-EX7149-HYDSYS-HDVLV-MONO1 | Valve Monoblock Boom LH | 5321 | 5321 | 6200
500158161 | CLB-MP-EXCV-EX7149-HYDSYS-ROTRY | Rotary Connection | 5321 | 5321 | 6200
500158160 | CLB-MP-EXCV-EX7149-HYDSYS-HDOCO-OCHYR | Hyd Oil Cooler LH Rear | 5321 | 5321 | 6200
500158159 | CLB-MP-EXCV-EX7149-HYDSYS-HDOCO-OCHYF | Hyd Oil Cooler Hyd Front | 5321 | 5321 | 6200
500158158 | CLB-MP-EXCV-EX7149-HYDSYS-HDOCO-OCPTO | Hyd Oil Cooler Pump Drive | 5321 | 5321 | 6200
500158157 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH Lift | 5321 | 5321 | 6200
500158156 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH Lift | 5321 | 5321 | 6200
500158155 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 5321 | 5321 | 6200
500158154 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 5321 | 5321 | 6200
500158153 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 5321 | 5321 | 6200
500158152 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 5321 | 5321 | 6200
500158151 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 5321 | 5321 | 6200
500158150 | CLB-MP-EXCV-EX7149-HYDSYS-HDCYL-SHCYL | Cylinder Hatch Lock | 5321 | 5321 | 6200
500158149 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-RPPP1 | Hyd Pump Oil Replenishing | 5321 | 5321 | 6200
500158148 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-PTOLU | Lube Pump Splitter Gear Box | 5321 | 5321 | 6200
500158147 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SVPP1 | Pump Servo Bearing Lube | 5321 | 5321 | 6200
500158146 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-HECP1 | Hyd Pump Fan Hyd Oil Cooler | 5321 | 5321 | 6200
500158145 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-SWPP1 | Hyd Pump Swing Pos1 & Pos2 | 5321 | 5321 | 6200
500158144 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-WPPP2 | Pump Hyd Work Pos3 & Pos4 | 5321 | 5321 | 6200
500158143 | CLB-MP-EXCV-EX7149-HYDSYS-HYDPP-WPPP1 | Pump Hyd Work Pos1 & Pos2 | 5321 | 5321 | 6200
500158142 | CLB-MP-EXCV-EX7149-HYDSYS-PMPDR-PDBRE | Breather Pump Drive | 5321 | 5321 | 6200
500158141 | CLB-MP-EXCV-EX7149-HYDSYS-PMPDR | Splitter Gearbox | 5321 | 5321 | 6200
500158140 | CLB-MP-EXCV-EX7149-HYDSYS-TBKLH-TBKLR | Brake Travel LH Rear | 5321 | 5321 | 6200
500158139 | CLB-MP-EXCV-EX7149-HYDSYS-TBKLH-TBKLF | Brake Travel LH Front | 5321 | 5321 | 6200
500158138 | CLB-MP-EXCV-EX7149-HYDSYS-TBKRH-TBKRR | Brake Travel RH Rear | 5321 | 5321 | 6200
500158137 | CLB-MP-EXCV-EX7149-HYDSYS-TBKRH-TBKRF | Brake Travel RH Front | 5321 | 5321 | 6200
500158136 | CLB-MP-EXCV-EX7149-SWGSYS-SWBRK-SBKPR | Brake Swing P2 | 5321 | 5321 | 6200
500158135 | CLB-MP-EXCV-EX7149-SWGSYS-SWBRK-SBKPF | Brake Swing P1 | 5321 | 5321 | 6200
500158134 | CLB-MP-EXCV-EX7149-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 5321 | 5321 | 6200
500158133 | CLB-MP-EXCV-EX7149-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 5321 | 5321 | 6200
500158132 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-CARRR | Roller Carrier RH Pos2 | 5321 | 5321 | 6200
500158131 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-CARRF | Roller Carrier RH Pos1 | 5321 | 5321 | 6200
500158130 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH9 | Roller Load RH Pos9 | 5321 | 5321 | 6200
500158129 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH8 | Roller Load RH Pos8 | 5321 | 5321 | 6200
500158128 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH7 | Roller Load RH Pos7 | 5321 | 5321 | 6200
500158127 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH6 | Roller Load RH Pos6 | 5321 | 5321 | 6200
500158126 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH5 | Roller Load RH Pos5 | 5321 | 5321 | 6200
500158125 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH4 | Roller Load RH Pos4 | 5321 | 5321 | 6200
500158124 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH3 | Roller Load RH Pos3 | 5321 | 5321 | 6200
500158123 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH2 | Roller Load RH Pos2 | 5321 | 5321 | 6200
500158122 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-LORH1 | Roller Load RH Pos1 | 5321 | 5321 | 6200
500158121 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-TENSR | Track Hyd Tensioner RH | 5321 | 5321 | 6200
500158120 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-IDLRH | Track Idler RH | 5321 | 5321 | 6200
500158119 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-SPRKR | Sprocket RH | 5321 | 5321 | 6200
500158118 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-FDRRH | Final Drive RH Side | 5321 | 5321 | 6200
500158117 | CLB-MP-EXCV-EX7149-UNDERC-TKFRR-TRKRH | Track Assembly RH | 5321 | 5321 | 6200
500158116 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-CARLR | Roller Carrier LH Pos2 | 5321 | 5321 | 6200
500158115 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-CARLF | Roller Carrier LH Pos1 | 5321 | 5321 | 6200
500158114 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH9 | Roller Load LH Pos9 | 5321 | 5321 | 6200
500158113 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH8 | Roller Load LH Pos8 | 5321 | 5321 | 6200
500158112 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH7 | Roller Load LH Pos7 | 5321 | 5321 | 6200
500158111 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH6 | Roller Load LH Pos6 | 5321 | 5321 | 6200
500158110 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH5 | Roller Load LH Pos5 | 5321 | 5321 | 6200
500158109 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH4 | Roller Load LH Pos4 | 5321 | 5321 | 6200
500158108 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH3 | Roller Load LH Pos3 | 5321 | 5321 | 6200
500158107 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH2 | Roller Load LH Pos2 | 5321 | 5321 | 6200
500158106 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-LOLH1 | Roller Load LH Pos1 | 5321 | 5321 | 6200
500158105 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-TENSL | Track Hyd Tensioner LH | 5321 | 5321 | 6200
500158104 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-IDLLH | Track Idler LH | 5321 | 5321 | 6200
500158103 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-SPRKL | Sprocket LH | 5321 | 5321 | 6200
500158102 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-FDRLH | Final Drive LH Side | 5321 | 5321 | 6200
500158101 | CLB-MP-EXCV-EX7149-UNDERC-TKFRL-TRKLH | Track Assembly LH | 5321 | 5321 | 6200
500158100 | CLB-MP-EXCV-EX7149-UNDERC-SLEWB | Bearing Slew | 5321 | 5321 | 6200
500158099 | CLB-MP-EXCV-EX7149-UNDERC | Undercarriage | 5321 | 5321 | 6200
500158098 | CLB-MP-EXCV-EX7149-ELCTHV-HVMOT-COUPL | HV Motor Coupling | 5321 | 5321 | 6200
500158097 | CLB-MP-EXCV-EX7149-ELCTHV-HVMOT | Electrical HV Motor | 5321 | 5321 | 6200
500158096 | CLB-MP-EXCV-EX7149-ELCTHV-HVRJO | Electrical HV Rotary Joint | 5321 | 5321 | 6200
500158095 | CLB-MP-EXCV-EX7149-ELCTHV-HVCRL | Cable Reeler | 5321 | 5321 | 6200
500158094 | CLB-MP-EXCV-EX7149-ELCTHV-HVCBL | High Voltage Cables | 5321 | 5321 | 6200
500158093 | CLB-MP-EXCV-EX7149-ELCTHV-HVC02 | S2 Electrical Cabinet | 5321 | 5321 | 6200
500158092 | CLB-MP-EXCV-EX7149-ELCTHV-HVC01 | S1 Electrical Cabinet | 5321 | 5321 | 6200
500158091 | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-BATST | Batteries | 5321 | 5321 | 6200
500158090 | CLB-MP-EXCV-EX7149-ELCTLV-CHARG-CACDC | Battery Charger ACDC | 5321 | 5321 | 6200
500158089 | CLB-MP-EXCV-EX7149 | EX7149 Liebherr R9400E Excavator | 5321 | 5321 | 6200
500159250 | CLB-MP-EXCV-EX7148 | R9400E Excavator, EX7148 Travel Hours | 349 | 349 | 325
500157535 | CLB-MP-EXCV-EX7148-STRUCT-AIRC2-ACONM | Motor Comp Drive Rear Aircon Unit | 6057 | 6057 | 6200
500157534 | CLB-MP-EXCV-EX7148-STRUCT-AIRC1-ACONM | Motor Comp Drive Side Aircon Unit | 6057 | 6057 | 6200
500157533 | CLB-MP-EXCV-EX7148-ELCTHV-HVC02-CABPR | S2 Cabinet Pressuriser Unit | 6057 | 6057 | 6200
500157532 | CLB-MP-EXCV-EX7148-ELCTHV-HVC01-CABPR | S1 Cabinet Pressuriser Unit | 6057 | 6057 | 6200
500157531 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCB | Accumulator Boarding Ladder Hyd | 6057 | 6057 | 6200
500157530 | CLB-MP-EXCV-EX7148-COMMUN-FLMGT | Fleet Management | 6057 | 6057 | 6200
500157529 | CLB-MP-EXCV-EX7148-MANGMT-UMMMC | Mine Monitoring & Control | 6057 | 6057 | 6200
500157528 | CLB-MP-EXCV-EX7148-FRSUPP | Fire Suppression System | 6057 | 6057 | 6200
500157527 | CLB-MP-EXCV-EX7148-PNEUMC-COMPR | Compressor Air System | 6057 | 6057 | 6200
500157526 | CLB-MP-EXCV-EX7148-PNEUMC-AIRDR | Drier Air System | 6057 | 6057 | 6200
500157525 | CLB-MP-EXCV-EX7148-PNEUMC-PNTNK | Tank Air System | 6057 | 6057 | 6200
500157524 | CLB-MP-EXCV-EX7148-GRSYST-GRINJ | Auto Lube Injectors | 6057 | 6057 | 6200
500157523 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 6057 | 6057 | 6200
500157522 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-ALBPP | Auto Lube Pump P1 Attachment Slew | 6057 | 6057 | 6200
500157521 | CLB-MP-EXCV-EX7148-GRSYST-AUTLU-GRTNK | Reservoir Grease Auto Lube | 6057 | 6057 | 6200
500157520 | CLB-MP-EXCV-EX7148-STRUCT-BUCKT | Bucket Assembly | 6057 | 6057 | 6200
500157519 | CLB-MP-EXCV-EX7148-STRUCT-SRVCT | Service Centre | 6057 | 6057 | 6200
500157518 | CLB-MP-EXCV-EX7148-STRUCT-STICK-SLVRR | Linkage Bucket Link- Shift Lever RH | 6057 | 6057 | 6200
500157517 | CLB-MP-EXCV-EX7148-STRUCT-STICK-SLVRL | Linkage Bucket Link- Shift Lever LH | 6057 | 6057 | 6200
500157516 | CLB-MP-EXCV-EX7148-STRUCT-STICK-LINKR | Linkage Stick To Bucket RH | 6057 | 6057 | 6200
500157515 | CLB-MP-EXCV-EX7148-STRUCT-STICK-LINKL | Linkage Stick To Bucket LH | 6057 | 6057 | 6200
500157514 | CLB-MP-EXCV-EX7148-STRUCT-STICK | Stick Assembly | 6057 | 6057 | 6200
500157513 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS-LKBST | Linkage Boom to Stick | 6057 | 6057 | 6200
500157512 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS-LKBSS | Linkage Boom to Superstructure | 6057 | 6057 | 6200
500157511 | CLB-MP-EXCV-EX7148-STRUCT-BOOMS | Boom Assembly | 6057 | 6057 | 6200
500157510 | CLB-MP-EXCV-EX7148-STRUCT-HDTNK | Tank Hydraulic | 6057 | 6057 | 6200
500157509 | CLB-MP-EXCV-EX7148-STRUCT-CABIN-SEATO | Operators Seat | 6057 | 6057 | 6200
500157508 | CLB-MP-EXCV-EX7148-STRUCT-AIRC2 | Cab Airconditioning System Rear Unit | 6057 | 6057 | 6200
500157507 | CLB-MP-EXCV-EX7148-STRUCT-AIRC1 | Cab Airconditioning System Side Unit | 6057 | 6057 | 6200
500157506 | CLB-MP-EXCV-EX7148-STRUCT-CABIN | Operators Cabin | 6057 | 6057 | 6200
500157505 | CLB-MP-EXCV-EX7148-STRUCT | Structure | 6057 | 6057 | 6200
500157504 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 6057 | 6057 | 6200
500157503 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 6057 | 6057 | 6200
500157502 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSPSM | Hose Hyd Swing Pump to Swing Motor | 6057 | 6057 | 6200
500157501 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps | 6057 | 6057 | 6200
500157500 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HMCVV | Hose Hyd Main Valve Bank | 6057 | 6057 | 6200
500157499 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCL | Hose Hyd Bucket Cylinder | 6057 | 6057 | 6200
500157498 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCL | Hose Hyd Stick Cylinder | 6057 | 6057 | 6200
500157496 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCL | Hose Hyd Boom Cylinder | 6057 | 6057 | 6200
500157495 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HLFPH | Hose Hyd Pilot | 6057 | 6057 | 6200
500157494 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HLFCR | Hoses Hyd Cascade Room | 6057 | 6057 | 6200
500157493 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HLFCO | Hoses Hyd Cooler | 6057 | 6057 | 6200
500157491 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 6057 | 6057 | 6200
500157488 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMAR | Hoses Hyd Boom Arch | 6057 | 6057 | 6200
500157487 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCS | Accumulator Servo Hydraulic | 6057 | 6057 | 6200
500157486 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCR | Accumulator Track Hydraulic R/H | 6057 | 6057 | 6200
500157485 | CLB-MP-EXCV-EX7148-HYDSYS-HDACC-HACCL | Accumulator Track Hydraulic L/H | 6057 | 6057 | 6200
500157484 | CLB-MP-EXCV-EX7148-HYDSYS-HDCFM-CFHP2 | Fan Hyd Cooling System Pos 2 | 6057 | 6057 | 6200
500157483 | CLB-MP-EXCV-EX7148-HYDSYS-HDCFM-CFHP1 | Fan Hyd Cooling System Pos 1 | 6057 | 6057 | 6200
500157482 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMRR | Hyd Motor Travel RH Rear | 6057 | 6057 | 6200
500157481 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMRF | Hyd Motor Travel RH Front | 6057 | 6057 | 6200
500157480 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMLR | Hyd Motor Travel LH Rear | 6057 | 6057 | 6200
500157479 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-TRMLF | Hyd Motor Travel LH Front | 6057 | 6057 | 6200
500157478 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-FMCH2 | Hyd Motor Fan Hyd Cooling Rear | 6057 | 6057 | 6200
500157477 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-FMCH1 | Hyd Motor Fan Hyd Cooling Front | 6057 | 6057 | 6200
500157476 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 6057 | 6057 | 6200
500157475 | CLB-MP-EXCV-EX7148-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 6057 | 6057 | 6200
500157474 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 6057 | 6057 | 6200
500157473 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 6057 | 6057 | 6200
500157472 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVRU | Valve Main Control RH Upper | 6057 | 6057 | 6200
500157471 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVRL | Valve Main Control RH Lower | 6057 | 6057 | 6200
500157470 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVLU | Valve Main Control LH Upper | 6057 | 6057 | 6200
500157469 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MCVLL | Valve Main Control LH Lower | 6057 | 6057 | 6200
500157468 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VLVSR | Valve Hyd Secondary Relief | 6057 | 6057 | 6200
500157467 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VLVPR | Valve Primary Hyd Relief | 6057 | 6057 | 6200
500157466 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-VLVAU | Valve Hyd Auxiliary Control | 6057 | 6057 | 6200
500157465 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MONO2 | Valve Monoblock Boom RH | 6057 | 6057 | 6200
500157464 | CLB-MP-EXCV-EX7148-HYDSYS-HDVLV-MONO1 | Valve Monoblock Boom LH | 6057 | 6057 | 6200
500157463 | CLB-MP-EXCV-EX7148-HYDSYS-ROTRY | Rotary Connection | 6057 | 6057 | 6200
500157462 | CLB-MP-EXCV-EX7148-HYDSYS-HDOCO-OCHYR | Hyd Oil Cooler LH Rear | 6057 | 6057 | 6200
500157461 | CLB-MP-EXCV-EX7148-HYDSYS-HDOCO-OCHYF | Hyd Oil Cooler Hyd Front | 6057 | 6057 | 6200
500157460 | CLB-MP-EXCV-EX7148-HYDSYS-HDOCO-OCPTO | Hyd Oil Cooler Pump Drive | 6057 | 6057 | 6200
500157459 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH Lift | 6057 | 6057 | 6200
500157458 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH Lift | 6057 | 6057 | 6200
500157457 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 6057 | 6057 | 6200
500157456 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 6057 | 6057 | 6200
500157455 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 6057 | 6057 | 6200
500157454 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 6057 | 6057 | 6200
500157453 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 6057 | 6057 | 6200
500157452 | CLB-MP-EXCV-EX7148-HYDSYS-HDCYL-SHCYL | Cylinder Hatch Lock | 6057 | 6057 | 6200
500157451 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-RPPP1 | Hyd Pump Oil Replenishing | 6057 | 6057 | 6200
500157450 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-PTOLU | Lube Pump Splitter Gear Box | 6057 | 6057 | 6200
500157449 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SVPP1 | Pump Servo Bearing Lube | 6057 | 6057 | 6200
500157448 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-HECP1 | Hyd Pump Fan Hyd Oil Cooler | 6057 | 6057 | 6200
500157447 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-SWPP1 | Hyd Pump Swing Pos1 & Pos2 | 6057 | 6057 | 6200
500157446 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-WPPP2 | Pump Hyd Work Pos3 & Pos4 | 6057 | 6057 | 6200
500157445 | CLB-MP-EXCV-EX7148-HYDSYS-HYDPP-WPPP1 | Pump Hyd Work Pos1 & Pos2 | 6057 | 6057 | 6200
500157444 | CLB-MP-EXCV-EX7148-HYDSYS-PMPDR-PDBRE | Breather Pump Drive | 6057 | 6057 | 6200
500157443 | CLB-MP-EXCV-EX7148-HYDSYS-PMPDR | Pump Drive/Splitter Gearbox | 6057 | 6057 | 6200
500157442 | CLB-MP-EXCV-EX7148-HYDSYS-TBKLH-TBKLR | Brake Travel LH Rear | 6057 | 6057 | 6200
500157441 | CLB-MP-EXCV-EX7148-HYDSYS-TBKLH-TBKLF | Brake Travel LH Front | 6057 | 6057 | 6200
500157440 | CLB-MP-EXCV-EX7148-HYDSYS-TBKRH-TBKRR | Brake Travel RH Rear | 6057 | 6057 | 6200
500157439 | CLB-MP-EXCV-EX7148-HYDSYS-TBKRH-TBKRF | Brake Travel RH Front | 6057 | 6057 | 6200
500157438 | CLB-MP-EXCV-EX7148-SWGSYS-SWBRK-SBKPR | Brake Swing P2 | 6057 | 6057 | 6200
500157437 | CLB-MP-EXCV-EX7148-SWGSYS-SWBRK-SBKPF | Brake Swing P1 | 6057 | 6057 | 6200
500157436 | CLB-MP-EXCV-EX7148-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 6057 | 6057 | 6200
500157435 | CLB-MP-EXCV-EX7148-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 6057 | 6057 | 6200
500157434 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-CARRR | Roller Carrier RH Pos2 | 6057 | 6057 | 6200
500157433 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-CARRF | Roller Carrier RH Pos1 | 6057 | 6057 | 6200
500157432 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH9 | Roller Load RH Pos9 | 6057 | 6057 | 6200
500157431 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH8 | Roller Load RH Pos8 | 6057 | 6057 | 6200
500157430 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH7 | Roller Load RH Pos7 | 6057 | 6057 | 6200
500157429 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH6 | Roller Load RH Pos6 | 6057 | 6057 | 6200
500157428 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH5 | Roller Load RH Pos5 | 6057 | 6057 | 6200
500157427 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH4 | Roller Load RH Pos4 | 6057 | 6057 | 6200
500157426 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH3 | Roller Load RH Pos3 | 6057 | 6057 | 6200
500157425 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH2 | Roller Load RH Pos2 | 6057 | 6057 | 6200
500157424 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-LORH1 | Roller Load RH Pos1 | 6057 | 6057 | 6200
500157423 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-TENSR | Track Hyd Tensioner RH | 6057 | 6057 | 6200
500157422 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-IDLRH | Track Idler RH | 6057 | 6057 | 6200
500157421 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-SPRKR | Sprocket RH | 6057 | 6057 | 6200
500157420 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-FDRRH | Final Drive RH Side | 6057 | 6057 | 6200
500157419 | CLB-MP-EXCV-EX7148-UNDERC-TKFRR-TRKRH | Track Assembly RH | 6057 | 6057 | 6200
500157418 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-CARLR | Roller Carrier LH Pos2 | 6057 | 6057 | 6200
500157417 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-CARLF | Roller Carrier LH Pos1 | 6057 | 6057 | 6200
500157416 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH9 | Roller Load LH Pos9 | 6057 | 6057 | 6200
500157415 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH8 | Roller Load LH Pos8 | 6057 | 6057 | 6200
500157414 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH7 | Roller Load LH Pos7 | 6057 | 6057 | 6200
500157413 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH6 | Roller Load LH Pos6 | 6057 | 6057 | 6200
500157412 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH5 | Roller Load LH Pos5 | 6057 | 6057 | 6200
500157411 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH4 | Roller Load LH Pos4 | 6057 | 6057 | 6200
500157410 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH3 | Roller Load LH Pos3 | 6057 | 6057 | 6200
500157409 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH2 | Roller Load LH Pos2 | 6057 | 6057 | 6200
500157408 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-LOLH1 | Roller Load LH Pos1 | 6057 | 6057 | 6200
500157407 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-TENSL | Track Hyd Tensioner LH | 6057 | 6057 | 6200
500157406 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-IDLLH | Track Idler LH | 6057 | 6057 | 6200
500157405 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-SPRKL | Sprocket LH | 6057 | 6057 | 6200
500157404 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-FDRLH | Final Drive LH Side | 6057 | 6057 | 6200
500157403 | CLB-MP-EXCV-EX7148-UNDERC-TKFRL-TRKLH | Track Assembly LH | 6057 | 6057 | 6200
500157402 | CLB-MP-EXCV-EX7148-UNDERC-SLEWB | Bearing Slew | 6057 | 6057 | 6200
500157401 | CLB-MP-EXCV-EX7148-UNDERC | Undercarriage | 6057 | 6057 | 6200
500157400 | CLB-MP-EXCV-EX7148-ELCTHV-HVMOT-COUPL | HV Motor Coupling | 6057 | 6057 | 6200
500157399 | CLB-MP-EXCV-EX7148-ELCTHV-HVMOT | Electrical HV Motor | 6057 | 6057 | 6200
500157398 | CLB-MP-EXCV-EX7148-ELCTHV-HVRJO | Electrical HV Rotary Joint | 6057 | 6057 | 6200
500157397 | CLB-MP-EXCV-EX7148-ELCTHV-HVCRL | Cable Reeler | 6057 | 6057 | 6200
500157396 | CLB-MP-EXCV-EX7148-ELCTHV-HVCBL | High Voltage Cables | 6057 | 6057 | 6200
500157395 | CLB-MP-EXCV-EX7148-ELCTHV-HVC02 | S2 Electrical Cabinet | 6057 | 6057 | 6200
500157394 | CLB-MP-EXCV-EX7148-ELCTHV-HVC01 | S1 Electrical Cabinet | 6057 | 6057 | 6200
500157393 | CLB-MP-EXCV-EX7148-ELCTLV-CHARG-BATST | Batteries | 6057 | 6057 | 6200
500157392 | CLB-MP-EXCV-EX7148-ELCTLV-CHARG-CACDC | Battery Charger ACDC | 6057 | 6057 | 6200
500157391 | CLB-MP-EXCV-EX7148 | EX7148 Liebherr R9400E Excavator | 6057 | 6057 | 6200
500157608 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 8353 | 498 | 6200
500154934 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-TRKRH | Assembly Track Right Hand | 8353 | 8353 | 6200
500154933 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-TENSL | Tensioner Track Hydraulic Right Hand | 8353 | 8353 | 6200
500154932 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-SPRKR | Sprocket Right Hand | 8353 | 8353 | 6200
500154931 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH9 | Roller Load Right Hand P9 | 8353 | 8353 | 6200
500154930 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH8 | Roller Load Right Hand P8 | 8353 | 8353 | 6200
500154929 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH7 | Roller Load Right Hand P7 | 8353 | 8353 | 6200
500154928 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH6 | Roller Load Right Hand P6 | 8353 | 8353 | 6200
500154927 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH5 | Roller Load Right Hand P5 | 8353 | 8353 | 6200
500154926 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH4 | Roller Load Right Hand P4 | 8353 | 8353 | 6200
500154925 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH3 | Roller Load Right Hand P3 | 8353 | 8353 | 6200
500154924 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH2 | Roller Load Right Hand P2 | 8353 | 8353 | 6200
500154923 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-LORH1 | Roller Load Right Hand P1 | 8353 | 8353 | 6200
500154922 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-IDLRH | Idler Track Right Hand | 8353 | 8353 | 6200
500154921 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-FDRRH | Final Drive Right Hand | 8353 | 8353 | 6200
500154920 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-CARRR | Roller Carrier Right Hand P2 | 8353 | 8353 | 6200
500154919 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-CARRF | Roller Carrier Right Hand P1 | 8353 | 8353 | 6200
500154918 | CLB-MP-EXCV-EX7141-UNDERC-TKFRR-ADJGR | Adjuster Track Grease RH | 8353 | 8353 | 6200
500154917 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-TRKLH | Assembly Track Left Hand | 8353 | 8353 | 6200
500154916 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-TENSL | Tensioner Track Hydraulic Left Hand | 8353 | 8353 | 6200
500154915 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-SPRKL | Sprocket Left Hand | 8353 | 8353 | 6200
500154914 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH9 | Roller Load Left Hand P9 | 8353 | 8353 | 6200
500154913 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH8 | Roller Load Left Hand P8 | 8353 | 8353 | 6200
500154912 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH7 | Roller Load Left Hand P7 | 8353 | 8353 | 6200
500154911 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH6 | Roller Load Left Hand P6 | 8353 | 8353 | 6200
500154910 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH5 | Roller Load Left Hand P5 | 8353 | 8353 | 6200
500154909 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH4 | Roller Load Left Hand P4 | 8353 | 8353 | 6200
500154908 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH3 | Roller Load Left Hand P3 | 8353 | 8353 | 6200
500154907 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH2 | Roller Load Left Hand P2 | 8353 | 8353 | 6200
500154906 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-LOLH1 | Roller Load Left Hand P1 | 8353 | 8353 | 6200
500154905 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-IDLLH | Idler Track Left Hand | 8353 | 8353 | 6200
500154904 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-FDRLH | Final Drive Left Hand | 8353 | 8353 | 6200
500154903 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-CARLR | Roller Carrier Left Hand P2 | 8353 | 8353 | 6200
500154902 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-CARLF | Roller Carrier Left Hand P1 | 8353 | 8353 | 6200
500154901 | CLB-MP-EXCV-EX7141-UNDERC-TKFRL-ADJGL | Adjuster Track Grease LH | 8353 | 8353 | 6200
500154900 | CLB-MP-EXCV-EX7141-UNDERC-SLEWB | Bearing Slew | 8353 | 8353 | 6200
500154899 | CLB-MP-EXCV-EX7141-UNDERC | Undercarriage | 8353 | 8353 | 6200
500154898 | CLB-MP-EXCV-EX7141-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 8353 | 8353 | 6200
500154897 | CLB-MP-EXCV-EX7141-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 8353 | 8353 | 6200
500154896 | CLB-MP-EXCV-EX7141-STRUCT-STICK-SLVRR | Bucket Link Shift Lever RH | 8353 | 8353 | 6200
500154895 | CLB-MP-EXCV-EX7141-STRUCT-STICK-SLVRL | Bucket Link Shift Lever LH | 8353 | 8353 | 6200
500154894 | CLB-MP-EXCV-EX7141-STRUCT-STICK-LINKR | Bucket Linkage RH | 8353 | 8353 | 6200
500154893 | CLB-MP-EXCV-EX7141-STRUCT-STICK-LINKL | Bucket Linkage LH | 8353 | 8353 | 6200
500154892 | CLB-MP-EXCV-EX7141-STRUCT-STICK | Stick Assembly | 8353 | 8353 | 6200
500154891 | CLB-MP-EXCV-EX7141-STRUCT-SRVCT | Service Centre | 8353 | 8353 | 6200
500154890 | CLB-MP-EXCV-EX7141-STRUCT-HDTNK | Tank Hydraulic | 8353 | 8353 | 6200
500154889 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-SEATO | Seat Operators | 8353 | 8353 | 6200
500154887 | CLB-MP-EXCV-EX7141-STRUCT-BUCKT | Bucket Assembly | 8353 | 8353 | 6200
500154886 | CLB-MP-EXCV-EX7141-STRUCT-BOOMS | Boom Assembly | 8353 | 8353 | 6200
500154885 | CLB-MP-EXCV-EX7141-STRUCT | Structure | 8353 | 8353 | 6200
500154884 | CLB-MP-EXCV-EX7141-PNEUMC-COMPR | Compressor Air System | 8353 | 8353 | 6200
500154883 | CLB-MP-EXCV-EX7141-MANGMT-UMMMC | Mine Monitoring & Control | 8353 | 8353 | 6200
500154882 | CLB-MP-EXCV-EX7141-HYDSYS-ROTRY | Rotary Connection | 8353 | 8353 | 6200
500154881 | CLB-MP-EXCV-EX7141-HYDSYS-PMPDR | Pump Drive-Splitter Gearbox | 8353 | 8353 | 6200
500154880 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-WPPP2 | Pump Work P3 & 4 | 8353 | 8353 | 6200
500154879 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-WPPP1 | Pump Work P1 & 2 | 8353 | 8353 | 6200
500154878 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-SWPP1 | Pump Swing P1 & 2 | 8353 | 4888 | 6200
500154877 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-SVPP1 | Pump Servo-Brg Lube | 8353 | 8353 | 6200
500154876 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-RPPP1 | Pump Replenishing | 8353 | 8353 | 6200
500154875 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-PTOLU | Pump Splitter Gear Box Lube | 8353 | 8353 | 6200
500154874 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-HECP1 | Pump Cooler Fan | 8353 | 8353 | 6200
500154873 | CLB-MP-EXCV-EX7141-HYDSYS-HYDPP-ACONP | Pump Aircon Drive | 8353 | 8353 | 6200
500154872 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 8353 | 8353 | 6200
500154871 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 8353 | 8353 | 6200
500154870 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVRU | Valve Main Control Right Hand Upper VB2 | 8353 | 8353 | 6200
500154869 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVRL | Valve Main Control Right Hand Lower VB3 | 8353 | 8353 | 6200
500154868 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVLU | Valve Main Control Left Hand Upper VB1 | 8353 | 8353 | 6200
500154867 | CLB-MP-EXCV-EX7141-HYDSYS-HDVLV-MCVLL | Valve Main Control Left Hand Lower VB4 | 8353 | 8353 | 6200
500154866 | CLB-MP-EXCV-EX7141-HYDSYS-HDOCO-OCHYR | Cooler Hyd Rear | 8353 | 8353 | 6200
500154865 | CLB-MP-EXCV-EX7141-HYDSYS-HDOCO-OCHYF | Cooler Hyd Front | 8353 | 8353 | 6200
500154864 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 8353 | 8353 | 6200
500154863 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 8353 | 8353 | 6200
500154862 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 8353 | 8353 | 6200
500154861 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 8353 | 8353 | 6200
500154860 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 8353 | 8353 | 6200
500154859 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 8353 | 8353 | 6200
500154858 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-FMEC4 | Motor Fan Eng Cooling LH Lower P4 | 8353 | 8353 | 6200
500154857 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-FMEC3 | Motor Fan Eng Cooling RH lower P3 | 8353 | 8353 | 6200
500154856 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-FMEC2 | Motor Fan Eng Cooling RH Upper P2 | 8353 | 8353 | 6200
500154855 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-FMEC1 | Motor Fan Eng Cooling LH Upper P1 | 8353 | 8353 | 6200
500154854 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-FMCH2 | Motor Fan Hyd Cooling Rear | 8353 | 8353 | 6200
500154853 | CLB-MP-EXCV-EX7141-HYDSYS-HDMOT-FMCH1 | Motor Fan Hyd Cooling Front | 8353 | 8353 | 6200
500154852 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps to Valves | 8353 | 8353 | 6200
500154851 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HSTCL | Hose Hydraulic Stick Cylinder | 8353 | 2659 | 6200
500154850 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HSPSM | Hose Hydraulic Swing Pump-Swing Motor | 8353 | 8353 | 6200
500154849 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 8353 | 8353 | 6200
500154848 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 8353 | 8353 | 6200
500154847 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HMCVV | Hose Hydraulic Main Valve Bank | 8353 | 8353 | 6200
500154845 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 8353 | 8353 | 6200
500154844 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBMCL | Hose Hydraulic Boom Cylinder | 8353 | 2659 | 6200
500154843 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBMAR | Hose Hydraulic Boom Arch | 8353 | 8353 | 6200
500154842 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HBKCL | Hose Hydraulic Bucket Cylinder | 8353 | 2659 | 6200
500154841 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 8353 | 8353 | 6200
500154840 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 8353 | 8353 | 6200
500154839 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 8353 | 8353 | 6200
500154838 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 8353 | 2659 | 6200
500154837 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 8353 | 3074 | 6200
500154836 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 8353 | 8353 | 6200
500154835 | CLB-MP-EXCV-EX7141-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 8353 | 8353 | 6200
500154834 | CLB-MP-EXCV-EX7141-HYDSYS-HDCFM-CFHP2 | Fan Cooling Hydraulic P2 | 8353 | 8353 | 6200
500154833 | CLB-MP-EXCV-EX7141-HYDSYS-HDCFM-CFHP1 | Fan Cooling Hydraulic P1 | 8353 | 8353 | 6200
500154832 | CLB-MP-EXCV-EX7141-HYDSYS-HDCFM-CFEP4 | Fan Cooling Engine Left Hand Lower P4 | 8353 | 8353 | 6200
500154831 | CLB-MP-EXCV-EX7141-HYDSYS-HDCFM-CFEP3 | Fan Cooling Engine Right Hand Lower P3 | 8353 | 8353 | 6200
500154830 | CLB-MP-EXCV-EX7141-HYDSYS-HDCFM-CFEP2 | Fan Cooling Engine Right Hand Upper P2 | 8353 | 8353 | 6200
500154829 | CLB-MP-EXCV-EX7141-HYDSYS-HDCFM-CFEP1 | Fan Cooling Engine Left Hand Upper P1 | 8353 | 8353 | 6200
500154828 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCS | Accumulator Servo | 8353 | 8353 | 6200
500154827 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCR | Accumulator Track Hydraulic Right Hand | 8353 | 8353 | 6200
500154826 | CLB-MP-EXCV-EX7141-HYDSYS-HDACC-HACCL | Accumulator Track Hydraulic Left Hand | 8353 | 8353 | 6200
500154825 | CLB-MP-EXCV-EX7141-HYDSYS | Hydraulic System | 8353 | 1263 | 6200
500154824 | CLB-MP-EXCV-EX7141-GRSYST-GRINJ | Auto Lube Injectors | 8353 | 8353 | 6200
500154823 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-GRTNK | Reservoir Auto Lube | 8353 | 8353 | 6200
500154822 | CLB-MP-EXCV-EX7141-GRSYST-AUTLU-ALBPP | Pump Auto Lube | 8353 | 8353 | 6200
500154821 | CLB-MP-EXCV-EX7141-FRSUPP | R9400 Fire Suppression System | 8353 | 8353 | 6200
500154820 | CLB-MP-EXCV-EX7141-ENGINE-ENGIN-TBOP2 | Turbocharger RH | 8353 | 8353 | 6200
500154819 | CLB-MP-EXCV-EX7141-ENGINE-ENGIN-TBOP1 | Turbocharger LH | 8353 | 8353 | 6200
500154818 | CLB-MP-EXCV-EX7141-ENGINE-ENGEX | Exhaust System Engine | 8353 | 8353 | 6200
500154817 | CLB-MP-EXCV-EX7141-ENGINE-COUPL | Engine Coupling | 8353 | 8353 | 6200
500154816 | CLB-MP-EXCV-EX7141-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 8353 | 8353 | 6200
500154815 | CLB-MP-EXCV-EX7141-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 8353 | 8353 | 6200
500154814 | CLB-MP-EXCV-EX7141-ENGINE-COSYS-RADTR | Radiator Engine | 8353 | 8353 | 6200
500154813 | CLB-MP-EXCV-EX7141-ENGINE-COSYS-LTWPP | Engine Water Pump Low Temperature | 8353 | 8353 | 6200
500154792 | CLB-MP-EXCV-EX7141-ENGINE-COSYS-HTWPP | Engine Water Pump High Temperature | 8353 | 8353 | 6200
500154791 | CLB-MP-EXCV-EX7141-ENGINE | Engine Assembly Liebherr D9812 | 8353 | 8353 | 6200
500154790 | CLB-MP-EXCV-EX7141-ELCTLV-START-STMLU | Starter Motor Eng P1 | 8353 | 8353 | 6200
500154789 | CLB-MP-EXCV-EX7141-ELCTLV-START-STMLL | Starter Motor Eng P2 | 8353 | 8353 | 6200
500154788 | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-BATST | Batteries Engine | 8353 | 3485 | 6200
500154787 | CLB-MP-EXCV-EX7141-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 8353 | 8353 | 6200
500154786 | CLB-MP-EXCV-EX7141-COMMUN-FLMGT | Fleet Management | 8353 | 8353 | 6200
500154784 | CLB-MP-EXCV-EX7141 | Liebherr R9400HP Excavator EX7141 | 8353 | 8353 | 6200
500150272 | CLB-MP-EXCV-EX7140 | R9400 Excavator EX7140 TRAVEL HOURS | 860 | 860 | 440
500157607 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 10954 | 1170 | 6200
500150614 | CLB-MP-EXCV-EX7140-ENGINE-ENGIN-TBOPR | Turbocharger Engine Low Pressure Rear | 10954 | 1170 | 6200
500150613 | CLB-MP-EXCV-EX7140-ENGINE-ENGIN-TBOPF | Turbocharger Engne Low Pressure Front | 10954 | 1170 | 6200
500150591 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-TRKRH | Assembly Track Right Hand | 10954 | 10954 | 6200
500150590 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-TENSL | Tensioner Track Hydraulic Right Hand | 10954 | 10954 | 6200
500150589 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-SPRKR | Sprocket Right Hand | 10954 | 10954 | 6200
500150588 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH9 | Roller Load Right Hand P9 | 10954 | 10954 | 6200
500150587 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH8 | Roller Load Right Hand P8 | 10954 | 10954 | 6200
500150586 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH7 | Roller Load Right Hand P7 | 10954 | 10954 | 6200
500150585 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH6 | Roller Load Right Hand P6 | 10954 | 10954 | 6200
500150584 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH5 | Roller Load Right Hand P5 | 10954 | 10954 | 6200
500150583 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH4 | Roller Load Right Hand P4 | 10954 | 10954 | 6200
500150582 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH3 | Roller Load Right Hand P3 | 10954 | 10954 | 6200
500150581 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH2 | Roller Load Right Hand P2 | 10954 | 10954 | 6200
500150580 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-LORH1 | Roller Load Right Hand P1 | 10954 | 10954 | 6200
500150579 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-IDLRH | Idler Track Right Hand | 10954 | 10954 | 6200
500150578 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-FDRRH | Final Drive Right Hand | 10954 | 10954 | 6200
500150577 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-CARRR | Roller Carrier Right Hand P2 | 10954 | 10954 | 6200
500150576 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-CARRF | Roller Carrier Right Hand P1 | 10954 | 10954 | 6200
500150575 | CLB-MP-EXCV-EX7140-UNDERC-TKFRR-ADJGR | Adjuster Track Grease RH | 10954 | 10954 | 6200
500150574 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-TRKLH | Assembly Track Left Hand | 10954 | 10954 | 6200
500150573 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-TENSL | Tensioner Track Hydraulic Left Hand | 10954 | 10954 | 6200
500150572 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-SPRKL | Sprocket Left Hand | 10954 | 10954 | 6200
500150571 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH9 | Roller Load Left Hand P9 | 10954 | 10954 | 6200
500150570 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH8 | Roller Load Left Hand P8 | 10954 | 10954 | 6200
500150569 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH7 | Roller Load Left Hand P7 | 10954 | 10954 | 6200
500150568 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH6 | Roller Load Left Hand P6 | 10954 | 10954 | 6200
500150567 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH5 | Roller Load Left Hand P5 | 10954 | 10954 | 6200
500150566 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH4 | Roller Load Left Hand P4 | 10954 | 10954 | 6200
500150565 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH3 | Roller Load Left Hand P3 | 10954 | 10954 | 6200
500150564 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH2 | Roller Load Left Hand P2 | 10954 | 10954 | 6200
500150563 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-LOLH1 | Roller Load Left Hand P1 | 10954 | 10954 | 6200
500150562 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-IDLLH | Idler Track Left Hand | 10954 | 10954 | 6200
500150561 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-FDRLH | Final Drive Left Hand | 10954 | 10954 | 6200
500150560 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-CARLR | Roller Carrier Left Hand P2 | 10954 | 10954 | 6200
500150559 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-CARLF | Roller Carrier Left Hand P1 | 10954 | 10954 | 6200
500150558 | CLB-MP-EXCV-EX7140-UNDERC-TKFRL-ADJGL | Adjuster Track Grease LH | 10954 | 10954 | 6200
500150557 | CLB-MP-EXCV-EX7140-UNDERC-SLEWB | Bearing Slew | 10954 | 10954 | 6200
500150556 | CLB-MP-EXCV-EX7140-UNDERC | Undercarriage | 10954 | 10954 | 6200
500150555 | CLB-MP-EXCV-EX7140-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 10954 | 10954 | 6200
500150554 | CLB-MP-EXCV-EX7140-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 10954 | 10954 | 6200
500150553 | CLB-MP-EXCV-EX7140-STRUCT-STICK-SLVRR | Bucket Link Shift Lever RH | 10954 | 10954 | 6200
500150552 | CLB-MP-EXCV-EX7140-STRUCT-STICK-SLVRL | Bucket Link Shift Lever LH | 10954 | 10954 | 6200
500150551 | CLB-MP-EXCV-EX7140-STRUCT-STICK-LINKR | Bucket Linkage RH | 10954 | 10954 | 6200
500150550 | CLB-MP-EXCV-EX7140-STRUCT-STICK-LINKL | Bucket Linkage LH | 10954 | 10954 | 6200
500150549 | CLB-MP-EXCV-EX7140-STRUCT-STICK | Stick Assembly | 10954 | 10954 | 6200
500150548 | CLB-MP-EXCV-EX7140-STRUCT-SRVCT | Service Centre | 10954 | 10954 | 6200
500150547 | CLB-MP-EXCV-EX7140-STRUCT-HDTNK | Tank Hydraulic | 10954 | 10954 | 6200
500150546 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-SEATO | Seat Operators | 10954 | 1170 | 6200
500150544 | CLB-MP-EXCV-EX7140-STRUCT-BUCKT | Bucket Assembly | 10954 | 10954 | 6200
500150543 | CLB-MP-EXCV-EX7140-STRUCT-BOOMS | Boom Assembly | 10954 | 10954 | 6200
500150542 | CLB-MP-EXCV-EX7140-STRUCT | Structure | 10954 | 10954 | 6200
500150541 | CLB-MP-EXCV-EX7140-PNEUMC-COMPR | Compressor Air System | 10954 | 1170 | 6200
500150540 | CLB-MP-EXCV-EX7140-MANGMT-UMMMC | Mine Monitoring & Control | 10954 | 10954 | 6200
500150539 | CLB-MP-EXCV-EX7140-HYDSYS-ROTRY | Rotary Connection | 10954 | 10954 | 6200
500150538 | CLB-MP-EXCV-EX7140-HYDSYS-PMPDR | Pump Drive-Splitter Gearbox | 10954 | 10954 | 6200
500150537 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-WPPP2 | Pump Work P3 & 4 | 10954 | 10954 | 6200
500150536 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-WPPP1 | Pump Work P1 & 2 | 10954 | 10954 | 6200
500150535 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-SWPP1 | Pump Swing P1 & 2 | 10954 | 1170 | 6200
500150534 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-SVPP1 | Pump Servo-Brg Lube | 10954 | 10954 | 6200
500150533 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-RPPP1 | Pump Replenishing | 10954 | 10954 | 6200
500150532 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-PTOLU | Pump Splitter Gear Box Lube | 10954 | 10954 | 6200
500150531 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-HECP1 | Pump Cooler Fan | 10954 | 10954 | 6200
500150530 | CLB-MP-EXCV-EX7140-HYDSYS-HYDPP-ACONP | Pump Aircon Drive | 10954 | 10954 | 6200
500150529 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 10954 | 10954 | 6200
500150528 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 10954 | 1170 | 6200
500150527 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-MCVRU | Valve Main Control Right Hand Upper VB2 | 10954 | 10954 | 6200
500150526 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-MCVRL | Valve Main Control Right Hand Lower VB3 | 10954 | 10954 | 6200
500150525 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-MCVLU | Valve Main Control Left Hand Upper VB1 | 10954 | 1170 | 6200
500150524 | CLB-MP-EXCV-EX7140-HYDSYS-HDVLV-MCVLL | Valve Main Control Left Hand Lower VB4 | 10954 | 10954 | 6200
500150523 | CLB-MP-EXCV-EX7140-HYDSYS-HDOCO-OCHYR | Cooler Hyd Rear | 10954 | 10954 | 6200
500150522 | CLB-MP-EXCV-EX7140-HYDSYS-HDOCO-OCHYF | Cooler Hyd Front | 10954 | 10954 | 6200
500150521 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 10954 | 10954 | 6200
500150520 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 10954 | 10954 | 6200
500150519 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 10954 | 10954 | 6200
500150518 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 10954 | 10954 | 6200
500150517 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 10954 | 10954 | 6200
500150516 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 10954 | 10954 | 6200
500150515 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-FMEC4 | Motor Fan Eng Cooling LH Lower P4 | 10954 | 1170 | 6200
500150514 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-FMEC3 | Motor Fan Eng Cooling RH lower P3 | 10954 | 1170 | 6200
500150513 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-FMEC2 | Motor Fan Eng Cooling RH Upper P2 | 10954 | 10954 | 6200
500150512 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-FMEC1 | Motor Fan Eng Cooling LH Upper P1 | 10954 | 10954 | 6200
500150511 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-FMCH2 | Motor Fan Hyd Cooling Rear | 10954 | 10954 | 6200
500150510 | CLB-MP-EXCV-EX7140-HYDSYS-HDMOT-FMCH1 | Motor Fan Hyd Cooling Front | 10954 | 10954 | 6200
500150509 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps to Valves | 10954 | 1170 | 6200
500150508 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HSTCL | Hose Hydraulic Stick Cylinder | 10954 | 10954 | 6200
500150507 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HSPSM | Hose Hydraulic Swing Pump-Swing Motor | 10954 | 1170 | 6200
500150506 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 10954 | 10954 | 6200
500150505 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 10954 | 10954 | 6200
500150504 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HMCVV | Hose Hydraulic Main Valve Bank | 10954 | 10954 | 6200
500150502 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 10954 | 10954 | 6200
500150501 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBMCL | Hose Hydraulic Boom Cylinder | 10954 | 10954 | 6200
500150500 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBMAR | Hose Hydraulic Boom Arch | 10954 | 672 | 6200
500150499 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HBKCL | Hose Hydraulic Bucket Cylinder | 10954 | 10954 | 6200
500150498 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 10954 | 10954 | 6200
500150497 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 10954 | 10954 | 6200
500150496 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 10954 | 10954 | 6200
500150495 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 10954 | 1170 | 6200
500150494 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 10954 | 1170 | 6200
500150493 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 10954 | 10954 | 6200
500150492 | CLB-MP-EXCV-EX7140-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 10954 | 10954 | 6200
500150491 | CLB-MP-EXCV-EX7140-HYDSYS-HDCFM-CFHP2 | Fan Cooling Hydraulic P2 | 10954 | 10954 | 6200
500150490 | CLB-MP-EXCV-EX7140-HYDSYS-HDCFM-CFHP1 | Fan Cooling Hydraulic P1 | 10954 | 10954 | 6200
500150489 | CLB-MP-EXCV-EX7140-HYDSYS-HDCFM-CFEP4 | Fan Cooling Engine Left Hand Lower P4 | 10954 | 10954 | 6200
500150488 | CLB-MP-EXCV-EX7140-HYDSYS-HDCFM-CFEP3 | Fan Cooling Engine Right Hand Lower P3 | 10954 | 10954 | 6200
500150487 | CLB-MP-EXCV-EX7140-HYDSYS-HDCFM-CFEP2 | Fan Cooling Engine Right Hand Upper P2 | 10954 | 10954 | 6200
500150486 | CLB-MP-EXCV-EX7140-HYDSYS-HDCFM-CFEP1 | Fan Cooling Engine Left Hand Upper P1 | 10954 | 10954 | 6200
500150485 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCS | Accumulator Servo | 10954 | 10954 | 6200
500150484 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCR | Accumulator Track Hydraulic Right Hand | 10954 | 10954 | 6200
500150483 | CLB-MP-EXCV-EX7140-HYDSYS-HDACC-HACCL | Accumulator Track Hydraulic Left Hand | 10954 | 10954 | 6200
500150482 | CLB-MP-EXCV-EX7140-HYDSYS | Hydraulic System | 10954 | 10954 | 6200
500150481 | CLB-MP-EXCV-EX7140-GRSYST-GRINJ | Auto Lube Injectors | 10954 | 672 | 6200
500150480 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-GRTNK | Reservoir Auto Lube | 10954 | 10954 | 6200
500150479 | CLB-MP-EXCV-EX7140-GRSYST-AUTLU-ALBPP | Pump Auto Lube | 10954 | 1170 | 6200
500150478 | CLB-MP-EXCV-EX7140-FRSUPP | R9400 Fire Suppression System | 10954 | 10954 | 6200
500150477 | CLB-MP-EXCV-EX7140-ENGINE-ENGIN-TBOP2 | Turbocharger RH | 10954 | 1170 | 6200
500150476 | CLB-MP-EXCV-EX7140-ENGINE-ENGIN-TBOP1 | Turbocharger LH | 10954 | 1170 | 6200
500150475 | CLB-MP-EXCV-EX7140-ENGINE-ENGEX | Exhaust System Engine | 10954 | 10954 | 6200
500150474 | CLB-MP-EXCV-EX7140-ENGINE-COUPL | Engine Coupling | 10954 | 10954 | 6200
500150472 | CLB-MP-EXCV-EX7140-ENGINE-COSYS-THERM | Thermostats & Regulators High Temp | 10954 | 1170 | 6200
500150471 | CLB-MP-EXCV-EX7140-ENGINE-COSYS-RADTR | Radiator Engine | 10954 | 10954 | 6200
500150469 | CLB-MP-EXCV-EX7140-ENGINE-COSYS-WTRPP | Engine Water Pump High Temperature | 10954 | 1170 | 6200
500150468 | CLB-MP-EXCV-EX7140-ENGINE | Engine Assembly Cummins QSK50 | 10954 | 10954 | 6200
500150467 | CLB-MP-EXCV-EX7140-ELCTLV-START-STMLU | Starter Motor Eng P1 | 10954 | 10954 | 6200
500150466 | CLB-MP-EXCV-EX7140-ELCTLV-START-STMLL | Starter Motor Eng P2 | 10954 | 10954 | 6200
500150465 | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-BATST | Batteries Engine | 10954 | 3519 | 6200
500150464 | CLB-MP-EXCV-EX7140-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 10954 | 10954 | 6200
500150463 | CLB-MP-EXCV-EX7140-COMMUN-FLMGT | Fleet Management | 10954 | 10954 | 6200
500150271 | CLB-MP-EXCV-EX7140 | Liebherr R9400HP Excavator EX7140 | 10954 | 10954 | 6200
500148668 | CLB-MP-EXCV-EX7139 | R9400 Excavator EX7139 TRAVEL HOURS | 835 | 835 | 440
500157606 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 11740 | 1367 | 6200
500156844 | CLB-MP-EXCV-EX7139-ENGINE-ENGIN-AFCLR | Aftercooler Engine | 11792 | 1367 | 6200
500156843 | CLB-MP-EXCV-EX7139-ENGINE-FUSYS-FUINJ | Fuel Injectors | 11792 | 1367 | 6200
500156842 | CLB-MP-EXCV-EX7139-ENGINE-FUSYS-FULPP | Fuel Pump Engine | 11792 | 1367 | 6200
500149007 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-TRKRH | Assembly Track Right Hand | 11792 | 11792 | 6200
500149006 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-TENSL | Tensioner Track Hydraulic Right Hand | 11792 | 11792 | 6200
500149005 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-SPRKR | Sprocket Right Hand | 11792 | 11792 | 6200
500149004 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH9 | Roller Load Right Hand P9 | 11792 | 11792 | 6200
500149003 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH8 | Roller Load Right Hand P8 | 11792 | 11792 | 6200
500149002 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH7 | Roller Load Right Hand P7 | 11792 | 11792 | 6200
500149001 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH6 | Roller Load Right Hand P6 | 11792 | 11792 | 6200
500149000 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH5 | Roller Load Right Hand P5 | 11792 | 11792 | 6200
500148999 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH4 | Roller Load Right Hand P4 | 11792 | 11792 | 6200
500148998 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH3 | Roller Load Right Hand P3 | 11792 | 11792 | 6200
500148997 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH2 | Roller Load Right Hand P2 | 11792 | 11792 | 6200
500148996 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-LORH1 | Roller Load Right Hand P1 | 11792 | 11792 | 6200
500148995 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-IDLRH | Idler Track Right Hand | 11792 | 11792 | 6200
500148994 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-FDRRH | Final Drive Right Hand | 11792 | 11792 | 6200
500148993 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-CARRR | Roller Carrier Right Hand P2 | 11792 | 11792 | 6200
500148992 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-CARRF | Roller Carrier Right Hand P1 | 11792 | 11792 | 6200
500148991 | CLB-MP-EXCV-EX7139-UNDERC-TKFRR-ADJGR | Adjuster Track Grease RH | 11792 | 11792 | 6200
500148990 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-TRKLH | Assembly Track Left Hand | 11792 | 11792 | 6200
500148989 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-TENSL | Tensioner Track Hydraulic Left Hand | 11792 | 11792 | 6200
500148988 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-SPRKL | Sprocket Left Hand | 11792 | 11792 | 6200
500148987 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH9 | Roller Load Left Hand P9 | 11792 | 11792 | 6200
500148986 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH8 | Roller Load Left Hand P8 | 11792 | 11792 | 6200
500148985 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH7 | Roller Load Left Hand P7 | 11792 | 11792 | 6200
500148984 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH6 | Roller Load Left Hand P6 | 11792 | 11792 | 6200
500148983 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH5 | Roller Load Left Hand P5 | 11792 | 11792 | 6200
500148982 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH4 | Roller Load Left Hand P4 | 11792 | 11792 | 6200
500148981 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH3 | Roller Load Left Hand P3 | 11792 | 11792 | 6200
500148980 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH2 | Roller Load Left Hand P2 | 11792 | 11792 | 6200
500148979 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-LOLH1 | Roller Load Left Hand P1 | 11792 | 10483 | 6200
500148978 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-IDLLH | Idler Track Left Hand | 11792 | 11792 | 6200
500148977 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-FDRLH | Final Drive Left Hand | 11792 | 11792 | 6200
500148976 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-CARLR | Roller Carrier Left Hand P2 | 11792 | 11792 | 6200
500148975 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-CARLF | Roller Carrier Left Hand P1 | 11792 | 11792 | 6200
500148974 | CLB-MP-EXCV-EX7139-UNDERC-TKFRL-ADJGL | Adjuster Track Grease LH | 11792 | 11792 | 6200
500148973 | CLB-MP-EXCV-EX7139-UNDERC-SLEWB | Bearing Slew | 11792 | 11792 | 6200
500148972 | CLB-MP-EXCV-EX7139-UNDERC | Undercarriage | 11792 | 11792 | 6200
500148971 | CLB-MP-EXCV-EX7139-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 11792 | 11792 | 6200
500148970 | CLB-MP-EXCV-EX7139-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 11792 | 11792 | 6200
500148969 | CLB-MP-EXCV-EX7139-STRUCT-STICK-SLVRR | Bucket Link Shift Lever RH | 11792 | 11792 | 6200
500148968 | CLB-MP-EXCV-EX7139-STRUCT-STICK-SLVRL | Bucket Link Shift Lever LH | 11792 | 11792 | 6200
500148967 | CLB-MP-EXCV-EX7139-STRUCT-STICK-LINKR | Bucket Linkage RH | 11792 | 11792 | 6200
500148966 | CLB-MP-EXCV-EX7139-STRUCT-STICK-LINKL | Bucket Linkage LH | 11792 | 11792 | 6200
500148965 | CLB-MP-EXCV-EX7139-STRUCT-STICK | Stick Assembly | 11792 | 11792 | 6200
500148964 | CLB-MP-EXCV-EX7139-STRUCT-SRVCT | Service Centre | 11792 | 11792 | 6200
500148963 | CLB-MP-EXCV-EX7139-STRUCT-HDTNK | Tank Hydraulic | 11792 | 11792 | 6200
500148962 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-SEATO | Seat Operators | 11792 | 3070 | 6200
500148960 | CLB-MP-EXCV-EX7139-STRUCT-BUCKT | Bucket Assembly | 11792 | 2318 | 6200
500148959 | CLB-MP-EXCV-EX7139-STRUCT-BOOMS | Boom Assembly | 11792 | 11792 | 6200
500148958 | CLB-MP-EXCV-EX7139-STRUCT | Structure | 11792 | 11792 | 6200
500148957 | CLB-MP-EXCV-EX7139-PNEUMC-COMPR | Compressor Air System | 11792 | 11792 | 6200
500148956 | CLB-MP-EXCV-EX7139-MANGMT-UMMMC | Mine Monitoring & Control | 11792 | 5210 | 6200
500148955 | CLB-MP-EXCV-EX7139-HYDSYS-ROTRY | Rotary Connection | 11792 | 11792 | 6200
500148954 | CLB-MP-EXCV-EX7139-HYDSYS-PMPDR | Pump Drive-Splitter Gearbox | 11792 | 11792 | 6200
500148953 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-WPPP2 | Pump Work P3 & 4 | 11792 | 11792 | 6200
500148952 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-WPPP1 | Pump Work P1 & 2 | 11792 | 11792 | 6200
500148951 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-SWPP1 | Pump Swing P1 & 2 | 11792 | 1367 | 6200
500148950 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-SVPP1 | Pump Servo-Brg Lube | 11792 | 11792 | 6200
500148949 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-RPPP1 | Pump Replenishing | 11792 | 11792 | 6200
500148948 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-PTOLU | Pump Splitter Gear Box Lube | 11792 | 11792 | 6200
500148947 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-HECP1 | Pump Cooler Fan | 11792 | 11792 | 6200
500148946 | CLB-MP-EXCV-EX7139-HYDSYS-HYDPP-ACONP | Pump Aircon Drive | 11792 | 11792 | 6200
500148945 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 11792 | 11792 | 6200
500148944 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 11792 | 1367 | 6200
500148943 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-MCVRU | Valve Main Control Right Hand Upper VB2 | 11792 | 11792 | 6200
500148942 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-MCVRL | Valve Main Control Right Hand Lower VB3 | 11792 | 11792 | 6200
500148941 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-MCVLU | Valve Main Control Left Hand Upper VB1 | 11792 | 1367 | 6200
500148940 | CLB-MP-EXCV-EX7139-HYDSYS-HDVLV-MCVLL | Valve Main Control Left Hand Lower VB4 | 11792 | 11792 | 6200
500148939 | CLB-MP-EXCV-EX7139-HYDSYS-HDOCO-OCHYR | Cooler Hyd Rear | 11792 | 11792 | 6200
500148938 | CLB-MP-EXCV-EX7139-HYDSYS-HDOCO-OCHYF | Cooler Hyd Front | 11792 | 11792 | 6200
500148937 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 11792 | 11792 | 6200
500148936 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 11792 | 11792 | 6200
500148935 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 11792 | 11792 | 6200
500148934 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 11792 | 11792 | 6200
500148933 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 11792 | 11792 | 6200
500148932 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 11792 | 11792 | 6200
500148931 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-FMEC4 | Motor Fan Eng Cooling LH Lower P4 | 11792 | 11792 | 6200
500148930 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-FMEC3 | Motor Fan Eng Cooling RH lower P3 | 11792 | 11792 | 6200
500148929 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-FMEC2 | Motor Fan Eng Cooling RH Upper P2 | 11792 | 11792 | 6200
500148928 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-FMEC1 | Motor Fan Eng Cooling LH Upper P1 | 11792 | 11792 | 6200
500148927 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-FMCH2 | Motor Fan Hyd Cooling Rear | 11792 | 11792 | 6200
500148926 | CLB-MP-EXCV-EX7139-HYDSYS-HDMOT-FMCH1 | Motor Fan Hyd Cooling Front | 11792 | 11792 | 6200
500148925 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps to Valves | 11792 | 1367 | 6200
500148924 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSTCL | Hose Hydraulic Stick Cylinder | 11792 | 7008 | 6200
500148923 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HSPSM | Hose Hydraulic Swing Pump-Swing Motor | 11792 | 1367 | 6200
500148922 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 11792 | 1367 | 6200
500148921 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 11792 | 1367 | 6200
500148920 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HMCVV | Hose Hydraulic Main Valve Bank | 11792 | 1367 | 6200
500148918 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 11792 | 1367 | 6200
500148917 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMCL | Hose Hydraulic Boom Cylinder | 11792 | 7008 | 6200
500148916 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBMAR | Hose Hydraulic Boom Arch | 11792 | 843 | 6200
500148915 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HBKCL | Hose Hydraulic Bucket Cylinder | 11792 | 7008 | 6200
500148914 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 11792 | 11792 | 6200
500148913 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 11792 | 11792 | 6200
500148912 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 11792 | 11792 | 6200
500148911 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 11792 | 1367 | 6200
500148910 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 11792 | 4733 | 6200
500148909 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 11792 | 11792 | 6200
500148908 | CLB-MP-EXCV-EX7139-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 11792 | 11792 | 6200
500148907 | CLB-MP-EXCV-EX7139-HYDSYS-HDCFM-CFHP2 | Fan Cooling Hydraulic P2 | 11792 | 11792 | 6200
500148906 | CLB-MP-EXCV-EX7139-HYDSYS-HDCFM-CFHP1 | Fan Cooling Hydraulic P1 | 11792 | 11792 | 6200
500148905 | CLB-MP-EXCV-EX7139-HYDSYS-HDCFM-CFEP4 | Fan Cooling Engine Left Hand Lower P4 | 11792 | 11792 | 6200
500148904 | CLB-MP-EXCV-EX7139-HYDSYS-HDCFM-CFEP3 | Fan Cooling Engine Right Hand Lower P3 | 11792 | 11792 | 6200
500148903 | CLB-MP-EXCV-EX7139-HYDSYS-HDCFM-CFEP2 | Fan Cooling Engine Right Hand Upper P2 | 11792 | 11792 | 6200
500148902 | CLB-MP-EXCV-EX7139-HYDSYS-HDCFM-CFEP1 | Fan Cooling Engine Left Hand Upper P1 | 11792 | 11792 | 6200
500148901 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCS | Accumulator Servo | 11792 | 1367 | 6200
500148900 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCR | Accumulator Track Hydraulic Right Hand | 11792 | 11792 | 6200
500148899 | CLB-MP-EXCV-EX7139-HYDSYS-HDACC-HACCL | Accumulator Track Hydraulic Left Hand | 11792 | 11792 | 6200
500148898 | CLB-MP-EXCV-EX7139-HYDSYS | Hydraulic System | 11792 | 11792 | 6200
500148897 | CLB-MP-EXCV-EX7139-GRSYST-GRINJ | Auto Lube Injectors | 11792 | 11792 | 6200
500148896 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-GRTNK | Reservoir Auto Lube | 11792 | 11792 | 6200
500148895 | CLB-MP-EXCV-EX7139-GRSYST-AUTLU-ALBPP | Pump Auto Lube | 11792 | 1367 | 6200
500148894 | CLB-MP-EXCV-EX7139-FRSUPP | R9400 Fire Suppression System | 11792 | 11792 | 6200
500148893 | CLB-MP-EXCV-EX7139-ENGINE-ENGIN-TBOP2 | Turbocharger RH | 11792 | 1367 | 6200
500148892 | CLB-MP-EXCV-EX7139-ENGINE-ENGIN-TBOP1 | Turbocharger LH | 11792 | 1367 | 6200
500148891 | CLB-MP-EXCV-EX7139-ENGINE-ENGEX | Exhaust System Engine | 11792 | 11792 | 6200
500148890 | CLB-MP-EXCV-EX7139-ENGINE-COUPL | Engine Coupling | 11792 | 11792 | 6200
500148889 | CLB-MP-EXCV-EX7139-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 11792 | 1367 | 6200
500148888 | CLB-MP-EXCV-EX7139-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 11792 | 1367 | 6200
500148887 | CLB-MP-EXCV-EX7139-ENGINE-COSYS-RADTR | Radiator Engine | 11792 | 11792 | 6200
500148886 | CLB-MP-EXCV-EX7139-ENGINE-COSYS-LTWPP | Engine Water Pump Low Temperature | 11792 | 1367 | 6200
500148885 | CLB-MP-EXCV-EX7139-ENGINE-COSYS-HTWPP | Engine Water Pump High Temperature | 11792 | 1367 | 6200
500148884 | CLB-MP-EXCV-EX7139-ENGINE | Engine Assembly Liebherr D9812 | 11792 | 11792 | 6200
500148883 | CLB-MP-EXCV-EX7139-ELCTLV-START-STMLU | Starter Motor Eng P1 | 11792 | 11792 | 6200
500148672 | CLB-MP-EXCV-EX7139-ELCTLV-START-STMLL | Starter Motor Eng P2 | 11792 | 11792 | 6200
500148671 | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-BATST | Batteries Engine | 11792 | 2453 | 6200
500148670 | CLB-MP-EXCV-EX7139-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 11792 | 11792 | 6200
500148669 | CLB-MP-EXCV-EX7139-COMMUN-FLMGT | Fleet Management | 11792 | 11792 | 6200
500148667 | CLB-MP-EXCV-EX7139 | Liebherr R9400HP Excavator EX7139 | 11792 | 11792 | 6200
500148615 | CLB-MP-EXCV-EX7133 | R9400E Excavator, EX7133 Travel Hours | 745 | 745 | 325
500158778 | CLB-MP-EXCV-EX7133-ELCTHV-HVC02-CABPR | S2 Cabinet Pressuriser Unit | 5658 | 5658 | 6200
500158777 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01-CABPR | S1 Cabinet Pressuriser Unit | 5658 | 5658 | 6200
500139296 | CLB-MP-EXCV-EX7133-STRUCT-AIRC2 | Motor Electrical Aircon Comp Drive Sys 2 | 13908 | 4116 | 6200
500139295 | CLB-MP-EXCV-EX7133-STRUCT-AIRC2 | Cabin Air Conditioning System 1 | 13907 | 13907 | 6200
500139293 | CLB-MP-EXCV-EX7133-STRUCT-AIRC1 | Motor Electrical Aircon Comp Drive Sys 1 | 13908 | 4116 | 6200
500138946 | CLB-MP-EXCV-EX7133-ELCTHV-HVC02 | SEPAM Protection Relay S2 Cabinet | 13908 | 13908 | 6200
500138945 | CLB-MP-EXCV-EX7133-ELCTHV-HVC02 | Transformer 24V S2 Cabinet | 13908 | 13908 | 6200
500138944 | CLB-MP-EXCV-EX7133-ELCTHV-HVC02 | Main Breaker Q1M 400V S2 Cabinet | 13908 | 13908 | 6200
500138943 | CLB-MP-EXCV-EX7133-ELCTHV-HVC02 | Pressuriser Unit S2 Cabinet | 13908 | 13908 | 6200
500138941 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Current Transformer S1 Cabinet | 13908 | 13908 | 6200
500138940 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Contactor Q1 S1 Cabinet | 13908 | 13908 | 6200
500138939 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Transformer Starter S1 Cabinet | 13908 | 13908 | 6200
500138938 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Transformer Voltage Measure S1 Cabinet | 13908 | 13908 | 6200
500138937 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Transformer 35kVA T2 S1 Cabinet | 13908 | 13908 | 6200
500138936 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Transformer 65kVA T5M S1 Cabinet | 13908 | 13908 | 6200
500138935 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Breaker Main S1 Cabinet | 13908 | 13908 | 6200
500138934 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Switch Load Break S1 Cabinet | 13908 | 13908 | 6200
500138933 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | Pressuriser Unit S1 Cabinet | 13908 | 13908 | 6200
500138908 | CLB-MP-EXCV-EX7133-ELCTHV-HVMOT | Main HV Drive Motor | 13908 | 13908 | 6200
500138907 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | Accumulator Ladder Hydraulic | 13908 | 4795 | 6200
500138906 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | Accumulator Servo Hydraulic | 13908 | 4795 | 6200
500138904 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | Accumulator Track Hydraulic R/H | 13908 | 13908 | 6200
500135828 | CLB-MP-EXCV-EX7133-COMMUN-FLMGT | Fleet Management | 13908 | 13908 | 6200
500135827 | CLB-MP-EXCV-EX7133-MANGMT-UMMMC | Mine Monitoring & Control | 13908 | 13908 | 6200
500135826 | CLB-MP-EXCV-EX7133-FRSUPP | Fire Suppression System | 13908 | 13908 | 6200
500135825 | CLB-MP-EXCV-EX7133-PNEUMC-COMPR | Compressor Air System | 13908 | 4700 | 6200
500135824 | CLB-MP-EXCV-EX7133-PNEUMC-AIRDR | Drier Air System | 13908 | 13908 | 6200
500135823 | CLB-MP-EXCV-EX7133-PNEUMC-PNTNK | Tank Air System | 13908 | 13908 | 6200
500135822 | CLB-MP-EXCV-EX7133-GRSYST-GRINJ | Auto Lube Injectors | 13908 | 4116 | 6200
500135821 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 13908 | 9063 | 6200
500135820 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-ALBPP | Auto Lube Pump P1 Attachment Slew | 13908 | 1906 | 6200
500135819 | CLB-MP-EXCV-EX7133-GRSYST-AUTLU-GRTNK | Reservoir Grease Auto Lube | 13908 | 13908 | 6200
500135818 | CLB-MP-EXCV-EX7133-STRUCT-BUCKT | Bucket Assembly | 13908 | 13908 | 6200
500135817 | CLB-MP-EXCV-EX7133-STRUCT-SRVCT | Service Centre | 13908 | 13908 | 6200
500135816 | CLB-MP-EXCV-EX7133-STRUCT-STICK-SLVRR | Linkage Bucket Link-Shift Lever RH | 13908 | 13908 | 6200
500135815 | CLB-MP-EXCV-EX7133-STRUCT-STICK-SLVRL | Linkage Bucket Link-Shift Lever LH | 13908 | 13908 | 6200
500135814 | CLB-MP-EXCV-EX7133-STRUCT-STICK-LINKR | Linkage Stick To Bucket RH | 13908 | 13908 | 6200
500135813 | CLB-MP-EXCV-EX7133-STRUCT-STICK-LINKL | Linkage Stick To Bucket LH | 13908 | 13908 | 6200
500135812 | CLB-MP-EXCV-EX7133-STRUCT-STICK | Stick Assembly | 13908 | 13908 | 6200
500135811 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS-LKBST | Linkage Boom to Stick | 13908 | 13908 | 6200
500135810 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS-LKBSS | Linkage Boom to Superstructure | 13908 | 13908 | 6200
500135809 | CLB-MP-EXCV-EX7133-STRUCT-BOOMS | Boom Assembly | 13908 | 4116 | 6200
500135808 | CLB-MP-EXCV-EX7133-STRUCT-HDTNK | Tank Hydraulic | 13908 | 13908 | 6200
500135807 | CLB-MP-EXCV-EX7133-STRUCT-CABIN-SEATO | Operators Seat | 13908 | 4795 | 6200
500135806 | CLB-MP-EXCV-EX7133-STRUCT-AIRC1 | Cabin Air Conditioning System | 13908 | 8694 | 6200
500135805 | CLB-MP-EXCV-EX7133-STRUCT-CABIN | Operators Cabin | 13908 | 13908 | 6200
500135804 | CLB-MP-EXCV-EX7133-STRUCT | Structure | 13908 | 13908 | 6200
500135803 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 13908 | 4116 | 6200
500135802 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 13908 | 4795 | 6200
500135801 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSPSM | Hose Hyd Swing Pump to Swing Motor | 13908 | 4795 | 6200
500135800 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps | 13908 | 4795 | 6200
500135799 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HMCVV | Hose Hyd Main Valve Bank | 13908 | 13908 | 6200
500135798 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBKCL | Hose Hyd Bucket Cylinder | 13908 | 389 | 6200
500135797 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSTCL | Hose Hyd Stick Cylinder | 13908 | 208 | 6200
500135795 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMCL | Hose Hyd Boom Cylinder | 13908 | 208 | 6200
500135794 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HLFPH | Hose Hyd Pilot | 13908 | 13908 | 6200
500135793 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HLFCR | Hoses Hyd Cascade Room | 13908 | 13908 | 6200
500135792 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HLFCO | Hoses Hyd Cooler | 13908 | 13908 | 6200
500135790 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 13908 | 13908 | 6200
500135787 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMAR | Hoses Hyd Boom Arch | 13908 | 13908 | 6200
500135786 | CLB-MP-EXCV-EX7133-HYDSYS-HDACC | Accumulator Track Hydraulic L/H | 13908 | 13908 | 6200
500135781 | CLB-MP-EXCV-EX7133-HYDSYS-HDCFM-CFHP2 | Fan Hyd Cooling System Pos 2 | 13908 | 13908 | 6200
500135780 | CLB-MP-EXCV-EX7133-HYDSYS-HDCFM-CFHP1 | Fan Hyd Cooling System Pos 1 | 13908 | 13908 | 6200
500135779 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMRR | Hyd Motor Travel RH Rear | 13908 | 13908 | 6200
500135778 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMRF | Hyd Motor Travel RH Front | 13908 | 13908 | 6200
500135777 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMLR | Hyd Motor Travel LH Rear | 13908 | 13908 | 6200
500135776 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-TRMLF | Hyd Motor Travel LH Front | 13908 | 13908 | 6200
500135775 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-FMCH2 | Hyd Motor Fan Hyd Cooling Rear | 13908 | 13908 | 6200
500135774 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-FMCH1 | Hyd Motor Fan Hyd Cooling Front | 13908 | 13908 | 6200
500135773 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 13908 | 13908 | 6200
500135772 | CLB-MP-EXCV-EX7133-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 13908 | 13908 | 6200
500135771 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 13908 | 4795 | 6200
500135770 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 13908 | 13908 | 6200
500135769 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVRU | Valve Main Control RH Upper | 13908 | 13908 | 6200
500135768 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVRL | Valve Main Control RH Lower | 13908 | 13908 | 6200
500135767 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVLU | Valve Main Control LH Upper | 13908 | 4795 | 6200
500135766 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MCVLL | Valve Main Control LH Lower | 13908 | 13908 | 6200
500135765 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VLVSR | Valve Hyd Secondary Relief | 13908 | 8423 | 6200
500135764 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VLVPR | Valve Primary Hyd Relief | 13908 | 13908 | 6200
500135763 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-VLVAU | Valve Hyd Auxiliary Control | 13908 | 13908 | 6200
500135762 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MONO2 | Valve Monoblock Boom RH | 13908 | 13908 | 6200
500135761 | CLB-MP-EXCV-EX7133-HYDSYS-HDVLV-MONO1 | Valve Monoblock Boom LH | 13908 | 13908 | 6200
500135760 | CLB-MP-EXCV-EX7133-HYDSYS-ROTRY | Rotary Connection | 13908 | 13908 | 6200
500135759 | CLB-MP-EXCV-EX7133-HYDSYS-HDOCO-OCHYR | Hyd Oil Cooler LH Rear | 13908 | 13908 | 6200
500135758 | CLB-MP-EXCV-EX7133-HYDSYS-HDOCO-OCHYF | Hyd Oil Cooler Hyd Front | 13908 | 13908 | 6200
500135757 | CLB-MP-EXCV-EX7133-HYDSYS-HDOCO-OCPTO | Hyd Oil Cooler Pump Drive | 13908 | 13908 | 6200
500135756 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH Lift | 13908 | 8495 | 6200
500135755 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH Lift | 13908 | 4116 | 6200
500135754 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 13908 | 13908 | 6200
500135753 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 13908 | 13908 | 6200
500135752 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 13908 | 13908 | 6200
500135751 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 13908 | 13908 | 6200
500135750 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 13908 | 13908 | 6200
500135749 | CLB-MP-EXCV-EX7133-HYDSYS-HDCYL-SHCYL | Cylinder Hatch Lock | 13908 | 13908 | 6200
500135748 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-RPPP1 | Hyd Pump Oil Replenishing | 13908 | 13908 | 6200
500135747 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-PTOLU | Lube Pump Splitter Gear Box | 13908 | 13908 | 6200
500135746 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-SVPP1 | Pump Servo Bearing Lube | 13908 | 13908 | 6200
500135745 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-HECP1 | Hyd Pump Fan Hyd Oil Cooler | 13908 | 13908 | 6200
500135744 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-SWPP1 | Hyd Pump Swing Pos1 & Pos2 | 13908 | 1906 | 6200
500135743 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-WPPP2 | Pump Hyd Work Pos3 & Pos4 | 13908 | 13908 | 6200
500135742 | CLB-MP-EXCV-EX7133-HYDSYS-HYDPP-WPPP1 | Pump Hyd Work Pos1 & Pos2 | 13908 | 13908 | 6200
500135741 | CLB-MP-EXCV-EX7133-HYDSYS-PMPDR-PDBRE | Breather Pump Drive | 13908 | 13908 | 6200
500135740 | CLB-MP-EXCV-EX7133-HYDSYS-PMPDR | Pump Drive/Splitter Gearbox | 13908 | 13908 | 6200
500135739 | CLB-MP-EXCV-EX7133-HYDSYS-TBKLH-TBKLR | Brake Travel LH Rear | 13908 | 13908 | 6200
500135738 | CLB-MP-EXCV-EX7133-HYDSYS-TBKLH-TBKLF | Brake Travel LH Front | 13908 | 13908 | 6200
500135737 | CLB-MP-EXCV-EX7133-HYDSYS-TBKRH-TBKRR | Brake Travel RH Rear | 13908 | 13908 | 6200
500135736 | CLB-MP-EXCV-EX7133-HYDSYS-TBKRH-TBKRF | Brake Travel RH Front | 13908 | 13908 | 6200
500135735 | CLB-MP-EXCV-EX7133-SWGSYS-SWBRK-SBKPR | Brake Swing P2 | 13908 | 13908 | 6200
500135734 | CLB-MP-EXCV-EX7133-SWGSYS-SWBRK-SBKPF | Brake Swing P1 | 13908 | 13908 | 6200
500135733 | CLB-MP-EXCV-EX7133-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 13908 | 4720 | 6200
500135732 | CLB-MP-EXCV-EX7133-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 13908 | 13908 | 6200
500135731 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-CARRR | Roller Carrier RH Pos2 | 13908 | 13908 | 6200
500135730 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-CARRF | Roller Carrier RH Pos1 | 13908 | 7211 | 6200
500135729 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH9 | Roller Load RH Pos9 | 13908 | 13908 | 6200
500135728 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH8 | Roller Load RH Pos8 | 13908 | 13908 | 6200
500135727 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH7 | Roller Load RH Pos7 | 13908 | 13908 | 6200
500135726 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH6 | Roller Load RH Pos6 | 13908 | 13908 | 6200
500135725 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH5 | Roller Load RH Pos5 | 13908 | 13908 | 6200
500135724 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH4 | Roller Load RH Pos4 | 13908 | 13908 | 6200
500135723 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH3 | Roller Load RH Pos3 | 13908 | 13908 | 6200
500135722 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH2 | Roller Load RH Pos2 | 13908 | 13908 | 6200
500135721 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-LORH1 | Roller Load RH Pos1 | 13908 | 13908 | 6200
500135720 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-TENSR | Track Hyd Tensioner RH | 13908 | 13908 | 6200
500135719 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-IDLRH | Track Idler RH | 13908 | 13908 | 6200
500135718 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-SPRKR | Sprocket RH | 13908 | 13908 | 6200
500135717 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-FDRRH | Final Drive RH Side | 13908 | 13908 | 6200
500135716 | CLB-MP-EXCV-EX7133-UNDERC-TKFRR-TRKRH | Track Assembly RH | 13908 | 13908 | 6200
500135715 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-CARLR | Roller Carrier LH Pos2 | 13908 | 13908 | 6200
500135714 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-CARLF | Roller Carrier LH Pos1 | 13908 | 13908 | 6200
500135713 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH9 | Roller Load LH Pos9 | 13908 | 13908 | 6200
500135712 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH8 | Roller Load LH Pos8 | 13908 | 13908 | 6200
500135711 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH7 | Roller Load LH Pos7 | 13908 | 13908 | 6200
500135710 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH6 | Roller Load LH Pos6 | 13908 | 13908 | 6200
500135709 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH5 | Roller Load LH Pos5 | 13908 | 13908 | 6200
500135708 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH4 | Roller Load LH Pos4 | 13908 | 13908 | 6200
500135707 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH3 | Roller Load LH Pos3 | 13908 | 13908 | 6200
500135706 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH2 | Roller Load LH Pos2 | 13908 | 13908 | 6200
500135705 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-LOLH1 | Roller Load LH Pos1 | 13908 | 13908 | 6200
500135704 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-TENSL | Track Hyd Tensioner LH | 13908 | 13908 | 6200
500135703 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-IDLLH | Track Idler LH | 13908 | 13908 | 6200
500135702 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-SPRKL | Sprocket LH | 13908 | 13908 | 6200
500135701 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-FDRLH | Final Drive LH Side | 13908 | 13908 | 6200
500135700 | CLB-MP-EXCV-EX7133-UNDERC-TKFRL-TRKLH | Track Assembly LH | 13908 | 13908 | 6200
500135699 | CLB-MP-EXCV-EX7133-UNDERC-SLEWB | Bearing Slew | 13908 | 13908 | 6200
500135698 | CLB-MP-EXCV-EX7133-UNDERC | Undercarriage | 13908 | 13908 | 6200
500135697 | CLB-MP-EXCV-EX7133-ELCTHV-HVC02 | S2 Electrical Cabinet | 13908 | 13908 | 6200
500135696 | CLB-MP-EXCV-EX7133-ELCTHV-HVC01 | S1 Electrical Cabinet | 13908 | 13908 | 6200
500135695 | CLB-MP-EXCV-EX7133-ELCTHV-HVMOT-COUPL | HV Motor Coupling | 13908 | 13908 | 6200
500135694 | CLB-MP-EXCV-EX7133-ELCTHV-HVMOT-ACMOT | Air Cond Comp Drive Motor | 13908 | 13908 | 6200
500135693 | CLB-MP-EXCV-EX7133-ELCTHV-HVMOT-DRMOT | Main HV Drive Motor | 13908 | 13908 | 6200
500135692 | CLB-MP-EXCV-EX7133-ELCTHV-HVRJO | Electrical HV Rotary Joint | 13908 | 13908 | 6200
500135691 | CLB-MP-EXCV-EX7133-ELCTHV-HVCRL | Cable Reeler | 13908 | 13908 | 6200
500135690 | CLB-MP-EXCV-EX7133-ELCTHV-HVCBL | High Voltage Cables | 13908 | 13908 | 6200
500135689 | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-BATST | Batteries | 13908 | 8694 | 6200
500135688 | CLB-MP-EXCV-EX7133-ELCTLV-CHARG-CACDC | Battery Charger ACDC | 13908 | 13908 | 6200
500135687 | CLB-MP-EXCV-EX7133 | EX7133 Liebherr R9400E Excavator | 13908 | 13908 | 6200
500131817 | CLB-MP-EXCV-EX7124-TRAVEL-TRKRH | Track Assembly Right Hand | 1756 | 1756 | 470
500131816 | CLB-MP-EXCV-EX7124-TRAVEL-TRKLH | Track Assembly Left Hand | 1756 | 1756 | 470
500131811 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKR | Sprocket Right Hand | 1756 | 1756 | 470
500131810 | CLB-MP-EXCV-EX7124-TRAVEL-SPRKL | Sprocket Left Hand | 1756 | 1756 | 470
500131797 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH7 | Roller Load Pos 7 Right Hand | 1756 | 1756 | 470
500131796 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH6 | Roller Load Pos 6 Right Hand | 1756 | 1756 | 470
500131795 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH5 | Roller Load Pos 5 Right Hand | 1756 | 1756 | 470
500131794 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH4 | Roller Load Pos 4 Right Hand | 1756 | 1756 | 470
500131793 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH3 | Roller Load Pos 3 Right Hand | 1756 | 1756 | 470
500131792 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH2 | Roller Load Pos 2 Right Hand | 1756 | 1756 | 470
500131791 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-LORH1 | Roller Load Pos 1 Right Hand | 1756 | 1756 | 470
500131790 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-IDLRH | Idler Track Right Hand | 1756 | 206 | 470
500131789 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-CARRR | Roller Carrier Right Hand Rear | 1756 | 1756 | 470
500131788 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-CARRF | Roller Carrier Right Hand Front | 1756 | 1756 | 470
500131786 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 Left Hand | 1756 | 1756 | 470
500131785 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 Left Hand | 1756 | 1756 | 470
500131784 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 Left Hand | 1756 | 1756 | 470
500131783 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 Left Hand | 1756 | 1756 | 470
500131782 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 Left Hand | 1756 | 1756 | 470
500131781 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 Left Hand | 1756 | 1756 | 470
500131780 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 Left Hand | 1756 | 1756 | 470
500131779 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-IDLLH | Idler Track Left Hand | 1756 | 206 | 470
500131778 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-CARLR | Roller Carrier Left Hand Rear | 1756 | 1756 | 470
500131777 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-CARLF | Roller Carrier Left Hand Front | 1756 | 1511 | 470
500131807 | CLB-MP-EXCV-EX7124-TRAVEL | 6040 Excavator, EX7124 TRAVEL HOURS | 1756 | 1756 | 470
500146780 | CLB-MP-EXCV-EX7124-HYDSYS-HDACC | Hydraulic Ladder Accumulator | 19559 | 19559 | 6700
500146779 | CLB-MP-EXCV-EX7124-HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 19559 | 19559 | 6700
500146778 | CLB-MP-EXCV-EX7124-HYDSYS-HDACC | Track Tension Accumulator RH | 19559 | 19559 | 6700
500146777 | CLB-MP-EXCV-EX7124-HYDSYS-HDACC | Track Tension Accumulator LH | 19559 | 19559 | 6700
500139323 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 19559 | 8295 | 6700
500131815 | CLB-MP-EXCV-EX7124-TRAVEL-TRBKR-TBKRR | Brake Travel Right Hand Rear | 19559 | 19559 | 6700
500131814 | CLB-MP-EXCV-EX7124-TRAVEL-TRBKR-TBKRF | Brake Travel Right Hand Front | 19559 | 19559 | 6700
500131813 | CLB-MP-EXCV-EX7124-TRAVEL-TRBKL-TBKLR | Brake Travel Left Hand Rear | 19559 | 19559 | 6700
500131812 | CLB-MP-EXCV-EX7124-TRAVEL-TRBKL-TBKLF | Brake Travel Left Hand Front | 19559 | 19559 | 6700
500131809 | CLB-MP-EXCV-EX7124-TRAVEL-FDRRH | Final Drive Right Hand | 19559 | 19559 | 6700
500131808 | CLB-MP-EXCV-EX7124-TRAVEL-FDRLH | Final Drive Left Hand | 19559 | 19559 | 6700
500131806 | CLB-MP-EXCV-EX7124-SWGSYS-SWLUB | Swing System Lubrication | 19559 | 19559 | 6700
500131805 | CLB-MP-EXCV-EX7124-SWGSYS-SWBRK-SBKRR | Brake Swing Right Hand Rear | 19559 | 19559 | 6700
500131804 | CLB-MP-EXCV-EX7124-SWGSYS-SWBRK-SBKRF | Brake Swing Right Hand Front | 19559 | 19559 | 6700
500131803 | CLB-MP-EXCV-EX7124-SWGSYS-SWBRK-SBKLR | Brake Swing Left Hand Rear | 19559 | 19559 | 6700
500131802 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBRR | Gearbox Swing Right Hand Rear | 19559 | 19559 | 6700
500131801 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBRF | Gearbox Swing Right Hand Front | 19559 | 19559 | 6700
500131800 | CLB-MP-EXCV-EX7124-SWGSYS-SWBOX-SGBLR | Gearbox Swing Left Hand Rear | 19559 | 19559 | 6700
500131799 | CLB-MP-EXCV-EX7124-STRUCT-UNDER-SLEWB | Slew Bearing | 19559 | 2565 | 6700
500131798 | CLB-MP-EXCV-EX7124-STRUCT-TKFRR-TENSR | Track Tensioner Right Hand | 19559 | 2055 | 6700
500131787 | CLB-MP-EXCV-EX7124-STRUCT-TKFRL-TENSR | Track Tensioner Left Hand | 19559 | 2055 | 6700
500131776 | CLB-MP-EXCV-EX7124-STRUCT-SUPER-ROLTK | Reserve Oil Tank | 19559 | 19559 | 6700
500131775 | CLB-MP-EXCV-EX7124-STRUCT-STICK | Stick Assembly | 19559 | 19559 | 6700
500131774 | CLB-MP-EXCV-EX7124-STRUCT-HLINK-LINKR | Stick To Bucket Linkages Right | 19559 | 19559 | 6700
500131773 | CLB-MP-EXCV-EX7124-STRUCT-HLINK-LINKL | Stick To Bucket Linkages Left | 19559 | 19559 | 6700
500131772 | CLB-MP-EXCV-EX7124-STRUCT-HLINK | H Link Assembly | 19559 | 19559 | 6700
500131771 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-SEATS | Operators Seat | 19559 | 9696 | 6700
500131770 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-SBELT | Seat Belt | 19559 | 19559 | 6700
500131769 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 19559 | 19559 | 6700
500131768 | CLB-MP-EXCV-EX7124-STRUCT-CABIN-AIRCR | Air Conditioning System | 19559 | 8295 | 6700
500131767 | CLB-MP-EXCV-EX7124-STRUCT-BUCKT | Bucket | 19559 | 19559 | 6700
500131766 | CLB-MP-EXCV-EX7124-STRUCT-BOOMS | Boom Static Lines | 19559 | 19559 | 6700
500131765 | CLB-MP-EXCV-EX7124-STRUCT-BOOMS | Boom Assembly | 19559 | 19559 | 6700
500131764 | CLB-MP-EXCV-EX7124-RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 19559 | 19559 | 6700
500131763 | CLB-MP-EXCV-EX7124-RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 19559 | 2565 | 6700
500131762 | CLB-MP-EXCV-EX7124-RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 19559 | 2565 | 6700
500131761 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-TBORH | RH Engine Turbocharger Right Hand Side | 19559 | 2565 | 6700
500131760 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-TBOLH | RH Engine Turbocharger Left Hand Side | 19559 | 2565 | 6700
500131759 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-EXHST | RH Engine Exhaust System | 19559 | 19559 | 6700
500131758 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 19559 | 19559 | 6700
500131757 | CLB-MP-EXCV-EX7124-RHENGN-INTEX-AFTER | RH Engine Aftercooler | 19559 | 2565 | 6700
500131756 | CLB-MP-EXCV-EX7124-RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 19559 | 2565 | 6700
500131755 | CLB-MP-EXCV-EX7124-RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 19559 | 2565 | 6700
500131754 | CLB-MP-EXCV-EX7124-RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 19559 | 19559 | 6700
500131753 | CLB-MP-EXCV-EX7124-RHENGN-COUPL | RH Engine Coupling | 19559 | 2565 | 6700
500131752 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-WTRPP | RH Engine Water Pump | 19559 | 2565 | 6700
500131751 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-THERM | RH Engine Thermostats & Regulators | 19559 | 2565 | 6700
500131750 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 19559 | 19559 | 6700
500131749 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-RADTR | RH Engine Radiator | 19559 | 2565 | 6700
500131748 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 19559 | 19559 | 6700
500131747 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 19559 | 19559 | 6700
500131746 | CLB-MP-EXCV-EX7124-RHENGN-COSYS-BELTS | RH Engine V Belts | 19559 | 2565 | 6700
500131744 | CLB-MP-EXCV-EX7124-RHENGN | RH Engine Assembly C32 | 19559 | 2565 | 6700
500131743 | CLB-MP-EXCV-EX7124-MANGMT-UMPMP | Pump Management System | 19559 | 19559 | 6700
500131742 | CLB-MP-EXCV-EX7124-MANGMT-UMMMC | Mine Monitoring and Control | 19559 | 19559 | 6700
500131741 | CLB-MP-EXCV-EX7124-MANGMT-UMENG | Engine Management System | 19559 | 19559 | 6700
500131740 | CLB-MP-EXCV-EX7124-MANGMT-UMBRD | Board Control System | 19559 | 19559 | 6700
500131739 | CLB-MP-EXCV-EX7124-LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 19559 | 19559 | 6700
500131738 | CLB-MP-EXCV-EX7124-LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 19559 | 2565 | 6700
500131737 | CLB-MP-EXCV-EX7124-LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 19559 | 2565 | 6700
500131736 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-TBORH | LH Engine Turbocharger Right Hand Side | 19559 | 2565 | 6700
500131735 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-TBOLH | LH Engine Turbocharger Left Hand Side | 19559 | 2565 | 6700
500131734 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-EXHST | LH Engine Exhaust System | 19559 | 19559 | 6700
500131733 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 19559 | 19559 | 6700
500131732 | CLB-MP-EXCV-EX7124-LHENGN-INTEX-AFTER | LH Engine Aftercooler | 19559 | 2565 | 6700
500131731 | CLB-MP-EXCV-EX7124-LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 19559 | 2565 | 6700
500131730 | CLB-MP-EXCV-EX7124-LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 19559 | 2565 | 6700
500131729 | CLB-MP-EXCV-EX7124-LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 19559 | 19559 | 6700
500131728 | CLB-MP-EXCV-EX7124-LHENGN-COUPL | LH Engine Coupling | 19559 | 19559 | 6700
500131727 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-WTRPP | LH Engine Water Pump | 19559 | 2565 | 6700
500131726 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-THERM | LH Engine Thermostats & Regulators | 19559 | 2565 | 6700
500131725 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 19559 | 19559 | 6700
500131724 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-RADTR | LH Engine Radiator | 19559 | 2565 | 6700
500131723 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 19559 | 19559 | 6700
500131722 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 19559 | 19559 | 6700
500131721 | CLB-MP-EXCV-EX7124-LHENGN-COSYS-BELTS | LH Engine V Belts | 19559 | 2565 | 6700
500131719 | CLB-MP-EXCV-EX7124-LHENGN | LH Engine Assembly C32 | 19559 | 2565 | 6700
500131718 | CLB-MP-EXCV-EX7124-HYDSYS-ROTRY | Rotary Joint | 19559 | 19559 | 6700
500131717 | CLB-MP-EXCV-EX7124-HYDSYS-PPDRR | Pump Drive Gearbox Right Hand | 19559 | 2565 | 6700
500131716 | CLB-MP-EXCV-EX7124-HYDSYS-PPDRL | Pump Drive Gearbox Left Hand | 19559 | 2565 | 6700
500131715 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPR | Pump Servo Right Hand | 19559 | 6544 | 6700
500131714 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SVPPL | Pump Servo Left Hand | 19559 | 6544 | 6700
500131713 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing Right Hand | 19559 | 6544 | 6700
500131712 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing Left Hand | 19559 | 6544 | 6700
500131711 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 19559 | 3107 | 6700
500131710 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 19559 | 6544 | 6700
500131709 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 19559 | 6544 | 6700
500131708 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 19559 | 6544 | 6700
500131707 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 19559 | 6544 | 6700
500131706 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 19559 | 6544 | 6700
500131705 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling Right Hand | 19559 | 2565 | 6700
500131704 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling Left Hand | 19559 | 2565 | 6700
500131703 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 19559 | 19559 | 6700
500131702 | CLB-MP-EXCV-EX7124-HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 19559 | 19559 | 6700
500131701 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-TCVVR | Travel Control Valve Block Right Hand | 19559 | 19559 | 6700
500131700 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-TCVVL | Travel Control Valve Block Left Hand | 19559 | 19559 | 6700
500131699 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-MCVVR | Main Control Valve Block Right Hand | 19559 | 19559 | 6700
500131698 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-MCVVL | Main Control Valve Block Left Hand | 19559 | 19559 | 6700
500131697 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-FTVRH | Valve Float Right Hand | 19559 | 19559 | 6700
500131696 | CLB-MP-EXCV-EX7124-HYDSYS-HDVLV-FTVLH | Valve Float Left Hand | 19559 | 19559 | 6700
500131695 | CLB-MP-EXCV-EX7124-HYDSYS-HDTNK | Tank Hydraulic | 19559 | 19559 | 6700
500131694 | CLB-MP-EXCV-EX7124-HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 19559 | 2055 | 6700
500131693 | CLB-MP-EXCV-EX7124-HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 19559 | 2055 | 6700
500131692 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 19559 | 5712 | 6700
500131691 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 19559 | 5733 | 6700
500131690 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 19559 | 1670 | 6700
500131689 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 19559 | 5733 | 6700
500131688 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMRR | Motor Swing Right Hand Rear | 19559 | 4086 | 6700
500131687 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMRF | Motor Swing Right Hand Front | 19559 | 4086 | 6700
500131686 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-SWMLR | Motor Swing Left Hand Rear | 19559 | 9603 | 6700
500131685 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 19559 | 2565 | 6700
500131684 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator Left Hand | 19559 | 2565 | 6700
500131683 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 19559 | 2565 | 6700
500131682 | CLB-MP-EXCV-EX7124-HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 19559 | 3275 | 6700
500131681 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 19559 | 10250 | 6700
500131680 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 19559 | 8295 | 6700
500131679 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 19559 | 8295 | 6700
500131678 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SWCRT | Swing Circuit Hoses | 19559 | 2589 | 6700
500131677 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SSTBR | 2nd Speed Travel Brake Release Hoses | 19559 | 8190 | 6700
500131676 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 19559 | 6544 | 6700
500131675 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 19559 | 1440 | 6700
500131674 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 19559 | 6544 | 6700
500131673 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 19559 | 6544 | 6700
500131672 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 19559 | 8295 | 6700
500131671 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 19559 | 2565 | 6700
500131670 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 19559 | 2565 | 6700
500131669 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 19559 | 2565 | 6700
500131668 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 19559 | 4086 | 6700
500131667 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 19559 | 10250 | 6700
500131666 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 19559 | 11480 | 6700
500131665 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 19559 | 10250 | 6700
500131664 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 19559 | 9696 | 6700
500131663 | CLB-MP-EXCV-EX7124-HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 19559 | 1440 | 6700
500131662 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 19559 | 7304 | 6700
500131661 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 19559 | 7278 | 6700
500131660 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 19559 | 899 | 6700
500131659 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 19559 | 8904 | 6700
500131658 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 19559 | 2565 | 6700
500131657 | CLB-MP-EXCV-EX7124-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 19559 | 2565 | 6700
500131656 | CLB-MP-EXCV-EX7124-HYDSYS-HDACC-HACCR | Accumulator Hydraulic Right Hand | 19559 | 19559 | 6700
500131655 | CLB-MP-EXCV-EX7124-HYDSYS-HDACC-HACCL | Accumulator Hydraulic Left Hand | 19559 | 19559 | 6700
500131654 | CLB-MP-EXCV-EX7124-HYDSYS | Hydraulic System | 19559 | 2589 | 6700
500131653 | CLB-MP-EXCV-EX7124-HYDSYS | Hydraulic Oil | 19559 | 2589 | 6700
500131652 | CLB-MP-EXCV-EX7124-GRSYST-GRTNK | Auto Lube Resevoir | 19559 | 19559 | 6700
500131651 | CLB-MP-EXCV-EX7124-GRSYST-GRINJ | Auto Lube Injectors | 19559 | 19559 | 6700
500131649 | CLB-MP-EXCV-EX7124-GRSYST-ALBPP | Auto Lube Pump | 19559 | 6544 | 6700
500131648 | CLB-MP-EXCV-EX7124-FRSUPP | Fire Suppression System | 19559 | 19559 | 6700
500131647 | CLB-MP-EXCV-EX7124-ELCTLV-START-STMRR | Starter Motor Right Hand Engine Upper | 19559 | 2565 | 6700
500131646 | CLB-MP-EXCV-EX7124-ELCTLV-START-STMRL | Starter Motor Right Hand Engine Lower | 19559 | 2565 | 6700
500131645 | CLB-MP-EXCV-EX7124-ELCTLV-START-STMLR | Starter Motor Left Hand Engine Upper | 19559 | 2565 | 6700
500131644 | CLB-MP-EXCV-EX7124-ELCTLV-START-STMLL | Starter Motor Left Hand Engine Lower | 19559 | 2565 | 6700
500131643 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-BATTY | Batteries | 19559 | 4086 | 6700
500131632 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-ALTRH | Alternator 24V Right Hand Engine | 19559 | 2565 | 6700
500131631 | CLB-MP-EXCV-EX7124-ELCTLV-CHARG-ALTLH | Alternator 24V Left Hand Engine | 19559 | 769 | 6700
500131630 | CLB-MP-EXCV-EX7124 | EX7124 Lubrication & Mechanical Services | 19559 | 19559 | 6700
500131629 | CLB-MP-EXCV-EX7124 | Caterpillar 6040 Excavator EX7124 | 19559 | 19559 | 6700
500136741 | CLB-MP-EXCV-EX7122-TRAVEL-TRKRH | Track Assembly Right Hand | 1344 | 1344 | 470
500136740 | CLB-MP-EXCV-EX7122-TRAVEL-TRKLH | Track Assembly Left Hand | 1344 | 1344 | 470
500136735 | CLB-MP-EXCV-EX7122-TRAVEL-SPRKR | Sprocket Right Hand | 1344 | 1344 | 470
500136734 | CLB-MP-EXCV-EX7122-TRAVEL-SPRKL | Sprocket Left Hand | 1344 | 1344 | 470
500136721 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH7 | Roller Load Pos 7 Right Hand | 1344 | 1344 | 470
500136720 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH6 | Roller Load Pos 6 Right Hand | 1344 | 1344 | 470
500136719 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH5 | Roller Load Pos 5 Right Hand | 1344 | 1344 | 470
500136718 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH4 | Roller Load Pos 4 Right Hand | 1344 | 1344 | 470
500136717 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH3 | Roller Load Pos 3 Right Hand | 1344 | 1344 | 470
500136716 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH2 | Roller Load Pos 2 Right Hand | 1344 | 1344 | 470
500136715 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-LORH1 | Roller Load Pos 1 Right Hand | 1344 | 1344 | 470
500136714 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-IDLRH | Idler Track Right Hand | 1344 | 1344 | 470
500136713 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-CARRR | Roller Carrier Right Hand Rear | 1344 | 1344 | 470
500136712 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-CARRF | Roller Carrier Right Hand Front | 1344 | 1344 | 470
500136710 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 Left Hand | 1344 | 1344 | 470
500136709 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 Left Hand | 1344 | 1344 | 470
500136708 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 Left Hand | 1344 | 1344 | 470
500136707 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 Left Hand | 1344 | 1344 | 470
500136706 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 Left Hand | 1344 | 1344 | 470
500136705 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 Left Hand | 1344 | 1344 | 470
500136704 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 Left Hand | 1344 | 1344 | 470
500136703 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-IDLLH | Idler Track Left Hand | 1344 | 1344 | 470
500136702 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-CARLR | Roller Carrier Left Hand Rear | 1344 | 1344 | 470
500136701 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-CARLF | Roller Carrier Left Hand Front | 1344 | 1344 | 470
500136731 | CLB-MP-EXCV-EX7122-TRAVEL | Travel Hours | 1344 | 1344 | 470
500139322 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 16452 | 10297 | 6700
500136739 | CLB-MP-EXCV-EX7122-TRAVEL-TRBKR-TBKRR | Brake Travel Right Hand Rear | 16452 | 16452 | 6700
500136738 | CLB-MP-EXCV-EX7122-TRAVEL-TRBKR-TBKRF | Brake Travel Right Hand Front | 16452 | 16452 | 6700
500136737 | CLB-MP-EXCV-EX7122-TRAVEL-TRBKL-TBKLR | Brake Travel Left Hand Rear | 16452 | 16452 | 6700
500136736 | CLB-MP-EXCV-EX7122-TRAVEL-TRBKL-TBKLF | Brake Travel Left Hand Front | 16452 | 16452 | 6700
500136733 | CLB-MP-EXCV-EX7122-TRAVEL-FDRRH | Final Drive Right Hand | 16452 | 16452 | 6700
500136732 | CLB-MP-EXCV-EX7122-TRAVEL-FDRLH | Final Drive Left Hand | 16452 | 16452 | 6700
500136730 | CLB-MP-EXCV-EX7122-SWGSYS-SWLUB | Swing System Lubrication | 16452 | 16452 | 6700
500136729 | CLB-MP-EXCV-EX7122-SWGSYS-SWBRK-SBKRR | Brake Swing Right Hand Rear | 16452 | 16452 | 6700
500136728 | CLB-MP-EXCV-EX7122-SWGSYS-SWBRK-SBKRF | Brake Swing Right Hand Front | 16452 | 7198 | 6700
500136727 | CLB-MP-EXCV-EX7122-SWGSYS-SWBRK-SBKLR | Brake Swing Left Hand Rear | 16452 | 16452 | 6700
500136726 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBRR | Gearbox Swing Right Hand Rear | 16452 | 16452 | 6700
500136725 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBRF | Gearbox Swing Right Hand Front | 16452 | 16452 | 6700
500136724 | CLB-MP-EXCV-EX7122-SWGSYS-SWBOX-SGBLR | Gearbox Swing Left Hand Rear | 16452 | 16452 | 6700
500136723 | CLB-MP-EXCV-EX7122-STRUCT-UNDER-SLEWB | Slew Bearing | 16452 | 16452 | 6700
500136722 | CLB-MP-EXCV-EX7122-STRUCT-TKFRR-TENSR | Track Tensioner Right Hand | 16452 | 16452 | 6700
500136711 | CLB-MP-EXCV-EX7122-STRUCT-TKFRL-TENSR | Track Tensioner Left Hand | 16452 | 16452 | 6700
500136700 | CLB-MP-EXCV-EX7122-STRUCT-SUPER-ROLTK | Reserve Oil Tank | 16452 | 16452 | 6700
500136699 | CLB-MP-EXCV-EX7122-STRUCT-STICK | Stick Assembly | 16452 | 16452 | 6700
500136698 | CLB-MP-EXCV-EX7122-STRUCT-HLINK-LINKR | Stick To Bucket Linkages Right | 16452 | 16452 | 6700
500136697 | CLB-MP-EXCV-EX7122-STRUCT-HLINK-LINKL | Stick To Bucket Linkages Left | 16452 | 16452 | 6700
500136696 | CLB-MP-EXCV-EX7122-STRUCT-HLINK | H Link Assembly | 16452 | 5151 | 6700
500136695 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-SEATS | Operators Seat | 16452 | 6191 | 6700
500136694 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-SBELT | Seat Belt | 16452 | 16452 | 6700
500136693 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 16452 | 16452 | 6700
500136692 | CLB-MP-EXCV-EX7122-STRUCT-CABIN-AIRCR | Air Conditioning System | 16452 | 10297 | 6700
500136691 | CLB-MP-EXCV-EX7122-STRUCT-BUCKT | Bucket | 16452 | 3196 | 6700
500136690 | CLB-MP-EXCV-EX7122-STRUCT-BOOMS | Boom Static Lines | 16452 | 16452 | 6700
500136689 | CLB-MP-EXCV-EX7122-STRUCT-BOOMS | Boom Assembly | 16452 | 16452 | 6700
500136688 | CLB-MP-EXCV-EX7122-RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 16452 | 16452 | 6700
500136687 | CLB-MP-EXCV-EX7122-RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 16452 | 16452 | 6700
500136686 | CLB-MP-EXCV-EX7122-RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 16452 | 16452 | 6700
500136685 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-TBORH | RH Engine Turbocharger Right Hand Side | 16452 | 7953 | 6700
500136684 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-TBOLH | RH Engine Turbocharger Left Hand Side | 16452 | 7953 | 6700
500136683 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-EXHST | RH Engine Exhaust System | 16452 | 16452 | 6700
500136682 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 16452 | 16452 | 6700
500136681 | CLB-MP-EXCV-EX7122-RHENGN-INTEX-AFTER | RH Engine Aftercooler | 16452 | 16452 | 6700
500136680 | CLB-MP-EXCV-EX7122-RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 16452 | 7953 | 6700
500136679 | CLB-MP-EXCV-EX7122-RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 16452 | 7953 | 6700
500136678 | CLB-MP-EXCV-EX7122-RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 16452 | 16452 | 6700
500136677 | CLB-MP-EXCV-EX7122-RHENGN-COUPL | RH Engine Coupling | 16452 | 16452 | 6700
500136676 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-WTRPP | RH Engine Water Pump | 16452 | 7953 | 6700
500136675 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-THERM | RH Engine Thermostats & Regulators | 16452 | 7953 | 6700
500136674 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 16452 | 16452 | 6700
500136673 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-RADTR | RH Engine Radiator | 16452 | 16452 | 6700
500136672 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 16452 | 16452 | 6700
500136671 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 16452 | 16452 | 6700
500136670 | CLB-MP-EXCV-EX7122-RHENGN-COSYS-BELTS | RH Engine V Belts | 16452 | 16452 | 6700
500136668 | CLB-MP-EXCV-EX7122-RHENGN | RH Engine Assembly C32 | 16452 | 16452 | 6700
500136667 | CLB-MP-EXCV-EX7122-MANGMT-UMPMP | Pump Management System | 16452 | 16452 | 6700
500136666 | CLB-MP-EXCV-EX7122-MANGMT-UMMMC | Mine Monitoring and Control | 16452 | 16452 | 6700
500136665 | CLB-MP-EXCV-EX7122-MANGMT-UMENG | Engine Management System | 16452 | 16452 | 6700
500136664 | CLB-MP-EXCV-EX7122-MANGMT-UMBRD | Board Control System | 16452 | 16452 | 6700
500136663 | CLB-MP-EXCV-EX7122-LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 16452 | 16452 | 6700
500136662 | CLB-MP-EXCV-EX7122-LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 16452 | 16452 | 6700
500136661 | CLB-MP-EXCV-EX7122-LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 16452 | 16452 | 6700
500136660 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-TBORH | LH Engine Turbocharger Right Hand Side | 16452 | 7953 | 6700
500136659 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-TBOLH | LH Engine Turbocharger Left Hand Side | 16452 | 7953 | 6700
500136658 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-EXHST | LH Engine Exhaust System | 16452 | 16452 | 6700
500136657 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 16452 | 16452 | 6700
500136656 | CLB-MP-EXCV-EX7122-LHENGN-INTEX-AFTER | LH Engine Aftercooler | 16452 | 16452 | 6700
500136655 | CLB-MP-EXCV-EX7122-LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 16452 | 7953 | 6700
500136654 | CLB-MP-EXCV-EX7122-LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 16452 | 7953 | 6700
500136653 | CLB-MP-EXCV-EX7122-LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 16452 | 16452 | 6700
500136652 | CLB-MP-EXCV-EX7122-LHENGN-COUPL | LH Engine Coupling | 16452 | 16452 | 6700
500136651 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-WTRPP | LH Engine Water Pump | 16452 | 7953 | 6700
500136650 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-THERM | LH Engine Thermostats & Regulators | 16452 | 7953 | 6700
500136649 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 16452 | 16452 | 6700
500136648 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-RADTR | LH Engine Radiator | 16452 | 16452 | 6700
500136647 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 16452 | 16452 | 6700
500136646 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 16452 | 16452 | 6700
500136645 | CLB-MP-EXCV-EX7122-LHENGN-COSYS-BELTS | LH Engine V Belts | 16452 | 16452 | 6700
500136643 | CLB-MP-EXCV-EX7122-LHENGN | LH Engine Assembly C32 | 16452 | 16452 | 6700
500136642 | CLB-MP-EXCV-EX7122-HYDSYS-ROTRY | Rotary Joint | 16452 | 16452 | 6700
500136641 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRR | Pump Drive Gearbox Right Hand | 16452 | 16452 | 6700
500136640 | CLB-MP-EXCV-EX7122-HYDSYS-PPDRL | Pump Drive Gearbox Left Hand | 16452 | 16452 | 6700
500136639 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPR | Pump Servo Right Hand | 16452 | 4768 | 6700
500136638 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SVPPL | Pump Servo Left Hand | 16452 | 4768 | 6700
500136637 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing Right Hand | 16452 | 16452 | 6700
500136636 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing Left Hand | 16452 | 16452 | 6700
500136635 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 16452 | 4768 | 6700
500136634 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 16452 | 5351 | 6700
500136633 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 16452 | 4768 | 6700
500136632 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 16452 | 4768 | 6700
500136631 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 16452 | 5351 | 6700
500136630 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 16452 | 5351 | 6700
500136629 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling Right Hand | 16452 | 16452 | 6700
500136628 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling Left Hand | 16452 | 16452 | 6700
500136627 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 16452 | 4768 | 6700
500136626 | CLB-MP-EXCV-EX7122-HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 16452 | 3837 | 6700
500136625 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-TCVVR | Travel Control Valve Block Right Hand | 16452 | 16452 | 6700
500136624 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-TCVVL | Travel Control Valve Block Left Hand | 16452 | 16452 | 6700
500136623 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-MCVVR | Main Control Valve Block Right Hand | 16452 | 16452 | 6700
500136622 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-MCVVL | Main Control Valve Block Left Hand | 16452 | 16452 | 6700
500136621 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-FTVRH | Valve Float Right Hand | 16452 | 16452 | 6700
500136620 | CLB-MP-EXCV-EX7122-HYDSYS-HDVLV-FTVLH | Valve Float Left Hand | 16452 | 16452 | 6700
500136619 | CLB-MP-EXCV-EX7122-HYDSYS-HDTNK | Tank Hydraulic | 16452 | 16452 | 6700
500136618 | CLB-MP-EXCV-EX7122-HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 16452 | 16452 | 6700
500136617 | CLB-MP-EXCV-EX7122-HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 16452 | 16452 | 6700
500136616 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 16452 | 3837 | 6700
500136615 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 16452 | 3837 | 6700
500136614 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 16452 | 139 | 6700
500136613 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 16452 | 8735 | 6700
500136612 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMRR | Motor Swing Right Hand Rear | 16452 | 1563 | 6700
500136611 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMRF | Motor Swing Right Hand Front | 16452 | 1563 | 6700
500136610 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-SWMLR | Motor Swing Left Hand Rear | 16452 | 1563 | 6700
500136609 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 16452 | 16452 | 6700
500136608 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator Left Hand | 16452 | 16452 | 6700
500136607 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 16452 | 16452 | 6700
500136606 | CLB-MP-EXCV-EX7122-HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 16452 | 16452 | 6700
500136605 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 16452 | 3837 | 6700
500136604 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 16452 | 3837 | 6700
500136603 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 16452 | 4768 | 6700
500136602 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SWCRT | Swing Circuit Hoses | 16452 | 1021 | 6700
500136601 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SSTBR | 2nd Speed Travel Brake Release Hoses | 16452 | 3837 | 6700
500136600 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 16452 | 3193 | 6700
500136599 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 16452 | 10297 | 6700
500136598 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 16452 | 2288 | 6700
500136597 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 16452 | 1563 | 6700
500136596 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 16452 | 3837 | 6700
500136595 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 16452 | 16452 | 6700
500136594 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 16452 | 16452 | 6700
500136593 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 16452 | 10297 | 6700
500136592 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 16452 | 2288 | 6700
500136591 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 16452 | 1563 | 6700
500136590 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 16452 | 1021 | 6700
500136589 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 16452 | 1563 | 6700
500136588 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 16452 | 4768 | 6700
500136587 | CLB-MP-EXCV-EX7122-HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 16452 | 2288 | 6700
500136586 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 16452 | 976 | 6700
500136585 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 16452 | 2288 | 6700
500136584 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 16452 | 1563 | 6700
500136583 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 16452 | 2288 | 6700
500136582 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 16452 | 16452 | 6700
500136581 | CLB-MP-EXCV-EX7122-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 16452 | 16452 | 6700
500136580 | CLB-MP-EXCV-EX7122-HYDSYS-HDACC-HACCR | Accumulator Hydraulic Right Hand | 16452 | 16452 | 6700
500136579 | CLB-MP-EXCV-EX7122-HYDSYS-HDACC-HACCL | Accumulator Hydraulic Left Hand | 16452 | 16452 | 6700
500136578 | CLB-MP-EXCV-EX7122-HYDSYS | Hydraulic System | 16452 | 3837 | 6700
500136577 | CLB-MP-EXCV-EX7122-HYDSYS | Hydraulic Oil | 16452 | 3837 | 6700
500136576 | CLB-MP-EXCV-EX7122-GRSYST-GRTNK | Auto Lube Resevoir | 16452 | 16452 | 6700
500136575 | CLB-MP-EXCV-EX7122-GRSYST-GRINJ | Auto Lube Injectors | 16452 | 16452 | 6700
500136574 | CLB-MP-EXCV-EX7122-GRSYST-ALBPU | Auto Lube Pump Undercarriage | 16452 | 16452 | 6700
500136573 | CLB-MP-EXCV-EX7122-GRSYST-ALBPP | Auto Lube Pump | 16452 | 4768 | 6700
500136572 | CLB-MP-EXCV-EX7122-FRSUPP | Fire Suppression System | 16452 | 5325 | 6700
500136571 | CLB-MP-EXCV-EX7122-ELCTLV-START-STMRR | Starter Motor Right Hand Engine Upper | 16452 | 7953 | 6700
500136570 | CLB-MP-EXCV-EX7122-ELCTLV-START-STMRL | Starter Motor Right Hand Engine Lower | 16452 | 7953 | 6700
500136569 | CLB-MP-EXCV-EX7122-ELCTLV-START-STMLR | Starter Motor Left Hand Engine Upper | 16452 | 7953 | 6700
500136568 | CLB-MP-EXCV-EX7122-ELCTLV-START-STMLL | Starter Motor Left Hand Engine Lower | 16452 | 7953 | 6700
500136567 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-BATTY | Batteries | 16452 | 5351 | 6700
500136566 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-ALTRH | Alternator 24V Right Hand Engine | 16452 | 7953 | 6700
500136565 | CLB-MP-EXCV-EX7122-ELCTLV-CHARG-ALTLH | Alternator 24V Left Hand Engine | 16452 | 6900 | 6700
500136564 | CLB-MP-EXCV-EX7122 | EX7124 Lubrication & Mechanical Services | 16452 | 16452 | 6700
500136563 | CLB-MP-EXCV-EX7122 | Caterpillar 6040 Excavator EX7122 | 16452 | 16452 | 6700
500126576 | CLB-MP-EXCV-EX7119-TRAVEL-TRKRH | Track Assembly Right Hand | 2901 | 1807 | 470
500126575 | CLB-MP-EXCV-EX7119-TRAVEL-TRKLH | Track Assembly Left Hand | 2901 | 1807 | 470
500126570 | CLB-MP-EXCV-EX7119-TRAVEL-SPRKR | Sprocket Right Hand | 2901 | 1807 | 470
500126569 | CLB-MP-EXCV-EX7119-TRAVEL-SPRKL | Sprocket Left Hand | 2901 | 1807 | 470
500126556 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH7 | Roller Load Pos 7 Right Hand | 2901 | 1807 | 470
500126555 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH6 | Roller Load Pos 6 Right Hand | 2901 | 1807 | 470
500126554 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH5 | Roller Load Pos 5 Right Hand | 2901 | 1807 | 470
500126553 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH4 | Roller Load Pos 4 Right Hand | 2901 | 1807 | 470
500126552 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH3 | Roller Load Pos 3 Right Hand | 2901 | 1807 | 470
500126551 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH2 | Roller Load Pos 2 Right Hand | 2901 | 1807 | 470
500126550 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-LORH1 | Roller Load Pos 1 Right Hand | 2901 | 1807 | 470
500126549 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-IDLRH | Idler Track Right Hand | 2901 | 1807 | 470
500126548 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-CARRR | Roller Carrier Right Hand Rear | 2901 | 1807 | 470
500126547 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-CARRF | Roller Carrier Right Hand Front | 2901 | 1807 | 470
500126544 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 Left Hand | 2901 | 1807 | 470
500126543 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 Left Hand | 2901 | 1807 | 470
500126542 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 Left Hand | 2901 | 1807 | 470
500126541 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 Left Hand | 2901 | 1807 | 470
500126540 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 Left Hand | 2901 | 1807 | 470
500126539 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 Left Hand | 2901 | 1807 | 470
500126538 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 Left Hand | 2901 | 1807 | 470
500126537 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-IDLLH | Idler Track Left Hand | 2901 | 1807 | 470
500126536 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-CARLR | Roller Carrier Left Hand Rear | 2901 | 1807 | 470
500126535 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-CARLF | Roller Carrier Left Hand Front | 2901 | 1807 | 470
500126566 | CLB-MP-EXCV-EX7119-TRAVEL | 6040 Excavator, EX7119 TRAVEL HOURS | 2901 | 1807 | 470
500146776 | CLB-MP-EXCV-EX7119-HYDSYS-HDACC | Hydraulic Ladder Accumulator | 27054 | 27054 | 6700
500146775 | CLB-MP-EXCV-EX7119-HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 27054 | 27054 | 6700
500146774 | CLB-MP-EXCV-EX7119-HYDSYS-HDACC | Track Tension Accumulator RH | 27054 | 27054 | 6700
500146773 | CLB-MP-EXCV-EX7119-HYDSYS-HDACC | Track Tension Accumulator LH | 27054 | 27054 | 6700
500139325 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 19940 | 6054 | 6700
500126574 | CLB-MP-EXCV-EX7119-TRAVEL-TRBKR-TBKRR | Brake Travel Right Hand Rear | 27054 | 10337 | 6700
500126573 | CLB-MP-EXCV-EX7119-TRAVEL-TRBKR-TBKRF | Brake Travel Right Hand Front | 27054 | 10337 | 6700
500126572 | CLB-MP-EXCV-EX7119-TRAVEL-TRBKL-TBKLR | Brake Travel Left Hand Rear | 27054 | 10337 | 6700
500126571 | CLB-MP-EXCV-EX7119-TRAVEL-TRBKL-TBKLF | Brake Travel Left Hand Front | 27054 | 10337 | 6700
500126568 | CLB-MP-EXCV-EX7119-TRAVEL-FDRRH | Final Drive Right Hand | 27054 | 10337 | 6700
500126567 | CLB-MP-EXCV-EX7119-TRAVEL-FDRLH | Final Drive Left Hand | 27054 | 10337 | 6700
500126565 | CLB-MP-EXCV-EX7119-SWGSYS-SWLUB | Swing System Lubrication | 27054 | 27054 | 6700
500126564 | CLB-MP-EXCV-EX7119-SWGSYS-SWBRK-SBKRR | Brake Swing Right Hand Rear | 27054 | 6054 | 6700
500126563 | CLB-MP-EXCV-EX7119-SWGSYS-SWBRK-SBKRF | Brake Swing Right Hand Front | 27054 | 3148 | 6700
500126562 | CLB-MP-EXCV-EX7119-SWGSYS-SWBRK-SBKLR | Brake Swing Left Hand Rear | 27054 | 6054 | 6700
500126561 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBRR | Gearbox Swing Right Hand Rear | 27054 | 6054 | 6700
500126560 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBRF | Gearbox Swing Right Hand Front | 27054 | 6054 | 6700
500126559 | CLB-MP-EXCV-EX7119-SWGSYS-SWBOX-SGBLR | Gearbox Swing Left Hand Rear | 27054 | 6054 | 6700
500126558 | CLB-MP-EXCV-EX7119-STRUCT-UNDER-SLEWB | Slew Bearing | 27054 | 27054 | 6700
500126557 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR-TENSR | Track Tensioner Right Hand | 27054 | 10337 | 6700
500126546 | CLB-MP-EXCV-EX7119-STRUCT-TKFRR | 6040 RH Track Wear EX7119 | 27054 | 10337 | 42
500126545 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL-TENSR | Track Tensioner Left Hand | 27054 | 10337 | 6700
500126534 | CLB-MP-EXCV-EX7119-STRUCT-TKFRL | 6040 LH Track Wear EX7119 | 27054 | 10337 | 42
500126533 | CLB-MP-EXCV-EX7119-STRUCT-SUPER-ROLTK | Reserve Oil Tank | 27054 | 27054 | 6700
500126532 | CLB-MP-EXCV-EX7119-STRUCT-STICK | Stick Assembly | 27054 | 27054 | 6700
500126531 | CLB-MP-EXCV-EX7119-STRUCT-HLINK-LINKR | Stick To Bucket Linkages Right | 27054 | 27054 | 6700
500126530 | CLB-MP-EXCV-EX7119-STRUCT-HLINK-LINKL | Stick To Bucket Linkages Left | 27054 | 27054 | 6700
500126529 | CLB-MP-EXCV-EX7119-STRUCT-HLINK | H Link Assembly | 27054 | 4463 | 6700
500126528 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-SEATS | Operators Seat | 27054 | 1520 | 6700
500126527 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-SBELT | Seat Belt | 27054 | 27054 | 6700
500126526 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 27054 | 27054 | 6700
500126525 | CLB-MP-EXCV-EX7119-STRUCT-CABIN-AIRCR | Air Conditioning System | 27054 | 19941 | 6700
500126524 | CLB-MP-EXCV-EX7119-STRUCT-BUCKT | Bucket | 27054 | 4463 | 6700
500126523 | CLB-MP-EXCV-EX7119-STRUCT-BOOMS | Boom Static Lines | 27054 | 27054 | 6700
500126522 | CLB-MP-EXCV-EX7119-STRUCT-BOOMS | Boom Assembly | 27054 | 27054 | 6700
500126521 | CLB-MP-EXCV-EX7119-RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 27054 | 27054 | 6700
500126520 | CLB-MP-EXCV-EX7119-RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 27054 | 27054 | 6700
500126519 | CLB-MP-EXCV-EX7119-RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 27054 | 27054 | 6700
500126518 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-TBORH | RH Engine Turbocharger Right Hand Side | 27054 | 1520 | 6700
500126517 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-TBOLH | RH Engine Turbocharger Left Hand Side | 27054 | 1520 | 6700
500126516 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-EXHST | RH Engine Exhaust System | 27054 | 27054 | 6700
500126515 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 27054 | 27054 | 6700
500126514 | CLB-MP-EXCV-EX7119-RHENGN-INTEX-AFTER | RH Engine Aftercooler | 27054 | 8438 | 6700
500126513 | CLB-MP-EXCV-EX7119-RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 27054 | 1520 | 6700
500126512 | CLB-MP-EXCV-EX7119-RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 27054 | 1520 | 6700
500126511 | CLB-MP-EXCV-EX7119-RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 27054 | 27054 | 6700
500126510 | CLB-MP-EXCV-EX7119-RHENGN-COUPL | RH Engine Coupling | 27054 | 27054 | 6700
500126509 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-WTRPP | RH Engine Water Pump | 27054 | 1520 | 6700
500126508 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-THERM | RH Engine Thermostats & Regulators | 27054 | 1520 | 6700
500126507 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 27054 | 27054 | 6700
500126506 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-RADTR | RH Engine Radiator | 27054 | 7738 | 6700
500126505 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 27054 | 27054 | 6700
500126504 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 27054 | 27054 | 6700
500126503 | CLB-MP-EXCV-EX7119-RHENGN-COSYS-BELTS | RH Engine V Belts | 27054 | 27054 | 6700
500126501 | CLB-MP-EXCV-EX7119-RHENGN | RH Engine Assembly C32 | 27054 | 1520 | 6700
500126500 | CLB-MP-EXCV-EX7119-MANGMT-UMPMP | Pump Management System | 27054 | 27054 | 6700
500126499 | CLB-MP-EXCV-EX7119-MANGMT-UMMMC | Mine Monitoring and Control | 27054 | 1520 | 6700
500126498 | CLB-MP-EXCV-EX7119-MANGMT-UMENG | Engine Management System | 27054 | 27054 | 6700
500126497 | CLB-MP-EXCV-EX7119-MANGMT-UMBRD | Board Control System | 27054 | 27054 | 6700
500126496 | CLB-MP-EXCV-EX7119-LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 27054 | 27054 | 6700
500126495 | CLB-MP-EXCV-EX7119-LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 27054 | 27054 | 6700
500126494 | CLB-MP-EXCV-EX7119-LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 27054 | 27054 | 6700
500126493 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-TBORH | LH Engine Turbocharger Right Hand Side | 27054 | 5348 | 6700
500126492 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-TBOLH | LH Engine Turbocharger Left Hand Side | 27054 | 5348 | 6700
500126491 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-EXHST | LH Engine Exhaust System | 27054 | 27054 | 6700
500126490 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 27054 | 27054 | 6700
500126489 | CLB-MP-EXCV-EX7119-LHENGN-INTEX-AFTER | LH Engine Aftercooler | 27054 | 8823 | 6700
500126488 | CLB-MP-EXCV-EX7119-LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 27054 | 5348 | 6700
500126487 | CLB-MP-EXCV-EX7119-LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 27054 | 5348 | 6700
500126486 | CLB-MP-EXCV-EX7119-LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 27054 | 27054 | 6700
500126485 | CLB-MP-EXCV-EX7119-LHENGN-COUPL | LH Engine Coupling | 27054 | 27054 | 6700
500126484 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-WTRPP | LH Engine Water Pump | 27054 | 5348 | 6700
500126483 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-THERM | LH Engine Thermostats & Regulators | 27054 | 5348 | 6700
500126482 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 27054 | 27054 | 6700
500126481 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-RADTR | LH Engine Radiator | 27054 | 8823 | 6700
500126480 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 27054 | 27054 | 6700
500126479 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 27054 | 27054 | 6700
500126478 | CLB-MP-EXCV-EX7119-LHENGN-COSYS-BELTS | LH Engine V Belts | 27054 | 27054 | 6700
500126476 | CLB-MP-EXCV-EX7119-LHENGN | LH Engine Assembly C32 | 27054 | 5348 | 6700
500126475 | CLB-MP-EXCV-EX7119-HYDSYS-ROTRY | Rotary Joint | 27054 | 1520 | 6700
500126474 | CLB-MP-EXCV-EX7119-HYDSYS-PPDRR | Pump Drive Gearbox Right Hand | 27054 | 8476 | 6700
500126473 | CLB-MP-EXCV-EX7119-HYDSYS-PPDRL | Pump Drive Gearbox Left Hand | 27054 | 9084 | 6700
500126472 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SVPPR | Pump Servo Right Hand | 27054 | 1985 | 6700
500126471 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SVPPL | Pump Servo Left Hand | 27054 | 1985 | 6700
500126470 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing Right Hand | 27054 | 1985 | 6700
500126469 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing Left Hand | 27054 | 1985 | 6700
500126468 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 27054 | 1985 | 6700
500126467 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 27054 | 1985 | 6700
500126466 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 27054 | 1985 | 6700
500126465 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 27054 | 4463 | 6700
500126464 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 27054 | 322 | 6700
500126463 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 27054 | 1162 | 6700
500126462 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling Right Hand | 27054 | 9736 | 6700
500126461 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling Left Hand | 27054 | 9736 | 6700
500126460 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 27054 | 27054 | 6700
500126459 | CLB-MP-EXCV-EX7119-HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 27054 | 27054 | 6700
500126458 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-TCVVR | Travel Control Valve Block Right Hand | 27054 | 27054 | 6700
500126457 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-TCVVL | Travel Control Valve Block Left Hand | 27054 | 27054 | 6700
500126456 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-MCVVR | Main Control Valve Block Right Hand | 27054 | 27054 | 6700
500126455 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-MCVVL | Main Control Valve Block Left Hand | 27054 | 27054 | 6700
500126454 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-FTVRH | Valve Float Right Hand | 27054 | 27054 | 6700
500126453 | CLB-MP-EXCV-EX7119-HYDSYS-HDVLV-FTVLH | Valve Float Left Hand | 27054 | 27054 | 6700
500126452 | CLB-MP-EXCV-EX7119-HYDSYS-HDTNK | Tank Hydraulic | 27054 | 27054 | 6700
500126451 | CLB-MP-EXCV-EX7119-HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 27054 | 3710 | 6700
500126450 | CLB-MP-EXCV-EX7119-HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 27054 | 3710 | 6700
500126449 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 27054 | 10337 | 6700
500126448 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 27054 | 10337 | 6700
500126447 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 27054 | 10337 | 6700
500126446 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 27054 | 10337 | 6700
500126445 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRR | Motor Swing Right Hand Rear | 27054 | 11930 | 6700
500126444 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMRF | Motor Swing Right Hand Front | 27054 | 11930 | 6700
500126443 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-SWMLR | Motor Swing Left Hand Rear | 27054 | 11941 | 6700
500126442 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 27054 | 3277 | 6700
500126441 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator Left Hand | 27054 | 1722 | 6700
500126440 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 27054 | 9736 | 6700
500126439 | CLB-MP-EXCV-EX7119-HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 27054 | 13200 | 6700
500126438 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 27054 | 1520 | 6700
500126437 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 27054 | 1520 | 6700
500126436 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 27054 | 1520 | 6700
500126435 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 27054 | 6054 | 6700
500126434 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SSTBR | 2nd Speed Travel Brake Release Hoses | 27054 | 1520 | 6700
500126433 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 27054 | 1021 | 6700
500126432 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 27054 | 8438 | 6700
500126431 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 27054 | 1021 | 6700
500126430 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 27054 | 1021 | 6700
500126429 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 27054 | 1520 | 6700
500126428 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 27054 | 9084 | 6700
500126427 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 27054 | 9084 | 6700
500126426 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 27054 | 180 | 6700
500126425 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 27054 | 14526 | 6700
500126424 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 27054 | 5348 | 6700
500126423 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 27054 | 3710 | 6700
500126422 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 27054 | 3710 | 6700
500126421 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 27054 | 14228 | 6700
500126420 | CLB-MP-EXCV-EX7119-HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 27054 | 11930 | 6700
500126419 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 27054 | 4463 | 6700
500126418 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 27054 | 1520 | 6700
500126417 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 27054 | 6054 | 6700
500126416 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 27054 | 5348 | 6700
500126415 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 27054 | 8059 | 6700
500126414 | CLB-MP-EXCV-EX7119-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 27054 | 6979 | 6700
500126413 | CLB-MP-EXCV-EX7119-HYDSYS-HDACC-HACCR | Accumulator Hydraulic Right Hand | 27054 | 20483 | 6700
500126412 | CLB-MP-EXCV-EX7119-HYDSYS-HDACC-HACCL | Accumulator Hydraulic Left Hand | 27054 | 27054 | 6700
500126411 | CLB-MP-EXCV-EX7119-HYDSYS | Hydraulic System | 27054 | 322 | 6700
500126410 | CLB-MP-EXCV-EX7119-HYDSYS | Hydraulic Oil | 27054 | 180 | 6700
500126409 | CLB-MP-EXCV-EX7119-GRSYST-GRTNK | Auto Lube Resevoir | 27054 | 27054 | 6700
500126408 | CLB-MP-EXCV-EX7119-GRSYST-GRINJ | Auto Lube Injectors | 27054 | 27054 | 6700
500126406 | CLB-MP-EXCV-EX7119-GRSYST-ALBPP | Auto Lube Pump | 27054 | 4463 | 6700
500126405 | CLB-MP-EXCV-EX7119-FRSUPP | Fire Suppression System | 27054 | 27054 | 6700
500126404 | CLB-MP-EXCV-EX7119-ELCTLV-START-STMRR | Starter Motor Right Hand Engine Upper | 27054 | 1520 | 6700
500126403 | CLB-MP-EXCV-EX7119-ELCTLV-START-STMRL | Starter Motor Right Hand Engine Lower | 27054 | 1520 | 6700
500126402 | CLB-MP-EXCV-EX7119-ELCTLV-START-STMLR | Starter Motor Left Hand Engine Upper | 27054 | 5348 | 6700
500126401 | CLB-MP-EXCV-EX7119-ELCTLV-START-STMLL | Starter Motor Left Hand Engine Lower | 27054 | 5348 | 6700
500126400 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-BATTY | EX7119 Batteries | 27054 | 3710 | 6700
500126399 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-ALTRH | Alternator 24V Right Hand Engine | 27054 | 1520 | 6700
500126398 | CLB-MP-EXCV-EX7119-ELCTLV-CHARG-ALTLH | Alternator 24V Left Hand Engine | 27054 | 4463 | 6700
500126397 | CLB-MP-EXCV-EX7119 | EX7119 Lubrication & Mechanical Services | 27054 | 27054 | 6700
500126396 | CLB-MP-EXCV-EX7119 | Caterpillar 6040 Excavator EX7119 | 27054 | 27054 | 6700
500126395 | CLB-MP-EXCV-EX7118-TRAVEL-TRKRH | Track Assembly Right Hand | 1775 | 30 | 470
500126394 | CLB-MP-EXCV-EX7118-TRAVEL-TRKLH | Track Assembly Left Hand | 1775 | 30 | 470
500126389 | CLB-MP-EXCV-EX7118-TRAVEL-SPRKR | Sprocket Right Hand | 1775 | 30 | 470
500126388 | CLB-MP-EXCV-EX7118-TRAVEL-SPRKL | Sprocket Left Hand | 1775 | 30 | 470
500126375 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH7 | Roller Load Pos 7 Right Hand | 1775 | 1775 | 470
500126374 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH6 | Roller Load Pos 6 Right Hand | 1775 | 1775 | 470
500126373 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH5 | Roller Load Pos 5 Right Hand | 1775 | 1775 | 470
500126372 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH4 | Roller Load Pos 4 Right Hand | 1775 | 1775 | 470
500126371 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH3 | Roller Load Pos 3 Right Hand | 1775 | 1775 | 470
500126370 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH2 | Roller Load Pos 2 Right Hand | 1775 | 1775 | 470
500126369 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-LORH1 | Roller Load Pos 1 Right Hand | 1775 | 1775 | 470
500126368 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-IDLRH | Idler Track Right Hand | 1775 | 30 | 470
500126367 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-CARRR | Roller Carrier Right Hand Rear | 1775 | 1775 | 470
500126366 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-CARRF | Roller Carrier Right Hand Front | 1775 | 1775 | 470
500126363 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 Left Hand | 1775 | 1775 | 470
500126362 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 Left Hand | 1775 | 1775 | 470
500126361 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 Left Hand | 1775 | 1775 | 470
500126360 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 Left Hand | 1775 | 1775 | 470
500126359 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 Left Hand | 1775 | 1775 | 470
500126358 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 Left Hand | 1775 | 1775 | 470
500126357 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 Left Hand | 1775 | 1775 | 470
500126356 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-IDLLH | Idler Track Left Hand | 1775 | 30 | 470
500126355 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-CARLR | Roller Carrier Left Hand Rear | 1775 | 1486 | 470
500126354 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-CARLF | Roller Carrier Left Hand Front | 1775 | 1486 | 470
500126385 | CLB-MP-EXCV-EX7118-TRAVEL | 6040 Excavator, EX7118 TRAVEL HOURS | 1775 | 1775 | 470
500146772 | CLB-MP-EXCV-EX7118-HYDSYS-HDACC | Hydraulic Ladder Accumulator | 25972 | 25972 | 6700
500146771 | CLB-MP-EXCV-EX7118-HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 25972 | 25972 | 6700
500146770 | CLB-MP-EXCV-EX7118-HYDSYS-HDACC | Track Tension Accumulator RH | 25972 | 25972 | 6700
500146769 | CLB-MP-EXCV-EX7118-HYDSYS-HDACC | Track Tension Accumulator LH | 25972 | 25972 | 6700
500139324 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 17550 | 5056 | 6700
500126393 | CLB-MP-EXCV-EX7118-TRAVEL-TRBKR-TBKRR | Brake Travel Right Hand Rear | 25972 | 25972 | 6700
500126392 | CLB-MP-EXCV-EX7118-TRAVEL-TRBKR-TBKRF | Brake Travel Right Hand Front | 25972 | 25972 | 6700
500126391 | CLB-MP-EXCV-EX7118-TRAVEL-TRBKL-TBKLR | Brake Travel Left Hand Rear | 25972 | 25972 | 6700
500126390 | CLB-MP-EXCV-EX7118-TRAVEL-TRBKL-TBKLF | Brake Travel Left Hand Front | 25972 | 25972 | 6700
500126387 | CLB-MP-EXCV-EX7118-TRAVEL-FDRRH | Final Drive Right Hand | 25972 | 25972 | 6700
500126386 | CLB-MP-EXCV-EX7118-TRAVEL-FDRLH | Final Drive Left Hand | 25972 | 25972 | 6700
500126384 | CLB-MP-EXCV-EX7118-SWGSYS-SWLUB | Swing System Lubrication | 25972 | 25972 | 6700
500126383 | CLB-MP-EXCV-EX7118-SWGSYS-SWBRK-SBKRR | Brake Swing Right Hand Rear | 25972 | 11914 | 6700
500126382 | CLB-MP-EXCV-EX7118-SWGSYS-SWBRK-SBKRF | Brake Swing Right Hand Front | 25972 | 9528 | 6700
500126381 | CLB-MP-EXCV-EX7118-SWGSYS-SWBRK-SBKLR | Brake Swing Left Hand Rear | 25972 | 25972 | 6700
500126380 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBRR | Gearbox Swing Right Hand Rear | 25972 | 5908 | 6700
500126379 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBRF | Gearbox Swing Right Hand Front | 25972 | 5908 | 6700
500126378 | CLB-MP-EXCV-EX7118-SWGSYS-SWBOX-SGBLR | Gearbox Swing Left Hand Rear | 25972 | 5908 | 6700
500126377 | CLB-MP-EXCV-EX7118-STRUCT-UNDER-SLEWB | Slew Bearing | 25972 | 25972 | 6700
500126376 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR-TENSR | Track Tensioner Right Hand | 25972 | 403 | 6700
500126365 | CLB-MP-EXCV-EX7118-STRUCT-TKFRR | 6040 RH Track Wear EX7118 | 25972 | 25972 | 42
500126364 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL-TENSR | Track Tensioner Left Hand | 25972 | 10895 | 6700
500126353 | CLB-MP-EXCV-EX7118-STRUCT-TKFRL | 6040 LH Track Wear EX7118 | 25972 | 25972 | 42
500126352 | CLB-MP-EXCV-EX7118-STRUCT-SUPER-ROLTK | Reserve Oil Tank | 25972 | 25972 | 6700
500126351 | CLB-MP-EXCV-EX7118-STRUCT-STICK | Stick Assembly | 25972 | 25972 | 6700
500126350 | CLB-MP-EXCV-EX7118-STRUCT-HLINK-LINKR | Stick To Bucket Linkages Right | 25972 | 25972 | 6700
500126349 | CLB-MP-EXCV-EX7118-STRUCT-HLINK-LINKL | Stick To Bucket Linkages Left | 25972 | 25972 | 6700
500126348 | CLB-MP-EXCV-EX7118-STRUCT-HLINK | H Link Assembly | 25972 | 22757 | 6700
500126347 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-SEATS | Operators Seat | 25972 | 8861 | 6700
500126346 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-SBELT | Seat Belt | 25972 | 25972 | 6700
500126345 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 25972 | 25972 | 6700
500126344 | CLB-MP-EXCV-EX7118-STRUCT-CABIN-AIRCR | Air Conditioning System | 25972 | 6562 | 6700
500126343 | CLB-MP-EXCV-EX7118-STRUCT-BUCKT | Bucket | 25972 | 6562 | 6700
500126342 | CLB-MP-EXCV-EX7118-STRUCT-BOOMS | Boom Static Lines | 25972 | 25972 | 6700
500126341 | CLB-MP-EXCV-EX7118-STRUCT-BOOMS | Boom Assembly | 25972 | 25972 | 6700
500126340 | CLB-MP-EXCV-EX7118-RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 25972 | 25972 | 6700
500126339 | CLB-MP-EXCV-EX7118-RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 25972 | 25972 | 6700
500126338 | CLB-MP-EXCV-EX7118-RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 25972 | 25972 | 6700
500126337 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-TBORH | RH Engine Turbocharger Right Hand Side | 25972 | 5908 | 6700
500126336 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-TBOLH | RH Engine Turbocharger Left Hand Side | 25972 | 5908 | 6700
500126335 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-EXHST | RH Engine Exhaust System | 25972 | 25972 | 6700
500126334 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 25972 | 25972 | 6700
500126333 | CLB-MP-EXCV-EX7118-RHENGN-INTEX-AFTER | RH Engine Aftercooler | 25972 | 7182 | 6700
500126332 | CLB-MP-EXCV-EX7118-RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 25972 | 5908 | 6700
500126331 | CLB-MP-EXCV-EX7118-RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 25972 | 5908 | 6700
500126330 | CLB-MP-EXCV-EX7118-RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 25972 | 25972 | 6700
500126329 | CLB-MP-EXCV-EX7118-RHENGN-COUPL | RH Engine Coupling | 25972 | 25972 | 6700
500126328 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-WTRPP | RH Engine Water Pump | 25972 | 5908 | 6700
500126327 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-THERM | RH Engine Thermostats & Regulators | 25972 | 5908 | 6700
500126326 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 25972 | 25972 | 6700
500126325 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-RADTR | RH Engine Radiator | 25972 | 7182 | 6700
500126324 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 25972 | 25972 | 6700
500126323 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 25972 | 25972 | 6700
500126322 | CLB-MP-EXCV-EX7118-RHENGN-COSYS-BELTS | RH Engine V Belts | 25972 | 25972 | 6700
500126320 | CLB-MP-EXCV-EX7118-RHENGN | RH Engine Assembly C32 | 25972 | 14409 | 6700
500126319 | CLB-MP-EXCV-EX7118-MANGMT-UMPMP | Pump Management System | 25972 | 25972 | 6700
500126318 | CLB-MP-EXCV-EX7118-MANGMT-UMMMC | Mine Monitoring and Control | 25972 | 25972 | 6700
500126317 | CLB-MP-EXCV-EX7118-MANGMT-UMENG | Engine Management System | 25972 | 25972 | 6700
500126316 | CLB-MP-EXCV-EX7118-MANGMT-UMBRD | Board Control System | 25972 | 25972 | 6700
500126315 | CLB-MP-EXCV-EX7118-LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 25972 | 25972 | 6700
500126314 | CLB-MP-EXCV-EX7118-LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 25972 | 25972 | 6700
500126313 | CLB-MP-EXCV-EX7118-LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 25972 | 25972 | 6700
500126312 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-TBORH | LH Engine Turbocharger Right Hand Side | 25972 | 7182 | 6700
500126311 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-TBOLH | LH Engine Turbocharger Left Hand Side | 25972 | 7182 | 6700
500126310 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-EXHST | LH Engine Exhaust System | 25972 | 25972 | 6700
500126309 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 25972 | 25972 | 6700
500126308 | CLB-MP-EXCV-EX7118-LHENGN-INTEX-AFTER | LH Engine Aftercooler | 25972 | 12463 | 6700
500126307 | CLB-MP-EXCV-EX7118-LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 25972 | 7182 | 6700
500126306 | CLB-MP-EXCV-EX7118-LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 25972 | 7182 | 6700
500126305 | CLB-MP-EXCV-EX7118-LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 25972 | 25972 | 6700
500126304 | CLB-MP-EXCV-EX7118-LHENGN-COUPL | LH Engine Coupling | 25972 | 25972 | 6700
500126303 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-WTRPP | LH Engine Water Pump | 25972 | 7182 | 6700
500126302 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-THERM | LH Engine Thermostats & Regulators | 25972 | 7182 | 6700
500126301 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 25972 | 11914 | 6700
500126300 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-RADTR | LH Engine Radiator | 25972 | 11914 | 6700
500126299 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 25972 | 25972 | 6700
500126298 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 25972 | 25972 | 6700
500126297 | CLB-MP-EXCV-EX7118-LHENGN-COSYS-BELTS | LH Engine V Belts | 25972 | 25972 | 6700
500126295 | CLB-MP-EXCV-EX7118-LHENGN | LH Engine Assembly C32 | 25972 | 7182 | 6700
500126294 | CLB-MP-EXCV-EX7118-HYDSYS-ROTRY | Rotary Joint | 25972 | 25972 | 6700
500126293 | CLB-MP-EXCV-EX7118-HYDSYS-PPDRR | Pump Drive Gearbox Right Hand | 25972 | 6562 | 6700
500126292 | CLB-MP-EXCV-EX7118-HYDSYS-PPDRL | Pump Drive Gearbox Left Hand | 25972 | 6562 | 6700
500126291 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPR | Pump Servo Right Hand | 25972 | 12762 | 6700
500126290 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SVPPL | Pump Servo Left Hand | 25972 | 3545 | 6700
500126289 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing Right Hand | 25972 | 13898 | 6700
500126288 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing Left Hand | 25972 | 13898 | 6700
500126287 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 25972 | 13898 | 6700
500126286 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 25972 | 13898 | 6700
500126285 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 25972 | 11914 | 6700
500126284 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 25972 | 13291 | 6700
500126283 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 25972 | 13898 | 6700
500126282 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 25972 | 13898 | 6700
500126281 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling Right Hand | 25972 | 8726 | 6700
500126280 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling Left Hand | 25972 | 8070 | 6700
500126279 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 25972 | 25972 | 6700
500126278 | CLB-MP-EXCV-EX7118-HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 25972 | 15362 | 6700
500126277 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-TCVVR | Travel Control Valve Block Right Hand | 25972 | 25972 | 6700
500126276 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-TCVVL | Travel Control Valve Block Left Hand | 25972 | 25972 | 6700
500126275 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-MCVVR | Main Control Valve Block Right Hand | 25972 | 25972 | 6700
500126274 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-MCVVL | Main Control Valve Block Left Hand | 25972 | 25972 | 6700
500126273 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-FTVRH | Valve Float Right Hand | 25972 | 25972 | 6700
500126272 | CLB-MP-EXCV-EX7118-HYDSYS-HDVLV-FTVLH | Valve Float Left Hand | 25972 | 25972 | 6700
500126271 | CLB-MP-EXCV-EX7118-HYDSYS-HDTNK | Tank Hydraulic | 25972 | 25972 | 6700
500126270 | CLB-MP-EXCV-EX7118-HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 25972 | 403 | 6700
500126269 | CLB-MP-EXCV-EX7118-HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 25972 | 403 | 6700
500126268 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 25972 | 13898 | 6700
500126267 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 25972 | 13898 | 6700
500126266 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 25972 | 13898 | 6700
500126265 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 25972 | 13317 | 6700
500126264 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRR | Motor Swing Right Hand Rear | 25972 | 11422 | 6700
500126263 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMRF | Motor Swing Right Hand Front | 25972 | 11422 | 6700
500126262 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-SWMLR | Motor Swing Left Hand Rear | 25972 | 11422 | 6700
500126261 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 25972 | 8726 | 6700
500126260 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator Left Hand | 25972 | 18775 | 6700
500126259 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 25972 | 8726 | 6700
500126258 | CLB-MP-EXCV-EX7118-HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 25972 | 8070 | 6700
500126257 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 25972 | 4282 | 6700
500126256 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 25972 | 12789 | 6700
500126255 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 25972 | 12789 | 6700
500126254 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SWCRT | Swing Circuit Hoses | 25972 | 25972 | 6700
500126253 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SSTBR | 2nd Speed Travel Brake Release Hoses | 25972 | 12789 | 6700
500126252 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 25948 | 13851 | 6700
500126251 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 25972 | 7182 | 6700
500126250 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 25972 | 12762 | 6700
500126249 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 25972 | 12789 | 6700
500126248 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 25972 | 12789 | 6700
500126247 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 25972 | 8070 | 6700
500126246 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 25972 | 966 | 6700
500126245 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 25972 | 8726 | 6700
500126244 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 25948 | 13851 | 6700
500126243 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 25972 | 15339 | 6700
500126242 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 25972 | 4282 | 6700
500126241 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 25925 | 14626 | 6700
500126240 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 25972 | 4282 | 6700
500126239 | CLB-MP-EXCV-EX7118-HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 25972 | 11914 | 6700
500126238 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 25972 | 12481 | 6700
500126237 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 25972 | 7182 | 6700
500126236 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 25972 | 9228 | 6700
500126235 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 25972 | 4282 | 6700
500126234 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 25972 | 8726 | 6700
500126233 | CLB-MP-EXCV-EX7118-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 25972 | 3545 | 6700
500126232 | CLB-MP-EXCV-EX7118-HYDSYS-HDACC-HACCR | Accumulator Hydraulic Right Hand | 25972 | 25972 | 6700
500126231 | CLB-MP-EXCV-EX7118-HYDSYS-HDACC-HACCL | Accumulator Hydraulic Left Hand | 25972 | 25972 | 6700
500126230 | CLB-MP-EXCV-EX7118-HYDSYS | Hydraulic System | 25972 | 966 | 6700
500126229 | CLB-MP-EXCV-EX7118-HYDSYS | Hydraulic Oil | 25972 | 966 | 6700
500126228 | CLB-MP-EXCV-EX7118-GRSYST-GRTNK | Auto Lube Resevoir | 25972 | 25972 | 6700
500126227 | CLB-MP-EXCV-EX7118-GRSYST-GRINJ | Auto Lube Injectors | 25972 | 25972 | 6700
500126225 | CLB-MP-EXCV-EX7118-GRSYST-ALBPP | Auto Lube Pump | 25972 | 8726 | 6700
500126224 | CLB-MP-EXCV-EX7118-FRSUPP | Fire Suppression System | 25972 | 25972 | 6700
500126223 | CLB-MP-EXCV-EX7118-ELCTLV-START-STMRR | Starter Motor Right Hand Engine Upper | 25972 | 5908 | 6700
500126222 | CLB-MP-EXCV-EX7118-ELCTLV-START-STMRL | Starter Motor Right Hand Engine Lower | 25972 | 5908 | 6700
500126221 | CLB-MP-EXCV-EX7118-ELCTLV-START-STMLR | Starter Motor Left Hand Engine Upper | 25972 | 7182 | 6700
500126210 | CLB-MP-EXCV-EX7118-ELCTLV-START-STMLL | Starter Motor Left Hand Engine Lower | 25972 | 7182 | 6700
500126209 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-BATTY | Batteries | 25972 | 5056 | 6700
500126208 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-ALTRH | Alternator 24V Right Hand Engine | 25972 | 5908 | 6700
500126207 | CLB-MP-EXCV-EX7118-ELCTLV-CHARG-ALTLH | Alternator 24V Left Hand Engine | 25972 | 7182 | 6700
500126206 | CLB-MP-EXCV-EX7118 | EX7118 Lubrication & Mechanical Services | 25972 | 25972 | 6700
500126205 | CLB-MP-EXCV-EX7118 | Caterpillar 6040 Excavator EX7118 | 25972 | 25972 | 6700
500114719 | CLB-MP-EXCV-EX7112-TRAVEL-TRKRH | Track Assembly Right Hand | 2622 | 1035 | 470
500114718 | CLB-MP-EXCV-EX7112-TRAVEL-TRKLH | Track Assembly Left Hand | 2622 | 1035 | 470
500114713 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKR | Sprocket Right Hand | 2622 | 2622 | 470
500114712 | CLB-MP-EXCV-EX7112-TRAVEL-SPRKL | Sprocket Left Hand | 2622 | 26 | 470
500114699 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH7 | Roller Load Pos 7 Right Hand | 2622 | 2622 | 470
500114698 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH6 | Roller Load Pos 6 Right Hand | 2622 | 2622 | 470
500114697 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH5 | Roller Load Pos 5 Right Hand | 2622 | 2622 | 470
500114696 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH4 | Roller Load Pos 4 Right Hand | 2622 | 2622 | 470
500114695 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH3 | Roller Load Pos 3 Right Hand | 2622 | 2622 | 470
500114694 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH2 | Roller Load Pos 2 Right Hand | 2622 | 2622 | 470
500114693 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-LORH1 | Roller Load Pos 1 Right Hand | 2622 | 2622 | 470
500114692 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-IDLRH | Idler Track Right Hand | 2622 | 1697 | 470
500114691 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-CARRR | Roller Carrier Right Hand Rear | 2622 | 2622 | 470
500114690 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-CARRF | Roller Carrier Right Hand Front | 2622 | 2622 | 470
500114687 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 Left Hand | 2622 | 2622 | 470
500114686 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 Left Hand | 2622 | 2622 | 470
500114685 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 Left Hand | 2622 | 2622 | 470
500114684 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 Left Hand | 2622 | 2622 | 470
500114683 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 Left Hand | 2622 | 2622 | 470
500114682 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 Left Hand | 2622 | 2622 | 470
500114681 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 Left Hand | 2622 | 2622 | 470
500114680 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-IDLLH | Idler Track Left Hand | 2622 | 1533 | 470
500114679 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-CARLR | Roller Carrier Left Hand Rear | 2622 | 2622 | 470
500114678 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-CARLF | Roller Carrier Left Hand Front | 2622 | 2622 | 470
500114709 | CLB-MP-EXCV-EX7112-TRAVEL | 6040 Excavator, EX7112 TRAVEL HOURS | 2622 | 2622 | 470
500146768 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC | Hydraulic Ladder Accumulator | 31524 | 31524 | 6700
500146767 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 31524 | 31524 | 6700
500146766 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC | Track Tension Accumulator RH | 31524 | 7104 | 6700
500146765 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC | Track Tension Accumulator LH | 31524 | 7104 | 6700
500139321 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 21488 | 7104 | 6700
500114725 | CLB-MP-EXCV-EX7112-GRSYST-ALCON | Auto Lube Controller | 31524 | 4098 | 6700
500114724 | CLB-MP-EXCV-EX7112-STRUCT-CABIN | Operators Cabin | 31524 | 31524 | 6700
500114717 | CLB-MP-EXCV-EX7112-TRAVEL-TRBKR-TBKRR | Brake Travel Right Hand Rear | 31524 | 31524 | 6700
500114716 | CLB-MP-EXCV-EX7112-TRAVEL-TRBKR-TBKRF | Brake Travel Right Hand Front | 31524 | 31524 | 6700
500114715 | CLB-MP-EXCV-EX7112-TRAVEL-TRBKL-TBKLR | Brake Travel Left Hand Rear | 31524 | 31524 | 6700
500114714 | CLB-MP-EXCV-EX7112-TRAVEL-TRBKL-TBKLF | Brake Travel Left Hand Front | 31524 | 31524 | 6700
500114711 | CLB-MP-EXCV-EX7112-TRAVEL-FDRRH | Final Drive Right Hand | 31524 | 20738 | 6700
500114710 | CLB-MP-EXCV-EX7112-TRAVEL-FDRLH | Final Drive Left Hand | 31524 | 304 | 6700
500114708 | CLB-MP-EXCV-EX7112-SWGSYS-SWLUB | Swing System Lubrication | 31524 | 31524 | 6700
500114707 | CLB-MP-EXCV-EX7112-SWGSYS-SWBRK-SBKRR | Brake Swing Right Hand Rear | 31524 | 31524 | 6700
500114706 | CLB-MP-EXCV-EX7112-SWGSYS-SWBRK-SBKRF | Brake Swing Right Hand Front | 31524 | 31524 | 6700
500114705 | CLB-MP-EXCV-EX7112-SWGSYS-SWBRK-SBKLR | Brake Swing Left Hand Rear | 31524 | 31524 | 6700
500114704 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBRR | Gearbox Swing Right Hand Rear | 31524 | 11232 | 6700
500114703 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBRF | Gearbox Swing Right Hand Front | 31524 | 11232 | 6700
500114702 | CLB-MP-EXCV-EX7112-SWGSYS-SWBOX-SGBLR | Gearbox Swing Left Hand Rear | 31524 | 11232 | 6700
500114701 | CLB-MP-EXCV-EX7112-STRUCT-UNDER-SLEWB | Slew Bearing | 31524 | 31524 | 6700
500114700 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR-TENSR | Track Tensioner Right Hand | 31524 | 13589 | 6700
500114689 | CLB-MP-EXCV-EX7112-STRUCT-TKFRR | 6040 RH Track Wear EX7112 | 31524 | 31524 | 42
500114688 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL-TENSR | Track Tensioner Left Hand | 31524 | 415 | 6700
500114677 | CLB-MP-EXCV-EX7112-STRUCT-TKFRL | 6040 LH Track Wear EX7112 | 31524 | 31524 | 42
500114676 | CLB-MP-EXCV-EX7112-STRUCT-SUPER-ROLTK | Reserve Oil Tank | 31524 | 31524 | 6700
500114675 | CLB-MP-EXCV-EX7112-STRUCT-STICK | Stick Assembly | 31524 | 14061 | 6700
500114674 | CLB-MP-EXCV-EX7112-STRUCT-HLINK-LINKR | Stick To Bucket Linkages - Right | 31524 | 31524 | 6700
500114673 | CLB-MP-EXCV-EX7112-STRUCT-HLINK-LINKL | Stick To Bucket Linkages - Left | 31524 | 31524 | 6700
500114672 | CLB-MP-EXCV-EX7112-STRUCT-HLINK | H Link Assembly | 31524 | 3553 | 6700
500114671 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-SEATS | Operators Seat | 31524 | 3374 | 6700
500114670 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-SBELT | Seat Belt | 31524 | 31524 | 6700
500114669 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 31524 | 31524 | 6700
500114668 | CLB-MP-EXCV-EX7112-STRUCT-CABIN-AIRCR | Air Conditioning System | 31524 | 31524 | 6700
500114667 | CLB-MP-EXCV-EX7112-STRUCT-BUCKT | Bucket | 31524 | 4098 | 6700
500114666 | CLB-MP-EXCV-EX7112-STRUCT-BOOMS | Boom Static Lines | 31524 | 31524 | 6700
500114665 | CLB-MP-EXCV-EX7112-STRUCT-BOOMS | Boom Assembly | 31524 | 31524 | 6700
500114664 | CLB-MP-EXCV-EX7112-RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 31524 | 31524 | 6700
500114663 | CLB-MP-EXCV-EX7112-RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 31524 | 14061 | 6700
500114662 | CLB-MP-EXCV-EX7112-RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 31524 | 14061 | 6700
500114661 | CLB-MP-EXCV-EX7112-RHENGN-INTEX-TBORH | RH Engine Turbocharger Right Hand Side | 31524 | 4949 | 6700
500114660 | CLB-MP-EXCV-EX7112-RHENGN-INTEX-TBOLH | RH Engine Turbocharger Left Hand Side | 31524 | 4949 | 6700
500114659 | CLB-MP-EXCV-EX7112-RHENGN-INTEX-EXHST | RH Engine Exhaust System | 31524 | 31524 | 6700
500114658 | CLB-MP-EXCV-EX7112-RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 31524 | 31524 | 6700
500114657 | CLB-MP-EXCV-EX7112-RHENGN-INTEX-AFTER | RH Engine Aftercooler | 31524 | 31524 | 6700
500114656 | CLB-MP-EXCV-EX7112-RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 31524 | 4949 | 6700
500114655 | CLB-MP-EXCV-EX7112-RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 31524 | 4949 | 6700
500114654 | CLB-MP-EXCV-EX7112-RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 31524 | 31524 | 6700
500114653 | CLB-MP-EXCV-EX7112-RHENGN-COUPL | RH Engine Coupling | 31524 | 14061 | 6700
500114652 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-WTRPP | RH Engine Water Pump | 31524 | 4949 | 6700
500114651 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 31524 | 4949 | 6700
500114650 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 31524 | 31524 | 6700
500114649 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-RADTR | RH Engine Radiator | 31524 | 14061 | 6700
500114648 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 31524 | 31524 | 6700
500114647 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 31524 | 31524 | 6700
500114646 | CLB-MP-EXCV-EX7112-RHENGN-COSYS-BELTS | RH Engine V Belts | 31524 | 14061 | 6700
500114644 | CLB-MP-EXCV-EX7112-RHENGN | RH Engine Assembly C32 | 31524 | 14061 | 6700
500114643 | CLB-MP-EXCV-EX7112-MANGMT-UMPMP | Pump Management System | 31524 | 31524 | 6700
500114642 | CLB-MP-EXCV-EX7112-MANGMT-UMMMC | Mine Monitoring and Control | 31524 | 31524 | 6700
500114641 | CLB-MP-EXCV-EX7112-MANGMT-UMENG | Engine Management System | 31524 | 31524 | 6700
500114640 | CLB-MP-EXCV-EX7112-MANGMT-UMBRD | Board Control System | 31524 | 31524 | 6700
500114639 | CLB-MP-EXCV-EX7112-LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 31524 | 31524 | 6700
500114638 | CLB-MP-EXCV-EX7112-LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 31524 | 13589 | 6700
500114637 | CLB-MP-EXCV-EX7112-LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 31524 | 13589 | 6700
500114636 | CLB-MP-EXCV-EX7112-LHENGN-INTEX-TBORH | LH Engine Turbocharger Right Hand Side | 31524 | 4949 | 6700
500114635 | CLB-MP-EXCV-EX7112-LHENGN-INTEX-TBOLH | LH Engine Turbocharger Left Hand Side | 31524 | 4949 | 6700
500114634 | CLB-MP-EXCV-EX7112-LHENGN-INTEX-EXHST | LH Engine Exhaust System | 31524 | 31524 | 6700
500114633 | CLB-MP-EXCV-EX7112-LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 31524 | 31524 | 6700
500114632 | CLB-MP-EXCV-EX7112-LHENGN-INTEX-AFTER | LH Engine Aftercooler | 31524 | 31524 | 6700
500114631 | CLB-MP-EXCV-EX7112-LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 31524 | 4949 | 6700
500114630 | CLB-MP-EXCV-EX7112-LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 31524 | 4949 | 6700
500114629 | CLB-MP-EXCV-EX7112-LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 31524 | 31524 | 6700
500114628 | CLB-MP-EXCV-EX7112-LHENGN-COUPL | LH Engine Coupling | 31524 | 13589 | 6700
500114627 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-WTRPP | LH Engine Water Pump | 31524 | 4949 | 6700
500114626 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 31524 | 4949 | 6700
500114625 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 31524 | 31524 | 6700
500114624 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-RADTR | LH Engine Radiator | 31524 | 12981 | 6700
500114623 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 31524 | 31524 | 6700
500114622 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 31524 | 31524 | 6700
500114621 | CLB-MP-EXCV-EX7112-LHENGN-COSYS-BELTS | LH Engine V Belts | 31524 | 13589 | 6700
500114619 | CLB-MP-EXCV-EX7112-LHENGN | LH Engine Assembly C32 | 31524 | 13589 | 6700
500114618 | CLB-MP-EXCV-EX7112-HYDSYS-ROTRY | Rotary Joint | 31524 | 5544 | 6700
500114617 | CLB-MP-EXCV-EX7112-HYDSYS-PPDRR | Pump Drive Gearbox Right Hand | 31524 | 14061 | 6700
500114616 | CLB-MP-EXCV-EX7112-HYDSYS-PPDRL | Pump Drive Gearbox Left Hand | 31524 | 13589 | 6700
500114615 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPR | Pump Servo Right Hand | 31524 | 7104 | 6700
500114614 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SVPPL | Pump Servo Left Hand | 31524 | 7104 | 6700
500114613 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing Right Hand | 31524 | 7104 | 6700
500114612 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing Left Hand | 31524 | 7104 | 6700
500114611 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 31524 | 6351 | 6700
500114610 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 31524 | 5544 | 6700
500114609 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 31524 | 6351 | 6700
500114608 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 31524 | 3374 | 6700
500114607 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 31524 | 7104 | 6700
500114606 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 31524 | 7104 | 6700
500114605 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling Right Hand | 31524 | 13589 | 6700
500114604 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling Left Hand | 31524 | 13589 | 6700
500114603 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 31524 | 31524 | 6700
500114602 | CLB-MP-EXCV-EX7112-HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 31524 | 31524 | 6700
500114601 | CLB-MP-EXCV-EX7112-HYDSYS-HDVLV-TCVVR | Travel Control Valve Block Right Hand | 31524 | 31524 | 6700
500114600 | CLB-MP-EXCV-EX7112-HYDSYS-HDVLV-TCVVL | Travel Control Valve Block Left Hand | 31524 | 31524 | 6700
500114599 | CLB-MP-EXCV-EX7112-HYDSYS-HDVLV-MCVVR | Main Control Valve Block Right Hand | 31524 | 31524 | 6700
500114598 | CLB-MP-EXCV-EX7112-HYDSYS-HDVLV-MCVVL | Main Control Valve Block Left Hand | 31524 | 31524 | 6700
500114597 | CLB-MP-EXCV-EX7112-HYDSYS-HDVLV-FTVRH | Valve Float Right Hand | 31524 | 31524 | 6700
500114596 | CLB-MP-EXCV-EX7112-HYDSYS-HDVLV-FTVLH | Valve Float Left Hand | 31524 | 31524 | 6700
500114595 | CLB-MP-EXCV-EX7112-HYDSYS-HDTNK | Tank Hydraulic | 31524 | 31524 | 6700
500114594 | CLB-MP-EXCV-EX7112-HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 31524 | 7104 | 6700
500114593 | CLB-MP-EXCV-EX7112-HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 31524 | 7104 | 6700
500114592 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 31524 | 20738 | 6700
500114591 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 31524 | 6351 | 6700
500114590 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 31524 | 3374 | 6700
500114589 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 31524 | 9874 | 6700
500114588 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMRR | Motor Swing Right Hand Rear | 31524 | 4949 | 6700
500114587 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMRF | Motor Swing Right Hand Front | 31524 | 415 | 6700
500114586 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-SWMLR | Motor Swing Left Hand Rear | 31524 | 16212 | 6700
500114585 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 31524 | 12394 | 6700
500114584 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator Left Hand | 31524 | 12394 | 6700
500114583 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 31524 | 9101 | 6700
500114582 | CLB-MP-EXCV-EX7112-HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 31524 | 12394 | 6700
500114581 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 31524 | 2640 | 6700
500114580 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 31524 | 4098 | 6700
500114579 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 31524 | 7104 | 6700
500114578 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 31524 | 4098 | 6700
500114577 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SSTBR | 2nd Speed Travel - Brake Release Hoses | 31524 | 3374 | 6700
500114576 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 31524 | 7104 | 6700
500114575 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 31524 | 2019 | 6700
500114574 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 31524 | 19618 | 6700
500114573 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 31524 | 3374 | 6700
500114572 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 31524 | 3374 | 6700
500114571 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 31524 | 13589 | 6700
500114570 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 31524 | 13589 | 6700
500114569 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 31524 | 2019 | 6700
500114568 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 31524 | 4949 | 6700
500114567 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 31524 | 11872 | 6700
500114566 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 31524 | 415 | 6700
500114565 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 31524 | 11872 | 6700
500114564 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 31524 | 415 | 6700
500114563 | CLB-MP-EXCV-EX7112-HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 31524 | 2019 | 6700
500114562 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 31524 | 3374 | 6700
500114561 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 31524 | 3374 | 6700
500114560 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 31524 | 3374 | 6700
500114559 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 31524 | 10817 | 6700
500114558 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 31524 | 8103 | 6700
500114557 | CLB-MP-EXCV-EX7112-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 31524 | 14047 | 6700
500114556 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC-HACCR | Accumulator Hydraulic Right Hand | 31524 | 31524 | 6700
500114555 | CLB-MP-EXCV-EX7112-HYDSYS-HDACC-HACCL | Accumulator Hydraulic Left Hand | 31524 | 31524 | 6700
500114554 | CLB-MP-EXCV-EX7112-HYDSYS | Hydraulic System | 31524 | 4098 | 6700
500114553 | CLB-MP-EXCV-EX7112-HYDSYS | Hydraulic Oil | 31524 | 4098 | 6700
500114552 | CLB-MP-EXCV-EX7112-GRSYST-GRTNK | Auto Lube Resevoir | 31524 | 31524 | 6700
500114551 | CLB-MP-EXCV-EX7112-GRSYST-GRINJ | Auto Lube Injectors | 31524 | 31524 | 6700
500114549 | CLB-MP-EXCV-EX7112-GRSYST-ALBPP | Auto Lube Pump | 31524 | 6351 | 6700
500114548 | CLB-MP-EXCV-EX7112-FRSUPP | Fire Suppression System | 31524 | 31524 | 6700
500114547 | CLB-MP-EXCV-EX7112-ELCTLV-START-STMRR | Starter Motor Right Hand Engine Upper | 31524 | 4949 | 6700
500114546 | CLB-MP-EXCV-EX7112-ELCTLV-START-STMRL | Starter Motor Right Hand Engine Lower | 31524 | 4949 | 6700
500114545 | CLB-MP-EXCV-EX7112-ELCTLV-START-STMLR | Starter Motor Left Hand Engine Upper | 31524 | 4949 | 6700
500114544 | CLB-MP-EXCV-EX7112-ELCTLV-START-STMLL | Starter Motor Left Hand Engine Lower | 31524 | 4949 | 6700
500114543 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-BATTY | EX7112 Batteries | 31524 | 3374 | 6700
500114542 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-ALTRH | Alternator 24V Right Hand Engine | 31524 | 4949 | 6700
500114541 | CLB-MP-EXCV-EX7112-ELCTLV-CHARG-ALTLH | Alternator 24V Left Hand Engine | 31524 | 4949 | 6700
500114540 | CLB-MP-EXCV-EX7112 | EX7112 Lubrication & Mechanical Services | 31524 | 31524 | 6700
500114539 | CLB-MP-EXCV-EX7112 | Caterpillar 6040 Excavator EX7112 | 31524 | 31524 | 6700
500114538 | CLB-MP-EXCV-EX7109-TRAVEL-TRKRH | Track Assembly Right Hand | 1633 | 1633 | 470
500114537 | CLB-MP-EXCV-EX7109-TRAVEL-TRKLH | Track Assembly Left Hand | 1633 | 1633 | 470
500114532 | CLB-MP-EXCV-EX7109-TRAVEL-SPRKR | Sprocket Right Hand | 1633 | 0 | 470
500114531 | CLB-MP-EXCV-EX7109-TRAVEL-SPRKL | Sprocket Left Hand | 1633 | 0 | 470
500114518 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH7 | Roller Load Pos 7 Right Hand | 1633 | 1633 | 470
500114517 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH6 | Roller Load Pos 6 Right Hand | 1633 | 1633 | 470
500114516 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH5 | Roller Load Pos 5 Right Hand | 1633 | 1633 | 470
500114515 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH4 | Roller Load Pos 4 Right Hand | 1633 | 1633 | 470
500114514 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH3 | Roller Load Pos 3 Right Hand | 1633 | 1633 | 470
500114513 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH2 | Roller Load Pos 2 Right Hand | 1633 | 1633 | 470
500114512 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-LORH1 | Roller Load Pos 1 Right Hand | 1633 | 1068 | 470
500114511 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-IDLRH | Idler Track Right Hand | 1633 | 361 | 470
500114510 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-CARRR | Roller Carrier Right Hand Rear | 1633 | 1068 | 470
500114509 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-CARRF | Roller Carrier Right Hand Front | 1633 | 1174 | 470
500114506 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 Left Hand | 1633 | 1174 | 470
500114505 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 Left Hand | 1633 | 1633 | 470
500114504 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 Left Hand | 1633 | 1633 | 470
500114503 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 Left Hand | 1633 | 1633 | 470
500114502 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 Left Hand | 1633 | 1633 | 470
500114501 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 Left Hand | 1633 | 1633 | 470
500114500 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 Left Hand | 1633 | 1633 | 470
500114499 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-IDLLH | Idler Track Left Hand | 1633 | 816 | 470
500114498 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-CARLR | Roller Carrier Left Hand Rear | 1633 | 0 | 470
500114497 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-CARLF | Roller Carrier Left Hand Front | 1633 | 994 | 470
500114528 | CLB-MP-EXCV-EX7109-TRAVEL | 6040 Excavator, EX7109 TRAVEL HOURS | 1633 | 1633 | 470
500146760 | CLB-MP-EXCV-EX7109-HYDSYS-HDACC | Hydraulic Ladder Accumulator | 25093 | 25093 | 6700
500146759 | CLB-MP-EXCV-EX7109-HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 25093 | 25093 | 6700
500146758 | CLB-MP-EXCV-EX7109-HYDSYS-HDACC | Track Tension Accumulator RH | 25093 | 25093 | 6700
500146757 | CLB-MP-EXCV-EX7109-HYDSYS-HDACC | Track Tension Accumulator LH | 25093 | 25093 | 6700
500114723 | CLB-MP-EXCV-EX7109-GRSYST-ALCON | Auto Lube Controller | 25093 | 12176 | 6700
500114722 | CLB-MP-EXCV-EX7109-STRUCT-CABIN | Operators Cabin | 25093 | 25093 | 6700
500114536 | CLB-MP-EXCV-EX7109-TRAVEL-TRBKR-TBKRR | Brake Travel Right Hand Rear | 25093 | 25093 | 6700
500114535 | CLB-MP-EXCV-EX7109-TRAVEL-TRBKR-TBKRF | Brake Travel Right Hand Front | 25093 | 25093 | 6700
500114534 | CLB-MP-EXCV-EX7109-TRAVEL-TRBKL-TBKLR | Brake Travel Left Hand Rear | 25093 | 25093 | 6700
500114533 | CLB-MP-EXCV-EX7109-TRAVEL-TRBKL-TBKLF | Brake Travel Left Hand Front | 25093 | 25093 | 6700
500114530 | CLB-MP-EXCV-EX7109-TRAVEL-FDRRH | Final Drive Right Hand | 25093 | 14026 | 6700
500114529 | CLB-MP-EXCV-EX7109-TRAVEL-FDRLH | Final Drive Left Hand | 25093 | 14026 | 6700
500114527 | CLB-MP-EXCV-EX7109-SWINGS-SWLUB | Swing System Lubrication | 25093 | 25093 | 6700
500114526 | CLB-MP-EXCV-EX7109-SWINGS-SWBRK-SBKRR | Brake Swing Right Hand Rear | 25093 | 25093 | 6700
500114525 | CLB-MP-EXCV-EX7109-SWINGS-SWBRK-SBKRF | Brake Swing Right Hand Front | 25093 | 25093 | 6700
500114524 | CLB-MP-EXCV-EX7109-SWINGS-SWBRK-SBKLR | Brake Swing Left Hand Rear | 25093 | 25093 | 6700
500114523 | CLB-MP-EXCV-EX7109-SWINGS-SWBOX-SGBRR | Gearbox Swing Right Hand Rear | 25093 | 6253 | 6700
500114522 | CLB-MP-EXCV-EX7109-SWINGS-SWBOX-SGBRF | Gearbox Swing Right Hand Front | 25093 | 6253 | 6700
500114521 | CLB-MP-EXCV-EX7109-SWINGS-SWBOX-SGBLR | Gearbox Swing Left Hand Rear | 25093 | 6253 | 6700
500114520 | CLB-MP-EXCV-EX7109-STRUCT-UNDER-SLEWB | Slew Bearing | 25093 | 25093 | 6700
500114519 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR-TENSR | Track Tensioner Right Hand | 25093 | 2195 | 6700
500114508 | CLB-MP-EXCV-EX7109-STRUCT-TKFRR | 6040 RH Track Wear EX7109 | 25093 | 25093 | 42
500114507 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL-TENSR | Track Tensioner Left Hand | 25093 | 5298 | 6700
500114496 | CLB-MP-EXCV-EX7109-STRUCT-TKFRL | 6040 LH Track Wear EX7109 | 25093 | 25093 | 42
500114495 | CLB-MP-EXCV-EX7109-STRUCT-SUPER-ROLTK | Reserve Oil Tank | 25093 | 25093 | 6700
500114494 | CLB-MP-EXCV-EX7109-STRUCT-STICK | Stick Assembly | 25093 | 25093 | 6700
500114493 | CLB-MP-EXCV-EX7109-STRUCT-HLINK-LINKR | Stick To Bucket Linkages - Right | 25093 | 25093 | 6700
500114492 | CLB-MP-EXCV-EX7109-STRUCT-HLINK-LINKL | Stick To Bucket Linkages - Left | 25093 | 25093 | 6700
500114491 | CLB-MP-EXCV-EX7109-STRUCT-HLINK | H Link Assembly | 25093 | 25093 | 6700
500114490 | CLB-MP-EXCV-EX7109-STRUCT-CABIN-SEATS | Operators Seat | 25093 | 0 | 6700
500114489 | CLB-MP-EXCV-EX7109-STRUCT-CABIN-SBELT | Seat Belt | 25093 | 25093 | 6700
500114488 | CLB-MP-EXCV-EX7109-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 25093 | 25093 | 6700
500114487 | CLB-MP-EXCV-EX7109-STRUCT-CABIN-AIRCR | Air Conditioning System | 25093 | 6253 | 6700
500114486 | CLB-MP-EXCV-EX7109-STRUCT-BUCKT | Bucket | 25093 | 14625 | 6700
500114485 | CLB-MP-EXCV-EX7109-STRUCT-BOOMS | Boom Static Lines | 25093 | 25093 | 6700
500114484 | CLB-MP-EXCV-EX7109-STRUCT-BOOMS | Boom Assembly | 25093 | 25093 | 6700
500114483 | CLB-MP-EXCV-EX7109-RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 25093 | 25093 | 6700
500114482 | CLB-MP-EXCV-EX7109-RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 25093 | 25093 | 6700
500114481 | CLB-MP-EXCV-EX7109-RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 25093 | 25093 | 6700
500114480 | CLB-MP-EXCV-EX7109-RHENGN-INTEX-TBORH | RH Engine Turbocharger Right Hand Side | 25093 | 15983 | 6700
500114479 | CLB-MP-EXCV-EX7109-RHENGN-INTEX-TBOLH | RH Engine Turbocharger Left Hand Side | 25093 | 13611 | 6700
500114478 | CLB-MP-EXCV-EX7109-RHENGN-INTEX-EXHST | RH Engine Exhaust System | 25093 | 25093 | 6700
500114477 | CLB-MP-EXCV-EX7109-RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 25093 | 25093 | 6700
500114476 | CLB-MP-EXCV-EX7109-RHENGN-INTEX-AFTER | RH Engine Aftercooler | 25093 | 25093 | 6700
500114475 | CLB-MP-EXCV-EX7109-RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 25093 | 15983 | 6700
500114474 | CLB-MP-EXCV-EX7109-RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 25093 | 15983 | 6700
500114473 | CLB-MP-EXCV-EX7109-RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 25093 | 25093 | 6700
500114472 | CLB-MP-EXCV-EX7109-RHENGN-COUPL | RH Engine Coupling | 25093 | 25093 | 6700
500114471 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-WTRPP | RH Engine Water Pump | 25093 | 15983 | 6700
500114470 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 25093 | 15983 | 6700
500114469 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 25093 | 25093 | 7100
500114468 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-RADTR | RH Engine Radiator | 25093 | 6579 | 6700
500114467 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 25093 | 25093 | 6700
500114466 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 25093 | 25093 | 6700
500114465 | CLB-MP-EXCV-EX7109-RHENGN-COSYS-BELTS | RH Engine V Belts | 25093 | 25093 | 6700
500114463 | CLB-MP-EXCV-EX7109-RHENGN | RH Engine Assembly C32 | 25093 | 6573 | 6700
500114462 | CLB-MP-EXCV-EX7109-MANGMT-UMPMP | Pump Management System | 25093 | 25093 | 6700
500114461 | CLB-MP-EXCV-EX7109-MANGMT-UMMMC | Mine Monitoring and Control | 25093 | 6253 | 6700
500114460 | CLB-MP-EXCV-EX7109-MANGMT-UMENG | Engine Management System | 25093 | 25093 | 6700
500114459 | CLB-MP-EXCV-EX7109-MANGMT-UMBRD | Board Control System | 25093 | 25093 | 6700
500114458 | CLB-MP-EXCV-EX7109-LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 25093 | 25093 | 6700
500114457 | CLB-MP-EXCV-EX7109-LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 25093 | 25093 | 6700
500114456 | CLB-MP-EXCV-EX7109-LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 25093 | 6579 | 6700
500114455 | CLB-MP-EXCV-EX7109-LHENGN-INTEX-TBORH | LH Engine Turbocharger Right Hand Side | 25093 | 6579 | 6700
500114454 | CLB-MP-EXCV-EX7109-LHENGN-INTEX-TBOLH | LH Engine Turbocharger Left Hand Side | 25093 | 6579 | 6700
500114453 | CLB-MP-EXCV-EX7109-LHENGN-INTEX-EXHST | LH Engine Exhaust System | 25093 | 25093 | 6700
500114452 | CLB-MP-EXCV-EX7109-LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 25093 | 25093 | 6700
500114451 | CLB-MP-EXCV-EX7109-LHENGN-INTEX-AFTER | LH Engine Aftercooler | 25093 | 25093 | 6700
500114450 | CLB-MP-EXCV-EX7109-LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 25093 | 6573 | 6700
500114449 | CLB-MP-EXCV-EX7109-LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 25093 | 6579 | 6700
500114448 | CLB-MP-EXCV-EX7109-LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 25093 | 25093 | 6700
500114447 | CLB-MP-EXCV-EX7109-LHENGN-COUPL | LH Engine Coupling | 25093 | 6579 | 6700
500114446 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-WTRPP | LH Engine Water Pump | 25093 | 6579 | 6700
500114445 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 25093 | 6573 | 6700
500114444 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 25093 | 25093 | 7100
500114443 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-RADTR | LH Engine Radiator | 25093 | 6579 | 6700
500114442 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 25093 | 25093 | 6700
500114441 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 25093 | 25093 | 6700
500114440 | CLB-MP-EXCV-EX7109-LHENGN-COSYS-BELTS | LH Engine V Belts | 25093 | 6579 | 6700
500114438 | CLB-MP-EXCV-EX7109-LHENGN | LH Engine Assembly C32 | 25093 | 6579 | 6700
500114437 | CLB-MP-EXCV-EX7109-HYDSYS-ROTRY | Rotary Joint | 25093 | 12176 | 6700
500114436 | CLB-MP-EXCV-EX7109-HYDSYS-PPDRR | Pump Drive Gearbox Right Hand | 25093 | 6573 | 6700
500114435 | CLB-MP-EXCV-EX7109-HYDSYS-PPDRL | Pump Drive Gearbox Left Hand | 25093 | 6253 | 6700
500114434 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-SVPPR | Pump Servo Right Hand | 25093 | 0 | 6700
500114433 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-SVPPL | Pump Servo Left Hand | 25093 | 0 | 6700
500114432 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing Right Hand | 25093 | 0 | 6700
500114431 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing Left Hand | 25093 | 0 | 6700
500114430 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 25093 | 0 | 6700
500114429 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 25093 | 0 | 6700
500114428 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 25093 | 0 | 6700
500114427 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 25093 | 0 | 6700
500114426 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 25093 | 0 | 6700
500114425 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 25093 | 0 | 6700
500114424 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling Right Hand | 25093 | 5852 | 6700
500114423 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling Left Hand | 25093 | 5890 | 6700
500114422 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 25093 | 25093 | 6700
500114421 | CLB-MP-EXCV-EX7109-HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 25093 | 25093 | 6700
500114420 | CLB-MP-EXCV-EX7109-HYDSYS-HDVLV-TCVVR | Travel Control Valve Block Right Hand | 25093 | 25093 | 6700
500114419 | CLB-MP-EXCV-EX7109-HYDSYS-HDVLV-TCVVL | Travel Control Valve Block Left Hand | 25093 | 25093 | 6700
500114418 | CLB-MP-EXCV-EX7109-HYDSYS-HDVLV-MCVVR | Main Control Valve Block Right Hand | 25093 | 25093 | 6700
500114417 | CLB-MP-EXCV-EX7109-HYDSYS-HDVLV-MCVVL | Main Control Valve Block Left Hand | 25093 | 25093 | 6700
500114416 | CLB-MP-EXCV-EX7109-HYDSYS-HDVLV-FTVRH | Valve Float Right Hand | 25093 | 25093 | 6700
500114415 | CLB-MP-EXCV-EX7109-HYDSYS-HDVLV-FTVLH | Valve Float Left Hand | 25093 | 25093 | 6700
500114414 | CLB-MP-EXCV-EX7109-HYDSYS-HDTNK | Tank Hydraulic | 25093 | 25093 | 6700
500114413 | CLB-MP-EXCV-EX7109-HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 25093 | 1816 | 6700
500114412 | CLB-MP-EXCV-EX7109-HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 25093 | 8634 | 6700
500114411 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 25093 | 12176 | 6700
500114410 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 25093 | 6253 | 6700
500114409 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 25093 | 0 | 6700
500114408 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 25093 | 0 | 6700
500114407 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-SWMRR | Motor Swing Right Hand Rear | 25093 | 12176 | 6700
500114406 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-SWMRF | Motor Swing Right Hand Front | 25093 | 12176 | 6700
500114405 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-SWMLR | Motor Swing Left Hand Rear | 25093 | 3294 | 6700
500114404 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 25093 | 6253 | 6700
500114403 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator Left Hand | 25093 | 6253 | 6700
500114402 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 25093 | 6253 | 6700
500114401 | CLB-MP-EXCV-EX7109-HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 25093 | 6253 | 6700
500114400 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 25093 | 6253 | 6700
500114399 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 25093 | 0 | 6700
500114398 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 25093 | 0 | 6700
500114397 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 25093 | 6253 | 6700
500114396 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-SSTBR | 2nd Speed Travel - Brake Release Hoses | 25093 | 0 | 6700
500114395 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 25093 | 0 | 6700
500114394 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 25093 | 0 | 6700
500114393 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 25093 | 0 | 6700
500114392 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 25093 | 0 | 6700
500114391 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 25093 | 0 | 6700
500114390 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 25093 | 6253 | 6700
500114389 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 25093 | 6253 | 6700
500114388 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 25093 | 6253 | 6700
500114387 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 25093 | 12176 | 6700
500114386 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 25093 | 6253 | 6700
500114385 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 25093 | 6253 | 6700
500114384 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 25093 | 6253 | 6700
500114383 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 25093 | 12176 | 6700
500114382 | CLB-MP-EXCV-EX7109-HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 25093 | 12176 | 6700
500114381 | CLB-MP-EXCV-EX7109-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 25093 | 0 | 6700
500114380 | CLB-MP-EXCV-EX7109-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 25093 | 0 | 6700
500114379 | CLB-MP-EXCV-EX7109-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 25093 | 407 | 6700
500114378 | CLB-MP-EXCV-EX7109-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 25093 | 3294 | 6700
500114377 | CLB-MP-EXCV-EX7109-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 25093 | 4661 | 6700
500114376 | CLB-MP-EXCV-EX7109-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 25093 | 4661 | 6700
500114375 | CLB-MP-EXCV-EX7109-HYDSYS-HDACC-HACCR | Accumulator Hydraulic Right Hand | 25093 | 25093 | 6700
500114374 | CLB-MP-EXCV-EX7109-HYDSYS-HDACC-HACCL | Accumulator Hydraulic Left Hand | 25093 | 25093 | 6700
500114373 | CLB-MP-EXCV-EX7109-HYDSYS | Hydraulic System | 25093 | 6253 | 6700
500114372 | CLB-MP-EXCV-EX7109-HYDSYS | Hydraulic Oil | 25093 | 0 | 6700
500114371 | CLB-MP-EXCV-EX7109-GRSYST-GRTNK | Auto Lube Resevoir | 25093 | 25093 | 6700
500114370 | CLB-MP-EXCV-EX7109-GRSYST-GRINJ | Auto Lube Injectors | 25093 | 25093 | 6700
500114369 | CLB-MP-EXCV-EX7109-GRSYST-ALBPU | Auto Lube Pump Undercarriage | 25093 | 12176 | 6700
500114368 | CLB-MP-EXCV-EX7109-GRSYST-ALBPP | Auto Lube Pump | 25093 | 16 | 6700
500114367 | CLB-MP-EXCV-EX7109-FRSUPP | Fire Suppression System | 25093 | 25093 | 6700
500114366 | CLB-MP-EXCV-EX7109-ELCTLV-START-STMRR | Starter Motor Right Hand Engine Upper | 25093 | 15983 | 6700
500114365 | CLB-MP-EXCV-EX7109-ELCTLV-START-STMRL | Starter Motor Right Hand Engine Lower | 25093 | 25093 | 6700
500114364 | CLB-MP-EXCV-EX7109-ELCTLV-START-STMLR | Starter Motor Left Hand Engine Upper | 25093 | 6579 | 6700
500114363 | CLB-MP-EXCV-EX7109-ELCTLV-START-STMLL | Starter Motor Left Hand Engine Lower | 25093 | 6579 | 6700
500114362 | CLB-MP-EXCV-EX7109-ELCTLV-CHARG-BATTY | EX014 Batteries | 25093 | 6253 | 6700
500114361 | CLB-MP-EXCV-EX7109-ELCTLV-CHARG-ALTRH | Alternator 24V Right Hand Engine | 25093 | 15983 | 6700
500114360 | CLB-MP-EXCV-EX7109-ELCTLV-CHARG-ALTLH | Alternator 24V Left Hand Engine | 25093 | 6579 | 6700
500114359 | CLB-MP-EXCV-EX7109 | EX7109 Lubrication & Mechanical Services | 25093 | 25093 | 6700
500114358 | CLB-MP-EXCV-EX7109 | Caterpillar 6040 Excavator EX7109 | 25093 | 25093 | 6700
500103203 | CLB-MP-EXCV-EX014 -TRAVEL-TRKRH | Track Assembly RH | 3415 | 1963 | 470
500103202 | CLB-MP-EXCV-EX014 -TRAVEL-TRKLH | Track Assembly LH | 3415 | 1963 | 470
500103197 | CLB-MP-EXCV-EX014 -TRAVEL-SPRKR | Sprocket RH | 3415 | 1140 | 470
500103196 | CLB-MP-EXCV-EX014 -TRAVEL-SPRKL | Sprocket LH | 3415 | 1963 | 470
500103183 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH7 | Roller Load Pos 7 R/H | 3415 | 3415 | 470
500103182 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH6 | Roller Load Pos 6 R/H | 3415 | 3415 | 470
500103181 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH5 | Roller Load Pos 5 R/H | 3415 | 3415 | 470
500103180 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH4 | Roller Load Pos 4 R/H | 3415 | 3415 | 470
500103179 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH3 | Roller Load Pos 3 R/H | 3415 | 3415 | 470
500103178 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH2 | Roller Load Pos 2 R/H | 3415 | 3415 | 470
500103177 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-LORH1 | Roller Load Pos 1 R/H | 3415 | 3415 | 470
500103176 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-IDLRH | Idler Track R/H | 3415 | 3415 | 470
500103175 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-CARRR | Roller Carrier R/H Rear | 3415 | 3415 | 470
500103174 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-CARRF | Roller Carrier R/H Front | 3415 | 3415 | 470
500103171 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 L/H | 3415 | 3415 | 470
500103170 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 L/H | 3415 | 3415 | 470
500103169 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 L/H | 3415 | 3415 | 470
500103168 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 L/H | 3415 | 3415 | 470
500103167 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 L/H | 3415 | 3415 | 470
500103166 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 L/H | 3415 | 3415 | 470
500103165 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 L/H | 3415 | 3415 | 470
500103164 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-IDLLH | Idler Track L/H | 3415 | 2018 | 470
500103163 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-CARLR | Roller Carrier L/H Rear | 3415 | 3415 | 470
500103162 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-CARLF | Roller Carrier L/H Front | 3415 | 854 | 470
500103193 | CLB-MP-EXCV-EX014 -TRAVEL | 6040 Excavator, EX014 TRAVEL HOURS | 3415 | 3415 | 470
500146732 | CLB-MP-EXCV-EX014 -HYDSYS-HDACC | Hydraulic Ladder Accumulator | 42775 | 42775 | 6700
500146731 | CLB-MP-EXCV-EX014 -HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 42775 | 42775 | 6700
500146730 | CLB-MP-EXCV-EX014 -HYDSYS-HDACC | Track Tension Accumulator RH | 42775 | 42775 | 6700
500146729 | CLB-MP-EXCV-EX014 -HYDSYS-HDACC | Track Tension Accumulator LH | 42775 | 42775 | 6700
500139317 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 19252 | 8084 | 6700
500104287 | CLB-MP-EXCV-EX014 -HYDSYS | Hydraulic System | 42775 | 3932 | 6700
500103201 | CLB-MP-EXCV-EX014 -TRAVEL-TRBKR-TBKRR | Brake Travel RH Rear | 42775 | 42775 | 6700
500103200 | CLB-MP-EXCV-EX014 -TRAVEL-TRBKR-TBKRF | Brake Travel RH Front | 42775 | 42775 | 6700
500103199 | CLB-MP-EXCV-EX014 -TRAVEL-TRBKL-TBKLR | Brake Travel LH Rear | 42775 | 42775 | 6700
500103198 | CLB-MP-EXCV-EX014 -TRAVEL-TRBKL-TBKLF | Brake Travel LH Front | 42775 | 42775 | 6700
500103195 | CLB-MP-EXCV-EX014 -TRAVEL-FDRRH | Final Drive RH | 42775 | 13967 | 6700
500103194 | CLB-MP-EXCV-EX014 -TRAVEL-FDRLH | Final Drive LH | 42775 | 15061 | 6700
500103192 | CLB-MP-EXCV-EX014 -SWGSYS-SWLUB | Swing System Lubrication | 42775 | 42775 | 6700
500103191 | CLB-MP-EXCV-EX014 -SWGSYS-SWBRK-SBKRR | Brake Swing RH Rear | 42775 | 3088 | 6700
500103190 | CLB-MP-EXCV-EX014 -SWGSYS-SWBRK-SBKRF | Brake Swing RH Front | 42775 | 13967 | 6700
500103189 | CLB-MP-EXCV-EX014 -SWGSYS-SWBRK-SBKLR | Brake Swing LH Rear | 42775 | 3088 | 6700
500103188 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBRR | Gearbox Swing RH Rear | 42775 | 3088 | 6700
500103187 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBRF | Gearbox Swing RH Front | 42775 | 13967 | 6700
500103186 | CLB-MP-EXCV-EX014 -SWGSYS-SWBOX-SGBLR | Gearbox Swing LH Rear | 42775 | 3088 | 6700
500103185 | CLB-MP-EXCV-EX014 -STRUCT-UNDER-SLEWB | Slew Bearing | 42775 | 8338 | 6700
500103184 | CLB-MP-EXCV-EX014 -STRUCT-TKFRR-TENSR | Track Tensioner R/H | 42775 | 6421 | 6700
500103172 | CLB-MP-EXCV-EX014 -STRUCT-TKFRL-TENSR | Track Tensioner L/H | 42775 | 6421 | 6700
500103160 | CLB-MP-EXCV-EX014 -STRUCT-SUPER-ROLTK | Reserve Oil Tank | 42775 | 42775 | 6700
500103159 | CLB-MP-EXCV-EX014 -STRUCT-STICK | Stick Assembly | 42775 | 42775 | 6700
500103158 | CLB-MP-EXCV-EX014 -STRUCT-HLINK-LINKR | Stick To Bucket Linkages - Right | 42775 | 42775 | 6700
500103157 | CLB-MP-EXCV-EX014 -STRUCT-HLINK-LINKL | Stick To Bucket Linkages - Left | 42775 | 42775 | 6700
500103156 | CLB-MP-EXCV-EX014 -STRUCT-HLINK | H Link Assembly | 42775 | 13843 | 6700
500103155 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-SEATS | Operators Seat | 42775 | 9748 | 6700
500103154 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-SBELT | Seat Belt | 42775 | 42775 | 6700
500103153 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 42775 | 42775 | 6700
500103152 | CLB-MP-EXCV-EX014 -STRUCT-CABIN-AIRCR | Air Conditioning System | 42775 | 8084 | 6700
500103151 | CLB-MP-EXCV-EX014 -STRUCT-BUCKT | Bucket | 42775 | 13843 | 6700
500103150 | CLB-MP-EXCV-EX014 -STRUCT-BOOMS | Boom Static Lines | 42775 | 42775 | 6700
500103149 | CLB-MP-EXCV-EX014 -STRUCT-BOOMS | Boom Assembly | 42775 | 42775 | 6700
500103148 | CLB-MP-EXCV-EX014 -RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 42775 | 42775 | 6700
500103147 | CLB-MP-EXCV-EX014 -RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 42775 | 5523 | 6700
500103146 | CLB-MP-EXCV-EX014 -RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 42775 | 5523 | 6700
500103145 | CLB-MP-EXCV-EX014 -RHENGN-INTEX-TBORH | RH Engine Turbocharger RH Side | 42775 | 5523 | 6700
500103144 | CLB-MP-EXCV-EX014 -RHENGN-INTEX-TBOLH | RH Engine Turbocharger LH Side | 42775 | 5523 | 6700
500103143 | CLB-MP-EXCV-EX014 -RHENGN-INTEX-EXHST | RH Engine Exhaust System | 42775 | 42775 | 6700
500103142 | CLB-MP-EXCV-EX014 -RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 42775 | 42775 | 6700
500103141 | CLB-MP-EXCV-EX014 -RHENGN-INTEX-AFTER | RH Engine Aftercooler | 42775 | 42775 | 6700
500103140 | CLB-MP-EXCV-EX014 -RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 42775 | 5523 | 6700
500103139 | CLB-MP-EXCV-EX014 -RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 42775 | 5523 | 6700
500103138 | CLB-MP-EXCV-EX014 -RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 42775 | 42775 | 6700
500103137 | CLB-MP-EXCV-EX014 -RHENGN-COUPL | RH Engine Coupling | 42775 | 5523 | 6700
500103136 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-WTRPP | RH Engine Water Pump | 42775 | 5523 | 6700
500103135 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 42775 | 5523 | 6700
500103134 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 42775 | 42775 | 6700
500103133 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-RADTR | RH Engine Radiator | 42775 | 5523 | 6700
500103132 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 42775 | 42775 | 6700
500103131 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 42775 | 42775 | 6700
500103130 | CLB-MP-EXCV-EX014 -RHENGN-COSYS-BELTS | RH Engine V Belts | 42775 | 42775 | 6700
500103128 | CLB-MP-EXCV-EX014 -RHENGN | RH Engine Assembly C32 | 42775 | 5523 | 6700
500103127 | CLB-MP-EXCV-EX014 -MANGMT-UMPMP | Pump Management System | 42775 | 42775 | 6700
500103126 | CLB-MP-EXCV-EX014 -MANGMT-UMMMC | Mine Monitoring and Control | 42775 | 3932 | 6700
500103125 | CLB-MP-EXCV-EX014 -MANGMT-UMENG | Engine Management System | 42775 | 42775 | 6700
500103124 | CLB-MP-EXCV-EX014 -MANGMT-UMBRD | Board Control System | 42775 | 42775 | 6700
500103123 | CLB-MP-EXCV-EX014 -LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 42775 | 42775 | 6700
500103122 | CLB-MP-EXCV-EX014 -LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 42775 | 4657 | 6700
500103121 | CLB-MP-EXCV-EX014 -LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 42775 | 4657 | 6700
500103120 | CLB-MP-EXCV-EX014 -LHENGN-INTEX-TBORH | LH Engine Turbocharger RH Side | 42775 | 4657 | 6700
500103119 | CLB-MP-EXCV-EX014 -LHENGN-INTEX-TBOLH | LH Engine Turbocharger LH Side | 42775 | 4657 | 6700
500103118 | CLB-MP-EXCV-EX014 -LHENGN-INTEX-EXHST | LH Engine Exhaust System | 42775 | 42775 | 6700
500103117 | CLB-MP-EXCV-EX014 -LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 42775 | 42775 | 6700
500103116 | CLB-MP-EXCV-EX014 -LHENGN-INTEX-AFTER | LH Engine Aftercooler | 42775 | 42775 | 6700
500103115 | CLB-MP-EXCV-EX014 -LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 42775 | 4657 | 6700
500103114 | CLB-MP-EXCV-EX014 -LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 42775 | 4657 | 6700
500103113 | CLB-MP-EXCV-EX014 -LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 42775 | 42775 | 6700
500103112 | CLB-MP-EXCV-EX014 -LHENGN-COUPL | LH Engine Coupling | 42775 | 4657 | 6700
500103111 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-WTRPP | LH Engine Water Pump | 42775 | 4657 | 6700
500103110 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 42775 | 4657 | 6700
500103109 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 42775 | 23025 | 6700
500103108 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-RADTR | LH Engine Radiator | 42775 | 4657 | 6700
500103107 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 42775 | 42775 | 6700
500103106 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 42775 | 42775 | 6700
500103105 | CLB-MP-EXCV-EX014 -LHENGN-COSYS-BELTS | LH Engine V Belts | 42775 | 4657 | 6700
500103103 | CLB-MP-EXCV-EX014 -LHENGN | LH Engine Assembly C32 | 42775 | 4657 | 6700
500103102 | CLB-MP-EXCV-EX014 -HYDSYS-ROTRY | Rotary Joint | 42775 | 19265 | 6700
500103101 | CLB-MP-EXCV-EX014 -HYDSYS-PPDRR | Pump Drive Gearbox RH | 42775 | 5523 | 6700
500103100 | CLB-MP-EXCV-EX014 -HYDSYS-PPDRL | Pump Drive Gearbox LH | 42775 | 4657 | 6700
500103099 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SVPPR | Pump Servo RH | 42775 | 3088 | 6700
500103098 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SVPPL | Pump Servo LH | 42775 | 3088 | 6700
500103097 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing RH | 42775 | 5523 | 6700
500103096 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing LH | 42775 | 4657 | 6700
500103095 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 42775 | 8084 | 6700
500103094 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 42775 | 9748 | 6700
500103093 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 42775 | 3088 | 6700
500103092 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 42775 | 5523 | 6700
500103091 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 42775 | 4657 | 6700
500103090 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 42775 | 4657 | 6700
500103089 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling RH | 42775 | 5523 | 6700
500103088 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling LH | 42775 | 4657 | 6700
500103087 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 42775 | 42775 | 6700
500103086 | CLB-MP-EXCV-EX014 -HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 42775 | 42775 | 6700
500103085 | CLB-MP-EXCV-EX014 -HYDSYS-HDVLV-TCVVR | Travel Control Valve Block RH | 42775 | 42775 | 6700
500103084 | CLB-MP-EXCV-EX014 -HYDSYS-HDVLV-TCVVL | Travel Control Valve Block LH | 42775 | 42775 | 6700
500103083 | CLB-MP-EXCV-EX014 -HYDSYS-HDVLV-MCVVR | Main Control Valve Block RH | 42775 | 42775 | 6700
500103082 | CLB-MP-EXCV-EX014 -HYDSYS-HDVLV-MCVVL | Main Control Valve Block LH | 42775 | 42775 | 6700
500103080 | CLB-MP-EXCV-EX014 -HYDSYS-HDVLV-FTVLH | Valve Float LH | 42775 | 28869 | 6700
500103079 | CLB-MP-EXCV-EX014 -HYDSYS-HDTNK | Tank Hydraulic | 42775 | 42775 | 6700
500103078 | CLB-MP-EXCV-EX014 -HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 42775 | 16486 | 6700
500103077 | CLB-MP-EXCV-EX014 -HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 42775 | 16486 | 6700
500103076 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRR | Motor Travel RH Rear | 42775 | 21181 | 6700
500103075 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMRF | Motor Travel RH Front | 42775 | 5487 | 6700
500103074 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLR | Motor Travel LH Rear | 42775 | 3932 | 6700
500103073 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-TRMLF | Motor Travel LH Front | 42775 | 1209 | 6700
500103072 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRR | Motor Swing RH Rear | 42775 | 8084 | 6700
500103071 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMRF | Motor Swing RH Front | 42775 | 11163 | 6700
500103070 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-SWMLR | Motor Swing LH Rear | 42775 | 11163 | 6700
500103069 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 42775 | 7327 | 6700
500103068 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator LH | 42775 | 7327 | 6700
500103067 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 42775 | 10414 | 6700
500103066 | CLB-MP-EXCV-EX014 -HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 42775 | 1744 | 6700
500103065 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TRTNH | Track Tensioning Hoses | 42775 | 757 | 6700
500103064 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-TMCDH | Travel Motor Case Drain Hoses | 42775 | 32631 | 6700
500103063 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 42775 | 3932 | 6700
500103062 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 42775 | 368 | 6700
500103061 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 42775 | 6421 | 6700
500103060 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 42775 | 10414 | 6700
500103059 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 42775 | 8084 | 6700
500103058 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCLVH | Rotary Coupling and Logic Valve HP Hoses | 42775 | 15680 | 6700
500103057 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-RCDMH | Rotary Coupling to Drive Motor Hoses | 42775 | 8761 | 6700
500103056 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 42775 | 5487 | 6700
500103055 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 42775 | 3932 | 6700
500103054 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-MPRCH | Main Pump to Rotary Coupling HP Hoses | 42775 | 11163 | 6700
500103053 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 42775 | 368 | 6700
500103052 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HCCHH | Hydraulic Cooling Circulation Hoses | 42775 | 368 | 6700
500103051 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDHCH | Fan Drive Circut for Hyd Cooling Hoses | 42775 | 368 | 6700
500103050 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-FDECH | Fan Drive Circut for Eng Cooling Hoses | 42775 | 11163 | 6700
500103049 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 42775 | 16172 | 6700
500103048 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-BMARH | Boom Arch Hoses | 42775 | 746 | 6700
500103047 | CLB-MP-EXCV-EX014 -HYDSYS-HDHLF-2STBR | 2nd Speed Travel / Brake Release Hoses | 42775 | 8761 | 6700
500103046 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 42775 | 2343 | 6700
500103045 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 42775 | 2343 | 6700
500103044 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 42775 | 746 | 6700
500103043 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 42775 | 3932 | 6700
500103042 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 42775 | 8761 | 6700
500103041 | CLB-MP-EXCV-EX014 -HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 42775 | 9748 | 6700
500103040 | CLB-MP-EXCV-EX014 -HYDSYS-HDACC-HACCR | Accumulator Hydraulic RH | 42775 | 13967 | 6700
500103039 | CLB-MP-EXCV-EX014 -HYDSYS-HDACC-HACCL | Accumulator Hydraulic LH | 42775 | 42775 | 6700
500103038 | CLB-MP-EXCV-EX014 -HYDSYS | Do Not Use | 42775 | 42775
500103037 | CLB-MP-EXCV-EX014 -HYDSYS | Hydraulic Oil | 42775 | 3932 | 6700
500103036 | CLB-MP-EXCV-EX014 -GRSYST-GRTNK | Auto Lube Resevoir | 42775 | 42775 | 6700
500103035 | CLB-MP-EXCV-EX014 -GRSYST-GRINJ | Auto Lube Injectors | 42775 | 42775 | 6700
500103034 | CLB-MP-EXCV-EX014 -GRSYST-ALBPU | Auto Lube Pump Undercarriage | 42775 | 11893 | 6700
500103033 | CLB-MP-EXCV-EX014 -GRSYST-ALBPP | Auto Lube Pump | 42775 | 3932 | 6700
500103032 | CLB-MP-EXCV-EX014 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 42775 | 42775 | 6700
500103031 | CLB-MP-EXCV-EX014 -ELCTLV-START-STMRR | Starter Motor RH Engine Upper | 42775 | 5523 | 6700
500103030 | CLB-MP-EXCV-EX014 -ELCTLV-START-STMRL | Starter Motor RH Engine Lower | 42775 | 5523 | 6700
500103029 | CLB-MP-EXCV-EX014 -ELCTLV-START-STMLR | Starter Motor LH Engine Upper | 42775 | 4657 | 6700
500103028 | CLB-MP-EXCV-EX014 -ELCTLV-START-STMLL | Starter Motor LH Engine Lower | 42775 | 4657 | 6700
500103027 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-BATTY | EX014 Batteries | 42775 | 11163 | 6700
500103026 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-ALTRH | Alternator 24V RH Engine | 42775 | 5523 | 6700
500103025 | CLB-MP-EXCV-EX014 -ELCTLV-CHARG-ALTLH | Alternator 24V LH Engine | 42775 | 4657 | 6700
500103024 | CLB-MP-EXCV-EX014 | EX014 Lubrication & Mechanical Services | 42775 | 42775 | 6700
500103023 | CLB-MP-EXCV-EX014 | Caterpillar 6040 Excavator, EX014 | 42775 | 42775 | 6700
500046188 | CLB-MP-EXCV-EX011 -TRAVEL-TRKRH | Track Assembly RH | 6173 | 1311 | 470
500046187 | CLB-MP-EXCV-EX011 -TRAVEL-SPRKR | Sprocket RH | 6265 | 2201 | 470
500046183 | CLB-MP-EXCV-EX011 -TRAVEL-TRKLH | Track Assembly LH | 6173 | 1311 | 470
500046182 | CLB-MP-EXCV-EX011 -TRAVEL-SPRKL | Sprocket LH | 6265 | 1415 | 470
500065087 | CLB-MP-EXCV-EX011 -TRAVEL | 6040 Excavator, EX011 TRAVEL HOURS | 6173 | 6173 | 470
500146720 | CLB-MP-EXCV-EX011 -HYDSYS-HDACC | Hydraulic Ladder Accumulator | 76952 | 76952 | 6700
500146719 | CLB-MP-EXCV-EX011 -HYDSYS-HDACC | Emergency Lowering Accumulator (Boom) | 76952 | 76952 | 6700
500146718 | CLB-MP-EXCV-EX011 -HYDSYS-HDACC | Track Tension Accumulator RH | 76952 | 76952 | 6700
500146717 | CLB-MP-EXCV-EX011 -HYDSYS-HDACC | Track Tension Accumulator LH | 76952 | 76952 | 6700
500139314 | CLB-MP-EXCV-EX011 -STRUCT-CABIN-AIRCL | Cabin Air Conditioning System Left | 20650 | 20650 | 6700
500102354 | CLB-MP-EXCV-EX011 -ELCTLV-CHARG-BATTY | EX011 Batteries | 76952 | 7059 | 6700
500101473 | CLB-MP-EXCV-EX011 -HYDSYS | Hydraulic Oil | 76952 | 6237 | 6700
500079341 | CLB-MP-EXCV-EX011 -STRUCT-HLINK | H Link Assembly | 76952 | 10423 | 6700
500060253 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-TRTN | Track Tensioning Hoses | 76952 | 6237 | 6700
500060252 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-TMCD | Travel Motor Case Drain Hoses | 76952 | 13087 | 6700
500060251 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-SWMCD | Swing Motor Case Drain Hoses | 76952 | 11678 | 6700
500060250 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-SWCRT | Swing Circut Hoses | 76952 | 13087 | 6700
500060249 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-SHTRV | Servo Hoses Cascade Room to Travel Valve | 76952 | 13087 | 6700
500060248 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-SHMCV | Servo Hoses Bulk Head to MCV | 76952 | 10962 | 6700
500060247 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-SHBLK | Servo Hoses Cascade Room to Bulk Head | 76952 | 13744 | 6700
500060246 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-RCLV | Rotary Coupling and Logic Valve HP Hoses | 76952 | 12683 | 6700
500060245 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-RCDM | Rotary Coupling to Drive Motor Hoses | 76952 | 13087 | 6700
500060244 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-PTOCL | PTO Cooling Hoses | 76952 | 4732 | 6700
500060243 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-OILSC | Oil Suction Hoses | 76952 | 17891 | 6700
500060242 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-MPRC | Main Pump to Rotary Coupling HP Hoses | 76952 | 8589 | 6700
500060241 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-HPCDL | Hydraulic Pump Case Drain Hoses | 76952 | 17891 | 6700
500060239 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-HCC | Hydraulic Cooling Circulation Hoses | 76952 | 14965 | 6700
500060238 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-FDHC | Fan Drive Circut for Hyd Cooling Hoses | 76952 | 14175 | 6700
500060237 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-FDEC | Fan Drive Circut for Eng Cooling Hoses | 76952 | 12683 | 6700
500060236 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-HBSBC | Boom Stick and Bucket Cylinder Hoses | 76952 | 13087 | 6700
500060235 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-BMAR | Boom Arch Hoses | 76952 | 10458 | 6700
500060234 | CLB-MP-EXCV-EX011 -HYDSYS-HDHLF-2STBR | 2nd Speed Travel / Brake Release Hoses | 76952 | 10458 | 6700
500046290 | CLB-MP-EXCV-EX011 -MANGMT-UMPMP | Pump Management System | 76952 | 76952 | 6700
500046289 | CLB-MP-EXCV-EX011 -MANGMT-UMBRD | Board Control System | 76952 | 76952 | 6700
500046288 | CLB-MP-EXCV-EX011 -MANGMT-UMMMC | Mine Monitoring and Control | 76952 | 18477 | 6700
500046287 | CLB-MP-EXCV-EX011 -MANGMT-UMENG | Engine Management System | 76952 | 76952 | 6700
500046286 | CLB-MP-EXCV-EX011 -FRSUPP-FSAUT-FFOAM | Fire Suppression Foam | 76952 | 76952 | 6700
500046285 | CLB-MP-EXCV-EX011 -GRSYST-ALBPU | Auto Lube Pump Undercarriage | 76952 | 10962 | 6700
500046284 | CLB-MP-EXCV-EX011 -GRSYST-ALBPP | Auto Lube Pump | 76952 | 4732 | 6700
500046283 | CLB-MP-EXCV-EX011 -GRSYST-GRTNK | Auto Lube Resevoir | 76952 | 76952 | 6700
500046282 | CLB-MP-EXCV-EX011 -GRSYST-GRINJ | Auto Lube Injectors | 76952 | 76952 | 6700
500046281 | CLB-MP-EXCV-EX011 -STRUCT-UNDER-SLEWB | Slew Bearing | 76952 | 37891 | 6700
500046280 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-CARRR | Roller Carrier R/H Rear | 76952 | 29757 | 6700
500046279 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-CARRF | Roller Carrier R/H Front | 76952 | 61372 | 6700
500046278 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH7 | Roller Load Pos 7 R/H | 76952 | 41646 | 6700
500046277 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH6 | Roller Load Pos 6 R/H | 76952 | 63773 | 6700
500046276 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH5 | Roller Load Pos 5 R/H | 76952 | 16620 | 6700
500046275 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH4 | Roller Load Pos 4 R/H | 76952 | 35176 | 6700
500046274 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH3 | Roller Load Pos 3 R/H | 76952 | 21495 | 6700
500046273 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH2 | Roller Load Pos 2 R/H | 76952 | 36555 | 6700
500046272 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-LORH1 | Roller Load Pos 1 R/H | 76952 | 26912 | 6700
500046271 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-TENSR | Track Tensioner R/H | 76952 | 17891 | 6700
500046270 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR-IDLRH | Idler Track R/H | 76952 | 6237 | 6700
500046269 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-CARLR | Roller Carrier L/H Rear | 76952 | 5594 | 6700
500046268 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-CARLF | Roller Carrier L/H Front | 76952 | 38186 | 6700
500046267 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH7 | Roller Load Pos 7 L/H | 76952 | 26912 | 6700
500046266 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH6 | Roller Load Pos 6 L/H | 76952 | 38763 | 6700
500046265 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH5 | Roller Load Pos 5 L/H | 76952 | 76952 | 6700
500046264 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH4 | Roller Load Pos 4 L/H | 76952 | 29757 | 6700
500046263 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH3 | Roller Load Pos 3 L/H | 76952 | 62091 | 6700
500046262 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH2 | Roller Load Pos 2 L/H | 76952 | 16620 | 6700
500046261 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-LOLH1 | Roller Load Pos 1 L/H | 76952 | 59907 | 6700
500046260 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-TENSR | Track Tensioner L/H | 76952 | 17719 | 6700
500046259 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL-IDLLH | Idler Track L/H | 76952 | 6237 | 6700
500046257 | CLB-MP-EXCV-EX011 -STRUCT-BUCKT | Bucket | 76952 | 11045 | 6700
500046255 | CLB-MP-EXCV-EX011 -STRUCT-HLINK-LINKR | Stick To Bucket Linkages - Right | 76952 | 10458 | 6700
500046254 | CLB-MP-EXCV-EX011 -STRUCT-HLINK-LINKL | Stick To Bucket Linkages - Left | 76952 | 10423 | 6700
500046253 | CLB-MP-EXCV-EX011 -STRUCT-STICK | Stick Assembly | 76952 | 10423 | 6700
500046252 | CLB-MP-EXCV-EX011 -STRUCT-BOOMS | Boom Static Lines | 76952 | 76952 | 6700
500046251 | CLB-MP-EXCV-EX011 -STRUCT-BOOMS | Boom Assembly | 76952 | 76952 | 6700
500046250 | CLB-MP-EXCV-EX011 -STRUCT-SUPER-ROLTK | Reserve Oil Tank | 76952 | 76952 | 6700
500046249 | CLB-MP-EXCV-EX011 -STRUCT-CABIN-SBELT | Seat Belt | 76952 | 76952 | 6700
500046248 | CLB-MP-EXCV-EX011 -STRUCT-CABIN-SEATS | Operators Seat | 76952 | 6237 | 6700
500046247 | CLB-MP-EXCV-EX011 -STRUCT-CABIN-CABPR | Cabin Pressurisation System | 76952 | 76952 | 6700
500046246 | CLB-MP-EXCV-EX011 -STRUCT-CABIN-AIRCR | Air Conditioning System | 76952 | 8589 | 6700
500046245 | CLB-MP-EXCV-EX011 -HYDSYS-HDACC-HACCR | Accumulator Hydraulic RH | 76952 | 70884 | 6700
500046244 | CLB-MP-EXCV-EX011 -HYDSYS-HDACC-HACCL | Accumulator Hydraulic LH | 76952 | 70884 | 6700
500046243 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-TRMRR | Motor Travel RH Rear | 76952 | 10458 | 6700
500046242 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-TRMRF | Motor Travel RH Front | 76952 | 7059 | 6700
500046241 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-TRMLR | Motor Travel LH Rear | 76952 | 9263 | 6700
500046240 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-TRMLF | Motor Travel LH Front | 76952 | 7059 | 6700
500046239 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-FMECR | Motor Fan Engine Radiator RH | 76952 | 3041 | 6700
500046238 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-FMECL | Motor Fan Engine Radiator LH | 76952 | 129 | 6700
500046237 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-FMCHR | Motor Fan Hydraulic Cooler Rear | 76952 | 10458 | 6700
500046236 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-FMCHF | Motor Fan Hydraulic Cooler Front | 76952 | 4732 | 6700
500046235 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-SWMRR | Motor Swing RH Rear | 76952 | 5594 | 6700
500046234 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-SWMRF | Motor Swing RH Front | 76952 | 6237 | 6700
500046233 | CLB-MP-EXCV-EX011 -HYDSYS-HDMOT-SWMLR | Motor Swing LH Rear | 76952 | 5594 | 6700
500046232 | CLB-MP-EXCV-EX011 -HYDSYS-HDVLV-FTVRH | Valve Float RH | 76952 | 38763 | 6700
500046231 | CLB-MP-EXCV-EX011 -HYDSYS-HDVLV-FTVLH | Valve Float LH | 76952 | 76952 | 6700
500046230 | CLB-MP-EXCV-EX011 -HYDSYS-HDVLV-TCVVR | Travel Control Valve Block RH | 76952 | 76952 | 6700
500046229 | CLB-MP-EXCV-EX011 -HYDSYS-HDVLV-TCVVL | Travel Control Valve Block LH | 76952 | 76952 | 6700
500046228 | CLB-MP-EXCV-EX011 -HYDSYS-HDVLV-MCVVR | Main Control Valve Block RH | 76952 | 17276 | 6700
500046227 | CLB-MP-EXCV-EX011 -HYDSYS-HDVLV-MCVVL | Main Control Valve Block LH | 76952 | 19577 | 6700
500046226 | CLB-MP-EXCV-EX011 -HYDSYS-ROTRY | Rotary Joint | 76952 | 15588 | 6700
500046225 | CLB-MP-EXCV-EX011 -HYDSYS-HDOCO-OCHYR | Oil Cooler Hydraulic Rear | 76952 | 14175 | 6700
500046224 | CLB-MP-EXCV-EX011 -HYDSYS-HDOCO-OCHYF | Oil Cooler Hydraulic Front | 76952 | 11678 | 6700
500046223 | CLB-MP-EXCV-EX011 -HYDSYS-HDTNK | Tank Hydraulic | 76952 | 76952 | 6700
500046222 | CLB-MP-EXCV-EX011 -HYDSYS-HDCYL-BUCYR | Cylinder Bucket RH | 76947 | 2596 | 6700
500046221 | CLB-MP-EXCV-EX011 -HYDSYS-HDCYL-BUCYL | Cylinder Bucket LH | 76952 | 16620 | 6700
500046220 | CLB-MP-EXCV-EX011 -HYDSYS-HDCYL-STCLR | Cylinder Stick RH | 76952 | 9933 | 6700
500046219 | CLB-MP-EXCV-EX011 -HYDSYS-HDCYL-STCLL | Cylinder Stick LH | 76952 | 7059 | 6700
500046218 | CLB-MP-EXCV-EX011 -HYDSYS-HDCYL-BMCYR | Cylinder Boom RH | 76952 | 19125 | 6700
500046217 | CLB-MP-EXCV-EX011 -HYDSYS-HDCYL-BMCYL | Cylinder Boom LH | 76952 | 8589 | 6700
500046216 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-SRPPR | Pump Swing Replenishing RH | 76952 | 12245 | 6700
500046215 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-SRPPL | Pump Swing Replenishing LH | 76952 | 12245 | 6700
500046214 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-HCCPR | Pump Circulation Hydraulic Cooling RH | 76952 | 23453 | 6700
500046213 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-HCCPL | Pump Circulation Hydraulic Cooling LH | 76952 | 76952 | 6700
500046212 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-SVPPR | Pump Servo RH | 76952 | 3190 | 6700
500046211 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-SVPPL | Pump Servo LH | 76952 | 14175 | 6700
500046210 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-HECPR | Pump Fan Hyd & Eng Cooling RH | 76952 | 4732 | 6700
500046209 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-HECPL | Pump Fan Hyd & Eng Cooling LH | 76952 | 8589 | 6700
500046208 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-SP3P4 | Pump Swing Position 3&4 | 76952 | 7059 | 6700
500046205 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-SP1P2 | Pump Swing Position 1&2 | 76952 | 6237 | 6700
500046204 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-MNPP4 | Pump Main Position 4 | 76952 | 7059 | 6700
500046203 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-MNPP3 | Pump Main Position 3 | 76952 | 12245 | 6700
500046202 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-MNPP2 | Pump Main Position 2 | 76952 | 12245 | 6700
500046201 | CLB-MP-EXCV-EX011 -HYDSYS-HYDPP-MNPP1 | Pump Main Position 1 | 76952 | 14351 | 6700
500046200 | CLB-MP-EXCV-EX011 -HYDSYS-PPDRR | Pump Drive Gearbox RH | 76952 | 23453 | 6700
500046199 | CLB-MP-EXCV-EX011 -HYDSYS-PPDRL | Pump Drive Gearbox LH | 76952 | 11678 | 6700
500046198 | CLB-MP-EXCV-EX011 -HYDSYS | Hydraulic System | 76952 | 20696 | 6700
500046197 | CLB-MP-EXCV-EX011 -SWGSYS-SWLUB | Swing System Lubrication | 76952 | 76952 | 6700
500046196 | CLB-MP-EXCV-EX011 -SWGSYS-SWBRK-SBKRR | Brake Swing RH Rear | 76952 | 4751 | 6700
500046195 | CLB-MP-EXCV-EX011 -SWGSYS-SWBRK-SBKRF | Brake Swing RH Front | 76952 | 22667 | 6700
500046194 | CLB-MP-EXCV-EX011 -SWGSYS-SWBRK-SBKLR | Brake Swing LH Rear | 76952 | 4732 | 6700
500046193 | CLB-MP-EXCV-EX011 -SWGSYS-SWBOX-SGBRR | Gearbox Swing RH Rear | 76908 | 23453 | 6700
500046192 | CLB-MP-EXCV-EX011 -SWGSYS-SWBOX-SGBRF | Gearbox Swing RH Front | 76952 | 22667 | 6700
500046191 | CLB-MP-EXCV-EX011 -SWGSYS-SWBOX-SGBLR | Gearbox Swing LH Rear | 76952 | 23453 | 6700
500046190 | CLB-MP-EXCV-EX011 -TRAVEL-TRBKR-TBKRR | Brake Travel RH Rear | 76952 | 76952 | 6700
500046189 | CLB-MP-EXCV-EX011 -TRAVEL-TRBKR-TBKRF | Brake Travel RH Front | 76952 | 76952 | 6700
500046186 | CLB-MP-EXCV-EX011 -TRAVEL-FDRRH | Final Drive RH | 76952 | 27502 | 6700
500046185 | CLB-MP-EXCV-EX011 -TRAVEL-TRBKL-TBKLR | Brake Travel LH Rear | 76952 | 76952 | 6700
500046184 | CLB-MP-EXCV-EX011 -TRAVEL-TRBKL-TBKLF | Brake Travel LH Front | 76952 | 76952 | 6700
500046181 | CLB-MP-EXCV-EX011 -TRAVEL-FDRLH | Final Drive LH | 76952 | 28642 | 6700
500046180 | CLB-MP-EXCV-EX011 -ELCTLV-START-STMRU | Starter Motor RH Engine Upper | 76952 | 7059 | 6700
500046179 | CLB-MP-EXCV-EX011 -ELCTLV-START-STMRL | Starter Motor RH Engine Lower | 76952 | 7059 | 6700
500046178 | CLB-MP-EXCV-EX011 -ELCTLV-START-STMLU | Starter Motor LH Engine Upper | 76952 | 14207 | 6700
500046177 | CLB-MP-EXCV-EX011 -ELCTLV-START-STMLL | Starter Motor LH Engine Lower | 76952 | 14207 | 6700
500046174 | CLB-MP-EXCV-EX011 -ELCTLV-CHARG-ALTRH | Alternator 24V RH Engine | 76952 | 7059 | 6700
500046173 | CLB-MP-EXCV-EX011 -ELCTLV-CHARG-ALTLH | Alternator 24V LH Engine | 76952 | 8589 | 6700
500046172 | CLB-MP-EXCV-EX011 -RHENGN-COUPL | RH Engine Coupling | 76952 | 7059 | 6700
500046171 | CLB-MP-EXCV-EX011 -RHENGN-FUSYS-FUHLF | RH Engine Fuel System Hoses & Fittings | 76952 | 39853 | 6700
500046170 | CLB-MP-EXCV-EX011 -RHENGN-FUSYS-FUINJ | RH Engine Fuel Injectors | 76952 | 7059 | 6700
500046169 | CLB-MP-EXCV-EX011 -RHENGN-FUSYS-FULPP | RH Engine Fuel Pump | 76952 | 7059 | 6700
500046168 | CLB-MP-EXCV-EX011 -RHENGN-INTEX-EXHST | RH Engine Exhaust System | 76952 | 57799 | 6700
500046167 | CLB-MP-EXCV-EX011 -RHENGN-INTEX-AFTER | RH Engine Aftercooler | 76952 | 25505 | 6700
500046166 | CLB-MP-EXCV-EX011 -RHENGN-INTEX-TBORH | RH Engine Turbocharger RH Side | 76952 | 7059 | 6700
500046165 | CLB-MP-EXCV-EX011 -RHENGN-INTEX-TBOLH | RH Engine Turbocharger LH Side | 76952 | 7059 | 6700
500046164 | CLB-MP-EXCV-EX011 -RHENGN-INTEX-AIRFL | RH Engine Air Filtration System | 76952 | 57799 | 6700
500046163 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-CSHLF | RH Engine Cooling Syst Hoses & Fittings | 76952 | 39853 | 6700
500046162 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-THERM | RH Engine Thermostats-Regulators | 76952 | 7059 | 6700
500046161 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-BELTS | RH Engine V Belts | 76952 | 6951 | 6700
500046160 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-COFAN | RH Engine Fan Cooling System | 76952 | 39853 | 6700
500046159 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-RADTR | RH Radiator Coolant Change Out | 76952 | 25505 | 6700
500046158 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-RADTR | RH Engine Radiator | 76952 | 17891 | 6700
500046157 | CLB-MP-EXCV-EX011 -RHENGN-COSYS-WTRPP | RH Engine Water Pump | 76952 | 7059 | 6700
500046156 | CLB-MP-EXCV-EX011 -RHENGN-LUBSY-PREPP | RH Engine Pre-Lube Pump | 76952 | 7059 | 6700
500046155 | CLB-MP-EXCV-EX011 -RHENGN-LUBSY-ENOLC | RH Engine Oil Cooler | 76952 | 25505 | 6700
500046154 | CLB-MP-EXCV-EX011 -RHENGN-LUBSY-OILPP | RH Engine Oil Pump | 76952 | 7059 | 6700
500046152 | CLB-MP-EXCV-EX011 -RHENGN | RH Engine Assembly Cummins KTA38C | 76952 | 6951 | 6700
500046151 | CLB-MP-EXCV-EX011 -LHENGN-COUPL | LH Engine Coupling | 76952 | 11678 | 6700
500046150 | CLB-MP-EXCV-EX011 -LHENGN-FUSYS-FUHLF | LH Engine Fuel System Hoses & Fittings | 76952 | 76952 | 6700
500046149 | CLB-MP-EXCV-EX011 -LHENGN-FUSYS-FUINJ | LH Engine Fuel Injectors | 76952 | 14207 | 6700
500046148 | CLB-MP-EXCV-EX011 -LHENGN-FUSYS-FULPP | LH Engine Fuel Pump | 76952 | 14207 | 6700
500046147 | CLB-MP-EXCV-EX011 -LHENGN-INTEX-EXHST | LH Engine Exhaust System | 76952 | 76952 | 6700
500046146 | CLB-MP-EXCV-EX011 -LHENGN-INTEX-AFTER | LH Engine Aftercooler | 76952 | 41646 | 6700
500046145 | CLB-MP-EXCV-EX011 -LHENGN-INTEX-TBORH | LH Engine Turbocharger RH Side | 76952 | 14207 | 6700
500046144 | CLB-MP-EXCV-EX011 -LHENGN-INTEX-TBOLH | LH Engine Turbocharger LH Side | 76952 | 4732 | 6700
500046143 | CLB-MP-EXCV-EX011 -LHENGN-INTEX-AIRFL | LH Engine Air Filtration System | 76952 | 76952 | 6700
500046142 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-CSHLF | LH Engine Cooling Syst Hoses & Fittings | 76952 | 76952 | 6700
500046141 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-THERM | LH Engine Thermostats-Regulators | 76952 | 14207 | 6700
500046140 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-BELTS | LH Engine V Belts | 76952 | 41646 | 6700
500046139 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-COFAN | LH Engine Fan Cooling System | 76952 | 76952 | 6700
500046138 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-RADTR | LH Radiator Coolant Change Out | 76952 | 76952 | 6700
500046137 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-RADTR | LH Engine Radiator | 76952 | 16205 | 6700
500046136 | CLB-MP-EXCV-EX011 -LHENGN-COSYS-WTRPP | LH Engine Water Pump | 76952 | 14207 | 6700
500046135 | CLB-MP-EXCV-EX011 -LHENGN-LUBSY-PREPP | LH Engine Pre-Lube Pump | 76952 | 41646 | 6700
500046134 | CLB-MP-EXCV-EX011 -LHENGN-LUBSY-ENOLC | LH Engine Oil Cooler | 76952 | 41646 | 6700
500046133 | CLB-MP-EXCV-EX011 -LHENGN-LUBSY-OILPP | LH Engine Oil Pump | 76952 | 41646 | 6700
500046131 | CLB-MP-EXCV-EX011 -LHENGN | LH Engine Assembly Cummins KTA38C | 76952 | 5537 | 6700
500036297 | CLB-MP-EXCV-EX011 | EX011 Lubrication & Mechanical Services | 76952 | 76952 | 6700
500036296 | CLB-MP-EXCV-EX011 | Caterpillar 6040 Excavator, EX011 | 76952 | 76952 | 6700
500127377 | CCK-MP-LV01-EXCVTR-EX1074 | EX1074 Caterpillar 349 RBY Excavator | 8405 | 8405 | 3500
500146048 | CLB-MP-DRLL-DR3126-AIRSYS-ARTNK | DR3126 Receiver Tank | 17932 | 4496 | 4400
500126716 | CLB-MP-DRLL-DR3126-TRAVEL-TRKRH | DR3126 Track Assembly RH | 17885 | 8631 | 4400
500126715 | CLB-MP-DRLL-DR3126-TRAVEL-TRKLH | DR3126 Track Assembly LH | 17885 | 8631 | 4400
500126714 | CLB-MP-DRLL-DR3126-TRAVEL-SPRKR | DR3126 Sprocket RH | 17885 | 8631 | 4400
500126713 | CLB-MP-DRLL-DR3126-TRAVEL-SPRKL | DR3126 Sprocket LH | 17885 | 8631 | 4400
500126712 | CLB-MP-DRLL-DR3126-TRAVEL-FDRRH | DR3126 Final Drive RH | 17885 | 8631 | 4400
500126711 | CLB-MP-DRLL-DR3126-TRAVEL-FDRLH | DR3126 Final Drive LH | 17885 | 8631 | 4400
500126710 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF10 | DR3126 Roller Load Pos 10 Single Flange | 17885 | 8631 | 4400
500126709 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF09 | DR3126 Roller Load Pos 9 Single Flange R | 17885 | 8631 | 4400
500126708 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF08 | DR3126 Roller Load Pos 8 Single Flange R | 17885 | 8631 | 4400
500126707 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF07 | DR3126 Roller Load Pos 7 Single Flange R | 17885 | 8631 | 4400
500126706 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF06 | DR3126 Roller Load Pos 6 Single Flange R | 17885 | 8631 | 4400
500126705 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF05 | DR3126 Roller Load Pos 5 Single Flange R | 17885 | 8631 | 4400
500126704 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF04 | DR3126 Roller Load Pos 4 Single Flange R | 17885 | 8631 | 4400
500126703 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF03 | DR3126 Roller Load Pos 3 Single Flange R | 17885 | 8631 | 4400
500126702 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF02 | DR3126 Roller Load Pos 2 Single Flange R | 17885 | 8631 | 4400
500126701 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-RSF01 | DR3126 Roller Load Pos 1 Single Flange R | 17885 | 8631 | 4400
500126700 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-IDLRH | DR3126 Idler Track RH | 17885 | 8631 | 4400
500126699 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-CARRF | DR3126 Roller Carrier RH | 17885 | 8631 | 4400
500126698 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR-ADJGR | DR3126 Track Adjuster Grease RH | 17885 | 8631 | 4400
500126697 | CLB-MP-DRLL-DR3126-STRUCT-TKFRR | DR3126 Track Frame RH | 17885 | 8631 | 4400
500126696 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF10 | DR3126 Roller Load Pos 10 Single Flange | 17885 | 8631 | 4400
500126695 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF09 | DR3126 Roller Load Pos 9 Single Flange L | 17885 | 8631 | 4400
500126694 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF08 | DR3126 Roller Load Pos 8 Single Flange L | 17885 | 8631 | 4400
500126693 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF07 | DR3126 Roller Load Pos 7 Single Flange L | 17885 | 8631 | 4400
500126692 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF06 | DR3126 Roller Load Pos 6 Single Flange L | 17885 | 8631 | 4400
500126691 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF05 | DR3126 Roller Load Pos 5 Single Flange L | 17885 | 8631 | 4400
500126690 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF04 | DR3126 Roller Load Pos 4 Single Flange L | 17885 | 8631 | 4400
500126689 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF03 | DR3126 Roller Load Pos 3 Single Flange L | 17885 | 8631 | 4400
500126688 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF02 | DR3126 Roller Load Pos 2 Single Flange L | 17885 | 8631 | 4400
500126687 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-RSF01 | DR3126 Roller Load Pos 1 Single Flange L | 17885 | 8631 | 4400
500126686 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-IDLLH | DR3126 Idler Track LH | 17885 | 8631 | 4400
500126685 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-CARLF | DR3126 Roller Carrier LH | 17885 | 8631 | 4400
500126684 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL-ADJGL | DR3126 Track Adjuster Grease LH | 17885 | 8631 | 4400
500126683 | CLB-MP-DRLL-DR3126-STRUCT-TKFRL | DR3126 Track Frame LH | 17885 | 8631 | 4400
500126682 | CLB-MP-DRLL-DR3126-STRUCT-CARAS-RMAGA | DR3126 Rod Magazine Assembly | 17885 | 769 | 4400
500126681 | CLB-MP-DRLL-DR3126-STRUCT-CARAS-RGRPA | DR3126 Rod Gripper Assembly | 17885 | 769 | 4400
500126680 | CLB-MP-DRLL-DR3126-STRUCT-CARAS | DR3126 Carousel Assembly | 17885 | 769 | 4400
500126679 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-SEATS | DR3126 Operators Seat | 17885 | 325 | 4400
500126678 | CLB-MP-DRLL-DR3126-STRUCT-CABIN-ACCOM | DR3126 Air Conditioning Compressor | 17885 | 4496 | 4400
500126677 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-PWRHD | DR3126 Gearbox Power Head | 17885 | 769 | 4400
500126676 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDMBA | DR3126 Feed Motor Brake Assembly | 17885 | 769 | 4400
500126675 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDS | DR3126 Feed Chain Hose Drum Sprocket | 17885 | 769 | 4400
500126674 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDHDA | DR3126 Hose Drum Assembly | 17885 | 769 | 4400
500126673 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHS | DR3126 Feed Chain Sprockets | 17885 | 769 | 4400
500126672 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHP | DR3126 Feed Chain Pulldown | 17885 | 769 | 4400
500126671 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-FDCHH | DR3126 Feed Chain Hoist | 17885 | 1481 | 4400
500126670 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-DSSAY | DR3126 Drill Steel Support Assembly | 17885 | 769 | 4400
500126669 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-DMAST | DR3126 Mast | 17885 | 769 | 4400
500126668 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BPERU | DR3126 Piston End Break Out Cylinder RH | 17885 | 769 | 4400
500126667 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BPERL | DR3126 Piston End Break Out Cylinder RH | 17885 | 769 | 4400
500126666 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BPELU | DR3126 Piston End Break Out Cylinder LH | 17885 | 769 | 4400
500126665 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BPELL | DR3126 Piston End Break Out Cylinder LH | 17885 | 769 | 4400
500126664 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BOTBL | DR3126 Breakout Table Assembly | 17885 | 769 | 4400
500126663 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BMHDA | DR3126 Boom Head Assembly | 17885 | 769 | 4400
500126662 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BMFHA | DR3126 Feed Holder Assembly | 17885 | 769 | 4400
500126661 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BMASY | DR3126 Boom Assembly | 17885 | 769 | 4400
500126660 | CLB-MP-DRLL-DR3126-STRUCT-BOOMS-BFEED | DR3126 Feed Beam Assembly | 17885 | 769 | 4400
500126659 | CLB-MP-DRLL-DR3126-LUBSYS-DHDPP | DR3126 HECL Oil Pump | 17885 | 17885 | 4400
500126658 | CLB-MP-DRLL-DR3126-HYDSYS-PMPDR-COUPL | DR3126 Pump Drive Coupling | 17885 | 4496 | 4400
500126657 | CLB-MP-DRLL-DR3126-HYDSYS-HYDPP-MNPP4 | DR3126 Pump Hydraulic 45 | 17885 | 4496 | 4400
500126656 | CLB-MP-DRLL-DR3126-HYDSYS-HYDPP-MNPP3 | DR3126 Pump Hydraulic 3 | 17885 | 4496 | 4400
500126655 | CLB-MP-DRLL-DR3126-HYDSYS-HYDPP-MNPP2 | DR3126 Pump Hydraulic 2 | 17885 | 4496 | 4400
500126654 | CLB-MP-DRLL-DR3126-HYDSYS-HYDPP-MNPP1 | DR3126 Pump Hydraulic 1 | 17885 | 4496 | 4400
500126653 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVOST | DR3126 Valve Oscillation Track | 17885 | 4496 | 4400
500126652 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVOSR | DR3126 Valve Oscillation Relief | 17885 | 4070 | 4400
500126651 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVOCR | DR3126 Valve Over Centre | 17885 | 17885 | 4400
500126650 | CLB-MP-DRLL-DR3126-HYDSYS-HDVLV-VVMBK | DR3126 Valve Main Block | 17885 | 4496 | 4400
500126649 | CLB-MP-DRLL-DR3126-HYDSYS-HDTNK | DR3126 Tank Hydraulic | 17885 | 17885 | 4400
500126648 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MRTNR | DR3126 Motor Rotation RH | 17885 | 7221 | 4400
500126647 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MRTNL | DR3126 Motor Rotation LH | 17885 | 7221 | 4400
500126646 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MPRPR | DR3126 Motor Propel RH | 17885 | 17885 | 4400
500126645 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MPRPL | DR3126 Motor Propel LH | 17885 | 17885 | 4400
500126644 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFRCA | DR3126 Motor Fan RadCAC Cooler Assy | 17885 | 4496 | 4400
500126643 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFHCA | DR3126 Motor Fan HydComp Cooler Assy | 17885 | 4496 | 4400
500126642 | CLB-MP-DRLL-DR3126-HYDSYS-HDMOT-MFEED | DR3126 Motor Feed | 17885 | 769 | 4400
500126641 | CLB-MP-DRLL-DR3126-HYDSYS-HDHLF | Hydraulic System Hose Lines Fittings | 17885 | 17885 | 4400
500126640 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-TFCOR | DR3126 Cylinder Oscillation RH | 17885 | 1925 | 4400
500126639 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-TFCOL | DR3126 Cylinder Oscillation LH | 17885 | 1925 | 4400
500126638 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-RSFEC | DR3126 Cylinder Rod Support Feed Extensi | 17885 | 769 | 4400
500126637 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-RMCTN | DR3126 Cylinder Rod Magazine Turning | 17885 | 769 | 4400
500126636 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-RMCSU | DR3126 Cylinder Rod Magazine Securing Up | 17885 | 769 | 4400
500126635 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-RMCSL | DR3126 Cylinder Rod Magazine Securing Lo | 17885 | 769 | 4400
500126634 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-JLCYR | DR3126 Cylinder Jack levelling Rear | 17885 | 7491 | 4400
500126633 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-HASCU | DR3126 Cylinder Handling Arm Swing Upper | 17885 | 769 | 4400
500126632 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-HASCL | DR3126 Cylinder Handling Arm Swing Lower | 17885 | 769 | 4400
500126631 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-HACTN | DR3126 Cylinder Rod Handling Arm Gripper | 17885 | 769 | 4400
500126630 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-HACGU | DR3126 Cylinder Rod Handling Arm Gripper | 17885 | 769 | 4400
500126629 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-HACGL | DR3126 Cylinder Rod Handling Arm Gripper | 17885 | 769 | 4400
500126628 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-FDHCS | DR3126 Cylinder Feed Holder Swing | 17885 | 769 | 4400
500126627 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-FDDCR | DR3126 Cylinder Feed Dump RH | 17885 | 769 | 4400
500126626 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-FDDCL | DR3126 Cylinder Feed Dump LH | 17885 | 769 | 4400
500126625 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-FDCYE | DR3126 Cylinder Feed Extension | 17885 | 769 | 4400
500126624 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-DSCRH | DR3126 Cylinder Drill Steel Support lowe | 17885 | 769 | 4400
500126623 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-DSCLH | DR3126 Cylinder Drill Steel Support lowe | 17885 | 769 | 4400
500126622 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOTMC | DR3126 Cylinder Main Break Out Table | 17885 | 769 | 4400
500126621 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOTLR | DR3126 Cylinder Break Out Table Lower R | 17885 | 769 | 4400
500126620 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOTLL | DR3126 Cylinder Break Out Table Lower L | 17885 | 769 | 4400
500126619 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOBRU | DR3126 Cylinder Break Out Table Breaking | 17885 | 769 | 4400
500126618 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOBRL | DR3126 Cylinder Break Out Table Breaking | 17885 | 769 | 4400
500126617 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOBLU | DR3126 Cylinder Break Out Table Breaking | 17885 | 769 | 4400
500126616 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BOBLL | DR3126 Cylinder Break Out Table Breaking | 17885 | 769 | 4400
500126615 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BMCYS | DR3126 Cylinder Boom Swing | 17885 | 769 | 4400
500126614 | CLB-MP-DRLL-DR3126-HYDSYS-HDCYL-BMCYH | DR3126 Cylinder Boom Lift | 17885 | 769 | 4400
500126613 | CLB-MP-DRLL-DR3126-HYDSYS-COFAN-FCHCA | DR3126 Fan HydraulicCompressor Cooling | 17885 | 4496 | 4400
500126612 | CLB-MP-DRLL-DR3126-HYDSYS-COFAN-FCECA | DR3126 Fan EngineCAC Cooling | 17885 | 4496 | 4400
500126611 | CLB-MP-DRLL-DR3126-GRSYST-RTLPP | DR3126 Rod Thread lube Pump | 17885 | 9803 | 4400
500126610 | CLB-MP-DRLL-DR3126-GRSYST-ALPSV | DR3126 Auto lube Pump Safety Valve | 17885 | 8607 | 4400
500126609 | CLB-MP-DRLL-DR3126-GRSYST-ALBPP | DR3126 Auto lube Pump | 17885 | 10500 | 4400
500126608 | CLB-MP-DRLL-DR3126-FRSUPP | DR3126 Fire Suppression System | 17885 | 17885 | 4400
500126607 | CLB-MP-DRLL-DR3126-ENGINE-INTEX-TBOP1 | DR3126 Turbocharger Engine | 17885 | 4496 | 4400
500126606 | CLB-MP-DRLL-DR3126-ENGINE-FUSYS-FULTK | DR3126 Fuel Tank Engine | 17885 | 4496 | 4400
500126605 | CLB-MP-DRLL-DR3126-ENGINE-FUSYS-FULPP | DR3126 Fuel Pump Engine | 17885 | 4496 | 4400
500126604 | CLB-MP-DRLL-DR3126-ENGINE-FUSYS-FULCO | DR3126 Fuel Cooler Engine | 17885 | 4496 | 4400
500126603 | CLB-MP-DRLL-DR3126-ENGINE-FUSYS-FUINJ | DR3126 Fuel Injectors Engine | 17885 | 4496 | 4400
500126602 | CLB-MP-DRLL-DR3126-ENGINE-FUSYS | DR3126 Engine Fuel System | 17885 | 17885 | 4400
500126601 | CLB-MP-DRLL-DR3126-ENGINE-COSYS-WTRPP | DR3126 Water pump Engine | 17885 | 4496 | 4400
500126600 | CLB-MP-DRLL-DR3126-ENGINE-COSYS-THERM | DR3126 ThermostatsRegulators Engine | 17885 | 4496 | 4400
500126599 | CLB-MP-DRLL-DR3126-ENGINE | DR3126 Engine Assembly C15 | 17885 | 4496 | 4400
500126598 | CLB-MP-DRLL-DR3126-ELCTLV-START-STRMR | DR3126 Starter Motor Engine | 17885 | 4496 | 4400
500126596 | CLB-MP-DRLL-DR3126-ELCTLV-HARNS | Wiring Harness | 17885 | 17885 | 4400
500126589 | CLB-MP-DRLL-DR3126-ELCTLV-CHARG-BATTY | DR3126 Batteries Engine | 17885 | 4043 | 4400
500126588 | CLB-MP-DRLL-DR3126-ELCTLV-CHARG-ALTER | DR3126 Alternator 24V | 17885 | 4496 | 4400
500126587 | CLB-MP-DRLL-DR3126-DSTSUP-WTTNK | DR3126 Water Tank | 17885 | 17885 | 4400
500126586 | CLB-MP-DRLL-DR3126-DSTSUP-WTRPP | DR3126 Pump Water Mist | 17885 | 7491 | 4400
500126585 | CLB-MP-DRLL-DR3126-COOLER-RADCA | DR3126 Cooler Radiator Charge Air | 17885 | 4496 | 4400
500126584 | CLB-MP-DRLL-DR3126-COOLER-HDOCO | DR3126 Cooler Hydraulic Compressor | 17885 | 4496 | 4400
500126583 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-VCSRL | DR3126 Air Compressor Safety Relief | 17885 | 4496 | 4400
500126582 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-VCOSP | DR3126 Air Compressor Oil Stop Valve | 17885 | 4496 | 4400
500126581 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-VCLOD | DR3126 Compressor Load Solenoid Valve | 17885 | 4496 | 4400
500126220 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-VCFLS | DR3126 Air Compressor Flushing Valves | 17885 | 4496 | 4400
500126219 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-VCBLW | DR3126 Air Compressor Blow Off Valve | 17885 | 4496 | 4400
500126218 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-VC34B | DR3126 34 bar Control Valves | 17885 | 4496 | 4400
500126217 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PNHLF | DR3126 Air Hose Restraints | 17885 | 17885 | 4400
500126216 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-PALUB | DR3126 Pump Air Lubrication | 17885 | 6064 | 4400
500126215 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-COUPL | DR3126 Compressor Coupling | 17885 | 4496 | 4400
500126213 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR | DR3126 Main Air Compressor | 17885 | 4496 | 4400
500126212 | CLB-MP-DRLL-DR3126 | Epiroc D65 XLF Drill DR3126 | 17885 | 17885 | 4400
500146033 | CLB-MP-DRLL-DR3110-AIRSYS-ARTNK | DR3110 Receiver Tank | 30612 | 30612 | 4200
500118511 | CLB-MP-DRLL-DR3110-HYDSYS-HDHLF | Hydraulic System Hose Lines Fittings | 30594 | 7471 | 4200
500116541 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-RSFEC | Cylinder Rod Support Feed Extension | 30594 | 30594 | 4200
500116532 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BOTMC | Cylinder Main Break Out Table | 30594 | 30594 | 4200
500116523 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BOBRU | Cylinder Break Out Table Breaking RHU | 30594 | 517 | 4200
500116514 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BOBRL | Cylinder Break Out Table Breaking RHL | 30594 | 517 | 4200
500116505 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BOBLL | Cyl Break Out Table Breaking LHL | 30594 | 1870 | 4200
500116496 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BOBLU | Cyl Break Out Table Breaking LHU | 30594 | 12476 | 4200
500116487 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-RMCSL | Cyl Rod Magazine Securing Lower | 30594 | 13910 | 4200
500116478 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-RMCSU | Cyl Rod Magazine Securing Upper | 30594 | 13910 | 4200
500116469 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-HACGL | Cylinder Rod Handling Arm Gripper Lower | 30594 | 13910 | 4200
500116460 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-HACGU | Cylinder Rod Handling Arm Gripper Upper | 30594 | 13910 | 4200
500116451 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-HASCL | Cylinder Handling Arm Swing Lower | 30594 | 13910 | 4200
500116442 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-HASCU | Cylinder Handling Arm Swing Upper | 30594 | 13910 | 4200
500116433 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-DSCRH | Cylinder Rod Supt Lower RH | 30594 | 13910 | 4200
500116414 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-DSCLH | Cylinder Rod Supt Lower LH | 30594 | 13910 | 4200
500116366 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-CARRF | Carrier Roller RH | 30594 | 5268 | 4200
500116357 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-CARLF | Carrier Roller LH | 30594 | 5268 | 4200
500116196 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 RH | 30594 | 517 | 4200
500116195 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 RH | 30594 | 5268 | 4200
500116194 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 RH | 30594 | 5268 | 4200
500116193 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 RH | 30594 | 5268 | 4200
500116192 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 RH | 30594 | 5268 | 4200
500116191 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 RH | 30594 | 5268 | 4200
500116190 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 RH | 30594 | 5268 | 4200
500116189 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 RH | 30594 | 5268 | 4200
500116188 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 RH | 30594 | 5268 | 4200
500116187 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 RH | 30594 | 5268 | 4200
500116186 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 LH | 30594 | 5268 | 4200
500116185 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 LH | 30594 | 5268 | 4200
500116184 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 LH | 30594 | 5268 | 4200
500116183 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 LH | 30594 | 5268 | 4200
500116182 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 LH | 30594 | 5268 | 4200
500116181 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 LH | 30594 | 5268 | 4200
500116180 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 LH | 30594 | 5268 | 4200
500116179 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 LH | 30594 | 5268 | 4200
500116178 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 LH | 30594 | 5268 | 4200
500116177 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 LH | 30594 | 5268 | 4200
500116168 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR-IDLRH | Idler Track RH | 30594 | 5268 | 4200
500116159 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL-IDLLH | Idler Track LH | 30594 | 5268 | 4200
500116150 | CLB-MP-DRLL-DR3110-TRAVEL-TRKRH | Track Assembly RH | 30594 | 5268 | 4200
500116141 | CLB-MP-DRLL-DR3110-TRAVEL-TRKLH | Track Assembly LH | 30594 | 5268 | 4200
500116132 | CLB-MP-DRLL-DR3110-TRAVEL-SPRKR | Sprocket RH | 30594 | 5268 | 4200
500116123 | CLB-MP-DRLL-DR3110-TRAVEL-SPRKL | Sprocket LH | 30594 | 5268 | 4200
500116114 | CLB-MP-DRLL-DR3110-STRUCT-TKFRR | Track Frame RH | 30594 | 5268 | 4200
500116105 | CLB-MP-DRLL-DR3110-STRUCT-TKFRL | Track Frame LH | 30594 | 5268 | 4200
500116087 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-DMAST | Mast | 30594 | 7471 | 4200
500116028 | CLB-MP-DRLL-DR3110-ELCTLV-HARNS | Wiring Harness | 30594 | 30594 | 4200
500101142 | CLB-MP-DRLL-DR3110-TRAVEL-FDRRH | DR3110 Final Drive R/H | 30594 | 5268 | 4200
500101141 | CLB-MP-DRLL-DR3110-TRAVEL-FDRLH | DR3110 Final Drive L/H | 30594 | 5268 | 4200
500101137 | CLB-MP-DRLL-DR3110-STRUCT-CARAS-RMAGA | DR3110 Rod Magazine Assembly | 30594 | 25440 | 4200
500101136 | CLB-MP-DRLL-DR3110-STRUCT-CARAS-RGRPA | DR3110 Rod Gripper Assembly | 30594 | 30594 | 4200
500101135 | CLB-MP-DRLL-DR3110-STRUCT-CARAS | DR3110 Carousel Assembly | 30594 | 30594 | 4200
500101134 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-SEATS | DR3110 Operators Seat | 30594 | 8770 | 4200
500101133 | CLB-MP-DRLL-DR3110-STRUCT-CABIN-ACCOM | DR3110 Air Conditioning Compressor | 30594 | 7471 | 4200
500101132 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-PWRHD | DR3110 Gearbox Power Head | 30472 | 3162 | 4200
500101131 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDS | DR3110 Feed Chain Hose Drum Sprocket | 30594 | 7471 | 4200
500101130 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDHDA | DR3110 Hose Drum Assembly | 30594 | 7471 | 4200
500101129 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHS | DR3110 Feed Chain Sprockets | 30594 | 7471 | 4200
500101128 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHP | DR3110 Feed Chain Pulldown | 30594 | 1605 | 4200
500101127 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-FDCHH | DR3110 Feed Chain Hoist | 30594 | 2427 | 4200
500101126 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-DSSAY | DR3110 Drill Steel Support Assembly | 30594 | 30594 | 4200
500101125 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BPERU | DR3110 Piston End Break Out Cyl R/H/U | 30594 | 17934 | 4200
500101124 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BPERL | DR3110 Piston End Break Out Cyl R/H/L | 30594 | 21769 | 4200
500101123 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BPELU | DR3110 Piston End Break Out Cyl L/H/U | 30594 | 30594 | 4200
500101122 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BPELL | DR3110 Piston End Break Out Cyl L/H/L | 30594 | 30594 | 4200
500101121 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BOTBL | DR3110 Breakout Table Assembly | 30594 | 11216 | 4200
500101120 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BMHDA | DR3110 Boom Head Assembly | 30594 | 30594 | 4200
500101119 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BMFHA | DR3110 Feed Holder Assembly | 30594 | 30594 | 4200
500101118 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BMATM | DR3110 Boom Attachment Assembly | 30594 | 30594 | 4200
500101117 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BMASY | DR3110 Boom Assembly | 30594 | 13910 | 4200
500101116 | CLB-MP-DRLL-DR3110-STRUCT-BOOMS-BFEED | DR3110 Feed Beam Assembly | 30594 | 30594 | 4200
500101115 | CLB-MP-DRLL-DR3110-LUBSYS-DHDPP | DR3110 DHD Oil Pump | 30594 | 1314 | 4200
500101114 | CLB-MP-DRLL-DR3110-HYDSYS-PMPDR-DRSHT | DR3110 Pump Drive Drive Shaft | 30594 | 7471 | 4200
500101113 | CLB-MP-DRLL-DR3110-HYDSYS-HYDPP-MNPP3 | DR3110 Pump Hydraulic 25CC + 25CC | 30594 | 5567 | 4200
500101112 | CLB-MP-DRLL-DR3110-HYDSYS-HYDPP-MNPP2 | DR3110 Pump Hydraulic 2A | 30594 | 7471 | 4200
500101111 | CLB-MP-DRLL-DR3110-HYDSYS-HYDPP-MNPP1 | DR3110 Pump Hydraulic 3A | 30594 | 7471 | 4200
500101110 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOST | DR3110 Valve Oscillation Track | 30594 | 7471 | 4200
500101109 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOSR | DR3110 Valve Oscillation Relief | 30594 | 7471 | 4200
500101108 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVOCR | DR3110 Valve Over Centre | 30594 | 30594 | 4200
500101107 | CLB-MP-DRLL-DR3110-HYDSYS-HDVLV-VVMBK | DR3110 Valve Main Block | 30594 | 6461 | 4200
500101106 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MWINC | DR3110 Motor Winch | 30594 | 30594 | 4200
500101105 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MRTNR | DR3110 Motor Rotation R/H | 30594 | 24371 | 4200
500101104 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MRTNL | DR3110 Motor Rotation L/H | 30594 | 13791 | 4200
500101103 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MPRPR | DR3110 Motor Propel R/H | 30594 | 30594 | 4200
500101102 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MPRPL | DR3110 Motor Propel L/H | 30594 | 30594 | 4200
500101101 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MFRCA | DR3110 Motor Fan Rad/CAC Cooler Assy | 30594 | 12476 | 4200
500101100 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MFHCA | DR3110 Motor Fan HYD/COMP Cooler Assy | 30594 | 1870 | 4200
500101099 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-MFEED | DR3110 Motor Feed | 30594 | 1634 | 4200
500101098 | CLB-MP-DRLL-DR3110-HYDSYS-HDMOT-ACONM | DR3110 Motor Hyd Air Con | 30594 | 1870 | 4200
500101097 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-TFCOR | DR3110 Cylinder Oscillation R/H | 30594 | 5268 | 4200
500101096 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-TFCOL | DR3110 Cylinder Oscillation L/H | 30594 | 5268 | 4200
500101095 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-RMCTN | DR3110 Cyl Rod Magazine Turning | 30594 | 7471 | 4200
500101094 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-JLCYR | DR3110 Cylinder Jack levelling Rear | 30594 | 9692 | 4200
500101093 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-HACTN | DR3110 Cyl Rod Handling Arm Grip Turn | 30594 | 7471 | 4200
500101092 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-FDHCS | DR3110 Cylinder Feed Holder Swing | 30594 | 13910 | 4200
500101091 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-FDDCR | DR3110 Cylinder Feed Dump R/H | 30594 | 13910 | 4200
500101090 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-FDDCL | DR3110 Cylinder Feed Dump L/H | 30594 | 13910 | 4200
500101089 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-FDCYE | DR3110 Cylinder Feed Extension | 30594 | 13910 | 4200
500101088 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BMCYS | DR3110 Cylinder Boom Swing | 30594 | 13910 | 4200
500101087 | CLB-MP-DRLL-DR3110-HYDSYS-HDCYL-BMCYH | DR3110 Cylinder Boom Lift | 30594 | 13910 | 4200
500101086 | CLB-MP-DRLL-DR3110-HYDSYS-COFAN-FCHCA | DR3110 Fan Hydraulic/Compressor Cooling | 30594 | 30594 | 4200
500101085 | CLB-MP-DRLL-DR3110-HYDSYS-COFAN-FCECA | DR3110 Fan Engine/CAC Cooling | 30594 | 13910 | 4200
500101084 | CLB-MP-DRLL-DR3110-GRSYST-RTLPP | DR3110 Rod Thread lube Pump | 30594 | 208 | 4200
500101083 | CLB-MP-DRLL-DR3110-GRSYST-ALPSV | DR3110 Auto lube Pump Safety Valve | 30594 | 30594 | 4200
500101082 | CLB-MP-DRLL-DR3110-GRSYST-ALBPP | DR3110 Auto lube Pump | 30594 | 6871 | 4200
500101081 | CLB-MP-DRLL-DR3110-FRSUPP | DR3110 Fire Suppression System | 30594 | 30594 | 4200
500101080 | CLB-MP-DRLL-DR3110-ENGINE-INTEX-TBOP1 | DR3110 Turbocharger Engine | 30594 | 7471 | 4200
500101079 | CLB-MP-DRLL-DR3110-ENGINE-FUSYS-FULPP | DR3110 Fuel Pump Engine | 30594 | 7471 | 4200
500101078 | CLB-MP-DRLL-DR3110-ENGINE-FUSYS-FULCO | DR3110 Fuel Cooler Engine | 30594 | 30594 | 4200
500101077 | CLB-MP-DRLL-DR3110-ENGINE-FUSYS-FUINJ | DR3110 Fuel Injectors Engine | 30594 | 7471 | 4200
500101076 | CLB-MP-DRLL-DR3110-ENGINE-COSYS-WTRPP | DR3110 Water pump Engine | 30594 | 7471 | 4200
500101075 | CLB-MP-DRLL-DR3110-ENGINE-COSYS-THERM | DR3110 Thermostats/Regulators Engine | 30594 | 7471 | 4200
500101074 | CLB-MP-DRLL-DR3110-ENGINE-COSYS-CSHLF | DR3110 Coolant Hoses | 30594 | 7471 | 4200
500101073 | CLB-MP-DRLL-DR3110-ENGINE | DR3110 Engine Assembly | 30594 | 7471 | 4200
500101072 | CLB-MP-DRLL-DR3110-ELCTLV-START-STRMR | DR3110 Starter Motor Engine | 30594 | 7471 | 4200
500101068 | CLB-MP-DRLL-DR3110-ELCTLV-CONTL-D103 | DR3110 Module I/O RCS4 D103 | 30594 | 30594 | 4200
500101067 | CLB-MP-DRLL-DR3110-ELCTLV-CONTL-D102 | DR3110 Module I/O RCS4 D102 | 30594 | 30594 | 4200
500101066 | CLB-MP-DRLL-DR3110-ELCTLV-CONTL-D101 | DR3110 Module I/O RCS4 D101 | 30594 | 30594 | 4200
500101065 | CLB-MP-DRLL-DR3110-ELCTLV-CHARG-ALTER | DR3110 Alternator 24V | 30594 | 7471 | 4200
500101064 | CLB-MP-DRLL-DR3110-DSTSUP-WTTNK | DR3110 Water Tank | 30594 | 30594 | 4200
500101063 | CLB-MP-DRLL-DR3110-DSTSUP-WTRPP | DR3110 Pump Water Injection | 30594 | 772 | 4200
500101062 | CLB-MP-DRLL-DR3110-COOLER-RADCA | DR3110 Cooler Radiator / Charge Air | 30594 | 7471 | 4200
500101061 | CLB-MP-DRLL-DR3110-COOLER-HDOCO | DR3110 Cooler Hydraulic / Compressor | 30594 | 7471 | 4200
500101060 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCSRL | DR3110 Air Compressor Safety Relief | 30594 | 7471 | 4200
500101059 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCOSP | DR3110 Air Compressor Oil Stop Valve | 30594 | 30594 | 4200
500101058 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCLOD | DR3110 Air Compressor Load Valves | 30594 | 7471 | 4200
500101057 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCINL | DR3110 Air Compressor Inlet Valve | 30594 | 30594 | 4200
500101056 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCFLS | DR3110 Air Compressor Flushing Valves | 30612 | 7471 | 4200
500101055 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VCBLW | DR3110 Air Compressor Blow Off Valve | 30612 | 7471 | 4200
500101054 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-VC34B | DR3110 34 bar Control Valves | 30612 | 7471 | 4200
500101053 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-PALUB | DR3110 Pump Air Lubrication | 30612 | 9932 | 4200
500101052 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-COUPL | DR3110 Compressor Coupling Ringfeeder | 30612 | 7471 | 4200
500101050 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR | DR3110 Main Air Compressor | 30612 | 7471 | 4200
500101049 | CLB-MP-DRLL-DR3110 | Epiroc Smartroc D65 Drill DR3110 | 30612 | 30612 | 5400
500146046 | CLB-MP-DRLL-DR2133-AIRSYS-ARTNK | DR2133 Receiver Tank | 15211 | 3277 | 6700
500140562 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 15193 | 455 | 6700
500140561 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 15193 | 2584 | 6700
500138790 | CLB-MP-DRLL-DR2133-STRUCT-UNDER-EQUAL | Equaliser Bar | 15193 | 15193 | 6700
500138763 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKS | Water Tank Secondary | 15193 | 15193 | 6700
500135676 | CLB-MP-DRLL-DR2133-TRAVEL-TRKRH | Track Assembly Right Hand | 15193 | 10303 | 6700
500135675 | CLB-MP-DRLL-DR2133-TRAVEL-TRKLH | Track Assembly Left Hand | 15193 | 15193 | 6700
500135674 | CLB-MP-DRLL-DR2133-TRAVEL-TRBKR | Travel Brake Right Hand | 15193 | 15193 | 6700
500135673 | CLB-MP-DRLL-DR2133-TRAVEL-TRBKL | Travel Brake Left Hand | 15193 | 15193 | 6700
500135672 | CLB-MP-DRLL-DR2133-TRAVEL-SPRKR | Sprocket Right Hand | 15193 | 2584 | 6700
500135671 | CLB-MP-DRLL-DR2133-TRAVEL-SPRKL | Sprocket Left Hand | 15193 | 2584 | 6700
500135670 | CLB-MP-DRLL-DR2133-TRAVEL-FDRRH | Final Drive Right Hand | 15193 | 15193 | 6700
500135669 | CLB-MP-DRLL-DR2133-TRAVEL-FDRLH | Final Drive Left Hand | 15193 | 15193 | 6700
500135668 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 15193 | 2584 | 6700
500135667 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 15193 | 15193 | 6700
500135666 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 15193 | 15193 | 6700
500135665 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 15193 | 12396 | 6700
500135664 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 15193 | 15193 | 6700
500135663 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 15193 | 15193 | 6700
500135662 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 15193 | 15193 | 6700
500135661 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 15193 | 15193 | 6700
500135660 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 15193 | 15193 | 6700
500135659 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 15193 | 15193 | 6700
500135658 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 15193 | 15193 | 6700
500135657 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 15193 | 2584 | 6700
500135656 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 15193 | 2584 | 6700
500135655 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 15193 | 15193 | 6700
500135654 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 15193 | 15193 | 6700
500135653 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 15193 | 15193 | 6700
500135652 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 15193 | 15193 | 6700
500135651 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 15193 | 15193 | 6700
500135650 | CLB-MP-DRLL-DR2133-STRUCT-TKFRR | Track Frame-Cab Side | 15193 | 15193 | 6700
500135649 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 15193 | 2584 | 6700
500135648 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 15193 | 15193 | 6700
500135647 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 15193 | 15193 | 6700
500135646 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 15193 | 15193 | 6700
500135645 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 15193 | 15193 | 6700
500135644 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 15193 | 15193 | 6700
500135643 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 15193 | 15193 | 6700
500135642 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 15193 | 15193 | 6700
500135641 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 15193 | 15193 | 6700
500135640 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 15193 | 15193 | 6700
500135639 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 15193 | 15193 | 6700
500135638 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 15193 | 2584 | 6700
500135637 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 15193 | 2584 | 6700
500135636 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 15193 | 15193 | 6700
500135635 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 15193 | 15193 | 6700
500135634 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 15193 | 15193 | 6700
500135633 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 15193 | 15193 | 6700
500135632 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 15193 | 15193 | 6700
500135631 | CLB-MP-DRLL-DR2133-STRUCT-TKFRL | Track Frame-Non Cab Side | 15193 | 15193 | 6700
500135630 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 15193 | 15193 | 6700
500135629 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 15193 | 15193 | 6700
500135628 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 15193 | 15193 | 6700
500135627 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 15193 | 15193 | 6700
500135626 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 15193 | 3176 | 6700
500135625 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 15193 | 3176 | 6700
500135624 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 15193 | 3176 | 6700
500135623 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 15193 | 3176 | 6700
500135622 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 15193 | 15193 | 6700
500135621 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 15193 | 15193 | 6700
500135620 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 15193 | 15193 | 6700
500135619 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 15193 | 15193 | 6700
500135618 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 15193 | 15193 | 6700
500135617 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 15193 | 961 | 6700
500135616 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 15193 | 961 | 6700
500135615 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 15193 | 15193 | 6700
500135614 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 15193 | 15193 | 6700
500135613 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 15193 | 961 | 6700
500135612 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 15193 | 961 | 6700
500135611 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 15193 | 961 | 6700
500135610 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-DSPAN | Deck Spanner | 15193 | 15193 | 6700
500135609 | CLB-MP-DRLL-DR2133-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 15193 | 15193 | 6700
500135608 | CLB-MP-DRLL-DR2133-STRUCT-DMAST | Mast | 15193 | 15193 | 6700
500135607 | CLB-MP-DRLL-DR2133-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 15193 | 602 | 6700
500135606 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-SEATS | Operators Seat | 15193 | 15193 | 6700
500135605 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-AIRCN | Air Conditioning System | 15193 | 15193 | 6700
500135604 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 15193 | 15193 | 6700
500135603 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 15193 | 15193 | 6700
500135602 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 15193 | 15193 | 6700
500135601 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 15193 | 15193 | 6700
500135600 | CLB-MP-DRLL-DR2133-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 15193 | 15193 | 6700
500135599 | CLB-MP-DRLL-DR2133-STRUCT-CABIN | Operators Cabin | 15193 | 15193 | 6700
500135598 | CLB-MP-DRLL-DR2133-LUBSYS-DHTNK | DHD Reservoir | 15193 | 15193 | 6700
500135597 | CLB-MP-DRLL-DR2133-LUBSYS-DHDPP | DHD Oil Pump | 15193 | 15193 | 6700
500135596 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 15193 | 9653 | 6700
500135595 | CLB-MP-DRLL-DR2133-HYDSYS-PMPDG | Pump Drive Gearbox | 15193 | 13 | 6700
500135594 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 15193 | 1840 | 6700
500135593 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 15193 | 1922 | 6700
500135592 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 15193 | 1961 | 6700
500135591 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 15193 | 1915 | 6700
500135590 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 15193 | 1961 | 6700
500135589 | CLB-MP-DRLL-DR2133-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 15193 | 1961 | 6700
500135588 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 15193 | 15193 | 6700
500135587 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 15193 | 15193 | 6700
500135586 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 15193 | 15193 | 6700
500135585 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 15193 | 15193 | 6700
500135584 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 15193 | 15193 | 6700
500135583 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 15193 | 15193 | 6700
500135582 | CLB-MP-DRLL-DR2133-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 15193 | 15193 | 6700
500135581 | CLB-MP-DRLL-DR2133-HYDSYS-HDTNK | Tank Hydraulic | 15193 | 15193 | 6700
500135580 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 15193 | 961 | 6700
500135579 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 15193 | 961 | 6700
500135578 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 15193 | 15193 | 6700
500135577 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 15193 | 15193 | 6700
500135576 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 15193 | 15193 | 6700
500135575 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 15193 | 15193 | 6700
500135574 | CLB-MP-DRLL-DR2133-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 15193 | 15193 | 6700
500135573 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 15193 | 15193 | 6700
500135572 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 15193 | 9 | 6700
500135571 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 15193 | 3176 | 6700
500135570 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 15193 | 13 | 6700
500135569 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 15193 | 13 | 6700
500135568 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 15193 | 15193 | 6700
500135567 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 15193 | 13 | 6700
500135566 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 15193 | 2198 | 6700
500135565 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 15193 | 15193 | 6700
500135564 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 15193 | 1223 | 6700
500135563 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 15193 | 961 | 6700
500135562 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 15193 | 15193 | 6700
500135561 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 15193 | 15193 | 6700
500135560 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 15193 | 15193 | 6700
500135559 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 15193 | 15193 | 6700
500135558 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 15193 | 15193 | 6700
500135557 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 15193 | 15193 | 6700
500135556 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 15193 | 15193 | 6700
500135555 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 15193 | 15193 | 6700
500135554 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 15193 | 15193 | 6700
500135553 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 15193 | 15193 | 6700
500135552 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 15193 | 15193 | 6700
500135551 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 15193 | 15193 | 6700
500135550 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 15193 | 15193 | 6700
500135549 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 15193 | 15193 | 6700
500135548 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 15193 | 15193 | 6700
500135547 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 15193 | 15193 | 6700
500135546 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 15193 | 15193 | 6700
500135545 | CLB-MP-DRLL-DR2133-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 15193 | 15193 | 6700
500135544 | CLB-MP-DRLL-DR2133-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 15193 | 15193 | 6700
500135543 | CLB-MP-DRLL-DR2133-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 15193 | 15193 | 6700
500135542 | CLB-MP-DRLL-DR2133-GRSYST-RTTNK | Rod Thread Lube Reservoir | 15193 | 15193 | 6700
500135541 | CLB-MP-DRLL-DR2133-GRSYST-RTLPP | Rod Thread lube Pump | 15193 | 15193 | 6700
500135540 | CLB-MP-DRLL-DR2133-GRSYST-RTINJ | Rod Thread Grease Injector | 15193 | 15193 | 6700
500135539 | CLB-MP-DRLL-DR2133-GRSYST-GRTNK | Auto Lube Reservoir | 15193 | 15193 | 6700
500135538 | CLB-MP-DRLL-DR2133-GRSYST-GRINJ | Auto Lube Injectors | 15193 | 15193 | 6700
500135537 | CLB-MP-DRLL-DR2133-GRSYST-ALBPP | Auto lube Pump | 15193 | 15193 | 6700
500135536 | CLB-MP-DRLL-DR2133-FRSUPP | Fire Suppression System | 15193 | 15193 | 6700
500135535 | CLB-MP-DRLL-DR2133-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 15193 | 13 | 6700
500135534 | CLB-MP-DRLL-DR2133-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 15193 | 13 | 6700
500135533 | CLB-MP-DRLL-DR2133-ENGINE-INTEX-EXHST | Exhaust System Engine | 15193 | 15193 | 6700
500135532 | CLB-MP-DRLL-DR2133-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 15193 | 15193 | 6700
500135531 | CLB-MP-DRLL-DR2133-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 15193 | 15193 | 6700
500135530 | CLB-MP-DRLL-DR2133-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 15193 | 13 | 6700
500135529 | CLB-MP-DRLL-DR2133-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 15193 | 15193 | 6700
500135528 | CLB-MP-DRLL-DR2133-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 15193 | 13 | 6700
500135527 | CLB-MP-DRLL-DR2133-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 15193 | 15193 | 6700
500135526 | CLB-MP-DRLL-DR2133-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 15193 | 13 | 6700
500135525 | CLB-MP-DRLL-DR2133-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 15193 | 15193 | 6700
500135524 | CLB-MP-DRLL-DR2133-ENGINE-COSYS-WTRPP | Water Pump Engine | 15193 | 13 | 6700
500135523 | CLB-MP-DRLL-DR2133-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 15193 | 13 | 6700
500135522 | CLB-MP-DRLL-DR2133-ENGINE-COSYS-RADTR | Radiator Engine | 15193 | 15193 | 6700
500135521 | CLB-MP-DRLL-DR2133-ENGINE | Engine Assembly CAT C32 | 15193 | 13 | 6700
500135520 | CLB-MP-DRLL-DR2133-ELCTLV-START-STMRH | Starter Motor Engine Right | 15193 | 13 | 6700
500135519 | CLB-MP-DRLL-DR2133-ELCTLV-START-STMLH | Starter Motor Engine Left | 15193 | 13 | 6700
500135518 | CLB-MP-DRLL-DR2133-ELCTLV-HARNS | Wiring Harness | 15193 | 13 | 6700
500135517 | CLB-MP-DRLL-DR2133-ELCTLV-CHARG-BATTY | Batteries Engine | 15193 | 9047 | 6700
500135516 | CLB-MP-DRLL-DR2133-ELCTLV-CHARG-ALTER | Alternator 24V | 15193 | 13 | 6700
500135515 | CLB-MP-DRLL-DR2133-DSTSUP-WTNKP | Water Tank Primary | 15193 | 15193 | 6700
500135514 | CLB-MP-DRLL-DR2133-DSTSUP-WTRPP | Dynaset Water Pump | 15193 | 610 | 6700
500135513 | CLB-MP-DRLL-DR2133-DSTSUP-WSHPP | Pump Wash Down | 15193 | 4539 | 6700
500135512 | CLB-MP-DRLL-DR2133-DSTSUP-WSHMT | Engine Wash Down | 15193 | 15193 | 6700
500135511 | CLB-MP-DRLL-DR2133-COOLER-HDOCO | Hydraulic Oil Cooler Core | 15193 | 15193 | 6700
500135510 | CLB-MP-DRLL-DR2133-COOLER-COOCO | Compressor Oil Cooler Core | 15193 | 11678 | 6700
500135509 | CLB-MP-DRLL-DR2133-COOLER | Cooler Module Assembly | 15193 | 15193 | 6700
500135508 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 15193 | 13 | 6700
500135506 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 15193 | 12398 | 6700
500135505 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 15193 | 15193 | 6700
500135504 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR | Main Air Compressor | 15193 | 13 | 6700
500135503 | CLB-MP-DRLL-DR2133-ADSYST-HARNC | ADS Harnesses & Connectors | 15193 | 15193 | 6700
500135502 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 15193 | 15193 | 6700
500135501 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 15193 | 15193 | 6700
500135500 | CLB-MP-DRLL-DR2133-ADSYST-ADSPR | ADS HazTech | 15193 | 15193 | 6700
500135499 | CLB-MP-DRLL-DR2133-ADSYST-ADSPO | ADS Global Positioning System | 15193 | 15193 | 6700
500135498 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 15193 | 4538 | 6700
500135497 | CLB-MP-DRLL-DR2133-ADSYST-ADSIS | ADS Instrumentation & Sensors | 15193 | 15193 | 6700
500135496 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 15193 | 15193 | 6700
500135495 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 15193 | 15193 | 6700
500135494 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 15193 | 15193 | 6700
500135493 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 15193 | 15193 | 6700
500135492 | CLB-MP-DRLL-DR2133-ADSYST-ADSHW | ADS Hardware & Control System | 15193 | 15193 | 6700
500135491 | CLB-MP-DRLL-DR2133-ADSYST | ADS Autonomous Rig Control System | 15193 | 15193 | 6700
500135490 | CLB-MP-DRLL-DR2133 | CAT MD6310 Drill DR2133 | 15193 | 15193 | 6700
500146045 | CLB-MP-DRLL-DR2132-AIRSYS-ARTNK | DR2132 Receiver Tank | 15850 | 15850 | 6700
500140560 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 15827 | 13055 | 6700
500140559 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 15827 | 15827 | 6700
500138789 | CLB-MP-DRLL-DR2132-STRUCT-UNDER-EQUAL | Equaliser Bar | 15850 | 15850 | 6700
500138752 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKS | Water Tank Secondary | 15850 | 15850 | 6700
500135489 | CLB-MP-DRLL-DR2132-TRAVEL-TRKRH | Track Assembly Right Hand | 15850 | 15850 | 6700
500135488 | CLB-MP-DRLL-DR2132-TRAVEL-TRKLH | Track Assembly Left Hand | 15850 | 15850 | 6700
500135487 | CLB-MP-DRLL-DR2132-TRAVEL-TRBKR | Travel Brake Right Hand | 15850 | 15850 | 6700
500135486 | CLB-MP-DRLL-DR2132-TRAVEL-TRBKL | Travel Brake Left Hand | 15850 | 15850 | 6700
500135485 | CLB-MP-DRLL-DR2132-TRAVEL-SPRKR | Sprocket Right Hand | 15850 | 15850 | 6700
500135484 | CLB-MP-DRLL-DR2132-TRAVEL-SPRKL | Sprocket Left Hand | 15850 | 4205 | 6700
500135483 | CLB-MP-DRLL-DR2132-TRAVEL-FDRRH | Final Drive Right Hand | 15850 | 8291 | 6700
500135482 | CLB-MP-DRLL-DR2132-TRAVEL-FDRLH | Final Drive Left Hand | 15850 | 15850 | 6700
500135481 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 15850 | 13055 | 6700
500135480 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 15850 | 15850 | 6700
500135479 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 15850 | 15850 | 6700
500135478 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 15850 | 3585 | 6700
500135477 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 15850 | 15850 | 6700
500135476 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 15850 | 15850 | 6700
500135475 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 15850 | 15850 | 6700
500135474 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 15850 | 15850 | 6700
500135473 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 15850 | 15850 | 6700
500135472 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 15850 | 15850 | 6700
500135471 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 15850 | 15850 | 6700
500135470 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 15850 | 15850 | 6700
500135469 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 15850 | 15850 | 6700
500135468 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 15850 | 15850 | 6700
500135467 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 15850 | 15850 | 6700
500135466 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 15850 | 15850 | 6700
500135465 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 15850 | 15850 | 6700
500135464 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 15850 | 15850 | 6700
500135463 | CLB-MP-DRLL-DR2132-STRUCT-TKFRR | Track Frame-Cab Side | 15850 | 15850 | 6700
500135462 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 15850 | 9904 | 6700
500135461 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 15850 | 15850 | 6700
500135460 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 15850 | 15850 | 6700
500135459 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 15850 | 15850 | 6700
500135458 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 15850 | 15850 | 6700
500135457 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 15850 | 15850 | 6700
500135456 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 15850 | 15850 | 6700
500135455 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 15850 | 15850 | 6700
500135454 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 15850 | 15850 | 6700
500135453 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 15850 | 15850 | 6700
500135452 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 15850 | 15850 | 6700
500135451 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 15850 | 15850 | 6700
500135450 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 15850 | 15850 | 6700
500135449 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 15850 | 15850 | 6700
500135448 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 15850 | 15850 | 6700
500135447 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 15850 | 15850 | 6700
500135446 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 15850 | 15850 | 6700
500135445 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 15850 | 15850 | 6700
500135444 | CLB-MP-DRLL-DR2132-STRUCT-TKFRL | Track Frame-Non Cab Side | 15850 | 15850 | 6700
500135443 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 15850 | 15850 | 6700
500135442 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 15850 | 8895 | 6700
500135441 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 15850 | 15850 | 6700
500135440 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 15850 | 8895 | 6700
500135439 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 15850 | 8895 | 6700
500135438 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 15850 | 15850 | 6700
500135437 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 15850 | 15850 | 6700
500135436 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 15850 | 8895 | 6700
500135435 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 15850 | 8895 | 6700
500135434 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 15850 | 8895 | 6700
500135433 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 15850 | 15850 | 6700
500135432 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 15850 | 15850 | 6700
500135431 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 15850 | 15850 | 6700
500135430 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 15850 | 4917 | 6700
500135429 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 15850 | 4917 | 6700
500135428 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 15850 | 15850 | 6700
500135427 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 15850 | 15850 | 6700
500135426 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 15850 | 6250 | 6700
500135425 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 15850 | 6250 | 6700
500135424 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 15850 | 2252 | 6700
500135423 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-DSPAN | Deck Spanner | 15850 | 15850 | 6700
500135422 | CLB-MP-DRLL-DR2132-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 15850 | 15850 | 6700
500135421 | CLB-MP-DRLL-DR2132-STRUCT-DMAST | Mast | 15850 | 2252 | 6700
500135420 | CLB-MP-DRLL-DR2132-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 15850 | 1601 | 6700
500135419 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-SEATS | Operators Seat | 15850 | 15850 | 6700
500135418 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-AIRCN | Air Conditioning System | 15850 | 15850 | 6700
500135417 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 15850 | 15850 | 6700
500135416 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 15850 | 15850 | 6700
500135415 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 15850 | 15850 | 6700
500135414 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 15850 | 15850 | 6700
500135413 | CLB-MP-DRLL-DR2132-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 15850 | 15850 | 6700
500135412 | CLB-MP-DRLL-DR2132-STRUCT-CABIN | Operators Cabin | 15850 | 15850 | 6700
500135411 | CLB-MP-DRLL-DR2132-LUBSYS-DHTNK | DHD Reservoir | 15850 | 15850 | 6700
500135410 | CLB-MP-DRLL-DR2132-LUBSYS-DHDPP | DHD Oil Pump | 15850 | 15850 | 6700
500135409 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 15850 | 8503 | 6700
500135408 | CLB-MP-DRLL-DR2132-HYDSYS-PMPDG | Pump Drive Gearbox | 15850 | 15850 | 6700
500135407 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 15850 | 15850 | 6700
500135406 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 15850 | 15850 | 6700
500135405 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 15850 | 15850 | 6700
500135404 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 15850 | 15850 | 6700
500135403 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 15850 | 15850 | 6700
500135402 | CLB-MP-DRLL-DR2132-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 15850 | 15850 | 6700
500135401 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 15850 | 15850 | 6700
500135400 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 15850 | 15850 | 6700
500135399 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 15850 | 15850 | 6700
500135398 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 15850 | 15850 | 6700
500135397 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 15850 | 15850 | 6700
500135396 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 15850 | 15850 | 6700
500135395 | CLB-MP-DRLL-DR2132-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 15850 | 15850 | 6700
500135394 | CLB-MP-DRLL-DR2132-HYDSYS-HDTNK | Tank Hydraulic | 15850 | 15850 | 6700
500135393 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 15850 | 8910 | 6700
500135392 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 15850 | 8503 | 6700
500135391 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 15850 | 15850 | 6700
500135390 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 15850 | 15850 | 6700
500135389 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 15850 | 15850 | 6700
500135388 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 15850 | 8910 | 6700
500135387 | CLB-MP-DRLL-DR2132-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 15850 | 15850 | 6700
500135386 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 15850 | 15850 | 6700
500135385 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 15850 | 5572 | 6700
500135384 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 15850 | 1601 | 6700
500135383 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 15850 | 15850 | 6700
500135382 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 15850 | 15850 | 6700
500135381 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 15850 | 15850 | 6700
500135380 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 15850 | 7007 | 6700
500135379 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 15850 | 4205 | 6700
500135378 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 15850 | 735 | 6700
500135377 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 15850 | 2485 | 6700
500135376 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 15850 | 11347 | 6700
500135375 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 15850 | 5566 | 6700
500135374 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 15850 | 15850 | 6700
500135373 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 15850 | 15850 | 6700
500135372 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 15850 | 15850 | 6700
500135371 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 15850 | 15850 | 6700
500135370 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 15850 | 15850 | 6700
500135369 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 15850 | 15850 | 6700
500135368 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 15850 | 15850 | 6700
500135367 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 15850 | 15850 | 6700
500135366 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 15850 | 15850 | 6700
500135365 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 15850 | 15850 | 6700
500135364 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 15850 | 15850 | 6700
500135363 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 15850 | 15850 | 6700
500135362 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 15850 | 15850 | 6700
500135361 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 15850 | 15850 | 6700
500135360 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 15850 | 6250 | 6700
500135359 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 15850 | 15850 | 6700
500135358 | CLB-MP-DRLL-DR2132-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 15850 | 15850 | 6700
500135357 | CLB-MP-DRLL-DR2132-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 15850 | 15850 | 6700
500135356 | CLB-MP-DRLL-DR2132-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 15850 | 15850 | 6700
500135355 | CLB-MP-DRLL-DR2132-GRSYST-RTTNK | Rod Thread Lube Reservoir | 15850 | 15850 | 6700
500135354 | CLB-MP-DRLL-DR2132-GRSYST-RTLPP | Rod Thread lube Pump | 15850 | 5566 | 6700
500135353 | CLB-MP-DRLL-DR2132-GRSYST-RTINJ | Rod Thread Grease Injector | 15850 | 15850 | 6700
500135352 | CLB-MP-DRLL-DR2132-GRSYST-GRTNK | Auto Lube Reservoir | 15850 | 15850 | 6700
500135351 | CLB-MP-DRLL-DR2132-GRSYST-GRINJ | Auto Lube Injectors | 15850 | 15850 | 6700
500135350 | CLB-MP-DRLL-DR2132-GRSYST-ALBPP | Auto lube Pump | 15850 | 15850 | 6700
500135349 | CLB-MP-DRLL-DR2132-FRSUPP | Fire Suppression System | 15850 | 15850 | 6700
500135348 | CLB-MP-DRLL-DR2132-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 15850 | 7672 | 6700
500135347 | CLB-MP-DRLL-DR2132-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 15850 | 7672 | 6700
500135346 | CLB-MP-DRLL-DR2132-ENGINE-INTEX-EXHST | Exhaust System Engine | 15850 | 15850 | 6700
500135345 | CLB-MP-DRLL-DR2132-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 15850 | 15850 | 6700
500135344 | CLB-MP-DRLL-DR2132-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 15850 | 15850 | 6700
500135343 | CLB-MP-DRLL-DR2132-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 15850 | 7672 | 6700
500135342 | CLB-MP-DRLL-DR2132-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 15850 | 15850 | 6700
500135341 | CLB-MP-DRLL-DR2132-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 15850 | 15850 | 6700
500135340 | CLB-MP-DRLL-DR2132-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 15850 | 15850 | 6700
500135339 | CLB-MP-DRLL-DR2132-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 15850 | 7672 | 6700
500135338 | CLB-MP-DRLL-DR2132-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 15850 | 15850 | 6700
500135337 | CLB-MP-DRLL-DR2132-ENGINE-COSYS-WTRPP | Water Pump Engine | 15850 | 7672 | 6700
500135336 | CLB-MP-DRLL-DR2132-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 15850 | 7672 | 6700
500135335 | CLB-MP-DRLL-DR2132-ENGINE-COSYS-RADTR | Radiator Engine | 15850 | 15850 | 6700
500135334 | CLB-MP-DRLL-DR2132-ENGINE | Engine Assembly CAT C32 | 15850 | 15850 | 6700
500135333 | CLB-MP-DRLL-DR2132-ELCTLV-START-STMRH | Starter Motor Engine Right | 15850 | 1601 | 6700
500135332 | CLB-MP-DRLL-DR2132-ELCTLV-START-STMLH | Starter Motor Engine Left | 15850 | 1601 | 6700
500135331 | CLB-MP-DRLL-DR2132-ELCTLV-HARNS | Wiring Harness | 15850 | 15850 | 6700
500135330 | CLB-MP-DRLL-DR2132-ELCTLV-CHARG-BATTY | Batteries Engine | 15850 | 1601 | 6700
500135329 | CLB-MP-DRLL-DR2132-ELCTLV-CHARG-ALTER | Alternator 24V | 15850 | 7672 | 6700
500135328 | CLB-MP-DRLL-DR2132-DSTSUP-WTNKP | Water Tank Primary | 15850 | 15850 | 6700
500135327 | CLB-MP-DRLL-DR2132-DSTSUP-WTRPP | Dynaset Water Pump | 15850 | 7007 | 6700
500135326 | CLB-MP-DRLL-DR2132-DSTSUP-WSHPP | Pump Wash Down | 15850 | 2962 | 6700
500135325 | CLB-MP-DRLL-DR2132-DSTSUP-WSHMT | Engine Wash Down | 15850 | 15850 | 6700
500135324 | CLB-MP-DRLL-DR2132-COOLER-HDOCO | Hydraulic Oil Cooler Core | 15850 | 15850 | 6700
500135323 | CLB-MP-DRLL-DR2132-COOLER-COOCO | Compressor Oil Cooler Core | 15850 | 15850 | 6700
500135322 | CLB-MP-DRLL-DR2132-COOLER | Cooler Module Assembly | 15850 | 15850 | 6700
500135321 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 15850 | 6250 | 6700
500135319 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 15850 | 8291 | 6700
500135318 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 15850 | 9731 | 6700
500135317 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR | Main Air Compressor | 15850 | 6250 | 6700
500135316 | CLB-MP-DRLL-DR2132-ADSYST-HARNC | ADS Harnesses & Connectors | 15850 | 15850 | 6700
500135315 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 15850 | 10602 | 6700
500135314 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 15850 | 15850 | 6700
500135313 | CLB-MP-DRLL-DR2132-ADSYST-ADSPR | ADS HazTech | 15850 | 15850 | 6700
500135312 | CLB-MP-DRLL-DR2132-ADSYST-ADSPO | ADS Global Positioning System | 15850 | 15850 | 6700
500135311 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 15850 | 15850 | 6700
500135310 | CLB-MP-DRLL-DR2132-ADSYST-ADSIS | ADS Instrumentation & Sensors | 15850 | 15850 | 6700
500135309 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 15850 | 15850 | 6700
500135308 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 15850 | 15850 | 6700
500135307 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 15850 | 15850 | 6700
500135306 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 15850 | 15850 | 6700
500135305 | CLB-MP-DRLL-DR2132-ADSYST-ADSHW | ADS Hardware & Control System | 15850 | 15850 | 6700
500135304 | CLB-MP-DRLL-DR2132-ADSYST | ADS Autonomous Rig Control System | 15850 | 15850 | 6700
500135303 | CLB-MP-DRLL-DR2132 | CAT MD6310 Drill DR2132 | 15850 | 15850 | 6700
500146044 | CLB-MP-DRLL-DR2131-AIRSYS-ARTNK | DR2131 Receiver Tank | 16896 | 3896 | 6700
500140558 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 16830 | 16830 | 6700
500140557 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 16830 | 12446 | 6700
500138788 | CLB-MP-DRLL-DR2131-STRUCT-UNDER-EQUAL | Equaliser Bar | 16830 | 16830 | 6700
500138751 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKS | Water Tank Secondary | 16830 | 16830 | 6700
500135302 | CLB-MP-DRLL-DR2131-TRAVEL-TRKRH | Track Assembly Right Hand | 16830 | 16830 | 6700
500135301 | CLB-MP-DRLL-DR2131-TRAVEL-TRKLH | Track Assembly Left Hand | 16830 | 16830 | 6700
500135300 | CLB-MP-DRLL-DR2131-TRAVEL-TRBKR | Travel Brake Right Hand | 16830 | 16830 | 6700
500135299 | CLB-MP-DRLL-DR2131-TRAVEL-TRBKL | Travel Brake Left Hand | 16830 | 16830 | 6700
500135298 | CLB-MP-DRLL-DR2131-TRAVEL-SPRKR | Sprocket Right Hand | 16830 | 6761 | 6700
500135297 | CLB-MP-DRLL-DR2131-TRAVEL-SPRKL | Sprocket Left Hand | 16830 | 1512 | 6700
500135296 | CLB-MP-DRLL-DR2131-TRAVEL-FDRRH | Final Drive Right Hand | 16830 | 13448 | 6700
500135295 | CLB-MP-DRLL-DR2131-TRAVEL-FDRLH | Final Drive Left Hand | 16830 | 1512 | 6700
500135294 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 16830 | 12446 | 6700
500135293 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 16830 | 12446 | 6700
500135292 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 16830 | 16830 | 6700
500135291 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 16830 | 16830 | 6700
500135290 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 16830 | 16830 | 6700
500135289 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 16830 | 16830 | 6700
500135288 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 16830 | 16830 | 6700
500135287 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 16830 | 16830 | 6700
500135286 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 16830 | 16830 | 6700
500135285 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 16830 | 16830 | 6700
500135284 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 16830 | 16830 | 6700
500135283 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 16830 | 16830 | 6700
500135282 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 16830 | 16830 | 6700
500135281 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 16830 | 16830 | 6700
500135280 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 16830 | 16830 | 6700
500135279 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 16830 | 16830 | 6700
500135278 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 16830 | 16830 | 6700
500135277 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 16830 | 16830 | 6700
500135276 | CLB-MP-DRLL-DR2131-STRUCT-TKFRR | Track Frame-Cab Side | 16830 | 16830 | 6700
500135275 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 16830 | 12446 | 6700
500135274 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 16830 | 16830 | 6700
500135273 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 16830 | 16830 | 6700
500135272 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 16830 | 16830 | 6700
500135271 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 16830 | 16830 | 6700
500135270 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 16830 | 16830 | 6700
500135269 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 16830 | 16830 | 6700
500135268 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 16830 | 16830 | 6700
500135267 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 16830 | 16830 | 6700
500135266 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 16830 | 16830 | 6700
500135265 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 16830 | 16830 | 6700
500135264 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 16830 | 16830 | 6700
500135263 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 16830 | 12446 | 6700
500135262 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 16830 | 16830 | 6700
500135261 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 16830 | 16830 | 6700
500135260 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 16830 | 16830 | 6700
500135259 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 16830 | 16830 | 6700
500135258 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 16830 | 16830 | 6700
500135257 | CLB-MP-DRLL-DR2131-STRUCT-TKFRL | Track Frame-Non Cab Side | 16830 | 16830 | 6700
500135256 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 16830 | 9883 | 6700
500135255 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 16830 | 9883 | 6700
500135254 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 16830 | 9883 | 6700
500135253 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 16830 | 9883 | 6700
500135252 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 16830 | 9883 | 6700
500135251 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 16830 | 9883 | 6700
500135250 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 16830 | 9883 | 6700
500135249 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 16830 | 9883 | 6700
500135248 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 16830 | 9883 | 6700
500135247 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 16830 | 9883 | 6700
500135246 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 16830 | 9883 | 6700
500135245 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 16830 | 9883 | 6700
500135244 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 16830 | 16830 | 6700
500135243 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 16830 | 1354 | 6700
500135242 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 16830 | 1354 | 6700
500135241 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 16830 | 16830 | 6700
500135240 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 16830 | 16830 | 6700
500135239 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 16830 | 1354 | 6700
500135238 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 16830 | 1354 | 6700
500135237 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 16830 | 2470 | 6700
500135236 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-DSPAN | Deck Spanner | 16830 | 16830 | 6700
500135235 | CLB-MP-DRLL-DR2131-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 16830 | 16830 | 6700
500135234 | CLB-MP-DRLL-DR2131-STRUCT-DMAST | Mast | 16830 | 16830 | 6700
500135233 | CLB-MP-DRLL-DR2131-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 16830 | 2470 | 6700
500135232 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-SEATS | Operators Seat | 16830 | 10291 | 6700
500135231 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-AIRCN | Air Conditioning System | 16830 | 16830 | 6700
500135230 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 16830 | 16830 | 6700
500135229 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 16830 | 16830 | 6700
500135228 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 16830 | 16830 | 6700
500135227 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 16830 | 7196 | 6700
500135226 | CLB-MP-DRLL-DR2131-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 16830 | 16830 | 6700
500135225 | CLB-MP-DRLL-DR2131-STRUCT-CABIN | Operators Cabin | 16830 | 16830 | 6700
500135224 | CLB-MP-DRLL-DR2131-LUBSYS-DHTNK | DHD Reservoir | 16830 | 16830 | 6700
500135223 | CLB-MP-DRLL-DR2131-LUBSYS-DHDPP | DHD Oil Pump | 16830 | 16830 | 6700
500135222 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 16830 | 5228 | 6700
500135221 | CLB-MP-DRLL-DR2131-HYDSYS-PMPDG | Pump Drive Gearbox | 16830 | 586 | 6700
500135220 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 16830 | 586 | 6700
500135219 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 16830 | 586 | 6700
500135218 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 16830 | 3896 | 6700
500135217 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 16830 | 16830 | 6700
500135216 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 16830 | 586 | 6700
500135215 | CLB-MP-DRLL-DR2131-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 16830 | 586 | 6700
500135214 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 16830 | 16830 | 6700
500135213 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 16830 | 16830 | 6700
500135212 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 16830 | 16830 | 6700
500135211 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 16830 | 16830 | 6700
500135210 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 16830 | 16830 | 6700
500135209 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 16830 | 16830 | 6700
500135208 | CLB-MP-DRLL-DR2131-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 16830 | 16830 | 6700
500135207 | CLB-MP-DRLL-DR2131-HYDSYS-HDTNK | Tank Hydraulic | 16830 | 16830 | 6700
500135206 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 16830 | 2470 | 6700
500135205 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 16830 | 1920 | 6700
500135204 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 16830 | 16830 | 6700
500135203 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 16830 | 16830 | 6700
500135202 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 16830 | 16830 | 6700
500135201 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 16830 | 16830 | 6700
500135200 | CLB-MP-DRLL-DR2131-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 16830 | 7196 | 6700
500135199 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 16830 | 16830 | 6700
500135198 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 16830 | 16830 | 6700
500135197 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 16830 | 16830 | 6700
500135196 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 16830 | 16830 | 6700
500135195 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 16830 | 16830 | 6700
500135194 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 16830 | 16830 | 6700
500135193 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 16830 | 16830 | 6700
500135192 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 16830 | 4546 | 6700
500135191 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 16830 | 1171 | 6700
500135190 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 16830 | 9883 | 6700
500135189 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 16830 | 16830 | 6700
500135188 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 16830 | 7748 | 6700
500135187 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 16830 | 16830 | 6700
500135186 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 16830 | 16830 | 6700
500135185 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 16830 | 16830 | 6700
500135184 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 16830 | 16830 | 6700
500135183 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 16830 | 16830 | 6700
500135182 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 16830 | 16830 | 6700
500135181 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 16830 | 16830 | 6700
500135180 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 16830 | 16830 | 6700
500135179 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 16830 | 16830 | 6700
500135178 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 16830 | 16830 | 6700
500135177 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 16830 | 16830 | 6700
500135176 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 16830 | 16830 | 6700
500135175 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 16830 | 16830 | 6700
500135174 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 16830 | 16830 | 6700
500135173 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 16830 | 2067 | 6700
500135172 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 16830 | 6761 | 6700
500135171 | CLB-MP-DRLL-DR2131-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 16830 | 6761 | 6700
500135170 | CLB-MP-DRLL-DR2131-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 16830 | 10291 | 6700
500135169 | CLB-MP-DRLL-DR2131-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 16830 | 10291 | 6700
500135168 | CLB-MP-DRLL-DR2131-GRSYST-RTTNK | Rod Thread Lube Reservoir | 16830 | 16830 | 6700
500135167 | CLB-MP-DRLL-DR2131-GRSYST-RTLPP | Rod Thread lube Pump | 16830 | 16830 | 6700
500135166 | CLB-MP-DRLL-DR2131-GRSYST-RTINJ | Rod Thread Grease Injector | 16830 | 16830 | 6700
500135165 | CLB-MP-DRLL-DR2131-GRSYST-GRTNK | Auto Lube Reservoir | 16830 | 16830 | 6700
500135164 | CLB-MP-DRLL-DR2131-GRSYST-GRINJ | Auto Lube Injectors | 16830 | 16830 | 6700
500135163 | CLB-MP-DRLL-DR2131-GRSYST-ALBPP | Auto lube Pump | 16830 | 16830 | 6700
500135162 | CLB-MP-DRLL-DR2131-FRSUPP | Fire Suppression System | 16830 | 16830 | 6700
500135161 | CLB-MP-DRLL-DR2131-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 16830 | 586 | 6700
500135160 | CLB-MP-DRLL-DR2131-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 16830 | 586 | 6700
500135159 | CLB-MP-DRLL-DR2131-ENGINE-INTEX-EXHST | Exhaust System Engine | 16830 | 16830 | 6700
500135158 | CLB-MP-DRLL-DR2131-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 16830 | 16830 | 6700
500135157 | CLB-MP-DRLL-DR2131-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 16830 | 16830 | 6700
500135156 | CLB-MP-DRLL-DR2131-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 16830 | 586 | 6700
500135155 | CLB-MP-DRLL-DR2131-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 16830 | 16830 | 6700
500135154 | CLB-MP-DRLL-DR2131-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 16830 | 586 | 6700
500135153 | CLB-MP-DRLL-DR2131-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 16830 | 16830 | 6700
500135152 | CLB-MP-DRLL-DR2131-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 16830 | 586 | 6700
500135151 | CLB-MP-DRLL-DR2131-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 16830 | 16830 | 6700
500135150 | CLB-MP-DRLL-DR2131-ENGINE-COSYS-WTRPP | Water Pump Engine | 16830 | 586 | 6700
500135149 | CLB-MP-DRLL-DR2131-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 16830 | 586 | 6700
500135148 | CLB-MP-DRLL-DR2131-ENGINE-COSYS-RADTR | Radiator Engine | 16830 | 16830 | 6700
500135147 | CLB-MP-DRLL-DR2131-ENGINE | Engine Assembly CAT C32 | 16830 | 586 | 6700
500135146 | CLB-MP-DRLL-DR2131-ELCTLV-START-STMRH | Starter Motor Engine Right | 16830 | 586 | 6700
500135145 | CLB-MP-DRLL-DR2131-ELCTLV-START-STMLH | Starter Motor Engine Left | 16830 | 586 | 6700
500135144 | CLB-MP-DRLL-DR2131-ELCTLV-HARNS | Wiring Harness | 16830 | 16830 | 6700
500135143 | CLB-MP-DRLL-DR2131-ELCTLV-CHARG-BATTY | Batteries Engine | 16830 | 1328 | 6700
500135142 | CLB-MP-DRLL-DR2131-ELCTLV-CHARG-ALTER | Alternator 24V | 16830 | 586 | 6700
500135141 | CLB-MP-DRLL-DR2131-DSTSUP-WTNKP | Water Tank Primary | 16830 | 16830 | 6700
500135140 | CLB-MP-DRLL-DR2131-DSTSUP-WTRPP | Dynaset Water Pump | 16830 | 586 | 6700
500135139 | CLB-MP-DRLL-DR2131-DSTSUP-WSHPP | Pump Wash Down | 16830 | 16830 | 6700
500135138 | CLB-MP-DRLL-DR2131-DSTSUP-WSHMT | Engine Wash Down | 16830 | 16830 | 6700
500135137 | CLB-MP-DRLL-DR2131-COOLER-HDOCO | Hydraulic Oil Cooler Core | 16830 | 16830 | 6700
500135136 | CLB-MP-DRLL-DR2131-COOLER-COOCO | Compressor Oil Cooler Core | 16830 | 16830 | 6700
500135135 | CLB-MP-DRLL-DR2131-COOLER | Cooler Module Assembly | 16830 | 16830 | 6700
500135134 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 16830 | 586 | 6700
500135132 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 16830 | 2105 | 6700
500135131 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 16830 | 5817 | 6700
500135130 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR | Main Air Compressor | 16830 | 11673 | 6700
500135129 | CLB-MP-DRLL-DR2131-ADSYST-HARNC | ADS Harnesses & Connectors | 16830 | 16830 | 6700
500135128 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 16830 | 11072 | 6700
500135127 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 16830 | 5228 | 6700
500135126 | CLB-MP-DRLL-DR2131-ADSYST-ADSPR | ADS HazTech | 16830 | 16830 | 6700
500135125 | CLB-MP-DRLL-DR2131-ADSYST-ADSPO | ADS Global Positioning System | 16830 | 16830 | 6700
500135124 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 16830 | 5228 | 6700
500135123 | CLB-MP-DRLL-DR2131-ADSYST-ADSIS | ADS Instrumentation & Sensors | 16830 | 16830 | 6700
500135122 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 16830 | 16830 | 6700
500135121 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 16830 | 16830 | 6700
500135120 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 16830 | 16830 | 6700
500135119 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 16830 | 16830 | 6700
500135118 | CLB-MP-DRLL-DR2131-ADSYST-ADSHW | ADS Hardware & Control System | 16830 | 16830 | 6700
500135117 | CLB-MP-DRLL-DR2131-ADSYST | ADS Autonomous Rig Control System | 16830 | 16830 | 6700
500135116 | CLB-MP-DRLL-DR2131 | CAT MD6310 Drill DR2131 | 16830 | 16830 | 6700
500146043 | CLB-MP-DRLL-DR2130-AIRSYS-ARTNK | DR2130 Receiver Tank | 17370 | 17370 | 6700
500140556 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF14 | Roller Load Pos 14 Single Flange CS | 17309 | 11323 | 6700
500140555 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF14 | Roller Load Pos 14 Single Flange NCS | 17309 | 17309 | 6700
500138787 | CLB-MP-DRLL-DR2130-STRUCT-UNDER-EQUAL | Equaliser Bar | 17285 | 17285 | 6700
500138750 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKS | Water Tank Secondary | 17309 | 17309 | 6700
500134026 | CLB-MP-DRLL-DR2130-TRAVEL-TRKRH | Track Assembly Right Hand | 17309 | 17309 | 6700
500134025 | CLB-MP-DRLL-DR2130-TRAVEL-TRKLH | Track Assembly Left Hand | 17309 | 17309 | 6700
500134024 | CLB-MP-DRLL-DR2130-TRAVEL-TRBKR | Travel Brake Right Hand | 17309 | 17309 | 6700
500134023 | CLB-MP-DRLL-DR2130-TRAVEL-TRBKL | Travel Brake Left Hand | 17309 | 17309 | 6700
500134022 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKR | Sprocket Right Hand | 17309 | 10248 | 6700
500134021 | CLB-MP-DRLL-DR2130-TRAVEL-SPRKL | Sprocket Left Hand | 17309 | 10248 | 6700
500134020 | CLB-MP-DRLL-DR2130-TRAVEL-FDRRH | Final Drive Right Hand | 17309 | 17309 | 6700
500134019 | CLB-MP-DRLL-DR2130-TRAVEL-FDRLH | Final Drive Left Hand | 17309 | 17309 | 6700
500134018 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 17309 | 17309 | 6700
500134017 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 17309 | 9651 | 6700
500134016 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 17309 | 17309 | 6700
500134015 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 17309 | 17309 | 6700
500134014 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 17309 | 5537 | 6700
500134013 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 17309 | 17309 | 6700
500134012 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 17309 | 17309 | 6700
500134011 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 17309 | 17309 | 6700
500134010 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 17309 | 17309 | 6700
500134009 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 17309 | 17309 | 6700
500134008 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 17309 | 9651 | 6700
500134007 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 17309 | 17309 | 6700
500134006 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 17309 | 17309 | 6700
500134005 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 17309 | 17309 | 6700
500134004 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 17309 | 17309 | 6700
500134003 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 17309 | 17309 | 6700
500134002 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 17309 | 17309 | 6700
500134001 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 17309 | 17309 | 6700
500134000 | CLB-MP-DRLL-DR2130-STRUCT-TKFRR | Track Frame-Cab Side | 17309 | 17309 | 6700
500133999 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 17309 | 17309 | 6700
500133998 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 17309 | 17309 | 6700
500133997 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 17309 | 17309 | 6700
500133996 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 17309 | 17309 | 6700
500133995 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 17309 | 17309 | 6700
500133994 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 17309 | 17309 | 6700
500133993 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 17309 | 17309 | 6700
500133992 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 17309 | 17309 | 6700
500133991 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 17309 | 17309 | 6700
500133990 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 17309 | 17309 | 6700
500133989 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 17309 | 17309 | 6700
500133988 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 17309 | 17309 | 6700
500133987 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 17309 | 17309 | 6700
500133986 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 17309 | 17309 | 6700
500133985 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 17309 | 17309 | 6700
500133984 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 17309 | 17309 | 6700
500133983 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 17309 | 17309 | 6700
500133982 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 17309 | 17309 | 6700
500133981 | CLB-MP-DRLL-DR2130-STRUCT-TKFRL | Track Frame-Non Cab Side | 17309 | 17309 | 6700
500133980 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 17309 | 17309 | 6700
500133979 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 17309 | 17309 | 6700
500133978 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 17309 | 17309 | 6700
500133977 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 17309 | 17309 | 6700
500133976 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 17309 | 17309 | 6700
500133975 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 17309 | 17309 | 6700
500133974 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 17309 | 17309 | 6700
500133973 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 17309 | 17309 | 6700
500133972 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 17309 | 17309 | 6700
500133971 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 17309 | 17309 | 6700
500133970 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 17309 | 17309 | 6700
500133969 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 17309 | 17309 | 6700
500133968 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 17309 | 17309 | 6700
500133967 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 17309 | 135 | 6700
500133966 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 17309 | 135 | 6700
500133965 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 17309 | 17309 | 6700
500133964 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 17309 | 17309 | 6700
500133963 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 17309 | 3262 | 6700
500133962 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 17309 | 3262 | 6700
500133961 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 17309 | 2411 | 6700
500133960 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-DSPAN | Deck Spanner | 17309 | 17309 | 6700
500133959 | CLB-MP-DRLL-DR2130-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 17309 | 17309 | 6700
500133958 | CLB-MP-DRLL-DR2130-STRUCT-DMAST | Mast | 17309 | 17309 | 6700
500133957 | CLB-MP-DRLL-DR2130-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 17309 | 17309 | 6700
500133956 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-SEATS | Operators Seat | 17309 | 14596 | 6700
500133955 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-AIRCN | Air Conditioning System | 17309 | 6755 | 6700
500133954 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 17309 | 17309 | 6700
500133953 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 17309 | 17309 | 6700
500133952 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 17309 | 17309 | 6700
500133951 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 17309 | 17309 | 6700
500133950 | CLB-MP-DRLL-DR2130-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 17309 | 17309 | 6700
500133949 | CLB-MP-DRLL-DR2130-STRUCT-CABIN | Operators Cabin | 17309 | 17309 | 6700
500133948 | CLB-MP-DRLL-DR2130-LUBSYS-DHTNK | DHD Reservoir | 17309 | 17309 | 6700
500133947 | CLB-MP-DRLL-DR2130-LUBSYS-DHDPP | DHD Oil Pump | 17309 | 17309 | 6700
500133946 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 17309 | 741 | 6700
500133945 | CLB-MP-DRLL-DR2130-HYDSYS-PMPDG | Pump Drive Gearbox | 17309 | 5941 | 6700
500133944 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 17309 | 5872 | 6700
500133943 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 17309 | 5872 | 6700
500133942 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 17309 | 6154 | 6700
500133941 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 17309 | 5872 | 6700
500133940 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 17309 | 741 | 6700
500133939 | CLB-MP-DRLL-DR2130-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 17309 | 741 | 6700
500133938 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 17309 | 17309 | 6700
500133937 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 17309 | 17309 | 6700
500133936 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 17309 | 17309 | 6700
500133935 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 17309 | 17309 | 6700
500133934 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 17309 | 17309 | 6700
500133933 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 17309 | 17309 | 6700
500133932 | CLB-MP-DRLL-DR2130-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 17309 | 17309 | 6700
500133931 | CLB-MP-DRLL-DR2130-HYDSYS-HDTNK | Tank Hydraulic | 17309 | 17309 | 6700
500133930 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 17309 | 5309 | 6700
500133929 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 17309 | 5309 | 6700
500133928 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 17309 | 17309 | 6700
500133927 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 17309 | 17309 | 6700
500133926 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 17309 | 17309 | 6700
500133925 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 17309 | 9651 | 6700
500133924 | CLB-MP-DRLL-DR2130-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 17309 | 17309 | 6700
500133923 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 17309 | 17309 | 6700
500133922 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 17309 | 10627 | 6700
500133921 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 17309 | 11323 | 6700
500133920 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 17309 | 2411 | 6700
500133919 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 17309 | 2411 | 6700
500133918 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 17309 | 17309 | 6700
500133917 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 17309 | 1426 | 6700
500133916 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 17309 | 9936 | 6700
500133915 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 17309 | 747 | 6700
500133914 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 17309 | 3262 | 6700
500133913 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 17309 | 17309 | 6700
500133912 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 17309 | 9388 | 6700
500133911 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 17309 | 17309 | 6700
500133910 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 17309 | 17309 | 6700
500133909 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 17309 | 17309 | 6700
500133908 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 17309 | 17309 | 6700
500133907 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 17309 | 17309 | 6700
500133906 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 17309 | 17309 | 6700
500133905 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 17309 | 17309 | 6700
500133904 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 17309 | 17309 | 6700
500133903 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 17309 | 17309 | 6700
500133902 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 17309 | 17309 | 6700
500133901 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 17309 | 17309 | 6700
500133900 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 17309 | 17309 | 6700
500133899 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 17309 | 17309 | 6700
500133898 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 17309 | 17309 | 6700
500133897 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 17309 | 17309 | 6700
500133896 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 17309 | 2411 | 6700
500133895 | CLB-MP-DRLL-DR2130-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 17309 | 17309 | 6700
500133894 | CLB-MP-DRLL-DR2130-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 17309 | 17309 | 6700
500133893 | CLB-MP-DRLL-DR2130-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 17309 | 11851 | 6700
500133892 | CLB-MP-DRLL-DR2130-GRSYST-RTTNK | Rod Thread Lube Reservoir | 17309 | 17309 | 6700
500133891 | CLB-MP-DRLL-DR2130-GRSYST-RTLPP | Rod Thread lube Pump | 17309 | 17309 | 6700
500133890 | CLB-MP-DRLL-DR2130-GRSYST-RTINJ | Rod Thread Grease Injector | 17309 | 17309 | 6700
500133889 | CLB-MP-DRLL-DR2130-GRSYST-GRTNK | Auto Lube Reservoir | 17309 | 17309 | 6700
500133888 | CLB-MP-DRLL-DR2130-GRSYST-GRINJ | Auto Lube Injectors | 17309 | 17309 | 6700
500133887 | CLB-MP-DRLL-DR2130-GRSYST-ALBPP | Auto lube Pump | 17309 | 8825 | 6700
500133886 | CLB-MP-DRLL-DR2130-FRSUPP | Fire Suppression System | 17309 | 17309 | 6700
500133885 | CLB-MP-DRLL-DR2130-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 17309 | 741 | 6700
500133884 | CLB-MP-DRLL-DR2130-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 17309 | 741 | 6700
500133883 | CLB-MP-DRLL-DR2130-ENGINE-INTEX-EXHST | Exhaust System Engine | 17309 | 17309 | 6700
500133882 | CLB-MP-DRLL-DR2130-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 17309 | 17309 | 6700
500133881 | CLB-MP-DRLL-DR2130-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 17309 | 17309 | 6700
500133880 | CLB-MP-DRLL-DR2130-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 17309 | 741 | 6700
500133879 | CLB-MP-DRLL-DR2130-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 17309 | 17309 | 6700
500133878 | CLB-MP-DRLL-DR2130-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 17309 | 741 | 6700
500133877 | CLB-MP-DRLL-DR2130-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 17309 | 17309 | 6700
500133876 | CLB-MP-DRLL-DR2130-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 17309 | 741 | 6700
500133875 | CLB-MP-DRLL-DR2130-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 17309 | 17309 | 6700
500133874 | CLB-MP-DRLL-DR2130-ENGINE-COSYS-WTRPP | Water Pump Engine | 17309 | 741 | 6700
500133873 | CLB-MP-DRLL-DR2130-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 17309 | 741 | 6700
500133872 | CLB-MP-DRLL-DR2130-ENGINE-COSYS-RADTR | Radiator Engine | 17309 | 17309 | 6700
500133871 | CLB-MP-DRLL-DR2130-ENGINE | Engine Assembly CAT C32 | 17309 | 741 | 6700
500133870 | CLB-MP-DRLL-DR2130-ELCTLV-START-STMRH | Starter Motor Engine Right | 17309 | 40 | 6700
500133869 | CLB-MP-DRLL-DR2130-ELCTLV-START-STMLH | Starter Motor Engine Left | 17309 | 40 | 6700
500133868 | CLB-MP-DRLL-DR2130-ELCTLV-HARNS | Wiring Harness | 17309 | 17309 | 6700
500133867 | CLB-MP-DRLL-DR2130-ELCTLV-CHARG-BATTY | Batteries Engine | 17309 | 1426 | 6700
500133866 | CLB-MP-DRLL-DR2130-ELCTLV-CHARG-ALTER | Alternator 24V | 17309 | 741 | 6700
500133865 | CLB-MP-DRLL-DR2130-DSTSUP-WTNKP | Water Tank Primary | 17309 | 17309 | 6700
500133864 | CLB-MP-DRLL-DR2130-DSTSUP-WTRPP | Dynaset Water Pump | 17309 | 6755 | 6700
500133863 | CLB-MP-DRLL-DR2130-DSTSUP-WSHPP | Pump Wash Down | 17309 | 17309 | 6700
500133862 | CLB-MP-DRLL-DR2130-DSTSUP-WSHMT | Engine Wash Down | 17309 | 12561 | 6700
500133861 | CLB-MP-DRLL-DR2130-COOLER-HDOCO | Hydraulic Oil Cooler Core | 17309 | 17309 | 6700
500133860 | CLB-MP-DRLL-DR2130-COOLER-COOCO | Compressor Oil Cooler Core | 17309 | 17309 | 6700
500133859 | CLB-MP-DRLL-DR2130-COOLER | Cooler Module Assembly | 17309 | 17309 | 6700
500133858 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 17309 | 1426 | 6700
500133856 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 17309 | 17309 | 6700
500133855 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 17309 | 11540 | 6700
500133854 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR | Main Air Compressor | 17309 | 1426 | 6700
500133853 | CLB-MP-DRLL-DR2130-ADSYST-HARNC | ADS Harnesses & Connectors | 17309 | 17309 | 6700
500133852 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 17309 | 10248 | 6700
500133851 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 17309 | 17309 | 6700
500133850 | CLB-MP-DRLL-DR2130-ADSYST-ADSPR | ADS HazTech | 17309 | 17309 | 6700
500133849 | CLB-MP-DRLL-DR2130-ADSYST-ADSPO | ADS Global Positioning System | 17309 | 17309 | 6700
500133848 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 17309 | 17309 | 6700
500133847 | CLB-MP-DRLL-DR2130-ADSYST-ADSIS | ADS Instrumentation & Sensors | 17309 | 17309 | 6700
500133846 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 17309 | 17309 | 6700
500133845 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 17309 | 17309 | 6700
500133844 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 17309 | 17309 | 6700
500133843 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 17309 | 17309 | 6700
500133832 | CLB-MP-DRLL-DR2130-ADSYST-ADSHW | ADS Hardware & Control System | 17309 | 17309 | 6700
500133831 | CLB-MP-DRLL-DR2130-ADSYST | ADS Autonomous Rig Control System | 17309 | 17309 | 6700
500133830 | CLB-MP-DRLL-DR2130 | CAT MD6310 Drill DR2130 | 17309 | 17309 | 6700
500146042 | CLB-MP-DRLL-DR2126-AIRSYS-ARTNK | DR2126 Receiver Tank | 14849 | 2463 | 6700
500138785 | CLB-MP-DRLL-DR2126-STRUCT-UNDER-EQUAL | Equaliser Bar | 14763 | 14763 | 6700
500138748 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKS | Water Tank Secondary | 14786 | 14786 | 6700
500132530 | CLB-MP-DRLL-DR2126-ADSYST-HARNC | ADS Harnesses & Connectors | 14786 | 14786 | 6700
500132529 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-LIDAR | ADS LiDAR System | 14786 | 14786 | 6700
500132528 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 14786 | 14786 | 6700
500132527 | CLB-MP-DRLL-DR2126-ADSYST-ADSPR | ADS HazTech | 14786 | 14786 | 6700
500132526 | CLB-MP-DRLL-DR2126-ADSYST-ADSPO | ADS Global Positioning System | 14786 | 14786 | 6700
500132525 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS-DSVSN | ADS Drill string Vibration Sensor | 14786 | 2463 | 6700
500132524 | CLB-MP-DRLL-DR2126-ADSYST-ADSIS | ADS Instrumentation & Sensors | 14786 | 14786 | 6700
500132523 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 14786 | 14786 | 6700
500132522 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 14786 | 14786 | 6700
500132521 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 14786 | 14786 | 6700
500132520 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 14786 | 14786 | 6700
500132519 | CLB-MP-DRLL-DR2126-ADSYST-ADSHW | ADS Hardware & Control System | 14786 | 14786 | 6700
500132388 | CLB-MP-DRLL-DR2126-ELCTLV-HARNS | Wiring Harness | 14786 | 14786 | 6700
500127936 | CLB-MP-DRLL-DR2126-TRAVEL-TRKRH | Track Assembly Right Hand | 14786 | 14786 | 6700
500127935 | CLB-MP-DRLL-DR2126-TRAVEL-TRKLH | Track Assembly Left Hand | 14786 | 14786 | 6700
500127934 | CLB-MP-DRLL-DR2126-TRAVEL-TRBKR | Travel Brake Right Hand | 14786 | 443 | 6700
500127933 | CLB-MP-DRLL-DR2126-TRAVEL-TRBKL | Travel Brake Left Hand | 14786 | 443 | 6700
500127932 | CLB-MP-DRLL-DR2126-TRAVEL-SPRKR | Sprocket Right Hand | 14786 | 9298 | 6700
500127931 | CLB-MP-DRLL-DR2126-TRAVEL-SPRKL | Sprocket Left Hand | 14786 | 2066 | 6700
500127930 | CLB-MP-DRLL-DR2126-TRAVEL-FDRRH | Final Drive Right Hand | 14786 | 14786 | 6700
500127929 | CLB-MP-DRLL-DR2126-TRAVEL-FDRLH | Final Drive Left Hand | 14786 | 2066 | 6700
500127928 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF13 | Roller Load Pos 13 Single Flange CS | 14786 | 14786 | 6700
500127927 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF12 | Roller Load Pos 12 Single Flange CS | 14786 | 14786 | 6700
500127926 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF11 | Roller Load Pos 11 Single Flange CS | 14786 | 14786 | 6700
500127925 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF10 | Roller Load Pos 10 Single Flange CS | 14786 | 14786 | 6700
500127924 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF09 | Roller Load Pos 9 Single Flange CS | 14786 | 14786 | 6700
500127923 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF08 | Roller Load Pos 8 Single Flange CS | 14786 | 14786 | 6700
500127922 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF07 | Roller Load Pos 7 Single Flange CS | 14786 | 14786 | 6700
500127921 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF06 | Roller Load Pos 6 Single Flange CS | 14786 | 14786 | 6700
500127920 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF05 | Roller Load Pos 5 Single Flange CS | 14786 | 14786 | 6700
500127919 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF04 | Roller Load Pos 4 Single Flange CS | 14786 | 14786 | 6700
500127918 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF03 | Roller Load Pos 3 Single Flange CS | 14786 | 14786 | 6700
500127917 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF02 | Roller Load Pos 2 Single Flange CS | 14786 | 14786 | 6700
500127916 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-RSF01 | Roller Load Pos 1 Single Flange CS | 14786 | 12160 | 6700
500127915 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-IDLRH | Idler Track Cab Side | 14786 | 14786 | 6700
500127914 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRR | Roller Carrier CS Rear | 14786 | 14786 | 6700
500127913 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRM | Roller Carrier CS Middle | 14786 | 14786 | 6700
500127912 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-CARRF | Roller Carrier CS Front | 14786 | 14786 | 6700
500127911 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR-ADJGR | Track Adjuster Grease Cab Side | 14786 | 14786 | 6700
500127910 | CLB-MP-DRLL-DR2126-STRUCT-TKFRR | Track Frame-Cab Side | 14786 | 2066 | 6700
500127909 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF13 | Roller Load Pos 13 Single Flange NCS | 14786 | 14786 | 6700
500127908 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF12 | Roller Load Pos 12 Single Flange NCS | 14786 | 14786 | 6700
500127907 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF11 | Roller Load Pos 11 Single Flange NCS | 14786 | 14786 | 6700
500127906 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF10 | Roller Load Pos 10 Single Flange NCS | 14786 | 14786 | 6700
500127905 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF09 | Roller Load Pos 9 Single Flange NCS | 14786 | 14786 | 6700
500127904 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF08 | Roller Load Pos 8 Single Flange NCS | 14786 | 14786 | 6700
500127903 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF07 | Roller Load Pos 7 Single Flange NCS | 14786 | 14786 | 6700
500127902 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF06 | Roller Load Pos 6 Single Flange NCS | 14786 | 14786 | 6700
500127901 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF05 | Roller Load Pos 5 Single Flange NCS | 14786 | 14786 | 6700
500127900 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF04 | Roller Load Pos 4 Single Flange NCS | 14786 | 14786 | 6700
500127899 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF03 | Roller Load Pos 3 Single Flange NCS | 14786 | 14786 | 6700
500127898 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF02 | Roller Load Pos 2 Single Flange NCS | 14786 | 14786 | 6700
500127897 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-RSF01 | Roller Load Pos 1 Single Flange NCS | 14786 | 14786 | 6700
500127896 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-IDLLH | Idler Track Non Cab Side | 14786 | 14786 | 6700
500127895 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLR | Roller Carrier NCS Rear | 14786 | 14786 | 6700
500127894 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLM | Roller Carrier NCS Middle | 14786 | 14786 | 6700
500127893 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-CARLF | Roller Carrier NCS Front | 14786 | 14786 | 6700
500127892 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL-ADJGL | Track Adjuster Grease Non Cab Side | 14786 | 14786 | 6700
500127891 | CLB-MP-DRLL-DR2126-STRUCT-TKFRL | Track Frame-Non Cab Side | 14786 | 2066 | 6700
500127890 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHURR | Mast Sheave Assembly Upper Right Rear | 14786 | 4882 | 6700
500127889 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHURF | Mast Sheave Assembly Upper Right Front | 14786 | 4882 | 6700
500127888 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHULR | Mast Sheave Assembly Upper Left Rear | 14786 | 4882 | 6700
500127887 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHULF | Mast Sheave Assembly Upper Left Front | 14786 | 4882 | 6700
500127886 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHLRR | Mast Sheave Assembly Lower Right Rear | 14786 | 4882 | 6700
500127885 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHLRF | Mast Sheave Assembly Lower Right Front | 14786 | 4882 | 6700
500127884 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHLLR | Mast Sheave Assembly Lower Left Rear | 14786 | 4882 | 6700
500127883 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHLLF | Mast Sheave Assembly Lower Left Front | 14786 | 4882 | 6700
500127882 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHAUR | Mast Traveling Sheave Upper Right Hand | 14786 | 4882 | 6700
500127881 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHAUL | Mast Traveling Sheave Upper Left Hand | 14786 | 4882 | 6700
500127880 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHALR | Mast Traveling Sheave Lower Right Hand | 14786 | 4882 | 6700
500127879 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-SHALL | Mast Traveling Sheave Lower Left Hand | 14786 | 4882 | 6700
500127878 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-PPARM | Pipe Positioner Swing Arm | 14786 | 14786 | 6700
500127877 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-PDCBR | Pulldown Cable Right Hand | 14786 | 3064 | 6700
500127876 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-PDCBL | Pulldown Cable Left Hand | 14786 | 3064 | 6700
500127875 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-MHOBO | Hydraulically Operated Breakout Wrench | 14786 | 14786 | 6700
500127874 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-MHOBB | Hydraulically Operated Bit Basket | 14786 | 14786 | 6700
500127873 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-HOCBR | Hoist Cable Right Hand | 15135 | 3064 | 6700
500127872 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-HOCBL | Hoist Cable Left Hand | 14786 | 3064 | 6700
500127871 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-GBRTY | Gearbox Rotary Head | 14786 | 668 | 6700
500127870 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-DSPAN | Deck Spanner | 14786 | 14786 | 6700
500127869 | CLB-MP-DRLL-DR2126-STRUCT-DMAST-CSPRK | Drill Rod Carousel Pipe Rack | 14786 | 14786 | 6700
500127868 | CLB-MP-DRLL-DR2126-STRUCT-DMAST | Mast | 14786 | 14786 | 6700
500127867 | CLB-MP-DRLL-DR2126-STRUCT-CRANE | Hiab Crane Palfinger PC2700 | 14786 | 14786 | 6700
500127866 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-SEATS | Operators Seat | 14786 | 14786 | 6700
500127865 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-AIRCN | Air Conditioning System | 14786 | 14786 | 6700
500127864 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-ACHLF | Air Conditioner Hoses Lines Fittings | 14786 | 14786 | 6700
500127863 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-ACEVP | Air Conditioning Evaporator | 14786 | 14786 | 6700
500127862 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-ACEBF | Air Conditioning Evaporator Blower Fans | 14786 | 14786 | 6700
500127861 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-ACCOM | Air Conditioning Compressor | 14786 | 14786 | 6700
500127860 | CLB-MP-DRLL-DR2126-STRUCT-CABIN-ACCND | Air Conditioning Condensor | 14786 | 14786 | 6700
500127859 | CLB-MP-DRLL-DR2126-STRUCT-CABIN | Operators Cabin | 14786 | 14786 | 6700
500127858 | CLB-MP-DRLL-DR2126-ADSYST | ADS Autonomous Rig Control System | 14786 | 14786 | 6700
500127857 | CLB-MP-DRLL-DR2126-LUBSYS-DHTNK | DHD Reservoir | 14786 | 14786 | 6700
500127856 | CLB-MP-DRLL-DR2126-LUBSYS-DHDPP | DHD Oil Pump | 14786 | 14786 | 6700
500127855 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG-DRSHT | Pump Drive Drive Shaft | 14786 | 3637 | 6700
500127854 | CLB-MP-DRLL-DR2126-HYDSYS-PMPDG | Pump Drive Gearbox | 14781 | 14781 | 6700
500127853 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-PPAUX | Hydraulic Pump Auxiliary | 14786 | 443 | 6700
500127852 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP3 | Charge Gear Pump Double Stacked | 14786 | 443 | 6700
500127851 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP2 | Main Pump-Cab Side | 14786 | 233 | 6700
500127850 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-MNPP1 | Main Pump-Non Cab Side | 14786 | 443 | 6700
500127849 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-FANP2 | Pump Engine Cooler Fan-Cab Side | 14786 | 3626 | 6700
500127848 | CLB-MP-DRLL-DR2126-HYDSYS-HYDPP-FANP1 | Pump Comp Cooler Fan-Non Cab Side | 14786 | 3110 | 6700
500127847 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-VVDVR | Valve Diverter Right Hand | 14786 | 14786 | 6700
500127846 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-VVDVL | Valve Diverter Left Hand | 14786 | 14786 | 6700
500127845 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-VLVMA | Jack & Mast raise Valve | 14786 | 14786 | 6700
500127844 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-VLVAU | Auxiliary Valve Control-4 Bank | 14786 | 14786 | 6700
500127843 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-MCVV2 | Main Mast Valve Two-4 Bank | 14786 | 14786 | 6700
500127842 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-MCVV1 | Main Mast Valve One-6 Bank | 14786 | 14786 | 6700
500127841 | CLB-MP-DRLL-DR2126-HYDSYS-HDVLV-FLUVV | Valve - Relief Flushing | 14786 | 14786 | 6700
500127840 | CLB-MP-DRLL-DR2126-HYDSYS-HDTNK | Tank Hydraulic | 14786 | 14786 | 6700
500127839 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MRTNR | Motor Rotation-Cab Side | 14786 | 668 | 6700
500127838 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MRTNL | Motor Rotation-Non Cab Side | 14786 | 668 | 6700
500127837 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MPRPR | Motor Travel-Cab Side | 14786 | 14786 | 6700
500127836 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-MPRPL | Motor Travel-Non Cab Side | 14786 | 14786 | 6700
500127835 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-HDCFM | Motor Fan Hydraulic Cooling | 14786 | 8599 | 6700
500127834 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-FMECO | Motor Fan Engine Cooling | 14786 | 14786 | 6700
500127833 | CLB-MP-DRLL-DR2126-HYDSYS-HDMOT-ACONM | Motor Hyd Air Con | 14786 | 14786 | 6700
500127832 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-PCCYL | Cylinder Pipe Catcher Raise | 14786 | 14786 | 6700
500127831 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MRCYR | Cylinder Mast Raise-Cab Side | 14786 | 4255 | 6700
500127830 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MRCYL | Cylinder Mast Raise-Non Cab Side | 14786 | 3846 | 6700
500127829 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYR | Cylinder Mast Locking-Cab Side | 14786 | 14786 | 6700
500127828 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-MLCYL | Cylinder Mast Locking-Non Cab Side | 14786 | 14786 | 6700
500127827 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 14786 | 14786 | 6700
500127826 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRR | Cyl Jack RHR Drill End-Cab Side | 14786 | 14786 | 6700
500127825 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYRF | Cyl Jack RHF Non Drill End-Cab Side | 14786 | 2078 | 6700
500127824 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLR | Cyl Jack LHR Drill End-Non Cab Side | 14786 | 4172 | 6700
500127823 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-JCYLF | Cyl Jack LHF Non Drill End-Non Cab Side | 14786 | 889 | 6700
500127822 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-FDCYL | Cylinder Hoist Pulldown | 14786 | 3614 | 6700
500127821 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 14786 | 14786 | 6700
500127820 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CYPPS | Cylinder Pipe Positioner Swing | 14786 | 14786 | 6700
500127819 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CYPPL | Cylinder Pipe Positioner Lock | 14786 | 14786 | 6700
500127818 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CYLDH | Cylinder Deck Viewing Hatch | 14786 | 14786 | 6700
500127817 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CYCLU | Cylinder Carousel Lock | 14786 | 14786 | 6700
500127816 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CYCLL | Cylinder Carousel Indexing Lock | 14786 | 7622 | 6700
500127815 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CTCRU | Cylinder Cable Tension RHU Cab Side | 14786 | 14786 | 6700
500127814 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CTCRL | Cylinder Cable Tension RHL Cab Side | 14786 | 14786 | 6700
500127813 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CTCLU | Cylinder Cable Tension LHU-Non Cab Side | 14786 | 14786 | 6700
500127812 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CTCLL | Cylinder Cable Tension LHL-Non Cab Side | 14786 | 14786 | 6700
500127811 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 14786 | 14786 | 6700
500127810 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CSCYL | Cylinder Carousel Swing Lower | 14786 | 14786 | 6700
500127809 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CHBOS | Cylinder HOBO Swing | 14786 | 14786 | 6700
500127808 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CHBOR | Cylinder HOBO Rotation | 14786 | 14786 | 6700
500127807 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-CHBOC | Cylinder HOBO Clamp | 14786 | 14786 | 6700
500127806 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-BKOCY | Cylinder Deck Wrench fork | 14786 | 55 | 6700
500127805 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-BBCYR | Cylinder Bit basket Cab Side | 14786 | 4882 | 6700
500127804 | CLB-MP-DRLL-DR2126-HYDSYS-HDCYL-BBCYL | Cylinder Bit basket Non Cab side | 14786 | 4882 | 6700
500127803 | CLB-MP-DRLL-DR2126-HYDSYS-COFAN-CFHDY | Fan Hydraulic Cooling | 14786 | 14786 | 6700
500127802 | CLB-MP-DRLL-DR2126-HYDSYS-COFAN-CFENG | Fan Engine Cooling | 14786 | 3631 | 6700
500127801 | CLB-MP-DRLL-DR2126-GRSYST-RTTNK | Rod Thread Lube Reservoir | 14786 | 14786 | 6700
500127800 | CLB-MP-DRLL-DR2126-GRSYST-RTLPP | Rod Thread lube Pump | 14786 | 55 | 6700
500127799 | CLB-MP-DRLL-DR2126-GRSYST-RTINJ | Rod Thread Grease Injector | 14786 | 14786 | 6700
500127798 | CLB-MP-DRLL-DR2126-GRSYST-GRTNK | Auto Lube Reservoir | 14786 | 14786 | 6700
500127797 | CLB-MP-DRLL-DR2126-GRSYST-GRINJ | Auto Lube Injectors | 14786 | 14786 | 6700
500127796 | CLB-MP-DRLL-DR2126-GRSYST-ALBPP | Auto lube Pump | 14786 | 14786 | 6700
500127795 | CLB-MP-DRLL-DR2126-FRSUPP | Fire Suppression System | 14786 | 14786 | 6700
500127794 | CLB-MP-DRLL-DR2126-ENGINE-INTEX-TBOP2 | Turbocharger Engine Right Hand | 14786 | 1986 | 6700
500127793 | CLB-MP-DRLL-DR2126-ENGINE-INTEX-TBOP1 | Turbocharger Engine Left Hand | 14786 | 7622 | 6700
500127792 | CLB-MP-DRLL-DR2126-ENGINE-INTEX-EXHST | Exhaust System Engine | 14786 | 14786 | 6700
500127791 | CLB-MP-DRLL-DR2126-ENGINE-INTEX-AIRFL | Air Filtration Systems Engine | 14786 | 14786 | 6700
500127790 | CLB-MP-DRLL-DR2126-ENGINE-INTEX-AFTER | Aftercooler Core ATAAC | 14786 | 14786 | 6700
500127789 | CLB-MP-DRLL-DR2126-ENGINE-FUSYS-FUTFP | Fuel Transfer Pump | 14786 | 7622 | 6700
500127788 | CLB-MP-DRLL-DR2126-ENGINE-FUSYS-FULTK | Fuel Tank Engine | 14786 | 14786 | 6700
500127787 | CLB-MP-DRLL-DR2126-ENGINE-FUSYS-FULPP | Fuel Priming Pump Engine | 14786 | 14786 | 6700
500127786 | CLB-MP-DRLL-DR2126-ENGINE-FUSYS-FULCO | Fuel Cooler Engine | 14786 | 14786 | 6700
500127785 | CLB-MP-DRLL-DR2126-ENGINE-FUSYS-FUINJ | Fuel Unit Injector Engine | 14786 | 7622 | 6700
500127784 | CLB-MP-DRLL-DR2126-ENGINE-FUSYS-FUHLF | Fuel System Hoses Lines & Fittings | 14786 | 14786 | 6700
500127783 | CLB-MP-DRLL-DR2126-ENGINE-COSYS-WTRPP | Water Pump Engine | 14786 | 7622 | 6700
500127782 | CLB-MP-DRLL-DR2126-ENGINE-COSYS-THERM | Thermostats/Regulators Engine | 14786 | 7622 | 6700
500127781 | CLB-MP-DRLL-DR2126-ENGINE-COSYS-RADTR | Radiator Engine | 14786 | 14786 | 6700
500127780 | CLB-MP-DRLL-DR2126-ENGINE | Engine Assembly CAT C32 | 14786 | 14786 | 6700
500127779 | CLB-MP-DRLL-DR2126-ELCTLV-START-STMRH | Starter Motor Engine Right | 14786 | 3152 | 6700
500127778 | CLB-MP-DRLL-DR2126-ELCTLV-START-STMLH | Starter Motor Engine Left | 14786 | 3152 | 6700
500127777 | CLB-MP-DRLL-DR2126-ELCTLV-CHARG-BATTY | Batteries Engine | 14786 | 1986 | 6700
500127776 | CLB-MP-DRLL-DR2126-ELCTLV-CHARG-ALTER | Alternator 24V | 14786 | 1826 | 6700
500127775 | CLB-MP-DRLL-DR2126-DSTSUP-WTNKP | Water Tank Primary | 14786 | 14786 | 6700
500127774 | CLB-MP-DRLL-DR2126-DSTSUP-WTRPP | Dynaset Water Pump | 14786 | 7896 | 6700
500127773 | CLB-MP-DRLL-DR2126-DSTSUP-WSHPP | Pump Wash Down | 14786 | 14786 | 6700
500127772 | CLB-MP-DRLL-DR2126-DSTSUP-WSHMT | Engine Wash Down | 14786 | 14786 | 6700
500127771 | CLB-MP-DRLL-DR2126-COOLER-HDOCO | Hydraulic Oil Cooler Core | 14786 | 14786 | 6700
500127770 | CLB-MP-DRLL-DR2126-COOLER-COOCO | Compressor Oil Cooler Core | 14786 | 14786 | 6700
500127769 | CLB-MP-DRLL-DR2126-COOLER | Cooler Module Assembly | 14786 | 14786 | 6700
500127768 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-COUPL | Compressor Torsional Coupling | 14786 | 8105 | 6700
500127766 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-ACTBV | Actuator Butterfly Valve | 14786 | 3185 | 6700
500127765 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-ACTBD | Actuator Running Blowdown Valve | 14786 | 3387 | 6700
500127764 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR | Main Air Compressor | 14786 | 8105 | 6700
500127763 | CLB-MP-DRLL-DR2126 | CAT MD6310 Drill DR2126 | 14786 | 14786 | 6700
500146041 | CLB-MP-DRLL-DR061 -AIRSYS-ARTNK | DR061 Receiver Tank | 43460 | 43460 | 6300
500140227 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-DHCYL | Cylinder Deck Viewing Hatch | 43421 | 1524 | 6300
500140226 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-CRTCY | Cylinder Carousel Rotation indexing | 43421 | 1524 | 6300
500140225 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-BWRCY | Cylinder Rotate Breakout Wrench | 43421 | 1524 | 6300
500140224 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-BWCCY | Cylinder Clamp Breakout Wrench | 43421 | 1524 | 6300
500140223 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-BKOCY | Cyl Breakout Fork | 43421 | 1524 | 6300
500140222 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-CSCYL | Cyl Carousel Swing Lower | 43421 | 1524 | 6300
500140221 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-BBCYL | Cyl Bit Basket Non Cab Side | 43421 | 1524 | 6300
500140220 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-BWSCY | Cylinder Swing Breakout Wrench | 43421 | 1524 | 6300
500140219 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-DSRCY | Cylinder Dust Skirt Raise | 43421 | 240 | 6300
500140218 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-CSCYU | Cylinder Carousel Swing Upper | 43421 | 1524 | 6300
500140217 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-BBCYR | Cylinder Bit Basket Cab Side | 43421 | 1524 | 6300
500138261 | CLB-MP-DRLL-DR061 -ELCTLV-HARNS-HARCO | Electrical Harness Control | 43421 | 1524 | 6300
500133736 | CLB-MP-DRLL-DR061 -ADSYST-HARNC | ADS Harnesses & Connectors | 43421 | 1524 | 6300
500133735 | CLB-MP-DRLL-DR061 -ADSYST-ADSPR-LIDAR | ADS LiDAR System | 43421 | 1524 | 6300
500133734 | CLB-MP-DRLL-DR061 -ADSYST-ADSPR-HTCAM | ADS Camera Systems PTZ Fish-Eye | 43421 | 1524 | 6300
500133733 | CLB-MP-DRLL-DR061 -ADSYST-ADSPR | ADS HazTech | 43421 | 35330 | 6300
500133732 | CLB-MP-DRLL-DR061 -ADSYST-ADSPO | ADS Global Positioning System | 43421 | 35330 | 6300
500133731 | CLB-MP-DRLL-DR061 -ADSYST-ADSHW-HMIJK | ADS HMI Screen Josticks Keypad | 43421 | 1524 | 6300
500133730 | CLB-MP-DRLL-DR061 -ADSYST-ADSHW-CLXEN | ADS Control Power Enclosure CLX | 43421 | 1524 | 6300
500133729 | CLB-MP-DRLL-DR061 -ADSYST-ADSHW-ARDIO | ADS Input Output Modules | 43421 | 35330 | 6300
500133728 | CLB-MP-DRLL-DR061 -ADSYST-ADSHW-ADSMF | ADS Mounts & Frames | 43421 | 35330 | 6300
500133653 | CLB-MP-DRLL-DR061 -ADSYST | Autonomous Drilling System | 43421 | 35330 | 6300
500132386 | CLB-MP-DRLL-DR061 -ELCTLV-HARNS | Wiring Harness | 43421 | 43421 | 6300
500113832 | CLB-MP-DRLL-DR061 -TRAVEL-TRKRH | DR061 Track Assembly - Cab Side | 43398 | 1524 | 6300
500113831 | CLB-MP-DRLL-DR061 -TRAVEL-TRKLH | DR061 Track Assembly - Non Cab Side | 43398 | 1524 | 6300
500113830 | CLB-MP-DRLL-DR061 -TRAVEL-SPRKR | DR061 Sprocket - Cab Side | 43398 | 1524 | 6300
500113829 | CLB-MP-DRLL-DR061 -TRAVEL-SPRKL | DR061 Sprocket - Non Cab Side | 43398 | 1524 | 6300
500113828 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RSF04 | DR061 Roller Load Pos 4 S Flange - CS | 43398 | 1524 | 6300
500113827 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RSF03 | DR061 Roller Load Pos 3 S Flange - CS | 43398 | 1524 | 6300
500113826 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RSF02 | DR061 Roller Load Pos 2 S Flange - CS | 43398 | 1524 | 6300
500113825 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RSF01 | DR061 Roller Load Pos 1 S Flange - CS | 43398 | 1524 | 6300
500113824 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF13 | DR061 Roller Load Pos 13 D Flange - CS | 43398 | 1524 | 6300
500113823 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF12 | DR061 Roller Load Pos 12 D Flange - CS | 43398 | 1524 | 6300
500113822 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF11 | DR061 Roller Load Pos 11 D Flange - CS | 43398 | 1524 | 6300
500113821 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF10 | DR061 Roller Load Pos 10 D Flange - CS | 43398 | 1524 | 6300
500113820 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF09 | DR061 Roller Load Pos 9 D Flange - CS | 43398 | 1524 | 6300
500113819 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF08 | DR061 Roller Load Pos 8 D Flange - CS | 43398 | 1524 | 6300
500113818 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF07 | DR061 Roller Load Pos 7 D Flange - CS | 43398 | 1524 | 6300
500113817 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF06 | DR061 Roller Load Pos 6 D Flange - CS | 43398 | 240 | 6300
500113816 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-RDF05 | DR061 Roller Load Pos 5 D Flange - CS | 43398 | 1524 | 6300
500113815 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-IDLRH | DR061 Idler Track - Cab Side | 43398 | 1524 | 6300
500113814 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-CARRR | DR061 Roller Carrier Rear - Cab Side | 43398 | 1524 | 6300
500113813 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-CARRM | DR061 Roller Carrier Middle - Cab Side | 43398 | 1524 | 6300
500113812 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-CARRF | DR061 Roller Carrier Front - Cab Side | 43398 | 1524 | 6300
500113811 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR | DR061 Track Frame - Cab Side | 43398 | 1524 | 6300
500113810 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RSF04 | DR061 Roller Load Pos 4 S Flange - NCS | 43398 | 1524 | 6300
500113809 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RSF03 | DR061 Roller Load Pos 3 S Flange - NCS | 43398 | 1524 | 6300
500113808 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RSF02 | DR061 Roller Load Pos 2 S Flange - NCS | 43398 | 1524 | 6300
500113807 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RSF01 | DR061 Roller Load Pos 1 S Flange - NCS | 43398 | 1524 | 6300
500113806 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF13 | DR061 Roller Load Pos 13 D Flange - NCS | 43398 | 1524 | 6300
500113805 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF12 | DR061 Roller Load Pos 12 D Flange - NCS | 43398 | 1524 | 6300
500113804 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF11 | DR061 Roller Load Pos 11 D Flange - NCS | 43398 | 1524 | 6300
500113803 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF10 | DR061 Roller Load Pos 10 D Flange - NCS | 43398 | 1524 | 6300
500113802 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF09 | DR061 Roller Load Pos 9 D Flange - NCS | 43398 | 1524 | 6300
500113801 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF08 | DR061 Roller Load Pos 8 D Flange - NCS | 43398 | 1524 | 6300
500113550 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-AFRME | DR061 Tower A Frame | 43398 | 1524 | 6300
500113480 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF07 | DR061 Roller Load Pos 7 D Flange - NCS | 43398 | 1524 | 6300
500113479 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF06 | DR061 Roller Load Pos 6 D Flange - NCS | 43398 | 1524 | 6300
500113478 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-RDF05 | DR061 Roller Load Pos 5 D Flange - NCS | 43398 | 1524 | 6300
500113477 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-IDLLH | DR061 Idler Track - Non Cab Side | 43398 | 1524 | 6300
500113476 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-CARLR | DR061 Roller Carrier Rear - NCS | 43398 | 1524 | 6300
500113475 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-CARLM | DR061 Roller Carrier Middle - NCS | 43398 | 1524 | 6300
500113474 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-CARLF | DR061 Roller Carrier Front - NCS | 43398 | 1524 | 6300
500113473 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL | DR061 Track Frame - Non Cab Side | 43398 | 1524 | 6300
500107960 | CLB-MP-DRLL-DR061 -AIRSYS-EARCS-BDVVE | DR061 Blowdown Valve | 43398 | 1524 | 6300
500107959 | CLB-MP-DRLL-DR061 -AIRSYS-EARCS-ACTBD | DR061 Actuator Blowdown Valve | 43398 | 1524 | 6300
500107958 | CLB-MP-DRLL-DR061 -AIRSYS-EARCS-BFVVE | DR061 Comp Butterfly Valve | 43398 | 1524 | 6300
500107957 | CLB-MP-DRLL-DR061 -AIRSYS-EARCS-ACTBV | DR061 Actuator Butterfly Valve | 43398 | 1524 | 6300
500104102 | CLB-MP-DRLL-DR061 -FRSUPP | DR061 Fire Suppression System | 43308 | 20754 | 6300
500103010 | CLB-MP-DRLL-DR061 -STRUCT-TOWER | DR061 Tower Assembly | 43398 | 1524 | 6300
500102295 | CLB-MP-DRLL-DR061 -DSTSUP-WTRPP | DR061 Pump Water Injection Dynaset | 43398 | 240 | 6300
500102294 | CLB-MP-DRLL-DR061 -GRSYST-RTLPP | DR061 Rod Thread lube Pump | 43398 | 20378 | 6300
500102293 | CLB-MP-DRLL-DR061 -GRSYST-ALBPP | DR061 Auto lube Pump | 43398 | 20754 | 6300
500102292 | CLB-MP-DRLL-DR061 -LUBSYS-DHDPP | DR061 DHD Oil Pump | 43398 | 43398 | 6300
500102291 | CLB-MP-DRLL-DR061 -STRUCT-UNDER-YKOSC | DR061 Yoke Oscillation | 43398 | 1524 | 6300
500102290 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-BOFKA | DR061 Breakout Fork Sliding Assembly | 43398 | 1524 | 6300
500102289 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-BOWRH | DR061 Breakout Wrench Assy | 43398 | 1524 | 6300
500102288 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-CARAS | DR061 Rod Changer / Carousel | 43398 | 1524 | 6300
500102287 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-RDSPT | DR061 Rod support | 43398 | 1524 | 6300
500102286 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SCBTR | DR061 Screw Jack Cable Tension R/H | 43398 | 1524 | 6300
500102285 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SCBTL | DR061 Screw Jack Cable Tension L/H | 43398 | 1524 | 6300
500102284 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SHULR | DR061 Sheave Assy Up/Lower - Cab Side | 43398 | 1524 | 6300
500102283 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SHULL | DR061 Sheave Assy Up/Lower-Non Cab Side | 43398 | 1524 | 6300
500102282 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SHAUR | DR061 Sheave Assembly Upper R/H | 43398 | 1524 | 6300
500102281 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SHAUL | DR061 Sheave Assembly Upper L/H | 43398 | 1524 | 6300
500102280 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SHALR | DR061 Sheave Assembly Lower R/H | 43398 | 1524 | 6300
500102279 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-SHALL | DR061 Sheave Assembly Lower L/H | 43398 | 1524 | 6300
500102278 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-CSHAR | DR061 Carriage Sheave Assembly R/H | 43398 | 1524 | 6300
500102277 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-CSHAL | DR061 Carriage Sheave Assembly L/H | 43398 | 1524 | 6300
500102276 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PBCBR | DR061 Pullback Cable R/H | 43398 | 1524 | 6300
500102275 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PBCBL | DR061 Pullback Cable L/H | 43398 | 1524 | 6300
500102274 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PDCBR | DR061 Pulldown Cable R/H | 43398 | 1524 | 6300
500102273 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PDCBL | DR061 Pulldown Cable L/H | 43398 | 1524 | 6300
500102272 | CLB-MP-DRLL-DR061 -STRUCT-TOWER-PWRHD | DR061 Gearbox Power Head | 43398 | 1524 | 6300
500102271 | CLB-MP-DRLL-DR061 -STRUCT-TKFRR-ADJGR | DR061 Track Adjuster Grease R/H | 43398 | 1524 | 6300
500102270 | CLB-MP-DRLL-DR061 -STRUCT-TKFRL-ADJGL | DR061 Track Adjuster Grease L/H | 43398 | 1524 | 6300
500102269 | CLB-MP-DRLL-DR061 -STRUCT-CRANE | DR061 Hiab Crane | 43398 | 20754 | 6300
500102268 | CLB-MP-DRLL-DR061 -STRUCT-CABIN-SEATS | DR061 Operators Seat | 43398 | 1524 | 6300
500102267 | CLB-MP-DRLL-DR061 -STRUCT-CABIN-ACCOM | DR061 Air Conditioning Compressor | 43398 | 1524 | 6300
500102266 | CLB-MP-DRLL-DR061 -HYDSYS-COFAN-FCCAC | DR061 Fan Cooling Charge Air Cooler | 43398 | 1524 | 6300
500102265 | CLB-MP-DRLL-DR061 -HYDSYS-COFAN-FCCMA | DR061 Fan Cooling Cooler Module Assy | 43398 | 1524 | 6300
500102264 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-ACONM | DR061 Motor Hyd Air Con | 43398 | 1524 | 6300
500102263 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MRTNR | DR061 Motor Rotation R/H | 43398 | 1486 | 6300
500102262 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MRTNL | DR061 Motor Rotation L/H | 43398 | 1486 | 6300
500102261 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTR | DR061 Mtr 4.9 CID ScrewJack Tension R/H | 43398 | 1524 | 6300
500102260 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MSJTL | DR061 Mtr 4.9 CID ScrewJack Tension L/H | 43398 | 1524 | 6300
500102259 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MPRPR | DR061 Motor Propel R/H | 43398 | 1524 | 6300
500102258 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MPRPL | DR061 Motor Propel L/H | 43398 | 1524 | 6300
500102257 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MFCAC | DR061 Motor Fan CAC Cooler | 43398 | 1524 | 6300
500102256 | CLB-MP-DRLL-DR061 -HYDSYS-HDMOT-MFMCA | DR061 Motor Fan Main Cooler Assy | 43398 | 1524 | 6300
500102255 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVTNC | DR061 Valve Tension Cable | 43398 | 1524 | 6300
500102254 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDPC | DR061 Valve Drill/Propel Control | 43398 | 1524 | 6300
500102253 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDVR | DR061 Valve Diverter RH | 43398 | 1524 | 6300
500102252 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDVL | DR061 Valve Diverter LH | 43398 | 1524 | 6300
500102251 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVCNB | DR061 Valve Counter Balance | 43398 | 1524 | 6300
500102250 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVDCB | DR061 Valve Dual Counter Balance | 43398 | 1524 | 6300
500102249 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VV11S | DR061 Valve Stacking 11 spool | 43398 | 1524 | 6300
500102248 | CLB-MP-DRLL-DR061 -HYDSYS-HDVLV-VVS8S | DR061 Valve Stacking 8 spool | 43398 | 1524 | 6300
500102247 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-CTCYR | DR061 Cylinder Cable Tension R/H | 43398 | 1524 | 6300
500102246 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-CTCYL | DR061 Cylinder Cable Tension L/H | 43398 | 1524 | 6300
500102245 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-FDCYR | DR061 Cylinder Feed Hyd R/H | 43398 | 1524 | 6300
500102244 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-FDCYL | DR061 Cylinder Feed Hyd L/H | 43398 | 1524 | 6300
500102243 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRR | DR061 Cylinder Jack Leg R/H/R | 43398 | 9387 | 6300
500102242 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLR | DR061 Cylinder Jack Leg L/H/R | 43398 | 1524 | 6300
500102241 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYRF | DR061 Cylinder Jack Leg R/H/F | 43398 | 14161 | 6300
500102240 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-JCYLF | DR061 Cylinder Jack Leg L/H/F | 43398 | 14180 | 6300
500102239 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TACYR | DR061 Cyl Tower Support Angle Lock R/H | 43398 | 243 | 6300
500102238 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TACYL | DR061 Cyl Tower Support Angle Lock L/H | 43398 | 1524 | 6300
500102237 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TLCYR | DR061 Cylinder Tower locking R/H | 43398 | 1524 | 6300
500102236 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TLCYL | DR061 Cylinder Tower locking L/H | 43398 | 1524 | 6300
500102235 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYR | DR061 Cylinder Tower Raise R/H | 43398 | 1524 | 6300
500102234 | CLB-MP-DRLL-DR061 -HYDSYS-HDCYL-TRCYL | DR061 Cylinder Tower Raise L/H | 43398 | 1524 | 6300
500102233 | CLB-MP-DRLL-DR061 -HYDSYS-HYDPP-PRHDL | DR061 Pump Self Revers Power Head Lube | 43398 | 1524 | 6300
500102232 | CLB-MP-DRLL-DR061 -HYDSYS-HYDPP-MNPP3 | DR061 Pump Hydraulic triple | 43398 | 1524 | 6300
500102231 | CLB-MP-DRLL-DR061 -HYDSYS-HYDPP-MNPP2 | DR061 Pump Hydraulic P7,9A CONT | 43398 | 1524 | 6300
500102230 | CLB-MP-DRLL-DR061 -HYDSYS-HYDPP-MNPP1 | DR061 Pump Hydraulic P7,9A CONT | 43398 | 1524 | 6300
500102229 | CLB-MP-DRLL-DR061 -HYDSYS-PMPDR-DRSHT | DR061 Pump Drive Drive Shaft | 43398 | 1524 | 6300
500102228 | CLB-MP-DRLL-DR061 -HYDSYS-PMPDR | DR061 Pump Drive Gearbox 3 Hole | 43398 | 1524 | 6300
500102227 | CLB-MP-DRLL-DR061 -COOLER | DR061 Cooler Module Assembly | 43398 | 1524 | 6300
500102226 | CLB-MP-DRLL-DR061 -AIRSYS-COMPR-COUPL | DR061 Compressor Coupling Ringfeeder | 43398 | 1524 | 6300
500102225 | CLB-MP-DRLL-DR061 -AIRSYS-COMPR | DR061 Main Air Compressor | 43398 | 1524 | 6300
500102224 | CLB-MP-DRLL-DR061 -TRAVEL-FDRRH | DR061 Final Drive R/H | 43398 | 1524 | 6300
500102223 | CLB-MP-DRLL-DR061 -TRAVEL-FDRLH | DR061 Final Drive L/H | 43398 | 1524 | 6300
500102222 | CLB-MP-DRLL-DR061 -ELCTLV-START-STMRH | DR061 Starter Motor Engine Right | 43398 | 1524 | 6300
500102221 | CLB-MP-DRLL-DR061 -ELCTLV-START-STMLH | DR061 Starter Motor Engine Left | 43398 | 1524 | 6300
500102220 | CLB-MP-DRLL-DR061 -ELCTLV-CHARG-ALTER | DR061 Alternator 24V | 43398 | 1524 | 6300
500102219 | CLB-MP-DRLL-DR061 -ENGINE-FUSYS-FULCO | DR061 Fuel Cooler Engine | 43398 | 1524 | 6300
500102218 | CLB-MP-DRLL-DR061 -ENGINE-FUSYS-FUINJ | DR061 Fuel Injectors Engine | 43398 | 1524 | 6300
500102217 | CLB-MP-DRLL-DR061 -ENGINE-FUSYS-FULPP | DR061 Fuel Pump Engine | 43398 | 1524 | 6300
500102216 | CLB-MP-DRLL-DR061 -ENGINE-INTEX-CACAS | DR061 Charge Air Cooler | 43421 | 1524 | 6300
500102215 | CLB-MP-DRLL-DR061 -ENGINE-INTEX-TBOP2 | DR061 Turbocharger Engine | 43398 | 1524 | 6300
500102214 | CLB-MP-DRLL-DR061 -ENGINE-INTEX-TBOP1 | DR061 Turbocharger Engine | 43398 | 1524 | 6300
500102213 | CLB-MP-DRLL-DR061 -ENGINE-COSYS-THERM | DR061 Thermostats/Regulators Engine | 43398 | 1524 | 6300
500102212 | CLB-MP-DRLL-DR061 -ENGINE-COSYS-WTRPP | DR061 Water pump Engine | 43398 | 1524 | 6300
500102211 | CLB-MP-DRLL-DR061 -ENGINE | DR061 Engine Assembly | 43421 | 1524 | 6300
500101451 | CLB-MP-DRLL-DR061 | Atlas Copco PV271LP Drill, DR061 | 43421 | 43421 | 6300
500140494 | CLB-MP-HAUL-DT225 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 51224 | 45033 | 7500
500117837 | CLB-MP-HAUL-DT225 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 51224 | 45033 | 7500
500117797 | CLB-MP-HAUL-DT225 -AHSYST-CTRLH-ECMA6 | ECM A6 | 51224 | 16739 | 7500
500117719 | CLB-MP-HAUL-DT225 -AHSYST-CTRLH-LIDAR | AHS Lidar | 51260 | 41955 | 7500
500117641 | CLB-MP-HAUL-DT225 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 51224 | 45033 | 7500
500117601 | CLB-MP-HAUL-DT225 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 51224 | 45033 | 7500
500117561 | CLB-MP-HAUL-DT225 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 51224 | 45033 | 7500
500117521 | CLB-MP-HAUL-DT225 -AHSYST-AHSMF | AHS System Mounts & Frames | 51224 | 45033 | 7500
500117481 | CLB-MP-HAUL-DT225 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 51224 | 45033 | 7500
500117401 | CLB-MP-HAUL-DT225 -AHSYST-SNSRS | AHS Sensors | 51224 | 45033 | 7500
500117361 | CLB-MP-HAUL-DT225 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 51224 | 45033 | 7500
500117281 | CLB-MP-HAUL-DT225 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 51224 | 45033 | 7500
500117241 | CLB-MP-HAUL-DT225 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 51224 | 45033 | 7500
500117201 | CLB-MP-HAUL-DT225 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 51224 | 45033 | 7500
500117161 | CLB-MP-HAUL-DT225 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 51224 | 45033 | 7500
500117121 | CLB-MP-HAUL-DT225 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 51224 | 45033 | 7500
500101394 | CLB-MP-HAUL-DT225 -STRSYS-AHSEV | Valve Steering | 51224 | 6100 | 7500
500140493 | CLB-MP-HAUL-DT224 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 49652 | 43501 | 7500
500117836 | CLB-MP-HAUL-DT224 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 49652 | 43501 | 7500
500117796 | CLB-MP-HAUL-DT224 -AHSYST-CTRLH-ECMA6 | ECM A6 | 49652 | 43501 | 7500
500117718 | CLB-MP-HAUL-DT224 -AHSYST-CTRLH-LIDAR | AHS Lidar | 49696 | 39001 | 7500
500117640 | CLB-MP-HAUL-DT224 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 49652 | 43501 | 7500
500117600 | CLB-MP-HAUL-DT224 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 49652 | 43501 | 7500
500117560 | CLB-MP-HAUL-DT224 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 49652 | 43501 | 7500
500117520 | CLB-MP-HAUL-DT224 -AHSYST-AHSMF | AHS System Mounts & Frames | 49652 | 43501 | 7500
500117480 | CLB-MP-HAUL-DT224 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 49652 | 43501 | 7500
500117400 | CLB-MP-HAUL-DT224 -AHSYST-SNSRS | AHS Sensors | 49652 | 43501 | 7500
500117360 | CLB-MP-HAUL-DT224 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 49652 | 43501 | 7500
500117280 | CLB-MP-HAUL-DT224 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 49652 | 43501 | 7500
500117240 | CLB-MP-HAUL-DT224 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 49652 | 43501 | 7500
500117200 | CLB-MP-HAUL-DT224 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 49652 | 43501 | 7500
500117160 | CLB-MP-HAUL-DT224 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 49652 | 43501 | 7500
500117120 | CLB-MP-HAUL-DT224 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 49652 | 43501 | 7500
500101261 | CLB-MP-HAUL-DT224 -STRSYS-AHSEV | Valve Steering | 49652 | 4796 | 7500
500117835 | CLB-MP-HAUL-DT200 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 92465 | 45721 | 7500
500117795 | CLB-MP-HAUL-DT200 -AHSYST-CTRLH-ECMA6 | ECM A6 | 92465 | 45721 | 7500
500117757 | CLB-MP-HAUL-DT200 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 92465 | 45721 | 7500
500117717 | CLB-MP-HAUL-DT200 -AHSYST-CTRLH-LIDAR | AHS Lidar | 109403 | 37488 | 7500
500117679 | CLB-MP-HAUL-DT200 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 92465 | 45721 | 7500
500117639 | CLB-MP-HAUL-DT200 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 92465 | 45721 | 7500
500117599 | CLB-MP-HAUL-DT200 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 92465 | 45721 | 7500
500117559 | CLB-MP-HAUL-DT200 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 92465 | 45721 | 7500
500117519 | CLB-MP-HAUL-DT200 -AHSYST-AHSMF | AHS System Mounts & Frames | 92465 | 45721 | 7500
500117479 | CLB-MP-HAUL-DT200 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 92465 | 45721 | 7500
500117399 | CLB-MP-HAUL-DT200 -AHSYST-SNSRS | AHS Sensors | 92465 | 45721 | 7500
500117359 | CLB-MP-HAUL-DT200 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 92465 | 45721 | 7500
500117279 | CLB-MP-HAUL-DT200 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 92465 | 45721 | 7500
500117239 | CLB-MP-HAUL-DT200 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 92465 | 45721 | 7500
500117199 | CLB-MP-HAUL-DT200 -STRSYS-AHSEV | AHS EH Steering Valve | 92465 | 27715 | 7500
500117159 | CLB-MP-HAUL-DT200 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 92465 | 45721 | 7500
500117119 | CLB-MP-HAUL-DT200 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 92465 | 45721 | 7500
500117834 | CLB-MP-HAUL-DT199 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 85856 | 54160 | 7500
500117794 | CLB-MP-HAUL-DT199 -AHSYST-CTRLH-ECMA6 | ECM A6 | 85856 | 54160 | 7500
500117756 | CLB-MP-HAUL-DT199 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 85856 | 34185 | 7500
500117716 | CLB-MP-HAUL-DT199 -AHSYST-CTRLH-LIDAR | AHS Lidar | 85864 | 31416 | 7500
500117678 | CLB-MP-HAUL-DT199 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 85856 | 54160 | 7500
500117638 | CLB-MP-HAUL-DT199 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 85856 | 54160 | 7500
500117598 | CLB-MP-HAUL-DT199 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 85856 | 54160 | 7500
500117558 | CLB-MP-HAUL-DT199 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 85856 | 54160 | 7500
500117518 | CLB-MP-HAUL-DT199 -AHSYST-AHSMF | AHS System Mounts & Frames | 85856 | 54160 | 7500
500117478 | CLB-MP-HAUL-DT199 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 85856 | 54160 | 7500
500117398 | CLB-MP-HAUL-DT199 -AHSYST-SNSRS | AHS Sensors | 85856 | 54160 | 7500
500117358 | CLB-MP-HAUL-DT199 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 85856 | 54160 | 7500
500117278 | CLB-MP-HAUL-DT199 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 85856 | 54160 | 7500
500117238 | CLB-MP-HAUL-DT199 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 85856 | 54160 | 7500
500117198 | CLB-MP-HAUL-DT199 -STRSYS-AHSEV | AHS EH Steering Valve | 85856 | 54160 | 7500
500117158 | CLB-MP-HAUL-DT199 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 85856 | 54160 | 7500
500117118 | CLB-MP-HAUL-DT199 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 85856 | 54160 | 7500
500117833 | CLB-MP-HAUL-DT198 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 88600 | 47564 | 7500
500117793 | CLB-MP-HAUL-DT198 -AHSYST-CTRLH-ECMA6 | ECM A6 | 88600 | 47564 | 7500
500117755 | CLB-MP-HAUL-DT198 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 88600 | 13955 | 7500
500117715 | CLB-MP-HAUL-DT198 -AHSYST-CTRLH-LIDAR | AHS Lidar | 88628 | 40040 | 7500
500117677 | CLB-MP-HAUL-DT198 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 88600 | 47564 | 7500
500117637 | CLB-MP-HAUL-DT198 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 88600 | 47564 | 7500
500117597 | CLB-MP-HAUL-DT198 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 88600 | 47564 | 7500
500117557 | CLB-MP-HAUL-DT198 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 88600 | 47564 | 7500
500117517 | CLB-MP-HAUL-DT198 -AHSYST-AHSMF | AHS System Mounts & Frames | 88600 | 47564 | 7500
500117477 | CLB-MP-HAUL-DT198 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 88600 | 47564 | 7500
500117397 | CLB-MP-HAUL-DT198 -AHSYST-SNSRS | AHS Sensors | 88600 | 47564 | 7500
500117357 | CLB-MP-HAUL-DT198 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 88600 | 47564 | 7500
500117277 | CLB-MP-HAUL-DT198 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 88600 | 47564 | 7500
500117237 | CLB-MP-HAUL-DT198 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 88600 | 47564 | 7500
500117197 | CLB-MP-HAUL-DT198 -STRSYS-AHSEV | AHS EH Steering Valve | 88600 | 47564 | 7500
500117157 | CLB-MP-HAUL-DT198 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 88600 | 47564 | 7500
500117117 | CLB-MP-HAUL-DT198 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 88600 | 47564 | 7500
500117832 | CLB-MP-HAUL-DT197 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 86138 | 47609 | 7500
500117792 | CLB-MP-HAUL-DT197 -AHSYST-CTRLH-ECMA6 | ECM A6 | 86138 | 47609 | 7500
500117754 | CLB-MP-HAUL-DT197 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 86138 | 47609 | 7500
500117714 | CLB-MP-HAUL-DT197 -AHSYST-CTRLH-LIDAR | AHS Lidar | 86163 | 12489 | 7500
500117676 | CLB-MP-HAUL-DT197 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 86138 | 47609 | 7500
500117636 | CLB-MP-HAUL-DT197 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 86138 | 47609 | 7500
500117596 | CLB-MP-HAUL-DT197 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 86138 | 47609 | 7500
500117556 | CLB-MP-HAUL-DT197 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 86138 | 47609 | 7500
500117516 | CLB-MP-HAUL-DT197 -AHSYST-AHSMF | AHS System Mounts & Frames | 86138 | 47609 | 7500
500117476 | CLB-MP-HAUL-DT197 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 86138 | 47609 | 7500
500117396 | CLB-MP-HAUL-DT197 -AHSYST-SNSRS | AHS Sensors | 86138 | 47609 | 7500
500117356 | CLB-MP-HAUL-DT197 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 86138 | 47609 | 7500
500117276 | CLB-MP-HAUL-DT197 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 86138 | 47609 | 7500
500117236 | CLB-MP-HAUL-DT197 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 86138 | 47609 | 7500
500117196 | CLB-MP-HAUL-DT197 -STRSYS-AHSEV | AHS EH Steering Valve | 86138 | 47609 | 7500
500117156 | CLB-MP-HAUL-DT197 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 86138 | 47609 | 7500
500117116 | CLB-MP-HAUL-DT197 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 86138 | 47609 | 7500
500117831 | CLB-MP-HAUL-DT196 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 85038 | 52536 | 7500
500117791 | CLB-MP-HAUL-DT196 -AHSYST-CTRLH-ECMA6 | ECM A6 | 85038 | 52536 | 7500
500117753 | CLB-MP-HAUL-DT196 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 85038 | 52536 | 7500
500117713 | CLB-MP-HAUL-DT196 -AHSYST-CTRLH-LIDAR | AHS Lidar | 85070 | 30228 | 7500
500117675 | CLB-MP-HAUL-DT196 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 85038 | 52536 | 7500
500117635 | CLB-MP-HAUL-DT196 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 85038 | 52536 | 7500
500117595 | CLB-MP-HAUL-DT196 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 85038 | 52536 | 7500
500117555 | CLB-MP-HAUL-DT196 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 85038 | 52536 | 7500
500117515 | CLB-MP-HAUL-DT196 -AHSYST-AHSMF | AHS System Mounts & Frames | 85038 | 52536 | 7500
500117475 | CLB-MP-HAUL-DT196 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 85038 | 52536 | 7500
500117395 | CLB-MP-HAUL-DT196 -AHSYST-SNSRS | AHS Sensors | 85038 | 52536 | 7500
500117355 | CLB-MP-HAUL-DT196 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 85038 | 52536 | 7500
500117275 | CLB-MP-HAUL-DT196 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 85038 | 52536 | 7500
500117235 | CLB-MP-HAUL-DT196 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 85038 | 52536 | 7500
500117195 | CLB-MP-HAUL-DT196 -STRSYS-AHSEV | AHS EH Steering Valve | 85038 | 52536 | 7500
500117155 | CLB-MP-HAUL-DT196 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 85038 | 52536 | 7500
500117115 | CLB-MP-HAUL-DT196 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 85038 | 52536 | 7500
500117830 | CLB-MP-HAUL-DT195 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 82430 | 50047 | 7500
500117790 | CLB-MP-HAUL-DT195 -AHSYST-CTRLH-ECMA6 | ECM A6 | 82430 | 50047 | 7500
500117752 | CLB-MP-HAUL-DT195 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 82430 | 50047 | 7500
500117712 | CLB-MP-HAUL-DT195 -AHSYST-CTRLH-LIDAR | AHS Lidar | 82448 | 15358 | 7500
500117674 | CLB-MP-HAUL-DT195 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 82430 | 50047 | 7500
500117634 | CLB-MP-HAUL-DT195 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 82430 | 50047 | 7500
500117594 | CLB-MP-HAUL-DT195 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 82430 | 50047 | 7500
500117554 | CLB-MP-HAUL-DT195 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 82430 | 50047 | 7500
500117514 | CLB-MP-HAUL-DT195 -AHSYST-AHSMF | AHS System Mounts & Frames | 82430 | 50047 | 7500
500117474 | CLB-MP-HAUL-DT195 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 82430 | 50047 | 7500
500117394 | CLB-MP-HAUL-DT195 -AHSYST-SNSRS | AHS Sensors | 82430 | 50047 | 7500
500117354 | CLB-MP-HAUL-DT195 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 82430 | 50047 | 7500
500117274 | CLB-MP-HAUL-DT195 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 82430 | 50047 | 7500
500117234 | CLB-MP-HAUL-DT195 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 82430 | 50047 | 7500
500117194 | CLB-MP-HAUL-DT195 -STRSYS-AHSEV | AHS EH Steering Valve | 82430 | 50047 | 7500
500117154 | CLB-MP-HAUL-DT195 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 82430 | 50047 | 7500
500117114 | CLB-MP-HAUL-DT195 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 82430 | 50047 | 7500
500117829 | CLB-MP-HAUL-DT194 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 86451 | 46687 | 7500
500117789 | CLB-MP-HAUL-DT194 -AHSYST-CTRLH-ECMA6 | ECM A6 | 86451 | 46687 | 7500
500117751 | CLB-MP-HAUL-DT194 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 86451 | 14133 | 7500
500117711 | CLB-MP-HAUL-DT194 -AHSYST-CTRLH-LIDAR | AHS Lidar | 86451 | 39009 | 7500
500117673 | CLB-MP-HAUL-DT194 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 86451 | 19096 | 7500
500117633 | CLB-MP-HAUL-DT194 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 86451 | 46687 | 7500
500117593 | CLB-MP-HAUL-DT194 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 86451 | 46687 | 7500
500117553 | CLB-MP-HAUL-DT194 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 86451 | 46687 | 7500
500117513 | CLB-MP-HAUL-DT194 -AHSYST-AHSMF | AHS System Mounts & Frames | 86451 | 46687 | 7500
500117473 | CLB-MP-HAUL-DT194 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 86451 | 46687 | 7500
500117393 | CLB-MP-HAUL-DT194 -AHSYST-SNSRS | AHS Sensors | 86451 | 46687 | 7500
500117353 | CLB-MP-HAUL-DT194 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 86451 | 46687 | 7500
500117273 | CLB-MP-HAUL-DT194 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 86451 | 46687 | 7500
500117233 | CLB-MP-HAUL-DT194 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 86451 | 46687 | 7500
500117193 | CLB-MP-HAUL-DT194 -STRSYS-AHSEV | AHS EH Steering Valve | 86451 | 15565 | 7500
500117153 | CLB-MP-HAUL-DT194 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 86451 | 46687 | 7500
500117113 | CLB-MP-HAUL-DT194 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 86451 | 46687 | 7500
500117828 | CLB-MP-HAUL-DT193 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83019 | 52523 | 7500
500117788 | CLB-MP-HAUL-DT193 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83019 | 52523 | 7500
500117750 | CLB-MP-HAUL-DT193 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83019 | 18661 | 7500
500117710 | CLB-MP-HAUL-DT193 -AHSYST-CTRLH-LIDAR | AHS Lidar | 83053 | 40279 | 7500
500117672 | CLB-MP-HAUL-DT193 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83019 | 52523 | 7500
500117632 | CLB-MP-HAUL-DT193 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83019 | 52523 | 7500
500117592 | CLB-MP-HAUL-DT193 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83019 | 52523 | 7500
500117552 | CLB-MP-HAUL-DT193 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83019 | 52523 | 7500
500117512 | CLB-MP-HAUL-DT193 -AHSYST-AHSMF | AHS System Mounts & Frames | 83019 | 52523 | 7500
500117472 | CLB-MP-HAUL-DT193 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83019 | 52523 | 7500
500117392 | CLB-MP-HAUL-DT193 -AHSYST-SNSRS | AHS Sensors | 83019 | 52523 | 7500
500117352 | CLB-MP-HAUL-DT193 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83019 | 52523 | 7500
500117272 | CLB-MP-HAUL-DT193 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83019 | 52523 | 7500
500117232 | CLB-MP-HAUL-DT193 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83019 | 52523 | 7500
500117192 | CLB-MP-HAUL-DT193 -STRSYS-AHSEV | AHS EH Steering Valve | 83019 | 52523 | 7500
500117152 | CLB-MP-HAUL-DT193 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83019 | 52523 | 7500
500117112 | CLB-MP-HAUL-DT193 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83019 | 52523 | 7500
500117827 | CLB-MP-HAUL-DT192 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 91058 | 44238 | 7500
500117787 | CLB-MP-HAUL-DT192 -AHSYST-CTRLH-ECMA6 | ECM A6 | 91058 | 44238 | 7500
500117749 | CLB-MP-HAUL-DT192 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 91058 | 44238 | 7500
500117709 | CLB-MP-HAUL-DT192 -AHSYST-CTRLH-LIDAR | AHS Lidar | 91071 | 44293 | 7500
500117671 | CLB-MP-HAUL-DT192 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 91058 | 44238 | 7500
500117631 | CLB-MP-HAUL-DT192 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 91058 | 44238 | 7500
500117591 | CLB-MP-HAUL-DT192 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 91058 | 44238 | 7500
500117551 | CLB-MP-HAUL-DT192 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 91058 | 44238 | 7500
500117511 | CLB-MP-HAUL-DT192 -AHSYST-AHSMF | AHS System Mounts & Frames | 91058 | 44238 | 7500
500117471 | CLB-MP-HAUL-DT192 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 91058 | 44238 | 7500
500117391 | CLB-MP-HAUL-DT192 -AHSYST-SNSRS | AHS Sensors | 91058 | 44238 | 7500
500117351 | CLB-MP-HAUL-DT192 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 91058 | 44238 | 7500
500117271 | CLB-MP-HAUL-DT192 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 91058 | 44238 | 7500
500117231 | CLB-MP-HAUL-DT192 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 91058 | 44238 | 7500
500117191 | CLB-MP-HAUL-DT192 -STRSYS-AHSEV | AHS EH Steering Valve | 91058 | 44238 | 7500
500117151 | CLB-MP-HAUL-DT192 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 91058 | 44238 | 7500
500117111 | CLB-MP-HAUL-DT192 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 91058 | 44238 | 7500
500117826 | CLB-MP-HAUL-DT191 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 86925 | 53610 | 7500
500117786 | CLB-MP-HAUL-DT191 -AHSYST-CTRLH-ECMA6 | ECM A6 | 86925 | 53610 | 7500
500117748 | CLB-MP-HAUL-DT191 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 86925 | 53610 | 7500
500117708 | CLB-MP-HAUL-DT191 -AHSYST-CTRLH-LIDAR | AHS Lidar | 86941 | 35419 | 7500
500117670 | CLB-MP-HAUL-DT191 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 86925 | 15564 | 7500
500117630 | CLB-MP-HAUL-DT191 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 86925 | 53610 | 7500
500117590 | CLB-MP-HAUL-DT191 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 86925 | 53610 | 7500
500117550 | CLB-MP-HAUL-DT191 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 86925 | 53610 | 7500
500117510 | CLB-MP-HAUL-DT191 -AHSYST-AHSMF | AHS System Mounts & Frames | 86925 | 53610 | 7500
500117470 | CLB-MP-HAUL-DT191 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 86925 | 53610 | 7500
500117390 | CLB-MP-HAUL-DT191 -AHSYST-SNSRS | AHS Sensors | 86925 | 53610 | 7500
500117350 | CLB-MP-HAUL-DT191 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 86925 | 53610 | 7500
500117270 | CLB-MP-HAUL-DT191 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 86925 | 53610 | 7500
500117230 | CLB-MP-HAUL-DT191 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 86925 | 53610 | 7500
500117190 | CLB-MP-HAUL-DT191 -STRSYS-AHSEV | AHS EH Steering Valve | 86925 | 53610 | 7500
500117150 | CLB-MP-HAUL-DT191 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 86925 | 53610 | 7500
500117110 | CLB-MP-HAUL-DT191 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 86925 | 53610 | 7500
500117825 | CLB-MP-HAUL-DT190 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 90611 | 46772 | 7500
500117785 | CLB-MP-HAUL-DT190 -AHSYST-CTRLH-ECMA6 | ECM A6 | 90611 | 28387 | 7500
500117747 | CLB-MP-HAUL-DT190 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 90611 | 15614 | 7500
500117707 | CLB-MP-HAUL-DT190 -AHSYST-CTRLH-LIDAR | AHS Lidar | 90629 | 10715 | 7500
500117669 | CLB-MP-HAUL-DT190 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 90611 | 46772 | 7500
500117629 | CLB-MP-HAUL-DT190 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 90611 | 46772 | 7500
500117589 | CLB-MP-HAUL-DT190 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 90611 | 46772 | 7500
500117549 | CLB-MP-HAUL-DT190 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 90611 | 46772 | 7500
500117509 | CLB-MP-HAUL-DT190 -AHSYST-AHSMF | AHS System Mounts & Frames | 90611 | 46772 | 7500
500117469 | CLB-MP-HAUL-DT190 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 90611 | 46772 | 7500
500117389 | CLB-MP-HAUL-DT190 -AHSYST-SNSRS | AHS Sensors | 90611 | 46772 | 7500
500117349 | CLB-MP-HAUL-DT190 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 90611 | 46772 | 7500
500117269 | CLB-MP-HAUL-DT190 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 90611 | 46772 | 7500
500117229 | CLB-MP-HAUL-DT190 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 90611 | 46772 | 7500
500117189 | CLB-MP-HAUL-DT190 -STRSYS-AHSEV | AHS EH Steering Valve | 90611 | 46772 | 7500
500117149 | CLB-MP-HAUL-DT190 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 90611 | 46772 | 7500
500117109 | CLB-MP-HAUL-DT190 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 90611 | 46772 | 7500
500117824 | CLB-MP-HAUL-DT189 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 84424 | 53093 | 7500
500117784 | CLB-MP-HAUL-DT189 -AHSYST-CTRLH-ECMA6 | ECM A6 | 84424 | 53093 | 7500
500117746 | CLB-MP-HAUL-DT189 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 84424 | 53093 | 7500
500117706 | CLB-MP-HAUL-DT189 -AHSYST-CTRLH-LIDAR | AHS Lidar | 84424 | 31343 | 7500
500117668 | CLB-MP-HAUL-DT189 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 84424 | 53093 | 7500
500117628 | CLB-MP-HAUL-DT189 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 84424 | 53093 | 7500
500117588 | CLB-MP-HAUL-DT189 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 84424 | 53093 | 7500
500117548 | CLB-MP-HAUL-DT189 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 84424 | 53093 | 7500
500117508 | CLB-MP-HAUL-DT189 -AHSYST-AHSMF | AHS System Mounts & Frames | 84424 | 53093 | 7500
500117468 | CLB-MP-HAUL-DT189 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 84424 | 53093 | 7500
500117388 | CLB-MP-HAUL-DT189 -AHSYST-SNSRS | AHS Sensors | 84424 | 53093 | 7500
500117348 | CLB-MP-HAUL-DT189 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 84424 | 53093 | 7500
500117268 | CLB-MP-HAUL-DT189 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 84424 | 53093 | 7500
500117228 | CLB-MP-HAUL-DT189 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 84424 | 53093 | 7500
500117188 | CLB-MP-HAUL-DT189 -STRSYS-AHSEV | AHS EH Steering Valve | 84424 | 53093 | 7500
500117148 | CLB-MP-HAUL-DT189 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 84424 | 53093 | 7500
500117108 | CLB-MP-HAUL-DT189 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 84424 | 53093 | 7500
500117823 | CLB-MP-HAUL-DT188 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83809 | 52210 | 7500
500117783 | CLB-MP-HAUL-DT188 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83809 | 9684 | 7500
500117745 | CLB-MP-HAUL-DT188 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83809 | 52210 | 7500
500117705 | CLB-MP-HAUL-DT188 -AHSYST-CTRLH-LIDAR | AHS Lidar | 83866 | 15462 | 7500
500117667 | CLB-MP-HAUL-DT188 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83809 | 52210 | 7500
500117627 | CLB-MP-HAUL-DT188 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83809 | 52210 | 7500
500117587 | CLB-MP-HAUL-DT188 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83809 | 52210 | 7500
500117547 | CLB-MP-HAUL-DT188 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83809 | 52210 | 7500
500117507 | CLB-MP-HAUL-DT188 -AHSYST-AHSMF | AHS System Mounts & Frames | 83809 | 52210 | 7500
500117467 | CLB-MP-HAUL-DT188 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83809 | 52210 | 7500
500117387 | CLB-MP-HAUL-DT188 -AHSYST-SNSRS | AHS Sensors | 83809 | 52210 | 7500
500117347 | CLB-MP-HAUL-DT188 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83809 | 52210 | 7500
500117267 | CLB-MP-HAUL-DT188 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83809 | 52210 | 7500
500117227 | CLB-MP-HAUL-DT188 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83809 | 52210 | 7500
500117187 | CLB-MP-HAUL-DT188 -STRSYS-AHSEV | AHS EH Steering Valve | 83809 | 52210 | 7500
500117147 | CLB-MP-HAUL-DT188 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83809 | 52210 | 7500
500117107 | CLB-MP-HAUL-DT188 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83809 | 52210 | 7500
500117822 | CLB-MP-HAUL-DT187 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 93064 | 45695 | 7500
500117782 | CLB-MP-HAUL-DT187 -AHSYST-CTRLH-ECMA6 | ECM A6 | 93064 | 45695 | 7500
500117744 | CLB-MP-HAUL-DT187 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 93064 | 22560 | 7500
500117704 | CLB-MP-HAUL-DT187 -AHSYST-CTRLH-LIDAR | AHS Lidar | 93065 | 10469 | 7500
500117666 | CLB-MP-HAUL-DT187 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 93064 | 45695 | 7500
500117626 | CLB-MP-HAUL-DT187 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 93064 | 45695 | 7500
500117586 | CLB-MP-HAUL-DT187 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 93064 | 45695 | 7500
500117546 | CLB-MP-HAUL-DT187 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 93064 | 45695 | 7500
500117506 | CLB-MP-HAUL-DT187 -AHSYST-AHSMF | AHS System Mounts & Frames | 93064 | 45695 | 7500
500117466 | CLB-MP-HAUL-DT187 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 93064 | 45695 | 7500
500117386 | CLB-MP-HAUL-DT187 -AHSYST-SNSRS | AHS Sensors | 93064 | 45695 | 7500
500117346 | CLB-MP-HAUL-DT187 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 93064 | 45695 | 7500
500117266 | CLB-MP-HAUL-DT187 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 93064 | 45695 | 7500
500117226 | CLB-MP-HAUL-DT187 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 93064 | 45695 | 7500
500117186 | CLB-MP-HAUL-DT187 -STRSYS-AHSEV | AHS EH Steering Valve | 93064 | 45695 | 7500
500117146 | CLB-MP-HAUL-DT187 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 93064 | 45695 | 7500
500117106 | CLB-MP-HAUL-DT187 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 93064 | 45695 | 7500
500117821 | CLB-MP-HAUL-DT186 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 89630 | 42996 | 7500
500117781 | CLB-MP-HAUL-DT186 -AHSYST-CTRLH-ECMA6 | ECM A6 | 89630 | 27338 | 7500
500117743 | CLB-MP-HAUL-DT186 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 89630 | 9823 | 7500
500117703 | CLB-MP-HAUL-DT186 -AHSYST-CTRLH-LIDAR | AHS Lidar | 89630 | 15397 | 7500
500117665 | CLB-MP-HAUL-DT186 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 89630 | 42996 | 7500
500117625 | CLB-MP-HAUL-DT186 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 89630 | 42996 | 7500
500117585 | CLB-MP-HAUL-DT186 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 89630 | 42996 | 7500
500117545 | CLB-MP-HAUL-DT186 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 89630 | 42996 | 7500
500117505 | CLB-MP-HAUL-DT186 -AHSYST-AHSMF | AHS System Mounts & Frames | 89630 | 42996 | 7500
500117465 | CLB-MP-HAUL-DT186 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 89630 | 42996 | 7500
500117385 | CLB-MP-HAUL-DT186 -AHSYST-SNSRS | AHS Sensors | 89630 | 42996 | 7500
500117345 | CLB-MP-HAUL-DT186 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 89630 | 42996 | 7500
500117265 | CLB-MP-HAUL-DT186 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 89630 | 42996 | 7500
500117225 | CLB-MP-HAUL-DT186 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 89630 | 42996 | 7500
500117185 | CLB-MP-HAUL-DT186 -STRSYS-AHSEV | AHS EH Steering Valve | 89630 | 23365 | 7500
500117145 | CLB-MP-HAUL-DT186 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 89630 | 42996 | 7500
500117105 | CLB-MP-HAUL-DT186 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 89630 | 42996 | 7500
500117820 | CLB-MP-HAUL-DT185 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 91965 | 43942 | 7500
500117780 | CLB-MP-HAUL-DT185 -AHSYST-CTRLH-ECMA6 | ECM A6 | 91965 | 43942 | 7500
500117742 | CLB-MP-HAUL-DT185 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 91965 | 43942 | 7500
500117702 | CLB-MP-HAUL-DT185 -AHSYST-CTRLH-LIDAR | AHS Lidar | 91965 | 43948 | 7500
500117664 | CLB-MP-HAUL-DT185 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 91965 | 43942 | 7500
500117624 | CLB-MP-HAUL-DT185 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 91965 | 43942 | 7500
500117584 | CLB-MP-HAUL-DT185 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 91965 | 43942 | 7500
500117544 | CLB-MP-HAUL-DT185 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 91965 | 43942 | 7500
500117504 | CLB-MP-HAUL-DT185 -AHSYST-AHSMF | AHS System Mounts & Frames | 91965 | 43942 | 7500
500117464 | CLB-MP-HAUL-DT185 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 91965 | 43942 | 7500
500117384 | CLB-MP-HAUL-DT185 -AHSYST-SNSRS | AHS Sensors | 91965 | 43942 | 7500
500117344 | CLB-MP-HAUL-DT185 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 91965 | 43942 | 7500
500117264 | CLB-MP-HAUL-DT185 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 91965 | 43942 | 7500
500117224 | CLB-MP-HAUL-DT185 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 91965 | 43942 | 7500
500117184 | CLB-MP-HAUL-DT185 -STRSYS-AHSEV | AHS EH Steering Valve | 91965 | 43942 | 7500
500117144 | CLB-MP-HAUL-DT185 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 91965 | 43942 | 7500
500117104 | CLB-MP-HAUL-DT185 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 91965 | 43942 | 7500
500117819 | CLB-MP-HAUL-DT184 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83351 | 50693 | 7500
500117779 | CLB-MP-HAUL-DT184 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83351 | 25411 | 7500
500117741 | CLB-MP-HAUL-DT184 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83351 | 17738 | 7500
500117701 | CLB-MP-HAUL-DT184 -AHSYST-CTRLH-LIDAR | AHS Lidar | 112969 | 15022 | 7500
500117663 | CLB-MP-HAUL-DT184 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83351 | 50693 | 7500
500117623 | CLB-MP-HAUL-DT184 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83351 | 50693 | 7500
500117583 | CLB-MP-HAUL-DT184 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83351 | 50693 | 7500
500117543 | CLB-MP-HAUL-DT184 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83351 | 50693 | 7500
500117503 | CLB-MP-HAUL-DT184 -AHSYST-AHSMF | AHS System Mounts & Frames | 83351 | 50693 | 7500
500117463 | CLB-MP-HAUL-DT184 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83351 | 50693 | 7500
500117383 | CLB-MP-HAUL-DT184 -AHSYST-SNSRS | AHS Sensors | 83351 | 50693 | 7500
500117343 | CLB-MP-HAUL-DT184 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83351 | 50693 | 7500
500117263 | CLB-MP-HAUL-DT184 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83351 | 50693 | 7500
500117223 | CLB-MP-HAUL-DT184 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83351 | 50693 | 7500
500117183 | CLB-MP-HAUL-DT184 -STRSYS-AHSEV | AHS EH Steering Valve | 83351 | 50693 | 7500
500117143 | CLB-MP-HAUL-DT184 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83351 | 50693 | 7500
500117103 | CLB-MP-HAUL-DT184 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83351 | 50693 | 7500
500117818 | CLB-MP-HAUL-DT183 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 90142 | 46111 | 7500
500117778 | CLB-MP-HAUL-DT183 -AHSYST-CTRLH-ECMA6 | ECM A6 | 90142 | 46111 | 7500
500117740 | CLB-MP-HAUL-DT183 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 90142 | 18359 | 7500
500117700 | CLB-MP-HAUL-DT183 -AHSYST-CTRLH-LIDAR | AHS Lidar | 90150 | 8842 | 7500
500117662 | CLB-MP-HAUL-DT183 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 90142 | 46111 | 7500
500117622 | CLB-MP-HAUL-DT183 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 90142 | 46111 | 7500
500117582 | CLB-MP-HAUL-DT183 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 90142 | 46111 | 7500
500117542 | CLB-MP-HAUL-DT183 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 90142 | 46111 | 7500
500117502 | CLB-MP-HAUL-DT183 -AHSYST-AHSMF | AHS System Mounts & Frames | 90142 | 46111 | 7500
500117462 | CLB-MP-HAUL-DT183 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 90142 | 46111 | 7500
500117382 | CLB-MP-HAUL-DT183 -AHSYST-SNSRS | AHS Sensors | 90142 | 46111 | 7500
500117342 | CLB-MP-HAUL-DT183 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 90142 | 46111 | 7500
500117262 | CLB-MP-HAUL-DT183 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 90142 | 46111 | 7500
500117222 | CLB-MP-HAUL-DT183 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 90142 | 46111 | 7500
500117182 | CLB-MP-HAUL-DT183 -STRSYS-AHSEV | AHS EH Steering Valve | 90142 | 46111 | 7500
500117142 | CLB-MP-HAUL-DT183 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 90142 | 46111 | 7500
500117102 | CLB-MP-HAUL-DT183 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 90142 | 46111 | 7500
500117817 | CLB-MP-HAUL-DT182 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 91879 | 45872 | 7500
500117777 | CLB-MP-HAUL-DT182 -AHSYST-CTRLH-ECMA6 | ECM A6 | 91879 | 24586 | 7500
500117739 | CLB-MP-HAUL-DT182 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 91879 | 45872 | 7500
500117699 | CLB-MP-HAUL-DT182 -AHSYST-CTRLH-LIDAR | AHS Lidar | 91911 | 46502 | 7500
500117661 | CLB-MP-HAUL-DT182 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 91879 | 45872 | 7500
500117621 | CLB-MP-HAUL-DT182 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 91879 | 45872 | 7500
500117581 | CLB-MP-HAUL-DT182 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 91879 | 45872 | 7500
500117541 | CLB-MP-HAUL-DT182 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 91879 | 45872 | 7500
500117501 | CLB-MP-HAUL-DT182 -AHSYST-AHSMF | AHS System Mounts & Frames | 91879 | 45872 | 7500
500117461 | CLB-MP-HAUL-DT182 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 91879 | 45872 | 7500
500117381 | CLB-MP-HAUL-DT182 -AHSYST-SNSRS | AHS Sensors | 91879 | 45872 | 7500
500117341 | CLB-MP-HAUL-DT182 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 91879 | 45872 | 7500
500117261 | CLB-MP-HAUL-DT182 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 91879 | 45872 | 7500
500117221 | CLB-MP-HAUL-DT182 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 91879 | 45872 | 7500
500117181 | CLB-MP-HAUL-DT182 -STRSYS-AHSEV | AHS EH Steering Valve | 91879 | 27613 | 7500
500117141 | CLB-MP-HAUL-DT182 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 91879 | 45872 | 7500
500117101 | CLB-MP-HAUL-DT182 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 91879 | 45872 | 7500
500117816 | CLB-MP-HAUL-DT181 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83318 | 50159 | 7500
500117776 | CLB-MP-HAUL-DT181 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83318 | 50159 | 7500
500117738 | CLB-MP-HAUL-DT181 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83318 | 50159 | 7500
500117698 | CLB-MP-HAUL-DT181 -AHSYST-CTRLH-LIDAR | AHS Lidar | 109791 | 10108 | 7500
500117660 | CLB-MP-HAUL-DT181 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83318 | 50159 | 7500
500117620 | CLB-MP-HAUL-DT181 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83318 | 50159 | 7500
500117580 | CLB-MP-HAUL-DT181 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83318 | 50159 | 7500
500117540 | CLB-MP-HAUL-DT181 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83318 | 50159 | 7500
500117500 | CLB-MP-HAUL-DT181 -AHSYST-AHSMF | AHS System Mounts & Frames | 83318 | 50159 | 7500
500117460 | CLB-MP-HAUL-DT181 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83318 | 50159 | 7500
500117380 | CLB-MP-HAUL-DT181 -AHSYST-SNSRS | AHS Sensors | 83318 | 50159 | 7500
500117340 | CLB-MP-HAUL-DT181 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83318 | 50159 | 7500
500117260 | CLB-MP-HAUL-DT181 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83318 | 50159 | 7500
500117220 | CLB-MP-HAUL-DT181 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83318 | 50159 | 7500
500117180 | CLB-MP-HAUL-DT181 -STRSYS-AHSEV | AHS EH Steering Valve | 83318 | 50159 | 7500
500117140 | CLB-MP-HAUL-DT181 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83318 | 50159 | 7500
500117100 | CLB-MP-HAUL-DT181 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83318 | 50159 | 7500
500117815 | CLB-MP-HAUL-DT180 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 89437 | 46108 | 7500
500117775 | CLB-MP-HAUL-DT180 -AHSYST-CTRLH-ECMA6 | ECM A6 | 89437 | 46108 | 7500
500117737 | CLB-MP-HAUL-DT180 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 89437 | 20044 | 7500
500117697 | CLB-MP-HAUL-DT180 -AHSYST-CTRLH-LIDAR | AHS Lidar | 89487 | 46204 | 7500
500117659 | CLB-MP-HAUL-DT180 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 89437 | 46108 | 7500
500117619 | CLB-MP-HAUL-DT180 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 89437 | 46108 | 7500
500117579 | CLB-MP-HAUL-DT180 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 89437 | 46108 | 7500
500117539 | CLB-MP-HAUL-DT180 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 89437 | 46108 | 7500
500117499 | CLB-MP-HAUL-DT180 -AHSYST-AHSMF | AHS System Mounts & Frames | 89437 | 46108 | 7500
500117459 | CLB-MP-HAUL-DT180 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 89437 | 46108 | 7500
500117379 | CLB-MP-HAUL-DT180 -AHSYST-SNSRS | AHS Sensors | 89437 | 46108 | 7500
500117339 | CLB-MP-HAUL-DT180 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 89437 | 46108 | 7500
500117259 | CLB-MP-HAUL-DT180 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 89437 | 46108 | 7500
500117219 | CLB-MP-HAUL-DT180 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 89437 | 46108 | 7500
500117179 | CLB-MP-HAUL-DT180 -STRSYS-AHSEV | AHS EH Steering Valve | 89437 | 46108 | 7500
500117139 | CLB-MP-HAUL-DT180 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 89437 | 46108 | 7500
500117099 | CLB-MP-HAUL-DT180 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 89437 | 46108 | 7500
500117814 | CLB-MP-HAUL-DT179 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83956 | 51850 | 7500
500117774 | CLB-MP-HAUL-DT179 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83956 | 15893 | 7500
500117736 | CLB-MP-HAUL-DT179 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83956 | 51850 | 7500
500117696 | CLB-MP-HAUL-DT179 -AHSYST-CTRLH-LIDAR | AHS Lidar | 113840 | 45070 | 7500
500117658 | CLB-MP-HAUL-DT179 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83956 | 51850 | 7500
500117618 | CLB-MP-HAUL-DT179 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83956 | 51850 | 7500
500117578 | CLB-MP-HAUL-DT179 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83956 | 51850 | 7500
500117538 | CLB-MP-HAUL-DT179 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83956 | 51850 | 7500
500117498 | CLB-MP-HAUL-DT179 -AHSYST-AHSMF | AHS System Mounts & Frames | 83956 | 51850 | 7500
500117458 | CLB-MP-HAUL-DT179 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83956 | 51850 | 7500
500117378 | CLB-MP-HAUL-DT179 -AHSYST-SNSRS | AHS Sensors | 83956 | 51850 | 7500
500117338 | CLB-MP-HAUL-DT179 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83956 | 51850 | 7500
500117258 | CLB-MP-HAUL-DT179 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83956 | 51850 | 7500
500117218 | CLB-MP-HAUL-DT179 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83956 | 51850 | 7500
500117178 | CLB-MP-HAUL-DT179 -STRSYS-AHSEV | AHS EH Steering Valve | 83956 | 51850 | 7500
500117138 | CLB-MP-HAUL-DT179 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83956 | 51850 | 7500
500117098 | CLB-MP-HAUL-DT179 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83956 | 51850 | 7500
500117813 | CLB-MP-HAUL-DT178 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 81477 | 49151 | 7500
500117773 | CLB-MP-HAUL-DT178 -AHSYST-CTRLH-ECMA6 | ECM A6 | 81477 | 49151 | 7500
500117735 | CLB-MP-HAUL-DT178 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 81477 | 49151 | 7500
500117695 | CLB-MP-HAUL-DT178 -AHSYST-CTRLH-LIDAR | AHS Lidar | 81479 | 41654 | 7500
500117657 | CLB-MP-HAUL-DT178 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 81477 | 49151 | 7500
500117617 | CLB-MP-HAUL-DT178 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 81477 | 49151 | 7500
500117577 | CLB-MP-HAUL-DT178 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 81477 | 49151 | 7500
500117537 | CLB-MP-HAUL-DT178 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 81477 | 49151 | 7500
500117497 | CLB-MP-HAUL-DT178 -AHSYST-AHSMF | AHS System Mounts & Frames | 81477 | 49151 | 7500
500117457 | CLB-MP-HAUL-DT178 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 81477 | 49151 | 7500
500117377 | CLB-MP-HAUL-DT178 -AHSYST-SNSRS | AHS Sensors | 81477 | 49151 | 7500
500117337 | CLB-MP-HAUL-DT178 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 81477 | 49151 | 7500
500117257 | CLB-MP-HAUL-DT178 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 81477 | 49151 | 7500
500117217 | CLB-MP-HAUL-DT178 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 81477 | 49151 | 7500
500117177 | CLB-MP-HAUL-DT178 -STRSYS-AHSEV | AHS EH Steering Valve | 81477 | 49151 | 7500
500117137 | CLB-MP-HAUL-DT178 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 81477 | 49151 | 7500
500117097 | CLB-MP-HAUL-DT178 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 81477 | 49151 | 7500
500117812 | CLB-MP-HAUL-DT177 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 81669 | 50606 | 7500
500117772 | CLB-MP-HAUL-DT177 -AHSYST-CTRLH-ECMA6 | ECM A6 | 81669 | 50606 | 7500
500117734 | CLB-MP-HAUL-DT177 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 81669 | 50606 | 7500
500117694 | CLB-MP-HAUL-DT177 -AHSYST-CTRLH-LIDAR | AHS Lidar | 101220 | 9898 | 7500
500117656 | CLB-MP-HAUL-DT177 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 81669 | 50606 | 7500
500117616 | CLB-MP-HAUL-DT177 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 81669 | 50606 | 7500
500117576 | CLB-MP-HAUL-DT177 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 81669 | 50606 | 7500
500117536 | CLB-MP-HAUL-DT177 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 81669 | 50606 | 7500
500117496 | CLB-MP-HAUL-DT177 -AHSYST-AHSMF | AHS System Mounts & Frames | 81669 | 50606 | 7500
500117456 | CLB-MP-HAUL-DT177 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 81669 | 50606 | 7500
500117376 | CLB-MP-HAUL-DT177 -AHSYST-SNSRS | AHS Sensors | 81669 | 50606 | 7500
500117336 | CLB-MP-HAUL-DT177 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 81669 | 50606 | 7500
500117256 | CLB-MP-HAUL-DT177 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 81669 | 50606 | 7500
500117216 | CLB-MP-HAUL-DT177 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 81669 | 50606 | 7500
500117176 | CLB-MP-HAUL-DT177 -STRSYS-AHSEV | AHS EH Steering Valve | 81669 | 50606 | 7500
500117136 | CLB-MP-HAUL-DT177 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 81669 | 50606 | 7500
500117096 | CLB-MP-HAUL-DT177 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 81669 | 50606 | 7500
500117811 | CLB-MP-HAUL-DT176 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 85161 | 52147 | 7500
500117771 | CLB-MP-HAUL-DT176 -AHSYST-CTRLH-ECMA6 | ECM A6 | 85161 | 52147 | 7500
500117733 | CLB-MP-HAUL-DT176 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 85161 | 52147 | 7500
500117693 | CLB-MP-HAUL-DT176 -AHSYST-CTRLH-LIDAR | AHS Lidar | 85162 | 30580 | 7500
500117655 | CLB-MP-HAUL-DT176 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 85161 | 52147 | 7500
500117615 | CLB-MP-HAUL-DT176 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 85161 | 52147 | 7500
500117575 | CLB-MP-HAUL-DT176 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 85161 | 52147 | 7500
500117535 | CLB-MP-HAUL-DT176 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 85161 | 52147 | 7500
500117495 | CLB-MP-HAUL-DT176 -AHSYST-AHSMF | AHS System Mounts & Frames | 85161 | 52147 | 7500
500117455 | CLB-MP-HAUL-DT176 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 85161 | 52147 | 7500
500117375 | CLB-MP-HAUL-DT176 -AHSYST-SNSRS | AHS Sensors | 85161 | 52147 | 7500
500117335 | CLB-MP-HAUL-DT176 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 85161 | 52147 | 7500
500117255 | CLB-MP-HAUL-DT176 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 85161 | 52147 | 7500
500117215 | CLB-MP-HAUL-DT176 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 85161 | 52147 | 7500
500117175 | CLB-MP-HAUL-DT176 -STRSYS-AHSEV | AHS EH Steering Valve | 85161 | 52147 | 7500
500117135 | CLB-MP-HAUL-DT176 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 85161 | 52147 | 7500
500117095 | CLB-MP-HAUL-DT176 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 85161 | 52147 | 7500
500117810 | CLB-MP-HAUL-DT175 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 82597 | 50582 | 7500
500117770 | CLB-MP-HAUL-DT175 -AHSYST-CTRLH-ECMA6 | ECM A6 | 82597 | 23065 | 7500
500117732 | CLB-MP-HAUL-DT175 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 82597 | 18948 | 7500
500117692 | CLB-MP-HAUL-DT175 -AHSYST-CTRLH-LIDAR | AHS Lidar | 82622 | 45098 | 7500
500117654 | CLB-MP-HAUL-DT175 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 82597 | 50582 | 7500
500117614 | CLB-MP-HAUL-DT175 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 82597 | 50582 | 7500
500117574 | CLB-MP-HAUL-DT175 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 82597 | 50582 | 7500
500117534 | CLB-MP-HAUL-DT175 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 82597 | 50582 | 7500
500117494 | CLB-MP-HAUL-DT175 -AHSYST-AHSMF | AHS System Mounts & Frames | 82597 | 50582 | 7500
500117454 | CLB-MP-HAUL-DT175 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 82597 | 50582 | 7500
500117374 | CLB-MP-HAUL-DT175 -AHSYST-SNSRS | AHS Sensors | 82597 | 50582 | 7500
500117334 | CLB-MP-HAUL-DT175 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 82597 | 50582 | 7500
500117254 | CLB-MP-HAUL-DT175 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 82597 | 50582 | 7500
500117214 | CLB-MP-HAUL-DT175 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 82597 | 50582 | 7500
500117174 | CLB-MP-HAUL-DT175 -STRSYS-AHSEV | AHS EH Steering Valve | 82597 | 50582 | 7500
500117134 | CLB-MP-HAUL-DT175 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 82597 | 50582 | 7500
500117094 | CLB-MP-HAUL-DT175 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 82597 | 50582 | 7500
500117809 | CLB-MP-HAUL-DT174 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83639 | 54299 | 7500
500117769 | CLB-MP-HAUL-DT174 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83639 | 54299 | 7500
500117731 | CLB-MP-HAUL-DT174 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83639 | 54299 | 7500
500117691 | CLB-MP-HAUL-DT174 -AHSYST-CTRLH-LIDAR | AHS Lidar | 83662 | 39738 | 7500
500117653 | CLB-MP-HAUL-DT174 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83639 | 54299 | 7500
500117613 | CLB-MP-HAUL-DT174 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83639 | 54299 | 7500
500117573 | CLB-MP-HAUL-DT174 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83639 | 54299 | 7500
500117533 | CLB-MP-HAUL-DT174 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83639 | 54299 | 7500
500117493 | CLB-MP-HAUL-DT174 -AHSYST-AHSMF | AHS System Mounts & Frames | 83639 | 54299 | 7500
500117453 | CLB-MP-HAUL-DT174 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83639 | 54299 | 7500
500117373 | CLB-MP-HAUL-DT174 -AHSYST-SNSRS | AHS Sensors | 83639 | 54299 | 7500
500117333 | CLB-MP-HAUL-DT174 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83639 | 54299 | 7500
500117253 | CLB-MP-HAUL-DT174 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83639 | 54299 | 7500
500117213 | CLB-MP-HAUL-DT174 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83639 | 54299 | 7500
500117173 | CLB-MP-HAUL-DT174 -STRSYS-AHSEV | AHS EH Steering Valve | 83639 | 54299 | 7500
500117133 | CLB-MP-HAUL-DT174 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83639 | 54299 | 7500
500117093 | CLB-MP-HAUL-DT174 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83639 | 54299 | 7500
500117808 | CLB-MP-HAUL-DT173 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 82529 | 49663 | 7500
500117768 | CLB-MP-HAUL-DT173 -AHSYST-CTRLH-ECMA6 | ECM A6 | 82529 | 49663 | 7500
500117730 | CLB-MP-HAUL-DT173 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 82529 | 49663 | 7500
500117690 | CLB-MP-HAUL-DT173 -AHSYST-CTRLH-LIDAR | AHS Lidar | 82545 | 37947 | 7500
500117652 | CLB-MP-HAUL-DT173 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 82529 | 49663 | 7500
500117612 | CLB-MP-HAUL-DT173 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 82529 | 49663 | 7500
500117572 | CLB-MP-HAUL-DT173 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 82529 | 49663 | 7500
500117532 | CLB-MP-HAUL-DT173 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 82529 | 49663 | 7500
500117492 | CLB-MP-HAUL-DT173 -AHSYST-AHSMF | AHS System Mounts & Frames | 82529 | 49663 | 7500
500117452 | CLB-MP-HAUL-DT173 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 82529 | 49663 | 7500
500117372 | CLB-MP-HAUL-DT173 -AHSYST-SNSRS | AHS Sensors | 82529 | 49663 | 7500
500117332 | CLB-MP-HAUL-DT173 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 82529 | 49663 | 7500
500117252 | CLB-MP-HAUL-DT173 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 82529 | 49663 | 7500
500117212 | CLB-MP-HAUL-DT173 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 82529 | 49663 | 7500
500117172 | CLB-MP-HAUL-DT173 -STRSYS-AHSEV | AHS EH Steering Valve | 82529 | 49663 | 7500
500117132 | CLB-MP-HAUL-DT173 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 82529 | 49663 | 7500
500117092 | CLB-MP-HAUL-DT173 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 82529 | 49663 | 7500
500117807 | CLB-MP-HAUL-DT172 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 92229 | 45430 | 7500
500117767 | CLB-MP-HAUL-DT172 -AHSYST-CTRLH-ECMA6 | ECM A6 | 92229 | 23392 | 7500
500117729 | CLB-MP-HAUL-DT172 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 92229 | 45430 | 7500
500117689 | CLB-MP-HAUL-DT172 -AHSYST-CTRLH-LIDAR | AHS Lidar | 92274 | 8840 | 7500
500117651 | CLB-MP-HAUL-DT172 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 92229 | 45430 | 7500
500117611 | CLB-MP-HAUL-DT172 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 92229 | 45430 | 7500
500117571 | CLB-MP-HAUL-DT172 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 92229 | 45430 | 7500
500117531 | CLB-MP-HAUL-DT172 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 92229 | 45430 | 7500
500117491 | CLB-MP-HAUL-DT172 -AHSYST-AHSMF | AHS System Mounts & Frames | 92229 | 45430 | 7500
500117451 | CLB-MP-HAUL-DT172 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 92229 | 45430 | 7500
500117371 | CLB-MP-HAUL-DT172 -AHSYST-SNSRS | AHS Sensors | 92229 | 45430 | 7500
500117331 | CLB-MP-HAUL-DT172 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 92229 | 45430 | 7500
500117251 | CLB-MP-HAUL-DT172 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 92229 | 45430 | 7500
500117211 | CLB-MP-HAUL-DT172 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 92229 | 45430 | 7500
500117171 | CLB-MP-HAUL-DT172 -STRSYS-AHSEV | AHS EH Steering Valve | 92229 | 45430 | 7500
500117131 | CLB-MP-HAUL-DT172 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 92229 | 45430 | 7500
500117091 | CLB-MP-HAUL-DT172 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 92229 | 45430 | 7500
500117806 | CLB-MP-HAUL-DT171 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 90064 | 43262 | 7500
500117766 | CLB-MP-HAUL-DT171 -AHSYST-CTRLH-ECMA6 | ECM A6 | 90064 | 43262 | 7500
500117728 | CLB-MP-HAUL-DT171 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 90064 | 43262 | 7500
500117688 | CLB-MP-HAUL-DT171 -AHSYST-CTRLH-LIDAR | AHS Lidar | 90086 | 43308 | 7500
500117650 | CLB-MP-HAUL-DT171 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 90064 | 43262 | 7500
500117610 | CLB-MP-HAUL-DT171 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 90064 | 43262 | 7500
500117570 | CLB-MP-HAUL-DT171 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 90064 | 43262 | 7500
500117530 | CLB-MP-HAUL-DT171 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 90064 | 43262 | 7500
500117490 | CLB-MP-HAUL-DT171 -AHSYST-AHSMF | AHS System Mounts & Frames | 90064 | 43262 | 7500
500117450 | CLB-MP-HAUL-DT171 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 90064 | 43262 | 7500
500117370 | CLB-MP-HAUL-DT171 -AHSYST-SNSRS | AHS Sensors | 90064 | 43262 | 7500
500117330 | CLB-MP-HAUL-DT171 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 90064 | 43262 | 7500
500117250 | CLB-MP-HAUL-DT171 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 90064 | 43262 | 7500
500117210 | CLB-MP-HAUL-DT171 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 90064 | 43262 | 7500
500117170 | CLB-MP-HAUL-DT171 -STRSYS-AHSEV | AHS EH Steering Valve | 90064 | 43262 | 7500
500117130 | CLB-MP-HAUL-DT171 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 90064 | 43262 | 7500
500117090 | CLB-MP-HAUL-DT171 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 90064 | 43262 | 7500
500117805 | CLB-MP-HAUL-DT170 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 91071 | 46703 | 7500
500117765 | CLB-MP-HAUL-DT170 -AHSYST-CTRLH-ECMA6 | ECM A6 | 91071 | 46703 | 7500
500117727 | CLB-MP-HAUL-DT170 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 91071 | 46703 | 7500
500117687 | CLB-MP-HAUL-DT170 -AHSYST-CTRLH-LIDAR | AHS Lidar | 91071 | 8914 | 7500
500117649 | CLB-MP-HAUL-DT170 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 91071 | 46703 | 7500
500117609 | CLB-MP-HAUL-DT170 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 91071 | 46703 | 7500
500117569 | CLB-MP-HAUL-DT170 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 91071 | 46703 | 7500
500117529 | CLB-MP-HAUL-DT170 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 91071 | 46703 | 7500
500117489 | CLB-MP-HAUL-DT170 -AHSYST-AHSMF | AHS System Mounts & Frames | 91071 | 46703 | 7500
500117449 | CLB-MP-HAUL-DT170 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 91071 | 46703 | 7500
500117369 | CLB-MP-HAUL-DT170 -AHSYST-SNSRS | AHS Sensors | 91071 | 46703 | 7500
500117329 | CLB-MP-HAUL-DT170 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 91071 | 46703 | 7500
500117249 | CLB-MP-HAUL-DT170 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 91071 | 46703 | 7500
500117209 | CLB-MP-HAUL-DT170 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 91071 | 46703 | 7500
500117169 | CLB-MP-HAUL-DT170 -STRSYS-AHSEV | AHS EH Steering Valve | 91071 | 46703 | 7500
500117129 | CLB-MP-HAUL-DT170 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 91071 | 46703 | 7500
500117089 | CLB-MP-HAUL-DT170 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 91071 | 46703 | 7500
500117804 | CLB-MP-HAUL-DT169 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 93287 | 48492 | 7500
500117764 | CLB-MP-HAUL-DT169 -AHSYST-CTRLH-ECMA6 | ECM A6 | 93287 | 15288 | 7500
500117726 | CLB-MP-HAUL-DT169 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 93287 | 48492 | 7500
500117686 | CLB-MP-HAUL-DT169 -AHSYST-CTRLH-LIDAR | AHS Lidar | 93318 | 12069 | 7500
500117648 | CLB-MP-HAUL-DT169 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 93287 | 48492 | 7500
500117608 | CLB-MP-HAUL-DT169 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 93287 | 48492 | 7500
500117568 | CLB-MP-HAUL-DT169 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 93287 | 48492 | 7500
500117528 | CLB-MP-HAUL-DT169 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 93287 | 48492 | 7500
500117488 | CLB-MP-HAUL-DT169 -AHSYST-AHSMF | AHS System Mounts & Frames | 93287 | 48492 | 7500
500117448 | CLB-MP-HAUL-DT169 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 93287 | 48492 | 7500
500117368 | CLB-MP-HAUL-DT169 -AHSYST-SNSRS | AHS Sensors | 93287 | 48492 | 7500
500117328 | CLB-MP-HAUL-DT169 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 93287 | 48492 | 7500
500117248 | CLB-MP-HAUL-DT169 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 93287 | 48492 | 7500
500117208 | CLB-MP-HAUL-DT169 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 93287 | 48492 | 7500
500117168 | CLB-MP-HAUL-DT169 -STRSYS-AHSEV | AHS EH Steering Valve | 93287 | 48492 | 7500
500117128 | CLB-MP-HAUL-DT169 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 93287 | 48492 | 7500
500117088 | CLB-MP-HAUL-DT169 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 93287 | 48492 | 7500
500117803 | CLB-MP-HAUL-DT168 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 93073 | 50273 | 7500
500117763 | CLB-MP-HAUL-DT168 -AHSYST-CTRLH-ECMA6 | ECM A6 | 93073 | 50273 | 7500
500117725 | CLB-MP-HAUL-DT168 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 93073 | 50273 | 7500
500117685 | CLB-MP-HAUL-DT168 -AHSYST-CTRLH-LIDAR | AHS Lidar | 93102 | 11034 | 7500
500117647 | CLB-MP-HAUL-DT168 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 93073 | 50273 | 7500
500117607 | CLB-MP-HAUL-DT168 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 93073 | 50273 | 7500
500117567 | CLB-MP-HAUL-DT168 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 93073 | 50273 | 7500
500117527 | CLB-MP-HAUL-DT168 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 93073 | 50273 | 7500
500117487 | CLB-MP-HAUL-DT168 -AHSYST-AHSMF | AHS System Mounts & Frames | 93073 | 50273 | 7500
500117447 | CLB-MP-HAUL-DT168 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 93073 | 50273 | 7500
500117367 | CLB-MP-HAUL-DT168 -AHSYST-SNSRS | AHS Sensors | 93073 | 50273 | 7500
500117327 | CLB-MP-HAUL-DT168 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 93073 | 50273 | 7500
500117247 | CLB-MP-HAUL-DT168 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 93073 | 50273 | 7500
500117207 | CLB-MP-HAUL-DT168 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 93073 | 50273 | 7500
500117167 | CLB-MP-HAUL-DT168 -STRSYS-AHSEV | AHS EH Steering Valve | 93073 | 50273 | 7500
500117127 | CLB-MP-HAUL-DT168 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 93073 | 50273 | 7500
500117087 | CLB-MP-HAUL-DT168 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 93073 | 50273 | 7500
500117802 | CLB-MP-HAUL-DT167 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 83223 | 50581 | 7500
500117762 | CLB-MP-HAUL-DT167 -AHSYST-CTRLH-ECMA6 | ECM A6 | 83223 | 50581 | 7500
500117724 | CLB-MP-HAUL-DT167 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 83223 | 50581 | 7500
500117684 | CLB-MP-HAUL-DT167 -AHSYST-CTRLH-LIDAR | AHS Lidar | 83249 | 30111 | 7500
500117646 | CLB-MP-HAUL-DT167 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 83223 | 50581 | 7500
500117606 | CLB-MP-HAUL-DT167 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 83223 | 50581 | 7500
500117566 | CLB-MP-HAUL-DT167 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 83223 | 50581 | 7500
500117526 | CLB-MP-HAUL-DT167 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 83223 | 50581 | 7500
500117486 | CLB-MP-HAUL-DT167 -AHSYST-AHSMF | AHS System Mounts & Frames | 83223 | 50581 | 7500
500117446 | CLB-MP-HAUL-DT167 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 83223 | 50581 | 7500
500117366 | CLB-MP-HAUL-DT167 -AHSYST-SNSRS | AHS Sensors | 83223 | 50581 | 7500
500117326 | CLB-MP-HAUL-DT167 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 83223 | 50581 | 7500
500117246 | CLB-MP-HAUL-DT167 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 83223 | 50581 | 7500
500117206 | CLB-MP-HAUL-DT167 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 83223 | 50581 | 7500
500117166 | CLB-MP-HAUL-DT167 -STRSYS-AHSEV | AHS EH Steering Valve | 83223 | 50581 | 7500
500117126 | CLB-MP-HAUL-DT167 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 83223 | 50581 | 7500
500117086 | CLB-MP-HAUL-DT167 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 83223 | 50581 | 7500
500117801 | CLB-MP-HAUL-DT166 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 95368 | 48693 | 7500
500117761 | CLB-MP-HAUL-DT166 -AHSYST-CTRLH-ECMA6 | ECM A6 | 95368 | 48693 | 7500
500117723 | CLB-MP-HAUL-DT166 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 95368 | 19092 | 7500
500117683 | CLB-MP-HAUL-DT166 -AHSYST-CTRLH-LIDAR | AHS Lidar | 95378 | 40844 | 7500
500117645 | CLB-MP-HAUL-DT166 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 95368 | 48693 | 7500
500117605 | CLB-MP-HAUL-DT166 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 95368 | 48693 | 7500
500117565 | CLB-MP-HAUL-DT166 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 95368 | 48693 | 7500
500117525 | CLB-MP-HAUL-DT166 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 95368 | 48693 | 7500
500117485 | CLB-MP-HAUL-DT166 -AHSYST-AHSMF | AHS System Mounts & Frames | 95368 | 48693 | 7500
500117445 | CLB-MP-HAUL-DT166 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 95368 | 48693 | 7500
500117365 | CLB-MP-HAUL-DT166 -AHSYST-SNSRS | AHS Sensors | 95368 | 48693 | 7500
500117325 | CLB-MP-HAUL-DT166 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 95368 | 48693 | 7500
500117245 | CLB-MP-HAUL-DT166 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 95368 | 48693 | 7500
500117205 | CLB-MP-HAUL-DT166 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 95368 | 48693 | 7500
500117165 | CLB-MP-HAUL-DT166 -STRSYS-AHSEV | AHS EH Steering Valve | 95368 | 48693 | 7500
500117125 | CLB-MP-HAUL-DT166 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 95368 | 48693 | 7500
500117085 | CLB-MP-HAUL-DT166 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 95368 | 48693 | 7500
500117800 | CLB-MP-HAUL-DT165 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 78849 | 50624 | 7500
500117760 | CLB-MP-HAUL-DT165 -AHSYST-CTRLH-ECMA6 | ECM A6 | 78849 | 50624 | 7500
500117722 | CLB-MP-HAUL-DT165 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 78849 | 28621 | 7500
500117682 | CLB-MP-HAUL-DT165 -AHSYST-CTRLH-LIDAR | AHS Lidar | 78868 | 36413 | 7500
500117644 | CLB-MP-HAUL-DT165 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 78849 | 50624 | 7500
500117604 | CLB-MP-HAUL-DT165 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 78849 | 50624 | 7500
500117564 | CLB-MP-HAUL-DT165 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 78849 | 50624 | 7500
500117524 | CLB-MP-HAUL-DT165 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 78849 | 50624 | 7500
500117484 | CLB-MP-HAUL-DT165 -AHSYST-AHSMF | AHS System Mounts & Frames | 78849 | 50624 | 7500
500117444 | CLB-MP-HAUL-DT165 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 78849 | 50624 | 7500
500117364 | CLB-MP-HAUL-DT165 -AHSYST-SNSRS | AHS Sensors | 78849 | 50624 | 7500
500117324 | CLB-MP-HAUL-DT165 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 78849 | 50624 | 7500
500117244 | CLB-MP-HAUL-DT165 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 78849 | 50624 | 7500
500117204 | CLB-MP-HAUL-DT165 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 78849 | 50624 | 7500
500117164 | CLB-MP-HAUL-DT165 -STRSYS-AHSEV | AHS EH Steering Valve | 78849 | 50624 | 7500
500117124 | CLB-MP-HAUL-DT165 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 78849 | 50624 | 7500
500117084 | CLB-MP-HAUL-DT165 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 78849 | 50624 | 7500
500117799 | CLB-MP-HAUL-DT164 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 81806 | 50368 | 7500
500117759 | CLB-MP-HAUL-DT164 -AHSYST-CTRLH-ECMA6 | ECM A6 | 81806 | 50368 | 7500
500117721 | CLB-MP-HAUL-DT164 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 81806 | 50368 | 7500
500117681 | CLB-MP-HAUL-DT164 -AHSYST-CTRLH-LIDAR | AHS Lidar | 83049 | 18695 | 7500
500117643 | CLB-MP-HAUL-DT164 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 81806 | 50368 | 7500
500117603 | CLB-MP-HAUL-DT164 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 81806 | 50368 | 7500
500117563 | CLB-MP-HAUL-DT164 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 81806 | 50368 | 7500
500117523 | CLB-MP-HAUL-DT164 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 81806 | 50368 | 7500
500117483 | CLB-MP-HAUL-DT164 -AHSYST-AHSMF | AHS System Mounts & Frames | 81806 | 50368 | 7500
500117443 | CLB-MP-HAUL-DT164 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 81806 | 50368 | 7500
500117363 | CLB-MP-HAUL-DT164 -AHSYST-SNSRS | AHS Sensors | 81806 | 50368 | 7500
500117323 | CLB-MP-HAUL-DT164 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 81806 | 50368 | 7500
500117243 | CLB-MP-HAUL-DT164 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 81806 | 50368 | 7500
500117203 | CLB-MP-HAUL-DT164 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 81806 | 50368 | 7500
500117163 | CLB-MP-HAUL-DT164 -STRSYS-AHSEV | AHS EH Steering Valve | 81806 | 50368 | 7500
500117123 | CLB-MP-HAUL-DT164 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 81806 | 50368 | 7500
500117083 | CLB-MP-HAUL-DT164 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 81806 | 50368 | 7500
500117798 | CLB-MP-HAUL-DT163 -AHSYST-HARNC-ETHER | AHS Harness & Ethernet Switch | 81121 | 49689 | 7500
500117758 | CLB-MP-HAUL-DT163 -AHSYST-CTRLH-ECMA6 | ECM A6 | 81121 | 49689 | 7500
500117720 | CLB-MP-HAUL-DT163 -AHSYST-CTRLH-ECMPC | ECM Position Control System | 81121 | 49689 | 7500
500117680 | CLB-MP-HAUL-DT163 -AHSYST-CTRLH-LIDAR | AHS Lidar | 81121 | 40746 | 7500
500117642 | CLB-MP-HAUL-DT163 -AHSYST-CTRLH-ECMIM | ECM Inertial Measurement Unit | 81121 | 49689 | 7500
500117602 | CLB-MP-HAUL-DT163 -AHSYST-AHSCM-CMDCF | Command Cabinet Cooling Fan | 81121 | 49689 | 7500
500117562 | CLB-MP-HAUL-DT163 -AHSYST-AHSCM-DMIFR | AHS DMI Filter | 81121 | 49689 | 7500
500117522 | CLB-MP-HAUL-DT163 -AHSYST-AHSCN-ANTEN | AHS Radio Antenna | 81121 | 49689 | 7500
500117482 | CLB-MP-HAUL-DT163 -AHSYST-AHSMF | AHS System Mounts & Frames | 81121 | 49689 | 7500
500117442 | CLB-MP-HAUL-DT163 -AHSYST-AHSHW-ECMBA | AHS Cabinet Backup Batteries | 81121 | 49689 | 7500
500117362 | CLB-MP-HAUL-DT163 -AHSYST-SNSRS | AHS Sensors | 81121 | 49689 | 7500
500117322 | CLB-MP-HAUL-DT163 -AHSYST-AHSCM-CMDCB | AHS Cabinet | 81121 | 49689 | 7500
500117242 | CLB-MP-HAUL-DT163 -AHSYST-HARNC-COAXL | AHS Coaxial Cables | 81121 | 49689 | 7500
500117202 | CLB-MP-HAUL-DT163 -AHSYST-AHSHW-CVRTR | DC To DC Converter | 81121 | 49689 | 7500
500117162 | CLB-MP-HAUL-DT163 -STRSYS-AHSEV | AHS EH Steering Valve | 81121 | 49689 | 7500
500117122 | CLB-MP-HAUL-DT163 -AHSYST-AHSCM-ELCPT | AHS Cabinet Relays | 81121 | 49689 | 7500
500117082 | CLB-MP-HAUL-DT163 -AHSYST-AHSAS-ANTEN | A-Stop Radio Antennas | 81121 | 49689 | 7500
500141840 | CLB-MP-EXCV-EX7138-STRUCT-BUCKT | Bucket Assembly | 9369 | 0 | 6200
500141796 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBMAR | Hose Hydraulic Boom Arch | 9369 | 0 | 6200
500146810 | CLB-MP-SUPP-WC014 -BRKSYS-BACCM | DO NOT USE | 18945 | 18945 | 5000
500146809 | CLB-MP-SUPP-WC014 -STRSYS-STACC | DO NOT USE | 18945 | 18945 | 5000
500146808 | CLB-MP-SUPP-WC014 -STRSYS-STACC | DO NOT USE | 18945 | 18945 | 5000
500157610 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-ALBP3 | Auto Lube Pump P3 Slew Teeth | 9369 | 9369 | 6200
500156838 | CLB-MP-EXCV-EX7138-ENGINE-ENGIN-AFCLR | Aftercooler Engine | 9369 | 9369 | 6200
500156837 | CLB-MP-EXCV-EX7138-ENGINE-FUSYS-FUINJ | Fuel Injectors | 9369 | 9369 | 6200
500156836 | CLB-MP-EXCV-EX7138-ENGINE-FUSYS-FULPP | Fuel Pump Engine | 9369 | 9369 | 6200
500152563 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-CABPR | Cabin Pressurisation System | 9369 | 9369 | 6200
500146185 | CLB-MP-EXCV-EX7138-ENGINE-COSYS-THERL | Thermostats & Regulators Low Temp | 9369 | 9369 | 6200
500146184 | CLB-MP-EXCV-EX7138-ENGINE-COSYS-LTWPP | Engine Water Pump Low Temperature | 9369 | 9369 | 6200
500141887 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-TRKRH | Assembly Track Right Hand | 9369 | 9369 | 6200
500141886 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-TENSL | Tensioner Track Hydraulic Right Hand | 9369 | 9369 | 6200
500141885 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-SPRKR | Sprocket Right Hand | 9369 | 9369 | 6200
500141884 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH9 | Roller Load Right Hand P9 | 9369 | 9369 | 6200
500141883 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH8 | Roller Load Right Hand P8 | 9369 | 9369 | 6200
500141882 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH7 | Roller Load Right Hand P7 | 9369 | 9369 | 6200
500141881 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH6 | Roller Load Right Hand P6 | 9369 | 9369 | 6200
500141880 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH5 | Roller Load Right Hand P5 | 9369 | 9369 | 6200
500141879 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH4 | Roller Load Right Hand P4 | 9369 | 9369 | 6200
500141878 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH3 | Roller Load Right Hand P3 | 9369 | 9369 | 6200
500141877 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH2 | Roller Load Right Hand P2 | 9369 | 9369 | 6200
500141876 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-LORH1 | Roller Load Right Hand P1 | 9369 | 9369 | 6200
500141875 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-IDLRH | Idler Track Right Hand | 9369 | 9369 | 6200
500141874 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-FDRRH | Final Drive Right Hand | 9369 | 9369 | 6200
500141873 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-CARRR | Roller Carrier Right Hand P2 | 9369 | 9369 | 6200
500141872 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-CARRF | Roller Carrier Right Hand P1 | 9369 | 9369 | 6200
500141871 | CLB-MP-EXCV-EX7138-UNDERC-TKFRR-ADJGR | Adjuster Track Grease RH | 9369 | 9369 | 6200
500141870 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-TRKLH | Assembly Track Left Hand | 9369 | 9369 | 6200
500141869 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-TENSL | Tensioner Track Hydraulic Left Hand | 9369 | 9369 | 6200
500141868 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-SPRKL | Sprocket Left Hand | 9369 | 9369 | 6200
500141867 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH9 | Roller Load Left Hand P9 | 9369 | 9369 | 6200
500141866 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH8 | Roller Load Left Hand P8 | 9369 | 9369 | 6200
500141865 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH7 | Roller Load Left Hand P7 | 9369 | 9369 | 6200
500141864 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH6 | Roller Load Left Hand P6 | 9369 | 9369 | 6200
500141863 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH5 | Roller Load Left Hand P5 | 9369 | 9369 | 6200
500141862 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH4 | Roller Load Left Hand P4 | 9369 | 9369 | 6200
500141861 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH3 | Roller Load Left Hand P3 | 9369 | 9369 | 6200
500141860 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH2 | Roller Load Left Hand P2 | 9369 | 9369 | 6200
500141859 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-LOLH1 | Roller Load Left Hand P1 | 9369 | 9369 | 6200
500141858 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-IDLLH | Idler Track Left Hand | 9369 | 9369 | 6200
500141857 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-FDRLH | Final Drive Left Hand | 9369 | 9369 | 6200
500141856 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-CARLR | Roller Carrier Left Hand P2 | 9369 | 9369 | 6200
500141855 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-CARLF | Roller Carrier Left Hand P1 | 9369 | 9369 | 6200
500141854 | CLB-MP-EXCV-EX7138-UNDERC-TKFRL-ADJGL | Adjuster Track Grease LH | 9369 | 9369 | 6200
500141853 | CLB-MP-EXCV-EX7138-UNDERC-SLEWB | Bearing Slew | 9369 | 9369 | 6200
500141852 | CLB-MP-EXCV-EX7138-UNDERC | Undercarriage | 9369 | 9369 | 6200
500141851 | CLB-MP-EXCV-EX7138-SWGSYS-SWBOX-SGBPR | Gearbox Swing P2 | 9369 | 9369 | 6200
500141850 | CLB-MP-EXCV-EX7138-SWGSYS-SWBOX-SGBPF | Gearbox Swing P1 | 9369 | 9369 | 6200
500141849 | CLB-MP-EXCV-EX7138-STRUCT-STICK-SLVRR | Bucket Link Shift Lever RH | 9369 | 9369 | 6200
500141848 | CLB-MP-EXCV-EX7138-STRUCT-STICK-SLVRL | Bucket Link Shift Lever LH | 9369 | 9369 | 6200
500141847 | CLB-MP-EXCV-EX7138-STRUCT-STICK-LINKR | Bucket Linkage RH | 9369 | 9369 | 6200
500141846 | CLB-MP-EXCV-EX7138-STRUCT-STICK-LINKL | Bucket Linkage LH | 9369 | 9369 | 6200
500141845 | CLB-MP-EXCV-EX7138-STRUCT-STICK | Stick Assembly | 9369 | 9369 | 6200
500141844 | CLB-MP-EXCV-EX7138-STRUCT-SRVCT | Service Centre | 9369 | 9369 | 6200
500141843 | CLB-MP-EXCV-EX7138-STRUCT-HDTNK | Tank Hydraulic | 9369 | 9369 | 6200
500141842 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-SEATO | Seat Operators | 9369 | 9369 | 6200
500141839 | CLB-MP-EXCV-EX7138-STRUCT-BOOMS | Boom Assembly | 9369 | 9369 | 6200
500141838 | CLB-MP-EXCV-EX7138-STRUCT | Structure | 9369 | 9369 | 6200
500141837 | CLB-MP-EXCV-EX7138-PNEUMC-COMPR | Compressor Air System | 9369 | 2810 | 6200
500141836 | CLB-MP-EXCV-EX7138-MANGMT-UMMMC | Mine Monitoring & Control | 9369 | 9369 | 6200
500141835 | CLB-MP-EXCV-EX7138-HYDSYS-ROTRY | Rotary Connection | 9369 | 9369 | 6200
500141834 | CLB-MP-EXCV-EX7138-HYDSYS-PMPDR | Pump Drive-Splitter Gearbox | 9369 | 9369 | 6200
500141833 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-WPPP2 | Pump Work P3 & 4 | 9369 | 9369 | 6200
500141832 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-WPPP1 | Pump Work P1 & 2 | 9369 | 9369 | 6200
500141831 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-SWPP1 | Pump Swing P1 & 2 | 9369 | 9369 | 6200
500141830 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-SVPP1 | Pump Servo-Brg Lube | 9369 | 9369 | 6200
500141829 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-RPPP1 | Pump Replenishing | 9369 | 9369 | 6200
500141828 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-PTOLU | Pump Splitter Gear Box Lube | 9369 | 9369 | 6200
500141827 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-HECP1 | Pump Cooler Fan | 9369 | 9369 | 6200
500141826 | CLB-MP-EXCV-EX7138-HYDSYS-HYDPP-ACONP | Pump Aircon Drive | 9369 | 9369 | 6200
500141825 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-VVPRV | Valve Pressure Reducing Y3 | 9369 | 9369 | 6200
500141824 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-VVPLV | Valve pressure Limiting Y4 | 9369 | 9369 | 6200
500141823 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-MCVRU | Valve Main Control Right Hand Upper VB2 | 9369 | 9369 | 6200
500141822 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-MCVRL | Valve Main Control Right Hand Lower VB3 | 9369 | 9369 | 6200
500141821 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-MCVLU | Valve Main Control Left Hand Upper VB1 | 9369 | 9369 | 6200
500141820 | CLB-MP-EXCV-EX7138-HYDSYS-HDVLV-MCVLL | Valve Main Control Left Hand Lower VB4 | 9369 | 9369 | 6200
500141819 | CLB-MP-EXCV-EX7138-HYDSYS-HDOCO-OCHYR | Cooler Hyd Rear | 9369 | 9369 | 6200
500141818 | CLB-MP-EXCV-EX7138-HYDSYS-HDOCO-OCHYF | Cooler Hyd Front | 9369 | 9369 | 6200
500141817 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMRR | Motor Travel Right Hand Rear | 9369 | 9369 | 6200
500141816 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMRF | Motor Travel Right Hand Front | 9369 | 9369 | 6200
500141815 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMLR | Motor Travel Left Hand Rear | 9369 | 9369 | 6200
500141814 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-TRMLF | Motor Travel Left Hand Front | 9369 | 9369 | 6200
500141813 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-SWMOR | Hyd Motor Swing Rear | 9369 | 9369 | 6200
500141812 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-SWMOF | Hyd Motor Swing Front | 9369 | 9369 | 6200
500141811 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-FMEC4 | Motor Fan Eng Cooling LH Lower P4 | 9369 | 9369 | 6200
500141810 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-FMEC3 | Motor Fan Eng Cooling RH lower P3 | 9369 | 9369 | 6200
500141809 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-FMEC2 | Motor Fan Eng Cooling RH Upper P2 | 9369 | 9369 | 6200
500141808 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-FMEC1 | Motor Fan Eng Cooling LH Upper P1 | 9369 | 9369 | 6200
500141807 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-FMCH2 | Motor Fan Hyd Cooling Rear | 9369 | 9369 | 6200
500141806 | CLB-MP-EXCV-EX7138-HYDSYS-HDMOT-FMCH1 | Motor Fan Hyd Cooling Front | 9369 | 9369 | 6200
500141805 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HWPVV | Hose Hydraulic Work Pumps to Valves | 9369 | 9369 | 6200
500141804 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HSTCL | Hose Hydraulic Stick Cylinder | 9369 | 4227 | 6200
500141803 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HSPSM | Hose Hydraulic Swing Pump-Swing Motor | 9369 | 9369 | 6200
500141802 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HRCVV | Hose Hyd Rotary Connection To Valve Bank | 9369 | 9369 | 6200
500141801 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HRCTM | Hose Hyd Rotary Connection to Travel Mtr | 9369 | 9369 | 6200
500141800 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HMCVV | Hose Hydraulic Main Valve Bank | 9369 | 9369 | 6200
500141798 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HHTTL | Hose HP Hyd Track Tensioner | 9369 | 9369 | 6200
500141797 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBMCL | Hose Hydraulic Boom Cylinder | 9369 | 3729 | 6200
500141795 | CLB-MP-EXCV-EX7138-HYDSYS-HDHLF-HBKCL | Hose Hydraulic Bucket Cylinder | 9369 | 3729 | 6200
500141794 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-STCLR | Cylinder Stick Right Hand | 9369 | 9369 | 6200
500141793 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-STCLL | Cylinder Stick Left Hand | 9369 | 9369 | 6200
500141792 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-LACYL | Cylinder Ladder Raise | 9369 | 9369 | 6200
500141791 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYR | Cylinder Bucket Right Hand | 9369 | 9369 | 6200
500141790 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BUCYL | Cylinder Bucket Left Hand | 9369 | 2193 | 6200
500141789 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BMCYR | Cylinder Boom Right Hand | 9369 | 9369 | 6200
500141788 | CLB-MP-EXCV-EX7138-HYDSYS-HDCYL-BMCYL | Cylinder Boom Left Hand | 9369 | 9369 | 6200
500141787 | CLB-MP-EXCV-EX7138-HYDSYS-HDCFM-CFHP2 | Fan Cooling Hydraulic P2 | 9369 | 9369 | 6200
500141786 | CLB-MP-EXCV-EX7138-HYDSYS-HDCFM-CFHP1 | Fan Cooling Hydraulic P1 | 9369 | 9369 | 6200
500141785 | CLB-MP-EXCV-EX7138-HYDSYS-HDCFM-CFEP4 | Fan Cooling Engine Left Hand Lower P4 | 9369 | 9369 | 6200
500141784 | CLB-MP-EXCV-EX7138-HYDSYS-HDCFM-CFEP3 | Fan Cooling Engine Right Hand Lower P3 | 9369 | 9369 | 6200
500141783 | CLB-MP-EXCV-EX7138-HYDSYS-HDCFM-CFEP2 | Fan Cooling Engine Right Hand Upper P2 | 9369 | 9369 | 6200
500141782 | CLB-MP-EXCV-EX7138-HYDSYS-HDCFM-CFEP1 | Fan Cooling Engine Left Hand Upper P1 | 9369 | 9369 | 6200
500141781 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCS | Accumulator Servo | 9369 | 9369 | 6200
500141780 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCR | Accumulator Track Hydraulic Right Hand | 9369 | 9369 | 6200
500141779 | CLB-MP-EXCV-EX7138-HYDSYS-HDACC-HACCL | Accumulator Track Hydraulic Left Hand | 9369 | 9369 | 6200
500141778 | CLB-MP-EXCV-EX7138-HYDSYS | Hydraulic System | 9369 | 9369 | 6200
500141777 | CLB-MP-EXCV-EX7138-GRSYST-GRINJ | Auto Lube Injectors | 9369 | 9369 | 6200
500141776 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-GRTNK | Reservoir Auto Lube | 9369 | 2810 | 6200
500141775 | CLB-MP-EXCV-EX7138-GRSYST-AUTLU-ALBPP | Pump Auto Lube | 9369 | 9369 | 6200
500141774 | CLB-MP-EXCV-EX7138-FRSUPP | R9400 Fire Suppression System | 9369 | 9369 | 6200
500141771 | CLB-MP-EXCV-EX7138-ENGINE-ENGIN-TBOP2 | Turbocharger RH | 9369 | 3769 | 6200
500141770 | CLB-MP-EXCV-EX7138-ENGINE-ENGIN-TBOP1 | Turbocharger LH | 9369 | 3769 | 6200
500141769 | CLB-MP-EXCV-EX7138-ENGINE-ENGEX | Exhaust System Engine | 9369 | 9369 | 6200
500141768 | CLB-MP-EXCV-EX7138-ENGINE-COUPL | Engine Coupling | 9369 | 9369 | 6200
500141767 | CLB-MP-EXCV-EX7138-ENGINE-COSYS-HTWPP | Engine Water Pump High Temperature | 9369 | 9369 | 6200
500141766 | CLB-MP-EXCV-EX7138-ENGINE-COSYS-THERH | Thermostats & Regulators High Temp | 9369 | 9369 | 6200
500141765 | CLB-MP-EXCV-EX7138-ENGINE-COSYS-RADTR | Radiator Engine | 9369 | 9369 | 6200
500141764 | CLB-MP-EXCV-EX7138-ENGINE | Engine Assembly Liebherr D9812 | 9369 | 9369 | 6200
500141763 | CLB-MP-EXCV-EX7138-ELCTLV-START-STMLU | Starter Motor Eng P1 | 9369 | 9369 | 6200
500141762 | CLB-MP-EXCV-EX7138-ELCTLV-START-STMLL | Starter Motor Eng P2 | 9369 | 9369 | 6200
500141761 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-BATST | Batteries Engine | 9369 | 1820 | 6200
500141760 | CLB-MP-EXCV-EX7138-ELCTLV-CHARG-ALTER | Alternator 24V Engine | 9369 | 3998 | 6200
500141759 | CLB-MP-EXCV-EX7138-COMMUN-FLMGT | Fleet Management | 9369 | 9369 | 6200
500141757 | CLB-MP-EXCV-EX7138 | Liebherr R9400 Excavator EX7138 | 9369 | 9369 | 6200
500114944 | CLB-MP-DRLL-DR061 -STRUCT-CABIN | Operators Cabin | 0 | 0 | 6300
500152527 | CCK-MP-LV01-ARTTRK-ADT180 | ADT180 Komatsu HM400-3 Artic Dump Truck | 5337 | 5337 | 5000
500157552 | ELW-MP-LV01-TRUCKS-WC0159 | WC0159 Isuzu FYH 350 Water Cart | 107045 | 107045 | 411250
500141799 | ELW-MP-EXCV-EX7138-HYDSYS-HDHLF-HHTTR | Deleted | 5923 | 5923 | 6000
500158190 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HHTTR | Deleted | 459 | 459 | 6500
500157492 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HHTTR | Deleted | 1401 | 1401 | 6500
500154846 | CLB-MP-EXCV-EX7141-HYDSYS-HDHLF-HHTTR | Deleted | 3704 | 3704 | 6500
500150503 | CLB-MP-EXCV-EX7140-HYDSYS-HDHLF-HHTTR | Deleted | 6754 | 6754 | 6500
500148919 | CLB-MP-EXCV-EX7139-HYDSYS-HDHLF-HHTTR | Deleted | 6970 | 6970 | 6500
500135791 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HHTTR | Deleted | 9279 | 9279 | 6500
500158195 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HSTCR | Deleted | 459 | 459 | 6500
500158188 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBMCR | Deleted | 459 | 459 | 6500
500158187 | CLB-MP-EXCV-EX7149-HYDSYS-HDHLF-HBKCR | Deleted | 459 | 459 | 6500
500157497 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HSTCR | Deleted | 1401 | 1401 | 6500
500157490 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBMCR | Deleted | 1401 | 1401 | 6500
500157489 | CLB-MP-EXCV-EX7148-HYDSYS-HDHLF-HBKCR | Deleted | 1401 | 1401 | 6500
500135796 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HSTCR | Deleted | 9279 | 9279 | 6500
500135789 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBMCR | Deleted | 9279 | 9279 | 6500
500135788 | CLB-MP-EXCV-EX7133-HYDSYS-HDHLF-HBKCR | Deleted | 9279 | 9279 | 6500
500154785 | CLB-MP-EXCV-EX7141 | R9400 Excavator EX7141 TRAVEL HOURS | 761 | 761 | 440
500141841 | CLB-MP-EXCV-EX7138-STRUCT-CABIN-AIRC1 | DO NOT USE | 3940 | 3940 | 6000
500154888 | CLB-MP-EXCV-EX7141-STRUCT-CABIN-AIRC1 | DO NOT USE | 1175 | 1175 | 6500
500150545 | CLB-MP-EXCV-EX7140-STRUCT-CABIN-AIRC1 | DO NOT USE | 4257 | 4257 | 6500
500148961 | CLB-MP-EXCV-EX7139-STRUCT-CABIN-AIRC1 | DO NOT USE | 4530 | 4530 | 6500
500147345 | CLB-MP-HAUL-DT225 -BRKSYS-BACCM | Brake Accumulator | 4700 | 4700 | 7500
500147341 | CLB-MP-HAUL-DT224 -BRKSYS-BACCM | Brake Accumulator | 4556 | 4556 | 7500
500147319 | CLB-MP-HAUL-DT200 -BRKSYS-BACCM | Brake Accumulator | 4644 | 4644 | 7500
500147315 | CLB-MP-HAUL-DT199 -BRKSYS-BACCM | Brake Accumulator | 3539 | 3539 | 7500
500147311 | CLB-MP-HAUL-DT198 -BRKSYS-BACCM | Brake Accumulator | 4807 | 4807 | 7500
500147307 | CLB-MP-HAUL-DT197 -BRKSYS-BACCM | Brake Accumulator | 4770 | 4770 | 7500
500147303 | CLB-MP-HAUL-DT196 -BRKSYS-BACCM | Brake Accumulator | 3582 | 3582 | 7500
500147299 | CLB-MP-HAUL-DT195 -BRKSYS-BACCM | Brake Accumulator | 4676 | 4676 | 7500
500147295 | CLB-MP-HAUL-DT194 -BRKSYS-BACCM | Brake Accumulator | 26505 | 26505 | 7500
500147291 | CLB-MP-HAUL-DT193 -BRKSYS-BACCM | Brake Accumulator | 3368 | 3368 | 7500
500147287 | CLB-MP-HAUL-DT192 -BRKSYS-BACCM | Brake Accumulator | 4796 | 4796 | 7500
500147283 | CLB-MP-HAUL-DT191 -BRKSYS-BACCM | Brake Accumulator | 26316 | 26316 | 7500
500147279 | CLB-MP-HAUL-DT190 -BRKSYS-BACCM | Brake Accumulator | 4871 | 4871 | 7500
500147275 | CLB-MP-HAUL-DT189 -BRKSYS-BACCM | Brake Accumulator | 3595 | 3595 | 7500
500147271 | CLB-MP-HAUL-DT188 -BRKSYS-BACCM | Brake Accumulator | 4011 | 4011 | 7500
500147267 | CLB-MP-HAUL-DT187 -BRKSYS-BACCM | Brake Accumulator | 4616 | 4616 | 7500
500147263 | CLB-MP-HAUL-DT186 -BRKSYS-BACCM | Brake Accumulator | 4782 | 4782 | 7500
500147259 | CLB-MP-HAUL-DT185 -BRKSYS-BACCM | Brake Accumulator | 4857 | 4857 | 7500
500147255 | CLB-MP-HAUL-DT184 -BRKSYS-BACCM | Brake Accumulator | 4841 | 4841 | 7500
500147251 | CLB-MP-HAUL-DT183 -BRKSYS-BACCM | Brake Accumulator | 4729 | 4729 | 7500
500147247 | CLB-MP-HAUL-DT181 -BRKSYS-BACCM | Brake Accumulator | 4790 | 4790 | 7500
500147243 | CLB-MP-HAUL-DT180 -BRKSYS-BACCM | Brake Accumulator | 4666 | 4666 | 7500
500147239 | CLB-MP-HAUL-DT179 -BRKSYS-BACCM | Brake Accumulator | 3526 | 3526 | 7500
500147235 | CLB-MP-HAUL-DT178 -BRKSYS-BACCM | Brake Accumulator | 4747 | 4747 | 7500
500147231 | CLB-MP-HAUL-DT177 -BRKSYS-BACCM | Brake Accumulator | 4716 | 4716 | 7500
500147227 | CLB-MP-HAUL-DT176 -BRKSYS-BACCM | Brake Accumulator | 3267 | 3267 | 7500
500147223 | CLB-MP-HAUL-DT175 -BRKSYS-BACCM | Brake Accumulator | 4738 | 4738 | 7500
500147219 | CLB-MP-HAUL-DT174 -BRKSYS-BACCM | Brake Accumulator | 4652 | 4652 | 7500
500147218 | CLB-MP-HAUL-DT173 -BRKSYS-BACCM | Brake Accumulator | 3483 | 3483 | 7500
500147211 | CLB-MP-HAUL-DT172 -BRKSYS-BACCM | Brake Accumulator | 4761 | 4761 | 7500
500147207 | CLB-MP-HAUL-DT171 -BRKSYS-BACCM | Brake Accumulator | 4781 | 4781 | 7500
500147203 | CLB-MP-HAUL-DT170 -BRKSYS-BACCM | Brake Accumulator | 4834 | 4834 | 7500
500147199 | CLB-MP-HAUL-DT169 -BRKSYS-BACCM | Brake Accumulator | 4819 | 4819 | 7500
500147195 | CLB-MP-HAUL-DT168 -BRKSYS-BACCM | Brake Accumulator | 4702 | 4702 | 7500
500147191 | CLB-MP-HAUL-DT167 -BRKSYS-BACCM | Brake Accumulator | 4643 | 4643 | 7500
500147187 | CLB-MP-HAUL-DT166 -BRKSYS-BACCM | Brake Accumulator | 4665 | 4665 | 7500
500147183 | CLB-MP-HAUL-DT165 -BRKSYS-BACCM | Brake Accumulator | 4781 | 4781 | 7500
500147175 | CLB-MP-HAUL-DT163 -BRKSYS-BACCM | Brake Accumulator | 4741 | 4741 | 7500
500147179 | CLB-MP-HAUL-DT164 -BRKSYS-BACCM | Brake Accumulator | 3106 | 141 | 7500
500141758 | CLB-MP-EXCV-EX7138 | R9400 Excavator EX7138 TRAVEL HOURS | 48 | 48 | 440
500127707 | IBO-MP-LV01-TRUCKS-WC0143 | WC0143 Isuzu FVZ 6X4 Water Truck | 10933 | 10933 | 6000
500116391 | CLB-MP-LV01-TRUCKS-WC0150 | WC0150 Isuzu FVZ 6X4 Water Cart | 304876 | 304876 | 10000
500126214 | CLB-MP-DRLL-DR3126-AIRSYS-COMPR-ARTNK | DR3126 Receiver Tank | 8649 | 8649 | 5300
500135507 | CLB-MP-DRLL-DR2133-AIRSYS-COMPR-ARTNK | Receiver Tank | 1802 | 1802 | 6000
500135320 | CLB-MP-DRLL-DR2132-AIRSYS-COMPR-ARTNK | Receiver Tank | 2609 | 2609 | 6000
500135133 | CLB-MP-DRLL-DR2131-AIRSYS-COMPR-ARTNK | Receiver Tank | 3269 | 2196 | 6000
500133857 | CLB-MP-DRLL-DR2130-AIRSYS-COMPR-ARTNK | Receiver Tank | 5528 | 5528 | 6000
500127767 | CLB-MP-DRLL-DR2126-AIRSYS-COMPR-ARTNK | Receiver Tank | 11162 | 11162 | 6700
500077251 | CLB-MP-DRLL-DR060 -AIRSYS-COMPR-ARTNK | DR060 Compressor Safety Valve | 62187 | 15293 | 6000
500101051 | CLB-MP-DRLL-DR3110-AIRSYS-COMPR-ARTNK | DR3110 Receiver Tank | 24461 | 1320 | 4200
500101416 | CLB-MP-HAUL-DT225 -STRUCT-TRAYS | 789D Tray Wear, DT225 | 0 | 0 | 25
500059660 | CLB-MP-HAUL-DT193 -STRUCT-TRAYS | 789D Tray Wear, DT193 | 37 | 0 | 25
500101140 | FMG-CC-MP-DRLL-DR3110-STRUCT-WINCH-WINSH | DR3110 Winch Sheaves | 23390 | 23390 | 6000
500101139 | FMG-CC-MP-DRLL-DR3110-STRUCT-WINCH-WINRP | DR3110 Winch Rope | 23390 | 23390 | 6000
500101138 | FMG-CC-MP-DRLL-DR3110-STRUCT-WINCH | DR3110 Winch Assembly | 23390 | 23390 | 6000
500135785 | CLB-MP-EXCV-EX7133-HYDSYS-HDCFM-CFEP4 | Fan Cooling System LH Lower | 1 | 1 | 6200
500135784 | CLB-MP-EXCV-EX7133-HYDSYS-HDCFM-CFEP3 | Fan Cooling System RH Lower | 1 | 1 | 6200
500135783 | CLB-MP-EXCV-EX7133-HYDSYS-HDCFM-CFEP2 | Fan Cooling System RH Upper | 1 | 1 | 6200
500135782 | CLB-MP-EXCV-EX7133-HYDSYS-HDCFM-CFEP1 | Fan Cooling System LH Upper | 1 | 1 | 6200
500131650 | CLB-MP-EXCV-EX7124-GRSYST-ALBPU | Auto Lube Pump Undercarriage | 1548 | 1548 | 6700
500126407 | CLB-MP-EXCV-EX7119-GRSYST-ALBPU | Auto Lube Pump Undercarriage | 9271 | 9271 | 6700
500126226 | CLB-MP-EXCV-EX7118-GRSYST-ALBPU | Auto Lube Pump Undercarriage | 9194 | 9194 | 6700
500114550 | CLB-MP-EXCV-EX7112-GRSYST-ALBPU | Auto Lube Pump Undercarriage | 11811 | 11811 | 6700
500080004 | CLB-MP-SUPP-PM0004-PNEUMC-START | PM0004 Pneumatic Starter Motor | 82850 | 0 | 3500
500117980 | CCK-MP-DRLL-DR3110-ELCTLV-HARNS-HARMS | Harness Minestar | 20794 | 20794 | 4200
500101071 | CCK-MP-DRLL-DR3110-ELCTLV-CONTL-MD512 | DR3110 Module I/O RCS4 MD512 | 20794 | 20794 | 4200
500101070 | CCK-MP-DRLL-DR3110-ELCTLV-CONTL-MD511 | DR3110 Module I/O RCS4 MD511 | 20794 | 20794 | 4200
500101069 | CCK-MP-DRLL-DR3110-ELCTLV-CONTL-MD510 | DR3110 Module I/O RCS4 MD510 | 20794 | 20794 | 4200
500126597 | CLB-MP-DRLL-DR3126-ELCTLV-HARNS-HARMS | Harness Minestar | 4841 | 4841 | 4400
500126595 | CLB-MP-DRLL-DR3126-ELCTLV-CONTL-MD515 | DR3126 Module IO RCS4 | 4841 | 4841 | 4400
500126594 | CLB-MP-DRLL-DR3126-ELCTLV-CONTL-MD514 | DR3126 Module IO RCS4 | 4841 | 4841 | 4400
500126593 | CLB-MP-DRLL-DR3126-ELCTLV-CONTL-MD513 | DR3126 Module IO RCS4 | 4841 | 4841 | 4400
500126592 | CLB-MP-DRLL-DR3126-ELCTLV-CONTL-MD512 | DR3126 Module IO RCS4 | 4841 | 4841 | 4400
500126591 | CLB-MP-DRLL-DR3126-ELCTLV-CONTL-MD511 | DR3126 Module IO RCS4 | 4841 | 4841 | 4400
500126590 | CLB-MP-DRLL-DR3126-ELCTLV-CONTL-MD510 | DR3126 Module IO RCS4 | 4841 | 4841 | 4400
500079945 | CLB-MP-DRLL-DR060 -ELCTLV-CONTL-MD514 | Module I/O RCS4 MD514 | 51460 | 51460 | 6300
500079944 | CLB-MP-DRLL-DR060 -ELCTLV-CONTL-MD513 | Module I/O RCS4 MD513 | 51460 | 51460 | 6300
500079943 | CLB-MP-DRLL-DR060 -ELCTLV-CONTL-MD512 | Module I/O RCS4 MD512 | 51460 | 51460 | 6300
500079942 | CLB-MP-DRLL-DR060 -ELCTLV-CONTL-MD511 | Module I/O RCS4 MD511 | 51460 | 25979 | 6300
500079941 | CLB-MP-DRLL-DR060 -ELCTLV-CONTL-MD510 | Module I/O RCS4 MD510 | 51460 | 51460 | 6300
500056829 | CCK-MP-DOZR-DZX024-STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 53128 | 53128 | 2000
500056828 | CCK-MP-DOZR-DZX024-STRUCT-BLADE-BLLIN | Blade Liner | 53128 | 53128 | 2000
500108406 | CLB-MP-DOZR-WD6106-STRUCT-BLADE-BLLIN | WD6106 Blade Liner | 11678 | 11678 | 5900
500108405 | CLB-MP-DOZR-WD6106-STRUCT-BLADE-BLGET | WD6106 Blade Wear Elements (GET) | 11678 | 11678 | 5900
500107109 | CLB-MP-DOZR-WD6105-STRUCT-BLADE-BLLIN | Blade Liner | 36072 | 36072 | 5900
500107108 | CLB-MP-DOZR-WD6105-STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 36072 | 36072 | 5900
500029302 | CLB-MP-DOZR-WD004 -STRUCT-BLADE-BLLIN | Blade Liner | 54604 | 54604 | 5900
500029301 | CLB-MP-DOZR-WD004 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 54604 | 54604 | 5900
500056909 | CLB-MP-DOZR-DZX025-STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 51213 | 51213 | 4400
500056908 | CLB-MP-DOZR-DZX025-STRUCT-BLADE-BLLIN | Blade Liner | 51213 | 51213 | 4400
500056749 | CLB-MP-DOZR-DZX023-STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 49953 | 49953 | 4400
500056748 | CLB-MP-DOZR-DZX023-STRUCT-BLADE-BLLIN | Blade Liner | 49953 | 49953 | 4400
500056669 | CLB-MP-DOZR-DZX022-STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 50536 | 50536 | 4400
500056668 | CLB-MP-DOZR-DZX022-STRUCT-BLADE-BLLIN | Blade Liner | 50536 | 50536 | 4400
500056589 | CLB-MP-DOZR-DZX021-STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 54136 | 54136 | 5000
500056588 | CLB-MP-DOZR-DZX021-STRUCT-BLADE-BLLIN | Blade Liner | 54136 | 54136 | 5000
500037238 | CLB-MP-DOZR-DZ018 -STRUCT-BLADE-BLLIN | Blade Liner | 53819 | 53819 | 4700
500037237 | CLB-MP-DOZR-DZ018 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 53819 | 53819 | 4700
500037116 | CLB-MP-DOZR-DZ017 -STRUCT-BLADE-BLLIN | Blade Liner | 53568 | 53568 | 4700
500037115 | CLB-MP-DOZR-DZ017 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 53568 | 53568 | 4700
500036994 | CLB-MP-DOZR-DZ016 -STRUCT-BLADE-BLLIN | Blade Liner | 57054 | 57054 | 4700
500036993 | CLB-MP-DOZR-DZ016 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 57054 | 57054 | 4700
500036872 | CLB-MP-DOZR-DZ015 -STRUCT-BLADE-BLLIN | Blade Liner | 55657 | 55657 | 4700
500036871 | CLB-MP-DOZR-DZ015 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 55657 | 55657 | 4700
500028458 | CLB-MP-DOZR-DZ013 -STRUCT-BLADE-BLLIN | Blade Liner | 55899 | 55899 | 4700
500028457 | CLB-MP-DOZR-DZ013 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 55899 | 55899 | 4700
500027632 | CLB-MP-DOZR-DZ012 -STRUCT-BLADE-BLLIN | Blade Liner | 44032 | 44032 | 4700
500027631 | CLB-MP-DOZR-DZ012 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 44032 | 44032 | 4700
500025556 | CLB-MP-DOZR-DZ011 -STRUCT-BLADE-BLLIN | Blade Liner | 54923 | 54923 | 4700
500025555 | CLB-MP-DOZR-DZ011 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 54923 | 54923 | 4700
500131152 | CLB-MP-DRLL-DR061 -STRUCT-TRKLH | Deleted | 23086 | 23086 | 5600
500131146 | CLB-MP-DRLL-DR061 -STRUCT-TRKRH | Deleted | 23086 | 23086 | 5600
500131151 | CLB-MP-DRLL-DR060 -STRUCT-TRKLH | Deleted | 50392 | 50392 | 5600
500131145 | CLB-MP-DRLL-DR060 -STRUCT-TRKRH | Deleted | 50392 | 50392 | 5600
500120218 | IBO-MP-LV01-TRUCKS-WC0120 | WC0120 Mack MP804 Water Truck | 12342 | 12342 | 5300
500029342 | CLB-MP-DOZR-WD005 -FDRSYS-RRDIF | Spare | 57839 | 57839 | 6200
500029225 | CLB-MP-DOZR-WD004 -FDRSYS-RRDIF | Spare | 51895 | 51895 | 6200
500059644 | CLB-MP-HAUL-DT177 -STRUCT-TRAYS | 789D Tray Wear, DT177 | 10 | 0 | 25
500059634 | CLB-MP-HAUL-DT167 -STRUCT-TRAYS | 789D Tray Wear, DT167 | 26 | 0 | 25
500102973 | CLB-MP-SUPP-LL0003 | Float DO NOT USE | 36911 | 36911 | 5300
500059631 | CLB-MP-HAUL-DT164 -STRUCT-TRAYS | 789D Tray Wear, DT164 | 13 | 0 | 25
500059648 | CLB-MP-HAUL-DT181 -STRUCT-TRAYS | 789D Tray Wear, DT181 | 17 | 0 | 25
500059646 | CLB-MP-HAUL-DT179 -STRUCT-TRAYS | 789D Tray Wear, DT179 | 14 | 0 | 25
500059641 | CLB-MP-HAUL-DT174 -STRUCT-TRAYS | 789D Tray Wear, DT174 | 28 | 0 | 25
500103081 | RED-CB-MP-EXCV-EX014 -HYDSYS-HDVLV-FTVRH | Valve Float RH | 13871 | 13871 | 6500
500059643 | CLB-MP-HAUL-DT176 -STRUCT-TRAYS | 789D Tray Wear, DT176 | 31 | 0 | 25
500048577 | CLB-MP-HAUL-DT175 -ENGINE-COSYS-RADTR | Radiator Coolant | 20550 | 0 | 7400
500029419 | RED-CB-MP-DOZR-WD005 -STRUCT-BLADE-BLLIN | Blade Liner | 50071 | 50071 | 6200
500029418 | RED-CB-MP-DOZR-WD005 -STRUCT-BLADE-BLGET | Blade Wear Elements (GET) | 50071 | 38063 | 6200
500002873 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-RAMPL | Ramp LH DO NOT USE | 30307 | 0 | 5300
500002874 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-RAMPR | Ramp RH DO NOT USE | 30307 | 0 | 5300
500102103 | RED-CB-MP-DRLL-DR060 -MANGMT-UMPMP | DR060 Pump Management System | 38560 | 38560 | 6700
500102100 | RED-CB-MP-DRLL-DR060 -MANGMT-UMCON | DR060 Control Management System | 38560 | 38560 | 6700
500111924 | FMG-EW-MP-LV01-LVEHCL-SV019 | SV019 ESO Landcruiser Ambulance | 62023 | 62023 | 10000
500101380 | RED-CB-MP-HAUL-DT225 -PNEUMC-START | Air Starter | 6176 | 6176 | 7200
500101247 | RED-CB-MP-HAUL-DT224 -PNEUMC-START | Air Starter | 5323 | 5323 | 7200
500043083 | RED-CB-MP-EXCV-EX109 -HYDSYS-HDOCO-OCHBR | Oil Cooler Hydraulic Bottom Rear | 41504 | 13693 | 7100
500043082 | RED-CB-MP-EXCV-EX109 -HYDSYS-HDOCO-OCHBF | Oil Cooler Hydraulic Bottom Front | 41504 | 13693 | 7100
500042932 | RED-CB-MP-EXCV-EX108 -HYDSYS-HDOCO-OCHBR | Oil Cooler Hydraulic Bottom Rear | 35537 | 19866 | 7100
500042931 | RED-CB-MP-EXCV-EX108 -HYDSYS-HDOCO-OCHBF | Oil Cooler Hydraulic Bottom Front | 35537 | 21090 | 7100
500042781 | RED-CB-MP-EXCV-EX107 -HYDSYS-HDOCO-OCHBR | Oil Cooler Hydraulic Bottom Rear | 45148 | 1901 | 7100
500042780 | RED-CB-MP-EXCV-EX107 -HYDSYS-HDOCO-OCHBF | Oil Cooler Hydraulic Bottom Front | 45148 | 13639 | 7100
500065754 | RED-CC-MP-LOAD-WL263 -STRUCT-BUCKT-BWELM | WL263 Bucket Wear Elements | 28148 | 28148 | 6000
500043030 | RED-CB-MP-EXCV-EX109 -ELCTLV-CHARG-BATRH | Batteries RH Engine | 35163 | 15132 | 7100
500043029 | RED-CB-MP-EXCV-EX109 -ELCTLV-CHARG-BATLH | Batteries LH Engine | 35163 | 15132 | 7100
500042879 | RED-CB-MP-EXCV-EX108 -ELCTLV-CHARG-BATRH | Batteries RH Engine | 29015 | 29015 | 7100
500042878 | RED-CB-MP-EXCV-EX108 -ELCTLV-CHARG-BATLH | Batteries LH Engine | 29015 | 29015 | 7100
500042728 | RED-CB-MP-EXCV-EX107 -ELCTLV-CHARG-BATRH | Batteries RH Engine | 38990 | 967 | 7100
500042727 | RED-CB-MP-EXCV-EX107 -ELCTLV-CHARG-BATLH | Batteries LH Engine | 38990 | 967 | 7100
500046176 | RED-CB-MP-EXCV-EX011 -ELCTLV-CHARG-BATRH | Batteries RH Engine | 35595 | 2751 | 6500
500046175 | RED-CB-MP-EXCV-EX011 -ELCTLV-CHARG-BATLH | Batteries LH Engine | 35595 | 2751 | 6500
500002872 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-PIVOT | Pivot Group DO NOT USE | 30307 | 0 | 5300
500002871 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-HITCH | Hitch DO NOT USE | 30307 | 0 | 5300
500002867 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT-CLAMP | Clamp DO NOT USE | 30307 | 0 | 5300
500059208 | CLB-MP-EXCV-EX109 -STRUCT-TKFRR | 6060 RH Track Wear, EX109 | 64 | 0 | 42
500059207 | CLB-MP-EXCV-EX109 -STRUCT-TKFRL | 6060 LH Track Wear, EX109 | 64 | 0 | 42
500059205 | CLB-MP-EXCV-EX108 -STRUCT-TKFRR | 6060 RH Track Wear, EX108 | 41 | 0 | 42
500059206 | CLB-MP-EXCV-EX108 -STRUCT-TKFRL | 6060 LH Track Wear, EX108 | 33 | 0 | 42
500002876 | CLB-MP-SUPP-LL0003-BRKSYS-SRVBK-SVBRH | Service Brake R/H Rear DO NOT USE | 30307 | 30307 | 5300
500002875 | CLB-MP-SUPP-LL0003-BRKSYS-SRVBK-SVBLH | Service Brake L/H Rear DO NOT USE | 30307 | 30307 | 5300
500002870 | CLB-MP-SUPP-LL0003-STRUCT-FLOAT | Bed DO NOT USE | 30307 | 30307 | 5300
500002869 | CLB-MP-SUPP-LL0003-FDRSYS-FDRRH | Final Drive R/H DO NOT USE | 30307 | 30307 | 5300
500002868 | CLB-MP-SUPP-LL0003-FDRSYS-FDRLH | Final Drive L/H DO NOT USE | 30307 | 30307 | 5300
500046256 | RED-CB-MP-EXCV-EX011 -STRUCT-STICK-LINKH | Stick To Bucket H Linkage | 22006 | 22006 | 6500
500056466 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056465 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056464 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056463 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056462 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056461 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056460 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056459 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056458 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056457 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056456 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056455 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056454 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056453 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056452 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056451 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056450 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056449 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056448 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056447 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056446 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056445 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056444 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056443 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056442 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056441 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056440 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056439 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056438 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056437 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056436 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056435 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056434 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056433 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500056432 | CLB-MP-DRLL-DR060 | Obsolete | 11780 | 11780 | 6700
500055548 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055547 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055546 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055545 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055544 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055543 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055542 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055541 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055540 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055539 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055538 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055537 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055536 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055535 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055534 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055533 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055532 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055531 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055530 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055529 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055528 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055527 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055526 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055525 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055524 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055523 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055522 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055521 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055520 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500055519 | CLB-MP-GRDR-GR102 | obsolete | 9322 | 9322 | 6000
500059183 | CLB-MP-EXCV-EX011 -STRUCT-TKFRR | 6040 RH Track Wear, EX011 | 0 | 78 | 42
500059182 | CLB-MP-EXCV-EX011 -STRUCT-TKFRL | 6040 LH Track Wear, EX011 | 0 | 83 | 42
500025548 | CLB-MP-DOZR-DZ011 -HYDSYS-HDTNK | DO NOT USE | 20807 |  | 5602
500059204 | CLB-MP-EXCV-EX107 -STRUCT-TKFRR | 6060 RH Track Wear, EX107 | 58 | 58 | 42
500059203 | CLB-MP-EXCV-EX107 -STRUCT-TKFRL | 6060 LH Track Wear, EX107 | 65 | 65 | 42
500059667 | CLB-MP-HAUL-DT200 -STRUCT-TRAYS | 789D Tray Wear, DT200 | 8 | 8 | 25
500059666 | CLB-MP-HAUL-DT199 -STRUCT-TRAYS | 789D Tray Wear, DT199 | 40 | 40 | 25
500059665 | CLB-MP-HAUL-DT198 -STRUCT-TRAYS | 789D Tray Wear, DT198 | 18 | 18 | 25
500059664 | CLB-MP-HAUL-DT197 -STRUCT-TRAYS | 789D Tray Wear, DT197 | 13 | 13 | 25
500059663 | CLB-MP-HAUL-DT196 -STRUCT-TRAYS | 789D Tray Wear, DT196 | 0 | 0 | 25
500059662 | CLB-MP-HAUL-DT195 -STRUCT-TRAYS | 789D Tray Wear, DT195 | 9 | 9 | 25
500059661 | CLB-MP-HAUL-DT194 -STRUCT-TRAYS | 789D Tray Wear, DT194 | 7 | 7 | 25
500059659 | CLB-MP-HAUL-DT192 -STRUCT-TRAYS | 789D Tray Wear, DT192 | 21 | 21 | 25
500059658 | CLB-MP-HAUL-DT191 -STRUCT-TRAYS | 789D Tray Wear, DT191 | 13 | 13 | 25
500059657 | CLB-MP-HAUL-DT190 -STRUCT-TRAYS | 789D Tray Wear, DT190 | 7 | 7 | 25
500059656 | CLB-MP-HAUL-DT189 -STRUCT-TRAYS | 789D Tray Wear, DT189 | 10 | 10 | 25
500059655 | CLB-MP-HAUL-DT188 -STRUCT-TRAYS | 789D Tray Wear, DT188 | 0 | 0 | 25
500059654 | CLB-MP-HAUL-DT187 -STRUCT-TRAYS | 789D Tray Wear, DT187 | 25 | 25 | 25
500059653 | CLB-MP-HAUL-DT186 -STRUCT-TRAYS | 789D Tray Wear, DT186 | 9 | 9 | 25
500059652 | CLB-MP-HAUL-DT185 -STRUCT-TRAYS | 789D Tray Wear, DT185 | 25 | 25 | 25
500059651 | CLB-MP-HAUL-DT184 -STRUCT-TRAYS | 789D Tray Wear, DT184 | 9 | 9 | 25
500059650 | CLB-MP-HAUL-DT183 -STRUCT-TRAYS | 789D Tray Wear, DT183 | 12 | 12 | 25
500059649 | CLB-MP-HAUL-DT182 -STRUCT-TRAYS | 789D Tray Wear, DT182 | 20 | 20 | 25
500059647 | CLB-MP-HAUL-DT180 -STRUCT-TRAYS | 789D Tray Wear, DT180 | 27 | 27 | 25
500059645 | CLB-MP-HAUL-DT178 -STRUCT-TRAYS | 789D Tray Wear, DT178 | 14 | 14 | 25
500059642 | CLB-MP-HAUL-DT175 -STRUCT-TRAYS | 789D Tray Wear, DT175 | 9 | 9 | 25
500059640 | CLB-MP-HAUL-DT173 -STRUCT-TRAYS | 789D Tray Wear, DT173 | 15 | 15 | 25
500059639 | CLB-MP-HAUL-DT172 -STRUCT-TRAYS | 789D Tray Wear, DT172 | 21 | 21 | 25
500059638 | CLB-MP-HAUL-DT171 -STRUCT-TRAYS | 789D Tray Wear, DT171 | 9 | 9 | 25
500059637 | CLB-MP-HAUL-DT170 -STRUCT-TRAYS | 789D Tray Wear, DT170 | 0 | 0 | 25
500059636 | CLB-MP-HAUL-DT169 -STRUCT-TRAYS | 789D Tray Wear, DT169 | 10 | 10 | 25
500059635 | CLB-MP-HAUL-DT168 -STRUCT-TRAYS | 789D Tray Wear, DT168 | 4 | 4 | 25
500059633 | CLB-MP-HAUL-DT166 -STRUCT-TRAYS | 789D Tray Wear, DT166 | 12 | 12 | 25
500059632 | CLB-MP-HAUL-DT165 -STRUCT-TRAYS | 789D Tray Wear, DT165 | 13 | 13 | 25
500059630 | CLB-MP-HAUL-DT163 -STRUCT-TRAYS | 789D Tray Wear, DT163 | 7 | 7 | 25
500061369 | RED-CB-MP-HAUL-DT200 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15755 | 15755 | 7200
500061352 | RED-CB-MP-HAUL-DT199 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15609 | 15609 | 7200
500061335 | RED-CB-MP-HAUL-DT198 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15330 | 15330 | 7200
500062750 | RED-CB-MP-HAUL-DT197 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 14090 | 14090 | 7200
500062731 | RED-CB-MP-HAUL-DT196 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 13237 | 13237 | 7200
500061318 | RED-CB-MP-HAUL-DT195 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15846 | 15846 | 7200
500061301 | RED-CB-MP-HAUL-DT194 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16250 | 16250 | 7200
500062712 | RED-CB-MP-HAUL-DT193 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15852 | 15852 | 7200
500061284 | RED-CB-MP-HAUL-DT192 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17125 | 17125 | 7200
500061267 | RED-CB-MP-HAUL-DT191 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16587 | 16587 | 7200
500061250 | RED-CB-MP-HAUL-DT190 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16352 | 16352 | 7200
500062693 | RED-CB-MP-HAUL-DT189 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15907 | 15907 | 7200
500061233 | RED-CB-MP-HAUL-DT188 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16286 | 16286 | 7200
500061216 | RED-CB-MP-HAUL-DT187 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16878 | 16878 | 7200
500061199 | RED-CB-MP-HAUL-DT186 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16655 | 16655 | 7200
500061182 | RED-CB-MP-HAUL-DT185 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17245 | 17245 | 7200
500061165 | RED-CB-MP-HAUL-DT184 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17319 | 17319 | 7200
500062674 | RED-CB-MP-HAUL-DT183 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16200 | 16200 | 7200
500061148 | RED-CB-MP-HAUL-DT182 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17569 | 17569 | 7200
500062655 | RED-CB-MP-HAUL-DT181 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15778 | 15778 | 7200
500061131 | RED-CB-MP-HAUL-DT180 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16229 | 16229 | 7200
500061114 | RED-CB-MP-HAUL-DT179 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17119 | 17119 | 7200
500061097 | RED-CB-MP-HAUL-DT178 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15679 | 15679 | 7200
500061080 | RED-CB-MP-HAUL-DT177 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17990 | 17990 | 7200
500062636 | RED-CB-MP-HAUL-DT176 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16583 | 16583 | 7200
500062617 | RED-CB-MP-HAUL-DT175 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 16418 | 16418 | 7200
500061063 | RED-CB-MP-HAUL-DT174 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 18076 | 18076 | 7200
500061046 | RED-CB-MP-HAUL-DT173 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17251 | 17251 | 7200
500061029 | RED-CB-MP-HAUL-DT172 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17250 | 17250 | 7200
500061012 | RED-CB-MP-HAUL-DT171 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17701 | 17701 | 7200
500060995 | RED-CB-MP-HAUL-DT170 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 18018 | 18018 | 7200
500060978 | RED-CB-MP-HAUL-DT169 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17980 | 17980 | 7200
500060961 | RED-CB-MP-HAUL-DT168 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17303 | 17303 | 7200
500060944 | RED-CB-MP-HAUL-DT167 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15021 | 15021 | 7200
500060927 | RED-CB-MP-HAUL-DT166 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17298 | 17298 | 7200
500060910 | RED-CB-MP-HAUL-DT165 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17478 | 17478 | 7200
500060893 | RED-CB-MP-HAUL-DT164 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 17858 | 17858 | 7200
500060870 | RED-CB-MP-HAUL-DT163 -HYDSYS-AUXDS | AUX Pump Drive Shaft | 15874 | 15874 | 7200
500057162 | RED-CC-MP-LOAD-WL265 | WL265 Lube & Mechanical Services | 8063 | 8063 | 6570
500057161 | RED-CC-MP-LOAD-WL265 | Caterpillar 994H Wheel Loader WL265 | 8064 | 8064 | 6570
500052525 | RED-CB-MP-HAUL-DT200 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7259 | 7259 | 7200
500052524 | RED-CB-MP-HAUL-DT200 -STRUCT-TRAYS-TYLIN | Tray Liners | 7259 | 7259 | 7200
500052417 | RED-CB-MP-HAUL-DT199 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7283 | 7283 | 7200
500052416 | RED-CB-MP-HAUL-DT199 -STRUCT-TRAYS-TYLIN | Tray Liners | 7283 | 7283 | 7200
500052309 | RED-CB-MP-HAUL-DT198 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7105 | 7105 | 7200
500052308 | RED-CB-MP-HAUL-DT198 -STRUCT-TRAYS-TYLIN | Tray Liners | 7105 | 7105 | 7200
500052201 | RED-CB-MP-HAUL-DT197 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7099 | 7099 | 7200
500052200 | RED-CB-MP-HAUL-DT197 -STRUCT-TRAYS-TYLIN | Tray Liners | 7099 | 7099 | 7200
500052093 | RED-CB-MP-HAUL-DT196 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7431 | 7431 | 7200
500052092 | RED-CB-MP-HAUL-DT196 -STRUCT-TRAYS-TYLIN | Tray Liners | 7431 | 7431 | 7200
500051985 | RED-CB-MP-HAUL-DT195 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7515 | 7515 | 7200
500051984 | RED-CB-MP-HAUL-DT195 -STRUCT-TRAYS-TYLIN | Tray Liners | 7515 | 7515 | 7200
500051877 | RED-CB-MP-HAUL-DT194 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7640 | 7640 | 7200
500051876 | RED-CB-MP-HAUL-DT194 -STRUCT-TRAYS-TYLIN | Tray Liners | 7640 | 7640 | 7200
500051769 | RED-CB-MP-HAUL-DT193 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8303 | 8303 | 7200
500051768 | RED-CB-MP-HAUL-DT193 -STRUCT-TRAYS-TYLIN | Tray Liners | 8303 | 8303 | 7200
500051661 | RED-CB-MP-HAUL-DT192 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8587 | 8587 | 7200
500051660 | RED-CB-MP-HAUL-DT192 -STRUCT-TRAYS-TYLIN | Tray Liners | 8587 | 8587 | 7200
500051553 | RED-CB-MP-HAUL-DT191 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7963 | 7963 | 7200
500051552 | RED-CB-MP-HAUL-DT191 -STRUCT-TRAYS-TYLIN | Tray Liners | 7963 | 7963 | 7200
500051445 | RED-CB-MP-HAUL-DT190 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8207 | 8207 | 7200
500051444 | RED-CB-MP-HAUL-DT190 -STRUCT-TRAYS-TYLIN | Tray Liners | 8207 | 8207 | 7200
500051337 | RED-CB-MP-HAUL-DT189 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8174 | 8174 | 7200
500051336 | RED-CB-MP-HAUL-DT189 -STRUCT-TRAYS-TYLIN | Tray Liners | 8174 | 8174 | 7200
500051229 | RED-CB-MP-HAUL-DT188 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8618 | 8618 | 7200
500051228 | RED-CB-MP-HAUL-DT188 -STRUCT-TRAYS-TYLIN | Tray Liners | 8618 | 8618 | 7200
500051121 | RED-CB-MP-HAUL-DT187 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8474 | 8474 | 7200
500051120 | RED-CB-MP-HAUL-DT187 -STRUCT-TRAYS-TYLIN | Tray Liners | 8474 | 8474 | 7200
500051013 | RED-CB-MP-HAUL-DT186 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9014 | 9014 | 7200
500051012 | RED-CB-MP-HAUL-DT186 -STRUCT-TRAYS-TYLIN | Tray Liners | 9014 | 9014 | 7200
500050905 | RED-CB-MP-HAUL-DT185 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9080 | 9080 | 7200
500050904 | RED-CB-MP-HAUL-DT185 -STRUCT-TRAYS-TYLIN | Tray Liners | 9080 | 9080 | 7200
500050797 | RED-CB-MP-HAUL-DT184 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8956 | 8956 | 7200
500050796 | RED-CB-MP-HAUL-DT184 -STRUCT-TRAYS-TYLIN | Tray Liners | 8956 | 8956 | 7200
500050689 | RED-CB-MP-HAUL-DT183 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8984 | 8984 | 7200
500050688 | RED-CB-MP-HAUL-DT183 -STRUCT-TRAYS-TYLIN | Tray Liners | 8984 | 8984 | 7200
500050581 | RED-CB-MP-HAUL-DT182 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8969 | 8969 | 7200
500050580 | RED-CB-MP-HAUL-DT182 -STRUCT-TRAYS-TYLIN | Tray Liners | 8969 | 8969 | 7200
500050472 | RED-CB-MP-HAUL-DT181 -STRUCT-TRAYS-TYLIN | Tray Liners | 8072 | 8072 | 7200
500050473 | RED-CB-MP-HAUL-DT181 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8067 | 8067 | 7200
500050365 | RED-CB-MP-HAUL-DT180 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8084 | 8084 | 7200
500050364 | RED-CB-MP-HAUL-DT180 -STRUCT-TRAYS-TYLIN | Tray Liners | 8084 | 8084 | 7200
500050257 | RED-CB-MP-HAUL-DT179 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9213 | 9213 | 7200
500050256 | RED-CB-MP-HAUL-DT179 -STRUCT-TRAYS-TYLIN | Tray Liners | 9213 | 9213 | 7200
500050149 | RED-CB-MP-HAUL-DT178 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9141 | 9141 | 7200
500050148 | RED-CB-MP-HAUL-DT178 -STRUCT-TRAYS-TYLIN | Tray Liners | 9141 | 9141 | 7200
500050041 | RED-CB-MP-HAUL-DT177 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9421 | 9421 | 7200
500049933 | RED-CB-MP-HAUL-DT176 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9373 | 9373 | 7200
500049932 | RED-CB-MP-HAUL-DT176 -STRUCT-TRAYS-TYLIN | Tray Liners | 9373 | 9373 | 7200
500048670 | RED-CB-MP-HAUL-DT175 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9401 | 9401 | 7200
500048669 | RED-CB-MP-HAUL-DT175 -STRUCT-TRAYS-TYLIN | Tray Liners | 9401 | 9401 | 7200
500048559 | RED-CB-MP-HAUL-DT174 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9908 | 9908 | 7200
500048558 | RED-CB-MP-HAUL-DT174 -STRUCT-TRAYS-TYLIN | Tray Liners | 9908 | 9908 | 7200
500049825 | RED-CB-MP-HAUL-DT173 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9682 | 9682 | 7200
500049824 | RED-CB-MP-HAUL-DT173 -STRUCT-TRAYS-TYLIN | Tray Liners | 9682 | 9682 | 7200
500049721 | RED-CB-MP-HAUL-DT172 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 8860 | 8860 | 7200
500049720 | RED-CB-MP-HAUL-DT172 -STRUCT-TRAYS-TYLIN | Tray Liners | 8860 | 8860 | 7200
500049617 | RED-CB-MP-HAUL-DT171 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9856 | 9856 | 7200
500049616 | RED-CB-MP-HAUL-DT171 -STRUCT-TRAYS-TYLIN | Tray Liners | 9856 | 9856 | 7200
500049513 | RED-CB-MP-HAUL-DT170 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 10217 | 10217 | 7200
500049512 | RED-CB-MP-HAUL-DT170 -STRUCT-TRAYS-TYLIN | Tray Liners | 10217 | 10217 | 7200
500049409 | RED-CB-MP-HAUL-DT169 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 10064 | 10064 | 7200
500049408 | RED-CB-MP-HAUL-DT169 -STRUCT-TRAYS-TYLIN | Tray Liners | 10064 | 10064 | 7200
500049305 | RED-CB-MP-HAUL-DT168 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9883 | 9883 | 7200
500049304 | RED-CB-MP-HAUL-DT168 -STRUCT-TRAYS-TYLIN | Tray Liners | 9883 | 9883 | 7200
500049201 | RED-CB-MP-HAUL-DT167 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 10258 | 10258 | 7200
500049200 | RED-CB-MP-HAUL-DT167 -STRUCT-TRAYS-TYLIN | Tray Liners | 10258 | 10258 | 7200
500049097 | RED-CB-MP-HAUL-DT166 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9894 | 9894 | 7200
500049096 | RED-CB-MP-HAUL-DT166 -STRUCT-TRAYS-TYLIN | Tray Liners | 9894 | 9894 | 7200
500048993 | RED-CB-MP-HAUL-DT165 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9988 | 9988 | 7200
500048992 | RED-CB-MP-HAUL-DT165 -STRUCT-TRAYS-TYLIN | Tray Liners | 9988 | 9988 | 7200
500048889 | RED-CB-MP-HAUL-DT164 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 9867 | 9867 | 7200
500048888 | RED-CB-MP-HAUL-DT164 -STRUCT-TRAYS-TYLIN | Tray Liners | 9867 | 9867 | 7200
500048785 | RED-CB-MP-HAUL-DT163 -STRUCT-TRAYS-TRELM | Tray Wear Elements | 7870 | 7870 | 7200
500048784 | RED-CB-MP-HAUL-DT163 -STRUCT-TRAYS-TYLIN | Tray Liners | 7870 | 7870 | 7200
500043117 | RED-CB-MP-EXCV-EX109 -STRUCT-BUCKT-BUGET | Bucket Wear Elements-GET | 9699 | 9699 | 7100
500042966 | RED-CB-MP-EXCV-EX108 -STRUCT-BUCKT-BUGET | Bucket Wear Elements-GET | 10298 | 10298 | 7100
500042815 | RED-CB-MP-EXCV-EX107 -STRUCT-BUCKT-BUGET | Bucket Wear Elements-GET | 11413 | 11413 | 7100
500046258 | RED-CB-MP-EXCV-EX011 -STRUCT-BUCKT-BUGET | Bucket Wear Elements (GET) | 8415 | 8415 | 6500
500046207 | RED-CB-MP-EXCV-EX011 -HYDSYS-HYDPP-SWPP3 | Pump Swing Position 3 | 7035 | 7035 | 6500
500046206 | RED-CB-MP-EXCV-EX011 -HYDSYS-HYDPP-SWPP2 | Pump Swing Position 2 | 7035 | 7035 | 6500